## Read Me
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization (Revision 2 Audited)
Author & Lead Architect: OLIVER TUNGOL ¦ Date: September 28, 2026 ¦ Comclark Network & Technology Corp. / TelTech
Overview | This Revision 2 workbook integrates Codex's independent spatial audit of Converge ICT's optical backbone (2,405 nodes & 4,401 fiber lines from the November 2024 KMZ).
Audited Fiber Screening | Every site is categorized into Classes A through F based on verified node candidates (1,296 points) and screened cable routes:
Class A | Node <= 0.5 km: Direct drop connection candidate. First survey priority.
Class B | Node > 0.5 km and <= 1.0 km: Short node lateral candidate.
Class C | Line <= 0.5 km; Node > 1.0 km: Splice closure / line-tap workstream candidate.
Class D | Other node or line <= 3.0 km: Route options evaluation (lateral vs line-tap).
Class E | Nearest node or line > 3.0 km and <= 5.0 km: Intermediate review candidate.
Class F | Nearest node and line > 5.0 km: Prime Starlink LEO satellite backhaul candidate.
BTS Radio Model | Standardized on Band n50 (1.5 GHz, 100 MHz TDD) with 3-Sector 8T8R MIMO AAUs / RRUs + Distributed BBU, sized @ 1,000 subscribers per BTS.
Standard Edition | Fixed baseline values for auditing and regulatory distribution.

## Executive Summary
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization (Executive Summary)
Revision 2 Audited Fiber Engineering & Siting Statistics
TOTAL SITES |  | BATCH 1 POPULATION |  | BATCH 1 TARGET SUBS |  | PROGRAM TARGET SUBS |  | PEAK BTS CAPACITY
5,000 |  | 9,100,900 |  | 761,219 |  | 2,453,270 |  | 6,139
1,000 per Batch (5 Batches) |  | Phase 1 Direct Reach |  | @ 30% Market Take-Rate |  | Across Full 5,000 Sites |  | @ 1,000 Subs / 8T8R BTS
PHASE-BY-PHASE ROLLOUT & AUDITED TRANSMISSION PROFILE
Phase | Barangays | 2024 Population | 2024 Households | Subs @ 30% | Day 1 BTS | Peak BTS | Node <=1km (A+B) | Line <=500m (C) | Other <=3km (D) | Remote >3km (E+F)
Phase 1 (Batch 1) | 1000 | 9100900 | 2537442 | 761219 | 1000 | 1420 | 282 | 170 | 297 | 251
Phase 2 (Batch 2) | 1000 | 6178076 | 1696615 | 508968 | 1000 | 1236 | 187 | 131 | 253 | 429
Phase 3 (Batch 3) | 1000 | 5263116 | 1446389 | 433941 | 1000 | 1200 | 171 | 148 | 212 | 469
Phase 4 (Batch 4) | 2000 | 9298596 | 2497053 | 749142 | 2000 | 2283 | 298 | 324 | 521 | 857
Phase 5 (Batch 5) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL (5,000 SITES) | 5000 | 29840688 | 8177499 | 2453270 | 5000 | 6139 | 938 | 773 | 1283 | 2006

## Batch 1 (First 1,000)
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization — Batch 1 (First 1,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
1 | 1 | 1 | 1403213008 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao | 17.4077 | 121.4451 | U | 20300 | 4.3 | 4721 | 1416 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.64 | 0.55 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 73.95 | 73.95 | 81.51 | 77.73 | B - Node 0.5-1 km | 0.64 | 0.49 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 1
1 | 2 | 2 | 0102815010 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pancian | 18.5645 | 120.7878 | R | 2434 | 3.7 | 658 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 0.22 | Tier 1B: High GIDA Priority | 63.8 | 63.8 | 90.26 | 77.03 | C - Line within 0.5 km; node over 1 km | 3.67 | 0.22 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2
1 | 3 | 3 | 0307702019 | Region III (Central Luzon) | Aurora | Casiguran | Bianuan | 16.2056 | 122.0424 | R | 2790 | 3.8 | 734 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.2 | 0.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.8 | 66.8 | 86.82 | 76.81 | A - Node within 0.5 km | 0.2 | 999999 | Node: CSA002 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3
1 | 4 | 4 | 0403418006 | Region IV-A (CALABARZON) | Laguna | Paete | Ilaya del Norte | 14.3671 | 121.5212 | R | 2622 | 3.3 | 795 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 4.25 | Tier 1B: High GIDA Priority | 64.43 | 64.43 | 87.69 | 76.06 | E - Nearest node or line 3-5 km | 3.25 | 4.25 | Node: KYL002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4
1 | 5 | 5 | 0102815011 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pasaleng | 18.5487 | 120.9363 | R | 1820 | 3.7 | 492 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.24 | 63.24 | 87.34 | 75.29 | B - Node 0.5-1 km | 0.98 | 0.06 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 5
1 | 6 | 6 | 1401105003 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Amlimay | 16.7039 | 120.8306 | R | 2411 | 3.5 | 689 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 4.65 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.25 | 59.25 | 87.95 | 73.6 | D - Other node or line within 3 km | 1.78 | 4.54 | Node: BGB002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 6
1 | 7 | 7 | 0307704009 | Region III (Central Luzon) | Aurora | Dinalungan | Simbahan | 16.129 | 121.895 | R | 1295 | 3.8 | 341 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.07 | 0.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61 | 61 | 85.97 | 73.49 | A - Node within 0.5 km | 0.07 | 11.17 | Node: DNA001 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 7
1 | 8 | 8 | 0307104013 | Region III (Central Luzon) | Zambales | Castillejos | San Pablo | 14.9605 | 120.2527 | U | 11681 | 3.8 | 3074 | 922 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.53 | 5.32 | Tier 1B: High GIDA Priority | 59.79 | 59.79 | 87.12 | 73.45 | F - Nearest node and line over 5 km | 6.53 | 5.31 | Line: SUBIC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 8
1 | 9 | 9 | 1380900018 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tanza 2 | 14.6641 | 120.9647 | U | 16184 | 3.48 | 4652 | 1396 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.54 | 0.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.98 | 68.98 | 77.46 | 73.22 | B - Node 0.5-1 km | 0.54 | 0.43 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 9
1 | 10 | 10 | 0402104009 | Region IV-A (CALABARZON) | Cavite | Carmona | Mabuhay | 14.3103 | 121.0505 | U | 13384 | 3.4 | 3936 | 1181 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.08 | 0.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 73.4 | 73.4 | 72.27 | 72.83 | A - Node within 0.5 km | 0.08 | 0.09 | Node: CRC005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 10
1 | 11 | 11 | 0600406014 | Region VI (Western Visayas) | Aklan | Ibajay | Laguinbanua | 11.7081 | 122.3481 | R | 3333 | 3.9 | 855 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.13 | 66.13 | 78.93 | 72.53 | D - Other node or line within 3 km | 2.27 | 1.52 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 11
1 | 12 | 12 | 0201514006 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Cabiraoan | 18.3101 | 122.1093 | R | 3878 | 3.9 | 994 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.26 | 4.82 | Tier 1B: High GIDA Priority | 61.57 | 61.57 | 83.2 | 72.38 | E - Nearest node or line 3-5 km | 5.26 | 4.82 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 12
1 | 13 | 13 | 1380400005 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Concepcion | 14.6676 | 120.9496 | U | 13098 | 3.47 | 3771 | 1131 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.8 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.53 | 66.53 | 78.11 | 72.32 | B - Node 0.5-1 km | 0.8 | 0.31 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 13
1 | 14 | 14 | 0203131023 | Region II (Cagayan Valley) | Isabela | San Mariano | Minanga | 17.0004 | 122.0312 | R | 4830 | 3.8 | 1271 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.56 | 18.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65 | 65 | 79.58 | 72.29 | D - Other node or line within 3 km | 2.56 | 18.3 | Node: SOI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 14
1 | 15 | 15 | 0201511041 | Region II (Cagayan Valley) | Cagayan | Claveria | Taggat Sur | 18.6028 | 121.0582 | R | 2210 | 3.9 | 567 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.19 | 60.19 | 83.85 | 72.02 | C - Line within 0.5 km; node over 1 km | 1.27 | 0.08 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 15
1 | 16 | 16 | 0403403001 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Biñan | 14.3158 | 121.0769 | U | 7786 | 3.3 | 2359 | 708 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.93 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.74 | 65.74 | 78.15 | 71.94 | D - Other node or line within 3 km | 1.5 | 0.92 | Line: AE CRC005-BNL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 16
1 | 17 | 17 | 1380900012 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Roque | 14.6693 | 120.9378 | U | 20173 | 3.33 | 6061 | 1818 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.85 | 0.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.61 | 66.61 | 77.12 | 71.87 | B - Node 0.5-1 km | 0.85 | 0.85 | Node: MAL002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 17
1 | 18 | 18 | 0304904026 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Santa Ines | 15.2344 | 120.8566 | R | 2373 | 3.5 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 1 | Tier 1B: High GIDA Priority | 60.21 | 60.21 | 83.44 | 71.83 | D - Other node or line within 3 km | 3.32 | 1 | Line: SANTA ROSA TO ARAYAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 18
1 | 19 | 19 | 0403403004 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Canlalay | 14.3425 | 121.072 | U | 22311 | 3.3 | 6761 | 2028 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.59 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.26 | 70.26 | 72.77 | 71.51 | B - Node 0.5-1 km | 0.59 | 0.19 | Line: MUNTINLUPA - BINAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 19
1 | 20 | 20 | 0201516025 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Maxingal | 18.2119 | 121.6657 | R | 2741 | 3.9 | 703 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.89 | 62.89 | 80.08 | 71.48 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.06 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 20
1 | 21 | 21 | 0403403020 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Jose | 14.3458 | 121.0817 | U | 7234 | 3.3 | 2192 | 658 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.77 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.07 | 66.07 | 76.84 | 71.46 | D - Other node or line within 3 km | 1.03 | 0.77 | Line: BÑL001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 21
1 | 22 | 22 | 1380400018 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tañong | 14.6731 | 120.9644 | U | 14836 | 3.57 | 4159 | 1248 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.59 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.11 | 68.11 | 74.79 | 71.45 | B - Node 0.5-1 km | 0.59 | 0.52 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 22
1 | 23 | 23 | 0201516034 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Sta. Maria | 18.1829 | 121.6603 | R | 2451 | 3.9 | 628 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.54 | 61.54 | 81.25 | 71.4 | C - Line within 0.5 km; node over 1 km | 1.42 | 0.23 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 23
1 | 24 | 24 | 1102315029 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Francisco | 7.3033 | 125.6813 | U | 14187 | 3.7 | 3834 | 1150 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.32 | 0.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 73.7 | 73.7 | 68.81 | 71.25 | A - Node within 0.5 km | 0.32 | 0.1 | Line: DAVAO CITY - TRENTO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 24
1 | 25 | 25 | 0403403005 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Casile | 14.3426 | 121.0895 | R | 4648 | 3.3 | 1408 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.23 | 70.23 | 71.95 | 71.09 | D - Other node or line within 3 km | 1.55 | 0.57 | Line: RELIANCE TO SAN PABLO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 25
1 | 26 | 26 | 0403403016 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Poblacion | 14.32 | 121.067 | U | 5494 | 3.3 | 1665 | 500 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.54 | 64.54 | 77.59 | 71.06 | B - Node 0.5-1 km | 0.98 | 0.26 | Line: AE CRC005-BNL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 26
1 | 27 | 27 | 1380900005 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Daanghari | 14.6658 | 120.9405 | U | 14837 | 3.39 | 4377 | 1313 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.97 | 0.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.99 | 67.99 | 73.81 | 70.9 | B - Node 0.5-1 km | 0.97 | 0.8 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 27
1 | 28 | 28 | 0702232002 | Region VII (Central Visayas) | Cebu | Minglanilla | Calajo-an | 10.2397 | 123.8028 | U | 13251 | 3.8 | 3487 | 1046 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.97 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 72.21 | 72.21 | 69.57 | 70.89 | B - Node 0.5-1 km | 0.97 | 0.04 | Line: 96c | Survey short node lateral; confirm port/fiber capacity, access and route. | 28
1 | 29 | 29 | 1380400008 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Hulong Duhat | 14.6768 | 120.9412 | U | 12265 | 3.45 | 3559 | 1068 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.14 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.3 | 67.3 | 74.42 | 70.86 | A - Node within 0.5 km | 0.14 | 0.12 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 29
1 | 30 | 30 | 1400101010 | Cordillera Administrative Region (CAR) | Abra | Bangued | Dangdangla | 17.599 | 120.6287 | R | 2037 | 3.8 | 536 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.75 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.65 | 59.65 | 82.03 | 70.84 | D - Other node or line within 3 km | 1.23 | 0.75 | Line: Bangued | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 30
1 | 31 | 31 | 0403403023 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Domingo | 14.336 | 121.0809 | U | 6751 | 3.3 | 2046 | 614 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.41 | 66.41 | 75.26 | 70.83 | B - Node 0.5-1 km | 0.63 | 0.27 | Line: AE CRC005-BNL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 31
1 | 32 | 32 | 0402106069 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco II | 14.3505 | 121.0012 | R | 3540 | 3.4 | 1041 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.93 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.22 | 70.22 | 71.27 | 70.75 | B - Node 0.5-1 km | 0.92 | 4.05 | Node: MUN048 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 32
1 | 33 | 33 | 1705309032 | MIMAROPA Region | Palawan | Coron | Barangay VI | 12.0505 | 120.1531 | U | 5297 | 3.9 | 1358 | 407 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 104.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.19 | 61.19 | 79.98 | 70.59 | D - Other node or line within 3 km | 1.2 | 999999 | Node: CNW002-BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 33
1 | 34 | 34 | 1380900008 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | North Bay Boulevard North | 14.6497 | 120.9449 | U | 14782 | 3.51 | 4206 | 1262 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.73 | 1.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.97 | 67.97 | 73.09 | 70.53 | B - Node 0.5-1 km | 0.73 | 2.23 | Node: NAV001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 34
1 | 35 | 35 | 1381400002 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Balong-Bato | 14.6063 | 121.0224 | U | 7528 | 3.35 | 2247 | 674 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.89 | 60.89 | 79.59 | 70.24 | C - Line within 0.5 km; node over 1 km | 1.42 | 0.27 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 35
1 | 36 | 36 | 0102822013 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Manalpac | 18.0981 | 120.8115 | R | 2162 | 3.7 | 584 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 4.26 | Tier 1B: High GIDA Priority | 53.31 | 53.31 | 86.98 | 70.14 | E - Nearest node or line 3-5 km | 4.22 | 4.26 | Node: SSI001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 36
1 | 37 | 37 | 0402104019 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 8 | 14.3137 | 121.0538 | R | 3290 | 3.4 | 968 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.83 | 70.83 | 69.42 | 70.12 | B - Node 0.5-1 km | 0.51 | 0.19 | Line: AE CRC005-BNL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 37
1 | 38 | 38 | 0405811001 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid I | 14.6778 | 121.1168 | U | 26178 | 3.6 | 7272 | 2182 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.01 | 0.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.77 | 68.77 | 71.44 | 70.11 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.41 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 38
1 | 39 | 39 | 0500518020 | Region V (Bicol Region) | Albay | Tiwi | Misibis | 13.509 | 123.6092 | R | 2262 | 4.1 | 552 | 166 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.23 | 63.23 | 76.96 | 70.09 | A - Node within 0.5 km | 0.17 | 0.03 | Line: PILI - TIWI AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 39
1 | 40 | 40 | 0201514003 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Baua | 18.3495 | 122.0908 | R | 2350 | 3.9 | 603 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 0.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.85 | 60.85 | 79.34 | 70.09 | C - Line within 0.5 km; node over 1 km | 1.45 | 0.14 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 40
1 | 41 | 41 | 1380900010 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Jose | 14.6625 | 120.9438 | U | 24722 | 3.48 | 7105 | 2132 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.78 | 0.65 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.45 | 65.45 | 74.64 | 70.04 | B - Node 0.5-1 km | 0.78 | 0.86 | Node: NAV001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 41
1 | 42 | 42 | 1381300062 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Marilag | 14.6255 | 121.0696 | U | 17891 | 4.39 | 4080 | 1224 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.13 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.87 | 68.87 | 71.19 | 70.03 | A - Node within 0.5 km | 0.13 | 0.05 | Line: UG 144C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 42
1 | 43 | 43 | 0405801009 | Region IV-A (CALABARZON) | Rizal | Angono | San Isidro | 14.5295 | 121.1543 | U | 32767 | 3.6 | 9102 | 2731 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.23 | 0.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.98 | 67.98 | 72.08 | 70.03 | A - Node within 0.5 km | 0.23 | 0.02 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 43
1 | 44 | 44 | 1381600003 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Balangkas | 14.7114 | 120.9422 | U | 14658 | 3.75 | 3908 | 1172 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.64 | 1.74 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.27 | 67.27 | 72.75 | 70.01 | B - Node 0.5-1 km | 0.64 | 1.74 | Node: OBB001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 44
1 | 45 | 45 | 0405801005 | Region IV-A (CALABARZON) | Rizal | Angono | Kalayaan | 14.5297 | 121.1536 | U | 19309 | 3.6 | 5364 | 1609 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.27 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 72.75 | 72.75 | 67.22 | 69.99 | A - Node within 0.5 km | 0.27 | 0.05 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 45
1 | 46 | 46 | 0402118011 | Region IV-A (CALABARZON) | Cavite | Silang | Bulihan | 14.2802 | 120.9962 | U | 26302 | 3.4 | 7736 | 2321 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.68 | 3.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.31 | 65.31 | 74.67 | 69.99 | B - Node 0.5-1 km | 0.68 | 3.28 | Node: MAC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 46
1 | 47 | 47 | 0405805019 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Niño | 14.5863 | 121.1082 | U | 6105 | 3.6 | 1696 | 509 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.39 | 63.39 | 76.49 | 69.94 | C - Line within 0.5 km; node over 1 km | 1.68 | 0.18 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 47
1 | 48 | 48 | 0102814001 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Acnam | 17.9151 | 120.6557 | R | 779 | 3.7 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.93 | 51.93 | 87.87 | 69.9 | B - Node 0.5-1 km | 0.56 | 0.57 | Node: NEI001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 48
1 | 49 | 49 | 0405805017 | Region IV-A (CALABARZON) | Rizal | Cainta | San Roque | 14.5763 | 121.1173 | U | 9850 | 3.6 | 2736 | 821 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.72 | 67.72 | 71.89 | 69.81 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.04 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 49
1 | 50 | 50 | 1380300029 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Tejeros | 14.5668 | 121.0178 | U | 16019 | 3.44 | 4655 | 1396 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.93 | 0.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.2 | 68.2 | 71.37 | 69.79 | B - Node 0.5-1 km | 0.93 | 0.47 | Line: UG 288C via V-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 50
1 | 51 | 51 | 1380900001 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Sipac-Almacen | 14.6583 | 120.9483 | U | 9097 | 3.48 | 2616 | 785 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.13 | 64.13 | 75.4 | 69.77 | A - Node within 0.5 km | 0.31 | 1.28 | Node: NAV001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 51
1 | 52 | 52 | 0402118055 | Region IV-A (CALABARZON) | Cavite | Silang | Banaba | 14.1991 | 121.0021 | U | 6648 | 3.4 | 1955 | 586 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 1.81 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.16 | 64.16 | 75.23 | 69.69 | D - Other node or line within 3 km | 1.7 | 1.81 | Node: SGC004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 52
1 | 53 | 53 | 0201514002 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Batangan | 18.2825 | 122.0027 | R | 2268 | 3.9 | 582 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 0.77 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.18 | 59.18 | 80.13 | 69.66 | D - Other node or line within 3 km | 2.16 | 0.77 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 53
1 | 54 | 54 | 0201514008 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Calayan | 18.282 | 122.0101 | R | 2054 | 3.9 | 527 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.38 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.34 | 57.34 | 81.94 | 69.64 | C - Line within 0.5 km; node over 1 km | 2.38 | 0.08 | Line: SANTA ANA - GONZAGA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 54
1 | 55 | 55 | 1380400003 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Bayan-bayanan | 14.6648 | 120.9615 | U | 6708 | 3.75 | 1790 | 537 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.52 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.86 | 60.86 | 78.33 | 69.59 | B - Node 0.5-1 km | 0.71 | 0.44 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 55
1 | 56 | 56 | 0102810004 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Quibel | 18.5245 | 120.8096 | R | 984 | 3.7 | 266 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.55 | 1.73 | Tier 1B: High GIDA Priority | 52.5 | 52.5 | 86.63 | 69.56 | D - Other node or line within 3 km | 4.55 | 1.72 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 56
1 | 57 | 57 | 0201528010 | Region II (Cagayan Valley) | Cagayan | Tuao | Bulagao | 17.6868 | 121.491 | R | 3867 | 3.9 | 992 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 5.63 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.78 | 63.78 | 75.33 | 69.55 | D - Other node or line within 3 km | 2.85 | 5.49 | Node: TUC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 57
1 | 58 | 58 | 1380400002 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Baritan | 14.6717 | 120.9493 | U | 12461 | 3.23 | 3857 | 1157 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.49 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.42 | 67.42 | 71.66 | 69.54 | A - Node within 0.5 km | 0.49 | 0.14 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 58
1 | 59 | 59 | 1380400007 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Flores | 14.669 | 120.9516 | U | 3977 | 3.55 | 1119 | 336 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.59 | 58.59 | 80.47 | 69.53 | B - Node 0.5-1 km | 0.86 | 0.21 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 59
1 | 60 | 60 | 1381300070 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Novaliches Proper | 14.7186 | 121.035 | U | 16096 | 3.99 | 4038 | 1211 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.83 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.27 | 67.27 | 71.77 | 69.52 | B - Node 0.5-1 km | 0.83 | 0.35 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 60
1 | 61 | 61 | 0405811012 | Region IV-A (CALABARZON) | Rizal | San Mateo | Banaba | 14.6726 | 121.1128 | U | 26718 | 3.6 | 7422 | 2227 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.62 | 0.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.49 | 67.49 | 71.43 | 69.46 | C - Line within 0.5 km; node over 1 km | 1.62 | 0.41 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 61
1 | 62 | 62 | 1401113001 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Ansagan | 16.2119 | 120.5984 | R | 2370 | 3.5 | 677 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.04 | 9.02 | Tier 1B: High GIDA Priority | 50.39 | 50.39 | 88.51 | 69.45 | F - Nearest node and line over 5 km | 11.04 | 9.02 | Line: POZORRUBIO - ROSARIO PANGASINAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 62
1 | 63 | 63 | 0500518001 | Region V (Bicol Region) | Albay | Tiwi | Bagumbayan | 13.4525 | 123.6619 | R | 2758 | 4.1 | 673 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 1.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.16 | 63.16 | 75.72 | 69.44 | D - Other node or line within 3 km | 1.59 | 1.24 | Line: EE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 63
1 | 64 | 64 | 1380500024 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Poblacion | 14.5865 | 121.0249 | U | 16407 | 3.47 | 4734 | 1420 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.47 | 0.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 69.03 | 69.03 | 69.58 | 69.31 | A - Node within 0.5 km | 0.47 | 0.38 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 64
1 | 65 | 65 | 0403403019 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Antonio | 14.3364 | 121.0882 | U | 39641 | 3.3 | 12012 | 3604 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.36 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.97 | 61.97 | 76.63 | 69.3 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.4 | Line: RELIANCE TO SAN PABLO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 65
1 | 66 | 66 | 1381200026 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santo Tomas | 14.5697 | 121.0742 | U | 13989 | 3.86 | 3625 | 1088 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.88 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.95 | 65.95 | 72.49 | 69.22 | B - Node 0.5-1 km | 0.88 | 0.33 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 66
1 | 67 | 67 | 1381600016 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Malanday | 14.717 | 120.9556 | U | 19344 | 3.72 | 5202 | 1561 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.03 | 0.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.32 | 67.32 | 71.04 | 69.18 | C - Line within 0.5 km; node over 1 km | 1.03 | 0.18 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 67
1 | 68 | 68 | 0403416007 | Region IV-A (CALABARZON) | Laguna | Majayjay | Banilad | 14.1393 | 121.4756 | R | 224 | 3.3 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.62 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.69 | 53.69 | 84.63 | 69.16 | B - Node 0.5-1 km | 0.72 | 0.61 | Line: SPO001 TO LBQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 68
1 | 69 | 69 | 1380300001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Bangkal | 14.5428 | 121.0083 | U | 18013 | 3.04 | 5929 | 1779 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.84 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.78 | 66.78 | 71.46 | 69.12 | B - Node 0.5-1 km | 0.84 | 0.5 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 69
1 | 70 | 70 | 1401107003 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Ballay | 16.6789 | 120.8366 | R | 3093 | 3.5 | 884 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.63 | 6.46 | Tier 1B: High GIDA Priority | 65.51 | 65.51 | 72.73 | 69.12 | E - Nearest node or line 3-5 km | 4.63 | 6.43 | Node: BGB002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 70
1 | 71 | 71 | 0402106028 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Esteban | 14.2972 | 120.9503 | R | 4825 | 3.4 | 1419 | 426 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 71.3 | 71.3 | 66.81 | 69.06 | B - Node 0.5-1 km | 0.97 | 0.4 | Line: NCC001 TO TGY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 71
1 | 72 | 72 | 1381400003 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Batis | 14.6049 | 121.0232 | U | 7938 | 3.62 | 2194 | 658 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 0.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.43 | 60.43 | 77.7 | 69.06 | C - Line within 0.5 km; node over 1 km | 1.6 | 0.43 | Line: UG 288C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 72
1 | 73 | 73 | 0401001007 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Barigon | 14.0001 | 120.9138 | R | 1877 | 3.6 | 521 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.29 | 9.79 | Tier 1B: High GIDA Priority | 54.72 | 54.72 | 83.41 | 69.06 | F - Nearest node and line over 5 km | 6.29 | 9.79 | Node: LRB002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 73
1 | 74 | 74 | 0405811006 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan II | 14.685 | 121.1271 | U | 18821 | 3.6 | 5228 | 1568 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.19 | 0.75 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 71.09 | 71.09 | 67 | 69.04 | D - Other node or line within 3 km | 1.19 | 0.59 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 74
1 | 75 | 75 | 0405804002 | Region IV-A (CALABARZON) | Rizal | Binangonan | Batingan | 14.4726 | 121.1968 | U | 15585 | 3.6 | 4329 | 1299 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.5 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 73.6 | 73.6 | 64.46 | 69.03 | B - Node 0.5-1 km | 0.5 | 0.04 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 75
1 | 76 | 76 | 1404405004 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Banawal | 17.1114 | 121.2952 | R | 2176 | 3.7 | 588 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 22.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.25 | 61.25 | 76.81 | 69.03 | D - Other node or line within 3 km | 1.64 | 22.49 | Node: NNV001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 76
1 | 77 | 77 | 1381600012 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Isla | 14.7063 | 120.9504 | U | 5161 | 3.67 | 1405 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 1.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.07 | 59.07 | 78.95 | 69.01 | D - Other node or line within 3 km | 1.05 | 1.05 | Line: Existing 24F | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 77
1 | 78 | 78 | 0600413005 | Region VI (Western Visayas) | Aklan | Malinao | Capataga | 11.6275 | 122.2973 | R | 55 | 3.9 | 14 | 4 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 4.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.56 | 54.56 | 83.4 | 68.98 | B - Node 0.5-1 km | 0.52 | 4.28 | Node: MLK001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 78
1 | 79 | 79 | 0102818011 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Estancia | 18.1589 | 120.7616 | R | 1853 | 3.7 | 501 | 150 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.95 | 3.77 | Tier 1B: High GIDA Priority | 50.49 | 50.49 | 87.46 | 68.98 | E - Nearest node or line 3-5 km | 4.95 | 3.77 | Line: SEGMENT 1 PIDDIG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 79
1 | 80 | 80 | 0201517002 | Region II (Cagayan Valley) | Cagayan | Lasam | Alannay | 18.0602 | 121.5678 | R | 2212 | 3.9 | 567 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.21 | 6.93 | Tier 1B: High GIDA Priority | 52.86 | 52.86 | 85.05 | 68.96 | E - Nearest node or line 3-5 km | 4.21 | 6.93 | Node: LSC001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 80
1 | 81 | 81 | 1401113009 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Tabaan Norte | 16.3366 | 120.5093 | R | 1327 | 3.5 | 379 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.4 | 1.42 | Tier 1B: High GIDA Priority | 52.45 | 52.45 | 85.42 | 68.94 | D - Other node or line within 3 km | 3.4 | 1.39 | Line: TUBA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 81
1 | 82 | 82 | 1380400016 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | San Agustin | 14.6622 | 120.9525 | U | 10993 | 3.54 | 3104 | 931 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.15 | 65.15 | 72.63 | 68.89 | B - Node 0.5-1 km | 0.51 | 0.96 | Node: MAL004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 82
1 | 83 | 83 | 1380200019 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Kuatro | 14.435 | 121.0036 | U | 17656 | 3.64 | 4845 | 1454 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.37 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 69.09 | 69.09 | 68.61 | 68.85 | A - Node within 0.5 km | 0.37 | 0.35 | Line: UG 144C via B-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 83
1 | 84 | 84 | 0403425027 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 2 | 14.1212 | 121.4308 | U | 13146 | 3.3 | 3984 | 1195 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.77 | 1.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.28 | 70.28 | 67.31 | 68.8 | D - Other node or line within 3 km | 1.77 | 1.23 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 84
1 | 85 | 85 | 1381200001 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bagong Ilog | 14.5637 | 121.0713 | U | 21909 | 3.58 | 6119 | 1836 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.11 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.03 | 66.03 | 71.56 | 68.8 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.16 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 85
1 | 86 | 86 | 1381300107 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Teresita | 14.7276 | 121.0248 | U | 17838 | 4.18 | 4270 | 1281 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.55 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.64 | 66.64 | 70.9 | 68.77 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.11 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 86
1 | 87 | 87 | 0300807008 | Region III (Central Luzon) | Bataan | Mariveles | Poblacion | 14.4361 | 120.4841 | U | 8835 | 3.6 | 2454 | 736 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.56 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.09 | 66.09 | 71.42 | 68.76 | C - Line within 0.5 km; node over 1 km | 1.56 | 0.29 | Line: 24 CORE 3X8 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 87
1 | 88 | 88 | 1381600024 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pasolo | 14.7054 | 120.9543 | U | 8190 | 4 | 2047 | 614 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.69 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.66 | 61.66 | 75.85 | 68.75 | B - Node 0.5-1 km | 0.7 | 0.69 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 88
1 | 89 | 89 | 0402106035 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Mateo | 14.3341 | 120.9401 | R | 5211 | 3.4 | 1533 | 460 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 3.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.65 | 66.65 | 70.67 | 68.66 | D - Other node or line within 3 km | 1.83 | 3.82 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 89
1 | 90 | 90 | 0102817011 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Dilavo | 18.4314 | 120.5882 | R | 651 | 3.7 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.17 | 0.07 | Tier 1B: High GIDA Priority | 46.9 | 46.9 | 90.35 | 68.63 | C - Line within 0.5 km; node over 1 km | 3.17 | 0.06 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 90
1 | 91 | 91 | 0402103014 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino I | 14.2769 | 120.9201 | U | 17504 | 3.4 | 5148 | 1544 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.21 | 1.71 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 69.54 | 69.54 | 67.67 | 68.61 | D - Other node or line within 3 km | 2.21 | 1.7 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 91
1 | 92 | 92 | 1381400008 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Kabayanan | 14.5987 | 121.0323 | U | 6258 | 3.52 | 1778 | 533 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.91 | 59.91 | 77.31 | 68.61 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.38 | Line: UG 288C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 92
1 | 93 | 93 | 1380300015 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Palanan | 14.5606 | 121.0015 | U | 11934 | 3.2 | 3735 | 1120 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.33 | 0.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.44 | 65.44 | 71.52 | 68.48 | C - Line within 0.5 km; node over 1 km | 1.33 | 0.49 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 93
1 | 94 | 94 | 0300808004 | Region III (Central Luzon) | Bataan | Morong | Poblacion | 14.6777 | 120.268 | U | 7656 | 3.6 | 2127 | 638 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 0.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.28 | 67.28 | 69.66 | 68.47 | A - Node within 0.5 km | 0.41 | 0.23 | Line: Subic-Bagac AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 94
1 | 95 | 95 | 1381200004 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Buting | 14.5555 | 121.066 | U | 10698 | 3.48 | 3075 | 922 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.66 | 63.66 | 73.26 | 68.46 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.11 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 95
1 | 96 | 96 | 0102810003 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Kalaw | 18.5231 | 120.8064 | R | 654 | 3.7 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.28 | 1.51 | Tier 1B: High GIDA Priority | 50.29 | 50.29 | 86.63 | 68.46 | D - Other node or line within 3 km | 4.28 | 1.5 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 96
1 | 97 | 97 | 0402106022 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima I | 14.3083 | 120.9485 | U | 7140 | 3.4 | 2100 | 630 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.91 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.06 | 65.06 | 71.78 | 68.42 | D - Other node or line within 3 km | 1.43 | 0.87 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 97
1 | 98 | 98 | 0501609006 | Region V (Bicol Region) | Camarines Norte | San Vicente | Man-Ogob | 14.1014 | 122.8721 | R | 3172 | 4 | 793 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.98 | 4.8 | Tier 1B: High GIDA Priority | 62.06 | 62.06 | 74.75 | 68.41 | E - Nearest node or line 3-5 km | 6.98 | 4.8 | Line: PAGBILAO - NAGA (UG + Aerial) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 98
1 | 99 | 99 | 0405805020 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Domingo | 14.5833 | 121.1112 | U | 45228 | 3.6 | 12563 | 3769 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.32 | 0.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.32 | 61.32 | 75.47 | 68.4 | C - Line within 0.5 km; node over 1 km | 1.32 | 0.42 | Line: PSG001 TO TAYTAY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 99
1 | 100 | 100 | 1381400013 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Pedro Cruz | 14.6055 | 121.0262 | U | 4971 | 3.46 | 1435 | 430 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.98 | 57.98 | 78.83 | 68.4 | C - Line within 0.5 km; node over 1 km | 1.72 | 0.17 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 100
1 | 101 | 101 | 0203130017 | Region II (Cagayan Valley) | Isabela | San Manuel | Sandiat East | 17.0721 | 121.6412 | R | 1434 | 3.8 | 377 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.95 | 1.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.05 | 57.05 | 79.76 | 68.4 | D - Other node or line within 3 km | 2.95 | 1.83 | Line: ROXAS - CABATUAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 101
1 | 102 | 102 | 0402106073 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel II | 14.2827 | 120.9092 | R | 2717 | 3.4 | 799 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.28 | 1.02 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.45 | 66.45 | 70.33 | 68.39 | D - Other node or line within 3 km | 1.28 | 1.03 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 102
1 | 103 | 103 | 1380300014 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Olympia | 14.5729 | 121.0218 | U | 19035 | 3.83 | 4971 | 1491 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.03 | 0.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.62 | 67.62 | 68.88 | 68.25 | C - Line within 0.5 km; node over 1 km | 1.03 | 0.09 | Line: UG 288C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 103
1 | 104 | 104 | 0403418007 | Region IV-A (CALABARZON) | Laguna | Paete | Ilaya del Sur | 14.3561 | 121.5072 | R | 1722 | 3.3 | 522 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.79 | 2.45 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.61 | 57.61 | 78.89 | 68.25 | D - Other node or line within 3 km | 2.79 | 2.45 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 104
1 | 105 | 105 | 1380900007 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Navotas West | 14.6632 | 120.9527 | U | 6293 | 3.52 | 1788 | 536 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.17 | 61.17 | 75.23 | 68.2 | B - Node 0.5-1 km | 0.56 | 0.86 | Node: MAL004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 105
1 | 106 | 106 | 0600413015 | Region VI (Western Visayas) | Aklan | Malinao | Poblacion | 11.643 | 122.309 | R | 1665 | 3.9 | 427 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 2.84 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.11 | 57.11 | 79.26 | 68.18 | D - Other node or line within 3 km | 2.6 | 2.84 | Node: MLK001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 106
1 | 107 | 107 | 0702232009 | Region VII (Central Visayas) | Cebu | Minglanilla | Pakigne | 10.2591 | 123.7922 | U | 14675 | 3.8 | 3862 | 1159 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.51 | 1.58 | Tier 1B: High GIDA Priority | 72.2 | 72.2 | 64.11 | 68.15 | D - Other node or line within 3 km | 1.51 | 1.57 | Node: MLL001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 107
1 | 108 | 108 | 0402123024 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Gabriel | 14.2826 | 121.0011 | U | 9168 | 3.4 | 2696 | 809 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.11 | 3.89 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.02 | 66.02 | 70.27 | 68.15 | A - Node within 0.5 km | 0.11 | 3.87 | Node: MAC001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 108
1 | 109 | 109 | 0102818008 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Calambeg | 18.188 | 120.7249 | R | 1351 | 3.7 | 365 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 2.63 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.96 | 48.96 | 87.31 | 68.14 | D - Other node or line within 3 km | 2.8 | 2.63 | Line: SEGMENT 1 PIDDIG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 109
1 | 110 | 110 | 1381600021 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Palasan | 14.7064 | 120.9459 | U | 6786 | 4.11 | 1651 | 495 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 1.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.8 | 59.8 | 76.46 | 68.13 | D - Other node or line within 3 km | 1.05 | 1.35 | Node: OBB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 110
1 | 111 | 111 | 0102817001 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Batuli | 18.3154 | 120.6153 | R | 459 | 3.7 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.67 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.54 | 49.54 | 86.65 | 68.1 | B - Node 0.5-1 km | 0.67 | 0.58 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Survey short node lateral; confirm port/fiber capacity, access and route. | 111
1 | 112 | 112 | 0300803016 | Region III (Central Luzon) | Bataan | City of Balanga | San Jose | 14.6752 | 120.5385 | U | 7018 | 3.6 | 1949 | 585 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 0.63 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.44 | 65.44 | 70.71 | 68.08 | D - Other node or line within 3 km | 1.07 | 0.58 | Line: 60 CORE 5X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 112
1 | 113 | 113 | 0402106067 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres II | 14.28 | 120.9992 | R | 3585 | 3.4 | 1054 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 3.6 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.8 | 67.8 | 68.32 | 68.06 | A - Node within 0.5 km | 0.41 | 3.57 | Node: MAC001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 113
1 | 114 | 114 | 0403416008 | Region IV-A (CALABARZON) | Laguna | Majayjay | Banti | 14.1569 | 121.4715 | R | 90 | 3.3 | 27 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.16 | 52.16 | 83.96 | 68.06 | D - Other node or line within 3 km | 1.55 | 1.27 | Line: SAN PABLO - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 114
1 | 115 | 115 | 0401003039 | Region IV-A (CALABARZON) | Batangas | Balayan | Patugo | 14.0041 | 120.7845 | R | 2457 | 3.6 | 682 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.35 | 5.91 | Tier 1B: High GIDA Priority | 54.65 | 54.65 | 81.39 | 68.02 | F - Nearest node and line over 5 km | 6.35 | 5.91 | Line: TGY001 TO BYB001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 115
1 | 116 | 116 | 0402106034 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel I | 14.2878 | 120.9617 | R | 2971 | 3.4 | 874 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.24 | 68.24 | 67.76 | 68 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.42 | Line: NCC001 TO TGY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 116
1 | 117 | 117 | 1381600010 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Dalandanan | 14.7046 | 120.9642 | U | 20084 | 3.72 | 5404 | 1621 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.65 | 0.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.82 | 67.82 | 68.19 | 68 | B - Node 0.5-1 km | 0.66 | 0.28 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 117
1 | 118 | 118 | 0405810005 | Region IV-A (CALABARZON) | Rizal | Pililla | Imatong | 14.4504 | 121.3355 | R | 916 | 3.6 | 254 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 1.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.01 | 52.01 | 83.95 | 67.98 | D - Other node or line within 3 km | 1.02 | 1.23 | Node: PLR002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 118
1 | 119 | 119 | 0402106033 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis I | 14.3336 | 120.9772 | R | 4172 | 3.4 | 1227 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 4.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.07 | 66.07 | 69.88 | 67.97 | D - Other node or line within 3 km | 1.61 | 4.28 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 119
1 | 120 | 120 | 0501720004 | Region V (Bicol Region) | Camarines Sur | Magarao | Carigsa | 13.6622 | 123.1816 | R | 229 | 4.2 | 55 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.68 | 57.68 | 78.24 | 67.96 | B - Node 0.5-1 km | 0.7 | 0.21 | Line: EE11-HH12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 120
1 | 121 | 121 | 0102911006 | Region I (Ilocos Region) | Ilocos Sur | Lidlidda | Labut | 17.2574 | 120.5349 | R | 309 | 3.8 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 1.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.64 | 52.64 | 82.95 | 67.79 | D - Other node or line within 3 km | 1.42 | 1.42 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 121
1 | 122 | 122 | 1381200003 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bambang | 14.5547 | 121.0781 | U | 20908 | 3.51 | 5955 | 1786 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.74 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.95 | 66.95 | 68.62 | 67.78 | B - Node 0.5-1 km | 0.74 | 0.2 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 122
1 | 123 | 123 | 0402123016 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Jacinto Lumbreras | 14.2906 | 121.002 | R | 4497 | 3.4 | 1323 | 397 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 4.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.62 | 67.62 | 67.88 | 67.75 | B - Node 0.5-1 km | 0.91 | 4.29 | Node: MAC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 123
1 | 124 | 124 | 0402106023 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Luzviminda I | 14.3279 | 120.9656 | R | 3753 | 3.4 | 1104 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 3.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.52 | 65.52 | 69.98 | 67.75 | D - Other node or line within 3 km | 1.71 | 3.11 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 124
1 | 125 | 125 | 0403405039 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 2 | 14.1982 | 121.1382 | U | 11649 | 3.3 | 3530 | 1059 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.87 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 70.49 | 70.49 | 64.99 | 67.74 | B - Node 0.5-1 km | 0.87 | 0.1 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 125
1 | 126 | 126 | 0405811011 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid II | 14.6871 | 121.1147 | U | 4458 | 3.6 | 1238 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.91 | 64.91 | 70.56 | 67.74 | A - Node within 0.5 km | 0.16 | 0.17 | Node: SMT001-TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 126
1 | 127 | 127 | 1381200024 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Cruz | 14.563 | 121.0791 | U | 5821 | 3.52 | 1656 | 497 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.27 | 61.27 | 74.2 | 67.74 | A - Node within 0.5 km | 0.33 | 0.27 | Line: Aerial 216C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 127
1 | 128 | 128 | 0301412011 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Lawa | 14.7348 | 120.9778 | U | 16298 | 3.5 | 4657 | 1397 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.08 | 1.34 | Tier 1B: High GIDA Priority | 72.38 | 72.38 | 62.98 | 67.68 | D - Other node or line within 3 km | 1.08 | 1.3 | Node: MEB003 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 128
1 | 129 | 129 | 1102319024 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo North | 7.4653 | 125.8138 | U | 8739 | 3.7 | 2362 | 709 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.65 | 68.65 | 66.63 | 67.64 | B - Node 0.5-1 km | 0.82 | 0.81 | Line: DAVAO CITY - TRENTO | Survey short node lateral; confirm port/fiber capacity, access and route. | 129
1 | 130 | 130 | 1380601118 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 118 | 14.101 | 120.8968 | U | 10891 | 4.58 | 2379 | 714 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.56 | 1.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.54 | 59.54 | 75.68 | 67.61 | D - Other node or line within 3 km | 2.56 | 1.39 | Line: TGY001 TO BYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 130
1 | 131 | 131 | 1381300013 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Balingasa | 14.6521 | 121.0013 | U | 22109 | 3.9 | 5662 | 1699 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.57 | 1.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.8 | 65.8 | 69.4 | 67.6 | D - Other node or line within 3 km | 1.57 | 1.51 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 131
1 | 132 | 132 | 0402123013 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Gavino Maderan | 14.3207 | 121.0204 | U | 9052 | 3.4 | 2662 | 799 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.56 | 3.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.56 | 61.56 | 73.62 | 67.59 | D - Other node or line within 3 km | 2.56 | 3.14 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 132
1 | 133 | 133 | 0304928003 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Liwayway | 15.4435 | 121.0651 | R | 4402 | 3.5 | 1258 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.07 | 0.09 | Tier 1B: High GIDA Priority | 72.89 | 72.89 | 62.17 | 67.53 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.08 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 133
1 | 134 | 134 | 0403429015 | Region IV-A (CALABARZON) | Laguna | Siniloan | Magsaysay | 14.4994 | 121.5219 | R | 2603 | 3.3 | 789 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.13 | 10.06 | Tier 1B: High GIDA Priority | 58.95 | 58.95 | 76.11 | 67.53 | E - Nearest node or line 3-5 km | 4.13 | 10.05 | Node: FYL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 134
1 | 135 | 135 | 0102814010 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Santo Niño | 17.956 | 120.7148 | R | 1202 | 3.7 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.74 | 5.75 | Tier 1B: High GIDA Priority | 44.95 | 44.95 | 90.07 | 67.51 | F - Nearest node and line over 5 km | 6.74 | 5.7 | Line: SEGMENT 5 BANNA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 135
1 | 136 | 136 | 1380200018 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Tres | 14.4407 | 121.004 | U | 33192 | 4 | 8306 | 2492 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.37 | 0.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.78 | 64.78 | 70.21 | 67.5 | A - Node within 0.5 km | 0.37 | 0.25 | Line: UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 136
1 | 137 | 137 | 1381300136 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Capri | 14.7058 | 120.9619 | U | 12940 | 3.9 | 3318 | 995 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.04 | 66.04 | 68.85 | 67.45 | A - Node within 0.5 km | 0.39 | 0.1 | Line: Mnla Pipe | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 137
1 | 138 | 138 | 0402106068 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua II | 14.3143 | 120.9066 | R | 3223 | 3.4 | 948 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 2.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.18 | 64.18 | 70.69 | 67.44 | D - Other node or line within 3 km | 2.27 | 2.5 | Node: TRC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 138
1 | 139 | 139 | 1401104005 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Ekip | 16.5249 | 120.8768 | R | 988 | 3.5 | 282 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.58 | 8.81 | Tier 1B: High GIDA Priority | 48.39 | 48.39 | 86.49 | 67.44 | F - Nearest node and line over 5 km | 7.58 | 8.79 | Node: BKB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 139
1 | 140 | 140 | 0402106021 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado I | 14.3113 | 120.9721 | U | 8424 | 3.4 | 2478 | 743 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 2.02 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.07 | 64.07 | 70.75 | 67.41 | B - Node 0.5-1 km | 0.71 | 1.99 | Node: DMC004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 140
1 | 141 | 141 | 1381701001 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Aguho | 14.544 | 121.0615 | U | 7448 | 3.98 | 1871 | 561 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.05 | 61.05 | 73.75 | 67.4 | B - Node 0.5-1 km | 0.74 | 0.15 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 141
1 | 142 | 142 | 1381400017 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | San Perfecto | 14.6031 | 121.0231 | U | 4669 | 3.31 | 1410 | 423 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.84 | 57.84 | 76.92 | 67.38 | D - Other node or line within 3 km | 1.77 | 0.55 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 142
1 | 143 | 143 | 0402106041 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz I | 14.3128 | 120.9607 | U | 5381 | 3.4 | 1583 | 475 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 1.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.15 | 65.15 | 69.59 | 67.37 | B - Node 0.5-1 km | 0.55 | 1.36 | Node: DMC004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 143
1 | 144 | 144 | 1403215014 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Poblacion | 17.265 | 121.149 | R | 861 | 4.3 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.14 | 0.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.54 | 57.54 | 77.21 | 67.37 | A - Node within 0.5 km | 0.14 | 0.08 | Line: Untitled Path | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 144
1 | 145 | 145 | 1380400021 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tugatog | 14.6606 | 120.9676 | U | 26498 | 3.64 | 7275 | 2182 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.87 | 0.75 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.06 | 65.06 | 69.64 | 67.35 | B - Node 0.5-1 km | 0.87 | 0.85 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 145
1 | 146 | 146 | 1403209022 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Taga | 17.5733 | 121.3647 | R | 2397 | 4.3 | 557 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.12 | 6.49 | Tier 1B: High GIDA Priority | 53.9 | 53.9 | 80.81 | 67.35 | E - Nearest node or line 3-5 km | 3.12 | 6.49 | Node: PKK002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 146
1 | 147 | 147 | 0402103004 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Bayanan | 14.2809 | 120.8995 | U | 11757 | 3.4 | 3458 | 1037 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.85 | 0.77 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.54 | 68.54 | 66.09 | 67.31 | D - Other node or line within 3 km | 1.85 | 0.73 | Line: TRECE MARTIRES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 147
1 | 148 | 148 | 0600402007 | Region VI (Western Visayas) | Aklan | Balete | Fulgencio | 11.5882 | 122.3687 | R | 3736 | 3.9 | 958 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.77 | 1.24 | Tier 1B: High GIDA Priority | 72.28 | 72.28 | 62.33 | 67.3 | D - Other node or line within 3 km | 2.77 | 1.22 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 148
1 | 149 | 149 | 1400118019 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Yuyeng | 17.5528 | 120.5697 | R | 423 | 3.8 | 111 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.45 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.33 | 54.33 | 80.26 | 67.3 | B - Node 0.5-1 km | 0.84 | 0.45 | Line: CABLE LAYED | Survey short node lateral; confirm port/fiber capacity, access and route. | 149
1 | 150 | 150 | 0402104001 | Region IV-A (CALABARZON) | Cavite | Carmona | Bancal | 14.282 | 121.0072 | U | 17076 | 3.4 | 5022 | 1507 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.57 | 4.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 69.07 | 69.07 | 65.52 | 67.29 | B - Node 0.5-1 km | 0.57 | 4.47 | Node: MAC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 150
1 | 151 | 151 | 0402106047 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol I | 14.3262 | 120.96 | U | 18198 | 3.4 | 5352 | 1606 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.65 | 2.81 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.64 | 66.64 | 67.94 | 67.29 | D - Other node or line within 3 km | 1.65 | 2.73 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 151
1 | 152 | 152 | 1381400015 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Rivera | 14.5898 | 121.036 | U | 2439 | 2.97 | 821 | 246 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.46 | 56.46 | 78.09 | 67.27 | A - Node within 0.5 km | 0.17 | 0.04 | Line: Aerial 216C MTF | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 152
1 | 153 | 153 | 0403428002 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Balibago | 14.2963 | 121.1045 | U | 23640 | 3.3 | 7164 | 2149 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.28 | 0.12 | Tier 1B: High GIDA Priority | 70.4 | 70.4 | 64.13 | 67.26 | A - Node within 0.5 km | 0.28 | 0.12 | Line: UG SPL001 TO CBL001 (STA ROSA CABUYAO BOUNDERY) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 153
1 | 154 | 154 | 1381400004 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Corazon De Jesus | 14.6059 | 121.0292 | U | 9220 | 3.89 | 2368 | 710 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.43 | 60.43 | 74.09 | 67.26 | C - Line within 0.5 km; node over 1 km | 1.92 | 0.12 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 154
1 | 155 | 155 | 0402106076 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina II | 14.2597 | 120.9899 | R | 3690 | 3.4 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 1.7 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.33 | 67.33 | 67.14 | 67.24 | D - Other node or line within 3 km | 2.85 | 1.69 | Line: SILANG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 155
1 | 156 | 156 | 0402106029 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco I | 14.335 | 120.9558 | R | 3262 | 3.4 | 959 | 288 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.45 | 3.71 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.97 | 63.97 | 70.49 | 67.23 | D - Other node or line within 3 km | 2.45 | 3.63 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 156
1 | 157 | 157 | 1380604008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 275 | 13.3924 | 123.219 | U | 20995 | 3.74 | 5614 | 1684 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 8.7 | 15.87 | Tier 1B: High GIDA Priority | 55.9 | 55.9 | 78.56 | 67.23 | F - Nearest node and line over 5 km | 8.7 | 15.86 | Node: BNC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 157
1 | 158 | 158 | 1380900003 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bagumbayan South | 14.6512 | 120.9486 | U | 4489 | 3.38 | 1330 | 399 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.93 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.78 | 59.78 | 74.64 | 67.21 | B - Node 0.5-1 km | 0.58 | 2.06 | Node: NAV001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 158
1 | 159 | 159 | 1404407002 | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | Bun-ayan | 16.9734 | 120.9094 | R | 773 | 3.7 | 209 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.56 | 0.29 | Tier 1B: High GIDA Priority | 51.42 | 51.42 | 82.96 | 67.19 | C - Line within 0.5 km; node over 1 km | 4.56 | 0.21 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 159
1 | 160 | 160 | 1108211009 | Region XI (Davao Region) | Davao de Oro | Pantukan | Tagdangua | 7.2067 | 125.8825 | U | 4866 | 3.7 | 1315 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.26 | 0.16 | Tier 1B: High GIDA Priority | 58.48 | 58.48 | 75.88 | 67.18 | C - Line within 0.5 km; node over 1 km | 8.26 | 0.16 | Line: TAGUM - PANTUKAN SEGMENT 4 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 160
1 | 161 | 161 | 0402111016 | Region IV-A (CALABARZON) | Cavite | Kawit | Congbalay-Legaspi | 14.4513 | 120.9226 | R | 4597 | 3.4 | 1352 | 406 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.16 | 68.16 | 66.17 | 67.17 | C - Line within 0.5 km; node over 1 km | 2.85 | 0.27 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 161
1 | 162 | 162 | 1381701007 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santa Ana | 14.5466 | 121.0718 | U | 30950 | 3.82 | 8107 | 2432 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.43 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.89 | 64.89 | 69.39 | 67.14 | A - Node within 0.5 km | 0.43 | 0.13 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 162
1 | 163 | 163 | 0403428012 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Market Area | 14.3151 | 121.1114 | U | 17557 | 3.3 | 5320 | 1596 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.18 | 1.25 | Tier 1B: High GIDA Priority | 70.99 | 70.99 | 63.26 | 67.13 | D - Other node or line within 3 km | 1.18 | 1.24 | Node: SRL004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 163
1 | 164 | 164 | 1380900004 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bangculasi | 14.6512 | 120.9527 | U | 8621 | 3.32 | 2598 | 779 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.66 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.97 | 62.97 | 71.29 | 67.13 | B - Node 0.5-1 km | 0.85 | 2.16 | Node: NAV001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 164
1 | 165 | 165 | 0403403021 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Vicente | 14.3296 | 121.0779 | U | 10124 | 3.3 | 3068 | 920 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.76 | 68.76 | 65.49 | 67.12 | C - Line within 0.5 km; node over 1 km | 1.03 | 0.05 | Line: AE CRC005-BNL001-CLB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 165
1 | 166 | 166 | 0402106072 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis II | 14.3043 | 121.019 | R | 4565 | 3.4 | 1343 | 403 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 3.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.99 | 64.99 | 69.18 | 67.09 | D - Other node or line within 3 km | 2.57 | 3.42 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 166
1 | 167 | 167 | 0600406005 | Region VI (Western Visayas) | Aklan | Ibajay | Aquino | 11.8161 | 122.119 | R | 3505 | 3.9 | 899 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22 | 0.61 | Tier 1B: High GIDA Priority | 54.17 | 54.17 | 79.99 | 67.08 | F - Nearest node and line over 5 km | 22 | 28.35 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 167
1 | 168 | 168 | 0102803025 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Nagrebcan | 17.9105 | 120.4793 | R | 536 | 3.7 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.63 | 48.63 | 85.54 | 67.08 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.48 | Line: SEGMENT 3 (VIGAN - BATAC) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 168
1 | 169 | 169 | 0102822012 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Maananteng | 18.1012 | 120.8113 | R | 1314 | 3.7 | 355 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.19 | 4.24 | Tier 1B: High GIDA Priority | 47.13 | 47.13 | 87.03 | 67.08 | E - Nearest node or line 3-5 km | 4.19 | 4.24 | Node: SSI001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 169
1 | 170 | 170 | 0403405053 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Cristobal | 14.2226 | 121.1456 | U | 16312 | 3.3 | 4943 | 1483 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.78 | 0.61 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 69.03 | 69.03 | 65.11 | 67.07 | D - Other node or line within 3 km | 2.78 | 0.61 | Line: AE SPL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 170
1 | 171 | 171 | 0307703004 | Region III (Central Luzon) | Aurora | Dilasag | Dimaseset | 16.3773 | 122.1566 | R | 1085 | 3.8 | 286 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.18 | 0.16 | Tier 1B: High GIDA Priority | 48.09 | 48.09 | 86.04 | 67.06 | F - Nearest node and line over 5 km | 5.18 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 171
1 | 172 | 172 | 0403428008 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Labas | 14.3064 | 121.1113 | U | 23335 | 3.3 | 7071 | 2121 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.05 | 0.92 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.96 | 68.96 | 65.15 | 67.05 | D - Other node or line within 3 km | 1.05 | 0.92 | Line: BINAN - CABUYAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 172
1 | 173 | 173 | 0201529022 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Cataggaman Viejo | 17.5968 | 121.7072 | R | 4626 | 3.9 | 1186 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.04 | 1.87 | Tier 1B: High GIDA Priority | 66.59 | 66.59 | 67.49 | 67.04 | D - Other node or line within 3 km | 4.04 | 1.86 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 173
1 | 174 | 174 | 1907005025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Sipangkot | 16.09 | 120.39 | U | 7560 | 5.8 | 1303 | 391 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.57 | 59.57 | 74.5 | 67.04 | C - Line within 0.5 km; node over 1 km | 2.8 | 0.19 | Line: MANGALDAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 174
1 | 175 | 175 | 0301412012 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Libtong | 14.7442 | 120.9804 | U | 13319 | 3.5 | 3805 | 1142 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.45 | 1.05 | Tier 1B: High GIDA Priority | 70.41 | 70.41 | 63.65 | 67.03 | D - Other node or line within 3 km | 1.45 | 1.05 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 175
1 | 176 | 176 | 0500503038 | Region V (Bicol Region) | Albay | Daraga | Mi-isi | 13.1035 | 123.7 | R | 1123 | 4.1 | 274 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.97 | 0.39 | Tier 1B: High GIDA Priority | 51.13 | 51.13 | 82.91 | 67.02 | C - Line within 0.5 km; node over 1 km | 3.97 | 0.2 | Line: DARAGA - SORSOGON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 176
1 | 177 | 177 | 0702232015 | Region VII (Central Visayas) | Cebu | Minglanilla | Tulay | 10.2391 | 123.7927 | U | 12101 | 3.8 | 3184 | 955 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.28 | 0.21 | Tier 1B: High GIDA Priority | 70.88 | 70.88 | 63.12 | 67 | C - Line within 0.5 km; node over 1 km | 1.28 | 0.06 | Line: 96c | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 177
1 | 178 | 178 | 0402106050 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado II | 14.299 | 120.9987 | R | 2943 | 3.4 | 866 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 4.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.77 | 63.77 | 70.23 | 67 | D - Other node or line within 3 km | 1.88 | 4.3 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 178
1 | 179 | 179 | 0402106040 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina I | 14.3219 | 120.971 | R | 3481 | 3.4 | 1024 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 2.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.16 | 66.16 | 67.8 | 66.98 | D - Other node or line within 3 km | 1.2 | 2.83 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 179
1 | 180 | 180 | 0402118061 | Region IV-A (CALABARZON) | Cavite | Silang | Narra III | 14.1855 | 120.9843 | R | 3393 | 3.4 | 998 | 299 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 2.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.02 | 64.02 | 69.95 | 66.98 | D - Other node or line within 3 km | 2.5 | 2.33 | Line: TGY001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 180
1 | 181 | 181 | 1381300141 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Greater Lagro | 14.7306 | 121.0662 | U | 24104 | 3.86 | 6237 | 1871 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.5 | 0.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.1 | 67.1 | 66.85 | 66.97 | A - Node within 0.5 km | 0.5 | 0.5 | Node: QCY093 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 181
1 | 182 | 182 | 1380700012 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Concepcion Dos | 14.6399 | 121.1213 | U | 25268 | 4.21 | 5998 | 1799 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.2 | 0.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.02 | 66.02 | 67.92 | 66.97 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.07 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 182
1 | 183 | 183 | 0403428009 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Macabling | 14.2986 | 121.0975 | U | 22368 | 3.3 | 6778 | 2033 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.81 | 0.76 | Tier 1B: High GIDA Priority | 69.8 | 69.8 | 64.07 | 66.94 | B - Node 0.5-1 km | 0.81 | 0.65 | Line: TGY001 TO CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 183
1 | 184 | 184 | 0702232007 | Region VII (Central Visayas) | Cebu | Minglanilla | Linao | 10.255 | 123.8103 | U | 16506 | 3.8 | 4344 | 1303 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.36 | 0.11 | Tier 1B: High GIDA Priority | 73.66 | 73.66 | 60.19 | 66.93 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.02 | Line: CEBU - TOLEDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 184
1 | 185 | 185 | 0402123020 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Marcelino Memije | 14.2943 | 121.0343 | R | 5213 | 3.4 | 1533 | 460 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 2.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.36 | 66.36 | 67.51 | 66.93 | D - Other node or line within 3 km | 2.02 | 2.51 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 185
1 | 186 | 186 | 0402118052 | Region IV-A (CALABARZON) | Cavite | Silang | Narra I | 14.2176 | 121.0012 | R | 3334 | 3.4 | 981 | 294 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.63 | 2.65 | Tier 1B: High GIDA Priority | 62.62 | 62.62 | 71.22 | 66.92 | D - Other node or line within 3 km | 3.63 | 2.65 | Line: TGY001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 186
1 | 187 | 187 | 0500518019 | Region V (Bicol Region) | Albay | Tiwi | Mayong | 13.52 | 123.5996 | R | 1693 | 4.1 | 413 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 0.11 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.13 | 57.13 | 76.72 | 66.92 | C - Line within 0.5 km; node over 1 km | 1.71 | 0.05 | Line: LEGAZP - TIWI AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 187
1 | 188 | 188 | 0402106051 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima II | 14.3002 | 120.9203 | U | 4532 | 3.4 | 1333 | 400 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.92 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.92 | 62.92 | 70.89 | 66.9 | D - Other node or line within 3 km | 1.3 | 0.92 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 188
1 | 189 | 189 | 0402123004 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 3 Poblacion | 14.3077 | 121.0088 | R | 2589 | 3.4 | 761 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.91 | 4.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.42 | 59.42 | 74.36 | 66.89 | D - Other node or line within 3 km | 2.91 | 4.46 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 189
1 | 190 | 190 | 1380300023 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | San Antonio | 14.5621 | 121.0082 | U | 18012 | 3.54 | 5083 | 1525 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.41 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.79 | 66.79 | 66.97 | 66.88 | C - Line within 0.5 km; node over 1 km | 1.41 | 0.29 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 190
1 | 191 | 191 | 0403405019 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lawa | 14.207 | 121.1453 | U | 13423 | 3.3 | 4068 | 1220 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.08 | 0.37 | Tier 1B: High GIDA Priority | 71.73 | 71.73 | 61.89 | 66.81 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.3 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 191
1 | 192 | 192 | 0205001009 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Tiblac | 16.5201 | 121.0763 | R | 2624 | 3.8 | 691 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.36 | 6.64 | Tier 1B: High GIDA Priority | 57.94 | 57.94 | 75.63 | 66.79 | F - Nearest node and line over 5 km | 8.36 | 6.64 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 192
1 | 193 | 193 | 0402106038 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Roque | 14.2947 | 120.9363 | R | 3006 | 3.4 | 884 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 0.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.82 | 66.82 | 66.71 | 66.77 | C - Line within 0.5 km; node over 1 km | 2.49 | 0.18 | Line: NCC001 TO TGY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 193
1 | 194 | 194 | 0405811005 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan I | 14.6953 | 121.1209 | U | 33621 | 3.6 | 9339 | 2802 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.08 | 0.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.96 | 65.96 | 67.54 | 66.75 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.15 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 194
1 | 195 | 195 | 0402106036 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel | 14.3131 | 120.9906 | R | 4335 | 3.4 | 1275 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 3.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.04 | 67.04 | 66.43 | 66.74 | D - Other node or line within 3 km | 1.13 | 3.78 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 195
1 | 196 | 196 | 0102915001 | Region I (Ilocos Region) | Ilocos Sur | Quirino | Banoen | 17.1573 | 120.6805 | R | 596 | 3.9 | 153 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 2.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.45 | 48.45 | 84.97 | 66.71 | D - Other node or line within 3 km | 2.26 | 1.91 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 196
1 | 197 | 197 | 1380400015 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Potrero | 14.6695 | 120.998 | U | 43411 | 3.49 | 12451 | 3735 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.31 | 0.69 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.78 | 57.78 | 75.61 | 66.7 | D - Other node or line within 3 km | 1.31 | 1.07 | Line: Aerial 216C MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 197
1 | 198 | 198 | 1381100036 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 36 | 14.5902 | 120.9993 | U | 5575 | 2.87 | 1943 | 583 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.24 | 61.24 | 72.06 | 66.65 | B - Node 0.5-1 km | 0.75 | 0.38 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 198
1 | 199 | 199 | 1381200010 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Malinao | 14.5803 | 121.0925 | U | 5370 | 3.65 | 1471 | 441 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.58 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.41 | 59.41 | 73.88 | 66.65 | B - Node 0.5-1 km | 0.97 | 0.58 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 199
1 | 200 | 200 | 1380601105 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 105 | 14.3303 | 121.3753 | U | 26494 | 3.44 | 7699 | 2310 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 3.88 | 6.97 | Tier 1B: High GIDA Priority | 56.75 | 56.75 | 76.53 | 66.64 | E - Nearest node or line 3-5 km | 3.88 | 6.96 | Node: JLR002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 200
1 | 201 | 201 | 0402123005 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 4 Poblacion | 14.3119 | 121.0215 | R | 4992 | 3.4 | 1468 | 440 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 3.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.9 | 65.9 | 67.37 | 66.63 | D - Other node or line within 3 km | 2.19 | 3.07 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 201
1 | 202 | 202 | 1401111005 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Colalo | 16.9129 | 120.7664 | R | 1676 | 3.5 | 479 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.27 | 0.31 | Tier 1B: High GIDA Priority | 52.7 | 52.7 | 80.54 | 66.62 | C - Line within 0.5 km; node over 1 km | 7.27 | 0.16 | Line: PROPOSED 96C FOC - BUGIAS TO CERVANTES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 202
1 | 203 | 203 | 0102934040 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay IX | 17.5669 | 120.3868 | R | 2598 | 3.8 | 684 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3 | 1.58 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.76 | 60.76 | 72.44 | 66.6 | D - Other node or line within 3 km | 3 | 1.58 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 203
1 | 204 | 204 | 0405802018 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Muntingdilaw | 14.5974 | 121.1262 | U | 12938 | 3.6 | 3594 | 1078 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.57 | 1.53 | Tier 1B: High GIDA Priority | 69.41 | 69.41 | 63.77 | 66.59 | D - Other node or line within 3 km | 1.57 | 1.53 | Line: TAYTAY - CAINTA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 204
1 | 205 | 205 | 1381100076 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 76 | 14.4616 | 120.9515 | U | 25631 | 2.7 | 9497 | 2849 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.91 | 0.89 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.2 | 62.2 | 70.97 | 66.58 | B - Node 0.5-1 km | 0.91 | 0.89 | Line: PSG001 RELIANCE TO NCC001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 205
1 | 206 | 206 | 0307113012 | Region III (Central Luzon) | Zambales | Santa Cruz | Lomboy | 15.7784 | 119.9426 | R | 1889 | 3.8 | 497 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.75 | 3.75 | Tier 1B: High GIDA Priority | 51.4 | 51.4 | 81.66 | 66.53 | E - Nearest node or line 3-5 km | 3.75 | 3.71 | Line: STA CRUZ MUNICIPALITY | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 206
1 | 207 | 207 | 1102319023 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo East | 7.4497 | 125.8167 | U | 16035 | 3.7 | 4334 | 1300 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.31 | 0.49 | Tier 1B: High GIDA Priority | 73.12 | 73.12 | 59.93 | 66.52 | C - Line within 0.5 km; node over 1 km | 1.31 | 0.49 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 207
1 | 208 | 208 | 0405801011 | Region IV-A (CALABARZON) | Rizal | Angono | San Roque | 14.5325 | 121.1614 | U | 12209 | 3.6 | 3391 | 1017 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.91 | 0.87 | Tier 1B: High GIDA Priority | 69.97 | 69.97 | 63.06 | 66.52 | B - Node 0.5-1 km | 0.91 | 0.85 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 208
1 | 209 | 209 | 0300811023 | Region III (Central Luzon) | Bataan | Pilar | Santa Rosa | 14.6772 | 120.5473 | U | 7499 | 3.6 | 2083 | 625 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.45 | 66.45 | 66.58 | 66.51 | B - Node 0.5-1 km | 0.75 | 0.26 | Line: PILAR | Survey short node lateral; confirm port/fiber capacity, access and route. | 209
1 | 210 | 210 | 1381200018 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Sagad | 14.5661 | 121.0796 | U | 6357 | 3.48 | 1827 | 548 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.16 | 61.16 | 71.87 | 66.51 | B - Node 0.5-1 km | 0.62 | 0.08 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 210
1 | 211 | 211 | 0402104006 | Region IV-A (CALABARZON) | Cavite | Carmona | Cabilang Baybay | 14.3177 | 121.0498 | U | 8144 | 3.4 | 2395 | 718 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 0.76 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.2 | 67.2 | 65.81 | 66.5 | B - Node 0.5-1 km | 0.76 | 0.76 | Line: AE CRC005-BNL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 211
1 | 212 | 212 | 0403405020 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lecheria | 14.2033 | 121.1614 | U | 11956 | 3.3 | 3623 | 1087 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.78 | 0.21 | Tier 1B: High GIDA Priority | 69.17 | 69.17 | 63.81 | 66.49 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.21 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 212
1 | 213 | 213 | 0405811010 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santa Ana | 14.6963 | 121.116 | U | 10398 | 3.6 | 2888 | 866 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.58 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 68.16 | 68.16 | 64.82 | 66.49 | D - Other node or line within 3 km | 1.05 | 0.5 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 213
1 | 214 | 214 | 1380400009 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Ibaba | 14.6654 | 120.9506 | U | 8219 | 3.58 | 2295 | 688 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.99 | 61.99 | 71 | 66.49 | B - Node 0.5-1 km | 0.9 | 0.57 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 214
1 | 215 | 215 | 1404407005 | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | Capinitan | 16.95 | 120.9087 | R | 591 | 3.7 | 160 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.47 | 0.17 | Tier 1B: High GIDA Priority | 50.18 | 50.18 | 82.8 | 66.49 | C - Line within 0.5 km; node over 1 km | 4.47 | 0.05 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 215
1 | 216 | 216 | 0403405040 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 3 | 14.2074 | 121.1622 | U | 4973 | 3.3 | 1507 | 452 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.07 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.2 | 62.2 | 70.76 | 66.48 | C - Line within 0.5 km; node over 1 km | 2.07 | 0.19 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 216
1 | 217 | 217 | 0403405049 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Real | 14.1985 | 121.1492 | U | 17945 | 3.3 | 5438 | 1631 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.36 | 0.2 | Tier 1B: High GIDA Priority | 72.47 | 72.47 | 60.45 | 66.46 | A - Node within 0.5 km | 0.36 | 0.18 | Line: AE LBL001-STB001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 217
1 | 218 | 218 | 0402106025 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres I | 14.3216 | 120.9445 | R | 4484 | 3.4 | 1319 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 2.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.01 | 65.01 | 67.9 | 66.46 | D - Other node or line within 3 km | 2.5 | 2.36 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 218
1 | 219 | 219 | 1381701008 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santo Rosario-Kanluran | 14.5522 | 121.0689 | U | 5504 | 4.04 | 1362 | 409 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.34 | 59.34 | 73.55 | 66.45 | B - Node 0.5-1 km | 0.84 | 0.19 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 219
1 | 220 | 220 | 0205006015 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Rosario | 16.6152 | 121.3264 | R | 363 | 3.8 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.69 | 0.04 | Tier 1B: High GIDA Priority | 47.65 | 47.65 | 85.25 | 66.45 | C - Line within 0.5 km; node over 1 km | 6.69 | 0.02 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 220
1 | 221 | 221 | 1108202008 | Region XI (Davao Region) | Davao de Oro | Laak | Kidawa | 7.9045 | 125.9103 | R | 3785 | 3.7 | 1023 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.21 | 15.9 | Tier 1B: High GIDA Priority | 54.59 | 54.59 | 78.23 | 66.41 | F - Nearest node and line over 5 km | 18.21 | 15.9 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 221
1 | 222 | 222 | 0402106031 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Juan | 14.3014 | 120.9795 | R | 3860 | 3.4 | 1135 | 340 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.93 | 2.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.27 | 65.27 | 67.52 | 66.4 | D - Other node or line within 3 km | 1.93 | 2.25 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 222
1 | 223 | 223 | 1380300024 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | San Isidro | 14.5554 | 121.0071 | U | 6260 | 3.15 | 1987 | 596 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.31 | 61.31 | 71.47 | 66.39 | B - Node 0.5-1 km | 0.78 | 0.29 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 223
1 | 224 | 224 | 0301412005 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bayugo | 14.7329 | 120.9536 | U | 20064 | 3.5 | 5733 | 1720 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.71 | 0.85 | Tier 1B: High GIDA Priority | 69.9 | 69.9 | 62.85 | 66.37 | D - Other node or line within 3 km | 1.71 | 0.85 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 224
1 | 225 | 225 | 0201516035 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Tucalana | 18.1826 | 121.6601 | R | 1572 | 3.9 | 403 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.46 | 55.46 | 77.27 | 66.36 | C - Line within 0.5 km; node over 1 km | 1.45 | 0.2 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 225
1 | 226 | 226 | 1380200008 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Uno | 14.4385 | 121.0024 | U | 42677 | 3.88 | 11002 | 3301 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.36 | 0.24 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.45 | 61.45 | 71.26 | 66.35 | A - Node within 0.5 km | 0.36 | 0.1 | Line: UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 226
1 | 227 | 227 | 1381600033 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Canumay East | 14.7209 | 120.9833 | U | 15058 | 3.48 | 4325 | 1298 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.33 | 0.7 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.61 | 65.61 | 67.06 | 66.34 | D - Other node or line within 3 km | 2.33 | 0.67 | Line: Existing MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 227
1 | 228 | 228 | 1381300067 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Milagrosa | 14.6218 | 121.0682 | U | 6923 | 4.1 | 1690 | 507 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.52 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.93 | 60.93 | 71.74 | 66.34 | B - Node 0.5-1 km | 0.53 | 0.12 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 228
1 | 229 | 229 | 1705305004 | MIMAROPA Region | Palawan | Bataraza | Culandanum | 8.644 | 117.4618 | R | 5631 | 3.9 | 1444 | 433 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 185.36 | 187.64 | Tier 1B: High GIDA Priority | 52.4 | 52.4 | 80.28 | 66.34 | F - Nearest node and line over 5 km | 185.36 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 229
1 | 230 | 230 | 0102815007 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Dampig | 18.5404 | 120.8199 | R | 1041 | 3.7 | 281 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.43 | 2.52 | Tier 1B: High GIDA Priority | 48.76 | 48.76 | 83.84 | 66.3 | D - Other node or line within 3 km | 5.43 | 2.51 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 230
1 | 231 | 231 | 0300803021 | Region III (Central Luzon) | Bataan | City of Balanga | Tenejero | 14.6787 | 120.533 | U | 9639 | 3.6 | 2678 | 803 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.96 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 67.78 | 67.78 | 64.81 | 66.29 | D - Other node or line within 3 km | 1 | 0.95 | Line: 60 CORE 5X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 231
1 | 232 | 232 | 0402106043 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Lucia | 14.2871 | 120.9802 | U | 5826 | 3.4 | 1714 | 514 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 1.99 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.35 | 62.35 | 70.24 | 66.29 | D - Other node or line within 3 km | 2.41 | 1.99 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 232
1 | 233 | 233 | 0402106048 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol II | 14.2787 | 120.9489 | U | 6343 | 3.4 | 1866 | 560 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 1.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.56 | 62.56 | 70.01 | 66.28 | D - Other node or line within 3 km | 2.6 | 1.33 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 233
1 | 234 | 234 | 0405801013 | Region IV-A (CALABARZON) | Rizal | Angono | Santo Niño | 14.5446 | 121.1552 | R | 2316 | 3.6 | 643 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.9 | 1.01 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.14 | 61.14 | 71.41 | 66.27 | D - Other node or line within 3 km | 1.9 | 1.01 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 234
1 | 235 | 235 | 0402106030 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Isidro Labrador I | 14.3407 | 120.9506 | R | 5089 | 3.4 | 1497 | 449 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 4.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.9 | 66.9 | 65.59 | 66.24 | D - Other node or line within 3 km | 1.61 | 4.28 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 235
1 | 236 | 236 | 0402123006 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 5 Poblacion | 14.3041 | 121.0076 | U | 17917 | 3.4 | 5270 | 1581 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.48 | 4.63 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.49 | 65.49 | 66.97 | 66.23 | D - Other node or line within 3 km | 2.48 | 4.63 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 236
1 | 237 | 237 | 0600406021 | Region VI (Western Visayas) | Aklan | Ibajay | Naisud | 11.8057 | 122.1941 | R | 3304 | 3.9 | 847 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.71 | 0.41 | Tier 1B: High GIDA Priority | 55.63 | 55.63 | 76.8 | 66.22 | F - Nearest node and line over 5 km | 14.71 | 20.48 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 237
1 | 238 | 238 | 0600402008 | Region VI (Western Visayas) | Aklan | Balete | Guanko | 11.5328 | 122.3765 | R | 1216 | 3.9 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.71 | 2.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.42 | 54.42 | 78.02 | 66.22 | D - Other node or line within 3 km | 2.71 | 2.48 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 238
1 | 239 | 239 | 0403425008 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Magsaysay | 14.085 | 121.3089 | U | 14023 | 3.3 | 4249 | 1275 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.92 | 0.39 | Tier 1B: High GIDA Priority | 72.6 | 72.6 | 59.8 | 66.2 | B - Node 0.5-1 km | 0.92 | 0.38 | Line: AE SPO001 TO CLL001-NEW | Survey short node lateral; confirm port/fiber capacity, access and route. | 239
1 | 240 | 240 | 0402106065 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin II | 14.318 | 120.9524 | U | 12308 | 3.4 | 3620 | 1086 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.56 | 1.82 | Tier 1B: High GIDA Priority | 69.51 | 69.51 | 62.89 | 66.2 | D - Other node or line within 3 km | 1.56 | 1.75 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 240
1 | 241 | 241 | 0402106045 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Cristo | 14.3394 | 120.9556 | R | 4791 | 3.4 | 1409 | 423 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.12 | 4.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.83 | 65.83 | 66.57 | 66.2 | D - Other node or line within 3 km | 2.12 | 4.13 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 241
1 | 242 | 242 | 0405811007 | Region IV-A (CALABARZON) | Rizal | San Mateo | Malanday | 14.7046 | 121.125 | U | 13906 | 3.6 | 3863 | 1159 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.1 | 0.44 | Tier 1B: High GIDA Priority | 69.41 | 69.41 | 62.96 | 66.18 | C - Line within 0.5 km; node over 1 km | 2.1 | 0.36 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 242
1 | 243 | 243 | 1380400011 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Maysilo | 14.6827 | 120.9617 | U | 10481 | 3.49 | 3001 | 900 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.2 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.52 | 65.52 | 66.85 | 66.18 | A - Node within 0.5 km | 0.2 | 0.6 | Node: MAL005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 243
1 | 244 | 244 | 0403425024 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Fatima | 14.2672 | 121.4638 | U | 7115 | 3.3 | 2156 | 647 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 1.04 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.91 | 64.91 | 67.45 | 66.18 | D - Other node or line within 3 km | 1.62 | 1.04 | Line: SNL001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 244
1 | 245 | 245 | 1381300095 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Agustin | 14.7297 | 121.0352 | U | 26034 | 3.87 | 6723 | 2017 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.17 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.17 | 65.17 | 67.13 | 66.15 | C - Line within 0.5 km; node over 1 km | 1.17 | 0.25 | Line: Aerial 216C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 245
1 | 246 | 246 | 1380700013 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Marikina Heights | 14.6489 | 121.1186 | U | 45968 | 4.25 | 10816 | 3245 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.46 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.45 | 61.45 | 70.85 | 66.15 | A - Node within 0.5 km | 0.46 | 0.16 | Line: Aerial 96C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 246
1 | 247 | 247 | 0102807001 | Region I (Ilocos Region) | Ilocos Norte | Carasi | Angset | 18.1449 | 120.7951 | R | 179 | 3.7 | 48 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.61 | 5.27 | Tier 1B: High GIDA Priority | 44.61 | 44.61 | 87.57 | 66.09 | F - Nearest node and line over 5 km | 5.61 | 5.25 | Line: SEGMENT 2 SOLSONA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 247
1 | 248 | 248 | 0102915002 | Region I (Ilocos Region) | Ilocos Sur | Quirino | Cayus | 17.1521 | 120.6684 | R | 761 | 3.9 | 195 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 1.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.43 | 53.43 | 78.74 | 66.08 | D - Other node or line within 3 km | 1.99 | 1.03 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 248
1 | 249 | 249 | 0600402009 | Region VI (Western Visayas) | Aklan | Balete | Morales | 11.5452 | 122.3735 | R | 3496 | 3.9 | 896 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 1.21 | Tier 1B: High GIDA Priority | 73.07 | 73.07 | 59.08 | 66.07 | D - Other node or line within 3 km | 1.35 | 1.21 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 249
1 | 250 | 250 | 0402123002 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 1 Poblacion | 14.2974 | 121.0078 | U | 6913 | 3.4 | 2033 | 610 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 4.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.77 | 60.77 | 71.34 | 66.06 | D - Other node or line within 3 km | 1.78 | 4.79 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 250
1 | 251 | 251 | 0403425017 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Santo Niño | 14.079 | 121.2536 | R | 4266 | 3.3 | 1293 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.77 | 1.86 | Tier 1B: High GIDA Priority | 65.08 | 65.08 | 66.99 | 66.03 | D - Other node or line within 3 km | 6.77 | 1.86 | Line: CLB001 TO SPO001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 251
1 | 252 | 252 | 0102814006 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Caray | 17.9335 | 120.6862 | R | 837 | 3.7 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.28 | 2.99 | Tier 1B: High GIDA Priority | 44.62 | 44.62 | 87.45 | 66.03 | D - Other node or line within 3 km | 3.28 | 2.98 | Line: SEGMENT 5 BANNA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 252
1 | 253 | 253 | 0402103034 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay II | 14.2979 | 120.9486 | U | 12515 | 3.4 | 3681 | 1104 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.12 | 0.05 | Tier 1B: High GIDA Priority | 70.48 | 70.48 | 61.54 | 66.01 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.47 | Line: NCC001 TO TGY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 253
1 | 254 | 254 | 0301412003 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bancal | 14.7207 | 120.9618 | U | 13261 | 3.5 | 3789 | 1137 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.35 | 0.3 | Tier 1B: High GIDA Priority | 70.53 | 70.53 | 61.47 | 66 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.3 | Line: GOTACO TO HH 71 BULACAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 254
1 | 255 | 255 | 0402123022 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Pantaleon Granados | 14.3041 | 120.9909 | R | 3651 | 3.4 | 1074 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 3.62 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.99 | 64.99 | 66.99 | 65.99 | D - Other node or line within 3 km | 1.99 | 3.51 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 255
1 | 256 | 256 | 1380500015 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Mabini-J. Rizal | 14.5855 | 121.0212 | U | 8878 | 3.61 | 2459 | 738 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.72 | 62.72 | 69.21 | 65.97 | B - Node 0.5-1 km | 0.77 | 0.35 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 256
1 | 257 | 257 | 0201514013 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Isca | 18.236 | 121.9773 | R | 1572 | 3.9 | 403 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.81 | 1.28 | Tier 1B: High GIDA Priority | 52.33 | 52.33 | 79.62 | 65.97 | D - Other node or line within 3 km | 3.81 | 1.24 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 257
1 | 258 | 258 | 0205704038 | Region II (Cagayan Valley) | Quirino | Maddela | Jose Ancheta | 16.3204 | 121.6471 | R | 1069 | 3.9 | 274 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.95 | 0.95 | Tier 1B: High GIDA Priority | 48.69 | 48.69 | 83.23 | 65.96 | D - Other node or line within 3 km | 3.95 | 0.95 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 258
1 | 259 | 259 | 0403403018 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Niño | 14.328 | 121.0823 | U | 8480 | 3.3 | 2570 | 771 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 0.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.61 | 66.61 | 65.28 | 65.94 | C - Line within 0.5 km; node over 1 km | 1.37 | 0.47 | Line: AE CRC005-BNL001-CLB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 259
1 | 260 | 260 | 0405811003 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 2 | 14.6808 | 121.137 | U | 12514 | 3.6 | 3476 | 1043 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.34 | 0.99 | Tier 1B: High GIDA Priority | 67.86 | 67.86 | 63.99 | 65.93 | D - Other node or line within 3 km | 2.34 | 0.98 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 260
1 | 261 | 261 | 0402123008 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Bernardo Pulido | 14.3122 | 121.0201 | U | 15115 | 3.4 | 4446 | 1334 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.35 | 3.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 66.75 | 66.75 | 65.07 | 65.91 | D - Other node or line within 3 km | 2.35 | 3.23 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 261
1 | 262 | 262 | 1381300110 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santol | 14.6126 | 121.0154 | U | 6590 | 3.75 | 1755 | 526 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.11 | 61.11 | 70.71 | 65.91 | B - Node 0.5-1 km | 0.53 | 0.26 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 262
1 | 263 | 263 | 1381300127 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Unang Sigaw | 14.6583 | 120.9994 | U | 6672 | 4.07 | 1638 | 491 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 1.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.56 | 59.56 | 72.24 | 65.9 | D - Other node or line within 3 km | 1.15 | 1.3 | Node: CCS005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 263
1 | 264 | 264 | 1380700007 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Parang | 14.666 | 121.1179 | U | 41259 | 4.27 | 9672 | 2902 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.61 | 0.68 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.73 | 60.73 | 71.05 | 65.89 | D - Other node or line within 3 km | 1.61 | 0.64 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 264
1 | 265 | 265 | 1381300079 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pasong Putik Proper | 14.7418 | 121.0655 | U | 40919 | 3.97 | 10306 | 3092 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.3 | 0.7 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.48 | 60.48 | 71.3 | 65.89 | D - Other node or line within 3 km | 1.3 | 0.7 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 265
1 | 266 | 266 | 0403405038 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 1 | 14.2049 | 121.1584 | U | 6383 | 3.3 | 1934 | 580 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 0.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.31 | 64.31 | 67.45 | 65.88 | C - Line within 0.5 km; node over 1 km | 1.57 | 0.18 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 266
1 | 267 | 267 | 1381600031 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Viente Reales | 14.709 | 120.9654 | U | 18874 | 3.44 | 5488 | 1646 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.6 | 0.42 | Tier 1B: High GIDA Priority | 67.82 | 67.82 | 63.89 | 65.85 | B - Node 0.5-1 km | 0.6 | 0.24 | Line: Existing MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 267
1 | 268 | 268 | 1381200016 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Pineda | 14.5656 | 121.0665 | U | 20986 | 3.4 | 6179 | 1854 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.56 | 0.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.16 | 65.16 | 66.54 | 65.85 | C - Line within 0.5 km; node over 1 km | 1.56 | 0.36 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 268
1 | 269 | 269 | 0102814005 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Cabittauran | 17.9445 | 120.7063 | R | 1091 | 3.7 | 295 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.74 | 4.88 | Tier 1B: High GIDA Priority | 44.45 | 44.45 | 87.24 | 65.85 | E - Nearest node or line 3-5 km | 5.74 | 4.84 | Line: SEGMENT 5 BANNA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 269
1 | 270 | 270 | 0402123003 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 2 Poblacion | 14.3035 | 121.0187 | R | 4382 | 3.4 | 1289 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.62 | 3.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.75 | 64.75 | 66.93 | 65.84 | D - Other node or line within 3 km | 2.62 | 3.47 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 270
1 | 271 | 271 | 0105536005 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Cacabugaoan | 16.0706 | 120.7916 | R | 1415 | 3.6 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.99 | 7.11 | Tier 1B: High GIDA Priority | 46.67 | 46.67 | 85 | 65.84 | F - Nearest node and line over 5 km | 6.99 | 6.89 | Line: BINALONAN - UMINGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 271
1 | 272 | 272 | 1381400019 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Tibagan | 14.6116 | 121.0137 | U | 4024 | 3.75 | 1072 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.79 | 58.79 | 72.86 | 65.83 | B - Node 0.5-1 km | 0.69 | 0.1 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 272
1 | 273 | 273 | 0203131015 | Region II (Cagayan Valley) | Isabela | San Mariano | Disulap | 16.9678 | 122.0702 | R | 3026 | 3.8 | 796 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.38 | 23.14 | Tier 1B: High GIDA Priority | 57.74 | 57.74 | 73.88 | 65.81 | F - Nearest node and line over 5 km | 6.38 | 23.13 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 273
1 | 274 | 274 | 0301407020 | Region III (Central Luzon) | Bulacan | Calumpit | Pio Cruzcosa | 14.9048 | 120.7667 | U | 4874 | 3.5 | 1393 | 418 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.5 | 65.5 | 66.09 | 65.79 | A - Node within 0.5 km | 0.21 | 0.15 | Line: GOTACO TO HH 71 BULACAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 274
1 | 275 | 275 | 1381300007 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagumbuhay | 14.6253 | 121.0642 | U | 6739 | 4.1 | 1642 | 493 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.76 | 60.76 | 70.82 | 65.79 | B - Node 0.5-1 km | 0.55 | 0.2 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 275
1 | 276 | 276 | 1102509012 | Region XI (Davao Region) | Davao Oriental | City of Mati | Don Salvador Lopez, Sr. | 7.0774 | 126.2578 | R | 4799 | 3.6 | 1333 | 400 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.14 | 14.07 | Tier 1B: High GIDA Priority | 57.35 | 57.35 | 74.23 | 65.79 | F - Nearest node and line over 5 km | 14.14 | 14.05 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 276
1 | 277 | 277 | 1381100179 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 179 | 14.5356 | 120.9983 | U | 7649 | 3.57 | 2142 | 643 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.6 | 61.6 | 69.95 | 65.78 | B - Node 0.5-1 km | 0.86 | 0.11 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 277
1 | 278 | 278 | 1380500021 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Pag-asa | 14.586 | 121.0527 | U | 4493 | 3.29 | 1366 | 410 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 0.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.19 | 60.19 | 71.36 | 65.77 | A - Node within 0.5 km | 0.43 | 0.36 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 278
1 | 279 | 279 | 0201501002 | Region II (Cagayan Valley) | Cagayan | Abulug | Bagu | 18.4345 | 121.4687 | R | 2054 | 3.9 | 527 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.47 | 9 | Tier 1B: High GIDA Priority | 50.89 | 50.89 | 80.64 | 65.76 | F - Nearest node and line over 5 km | 5.47 | 8.98 | Node: BLC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 279
1 | 280 | 280 | 0402106024 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Saint Peter I | 14.2998 | 120.9667 | R | 2408 | 3.4 | 708 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.98 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.69 | 64.69 | 66.81 | 65.75 | B - Node 0.5-1 km | 0.86 | 0.86 | Node: DMC002 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 280
1 | 281 | 281 | 0403405041 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 4 | 14.1847 | 121.1303 | R | 3618 | 3.3 | 1096 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.21 | 0.39 | Tier 1B: High GIDA Priority | 68.24 | 68.24 | 63.25 | 65.74 | C - Line within 0.5 km; node over 1 km | 2.21 | 0.39 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 281
1 | 282 | 282 | 1380300013 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Magallanes | 14.5683 | 121.0281 | U | 5473 | 4.68 | 1170 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.22 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.06 | 60.06 | 71.43 | 65.74 | A - Node within 0.5 km | 0.22 | 0.03 | Line: UG 144C via V-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 282
1 | 283 | 283 | 1381400010 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Maytunas | 14.6013 | 121.0414 | U | 3308 | 3.94 | 839 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.54 | 54.54 | 76.94 | 65.74 | C - Line within 0.5 km; node over 1 km | 1.41 | 0.43 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 283
1 | 284 | 284 | 0301412009 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Iba | 14.7539 | 120.9818 | U | 9791 | 3.5 | 2797 | 839 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 1.48 | Tier 1B: High GIDA Priority | 68.32 | 68.32 | 63.12 | 65.72 | B - Node 0.5-1 km | 0.91 | 1.48 | Node: MEB001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 284
1 | 285 | 285 | 0405647001 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Alitao | 14.0165 | 121.6121 | R | 133 | 3.8 | 35 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 0.95 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.69 | 46.69 | 84.74 | 65.72 | D - Other node or line within 3 km | 2.16 | 0.95 | Line: LUCENA - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 285
1 | 286 | 286 | 1380500019 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | New Zañiga | 14.566 | 121.0408 | U | 8872 | 3.67 | 2415 | 724 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.59 | 61.59 | 69.83 | 65.71 | C - Line within 0.5 km; node over 1 km | 1.3 | 0.16 | Line: UG 144C via V-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 286
1 | 287 | 287 | 0403403015 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Platero | 14.3205 | 121.0916 | U | 16227 | 3.3 | 4917 | 1475 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.64 | 0.56 | Tier 1B: High GIDA Priority | 69.24 | 69.24 | 62.04 | 65.64 | D - Other node or line within 3 km | 2.64 | 0.55 | Line: BÑL001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 287
1 | 288 | 288 | 0102810001 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Cabaritan | 18.5219 | 120.8184 | R | 455 | 3.7 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.52 | 2.69 | Tier 1B: High GIDA Priority | 44.66 | 44.66 | 86.63 | 65.64 | D - Other node or line within 3 km | 5.52 | 2.69 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 288
1 | 289 | 289 | 0205009010 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Didipio | 16.3363 | 121.4545 | R | 3856 | 3.8 | 1015 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.24 | 21.48 | Tier 1B: High GIDA Priority | 53.06 | 53.06 | 78.15 | 65.6 | F - Nearest node and line over 5 km | 17.24 | 21.48 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 289
1 | 290 | 290 | 1380900009 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Kaunlaran | 14.6673 | 120.9407 | U | 22647 | 3.37 | 6722 | 2017 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.82 | 0.69 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.83 | 65.83 | 65.35 | 65.59 | B - Node 0.5-1 km | 0.82 | 0.7 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 290
1 | 291 | 291 | 0405802017 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Santa Cruz | 14.6153 | 121.1708 | U | 62537 | 3.6 | 17371 | 5211 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.63 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.4 | 56.4 | 74.69 | 65.55 | B - Node 0.5-1 km | 0.63 | 0.17 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 291
1 | 292 | 292 | 1380900014 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tanza 1 | 14.6525 | 120.9345 | U | 15795 | 3.3 | 4781 | 1434 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.35 | 2.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.77 | 63.77 | 67.3 | 65.54 | D - Other node or line within 3 km | 1.35 | 2.32 | Node: NAV001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 292
1 | 293 | 293 | 1004325016 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Sibantang | 8.9827 | 124.9022 | R | 896 | 3.9 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.94 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.68 | 54.68 | 76.37 | 65.53 | C - Line within 0.5 km; node over 1 km | 2.94 | 0.21 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 293
1 | 294 | 294 | 1403215001 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Ambato Legleg | 17.2719 | 121.1562 | R | 410 | 4.3 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.67 | 53.67 | 77.39 | 65.53 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.18 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 294
1 | 295 | 295 | 1381100178 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 178 | 14.5312 | 121.2345 | U | 4496 | 3.68 | 1221 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.25 | 58.25 | 72.77 | 65.51 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.41 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 295
1 | 296 | 296 | 0301412015 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Malhacan | 14.7399 | 120.9637 | U | 22515 | 3.5 | 6433 | 1930 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.55 | 0.38 | Tier 1B: High GIDA Priority | 71.14 | 71.14 | 59.86 | 65.5 | B - Node 0.5-1 km | 0.55 | 0.36 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 296
1 | 297 | 297 | 1381300102 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Roque | 14.6171 | 121.0632 | U | 19654 | 3.85 | 5110 | 1533 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.67 | 0.28 | Tier 1B: High GIDA Priority | 68.15 | 68.15 | 62.83 | 65.49 | B - Node 0.5-1 km | 0.67 | 0.28 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 297
1 | 298 | 298 | 1380900011 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Rafael Village | 14.6371 | 120.9644 | U | 3346 | 3.32 | 1009 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.49 | 0.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.11 | 57.11 | 73.87 | 65.49 | D - Other node or line within 3 km | 1.49 | 1.45 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 298
1 | 299 | 299 | 1380500018 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Namayan | 14.5803 | 121.0186 | U | 8185 | 3.33 | 2459 | 738 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.13 | 62.13 | 68.84 | 65.48 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.46 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 299
1 | 300 | 300 | 1381200028 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Sumilang | 14.5892 | 121.0913 | U | 4499 | 3.41 | 1318 | 395 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.57 | 58.57 | 72.38 | 65.48 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.12 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 300
1 | 301 | 301 | 0102908017 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Malaya | 16.9742 | 120.6997 | R | 1893 | 3.8 | 498 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.18 | 3.75 | Tier 1B: High GIDA Priority | 56.52 | 56.52 | 74.42 | 65.47 | E - Nearest node or line 3-5 km | 3.18 | 3.51 | Node: CVI001 - TYPE 2 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 301
1 | 302 | 302 | 0301412006 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Calvario | 14.7335 | 120.961 | U | 5304 | 3.5 | 1515 | 454 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.31 | 64.31 | 66.62 | 65.46 | B - Node 0.5-1 km | 0.96 | 0.05 | Line: GOTACO TO HH 71 BULACAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 302
1 | 303 | 303 | 1381300105 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Lucia | 14.7073 | 121.0526 | U | 28974 | 4.06 | 7138 | 2141 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.95 | 0.96 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.35 | 63.35 | 67.54 | 65.45 | D - Other node or line within 3 km | 1.95 | 0.96 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 303
1 | 304 | 304 | 1380700006 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Nangka | 14.6732 | 121.1084 | U | 43661 | 3.99 | 10940 | 3282 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.44 | 0.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.44 | 59.44 | 71.44 | 65.44 | C - Line within 0.5 km; node over 1 km | 1.44 | 0.14 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 304
1 | 305 | 305 | 0103315002 | Region I (Ilocos Region) | La Union | San Gabriel | Amontoc | 16.6569 | 120.4658 | R | 2058 | 3.7 | 556 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.88 | 13.32 | Tier 1B: High GIDA Priority | 54.96 | 54.96 | 75.93 | 65.44 | F - Nearest node and line over 5 km | 7.88 | 13.32 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 305
1 | 306 | 306 | 1381100014 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 14 | 14.528 | 121.0227 | U | 4807 | 3.39 | 1416 | 425 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.87 | 59.87 | 71 | 65.43 | B - Node 0.5-1 km | 0.66 | 0.1 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 306
1 | 307 | 307 | 1381300074 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pag-ibig Sa Nayon | 14.6466 | 120.9965 | U | 6279 | 3.12 | 2011 | 603 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 1.02 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.81 | 60.81 | 70.02 | 65.42 | D - Other node or line within 3 km | 1.08 | 1.02 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 307
1 | 308 | 308 | 1381300135 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Balong Bato | 14.6636 | 121.0031 | U | 7205 | 3.79 | 1902 | 571 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.21 | 60.21 | 70.59 | 65.4 | D - Other node or line within 3 km | 1.23 | 0.61 | Line: Aerial 216C MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 308
1 | 309 | 309 | 1380400017 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Santolan | 14.6854 | 120.9589 | U | 13736 | 3.58 | 3840 | 1152 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.4 | 0.19 | Tier 1B: High GIDA Priority | 67.55 | 67.55 | 63.23 | 65.39 | A - Node within 0.5 km | 0.4 | 0.26 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 309
1 | 310 | 310 | 1380500010 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Hagdang Bato Itaas | 14.5896 | 121.0308 | U | 10303 | 3.39 | 3037 | 911 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.53 | 64.53 | 66.26 | 65.39 | B - Node 0.5-1 km | 0.72 | 0.23 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 310
1 | 311 | 311 | 0402104010 | Region IV-A (CALABARZON) | Cavite | Carmona | Maduya | 14.3169 | 121.0608 | U | 11154 | 3.4 | 3281 | 984 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.21 | Tier 1B: High GIDA Priority | 70.17 | 70.17 | 60.59 | 65.38 | B - Node 0.5-1 km | 0.64 | 0.16 | Line: AE CRC005-BNL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 311
1 | 312 | 312 | 0402104011 | Region IV-A (CALABARZON) | Cavite | Carmona | Milagrosa | 14.3083 | 121.0494 | U | 25103 | 3.4 | 7383 | 2215 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.29 | 0.29 | Tier 1B: High GIDA Priority | 70.08 | 70.08 | 60.68 | 65.38 | A - Node within 0.5 km | 0.29 | 0.29 | Node: CRC005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 312
1 | 313 | 313 | 1380200001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Almanza Uno | 14.4319 | 121.0133 | U | 33683 | 3.15 | 10707 | 3212 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.5 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.52 | 61.52 | 69.23 | 65.38 | A - Node within 0.5 km | 0.5 | 0.06 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 313
1 | 314 | 314 | 0405805018 | Region IV-A (CALABARZON) | Rizal | Cainta | Santa Rosa | 14.5821 | 121.1181 | R | 1550 | 3.6 | 431 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.65 | 57.65 | 73.1 | 65.38 | B - Node 0.5-1 km | 0.6 | 0.35 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 314
1 | 315 | 315 | 0600402010 | Region VI (Western Visayas) | Aklan | Balete | Oquendo | 11.5304 | 122.3872 | R | 1064 | 3.9 | 273 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.24 | 2.84 | Tier 1B: High GIDA Priority | 52.88 | 52.88 | 77.88 | 65.38 | D - Other node or line within 3 km | 3.24 | 2.78 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 315
1 | 316 | 316 | 0201529029 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Namabbalan Norte | 17.6378 | 121.7272 | R | 1566 | 3.9 | 402 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 0.98 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.71 | 53.71 | 77 | 65.36 | D - Other node or line within 3 km | 2.6 | 0.98 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 316
1 | 317 | 317 | 1381300035 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | E. Rodriguez | 14.6225 | 121.051 | U | 19291 | 3.34 | 5772 | 1732 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.77 | 0.1 | Tier 1B: High GIDA Priority | 67.12 | 67.12 | 63.51 | 65.31 | B - Node 0.5-1 km | 0.77 | 0.05 | Line: UG 144C via R-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 317
1 | 318 | 318 | 0405804040 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pag-Asa | 14.527 | 121.1605 | U | 18644 | 3.6 | 5179 | 1554 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.63 | 0.63 | Tier 1B: High GIDA Priority | 72.24 | 72.24 | 58.36 | 65.3 | B - Node 0.5-1 km | 0.63 | 0.63 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 318
1 | 319 | 319 | 1380700003 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Concepcion Uno | 14.6478 | 121.1035 | U | 46629 | 3.99 | 11672 | 3502 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.9 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.51 | 59.51 | 71.08 | 65.29 | B - Node 0.5-1 km | 0.9 | 0.25 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 319
1 | 320 | 320 | 1004322001 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Alipuaton | 8.8681 | 124.8087 | R | 1103 | 3.9 | 283 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 2.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.91 | 52.91 | 77.66 | 65.29 | D - Other node or line within 3 km | 2.6 | 2.08 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 320
1 | 321 | 321 | 0402118051 | Region IV-A (CALABARZON) | Cavite | Silang | Ipil I | 14.2739 | 120.9947 | R | 3128 | 3.4 | 920 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 2.95 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.78 | 65.78 | 64.78 | 65.28 | D - Other node or line within 3 km | 1.23 | 2.94 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 321
1 | 322 | 322 | 1380612011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 843 | 13.8363 | 122.9435 | U | 9355 | 4.2 | 2229 | 669 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 1.67 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.56 | 59.56 | 70.97 | 65.26 | D - Other node or line within 3 km | 2.23 | 1.67 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 322
1 | 323 | 323 | 0500518018 | Region V (Bicol Region) | Albay | Tiwi | Maynonong | 13.4975 | 123.6175 | R | 990 | 4.1 | 241 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.65 | 53.65 | 76.86 | 65.26 | C - Line within 0.5 km; node over 1 km | 1.46 | 0.11 | Line: LEGAZP - TIWI AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 323
1 | 324 | 324 | 1403213038 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Lacnog | 17.398 | 121.5131 | R | 3315 | 4.3 | 771 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 4.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.28 | 60.28 | 70.22 | 65.25 | D - Other node or line within 3 km | 2.49 | 4.42 | Node: TKK004 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 324
1 | 325 | 325 | 0402106032 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz I | 14.3112 | 120.9361 | R | 3486 | 3.4 | 1025 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 1.94 | Tier 1B: High GIDA Priority | 67.29 | 67.29 | 63.19 | 65.24 | D - Other node or line within 3 km | 2.74 | 1.94 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 325
1 | 326 | 326 | 1381100081 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 81 | 14.4401 | 121.0037 | U | 2479 | 2.62 | 945 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.34 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.15 | 59.15 | 71.33 | 65.24 | A - Node within 0.5 km | 0.34 | 0.2 | Line: UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 326
1 | 327 | 327 | 0402106042 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Fe | 14.346 | 120.9648 | U | 6647 | 3.4 | 1955 | 586 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.76 | 4.86 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.12 | 59.12 | 71.35 | 65.24 | D - Other node or line within 3 km | 2.76 | 4.99 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 327
1 | 328 | 328 | 0301412008 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Hulo | 14.7425 | 120.9708 | U | 2804 | 3.5 | 801 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 1.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.41 | 60.41 | 70.01 | 65.21 | B - Node 0.5-1 km | 0.52 | 1.16 | Node: MEB003 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 328
1 | 329 | 329 | 0402118049 | Region IV-A (CALABARZON) | Cavite | Silang | Acacia | 14.1975 | 120.9893 | U | 10181 | 3.4 | 2994 | 898 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 2.56 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.53 | 62.53 | 67.86 | 65.2 | D - Other node or line within 3 km | 2.6 | 2.56 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 329
1 | 330 | 330 | 0307702022 | Region III (Central Luzon) | Aurora | Casiguran | Ditinagyan | 16.2457 | 122.0808 | R | 404 | 3.8 | 106 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.98 | 0.31 | Tier 1B: High GIDA Priority | 43.43 | 43.43 | 86.97 | 65.2 | F - Nearest node and line over 5 km | 5.98 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 330
1 | 331 | 331 | 1403209006 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ballayangon | 17.5565 | 121.3176 | R | 1341 | 4.3 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.45 | 11.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.38 | 48.38 | 82 | 65.19 | D - Other node or line within 3 km | 2.45 | 11.53 | Node: PKK002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 331
1 | 332 | 332 | 0402111017 | Region IV-A (CALABARZON) | Cavite | Kawit | Manggahan-Lawin | 14.4504 | 120.8917 | R | 4886 | 3.4 | 1437 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 2.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 65.37 | 65.37 | 64.94 | 65.15 | D - Other node or line within 3 km | 2.5 | 2.05 | Line: KAWIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 332
1 | 333 | 333 | 1380500009 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Daang Bakal | 14.5892 | 121.0288 | U | 4648 | 3.36 | 1384 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.83 | 59.83 | 70.44 | 65.13 | B - Node 0.5-1 km | 0.63 | 0.37 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 333
1 | 334 | 334 | 1381300099 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Isidro Labrador | 14.6852 | 120.9845 | U | 6419 | 3 | 2140 | 642 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.35 | 61.35 | 68.89 | 65.12 | B - Node 0.5-1 km | 0.99 | 0.16 | Line: Aerial 96C | Survey short node lateral; confirm port/fiber capacity, access and route. | 334
1 | 335 | 335 | 0403425028 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Rosario | 14.2236 | 121.1181 | U | 6479 | 3.3 | 1963 | 589 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 1.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.58 | 64.58 | 65.59 | 65.09 | D - Other node or line within 3 km | 1.46 | 1.44 | Line: AE CLB001 TO CLB002 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 335
1 | 336 | 336 | 1380700008 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | San Roque | 14.6228 | 121.0971 | U | 17268 | 3.92 | 4407 | 1322 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.62 | 0.27 | Tier 1B: High GIDA Priority | 66.93 | 66.93 | 63.23 | 65.08 | C - Line within 0.5 km; node over 1 km | 1.62 | 0.14 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 336
1 | 337 | 337 | 0402103021 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas I | 14.2885 | 120.9312 | U | 8425 | 3.4 | 2478 | 743 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.37 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.74 | 64.74 | 65.42 | 65.08 | C - Line within 0.5 km; node over 1 km | 2.37 | 0.35 | Line: NCC001 TO TGY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 337
1 | 338 | 338 | 1403211016 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Bulbol | 17.5416 | 121.5767 | R | 1062 | 3.6 | 295 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.24 | 5.1 | Tier 1B: High GIDA Priority | 49.63 | 49.63 | 80.52 | 65.08 | F - Nearest node and line over 5 km | 5.24 | 5.1 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 338
1 | 339 | 339 | 0604528038 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12 | 10.7394 | 122.9686 | R | 2653 | 3.7 | 717 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.11 | Tier 1B: High GIDA Priority | 66.89 | 66.89 | 63.24 | 65.06 | A - Node within 0.5 km | 0.17 | 0.11 | Line: FOC 144C TALISAY CLS TO BACONG CLS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 339
1 | 340 | 340 | 0105527020 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cabaluyan 2nd | 15.6903 | 120.3343 | R | 1128 | 3.6 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.93 | 8.66 | Tier 1B: High GIDA Priority | 46.29 | 46.29 | 83.77 | 65.03 | E - Nearest node or line 3-5 km | 3.93 | 8.65 | Node: SCT001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 340
1 | 341 | 341 | 0702232019 | Region VII (Central Visayas) | Cebu | Minglanilla | Tungkil | 10.2407 | 123.8124 | U | 13904 | 3.8 | 3659 | 1098 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.57 | 0.64 | Tier 1B: High GIDA Priority | 71.57 | 71.57 | 58.45 | 65.01 | D - Other node or line within 3 km | 1.57 | 0.64 | Line: 96c | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 341
1 | 342 | 342 | 0603018031 | Region VI (Western Visayas) | Iloilo | Dumangas | Nanding Lopez | 10.8805 | 122.7712 | R | 1881 | 3.8 | 495 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.44 | 6.29 | Tier 1B: High GIDA Priority | 50.73 | 50.73 | 79.27 | 65 | F - Nearest node and line over 5 km | 7.44 | 6.29 | Line: DUMANGAS CO-BAROTAC NUEVO CO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 342
1 | 343 | 343 | 0402106049 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol III | 14.3494 | 120.9436 | U | 11497 | 3.4 | 3381 | 1014 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.45 | 5.41 | Tier 1B: High GIDA Priority | 67.38 | 67.38 | 62.6 | 64.99 | A - Node within 0.5 km | 0.45 | 5.35 | Node: DMC006 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 343
1 | 344 | 344 | 1381200008 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kapasigan | 14.5762 | 121.0797 | U | 4952 | 3.26 | 1518 | 455 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.54 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.42 | 60.42 | 69.51 | 64.96 | B - Node 0.5-1 km | 0.53 | 0.31 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 344
1 | 345 | 345 | 1380300027 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Singkamas | 14.573 | 121.0103 | U | 7485 | 3.88 | 1930 | 579 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.8 | 59.8 | 70.12 | 64.96 | C - Line within 0.5 km; node over 1 km | 1.51 | 0.23 | Line: UG 288C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 345
1 | 346 | 346 | 0402106046 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño I | 14.3323 | 120.9927 | R | 3010 | 3.4 | 885 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 2.96 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.67 | 64.67 | 65.21 | 64.94 | D - Other node or line within 3 km | 1.66 | 5.03 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 346
1 | 347 | 347 | 1381300098 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Isidro | 14.609 | 121.0751 | U | 6794 | 3.69 | 1840 | 552 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.03 | 61.03 | 68.86 | 64.94 | B - Node 0.5-1 km | 0.7 | 0.48 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 347
1 | 348 | 348 | 1380400013 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Niugan | 14.6675 | 120.955 | U | 7529 | 3.89 | 1933 | 580 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.97 | 60.97 | 68.9 | 64.94 | B - Node 0.5-1 km | 0.87 | 0.38 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 348
1 | 349 | 349 | 1381100132 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 132 | 14.548 | 121.0063 | U | 3967 | 3.03 | 1309 | 393 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.71 | 59.71 | 70.15 | 64.93 | B - Node 0.5-1 km | 0.58 | 0.24 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 349
1 | 350 | 350 | 1380700014 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Industrial Valley | 14.6216 | 121.0804 | U | 16678 | 4.05 | 4115 | 1234 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.32 | 1.31 | Tier 1B: High GIDA Priority | 66.57 | 66.57 | 63.26 | 64.92 | D - Other node or line within 3 km | 1.32 | 0.96 | Line: UG 144C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 350
1 | 351 | 351 | 1381300094 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Salvacion | 14.7219 | 121.0618 | U | 6861 | 3.72 | 1843 | 553 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.48 | 60.48 | 69.35 | 64.91 | B - Node 0.5-1 km | 0.99 | 0.85 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 351
1 | 352 | 352 | 1381100046 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 46 | 14.5991 | 121.0198 | U | 5864 | 3.69 | 1588 | 476 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.51 | 58.51 | 71.3 | 64.9 | D - Other node or line within 3 km | 1.68 | 0.61 | Line: UG 288C via W-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 352
1 | 353 | 353 | 1380500016 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Malamig | 14.594 | 121.0396 | U | 14489 | 2.8 | 5171 | 1551 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.58 | 0.11 | Tier 1B: High GIDA Priority | 68.25 | 68.25 | 61.54 | 64.89 | B - Node 0.5-1 km | 0.58 | 0.11 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 353
1 | 354 | 354 | 1381701009 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santo Rosario-Silangan | 14.5371 | 121.0664 | U | 4744 | 4.03 | 1176 | 353 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.74 | 58.74 | 71.04 | 64.89 | B - Node 0.5-1 km | 0.87 | 0.14 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 354
1 | 355 | 355 | 0403428015 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Kanluran | 14.2957 | 121.0959 | U | 4643 | 3.3 | 1407 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.54 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.62 | 63.62 | 66.12 | 64.87 | D - Other node or line within 3 km | 1.04 | 0.54 | Line: AE SRL007-CBL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 355
1 | 356 | 356 | 1381300073 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paang Bundok | 14.7129 | 121.0412 | U | 4900 | 3.71 | 1322 | 397 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.99 | 58.99 | 70.72 | 64.86 | B - Node 0.5-1 km | 0.96 | 0.19 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 356
1 | 357 | 357 | 0506215012 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Rafael | 12.6636 | 124.1285 | R | 1362 | 4 | 340 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.18 | 1.67 | Tier 1B: High GIDA Priority | 57.94 | 57.94 | 71.76 | 64.85 | D - Other node or line within 3 km | 3.18 | 1.67 | Line: STA MAGDALENA CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 357
1 | 358 | 358 | 0201515021 | Region II (Cagayan Valley) | Cagayan | Iguig | San Lorenzo | 17.7366 | 121.7271 | R | 482 | 3.9 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.36 | 1.18 | Tier 1B: High GIDA Priority | 48.96 | 48.96 | 80.74 | 64.85 | D - Other node or line within 3 km | 4.36 | 1.18 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 358
1 | 359 | 359 | 1380400019 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tinajeros | 14.6713 | 120.9699 | U | 18677 | 3.49 | 5349 | 1605 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.45 | 0.22 | Tier 1B: High GIDA Priority | 68.31 | 68.31 | 61.37 | 64.84 | A - Node within 0.5 km | 0.45 | 0.18 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 359
1 | 360 | 360 | 1403209003 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ammacian | 17.6089 | 121.3447 | R | 1731 | 4.3 | 403 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.77 | 6.65 | Tier 1B: High GIDA Priority | 47.72 | 47.72 | 81.95 | 64.83 | F - Nearest node and line over 5 km | 5.77 | 6.59 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 360
1 | 361 | 361 | 0405813003 | Region IV-A (CALABARZON) | Rizal | Taytay | San Isidro | 14.5728 | 121.1314 | U | 39685 | 3.6 | 11024 | 3307 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.36 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.25 | 63.25 | 66.39 | 64.82 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.23 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 361
1 | 362 | 362 | 1380300012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | La Paz | 14.5694 | 121.0067 | U | 6682 | 3.14 | 2127 | 638 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.61 | 60.61 | 69.01 | 64.81 | C - Line within 0.5 km; node over 1 km | 1.38 | 0.14 | Line: UG 288C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 362
1 | 363 | 363 | 1381100187 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 187 | 14.5332 | 121.0006 | U | 5321 | 3.65 | 1458 | 437 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.91 | 59.91 | 69.69 | 64.8 | B - Node 0.5-1 km | 0.7 | 0.26 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 363
1 | 364 | 364 | 0300809010 | Region III (Central Luzon) | Bataan | Orani | Mulawin | 14.8052 | 120.5009 | R | 4958 | 3.6 | 1377 | 413 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.51 | 1.13 | Tier 1B: High GIDA Priority | 67.68 | 67.68 | 61.89 | 64.79 | D - Other node or line within 3 km | 3.51 | 1.13 | Line: ORANI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 364
1 | 365 | 365 | 0301412021 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saluysoy | 14.7435 | 120.9556 | U | 11523 | 3.5 | 3292 | 988 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.36 | Tier 1B: High GIDA Priority | 70.26 | 70.26 | 59.28 | 64.77 | B - Node 0.5-1 km | 0.69 | 0.36 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 365
1 | 366 | 366 | 0402111015 | Region IV-A (CALABARZON) | Cavite | Kawit | Binakayan-Aplaya | 14.4286 | 120.914 | R | 3521 | 3.4 | 1036 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 1.24 | Tier 1B: High GIDA Priority | 66.61 | 66.61 | 62.92 | 64.77 | D - Other node or line within 3 km | 3.33 | 1.24 | Line: KAWIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 366
1 | 367 | 367 | 1380900013 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tangos South | 14.6555 | 120.9582 | U | 18971 | 3.45 | 5496 | 1649 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.51 | 0.13 | Tier 1B: High GIDA Priority | 67.99 | 67.99 | 61.52 | 64.76 | B - Node 0.5-1 km | 0.51 | 1.52 | Node: MAL004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 367
1 | 368 | 368 | 0102916004 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Baluarte | 17.0999 | 120.5209 | R | 671 | 3.8 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 6.6 | Tier 1B: High GIDA Priority | 45.76 | 45.76 | 83.76 | 64.76 | F - Nearest node and line over 5 km | 5.83 | 6.59 | Node: SDI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 368
1 | 369 | 369 | 0402106071 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz II | 14.3589 | 120.9252 | R | 4500 | 3.4 | 1324 | 397 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.82 | 7.06 | Tier 1B: High GIDA Priority | 66.03 | 66.03 | 63.47 | 64.75 | D - Other node or line within 3 km | 1.82 | 7.01 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 369
1 | 370 | 370 | 1102319026 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo West | 7.4336 | 125.7916 | U | 13141 | 3.7 | 3552 | 1066 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.37 | 0.72 | Tier 1B: High GIDA Priority | 70.89 | 70.89 | 58.6 | 64.74 | D - Other node or line within 3 km | 1.37 | 0.64 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 370
1 | 371 | 371 | 0600410020 | Region VI (Western Visayas) | Aklan | Madalag | Poblacion | 11.5275 | 122.3058 | R | 1870 | 3.9 | 479 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.24 | 7.6 | Tier 1B: High GIDA Priority | 53.95 | 53.95 | 75.52 | 64.74 | F - Nearest node and line over 5 km | 8.24 | 7.59 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 371
1 | 372 | 372 | 0600402005 | Region VI (Western Visayas) | Aklan | Balete | Cortes | 11.5286 | 122.3974 | R | 3645 | 3.9 | 935 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.98 | 3.39 | Tier 1B: High GIDA Priority | 66.93 | 66.93 | 62.54 | 64.73 | E - Nearest node or line 3-5 km | 3.98 | 3.39 | Line: IVISAN - KALIBO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 372
1 | 373 | 373 | 0403425016 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Vicente | 14.315 | 121.4315 | U | 30211 | 3.3 | 9155 | 2746 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 3.83 | 3.9 | Tier 1B: High GIDA Priority | 58.88 | 58.88 | 70.59 | 64.73 | E - Nearest node or line 3-5 km | 3.83 | 3.9 | Node: LML002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 373
1 | 374 | 374 | 0405804007 | Region IV-A (CALABARZON) | Rizal | Binangonan | Calumpang | 14.4777 | 121.1888 | U | 18277 | 3.6 | 5077 | 1523 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.28 | 0.14 | Tier 1B: High GIDA Priority | 71.12 | 71.12 | 58.31 | 64.72 | C - Line within 0.5 km; node over 1 km | 1.28 | 0.05 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 374
1 | 375 | 375 | 1381300089 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Ramon Magsaysay | 14.6616 | 121.0218 | U | 16641 | 3.38 | 4929 | 1479 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.17 | 0.17 | Tier 1B: High GIDA Priority | 69.44 | 69.44 | 59.93 | 64.69 | A - Node within 0.5 km | 0.17 | 0.17 | Node: QCY003 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 375
1 | 376 | 376 | 1381300109 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santo Niño | 14.6294 | 121.1069 | U | 7646 | 3.88 | 1969 | 591 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.75 | 59.75 | 69.57 | 64.66 | C - Line within 0.5 km; node over 1 km | 1.61 | 0.49 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 376
1 | 377 | 377 | 0405625013 | Region IV-A (CALABARZON) | Quezon | Macalelon | Olongtao Ilaya | 13.7202 | 122.1985 | R | 747 | 3.8 | 197 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.06 | 1.9 | Tier 1B: High GIDA Priority | 50.82 | 50.82 | 78.5 | 64.66 | D - Other node or line within 3 km | 4.06 | 1.9 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 377
1 | 378 | 378 | 1381100183 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 183 | 14.5239 | 121.0131 | U | 41113 | 3.31 | 12409 | 3723 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.35 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.71 | 59.71 | 69.6 | 64.65 | A - Node within 0.5 km | 0.35 | 0.12 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 378
1 | 379 | 379 | 1381100171 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 171 | 14.7513 | 120.9555 | U | 3492 | 3.35 | 1043 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.71 | 59.71 | 69.57 | 64.64 | A - Node within 0.5 km | 0.21 | 0.1 | Line: Mnla Pipe | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 379
1 | 380 | 380 | 0405801012 | Region IV-A (CALABARZON) | Rizal | Angono | San Vicente | 14.523 | 121.1468 | U | 13646 | 3.6 | 3791 | 1137 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.99 | 0.68 | Tier 1B: High GIDA Priority | 71.05 | 71.05 | 58.21 | 64.63 | B - Node 0.5-1 km | 0.99 | 0.66 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 380
1 | 381 | 381 | 1208001011 | Region XII (SOCCSKSARGEN) | Sarangani | Alabel | Spring | 6.076 | 125.3154 | U | 5630 | 3.9 | 1444 | 433 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.24 | 14.03 | Tier 1B: High GIDA Priority | 57.2 | 57.2 | 72.07 | 64.63 | F - Nearest node and line over 5 km | 5.24 | 13.99 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 381
1 | 382 | 382 | 1204704032 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Poblacion | 7.0067 | 125.0899 | U | 23166 | 3.8 | 6096 | 1829 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.36 | 0.12 | Tier 2A: High Commercial ROI | 74.94 | 74.94 | 54.3 | 64.62 | A - Node within 0.5 km | 0.36 | 0.1 | Line: QUIRINO - KIDAPAWAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 382
1 | 383 | 383 | 1380900016 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Proper | 14.644 | 120.9527 | U | 18689 | 3.49 | 5356 | 1607 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.49 | 0.65 | Tier 1B: High GIDA Priority | 66.31 | 66.31 | 62.94 | 64.62 | D - Other node or line within 3 km | 1.49 | 2.79 | Node: NAV001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 383
1 | 384 | 384 | 1380200009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Zapote | 14.4639 | 120.9708 | U | 19994 | 3.82 | 5239 | 1572 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.28 | 0.21 | Tier 1B: High GIDA Priority | 68.81 | 68.81 | 60.42 | 64.61 | A - Node within 0.5 km | 0.28 | 0.14 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 384
1 | 385 | 385 | 1380500002 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Bagong Silang | 14.5769 | 121.038 | U | 4349 | 3.24 | 1344 | 403 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.42 | 58.42 | 70.8 | 64.61 | C - Line within 0.5 km; node over 1 km | 1.31 | 0.13 | Line: Aerial 216C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 385
1 | 386 | 386 | 0402104012 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 1 | 14.2989 | 121.049 | R | 3303 | 3.4 | 971 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 1.34 | Tier 1B: High GIDA Priority | 69.54 | 69.54 | 59.64 | 64.59 | D - Other node or line within 3 km | 1.17 | 1.34 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 386
1 | 387 | 387 | 1401108002 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Beleng-Belis | 16.6489 | 120.6401 | R | 793 | 3.5 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.49 | 12.96 | Tier 1B: High GIDA Priority | 47.74 | 47.74 | 81.41 | 64.57 | F - Nearest node and line over 5 km | 5.49 | 12.87 | Node: KIB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 387
1 | 388 | 388 | 0500502001 | Region V (Bicol Region) | Albay | Camalig | Anoling | 13.1283 | 123.6388 | R | 1060 | 4.1 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.41 | 5.55 | Tier 1B: High GIDA Priority | 46.95 | 46.95 | 82.19 | 64.57 | E - Nearest node or line 3-5 km | 4.41 | 5.53 | Node: GNA002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 388
1 | 389 | 389 | 0504111030 | Region V (Bicol Region) | Masbate | City of Masbate | Usab | 12.3307 | 123.5803 | R | 3146 | 4.1 | 767 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.97 | 0.48 | Tier 1B: High GIDA Priority | 61.39 | 61.39 | 67.73 | 64.56 | C - Line within 0.5 km; node over 1 km | 4.97 | 0.45 | Line: MASBATE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 389
1 | 390 | 390 | 1381200019 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Antonio | 14.5668 | 121.0846 | U | 14904 | 3.59 | 4156 | 1247 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.33 | 0.29 | Tier 1B: High GIDA Priority | 68.65 | 68.65 | 60.45 | 64.55 | A - Node within 0.5 km | 0.33 | 0.13 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 390
1 | 391 | 391 | 0501730024 | Region V (Bicol Region) | Camarines Sur | Ragay | Lower Santa Cruz | 13.8166 | 122.7976 | R | 1448 | 4.2 | 345 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.87 | 56.87 | 72.23 | 64.55 | C - Line within 0.5 km; node over 1 km | 1 | 0.1 | Line: CALAUAG - SIPOCOT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 391
1 | 392 | 392 | 0402106039 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Simon | 14.3213 | 120.9714 | U | 6571 | 3.4 | 1933 | 580 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 2.82 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.51 | 61.51 | 67.57 | 64.54 | D - Other node or line within 3 km | 1.17 | 2.81 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 392
1 | 393 | 393 | 1705213002 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Calangatan | 13.3701 | 120.9657 | R | 2758 | 3.9 | 707 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.32 | 8.06 | Tier 1B: High GIDA Priority | 57.5 | 57.5 | 71.58 | 64.54 | F - Nearest node and line over 5 km | 9.32 | 8.02 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 393
1 | 394 | 394 | 0300803022 | Region III (Central Luzon) | Bataan | City of Balanga | Tortugas | 14.6928 | 120.5601 | R | 2979 | 3.6 | 828 | 248 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 1.65 | Tier 1B: High GIDA Priority | 66.16 | 66.16 | 62.89 | 64.52 | D - Other node or line within 3 km | 1.89 | 1.64 | Line: CITY OF BALANGA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 394
1 | 395 | 395 | 1102403030 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 3 | 6.7442 | 125.3591 | U | 18722 | 3.4 | 5506 | 1652 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.89 | 0.56 | Tier 2A: High Commercial ROI | 74.52 | 74.52 | 54.5 | 64.51 | B - Node 0.5-1 km | 0.89 | 0.56 | Line: Digos to POI of existing aerial 96F | Survey short node lateral; confirm port/fiber capacity, access and route. | 395
1 | 396 | 396 | 0300803010 | Region III (Central Luzon) | Bataan | City of Balanga | Dangcol | 14.6637 | 120.4686 | R | 1855 | 3.6 | 515 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.89 | 3.51 | Tier 1B: High GIDA Priority | 49.28 | 49.28 | 79.75 | 64.51 | E - Nearest node or line 3-5 km | 7.89 | 3.5 | Line: Bagac-Pilar AERIAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 396
1 | 397 | 397 | 0301411015 | Region III (Central Luzon) | Bulacan | Marilao | Saog | 14.7647 | 120.9558 | U | 16319 | 3.5 | 4663 | 1399 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.67 | 0.5 | Tier 1B: High GIDA Priority | 71.33 | 71.33 | 57.67 | 64.5 | D - Other node or line within 3 km | 1.67 | 0.63 | Line: BOCAUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 397
1 | 398 | 398 | 1380400020 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tonsuya | 14.6636 | 120.9575 | U | 41669 | 3.85 | 10822 | 3247 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.43 | 0.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.52 | 61.52 | 67.47 | 64.49 | A - Node within 0.5 km | 0.43 | 0.77 | Node: MAL004 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 398
1 | 399 | 399 | 0402106027 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Dionisio | 14.3199 | 120.9786 | U | 7096 | 3.4 | 2087 | 626 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 3.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.26 | 63.26 | 65.69 | 64.48 | B - Node 0.5-1 km | 0.51 | 3.16 | Node: DMC005 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 399
1 | 400 | 400 | 1380500012 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Harapin Ang Bukas | 14.5745 | 121.0226 | U | 4021 | 3.8 | 1058 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.11 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.92 | 57.92 | 71.03 | 64.48 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.11 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 400
1 | 401 | 401 | 0402103064 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas II | 14.2529 | 120.8194 | U | 12673 | 3.4 | 3727 | 1118 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.93 | 3.98 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 64.37 | 64.37 | 64.56 | 64.46 | D - Other node or line within 3 km | 2.93 | 3.97 | Node: MRC002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 401
1 | 402 | 402 | 0403403002 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Bungahan | 14.3024 | 121.0728 | R | 4179 | 3.3 | 1266 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 1.3 | Tier 1B: High GIDA Priority | 69.97 | 69.97 | 58.93 | 64.45 | D - Other node or line within 3 km | 1.45 | 1.3 | Line: AE CRC005-BNL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 402
1 | 403 | 403 | 0401005075 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 6 | 13.7603 | 121.0637 | R | 1864 | 3.6 | 518 | 155 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.66 | 59.66 | 69.23 | 64.45 | B - Node 0.5-1 km | 0.78 | 0.08 | Line: LEMERY TO SAN JUAN CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 403
1 | 404 | 404 | 1380200015 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pilar | 14.4123 | 121.0059 | U | 31420 | 3.84 | 8176 | 2453 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.87 | 1.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.18 | 62.18 | 66.7 | 64.44 | D - Other node or line within 3 km | 1.87 | 1.8 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 404
1 | 405 | 405 | 0403405013 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Halang | 14.1978 | 121.1603 | U | 9407 | 3.3 | 2851 | 855 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 0.27 | Tier 1B: High GIDA Priority | 67.21 | 67.21 | 61.66 | 64.43 | C - Line within 0.5 km; node over 1 km | 1.52 | 0.2 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 405
1 | 406 | 406 | 0402106037 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas I | 14.3151 | 120.9685 | R | 2180 | 3.4 | 641 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 2.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.27 | 60.27 | 68.59 | 64.43 | A - Node within 0.5 km | 0.42 | 2.06 | Node: DMC004 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 406
1 | 407 | 407 | 0201514014 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Magrafil | 18.2762 | 122.075 | R | 1256 | 3.9 | 322 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.15 | 4.81 | Tier 1B: High GIDA Priority | 43.82 | 43.82 | 85.03 | 64.43 | E - Nearest node or line 3-5 km | 8.15 | 4.8 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 407
1 | 408 | 408 | 1403213043 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Ipil | 17.439 | 121.4846 | R | 3410 | 4.3 | 793 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.57 | 0.95 | Tier 1B: High GIDA Priority | 62.2 | 62.2 | 66.64 | 64.42 | D - Other node or line within 3 km | 4.57 | 0.95 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 408
1 | 409 | 409 | 1108204019 | Region XI (Davao Region) | Davao de Oro | Maco | Malamodao | 7.3685 | 125.9713 | R | 2703 | 3.7 | 731 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.78 | 12.69 | Tier 1B: High GIDA Priority | 50.57 | 50.57 | 78.21 | 64.39 | F - Nearest node and line over 5 km | 12.78 | 12.67 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 409
1 | 410 | 410 | 1381100013 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 13 | 14.5616 | 120.999 | U | 2949 | 2.66 | 1109 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 0.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.91 | 57.91 | 70.86 | 64.38 | C - Line within 0.5 km; node over 1 km | 1.21 | 0.34 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 410
1 | 411 | 411 | 0506210013 | Region V (Bicol Region) | Sorsogon | Juban | Embarcadero | 12.8549 | 123.9884 | R | 1368 | 4 | 342 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 0.71 | Tier 1B: High GIDA Priority | 57.79 | 57.79 | 70.97 | 64.38 | D - Other node or line within 3 km | 3.38 | 0.71 | Line: SORSOGON - MATNOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 411
1 | 412 | 412 | 1402706015 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Inwaloy | 16.9737 | 121.1939 | R | 393 | 3.9 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.96 | 14.94 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.51 | 47.51 | 81.25 | 64.38 | D - Other node or line within 3 km | 2.96 | 17.78 | Node: MOF001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 412
1 | 413 | 413 | 1208004009 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Lumasal | 5.8883 | 124.85 | R | 4847 | 3.9 | 1243 | 373 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.12 | 41.53 | Tier 1B: High GIDA Priority | 52.56 | 52.56 | 76.18 | 64.37 | F - Nearest node and line over 5 km | 38.12 | 41.53 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 413
1 | 414 | 414 | 0300803019 | Region III (Central Luzon) | Bataan | City of Balanga | Talisay | 14.6811 | 120.5454 | R | 2278 | 3.6 | 633 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.93 | 63.93 | 64.79 | 64.36 | A - Node within 0.5 km | 0.28 | 0.13 | Line: CITY OF BALANGA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 414
1 | 415 | 415 | 1380606235 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 628 | 11.5236 | 122.4227 | U | 16279 | 3.97 | 4097 | 1229 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 6.36 | 2.71 | Tier 1B: High GIDA Priority | 57.98 | 57.98 | 70.73 | 64.36 | D - Other node or line within 3 km | 6.36 | 2.66 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 415
1 | 416 | 416 | 0201514009 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Caroan | 18.2682 | 121.9154 | R | 1293 | 3.9 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.36 | 2.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.66 | 48.66 | 80.04 | 64.35 | D - Other node or line within 3 km | 2.36 | 2.32 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 416
1 | 417 | 417 | 0403405006 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bucal | 14.1887 | 121.1689 | U | 15663 | 3.3 | 4746 | 1424 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.62 | 0.07 | Tier 1B: High GIDA Priority | 69.48 | 69.48 | 59.21 | 64.34 | C - Line within 0.5 km; node over 1 km | 2.62 | 0.07 | Line: AE LBL001-STB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 417
1 | 418 | 418 | 0402106026 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua I | 14.3201 | 120.9565 | U | 3587 | 3.4 | 1055 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 2.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.55 | 58.55 | 70.09 | 64.32 | D - Other node or line within 3 km | 1.31 | 2 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 418
1 | 419 | 419 | 0402106075 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas II | 14.3726 | 120.9766 | R | 4817 | 3.4 | 1417 | 425 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 4.1 | Tier 1B: High GIDA Priority | 65.28 | 65.28 | 63.34 | 64.31 | D - Other node or line within 3 km | 2.52 | 7.21 | Node: BRC002-TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 419
1 | 420 | 420 | 0504102005 | Region V (Bicol Region) | Masbate | Baleno | Cagpandan | 12.5135 | 123.4372 | R | 1191 | 4.1 | 290 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.18 | 0.41 | Tier 1B: High GIDA Priority | 55.82 | 55.82 | 72.81 | 64.31 | E - Nearest node or line 3-5 km | 4.18 | 24.55 | Node: AYM001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 420
1 | 421 | 421 | 1380800003 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Buli | 14.9567 | 120.0885 | U | 14802 | 3.25 | 4558 | 1367 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.75 | 0.58 | Tier 1B: High GIDA Priority | 68.68 | 68.68 | 59.91 | 64.3 | B - Node 0.5-1 km | 0.75 | 0.58 | Line: BACKBONE ROUTE | Survey short node lateral; confirm port/fiber capacity, access and route. | 421
1 | 422 | 422 | 1004315008 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Tangcub | 8.5305 | 124.372 | R | 1075 | 3.9 | 276 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.9 | 3.94 | Tier 1B: High GIDA Priority | 51.27 | 51.27 | 77.31 | 64.29 | E - Nearest node or line 3-5 km | 3.9 | 3.94 | Node: LDM001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 422
1 | 423 | 423 | 0203110004 | Region II (Cagayan Valley) | Isabela | Dinapigue | Dibulo | 16.5057 | 122.2349 | R | 1198 | 3.8 | 315 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.8 | 0.26 | Tier 1B: High GIDA Priority | 49.91 | 49.91 | 78.67 | 64.29 | E - Nearest node or line 3-5 km | 3.8 | 999999 | Node: DPI001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 423
1 | 424 | 424 | 0300803005 | Region III (Central Luzon) | Bataan | City of Balanga | Cataning | 14.6603 | 120.4939 | U | 10211 | 3.6 | 2836 | 851 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.15 | 2.68 | Tier 1B: High GIDA Priority | 59.75 | 59.75 | 68.79 | 64.27 | D - Other node or line within 3 km | 5.15 | 2.68 | Line: Bagac-Pilar AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 424
1 | 425 | 425 | 1381300100 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Jose | 14.5637 | 121.0473 | U | 6004 | 3.66 | 1642 | 493 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.03 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.12 | 58.12 | 70.38 | 64.25 | C - Line within 0.5 km; node over 1 km | 2.03 | 0.44 | Line: UG 144C via V-DUCT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 425
1 | 426 | 426 | 1380500011 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Hagdang Bato Libis | 14.5775 | 121.0462 | U | 6870 | 3.11 | 2212 | 664 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.99 | 61.99 | 66.46 | 64.23 | B - Node 0.5-1 km | 0.77 | 0.13 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 426
1 | 427 | 427 | 0205005019 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Bansing | 16.4597 | 121.1787 | R | 1083 | 3.8 | 285 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 3.99 | Tier 1B: High GIDA Priority | 45 | 45 | 83.44 | 64.22 | E - Nearest node or line 3-5 km | 4.59 | 3.99 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 427
1 | 428 | 428 | 0304902007 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Digmala | 15.6252 | 121.1543 | R | 1683 | 3.5 | 481 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.78 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.66 | 58.66 | 69.75 | 64.2 | B - Node 0.5-1 km | 0.84 | 0.73 | Line: Proposed AE F1-6 | Survey short node lateral; confirm port/fiber capacity, access and route. | 428
1 | 429 | 429 | 0403404014 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Sala | 14.2517 | 121.291 | U | 11951 | 3.3 | 3622 | 1087 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 7.85 | 7.99 | Tier 1B: High GIDA Priority | 60.6 | 60.6 | 67.78 | 64.19 | F - Nearest node and line over 5 km | 7.85 | 7.97 | Node: VTL001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 429
1 | 430 | 430 | 0402123017 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Kapitan Kua | 14.3127 | 121.0334 | R | 3595 | 3.4 | 1057 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 1.8 | Tier 1B: High GIDA Priority | 70.26 | 70.26 | 58.06 | 64.16 | B - Node 0.5-1 km | 0.93 | 1.8 | Node: CRC002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 430
1 | 431 | 431 | 1380700010 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Santo Niño | 14.639 | 121.0958 | U | 30271 | 3.67 | 8241 | 2472 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.28 | 0.17 | Tier 1B: High GIDA Priority | 65.07 | 65.07 | 63.24 | 64.15 | A - Node within 0.5 km | 0.28 | 0.17 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 431
1 | 432 | 432 | 0201512026 | Region II (Cagayan Valley) | Cagayan | Enrile | Roma Sur | 17.5095 | 121.6991 | R | 1391 | 3.9 | 357 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.86 | 1.5 | Tier 1B: High GIDA Priority | 49.6 | 49.6 | 78.7 | 64.15 | D - Other node or line within 3 km | 5.86 | 1.5 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 432
1 | 433 | 433 | 0102916005 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Baybayading | 17.1167 | 120.5711 | R | 193 | 3.8 | 51 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.1 | 8.99 | Tier 1B: High GIDA Priority | 44.91 | 44.91 | 83.33 | 64.12 | F - Nearest node and line over 5 km | 5.1 | 8.8 | Node: SDI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 433
1 | 434 | 434 | 0403403025 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Tubigan | 14.3288 | 121.07 | U | 6848 | 3.3 | 2075 | 622 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.65 | Tier 1B: High GIDA Priority | 65.29 | 65.29 | 62.93 | 64.11 | D - Other node or line within 3 km | 1.25 | 0.61 | Line: AE CRC005-BNL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 434
1 | 435 | 435 | 0405627001 | Region IV-A (CALABARZON) | Quezon | Mauban | Abo-abo | 14.1883 | 121.7453 | R | 196 | 3.8 | 52 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.02 | 20.46 | Tier 1B: High GIDA Priority | 42.05 | 42.05 | 86.16 | 64.1 | E - Nearest node or line 3-5 km | 3.02 | 20.37 | Node: MBQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 435
1 | 436 | 436 | 0403405042 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 5 | 14.2104 | 121.1676 | U | 6421 | 3.3 | 1946 | 584 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 0.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.64 | 62.64 | 65.55 | 64.09 | C - Line within 0.5 km; node over 1 km | 2.73 | 0.39 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 436
1 | 437 | 437 | 0403425005 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Landayan | 14.1545 | 121.4198 | U | 36431 | 3.3 | 11040 | 3312 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.97 | 1.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.24 | 62.24 | 65.94 | 64.09 | D - Other node or line within 3 km | 1.97 | 1.77 | Line: SAN PABLO - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 437
1 | 438 | 438 | 1381100005 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 5 | 14.5496 | 120.998 | U | 2837 | 3.15 | 902 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.56 | 57.56 | 70.63 | 64.09 | B - Node 0.5-1 km | 0.68 | 0.23 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 438
1 | 439 | 439 | 0301412001 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bagbaguin | 14.8189 | 120.9555 | U | 8807 | 3.5 | 2516 | 755 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.33 | Tier 1B: High GIDA Priority | 67.85 | 67.85 | 60.3 | 64.08 | B - Node 0.5-1 km | 0.71 | 0.27 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 439
1 | 440 | 440 | 1381000001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Baclaran | 14.5298 | 120.9989 | U | 35290 | 2.42 | 14588 | 4376 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.28 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.15 | 57.15 | 71.02 | 64.08 | A - Node within 0.5 km | 0.28 | 0.19 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 440
1 | 441 | 441 | 1381100156 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 156 | 14.7389 | 121.0037 | U | 3831 | 3.85 | 996 | 299 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.06 | 57.06 | 71.09 | 64.08 | C - Line within 0.5 km; node over 1 km | 1.5 | 0.33 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 441
1 | 442 | 442 | 1381600001 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Arkong Bato | 14.6988 | 120.9493 | U | 10746 | 3.74 | 2873 | 862 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.48 | 62.48 | 65.65 | 64.06 | C - Line within 0.5 km; node over 1 km | 1.58 | 0.45 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 442
1 | 443 | 443 | 0301411005 | Region III (Central Luzon) | Bulacan | Marilao | Lias | 14.7619 | 120.9653 | U | 15947 | 3.5 | 4556 | 1367 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.66 | 1.16 | Tier 2A: High Commercial ROI | 71.49 | 71.49 | 56.62 | 64.05 | D - Other node or line within 3 km | 1.66 | 1.45 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 443
1 | 444 | 444 | 1381300031 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Doña Imelda | 14.6153 | 121.0183 | U | 17695 | 4.03 | 4391 | 1317 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.35 | 0.28 | Tier 1B: High GIDA Priority | 69.29 | 69.29 | 58.79 | 64.04 | A - Node within 0.5 km | 0.35 | 0.08 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 444
1 | 445 | 445 | 0301414002 | Region III (Central Luzon) | Bulacan | Obando | Catanghalan | 14.7069 | 120.9412 | U | 3385 | 3.5 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 1.65 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.43 | 63.43 | 64.64 | 64.03 | B - Node 0.5-1 km | 0.57 | 1.62 | Node: OBB001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 445
1 | 446 | 446 | 1003508027 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Sucodan | 8.0947 | 123.8849 | R | 826 | 4.2 | 197 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.06 | 1.09 | Tier 1B: High GIDA Priority | 46.98 | 46.98 | 81.06 | 64.02 | D - Other node or line within 3 km | 11.06 | 1.09 | Line: ILIGAN - PAGADIAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 446
1 | 447 | 447 | 1380300010 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Guadalupe Viejo | 14.5673 | 121.0403 | U | 13525 | 3.6 | 3755 | 1126 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.25 | 0.08 | Tier 1B: High GIDA Priority | 65.64 | 65.64 | 62.38 | 64.01 | C - Line within 0.5 km; node over 1 km | 1.25 | 0.02 | Line: UG 144C via V-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 447
1 | 448 | 448 | 1380300011 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Kasilawan | 14.5507 | 121.0322 | U | 5007 | 3.62 | 1384 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.63 | 58.63 | 69.39 | 64.01 | D - Other node or line within 3 km | 1.26 | 1.42 | Node: MKT001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 448
1 | 449 | 449 | 0506204013 | Region V (Bicol Region) | Sorsogon | Bulusan | Salvacion | 12.7216 | 124.0962 | R | 488 | 4 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.76 | 1.94 | Tier 1B: High GIDA Priority | 51.73 | 51.73 | 76.25 | 63.99 | F - Nearest node and line over 5 km | 5.76 | 6.89 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 449
1 | 450 | 450 | 0102814011 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Uguis | 17.8944 | 120.5712 | R | 1111 | 3.7 | 300 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.74 | 9.11 | Tier 1B: High GIDA Priority | 43.72 | 43.72 | 84.25 | 63.99 | F - Nearest node and line over 5 km | 7.74 | 9.1 | Node: PNI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 450
1 | 451 | 451 | 0102916014 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Madarang | 17.1592 | 120.5787 | R | 259 | 3.8 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.47 | 7.29 | Tier 1B: High GIDA Priority | 45.37 | 45.37 | 82.58 | 63.98 | E - Nearest node or line 3-5 km | 4.47 | 7.25 | Node: SDI001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 451
1 | 452 | 452 | 0403405037 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Parian | 14.2142 | 121.1515 | U | 28016 | 3.3 | 8490 | 2547 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.97 | 0.08 | Tier 1B: High GIDA Priority | 65.55 | 65.55 | 62.37 | 63.96 | C - Line within 0.5 km; node over 1 km | 1.97 | 0.08 | Line: AE SRL007-CBL001-CLB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 452
1 | 453 | 453 | 1381400018 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Santa Lucia | 14.5978 | 121.0353 | U | 9134 | 3.27 | 2796 | 839 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 63.3 | 63.3 | 64.61 | 63.96 | B - Node 0.5-1 km | 0.99 | 0.2 | Line: UG 288C via V-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 453
1 | 454 | 454 | 0203110002 | Region II (Cagayan Valley) | Isabela | Dinapigue | Bucal Sur | 16.541 | 122.2644 | R | 892 | 3.8 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 1.94 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.43 | 50.43 | 77.46 | 63.95 | D - Other node or line within 3 km | 1.72 | 999999 | Node: DPI001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 454
1 | 455 | 455 | 1401109007 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Tacadang | 16.7361 | 120.5799 | R | 1701 | 3.5 | 486 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.15 | 17.94 | Tier 1B: High GIDA Priority | 51.79 | 51.79 | 76.09 | 63.94 | F - Nearest node and line over 5 km | 9.15 | 17.94 | Node: KIB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 455
1 | 456 | 456 | 1404406007 | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | Buringal | 17.2175 | 121.4963 | R | 2601 | 3.7 | 703 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.69 | 12.08 | Tier 1B: High GIDA Priority | 51.4 | 51.4 | 76.47 | 63.94 | F - Nearest node and line over 5 km | 10.69 | 12.08 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 456
1 | 457 | 457 | 1380500003 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Drive | 14.5733 | 121.0381 | U | 15782 | 3.37 | 4687 | 1406 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.27 | 0.31 | Tier 1B: High GIDA Priority | 67.53 | 67.53 | 60.33 | 63.93 | C - Line within 0.5 km; node over 1 km | 1.27 | 0.31 | Line: Aerial 216C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 457
1 | 458 | 458 | 1381300106 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Monica | 14.7227 | 121.0469 | U | 52203 | 3.94 | 13255 | 3976 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.53 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.27 | 58.27 | 69.58 | 63.92 | B - Node 0.5-1 km | 0.53 | 0.44 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 458
1 | 459 | 459 | 1381300056 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Maharlika | 14.6816 | 121.0779 | U | 5211 | 3.14 | 1658 | 497 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.64 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.08 | 60.08 | 67.71 | 63.9 | B - Node 0.5-1 km | 0.91 | 0.64 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 459
1 | 460 | 460 | 1381701005 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | San Pedro | 14.5468 | 121.0674 | U | 2252 | 3.34 | 674 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.26 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.43 | 52.43 | 75.37 | 63.9 | A - Node within 0.5 km | 0.26 | 0.19 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 460
1 | 461 | 461 | 1108204033 | Region XI (Davao Region) | Davao de Oro | Maco | New Leyte | 7.4043 | 126.0561 | R | 2939 | 3.7 | 794 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.68 | 18.81 | Tier 1B: High GIDA Priority | 48.08 | 48.08 | 79.71 | 63.9 | F - Nearest node and line over 5 km | 22.68 | 18.81 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 461
1 | 462 | 462 | 0600410013 | Region VI (Western Visayas) | Aklan | Madalag | Maria Cristina | 11.5232 | 122.2275 | R | 1171 | 3.9 | 300 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.41 | 15.52 | Tier 1B: High GIDA Priority | 45.15 | 45.15 | 82.63 | 63.89 | F - Nearest node and line over 5 km | 13.41 | 15.52 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 462
1 | 463 | 463 | 0403425015 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Roque | 14.258 | 121.1385 | U | 7850 | 3.3 | 2379 | 714 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 1.19 | Tier 1B: High GIDA Priority | 65.79 | 65.79 | 61.98 | 63.88 | D - Other node or line within 3 km | 1.51 | 1.19 | Line: AE SRL007-CBL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 463
1 | 464 | 464 | 0402106074 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel II | 14.3385 | 120.9496 | R | 2392 | 3.4 | 704 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 4.11 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.56 | 59.56 | 68.14 | 63.85 | D - Other node or line within 3 km | 1.72 | 4.04 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 464
1 | 465 | 465 | 1380900006 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Navotas East | 14.6591 | 120.94 | U | 2176 | 3.35 | 649 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 1.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.72 | 50.72 | 76.98 | 63.85 | B - Node 0.5-1 km | 0.78 | 1.38 | Node: NAV001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 465
1 | 466 | 466 | 1380700002 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Calumpang | 14.6222 | 121.0903 | U | 15914 | 3.87 | 4117 | 1235 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.71 | 0.82 | Tier 1B: High GIDA Priority | 65.92 | 65.92 | 61.75 | 63.84 | D - Other node or line within 3 km | 1.71 | 0.82 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 466
1 | 467 | 467 | 0506210007 | Region V (Bicol Region) | Sorsogon | Juban | Calateo | 12.8053 | 123.986 | R | 771 | 4 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.27 | 1.51 | Tier 1B: High GIDA Priority | 54.55 | 54.55 | 73.14 | 63.84 | D - Other node or line within 3 km | 3.27 | 1.51 | Line: SORSOGON - MATNOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 467
1 | 468 | 468 | 1102510007 | Region XI (Davao Region) | Davao Oriental | San Isidro | La Union | 6.7187 | 126.1125 | R | 4594 | 3.6 | 1276 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.64 | 17.78 | Tier 1B: High GIDA Priority | 54.06 | 54.06 | 73.62 | 63.84 | F - Nearest node and line over 5 km | 22.64 | 17.77 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 468
1 | 469 | 469 | 0305404005 | Region III (Central Luzon) | Pampanga | Bacolor | Calibutbut | 15.1024 | 120.6055 | U | 13476 | 4 | 3369 | 1011 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.32 | 1.14 | Tier 1B: High GIDA Priority | 69.3 | 69.3 | 58.35 | 63.83 | D - Other node or line within 3 km | 1.32 | 1.12 | Line: Pipe 58-58A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 469
1 | 470 | 470 | 1102315026 | Region XI (Davao Region) | Davao del Norte | City of Panabo | New Visayas | 7.3088 | 125.6677 | U | 19306 | 3.7 | 5218 | 1565 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.65 | 1.69 | Tier 2A: High Commercial ROI | 73.5 | 73.5 | 54.14 | 63.82 | D - Other node or line within 3 km | 1.65 | 1.65 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 470
1 | 471 | 471 | 1381400011 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Onse | 14.6018 | 121.0302 | U | 3636 | 3.92 | 928 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.48 | 56.48 | 71.12 | 63.8 | C - Line within 0.5 km; node over 1 km | 1.6 | 0.22 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 471
1 | 472 | 472 | 0300803025 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang North | 14.6841 | 120.5194 | R | 2656 | 3.6 | 738 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 0.34 | Tier 1B: High GIDA Priority | 63.27 | 63.27 | 64.27 | 63.77 | C - Line within 0.5 km; node over 1 km | 2.19 | 0.34 | Line: Bagac-Pilar AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 472
1 | 473 | 473 | 1004312008 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Kagumahan | 8.9892 | 124.8186 | R | 250 | 3.9 | 64 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.86 | 1.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.69 | 52.69 | 74.85 | 63.77 | D - Other node or line within 3 km | 2.86 | 1.28 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 473
1 | 474 | 474 | 0402106078 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño II | 14.3389 | 121.0218 | R | 2881 | 3.4 | 847 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.08 | 1.54 | Tier 1B: High GIDA Priority | 66.42 | 66.42 | 61.1 | 63.76 | D - Other node or line within 3 km | 2.08 | 1.81 | Line: AE SPL002 TO SPL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 474
1 | 475 | 475 | 1381300004 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Aurora | 14.6161 | 121.0084 | U | 4344 | 4.29 | 1013 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.48 | 58.48 | 69.03 | 63.76 | B - Node 0.5-1 km | 0.75 | 0.23 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 475
1 | 476 | 476 | 0401030016 | Region IV-A (CALABARZON) | Batangas | Talisay | Poblacion Barangay 6 | 14.0895 | 121.0046 | R | 421 | 3.6 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.54 | 4.86 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.17 | 44.17 | 83.36 | 63.76 | D - Other node or line within 3 km | 1.54 | 4.86 | Node: TSB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 476
1 | 477 | 477 | 0402117010 | Region IV-A (CALABARZON) | Cavite | Rosario | Tejeros Convention | 14.403 | 120.86 | U | 21580 | 3.4 | 6347 | 1904 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.57 | 0.81 | Tier 2A: High Commercial ROI | 70.83 | 70.83 | 56.66 | 63.75 | B - Node 0.5-1 km | 0.57 | 0.81 | Node: TRC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 477
1 | 478 | 478 | 0203110003 | Region II (Cagayan Valley) | Isabela | Dinapigue | Bucal Norte | 16.5319 | 122.2634 | R | 293 | 3.8 | 77 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.93 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.48 | 49.48 | 78.01 | 63.75 | B - Node 0.5-1 km | 0.7 | 999999 | Node: DPI001 - TYPE 4A | Survey short node lateral; confirm port/fiber capacity, access and route. | 478
1 | 479 | 479 | 1908704013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Tubuan | 17.2541 | 122.2282 | R | 6357 | 4.3 | 1478 | 443 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 50.7 | 50.7 | 76.77 | 63.74 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 479
1 | 480 | 480 | 0601909026 | Region VI (Western Visayas) | Capiz | Panay | Lat-Asan | 11.5457 | 122.8632 | R | 823 | 3.8 | 217 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.46 | 7.06 | Tier 1B: High GIDA Priority | 44.52 | 44.52 | 82.96 | 63.74 | F - Nearest node and line over 5 km | 7.46 | 7.04 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 480
1 | 481 | 481 | 0405801007 | Region IV-A (CALABARZON) | Rizal | Angono | Poblacion Ibaba | 14.5364 | 121.1545 | R | 3472 | 3.6 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.42 | Tier 1B: High GIDA Priority | 69.86 | 69.86 | 57.61 | 63.73 | B - Node 0.5-1 km | 0.99 | 0.42 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 481
1 | 482 | 482 | 1381200014 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Palatiw | 14.5646 | 121.083 | U | 28185 | 3.54 | 7973 | 2392 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.24 | 0.21 | Tier 1B: High GIDA Priority | 65.49 | 65.49 | 61.98 | 63.73 | A - Node within 0.5 km | 0.24 | 0.21 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 482
1 | 483 | 483 | 1381300042 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | N.S. Amoranto | 14.6624 | 121.0759 | U | 6061 | 3.87 | 1568 | 470 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.52 | 60.52 | 66.94 | 63.73 | B - Node 0.5-1 km | 0.55 | 0.1 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 483
1 | 484 | 484 | 0401001010 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Mabini | 13.9452 | 120.9288 | R | 1347 | 3.6 | 374 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 5.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.96 | 55.96 | 71.49 | 63.72 | D - Other node or line within 3 km | 1.2 | 5.31 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 484
1 | 485 | 485 | 0300809008 | Region III (Central Luzon) | Bataan | Orani | Kaparangan | 14.7943 | 120.5386 | R | 3108 | 3.6 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.16 | Tier 1B: High GIDA Priority | 68.87 | 68.87 | 58.55 | 63.71 | B - Node 0.5-1 km | 0.9 | 0.04 | Line: 36 CORE 3X12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 485
1 | 486 | 486 | 0702219003 | Region VII (Central Visayas) | Cebu | Consolacion | Casili | 10.3791 | 123.9353 | U | 19021 | 3.8 | 5006 | 1502 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.02 | 0.21 | Tier 2A: High Commercial ROI | 74.26 | 74.26 | 53.09 | 63.68 | C - Line within 0.5 km; node over 1 km | 2.02 | 0.19 | Line: Route 11.925km | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 486
1 | 487 | 487 | 0103314022 | Region I (Ilocos Region) | La Union | City of San Fernando | Catbangen | 16.6126 | 120.3124 | U | 9670 | 3.7 | 2614 | 784 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.4 | Tier 1B: High GIDA Priority | 67.3 | 67.3 | 60.05 | 63.68 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.4 | Line: SAN FERNANDO - SUPIDEN AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 487
1 | 488 | 488 | 1380700001 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Barangka | 14.6332 | 121.0819 | U | 16144 | 3.7 | 4364 | 1309 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.39 | 0.85 | Tier 1B: High GIDA Priority | 67.19 | 67.19 | 60.15 | 63.67 | D - Other node or line within 3 km | 1.39 | 0.85 | Line: UG 288C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 488
1 | 489 | 489 | 0403425029 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Lorenzo Ruiz | 14.3539 | 121.4224 | U | 6358 | 3.3 | 1927 | 578 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.98 | 6.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.77 | 58.77 | 68.55 | 63.66 | D - Other node or line within 3 km | 2.98 | 6.18 | Node: PKL002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 489
1 | 490 | 490 | 0405627026 | Region IV-A (CALABARZON) | Quezon | Mauban | Remedios II | 14.1905 | 121.6642 | R | 404 | 3.8 | 106 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 13.77 | Tier 1B: High GIDA Priority | 40.82 | 40.82 | 86.5 | 63.66 | E - Nearest node or line 3-5 km | 4.22 | 13.77 | Node: SPQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 490
1 | 491 | 491 | 0301420045 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Manuel | 14.7763 | 121.0677 | U | 11950 | 3.5 | 3414 | 1024 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.74 | 0.78 | Tier 1B: High GIDA Priority | 68.73 | 68.73 | 58.58 | 63.65 | D - Other node or line within 3 km | 1.74 | 0.75 | Line: SJDM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 491
1 | 492 | 492 | 0102934006 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay IV | 17.5742 | 120.3836 | R | 2081 | 3.8 | 548 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 1.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.04 | 58.04 | 69.26 | 63.65 | D - Other node or line within 3 km | 2.27 | 0.97 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 492
1 | 493 | 493 | 1381300034 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Duyan-duyan | 14.631 | 121.0668 | U | 3390 | 3.61 | 938 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.66 | 58.66 | 68.61 | 63.64 | B - Node 0.5-1 km | 0.55 | 0.27 | Line: UG 144C via R-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 493
1 | 494 | 494 | 1381600023 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Paso De Blas | 14.7054 | 120.9911 | U | 12882 | 3.22 | 4003 | 1201 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.32 | 0.19 | Tier 1B: High GIDA Priority | 66.26 | 66.26 | 61 | 63.63 | C - Line within 0.5 km; node over 1 km | 1.32 | 0.14 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 494
1 | 495 | 495 | 1381300142 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | North Fairview | 14.7085 | 121.066 | U | 47019 | 4.06 | 11586 | 3476 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.21 | 0.24 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.03 | 59.03 | 68.23 | 63.63 | C - Line within 0.5 km; node over 1 km | 1.21 | 0.24 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 495
1 | 496 | 496 | 0205007022 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Macabenga | 16.2108 | 121.2328 | R | 1807 | 3.8 | 476 | 143 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 21.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.95 | 55.95 | 71.3 | 63.62 | A - Node within 0.5 km | 0.41 | 21.28 | Node: DNV002 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 496
1 | 497 | 497 | 0300803001 | Region III (Central Luzon) | Bataan | City of Balanga | Bagumbayan | 14.6796 | 120.5464 | R | 2159 | 3.6 | 600 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 62.63 | 62.63 | 64.59 | 63.61 | A - Node within 0.5 km | 0.47 | 0.32 | Line: CITY OF BALANGA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 497
1 | 498 | 498 | 0205008020 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Kinabuan | 16.2016 | 121.2013 | R | 1412 | 3.8 | 372 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 19.43 | Tier 1B: High GIDA Priority | 48.34 | 48.34 | 78.89 | 63.61 | E - Nearest node or line 3-5 km | 3.5 | 19.42 | Node: DNV002 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 498
1 | 499 | 499 | 1408102008 | Cordillera Administrative Region (CAR) | Apayao | Conner | Karikitan | 17.7478 | 121.3646 | R | 1935 | 4.2 | 461 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.94 | 0.07 | Tier 1B: High GIDA Priority | 52.25 | 52.25 | 74.94 | 63.6 | C - Line within 0.5 km; node over 1 km | 6.94 | 0.05 | Line: Tabuk-Conner | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 499
1 | 500 | 500 | 0500518005 | Region V (Bicol Region) | Albay | Tiwi | Biyong | 13.4481 | 123.6496 | R | 1705 | 4.1 | 416 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3 | 2.44 | Tier 1B: High GIDA Priority | 51.87 | 51.87 | 75.31 | 63.59 | D - Other node or line within 3 km | 3 | 2.42 | Line: EE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 500
1 | 501 | 501 | 1102315032 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Vicente | 7.3095 | 125.6997 | U | 19658 | 3.7 | 5313 | 1594 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.36 | 1.56 | Tier 2A: High Commercial ROI | 72.32 | 72.32 | 54.85 | 63.58 | D - Other node or line within 3 km | 2.36 | 1.56 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 501
1 | 502 | 502 | 1381400009 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Little Baguio | 14.6131 | 121.024 | U | 6643 | 3.24 | 2051 | 615 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.08 | 61.08 | 66.06 | 63.57 | B - Node 0.5-1 km | 1 | 0.33 | Line: UG 144C via W-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 502
1 | 503 | 503 | 0301412010 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Langka | 14.7395 | 120.9806 | U | 4515 | 3.5 | 1290 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.93 | Tier 1B: High GIDA Priority | 63 | 63 | 64.12 | 63.56 | D - Other node or line within 3 km | 1.31 | 0.93 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 503
1 | 504 | 504 | 1380400012 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Muzon | 14.6765 | 120.95 | U | 6127 | 3.46 | 1773 | 532 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.65 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.96 | 60.96 | 66.16 | 63.56 | B - Node 0.5-1 km | 0.64 | 0.6 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 504
1 | 505 | 505 | 0600406032 | Region VI (Western Visayas) | Aklan | Ibajay | Tagbaya | 11.8109 | 122.1309 | R | 1740 | 3.9 | 446 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.6 | 0.3 | Tier 1B: High GIDA Priority | 44.34 | 44.34 | 82.78 | 63.56 | F - Nearest node and line over 5 km | 20.6 | 26.93 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 505
1 | 506 | 506 | 0405804022 | Region IV-A (CALABARZON) | Rizal | Binangonan | Lunsad | 14.4621 | 121.1955 | U | 11246 | 3.6 | 3124 | 937 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 0.74 | Tier 1B: High GIDA Priority | 67.96 | 67.96 | 59.13 | 63.55 | D - Other node or line within 3 km | 1.57 | 0.58 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 506
1 | 507 | 507 | 0301420011 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Tungkong Mangga | 14.7875 | 121.0718 | U | 17063 | 3.5 | 4875 | 1462 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.16 | 0.27 | Tier 2A: High Commercial ROI | 71.94 | 71.94 | 55.14 | 63.54 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.27 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 507
1 | 508 | 508 | 1381600028 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Rincon | 14.6993 | 120.9579 | U | 7097 | 3.72 | 1909 | 573 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.54 | 60.54 | 66.54 | 63.54 | D - Other node or line within 3 km | 1.06 | 0.52 | Line: Existing 216F | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 508
1 | 509 | 509 | 0402123018 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Koronel Jose P. Elises | 14.2901 | 121.0051 | R | 4747 | 3.4 | 1396 | 419 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 4.57 | Tier 1B: High GIDA Priority | 67.85 | 67.85 | 59.21 | 63.53 | B - Node 0.5-1 km | 0.91 | 4.57 | Node: MAC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 509
1 | 510 | 510 | 0702232013 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward IV | 10.2539 | 123.7872 | U | 4414 | 3.8 | 1162 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.17 | Tier 1B: High GIDA Priority | 65.29 | 65.29 | 61.77 | 63.53 | D - Other node or line within 3 km | 1.55 | 1.17 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 510
1 | 511 | 511 | 0403403006 | Region IV-A (CALABARZON) | Laguna | City of Biñan | De La Paz | 14.3482 | 121.085 | U | 35999 | 3.3 | 10909 | 3273 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.46 | 1.02 | Tier 1B: High GIDA Priority | 63.24 | 63.24 | 63.81 | 63.52 | D - Other node or line within 3 km | 1.46 | 1.02 | Line: RELIANCE TO SAN PABLO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 511
1 | 512 | 512 | 1381200023 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Nicolas | 14.5615 | 121.0788 | U | 2869 | 4 | 717 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.26 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.55 | 53.55 | 73.48 | 63.52 | A - Node within 0.5 km | 0.26 | 0.23 | Line: Aerial 216C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 512
1 | 513 | 513 | 0402106081 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Victoria Reyes | 14.3186 | 120.9752 | U | 14568 | 3.4 | 4285 | 1286 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.91 | 2.81 | Tier 1B: High GIDA Priority | 69.24 | 69.24 | 57.75 | 63.5 | B - Node 0.5-1 km | 0.91 | 2.81 | Node: DMC005 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 513
1 | 514 | 514 | 0102817027 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Santa Catalina | 18.3064 | 120.6713 | R | 860 | 3.7 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.51 | 6.34 | Tier 1B: High GIDA Priority | 43.63 | 43.63 | 83.38 | 63.5 | E - Nearest node or line 3-5 km | 4.51 | 6.27 | Node: VNI001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 514
1 | 515 | 515 | 1108602009 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Caburan Big | 5.9226 | 125.6066 | R | 5203 | 3.6 | 1445 | 434 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.61 | 50.47 | Tier 1B: High GIDA Priority | 53.03 | 53.03 | 73.95 | 63.49 | F - Nearest node and line over 5 km | 41.61 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 515
1 | 516 | 516 | 0600410019 | Region VI (Western Visayas) | Aklan | Madalag | Panipiason | 11.4095 | 122.2485 | R | 1877 | 3.9 | 481 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.48 | 21.36 | Tier 1B: High GIDA Priority | 45.87 | 45.87 | 81.11 | 63.49 | F - Nearest node and line over 5 km | 21.48 | 21.32 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 516
1 | 517 | 517 | 0402116002 | Region IV-A (CALABARZON) | Cavite | Noveleta | Poblacion | 14.4264 | 120.8802 | R | 2291 | 3.4 | 674 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.46 | 0.45 | Tier 1B: High GIDA Priority | 64.58 | 64.58 | 62.38 | 63.48 | A - Node within 0.5 km | 0.46 | 0.45 | Line: NOVELETA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 517
1 | 518 | 518 | 1381300063 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Masagana | 14.7015 | 121.0661 | U | 4291 | 3.96 | 1084 | 325 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.54 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.81 | 57.81 | 69.15 | 63.48 | D - Other node or line within 3 km | 1.22 | 0.54 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 518
1 | 519 | 519 | 0301412022 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saint Francis (Gasak) | 14.733 | 120.9567 | R | 1372 | 3.5 | 392 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.52 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.29 | 55.29 | 71.65 | 63.47 | D - Other node or line within 3 km | 1.4 | 0.52 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 519
1 | 520 | 520 | 0402118054 | Region IV-A (CALABARZON) | Cavite | Silang | Anahaw II | 14.2327 | 120.9784 | R | 3770 | 3.4 | 1109 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.09 | 0.28 | Tier 1B: High GIDA Priority | 64.77 | 64.77 | 62.15 | 63.46 | C - Line within 0.5 km; node over 1 km | 6.09 | 0.26 | Line: SILANG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 520
1 | 521 | 521 | 1380606003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 397 | 14.2411 | 121.3337 | U | 8835 | 3.72 | 2372 | 712 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 3.45 | Tier 1B: High GIDA Priority | 54.9 | 54.9 | 72.02 | 63.46 | E - Nearest node or line 3-5 km | 3.5 | 3.43 | Line: CLB001 TO SCL001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 521
1 | 522 | 522 | 0402106070 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Isidro Labrador II | 14.2597 | 120.9555 | R | 2593 | 3.4 | 763 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.51 | 1.49 | Tier 1B: High GIDA Priority | 61.4 | 61.4 | 65.49 | 63.45 | D - Other node or line within 3 km | 4.51 | 1.49 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 522
1 | 523 | 523 | 1381100015 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 15 | 14.5378 | 120.9793 | U | 2393 | 2.72 | 881 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.79 | 1.77 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.95 | 54.95 | 71.95 | 63.45 | D - Other node or line within 3 km | 1.79 | 1.74 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 523
1 | 524 | 524 | 1380700015 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Fortune | 14.6592 | 121.1264 | U | 40941 | 4.05 | 10105 | 3032 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.96 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.35 | 61.35 | 65.51 | 63.43 | B - Node 0.5-1 km | 0.96 | 0.06 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 524
1 | 525 | 525 | 0200901003 | Region II (Cagayan Valley) | Batanes | Basco | San Antonio | 20.4505 | 121.9682 | R | 2260 | 3 | 753 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 223.95 | 217.52 | Tier 1B: High GIDA Priority | 49.8 | 49.8 | 77.03 | 63.42 | F - Nearest node and line over 5 km | 220.62 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 525
1 | 526 | 526 | 1381200029 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Ugong | 14.5791 | 121.0787 | U | 31627 | 3.9 | 8116 | 2435 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.53 | 0.38 | Tier 1B: High GIDA Priority | 64.69 | 64.69 | 62.13 | 63.41 | B - Node 0.5-1 km | 0.53 | 0.34 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 526
1 | 527 | 527 | 0301411003 | Region III (Central Luzon) | Bulacan | Marilao | Ibayo | 14.753 | 120.9597 | U | 8686 | 3.5 | 2482 | 745 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 0.48 | Tier 1B: High GIDA Priority | 68.15 | 68.15 | 58.64 | 63.4 | B - Node 0.5-1 km | 0.52 | 0.48 | Line: GOTACO TO HH 71 BULACAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 527
1 | 528 | 528 | 1381300085 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-A | 14.6998 | 121.0865 | U | 4751 | 3.36 | 1412 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.55 | 60.55 | 66.23 | 63.39 | A - Node within 0.5 km | 0.32 | 0.04 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 528
1 | 529 | 529 | 1380200006 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pamplona Uno | 14.4581 | 120.97 | U | 19658 | 3.72 | 5279 | 1584 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.43 | 0.11 | Tier 1B: High GIDA Priority | 68.43 | 68.43 | 58.32 | 63.37 | A - Node within 0.5 km | 0.43 | 0.11 | Line: Aerial 216C MTF | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 529
1 | 530 | 530 | 0806010014 | Region VIII (Eastern Visayas) | Samar | Marabut | Tinabanan | 11.2076 | 125.1874 | R | 2041 | 4.1 | 498 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.42 | 18.26 | Tier 1B: High GIDA Priority | 46.8 | 46.8 | 79.91 | 63.36 | F - Nearest node and line over 5 km | 19.42 | 19.41 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 530
1 | 531 | 531 | 1381300076 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paltok | 14.6452 | 121.0217 | U | 18657 | 4.28 | 4355 | 1306 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.67 | 0.45 | Tier 1B: High GIDA Priority | 68.52 | 68.52 | 58.16 | 63.34 | B - Node 0.5-1 km | 0.67 | 0.42 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 531
1 | 532 | 532 | 0205706004 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Guino | 16.1514 | 121.244 | R | 1563 | 3.9 | 401 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.97 | 26.61 | Tier 1B: High GIDA Priority | 46.86 | 46.86 | 79.78 | 63.32 | F - Nearest node and line over 5 km | 6.97 | 26.61 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 532
1 | 533 | 533 | 0405811008 | Region IV-A (CALABARZON) | Rizal | San Mateo | Maly | 14.7083 | 121.1315 | U | 13988 | 3.6 | 3886 | 1166 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.67 | 0.21 | Tier 1B: High GIDA Priority | 68.68 | 68.68 | 57.94 | 63.31 | C - Line within 0.5 km; node over 1 km | 2.67 | 0.13 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 533
1 | 534 | 534 | 1408106027 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Lt. Balag | 18.1714 | 121.3625 | R | 210 | 4.2 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.31 | 1.01 | Tier 1B: High GIDA Priority | 48.91 | 48.91 | 77.72 | 63.31 | F - Nearest node and line over 5 km | 5.31 | 19.68 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 534
1 | 535 | 535 | 1402701009 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Cambulo | 16.952 | 121.1281 | R | 1156 | 3.9 | 296 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.19 | 7.73 | Tier 1B: High GIDA Priority | 49.23 | 49.23 | 77.37 | 63.3 | F - Nearest node and line over 5 km | 6.19 | 11.1 | Node: MOF002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 535
1 | 536 | 536 | 0102814007 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Garnaden | 17.9163 | 120.6235 | R | 722 | 3.7 | 195 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.79 | 3.72 | Tier 1B: High GIDA Priority | 43.18 | 43.18 | 83.42 | 63.3 | E - Nearest node or line 3-5 km | 3.79 | 3.7 | Line: SEGMENT 5 BANNA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 536
1 | 537 | 537 | 0600414010 | Region VI (Western Visayas) | Aklan | Nabas | Matabana | 11.8746 | 122.0282 | R | 1010 | 3.9 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.15 | 0.27 | Tier 1B: High GIDA Priority | 48.65 | 48.65 | 77.93 | 63.29 | F - Nearest node and line over 5 km | 12.15 | 40.04 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 537
1 | 538 | 538 | 0102910007 | Region I (Ilocos Region) | Ilocos Sur | Gregorio del Pilar | Poblacion Norte | 17.1498 | 120.6109 | R | 571 | 3.8 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.32 | 3.95 | Tier 1B: High GIDA Priority | 44.54 | 44.54 | 82.05 | 63.29 | E - Nearest node or line 3-5 km | 7.32 | 3.88 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 538
1 | 539 | 539 | 1381100130 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 130 | 14.3843 | 121.0547 | U | 3894 | 3.84 | 1014 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 1.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.81 | 56.81 | 69.75 | 63.28 | D - Other node or line within 3 km | 1.68 | 1.06 | Line: Aerial 216C MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 539
1 | 540 | 540 | 1208006012 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Upper Suyan | 6.0743 | 125.4503 | R | 4980 | 3.9 | 1277 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.36 | 27.46 | Tier 1B: High GIDA Priority | 54.9 | 54.9 | 71.64 | 63.27 | F - Nearest node and line over 5 km | 19.36 | 27.46 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 540
1 | 541 | 541 | 0205006009 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Pinya | 16.6844 | 121.3232 | R | 787 | 3.8 | 207 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.57 | 4.47 | Tier 1B: High GIDA Priority | 46.7 | 46.7 | 79.83 | 63.27 | E - Nearest node or line 3-5 km | 5.57 | 4.46 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 541
1 | 542 | 542 | 1705312009 | MIMAROPA Region | Palawan | El Nido | New Ibajay | 11.1624 | 119.4777 | R | 4156 | 3.9 | 1066 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.66 | 37.92 | Tier 1B: High GIDA Priority | 59.71 | 59.71 | 66.8 | 63.26 | F - Nearest node and line over 5 km | 9.66 | 37.71 | Node: ENW001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 542
1 | 543 | 543 | 1381300096 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Antonio | 14.647 | 121.0164 | U | 22880 | 3.62 | 6328 | 1898 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.1 | 0.09 | Tier 1B: High GIDA Priority | 67.85 | 67.85 | 58.63 | 63.24 | A - Node within 0.5 km | 0.1 | 0.08 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 543
1 | 544 | 544 | 0306916073 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Roque | 15.4845 | 120.5896 | U | 6267 | 3.9 | 1607 | 482 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.43 | 0.34 | Tier 1B: High GIDA Priority | 62.2 | 62.2 | 64.27 | 63.24 | C - Line within 0.5 km; node over 1 km | 2.43 | 0.27 | Line: (TCT 395)San Vicente 1188mtrs. | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 544
1 | 545 | 545 | 0301412017 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Pandayan | 14.7505 | 120.9684 | U | 17948 | 3.5 | 5128 | 1538 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.29 | 1.2 | Tier 2A: High Commercial ROI | 71.4 | 71.4 | 55.05 | 63.22 | D - Other node or line within 3 km | 1.29 | 1.2 | Line: GOTACO TO HH 71 BULACAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 545
1 | 546 | 546 | 0702234019 | Region VII (Central Visayas) | Cebu | City of Naga | North Poblacion | 10.1942 | 123.7447 | R | 3151 | 3.8 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.16 | 0.12 | Tier 1B: High GIDA Priority | 62.69 | 62.69 | 63.74 | 63.22 | C - Line within 0.5 km; node over 1 km | 5.3 | 0.12 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 546
1 | 547 | 547 | 1381200006 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Dela Paz | 14.615 | 121.0953 | U | 20484 | 3.21 | 6382 | 1915 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.64 | 0.15 | Tier 1B: High GIDA Priority | 64.78 | 64.78 | 61.62 | 63.2 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.25 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 547
1 | 548 | 548 | 1380606207 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 600 | 13.5588 | 123.1122 | U | 6276 | 4.84 | 1298 | 389 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.01 | 0.53 | Tier 1B: High GIDA Priority | 55.77 | 55.77 | 70.62 | 63.2 | D - Other node or line within 3 km | 3.01 | 0.53 | Line: PILI - PAMPLONA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 548
1 | 549 | 549 | 1004303002 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Dahilig | 8.9832 | 124.856 | R | 335 | 3.9 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 2.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.34 | 49.34 | 77.07 | 63.2 | D - Other node or line within 3 km | 2.74 | 2.25 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 549
1 | 550 | 550 | 1401108010 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Gasweling | 16.5787 | 120.5082 | R | 1032 | 3.5 | 295 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.18 | 8.47 | Tier 1B: High GIDA Priority | 46.69 | 46.69 | 79.72 | 63.2 | F - Nearest node and line over 5 km | 9.18 | 8.28 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 550
1 | 551 | 551 | 0205007023 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Parai | 16.3117 | 121.1702 | R | 975 | 3.8 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.06 | 9.71 | Tier 1B: High GIDA Priority | 42.97 | 42.97 | 83.44 | 63.2 | F - Nearest node and line over 5 km | 7.06 | 9.71 | Node: DNV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 551
1 | 552 | 552 | 1380900017 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tangos North | 14.6658 | 120.9305 | U | 17384 | 3.52 | 4935 | 1480 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.67 | 1.67 | Tier 1B: High GIDA Priority | 66.55 | 66.55 | 59.83 | 63.19 | D - Other node or line within 3 km | 1.67 | 1.66 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 552
1 | 553 | 553 | 1381200005 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Caniogan | 14.5718 | 121.0785 | U | 28576 | 3.17 | 9028 | 2708 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.81 | 0.46 | Tier 1B: High GIDA Priority | 62.99 | 62.99 | 63.37 | 63.18 | B - Node 0.5-1 km | 0.81 | 0.46 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 553
1 | 554 | 554 | 0702219013 | Region VII (Central Visayas) | Cebu | Consolacion | Poblacion Occidental | 10.3727 | 123.954 | U | 6123 | 3.8 | 1611 | 483 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.11 | Tier 1B: High GIDA Priority | 68.04 | 68.04 | 58.28 | 63.16 | B - Node 0.5-1 km | 0.68 | 0.07 | Line: Route 11.925km | Survey short node lateral; confirm port/fiber capacity, access and route. | 554
1 | 555 | 555 | 0102931005 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Danac | 16.7793 | 120.5395 | R | 605 | 3.8 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.91 | 12.82 | Tier 1B: High GIDA Priority | 38.15 | 38.15 | 88.16 | 63.15 | F - Nearest node and line over 5 km | 14.91 | 12.82 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 555
1 | 556 | 556 | 0402117021 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa III | 14.4005 | 120.8494 | U | 12517 | 3.4 | 3681 | 1104 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.39 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 69.99 | 69.99 | 56.27 | 63.13 | D - Other node or line within 3 km | 1.39 | 0.96 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 556
1 | 557 | 557 | 0301411016 | Region III (Central Luzon) | Bulacan | Marilao | Tabing Ilog | 14.7649 | 120.9489 | U | 8421 | 3.5 | 2406 | 722 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 0.28 | Tier 1B: High GIDA Priority | 66.82 | 66.82 | 59.42 | 63.12 | C - Line within 0.5 km; node over 1 km | 1.07 | 0.28 | Line: GOTACO TO HH 71 BULACAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 557
1 | 558 | 558 | 1102319016 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo Poblacion | 7.4294 | 125.8013 | U | 2994 | 3.7 | 809 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.18 | 59.18 | 67.06 | 63.12 | D - Other node or line within 3 km | 1.32 | 0.51 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 558
1 | 559 | 559 | 1380700016 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Tumana | 14.6479 | 121.1077 | U | 49950 | 4.03 | 12381 | 3714 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1 | 0.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.43 | 58.43 | 67.79 | 63.11 | C - Line within 0.5 km; node over 1 km | 1 | 0.31 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 559
1 | 560 | 560 | 1400108013 | Cordillera Administrative Region (CAR) | Abra | La Paz | Udangan | 17.639 | 120.6141 | R | 549 | 3.8 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.18 | 1.33 | Tier 1B: High GIDA Priority | 49.24 | 49.24 | 76.97 | 63.11 | D - Other node or line within 3 km | 5.18 | 1.32 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 560
1 | 561 | 561 | 0203131012 | Region II (Cagayan Valley) | Isabela | San Mariano | Dibuluan | 16.9981 | 122.1082 | R | 1951 | 3.8 | 513 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.22 | 25.39 | Tier 1B: High GIDA Priority | 46.64 | 46.64 | 79.58 | 63.11 | F - Nearest node and line over 5 km | 10.22 | 25.39 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 561
1 | 562 | 562 | 0702219009 | Region VII (Central Visayas) | Cebu | Consolacion | Nangka | 10.3721 | 123.9591 | U | 13307 | 3.8 | 3502 | 1051 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.49 | 0.48 | Tier 2A: High Commercial ROI | 73.21 | 73.21 | 52.99 | 63.1 | A - Node within 0.5 km | 0.49 | 0.47 | Line: DANAO - CEBU | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 562
1 | 563 | 563 | 0506211007 | Region V (Bicol Region) | Sorsogon | Magallanes | Biga | 12.8313 | 123.8216 | R | 1330 | 4 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.25 | 1.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.5 | 54.5 | 71.7 | 63.1 | D - Other node or line within 3 km | 2.25 | 1.31 | Line: 28,000 m | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 563
1 | 564 | 564 | 0500504012 | Region V (Bicol Region) | Albay | Guinobatan | Doña Tomasa | 13.1595 | 123.5743 | R | 1298 | 4.1 | 317 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.36 | 4.51 | Tier 1B: High GIDA Priority | 48.26 | 48.26 | 77.95 | 63.1 | E - Nearest node or line 3-5 km | 4.36 | 4.48 | Node: GNA002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 564
1 | 565 | 565 | 0403428011 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Malusak | 14.3142 | 121.1126 | U | 3185 | 3.3 | 965 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 1.36 | Tier 1B: High GIDA Priority | 62.32 | 62.32 | 63.87 | 63.09 | D - Other node or line within 3 km | 1.02 | 1.33 | Node: SRL004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 565
1 | 566 | 566 | 0402103049 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino VI | 14.3537 | 120.8803 | U | 21186 | 3.4 | 6231 | 1869 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.24 | 4.12 | Tier 1B: High GIDA Priority | 63.3 | 63.3 | 62.86 | 63.08 | E - Nearest node or line 3-5 km | 3.24 | 4.12 | Node: TZC002 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 566
1 | 567 | 567 | 1381100001 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 1 | 14.5373 | 121.0072 | U | 3935 | 3.3 | 1193 | 358 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 0.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.71 | 57.71 | 68.45 | 63.08 | C - Line within 0.5 km; node over 1 km | 1.46 | 0.41 | Line: Existing 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 567
1 | 568 | 568 | 0405814009 | Region IV-A (CALABARZON) | Rizal | Teresa | San Roque | 14.5679 | 121.2248 | R | 3326 | 3.6 | 924 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 1.69 | Tier 1B: High GIDA Priority | 68.05 | 68.05 | 58.07 | 63.06 | D - Other node or line within 3 km | 1.98 | 1.69 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 568
1 | 569 | 569 | 1381000014 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Martin De Porres | 14.4947 | 121.0431 | U | 15377 | 3.17 | 4856 | 1457 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.91 | 0.21 | Tier 1B: High GIDA Priority | 68 | 68 | 58.12 | 63.06 | B - Node 0.5-1 km | 0.91 | 0.13 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 569
1 | 570 | 570 | 0403428007 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Ibaba | 14.2915 | 121.1058 | U | 8845 | 3.3 | 2680 | 804 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.81 | 0.22 | Tier 1B: High GIDA Priority | 67.99 | 67.99 | 58.13 | 63.06 | B - Node 0.5-1 km | 0.81 | 0.19 | Line: BINAN - CABUYAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 570
1 | 571 | 571 | 1401105014 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Baculongan Sur | 16.752 | 120.8859 | R | 3798 | 3.5 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.24 | 5.17 | Tier 1B: High GIDA Priority | 61.58 | 61.58 | 64.55 | 63.06 | F - Nearest node and line over 5 km | 7.24 | 5.04 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 571
1 | 572 | 572 | 1102412019 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone II | 6.8521 | 125.3964 | U | 6310 | 3.4 | 1856 | 557 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 1.85 | Tier 1B: High GIDA Priority | 65.4 | 65.4 | 60.7 | 63.05 | D - Other node or line within 3 km | 1.87 | 1.85 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 572
1 | 573 | 573 | 0203133007 | Region II (Cagayan Valley) | Isabela | San Pablo | Caddangan/Limbauan | 17.431 | 121.8574 | R | 1705 | 3.8 | 449 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.92 | 6.02 | Tier 1B: High GIDA Priority | 46.3 | 46.3 | 79.79 | 63.05 | F - Nearest node and line over 5 km | 8.92 | 6.01 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 573
1 | 574 | 574 | 1381100161 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 161 | 14.5355 | 121.0079 | U | 2893 | 3.21 | 900 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.07 | 56.07 | 70.02 | 63.04 | C - Line within 0.5 km; node over 1 km | 1.44 | 0.47 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 574
1 | 575 | 575 | 1102506018 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Tiblawan | 6.4967 | 126.1194 | R | 4646 | 3.6 | 1291 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.97 | 42.47 | Tier 1B: High GIDA Priority | 52.54 | 52.54 | 73.54 | 63.04 | F - Nearest node and line over 5 km | 45.97 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 575
1 | 576 | 576 | 1403209018 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Mapaco | 17.5683 | 121.4314 | R | 932 | 4.3 | 217 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.16 | 0.34 | Tier 1B: High GIDA Priority | 46.67 | 46.67 | 79.41 | 63.04 | C - Line within 0.5 km; node over 1 km | 5.16 | 0.34 | Line: Tabuk-Conner | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 576
1 | 577 | 577 | 1705309023 | MIMAROPA Region | Palawan | Coron | San Nicolas | 12.0798 | 120.1931 | R | 3815 | 3.9 | 978 | 293 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.64 | 99.08 | Tier 1B: High GIDA Priority | 62.19 | 62.19 | 63.84 | 63.01 | F - Nearest node and line over 5 km | 6.64 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 577
1 | 578 | 578 | 0402113016 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pinagsanhan I A | 14.2415 | 120.7497 | R | 1651 | 3.4 | 486 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.04 | 2.44 | Tier 1B: High GIDA Priority | 50.75 | 50.75 | 75.26 | 63.01 | D - Other node or line within 3 km | 4.04 | 2.44 | Line: NCC001 TO NSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 578
1 | 579 | 579 | 0205008021 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Sanguit | 16.1396 | 121.1557 | R | 1147 | 3.8 | 302 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.96 | 20.32 | Tier 1B: High GIDA Priority | 45.99 | 45.99 | 80.02 | 63.01 | E - Nearest node or line 3-5 km | 3.96 | 20.28 | Node: DSV001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 579
1 | 580 | 580 | 0402117003 | Region IV-A (CALABARZON) | Cavite | Rosario | Kanluran | 14.414 | 120.863 | R | 3968 | 3.4 | 1167 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 69.14 | 69.14 | 56.85 | 62.99 | D - Other node or line within 3 km | 1.76 | 1.83 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 580
1 | 581 | 581 | 0102934038 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VII | 17.5731 | 120.3826 | R | 1628 | 3.8 | 428 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.42 | 1.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.59 | 54.59 | 71.4 | 62.99 | D - Other node or line within 3 km | 2.42 | 1.13 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 581
1 | 582 | 582 | 1380601121 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 121 | 13.707 | 122.986 | U | 4097 | 4.91 | 835 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.78 | 0.51 | Tier 1B: High GIDA Priority | 50.34 | 50.34 | 75.64 | 62.99 | D - Other node or line within 3 km | 4.78 | 0.51 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 582
1 | 583 | 583 | 0402103048 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino V | 14.2303 | 120.8724 | U | 6908 | 3.4 | 2032 | 610 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.69 | 5.51 | Tier 1B: High GIDA Priority | 58.3 | 58.3 | 67.66 | 62.98 | E - Nearest node or line 3-5 km | 3.69 | 5.51 | Node: IDC003-BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 583
1 | 584 | 584 | 1380612035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 868 | 13.9201 | 122.5929 | U | 3002 | 3.69 | 814 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.99 | 54.99 | 70.92 | 62.96 | B - Node 0.5-1 km | 0.79 | 0.53 | Line: CALAUAG - SIPOCOT | Survey short node lateral; confirm port/fiber capacity, access and route. | 584
1 | 585 | 585 | 0102806007 | Region I (Ilocos Region) | Ilocos Norte | Burgos | Buduan | 18.5014 | 120.6309 | R | 954 | 3.7 | 258 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 1.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.89 | 54.89 | 71.02 | 62.96 | D - Other node or line within 3 km | 2.15 | 1.12 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 585
1 | 586 | 586 | 0600410018 | Region VI (Western Visayas) | Aklan | Madalag | Paningayan | 11.5393 | 122.3137 | R | 1060 | 3.9 | 272 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.88 | 6.19 | Tier 1B: High GIDA Priority | 50.42 | 50.42 | 75.5 | 62.96 | F - Nearest node and line over 5 km | 6.88 | 6.18 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 586
1 | 587 | 587 | 1380601101 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 101 | 13.4528 | 120.3546 | U | 13659 | 3.46 | 3944 | 1183 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 51.27 | 51.33 | Tier 1B: High GIDA Priority | 49.75 | 49.75 | 76.16 | 62.96 | F - Nearest node and line over 5 km | 51.27 | 999999 | Node: CTG001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 587
1 | 588 | 588 | 1381701003 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Martires Del 96 | 14.5465 | 121.0616 | U | 5130 | 3.86 | 1328 | 398 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.4 | 59.4 | 66.5 | 62.95 | B - Node 0.5-1 km | 0.76 | 0.01 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 588
1 | 589 | 589 | 1402706003 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Ayangan | 16.9011 | 121.1892 | R | 499 | 3.9 | 128 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.84 | 12.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.66 | 47.66 | 78.21 | 62.94 | D - Other node or line within 3 km | 2.84 | 12.3 | Node: BEF002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 589
1 | 590 | 590 | 0405619056 | Region IV-A (CALABARZON) | Quezon | Gumaca | Villa Tañada | 13.917 | 122.0835 | R | 135 | 3.8 | 36 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.7 | 0.84 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.95 | 45.95 | 79.92 | 62.94 | D - Other node or line within 3 km | 2.7 | 0.79 | Line: AE UNQ001 TO CDQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 590
1 | 591 | 591 | 0405813002 | Region IV-A (CALABARZON) | Rizal | Taytay | Muzon | 14.5432 | 121.1444 | U | 32623 | 3.6 | 9062 | 2719 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.97 | 0.03 | Tier 1B: High GIDA Priority | 64.81 | 64.81 | 61.02 | 62.92 | C - Line within 0.5 km; node over 1 km | 1.97 | 0.03 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 591
1 | 592 | 592 | 0500511008 | Region V (Bicol Region) | Albay | Manito | Cawit | 13.1293 | 123.8626 | R | 1143 | 4.1 | 279 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 11.91 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.6 | 56.6 | 69.24 | 62.92 | B - Node 0.5-1 km | 0.89 | 11.9 | Node: MNT001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 592
1 | 593 | 593 | 1003508010 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Lumbac | 8.116 | 123.8825 | R | 611 | 4.2 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.26 | 0.6 | Tier 1B: High GIDA Priority | 44.79 | 44.79 | 81.05 | 62.92 | D - Other node or line within 3 km | 12.26 | 0.6 | Line: ILIGAN - PAGADIAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 593
1 | 594 | 594 | 0203137044 | Region II (Cagayan Valley) | Isabela | Tumauini | San Vicente | 17.32 | 121.8254 | R | 1801 | 3.8 | 474 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.35 | 2.17 | Tier 1B: High GIDA Priority | 49.52 | 49.52 | 76.3 | 62.91 | D - Other node or line within 3 km | 5.35 | 2.17 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 594
1 | 595 | 595 | 1381300051 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Krus Na Ligas | 14.6457 | 121.0625 | U | 21898 | 4.15 | 5275 | 1582 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.02 | 0.9 | Tier 1B: High GIDA Priority | 67.27 | 67.27 | 58.53 | 62.9 | D - Other node or line within 3 km | 1.02 | 0.86 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 595
1 | 596 | 596 | 1381300128 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Valencia | 14.7369 | 121.002 | U | 14525 | 4.63 | 3135 | 940 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 0.68 | Tier 1B: High GIDA Priority | 62.91 | 62.91 | 62.82 | 62.87 | D - Other node or line within 3 km | 1.78 | 0.54 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 596
1 | 597 | 597 | 1381300039 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa III | 14.6371 | 121.0469 | U | 8359 | 3.9 | 2146 | 644 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 61.28 | 61.28 | 64.47 | 62.87 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.08 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 597
1 | 598 | 598 | 1381300086 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-B | 14.6327 | 121.0613 | U | 4212 | 3.39 | 1243 | 373 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 0.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.51 | 58.51 | 67.23 | 62.87 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.1 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 598
1 | 599 | 599 | 0403428023 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Tagapo | 14.3189 | 121.1032 | U | 46153 | 3.3 | 13986 | 4196 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 2.16 | 0.56 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.13 | 58.13 | 67.6 | 62.87 | D - Other node or line within 3 km | 2.16 | 0.55 | Line: BINAN - CABUYAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 599
1 | 600 | 600 | 0402111018 | Region IV-A (CALABARZON) | Cavite | Kawit | Pulvorista | 14.4574 | 120.9218 | U | 12519 | 3.4 | 3682 | 1105 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.13 | 0.9 | Tier 1B: High GIDA Priority | 67.49 | 67.49 | 58.22 | 62.86 | D - Other node or line within 3 km | 3.13 | 0.9 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 600
1 | 601 | 601 | 0702219002 | Region VII (Central Visayas) | Cebu | Consolacion | Cansaga | 10.3788 | 123.9627 | U | 6651 | 3.8 | 1750 | 525 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.5 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 68.75 | 68.75 | 56.96 | 62.85 | B - Node 0.5-1 km | 0.5 | 0.09 | Line: Route 3.415km | Survey short node lateral; confirm port/fiber capacity, access and route. | 601
1 | 602 | 602 | 0403425026 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 1 | 14.3992 | 121.2729 | U | 24752 | 3.3 | 7501 | 2250 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 7.37 | 9.19 | Tier 1B: High GIDA Priority | 59.07 | 59.07 | 66.62 | 62.85 | F - Nearest node and line over 5 km | 7.37 | 9.15 | Node: JLR001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 602
1 | 603 | 603 | 1108205002 | Region XI (Davao Region) | Davao de Oro | Maragusan | Mapawa | 7.2857 | 126.1467 | U | 6057 | 3.7 | 1637 | 491 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.09 | 30.14 | Tier 1B: High GIDA Priority | 46.4 | 46.4 | 79.27 | 62.84 | F - Nearest node and line over 5 km | 32.09 | 30.11 | Line: TAGUM - PANTUKAN SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 603
1 | 604 | 604 | 0102901011 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Dalawa | 16.9164 | 120.5199 | R | 1448 | 3.8 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.65 | 6.02 | Tier 1B: High GIDA Priority | 50.91 | 50.91 | 74.75 | 62.83 | F - Nearest node and line over 5 km | 6.65 | 5.92 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 604
1 | 605 | 605 | 0600412013 | Region VI (Western Visayas) | Aklan | Malay | Napaan | 11.8956 | 121.923 | R | 968 | 3.9 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.37 | 4.17 | Tier 1B: High GIDA Priority | 45.49 | 45.49 | 80.17 | 62.83 | F - Nearest node and line over 5 km | 6.37 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 605
1 | 606 | 606 | 1380300018 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Pio Del Pilar | 14.5504 | 121.0089 | U | 55572 | 3.25 | 17087 | 5126 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.27 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.04 | 54.04 | 71.61 | 62.82 | A - Node within 0.5 km | 0.27 | 0.05 | Line: UG 288C via W-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 606
1 | 607 | 607 | 0402117017 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa III | 14.4312 | 120.8647 | R | 4448 | 3.4 | 1308 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 69.22 | 69.22 | 56.4 | 62.81 | D - Other node or line within 3 km | 1.98 | 1.95 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 607
1 | 608 | 608 | 1381300043 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Gulod | 14.7179 | 121.0395 | U | 63651 | 3.89 | 16355 | 4906 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.5 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.48 | 54.48 | 71.14 | 62.81 | A - Node within 0.5 km | 0.5 | 0.1 | Line: UG 144C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 608
1 | 609 | 609 | 0401033003 | Region IV-A (CALABARZON) | Batangas | Tingloy | Gamao | 13.654 | 120.9341 | R | 1068 | 3.6 | 297 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.79 | 16.44 | Tier 1B: High GIDA Priority | 48.85 | 48.85 | 76.78 | 62.81 | F - Nearest node and line over 5 km | 5.79 | 16.38 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 609
1 | 610 | 610 | 1402706018 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Langayan | 16.954 | 121.2383 | R | 487 | 3.9 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.71 | 19.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.83 | 47.83 | 77.8 | 62.81 | D - Other node or line within 3 km | 2.71 | 19.94 | Node: MOF001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 610
1 | 611 | 611 | 0600414003 | Region VI (Western Visayas) | Aklan | Nabas | Buenafortuna | 11.8267 | 122.0646 | R | 1432 | 3.9 | 367 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.71 | 1.57 | Tier 1B: High GIDA Priority | 47.61 | 47.61 | 78 | 62.81 | F - Nearest node and line over 5 km | 18.71 | 34.28 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 611
1 | 612 | 612 | 0401006037 | Region IV-A (CALABARZON) | Batangas | Bauan | San Roque | 13.7943 | 120.9851 | U | 6554 | 3.6 | 1821 | 546 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 1.53 | Tier 1B: High GIDA Priority | 63.4 | 63.4 | 62.19 | 62.79 | D - Other node or line within 3 km | 1.92 | 1.53 | Line: UG BUN001 TO SSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 612
1 | 613 | 613 | 1381300115 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Socorro | 14.6214 | 121.0583 | U | 25177 | 3.46 | 7287 | 2186 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.17 | 0.13 | Tier 1B: High GIDA Priority | 66.5 | 66.5 | 59.06 | 62.78 | A - Node within 0.5 km | 0.17 | 0.13 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 613
1 | 614 | 614 | 0301412019 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Perez | 14.764 | 121.0009 | U | 19701 | 3.5 | 5629 | 1689 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.69 | 1.71 | Tier 2A: High Commercial ROI | 70.05 | 70.05 | 55.48 | 62.77 | D - Other node or line within 3 km | 1.69 | 1.66 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 614
1 | 615 | 615 | 0403405002 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Banadero | 14.22 | 121.1646 | U | 13863 | 3.3 | 4201 | 1260 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.22 | 0.76 | Tier 2B: Moderate GIDA Inclusion | 68.97 | 68.97 | 56.56 | 62.77 | D - Other node or line within 3 km | 3.22 | 0.74 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 615
1 | 616 | 616 | 1381600002 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Bagbaguin | 14.7567 | 121.0036 | U | 15524 | 3.41 | 4558 | 1367 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.91 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 68.36 | 68.36 | 57.17 | 62.77 | B - Node 0.5-1 km | 0.91 | 0.83 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 616
1 | 617 | 617 | 0405627034 | Region IV-A (CALABARZON) | Quezon | Mauban | San Roque | 14.1992 | 121.7259 | R | 160 | 3.8 | 42 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.43 | 19.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.81 | 42.81 | 82.73 | 62.77 | D - Other node or line within 3 km | 2.43 | 19.51 | Node: MBQ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 617
1 | 618 | 618 | 1380606024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 418 | 14.1425 | 121.4269 | U | 2977 | 4.06 | 734 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.78 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.07 | 52.07 | 73.45 | 62.76 | D - Other node or line within 3 km | 1.23 | 0.77 | Line: UG LWL001001 TO NGL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 618
1 | 619 | 619 | 0405623021 | Region IV-A (CALABARZON) | Quezon | Lucban | Mahabang Parang | 14.1177 | 121.5917 | R | 226 | 3.8 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.64 | 2.52 | Tier 1B: High GIDA Priority | 41.36 | 41.36 | 84.16 | 62.76 | D - Other node or line within 3 km | 3.64 | 2.52 | Line: LILIW TO LUCENA AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 619
1 | 620 | 620 | 1380300009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Guadalupe Nuevo | 14.5644 | 121.0479 | U | 21596 | 3.54 | 6093 | 1828 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.04 | 0.37 | Tier 1B: High GIDA Priority | 64.51 | 64.51 | 60.99 | 62.75 | C - Line within 0.5 km; node over 1 km | 2.04 | 0.39 | Line: UG 144C via V-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 620
1 | 621 | 621 | 1381300084 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Project 6 | 14.6626 | 121.0399 | U | 12595 | 3.14 | 4008 | 1202 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.52 | 0.49 | Tier 1B: High GIDA Priority | 67.8 | 67.8 | 57.65 | 62.72 | B - Node 0.5-1 km | 0.52 | 0.46 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 621
1 | 622 | 622 | 1108603003 | Region XI (Davao Region) | Davao Occidental | Malita | Buhangin | 6.4896 | 125.5436 | R | 4998 | 3.6 | 1388 | 416 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.85 | 19.73 | Tier 1B: High GIDA Priority | 55.37 | 55.37 | 70.07 | 62.72 | F - Nearest node and line over 5 km | 18.85 | 19.7 | Node: MGD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 622
1 | 623 | 623 | 1380612028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 860 | 14.1513 | 121.2992 | U | 3480 | 3.89 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 1.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.46 | 55.46 | 69.9 | 62.68 | D - Other node or line within 3 km | 1.69 | 1.27 | Line: AE SPO001 TO LBL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 623
1 | 624 | 624 | 1108602034 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Tabayon | 5.7955 | 125.5565 | R | 3658 | 3.6 | 1016 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.18 | 54.31 | Tier 1B: High GIDA Priority | 51.78 | 51.78 | 73.57 | 62.68 | F - Nearest node and line over 5 km | 46.18 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 624
1 | 625 | 625 | 0201514004 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Cabanbanan Norte | 18.2573 | 121.9458 | R | 722 | 3.9 | 185 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.83 | 1.17 | Tier 1B: High GIDA Priority | 46.47 | 46.47 | 78.89 | 62.68 | D - Other node or line within 3 km | 3.83 | 1.17 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 625
1 | 626 | 626 | 1381300046 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kaligayahan | 14.7327 | 121.0532 | U | 62132 | 3.84 | 16192 | 4858 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.93 | 0.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.81 | 53.81 | 71.52 | 62.67 | B - Node 0.5-1 km | 0.93 | 0.21 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 626
1 | 627 | 627 | 0405619025 | Region IV-A (CALABARZON) | Quezon | Gumaca | Laguna | 13.8755 | 122.1128 | R | 491 | 3.8 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.29 | 0.74 | Tier 1B: High GIDA Priority | 43.57 | 43.57 | 81.75 | 62.66 | D - Other node or line within 3 km | 5.29 | 0.64 | Line: AE UNQ001 TO CDQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 627
1 | 628 | 628 | 1403209001 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Aciga | 17.607 | 121.3059 | R | 1010 | 4.3 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.66 | 10.76 | Tier 1B: High GIDA Priority | 42.9 | 42.9 | 82.43 | 62.66 | F - Nearest node and line over 5 km | 6.66 | 10.69 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 628
1 | 629 | 629 | 0300809001 | Region III (Central Luzon) | Bataan | Orani | Bagong Paraiso | 14.7999 | 120.5302 | R | 3258 | 3.6 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.1 | Tier 2A: High Commercial ROI | 70.42 | 70.42 | 54.89 | 62.65 | B - Node 0.5-1 km | 0.71 | 0.08 | Line: 96C DONA TO ORANI | Survey short node lateral; confirm port/fiber capacity, access and route. | 629
1 | 630 | 630 | 0402116003 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo I | 14.4285 | 120.8763 | R | 1999 | 3.4 | 588 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.7 | Tier 1B: High GIDA Priority | 61.66 | 61.66 | 63.65 | 62.65 | B - Node 0.5-1 km | 0.73 | 0.7 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 630
1 | 631 | 631 | 0201501001 | Region II (Cagayan Valley) | Cagayan | Abulug | Alinunu | 18.4313 | 121.459 | R | 1211 | 3.9 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.23 | 7.92 | Tier 1B: High GIDA Priority | 44.68 | 44.68 | 80.61 | 62.64 | F - Nearest node and line over 5 km | 6.23 | 7.91 | Node: BLC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 631
1 | 632 | 632 | 1108602021 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Mangile | 6.0063 | 125.6796 | R | 3502 | 3.6 | 973 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.74 | 53.16 | Tier 1B: High GIDA Priority | 50.9 | 50.9 | 74.34 | 62.62 | F - Nearest node and line over 5 km | 45.74 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 632
1 | 633 | 633 | 1381300130 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Veterans Village | 14.6541 | 121.0247 | U | 13070 | 3.79 | 3448 | 1034 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.04 | 0.48 | Tier 1B: High GIDA Priority | 65.12 | 65.12 | 60.08 | 62.6 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.48 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 633
1 | 634 | 634 | 1408106017 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | San Antonio | 18.1708 | 121.3542 | R | 245 | 4.2 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.03 | 0.17 | Tier 1B: High GIDA Priority | 49.08 | 49.08 | 76.1 | 62.59 | F - Nearest node and line over 5 km | 5.03 | 20.02 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 634
1 | 635 | 635 | 1401107018 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Tawangan | 16.6565 | 120.9108 | R | 1037 | 3.5 | 296 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.46 | 12.97 | Tier 1B: High GIDA Priority | 47.61 | 47.61 | 77.56 | 62.59 | F - Nearest node and line over 5 km | 8.46 | 12.97 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 635
1 | 636 | 636 | 0403405033 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Paciano Rizal | 14.2168 | 121.1368 | U | 17187 | 3.3 | 5208 | 1562 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.64 | 0.35 | Tier 2A: High Commercial ROI | 70.34 | 70.34 | 54.82 | 62.58 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.25 | Line: AE CLB001 TO CLB002 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 636
1 | 637 | 637 | 0403426024 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Central | 14.2854 | 121.4084 | R | 5029 | 3.3 | 1524 | 457 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.85 | Tier 2A: High Commercial ROI | 71.83 | 71.83 | 53.31 | 62.57 | B - Node 0.5-1 km | 0.86 | 0.84 | Line: UG SCL001 TO LWL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 637
1 | 638 | 638 | 0201511024 | Region II (Cagayan Valley) | Cagayan | Claveria | Santiago | 18.5871 | 121.1149 | R | 364 | 3.9 | 93 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.01 | 2.88 | Tier 1B: High GIDA Priority | 40.48 | 40.48 | 84.66 | 62.57 | D - Other node or line within 3 km | 5.01 | 2.88 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 638
1 | 639 | 639 | 0301414009 | Region III (Central Luzon) | Bulacan | Obando | Panghulo | 14.6979 | 120.9463 | U | 13716 | 3.5 | 3919 | 1176 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.65 | 0.52 | Tier 2A: High Commercial ROI | 70.4 | 70.4 | 54.72 | 62.56 | C - Line within 0.5 km; node over 1 km | 1.65 | 0.49 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 639
1 | 640 | 640 | 1381300011 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagumbayan | 14.6078 | 121.0827 | U | 24092 | 3.74 | 6444 | 1933 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.1 | 0.29 | Tier 1B: High GIDA Priority | 67.71 | 67.71 | 57.4 | 62.56 | A - Node within 0.5 km | 0.1 | 0.29 | Node: QCY008 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 640
1 | 641 | 641 | 1380400004 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Catmon | 14.6647 | 120.9623 | U | 45841 | 3.97 | 11543 | 3463 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.66 | 0.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 60.15 | 60.15 | 64.96 | 62.55 | B - Node 0.5-1 km | 0.66 | 0.41 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 641
1 | 642 | 642 | 0205008019 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Kimbutan | 16.1657 | 121.2272 | R | 1561 | 3.8 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.99 | 24.23 | Tier 1B: High GIDA Priority | 48.04 | 48.04 | 77.05 | 62.55 | E - Nearest node or line 3-5 km | 4.99 | 24.22 | Node: DSV001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 642
1 | 643 | 643 | 0600410004 | Region VI (Western Visayas) | Aklan | Madalag | Balactasan | 11.5354 | 122.2895 | R | 865 | 3.9 | 222 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.5 | 8.76 | Tier 1B: High GIDA Priority | 46.73 | 46.73 | 78.36 | 62.55 | F - Nearest node and line over 5 km | 9.5 | 8.75 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 643
1 | 644 | 644 | 0403410028 | Region IV-A (CALABARZON) | Laguna | Liliw | Maslun | 14.1527 | 121.4559 | R | 3042 | 3.3 | 922 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 1.6 | Tier 2A: High Commercial ROI | 72.71 | 72.71 | 52.37 | 62.54 | D - Other node or line within 3 km | 1.87 | 1.59 | Line: SAN PABLO - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 644
1 | 645 | 645 | 0403426026 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Sur | 14.2812 | 121.4113 | U | 4457 | 3.3 | 1351 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.3 | Tier 1B: High GIDA Priority | 64.95 | 64.95 | 60.12 | 62.54 | A - Node within 0.5 km | 0.3 | 0.3 | Line: SNL001 TO SCL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 645
1 | 646 | 646 | 0306916052 | Region III (Central Luzon) | Tarlac | City of Tarlac | Matatalaib | 15.4966 | 120.6 | U | 26018 | 3.9 | 6671 | 2001 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.16 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68 | 68 | 57.06 | 62.53 | C - Line within 0.5 km; node over 1 km | 2.16 | 0.33 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 646
1 | 647 | 647 | 0403416039 | Region IV-A (CALABARZON) | Laguna | Majayjay | Tanawan | 14.134 | 121.4371 | R | 93 | 3.3 | 28 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.27 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.63 | 54.63 | 70.43 | 62.53 | A - Node within 0.5 km | 0.27 | 0.21 | Line: LILIW - LUCENA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 647
1 | 648 | 648 | 1380601263 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 262 | 13.8748 | 121.9084 | U | 3638 | 4.59 | 793 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.4 | 54.4 | 70.67 | 62.53 | B - Node 0.5-1 km | 0.82 | 0.3 | Line: SAN JUAN TO UNISAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 648
1 | 649 | 649 | 1380500006 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Itaas | 14.5852 | 121.0408 | U | 11354 | 3.12 | 3640 | 1092 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.58 | 0.28 | Tier 1B: High GIDA Priority | 66.6 | 66.6 | 58.44 | 62.52 | B - Node 0.5-1 km | 0.58 | 0.15 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 649
1 | 650 | 650 | 1381100192 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 192 | 14.3106 | 121.0675 | U | 4274 | 3.38 | 1266 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.44 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 59.88 | 59.88 | 65.17 | 62.52 | A - Node within 0.5 km | 0.44 | 0.23 | Line: AE CRC005-BNL001-CLB001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 650
1 | 651 | 651 | 1381701004 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Poblacion | 14.5506 | 121.0743 | U | 2089 | 3.26 | 640 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.19 | 50.19 | 74.82 | 62.51 | B - Node 0.5-1 km | 0.92 | 0.08 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 651
1 | 652 | 652 | 1102315009 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Gredu | 7.2961 | 125.6784 | U | 16525 | 3.7 | 4466 | 1340 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.55 | 0.22 | Tier 2A: High Commercial ROI | 74.95 | 74.95 | 50.04 | 62.5 | B - Node 0.5-1 km | 0.55 | 0.02 | Line: DAVAO CITY - TRENTO | Survey short node lateral; confirm port/fiber capacity, access and route. | 652
1 | 653 | 653 | 0403426023 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santisima Cruz | 14.2881 | 121.412 | U | 10744 | 3.3 | 3256 | 977 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.01 | 0.9 | Tier 2B: Moderate GIDA Inclusion | 69.38 | 69.38 | 55.62 | 62.5 | D - Other node or line within 3 km | 1.01 | 0.88 | Line: UG SCL001 TO LWL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 653
1 | 654 | 654 | 0205701020 | Region II (Cagayan Valley) | Quirino | Aglipay | Diodol | 16.4385 | 121.5976 | R | 922 | 3.9 | 236 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.3 | 3.52 | Tier 1B: High GIDA Priority | 43.89 | 43.89 | 81.12 | 62.5 | E - Nearest node or line 3-5 km | 4.3 | 3.51 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 654
1 | 655 | 655 | 1404404007 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Dalican | 17.1225 | 120.9357 | R | 898 | 3.7 | 243 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.63 | 3.98 | Tier 1B: High GIDA Priority | 43.6 | 43.6 | 81.41 | 62.5 | E - Nearest node or line 3-5 km | 5.63 | 3.98 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 655
1 | 656 | 656 | 1401109002 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Lubo | 16.6681 | 120.716 | R | 1437 | 3.5 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.11 | 6 | Tier 1B: High GIDA Priority | 51.9 | 51.9 | 73.06 | 62.48 | F - Nearest node and line over 5 km | 7.11 | 5.96 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 656
1 | 657 | 657 | 1381200020 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Joaquin | 14.5514 | 121.0759 | U | 14211 | 4.54 | 3128 | 938 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.03 | Tier 1B: High GIDA Priority | 64.05 | 64.05 | 60.86 | 62.46 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.03 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 657
1 | 658 | 658 | 1380500005 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Ilaya | 14.5716 | 121.0447 | U | 24467 | 3.07 | 7968 | 2390 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.39 | 0.05 | Tier 1B: High GIDA Priority | 63.23 | 63.23 | 61.7 | 62.46 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.05 | Line: UG 144C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 658
1 | 659 | 659 | 0401003013 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 8 | 13.9431 | 120.7362 | R | 2170 | 3.6 | 603 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.13 | Tier 1B: High GIDA Priority | 61.83 | 61.83 | 63.09 | 62.46 | B - Node 0.5-1 km | 0.88 | 0.04 | Line: WP BYB001 TO BCY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 659
1 | 660 | 660 | 0300811021 | Region III (Central Luzon) | Bataan | Pilar | Poblacion | 14.6674 | 120.5584 | R | 1369 | 3.6 | 380 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 0.24 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.51 | 53.51 | 71.42 | 62.46 | C - Line within 0.5 km; node over 1 km | 2.3 | 0.21 | Line: 48 CORE 4X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 660
1 | 661 | 661 | 0402123007 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Benjamin Tirona | 14.2983 | 121.0137 | R | 3078 | 3.4 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.17 | 4.16 | Tier 1B: High GIDA Priority | 64.21 | 64.21 | 60.68 | 62.45 | D - Other node or line within 3 km | 2.17 | 4.16 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 661
1 | 662 | 662 | 1381300090 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Roxas | 14.628 | 121.0226 | U | 11214 | 3.6 | 3111 | 933 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 1.14 | Tier 1B: High GIDA Priority | 63.7 | 63.7 | 61.19 | 62.45 | D - Other node or line within 3 km | 1.27 | 1.08 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 662
1 | 663 | 663 | 1381100065 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 65 | 14.5879 | 121.073 | U | 2869 | 3.44 | 833 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.83 | 54.83 | 70.07 | 62.45 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.16 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 663
1 | 664 | 664 | 1381300068 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Nagkaisang Nayon | 14.7236 | 121.025 | U | 54477 | 3.61 | 15071 | 4521 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.85 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.61 | 53.61 | 71.3 | 62.45 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.21 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 664
1 | 665 | 665 | 0403425011 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Poblacion | 14.1293 | 121.1811 | U | 6326 | 3.3 | 1917 | 575 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.41 | 4.05 | Tier 1B: High GIDA Priority | 57.29 | 57.29 | 67.6 | 62.44 | E - Nearest node or line 3-5 km | 4.41 | 4.03 | Line: UG SPO001 TO STB001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 665
1 | 666 | 666 | 0307112017 | Region III (Central Luzon) | Zambales | San Narciso | Omaya | 15.0045 | 120.161 | R | 641 | 3.8 | 169 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.93 | 3.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48 | 48 | 76.89 | 62.44 | D - Other node or line within 3 km | 2.93 | 3.41 | Node: SMZ002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 666
1 | 667 | 667 | 1403206003 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Mabongtot | 17.3382 | 121.1906 | R | 601 | 4.3 | 140 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.39 | 1.66 | Tier 1B: High GIDA Priority | 45.94 | 45.94 | 78.92 | 62.43 | D - Other node or line within 3 km | 9.39 | 1.62 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 667
1 | 668 | 668 | 0301412026 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Caingin | 14.7268 | 120.9688 | U | 7207 | 3.5 | 2059 | 618 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 0.82 | Tier 1B: High GIDA Priority | 65.38 | 65.38 | 59.46 | 62.42 | D - Other node or line within 3 km | 1.29 | 0.82 | Line: GOTACO TO HH 71 BULACAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 668
1 | 669 | 669 | 0403403012 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Malaban | 14.3461 | 121.0888 | U | 39450 | 3.3 | 11955 | 3586 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.63 | 0.85 | Tier 1B: High GIDA Priority | 61.59 | 61.59 | 63.26 | 62.42 | D - Other node or line within 3 km | 1.63 | 0.85 | Line: RELIANCE TO SAN PABLO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 669
1 | 670 | 670 | 1102403028 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 1 | 6.7576 | 125.3554 | U | 17556 | 3.4 | 5164 | 1549 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.29 | 1.71 | Tier 2A: High Commercial ROI | 76.15 | 76.15 | 48.66 | 62.4 | A - Node within 0.5 km | 0.29 | 1.71 | Node: DSD002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 670
1 | 671 | 671 | 1381300058 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Manresa | 14.628 | 121.0341 | U | 21729 | 3.56 | 6108 | 1832 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.16 | 0.49 | Tier 1B: High GIDA Priority | 65.96 | 65.96 | 58.84 | 62.4 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.49 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 671
1 | 672 | 672 | 0402106059 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran III | 14.3225 | 121.008 | U | 16208 | 3.4 | 4767 | 1430 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.67 | 3.33 | Tier 1B: High GIDA Priority | 65.9 | 65.9 | 58.85 | 62.37 | D - Other node or line within 3 km | 2.67 | 3.97 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 672
1 | 673 | 673 | 1380605052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 350 | 14.1592 | 122.5318 | U | 8026 | 3.95 | 2032 | 610 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.78 | 1.89 | Tier 1B: High GIDA Priority | 54.7 | 54.7 | 69.99 | 62.35 | D - Other node or line within 3 km | 7.78 | 1.89 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 673
1 | 674 | 674 | 0307706004 | Region III (Central Luzon) | Aurora | Dipaculao | Calaocan | 16.1287 | 121.7909 | R | 620 | 3.8 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.14 | 0.24 | Tier 1B: High GIDA Priority | 44.26 | 44.26 | 80.44 | 62.35 | C - Line within 0.5 km; node over 1 km | 6.14 | 0.15 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 674
1 | 675 | 675 | 0506216049 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Maricrum | 13.0125 | 124.0166 | R | 1659 | 4 | 415 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.06 | 3.62 | Tier 1B: High GIDA Priority | 51.73 | 51.73 | 72.95 | 62.34 | E - Nearest node or line 3-5 km | 3.06 | 3.43 | Node: SCS003 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 675
1 | 676 | 676 | 0203133017 | Region II (Cagayan Valley) | Isabela | San Pablo | Tupa | 17.481 | 121.8766 | R | 2485 | 3.8 | 654 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.35 | 7.65 | Tier 1B: High GIDA Priority | 48.58 | 48.58 | 76.1 | 62.34 | F - Nearest node and line over 5 km | 12.35 | 7.65 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 676
1 | 677 | 677 | 0506212001 | Region V (Bicol Region) | Sorsogon | Matnog | Balocawe | 12.5998 | 124.0661 | R | 1026 | 4 | 256 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.25 | 0.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.78 | 52.78 | 71.89 | 62.33 | D - Other node or line within 3 km | 2.25 | 0.5 | Line: MATNOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 677
1 | 678 | 678 | 0402106044 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Maria | 14.3218 | 120.9256 | U | 5335 | 3.4 | 1569 | 471 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.51 | 3.32 | Tier 1B: High GIDA Priority | 57.07 | 57.07 | 67.58 | 62.32 | E - Nearest node or line 3-5 km | 3.51 | 3.32 | Line: NCC001 TO TGY001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 678
1 | 679 | 679 | 1208006003 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Kinam | 5.9507 | 125.4321 | U | 12767 | 3.9 | 3274 | 982 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.18 | 32.56 | Tier 1B: High GIDA Priority | 51.74 | 51.74 | 72.89 | 62.32 | F - Nearest node and line over 5 km | 24.18 | 32.55 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 679
1 | 680 | 680 | 0600410022 | Region VI (Western Visayas) | Aklan | Madalag | Singay | 11.5372 | 122.2981 | R | 336 | 3.9 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.55 | 7.83 | Tier 1B: High GIDA Priority | 46.3 | 46.3 | 78.35 | 62.32 | F - Nearest node and line over 5 km | 8.55 | 7.82 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 680
1 | 681 | 681 | 0403404015 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | San Isidro | 14.2182 | 121.3147 | U | 25567 | 3.3 | 7748 | 2324 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 3.9 | 3.62 | Tier 1B: High GIDA Priority | 60.64 | 60.64 | 63.98 | 62.31 | E - Nearest node or line 3-5 km | 3.9 | 3.62 | Line: CLB001 TO SCL001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 681
1 | 682 | 682 | 1380700004 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Jesus De La Peña | 14.6396 | 121.1049 | U | 10224 | 3.6 | 2840 | 852 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.52 | Tier 1B: High GIDA Priority | 63.07 | 63.07 | 61.53 | 62.3 | D - Other node or line within 3 km | 1.18 | 0.51 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 682
1 | 683 | 683 | 0500511007 | Region V (Bicol Region) | Albay | Manito | Cawayan | 13.0584 | 123.8214 | R | 1873 | 4.1 | 457 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.93 | 8.03 | Tier 1B: High GIDA Priority | 52.61 | 52.61 | 71.97 | 62.29 | F - Nearest node and line over 5 km | 8.93 | 8.01 | Line: FOC-7,512m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 683
1 | 684 | 684 | 0603014004 | Region VI (Western Visayas) | Iloilo | Carles | Bancal | 11.5586 | 123.1532 | U | 5945 | 3.8 | 1564 | 469 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.55 | 11.48 | Tier 1B: High GIDA Priority | 53.49 | 53.49 | 71.07 | 62.28 | F - Nearest node and line over 5 km | 11.55 | 11.45 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 684
1 | 685 | 685 | 0402111019 | Region IV-A (CALABARZON) | Cavite | Kawit | Samala-Marquez | 14.4487 | 120.9259 | U | 6789 | 3.4 | 1997 | 599 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.45 | 0.23 | Tier 1B: High GIDA Priority | 63.17 | 63.17 | 61.37 | 62.27 | C - Line within 0.5 km; node over 1 km | 2.45 | 0.23 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 685
1 | 686 | 686 | 1380610016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 701 | 14.1683 | 121.7163 | U | 3328 | 3.43 | 969 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 16.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.09 | 54.09 | 70.46 | 62.27 | D - Other node or line within 3 km | 1.16 | 16.79 | Node: MBQ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 686
1 | 687 | 687 | 0305416024 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Agustin | 15.0418 | 120.6693 | U | 23914 | 4 | 5978 | 1793 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.12 | 0.45 | Tier 2A: High Commercial ROI | 70.61 | 70.61 | 53.91 | 62.26 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.45 | Line: SAN FERNANDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 687
1 | 688 | 688 | 0402103008 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay I | 14.3033 | 120.9061 | U | 21018 | 3.4 | 6182 | 1855 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.1 | 1.08 | Tier 2A: High Commercial ROI | 70.02 | 70.02 | 54.5 | 62.26 | D - Other node or line within 3 km | 1.1 | 1.29 | Node: TRC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 688
1 | 689 | 689 | 1402706036 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Epeng | 16.9605 | 121.1803 | R | 497 | 3.9 | 127 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.73 | 13.36 | Tier 1B: High GIDA Priority | 46.66 | 46.66 | 77.87 | 62.26 | E - Nearest node or line 3-5 km | 3.73 | 15.72 | Node: MOF002 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 689
1 | 690 | 690 | 0702234008 | Region VII (Central Visayas) | Cebu | City of Naga | Colon | 10.2213 | 123.7611 | U | 5364 | 3.8 | 1412 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 0.15 | Tier 1B: High GIDA Priority | 65.47 | 65.47 | 58.94 | 62.2 | C - Line within 0.5 km; node over 1 km | 1.94 | 0.11 | Line: CEBU - TOLEDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 690
1 | 691 | 691 | 0702232010 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward I | 10.2443 | 123.7983 | U | 2358 | 3.8 | 621 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.6 | 56.6 | 67.81 | 62.2 | A - Node within 0.5 km | 0.45 | 0.21 | Line: CEBU - TOLEDO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 691
1 | 692 | 692 | 1381200009 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kapitolyo | 14.5678 | 121.0631 | U | 10211 | 3.36 | 3041 | 912 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.52 | Tier 1B: High GIDA Priority | 62.91 | 62.91 | 61.44 | 62.18 | C - Line within 0.5 km; node over 1 km | 1.61 | 0.48 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 692
1 | 693 | 693 | 1102315028 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Salvacion | 7.3178 | 125.6887 | U | 10928 | 3.7 | 2954 | 886 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.12 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 68.02 | 68.02 | 56.27 | 62.15 | C - Line within 0.5 km; node over 1 km | 2.12 | 0.12 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 693
1 | 694 | 694 | 1380614023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 767 | 13.958 | 120.7604 | U | 5497 | 4.18 | 1315 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.51 | 1.39 | Tier 1B: High GIDA Priority | 55.25 | 55.25 | 69.06 | 62.15 | D - Other node or line within 3 km | 3.51 | 1.39 | Line: TUY - STA. TERESITA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 694
1 | 695 | 695 | 0405616013 | Region IV-A (CALABARZON) | Quezon | General Luna | Magsaysay | 13.6985 | 122.2717 | R | 679 | 3.8 | 179 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 6.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.67 | 50.67 | 73.62 | 62.15 | D - Other node or line within 3 km | 1.2 | 6.03 | Node: CTQ004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 695
1 | 696 | 696 | 1381000002 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Don Galo | 14.5081 | 120.9919 | U | 12397 | 3.03 | 4088 | 1226 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.12 | 0.27 | Tier 1B: High GIDA Priority | 66.86 | 66.86 | 57.41 | 62.14 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.27 | Line: Aerial 216C MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 696
1 | 697 | 697 | 0600410011 | Region VI (Western Visayas) | Aklan | Madalag | Logohon | 11.5317 | 122.2969 | R | 511 | 3.9 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.9 | 8.22 | Tier 1B: High GIDA Priority | 45.89 | 45.89 | 78.35 | 62.12 | F - Nearest node and line over 5 km | 8.9 | 8.2 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 697
1 | 698 | 698 | 0301402003 | Region III (Central Luzon) | Bulacan | Balagtas | Borol 1st | 14.8239 | 120.9051 | U | 11268 | 3.5 | 3219 | 966 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 0.22 | Tier 1B: High GIDA Priority | 65.79 | 65.79 | 58.43 | 62.11 | C - Line within 0.5 km; node over 1 km | 3.5 | 0.38 | Line: Mnla Pipe | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 698
1 | 699 | 699 | 1208001008 | Region XII (SOCCSKSARGEN) | Sarangani | Alabel | Pag-asa | 6.1229 | 125.409 | U | 8455 | 3.9 | 2168 | 650 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.62 | 20.68 | Tier 1B: High GIDA Priority | 51.85 | 51.85 | 72.36 | 62.11 | F - Nearest node and line over 5 km | 14.62 | 20.68 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 699
1 | 700 | 700 | 0405628013 | Region IV-A (CALABARZON) | Quezon | Mulanay | Buenavista | 13.5073 | 122.4569 | R | 1369 | 3.8 | 360 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.72 | 6.3 | Tier 1B: High GIDA Priority | 45.7 | 45.7 | 78.52 | 62.11 | F - Nearest node and line over 5 km | 6.72 | 6.19 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 700
1 | 701 | 701 | 0102911003 | Region I (Ilocos Region) | Ilocos Sur | Lidlidda | Bugui | 17.2627 | 120.5401 | R | 244 | 3.8 | 64 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 2.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.91 | 47.91 | 76.27 | 62.09 | D - Other node or line within 3 km | 2.2 | 2.19 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 701
1 | 702 | 702 | 0201506038 | Region II (Cagayan Valley) | Cagayan | Baggao | Santa Margarita | 17.9524 | 122.076 | U | 5147 | 3.9 | 1320 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.67 | 34.36 | Tier 1B: High GIDA Priority | 45.64 | 45.64 | 78.54 | 62.09 | F - Nearest node and line over 5 km | 19.67 | 999999 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 702
1 | 703 | 703 | 0403405003 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Banlic | 14.2286 | 121.1522 | U | 20098 | 3.3 | 6090 | 1827 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.13 | 1.35 | Tier 2B: Moderate GIDA Inclusion | 67.1 | 67.1 | 57.03 | 62.07 | D - Other node or line within 3 km | 3.13 | 1.33 | Line: RELIANCE TO SAN PABLO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 703
1 | 704 | 704 | 1380601152 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 152 | 14.2409 | 121.1956 | U | 6016 | 4.31 | 1396 | 419 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.12 | 3.13 | Tier 1B: High GIDA Priority | 50.64 | 50.64 | 73.5 | 62.07 | E - Nearest node or line 3-5 km | 5.12 | 3.11 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 704
1 | 705 | 705 | 0405804027 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pantok | 14.4945 | 121.1801 | U | 16083 | 3.6 | 4468 | 1340 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.1 | 0.1 | Tier 2A: High Commercial ROI | 74.3 | 74.3 | 49.82 | 62.06 | A - Node within 0.5 km | 0.1 | 0.1 | Node: BIR001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 705
1 | 706 | 706 | 0401005097 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Rita Karsada | 13.7783 | 121.0411 | U | 20924 | 3.6 | 5812 | 1744 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.97 | 0.05 | Tier 2A: High Commercial ROI | 70.74 | 70.74 | 53.36 | 62.05 | B - Node 0.5-1 km | 0.97 | 0.05 | Line: WP BYB001 TO BCY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 706
1 | 707 | 707 | 1380300020 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Poblacion | 14.5636 | 121.0336 | U | 17088 | 3.47 | 4928 | 1478 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.61 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 68.49 | 68.49 | 55.61 | 62.05 | B - Node 0.5-1 km | 0.61 | 0.36 | Line: UG 144C via V-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 707
1 | 708 | 708 | 1381300101 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Martin De Porres | 14.6883 | 121.1071 | U | 12012 | 3.45 | 3480 | 1044 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.98 | 0.56 | Tier 1B: High GIDA Priority | 65.33 | 65.33 | 58.77 | 62.05 | B - Node 0.5-1 km | 0.98 | 0.51 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 708
1 | 709 | 709 | 0402116009 | Region IV-A (CALABARZON) | Cavite | Noveleta | Santa Rosa I | 14.4281 | 120.893 | U | 5192 | 3.4 | 1527 | 458 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 0.23 | Tier 1B: High GIDA Priority | 63.9 | 63.9 | 60.2 | 62.05 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.07 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 709
1 | 710 | 710 | 0600417006 | Region VI (Western Visayas) | Aklan | Tangalan | Lanipga | 11.739 | 122.2105 | R | 342 | 3.9 | 88 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.38 | 2.79 | Tier 1B: High GIDA Priority | 45.36 | 45.36 | 78.75 | 62.05 | F - Nearest node and line over 5 km | 9.38 | 16.34 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 710
1 | 711 | 711 | 0301411001 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Norte | 14.7743 | 120.944 | U | 11934 | 3.5 | 3410 | 1023 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.55 | 0.5 | Tier 2A: High Commercial ROI | 70.9 | 70.9 | 53.17 | 62.04 | B - Node 0.5-1 km | 0.55 | 0.49 | Line: GOTACO TO HH 71 BULACAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 711
1 | 712 | 712 | 0300806004 | Region III (Central Luzon) | Bataan | Limay | Lamao | 14.5083 | 120.588 | U | 20836 | 3.6 | 5788 | 1736 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 6.24 | 1.48 | Tier 1B: High GIDA Priority | 65.49 | 65.49 | 58.6 | 62.04 | D - Other node or line within 3 km | 6.24 | 1.45 | Line: 24 CORE 2X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 712
1 | 713 | 713 | 1380604019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 286 | 14.2185 | 122.3429 | U | 4216 | 3.71 | 1136 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.84 | 6.31 | Tier 1B: High GIDA Priority | 49.08 | 49.08 | 74.98 | 62.03 | F - Nearest node and line over 5 km | 6.84 | 6.31 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 713
1 | 714 | 714 | 0402108025 | Region IV-A (CALABARZON) | Cavite | City of General Trias | San Juan I | 14.3826 | 120.8773 | U | 5496 | 3.4 | 1616 | 485 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 1.88 | Tier 1B: High GIDA Priority | 63.58 | 63.58 | 60.42 | 62 | D - Other node or line within 3 km | 1.43 | 1.88 | Node: TZC003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 714
1 | 715 | 715 | 1908709007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Guiday T. Biruar | 17.254 | 122.228 | R | 8250 | 4.3 | 1919 | 576 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 52.01 | 52.01 | 71.98 | 62 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 715
1 | 716 | 716 | 0601913014 | Region VI (Western Visayas) | Capiz | President Roxas | Pandan | 11.4739 | 122.9183 | R | 720 | 3.8 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.21 | 4.35 | Tier 1B: High GIDA Priority | 46.31 | 46.31 | 77.66 | 61.98 | E - Nearest node or line 3-5 km | 9.21 | 4.35 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 716
1 | 717 | 717 | 0403411004 | Region IV-A (CALABARZON) | Laguna | Los Baños | Batong Malake | 14.1741 | 121.2435 | U | 13788 | 3.3 | 4178 | 1253 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.58 | 0.44 | Tier 2A: High Commercial ROI | 73.06 | 73.06 | 50.83 | 61.95 | B - Node 0.5-1 km | 0.58 | 0.44 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 717
1 | 718 | 718 | 0402123026 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Severino De Las Alas | 14.2807 | 121.0165 | U | 8000 | 3.4 | 2353 | 706 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 4.94 | Tier 1B: High GIDA Priority | 62.1 | 62.1 | 61.79 | 61.95 | D - Other node or line within 3 km | 1.57 | 4.94 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 718
1 | 719 | 719 | 1381300050 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kaunlaran | 14.6143 | 121.0493 | U | 14602 | 3.8 | 3839 | 1152 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.1 | 0.9 | Tier 1B: High GIDA Priority | 66.17 | 66.17 | 57.71 | 61.94 | D - Other node or line within 3 km | 1.1 | 0.83 | Line: UG 144C via W-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 719
1 | 720 | 720 | 0102917004 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Matibuey | 17.2121 | 120.6624 | R | 1080 | 3.8 | 284 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.52 | 0.98 | Tier 1B: High GIDA Priority | 50.29 | 50.29 | 73.56 | 61.92 | D - Other node or line within 3 km | 8.52 | 0.86 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 720
1 | 721 | 721 | 1381100189 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 189 | 14.4512 | 121.2274 | U | 3437 | 3.65 | 942 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.25 | 2.78 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.22 | 52.22 | 71.59 | 61.9 | D - Other node or line within 3 km | 2.25 | 2.78 | Node: BIR003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 721
1 | 722 | 722 | 1381100043 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 43 | 14.5309 | 121.0623 | U | 2734 | 3.69 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.06 | 52.06 | 71.75 | 61.9 | C - Line within 0.5 km; node over 1 km | 1.33 | 0.21 | Line: Existing 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 722
1 | 723 | 723 | 0402116005 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan I | 14.4357 | 120.8876 | R | 3130 | 3.4 | 921 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 69.99 | 69.99 | 53.79 | 61.89 | B - Node 0.5-1 km | 0.85 | 0.52 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 723
1 | 724 | 724 | 0405805014 | Region IV-A (CALABARZON) | Rizal | Cainta | San Andres | 14.5741 | 121.1106 | U | 115400 | 3.6 | 32056 | 9617 | Band n50 (1.5 GHz, 100 MHz TDD) | 10 | 1 | 0.66 | 0.61 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.3 | 52.3 | 71.43 | 61.87 | B - Node 0.5-1 km | 0.66 | 0.49 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 724
1 | 725 | 725 | 0600410003 | Region VI (Western Visayas) | Aklan | Madalag | Bacyang | 11.5387 | 122.285 | R | 567 | 3.9 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.44 | 9.07 | Tier 1B: High GIDA Priority | 45.29 | 45.29 | 78.42 | 61.86 | F - Nearest node and line over 5 km | 9.44 | 9.05 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 725
1 | 726 | 726 | 0205706005 | Region II (Cagayan Valley) | Quirino | Nagtipunan | La Conwap | 16.2168 | 121.5997 | R | 442 | 3.9 | 113 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 7.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.1 | 47.1 | 76.57 | 61.84 | A - Node within 0.5 km | 0.17 | 7.1 | Node: NTQ001-BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 726
1 | 727 | 727 | 1404403002 | Cordillera Administrative Region (CAR) | Mountain Province | Besao | Ambaguio | 17.12 | 120.8453 | R | 179 | 3.7 | 48 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.1 | 7.09 | Tier 1B: High GIDA Priority | 44.66 | 44.66 | 79.02 | 61.84 | F - Nearest node and line over 5 km | 7.1 | 7.09 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 727
1 | 728 | 728 | 1381300028 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Damayang Lagi | 14.6709 | 121.0297 | U | 19920 | 3.72 | 5351 | 1605 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.09 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 67.04 | 67.04 | 56.61 | 61.83 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.3 | Line: UG 144C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 728
1 | 729 | 729 | 0402111001 | Region IV-A (CALABARZON) | Cavite | Kawit | Binakayan-Kanluran | 14.4395 | 120.9112 | R | 2655 | 3.4 | 781 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.23 | 0.09 | Tier 1B: High GIDA Priority | 63.08 | 63.08 | 60.55 | 61.82 | C - Line within 0.5 km; node over 1 km | 3.23 | 0.09 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 729
1 | 730 | 730 | 1381300055 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Loyola Heights | 14.6711 | 121.0107 | U | 21768 | 4.34 | 5010 | 1503 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.08 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 69.53 | 69.53 | 54.09 | 61.81 | A - Node within 0.5 km | 0.08 | 0.08 | Line: Aerial 216C MTF | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 730
1 | 731 | 731 | 1381300020 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Central | 14.6606 | 121.0574 | U | 20031 | 3.79 | 5283 | 1585 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.38 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 66.6 | 66.6 | 57.02 | 61.81 | C - Line within 0.5 km; node over 1 km | 1.38 | 0.2 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 731
1 | 732 | 732 | 1381300082 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pinyahan | 14.6383 | 121.0505 | U | 22335 | 3.58 | 6242 | 1873 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.78 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 66.51 | 66.51 | 57.11 | 61.81 | B - Node 0.5-1 km | 0.78 | 0.39 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 732
1 | 733 | 733 | 0102903022 | Region I (Ilocos Region) | Ilocos Sur | Bantay | San Mariano | 17.5525 | 120.4879 | R | 365 | 3.8 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.94 | 2.62 | Tier 1B: High GIDA Priority | 38.86 | 38.86 | 84.76 | 61.81 | D - Other node or line within 3 km | 7.94 | 2.62 | Line: SEGMENT 2 (CANDON - VIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 733
1 | 734 | 734 | 0300809003 | Region III (Central Luzon) | Bataan | Orani | Bayan | 14.7902 | 120.5197 | U | 6663 | 3.6 | 1851 | 555 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 1.04 | Tier 1B: High GIDA Priority | 63.22 | 63.22 | 60.38 | 61.8 | D - Other node or line within 3 km | 2.23 | 1.01 | Line: 96C DONA TO ORANI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 734
1 | 735 | 735 | 1380200016 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pulang Lupa Dos | 14.4586 | 120.9867 | U | 32788 | 3.8 | 8627 | 2588 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.71 | 0.72 | Tier 1B: High GIDA Priority | 63.68 | 63.68 | 59.9 | 61.79 | B - Node 0.5-1 km | 0.71 | 0.66 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 735
1 | 736 | 736 | 0402118060 | Region IV-A (CALABARZON) | Cavite | Silang | Narra II | 14.2313 | 120.9998 | R | 2291 | 3.4 | 674 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.15 | 2.56 | Tier 1B: High GIDA Priority | 54.98 | 54.98 | 68.59 | 61.79 | D - Other node or line within 3 km | 5.15 | 2.55 | Line: SILANG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 736
1 | 737 | 737 | 1108601008 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Dalupan | 6.1927 | 125.6364 | R | 3750 | 3.6 | 1042 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.81 | 42.21 | Tier 1B: High GIDA Priority | 51.94 | 51.94 | 71.61 | 61.78 | F - Nearest node and line over 5 km | 40.81 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 737
1 | 738 | 738 | 1402701007 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Banao | 16.8814 | 121.1886 | R | 517 | 3.9 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.89 | 11.3 | Tier 1B: High GIDA Priority | 46.5 | 46.5 | 77.07 | 61.78 | E - Nearest node or line 3-5 km | 3.89 | 11.23 | Node: BEF002 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 738
1 | 739 | 739 | 0301407024 | Region III (Central Luzon) | Bulacan | Calumpit | San Marcos | 14.8978 | 120.7787 | U | 2792 | 3.5 | 798 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.46 | 58.46 | 65.06 | 61.76 | C - Line within 0.5 km; node over 1 km | 1.51 | 0.28 | Line: Mnla Pipe | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 739
1 | 740 | 740 | 0105527061 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Pacalat | 15.7425 | 120.2765 | R | 1026 | 3.6 | 285 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.63 | 15.99 | Tier 1B: High GIDA Priority | 43.51 | 43.51 | 80.02 | 61.76 | F - Nearest node and line over 5 km | 7.63 | 15.98 | Node: MMP001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 740
1 | 741 | 741 | 1381200007 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kalawaan | 14.5514 | 121.0837 | U | 33677 | 3.59 | 9379 | 2814 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.08 | 0.24 | Tier 1B: High GIDA Priority | 62.03 | 62.03 | 61.47 | 61.75 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.19 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 741
1 | 742 | 742 | 0200901006 | Region II (Cagayan Valley) | Batanes | Basco | Kayhuvokan | 20.4475 | 121.9764 | R | 1899 | 3 | 633 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 223.93 | 217.11 | Tier 1B: High GIDA Priority | 46.57 | 46.57 | 76.93 | 61.75 | F - Nearest node and line over 5 km | 220.21 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 742
1 | 743 | 743 | 1403214007 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Lubo | 17.2621 | 121.231 | R | 497 | 4.3 | 116 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.72 | 7.68 | Tier 1B: High GIDA Priority | 43.03 | 43.03 | 80.46 | 61.75 | F - Nearest node and line over 5 km | 8.72 | 7.65 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 743
1 | 744 | 744 | 1381600014 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Lingunan | 14.7201 | 120.9757 | U | 25423 | 3.33 | 7624 | 2287 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.13 | 0.49 | Tier 1B: High GIDA Priority | 62.47 | 62.47 | 61 | 61.74 | C - Line within 0.5 km; node over 1 km | 2.13 | 0.43 | Line: Existing MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 744
1 | 745 | 745 | 1381600007 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Canumay West | 14.7079 | 120.9717 | U | 26517 | 3.25 | 8152 | 2446 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.24 | 0.64 | Tier 1B: High GIDA Priority | 63.26 | 63.26 | 60.2 | 61.73 | D - Other node or line within 3 km | 1.24 | 0.62 | Line: Existing MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 745
1 | 746 | 746 | 1381100066 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 66 | 14.4597 | 120.9851 | U | 2809 | 3.75 | 749 | 225 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.78 | 53.78 | 69.68 | 61.73 | B - Node 0.5-1 km | 0.57 | 0.57 | Node: LPS012 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 746
1 | 747 | 747 | 1908707003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bugasan Norte | 17.254 | 122.228 | R | 10312 | 4.3 | 2398 | 719 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 53.42 | 53.42 | 70.05 | 61.73 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 747
1 | 748 | 748 | 1705309005 | MIMAROPA Region | Palawan | Coron | Bulalacao | 11.6636 | 120.1087 | U | 4239 | 3.9 | 1087 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.77 | 114.19 | Tier 1B: High GIDA Priority | 44.07 | 44.07 | 79.36 | 61.72 | F - Nearest node and line over 5 km | 40.77 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 748
1 | 749 | 749 | 0402123023 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Ramon Cruz | 14.3265 | 121.032 | U | 8083 | 3.4 | 2377 | 713 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.03 | 2.21 | Tier 1B: High GIDA Priority | 61.44 | 61.44 | 61.99 | 61.71 | D - Other node or line within 3 km | 2.03 | 1.96 | Line: AE SPL002 TO SPL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 749
1 | 750 | 750 | 1381200030 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Lucia | 14.5869 | 121.0983 | U | 45116 | 3.52 | 12822 | 3847 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.61 | 0.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.8 | 56.8 | 66.61 | 61.71 | C - Line within 0.5 km; node over 1 km | 1.61 | 0.23 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 750
1 | 751 | 751 | 0403411012 | Region IV-A (CALABARZON) | Laguna | Los Baños | San Antonio | 14.1768 | 121.2451 | U | 17515 | 3.3 | 5308 | 1592 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.4 | 0.12 | Tier 2A: High Commercial ROI | 72.55 | 72.55 | 50.85 | 61.7 | A - Node within 0.5 km | 0.4 | 0.12 | Line: AE SPO001 TO LBL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 751
1 | 752 | 752 | 1381200022 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Miguel | 14.5669 | 121.0847 | U | 44629 | 3.41 | 13070 | 3921 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.34 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 58.91 | 58.91 | 64.5 | 61.7 | A - Node within 0.5 km | 0.34 | 0.11 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 752
1 | 753 | 753 | 1108211013 | Region XI (Davao Region) | Davao de Oro | Pantukan | Araibo | 7.2497 | 126.1565 | R | 2585 | 3.7 | 699 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.17 | 29.4 | Tier 1B: High GIDA Priority | 44.74 | 44.74 | 78.65 | 61.7 | F - Nearest node and line over 5 km | 31.17 | 29.36 | Line: PANTUKAN - MATI SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 753
1 | 754 | 754 | 0702232016 | Region VII (Central Visayas) | Cebu | Minglanilla | Tunghaan | 10.246 | 123.7786 | U | 16912 | 3.8 | 4451 | 1335 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.07 | 0.75 | Tier 2A: High Commercial ROI | 74.46 | 74.46 | 48.93 | 61.69 | D - Other node or line within 3 km | 1.74 | 0.73 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 754
1 | 755 | 755 | 1381300097 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Bartolome | 14.7102 | 121.0319 | U | 51472 | 4.02 | 12814 | 3844 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.67 | 0.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.71 | 56.71 | 66.68 | 61.69 | D - Other node or line within 3 km | 1.67 | 0.79 | Line: UG 144C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 755
1 | 756 | 756 | 0501711037 | Region V (Bicol Region) | Camarines Sur | Caramoan | Pili-Centro | 13.7646 | 123.8513 | R | 951 | 4.2 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 37.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.46 | 49.46 | 73.93 | 61.69 | D - Other node or line within 3 km | 1.7 | 37.31 | Node: COC001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 756
1 | 757 | 757 | 1381600018 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Mapulang Lupa | 14.7019 | 121.0007 | U | 30775 | 3.46 | 8882 | 2665 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.73 | 0.07 | Tier 1B: High GIDA Priority | 63.32 | 63.32 | 60.05 | 61.68 | B - Node 0.5-1 km | 0.73 | 0.05 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 757
1 | 758 | 758 | 1380800002 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Bayanan | 14.407 | 121.0453 | U | 38358 | 3.62 | 10600 | 3180 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.13 | 0.35 | Tier 1B: High GIDA Priority | 60.41 | 60.41 | 62.94 | 61.68 | C - Line within 0.5 km; node over 1 km | 1.13 | 0.23 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 758
1 | 759 | 759 | 1906603018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Kalingalan Caluang | Masjid Punjungan | 17.2555 | 122.2296 | R | 3769 | 4.3 | 877 | 263 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 52.03 | 52.03 | 71.34 | 61.68 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 759
1 | 760 | 760 | 1381300065 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santo Domingo | 14.6211 | 121.0575 | U | 11702 | 3.63 | 3222 | 967 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 66.35 | 66.35 | 57 | 61.67 | A - Node within 0.5 km | 0.12 | 0.18 | Node: QCY009 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 760
1 | 761 | 761 | 0403426022 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Sur | 14.2843 | 121.418 | R | 3508 | 3.3 | 1063 | 319 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.48 | Tier 2A: High Commercial ROI | 70.56 | 70.56 | 52.75 | 61.66 | B - Node 0.5-1 km | 0.79 | 0.48 | Line: UG SCL001 TO LWL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 761
1 | 762 | 762 | 0205015001 | Region II (Cagayan Valley) | Nueva Vizcaya | Alfonso Castaneda | Abuyo | 15.8483 | 121.2299 | R | 1613 | 3.8 | 424 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.27 | 6.22 | Tier 1B: High GIDA Priority | 44.16 | 44.16 | 79.16 | 61.66 | F - Nearest node and line over 5 km | 10.27 | 6.22 | Line: BALER - PANTABANGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 762
1 | 763 | 763 | 1403209014 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Limos | 17.5011 | 121.2912 | R | 936 | 4.3 | 218 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.15 | 9.88 | Tier 1B: High GIDA Priority | 41.4 | 41.4 | 81.92 | 61.66 | F - Nearest node and line over 5 km | 8.15 | 9.87 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 763
1 | 764 | 764 | 1108202011 | Region XI (Davao Region) | Davao de Oro | Laak | Langtud | 7.8465 | 125.8612 | R | 3066 | 3.7 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.58 | 18.84 | Tier 1B: High GIDA Priority | 49.22 | 49.22 | 74.08 | 61.65 | F - Nearest node and line over 5 km | 21.58 | 18.84 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 764
1 | 765 | 765 | 1402706020 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Maga | 16.9759 | 121.1722 | R | 425 | 3.9 | 109 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.28 | 12.66 | Tier 1B: High GIDA Priority | 45.42 | 45.42 | 77.87 | 61.65 | F - Nearest node and line over 5 km | 5.28 | 16.21 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 765
1 | 766 | 766 | 1403214003 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Dacalan | 17.2276 | 121.2258 | R | 348 | 4.3 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.11 | 8.92 | Tier 1B: High GIDA Priority | 42.59 | 42.59 | 80.72 | 61.65 | F - Nearest node and line over 5 km | 9.11 | 8.9 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 766
1 | 767 | 767 | 1381600004 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Parada | 14.6981 | 120.9877 | U | 21602 | 3.28 | 6580 | 1974 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.86 | 0.58 | Tier 1B: High GIDA Priority | 65.94 | 65.94 | 57.34 | 61.64 | B - Node 0.5-1 km | 0.86 | 0.58 | Line: UG 288C via Brown Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 767
1 | 768 | 768 | 0300809014 | Region III (Central Luzon) | Bataan | Orani | Pantalan Luma | 14.8014 | 120.5426 | U | 5862 | 3.6 | 1628 | 488 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.66 | Tier 1B: High GIDA Priority | 65.21 | 65.21 | 58.05 | 61.63 | B - Node 0.5-1 km | 0.68 | 0.63 | Line: 36 CORE 3X12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 768
1 | 769 | 769 | 0402111022 | Region IV-A (CALABARZON) | Cavite | Kawit | Tramo-Bantayan | 14.4461 | 120.9162 | U | 3563 | 3.4 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.48 | 0.11 | Tier 1B: High GIDA Priority | 58.99 | 58.99 | 64.27 | 61.63 | C - Line within 0.5 km; node over 1 km | 3.48 | 0.1 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 769
1 | 770 | 770 | 1003523029 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Tawanan | 8.0714 | 124.2534 | R | 959 | 4.2 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.21 | 0.24 | Tier 1B: High GIDA Priority | 51.7 | 51.7 | 71.55 | 61.63 | C - Line within 0.5 km; node over 1 km | 7.21 | 0.16 | Line: Pantar Done Layed | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 770
1 | 771 | 771 | 0600406010 | Region VI (Western Visayas) | Aklan | Ibajay | Bugtongbato | 11.7733 | 122.216 | R | 1761 | 3.9 | 452 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.56 | 0.73 | Tier 1B: High GIDA Priority | 49.84 | 49.84 | 73.43 | 61.63 | F - Nearest node and line over 5 km | 10.56 | 16.77 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 771
1 | 772 | 772 | 0806418026 | Region VIII (Eastern Visayas) | Southern Leyte | Tomas Oppus | San Roque | 10.2986 | 124.9673 | R | 347 | 4.1 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.86 | 1.55 | Tier 1B: High GIDA Priority | 48.35 | 48.35 | 74.91 | 61.63 | F - Nearest node and line over 5 km | 23.83 | 19.11 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 772
1 | 773 | 773 | 1402706025 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Nalbu | 16.9261 | 121.2392 | R | 284 | 3.9 | 73 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.48 | 18.45 | Tier 1B: High GIDA Priority | 45.31 | 45.31 | 77.93 | 61.62 | F - Nearest node and line over 5 km | 5.48 | 18.29 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 773
1 | 774 | 774 | 1380500004 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Ibaba | 14.581 | 121.028 | U | 9473 | 3.39 | 2792 | 838 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.29 | Tier 1B: High GIDA Priority | 64.72 | 64.72 | 58.47 | 61.59 | A - Node within 0.5 km | 0.29 | 0.1 | Line: Aerial 216C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 774
1 | 775 | 775 | 1908702010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Minabay | 17.2539 | 122.2279 | R | 5213 | 4.3 | 1212 | 364 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 49.93 | 49.93 | 73.25 | 61.59 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 775
1 | 776 | 776 | 1380900015 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Dagat-dagatan | 14.6721 | 120.9516 | U | 33389 | 3.52 | 9499 | 2850 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.71 | 0.14 | Tier 1B: High GIDA Priority | 62.58 | 62.58 | 60.57 | 61.58 | B - Node 0.5-1 km | 0.71 | 0.14 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 776
1 | 777 | 777 | 1381100172 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 172 | 14.4165 | 121.1872 | U | 5502 | 3.47 | 1586 | 476 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.77 | 5.65 | Tier 1B: High GIDA Priority | 52.29 | 52.29 | 70.87 | 61.58 | E - Nearest node or line 3-5 km | 3.77 | 5.61 | Node: BIR003 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 777
1 | 778 | 778 | 1102501014 | Region XI (Davao Region) | Davao Oriental | Baganga | Salingcomot | 7.6334 | 126.5365 | R | 3085 | 3.6 | 857 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.15 | 56.76 | Tier 1B: High GIDA Priority | 48 | 48 | 75.16 | 61.58 | F - Nearest node and line over 5 km | 57.15 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 778
1 | 779 | 779 | 1381300137 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sangandaan | 14.6743 | 121.0217 | U | 22847 | 3.84 | 5951 | 1785 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.15 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 66.17 | 66.17 | 56.97 | 61.57 | D - Other node or line within 3 km | 1.15 | 0.63 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 779
1 | 780 | 780 | 1381000009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Marcelo Green Village | 14.4587 | 121.0425 | U | 34237 | 3.71 | 9236 | 2771 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.71 | 0.43 | Tier 1B: High GIDA Priority | 62.91 | 62.91 | 60.23 | 61.57 | B - Node 0.5-1 km | 0.71 | 0.42 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 780
1 | 781 | 781 | 1705313009 | MIMAROPA Region | Palawan | Linapacan | Pical | 11.2663 | 119.6739 | R | 1776 | 3.9 | 455 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.51 | 52.55 | Tier 1B: High GIDA Priority | 47.6 | 47.6 | 75.53 | 61.57 | F - Nearest node and line over 5 km | 13.51 | 999999 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 781
1 | 782 | 782 | 1908704004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Matuber | 17.2541 | 122.2282 | R | 7440 | 4.3 | 1730 | 519 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 51.45 | 51.45 | 71.66 | 61.56 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 782
1 | 783 | 783 | 0600410016 | Region VI (Western Visayas) | Aklan | Madalag | Napnot | 11.5182 | 122.3192 | R | 535 | 3.9 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.51 | 7.12 | Tier 1B: High GIDA Priority | 47.64 | 47.64 | 75.49 | 61.56 | F - Nearest node and line over 5 km | 7.51 | 7.09 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 783
1 | 784 | 784 | 1380500025 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | San Jose | 14.58 | 121.0292 | U | 7888 | 3.31 | 2385 | 716 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.32 | Tier 1B: High GIDA Priority | 63.23 | 63.23 | 59.85 | 61.54 | A - Node within 0.5 km | 0.42 | 0.06 | Line: Aerial 216C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 784
1 | 785 | 785 | 0201528020 | Region II (Cagayan Valley) | Cagayan | Tuao | Mambacag | 17.6739 | 121.5351 | R | 1447 | 3.9 | 371 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.47 | 10.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.49 | 49.49 | 73.56 | 61.52 | D - Other node or line within 3 km | 2.47 | 10.31 | Node: TUC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 785
1 | 786 | 786 | 0205704021 | Region II (Cagayan Valley) | Quirino | Maddela | San Dionisio I | 16.4081 | 121.8013 | R | 561 | 3.9 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.81 | 13.93 | Tier 1B: High GIDA Priority | 34.5 | 34.5 | 88.54 | 61.52 | F - Nearest node and line over 5 km | 12.81 | 13.92 | Node: GTI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 786
1 | 787 | 787 | 0405804024 | Region IV-A (CALABARZON) | Rizal | Binangonan | Macamot | 14.4864 | 121.1971 | U | 9861 | 3.6 | 2739 | 822 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.28 | 1.13 | Tier 2B: Moderate GIDA Inclusion | 67.3 | 67.3 | 55.73 | 61.51 | D - Other node or line within 3 km | 1.28 | 1.11 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 787
1 | 788 | 788 | 0702232011 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward II | 10.2633 | 123.7824 | U | 3639 | 3.8 | 958 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.58 | 2.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.03 | 57.03 | 65.99 | 61.51 | D - Other node or line within 3 km | 2.58 | 2.33 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 788
1 | 789 | 789 | 0301407018 | Region III (Central Luzon) | Bulacan | Calumpit | Palimbang | 14.9007 | 120.7539 | R | 1760 | 3.5 | 503 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 1.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.88 | 57.88 | 65.1 | 61.49 | D - Other node or line within 3 km | 1.62 | 1.58 | Line: CALUMPIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 789
1 | 790 | 790 | 0403428006 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Don Jose | 14.2549 | 121.0644 | U | 19774 | 3.3 | 5992 | 1798 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.28 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 69.94 | 69.94 | 53.03 | 61.48 | D - Other node or line within 3 km | 1.28 | 0.58 | Line: TGY001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 790
1 | 791 | 791 | 1381300008 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagong Lipunan Ng Crame | 14.6059 | 121.052 | U | 14944 | 3.7 | 4035 | 1210 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.69 | 0.2 | Tier 1B: High GIDA Priority | 65.72 | 65.72 | 57.24 | 61.48 | D - Other node or line within 3 km | 1.69 | 0.66 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 791
1 | 792 | 792 | 1381300009 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagong Pag-asa | 14.6631 | 121.0338 | U | 28022 | 3.51 | 7975 | 2392 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.21 | 0.38 | Tier 1B: High GIDA Priority | 65.54 | 65.54 | 57.43 | 61.48 | A - Node within 0.5 km | 0.21 | 0.37 | Node: QCY088 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 792
1 | 793 | 793 | 1403209011 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Dugpa | 17.5156 | 121.3789 | R | 1263 | 4.3 | 294 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.14 | 6.47 | Tier 1B: High GIDA Priority | 44.66 | 44.66 | 78.3 | 61.48 | F - Nearest node and line over 5 km | 6.14 | 6.45 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 793
1 | 794 | 794 | 0402103027 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row East | 14.2542 | 120.8895 | U | 19338 | 3.4 | 5688 | 1706 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.84 | 2.93 | Tier 1B: High GIDA Priority | 63.37 | 63.37 | 59.56 | 61.47 | D - Other node or line within 3 km | 3.84 | 2.93 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 794
1 | 795 | 795 | 0403410021 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Taykin | 14.141 | 121.4448 | R | 3268 | 3.3 | 990 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.7 | Tier 2A: High Commercial ROI | 74.31 | 74.31 | 48.6 | 61.46 | D - Other node or line within 3 km | 1.06 | 0.7 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 795
1 | 796 | 796 | 0102908002 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Comillas North | 16.9702 | 120.7482 | R | 2377 | 3.8 | 626 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.98 | 0.11 | Tier 1B: High GIDA Priority | 63.76 | 63.76 | 59.16 | 61.46 | C - Line within 0.5 km; node over 1 km | 2.98 | 0.03 | Line: PROPOSED 96C FOC - BUGIAS TO CERVANTES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 796
1 | 797 | 797 | 0405811002 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 1 | 14.7002 | 121.1226 | U | 5006 | 3.6 | 1391 | 417 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.25 | Tier 1B: High GIDA Priority | 62.53 | 62.53 | 60.4 | 61.46 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.25 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 797
1 | 798 | 798 | 1380300026 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Santa Cruz | 14.5679 | 121.0172 | U | 6744 | 3.63 | 1857 | 557 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 0.34 | Tier 1B: High GIDA Priority | 60.38 | 60.38 | 62.55 | 61.46 | C - Line within 0.5 km; node over 1 km | 1.07 | 0.34 | Line: UG 288C via V-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 798
1 | 799 | 799 | 1381701006 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | San Roque | 14.5421 | 121.0707 | U | 4897 | 3.83 | 1277 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.38 | Tier 1B: High GIDA Priority | 60.04 | 60.04 | 62.88 | 61.46 | A - Node within 0.5 km | 0.38 | 0.37 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 799
1 | 800 | 800 | 0300803011 | Region III (Central Luzon) | Bataan | City of Balanga | Ibayo | 14.6759 | 120.5187 | U | 2379 | 3.6 | 661 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.47 | 0.58 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.31 | 53.31 | 69.61 | 61.46 | D - Other node or line within 3 km | 2.47 | 0.58 | Line: Bagac-Pilar AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 800
1 | 801 | 801 | 0205703010 | Region II (Cagayan Valley) | Quirino | Diffun | Don Mariano Perez, Sr. | 16.4814 | 121.3772 | R | 712 | 3.9 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.48 | 15.32 | Tier 1B: High GIDA Priority | 40.9 | 40.9 | 82.02 | 61.46 | F - Nearest node and line over 5 km | 7.48 | 15.16 | Node: QZV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 801
1 | 802 | 802 | 0102817028 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Santa Matilde | 18.3257 | 120.6833 | R | 427 | 3.7 | 115 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.99 | 6.87 | Tier 1B: High GIDA Priority | 39.57 | 39.57 | 83.35 | 61.46 | F - Nearest node and line over 5 km | 6.99 | 6.86 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 802
1 | 803 | 803 | 0403403024 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Timbao | 14.2823 | 121.0542 | U | 16951 | 3.3 | 5137 | 1541 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.52 | 3 | Tier 2B: Moderate GIDA Inclusion | 67.14 | 67.14 | 55.77 | 61.45 | D - Other node or line within 3 km | 1.52 | 3 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 803
1 | 804 | 804 | 1908701014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Togaig | 17.2541 | 122.2281 | R | 7196 | 4.3 | 1673 | 502 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 51.28 | 51.28 | 71.58 | 61.43 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 804
1 | 805 | 805 | 1381100185 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 185 | 14.6561 | 121.2098 | U | 4738 | 3.53 | 1341 | 402 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.11 | 5.06 | Tier 1B: High GIDA Priority | 51.24 | 51.24 | 71.62 | 61.43 | E - Nearest node or line 3-5 km | 4.11 | 4.98 | Node: ANR009 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 805
1 | 806 | 806 | 1403214015 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Dupligan | 17.3317 | 121.3608 | R | 1904 | 4.3 | 443 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.51 | 8.11 | Tier 1B: High GIDA Priority | 47.59 | 47.59 | 75.24 | 61.42 | F - Nearest node and line over 5 km | 12.51 | 8.11 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 806
1 | 807 | 807 | 1004321003 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Barra | 8.514 | 124.6076 | U | 15306 | 3.9 | 3925 | 1178 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.36 | 0.27 | Tier 2A: High Commercial ROI | 71.93 | 71.93 | 50.9 | 61.41 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.15 | Line: Implem. 96f aerial FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 807
1 | 808 | 808 | 0403403026 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Zapote | 14.3175 | 121.0812 | U | 16096 | 3.3 | 4878 | 1463 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2 | 1.04 | Tier 2A: High Commercial ROI | 70.2 | 70.2 | 52.61 | 61.41 | D - Other node or line within 3 km | 2 | 1 | Line: AE CRC005-BNL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 808
1 | 809 | 809 | 0402117020 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa II | 14.4232 | 120.8778 | U | 6185 | 3.4 | 1819 | 546 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.81 | Tier 1B: High GIDA Priority | 65.16 | 65.16 | 57.66 | 61.41 | B - Node 0.5-1 km | 0.9 | 0.78 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 809
1 | 810 | 810 | 1380601128 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 128 | 11.5489 | 121.0633 | U | 22298 | 3.72 | 5989 | 1797 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 85.03 | 83.31 | Tier 1B: High GIDA Priority | 49.49 | 49.49 | 73.31 | 61.4 | F - Nearest node and line over 5 km | 85.03 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 810
1 | 811 | 811 | 1404401010 | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | Ogo-og | 17.0436 | 121.192 | R | 461 | 3.7 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.52 | 16.3 | Tier 1B: High GIDA Priority | 43.27 | 43.27 | 79.51 | 61.39 | F - Nearest node and line over 5 km | 8.52 | 17.52 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 811
1 | 812 | 812 | 1380500022 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Plainview | 14.5782 | 121.0297 | U | 33472 | 3.09 | 10849 | 3255 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.63 | 0.26 | Tier 1B: High GIDA Priority | 61.08 | 61.08 | 61.68 | 61.38 | B - Node 0.5-1 km | 0.63 | 0.25 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 812
1 | 813 | 813 | 0102934018 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Capangpangan | 17.5719 | 120.3947 | R | 1764 | 3.8 | 464 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.52 | 55.52 | 67.23 | 61.38 | D - Other node or line within 3 km | 2.46 | 0.92 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 813
1 | 814 | 814 | 1380500007 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Burol | 14.5716 | 121.0329 | U | 2543 | 3.81 | 667 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.24 | 51.24 | 71.52 | 61.38 | B - Node 0.5-1 km | 0.74 | 0.21 | Line: UG 144C via W-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 814
1 | 815 | 815 | 1108602033 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Sugal | 5.8835 | 125.6235 | R | 3173 | 3.6 | 881 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.46 | 54.24 | Tier 1B: High GIDA Priority | 48.64 | 48.64 | 74.09 | 61.37 | F - Nearest node and line over 5 km | 45.46 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 815
1 | 816 | 816 | 0701230015 | Region VII (Central Visayas) | Bohol | Loon | Cabadug | 9.8198 | 123.827 | R | 320 | 4 | 80 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.57 | 2.55 | Tier 1B: High GIDA Priority | 45.4 | 45.4 | 77.35 | 61.37 | D - Other node or line within 3 km | 3.57 | 2.55 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 816
1 | 817 | 817 | 1908708011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Tumaguinting | 17.2595 | 122.2464 | R | 7177 | 4.3 | 1669 | 501 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.19 | 36.23 | Tier 1B: High GIDA Priority | 51.12 | 51.12 | 71.6 | 61.36 | F - Nearest node and line over 5 km | 31.19 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 817
1 | 818 | 818 | 1403201001 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Ababa-an | 17.5143 | 121.2842 | R | 420 | 4.3 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.65 | 11.26 | Tier 1B: High GIDA Priority | 39.87 | 39.87 | 82.84 | 61.36 | F - Nearest node and line over 5 km | 7.65 | 11.26 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 818
1 | 819 | 819 | 1907003014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Mapun | Liyubud | 17.2558 | 122.2298 | R | 3686 | 5.8 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.55 | 34.42 | Tier 1B: High GIDA Priority | 45.75 | 45.75 | 76.94 | 61.34 | F - Nearest node and line over 5 km | 29.55 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 819
1 | 820 | 820 | 0806417010 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Hipantag | 10.4859 | 124.98 | R | 251 | 4.1 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.1 | 1.92 | Tier 1B: High GIDA Priority | 42.68 | 42.68 | 80.01 | 61.34 | F - Nearest node and line over 5 km | 29.03 | 23.97 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 820
1 | 821 | 821 | 0301410019 | Region III (Central Luzon) | Bulacan | City of Malolos | Canalate | 14.8417 | 120.8024 | R | 3796 | 3.5 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 1.8 | Tier 2A: High Commercial ROI | 70.3 | 70.3 | 52.34 | 61.32 | D - Other node or line within 3 km | 1.07 | 1.89 | Node: MSB003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 821
1 | 822 | 822 | 1381300023 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | New Era | 14.6674 | 121.0579 | U | 14987 | 4.29 | 3490 | 1047 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.01 | 0.03 | Tier 1B: High GIDA Priority | 65.31 | 65.31 | 57.33 | 61.32 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.05 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 822
1 | 823 | 823 | 0600402006 | Region VI (Western Visayas) | Aklan | Balete | Feliciano | 11.5835 | 122.3572 | U | 2950 | 3.9 | 756 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 0.17 | Tier 1B: High GIDA Priority | 60.33 | 60.33 | 62.32 | 61.32 | C - Line within 0.5 km; node over 1 km | 2.74 | 0.16 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 823
1 | 824 | 824 | 0306916075 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Vicente | 15.4773 | 120.5865 | U | 18884 | 3.9 | 4842 | 1453 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.75 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 69.53 | 69.53 | 53.07 | 61.3 | C - Line within 0.5 km; node over 1 km | 2.75 | 0.04 | Line: 48 CORE (8X6) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 824
1 | 825 | 825 | 0702234029 | Region VII (Central Visayas) | Cebu | City of Naga | West Poblacion | 10.21 | 123.7555 | R | 4169 | 3.8 | 1097 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.07 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 70.46 | 70.46 | 52.12 | 61.29 | C - Line within 0.5 km; node over 1 km | 3.21 | 0.36 | Line: CEBU - TOLEDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 825
1 | 826 | 826 | 1381600005 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Bignay | 14.7457 | 121.0021 | U | 53837 | 3.69 | 14608 | 4382 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.01 | 0.02 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.63 | 55.63 | 66.95 | 61.29 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.01 | Line: Aerial 96C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 826
1 | 827 | 827 | 1102406007 | Region XI (Davao Region) | Davao del Sur | Kiblawan | Bonifacio | 6.4627 | 125.2603 | R | 1495 | 3.4 | 440 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.54 | 0.66 | Tier 1B: High GIDA Priority | 52.57 | 52.57 | 69.98 | 61.28 | F - Nearest node and line over 5 km | 6.54 | 5.45 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 827
1 | 828 | 828 | 0402103045 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino II | 14.2351 | 120.9304 | U | 44630 | 3.4 | 13126 | 3938 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 6.92 | 4.8 | Tier 1B: High GIDA Priority | 51.87 | 51.87 | 70.67 | 61.27 | E - Nearest node or line 3-5 km | 6.92 | 4.8 | Line: NCC001 TO TGY001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 828
1 | 829 | 829 | 0300805024 | Region III (Central Luzon) | Bataan | Hermosa | Judge Roman Cruz Sr. | 14.8341 | 120.4884 | R | 4747 | 3.6 | 1319 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.06 | 0.01 | Tier 2A: High Commercial ROI | 73.11 | 73.11 | 49.41 | 61.26 | A - Node within 0.5 km | 0.06 | 0 | Line: Pipe Dinalupian to Orion | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 829
1 | 830 | 830 | 1004324002 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Casinglot | 8.5184 | 124.7525 | U | 10539 | 3.9 | 2702 | 811 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 67.25 | 67.25 | 55.28 | 61.26 | D - Other node or line within 3 km | 2.18 | 0.68 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 830
1 | 831 | 831 | 0402111002 | Region IV-A (CALABARZON) | Cavite | Kawit | Gahak | 14.4437 | 120.9103 | R | 3089 | 3.4 | 909 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 66.23 | 66.23 | 56.29 | 61.26 | C - Line within 0.5 km; node over 1 km | 3.33 | 0.29 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 831
1 | 832 | 832 | 1381300117 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Tagumpay | 14.6669 | 121.1233 | U | 3267 | 3.75 | 871 | 261 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.88 | 54.88 | 67.64 | 61.26 | C - Line within 0.5 km; node over 1 km | 1.68 | 0.21 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 832
1 | 833 | 833 | 0600410007 | Region VI (Western Visayas) | Aklan | Madalag | Catabana | 11.5391 | 122.302 | R | 465 | 3.9 | 119 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.08 | 7.35 | Tier 1B: High GIDA Priority | 46.89 | 46.89 | 75.63 | 61.26 | F - Nearest node and line over 5 km | 8.08 | 7.34 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 833
1 | 834 | 834 | 0401005085 | Region IV-A (CALABARZON) | Batangas | Batangas City | San Agustin Silangan, Isla Verde | 13.5614 | 121.0598 | R | 741 | 3.6 | 206 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.97 | 13.2 | Tier 1B: High GIDA Priority | 40.7 | 40.7 | 81.81 | 61.26 | F - Nearest node and line over 5 km | 7.97 | 13.2 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 834
1 | 835 | 835 | 0403403022 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Soro-soro | 14.3255 | 121.0612 | U | 7880 | 3.3 | 2388 | 716 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.07 | Tier 2B: Moderate GIDA Inclusion | 65.74 | 65.74 | 56.76 | 61.25 | D - Other node or line within 3 km | 1.55 | 1.05 | Line: AE CRC005-BNL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 835
1 | 836 | 836 | 0405801001 | Region IV-A (CALABARZON) | Rizal | Angono | Bagumbayan | 14.5322 | 121.1644 | R | 2660 | 3.6 | 739 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 1.16 | Tier 1B: High GIDA Priority | 65.01 | 65.01 | 57.49 | 61.25 | D - Other node or line within 3 km | 1.17 | 1.15 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 836
1 | 837 | 837 | 0803722005 | Region VIII (Eastern Visayas) | Leyte | Isabel | Benog | 10.8852 | 124.4724 | R | 627 | 3.8 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.81 | 0.59 | Tier 1B: High GIDA Priority | 47.44 | 47.44 | 75.06 | 61.25 | C - Line within 0.5 km; node over 1 km | 5.81 | 0.48 | Line: ORMOC - PALOMPON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 837
1 | 838 | 838 | 0102916012 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Kinmarin | 17.0386 | 120.5412 | R | 377 | 3.8 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.15 | 9.31 | Tier 1B: High GIDA Priority | 44.03 | 44.03 | 78.47 | 61.25 | F - Nearest node and line over 5 km | 7.15 | 9.3 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 838
1 | 839 | 839 | 0403404003 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banlic | 14.2357 | 121.302 | U | 22631 | 3.3 | 6858 | 2057 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 5.9 | 5.9 | Tier 1B: High GIDA Priority | 60.39 | 60.39 | 62.09 | 61.24 | F - Nearest node and line over 5 km | 5.9 | 5.89 | Line: CLB001 TO SCL001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 839
1 | 840 | 840 | 0403428004 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dila | 14.2895 | 121.1091 | U | 43294 | 3.3 | 13119 | 3936 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.85 | 0.22 | Tier 1B: High GIDA Priority | 61.47 | 61.47 | 60.98 | 61.23 | B - Node 0.5-1 km | 0.85 | 0.07 | Line: BINAN - CABUYAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 840
1 | 841 | 841 | 0600406008 | Region VI (Western Visayas) | Aklan | Ibajay | Batuan | 11.7988 | 122.1371 | R | 1266 | 3.9 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.35 | 1.21 | Tier 1B: High GIDA Priority | 42.01 | 42.01 | 80.44 | 61.22 | F - Nearest node and line over 5 km | 19.35 | 25.81 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 841
1 | 842 | 842 | 0301404005 | Region III (Central Luzon) | Bulacan | Bocaue | Biñang 1st | 14.7939 | 120.9308 | R | 3560 | 3.5 | 1017 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 69.02 | 69.02 | 53.37 | 61.19 | C - Line within 0.5 km; node over 1 km | 1.69 | 0.06 | Line: BOCAUE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 842
1 | 843 | 843 | 1381300116 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | South Triangle | 14.7111 | 120.9873 | U | 15070 | 2.9 | 5198 | 1559 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.43 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 66.62 | 66.62 | 55.76 | 61.19 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.34 | Line: Existing MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 843
1 | 844 | 844 | 0304918009 | Region III (Central Luzon) | Nueva Ecija | Nampicuan | Edy | 15.7211 | 120.655 | R | 140 | 3.5 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.57 | 8.23 | Tier 1B: High GIDA Priority | 44.19 | 44.19 | 78.18 | 61.19 | F - Nearest node and line over 5 km | 6.57 | 8.24 | Node: CYN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 844
1 | 845 | 845 | 0301412025 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Zamora | 14.7352 | 120.9543 | U | 2477 | 3.5 | 708 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 0.76 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 55.94 | 55.94 | 66.41 | 61.18 | D - Other node or line within 3 km | 1.57 | 0.74 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 845
1 | 846 | 846 | 0401005071 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 24 | 13.7015 | 121.0638 | R | 1453 | 3.6 | 404 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 6.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.48 | 51.48 | 70.88 | 61.18 | D - Other node or line within 3 km | 1.66 | 6.1 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 846
1 | 847 | 847 | 0403405032 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mayapa | 14.2113 | 121.1273 | U | 31024 | 3.3 | 9401 | 2820 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.5 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 67.01 | 67.01 | 55.33 | 61.17 | B - Node 0.5-1 km | 0.5 | 0.08 | Line: AE CLB001 TO CLB002 | Survey short node lateral; confirm port/fiber capacity, access and route. | 847
1 | 848 | 848 | 0305412021 | Region III (Central Luzon) | Pampanga | Masantol | Sta. Cruz | 14.8752 | 120.6977 | R | 2602 | 4 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 2.83 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 57.65 | 57.65 | 64.7 | 61.17 | D - Other node or line within 3 km | 2.05 | 8.26 | Node: MSP001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 848
1 | 849 | 849 | 0405627030 | Region IV-A (CALABARZON) | Quezon | Mauban | San Jose | 14.1067 | 121.7921 | R | 596 | 3.8 | 157 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.18 | 10.53 | Tier 1B: High GIDA Priority | 35.93 | 35.93 | 86.42 | 61.17 | F - Nearest node and line over 5 km | 11.18 | 10.46 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 849
1 | 850 | 850 | 0401026025 | Region IV-A (CALABARZON) | Batangas | San Pascual | San Antonio | 13.7871 | 121.0186 | U | 10340 | 3.6 | 2872 | 862 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 67.08 | 67.08 | 55.25 | 61.16 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.18 | Line: UG BUN001 TO BCY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 850
1 | 851 | 851 | 1381300114 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Silangan | 14.5918 | 121.0554 | U | 5011 | 3.6 | 1393 | 418 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.41 | Tier 1B: High GIDA Priority | 58.87 | 58.87 | 63.45 | 61.16 | C - Line within 0.5 km; node over 1 km | 1.14 | 0.4 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 851
1 | 852 | 852 | 1381100052 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 52 | 14.5067 | 121.0649 | U | 2461 | 4.08 | 603 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.65 | 50.65 | 71.66 | 61.16 | A - Node within 0.5 km | 0.23 | 0.12 | Line: Aerial 216C MTF | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 852
1 | 853 | 853 | 0401033016 | Region IV-A (CALABARZON) | Batangas | Tingloy | Talahib | 13.6568 | 120.9085 | R | 1103 | 3.6 | 306 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.9 | 16.72 | Tier 1B: High GIDA Priority | 50.48 | 50.48 | 71.85 | 61.16 | E - Nearest node or line 3-5 km | 3.9 | 16.71 | Node: MBN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 853
1 | 854 | 854 | 0403426021 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Norte | 14.2774 | 121.4124 | R | 3016 | 3.3 | 914 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.2 | 0.2 | Tier 2A: High Commercial ROI | 71.32 | 71.32 | 50.98 | 61.15 | A - Node within 0.5 km | 0.2 | 0.19 | Line: UG SCL001 TO PLL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 854
1 | 855 | 855 | 1381300045 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Immaculate Concepcion | 14.644 | 121.0215 | U | 8633 | 3.66 | 2361 | 708 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.32 | Tier 1B: High GIDA Priority | 62.59 | 62.59 | 59.7 | 61.15 | B - Node 0.5-1 km | 0.69 | 0.3 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 855
1 | 856 | 856 | 1381100135 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 135 | 14.7091 | 120.9808 | U | 2391 | 3.25 | 735 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.51 | 52.51 | 69.79 | 61.15 | B - Node 0.5-1 km | 0.98 | 0.36 | Line: Existing MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 856
1 | 857 | 857 | 0600410012 | Region VI (Western Visayas) | Aklan | Madalag | Mamba | 11.4942 | 122.2729 | R | 877 | 3.9 | 225 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.2 | 12.67 | Tier 1B: High GIDA Priority | 43.65 | 43.65 | 78.65 | 61.15 | F - Nearest node and line over 5 km | 13.2 | 12.66 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 857
1 | 858 | 858 | 0403425010 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Nueva | 14.3311 | 121.1831 | U | 4698 | 3.3 | 1424 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.16 | 9.12 | Tier 1B: High GIDA Priority | 54.38 | 54.38 | 67.91 | 61.14 | F - Nearest node and line over 5 km | 7.16 | 9.12 | Node: SRL004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 858
1 | 859 | 859 | 0405625010 | Region IV-A (CALABARZON) | Quezon | Macalelon | Malabahay | 13.7548 | 122.2445 | R | 720 | 3.8 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.6 | 7.44 | Tier 1B: High GIDA Priority | 45.24 | 45.24 | 77.05 | 61.14 | F - Nearest node and line over 5 km | 7.6 | 7.42 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 859
1 | 860 | 860 | 0301412020 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Poblacion | 14.7467 | 120.9608 | R | 318 | 3.5 | 91 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.75 | 49.75 | 72.51 | 61.13 | B - Node 0.5-1 km | 0.57 | 0.29 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 860
1 | 861 | 861 | 1908702013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Pantawan | 17.2541 | 122.2281 | R | 4001 | 4.3 | 930 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.19 | Tier 1B: High GIDA Priority | 48.94 | 48.94 | 73.31 | 61.13 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 861
1 | 862 | 862 | 1403214011 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Poblacion | 17.3 | 121.2333 | R | 295 | 4.3 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.83 | 7.39 | Tier 1B: High GIDA Priority | 41.81 | 41.81 | 80.45 | 61.13 | F - Nearest node and line over 5 km | 9.83 | 7.18 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 862
1 | 863 | 863 | 1404402015 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Monamon Sur | 16.8814 | 120.8838 | R | 3671 | 3.7 | 992 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 0.62 | Tier 2A: High Commercial ROI | 73.74 | 73.74 | 48.51 | 61.12 | C - Line within 0.5 km; node over 1 km | 1.84 | 0.35 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 863
1 | 864 | 864 | 0403410022 | Region IV-A (CALABARZON) | Laguna | Liliw | Kanlurang Bukal | 14.1286 | 121.4395 | R | 4848 | 3.3 | 1469 | 441 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.32 | Tier 2A: High Commercial ROI | 76.05 | 76.05 | 46.17 | 61.11 | B - Node 0.5-1 km | 0.92 | 0.32 | Line: SAN PABLO - LUCBAN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 864
1 | 865 | 865 | 1381300119 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Talipapa | 14.687 | 121.0254 | U | 39244 | 3.94 | 9959 | 2988 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.86 | 0.08 | Tier 1B: High GIDA Priority | 61.72 | 61.72 | 60.46 | 61.09 | B - Node 0.5-1 km | 0.86 | 0.07 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 865
1 | 866 | 866 | 0403405044 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 7 | 14.2023 | 121.1262 | R | 2584 | 3.3 | 783 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 66.4 | 66.4 | 55.77 | 61.08 | D - Other node or line within 3 km | 1.06 | 0.76 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 866
1 | 867 | 867 | 0600402011 | Region VI (Western Visayas) | Aklan | Balete | Poblacion | 11.5573 | 122.3783 | R | 899 | 3.9 | 231 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.25 | Tier 1B: High GIDA Priority | 60.15 | 60.15 | 62 | 61.08 | A - Node within 0.5 km | 0.31 | 0.25 | Line: IVISAN - KALIBO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 867
1 | 868 | 868 | 0201522009 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Kittag | 18.5066 | 121.2153 | R | 341 | 3.9 | 87 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.17 | 5.87 | Tier 1B: High GIDA Priority | 39.84 | 39.84 | 82.31 | 61.08 | F - Nearest node and line over 5 km | 6.17 | 5.86 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 868
1 | 869 | 869 | 1108603013 | Region XI (Davao Region) | Davao Occidental | Malita | Kinangan | 6.2912 | 125.5821 | R | 3123 | 3.6 | 868 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.35 | 33.79 | Tier 1B: High GIDA Priority | 48.56 | 48.56 | 73.57 | 61.07 | F - Nearest node and line over 5 km | 35.35 | 33.78 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 869
1 | 870 | 870 | 1403209023 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pinococ | 17.6505 | 121.4687 | R | 800 | 4.3 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.11 | 5.02 | Tier 1B: High GIDA Priority | 42.42 | 42.42 | 79.71 | 61.06 | F - Nearest node and line over 5 km | 5.11 | 5 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 870
1 | 871 | 871 | 0203104019 | Region II (Cagayan Valley) | Isabela | Benito Soliven | San Francisco | 16.939 | 121.9856 | R | 649 | 3.8 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.66 | 16.31 | Tier 1B: High GIDA Priority | 45.67 | 45.67 | 76.44 | 61.05 | F - Nearest node and line over 5 km | 5.66 | 16.31 | Node: BLI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 871
1 | 872 | 872 | 0402103050 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino VII | 14.2556 | 120.9622 | U | 13562 | 3.4 | 3989 | 1197 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.96 | 1.08 | Tier 2B: Moderate GIDA Inclusion | 66.76 | 66.76 | 55.33 | 61.04 | D - Other node or line within 3 km | 4.96 | 1 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 872
1 | 873 | 873 | 0200901001 | Region II (Cagayan Valley) | Batanes | Basco | Ihubok II | 20.4392 | 121.9735 | U | 2641 | 3 | 880 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 222.96 | 216.22 | Tier 1B: High GIDA Priority | 45.72 | 45.72 | 76.37 | 61.04 | F - Nearest node and line over 5 km | 219.32 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 873
1 | 874 | 874 | 1380614091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 898 | 13.0731 | 123.2807 | U | 7812 | 4.32 | 1810 | 543 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.06 | 31.53 | Tier 1B: High GIDA Priority | 51.89 | 51.89 | 70.17 | 61.03 | F - Nearest node and line over 5 km | 5.06 | 31.46 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 874
1 | 875 | 875 | 1400112006 | Cordillera Administrative Region (CAR) | Abra | Langiden | Malapaao | 17.6267 | 120.5525 | R | 821 | 3.8 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.89 | 6.98 | Tier 1B: High GIDA Priority | 46.23 | 46.23 | 75.82 | 61.03 | F - Nearest node and line over 5 km | 7.89 | 6.93 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 875
1 | 876 | 876 | 1705306012 | MIMAROPA Region | Palawan | Brooke'S Point | Malis | 8.7185 | 117.7017 | R | 4292 | 3.9 | 1101 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 160.45 | 162.75 | Tier 1B: High GIDA Priority | 51.44 | 51.44 | 70.56 | 61 | F - Nearest node and line over 5 km | 160.45 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 876
1 | 877 | 877 | 0401019005 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 11 | 14.095 | 120.6758 | U | 3410 | 3.6 | 947 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.25 | 1.2 | Tier 1B: High GIDA Priority | 57.2 | 57.2 | 64.78 | 60.99 | D - Other node or line within 3 km | 5.25 | 1.18 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 877
1 | 878 | 878 | 0102930024 | Region I (Ilocos Region) | Ilocos Sur | Sinait | Nagcullooban | 17.8608 | 120.4446 | R | 446 | 3.8 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 1.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.65 | 47.65 | 74.32 | 60.99 | D - Other node or line within 3 km | 1.71 | 1.02 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 878
1 | 879 | 879 | 0402106003 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol | 14.3298 | 120.949 | U | 12529 | 3.4 | 3685 | 1106 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.51 | 3.16 | Tier 2B: Moderate GIDA Inclusion | 64.77 | 64.77 | 57.18 | 60.98 | D - Other node or line within 3 km | 2.51 | 3.1 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 879
1 | 880 | 880 | 1908704008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Pura | 17.2541 | 122.2282 | R | 5430 | 4.3 | 1263 | 379 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 50.07 | 50.07 | 71.89 | 60.98 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 880
1 | 881 | 881 | 0301412018 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Pantoc | 14.766 | 120.9839 | U | 13146 | 3.5 | 3756 | 1127 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.55 | 1.43 | Tier 2A: High Commercial ROI | 71.95 | 71.95 | 49.99 | 60.97 | B - Node 0.5-1 km | 0.55 | 2.45 | Node: MEB001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 881
1 | 882 | 882 | 1908708010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Sabaken | 17.2612 | 122.2118 | R | 5719 | 4.3 | 1330 | 399 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.52 | 32.78 | Tier 1B: High GIDA Priority | 50.34 | 50.34 | 71.57 | 60.96 | F - Nearest node and line over 5 km | 28.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 882
1 | 883 | 883 | 0305415033 | Region III (Central Luzon) | Pampanga | Porac | Sinura | 15.1161 | 120.57 | R | 3859 | 4 | 965 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.2 | Tier 2A: High Commercial ROI | 71.47 | 71.47 | 50.44 | 60.95 | A - Node within 0.5 km | 0.31 | 0.2 | Line: 24 CORE (3X8) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 883
1 | 884 | 884 | 0102811022 | Region I (Ilocos Region) | Ilocos Norte | Banna | Binacag | 17.9227 | 120.636 | R | 967 | 3.7 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 2.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.99 | 50.99 | 70.92 | 60.95 | D - Other node or line within 3 km | 2.5 | 2.29 | Line: SEGMENT 5 BANNA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 884
1 | 885 | 885 | 0601909015 | Region VI (Western Visayas) | Capiz | Panay | Butacal | 11.5172 | 122.9147 | R | 1221 | 3.8 | 321 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.83 | 8.19 | Tier 1B: High GIDA Priority | 44.06 | 44.06 | 77.83 | 60.95 | F - Nearest node and line over 5 km | 9.83 | 8.19 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 885
1 | 886 | 886 | 1380700011 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Tañong | 14.6438 | 121.0949 | U | 9415 | 4.03 | 2337 | 701 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.06 | Tier 1B: High GIDA Priority | 62.4 | 62.4 | 59.45 | 60.93 | B - Node 0.5-1 km | 0.75 | 0.06 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 886
1 | 887 | 887 | 1381701010 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Tabacalera | 14.5547 | 121.0623 | U | 2853 | 3.71 | 768 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.83 | 52.83 | 69.03 | 60.93 | C - Line within 0.5 km; node over 1 km | 1.29 | 0.2 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 887
1 | 888 | 888 | 0806002022 | Region VIII (Eastern Visayas) | Samar | Basey | Mabini | 11.4211 | 125.142 | R | 2877 | 4.1 | 702 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.27 | 27.27 | Tier 1B: High GIDA Priority | 45.65 | 45.65 | 76.2 | 60.93 | F - Nearest node and line over 5 km | 25.27 | 27.33 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 888
1 | 889 | 889 | 1381300036 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | East Kamias | 14.6507 | 121.0647 | U | 6441 | 3.97 | 1621 | 486 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 1.03 | Tier 1B: High GIDA Priority | 59.05 | 59.05 | 62.78 | 60.92 | D - Other node or line within 3 km | 1.41 | 1.05 | Line: UG 288C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 889
1 | 890 | 890 | 1102301004 | Region XI (Davao Region) | Davao del Norte | Asuncion | Binancian | 7.7305 | 125.886 | R | 2366 | 3.7 | 639 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.62 | 11.66 | Tier 1B: High GIDA Priority | 44.6 | 44.6 | 77.25 | 60.92 | F - Nearest node and line over 5 km | 21.62 | 11.66 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 890
1 | 891 | 891 | 1381000003 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | La Huerta | 14.4909 | 120.9885 | U | 11850 | 3.9 | 3037 | 911 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.02 | Tier 1B: High GIDA Priority | 64.32 | 64.32 | 57.5 | 60.91 | B - Node 0.5-1 km | 0.82 | 0.02 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 891
1 | 892 | 892 | 1380400001 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Acacia | 14.6675 | 120.9689 | U | 4965 | 3.82 | 1300 | 390 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.23 | Tier 1B: High GIDA Priority | 60.43 | 60.43 | 61.36 | 60.9 | A - Node within 0.5 km | 0.23 | 0.18 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 892
1 | 893 | 893 | 1381100040 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 40 | 14.4862 | 120.9988 | U | 2291 | 3.22 | 711 | 213 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 0.11 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.81 | 50.81 | 70.97 | 60.89 | C - Line within 0.5 km; node over 1 km | 1.6 | 0.11 | Line: Existing 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 893
1 | 894 | 894 | 0402108015 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Manggahan | 14.2966 | 120.9118 | U | 20805 | 3.4 | 6119 | 1836 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.33 | 0.34 | Tier 2A: High Commercial ROI | 71.63 | 71.63 | 50.1 | 60.87 | A - Node within 0.5 km | 0.33 | 0.5 | Node: TRC002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 894
1 | 895 | 895 | 0402123025 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Jose | 14.3313 | 121.0369 | R | 4558 | 3.4 | 1341 | 402 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 1.52 | Tier 2A: High Commercial ROI | 70.1 | 70.1 | 51.64 | 60.87 | D - Other node or line within 3 km | 1.5 | 1.32 | Line: AE SPL002 TO SPL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 895
1 | 896 | 896 | 1380606192 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 586 | 11.653 | 120.9723 | U | 6859 | 3.21 | 2140 | 642 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.44 | 74.31 | Tier 1B: High GIDA Priority | 44.43 | 44.43 | 77.31 | 60.87 | F - Nearest node and line over 5 km | 75.44 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 896
1 | 897 | 897 | 1402701025 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Pula | 16.9761 | 121.1063 | R | 479 | 3.9 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.71 | 5.76 | Tier 1B: High GIDA Priority | 43.05 | 43.05 | 78.7 | 60.87 | F - Nearest node and line over 5 km | 8.71 | 12.24 | Node: BEF001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 897
1 | 898 | 898 | 0401003004 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 10 | 13.9582 | 120.7236 | R | 2777 | 3.6 | 771 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 64.91 | 64.91 | 56.82 | 60.86 | D - Other node or line within 3 km | 1.7 | 0.51 | Line: NSB001 TO BYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 898
1 | 899 | 899 | 0306916078 | Region III (Central Luzon) | Tarlac | City of Tarlac | Santo Cristo | 15.4883 | 120.5944 | U | 3012 | 3.9 | 772 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 56.98 | 56.98 | 64.74 | 60.86 | C - Line within 0.5 km; node over 1 km | 2.05 | 0.08 | Line: 33,700 mtrs. | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 899
1 | 900 | 900 | 1907005021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Imam Sapie | 17.2558 | 122.2299 | R | 5021 | 5.8 | 866 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 47.26 | 47.26 | 74.46 | 60.86 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 900
1 | 901 | 901 | 0405804038 | Region IV-A (CALABARZON) | Rizal | Binangonan | Libid | 14.4615 | 121.1994 | U | 7723 | 3.6 | 2145 | 644 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.56 | 1.07 | Tier 2B: Moderate GIDA Inclusion | 64.99 | 64.99 | 56.71 | 60.85 | D - Other node or line within 3 km | 1.56 | 0.91 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 901
1 | 902 | 902 | 1401103007 | Cordillera Administrative Region (CAR) | Benguet | Bakun | Kayapa | 16.7574 | 120.6991 | R | 1508 | 3.5 | 431 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 8.55 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.41 | 54.41 | 67.29 | 60.85 | B - Node 0.5-1 km | 0.68 | 8.52 | Node: KIB002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 902
1 | 903 | 903 | 1908816007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Kalbugan | 17.255 | 122.229 | R | 4943 | 4.7 | 1052 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 49.44 | 49.44 | 72.25 | 60.85 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 903
1 | 904 | 904 | 0600410009 | Region VI (Western Visayas) | Aklan | Madalag | Galicia | 11.5475 | 122.2782 | R | 386 | 3.9 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.62 | 9.4 | Tier 1B: High GIDA Priority | 46.22 | 46.22 | 75.49 | 60.85 | F - Nearest node and line over 5 km | 8.62 | 9.4 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 904
1 | 905 | 905 | 1401101003 | Cordillera Administrative Region (CAR) | Benguet | Atok | Cattubo | 16.6791 | 120.7741 | R | 2747 | 3.5 | 785 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.93 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 66.26 | 66.26 | 55.43 | 60.84 | C - Line within 0.5 km; node over 1 km | 4.93 | 0.03 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 905
1 | 906 | 906 | 0405607084 | Region IV-A (CALABARZON) | Quezon | Calauag | Tamis | 14.1891 | 122.2595 | R | 612 | 3.8 | 161 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.34 | 13.22 | Tier 1B: High GIDA Priority | 40.09 | 40.09 | 81.59 | 60.84 | F - Nearest node and line over 5 km | 7.34 | 13.22 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 906
1 | 907 | 907 | 1102319025 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo South | 7.4486 | 125.8023 | U | 11757 | 3.7 | 3178 | 953 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 0.7 | Tier 2B: Moderate GIDA Inclusion | 68.25 | 68.25 | 53.38 | 60.82 | D - Other node or line within 3 km | 2.39 | 0.7 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 907
1 | 908 | 908 | 1380300031 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Valenzuela | 14.5424 | 121.0236 | U | 5598 | 2.91 | 1923 | 577 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.58 | Tier 1B: High GIDA Priority | 60.13 | 60.13 | 61.51 | 60.82 | D - Other node or line within 3 km | 1.31 | 0.58 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 908
1 | 909 | 909 | 1401106002 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Dalupirip | 16.3233 | 120.7228 | R | 2940 | 3.5 | 840 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.87 | 10.18 | Tier 1B: High GIDA Priority | 59.11 | 59.11 | 62.53 | 60.82 | F - Nearest node and line over 5 km | 5.87 | 10.02 | Node: ITB004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 909
1 | 910 | 910 | 1380606070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 464 | 14.0842 | 122.3501 | U | 3138 | 3.46 | 908 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.68 | 2.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.86 | 50.86 | 70.76 | 60.81 | D - Other node or line within 3 km | 2.68 | 2.36 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 910
1 | 911 | 911 | 1380200014 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pamplona Tres | 14.4539 | 120.9794 | U | 37234 | 3.57 | 10432 | 3130 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.34 | 0.42 | Tier 1B: High GIDA Priority | 60.24 | 60.24 | 61.35 | 60.8 | C - Line within 0.5 km; node over 1 km | 1.34 | 0.3 | Line: Aerial 216C MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 911
1 | 912 | 912 | 1381100061 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 61 | 14.4868 | 120.9478 | U | 3154 | 3.57 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 3.2 | Tier 1B: High GIDA Priority | 49.28 | 49.28 | 72.31 | 60.8 | E - Nearest node or line 3-5 km | 3.5 | 3.2 | Line: PSG001 RELIANCE TO NCC001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 912
1 | 913 | 913 | 0403425002 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Cuyab | 14.2785 | 121.43 | U | 23482 | 3.3 | 7116 | 2135 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.83 | 1.2 | Tier 2B: Moderate GIDA Inclusion | 67.56 | 67.56 | 54.02 | 60.79 | D - Other node or line within 3 km | 1.83 | 1.2 | Line: STA CRUZ TO PAGSANJAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 913
1 | 914 | 914 | 1403214014 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Anggacan Sur | 17.3014 | 121.2398 | R | 174 | 4.3 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.52 | 8.09 | Tier 1B: High GIDA Priority | 41.13 | 41.13 | 80.43 | 60.78 | F - Nearest node and line over 5 km | 10.52 | 7.86 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 914
1 | 915 | 915 | 0401005020 | Region IV-A (CALABARZON) | Batangas | Batangas City | Cuta | 13.7511 | 121.055 | U | 14489 | 3.6 | 4025 | 1208 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.26 | 0.68 | Tier 2A: High Commercial ROI | 71.28 | 71.28 | 50.26 | 60.77 | D - Other node or line within 3 km | 1.26 | 0.68 | Line: AE TO ELIMINATE COMMON 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 915
1 | 916 | 916 | 0205009007 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Biyoy | 16.2367 | 121.4072 | R | 2296 | 3.8 | 604 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.97 | 25.91 | Tier 1B: High GIDA Priority | 45.57 | 45.57 | 75.97 | 60.77 | F - Nearest node and line over 5 km | 14.97 | 25.86 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 916
1 | 917 | 917 | 0301410034 | Region III (Central Luzon) | Bulacan | City of Malolos | Mojon | 14.8662 | 120.8125 | U | 16901 | 3.5 | 4829 | 1449 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.34 | 0.69 | Tier 2A: High Commercial ROI | 71.67 | 71.67 | 49.85 | 60.76 | D - Other node or line within 3 km | 1.34 | 0.68 | Line: BOUND TO SFP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 917
1 | 918 | 918 | 0402116007 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael II | 14.4314 | 120.8797 | R | 3707 | 3.4 | 1090 | 327 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 0.37 | Tier 2A: High Commercial ROI | 71.42 | 71.42 | 50.1 | 60.76 | A - Node within 0.5 km | 0.41 | 0.37 | Line: NOVELETA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 918
1 | 919 | 919 | 0401003045 | Region IV-A (CALABARZON) | Batangas | Balayan | San Juan | 13.9379 | 120.7059 | R | 2018 | 3.6 | 561 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.48 | 1.42 | Tier 1B: High GIDA Priority | 58.02 | 58.02 | 63.5 | 60.76 | D - Other node or line within 3 km | 2.48 | 1.42 | Line: BALAYAN - CALATAGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 919
1 | 920 | 920 | 0803726005 | Region VIII (Eastern Visayas) | Leyte | Kananga | Libertad | 11.2277 | 124.5419 | R | 2021 | 3.8 | 532 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.21 | 3.31 | Tier 1B: High GIDA Priority | 52.5 | 52.5 | 69.02 | 60.76 | E - Nearest node or line 3-5 km | 5.21 | 3.31 | Line: ORMOC CLS - CAPOOCAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 920
1 | 921 | 921 | 1380603013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 393 | 14.0036 | 120.8893 | U | 4130 | 3.77 | 1095 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 7.66 | Tier 1B: High GIDA Priority | 50.86 | 50.86 | 70.64 | 60.75 | E - Nearest node or line 3-5 km | 3.74 | 7.65 | Node: LYB002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 921
1 | 922 | 922 | 1908816002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Buliok | 17.255 | 122.229 | R | 5559 | 4.7 | 1183 | 355 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 49.83 | 49.83 | 71.68 | 60.75 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 922
1 | 923 | 923 | 0403416035 | Region IV-A (CALABARZON) | Laguna | Majayjay | San Miguel | 14.1424 | 121.4711 | R | 4529 | 3.3 | 1372 | 412 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.11 | Tier 2A: High Commercial ROI | 77.41 | 77.41 | 44.07 | 60.74 | A - Node within 0.5 km | 0.12 | 0.11 | Line: LILIW - LUCENA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 923
1 | 924 | 924 | 0205009001 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Antutot | 16.3938 | 121.2154 | R | 1876 | 3.8 | 494 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.02 | 10.18 | Tier 1B: High GIDA Priority | 44.52 | 44.52 | 76.96 | 60.74 | F - Nearest node and line over 5 km | 12.02 | 10.16 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 924
1 | 925 | 925 | 1381300064 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Masambong | 14.6399 | 121.0073 | U | 9355 | 3.71 | 2521 | 756 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.09 | Tier 1B: High GIDA Priority | 63.03 | 63.03 | 58.44 | 60.73 | B - Node 0.5-1 km | 0.71 | 0.09 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 925
1 | 926 | 926 | 1381300077 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pansol | 14.6659 | 121.0713 | U | 35572 | 3.99 | 8924 | 2677 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.28 | 0.14 | Tier 1B: High GIDA Priority | 64.2 | 64.2 | 57.25 | 60.72 | A - Node within 0.5 km | 0.28 | 0.08 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 926
1 | 927 | 927 | 1208003005 | Region XII (SOCCSKSARGEN) | Sarangani | Kiamba | Katubao | 5.8951 | 124.8297 | U | 5601 | 3.9 | 1436 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.66 | 42.88 | Tier 1B: High GIDA Priority | 45.54 | 45.54 | 75.89 | 60.72 | F - Nearest node and line over 5 km | 39.66 | 42.88 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 927
1 | 928 | 928 | 1381300017 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Botocan | 14.6724 | 121.0399 | U | 7406 | 4.43 | 1671 | 501 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 0.22 | Tier 1B: High GIDA Priority | 59.59 | 59.59 | 61.84 | 60.71 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.16 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 928
1 | 929 | 929 | 1108205016 | Region XI (Davao Region) | Davao de Oro | Maragusan | New Katipunan | 7.3048 | 126.1121 | R | 3073 | 3.7 | 831 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.3 | 27.46 | Tier 1B: High GIDA Priority | 48.15 | 48.15 | 73.28 | 60.71 | F - Nearest node and line over 5 km | 28.3 | 27.46 | Line: TAGUM - PANTUKAN SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 929
1 | 930 | 930 | 0806012009 | Region VIII (Eastern Visayas) | Samar | Motiong | Calapi | 11.9416 | 125.0206 | R | 2690 | 4.1 | 656 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.08 | 79.88 | Tier 1B: High GIDA Priority | 47.92 | 47.92 | 73.5 | 60.71 | F - Nearest node and line over 5 km | 78.08 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 930
1 | 931 | 931 | 0205703031 | Region II (Cagayan Valley) | Quirino | Diffun | Aklan Village | 16.5019 | 121.4604 | R | 898 | 3.9 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.37 | 9.47 | Tier 1B: High GIDA Priority | 42.18 | 42.18 | 79.23 | 60.71 | F - Nearest node and line over 5 km | 7.37 | 9.47 | Node: CBQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 931
1 | 932 | 932 | 1908701006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Liong | 17.2539 | 122.2279 | R | 5838 | 4.3 | 1358 | 407 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 50.35 | 50.35 | 71.05 | 60.7 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 932
1 | 933 | 933 | 0301410015 | Region III (Central Luzon) | Bulacan | City of Malolos | Guinhawa | 14.8354 | 120.8277 | U | 4408 | 3.5 | 1259 | 378 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 1.34 | Tier 1B: High GIDA Priority | 62.17 | 62.17 | 59.22 | 60.69 | D - Other node or line within 3 km | 1.74 | 1.34 | Line: 48 CORE (6X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 933
1 | 934 | 934 | 0600407013 | Region VI (Western Visayas) | Aklan | Kalibo | Poblacion | 11.7078 | 122.3679 | U | 12369 | 3.9 | 3172 | 952 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.23 | Tier 2A: High Commercial ROI | 71.09 | 71.09 | 50.26 | 60.68 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.23 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 934
1 | 935 | 935 | 0402103026 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row Central | 14.3078 | 120.9332 | U | 6419 | 3.4 | 1888 | 566 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.88 | 1.63 | Tier 1B: High GIDA Priority | 62.26 | 62.26 | 59.1 | 60.68 | D - Other node or line within 3 km | 2.88 | 1.63 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 935
1 | 936 | 936 | 1908822008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Pandan | 17.2551 | 122.2291 | R | 5222 | 4.7 | 1111 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 49.61 | 49.61 | 71.76 | 60.68 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 936
1 | 937 | 937 | 1705313006 | MIMAROPA Region | Palawan | Linapacan | Maroyogroyog | 11.4714 | 119.7725 | R | 2167 | 3.9 | 556 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.94 | 77.71 | Tier 1B: High GIDA Priority | 45.67 | 45.67 | 75.68 | 60.68 | F - Nearest node and line over 5 km | 29.94 | 999999 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 937
1 | 938 | 938 | 1705320026 | MIMAROPA Region | Palawan | Taytay | Baras | 10.6809 | 119.6373 | R | 980 | 3.9 | 251 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.37 | 16 | Tier 1B: High GIDA Priority | 43.84 | 43.84 | 77.52 | 60.68 | F - Nearest node and line over 5 km | 7.37 | 15.99 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 938
1 | 939 | 939 | 1908706004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Gambar | 17.2541 | 122.2281 | R | 5001 | 4.3 | 1163 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.78 | 49.78 | 71.57 | 60.67 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 939
1 | 940 | 940 | 1908704005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Meti | 17.2541 | 122.2282 | R | 4330 | 4.3 | 1007 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 49.32 | 49.32 | 72.02 | 60.67 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 940
1 | 941 | 941 | 1381400014 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Progreso | 14.6179 | 121.0348 | U | 1752 | 3.72 | 471 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.83 | 43.83 | 77.51 | 60.67 | C - Line within 0.5 km; node over 1 km | 2.04 | 0.37 | Line: UG 144C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 941
1 | 942 | 942 | 1908704006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Nalkan | 6.9879 | 123.9872 | R | 5106 | 4.3 | 1187 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 82.72 | 82.66 | Tier 1B: High GIDA Priority | 49.13 | 49.13 | 72.2 | 60.66 | F - Nearest node and line over 5 km | 82.72 | 999999 | Node: TKC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 942
1 | 943 | 943 | 0301403014 | Region III (Central Luzon) | Bulacan | Baliuag | Poblacion | 14.9574 | 120.8988 | U | 11052 | 3.5 | 3158 | 947 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 68.23 | 68.23 | 53.07 | 60.65 | C - Line within 0.5 km; node over 1 km | 1.57 | 0.42 | Line: BUSTOS - BALIUAG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 943
1 | 944 | 944 | 0103315012 | Region I (Ilocos Region) | La Union | San Gabriel | Lacong | 16.7343 | 120.4334 | R | 1545 | 3.7 | 418 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.54 | 4.56 | Tier 1B: High GIDA Priority | 51.64 | 51.64 | 69.66 | 60.65 | E - Nearest node or line 3-5 km | 7.54 | 4.56 | Line: SAN FERNANDO - SUPIDEN AERIAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 944
1 | 945 | 945 | 1381600020 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Maysan | 14.7034 | 120.967 | U | 23501 | 3.36 | 6993 | 2098 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.96 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 65.22 | 65.22 | 56.05 | 60.64 | B - Node 0.5-1 km | 0.97 | 0.54 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 945
1 | 946 | 946 | 1380610052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 738 | 13.8271 | 122.7458 | U | 3548 | 4.14 | 857 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.71 | 0.29 | Tier 1B: High GIDA Priority | 51 | 51 | 70.29 | 60.64 | C - Line within 0.5 km; node over 1 km | 4.71 | 0.27 | Line: CALAUAG - SIPOCOT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 946
1 | 947 | 947 | 0301420015 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima I | 14.8289 | 121.0585 | R | 3250 | 3.5 | 929 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.08 | 1.51 | Tier 2B: Moderate GIDA Inclusion | 68.14 | 68.14 | 53.11 | 60.63 | D - Other node or line within 3 km | 2.08 | 3.72 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 947
1 | 948 | 948 | 0604517013 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Sag-Ang | 10.3681 | 123.0293 | U | 14107 | 3.7 | 3813 | 1144 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 5.39 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 67.81 | 67.81 | 53.45 | 60.63 | F - Nearest node and line over 5 km | 5.39 | 17.47 | Node: LCL001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 948
1 | 949 | 949 | 0102820002 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Ildefonso | 18.1728 | 120.5946 | R | 1769 | 3.7 | 478 | 143 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.15 | Tier 1B: High GIDA Priority | 59.67 | 59.67 | 61.6 | 60.63 | A - Node within 0.5 km | 0.3 | 0.04 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 949
1 | 950 | 950 | 0401019019 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Butucan | 14.1131 | 120.6743 | R | 2615 | 3.6 | 726 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.4 | 0.13 | Tier 1B: High GIDA Priority | 59.32 | 59.32 | 61.95 | 60.63 | C - Line within 0.5 km; node over 1 km | 6.4 | 0.13 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 950
1 | 951 | 951 | 0600410006 | Region VI (Western Visayas) | Aklan | Madalag | Cabilawan | 11.5379 | 122.2935 | R | 515 | 3.9 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.01 | 8.26 | Tier 1B: High GIDA Priority | 45.77 | 45.77 | 75.49 | 60.63 | F - Nearest node and line over 5 km | 9.01 | 8.24 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 951
1 | 952 | 952 | 0405647045 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Opias | 14.03 | 121.5908 | U | 5490 | 3.8 | 1445 | 434 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 64.31 | 64.31 | 56.91 | 60.61 | B - Node 0.5-1 km | 0.75 | 0.15 | Line: LUCENA - LUCBAN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 952
1 | 953 | 953 | 1380700009 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Santa Elena | 14.6312 | 121.0976 | U | 7599 | 5.2 | 1461 | 438 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.3 | Tier 1B: High GIDA Priority | 59.8 | 59.8 | 61.41 | 60.61 | B - Node 0.5-1 km | 0.75 | 0.26 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 953
1 | 954 | 954 | 0405625024 | Region IV-A (CALABARZON) | Quezon | Macalelon | San Jose | 13.7664 | 122.1887 | R | 212 | 3.8 | 56 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.09 | 3.23 | Tier 1B: High GIDA Priority | 44.12 | 44.12 | 77.1 | 60.61 | E - Nearest node or line 3-5 km | 6.09 | 3.23 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 954
1 | 955 | 955 | 0402103028 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row West | 14.3249 | 120.8842 | U | 11169 | 3.4 | 3285 | 986 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.4 | 2.56 | Tier 1B: High GIDA Priority | 61.51 | 61.51 | 59.68 | 60.6 | D - Other node or line within 3 km | 4.4 | 2.56 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 955
1 | 956 | 956 | 0402103065 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas III | 14.3717 | 120.9361 | U | 39437 | 3.4 | 11599 | 3480 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.37 | 7.24 | Tier 1B: High GIDA Priority | 58.99 | 58.99 | 62.21 | 60.6 | D - Other node or line within 3 km | 1.37 | 7.24 | Node: IMC003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 956
1 | 957 | 957 | 0402116004 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio I | 14.4316 | 120.8749 | U | 5804 | 3.4 | 1707 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.87 | Tier 2B: Moderate GIDA Inclusion | 64.8 | 64.8 | 56.37 | 60.59 | B - Node 0.5-1 km | 0.91 | 0.87 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 957
1 | 958 | 958 | 1381100032 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 32 | 14.4983 | 121.0155 | U | 1919 | 2.95 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.11 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.43 | 48.43 | 72.75 | 60.59 | C - Line within 0.5 km; node over 1 km | 2.11 | 0.27 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 958
1 | 959 | 959 | 1408103006 | Cordillera Administrative Region (CAR) | Apayao | Flora | Balluyan | 18.1265 | 121.4565 | R | 1415 | 4.2 | 337 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.8 | 11.61 | Tier 1B: High GIDA Priority | 41.69 | 41.69 | 79.48 | 60.59 | F - Nearest node and line over 5 km | 10.8 | 13.53 | Node: FAY001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 959
1 | 960 | 960 | 0401005095 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Clara | 13.7531 | 121.0446 | U | 13224 | 3.6 | 3673 | 1102 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.67 | 1.52 | Tier 2B: Moderate GIDA Inclusion | 69.49 | 69.49 | 51.67 | 60.58 | D - Other node or line within 3 km | 1.67 | 1.52 | Line: LEMERY TO SAN JUAN CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 960
1 | 961 | 961 | 0205009020 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Pudi | 16.295 | 121.3092 | R | 1973 | 3.8 | 519 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.88 | 23.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53 | 53 | 68.15 | 60.58 | D - Other node or line within 3 km | 2.88 | 23.46 | Node: KSV001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 961
1 | 962 | 962 | 1908804001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Adaon | 17.2552 | 122.2292 | R | 4333 | 4.7 | 922 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 48.75 | 48.75 | 72.39 | 60.57 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 962
1 | 963 | 963 | 1108601006 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Talagutong | 6.2574 | 125.6601 | U | 7486 | 3.6 | 2079 | 624 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.61 | 42.9 | Tier 1B: High GIDA Priority | 47.22 | 47.22 | 73.93 | 60.57 | F - Nearest node and line over 5 km | 44.61 | 999999 | Node: MGN002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 963
1 | 964 | 964 | 0205703033 | Region II (Cagayan Valley) | Quirino | Diffun | Don Faustino Pagaduan | 16.5987 | 121.3896 | R | 521 | 3.9 | 134 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.13 | 4.79 | Tier 1B: High GIDA Priority | 39.63 | 39.63 | 81.52 | 60.57 | E - Nearest node or line 3-5 km | 7.13 | 4.79 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 964
1 | 965 | 965 | 0402115013 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Silangan | 14.3243 | 120.7778 | U | 11097 | 3.4 | 3264 | 979 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 69.94 | 69.94 | 51.17 | 60.56 | B - Node 0.5-1 km | 0.73 | 0.35 | Line: NAIC | Survey short node lateral; confirm port/fiber capacity, access and route. | 965
1 | 966 | 966 | 0301408015 | Region III (Central Luzon) | Bulacan | Guiguinto | Tuktukan | 14.827 | 120.8917 | U | 12398 | 3.5 | 3542 | 1063 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.04 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 68.65 | 68.65 | 52.47 | 60.56 | C - Line within 0.5 km; node over 1 km | 2.04 | 0.08 | Line: GOTACO TO HH 71 BULACAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 966
1 | 967 | 967 | 1403208007 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Colayo | 17.3274 | 121.0294 | R | 371 | 4.3 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.53 | 13.21 | Tier 1B: High GIDA Priority | 38.17 | 38.17 | 82.94 | 60.56 | F - Nearest node and line over 5 km | 14.53 | 13.2 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 967
1 | 968 | 968 | 0403425013 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Riverside | 14.3826 | 121.3094 | R | 3319 | 3.3 | 1006 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 9.09 | Tier 1B: High GIDA Priority | 63.01 | 63.01 | 58.09 | 60.55 | E - Nearest node or line 3-5 km | 3.35 | 9.08 | Node: JLR001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 968
1 | 969 | 969 | 1381100051 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 51 | 14.6048 | 120.9829 | U | 2168 | 3.57 | 608 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.33 | 49.33 | 71.76 | 60.55 | B - Node 0.5-1 km | 0.91 | 0.12 | Line: PSG001 RELIANCE TO NCC001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 969
1 | 970 | 970 | 1401112005 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Banengbeng | 16.5102 | 120.5474 | R | 913 | 3.5 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.66 | 4.93 | Tier 1B: High GIDA Priority | 48.1 | 48.1 | 73.01 | 60.55 | E - Nearest node or line 3-5 km | 6.66 | 4.75 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 970
1 | 971 | 971 | 1908701010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Minabay | 17.2541 | 122.2282 | R | 4580 | 4.3 | 1065 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 49.49 | 49.49 | 71.56 | 60.53 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 971
1 | 972 | 972 | 0405802004 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mayamot | 14.6297 | 121.1209 | U | 50271 | 3.6 | 13964 | 4189 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.24 | 0.13 | Tier 1B: High GIDA Priority | 61.64 | 61.64 | 59.4 | 60.52 | A - Node within 0.5 km | 0.24 | 0.13 | Line: Aerial 96C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 972
1 | 973 | 973 | 1381300027 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Damayan | 14.6386 | 121.0148 | U | 7254 | 3.54 | 2048 | 614 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.22 | Tier 1B: High GIDA Priority | 61.26 | 61.26 | 59.78 | 60.52 | B - Node 0.5-1 km | 0.89 | 0.22 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 973
1 | 974 | 974 | 1381300037 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa I | 14.6605 | 121.0212 | U | 2268 | 3.81 | 596 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.46 | 50.46 | 70.58 | 60.52 | A - Node within 0.5 km | 0.24 | 0.09 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 974
1 | 975 | 975 | 1381300029 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Del Monte | 14.6445 | 121.0129 | U | 10819 | 3.97 | 2727 | 818 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 64.31 | 64.31 | 56.71 | 60.51 | A - Node within 0.5 km | 0.38 | 0.3 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 975
1 | 976 | 976 | 0402116010 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo II | 14.4251 | 120.8694 | U | 6752 | 3.4 | 1986 | 596 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.52 | Tier 2B: Moderate GIDA Inclusion | 64.51 | 64.51 | 56.46 | 60.49 | D - Other node or line within 3 km | 1.55 | 1.52 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 976
1 | 977 | 977 | 1908708005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Indatuan | 17.2627 | 122.2222 | R | 4501 | 4.3 | 1047 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 33.88 | Tier 1B: High GIDA Priority | 49.42 | 49.42 | 71.56 | 60.49 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 977
1 | 978 | 978 | 0103304004 | Region I (Ilocos Region) | La Union | Bagulin | Cardiz | 16.6233 | 120.4861 | R | 1434 | 3.7 | 388 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.41 | 11.7 | Tier 1B: High GIDA Priority | 46.64 | 46.64 | 74.34 | 60.49 | F - Nearest node and line over 5 km | 11.41 | 12.82 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 978
1 | 979 | 979 | 1380200010 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Almanza Dos | 14.4186 | 121.0178 | U | 36679 | 3.61 | 10172 | 3052 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.11 | 0.96 | Tier 1B: High GIDA Priority | 60.98 | 60.98 | 59.97 | 60.48 | D - Other node or line within 3 km | 1.11 | 0.75 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 979
1 | 980 | 980 | 1380601058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 58 | 13.5779 | 123.0146 | U | 4088 | 3.89 | 1051 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.54 | 4.83 | Tier 1B: High GIDA Priority | 49.36 | 49.36 | 71.59 | 60.48 | E - Nearest node or line 3-5 km | 5.54 | 4.8 | Line: PASACAO CLS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 980
1 | 981 | 981 | 1380500017 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Mauway | 14.5834 | 121.0445 | U | 26570 | 3.5 | 7585 | 2276 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.73 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 64.93 | 64.93 | 55.97 | 60.45 | B - Node 0.5-1 km | 0.73 | 0.07 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 981
1 | 982 | 982 | 1380200020 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Singko | 14.42 | 120.9922 | U | 42013 | 3.96 | 10622 | 3187 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 2.4 | 2.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.83 | 54.83 | 66.06 | 60.45 | D - Other node or line within 3 km | 2.4 | 2.37 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 982
1 | 983 | 983 | 0402103047 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino IV | 14.3144 | 120.9624 | U | 70412 | 3.4 | 20709 | 6213 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 0.42 | 1.69 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.8 | 52.8 | 68.1 | 60.45 | A - Node within 0.5 km | 0.42 | 1.62 | Node: DMC004 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 983
1 | 984 | 984 | 1108601015 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | West Lamidan | 6.0923 | 125.6551 | R | 3216 | 3.6 | 893 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.72 | 47.04 | Tier 1B: High GIDA Priority | 49.02 | 49.02 | 71.87 | 60.45 | F - Nearest node and line over 5 km | 41.72 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 984
1 | 985 | 985 | 1380900002 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bagumbayan North | 14.6549 | 120.9499 | U | 1283 | 3.36 | 382 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.55 | 44.55 | 76.35 | 60.45 | A - Node within 0.5 km | 0.39 | 1.68 | Node: NAV001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 985
1 | 986 | 986 | 1381300113 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sikatuna Village | 14.7219 | 121.0878 | U | 6322 | 4.59 | 1378 | 413 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 1.16 | Tier 1B: High GIDA Priority | 57.24 | 57.24 | 63.64 | 60.44 | D - Other node or line within 3 km | 2.09 | 0.89 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 986
1 | 987 | 987 | 1381300049 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Katipunan | 14.6579 | 121.0162 | U | 10837 | 4.29 | 2525 | 758 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.38 | Tier 1B: High GIDA Priority | 63.07 | 63.07 | 57.8 | 60.43 | B - Node 0.5-1 km | 0.7 | 0.37 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 987
1 | 988 | 988 | 0205002021 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Latar-Nocnoc-San Francisco | 16.2503 | 121.0238 | R | 708 | 3.8 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.95 | 1.77 | Tier 1B: High GIDA Priority | 41.6 | 41.6 | 79.27 | 60.43 | D - Other node or line within 3 km | 9.95 | 1.77 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 988
1 | 989 | 989 | 1908708002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Damatog | 17.2503 | 122.2315 | R | 4229 | 4.3 | 983 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.42 | Tier 1B: High GIDA Priority | 49.25 | 49.25 | 71.56 | 60.4 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 989
1 | 990 | 990 | 0402106080 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | H-2 | 14.3783 | 120.9397 | U | 9797 | 3.4 | 2881 | 864 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 7.26 | Tier 2B: Moderate GIDA Inclusion | 65.53 | 65.53 | 55.25 | 60.39 | B - Node 0.5-1 km | 0.6 | 7.26 | Node: IMC003 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 990
1 | 991 | 991 | 1380200003 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Elias Aldana | 14.4752 | 120.9777 | U | 11758 | 3.64 | 3232 | 970 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 63.86 | 63.86 | 56.91 | 60.39 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.16 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 991
1 | 992 | 992 | 1380300005 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Carmona | 14.5775 | 121.0175 | U | 3034 | 4.08 | 744 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.63 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.15 | 52.15 | 68.63 | 60.39 | D - Other node or line within 3 km | 1.32 | 0.59 | Line: UG 144C via Y-duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 992
1 | 993 | 993 | 1381100184 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 184 | 14.5905 | 120.7728 | U | 14217 | 3.71 | 3836 | 1151 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 17.84 | 19.29 | Tier 1B: High GIDA Priority | 49.44 | 49.44 | 71.35 | 60.39 | F - Nearest node and line over 5 km | 17.84 | 19.23 | Node: CVC001 -TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 993
1 | 994 | 994 | 0600410025 | Region VI (Western Visayas) | Aklan | Madalag | Tigbawan | 11.5081 | 122.2958 | R | 742 | 3.9 | 190 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.26 | 9.75 | Tier 1B: High GIDA Priority | 45.22 | 45.22 | 75.57 | 60.39 | F - Nearest node and line over 5 km | 10.26 | 9.74 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 994
1 | 995 | 995 | 0405622045 | Region IV-A (CALABARZON) | Quezon | Lopez | Mabini | 13.8256 | 122.2922 | R | 105 | 3.8 | 28 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.58 | 4.98 | Tier 1B: High GIDA Priority | 39.09 | 39.09 | 81.7 | 60.39 | E - Nearest node or line 3-5 km | 7.58 | 4.96 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 995
1 | 996 | 996 | 1380500027 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Wack-wack Greenhills | 14.5634 | 121.0243 | U | 13775 | 3.8 | 3627 | 1088 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.27 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 67.21 | 67.21 | 53.55 | 60.38 | A - Node within 0.5 km | 0.27 | 0.59 | Node: MKT132 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 996
1 | 997 | 997 | 0401005057 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 11 | 13.7609 | 121.0605 | R | 358 | 3.6 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.8 | 49.8 | 70.94 | 60.37 | A - Node within 0.5 km | 0.42 | 0.33 | Line: UG SSB001 TO BCY001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 997
1 | 998 | 998 | 0105536013 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Fianza | 16.1948 | 120.7777 | R | 988 | 3.6 | 274 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.55 | 17.18 | Tier 1B: High GIDA Priority | 35.48 | 35.48 | 85.23 | 60.36 | F - Nearest node and line over 5 km | 17.55 | 17.16 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 998
1 | 999 | 999 | 0205704037 | Region II (Cagayan Valley) | Quirino | Maddela | Villa Jose V Ylanan | 16.3626 | 121.754 | R | 467 | 3.9 | 120 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.4 | 7.69 | Tier 1B: High GIDA Priority | 38.28 | 38.28 | 82.39 | 60.34 | F - Nearest node and line over 5 km | 8.4 | 7.69 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 999
1 | 1000 | 1000 | 0301403020 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Cristo | 14.9564 | 120.8967 | U | 10035 | 3.5 | 2867 | 860 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 67.76 | 67.76 | 52.9 | 60.33 | D - Other node or line within 3 km | 1.33 | 0.5 | Line: BUSTOS - BALIUAG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1000

## Batch 2 (1,001 - 2,000)
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization — Batch 2 (1,001 - 2,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
2 | 1 | 1001 | 0600410014 | Region VI (Western Visayas) | Aklan | Madalag | Medina | 11.4658 | 122.2568 | R | 934 | 3.9 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.45 | 16.06 | Tier 1B: High GIDA Priority | 42.15 | 42.15 | 78.51 | 60.33 | F - Nearest node and line over 5 km | 16.45 | 16.04 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1001
2 | 2 | 1002 | 0301420054 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz II | 14.806 | 121.024 | R | 3559 | 3.5 | 1017 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.1 | Tier 2A: High Commercial ROI | 70.34 | 70.34 | 50.25 | 60.3 | B - Node 0.5-1 km | 0.94 | 0.1 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1002
2 | 3 | 1003 | 0301410025 | Region III (Central Luzon) | Bulacan | City of Malolos | Longos | 14.8731 | 120.7921 | U | 17769 | 3.5 | 5077 | 1523 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.38 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 68.49 | 68.49 | 52.11 | 60.3 | C - Line within 0.5 km; node over 1 km | 3.38 | 0.49 | Line: MALOLOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1003
2 | 4 | 1004 | 1381000006 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Tambo | 14.5167 | 120.9969 | U | 35356 | 3.68 | 9605 | 2882 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.28 | 0.06 | Tier 1B: High GIDA Priority | 63.35 | 63.35 | 57.23 | 60.29 | A - Node within 0.5 km | 0.28 | 0.04 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1004
2 | 5 | 1005 | 0402118053 | Region IV-A (CALABARZON) | Cavite | Silang | Yakal | 14.1949 | 120.9729 | U | 7419 | 3.4 | 2182 | 655 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.97 | 1.05 | Tier 1B: High GIDA Priority | 61.99 | 61.99 | 58.58 | 60.29 | D - Other node or line within 3 km | 3.97 | 1.05 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1005
2 | 6 | 1006 | 0601909024 | Region VI (Western Visayas) | Capiz | Panay | Jamul-awon | 11.5325 | 122.8611 | R | 831 | 3.8 | 219 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.75 | 5.73 | Tier 1B: High GIDA Priority | 44.76 | 44.76 | 75.81 | 60.29 | F - Nearest node and line over 5 km | 6.75 | 5.72 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1006
2 | 7 | 1007 | 0806412022 | Region VIII (Eastern Visayas) | Southern Leyte | Saint Bernard | Malinao | 10.3671 | 125.0937 | R | 42 | 4.1 | 10 | 3 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.36 | 11.22 | Tier 1B: High GIDA Priority | 42.66 | 42.66 | 77.93 | 60.29 | F - Nearest node and line over 5 km | 38.93 | 35.24 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1007
2 | 8 | 1008 | 0603023008 | Region VI (Western Visayas) | Iloilo | Janiuay | Barasalon | 11.0104 | 122.3566 | R | 1539 | 3.8 | 405 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.55 | 17 | Tier 1B: High GIDA Priority | 40.57 | 40.57 | 80.01 | 60.29 | F - Nearest node and line over 5 km | 18.55 | 16.94 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1008
2 | 9 | 1009 | 1380200005 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Manuyo Uno | 14.4825 | 120.9847 | U | 13908 | 3.89 | 3574 | 1072 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.84 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 64.11 | 64.11 | 56.45 | 60.28 | C - Line within 0.5 km; node over 1 km | 1.84 | 0.16 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1009
2 | 10 | 1010 | 1908815006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagagawan | Maridagao | 13.5737 | 123.4927 | R | 3398 | 4.7 | 723 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.39 | 2.85 | Tier 1B: High GIDA Priority | 55.26 | 55.26 | 65.3 | 60.28 | D - Other node or line within 3 km | 4.39 | 2.84 | Line: SAGNAY - PATITINAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1010
2 | 11 | 1011 | 1402706011 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Chumang | 16.9742 | 121.233 | R | 1064 | 3.9 | 273 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 19.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.79 | 53.79 | 66.77 | 60.28 | D - Other node or line within 3 km | 1.22 | 20.99 | Node: MOF001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1011
2 | 12 | 1012 | 1380606190 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 584 | 11.6083 | 122.3142 | U | 3486 | 3.77 | 924 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 3.84 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.55 | 51.55 | 69.01 | 60.28 | D - Other node or line within 3 km | 2.49 | 3.82 | Node: MLK001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1012
2 | 13 | 1013 | 1380601080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 80 | 14.122 | 121.5493 | U | 2566 | 4.57 | 562 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.55 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.44 | 47.44 | 73.12 | 60.28 | D - Other node or line within 3 km | 1.32 | 0.55 | Line: SPO001 TO LBQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1013
2 | 14 | 1014 | 0401026020 | Region IV-A (CALABARZON) | Batangas | San Pascual | Poblacion | 13.7867 | 121.0259 | U | 11379 | 3.6 | 3161 | 948 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 69.23 | 69.23 | 51.31 | 60.27 | B - Node 0.5-1 km | 0.93 | 0.19 | Line: WP BYB001 TO BCY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1014
2 | 15 | 1015 | 0402108029 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Tejero | 14.3922 | 120.8643 | U | 8578 | 3.4 | 2523 | 757 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.65 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 52.71 | 60.27 | B - Node 0.5-1 km | 0.65 | 0.42 | Line: PSG001 RELIANCE TO NCC001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1015
2 | 16 | 1016 | 1381300048 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kamuning | 14.6289 | 121.0446 | U | 12496 | 3.79 | 3298 | 989 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 63.62 | 63.62 | 56.93 | 60.27 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.22 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1016
2 | 17 | 1017 | 0600405002 | Region VI (Western Visayas) | Aklan | Buruanga | Bagongbayan | 11.8116 | 121.883 | R | 1018 | 3.9 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.67 | 14.31 | Tier 1B: High GIDA Priority | 42.5 | 42.5 | 78.04 | 60.27 | F - Nearest node and line over 5 km | 16.67 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1017
2 | 18 | 1018 | 0403406017 | Region IV-A (CALABARZON) | Laguna | Calauan | Santo Tomas | 14.1668 | 121.3384 | U | 14235 | 3.3 | 4314 | 1294 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.51 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 68.99 | 68.99 | 51.52 | 60.26 | C - Line within 0.5 km; node over 1 km | 3.51 | 0.05 | Line: AE CLL001-NEW TO PLL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1018
2 | 19 | 1019 | 1380601091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 91 | 14.1311 | 121.0328 | U | 4453 | 4.14 | 1075 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.54 | 4.65 | Tier 1B: High GIDA Priority | 50.1 | 50.1 | 70.4 | 60.25 | E - Nearest node or line 3-5 km | 4.54 | 4.65 | Node: TSB001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1019
2 | 20 | 1020 | 0603038016 | Region VI (Western Visayas) | Iloilo | San Dionisio | Naborot | 11.3253 | 123.0876 | R | 160 | 3.8 | 42 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.89 | 0.29 | Tier 1B: High GIDA Priority | 47.36 | 47.36 | 73.11 | 60.24 | C - Line within 0.5 km; node over 1 km | 10.89 | 0.29 | Line: ROXAS - SARA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1020
2 | 21 | 1021 | 0402106008 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan I | 14.3107 | 120.9639 | U | 10659 | 3.4 | 3135 | 940 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.27 | 1.39 | Tier 2A: High Commercial ROI | 70.49 | 70.49 | 49.92 | 60.21 | A - Node within 0.5 km | 0.27 | 1.39 | Node: DMC004 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1021
2 | 22 | 1022 | 0402104008 | Region IV-A (CALABARZON) | Cavite | Carmona | Lantic | 14.2976 | 121.05 | U | 26024 | 3.4 | 7654 | 2296 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.03 | 1.48 | Tier 2B: Moderate GIDA Inclusion | 68.25 | 68.25 | 52.18 | 60.21 | D - Other node or line within 3 km | 1.03 | 1.48 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1022
2 | 23 | 1023 | 1380400014 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Panghulo | 14.6979 | 120.9465 | U | 20317 | 3.64 | 5586 | 1676 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.66 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 65.74 | 65.74 | 54.67 | 60.21 | C - Line within 0.5 km; node over 1 km | 1.66 | 0.49 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1023
2 | 24 | 1024 | 1401109004 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Palina | 16.7528 | 120.6998 | R | 1481 | 3.5 | 423 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 8.22 | Tier 1B: High GIDA Priority | 58.77 | 58.77 | 61.63 | 60.2 | B - Node 0.5-1 km | 0.66 | 8.19 | Node: KIB002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 1024
2 | 25 | 1025 | 1705320006 | MIMAROPA Region | Palawan | Taytay | Beton | 10.8106 | 119.6326 | R | 1744 | 3.9 | 447 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.82 | 13.72 | Tier 1B: High GIDA Priority | 42.74 | 42.74 | 77.67 | 60.2 | F - Nearest node and line over 5 km | 13.82 | 13.72 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1025
2 | 26 | 1026 | 1403214001 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Anggacan | 17.31 | 121.2381 | R | 244 | 4.3 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.78 | 7.52 | Tier 1B: High GIDA Priority | 40.9 | 40.9 | 79.51 | 60.2 | F - Nearest node and line over 5 km | 10.78 | 7.48 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1026
2 | 27 | 1027 | 0405811015 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santo Niño | 14.6694 | 121.1347 | U | 12224 | 3.6 | 3396 | 1019 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.39 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 67.55 | 67.55 | 52.83 | 60.19 | C - Line within 0.5 km; node over 1 km | 2.39 | 0.05 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1027
2 | 28 | 1028 | 1381300091 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sacred Heart | 14.6298 | 121.0366 | U | 6261 | 3.28 | 1908 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.25 | Tier 1B: High GIDA Priority | 60.36 | 60.36 | 60.03 | 60.19 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.25 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1028
2 | 29 | 1029 | 1908702011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Nuyo | 17.2541 | 122.2281 | R | 6458 | 4.3 | 1502 | 451 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.19 | Tier 1B: High GIDA Priority | 50.78 | 50.78 | 69.59 | 60.19 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1029
2 | 30 | 1030 | 1380606002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 396 | 13.708 | 121.2327 | U | 4237 | 3.18 | 1333 | 400 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6 | 13.98 | Tier 1B: High GIDA Priority | 49.97 | 49.97 | 70.41 | 60.19 | F - Nearest node and line over 5 km | 6 | 13.97 | Node: TAB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1030
2 | 31 | 1031 | 0205706016 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Asaklat | 16.2726 | 121.6053 | R | 1262 | 3.9 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.38 | 4.67 | Tier 1B: High GIDA Priority | 44.98 | 44.98 | 75.4 | 60.19 | E - Nearest node or line 3-5 km | 6.38 | 4.6 | Line: NAGTIPUNAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1031
2 | 32 | 1032 | 1908707006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Langco | 17.2503 | 122.2315 | R | 5853 | 4.3 | 1361 | 408 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.42 | Tier 1B: High GIDA Priority | 50.36 | 50.36 | 70 | 60.18 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1032
2 | 33 | 1033 | 0201521022 | Region II (Cagayan Valley) | Cagayan | Rizal | Pasingan | 17.856 | 121.3785 | R | 206 | 3.6 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 7.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.61 | 48.61 | 71.74 | 60.17 | D - Other node or line within 3 km | 1.74 | 8.89 | Node: RZC001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1033
2 | 34 | 1034 | 1404406006 | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | Bunot | 17.1956 | 121.3406 | R | 1684 | 3.7 | 455 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.26 | 21.21 | Tier 1B: High GIDA Priority | 48.5 | 48.5 | 71.81 | 60.16 | F - Nearest node and line over 5 km | 7.26 | 21.19 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1034
2 | 35 | 1035 | 1381400016 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Salapan | 14.6113 | 121.0245 | U | 9046 | 3.71 | 2436 | 731 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.14 | Tier 1B: High GIDA Priority | 61.94 | 61.94 | 58.36 | 60.15 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.14 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1035
2 | 36 | 1036 | 0405622007 | Region IV-A (CALABARZON) | Quezon | Lopez | Magsaysay | 13.8871 | 122.261 | R | 4204 | 3.8 | 1106 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.13 | 0.12 | Tier 2A: High Commercial ROI | 72.08 | 72.08 | 48.2 | 60.14 | A - Node within 0.5 km | 0.13 | 0.12 | Line: AE LZQ001 TO SNQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1036
2 | 37 | 1037 | 0307708009 | Region III (Central Luzon) | Aurora | San Luis | Dikapinisan | 15.5787 | 121.5381 | R | 1359 | 3.8 | 358 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.18 | 18.48 | Tier 1B: High GIDA Priority | 37.49 | 37.49 | 82.79 | 60.14 | F - Nearest node and line over 5 km | 18.18 | 18.18 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1037
2 | 38 | 1038 | 1906603010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Kalingalan Caluang | Pang | 17.2555 | 122.2296 | U | 5469 | 4.3 | 1272 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 47.08 | 47.08 | 73.18 | 60.13 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1038
2 | 39 | 1039 | 1003516009 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Culubun | 8.0348 | 124.1419 | R | 1499 | 4.2 | 357 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.84 | 12.42 | Tier 1B: High GIDA Priority | 44.72 | 44.72 | 75.54 | 60.13 | F - Nearest node and line over 5 km | 14.84 | 12.34 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1039
2 | 40 | 1040 | 1403209019 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pakawit | 17.5677 | 121.3945 | R | 1030 | 4.3 | 240 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.48 | 3.97 | Tier 1B: High GIDA Priority | 43.6 | 43.6 | 76.67 | 60.13 | E - Nearest node or line 3-5 km | 5.48 | 3.97 | Line: Tabuk-Conner | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1040
2 | 41 | 1041 | 0405608008 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Norte | 13.9308 | 121.4386 | U | 12010 | 3.8 | 3161 | 948 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.12 | Tier 2A: High Commercial ROI | 70.92 | 70.92 | 49.3 | 60.11 | A - Node within 0.5 km | 0.12 | 0.1 | Line: UG TIQ001 TO SRQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1041
2 | 42 | 1042 | 0306916069 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Nicolas | 15.4927 | 120.5947 | U | 7100 | 3.9 | 1821 | 546 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 63.08 | 63.08 | 57.14 | 60.11 | C - Line within 0.5 km; node over 1 km | 2.26 | 0.29 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1042
2 | 43 | 1043 | 1380611048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 686 | 14.0244 | 122.5221 | U | 3306 | 4.09 | 809 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.94 | 1.03 | Tier 1B: High GIDA Priority | 49.04 | 49.04 | 71.17 | 60.1 | D - Other node or line within 3 km | 5.94 | 1.01 | Line: CALAUAG - SIPOCOT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1043
2 | 44 | 1044 | 0105527025 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cacaoiten | 15.6701 | 120.3242 | R | 522 | 3.6 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.21 | 9.23 | Tier 1B: High GIDA Priority | 40.28 | 40.28 | 79.92 | 60.1 | F - Nearest node and line over 5 km | 6.21 | 9.2 | Node: SCT001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1044
2 | 45 | 1045 | 1381600027 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Punturin | 14.7411 | 120.9893 | U | 25170 | 3.45 | 7295 | 2188 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.26 | 0.13 | Tier 1B: High GIDA Priority | 62.68 | 62.68 | 57.48 | 60.08 | C - Line within 0.5 km; node over 1 km | 2.26 | 0.11 | Line: Aerial 96C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1045
2 | 46 | 1046 | 1001321014 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Lourdes | 7.921 | 125.1021 | R | 2187 | 3.8 | 576 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2 | 0.96 | Tier 1B: High GIDA Priority | 59.89 | 59.89 | 60.26 | 60.08 | D - Other node or line within 3 km | 2 | 0.93 | Line: MALAYBALAY - KITAOTAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1046
2 | 47 | 1047 | 1908708004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Guiawa | 17.2451 | 122.2264 | R | 3925 | 4.3 | 913 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.52 | 33.74 | Tier 1B: High GIDA Priority | 48.58 | 48.58 | 71.57 | 60.08 | F - Nearest node and line over 5 km | 28.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1047
2 | 48 | 1048 | 0702227008 | Region VII (Central Visayas) | Cebu | Liloan | Poblacion | 10.4023 | 123.9978 | U | 17033 | 3.8 | 4482 | 1345 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.59 | 0.18 | Tier 2A: High Commercial ROI | 75.49 | 75.49 | 44.65 | 60.07 | B - Node 0.5-1 km | 0.59 | 0.18 | Line: Route 7.591km | Survey short node lateral; confirm port/fiber capacity, access and route. | 1048
2 | 49 | 1049 | 1003514013 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lininding | 7.9956 | 124.0887 | R | 1863 | 4.2 | 444 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.5 | 19.2 | Tier 1B: High GIDA Priority | 44.6 | 44.6 | 75.54 | 60.07 | F - Nearest node and line over 5 km | 20.5 | 18.97 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1049
2 | 50 | 1050 | 0205009011 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Dine | 16.2839 | 121.362 | R | 1215 | 3.8 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.09 | 29.13 | Tier 1B: High GIDA Priority | 43.8 | 43.8 | 76.34 | 60.07 | F - Nearest node and line over 5 km | 8.09 | 29.13 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1050
2 | 51 | 1051 | 0504107014 | Region V (Bicol Region) | Masbate | Claveria | Osmeña | 12.8285 | 123.2457 | R | 3207 | 4.1 | 782 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.13 | 40.31 | Tier 1B: High GIDA Priority | 47.63 | 47.63 | 72.48 | 60.06 | F - Nearest node and line over 5 km | 24.13 | 55.14 | Node: LOA004-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1051
2 | 52 | 1052 | 0702218014 | Region VII (Central Visayas) | Cebu | Compostela | Poblacion | 10.456 | 124.0115 | U | 12857 | 3.8 | 3383 | 1015 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.4 | 0.21 | Tier 2A: High Commercial ROI | 73.09 | 73.09 | 47.01 | 60.05 | A - Node within 0.5 km | 0.4 | 0.11 | Line: 6.035km FOC | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1052
2 | 53 | 1053 | 1381300053 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Libis | 14.6169 | 121.0715 | U | 4386 | 3.71 | 1183 | 355 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.1 | 0.3 | Tier 1B: High GIDA Priority | 58.33 | 58.33 | 61.76 | 60.05 | C - Line within 0.5 km; node over 1 km | 1.1 | 0.3 | Line: UG 144C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1053
2 | 54 | 1054 | 0907224007 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Baliguian | Linay | 7.774 | 122.3643 | R | 2277 | 3.6 | 632 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.39 | 17.31 | Tier 1B: High GIDA Priority | 44.4 | 44.4 | 75.69 | 60.05 | F - Nearest node and line over 5 km | 20.39 | 17.3 | Line: IPIL - TUNGAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1054
2 | 55 | 1055 | 0402123001 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Aldiano Olaes | 14.3104 | 121.013 | U | 10058 | 3.4 | 2958 | 887 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 3.99 | Tier 1B: High GIDA Priority | 61.78 | 61.78 | 58.31 | 60.04 | E - Nearest node or line 3-5 km | 3.11 | 3.99 | Node: CRC002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1055
2 | 56 | 1056 | 1102501012 | Region XI (Davao Region) | Davao Oriental | Baganga | Mahanub | 7.6316 | 126.5395 | R | 4568 | 3.6 | 1269 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.54 | 57.14 | Tier 1B: High GIDA Priority | 52.41 | 52.41 | 67.67 | 60.04 | F - Nearest node and line over 5 km | 57.54 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1056
2 | 57 | 1057 | 0403412010 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Antonio | 14.1857 | 121.5062 | R | 3605 | 3.3 | 1092 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 4.02 | Tier 2A: High Commercial ROI | 72.85 | 72.85 | 47.18 | 60.01 | A - Node within 0.5 km | 0.21 | 4 | Node: LSL001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1057
2 | 58 | 1058 | 0301411002 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Sur | 14.7639 | 120.9426 | U | 11075 | 3.5 | 3164 | 949 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 69.71 | 69.71 | 50.31 | 60.01 | B - Node 0.5-1 km | 0.76 | 0.11 | Line: BOCAUE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1058
2 | 59 | 1059 | 0402117007 | Region IV-A (CALABARZON) | Cavite | Rosario | Muzon I | 14.4223 | 120.8659 | R | 4091 | 3.4 | 1203 | 361 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 1.75 | Tier 2B: Moderate GIDA Inclusion | 68.85 | 68.85 | 51.17 | 60.01 | D - Other node or line within 3 km | 2.01 | 1.75 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1059
2 | 60 | 1060 | 1908804003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Mapayag | 17.2552 | 122.2292 | R | 4141 | 4.7 | 881 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 47.62 | 47.62 | 72.41 | 60.01 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1060
2 | 61 | 1061 | 0806407016 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Cagnituan | 10.159 | 124.9152 | R | 360 | 4.1 | 88 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.67 | 5.03 | Tier 1B: High GIDA Priority | 43.78 | 43.78 | 76.25 | 60.01 | F - Nearest node and line over 5 km | 9.84 | 5.02 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1061
2 | 62 | 1062 | 1381100094 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 94 | 14.6422 | 121.0641 | U | 2418 | 3.6 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.75 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.5 | 50.5 | 69.5 | 60 | D - Other node or line within 3 km | 1.22 | 0.74 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1062
2 | 63 | 1063 | 0702227014 | Region VII (Central Visayas) | Cebu | Liloan | Yati | 10.3933 | 123.9832 | U | 37883 | 3.8 | 9969 | 2991 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.25 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 69.47 | 69.47 | 50.51 | 59.99 | C - Line within 0.5 km; node over 1 km | 2.25 | 0.12 | Line: DANAO - CEBU | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1063
2 | 64 | 1064 | 1381400020 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | West Crame | 14.608 | 121.0506 | U | 17359 | 3.36 | 5161 | 1548 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.54 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 66.48 | 66.48 | 53.47 | 59.98 | D - Other node or line within 3 km | 1.54 | 0.81 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1064
2 | 65 | 1065 | 0403425025 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Maharlika | 14.0933 | 121.1961 | U | 6117 | 3.3 | 1854 | 556 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.38 | 1.59 | Tier 2B: Moderate GIDA Inclusion | 62.81 | 62.81 | 57.14 | 59.98 | D - Other node or line within 3 km | 2.38 | 1.59 | Line: CLB001 TO SPO001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1065
2 | 66 | 1066 | 1108204037 | Region XI (Davao Region) | Davao de Oro | Maco | Teresa | 7.3767 | 126.0259 | R | 2094 | 3.7 | 566 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.86 | 18.41 | Tier 1B: High GIDA Priority | 43.59 | 43.59 | 76.38 | 59.98 | F - Nearest node and line over 5 km | 18.86 | 18.38 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1066
2 | 67 | 1067 | 1380500020 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Old Zañiga | 14.5877 | 121.0185 | U | 5435 | 3.85 | 1412 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.33 | Tier 1B: High GIDA Priority | 58.96 | 58.96 | 60.98 | 59.97 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.33 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1067
2 | 68 | 1068 | 0403404019 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Tres | 14.2508 | 121.2753 | U | 4685 | 3.3 | 1420 | 426 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.79 | 7.93 | Tier 1B: High GIDA Priority | 53.91 | 53.91 | 66.03 | 59.97 | F - Nearest node and line over 5 km | 7.79 | 7.93 | Node: BAY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1068
2 | 69 | 1069 | 1908709019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Pinantao | 17.254 | 122.228 | R | 5143 | 4.3 | 1196 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 49.88 | 49.88 | 70.06 | 59.97 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1069
2 | 70 | 1070 | 1108210013 | Region XI (Davao Region) | Davao de Oro | New Bataan | Andap | 7.513 | 126.1584 | U | 6839 | 3.7 | 1848 | 554 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.73 | 23.67 | Tier 1B: High GIDA Priority | 46.75 | 46.75 | 73.18 | 59.97 | F - Nearest node and line over 5 km | 36.73 | 23.66 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1070
2 | 71 | 1071 | 0405808005 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Manggahan | 14.7235 | 121.143 | U | 17089 | 3.6 | 4747 | 1424 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.63 | 0.31 | Tier 2A: High Commercial ROI | 72.79 | 72.79 | 47.13 | 59.96 | B - Node 0.5-1 km | 0.63 | 0.31 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1071
2 | 72 | 1072 | 1705110040 | MIMAROPA Region | Occidental Mindoro | San Jose | Naibuan | 12.3536 | 121.1008 | R | 3607 | 3.9 | 925 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.94 | 1.56 | Tier 2B: Moderate GIDA Inclusion | 66.1 | 66.1 | 53.83 | 59.96 | D - Other node or line within 3 km | 3.94 | 1.56 | Line: ROXAS - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1072
2 | 73 | 1073 | 1403214013 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Upper Taloctoc | 17.3383 | 121.2262 | R | 348 | 4.3 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.66 | 5.26 | Tier 1B: High GIDA Priority | 40.14 | 40.14 | 79.79 | 59.96 | F - Nearest node and line over 5 km | 11.66 | 5.04 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1073
2 | 74 | 1074 | 1906618016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Laud Sibaud | 16.2428 | 122.0996 | R | 990 | 6 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.84 | 1.97 | Tier 1B: High GIDA Priority | 48.35 | 48.35 | 71.54 | 59.95 | E - Nearest node or line 3-5 km | 4.84 | 999999 | Node: CSA001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1074
2 | 75 | 1075 | 0301412023 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Tugatog | 14.7239 | 120.9666 | U | 5072 | 3.5 | 1449 | 435 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.69 | Tier 2B: Moderate GIDA Inclusion | 62.96 | 62.96 | 56.91 | 59.93 | D - Other node or line within 3 km | 1.61 | 0.68 | Line: GOTACO TO HH 71 BULACAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1075
2 | 76 | 1076 | 1381300057 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Malaya | 14.6347 | 121.0569 | U | 3067 | 3.43 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.21 | Tier 1B: High GIDA Priority | 56.3 | 56.3 | 63.56 | 59.93 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.19 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1076
2 | 77 | 1077 | 1908713023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Tinungkaan | 17.254 | 122.2281 | R | 5842 | 4.3 | 1359 | 408 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 50.36 | 50.36 | 69.5 | 59.93 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1077
2 | 78 | 1078 | 1381100075 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 75 | 14.5649 | 121.0962 | U | 1707 | 2.78 | 615 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.74 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.98 | 48.98 | 70.88 | 59.93 | D - Other node or line within 3 km | 1.2 | 0.74 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1078
2 | 79 | 1079 | 1380601103 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 103 | 11.5167 | 122.2829 | U | 5071 | 4.49 | 1129 | 339 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11 | 10.35 | Tier 1B: High GIDA Priority | 45.02 | 45.02 | 74.84 | 59.93 | F - Nearest node and line over 5 km | 11 | 10.34 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1079
2 | 80 | 1080 | 1381300075 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paligsahan | 14.629 | 121.0247 | U | 5627 | 2.8 | 2013 | 604 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.98 | Tier 1B: High GIDA Priority | 60.86 | 60.86 | 58.97 | 59.92 | D - Other node or line within 3 km | 1.05 | 0.9 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1080
2 | 81 | 1081 | 1380610054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 740 | 11.6183 | 122.4476 | U | 4185 | 4.4 | 952 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.6 | 4.16 | Tier 1B: High GIDA Priority | 50.6 | 50.6 | 69.22 | 59.91 | E - Nearest node or line 3-5 km | 3.6 | 4.16 | Node: NWK001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1081
2 | 82 | 1082 | 1380614037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 781 | 13.8016 | 120.647 | U | 4337 | 4.67 | 928 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.36 | 3.47 | Tier 1B: High GIDA Priority | 50.57 | 50.57 | 69.25 | 59.91 | E - Nearest node or line 3-5 km | 3.36 | 3.42 | Node: CTG001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1082
2 | 83 | 1083 | 1003514033 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Tamparan | 8.0448 | 124.0417 | R | 1989 | 4.2 | 474 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.9 | 15.44 | Tier 1B: High GIDA Priority | 44.27 | 44.27 | 75.55 | 59.91 | F - Nearest node and line over 5 km | 25.9 | 15.42 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1083
2 | 84 | 1084 | 0806010013 | Region VIII (Eastern Visayas) | Samar | Marabut | Tagalag | 11.2478 | 125.1835 | R | 977 | 4.1 | 238 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.39 | 18.43 | Tier 1B: High GIDA Priority | 40.98 | 40.98 | 78.84 | 59.91 | F - Nearest node and line over 5 km | 19.39 | 19.4 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1084
2 | 85 | 1085 | 1381300002 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Amihan | 14.6324 | 121.0705 | U | 4174 | 3.78 | 1105 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.67 | 0.24 | Tier 1B: High GIDA Priority | 58.93 | 58.93 | 60.87 | 59.9 | B - Node 0.5-1 km | 0.67 | 0.23 | Line: UG 288C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1085
2 | 86 | 1086 | 0402103046 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino III | 14.3114 | 120.84 | U | 63684 | 3.4 | 18731 | 5619 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 3.62 | 2.14 | Tier 1B: High GIDA Priority | 46.65 | 46.65 | 73.15 | 59.9 | D - Other node or line within 3 km | 3.62 | 2.14 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1086
2 | 87 | 1087 | 0102908010 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Pilipil | 16.9396 | 120.7574 | R | 502 | 3.8 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.22 | 0.14 | Tier 1B: High GIDA Priority | 47.92 | 47.92 | 71.85 | 59.88 | C - Line within 0.5 km; node over 1 km | 6.22 | 0.14 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1087
2 | 88 | 1088 | 1380601020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 20 | 12.0721 | 123.0744 | U | 43691 | 4.08 | 10700 | 3210 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 17.99 | 28.11 | Tier 1B: High GIDA Priority | 43.62 | 43.62 | 76.14 | 59.88 | F - Nearest node and line over 5 km | 17.99 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1088
2 | 89 | 1089 | 1381300132 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | West Kamias | 14.6268 | 120.9639 | U | 4546 | 3.47 | 1310 | 393 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.36 | Tier 1B: High GIDA Priority | 58.91 | 58.91 | 60.83 | 59.87 | B - Node 0.5-1 km | 0.99 | 0.91 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1089
2 | 90 | 1090 | 0402106077 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz II | 14.3359 | 120.8994 | R | 2251 | 3.4 | 662 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.63 | 4.49 | Tier 1B: High GIDA Priority | 55.08 | 55.08 | 64.67 | 59.87 | E - Nearest node or line 3-5 km | 4.63 | 4.49 | Line: TANZA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1090
2 | 91 | 1091 | 1400116008 | Cordillera Administrative Region (CAR) | Abra | Manabo | San Juan Sur | 17.4129 | 120.7057 | R | 705 | 3.8 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.44 | 19.48 | Tier 1B: High GIDA Priority | 37.47 | 37.47 | 82.28 | 59.87 | F - Nearest node and line over 5 km | 19.44 | 19.37 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1091
2 | 92 | 1092 | 0201525004 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Dungeg | 18.2349 | 121.9205 | R | 636 | 3.9 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 0.67 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.05 | 53.05 | 66.68 | 59.86 | D - Other node or line within 3 km | 1.72 | 0.67 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1092
2 | 93 | 1093 | 1381100004 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 4 | 14.5321 | 121.0021 | U | 2195 | 3.68 | 597 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.48 | 49.48 | 70.24 | 59.86 | B - Node 0.5-1 km | 0.71 | 0.23 | Line: Existing 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1093
2 | 94 | 1094 | 1004326013 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Poblacion 3 | 8.5725 | 124.7855 | R | 4299 | 3.9 | 1102 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 1.64 | Tier 2B: Moderate GIDA Inclusion | 69.42 | 69.42 | 50.26 | 59.84 | D - Other node or line within 3 km | 2.89 | 1.64 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1094
2 | 95 | 1095 | 0403406003 | Region IV-A (CALABARZON) | Laguna | Calauan | Dayap | 14.1772 | 121.338 | U | 23879 | 3.3 | 7236 | 2171 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 3.88 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 64.82 | 64.82 | 54.86 | 59.84 | C - Line within 0.5 km; node over 1 km | 3.88 | 0.14 | Line: AE CLL001-NEW TO PLL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1095
2 | 96 | 1096 | 0403403008 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Francisco | 14.3311 | 121.056 | U | 43047 | 3.3 | 13045 | 3914 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 2.25 | 1.36 | Tier 1B: High GIDA Priority | 59.21 | 59.21 | 60.47 | 59.84 | D - Other node or line within 3 km | 2.25 | 1.31 | Line: AE SPL002 TO SPL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1096
2 | 97 | 1097 | 1381200021 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Jose | 14.5844 | 121.0805 | U | 1870 | 3.22 | 581 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.42 | 48.42 | 71.25 | 59.84 | C - Line within 0.5 km; node over 1 km | 1.03 | 0.21 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1097
2 | 98 | 1098 | 0102805044 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Tabug | 18.0543 | 120.5566 | R | 3406 | 3.7 | 921 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 0.19 | Tier 2A: High Commercial ROI | 70.88 | 70.88 | 48.78 | 59.83 | B - Node 0.5-1 km | 0.52 | 0.19 | Line: SEGMENT 3 (VIGAN - BATAC) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1098
2 | 99 | 1099 | 0403405055 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Juan | 14.2171 | 121.1758 | R | 5290 | 3.3 | 1603 | 481 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 67.8 | 67.8 | 51.87 | 59.83 | C - Line within 0.5 km; node over 1 km | 3.88 | 0.09 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1099
2 | 100 | 1100 | 1404408001 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Anabel | 17.1328 | 121.0645 | R | 806 | 3.7 | 218 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.35 | 0.87 | Tier 1B: High GIDA Priority | 51.77 | 51.77 | 67.89 | 59.83 | D - Other node or line within 3 km | 4.35 | 0.76 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1100
2 | 101 | 1101 | 0403415022 | Region IV-A (CALABARZON) | Laguna | Magdalena | Tanawan | 14.2257 | 121.4474 | R | 322 | 3.3 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 1.8 | Tier 1B: High GIDA Priority | 49.5 | 49.5 | 70.15 | 59.83 | D - Other node or line within 3 km | 3.5 | 1.8 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1101
2 | 102 | 1102 | 0702232017 | Region VII (Central Visayas) | Cebu | Minglanilla | Tungkop | 10.2403 | 123.7824 | U | 14574 | 3.8 | 3835 | 1150 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.92 | 0.01 | Tier 2A: High Commercial ROI | 73.19 | 73.19 | 46.45 | 59.82 | C - Line within 0.5 km; node over 1 km | 1.29 | 0.03 | Line: CEBU - TOLEDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1102
2 | 103 | 1103 | 1380200007 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pulang Lupa Uno | 14.4604 | 120.9799 | U | 36908 | 3.82 | 9651 | 2895 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.72 | 0.72 | Tier 1B: High GIDA Priority | 62.39 | 62.39 | 57.24 | 59.82 | B - Node 0.5-1 km | 0.72 | 0.69 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 1103
2 | 104 | 1104 | 1705109023 | MIMAROPA Region | Occidental Mindoro | Sablayan | Malisbong | 12.7712 | 120.8421 | R | 4495 | 3.9 | 1153 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 52.62 | 50.14 | Tier 1B: High GIDA Priority | 51.63 | 51.63 | 68.02 | 59.82 | F - Nearest node and line over 5 km | 52.62 | 51.57 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1104
2 | 105 | 1105 | 1003516013 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Lomidong | 8.0534 | 124.1807 | R | 1672 | 4.2 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.38 | 7.85 | Tier 1B: High GIDA Priority | 48.06 | 48.06 | 71.58 | 59.82 | F - Nearest node and line over 5 km | 11.38 | 7.79 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1105
2 | 106 | 1106 | 0501712003 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Cabasag | 13.9254 | 122.6052 | R | 892 | 4.2 | 212 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.33 | Tier 1B: High GIDA Priority | 58.89 | 58.89 | 60.72 | 59.8 | B - Node 0.5-1 km | 0.74 | 0.32 | Line: LZQ001 TO DEL GALLEGO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1106
2 | 107 | 1107 | 1102315034 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Santo Niño | 7.3164 | 125.6293 | U | 5242 | 3.7 | 1417 | 425 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.89 | 5.88 | Tier 1B: High GIDA Priority | 56.77 | 56.77 | 62.83 | 59.8 | F - Nearest node and line over 5 km | 5.89 | 5.88 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1107
2 | 108 | 1108 | 1380605012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 310 | 14.3055 | 122.2352 | U | 13761 | 4.5 | 3061 | 918 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.36 | 21.34 | Tier 1B: High GIDA Priority | 47.14 | 47.14 | 72.46 | 59.8 | F - Nearest node and line over 5 km | 20.36 | 21.27 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1108
2 | 109 | 1109 | 0403425004 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | G.S.I.S. | 14.3675 | 121.258 | R | 3100 | 3.3 | 939 | 282 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.37 | 12.65 | Tier 1B: High GIDA Priority | 60.35 | 60.35 | 59.24 | 59.79 | F - Nearest node and line over 5 km | 7.37 | 12.65 | Node: JLR001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1109
2 | 110 | 1110 | 0205704023 | Region II (Cagayan Valley) | Quirino | Maddela | San Martin | 16.3913 | 121.7801 | R | 958 | 3.9 | 246 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.28 | 11.15 | Tier 1B: High GIDA Priority | 37.67 | 37.67 | 81.9 | 59.79 | F - Nearest node and line over 5 km | 12.28 | 11.13 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1110
2 | 111 | 1111 | 0301420001 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay I | 14.8165 | 121.0677 | U | 7593 | 3.5 | 2169 | 651 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 2.25 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 55.75 | 59.78 | A - Node within 0.5 km | 0.47 | 2.58 | Node: SJD003 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1111
2 | 112 | 1112 | 1380601210 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 209 | 13.2558 | 123.2138 | U | 4704 | 3.91 | 1202 | 361 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.09 | 19.68 | Tier 1B: High GIDA Priority | 49.21 | 49.21 | 70.36 | 59.78 | F - Nearest node and line over 5 km | 7.09 | 19.67 | Node: BNC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1112
2 | 113 | 1113 | 0501734038 | Region V (Bicol Region) | Camarines Sur | Sipocot | San Vicente | 13.7641 | 122.9755 | R | 1166 | 4.2 | 278 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 1 | Tier 1B: High GIDA Priority | 56.88 | 56.88 | 62.67 | 59.77 | A - Node within 0.5 km | 0.23 | 0.94 | Node: SPC001 - TYPE 2 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1113
2 | 114 | 1114 | 0405603028 | Region IV-A (CALABARZON) | Quezon | Atimonan | Montes Kallagan | 13.9872 | 121.9295 | R | 221 | 3.8 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.91 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.61 | 47.61 | 71.93 | 59.77 | D - Other node or line within 3 km | 1.58 | 0.91 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1114
2 | 115 | 1115 | 0301403016 | Region III (Central Luzon) | Bulacan | Baliuag | Sabang | 14.9653 | 120.9092 | U | 13115 | 3.5 | 3747 | 1124 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.87 | 0.51 | Tier 2A: High Commercial ROI | 71.27 | 71.27 | 48.24 | 59.76 | B - Node 0.5-1 km | 0.87 | 0.51 | Line: 32 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1115
2 | 116 | 1116 | 0102814002 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Barangobong | 17.8417 | 120.5756 | R | 450 | 3.7 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.33 | 9.52 | Tier 1B: High GIDA Priority | 34.48 | 34.48 | 85.04 | 59.76 | F - Nearest node and line over 5 km | 12.33 | 9.35 | Line: SEGMENT 6 NUEVA ERA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1116
2 | 117 | 1117 | 0301408011 | Region III (Central Luzon) | Bulacan | Guiguinto | Tabang | 14.8315 | 120.8641 | U | 11984 | 3.5 | 3424 | 1027 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.99 | 0.38 | Tier 2A: High Commercial ROI | 70.07 | 70.07 | 49.43 | 59.75 | B - Node 0.5-1 km | 0.99 | 0.29 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 1117
2 | 118 | 1118 | 0403428018 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pulong Santa Cruz | 14.28 | 121.0855 | U | 32250 | 3.3 | 9773 | 2932 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.53 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 66.48 | 66.48 | 53.03 | 59.75 | B - Node 0.5-1 km | 0.53 | 0.04 | Line: TGY001 TO CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1118
2 | 119 | 1119 | 1003502012 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Landa | 8.1017 | 124.2119 | R | 3451 | 4.2 | 822 | 247 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.29 | 1.79 | Tier 1B: High GIDA Priority | 56.69 | 56.69 | 62.81 | 59.75 | D - Other node or line within 3 km | 12.29 | 1.75 | Line: 216f feeder iligan completed | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1119
2 | 120 | 1120 | 0405647003 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone I | 14.0223 | 121.5959 | R | 1781 | 3.8 | 469 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.04 | Tier 1B: High GIDA Priority | 59.37 | 59.37 | 60.12 | 59.74 | A - Node within 0.5 km | 0.31 | 0.04 | Line: LUCENA - LUCBAN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1120
2 | 121 | 1121 | 1108601011 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Lapuan | 6.1537 | 125.6885 | U | 5455 | 3.6 | 1515 | 454 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.71 | 48.71 | Tier 1B: High GIDA Priority | 45.65 | 45.65 | 73.83 | 59.74 | F - Nearest node and line over 5 km | 45.71 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1121
2 | 122 | 1122 | 0506209022 | Region V (Bicol Region) | Sorsogon | Irosin | San Isidro | 12.6939 | 124.0058 | R | 785 | 4 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.37 | 0.74 | Tier 1B: High GIDA Priority | 50.02 | 50.02 | 69.44 | 59.73 | D - Other node or line within 3 km | 3.37 | 0.73 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1122
2 | 123 | 1123 | 0806405001 | Region VIII (Eastern Visayas) | Southern Leyte | Libagon | Biasong | 10.3061 | 125.0514 | R | 552 | 4.1 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.67 | 7.58 | Tier 1B: High GIDA Priority | 43.2 | 43.2 | 76.27 | 59.73 | F - Nearest node and line over 5 km | 31.01 | 27.05 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1123
2 | 124 | 1124 | 1108211014 | Region XI (Davao Region) | Davao de Oro | Pantukan | Tag-Ugpo | 7.2624 | 126.0911 | U | 4093 | 3.7 | 1106 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.53 | 23.49 | Tier 1B: High GIDA Priority | 45.6 | 45.6 | 73.84 | 59.72 | F - Nearest node and line over 5 km | 25.53 | 23.46 | Line: TAGUM - PANTUKAN SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1124
2 | 125 | 1125 | 0301410012 | Region III (Central Luzon) | Bulacan | City of Malolos | Bulihan | 14.8581 | 120.8005 | U | 16583 | 3.5 | 4738 | 1421 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.85 | 0.88 | Tier 2A: High Commercial ROI | 70.95 | 70.95 | 48.47 | 59.71 | D - Other node or line within 3 km | 1.85 | 0.88 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1125
2 | 126 | 1126 | 1380500023 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Pleasant Hills | 14.5872 | 121.0386 | U | 6097 | 3.59 | 1699 | 510 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.26 | 0.26 | Tier 1B: High GIDA Priority | 61.55 | 61.55 | 57.85 | 59.7 | A - Node within 0.5 km | 0.26 | 0.1 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1126
2 | 127 | 1127 | 1381300018 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bungad | 14.6511 | 121.0249 | U | 7791 | 3.85 | 2023 | 607 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.74 | Tier 1B: High GIDA Priority | 60.77 | 60.77 | 58.63 | 59.7 | D - Other node or line within 3 km | 1.12 | 0.73 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1127
2 | 128 | 1128 | 0301404018 | Region III (Central Luzon) | Bulacan | Bocaue | Turo | 14.8076 | 120.9384 | U | 12401 | 3.5 | 3543 | 1063 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.04 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 68.65 | 68.65 | 50.74 | 59.69 | D - Other node or line within 3 km | 2.04 | 1.07 | Line: STA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1128
2 | 129 | 1129 | 0301403022 | Region III (Central Luzon) | Bulacan | Baliuag | Subic | 14.9635 | 120.9033 | U | 6728 | 3.5 | 1922 | 577 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 64.77 | 64.77 | 54.6 | 59.69 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.34 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1129
2 | 130 | 1130 | 0306916041 | Region III (Central Luzon) | Tarlac | City of Tarlac | Ligtasan | 15.4798 | 120.5987 | U | 2478 | 3.9 | 635 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.2 | 54.2 | 65.18 | 59.69 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.37 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1130
2 | 131 | 1131 | 1380614064 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 866 | 14.1244 | 122.4386 | U | 4046 | 3.86 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.81 | 6.09 | Tier 1B: High GIDA Priority | 48.25 | 48.25 | 71.13 | 59.69 | F - Nearest node and line over 5 km | 7.81 | 6.09 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1131
2 | 132 | 1132 | 0201521026 | Region II (Cagayan Valley) | Cagayan | Rizal | Battut | 17.8543 | 121.4133 | R | 523 | 3.6 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.79 | 10.71 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.54 | 47.54 | 71.82 | 59.68 | D - Other node or line within 3 km | 2.79 | 11.51 | Node: RZC001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1132
2 | 133 | 1133 | 1381300054 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Lourdes | 14.6298 | 120.9993 | U | 5214 | 4.94 | 1055 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.6 | Tier 1B: High GIDA Priority | 58.26 | 58.26 | 61.07 | 59.67 | B - Node 0.5-1 km | 0.93 | 0.38 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1133
2 | 134 | 1134 | 1381100165 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 165 | 14.4452 | 120.8137 | U | 5892 | 3.9 | 1511 | 453 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.38 | 7.21 | Tier 1B: High GIDA Priority | 50.05 | 50.05 | 69.28 | 59.67 | F - Nearest node and line over 5 km | 7.38 | 7.2 | Line: PSG001 RELIANCE TO NCC001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1134
2 | 135 | 1135 | 0307706005 | Region III (Central Luzon) | Aurora | Dipaculao | Dianed | 16.0128 | 121.6723 | R | 577 | 3.8 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.53 | 0.17 | Tier 1B: High GIDA Priority | 38.47 | 38.47 | 80.86 | 59.67 | C - Line within 0.5 km; node over 1 km | 12.53 | 0.15 | Line: Route | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1135
2 | 136 | 1136 | 0300807015 | Region III (Central Luzon) | Bataan | Mariveles | Camaya | 14.4443 | 120.4802 | U | 19642 | 3.6 | 5456 | 1637 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.45 | 1.07 | Tier 2A: High Commercial ROI | 70.69 | 70.69 | 48.63 | 59.66 | D - Other node or line within 3 km | 1.45 | 1.07 | Line: PIPE ORION-MARIVELES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1136
2 | 137 | 1137 | 1380606237 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 630 | 12.2679 | 120.428 | U | 6552 | 1.91 | 3432 | 1030 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 35.28 | 69.25 | Tier 1B: High GIDA Priority | 48.25 | 48.25 | 71.08 | 59.66 | F - Nearest node and line over 5 km | 35.28 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1137
2 | 138 | 1138 | 0907307007 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Banta-ao | 7.8061 | 123.338 | R | 389 | 3.9 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.49 | 1.55 | Tier 1B: High GIDA Priority | 43.8 | 43.8 | 75.52 | 59.66 | D - Other node or line within 3 km | 11.49 | 1.55 | Line: PAGADIAN - BUUG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1138
2 | 139 | 1139 | 0402106052 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima III | 14.3522 | 120.9809 | R | 3878 | 3.4 | 1141 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.06 | 3.06 | Tier 2B: Moderate GIDA Inclusion | 63.75 | 63.75 | 55.55 | 59.65 | E - Nearest node or line 3-5 km | 3.06 | 6.24 | Node: MUN048 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1139
2 | 140 | 1140 | 0403403013 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Malamig | 14.2792 | 121.0529 | U | 6843 | 3.3 | 2074 | 622 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 2.89 | Tier 1B: High GIDA Priority | 60.73 | 60.73 | 58.58 | 59.65 | D - Other node or line within 3 km | 1.89 | 2.89 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1140
2 | 141 | 1141 | 1705320031 | MIMAROPA Region | Palawan | Taytay | Paglaum | 10.6561 | 119.5024 | R | 2540 | 3.9 | 651 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.41 | 4.61 | Tier 1B: High GIDA Priority | 54.1 | 54.1 | 65.17 | 59.64 | E - Nearest node or line 3-5 km | 6.41 | 4.61 | Line: TAYTAY - PUERTO PRINCESA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1141
2 | 142 | 1142 | 0402118050 | Region IV-A (CALABARZON) | Cavite | Silang | Anahaw I | 14.2193 | 120.9671 | U | 5504 | 3.4 | 1619 | 486 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.94 | 0.55 | Tier 1B: High GIDA Priority | 58.9 | 58.9 | 60.35 | 59.63 | D - Other node or line within 3 km | 5.94 | 0.55 | Line: SILANG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1142
2 | 143 | 1143 | 0102817034 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Tadao | 18.3823 | 120.694 | R | 395 | 3.7 | 107 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.18 | 9.28 | Tier 1B: High GIDA Priority | 35.41 | 35.41 | 83.85 | 59.63 | F - Nearest node and line over 5 km | 11.18 | 9.23 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1143
2 | 144 | 1144 | 0402120005 | Region IV-A (CALABARZON) | Cavite | Tanza | Bucal | 14.3903 | 120.8622 | U | 17246 | 3.4 | 5072 | 1522 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.52 | 0.6 | Tier 2A: High Commercial ROI | 72.6 | 72.6 | 46.63 | 59.62 | B - Node 0.5-1 km | 0.52 | 0.6 | Node: TZC003 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 1144
2 | 145 | 1145 | 1381600030 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Ugong | 14.6952 | 121.0117 | U | 56202 | 3.77 | 14917 | 4475 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.22 | 1.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 54.86 | 54.86 | 64.38 | 59.62 | D - Other node or line within 3 km | 1.22 | 1.15 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1145
2 | 146 | 1146 | 1705314003 | MIMAROPA Region | Palawan | Magsaysay | Canipo | 10.9805 | 120.9635 | R | 1221 | 3.9 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 109.15 | 109.11 | Tier 1B: High GIDA Priority | 38.93 | 38.93 | 80.31 | 59.62 | F - Nearest node and line over 5 km | 109.15 | 999999 | Node: SBV001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1146
2 | 147 | 1147 | 0405646029 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Poblacion | 13.9671 | 122.5362 | U | 3983 | 3.8 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 63.2 | 63.2 | 56.02 | 59.61 | B - Node 0.5-1 km | 0.69 | 0.37 | Line: CALAUAG - SIPOCOT | Survey short node lateral; confirm port/fiber capacity, access and route. | 1147
2 | 148 | 1148 | 0402106057 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Saint Peter II | 14.3387 | 120.9209 | R | 2601 | 3.4 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.4 | 5.09 | Tier 1B: High GIDA Priority | 60.27 | 60.27 | 58.96 | 59.61 | D - Other node or line within 3 km | 2.4 | 5.18 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1148
2 | 149 | 1149 | 0405617013 | Region IV-A (CALABARZON) | Quezon | General Nakar | Pagsangahan | 14.6073 | 121.4506 | R | 1547 | 3.8 | 407 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.75 | 18.31 | Tier 1B: High GIDA Priority | 42.27 | 42.27 | 76.96 | 59.61 | F - Nearest node and line over 5 km | 11.75 | 18.31 | Node: TNR001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1149
2 | 150 | 1150 | 0600406013 | Region VI (Western Visayas) | Aklan | Ibajay | Colongcolong | 11.8192 | 122.1692 | R | 1174 | 3.9 | 301 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.73 | 0.17 | Tier 1B: High GIDA Priority | 41.97 | 41.97 | 77.26 | 59.61 | F - Nearest node and line over 5 km | 17.73 | 23.58 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1150
2 | 151 | 1151 | 0600401010 | Region VI (Western Visayas) | Aklan | Altavas | Odiong | 11.5409 | 122.479 | R | 3364 | 3.9 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.36 | Tier 2A: High Commercial ROI | 72.74 | 72.74 | 46.45 | 59.6 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.27 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1151
2 | 152 | 1152 | 1908713004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Borongotan | 17.254 | 122.2281 | R | 8927 | 4.3 | 2076 | 623 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 52.47 | 52.47 | 66.73 | 59.6 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1152
2 | 153 | 1153 | 1381600022 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pariancillo Villa | 14.7161 | 120.9725 | U | 1989 | 3.75 | 530 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.11 | 46.11 | 73.08 | 59.6 | C - Line within 0.5 km; node over 1 km | 1.59 | 0.17 | Line: Existing MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1153
2 | 154 | 1154 | 0600407001 | Region VI (Western Visayas) | Aklan | Kalibo | Andagaw | 11.7041 | 122.377 | U | 15878 | 3.9 | 4071 | 1221 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.31 | 1.08 | Tier 2A: High Commercial ROI | 73.06 | 73.06 | 46.11 | 59.59 | D - Other node or line within 3 km | 1.31 | 1.07 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1154
2 | 155 | 1155 | 0405634040 | Region IV-A (CALABARZON) | Quezon | Pitogo | Sumag Weste | 13.8398 | 122.0711 | R | 258 | 3.8 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.15 | 0.39 | Tier 1B: High GIDA Priority | 48.87 | 48.87 | 70.31 | 59.59 | C - Line within 0.5 km; node over 1 km | 4.15 | 0.39 | Line: UNISAN TO MULANAY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1155
2 | 156 | 1156 | 1381100169 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 169 | 14.6049 | 121.2134 | U | 2919 | 3.49 | 836 | 251 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 2.89 | Tier 1B: High GIDA Priority | 48.33 | 48.33 | 70.85 | 59.59 | D - Other node or line within 3 km | 3.25 | 2.89 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1156
2 | 157 | 1157 | 0402104014 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 3 | 14.3072 | 121.0518 | R | 916 | 3.4 | 269 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.6 | 53.6 | 65.55 | 59.58 | A - Node within 0.5 km | 0.45 | 0.44 | Line: AE CRC005-BNL001-CLB001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1157
2 | 158 | 1158 | 1908702008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Kulimpang | 17.2541 | 122.2281 | R | 5281 | 4.3 | 1228 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 49.97 | 49.97 | 69.2 | 59.58 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1158
2 | 159 | 1159 | 1380601123 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 123 | 12.9446 | 120.2502 | U | 8879 | 4.72 | 1882 | 565 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 94.29 | 92.81 | Tier 1B: High GIDA Priority | 43.67 | 43.67 | 75.5 | 59.58 | F - Nearest node and line over 5 km | 94.29 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1159
2 | 160 | 1160 | 1705304021 | MIMAROPA Region | Palawan | Balabac | Salang | 8.057 | 117.0659 | R | 3233 | 3.9 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 261.93 | 264.23 | Tier 1B: High GIDA Priority | 47.34 | 47.34 | 71.79 | 59.57 | F - Nearest node and line over 5 km | 261.93 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1160
2 | 161 | 1161 | 0301412004 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Banga | 14.7275 | 120.9607 | U | 2638 | 3.5 | 754 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.06 | Tier 1B: High GIDA Priority | 57.37 | 57.37 | 61.75 | 59.56 | C - Line within 0.5 km; node over 1 km | 1.47 | 0.06 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1161
2 | 162 | 1162 | 0102917008 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | San Miliano | 17.2057 | 120.555 | R | 689 | 3.8 | 181 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.06 | 3.54 | Tier 1B: High GIDA Priority | 45.74 | 45.74 | 73.37 | 59.56 | E - Nearest node or line 3-5 km | 6.06 | 3.53 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1162
2 | 163 | 1163 | 0702223031 | Region VII (Central Visayas) | Cebu | Danao City | Poblacion | 10.5202 | 124.0277 | U | 9928 | 3.8 | 2613 | 784 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.12 | Tier 2A: High Commercial ROI | 71.5 | 71.5 | 47.6 | 59.55 | A - Node within 0.5 km | 0.24 | 0.12 | Line: BOGO - DANAO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1163
2 | 164 | 1164 | 1102315025 | Region XI (Davao Region) | Davao del Norte | City of Panabo | New Pandan | 7.2956 | 125.6835 | U | 8693 | 3.7 | 2349 | 705 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 68.92 | 68.92 | 50.19 | 59.55 | B - Node 0.5-1 km | 0.66 | 0.53 | Line: DAVAO CITY - TRENTO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1164
2 | 165 | 1165 | 1705318026 | MIMAROPA Region | Palawan | Roxas | Tinitian | 10.0455 | 119.1778 | R | 2341 | 3.9 | 600 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.17 | 0.13 | Tier 1B: High GIDA Priority | 51.21 | 51.21 | 67.89 | 59.55 | C - Line within 0.5 km; node over 1 km | 12.17 | 0.13 | Line: TAYTAY - PUERTO PRINCESA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1165
2 | 166 | 1166 | 0402123021 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Nicolasa Virata | 14.3304 | 121.0354 | U | 6608 | 3.4 | 1944 | 583 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.65 | 1.67 | Tier 2B: Moderate GIDA Inclusion | 64.2 | 64.2 | 54.88 | 59.54 | D - Other node or line within 3 km | 1.65 | 1.45 | Line: AE SPL002 TO SPL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1166
2 | 167 | 1167 | 0301402002 | Region III (Central Luzon) | Bulacan | Balagtas | Borol 2nd | 14.8348 | 120.9048 | U | 8738 | 3.5 | 2497 | 749 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.49 | 1 | Tier 2B: Moderate GIDA Inclusion | 63.61 | 63.61 | 55.47 | 59.54 | D - Other node or line within 3 km | 3.49 | 1.25 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1167
2 | 168 | 1168 | 1380700005 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Malanday | 14.6502 | 121.0944 | U | 54134 | 3.91 | 13857 | 4157 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.15 | 0.38 | Tier 1B: High GIDA Priority | 56.31 | 56.31 | 62.76 | 59.54 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.38 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1168
2 | 169 | 1169 | 0301420057 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz V | 14.7776 | 121.0761 | R | 3984 | 3.5 | 1138 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.24 | Tier 2A: High Commercial ROI | 70.17 | 70.17 | 48.9 | 59.53 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.1 | Line: STA MARIA TO BRGY 181 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1169
2 | 170 | 1170 | 0506204018 | Region V (Bicol Region) | Sorsogon | Bulusan | San Jose | 12.7601 | 124.1265 | R | 1023 | 4 | 256 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 0.97 | Tier 1B: High GIDA Priority | 59.44 | 59.44 | 59.62 | 59.53 | B - Node 0.5-1 km | 0.95 | 11.7 | Node: BSS001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 1170
2 | 171 | 1171 | 1381300083 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pinagkaisahan | 14.6274 | 121.0466 | U | 5903 | 3.65 | 1616 | 485 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 0.37 | Tier 1B: High GIDA Priority | 58.97 | 58.97 | 60.08 | 59.53 | C - Line within 0.5 km; node over 1 km | 1.45 | 0.36 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1171
2 | 172 | 1172 | 1102501004 | Region XI (Davao Region) | Davao Oriental | Baganga | Batiano | 7.574 | 126.56 | R | 2886 | 3.6 | 802 | 241 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.26 | 62.13 | Tier 1B: High GIDA Priority | 46.7 | 46.7 | 72.36 | 59.53 | F - Nearest node and line over 5 km | 62.26 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1172
2 | 173 | 1173 | 0205009008 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Capisaan | 16.3322 | 121.3937 | R | 1477 | 3.8 | 389 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.75 | 26.23 | Tier 1B: High GIDA Priority | 42.81 | 42.81 | 76.26 | 59.53 | F - Nearest node and line over 5 km | 10.75 | 26.22 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1173
2 | 174 | 1174 | 0403425020 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Sampaguita Village | 14.1693 | 121.1418 | R | 5416 | 3.3 | 1641 | 492 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.15 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 50.35 | 59.52 | C - Line within 0.5 km; node over 1 km | 3.15 | 0.49 | Line: AE LBL001-STB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1174
2 | 175 | 1175 | 0402106054 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Luzviminda II | 14.2717 | 120.9723 | U | 5125 | 3.4 | 1507 | 452 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.42 | 0.56 | Tier 1B: High GIDA Priority | 60.46 | 60.46 | 58.57 | 59.52 | D - Other node or line within 3 km | 3.42 | 0.54 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1175
2 | 176 | 1176 | 0203108031 | Region II (Cagayan Valley) | Isabela | City of Cauayan | District I | 16.9316 | 121.7715 | U | 11763 | 3.8 | 3096 | 929 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 69.51 | 69.51 | 49.51 | 59.51 | B - Node 0.5-1 km | 0.77 | 0.63 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1176
2 | 177 | 1177 | 0603014003 | Region VI (Western Visayas) | Iloilo | Carles | Asluman | 11.6187 | 123.3489 | R | 3446 | 3.8 | 907 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.1 | 20.48 | Tier 1B: High GIDA Priority | 49.68 | 49.68 | 69.35 | 59.51 | F - Nearest node and line over 5 km | 30.1 | 31.1 | Node: ECI001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1177
2 | 178 | 1178 | 0702241013 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion North | 10.1642 | 123.7078 | R | 4710 | 3.8 | 1239 | 372 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.18 | Tier 2A: High Commercial ROI | 75.59 | 75.59 | 43.42 | 59.5 | A - Node within 0.5 km | 0.21 | 0.04 | Line: 216F | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1178
2 | 179 | 1179 | 1380606205 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 598 | 12.5567 | 123.2685 | U | 10510 | 4.18 | 2517 | 755 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.05 | 18.65 | Tier 1B: High GIDA Priority | 46.3 | 46.3 | 72.69 | 59.5 | F - Nearest node and line over 5 km | 15.05 | 41.23 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1179
2 | 180 | 1180 | 0307101032 | Region III (Central Luzon) | Zambales | Botolan | Owaog-Nebloc | 15.2676 | 120.0756 | R | 440 | 3.8 | 116 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.88 | 4.2 | Tier 1B: High GIDA Priority | 34.84 | 34.84 | 84.13 | 59.48 | E - Nearest node or line 3-5 km | 11.88 | 4.16 | Line: BOTOLAN - CABANGAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1180
2 | 181 | 1181 | 1403206008 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Antonio Canao | 17.3501 | 121.1872 | R | 827 | 4.3 | 192 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.42 | 1.15 | Tier 1B: High GIDA Priority | 46.29 | 46.29 | 72.64 | 59.47 | D - Other node or line within 3 km | 10.42 | 0.81 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1181
2 | 182 | 1182 | 1003512004 | Region X (Northern Mindanao) | Lanao del Norte | Maigo | Inoma | 8.1438 | 123.9687 | R | 786 | 4.2 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.77 | 2.05 | Tier 1B: High GIDA Priority | 38.05 | 38.05 | 80.88 | 59.47 | D - Other node or line within 3 km | 21.77 | 2.05 | Line: ILIGAN - PAGADIAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1182
2 | 183 | 1183 | 1381300129 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Vasra | 14.6589 | 121.0466 | U | 7883 | 3.87 | 2036 | 611 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 62.09 | 62.09 | 56.82 | 59.46 | A - Node within 0.5 km | 0.47 | 0.16 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1183
2 | 184 | 1184 | 0402123015 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Inocencio Salud | 14.3144 | 120.9993 | R | 2702 | 3.4 | 795 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 4.46 | Tier 2B: Moderate GIDA Inclusion | 61.83 | 61.83 | 57.09 | 59.46 | D - Other node or line within 3 km | 1.84 | 4.69 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1184
2 | 185 | 1185 | 1381100097 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 97 | 14.5567 | 121.1277 | U | 1291 | 2.86 | 451 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.1 | 45.1 | 73.82 | 59.46 | B - Node 0.5-1 km | 0.98 | 0.87 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1185
2 | 186 | 1186 | 0405804041 | Region IV-A (CALABARZON) | Rizal | Binangonan | San Carlos | 14.5153 | 121.1692 | U | 13488 | 3.6 | 3747 | 1124 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.06 | 0.61 | Tier 2B: Moderate GIDA Inclusion | 69.11 | 69.11 | 49.8 | 59.45 | D - Other node or line within 3 km | 2.06 | 0.61 | Line: TAYTAY TO SNL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1186
2 | 187 | 1187 | 0401019006 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 12 | 14.0991 | 120.6886 | R | 2382 | 3.6 | 662 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.67 | 1.99 | Tier 1B: High GIDA Priority | 57.49 | 57.49 | 61.41 | 59.45 | D - Other node or line within 3 km | 6.67 | 1.99 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1187
2 | 188 | 1188 | 1108604022 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Datu Intan | 6.4622 | 125.4004 | R | 1659 | 3.6 | 461 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.08 | 6.44 | Tier 1B: High GIDA Priority | 47.35 | 47.35 | 71.55 | 59.45 | F - Nearest node and line over 5 km | 9.08 | 6.44 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1188
2 | 189 | 1189 | 0403413016 | Region IV-A (CALABARZON) | Laguna | Lumban | Wawa | 14.3047 | 121.4596 | R | 4477 | 3.3 | 1357 | 407 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.69 | Tier 2A: High Commercial ROI | 71 | 71 | 47.86 | 59.43 | D - Other node or line within 3 km | 1.03 | 0.68 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1189
2 | 190 | 1190 | 1400127003 | Cordillera Administrative Region (CAR) | Abra | Villaviciosa | Cal-lao | 17.4148 | 120.6421 | R | 925 | 3.8 | 243 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.83 | 16.12 | Tier 1B: High GIDA Priority | 42.13 | 42.13 | 76.72 | 59.42 | F - Nearest node and line over 5 km | 12.83 | 16.07 | Node: NKI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1190
2 | 191 | 1191 | 0403429019 | Region IV-A (CALABARZON) | Laguna | Siniloan | P. Burgos | 14.4689 | 121.4809 | R | 5267 | 3.3 | 1596 | 479 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 4.84 | Tier 2B: Moderate GIDA Inclusion | 67.49 | 67.49 | 51.33 | 59.41 | D - Other node or line within 3 km | 1.44 | 4.84 | Node: FYL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1191
2 | 192 | 1192 | 1381300108 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santo Cristo | 14.6612 | 121.0287 | U | 30809 | 2.93 | 10526 | 3158 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.43 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 61.89 | 61.89 | 56.93 | 59.41 | A - Node within 0.5 km | 0.43 | 0.16 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1192
2 | 193 | 1193 | 0806405012 | Region VIII (Eastern Visayas) | Southern Leyte | Libagon | Punta | 10.3009 | 125.0464 | R | 249 | 4.1 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.79 | 7.04 | Tier 1B: High GIDA Priority | 43.11 | 43.11 | 75.69 | 59.4 | F - Nearest node and line over 5 km | 30.22 | 26.26 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1193
2 | 194 | 1194 | 0405804034 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tagpos | 14.5082 | 121.169 | U | 15316 | 3.6 | 4254 | 1276 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.9 | 0.24 | Tier 2A: High Commercial ROI | 70.91 | 70.91 | 47.87 | 59.39 | C - Line within 0.5 km; node over 1 km | 1.9 | 0.2 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1194
2 | 195 | 1195 | 0405803006 | Region IV-A (CALABARZON) | Rizal | Baras | Concepcion | 14.5215 | 121.2679 | R | 1095 | 3.6 | 304 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.12 | Tier 1B: High GIDA Priority | 58.79 | 58.79 | 59.99 | 59.39 | B - Node 0.5-1 km | 0.56 | 0.06 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 1195
2 | 196 | 1196 | 1381400012 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Pasadeña | 14.5983 | 121.0178 | U | 4643 | 4.49 | 1034 | 310 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 0.52 | Tier 1B: High GIDA Priority | 57.2 | 57.2 | 61.57 | 59.38 | D - Other node or line within 3 km | 1.48 | 0.56 | Line: UG 288C via W-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1196
2 | 197 | 1197 | 1380610061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 736 | 14.1478 | 121.1674 | U | 3825 | 4.45 | 860 | 258 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.96 | 3.4 | Tier 1B: High GIDA Priority | 46.84 | 46.84 | 71.93 | 59.38 | E - Nearest node or line 3-5 km | 5.96 | 3.4 | Line: AE LBL001-STB001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1197
2 | 198 | 1198 | 1908704002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Laguitan | 17.2541 | 122.2282 | R | 3528 | 4.3 | 820 | 246 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 46.06 | 46.06 | 72.7 | 59.38 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1198
2 | 199 | 1199 | 1408103005 | Cordillera Administrative Region (CAR) | Apayao | Flora | Balasi | 18.1757 | 121.4026 | R | 292 | 4.2 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.87 | 4.79 | Tier 1B: High GIDA Priority | 41.19 | 41.19 | 77.56 | 59.38 | E - Nearest node or line 3-5 km | 4.87 | 16.61 | Node: FAY001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1199
2 | 200 | 1200 | 0702227003 | Region VII (Central Visayas) | Cebu | Liloan | Catarman | 10.3864 | 124.0125 | U | 20618 | 3.8 | 5426 | 1628 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.84 | 1.27 | Tier 2A: High Commercial ROI | 73.53 | 73.53 | 45.2 | 59.37 | D - Other node or line within 3 km | 2.84 | 1.26 | Line: Route 7.591km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1200
2 | 201 | 1201 | 0403405026 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Makiling | 14.154 | 121.1371 | U | 13711 | 3.3 | 4155 | 1246 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.77 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 68.25 | 68.25 | 50.49 | 59.37 | C - Line within 0.5 km; node over 1 km | 3.77 | 0.24 | Line: AE LBL001-STB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1201
2 | 202 | 1202 | 1380603005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 385 | 14.1716 | 122.2564 | U | 3549 | 3.93 | 904 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.38 | 13.33 | Tier 1B: High GIDA Priority | 48.28 | 48.28 | 70.47 | 59.37 | F - Nearest node and line over 5 km | 5.38 | 13.33 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1202
2 | 203 | 1203 | 1381100031 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 31 | 14.5788 | 121.0241 | U | 1970 | 3.65 | 540 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.61 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.04 | 48.04 | 70.7 | 59.37 | B - Node 0.5-1 km | 0.68 | 0.55 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1203
2 | 204 | 1204 | 0301411007 | Region III (Central Luzon) | Bulacan | Marilao | Nagbalon | 14.7682 | 120.9756 | U | 3677 | 3.5 | 1051 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.82 | Tier 2B: Moderate GIDA Inclusion | 62.27 | 62.27 | 56.44 | 59.35 | D - Other node or line within 3 km | 1.31 | 2.71 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1204
2 | 205 | 1205 | 0203135020 | Region II (Cagayan Valley) | Isabela | City of Santiago | Malvar | 16.6869 | 121.5489 | U | 5125 | 3.8 | 1349 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.36 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 61.51 | 61.51 | 57.18 | 59.35 | C - Line within 0.5 km; node over 1 km | 2.36 | 0.16 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1205
2 | 206 | 1206 | 1908820008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Aguak | Poblacion I | 14.6528 | 122.7944 | R | 3711 | 4.7 | 790 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.53 | 50.84 | Tier 1B: High GIDA Priority | 44.72 | 44.72 | 73.99 | 59.35 | F - Nearest node and line over 5 km | 41.53 | 999999 | Node: PEC002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1206
2 | 207 | 1207 | 0403405057 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Milagrosa | 14.1758 | 121.1368 | U | 10619 | 3.3 | 3218 | 965 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 66.72 | 66.72 | 51.96 | 59.34 | C - Line within 0.5 km; node over 1 km | 2.59 | 0.17 | Line: AE LBL001-STB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1207
2 | 208 | 1208 | 1381300118 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Talayan | 14.6096 | 120.9898 | U | 4832 | 4.01 | 1206 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.23 | Tier 1B: High GIDA Priority | 59.1 | 59.1 | 59.59 | 59.34 | B - Node 0.5-1 km | 0.73 | 0.23 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | Survey short node lateral; confirm port/fiber capacity, access and route. | 1208
2 | 209 | 1209 | 1380500026 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Vergara | 14.5772 | 121.0251 | U | 4740 | 3.88 | 1223 | 367 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.52 | Tier 1B: High GIDA Priority | 59.05 | 59.05 | 59.63 | 59.34 | B - Node 0.5-1 km | 0.78 | 0.52 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1209
2 | 210 | 1210 | 1381100145 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 145 | 14.596 | 120.8233 | U | 10288 | 3.49 | 2952 | 886 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.85 | 15.2 | Tier 1B: High GIDA Priority | 47.71 | 47.71 | 70.95 | 59.33 | F - Nearest node and line over 5 km | 14.85 | 15.55 | Node: NAV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1210
2 | 211 | 1211 | 1380601107 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 107 | 11.436 | 122.1023 | U | 7153 | 4.59 | 1558 | 467 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.68 | 31.94 | Tier 1B: High GIDA Priority | 42.7 | 42.7 | 75.96 | 59.33 | F - Nearest node and line over 5 km | 29.68 | 31.92 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1211
2 | 212 | 1212 | 0702241018 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion South | 10.1621 | 123.707 | U | 9150 | 3.8 | 2408 | 722 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.11 | 0.06 | Tier 2A: High Commercial ROI | 71.26 | 71.26 | 47.37 | 59.31 | A - Node within 0.5 km | 0.11 | 0.05 | Line: 216f | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1212
2 | 213 | 1213 | 1381400021 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Greenhills | 14.6099 | 121.0479 | U | 19156 | 4.12 | 4645 | 1394 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.54 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 67.12 | 67.12 | 51.5 | 59.31 | D - Other node or line within 3 km | 1.54 | 0.97 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1213
2 | 214 | 1214 | 0403419010 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Maulawin | 14.2697 | 121.4546 | R | 4627 | 3.3 | 1402 | 421 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.35 | Tier 2A: High Commercial ROI | 71.91 | 71.91 | 46.69 | 59.3 | B - Node 0.5-1 km | 0.63 | 0.35 | Line: SNL001 TO SCL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1214
2 | 215 | 1215 | 0405804037 | Region IV-A (CALABARZON) | Rizal | Binangonan | Layunan | 14.4695 | 121.1934 | U | 2465 | 3.6 | 685 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.01 | 0.15 | Tier 1B: High GIDA Priority | 56.36 | 56.36 | 62.24 | 59.3 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.03 | Line: TAYTAY TO SNL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1215
2 | 216 | 1216 | 1381300061 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Mariblo | 14.6495 | 121.0055 | U | 3630 | 3.74 | 971 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 1.15 | Tier 1B: High GIDA Priority | 57.62 | 57.62 | 60.94 | 59.28 | D - Other node or line within 3 km | 1.14 | 1.14 | Node: QCY070 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1216
2 | 217 | 1217 | 1908706009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Lower Taviran | 17.2541 | 122.2281 | R | 4891 | 4.3 | 1137 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.7 | 49.7 | 68.86 | 59.28 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1217
2 | 218 | 1218 | 0306916074 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Sebastian | 15.4746 | 120.598 | U | 4413 | 3.9 | 1132 | 340 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 61.93 | 61.93 | 56.61 | 59.27 | C - Line within 0.5 km; node over 1 km | 1.66 | 0.07 | Line: PIPE 73-92 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1218
2 | 219 | 1219 | 1380500008 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Buayang Bato | 14.5683 | 121.0514 | U | 5086 | 3.63 | 1402 | 421 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 0.11 | Tier 1B: High GIDA Priority | 58.15 | 58.15 | 60.39 | 59.27 | C - Line within 0.5 km; node over 1 km | 1.57 | 0.11 | Line: UG 144C via V-DUCT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1219
2 | 220 | 1220 | 0405805015 | Region IV-A (CALABARZON) | Rizal | Cainta | San Isidro | 14.6362 | 121.1086 | U | 83020 | 3.6 | 23061 | 6918 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 1.55 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.66 | 50.66 | 67.87 | 59.26 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.03 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1220
2 | 221 | 1221 | 0405811013 | Region IV-A (CALABARZON) | Rizal | San Mateo | Gulod Malaya | 14.6735 | 121.1333 | U | 12408 | 3.6 | 3447 | 1034 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.37 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 67.74 | 67.74 | 50.76 | 59.25 | C - Line within 0.5 km; node over 1 km | 2.37 | 0.12 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1221
2 | 222 | 1222 | 0403405054 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Jose | 14.1905 | 121.1436 | U | 4452 | 3.3 | 1349 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 63.92 | 63.92 | 54.57 | 59.25 | B - Node 0.5-1 km | 0.8 | 0.39 | Line: RELIANCE TO SAN PABLO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1222
2 | 223 | 1223 | 1705208065 | MIMAROPA Region | Oriental Mindoro | Naujan | Tigkan | 13.2879 | 121.1851 | R | 816 | 3.9 | 209 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 1.98 | Tier 1B: High GIDA Priority | 49.06 | 49.06 | 69.43 | 59.25 | D - Other node or line within 3 km | 3.11 | 1.98 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1223
2 | 224 | 1224 | 0500510007 | Region V (Bicol Region) | Albay | Malinao | Bulang | 13.361 | 123.6243 | R | 1018 | 4.1 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.65 | 4.49 | Tier 1B: High GIDA Priority | 46.46 | 46.46 | 72.04 | 59.25 | E - Nearest node or line 3-5 km | 4.65 | 4.49 | Line: TABACO - LIGAO AERIAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1224
2 | 225 | 1225 | 0203110001 | Region II (Cagayan Valley) | Isabela | Dinapigue | Ayod | 16.5816 | 122.2698 | R | 324 | 3.8 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.26 | 6.48 | Tier 1B: High GIDA Priority | 39.81 | 39.81 | 78.67 | 59.24 | F - Nearest node and line over 5 km | 6.26 | 999999 | Node: DPI001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1225
2 | 226 | 1226 | 0103314057 | Region I (Ilocos Region) | La Union | City of San Fernando | Sevilla | 16.6021 | 120.3216 | U | 11353 | 3.7 | 3068 | 920 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.44 | 0.43 | Tier 2A: High Commercial ROI | 70.08 | 70.08 | 48.35 | 59.22 | A - Node within 0.5 km | 0.44 | 0.37 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1226
2 | 227 | 1227 | 1381300093 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Saint Peter | 14.632 | 120.9943 | U | 4092 | 4.58 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.33 | Tier 1B: High GIDA Priority | 56.7 | 56.7 | 61.74 | 59.22 | B - Node 0.5-1 km | 0.99 | 0.26 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1227
2 | 228 | 1228 | 1907004014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Timundon | 17.2558 | 122.2299 | R | 5264 | 5.8 | 908 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 52.81 | 52.81 | 65.64 | 59.22 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1228
2 | 229 | 1229 | 0401008015 | Region IV-A (CALABARZON) | Batangas | Calatagan | Paraiso | 13.9132 | 120.6679 | R | 1426 | 3.6 | 396 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3 | 3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.4 | 49.4 | 69.05 | 59.22 | D - Other node or line within 3 km | 3 | 3 | Node: CTG002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1229
2 | 230 | 1230 | 1908804005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Nunangan | 17.2552 | 122.2292 | R | 4564 | 4.7 | 971 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 49.19 | 49.19 | 69.24 | 59.22 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1230
2 | 231 | 1231 | 1003511014 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Pelingkingan | 8.0321 | 123.9206 | R | 1040 | 4.2 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.42 | 9.08 | Tier 1B: High GIDA Priority | 42.9 | 42.9 | 75.54 | 59.22 | F - Nearest node and line over 5 km | 13.42 | 9.08 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1231
2 | 232 | 1232 | 1380200013 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pamplona Dos | 14.4446 | 120.9966 | U | 11443 | 3.46 | 3305 | 992 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 64.35 | 64.35 | 54.06 | 59.21 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.2 | Line: UG 144C via Brown Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1232
2 | 233 | 1233 | 1606805008 | Region XIII (Caraga) | Surigao del Sur | Cantilan | General Island | 9.4223 | 126.0105 | R | 971 | 4.1 | 237 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.09 | 9.09 | Tier 1B: High GIDA Priority | 41.91 | 41.91 | 76.52 | 59.21 | F - Nearest node and line over 5 km | 9.09 | 9.09 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1233
2 | 234 | 1234 | 1380606202 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 595 | 12.1653 | 123.0433 | U | 4229 | 4.16 | 1017 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.85 | 37.27 | Tier 1B: High GIDA Priority | 41.11 | 41.11 | 77.32 | 59.21 | F - Nearest node and line over 5 km | 23.85 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1234
2 | 235 | 1235 | 0301404010 | Region III (Central Luzon) | Bulacan | Bocaue | Caingin | 14.7975 | 120.9362 | R | 5031 | 3.5 | 1437 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.61 | Tier 2B: Moderate GIDA Inclusion | 69.8 | 69.8 | 48.6 | 59.2 | D - Other node or line within 3 km | 2.01 | 0.68 | Line: BOCAUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1235
2 | 236 | 1236 | 0402123027 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Tiniente Tiago | 14.3269 | 120.9949 | R | 3276 | 3.4 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 3.34 | Tier 2B: Moderate GIDA Inclusion | 65.55 | 65.55 | 52.85 | 59.2 | D - Other node or line within 3 km | 1.44 | 4.98 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1236
2 | 237 | 1237 | 1102401002 | Region XI (Davao Region) | Davao del Sur | Bansalan | Alta Vista | 6.8341 | 125.2286 | R | 1049 | 3.4 | 309 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.54 | 16.52 | Tier 1B: High GIDA Priority | 46.36 | 46.36 | 71.98 | 59.17 | F - Nearest node and line over 5 km | 5.54 | 16.5 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1237
2 | 238 | 1238 | 0405811004 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guinayang | 14.7074 | 121.1325 | U | 9449 | 3.6 | 2625 | 788 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.71 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 64.76 | 64.76 | 53.57 | 59.16 | C - Line within 0.5 km; node over 1 km | 2.71 | 0.12 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1238
2 | 239 | 1239 | 1381000016 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Vitalez | 14.5092 | 121.0074 | U | 5477 | 2.63 | 2079 | 624 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.81 | Tier 1B: High GIDA Priority | 60.82 | 60.82 | 57.49 | 59.16 | D - Other node or line within 3 km | 1.18 | 0.73 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1239
2 | 240 | 1240 | 1380200002 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Daniel Fajardo | 14.4811 | 120.9803 | U | 10719 | 4.06 | 2640 | 792 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 61.29 | 61.29 | 57.01 | 59.15 | C - Line within 0.5 km; node over 1 km | 1.88 | 0.23 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1240
2 | 241 | 1241 | 1001302003 | Region X (Northern Mindanao) | Bukidnon | Damulog | Tangkulan | 7.42 | 124.9945 | R | 3841 | 3.8 | 1011 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.12 | 8.69 | Tier 1B: High GIDA Priority | 59.91 | 59.91 | 58.39 | 59.15 | F - Nearest node and line over 5 km | 16.12 | 8.62 | Line: DAMULOG - VALENCIA - QUEZON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1241
2 | 242 | 1242 | 1381200013 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Oranbo | 14.5757 | 121.0657 | U | 3374 | 3.54 | 954 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.41 | Tier 1B: High GIDA Priority | 57.99 | 57.99 | 60.32 | 59.15 | B - Node 0.5-1 km | 0.92 | 0.41 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1242
2 | 243 | 1243 | 1381300006 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagbag | 14.6909 | 121.0317 | U | 66268 | 3.98 | 16631 | 4989 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.4 | 0.31 | Tier 1B: High GIDA Priority | 54.33 | 54.33 | 63.97 | 59.15 | A - Node within 0.5 km | 0.4 | 0.29 | Line: UG 144C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1243
2 | 244 | 1244 | 0405644019 | Region IV-A (CALABARZON) | Quezon | San Narciso | San Isidro | 13.571 | 122.5628 | R | 1053 | 3.8 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 1.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.55 | 52.55 | 65.74 | 59.15 | D - Other node or line within 3 km | 1.07 | 1.06 | Line: UG SNQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1244
2 | 245 | 1245 | 0304928002 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | La Fuente | 15.4297 | 120.9259 | R | 3386 | 3.5 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.03 | 0.1 | Tier 2A: High Commercial ROI | 72.09 | 72.09 | 46.19 | 59.14 | B - Node 0.5-1 km | 0.81 | 0.03 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 1245
2 | 246 | 1246 | 0203135035 | Region II (Cagayan Valley) | Isabela | City of Santiago | Victory Norte | 16.6856 | 121.5506 | U | 4403 | 3.8 | 1159 | 348 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 0.21 | Tier 1B: High GIDA Priority | 60.64 | 60.64 | 57.63 | 59.14 | C - Line within 0.5 km; node over 1 km | 2.57 | 0.12 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1246
2 | 247 | 1247 | 1402711003 | Cordillera Administrative Region (CAR) | Ifugao | Asipulo | Camandag | 16.5765 | 121.0149 | R | 4217 | 3.9 | 1081 | 324 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.2 | 15.7 | Tier 1B: High GIDA Priority | 58.31 | 58.31 | 59.98 | 59.14 | F - Nearest node and line over 5 km | 17.2 | 15.7 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1247
2 | 248 | 1248 | 1380611046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 831 | 13.7126 | 122.8874 | U | 3678 | 3.3 | 1115 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.34 | 7.34 | Tier 1B: High GIDA Priority | 48.89 | 48.89 | 69.39 | 59.14 | F - Nearest node and line over 5 km | 7.34 | 7.3 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1248
2 | 249 | 1249 | 1705304020 | MIMAROPA Region | Palawan | Balabac | Ramos | 8.1196 | 117.0208 | R | 3106 | 3.9 | 796 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 260.54 | 262.84 | Tier 1B: High GIDA Priority | 46.51 | 46.51 | 71.78 | 59.14 | F - Nearest node and line over 5 km | 260.54 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1249
2 | 250 | 1250 | 1108602023 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Meybio | 5.8443 | 125.5936 | R | 2462 | 3.6 | 684 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.37 | 53.92 | Tier 1B: High GIDA Priority | 43.87 | 43.87 | 74.41 | 59.14 | F - Nearest node and line over 5 km | 45.37 | 53.92 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1250
2 | 251 | 1251 | 1907004009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Luuk Datan | 17.2558 | 122.2299 | R | 2275 | 5.8 | 392 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 39.38 | 39.38 | 78.9 | 59.14 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1251
2 | 252 | 1252 | 1401113004 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Camp 4 | 16.3099 | 120.6163 | U | 7022 | 3.5 | 2006 | 602 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.18 | 9.68 | Tier 2B: Moderate GIDA Inclusion | 64.37 | 64.37 | 53.88 | 59.13 | A - Node within 0.5 km | 0.18 | 9.57 | Node: TBB003 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1252
2 | 253 | 1253 | 1381100023 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 23 | 14.6171 | 120.9813 | U | 1591 | 3.34 | 477 | 143 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.18 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.44 | 47.44 | 70.82 | 59.13 | A - Node within 0.5 km | 0.18 | 0.06 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1253
2 | 254 | 1254 | 0601912009 | Region VI (Western Visayas) | Capiz | Pontevedra | Gabuc | 11.4534 | 122.8835 | R | 646 | 3.8 | 170 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.05 | 4.02 | Tier 1B: High GIDA Priority | 43.91 | 43.91 | 74.35 | 59.13 | E - Nearest node or line 3-5 km | 6.05 | 4.02 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1254
2 | 255 | 1255 | 1004324006 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Poblacion | 8.5373 | 124.7553 | U | 10662 | 3.9 | 2734 | 820 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.15 | Tier 2A: High Commercial ROI | 70.75 | 70.75 | 47.48 | 59.11 | A - Node within 0.5 km | 0.29 | 0.15 | Line: CDO - BUENAVISTA via GINGOOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1255
2 | 256 | 1256 | 1003514014 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lumba-Bayabao | 8.0508 | 124.0808 | R | 1585 | 4.2 | 377 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.78 | 15.03 | Tier 1B: High GIDA Priority | 42.66 | 42.66 | 75.54 | 59.1 | F - Nearest node and line over 5 km | 21.78 | 14.97 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1256
2 | 257 | 1257 | 0403410008 | Region IV-A (CALABARZON) | Laguna | Liliw | Calumpang | 14.2011 | 121.4016 | R | 4088 | 3.3 | 1239 | 372 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.17 | 2.95 | Tier 2B: Moderate GIDA Inclusion | 68.43 | 68.43 | 49.75 | 59.09 | D - Other node or line within 3 km | 3.17 | 2.95 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1257
2 | 258 | 1258 | 1380605017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 315 | 13.5724 | 122.5494 | U | 2150 | 3.79 | 568 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.75 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.29 | 48.29 | 69.88 | 59.09 | B - Node 0.5-1 km | 0.91 | 0.49 | Line: UG SNQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1258
2 | 259 | 1259 | 0401033014 | Region IV-A (CALABARZON) | Batangas | Tingloy | San Pedro | 13.6571 | 120.9148 | R | 516 | 3.6 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.19 | 16.75 | Tier 1B: High GIDA Priority | 45.75 | 45.75 | 72.43 | 59.09 | E - Nearest node or line 3-5 km | 4.19 | 16.74 | Node: MBN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1259
2 | 260 | 1260 | 0600406025 | Region VI (Western Visayas) | Aklan | Ibajay | Polo | 11.7814 | 122.1684 | R | 1288 | 3.9 | 330 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.44 | 3.49 | Tier 1B: High GIDA Priority | 40.16 | 40.16 | 78.02 | 59.09 | F - Nearest node and line over 5 km | 15.44 | 21.95 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1260
2 | 261 | 1261 | 0300809015 | Region III (Central Luzon) | Bataan | Orani | Parang Parang | 14.797 | 120.5385 | U | 1363 | 3.6 | 379 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.9 | 48.9 | 69.26 | 59.08 | B - Node 0.5-1 km | 0.62 | 0.11 | Line: 36 CORE 3X12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1261
2 | 262 | 1262 | 1381100041 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 41 | 14.5616 | 120.9959 | U | 1502 | 2.79 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.38 | 47.38 | 70.78 | 59.08 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.13 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1262
2 | 263 | 1263 | 1003511006 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lamigadato | 8.0177 | 123.9012 | R | 689 | 4.2 | 164 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.59 | 9.8 | Tier 1B: High GIDA Priority | 42.22 | 42.22 | 75.93 | 59.08 | F - Nearest node and line over 5 km | 11.59 | 9.8 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1263
2 | 264 | 1264 | 0306916048 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maliwalo | 15.4821 | 120.6195 | U | 16799 | 3.9 | 4307 | 1292 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.82 | 0.11 | Tier 2A: High Commercial ROI | 73.07 | 73.07 | 45.06 | 59.07 | B - Node 0.5-1 km | 0.82 | 0.09 | Line: SEGMENT 31 (ZARAGOZA - TARLAC) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1264
2 | 265 | 1265 | 0402108026 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Santa Clara | 14.3378 | 120.8829 | R | 3542 | 3.4 | 1042 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 3.05 | Tier 2B: Moderate GIDA Inclusion | 61.96 | 61.96 | 56.19 | 59.07 | E - Nearest node or line 3-5 km | 4.59 | 3.05 | Line: TANZA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1265
2 | 266 | 1266 | 1380606193 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 587 | 14.0549 | 121.1464 | U | 2685 | 4.18 | 642 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.12 | 0.91 | Tier 1B: High GIDA Priority | 46.92 | 46.92 | 71.22 | 59.07 | D - Other node or line within 3 km | 3.12 | 0.88 | Line: CLB001 TO BCY01 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1266
2 | 267 | 1267 | 1381300033 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Don Manuel | 14.6843 | 121.0409 | U | 2417 | 4.53 | 533 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.84 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.24 | 47.24 | 70.88 | 59.06 | D - Other node or line within 3 km | 1 | 0.96 | Line: UG 144C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1267
2 | 268 | 1268 | 1108601007 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Baluntaya | 6.2461 | 125.6403 | R | 2604 | 3.6 | 723 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.01 | 41.93 | Tier 1B: High GIDA Priority | 44.87 | 44.87 | 73.24 | 59.06 | F - Nearest node and line over 5 km | 43.01 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1268
2 | 269 | 1269 | 1907005023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Panglima Alari | 17.2558 | 122.2299 | U | 9227 | 5.8 | 1591 | 477 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 43.51 | 43.51 | 74.61 | 59.06 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1269
2 | 270 | 1270 | 0300809022 | Region III (Central Luzon) | Bataan | Orani | Tenejero | 14.7819 | 120.5128 | R | 1747 | 3.6 | 485 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 1.64 | Tier 1B: High GIDA Priority | 55.02 | 55.02 | 63.08 | 59.05 | D - Other node or line within 3 km | 3.38 | 1.63 | Line: 96C DONA TO ORANI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1270
2 | 271 | 1271 | 1380601056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 56 | 14.2286 | 121.4672 | U | 3377 | 3.97 | 850 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.14 | 3.76 | Tier 1B: High GIDA Priority | 47.79 | 47.79 | 70.3 | 59.05 | E - Nearest node or line 3-5 km | 4.14 | 3.76 | Line: PAGSANJAN TO LILIW | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1271
2 | 272 | 1272 | 1102506013 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Surop | 6.4444 | 126.1321 | R | 2719 | 3.6 | 755 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 51.96 | 48.33 | Tier 1B: High GIDA Priority | 45.51 | 45.51 | 72.59 | 59.05 | F - Nearest node and line over 5 km | 51.96 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1272
2 | 273 | 1273 | 1380601102 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 102 | 13.4249 | 123.1243 | U | 4616 | 4.64 | 995 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.71 | 12.69 | Tier 1B: High GIDA Priority | 43.26 | 43.26 | 74.85 | 59.05 | F - Nearest node and line over 5 km | 12.71 | 12.68 | Line: PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1273
2 | 274 | 1274 | 0405622057 | Region IV-A (CALABARZON) | Quezon | Lopez | Pisipis | 13.8969 | 122.3695 | R | 717 | 3.8 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.47 | 5.9 | Tier 1B: High GIDA Priority | 39.62 | 39.62 | 78.49 | 59.05 | F - Nearest node and line over 5 km | 8.47 | 5.88 | Line: AE LZQ001 TO SNQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1274
2 | 275 | 1275 | 0405805016 | Region IV-A (CALABARZON) | Rizal | Cainta | San Juan | 14.5398 | 121.1109 | U | 99685 | 3.6 | 27690 | 8307 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.63 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.37 | 52.37 | 65.71 | 59.04 | B - Node 0.5-1 km | 0.63 | 0.27 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1275
2 | 276 | 1276 | 0301408003 | Region III (Central Luzon) | Bulacan | Guiguinto | Ilang-Ilang | 14.8391 | 120.866 | U | 6006 | 3.5 | 1716 | 515 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 64.22 | 64.22 | 53.83 | 59.03 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.37 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1276
2 | 277 | 1277 | 1381600008 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Karuhatan | 14.6911 | 120.9761 | U | 42845 | 3.4 | 12609 | 3783 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.1 | 0.17 | Tier 1B: High GIDA Priority | 57.96 | 57.96 | 60.1 | 59.03 | C - Line within 0.5 km; node over 1 km | 1.1 | 0.16 | Line: EXISTING 216 C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1277
2 | 278 | 1278 | 0201518011 | Region II (Cagayan Valley) | Cagayan | Pamplona | Gattu | 18.4673 | 121.3481 | R | 484 | 3.9 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 53.67 | 53.67 | 64.39 | 59.03 | B - Node 0.5-1 km | 0.86 | 0.44 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1278
2 | 279 | 1279 | 0603015011 | Region VI (Western Visayas) | Iloilo | Concepcion | Igbon | 11.215 | 123.1885 | R | 2506 | 3.8 | 659 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.24 | 12.42 | Tier 1B: High GIDA Priority | 46.02 | 46.02 | 72.03 | 59.03 | F - Nearest node and line over 5 km | 19.24 | 12.13 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1279
2 | 280 | 1280 | 0506209009 | Region V (Bicol Region) | Sorsogon | Irosin | Cawayan | 12.6943 | 124.0863 | R | 474 | 4 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.57 | 3.95 | Tier 1B: High GIDA Priority | 43.83 | 43.83 | 74.24 | 59.03 | E - Nearest node or line 3-5 km | 5.57 | 4.94 | Line: STA MAGDALENA CLS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1280
2 | 281 | 1281 | 1380601112 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 112 | 11.9877 | 120.5815 | U | 5840 | 4.78 | 1221 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.31 | 66.21 | Tier 1B: High GIDA Priority | 41.71 | 41.71 | 76.33 | 59.02 | F - Nearest node and line over 5 km | 36.31 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1281
2 | 282 | 1282 | 1381300003 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Apolonio Samson | 14.6563 | 121.0078 | U | 34163 | 3.53 | 9677 | 2903 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.37 | 1.05 | Tier 2B: Moderate GIDA Inclusion | 61.13 | 61.13 | 56.89 | 59.01 | D - Other node or line within 3 km | 1.37 | 1.18 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1282
2 | 283 | 1283 | 1108605004 | Region XI (Davao Region) | Davao Occidental | Sarangani | Mabila | 5.411 | 125.4217 | U | 5248 | 3.9 | 1346 | 404 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.79 | 82.9 | Tier 1B: High GIDA Priority | 49.6 | 49.6 | 68.4 | 59 | F - Nearest node and line over 5 km | 78.79 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1283
2 | 284 | 1284 | 1380607012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 648 | 14.324 | 122.0353 | U | 9086 | 4.08 | 2226 | 668 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.3 | 37.85 | Tier 1B: High GIDA Priority | 44.68 | 44.68 | 73.31 | 59 | F - Nearest node and line over 5 km | 32.3 | 37.85 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1284
2 | 285 | 1285 | 1381300032 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Doña Josefa | 14.6465 | 121.0354 | U | 2198 | 4.41 | 498 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.12 | 47.12 | 70.86 | 58.99 | B - Node 0.5-1 km | 0.58 | 0.35 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1285
2 | 286 | 1286 | 0307706025 | Region III (Central Luzon) | Aurora | Dipaculao | Diamanen | 15.8899 | 121.5218 | R | 298 | 3.8 | 78 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.25 | 2.91 | Tier 1B: High GIDA Priority | 39.81 | 39.81 | 78.17 | 58.99 | D - Other node or line within 3 km | 6.25 | 2.9 | Line: Route | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1286
2 | 287 | 1287 | 0403403014 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Mampalasan | 14.2917 | 121.0781 | U | 14892 | 3.3 | 4513 | 1354 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.78 | 1.35 | Tier 2A: High Commercial ROI | 71.02 | 71.02 | 46.93 | 58.98 | D - Other node or line within 3 km | 1.78 | 1.35 | Line: AE SRL007-CBL001-CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1287
2 | 288 | 1288 | 0403403011 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Loma | 14.2878 | 121.0668 | U | 14325 | 3.3 | 4341 | 1302 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.16 | 2.13 | Tier 2B: Moderate GIDA Inclusion | 68.8 | 68.8 | 49.16 | 58.98 | D - Other node or line within 3 km | 1.16 | 2.13 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1288
2 | 289 | 1289 | 1381100152 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 152 | 14.3513 | 121.0383 | U | 1521 | 3.2 | 475 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.08 | 46.08 | 71.88 | 58.98 | B - Node 0.5-1 km | 0.79 | 0.77 | Line: AE SPL002 TO SPL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1289
2 | 290 | 1290 | 1408103008 | Cordillera Administrative Region (CAR) | Apayao | Flora | Malayugan | 18.1069 | 121.4545 | R | 1277 | 4.2 | 304 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.59 | 11.6 | Tier 1B: High GIDA Priority | 40.14 | 40.14 | 77.79 | 58.96 | F - Nearest node and line over 5 km | 11.59 | 15.04 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1290
2 | 291 | 1291 | 0806412017 | Region VIII (Eastern Visayas) | Southern Leyte | Saint Bernard | Magatas | 10.3123 | 125.1171 | R | 89 | 4.1 | 22 | 7 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.87 | 14.79 | Tier 1B: High GIDA Priority | 40.09 | 40.09 | 77.84 | 58.96 | F - Nearest node and line over 5 km | 37.28 | 32.59 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1291
2 | 292 | 1292 | 0205001006 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Napo | 16.5584 | 120.9647 | R | 1642 | 3.8 | 432 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.45 | 17.82 | Tier 1B: High GIDA Priority | 45.24 | 45.24 | 72.66 | 58.95 | F - Nearest node and line over 5 km | 15.45 | 17.81 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1292
2 | 293 | 1293 | 1381100085 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 85 | 14.6455 | 121.0228 | U | 1326 | 3.2 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.54 | 44.54 | 73.37 | 58.95 | B - Node 0.5-1 km | 0.78 | 0.43 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1293
2 | 294 | 1294 | 0806010003 | Region VIII (Eastern Visayas) | Samar | Marabut | Canyoyo | 11.1713 | 125.1963 | R | 614 | 4.1 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.59 | 19.56 | Tier 1B: High GIDA Priority | 38.82 | 38.82 | 79.07 | 58.95 | F - Nearest node and line over 5 km | 20.59 | 20.85 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1294
2 | 295 | 1295 | 0405803005 | Region IV-A (CALABARZON) | Rizal | Baras | Santiago | 14.5215 | 121.2622 | R | 3964 | 3.6 | 1101 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 0.23 | Tier 2A: High Commercial ROI | 75.22 | 75.22 | 42.67 | 58.94 | B - Node 0.5-1 km | 0.76 | 0.21 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 1295
2 | 296 | 1296 | 0300804014 | Region III (Central Luzon) | Bataan | Dinalupihan | Kataasan | 14.8713 | 120.4628 | R | 3219 | 3.6 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 69.83 | 69.83 | 48.06 | 58.94 | B - Node 0.5-1 km | 0.82 | 0.39 | Line: Path Measure | Survey short node lateral; confirm port/fiber capacity, access and route. | 1296
2 | 297 | 1297 | 0907311019 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Mahayahay | 7.7481 | 123.1442 | R | 822 | 3.9 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.03 | 1.11 | Tier 1B: High GIDA Priority | 47.13 | 47.13 | 70.76 | 58.94 | D - Other node or line within 3 km | 10.03 | 1.11 | Line: PAGADIAN - BUUG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1297
2 | 298 | 1298 | 0506212021 | Region V (Bicol Region) | Sorsogon | Matnog | Genablan Oriental | 12.5394 | 124.0354 | R | 1116 | 4 | 279 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.23 | 7.25 | Tier 1B: High GIDA Priority | 45.99 | 45.99 | 71.9 | 58.94 | F - Nearest node and line over 5 km | 7.23 | 7.23 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1298
2 | 299 | 1299 | 0401033013 | Region IV-A (CALABARZON) | Batangas | Tingloy | San Juan | 13.6379 | 120.8755 | R | 2472 | 3.6 | 687 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.05 | 15.09 | Tier 1B: High GIDA Priority | 59.37 | 59.37 | 58.5 | 58.93 | F - Nearest node and line over 5 km | 6.05 | 15.07 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1299
2 | 300 | 1300 | 0806010020 | Region VIII (Eastern Visayas) | Samar | Marabut | Odoc | 11.1635 | 125.1896 | R | 300 | 4.1 | 73 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.61 | 19.01 | Tier 1B: High GIDA Priority | 39.1 | 39.1 | 78.75 | 58.93 | F - Nearest node and line over 5 km | 19.61 | 20.33 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1300
2 | 301 | 1301 | 0201510028 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Dammang Sur | 18.2484 | 121.6962 | R | 264 | 3.9 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 1.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.31 | 52.31 | 65.52 | 58.92 | D - Other node or line within 3 km | 1.61 | 1.15 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1301
2 | 302 | 1302 | 0402117009 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa I | 14.4088 | 120.858 | R | 2056 | 3.4 | 605 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 61.22 | 61.22 | 56.61 | 58.91 | D - Other node or line within 3 km | 1.26 | 1.49 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1302
2 | 303 | 1303 | 0702219014 | Region VII (Central Visayas) | Cebu | Consolacion | Poblacion Oriental | 10.3889 | 123.9557 | U | 3218 | 3.8 | 847 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 1.44 | Tier 1B: High GIDA Priority | 59.83 | 59.83 | 57.98 | 58.91 | D - Other node or line within 3 km | 1.42 | 1.25 | Line: Route 11.925km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1303
2 | 304 | 1304 | 0401029029 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 5 | 13.8617 | 120.934 | R | 2098 | 3.6 | 583 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 2.62 | Tier 1B: High GIDA Priority | 56.11 | 56.11 | 61.71 | 58.91 | D - Other node or line within 3 km | 1.83 | 2.62 | Node: SUB001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1304
2 | 305 | 1305 | 0702207030 | Region VII (Central Visayas) | Cebu | Badian | Zaragosa | 9.882 | 123.3825 | R | 2105 | 3.8 | 554 | 166 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.44 | 1.94 | Tier 1B: High GIDA Priority | 55.85 | 55.85 | 61.98 | 58.91 | D - Other node or line within 3 km | 6.44 | 1.94 | Line: Segment 6 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1305
2 | 306 | 1306 | 0506210026 | Region V (Bicol Region) | Sorsogon | Juban | Tinago | 12.8523 | 123.94 | R | 934 | 4 | 234 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.31 | 3.14 | Tier 1B: High GIDA Priority | 48.33 | 48.33 | 69.5 | 58.91 | D - Other node or line within 3 km | 8.31 | 2.99 | Line: 28,000 m | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1306
2 | 307 | 1307 | 1102504018 | Region XI (Davao Region) | Davao Oriental | Caraga | Sobrecarey | 7.3551 | 126.3894 | U | 5177 | 3.6 | 1438 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.24 | 48.18 | Tier 1B: High GIDA Priority | 45.42 | 45.42 | 72.41 | 58.91 | F - Nearest node and line over 5 km | 48.24 | 56.96 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1307
2 | 308 | 1308 | 0405814001 | Region IV-A (CALABARZON) | Rizal | Teresa | Bagumbayan | 14.5499 | 121.2184 | U | 15588 | 3.6 | 4330 | 1299 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.42 | 0.11 | Tier 2A: High Commercial ROI | 73.78 | 73.78 | 44.03 | 58.9 | A - Node within 0.5 km | 0.42 | 0.01 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1308
2 | 309 | 1309 | 0702234027 | Region VII (Central Visayas) | Cebu | City of Naga | Tuyan | 10.2299 | 123.7682 | U | 13748 | 3.8 | 3618 | 1085 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.85 | 0.22 | Tier 2A: High Commercial ROI | 72.76 | 72.76 | 45.04 | 58.9 | B - Node 0.5-1 km | 0.87 | 0.03 | Line: CEBU - TOLEDO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1309
2 | 310 | 1310 | 1381600017 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Malinta | 14.6911 | 120.9658 | U | 53486 | 3.64 | 14697 | 4409 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.2 | 0.18 | Tier 1B: High GIDA Priority | 55.17 | 55.17 | 62.62 | 58.9 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.16 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1310
2 | 311 | 1311 | 0401005101 | Region IV-A (CALABARZON) | Batangas | Batangas City | Simlong | 13.6671 | 121.0544 | U | 4312 | 3.6 | 1198 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 9.91 | Tier 1B: High GIDA Priority | 57.28 | 57.28 | 60.49 | 58.89 | D - Other node or line within 3 km | 2.39 | 9.91 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1311
2 | 312 | 1312 | 0504102007 | Region V (Bicol Region) | Masbate | Baleno | Canjunday | 12.3988 | 123.5189 | R | 838 | 4.1 | 204 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.62 | 0.17 | Tier 1B: High GIDA Priority | 50.78 | 50.78 | 66.99 | 58.89 | F - Nearest node and line over 5 km | 8.62 | 9.35 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1312
2 | 313 | 1313 | 0301402009 | Region III (Central Luzon) | Bulacan | Balagtas | San Juan | 14.8103 | 120.9051 | U | 9841 | 3.5 | 2812 | 844 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.31 | 0.8 | Tier 2B: Moderate GIDA Inclusion | 64.76 | 64.76 | 52.99 | 58.88 | D - Other node or line within 3 km | 3.31 | 0.8 | Line: BALAGTAS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1313
2 | 314 | 1314 | 0301403001 | Region III (Central Luzon) | Bulacan | Baliuag | Bagong Nayon | 14.9597 | 120.8988 | U | 4441 | 3.5 | 1269 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 62.2 | 62.2 | 55.57 | 58.88 | C - Line within 0.5 km; node over 1 km | 1.74 | 0.43 | Line: SanLuis-Candaba Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1314
2 | 315 | 1315 | 0702232012 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward III | 10.2675 | 123.7949 | U | 2742 | 3.8 | 722 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 2.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 52.27 | 52.27 | 65.48 | 58.88 | D - Other node or line within 3 km | 2.23 | 2.13 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1315
2 | 316 | 1316 | 0402104016 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 5 | 14.3113 | 121.0398 | R | 560 | 3.4 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.22 | 1.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.27 | 51.27 | 66.49 | 58.88 | A - Node within 0.5 km | 0.22 | 1.1 | Node: CRC002 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1316
2 | 317 | 1317 | 0205002022 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Ocao-Capiniaan | 16.2029 | 121.0051 | R | 1053 | 3.8 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.8 | 3.83 | Tier 1B: High GIDA Priority | 41.77 | 41.77 | 76 | 58.88 | E - Nearest node or line 3-5 km | 8.8 | 3.83 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1317
2 | 318 | 1318 | 0702219016 | Region VII (Central Visayas) | Cebu | Consolacion | Pulpogan | 10.3862 | 123.9567 | U | 15032 | 3.8 | 3956 | 1187 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.1 | 1.12 | Tier 2A: High Commercial ROI | 73.16 | 73.16 | 44.58 | 58.87 | D - Other node or line within 3 km | 1.1 | 0.94 | Line: Route 11.925km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1318
2 | 319 | 1319 | 0402116012 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose II | 14.4318 | 120.8864 | R | 1941 | 3.4 | 571 | 171 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.44 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 61.8 | 61.8 | 55.93 | 58.87 | A - Node within 0.5 km | 0.44 | 0.14 | Line: NOVELETA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1319
2 | 320 | 1320 | 1380602007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 293 | 13.8614 | 120.7669 | U | 3708 | 3.22 | 1150 | 345 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.79 | 8.71 | Tier 1B: High GIDA Priority | 47.34 | 47.34 | 70.41 | 58.87 | F - Nearest node and line over 5 km | 8.79 | 8.71 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1320
2 | 321 | 1321 | 0301416001 | Region III (Central Luzon) | Bulacan | Paombong | Binakod | 14.7825 | 120.785 | R | 1971 | 3.5 | 563 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.36 | 8.35 | Tier 1B: High GIDA Priority | 51.94 | 51.94 | 65.77 | 58.86 | F - Nearest node and line over 5 km | 5.36 | 8.42 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1321
2 | 322 | 1322 | 0201524005 | Region II (Cagayan Valley) | Cagayan | Santa Praxedes | Macatel | 18.5444 | 121.0041 | R | 151 | 3.9 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.28 | 0.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 51.28 | 51.28 | 66.44 | 58.86 | C - Line within 0.5 km; node over 1 km | 2.28 | 0.14 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1322
2 | 323 | 1323 | 0301412002 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bahay Pare | 14.7672 | 121.0105 | U | 13831 | 3.5 | 3952 | 1186 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.8 | 1.78 | Tier 2A: High Commercial ROI | 70.27 | 70.27 | 47.43 | 58.85 | D - Other node or line within 3 km | 1.8 | 1.77 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1323
2 | 324 | 1324 | 0501705012 | Region V (Bicol Region) | Camarines Sur | Buhi | Ibayugan | 13.487 | 123.5195 | R | 1957 | 4.2 | 466 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.91 | 7.59 | Tier 1B: High GIDA Priority | 49.58 | 49.58 | 68.12 | 58.85 | F - Nearest node and line over 5 km | 7.91 | 7.59 | Line: SAGNAY - PATITINAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1324
2 | 325 | 1325 | 1403214008 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Upper Lubo | 17.2946 | 121.2913 | R | 333 | 4.3 | 77 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.51 | 12.01 | Tier 1B: High GIDA Priority | 37.65 | 37.65 | 80.06 | 58.85 | F - Nearest node and line over 5 km | 15.51 | 12 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1325
2 | 326 | 1326 | 1381300087 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-C | 14.609 | 121.0407 | U | 3312 | 3.56 | 931 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 0.23 | Tier 1B: High GIDA Priority | 55.64 | 55.64 | 62.05 | 58.84 | D - Other node or line within 3 km | 2.2 | 0.81 | Line: UG 144C via W-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1326
2 | 327 | 1327 | 1004317024 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Tama | 8.9741 | 125.1993 | R | 783 | 3.9 | 201 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.37 | 1.65 | Tier 1B: High GIDA Priority | 51.79 | 51.79 | 65.9 | 58.84 | D - Other node or line within 3 km | 5.37 | 1.64 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1327
2 | 328 | 1328 | 0103315016 | Region I (Ilocos Region) | La Union | San Gabriel | Lipay Sur | 16.7061 | 120.4446 | R | 1000 | 3.7 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.18 | 7.6 | Tier 1B: High GIDA Priority | 48.12 | 48.12 | 69.55 | 58.84 | F - Nearest node and line over 5 km | 6.18 | 7.6 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1328
2 | 329 | 1329 | 1003511013 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Pangao | 8.0337 | 123.8872 | R | 1060 | 4.2 | 252 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.74 | 7.58 | Tier 1B: High GIDA Priority | 46.11 | 46.11 | 71.56 | 58.84 | F - Nearest node and line over 5 km | 9.74 | 7.58 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1329
2 | 330 | 1330 | 0300809012 | Region III (Central Luzon) | Bataan | Orani | Palihan | 14.7934 | 120.5183 | R | 2633 | 3.6 | 731 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.17 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 63.13 | 63.13 | 54.54 | 58.83 | D - Other node or line within 3 km | 2.17 | 0.62 | Line: 96C DONA TO ORANI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1330
2 | 331 | 1331 | 1206302013 | Region XII (SOCCSKSARGEN) | South Cotabato | Banga | Lampari | 6.2907 | 124.8897 | R | 2769 | 3.6 | 769 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.93 | 10.59 | Tier 1B: High GIDA Priority | 56.26 | 56.26 | 61.39 | 58.83 | F - Nearest node and line over 5 km | 7.93 | 10.59 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1331
2 | 332 | 1332 | 1381300001 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Alicia | 14.66 | 121.0491 | U | 6298 | 3.86 | 1631 | 489 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 60.7 | 60.7 | 56.95 | 58.82 | B - Node 0.5-1 km | 0.56 | 0.24 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1332
2 | 333 | 1333 | 1380605078 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 375 | 13.1241 | 123.1956 | U | 4466 | 4.75 | 941 | 282 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.6 | 31.46 | Tier 1B: High GIDA Priority | 44.82 | 44.82 | 72.83 | 58.82 | F - Nearest node and line over 5 km | 10.6 | 31.41 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1333
2 | 334 | 1334 | 1381000005 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Santo Niño | 14.5033 | 120.9962 | U | 33329 | 3.05 | 10915 | 3274 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.84 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 60.56 | 60.56 | 57.05 | 58.81 | B - Node 0.5-1 km | 0.84 | 0.3 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 1334
2 | 335 | 1335 | 0305415011 | Region III (Central Luzon) | Pampanga | Porac | Diaz | 15.0509 | 120.5456 | R | 470 | 4 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 1.04 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48 | 48 | 69.62 | 58.81 | D - Other node or line within 3 km | 1.5 | 1.04 | Line: 48 CORE (4X12) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1335
2 | 336 | 1336 | 1907002005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Ipil | 14.4929 | 121.6792 | R | 1713 | 5.8 | 295 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.6 | 24.2 | Tier 1B: High GIDA Priority | 43.19 | 43.19 | 74.42 | 58.81 | F - Nearest node and line over 5 km | 5.6 | 24.2 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1336
2 | 337 | 1337 | 0603030036 | Region VI (Western Visayas) | Iloilo | Miagao | Dalije | 10.6788 | 122.1669 | R | 1651 | 3.8 | 434 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.41 | 6.02 | Tier 1B: High GIDA Priority | 39.91 | 39.91 | 77.72 | 58.81 | F - Nearest node and line over 5 km | 23.41 | 6.01 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1337
2 | 338 | 1338 | 1381100162 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 162 | 14.5353 | 121.0065 | U | 2062 | 3.41 | 605 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.62 | 48.62 | 68.99 | 58.8 | C - Line within 0.5 km; node over 1 km | 1.3 | 0.31 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1338
2 | 339 | 1339 | 0205706015 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Wasid | 16.1368 | 121.5388 | R | 1278 | 3.9 | 328 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.94 | 18.04 | Tier 1B: High GIDA Priority | 40.93 | 40.93 | 76.66 | 58.8 | F - Nearest node and line over 5 km | 10.94 | 18.01 | Node: NTQ001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1339
2 | 340 | 1340 | 0300803009 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang West | 14.6717 | 120.5286 | R | 2122 | 3.6 | 589 | 177 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 1.52 | Tier 1B: High GIDA Priority | 59.78 | 59.78 | 57.79 | 58.79 | D - Other node or line within 3 km | 1.88 | 1.52 | Line: Bagac-Pilar AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1340
2 | 341 | 1341 | 0103319006 | Region I (Ilocos Region) | La Union | Sudipen | Maliclico | 16.5102 | 120.2936 | R | 850 | 3.7 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.54 | 3.92 | Tier 1B: High GIDA Priority | 48.01 | 48.01 | 69.57 | 58.79 | E - Nearest node or line 3-5 km | 4.54 | 3.91 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1341
2 | 342 | 1342 | 1705304006 | MIMAROPA Region | Palawan | Balabac | Catagupan | 7.9807 | 116.9719 | R | 3106 | 3.9 | 796 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 275.24 | 999 | Tier 1B: High GIDA Priority | 46.51 | 46.51 | 71.03 | 58.77 | F - Nearest node and line over 5 km | 275.24 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1342
2 | 343 | 1343 | 0806010015 | Region VIII (Eastern Visayas) | Samar | Marabut | Amantillo | 11.108 | 125.215 | R | 628 | 4.1 | 153 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.28 | 20.16 | Tier 1B: High GIDA Priority | 38.65 | 38.65 | 78.89 | 58.77 | F - Nearest node and line over 5 km | 21.28 | 24.49 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1343
2 | 344 | 1344 | 0403404013 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pulo | 14.2139 | 121.2855 | U | 38490 | 3.3 | 11664 | 3499 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 3.71 | 3.82 | Tier 1B: High GIDA Priority | 55.74 | 55.74 | 61.78 | 58.76 | E - Nearest node or line 3-5 km | 3.71 | 3.82 | Node: BAY001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1344
2 | 345 | 1345 | 1400121013 | Cordillera Administrative Region (CAR) | Abra | San Isidro | Tangbao | 17.4432 | 120.5941 | R | 650 | 3.8 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.26 | 10.57 | Tier 1B: High GIDA Priority | 45.58 | 45.58 | 71.93 | 58.76 | F - Nearest node and line over 5 km | 7.26 | 10.56 | Node: NKI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1345
2 | 346 | 1346 | 1907005004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Sitangkai Poblacion | 17.2558 | 122.2299 | R | 4093 | 5.8 | 706 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 43.08 | 43.08 | 74.45 | 58.76 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1346
2 | 347 | 1347 | 0201505025 | Region II (Cagayan Valley) | Cagayan | Aparri | Fuga Island | 18.8861 | 121.4133 | R | 1994 | 3.9 | 511 | 153 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.94 | 39.47 | Tier 1B: High GIDA Priority | 38.91 | 38.91 | 78.62 | 58.76 | F - Nearest node and line over 5 km | 40.94 | 999999 | Node: SMC001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1347
2 | 348 | 1348 | 0806010021 | Region VIII (Eastern Visayas) | Samar | Marabut | Panan-awan | 11.1831 | 125.2064 | R | 386 | 4.1 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.74 | 20.49 | Tier 1B: High GIDA Priority | 38.54 | 38.54 | 78.98 | 58.76 | F - Nearest node and line over 5 km | 21.74 | 21.71 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1348
2 | 349 | 1349 | 0405804035 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tatala | 14.4829 | 121.205 | U | 15462 | 3.6 | 4295 | 1288 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.96 | 0.76 | Tier 2A: High Commercial ROI | 72.66 | 72.66 | 44.83 | 58.75 | B - Node 0.5-1 km | 0.96 | 0.75 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 1349
2 | 350 | 1350 | 1381100077 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 77 | 14.6348 | 120.9866 | U | 1750 | 2.85 | 614 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.36 | 48.36 | 69.14 | 58.75 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.46 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1350
2 | 351 | 1351 | 0403428010 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Malitlit | 14.2682 | 121.1133 | U | 30071 | 3.3 | 9112 | 2734 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.61 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 63.83 | 63.83 | 53.66 | 58.74 | D - Other node or line within 3 km | 2.61 | 0.98 | Line: BINAN - CABUYAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1351
2 | 352 | 1352 | 1403214006 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Taloctoc | 17.2904 | 121.3014 | R | 365 | 4.3 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.46 | 12.4 | Tier 1B: High GIDA Priority | 37.19 | 37.19 | 80.29 | 58.74 | F - Nearest node and line over 5 km | 16.46 | 12.39 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1352
2 | 353 | 1353 | 1380608012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 670 | 11.6997 | 122.3384 | U | 2904 | 3.13 | 929 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.78 | Tier 1B: High GIDA Priority | 57.22 | 57.22 | 60.24 | 58.73 | D - Other node or line within 3 km | 1.23 | 2.92 | Node: NUK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1353
2 | 354 | 1354 | 1381200012 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Maybunga | 14.5786 | 121.0837 | U | 50069 | 3.11 | 16117 | 4835 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.31 | 0.24 | Tier 1B: High GIDA Priority | 55.17 | 55.17 | 62.3 | 58.73 | A - Node within 0.5 km | 0.31 | 0.17 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1354
2 | 355 | 1355 | 1908705019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Labungan | 17.2539 | 122.2279 | R | 6968 | 4.3 | 1620 | 486 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 51.13 | 51.13 | 66.34 | 58.73 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1355
2 | 356 | 1356 | 1380601055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 55 | 13.9628 | 121.1325 | U | 2427 | 4.22 | 575 | 172 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 1.98 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.63 | 46.63 | 70.82 | 58.72 | D - Other node or line within 3 km | 1.98 | 1.98 | Line: UG_LPB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1356
2 | 357 | 1357 | 0103305019 | Region I (Ilocos Region) | La Union | Balaoan | Nagsabaran Sur | 16.7785 | 120.3842 | R | 1223 | 3.7 | 331 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.42 | 2.23 | Tier 1B: High GIDA Priority | 46.31 | 46.31 | 71.14 | 58.72 | D - Other node or line within 3 km | 4.42 | 2.22 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1357
2 | 358 | 1358 | 0603002035 | Region VI (Western Visayas) | Iloilo | Alimodian | Manasa | 10.7565 | 122.3908 | R | 162 | 3.8 | 43 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.66 | 1.31 | Tier 1B: High GIDA Priority | 45.17 | 45.17 | 72.26 | 58.72 | D - Other node or line within 3 km | 8.66 | 1.3 | Line: 17,509 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1358
2 | 359 | 1359 | 1907010023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tup-tup Banaran | 16.3056 | 122.0697 | R | 1649 | 5.8 | 284 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.6 | 4.82 | Tier 1B: High GIDA Priority | 42.5 | 42.5 | 74.95 | 58.72 | F - Nearest node and line over 5 km | 6.6 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1359
2 | 360 | 1360 | 1381100010 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 10 | 14.5481 | 120.9877 | U | 1427 | 2.94 | 485 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.6 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.57 | 46.57 | 70.85 | 58.71 | B - Node 0.5-1 km | 0.72 | 0.59 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 1360
2 | 361 | 1361 | 0102903035 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Barangay 6 | 17.5923 | 120.4094 | R | 500 | 3.8 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.26 | 47.26 | 70.14 | 58.7 | D - Other node or line within 3 km | 2.02 | 0.58 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1361
2 | 362 | 1362 | 0401005012 | Region IV-A (CALABARZON) | Batangas | Batangas City | Bolbok | 13.7741 | 121.046 | U | 13167 | 3.6 | 3658 | 1097 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.66 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 69.47 | 69.47 | 47.91 | 58.69 | C - Line within 0.5 km; node over 1 km | 1.66 | 0.07 | Line: WP BYB001 TO BCY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1362
2 | 363 | 1363 | 0307708008 | Region III (Central Luzon) | Aurora | San Luis | Dibut | 15.6676 | 121.5981 | R | 577 | 3.8 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11 | 10.83 | Tier 1B: High GIDA Priority | 36.21 | 36.21 | 81.18 | 58.69 | F - Nearest node and line over 5 km | 11 | 10.83 | Line: SEGMENT 49 (DIPACULAO - BALER) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1363
2 | 364 | 1364 | 0307708010 | Region III (Central Luzon) | Aurora | San Luis | Dimanayat | 15.5277 | 121.4959 | R | 978 | 3.8 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.13 | 23.79 | Tier 1B: High GIDA Priority | 34.82 | 34.82 | 82.57 | 58.69 | F - Nearest node and line over 5 km | 18.13 | 23.43 | Node: GBN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1364
2 | 365 | 1365 | 0403404011 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Niugan | 14.2383 | 121.2797 | U | 42286 | 3.3 | 12814 | 3844 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 6.38 | 6.52 | Tier 1B: High GIDA Priority | 52.45 | 52.45 | 64.9 | 58.68 | F - Nearest node and line over 5 km | 6.38 | 6.52 | Node: BAY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1365
2 | 366 | 1366 | 0304918001 | Region III (Central Luzon) | Nueva Ecija | Nampicuan | Alemania | 15.7088 | 120.6643 | R | 134 | 3.5 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.87 | 8.94 | Tier 1B: High GIDA Priority | 43.46 | 43.46 | 73.9 | 58.68 | F - Nearest node and line over 5 km | 7.87 | 8.98 | Node: CYN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1366
2 | 367 | 1367 | 1380610007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 692 | 13.6072 | 122.1625 | U | 2508 | 2 | 1257 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.55 | 7.53 | Tier 1B: High GIDA Priority | 46.8 | 46.8 | 70.53 | 58.67 | F - Nearest node and line over 5 km | 9.55 | 7.51 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1367
2 | 368 | 1368 | 0603034020 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion East | 10.6914 | 122.4787 | R | 4302 | 3.8 | 1132 | 340 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.23 | Tier 2A: High Commercial ROI | 75.26 | 75.26 | 42.05 | 58.66 | A - Node within 0.5 km | 0.24 | 0.09 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1368
2 | 369 | 1369 | 1403209005 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ba-ay | 17.4833 | 121.2753 | R | 525 | 4.3 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.75 | 7.8 | Tier 1B: High GIDA Priority | 36.42 | 36.42 | 80.9 | 58.66 | F - Nearest node and line over 5 km | 10.75 | 7.78 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1369
2 | 370 | 1370 | 0405809002 | Region IV-A (CALABARZON) | Rizal | Morong | Can-Cal-Lan | 14.5271 | 121.2499 | R | 4707 | 3.6 | 1308 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 0.13 | Tier 2A: High Commercial ROI | 70.36 | 70.36 | 46.94 | 58.65 | C - Line within 0.5 km; node over 1 km | 1.29 | 0.08 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1370
2 | 371 | 1371 | 1108602014 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Culaman | 5.9597 | 125.6613 | R | 3519 | 3.6 | 978 | 293 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.36 | 53.95 | Tier 1B: High GIDA Priority | 50.99 | 50.99 | 66.28 | 58.64 | F - Nearest node and line over 5 km | 45.36 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1371
2 | 372 | 1372 | 1908713006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Bungcog | 17.254 | 122.2281 | R | 5316 | 4.3 | 1236 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 50 | 50 | 67.28 | 58.64 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1372
2 | 373 | 1373 | 1380614010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 753 | 13.8494 | 121.0107 | U | 2531 | 3.7 | 684 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 1.79 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.36 | 48.36 | 68.92 | 58.64 | D - Other node or line within 3 km | 2.8 | 1.79 | Line: UG BUN001 TO SSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1373
2 | 374 | 1374 | 1381100037 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 37 | 14.5066 | 121.0424 | U | 1568 | 3.02 | 519 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.01 | 46.01 | 71.27 | 58.64 | D - Other node or line within 3 km | 1.5 | 0.64 | Line: Existing 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1374
2 | 375 | 1375 | 0501711033 | Region V (Bicol Region) | Camarines Sur | Caramoan | Pagolinan | 13.7175 | 123.8505 | R | 467 | 4.2 | 111 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.46 | 33.94 | Tier 1B: High GIDA Priority | 43.43 | 43.43 | 73.85 | 58.64 | F - Nearest node and line over 5 km | 6.46 | 33.94 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1375
2 | 376 | 1376 | 1380300025 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | San Lorenzo | 14.545 | 121.04 | U | 14793 | 3.02 | 4894 | 1468 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.69 | 1.24 | Tier 2B: Moderate GIDA Inclusion | 66.55 | 66.55 | 50.7 | 58.63 | D - Other node or line within 3 km | 1.69 | 1.42 | Line: RELIANCE PSG001 TO BÑL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1376
2 | 377 | 1377 | 1381100148 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 148 | 14.7168 | 120.9376 | U | 2077 | 3.28 | 634 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 2.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.71 | 46.71 | 70.56 | 58.63 | B - Node 0.5-1 km | 0.82 | 2.1 | Node: OBB001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 1377
2 | 378 | 1378 | 1908709011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Limbayan | 17.2541 | 122.2282 | R | 5270 | 4.3 | 1226 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.97 | 49.97 | 67.27 | 58.62 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1378
2 | 379 | 1379 | 1381100133 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 133 | 14.577 | 121.1721 | U | 2140 | 3.81 | 561 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.56 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.67 | 47.67 | 69.58 | 58.62 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.37 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1379
2 | 380 | 1380 | 1908816005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Galakit | 7.0696 | 124.7099 | R | 2798 | 4.7 | 595 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.63 | 11.85 | Tier 1B: High GIDA Priority | 42.51 | 42.51 | 74.74 | 58.62 | F - Nearest node and line over 5 km | 17.63 | 11.72 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1380
2 | 381 | 1381 | 0301404013 | Region III (Central Luzon) | Bulacan | Bocaue | Lolomboy | 14.7794 | 120.9337 | U | 15091 | 3.5 | 4312 | 1294 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.2 | 0.26 | Tier 2A: High Commercial ROI | 74.38 | 74.38 | 42.83 | 58.61 | A - Node within 0.5 km | 0.2 | 0.25 | Node: BOB001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1381
2 | 382 | 1382 | 0307708007 | Region III (Central Luzon) | Aurora | San Luis | Dibayabay | 15.6338 | 121.583 | R | 746 | 3.8 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.53 | 14.13 | Tier 1B: High GIDA Priority | 35.45 | 35.45 | 81.76 | 58.61 | F - Nearest node and line over 5 km | 13.53 | 14.12 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1382
2 | 383 | 1383 | 0403420007 | Region IV-A (CALABARZON) | Laguna | Pakil | Gonzales | 14.3847 | 121.4769 | R | 2865 | 3.3 | 868 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.12 | Tier 2A: High Commercial ROI | 74.01 | 74.01 | 43.18 | 58.6 | B - Node 0.5-1 km | 0.63 | 0.07 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1383
2 | 384 | 1384 | 1380300002 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Bel-Air | 14.5559 | 121.0373 | U | 39354 | 3.8 | 10363 | 3109 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.22 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 60.53 | 60.53 | 56.67 | 58.6 | D - Other node or line within 3 km | 1.22 | 1.19 | Line: UG 144C via V-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1384
2 | 385 | 1385 | 1381100108 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 108 | 14.4743 | 120.8846 | U | 2094 | 3.49 | 600 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 4.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.85 | 46.85 | 70.33 | 58.59 | A - Node within 0.5 km | 0.33 | 4.49 | Node: CVC001 -TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1385
2 | 386 | 1386 | 1907001003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Buan | 17.2557 | 122.2297 | R | 4393 | 5.8 | 757 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 44.39 | 44.39 | 72.8 | 58.59 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1386
2 | 387 | 1387 | 1380603007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 387 | 14.0614 | 121.2719 | U | 2678 | 4.2 | 637 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.28 | 0.07 | Tier 1B: High GIDA Priority | 44.85 | 44.85 | 72.31 | 58.58 | C - Line within 0.5 km; node over 1 km | 5.28 | 0.07 | Line: STO. TOMAS - CANDELARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1387
2 | 388 | 1388 | 0604528042 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 3 | 10.7437 | 122.9634 | U | 6901 | 3.7 | 1865 | 560 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.15 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 69.8 | 69.8 | 47.33 | 58.57 | B - Node 0.5-1 km | 0.58 | 0.05 | Line: FH TALISAY, NEGROS OCCIDENTAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 1388
2 | 389 | 1389 | 0402120037 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan III | 14.3826 | 120.8238 | R | 2229 | 3.4 | 656 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 1.05 | Tier 2B: Moderate GIDA Inclusion | 62.31 | 62.31 | 54.83 | 58.57 | D - Other node or line within 3 km | 1.41 | 1.05 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1389
2 | 390 | 1390 | 1907004012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Panglima Mastul | 17.2558 | 122.2299 | R | 2029 | 5.8 | 350 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 38.24 | 38.24 | 78.9 | 58.57 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1390
2 | 391 | 1391 | 0301409026 | Region III (Central Luzon) | Bulacan | Hagonoy | Tibaguin | 14.7737 | 120.7522 | R | 3449 | 3.5 | 985 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.29 | 9.77 | Tier 2B: Moderate GIDA Inclusion | 60.73 | 60.73 | 56.39 | 58.56 | F - Nearest node and line over 5 km | 7.29 | 11.12 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1391
2 | 392 | 1392 | 0506207015 | Region V (Bicol Region) | Sorsogon | Donsol | Girawan | 12.9348 | 123.5873 | R | 375 | 4 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 16.58 | Tier 1B: High GIDA Priority | 45.6 | 45.6 | 71.53 | 58.56 | E - Nearest node or line 3-5 km | 3.38 | 16.41 | Node: DLS001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1392
2 | 393 | 1393 | 1102401021 | Region XI (Davao Region) | Davao del Sur | Bansalan | Sibayan | 6.8362 | 125.2508 | R | 733 | 3.4 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.02 | 14.16 | Tier 1B: High GIDA Priority | 43.5 | 43.5 | 73.61 | 58.56 | F - Nearest node and line over 5 km | 7.02 | 14.13 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1393
2 | 394 | 1394 | 0600409009 | Region VI (Western Visayas) | Aklan | Libacao | Dalagsa-an | 11.2802 | 122.2721 | R | 2150 | 3.9 | 551 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.8 | 31.46 | Tier 1B: High GIDA Priority | 41.49 | 41.49 | 75.64 | 58.56 | F - Nearest node and line over 5 km | 32.8 | 32.68 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1394
2 | 395 | 1395 | 1381600026 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pulo | 14.7014 | 120.9662 | U | 1147 | 3.36 | 341 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.06 | 42.06 | 75.04 | 58.55 | C - Line within 0.5 km; node over 1 km | 1.07 | 0.41 | Line: Mnla Pipe | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1395
2 | 396 | 1396 | 1403214005 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Mangali | 17.3079 | 121.2301 | R | 262 | 4.3 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.93 | 6.9 | Tier 1B: High GIDA Priority | 41.71 | 41.71 | 75.38 | 58.55 | F - Nearest node and line over 5 km | 9.93 | 6.83 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1396
2 | 397 | 1397 | 1380601029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 29 | 11.8636 | 120.7317 | U | 4422 | 4.31 | 1027 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.88 | 65.15 | Tier 1B: High GIDA Priority | 41.14 | 41.14 | 75.97 | 58.55 | F - Nearest node and line over 5 km | 54.88 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1397
2 | 398 | 1398 | 0603023006 | Region VI (Western Visayas) | Iloilo | Janiuay | Atimonan | 11.0512 | 122.3587 | R | 1066 | 3.8 | 281 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.57 | 19.31 | Tier 1B: High GIDA Priority | 37.11 | 37.11 | 80 | 58.55 | F - Nearest node and line over 5 km | 20.57 | 19.29 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1398
2 | 399 | 1399 | 0401006022 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Proper | 13.7944 | 120.9978 | U | 11200 | 3.6 | 3111 | 933 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 69.83 | 69.83 | 47.26 | 58.54 | B - Node 0.5-1 km | 0.55 | 0.28 | Line: BAUAN - SAN JOSE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1399
2 | 400 | 1400 | 1102508016 | Region XI (Davao Region) | Davao Oriental | Manay | New Taokanga | 7.2635 | 126.3908 | R | 3025 | 3.6 | 840 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.26 | 38.83 | Tier 1B: High GIDA Priority | 47.78 | 47.78 | 69.29 | 58.54 | F - Nearest node and line over 5 km | 39.26 | 51.66 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1400
2 | 401 | 1401 | 0403405036 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Pansol | 14.1804 | 121.1791 | U | 12741 | 3.3 | 3861 | 1158 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.02 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 67.11 | 67.11 | 49.95 | 58.53 | C - Line within 0.5 km; node over 1 km | 4.02 | 0.05 | Line: CLB001 TO SCL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1401
2 | 402 | 1402 | 1908707001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bayanga Norte | 17.254 | 122.228 | R | 9210 | 4.3 | 2142 | 643 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 52.67 | 52.67 | 64.38 | 58.53 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1402
2 | 403 | 1403 | 1380611049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 687 | 13.5262 | 122.3817 | U | 2106 | 3.92 | 537 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 0.95 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.53 | 46.53 | 70.54 | 58.53 | D - Other node or line within 3 km | 1.45 | 0.95 | Line: UNISAN TO MULANAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1403
2 | 404 | 1404 | 1380601129 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 129 | 11.6416 | 122.5831 | U | 5207 | 3.77 | 1380 | 414 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.68 | 9.79 | Tier 1B: High GIDA Priority | 43.15 | 43.15 | 73.91 | 58.53 | F - Nearest node and line over 5 km | 15.91 | 15.28 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1404
2 | 405 | 1405 | 0301407014 | Region III (Central Luzon) | Bulacan | Calumpit | Iba O'Este | 14.8896 | 120.7641 | U | 14723 | 3.5 | 4207 | 1262 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.9 | 1.52 | Tier 2A: High Commercial ROI | 70.88 | 70.88 | 46.17 | 58.52 | D - Other node or line within 3 km | 1.9 | 1.5 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1405
2 | 406 | 1406 | 0402117002 | Region IV-A (CALABARZON) | Cavite | Rosario | Bagbag I | 14.4235 | 120.8678 | U | 6350 | 3.4 | 1868 | 560 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 1.65 | Tier 2B: Moderate GIDA Inclusion | 63.77 | 63.77 | 53.26 | 58.52 | D - Other node or line within 3 km | 1.77 | 1.65 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1406
2 | 407 | 1407 | 1403215006 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Belong Manubal | 17.2977 | 121.1341 | R | 495 | 4.3 | 115 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.08 | 2.44 | Tier 1B: High GIDA Priority | 46.32 | 46.32 | 70.71 | 58.52 | D - Other node or line within 3 km | 4.08 | 2.39 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1407
2 | 408 | 1408 | 0806417004 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Cabadbaran | 10.4039 | 124.9396 | R | 220 | 4.1 | 54 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.08 | 4.37 | Tier 1B: High GIDA Priority | 44.12 | 44.12 | 72.91 | 58.52 | F - Nearest node and line over 5 km | 32.46 | 18.33 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1408
2 | 409 | 1409 | 0301420056 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz IV | 14.8581 | 121.0847 | R | 3319 | 3.5 | 948 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 5.48 | Tier 2B: Moderate GIDA Inclusion | 66.15 | 66.15 | 50.87 | 58.51 | D - Other node or line within 3 km | 1.2 | 7.21 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1409
2 | 410 | 1410 | 0603027031 | Region VI (Western Visayas) | Iloilo | Lemery | Yawyawan | 11.2754 | 122.8745 | R | 626 | 3.8 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.08 | 7.96 | Tier 1B: High GIDA Priority | 47.13 | 47.13 | 69.89 | 58.51 | F - Nearest node and line over 5 km | 8.08 | 7.96 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1410
2 | 411 | 1411 | 1403201005 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Buaya | 17.5793 | 121.2572 | R | 981 | 4.3 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.19 | 16.38 | Tier 1B: High GIDA Priority | 40.44 | 40.44 | 76.58 | 58.51 | F - Nearest node and line over 5 km | 9.19 | 16.36 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1411
2 | 412 | 1412 | 1403213027 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Naneng | 17.4054 | 121.2692 | R | 734 | 4.3 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18 | 0.7 | Tier 1B: High GIDA Priority | 36.52 | 36.52 | 80.47 | 58.5 | D - Other node or line within 3 km | 18 | 0.66 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1412
2 | 413 | 1413 | 1380612034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 867 | 14.0113 | 121.6212 | U | 2396 | 4.45 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.29 | 1.48 | Tier 1B: High GIDA Priority | 44.02 | 44.02 | 72.96 | 58.49 | D - Other node or line within 3 km | 3.29 | 1.46 | Line: AE LCQ001 TO TYQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1413
2 | 414 | 1414 | 1108602035 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Tanuman | 5.7478 | 125.5108 | R | 2420 | 3.6 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.33 | 54.63 | Tier 1B: High GIDA Priority | 43.6 | 43.6 | 73.38 | 58.49 | F - Nearest node and line over 5 km | 47.33 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1414
2 | 415 | 1415 | 0301403030 | Region III (Central Luzon) | Bulacan | Baliuag | Virgen delas Flores | 14.9458 | 120.886 | U | 7686 | 3.5 | 2196 | 659 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 67.68 | 67.68 | 49.29 | 58.48 | A - Node within 0.5 km | 0.33 | 0.3 | Line: 24 CORE (3X8) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1415
2 | 416 | 1416 | 0402108031 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Bacao II | 14.4052 | 120.8832 | U | 9416 | 3.4 | 2769 | 831 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.4 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 65.6 | 65.6 | 51.36 | 58.48 | D - Other node or line within 3 km | 2.4 | 0.6 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1416
2 | 417 | 1417 | 0405607067 | Region IV-A (CALABARZON) | Quezon | Calauag | Sabang II | 13.9568 | 122.2808 | R | 3981 | 3.8 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.47 | Tier 2A: High Commercial ROI | 70.72 | 70.72 | 46.22 | 58.47 | B - Node 0.5-1 km | 0.68 | 0.44 | Line: WP CLQ001 TO MLQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1417
2 | 418 | 1418 | 1381100044 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 44 | 14.5567 | 120.9971 | U | 1506 | 3.27 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.93 | 45.93 | 71.01 | 58.47 | B - Node 0.5-1 km | 0.69 | 0.23 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1418
2 | 419 | 1419 | 1102505001 | Region XI (Davao Region) | Davao Oriental | Cateel | Abijod | 7.7822 | 126.4154 | R | 2136 | 3.6 | 593 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.89 | 38.55 | Tier 1B: High GIDA Priority | 41.78 | 41.78 | 75.17 | 58.47 | F - Nearest node and line over 5 km | 39.89 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1419
2 | 420 | 1420 | 0806002005 | Region VIII (Eastern Visayas) | Samar | Basey | Basiao | 11.2614 | 125.1613 | R | 1455 | 4.1 | 355 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.43 | 16.6 | Tier 1B: High GIDA Priority | 39.78 | 39.78 | 77.16 | 58.47 | F - Nearest node and line over 5 km | 17.43 | 17.44 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1420
2 | 421 | 1421 | 0305405028 | Region III (Central Luzon) | Pampanga | Candaba | Salapungan | 15.1381 | 120.9345 | U | 5325 | 4 | 1331 | 399 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.17 | 2.28 | Tier 1B: High GIDA Priority | 56.92 | 56.92 | 60 | 58.46 | D - Other node or line within 3 km | 3.17 | 2.27 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1421
2 | 422 | 1422 | 1381100110 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 110 | 14.4178 | 121.063 | U | 2260 | 3.87 | 584 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 1.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.24 | 47.24 | 69.69 | 58.46 | D - Other node or line within 3 km | 1.76 | 1.39 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1422
2 | 423 | 1423 | 1381100007 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 7 | 14.5349 | 120.9918 | U | 1617 | 3.11 | 520 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.52 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.95 | 46.95 | 69.96 | 58.46 | B - Node 0.5-1 km | 0.97 | 0.52 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1423
2 | 424 | 1424 | 0401006011 | Region IV-A (CALABARZON) | Batangas | Bauan | Bolo | 13.7867 | 120.9767 | R | 4397 | 3.6 | 1221 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 2.68 | Tier 2B: Moderate GIDA Inclusion | 66.98 | 66.98 | 49.91 | 58.45 | D - Other node or line within 3 km | 1.08 | 2.68 | Node: BUN002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1424
2 | 425 | 1425 | 1003511022 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Tawinian | 8.0462 | 123.8829 | R | 830 | 4.2 | 198 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.23 | 6.11 | Tier 1B: High GIDA Priority | 45.29 | 45.29 | 71.62 | 58.45 | F - Nearest node and line over 5 km | 9.23 | 6.11 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1425
2 | 426 | 1426 | 1380601104 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 104 | 13.26 | 120.3181 | U | 5801 | 4.49 | 1293 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.09 | 67.49 | Tier 1B: High GIDA Priority | 41.92 | 41.92 | 74.97 | 58.45 | F - Nearest node and line over 5 km | 69.09 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1426
2 | 427 | 1427 | 0803731005 | Region VIII (Eastern Visayas) | Leyte | Mahaplag | Hinaguimitan | 10.593 | 125.0059 | R | 506 | 3.8 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.15 | 4.67 | Tier 1B: High GIDA Priority | 38.24 | 38.24 | 78.67 | 58.45 | F - Nearest node and line over 5 km | 24.3 | 22.66 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1427
2 | 428 | 1428 | 1381400007 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Isabelita | 14.6038 | 121.0296 | U | 1694 | 3.66 | 463 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.98 | 43.98 | 72.91 | 58.44 | C - Line within 0.5 km; node over 1 km | 1.83 | 0.05 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1428
2 | 429 | 1429 | 0305410001 | Region III (Central Luzon) | Pampanga | Macabebe | Batasan | 14.8918 | 120.7151 | R | 4722 | 4 | 1180 | 354 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.82 | Tier 2A: High Commercial ROI | 70.92 | 70.92 | 45.94 | 58.43 | B - Node 0.5-1 km | 0.9 | 5.83 | Node: MSP001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 1429
2 | 430 | 1430 | 0402120034 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya II | 14.3967 | 120.8535 | U | 7228 | 3.4 | 2126 | 638 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 66.04 | 66.04 | 50.82 | 58.43 | B - Node 0.5-1 km | 0.94 | 0.41 | Line: TANZA | Survey short node lateral; confirm port/fiber capacity, access and route. | 1430
2 | 431 | 1431 | 0305408041 | Region III (Central Luzon) | Pampanga | Lubao | Santa Teresa 2nd | 14.8869 | 120.5635 | R | 4515 | 4 | 1129 | 339 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 2.24 | Tier 2B: Moderate GIDA Inclusion | 64.19 | 64.19 | 52.68 | 58.43 | D - Other node or line within 3 km | 2.85 | 2.24 | Line: foc | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1431
2 | 432 | 1432 | 1380200012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Manuyo Dos | 14.4703 | 120.9914 | U | 51459 | 3.95 | 13041 | 3912 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.93 | 0.6 | Tier 1B: High GIDA Priority | 57.74 | 57.74 | 59.13 | 58.43 | B - Node 0.5-1 km | 0.93 | 0.6 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1432
2 | 433 | 1433 | 0504103030 | Region V (Bicol Region) | Masbate | Balud | Tonga | 12.0681 | 123.2379 | R | 1044 | 4.1 | 255 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 14.62 | Tier 1B: High GIDA Priority | 57.23 | 57.23 | 59.64 | 58.43 | A - Node within 0.5 km | 0.29 | 33.81 | Node: BDM001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1433
2 | 434 | 1434 | 1908708006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Kapimpilan | 17.2509 | 122.2398 | R | 3410 | 4.3 | 793 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.05 | 35.29 | Tier 1B: High GIDA Priority | 45.3 | 45.3 | 71.55 | 58.43 | F - Nearest node and line over 5 km | 30.05 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1434
2 | 435 | 1435 | 0205001004 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Camandag | 16.593 | 121.0421 | R | 1574 | 3.8 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.71 | 15.12 | Tier 1B: High GIDA Priority | 44.56 | 44.56 | 72.3 | 58.43 | F - Nearest node and line over 5 km | 15.71 | 15.12 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1435
2 | 436 | 1436 | 1381100201 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 201 | 14.5081 | 121.0306 | U | 20673 | 3.78 | 5475 | 1642 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.77 | 0.46 | Tier 2B: Moderate GIDA Inclusion | 65.71 | 65.71 | 51.14 | 58.42 | C - Line within 0.5 km; node over 1 km | 1.77 | 0.45 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1436
2 | 437 | 1437 | 0300811003 | Region III (Central Luzon) | Bataan | Pilar | Bagumbayan | 14.666 | 120.5645 | R | 1531 | 3.6 | 425 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 0.55 | Tier 1B: High GIDA Priority | 54.03 | 54.03 | 62.82 | 58.42 | D - Other node or line within 3 km | 2.85 | 0.51 | Line: PILAR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1437
2 | 438 | 1438 | 0907311014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Gusom | 7.6992 | 123.0878 | R | 823 | 3.9 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.96 | 4.18 | Tier 1B: High GIDA Priority | 47.65 | 47.65 | 69.18 | 58.42 | E - Nearest node or line 3-5 km | 4.96 | 4.15 | Line: PAGADIAN - BUUG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1438
2 | 439 | 1439 | 1381300024 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kristong Hari | 14.6772 | 121.0508 | U | 6260 | 4.55 | 1377 | 413 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 60.26 | 60.26 | 56.56 | 58.41 | A - Node within 0.5 km | 0.41 | 0.37 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1439
2 | 440 | 1440 | 1381100017 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 17 | 14.5144 | 121.0049 | U | 1109 | 2.5 | 444 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.48 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.62 | 45.62 | 71.2 | 58.41 | B - Node 0.5-1 km | 0.63 | 0.1 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1440
2 | 441 | 1441 | 0504113010 | Region V (Bicol Region) | Masbate | Mobo | Lomocloc | 12.2537 | 123.6229 | R | 652 | 4.1 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.02 | 8.64 | Tier 1B: High GIDA Priority | 44.78 | 44.78 | 72.03 | 58.41 | F - Nearest node and line over 5 km | 10.02 | 8.64 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1441
2 | 442 | 1442 | 0102934008 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VI | 17.5623 | 120.3968 | R | 1370 | 3.8 | 361 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 2.09 | Tier 1B: High GIDA Priority | 47.92 | 47.92 | 68.85 | 58.39 | D - Other node or line within 3 km | 3.55 | 1.99 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1442
2 | 443 | 1443 | 1381100072 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 72 | 14.4564 | 121.0355 | U | 1470 | 3.2 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.13 | 0.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.13 | 47.13 | 69.65 | 58.39 | A - Node within 0.5 km | 0.13 | 0.03 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1443
2 | 444 | 1444 | 0501606002 | Region V (Bicol Region) | Camarines Norte | Labo | Awitan | 14.1503 | 122.7128 | R | 720 | 4 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.3 | 5 | Tier 1B: High GIDA Priority | 42.64 | 42.64 | 74.14 | 58.39 | F - Nearest node and line over 5 km | 8.3 | 5 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1444
2 | 445 | 1445 | 1003514001 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Bacayawan | 8.0337 | 124.0792 | R | 1212 | 4.2 | 289 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.64 | 16.9 | Tier 1B: High GIDA Priority | 40.59 | 40.59 | 76.18 | 58.39 | F - Nearest node and line over 5 km | 21.64 | 16.85 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1445
2 | 446 | 1446 | 1003514011 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lindongan | 8.0343 | 124.0872 | R | 1280 | 4.2 | 305 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.77 | 16.8 | Tier 1B: High GIDA Priority | 41.21 | 41.21 | 75.54 | 58.38 | F - Nearest node and line over 5 km | 20.77 | 16.8 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1446
2 | 447 | 1447 | 1705306024 | MIMAROPA Region | Palawan | Brooke'S Point | Samareñana | 8.8138 | 117.8267 | R | 4265 | 3.9 | 1094 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 143.26 | 145.56 | Tier 1B: High GIDA Priority | 51.42 | 51.42 | 65.33 | 58.37 | F - Nearest node and line over 5 km | 143.26 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1447
2 | 448 | 1448 | 1380603004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 384 | 13.9412 | 122.6877 | U | 3830 | 3.36 | 1141 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.81 | 5.86 | Tier 1B: High GIDA Priority | 46.19 | 46.19 | 70.55 | 58.37 | F - Nearest node and line over 5 km | 9.81 | 5.8 | Line: LZQ001 TO DEL GALLEGO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1448
2 | 449 | 1449 | 0300810012 | Region III (Central Luzon) | Bataan | Orion | Daang Bilolo | 14.6181 | 120.577 | R | 3206 | 3.6 | 891 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.14 | Tier 2A: High Commercial ROI | 70.65 | 70.65 | 46.06 | 58.36 | A - Node within 0.5 km | 0.38 | 0.14 | Line: ORION | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1449
2 | 450 | 1450 | 1381300071 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Obrero | 14.6718 | 121.0933 | U | 9639 | 3.71 | 2597 | 779 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 1.24 | Tier 2B: Moderate GIDA Inclusion | 61.99 | 61.99 | 54.73 | 58.36 | D - Other node or line within 3 km | 1.38 | 1.24 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1450
2 | 451 | 1451 | 1908704011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Sinipak | 17.2541 | 122.2282 | R | 3261 | 4.3 | 758 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 44.41 | 44.41 | 72.31 | 58.36 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1451
2 | 452 | 1452 | 0600611025 | Region VI (Western Visayas) | Antique | Pandan | Perfecta | 11.7273 | 122.1258 | R | 214 | 3.9 | 55 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.3 | 9.25 | Tier 1B: High GIDA Priority | 39.53 | 39.53 | 77.19 | 58.36 | F - Nearest node and line over 5 km | 18.3 | 24.78 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1452
2 | 453 | 1453 | 0601901015 | Region VI (Western Visayas) | Capiz | Cuartero | Malagab-i | 11.325 | 122.6921 | R | 1776 | 3.8 | 467 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.78 | 2.34 | Tier 1B: High GIDA Priority | 54.25 | 54.25 | 62.46 | 58.35 | D - Other node or line within 3 km | 7.78 | 2.34 | Line: ROXAS - ILOILO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1453
2 | 454 | 1454 | 0105536016 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Malico | 16.1759 | 120.8682 | R | 351 | 3.6 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.67 | 7.41 | Tier 1B: High GIDA Priority | 39.23 | 39.23 | 77.47 | 58.35 | F - Nearest node and line over 5 km | 7.67 | 7.39 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1454
2 | 455 | 1455 | 0402103007 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Dulong Bayan | 14.2838 | 120.8891 | U | 7100 | 3.4 | 2088 | 626 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 63.82 | 63.82 | 52.87 | 58.34 | C - Line within 0.5 km; node over 1 km | 2.18 | 0.2 | Line: TRECE MARTIRES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1455
2 | 456 | 1456 | 1381300060 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Mariana | 14.6483 | 121.0839 | U | 12144 | 4.9 | 2477 | 743 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 1.02 | Tier 2B: Moderate GIDA Inclusion | 61.16 | 61.16 | 55.52 | 58.34 | D - Other node or line within 3 km | 1.67 | 1.02 | Line: UG 288C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1456
2 | 457 | 1457 | 0501703025 | Region V (Bicol Region) | Camarines Sur | Bato | San Isidro | 13.3475 | 123.3316 | R | 211 | 4.2 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 3.7 | Tier 1B: High GIDA Priority | 45.08 | 45.08 | 71.6 | 58.34 | E - Nearest node or line 3-5 km | 3.88 | 3.7 | Line: IRIGA - LEGAZPI | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1457
2 | 458 | 1458 | 0301408009 | Region III (Central Luzon) | Bulacan | Guiguinto | Santa Cruz | 14.8398 | 120.8679 | U | 12270 | 3.5 | 3506 | 1052 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.33 | 0.61 | Tier 2B: Moderate GIDA Inclusion | 69.7 | 69.7 | 46.95 | 58.33 | D - Other node or line within 3 km | 1.33 | 0.58 | Line: 48 CORE (6X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1458
2 | 459 | 1459 | 0103314059 | Region I (Ilocos Region) | La Union | City of San Fernando | Tanqui | 16.6165 | 120.3239 | U | 5298 | 3.7 | 1432 | 430 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 62.96 | 62.96 | 53.68 | 58.32 | D - Other node or line within 3 km | 1.58 | 0.73 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1459
2 | 460 | 1460 | 0402106020 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Datu Esmael | 14.3312 | 120.9592 | U | 8389 | 3.4 | 2467 | 740 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 3.33 | Tier 2B: Moderate GIDA Inclusion | 61.46 | 61.46 | 55.17 | 58.32 | D - Other node or line within 3 km | 2.2 | 3.26 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1460
2 | 461 | 1461 | 1381300104 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Cruz | 14.6041 | 121.017 | U | 4061 | 3.23 | 1257 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.02 | Tier 1B: High GIDA Priority | 58.07 | 58.07 | 58.57 | 58.32 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.02 | Line: UG 288C via W-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1461
2 | 462 | 1462 | 0403412013 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Isidro | 14.1786 | 121.5221 | R | 3051 | 3.3 | 925 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.97 | 4.41 | Tier 2B: Moderate GIDA Inclusion | 69.07 | 69.07 | 47.54 | 58.3 | D - Other node or line within 3 km | 1.97 | 4.38 | Node: LSL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1462
2 | 463 | 1463 | 1108605002 | Region XI (Davao Region) | Davao Occidental | Sarangani | Konel | 5.4312 | 125.3926 | R | 2140 | 3.9 | 549 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.98 | 79.79 | Tier 1B: High GIDA Priority | 45.03 | 45.03 | 71.57 | 58.3 | F - Nearest node and line over 5 km | 75.98 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1463
2 | 464 | 1464 | 1401114002 | Cordillera Administrative Region (CAR) | Benguet | Tublay | Ambongdolan | 16.5342 | 120.6038 | R | 1083 | 3.5 | 309 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.65 | 6.55 | Tier 1B: High GIDA Priority | 50.47 | 50.47 | 66.11 | 58.29 | E - Nearest node or line 3-5 km | 4.65 | 6.47 | Node: KPB001 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1464
2 | 465 | 1465 | 1380610034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 719 | 12.4358 | 120.3299 | U | 8846 | 3.5 | 2528 | 758 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.93 | 79.52 | Tier 1B: High GIDA Priority | 45.57 | 45.57 | 71.01 | 58.29 | F - Nearest node and line over 5 km | 47.93 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1465
2 | 466 | 1466 | 0401005068 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 21 | 13.6947 | 121.0891 | R | 700 | 3.6 | 194 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.9 | 7.45 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.98 | 43.98 | 72.61 | 58.29 | D - Other node or line within 3 km | 2.9 | 7.45 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1466
2 | 467 | 1467 | 0305415018 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Paralaya | 15.1151 | 120.5671 | U | 14310 | 4 | 3578 | 1073 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.48 | 0.03 | Tier 2A: High Commercial ROI | 71.55 | 71.55 | 45.01 | 58.28 | A - Node within 0.5 km | 0.48 | 0.03 | Line: 24 CORE (3X8) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1467
2 | 468 | 1468 | 0103304009 | Region I (Ilocos Region) | La Union | Bagulin | Tio-angan | 16.5943 | 120.5138 | R | 998 | 3.7 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.95 | 10.24 | Tier 1B: High GIDA Priority | 44.84 | 44.84 | 71.72 | 58.28 | F - Nearest node and line over 5 km | 9.95 | 10.11 | Node: KPB001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1468
2 | 469 | 1469 | 0405627042 | Region IV-A (CALABARZON) | Quezon | Mauban | Lual Rural | 14.1888 | 121.7175 | R | 4093 | 3.8 | 1077 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 18.12 | Tier 2B: Moderate GIDA Inclusion | 66.33 | 66.33 | 50.2 | 58.27 | D - Other node or line within 3 km | 1.19 | 18.12 | Node: MBQ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1469
2 | 470 | 1470 | 1908709025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Tuca-Maror | 17.2541 | 122.2282 | R | 4924 | 4.3 | 1145 | 344 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.73 | 49.73 | 66.81 | 58.27 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1470
2 | 471 | 1471 | 1908711008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Mastura | Simuay/Seashore | 17.2541 | 122.2281 | R | 4505 | 4.3 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.43 | 49.43 | 67.1 | 58.27 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1471
2 | 472 | 1472 | 0403405043 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 6 | 14.2121 | 121.1636 | U | 1856 | 3.3 | 562 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 0.24 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.59 | 50.59 | 65.91 | 58.25 | C - Line within 0.5 km; node over 1 km | 2.5 | 0.05 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1472
2 | 473 | 1473 | 1206512016 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Sen. Ninoy Aquino | Midtungok | 6.4019 | 124.2522 | R | 3412 | 3.8 | 898 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.49 | 56.42 | Tier 1B: High GIDA Priority | 48.98 | 48.98 | 67.53 | 58.25 | F - Nearest node and line over 5 km | 56.49 | 999999 | Node: TKC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1473
2 | 474 | 1474 | 0102934020 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Mindoro | 17.5599 | 120.3518 | R | 1575 | 3.8 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.55 | 4.8 | Tier 1B: High GIDA Priority | 47.79 | 47.79 | 68.72 | 58.25 | E - Nearest node or line 3-5 km | 5.55 | 4.52 | Line: SEGMENT 3 (VIGAN - BATAC) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1474
2 | 475 | 1475 | 1900707021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Duga-a | 6.6054 | 122.2022 | R | 4167 | 5.1 | 817 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.75 | 36.75 | Tier 1B: High GIDA Priority | 45.54 | 45.54 | 70.96 | 58.25 | F - Nearest node and line over 5 km | 36.75 | 36.74 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1475
2 | 476 | 1476 | 0201526028 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Santa Felicitas | 17.9067 | 121.5825 | R | 410 | 3.9 | 105 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.91 | 6.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.44 | 42.44 | 74.06 | 58.25 | D - Other node or line within 3 km | 2.91 | 6.13 | Node: SÑC001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1476
2 | 477 | 1477 | 1705314001 | MIMAROPA Region | Palawan | Magsaysay | Alcoba | 11.0102 | 120.8193 | R | 811 | 3.9 | 208 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 125.23 | 125.19 | Tier 1B: High GIDA Priority | 36.26 | 36.26 | 80.24 | 58.25 | F - Nearest node and line over 5 km | 125.23 | 999999 | Node: SBV001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1477
2 | 478 | 1478 | 0301404008 | Region III (Central Luzon) | Bulacan | Bocaue | Bundukan | 14.7896 | 120.9414 | U | 11633 | 3.5 | 3324 | 997 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 1 | Tier 2B: Moderate GIDA Inclusion | 69.21 | 69.21 | 47.26 | 58.24 | D - Other node or line within 3 km | 1.29 | 0.97 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1478
2 | 479 | 1479 | 1380601116 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 116 | 11.4964 | 121.2575 | U | 6182 | 4.68 | 1320 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 90.22 | 87.21 | Tier 1B: High GIDA Priority | 42 | 42 | 74.47 | 58.24 | F - Nearest node and line over 5 km | 90.22 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1479
2 | 480 | 1480 | 0203108059 | Region II (Cagayan Valley) | Isabela | City of Cauayan | San Fermin | 16.9373 | 121.7606 | U | 12480 | 3.8 | 3284 | 985 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.56 | Tier 2A: High Commercial ROI | 70.5 | 70.5 | 45.94 | 58.22 | B - Node 0.5-1 km | 0.56 | 0.55 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1480
2 | 481 | 1481 | 1908713015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Nangi | 17.254 | 122.2281 | R | 8566 | 4.3 | 1992 | 598 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 52.23 | 52.23 | 64.21 | 58.22 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1481
2 | 482 | 1482 | 1102319022 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Visayan Village | 7.4356 | 125.8147 | U | 43363 | 3.7 | 11720 | 3516 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 2.9 | 0.66 | Tier 2B: Moderate GIDA Inclusion | 64.19 | 64.19 | 52.23 | 58.21 | D - Other node or line within 3 km | 2.9 | 0.66 | Line: TAGUM - PANTUKAN SEGMENT 1 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1482
2 | 483 | 1483 | 0103304006 | Region I (Ilocos Region) | La Union | Bagulin | Libbo | 16.57 | 120.5244 | R | 961 | 3.7 | 260 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.64 | 8.33 | Tier 1B: High GIDA Priority | 46.01 | 46.01 | 70.4 | 58.21 | F - Nearest node and line over 5 km | 8.64 | 8.14 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1483
2 | 484 | 1484 | 0306916060 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Isidro | 15.4953 | 120.5864 | U | 15243 | 3.9 | 3908 | 1172 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.17 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 68.25 | 68.25 | 48.14 | 58.2 | D - Other node or line within 3 km | 3.17 | 0.52 | Line: 33,700 mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1484
2 | 485 | 1485 | 1908709003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Cotongan | 17.2541 | 122.2282 | R | 4067 | 4.3 | 946 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 49.14 | 49.14 | 67.24 | 58.19 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1485
2 | 486 | 1486 | 1402706019 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Liwo | 16.9813 | 121.2622 | R | 196 | 3.9 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.42 | 22.25 | Tier 1B: High GIDA Priority | 46.04 | 46.04 | 70.35 | 58.19 | E - Nearest node or line 3-5 km | 4.42 | 23.84 | Node: MOF001 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1486
2 | 487 | 1487 | 0402118026 | Region IV-A (CALABARZON) | Cavite | Silang | Maguyam | 14.2647 | 121.0063 | U | 14069 | 3.4 | 4138 | 1241 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.03 | 3.54 | Tier 2B: Moderate GIDA Inclusion | 66.85 | 66.85 | 49.5 | 58.18 | D - Other node or line within 3 km | 2.03 | 3.54 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1487
2 | 488 | 1488 | 0803726022 | Region VIII (Eastern Visayas) | Leyte | Kananga | Tongonan | 11.1306 | 124.6411 | U | 1652 | 3.8 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.64 | 5.89 | Tier 1B: High GIDA Priority | 41.69 | 41.69 | 74.67 | 58.18 | F - Nearest node and line over 5 km | 7.64 | 5.89 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1488
2 | 489 | 1489 | 1381701002 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Magtanggol | 14.5423 | 121.0715 | U | 1452 | 3.43 | 423 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 0.44 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.51 | 45.51 | 70.83 | 58.17 | A - Node within 0.5 km | 0.43 | 0.44 | Node: PAT001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1489
2 | 490 | 1490 | 1102503001 | Region XI (Davao Region) | Davao Oriental | Boston | Cabasagan | 7.8112 | 126.3519 | R | 1983 | 3.6 | 551 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.62 | 31.05 | Tier 1B: High GIDA Priority | 41.01 | 41.01 | 75.33 | 58.17 | F - Nearest node and line over 5 km | 32.62 | 31.05 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1490
2 | 491 | 1491 | 1606803016 | Region XIII (Caraga) | Surigao del Sur | City of Bislig | San Jose | 8.1454 | 126.333 | R | 4834 | 4.1 | 1179 | 354 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.74 | 31.66 | Tier 1B: High GIDA Priority | 52.67 | 52.67 | 63.65 | 58.16 | F - Nearest node and line over 5 km | 31.74 | 31.65 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1491
2 | 492 | 1492 | 0102901006 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Batbato | 16.913 | 120.565 | R | 577 | 3.8 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.16 | 10.78 | Tier 1B: High GIDA Priority | 43.72 | 43.72 | 72.59 | 58.16 | F - Nearest node and line over 5 km | 8.16 | 10.67 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1492
2 | 493 | 1493 | 0205009016 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Malabing | 16.3468 | 121.3753 | R | 887 | 3.8 | 233 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.28 | 26.32 | Tier 1B: High GIDA Priority | 40.07 | 40.07 | 76.26 | 58.16 | F - Nearest node and line over 5 km | 9.28 | 26.31 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1493
2 | 494 | 1494 | 1381100028 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 28 | 14.576 | 120.9868 | U | 1077 | 2.74 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.75 | 43.75 | 72.56 | 58.15 | B - Node 0.5-1 km | 0.91 | 0.53 | Line: PSG001 RELIANCE TO NCC001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1494
2 | 495 | 1495 | 1906605010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Maimbung | Kandang | 16.1321 | 122.1028 | R | 1147 | 6 | 191 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.62 | 9.62 | Tier 1B: High GIDA Priority | 40.79 | 40.79 | 75.52 | 58.15 | F - Nearest node and line over 5 km | 10.62 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1495
2 | 496 | 1496 | 1403213002 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Amlao | 17.3944 | 121.3188 | R | 852 | 4.3 | 198 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.27 | 1.13 | Tier 1B: High GIDA Priority | 39.6 | 39.6 | 76.7 | 58.15 | D - Other node or line within 3 km | 13.27 | 1.1 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1496
2 | 497 | 1497 | 0301408004 | Region III (Central Luzon) | Bulacan | Guiguinto | Malis | 14.8403 | 120.8819 | U | 17614 | 3.5 | 5033 | 1510 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.59 | 1.17 | Tier 2A: High Commercial ROI | 70.99 | 70.99 | 45.29 | 58.14 | D - Other node or line within 3 km | 1.59 | 1.33 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1497
2 | 498 | 1498 | 0304902020 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Rizal | 15.629 | 121.1392 | R | 3481 | 3.5 | 995 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.77 | Tier 2A: High Commercial ROI | 70.24 | 70.24 | 46.03 | 58.14 | B - Node 0.5-1 km | 0.96 | 0.77 | Line: Proposed AE F1-6 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1498
2 | 499 | 1499 | 0402117016 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa II | 14.4159 | 120.8508 | U | 7136 | 3.4 | 2099 | 630 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.31 | 2.49 | Tier 2B: Moderate GIDA Inclusion | 60.18 | 60.18 | 56.1 | 58.14 | D - Other node or line within 3 km | 2.31 | 2.49 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1499
2 | 500 | 1500 | 1705305003 | MIMAROPA Region | Palawan | Bataraza | Buliluyan | 8.3331 | 117.2018 | R | 2485 | 3.9 | 637 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 229.75 | 232.04 | Tier 1B: High GIDA Priority | 42.51 | 42.51 | 73.77 | 58.14 | F - Nearest node and line over 5 km | 229.75 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1500
2 | 501 | 1501 | 1907009005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Languyan Proper | 17.2558 | 122.2298 | U | 4399 | 5.8 | 758 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 36.88 | 36.88 | 79.4 | 58.14 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1501
2 | 502 | 1502 | 1381300041 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Fairview | 14.7102 | 121.0652 | U | 63913 | 4.05 | 15797 | 4739 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.35 | 0.42 | Tier 1B: High GIDA Priority | 53.54 | 53.54 | 62.72 | 58.13 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.34 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1502
2 | 503 | 1503 | 1380601093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 93 | 14.2843 | 121.6479 | U | 4586 | 3.82 | 1200 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.85 | 18.68 | Tier 1B: High GIDA Priority | 44.51 | 44.51 | 71.74 | 58.13 | F - Nearest node and line over 5 km | 11.85 | 18.65 | Node: CVL003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1503
2 | 504 | 1504 | 0403425006 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Langgam | 14.2061 | 121.1494 | U | 33922 | 3.3 | 10279 | 3084 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.04 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 64.8 | 64.8 | 51.45 | 58.12 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.13 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1504
2 | 505 | 1505 | 0806022044 | Region VIII (Eastern Visayas) | Samar | Paranas | Tenani | 11.8121 | 125.1548 | R | 2204 | 4.1 | 538 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.79 | 68.54 | Tier 1B: High GIDA Priority | 40.73 | 40.73 | 75.5 | 58.12 | F - Nearest node and line over 5 km | 65.79 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1505
2 | 506 | 1506 | 0601917030 | Region VI (Western Visayas) | Capiz | Tapaz | Minan | 11.2519 | 122.3664 | R | 555 | 3.8 | 146 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.85 | 20.94 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 83.65 | 58.12 | F - Nearest node and line over 5 km | 33.85 | 25.01 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1506
2 | 507 | 1507 | 0403430001 | Region IV-A (CALABARZON) | Laguna | Victoria | Banca-banca | 14.2024 | 121.3455 | R | 4281 | 3.3 | 1297 | 389 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.1 | Tier 2A: High Commercial ROI | 75.39 | 75.39 | 40.82 | 58.11 | B - Node 0.5-1 km | 0.99 | 0.05 | Line: AE CLL001-NEW TO PLL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1507
2 | 508 | 1508 | 0403421006 | Region IV-A (CALABARZON) | Laguna | Pangil | Natividad | 14.406 | 121.4684 | R | 2814 | 3.3 | 853 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.19 | Tier 2A: High Commercial ROI | 73.62 | 73.62 | 42.61 | 58.11 | B - Node 0.5-1 km | 0.64 | 0.16 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1508
2 | 509 | 1509 | 0300803008 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang Proper | 14.6684 | 120.5436 | U | 12098 | 3.6 | 3361 | 1008 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.71 | 0.7 | Tier 2B: Moderate GIDA Inclusion | 68.61 | 68.61 | 47.61 | 58.11 | D - Other node or line within 3 km | 1.71 | 0.7 | Line: PILAR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1509
2 | 510 | 1510 | 1381100194 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 194 | 14.5828 | 121.249 | U | 4693 | 3.39 | 1383 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.17 | 4.77 | Tier 1B: High GIDA Priority | 53.64 | 53.64 | 62.59 | 58.11 | D - Other node or line within 3 km | 2.17 | 4.77 | Node: BSR004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1510
2 | 511 | 1511 | 1705320005 | MIMAROPA Region | Palawan | Taytay | Bato | 10.7121 | 119.4853 | R | 4263 | 3.9 | 1093 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.61 | 0.63 | Tier 2A: High Commercial ROI | 72.59 | 72.59 | 43.62 | 58.1 | B - Node 0.5-1 km | 0.61 | 0.63 | Node: TYW004 - TYPE 4 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1511
2 | 512 | 1512 | 1380601125 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 125 | 13.0678 | 120.3085 | U | 3749 | 3.62 | 1037 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.75 | 79.22 | Tier 1B: High GIDA Priority | 41.17 | 41.17 | 75.04 | 58.1 | F - Nearest node and line over 5 km | 80.75 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1512
2 | 513 | 1513 | 0102815012 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Poblacion 1 | 18.5582 | 120.7846 | R | 2710 | 3.7 | 732 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.9 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 66.73 | 66.73 | 49.44 | 58.09 | C - Line within 0.5 km; node over 1 km | 2.9 | 0.32 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1513
2 | 514 | 1514 | 0403413005 | Region IV-A (CALABARZON) | Laguna | Lumban | Concepcion | 14.299 | 121.4566 | R | 4711 | 3.3 | 1428 | 428 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.75 | Tier 2A: High Commercial ROI | 72.04 | 72.04 | 44.12 | 58.08 | B - Node 0.5-1 km | 0.6 | 0.73 | Node: LML002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 1514
2 | 515 | 1515 | 0402120004 | Region IV-A (CALABARZON) | Cavite | Tanza | Biwas | 14.3983 | 120.855 | U | 7357 | 3.4 | 2164 | 649 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 66.49 | 66.49 | 49.66 | 58.08 | B - Node 0.5-1 km | 0.76 | 0.52 | Line: TANZA | Survey short node lateral; confirm port/fiber capacity, access and route. | 1515
2 | 516 | 1516 | 0403425007 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Laram | 14.3464 | 121.387 | U | 7165 | 3.3 | 2171 | 651 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 7.92 | Tier 2B: Moderate GIDA Inclusion | 59.05 | 59.05 | 57.11 | 58.08 | E - Nearest node or line 3-5 km | 3.38 | 7.9 | Node: PKL002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1516
2 | 517 | 1517 | 1381600013 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Lawang Bato | 14.7341 | 120.9908 | U | 23880 | 3.03 | 7870 | 2361 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.45 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 61.7 | 61.7 | 54.44 | 58.07 | C - Line within 0.5 km; node over 1 km | 2.45 | 0.04 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1517
2 | 518 | 1518 | 0604513013 | Region VI (Western Visayas) | Negros Occidental | Ilog | Pinggot | 9.7239 | 122.6775 | R | 3513 | 3.7 | 949 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.51 | 24.35 | Tier 1B: High GIDA Priority | 50.9 | 50.9 | 65.25 | 58.07 | F - Nearest node and line over 5 km | 27.51 | 24.35 | Line: SIPALAY TO BAYAWAN-84,748m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1518
2 | 519 | 1519 | 0102934005 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay III | 17.5752 | 120.3857 | U | 1150 | 3.8 | 303 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 0.84 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.22 | 44.22 | 71.92 | 58.07 | D - Other node or line within 3 km | 2.1 | 0.79 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1519
2 | 520 | 1520 | 1004322003 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Bunal | 8.8333 | 124.833 | R | 497 | 3.9 | 127 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.63 | 4.5 | Tier 1B: High GIDA Priority | 46.78 | 46.78 | 69.33 | 58.06 | E - Nearest node or line 3-5 km | 5.63 | 4.45 | Line: CDO - BUENAVISTA via GINGOOG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1520
2 | 521 | 1521 | 1380601043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 43 | 14.0358 | 121.0185 | U | 2949 | 4.57 | 645 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.33 | 10.39 | Tier 1B: High GIDA Priority | 41.09 | 41.09 | 75.02 | 58.06 | F - Nearest node and line over 5 km | 6.33 | 10.37 | Node: TSB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1521
2 | 522 | 1522 | 0405804003 | Region IV-A (CALABARZON) | Rizal | Binangonan | Bilibiran | 14.4995 | 121.1736 | U | 17784 | 3.6 | 4940 | 1482 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.84 | 0.07 | Tier 2A: High Commercial ROI | 72.14 | 72.14 | 43.97 | 58.05 | B - Node 0.5-1 km | 0.84 | 0.05 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1522
2 | 523 | 1523 | 0403404002 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banaybanay | 14.2316 | 121.2892 | U | 37555 | 3.3 | 11380 | 3414 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 5.71 | 5.82 | Tier 1B: High GIDA Priority | 54.61 | 54.61 | 61.49 | 58.05 | F - Nearest node and line over 5 km | 5.71 | 5.82 | Node: BAY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1523
2 | 524 | 1524 | 0205007018 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | New Gumiad | 16.0209 | 121.3026 | R | 650 | 3.8 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.75 | 24.61 | Tier 1B: High GIDA Priority | 31.67 | 31.67 | 84.41 | 58.04 | F - Nearest node and line over 5 km | 20.75 | 24.55 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1524
2 | 525 | 1525 | 0402117012 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong III | 14.4264 | 120.8539 | U | 5980 | 3.4 | 1759 | 528 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.16 | 3.11 | Tier 1B: High GIDA Priority | 58.04 | 58.04 | 58.02 | 58.03 | E - Nearest node or line 3-5 km | 3.16 | 3.11 | Line: PSG001 RELIANCE TO NCC001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1525
2 | 526 | 1526 | 0402116008 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose I | 14.4398 | 120.8756 | R | 1532 | 3.4 | 451 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 1.35 | Tier 1B: High GIDA Priority | 56.7 | 56.7 | 59.36 | 58.03 | D - Other node or line within 3 km | 1.39 | 1.35 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1526
2 | 527 | 1527 | 1381100177 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 177 | 14.6981 | 120.8414 | U | 6250 | 4.23 | 1476 | 443 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.33 | 10.97 | Tier 1B: High GIDA Priority | 46.67 | 46.67 | 69.39 | 58.03 | F - Nearest node and line over 5 km | 10.33 | 10.9 | Node: OBB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1527
2 | 528 | 1528 | 1906618008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Mamanok | 16.2346 | 122.0989 | R | 1052 | 6 | 175 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.65 | 2.39 | Tier 1B: High GIDA Priority | 44.52 | 44.52 | 71.54 | 58.03 | F - Nearest node and line over 5 km | 5.65 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1528
2 | 529 | 1529 | 1108603041 | Region XI (Davao Region) | Davao Occidental | Malita | Pangaleon | 6.3316 | 125.525 | R | 2435 | 3.6 | 676 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.61 | 26.08 | Tier 1B: High GIDA Priority | 44.5 | 44.5 | 71.57 | 58.03 | F - Nearest node and line over 5 km | 27.61 | 26.07 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1529
2 | 530 | 1530 | 1403214016 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lay-asan | 17.2836 | 121.3906 | R | 714 | 4.3 | 166 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.11 | 13.39 | Tier 1B: High GIDA Priority | 40.65 | 40.65 | 75.42 | 58.03 | F - Nearest node and line over 5 km | 12.11 | 13.36 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1530
2 | 531 | 1531 | 1380614031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 775 | 12.1329 | 120.4471 | U | 12116 | 4.58 | 2647 | 794 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.97 | 71.09 | Tier 1B: High GIDA Priority | 45.92 | 45.92 | 70.12 | 58.02 | F - Nearest node and line over 5 km | 25.97 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1531
2 | 532 | 1532 | 0501610012 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Guitol | 14.1043 | 122.4067 | R | 378 | 4 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5 | 2.76 | Tier 1B: High GIDA Priority | 44.17 | 44.17 | 71.87 | 58.02 | D - Other node or line within 3 km | 5 | 2.7 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1532
2 | 533 | 1533 | 0403428005 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dita | 14.2815 | 121.1122 | U | 37982 | 3.3 | 11510 | 3453 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.2 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 62.91 | 62.91 | 53.11 | 58.01 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.02 | Line: BINAN - CABUYAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1533
2 | 534 | 1534 | 1381300103 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Vicente | 14.6534 | 121.0573 | U | 7362 | 3.85 | 1913 | 574 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.87 | Tier 2B: Moderate GIDA Inclusion | 60.56 | 60.56 | 55.47 | 58.01 | D - Other node or line within 3 km | 1.06 | 0.95 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1534
2 | 535 | 1535 | 1380200004 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Ilaya | 14.4781 | 120.9803 | U | 7287 | 3.88 | 1876 | 563 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 59.57 | 59.57 | 56.45 | 58.01 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.05 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1535
2 | 536 | 1536 | 0401003003 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 1 | 13.954 | 120.7335 | R | 2162 | 3.6 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 60.96 | 60.96 | 55.05 | 58 | D - Other node or line within 3 km | 1.3 | 0.5 | Line: TGY001 TO BYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1536
2 | 537 | 1537 | 0301410043 | Region III (Central Luzon) | Bulacan | City of Malolos | San Juan | 14.8344 | 120.8148 | U | 4773 | 3.5 | 1364 | 409 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 1.87 | Tier 2B: Moderate GIDA Inclusion | 64.35 | 64.35 | 51.62 | 57.99 | B - Node 0.5-1 km | 0.71 | 1.89 | Node: MSB003 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1537
2 | 538 | 1538 | 0401003008 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 3 | 13.9488 | 120.7284 | R | 1519 | 3.6 | 422 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.14 | Tier 1B: High GIDA Priority | 57.5 | 57.5 | 58.48 | 57.99 | B - Node 0.5-1 km | 0.59 | 0.11 | Line: AE NSB001 TO BYB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1538
2 | 539 | 1539 | 0301416004 | Region III (Central Luzon) | Bulacan | Paombong | Masukol | 14.7642 | 120.7707 | R | 1452 | 3.5 | 415 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.9 | 10.85 | Tier 1B: High GIDA Priority | 46.56 | 46.56 | 69.41 | 57.99 | F - Nearest node and line over 5 km | 7.9 | 10.93 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1539
2 | 540 | 1540 | 1380605042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 340 | 13.9348 | 122.1152 | U | 1785 | 3.53 | 506 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.56 | 45.56 | 70.41 | 57.99 | D - Other node or line within 3 km | 1.55 | 1.2 | Line: GCQ001 TO TKQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1540
2 | 541 | 1541 | 0604531017 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XIV | 10.9038 | 123.0608 | R | 4791 | 3.7 | 1295 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 0.96 | Tier 2A: High Commercial ROI | 73.43 | 73.43 | 42.53 | 57.98 | D - Other node or line within 3 km | 1.37 | 0.89 | Line: TALISAY - VICTORIAS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1541
2 | 542 | 1542 | 0405802013 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dalig | 14.561 | 121.1897 | U | 56096 | 3.6 | 15582 | 4675 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.88 | 0.34 | Tier 1B: High GIDA Priority | 58.22 | 58.22 | 57.74 | 57.98 | B - Node 0.5-1 km | 0.88 | 0.16 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1542
2 | 543 | 1543 | 1380800007 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Sucat | 14.4442 | 121.0421 | U | 59601 | 3.51 | 17004 | 5101 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 1.43 | 0.4 | Tier 1B: High GIDA Priority | 51.89 | 51.89 | 64.07 | 57.98 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.4 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1543
2 | 544 | 1544 | 1380601108 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 108 | 11.4185 | 121.774 | U | 5114 | 4.85 | 1055 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.33 | 56.28 | Tier 1B: High GIDA Priority | 41.21 | 41.21 | 74.74 | 57.98 | F - Nearest node and line over 5 km | 61.33 | 999999 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1544
2 | 545 | 1545 | 0907344002 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Busol | 7.8539 | 123.2388 | R | 752 | 3.9 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.23 | 1.56 | Tier 1B: High GIDA Priority | 40.44 | 40.44 | 75.52 | 57.98 | D - Other node or line within 3 km | 22.23 | 1.56 | Line: PAGADIAN - BUUG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1545
2 | 546 | 1546 | 0405808006 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Mascap | 14.7627 | 121.1834 | R | 4507 | 3.6 | 1252 | 376 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.23 | 2.86 | Tier 2B: Moderate GIDA Inclusion | 62.9 | 62.9 | 53.04 | 57.97 | D - Other node or line within 3 km | 4.23 | 2.84 | Line: Aerial 216C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1546
2 | 547 | 1547 | 1001307013 | Region X (Northern Mindanao) | Bukidnon | Kalilangan | Ninoy Aquino | 7.7686 | 124.7857 | R | 5005 | 3.8 | 1317 | 395 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.02 | 18.67 | Tier 1B: High GIDA Priority | 55.85 | 55.85 | 60.06 | 57.96 | F - Nearest node and line over 5 km | 17.02 | 18.54 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1547
2 | 548 | 1548 | 0803730010 | Region VIII (Eastern Visayas) | Leyte | Macarthur | Lanawan | 10.8573 | 124.8591 | R | 353 | 3.8 | 93 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.98 | 11.39 | Tier 1B: High GIDA Priority | 40.04 | 40.04 | 75.87 | 57.96 | F - Nearest node and line over 5 km | 16.98 | 11.39 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1548
2 | 549 | 1549 | 0806022022 | Region VIII (Eastern Visayas) | Samar | Paranas | Pabanog | 11.7361 | 125.0644 | R | 1894 | 4.1 | 462 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.61 | 58.53 | Tier 1B: High GIDA Priority | 39.11 | 39.11 | 76.81 | 57.96 | F - Nearest node and line over 5 km | 55.61 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1549
2 | 550 | 1550 | 0205015002 | Region II (Cagayan Valley) | Nueva Vizcaya | Alfonso Castaneda | Galintuja | 15.8114 | 121.3238 | R | 1036 | 3.8 | 273 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.46 | 2.41 | Tier 1B: High GIDA Priority | 35.94 | 35.94 | 79.99 | 57.96 | D - Other node or line within 3 km | 16.46 | 2.4 | Line: BALER - PANTABANGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1550
2 | 551 | 1551 | 1004326011 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Looc | 8.5943 | 124.7735 | R | 5071 | 3.9 | 1300 | 390 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.16 | Tier 2A: High Commercial ROI | 74.61 | 74.61 | 41.3 | 57.95 | A - Node within 0.5 km | 0.16 | 0.15 | Line: CDO - BUENAVISTA via GINGOOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1551
2 | 552 | 1552 | 0403421004 | Region IV-A (CALABARZON) | Laguna | Pangil | Isla | 14.3996 | 121.4711 | R | 3151 | 3.3 | 955 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.43 | Tier 2A: High Commercial ROI | 74.05 | 74.05 | 41.85 | 57.95 | C - Line within 0.5 km; node over 1 km | 1.14 | 0.43 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1552
2 | 553 | 1553 | 0300810016 | Region III (Central Luzon) | Bataan | Orion | Kapunitan | 14.6163 | 120.5817 | R | 4322 | 3.6 | 1201 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.29 | Tier 2A: High Commercial ROI | 72.21 | 72.21 | 43.68 | 57.95 | A - Node within 0.5 km | 0.3 | 0.29 | Line: 36 CORE 3X12 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1553
2 | 554 | 1554 | 1381400005 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Ermitaño | 14.609 | 121.036 | U | 3680 | 3.41 | 1079 | 324 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 0.37 | Tier 1B: High GIDA Priority | 56.2 | 56.2 | 59.7 | 57.95 | D - Other node or line within 3 km | 2.2 | 0.54 | Line: UG 144C via W-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1554
2 | 555 | 1555 | 0405646033 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Francisco | 14.0157 | 122.4884 | R | 978 | 3.8 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.17 | 50.17 | 65.74 | 57.95 | C - Line within 0.5 km; node over 1 km | 2.18 | 0.04 | Line: CALAUAG - SIPOCOT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1555
2 | 556 | 1556 | 1400126002 | Cordillera Administrative Region (CAR) | Abra | Tubo | Amtuagan | 17.3064 | 120.7302 | R | 511 | 3.8 | 134 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.61 | 13.41 | Tier 1B: High GIDA Priority | 36.03 | 36.03 | 79.87 | 57.95 | F - Nearest node and line over 5 km | 19.61 | 13.3 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1556
2 | 557 | 1557 | 1381300052 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Laging Handa | 14.6364 | 121.0654 | U | 4963 | 3.39 | 1464 | 439 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 59.02 | 59.02 | 56.85 | 57.94 | D - Other node or line within 3 km | 1.17 | 0.7 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1557
2 | 558 | 1558 | 1381100190 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 190 | 14.4603 | 120.7749 | U | 4445 | 3.78 | 1175 | 352 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.29 | 11.1 | Tier 1B: High GIDA Priority | 44.89 | 44.89 | 70.99 | 57.94 | F - Nearest node and line over 5 km | 11.29 | 11.1 | Line: TANZA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1558
2 | 559 | 1559 | 0702234022 | Region VII (Central Visayas) | Cebu | City of Naga | South Poblacion | 10.2011 | 123.7536 | U | 7068 | 3.8 | 1860 | 558 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.94 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 63.97 | 63.97 | 51.9 | 57.93 | C - Line within 0.5 km; node over 1 km | 4.09 | 0.16 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1559
2 | 560 | 1560 | 0305412027 | Region III (Central Luzon) | Pampanga | Masantol | Sapang Kawayan | 14.8053 | 120.6858 | U | 3449 | 4 | 862 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8 | 8.83 | Tier 1B: High GIDA Priority | 51.06 | 51.06 | 64.79 | 57.93 | F - Nearest node and line over 5 km | 8 | 14.03 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1560
2 | 561 | 1561 | 1381300124 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | U.P. Campus | 14.6742 | 120.9631 | U | 48951 | 3.97 | 12342 | 3703 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.76 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 58.94 | 58.94 | 56.89 | 57.92 | B - Node 0.5-1 km | 0.76 | 0.55 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1561
2 | 562 | 1562 | 1908706002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Buterin | 17.2541 | 122.2282 | R | 3136 | 4.3 | 729 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 43.71 | 43.71 | 72.14 | 57.92 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1562
2 | 563 | 1563 | 0600406011 | Region VI (Western Visayas) | Aklan | Ibajay | Cabugao | 11.737 | 122.1693 | R | 274 | 3.9 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.71 | 5.51 | Tier 1B: High GIDA Priority | 37.23 | 37.23 | 78.61 | 57.92 | F - Nearest node and line over 5 km | 13.71 | 20.76 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1563
2 | 564 | 1564 | 0301403019 | Region III (Central Luzon) | Bulacan | Baliuag | Santa Barbara | 14.9419 | 120.8903 | U | 13210 | 3.5 | 3774 | 1132 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.73 | 0.09 | Tier 2A: High Commercial ROI | 71.64 | 71.64 | 44.19 | 57.91 | B - Node 0.5-1 km | 0.73 | 0.09 | Line: Calumpit-Baliuag Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 1564
2 | 565 | 1565 | 0300803018 | Region III (Central Luzon) | Bataan | City of Balanga | Camacho | 14.682 | 120.5274 | R | 4015 | 3.6 | 1115 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 0.69 | Tier 2B: Moderate GIDA Inclusion | 69.86 | 69.86 | 45.96 | 57.91 | D - Other node or line within 3 km | 1.37 | 0.69 | Line: Pipe Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1565
2 | 566 | 1566 | 1381100047 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 47 | 14.4862 | 121.0331 | U | 1277 | 3.19 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.96 | 44.96 | 70.86 | 57.91 | A - Node within 0.5 km | 0.4 | 0.25 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1566
2 | 567 | 1567 | 1381200002 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bagong Katipunan | 14.572 | 121.0897 | U | 945 | 3.03 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.36 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.08 | 42.08 | 73.74 | 57.91 | B - Node 0.5-1 km | 0.69 | 0.25 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1567
2 | 568 | 1568 | 0401003014 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 9 | 13.9648 | 120.7141 | R | 1830 | 3.6 | 508 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.82 | 1.37 | Tier 1B: High GIDA Priority | 56.12 | 56.12 | 59.65 | 57.89 | D - Other node or line within 3 km | 2.82 | 1.37 | Line: NSB001 TO BYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1568
2 | 569 | 1569 | 1380612004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 836 | 13.956 | 122.7857 | U | 5673 | 3.89 | 1457 | 437 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.26 | 13.72 | Tier 1B: High GIDA Priority | 44.95 | 44.95 | 70.83 | 57.89 | F - Nearest node and line over 5 km | 12.26 | 13.71 | Node: SLC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1569
2 | 570 | 1570 | 1380606197 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 590 | 13.4505 | 123.0296 | U | 2854 | 3.73 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 5.88 | Tier 1B: High GIDA Priority | 44.46 | 44.46 | 71.32 | 57.89 | F - Nearest node and line over 5 km | 5.83 | 5.82 | Line: PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1570
2 | 571 | 1571 | 0506211024 | Region V (Bicol Region) | Sorsogon | Magallanes | Malbog | 12.8079 | 123.895 | R | 366 | 4 | 92 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.17 | 2.47 | Tier 1B: High GIDA Priority | 43.54 | 43.54 | 72.24 | 57.89 | D - Other node or line within 3 km | 6.17 | 2.36 | Line: 30,000m | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1571
2 | 572 | 1572 | 1381100086 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 86 | 14.4502 | 121.0634 | U | 1448 | 2.74 | 529 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 1.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.86 | 44.86 | 70.91 | 57.88 | D - Other node or line within 3 km | 2.41 | 1.3 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1572
2 | 573 | 1573 | 0803730013 | Region VIII (Eastern Visayas) | Leyte | Macarthur | Oguisan | 10.8234 | 124.8633 | R | 157 | 3.8 | 41 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.35 | 10.11 | Tier 1B: High GIDA Priority | 39.89 | 39.89 | 75.87 | 57.88 | F - Nearest node and line over 5 km | 17.35 | 10.11 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1573
2 | 574 | 1574 | 1003511008 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lubo | 8.0235 | 123.9142 | R | 1184 | 4.2 | 282 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.85 | 9.63 | Tier 1B: High GIDA Priority | 44.17 | 44.17 | 71.56 | 57.87 | F - Nearest node and line over 5 km | 12.85 | 9.63 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1574
2 | 575 | 1575 | 1908704010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Sedem | 17.2541 | 122.2282 | R | 2947 | 4.3 | 685 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.2 | Tier 1B: High GIDA Priority | 42.58 | 42.58 | 73.17 | 57.87 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1575
2 | 576 | 1576 | 1381300078 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paraiso | 14.6293 | 121.0844 | U | 3584 | 4.22 | 850 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 1.15 | Tier 1B: High GIDA Priority | 54.88 | 54.88 | 60.83 | 57.86 | D - Other node or line within 3 km | 1.36 | 1.15 | Line: UG 288C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1576
2 | 577 | 1577 | 1908707002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bayanga Sur | 17.254 | 122.228 | R | 9894 | 4.3 | 2301 | 690 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 53.13 | 53.13 | 62.56 | 57.85 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1577
2 | 578 | 1578 | 0402117019 | Region IV-A (CALABARZON) | Cavite | Rosario | Silangan II | 14.4249 | 120.8436 | R | 4077 | 3.4 | 1199 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.57 | 3.72 | Tier 2B: Moderate GIDA Inclusion | 63.36 | 63.36 | 52.32 | 57.84 | E - Nearest node or line 3-5 km | 3.57 | 3.71 | Node: TRC001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1578
2 | 579 | 1579 | 0405607068 | Region IV-A (CALABARZON) | Quezon | Calauag | Salvacion | 14.0977 | 122.2747 | R | 255 | 3.8 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.63 | 9.31 | Tier 1B: High GIDA Priority | 41.37 | 41.37 | 74.31 | 57.84 | E - Nearest node or line 3-5 km | 3.63 | 9.2 | Node: CLQ004 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1579
2 | 580 | 1580 | 0601917052 | Region VI (Western Visayas) | Capiz | Tapaz | Siya | 11.236 | 122.3444 | R | 827 | 3.8 | 218 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.46 | 23.33 | Tier 1B: High GIDA Priority | 33.88 | 33.88 | 81.79 | 57.84 | F - Nearest node and line over 5 km | 35.46 | 27.56 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1580
2 | 581 | 1581 | 0403411001 | Region IV-A (CALABARZON) | Laguna | Los Baños | Anos | 14.1798 | 121.2295 | U | 9663 | 3.3 | 2928 | 878 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 67.67 | 67.67 | 47.99 | 57.83 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.17 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1581
2 | 582 | 1582 | 0702227005 | Region VII (Central Visayas) | Cebu | Liloan | Jubay | 10.4188 | 123.9959 | U | 15241 | 3.8 | 4011 | 1203 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.33 | 0.21 | Tier 2A: High Commercial ROI | 74.83 | 74.83 | 40.8 | 57.82 | C - Line within 0.5 km; node over 1 km | 1.27 | 0.19 | Line: 6.035km FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1582
2 | 583 | 1583 | 0401019048 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Wawa | 14.0812 | 120.6246 | U | 15886 | 3.6 | 4413 | 1324 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.54 | 0.21 | Tier 2A: High Commercial ROI | 71.53 | 71.53 | 44.1 | 57.82 | C - Line within 0.5 km; node over 1 km | 1.54 | 0.21 | Line: NASUGBU UPLINK | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1583
2 | 584 | 1584 | 1380601260 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 259 | 13.908 | 122.2659 | U | 2014 | 3.67 | 549 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 1.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.47 | 45.47 | 70.18 | 57.82 | D - Other node or line within 3 km | 2.35 | 1.46 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1584
2 | 585 | 1585 | 1380601095 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 95 | 12.7521 | 123.27 | U | 4994 | 4.6 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.29 | 31.73 | Tier 1B: High GIDA Priority | 41.31 | 41.31 | 74.33 | 57.82 | F - Nearest node and line over 5 km | 30.29 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1585
2 | 586 | 1586 | 1402708016 | Cordillera Administrative Region (CAR) | Ifugao | Aguinaldo | Buwag | 16.9349 | 121.3128 | R | 390 | 3.9 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.18 | 25.2 | Tier 1B: High GIDA Priority | 40.99 | 40.99 | 74.66 | 57.82 | F - Nearest node and line over 5 km | 5.18 | 25.16 | Node: AOF001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1586
2 | 587 | 1587 | 0403418004 | Region IV-A (CALABARZON) | Laguna | Paete | Ibaba del Norte | 14.3639 | 121.4792 | R | 3407 | 3.3 | 1032 | 310 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.04 | Tier 2A: High Commercial ROI | 75.29 | 75.29 | 40.32 | 57.81 | B - Node 0.5-1 km | 0.62 | 0.04 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1587
2 | 588 | 1588 | 0300809013 | Region III (Central Luzon) | Bataan | Orani | Pantalan Bago | 14.803 | 120.5417 | R | 2370 | 3.6 | 658 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 63.92 | 63.92 | 51.71 | 57.81 | B - Node 0.5-1 km | 0.59 | 0.56 | Line: 96CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1588
2 | 589 | 1589 | 1003516019 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Pansor | 8.0429 | 124.1939 | R | 1502 | 4.2 | 358 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.58 | 7.19 | Tier 1B: High GIDA Priority | 48.8 | 48.8 | 66.82 | 57.81 | F - Nearest node and line over 5 km | 9.58 | 7.11 | Line: Pantar Done Layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1589
2 | 590 | 1590 | 1102403029 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 2 | 6.7505 | 125.3573 | U | 7839 | 3.4 | 2306 | 692 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 69.1 | 69.1 | 46.5 | 57.8 | B - Node 0.5-1 km | 0.52 | 0.98 | Node: DSD002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1590
2 | 591 | 1591 | 0402116011 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio II | 14.4186 | 120.8858 | R | 2182 | 3.4 | 642 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 62.22 | 62.22 | 53.37 | 57.8 | C - Line within 0.5 km; node over 1 km | 1.25 | 0.24 | Line: NOVELETA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1591
2 | 592 | 1592 | 0102929002 | Region I (Ilocos Region) | Ilocos Sur | Sigay | Mabileg | 17.0336 | 120.5828 | R | 321 | 3.8 | 84 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.92 | 12.19 | Tier 1B: High GIDA Priority | 44.45 | 44.45 | 71.14 | 57.8 | F - Nearest node and line over 5 km | 5.92 | 11.8 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1592
2 | 593 | 1593 | 1381100091 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 91 | 14.6452 | 120.9591 | U | 1825 | 3.94 | 463 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.43 | 44.43 | 71.18 | 57.8 | D - Other node or line within 3 km | 1.55 | 2.1 | Node: CCS004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1593
2 | 594 | 1594 | 1908701012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Panggao | 16.7051 | 122.3464 | R | 3009 | 4.3 | 700 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.81 | 22.13 | Tier 1B: High GIDA Priority | 44.04 | 44.04 | 71.57 | 57.8 | F - Nearest node and line over 5 km | 21.81 | 999999 | Node: DPI001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1594
2 | 595 | 1595 | 1907010017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Lookan Latuan | 16.315 | 122.0648 | R | 1500 | 5.8 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.57 | 5.99 | Tier 1B: High GIDA Priority | 41.56 | 41.56 | 74.03 | 57.8 | F - Nearest node and line over 5 km | 7.57 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1595
2 | 596 | 1596 | 0306918007 | Region III (Central Luzon) | Tarlac | San Jose | Maamot | 15.3915 | 120.3497 | R | 2740 | 3.9 | 703 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.71 | 23.15 | Tier 1B: High GIDA Priority | 46.06 | 46.06 | 69.53 | 57.79 | F - Nearest node and line over 5 km | 20.71 | 22.79 | Node: CPT002 -BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1596
2 | 597 | 1597 | 1108601003 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | North Lamidan | 6.0954 | 125.703 | R | 2195 | 3.6 | 610 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.01 | 52.03 | Tier 1B: High GIDA Priority | 42.07 | 42.07 | 73.51 | 57.79 | F - Nearest node and line over 5 km | 47.01 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1597
2 | 598 | 1598 | 0301402005 | Region III (Central Luzon) | Bulacan | Balagtas | Longos | 14.8198 | 120.9109 | R | 2834 | 3.5 | 810 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 62.92 | 62.92 | 52.64 | 57.78 | C - Line within 0.5 km; node over 1 km | 4.22 | 0.4 | Line: BALAGTAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1598
2 | 599 | 1599 | 1906614014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kalang | 17.2557 | 122.2297 | R | 3332 | 6 | 555 | 166 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 43.57 | 43.57 | 72 | 57.78 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1599
2 | 600 | 1600 | 0702223040 | Region VII (Central Visayas) | Cebu | Danao City | Suba | 10.5245 | 124.0287 | U | 7790 | 3.8 | 2050 | 615 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 69.73 | 69.73 | 45.82 | 57.77 | A - Node within 0.5 km | 0.4 | 0.24 | Line: UPLINK 2 CRM001- DOC001 via AE BACKBONE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1600
2 | 601 | 1601 | 0301403017 | Region III (Central Luzon) | Bulacan | Baliuag | San Jose | 14.9484 | 120.8943 | U | 7044 | 3.5 | 2013 | 604 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 66.39 | 66.39 | 49.16 | 57.77 | B - Node 0.5-1 km | 0.68 | 0.04 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 1601
2 | 602 | 1602 | 0504120006 | Region V (Bicol Region) | Masbate | San Pascual | Iniwaran | 13.1534 | 122.8733 | R | 2365 | 4.1 | 577 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.86 | 42.67 | Tier 1B: High GIDA Priority | 43.69 | 43.69 | 71.86 | 57.77 | F - Nearest node and line over 5 km | 20.86 | 999999 | Node: SDQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1602
2 | 603 | 1603 | 1381100174 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 174 | 14.5335 | 121.0129 | U | 1710 | 3.56 | 480 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.6 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.26 | 45.26 | 70.26 | 57.76 | D - Other node or line within 3 km | 1.32 | 0.58 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1603
2 | 604 | 1604 | 1102502004 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Causwagan | 7.0099 | 126.015 | R | 831 | 3.6 | 231 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.18 | 2.03 | Tier 1B: High GIDA Priority | 44.63 | 44.63 | 70.89 | 57.76 | D - Other node or line within 3 km | 5.18 | 2.01 | Line: PANTUKAN - MATI SEGMENT 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1604
2 | 605 | 1605 | 0601917028 | Region VI (Western Visayas) | Capiz | Tapaz | Maliao | 11.3526 | 122.3585 | R | 850 | 3.8 | 224 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.82 | 22.49 | Tier 1B: High GIDA Priority | 35.31 | 35.31 | 80.19 | 57.75 | F - Nearest node and line over 5 km | 22.82 | 22.41 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1605
2 | 606 | 1606 | 0306916083 | Region III (Central Luzon) | Tarlac | City of Tarlac | Sepung Calzada | 15.5038 | 120.6013 | U | 5024 | 3.9 | 1288 | 386 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.78 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 60.76 | 60.76 | 54.73 | 57.74 | D - Other node or line within 3 km | 2.78 | 0.5 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1606
2 | 607 | 1607 | 1003523021 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Pitubo | 8.0686 | 124.2636 | R | 768 | 4.2 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.62 | 0.51 | Tier 1B: High GIDA Priority | 50.81 | 50.81 | 64.66 | 57.74 | C - Line within 0.5 km; node over 1 km | 6.62 | 0.38 | Line: Pantar Done Layed | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1607
2 | 608 | 1608 | 0102902008 | Region I (Ilocos Region) | Ilocos Sur | Banayoyo | Elefante | 17.2293 | 120.4837 | R | 630 | 3.8 | 166 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.85 | 0.78 | Tier 1B: High GIDA Priority | 49.58 | 49.58 | 65.91 | 57.74 | D - Other node or line within 3 km | 4.85 | 0.76 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1608
2 | 609 | 1609 | 1380601012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 12 | 13.7592 | 121.017 | U | 1723 | 3.82 | 451 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.03 | 2.96 | Tier 1B: High GIDA Priority | 38.46 | 38.46 | 77 | 57.73 | D - Other node or line within 3 km | 3.03 | 2.94 | Line: WP BYB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1609
2 | 610 | 1610 | 0405622032 | Region IV-A (CALABARZON) | Quezon | Lopez | Esperanza Ilaya | 13.8392 | 122.31 | R | 263 | 3.8 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.42 | 2.57 | Tier 1B: High GIDA Priority | 39.21 | 39.21 | 76.23 | 57.72 | D - Other node or line within 3 km | 7.42 | 2.56 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1610
2 | 611 | 1611 | 0201529019 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Caritan Norte | 17.6747 | 121.7561 | R | 3683 | 3.9 | 944 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.77 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 67.23 | 67.23 | 48.19 | 57.71 | C - Line within 0.5 km; node over 1 km | 2.77 | 0.3 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1611
2 | 612 | 1612 | 0301411008 | Region III (Central Luzon) | Bulacan | Marilao | Patubig | 14.7787 | 120.9603 | U | 8800 | 3.5 | 2514 | 754 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.29 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 65.15 | 65.15 | 50.27 | 57.71 | D - Other node or line within 3 km | 2.29 | 2.21 | Line: BOCAUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1612
2 | 613 | 1613 | 0402123014 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Gregoria De Jesus | 14.2926 | 121.0215 | U | 11804 | 3.4 | 3472 | 1042 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.38 | 3.69 | Tier 2B: Moderate GIDA Inclusion | 64.3 | 64.3 | 51.13 | 57.71 | D - Other node or line within 3 km | 2.38 | 3.69 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1613
2 | 614 | 1614 | 0403428016 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pook | 14.3024 | 121.1096 | U | 61062 | 3.3 | 18504 | 5551 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.64 | 0.59 | Tier 1B: High GIDA Priority | 54.91 | 54.91 | 60.5 | 57.7 | B - Node 0.5-1 km | 0.64 | 0.59 | Line: AE SPL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1614
2 | 615 | 1615 | 0405809004 | Region IV-A (CALABARZON) | Rizal | Morong | Maybancal | 14.5251 | 121.2424 | U | 17211 | 3.6 | 4781 | 1434 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.52 | 0.13 | Tier 2A: High Commercial ROI | 72.99 | 72.99 | 42.39 | 57.69 | B - Node 0.5-1 km | 0.52 | 0.08 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 1615
2 | 616 | 1616 | 1403209008 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Wagud | 17.576 | 121.3415 | R | 1057 | 4.3 | 246 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 8.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.13 | 47.13 | 68.25 | 57.69 | D - Other node or line within 3 km | 2.1 | 8.22 | Node: PKK002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1616
2 | 617 | 1617 | 0403405004 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barandal | 14.1885 | 121.1302 | U | 19814 | 3.3 | 6004 | 1801 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.98 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 68.77 | 68.77 | 46.59 | 57.68 | C - Line within 0.5 km; node over 1 km | 1.98 | 0.2 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1617
2 | 618 | 1618 | 0300803026 | Region III (Central Luzon) | Bataan | City of Balanga | Doña Francisca | 14.6724 | 120.5368 | U | 2426 | 3.6 | 674 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.94 | Tier 1B: High GIDA Priority | 55.3 | 55.3 | 60.05 | 57.68 | D - Other node or line within 3 km | 1.42 | 0.91 | Line: 60 CORE 5X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1618
2 | 619 | 1619 | 0601912018 | Region VI (Western Visayas) | Capiz | Pontevedra | Manapao | 11.4456 | 122.8684 | R | 675 | 3.8 | 178 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.2 | 3.24 | Tier 1B: High GIDA Priority | 44.51 | 44.51 | 70.85 | 57.68 | E - Nearest node or line 3-5 km | 5.2 | 3.24 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1619
2 | 620 | 1620 | 0307708006 | Region III (Central Luzon) | Aurora | San Luis | Dibalo | 15.6648 | 121.5632 | R | 135 | 3.8 | 36 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.5 | 10.34 | Tier 1B: High GIDA Priority | 37.03 | 37.03 | 78.34 | 57.68 | F - Nearest node and line over 5 km | 9.5 | 10.34 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1620
2 | 621 | 1621 | 0301406010 | Region III (Central Luzon) | Bulacan | Bustos | Poblacion | 14.9558 | 120.919 | U | 8636 | 3.5 | 2467 | 740 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 68.43 | 68.43 | 46.91 | 57.67 | A - Node within 0.5 km | 0.36 | 0.42 | Node: BTS001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1621
2 | 622 | 1622 | 0405617007 | Region IV-A (CALABARZON) | Quezon | General Nakar | Mahabang Lalim | 14.6897 | 121.5509 | R | 701 | 3.8 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.1 | 30.23 | Tier 1B: High GIDA Priority | 39.91 | 39.91 | 75.41 | 57.66 | F - Nearest node and line over 5 km | 8.1 | 30.19 | Node: RLQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1622
2 | 623 | 1623 | 0401005044 | Region IV-A (CALABARZON) | Batangas | Batangas City | Malitam | 13.7442 | 121.0586 | U | 8817 | 3.6 | 2449 | 735 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 1.32 | Tier 2B: Moderate GIDA Inclusion | 65.18 | 65.18 | 50.12 | 57.65 | D - Other node or line within 3 km | 2.02 | 1.32 | Line: AE TO ELIMINATE COMMON 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1623
2 | 624 | 1624 | 0501610010 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Villa San Isidro | 14.1683 | 122.2155 | R | 268 | 4 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.49 | 17.73 | Tier 1B: High GIDA Priority | 43.42 | 43.42 | 71.88 | 57.65 | F - Nearest node and line over 5 km | 6.49 | 17.73 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1624
2 | 625 | 1625 | 0603002030 | Region VI (Western Visayas) | Iloilo | Alimodian | Lico | 10.7766 | 122.3563 | R | 331 | 3.8 | 87 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.17 | 5.42 | Tier 1B: High GIDA Priority | 39.12 | 39.12 | 76.17 | 57.65 | F - Nearest node and line over 5 km | 11.17 | 5.25 | Line: 17,509 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1625
2 | 626 | 1626 | 0300804048 | Region III (Central Luzon) | Bataan | Dinalupihan | Pentor | 14.8711 | 120.4739 | R | 3429 | 3.6 | 952 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.82 | Tier 2A: High Commercial ROI | 70.2 | 70.2 | 45.07 | 57.64 | B - Node 0.5-1 km | 0.91 | 0.71 | Line: 96 CORE 8X12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1626
2 | 627 | 1627 | 0702234024 | Region VII (Central Visayas) | Cebu | City of Naga | Tangke | 10.2162 | 123.7533 | U | 5288 | 3.8 | 1392 | 418 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.86 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 63.97 | 63.97 | 51.3 | 57.64 | D - Other node or line within 3 km | 2.96 | 0.7 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1627
2 | 628 | 1628 | 0300809025 | Region III (Central Luzon) | Bataan | Orani | Apollo | 14.802 | 120.5248 | R | 1948 | 3.6 | 541 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 59.51 | 59.51 | 55.77 | 57.64 | C - Line within 0.5 km; node over 1 km | 1.24 | 0.12 | Line: 96C DONA TO ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1628
2 | 629 | 1629 | 0401019049 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 1 | 14.0773 | 120.6721 | R | 1444 | 3.6 | 401 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.17 | 1.49 | Tier 1B: High GIDA Priority | 51.77 | 51.77 | 63.51 | 57.64 | D - Other node or line within 3 km | 4.17 | 1.49 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1629
2 | 630 | 1630 | 0205010023 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Alang Salacsac | 16.2827 | 120.8492 | R | 701 | 3.8 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.4 | 9.22 | Tier 1B: High GIDA Priority | 38.58 | 38.58 | 76.71 | 57.64 | F - Nearest node and line over 5 km | 9.4 | 9.12 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1630
2 | 631 | 1631 | 1102315041 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Pedro | 7.2975 | 125.7109 | U | 3465 | 3.7 | 936 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.39 | 3.23 | Tier 1B: High GIDA Priority | 55.82 | 55.82 | 59.44 | 57.63 | E - Nearest node or line 3-5 km | 3.39 | 3.22 | Line: DAVAO CITY - TRENTO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1631
2 | 632 | 1632 | 1381100029 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 29 | 14.5256 | 121.0419 | U | 1634 | 3.24 | 504 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 1.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.01 | 46.01 | 69.26 | 57.63 | D - Other node or line within 3 km | 1.25 | 1.07 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1632
2 | 633 | 1633 | 1408104016 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Magabta | 18.028 | 121.1999 | R | 194 | 4.2 | 46 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 9.04 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.03 | 44.03 | 71.24 | 57.63 | D - Other node or line within 3 km | 2.2 | 41.68 | Node: KOY001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1633
2 | 634 | 1634 | 1380610024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 709 | 13.3665 | 120.4019 | U | 5339 | 3.05 | 1749 | 525 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.58 | 54.99 | Tier 1B: High GIDA Priority | 43.27 | 43.27 | 71.98 | 57.63 | F - Nearest node and line over 5 km | 56.58 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1634
2 | 635 | 1635 | 1380606208 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 601 | 11.7438 | 120.7963 | U | 7765 | 4.6 | 1689 | 507 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.29 | 73.23 | Tier 1B: High GIDA Priority | 43.1 | 43.1 | 72.16 | 57.63 | F - Nearest node and line over 5 km | 66.29 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1635
2 | 636 | 1636 | 0405627038 | Region IV-A (CALABARZON) | Quezon | Mauban | Santo Niño | 14.0893 | 121.8155 | R | 385 | 3.8 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.34 | 8.68 | Tier 1B: High GIDA Priority | 32.89 | 32.89 | 82.36 | 57.63 | F - Nearest node and line over 5 km | 14.34 | 8.64 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1636
2 | 637 | 1637 | 0301408006 | Region III (Central Luzon) | Bulacan | Guiguinto | Poblacion | 14.8286 | 120.8791 | U | 3625 | 3.5 | 1036 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.67 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 63.43 | 63.43 | 51.82 | 57.62 | B - Node 0.5-1 km | 0.67 | 0.07 | Line: GUIGUINTO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1637
2 | 638 | 1638 | 0301402011 | Region III (Central Luzon) | Bulacan | Balagtas | Wawa | 14.8176 | 120.9055 | U | 5090 | 3.5 | 1454 | 436 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.73 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 60.19 | 60.19 | 55.06 | 57.62 | C - Line within 0.5 km; node over 1 km | 3.73 | 0.08 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1638
2 | 639 | 1639 | 1381300040 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa IV | 14.6834 | 121.0253 | U | 1911 | 3.9 | 490 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.68 | 46.68 | 68.56 | 57.62 | B - Node 0.5-1 km | 0.71 | 0.26 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1639
2 | 640 | 1640 | 1380606007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 401 | 13.952 | 122.3466 | U | 2112 | 3.65 | 579 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.12 | 1.78 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.59 | 46.59 | 68.64 | 57.62 | D - Other node or line within 3 km | 2.12 | 1.78 | Line: GCQ001 TO TKQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1640
2 | 641 | 1641 | 0201519004 | Region II (Cagayan Valley) | Cagayan | Peñablanca | Bical | 17.5631 | 121.8248 | R | 1936 | 3.9 | 496 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.26 | 4.61 | Tier 1B: High GIDA Priority | 44.43 | 44.43 | 70.82 | 57.62 | E - Nearest node or line 3-5 km | 12.26 | 4.6 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1641
2 | 642 | 1642 | 0806008001 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Bagacay | 11.8177 | 125.232 | R | 1378 | 4.1 | 336 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 68.97 | 71.54 | Tier 1B: High GIDA Priority | 40.75 | 40.75 | 74.48 | 57.61 | F - Nearest node and line over 5 km | 68.97 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1642
2 | 643 | 1643 | 0201513056 | Region II (Cagayan Valley) | Cagayan | Gattaran | Bolos Point | 18.0294 | 122.1773 | R | 945 | 3.9 | 242 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.5 | 32.1 | Tier 1B: High GIDA Priority | 32.1 | 32.1 | 83.13 | 57.61 | F - Nearest node and line over 5 km | 31.5 | 32.08 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1643
2 | 644 | 1644 | 0102820008 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Fernando | 18.1531 | 120.6091 | R | 1148 | 3.7 | 310 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.54 | 2.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.78 | 47.78 | 67.41 | 57.6 | D - Other node or line within 3 km | 2.54 | 2.32 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1644
2 | 645 | 1645 | 1108604014 | Region XI (Davao Region) | Davao Occidental | Santa Maria | San Juan | 6.4045 | 125.4183 | R | 1641 | 3.6 | 456 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.3 | 11.98 | Tier 1B: High GIDA Priority | 43.58 | 43.58 | 71.63 | 57.6 | F - Nearest node and line over 5 km | 13.3 | 11.96 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1645
2 | 646 | 1646 | 1906619003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Omar | Capual Island | 17.2555 | 122.2296 | U | 8706 | 6 | 1451 | 435 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 43.11 | 43.11 | 72.09 | 57.6 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1646
2 | 647 | 1647 | 0401006031 | Region IV-A (CALABARZON) | Batangas | Bauan | San Andres Proper | 13.7828 | 120.9974 | R | 2576 | 3.6 | 716 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 1.43 | Tier 2B: Moderate GIDA Inclusion | 63.89 | 63.89 | 51.28 | 57.59 | D - Other node or line within 3 km | 1.44 | 1.43 | Line: UG BUN001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1647
2 | 648 | 1648 | 1381300131 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Villa Maria Clara | 14.6378 | 121.1304 | U | 2807 | 4 | 701 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.94 | Tier 1B: High GIDA Priority | 51.19 | 51.19 | 64 | 57.59 | D - Other node or line within 3 km | 1.23 | 0.94 | Line: Aerial 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1648
2 | 649 | 1649 | 1102506007 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Monserrat | 6.6005 | 126.0908 | R | 2052 | 3.6 | 570 | 171 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.01 | 31.01 | Tier 1B: High GIDA Priority | 41.42 | 41.42 | 73.76 | 57.59 | F - Nearest node and line over 5 km | 34.01 | 31 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1649
2 | 650 | 1650 | 1003519005 | Region X (Northern Mindanao) | Lanao del Norte | Sapad | Gamal | 7.8518 | 123.8516 | R | 593 | 4.2 | 141 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.02 | 10.42 | Tier 1B: High GIDA Priority | 36.96 | 36.96 | 78.21 | 57.59 | F - Nearest node and line over 5 km | 22.02 | 10.39 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1650
2 | 651 | 1651 | 1380300017 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Pinagkaisahan | 14.5566 | 121.0455 | U | 5323 | 3.59 | 1484 | 445 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 0.29 | Tier 1B: High GIDA Priority | 57.64 | 57.64 | 57.52 | 57.58 | D - Other node or line within 3 km | 2.04 | 1.24 | Line: UG 144C via V-DUCT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1651
2 | 652 | 1652 | 1907004006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tubig Indangan | 17.2559 | 122.2299 | R | 4140 | 5.8 | 714 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.44 | Tier 1B: High GIDA Priority | 47.75 | 47.75 | 67.41 | 57.58 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1652
2 | 653 | 1653 | 0405605040 | Region IV-A (CALABARZON) | Quezon | Buenavista | Villa Magsaysay | 13.7389 | 122.3899 | R | 576 | 3.8 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.43 | 6.01 | Tier 1B: High GIDA Priority | 44.39 | 44.39 | 70.77 | 57.58 | F - Nearest node and line over 5 km | 7.43 | 5.84 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1653
2 | 654 | 1654 | 1381100181 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 181 | 14.7653 | 121.0342 | U | 1918 | 4.09 | 469 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 1.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.67 | 44.67 | 70.47 | 57.57 | D - Other node or line within 3 km | 1.51 | 1.03 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1654
2 | 655 | 1655 | 1003511024 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Tombador | 8.0069 | 123.8791 | R | 544 | 4.2 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.68 | 9.32 | Tier 1B: High GIDA Priority | 43.53 | 43.53 | 71.61 | 57.57 | F - Nearest node and line over 5 km | 9.68 | 9.26 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1655
2 | 656 | 1656 | 0201529001 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Annafunan East | 17.6433 | 121.7205 | R | 5084 | 3.9 | 1304 | 391 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.97 | 1.84 | Tier 2B: Moderate GIDA Inclusion | 68.07 | 68.07 | 47.04 | 57.56 | D - Other node or line within 3 km | 2.97 | 1.78 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1656
2 | 657 | 1657 | 0201512001 | Region II (Cagayan Valley) | Cagayan | Enrile | Alibago | 17.5727 | 121.7428 | R | 2285 | 3.9 | 586 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.09 | 2.47 | Tier 1B: High GIDA Priority | 52.73 | 52.73 | 62.38 | 57.56 | D - Other node or line within 3 km | 5.09 | 2.43 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1657
2 | 658 | 1658 | 1381100002 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 2 | 14.5415 | 120.9972 | U | 1332 | 3.66 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.3 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.88 | 43.88 | 71.24 | 57.56 | A - Node within 0.5 km | 0.45 | 0.24 | Line: Existing 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1658
2 | 659 | 1659 | 1381300021 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Claro | 14.6576 | 121.0337 | U | 3996 | 3.44 | 1162 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 59.55 | 59.55 | 55.53 | 57.54 | A - Node within 0.5 km | 0.45 | 0.16 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1659
2 | 660 | 1660 | 1908709004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Datu Macarimbang Biruar | 17.2541 | 122.2282 | R | 3883 | 4.3 | 903 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 48.24 | 48.24 | 66.83 | 57.54 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1660
2 | 661 | 1661 | 0102931007 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Pangotan | 16.8593 | 120.5186 | R | 381 | 3.8 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.66 | 7.84 | Tier 1B: High GIDA Priority | 40.38 | 40.38 | 74.7 | 57.54 | F - Nearest node and line over 5 km | 10.66 | 7.82 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1661
2 | 662 | 1662 | 0201509009 | Region II (Cagayan Valley) | Cagayan | Calayan | Babuyan Claro | 19.4962 | 121.9323 | R | 1964 | 3.9 | 504 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 115.99 | 112.93 | Tier 1B: High GIDA Priority | 38.56 | 38.56 | 76.49 | 57.53 | F - Nearest node and line over 5 km | 115.99 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1662
2 | 663 | 1663 | 0304908011 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Nicolas | 15.3037 | 120.9361 | U | 14324 | 3.5 | 4093 | 1228 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.04 | 0.07 | Tier 2A: High Commercial ROI | 74.07 | 74.07 | 40.96 | 57.52 | C - Line within 0.5 km; node over 1 km | 2.01 | 0.04 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1663
2 | 664 | 1664 | 0401003005 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 11 | 13.9343 | 120.7328 | R | 1479 | 3.6 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.54 | Tier 1B: High GIDA Priority | 56.06 | 56.06 | 58.99 | 57.52 | D - Other node or line within 3 km | 1.14 | 0.53 | Line: UG NSB001 TO BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1664
2 | 665 | 1665 | 0301403005 | Region III (Central Luzon) | Bulacan | Baliuag | Concepcion | 14.9527 | 120.8889 | U | 10619 | 3.5 | 3034 | 910 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 69.8 | 69.8 | 45.22 | 57.51 | B - Node 0.5-1 km | 0.53 | 0.31 | Line: SanLuis-Candaba Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 1665
2 | 666 | 1666 | 1381100089 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 89 | 14.5918 | 121.1047 | U | 1432 | 3.21 | 446 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.79 | 43.79 | 71.23 | 57.51 | C - Line within 0.5 km; node over 1 km | 1.67 | 0.34 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1666
2 | 667 | 1667 | 1004326012 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Poblacion 2 | 8.5843 | 124.7717 | R | 2792 | 3.9 | 716 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 64.65 | 64.65 | 50.33 | 57.49 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.11 | Line: As built-kmz | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1667
2 | 668 | 1668 | 1204712003 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Balabak | 7.1216 | 124.7205 | R | 3628 | 3.8 | 955 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.33 | 9.28 | Tier 1B: High GIDA Priority | 56.32 | 56.32 | 58.65 | 57.49 | F - Nearest node and line over 5 km | 12.33 | 9.28 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1668
2 | 669 | 1669 | 0103318004 | Region I (Ilocos Region) | La Union | Santol | Lettac Sur | 16.7382 | 120.454 | R | 1348 | 3.7 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.23 | 6.06 | Tier 1B: High GIDA Priority | 48.12 | 48.12 | 66.87 | 57.49 | F - Nearest node and line over 5 km | 9.23 | 6.05 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1669
2 | 670 | 1670 | 1208007022 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Panamin | 6.3745 | 125.3792 | R | 1683 | 3.9 | 432 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.71 | 9.74 | Tier 1B: High GIDA Priority | 43.41 | 43.41 | 71.56 | 57.49 | F - Nearest node and line over 5 km | 12.71 | 9.74 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1670
2 | 671 | 1671 | 0802623024 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | San Pablo | 11.879 | 125.3611 | R | 712 | 3.9 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.12 | 83.42 | Tier 1B: High GIDA Priority | 37.3 | 37.3 | 77.67 | 57.49 | F - Nearest node and line over 5 km | 81.12 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1671
2 | 672 | 1672 | 0401019039 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Pantalan | 14.0832 | 120.6342 | R | 3962 | 3.6 | 1101 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.69 | Tier 2B: Moderate GIDA Inclusion | 69.55 | 69.55 | 45.4 | 57.48 | D - Other node or line within 3 km | 1.39 | 0.68 | Line: NASUGBU UPLINK | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1672
2 | 673 | 1673 | 1381000008 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Don Bosco | 14.4886 | 121.0261 | U | 56113 | 3.63 | 15454 | 4636 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.54 | 0.17 | Tier 1B: High GIDA Priority | 55.51 | 55.51 | 59.44 | 57.48 | B - Node 0.5-1 km | 0.54 | 0.13 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1673
2 | 674 | 1674 | 1380601099 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 99 | 12.2565 | 123.1451 | U | 3682 | 3.24 | 1138 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.42 | 34.86 | Tier 1B: High GIDA Priority | 41.46 | 41.46 | 73.49 | 57.48 | F - Nearest node and line over 5 km | 18.42 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1674
2 | 675 | 1675 | 0405804026 | Region IV-A (CALABARZON) | Rizal | Binangonan | Palangoy | 14.507 | 121.1873 | U | 17102 | 3.6 | 4751 | 1425 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.67 | 1.66 | Tier 2A: High Commercial ROI | 70.89 | 70.89 | 44.06 | 57.47 | D - Other node or line within 3 km | 1.67 | 1.66 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1675
2 | 676 | 1676 | 0301407001 | Region III (Central Luzon) | Bulacan | Calumpit | Balite | 14.8984 | 120.7864 | U | 5243 | 3.5 | 1498 | 449 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 62.21 | 62.21 | 52.74 | 57.47 | D - Other node or line within 3 km | 2.19 | 0.77 | Line: Calumpit-Baliuag Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1676
2 | 677 | 1677 | 0405802009 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Roque | 14.5844 | 121.1737 | U | 67126 | 3.6 | 18646 | 5594 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.35 | 0.26 | Tier 1B: High GIDA Priority | 55.33 | 55.33 | 59.6 | 57.47 | A - Node within 0.5 km | 0.35 | 0.08 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1677
2 | 678 | 1678 | 1381100054 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 54 | 14.5521 | 121.0011 | U | 1499 | 3.47 | 432 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.6 | 44.6 | 70.34 | 57.47 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.27 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1678
2 | 679 | 1679 | 1380606030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 424 | 13.9306 | 121.5839 | U | 2079 | 4.17 | 498 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 1.74 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.34 | 44.34 | 70.6 | 57.47 | D - Other node or line within 3 km | 2.16 | 1.72 | Line: UG LCQ001 TO SJB002 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1679
2 | 680 | 1680 | 0205010012 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Kayapa Proper East | 16.2834 | 120.8685 | R | 254 | 3.8 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.56 | 8.46 | Tier 1B: High GIDA Priority | 38.09 | 38.09 | 76.84 | 57.47 | F - Nearest node and line over 5 km | 8.56 | 8.21 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1680
2 | 681 | 1681 | 1381100151 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 151 | 14.7022 | 121.1098 | U | 1123 | 3.04 | 369 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 1.49 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.63 | 43.63 | 71.29 | 57.46 | B - Node 0.5-1 km | 0.66 | 1.42 | Node: QCY069 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 1681
2 | 682 | 1682 | 0502011023 | Region V (Bicol Region) | Catanduanes | Virac | Dugui Too | 13.6479 | 124.1836 | R | 1416 | 4.2 | 337 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 37.33 | 58.07 | Tier 1B: High GIDA Priority | 36.5 | 36.5 | 78.42 | 57.46 | F - Nearest node and line over 5 km | 37.33 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1682
2 | 683 | 1683 | 0306902001 | Region III (Central Luzon) | Tarlac | Bamban | Anupul | 15.2937 | 120.5629 | U | 22732 | 3.9 | 5829 | 1749 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.24 | 0.46 | Tier 2A: High Commercial ROI | 70.58 | 70.58 | 44.31 | 57.45 | C - Line within 0.5 km; node over 1 km | 1.24 | 0.24 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1683
2 | 684 | 1684 | 0403405001 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bagong Kalsada | 14.1899 | 121.1354 | U | 4266 | 3.3 | 1293 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 62.59 | 62.59 | 52.3 | 57.45 | C - Line within 0.5 km; node over 1 km | 1.42 | 0.22 | Line: CLB001 TO SPO001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1684
2 | 685 | 1685 | 0402111010 | Region IV-A (CALABARZON) | Cavite | Kawit | Tabon I | 14.4401 | 120.9194 | U | 5537 | 3.4 | 1629 | 489 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 61.27 | 61.27 | 53.64 | 57.45 | D - Other node or line within 3 km | 3.05 | 0.72 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1685
2 | 686 | 1686 | 0402117011 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa I | 14.4118 | 120.8479 | U | 5802 | 3.4 | 1706 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 2.19 | Tier 2B: Moderate GIDA Inclusion | 59.2 | 59.2 | 55.67 | 57.44 | D - Other node or line within 3 km | 2.15 | 2.19 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1686
2 | 687 | 1687 | 1705205016 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Camilmil | 13.4043 | 121.1775 | U | 4121 | 3.9 | 1057 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.86 | 3.34 | Tier 2B: Moderate GIDA Inclusion | 57.83 | 57.83 | 57.04 | 57.44 | D - Other node or line within 3 km | 2.86 | 3.32 | Node: CLM002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1687
2 | 688 | 1688 | 1380608002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 659-A | 11.8055 | 122.476 | U | 3547 | 2.03 | 1749 | 525 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.88 | 9.62 | Tier 1B: High GIDA Priority | 43.27 | 43.27 | 71.6 | 57.44 | F - Nearest node and line over 5 km | 16.88 | 15.93 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1688
2 | 689 | 1689 | 1908824012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Talayan | 17.2551 | 122.2291 | U | 5829 | 4.7 | 1240 | 372 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 42.49 | 42.49 | 72.39 | 57.44 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1689
2 | 690 | 1690 | 0203109013 | Region II (Cagayan Valley) | Isabela | Cordon | Quirino | 16.6867 | 121.4553 | R | 2847 | 3.8 | 749 | 225 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.71 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 59.39 | 59.39 | 55.47 | 57.43 | D - Other node or line within 3 km | 7.71 | 1.77 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1690
2 | 691 | 1691 | 0401019009 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 4 | 14.0735 | 120.6335 | R | 1373 | 3.6 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.14 | Tier 1B: High GIDA Priority | 56.91 | 56.91 | 57.95 | 57.43 | A - Node within 0.5 km | 0.31 | 0.08 | Line: NASUGBU UPLINK | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1691
2 | 692 | 1692 | 1380200011 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | B. F. International Village | 14.4603 | 120.9989 | U | 80621 | 4.08 | 19757 | 5927 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.59 | 0.45 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 50.04 | 50.04 | 64.83 | 57.43 | B - Node 0.5-1 km | 0.59 | 0.44 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1692
2 | 693 | 1693 | 1908705020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Linek | 17.2539 | 122.228 | R | 4505 | 4.3 | 1048 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 49.44 | 49.44 | 65.42 | 57.43 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1693
2 | 694 | 1694 | 0704603015 | Region VII (Central Visayas) | Negros Oriental | Bacong | Sacsac | 9.2547 | 123.2901 | R | 4372 | 3.8 | 1151 | 345 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.21 | Tier 2A: High Commercial ROI | 79.83 | 79.83 | 35.02 | 57.42 | A - Node within 0.5 km | 0.23 | 0.22 | Line: PROPOSED AERIAL FOC- 58.765km | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1694
2 | 695 | 1695 | 0203105007 | Region II (Cagayan Valley) | Isabela | Burgos | Cullalabo San Antonio | 17.0888 | 121.7049 | R | 3513 | 3.8 | 924 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 0.49 | Tier 2A: High Commercial ROI | 75.97 | 75.97 | 38.88 | 57.42 | A - Node within 0.5 km | 0.25 | 0.26 | Node: BUI001 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1695
2 | 696 | 1696 | 0306902013 | Region III (Central Luzon) | Tarlac | Bamban | San Roque | 15.2763 | 120.5662 | U | 12502 | 3.9 | 3206 | 962 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 69.63 | 69.63 | 45.21 | 57.42 | B - Node 0.5-1 km | 0.88 | 0.17 | Line: 48 CORE (6X8) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1696
2 | 697 | 1697 | 0403425021 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Calendola | 14.3787 | 121.3667 | R | 4162 | 3.3 | 1261 | 378 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.93 | 7.15 | Tier 2B: Moderate GIDA Inclusion | 63.19 | 63.19 | 51.65 | 57.42 | E - Nearest node or line 3-5 km | 3.93 | 7.14 | Node: PKL002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1697
2 | 698 | 1698 | 1381000012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Antonio | 14.4608 | 121.0307 | U | 73832 | 3.52 | 20952 | 6286 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 0.84 | 0.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.05 | 48.05 | 66.77 | 57.41 | B - Node 0.5-1 km | 0.84 | 0.15 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1698
2 | 699 | 1699 | 1402706027 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Palaad | 16.9157 | 121.2081 | R | 314 | 3.9 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.22 | 15.02 | Tier 1B: High GIDA Priority | 47.2 | 47.2 | 67.63 | 57.41 | E - Nearest node or line 3-5 km | 3.22 | 14.86 | Node: MOF002 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1699
2 | 700 | 1700 | 1381100059 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 59 | 14.5442 | 121.0813 | U | 1514 | 3.79 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.71 | 43.71 | 71.1 | 57.41 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.26 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1700
2 | 701 | 1701 | 1380611042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 827 | 13.9909 | 122.4321 | U | 2719 | 3.84 | 708 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.61 | 4.51 | Tier 1B: High GIDA Priority | 43.65 | 43.65 | 71.18 | 57.41 | E - Nearest node or line 3-5 km | 4.61 | 4.49 | Line: CALAUAG - SIPOCOT | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1701
2 | 702 | 1702 | 1380614073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 880 | 13.2943 | 123.123 | U | 3751 | 3.89 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.44 | 24.97 | Tier 1B: High GIDA Priority | 43.36 | 43.36 | 71.45 | 57.41 | F - Nearest node and line over 5 km | 12.44 | 24.88 | Node: BNC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1702
2 | 703 | 1703 | 1003511017 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Rarab | 8.0472 | 123.8982 | R | 749 | 4.2 | 178 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.91 | 6.55 | Tier 1B: High GIDA Priority | 43.12 | 43.12 | 71.7 | 57.41 | F - Nearest node and line over 5 km | 10.91 | 6.55 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1703
2 | 704 | 1704 | 0600406003 | Region VI (Western Visayas) | Aklan | Ibajay | Antipolo | 11.8015 | 122.1226 | R | 844 | 3.9 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.88 | 1.67 | Tier 1B: High GIDA Priority | 39.11 | 39.11 | 75.71 | 57.41 | F - Nearest node and line over 5 km | 20.88 | 27.39 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1704
2 | 705 | 1705 | 1705303010 | MIMAROPA Region | Palawan | Araceli | San Jose De Oro | 10.5904 | 119.8683 | R | 719 | 3.9 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.04 | 42.88 | Tier 1B: High GIDA Priority | 36.08 | 36.08 | 78.72 | 57.4 | F - Nearest node and line over 5 km | 34.04 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1705
2 | 706 | 1706 | 0301423016 | Region III (Central Luzon) | Bulacan | Santa Maria | Poblacion | 14.822 | 120.9625 | U | 13454 | 3.5 | 3844 | 1153 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.33 | 0.3 | Tier 2A: High Commercial ROI | 72.68 | 72.68 | 42.1 | 57.39 | A - Node within 0.5 km | 0.33 | 0.08 | Line: STA MARIA TOC Link | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1706
2 | 707 | 1707 | 0300806007 | Region III (Central Luzon) | Bataan | Limay | Poblacion | 14.5464 | 120.5841 | R | 682 | 3.6 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.96 | 0.55 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.5 | 47.5 | 67.28 | 57.39 | D - Other node or line within 3 km | 2.96 | 0.54 | Line: PIPE ORION-MARIVELES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1707
2 | 708 | 1708 | 0301407013 | Region III (Central Luzon) | Bulacan | Calumpit | Iba Este | 14.8912 | 120.7677 | U | 4349 | 3.5 | 1243 | 373 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 1.11 | Tier 2B: Moderate GIDA Inclusion | 62.22 | 62.22 | 52.55 | 57.38 | D - Other node or line within 3 km | 1.68 | 1.1 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1708
2 | 709 | 1709 | 0402123011 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Francisco Reyes | 14.3042 | 121.0269 | U | 8348 | 3.4 | 2455 | 736 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 2.6 | Tier 2B: Moderate GIDA Inclusion | 62.07 | 62.07 | 52.69 | 57.38 | D - Other node or line within 3 km | 1.77 | 2.6 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1709
2 | 710 | 1710 | 0301410021 | Region III (Central Luzon) | Bulacan | City of Malolos | Catmon | 14.8504 | 120.8136 | U | 2350 | 3.5 | 671 | 201 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.67 | 0.27 | Tier 1B: High GIDA Priority | 56.61 | 56.61 | 58.14 | 57.38 | B - Node 0.5-1 km | 0.67 | 0.35 | Line: 24 CORE (PRISMIAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1710
2 | 711 | 1711 | 0506207029 | Region V (Bicol Region) | Sorsogon | Donsol | Parina | 12.9667 | 123.5667 | R | 231 | 4 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.45 | 17.01 | Tier 1B: High GIDA Priority | 43.16 | 43.16 | 71.6 | 57.38 | F - Nearest node and line over 5 km | 7.45 | 16.92 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1711
2 | 712 | 1712 | 0704619008 | Region VII (Central Visayas) | Negros Oriental | Siaton | Casala-an | 9.1248 | 123.0333 | R | 4277 | 3.8 | 1126 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.05 | 7.04 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 50.41 | 57.37 | F - Nearest node and line over 5 km | 7.05 | 31.31 | Node: SIA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1712
2 | 713 | 1713 | 0203131016 | Region II (Cagayan Valley) | Isabela | San Mariano | Disusuan | 16.9834 | 122.0562 | R | 656 | 3.8 | 173 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.6 | 21.27 | Tier 1B: High GIDA Priority | 41.94 | 41.94 | 72.8 | 57.37 | E - Nearest node or line 3-5 km | 4.6 | 21.26 | Node: SOI001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1713
2 | 714 | 1714 | 0504113004 | Region V (Bicol Region) | Masbate | Mobo | Barag | 12.2157 | 123.6476 | R | 526 | 4.1 | 128 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.13 | 12.99 | Tier 1B: High GIDA Priority | 42.84 | 42.84 | 71.89 | 57.36 | F - Nearest node and line over 5 km | 12.13 | 12.99 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1714
2 | 715 | 1715 | 0501603027 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay IV | 14.117 | 122.949 | U | 7810 | 4 | 1952 | 586 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 1.18 | Tier 2B: Moderate GIDA Inclusion | 69.11 | 69.11 | 45.59 | 57.35 | B - Node 0.5-1 km | 0.58 | 1.18 | Node: DEC001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1715
2 | 716 | 1716 | 0102916013 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Lucbuban | 17.1293 | 120.5434 | R | 562 | 3.8 | 148 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 9.55 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 48.14 | 48.14 | 66.57 | 57.35 | D - Other node or line within 3 km | 2.35 | 9.55 | Node: SDI001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1716
2 | 717 | 1717 | 1381100164 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 164 | 14.4876 | 121.2093 | U | 1799 | 3.66 | 492 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.65 | 1.13 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.05 | 45.05 | 69.66 | 57.35 | D - Other node or line within 3 km | 1.65 | 1.13 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1717
2 | 718 | 1718 | 1908822009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Pilar | 17.2551 | 122.2291 | U | 6086 | 4.7 | 1295 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 42.65 | 42.65 | 72.06 | 57.35 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1718
2 | 719 | 1719 | 0305415031 | Region III (Central Luzon) | Pampanga | Porac | Sta. Cruz | 15.083 | 120.53 | U | 19760 | 4 | 4940 | 1482 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.5 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 69.73 | 69.73 | 44.94 | 57.34 | D - Other node or line within 3 km | 2.5 | 1.67 | Line: 24 CORE (3X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1719
2 | 720 | 1720 | 0401005014 | Region IV-A (CALABARZON) | Batangas | Batangas City | Calicanto | 13.7669 | 121.0534 | U | 11089 | 3.6 | 3080 | 924 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 69.58 | 69.58 | 45.11 | 57.34 | B - Node 0.5-1 km | 0.63 | 0.13 | Line: WP BYB001 TO BCY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1720
2 | 721 | 1721 | 1380614093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 900 | 11.8293 | 122.8515 | U | 8689 | 3.94 | 2204 | 661 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.81 | 7.06 | Tier 1B: High GIDA Priority | 44.61 | 44.61 | 70.04 | 57.33 | F - Nearest node and line over 5 km | 28.99 | 999999 | Node: RCZ001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1721
2 | 722 | 1722 | 1600303039 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Kinamaybay | 8.6011 | 125.9153 | R | 886 | 3.9 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.27 | Tier 1B: High GIDA Priority | 53.31 | 53.31 | 61.33 | 57.32 | B - Node 0.5-1 km | 0.88 | 0.27 | Line: TRENTO - BUENAVISTA CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 1722
2 | 723 | 1723 | 1381100175 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 175 | 14.7091 | 121.1495 | U | 1959 | 3.63 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 1.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.28 | 45.28 | 69.36 | 57.32 | D - Other node or line within 3 km | 2.3 | 1.34 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1723
2 | 724 | 1724 | 1108601013 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Mabuhay | 6.2348 | 125.6912 | R | 2305 | 3.6 | 640 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.91 | 47.16 | Tier 1B: High GIDA Priority | 42.79 | 42.79 | 71.85 | 57.32 | F - Nearest node and line over 5 km | 47.91 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1724
2 | 725 | 1725 | 0403405045 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Prinza | 14.2007 | 121.1405 | U | 5792 | 3.3 | 1755 | 526 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 65.3 | 65.3 | 49.3 | 57.3 | B - Node 0.5-1 km | 0.73 | 0.05 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 1725
2 | 726 | 1726 | 0200901002 | Region II (Cagayan Valley) | Batanes | Basco | Ihubok I | 20.4434 | 121.9633 | U | 1778 | 3 | 593 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 223.03 | 216.78 | Tier 1B: High GIDA Priority | 37.99 | 37.99 | 76.62 | 57.3 | F - Nearest node and line over 5 km | 219.88 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1726
2 | 727 | 1727 | 0402111005 | Region IV-A (CALABARZON) | Cavite | Kawit | Panamitan | 14.4369 | 120.8931 | R | 3577 | 3.4 | 1052 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 69.46 | 69.46 | 45.12 | 57.29 | D - Other node or line within 3 km | 1.36 | 0.74 | Line: KAWIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1727
2 | 728 | 1728 | 0403426011 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Pagsawitan | 14.2651 | 121.4252 | U | 11162 | 3.3 | 3382 | 1015 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.02 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 68.04 | 68.04 | 46.53 | 57.29 | C - Line within 0.5 km; node over 1 km | 2.02 | 0.14 | Line: UG SCL001 TO LWL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1728
2 | 729 | 1729 | 0306916056 | Region III (Central Luzon) | Tarlac | City of Tarlac | Paraiso | 15.443 | 120.5987 | R | 3583 | 3.9 | 919 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.61 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 67.36 | 67.36 | 47.22 | 57.29 | C - Line within 0.5 km; node over 1 km | 2.61 | 0.08 | Line: CITY OF TARLAC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1729
2 | 730 | 1730 | 1907004002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Manuk Mangkaw | 17.2558 | 122.2299 | R | 4168 | 5.8 | 719 | 216 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 47.92 | 47.92 | 66.66 | 57.29 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1730
2 | 731 | 1731 | 1102401022 | Region XI (Davao Region) | Davao del Sur | Bansalan | Tinongtongan | 6.813 | 125.2595 | R | 1056 | 3.4 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.17 | 12.87 | Tier 1B: High GIDA Priority | 46.06 | 46.06 | 68.52 | 57.29 | F - Nearest node and line over 5 km | 6.17 | 12.86 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1731
2 | 732 | 1732 | 0205009023 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Tadji | 16.3902 | 121.3966 | R | 1104 | 3.8 | 291 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.65 | 21.36 | Tier 1B: High GIDA Priority | 37.9 | 37.9 | 76.68 | 57.29 | F - Nearest node and line over 5 km | 13.65 | 21.35 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1732
2 | 733 | 1733 | 0300811019 | Region III (Central Luzon) | Bataan | Pilar | Panilao | 14.6699 | 120.5512 | U | 6118 | 3.6 | 1699 | 510 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 63.65 | 63.65 | 50.91 | 57.28 | C - Line within 0.5 km; node over 1 km | 1.66 | 0.09 | Line: 60 CORE 5X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1733
2 | 734 | 1734 | 1381100090 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 90 | 14.4361 | 120.9643 | U | 1506 | 3.67 | 410 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 1.6 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.49 | 43.49 | 71.08 | 57.28 | D - Other node or line within 3 km | 1.29 | 1.6 | Node: BRC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1734
2 | 735 | 1735 | 1003514012 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lingco-an | 8.0313 | 124.0641 | R | 1011 | 4.2 | 241 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.26 | 17.08 | Tier 1B: High GIDA Priority | 39.03 | 39.03 | 75.53 | 57.28 | F - Nearest node and line over 5 km | 23.26 | 17.04 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1735
2 | 736 | 1736 | 0301410020 | Region III (Central Luzon) | Bulacan | City of Malolos | Caniogan | 14.8462 | 120.817 | U | 5455 | 3.5 | 1559 | 468 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 64.72 | 64.72 | 49.83 | 57.27 | B - Node 0.5-1 km | 0.83 | 0.56 | Line: 48 CORE (6X8) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1736
2 | 737 | 1737 | 0201507005 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Cabayu | 18.2901 | 121.4785 | R | 942 | 3.9 | 242 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.25 | 4.84 | Tier 1B: High GIDA Priority | 48.61 | 48.61 | 65.93 | 57.27 | E - Nearest node or line 3-5 km | 4.25 | 4.84 | Node: SMY001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1737
2 | 738 | 1738 | 1001320025 | Region X (Northern Mindanao) | Bukidnon | Talakag | Salucot | 8.0498 | 124.6424 | R | 1959 | 3.8 | 516 | 155 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.36 | 1.98 | Tier 1B: High GIDA Priority | 45.16 | 45.16 | 69.38 | 57.27 | F - Nearest node and line over 5 km | 21.36 | 21.37 | Node: TKB001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1738
2 | 739 | 1739 | 1381100039 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 39 | 14.5771 | 121.0445 | U | 1224 | 3.21 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.35 | 43.35 | 71.2 | 57.27 | B - Node 0.5-1 km | 0.94 | 0.07 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1739
2 | 740 | 1740 | 0501727013 | Region V (Bicol Region) | Camarines Sur | Pasacao | Salvacion | 13.6033 | 122.9375 | R | 993 | 4.2 | 236 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.75 | 12.13 | Tier 1B: High GIDA Priority | 41.3 | 41.3 | 73.21 | 57.26 | F - Nearest node and line over 5 km | 10.75 | 12.13 | Node: LBC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1740
2 | 741 | 1741 | 0300803012 | Region III (Central Luzon) | Bataan | City of Balanga | Malabia | 14.68 | 120.5314 | R | 757 | 3.6 | 210 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.96 | Tier 1B: High GIDA Priority | 50.99 | 50.99 | 63.52 | 57.25 | D - Other node or line within 3 km | 1.04 | 0.96 | Line: CITY OF BALANGA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1741
2 | 742 | 1742 | 1381100080 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 80 | 14.6142 | 121.0731 | U | 1261 | 3.17 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.45 | 43.45 | 71.04 | 57.25 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.27 | Line: UG 144C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1742
2 | 743 | 1743 | 1907005022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | North Larap | 16.4461 | 121.9643 | R | 3176 | 5.8 | 548 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.61 | 20.83 | Tier 1B: High GIDA Priority | 39.85 | 39.85 | 74.65 | 57.25 | F - Nearest node and line over 5 km | 22.61 | 31.69 | Node: JNI002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1743
2 | 744 | 1744 | 0907333004 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Bululawan | 7.867 | 123.1039 | R | 1352 | 3.9 | 347 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.18 | 9.64 | Tier 1B: High GIDA Priority | 42.92 | 42.92 | 71.57 | 57.24 | F - Nearest node and line over 5 km | 16.18 | 9.6 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1744
2 | 745 | 1745 | 1908822002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Bongo | 17.2551 | 122.2291 | R | 2565 | 4.7 | 546 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 38.9 | 38.9 | 75.58 | 57.24 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1745
2 | 746 | 1746 | 0702234011 | Region VII (Central Visayas) | Cebu | City of Naga | Inayagan | 10.2361 | 123.7733 | U | 10585 | 3.8 | 2786 | 836 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.18 | 0.07 | Tier 2A: High Commercial ROI | 72.06 | 72.06 | 42.4 | 57.23 | B - Node 0.5-1 km | 0.69 | 0.06 | Line: CEBU - TOLEDO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1746
2 | 747 | 1747 | 0306916072 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Rafael | 15.4611 | 120.5846 | U | 21903 | 3.9 | 5616 | 1685 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.67 | 1.5 | Tier 2B: Moderate GIDA Inclusion | 67.49 | 67.49 | 46.97 | 57.23 | D - Other node or line within 3 km | 3.67 | 1.5 | Line: 40 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1747
2 | 748 | 1748 | 0300812008 | Region III (Central Luzon) | Bataan | Samal | San Juan | 14.7697 | 120.5395 | R | 4655 | 3.6 | 1293 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.62 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 71.81 | 71.81 | 42.63 | 57.22 | C - Line within 0.5 km; node over 1 km | 3.62 | 0.37 | Line: 36 CORE 3X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1748
2 | 749 | 1749 | 0102934034 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Julian Norte | 17.5717 | 120.3974 | R | 2931 | 3.8 | 771 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.55 | 1.04 | Tier 2B: Moderate GIDA Inclusion | 63.67 | 63.67 | 50.75 | 57.21 | D - Other node or line within 3 km | 2.55 | 0.95 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1749
2 | 750 | 1750 | 0405622050 | Region IV-A (CALABARZON) | Quezon | Lopez | Mandoog | 13.8838 | 122.2953 | R | 262 | 3.8 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.6 | 0.11 | Tier 1B: High GIDA Priority | 44.91 | 44.91 | 69.52 | 57.21 | C - Line within 0.5 km; node over 1 km | 3.6 | 0.03 | Line: LZQ001 TO MCQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1750
2 | 751 | 1751 | 0702232018 | Region VII (Central Visayas) | Cebu | Minglanilla | Vito | 10.2543 | 123.7925 | U | 11385 | 3.8 | 2996 | 899 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 1.04 | Tier 2A: High Commercial ROI | 70.76 | 70.76 | 43.63 | 57.2 | D - Other node or line within 3 km | 1.08 | 1.04 | Line: CEBU - TOLEDO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1751
2 | 752 | 1752 | 0301414007 | Region III (Central Luzon) | Bulacan | Obando | Pag-asa | 14.7203 | 120.9192 | R | 3604 | 3.5 | 1030 | 309 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.24 | 4.09 | Tier 2B: Moderate GIDA Inclusion | 64.71 | 64.71 | 49.69 | 57.2 | D - Other node or line within 3 km | 2.24 | 4.09 | Node: OBB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1752
2 | 753 | 1753 | 0105546032 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Poblacion | 15.9752 | 120.5655 | U | 7343 | 3.6 | 2040 | 612 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.94 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 64.23 | 64.23 | 50.18 | 57.2 | C - Line within 0.5 km; node over 1 km | 1.94 | 0.06 | Line: URDANETA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1753
2 | 754 | 1754 | 0305412019 | Region III (Central Luzon) | Pampanga | Masantol | San Nicolas | 14.8906 | 120.7072 | R | 3980 | 4 | 995 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 1.54 | Tier 2A: High Commercial ROI | 72.02 | 72.02 | 42.35 | 57.19 | A - Node within 0.5 km | 0.1 | 6.69 | Node: MSP001 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1754
2 | 755 | 1755 | 0301404003 | Region III (Central Luzon) | Bulacan | Bocaue | Bambang | 14.7885 | 120.9286 | U | 9241 | 3.5 | 2640 | 792 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 67.19 | 67.19 | 47.19 | 57.19 | C - Line within 0.5 km; node over 1 km | 1.26 | 0.3 | Line: Mnla Pipe | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1755
2 | 756 | 1756 | 0301420050 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael III | 14.7845 | 121.0527 | R | 2841 | 3.5 | 812 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 1.01 | Tier 2B: Moderate GIDA Inclusion | 67.09 | 67.09 | 47.29 | 57.19 | D - Other node or line within 3 km | 1.13 | 0.93 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1756
2 | 757 | 1757 | 1380500013 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Highway Hills | 14.5824 | 121.0494 | U | 49455 | 3.38 | 14625 | 4388 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.2 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 57.28 | 57.28 | 57.11 | 57.19 | A - Node within 0.5 km | 0.2 | 0.04 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1757
2 | 758 | 1758 | 1381100098 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 98 | 14.4472 | 120.9225 | U | 1411 | 3.1 | 455 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.27 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.33 | 42.33 | 72.06 | 57.19 | C - Line within 0.5 km; node over 1 km | 2.81 | 0.27 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1758
2 | 759 | 1759 | 0402116001 | Region IV-A (CALABARZON) | Cavite | Noveleta | Magdiwang | 14.4274 | 120.8848 | U | 2351 | 3.4 | 691 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 57.88 | 57.88 | 56.46 | 57.17 | A - Node within 0.5 km | 0.3 | 0.31 | Node: NVC001 -TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1759
2 | 760 | 1760 | 1381100182 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 182 | 14.3544 | 121.1386 | U | 2938 | 3.95 | 744 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.38 | 5.79 | Tier 1B: High GIDA Priority | 44.08 | 44.08 | 70.24 | 57.16 | F - Nearest node and line over 5 km | 5.38 | 5.76 | Node: SRL004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1760
2 | 761 | 1761 | 1908816008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Kilangan | 17.255 | 122.229 | U | 6210 | 4.7 | 1321 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 42.73 | 42.73 | 71.6 | 57.16 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1761
2 | 762 | 1762 | 1208004013 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Pananag | 5.8837 | 124.8637 | R | 1725 | 3.9 | 442 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 37.13 | 40.68 | Tier 1B: High GIDA Priority | 38.21 | 38.21 | 76.11 | 57.16 | F - Nearest node and line over 5 km | 37.13 | 40.68 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1762
2 | 763 | 1763 | 0403408006 | Region IV-A (CALABARZON) | Laguna | Famy | Batuhan | 14.4723 | 121.4613 | R | 3260 | 3.3 | 988 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.24 | 4.23 | Tier 2B: Moderate GIDA Inclusion | 67.56 | 67.56 | 46.74 | 57.15 | E - Nearest node or line 3-5 km | 3.24 | 4.21 | Node: FYL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1763
2 | 764 | 1764 | 1402703011 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Hucab | 16.7752 | 121.1405 | R | 1768 | 3.9 | 453 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.14 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 59.17 | 59.17 | 55.14 | 57.15 | C - Line within 0.5 km; node over 1 km | 3.14 | 0.19 | Line: FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1764
2 | 765 | 1765 | 1380200017 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Dos | 14.4332 | 120.9846 | U | 44452 | 3.57 | 12459 | 3738 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 2.23 | 1.56 | Tier 1B: High GIDA Priority | 56.29 | 56.29 | 58.01 | 57.15 | D - Other node or line within 3 km | 2.23 | 1.56 | Line: Aerial 216C MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1765
2 | 766 | 1766 | 0506207024 | Region V (Bicol Region) | Sorsogon | Donsol | New Maguisa | 12.9742 | 123.5784 | R | 376 | 4 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.87 | 15.55 | Tier 1B: High GIDA Priority | 42.66 | 42.66 | 71.6 | 57.13 | F - Nearest node and line over 5 km | 7.87 | 15.47 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1766
2 | 767 | 1767 | 0604528032 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 15 | 10.7311 | 123.0103 | U | 8973 | 3.7 | 2425 | 728 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.78 | 1.31 | Tier 2B: Moderate GIDA Inclusion | 64.71 | 64.71 | 49.53 | 57.12 | D - Other node or line within 3 km | 4.78 | 1.29 | Line: TALISAY - BACOLOD (REDUNDANCY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1767
2 | 768 | 1768 | 0402111014 | Region IV-A (CALABARZON) | Cavite | Kawit | Balsahan-Bisita | 14.4567 | 120.9128 | U | 2024 | 3.4 | 595 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 1.09 | Tier 1B: High GIDA Priority | 50.32 | 50.32 | 63.92 | 57.12 | D - Other node or line within 3 km | 3.38 | 1.07 | Line: BACOOR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1768
2 | 769 | 1769 | 1003511001 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Babasalon | 8.0229 | 123.9062 | R | 810 | 4.2 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.99 | 9.39 | Tier 1B: High GIDA Priority | 42.62 | 42.62 | 71.62 | 57.12 | F - Nearest node and line over 5 km | 11.99 | 9.39 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1769
2 | 770 | 1770 | 0405619042 | Region IV-A (CALABARZON) | Quezon | Gumaca | San Isidro Kanluran | 13.9001 | 122.0882 | R | 192 | 3.8 | 51 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.3 | 0.74 | Tier 1B: High GIDA Priority | 45.23 | 45.23 | 68.99 | 57.11 | D - Other node or line within 3 km | 3.3 | 0.67 | Line: AE UNQ001 TO CDQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1770
2 | 771 | 1771 | 1705303012 | MIMAROPA Region | Palawan | Araceli | Taloto | 10.6011 | 119.8953 | R | 636 | 3.9 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.58 | 45.41 | Tier 1B: High GIDA Priority | 35.47 | 35.47 | 78.72 | 57.1 | F - Nearest node and line over 5 km | 36.58 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1771
2 | 772 | 1772 | 0304922005 | Region III (Central Luzon) | Nueva Ecija | Quezon | Dulong Bayan | 15.5544 | 120.8141 | U | 4184 | 3.8 | 1101 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 67.92 | 67.92 | 46.27 | 57.09 | B - Node 0.5-1 km | 0.78 | 0.1 | Line: 38,161m. | Survey short node lateral; confirm port/fiber capacity, access and route. | 1772
2 | 773 | 1773 | 1108604004 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kidadan | 6.5005 | 125.4404 | R | 1168 | 3.6 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.52 | 8.67 | Tier 1B: High GIDA Priority | 42.54 | 42.54 | 71.63 | 57.09 | F - Nearest node and line over 5 km | 10.52 | 8.62 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1773
2 | 774 | 1774 | 1102501007 | Region XI (Davao Region) | Davao Oriental | Baganga | Campawan | 7.574 | 126.56 | R | 2164 | 3.6 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.26 | 62.12 | Tier 1B: High GIDA Priority | 41.76 | 41.76 | 72.43 | 57.09 | F - Nearest node and line over 5 km | 62.26 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1774
2 | 775 | 1775 | 0301420058 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santo Niño II | 14.8446 | 121.0246 | R | 3916 | 3.5 | 1119 | 336 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 2.48 | Tier 2B: Moderate GIDA Inclusion | 66.4 | 66.4 | 47.77 | 57.08 | D - Other node or line within 3 km | 1.36 | 3.7 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1775
2 | 776 | 1776 | 0103314051 | Region I (Ilocos Region) | La Union | City of San Fernando | San Agustin | 16.6061 | 120.2993 | R | 2277 | 3.7 | 615 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 60.25 | 60.25 | 53.91 | 57.08 | D - Other node or line within 3 km | 1.99 | 1.06 | Line: SEGMENT 51 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1776
2 | 777 | 1777 | 1108204020 | Region XI (Davao Region) | Davao de Oro | Maco | Manipongol | 7.3564 | 125.9074 | R | 590 | 3.7 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.66 | 5.53 | Tier 1B: High GIDA Priority | 42.65 | 42.65 | 71.51 | 57.08 | F - Nearest node and line over 5 km | 5.66 | 5.5 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1777
2 | 778 | 1778 | 1908822004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Kigan | 17.2551 | 122.2291 | R | 3234 | 4.7 | 688 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 42.56 | 42.56 | 71.6 | 57.08 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1778
2 | 779 | 1779 | 0301420014 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz I | 14.8113 | 121.0627 | U | 5074 | 3.5 | 1450 | 435 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 1.61 | Tier 2B: Moderate GIDA Inclusion | 63.87 | 63.87 | 50.26 | 57.07 | D - Other node or line within 3 km | 1.09 | 2.12 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1779
2 | 780 | 1780 | 0403418001 | Region IV-A (CALABARZON) | Laguna | Paete | Bagumbayan | 14.3661 | 121.482 | U | 6032 | 3.3 | 1828 | 548 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 69.85 | 69.85 | 44.26 | 57.06 | B - Node 0.5-1 km | 0.82 | 0.34 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1780
2 | 781 | 1781 | 0702234025 | Region VII (Central Visayas) | Cebu | City of Naga | Tinaan | 10.1934 | 123.7445 | U | 7625 | 3.8 | 2007 | 602 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.24 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 63.33 | 63.33 | 50.79 | 57.06 | C - Line within 0.5 km; node over 1 km | 5.28 | 0.05 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1781
2 | 782 | 1782 | 0403425001 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Bagong Silang | 14.2836 | 121.1649 | U | 6288 | 3.3 | 1905 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.97 | 4.48 | Tier 2B: Moderate GIDA Inclusion | 58.71 | 58.71 | 55.39 | 57.05 | D - Other node or line within 3 km | 2.97 | 4.48 | Node: CBL003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1782
2 | 783 | 1783 | 1906608010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Panducan | 17.2553 | 122.2294 | R | 3077 | 6 | 513 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.36 | Tier 1B: High GIDA Priority | 42.52 | 42.52 | 71.57 | 57.05 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1783
2 | 784 | 1784 | 0301417004 | Region III (Central Luzon) | Bulacan | Plaridel | Banga II | 14.8866 | 120.8712 | U | 9137 | 3.5 | 2611 | 783 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 64.74 | 64.74 | 49.33 | 57.04 | C - Line within 0.5 km; node over 1 km | 2.81 | 0.36 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1784
2 | 785 | 1785 | 1908712003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Talitay | Kiladap | 17.2551 | 122.2291 | R | 3337 | 4.3 | 776 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 44.92 | 44.92 | 69.16 | 57.04 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1785
2 | 786 | 1786 | 1908713001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Bantek | 17.254 | 122.2281 | R | 3237 | 4.3 | 753 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 44.32 | 44.32 | 69.76 | 57.04 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1786
2 | 787 | 1787 | 1381100042 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 42 | 14.5855 | 120.9683 | U | 1675 | 4.36 | 384 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 1.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.96 | 42.96 | 71.11 | 57.04 | D - Other node or line within 3 km | 1.19 | 1.57 | Node: MNL068 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1787
2 | 788 | 1788 | 1380601004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 4 | 13.8064 | 122.12 | U | 1717 | 4.59 | 374 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.69 | 40.69 | 73.39 | 57.04 | D - Other node or line within 3 km | 2.46 | 0.59 | Line: AE MCQ001 TO UNQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1788
2 | 789 | 1789 | 0306916085 | Region III (Central Luzon) | Tarlac | City of Tarlac | Suizo | 15.4643 | 120.6052 | R | 4138 | 3.9 | 1061 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 45.39 | 57.03 | D - Other node or line within 3 km | 1.99 | 0.67 | Line: PIPE 73-92 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1789
2 | 790 | 1790 | 0401017020 | Region IV-A (CALABARZON) | Batangas | Malvar | Santiago | 14.0193 | 121.1631 | U | 8479 | 3.6 | 2355 | 706 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.14 | 0.01 | Tier 2B: Moderate GIDA Inclusion | 68.38 | 68.38 | 45.68 | 57.03 | A - Node within 0.5 km | 0.14 | 0.01 | Line: UG_TNB001 TO DIVERSION RD | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1790
2 | 791 | 1791 | 0604528030 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | San Fernando | 10.6933 | 123.1106 | R | 4803 | 3.7 | 1298 | 389 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.77 | 12.21 | Tier 2B: Moderate GIDA Inclusion | 63.06 | 63.06 | 50.98 | 57.02 | F - Nearest node and line over 5 km | 8.77 | 12.13 | Node: BDN004 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1791
2 | 792 | 1792 | 0306902014 | Region III (Central Luzon) | Tarlac | Bamban | San Vicente | 15.2353 | 120.5336 | R | 3934 | 3.9 | 1009 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.95 | 2.47 | Tier 2B: Moderate GIDA Inclusion | 61.25 | 61.25 | 52.8 | 57.02 | D - Other node or line within 3 km | 5.95 | 2.93 | Line: Aerial 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1792
2 | 793 | 1793 | 1380601016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 16 | 13.7023 | 121.4245 | U | 1371 | 4.04 | 339 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 9.68 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.41 | 38.41 | 75.63 | 57.02 | D - Other node or line within 3 km | 1.15 | 13.55 | Node: SJB003 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1793
2 | 794 | 1794 | 0205002016 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Anayo | 16.1959 | 121.0746 | R | 507 | 3.8 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.8 | 9.63 | Tier 1B: High GIDA Priority | 35 | 35 | 79.05 | 57.02 | F - Nearest node and line over 5 km | 11.8 | 9.59 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1794
2 | 795 | 1795 | 1381100008 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 8 | 14.5544 | 121.0088 | U | 1147 | 3.13 | 367 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.68 | 43.68 | 70.34 | 57.01 | B - Node 0.5-1 km | 0.59 | 0.4 | Line: Existing 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1795
2 | 796 | 1796 | 1108201010 | Region XI (Davao Region) | Davao de Oro | Compostela | Panansalan | 7.6792 | 126.074 | R | 1104 | 3.7 | 298 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.59 | 9.53 | Tier 1B: High GIDA Priority | 37.9 | 37.9 | 76.12 | 57.01 | F - Nearest node and line over 5 km | 16.59 | 9.53 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1796
2 | 797 | 1797 | 0405801010 | Region IV-A (CALABARZON) | Rizal | Angono | San Pedro | 14.527 | 121.1594 | U | 1739 | 3.6 | 483 | 145 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.51 | Tier 1B: High GIDA Priority | 51.81 | 51.81 | 62.19 | 57 | B - Node 0.5-1 km | 0.51 | 0.5 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1797
2 | 798 | 1798 | 1380601183 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 183 | 14.3625 | 121.7076 | U | 8512 | 4.07 | 2093 | 628 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.03 | 24.04 | Tier 1B: High GIDA Priority | 44.29 | 44.29 | 69.72 | 57 | F - Nearest node and line over 5 km | 18.03 | 24.04 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1798
2 | 799 | 1799 | 0405628019 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ibabang Yuni | 13.4251 | 122.4707 | R | 2454 | 3.8 | 646 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.6 | 13.59 | Tier 1B: High GIDA Priority | 53.56 | 53.56 | 60.42 | 56.99 | F - Nearest node and line over 5 km | 6.6 | 13.59 | Node: MLQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1799
2 | 800 | 1800 | 0604530017 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Tabao Proper | 10.4451 | 122.8263 | R | 4471 | 3.7 | 1208 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 0.29 | Tier 2A: High Commercial ROI | 76.17 | 76.17 | 37.79 | 56.98 | C - Line within 0.5 km; node over 1 km | 2.35 | 0.29 | Line: TALISAY CITY - KABANGKALAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1800
2 | 801 | 1801 | 0304908013 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Vicente | 15.3141 | 120.9479 | U | 9910 | 3.5 | 2831 | 849 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 68.74 | 68.74 | 45.23 | 56.98 | C - Line within 0.5 km; node over 1 km | 2.58 | 0.28 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1801
2 | 802 | 1802 | 0401006002 | Region IV-A (CALABARZON) | Batangas | Bauan | Aplaya | 13.7817 | 121.0069 | U | 8070 | 3.6 | 2242 | 673 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 65.37 | 65.37 | 48.59 | 56.98 | D - Other node or line within 3 km | 1.51 | 1.06 | Line: UG BUN001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1802
2 | 803 | 1803 | 0402123019 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Macario Dacon | 14.3278 | 121.0105 | U | 5454 | 3.4 | 1604 | 481 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 2.69 | Tier 2B: Moderate GIDA Inclusion | 57.92 | 57.92 | 56.04 | 56.98 | D - Other node or line within 3 km | 2.85 | 3.41 | Node: MUN048 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1803
2 | 804 | 1804 | 0402117018 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa IV | 14.4031 | 120.8658 | R | 1019 | 3.4 | 300 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.71 | Tier 1B: High GIDA Priority | 53.95 | 53.95 | 59.99 | 56.97 | B - Node 0.5-1 km | 0.68 | 0.78 | Node: TRC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1804
2 | 805 | 1805 | 1380601033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 33 | 12.6335 | 123.2065 | U | 4343 | 4.89 | 888 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.95 | 28.02 | Tier 1B: High GIDA Priority | 39.59 | 39.59 | 74.34 | 56.97 | F - Nearest node and line over 5 km | 24.95 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1805
2 | 806 | 1806 | 0301420040 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan V | 14.8005 | 121.04 | R | 2300 | 3.5 | 657 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 64.33 | 64.33 | 49.59 | 56.96 | A - Node within 0.5 km | 0.39 | 0.13 | Line: 48 CORE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1806
2 | 807 | 1807 | 1908705004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Bagoenged | 17.2539 | 122.228 | R | 4600 | 4.3 | 1070 | 321 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.18 | Tier 1B: High GIDA Priority | 49.51 | 49.51 | 64.42 | 56.96 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1807
2 | 808 | 1808 | 1003511015 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lower Caningag | 8.0094 | 123.8928 | R | 396 | 4.2 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.97 | 10.35 | Tier 1B: High GIDA Priority | 42.28 | 42.28 | 71.63 | 56.96 | F - Nearest node and line over 5 km | 10.97 | 10.35 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1808
2 | 809 | 1809 | 1102501015 | Region XI (Davao Region) | Davao Oriental | Baganga | San Isidro | 7.574 | 126.5601 | R | 2186 | 3.6 | 607 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.27 | 62.14 | Tier 1B: High GIDA Priority | 41.92 | 41.92 | 71.99 | 56.96 | F - Nearest node and line over 5 km | 62.27 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1809
2 | 810 | 1810 | 0103302025 | Region I (Ilocos Region) | La Union | Aringay | Santa Rita West | 16.3532 | 120.3451 | R | 3652 | 3.7 | 987 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.14 | 1.5 | Tier 2B: Moderate GIDA Inclusion | 65.88 | 65.88 | 48.02 | 56.95 | D - Other node or line within 3 km | 4.14 | 1.5 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1810
2 | 811 | 1811 | 0403426025 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Norte | 14.2885 | 121.4058 | U | 5938 | 3.3 | 1799 | 540 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 1.29 | Tier 2B: Moderate GIDA Inclusion | 64.35 | 64.35 | 49.54 | 56.95 | D - Other node or line within 3 km | 1.31 | 1.28 | Line: UG SCL001 TO LWL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1811
2 | 812 | 1812 | 1004324010 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Sugbongcogon | 8.5363 | 124.7679 | U | 4752 | 3.9 | 1218 | 365 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 1.35 | Tier 2B: Moderate GIDA Inclusion | 63.97 | 63.97 | 49.93 | 56.95 | D - Other node or line within 3 km | 1.67 | 1.34 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1812
2 | 813 | 1813 | 0402120019 | Region IV-A (CALABARZON) | Cavite | Tanza | Barangay IV | 14.3569 | 120.8322 | R | 1740 | 3.4 | 512 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 1.78 | Tier 2B: Moderate GIDA Inclusion | 57.8 | 57.8 | 56.09 | 56.95 | D - Other node or line within 3 km | 1.77 | 1.77 | Node: TZC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1813
2 | 814 | 1814 | 1908705024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Nekitan | 17.2539 | 122.228 | R | 4632 | 4.3 | 1077 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 49.53 | 49.53 | 64.37 | 56.95 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1814
2 | 815 | 1815 | 1606818017 | Region XIII (Caraga) | Surigao del Sur | Tago | Mercedes | 9.0176 | 126.2227 | R | 334 | 4.1 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.16 | 2.46 | Tier 1B: High GIDA Priority | 41.71 | 41.71 | 72.19 | 56.95 | D - Other node or line within 3 km | 7.16 | 2.39 | Line: Route | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1815
2 | 816 | 1816 | 0806016037 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Napuro II | 12.0511 | 124.7145 | R | 1116 | 4.1 | 272 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 83.59 | 83.56 | Tier 1B: High GIDA Priority | 39.32 | 39.32 | 74.57 | 56.95 | F - Nearest node and line over 5 km | 83.59 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1816
2 | 817 | 1817 | 0105522028 | Region I (Ilocos Region) | Pangasinan | Lingayen | Poblacion | 16.0316 | 120.231 | U | 12958 | 3.6 | 3599 | 1080 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.97 | 0.97 | Tier 2A: High Commercial ROI | 70.64 | 70.64 | 43.24 | 56.94 | B - Node 0.5-1 km | 0.97 | 1.14 | Node: LNP001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1817
2 | 818 | 1818 | 0403405028 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mapagong | 14.2333 | 121.1212 | U | 7952 | 3.3 | 2410 | 723 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 1.39 | Tier 2B: Moderate GIDA Inclusion | 65.57 | 65.57 | 48.3 | 56.94 | D - Other node or line within 3 km | 1.69 | 1.39 | Line: BÑL001 TO CLB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1818
2 | 819 | 1819 | 0306916018 | Region III (Central Luzon) | Tarlac | City of Tarlac | Binauganan | 15.4769 | 120.6045 | U | 6040 | 3.9 | 1549 | 465 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.82 | Tier 2B: Moderate GIDA Inclusion | 64.5 | 64.5 | 49.38 | 56.94 | B - Node 0.5-1 km | 0.92 | 0.8 | Line: PIPE 73-92 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1819
2 | 820 | 1820 | 0401005077 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 8 | 13.7392 | 121.12 | R | 492 | 3.6 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 6.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.19 | 44.19 | 69.7 | 56.94 | D - Other node or line within 3 km | 1.67 | 6.28 | Node: BCY007-PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1820
2 | 821 | 1821 | 1705320004 | MIMAROPA Region | Palawan | Taytay | Batas | 11.1526 | 119.6072 | R | 1445 | 3.9 | 371 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.09 | 38.26 | Tier 1B: High GIDA Priority | 40.66 | 40.66 | 73.22 | 56.94 | F - Nearest node and line over 5 km | 14.09 | 38.09 | Node: TYW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1821
2 | 822 | 1822 | 0907333010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Matalang | 7.8548 | 123.1511 | R | 753 | 3.9 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.47 | 7.9 | Tier 1B: High GIDA Priority | 38.35 | 38.35 | 75.53 | 56.94 | F - Nearest node and line over 5 km | 17.47 | 7.87 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1822
2 | 823 | 1823 | 0601917033 | Region VI (Western Visayas) | Capiz | Tapaz | Rizal Norte | 11.2667 | 122.5333 | R | 327 | 3.8 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.68 | 3.43 | Tier 1B: High GIDA Priority | 36.13 | 36.13 | 77.75 | 56.94 | F - Nearest node and line over 5 km | 15.68 | 6.76 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1823
2 | 824 | 1824 | 1380606004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 398 | 13.9081 | 120.8888 | U | 2413 | 4.04 | 598 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.01 | 0.15 | Tier 1B: High GIDA Priority | 44.77 | 44.77 | 69.1 | 56.93 | C - Line within 0.5 km; node over 1 km | 4.01 | 0.06 | Line: AE BYB001 TO LYB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1824
2 | 825 | 1825 | 0704624002 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Bairan | 10.3946 | 123.2925 | R | 635 | 3.8 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.69 | 2.05 | Tier 1B: High GIDA Priority | 44.63 | 44.63 | 69.23 | 56.93 | E - Nearest node or line 3-5 km | 4.69 | 12.51 | Node: VHN001-BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1825
2 | 826 | 1826 | 0501727014 | Region V (Bicol Region) | Camarines Sur | Pasacao | San Antonio | 13.5886 | 122.9318 | R | 612 | 4.2 | 146 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.35 | 12.64 | Tier 1B: High GIDA Priority | 38.16 | 38.16 | 75.7 | 56.93 | F - Nearest node and line over 5 km | 12.35 | 13.02 | Node: LBC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1826
2 | 827 | 1827 | 1380614026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 770 | 11.4029 | 121.5746 | U | 9673 | 4.4 | 2197 | 659 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 72.89 | 70.77 | Tier 1B: High GIDA Priority | 44.59 | 44.59 | 69.24 | 56.92 | F - Nearest node and line over 5 km | 72.89 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1827
2 | 828 | 1828 | 0500507009 | Region V (Bicol Region) | Albay | Libon | Zone VI | 13.2604 | 123.3827 | R | 561 | 4.1 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.77 | 8.41 | Tier 1B: High GIDA Priority | 43.32 | 43.32 | 70.52 | 56.92 | F - Nearest node and line over 5 km | 6.77 | 8.41 | Node: LBN002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1828
2 | 829 | 1829 | 0103314047 | Region I (Ilocos Region) | La Union | City of San Fernando | Poro | 16.6339 | 120.3085 | U | 6819 | 3.7 | 1843 | 553 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.52 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 61.6 | 61.6 | 52.22 | 56.91 | C - Line within 0.5 km; node over 1 km | 3.52 | 0.47 | Line: SAN FERNANDO - SUPIDEN AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1829
2 | 830 | 1830 | 0504101032 | Region V (Bicol Region) | Masbate | Aroroy | Puro | 12.4843 | 123.3825 | U | 8299 | 4.1 | 2024 | 607 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.41 | 6.79 | Tier 2B: Moderate GIDA Inclusion | 61.42 | 61.42 | 52.39 | 56.91 | E - Nearest node or line 3-5 km | 3.41 | 26.58 | Node: AYM001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1830
2 | 831 | 1831 | 1208002009 | Region XII (SOCCSKSARGEN) | Sarangani | Glan | Congan | 5.8117 | 125.2776 | R | 2344 | 3.9 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.58 | 35.61 | Tier 1B: High GIDA Priority | 42.22 | 42.22 | 71.59 | 56.91 | F - Nearest node and line over 5 km | 32.58 | 35.61 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1831
2 | 832 | 1832 | 1705101010 | MIMAROPA Region | Occidental Mindoro | Abra De Ilog | Santa Maria | 13.4229 | 120.7069 | R | 2156 | 3.9 | 553 | 166 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.29 | 21.69 | Tier 1B: High GIDA Priority | 41.95 | 41.95 | 71.86 | 56.91 | F - Nearest node and line over 5 km | 23.29 | 21.21 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1832
2 | 833 | 1833 | 0301408012 | Region III (Central Luzon) | Bulacan | Guiguinto | Tabe | 14.8368 | 120.8876 | U | 9629 | 3.5 | 2751 | 825 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 0.86 | Tier 2B: Moderate GIDA Inclusion | 66.59 | 66.59 | 47.21 | 56.9 | D - Other node or line within 3 km | 1.81 | 0.92 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1833
2 | 834 | 1834 | 0403411003 | Region IV-A (CALABARZON) | Laguna | Los Baños | Bambang | 14.1777 | 121.2185 | U | 8373 | 3.3 | 2537 | 761 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 64.66 | 64.66 | 49.15 | 56.9 | C - Line within 0.5 km; node over 1 km | 2.57 | 0.14 | Line: CLB001 TO SCL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1834
2 | 835 | 1835 | 0307702013 | Region III (Central Luzon) | Aurora | Casiguran | Dibet | 16.215 | 122.0615 | R | 849 | 3.8 | 223 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 0.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 49.28 | 49.28 | 64.52 | 56.9 | D - Other node or line within 3 km | 2.3 | 999999 | Node: CSA002 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1835
2 | 836 | 1836 | 0501711012 | Region V (Bicol Region) | Camarines Sur | Caramoan | Gogon | 13.9445 | 123.8292 | R | 1595 | 4.2 | 380 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.29 | 46.08 | Tier 1B: High GIDA Priority | 39.72 | 39.72 | 74.07 | 56.9 | F - Nearest node and line over 5 km | 19.29 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1836
2 | 837 | 1837 | 0601917051 | Region VI (Western Visayas) | Capiz | Tapaz | Senonod | 11.2667 | 122.5333 | R | 230 | 3.8 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.68 | 3.43 | Tier 1B: High GIDA Priority | 36.13 | 36.13 | 77.66 | 56.9 | F - Nearest node and line over 5 km | 15.68 | 6.76 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1837
2 | 838 | 1838 | 0102934033 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Jose | 17.585 | 120.3643 | R | 915 | 3.8 | 241 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.93 | 2.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.39 | 45.39 | 68.38 | 56.89 | D - Other node or line within 3 km | 2.93 | 2.48 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1838
2 | 839 | 1839 | 1381100186 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 186 | 14.32 | 120.9317 | U | 2213 | 3.52 | 628 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 2.97 | Tier 1B: High GIDA Priority | 42.55 | 42.55 | 71.22 | 56.89 | D - Other node or line within 3 km | 3.5 | 2.97 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1839
2 | 840 | 1840 | 0600602029 | Region VI (Western Visayas) | Antique | Barbaza | Mayabay | 11.2745 | 122.1354 | R | 272 | 3.9 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.9 | 40.77 | Tier 1B: High GIDA Priority | 36.86 | 36.86 | 76.91 | 56.88 | F - Nearest node and line over 5 km | 40.9 | 40.73 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1840
2 | 841 | 1841 | 0205008023 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Talbek | 16.0239 | 121.2118 | R | 542 | 3.8 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.16 | 25.54 | Tier 1B: High GIDA Priority | 32.57 | 32.57 | 81.19 | 56.88 | F - Nearest node and line over 5 km | 16.16 | 25.54 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1841
2 | 842 | 1842 | 0403421008 | Region IV-A (CALABARZON) | Laguna | Pangil | Sulib | 14.4049 | 121.4638 | U | 7425 | 3.3 | 2250 | 675 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.42 | Tier 2A: High Commercial ROI | 72.53 | 72.53 | 41.16 | 56.85 | A - Node within 0.5 km | 0.16 | 0.41 | Node: PGL001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1842
2 | 843 | 1843 | 0403413001 | Region IV-A (CALABARZON) | Laguna | Lumban | Bagong Silang | 14.2914 | 121.4678 | R | 3248 | 3.3 | 984 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.6 | Tier 2A: High Commercial ROI | 70.15 | 70.15 | 43.55 | 56.85 | B - Node 0.5-1 km | 0.87 | 0.6 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1843
2 | 844 | 1844 | 1404402004 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Balintaugan | 17.0522 | 120.8778 | R | 152 | 3.7 | 41 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.34 | 2.82 | Tier 1B: High GIDA Priority | 46.1 | 46.1 | 67.59 | 56.85 | D - Other node or line within 3 km | 4.34 | 2.73 | Line: LA TRINIDAD-SAGADA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1844
2 | 845 | 1845 | 0402120040 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan VI | 14.3946 | 120.8484 | R | 5236 | 3.4 | 1540 | 462 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 0.46 | Tier 2A: High Commercial ROI | 70.68 | 70.68 | 43 | 56.84 | C - Line within 0.5 km; node over 1 km | 1.52 | 0.46 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1845
2 | 846 | 1846 | 0402120021 | Region IV-A (CALABARZON) | Cavite | Tanza | Sahud Ulan | 14.3776 | 120.8246 | U | 23343 | 3.4 | 6866 | 2060 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.87 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 69.58 | 69.58 | 44.1 | 56.84 | B - Node 0.5-1 km | 0.87 | 0.55 | Line: TANZA | Survey short node lateral; confirm port/fiber capacity, access and route. | 1846
2 | 847 | 1847 | 1380606026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 420 | 11.7124 | 122.4653 | U | 2890 | 3.84 | 753 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.91 | 10.69 | Tier 1B: High GIDA Priority | 43.02 | 43.02 | 70.66 | 56.84 | F - Nearest node and line over 5 km | 7.91 | 10.69 | Node: NWK001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1847
2 | 848 | 1848 | 1381300088 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 3-A | 14.7083 | 121.0103 | U | 1253 | 3.88 | 323 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.68 | 42.68 | 71.01 | 56.84 | B - Node 0.5-1 km | 0.53 | 0.19 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1848
2 | 849 | 1849 | 1906612041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | North Silumpak | 16.3688 | 122.135 | R | 740 | 6 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.61 | 0.76 | Tier 1B: High GIDA Priority | 41.7 | 41.7 | 71.97 | 56.84 | F - Nearest node and line over 5 km | 7.61 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1849
2 | 850 | 1850 | 1408103012 | Cordillera Administrative Region (CAR) | Apayao | Flora | Mallig | 18.1197 | 121.414 | R | 720 | 4.2 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.15 | 7.16 | Tier 1B: High GIDA Priority | 41.1 | 41.1 | 72.58 | 56.84 | F - Nearest node and line over 5 km | 7.15 | 17.76 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1850
2 | 851 | 1851 | 1705305014 | MIMAROPA Region | Palawan | Bataraza | Sandoval | 8.5948 | 117.4538 | R | 4123 | 3.9 | 1057 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 189.65 | 191.94 | Tier 1B: High GIDA Priority | 51.31 | 51.31 | 62.35 | 56.83 | F - Nearest node and line over 5 km | 189.65 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1851
2 | 852 | 1852 | 1908824007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Katibpuan | 17.2551 | 122.2291 | R | 3559 | 4.7 | 757 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 44.39 | 44.39 | 69.27 | 56.83 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1852
2 | 853 | 1853 | 1380614098 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 905 | 13.7287 | 120.5303 | U | 7428 | 4.26 | 1744 | 523 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.48 | 15.52 | Tier 1B: High GIDA Priority | 43.8 | 43.8 | 69.86 | 56.83 | F - Nearest node and line over 5 km | 15.48 | 15.42 | Line: BALAYAN - CALATAGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1853
2 | 854 | 1854 | 0504106005 | Region V (Bicol Region) | Masbate | Cawayan | Calapayan | 11.9939 | 123.8181 | R | 1426 | 4.1 | 348 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17 | 41.86 | Tier 1B: High GIDA Priority | 39.81 | 39.81 | 73.84 | 56.83 | F - Nearest node and line over 5 km | 17 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1854
2 | 855 | 1855 | 0102931002 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Caoayan | 16.8067 | 120.5418 | R | 748 | 3.8 | 197 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.68 | 13.27 | Tier 1B: High GIDA Priority | 39.26 | 39.26 | 74.4 | 56.83 | F - Nearest node and line over 5 km | 14.68 | 13.27 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1855
2 | 856 | 1856 | 0301403010 | Region III (Central Luzon) | Bulacan | Baliuag | Pagala | 14.9591 | 120.8928 | U | 7563 | 3.5 | 2161 | 648 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 65.6 | 65.6 | 48.03 | 56.82 | C - Line within 0.5 km; node over 1 km | 1.33 | 0.16 | Line: BALIUAG - CANDABA LINK | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1856
2 | 857 | 1857 | 1906606003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Kabuukan | 17.2553 | 122.2294 | R | 2973 | 6 | 496 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.36 | Tier 1B: High GIDA Priority | 42.09 | 42.09 | 71.55 | 56.82 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1857
2 | 858 | 1858 | 0500502002 | Region V (Bicol Region) | Albay | Camalig | Baligang | 13.1526 | 123.6431 | R | 3858 | 4.1 | 941 | 282 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.55 | 2.82 | Tier 2B: Moderate GIDA Inclusion | 62.09 | 62.09 | 51.52 | 56.81 | D - Other node or line within 3 km | 4.55 | 2.79 | Line: IRIGA - LEGAZPI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1858
2 | 859 | 1859 | 1705205027 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Ilaya | 13.3555 | 121.189 | U | 4014 | 3.9 | 1029 | 309 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.43 | 2.07 | Tier 2B: Moderate GIDA Inclusion | 57.09 | 57.09 | 56.52 | 56.81 | D - Other node or line within 3 km | 3.43 | 2.06 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1859
2 | 860 | 1860 | 1408103017 | Cordillera Administrative Region (CAR) | Apayao | Flora | Upper Atok | 18.0813 | 121.3552 | R | 315 | 4.2 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.06 | 1.21 | Tier 1B: High GIDA Priority | 44.56 | 44.56 | 69.05 | 56.81 | F - Nearest node and line over 5 km | 5.06 | 25.27 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1860
2 | 861 | 1861 | 0506216030 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Sampaloc | 12.9711 | 124.0104 | R | 4685 | 4 | 1171 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.44 | Tier 2A: High Commercial ROI | 74.23 | 74.23 | 39.36 | 56.8 | B - Node 0.5-1 km | 0.77 | 0.35 | Line: SORSOGON - MATNOG | Survey short node lateral; confirm port/fiber capacity, access and route. | 1861
2 | 862 | 1862 | 0301420048 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin IV | 14.8276 | 121.0293 | R | 4270 | 3.5 | 1220 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 1.45 | Tier 2B: Moderate GIDA Inclusion | 69.44 | 69.44 | 44.15 | 56.8 | D - Other node or line within 3 km | 1.81 | 2.55 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1862
2 | 863 | 1863 | 1907001009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tungbangkaw | 17.2557 | 122.2297 | R | 3589 | 5.8 | 619 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 40.81 | 40.81 | 72.77 | 56.79 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1863
2 | 864 | 1864 | 0102805023 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Ablan Pob. | 18.0595 | 120.5606 | R | 751 | 3.7 | 203 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 0.28 | Tier 1B: High GIDA Priority | 50.98 | 50.98 | 62.59 | 56.78 | B - Node 0.5-1 km | 0.95 | 0.2 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Survey short node lateral; confirm port/fiber capacity, access and route. | 1864
2 | 865 | 1865 | 0500504011 | Region V (Bicol Region) | Albay | Guinobatan | Doña Mercedes | 13.173 | 123.5822 | R | 1476 | 4.1 | 360 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.91 | 2.83 | Tier 1B: High GIDA Priority | 50.72 | 50.72 | 62.85 | 56.78 | D - Other node or line within 3 km | 2.91 | 2.76 | Line: IRIGA - LEGAZPI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1865
2 | 866 | 1866 | 1908705008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Bongued | 17.2539 | 122.228 | R | 4061 | 4.3 | 944 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 49.13 | 49.13 | 64.43 | 56.78 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1866
2 | 867 | 1867 | 0600602015 | Region VI (Western Visayas) | Antique | Barbaza | Idao | 11.236 | 122.0745 | R | 255 | 3.9 | 65 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.49 | 48.29 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 76.81 | 56.78 | F - Nearest node and line over 5 km | 48.49 | 48.25 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1867
2 | 868 | 1868 | 1381300125 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | U.P. Village | 14.7106 | 121.115 | U | 3257 | 3.69 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 1.27 | Tier 1B: High GIDA Priority | 56.19 | 56.19 | 57.34 | 56.77 | D - Other node or line within 3 km | 1.12 | 1.26 | Node: QCY069 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1868
2 | 869 | 1869 | 0402104017 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 6 | 14.2995 | 121.0572 | R | 767 | 3.4 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 1.49 | Tier 1B: High GIDA Priority | 52.24 | 52.24 | 61.3 | 56.77 | B - Node 0.5-1 km | 0.53 | 1.41 | Node: BNL003 - TYPE 4A | Survey short node lateral; confirm port/fiber capacity, access and route. | 1869
2 | 870 | 1870 | 1381100067 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 67 | 14.6142 | 120.96 | U | 1046 | 3.28 | 319 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.73 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.63 | 42.63 | 70.91 | 56.77 | B - Node 0.5-1 km | 0.51 | 1.08 | Node: MNL045 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1870
2 | 871 | 1871 | 0506203019 | Region V (Bicol Region) | Sorsogon | Bulan | Daganas | 12.7064 | 123.9468 | R | 431 | 4 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.99 | 4.54 | Tier 1B: High GIDA Priority | 41.28 | 41.28 | 72.26 | 56.77 | E - Nearest node or line 3-5 km | 8.99 | 4.54 | Line: 30,000m | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1871
2 | 872 | 1872 | 0102823005 | Region I (Ilocos Region) | Ilocos Norte | Vintar | Bago | 18.3257 | 120.6832 | R | 400 | 3.7 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.98 | 6.86 | Tier 1B: High GIDA Priority | 39.57 | 39.57 | 73.98 | 56.77 | F - Nearest node and line over 5 km | 6.98 | 6.85 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1872
2 | 873 | 1873 | 0600404009 | Region VI (Western Visayas) | Aklan | Batan | Lalab | 11.5752 | 122.4308 | R | 3272 | 3.9 | 839 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.35 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 66.81 | 66.81 | 46.71 | 56.76 | C - Line within 0.5 km; node over 1 km | 6.35 | 0.1 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1873
2 | 874 | 1874 | 0604507012 | Region VI (Western Visayas) | Negros Occidental | Cauayan | Camindangan | 9.8328 | 122.5721 | R | 2781 | 3.7 | 752 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.77 | 18.92 | Tier 1B: High GIDA Priority | 47.67 | 47.67 | 65.85 | 56.76 | F - Nearest node and line over 5 km | 20.77 | 18.88 | Line: SIPALAY TO BAYAWAN-84,748m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1874
2 | 875 | 1875 | 1381000013 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Isidro | 14.4715 | 121.0122 | U | 78765 | 3.18 | 24747 | 7424 | Band n50 (1.5 GHz, 100 MHz TDD) | 8 | 1 | 2.41 | 0.29 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.97 | 44.97 | 68.54 | 56.76 | C - Line within 0.5 km; node over 1 km | 2.41 | 0.29 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1875
2 | 876 | 1876 | 0304904014 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Sur | 15.2632 | 120.8669 | U | 14187 | 3.5 | 4053 | 1216 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.07 | 0.09 | Tier 2A: High Commercial ROI | 73.89 | 73.89 | 39.62 | 56.75 | A - Node within 0.5 km | 0.07 | 0.09 | Node: CAN001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1876
2 | 877 | 1877 | 1908705016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Kenebeka | 17.2539 | 122.228 | R | 3364 | 4.3 | 782 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 45.11 | 45.11 | 68.39 | 56.75 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1877
2 | 878 | 1878 | 1380611044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 829 | 14.0523 | 122.6163 | U | 4375 | 4.32 | 1012 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.48 | 10.71 | Tier 1B: High GIDA Priority | 43.48 | 43.48 | 70.03 | 56.75 | F - Nearest node and line over 5 km | 12.48 | 10.69 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1878
2 | 879 | 1879 | 1907001011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Belatan Halu | 17.2557 | 122.2297 | R | 3579 | 5.8 | 617 | 185 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 40.72 | 40.72 | 72.77 | 56.75 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1879
2 | 880 | 1880 | 0300805008 | Region III (Central Luzon) | Bataan | Hermosa | Culis | 14.8396 | 120.4818 | U | 10782 | 3.6 | 2995 | 898 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 68.96 | 68.96 | 44.52 | 56.74 | B - Node 0.5-1 km | 0.89 | 0.13 | Line: Pipe Dinalupian to Orion | Survey short node lateral; confirm port/fiber capacity, access and route. | 1880
2 | 881 | 1881 | 0301411010 | Region III (Central Luzon) | Bulacan | Marilao | Poblacion II | 14.7724 | 120.9657 | U | 5193 | 3.5 | 1484 | 445 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 61.78 | 61.78 | 51.69 | 56.74 | D - Other node or line within 3 km | 2.46 | 1.99 | Line: BOCAUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1881
2 | 882 | 1882 | 1380606175 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 569 | 13.8825 | 121.2385 | U | 2107 | 4.48 | 470 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.24 | 44.24 | 69.24 | 56.74 | C - Line within 0.5 km; node over 1 km | 1.77 | 0.49 | Line: AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1882
2 | 883 | 1883 | 1102319010 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magdum | 7.4732 | 125.8424 | U | 13786 | 3.7 | 3726 | 1118 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.82 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 69.19 | 69.19 | 44.28 | 56.73 | C - Line within 0.5 km; node over 1 km | 2.82 | 0.12 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1883
2 | 884 | 1884 | 0201529002 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Atulayan Norte | 17.6135 | 121.7355 | R | 4335 | 3.9 | 1112 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.39 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 66.06 | 66.06 | 47.4 | 56.73 | C - Line within 0.5 km; node over 1 km | 4.39 | 0.09 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1884
2 | 885 | 1885 | 0802615015 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 3 | 11.4866 | 125.4335 | R | 988 | 3.9 | 253 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.42 | 54.82 | Tier 1B: High GIDA Priority | 38.9 | 38.9 | 74.56 | 56.73 | F - Nearest node and line over 5 km | 54.42 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1885
2 | 886 | 1886 | 0702219007 | Region VII (Central Visayas) | Cebu | Consolacion | Lamac | 10.3857 | 123.9651 | U | 11475 | 3.8 | 3020 | 906 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.63 | Tier 2A: High Commercial ROI | 70.55 | 70.55 | 42.9 | 56.72 | D - Other node or line within 3 km | 1.23 | 0.62 | Line: DANAO - CEBU | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1886
2 | 887 | 1887 | 1403208010 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Galdang | 17.3951 | 121.1487 | R | 380 | 4.3 | 88 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.6 | 3.97 | Tier 1B: High GIDA Priority | 38.13 | 38.13 | 75.31 | 56.72 | E - Nearest node or line 3-5 km | 14.6 | 3.81 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1887
2 | 888 | 1888 | 1907011008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Nunukan | 13.4909 | 121.421 | R | 2665 | 5.8 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.81 | 29.69 | Tier 1B: High GIDA Priority | 37.54 | 37.54 | 75.9 | 56.72 | F - Nearest node and line over 5 km | 22.81 | 29.69 | Node: NJM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1888
2 | 889 | 1889 | 1381100109 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 109 | 14.6692 | 121.0455 | U | 1299 | 3.46 | 375 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.57 | 43.57 | 69.84 | 56.71 | B - Node 0.5-1 km | 0.73 | 0.22 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1889
2 | 890 | 1890 | 0401005076 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 7 | 13.7609 | 121.0613 | U | 464 | 3.6 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.17 | 42.17 | 71.26 | 56.71 | B - Node 0.5-1 km | 0.51 | 0.25 | Line: UG SSB001 TO BCY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1890
2 | 891 | 1891 | 0600602031 | Region VI (Western Visayas) | Antique | Barbaza | Nalusdan | 11.196 | 122.0707 | R | 182 | 3.9 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.35 | 44.38 | Tier 1B: High GIDA Priority | 36.74 | 36.74 | 76.69 | 56.71 | F - Nearest node and line over 5 km | 50.35 | 44.01 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1891
2 | 892 | 1892 | 0702223042 | Region VII (Central Visayas) | Cebu | Danao City | Taytay | 10.5322 | 124.0275 | R | 4744 | 3.8 | 1248 | 374 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.26 | Tier 2A: High Commercial ROI | 73.69 | 73.69 | 39.71 | 56.7 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.24 | Line: UPLINK 2 CRM001- DOC001 via AE BACKBONE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1892
2 | 893 | 1893 | 1381100124 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 124 | 14.6248 | 121.1397 | U | 1722 | 3.66 | 471 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.11 | 44.11 | 69.29 | 56.7 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.14 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1893
2 | 894 | 1894 | 1381100166 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 166 | 14.7371 | 121.0775 | U | 1228 | 3.18 | 386 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.94 | 41.94 | 71.46 | 56.7 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.43 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1894
2 | 895 | 1895 | 0702252002 | Region VII (Central Visayas) | Cebu | Tuburan | Amatugan | 10.6758 | 123.8876 | R | 953 | 3.8 | 251 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.96 | 8.53 | Tier 1B: High GIDA Priority | 39.19 | 39.19 | 74.21 | 56.7 | F - Nearest node and line over 5 km | 13.96 | 8.53 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1895
2 | 896 | 1896 | 0403411010 | Region IV-A (CALABARZON) | Laguna | Los Baños | Mayondon | 14.1882 | 121.2383 | U | 19530 | 3.3 | 5918 | 1775 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.09 | 0.95 | Tier 2A: High Commercial ROI | 70.38 | 70.38 | 43 | 56.69 | D - Other node or line within 3 km | 1.09 | 0.95 | Line: CLB001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1896
2 | 897 | 1897 | 0301412007 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Camalig | 14.7721 | 120.9934 | U | 8768 | 3.5 | 2505 | 752 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 2.01 | Tier 2B: Moderate GIDA Inclusion | 62.89 | 62.89 | 50.49 | 56.69 | D - Other node or line within 3 km | 1.48 | 2.81 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1897
2 | 898 | 1898 | 1402709005 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Mompolia | 16.8721 | 121.1447 | R | 1271 | 3.9 | 326 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.31 | 6.73 | Tier 1B: High GIDA Priority | 51.18 | 51.18 | 62.2 | 56.69 | E - Nearest node or line 3-5 km | 4.31 | 6.58 | Node: BEF002 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1898
2 | 899 | 1899 | 1908706010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Maitong | 17.2541 | 122.2281 | R | 3868 | 4.3 | 900 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 48.16 | 48.16 | 65.22 | 56.69 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1899
2 | 900 | 1900 | 0601912026 | Region VI (Western Visayas) | Capiz | Pontevedra | Tacas | 11.4767 | 122.8347 | R | 4684 | 3.8 | 1233 | 370 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.2 | Tier 2A: High Commercial ROI | 75.68 | 75.68 | 37.68 | 56.68 | A - Node within 0.5 km | 0.16 | 0.1 | Line: ROXAS - SARA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1900
2 | 901 | 1901 | 0402123009 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Epifanio Malia | 14.3159 | 121.0095 | R | 4369 | 3.4 | 1285 | 386 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.86 | 4.02 | Tier 2B: Moderate GIDA Inclusion | 64.44 | 64.44 | 48.92 | 56.68 | D - Other node or line within 3 km | 2.86 | 4.31 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1901
2 | 902 | 1902 | 0102805018 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Valdez Pob. | 18.053 | 120.5651 | R | 820 | 3.7 | 222 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 0.86 | Tier 1B: High GIDA Priority | 50.67 | 50.67 | 62.69 | 56.68 | D - Other node or line within 3 km | 1.41 | 0.86 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1902
2 | 903 | 1903 | 0600602017 | Region VI (Western Visayas) | Antique | Barbaza | Igtunarum | 11.208 | 122.0757 | R | 76 | 3.9 | 19 | 6 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.76 | 45.79 | Tier 1B: High GIDA Priority | 36.74 | 36.74 | 76.63 | 56.68 | F - Nearest node and line over 5 km | 50.76 | 50.58 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1903
2 | 904 | 1904 | 0305412018 | Region III (Central Luzon) | Pampanga | Masantol | San Isidro Matua | 14.8913 | 120.7009 | R | 3735 | 4 | 934 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 2.21 | Tier 2B: Moderate GIDA Inclusion | 67.21 | 67.21 | 46.13 | 56.67 | B - Node 0.5-1 km | 0.63 | 7.31 | Node: MSP001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 1904
2 | 905 | 1905 | 1408104011 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Lenneng | 17.9235 | 121.2147 | R | 2618 | 4.2 | 623 | 187 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.25 | 0.26 | Tier 1B: High GIDA Priority | 52.3 | 52.3 | 61.04 | 56.67 | F - Nearest node and line over 5 km | 11.25 | 18.19 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1905
2 | 906 | 1906 | 1206506008 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Lebak | Kalamongog | 6.7285 | 124.0768 | R | 2967 | 3.8 | 781 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.04 | 66.01 | Tier 1B: High GIDA Priority | 46.13 | 46.13 | 67.21 | 56.67 | F - Nearest node and line over 5 km | 66.04 | 999999 | Node: TKC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1906
2 | 907 | 1907 | 0907312008 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Labangan | Cogonan | 7.9485 | 123.3146 | R | 2018 | 3.9 | 517 | 155 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.97 | 11.83 | Tier 1B: High GIDA Priority | 41.77 | 41.77 | 71.57 | 56.67 | F - Nearest node and line over 5 km | 18.97 | 11.8 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1907
2 | 908 | 1908 | 0806002012 | Region VIII (Eastern Visayas) | Samar | Basey | Catadman | 11.2702 | 125.1544 | R | 681 | 4.1 | 166 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.92 | 16.31 | Tier 1B: High GIDA Priority | 35.81 | 35.81 | 77.52 | 56.66 | F - Nearest node and line over 5 km | 16.92 | 17.08 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1908
2 | 909 | 1909 | 0403415019 | Region IV-A (CALABARZON) | Laguna | Magdalena | Poblacion | 14.1993 | 121.4286 | R | 2735 | 3.3 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.26 | 0.13 | Tier 2A: High Commercial ROI | 73.8 | 73.8 | 39.51 | 56.65 | A - Node within 0.5 km | 0.26 | 0.12 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1909
2 | 910 | 1910 | 0403425023 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Chrysanthemum | 14.3139 | 121.1478 | U | 13629 | 3.3 | 4130 | 1239 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.98 | 4.88 | Tier 2B: Moderate GIDA Inclusion | 65.54 | 65.54 | 47.76 | 56.65 | D - Other node or line within 3 km | 2.98 | 4.88 | Node: SRL004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1910
2 | 911 | 1911 | 1907004003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Mongkay | 4.9239 | 119.8057 | R | 2260 | 5.8 | 390 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 38.59 | 38.59 | 74.7 | 56.65 | F - Nearest node and line over 5 km | 334.23 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1911
2 | 912 | 1912 | 1003521010 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Lindongan | 8.0194 | 123.9703 | R | 411 | 4.2 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.03 | 13.03 | Tier 1B: High GIDA Priority | 37.77 | 37.77 | 75.52 | 56.65 | F - Nearest node and line over 5 km | 19.03 | 13.03 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1912
2 | 913 | 1913 | 1380614025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 769 | 13.9741 | 121.725 | U | 2317 | 4.33 | 535 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.65 | 1.33 | Tier 1B: High GIDA Priority | 42.57 | 42.57 | 70.71 | 56.64 | D - Other node or line within 3 km | 4.65 | 1.32 | Line: LBQ001 TO GCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1913
2 | 914 | 1914 | 0405606011 | Region IV-A (CALABARZON) | Quezon | Burdeos | Palasan | 14.8532 | 122.0502 | R | 1151 | 3.8 | 303 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.78 | 78.78 | Tier 1B: High GIDA Priority | 37.64 | 37.64 | 75.64 | 56.64 | F - Nearest node and line over 5 km | 42.78 | 999999 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1914
2 | 915 | 1915 | 1004316001 | Region X (Northern Mindanao) | Misamis Oriental | Lugait | Aya-aya | 8.3387 | 124.3088 | R | 1697 | 3.9 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.14 | 5.28 | Tier 1B: High GIDA Priority | 48.74 | 48.74 | 64.52 | 56.63 | F - Nearest node and line over 5 km | 7.14 | 5.27 | Line: CDO - ILIGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1915
2 | 916 | 1916 | 0405618045 | Region IV-A (CALABARZON) | Quezon | Guinayangan | San Pedro II | 13.9169 | 122.4675 | R | 266 | 3.8 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 9.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.77 | 42.77 | 70.49 | 56.63 | D - Other node or line within 3 km | 2.46 | 9.07 | Node: GYQ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1916
2 | 917 | 1917 | 1908711003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Mastura | Bungabong | 17.2541 | 122.2281 | R | 2814 | 4.3 | 654 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.19 | Tier 1B: High GIDA Priority | 41.7 | 41.7 | 71.56 | 56.63 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1917
2 | 918 | 1918 | 0600602038 | Region VI (Western Visayas) | Antique | Barbaza | Tabongtabong | 11.1664 | 122.0775 | R | 530 | 3.9 | 136 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.44 | 41.33 | Tier 1B: High GIDA Priority | 36.76 | 36.76 | 76.5 | 56.63 | F - Nearest node and line over 5 km | 47.44 | 40.97 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1918
2 | 919 | 1919 | 0105535008 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Sur | 16.0636 | 120.6672 | R | 4860 | 3.6 | 1350 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.37 | Tier 2A: High Commercial ROI | 72.68 | 72.68 | 40.56 | 56.62 | A - Node within 0.5 km | 0.29 | 0.37 | Node: SMP001 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1919
2 | 920 | 1920 | 1402701005 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Bocos | 16.9162 | 121.0632 | R | 2621 | 3.9 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 44.36 | 56.62 | B - Node 0.5-1 km | 0.64 | 4.65 | Node: BEF001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1920
2 | 921 | 1921 | 1380614034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 778 | 13.9283 | 121.821 | U | 1860 | 4.43 | 420 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.38 | 43.38 | 69.87 | 56.62 | C - Line within 0.5 km; node over 1 km | 1.5 | 0.12 | Line: LCQ001 TO MCQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1921
2 | 922 | 1922 | 1380601011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 11 | 13.9418 | 121.0111 | U | 2790 | 5.09 | 548 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.35 | 6.39 | Tier 1B: High GIDA Priority | 38.47 | 38.47 | 74.78 | 56.62 | F - Nearest node and line over 5 km | 6.35 | 6.31 | Line: UG BUN001 TO SSB001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1922
2 | 923 | 1923 | 0205010010 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Cabalatan Alang | 16.2495 | 120.8833 | R | 232 | 3.8 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.98 | 8.45 | Tier 1B: High GIDA Priority | 36.53 | 36.53 | 76.7 | 56.62 | F - Nearest node and line over 5 km | 9.98 | 8.4 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1923
2 | 924 | 1924 | 0405622087 | Region IV-A (CALABARZON) | Quezon | Lopez | Vergaña | 13.8421 | 122.3494 | R | 874 | 3.8 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.67 | 0.42 | Tier 1B: High GIDA Priority | 41.88 | 41.88 | 71.33 | 56.61 | C - Line within 0.5 km; node over 1 km | 10.67 | 0.39 | Line: LZQ001 TO MCQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1924
2 | 925 | 1925 | 0102901010 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Daddaay | 16.9092 | 120.6013 | R | 713 | 3.8 | 188 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.94 | 14.64 | Tier 1B: High GIDA Priority | 41.66 | 41.66 | 71.57 | 56.61 | F - Nearest node and line over 5 km | 10.94 | 14.51 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1925
2 | 926 | 1926 | 1380611038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 823 | 11.7867 | 120.9889 | U | 3590 | 3.96 | 906 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.65 | 59.67 | Tier 1B: High GIDA Priority | 40.12 | 40.12 | 73.11 | 56.61 | F - Nearest node and line over 5 km | 60.65 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1926
2 | 927 | 1927 | 1381000015 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Sun Valley | 14.4913 | 121.0372 | U | 39136 | 2.7 | 14503 | 4351 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.07 | 0.68 | Tier 1B: High GIDA Priority | 55.66 | 55.66 | 57.53 | 56.6 | D - Other node or line within 3 km | 1.07 | 0.64 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1927
2 | 928 | 1928 | 0405622078 | Region IV-A (CALABARZON) | Quezon | Lopez | Santo Niño Ibaba | 13.8848 | 122.2652 | R | 552 | 3.8 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.21 | Tier 1B: High GIDA Priority | 50.3 | 50.3 | 62.89 | 56.6 | A - Node within 0.5 km | 0.42 | 0.14 | Line: UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1928
2 | 929 | 1929 | 1380601072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 72 | 12.5288 | 120.4304 | U | 3743 | 4.31 | 869 | 261 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.64 | 70.44 | Tier 1B: High GIDA Priority | 39.16 | 39.16 | 74.05 | 56.6 | F - Nearest node and line over 5 km | 61.64 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1929
2 | 930 | 1930 | 0103307033 | Region I (Ilocos Region) | La Union | Bauang | Quinavite | 16.5378 | 120.3295 | R | 3893 | 3.7 | 1052 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.49 | 0.13 | Tier 2A: High Commercial ROI | 71.35 | 71.35 | 41.83 | 56.59 | A - Node within 0.5 km | 0.49 | 0.13 | Line: AGOO - SAN FERNANDO AERIAL_SEGMENT 0 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1930
2 | 931 | 1931 | 0403422004 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Norte | 14.2349 | 121.3655 | R | 2537 | 3.3 | 769 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 67.69 | 67.69 | 45.49 | 56.59 | A - Node within 0.5 km | 0.24 | 0.11 | Line: CLB001 TO SCL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1931
2 | 932 | 1932 | 1003514025 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Pantaon | 8.0566 | 124.0922 | R | 675 | 4.2 | 161 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.71 | 14.27 | Tier 1B: High GIDA Priority | 37.66 | 37.66 | 75.52 | 56.59 | F - Nearest node and line over 5 km | 20.71 | 14.27 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1932
2 | 933 | 1933 | 0301411013 | Region III (Central Luzon) | Bulacan | Marilao | Santa Rosa I | 14.7785 | 120.9732 | U | 11770 | 3.5 | 3363 | 1009 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.32 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 67.68 | 67.68 | 45.48 | 56.58 | D - Other node or line within 3 km | 2.32 | 3.05 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1933
2 | 934 | 1934 | 1380606093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 487 | 12.3426 | 121.056 | U | 1464 | 3.33 | 440 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 1.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.25 | 44.25 | 68.92 | 56.58 | D - Other node or line within 3 km | 1.3 | 1.3 | Node: JOM001 - TYPE 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1934
2 | 935 | 1935 | 0506203011 | Region V (Bicol Region) | Sorsogon | Bulan | Bical | 12.7349 | 123.9377 | R | 686 | 4 | 172 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.39 | 3.36 | Tier 1B: High GIDA Priority | 43.56 | 43.56 | 69.6 | 56.58 | E - Nearest node or line 3-5 km | 7.39 | 3.35 | Line: 30,000m | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1935
2 | 936 | 1936 | 0601903009 | Region VI (Western Visayas) | Capiz | Dumalag | San Martin | 11.3203 | 122.5804 | R | 449 | 3.8 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.66 | 4.77 | Tier 1B: High GIDA Priority | 42.44 | 42.44 | 70.72 | 56.58 | E - Nearest node or line 3-5 km | 12.66 | 4.77 | Line: CABLE LAYED | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1936
2 | 937 | 1937 | 1380611034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 819 | 13.7826 | 121.1255 | U | 2280 | 3.73 | 611 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.53 | 2.58 | Tier 1B: High GIDA Priority | 42.1 | 42.1 | 71.06 | 56.58 | D - Other node or line within 3 km | 3.53 | 2.58 | Line: BATANGAS - SAN JUAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1937
2 | 938 | 1938 | 0600602010 | Region VI (Western Visayas) | Antique | Barbaza | Calapadan | 11.2195 | 122.081 | R | 155 | 3.9 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 49.4 | 47.17 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 76.42 | 56.58 | F - Nearest node and line over 5 km | 49.4 | 49.21 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1938
2 | 939 | 1939 | 0403405056 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Sirang Lupa | 14.2027 | 121.1062 | U | 14182 | 3.3 | 4298 | 1289 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.01 | 0.69 | Tier 2A: High Commercial ROI | 70.87 | 70.87 | 42.25 | 56.56 | D - Other node or line within 3 km | 2.01 | 0.68 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1939
2 | 940 | 1940 | 0402106058 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran II | 14.3494 | 120.9406 | U | 12987 | 3.4 | 3820 | 1146 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.17 | 5.48 | Tier 2B: Moderate GIDA Inclusion | 69.34 | 69.34 | 43.77 | 56.55 | A - Node within 0.5 km | 0.17 | 5.42 | Node: DMC006 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1940
2 | 941 | 1941 | 0306902010 | Region III (Central Luzon) | Tarlac | Bamban | San Nicolas | 15.2788 | 120.5221 | U | 20628 | 3.9 | 5289 | 1587 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.3 | 2.27 | Tier 2B: Moderate GIDA Inclusion | 67.65 | 67.65 | 45.44 | 56.55 | D - Other node or line within 3 km | 1.3 | 1.88 | Node: BBT002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1941
2 | 942 | 1942 | 0600618022 | Region VI (Western Visayas) | Antique | Valderrama | Alon | 11.0566 | 122.2169 | R | 193 | 3.9 | 49 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.61 | 32.98 | Tier 1B: High GIDA Priority | 37.06 | 37.06 | 76.04 | 56.55 | F - Nearest node and line over 5 km | 34.61 | 32.92 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1942
2 | 943 | 1943 | 0301420046 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin II | 14.7929 | 121.084 | R | 3687 | 3.5 | 1053 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 1.08 | Tier 2B: Moderate GIDA Inclusion | 69.3 | 69.3 | 43.79 | 56.54 | D - Other node or line within 3 km | 1.59 | 1.08 | Line: SJDM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1943
2 | 944 | 1944 | 0402123010 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Francisco De Castro | 14.3232 | 121.0275 | U | 10598 | 3.4 | 3117 | 935 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.06 | 2.75 | Tier 2B: Moderate GIDA Inclusion | 63.67 | 63.67 | 49.41 | 56.54 | D - Other node or line within 3 km | 2.06 | 2.49 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1944
2 | 945 | 1945 | 1908702015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Rumidas | 17.2539 | 122.2279 | R | 4409 | 4.3 | 1025 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 49.38 | 49.38 | 63.71 | 56.54 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1945
2 | 946 | 1946 | 1908810006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Meta | 6.8881 | 124.4338 | R | 3810 | 4.7 | 811 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.46 | 34.39 | Tier 1B: High GIDA Priority | 45.46 | 45.46 | 67.62 | 56.54 | F - Nearest node and line over 5 km | 34.46 | 34.39 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1946
2 | 947 | 1947 | 1381100104 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 104 | 14.5449 | 121.0019 | U | 1306 | 3.37 | 387 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.79 | 43.79 | 69.29 | 56.54 | B - Node 0.5-1 km | 0.8 | 0.26 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 1947
2 | 948 | 1948 | 0806017027 | Region VIII (Eastern Visayas) | Samar | Santa Rita | San Pascual | 11.4037 | 124.9964 | R | 1019 | 4.1 | 249 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.26 | 21.31 | Tier 1B: High GIDA Priority | 37.15 | 37.15 | 75.92 | 56.54 | F - Nearest node and line over 5 km | 18.26 | 21.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1948
2 | 949 | 1949 | 0501709013 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Roque | 13.6207 | 123.1741 | U | 3091 | 4.2 | 736 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 1.28 | Tier 2B: Moderate GIDA Inclusion | 64.17 | 64.17 | 48.89 | 56.53 | A - Node within 0.5 km | 0.24 | 1.17 | Node: CLC001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1949
2 | 950 | 1950 | 0301403027 | Region III (Central Luzon) | Bulacan | Baliuag | Tibag | 14.9555 | 120.9039 | U | 3114 | 3.5 | 890 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 60.91 | 60.91 | 52.15 | 56.53 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.09 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1950
2 | 951 | 1951 | 1381200027 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santolan | 14.615 | 121.0823 | U | 61308 | 3.32 | 18476 | 5543 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.73 | 1.08 | Tier 1B: High GIDA Priority | 51.35 | 51.35 | 61.72 | 56.53 | B - Node 0.5-1 km | 0.73 | 1.08 | Node: PSG002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1951
2 | 952 | 1952 | 1705305020 | MIMAROPA Region | Palawan | Bataraza | Tagolango | 8.4802 | 117.2199 | R | 1220 | 3.9 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 217.39 | 219.67 | Tier 1B: High GIDA Priority | 34.43 | 34.43 | 78.62 | 56.53 | F - Nearest node and line over 5 km | 217.39 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1952
2 | 953 | 1953 | 0301403007 | Region III (Central Luzon) | Bulacan | Baliuag | Makinabang | 14.9199 | 120.8866 | U | 13209 | 3.5 | 3774 | 1132 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.13 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 67.9 | 67.9 | 45.14 | 56.52 | C - Line within 0.5 km; node over 1 km | 3.13 | 0.04 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1953
2 | 954 | 1954 | 0402111021 | Region IV-A (CALABARZON) | Cavite | Kawit | Tabon III | 14.426 | 120.8975 | R | 2424 | 3.4 | 713 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 63.52 | 63.52 | 49.53 | 56.52 | C - Line within 0.5 km; node over 1 km | 1.61 | 0.45 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1954
2 | 955 | 1955 | 1403201016 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Tawang | 17.5905 | 121.2204 | R | 836 | 4.3 | 194 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.28 | 19.71 | Tier 1B: High GIDA Priority | 36.01 | 36.01 | 77.03 | 56.52 | F - Nearest node and line over 5 km | 13.28 | 19.7 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1955
2 | 956 | 1956 | 0501605007 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Luklukan Sur | 14.3065 | 122.7192 | R | 4173 | 4 | 1043 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.44 | 12.77 | Tier 2B: Moderate GIDA Inclusion | 65.43 | 65.43 | 47.58 | 56.51 | E - Nearest node or line 3-5 km | 3.44 | 12.77 | Node: JPC001 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1956
2 | 957 | 1957 | 0301406002 | Region III (Central Luzon) | Bulacan | Bustos | Bonga Menor | 14.9499 | 120.9339 | U | 5541 | 3.5 | 1583 | 475 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.73 | 0.94 | Tier 2B: Moderate GIDA Inclusion | 63.18 | 63.18 | 49.84 | 56.51 | D - Other node or line within 3 km | 1.73 | 1.11 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1957
2 | 958 | 1958 | 0301414008 | Region III (Central Luzon) | Bulacan | Obando | Paliwas | 14.7132 | 120.935 | U | 5749 | 3.5 | 1643 | 493 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 2.42 | Tier 2B: Moderate GIDA Inclusion | 62.24 | 62.24 | 50.78 | 56.51 | A - Node within 0.5 km | 0.45 | 2.42 | Node: OBB001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1958
2 | 959 | 1959 | 1381400001 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Addition Hills | 14.6007 | 121.0332 | U | 5436 | 4.57 | 1189 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 57.88 | 57.88 | 55.14 | 56.51 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.19 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1959
2 | 960 | 1960 | 0405640001 | Region IV-A (CALABARZON) | Quezon | San Andres | Alibihaban | 13.3276 | 122.716 | R | 1552 | 3.8 | 408 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.21 | 31.73 | Tier 1B: High GIDA Priority | 52.92 | 52.92 | 60.09 | 56.51 | E - Nearest node or line 3-5 km | 4.21 | 31.73 | Node: SDQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1960
2 | 961 | 1961 | 1908804006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Tugal | 17.2552 | 122.2292 | R | 4470 | 4.7 | 951 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 49.13 | 49.13 | 63.89 | 56.51 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1961
2 | 962 | 1962 | 1381100062 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 62 | 14.6187 | 121.0072 | U | 1268 | 3.37 | 376 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.21 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.27 | 43.27 | 69.75 | 56.51 | B - Node 0.5-1 km | 0.93 | 0.09 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 1962
2 | 963 | 1963 | 0205009018 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Pao | 16.2313 | 121.3495 | R | 1508 | 3.8 | 397 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.16 | 30.59 | Tier 1B: High GIDA Priority | 42.62 | 42.62 | 70.39 | 56.51 | F - Nearest node and line over 5 km | 11.16 | 30.58 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1963
2 | 964 | 1964 | 0600401011 | Region VI (Western Visayas) | Aklan | Altavas | Poblacion | 11.535 | 122.4913 | R | 4795 | 3.9 | 1229 | 369 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.25 | Tier 2A: High Commercial ROI | 79.41 | 79.41 | 33.58 | 56.5 | B - Node 0.5-1 km | 0.51 | 0.25 | Line: IVISAN - KALIBO | Survey short node lateral; confirm port/fiber capacity, access and route. | 1964
2 | 965 | 1965 | 1380610019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 704 | 12.7526 | 120.2835 | U | 5339 | 4.29 | 1245 | 374 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.64 | 94.17 | Tier 1B: High GIDA Priority | 41.79 | 41.79 | 71.22 | 56.5 | F - Nearest node and line over 5 km | 78.64 | 999999 | Node: BSW001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1965
2 | 966 | 1966 | 1003511010 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Malabaogan | 8.0401 | 123.9078 | R | 523 | 4.2 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.96 | 7.66 | Tier 1B: High GIDA Priority | 41.45 | 41.45 | 71.55 | 56.5 | F - Nearest node and line over 5 km | 11.96 | 7.66 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1966
2 | 967 | 1967 | 0401005058 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 12 | 13.7347 | 121.093 | U | 1434 | 3.6 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.86 | 4.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.06 | 42.06 | 70.91 | 56.49 | D - Other node or line within 3 km | 2.86 | 4.05 | Node: BCY003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1967
2 | 968 | 1968 | 0205009005 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Binogawan | 16.3746 | 121.3939 | R | 891 | 3.8 | 234 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.43 | 22.74 | Tier 1B: High GIDA Priority | 37.2 | 37.2 | 75.77 | 56.49 | F - Nearest node and line over 5 km | 12.43 | 22.73 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1968
2 | 969 | 1969 | 0300812005 | Region III (Central Luzon) | Bataan | Samal | Lalawigan | 14.779 | 120.5426 | R | 5001 | 3.6 | 1389 | 417 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.65 | 0.19 | Tier 2A: High Commercial ROI | 73.23 | 73.23 | 39.72 | 56.48 | C - Line within 0.5 km; node over 1 km | 2.65 | 0.07 | Line: 36 CORE 3X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1969
2 | 970 | 1970 | 0403426013 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Patimbao | 14.2724 | 121.4172 | U | 10201 | 3.3 | 3091 | 927 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 69.13 | 69.13 | 43.83 | 56.48 | B - Node 0.5-1 km | 0.87 | 0.03 | Line: CLB001 TO SCL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1970
2 | 971 | 1971 | 0304926033 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Sibut | 15.7894 | 120.9978 | U | 7055 | 3.5 | 2016 | 605 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 65.37 | 65.37 | 47.58 | 56.48 | D - Other node or line within 3 km | 1.22 | 0.58 | Line: SAN JOSE DICT PROJECT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1971
2 | 972 | 1972 | 0201528033 | Region II (Cagayan Valley) | Cagayan | Tuao | Malalinta | 17.6591 | 121.4887 | R | 970 | 3.9 | 249 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.79 | 6.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.84 | 45.84 | 67.12 | 56.48 | D - Other node or line within 3 km | 2.79 | 6.21 | Node: TUC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1972
2 | 973 | 1973 | 0907312010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Labangan | Dipaya | 7.9232 | 123.434 | R | 1191 | 3.9 | 305 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.29 | 8.97 | Tier 1B: High GIDA Priority | 41.4 | 41.4 | 71.56 | 56.48 | F - Nearest node and line over 5 km | 10.29 | 8.97 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1973
2 | 974 | 1974 | 1401110005 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Balili | 16.4497 | 120.5949 | U | 18238 | 3.5 | 5211 | 1563 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.75 | 0.52 | Tier 2A: High Commercial ROI | 73.1 | 73.1 | 39.84 | 56.47 | B - Node 0.5-1 km | 0.75 | 0.52 | Line: LA TRINIDAD-SAGADA | Survey short node lateral; confirm port/fiber capacity, access and route. | 1974
2 | 975 | 1975 | 0304925004 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Malapit | 15.3043 | 120.9212 | U | 10459 | 3.5 | 2988 | 896 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.07 | 0.16 | Tier 2A: High Commercial ROI | 70.66 | 70.66 | 42.28 | 56.47 | C - Line within 0.5 km; node over 1 km | 2.18 | 0.07 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1975
2 | 976 | 1976 | 0403411008 | Region IV-A (CALABARZON) | Laguna | Los Baños | Maahas | 14.1774 | 121.2511 | U | 9630 | 3.3 | 2918 | 875 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 68.42 | 68.42 | 44.52 | 56.47 | B - Node 0.5-1 km | 0.96 | 0.08 | Line: AE SPO001 TO LBL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 1976
2 | 977 | 1977 | 0601904003 | Region VI (Western Visayas) | Capiz | Dumarao | Aglanot | 11.2396 | 122.8401 | R | 1928 | 3.8 | 507 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.79 | 6.51 | Tier 1B: High GIDA Priority | 51.19 | 51.19 | 61.76 | 56.47 | F - Nearest node and line over 5 km | 6.79 | 6.5 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1977
2 | 978 | 1978 | 0600618008 | Region VI (Western Visayas) | Antique | Valderrama | Busog | 11.071 | 122.2418 | R | 203 | 3.9 | 52 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.74 | 31.23 | Tier 1B: High GIDA Priority | 37.16 | 37.16 | 75.79 | 56.47 | F - Nearest node and line over 5 km | 32.74 | 31.16 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1978
2 | 979 | 1979 | 0403419016 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | San Isidro | 14.2798 | 121.4581 | R | 3022 | 3.3 | 916 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 69.52 | 69.52 | 43.41 | 56.46 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.09 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1979
2 | 980 | 1980 | 0402118016 | Region IV-A (CALABARZON) | Cavite | Silang | Inchican | 14.2504 | 121.0533 | U | 6206 | 3.4 | 1825 | 548 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 66.73 | 66.73 | 46.18 | 56.46 | A - Node within 0.5 km | 0.16 | 0.97 | Node: SGC005 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1980
2 | 981 | 1981 | 1403211017 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Romualdez | 17.4318 | 121.6154 | R | 834 | 3.6 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.65 | 0.14 | Tier 1B: High GIDA Priority | 50.49 | 50.49 | 62.44 | 56.46 | C - Line within 0.5 km; node over 1 km | 7.65 | 0.12 | Line: RIZAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1981
2 | 982 | 1982 | 0203110006 | Region II (Cagayan Valley) | Isabela | Dinapigue | Dimaluade | 16.5361 | 122.2533 | R | 300 | 3.8 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 1.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.8 | 47.8 | 65.12 | 56.46 | D - Other node or line within 3 km | 1.62 | 999999 | Node: DPI001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1982
2 | 983 | 1983 | 1400126010 | Cordillera Administrative Region (CAR) | Abra | Tubo | Tabacda | 17.2666 | 120.845 | R | 279 | 3.8 | 73 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.1 | 20.91 | Tier 1B: High GIDA Priority | 35.62 | 35.62 | 77.31 | 56.46 | F - Nearest node and line over 5 km | 21.1 | 20.8 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1983
2 | 984 | 1984 | 0301420020 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay II | 14.8274 | 121.0482 | U | 4364 | 3.5 | 1247 | 374 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 61.67 | 61.67 | 51.23 | 56.45 | D - Other node or line within 3 km | 2.04 | 3.16 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1984
2 | 985 | 1985 | 0102906016 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Calaoaan | 17.1678 | 120.4417 | R | 2658 | 3.8 | 699 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.72 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 61.56 | 61.56 | 51.34 | 56.45 | C - Line within 0.5 km; node over 1 km | 2.72 | 0.11 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1985
2 | 986 | 1986 | 0806010019 | Region VIII (Eastern Visayas) | Samar | Marabut | Malobago | 11.1156 | 125.2443 | R | 529 | 4.1 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.51 | 23.47 | Tier 1B: High GIDA Priority | 38 | 38 | 74.9 | 56.45 | F - Nearest node and line over 5 km | 24.51 | 27.3 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1986
2 | 987 | 1987 | 0702227013 | Region VII (Central Visayas) | Cebu | Liloan | Tayud | 10.381 | 123.9954 | U | 22475 | 3.8 | 5914 | 1774 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.97 | 0.25 | Tier 2A: High Commercial ROI | 72.85 | 72.85 | 40.02 | 56.44 | C - Line within 0.5 km; node over 1 km | 2.97 | 0.05 | Line: Route 7.591km | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1987
2 | 988 | 1988 | 1108211004 | Region XI (Davao Region) | Davao de Oro | Pantukan | Kingking | 7.1375 | 125.9237 | U | 29937 | 3.7 | 8091 | 2427 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.75 | 2.74 | Tier 2B: Moderate GIDA Inclusion | 65.08 | 65.08 | 47.79 | 56.44 | D - Other node or line within 3 km | 2.75 | 2.73 | Line: TAGUM - PANTUKAN SEGMENT 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1988
2 | 989 | 1989 | 1403201007 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Gawa-an | 17.5162 | 121.2066 | R | 1006 | 4.3 | 234 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.92 | 12.19 | Tier 1B: High GIDA Priority | 36.06 | 36.06 | 76.82 | 56.44 | F - Nearest node and line over 5 km | 14.92 | 12.18 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1989
2 | 990 | 1990 | 0405801008 | Region IV-A (CALABARZON) | Rizal | Angono | Poblacion Itaas | 14.5405 | 121.1672 | R | 538 | 3.6 | 149 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 1.83 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.56 | 47.56 | 65.3 | 56.43 | D - Other node or line within 3 km | 1.98 | 1.8 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1990
2 | 991 | 1991 | 0205702014 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Dingasan | 16.3413 | 121.5177 | R | 1393 | 3.9 | 357 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.54 | 14.91 | Tier 1B: High GIDA Priority | 38.15 | 38.15 | 74.72 | 56.43 | F - Nearest node and line over 5 km | 16.54 | 14.91 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1991
2 | 992 | 1992 | 0304901021 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Poblacion East I | 15.5031 | 120.8686 | R | 2597 | 3.5 | 742 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.27 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 66.92 | 66.92 | 45.92 | 56.42 | A - Node within 0.5 km | 0.27 | 0.05 | Line: 38,161m. | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 1992
2 | 993 | 1993 | 0300810013 | Region III (Central Luzon) | Bataan | Orion | Daang Pare | 14.6001 | 120.5794 | U | 8415 | 3.6 | 2338 | 701 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 65.51 | 65.51 | 47.34 | 56.42 | C - Line within 0.5 km; node over 1 km | 1.7 | 0.03 | Line: PIPE ORION-MARIVELES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 1993
2 | 994 | 1994 | 0604531004 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay I | 10.8848 | 123.117 | R | 3756 | 3.7 | 1015 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.14 | 3.67 | Tier 2B: Moderate GIDA Inclusion | 63.32 | 63.32 | 49.53 | 56.42 | E - Nearest node or line 3-5 km | 5.14 | 3.66 | Line: TALISAY - VICTORIAS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1994
2 | 995 | 1995 | 1004326004 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Katipunan | 8.5778 | 124.7905 | U | 5463 | 3.9 | 1401 | 420 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.77 | 2.2 | Tier 2B: Moderate GIDA Inclusion | 59.38 | 59.38 | 53.47 | 56.42 | D - Other node or line within 3 km | 2.77 | 2.2 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 1995
2 | 996 | 1996 | 1404405003 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Banao | 17.0715 | 121.2126 | R | 300 | 3.7 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.27 | 18.01 | Tier 1B: High GIDA Priority | 43.57 | 43.57 | 69.26 | 56.42 | F - Nearest node and line over 5 km | 8.27 | 17.91 | Node: NNV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1996
2 | 997 | 1997 | 0401005029 | Region IV-A (CALABARZON) | Batangas | Batangas City | Gulod Labak | 13.7217 | 121.0815 | U | 2487 | 3.6 | 691 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.36 | 4.37 | Tier 1B: High GIDA Priority | 48.52 | 48.52 | 64.3 | 56.41 | E - Nearest node or line 3-5 km | 4.36 | 4.37 | Node: BCY004 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1997
2 | 998 | 1998 | 0102917006 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Sibsibbu | 17.2978 | 120.5731 | R | 633 | 3.8 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.41 | 6.5 | Tier 1B: High GIDA Priority | 44.97 | 44.97 | 67.85 | 56.41 | F - Nearest node and line over 5 km | 7.41 | 6.49 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1998
2 | 999 | 1999 | 1380606206 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 599 | 11.4591 | 121.9659 | U | 4577 | 4.94 | 927 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.4 | 42.03 | Tier 1B: High GIDA Priority | 40.64 | 40.64 | 72.17 | 56.41 | F - Nearest node and line over 5 km | 40.4 | 999999 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1999
2 | 1000 | 2000 | 1606808009 | Region XIII (Caraga) | Surigao del Sur | Cortes | Tag-Anongan | 9.2315 | 126.1919 | R | 916 | 4.1 | 223 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.2 | 2.44 | Tier 1B: High GIDA Priority | 40.36 | 40.36 | 72.46 | 56.41 | D - Other node or line within 3 km | 17.2 | 2.44 | Line: Route | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2000

## Batch 3 (2,001 - 3,000)
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization — Batch 3 (2,001 - 3,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
3 | 1 | 2001 | 0502002012 | Region V (Bicol Region) | Catanduanes | Baras | J. M. Alberto | 13.686 | 124.3724 | R | 764 | 4.2 | 182 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.85 | 78.23 | Tier 1B: High GIDA Priority | 37.33 | 37.33 | 75.49 | 56.41 | F - Nearest node and line over 5 km | 55.85 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2001
3 | 2 | 2002 | 1380601117 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 117 | 11.5872 | 121.1557 | U | 4262 | 4.82 | 885 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.26 | 77.96 | Tier 1B: High GIDA Priority | 39.59 | 39.59 | 73.21 | 56.4 | F - Nearest node and line over 5 km | 80.26 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2002
3 | 3 | 2003 | 0405802003 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dela Paz | 14.5975 | 121.1726 | U | 73910 | 3.6 | 20531 | 6159 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 1.12 | 0.08 | Tier 1B: High GIDA Priority | 51.41 | 51.41 | 61.36 | 56.38 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.08 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2003
3 | 4 | 2004 | 0601909009 | Region VI (Western Visayas) | Capiz | Panay | Bantique | 11.4937 | 122.8898 | R | 1408 | 3.8 | 371 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.34 | 6.21 | Tier 1B: High GIDA Priority | 48.27 | 48.27 | 64.48 | 56.38 | F - Nearest node and line over 5 km | 6.34 | 6.2 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2004
3 | 5 | 2005 | 1380604014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 281 | 13.7923 | 122.5595 | U | 3436 | 4.27 | 805 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.59 | 11.91 | Tier 1B: High GIDA Priority | 43.57 | 43.57 | 69.19 | 56.38 | F - Nearest node and line over 5 km | 8.59 | 11.89 | Node: GYQ002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2005
3 | 6 | 2006 | 0401005067 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 20 | 13.7552 | 121.0545 | U | 394 | 3.6 | 109 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.43 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.45 | 41.45 | 71.3 | 56.38 | B - Node 0.5-1 km | 0.84 | 0.43 | Line: LEMERY TO SAN JUAN CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 2006
3 | 7 | 2007 | 0601905007 | Region VI (Western Visayas) | Capiz | Ivisan | Ilaya-Ivisan | 11.5178 | 122.7197 | R | 4049 | 3.8 | 1066 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.83 | 0.12 | Tier 2A: High Commercial ROI | 74.67 | 74.67 | 38.06 | 56.37 | C - Line within 0.5 km; node over 1 km | 2.83 | 0.12 | Line: ROXAS - IVISAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2007
3 | 8 | 2008 | 0301420024 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima III | 14.8455 | 121.0482 | R | 2038 | 3.5 | 582 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 1.78 | Tier 2B: Moderate GIDA Inclusion | 60.64 | 60.64 | 52.1 | 56.37 | D - Other node or line within 3 km | 1.27 | 5 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2008
3 | 9 | 2009 | 1381300047 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kalusugan | 14.6953 | 121.05 | U | 5334 | 4.41 | 1209 | 363 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.06 | 1.67 | Tier 2B: Moderate GIDA Inclusion | 56.79 | 56.79 | 55.96 | 56.37 | D - Other node or line within 3 km | 2.06 | 1.67 | Line: UG 144C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2009
3 | 10 | 2010 | 0403418009 | Region IV-A (CALABARZON) | Laguna | Paete | Quinale | 14.3617 | 121.4834 | U | 7953 | 3.3 | 2410 | 723 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.4 | Tier 2A: High Commercial ROI | 72.51 | 72.51 | 40.22 | 56.36 | A - Node within 0.5 km | 0.39 | 0.36 | Line: SEGMENT 23 (FAMY - STA CRUZ) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2010
3 | 11 | 2011 | 0501705014 | Region V (Bicol Region) | Camarines Sur | Buhi | Iraya | 13.4712 | 123.526 | R | 3170 | 4.2 | 755 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.25 | 6.48 | Tier 2B: Moderate GIDA Inclusion | 56.9 | 56.9 | 55.82 | 56.36 | F - Nearest node and line over 5 km | 6.25 | 9.04 | Node: BIC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2011
3 | 12 | 2012 | 1381200025 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Rosa | 14.5726 | 121.0979 | U | 1044 | 3.73 | 280 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.81 | 40.81 | 71.9 | 56.36 | B - Node 0.5-1 km | 0.89 | 0.33 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2012
3 | 13 | 2013 | 0301417021 | Region III (Central Luzon) | Bulacan | Plaridel | Tabang | 14.8743 | 120.8619 | U | 18030 | 3.5 | 5151 | 1545 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.34 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 68.43 | 68.43 | 44.27 | 56.35 | C - Line within 0.5 km; node over 1 km | 3.34 | 0.09 | Line: 16 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2013
3 | 14 | 2014 | 0301413006 | Region III (Central Luzon) | Bulacan | Norzagaray | Bigte | 14.8616 | 121.0951 | U | 15803 | 3.5 | 4515 | 1354 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.16 | 6.63 | Tier 2B: Moderate GIDA Inclusion | 67.27 | 67.27 | 45.43 | 56.35 | D - Other node or line within 3 km | 2.16 | 7.84 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2014
3 | 15 | 2015 | 0504103011 | Region V (Bicol Region) | Masbate | Balud | Jangan | 12.0162 | 123.2738 | R | 866 | 4.1 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.02 | 8.58 | Tier 1B: High GIDA Priority | 48.96 | 48.96 | 63.74 | 56.35 | F - Nearest node and line over 5 km | 7.02 | 34.02 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2015
3 | 16 | 2016 | 1908709009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Kabuan | 17.2541 | 122.2281 | R | 3495 | 4.3 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.19 | Tier 1B: High GIDA Priority | 45.89 | 45.89 | 66.8 | 56.35 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2016
3 | 17 | 2017 | 0500512033 | Region V (Bicol Region) | Albay | Oas | Mayag | 13.168 | 123.3985 | R | 453 | 4.1 | 110 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.69 | 14.99 | Tier 1B: High GIDA Priority | 43.35 | 43.35 | 69.36 | 56.35 | F - Nearest node and line over 5 km | 6.69 | 14.93 | Node: LOA003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2017
3 | 18 | 2018 | 1102505004 | Region XI (Davao Region) | Davao Oriental | Cateel | Aragon | 7.7655 | 126.3669 | R | 2252 | 3.6 | 626 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.92 | 33.88 | Tier 1B: High GIDA Priority | 42.75 | 42.75 | 69.94 | 56.35 | F - Nearest node and line over 5 km | 34.92 | 33.88 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2018
3 | 19 | 2019 | 1381100038 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 38 | 14.5409 | 120.9498 | U | 1979 | 3.09 | 641 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.72 | 4.73 | Tier 1B: High GIDA Priority | 41.82 | 41.82 | 70.86 | 56.34 | E - Nearest node or line 3-5 km | 4.72 | 4.72 | Node: PSY002 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2019
3 | 20 | 2020 | 0803734019 | Region VIII (Eastern Visayas) | Leyte | Matalom | President Garcia | 10.2493 | 124.8171 | R | 874 | 3.8 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.87 | 4.48 | Tier 1B: High GIDA Priority | 39.45 | 39.45 | 73.23 | 56.34 | E - Nearest node or line 3-5 km | 13 | 4.48 | Line: INOPACAN (BAYBAY) - MAASIN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2020
3 | 21 | 2021 | 0802615011 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Omawas | 11.5311 | 125.474 | R | 1082 | 3.9 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.77 | 61.29 | Tier 1B: High GIDA Priority | 39.41 | 39.41 | 73.28 | 56.34 | F - Nearest node and line over 5 km | 60.77 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2021
3 | 22 | 2022 | 0402104015 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 4 | 14.2937 | 121.0439 | R | 684 | 3.4 | 201 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.65 | 2.03 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.95 | 45.95 | 66.71 | 56.33 | D - Other node or line within 3 km | 1.65 | 2.03 | Node: BNL003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2022
3 | 23 | 2023 | 1907010007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Kohec | 16.3108 | 122.0748 | R | 407 | 5.8 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.42 | 5.18 | Tier 1B: High GIDA Priority | 38.64 | 38.64 | 74.01 | 56.33 | F - Nearest node and line over 5 km | 6.42 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2023
3 | 24 | 2024 | 0600618009 | Region VI (Western Visayas) | Antique | Valderrama | Cananghan | 11.025 | 122.1841 | R | 308 | 3.9 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.98 | 32.42 | Tier 1B: High GIDA Priority | 36.96 | 36.96 | 75.69 | 56.33 | F - Nearest node and line over 5 km | 36.98 | 32.16 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2024
3 | 25 | 2025 | 0306916088 | Region III (Central Luzon) | Tarlac | City of Tarlac | Tibag | 15.5073 | 120.5707 | U | 18566 | 3.9 | 4761 | 1428 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.31 | 0.11 | Tier 2A: High Commercial ROI | 71.82 | 71.82 | 40.81 | 56.32 | C - Line within 0.5 km; node over 1 km | 1.31 | 0.06 | Line: 48 CORE (8X6) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2025
3 | 26 | 2026 | 0401003029 | Region IV-A (CALABARZON) | Batangas | Balayan | Gumamela | 13.9453 | 120.7417 | R | 3142 | 3.6 | 873 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.49 | 0.02 | Tier 2B: Moderate GIDA Inclusion | 68.09 | 68.09 | 44.55 | 56.32 | C - Line within 0.5 km; node over 1 km | 1.49 | 0.02 | Line: AE BYB001 TO LYB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2026
3 | 27 | 2027 | 0600404003 | Region VI (Western Visayas) | Aklan | Batan | Bay-ang | 11.5994 | 122.4447 | R | 2259 | 3.9 | 579 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.51 | 2.1 | Tier 2B: Moderate GIDA Inclusion | 57.87 | 57.87 | 54.77 | 56.32 | D - Other node or line within 3 km | 5.51 | 2.08 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2027
3 | 28 | 2028 | 0403416033 | Region IV-A (CALABARZON) | Laguna | Majayjay | San Francisco | 14.1832 | 121.4603 | R | 3178 | 3.3 | 963 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.6 | 3.2 | Tier 2B: Moderate GIDA Inclusion | 67.1 | 67.1 | 45.51 | 56.31 | E - Nearest node or line 3-5 km | 3.6 | 3.19 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2028
3 | 29 | 2029 | 1380613002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 650 | 11.9926 | 122.9599 | U | 4889 | 3.51 | 1394 | 418 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.63 | 21.67 | Tier 1B: High GIDA Priority | 42.22 | 42.22 | 70.4 | 56.31 | F - Nearest node and line over 5 km | 31.63 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2029
3 | 30 | 2030 | 0301407008 | Region III (Central Luzon) | Bulacan | Calumpit | Caniogan | 14.9044 | 120.7739 | U | 4714 | 3.5 | 1347 | 404 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 48.26 | 56.3 | B - Node 0.5-1 km | 0.69 | 0.09 | Line: Calumpit-Baliuag Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 2030
3 | 31 | 2031 | 0402117008 | Region IV-A (CALABARZON) | Cavite | Rosario | Poblacion | 14.4172 | 120.8559 | U | 2210 | 3.4 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.21 | 2.44 | Tier 1B: High GIDA Priority | 49.86 | 49.86 | 62.74 | 56.3 | D - Other node or line within 3 km | 2.21 | 2.44 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2031
3 | 32 | 2032 | 0301404017 | Region III (Central Luzon) | Bulacan | Bocaue | Tambobong | 14.8157 | 120.9398 | U | 7655 | 3.5 | 2187 | 656 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 64.57 | 64.57 | 48.01 | 56.29 | D - Other node or line within 3 km | 2.01 | 0.96 | Line: STA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2032
3 | 33 | 2033 | 1102319009 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Madaum | 7.3789 | 125.8088 | U | 14663 | 3.7 | 3963 | 1189 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 5.05 | 3.3 | Tier 2B: Moderate GIDA Inclusion | 64.22 | 64.22 | 48.35 | 56.29 | E - Nearest node or line 3-5 km | 5.05 | 3.26 | Line: TAGUM - PANTUKAN SEGMENT 2 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2033
3 | 34 | 2034 | 1403213021 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Magnao | 17.434 | 121.3196 | R | 1158 | 4.3 | 269 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.93 | 3.08 | Tier 1B: High GIDA Priority | 38.99 | 38.99 | 73.58 | 56.29 | E - Nearest node or line 3-5 km | 11.93 | 3.02 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2034
3 | 35 | 2035 | 0403410018 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Palina | 14.134 | 121.4335 | R | 2517 | 3.3 | 763 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.15 | Tier 2A: High Commercial ROI | 71.69 | 71.69 | 40.87 | 56.28 | A - Node within 0.5 km | 0.39 | 0.05 | Line: SPO001 TO LBQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2035
3 | 36 | 2036 | 0403426002 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Bagumbayan | 14.2684 | 121.4 | U | 14649 | 3.3 | 4439 | 1332 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.85 | 0.71 | Tier 2A: High Commercial ROI | 71 | 71 | 41.55 | 56.28 | D - Other node or line within 3 km | 1.85 | 0.71 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2036
3 | 37 | 2037 | 1108202022 | Region XI (Davao Region) | Davao de Oro | Laak | Bullucan | 7.8604 | 125.8094 | R | 1345 | 3.7 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.43 | 24.65 | Tier 1B: High GIDA Priority | 36.91 | 36.91 | 75.65 | 56.28 | F - Nearest node and line over 5 km | 27.43 | 24.6 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2037
3 | 38 | 2038 | 0305417014 | Region III (Central Luzon) | Pampanga | San Luis | Santa Monica | 15.0364 | 120.7896 | R | 3403 | 4 | 851 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 69.7 | 69.7 | 42.84 | 56.27 | A - Node within 0.5 km | 0.32 | 0.06 | Line: SanLuis PIPE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2038
3 | 39 | 2039 | 0401003048 | Region IV-A (CALABARZON) | Batangas | Balayan | Santol | 13.9412 | 120.7131 | R | 4267 | 3.6 | 1185 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 1.03 | Tier 2B: Moderate GIDA Inclusion | 69.39 | 69.39 | 43.16 | 56.27 | D - Other node or line within 3 km | 1.64 | 1.03 | Line: BALAYAN - CALATAGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2039
3 | 40 | 2040 | 0205705003 | Region II (Cagayan Valley) | Quirino | Saguday | Magsaysay | 16.5383 | 121.5609 | R | 2636 | 3.9 | 676 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 68.81 | 68.81 | 43.73 | 56.27 | B - Node 0.5-1 km | 0.66 | 0.08 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2040
3 | 41 | 2041 | 1401107004 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Bashoy | 16.5712 | 120.8485 | R | 2224 | 3.5 | 635 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.19 | 9.57 | Tier 2B: Moderate GIDA Inclusion | 58.05 | 58.05 | 54.5 | 56.27 | F - Nearest node and line over 5 km | 6.19 | 9.42 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2041
3 | 42 | 2042 | 1705323011 | MIMAROPA Region | Palawan | Rizal | Taburi | 8.7258 | 117.3748 | U | 5624 | 3.6 | 1562 | 469 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 187.01 | 189.26 | Tier 1B: High GIDA Priority | 45.24 | 45.24 | 67.29 | 56.27 | F - Nearest node and line over 5 km | 187.01 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2042
3 | 43 | 2043 | 0501607001 | Region V (Bicol Region) | Camarines Norte | Mercedes | Apuao | 14.0806 | 123.0945 | R | 610 | 4 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.24 | 14.33 | Tier 1B: High GIDA Priority | 41.01 | 41.01 | 71.53 | 56.27 | F - Nearest node and line over 5 km | 9.24 | 14.33 | Node: BDC002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2043
3 | 44 | 2044 | 0403413011 | Region IV-A (CALABARZON) | Laguna | Lumban | Primera Pulo | 14.3038 | 121.4586 | R | 2306 | 3.3 | 699 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 48.19 | 56.26 | B - Node 0.5-1 km | 0.95 | 0.74 | Line: SNL001 TO SCL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2044
3 | 45 | 2045 | 0304926021 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Canuto Ramos Pob. | 15.7887 | 120.9897 | R | 2255 | 3.5 | 644 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 63.36 | 63.36 | 49.16 | 56.26 | B - Node 0.5-1 km | 0.68 | 0.22 | Line: SAN JOSE DICT PROJECT | Survey short node lateral; confirm port/fiber capacity, access and route. | 2045
3 | 46 | 2046 | 0504113014 | Region V (Bicol Region) | Masbate | Mobo | Mapuyo | 12.2286 | 123.6424 | R | 570 | 4.1 | 139 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.16 | 11.77 | Tier 1B: High GIDA Priority | 42.81 | 42.81 | 69.71 | 56.26 | F - Nearest node and line over 5 km | 12.16 | 11.76 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2046
3 | 47 | 2047 | 1381100022 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 22 | 14.5726 | 121.008 | U | 1224 | 3.4 | 360 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.93 | 41.93 | 70.59 | 56.26 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.39 | Line: UG 288C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2047
3 | 48 | 2048 | 1108602026 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Patulang | 5.6812 | 125.4807 | R | 1662 | 3.6 | 462 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 52.19 | 58.53 | Tier 1B: High GIDA Priority | 38.47 | 38.47 | 74.06 | 56.26 | F - Nearest node and line over 5 km | 52.19 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2048
3 | 49 | 2049 | 0102908006 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Dinwede West | 16.9055 | 120.6042 | R | 843 | 3.8 | 222 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.45 | 14.95 | Tier 1B: High GIDA Priority | 42.2 | 42.2 | 70.29 | 56.25 | F - Nearest node and line over 5 km | 11.45 | 14.82 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2049
3 | 50 | 2050 | 1102506012 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Sergio Osmeña | 6.5349 | 126.1108 | R | 2020 | 3.6 | 561 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.63 | 38.22 | Tier 1B: High GIDA Priority | 40.93 | 40.93 | 71.57 | 56.25 | F - Nearest node and line over 5 km | 41.63 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2050
3 | 51 | 2051 | 0506207004 | Region V (Bicol Region) | Sorsogon | Donsol | Bandi | 12.9886 | 123.5854 | R | 372 | 4 | 93 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.33 | 14.39 | Tier 1B: High GIDA Priority | 40.91 | 40.91 | 71.6 | 56.25 | F - Nearest node and line over 5 km | 9.33 | 14.34 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2051
3 | 52 | 2052 | 0203135026 | Region II (Cagayan Valley) | Isabela | City of Santiago | Rosario | 16.6799 | 121.5457 | U | 12845 | 3.8 | 3380 | 1014 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.39 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 44.84 | 56.24 | D - Other node or line within 3 km | 2.39 | 0.61 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2052
3 | 53 | 2053 | 0403411014 | Region IV-A (CALABARZON) | Laguna | Los Baños | Timugan | 14.1781 | 121.2224 | U | 6410 | 3.3 | 1942 | 583 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 63.41 | 63.41 | 49.07 | 56.24 | C - Line within 0.5 km; node over 1 km | 2.16 | 0.06 | Line: AE LBL001-STB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2053
3 | 54 | 2054 | 1381100024 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 24 | 14.5136 | 121.0234 | U | 767 | 2.56 | 300 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.59 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.84 | 40.84 | 71.63 | 56.24 | D - Other node or line within 3 km | 1.16 | 0.59 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2054
3 | 55 | 2055 | 0300809023 | Region III (Central Luzon) | Bataan | Orani | Tugatog | 14.8014 | 120.5192 | U | 8501 | 3.6 | 2361 | 708 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 65.35 | 65.35 | 47.11 | 56.23 | C - Line within 0.5 km; node over 1 km | 1.84 | 0.12 | Line: ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2055
3 | 56 | 2056 | 1381600015 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Mabolo | 14.6985 | 120.9766 | U | 1122 | 3.01 | 373 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.22 | 44.22 | 68.25 | 56.23 | A - Node within 0.5 km | 0.42 | 0.05 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2056
3 | 57 | 2057 | 0702219006 | Region VII (Central Visayas) | Cebu | Consolacion | Jugan | 10.38 | 123.9725 | U | 13063 | 3.8 | 3438 | 1031 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.55 | 0.38 | Tier 2A: High Commercial ROI | 71.05 | 71.05 | 41.39 | 56.22 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.29 | Line: DANAO - CEBU | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2057
3 | 58 | 2058 | 1600308019 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 5 | 8.5042 | 125.9821 | U | 6068 | 3.9 | 1556 | 467 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 66.34 | 66.34 | 46.1 | 56.22 | B - Node 0.5-1 km | 0.87 | 0.48 | Line: TRENTO - BUENAVISTA CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 2058
3 | 59 | 2059 | 1705320018 | MIMAROPA Region | Palawan | Taytay | Pancol | 10.8707 | 119.4166 | R | 3530 | 3.9 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 10.77 | Tier 2B: Moderate GIDA Inclusion | 67.73 | 67.73 | 44.68 | 56.21 | A - Node within 0.5 km | 0.23 | 10.77 | Node: TYW006 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2059
3 | 60 | 2060 | 0402117015 | Region IV-A (CALABARZON) | Cavite | Rosario | Muzon II | 14.4116 | 120.8476 | R | 2960 | 3.4 | 871 | 261 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 2.18 | Tier 2B: Moderate GIDA Inclusion | 63.44 | 63.44 | 48.98 | 56.21 | D - Other node or line within 3 km | 2.15 | 2.18 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2060
3 | 61 | 2061 | 0402117001 | Region IV-A (CALABARZON) | Cavite | Rosario | Silangan I | 14.4197 | 120.862 | U | 9634 | 3.4 | 2834 | 850 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 2.01 | Tier 2B: Moderate GIDA Inclusion | 62.32 | 62.32 | 50.1 | 56.21 | D - Other node or line within 3 km | 2.39 | 2.02 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2061
3 | 62 | 2062 | 1404408003 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Betwagan | 17.1478 | 121.0733 | R | 2009 | 3.7 | 543 | 163 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 60.88 | 60.88 | 51.53 | 56.21 | D - Other node or line within 3 km | 3.74 | 1.69 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2062
3 | 63 | 2063 | 0403404012 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pittland | 14.2366 | 121.3138 | U | 6634 | 3.3 | 2010 | 603 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.87 | 5.06 | Tier 2B: Moderate GIDA Inclusion | 57.22 | 57.22 | 55.2 | 56.21 | E - Nearest node or line 3-5 km | 4.87 | 5.04 | Node: VTL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2063
3 | 64 | 2064 | 1380611028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 814 | 13.8605 | 122.415 | U | 2528 | 3.71 | 682 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.03 | 6.25 | Tier 1B: High GIDA Priority | 42.18 | 42.18 | 70.25 | 56.21 | F - Nearest node and line over 5 km | 6.03 | 6.25 | Node: GYQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2064
3 | 65 | 2065 | 1108204035 | Region XI (Davao Region) | Davao de Oro | Maco | Panangan | 7.4113 | 125.9486 | R | 724 | 3.7 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.88 | 10.36 | Tier 1B: High GIDA Priority | 38.29 | 38.29 | 74.12 | 56.21 | F - Nearest node and line over 5 km | 11.88 | 10.3 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2065
3 | 66 | 2066 | 0304904010 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Palasinan | 15.2536 | 120.8563 | R | 3900 | 3.5 | 1114 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 69.61 | 69.61 | 42.8 | 56.2 | C - Line within 0.5 km; node over 1 km | 1.51 | 0.39 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2066
3 | 67 | 2067 | 0405623027 | Region IV-A (CALABARZON) | Quezon | Lucban | Palola | 14.0917 | 121.5813 | R | 2283 | 3.8 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 0.02 | Tier 2B: Moderate GIDA Inclusion | 57.87 | 57.87 | 54.53 | 56.2 | C - Line within 0.5 km; node over 1 km | 3.5 | 0.02 | Line: LUCENA - LUCBAN AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2067
3 | 68 | 2068 | 0702216002 | Region VII (Central Visayas) | Cebu | Catmon | Amancion | 10.6375 | 123.9181 | R | 195 | 3.8 | 51 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.22 | 11.46 | Tier 1B: High GIDA Priority | 42.77 | 42.77 | 69.64 | 56.2 | F - Nearest node and line over 5 km | 12.22 | 11.46 | Line: BOGO - DANAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2068
3 | 69 | 2069 | 1003514031 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Tagoranao | 8.069 | 124.08 | R | 452 | 4.2 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.37 | 13.02 | Tier 1B: High GIDA Priority | 36.88 | 36.88 | 75.51 | 56.2 | F - Nearest node and line over 5 km | 22.37 | 12.95 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2069
3 | 70 | 2070 | 0702214012 | Region VII (Central Visayas) | Cebu | City of Carcar | Poblacion I | 10.106 | 123.6314 | U | 10763 | 3.8 | 2832 | 850 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 1.11 | Tier 2A: High Commercial ROI | 70.3 | 70.3 | 42.09 | 56.19 | D - Other node or line within 3 km | 1.11 | 1.02 | Line: 216F | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2070
3 | 71 | 2071 | 0401005035 | Region IV-A (CALABARZON) | Batangas | Batangas City | Kumintang Ilaya | 13.7744 | 121.0656 | U | 11223 | 3.6 | 3118 | 935 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 67.83 | 67.83 | 44.55 | 56.19 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.09 | Line: AE TO ELIMINATE COMMON 96C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2071
3 | 72 | 2072 | 1102319005 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Canocotan | 7.4068 | 125.7784 | U | 9916 | 3.7 | 2680 | 804 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.24 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 67.1 | 67.1 | 45.28 | 56.19 | C - Line within 0.5 km; node over 1 km | 2.24 | 0.09 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2072
3 | 73 | 2073 | 0304902028 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Tulay na Bato | 15.6239 | 121.1453 | R | 2497 | 3.5 | 713 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.14 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 66.41 | 66.41 | 45.96 | 56.19 | A - Node within 0.5 km | 0.14 | 0.14 | Node: BGN001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2073
3 | 74 | 2074 | 0306910025 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Sur | 15.6647 | 120.5807 | U | 4922 | 3.9 | 1262 | 379 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 63.9 | 63.9 | 48.48 | 56.19 | B - Node 0.5-1 km | 0.78 | 0.49 | Line: 20,642 mtrs. | Survey short node lateral; confirm port/fiber capacity, access and route. | 2074
3 | 75 | 2075 | 1381100134 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 134 | 14.4031 | 120.904 | U | 1867 | 3.56 | 524 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 2.83 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.3 | 41.3 | 71.09 | 56.19 | D - Other node or line within 3 km | 2.33 | 2.83 | Node: TRC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2075
3 | 76 | 2076 | 0102934007 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay V | 17.574 | 120.3791 | U | 706 | 3.8 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.48 | 1.5 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.53 | 40.53 | 71.85 | 56.19 | D - Other node or line within 3 km | 2.48 | 1.26 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2076
3 | 77 | 2077 | 0603001025 | Region VI (Western Visayas) | Iloilo | Ajuy | Punta Buri | 11.1376 | 123.1199 | R | 1338 | 3.8 | 352 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.25 | 11.47 | Tier 1B: High GIDA Priority | 39.85 | 39.85 | 72.53 | 56.19 | F - Nearest node and line over 5 km | 17.25 | 11.42 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2077
3 | 78 | 2078 | 0304926002 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Abar Ist | 15.7895 | 120.9811 | U | 23122 | 3.5 | 6606 | 1982 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.92 | 0.07 | Tier 2A: High Commercial ROI | 70.17 | 70.17 | 42.19 | 56.18 | B - Node 0.5-1 km | 0.92 | 0.07 | Line: Existing UG | Survey short node lateral; confirm port/fiber capacity, access and route. | 2078
3 | 79 | 2079 | 0401003044 | Region IV-A (CALABARZON) | Batangas | Balayan | Sampaga | 13.9563 | 120.7601 | R | 3215 | 3.6 | 893 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.44 | 1.2 | Tier 2B: Moderate GIDA Inclusion | 65.95 | 65.95 | 46.42 | 56.18 | D - Other node or line within 3 km | 3.44 | 1.2 | Line: TUY - STA. TERESITA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2079
3 | 80 | 2080 | 0102820020 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Rufino | 18.1617 | 120.6158 | R | 1162 | 3.7 | 314 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.55 | 2.61 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 47.85 | 47.85 | 64.5 | 56.18 | D - Other node or line within 3 km | 2.55 | 2.59 | Node: SNI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2080
3 | 81 | 2081 | 1381100146 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 146 | 14.6189 | 121.1764 | U | 992 | 3.77 | 263 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.79 | 40.79 | 71.58 | 56.18 | B - Node 0.5-1 km | 0.69 | 0.15 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2081
3 | 82 | 2082 | 0402120001 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya I | 14.3832 | 120.8337 | U | 14142 | 3.4 | 4159 | 1248 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.88 | 0.48 | Tier 2A: High Commercial ROI | 70.66 | 70.66 | 41.68 | 56.17 | C - Line within 0.5 km; node over 1 km | 1.88 | 0.45 | Line: TANZA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2082
3 | 83 | 2083 | 0301420037 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan II | 14.8399 | 121.0439 | U | 6248 | 3.5 | 1785 | 536 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 65.49 | 65.49 | 46.84 | 56.17 | B - Node 0.5-1 km | 0.78 | 4.26 | Node: SJD005 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 2083
3 | 84 | 2084 | 1705313004 | MIMAROPA Region | Palawan | Linapacan | Decabaitot | 11.6484 | 119.9636 | R | 877 | 3.9 | 225 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.27 | 104.41 | Tier 1B: High GIDA Priority | 36.83 | 36.83 | 75.51 | 56.17 | F - Nearest node and line over 5 km | 48.27 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2084
3 | 85 | 2085 | 0405619043 | Region IV-A (CALABARZON) | Quezon | Gumaca | San Isidro Silangan | 13.9106 | 122.1551 | R | 91 | 3.8 | 24 | 7 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.29 | 0.33 | Tier 1B: High GIDA Priority | 43.53 | 43.53 | 68.78 | 56.16 | C - Line within 0.5 km; node over 1 km | 5.29 | 0.33 | Line: GCQ001 TO TKQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2085
3 | 86 | 2086 | 1381100034 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 34 | 14.549 | 121.0513 | U | 1241 | 2.93 | 424 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.07 | 43.07 | 69.25 | 56.16 | D - Other node or line within 3 km | 1.74 | 0.53 | Line: RELIANCE PSG001 TO BÑL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2086
3 | 87 | 2087 | 1381100143 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 143 | 14.717 | 121.0441 | U | 817 | 3.15 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.4 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.99 | 40.99 | 71.33 | 56.16 | B - Node 0.5-1 km | 0.55 | 0.4 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 2087
3 | 88 | 2088 | 0806008010 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Osmeña | 11.724 | 125.1392 | R | 494 | 4.1 | 120 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.89 | 58.62 | Tier 1B: High GIDA Priority | 36.71 | 36.71 | 75.61 | 56.16 | F - Nearest node and line over 5 km | 55.89 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2088
3 | 89 | 2089 | 1705305019 | MIMAROPA Region | Palawan | Bataraza | Tagnato | 8.4094 | 117.2564 | R | 1118 | 3.9 | 287 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 219.59 | 221.88 | Tier 1B: High GIDA Priority | 33.76 | 33.76 | 78.55 | 56.16 | F - Nearest node and line over 5 km | 219.59 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2089
3 | 90 | 2090 | 0201505004 | Region II (Cagayan Valley) | Cagayan | Aparri | Bisagu | 18.348 | 121.6187 | R | 1830 | 3.9 | 469 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.06 | 8.33 | Tier 1B: High GIDA Priority | 52.78 | 52.78 | 59.51 | 56.15 | D - Other node or line within 3 km | 2.06 | 8.33 | Node: ARC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2090
3 | 91 | 2091 | 0205006014 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Lurad | 16.601 | 121.3601 | R | 674 | 3.8 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.59 | 2.44 | Tier 1B: High GIDA Priority | 45.45 | 45.45 | 66.85 | 56.15 | D - Other node or line within 3 km | 6.59 | 2.44 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2091
3 | 92 | 2092 | 1381100095 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 95 | 14.4254 | 121.0302 | U | 1151 | 3.46 | 333 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.04 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.23 | 43.23 | 69.07 | 56.15 | A - Node within 0.5 km | 0.39 | 0.04 | Line: UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2092
3 | 93 | 2093 | 1908820009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Aguak | Poblacion II | 14.6498 | 122.7708 | R | 2856 | 4.7 | 608 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.23 | 50.49 | Tier 1B: High GIDA Priority | 39.93 | 39.93 | 72.38 | 56.15 | F - Nearest node and line over 5 km | 41.23 | 999999 | Node: PEC002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2093
3 | 94 | 2094 | 1403209015 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Magaogao | 17.5974 | 121.4462 | R | 749 | 4.3 | 174 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.59 | 1.7 | Tier 1B: High GIDA Priority | 46.84 | 46.84 | 65.44 | 56.14 | D - Other node or line within 3 km | 3.59 | 1.53 | Line: Tabuk-Conner | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2094
3 | 95 | 2095 | 1381300015 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Blue Ridge A | 14.6683 | 121.052 | U | 1580 | 4.34 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.61 | 43.61 | 68.67 | 56.14 | B - Node 0.5-1 km | 0.58 | 0.21 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2095
3 | 96 | 2096 | 1380603011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 391 | 13.8127 | 122.651 | U | 2633 | 3.88 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.35 | 5.7 | Tier 1B: High GIDA Priority | 41.87 | 41.87 | 70.4 | 56.14 | F - Nearest node and line over 5 km | 6.35 | 5.7 | Line: CALAUAG TO RAGAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2096
3 | 97 | 2097 | 0600609018 | Region VI (Western Visayas) | Antique | Laua-An | Laua-an | 11.1172 | 122.0875 | R | 399 | 3.9 | 102 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.7 | 36.34 | Tier 1B: High GIDA Priority | 36.82 | 36.82 | 75.46 | 56.14 | F - Nearest node and line over 5 km | 42.7 | 35.99 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2097
3 | 98 | 2098 | 1102319001 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Apokon | 7.4341 | 125.8238 | U | 38621 | 3.7 | 10438 | 3131 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 3.03 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 65.51 | 65.51 | 46.74 | 56.13 | C - Line within 0.5 km; node over 1 km | 3.03 | 0.04 | Line: TAGUM - PANTUKAN SEGMENT 1 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2098
3 | 99 | 2099 | 0201529052 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Ugac Sur | 17.6128 | 121.7212 | U | 10202 | 3.9 | 2616 | 785 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.09 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 62.61 | 62.61 | 49.66 | 56.13 | C - Line within 0.5 km; node over 1 km | 5.09 | 0.04 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2099
3 | 100 | 2100 | 0601912006 | Region VI (Western Visayas) | Capiz | Pontevedra | Bantigue | 11.4491 | 122.8505 | R | 515 | 3.8 | 136 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 1.74 | Tier 1B: High GIDA Priority | 48.79 | 48.79 | 63.48 | 56.13 | D - Other node or line within 3 km | 3.67 | 1.74 | Line: ROXAS - SARA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2100
3 | 101 | 2101 | 1380611045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 830 | 14.3134 | 121.5147 | U | 5407 | 9.57 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.98 | 4.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.58 | 41.58 | 70.68 | 56.13 | D - Other node or line within 3 km | 2.98 | 3.98 | Node: KYL002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2101
3 | 102 | 2102 | 1108604023 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kinilidan | 6.446 | 125.4476 | R | 1329 | 3.6 | 369 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.51 | 11.94 | Tier 1B: High GIDA Priority | 40.73 | 40.73 | 71.54 | 56.13 | F - Nearest node and line over 5 km | 14.51 | 11.94 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2102
3 | 103 | 2103 | 1380601013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 13 | 14.0907 | 121.6653 | U | 2435 | 4.03 | 604 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.52 | 8.9 | Tier 1B: High GIDA Priority | 38.32 | 38.32 | 73.93 | 56.13 | F - Nearest node and line over 5 km | 8.52 | 8.9 | Node: SPQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2103
3 | 104 | 2104 | 1705313002 | MIMAROPA Region | Palawan | Linapacan | Cabunlawan | 11.3838 | 120.098 | R | 843 | 3.9 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59.68 | 89.68 | Tier 1B: High GIDA Priority | 36.53 | 36.53 | 75.73 | 56.13 | F - Nearest node and line over 5 km | 59.68 | 999999 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2104
3 | 105 | 2105 | 0405628008 | Region IV-A (CALABARZON) | Quezon | Mulanay | Barangay 2 | 13.5239 | 122.4061 | R | 3381 | 3.8 | 890 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 68.95 | 68.95 | 43.29 | 56.12 | D - Other node or line within 3 km | 1.25 | 0.67 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2105
3 | 106 | 2106 | 0301412024 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Ubihan | 14.7537 | 120.9222 | R | 2383 | 3.5 | 681 | 204 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 2.58 | Tier 2B: Moderate GIDA Inclusion | 57.49 | 57.49 | 54.74 | 56.12 | D - Other node or line within 3 km | 2.74 | 2.58 | Line: BOCAUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2106
3 | 107 | 2107 | 0401005074 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 5 | 13.7287 | 121.0531 | R | 586 | 3.6 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.76 | 3.11 | Tier 1B: High GIDA Priority | 42.19 | 42.19 | 70.05 | 56.12 | E - Nearest node or line 3-5 km | 3.76 | 3.11 | Line: AE TO ELIMINATE COMMON 96C | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2107
3 | 108 | 2108 | 1102407016 | Region XI (Davao Region) | Davao del Sur | Magsaysay | San Isidro | 6.7743 | 125.1246 | R | 4302 | 3.4 | 1265 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.81 | 21.3 | Tier 2B: Moderate GIDA Inclusion | 65.34 | 65.34 | 46.87 | 56.11 | E - Nearest node or line 3-5 km | 3.81 | 21.3 | Node: MYD001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2108
3 | 109 | 2109 | 1108605007 | Region XI (Davao Region) | Davao Occidental | Sarangani | Tinina | 5.3778 | 125.3964 | R | 1438 | 3.9 | 369 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.91 | 85.62 | Tier 1B: High GIDA Priority | 40.66 | 40.66 | 71.56 | 56.11 | F - Nearest node and line over 5 km | 81.91 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2109
3 | 110 | 2110 | 0600609025 | Region VI (Western Visayas) | Antique | Laua-An | Magyapo | 11.1274 | 122.0602 | R | 209 | 3.9 | 54 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.74 | 36.69 | Tier 1B: High GIDA Priority | 36.82 | 36.82 | 75.4 | 56.11 | F - Nearest node and line over 5 km | 42.74 | 36.32 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2110
3 | 111 | 2111 | 0603036019 | Region VI (Western Visayas) | Iloilo | Pavia | Ungka II | 10.7515 | 122.5392 | U | 5504 | 3.8 | 1448 | 434 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.62 | 2.79 | Tier 2B: Moderate GIDA Inclusion | 60.92 | 60.92 | 51.28 | 56.1 | D - Other node or line within 3 km | 2.62 | 2.78 | Node: PVI001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2111
3 | 112 | 2112 | 0501606017 | Region V (Bicol Region) | Camarines Norte | Labo | Cabatuhan | 14.1189 | 122.5375 | R | 1650 | 4 | 412 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.92 | 5.5 | Tier 1B: High GIDA Priority | 45.11 | 45.11 | 67.1 | 56.1 | F - Nearest node and line over 5 km | 10.92 | 5.5 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2112
3 | 113 | 2113 | 0806011012 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Maduroto Pob. | 12.1432 | 124.8769 | R | 1744 | 4.1 | 425 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 95.98 | 95.94 | Tier 1B: High GIDA Priority | 42.76 | 42.76 | 69.44 | 56.1 | F - Nearest node and line over 5 km | 95.98 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2113
3 | 114 | 2114 | 0600609015 | Region VI (Western Visayas) | Antique | Laua-An | Jinalinan | 11.1289 | 122.0703 | R | 193 | 3.9 | 49 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.25 | 37.1 | Tier 1B: High GIDA Priority | 36.81 | 36.81 | 75.39 | 56.1 | F - Nearest node and line over 5 km | 43.25 | 36.74 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2114
3 | 115 | 2115 | 0405808001 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Balite | 14.7325 | 121.1445 | U | 8169 | 3.6 | 2269 | 681 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 67.59 | 67.59 | 44.59 | 56.09 | A - Node within 0.5 km | 0.39 | 0.33 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2115
3 | 116 | 2116 | 1001309035 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Napalico | 7.4971 | 125.2497 | R | 1268 | 3.8 | 334 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 0.17 | Tier 1B: High GIDA Priority | 53.84 | 53.84 | 58.34 | 56.09 | C - Line within 0.5 km; node over 1 km | 2.09 | 0.08 | Line: MALAYBALAY - KITAOTAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2116
3 | 117 | 2117 | 1380604009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 276 | 13.4603 | 120.6299 | U | 3077 | 3.73 | 825 | 248 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.23 | 28.66 | Tier 1B: High GIDA Priority | 38.02 | 38.02 | 74.15 | 56.09 | F - Nearest node and line over 5 km | 30.23 | 28.17 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2117
3 | 118 | 2118 | 1108204029 | Region XI (Davao Region) | Davao de Oro | Maco | Sangab | 7.4442 | 125.9221 | R | 595 | 3.7 | 161 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.42 | 5.91 | Tier 1B: High GIDA Priority | 37.78 | 37.78 | 74.41 | 56.09 | F - Nearest node and line over 5 km | 11.42 | 5.87 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2118
3 | 119 | 2119 | 0600609040 | Region VI (Western Visayas) | Antique | Laua-An | Tibacan | 11.1409 | 122.0713 | R | 169 | 3.9 | 43 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.54 | 38.41 | Tier 1B: High GIDA Priority | 36.79 | 36.79 | 75.39 | 56.09 | F - Nearest node and line over 5 km | 44.54 | 38.05 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2119
3 | 120 | 2120 | 0105543023 | Region I (Ilocos Region) | Pangasinan | Tayug | Trenchera | 16.0246 | 120.7555 | R | 4345 | 3.6 | 1207 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.01 | 0.95 | Tier 2A: High Commercial ROI | 70.79 | 70.79 | 41.37 | 56.08 | D - Other node or line within 3 km | 1.01 | 0.95 | Line: BINALONAN - UMINGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2120
3 | 121 | 2121 | 1907009012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Tumbagaan | 17.2558 | 122.2298 | R | 1979 | 5.8 | 341 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 33.48 | 33.48 | 78.65 | 56.07 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2121
3 | 122 | 2122 | 1381300005 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Baesa | 14.6706 | 121.0095 | U | 56514 | 3.59 | 15731 | 4719 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.23 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 55.84 | 55.84 | 56.28 | 56.06 | A - Node within 0.5 km | 0.23 | 0.15 | Line: UG 144C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2122
3 | 123 | 2123 | 0301416014 | Region III (Central Luzon) | Bulacan | Paombong | Santa Cruz | 14.7609 | 120.7916 | R | 1449 | 3.5 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.04 | 10.4 | Tier 1B: High GIDA Priority | 47.2 | 47.2 | 64.9 | 56.05 | F - Nearest node and line over 5 km | 7.04 | 10.42 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2123
3 | 124 | 2124 | 1908702002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Aratuc | 17.2539 | 122.2279 | R | 2757 | 4.3 | 641 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 41.36 | 41.36 | 70.75 | 56.05 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2124
3 | 125 | 2125 | 0806022015 | Region VIII (Eastern Visayas) | Samar | Paranas | Lawaan I | 11.8655 | 125.0819 | R | 1499 | 4.1 | 366 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 70.14 | 73.05 | Tier 1B: High GIDA Priority | 36.92 | 36.92 | 75.16 | 56.04 | F - Nearest node and line over 5 km | 70.14 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2125
3 | 126 | 2126 | 1102412011 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone I | 6.8494 | 125.4189 | U | 9351 | 3.4 | 2750 | 825 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 43.37 | 56.03 | C - Line within 0.5 km; node over 1 km | 1.37 | 0.04 | Line: Digos to POI of existing aerial 96F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2126
3 | 127 | 2127 | 1381100129 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 129 | 14.6885 | 121.0748 | U | 1081 | 3.27 | 331 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 1.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.78 | 41.78 | 70.29 | 56.03 | D - Other node or line within 3 km | 1.08 | 1 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2127
3 | 128 | 2128 | 0803705004 | Region VIII (Eastern Visayas) | Leyte | Babatngon | Malibago | 11.4107 | 124.9241 | R | 870 | 3.8 | 229 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.85 | 23.92 | Tier 1B: High GIDA Priority | 40.41 | 40.41 | 71.64 | 56.03 | F - Nearest node and line over 5 km | 20.85 | 23.91 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2128
3 | 129 | 2129 | 0301421050 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Rita Matanda | 15.1336 | 120.9661 | R | 3118 | 3.5 | 891 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.17 | Tier 2A: High Commercial ROI | 70.86 | 70.86 | 41.18 | 56.02 | A - Node within 0.5 km | 0.28 | 0.17 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2129
3 | 130 | 2130 | 0702227004 | Region VII (Central Visayas) | Cebu | Liloan | Cotcot | 10.4333 | 123.9929 | U | 10837 | 3.8 | 2852 | 856 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.96 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 68.91 | 68.91 | 43.13 | 56.02 | D - Other node or line within 3 km | 2.91 | 1.12 | Line: DANAO - CEBU | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2130
3 | 131 | 2131 | 0405808011 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Rafael | 14.7325 | 121.1584 | U | 30559 | 3.6 | 8489 | 2547 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.39 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 68.44 | 68.44 | 43.6 | 56.02 | A - Node within 0.5 km | 0.39 | 0.56 | Node: ROD003 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2131
3 | 132 | 2132 | 0201505040 | Region II (Cagayan Valley) | Cagayan | Aparri | Toran | 18.3138 | 121.6562 | R | 3771 | 3.9 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.17 | 7.13 | Tier 2B: Moderate GIDA Inclusion | 61.54 | 61.54 | 50.49 | 56.02 | F - Nearest node and line over 5 km | 5.17 | 6.73 | Node: ARC001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2132
3 | 133 | 2133 | 0300810004 | Region III (Central Luzon) | Bataan | Orion | Balut | 14.6228 | 120.5789 | R | 1461 | 3.6 | 406 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 56.71 | 56.71 | 55.33 | 56.02 | B - Node 0.5-1 km | 0.82 | 0.23 | Line: ORION | Survey short node lateral; confirm port/fiber capacity, access and route. | 2133
3 | 134 | 2134 | 0403407019 | Region IV-A (CALABARZON) | Laguna | Cavinti | Tibatib | 14.2373 | 121.5381 | R | 218 | 3.3 | 66 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 9.69 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 45.61 | 45.61 | 66.44 | 56.02 | B - Node 0.5-1 km | 0.76 | 9.69 | Node: CVL002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 2134
3 | 135 | 2135 | 1380605075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 372 | 14.252 | 122.1512 | U | 4332 | 3.45 | 1257 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.09 | 26.42 | Tier 1B: High GIDA Priority | 41.82 | 41.82 | 70.22 | 56.02 | F - Nearest node and line over 5 km | 18.09 | 26.42 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2135
3 | 136 | 2136 | 0803740022 | Region VIII (Eastern Visayas) | Leyte | Palompon | Mazawalo Pob. | 11.0458 | 124.389 | R | 4628 | 3.8 | 1218 | 365 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.24 | Tier 2A: High Commercial ROI | 74.45 | 74.45 | 37.58 | 56.01 | B - Node 0.5-1 km | 0.73 | 0.2 | Line: ORMOC - PALOMPON | Survey short node lateral; confirm port/fiber capacity, access and route. | 2136
3 | 137 | 2137 | 0300801008 | Region III (Central Luzon) | Bataan | Abucay | Omboy | 14.7186 | 120.5386 | R | 3538 | 3.6 | 983 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.76 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 66.23 | 66.23 | 45.79 | 56.01 | C - Line within 0.5 km; node over 1 km | 3.76 | 0.24 | Line: 60 CORE 5X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2137
3 | 138 | 2138 | 0402117013 | Region IV-A (CALABARZON) | Cavite | Rosario | Bagbag II | 14.4207 | 120.8673 | U | 6477 | 3.4 | 1905 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.96 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 63.61 | 63.61 | 48.41 | 56.01 | D - Other node or line within 3 km | 1.96 | 1.53 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2138
3 | 139 | 2139 | 1408106024 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Doña Loreta | 18.1791 | 121.357 | R | 758 | 4.2 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.99 | 0.28 | Tier 1B: High GIDA Priority | 49.76 | 49.76 | 62.26 | 56.01 | F - Nearest node and line over 5 km | 5.99 | 19.05 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2139
3 | 140 | 2140 | 1402710008 | Cordillera Administrative Region (CAR) | Ifugao | Tinoc | Luhong | 16.6537 | 120.9581 | R | 1486 | 3.9 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.15 | 16.71 | Tier 1B: High GIDA Priority | 45.48 | 45.48 | 66.54 | 56.01 | F - Nearest node and line over 5 km | 13.15 | 16.71 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2140
3 | 141 | 2141 | 1380602010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 296 | 13.3736 | 121.2211 | U | 2273 | 3.1 | 733 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.22 | 5.7 | Tier 1B: High GIDA Priority | 43.41 | 43.41 | 68.62 | 56.01 | F - Nearest node and line over 5 km | 6.22 | 5.7 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2141
3 | 142 | 2142 | 0806002052 | Region VIII (Eastern Visayas) | Samar | Basey | Bulao | 11.3383 | 125.1028 | R | 1345 | 4.1 | 328 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.5 | 17.2 | Tier 1B: High GIDA Priority | 40.05 | 40.05 | 71.97 | 56.01 | F - Nearest node and line over 5 km | 15.5 | 17.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2142
3 | 143 | 2143 | 1380614101 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 818-A | 13.7319 | 122.1816 | U | 1659 | 4.01 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.47 | 0.3 | Tier 1B: High GIDA Priority | 39.57 | 39.57 | 72.45 | 56.01 | C - Line within 0.5 km; node over 1 km | 4.47 | 0.3 | Line: LZQ001 TO MCQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2143
3 | 144 | 2144 | 1003506030 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Rebucon | 7.8023 | 123.7458 | R | 1592 | 4.2 | 379 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.25 | 9.36 | Tier 1B: High GIDA Priority | 37.76 | 37.76 | 74.27 | 56.01 | F - Nearest node and line over 5 km | 24.25 | 9.36 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2144
3 | 145 | 2145 | 0301420019 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Assumption | 14.8056 | 121.0705 | R | 4559 | 3.5 | 1303 | 391 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 1.39 | Tier 2A: High Commercial ROI | 71.38 | 71.38 | 40.63 | 56 | B - Node 0.5-1 km | 0.86 | 1.33 | Node: SJD004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2145
3 | 146 | 2146 | 0403417035 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Poblacion III | 14.1158 | 121.427 | R | 2572 | 3.3 | 779 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.48 | 1.07 | Tier 2B: Moderate GIDA Inclusion | 64.02 | 64.02 | 47.99 | 56 | D - Other node or line within 3 km | 2.48 | 1.02 | Line: SPO001 TO LBQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2146
3 | 147 | 2147 | 0102820018 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Paulo | 18.1634 | 120.5809 | R | 959 | 3.7 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.53 | 0.89 | Tier 1B: High GIDA Priority | 51.47 | 51.47 | 60.54 | 56 | D - Other node or line within 3 km | 1.53 | 0.87 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2147
3 | 148 | 2148 | 0502002025 | Region V (Bicol Region) | Catanduanes | Baras | San Lorenzo | 13.6596 | 124.3696 | R | 157 | 4.2 | 37 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.15 | 76.65 | Tier 1B: High GIDA Priority | 36.71 | 36.71 | 75.29 | 56 | F - Nearest node and line over 5 km | 56.15 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2148
3 | 149 | 2149 | 1381600006 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Bisig | 14.7037 | 120.9817 | U | 1448 | 3.14 | 461 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 0.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 46.48 | 46.48 | 65.51 | 55.99 | A - Node within 0.5 km | 0.43 | 0.31 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2149
3 | 150 | 2150 | 1108602001 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Buguis | 5.9761 | 125.6857 | R | 1415 | 3.6 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.31 | 55.34 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 75.18 | 55.99 | F - Nearest node and line over 5 km | 47.31 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2150
3 | 151 | 2151 | 0604517010 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Nato | 10.314 | 122.9914 | R | 4431 | 3.7 | 1198 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.23 | 3.09 | Tier 2B: Moderate GIDA Inclusion | 67.02 | 67.02 | 44.93 | 55.98 | E - Nearest node or line 3-5 km | 3.23 | 13.8 | Node: LCL001-TYPE 2 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2151
3 | 152 | 2152 | 0103301028 | Region I (Ilocos Region) | La Union | Agoo | San Marcos | 16.3746 | 120.348 | R | 2198 | 3.7 | 594 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.09 | 0.8 | Tier 2B: Moderate GIDA Inclusion | 55.88 | 55.88 | 56.08 | 55.98 | D - Other node or line within 3 km | 6.09 | 0.76 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2152
3 | 153 | 2153 | 0405607024 | Region IV-A (CALABARZON) | Quezon | Calauag | Dominlog | 13.9708 | 122.2317 | R | 466 | 3.8 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.16 | 6 | Tier 1B: High GIDA Priority | 39.59 | 39.59 | 72.38 | 55.98 | F - Nearest node and line over 5 km | 6.16 | 5.95 | Line: WP CLQ001 TO MLQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2153
3 | 154 | 2154 | 1380601085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 85 | 11.9262 | 122.8414 | U | 4051 | 4.79 | 845 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38 | 17.31 | Tier 1B: High GIDA Priority | 38.54 | 38.54 | 73.42 | 55.98 | F - Nearest node and line over 5 km | 38.85 | 999999 | Node: RCZ001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2154
3 | 155 | 2155 | 0201503025 | Region II (Cagayan Valley) | Cagayan | Allacapan | Tamboli | 18.2647 | 121.5756 | R | 843 | 3.9 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.8 | 2.34 | Tier 1B: High GIDA Priority | 43.8 | 43.8 | 68.13 | 55.97 | D - Other node or line within 3 km | 3.8 | 2.33 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2155
3 | 156 | 2156 | 1381100138 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 138 | 14.6637 | 121.1306 | U | 1110 | 3.37 | 329 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 0.46 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.81 | 40.81 | 71.13 | 55.97 | C - Line within 0.5 km; node over 1 km | 1.63 | 0.46 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2156
3 | 157 | 2157 | 0205010003 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Ansipsip | 16.3419 | 120.8209 | R | 129 | 3.8 | 34 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.62 | 6.44 | Tier 1B: High GIDA Priority | 39.29 | 39.29 | 72.66 | 55.97 | F - Nearest node and line over 5 km | 7.62 | 6.23 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2157
3 | 158 | 2158 | 1705303004 | MIMAROPA Region | Palawan | Araceli | Dagman | 10.5255 | 119.9617 | R | 937 | 3.9 | 240 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.06 | 54.87 | Tier 1B: High GIDA Priority | 37.19 | 37.19 | 74.75 | 55.97 | F - Nearest node and line over 5 km | 46.06 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2158
3 | 159 | 2159 | 0300806015 | Region III (Central Luzon) | Bataan | Limay | St. Francis II | 14.5719 | 120.5924 | U | 13425 | 3.6 | 3729 | 1119 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.39 | 0.12 | Tier 2A: High Commercial ROI | 72.21 | 72.21 | 39.69 | 55.95 | A - Node within 0.5 km | 0.39 | 0.11 | Line: 36 CORE 3X12 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2159
3 | 160 | 2160 | 0306910004 | Region III (Central Luzon) | Tarlac | Paniqui | Apulid | 15.6832 | 120.5816 | R | 4025 | 3.9 | 1032 | 310 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 68.92 | 68.92 | 42.99 | 55.95 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.2 | Line: PANIQUI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2160
3 | 161 | 2161 | 1108605011 | Region XI (Davao Region) | Davao Occidental | Sarangani | Tagen | 5.3799 | 125.3516 | R | 1396 | 3.9 | 358 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.34 | 84.18 | Tier 1B: High GIDA Priority | 40.34 | 40.34 | 71.56 | 55.95 | F - Nearest node and line over 5 km | 80.34 | 999999 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2161
3 | 162 | 2162 | 0803748046 | Region VIII (Eastern Visayas) | Leyte | Tanauan | San Roque | 11.111 | 125.0213 | R | 3634 | 3.8 | 956 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.65 | 0.18 | Tier 2A: High Commercial ROI | 71.25 | 71.25 | 40.64 | 55.94 | B - Node 0.5-1 km | 0.65 | 6.19 | Node: TAL001-TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2162
3 | 163 | 2163 | 1380601265 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 264 | 13.8931 | 122.5019 | U | 2758 | 3.86 | 714 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.73 | 8.12 | Tier 1B: High GIDA Priority | 43.11 | 43.11 | 68.77 | 55.94 | F - Nearest node and line over 5 km | 5.73 | 8.1 | Node: GYQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2163
3 | 164 | 2164 | 1381300059 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Mangga | 14.6987 | 121.0288 | U | 916 | 3.38 | 271 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 0.45 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.29 | 41.29 | 70.58 | 55.94 | B - Node 0.5-1 km | 0.52 | 0.45 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2164
3 | 165 | 2165 | 1704006011 | MIMAROPA Region | Marinduque | Torrijos | Makawayan | 13.2619 | 122.0456 | R | 1084 | 3.8 | 285 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.52 | 45.92 | Tier 1B: High GIDA Priority | 33.85 | 33.85 | 78.04 | 55.94 | F - Nearest node and line over 5 km | 46.52 | 45.8 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2165
3 | 166 | 2166 | 0403404004 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Butong | 14.2222 | 121.2941 | U | 16184 | 3.3 | 4904 | 1471 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.82 | 4.83 | Tier 2B: Moderate GIDA Inclusion | 63.57 | 63.57 | 48.29 | 55.93 | E - Nearest node or line 3-5 km | 4.82 | 4.83 | Node: BAY001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2166
3 | 167 | 2167 | 1004302014 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Kibanban | 8.7375 | 124.8149 | R | 2475 | 3.9 | 635 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.98 | 2.86 | Tier 2B: Moderate GIDA Inclusion | 55.36 | 55.36 | 56.51 | 55.93 | D - Other node or line within 3 km | 3.98 | 2.83 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2167
3 | 168 | 2168 | 1408104002 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Baliwanan | 18.13 | 121.1397 | R | 475 | 4.2 | 113 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.04 | 18.78 | Tier 1B: High GIDA Priority | 34.6 | 34.6 | 77.25 | 55.93 | F - Nearest node and line over 5 km | 13.04 | 37.54 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2168
3 | 169 | 2169 | 0304930055 | Region III (Central Luzon) | Nueva Ecija | Talavera | Tabacao | 15.5838 | 120.9188 | R | 4856 | 3.5 | 1387 | 416 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.1 | Tier 2A: High Commercial ROI | 72.97 | 72.97 | 38.88 | 55.92 | A - Node within 0.5 km | 0.21 | 0.1 | Line: Existing UG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2169
3 | 170 | 2170 | 1380601048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 48 | 11.4697 | 121.6475 | U | 4191 | 3.56 | 1178 | 353 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.35 | 60.15 | Tier 1B: High GIDA Priority | 41.58 | 41.58 | 70.26 | 55.92 | F - Nearest node and line over 5 km | 62.35 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2170
3 | 171 | 2171 | 1380601189 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 189 | 13.6543 | 122.2327 | U | 1618 | 4.12 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 1.39 | Tier 1B: High GIDA Priority | 39.89 | 39.89 | 71.95 | 55.92 | D - Other node or line within 3 km | 3.55 | 1.38 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2171
3 | 172 | 2172 | 0806403039 | Region VIII (Eastern Visayas) | Southern Leyte | Hinunangan | Upper Bantawon | 10.3894 | 125.202 | R | 146 | 4.1 | 36 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.03 | 21.61 | Tier 1B: High GIDA Priority | 33.58 | 33.58 | 78.27 | 55.92 | F - Nearest node and line over 5 km | 49.77 | 999999 | Node: MSL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2172
3 | 173 | 2173 | 0604503001 | Region VI (Western Visayas) | Negros Occidental | Binalbagan | Amontay | 10.1286 | 123.0796 | R | 3162 | 3.7 | 855 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.89 | 15.51 | Tier 1B: High GIDA Priority | 49.89 | 49.89 | 61.94 | 55.91 | F - Nearest node and line over 5 km | 20.89 | 20.34 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2173
3 | 174 | 2174 | 1381100125 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 125 | 14.3888 | 120.9616 | U | 1554 | 3.33 | 467 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.61 | 6.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.76 | 42.76 | 69.06 | 55.91 | B - Node 0.5-1 km | 0.61 | 6.35 | Node: IMC004 -TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2174
3 | 175 | 2175 | 1906612026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Luuk Tara | 16.363 | 122.1216 | R | 914 | 6 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.17 | 1.98 | Tier 1B: High GIDA Priority | 40.3 | 40.3 | 71.53 | 55.91 | F - Nearest node and line over 5 km | 9.17 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2175
3 | 176 | 2176 | 0300812011 | Region III (Central Luzon) | Bataan | Samal | Sapa | 14.7539 | 120.541 | R | 4845 | 3.6 | 1346 | 404 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.38 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 70.57 | 70.57 | 41.23 | 55.9 | C - Line within 0.5 km; node over 1 km | 5.38 | 0.2 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2176
3 | 177 | 2177 | 0102916007 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Bulala-Leguey | 17.1302 | 120.5755 | R | 301 | 3.8 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.56 | 8.2 | Tier 1B: High GIDA Priority | 45.3 | 45.3 | 66.5 | 55.9 | E - Nearest node or line 3-5 km | 4.56 | 8.06 | Node: SDI001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2177
3 | 178 | 2178 | 1903631017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Marogong East | 15.6438 | 122.5553 | R | 2587 | 5.7 | 454 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 83.32 | 82.15 | Tier 1B: High GIDA Priority | 40.25 | 40.25 | 71.55 | 55.9 | F - Nearest node and line over 5 km | 83.32 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2178
3 | 179 | 2179 | 0501602018 | Region V (Bicol Region) | Camarines Norte | Capalonga | San Roque | 14.3292 | 122.5521 | R | 1011 | 4 | 253 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.19 | 16.18 | Tier 1B: High GIDA Priority | 41.29 | 41.29 | 70.5 | 55.89 | F - Nearest node and line over 5 km | 11.19 | 16.18 | Node: CCA001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2179
3 | 180 | 2180 | 1380606127 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 521 | 13.8719 | 121.1256 | U | 1582 | 3.08 | 513 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.37 | 2.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.98 | 40.98 | 70.79 | 55.89 | D - Other node or line within 3 km | 2.37 | 2.18 | Line: UG SSB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2180
3 | 181 | 2181 | 0403429007 | Region IV-A (CALABARZON) | Laguna | Siniloan | Halayhayin | 14.4237 | 121.4483 | U | 5313 | 3.3 | 1610 | 483 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 1.23 | Tier 2B: Moderate GIDA Inclusion | 63.73 | 63.73 | 48.02 | 55.88 | D - Other node or line within 3 km | 1.33 | 1.22 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2181
3 | 182 | 2182 | 0301420041 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan Proper | 14.8447 | 121.0801 | U | 48261 | 3.5 | 13789 | 4137 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.37 | 4.34 | Tier 2B: Moderate GIDA Inclusion | 58.56 | 58.56 | 53.21 | 55.88 | A - Node within 0.5 km | 0.37 | 5.66 | Node: SJD002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2182
3 | 183 | 2183 | 1380800004 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Cupang | 14.9528 | 120.0891 | U | 57482 | 4.01 | 14334 | 4300 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.32 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 57.37 | 57.37 | 54.39 | 55.88 | A - Node within 0.5 km | 0.32 | 0.15 | Line: BACKBONE ROUTE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2183
3 | 184 | 2184 | 0500501055 | Region V (Bicol Region) | Albay | Bacacay | Tanagan | 13.3132 | 123.8642 | R | 1153 | 4.1 | 281 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.2 | 11.55 | Tier 1B: High GIDA Priority | 43.84 | 43.84 | 67.92 | 55.88 | F - Nearest node and line over 5 km | 9.2 | 11.55 | Node: BYY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2184
3 | 185 | 2185 | 1908702001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Ampuan | 17.2541 | 122.2281 | R | 2691 | 4.3 | 626 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.19 | Tier 1B: High GIDA Priority | 41.01 | 41.01 | 70.75 | 55.88 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2185
3 | 186 | 2186 | 0806411014 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Nueva Estrella Sur | 9.9519 | 125.2294 | R | 420 | 4.1 | 102 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.31 | 24.52 | Tier 1B: High GIDA Priority | 37.07 | 37.07 | 74.68 | 55.88 | F - Nearest node and line over 5 km | 34.31 | 33.76 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2186
3 | 187 | 2187 | 0304902008 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Curva | 15.6187 | 121.1489 | R | 4163 | 3.5 | 1189 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.65 | 0.23 | Tier 2A: High Commercial ROI | 71.44 | 71.44 | 40.3 | 55.87 | B - Node 0.5-1 km | 0.65 | 0.15 | Line: Proposed AE F1-6 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2187
3 | 188 | 2188 | 0403429013 | Region IV-A (CALABARZON) | Laguna | Siniloan | Pandeno | 14.4178 | 121.4434 | R | 3808 | 3.3 | 1154 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 2.05 | Tier 2B: Moderate GIDA Inclusion | 65.08 | 65.08 | 46.67 | 55.87 | D - Other node or line within 3 km | 2.09 | 2.05 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2188
3 | 189 | 2189 | 1380614090 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 897 | 13.9687 | 121.3674 | U | 2184 | 3.59 | 609 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.16 | 2.6 | Tier 1B: High GIDA Priority | 42.5 | 42.5 | 69.23 | 55.87 | D - Other node or line within 3 km | 3.16 | 2.6 | Line: STO. TOMAS - CANDELARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2189
3 | 190 | 2190 | 0806010022 | Region VIII (Eastern Visayas) | Samar | Marabut | Roño | 11.155 | 125.2076 | R | 526 | 4.1 | 128 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.2 | 21 | Tier 1B: High GIDA Priority | 38.67 | 38.67 | 73.08 | 55.87 | F - Nearest node and line over 5 km | 21.2 | 22.46 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2190
3 | 191 | 2191 | 0806411023 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Pociano D. Equipilag | 9.9407 | 125.2499 | R | 400 | 4.1 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.75 | 27.07 | Tier 1B: High GIDA Priority | 37.22 | 37.22 | 74.53 | 55.87 | F - Nearest node and line over 5 km | 31.75 | 31.21 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2191
3 | 192 | 2192 | 0201529045 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Libag Sur | 17.5975 | 121.7074 | R | 3001 | 3.9 | 769 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.11 | 1.8 | Tier 2B: Moderate GIDA Inclusion | 61.93 | 61.93 | 49.78 | 55.86 | D - Other node or line within 3 km | 4.11 | 1.8 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2192
3 | 193 | 2193 | 1380610048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 733 | 12.9423 | 123.2452 | U | 4317 | 3.91 | 1104 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.13 | 44.81 | Tier 1B: High GIDA Priority | 42.65 | 42.65 | 69.08 | 55.86 | F - Nearest node and line over 5 km | 14.13 | 44.78 | Node: LOA004-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2193
3 | 194 | 2194 | 1705209034 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Wawa | 13.0417 | 121.4928 | R | 4823 | 3.9 | 1237 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 1.46 | Tier 2A: High Commercial ROI | 70.88 | 70.88 | 40.82 | 55.85 | D - Other node or line within 3 km | 1.77 | 1.39 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2194
3 | 195 | 2195 | 0300804008 | Region III (Central Luzon) | Bataan | Dinalupihan | Daang Bago | 14.857 | 120.4794 | R | 3392 | 3.6 | 942 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 69.35 | 69.35 | 42.35 | 55.85 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.11 | Line: Pipe Dinalupian to Orion | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2195
3 | 196 | 2196 | 0201529031 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Pengue | 17.6042 | 121.7513 | U | 6832 | 3.9 | 1752 | 526 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.25 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 59.88 | 59.88 | 51.82 | 55.85 | C - Line within 0.5 km; node over 1 km | 5.25 | 0.26 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2196
3 | 197 | 2197 | 0806411009 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Dan-an | 9.9885 | 125.2097 | R | 494 | 4.1 | 120 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.72 | 21.08 | Tier 1B: High GIDA Priority | 36.97 | 36.97 | 74.72 | 55.85 | F - Nearest node and line over 5 km | 38.37 | 37.92 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2197
3 | 198 | 2198 | 0403414007 | Region IV-A (CALABARZON) | Laguna | Mabitac | Paagahan | 14.4423 | 121.4004 | R | 4432 | 3.3 | 1343 | 403 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.14 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 72.27 | 72.27 | 39.41 | 55.84 | C - Line within 0.5 km; node over 1 km | 3.14 | 0.1 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2198
3 | 199 | 2199 | 0405814003 | Region IV-A (CALABARZON) | Rizal | Teresa | Dalig | 14.5845 | 121.2298 | U | 15028 | 3.6 | 4174 | 1252 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.87 | 3.36 | Tier 2B: Moderate GIDA Inclusion | 64.72 | 64.72 | 46.96 | 55.84 | E - Nearest node or line 3-5 km | 3.87 | 3.21 | Line: Aerial 24C | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2199
3 | 200 | 2200 | 0405813005 | Region IV-A (CALABARZON) | Rizal | Taytay | Santa Ana | 14.5372 | 121.1093 | U | 102828 | 3.6 | 28563 | 8569 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.68 | 0.58 | Tier 1B: High GIDA Priority | 52.27 | 52.27 | 59.41 | 55.84 | B - Node 0.5-1 km | 0.68 | 0.57 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2200
3 | 201 | 2201 | 1380610011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 696 | 13.3001 | 120.5892 | U | 4121 | 3.93 | 1049 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.01 | 39.46 | Tier 1B: High GIDA Priority | 41.2 | 41.2 | 70.47 | 55.84 | F - Nearest node and line over 5 km | 41.01 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2201
3 | 202 | 2202 | 1102503002 | Region XI (Davao Region) | Davao Oriental | Boston | Caatihan | 7.8946 | 126.2873 | R | 1654 | 3.6 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.53 | 22.85 | Tier 1B: High GIDA Priority | 39.36 | 39.36 | 72.29 | 55.83 | F - Nearest node and line over 5 km | 26.53 | 22.83 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2202
3 | 203 | 2203 | 0803738016 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Cogon Combado | 11.0208 | 124.6052 | U | 6006 | 3.8 | 1581 | 474 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 67.83 | 67.83 | 43.82 | 55.82 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.27 | Line: ORMOC CLS - CAPOOCAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2203
3 | 204 | 2204 | 0405814005 | Region IV-A (CALABARZON) | Rizal | Teresa | May-Iba | 14.5633 | 121.2067 | U | 5907 | 3.6 | 1641 | 492 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.53 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 63.47 | 63.47 | 48.17 | 55.82 | C - Line within 0.5 km; node over 1 km | 1.53 | 0.11 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2204
3 | 205 | 2205 | 0604515025 | Region VI (Western Visayas) | Negros Occidental | City of Kabankalan | Barangay 4 | 9.9883 | 122.8158 | R | 1475 | 3.7 | 399 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 59.23 | 59.23 | 52.41 | 55.82 | A - Node within 0.5 km | 0.42 | 0.26 | Line: FOC 144C FACING TO BACONG CLS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2205
3 | 206 | 2206 | 1380607011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 647 | 12.6122 | 120.5363 | U | 3019 | 2.97 | 1018 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.3 | 62.69 | Tier 1B: High GIDA Priority | 41.11 | 41.11 | 70.53 | 55.82 | F - Nearest node and line over 5 km | 64.3 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2206
3 | 207 | 2207 | 0102901005 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Apaya | 16.8814 | 120.5826 | R | 609 | 3.8 | 160 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.13 | 12.99 | Tier 1B: High GIDA Priority | 39.95 | 39.95 | 71.69 | 55.82 | F - Nearest node and line over 5 km | 12.13 | 12.86 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2207
3 | 208 | 2208 | 1381100099 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 99 | 14.5399 | 121.0025 | U | 1067 | 3.33 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.01 | 0.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.64 | 41.64 | 69.98 | 55.81 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.21 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2208
3 | 209 | 2209 | 1704005026 | MIMAROPA Region | Marinduque | Santa Cruz | Kinyaman | 13.4758 | 122.0429 | R | 380 | 3.8 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.94 | 26.67 | Tier 1B: High GIDA Priority | 30.95 | 30.95 | 80.66 | 55.81 | F - Nearest node and line over 5 km | 27.94 | 26.67 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2209
3 | 210 | 2210 | 0403426008 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Labuin | 14.2685 | 121.4136 | R | 5029 | 3.3 | 1524 | 457 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.14 | Tier 2A: High Commercial ROI | 71.23 | 71.23 | 40.37 | 55.8 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.11 | Line: CLB001 TO SCL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2210
3 | 211 | 2211 | 1003514020 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Old Poblacion | 8.0202 | 124.0658 | R | 4145 | 4.2 | 987 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.98 | 18.32 | Tier 2B: Moderate GIDA Inclusion | 57.22 | 57.22 | 54.39 | 55.8 | F - Nearest node and line over 5 km | 22.98 | 18.28 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2211
3 | 212 | 2212 | 1004325006 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Mahayag | 8.9774 | 124.9042 | R | 403 | 3.9 | 103 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.51 | 0.6 | Tier 1B: High GIDA Priority | 51.95 | 51.95 | 59.65 | 55.8 | C - Line within 0.5 km; node over 1 km | 3.51 | 0.46 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2212
3 | 213 | 2213 | 1908708008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Montay | 17.2675 | 122.2332 | R | 4773 | 4.3 | 1110 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.67 | 35.16 | Tier 1B: High GIDA Priority | 49.51 | 49.51 | 62.09 | 55.8 | F - Nearest node and line over 5 km | 30.67 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2213
3 | 214 | 2214 | 1908803001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Abdullah Sangki | Banaba | 17.2552 | 122.2292 | R | 4337 | 4.7 | 923 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 34.34 | Tier 1B: High GIDA Priority | 48.75 | 48.75 | 62.84 | 55.8 | F - Nearest node and line over 5 km | 29.46 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2214
3 | 215 | 2215 | 0305422002 | Region III (Central Luzon) | Pampanga | Sasmuan | Batang 2nd | 14.8188 | 120.6193 | R | 1297 | 4 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.11 | 9.12 | Tier 1B: High GIDA Priority | 47.18 | 47.18 | 64.42 | 55.8 | F - Nearest node and line over 5 km | 9.11 | 9.08 | Line: 96CORE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2215
3 | 216 | 2216 | 0301418003 | Region III (Central Luzon) | Bulacan | Pulilan | Cutcot | 14.9118 | 120.8444 | U | 8697 | 3.5 | 2485 | 746 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 66.73 | 66.73 | 44.85 | 55.79 | D - Other node or line within 3 km | 1.25 | 1.05 | Line: CALUMPIT - BALIUAG LINK | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2216
3 | 217 | 2217 | 0603036001 | Region VI (Western Visayas) | Iloilo | Pavia | Aganan | 10.7675 | 122.5373 | U | 5042 | 3.8 | 1327 | 398 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 3.53 | Tier 2B: Moderate GIDA Inclusion | 63.14 | 63.14 | 48.45 | 55.79 | D - Other node or line within 3 km | 1.03 | 3.53 | Node: PVI001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2217
3 | 218 | 2218 | 1381100114 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 114 | 14.6774 | 120.9659 | U | 1078 | 3.21 | 336 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.45 | 42.45 | 69.12 | 55.79 | B - Node 0.5-1 km | 0.82 | 0.96 | Node: MAL005 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2218
3 | 219 | 2219 | 1381300123 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Teachers Village West | 14.603 | 121.0983 | U | 3289 | 4.09 | 804 | 241 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 54.7 | 54.7 | 56.86 | 55.78 | B - Node 0.5-1 km | 0.8 | 0.65 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2219
3 | 220 | 2220 | 0201503007 | Region II (Cagayan Valley) | Cagayan | Allacapan | Capanickian Norte | 18.2144 | 121.5035 | R | 1222 | 3.9 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.95 | 5.49 | Tier 1B: High GIDA Priority | 44.89 | 44.89 | 66.68 | 55.78 | F - Nearest node and line over 5 km | 5.95 | 5.48 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2220
3 | 221 | 2221 | 1208005019 | Region XII (SOCCSKSARGEN) | Sarangani | Maitum | Zion | 6.0855 | 124.5286 | R | 1705 | 3.9 | 437 | 131 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.89 | 52.99 | Tier 1B: High GIDA Priority | 37.81 | 37.81 | 73.75 | 55.78 | F - Nearest node and line over 5 km | 53.89 | 999999 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2221
3 | 222 | 2222 | 0103314015 | Region I (Ilocos Region) | La Union | City of San Fernando | Cabaroan | 16.5923 | 120.3381 | R | 3672 | 3.7 | 992 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.51 | 1.93 | Tier 2B: Moderate GIDA Inclusion | 67.73 | 67.73 | 43.82 | 55.77 | D - Other node or line within 3 km | 2.51 | 1.93 | Line: AGOO - SAN FERNANDO AERIAL_SEGMENT 0 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2222
3 | 223 | 2223 | 0405619059 | Region IV-A (CALABARZON) | Quezon | Gumaca | Villa Nava | 13.917 | 122.1 | R | 3091 | 3.8 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 67.21 | 67.21 | 44.33 | 55.77 | C - Line within 0.5 km; node over 1 km | 1.06 | 0.42 | Line: UG GCQ001 TO LZQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2223
3 | 224 | 2224 | 0500517026 | Region V (Bicol Region) | Albay | City of Tabaco | Oson | 13.3205 | 123.6835 | R | 1266 | 4.1 | 309 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 3.08 | Tier 1B: High GIDA Priority | 49.2 | 49.2 | 62.35 | 55.77 | E - Nearest node or line 3-5 km | 3.25 | 3.08 | Line: TABACO - LIGAO AERIAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2224
3 | 225 | 2225 | 0806017004 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Bagolibas | 11.3943 | 125.0012 | R | 705 | 4.1 | 172 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.2 | 20.24 | Tier 1B: High GIDA Priority | 35.84 | 35.84 | 75.7 | 55.77 | F - Nearest node and line over 5 km | 17.2 | 20.23 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2225
3 | 226 | 2226 | 0405802007 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Isidro | 14.6182 | 121.1857 | U | 62732 | 3.6 | 17426 | 5228 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.15 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 57.35 | 57.35 | 54.16 | 55.76 | A - Node within 0.5 km | 0.15 | 0.15 | Node: ANR005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2226
3 | 227 | 2227 | 0907311027 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Suminalum | 7.8343 | 123.1256 | R | 1109 | 3.9 | 284 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.98 | 5.89 | Tier 1B: High GIDA Priority | 42.43 | 42.43 | 69.08 | 55.76 | F - Nearest node and line over 5 km | 13.98 | 5.88 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2227
3 | 228 | 2228 | 1906612025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Latung | 17.2555 | 122.2295 | R | 3526 | 6 | 588 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 39.94 | 39.94 | 71.58 | 55.76 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2228
3 | 229 | 2229 | 0405809007 | Region IV-A (CALABARZON) | Rizal | Morong | San Juan | 14.5142 | 121.247 | U | 10706 | 3.6 | 2974 | 892 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.91 | Tier 2B: Moderate GIDA Inclusion | 68.25 | 68.25 | 43.25 | 55.75 | D - Other node or line within 3 km | 1.15 | 0.83 | Line: TAYTAY TO SNL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2229
3 | 230 | 2230 | 0103311003 | Region I (Ilocos Region) | La Union | Naguilian | Al-alinao Sur | 16.5036 | 120.4225 | R | 1000 | 3.7 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.72 | 1.12 | Tier 1B: High GIDA Priority | 48.82 | 48.82 | 62.68 | 55.75 | E - Nearest node or line 3-5 km | 3.72 | 5.12 | Node: NGU001 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2230
3 | 231 | 2231 | 0504117022 | Region V (Bicol Region) | Masbate | Placer | Nagarao | 11.8184 | 123.8447 | R | 835 | 4.1 | 204 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.13 | 31.85 | Tier 1B: High GIDA Priority | 42.19 | 42.19 | 69.3 | 55.75 | F - Nearest node and line over 5 km | 9.13 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2231
3 | 232 | 2232 | 0603030024 | Region VI (Western Visayas) | Iloilo | Miagao | Cabalaunan | 10.648 | 122.1779 | R | 262 | 3.8 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.48 | 2.45 | Tier 1B: High GIDA Priority | 33.87 | 33.87 | 77.62 | 55.75 | D - Other node or line within 3 km | 22.48 | 2.45 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2232
3 | 233 | 2233 | 1380601067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 67 | 12.1171 | 120.546 | U | 3641 | 4.42 | 824 | 247 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.76 | 61.87 | Tier 1B: High GIDA Priority | 37.93 | 37.93 | 73.55 | 55.74 | F - Nearest node and line over 5 km | 34.76 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2233
3 | 234 | 2234 | 0304908017 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Niño | 15.3051 | 120.9435 | U | 5470 | 3.5 | 1563 | 469 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.04 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 66.39 | 66.39 | 45.08 | 55.73 | C - Line within 0.5 km; node over 1 km | 1.69 | 0.04 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2234
3 | 235 | 2235 | 0405802002 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Cupang | 14.6388 | 121.1331 | U | 129296 | 3.6 | 35916 | 10775 | Band n50 (1.5 GHz, 100 MHz TDD) | 11 | 1 | 1.51 | 1.22 | Tier 1B: High GIDA Priority | 50.72 | 50.72 | 60.74 | 55.73 | D - Other node or line within 3 km | 1.51 | 1.2 | Line: Aerial 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2235
3 | 236 | 2236 | 0203102053 | Region II (Cagayan Valley) | Isabela | Angadanan | San Vicente | 16.713 | 121.7821 | R | 514 | 3.8 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.11 | 9.96 | Tier 1B: High GIDA Priority | 40.5 | 40.5 | 70.97 | 55.73 | F - Nearest node and line over 5 km | 5.11 | 9.96 | Node: ANI002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2236
3 | 237 | 2237 | 0804819030 | Region VIII (Eastern Visayas) | Northern Samar | San Jose | Barangay West | 12.5011 | 124.4831 | R | 1055 | 4.3 | 245 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.99 | 43.41 | Tier 1B: High GIDA Priority | 38.84 | 38.84 | 72.62 | 55.73 | F - Nearest node and line over 5 km | 43.99 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2237
3 | 238 | 2238 | 0403403007 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Ganado | 14.285 | 121.0804 | U | 7085 | 3.3 | 2147 | 644 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 65.98 | 65.98 | 45.46 | 55.72 | B - Node 0.5-1 km | 1 | 0.73 | Line: AE SRL007-CBL001-CLB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2238
3 | 239 | 2239 | 0402114002 | Region IV-A (CALABARZON) | Cavite | Mendez | Asis I | 14.137 | 120.9007 | R | 3842 | 3.4 | 1130 | 339 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.2 | 4.82 | Tier 2A: High Commercial ROI | 73 | 73 | 38.43 | 55.71 | A - Node within 0.5 km | 0.2 | 4.81 | Node: MZC001 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2239
3 | 240 | 2240 | 0305408034 | Region III (Central Luzon) | Pampanga | Lubao | Santa Cruz | 14.9104 | 120.5627 | U | 18780 | 4 | 4695 | 1408 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.96 | 0.1 | Tier 2A: High Commercial ROI | 72.56 | 72.56 | 38.86 | 55.71 | B - Node 0.5-1 km | 0.96 | 0.03 | Line: LUBAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 2240
3 | 241 | 2241 | 0301406011 | Region III (Central Luzon) | Bulacan | Bustos | San Pedro | 14.9491 | 120.9083 | U | 8480 | 3.5 | 2423 | 727 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 66.76 | 66.76 | 44.65 | 55.71 | D - Other node or line within 3 km | 1.13 | 0.63 | Line: Path Measure | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2241
3 | 242 | 2242 | 0105526025 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Poblacion | 16.0703 | 120.4056 | U | 4206 | 3.6 | 1168 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 64.29 | 64.29 | 47.13 | 55.71 | A - Node within 0.5 km | 0.45 | 0.21 | Line: MANGALDAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2242
3 | 243 | 2243 | 1380500014 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Hulo | 14.5686 | 121.0353 | U | 47757 | 3.17 | 15060 | 4518 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.76 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 55.56 | 55.56 | 55.83 | 55.7 | B - Node 0.5-1 km | 0.76 | 0.13 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 2243
3 | 244 | 2244 | 1380800001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Alabang | 14.9528 | 120.0891 | U | 69215 | 3.66 | 18926 | 5678 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.31 | 0.14 | Tier 1B: High GIDA Priority | 51.66 | 51.66 | 59.74 | 55.7 | A - Node within 0.5 km | 0.31 | 0.14 | Line: BACKBONE ROUTE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2244
3 | 245 | 2245 | 1900708002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Linongan | 6.7296 | 122.2563 | R | 3410 | 5.1 | 669 | 201 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.46 | 28.29 | Tier 1B: High GIDA Priority | 42.22 | 42.22 | 69.18 | 55.7 | F - Nearest node and line over 5 km | 28.46 | 28.27 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2245
3 | 246 | 2246 | 0601905013 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Norte | 11.5223 | 122.6948 | R | 2776 | 3.8 | 731 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.21 | Tier 2A: High Commercial ROI | 71.68 | 71.68 | 39.69 | 55.69 | A - Node within 0.5 km | 0.17 | 0.04 | Line: ROXAS - ILOILO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2246
3 | 247 | 2247 | 0403420003 | Region IV-A (CALABARZON) | Laguna | Pakil | Burgos | 14.3803 | 121.4778 | R | 2415 | 3.3 | 732 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.17 | Tier 2A: High Commercial ROI | 71.38 | 71.38 | 39.99 | 55.69 | A - Node within 0.5 km | 0.16 | 0.17 | Node: PKL001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2247
3 | 248 | 2248 | 0403419002 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Biñan | 14.253 | 121.4517 | U | 7053 | 3.3 | 2137 | 641 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.29 | 1.72 | Tier 2B: Moderate GIDA Inclusion | 63.82 | 63.82 | 47.55 | 55.69 | D - Other node or line within 3 km | 2.29 | 1.71 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2248
3 | 249 | 2249 | 0403425018 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | United Bayanihan | 14.372 | 121.22 | U | 5903 | 3.3 | 1789 | 537 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.11 | 11.05 | Tier 2B: Moderate GIDA Inclusion | 54.64 | 54.64 | 56.75 | 55.69 | F - Nearest node and line over 5 km | 8.11 | 10.93 | Node: BIR003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2249
3 | 250 | 2250 | 1102504009 | Region XI (Davao Region) | Davao Oriental | Caraga | Pichon | 7.446 | 126.3491 | R | 5064 | 3.6 | 1407 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.3 | 45.81 | Tier 1B: High GIDA Priority | 52.8 | 52.8 | 58.58 | 55.69 | F - Nearest node and line over 5 km | 53.3 | 50.36 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2250
3 | 251 | 2251 | 1907002014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Luuk Pandan | 14.5052 | 121.67 | R | 3101 | 5.8 | 535 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.43 | 23.72 | Tier 1B: High GIDA Priority | 50.26 | 50.26 | 61.12 | 55.69 | E - Nearest node or line 3-5 km | 4.43 | 23.72 | Node: RLQ003 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2251
3 | 252 | 2252 | 0501705010 | Region V (Bicol Region) | Camarines Sur | Buhi | Ipil | 13.453 | 123.5342 | R | 1529 | 4.2 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.64 | 4.89 | Tier 1B: High GIDA Priority | 49.09 | 49.09 | 62.29 | 55.69 | E - Nearest node or line 3-5 km | 4.64 | 9.94 | Node: BIC001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2252
3 | 253 | 2253 | 0601912001 | Region VI (Western Visayas) | Capiz | Pontevedra | Agbanog | 11.4717 | 122.8633 | R | 963 | 3.8 | 253 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.28 | 3.05 | Tier 1B: High GIDA Priority | 47.89 | 47.89 | 63.48 | 55.69 | E - Nearest node or line 3-5 km | 3.28 | 3.05 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2253
3 | 254 | 2254 | 0403410002 | Region IV-A (CALABARZON) | Laguna | Liliw | Bagong Anyo | 14.1503 | 121.4292 | R | 1236 | 3.3 | 375 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.73 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 58.54 | 58.54 | 52.82 | 55.68 | D - Other node or line within 3 km | 1.73 | 0.97 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2254
3 | 255 | 2255 | 0300809004 | Region III (Central Luzon) | Bataan | Orani | Calero | 14.7928 | 120.5101 | R | 1465 | 3.6 | 407 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.01 | 0.42 | Tier 1B: High GIDA Priority | 53.29 | 53.29 | 58.07 | 55.68 | C - Line within 0.5 km; node over 1 km | 3.01 | 0.39 | Line: 96C DONA TO ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2255
3 | 256 | 2256 | 0702219012 | Region VII (Central Visayas) | Cebu | Consolacion | Pitogo | 10.3794 | 123.9659 | U | 4392 | 3.8 | 1156 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 66.56 | 66.56 | 44.79 | 55.67 | B - Node 0.5-1 km | 0.85 | 0.06 | Line: DANAO - CEBU | Survey short node lateral; confirm port/fiber capacity, access and route. | 2256
3 | 257 | 2257 | 1381300081 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Phil-Am | 14.6636 | 120.9917 | U | 2596 | 3.43 | 756 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.37 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 54.36 | 54.36 | 56.98 | 55.67 | A - Node within 0.5 km | 0.37 | 0.82 | Node: CCS005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2257
3 | 258 | 2258 | 1380605014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 312 | 11.873 | 122.7203 | U | 2945 | 3.11 | 946 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 14.39 | Tier 1B: High GIDA Priority | 40.9 | 40.9 | 70.44 | 55.67 | F - Nearest node and line over 5 km | 31.74 | 999999 | Node: RCZ001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2258
3 | 259 | 2259 | 0402120003 | Region IV-A (CALABARZON) | Cavite | Tanza | Biga | 14.3617 | 120.8563 | U | 17918 | 3.4 | 5270 | 1581 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.79 | 2.17 | Tier 2B: Moderate GIDA Inclusion | 68.3 | 68.3 | 43.02 | 55.66 | B - Node 0.5-1 km | 0.79 | 2.17 | Node: TZC002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2259
3 | 260 | 2260 | 0402106060 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran IV | 14.2761 | 120.9302 | U | 12442 | 3.4 | 3659 | 1098 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.97 | 1.72 | Tier 2B: Moderate GIDA Inclusion | 67.61 | 67.61 | 43.71 | 55.66 | D - Other node or line within 3 km | 2.97 | 1.73 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2260
3 | 261 | 2261 | 0403412012 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Diego | 14.1875 | 121.5352 | R | 2965 | 3.3 | 898 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 6.13 | Tier 2B: Moderate GIDA Inclusion | 67.41 | 67.41 | 43.92 | 55.66 | E - Nearest node or line 3-5 km | 3.11 | 6.09 | Node: LSL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2261
3 | 262 | 2262 | 0402115012 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Estacion | 14.3233 | 120.7644 | U | 5324 | 3.4 | 1566 | 470 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.79 | Tier 2B: Moderate GIDA Inclusion | 64.58 | 64.58 | 46.75 | 55.66 | B - Node 0.5-1 km | 0.8 | 0.79 | Line: NCC001 TO TGY001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2262
3 | 263 | 2263 | 1907009001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Bakong | 17.2558 | 122.2298 | R | 1989 | 5.8 | 343 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 33.57 | 33.57 | 77.76 | 55.66 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2263
3 | 264 | 2264 | 1907009003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Basnunuk | 17.2558 | 122.2298 | R | 1984 | 5.8 | 342 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 33.57 | 33.57 | 77.76 | 55.66 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2264
3 | 265 | 2265 | 0205007002 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Belance | 16.1928 | 121.2418 | R | 3949 | 3.8 | 1039 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.63 | 23.28 | Tier 2B: Moderate GIDA Inclusion | 64.21 | 64.21 | 47.09 | 55.65 | D - Other node or line within 3 km | 2.63 | 23.28 | Node: DNV002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2265
3 | 266 | 2266 | 0405808002 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Burgos | 14.7194 | 121.1393 | U | 49247 | 3.6 | 13680 | 4104 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.19 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 60.11 | 60.11 | 51.19 | 55.65 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.36 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2266
3 | 267 | 2267 | 1380605053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 351 | 12.2455 | 120.5242 | U | 3415 | 3.55 | 962 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.29 | 59.42 | Tier 1B: High GIDA Priority | 40.95 | 40.95 | 70.35 | 55.65 | F - Nearest node and line over 5 km | 40.29 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2267
3 | 268 | 2268 | 0504101022 | Region V (Bicol Region) | Masbate | Aroroy | Manamoc | 12.3499 | 123.4421 | R | 1119 | 4.1 | 273 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.84 | 9.35 | Tier 1B: High GIDA Priority | 39.2 | 39.2 | 72.1 | 55.65 | F - Nearest node and line over 5 km | 14.84 | 13.31 | Line: AERIAL FOC 96_CORE - 11,192 METERS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2268
3 | 269 | 2269 | 1900707025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Mahawid | 6.6038 | 122.1934 | R | 2719 | 5.1 | 533 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.56 | 36.56 | Tier 1B: High GIDA Priority | 38.14 | 38.14 | 73.16 | 55.65 | F - Nearest node and line over 5 km | 36.56 | 36.55 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2269
3 | 270 | 2270 | 1001310009 | Region X (Northern Mindanao) | Bukidnon | Lantapan | Cawayan | 7.9211 | 125.0056 | R | 3247 | 3.8 | 854 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 2.13 | Tier 2B: Moderate GIDA Inclusion | 62.08 | 62.08 | 49.2 | 55.64 | D - Other node or line within 3 km | 2.73 | 2.04 | Line: DAMULOG - VALENCIA - QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2270
3 | 271 | 2271 | 1906610014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Sangkap | 17.2556 | 122.2296 | R | 2444 | 6 | 407 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 39.73 | 39.73 | 71.56 | 55.64 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2271
3 | 272 | 2272 | 0600401008 | Region VI (Western Visayas) | Aklan | Altavas | Lupo | 11.5231 | 122.4801 | R | 2284 | 3.9 | 586 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 1.52 | Tier 2B: Moderate GIDA Inclusion | 65.98 | 65.98 | 45.28 | 55.63 | D - Other node or line within 3 km | 1.43 | 1.52 | Node: ASK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2272
3 | 273 | 2273 | 0402106055 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan II | 14.3017 | 120.993 | U | 21901 | 3.4 | 6441 | 1932 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.33 | 3.82 | Tier 2B: Moderate GIDA Inclusion | 64.19 | 64.19 | 47.07 | 55.63 | D - Other node or line within 3 km | 2.33 | 3.7 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2273
3 | 274 | 2274 | 1403211019 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | San Pedro | 17.5634 | 121.5475 | R | 751 | 3.6 | 209 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.86 | 8.81 | Tier 1B: High GIDA Priority | 44.87 | 44.87 | 66.4 | 55.63 | F - Nearest node and line over 5 km | 8.86 | 8.81 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2274
3 | 275 | 2275 | 1380604003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 270 | 13.1568 | 121.2816 | U | 954 | 3.99 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.39 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.2 | 39.2 | 72.06 | 55.63 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.38 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2275
3 | 276 | 2276 | 0601917054 | Region VI (Western Visayas) | Capiz | Tapaz | Tabon | 11.3106 | 122.4316 | R | 635 | 3.8 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.58 | 15.49 | Tier 1B: High GIDA Priority | 33.57 | 33.57 | 77.69 | 55.63 | F - Nearest node and line over 5 km | 25.58 | 18.42 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2276
3 | 277 | 2277 | 0300807016 | Region III (Central Luzon) | Bataan | Mariveles | Ipag | 14.4298 | 120.4782 | U | 12016 | 3.6 | 3338 | 1001 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.17 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 69.47 | 69.47 | 41.78 | 55.62 | D - Other node or line within 3 km | 1.17 | 0.54 | Line: PIPE ORION-MARIVELES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2277
3 | 278 | 2278 | 0600409013 | Region VI (Western Visayas) | Aklan | Libacao | Luctoga | 11.399 | 122.2914 | R | 1487 | 3.9 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.84 | 19.75 | Tier 1B: High GIDA Priority | 39.56 | 39.56 | 71.68 | 55.62 | F - Nearest node and line over 5 km | 19.84 | 19.75 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2278
3 | 279 | 2279 | 0301403024 | Region III (Central Luzon) | Bulacan | Baliuag | Tangos | 14.9703 | 120.8945 | U | 8119 | 3.5 | 2320 | 696 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 65.11 | 65.11 | 46.11 | 55.61 | C - Line within 0.5 km; node over 1 km | 1.92 | 0.12 | Line: SanLuis-Candaba Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2279
3 | 280 | 2280 | 0102934003 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay I | 17.5699 | 120.3913 | U | 400 | 3.8 | 105 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.63 | 1.16 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.8 | 38.8 | 72.42 | 55.61 | D - Other node or line within 3 km | 2.63 | 1.16 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2280
3 | 281 | 2281 | 1381000010 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Merville | 14.497 | 121.0248 | U | 34153 | 3.33 | 10247 | 3074 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.42 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 60.34 | 60.34 | 50.86 | 55.6 | D - Other node or line within 3 km | 1.42 | 0.99 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2281
3 | 282 | 2282 | 0402120035 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya III | 14.3364 | 120.8453 | U | 3612 | 3.4 | 1062 | 319 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 2.44 | Tier 2B: Moderate GIDA Inclusion | 55.3 | 55.3 | 55.9 | 55.6 | D - Other node or line within 3 km | 3.71 | 2.44 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2282
3 | 283 | 2283 | 1381300121 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Tatalon | 14.6224 | 121.0125 | U | 58286 | 3.62 | 16103 | 4831 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.66 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 54.45 | 54.45 | 56.76 | 55.6 | B - Node 0.5-1 km | 0.66 | 0.45 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2283
3 | 284 | 2284 | 0601917011 | Region VI (Western Visayas) | Capiz | Tapaz | Buri | 11.2066 | 122.4021 | R | 668 | 3.8 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.41 | 17.53 | Tier 1B: High GIDA Priority | 33.45 | 33.45 | 77.75 | 55.6 | F - Nearest node and line over 5 km | 28.41 | 22.08 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2284
3 | 285 | 2285 | 0403402002 | Region IV-A (CALABARZON) | Laguna | Bay | Calo | 14.182 | 121.2796 | R | 4494 | 3.3 | 1362 | 409 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.15 | 0.27 | Tier 2A: High Commercial ROI | 72.83 | 72.83 | 38.36 | 55.59 | A - Node within 0.5 km | 0.15 | 0.27 | Node: BAY001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2285
3 | 286 | 2286 | 1380601222 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 221 | 11.531 | 121.5301 | U | 3395 | 3.52 | 965 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.82 | 63.1 | Tier 1B: High GIDA Priority | 40.96 | 40.96 | 70.22 | 55.59 | F - Nearest node and line over 5 km | 64.82 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2286
3 | 287 | 2287 | 0205008010 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Lukidnon | 15.9444 | 121.1842 | R | 358 | 3.8 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.83 | 17.98 | Tier 1B: High GIDA Priority | 32.36 | 32.36 | 78.81 | 55.59 | F - Nearest node and line over 5 km | 15.83 | 17.98 | Node: PTN001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2287
3 | 288 | 2288 | 0301420017 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael II | 14.8141 | 121.0523 | U | 8507 | 3.5 | 2431 | 729 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.11 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 65.15 | 65.15 | 46 | 55.58 | D - Other node or line within 3 km | 2.11 | 1.96 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2288
3 | 289 | 2289 | 0401033015 | Region IV-A (CALABARZON) | Batangas | Tingloy | Santo Tomas | 13.6558 | 120.8818 | R | 2142 | 3.6 | 595 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.95 | 16.88 | Tier 2B: Moderate GIDA Inclusion | 58.25 | 58.25 | 52.91 | 55.58 | E - Nearest node or line 3-5 km | 3.95 | 16.87 | Node: MBN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2289
3 | 290 | 2290 | 0103315003 | Region I (Ilocos Region) | La Union | San Gabriel | Apayao | 16.6689 | 120.4999 | R | 988 | 3.7 | 267 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.21 | 14.69 | Tier 1B: High GIDA Priority | 43.57 | 43.57 | 67.59 | 55.58 | F - Nearest node and line over 5 km | 11.21 | 14.69 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2290
3 | 291 | 2291 | 0405607088 | Region IV-A (CALABARZON) | Quezon | Calauag | Villa San Isidro | 14.1681 | 122.2155 | R | 992 | 3.8 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.47 | 17.73 | Tier 1B: High GIDA Priority | 43.06 | 43.06 | 68.11 | 55.58 | F - Nearest node and line over 5 km | 6.47 | 17.73 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2291
3 | 292 | 2292 | 1380601155 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 155 | 13.7076 | 120.6672 | U | 3292 | 3.73 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.9 | 14.01 | Tier 1B: High GIDA Priority | 40.93 | 40.93 | 70.23 | 55.58 | F - Nearest node and line over 5 km | 13.9 | 13.95 | Node: CTG001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2292
3 | 293 | 2293 | 1600305014 | Region XIII (Caraga) | Agusan del Sur | Loreto | Katipunan | 8.1853 | 125.8978 | R | 634 | 3.9 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.39 | 10.53 | Tier 1B: High GIDA Priority | 38.78 | 38.78 | 72.38 | 55.58 | F - Nearest node and line over 5 km | 10.39 | 10.51 | Node: BWA001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2293
3 | 294 | 2294 | 0300812003 | Region III (Central Luzon) | Bataan | Samal | Ibaba | 14.764 | 120.5372 | R | 3374 | 3.6 | 937 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.24 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 70.14 | 70.14 | 40.99 | 55.57 | C - Line within 0.5 km; node over 1 km | 4.24 | 0.43 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2294
3 | 295 | 2295 | 0301420018 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santo Niño I | 14.8337 | 121.0694 | R | 2728 | 3.5 | 779 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 2.78 | Tier 2B: Moderate GIDA Inclusion | 61.22 | 61.22 | 49.92 | 55.57 | D - Other node or line within 3 km | 2.01 | 4.43 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2295
3 | 296 | 2296 | 0403429008 | Region IV-A (CALABARZON) | Laguna | Siniloan | Mendiola | 14.4641 | 121.4701 | U | 6553 | 3.3 | 1986 | 596 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.69 | 3.85 | Tier 2B: Moderate GIDA Inclusion | 59.31 | 59.31 | 51.84 | 55.57 | D - Other node or line within 3 km | 2.69 | 3.85 | Node: FYL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2296
3 | 297 | 2297 | 1381100100 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 100 | 14.6645 | 120.9981 | U | 1243 | 3.58 | 347 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.82 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.31 | 42.31 | 68.84 | 55.57 | D - Other node or line within 3 km | 1.03 | 1.05 | Node: CCS005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2297
3 | 298 | 2298 | 0105533024 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tempra-Guilig | 16.1265 | 120.4087 | R | 3955 | 3.6 | 1099 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 69.5 | 69.5 | 41.63 | 55.56 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.19 | Line: SAN FABIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2298
3 | 299 | 2299 | 0301420021 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay III | 14.8257 | 121.0825 | U | 5956 | 3.5 | 1702 | 511 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 3.84 | Tier 2B: Moderate GIDA Inclusion | 60.23 | 60.23 | 50.89 | 55.56 | D - Other node or line within 3 km | 1.61 | 3.63 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2299
3 | 300 | 2300 | 1381100060 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 60 | 14.5511 | 120.9993 | U | 1101 | 3.37 | 327 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.15 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.11 | 42.11 | 69.01 | 55.56 | B - Node 0.5-1 km | 0.85 | 0.29 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 2300
3 | 301 | 2301 | 1380602002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 288 | 14.0389 | 122.2666 | U | 2800 | 4.17 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.94 | 7.38 | Tier 1B: High GIDA Priority | 40.88 | 40.88 | 70.24 | 55.56 | F - Nearest node and line over 5 km | 7.94 | 7.37 | Line: GCQ001 TO TKQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2301
3 | 302 | 2302 | 1906610003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Daungdong | 17.2555 | 122.2296 | R | 2408 | 6 | 401 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 39.56 | 39.56 | 71.56 | 55.56 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2302
3 | 303 | 2303 | 1906610015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Timuddas | 17.2556 | 122.2296 | R | 2397 | 6 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 39.56 | 39.56 | 71.56 | 55.56 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2303
3 | 304 | 2304 | 0403429022 | Region IV-A (CALABARZON) | Laguna | Siniloan | Wawa | 14.4155 | 121.4466 | R | 3321 | 3.3 | 1006 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 1.72 | Tier 2B: Moderate GIDA Inclusion | 68.21 | 68.21 | 42.89 | 55.55 | D - Other node or line within 3 km | 2.04 | 1.72 | Line: SNL001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2304
3 | 305 | 2305 | 0405647047 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Pook | 13.9929 | 121.6283 | R | 238 | 3.8 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.71 | 1.81 | Tier 1B: High GIDA Priority | 43.92 | 43.92 | 67.17 | 55.55 | D - Other node or line within 3 km | 4.71 | 1.8 | Line: LILIW TO LUCENA AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2305
3 | 306 | 2306 | 0300803013 | Region III (Central Luzon) | Bataan | City of Balanga | Poblacion | 14.6665 | 120.5236 | U | 769 | 3.6 | 214 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.67 | 1.72 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41 | 41 | 70.09 | 55.55 | D - Other node or line within 3 km | 2.67 | 1.72 | Line: Bagac-Pilar AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2306
3 | 307 | 2307 | 1907001018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tundon | 17.2557 | 122.2297 | R | 3035 | 5.8 | 523 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 38.28 | 38.28 | 72.81 | 55.55 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2307
3 | 308 | 2308 | 0603030086 | Region VI (Western Visayas) | Iloilo | Miagao | Ongyod | 10.6307 | 122.1213 | R | 211 | 3.8 | 56 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.8 | 4.65 | Tier 1B: High GIDA Priority | 33.45 | 33.45 | 77.65 | 55.55 | E - Nearest node or line 3-5 km | 24.8 | 4.49 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2308
3 | 309 | 2309 | 0405814004 | Region IV-A (CALABARZON) | Rizal | Teresa | Dulumbayan | 14.5633 | 121.2067 | U | 8898 | 3.6 | 2472 | 742 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.53 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 66.03 | 66.03 | 45.04 | 55.54 | C - Line within 0.5 km; node over 1 km | 1.53 | 0.11 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2309
3 | 310 | 2310 | 0603027010 | Region VI (Western Visayas) | Iloilo | Lemery | Dapdapan | 11.2222 | 122.981 | R | 588 | 3.8 | 155 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.38 | 2.53 | Tier 1B: High GIDA Priority | 48.43 | 48.43 | 62.64 | 55.54 | D - Other node or line within 3 km | 5.38 | 2.52 | Line: SARA - PASSI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2310
3 | 311 | 2311 | 0401009014 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Isidro | 13.905 | 121.0596 | R | 2641 | 3.6 | 734 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 69.04 | 69.04 | 42.02 | 55.53 | C - Line within 0.5 km; node over 1 km | 1.33 | 0.33 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2311
3 | 312 | 2312 | 0301403013 | Region III (Central Luzon) | Bulacan | Baliuag | Pinagbarilan | 14.9566 | 120.8787 | U | 6878 | 3.5 | 1965 | 590 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.78 | Tier 2B: Moderate GIDA Inclusion | 64.94 | 64.94 | 46.13 | 55.53 | D - Other node or line within 3 km | 1.38 | 0.78 | Line: 48 CORE 4X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2312
3 | 313 | 2313 | 1908824010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Linamunan | 17.2551 | 122.2291 | R | 3100 | 4.7 | 660 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 41.87 | 41.87 | 69.19 | 55.53 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2313
3 | 314 | 2314 | 1381100018 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 18 | 14.5588 | 120.991 | U | 991 | 3.6 | 275 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.61 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.18 | 41.18 | 69.88 | 55.53 | B - Node 0.5-1 km | 0.62 | 0.55 | Line: UG 288C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 2314
3 | 315 | 2315 | 0601917034 | Region VI (Western Visayas) | Capiz | Tapaz | Rizal Sur | 11.3159 | 122.3863 | R | 443 | 3.8 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.62 | 20.25 | Tier 1B: High GIDA Priority | 33.19 | 33.19 | 77.87 | 55.53 | F - Nearest node and line over 5 km | 26.62 | 23.38 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2315
3 | 316 | 2316 | 0502011020 | Region V (Bicol Region) | Catanduanes | Virac | Dugui San Vicente | 13.6574 | 124.1547 | R | 628 | 4.2 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.04 | 55.59 | Tier 1B: High GIDA Priority | 32.59 | 32.59 | 78.48 | 55.53 | F - Nearest node and line over 5 km | 34.04 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2316
3 | 317 | 2317 | 0304908016 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Sur | 15.2675 | 120.9499 | R | 4886 | 3.5 | 1396 | 419 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.13 | 0.14 | Tier 2A: High Commercial ROI | 73.19 | 73.19 | 37.86 | 55.52 | C - Line within 0.5 km; node over 1 km | 2.62 | 0.13 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2317
3 | 318 | 2318 | 0403426004 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Calios | 14.275 | 121.4029 | U | 11052 | 3.3 | 3349 | 1005 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.19 | 1.14 | Tier 2B: Moderate GIDA Inclusion | 69.34 | 69.34 | 41.7 | 55.52 | D - Other node or line within 3 km | 1.19 | 1.14 | Line: UG SCL001 TO PLL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2318
3 | 319 | 2319 | 0403430003 | Region IV-A (CALABARZON) | Laguna | Victoria | Masapang | 14.1913 | 121.3377 | U | 7433 | 3.3 | 2252 | 676 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.48 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 68.42 | 68.42 | 42.62 | 55.52 | C - Line within 0.5 km; node over 1 km | 2.48 | 0.07 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2319
3 | 320 | 2320 | 1381300038 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa II | 14.6829 | 121.0624 | U | 1736 | 3.89 | 446 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 1.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.88 | 43.88 | 67.16 | 55.52 | D - Other node or line within 3 km | 1.62 | 1.12 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2320
3 | 321 | 2321 | 1380612012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 844 | 12.699 | 120.3661 | U | 4285 | 4.67 | 917 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 76.62 | 83.5 | Tier 1B: High GIDA Priority | 40.38 | 40.38 | 70.67 | 55.52 | F - Nearest node and line over 5 km | 76.62 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2321
3 | 322 | 2322 | 0405804023 | Region IV-A (CALABARZON) | Rizal | Binangonan | Mahabang Parang | 14.4684 | 121.2078 | U | 10580 | 3.6 | 2939 | 882 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.1 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 68.23 | 68.23 | 42.8 | 55.51 | D - Other node or line within 3 km | 1.1 | 0.84 | Line: TAYTAY TO SNL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2322
3 | 323 | 2323 | 1102404013 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Leling | 6.7104 | 125.3612 | R | 3293 | 3.4 | 969 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.1 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 67.96 | 67.96 | 43.06 | 55.51 | D - Other node or line within 3 km | 3.1 | 1.12 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2323
3 | 324 | 2324 | 0402111004 | Region IV-A (CALABARZON) | Cavite | Kawit | Marulas | 14.4478 | 120.914 | R | 4054 | 3.4 | 1192 | 358 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.72 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 66.69 | 66.69 | 44.33 | 55.51 | C - Line within 0.5 km; node over 1 km | 3.72 | 0.17 | Line: PSG001 RELIANCE TO NCC001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2324
3 | 325 | 2325 | 0506203038 | Region V (Bicol Region) | Sorsogon | Bulan | Obrero | 12.6693 | 123.8788 | R | 2985 | 4 | 746 | 224 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.65 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 66.54 | 66.54 | 44.48 | 55.51 | B - Node 0.5-1 km | 0.65 | 0.43 | Line: 14,546 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2325
3 | 326 | 2326 | 1380800008 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Tunasan | 14.9567 | 120.0884 | U | 63217 | 3.65 | 17317 | 5195 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.75 | 0.59 | Tier 1B: High GIDA Priority | 52.76 | 52.76 | 58.26 | 55.51 | B - Node 0.5-1 km | 0.75 | 0.59 | Line: BACKBONE ROUTE | Survey short node lateral; confirm port/fiber capacity, access and route. | 2326
3 | 327 | 2327 | 1408105019 | Cordillera Administrative Region (CAR) | Apayao | Luna | Luyon | 18.351 | 121.3693 | R | 452 | 4.2 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 2.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 43.98 | 43.98 | 67.05 | 55.51 | D - Other node or line within 3 km | 2.23 | 3.86 | Node: LAY001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2327
3 | 328 | 2328 | 0806022048 | Region VIII (Eastern Visayas) | Samar | Paranas | Casandig II | 11.8272 | 125.0675 | R | 1297 | 4.1 | 316 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.72 | 68.65 | Tier 1B: High GIDA Priority | 35.8 | 35.8 | 75.23 | 55.51 | F - Nearest node and line over 5 km | 65.72 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2328
3 | 329 | 2329 | 0501711019 | Region V (Bicol Region) | Camarines Sur | Caramoan | Haponan | 13.84 | 123.8486 | R | 781 | 4.2 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.48 | 41.93 | Tier 1B: High GIDA Priority | 43.84 | 43.84 | 67.15 | 55.5 | F - Nearest node and line over 5 km | 7.48 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2329
3 | 330 | 2330 | 1380614067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 874 | 13.9548 | 121.4785 | U | 2030 | 3.47 | 585 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.26 | 2.07 | Tier 1B: High GIDA Priority | 40.79 | 40.79 | 70.22 | 55.5 | D - Other node or line within 3 km | 4.26 | 2.06 | Line: BCY001 TO LCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2330
3 | 331 | 2331 | 0601917055 | Region VI (Western Visayas) | Capiz | Tapaz | Tacayan | 11.2275 | 122.4381 | R | 434 | 3.8 | 114 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.23 | 13.24 | Tier 1B: High GIDA Priority | 33.24 | 33.24 | 77.75 | 55.5 | F - Nearest node and line over 5 km | 26.23 | 17.68 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2331
3 | 332 | 2332 | 0600402004 | Region VI (Western Visayas) | Aklan | Balete | Calizo | 11.5682 | 122.3639 | R | 4501 | 3.9 | 1154 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.14 | Tier 2A: High Commercial ROI | 78.22 | 78.22 | 32.76 | 55.49 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.14 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2332
3 | 333 | 2333 | 0704601008 | Region VII (Central Visayas) | Negros Oriental | Amlan | Tandayag | 9.4478 | 123.2361 | R | 4074 | 3.8 | 1072 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 0.13 | Tier 2A: High Commercial ROI | 75.7 | 75.7 | 35.27 | 55.49 | C - Line within 0.5 km; node over 1 km | 2.18 | 0.11 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2333
3 | 334 | 2334 | 0301423002 | Region III (Central Luzon) | Bulacan | Santa Maria | Balasing | 14.8506 | 121.0019 | U | 10173 | 3.5 | 2907 | 872 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 1.58 | Tier 2B: Moderate GIDA Inclusion | 69.9 | 69.9 | 41.08 | 55.49 | A - Node within 0.5 km | 0.3 | 1.58 | Node: SMR007 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2334
3 | 335 | 2335 | 0405804036 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tayuman | 14.5408 | 121.1962 | U | 11775 | 3.6 | 3271 | 981 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 2.46 | Tier 2B: Moderate GIDA Inclusion | 63.56 | 63.56 | 47.41 | 55.49 | D - Other node or line within 3 km | 2.46 | 2.35 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2335
3 | 336 | 2336 | 1380605007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 303 | 13.0512 | 121.3967 | U | 738 | 2.87 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 1.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.06 | 40.06 | 70.91 | 55.49 | B - Node 0.5-1 km | 0.97 | 1.12 | Node: SOM001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2336
3 | 337 | 2337 | 1381100117 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 117 | 14.6562 | 121.0951 | U | 916 | 3.79 | 242 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.88 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.87 | 39.87 | 71.12 | 55.49 | B - Node 0.5-1 km | 0.89 | 0.85 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2337
3 | 338 | 2338 | 1381100083 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 83 | 14.5319 | 121.1102 | U | 821 | 3.09 | 266 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 1.14 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.82 | 39.82 | 71.17 | 55.49 | D - Other node or line within 3 km | 1.24 | 1.14 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2338
3 | 339 | 2339 | 0704607009 | Region VII (Central Visayas) | Negros Oriental | Bindoy | Danawan | 9.742 | 123.0766 | R | 1180 | 3.8 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.3 | 7.2 | Tier 1B: High GIDA Priority | 39.29 | 39.29 | 71.69 | 55.49 | F - Nearest node and line over 5 km | 16.3 | 8.96 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2339
3 | 340 | 2340 | 0802607007 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Magsaysay | 11.2825 | 125.4403 | R | 146 | 3.9 | 37 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.63 | 46.62 | Tier 1B: High GIDA Priority | 36.76 | 36.76 | 74.21 | 55.49 | F - Nearest node and line over 5 km | 47.63 | 999999 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2340
3 | 341 | 2341 | 1001315014 | Region X (Northern Mindanao) | Bukidnon | Maramag | North Poblacion | 7.7596 | 125.0075 | U | 16064 | 3.8 | 4227 | 1268 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.7 | 0.33 | Tier 2A: High Commercial ROI | 73.98 | 73.98 | 36.98 | 55.48 | B - Node 0.5-1 km | 0.7 | 0.33 | Line: DAMULOG - VALENCIA - QUEZON | Survey short node lateral; confirm port/fiber capacity, access and route. | 2341
3 | 342 | 2342 | 1003518021 | Region X (Northern Mindanao) | Lanao del Norte | Salvador | Pawak | 7.8926 | 123.8529 | R | 1156 | 4.2 | 275 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.73 | 9.17 | Tier 1B: High GIDA Priority | 41.36 | 41.36 | 69.6 | 55.48 | F - Nearest node and line over 5 km | 17.73 | 9.17 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2342
3 | 343 | 2343 | 1380614096 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 903 | 11.738 | 122.5941 | U | 3879 | 3.69 | 1051 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.43 | 3.07 | Tier 1B: High GIDA Priority | 41.2 | 41.2 | 69.76 | 55.48 | F - Nearest node and line over 5 km | 20.04 | 23.44 | Node: NWK001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2343
3 | 344 | 2344 | 0504121028 | Region V (Bicol Region) | Masbate | Uson | San Isidro | 12.127 | 123.7534 | R | 854 | 4.1 | 208 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.28 | 27.94 | Tier 1B: High GIDA Priority | 39.35 | 39.35 | 71.61 | 55.48 | F - Nearest node and line over 5 km | 12.28 | 27.92 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2344
3 | 345 | 2345 | 1705304009 | MIMAROPA Region | Palawan | Balabac | Melville | 7.832 | 117.0018 | R | 1975 | 3.9 | 506 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 285.05 | 999 | Tier 1B: High GIDA Priority | 39.26 | 39.26 | 71.69 | 55.48 | F - Nearest node and line over 5 km | 285.05 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2345
3 | 346 | 2346 | 0702252013 | Region VII (Central Visayas) | Cebu | Tuburan | Kanlunsing | 10.6189 | 123.8922 | R | 201 | 3.8 | 53 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.64 | 11.36 | Tier 1B: High GIDA Priority | 36.68 | 36.68 | 74.27 | 55.48 | F - Nearest node and line over 5 km | 14.64 | 11.35 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2346
3 | 347 | 2347 | 0401009012 | Region IV-A (CALABARZON) | Batangas | Cuenca | Pinagkaisahan | 13.9062 | 121.0525 | R | 2020 | 3.6 | 561 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.84 | Tier 2B: Moderate GIDA Inclusion | 65.02 | 65.02 | 45.91 | 55.47 | B - Node 0.5-1 km | 0.94 | 0.84 | Line: UG BUN001 TO SSB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2347
3 | 348 | 2348 | 1001318021 | Region X (Northern Mindanao) | Bukidnon | San Fernando | Palacpacan | 7.7835 | 125.369 | R | 1651 | 3.8 | 434 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.68 | 2.94 | Tier 1B: High GIDA Priority | 38.7 | 38.7 | 72.25 | 55.47 | F - Nearest node and line over 5 km | 26.68 | 27.87 | Node: VCB003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2348
3 | 349 | 2349 | 0802615014 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 2 | 11.4988 | 125.5026 | R | 552 | 3.9 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.67 | 61.87 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 74.24 | 55.47 | F - Nearest node and line over 5 km | 61.67 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2349
3 | 350 | 2350 | 1908712008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Talitay | Pageda | 17.2551 | 122.2291 | R | 4332 | 4.3 | 1007 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 49.3 | 49.3 | 61.61 | 55.46 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2350
3 | 351 | 2351 | 1381100119 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 119 | 14.6409 | 120.891 | U | 1695 | 3.1 | 546 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.21 | 6.72 | Tier 1B: High GIDA Priority | 38.52 | 38.52 | 72.4 | 55.46 | F - Nearest node and line over 5 km | 6.21 | 6.72 | Node: NAV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2351
3 | 352 | 2352 | 1380614032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 776 | 12.4448 | 123.189 | U | 4606 | 4.29 | 1074 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.32 | 27.92 | Tier 1B: High GIDA Priority | 41.27 | 41.27 | 69.63 | 55.45 | F - Nearest node and line over 5 km | 23.32 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2352
3 | 353 | 2353 | 1380601038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 38 | 11.5719 | 121.8914 | U | 3144 | 4.33 | 726 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.27 | 34.97 | Tier 1B: High GIDA Priority | 35.4 | 35.4 | 75.49 | 55.45 | F - Nearest node and line over 5 km | 42.27 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2353
3 | 354 | 2354 | 0403414005 | Region IV-A (CALABARZON) | Laguna | Mabitac | Nanguma | 14.445 | 121.4214 | R | 2749 | 3.3 | 833 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.8 | 0.21 | Tier 2A: High Commercial ROI | 70.99 | 70.99 | 39.89 | 55.44 | C - Line within 0.5 km; node over 1 km | 1.8 | 0.13 | Line: TAYTAY TO SNL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2354
3 | 355 | 2355 | 0403425022 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Narra | 14.0745 | 121.3466 | R | 2518 | 3.3 | 763 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 63.54 | 63.54 | 47.35 | 55.44 | D - Other node or line within 3 km | 2.5 | 0.99 | Line: SPO001 TO LBQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2355
3 | 356 | 2356 | 1381000007 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | B. F. Homes | 14.452 | 121.0406 | U | 96523 | 3.52 | 27425 | 8228 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.62 | 0.37 | Tier 1B: High GIDA Priority | 48.03 | 48.03 | 62.85 | 55.44 | B - Node 0.5-1 km | 0.62 | 0.34 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 2356
3 | 357 | 2357 | 1402704008 | Cordillera Administrative Region (CAR) | Ifugao | Lagawe | Buyabuyan | 16.7817 | 121.2014 | R | 504 | 3.9 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.64 | 6.51 | Tier 1B: High GIDA Priority | 44.4 | 44.4 | 66.48 | 55.44 | F - Nearest node and line over 5 km | 7.64 | 6.51 | Line: FOC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2357
3 | 358 | 2358 | 1003507005 | Region X (Northern Mindanao) | Lanao del Norte | Kauswagan | Inudaran | 8.1868 | 124.09 | R | 951 | 4.2 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.2 | 0.06 | Tier 1B: High GIDA Priority | 43.94 | 43.94 | 66.94 | 55.44 | C - Line within 0.5 km; node over 1 km | 17.2 | 0.06 | Line: ILIGAN - PAGADIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2358
3 | 359 | 2359 | 1380601255 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 254 | 13.1817 | 120.3768 | U | 3513 | 3.93 | 895 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 67.47 | 65.91 | Tier 1B: High GIDA Priority | 39.77 | 39.77 | 71.11 | 55.44 | F - Nearest node and line over 5 km | 67.47 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2359
3 | 360 | 2360 | 1381100118 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 118 | 14.3948 | 121.0169 | U | 1513 | 3.5 | 432 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 2.79 | Tier 1B: High GIDA Priority | 37.93 | 37.93 | 72.94 | 55.44 | D - Other node or line within 3 km | 3.11 | 2.4 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2360
3 | 361 | 2361 | 0102814009 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Poblacion | 17.9167 | 120.663 | R | 3255 | 3.7 | 880 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.22 | Tier 2A: High Commercial ROI | 70.22 | 70.22 | 40.64 | 55.43 | A - Node within 0.5 km | 0.45 | 0.11 | Line: SEGMENT 5 BANNA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2361
3 | 362 | 2362 | 0405806014 | Region IV-A (CALABARZON) | Rizal | Cardona | Looc | 14.4797 | 121.2237 | U | 9929 | 3.6 | 2758 | 827 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 67.96 | 67.96 | 42.89 | 55.43 | B - Node 0.5-1 km | 0.94 | 0.09 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2362
3 | 363 | 2363 | 0401034008 | Region IV-A (CALABARZON) | Batangas | Tuy | Luntal | 14.034 | 120.7094 | R | 3732 | 3.6 | 1037 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.48 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 67.67 | 67.67 | 43.19 | 55.43 | C - Line within 0.5 km; node over 1 km | 2.48 | 0.24 | Line: TUY - STA. TERESITA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2363
3 | 364 | 2364 | 0405804020 | Region IV-A (CALABARZON) | Rizal | Binangonan | Libis | 14.4653 | 121.1888 | U | 5653 | 3.6 | 1570 | 471 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 62.99 | 62.99 | 47.86 | 55.43 | C - Line within 0.5 km; node over 1 km | 1.69 | 0.32 | Line: TAYTAY TO SNL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2364
3 | 365 | 2365 | 0907311017 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Limamawan | 7.7982 | 123.1703 | R | 326 | 3.9 | 84 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.8 | 1.57 | Tier 1B: High GIDA Priority | 41.54 | 41.54 | 69.31 | 55.43 | D - Other node or line within 3 km | 14.8 | 1.57 | Line: PAGADIAN - BUUG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2365
3 | 366 | 2366 | 1381100113 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 113 | 14.4168 | 120.937 | U | 1677 | 3.66 | 458 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 3.47 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.44 | 41.44 | 69.42 | 55.43 | D - Other node or line within 3 km | 1.16 | 3.46 | Node: IMC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2366
3 | 367 | 2367 | 0907325006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | San Pablo | Kalilangan | 7.6483 | 123.4212 | R | 1042 | 3.9 | 267 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.39 | 19.45 | Tier 1B: High GIDA Priority | 39.31 | 39.31 | 71.55 | 55.43 | F - Nearest node and line over 5 km | 20.39 | 19.41 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2367
3 | 368 | 2368 | 1003505026 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Kidalos | 7.8493 | 123.7747 | R | 1174 | 4.2 | 280 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.7 | 4.67 | Tier 1B: High GIDA Priority | 35.83 | 35.83 | 75.03 | 55.43 | E - Nearest node or line 3-5 km | 21.7 | 4.66 | Line: ILIGAN - PAGADIAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2368
3 | 369 | 2369 | 0702233011 | Region VII (Central Visayas) | Cebu | Moalboal | Poblacion West | 9.939 | 123.3927 | R | 3648 | 3.8 | 960 | 288 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.34 | Tier 2A: High Commercial ROI | 76.69 | 76.69 | 34.15 | 55.42 | A - Node within 0.5 km | 0.24 | 0.12 | Line: Segment 7 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2369
3 | 370 | 2370 | 1004321006 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Igpit | 8.5035 | 124.5854 | U | 13322 | 3.9 | 3416 | 1025 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.21 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 69.17 | 69.17 | 41.67 | 55.42 | D - Other node or line within 3 km | 2.21 | 0.67 | Line: CDO - ILIGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2370
3 | 371 | 2371 | 1381600009 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Coloong | 14.725 | 120.945 | U | 13035 | 3.51 | 3711 | 1113 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.95 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 46.49 | 55.42 | D - Other node or line within 3 km | 1.95 | 1.5 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2371
3 | 372 | 2372 | 0405649017 | Region IV-A (CALABARZON) | Quezon | Unisan | Mairok Ilaya | 13.8643 | 122.0071 | R | 172 | 3.8 | 45 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.12 | 3.32 | Tier 1B: High GIDA Priority | 45.41 | 45.41 | 65.44 | 55.42 | E - Nearest node or line 3-5 km | 4.12 | 3.26 | Line: LCQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2372
3 | 373 | 2373 | 1906612021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Kungtad West | 16.3765 | 122.1296 | R | 1775 | 6 | 296 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.72 | 1.65 | Tier 1B: High GIDA Priority | 45.82 | 45.82 | 65.01 | 55.41 | F - Nearest node and line over 5 km | 7.72 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2373
3 | 374 | 2374 | 0702252012 | Region VII (Central Visayas) | Cebu | Tuburan | Kan-an | 10.5962 | 123.8821 | R | 250 | 3.8 | 66 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.13 | 11.84 | Tier 1B: High GIDA Priority | 36.41 | 36.41 | 74.41 | 55.41 | F - Nearest node and line over 5 km | 15.13 | 11.83 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2374
3 | 375 | 2375 | 1102303007 | Region XI (Davao Region) | Davao del Norte | Carmen | Ising | 7.3598 | 125.7063 | U | 14442 | 3.7 | 3903 | 1171 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.01 | 0.06 | Tier 2A: High Commercial ROI | 72.5 | 72.5 | 38.3 | 55.4 | C - Line within 0.5 km; node over 1 km | 1.01 | 0.06 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2375
3 | 376 | 2376 | 0702227010 | Region VII (Central Visayas) | Cebu | Liloan | San Vicente | 10.3992 | 123.9761 | U | 13364 | 3.8 | 3517 | 1055 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.55 | 1.13 | Tier 2B: Moderate GIDA Inclusion | 69.74 | 69.74 | 41.06 | 55.4 | D - Other node or line within 3 km | 2.55 | 1.13 | Line: DANAO - CEBU | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2376
3 | 377 | 2377 | 0405623007 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 4 | 14.1277 | 121.5558 | R | 2555 | 3.8 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.56 | 1.4 | Tier 2B: Moderate GIDA Inclusion | 62.5 | 62.5 | 48.29 | 55.4 | D - Other node or line within 3 km | 1.56 | 1.4 | Line: SAN PABLO - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2377
3 | 378 | 2378 | 1380614040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 784 | 12.5246 | 123.1336 | U | 3425 | 3.61 | 950 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.83 | 32.77 | Tier 1B: High GIDA Priority | 40.91 | 40.91 | 69.9 | 55.4 | F - Nearest node and line over 5 km | 28.83 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2378
3 | 379 | 2379 | 1004322008 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Looc | 8.8492 | 124.7885 | R | 3486 | 3.9 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.15 | Tier 2A: High Commercial ROI | 73.97 | 73.97 | 36.82 | 55.39 | B - Node 0.5-1 km | 0.9 | 0.15 | Line: CDO - BUENAVISTA via GINGOOG | Survey short node lateral; confirm port/fiber capacity, access and route. | 2379
3 | 380 | 2380 | 1705205026 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Ibaba West | 13.4146 | 121.1755 | R | 2793 | 3.9 | 716 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 4.34 | Tier 2B: Moderate GIDA Inclusion | 59.23 | 59.23 | 51.54 | 55.39 | D - Other node or line within 3 km | 2.33 | 4.32 | Node: CLM002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2380
3 | 381 | 2381 | 0201502003 | Region II (Cagayan Valley) | Cagayan | Alcala | Afusing Daga | 17.8525 | 121.6278 | R | 3236 | 3.9 | 830 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.55 | 5.76 | Tier 2B: Moderate GIDA Inclusion | 58.58 | 58.58 | 52.2 | 55.39 | F - Nearest node and line over 5 km | 6.55 | 5.74 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2381
3 | 382 | 2382 | 1906609024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Alu Layag-Layag | 17.2554 | 122.2294 | R | 5473 | 6 | 912 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.5 | 34.37 | Tier 1B: High GIDA Priority | 48.49 | 48.49 | 62.3 | 55.39 | F - Nearest node and line over 5 km | 29.5 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2382
3 | 383 | 2383 | 0405601002 | Region IV-A (CALABARZON) | Quezon | Agdangan | Dayap | 13.9103 | 121.9361 | R | 306 | 3.8 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.51 | 4.21 | Tier 1B: High GIDA Priority | 45.07 | 45.07 | 65.71 | 55.39 | E - Nearest node or line 3-5 km | 4.51 | 4.13 | Line: LCQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2383
3 | 384 | 2384 | 1380606028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 422 | 13.724 | 120.9079 | U | 2650 | 4.31 | 615 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.14 | 12.75 | Tier 1B: High GIDA Priority | 41.59 | 41.59 | 69.2 | 55.39 | E - Nearest node or line 3-5 km | 4.14 | 12.75 | Node: MBN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2384
3 | 385 | 2385 | 1400102005 | Cordillera Administrative Region (CAR) | Abra | Boliney | Dumagas | 17.412 | 120.765 | R | 506 | 3.8 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.35 | 23.38 | Tier 1B: High GIDA Priority | 34.79 | 34.79 | 75.98 | 55.39 | F - Nearest node and line over 5 km | 25.35 | 23.29 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2385
3 | 386 | 2386 | 0601917057 | Region VI (Western Visayas) | Capiz | Tapaz | Taganghin | 11.2222 | 122.3861 | R | 644 | 3.8 | 169 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.83 | 18.93 | Tier 1B: High GIDA Priority | 33.1 | 33.1 | 77.66 | 55.38 | F - Nearest node and line over 5 km | 30.83 | 23.33 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2386
3 | 387 | 2387 | 0403413008 | Region IV-A (CALABARZON) | Laguna | Lumban | Maytalang I | 14.2889 | 121.4582 | U | 4369 | 3.3 | 1324 | 397 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 63.83 | 63.83 | 46.9 | 55.37 | B - Node 0.5-1 km | 0.8 | 0.03 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2387
3 | 388 | 2388 | 1381100070 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 70 | 14.5442 | 120.9957 | U | 2081 | 8.1 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.15 | 0.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.76 | 41.76 | 68.99 | 55.37 | A - Node within 0.5 km | 0.15 | 0.19 | Node: PSY022 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2388
3 | 389 | 2389 | 1102315017 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Lower Panaga | 7.4467 | 125.5621 | R | 1625 | 3.7 | 439 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.01 | 18.56 | Tier 1B: High GIDA Priority | 40.46 | 40.46 | 70.28 | 55.37 | F - Nearest node and line over 5 km | 19.01 | 18.54 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2389
3 | 390 | 2390 | 0701219006 | Region VII (Central Visayas) | Bohol | Dauis | Mayacabac | 9.6158 | 123.8649 | R | 4925 | 4 | 1231 | 369 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.42 | 1.83 | Tier 2B: Moderate GIDA Inclusion | 74.9 | 74.9 | 35.81 | 55.36 | D - Other node or line within 3 km | 4.91 | 2.15 | Line: 11,428 mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2390
3 | 391 | 2391 | 0300805013 | Region III (Central Luzon) | Bataan | Hermosa | Mambog - Mandama | 14.8335 | 120.4938 | R | 3864 | 3.6 | 1073 | 322 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.11 | Tier 2A: High Commercial ROI | 71.11 | 71.11 | 39.61 | 55.36 | B - Node 0.5-1 km | 0.64 | 0.07 | Line: HERMOSA | Survey short node lateral; confirm port/fiber capacity, access and route. | 2391
3 | 392 | 2392 | 0401017006 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Sur | 14.0362 | 121.162 | R | 5100 | 3.6 | 1417 | 425 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.75 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 69.92 | 69.92 | 40.8 | 55.36 | C - Line within 0.5 km; node over 1 km | 1.75 | 0.15 | Line: TANAUAN - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2392
3 | 393 | 2393 | 1705205057 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Sto. Niño | 13.3612 | 121.1663 | U | 3715 | 3.9 | 953 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 62.76 | 62.76 | 47.95 | 55.36 | C - Line within 0.5 km; node over 1 km | 1.31 | 0.31 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2393
3 | 394 | 2394 | 0305422007 | Region III (Central Luzon) | Pampanga | Sasmuan | San Antonio | 14.8982 | 120.6221 | R | 2694 | 4 | 674 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.47 | 4.8 | Tier 2B: Moderate GIDA Inclusion | 58.61 | 58.61 | 52.11 | 55.36 | E - Nearest node or line 3-5 km | 7.47 | 4.7 | Line: foc | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2394
3 | 395 | 2395 | 0501705036 | Region V (Bicol Region) | Camarines Sur | Buhi | Santa Cruz | 13.4394 | 123.5342 | R | 2228 | 4.2 | 530 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 3.64 | Tier 2B: Moderate GIDA Inclusion | 53.98 | 53.98 | 56.74 | 55.36 | E - Nearest node or line 3-5 km | 3.38 | 10.74 | Node: BIC001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2395
3 | 396 | 2396 | 1408101002 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Cadaclan | 18.4363 | 121.1859 | R | 957 | 4.2 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.57 | 13.77 | Tier 1B: High GIDA Priority | 36.08 | 36.08 | 74.64 | 55.36 | F - Nearest node and line over 5 km | 14.57 | 13.77 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2396
3 | 397 | 2397 | 0604530011 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Mabini | 10.4939 | 122.8271 | R | 4270 | 3.7 | 1154 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.12 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 75.05 | 75.05 | 35.65 | 55.35 | C - Line within 0.5 km; node over 1 km | 3.12 | 0.07 | Line: TALISAY CITY - KABANGKALAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2397
3 | 398 | 2398 | 1401112002 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Bagong | 16.5332 | 120.5519 | R | 739 | 3.5 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.41 | 7.21 | Tier 1B: High GIDA Priority | 46.6 | 46.6 | 64.1 | 55.35 | F - Nearest node and line over 5 km | 7.41 | 7.08 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2398
3 | 399 | 2399 | 1380610053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 739 | 11.4702 | 121.4535 | U | 4598 | 4.05 | 1136 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.5 | 73.82 | Tier 1B: High GIDA Priority | 41.46 | 41.46 | 69.24 | 55.35 | F - Nearest node and line over 5 km | 75.5 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2399
3 | 400 | 2400 | 0806024007 | Region VIII (Eastern Visayas) | Samar | Tagapul-An | Nipa | 12.0764 | 124.1946 | R | 1019 | 4.1 | 249 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.53 | 58.02 | Tier 1B: High GIDA Priority | 39.02 | 39.02 | 71.68 | 55.35 | F - Nearest node and line over 5 km | 38.53 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2400
3 | 401 | 2401 | 0200901005 | Region II (Cagayan Valley) | Batanes | Basco | Chanarian | 20.4328 | 121.9589 | R | 451 | 3 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 221.77 | 215.65 | Tier 1B: High GIDA Priority | 33.54 | 33.54 | 77.17 | 55.35 | F - Nearest node and line over 5 km | 218.75 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2401
3 | 402 | 2402 | 1906613047 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Samak | 17.2554 | 122.2295 | R | 1990 | 6 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 33.31 | 33.31 | 77.39 | 55.35 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2402
3 | 403 | 2403 | 0702223033 | Region VII (Central Visayas) | Cebu | Danao City | Sabang | 10.4974 | 124.0309 | U | 16515 | 3.8 | 4346 | 1304 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.76 | 0.21 | Tier 2A: High Commercial ROI | 71.56 | 71.56 | 39.11 | 55.34 | C - Line within 0.5 km; node over 1 km | 2.76 | 0.02 | Line: 9.3km FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2403
3 | 404 | 2404 | 0306904020 | Region III (Central Luzon) | Tarlac | Capas | Santo Domingo 2nd | 15.3434 | 120.5952 | U | 7231 | 3.9 | 1854 | 556 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.44 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 66.39 | 66.39 | 44.29 | 55.34 | A - Node within 0.5 km | 0.44 | 0.16 | Line: 24 CORE (3X8) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2404
3 | 405 | 2405 | 0306910016 | Region III (Central Luzon) | Tarlac | Paniqui | Estacion | 15.6743 | 120.5847 | U | 4960 | 3.9 | 1272 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 64.02 | 64.02 | 46.66 | 55.34 | B - Node 0.5-1 km | 0.74 | 0.05 | Line: PANIQUI | Survey short node lateral; confirm port/fiber capacity, access and route. | 2405
3 | 406 | 2406 | 0804807010 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Dao | 12.4025 | 125.3227 | R | 1026 | 4.3 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 133.92 | 133.96 | Tier 1B: High GIDA Priority | 38.57 | 38.57 | 72.11 | 55.34 | F - Nearest node and line over 5 km | 133.92 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2406
3 | 407 | 2407 | 1401106006 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Tinongdan | 16.3901 | 120.7298 | R | 3745 | 3.5 | 1070 | 321 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.94 | 3.57 | Tier 2B: Moderate GIDA Inclusion | 65.82 | 65.82 | 44.85 | 55.33 | D - Other node or line within 3 km | 1.94 | 3.46 | Node: ITB004 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2407
3 | 408 | 2408 | 1381300012 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bahay Toro | 14.6648 | 121.0207 | U | 61106 | 3.54 | 17247 | 5174 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.26 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 53.88 | 53.88 | 56.79 | 55.33 | A - Node within 0.5 km | 0.26 | 0.14 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2408
3 | 409 | 2409 | 0102802046 | Region I (Ilocos Region) | Ilocos Norte | Bacarra | Santa Rita | 18.2513 | 120.6093 | R | 1136 | 3.7 | 307 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.14 | 0.72 | Tier 1B: High GIDA Priority | 48.65 | 48.65 | 62.01 | 55.33 | D - Other node or line within 3 km | 5.14 | 0.68 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2409
3 | 410 | 2410 | 1380610060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 735 | 13.9992 | 121.8745 | U | 2038 | 4.33 | 471 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.49 | 0.12 | Tier 1B: High GIDA Priority | 40.36 | 40.36 | 70.3 | 55.33 | C - Line within 0.5 km; node over 1 km | 5.49 | 0.02 | Line: ATIMONAN AERIAL to UG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2410
3 | 411 | 2411 | 0601917031 | Region VI (Western Visayas) | Capiz | Tapaz | Nayawan | 11.2442 | 122.4221 | R | 416 | 3.8 | 109 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.8 | 14.85 | Tier 1B: High GIDA Priority | 33.05 | 33.05 | 77.61 | 55.33 | F - Nearest node and line over 5 km | 27.8 | 19.04 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2411
3 | 412 | 2412 | 1004301010 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Poblacion | 8.5731 | 124.473 | R | 3800 | 3.9 | 974 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.39 | Tier 2A: High Commercial ROI | 77.07 | 77.07 | 33.57 | 55.32 | A - Node within 0.5 km | 0.33 | 0.19 | Line: CDO - ILIGAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2412
3 | 413 | 2413 | 0704601003 | Region VII (Central Visayas) | Negros Oriental | Amlan | Jugno | 9.4596 | 123.2002 | R | 4456 | 3.8 | 1173 | 352 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.37 | 0.06 | Tier 2A: High Commercial ROI | 76.06 | 76.06 | 34.58 | 55.32 | C - Line within 0.5 km; node over 1 km | 2.37 | 0.02 | Line: PROPOSED AERIAL FOC- 58.765km | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2413
3 | 414 | 2414 | 0301420028 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Mulawin | 14.8068 | 121.0621 | U | 11734 | 3.5 | 3353 | 1006 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.33 | 1.6 | Tier 2B: Moderate GIDA Inclusion | 69.24 | 69.24 | 41.4 | 55.32 | D - Other node or line within 3 km | 1.33 | 1.62 | Node: SJD004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2414
3 | 415 | 2415 | 0304902024 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Sinipit | 15.6246 | 121.1476 | R | 2771 | 3.5 | 792 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 68.6 | 68.6 | 42.04 | 55.32 | A - Node within 0.5 km | 0.12 | 0.02 | Line: Proposed AE F1-6 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2415
3 | 416 | 2416 | 0301423001 | Region III (Central Luzon) | Bulacan | Santa Maria | Bagbaguin | 14.8188 | 120.9555 | U | 8194 | 3.5 | 2341 | 702 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 67.32 | 67.32 | 43.33 | 55.32 | B - Node 0.5-1 km | 0.71 | 0.27 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 2416
3 | 417 | 2417 | 0405622008 | Region IV-A (CALABARZON) | Quezon | Lopez | Talolong | 13.879 | 122.2616 | U | 3786 | 3.8 | 996 | 299 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 62.59 | 62.59 | 48.04 | 55.32 | B - Node 0.5-1 km | 0.92 | 0.66 | Line: UG GCQ001 TO LZQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2417
3 | 418 | 2418 | 0907344012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Mate | 7.8773 | 123.2289 | R | 1111 | 3.9 | 285 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.75 | 4.23 | Tier 1B: High GIDA Priority | 39.08 | 39.08 | 71.56 | 55.32 | E - Nearest node or line 3-5 km | 23.75 | 4.2 | Line: PAGADIAN - BUUG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2418
3 | 419 | 2419 | 1400113010 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Subagan | 17.547 | 120.8941 | R | 605 | 3.8 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.29 | 27.26 | Tier 1B: High GIDA Priority | 35.23 | 35.23 | 75.41 | 55.32 | F - Nearest node and line over 5 km | 27.29 | 27.23 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2419
3 | 420 | 2420 | 1401110011 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Pico | 16.4409 | 120.5841 | U | 26490 | 3.5 | 7569 | 2271 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.83 | 0.53 | Tier 2A: High Commercial ROI | 70.01 | 70.01 | 40.61 | 55.31 | B - Node 0.5-1 km | 0.83 | 0.48 | Line: LA TRINIDAD-SAGADA | Survey short node lateral; confirm port/fiber capacity, access and route. | 2420
3 | 421 | 2421 | 0401012032 | Region IV-A (CALABARZON) | Batangas | Lemery | District I | 13.8844 | 120.9125 | R | 1364 | 3.6 | 379 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 1.35 | Tier 2B: Moderate GIDA Inclusion | 55.37 | 55.37 | 55.25 | 55.31 | D - Other node or line within 3 km | 1.07 | 1.35 | Node: TLB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2421
3 | 422 | 2422 | 1380601267 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 266 | 13.4759 | 122.5711 | U | 2072 | 3.54 | 586 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.81 | 10.16 | Tier 1B: High GIDA Priority | 40.35 | 40.35 | 70.27 | 55.31 | E - Nearest node or line 3-5 km | 4.81 | 10.16 | Node: SNQ003-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2422
3 | 423 | 2423 | 0305402012 | Region III (Central Luzon) | Pampanga | Apalit | San Vicente | 14.9457 | 120.7468 | U | 25131 | 4 | 6283 | 1885 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.37 | 1.18 | Tier 2B: Moderate GIDA Inclusion | 69.77 | 69.77 | 40.84 | 55.3 | D - Other node or line within 3 km | 1.37 | 1.18 | Line: Pipe 159-159A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2423
3 | 424 | 2424 | 0301415018 | Region III (Central Luzon) | Bulacan | Pandi | San Roque | 14.8579 | 120.956 | R | 3025 | 3.5 | 864 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 69.3 | 69.3 | 41.3 | 55.3 | B - Node 0.5-1 km | 0.68 | 0.11 | Line: PB HH24-25 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2424
3 | 425 | 2425 | 1380606035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 429 | 11.7212 | 121.1554 | U | 3113 | 3.44 | 904 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.35 | 63.21 | Tier 1B: High GIDA Priority | 40.03 | 40.03 | 70.58 | 55.3 | F - Nearest node and line over 5 km | 65.35 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2425
3 | 426 | 2426 | 0403420008 | Region IV-A (CALABARZON) | Laguna | Pakil | Kabulusan | 14.3682 | 121.3996 | R | 4746 | 3.3 | 1438 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 7.87 | Tier 2A: High Commercial ROI | 73.1 | 73.1 | 37.48 | 55.29 | B - Node 0.5-1 km | 0.59 | 7.83 | Node: PKL002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2426
3 | 427 | 2427 | 0300807019 | Region III (Central Luzon) | Bataan | Mariveles | Mt. View | 14.4501 | 120.5779 | U | 13666 | 3.6 | 3796 | 1139 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.79 | 0.2 | Tier 2A: High Commercial ROI | 71.59 | 71.59 | 38.99 | 55.29 | B - Node 0.5-1 km | 0.79 | 0.19 | Line: PIPE ORION-MARIVELES | Survey short node lateral; confirm port/fiber capacity, access and route. | 2427
3 | 428 | 2428 | 0403422016 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Norte | 14.2374 | 121.3736 | R | 2742 | 3.3 | 831 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.76 | Tier 2B: Moderate GIDA Inclusion | 68.1 | 68.1 | 42.48 | 55.29 | B - Node 0.5-1 km | 0.83 | 0.75 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2428
3 | 429 | 2429 | 0301423019 | Region III (Central Luzon) | Bulacan | Santa Maria | San Jose Patag | 14.8246 | 120.98 | U | 14618 | 3.5 | 4177 | 1253 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.02 | 1.05 | Tier 2A: High Commercial ROI | 72.31 | 72.31 | 38.26 | 55.28 | D - Other node or line within 3 km | 1.02 | 1 | Line: STA. MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2429
3 | 430 | 2430 | 0908310009 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Olutanga | Galas | 7.3677 | 122.7945 | R | 1992 | 4.2 | 474 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.06 | 34.23 | Tier 1B: High GIDA Priority | 42.59 | 42.59 | 67.97 | 55.28 | F - Nearest node and line over 5 km | 48.06 | 46.94 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2430
3 | 431 | 2431 | 0405622014 | Region IV-A (CALABARZON) | Quezon | Lopez | Binahian C | 13.8491 | 122.3027 | R | 166 | 3.8 | 44 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.09 | 2.98 | Tier 1B: High GIDA Priority | 39.62 | 39.62 | 70.95 | 55.28 | D - Other node or line within 3 km | 6.09 | 2.97 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2431
3 | 432 | 2432 | 0301423009 | Region III (Central Luzon) | Bulacan | Santa Maria | Guyong | 14.837 | 120.977 | U | 17675 | 3.5 | 5050 | 1515 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.35 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 69.81 | 69.81 | 40.74 | 55.27 | C - Line within 0.5 km; node over 1 km | 2.35 | 0.12 | Line: STA. MARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2432
3 | 433 | 2433 | 0300806001 | Region III (Central Luzon) | Bataan | Limay | Alangan | 14.5359 | 120.5904 | U | 7175 | 3.6 | 1993 | 598 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.08 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 61.5 | 61.5 | 49.05 | 55.27 | C - Line within 0.5 km; node over 1 km | 4.08 | 0.25 | Line: 24 CORE 2X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2433
3 | 434 | 2434 | 0405647006 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone IV | 14.0289 | 121.6029 | R | 919 | 3.8 | 242 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 0.96 | Tier 1B: High GIDA Priority | 51.46 | 51.46 | 59.05 | 55.26 | D - Other node or line within 3 km | 1.17 | 0.96 | Line: LBQ001 TO GCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2434
3 | 435 | 2435 | 1705305016 | MIMAROPA Region | Palawan | Bataraza | Sarong | 8.5177 | 117.4838 | R | 2848 | 3.9 | 730 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 193.18 | 195.47 | Tier 1B: High GIDA Priority | 44.84 | 44.84 | 65.67 | 55.26 | F - Nearest node and line over 5 km | 193.18 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2435
3 | 436 | 2436 | 1003521016 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Pelingkingan | 8.0546 | 123.9596 | R | 1283 | 4.2 | 305 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.72 | 9.09 | Tier 1B: High GIDA Priority | 42.18 | 42.18 | 68.33 | 55.26 | F - Nearest node and line over 5 km | 17.72 | 9.09 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2436
3 | 437 | 2437 | 1381100144 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 144 | 14.3835 | 121.0976 | U | 2033 | 3.57 | 569 | 171 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.19 | 4.93 | Tier 1B: High GIDA Priority | 39.66 | 39.66 | 70.85 | 55.26 | E - Nearest node or line 3-5 km | 5.19 | 4.92 | Line: MUNTINLUPA - BINAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2437
3 | 438 | 2438 | 0301418026 | Region III (Central Luzon) | Bulacan | Pulilan | Santo Cristo | 14.9017 | 120.875 | U | 8049 | 3.5 | 2300 | 690 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.62 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 64.05 | 64.05 | 46.45 | 55.25 | C - Line within 0.5 km; node over 1 km | 2.62 | 0.17 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2438
3 | 439 | 2439 | 1380601060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 60 | 11.7769 | 122.7233 | U | 3800 | 3.91 | 973 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.78 | 9.41 | Tier 1B: High GIDA Priority | 40.98 | 40.98 | 69.52 | 55.25 | F - Nearest node and line over 5 km | 21.08 | 21.01 | Line: ROXAS - IVISAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2439
3 | 440 | 2440 | 1380601181 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 181 | 14.1201 | 122.1752 | U | 2334 | 4.05 | 577 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.35 | 19.72 | Tier 1B: High GIDA Priority | 39.74 | 39.74 | 70.77 | 55.25 | F - Nearest node and line over 5 km | 5.35 | 19.68 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2440
3 | 441 | 2441 | 1906610006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kayawan | 17.2555 | 122.2296 | R | 2268 | 6 | 378 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 38.94 | 38.94 | 71.55 | 55.25 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2441
3 | 442 | 2442 | 0402104018 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 7 | 14.2965 | 121.0336 | R | 746 | 3.4 | 219 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 2.39 | Tier 1B: High GIDA Priority | 46.2 | 46.2 | 64.29 | 55.24 | D - Other node or line within 3 km | 1.83 | 2.39 | Node: CRC002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2442
3 | 443 | 2443 | 0401005069 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 22 | 13.7409 | 121.0676 | U | 97 | 3.6 | 27 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.65 | 1.83 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.51 | 38.51 | 71.97 | 55.24 | D - Other node or line within 3 km | 2.65 | 1.82 | Line: AE TO ELIMINATE COMMON 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2443
3 | 444 | 2444 | 1908819007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Panadtaban | 17.2552 | 122.2292 | R | 2997 | 4.7 | 638 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 34.34 | Tier 1B: High GIDA Priority | 41.25 | 41.25 | 69.21 | 55.23 | F - Nearest node and line over 5 km | 29.46 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2444
3 | 445 | 2445 | 0401015014 | Region IV-A (CALABARZON) | Batangas | Lobo | Malalim Na Sanog | 13.6591 | 121.2419 | R | 255 | 3.6 | 71 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.73 | 19.28 | Tier 1B: High GIDA Priority | 41.27 | 41.27 | 69.17 | 55.22 | E - Nearest node or line 3-5 km | 3.73 | 19.28 | Node: LBB001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2445
3 | 446 | 2446 | 1380601229 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 228 | 14.204 | 121.5952 | U | 2697 | 4.21 | 640 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.51 | 10.78 | Tier 1B: High GIDA Priority | 40.85 | 40.85 | 69.58 | 55.22 | F - Nearest node and line over 5 km | 6.51 | 10.78 | Node: SPQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2446
3 | 447 | 2447 | 1903639007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Kapatagan | 17.2546 | 122.2286 | R | 1794 | 5.7 | 315 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.37 | 34.26 | Tier 1B: High GIDA Priority | 37.3 | 37.3 | 73.14 | 55.22 | F - Nearest node and line over 5 km | 29.37 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2447
3 | 448 | 2448 | 0401009015 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 1 | 13.8978 | 121.0572 | R | 2058 | 3.6 | 572 | 172 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.58 | 65.58 | 44.85 | 55.21 | B - Node 0.5-1 km | 0.84 | 0.14 | Line: UG BUN001 TO SSB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2448
3 | 449 | 2449 | 0401029030 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 6 | 13.9079 | 120.9125 | R | 914 | 3.6 | 254 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.73 | 1.26 | Tier 1B: High GIDA Priority | 50.78 | 50.78 | 59.65 | 55.21 | D - Other node or line within 3 km | 1.73 | 1.25 | Line: UG NSB001 TO BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2449
3 | 450 | 2450 | 1903612039 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumbatan | Picotaan | 17.2548 | 122.2288 | R | 2403 | 5.7 | 422 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.41 | 34.29 | Tier 1B: High GIDA Priority | 40.18 | 40.18 | 70.24 | 55.21 | F - Nearest node and line over 5 km | 29.41 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2450
3 | 451 | 2451 | 0205706007 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Mataddi | 16.2679 | 121.4062 | R | 556 | 3.9 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.12 | 25.85 | Tier 1B: High GIDA Priority | 34.29 | 34.29 | 76.13 | 55.21 | F - Nearest node and line over 5 km | 13.12 | 25.78 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2451
3 | 452 | 2452 | 0301423008 | Region III (Central Luzon) | Bulacan | Santa Maria | Caysio | 14.8461 | 120.9685 | U | 15657 | 3.5 | 4473 | 1342 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.28 | 1.27 | Tier 2A: High Commercial ROI | 70.64 | 70.64 | 39.76 | 55.2 | D - Other node or line within 3 km | 2.28 | 1.24 | Line: PB HH24-25 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2452
3 | 453 | 2453 | 0304932027 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Young | 15.4451 | 120.7812 | R | 4233 | 3.5 | 1209 | 363 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.35 | Tier 2A: High Commercial ROI | 70.45 | 70.45 | 39.94 | 55.2 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.09 | Line: SEGMENT 31 (ZARAGOZA - TARLAC) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2453
3 | 454 | 2454 | 0304902029 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Vega | 15.6554 | 121.1356 | U | 6716 | 3.5 | 1919 | 576 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 61.67 | 61.67 | 48.74 | 55.2 | C - Line within 0.5 km; node over 1 km | 3.67 | 0.09 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2454
3 | 455 | 2455 | 1381300066 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Matandang Balara | 14.6644 | 121.0727 | U | 69667 | 3.92 | 17770 | 5331 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.3 | 0.3 | Tier 1B: High GIDA Priority | 53.14 | 53.14 | 57.26 | 55.2 | A - Node within 0.5 km | 0.3 | 0.06 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2455
3 | 456 | 2456 | 1108208019 | Region XI (Davao Region) | Davao de Oro | Montevista | Prosperidad | 7.8276 | 125.9473 | R | 2708 | 3.7 | 732 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12 | 9.42 | Tier 1B: High GIDA Priority | 51.24 | 51.24 | 59.17 | 55.2 | F - Nearest node and line over 5 km | 12 | 9.41 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2456
3 | 457 | 2457 | 1908705023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Mompong | 17.2539 | 122.228 | R | 3495 | 4.3 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 45.89 | 45.89 | 64.51 | 55.2 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2457
3 | 458 | 2458 | 0506207026 | Region V (Bicol Region) | Sorsogon | Donsol | Old Maguisa | 13.0051 | 123.5686 | R | 235 | 4 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.45 | 15.91 | Tier 1B: High GIDA Priority | 38.88 | 38.88 | 71.53 | 55.2 | F - Nearest node and line over 5 km | 11.45 | 15.79 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2458
3 | 459 | 2459 | 0402117005 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong I | 14.4276 | 120.8703 | R | 5045 | 3.4 | 1484 | 445 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 1.35 | Tier 2A: High Commercial ROI | 70.74 | 70.74 | 39.65 | 55.19 | D - Other node or line within 3 km | 1.39 | 1.35 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2459
3 | 460 | 2460 | 0403408007 | Region IV-A (CALABARZON) | Laguna | Famy | Bulihan | 14.4606 | 121.4787 | R | 3109 | 3.3 | 942 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 3.9 | Tier 2B: Moderate GIDA Inclusion | 68.63 | 68.63 | 41.76 | 55.19 | D - Other node or line within 3 km | 2.3 | 3.9 | Node: FYL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2460
3 | 461 | 2461 | 0603040075 | Region VI (Western Visayas) | Iloilo | San Joaquin | Santiago | 10.5637 | 122.0487 | R | 130 | 3.8 | 34 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.18 | 0.76 | Tier 1B: High GIDA Priority | 36.89 | 36.89 | 73.49 | 55.19 | D - Other node or line within 3 km | 25.18 | 0.62 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2461
3 | 462 | 2462 | 1400115007 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Lat-ey | 17.5835 | 121.0674 | R | 216 | 3.8 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.12 | 25.74 | Tier 1B: High GIDA Priority | 34.35 | 34.35 | 76.02 | 55.19 | F - Nearest node and line over 5 km | 29.12 | 25.64 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2462
3 | 463 | 2463 | 0502002027 | Region V (Bicol Region) | Catanduanes | Baras | Santa Maria | 13.6999 | 124.3898 | R | 185 | 4.2 | 44 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.45 | 80.61 | Tier 1B: High GIDA Priority | 36.71 | 36.71 | 73.66 | 55.18 | F - Nearest node and line over 5 km | 57.45 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2463
3 | 464 | 2464 | 0501603007 | Region V (Bicol Region) | Camarines Norte | Daet | Camambugan | 14.1072 | 122.9475 | U | 9118 | 4 | 2280 | 684 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 1.02 | Tier 2B: Moderate GIDA Inclusion | 69 | 69 | 41.34 | 55.17 | D - Other node or line within 3 km | 1.06 | 1.02 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2464
3 | 465 | 2465 | 0405608001 | Region IV-A (CALABARZON) | Quezon | Candelaria | Poblacion | 13.9315 | 121.4268 | U | 5761 | 3.8 | 1516 | 455 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 63.59 | 63.59 | 46.75 | 55.17 | C - Line within 0.5 km; node over 1 km | 1.24 | 0.31 | Line: STO. TOMAS - CANDELARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2465
3 | 466 | 2466 | 0806408004 | Region VIII (Eastern Visayas) | Southern Leyte | Macrohon | Cambaro | 10.094 | 124.9611 | R | 382 | 4.1 | 93 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.13 | 2.88 | Tier 1B: High GIDA Priority | 47.73 | 47.73 | 62.62 | 55.17 | F - Nearest node and line over 5 km | 15.07 | 7.2 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2466
3 | 467 | 2467 | 0401005073 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 4 | 13.6939 | 121.1076 | U | 1687 | 3.6 | 469 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.57 | 8.48 | Tier 1B: High GIDA Priority | 42.35 | 42.35 | 68 | 55.17 | E - Nearest node or line 3-5 km | 4.57 | 8.48 | Node: BCY007-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2467
3 | 468 | 2468 | 1381100157 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 157 | 14.394 | 121.1428 | U | 2519 | 3.63 | 693 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.94 | 8.67 | Tier 1B: High GIDA Priority | 40.18 | 40.18 | 70.16 | 55.17 | F - Nearest node and line over 5 km | 8.94 | 8.67 | Line: RELIANCE TO SAN PABLO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2468
3 | 469 | 2469 | 0201529039 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Atulayan Sur | 17.6352 | 121.7202 | R | 4645 | 3.9 | 1191 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.37 | 0.96 | Tier 2B: Moderate GIDA Inclusion | 67.26 | 67.26 | 43.06 | 55.16 | D - Other node or line within 3 km | 3.37 | 0.96 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2469
3 | 470 | 2470 | 0304926006 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Calaocan | 15.786 | 120.9948 | U | 6480 | 3.5 | 1851 | 555 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 64.85 | 64.85 | 45.47 | 55.16 | C - Line within 0.5 km; node over 1 km | 1.22 | 0.15 | Line: SAN JOSE DICT PROJECT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2470
3 | 471 | 2471 | 1908823006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Kulambog | 17.255 | 122.2291 | R | 3701 | 4.7 | 787 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.32 | Tier 1B: High GIDA Priority | 45.18 | 45.18 | 65.14 | 55.16 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2471
3 | 472 | 2472 | 1381300026 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Damar | 14.6491 | 121.0519 | U | 1750 | 5.79 | 302 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.49 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 42.24 | 42.24 | 68.08 | 55.16 | A - Node within 0.5 km | 0.49 | 0.38 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2472
3 | 473 | 2473 | 1108202029 | Region XI (Davao Region) | Davao de Oro | Laak | Inacayan | 7.8211 | 125.7569 | R | 1095 | 3.7 | 296 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.97 | 25.61 | Tier 1B: High GIDA Priority | 34.83 | 34.83 | 75.49 | 55.16 | F - Nearest node and line over 5 km | 32.97 | 27.77 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2473
3 | 474 | 2474 | 1004324009 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Santa Cruz | 8.5461 | 124.7689 | U | 16544 | 3.9 | 4242 | 1273 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.98 | 0.69 | Tier 2A: High Commercial ROI | 71.77 | 71.77 | 38.53 | 55.15 | D - Other node or line within 3 km | 1.98 | 0.68 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2474
3 | 475 | 2475 | 0304904003 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Bagong Silang | 15.2548 | 120.851 | R | 4654 | 3.5 | 1330 | 399 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 0.94 | Tier 2B: Moderate GIDA Inclusion | 69.61 | 69.61 | 40.69 | 55.15 | D - Other node or line within 3 km | 1.92 | 0.94 | Line: SANTA ROSA TO ARAYAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2475
3 | 476 | 2476 | 0501710020 | Region V (Bicol Region) | Camarines Sur | Canaman | San Vicente | 13.6357 | 123.1743 | R | 3158 | 4.2 | 752 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 1.23 | Tier 2B: Moderate GIDA Inclusion | 69.16 | 69.16 | 41.14 | 55.15 | D - Other node or line within 3 km | 1.76 | 1.23 | Line: EE05-HH06 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2476
3 | 477 | 2477 | 1907009019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Kiniktal | 17.2558 | 122.2298 | R | 1755 | 5.8 | 303 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 32.52 | 32.52 | 77.75 | 55.14 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2477
3 | 478 | 2478 | 0506212012 | Region V (Bicol Region) | Sorsogon | Matnog | Caloocan | 12.5835 | 124.0838 | R | 1082 | 4 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 56.37 | 56.37 | 53.9 | 55.13 | A - Node within 0.5 km | 0.4 | 0.36 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2478
3 | 479 | 2479 | 0402104013 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 2 | 14.3031 | 121.0391 | R | 705 | 3.4 | 207 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 1.47 | Tier 1B: High GIDA Priority | 50.92 | 50.92 | 59.33 | 55.13 | B - Node 0.5-1 km | 0.92 | 1.47 | Node: CRC002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2479
3 | 480 | 2480 | 1381100188 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 188 | 14.7521 | 120.902 | U | 1975 | 3.45 | 573 | 172 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.65 | 4.65 | Tier 1B: High GIDA Priority | 40.12 | 40.12 | 70.14 | 55.13 | E - Nearest node or line 3-5 km | 4.65 | 4.65 | Node: MRB001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2480
3 | 481 | 2481 | 1381100055 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 55 | 14.5991 | 121.0458 | U | 896 | 3.57 | 251 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.05 | 39.05 | 71.21 | 55.13 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.07 | Line: UG 288C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2481
3 | 482 | 2482 | 0501602017 | Region V (Bicol Region) | Camarines Norte | Capalonga | San Isidro | 14.3349 | 122.5327 | R | 215 | 4 | 54 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.99 | 16.45 | Tier 1B: High GIDA Priority | 38.44 | 38.44 | 71.81 | 55.13 | F - Nearest node and line over 5 km | 11.99 | 16.45 | Node: CCA001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2482
3 | 483 | 2483 | 1380601019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 19 | 13.2359 | 122.9329 | U | 2260 | 3.65 | 620 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.04 | 31.72 | Tier 1B: High GIDA Priority | 32.61 | 32.61 | 77.66 | 55.13 | F - Nearest node and line over 5 km | 26.04 | 31.71 | Node: SDQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2483
3 | 484 | 2484 | 0304908005 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Malimba | 15.2562 | 120.952 | R | 4045 | 3.5 | 1156 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.07 | 0.12 | Tier 2A: High Commercial ROI | 72.58 | 72.58 | 37.66 | 55.12 | C - Line within 0.5 km; node over 1 km | 3.88 | 0.06 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2484
3 | 485 | 2485 | 0405808008 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Rosario | 14.7465 | 121.1617 | U | 6573 | 3.6 | 1826 | 548 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 64.28 | 64.28 | 45.96 | 55.12 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.03 | Line: Aerial 216C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2485
3 | 486 | 2486 | 1108603039 | Region XI (Davao Region) | Davao Occidental | Malita | Tingolo | 6.3535 | 125.6301 | R | 2289 | 3.6 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.07 | 34.55 | Tier 1B: High GIDA Priority | 42.95 | 42.95 | 67.29 | 55.12 | F - Nearest node and line over 5 km | 36.07 | 999999 | Node: MGD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2486
3 | 487 | 2487 | 1401105010 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Loo | 16.7915 | 120.8309 | R | 5014 | 3.5 | 1433 | 430 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.07 | Tier 2A: High Commercial ROI | 70.8 | 70.8 | 39.42 | 55.11 | C - Line within 0.5 km; node over 1 km | 1.68 | 0.07 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2487
3 | 488 | 2488 | 0301406001 | Region III (Central Luzon) | Bulacan | Bustos | Bonga Mayor | 14.9543 | 120.9392 | U | 6788 | 3.5 | 1939 | 582 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 1.51 | Tier 2B: Moderate GIDA Inclusion | 63.43 | 63.43 | 46.78 | 55.11 | D - Other node or line within 3 km | 2.27 | 1.86 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2488
3 | 489 | 2489 | 0304930050 | Region III (Central Luzon) | Nueva Ecija | Talavera | San Miguel na Munti | 15.5385 | 120.9325 | U | 4087 | 3.5 | 1168 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.04 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 58.24 | 58.24 | 51.98 | 55.11 | C - Line within 0.5 km; node over 1 km | 5.04 | 0.06 | Line: TALAVERA CABLE SYSTEMS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2489
3 | 490 | 2490 | 0405804025 | Region IV-A (CALABARZON) | Rizal | Binangonan | Mambog | 14.4809 | 121.2124 | U | 10886 | 3.6 | 3024 | 907 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 67.93 | 67.93 | 42.26 | 55.1 | C - Line within 0.5 km; node over 1 km | 1.41 | 0.36 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2490
3 | 491 | 2491 | 0803739018 | Region VIII (Eastern Visayas) | Leyte | Palo | Naga-naga | 11.1539 | 124.9928 | R | 2731 | 3.8 | 719 | 216 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 65.37 | 65.37 | 44.84 | 55.1 | B - Node 0.5-1 km | 0.94 | 0.53 | Line: CAPOOCAN - TACLOBAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 2491
3 | 492 | 2492 | 0301423024 | Region III (Central Luzon) | Bulacan | Santa Maria | Tabing Bakod | 14.8017 | 120.9542 | U | 5655 | 3.5 | 1616 | 485 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.66 | Tier 2B: Moderate GIDA Inclusion | 64.7 | 64.7 | 45.5 | 55.1 | B - Node 0.5-1 km | 0.92 | 0.94 | Node: SMR006 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2492
3 | 493 | 2493 | 0300807010 | Region III (Central Luzon) | Bataan | Mariveles | San Isidro | 14.4546 | 120.5415 | U | 6806 | 3.6 | 1891 | 567 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.29 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 61.99 | 61.99 | 48.21 | 55.1 | D - Other node or line within 3 km | 3.29 | 0.71 | Line: PIPE ORION-MARIVELES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2493
3 | 494 | 2494 | 0401033001 | Region IV-A (CALABARZON) | Batangas | Tingloy | Corona | 13.6308 | 120.9293 | R | 1036 | 3.6 | 288 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.5 | 13.83 | Tier 1B: High GIDA Priority | 48.01 | 48.01 | 62.18 | 55.1 | F - Nearest node and line over 5 km | 7.5 | 13.78 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2494
3 | 495 | 2495 | 1003503004 | Region X (Northern Mindanao) | Lanao del Norte | Baroy | Bato | 7.9878 | 123.8177 | R | 419 | 4.2 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.46 | 4.19 | Tier 1B: High GIDA Priority | 46.42 | 46.42 | 63.78 | 55.1 | E - Nearest node or line 3-5 km | 6.46 | 4.19 | Line: ILIGAN - PAGADIAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2495
3 | 496 | 2496 | 1381100073 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 73 | 14.5426 | 120.9961 | U | 722 | 3.19 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.68 | 40.68 | 69.51 | 55.1 | A - Node within 0.5 km | 0.28 | 0.17 | Line: Existing 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2496
3 | 497 | 2497 | 0806011005 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Camonoan | 12.1484 | 124.8819 | R | 142 | 4.1 | 35 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.66 | 96.62 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 73.51 | 55.1 | F - Nearest node and line over 5 km | 96.66 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2497
3 | 498 | 2498 | 1404402021 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Sadsadan | 16.9021 | 120.8666 | R | 2745 | 3.7 | 742 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.65 | 1.38 | Tier 2B: Moderate GIDA Inclusion | 67.37 | 67.37 | 42.81 | 55.09 | D - Other node or line within 3 km | 2.65 | 1.34 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2498
3 | 499 | 2499 | 1400127002 | Cordillera Administrative Region (CAR) | Abra | Villaviciosa | Bol-lilising | 17.3532 | 120.5985 | R | 278 | 3.8 | 73 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.66 | 12.59 | Tier 1B: High GIDA Priority | 39.37 | 39.37 | 70.81 | 55.09 | F - Nearest node and line over 5 km | 12.66 | 12.59 | Line: SEGMENT 2 (CANDON - VIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2499
3 | 500 | 2500 | 0205706012 | Region II (Cagayan Valley) | Quirino | Nagtipunan | San Pugo | 16.1313 | 121.4946 | R | 503 | 3.9 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.66 | 21.84 | Tier 1B: High GIDA Priority | 32.98 | 32.98 | 77.2 | 55.09 | F - Nearest node and line over 5 km | 14.66 | 21.8 | Node: NTQ001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2500
3 | 501 | 2501 | 0201529013 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 10 | 17.6307 | 121.7371 | U | 2285 | 3.9 | 586 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.53 | 0.2 | Tier 1B: High GIDA Priority | 51.25 | 51.25 | 58.92 | 55.08 | C - Line within 0.5 km; node over 1 km | 2.53 | 0.2 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2501
3 | 502 | 2502 | 0300804044 | Region III (Central Luzon) | Bataan | Dinalupihan | Aquino | 14.8542 | 120.4528 | R | 119 | 3.6 | 33 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 1.24 | Tier 1B: High GIDA Priority | 48 | 48 | 62.16 | 55.08 | D - Other node or line within 3 km | 1.5 | 1.24 | Line: Path Measure | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2502
3 | 503 | 2503 | 1380614043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 787 | 11.9855 | 120.6809 | U | 3646 | 4.02 | 907 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.12 | 58.22 | Tier 1B: High GIDA Priority | 40.12 | 40.12 | 70.04 | 55.08 | F - Nearest node and line over 5 km | 47.12 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2503
3 | 504 | 2504 | 0600407008 | Region VI (Western Visayas) | Aklan | Kalibo | Estancia | 11.6873 | 122.3661 | U | 9882 | 3.9 | 2534 | 760 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 69.49 | 69.49 | 40.66 | 55.07 | C - Line within 0.5 km; node over 1 km | 1.14 | 0.06 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2504
3 | 505 | 2505 | 0401017005 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Norte | 14.0388 | 121.158 | R | 4522 | 3.6 | 1256 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68.9 | 68.9 | 41.24 | 55.07 | C - Line within 0.5 km; node over 1 km | 2.09 | 0.21 | Line: TANAUAN - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2505
3 | 506 | 2506 | 0301414001 | Region III (Central Luzon) | Bulacan | Obando | Binuangan | 14.717 | 120.9088 | U | 5273 | 3.5 | 1507 | 452 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 5.03 | Tier 2B: Moderate GIDA Inclusion | 57.53 | 57.53 | 52.61 | 55.07 | E - Nearest node or line 3-5 km | 3.11 | 5.03 | Node: OBB001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2506
3 | 507 | 2507 | 0305413026 | Region III (Central Luzon) | Pampanga | Mexico | San Antonio | 15.0636 | 120.7241 | U | 6110 | 4 | 1528 | 458 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 64.03 | 64.03 | 46.09 | 55.06 | C - Line within 0.5 km; node over 1 km | 1.13 | 0.19 | Line: EXISTING | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2507
3 | 508 | 2508 | 0500507013 | Region V (Bicol Region) | Albay | Libon | Buga | 13.296 | 123.3592 | R | 3747 | 4.1 | 914 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.98 | 6.24 | Tier 2B: Moderate GIDA Inclusion | 60.25 | 60.25 | 49.86 | 55.06 | F - Nearest node and line over 5 km | 6.98 | 6.24 | Line: IRIGA - LEGAZPI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2508
3 | 509 | 2509 | 1381600019 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Marulas | 14.6778 | 120.9884 | U | 61583 | 3.5 | 17595 | 5278 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.79 | 0.78 | Tier 1B: High GIDA Priority | 52.34 | 52.34 | 57.78 | 55.06 | B - Node 0.5-1 km | 0.79 | 0.77 | Line: Aerial 96C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2509
3 | 510 | 2510 | 0401029024 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 10 | 13.9088 | 120.9281 | R | 788 | 3.6 | 219 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.33 | 1.39 | Tier 1B: High GIDA Priority | 50.53 | 50.53 | 59.58 | 55.06 | D - Other node or line within 3 km | 1.33 | 1.38 | Node: LYB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2510
3 | 511 | 2511 | 1381100058 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 58 | 14.5883 | 120.9453 | U | 1527 | 3.67 | 416 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 3.33 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.25 | 39.25 | 70.88 | 55.06 | D - Other node or line within 3 km | 1.83 | 3.31 | Node: MNL068 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2511
3 | 512 | 2512 | 1381600025 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Poblacion | 14.7044 | 120.9899 | U | 224 | 3.15 | 71 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.34 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.49 | 36.49 | 73.62 | 55.06 | C - Line within 0.5 km; node over 1 km | 1.15 | 0.14 | Line: Reliance - J3 Core Ring, UG, VAL (In-House) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2512
3 | 513 | 2513 | 0103317022 | Region I (Ilocos Region) | La Union | Santo Tomas | Tubod | 16.2579 | 120.4 | R | 3216 | 3.7 | 869 | 261 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.99 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 69.24 | 69.24 | 40.86 | 55.05 | C - Line within 0.5 km; node over 1 km | 3.99 | 0.19 | Line: SANTO TOMAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2513
3 | 514 | 2514 | 1705312007 | MIMAROPA Region | Palawan | El Nido | Manlag | 11.117 | 119.4316 | R | 3345 | 3.9 | 858 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.49 | 33.76 | Tier 2B: Moderate GIDA Inclusion | 59.69 | 59.69 | 50.4 | 55.05 | F - Nearest node and line over 5 km | 5.49 | 33.55 | Node: ENW004 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2514
3 | 515 | 2515 | 1381200011 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Manggahan | 14.6002 | 121.0949 | U | 90884 | 3.09 | 29445 | 8834 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.37 | 0.33 | Tier 1B: High GIDA Priority | 48.55 | 48.55 | 61.55 | 55.05 | A - Node within 0.5 km | 0.37 | 0.32 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2515
3 | 516 | 2516 | 1003517002 | Region X (Northern Mindanao) | Lanao del Norte | Poona Piagapo | Bubong-Dinaig | 8.0748 | 124.1444 | R | 1134 | 4.2 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.02 | 9.22 | Tier 1B: High GIDA Priority | 42.01 | 42.01 | 68.09 | 55.05 | F - Nearest node and line over 5 km | 16.02 | 9.13 | Line: 216f feeder iligan completed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2516
3 | 517 | 2517 | 0603040013 | Region VI (Western Visayas) | Iloilo | San Joaquin | Cadluman | 10.5865 | 122.0977 | R | 197 | 3.8 | 52 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.2 | 0.83 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 73.35 | 55.05 | D - Other node or line within 3 km | 26.2 | 0.74 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2517
3 | 518 | 2518 | 0604531007 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay IV | 10.8989 | 123.0732 | R | 1183 | 3.7 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 57.7 | 57.7 | 52.38 | 55.04 | A - Node within 0.5 km | 0.3 | 0.1 | Line: TALISAY - VICTORIAS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2518
3 | 519 | 2519 | 0304902027 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Tugatug | 15.6452 | 121.1758 | R | 2462 | 3.5 | 703 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.92 | 3.6 | Tier 2B: Moderate GIDA Inclusion | 56.81 | 56.81 | 53.27 | 55.04 | E - Nearest node or line 3-5 km | 3.92 | 3.6 | Line: Proposed AE F1-6 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2519
3 | 520 | 2520 | 0102917003 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Lancuas | 17.2515 | 120.5914 | R | 950 | 3.8 | 250 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.23 | 1.82 | Tier 1B: High GIDA Priority | 50.75 | 50.75 | 59.33 | 55.04 | D - Other node or line within 3 km | 7.23 | 1.78 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2520
3 | 521 | 2521 | 0806008020 | Region VIII (Eastern Visayas) | Samar | Hinabangan | San Jose | 11.7323 | 125.142 | R | 802 | 4.1 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.86 | 59.59 | Tier 1B: High GIDA Priority | 37.62 | 37.62 | 72.45 | 55.04 | F - Nearest node and line over 5 km | 56.86 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2521
3 | 522 | 2522 | 0203110005 | Region II (Cagayan Valley) | Isabela | Dinapigue | Digumased | 16.5247 | 122.2657 | R | 3023 | 3.8 | 796 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 68.49 | 68.49 | 41.57 | 55.03 | A - Node within 0.5 km | 0.21 | 999999 | Node: DPI001 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2522
3 | 523 | 2523 | 0301420036 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Maharlika | 14.7936 | 121.0655 | U | 3195 | 3.5 | 913 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 63.01 | 63.01 | 47.05 | 55.03 | B - Node 0.5-1 km | 0.7 | 0.2 | Line: SJDM | Survey short node lateral; confirm port/fiber capacity, access and route. | 2523
3 | 524 | 2524 | 0402108018 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Pasong Camachile I | 14.316 | 120.9051 | U | 22626 | 3.4 | 6655 | 1996 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.49 | 2.47 | Tier 2B: Moderate GIDA Inclusion | 63.69 | 63.69 | 46.35 | 55.02 | D - Other node or line within 3 km | 2.49 | 2.7 | Node: TRC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2524
3 | 525 | 2525 | 1003514015 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Madaya | 8.0228 | 124.0819 | R | 844 | 4.2 | 201 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.23 | 18.14 | Tier 1B: High GIDA Priority | 38.5 | 38.5 | 71.54 | 55.02 | F - Nearest node and line over 5 km | 21.23 | 18.08 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2525
3 | 526 | 2526 | 1908706013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Payan | 16.5062 | 122.3865 | R | 1470 | 4.3 | 342 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.25 | 13.62 | Tier 1B: High GIDA Priority | 38.22 | 38.22 | 71.83 | 55.02 | F - Nearest node and line over 5 km | 13.25 | 999999 | Node: DPI001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2526
3 | 527 | 2527 | 0702214014 | Region VII (Central Visayas) | Cebu | City of Carcar | Poblacion III | 10.1056 | 123.6439 | U | 7495 | 3.8 | 1972 | 592 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 68.75 | 68.75 | 41.28 | 55.01 | B - Node 0.5-1 km | 0.78 | 0.1 | Line: 216f | Survey short node lateral; confirm port/fiber capacity, access and route. | 2527
3 | 528 | 2528 | 1004321015 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Taboc | 8.517 | 124.5762 | U | 4039 | 3.9 | 1036 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 65.86 | 65.86 | 44.16 | 55.01 | A - Node within 0.5 km | 0.4 | 0.16 | Line: Implem. 96f aerial FOC | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2528
3 | 529 | 2529 | 0600613010 | Region VI (Western Visayas) | Antique | San Jose | Barangay 8 | 10.7453 | 121.9493 | U | 5389 | 3.9 | 1382 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 64.74 | 64.74 | 45.29 | 55.01 | C - Line within 0.5 km; node over 1 km | 2.27 | 0.31 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2529
3 | 530 | 2530 | 1908803005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Abdullah Sangki | Maganoy | 17.2552 | 122.2292 | R | 2909 | 4.7 | 619 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 34.34 | Tier 1B: High GIDA Priority | 40.82 | 40.82 | 69.21 | 55.01 | F - Nearest node and line over 5 km | 29.46 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2530
3 | 531 | 2531 | 1380601198 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 198 | 13.5501 | 120.453 | U | 3840 | 4.19 | 917 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.36 | 36.43 | Tier 1B: High GIDA Priority | 40.38 | 40.38 | 69.65 | 55.01 | F - Nearest node and line over 5 km | 36.36 | 52.28 | Node: CTG001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2531
3 | 532 | 2532 | 1908816006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Inug-ug | 17.255 | 122.229 | R | 2498 | 4.7 | 531 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 38.46 | 38.46 | 71.56 | 55.01 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2532
3 | 533 | 2533 | 0301420043 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Poblacion I | 14.8518 | 121.0686 | U | 5871 | 3.5 | 1677 | 503 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 3.68 | Tier 2B: Moderate GIDA Inclusion | 60.56 | 60.56 | 49.44 | 55 | D - Other node or line within 3 km | 1.37 | 6.45 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2533
3 | 534 | 2534 | 1380605077 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 374 | 12.9984 | 123.1652 | U | 4221 | 4.77 | 884 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.14 | 45.07 | Tier 1B: High GIDA Priority | 39.51 | 39.51 | 70.5 | 55 | F - Nearest node and line over 5 km | 19.14 | 45.01 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2534
3 | 535 | 2535 | 0806008009 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Lim-ao | 11.7129 | 125.0901 | R | 307 | 4.1 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.49 | 56.34 | Tier 1B: High GIDA Priority | 36.72 | 36.72 | 73.27 | 55 | F - Nearest node and line over 5 km | 53.49 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2535
3 | 536 | 2536 | 1003502027 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Sarip-Alawi | 8.1045 | 124.2018 | R | 3403 | 4.2 | 810 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.2 | 2.32 | Tier 1B: High GIDA Priority | 52.23 | 52.23 | 57.76 | 54.99 | D - Other node or line within 3 km | 13.2 | 2.23 | Line: 216f feeder iligan completed | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2536
3 | 537 | 2537 | 0201528026 | Region II (Cagayan Valley) | Cagayan | Tuao | San Juan | 17.6063 | 121.5246 | R | 1045 | 3.9 | 268 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.3 | 10.01 | Tier 1B: High GIDA Priority | 43.18 | 43.18 | 66.79 | 54.99 | F - Nearest node and line over 5 km | 7.3 | 9.89 | Node: TUC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2537
3 | 538 | 2538 | 1381100088 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 88 | 14.5452 | 120.9965 | U | 942 | 4.04 | 233 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.24 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.95 | 40.95 | 69.03 | 54.99 | A - Node within 0.5 km | 0.23 | 0.24 | Node: PSY022 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2538
3 | 539 | 2539 | 1003514029 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Sandigamunai | 8.0176 | 124.0522 | R | 1067 | 4.2 | 254 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.47 | 18.48 | Tier 1B: High GIDA Priority | 39.14 | 39.14 | 70.83 | 54.99 | F - Nearest node and line over 5 km | 24.47 | 18.43 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2539
3 | 540 | 2540 | 1381100012 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 12 | 14.5238 | 120.9935 | U | 587 | 3.23 | 182 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.37 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.86 | 38.86 | 71.12 | 54.99 | B - Node 0.5-1 km | 0.6 | 0.37 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 2540
3 | 541 | 2541 | 1381100147 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 147 | 14.3693 | 120.9303 | U | 1321 | 3.36 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 6.85 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.57 | 38.57 | 71.41 | 54.99 | D - Other node or line within 3 km | 1.88 | 6.85 | Node: IMC003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2541
3 | 542 | 2542 | 1003521006 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Big Meladoc | 8.0427 | 123.9586 | R | 624 | 4.2 | 149 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.56 | 10.21 | Tier 1B: High GIDA Priority | 38.44 | 38.44 | 71.54 | 54.99 | F - Nearest node and line over 5 km | 17.56 | 10.2 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2542
3 | 543 | 2543 | 1102509013 | Region XI (Davao Region) | Davao Oriental | City of Mati | Langka | 6.3561 | 126.1989 | R | 1281 | 3.6 | 356 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 63.51 | 58.89 | Tier 1B: High GIDA Priority | 35.85 | 35.85 | 74.14 | 54.99 | F - Nearest node and line over 5 km | 63.51 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2543
3 | 544 | 2544 | 0403428001 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Aplaya | 14.318 | 121.1211 | U | 17383 | 3.3 | 5268 | 1580 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.97 | 2.35 | Tier 2B: Moderate GIDA Inclusion | 67.96 | 67.96 | 41.99 | 54.98 | B - Node 0.5-1 km | 0.97 | 2.34 | Node: SRL004 - TYPE 4A | Survey short node lateral; confirm port/fiber capacity, access and route. | 2544
3 | 545 | 2545 | 1600303024 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Segunda | 8.7092 | 125.7586 | R | 343 | 3.9 | 88 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.47 | Tier 1B: High GIDA Priority | 52 | 52 | 57.97 | 54.98 | B - Node 0.5-1 km | 0.54 | 0.26 | Line: FOC-96C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2545
3 | 546 | 2546 | 0205706009 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Old Gumiad | 16.1272 | 121.3939 | R | 962 | 3.9 | 247 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.88 | 28.34 | Tier 1B: High GIDA Priority | 33.98 | 33.98 | 75.99 | 54.98 | F - Nearest node and line over 5 km | 19.88 | 28.32 | Node: DNV002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2546
3 | 547 | 2547 | 0203111008 | Region II (Cagayan Valley) | Isabela | Divilacan | Dimapnat | 17.3011 | 122.3142 | R | 1052 | 3.8 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.71 | 44.51 | Tier 1B: High GIDA Priority | 32.65 | 32.65 | 77.32 | 54.98 | F - Nearest node and line over 5 km | 39.71 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2547
3 | 548 | 2548 | 0500516023 | Region V (Bicol Region) | Albay | Santo Domingo | Santa Misericordia | 13.2548 | 123.7587 | R | 3256 | 4.1 | 794 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 68.57 | 68.57 | 41.38 | 54.97 | C - Line within 0.5 km; node over 1 km | 2.81 | 0.15 | Line: CONVERGE HH-024 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2548
3 | 549 | 2549 | 0306916096 | Region III (Central Luzon) | Tarlac | City of Tarlac | Matadero | 15.487 | 120.5993 | U | 2278 | 3.9 | 584 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 0.01 | Tier 1B: High GIDA Priority | 52.71 | 52.71 | 57.23 | 54.97 | C - Line within 0.5 km; node over 1 km | 1.51 | 0.01 | Line: PIPE 92-100 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2549
3 | 550 | 2550 | 1400112008 | Cordillera Administrative Region (CAR) | Abra | Langiden | Quillat | 17.5872 | 120.5847 | R | 866 | 3.8 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.7 | 2.57 | Tier 1B: High GIDA Priority | 49.13 | 49.13 | 60.81 | 54.97 | D - Other node or line within 3 km | 3.7 | 2.46 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2550
3 | 551 | 2551 | 0205006018 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Villa Aurora | 16.6307 | 121.4012 | R | 592 | 3.8 | 156 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.73 | 2.16 | Tier 1B: High GIDA Priority | 45.9 | 45.9 | 64.04 | 54.97 | D - Other node or line within 3 km | 4.73 | 2.15 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2551
3 | 552 | 2552 | 0405647031 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Isabang | 13.9644 | 121.5653 | U | 12686 | 3.8 | 3338 | 1001 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.32 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 67.47 | 67.47 | 42.44 | 54.96 | C - Line within 0.5 km; node over 1 km | 2.32 | 0.06 | Line: SAN JUAN TO UNISAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2552
3 | 553 | 2553 | 0402120009 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya I | 14.3593 | 120.8476 | U | 5047 | 3.4 | 1484 | 445 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 2.55 | Tier 2B: Moderate GIDA Inclusion | 59.94 | 59.94 | 49.98 | 54.96 | D - Other node or line within 3 km | 1.27 | 2.55 | Node: TZC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2553
3 | 554 | 2554 | 0102934035 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Julian Sur | 17.564 | 120.4156 | R | 1387 | 3.8 | 365 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.24 | 2.57 | Tier 1B: High GIDA Priority | 47.45 | 47.45 | 62.48 | 54.96 | D - Other node or line within 3 km | 4.24 | 2.57 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2554
3 | 555 | 2555 | 1102504006 | Region XI (Davao Region) | Davao Oriental | Caraga | Manorigao | 7.4019 | 126.5492 | R | 1700 | 3.6 | 472 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.83 | 60.75 | Tier 1B: High GIDA Priority | 38.68 | 38.68 | 71.23 | 54.96 | F - Nearest node and line over 5 km | 61.83 | 999999 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2555
3 | 556 | 2556 | 1102503008 | Region XI (Davao Region) | Davao Oriental | Boston | Simulao | 7.8812 | 126.2504 | R | 1194 | 3.6 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.22 | 18.82 | Tier 1B: High GIDA Priority | 37.01 | 37.01 | 72.91 | 54.96 | F - Nearest node and line over 5 km | 22.22 | 18.81 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2556
3 | 557 | 2557 | 0405622006 | Region IV-A (CALABARZON) | Quezon | Lopez | Gomez | 13.8861 | 122.2587 | U | 3496 | 3.8 | 920 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 63.41 | 63.41 | 46.49 | 54.95 | A - Node within 0.5 km | 0.4 | 0.3 | Line: UG GCQ001 TO LZQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2557
3 | 558 | 2558 | 1705309006 | MIMAROPA Region | Palawan | Coron | Cabugao | 11.9266 | 120.254 | R | 3173 | 3.9 | 814 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.61 | 99.79 | Tier 2B: Moderate GIDA Inclusion | 56.47 | 56.47 | 53.43 | 54.95 | F - Nearest node and line over 5 km | 8.61 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2558
3 | 559 | 2559 | 0401029032 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 8 | 13.8685 | 120.9087 | R | 1335 | 3.6 | 371 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 3.07 | Tier 1B: High GIDA Priority | 51.35 | 51.35 | 58.55 | 54.95 | D - Other node or line within 3 km | 1.21 | 3.05 | Node: TLB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2559
3 | 560 | 2560 | 0205703026 | Region II (Cagayan Valley) | Quirino | Diffun | Ricarte Sur | 16.5329 | 121.5005 | R | 597 | 3.9 | 153 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.4 | 5.36 | Tier 1B: High GIDA Priority | 42.52 | 42.52 | 67.38 | 54.95 | E - Nearest node or line 3-5 km | 3.4 | 5.35 | Node: CBQ001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2560
3 | 561 | 2561 | 0201522017 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Santiago | 18.5231 | 121.2358 | R | 262 | 3.9 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.93 | 3.16 | Tier 1B: High GIDA Priority | 41.34 | 41.34 | 68.56 | 54.95 | E - Nearest node or line 3-5 km | 3.93 | 3.16 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2561
3 | 562 | 2562 | 1003511005 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Ilihan | 8.0312 | 123.9089 | R | 480 | 4.2 | 114 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.16 | 8.62 | Tier 1B: High GIDA Priority | 41.3 | 41.3 | 68.59 | 54.95 | F - Nearest node and line over 5 km | 12.16 | 8.62 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2562
3 | 563 | 2563 | 0301423022 | Region III (Central Luzon) | Bulacan | Santa Maria | Sta. Cruz | 14.8359 | 120.9745 | U | 11878 | 3.5 | 3394 | 1018 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.24 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 67.89 | 67.89 | 41.99 | 54.94 | C - Line within 0.5 km; node over 1 km | 2.24 | 0.2 | Line: STA. MARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2563
3 | 564 | 2564 | 1004301014 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Taparak | 8.5371 | 124.4613 | R | 1801 | 3.9 | 462 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.02 | 3.78 | Tier 2B: Moderate GIDA Inclusion | 55.69 | 55.69 | 54.19 | 54.94 | E - Nearest node or line 3-5 km | 4.02 | 3.78 | Line: CDO - ILIGAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2564
3 | 565 | 2565 | 1381100197 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 197 | 14.3753 | 121.1905 | U | 3870 | 3.13 | 1238 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.86 | 10.23 | Tier 1B: High GIDA Priority | 48.74 | 48.74 | 61.14 | 54.94 | F - Nearest node and line over 5 km | 7.86 | 10.17 | Node: BIR003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2565
3 | 566 | 2566 | 1381100035 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 35 | 14.5027 | 120.9734 | U | 1083 | 3.28 | 330 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 1.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.38 | 40.38 | 69.51 | 54.94 | D - Other node or line within 3 km | 1.89 | 1.87 | Line: Existing 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2566
3 | 567 | 2567 | 1380601182 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 182 | 11.7622 | 120.8944 | U | 4072 | 4.63 | 880 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.83 | 66.27 | Tier 1B: High GIDA Priority | 39.42 | 39.42 | 70.46 | 54.94 | F - Nearest node and line over 5 km | 66.83 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2567
3 | 568 | 2568 | 0301407004 | Region III (Central Luzon) | Bulacan | Calumpit | Buguion | 14.8983 | 120.7929 | R | 4015 | 3.5 | 1147 | 344 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.84 | 0.86 | Tier 2B: Moderate GIDA Inclusion | 67.75 | 67.75 | 42.11 | 54.93 | D - Other node or line within 3 km | 2.84 | 0.86 | Line: 24 CORE (3X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2568
3 | 569 | 2569 | 1001312058 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Saint Peter | 7.8638 | 125.0091 | R | 3152 | 3.8 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 63.93 | 63.93 | 45.92 | 54.93 | D - Other node or line within 3 km | 3.67 | 0.73 | Line: DAMULOG - VALENCIA - QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2569
3 | 570 | 2570 | 1380605044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 342 | 11.9245 | 121.9468 | U | 1765 | 5.28 | 334 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.65 | 0.38 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.38 | 39.38 | 70.49 | 54.93 | D - Other node or line within 3 km | 2.65 | 999999 | Node: MYK001 - TYPE 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2570
3 | 571 | 2571 | 0504106032 | Region V (Bicol Region) | Masbate | Cawayan | Lague-lague | 12.0829 | 123.7365 | R | 1042 | 4.1 | 254 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.33 | 28.95 | Tier 1B: High GIDA Priority | 37.58 | 37.58 | 72.29 | 54.93 | F - Nearest node and line over 5 km | 17.33 | 28.96 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2571
3 | 572 | 2572 | 0301411014 | Region III (Central Luzon) | Bulacan | Marilao | Santa Rosa II | 14.7859 | 120.969 | U | 13984 | 3.5 | 3995 | 1198 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.9 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 68.83 | 68.83 | 41 | 54.92 | D - Other node or line within 3 km | 2.9 | 2.65 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2572
3 | 573 | 2573 | 0402106066 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin III | 14.3636 | 120.956 | U | 10715 | 3.4 | 3151 | 945 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.29 | 5.84 | Tier 2B: Moderate GIDA Inclusion | 63.43 | 63.43 | 46.4 | 54.92 | D - Other node or line within 3 km | 2.29 | 6.82 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2573
3 | 574 | 2574 | 1102407018 | Region XI (Davao Region) | Davao del Sur | Magsaysay | Tacul | 6.8079 | 125.0861 | R | 3480 | 3.4 | 1024 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.47 | 16.55 | Tier 2B: Moderate GIDA Inclusion | 60.29 | 60.29 | 49.56 | 54.92 | F - Nearest node and line over 5 km | 9.47 | 16.55 | Node: MYD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2574
3 | 575 | 2575 | 1381100154 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 154 | 14.5579 | 121.2047 | U | 1065 | 3.46 | 308 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.72 | 40.72 | 69.13 | 54.92 | C - Line within 0.5 km; node over 1 km | 1.32 | 0.24 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2575
3 | 576 | 2576 | 1705315011 | MIMAROPA Region | Palawan | Narra | Ipilan | 9.1735 | 118.0939 | R | 2150 | 3.9 | 551 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 94.34 | 96.62 | Tier 1B: High GIDA Priority | 40.34 | 40.34 | 69.49 | 54.92 | F - Nearest node and line over 5 km | 94.34 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2576
3 | 577 | 2577 | 0600409008 | Region VI (Western Visayas) | Aklan | Libacao | Casit-an | 11.4719 | 122.308 | R | 360 | 3.9 | 92 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12 | 11.94 | Tier 1B: High GIDA Priority | 38.44 | 38.44 | 71.41 | 54.92 | F - Nearest node and line over 5 km | 12 | 11.92 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2577
3 | 578 | 2578 | 1108205023 | Region XI (Davao Region) | Davao de Oro | Maragusan | Tandik | 7.4132 | 126.0917 | R | 770 | 3.7 | 208 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.74 | 21.66 | Tier 1B: High GIDA Priority | 33.18 | 33.18 | 76.66 | 54.92 | F - Nearest node and line over 5 km | 26.74 | 21.65 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2578
3 | 579 | 2579 | 0403406015 | Region IV-A (CALABARZON) | Laguna | Calauan | Prinza | 14.1424 | 121.3168 | R | 3113 | 3.3 | 943 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.43 | Tier 2A: High Commercial ROI | 70.74 | 70.74 | 39.08 | 54.91 | B - Node 0.5-1 km | 0.51 | 0.26 | Line: AE SPO001 TO CLL001-NEW | Survey short node lateral; confirm port/fiber capacity, access and route. | 2579
3 | 580 | 2580 | 0403419011 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Pinagsanjan | 14.2671 | 121.4577 | U | 5628 | 3.3 | 1705 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 64.48 | 64.48 | 45.33 | 54.91 | D - Other node or line within 3 km | 1.08 | 0.65 | Line: SNL001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2580
3 | 581 | 2581 | 1108205013 | Region XI (Davao Region) | Davao de Oro | Maragusan | Magcagong | 7.3257 | 126.0999 | R | 3489 | 3.7 | 943 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.01 | 26.63 | Tier 1B: High GIDA Priority | 51.04 | 51.04 | 58.77 | 54.91 | F - Nearest node and line over 5 km | 27.01 | 26.62 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2581
3 | 582 | 2582 | 0205706003 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Dissimungal | 16.176 | 121.7657 | R | 2074 | 3.9 | 532 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.88 | 0.04 | Tier 1B: High GIDA Priority | 50.06 | 50.06 | 59.77 | 54.91 | C - Line within 0.5 km; node over 1 km | 10.88 | 0.02 | Line: NAGTIPUNAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2582
3 | 583 | 2583 | 1381100003 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 3 | 14.5456 | 121.01 | U | 822 | 3.91 | 210 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.49 | 0.26 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.79 | 39.79 | 70.02 | 54.91 | A - Node within 0.5 km | 0.49 | 0.17 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2583
3 | 584 | 2584 | 0804802004 | Region VIII (Eastern Visayas) | Northern Samar | Biri | Kauswagan | 12.6709 | 124.3914 | R | 772 | 4.3 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.43 | 28.73 | Tier 1B: High GIDA Priority | 37.93 | 37.93 | 71.88 | 54.91 | F - Nearest node and line over 5 km | 29.43 | 29.92 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2584
3 | 585 | 2585 | 0105526013 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guiguilonen | 16.0668 | 120.3985 | U | 3480 | 3.6 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 63.75 | 63.75 | 46.05 | 54.9 | A - Node within 0.5 km | 0.42 | 0.68 | Node: MDP001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2585
3 | 586 | 2586 | 0401029027 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 3 | 13.8851 | 120.9085 | R | 731 | 3.6 | 203 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 1.26 | Tier 1B: High GIDA Priority | 49.99 | 49.99 | 59.8 | 54.9 | D - Other node or line within 3 km | 1.38 | 1.22 | Line: TUY - STA. TERESITA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2586
3 | 587 | 2587 | 1108209026 | Region XI (Davao Region) | Davao de Oro | Nabunturan | Tagnocon | 7.5149 | 126.0365 | R | 2988 | 3.7 | 808 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.62 | 12.5 | Tier 1B: High GIDA Priority | 48.06 | 48.06 | 61.74 | 54.9 | F - Nearest node and line over 5 km | 24.62 | 12.5 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2587
3 | 588 | 2588 | 1381100137 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 137 | 14.5334 | 120.8259 | U | 2349 | 3.38 | 694 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.31 | 12.99 | Tier 1B: High GIDA Priority | 39.78 | 39.78 | 70.02 | 54.9 | F - Nearest node and line over 5 km | 9.31 | 12.98 | Node: CVC001 -TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2588
3 | 589 | 2589 | 1906614013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Alu-Kabingaan | 17.252 | 122.2332 | R | 2105 | 6 | 351 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.65 | Tier 1B: High GIDA Priority | 38.24 | 38.24 | 71.55 | 54.9 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2589
3 | 590 | 2590 | 0402106062 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc III | 14.2918 | 120.9747 | U | 14535 | 3.4 | 4275 | 1282 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.95 | 1.68 | Tier 2A: High Commercial ROI | 70.9 | 70.9 | 38.89 | 54.89 | D - Other node or line within 3 km | 1.95 | 1.71 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2590
3 | 591 | 2591 | 0402123012 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Fiorello Calimag | 14.3012 | 121.0033 | R | 2756 | 3.4 | 811 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 4.91 | Tier 2B: Moderate GIDA Inclusion | 61.9 | 61.9 | 47.88 | 54.89 | D - Other node or line within 3 km | 2.09 | 4.81 | Node: MAC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2591
3 | 592 | 2592 | 0405622089 | Region IV-A (CALABARZON) | Quezon | Lopez | Villa Aurora | 13.8242 | 122.3685 | R | 820 | 3.8 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.41 | 0.26 | Tier 1B: High GIDA Priority | 40.08 | 40.08 | 69.71 | 54.89 | C - Line within 0.5 km; node over 1 km | 12.41 | 0.1 | Line: AE LZQ001 TO SNQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2592
3 | 593 | 2593 | 0907333012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Sebuguey | 7.8855 | 123.1084 | R | 776 | 3.9 | 199 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.28 | 11.6 | Tier 1B: High GIDA Priority | 38.22 | 38.22 | 71.55 | 54.89 | F - Nearest node and line over 5 km | 18.28 | 11.58 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2593
3 | 594 | 2594 | 1380601097 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 97 | 14.2602 | 121.9604 | U | 3656 | 4.91 | 744 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.54 | 29.1 | Tier 1B: High GIDA Priority | 35.84 | 35.84 | 73.95 | 54.89 | F - Nearest node and line over 5 km | 27.54 | 29.1 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2594
3 | 595 | 2595 | 0405803001 | Region IV-A (CALABARZON) | Rizal | Baras | Evangelista | 14.517 | 121.2766 | R | 4064 | 3.6 | 1129 | 339 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.03 | 0.06 | Tier 2A: High Commercial ROI | 76.88 | 76.88 | 32.89 | 54.88 | A - Node within 0.5 km | 0.03 | 0.06 | Node: BSR002 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2595
3 | 596 | 2596 | 0301402007 | Region III (Central Luzon) | Bulacan | Balagtas | Panginay | 14.8186 | 120.8958 | U | 14625 | 3.5 | 4179 | 1254 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.72 | 0.76 | Tier 2B: Moderate GIDA Inclusion | 69.63 | 69.63 | 40.12 | 54.88 | D - Other node or line within 3 km | 2.72 | 0.74 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2596
3 | 597 | 2597 | 0604518010 | Region VI (Western Visayas) | Negros Occidental | Manapla | San Pablo | 10.8815 | 123.1484 | U | 9203 | 3.7 | 2487 | 746 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.9 | 6.48 | Tier 2B: Moderate GIDA Inclusion | 59.64 | 59.64 | 50.12 | 54.88 | F - Nearest node and line over 5 km | 7.9 | 6.48 | Line: VICTORIAS(MANAPLA) - ESCALANTE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2597
3 | 598 | 2598 | 0201528029 | Region II (Cagayan Valley) | Cagayan | Tuao | Taribubu | 17.6043 | 121.5091 | R | 1697 | 3.9 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.39 | 8.35 | Tier 1B: High GIDA Priority | 47.66 | 47.66 | 62.1 | 54.88 | F - Nearest node and line over 5 km | 7.39 | 8.23 | Node: TUC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2598
3 | 599 | 2599 | 1380606228 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 621 | 13.6953 | 121.132 | U | 2070 | 4.07 | 509 | 153 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.68 | 10.11 | Tier 1B: High GIDA Priority | 39.32 | 39.32 | 70.45 | 54.88 | E - Nearest node or line 3-5 km | 3.68 | 10.11 | Node: BCY007-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2599
3 | 600 | 2600 | 1380601001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 1 | 13.1682 | 123.109 | U | 3119 | 3.92 | 796 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.75 | 34.57 | Tier 1B: High GIDA Priority | 37.24 | 37.24 | 72.53 | 54.88 | F - Nearest node and line over 5 km | 20.75 | 34.56 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2600
3 | 601 | 2601 | 1606807002 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Babuyan | 9.3466 | 125.9 | R | 768 | 4.1 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.84 | 4.47 | Tier 1B: High GIDA Priority | 47.71 | 47.71 | 62.03 | 54.87 | E - Nearest node or line 3-5 km | 5.84 | 4.46 | Line: SURIGAO - CARASCAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2601
3 | 602 | 2602 | 0504103024 | Region V (Bicol Region) | Masbate | Balud | Sampad | 11.9871 | 123.2123 | R | 503 | 4.1 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.68 | 10.74 | Tier 1B: High GIDA Priority | 45.04 | 45.04 | 64.7 | 54.87 | F - Nearest node and line over 5 km | 9.68 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2602
3 | 603 | 2603 | 0405603031 | Region IV-A (CALABARZON) | Quezon | Atimonan | San Andres Bundok | 13.9527 | 121.8657 | R | 283 | 3.8 | 74 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.76 | 4.13 | Tier 1B: High GIDA Priority | 39.37 | 39.37 | 70.38 | 54.87 | E - Nearest node or line 3-5 km | 6.76 | 4.13 | Line: LCQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2603
3 | 604 | 2604 | 1408102004 | Cordillera Administrative Region (CAR) | Apayao | Conner | Calafug | 17.7813 | 121.3271 | R | 1069 | 4.2 | 255 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 0.32 | Tier 1B: High GIDA Priority | 51.33 | 51.33 | 58.39 | 54.86 | C - Line within 0.5 km; node over 1 km | 1.76 | 0.19 | Line: Tabuk-Conner | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2604
3 | 605 | 2605 | 1906614016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kamaunggi | 17.2556 | 122.2297 | R | 2069 | 6 | 345 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 38.16 | 38.16 | 71.56 | 54.86 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2605
3 | 606 | 2606 | 1408104009 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Kumao | 18.1027 | 121.1568 | R | 585 | 4.2 | 139 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.59 | 16.63 | Tier 1B: High GIDA Priority | 37.73 | 37.73 | 71.99 | 54.86 | F - Nearest node and line over 5 km | 9.59 | 38.19 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2606
3 | 607 | 2607 | 0403423009 | Region IV-A (CALABARZON) | Laguna | Rizal | Tala | 14.1024 | 121.3911 | R | 2885 | 3.6 | 801 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.91 | Tier 2A: High Commercial ROI | 71.62 | 71.62 | 38.08 | 54.85 | B - Node 0.5-1 km | 0.92 | 0.91 | Line: SAN PABLO - LUCBAN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 2607
3 | 608 | 2608 | 1001311009 | Region X (Northern Mindanao) | Bukidnon | Libona | Palabucan | 8.3989 | 124.7815 | R | 1829 | 3.8 | 481 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.15 | 4.48 | Tier 1B: High GIDA Priority | 50.19 | 50.19 | 59.51 | 54.85 | E - Nearest node or line 3-5 km | 6.15 | 4.48 | Line: CAGAYAN DE ORO - MALAYBALAY | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2608
3 | 609 | 2609 | 0504101034 | Region V (Bicol Region) | Masbate | Aroroy | San Isidro | 12.4291 | 123.3667 | R | 1177 | 4.1 | 287 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.69 | 12.27 | Tier 1B: High GIDA Priority | 43.46 | 43.46 | 66.25 | 54.85 | F - Nearest node and line over 5 km | 9.69 | 24.38 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2609
3 | 610 | 2610 | 1381100016 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 16 | 14.5602 | 121.0204 | U | 478 | 3.68 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.34 | 0.09 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.11 | 38.11 | 71.6 | 54.85 | A - Node within 0.5 km | 0.34 | 0.85 | Node: MKT007 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2610
3 | 611 | 2611 | 1400113004 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Domenglay | 17.6271 | 120.9464 | R | 443 | 3.8 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.91 | 29.88 | Tier 1B: High GIDA Priority | 34.28 | 34.28 | 75.41 | 54.85 | F - Nearest node and line over 5 km | 29.91 | 29.86 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2611
3 | 612 | 2612 | 0702241014 | Region VII (Central Visayas) | Cebu | San Fernando | Panadtaran | 10.1514 | 123.6988 | U | 6360 | 3.8 | 1674 | 502 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 66.54 | 66.54 | 43.13 | 54.84 | C - Line within 0.5 km; node over 1 km | 1.58 | 0.14 | Line: 216f | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2612
3 | 613 | 2613 | 0301418010 | Region III (Central Luzon) | Bulacan | Pulilan | Longos | 14.8967 | 120.8648 | U | 6080 | 3.5 | 1737 | 521 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 63.79 | 63.79 | 45.9 | 54.84 | C - Line within 0.5 km; node over 1 km | 1.64 | 0.11 | Line: CALUMPIT - BALIUAG LINK | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2613
3 | 614 | 2614 | 1381100026 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 26 | 14.5589 | 121.0359 | U | 944 | 3.32 | 284 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.35 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.75 | 40.75 | 68.94 | 54.84 | B - Node 0.5-1 km | 0.97 | 0.86 | Line: UG 144C via V-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 2614
3 | 615 | 2615 | 1705110039 | MIMAROPA Region | Occidental Mindoro | San Jose | San Roque | 12.3586 | 121.0566 | U | 16580 | 3.9 | 4251 | 1275 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.23 | 0.3 | Tier 2A: High Commercial ROI | 72.8 | 72.8 | 36.85 | 54.83 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.3 | Line: ROXAS - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2615
3 | 616 | 2616 | 0306910001 | Region III (Central Luzon) | Tarlac | Paniqui | Abogado | 15.6708 | 120.5917 | R | 4810 | 3.9 | 1233 | 370 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.65 | Tier 2A: High Commercial ROI | 71.71 | 71.71 | 37.95 | 54.83 | B - Node 0.5-1 km | 0.58 | 0.69 | Node: PQT001 - TYPE 4 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2616
3 | 617 | 2617 | 0203135011 | Region II (Cagayan Valley) | Isabela | City of Santiago | Calaocan | 16.6822 | 121.5493 | U | 6463 | 3.8 | 1701 | 510 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 62.27 | 62.27 | 47.4 | 54.83 | C - Line within 0.5 km; node over 1 km | 2.59 | 0.26 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2617
3 | 618 | 2618 | 0301420049 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael I | 14.8381 | 121.0965 | U | 3514 | 3.5 | 1004 | 301 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 5.72 | Tier 2B: Moderate GIDA Inclusion | 57.46 | 57.46 | 52.21 | 54.83 | D - Other node or line within 3 km | 2.02 | 5.47 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2618
3 | 619 | 2619 | 1908811001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Gen. S.K. Pendatun | Badak | 17.255 | 122.2291 | R | 5081 | 4.7 | 1081 | 324 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 49.52 | 49.52 | 60.14 | 54.83 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2619
3 | 620 | 2620 | 1108604002 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Buca | 6.4618 | 125.4786 | R | 2611 | 3.6 | 725 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.25 | 14.52 | Tier 1B: High GIDA Priority | 48.49 | 48.49 | 61.16 | 54.83 | F - Nearest node and line over 5 km | 16.25 | 14.47 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2620
3 | 621 | 2621 | 0403415011 | Region IV-A (CALABARZON) | Laguna | Magdalena | Cigaras | 14.2239 | 121.4301 | R | 3939 | 3.3 | 1194 | 358 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.82 | 0.16 | Tier 2A: High Commercial ROI | 72.21 | 72.21 | 37.44 | 54.82 | C - Line within 0.5 km; node over 1 km | 2.82 | 0.12 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2621
3 | 622 | 2622 | 0702234014 | Region VII (Central Visayas) | Cebu | City of Naga | Langtad | 10.1871 | 123.7368 | U | 7238 | 3.8 | 1905 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.19 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 63.86 | 63.86 | 45.77 | 54.82 | C - Line within 0.5 km; node over 1 km | 4.19 | 0.03 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2622
3 | 623 | 2623 | 0804824005 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Curry | 12.3284 | 124.678 | R | 892 | 4.3 | 207 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 70.82 | 70.81 | Tier 1B: High GIDA Priority | 37.83 | 37.83 | 71.82 | 54.82 | F - Nearest node and line over 5 km | 70.82 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2623
3 | 624 | 2624 | 0704601001 | Region VII (Central Visayas) | Negros Oriental | Amlan | Bio-os | 9.4707 | 123.1956 | R | 4275 | 3.8 | 1125 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 75.06 | 75.06 | 34.55 | 54.8 | C - Line within 0.5 km; node over 1 km | 3.05 | 0.17 | Line: KABANGKALAN - BACONG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2624
3 | 625 | 2625 | 0403422014 | Region IV-A (CALABARZON) | Laguna | Pila | San Antonio | 14.2179 | 121.3592 | R | 4205 | 3.3 | 1274 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.07 | Tier 2A: High Commercial ROI | 70.21 | 70.21 | 39.38 | 54.8 | C - Line within 0.5 km; node over 1 km | 1.32 | 0.05 | Line: CLB001 TO SCL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2625
3 | 626 | 2626 | 0405630022 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 4 Parang | 13.9714 | 121.6911 | R | 2057 | 3.8 | 541 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 59.9 | 59.9 | 49.69 | 54.8 | B - Node 0.5-1 km | 0.98 | 0.2 | Line: LBQ001 TO GCQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2626
3 | 627 | 2627 | 0501711041 | Region V (Bicol Region) | Camarines Sur | Caramoan | San Roque | 13.7525 | 123.8437 | R | 772 | 4.2 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.22 | 35.81 | Tier 1B: High GIDA Priority | 46.38 | 46.38 | 63.21 | 54.8 | E - Nearest node or line 3-5 km | 3.22 | 35.8 | Node: COC001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2627
3 | 628 | 2628 | 1381100136 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 136 | 14.431 | 121.139 | U | 2178 | 3.39 | 643 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.56 | 6.9 | Tier 1B: High GIDA Priority | 40.61 | 40.61 | 69 | 54.8 | F - Nearest node and line over 5 km | 7.56 | 6.9 | Line: TAYTAY TO SNL001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2628
3 | 629 | 2629 | 0401005070 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 23 | 13.7199 | 121.118 | U | 719 | 3.6 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 7.2 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.43 | 38.43 | 71.18 | 54.8 | D - Other node or line within 3 km | 1.66 | 7.2 | Node: BCY007-PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2629
3 | 630 | 2630 | 0403405035 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Palo-Alto | 14.1843 | 121.1073 | U | 20689 | 3.3 | 6269 | 1881 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.12 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 69.87 | 69.87 | 39.71 | 54.79 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.41 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2630
3 | 631 | 2631 | 0403417007 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Bambang | 14.1342 | 121.4057 | R | 2381 | 3.3 | 722 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 1.07 | Tier 2B: Moderate GIDA Inclusion | 64.7 | 64.7 | 44.88 | 54.79 | D - Other node or line within 3 km | 1.09 | 1.05 | Line: AE NGL001 TO SPO001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2631
3 | 632 | 2632 | 0405809006 | Region IV-A (CALABARZON) | Rizal | Morong | San Jose | 14.5239 | 121.2435 | R | 4110 | 3.6 | 1142 | 343 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.52 | 0.2 | Tier 2A: High Commercial ROI | 71.35 | 71.35 | 38.2 | 54.78 | B - Node 0.5-1 km | 0.52 | 0.2 | Line: TAYTAY TO SNL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2632
3 | 633 | 2633 | 0105503021 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Poblacion | 16.1602 | 119.9818 | U | 10961 | 3.6 | 3045 | 914 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 40.67 | 54.77 | D - Other node or line within 3 km | 1.02 | 0.57 | Line: SEGMENT 45 (ALAMINOS - BOLINAO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2633
3 | 634 | 2634 | 0403422017 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Sur | 14.2239 | 121.3657 | U | 6468 | 3.3 | 1960 | 588 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 64.57 | 64.57 | 44.97 | 54.77 | C - Line within 0.5 km; node over 1 km | 1.47 | 0.33 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2634
3 | 635 | 2635 | 0500511011 | Region V (Bicol Region) | Albay | Manito | Malobago | 13.0805 | 123.835 | R | 822 | 4.1 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.07 | 9.98 | Tier 1B: High GIDA Priority | 49.07 | 49.07 | 60.47 | 54.77 | F - Nearest node and line over 5 km | 6.07 | 9.91 | Node: MNT001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2635
3 | 636 | 2636 | 0600409004 | Region VI (Western Visayas) | Aklan | Libacao | Bonza | 11.4803 | 122.3303 | R | 431 | 3.9 | 111 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.86 | 9.78 | Tier 1B: High GIDA Priority | 40.35 | 40.35 | 69.2 | 54.77 | F - Nearest node and line over 5 km | 9.86 | 9.78 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2636
3 | 637 | 2637 | 1906614035 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Tulakan | 17.2557 | 122.2297 | R | 2038 | 6 | 340 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 37.98 | 37.98 | 71.55 | 54.77 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2637
3 | 638 | 2638 | 0806008008 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Dalosdoson | 11.6827 | 125.0723 | R | 333 | 4.1 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 49.85 | 52.73 | Tier 1B: High GIDA Priority | 36.74 | 36.74 | 72.79 | 54.77 | F - Nearest node and line over 5 km | 49.85 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2638
3 | 639 | 2639 | 0504111017 | Region V (Bicol Region) | Masbate | City of Masbate | Ibingay | 12.3725 | 123.6268 | U | 8138 | 4.1 | 1985 | 596 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 66.68 | 66.68 | 42.83 | 54.76 | D - Other node or line within 3 km | 1.98 | 1.82 | Line: MASBATE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2639
3 | 640 | 2640 | 0603019015 | Region VI (Western Visayas) | Iloilo | Estancia | Pa-on | 11.4741 | 123.1502 | R | 3195 | 3.8 | 841 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.13 | 4.4 | Tier 2B: Moderate GIDA Inclusion | 61.22 | 61.22 | 48.31 | 54.76 | E - Nearest node or line 3-5 km | 3.13 | 4.4 | Node: ECI001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2640
3 | 641 | 2641 | 0201505038 | Region II (Cagayan Valley) | Cagayan | Aparri | San Antonio | 18.3592 | 121.6407 | U | 4084 | 3.9 | 1047 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 10.9 | Tier 2B: Moderate GIDA Inclusion | 60.12 | 60.12 | 49.39 | 54.76 | B - Node 0.5-1 km | 0.59 | 10.88 | Node: ARC001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2641
3 | 642 | 2642 | 1381100193 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 193 | 14.6698 | 120.7948 | U | 7654 | 3.17 | 2416 | 725 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.85 | 15.84 | Tier 1B: High GIDA Priority | 45.6 | 45.6 | 63.91 | 54.76 | F - Nearest node and line over 5 km | 15.85 | 15.8 | Line: UG 288C via Y-Duct | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2642
3 | 643 | 2643 | 0300806008 | Region III (Central Luzon) | Bataan | Limay | Reformista | 14.5637 | 120.5955 | U | 5400 | 3.6 | 1500 | 450 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 63.81 | 63.81 | 45.69 | 54.75 | C - Line within 0.5 km; node over 1 km | 1.21 | 0.11 | Line: 36 CORE 3X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2643
3 | 644 | 2644 | 0304911060 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santa Veronica District | 15.663 | 120.7621 | U | 4221 | 3.5 | 1206 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 1.21 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 45.7 | 54.75 | B - Node 0.5-1 km | 0.75 | 0.8 | Node: GUN001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2644
3 | 645 | 2645 | 0105517022 | Region I (Ilocos Region) | Pangasinan | Calasiao | San Miguel | 16.0117 | 120.3589 | U | 7809 | 3.6 | 2169 | 651 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.09 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 63.06 | 63.06 | 46.44 | 54.75 | C - Line within 0.5 km; node over 1 km | 3.09 | 0.13 | Line: CALASIAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2645
3 | 646 | 2646 | 0405622079 | Region IV-A (CALABARZON) | Quezon | Lopez | Santo Niño Ilaya | 13.7715 | 122.3359 | R | 1087 | 3.8 | 286 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.04 | 6.19 | Tier 1B: High GIDA Priority | 40.53 | 40.53 | 68.97 | 54.75 | F - Nearest node and line over 5 km | 10.04 | 6.15 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2646
3 | 647 | 2647 | 0804824002 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Bonifacio | 12.2735 | 124.6083 | R | 867 | 4.3 | 202 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.94 | 66.93 | Tier 1B: High GIDA Priority | 37.76 | 37.76 | 71.75 | 54.75 | F - Nearest node and line over 5 km | 66.94 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2647
3 | 648 | 2648 | 1004217003 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Lake Duminagat | 8.3251 | 123.6365 | R | 156 | 3.9 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.12 | 33.73 | Tier 1B: High GIDA Priority | 35.48 | 35.48 | 74.01 | 54.75 | F - Nearest node and line over 5 km | 36.12 | 33.73 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2648
3 | 649 | 2649 | 0403430009 | Region IV-A (CALABARZON) | Laguna | Victoria | San Francisco | 14.2119 | 121.3444 | U | 7217 | 3.3 | 2187 | 656 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.77 | Tier 2A: High Commercial ROI | 71.33 | 71.33 | 38.15 | 54.74 | B - Node 0.5-1 km | 0.63 | 0.75 | Node: VTL001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2649
3 | 650 | 2650 | 0301410016 | Region III (Central Luzon) | Bulacan | City of Malolos | Caingin | 14.8442 | 120.8045 | U | 7681 | 3.5 | 2195 | 658 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 1.46 | Tier 2B: Moderate GIDA Inclusion | 66.41 | 66.41 | 43.06 | 54.74 | B - Node 0.5-1 km | 0.94 | 1.55 | Node: MSB003 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2650
3 | 651 | 2651 | 0300809005 | Region III (Central Luzon) | Bataan | Orani | Paking-Carbonero | 14.797 | 120.5001 | R | 968 | 3.6 | 269 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.94 | 0.24 | Tier 1B: High GIDA Priority | 48.61 | 48.61 | 60.87 | 54.74 | C - Line within 0.5 km; node over 1 km | 3.94 | 0.24 | Line: Pipe Dinalupian to Orion | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2651
3 | 652 | 2652 | 1907004001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Bakong | 17.2558 | 122.2299 | R | 3352 | 5.8 | 578 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 44.17 | 44.17 | 65.31 | 54.74 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2652
3 | 653 | 2653 | 1004325014 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | San Jose | 8.9937 | 124.8888 | R | 3886 | 3.9 | 996 | 299 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.25 | Tier 2A: High Commercial ROI | 76.24 | 76.24 | 33.22 | 54.73 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.25 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2653
3 | 654 | 2654 | 1705323008 | MIMAROPA Region | Palawan | Rizal | Panalingaan | 8.7273 | 117.4521 | R | 4526 | 3.6 | 1257 | 377 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 180.22 | 182.48 | Tier 1B: High GIDA Priority | 51.88 | 51.88 | 57.59 | 54.73 | F - Nearest node and line over 5 km | 180.22 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2654
3 | 655 | 2655 | 0301409006 | Region III (Central Luzon) | Bulacan | Hagonoy | Pugad | 14.7679 | 120.7432 | R | 1710 | 3.5 | 489 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.98 | 10.37 | Tier 1B: High GIDA Priority | 48.53 | 48.53 | 60.94 | 54.73 | F - Nearest node and line over 5 km | 7.98 | 12.23 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2655
3 | 656 | 2656 | 1400112001 | Cordillera Administrative Region (CAR) | Abra | Langiden | Baac | 17.6011 | 120.5764 | R | 362 | 3.8 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.63 | 4.23 | Tier 1B: High GIDA Priority | 45.87 | 45.87 | 63.58 | 54.73 | E - Nearest node or line 3-5 km | 4.63 | 4.12 | Line: CABLE LAYED | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2656
3 | 657 | 2657 | 1400115002 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Binasaran | 17.5937 | 120.9637 | R | 174 | 3.8 | 46 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.39 | 32.36 | Tier 1B: High GIDA Priority | 34.1 | 34.1 | 75.35 | 54.73 | F - Nearest node and line over 5 km | 32.39 | 32.34 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2657
3 | 658 | 2658 | 0604530006 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Central Tabao | 10.4116 | 122.871 | R | 3643 | 3.7 | 985 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.33 | 1.39 | Tier 2B: Moderate GIDA Inclusion | 71.32 | 71.32 | 38.1 | 54.71 | D - Other node or line within 3 km | 4.33 | 1.37 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2658
3 | 659 | 2659 | 0102817009 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Davila | 18.4681 | 120.5784 | R | 4050 | 3.7 | 1095 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.28 | Tier 2A: High Commercial ROI | 70.38 | 70.38 | 39.04 | 54.71 | C - Line within 0.5 km; node over 1 km | 1.05 | 0.03 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2659
3 | 660 | 2660 | 0403421001 | Region IV-A (CALABARZON) | Laguna | Pangil | Balian | 14.3943 | 121.4749 | U | 7054 | 3.3 | 2138 | 641 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 69.2 | 69.2 | 40.22 | 54.71 | C - Line within 0.5 km; node over 1 km | 1.71 | 0.31 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2660
3 | 661 | 2661 | 0102815006 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Caunayan | 18.6118 | 120.8336 | R | 1552 | 3.7 | 419 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.78 | 1.71 | Tier 1B: High GIDA Priority | 51.59 | 51.59 | 57.83 | 54.71 | D - Other node or line within 3 km | 10.78 | 1.55 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2661
3 | 662 | 2662 | 1381100127 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 127 | 14.4861 | 121.1592 | U | 1770 | 3.79 | 467 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 2.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.81 | 39.81 | 69.62 | 54.71 | D - Other node or line within 3 km | 2.33 | 2.1 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2662
3 | 663 | 2663 | 1381100020 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 20 | 14.5396 | 121.0339 | U | 880 | 2.95 | 298 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 1.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.52 | 39.52 | 69.91 | 54.71 | D - Other node or line within 3 km | 1.89 | 1.28 | Line: Existing 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2663
3 | 664 | 2664 | 1380601151 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 151 | 13.471 | 120.9835 | U | 1725 | 4.49 | 384 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.41 | 1.04 | Tier 1B: High GIDA Priority | 38.84 | 38.84 | 70.58 | 54.71 | D - Other node or line within 3 km | 4.41 | 1.03 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2664
3 | 665 | 2665 | 0806008017 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Yabon | 11.6906 | 125.1073 | R | 434 | 4.1 | 106 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 51.43 | 54.23 | Tier 1B: High GIDA Priority | 36.73 | 36.73 | 72.69 | 54.71 | F - Nearest node and line over 5 km | 51.43 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2665
3 | 666 | 2666 | 0405808007 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Puray | 14.772 | 121.2051 | R | 3550 | 3.6 | 986 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.67 | 5.38 | Tier 2B: Moderate GIDA Inclusion | 60.67 | 60.67 | 48.74 | 54.7 | F - Nearest node and line over 5 km | 6.67 | 5.37 | Line: Aerial 216C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2666
3 | 667 | 2667 | 1380612018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 850 | 13.6767 | 120.7997 | U | 2655 | 4.07 | 652 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.34 | 22.05 | Tier 1B: High GIDA Priority | 37.67 | 37.67 | 71.72 | 54.7 | F - Nearest node and line over 5 km | 10.34 | 22.03 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2667
3 | 668 | 2668 | 1907007002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Baliungan | 14.4126 | 121.7866 | R | 1925 | 5.8 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.89 | 33.2 | Tier 1B: High GIDA Priority | 34.94 | 34.94 | 74.46 | 54.7 | F - Nearest node and line over 5 km | 19.89 | 33.2 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2668
3 | 669 | 2669 | 0403411006 | Region IV-A (CALABARZON) | Laguna | Los Baños | Bayog | 14.1909 | 121.2444 | U | 12730 | 3.3 | 3858 | 1157 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.33 | 1.33 | Tier 2A: High Commercial ROI | 70.65 | 70.65 | 38.73 | 54.69 | D - Other node or line within 3 km | 1.33 | 1.33 | Line: AE SPO001 TO LBL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2669
3 | 670 | 2670 | 0401011002 | Region IV-A (CALABARZON) | Batangas | Laurel | Balakilong | 14.0702 | 120.9335 | R | 4467 | 3.6 | 1241 | 372 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 2.89 | Tier 2B: Moderate GIDA Inclusion | 65.68 | 65.68 | 43.69 | 54.69 | D - Other node or line within 3 km | 1.87 | 2.86 | Node: LRB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2670
3 | 671 | 2671 | 0806008005 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Canano | 11.6845 | 125.0882 | R | 287 | 4.1 | 70 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.34 | 53.19 | Tier 1B: High GIDA Priority | 36.74 | 36.74 | 72.64 | 54.69 | F - Nearest node and line over 5 km | 50.34 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2671
3 | 672 | 2672 | 0403419014 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sabang | 14.2654 | 121.4425 | R | 4090 | 3.3 | 1239 | 372 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.15 | Tier 2A: High Commercial ROI | 70.26 | 70.26 | 39.1 | 54.68 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.15 | Line: SNL001 TO SCL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2672
3 | 673 | 2673 | 0301404002 | Region III (Central Luzon) | Bulacan | Bocaue | Bagumbayan | 14.8069 | 120.9313 | R | 4038 | 3.5 | 1154 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.76 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 41.54 | 54.68 | D - Other node or line within 3 km | 2.81 | 0.99 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2673
3 | 674 | 2674 | 0301420055 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz III | 14.856 | 121.0515 | R | 3166 | 3.5 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 3.01 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 45.02 | 54.68 | D - Other node or line within 3 km | 2.2 | 5.56 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2674
3 | 675 | 2675 | 0403426017 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay IV | 14.2608 | 121.419 | U | 1071 | 3.3 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.13 | 0.76 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 44.65 | 44.65 | 64.71 | 54.68 | D - Other node or line within 3 km | 2.13 | 0.76 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2675
3 | 676 | 2676 | 1600301016 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Poblacion | 8.7144 | 125.7519 | U | 16880 | 3.9 | 4328 | 1298 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.51 | 0.33 | Tier 2A: High Commercial ROI | 74.65 | 74.65 | 34.7 | 54.67 | B - Node 0.5-1 km | 0.51 | 0.13 | Line: TRENTO - BUENAVISTA CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 2676
3 | 677 | 2677 | 0600411015 | Region VI (Western Visayas) | Aklan | Makato | Poblacion | 11.7125 | 122.29 | R | 3445 | 3.9 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.49 | Tier 2A: High Commercial ROI | 74.33 | 74.33 | 35.02 | 54.67 | B - Node 0.5-1 km | 0.54 | 7.51 | Node: MOK001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2677
3 | 678 | 2678 | 0300810020 | Region III (Central Luzon) | Bataan | Orion | Puting Buhangin | 14.585 | 120.5889 | R | 3189 | 3.6 | 886 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 68.62 | 68.62 | 40.71 | 54.67 | C - Line within 0.5 km; node over 1 km | 1.38 | 0.06 | Line: 36 CORE 3X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2678
3 | 679 | 2679 | 0103314052 | Region I (Ilocos Region) | La Union | City of San Fernando | San Francisco | 16.6176 | 120.3966 | R | 3665 | 3.7 | 991 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.65 | 8.36 | Tier 2B: Moderate GIDA Inclusion | 60.91 | 60.91 | 48.43 | 54.67 | F - Nearest node and line over 5 km | 6.65 | 8.36 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2679
3 | 680 | 2680 | 1380601138 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 138 | 12.3716 | 120.5158 | U | 3217 | 3.96 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.19 | 58.94 | Tier 1B: High GIDA Priority | 37.67 | 37.67 | 71.66 | 54.67 | F - Nearest node and line over 5 km | 50.19 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2680
3 | 681 | 2681 | 0806008004 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Cabalagnan | 11.7077 | 125.099 | R | 404 | 4.1 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.1 | 55.93 | Tier 1B: High GIDA Priority | 36.72 | 36.72 | 72.62 | 54.67 | F - Nearest node and line over 5 km | 53.1 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2681
3 | 682 | 2682 | 1907006006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bintawlan | 17.2558 | 122.2299 | R | 1493 | 5.8 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 31.3 | 31.3 | 78.03 | 54.67 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2682
3 | 683 | 2683 | 1102507028 | Region XI (Davao Region) | Davao Oriental | Lupon | Poblacion | 6.8879 | 126.0134 | U | 17775 | 3.6 | 4938 | 1481 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.94 | 0.89 | Tier 2A: High Commercial ROI | 75.09 | 75.09 | 34.24 | 54.66 | B - Node 0.5-1 km | 0.94 | 0.89 | Line: PANTUKAN - MATI SEGMENT 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2683
3 | 684 | 2684 | 0306906036 | Region III (Central Luzon) | Tarlac | Gerona | San Antonio | 15.5983 | 120.6051 | R | 3323 | 3.9 | 852 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.11 | 0.12 | Tier 2A: High Commercial ROI | 70.24 | 70.24 | 39.09 | 54.66 | A - Node within 0.5 km | 0.11 | 0.09 | Line: GERONA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2684
3 | 685 | 2685 | 0304904015 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Gregorio | 15.2551 | 120.86 | R | 2344 | 3.5 | 670 | 201 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 63.26 | 63.26 | 46.06 | 54.66 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.14 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2685
3 | 686 | 2686 | 1705323004 | MIMAROPA Region | Palawan | Rizal | Canipaan | 8.5743 | 117.2658 | R | 2842 | 3.6 | 789 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 206.83 | 209.1 | Tier 1B: High GIDA Priority | 46.34 | 46.34 | 62.97 | 54.66 | F - Nearest node and line over 5 km | 206.83 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2686
3 | 687 | 2687 | 1400115001 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Bayabas | 17.6392 | 120.9884 | R | 218 | 3.8 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.2 | 34.18 | Tier 1B: High GIDA Priority | 34.01 | 34.01 | 75.31 | 54.66 | F - Nearest node and line over 5 km | 34.2 | 34.16 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2687
3 | 688 | 2688 | 0301403025 | Region III (Central Luzon) | Bulacan | Baliuag | Tarcan | 14.9325 | 120.8792 | U | 9208 | 3.5 | 2631 | 789 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.96 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 66 | 66 | 43.3 | 54.65 | C - Line within 0.5 km; node over 1 km | 1.96 | 0.13 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2688
3 | 689 | 2689 | 0402118041 | Region IV-A (CALABARZON) | Cavite | Silang | Sabutan | 14.2335 | 120.9791 | U | 8306 | 3.4 | 2443 | 733 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.98 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 61.42 | 61.42 | 47.89 | 54.65 | C - Line within 0.5 km; node over 1 km | 5.98 | 0.31 | Line: SILANG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2689
3 | 690 | 2690 | 0301420052 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael V | 14.8048 | 121.1025 | R | 2973 | 3.5 | 849 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.49 | 3.47 | Tier 2B: Moderate GIDA Inclusion | 61.19 | 61.19 | 48.1 | 54.65 | E - Nearest node or line 3-5 km | 3.49 | 3.3 | Line: STA MARIA TO BRGY 181 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2690
3 | 691 | 2691 | 0401012015 | Region IV-A (CALABARZON) | Batangas | Lemery | Maguihan | 13.9273 | 120.8854 | R | 2178 | 3.6 | 605 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.36 | 1.74 | Tier 2B: Moderate GIDA Inclusion | 56.54 | 56.54 | 52.76 | 54.65 | D - Other node or line within 3 km | 5.36 | 1.72 | Line: TUY - STA. TERESITA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2691
3 | 692 | 2692 | 1401108003 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Boklaoan | 16.6236 | 120.6583 | R | 478 | 3.5 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.75 | 9.74 | Tier 1B: High GIDA Priority | 44.33 | 44.33 | 64.97 | 54.65 | F - Nearest node and line over 5 km | 7.75 | 9.64 | Node: KPB001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2692
3 | 693 | 2693 | 1206505013 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Kalamansig | Obial | 6.5789 | 124.0873 | R | 2464 | 3.8 | 648 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.91 | 65.9 | Tier 1B: High GIDA Priority | 42.89 | 42.89 | 66.41 | 54.65 | F - Nearest node and line over 5 km | 65.91 | 999999 | Node: TKC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2693
3 | 694 | 2694 | 1102319011 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Mankilam | 7.463 | 125.7776 | U | 42039 | 3.7 | 11362 | 3409 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 4.67 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 62.85 | 62.85 | 46.42 | 54.64 | E - Nearest node or line 3-5 km | 4.67 | 3.84 | Line: DAVAO CITY - TRENTO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2694
3 | 695 | 2695 | 0806009018 | Region VIII (Eastern Visayas) | Samar | Jiabong | Malino | 11.845 | 124.9822 | R | 870 | 4.1 | 212 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 67.35 | 68.4 | Tier 1B: High GIDA Priority | 37.98 | 37.98 | 71.3 | 54.64 | F - Nearest node and line over 5 km | 67.35 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2695
3 | 696 | 2696 | 1004217010 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Petianan | 8.2704 | 123.5786 | R | 871 | 3.9 | 223 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.06 | 33.7 | Tier 1B: High GIDA Priority | 37.45 | 37.45 | 71.84 | 54.64 | F - Nearest node and line over 5 km | 35.06 | 33.7 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2696
3 | 697 | 2697 | 1400115010 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Pacgued | 17.5921 | 121.0112 | R | 283 | 3.8 | 74 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.14 | 30.19 | Tier 1B: High GIDA Priority | 33.96 | 33.96 | 75.32 | 54.64 | F - Nearest node and line over 5 km | 35.14 | 30.03 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2697
3 | 698 | 2698 | 0300810024 | Region III (Central Luzon) | Bataan | Orion | Santo Domingo | 14.6338 | 120.5729 | R | 4590 | 3.6 | 1275 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 69.09 | 69.09 | 40.18 | 54.63 | C - Line within 0.5 km; node over 1 km | 2.15 | 0.08 | Line: Pipe 2 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2698
3 | 699 | 2699 | 0702215007 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Norte | 10.5766 | 124.0181 | R | 4807 | 3.8 | 1265 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 0.09 | Tier 2A: High Commercial ROI | 75.89 | 75.89 | 33.34 | 54.62 | A - Node within 0.5 km | 0.1 | 0.08 | Line: UPLINK 2 CRM001- DOC001 via AE BACKBONE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2699
3 | 700 | 2700 | 0600407005 | Region VI (Western Visayas) | Aklan | Kalibo | Buswang New | 11.7108 | 122.3753 | U | 11732 | 3.9 | 3008 | 902 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 0.9 | Tier 2B: Moderate GIDA Inclusion | 69.65 | 69.65 | 39.58 | 54.62 | D - Other node or line within 3 km | 1.74 | 0.89 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2700
3 | 701 | 2701 | 0401018003 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | District III | 13.9815 | 121.1088 | R | 3485 | 3.6 | 968 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 4.65 | Tier 2B: Moderate GIDA Inclusion | 68.03 | 68.03 | 41.21 | 54.62 | D - Other node or line within 3 km | 2.8 | 4.64 | Node: MKB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2701
3 | 702 | 2702 | 0301406012 | Region III (Central Luzon) | Bulacan | Bustos | Talampas | 14.9312 | 120.9068 | R | 3802 | 3.5 | 1086 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.69 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 67.77 | 67.77 | 41.46 | 54.62 | C - Line within 0.5 km; node over 1 km | 2.69 | 0.05 | Line: BUSTOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2702
3 | 703 | 2703 | 0301405003 | Region III (Central Luzon) | Bulacan | Bulacan | Bambang | 14.7761 | 120.8819 | U | 14902 | 3.5 | 4258 | 1277 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.26 | 5.17 | Tier 2B: Moderate GIDA Inclusion | 66.99 | 66.99 | 42.24 | 54.62 | D - Other node or line within 3 km | 2.26 | 5.17 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2703
3 | 704 | 2704 | 0301420039 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan IV | 14.8474 | 121.0745 | U | 4985 | 3.5 | 1424 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 3.92 | Tier 2B: Moderate GIDA Inclusion | 61.1 | 61.1 | 48.14 | 54.62 | B - Node 0.5-1 km | 0.68 | 5.93 | Node: SJD002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2704
3 | 705 | 2705 | 0405628028 | Region IV-A (CALABARZON) | Quezon | Mulanay | Sagongon | 13.5216 | 122.435 | R | 397 | 3.8 | 104 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.38 | 3.46 | Tier 1B: High GIDA Priority | 40.68 | 40.68 | 68.56 | 54.62 | E - Nearest node or line 3-5 km | 4.38 | 3.36 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2705
3 | 706 | 2706 | 1380612015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 847 | 14.1929 | 121.8919 | U | 3132 | 3.71 | 845 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.67 | 21.44 | Tier 1B: High GIDA Priority | 38.54 | 38.54 | 70.69 | 54.62 | F - Nearest node and line over 5 km | 18.67 | 21.43 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2706
3 | 707 | 2707 | 0300801011 | Region III (Central Luzon) | Bataan | Abucay | Wawa | 14.7214 | 120.5415 | R | 4432 | 3.6 | 1231 | 369 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.08 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 66.68 | 66.68 | 42.54 | 54.61 | D - Other node or line within 3 km | 4.08 | 0.61 | Line: 60 CORE 5X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2707
3 | 708 | 2708 | 0105512015 | Region I (Ilocos Region) | Pangasinan | Binalonan | Poblacion | 16.0529 | 120.5892 | U | 7412 | 3.6 | 2059 | 618 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.75 | Tier 2B: Moderate GIDA Inclusion | 65.81 | 65.81 | 43.4 | 54.61 | D - Other node or line within 3 km | 1.05 | 0.75 | Line: BINALONAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2708
3 | 709 | 2709 | 0907313010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Linokmadalum | 7.6576 | 123.1454 | R | 918 | 3.9 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.79 | 10.46 | Tier 1B: High GIDA Priority | 37.41 | 37.41 | 71.82 | 54.61 | F - Nearest node and line over 5 km | 12.79 | 10.45 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2709
3 | 710 | 2710 | 1903639010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Minimao | 17.2546 | 122.2286 | R | 1522 | 5.7 | 267 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.38 | 34.26 | Tier 1B: High GIDA Priority | 36.08 | 36.08 | 73.14 | 54.61 | F - Nearest node and line over 5 km | 29.38 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2710
3 | 711 | 2711 | 0401001022 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Subic Ilaya | 13.9511 | 120.9417 | R | 3767 | 3.6 | 1046 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 6.31 | Tier 2B: Moderate GIDA Inclusion | 69.81 | 69.81 | 39.4 | 54.6 | D - Other node or line within 3 km | 1.74 | 6.3 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2711
3 | 712 | 2712 | 0401003046 | Region IV-A (CALABARZON) | Batangas | Balayan | San Piro | 13.917 | 120.7034 | R | 3895 | 3.6 | 1082 | 325 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.97 | 3.47 | Tier 2B: Moderate GIDA Inclusion | 62.61 | 62.61 | 46.59 | 54.6 | E - Nearest node or line 3-5 km | 3.97 | 3.47 | Line: UG NSB001 TO BYB001 TO LYB001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2712
3 | 713 | 2713 | 0504101026 | Region V (Bicol Region) | Masbate | Aroroy | Matongog | 12.5708 | 123.2449 | R | 1360 | 4.1 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18 | 21.53 | Tier 1B: High GIDA Priority | 39.12 | 39.12 | 70.08 | 54.6 | F - Nearest node and line over 5 km | 18 | 44.2 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2713
3 | 714 | 2714 | 0806409009 | Region VIII (Eastern Visayas) | Southern Leyte | Malitbog | Caraatan | 10.1141 | 124.9719 | R | 243 | 4.1 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.08 | 3.96 | Tier 1B: High GIDA Priority | 46.89 | 46.89 | 62.3 | 54.59 | F - Nearest node and line over 5 km | 15.76 | 8.14 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2714
3 | 715 | 2715 | 1403213016 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Guilayon | 17.4616 | 121.3395 | R | 901 | 4.3 | 210 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.39 | 6.28 | Tier 1B: High GIDA Priority | 39.77 | 39.77 | 69.4 | 54.59 | F - Nearest node and line over 5 km | 9.39 | 6.26 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2715
3 | 716 | 2716 | 0600612032 | Region VI (Western Visayas) | Antique | Patnongon | Villa Flores | 10.9274 | 122.0752 | R | 240 | 3.9 | 62 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.69 | 16.53 | Tier 1B: High GIDA Priority | 33.64 | 33.64 | 75.54 | 54.59 | F - Nearest node and line over 5 km | 23.69 | 16.24 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2716
3 | 717 | 2717 | 1907006010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Lookan | 15.4272 | 121.9779 | R | 1548 | 5.8 | 267 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.85 | 57.63 | Tier 1B: High GIDA Priority | 30.89 | 30.89 | 78.3 | 54.59 | F - Nearest node and line over 5 km | 57.85 | 61.92 | Node: BLA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2717
3 | 718 | 2718 | 0301418022 | Region III (Central Luzon) | Bulacan | Pulilan | Poblacion | 14.9041 | 120.8481 | U | 13958 | 3.5 | 3988 | 1196 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.34 | 0.26 | Tier 2A: High Commercial ROI | 73.09 | 73.09 | 36.06 | 54.58 | A - Node within 0.5 km | 0.34 | 0.26 | Line: 24 CORE (3X8) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2718
3 | 719 | 2719 | 0301423021 | Region III (Central Luzon) | Bulacan | Santa Maria | Sta. Clara | 14.8317 | 120.9844 | U | 12981 | 3.5 | 3709 | 1113 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.91 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 69.35 | 69.35 | 39.81 | 54.58 | D - Other node or line within 3 km | 1.91 | 0.98 | Line: STA. MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2719
3 | 720 | 2720 | 0403410024 | Region IV-A (CALABARZON) | Laguna | Liliw | Rizal | 14.1284 | 121.4375 | R | 754 | 3.3 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 56.03 | 56.03 | 53.12 | 54.58 | B - Node 0.5-1 km | 0.89 | 0.26 | Line: LILIW - LUCENA | Survey short node lateral; confirm port/fiber capacity, access and route. | 2720
3 | 721 | 2721 | 0702244011 | Region VII (Central Visayas) | Cebu | Santa Fe | Talisay | 11.1659 | 123.8052 | U | 3232 | 3.8 | 851 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.96 | 5.41 | Tier 1B: High GIDA Priority | 48.12 | 48.12 | 61.05 | 54.58 | F - Nearest node and line over 5 km | 17.36 | 15.45 | Line: 10742 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2721
3 | 722 | 2722 | 1381100057 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 57 | 14.552 | 121.0016 | U | 938 | 3.83 | 245 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 0.25 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.6 | 39.6 | 69.56 | 54.58 | C - Line within 0.5 km; node over 1 km | 1.07 | 0.25 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2722
3 | 723 | 2723 | 1400115004 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Dulao | 17.6131 | 121.0256 | R | 248 | 3.8 | 65 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.97 | 31.04 | Tier 1B: High GIDA Priority | 34.02 | 34.02 | 75.15 | 54.58 | F - Nearest node and line over 5 km | 33.97 | 32.39 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2723
3 | 724 | 2724 | 0304926035 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 3rd | 15.8115 | 120.9749 | U | 10737 | 3.5 | 3068 | 920 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 1.65 | Tier 2B: Moderate GIDA Inclusion | 66.78 | 66.78 | 42.36 | 54.57 | D - Other node or line within 3 km | 2.33 | 1.65 | Line: LUPAO - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2724
3 | 725 | 2725 | 1705320010 | MIMAROPA Region | Palawan | Taytay | Cataban | 10.985 | 119.3967 | R | 1486 | 3.9 | 381 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.79 | 21.71 | Tier 1B: High GIDA Priority | 44.33 | 44.33 | 64.8 | 54.57 | F - Nearest node and line over 5 km | 9.79 | 21.53 | Node: ENW004 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2725
3 | 726 | 2726 | 1381100068 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 68 | 14.5151 | 121.0884 | U | 981 | 3.25 | 302 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 1.64 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.98 | 39.98 | 69.15 | 54.57 | D - Other node or line within 3 km | 1.71 | 1.64 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2726
3 | 727 | 2727 | 1380606038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 432 | 11.6844 | 121.0661 | U | 3132 | 3.68 | 850 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 70.04 | 68.41 | Tier 1B: High GIDA Priority | 38.63 | 38.63 | 70.51 | 54.57 | F - Nearest node and line over 5 km | 70.04 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2727
3 | 728 | 2728 | 0301423011 | Region III (Central Luzon) | Bulacan | Santa Maria | Mag-asawang Sapa | 14.8789 | 120.9827 | U | 10851 | 3.5 | 3100 | 930 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.94 | 1.92 | Tier 2B: Moderate GIDA Inclusion | 67.46 | 67.46 | 41.65 | 54.56 | D - Other node or line within 3 km | 1.94 | 1.93 | Line: PB HH24-25 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2728
3 | 729 | 2729 | 0403411005 | Region IV-A (CALABARZON) | Laguna | Los Baños | Baybayin | 14.1701 | 121.236 | R | 1607 | 3.3 | 487 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 1 | Tier 2B: Moderate GIDA Inclusion | 58.02 | 58.02 | 51.11 | 54.56 | D - Other node or line within 3 km | 1.21 | 1 | Line: CLB001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2729
3 | 730 | 2730 | 1705320022 | MIMAROPA Region | Palawan | Taytay | San Jose | 10.9309 | 119.2518 | R | 2960 | 3.9 | 759 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.13 | 29.79 | Tier 1B: High GIDA Priority | 48.15 | 48.15 | 60.96 | 54.56 | F - Nearest node and line over 5 km | 19.13 | 29.79 | Node: TYW006 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2730
3 | 731 | 2731 | 1705103002 | MIMAROPA Region | Occidental Mindoro | Looc | Ambil | 13.7931 | 120.2751 | R | 1819 | 3.9 | 466 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.53 | 38.6 | Tier 1B: High GIDA Priority | 42.99 | 42.99 | 66.14 | 54.56 | F - Nearest node and line over 5 km | 38.53 | 999999 | Node: CTG001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2731
3 | 732 | 2732 | 1400115003 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Buanao | 17.5879 | 121.0213 | R | 339 | 3.8 | 89 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.03 | 29.19 | Tier 1B: High GIDA Priority | 34.01 | 34.01 | 75.11 | 54.56 | F - Nearest node and line over 5 km | 34.03 | 29.03 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2732
3 | 733 | 2733 | 1004323008 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Poblacion | 8.9556 | 124.7883 | R | 3746 | 3.9 | 961 | 288 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.13 | 0.18 | Tier 2A: High Commercial ROI | 77.19 | 77.19 | 31.9 | 54.55 | A - Node within 0.5 km | 0.13 | 0.06 | Line: CDO - BUENAVISTA via GINGOOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2733
3 | 734 | 2734 | 0305403009 | Region III (Central Luzon) | Pampanga | Arayat | Guemasan | 15.1476 | 120.7767 | R | 4424 | 4 | 1106 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 0.73 | Tier 2A: High Commercial ROI | 70.89 | 70.89 | 38.2 | 54.55 | B - Node 0.5-1 km | 0.8 | 0.73 | Line: .46 km | Survey short node lateral; confirm port/fiber capacity, access and route. | 2734
3 | 735 | 2735 | 0804816012 | Region VIII (Eastern Visayas) | Northern Samar | Rosario | Kailingan | 12.5036 | 124.4485 | R | 341 | 4.3 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.41 | 39.87 | Tier 1B: High GIDA Priority | 36.87 | 36.87 | 72.23 | 54.55 | F - Nearest node and line over 5 km | 40.41 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2735
3 | 736 | 2736 | 0802615012 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Patag | 11.4873 | 125.3362 | R | 373 | 3.9 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.64 | 46.55 | Tier 1B: High GIDA Priority | 36.78 | 36.78 | 72.31 | 54.55 | F - Nearest node and line over 5 km | 45.64 | 46.95 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2736
3 | 737 | 2737 | 0205010028 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Latbang | 16.4877 | 120.9828 | R | 1027 | 3.8 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.9 | 13.86 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 73.45 | 54.55 | F - Nearest node and line over 5 km | 16.9 | 13.86 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2737
3 | 738 | 2738 | 0600612023 | Region VI (Western Visayas) | Antique | Patnongon | Quezon | 10.9333 | 122.0807 | R | 319 | 3.9 | 82 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.59 | 17.42 | Tier 1B: High GIDA Priority | 33.48 | 33.48 | 75.61 | 54.55 | F - Nearest node and line over 5 km | 24.59 | 17.13 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2738
3 | 739 | 2739 | 1004307012 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Poblacion | 8.557 | 124.5216 | U | 8953 | 3.9 | 2296 | 689 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.72 | Tier 2B: Moderate GIDA Inclusion | 69.65 | 69.65 | 39.43 | 54.54 | A - Node within 0.5 km | 0.24 | 0.63 | Node: ESM001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2739
3 | 740 | 2740 | 0403422008 | Region IV-A (CALABARZON) | Laguna | Pila | Linga | 14.2551 | 121.36 | R | 3924 | 3.3 | 1189 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 68.69 | 68.69 | 40.38 | 54.53 | D - Other node or line within 3 km | 2.1 | 1.51 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2740
3 | 741 | 2741 | 0306916068 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Miguel | 15.4376 | 120.5982 | U | 8881 | 3.9 | 2277 | 683 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 64.83 | 64.83 | 44.23 | 54.53 | C - Line within 0.5 km; node over 1 km | 2.02 | 0.06 | Line: HH67A Pipe | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2741
3 | 742 | 2742 | 1380601177 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 177 | 11.875 | 120.8296 | U | 3440 | 4.04 | 851 | 255 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 58.75 | 58.75 | Tier 1B: High GIDA Priority | 38.63 | 38.63 | 70.43 | 54.53 | F - Nearest node and line over 5 km | 58.75 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2742
3 | 743 | 2743 | 0301408010 | Region III (Central Luzon) | Bulacan | Guiguinto | Santa Rita | 14.8637 | 120.8638 | U | 17128 | 3.5 | 4894 | 1468 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.99 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 68.1 | 68.1 | 40.93 | 54.52 | C - Line within 0.5 km; node over 1 km | 3.99 | 0.46 | Line: 16 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2743
3 | 744 | 2744 | 0306910024 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Norte | 15.6718 | 120.5808 | U | 9205 | 3.9 | 2360 | 708 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 67.22 | 67.22 | 41.83 | 54.52 | B - Node 0.5-1 km | 0.79 | 0.24 | Line: PANIQUI | Survey short node lateral; confirm port/fiber capacity, access and route. | 2744
3 | 745 | 2745 | 1102305007 | Region XI (Davao Region) | Davao del Norte | Kapalong | Gupitan | 7.906 | 125.6301 | U | 18178 | 3.7 | 4913 | 1474 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 47.04 | 27.38 | Tier 2B: Moderate GIDA Inclusion | 54.67 | 54.67 | 54.36 | 54.52 | F - Nearest node and line over 5 km | 47.04 | 44.35 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2745
3 | 746 | 2746 | 1908705034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Tenonggos | 17.2539 | 122.228 | R | 2630 | 4.3 | 612 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 34.18 | Tier 1B: High GIDA Priority | 40.66 | 40.66 | 68.39 | 54.52 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2746
3 | 747 | 2747 | 1380614035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 779 | 14.3166 | 121.8384 | U | 4450 | 5.02 | 887 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.03 | 34.06 | Tier 1B: High GIDA Priority | 39.59 | 39.59 | 69.45 | 54.52 | F - Nearest node and line over 5 km | 20.03 | 34.01 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2747
3 | 748 | 2748 | 1906606008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Pag-asinan | 17.2517 | 122.2329 | R | 1919 | 6 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.6 | Tier 1B: High GIDA Priority | 37.46 | 37.46 | 71.57 | 54.52 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2748
3 | 749 | 2749 | 0702219018 | Region VII (Central Visayas) | Cebu | Consolacion | Tayud | 10.3626 | 123.9822 | U | 23732 | 3.8 | 6245 | 1874 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.99 | 0.23 | Tier 2A: High Commercial ROI | 72.47 | 72.47 | 36.56 | 54.51 | C - Line within 0.5 km; node over 1 km | 2.99 | 0.02 | Line: Route 7.591km | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2749
3 | 750 | 2750 | 0307114008 | Region III (Central Luzon) | Zambales | Subic | Calapacuan | 14.8624 | 120.2414 | U | 16386 | 3.8 | 4312 | 1294 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.99 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 69.7 | 69.7 | 39.32 | 54.51 | C - Line within 0.5 km; node over 1 km | 2.99 | 0.11 | Line: SUBIC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2750
3 | 751 | 2751 | 0305409002 | Region III (Central Luzon) | Pampanga | Mabalacat City | Bical | 15.8135 | 120.4382 | R | 5078 | 4 | 1270 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 1.82 | Tier 2B: Moderate GIDA Inclusion | 69.57 | 69.57 | 39.46 | 54.51 | D - Other node or line within 3 km | 1.83 | 1.82 | Line: AERIAL 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2751
3 | 752 | 2752 | 1381100056 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 56 | 14.4691 | 121.0135 | U | 1083 | 3.72 | 291 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.44 | 0.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.53 | 38.53 | 70.48 | 54.51 | C - Line within 0.5 km; node over 1 km | 2.44 | 0.12 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2752
3 | 753 | 2753 | 0102934039 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VIII | 17.5456 | 120.3604 | U | 1234 | 3.8 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.21 | 5.08 | Tier 1B: High GIDA Priority | 37.63 | 37.63 | 71.39 | 54.51 | E - Nearest node or line 3-5 km | 6.21 | 4.97 | Line: SEGMENT 3 (VIGAN - BATAC) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2753
3 | 754 | 2754 | 1906610007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kiput | 17.2556 | 122.2296 | R | 1916 | 6 | 319 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 37.46 | 37.46 | 71.55 | 54.51 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2754
3 | 755 | 2755 | 0702216014 | Region VII (Central Visayas) | Cebu | Catmon | Macaas | 10.6961 | 124.0119 | R | 3612 | 3.8 | 951 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.24 | Tier 2A: High Commercial ROI | 76.26 | 76.26 | 32.74 | 54.5 | A - Node within 0.5 km | 0.33 | 0.19 | Line: BOGO - DANAO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2755
3 | 756 | 2756 | 0403406006 | Region IV-A (CALABARZON) | Laguna | Calauan | Lamot 1 | 14.1423 | 121.3104 | R | 3215 | 3.3 | 974 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.31 | Tier 2A: High Commercial ROI | 70.74 | 70.74 | 38.25 | 54.5 | B - Node 0.5-1 km | 0.56 | 0.27 | Line: AE SPO001 TO CLL001-NEW | Survey short node lateral; confirm port/fiber capacity, access and route. | 2756
3 | 757 | 2757 | 0300801010 | Region III (Central Luzon) | Bataan | Abucay | Salian | 14.7125 | 120.5288 | R | 4003 | 3.6 | 1112 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.3 | 0.95 | Tier 2B: Moderate GIDA Inclusion | 67.11 | 67.11 | 41.89 | 54.5 | D - Other node or line within 3 km | 3.3 | 0.93 | Line: 60 CORE 5X12 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2757
3 | 758 | 2758 | 0603043019 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Bolong Oeste | 10.8142 | 122.5292 | R | 2985 | 3.8 | 786 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 1.59 | Tier 2B: Moderate GIDA Inclusion | 65.71 | 65.71 | 43.29 | 54.5 | D - Other node or line within 3 km | 1.58 | 1.43 | Line: Santa Barbara - Janiuay 18.361km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2758
3 | 759 | 2759 | 0802619005 | Region VIII (Eastern Visayas) | Eastern Samar | Salcedo | Balud | 11.1135 | 125.6797 | R | 336 | 3.9 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 71.99 | 70.42 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 72.3 | 54.5 | F - Nearest node and line over 5 km | 71.99 | 999999 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2759
3 | 760 | 2760 | 0804824016 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Roxas | 12.3075 | 124.7039 | R | 193 | 4.3 | 45 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74.35 | 74.34 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 72.31 | 54.5 | F - Nearest node and line over 5 km | 74.35 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2760
3 | 761 | 2761 | 1908709001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Bongo Island | 17.2541 | 122.2282 | R | 8765 | 4.3 | 2038 | 611 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 52.36 | 52.36 | 56.63 | 54.49 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2761
3 | 762 | 2762 | 0600404020 | Region VI (Western Visayas) | Aklan | Batan | Tabon | 11.571 | 122.4771 | R | 952 | 3.9 | 244 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 3.55 | Tier 1B: High GIDA Priority | 51.23 | 51.23 | 57.75 | 54.49 | E - Nearest node or line 3-5 km | 4.22 | 3.47 | Line: IVISAN - KALIBO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2762
3 | 763 | 2763 | 0103308007 | Region I (Ilocos Region) | La Union | Burgos | Libtong | 16.5383 | 120.4545 | R | 697 | 3.7 | 188 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.53 | 1.66 | Tier 1B: High GIDA Priority | 49.69 | 49.69 | 59.3 | 54.49 | E - Nearest node or line 3-5 km | 5.53 | 3.95 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2763
3 | 764 | 2764 | 1403206009 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Uma del Norte | 17.3495 | 121.1343 | R | 1145 | 4.3 | 266 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.65 | 3.49 | Tier 1B: High GIDA Priority | 45.48 | 45.48 | 63.5 | 54.49 | E - Nearest node or line 3-5 km | 9.65 | 3.45 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2764
3 | 765 | 2765 | 0403426003 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Bubukal | 14.2509 | 121.4029 | U | 7817 | 3.3 | 2369 | 711 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 1.1 | Tier 2B: Moderate GIDA Inclusion | 63.23 | 63.23 | 45.74 | 54.48 | D - Other node or line within 3 km | 3.32 | 1.02 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2765
3 | 766 | 2766 | 0401003012 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 7 | 13.9711 | 120.7351 | R | 341 | 3.6 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.17 | 0.99 | Tier 1B: High GIDA Priority | 45.38 | 45.38 | 63.58 | 54.48 | D - Other node or line within 3 km | 3.17 | 0.99 | Line: TUY - STA. TERESITA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2766
3 | 767 | 2767 | 0401005037 | Region IV-A (CALABARZON) | Batangas | Batangas City | Liponpon, Isla Verde | 13.5616 | 121.0915 | R | 684 | 3.6 | 190 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.05 | 15.77 | Tier 1B: High GIDA Priority | 40.97 | 40.97 | 67.98 | 54.48 | F - Nearest node and line over 5 km | 7.05 | 15.71 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2767
3 | 768 | 2768 | 0802610002 | Region VIII (Eastern Visayas) | Eastern Samar | Hernani | Cacatmonan | 11.3101 | 125.5746 | R | 102 | 3.9 | 26 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.58 | 61.58 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 72.27 | 54.48 | F - Nearest node and line over 5 km | 62.58 | 999999 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2768
3 | 769 | 2769 | 1907009002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Bas-bas Proper | 17.2558 | 122.2298 | R | 1467 | 5.8 | 253 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 31.21 | 31.21 | 77.74 | 54.48 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2769
3 | 770 | 2770 | 1004319007 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Maanas | 8.8912 | 125.0322 | R | 4451 | 3.9 | 1141 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 0.12 | Tier 2A: High Commercial ROI | 74.49 | 74.49 | 34.44 | 54.47 | C - Line within 0.5 km; node over 1 km | 2.52 | 0.03 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2770
3 | 771 | 2771 | 0604511009 | Region VI (Western Visayas) | Negros Occidental | Hinigaran | Calapi | 10.277 | 122.9737 | R | 3892 | 3.7 | 1052 | 316 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.02 | 4.44 | Tier 2B: Moderate GIDA Inclusion | 63.38 | 63.38 | 45.56 | 54.47 | F - Nearest node and line over 5 km | 7.02 | 12.34 | Node: LCL001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2771
3 | 772 | 2772 | 1908702007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Karim | 17.2541 | 122.2281 | R | 8356 | 4.3 | 1943 | 583 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 2B: Moderate GIDA Inclusion | 52.08 | 52.08 | 56.86 | 54.47 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2772
3 | 773 | 2773 | 0806017037 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Gumamela Pob. | 11.4633 | 124.9799 | R | 1315 | 4.1 | 321 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.99 | 28.07 | Tier 1B: High GIDA Priority | 37.1 | 37.1 | 71.84 | 54.47 | F - Nearest node and line over 5 km | 24.99 | 28.06 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2773
3 | 774 | 2774 | 1401110003 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Ambiong | 16.4364 | 120.6043 | U | 8567 | 3.5 | 2448 | 734 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 1.94 | Tier 2B: Moderate GIDA Inclusion | 66.33 | 66.33 | 42.59 | 54.46 | D - Other node or line within 3 km | 1.66 | 1.94 | Node: BGC004 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2774
3 | 775 | 2775 | 0401003009 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 4 | 13.9663 | 120.7243 | U | 2105 | 3.6 | 585 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 0.27 | Tier 1B: High GIDA Priority | 51.12 | 51.12 | 57.8 | 54.46 | C - Line within 0.5 km; node over 1 km | 2.57 | 0.27 | Line: NSB001 TO BYB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2775
3 | 776 | 2776 | 0907311015 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Kitaan Dagat | 7.8021 | 123.1421 | R | 511 | 3.9 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.52 | 3.29 | Tier 1B: High GIDA Priority | 39.5 | 39.5 | 69.42 | 54.46 | E - Nearest node or line 3-5 km | 12.52 | 3.25 | Line: PAGADIAN - BUUG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2776
3 | 777 | 2777 | 0403423010 | Region IV-A (CALABARZON) | Laguna | Rizal | Talaga | 14.1112 | 121.3913 | R | 2220 | 3.6 | 617 | 185 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.18 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 68.15 | 68.15 | 40.76 | 54.45 | A - Node within 0.5 km | 0.18 | 0.05 | Line: SAN PABLO - LUCBAN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2777
3 | 778 | 2778 | 0402106013 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc I | 14.2986 | 120.9559 | U | 8066 | 3.4 | 2372 | 712 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 67.98 | 67.98 | 40.92 | 54.45 | A - Node within 0.5 km | 0.35 | 0.06 | Line: NCC001 TO TGY001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2778
3 | 779 | 2779 | 0301403026 | Region III (Central Luzon) | Bulacan | Baliuag | Tiaong | 14.9442 | 120.8961 | U | 6126 | 3.5 | 1750 | 525 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 65.02 | 65.02 | 43.88 | 54.45 | B - Node 0.5-1 km | 0.97 | 0.42 | Line: Calumpit-Baliuag Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 2779
3 | 780 | 2780 | 1102315002 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Datu Abdul Dadia | 7.3159 | 125.6542 | U | 7518 | 3.7 | 2032 | 610 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.34 | 3.35 | Tier 2B: Moderate GIDA Inclusion | 60.44 | 60.44 | 48.47 | 54.45 | E - Nearest node or line 3-5 km | 3.34 | 3.33 | Line: DAVAO CITY - TRENTO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2780
3 | 781 | 2781 | 0601906002 | Region VI (Western Visayas) | Capiz | Jamindan | Agbun-od | 11.4712 | 122.4276 | R | 988 | 3.8 | 260 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.51 | 7.39 | Tier 1B: High GIDA Priority | 43.05 | 43.05 | 65.86 | 54.45 | F - Nearest node and line over 5 km | 9.51 | 7.32 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2781
3 | 782 | 2782 | 1381100103 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 103 | 14.623 | 121.1048 | U | 973 | 3.34 | 291 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.94 | 0.32 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.26 | 39.26 | 69.63 | 54.45 | C - Line within 0.5 km; node over 1 km | 1.94 | 0.29 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2782
3 | 783 | 2783 | 1380601122 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 122 | 12.3438 | 123.1013 | U | 3830 | 4.48 | 855 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.34 | 41.07 | Tier 1B: High GIDA Priority | 38.72 | 38.72 | 70.18 | 54.45 | F - Nearest node and line over 5 km | 24.34 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2783
3 | 784 | 2784 | 1380605049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 347 | 13.3527 | 121.1417 | U | 1283 | 3.89 | 330 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.15 | 0.31 | Tier 1B: High GIDA Priority | 38.68 | 38.68 | 70.21 | 54.45 | C - Line within 0.5 km; node over 1 km | 3.15 | 0.31 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2784
3 | 785 | 2785 | 1380601065 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 65 | 13.7861 | 121.4356 | U | 1721 | 4.28 | 402 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.72 | 0.28 | Tier 1B: High GIDA Priority | 38.49 | 38.49 | 70.4 | 54.45 | F - Nearest node and line over 5 km | 5.72 | 5.03 | Line: BATANGAS - SAN JUAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2785
3 | 786 | 2786 | 1907011016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Ungus-ungus | 13.5075 | 121.4145 | R | 2621 | 5.8 | 452 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.09 | 30.67 | Tier 1B: High GIDA Priority | 37.76 | 37.76 | 71.15 | 54.45 | F - Nearest node and line over 5 km | 21.09 | 30.68 | Node: SJB003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2786
3 | 787 | 2787 | 1381100011 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 11 | 14.5465 | 121.0219 | U | 444 | 3.22 | 138 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.41 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.17 | 37.17 | 71.73 | 54.45 | B - Node 0.5-1 km | 0.84 | 0.58 | Line: Reliance-Naga Rd Core Ring, UG, MKT (JEJ to In-House) 588m | Survey short node lateral; confirm port/fiber capacity, access and route. | 2787
3 | 788 | 2788 | 1380601071 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 71 | 13.4619 | 120.4933 | U | 3486 | 4.5 | 774 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.3 | 43.3 | Tier 1B: High GIDA Priority | 36.62 | 36.62 | 72.28 | 54.45 | F - Nearest node and line over 5 km | 43.3 | 58.59 | Node: CTG001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2788
3 | 789 | 2789 | 0600412010 | Region VI (Western Visayas) | Aklan | Malay | Manoc-Manoc | 11.95 | 121.9409 | U | 21135 | 3.9 | 5419 | 1626 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.57 | 2.52 | Tier 2A: High Commercial ROI | 73.75 | 73.75 | 35.13 | 54.44 | B - Node 0.5-1 km | 0.57 | 999999 | Node: MYK001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2789
3 | 790 | 2790 | 0304926030 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 1st | 15.7991 | 120.991 | U | 7950 | 3.5 | 2271 | 681 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 67.32 | 67.32 | 41.57 | 54.44 | B - Node 0.5-1 km | 0.6 | 0.4 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2790
3 | 791 | 2791 | 0803708092 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Poblacion Zone 1 | 10.6333 | 124.847 | R | 3204 | 3.8 | 843 | 253 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.13 | 1.69 | Tier 2B: Moderate GIDA Inclusion | 62.15 | 62.15 | 46.73 | 54.44 | E - Nearest node or line 3-5 km | 7.13 | 4.76 | Line: ORMOC - BAYBAY | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2791
3 | 792 | 2792 | 0403405023 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Looc | 14.2239 | 121.1791 | U | 29398 | 3.3 | 8908 | 2672 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 4.62 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 62.02 | 62.02 | 46.87 | 54.44 | D - Other node or line within 3 km | 4.62 | 0.77 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2792
3 | 793 | 2793 | 0301422030 | Region III (Central Luzon) | Bulacan | San Rafael | San Roque | 15.0084 | 120.9324 | U | 10112 | 3.5 | 2889 | 867 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 0.03 | Tier 2A: High Commercial ROI | 70.29 | 70.29 | 38.57 | 54.43 | A - Node within 0.5 km | 0.1 | 0.03 | Line: 24 CORE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2793
3 | 794 | 2794 | 0301404011 | Region III (Central Luzon) | Bulacan | Bocaue | Duhat | 14.7859 | 120.9534 | U | 9308 | 3.5 | 2659 | 798 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 1.01 | Tier 2B: Moderate GIDA Inclusion | 65.94 | 65.94 | 42.92 | 54.43 | D - Other node or line within 3 km | 2.05 | 1.96 | Line: GOTACO TO HH 71 BULACAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2794
3 | 795 | 2795 | 0401032005 | Region IV-A (CALABARZON) | Batangas | Taysan | Guinhawa | 13.7212 | 121.2628 | R | 1436 | 3.6 | 399 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.99 | 12.38 | Tier 1B: High GIDA Priority | 46.72 | 46.72 | 62.14 | 54.43 | F - Nearest node and line over 5 km | 6.99 | 12.38 | Node: TAB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2795
3 | 796 | 2796 | 0802615016 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 4 | 11.5042 | 125.4976 | R | 1706 | 3.9 | 437 | 131 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.47 | 61.72 | Tier 1B: High GIDA Priority | 43 | 43 | 65.87 | 54.43 | F - Nearest node and line over 5 km | 61.47 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2796
3 | 797 | 2797 | 1606718002 | Region XIII (Caraga) | Surigao del Norte | San Benito | Maribojoc | 9.9329 | 125.9627 | R | 1241 | 4.1 | 303 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.73 | 45.59 | Tier 1B: High GIDA Priority | 39.08 | 39.08 | 69.78 | 54.43 | F - Nearest node and line over 5 km | 53.73 | 50.04 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2797
3 | 798 | 2798 | 1380601014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 14 | 13.4857 | 122.7498 | U | 2479 | 3.86 | 643 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.57 | 22.92 | Tier 1B: High GIDA Priority | 34.25 | 34.25 | 74.61 | 54.43 | F - Nearest node and line over 5 km | 14.57 | 22.92 | Node: SNQ003-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2798
3 | 799 | 2799 | 1108205012 | Region XI (Davao Region) | Davao de Oro | Maragusan | Mabugnao | 7.3159 | 126.0785 | R | 415 | 3.7 | 112 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.6 | 24.31 | Tier 1B: High GIDA Priority | 31.97 | 31.97 | 76.89 | 54.43 | F - Nearest node and line over 5 km | 24.6 | 24.25 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2799
3 | 800 | 2800 | 0403423001 | Region IV-A (CALABARZON) | Laguna | Rizal | Antipolo | 14.1108 | 121.3814 | R | 2871 | 3.6 | 798 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.04 | Tier 2A: High Commercial ROI | 70.96 | 70.96 | 37.87 | 54.42 | C - Line within 0.5 km; node over 1 km | 1.22 | 0.04 | Line: AE NGL001 TO SPO001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2800
3 | 801 | 2801 | 0405801014 | Region IV-A (CALABARZON) | Rizal | Angono | Mahabang Parang | 14.5476 | 121.1897 | U | 36264 | 3.6 | 10073 | 3022 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 2.05 | 1.6 | Tier 2B: Moderate GIDA Inclusion | 63.37 | 63.37 | 45.48 | 54.42 | D - Other node or line within 3 km | 2.05 | 1.45 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2801
3 | 802 | 2802 | 1381200017 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Rosario | 14.5844 | 121.085 | U | 80002 | 3 | 26684 | 8005 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.93 | 0.34 | Tier 1B: High GIDA Priority | 47.4 | 47.4 | 61.45 | 54.42 | B - Node 0.5-1 km | 0.93 | 0.34 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2802
3 | 803 | 2803 | 1906614033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Tangkapaan | 17.2556 | 122.2297 | R | 1871 | 6 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 37.29 | 37.29 | 71.55 | 54.42 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2803
3 | 804 | 2804 | 1381100009 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 9 | 14.5264 | 121.0099 | U | 263 | 2.58 | 102 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.08 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.19 | 37.19 | 71.64 | 54.42 | B - Node 0.5-1 km | 0.78 | 0.08 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2804
3 | 805 | 2805 | 0300809021 | Region III (Central Luzon) | Bataan | Orani | Tapulao | 14.8131 | 120.5198 | R | 5148 | 3.6 | 1430 | 429 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 69.54 | 69.54 | 39.27 | 54.41 | C - Line within 0.5 km; node over 1 km | 2.16 | 0.13 | Line: ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2805
3 | 806 | 2806 | 0403405018 | Region IV-A (CALABARZON) | Laguna | City of Calamba | La Mesa | 14.1809 | 121.1569 | U | 19259 | 3.3 | 5836 | 1751 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.16 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 68.72 | 68.72 | 40.1 | 54.41 | D - Other node or line within 3 km | 2.16 | 1.46 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2806
3 | 807 | 2807 | 0300812001 | Region III (Central Luzon) | Bataan | Samal | East Calaguiman | 14.7607 | 120.5185 | R | 2913 | 3.6 | 809 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.99 | 1.86 | Tier 2B: Moderate GIDA Inclusion | 66.82 | 66.82 | 41.99 | 54.41 | D - Other node or line within 3 km | 4.99 | 1.85 | Line: Pipe Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2807
3 | 808 | 2808 | 0403417053 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Yukos | 14.1321 | 121.413 | U | 5953 | 3.3 | 1804 | 541 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 65.65 | 65.65 | 43.17 | 54.41 | B - Node 0.5-1 km | 0.63 | 0.26 | Line: SPO001 TO LBQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2808
3 | 809 | 2809 | 0802615008 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Malobago | 11.5024 | 125.4196 | R | 499 | 3.9 | 128 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.05 | 54.63 | Tier 1B: High GIDA Priority | 36.72 | 36.72 | 72.1 | 54.41 | F - Nearest node and line over 5 km | 54.05 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2809
3 | 810 | 2810 | 0802615010 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Maytigbao | 11.4729 | 125.4691 | R | 232 | 3.9 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.11 | 57.26 | Tier 1B: High GIDA Priority | 36.71 | 36.71 | 72.1 | 54.41 | F - Nearest node and line over 5 km | 57.11 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2810
3 | 811 | 2811 | 0702223021 | Region VII (Central Visayas) | Cebu | Danao City | Looc | 10.5066 | 124.0295 | U | 12347 | 3.8 | 3249 | 975 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 0.23 | Tier 2A: High Commercial ROI | 70.29 | 70.29 | 38.52 | 54.4 | C - Line within 0.5 km; node over 1 km | 1.72 | 0.06 | Line: DANAO - CEBU | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2811
3 | 812 | 2812 | 0604531010 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VII | 10.8714 | 123.0902 | R | 3980 | 3.7 | 1076 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.84 | 3.58 | Tier 2B: Moderate GIDA Inclusion | 65.77 | 65.77 | 43.02 | 54.4 | E - Nearest node or line 3-5 km | 3.84 | 3.54 | Line: TALISAY - VICTORIAS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2812
3 | 813 | 2813 | 0102820016 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Miguel | 18.1708 | 120.6026 | R | 1725 | 3.7 | 466 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.96 | Tier 2B: Moderate GIDA Inclusion | 58.04 | 58.04 | 50.77 | 54.4 | B - Node 0.5-1 km | 0.97 | 0.91 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2813
3 | 814 | 2814 | 1705323007 | MIMAROPA Region | Palawan | Rizal | Latud | 8.6707 | 117.3217 | R | 2499 | 3.6 | 694 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 195.37 | 197.62 | Tier 1B: High GIDA Priority | 43.93 | 43.93 | 64.87 | 54.4 | F - Nearest node and line over 5 km | 195.37 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2814
3 | 815 | 2815 | 0102934009 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barraca | 17.5593 | 120.3728 | R | 300 | 3.8 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.25 | 3.07 | Tier 1B: High GIDA Priority | 41.05 | 41.05 | 67.74 | 54.4 | D - Other node or line within 3 km | 4.25 | 2.98 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2815
3 | 816 | 2816 | 0105521010 | Region I (Ilocos Region) | Pangasinan | Labrador | Uyong | 16.05 | 120.1208 | R | 2852 | 3.6 | 792 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.05 | 0.14 | Tier 2A: High Commercial ROI | 73.27 | 73.27 | 35.52 | 54.39 | A - Node within 0.5 km | 0.05 | 0.04 | Line: LABRADOR | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2816
3 | 817 | 2817 | 1401106001 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Ampucao | 16.3253 | 120.6547 | U | 11221 | 3.5 | 3206 | 962 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.61 | 10.24 | Tier 2B: Moderate GIDA Inclusion | 67 | 67 | 41.78 | 54.39 | B - Node 0.5-1 km | 0.61 | 10.12 | Node: ITB003 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 2817
3 | 818 | 2818 | 0806417037 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | San Juan | 10.4428 | 125.0288 | R | 731 | 4.1 | 178 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.1 | 2.11 | Tier 1B: High GIDA Priority | 42.82 | 42.82 | 65.97 | 54.39 | F - Nearest node and line over 5 km | 36.18 | 33.46 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2818
3 | 819 | 2819 | 1380605076 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 373 | 11.5466 | 121.3428 | U | 3977 | 5.49 | 724 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 79.4 | 78.18 | Tier 1B: High GIDA Priority | 35.31 | 35.31 | 73.46 | 54.39 | F - Nearest node and line over 5 km | 79.4 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2819
3 | 820 | 2820 | 1380601018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 18 | 11.8155 | 122.016 | U | 2006 | 4.13 | 486 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.63 | 5.2 | Tier 1B: High GIDA Priority | 29.12 | 29.12 | 79.66 | 54.39 | F - Nearest node and line over 5 km | 16.63 | 38.9 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2820
3 | 821 | 2821 | 0604530003 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Bagumbayan | 10.4033 | 122.8682 | R | 3767 | 3.7 | 1018 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.39 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 72.89 | 72.89 | 35.88 | 54.38 | D - Other node or line within 3 km | 3.39 | 0.98 | Line: TALISAY CITY - KABANGKALAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2821
3 | 822 | 2822 | 0604532006 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pandanon | 10.5765 | 123.178 | R | 2908 | 3.7 | 786 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.85 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 68.37 | 68.37 | 40.4 | 54.38 | C - Line within 0.5 km; node over 1 km | 2.85 | 0.1 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2822
3 | 823 | 2823 | 0405808003 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Geronimo | 14.7325 | 121.1496 | U | 6475 | 3.6 | 1799 | 540 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 65.45 | 65.45 | 43.31 | 54.38 | B - Node 0.5-1 km | 0.72 | 0.17 | Line: Aerial 216C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2823
3 | 824 | 2824 | 0301419001 | Region III (Central Luzon) | Bulacan | San Ildefonso | Akle | 15.0484 | 121.0715 | U | 4864 | 3.5 | 1390 | 417 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 6.52 | Tier 2B: Moderate GIDA Inclusion | 61.74 | 61.74 | 47.01 | 54.38 | A - Node within 0.5 km | 0.32 | 13.74 | Node: SIB005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2824
3 | 825 | 2825 | 0205005012 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Paitan | 16.4656 | 121.1472 | R | 2829 | 3.8 | 744 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 2.24 | Tier 2B: Moderate GIDA Inclusion | 59.57 | 59.57 | 49.17 | 54.37 | D - Other node or line within 3 km | 2.46 | 2.24 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2825
3 | 826 | 2826 | 0103306026 | Region I (Ilocos Region) | La Union | Bangar | Central East No. 2 | 16.8957 | 120.4241 | R | 1049 | 3.7 | 284 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 54.48 | 54.48 | 54.26 | 54.37 | A - Node within 0.5 km | 0.29 | 0.09 | Line: SAN FERNANDO - SUPIDEN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2826
3 | 827 | 2827 | 1208007015 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Lower Mainit | 6.3729 | 125.3026 | R | 2203 | 3.9 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.15 | 3.09 | Tier 1B: High GIDA Priority | 49.86 | 49.86 | 58.87 | 54.37 | E - Nearest node or line 3-5 km | 9.15 | 3.07 | Line: DAVAO CITY - GENSAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2827
3 | 828 | 2828 | 0304916007 | Region III (Central Luzon) | Nueva Ecija | Lupao | Bagong Flores | 15.8879 | 120.9 | R | 4328 | 3.5 | 1237 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 1.62 | Tier 2A: High Commercial ROI | 72.08 | 72.08 | 36.64 | 54.36 | A - Node within 0.5 km | 0.41 | 1.62 | Node: LPN001 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2828
3 | 829 | 2829 | 0601916014 | Region VI (Western Visayas) | Capiz | Sigma | Mianay | 11.4603 | 122.69 | R | 3912 | 3.8 | 1029 | 309 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.92 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 71.84 | 71.84 | 36.89 | 54.36 | C - Line within 0.5 km; node over 1 km | 4.92 | 0.08 | Line: ROXAS - ILOILO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2829
3 | 830 | 2830 | 0802605028 | Region VIII (Eastern Visayas) | Eastern Samar | Can-Avid | Salvacion | 11.9706 | 125.3111 | R | 468 | 3.9 | 120 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 87.97 | 90.49 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 72.03 | 54.36 | F - Nearest node and line over 5 km | 87.97 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2830
3 | 831 | 2831 | 1408102009 | Cordillera Administrative Region (CAR) | Apayao | Conner | Katablangan | 17.818 | 121.1761 | R | 662 | 4.2 | 158 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.85 | 8.57 | Tier 1B: High GIDA Priority | 33.58 | 33.58 | 75.13 | 54.36 | F - Nearest node and line over 5 km | 15.85 | 15.38 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2831
3 | 832 | 2832 | 0300805014 | Region III (Central Luzon) | Bataan | Hermosa | Palihan | 14.8438 | 120.4732 | U | 6848 | 3.6 | 1902 | 571 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.9 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 63.87 | 63.87 | 44.82 | 54.35 | C - Line within 0.5 km; node over 1 km | 1.9 | 0.18 | Line: Pipe Dinalupian to Orion | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2832
3 | 833 | 2833 | 0300806009 | Region III (Central Luzon) | Bataan | Limay | Townsite | 14.561 | 120.5951 | U | 5874 | 3.6 | 1632 | 490 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 63.79 | 63.79 | 44.9 | 54.35 | C - Line within 0.5 km; node over 1 km | 1.45 | 0.02 | Line: 24 CORE 2X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2833
3 | 834 | 2834 | 0500501010 | Region V (Bicol Region) | Albay | Bacacay | Cagbulacao | 13.2852 | 123.888 | R | 896 | 4.1 | 219 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.72 | 13.14 | Tier 1B: High GIDA Priority | 40.09 | 40.09 | 68.61 | 54.35 | F - Nearest node and line over 5 km | 11.72 | 13.02 | Node: BYY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2834
3 | 835 | 2835 | 1380605045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 343 | 13.5893 | 120.8254 | U | 3037 | 3.94 | 770 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.99 | 12.46 | Tier 1B: High GIDA Priority | 38.56 | 38.56 | 70.15 | 54.35 | F - Nearest node and line over 5 km | 12.99 | 12.26 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2835
3 | 836 | 2836 | 0600618001 | Region VI (Western Visayas) | Antique | Valderrama | Bakiang | 11.0907 | 122.1801 | R | 580 | 3.9 | 149 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.77 | 38 | Tier 1B: High GIDA Priority | 36.88 | 36.88 | 71.82 | 54.35 | F - Nearest node and line over 5 km | 39.77 | 37.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2836
3 | 837 | 2837 | 0802614012 | Region VIII (Eastern Visayas) | Eastern Samar | Maslog | Tangbo | 12.1429 | 125.2659 | R | 204 | 3.9 | 52 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 104.46 | 107.17 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 72.02 | 54.35 | F - Nearest node and line over 5 km | 104.46 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2837
3 | 838 | 2838 | 0405809005 | Region IV-A (CALABARZON) | Rizal | Morong | San Guillermo | 14.5233 | 121.2131 | U | 12213 | 3.6 | 3392 | 1018 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.87 | 1.55 | Tier 2A: High Commercial ROI | 70.07 | 70.07 | 38.6 | 54.34 | B - Node 0.5-1 km | 0.87 | 1.53 | Node: MRR002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2838
3 | 839 | 2839 | 0301410037 | Region III (Central Luzon) | Bulacan | City of Malolos | Pamarawan | 14.7591 | 120.8145 | R | 3234 | 3.5 | 924 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.67 | 9.77 | Tier 2B: Moderate GIDA Inclusion | 60.7 | 60.7 | 47.97 | 54.34 | F - Nearest node and line over 5 km | 6.67 | 9.8 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2839
3 | 840 | 2840 | 0405603027 | Region IV-A (CALABARZON) | Quezon | Atimonan | Montes Balaon | 13.9492 | 121.8814 | R | 178 | 3.8 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.44 | 3.96 | Tier 1B: High GIDA Priority | 39.2 | 39.2 | 69.48 | 54.34 | E - Nearest node or line 3-5 km | 7.44 | 3.95 | Line: SAN JUAN TO UNISAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2840
3 | 841 | 2841 | 0806023014 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Monbon | 11.6429 | 124.8413 | R | 684 | 4.1 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.59 | 41.51 | Tier 1B: High GIDA Priority | 37.08 | 37.08 | 71.6 | 54.34 | F - Nearest node and line over 5 km | 41.59 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2841
3 | 842 | 2842 | 0205702008 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Mangandingay | 16.5162 | 121.5475 | R | 3342 | 3.9 | 857 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 66.64 | 66.64 | 42.01 | 54.33 | C - Line within 0.5 km; node over 1 km | 2.1 | 0.07 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2842
3 | 843 | 2843 | 0301406008 | Region III (Central Luzon) | Bulacan | Bustos | Malamig | 14.9325 | 120.928 | U | 8005 | 3.5 | 2287 | 686 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 66.1 | 66.1 | 42.56 | 54.33 | C - Line within 0.5 km; node over 1 km | 1.27 | 0.03 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2843
3 | 844 | 2844 | 0403419015 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sampaloc | 14.2696 | 121.4444 | U | 4667 | 3.3 | 1414 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 64.16 | 64.16 | 44.5 | 54.33 | B - Node 0.5-1 km | 0.77 | 0.03 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2844
3 | 845 | 2845 | 0103308006 | Region I (Ilocos Region) | La Union | Burgos | Imelda | 16.5207 | 120.4586 | R | 480 | 3.7 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.8 | 0.24 | Tier 1B: High GIDA Priority | 49.47 | 49.47 | 59.19 | 54.33 | D - Other node or line within 3 km | 3.8 | 2.07 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2845
3 | 846 | 2846 | 1408104012 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Lucab | 18.0299 | 121.132 | R | 575 | 4.2 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.32 | 13.49 | Tier 1B: High GIDA Priority | 40.98 | 40.98 | 67.68 | 54.33 | F - Nearest node and line over 5 km | 5.32 | 45.88 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2846
3 | 847 | 2847 | 1380601217 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 216 | 14.0558 | 121.3936 | U | 2237 | 4.61 | 485 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 5.52 | Tier 1B: High GIDA Priority | 37.9 | 37.9 | 70.76 | 54.33 | E - Nearest node or line 3-5 km | 4.59 | 5.54 | Node: DLQ001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2847
3 | 848 | 2848 | 1906608016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Suang Bunah | 17.2554 | 122.2294 | R | 1851 | 6 | 308 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.37 | Tier 1B: High GIDA Priority | 37.12 | 37.12 | 71.55 | 54.33 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2848
3 | 849 | 2849 | 0804824012 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Maghipid | 12.3286 | 124.6073 | R | 458 | 4.3 | 107 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 63.88 | 63.86 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 71.96 | 54.33 | F - Nearest node and line over 5 km | 63.88 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2849
3 | 850 | 2850 | 1402705019 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Sanafe | 16.7012 | 121.2365 | R | 1448 | 3.9 | 371 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.75 | 4.39 | Tier 1B: High GIDA Priority | 51.36 | 51.36 | 57.28 | 54.32 | E - Nearest node or line 3-5 km | 5.75 | 4.27 | Line: FOC | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2850
3 | 851 | 2851 | 0804824021 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Somoroy | 12.3202 | 124.725 | R | 166 | 4.3 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.86 | 75.85 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.95 | 54.32 | F - Nearest node and line over 5 km | 75.86 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2851
3 | 852 | 2852 | 0806012011 | Region VIII (Eastern Visayas) | Samar | Motiong | Canvais | 11.9649 | 125.0462 | R | 304 | 4.1 | 74 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.79 | 83.45 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.95 | 54.32 | F - Nearest node and line over 5 km | 80.79 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2852
3 | 853 | 2853 | 1903610032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Kining | 17.2544 | 122.2284 | R | 869 | 5.7 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 33.12 | 33.12 | 75.52 | 54.32 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2853
3 | 854 | 2854 | 1408101013 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Don Roque Ablan Sr. | 18.2494 | 120.9955 | R | 227 | 4.2 | 54 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.93 | 28.93 | Tier 1B: High GIDA Priority | 29.87 | 29.87 | 78.77 | 54.32 | F - Nearest node and line over 5 km | 28.93 | 28.92 | Line: SEGMENT 2 SOLSONA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2854
3 | 855 | 2855 | 1705320021 | MIMAROPA Region | Palawan | Taytay | Pularaquen | 10.9559 | 119.4853 | R | 3467 | 3.9 | 889 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 15 | Tier 2B: Moderate GIDA Inclusion | 67.14 | 67.14 | 41.48 | 54.31 | A - Node within 0.5 km | 0.31 | 14.8 | Node: TYW002 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2855
3 | 856 | 2856 | 0304927003 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Burgos District | 15.3595 | 120.9385 | R | 2367 | 3.5 | 676 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 64.18 | 64.18 | 44.43 | 54.31 | B - Node 0.5-1 km | 0.72 | 0.14 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2856
3 | 857 | 2857 | 0203135009 | Region II (Cagayan Valley) | Isabela | City of Santiago | Calao East | 16.6918 | 121.5581 | U | 4423 | 3.8 | 1164 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.26 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 59.81 | 59.81 | 48.81 | 54.31 | D - Other node or line within 3 km | 3.26 | 0.54 | Line: SEGMENT 12 (CAUAYAN - SANTIAGO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2857
3 | 858 | 2858 | 0704619027 | Region VII (Central Visayas) | Negros Oriental | Siaton | Tayak | 9.1122 | 123.0752 | R | 3238 | 3.8 | 852 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.41 | 7.4 | Tier 2B: Moderate GIDA Inclusion | 58.81 | 58.81 | 49.81 | 54.31 | F - Nearest node and line over 5 km | 7.41 | 27.88 | Node: SIA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2858
3 | 859 | 2859 | 1401107002 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Anchukey | 16.617 | 120.85 | R | 298 | 3.5 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 8.64 | Tier 1B: High GIDA Priority | 49.43 | 49.43 | 59.2 | 54.31 | D - Other node or line within 3 km | 1.62 | 8.4 | Node: KYB001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2859
3 | 860 | 2860 | 0504118012 | Region V (Bicol Region) | Masbate | San Fernando | Lahong | 12.4939 | 123.6693 | R | 392 | 4.1 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.2 | 13.74 | Tier 1B: High GIDA Priority | 40.38 | 40.38 | 68.24 | 54.31 | F - Nearest node and line over 5 km | 16.2 | 15.88 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2860
3 | 861 | 2861 | 1380614038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 782 | 13.3942 | 121.0202 | U | 1619 | 4.51 | 359 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.58 | 1.63 | Tier 1B: High GIDA Priority | 38.08 | 38.08 | 70.53 | 54.31 | D - Other node or line within 3 km | 4.58 | 1.56 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2861
3 | 862 | 2862 | 0806023005 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Botaera | 11.6681 | 124.841 | R | 662 | 4.1 | 161 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.16 | 44.1 | Tier 1B: High GIDA Priority | 36.89 | 36.89 | 71.74 | 54.31 | F - Nearest node and line over 5 km | 44.16 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2862
3 | 863 | 2863 | 1004217001 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Bagong Clarin | 8.258 | 123.5875 | R | 750 | 3.9 | 192 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.38 | 32.06 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 71.82 | 54.31 | F - Nearest node and line over 5 km | 33.38 | 32.06 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2863
3 | 864 | 2864 | 0802615004 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Canloterio | 11.4759 | 125.4032 | R | 506 | 3.9 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.99 | 51.44 | Tier 1B: High GIDA Priority | 36.74 | 36.74 | 71.89 | 54.31 | F - Nearest node and line over 5 km | 50.99 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2864
3 | 865 | 2865 | 0301423007 | Region III (Central Luzon) | Bulacan | Santa Maria | Cay Pombo | 14.8523 | 120.9779 | U | 34153 | 3.5 | 9758 | 2927 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 2.32 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 44.8 | 54.3 | C - Line within 0.5 km; node over 1 km | 2.32 | 0.5 | Line: STA. MARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2865
3 | 866 | 2866 | 1204712046 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Paidu Pulangi | 7.0211 | 124.5701 | R | 3801 | 3.8 | 1000 | 300 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.15 | 28.14 | Tier 2B: Moderate GIDA Inclusion | 51.96 | 51.96 | 56.64 | 54.3 | F - Nearest node and line over 5 km | 32.15 | 29.08 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2866
3 | 867 | 2867 | 1908804007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Tulunan | 17.2552 | 122.2292 | R | 2657 | 4.7 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 39.42 | 39.42 | 69.18 | 54.3 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2867
3 | 868 | 2868 | 0600416006 | Region VI (Western Visayas) | Aklan | Numancia | Bulwang | 11.7196 | 122.356 | U | 5334 | 3.9 | 1368 | 410 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 68.56 | 68.56 | 40.02 | 54.29 | C - Line within 0.5 km; node over 1 km | 2.73 | 0.44 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2868
3 | 869 | 2869 | 0300807020 | Region III (Central Luzon) | Bataan | Mariveles | Townsite | 14.4579 | 120.5944 | U | 7524 | 3.6 | 2090 | 627 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.44 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 63.65 | 63.65 | 44.93 | 54.29 | C - Line within 0.5 km; node over 1 km | 2.44 | 0.31 | Line: 96C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2869
3 | 870 | 2870 | 1004217007 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Maramara | 8.154 | 123.5656 | R | 522 | 3.9 | 134 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.51 | 22.44 | Tier 1B: High GIDA Priority | 36.86 | 36.86 | 71.73 | 54.29 | F - Nearest node and line over 5 km | 22.51 | 22.44 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2870
3 | 871 | 2871 | 0806023027 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Talib | 11.6706 | 124.8891 | R | 242 | 4.1 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.63 | 46.53 | Tier 1B: High GIDA Priority | 36.77 | 36.77 | 71.8 | 54.29 | F - Nearest node and line over 5 km | 46.63 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2871
3 | 872 | 2872 | 0301423006 | Region III (Central Luzon) | Bulacan | Santa Maria | Catmon | 14.8287 | 121.0014 | U | 16660 | 3.5 | 4760 | 1428 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.64 | 2.23 | Tier 2B: Moderate GIDA Inclusion | 69.59 | 69.59 | 38.96 | 54.28 | B - Node 0.5-1 km | 0.64 | 2.23 | Node: SMR002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 2872
3 | 873 | 2873 | 0405810001 | Region IV-A (CALABARZON) | Rizal | Pililla | Bagumbayan | 14.4813 | 121.3258 | U | 12893 | 3.6 | 3581 | 1074 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.86 | 1.11 | Tier 2B: Moderate GIDA Inclusion | 68.9 | 68.9 | 39.65 | 54.28 | D - Other node or line within 3 km | 1.86 | 1.1 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2873
3 | 874 | 2874 | 0305414004 | Region III (Central Luzon) | Pampanga | Minalin | Maniango | 14.9358 | 120.6688 | R | 2204 | 4 | 551 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.91 | 5.1 | Tier 2B: Moderate GIDA Inclusion | 55.79 | 55.79 | 52.78 | 54.28 | F - Nearest node and line over 5 km | 5.91 | 5.09 | Line: foc | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2874
3 | 875 | 2875 | 1206316023 | Region XII (SOCCSKSARGEN) | South Cotabato | T'Boli | Tudok | 6.049 | 124.8411 | R | 3621 | 3.6 | 1006 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.97 | 30.6 | Tier 2B: Moderate GIDA Inclusion | 52.21 | 52.21 | 56.36 | 54.28 | F - Nearest node and line over 5 km | 30.97 | 30.6 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2875
3 | 876 | 2876 | 1906612067 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Southwestern Bulikullul | 16.3658 | 122.1112 | R | 897 | 6 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.78 | 3.13 | Tier 1B: High GIDA Priority | 36.06 | 36.06 | 72.51 | 54.28 | F - Nearest node and line over 5 km | 9.78 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2876
3 | 877 | 2877 | 0301420012 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Citrus | 14.8482 | 121.0649 | U | 23929 | 3.5 | 6837 | 2051 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.7 | 3.11 | Tier 2B: Moderate GIDA Inclusion | 64.99 | 64.99 | 43.55 | 54.27 | D - Other node or line within 3 km | 1.7 | 5.97 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2877
3 | 878 | 2878 | 0804807011 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | G. M. Osias | 12.3618 | 125.2234 | R | 715 | 4.3 | 166 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 125.37 | 124.61 | Tier 1B: High GIDA Priority | 36.93 | 36.93 | 71.61 | 54.27 | F - Nearest node and line over 5 km | 125.37 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2878
3 | 879 | 2879 | 1003506013 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Ditago | 7.7769 | 123.7178 | R | 955 | 4.2 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.32 | 12.44 | Tier 1B: High GIDA Priority | 34.02 | 34.02 | 74.51 | 54.27 | F - Nearest node and line over 5 km | 24.32 | 12.42 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2879
3 | 880 | 2880 | 0305407024 | Region III (Central Luzon) | Pampanga | Guagua | San Rafael | 14.9618 | 120.6357 | R | 4510 | 4 | 1128 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 0.59 | Tier 2B: Moderate GIDA Inclusion | 69.82 | 69.82 | 38.7 | 54.26 | D - Other node or line within 3 km | 1.41 | 0.55 | Line: foc | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2880
3 | 881 | 2881 | 1404402014 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Monamon Norte | 16.8989 | 120.891 | R | 2809 | 3.7 | 759 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 0.94 | Tier 2B: Moderate GIDA Inclusion | 68.93 | 68.93 | 39.59 | 54.26 | D - Other node or line within 3 km | 1.87 | 0.95 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2881
3 | 882 | 2882 | 0304925006 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Poblacion | 15.307 | 120.905 | U | 8135 | 3.5 | 2324 | 697 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 67.8 | 67.8 | 40.73 | 54.26 | B - Node 0.5-1 km | 0.97 | 0.24 | Line: SANTA ROSA TO ARAYAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 2882
3 | 883 | 2883 | 1907001014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Liyaburan | 5.2544 | 120.1558 | R | 2636 | 5.8 | 454 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 35.75 | 35.75 | 72.76 | 54.26 | F - Nearest node and line over 5 km | 280.84 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2883
3 | 884 | 2884 | 0402108008 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Vibora Pob. | 14.3857 | 120.8807 | R | 960 | 3.4 | 282 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 1.87 | Tier 2B: Moderate GIDA Inclusion | 51.66 | 51.66 | 56.83 | 54.25 | D - Other node or line within 3 km | 1.68 | 1.89 | Node: TRC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2884
3 | 885 | 2885 | 0405813001 | Region IV-A (CALABARZON) | Rizal | Taytay | Dolores | 14.5695 | 121.1618 | U | 72280 | 3.6 | 20078 | 6023 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 2.08 | 1.61 | Tier 1B: High GIDA Priority | 50.33 | 50.33 | 58.16 | 54.25 | D - Other node or line within 3 km | 2.08 | 1.55 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2885
3 | 886 | 2886 | 0501711036 | Region V (Bicol Region) | Camarines Sur | Caramoan | Patag-Belen | 13.8001 | 123.8288 | R | 470 | 4.2 | 112 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.71 | 38.11 | Tier 1B: High GIDA Priority | 44.38 | 44.38 | 64.13 | 54.25 | E - Nearest node or line 3-5 km | 4.71 | 999999 | Node: COC001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2886
3 | 887 | 2887 | 1705309022 | MIMAROPA Region | Palawan | Coron | San Jose | 12.1768 | 120.091 | R | 1916 | 3.9 | 491 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.7 | 107.08 | Tier 1B: High GIDA Priority | 42.78 | 42.78 | 65.73 | 54.25 | F - Nearest node and line over 5 km | 15.7 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2887
3 | 888 | 2888 | 1380601184 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 184 | 14.2438 | 121.774 | U | 2126 | 3.64 | 584 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.37 | 25.89 | Tier 1B: High GIDA Priority | 36.83 | 36.83 | 71.67 | 54.25 | F - Nearest node and line over 5 km | 9.37 | 25.81 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2888
3 | 889 | 2889 | 0804822013 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Giguimitan | 12.3063 | 124.7993 | R | 423 | 4.3 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 83.92 | 83.76 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.82 | 54.25 | F - Nearest node and line over 5 km | 83.92 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2889
3 | 890 | 2890 | 0804807016 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Malidong | 12.3766 | 125.23 | R | 532 | 4.3 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 125.65 | 124.87 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.81 | 54.25 | F - Nearest node and line over 5 km | 125.65 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2890
3 | 891 | 2891 | 1401106007 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Tuding | 16.419 | 120.6406 | U | 10488 | 3.5 | 2997 | 899 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 1.17 | Tier 2B: Moderate GIDA Inclusion | 69.56 | 69.56 | 38.91 | 54.24 | B - Node 0.5-1 km | 0.77 | 1.08 | Node: ITB001 - TYPE 4A | Survey short node lateral; confirm port/fiber capacity, access and route. | 2891
3 | 892 | 2892 | 0307701007 | Region III (Central Luzon) | Aurora | Baler | Calabuanan | 15.7482 | 121.5097 | U | 4098 | 3.8 | 1078 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 61.61 | 61.61 | 46.87 | 54.24 | C - Line within 0.5 km; node over 1 km | 1.74 | 0.03 | Line: BALER - PANTABANGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2892
3 | 893 | 2893 | 0401012046 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ibaba | 13.9349 | 120.9171 | R | 2772 | 3.6 | 770 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2 | 4.07 | Tier 2B: Moderate GIDA Inclusion | 60.94 | 60.94 | 47.55 | 54.24 | D - Other node or line within 3 km | 2 | 4.07 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2893
3 | 894 | 2894 | 0405647005 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone III | 14.0113 | 121.607 | R | 187 | 3.8 | 49 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.18 | Tier 1B: High GIDA Priority | 46.92 | 46.92 | 61.57 | 54.24 | C - Line within 0.5 km; node over 1 km | 2.01 | 0.18 | Line: LILIW - LUCENA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2894
3 | 895 | 2895 | 1108208006 | Region XI (Davao Region) | Davao de Oro | Montevista | Camantangan | 7.7299 | 125.9691 | R | 994 | 3.7 | 269 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.47 | 2.53 | Tier 1B: High GIDA Priority | 38.32 | 38.32 | 70.17 | 54.24 | D - Other node or line within 3 km | 14.47 | 2.53 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2895
3 | 896 | 2896 | 1906610005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kanjarang | 17.2556 | 122.2296 | R | 1808 | 6 | 301 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 36.94 | 36.94 | 71.55 | 54.24 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2896
3 | 897 | 2897 | 0802607027 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Macapagal | 11.2416 | 125.4527 | R | 114 | 3.9 | 29 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.46 | 47.36 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 71.73 | 54.24 | F - Nearest node and line over 5 km | 48.46 | 999999 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2897
3 | 898 | 2898 | 0301415019 | Region III (Central Luzon) | Bulacan | Pandi | Siling Bata | 14.8924 | 120.97 | U | 13147 | 3.5 | 3756 | 1127 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.32 | 0.15 | Tier 2A: High Commercial ROI | 72.44 | 72.44 | 36.03 | 54.23 | A - Node within 0.5 km | 0.32 | 0.13 | Line: PANDI | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2898
3 | 899 | 2899 | 0306916024 | Region III (Central Luzon) | Tarlac | City of Tarlac | Calingcuan | 15.4876 | 120.6225 | R | 3837 | 3.9 | 984 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 69.49 | 69.49 | 38.96 | 54.23 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.44 | Line: SEGMENT 31 (ZARAGOZA - TARLAC) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2899
3 | 900 | 2900 | 0501721009 | Region V (Bicol Region) | Camarines Sur | Milaor | Flordeliz | 13.5899 | 123.1694 | R | 1523 | 4.2 | 363 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 61.65 | 61.65 | 46.8 | 54.23 | C - Line within 0.5 km; node over 1 km | 1.05 | 0.15 | Line: PILI - PAMPLONA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2900
3 | 901 | 2901 | 0403419012 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Barangay I | 14.2478 | 121.4466 | R | 1628 | 3.3 | 493 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 1.3 | Tier 2B: Moderate GIDA Inclusion | 55.67 | 55.67 | 52.8 | 54.23 | D - Other node or line within 3 km | 2.89 | 1.3 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2901
3 | 902 | 2902 | 0205008008 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Ganao | 16.1647 | 121.1809 | R | 1373 | 3.8 | 361 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.15 | 20.99 | Tier 2B: Moderate GIDA Inclusion | 53.35 | 53.35 | 55.1 | 54.23 | A - Node within 0.5 km | 0.15 | 20.97 | Node: DSV001 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2902
3 | 903 | 2903 | 0402116013 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan II | 14.4377 | 120.8852 | R | 3488 | 3.4 | 1026 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.7 | Tier 2A: High Commercial ROI | 70.16 | 70.16 | 38.29 | 54.22 | B - Node 0.5-1 km | 0.94 | 0.65 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 2903
3 | 904 | 2904 | 0604530016 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Sagua Banua | 10.4205 | 122.8698 | R | 3539 | 3.7 | 956 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.31 | 1.74 | Tier 2B: Moderate GIDA Inclusion | 69.94 | 69.94 | 38.51 | 54.22 | D - Other node or line within 3 km | 5.31 | 1.74 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2904
3 | 905 | 2905 | 1907002037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Tarawakan | 14.4836 | 121.6947 | R | 3238 | 5.8 | 558 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.5 | 25.4 | Tier 1B: High GIDA Priority | 49.42 | 49.42 | 59.03 | 54.22 | F - Nearest node and line over 5 km | 7.5 | 25.38 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2905
3 | 906 | 2906 | 1380606008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 402 | 12.5988 | 123.0739 | U | 2778 | 3.4 | 817 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.61 | 40.29 | Tier 1B: High GIDA Priority | 37.76 | 37.76 | 70.69 | 54.22 | F - Nearest node and line over 5 km | 36.61 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2906
3 | 907 | 2907 | 1380606119 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 513 | 13.7659 | 122.4716 | U | 1929 | 4.69 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 2.72 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.69 | 37.69 | 70.75 | 54.22 | D - Other node or line within 3 km | 2.8 | 2.72 | Line: AE LZQ001 TO SNQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2907
3 | 908 | 2908 | 1906615015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Tattalan | 17.2557 | 122.2297 | R | 2792 | 6 | 465 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 71.64 | 54.22 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2908
3 | 909 | 2909 | 0806023012 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Maga-an | 11.667 | 124.8926 | R | 608 | 4.1 | 148 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.45 | 46.34 | Tier 1B: High GIDA Priority | 36.77 | 36.77 | 71.67 | 54.22 | F - Nearest node and line over 5 km | 46.45 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2909
3 | 910 | 2910 | 0806012013 | Region VIII (Eastern Visayas) | Samar | Motiong | Candomacol | 11.8266 | 125.0222 | R | 393 | 4.1 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.3 | 68.3 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 71.75 | 54.22 | F - Nearest node and line over 5 km | 65.3 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2910
3 | 911 | 2911 | 0804824017 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Sampaguita | 12.3067 | 124.6387 | R | 154 | 4.3 | 36 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 68.01 | 68 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.74 | 54.22 | F - Nearest node and line over 5 km | 68.01 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2911
3 | 912 | 2912 | 1404408002 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Belwang | 17.1799 | 121.0106 | R | 870 | 3.7 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 4.03 | Tier 1B: High GIDA Priority | 49.12 | 49.12 | 59.29 | 54.21 | E - Nearest node or line 3-5 km | 3.88 | 3.69 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2912
3 | 913 | 2913 | 0806012022 | Region VIII (Eastern Visayas) | Samar | Motiong | Malonoy | 11.9436 | 125.0471 | R | 159 | 4.1 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.43 | 81.38 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.74 | 54.21 | F - Nearest node and line over 5 km | 78.43 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2913
3 | 914 | 2914 | 0804807014 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Lonoy | 12.3575 | 125.2107 | R | 145 | 4.3 | 34 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 124.16 | 123.41 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.74 | 54.21 | F - Nearest node and line over 5 km | 124.16 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2914
3 | 915 | 2915 | 0702216018 | Region VII (Central Visayas) | Cebu | Catmon | San Jose Pob. | 10.7283 | 124.0127 | R | 3846 | 3.8 | 1012 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.78 | 0.1 | Tier 2A: High Commercial ROI | 73.53 | 73.53 | 34.87 | 54.2 | C - Line within 0.5 km; node over 1 km | 2.78 | 0.06 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2915
3 | 916 | 2916 | 1102319008 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Liboganon | 7.348 | 125.7758 | R | 2850 | 3.7 | 770 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.15 | 4.04 | Tier 2B: Moderate GIDA Inclusion | 58.52 | 58.52 | 49.88 | 54.2 | E - Nearest node or line 3-5 km | 4.15 | 4.03 | Line: DAVAO CITY - TRENTO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2916
3 | 917 | 2917 | 1908705001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Ambolodto | 17.2539 | 122.228 | R | 3188 | 4.3 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.18 | Tier 1B: High GIDA Priority | 43.97 | 43.97 | 64.42 | 54.2 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2917
3 | 918 | 2918 | 0806020021 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Catan-agan | 11.9009 | 124.7523 | R | 67 | 4.1 | 16 | 5 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 67.2 | 67.17 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.71 | 54.2 | F - Nearest node and line over 5 km | 67.2 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2918
3 | 919 | 2919 | 0301414004 | Region III (Central Luzon) | Bulacan | Obando | Lawa | 14.7236 | 120.9283 | U | 9287 | 3.5 | 2653 | 796 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 3.17 | Tier 2B: Moderate GIDA Inclusion | 62.79 | 62.79 | 45.58 | 54.19 | D - Other node or line within 3 km | 1.81 | 3.16 | Node: OBB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2919
3 | 920 | 2920 | 0300809027 | Region III (Central Luzon) | Bataan | Orani | Maria Fe | 14.7793 | 120.4964 | R | 2290 | 3.6 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.99 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 57.65 | 57.65 | 50.72 | 54.19 | C - Line within 0.5 km; node over 1 km | 4.99 | 0.32 | Line: Pipe Dinalupian to Orion | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2920
3 | 921 | 2921 | 0300809018 | Region III (Central Luzon) | Bataan | Orani | Silahis | 14.81 | 120.5117 | R | 609 | 3.6 | 169 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.79 | 1.02 | Tier 1B: High GIDA Priority | 47.18 | 47.18 | 61.2 | 54.19 | D - Other node or line within 3 km | 2.79 | 1.02 | Line: Pipe Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2921
3 | 922 | 2922 | 0401029023 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 1 | 13.871 | 120.9227 | R | 393 | 3.6 | 109 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.81 | 2.46 | Tier 1B: High GIDA Priority | 45.51 | 45.51 | 62.88 | 54.19 | B - Node 0.5-1 km | 0.81 | 2.47 | Node: TLB001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 2922
3 | 923 | 2923 | 1380612003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 835 | 11.9667 | 122.7106 | U | 2943 | 3.37 | 874 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.86 | 20.08 | Tier 1B: High GIDA Priority | 39.24 | 39.24 | 69.14 | 54.19 | F - Nearest node and line over 5 km | 42.21 | 999999 | Node: RCZ001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2923
3 | 924 | 2924 | 0907343014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Guipos | Magting | 7.7581 | 123.3002 | R | 334 | 3.9 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.33 | 8.27 | Tier 1B: High GIDA Priority | 36.85 | 36.85 | 71.53 | 54.19 | F - Nearest node and line over 5 km | 17.33 | 8.22 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2924
3 | 925 | 2925 | 0405806027 | Region IV-A (CALABARZON) | Rizal | Cardona | San Roque | 14.4862 | 121.2265 | R | 2945 | 3.6 | 818 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68.57 | 68.57 | 39.78 | 54.18 | A - Node within 0.5 km | 0.42 | 0.27 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2925
3 | 926 | 2926 | 1401110008 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Betag | 16.4509 | 120.5958 | U | 9549 | 3.5 | 2728 | 818 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 68.52 | 68.52 | 39.84 | 54.18 | B - Node 0.5-1 km | 0.9 | 0.67 | Line: LA TRINIDAD-SAGADA | Survey short node lateral; confirm port/fiber capacity, access and route. | 2926
3 | 927 | 2927 | 1381100191 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 191 | 14.7512 | 121.1168 | U | 3226 | 3.6 | 896 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 55.67 | 55.67 | 52.68 | 54.18 | D - Other node or line within 3 km | 1.62 | 1.53 | Line: Aerial 216C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2927
3 | 928 | 2928 | 0401003010 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 5 | 13.9546 | 120.7417 | U | 1892 | 3.6 | 526 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.91 | 1.03 | Tier 1B: High GIDA Priority | 50.44 | 50.44 | 57.92 | 54.18 | D - Other node or line within 3 km | 1.91 | 1.01 | Line: AE BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2928
3 | 929 | 2929 | 0405619011 | Region IV-A (CALABARZON) | Quezon | Gumaca | Bungahan | 13.9014 | 122.1173 | R | 221 | 3.8 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 1.83 | Tier 1B: High GIDA Priority | 46.08 | 46.08 | 62.28 | 54.18 | D - Other node or line within 3 km | 2.6 | 1.83 | Line: UG GCQ001 TO LZQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2929
3 | 930 | 2930 | 0607903006 | Region VI (Western Visayas) | Guimaras | Nueva Valencia | Guiwanon | 10.3913 | 122.6153 | R | 1929 | 3.8 | 508 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.25 | 23.94 | Tier 1B: High GIDA Priority | 41.41 | 41.41 | 66.95 | 54.18 | F - Nearest node and line over 5 km | 24.25 | 23.93 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2930
3 | 931 | 2931 | 1381100063 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 63 | 14.4803 | 121.0563 | U | 648 | 3.21 | 202 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.89 | 38.89 | 69.48 | 54.18 | B - Node 0.5-1 km | 0.85 | 0.05 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 2931
3 | 932 | 2932 | 0804824003 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Cagamesarag | 12.3275 | 124.5883 | R | 161 | 4.3 | 37 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.09 | 62.08 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 71.67 | 54.18 | F - Nearest node and line over 5 km | 62.09 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2932
3 | 933 | 2933 | 0806012023 | Region VIII (Eastern Visayas) | Samar | Motiong | Mararangsi | 11.8296 | 125.0018 | R | 242 | 4.1 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 65.6 | 67.87 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 71.67 | 54.18 | F - Nearest node and line over 5 km | 65.6 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2933
3 | 934 | 2934 | 0806012020 | Region VIII (Eastern Visayas) | Samar | Motiong | Linonoban | 11.8397 | 125.003 | R | 157 | 4.1 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.73 | 68.93 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.67 | 54.18 | F - Nearest node and line over 5 km | 66.73 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2934
3 | 935 | 2935 | 0804824018 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | San Francisco | 12.2661 | 124.6748 | R | 137 | 4.3 | 32 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 73.6 | 73.59 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.67 | 54.18 | F - Nearest node and line over 5 km | 73.6 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2935
3 | 936 | 2936 | 0806012004 | Region VIII (Eastern Visayas) | Samar | Motiong | Barayong | 11.962 | 124.9917 | R | 174 | 4.1 | 42 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.33 | 80.58 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.67 | 54.18 | F - Nearest node and line over 5 km | 80.33 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2936
3 | 937 | 2937 | 0804807021 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Rizal | 12.3713 | 125.2083 | R | 485 | 4.3 | 113 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 123.51 | 122.75 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.68 | 54.18 | F - Nearest node and line over 5 km | 123.51 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2937
3 | 938 | 2938 | 1903639014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Tabuan | 17.2546 | 122.2286 | R | 984 | 5.7 | 173 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.37 | 34.26 | Tier 1B: High GIDA Priority | 33.64 | 33.64 | 74.72 | 54.18 | F - Nearest node and line over 5 km | 29.37 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2938
3 | 939 | 2939 | 1004313008 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Poblacion | 8.8105 | 124.7899 | R | 4238 | 3.9 | 1087 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.07 | Tier 2A: High Commercial ROI | 77.59 | 77.59 | 30.74 | 54.17 | B - Node 0.5-1 km | 0.6 | 0.07 | Line: CDO - BUENAVISTA via GINGOOG | Survey short node lateral; confirm port/fiber capacity, access and route. | 2939
3 | 940 | 2940 | 0403411015 | Region IV-A (CALABARZON) | Laguna | Los Baños | Malinta | 14.1859 | 121.2301 | U | 7159 | 3.3 | 2169 | 651 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 65.13 | 65.13 | 43.21 | 54.17 | D - Other node or line within 3 km | 1.52 | 0.52 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2940
3 | 941 | 2941 | 0403416026 | Region IV-A (CALABARZON) | Laguna | Majayjay | Origuel | 14.1285 | 121.453 | R | 1585 | 3.3 | 480 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 61.02 | 61.02 | 47.31 | 54.17 | D - Other node or line within 3 km | 2 | 0.77 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2941
3 | 942 | 2942 | 1400108006 | Cordillera Administrative Region (CAR) | Abra | La Paz | Liguis | 17.6518 | 120.633 | R | 1012 | 3.8 | 266 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.72 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 53.65 | 53.65 | 54.68 | 54.17 | D - Other node or line within 3 km | 3.72 | 0.97 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2942
3 | 943 | 2943 | 0305422001 | Region III (Central Luzon) | Pampanga | Sasmuan | Batang 1st | 14.8899 | 120.6193 | R | 317 | 4 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.41 | 5.32 | Tier 1B: High GIDA Priority | 43.97 | 43.97 | 64.37 | 54.17 | F - Nearest node and line over 5 km | 7.41 | 5.27 | Line: foc | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2943
3 | 944 | 2944 | 0806020026 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Lahong | 11.9333 | 124.7635 | R | 238 | 4.1 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 70.91 | 70.88 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.65 | 54.17 | F - Nearest node and line over 5 km | 70.91 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2944
3 | 945 | 2945 | 0806020007 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Bangon Gote | 11.9585 | 124.7117 | R | 145 | 4.1 | 35 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 73.29 | 73.26 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.64 | 54.17 | F - Nearest node and line over 5 km | 73.29 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2945
3 | 946 | 2946 | 0105521009 | Region I (Ilocos Region) | Pangasinan | Labrador | Tobuan | 16.0556 | 120.1097 | R | 3257 | 3.6 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.12 | Tier 2A: High Commercial ROI | 73.64 | 73.64 | 34.68 | 54.16 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.12 | Line: LABRADOR | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2946
3 | 947 | 2947 | 1004311014 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Upper Jasaan | 8.6541 | 124.7541 | R | 4469 | 3.9 | 1146 | 344 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.48 | 0.42 | Tier 2A: High Commercial ROI | 73.51 | 73.51 | 34.81 | 54.16 | A - Node within 0.5 km | 0.48 | 0.42 | Line: CDO - BUENAVISTA via GINGOOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2947
3 | 948 | 2948 | 0603035039 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilawod | 11.1052 | 122.6427 | U | 6043 | 3.8 | 1590 | 477 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 68.59 | 68.59 | 39.73 | 54.16 | A - Node within 0.5 km | 0.38 | 0.18 | Line: ROXAS - ILOILO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 2948
3 | 949 | 2949 | 0301404016 | Region III (Central Luzon) | Bulacan | Bocaue | Taal | 14.8125 | 120.9333 | U | 9493 | 3.5 | 2712 | 814 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.6 | 1.41 | Tier 2B: Moderate GIDA Inclusion | 65.33 | 65.33 | 43 | 54.16 | D - Other node or line within 3 km | 2.6 | 1.58 | Line: STA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2949
3 | 950 | 2950 | 0306916047 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maligaya | 15.4406 | 120.5992 | U | 4331 | 3.9 | 1111 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 60.8 | 60.8 | 47.51 | 54.16 | C - Line within 0.5 km; node over 1 km | 2.35 | 0.1 | Line: PIPE 53-64 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2950
3 | 951 | 2951 | 1381200015 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Pinagbuhatan | 14.5525 | 121.0995 | U | 173576 | 3.55 | 48958 | 14687 | Band n50 (1.5 GHz, 100 MHz TDD) | 15 | 1 | 1.33 | 0.3 | Tier 1B: High GIDA Priority | 46.68 | 46.68 | 61.65 | 54.16 | C - Line within 0.5 km; node over 1 km | 1.33 | 0.15 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2951
3 | 952 | 2952 | 1400126006 | Cordillera Administrative Region (CAR) | Abra | Tubo | Supo | 17.2465 | 120.6862 | R | 766 | 3.8 | 202 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.19 | 5.29 | Tier 1B: High GIDA Priority | 41.54 | 41.54 | 66.78 | 54.16 | F - Nearest node and line over 5 km | 12.19 | 5.22 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2952
3 | 953 | 2953 | 1908713017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Ranao Pilayan | 17.254 | 122.2281 | R | 2384 | 4.3 | 554 | 166 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 39.09 | 39.09 | 69.23 | 54.16 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2953
3 | 954 | 2954 | 1380611043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 828 | 12.3386 | 122.9644 | U | 2715 | 3.39 | 800 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.62 | 54.85 | Tier 1B: High GIDA Priority | 37.32 | 37.32 | 70.99 | 54.16 | F - Nearest node and line over 5 km | 38.62 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2954
3 | 955 | 2955 | 0304909019 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Poblacion | 15.6038 | 121.0509 | R | 4214 | 3.5 | 1204 | 361 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.15 | Tier 2A: High Commercial ROI | 74.83 | 74.83 | 33.47 | 54.15 | C - Line within 0.5 km; node over 1 km | 1.25 | 0.15 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2955
3 | 956 | 2956 | 0702218011 | Region VII (Central Visayas) | Cebu | Compostela | Magay | 10.4716 | 124.0188 | R | 3878 | 3.8 | 1021 | 306 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.29 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 69.85 | 69.85 | 38.45 | 54.15 | C - Line within 0.5 km; node over 1 km | 2.29 | 0.04 | Line: 9.3km FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2956
3 | 957 | 2957 | 1102501006 | Region XI (Davao Region) | Davao Oriental | Baganga | Bobonao | 7.4818 | 126.578 | R | 942 | 3.6 | 262 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.17 | 68.18 | Tier 1B: High GIDA Priority | 33.58 | 33.58 | 74.73 | 54.15 | F - Nearest node and line over 5 km | 69.17 | 999999 | Node: MKD001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2957
3 | 958 | 2958 | 0403426006 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Gatid | 14.2613 | 121.3855 | U | 10962 | 3.3 | 3322 | 997 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.43 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 66.05 | 66.05 | 42.24 | 54.14 | D - Other node or line within 3 km | 3.43 | 0.93 | Line: CLB001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2958
3 | 959 | 2959 | 1402702004 | Cordillera Administrative Region (CAR) | Ifugao | Hungduan | Bangbang | 16.8319 | 121.0253 | R | 603 | 3.9 | 155 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.03 | 5.22 | Tier 1B: High GIDA Priority | 45.2 | 45.2 | 63.08 | 54.14 | F - Nearest node and line over 5 km | 7.03 | 5.17 | Line: HINGYON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2959
3 | 960 | 2960 | 1380605015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 313 | 12.6522 | 120.4505 | U | 3587 | 4.28 | 839 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74.62 | 73 | Tier 1B: High GIDA Priority | 38.37 | 38.37 | 69.91 | 54.14 | F - Nearest node and line over 5 km | 74.62 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2960
3 | 961 | 2961 | 0802623004 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Bongdo | 11.9384 | 125.4014 | R | 266 | 3.9 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 89.04 | 91.3 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.6 | 54.14 | F - Nearest node and line over 5 km | 89.04 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2961
3 | 962 | 2962 | 0405623004 | Region IV-A (CALABARZON) | Quezon | Lucban | Ayuti | 14.1169 | 121.5487 | U | 10218 | 3.8 | 2689 | 807 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 67.5 | 67.5 | 40.76 | 54.13 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.05 | Line: LILIW - LUCENA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2962
3 | 963 | 2963 | 0301407011 | Region III (Central Luzon) | Bulacan | Calumpit | Gatbuca | 14.9228 | 120.769 | U | 6673 | 3.5 | 1907 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 63.99 | 63.99 | 44.27 | 54.13 | C - Line within 0.5 km; node over 1 km | 1.84 | 0.37 | Line: 24 CORE (3X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2963
3 | 964 | 2964 | 0301410045 | Region III (Central Luzon) | Bulacan | City of Malolos | San Vicente | 14.8477 | 120.8185 | U | 2511 | 3.5 | 717 | 215 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 57.55 | 57.55 | 50.7 | 54.13 | B - Node 0.5-1 km | 0.83 | 0.36 | Line: 48 CORE (6X8) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2964
3 | 965 | 2965 | 0301404006 | Region III (Central Luzon) | Bulacan | Bocaue | Biñang 2nd | 14.811 | 120.9441 | U | 2209 | 3.5 | 631 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 54.11 | 54.11 | 54.14 | 54.13 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.41 | Line: STA MARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2965
3 | 966 | 2966 | 1381100126 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 126 | 14.6818 | 120.928 | U | 805 | 3.11 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.65 | 1.52 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.94 | 38.94 | 69.33 | 54.13 | D - Other node or line within 3 km | 1.65 | 1.43 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2966
3 | 967 | 2967 | 1380601180 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 180 | 14.0046 | 122.0298 | U | 2160 | 4.21 | 513 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.48 | 5.11 | Tier 1B: High GIDA Priority | 38.01 | 38.01 | 70.26 | 54.13 | F - Nearest node and line over 5 km | 5.48 | 5.1 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2967
3 | 968 | 2968 | 0806025005 | Region VIII (Eastern Visayas) | Samar | San Jorge | Bungliw | 11.9026 | 124.9051 | R | 254 | 4.1 | 62 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 71.02 | 70.96 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.57 | 54.13 | F - Nearest node and line over 5 km | 71.02 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2968
3 | 969 | 2969 | 0907216006 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Lakiki | 7.2746 | 122.0837 | R | 648 | 3.6 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.89 | 17.71 | Tier 1B: High GIDA Priority | 32.68 | 32.68 | 75.58 | 54.13 | F - Nearest node and line over 5 km | 19.89 | 17.7 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2969
3 | 970 | 2970 | 1401112011 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Poblacion | 16.5022 | 120.4757 | R | 2816 | 3.5 | 805 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.22 | Tier 2A: High Commercial ROI | 71.35 | 71.35 | 36.88 | 54.12 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.17 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2970
3 | 971 | 2971 | 0300812010 | Region III (Central Luzon) | Bataan | Samal | Santa Lucia | 14.7626 | 120.5397 | R | 2669 | 3.6 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.4 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 65.37 | 65.37 | 42.86 | 54.12 | C - Line within 0.5 km; node over 1 km | 4.4 | 0.12 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2971
3 | 972 | 2972 | 0600403026 | Region VI (Western Visayas) | Aklan | Banga | Tabayon | 11.6327 | 122.347 | R | 2005 | 3.9 | 514 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 61.18 | 61.18 | 47.06 | 54.12 | B - Node 0.5-1 km | 0.71 | 0.64 | Line: IVISAN - KALIBO | Survey short node lateral; confirm port/fiber capacity, access and route. | 2972
3 | 973 | 2973 | 0403425019 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | United Better Living | 14.1763 | 121.451 | U | 6801 | 3.3 | 2061 | 618 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.28 | 2.07 | Tier 2B: Moderate GIDA Inclusion | 58.83 | 58.83 | 49.42 | 54.12 | D - Other node or line within 3 km | 3.28 | 2.06 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2973
3 | 974 | 2974 | 0403425003 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Estrella | 14.107 | 121.229 | U | 8797 | 3.3 | 2666 | 800 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.2 | 4.93 | Tier 2B: Moderate GIDA Inclusion | 58.51 | 58.51 | 49.73 | 54.12 | E - Nearest node or line 3-5 km | 6.2 | 4.93 | Line: CLB001 TO SPO001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2974
3 | 975 | 2975 | 1908819002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Bakat | 17.2552 | 122.2292 | R | 2579 | 4.7 | 549 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 34.34 | Tier 1B: High GIDA Priority | 38.99 | 38.99 | 69.26 | 54.12 | F - Nearest node and line over 5 km | 29.46 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2975
3 | 976 | 2976 | 1102510015 | Region XI (Davao Region) | Davao Oriental | San Isidro | Santo Rosario | 6.8141 | 126.154 | R | 930 | 3.6 | 258 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.3 | 8.55 | Tier 1B: High GIDA Priority | 36.63 | 36.63 | 71.62 | 54.12 | F - Nearest node and line over 5 km | 17.3 | 8.55 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2976
3 | 977 | 2977 | 0702243002 | Region VII (Central Visayas) | Cebu | San Remigio | Argawanon | 11.0703 | 123.9573 | R | 4845 | 3.8 | 1275 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 0.08 | Tier 2A: High Commercial ROI | 71.79 | 71.79 | 36.43 | 54.11 | C - Line within 0.5 km; node over 1 km | 2.39 | 0.02 | Line: FRONTHAUL - SAN REMIGIO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 2977
3 | 978 | 2978 | 0301414010 | Region III (Central Luzon) | Bulacan | Obando | San Pascual | 14.7206 | 120.9297 | U | 8121 | 3.5 | 2320 | 696 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 2.97 | Tier 2B: Moderate GIDA Inclusion | 62.38 | 62.38 | 45.85 | 54.11 | D - Other node or line within 3 km | 1.45 | 2.96 | Node: OBB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2978
3 | 979 | 2979 | 1003516001 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Aloon | 8.0636 | 124.1974 | R | 1779 | 4.2 | 424 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.35 | 5.75 | Tier 1B: High GIDA Priority | 49.63 | 49.63 | 58.58 | 54.11 | F - Nearest node and line over 5 km | 10.35 | 5.72 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2979
3 | 980 | 2980 | 1408104015 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Madduang | 18.0128 | 121.1267 | R | 637 | 4.2 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.8 | 12.82 | Tier 1B: High GIDA Priority | 41.16 | 41.16 | 67.06 | 54.11 | F - Nearest node and line over 5 km | 5.8 | 47.68 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2980
3 | 981 | 2981 | 1380606167 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 561 | 13.9716 | 121.2517 | U | 2387 | 4.42 | 540 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.3 | 7.42 | Tier 1B: High GIDA Priority | 38.81 | 38.81 | 69.41 | 54.11 | F - Nearest node and line over 5 km | 5.3 | 7.42 | Node: SPO003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2981
3 | 982 | 2982 | 1380601156 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 156 | 13.8148 | 121.9867 | U | 1627 | 4.05 | 402 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 2.22 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.52 | 37.52 | 70.7 | 54.11 | D - Other node or line within 3 km | 2.8 | 2.15 | Line: UNISAN TO MULANAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2982
3 | 983 | 2983 | 0802623015 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Pangabutan | 11.9578 | 125.3931 | R | 229 | 3.9 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 90.49 | 92.81 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.53 | 54.11 | F - Nearest node and line over 5 km | 90.49 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2983
3 | 984 | 2984 | 0501603028 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay V | 14.1212 | 122.9497 | U | 4639 | 4 | 1160 | 348 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 1.21 | Tier 2B: Moderate GIDA Inclusion | 66.56 | 66.56 | 41.64 | 54.1 | B - Node 0.5-1 km | 0.85 | 1.21 | Node: DEC001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 2984
3 | 985 | 2985 | 0102820007 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Eugenio | 18.1649 | 120.5914 | R | 1037 | 3.7 | 280 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 53.65 | 53.65 | 54.55 | 54.1 | B - Node 0.5-1 km | 0.64 | 0.12 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Survey short node lateral; confirm port/fiber capacity, access and route. | 2985
3 | 986 | 2986 | 1600304013 | Region XIII (Caraga) | Agusan del Sur | La Paz | Sabang Adgawan | 8.3086 | 125.8767 | R | 1861 | 3.9 | 477 | 143 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.03 | 12.64 | Tier 1B: High GIDA Priority | 43.6 | 43.6 | 64.59 | 54.1 | F - Nearest node and line over 5 km | 14.03 | 12.63 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2986
3 | 987 | 2987 | 0401005078 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 9 | 13.6856 | 121.0764 | U | 265 | 3.6 | 74 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 8.05 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.95 | 36.95 | 71.25 | 54.1 | D - Other node or line within 3 km | 1.38 | 8.03 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2987
3 | 988 | 2988 | 0603015008 | Region VI (Western Visayas) | Iloilo | Concepcion | Botlog | 11.2294 | 123.1554 | R | 465 | 3.8 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.38 | 8.52 | Tier 1B: High GIDA Priority | 36.29 | 36.29 | 71.92 | 54.1 | F - Nearest node and line over 5 km | 15.38 | 8.22 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2988
3 | 989 | 2989 | 1903621012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Katumbacan | 16.8731 | 122.2636 | R | 744 | 5.7 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.43 | 38.81 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 75.61 | 54.1 | F - Nearest node and line over 5 km | 29.43 | 999999 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2989
3 | 990 | 2990 | 0103317006 | Region I (Ilocos Region) | La Union | Santo Tomas | Cabaruan | 16.2701 | 120.3604 | R | 1733 | 3.7 | 468 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 3.36 | Tier 2B: Moderate GIDA Inclusion | 55.3 | 55.3 | 52.87 | 54.09 | E - Nearest node or line 3-5 km | 3.55 | 3.37 | Line: SANTO TOMAS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2990
3 | 991 | 2991 | 0405605023 | Region IV-A (CALABARZON) | Quezon | Buenavista | Maligaya | 13.707 | 122.3936 | R | 876 | 3.8 | 231 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.13 | 7.86 | Tier 1B: High GIDA Priority | 45.63 | 45.63 | 62.55 | 54.09 | F - Nearest node and line over 5 km | 8.13 | 7.85 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2991
3 | 992 | 2992 | 1705318033 | MIMAROPA Region | Palawan | Roxas | Barangay VI Pob. | 10.2526 | 119.384 | R | 714 | 3.9 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.44 | 8.44 | Tier 1B: High GIDA Priority | 40.93 | 40.93 | 67.26 | 54.09 | F - Nearest node and line over 5 km | 8.44 | 8.4 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2992
3 | 993 | 2993 | 1908709023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Samberen | 16.1899 | 122.4415 | R | 2286 | 4.3 | 532 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.22 | 34.22 | Tier 1B: High GIDA Priority | 38.19 | 38.19 | 69.99 | 54.09 | F - Nearest node and line over 5 km | 35.22 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2993
3 | 994 | 2994 | 0806025019 | Region VIII (Eastern Visayas) | Samar | San Jorge | Mobo-ob | 11.9731 | 124.9191 | R | 185 | 4.1 | 45 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.94 | 78.88 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.49 | 54.09 | F - Nearest node and line over 5 km | 78.94 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2994
3 | 995 | 2995 | 0806016010 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Camperito | 12.1239 | 124.744 | R | 245 | 4.1 | 60 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 88.44 | 88.43 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.5 | 54.09 | F - Nearest node and line over 5 km | 88.44 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2995
3 | 996 | 2996 | 1906613021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Kuhaw | 17.2554 | 122.2295 | R | 2766 | 6 | 461 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 36.63 | 36.63 | 71.56 | 54.09 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2996
3 | 997 | 2997 | 1906615012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Tainga-Bakkao | 17.2557 | 122.2297 | R | 2763 | 6 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 36.62 | 36.62 | 71.56 | 54.09 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2997
3 | 998 | 2998 | 1380601025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 25 | 13.2055 | 123.0213 | U | 3000 | 4.25 | 706 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.27 | 33.12 | Tier 1B: High GIDA Priority | 34.88 | 34.88 | 73.31 | 54.09 | F - Nearest node and line over 5 km | 26.27 | 33.04 | Node: BNC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2998
3 | 999 | 2999 | 0704603006 | Region VII (Central Visayas) | Negros Oriental | Bacong | Combado | 9.2506 | 123.2765 | R | 3914 | 3.8 | 1030 | 309 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.45 | 1.44 | Tier 2A: High Commercial ROI | 75.89 | 75.89 | 32.26 | 54.08 | D - Other node or line within 3 km | 1.45 | 1.35 | Line: FRONTHAUL-BACONG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 2999
3 | 1000 | 3000 | 0304927002 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Bonifacio District | 15.3553 | 120.9484 | R | 3590 | 3.5 | 1026 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 69.18 | 69.18 | 38.98 | 54.08 | D - Other node or line within 3 km | 1.61 | 0.98 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3000

## Batch 4 & 5 (3,001 - 5,000)
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization — Batch 4 & 5 (3,001 - 5,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
4 | 1 | 3001 | 0301410055 | Region III (Central Luzon) | Bulacan | City of Malolos | Tikay | 14.8406 | 120.8539 | U | 13170 | 3.5 | 3763 | 1129 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.42 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 68.77 | 68.77 | 39.4 | 54.08 | C - Line within 0.5 km; node over 1 km | 2.42 | 0.04 | Line: MALOLOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3001
4 | 2 | 3002 | 0403410032 | Region IV-A (CALABARZON) | Laguna | Liliw | Pag-Asa | 14.1856 | 121.43 | R | 1194 | 3.3 | 362 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 58.78 | 58.78 | 49.37 | 54.08 | C - Line within 0.5 km; node over 1 km | 1.42 | 0.21 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3002
4 | 3 | 3003 | 0103306001 | Region I (Ilocos Region) | La Union | Bangar | Agdeppa | 16.8845 | 120.4338 | R | 1328 | 3.7 | 359 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 1.33 | Tier 2B: Moderate GIDA Inclusion | 54.46 | 54.46 | 53.69 | 54.08 | D - Other node or line within 3 km | 1.35 | 1.33 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3003
4 | 4 | 3004 | 1600311008 | Region XIII (Caraga) | Agusan del Sur | Talacogon | Sabang Gibung | 8.3228 | 125.8906 | R | 834 | 3.9 | 214 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.72 | 12.06 | Tier 1B: High GIDA Priority | 38.07 | 38.07 | 70.1 | 54.08 | F - Nearest node and line over 5 km | 12.72 | 12.03 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3004
4 | 5 | 3005 | 0702212005 | Region VII (Central Visayas) | Cebu | Boljoon | Poblacion | 9.6253 | 123.4801 | R | 4263 | 3.8 | 1122 | 337 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.2 | 0.21 | Tier 2A: High Commercial ROI | 79.81 | 79.81 | 28.32 | 54.07 | A - Node within 0.5 km | 0.2 | 0.17 | Line: Alcoy-Boljoon | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3005
4 | 6 | 3006 | 1004319003 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Cabug | 8.9033 | 125.0239 | R | 2922 | 3.9 | 749 | 225 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.57 | Tier 2A: High Commercial ROI | 70.2 | 70.2 | 37.94 | 54.07 | D - Other node or line within 3 km | 1.05 | 0.56 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3006
4 | 7 | 3007 | 0702208006 | Region VII (Central Visayas) | Cebu | Balamban | Buanoy | 10.4671 | 123.7004 | U | 14411 | 3.8 | 3792 | 1138 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.91 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 68.07 | 68.07 | 40.08 | 54.07 | C - Line within 0.5 km; node over 1 km | 4.91 | 0.06 | Line: 104.3km-96FOC-toledo-san remigio | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3007
4 | 8 | 3008 | 0301417003 | Region III (Central Luzon) | Bulacan | Plaridel | Banga I | 14.8856 | 120.8646 | U | 6159 | 3.5 | 1760 | 528 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 62.72 | 62.72 | 45.42 | 54.07 | C - Line within 0.5 km; node over 1 km | 2.39 | 0.14 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3008
4 | 9 | 3009 | 0401033011 | Region IV-A (CALABARZON) | Batangas | Tingloy | San Isidro | 13.626 | 120.9092 | R | 1661 | 3.6 | 461 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.19 | 13.29 | Tier 2B: Moderate GIDA Inclusion | 52.8 | 52.8 | 55.34 | 54.07 | F - Nearest node and line over 5 km | 7.19 | 13.29 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3009
4 | 10 | 3010 | 1380601062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 62 | 13.8818 | 121.3482 | U | 1877 | 4.3 | 437 | 131 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.9 | 2.12 | Tier 1B: High GIDA Priority | 35.78 | 35.78 | 72.37 | 54.07 | F - Nearest node and line over 5 km | 5.9 | 5.1 | Line: AERIAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3010
4 | 11 | 3011 | 0305409003 | Region III (Central Luzon) | Pampanga | Mabalacat City | Bundagul | 15.2159 | 120.5774 | U | 4122 | 4 | 1030 | 309 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.75 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 61.47 | 61.47 | 46.66 | 54.06 | C - Line within 0.5 km; node over 1 km | 1.75 | 0.03 | Line: PIPE HH1-HH38 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3011
4 | 12 | 3012 | 1900710002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Mohammad Ajul | Buton | 6.5997 | 122.23 | R | 5749 | 5.1 | 1127 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.61 | 38.6 | Tier 1B: High GIDA Priority | 49.18 | 49.18 | 58.95 | 54.06 | F - Nearest node and line over 5 km | 38.61 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3012
4 | 13 | 3013 | 1908804004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Midtimbang | 17.2552 | 122.2292 | R | 4384 | 4.7 | 933 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 49.02 | 49.02 | 59.1 | 54.06 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3013
4 | 14 | 3014 | 1381100199 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 199 | 14.2926 | 120.9813 | U | 2316 | 3.57 | 648 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.51 | 2.4 | Tier 1B: High GIDA Priority | 44.28 | 44.28 | 63.84 | 54.06 | D - Other node or line within 3 km | 2.51 | 2.43 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3014
4 | 15 | 3015 | 0806016011 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Campeig | 12.0505 | 124.7064 | R | 84 | 4.1 | 20 | 6 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 83.49 | 83.44 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.43 | 54.06 | F - Nearest node and line over 5 km | 83.49 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3015
4 | 16 | 3016 | 0402106012 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran I | 14.3149 | 120.954 | U | 5430 | 3.4 | 1597 | 479 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 1.46 | Tier 2B: Moderate GIDA Inclusion | 63.76 | 63.76 | 44.35 | 54.05 | D - Other node or line within 3 km | 1.29 | 1.39 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3016
4 | 17 | 3017 | 0307702003 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 3 | 16.2431 | 122.1032 | R | 177 | 3.8 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.6 | 2.32 | Tier 1B: High GIDA Priority | 40.77 | 40.77 | 67.34 | 54.05 | E - Nearest node or line 3-5 km | 4.6 | 999999 | Node: CSA001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3017
4 | 18 | 3018 | 0504106027 | Region V (Bicol Region) | Masbate | Cawayan | Taberna | 12.0701 | 123.7169 | R | 1588 | 4.1 | 387 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.11 | 27.98 | Tier 1B: High GIDA Priority | 39.93 | 39.93 | 68.17 | 54.05 | F - Nearest node and line over 5 km | 19.11 | 27.99 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3018
4 | 19 | 3019 | 1380606236 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 629 | 13.6966 | 122.3079 | U | 1640 | 4.07 | 403 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.71 | 9.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.64 | 37.64 | 70.46 | 54.05 | D - Other node or line within 3 km | 2.71 | 9.28 | Node: CTQ004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3019
4 | 20 | 3020 | 0806014015 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Hibaca-an | 12.0521 | 125.0218 | R | 450 | 4.1 | 110 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 90.37 | 91.08 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.41 | 54.05 | F - Nearest node and line over 5 km | 90.37 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3020
4 | 21 | 3021 | 0603040086 | Region VI (Western Visayas) | Iloilo | San Joaquin | Torocadan | 10.6169 | 122.039 | R | 227 | 3.8 | 60 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.58 | 2.11 | Tier 1B: High GIDA Priority | 34.61 | 34.61 | 73.49 | 54.05 | D - Other node or line within 3 km | 19.58 | 2.11 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3021
4 | 22 | 3022 | 0201509011 | Region II (Cagayan Valley) | Cagayan | Calayan | Dalupiri | 19.0605 | 121.2463 | R | 638 | 3.9 | 164 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.23 | 50.18 | Tier 1B: High GIDA Priority | 29.43 | 29.43 | 78.67 | 54.05 | F - Nearest node and line over 5 km | 54.23 | 999999 | Node: CEC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3022
4 | 23 | 3023 | 1004301012 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Sungay | 8.5506 | 124.469 | R | 1940 | 3.9 | 497 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 2.35 | Tier 2B: Moderate GIDA Inclusion | 58.47 | 58.47 | 49.61 | 54.04 | D - Other node or line within 3 km | 2.33 | 2.35 | Node: AJM001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3023
4 | 24 | 3024 | 1102403001 | Region XI (Davao Region) | Davao del Sur | City of Digos | Aplaya | 6.7385 | 125.3804 | U | 19931 | 3.4 | 5862 | 1759 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.77 | 1.34 | Tier 2A: High Commercial ROI | 72.56 | 72.56 | 35.49 | 54.03 | D - Other node or line within 3 km | 1.77 | 1.34 | Line: Digos to POI of existing aerial 96F | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3024
4 | 25 | 3025 | 0402115016 | Region IV-A (CALABARZON) | Cavite | Naic | Latoria | 14.3184 | 120.7716 | R | 2301 | 3.4 | 677 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 64.89 | 64.89 | 43.17 | 54.03 | A - Node within 0.5 km | 0.36 | 0.04 | Line: NCC001 TO NSB001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3025
4 | 26 | 3026 | 1108202020 | Region XI (Davao Region) | Davao de Oro | Laak | Bagong Silang | 7.7424 | 125.7642 | R | 968 | 3.7 | 262 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.87 | 17.57 | Tier 1B: High GIDA Priority | 34.09 | 34.09 | 73.97 | 54.03 | F - Nearest node and line over 5 km | 31.87 | 25.15 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3026
4 | 27 | 3027 | 0304916018 | Region III (Central Luzon) | Nueva Ecija | Lupao | Parista | 15.8631 | 120.9193 | R | 4851 | 3.5 | 1386 | 416 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 67.92 | 67.92 | 40.13 | 54.02 | D - Other node or line within 3 km | 3.32 | 0.54 | Line: LUPAO - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3027
4 | 28 | 3028 | 0301410050 | Region III (Central Luzon) | Bulacan | City of Malolos | Santo Rosario | 14.8532 | 120.8177 | U | 7665 | 3.5 | 2190 | 657 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.22 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 67.9 | 67.9 | 40.14 | 54.02 | A - Node within 0.5 km | 0.22 | 0.1 | Line: BOUND TO GGT | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3028
4 | 29 | 3029 | 0105533017 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw East | 16.1265 | 120.4002 | R | 2555 | 3.6 | 710 | 213 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 64.21 | 64.21 | 43.83 | 54.02 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.47 | Line: SAN FABIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3029
4 | 30 | 3030 | 0806025018 | Region VIII (Eastern Visayas) | Samar | San Jorge | Matalud | 11.9995 | 124.9016 | R | 538 | 4.1 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.17 | 81.12 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.36 | 54.02 | F - Nearest node and line over 5 km | 81.17 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3030
4 | 31 | 3031 | 0806016036 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Matayonas | 12.1239 | 124.744 | R | 122 | 4.1 | 30 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 88.43 | 88.42 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.36 | 54.02 | F - Nearest node and line over 5 km | 88.43 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3031
4 | 32 | 3032 | 0806022045 | Region VIII (Eastern Visayas) | Samar | Paranas | Tigbawon | 11.7392 | 125.0465 | R | 1078 | 4.1 | 263 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.76 | 58.71 | Tier 1B: High GIDA Priority | 34.62 | 34.62 | 73.42 | 54.02 | F - Nearest node and line over 5 km | 55.76 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3032
4 | 33 | 3033 | 0702202006 | Region VII (Central Visayas) | Cebu | Alcoy | Poblacion | 9.7097 | 123.5073 | R | 4032 | 3.8 | 1061 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.14 | 0.14 | Tier 2A: High Commercial ROI | 79.14 | 79.14 | 28.89 | 54.01 | A - Node within 0.5 km | 0.14 | 0.14 | Line: Dalaguete-Alcoy | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3033
4 | 34 | 3034 | 0305410008 | Region III (Central Luzon) | Pampanga | Macabebe | San Esteban | 14.8549 | 120.6478 | U | 6953 | 4 | 1738 | 521 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.53 | 8.64 | Tier 2B: Moderate GIDA Inclusion | 55.44 | 55.44 | 52.58 | 54.01 | F - Nearest node and line over 5 km | 7.53 | 10.2 | Node: MSP001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3034
4 | 35 | 3035 | 1380608011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 669 | 12.4261 | 123.0524 | U | 3738 | 2.95 | 1265 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.03 | 42.78 | Tier 1B: High GIDA Priority | 41.85 | 41.85 | 66.18 | 54.01 | F - Nearest node and line over 5 km | 33.03 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3035
4 | 36 | 3036 | 0603040073 | Region VI (Western Visayas) | Iloilo | San Joaquin | San Mateo Norte | 10.64 | 122.0644 | R | 192 | 3.8 | 51 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.39 | 5.89 | Tier 1B: High GIDA Priority | 34.67 | 34.67 | 73.35 | 54.01 | F - Nearest node and line over 5 km | 19.39 | 5.88 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3036
4 | 37 | 3037 | 1903638013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Kalilangan | 17.2679 | 122.2336 | R | 545 | 5.7 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.74 | 35.22 | Tier 1B: High GIDA Priority | 32.49 | 32.49 | 75.52 | 54.01 | F - Nearest node and line over 5 km | 30.74 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3037
4 | 38 | 3038 | 0301420013 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin I | 14.8248 | 121.0705 | R | 4280 | 3.5 | 1223 | 367 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 2.76 | Tier 2B: Moderate GIDA Inclusion | 67.25 | 67.25 | 40.75 | 54 | D - Other node or line within 3 km | 1.06 | 3.44 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3038
4 | 39 | 3039 | 0806009013 | Region VIII (Eastern Visayas) | Samar | Jiabong | Hinaga | 11.7624 | 124.9502 | R | 290 | 4.1 | 71 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 58.4 | 58.64 | Tier 1B: High GIDA Priority | 36.71 | 36.71 | 71.29 | 54 | F - Nearest node and line over 5 km | 58.4 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3039
4 | 40 | 3040 | 0405807015 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Special District | 14.3541 | 121.324 | R | 4320 | 3.6 | 1200 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 11.66 | Tier 2A: High Commercial ROI | 72.88 | 72.88 | 35.1 | 53.99 | A - Node within 0.5 km | 0.35 | 11.62 | Node: JLR001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3040
4 | 41 | 3041 | 1380601120 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 120 | 13.6351 | 120.5577 | U | 3886 | 4.77 | 815 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.83 | 22.91 | Tier 1B: High GIDA Priority | 37.67 | 37.67 | 70.3 | 53.99 | F - Nearest node and line over 5 km | 22.83 | 22.82 | Line: BALAYAN - CALATAGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3041
4 | 42 | 3042 | 1381100167 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 167 | 14.3468 | 121.0868 | U | 626 | 3.42 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.87 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.19 | 37.19 | 70.79 | 53.99 | D - Other node or line within 3 km | 1.5 | 0.87 | Line: RELIANCE TO SAN PABLO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3042
4 | 43 | 3043 | 0806016013 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Canmoros | 12.0562 | 124.7307 | R | 218 | 4.1 | 53 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.23 | 84.21 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.29 | 53.99 | F - Nearest node and line over 5 km | 84.23 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3043
4 | 44 | 3044 | 1903610038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Pantaon | 17.2544 | 122.2284 | R | 1585 | 5.7 | 278 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 36.34 | 36.34 | 71.63 | 53.99 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3044
4 | 45 | 3045 | 1380601031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 31 | 11.9901 | 120.7781 | U | 3101 | 4.61 | 672 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50.78 | 50.79 | Tier 1B: High GIDA Priority | 34 | 34 | 73.98 | 53.99 | F - Nearest node and line over 5 km | 50.78 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3045
4 | 46 | 3046 | 0803748041 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Canramos | 11.1062 | 125.0142 | R | 3407 | 3.8 | 897 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 69.94 | 69.94 | 38.01 | 53.98 | B - Node 0.5-1 km | 0.63 | 6.32 | Node: TAL001-TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3046
4 | 47 | 3047 | 1404402012 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Mabaay | 16.917 | 120.8873 | R | 1289 | 3.7 | 348 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.18 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 61.29 | 61.29 | 46.67 | 53.98 | A - Node within 0.5 km | 0.18 | 1.66 | Node: BOV002-PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3047
4 | 48 | 3048 | 1003516023 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Tongcopan | 8.0595 | 124.2027 | R | 1421 | 4.2 | 338 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.62 | 5.64 | Tier 1B: High GIDA Priority | 48.27 | 48.27 | 59.69 | 53.98 | F - Nearest node and line over 5 km | 9.62 | 5.57 | Line: PANTAR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3048
4 | 49 | 3049 | 1705320016 | MIMAROPA Region | Palawan | Taytay | Old Guinlo | 10.7993 | 119.4363 | R | 1233 | 3.9 | 316 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.2 | 6.78 | Tier 1B: High GIDA Priority | 44.56 | 44.56 | 63.39 | 53.98 | F - Nearest node and line over 5 km | 8.2 | 6.71 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3049
4 | 50 | 3050 | 1381100006 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 6 | 14.5379 | 121.0154 | U | 595 | 3.02 | 197 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.39 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.72 | 37.72 | 70.24 | 53.98 | C - Line within 0.5 km; node over 1 km | 1.39 | 0.17 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3050
4 | 51 | 3051 | 0806009011 | Region VIII (Eastern Visayas) | Samar | Jiabong | Dogongan | 11.9107 | 124.9939 | R | 498 | 4.1 | 121 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74.63 | 75.51 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.27 | 53.98 | F - Nearest node and line over 5 km | 74.63 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3051
4 | 52 | 3052 | 0600409007 | Region VI (Western Visayas) | Aklan | Libacao | Can-Awan | 11.4347 | 122.3233 | R | 437 | 3.9 | 112 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.76 | 14.65 | Tier 1B: High GIDA Priority | 36.61 | 36.61 | 71.34 | 53.98 | F - Nearest node and line over 5 km | 14.76 | 14.65 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3052
4 | 53 | 3053 | 0603040040 | Region VI (Western Visayas) | Iloilo | San Joaquin | Igdagmay | 10.6703 | 122.0935 | R | 191 | 3.8 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.83 | 9.68 | Tier 1B: High GIDA Priority | 34.53 | 34.53 | 73.42 | 53.98 | F - Nearest node and line over 5 km | 19.83 | 9.59 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3053
4 | 54 | 3054 | 0105522021 | Region I (Ilocos Region) | Pangasinan | Lingayen | Maniboc | 16.0194 | 120.2312 | U | 8214 | 3.6 | 2282 | 685 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 67.72 | 67.72 | 40.23 | 53.97 | A - Node within 0.5 km | 0.43 | 0.03 | Line: DAGUPAN - ALAMINOS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3054
4 | 55 | 3055 | 0301412014 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Longos | 14.7371 | 120.9481 | R | 3034 | 3.5 | 867 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.66 | 1.33 | Tier 2B: Moderate GIDA Inclusion | 67.61 | 67.61 | 40.33 | 53.97 | D - Other node or line within 3 km | 1.66 | 1.33 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3055
4 | 56 | 3056 | 0201529014 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 11 | 17.6233 | 121.7342 | U | 3461 | 3.9 | 887 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.41 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 58.27 | 58.27 | 49.67 | 53.97 | C - Line within 0.5 km; node over 1 km | 3.41 | 0.34 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3056
4 | 57 | 3057 | 0600404011 | Region VI (Western Visayas) | Aklan | Batan | Magpag-ong | 11.5753 | 122.4743 | R | 1370 | 3.9 | 351 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.76 | 3.88 | Tier 2B: Moderate GIDA Inclusion | 53.19 | 53.19 | 54.75 | 53.97 | E - Nearest node or line 3-5 km | 4.76 | 3.86 | Line: IVISAN - KALIBO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3057
4 | 58 | 3058 | 1380601185 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 185 | 11.494 | 121.8361 | U | 3399 | 4.22 | 806 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 51.91 | 45.49 | Tier 1B: High GIDA Priority | 37.5 | 37.5 | 70.44 | 53.97 | F - Nearest node and line over 5 km | 51.91 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3058
4 | 59 | 3059 | 0401009013 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Felipe | 13.8914 | 121.0399 | R | 4012 | 3.6 | 1114 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 0.76 | Tier 2A: High Commercial ROI | 74.32 | 74.32 | 33.6 | 53.96 | D - Other node or line within 3 km | 1.26 | 0.76 | Line: UG BUN001 TO SSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3059
4 | 60 | 3060 | 0105526014 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guilig | 16.0666 | 120.4007 | R | 3480 | 3.6 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.43 | Tier 2A: High Commercial ROI | 71.69 | 71.69 | 36.23 | 53.96 | A - Node within 0.5 km | 0.21 | 0.45 | Node: MDP001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3060
4 | 61 | 3061 | 0600613005 | Region VI (Western Visayas) | Antique | San Jose | Barangay 3 | 12.3554 | 121.0673 | R | 3574 | 3.9 | 916 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.14 | Tier 2A: High Commercial ROI | 70.46 | 70.46 | 37.46 | 53.96 | B - Node 0.5-1 km | 0.59 | 0.11 | Line: ROXAS - SAN JOSE | Survey short node lateral; confirm port/fiber capacity, access and route. | 3061
4 | 62 | 3062 | 0301423004 | Region III (Central Luzon) | Bulacan | Santa Maria | Bulac | 14.8444 | 120.9803 | U | 10468 | 3.5 | 2991 | 897 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.7 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 66.04 | 66.04 | 41.89 | 53.96 | C - Line within 0.5 km; node over 1 km | 2.7 | 0.04 | Line: STA. MARIA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3062
4 | 63 | 3063 | 1380610042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 727 | 12.3259 | 120.8823 | U | 2842 | 3.52 | 808 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20 | 19.51 | Tier 1B: High GIDA Priority | 37.5 | 37.5 | 70.43 | 53.96 | F - Nearest node and line over 5 km | 20 | 19.51 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3063
4 | 64 | 3064 | 1380400006 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Dampalit | 14.6893 | 120.9403 | U | 13710 | 3.45 | 3974 | 1192 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.51 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 65.83 | 65.83 | 42.07 | 53.95 | D - Other node or line within 3 km | 1.51 | 0.52 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3064
4 | 65 | 3065 | 0405622090 | Region IV-A (CALABARZON) | Quezon | Lopez | Villa Espina | 13.8574 | 122.3794 | R | 916 | 3.8 | 241 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.14 | 3.17 | Tier 1B: High GIDA Priority | 40.21 | 40.21 | 67.7 | 53.95 | E - Nearest node or line 3-5 km | 9.14 | 3.11 | Line: AE LZQ001 TO SNQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3065
4 | 66 | 3066 | 1381100107 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 107 | 14.5124 | 121.1367 | U | 1489 | 3.49 | 427 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 2.18 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.44 | 38.44 | 69.47 | 53.95 | D - Other node or line within 3 km | 2.57 | 2.17 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3066
4 | 67 | 3067 | 1381100180 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 180 | 14.3963 | 120.8257 | U | 1608 | 4.09 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.94 | 2.12 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.08 | 37.08 | 70.81 | 53.95 | D - Other node or line within 3 km | 2.94 | 2.12 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3067
4 | 68 | 3068 | 0205010029 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Lawigan | 16.2057 | 120.7778 | R | 905 | 3.8 | 238 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.86 | 17.58 | Tier 1B: High GIDA Priority | 34.37 | 34.37 | 73.52 | 53.95 | F - Nearest node and line over 5 km | 17.86 | 17.57 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3068
4 | 69 | 3069 | 0304915006 | Region III (Central Luzon) | Nueva Ecija | Llanera | General Luna | 15.6178 | 120.9962 | R | 3303 | 3.5 | 944 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.88 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 69.08 | 69.08 | 38.8 | 53.94 | C - Line within 0.5 km; node over 1 km | 5.88 | 0.11 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3069
4 | 70 | 3070 | 1380601158 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 158 | 13.6714 | 121.0298 | U | 2037 | 4.41 | 462 | 139 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.03 | 9.92 | Tier 1B: High GIDA Priority | 37.76 | 37.76 | 70.13 | 53.94 | E - Nearest node or line 3-5 km | 4.03 | 9.92 | Node: BCY004 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3070
4 | 71 | 3071 | 0806014008 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Hiduroma | 12.0011 | 125.0337 | R | 281 | 4.1 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.74 | 86.46 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 71.19 | 53.94 | F - Nearest node and line over 5 km | 84.74 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3071
4 | 72 | 3072 | 0806002010 | Region VIII (Eastern Visayas) | Samar | Basey | Cancaiyas | 11.35 | 125.0836 | R | 617 | 4.1 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.13 | 17.29 | Tier 1B: High GIDA Priority | 36.41 | 36.41 | 71.47 | 53.94 | F - Nearest node and line over 5 km | 15.13 | 17.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3072
4 | 73 | 3073 | 0604530015 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Poblacion | 10.4605 | 122.8245 | U | 3790 | 3.7 | 1024 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 69.79 | 69.79 | 38.08 | 53.93 | B - Node 0.5-1 km | 0.63 | 0.04 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 3073
4 | 74 | 3074 | 0401026029 | Region IV-A (CALABARZON) | Batangas | San Pascual | Santo Niño | 13.7994 | 121.0212 | R | 3470 | 3.6 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 1.21 | Tier 2B: Moderate GIDA Inclusion | 68.06 | 68.06 | 39.81 | 53.93 | D - Other node or line within 3 km | 2.05 | 1.21 | Line: WP BYB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3074
4 | 75 | 3075 | 0105511010 | Region I (Ilocos Region) | Pangasinan | Bayambang | Bacnono | 15.8241 | 120.4627 | R | 2315 | 3.6 | 643 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 62.38 | 62.38 | 45.48 | 53.93 | D - Other node or line within 3 km | 1.2 | 0.63 | Line: AERIAL 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3075
4 | 76 | 3076 | 1380614036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 780 | 14.0675 | 121.9344 | U | 2340 | 4 | 585 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.48 | 7.49 | Tier 1B: High GIDA Priority | 39.2 | 39.2 | 68.66 | 53.93 | F - Nearest node and line over 5 km | 7.48 | 7.49 | Node: ATQ001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3076
4 | 77 | 3077 | 1380605032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 330 | 11.7224 | 121.5647 | U | 2949 | 3.5 | 843 | 253 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.49 | 47.44 | Tier 1B: High GIDA Priority | 38.46 | 38.46 | 69.4 | 53.93 | F - Nearest node and line over 5 km | 48.49 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3077
4 | 78 | 3078 | 1381100128 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 128 | 14.4791 | 120.8496 | U | 1444 | 2.95 | 489 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.12 | 6.52 | Tier 1B: High GIDA Priority | 38.37 | 38.37 | 69.48 | 53.93 | E - Nearest node or line 3-5 km | 4.12 | 6.51 | Node: CVC001 -TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3078
4 | 79 | 3079 | 1102319007 | Region XI (Davao Region) | Davao del Norte | City of Tagum | La Filipina | 7.4753 | 125.8051 | U | 21619 | 3.7 | 5843 | 1753 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.27 | 1.35 | Tier 2A: High Commercial ROI | 71.83 | 71.83 | 36.01 | 53.92 | D - Other node or line within 3 km | 2.27 | 2.26 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3079
4 | 80 | 3080 | 0604528015 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12-A | 10.7689 | 122.9685 | U | 13010 | 3.7 | 3516 | 1055 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.93 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 69.25 | 69.25 | 38.6 | 53.92 | C - Line within 0.5 km; node over 1 km | 3.15 | 0.31 | Line: TALISAY - VICTORIAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3080
4 | 81 | 3081 | 0803738076 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Punta | 11.009 | 124.5999 | U | 4544 | 3.8 | 1196 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 0.02 | Tier 2B: Moderate GIDA Inclusion | 67.65 | 67.65 | 40.2 | 53.92 | A - Node within 0.5 km | 0.36 | 0.02 | Line: ORMOC - BAYBAY | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3081
4 | 82 | 3082 | 0300806006 | Region III (Central Luzon) | Bataan | Limay | Landing | 14.5422 | 120.594 | R | 3333 | 3.6 | 926 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.43 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 66.4 | 66.4 | 41.44 | 53.92 | C - Line within 0.5 km; node over 1 km | 3.43 | 0.23 | Line: LIMAY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3082
4 | 83 | 3083 | 0704622003 | Region VII (Central Visayas) | Negros Oriental | Tayasan | Banga | 9.9398 | 123.1413 | R | 976 | 3.8 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.09 | 3.04 | Tier 1B: High GIDA Priority | 35.82 | 35.82 | 72.01 | 53.92 | F - Nearest node and line over 5 km | 24.09 | 12.28 | Line: OPENTRENCHING (505m) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3083
4 | 84 | 3084 | 0405632001 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Amaga | 14.828 | 122.1423 | R | 555 | 3.8 | 146 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 51.89 | 75.35 | Tier 1B: High GIDA Priority | 33.27 | 33.27 | 74.56 | 53.92 | F - Nearest node and line over 5 km | 51.89 | 999999 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3084
4 | 85 | 3085 | 0305415019 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Pasig | 15.2214 | 120.61 | U | 5346 | 4 | 1336 | 401 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 1.03 | Tier 2B: Moderate GIDA Inclusion | 63.71 | 63.71 | 44.11 | 53.91 | B - Node 0.5-1 km | 1 | 1.03 | Node: MTP005 - TYPE 4 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3085
4 | 86 | 3086 | 0907328034 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tambulig | Sumalig | 8.0188 | 123.6244 | R | 3043 | 3.9 | 780 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.47 | 7.92 | Tier 2B: Moderate GIDA Inclusion | 60.27 | 60.27 | 47.55 | 53.91 | F - Nearest node and line over 5 km | 8.47 | 7.92 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3086
4 | 87 | 3087 | 1401107012 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Gusaran | 16.6606 | 120.8253 | R | 1500 | 3.5 | 429 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.09 | 5.24 | Tier 2B: Moderate GIDA Inclusion | 54.08 | 54.08 | 53.73 | 53.91 | E - Nearest node or line 3-5 km | 4.09 | 5.19 | Node: KYB001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3087
4 | 88 | 3088 | 0600406009 | Region VI (Western Visayas) | Aklan | Ibajay | Buenavista | 11.8055 | 122.1735 | R | 557 | 3.9 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.42 | 0.95 | Tier 1B: High GIDA Priority | 39.28 | 39.28 | 68.54 | 53.91 | F - Nearest node and line over 5 km | 16.42 | 22.47 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3088
4 | 89 | 3089 | 1381100121 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 121 | 14.6924 | 121.0174 | U | 921 | 3.82 | 241 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 0.99 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.73 | 38.73 | 69.08 | 53.91 | D - Other node or line within 3 km | 1.46 | 0.99 | Line: UG 144C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3089
4 | 90 | 3090 | 0305409010 | Region III (Central Luzon) | Pampanga | Mabalacat City | Duquit | 15.178 | 120.6001 | U | 14747 | 4 | 3687 | 1106 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.33 | 1.08 | Tier 2A: High Commercial ROI | 70.24 | 70.24 | 37.55 | 53.9 | D - Other node or line within 3 km | 1.33 | 1.07 | Line: 104 CORE 13X8 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3090
4 | 91 | 3091 | 0103317015 | Region I (Ilocos Region) | La Union | Santo Tomas | Namboongan | 16.2935 | 120.381 | R | 2472 | 3.7 | 668 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 68.73 | 68.73 | 39.06 | 53.9 | B - Node 0.5-1 km | 0.56 | 0.23 | Line: SANTO TOMAS | Survey short node lateral; confirm port/fiber capacity, access and route. | 3091
4 | 92 | 3092 | 0403405052 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Sampiruhan | 14.2185 | 121.1853 | U | 10376 | 3.3 | 3144 | 943 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.84 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 64.24 | 64.24 | 43.57 | 53.9 | C - Line within 0.5 km; node over 1 km | 4.84 | 0.42 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3092
4 | 93 | 3093 | 0205004026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Magsaysay Hills | 16.3792 | 121.1114 | R | 2200 | 3.8 | 579 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 60.88 | 60.88 | 46.92 | 53.9 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.37 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3093
4 | 94 | 3094 | 1381300044 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Horseshoe | 14.7014 | 121.0636 | U | 3095 | 4.21 | 735 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 0.59 | Tier 2B: Moderate GIDA Inclusion | 51.63 | 51.63 | 56.17 | 53.9 | D - Other node or line within 3 km | 1.48 | 0.58 | Line: UG 288C via Y-Duct | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3094
4 | 95 | 3095 | 0405647009 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angustias Zone III | 14.0141 | 121.5967 | R | 381 | 3.8 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.5 | Tier 1B: High GIDA Priority | 48.41 | 48.41 | 59.4 | 53.9 | D - Other node or line within 3 km | 1.12 | 0.5 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3095
4 | 96 | 3096 | 0401029033 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 9 | 13.9198 | 120.9371 | R | 862 | 3.6 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 2.9 | Tier 1B: High GIDA Priority | 46.66 | 46.66 | 61.14 | 53.9 | D - Other node or line within 3 km | 1.88 | 2.9 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3096
4 | 97 | 3097 | 0201501015 | Region II (Cagayan Valley) | Cagayan | Abulug | Siguiran | 18.4704 | 121.4163 | R | 1415 | 3.9 | 363 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.04 | 7.41 | Tier 1B: High GIDA Priority | 45.04 | 45.04 | 62.76 | 53.9 | F - Nearest node and line over 5 km | 8.04 | 7.36 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3097
4 | 98 | 3098 | 1003521008 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Lamaosa | 8.028 | 123.9526 | R | 815 | 4.2 | 194 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.97 | 11.13 | Tier 1B: High GIDA Priority | 39.73 | 39.73 | 68.07 | 53.9 | F - Nearest node and line over 5 km | 16.97 | 11.13 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3098
4 | 99 | 3099 | 1380602006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 292 | 12.1765 | 122.9063 | U | 3113 | 3.92 | 795 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.15 | 42.92 | Tier 1B: High GIDA Priority | 37.15 | 37.15 | 70.66 | 53.9 | F - Nearest node and line over 5 km | 38.15 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3099
4 | 100 | 3100 | 0305409006 | Region III (Central Luzon) | Pampanga | Mabalacat City | Camachiles | 15.1929 | 120.5857 | U | 13860 | 4 | 3465 | 1040 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.95 | 0.24 | Tier 2A: High Commercial ROI | 70.27 | 70.27 | 37.5 | 53.89 | B - Node 0.5-1 km | 0.95 | 0.23 | Line: PIPE HH1-HH38 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3100
4 | 101 | 3101 | 0305402011 | Region III (Central Luzon) | Pampanga | Apalit | San Juan | 14.9544 | 120.7702 | U | 9402 | 4 | 2350 | 705 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 1.25 | Tier 2B: Moderate GIDA Inclusion | 66.12 | 66.12 | 41.66 | 53.89 | D - Other node or line within 3 km | 1.36 | 1.24 | Line: 24 CORE (3X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3101
4 | 102 | 3102 | 0405644004 | Region IV-A (CALABARZON) | Quezon | San Narciso | Binay | 13.5025 | 122.5984 | R | 2733 | 3.8 | 719 | 216 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.62 | 8.49 | Tier 2B: Moderate GIDA Inclusion | 57.52 | 57.52 | 50.25 | 53.89 | E - Nearest node or line 3-5 km | 3.62 | 8.49 | Node: SNQ003-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3102
4 | 103 | 3103 | 0105521002 | Region I (Ilocos Region) | Pangasinan | Labrador | Bongalon | 16.0069 | 120.1531 | R | 4409 | 3.6 | 1225 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.85 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 69.95 | 69.95 | 37.81 | 53.88 | C - Line within 0.5 km; node over 1 km | 5.85 | 0.25 | Line: LABRADOR | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3103
4 | 104 | 3104 | 0307114003 | Region III (Central Luzon) | Zambales | Subic | Asinan Proper | 14.8953 | 120.228 | U | 9489 | 3.8 | 2497 | 749 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 0.91 | Tier 2B: Moderate GIDA Inclusion | 66.75 | 66.75 | 40.99 | 53.87 | D - Other node or line within 3 km | 1.26 | 0.91 | Line: SUBIC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3104
4 | 105 | 3105 | 0405623032 | Region IV-A (CALABARZON) | Quezon | Lucban | Tinamnan | 14.154 | 121.5447 | U | 3361 | 3.8 | 884 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.7 | 3.37 | Tier 2B: Moderate GIDA Inclusion | 53.53 | 53.53 | 54.21 | 53.87 | E - Nearest node or line 3-5 km | 4.7 | 3.37 | Line: SAN PABLO - LUCBAN AERIAL | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3105
4 | 106 | 3106 | 0504101025 | Region V (Bicol Region) | Masbate | Aroroy | Matalangtalang | 12.517 | 123.3511 | R | 1642 | 4.1 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.24 | 9.16 | Tier 1B: High GIDA Priority | 49.5 | 49.5 | 58.24 | 53.87 | F - Nearest node and line over 5 km | 5.24 | 31.53 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3106
4 | 107 | 3107 | 1380606075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 469 | 13.3793 | 122.7585 | U | 2424 | 3.73 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.73 | 30.28 | Tier 1B: High GIDA Priority | 37.21 | 37.21 | 70.53 | 53.87 | F - Nearest node and line over 5 km | 10.73 | 30.28 | Node: SDQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3107
4 | 108 | 3108 | 0200901004 | Region II (Cagayan Valley) | Batanes | Basco | San Joaquin | 20.4412 | 121.9888 | R | 543 | 3 | 181 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 223.73 | 216.3 | Tier 1B: High GIDA Priority | 34.34 | 34.34 | 73.4 | 53.87 | F - Nearest node and line over 5 km | 219.41 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3108
4 | 109 | 3109 | 0301407028 | Region III (Central Luzon) | Bulacan | Calumpit | Sapang Bayan | 14.8913 | 120.7588 | R | 3282 | 3.5 | 938 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.93 | 1.8 | Tier 2B: Moderate GIDA Inclusion | 68.39 | 68.39 | 39.33 | 53.86 | D - Other node or line within 3 km | 1.93 | 1.79 | Line: CALUMPIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3109
4 | 110 | 3110 | 0105526006 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bari | 16.0616 | 120.4026 | U | 6120 | 3.6 | 1700 | 510 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 65.41 | 65.41 | 42.31 | 53.86 | B - Node 0.5-1 km | 0.69 | 0.3 | Line: MANGALDAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 3110
4 | 111 | 3111 | 0401009022 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 8 | 13.8984 | 121.0654 | R | 1738 | 3.6 | 483 | 145 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.73 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 61.55 | 61.55 | 46.16 | 53.86 | D - Other node or line within 3 km | 1.73 | 0.65 | Line: UG BUN001 TO SSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3111
4 | 112 | 3112 | 0201529040 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Caritan Centro | 17.6211 | 121.7258 | U | 4242 | 3.9 | 1088 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.05 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 58.77 | 58.77 | 48.95 | 53.86 | C - Line within 0.5 km; node over 1 km | 4.05 | 0.07 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3112
4 | 113 | 3113 | 1606806008 | Region XIII (Caraga) | Surigao del Sur | Carmen | Hinapoyan | 9.1986 | 125.9136 | R | 2674 | 4.1 | 652 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.22 | 8.88 | Tier 1B: High GIDA Priority | 50.08 | 50.08 | 57.65 | 53.86 | F - Nearest node and line over 5 km | 19.22 | 8.88 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3113
4 | 114 | 3114 | 1400126008 | Cordillera Administrative Region (CAR) | Abra | Tubo | Tubtuba | 17.1677 | 120.7446 | R | 424 | 3.8 | 112 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.8 | 7.7 | Tier 1B: High GIDA Priority | 44.17 | 44.17 | 63.55 | 53.86 | F - Nearest node and line over 5 km | 7.8 | 7.66 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3114
4 | 115 | 3115 | 1907004004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tampakan | 4.9182 | 119.7905 | R | 3019 | 5.8 | 521 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 42 | 42 | 65.73 | 53.86 | F - Nearest node and line over 5 km | 335.91 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3115
4 | 116 | 3116 | 0102903034 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Barangay 5 | 17.5804 | 120.3906 | U | 677 | 3.8 | 178 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.1 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 41.82 | 41.82 | 65.91 | 53.86 | C - Line within 0.5 km; node over 1 km | 1.47 | 0.1 | Line: SEGMENT 3 (VIGAN - BATAC) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3116
4 | 117 | 3117 | 1380609002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 655 | 13.5522 | 122.4639 | U | 1714 | 3.77 | 455 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.56 | 2.57 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39.15 | 39.15 | 68.58 | 53.86 | D - Other node or line within 3 km | 2.56 | 2.56 | Node: MLQ003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3117
4 | 118 | 3118 | 0504106011 | Region V (Bicol Region) | Masbate | Cawayan | Itombato | 11.9713 | 123.7726 | R | 1160 | 4.1 | 283 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.7 | 38.34 | Tier 1B: High GIDA Priority | 37.75 | 37.75 | 69.98 | 53.86 | F - Nearest node and line over 5 km | 18.7 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3118
4 | 119 | 3119 | 0702219004 | Region VII (Central Visayas) | Cebu | Consolacion | Danglag | 10.3908 | 123.9565 | R | 4615 | 3.8 | 1214 | 364 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 1.62 | Tier 2A: High Commercial ROI | 72.82 | 72.82 | 34.87 | 53.85 | D - Other node or line within 3 km | 1.61 | 1.45 | Line: Route 11.925km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3119
4 | 120 | 3120 | 0401012038 | Region IV-A (CALABARZON) | Batangas | Lemery | Sambal Ilaya | 13.8836 | 120.9081 | R | 4367 | 3.6 | 1213 | 364 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 1.41 | Tier 2A: High Commercial ROI | 70.07 | 70.07 | 37.63 | 53.85 | D - Other node or line within 3 km | 1.29 | 1.38 | Node: TLB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3120
4 | 121 | 3121 | 0604532007 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pinowayan | 10.5713 | 123.2182 | R | 2812 | 3.7 | 760 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.27 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 68.55 | 68.55 | 39.15 | 53.85 | D - Other node or line within 3 km | 2.27 | 0.5 | Line: SAN CARLOS CITY - TALISAY CITY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3121
4 | 122 | 3122 | 0504103014 | Region V (Bicol Region) | Masbate | Balud | Mapitogo | 12.076 | 123.2866 | R | 425 | 4.1 | 104 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.13 | 10.48 | Tier 1B: High GIDA Priority | 48.59 | 48.59 | 59.1 | 53.85 | F - Nearest node and line over 5 km | 5.13 | 28.84 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3122
4 | 123 | 3123 | 0504104015 | Region V (Bicol Region) | Masbate | Batuan | Sawang | 12.3672 | 123.767 | R | 1008 | 4.1 | 246 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.25 | 14.5 | Tier 1B: High GIDA Priority | 44.78 | 44.78 | 62.92 | 53.85 | F - Nearest node and line over 5 km | 12.25 | 16.33 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3123
4 | 124 | 3124 | 1381100021 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 21 | 14.5213 | 120.9795 | U | 782 | 3.04 | 257 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 1.86 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 38.24 | 38.24 | 69.46 | 53.85 | D - Other node or line within 3 km | 2.04 | 1.84 | Line: Aerial 216C MTF | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3124
4 | 125 | 3125 | 0600606042 | Region VI (Western Visayas) | Antique | Culasi | Simbola | 11.4075 | 122.0387 | R | 182 | 3.9 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.93 | 39.55 | Tier 1B: High GIDA Priority | 32.46 | 32.46 | 75.24 | 53.85 | F - Nearest node and line over 5 km | 36.93 | 39.54 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3125
4 | 126 | 3126 | 0301415002 | Region III (Central Luzon) | Bulacan | Pandi | Bagong Barrio | 14.8921 | 120.9544 | U | 16035 | 3.5 | 4581 | 1374 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.88 | 0.38 | Tier 2A: High Commercial ROI | 72.85 | 72.85 | 34.82 | 53.84 | B - Node 0.5-1 km | 0.88 | 0.35 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 3126
4 | 127 | 3127 | 0301408013 | Region III (Central Luzon) | Bulacan | Guiguinto | Tiaong | 14.8458 | 120.8915 | U | 10611 | 3.5 | 3032 | 910 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 66.11 | 66.11 | 41.57 | 53.84 | D - Other node or line within 3 km | 2.74 | 1.97 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3127
4 | 128 | 3128 | 0201505037 | Region II (Cagayan Valley) | Cagayan | Aparri | Punta | 18.3587 | 121.6344 | U | 4977 | 3.9 | 1276 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 10.35 | Tier 2B: Moderate GIDA Inclusion | 61.39 | 61.39 | 46.29 | 53.84 | A - Node within 0.5 km | 0.32 | 10.34 | Node: ARC001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3128
4 | 129 | 3129 | 0307113017 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion North | 15.7688 | 119.9092 | R | 3317 | 3.8 | 873 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.11 | Tier 2A: High Commercial ROI | 70.77 | 70.77 | 36.89 | 53.83 | A - Node within 0.5 km | 0.12 | 0.06 | Line: SANTA CRUZ TO ALAMINOS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3129
4 | 130 | 3130 | 0203108012 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Cabaruan | 16.9542 | 121.7694 | U | 8540 | 3.8 | 2247 | 674 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.13 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 64.57 | 64.57 | 43.08 | 53.83 | C - Line within 0.5 km; node over 1 km | 2.13 | 0.24 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3130
4 | 131 | 3131 | 0201529051 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | San Gabriel | 17.6257 | 121.718 | U | 7991 | 3.9 | 2049 | 615 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.21 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 61.56 | 61.56 | 46.1 | 53.83 | C - Line within 0.5 km; node over 1 km | 4.21 | 0.43 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3131
4 | 132 | 3132 | 0405646008 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Cagascas | 13.9997 | 122.4946 | R | 181 | 3.8 | 48 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.18 | 1.58 | Tier 1B: High GIDA Priority | 45.36 | 45.36 | 62.31 | 53.83 | D - Other node or line within 3 km | 3.18 | 1.58 | Line: GCQ001 TO TKQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3132
4 | 133 | 3133 | 1380601230 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 229 | 13.6117 | 122.3502 | U | 1825 | 4.37 | 418 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.39 | 3.22 | Tier 1B: High GIDA Priority | 37.18 | 37.18 | 70.48 | 53.83 | E - Nearest node or line 3-5 km | 3.39 | 3.22 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3133
4 | 134 | 3134 | 0401005066 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 2 | 13.7405 | 121.1046 | U | 516 | 3.6 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 4.83 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.82 | 36.82 | 70.84 | 53.83 | D - Other node or line within 3 km | 1.7 | 4.83 | Node: BCY003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3134
4 | 135 | 3135 | 0105526021 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Navaluan | 16.0659 | 120.4159 | R | 4149 | 3.6 | 1152 | 346 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 1.19 | Tier 2B: Moderate GIDA Inclusion | 69.8 | 69.8 | 37.84 | 53.82 | D - Other node or line within 3 km | 1.47 | 1.19 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3135
4 | 136 | 3136 | 0403409001 | Region IV-A (CALABARZON) | Laguna | Kalayaan | Longos | 14.337 | 121.4817 | U | 7487 | 3.3 | 2269 | 681 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.67 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 67 | 67 | 40.65 | 53.82 | B - Node 0.5-1 km | 0.67 | 0.05 | Line: SNL001 TO SCL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3136
4 | 137 | 3137 | 0403426014 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay I | 14.2788 | 121.4177 | R | 1367 | 3.3 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.5 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 57.4 | 57.4 | 50.24 | 53.82 | B - Node 0.5-1 km | 0.5 | 0.19 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3137
4 | 138 | 3138 | 0803739026 | Region VIII (Eastern Visayas) | Leyte | Palo | San Agustin | 11.1275 | 124.9371 | R | 1190 | 3.8 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.34 | 5.43 | Tier 1B: High GIDA Priority | 46.71 | 46.71 | 60.92 | 53.82 | F - Nearest node and line over 5 km | 7.34 | 5.43 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3138
4 | 139 | 3139 | 0500503021 | Region V (Bicol Region) | Albay | Daraga | Ibaugan | 13.0259 | 123.624 | R | 727 | 4.1 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.75 | 9.72 | Tier 1B: High GIDA Priority | 43.28 | 43.28 | 64.37 | 53.82 | F - Nearest node and line over 5 km | 7.75 | 9.61 | Node: PRS002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3139
4 | 140 | 3140 | 0305422005 | Region III (Central Luzon) | Pampanga | Sasmuan | Malusac | 14.8574 | 120.6213 | R | 2611 | 4 | 653 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.37 | 8.4 | Tier 2B: Moderate GIDA Inclusion | 55.78 | 55.78 | 51.84 | 53.81 | F - Nearest node and line over 5 km | 9.37 | 8.4 | Line: Pipe 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3140
4 | 141 | 3141 | 0402116016 | Region IV-A (CALABARZON) | Cavite | Noveleta | Santa Rosa II | 14.4165 | 120.8876 | R | 1300 | 3.4 | 382 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.53 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 54.65 | 54.65 | 52.97 | 53.81 | D - Other node or line within 3 km | 1.53 | 0.52 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3141
4 | 142 | 3142 | 0401019010 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 5 | 14.0914 | 120.6939 | R | 2047 | 3.6 | 569 | 171 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.44 | 2.96 | Tier 2B: Moderate GIDA Inclusion | 51.52 | 51.52 | 56.1 | 53.81 | D - Other node or line within 3 km | 6.44 | 2.96 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3142
4 | 143 | 3143 | 0803717030 | Region VIII (Eastern Visayas) | Leyte | Dagami | Lobe-lobe | 11.0739 | 124.9065 | R | 145 | 3.8 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.86 | 11.99 | Tier 1B: High GIDA Priority | 37.8 | 37.8 | 69.83 | 53.81 | F - Nearest node and line over 5 km | 12.86 | 11.98 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3143
4 | 144 | 3144 | 1380603003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 383 | 13.3797 | 120.674 | U | 2529 | 3.17 | 798 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.58 | 27 | Tier 1B: High GIDA Priority | 37.24 | 37.24 | 70.39 | 53.81 | F - Nearest node and line over 5 km | 28.58 | 26.53 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3144
4 | 145 | 3145 | 1907001005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Luuk Buntal | 17.2557 | 122.2297 | R | 2290 | 5.8 | 395 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 34.88 | 34.88 | 72.75 | 53.81 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3145
4 | 146 | 3146 | 1908806015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Mangadeg | 17.255 | 122.229 | R | 1344 | 4.7 | 286 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.43 | 34.31 | Tier 1B: High GIDA Priority | 32.1 | 32.1 | 75.53 | 53.81 | F - Nearest node and line over 5 km | 29.43 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3146
4 | 147 | 3147 | 0603035033 | Region VI (Western Visayas) | Iloilo | City of Passi | Man-it | 11.099 | 122.6362 | R | 4702 | 3.8 | 1237 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.28 | Tier 2A: High Commercial ROI | 73.42 | 73.42 | 34.17 | 53.8 | C - Line within 0.5 km; node over 1 km | 1.3 | 0.25 | Line: ROXAS - ILOILO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3147
4 | 148 | 3148 | 0305420001 | Region III (Central Luzon) | Pampanga | Santa Rita | Becuran | 15.0073 | 120.5928 | R | 4546 | 4 | 1136 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.48 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 69.87 | 69.87 | 37.73 | 53.8 | C - Line within 0.5 km; node over 1 km | 5.48 | 0.32 | Line: 24 CORE (2X12) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3148
4 | 149 | 3149 | 0105526022 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Nibaliw | 16.0773 | 120.4096 | R | 3363 | 3.6 | 934 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.93 | Tier 2B: Moderate GIDA Inclusion | 69.4 | 69.4 | 38.19 | 53.8 | D - Other node or line within 3 km | 1.31 | 0.95 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3149
4 | 150 | 3150 | 0403405062 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Majada Labas | 14.1951 | 121.1064 | U | 11588 | 3.3 | 3512 | 1054 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.32 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 68.01 | 68.01 | 39.6 | 53.8 | C - Line within 0.5 km; node over 1 km | 2.32 | 0.1 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3150
4 | 151 | 3151 | 0301410031 | Region III (Central Luzon) | Bulacan | City of Malolos | Mambog | 14.8097 | 120.8492 | R | 2964 | 3.5 | 847 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 3.21 | Tier 2B: Moderate GIDA Inclusion | 61.29 | 61.29 | 46.31 | 53.8 | E - Nearest node or line 3-5 km | 3.32 | 3.18 | Line: Mnla Pipe | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3151
4 | 152 | 3152 | 0102820012 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Juan Bautista | 18.1577 | 120.62 | R | 2985 | 3.7 | 807 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 3.21 | Tier 2B: Moderate GIDA Inclusion | 60.83 | 60.83 | 46.76 | 53.8 | D - Other node or line within 3 km | 2.8 | 3.21 | Node: SRI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3152
4 | 153 | 3153 | 1381300069 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Nayong Kanluran | 14.6881 | 121.0061 | U | 2603 | 3.6 | 723 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 52.46 | 52.46 | 55.14 | 53.8 | B - Node 0.5-1 km | 0.88 | 0.43 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 3153
4 | 154 | 3154 | 0504113024 | Region V (Bicol Region) | Masbate | Mobo | Sawmill | 12.2549 | 123.6672 | R | 1068 | 4.1 | 260 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.15 | 12.64 | Tier 1B: High GIDA Priority | 47.94 | 47.94 | 59.66 | 53.8 | F - Nearest node and line over 5 km | 9.15 | 12.6 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3154
4 | 155 | 3155 | 1906614028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Puok | 17.2557 | 122.2297 | R | 1600 | 6 | 267 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 36.07 | 36.07 | 71.54 | 53.8 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3155
4 | 156 | 3156 | 0600614021 | Region VI (Western Visayas) | Antique | San Remigio | General Luna | 10.8685 | 122.0835 | R | 830 | 3.9 | 213 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.8 | 12.49 | Tier 1B: High GIDA Priority | 35.83 | 35.83 | 71.76 | 53.8 | F - Nearest node and line over 5 km | 19.8 | 12.31 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3156
4 | 157 | 3157 | 0305402015 | Region III (Central Luzon) | Pampanga | Apalit | Tabuyuc | 14.9507 | 120.7737 | U | 9963 | 4 | 2491 | 747 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 1.58 | Tier 2B: Moderate GIDA Inclusion | 66.17 | 66.17 | 41.41 | 53.79 | D - Other node or line within 3 km | 1.58 | 1.6 | Node: ATP001 - TYPE 5 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3157
4 | 158 | 3158 | 1403206002 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Mabilong | 17.3494 | 121.1735 | R | 1395 | 4.3 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.87 | 0.23 | Tier 1B: High GIDA Priority | 50.24 | 50.24 | 57.34 | 53.79 | C - Line within 0.5 km; node over 1 km | 9.87 | 0.08 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3158
4 | 159 | 3159 | 0201508023 | Region II (Cagayan Valley) | Cagayan | Buguey | Tabbac | 18.2307 | 121.7992 | R | 1146 | 3.9 | 294 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.83 | 2.38 | Tier 1B: High GIDA Priority | 46.95 | 46.95 | 60.63 | 53.79 | D - Other node or line within 3 km | 2.83 | 2.38 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3159
4 | 160 | 3160 | 0201505032 | Region II (Cagayan Valley) | Cagayan | Aparri | Navagan | 18.3554 | 121.5705 | R | 1184 | 3.9 | 304 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.62 | 4.97 | Tier 1B: High GIDA Priority | 44.35 | 44.35 | 63.23 | 53.79 | E - Nearest node or line 3-5 km | 6.62 | 4.93 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3160
4 | 161 | 3161 | 0504118025 | Region V (Bicol Region) | Masbate | San Fernando | Talisay | 12.4803 | 123.6874 | R | 641 | 4.1 | 156 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.66 | 13.05 | Tier 1B: High GIDA Priority | 40.66 | 40.66 | 66.93 | 53.79 | F - Nearest node and line over 5 km | 15.66 | 15.44 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3161
4 | 162 | 3162 | 0304932026 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Old | 15.4407 | 120.7792 | R | 3933 | 3.5 | 1124 | 337 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 69.35 | 69.35 | 38.21 | 53.78 | D - Other node or line within 3 km | 1.68 | 0.55 | Line: SEGMENT 31 (ZARAGOZA - TARLAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3162
4 | 163 | 3163 | 0401005001 | Region IV-A (CALABARZON) | Batangas | Batangas City | Alangilan | 13.7876 | 121.0688 | U | 16134 | 3.6 | 4482 | 1345 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.09 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 69.24 | 69.24 | 38.33 | 53.78 | C - Line within 0.5 km; node over 1 km | 3.09 | 0.1 | Line: UG ROS001 TO BSY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3163
4 | 164 | 3164 | 0304926017 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Pinili | 15.7688 | 121.0355 | R | 4325 | 3.5 | 1236 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.86 | 1.61 | Tier 2B: Moderate GIDA Inclusion | 65.48 | 65.48 | 42.07 | 53.78 | D - Other node or line within 3 km | 5.86 | 1.61 | Line: Proposed AE F1-6 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3164
4 | 165 | 3165 | 0402117006 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong II | 14.4182 | 120.8531 | R | 1997 | 3.4 | 587 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.42 | 2.64 | Tier 2B: Moderate GIDA Inclusion | 55.33 | 55.33 | 52.23 | 53.78 | D - Other node or line within 3 km | 2.42 | 2.64 | Node: TRC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3165
4 | 166 | 3166 | 0403414004 | Region IV-A (CALABARZON) | Laguna | Mabitac | Matalatala | 14.4173 | 121.4104 | R | 4771 | 3.3 | 1446 | 434 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 2.93 | Tier 2A: High Commercial ROI | 70.32 | 70.32 | 37.22 | 53.77 | D - Other node or line within 3 km | 2.2 | 2.85 | Node: MCL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3166
4 | 167 | 3167 | 0501709017 | Region V (Bicol Region) | Camarines Sur | Camaligan | Tarosanan | 13.6165 | 123.1703 | R | 2223 | 4.2 | 529 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 66.64 | 66.64 | 40.9 | 53.77 | A - Node within 0.5 km | 0.43 | 1.31 | Node: CLC001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3167
4 | 168 | 3168 | 0402116014 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael III | 14.4365 | 120.8783 | U | 6490 | 3.4 | 1909 | 573 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 65.39 | 65.39 | 42.14 | 53.77 | B - Node 0.5-1 km | 0.93 | 0.89 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 3168
4 | 169 | 3169 | 0103307014 | Region I (Ilocos Region) | La Union | Bauang | Central East | 16.5281 | 120.3336 | U | 4199 | 3.7 | 1135 | 340 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 63.49 | 63.49 | 44.05 | 53.77 | B - Node 0.5-1 km | 0.79 | 0.17 | Line: 326 meters | Survey short node lateral; confirm port/fiber capacity, access and route. | 3169
4 | 170 | 3170 | 1380601157 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 157 | 13.4615 | 122.4853 | U | 1409 | 3.91 | 360 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 11.68 | Tier 1B: High GIDA Priority | 36.08 | 36.08 | 71.47 | 53.77 | E - Nearest node or line 3-5 km | 3.05 | 11.67 | Node: MLQ002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3170
4 | 171 | 3171 | 1600312006 | Region XIII (Caraga) | Agusan del Sur | Trento | Poblacion | 8.0475 | 126.0633 | U | 18953 | 3.9 | 4860 | 1458 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.24 | 0.11 | Tier 2A: High Commercial ROI | 76.61 | 76.61 | 30.9 | 53.76 | A - Node within 0.5 km | 0.24 | 0.06 | Line: TRENTO - BUENAVISTA CLS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3171
4 | 172 | 3172 | 0600613023 | Region VI (Western Visayas) | Antique | San Jose | Maybato Norte | 10.7305 | 121.9555 | R | 4778 | 3.9 | 1225 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.02 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 69.79 | 69.79 | 37.73 | 53.76 | C - Line within 0.5 km; node over 1 km | 4.02 | 0.02 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3172
4 | 173 | 3173 | 0402111007 | Region IV-A (CALABARZON) | Cavite | Kawit | Magdalo | 14.4343 | 120.9061 | U | 6528 | 3.4 | 1920 | 576 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.54 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 62.8 | 62.8 | 44.73 | 53.76 | C - Line within 0.5 km; node over 1 km | 2.54 | 0.29 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3173
4 | 174 | 3174 | 0403403003 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Tomas | 14.3113 | 121.0635 | U | 61000 | 3.3 | 18485 | 5546 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.06 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 56.18 | 56.18 | 51.33 | 53.76 | A - Node within 0.5 km | 0.06 | 0.04 | Line: AE CRC005-BNL001-CLB001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3174
4 | 175 | 3175 | 1705304003 | MIMAROPA Region | Palawan | Balabac | Bancalaan | 8.2192 | 117.1045 | U | 15433 | 3.9 | 3957 | 1187 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 246.24 | 248.53 | Tier 2B: Moderate GIDA Inclusion | 51.99 | 51.99 | 55.53 | 53.76 | F - Nearest node and line over 5 km | 246.24 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3175
4 | 176 | 3176 | 0405605031 | Region IV-A (CALABARZON) | Quezon | Buenavista | San Isidro Ibaba | 13.7453 | 122.4308 | R | 409 | 3.8 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3 | 2.19 | Tier 1B: High GIDA Priority | 46.58 | 46.58 | 60.94 | 53.76 | D - Other node or line within 3 km | 3 | 2.14 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3176
4 | 177 | 3177 | 1380606063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 457 | 11.6518 | 121.9398 | U | 2895 | 3.66 | 791 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.98 | 24.8 | Tier 1B: High GIDA Priority | 37.06 | 37.06 | 70.46 | 53.76 | F - Nearest node and line over 5 km | 32.98 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3177
4 | 178 | 3178 | 1108210002 | Region XI (Davao Region) | Davao de Oro | New Bataan | Batinao | 7.5714 | 126.0617 | R | 1378 | 3.7 | 372 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.47 | 11.29 | Tier 1B: High GIDA Priority | 37.04 | 37.04 | 70.48 | 53.76 | F - Nearest node and line over 5 km | 28.47 | 11.28 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3178
4 | 179 | 3179 | 1004318010 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Poblacion | 8.4043 | 124.2908 | U | 9067 | 3.9 | 2325 | 698 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.28 | Tier 2A: High Commercial ROI | 73.55 | 73.55 | 33.95 | 53.75 | B - Node 0.5-1 km | 0.57 | 0.28 | Line: CDO - ILIGAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 3179
4 | 180 | 3180 | 0401013004 | Region IV-A (CALABARZON) | Batangas | Lian | Binubusan | 13.9603 | 120.6382 | R | 4668 | 3.6 | 1297 | 389 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.08 | 0.56 | Tier 2A: High Commercial ROI | 72.77 | 72.77 | 34.73 | 53.75 | A - Node within 0.5 km | 0.08 | 0.56 | Node: LNB001 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3180
4 | 181 | 3181 | 0305409012 | Region III (Central Luzon) | Pampanga | Mabalacat City | Mabiga | 15.2121 | 120.58 | U | 25509 | 4 | 6377 | 1913 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.27 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 69.82 | 69.82 | 37.69 | 53.75 | C - Line within 0.5 km; node over 1 km | 1.27 | 0.18 | Line: PIPE HH1-HH38 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3181
4 | 182 | 3182 | 0301407017 | Region III (Central Luzon) | Bulacan | Calumpit | Meyto | 14.8897 | 120.7271 | R | 3057 | 3.5 | 873 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 66.95 | 66.95 | 40.54 | 53.75 | D - Other node or line within 3 km | 2.19 | 4.71 | Node: MSP001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3182
4 | 183 | 3183 | 0301420016 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Pedro | 14.8498 | 121.0574 | U | 17183 | 3.5 | 4909 | 1473 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.35 | 2.68 | Tier 2B: Moderate GIDA Inclusion | 66.48 | 66.48 | 41.03 | 53.75 | D - Other node or line within 3 km | 2.35 | 5.84 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3183
4 | 184 | 3184 | 0102820009 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Gregorio | 18.1746 | 120.5888 | R | 2017 | 3.7 | 545 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 60.77 | 60.77 | 46.74 | 53.75 | B - Node 0.5-1 km | 0.68 | 0.31 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3184
4 | 185 | 3185 | 1705307009 | MIMAROPA Region | Palawan | Busuanga | Panlaitan | 12.1186 | 119.8487 | R | 3606 | 3.9 | 925 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.71 | 134.18 | Tier 2B: Moderate GIDA Inclusion | 58.08 | 58.08 | 49.43 | 53.75 | F - Nearest node and line over 5 km | 9.71 | 999999 | Node: BSW001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3185
4 | 186 | 3186 | 0401033006 | Region IV-A (CALABARZON) | Batangas | Tingloy | Papaya | 13.6336 | 120.8858 | R | 1983 | 3.6 | 551 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.24 | 14.38 | Tier 2B: Moderate GIDA Inclusion | 55.56 | 55.56 | 51.94 | 53.75 | F - Nearest node and line over 5 km | 6.24 | 14.37 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3186
4 | 187 | 3187 | 0102820011 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Jose | 16.0548 | 120.7695 | R | 1474 | 3.7 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.11 | 4.28 | Tier 1B: High GIDA Priority | 48.37 | 48.37 | 59.12 | 53.75 | E - Nearest node or line 3-5 km | 4.11 | 4.28 | Node: TYP001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3187
4 | 188 | 3188 | 1380605072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 369 | 12.2759 | 121.1546 | U | 1785 | 3.69 | 484 | 145 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 2.56 | Tier 1B: High GIDA Priority | 38.59 | 38.59 | 68.91 | 53.75 | D - Other node or line within 3 km | 3.71 | 2.54 | Line: ROXAS - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3188
4 | 189 | 3189 | 1102412020 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone III | 6.8377 | 125.4155 | U | 12562 | 3.4 | 3695 | 1108 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.78 | 0.76 | Tier 2A: High Commercial ROI | 72.37 | 72.37 | 35.11 | 53.74 | B - Node 0.5-1 km | 0.78 | 0.75 | Line: DAVAO CITY - GENSAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 3189
4 | 190 | 3190 | 0405608019 | Region IV-A (CALABARZON) | Quezon | Candelaria | Pahinga Norte | 13.9163 | 121.4223 | U | 14495 | 3.8 | 3814 | 1144 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.31 | 1.16 | Tier 2A: High Commercial ROI | 70.54 | 70.54 | 36.94 | 53.74 | D - Other node or line within 3 km | 1.31 | 1.1 | Line: BCY001 TO LCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3190
4 | 191 | 3191 | 1401105007 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Buyacaoan | 16.776 | 120.8121 | R | 3989 | 3.5 | 1140 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.2 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 67.83 | 67.83 | 39.64 | 53.74 | C - Line within 0.5 km; node over 1 km | 3.2 | 0.34 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3191
4 | 192 | 3192 | 0402106005 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Langkaan I | 14.2751 | 120.9476 | U | 28359 | 3.4 | 8341 | 2502 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 3.03 | 1.67 | Tier 2B: Moderate GIDA Inclusion | 64.3 | 64.3 | 43.19 | 53.74 | D - Other node or line within 3 km | 3.03 | 1.67 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3192
4 | 193 | 3193 | 0702216003 | Region VII (Central Visayas) | Cebu | Catmon | Anapog | 10.6617 | 123.9071 | R | 287 | 3.8 | 76 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.21 | 11.03 | Tier 1B: High GIDA Priority | 42.77 | 42.77 | 64.71 | 53.74 | F - Nearest node and line over 5 km | 12.21 | 11.03 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3193
4 | 194 | 3194 | 1900708004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Mangalut | 6.6035 | 122.2107 | R | 2298 | 5.1 | 451 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 37.32 | 37.31 | Tier 1B: High GIDA Priority | 35.93 | 35.93 | 71.56 | 53.74 | F - Nearest node and line over 5 km | 37.32 | 37.31 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3194
4 | 195 | 3195 | 0306906018 | Region III (Central Luzon) | Tarlac | Gerona | Magaspac | 15.6154 | 120.5979 | R | 5109 | 3.9 | 1310 | 393 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.07 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 69.31 | 69.31 | 38.16 | 53.73 | C - Line within 0.5 km; node over 1 km | 2.07 | 0.16 | Line: GERONA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3195
4 | 196 | 3196 | 0301410051 | Region III (Central Luzon) | Bulacan | City of Malolos | Santor | 14.8525 | 120.8294 | U | 8937 | 3.5 | 2553 | 766 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.32 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 66.82 | 66.82 | 40.64 | 53.73 | D - Other node or line within 3 km | 1.32 | 0.52 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3196
4 | 197 | 3197 | 1401104001 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Ambuclao | 16.4535 | 120.7435 | U | 3391 | 3.5 | 969 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 59.81 | 59.81 | 47.65 | 53.73 | C - Line within 0.5 km; node over 1 km | 9 | 0.4 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3197
4 | 198 | 3198 | 1380605066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 364 | 13.5057 | 120.8569 | U | 2057 | 3.84 | 535 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.32 | 3.9 | Tier 1B: High GIDA Priority | 38.62 | 38.62 | 68.84 | 53.73 | E - Nearest node or line 3-5 km | 5.32 | 3.48 | Line: MINDORO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3198
4 | 199 | 3199 | 0806012029 | Region VIII (Eastern Visayas) | Samar | Motiong | Santo Niño | 11.9643 | 125.0674 | R | 90 | 4.1 | 22 | 7 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.89 | 83.84 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 70.78 | 53.73 | F - Nearest node and line over 5 km | 80.89 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3199
4 | 200 | 3200 | 1906617016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Sibul | 17.2555 | 122.2295 | R | 1563 | 6 | 260 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 35.89 | 35.89 | 71.56 | 53.73 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3200
4 | 201 | 3201 | 1907001004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Dungon | 17.2557 | 122.2297 | R | 2240 | 5.8 | 386 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 34.7 | 34.7 | 72.75 | 53.73 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3201
4 | 202 | 3202 | 0305408040 | Region III (Central Luzon) | Pampanga | Lubao | Santa Teresa 1st | 14.9246 | 120.5592 | R | 3826 | 4 | 956 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 1.5 | Tier 2B: Moderate GIDA Inclusion | 68.93 | 68.93 | 38.52 | 53.72 | D - Other node or line within 3 km | 1.63 | 1.5 | Line: LUBAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3202
4 | 203 | 3203 | 0305408029 | Region III (Central Luzon) | Pampanga | Lubao | San Roque Arbol | 14.8965 | 120.5451 | R | 3613 | 4 | 903 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 68.29 | 68.29 | 39.16 | 53.72 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.27 | Line: LUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3203
4 | 204 | 3204 | 0301404009 | Region III (Central Luzon) | Bulacan | Bocaue | Bunlo | 14.7882 | 120.932 | U | 4200 | 3.5 | 1200 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 63.21 | 63.21 | 44.23 | 53.72 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.05 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3204
4 | 205 | 3205 | 1402701004 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Batad | 16.9306 | 121.135 | R | 830 | 3.9 | 213 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.01 | 8.13 | Tier 1B: High GIDA Priority | 48.48 | 48.48 | 58.97 | 53.72 | E - Nearest node or line 3-5 km | 4.01 | 9.89 | Node: BEF002 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3205
4 | 206 | 3206 | 1400119012 | Cordillera Administrative Region (CAR) | Abra | Pilar | Narnara | 17.3806 | 120.5781 | R | 297 | 3.8 | 78 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.19 | 10.05 | Tier 1B: High GIDA Priority | 42.5 | 42.5 | 64.94 | 53.72 | F - Nearest node and line over 5 km | 9.19 | 10.05 | Node: NKI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3206
4 | 207 | 3207 | 1906608017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Tonggasang | 17.2553 | 122.2294 | R | 1562 | 6 | 260 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.36 | Tier 1B: High GIDA Priority | 35.89 | 35.89 | 71.54 | 53.72 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3207
4 | 208 | 3208 | 1900708006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Paguengan | 8.1643 | 122.2285 | R | 2326 | 5.1 | 456 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.89 | 57.89 | Tier 1B: High GIDA Priority | 35.86 | 35.86 | 71.58 | 53.72 | F - Nearest node and line over 5 km | 57.89 | 999999 | Node: ILZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3208
4 | 209 | 3209 | 1004309007 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Matangad | 8.5752 | 124.372 | R | 4152 | 3.9 | 1065 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.55 | 0.21 | Tier 2A: High Commercial ROI | 74.25 | 74.25 | 33.17 | 53.71 | C - Line within 0.5 km; node over 1 km | 2.55 | 0.21 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3209
4 | 210 | 3210 | 0301421015 | Region III (Central Luzon) | Bulacan | San Miguel | Bulualto | 15.2199 | 120.9539 | R | 3021 | 3.5 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.43 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 69.81 | 69.81 | 37.62 | 53.71 | C - Line within 0.5 km; node over 1 km | 5.11 | 0.04 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3210
4 | 211 | 3211 | 0301420006 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan I | 14.8207 | 121.0578 | R | 3484 | 3.5 | 995 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 69.04 | 69.04 | 38.37 | 53.71 | D - Other node or line within 3 km | 1.63 | 2.84 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3211
4 | 212 | 3212 | 1004318013 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Upper Malubog | 8.3642 | 124.4039 | R | 677 | 3.9 | 174 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.3 | 12.86 | Tier 1B: High GIDA Priority | 41.9 | 41.9 | 65.53 | 53.71 | F - Nearest node and line over 5 km | 12.3 | 12.83 | Node: OLM002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3212
4 | 213 | 3213 | 1380601041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 41 | 12.4002 | 120.4227 | U | 3957 | 5.04 | 785 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.99 | 69.18 | Tier 1B: High GIDA Priority | 36.97 | 36.97 | 70.44 | 53.71 | F - Nearest node and line over 5 km | 47.99 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3213
4 | 214 | 3214 | 1907006033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Tubig Dayang Center | 15.4378 | 122.0004 | R | 1198 | 5.8 | 207 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59 | 58.78 | Tier 1B: High GIDA Priority | 29.32 | 29.32 | 78.1 | 53.71 | F - Nearest node and line over 5 km | 59 | 999999 | Node: BLA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3214
4 | 215 | 3215 | 0203131003 | Region II (Cagayan Valley) | Isabela | San Mariano | Binatug | 16.9543 | 122.0699 | R | 2215 | 3.8 | 583 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.95 | 23.57 | Tier 2B: Moderate GIDA Inclusion | 51.8 | 51.8 | 55.59 | 53.7 | F - Nearest node and line over 5 km | 6.95 | 23.55 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3215
4 | 216 | 3216 | 1908709010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Landasan | 7.3406 | 124.2491 | U | 38559 | 4.3 | 8967 | 2690 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 62.32 | 58.09 | Tier 1B: High GIDA Priority | 45.83 | 45.83 | 61.58 | 53.7 | F - Nearest node and line over 5 km | 62.32 | 999999 | Node: CRE001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3216
4 | 217 | 3217 | 1380614018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 762 | 12.9582 | 121.4735 | U | 391 | 2.21 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.45 | 0.42 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 39 | 39 | 68.39 | 53.7 | A - Node within 0.5 km | 0.45 | 0.42 | Line: MINDORO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3217
4 | 218 | 3218 | 1380606068 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 462 | 13.7494 | 122.0553 | U | 1594 | 2.93 | 544 | 163 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.52 | 8.51 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 70.66 | 53.7 | F - Nearest node and line over 5 km | 8.52 | 8.51 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3218
4 | 219 | 3219 | 1380611047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 832 | 11.8329 | 122.598 | U | 2990 | 4.07 | 735 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.19 | 0.85 | Tier 1B: High GIDA Priority | 36.51 | 36.51 | 70.89 | 53.7 | F - Nearest node and line over 5 km | 27.19 | 28.62 | Node: NWK001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3219
4 | 220 | 3220 | 0405810008 | Region IV-A (CALABARZON) | Rizal | Pililla | Quisao | 14.4365 | 121.3356 | U | 16563 | 3.6 | 4601 | 1380 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.55 | 2.83 | Tier 2B: Moderate GIDA Inclusion | 69.64 | 69.64 | 37.73 | 53.69 | B - Node 0.5-1 km | 0.55 | 2.67 | Node: PLR002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 3220
4 | 221 | 3221 | 0301422034 | Region III (Central Luzon) | Bulacan | San Rafael | Ulingao | 14.9732 | 120.9174 | U | 3879 | 3.5 | 1108 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 63.86 | 63.86 | 43.52 | 53.69 | B - Node 0.5-1 km | 0.56 | 0.24 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3221
4 | 222 | 3222 | 0803708074 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Poblacion Zone 18 | 10.6575 | 124.8035 | R | 1637 | 3.8 | 431 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.45 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 56.38 | 56.38 | 50.99 | 53.69 | C - Line within 0.5 km; node over 1 km | 2.45 | 0.5 | Line: ORMOC - BAYBAY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3222
4 | 223 | 3223 | 0307702005 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 5 | 16.2472 | 122.0911 | R | 324 | 3.8 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.04 | 0.96 | Tier 1B: High GIDA Priority | 43.95 | 43.95 | 63.42 | 53.69 | F - Nearest node and line over 5 km | 5.04 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3223
4 | 224 | 3224 | 1900712006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Muhtamad | Palahangan | 6.736 | 121.5799 | R | 2792 | 5.1 | 547 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.87 | 57.87 | Tier 1B: High GIDA Priority | 38.21 | 38.21 | 69.17 | 53.69 | F - Nearest node and line over 5 km | 57.87 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3224
4 | 225 | 3225 | 1380605055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 353 | 13.5942 | 122.7292 | U | 3010 | 3.85 | 781 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.12 | 19.15 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 70.59 | 53.69 | F - Nearest node and line over 5 km | 18.12 | 19.15 | Node: SNQ003-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3225
4 | 226 | 3226 | 1400109002 | Cordillera Administrative Region (CAR) | Abra | Lacub | Buneg | 17.6673 | 120.9712 | R | 851 | 3.8 | 224 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.29 | 32.26 | Tier 1B: High GIDA Priority | 36.46 | 36.46 | 70.92 | 53.69 | F - Nearest node and line over 5 km | 32.29 | 32.24 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3226
4 | 227 | 3227 | 1102506009 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Oregon | 6.556 | 126.1246 | R | 1214 | 3.6 | 337 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.82 | 35.9 | Tier 1B: High GIDA Priority | 35.54 | 35.54 | 71.84 | 53.69 | F - Nearest node and line over 5 km | 39.82 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3227
4 | 228 | 3228 | 1380601110 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 110 | 13.6172 | 120.6936 | U | 2431 | 4.57 | 532 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.14 | 24.46 | Tier 1B: High GIDA Priority | 30.34 | 30.34 | 77.04 | 53.69 | F - Nearest node and line over 5 km | 23.14 | 24.4 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3228
4 | 229 | 3229 | 0203111013 | Region II (Cagayan Valley) | Isabela | Divilacan | Ditarum | 17.304 | 122.3037 | R | 351 | 3.8 | 92 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.03 | 43.58 | Tier 1B: High GIDA Priority | 28.71 | 28.71 | 78.67 | 53.69 | F - Nearest node and line over 5 km | 39.03 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3229
4 | 230 | 3230 | 0305402010 | Region III (Central Luzon) | Pampanga | Apalit | Sampaloc | 14.9673 | 120.7567 | U | 14226 | 4 | 3556 | 1067 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.13 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 68.56 | 68.56 | 38.8 | 53.68 | C - Line within 0.5 km; node over 1 km | 2.13 | 0.15 | Line: PIPE HH52-HH62 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3230
4 | 231 | 3231 | 1102412021 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone IV | 6.8335 | 125.4108 | U | 7229 | 3.4 | 2126 | 638 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 67.88 | 67.88 | 39.48 | 53.68 | B - Node 0.5-1 km | 0.88 | 0.46 | Line: DAVAO CITY - GENSAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 3231
4 | 232 | 3232 | 1600308018 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 4 | 8.5045 | 125.9844 | U | 3397 | 3.9 | 871 | 261 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 61.08 | 61.08 | 46.29 | 53.68 | D - Other node or line within 3 km | 1.07 | 0.73 | Line: TRENTO - BUENAVISTA CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3232
4 | 233 | 3233 | 0201510001 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Abagao | 18.2663 | 121.6922 | R | 413 | 3.9 | 106 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 53.9 | 53.9 | 53.45 | 53.68 | B - Node 0.5-1 km | 0.74 | 0.64 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3233
4 | 234 | 3234 | 1102319020 | Region XI (Davao Region) | Davao del Norte | City of Tagum | San Miguel | 7.4391 | 125.7738 | U | 22100 | 3.7 | 5973 | 1792 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.86 | 2.57 | Tier 2B: Moderate GIDA Inclusion | 67.39 | 67.39 | 39.96 | 53.67 | D - Other node or line within 3 km | 2.86 | 2.54 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3234
4 | 235 | 3235 | 0301410029 | Region III (Central Luzon) | Bulacan | City of Malolos | Mabolo | 14.8422 | 120.8259 | U | 6565 | 3.5 | 1876 | 563 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 0.69 | Tier 2B: Moderate GIDA Inclusion | 64.49 | 64.49 | 42.85 | 53.67 | D - Other node or line within 3 km | 1.48 | 0.69 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3235
4 | 236 | 3236 | 0201529034 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Ugac Norte | 17.614 | 121.7072 | U | 9529 | 3.9 | 2443 | 733 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.11 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 62.07 | 62.07 | 45.26 | 53.67 | C - Line within 0.5 km; node over 1 km | 5.11 | 0.16 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3236
4 | 237 | 3237 | 0401012041 | Region IV-A (CALABARZON) | Batangas | Lemery | Sangalang | 13.9096 | 120.8882 | R | 2175 | 3.6 | 604 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.13 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 57.35 | 57.35 | 49.99 | 53.67 | C - Line within 0.5 km; node over 1 km | 4.13 | 0.14 | Line: WP BYB001 TO BCY001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3237
4 | 238 | 3238 | 0401022031 | Region IV-A (CALABARZON) | Batangas | San Jose | Taysan | 13.8835 | 121.0996 | U | 3214 | 3.6 | 893 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 62.5 | 62.5 | 44.82 | 53.66 | B - Node 0.5-1 km | 0.75 | 0.09 | Line: UG_TNB001 TO DIVERSION RD | Survey short node lateral; confirm port/fiber capacity, access and route. | 3238
4 | 239 | 3239 | 0402106063 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc IV | 14.3132 | 120.9718 | U | 43875 | 3.4 | 12904 | 3871 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.66 | 2.13 | Tier 2B: Moderate GIDA Inclusion | 58.64 | 58.64 | 48.69 | 53.66 | B - Node 0.5-1 km | 0.66 | 2.12 | Node: DMC004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3239
4 | 240 | 3240 | 0702243011 | Region VII (Central Visayas) | Cebu | San Remigio | Hagnaya | 11.0927 | 123.9431 | R | 4317 | 3.8 | 1136 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 1.42 | Tier 2A: High Commercial ROI | 72.93 | 72.93 | 34.36 | 53.65 | D - Other node or line within 3 km | 1.7 | 1.42 | Line: FRONTHAUL - SAN REMIGIO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3240
4 | 241 | 3241 | 0701219011 | Region VII (Central Visayas) | Bohol | Dauis | Totolan | 9.6338 | 123.8519 | U | 8015 | 4 | 2004 | 601 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.26 | 0.92 | Tier 2A: High Commercial ROI | 72.43 | 72.43 | 34.87 | 53.65 | D - Other node or line within 3 km | 2.63 | 0.86 | Line: 11,428 mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3241
4 | 242 | 3242 | 0600613020 | Region VI (Western Visayas) | Antique | San Jose | Madrangca | 10.7713 | 121.9471 | R | 3077 | 3.9 | 789 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 66.07 | 66.07 | 41.23 | 53.65 | D - Other node or line within 3 km | 1.41 | 0.74 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3242
4 | 243 | 3243 | 1401107017 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Poblacion | 16.623 | 120.8387 | R | 1970 | 3.5 | 563 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.34 | 7.28 | Tier 2B: Moderate GIDA Inclusion | 63.12 | 63.12 | 44.19 | 53.65 | A - Node within 0.5 km | 0.34 | 7.05 | Node: KYB001 - TYPE 4A | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3243
4 | 244 | 3244 | 0405630021 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 3 Del Carmen | 13.9695 | 121.6834 | R | 1381 | 3.8 | 363 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 56.49 | 56.49 | 50.81 | 53.65 | A - Node within 0.5 km | 0.29 | 0.13 | Line: UG LCQ001 TO ATQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3244
4 | 245 | 3245 | 0704607015 | Region VII (Central Visayas) | Negros Oriental | Bindoy | Nalundan | 9.7875 | 122.9954 | U | 7426 | 3.8 | 1954 | 586 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.86 | 5.8 | Tier 2B: Moderate GIDA Inclusion | 56.03 | 56.03 | 51.27 | 53.65 | F - Nearest node and line over 5 km | 9.86 | 5.77 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3245
4 | 246 | 3246 | 1380612008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 840 | 11.6994 | 122.2147 | U | 2820 | 4.46 | 632 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.77 | 6.32 | Tier 1B: High GIDA Priority | 38.81 | 38.81 | 68.49 | 53.65 | F - Nearest node and line over 5 km | 8.77 | 14.69 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3246
4 | 247 | 3247 | 0403411013 | Region IV-A (CALABARZON) | Laguna | Los Baños | Tadlak | 14.1801 | 121.2094 | R | 4432 | 3.3 | 1343 | 403 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 67.32 | 67.32 | 39.97 | 53.64 | D - Other node or line within 3 km | 3.55 | 0.77 | Line: CLB001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3247
4 | 248 | 3248 | 0305413024 | Region III (Central Luzon) | Pampanga | Mexico | Parian | 15.0594 | 120.717 | U | 6107 | 4 | 1527 | 458 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.03 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 62.53 | 62.53 | 44.76 | 53.64 | C - Line within 0.5 km; node over 1 km | 2.03 | 0.18 | Line: Path Measure1 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3248
4 | 249 | 3249 | 0403428022 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Sinalhan | 14.326 | 121.1159 | U | 28801 | 3.3 | 8728 | 2618 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.93 | 2.1 | Tier 2B: Moderate GIDA Inclusion | 61.81 | 61.81 | 45.46 | 53.64 | D - Other node or line within 3 km | 1.93 | 2.1 | Node: SRL004 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3249
4 | 250 | 3250 | 0405622043 | Region IV-A (CALABARZON) | Quezon | Lopez | Lourdes | 13.9578 | 122.2261 | R | 293 | 3.8 | 77 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.58 | 6.32 | Tier 1B: High GIDA Priority | 39.43 | 39.43 | 67.86 | 53.64 | F - Nearest node and line over 5 km | 6.58 | 6.28 | Line: WP CLQ001 TO MLQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3250
4 | 251 | 3251 | 0401005084 | Region IV-A (CALABARZON) | Batangas | Batangas City | San Agustin Kanluran, Isla Verde | 13.5593 | 121.0494 | R | 689 | 3.6 | 191 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.75 | 12.12 | Tier 1B: High GIDA Priority | 39.29 | 39.29 | 67.99 | 53.64 | F - Nearest node and line over 5 km | 8.75 | 12.12 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3251
4 | 252 | 3252 | 0300807013 | Region III (Central Luzon) | Bataan | Mariveles | Balon-Anito | 14.4365 | 120.4734 | U | 16526 | 3.6 | 4591 | 1377 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.41 | 0.14 | Tier 2A: High Commercial ROI | 73.8 | 73.8 | 33.47 | 53.63 | A - Node within 0.5 km | 0.41 | 0.06 | Line: PIPE ORION-MARIVELES | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3252
4 | 253 | 3253 | 0402120028 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya II | 14.3685 | 120.8623 | U | 13139 | 3.4 | 3864 | 1159 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.85 | 1.64 | Tier 2A: High Commercial ROI | 71.56 | 71.56 | 35.7 | 53.63 | B - Node 0.5-1 km | 0.85 | 1.64 | Node: TZC002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3253
4 | 254 | 3254 | 0300802016 | Region III (Central Luzon) | Bataan | Bagac | Atilano L. Ricardo | 14.606 | 120.4058 | R | 3467 | 3.6 | 963 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.47 | Tier 2A: High Commercial ROI | 70.37 | 70.37 | 36.88 | 53.63 | B - Node 0.5-1 km | 0.84 | 0.37 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3254
4 | 255 | 3255 | 0401020021 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Pansol | 13.8861 | 121.2476 | R | 4860 | 3.6 | 1350 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.69 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 68.35 | 68.35 | 38.92 | 53.63 | C - Line within 0.5 km; node over 1 km | 2.69 | 0.34 | Line: AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3255
4 | 256 | 3256 | 1380606123 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 517 | 12.3789 | 121.3798 | U | 1355 | 3.89 | 348 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.69 | 1.2 | Tier 1B: High GIDA Priority | 36.61 | 36.61 | 70.66 | 53.63 | D - Other node or line within 3 km | 6.69 | 1.2 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3256
4 | 257 | 3257 | 0806022049 | Region VIII (Eastern Visayas) | Samar | Paranas | Lawaan II | 11.8155 | 125.0848 | R | 369 | 4.1 | 90 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.66 | 67.55 | Tier 1B: High GIDA Priority | 32.2 | 32.2 | 75.06 | 53.63 | F - Nearest node and line over 5 km | 64.66 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3257
4 | 258 | 3258 | 1004314006 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Mauswagon | 8.5801 | 124.4445 | R | 3634 | 3.9 | 932 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.78 | Tier 2A: High Commercial ROI | 75.36 | 75.36 | 31.89 | 53.62 | B - Node 0.5-1 km | 0.69 | 0.78 | Node: LGD001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 3258
4 | 259 | 3259 | 1400115012 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Umnap | 17.5824 | 121.0552 | R | 278 | 3.8 | 73 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.4 | 26.42 | Tier 1B: High GIDA Priority | 34.24 | 34.24 | 73 | 53.62 | F - Nearest node and line over 5 km | 30.4 | 26.33 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3259
4 | 260 | 3260 | 0304915023 | Region III (Central Luzon) | Nueva Ecija | Llanera | Victoria | 15.6789 | 121.016 | R | 3471 | 3.5 | 992 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 6.32 | Tier 2A: High Commercial ROI | 70.26 | 70.26 | 36.96 | 53.61 | D - Other node or line within 3 km | 1.5 | 6.16 | Node: LLN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3260
4 | 261 | 3261 | 0301420031 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Graceville | 14.7869 | 121.061 | U | 44118 | 3.5 | 12605 | 3782 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.57 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 61.31 | 61.31 | 45.92 | 53.61 | D - Other node or line within 3 km | 1.57 | 0.56 | Line: STA MARIA TO BRGY 181 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3261
4 | 262 | 3262 | 1381300022 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Commonwealth | 14.69 | 121.0992 | U | 215035 | 3.91 | 55017 | 16505 | Band n50 (1.5 GHz, 100 MHz TDD) | 17 | 1 | 0.81 | 0.36 | Tier 1B: High GIDA Priority | 47.65 | 47.65 | 59.58 | 53.61 | B - Node 0.5-1 km | 0.81 | 0.25 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 3262
4 | 263 | 3263 | 1381300139 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Batasan Hills | 14.6899 | 121.0941 | U | 168770 | 3.89 | 43402 | 13021 | Band n50 (1.5 GHz, 100 MHz TDD) | 14 | 1 | 0.98 | 0.13 | Tier 1B: High GIDA Priority | 47.32 | 47.32 | 59.9 | 53.61 | B - Node 0.5-1 km | 0.98 | 0.12 | Line: UG 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 3263
4 | 264 | 3264 | 1606710006 | Region XIII (Caraga) | Surigao del Norte | General Luna | Daku | 9.7419 | 126.1571 | R | 536 | 4.1 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.45 | 39.84 | Tier 1B: High GIDA Priority | 35.25 | 35.25 | 71.96 | 53.61 | F - Nearest node and line over 5 km | 47.45 | 39.83 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3264
4 | 265 | 3265 | 0301411012 | Region III (Central Luzon) | Bulacan | Marilao | Prenza II | 14.7765 | 120.9784 | U | 14408 | 3.5 | 4117 | 1235 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.86 | 0.38 | Tier 2A: High Commercial ROI | 70.68 | 70.68 | 36.52 | 53.6 | D - Other node or line within 3 km | 1.86 | 3.37 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3265
4 | 266 | 3266 | 1204704015 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Lanao | 7.0255 | 125.0814 | U | 7862 | 3.8 | 2069 | 621 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.95 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 65.87 | 65.87 | 41.33 | 53.6 | C - Line within 0.5 km; node over 1 km | 1.95 | 0.12 | Line: QUIRINO - KIDAPAWAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3266
4 | 267 | 3267 | 0402120011 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan I | 14.3635 | 120.8376 | U | 5325 | 3.4 | 1566 | 470 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.75 | 1.56 | Tier 2B: Moderate GIDA Inclusion | 62.89 | 62.89 | 44.32 | 53.6 | D - Other node or line within 3 km | 1.75 | 1.56 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3267
4 | 268 | 3268 | 0401005034 | Region IV-A (CALABARZON) | Batangas | Batangas City | Kumintang Ibaba | 13.7258 | 121.0942 | U | 9434 | 3.6 | 2621 | 786 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.64 | 4.8 | Tier 2B: Moderate GIDA Inclusion | 60.16 | 60.16 | 47.04 | 53.6 | E - Nearest node or line 3-5 km | 3.64 | 4.8 | Node: BCY003 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3268
4 | 269 | 3269 | 1380601028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 28 | 13.3785 | 120.5388 | U | 2515 | 3.92 | 642 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.05 | 40.45 | Tier 1B: High GIDA Priority | 33.22 | 33.22 | 73.98 | 53.6 | F - Nearest node and line over 5 km | 42.05 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3269
4 | 270 | 3270 | 1401107014 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Lusod | 16.6014 | 120.9534 | R | 896 | 3.5 | 256 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.59 | 19.71 | Tier 1B: High GIDA Priority | 42.64 | 42.64 | 64.53 | 53.59 | F - Nearest node and line over 5 km | 12.59 | 19.49 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3270
4 | 271 | 3271 | 1381100064 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 64 | 14.5514 | 120.9212 | U | 1646 | 3.32 | 496 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.4 | 7.61 | Tier 1B: High GIDA Priority | 37.14 | 37.14 | 70.04 | 53.59 | F - Nearest node and line over 5 km | 6.4 | 7.59 | Node: MNL068 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3271
4 | 272 | 3272 | 0604505016 | Region VI (Western Visayas) | Negros Occidental | Calatrava | Lalong | 10.6212 | 123.3484 | R | 2740 | 3.7 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.11 | 11.28 | Tier 2B: Moderate GIDA Inclusion | 56.33 | 56.33 | 50.82 | 53.58 | F - Nearest node and line over 5 km | 7.11 | 11.21 | Node: SCN004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3272
4 | 273 | 3273 | 1705313007 | MIMAROPA Region | Palawan | Linapacan | Nangalao | 11.4362 | 120.1628 | R | 2969 | 3.9 | 761 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 63.8 | 98.81 | Tier 2B: Moderate GIDA Inclusion | 50.1 | 50.1 | 57.06 | 53.58 | F - Nearest node and line over 5 km | 63.8 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3273
4 | 274 | 3274 | 1606810010 | Region XIII (Caraga) | Surigao del Sur | Lanuza | Mampi | 17.105 | 122.2741 | R | 940 | 4.1 | 229 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.53 | 37.62 | Tier 1B: High GIDA Priority | 38.16 | 38.16 | 69 | 53.58 | F - Nearest node and line over 5 km | 27.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3274
4 | 275 | 3275 | 1906614018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kanaway | 17.2556 | 122.2297 | R | 1503 | 6 | 250 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 35.63 | 35.63 | 71.54 | 53.58 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3275
4 | 276 | 3276 | 1380601109 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 109 | 11.5417 | 122.016 | U | 3495 | 5.5 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.89 | 31.61 | Tier 1B: High GIDA Priority | 33.04 | 33.04 | 74.12 | 53.58 | F - Nearest node and line over 5 km | 31.89 | 36.37 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3276
4 | 277 | 3277 | 1907007050 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Tandubato | 17.2559 | 122.2299 | R | 1801 | 5.8 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 32.7 | 32.7 | 74.46 | 53.58 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3277
4 | 278 | 3278 | 0301411004 | Region III (Central Luzon) | Bulacan | Marilao | Lambakin | 14.7655 | 120.971 | U | 50365 | 3.5 | 14390 | 4317 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.61 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 58.94 | 58.94 | 48.2 | 53.57 | D - Other node or line within 3 km | 1.61 | 2.15 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3278
4 | 279 | 3279 | 0301404007 | Region III (Central Luzon) | Bulacan | Bocaue | Bolacan | 14.8011 | 120.9456 | R | 1637 | 3.5 | 468 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.56 | 1.08 | Tier 2B: Moderate GIDA Inclusion | 56.99 | 56.99 | 50.14 | 53.57 | D - Other node or line within 3 km | 1.56 | 1.07 | Line: STA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3279
4 | 280 | 3280 | 0405619031 | Region IV-A (CALABARZON) | Quezon | Gumaca | Mataas Na Bundok | 13.9119 | 122.1397 | R | 170 | 3.8 | 45 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.65 | 0.17 | Tier 1B: High GIDA Priority | 44.85 | 44.85 | 62.3 | 53.57 | C - Line within 0.5 km; node over 1 km | 3.65 | 0.17 | Line: GCQ001 TO TKQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3280
4 | 281 | 3281 | 1380606124 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 518 | 13.6695 | 122.5164 | U | 2019 | 3.82 | 529 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.36 | 3.47 | Tier 1B: High GIDA Priority | 38.51 | 38.51 | 68.63 | 53.57 | E - Nearest node or line 3-5 km | 5.36 | 3.47 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3281
4 | 282 | 3282 | 1906612048 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Ratag | 17.2555 | 122.2295 | R | 2525 | 6 | 421 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 35.58 | 35.58 | 71.57 | 53.57 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3282
4 | 283 | 3283 | 1906608012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Patutol | 17.2554 | 122.2294 | R | 1480 | 6 | 247 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.37 | Tier 1B: High GIDA Priority | 35.55 | 35.55 | 71.59 | 53.57 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3283
4 | 284 | 3284 | 0305414013 | Region III (Central Luzon) | Pampanga | Minalin | Sta. Rita | 14.9718 | 120.6943 | R | 4792 | 4 | 1198 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 4.45 | Tier 2A: High Commercial ROI | 71.25 | 71.25 | 35.86 | 53.56 | D - Other node or line within 3 km | 1.29 | 4.43 | Node: MNP001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3284
4 | 285 | 3285 | 0405812005 | Region IV-A (CALABARZON) | Rizal | Tanay | Kaybuto | 14.4976 | 121.2811 | U | 8757 | 3.6 | 2432 | 730 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 68.18 | 68.18 | 38.94 | 53.56 | A - Node within 0.5 km | 0.35 | 0.37 | Node: TNR003 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3285
4 | 286 | 3286 | 0401031015 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Cale | 14.1177 | 121.0941 | R | 4068 | 3.6 | 1130 | 339 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 4.66 | Tier 2B: Moderate GIDA Inclusion | 65.28 | 65.28 | 41.85 | 53.56 | D - Other node or line within 3 km | 1.92 | 4.66 | Node: TNB003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3286
4 | 287 | 3287 | 0504113022 | Region V (Bicol Region) | Masbate | Mobo | Sambulawan | 12.2831 | 123.6222 | R | 379 | 4.1 | 92 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.16 | 7.46 | Tier 1B: High GIDA Priority | 47.72 | 47.72 | 59.39 | 53.56 | F - Nearest node and line over 5 km | 7.16 | 7.41 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3287
4 | 288 | 3288 | 1381100106 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 106 | 14.6478 | 120.9264 | U | 1199 | 3.61 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 3.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.29 | 36.29 | 70.84 | 53.56 | D - Other node or line within 3 km | 2.35 | 3.27 | Node: NAV001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3288
4 | 289 | 3289 | 1004206006 | Region X (Northern Mindanao) | Misamis Occidental | Concepcion | Lingatongan | 8.3993 | 123.5874 | R | 246 | 3.9 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.97 | 43.59 | Tier 1B: High GIDA Priority | 35.27 | 35.27 | 71.86 | 53.56 | F - Nearest node and line over 5 km | 45.97 | 43.58 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3289
4 | 290 | 3290 | 0306903036 | Region III (Central Luzon) | Tarlac | Camiling | Palimbo Caarosipan | 15.6907 | 120.4076 | R | 3626 | 3.9 | 930 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.83 | Tier 2A: High Commercial ROI | 70.3 | 70.3 | 36.8 | 53.55 | B - Node 0.5-1 km | 0.83 | 0.83 | Node: CMT001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 3290
4 | 291 | 3291 | 0300803017 | Region III (Central Luzon) | Bataan | City of Balanga | Sibacan | 14.687 | 120.5472 | R | 2889 | 3.6 | 802 | 241 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.42 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 68.22 | 68.22 | 38.87 | 53.55 | A - Node within 0.5 km | 0.42 | 0.25 | Line: CITY OF BALANGA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3291
4 | 292 | 3292 | 1401106004 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Loacan | 16.4185 | 120.671 | U | 8605 | 3.5 | 2459 | 738 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 64.08 | 64.08 | 43.02 | 53.55 | C - Line within 0.5 km; node over 1 km | 3.33 | 0.32 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3292
4 | 293 | 3293 | 0105533020 | Region I (Ilocos Region) | Pangasinan | San Fabian | Poblacion | 16.123 | 120.4022 | U | 3941 | 3.6 | 1095 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 63.24 | 63.24 | 43.86 | 53.55 | B - Node 0.5-1 km | 0.85 | 0.05 | Line: SAN FABIAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 3293
4 | 294 | 3294 | 1906614010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Hawan | 17.2556 | 122.2297 | R | 1481 | 6 | 247 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 35.54 | 35.54 | 71.55 | 53.55 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3294
4 | 295 | 3295 | 1003515008 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Kaludan | 7.7984 | 123.9241 | R | 1052 | 4.2 | 250 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.48 | 20.31 | Tier 1B: High GIDA Priority | 33.87 | 33.87 | 73.23 | 53.55 | F - Nearest node and line over 5 km | 30.48 | 20.31 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3295
4 | 296 | 3296 | 0601915010 | Region VI (Western Visayas) | Capiz | Sapi-An | Poblacion | 11.4961 | 122.5788 | U | 5405 | 3.8 | 1422 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.93 | 1.26 | Tier 2B: Moderate GIDA Inclusion | 68.46 | 68.46 | 38.62 | 53.54 | D - Other node or line within 3 km | 2.93 | 1.21 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3296
4 | 297 | 3297 | 0405605029 | Region IV-A (CALABARZON) | Quezon | Buenavista | Sabang Piris | 13.7376 | 122.4673 | R | 410 | 3.8 | 108 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 52.76 | 52.76 | 54.32 | 53.54 | C - Line within 0.5 km; node over 1 km | 1.21 | 0.29 | Line: AE LZQ001 TO SNQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3297
4 | 298 | 3298 | 0301412013 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Liputan | 14.7381 | 120.9273 | R | 1688 | 3.5 | 482 | 145 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 3.35 | Tier 2B: Moderate GIDA Inclusion | 51.47 | 51.47 | 55.61 | 53.54 | E - Nearest node or line 3-5 km | 3.35 | 3.35 | Node: OBB001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3298
4 | 299 | 3299 | 0304908001 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Bayanihan | 15.2995 | 120.9449 | U | 5999 | 3.5 | 1714 | 514 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 66.25 | 66.25 | 40.81 | 53.53 | C - Line within 0.5 km; node over 1 km | 1.07 | 0.31 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3299
4 | 300 | 3300 | 0301423017 | Region III (Central Luzon) | Bulacan | Santa Maria | Pulong Buhangin | 14.8666 | 120.997 | U | 43084 | 3.5 | 12310 | 3693 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.38 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 63.95 | 63.95 | 43.1 | 53.53 | A - Node within 0.5 km | 0.38 | 0.03 | Line: STA. MARIA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3300
4 | 301 | 3301 | 1380601066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 66 | 11.611 | 122.1844 | U | 3388 | 4.92 | 689 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.32 | 15.84 | Tier 1B: High GIDA Priority | 36.94 | 36.94 | 70.11 | 53.53 | F - Nearest node and line over 5 km | 12.32 | 16.68 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3301
4 | 302 | 3302 | 1003508004 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Bubong | 8.1119 | 123.8943 | R | 196 | 4.2 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.98 | 0.18 | Tier 1B: High GIDA Priority | 44.2 | 44.2 | 62.83 | 53.52 | C - Line within 0.5 km; node over 1 km | 12.98 | 0.1 | Line: ILIGAN - PAGADIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3302
4 | 303 | 3303 | 0401005062 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 16 | 13.704 | 121.0778 | U | 104 | 3.6 | 29 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.47 | 6.07 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.26 | 35.26 | 71.79 | 53.52 | D - Other node or line within 3 km | 2.47 | 6.06 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3303
4 | 304 | 3304 | 0702223027 | Region VII (Central Visayas) | Cebu | Danao City | Maslog | 10.482 | 124.0218 | U | 12167 | 3.8 | 3202 | 961 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.49 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 39.19 | 53.51 | C - Line within 0.5 km; node over 1 km | 3.49 | 0.07 | Line: 9.3km FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3304
4 | 305 | 3305 | 1401110006 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Beckel | 16.4363 | 120.6316 | U | 4684 | 3.5 | 1338 | 401 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.41 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 65.39 | 65.39 | 41.62 | 53.51 | A - Node within 0.5 km | 0.41 | 0.05 | Line: SEGMENT 15 (ARITAO - BAGUIO) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3305
4 | 306 | 3306 | 0401017008 | Region IV-A (CALABARZON) | Batangas | Malvar | Poblacion | 14.0422 | 121.1572 | U | 9064 | 3.6 | 2518 | 755 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 64.71 | 64.71 | 42.31 | 53.51 | C - Line within 0.5 km; node over 1 km | 2.49 | 0.22 | Line: TANAUAN - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3306
4 | 307 | 3307 | 0304928020 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Valenzuela | 15.444 | 120.9695 | U | 2923 | 3.5 | 835 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 59.02 | 59.02 | 48 | 53.51 | D - Other node or line within 3 km | 4.29 | 1.77 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3307
4 | 308 | 3308 | 1908818006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pandag | Malangit | 17.2552 | 122.2292 | R | 5154 | 4.7 | 1097 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.35 | Tier 1B: High GIDA Priority | 49.57 | 49.57 | 57.46 | 53.51 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3308
4 | 309 | 3309 | 0102803007 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Camanga | 17.9074 | 120.571 | R | 1231 | 3.7 | 333 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.6 | 8.51 | Tier 1B: High GIDA Priority | 45.17 | 45.17 | 61.85 | 53.51 | F - Nearest node and line over 5 km | 6.6 | 8.51 | Node: PNI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3309
4 | 310 | 3310 | 1908810004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Maitumaig | 17.2551 | 122.2292 | R | 2669 | 4.7 | 568 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 34.34 | Tier 1B: High GIDA Priority | 39.42 | 39.42 | 67.6 | 53.51 | F - Nearest node and line over 5 km | 29.46 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3310
4 | 311 | 3311 | 0502006027 | Region V (Bicol Region) | Catanduanes | Pandan | Wagdas | 14.0341 | 124.1713 | R | 638 | 4.2 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.03 | 82.71 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 70.22 | 53.51 | F - Nearest node and line over 5 km | 44.03 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3311
4 | 312 | 3312 | 0907333005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Dagum | 7.918 | 123.1422 | R | 555 | 3.9 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.03 | 13.6 | Tier 1B: High GIDA Priority | 35.46 | 35.46 | 71.55 | 53.51 | F - Nearest node and line over 5 km | 23.03 | 13.6 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3312
4 | 313 | 3313 | 1903621015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Lininding | 16.8771 | 122.2515 | R | 1346 | 5.7 | 236 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.07 | 39.27 | Tier 1B: High GIDA Priority | 35.42 | 35.42 | 71.6 | 53.51 | F - Nearest node and line over 5 km | 28.07 | 999999 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3313
4 | 314 | 3314 | 0603040043 | Region VI (Western Visayas) | Iloilo | San Joaquin | Igpayong | 10.627 | 122.1035 | R | 127 | 3.8 | 33 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.52 | 4.77 | Tier 1B: High GIDA Priority | 33.67 | 33.67 | 73.35 | 53.51 | E - Nearest node or line 3-5 km | 23.52 | 4.77 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3314
4 | 315 | 3315 | 1380601106 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 106 | 12.35 | 120.6087 | U | 2716 | 4.67 | 582 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 49.52 | 48.85 | Tier 1B: High GIDA Priority | 31.65 | 31.65 | 75.37 | 53.51 | F - Nearest node and line over 5 km | 49.52 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3315
4 | 316 | 3316 | 0405812014 | Region IV-A (CALABARZON) | Rizal | Tanay | San Isidro | 14.4956 | 121.2793 | R | 3187 | 3.6 | 885 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.67 | Tier 2A: High Commercial ROI | 70.17 | 70.17 | 36.83 | 53.5 | B - Node 0.5-1 km | 0.57 | 0.64 | Node: TNR003 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 3316
4 | 317 | 3317 | 0301416012 | Region III (Central Luzon) | Bulacan | Paombong | San Roque | 14.8319 | 120.7865 | R | 5028 | 3.5 | 1437 | 431 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.92 | 3.82 | Tier 2B: Moderate GIDA Inclusion | 65.03 | 65.03 | 41.97 | 53.5 | D - Other node or line within 3 km | 2.92 | 3.9 | Node: MSB003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3317
4 | 318 | 3318 | 0306903017 | Region III (Central Luzon) | Tarlac | Camiling | Cacamilingan Norte | 15.6876 | 120.4204 | R | 2597 | 3.9 | 666 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 64.19 | 64.19 | 42.81 | 53.5 | B - Node 0.5-1 km | 0.59 | 0.12 | Line: 20,642 mtrs. | Survey short node lateral; confirm port/fiber capacity, access and route. | 3318
4 | 319 | 3319 | 0604531008 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay V | 10.902 | 123.0753 | R | 1805 | 3.7 | 488 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 61.55 | 61.55 | 45.45 | 53.5 | A - Node within 0.5 km | 0.25 | 0.24 | Line: TALISAY - VICTORIAS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3319
4 | 320 | 3320 | 1402702020 | Cordillera Administrative Region (CAR) | Ifugao | Hungduan | Lubo-ong | 16.9271 | 121.0287 | R | 918 | 3.9 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 2.75 | Tier 1B: High GIDA Priority | 49.12 | 49.12 | 57.87 | 53.5 | E - Nearest node or line 3-5 km | 3.88 | 6.85 | Node: BEF001 - TYPE 2 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3320
4 | 321 | 3321 | 0604531028 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XXI | 10.8915 | 123.0919 | R | 5181 | 3.7 | 1400 | 420 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.34 | 1.78 | Tier 2A: High Commercial ROI | 72.17 | 72.17 | 34.81 | 53.49 | D - Other node or line within 3 km | 2.34 | 1.78 | Line: TALISAY - VICTORIAS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3321
4 | 322 | 3322 | 0304932005 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Del Pilar | 15.4355 | 120.8011 | R | 4083 | 3.5 | 1167 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 68.75 | 68.75 | 38.22 | 53.49 | D - Other node or line within 3 km | 2.15 | 1.48 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3322
4 | 323 | 3323 | 1102502009 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Panikian | 6.9943 | 126.0288 | R | 3259 | 3.6 | 905 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.84 | 2.01 | Tier 2B: Moderate GIDA Inclusion | 62.12 | 62.12 | 44.86 | 53.49 | D - Other node or line within 3 km | 3.84 | 1.96 | Line: PANTUKAN - MATI SEGMENT 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3323
4 | 324 | 3324 | 0803720016 | Region VIII (Eastern Visayas) | Leyte | Hindang | Mahilum | 10.4759 | 124.836 | R | 321 | 3.8 | 84 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.87 | 9.89 | Tier 1B: High GIDA Priority | 39.34 | 39.34 | 67.64 | 53.49 | F - Nearest node and line over 5 km | 22.95 | 9.88 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3324
4 | 325 | 3325 | 1380607004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 640 | 11.8807 | 122.3656 | U | 2179 | 2.96 | 736 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.93 | 7.95 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 71.31 | 53.49 | F - Nearest node and line over 5 km | 19.93 | 18.25 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3325
4 | 326 | 3326 | 1908706015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Pened | 17.2541 | 122.2282 | R | 1779 | 4.3 | 414 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 35.42 | 35.42 | 71.55 | 53.49 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3326
4 | 327 | 3327 | 1380601226 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 225 | 14.0643 | 122.0996 | U | 2275 | 3.53 | 644 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.86 | 14.35 | Tier 1B: High GIDA Priority | 35.33 | 35.33 | 71.66 | 53.49 | F - Nearest node and line over 5 km | 12.86 | 14.34 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3327
4 | 328 | 3328 | 0307114014 | Region III (Central Luzon) | Zambales | Subic | Mangan-Vaca | 14.8886 | 120.2376 | U | 14223 | 3.8 | 3743 | 1123 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.06 | 0.24 | Tier 2A: High Commercial ROI | 72.98 | 72.98 | 33.99 | 53.48 | A - Node within 0.5 km | 0.06 | 0.03 | Line: SUBIC | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3328
4 | 329 | 3329 | 0401003017 | Region IV-A (CALABARZON) | Batangas | Balayan | Caloocan | 13.9527 | 120.7239 | U | 6470 | 3.6 | 1797 | 539 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 64.68 | 64.68 | 42.29 | 53.48 | C - Line within 0.5 km; node over 1 km | 1.12 | 0.29 | Line: BALAYAN - CALATAGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3329
4 | 330 | 3330 | 0405603034 | Region IV-A (CALABARZON) | Quezon | Atimonan | San Jose Balatok | 14.0023 | 121.9067 | R | 62 | 3.8 | 16 | 5 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.83 | Tier 1B: High GIDA Priority | 46.9 | 46.9 | 60.06 | 53.48 | D - Other node or line within 3 km | 2.02 | 0.83 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3330
4 | 331 | 3331 | 0600608051 | Region VI (Western Visayas) | Antique | Hamtic | Suloc | 10.6531 | 122.0031 | R | 125 | 3.9 | 32 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.07 | 2.13 | Tier 1B: High GIDA Priority | 37.01 | 37.01 | 69.96 | 53.48 | D - Other node or line within 3 km | 14.07 | 2.13 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3331
4 | 332 | 3332 | 0105538021 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Poblacion Norte | 16.0007 | 120.4021 | R | 4714 | 3.6 | 1309 | 393 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 69.15 | 69.15 | 37.8 | 53.47 | C - Line within 0.5 km; node over 1 km | 2.18 | 0.17 | Line: SANTA BARBARA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3332
4 | 333 | 3333 | 0301407002 | Region III (Central Luzon) | Bulacan | Calumpit | Balungao | 14.8965 | 120.7639 | U | 5979 | 3.5 | 1708 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.17 | 1.01 | Tier 2B: Moderate GIDA Inclusion | 64.51 | 64.51 | 42.42 | 53.47 | D - Other node or line within 3 km | 1.17 | 1 | Line: CALUMPIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3333
4 | 334 | 3334 | 0105533022 | Region I (Ilocos Region) | Pangasinan | San Fabian | Sagud-Bahley | 16.1198 | 120.3888 | U | 4389 | 3.6 | 1219 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 1.2 | Tier 2B: Moderate GIDA Inclusion | 62.99 | 62.99 | 43.96 | 53.47 | D - Other node or line within 3 km | 1.19 | 1.2 | Node: SIP001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3334
4 | 335 | 3335 | 1001321002 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Banlag | 7.846 | 125.1749 | U | 9197 | 3.8 | 2420 | 726 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.44 | 8.97 | Tier 2B: Moderate GIDA Inclusion | 60.44 | 60.44 | 46.5 | 53.47 | E - Nearest node or line 3-5 km | 4.44 | 11.1 | Node: VCB003 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3335
4 | 336 | 3336 | 0402118063 | Region IV-A (CALABARZON) | Cavite | Silang | San Miguel II | 14.2252 | 120.9623 | U | 2693 | 3.4 | 792 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.76 | 1.28 | Tier 2B: Moderate GIDA Inclusion | 53.51 | 53.51 | 53.43 | 53.47 | D - Other node or line within 3 km | 6.76 | 1.28 | Line: SILANG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3336
4 | 337 | 3337 | 1908712004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Talitay | Kilalan | 17.2551 | 122.2291 | R | 4512 | 4.3 | 1049 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 49.43 | 49.43 | 57.51 | 53.47 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3337
4 | 338 | 3338 | 1380606090 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 484 | 11.8985 | 122.0437 | U | 2285 | 3.46 | 661 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.01 | 3.06 | Tier 1B: High GIDA Priority | 36.4 | 36.4 | 70.54 | 53.47 | F - Nearest node and line over 5 km | 12.01 | 39.81 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3338
4 | 339 | 3339 | 0304908008 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Pambuan | 15.3255 | 120.9619 | U | 16753 | 3.5 | 4787 | 1436 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.64 | 1.3 | Tier 2B: Moderate GIDA Inclusion | 69.74 | 69.74 | 37.17 | 53.46 | D - Other node or line within 3 km | 4.06 | 1.21 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3339
4 | 340 | 3340 | 0301423010 | Region III (Central Luzon) | Bulacan | Santa Maria | Lalakhan | 14.8151 | 120.9461 | R | 2424 | 3.5 | 693 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 63.44 | 63.44 | 43.48 | 53.46 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.29 | Line: SMB HH19-18 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3340
4 | 341 | 3341 | 1102411012 | Region XI (Davao Region) | Davao del Sur | Padada | Quirino District | 6.6383 | 125.3409 | R | 1762 | 3.4 | 518 | 155 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 61.2 | 61.2 | 45.72 | 53.46 | A - Node within 0.5 km | 0.47 | 0.67 | Node: PAD001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3341
4 | 342 | 3342 | 1408106014 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Mataguisi | 18.1287 | 121.3478 | R | 1114 | 4.2 | 265 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 58.91 | 58.91 | 48.01 | 53.46 | A - Node within 0.5 km | 0.31 | 23.76 | Node: PLY002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3342
4 | 343 | 3343 | 0301420025 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima IV | 14.8072 | 121.0833 | R | 2217 | 3.5 | 633 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 2.09 | Tier 2B: Moderate GIDA Inclusion | 58.04 | 58.04 | 48.88 | 53.46 | D - Other node or line within 3 km | 1.52 | 1.78 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3343
4 | 344 | 3344 | 0704616013 | Region VII (Central Visayas) | Negros Oriental | Pamplona | San Isidro | 9.3775 | 122.9882 | R | 3350 | 3.8 | 882 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.46 | 14.16 | Tier 2B: Moderate GIDA Inclusion | 50.96 | 50.96 | 55.95 | 53.46 | F - Nearest node and line over 5 km | 19.46 | 19.95 | Node: BWN001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3344
4 | 345 | 3345 | 0205009012 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Kakiduguen | 16.2223 | 121.379 | R | 1165 | 3.8 | 307 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.84 | 29.11 | Tier 1B: High GIDA Priority | 38.22 | 38.22 | 68.7 | 53.46 | F - Nearest node and line over 5 km | 13.84 | 33.81 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3345
4 | 346 | 3346 | 1907010013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Mantabuan Tabunan | 5.0244 | 120.2109 | R | 1984 | 5.8 | 342 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 32.87 | 32.87 | 74.04 | 53.46 | F - Nearest node and line over 5 km | 293.97 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3346
4 | 347 | 3347 | 1380601039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 39 | 13.4807 | 122.8419 | U | 2498 | 4.41 | 566 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.61 | 19.61 | Tier 1B: High GIDA Priority | 31.21 | 31.21 | 75.7 | 53.46 | F - Nearest node and line over 5 km | 19.61 | 19.97 | Node: PCC001 - PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3347
4 | 348 | 3348 | 0500516019 | Region V (Bicol Region) | Albay | Santo Domingo | San Andres | 13.2602 | 123.7777 | R | 4476 | 4.1 | 1092 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.58 | 1.58 | Tier 2A: High Commercial ROI | 75.57 | 75.57 | 31.33 | 53.45 | D - Other node or line within 3 km | 2.58 | 1.58 | Line: LEGAZP - TIWI AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3348
4 | 349 | 3349 | 0305402014 | Region III (Central Luzon) | Pampanga | Apalit | Sulipan | 14.9402 | 120.7598 | U | 12406 | 4 | 3102 | 931 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 69.27 | 69.27 | 37.63 | 53.45 | B - Node 0.5-1 km | 0.9 | 0.33 | Line: PIPE HH52-HH62 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3349
4 | 350 | 3350 | 0403419009 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Magdapio | 14.2744 | 121.4589 | R | 2560 | 3.3 | 776 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 66.46 | 66.46 | 40.45 | 53.45 | B - Node 0.5-1 km | 0.93 | 0.27 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3350
4 | 351 | 3351 | 0907219032 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Siocon | Tabayo | 7.7406 | 122.2673 | R | 3492 | 3.6 | 970 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.5 | 23.21 | Tier 2B: Moderate GIDA Inclusion | 51.72 | 51.72 | 55.17 | 53.45 | F - Nearest node and line over 5 km | 23.5 | 23.19 | Line: IPIL - TUNGAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3351
4 | 352 | 3352 | 0205006019 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Villa Florentino | 16.6316 | 121.4306 | R | 738 | 3.8 | 194 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.29 | 2.51 | Tier 1B: High GIDA Priority | 45.71 | 45.71 | 61.19 | 53.45 | D - Other node or line within 3 km | 7.29 | 2.51 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3352
4 | 353 | 3353 | 0102820004 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Baltazar | 18.1567 | 120.5906 | U | 816 | 3.7 | 221 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.38 | Tier 1B: High GIDA Priority | 42.86 | 42.86 | 64.05 | 53.45 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.38 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3353
4 | 354 | 3354 | 1380610014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 699 | 13.2854 | 120.454 | U | 2733 | 2.89 | 946 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.53 | 52.95 | Tier 1B: High GIDA Priority | 40.9 | 40.9 | 66.01 | 53.45 | F - Nearest node and line over 5 km | 54.53 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3354
4 | 355 | 3355 | 1381100112 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 112 | 14.5883 | 121.1382 | U | 659 | 3.29 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.97 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.63 | 37.63 | 69.27 | 53.45 | D - Other node or line within 3 km | 1.5 | 0.95 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3355
4 | 356 | 3356 | 1004206003 | Region X (Northern Mindanao) | Misamis Occidental | Concepcion | New Casul | 8.4087 | 123.5826 | R | 455 | 3.9 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.14 | 44.74 | Tier 1B: High GIDA Priority | 35.25 | 35.25 | 71.65 | 53.45 | F - Nearest node and line over 5 km | 47.14 | 999999 | Node: TDL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3356
4 | 357 | 3357 | 0603028040 | Region VI (Western Visayas) | Iloilo | Leon | Danao | 10.8531 | 122.2849 | R | 360 | 3.8 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.01 | 16.48 | Tier 1B: High GIDA Priority | 33.98 | 33.98 | 72.92 | 53.45 | F - Nearest node and line over 5 km | 22.01 | 16.24 | Line: 7,761 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3357
4 | 358 | 3358 | 0205004014 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Mabuslo | 16.3788 | 121.1723 | R | 3143 | 3.8 | 827 | 248 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.4 | 6.7 | Tier 2B: Moderate GIDA Inclusion | 58.26 | 58.26 | 48.61 | 53.44 | F - Nearest node and line over 5 km | 7.4 | 6.69 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3358
4 | 359 | 3359 | 1402703013 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Lingay | 16.8364 | 121.0667 | R | 260 | 3.9 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.62 | 1.8 | Tier 2B: Moderate GIDA Inclusion | 51.44 | 51.44 | 55.44 | 53.44 | D - Other node or line within 3 km | 2.62 | 1.77 | Line: HINGYON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3359
4 | 360 | 3360 | 0401029031 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 7 | 13.8869 | 120.9629 | R | 171 | 3.6 | 48 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.61 | Tier 1B: High GIDA Priority | 48.59 | 48.59 | 58.29 | 53.44 | D - Other node or line within 3 km | 1.03 | 0.61 | Line: WP BYB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3360
4 | 361 | 3361 | 1380500001 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Addition Hills | 14.5839 | 121.0369 | U | 110493 | 3.77 | 29288 | 8786 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.6 | 0.52 | Tier 1B: High GIDA Priority | 48.07 | 48.07 | 58.82 | 53.44 | B - Node 0.5-1 km | 0.6 | 0.4 | Line: Aerial 216C MTF | Survey short node lateral; confirm port/fiber capacity, access and route. | 3361
4 | 362 | 3362 | 1004318002 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Balintad | 8.3699 | 124.3784 | R | 631 | 3.9 | 162 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.42 | 10.01 | Tier 1B: High GIDA Priority | 43.25 | 43.25 | 63.63 | 53.44 | F - Nearest node and line over 5 km | 10.42 | 9.98 | Line: CDO - ILIGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3362
4 | 363 | 3363 | 1907009016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | BasLikud | 17.2558 | 122.2298 | R | 1901 | 5.8 | 328 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 33.13 | 33.13 | 73.75 | 53.44 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3363
4 | 364 | 3364 | 0307114009 | Region III (Central Luzon) | Zambales | Subic | Calapandayan | 14.8738 | 120.2355 | U | 10846 | 3.8 | 2854 | 856 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 67.06 | 67.06 | 39.8 | 53.43 | C - Line within 0.5 km; node over 1 km | 1.71 | 0.17 | Line: BACKBONE ROUTE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3364
4 | 365 | 3365 | 1380607009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 645 | 13.8491 | 121.5536 | U | 1716 | 3.58 | 479 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.07 | 3.15 | Tier 1B: High GIDA Priority | 37.38 | 37.38 | 69.48 | 53.43 | E - Nearest node or line 3-5 km | 5.07 | 3.15 | Line: SJB002 TO LCQ001 LUCBITZ AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3365
4 | 366 | 3366 | 1403211007 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Liwan West | 17.4925 | 121.5885 | R | 3022 | 3.6 | 839 | 252 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.23 | Tier 2A: High Commercial ROI | 72.75 | 72.75 | 34.09 | 53.42 | B - Node 0.5-1 km | 0.89 | 0.23 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3366
4 | 367 | 3367 | 0304915015 | Region III (Central Luzon) | Nueva Ecija | Llanera | Plaridel | 15.6712 | 121.015 | R | 4045 | 3.5 | 1156 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.76 | 5.46 | Tier 2A: High Commercial ROI | 72.12 | 72.12 | 34.72 | 53.42 | B - Node 0.5-1 km | 0.76 | 5.31 | Node: LLN001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 3367
4 | 368 | 3368 | 0401001021 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Subic Ibaba | 13.9461 | 120.9413 | R | 3755 | 3.6 | 1043 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 5.77 | Tier 2A: High Commercial ROI | 70.68 | 70.68 | 36.16 | 53.42 | D - Other node or line within 3 km | 1.22 | 5.76 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3368
4 | 369 | 3369 | 0304911056 | Region III (Central Luzon) | Nueva Ecija | Guimba | San Roque | 15.2418 | 120.9548 | U | 6874 | 3.5 | 1964 | 589 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.05 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 67.58 | 67.58 | 39.26 | 53.42 | C - Line within 0.5 km; node over 1 km | 5.5 | 0.05 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3369
4 | 370 | 3370 | 0403414014 | Region IV-A (CALABARZON) | Laguna | Mabitac | San Antonio | 14.4517 | 121.4213 | R | 1697 | 3.3 | 514 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.08 | 0.81 | Tier 2B: Moderate GIDA Inclusion | 61.81 | 61.81 | 45.02 | 53.42 | D - Other node or line within 3 km | 2.08 | 0.79 | Line: TAYTAY TO SNL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3370
4 | 371 | 3371 | 0403411007 | Region IV-A (CALABARZON) | Laguna | Los Baños | Lalakay | 14.1728 | 121.2148 | U | 4641 | 3.3 | 1406 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 60.58 | 60.58 | 46.27 | 53.42 | C - Line within 0.5 km; node over 1 km | 3.05 | 0.02 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3371
4 | 372 | 3372 | 0803738019 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Danao | 11.0898 | 124.682 | R | 2115 | 3.8 | 557 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.61 | 9.49 | Tier 1B: High GIDA Priority | 47.74 | 47.74 | 59.11 | 53.42 | F - Nearest node and line over 5 km | 11.87 | 9.48 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3372
4 | 373 | 3373 | 1403208002 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Balatoc | 17.3558 | 121.0928 | R | 1621 | 4.3 | 377 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.84 | 7.37 | Tier 1B: High GIDA Priority | 46.36 | 46.36 | 60.49 | 53.42 | F - Nearest node and line over 5 km | 11.84 | 7.35 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3373
4 | 374 | 3374 | 1381100155 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 155 | 14.396 | 120.8665 | U | 418 | 3.45 | 121 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.69 | 37.69 | 69.16 | 53.42 | B - Node 0.5-1 km | 0.54 | 0.06 | Line: PSG001 RELIANCE TO NCC001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3374
4 | 375 | 3375 | 1381100033 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 33 | 14.5653 | 120.9641 | U | 1018 | 2.8 | 364 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.19 | 2.86 | Tier 1B: High GIDA Priority | 36.01 | 36.01 | 70.83 | 53.42 | E - Nearest node or line 3-5 km | 3.19 | 3 | Line: PSG001 RELIANCE TO NCC001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3375
4 | 376 | 3376 | 1705207012 | MIMAROPA Region | Oriental Mindoro | Mansalay | Panaytayan | 12.4707 | 121.3972 | U | 12158 | 3.9 | 3117 | 935 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.18 | 2.16 | Tier 2B: Moderate GIDA Inclusion | 60.65 | 60.65 | 46.17 | 53.41 | D - Other node or line within 3 km | 7.18 | 2.14 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3376
4 | 377 | 3377 | 1380612030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 862 | 11.7907 | 122.3555 | U | 2525 | 4.08 | 619 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.17 | 8.23 | Tier 1B: High GIDA Priority | 36.96 | 36.96 | 69.85 | 53.41 | F - Nearest node and line over 5 km | 10.17 | 8.23 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3377
4 | 378 | 3378 | 0806014001 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Aguingayan | 12.116 | 125.0397 | R | 391 | 4.1 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 97.54 | 98.38 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 70.14 | 53.41 | F - Nearest node and line over 5 km | 97.54 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3378
4 | 379 | 3379 | 1907010001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Baldatal Islam | 17.2558 | 122.2298 | R | 1818 | 5.8 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.42 | Tier 1B: High GIDA Priority | 32.78 | 32.78 | 74.03 | 53.41 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3379
4 | 380 | 3380 | 1907006009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Tong | 15.4096 | 121.982 | R | 1072 | 5.8 | 185 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59.46 | 59.24 | Tier 1B: High GIDA Priority | 28.79 | 28.79 | 78.02 | 53.41 | F - Nearest node and line over 5 km | 59.46 | 63.56 | Node: BLA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3380
4 | 381 | 3381 | 0301413022 | Region III (Central Luzon) | Bulacan | Norzagaray | Poblacion | 14.9079 | 121.044 | U | 15956 | 3.5 | 4559 | 1368 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.79 | 6.11 | Tier 2B: Moderate GIDA Inclusion | 69.55 | 69.55 | 37.26 | 53.4 | B - Node 0.5-1 km | 0.79 | 6.11 | Node: NZB001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3381
4 | 382 | 3382 | 1907006011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Center | 17.2559 | 122.2299 | R | 914 | 5.8 | 158 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 28.68 | 28.68 | 78.12 | 53.4 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3382
4 | 383 | 3383 | 1004322019 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Casulog | 8.8805 | 124.7997 | R | 3479 | 3.9 | 892 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 0.86 | Tier 2A: High Commercial ROI | 70.84 | 70.84 | 35.93 | 53.39 | D - Other node or line within 3 km | 2.89 | 0.86 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3383
4 | 384 | 3384 | 0301420032 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc Central | 14.817 | 121.0398 | R | 4310 | 3.5 | 1231 | 369 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.77 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 69.54 | 69.54 | 37.23 | 53.39 | D - Other node or line within 3 km | 1.77 | 1.73 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3384
4 | 385 | 3385 | 0401002011 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Muzon Primero | 13.8482 | 120.9914 | R | 2599 | 3.6 | 722 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.34 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 68.76 | 68.76 | 38.03 | 53.39 | C - Line within 0.5 km; node over 1 km | 1.34 | 0.12 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3385
4 | 386 | 3386 | 0300809002 | Region III (Central Luzon) | Bataan | Orani | Balut | 14.8028 | 120.5339 | U | 1319 | 3.6 | 366 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.17 | Tier 1B: High GIDA Priority | 49.26 | 49.26 | 57.52 | 53.39 | A - Node within 0.5 km | 0.28 | 0.04 | Line: 96CORE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3386
4 | 387 | 3387 | 1705322009 | MIMAROPA Region | Palawan | Culion | Malaking Patag | 11.8218 | 119.9468 | R | 2091 | 3.9 | 536 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.77 | 120.98 | Tier 1B: High GIDA Priority | 40.48 | 40.48 | 66.31 | 53.39 | F - Nearest node and line over 5 km | 32.77 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3387
4 | 388 | 3388 | 1408104004 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Bulu | 17.9856 | 121.2829 | R | 408 | 4.2 | 97 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.41 | 0.21 | Tier 1B: High GIDA Priority | 39.34 | 39.34 | 67.44 | 53.39 | F - Nearest node and line over 5 km | 11.41 | 21.57 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3388
4 | 389 | 3389 | 0502004010 | Region V (Bicol Region) | Catanduanes | Caramoran | Guiamlong | 13.799 | 124.1364 | R | 757 | 4.2 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.61 | 61.92 | Tier 1B: High GIDA Priority | 33.42 | 33.42 | 73.36 | 53.39 | F - Nearest node and line over 5 km | 29.61 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3389
4 | 390 | 3390 | 1108202035 | Region XI (Davao Region) | Davao de Oro | Laak | New Bethlehem | 7.8924 | 125.7756 | R | 787 | 3.7 | 213 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.74 | 29.27 | Tier 1B: High GIDA Priority | 32.89 | 32.89 | 73.89 | 53.39 | F - Nearest node and line over 5 km | 31.74 | 29.7 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3390
4 | 391 | 3391 | 0402116006 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael I | 14.4222 | 120.8797 | R | 1316 | 3.4 | 387 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 55.91 | 55.91 | 50.85 | 53.38 | B - Node 0.5-1 km | 0.89 | 0.54 | Line: NOVELETA | Survey short node lateral; confirm port/fiber capacity, access and route. | 3391
4 | 392 | 3392 | 1608501008 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Geotina | 10.0882 | 125.5823 | R | 1231 | 3.8 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.72 | 34.73 | Tier 1B: High GIDA Priority | 39.89 | 39.89 | 66.86 | 53.38 | F - Nearest node and line over 5 km | 34.72 | 999999 | Node: SRO001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3392
4 | 393 | 3393 | 1903610017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Malna Proper | 17.2544 | 122.2284 | R | 1325 | 5.7 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 35.21 | 35.21 | 71.55 | 53.38 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3393
4 | 394 | 3394 | 0701243024 | Region VII (Central Visayas) | Bohol | Talibon | Sag | 10.2104 | 124.352 | R | 930 | 4 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.75 | 39.14 | Tier 1B: High GIDA Priority | 34.12 | 34.12 | 72.65 | 53.38 | F - Nearest node and line over 5 km | 39.75 | 43.17 | Node: LUC002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3394
4 | 395 | 3395 | 0305420008 | Region III (Central Luzon) | Pampanga | Santa Rita | San Matias | 14.9774 | 120.6207 | R | 3795 | 4 | 949 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.51 | Tier 2A: High Commercial ROI | 74.42 | 74.42 | 32.32 | 53.37 | C - Line within 0.5 km; node over 1 km | 1.06 | 0.48 | Line: GUAGUA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3395
4 | 396 | 3396 | 0306903044 | Region III (Central Luzon) | Tarlac | Camiling | Poblacion B | 15.6889 | 120.4133 | R | 1920 | 3.9 | 492 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.19 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 60.37 | 60.37 | 46.37 | 53.37 | A - Node within 0.5 km | 0.19 | 0.19 | Node: CMT001 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3396
4 | 397 | 3397 | 1380610017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 702 | 12.9988 | 120.3773 | U | 3572 | 4.47 | 799 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.09 | 78.64 | Tier 1B: High GIDA Priority | 37.32 | 37.32 | 69.41 | 53.37 | F - Nearest node and line over 5 km | 80.09 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3397
4 | 398 | 3398 | 0600608042 | Region VI (Western Visayas) | Antique | Hamtic | Pili 1, 2, 3 | 10.6751 | 122.0362 | R | 352 | 3.9 | 90 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.46 | 6.18 | Tier 1B: High GIDA Priority | 36.78 | 36.78 | 69.97 | 53.37 | F - Nearest node and line over 5 km | 14.46 | 6.15 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3398
4 | 399 | 3399 | 1907006034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Tubig Dayang Riverside | 15.3919 | 121.9848 | R | 1070 | 5.8 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.99 | 60.78 | Tier 1B: High GIDA Priority | 28.7 | 28.7 | 78.03 | 53.37 | F - Nearest node and line over 5 km | 60.99 | 999999 | Node: BLA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3399
4 | 400 | 3400 | 1102315005 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Cagangohan | 7.2798 | 125.6827 | U | 13446 | 3.7 | 3634 | 1090 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.33 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 69.59 | 69.59 | 37.14 | 53.36 | D - Other node or line within 3 km | 2.33 | 1.12 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3400
4 | 401 | 3401 | 0401005052 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pinamucan | 13.6979 | 121.0541 | R | 4422 | 3.6 | 1228 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 6.5 | Tier 2B: Moderate GIDA Inclusion | 66.05 | 66.05 | 40.67 | 53.36 | D - Other node or line within 3 km | 1.62 | 6.5 | Node: BCY004 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3401
4 | 402 | 3402 | 0600416010 | Region VI (Western Visayas) | Aklan | Numancia | Dongon West | 11.72 | 122.3168 | R | 2257 | 3.9 | 579 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 1.81 | Tier 2B: Moderate GIDA Inclusion | 64.6 | 64.6 | 42.11 | 53.36 | D - Other node or line within 3 km | 2.2 | 4.6 | Node: NUK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3402
4 | 403 | 3403 | 0403410014 | Region IV-A (CALABARZON) | Laguna | Liliw | Ibabang San Roque | 14.1612 | 121.4098 | R | 2292 | 3.3 | 695 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.72 | 2.63 | Tier 2B: Moderate GIDA Inclusion | 62.33 | 62.33 | 44.38 | 53.36 | D - Other node or line within 3 km | 2.72 | 2.63 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3403
4 | 404 | 3404 | 0704612003 | Region VII (Central Visayas) | Negros Oriental | Jimalalud | Apanangon | 10.0446 | 123.107 | R | 2628 | 3.8 | 692 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.51 | 12.43 | Tier 2B: Moderate GIDA Inclusion | 51.19 | 51.19 | 55.54 | 53.36 | F - Nearest node and line over 5 km | 19.51 | 13.41 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3404
4 | 405 | 3405 | 1606722003 | Region XIII (Caraga) | Surigao del Norte | Sison | Gacepan | 9.6805 | 125.4926 | R | 488 | 4.1 | 119 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.96 | 1.97 | Tier 1B: High GIDA Priority | 44.95 | 44.95 | 61.77 | 53.36 | D - Other node or line within 3 km | 11.96 | 1.97 | Line: ALEGRIA - SURIGAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3405
4 | 406 | 3406 | 0401005072 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 3 | 13.7529 | 121.0922 | U | 269 | 3.6 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 3.17 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.18 | 36.18 | 70.54 | 53.36 | D - Other node or line within 3 km | 1.84 | 3.16 | Node: BCY003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3406
4 | 407 | 3407 | 1906612057 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Siolakan | 17.2555 | 122.2295 | R | 2422 | 6 | 404 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 35.14 | 35.14 | 71.57 | 53.36 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3407
4 | 408 | 3408 | 0401005061 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 15 | 13.7267 | 121.1061 | U | 202 | 3.6 | 56 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.67 | 5.71 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 34.98 | 34.98 | 71.74 | 53.36 | D - Other node or line within 3 km | 2.67 | 5.71 | Node: BCY007-PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3408
4 | 409 | 3409 | 1906604029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Luuk | Guimbaun | 17.2519 | 122.2331 | R | 2065 | 6 | 344 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.55 | 34.63 | Tier 1B: High GIDA Priority | 33.57 | 33.57 | 73.14 | 53.36 | F - Nearest node and line over 5 km | 29.55 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3409
4 | 410 | 3410 | 1380601037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 37 | 12.1214 | 120.9251 | U | 2456 | 4.35 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.68 | 29.68 | Tier 1B: High GIDA Priority | 31.21 | 31.21 | 75.51 | 53.36 | F - Nearest node and line over 5 km | 29.68 | 29.67 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3410
4 | 411 | 3411 | 0304908010 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Lorenzo | 15.3125 | 120.9538 | U | 6467 | 3.5 | 1848 | 554 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.04 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 65.18 | 65.18 | 41.53 | 53.35 | C - Line within 0.5 km; node over 1 km | 2.43 | 0.13 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3411
4 | 412 | 3412 | 0304930006 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bakal III | 15.7035 | 120.8989 | U | 7145 | 3.5 | 2041 | 612 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.42 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 65.08 | 65.08 | 41.62 | 53.35 | C - Line within 0.5 km; node over 1 km | 1.42 | 0.29 | Line: DWDM SANTO DOMINGO, NUEVA ECIJA TO UMINGAN, PANGASINAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3412
4 | 413 | 3413 | 0403417034 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Poblacion II | 14.1747 | 121.4116 | U | 3627 | 3.3 | 1099 | 330 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 1.93 | Tier 2B: Moderate GIDA Inclusion | 59.29 | 59.29 | 47.41 | 53.35 | D - Other node or line within 3 km | 3.35 | 1.92 | Line: PAGSANJAN TO LILIW | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3413
4 | 414 | 3414 | 1381300111 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sauyo | 14.6896 | 121.0433 | U | 77274 | 3.76 | 20540 | 6162 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 1.44 | 1.3 | Tier 1B: High GIDA Priority | 47.46 | 47.46 | 59.24 | 53.35 | D - Other node or line within 3 km | 1.44 | 1.29 | Line: UG 144C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3414
4 | 415 | 3415 | 0405632004 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Luod | 14.8285 | 122.1019 | R | 1004 | 3.8 | 264 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.61 | 77.12 | Tier 1B: High GIDA Priority | 36.49 | 36.49 | 70.21 | 53.35 | F - Nearest node and line over 5 km | 47.61 | 999999 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3415
4 | 416 | 3416 | 1381100049 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 49 | 14.5655 | 121.0651 | U | 415 | 3.52 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.65 | 0.51 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.63 | 35.63 | 71.07 | 53.35 | C - Line within 0.5 km; node over 1 km | 1.65 | 0.48 | Line: UG 144C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3416
4 | 417 | 3417 | 1903621007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Bubong Tawa-an | 17.2545 | 122.2286 | R | 811 | 5.7 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.37 | 34.26 | Tier 1B: High GIDA Priority | 32.85 | 32.85 | 73.85 | 53.35 | F - Nearest node and line over 5 km | 29.37 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3417
4 | 418 | 3418 | 0403430010 | Region IV-A (CALABARZON) | Laguna | Victoria | San Roque | 14.2263 | 121.3219 | U | 11896 | 3.3 | 3605 | 1082 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.52 | 3.64 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 38.85 | 53.34 | E - Nearest node or line 3-5 km | 3.52 | 3.62 | Node: VTL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3418
4 | 419 | 3419 | 0402113007 | Region IV-A (CALABARZON) | Cavite | Maragondon | San Miguel I A | 14.2848 | 120.7448 | R | 1493 | 3.4 | 439 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 56.61 | 56.61 | 50.06 | 53.34 | C - Line within 0.5 km; node over 1 km | 1.29 | 0.04 | Line: MARAGONDON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3419
4 | 420 | 3420 | 1204716007 | Region XII (SOCCSKSARGEN) | Cotabato | Banisilan | Kiaring | 7.3755 | 124.6771 | R | 1749 | 3.8 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.31 | 11.6 | Tier 1B: High GIDA Priority | 39.87 | 39.87 | 66.81 | 53.34 | F - Nearest node and line over 5 km | 23.31 | 11.6 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3420
4 | 421 | 3421 | 0806014006 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Gusa | 12.1077 | 125.0526 | R | 394 | 4.1 | 96 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.68 | 98.08 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 70 | 53.34 | F - Nearest node and line over 5 km | 96.68 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3421
4 | 422 | 3422 | 0502004018 | Region V (Bicol Region) | Catanduanes | Caramoran | Maysuran | 13.9796 | 124.163 | R | 1099 | 4.2 | 262 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.59 | 77.76 | Tier 1B: High GIDA Priority | 34.79 | 34.79 | 71.89 | 53.34 | F - Nearest node and line over 5 km | 39.59 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3422
4 | 423 | 3423 | 0300803006 | Region III (Central Luzon) | Bataan | City of Balanga | Central | 14.6637 | 120.5376 | U | 7399 | 3.6 | 2055 | 616 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 64.68 | 64.68 | 41.97 | 53.33 | D - Other node or line within 3 km | 1.68 | 1.53 | Line: PILAR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3423
4 | 424 | 3424 | 1381300126 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Ugong Norte | 14.5824 | 121.0271 | U | 6580 | 5.23 | 1259 | 378 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 60.43 | 60.43 | 46.23 | 53.33 | A - Node within 0.5 km | 0.17 | 0.18 | Node: MAN033 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3424
4 | 425 | 3425 | 0600403013 | Region VI (Western Visayas) | Aklan | Banga | Linabuan Sur | 11.6499 | 122.3444 | R | 4098 | 3.9 | 1051 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.15 | 0.25 | Tier 2A: High Commercial ROI | 70.72 | 70.72 | 35.91 | 53.32 | C - Line within 0.5 km; node over 1 km | 2.15 | 0.25 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3425
4 | 426 | 3426 | 1401109006 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Sagpat | 16.6738 | 120.6316 | R | 3812 | 3.5 | 1089 | 327 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.52 | 14.93 | Tier 2B: Moderate GIDA Inclusion | 68.33 | 68.33 | 38.32 | 53.32 | E - Nearest node or line 3-5 km | 3.52 | 14.92 | Node: KIB001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3426
4 | 427 | 3427 | 0305403025 | Region III (Central Luzon) | Pampanga | Arayat | San Jose Mesulo | 15.1425 | 120.7707 | U | 5717 | 4 | 1429 | 429 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.11 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 65.84 | 65.84 | 40.81 | 53.32 | A - Node within 0.5 km | 0.11 | 0.11 | Node: ARP001 - TYPE 2 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3427
4 | 428 | 3428 | 0401033007 | Region IV-A (CALABARZON) | Batangas | Tingloy | Pisa | 13.6342 | 120.9392 | R | 705 | 3.6 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.79 | 14.27 | Tier 1B: High GIDA Priority | 45.17 | 45.17 | 61.46 | 53.32 | F - Nearest node and line over 5 km | 7.79 | 14.2 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3428
4 | 429 | 3429 | 0806013019 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Manaing | 11.4956 | 125.0623 | R | 312 | 4.1 | 76 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.2 | 32.01 | Tier 1B: High GIDA Priority | 37.42 | 37.42 | 69.22 | 53.32 | F - Nearest node and line over 5 km | 29.2 | 32 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3429
4 | 430 | 3430 | 1380614022 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 766 | 12.7043 | 123.1407 | U | 3321 | 4.2 | 790 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.35 | 38.18 | Tier 1B: High GIDA Priority | 37.06 | 37.06 | 69.57 | 53.32 | F - Nearest node and line over 5 km | 35.35 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3430
4 | 431 | 3431 | 1381100163 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 163 | 14.7136 | 120.8901 | U | 1487 | 3.42 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.03 | 6.53 | Tier 1B: High GIDA Priority | 36.18 | 36.18 | 70.45 | 53.32 | F - Nearest node and line over 5 km | 5.03 | 6.53 | Node: OBB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3431
4 | 432 | 3432 | 1705321004 | MIMAROPA Region | Palawan | Kalayaan | Pag-Asa | 9.4482 | 118.3879 | R | 229 | 3.9 | 59 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 49.94 | 52.22 | Tier 1B: High GIDA Priority | 34.65 | 34.65 | 71.99 | 53.32 | F - Nearest node and line over 5 km | 49.94 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3432
4 | 433 | 3433 | 0702215009 | Region VII (Central Visayas) | Cebu | Carmen | Cogon East | 10.5909 | 124.0212 | R | 3391 | 3.8 | 892 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 68.1 | 68.1 | 38.52 | 53.31 | C - Line within 0.5 km; node over 1 km | 1.58 | 0.34 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3433
4 | 434 | 3434 | 0806004039 | Region VIII (Eastern Visayas) | Samar | Calbiga | Sinalangtan | 11.5728 | 125.0783 | R | 154 | 4.1 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 37.96 | 40.76 | Tier 1B: High GIDA Priority | 36.93 | 36.93 | 69.68 | 53.31 | F - Nearest node and line over 5 km | 37.96 | 40.75 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3434
4 | 435 | 3435 | 1381100019 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 19 | 14.5606 | 120.9833 | U | 411 | 3.14 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 1.23 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.38 | 36.38 | 70.25 | 53.31 | D - Other node or line within 3 km | 1.22 | 1.21 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3435
4 | 436 | 3436 | 0405619010 | Region IV-A (CALABARZON) | Quezon | Gumaca | Buensuceso | 13.8838 | 122.1214 | R | 4024 | 3.8 | 1059 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 2.04 | Tier 2B: Moderate GIDA Inclusion | 62.01 | 62.01 | 44.58 | 53.3 | D - Other node or line within 3 km | 4.59 | 1.88 | Line: AE UNQ001 TO CDQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3436
4 | 437 | 3437 | 0501712002 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Bucal | 13.9002 | 122.6756 | R | 170 | 4.2 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.31 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 51.48 | 51.48 | 55.11 | 53.3 | D - Other node or line within 3 km | 6.31 | 1.95 | Line: CALAUAG TO RAGAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3437
4 | 438 | 3438 | 0203123013 | Region II (Cagayan Valley) | Isabela | Quirino | Santa Catalina | 17.1619 | 121.6775 | R | 802 | 3.9 | 206 | 62 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.93 | 6.74 | Tier 1B: High GIDA Priority | 46.16 | 46.16 | 60.45 | 53.3 | F - Nearest node and line over 5 km | 6.93 | 6.74 | Line: ROXAS - GAMU | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3438
4 | 439 | 3439 | 1108202024 | Region XI (Davao Region) | Davao de Oro | Laak | Datu Ampunan | 7.9489 | 125.6931 | R | 1777 | 3.7 | 480 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.77 | 35.61 | Tier 1B: High GIDA Priority | 38.98 | 38.98 | 67.6 | 53.29 | F - Nearest node and line over 5 km | 41.77 | 40.75 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3439
4 | 440 | 3440 | 0802615017 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 5 | 11.4907 | 125.446 | R | 841 | 3.9 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.84 | 56.21 | Tier 1B: High GIDA Priority | 38.07 | 38.07 | 68.5 | 53.29 | F - Nearest node and line over 5 km | 55.84 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3440
4 | 441 | 3441 | 1903610029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Dilabayan | 17.2544 | 122.2285 | R | 1279 | 5.7 | 224 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 34.95 | 34.95 | 71.64 | 53.29 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3441
4 | 442 | 3442 | 0307103007 | Region III (Central Luzon) | Zambales | Candelaria | Malabon | 15.6385 | 119.9349 | R | 3329 | 3.8 | 876 | 263 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 67.85 | 67.85 | 38.71 | 53.28 | C - Line within 0.5 km; node over 1 km | 1.68 | 0.35 | Line: IBA TO SANTA CRUZ | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3442
4 | 443 | 3443 | 0306905054 | Region III (Central Luzon) | Tarlac | Concepcion | San Vicente | 15.2951 | 120.6454 | R | 2335 | 3.9 | 599 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.38 | 0.78 | Tier 2B: Moderate GIDA Inclusion | 58.07 | 58.07 | 48.49 | 53.28 | D - Other node or line within 3 km | 3.38 | 0.78 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3443
4 | 444 | 3444 | 0603044025 | Region VI (Western Visayas) | Iloilo | Sara | Juaneza | 11.2265 | 123.0123 | R | 971 | 3.8 | 256 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 51.5 | 51.5 | 55.06 | 53.28 | D - Other node or line within 3 km | 3.25 | 0.76 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3444
4 | 445 | 3445 | 0405647010 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angustias Zone IV | 14.0337 | 121.6137 | R | 1208 | 3.8 | 318 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.45 | 2.24 | Tier 1B: High GIDA Priority | 47.92 | 47.92 | 58.63 | 53.28 | D - Other node or line within 3 km | 2.45 | 2.24 | Line: LBQ001 TO GCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3445
4 | 446 | 3446 | 1705305012 | MIMAROPA Region | Palawan | Bataraza | Puring | 8.3856 | 117.2259 | R | 1646 | 3.9 | 422 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 223.85 | 226.14 | Tier 1B: High GIDA Priority | 37.18 | 37.18 | 69.39 | 53.28 | F - Nearest node and line over 5 km | 223.85 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3446
4 | 447 | 3447 | 0502009021 | Region V (Bicol Region) | Catanduanes | San Miguel | San Marcos | 13.7163 | 124.2516 | R | 240 | 4.2 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.42 | 67.82 | Tier 1B: High GIDA Priority | 36.83 | 36.83 | 69.74 | 53.28 | F - Nearest node and line over 5 km | 42.42 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3447
4 | 448 | 3448 | 1906614025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Pagatpat | 17.2556 | 122.2297 | R | 1371 | 6 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 35.02 | 35.02 | 71.55 | 53.28 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3448
4 | 449 | 3449 | 1705205006 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Bayanan II | 13.357 | 121.1701 | R | 3122 | 3.9 | 801 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.91 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 65.44 | 65.44 | 41.09 | 53.27 | C - Line within 0.5 km; node over 1 km | 1.91 | 0.1 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3449
4 | 450 | 3450 | 0403405021 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lingga | 14.2157 | 121.1823 | U | 6789 | 3.3 | 2057 | 617 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.4 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 61.23 | 61.23 | 45.32 | 53.27 | C - Line within 0.5 km; node over 1 km | 4.4 | 0.03 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3450
4 | 451 | 3451 | 1004301006 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Loguilo | 8.5759 | 124.4941 | R | 3582 | 3.9 | 918 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 0.27 | Tier 2A: High Commercial ROI | 72.35 | 72.35 | 34.16 | 53.26 | C - Line within 0.5 km; node over 1 km | 2.19 | 0.21 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3451
4 | 452 | 3452 | 1908812003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Guindulungan | Datalpandan | 16.3155 | 122.4298 | R | 2245 | 4.7 | 478 | 143 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.92 | 25.89 | Tier 1B: High GIDA Priority | 37.33 | 37.33 | 69.2 | 53.26 | F - Nearest node and line over 5 km | 26.92 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3452
4 | 453 | 3453 | 0806004001 | Region VIII (Eastern Visayas) | Samar | Calbiga | Antol | 11.5446 | 125.1213 | R | 257 | 4.1 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.3 | 38.89 | Tier 1B: High GIDA Priority | 36.99 | 36.99 | 69.54 | 53.26 | F - Nearest node and line over 5 km | 36.3 | 38.89 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3453
4 | 454 | 3454 | 0806004009 | Region VIII (Eastern Visayas) | Samar | Calbiga | Caamlongan | 11.5681 | 125.1155 | R | 232 | 4.1 | 57 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.55 | 41.2 | Tier 1B: High GIDA Priority | 36.91 | 36.91 | 69.61 | 53.26 | F - Nearest node and line over 5 km | 38.55 | 41.2 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3454
4 | 455 | 3455 | 0806004019 | Region VIII (Eastern Visayas) | Samar | Calbiga | Mahangcao | 11.6118 | 125.0798 | R | 357 | 4.1 | 87 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.24 | 45.07 | Tier 1B: High GIDA Priority | 36.83 | 36.83 | 69.69 | 53.26 | F - Nearest node and line over 5 km | 42.24 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3455
4 | 456 | 3456 | 1381100159 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 159 | 14.6639 | 121.1693 | U | 1249 | 3.06 | 408 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.77 | 3.94 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 70.86 | 53.26 | E - Nearest node or line 3-5 km | 4.77 | 3.79 | Line: Aerial 24C | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3456
4 | 457 | 3457 | 1381100050 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 50 | 14.4814 | 120.975 | U | 490 | 3.14 | 156 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.13 | 0.7 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.49 | 35.49 | 71.03 | 53.26 | D - Other node or line within 3 km | 2.13 | 0.7 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3457
4 | 458 | 3458 | 0300802008 | Region III (Central Luzon) | Bataan | Bagac | Pag-asa | 14.6088 | 120.3868 | R | 3895 | 3.6 | 1082 | 325 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 69.98 | 69.98 | 36.52 | 53.25 | C - Line within 0.5 km; node over 1 km | 1.25 | 0.38 | Line: Subic-Bagac AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3458
4 | 459 | 3459 | 0305408012 | Region III (Central Luzon) | Pampanga | Lubao | Remedios | 14.9179 | 120.5797 | R | 4754 | 4 | 1188 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 38.69 | 53.25 | C - Line within 0.5 km; node over 1 km | 2.89 | 0.34 | Line: LUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3459
4 | 460 | 3460 | 0301404015 | Region III (Central Luzon) | Bulacan | Bocaue | Sulucan | 14.7902 | 120.9246 | R | 2919 | 3.5 | 834 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 66.68 | 66.68 | 39.83 | 53.25 | D - Other node or line within 3 km | 1.68 | 0.73 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3460
4 | 461 | 3461 | 0105533014 | Region I (Ilocos Region) | Pangasinan | San Fabian | Longos | 16.1059 | 120.3952 | R | 2872 | 3.6 | 798 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 66.53 | 66.53 | 39.98 | 53.25 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.04 | Line: SAN FABIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3461
4 | 462 | 3462 | 1380601131 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 131 | 13.2862 | 122.6682 | U | 1258 | 3.71 | 339 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.3 | 33.44 | Tier 1B: High GIDA Priority | 34.29 | 34.29 | 72.21 | 53.25 | E - Nearest node or line 3-5 km | 4.3 | 33.44 | Node: SDQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3462
4 | 463 | 3463 | 1906613009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Buroh | 17.2554 | 122.2295 | R | 1451 | 6 | 242 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.5 | 34.38 | Tier 1B: High GIDA Priority | 30.96 | 30.96 | 75.55 | 53.25 | F - Nearest node and line over 5 km | 29.5 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3463
4 | 464 | 3464 | 0203130014 | Region II (Cagayan Valley) | Isabela | San Manuel | District 4 | 17.0241 | 121.6379 | R | 2596 | 3.8 | 683 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.02 | 0.7 | Tier 2B: Moderate GIDA Inclusion | 65.24 | 65.24 | 41.24 | 53.24 | D - Other node or line within 3 km | 3.02 | 0.7 | Line: ROXAS - CABATUAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3464
4 | 465 | 3465 | 0501606023 | Region V (Bicol Region) | Camarines Norte | Labo | Dumagmang | 14.0887 | 122.629 | R | 2853 | 4 | 713 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.75 | 8.52 | Tier 2B: Moderate GIDA Inclusion | 52.97 | 52.97 | 53.52 | 53.24 | F - Nearest node and line over 5 km | 9.75 | 8.52 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3465
4 | 466 | 3466 | 1381100176 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 176 | 14.3202 | 121.0137 | U | 1503 | 4.04 | 372 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.21 | 3.5 | Tier 1B: High GIDA Priority | 36.25 | 36.25 | 70.24 | 53.24 | E - Nearest node or line 3-5 km | 3.21 | 3.66 | Node: CRC002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3466
4 | 467 | 3467 | 1400102006 | Cordillera Administrative Region (CAR) | Abra | Boliney | Kilong-Olao | 17.3742 | 120.8658 | R | 273 | 3.8 | 72 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.84 | 28.88 | Tier 1B: High GIDA Priority | 34.29 | 34.29 | 72.2 | 53.24 | F - Nearest node and line over 5 km | 29.84 | 28.74 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3467
4 | 468 | 3468 | 0403402013 | Region IV-A (CALABARZON) | Laguna | Bay | Santo Domingo | 14.1768 | 121.266 | U | 10856 | 3.3 | 3290 | 987 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 69.73 | 69.73 | 36.73 | 53.23 | B - Node 0.5-1 km | 0.88 | 0.1 | Line: CLB001 TO SCL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3468
4 | 469 | 3469 | 0301419021 | Region III (Central Luzon) | Bulacan | San Ildefonso | Matimbubong | 15.0659 | 120.9453 | R | 2933 | 3.5 | 838 | 251 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 68.08 | 68.08 | 38.37 | 53.23 | B - Node 0.5-1 km | 0.93 | 0.06 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3469
4 | 470 | 3470 | 0301405004 | Region III (Central Luzon) | Bulacan | Bulacan | Matungao | 14.8051 | 120.8804 | U | 13536 | 3.5 | 3867 | 1160 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.03 | 2.58 | Tier 2B: Moderate GIDA Inclusion | 67.84 | 67.84 | 38.61 | 53.23 | D - Other node or line within 3 km | 1.03 | 2.58 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3470
4 | 471 | 3471 | 0304932003 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Carmen | 15.4456 | 120.8278 | R | 3949 | 3.5 | 1128 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.1 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 66.34 | 66.34 | 40.11 | 53.23 | C - Line within 0.5 km; node over 1 km | 4.1 | 0.04 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3471
4 | 472 | 3472 | 0701230013 | Region VII (Central Visayas) | Bohol | Loon | Bugho | 9.7937 | 123.8332 | R | 212 | 4 | 53 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.06 | 4.03 | Tier 1B: High GIDA Priority | 44.92 | 44.92 | 61.55 | 53.23 | E - Nearest node or line 3-5 km | 4.06 | 4 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3472
4 | 473 | 3473 | 1900713012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Tong-Umus | 6.297 | 121.9728 | R | 3541 | 5.1 | 694 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.1 | 69.1 | Tier 1B: High GIDA Priority | 42.04 | 42.04 | 64.43 | 53.23 | F - Nearest node and line over 5 km | 69.1 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3473
4 | 474 | 3474 | 0907324008 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | San Miguel | Dumalian | 7.7227 | 123.2407 | R | 742 | 3.9 | 190 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.47 | 9.03 | Tier 1B: High GIDA Priority | 37.28 | 37.28 | 69.17 | 53.23 | F - Nearest node and line over 5 km | 20.47 | 9.03 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3474
4 | 475 | 3475 | 1381100139 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 139 | 14.3661 | 120.9958 | U | 956 | 3.29 | 291 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 2.01 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.65 | 35.65 | 70.8 | 53.23 | D - Other node or line within 3 km | 2.01 | 5.21 | Node: MUN048 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3475
4 | 476 | 3476 | 0601902017 | Region VI (Western Visayas) | Capiz | Dao | Nasunogan | 11.3717 | 122.6753 | R | 2942 | 3.8 | 774 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.83 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 68.09 | 68.09 | 38.36 | 53.22 | C - Line within 0.5 km; node over 1 km | 2.83 | 0.38 | Line: ROXAS - ILOILO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3476
4 | 477 | 3477 | 0504111015 | Region V (Bicol Region) | Masbate | City of Masbate | Espinosa | 12.3752 | 123.6209 | U | 7138 | 4.1 | 1741 | 522 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 66.01 | 66.01 | 40.44 | 53.22 | D - Other node or line within 3 km | 2.02 | 1.7 | Line: MASBATE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3477
4 | 478 | 3478 | 1381300030 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Dioquino Zobel | 14.6692 | 121.0639 | U | 1868 | 4.42 | 423 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 0.35 | Tier 1B: High GIDA Priority | 44.19 | 44.19 | 62.26 | 53.22 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.34 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3478
4 | 479 | 3479 | 1380612006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 838 | 13.5455 | 120.591 | U | 3238 | 4.27 | 759 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.66 | 31.76 | Tier 1B: High GIDA Priority | 36.27 | 36.27 | 70.17 | 53.22 | F - Nearest node and line over 5 km | 31.66 | 45.97 | Node: CTG001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3479
4 | 480 | 3480 | 0301405005 | Region III (Central Luzon) | Bulacan | Bulacan | Maysantol | 14.7867 | 120.8835 | R | 3089 | 3.5 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 4.25 | Tier 2B: Moderate GIDA Inclusion | 65.34 | 65.34 | 41.08 | 53.21 | D - Other node or line within 3 km | 1.2 | 4.25 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3480
4 | 481 | 3481 | 1001316016 | Region X (Northern Mindanao) | Bukidnon | Pangantucan | Payad | 7.5642 | 124.8543 | R | 1257 | 3.8 | 331 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.26 | 11.22 | Tier 1B: High GIDA Priority | 46.2 | 46.2 | 60.21 | 53.21 | F - Nearest node and line over 5 km | 7.26 | 11.21 | Node: KDB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3481
4 | 482 | 3482 | 0907307001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Bag-ong Misamis | 7.758 | 123.3558 | R | 250 | 3.9 | 64 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.25 | 6.45 | Tier 1B: High GIDA Priority | 39.7 | 39.7 | 66.73 | 53.21 | F - Nearest node and line over 5 km | 12.25 | 6.35 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3482
4 | 483 | 3483 | 0806004008 | Region VIII (Eastern Visayas) | Samar | Calbiga | Buluan | 11.6256 | 125.1354 | R | 642 | 4.1 | 157 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.3 | 47.95 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 69.63 | 53.21 | F - Nearest node and line over 5 km | 45.3 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3483
4 | 484 | 3484 | 0806014005 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Cataydongan | 12.0067 | 125.0381 | R | 324 | 4.1 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 85.39 | 87.22 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.74 | 53.21 | F - Nearest node and line over 5 km | 85.39 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3484
4 | 485 | 3485 | 0806022001 | Region VIII (Eastern Visayas) | Samar | Paranas | Anagasi | 11.9501 | 125.11 | R | 206 | 4.1 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 79.86 | 82.75 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 74.23 | 53.21 | F - Nearest node and line over 5 km | 79.86 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3485
4 | 486 | 3486 | 1380604007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 274 | 12.2243 | 120.8978 | U | 2062 | 3.83 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.94 | 22.92 | Tier 1B: High GIDA Priority | 30.51 | 30.51 | 75.9 | 53.21 | F - Nearest node and line over 5 km | 22.94 | 22.92 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3486
4 | 487 | 3487 | 0403422007 | Region IV-A (CALABARZON) | Laguna | Pila | Labuin | 14.246 | 121.3683 | U | 6312 | 3.3 | 1913 | 574 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.03 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 65.21 | 65.21 | 41.19 | 53.2 | C - Line within 0.5 km; node over 1 km | 1.03 | 0.17 | Line: UG SCL001 TO PLL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3487
4 | 488 | 3488 | 0304926031 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 2nd | 15.7975 | 120.9751 | U | 6641 | 3.5 | 1897 | 569 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 64.68 | 64.68 | 41.71 | 53.2 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.11 | Line: LUPAO - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3488
4 | 489 | 3489 | 0402111012 | Region IV-A (CALABARZON) | Cavite | Kawit | Wakas I | 14.4371 | 120.8958 | R | 2023 | 3.4 | 595 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 60.24 | 60.24 | 46.17 | 53.2 | D - Other node or line within 3 km | 1.61 | 0.58 | Line: KAWIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3489
4 | 490 | 3490 | 0402108004 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Sampalucan Pob. | 14.3871 | 120.8794 | R | 796 | 3.4 | 234 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 1.66 | Tier 2B: Moderate GIDA Inclusion | 50.45 | 50.45 | 55.95 | 53.2 | D - Other node or line within 3 km | 1.59 | 1.68 | Node: TZC003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3490
4 | 491 | 3491 | 1380601206 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 205 | 13.7955 | 121.3359 | U | 1832 | 4.37 | 419 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.9 | 3.54 | Tier 1B: High GIDA Priority | 35.92 | 35.92 | 70.47 | 53.2 | E - Nearest node or line 3-5 km | 4.9 | 3.51 | Line: BCY001 TO LCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3491
4 | 492 | 3492 | 1001304015 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Maraymaray | 7.7354 | 124.9307 | R | 3455 | 3.8 | 909 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.27 | 8.6 | Tier 2B: Moderate GIDA Inclusion | 61.09 | 61.09 | 45.29 | 53.19 | F - Nearest node and line over 5 km | 5.27 | 8.35 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3492
4 | 493 | 3493 | 1380601235 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 234 | 13.9413 | 121.966 | U | 2013 | 3.83 | 525 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.27 | 4.07 | Tier 1B: High GIDA Priority | 37.97 | 37.97 | 68.41 | 53.19 | E - Nearest node or line 3-5 km | 6.27 | 4.07 | Line: PAGBILAO - NAGA (UG + Aerial) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3493
4 | 494 | 3494 | 1380611006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 672 | 14.1943 | 122.073 | U | 3268 | 4.16 | 786 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.12 | 25.81 | Tier 1B: High GIDA Priority | 36.97 | 36.97 | 69.41 | 53.19 | F - Nearest node and line over 5 km | 19.12 | 25.81 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3494
4 | 495 | 3495 | 1380601032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 32 | 14.0494 | 121.774 | U | 2221 | 4.09 | 543 | 163 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.11 | 5.03 | Tier 1B: High GIDA Priority | 32.54 | 32.54 | 73.84 | 53.19 | E - Nearest node or line 3-5 km | 13.11 | 4.94 | Line: PAGBILAO - NAGA (UG + Aerial) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3495
4 | 496 | 3496 | 1001321004 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Batangan | 7.9128 | 125.1013 | U | 15973 | 3.8 | 4203 | 1261 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.31 | 0.91 | Tier 2A: High Commercial ROI | 72.77 | 72.77 | 33.58 | 53.18 | D - Other node or line within 3 km | 1.31 | 0.93 | Line: HDD | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3496
4 | 497 | 3497 | 0806407040 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Mantahan | 10.1333 | 124.8517 | R | 4152 | 4.1 | 1013 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.09 | Tier 2A: High Commercial ROI | 72.37 | 72.37 | 33.99 | 53.18 | C - Line within 0.5 km; node over 1 km | 2.46 | 0.12 | Line: INOPACAN (BAYBAY) - MAASIN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3497
4 | 498 | 3498 | 0300812004 | Region III (Central Luzon) | Bataan | Samal | Imelda | 14.7818 | 120.5034 | R | 3194 | 3.6 | 887 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.2 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 69.5 | 69.5 | 36.85 | 53.18 | D - Other node or line within 3 km | 4.2 | 1.12 | Line: SAMAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3498
4 | 499 | 3499 | 1705205017 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Canubing I | 13.3579 | 121.1355 | R | 3998 | 3.9 | 1025 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 0.61 | Tier 2B: Moderate GIDA Inclusion | 68.19 | 68.19 | 38.17 | 53.18 | C - Line within 0.5 km; node over 1 km | 3.33 | 0.39 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3499
4 | 500 | 3500 | 1001312003 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Busdi | 7.9091 | 125.0007 | R | 2958 | 3.8 | 778 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 1.2 | Tier 2B: Moderate GIDA Inclusion | 65.62 | 65.62 | 40.75 | 53.18 | D - Other node or line within 3 km | 1.46 | 1.19 | Line: DAMULOG - VALENCIA - QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3500
4 | 501 | 3501 | 0806004038 | Region VIII (Eastern Visayas) | Samar | Calbiga | San Mauricio | 11.5933 | 125.0447 | R | 302 | 4.1 | 74 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.6 | 42.52 | Tier 1B: High GIDA Priority | 36.89 | 36.89 | 69.48 | 53.18 | F - Nearest node and line over 5 km | 39.6 | 42.51 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3501
4 | 502 | 3502 | 0304904013 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Norte | 15.2763 | 120.8766 | R | 4166 | 3.5 | 1190 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 69.28 | 69.28 | 37.06 | 53.17 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.18 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3502
4 | 503 | 3503 | 0103302014 | Region I (Ilocos Region) | La Union | Aringay | San Benito Norte | 16.4127 | 120.3528 | R | 3012 | 3.7 | 814 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.97 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 65.67 | 65.67 | 40.66 | 53.17 | C - Line within 0.5 km; node over 1 km | 1.97 | 0.09 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3503
4 | 504 | 3504 | 0402111013 | Region IV-A (CALABARZON) | Cavite | Kawit | Batong Dalig | 14.4349 | 120.8971 | U | 5412 | 3.4 | 1592 | 478 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 63.16 | 63.16 | 43.19 | 53.17 | C - Line within 0.5 km; node over 1 km | 1.63 | 0.3 | Line: KAWIT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3504
4 | 505 | 3505 | 0203135019 | Region II (Cagayan Valley) | Isabela | City of Santiago | Mabini | 16.7001 | 121.5612 | U | 7548 | 3.8 | 1986 | 596 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.7 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 61.85 | 61.85 | 44.5 | 53.17 | C - Line within 0.5 km; node over 1 km | 3.7 | 0.33 | Line: SEGMENT 12 (CAUAYAN - SANTIAGO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3505
4 | 506 | 3506 | 0600407002 | Region VI (Western Visayas) | Aklan | Kalibo | Bachaw Norte | 11.7261 | 122.3685 | R | 2691 | 3.9 | 690 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.19 | 1.48 | Tier 2B: Moderate GIDA Inclusion | 61.29 | 61.29 | 45.05 | 53.17 | D - Other node or line within 3 km | 3.19 | 1.48 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3506
4 | 507 | 3507 | 0102821005 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Cristobal | 18.154 | 120.6651 | R | 1693 | 3.7 | 458 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 3 | Tier 2B: Moderate GIDA Inclusion | 57.03 | 57.03 | 49.32 | 53.17 | D - Other node or line within 3 km | 1.99 | 3 | Node: SRI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3507
4 | 508 | 3508 | 1903639008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Lusain | 17.2546 | 122.2286 | R | 1230 | 5.7 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.37 | 34.26 | Tier 1B: High GIDA Priority | 34.77 | 34.77 | 71.57 | 53.17 | F - Nearest node and line over 5 km | 29.37 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3508
4 | 509 | 3509 | 0806022046 | Region VIII (Eastern Visayas) | Samar | Paranas | Tula | 11.8859 | 125.2455 | R | 421 | 4.1 | 103 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 76.58 | 79.18 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 74.16 | 53.17 | F - Nearest node and line over 5 km | 76.58 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3509
4 | 510 | 3510 | 0600414021 | Region VI (Western Visayas) | Aklan | Nabas | Union | 11.933 | 121.9558 | R | 3744 | 3.9 | 960 | 288 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.33 | Tier 2A: High Commercial ROI | 73.4 | 73.4 | 32.91 | 53.16 | D - Other node or line within 3 km | 2.02 | 999999 | Node: MYK001 - TYPE 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3510
4 | 511 | 3511 | 0604531009 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VI | 10.8991 | 123.0729 | U | 5874 | 3.7 | 1588 | 476 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.27 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 68.83 | 68.83 | 37.49 | 53.16 | A - Node within 0.5 km | 0.27 | 0.11 | Line: TALISAY - VICTORIAS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3511
4 | 512 | 3512 | 0601902004 | Region VI (Western Visayas) | Capiz | Dao | Balucuan | 11.3744 | 122.7002 | R | 3516 | 3.8 | 925 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.82 | 2.89 | Tier 2B: Moderate GIDA Inclusion | 68.04 | 68.04 | 38.28 | 53.16 | D - Other node or line within 3 km | 2.82 | 2.85 | Node: DOZ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3512
4 | 513 | 3513 | 0403409003 | Region IV-A (CALABARZON) | Laguna | Kalayaan | San Juan | 14.3248 | 121.4766 | U | 7303 | 3.3 | 2213 | 664 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 66.46 | 66.46 | 39.87 | 53.16 | B - Node 0.5-1 km | 0.86 | 0.2 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3513
4 | 514 | 3514 | 1404408004 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Bekigan | 17.1824 | 121.0127 | R | 507 | 3.7 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.79 | 3.92 | Tier 1B: High GIDA Priority | 46.68 | 46.68 | 59.64 | 53.16 | E - Nearest node or line 3-5 km | 3.79 | 3.62 | Line: Untitled Path | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3514
4 | 515 | 3515 | 0601911022 | Region VI (Western Visayas) | Capiz | Pilar | San Silvestre | 11.4428 | 123.0425 | R | 824 | 3.8 | 217 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.02 | 4.74 | Tier 1B: High GIDA Priority | 44.97 | 44.97 | 61.35 | 53.16 | E - Nearest node or line 3-5 km | 6.02 | 4.74 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3515
4 | 516 | 3516 | 0806011023 | Region VIII (Eastern Visayas) | Samar | Matuguinao | San Roque | 12.146 | 124.8667 | R | 200 | 4.1 | 49 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.06 | 96.02 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.64 | 53.16 | F - Nearest node and line over 5 km | 96.06 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3516
4 | 517 | 3517 | 1906611013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Langhub | 16.7983 | 122.18 | R | 1366 | 6 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.34 | 31.67 | Tier 1B: High GIDA Priority | 30.74 | 30.74 | 75.59 | 53.16 | F - Nearest node and line over 5 km | 27.34 | 42.24 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3517
4 | 518 | 3518 | 0704603003 | Region VII (Central Visayas) | Negros Oriental | Bacong | Buntis | 9.2465 | 123.264 | R | 4151 | 3.8 | 1092 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 2.88 | Tier 2A: High Commercial ROI | 71.67 | 71.67 | 34.62 | 53.15 | D - Other node or line within 3 km | 2.89 | 2.78 | Line: FRONTHAUL-BACONG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3518
4 | 519 | 3519 | 1381100120 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 120 | 14.4391 | 120.8889 | U | 359 | 3.09 | 116 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 0.97 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.34 | 36.34 | 69.97 | 53.15 | D - Other node or line within 3 km | 1.24 | 0.91 | Line: NOVELETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3519
4 | 520 | 3520 | 0306910034 | Region III (Central Luzon) | Tarlac | Paniqui | Tablang | 15.6713 | 120.5681 | R | 3215 | 3.9 | 824 | 247 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.07 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 65.79 | 65.79 | 40.48 | 53.14 | D - Other node or line within 3 km | 2.07 | 0.58 | Line: 20,642 mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3520
4 | 521 | 3521 | 0105538027 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tuliao | 16.0123 | 120.3954 | U | 6475 | 3.6 | 1799 | 540 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 65.37 | 65.37 | 40.9 | 53.14 | B - Node 0.5-1 km | 0.86 | 0.09 | Line: SANTA BARBARA | Survey short node lateral; confirm port/fiber capacity, access and route. | 3521
4 | 522 | 3522 | 1208006002 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Kihan | 6.0897 | 125.3913 | R | 4025 | 3.9 | 1032 | 310 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.64 | 21.05 | Tier 2B: Moderate GIDA Inclusion | 57.51 | 57.51 | 48.77 | 53.14 | F - Nearest node and line over 5 km | 12.64 | 21.05 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3522
4 | 523 | 3523 | 0402120017 | Region IV-A (CALABARZON) | Cavite | Tanza | Barangay II | 14.3716 | 120.8384 | R | 1320 | 3.4 | 388 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 54.49 | 54.49 | 51.78 | 53.14 | D - Other node or line within 3 km | 1.68 | 0.88 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3523
4 | 524 | 3524 | 1900704008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Maluso | Muslim Area | 7.1271 | 121.9125 | R | 2187 | 5.1 | 429 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.96 | 28.59 | Tier 1B: High GIDA Priority | 40.3 | 40.3 | 65.97 | 53.14 | F - Nearest node and line over 5 km | 29.96 | 28.59 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3524
4 | 525 | 3525 | 0806004005 | Region VIII (Eastern Visayas) | Samar | Calbiga | Binanggaran | 11.6087 | 125.1227 | R | 159 | 4.1 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.08 | 45.76 | Tier 1B: High GIDA Priority | 36.82 | 36.82 | 69.47 | 53.14 | F - Nearest node and line over 5 km | 43.08 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3525
4 | 526 | 3526 | 1380610047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 732 | 13.8226 | 122.3324 | U | 1983 | 4.09 | 485 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.45 | 1.91 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 69.58 | 53.14 | D - Other node or line within 3 km | 10.45 | 1.9 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3526
4 | 527 | 3527 | 1908806016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Manindolo | 17.2552 | 122.2293 | R | 1527 | 4.7 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.48 | 34.35 | Tier 1B: High GIDA Priority | 33.14 | 33.14 | 73.14 | 53.14 | F - Nearest node and line over 5 km | 29.48 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3527
4 | 528 | 3528 | 0806022040 | Region VIII (Eastern Visayas) | Samar | Paranas | Santo Niño | 11.9319 | 125.0471 | R | 206 | 4.1 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 77.13 | 80.1 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 74.1 | 53.14 | F - Nearest node and line over 5 km | 77.13 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3528
4 | 529 | 3529 | 0403430007 | Region IV-A (CALABARZON) | Laguna | Victoria | San Benito | 14.1978 | 121.3176 | R | 3581 | 3.3 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 2.25 | Tier 2B: Moderate GIDA Inclusion | 67.34 | 67.34 | 38.92 | 53.13 | D - Other node or line within 3 km | 3.74 | 2.25 | Line: AE CLL001-NEW TO PLL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3529
4 | 530 | 3530 | 0401005051 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pallocan Kanluran | 13.7542 | 121.0662 | U | 7057 | 3.6 | 1960 | 588 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 64.76 | 64.76 | 41.51 | 53.13 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.44 | Line: BAUAN - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3530
4 | 531 | 3531 | 1908710017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Katidtuan | 17.254 | 122.2281 | R | 2978 | 3.8 | 784 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 45.11 | 45.11 | 61.15 | 53.13 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3531
4 | 532 | 3532 | 1380606212 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 605 | 13.3836 | 122.6693 | U | 2242 | 4.3 | 522 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.7 | 23.76 | Tier 1B: High GIDA Priority | 37.73 | 37.73 | 68.53 | 53.13 | F - Nearest node and line over 5 km | 6.7 | 23.76 | Node: SDQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3532
4 | 533 | 3533 | 0806011010 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Ligaya | 12.1567 | 124.8847 | R | 87 | 4.1 | 21 | 6 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 97.63 | 97.59 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.57 | 53.13 | F - Nearest node and line over 5 km | 97.63 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3533
4 | 534 | 3534 | 0702247016 | Region VII (Central Visayas) | Cebu | Sogod | Poblacion | 10.7491 | 124.0048 | R | 3637 | 3.8 | 957 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 0.21 | Tier 2A: High Commercial ROI | 76.44 | 76.44 | 29.79 | 53.12 | A - Node within 0.5 km | 0.32 | 0.08 | Line: BOGO - DANAO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3534
4 | 535 | 3535 | 0304909025 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Talabutab Norte | 15.5998 | 121.0781 | R | 4419 | 3.5 | 1263 | 379 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.95 | 0.11 | Tier 2A: High Commercial ROI | 72.48 | 72.48 | 33.76 | 53.12 | C - Line within 0.5 km; node over 1 km | 2.95 | 0.11 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3535
4 | 536 | 3536 | 1004307011 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Molugan | 8.5328 | 124.5622 | U | 13261 | 3.9 | 3400 | 1020 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.97 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 69.48 | 69.48 | 36.76 | 53.12 | C - Line within 0.5 km; node over 1 km | 1.97 | 0.3 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3536
4 | 537 | 3537 | 0702218006 | Region VII (Central Visayas) | Cebu | Compostela | Canamucan | 10.4674 | 124.0086 | U | 5088 | 3.8 | 1339 | 402 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.88 | Tier 2B: Moderate GIDA Inclusion | 65.51 | 65.51 | 40.72 | 53.12 | D - Other node or line within 3 km | 1.69 | 0.88 | Line: 9.3km FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3537
4 | 538 | 3538 | 0405607073 | Region IV-A (CALABARZON) | Quezon | Calauag | Santa Maria | 13.9572 | 122.2948 | U | 6195 | 3.8 | 1630 | 489 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 64.72 | 64.72 | 41.52 | 53.12 | B - Node 0.5-1 km | 0.83 | 0.16 | Line: CALAUAG TO RAGAY | Survey short node lateral; confirm port/fiber capacity, access and route. | 3538
4 | 539 | 3539 | 0403422005 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Sur | 14.234 | 121.3661 | U | 3816 | 3.3 | 1156 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 64.25 | 64.25 | 41.99 | 53.12 | A - Node within 0.5 km | 0.35 | 0.07 | Line: AE CLL001-NEW TO PLL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3539
4 | 540 | 3540 | 1380601052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 52 | 13.7114 | 122.7907 | U | 2249 | 3.46 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.06 | 9.32 | Tier 1B: High GIDA Priority | 36.92 | 36.92 | 69.32 | 53.12 | F - Nearest node and line over 5 km | 11.06 | 9.31 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3540
4 | 541 | 3541 | 1408101003 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Langnao | 18.1826 | 121.1142 | R | 234 | 4.2 | 56 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.46 | 22.49 | Tier 1B: High GIDA Priority | 31.58 | 31.58 | 74.66 | 53.12 | F - Nearest node and line over 5 km | 19.46 | 36.52 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3541
4 | 542 | 3542 | 0702216015 | Region VII (Central Visayas) | Cebu | Catmon | Panalipan | 10.6494 | 124.0239 | R | 4169 | 3.8 | 1097 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.08 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 73.14 | 73.14 | 33.09 | 53.11 | C - Line within 0.5 km; node over 1 km | 5.08 | 0.09 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3542
4 | 543 | 3543 | 1001321016 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Lumbo | 7.8823 | 125.0881 | U | 20396 | 3.8 | 5367 | 1610 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.72 | 1.58 | Tier 2A: High Commercial ROI | 71.77 | 71.77 | 34.46 | 53.11 | D - Other node or line within 3 km | 2.72 | 1.56 | Line: MALAYBALAY - KITAOTAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3543
4 | 544 | 3544 | 0307103016 | Region III (Central Luzon) | Zambales | Candelaria | Sinabacan | 15.6566 | 119.9351 | R | 4096 | 3.8 | 1078 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.68 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 66.6 | 66.6 | 39.63 | 53.11 | C - Line within 0.5 km; node over 1 km | 3.68 | 0.07 | Line: CANDELARIA MUNICIPALITY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3544
4 | 545 | 3545 | 1381100195 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 195 | 14.3485 | 120.8512 | U | 2512 | 3.91 | 643 | 193 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 3.3 | Tier 1B: High GIDA Priority | 44.54 | 44.54 | 61.67 | 53.11 | D - Other node or line within 3 km | 2.26 | 3.3 | Node: TZC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3545
4 | 546 | 3546 | 1003514002 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Balabacun | 8.0379 | 124.0695 | R | 1320 | 4.2 | 314 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.76 | 16.36 | Tier 1B: High GIDA Priority | 40.91 | 40.91 | 65.3 | 53.11 | F - Nearest node and line over 5 km | 22.76 | 16.32 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3546
4 | 547 | 3547 | 0504121008 | Region V (Bicol Region) | Masbate | Uson | Campana | 12.0759 | 123.8042 | R | 932 | 4.1 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.68 | 35.67 | Tier 1B: High GIDA Priority | 36.48 | 36.48 | 69.73 | 53.11 | F - Nearest node and line over 5 km | 18.68 | 37.3 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3547
4 | 548 | 3548 | 1001315008 | Region X (Northern Mindanao) | Bukidnon | Maramag | Dologon | 7.8351 | 125.0421 | U | 15472 | 3.8 | 4072 | 1222 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.76 | 0.71 | Tier 2A: High Commercial ROI | 73.44 | 73.44 | 32.77 | 53.1 | B - Node 0.5-1 km | 0.76 | 0.55 | Line: MALAYBALAY - KITAOTAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 3548
4 | 549 | 3549 | 0300804038 | Region III (Central Luzon) | Bataan | Dinalupihan | Santo Niño | 14.8765 | 120.4591 | R | 3633 | 3.6 | 1009 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.59 | Tier 2A: High Commercial ROI | 70.09 | 70.09 | 36.1 | 53.1 | C - Line within 0.5 km; node over 1 km | 1.06 | 0.46 | Line: 48 CORE (4X12) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3549
4 | 550 | 3550 | 0103302010 | Region I (Ilocos Region) | La Union | Aringay | Poblacion | 16.3958 | 120.3557 | R | 3517 | 3.7 | 951 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.86 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 66.03 | 66.03 | 40.17 | 53.1 | C - Line within 0.5 km; node over 1 km | 3.86 | 0.1 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3550
4 | 551 | 3551 | 0301418033 | Region III (Central Luzon) | Bulacan | Pulilan | Taal | 14.9091 | 120.8789 | U | 8270 | 3.5 | 2363 | 709 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.13 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 63.6 | 63.6 | 42.6 | 53.1 | C - Line within 0.5 km; node over 1 km | 3.13 | 0.21 | Line: Calumpit-Baliuag Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3551
4 | 552 | 3552 | 0403413015 | Region IV-A (CALABARZON) | Laguna | Lumban | Santo Niño | 14.2985 | 121.4615 | R | 1206 | 3.3 | 365 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 56.5 | 56.5 | 49.71 | 53.1 | A - Node within 0.5 km | 0.33 | 0.2 | Line: SNL001 TO SCL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3552
4 | 553 | 3553 | 1208007002 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Ampon | 6.3325 | 125.2968 | R | 2053 | 3.9 | 526 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.61 | 3.5 | Tier 2B: Moderate GIDA Inclusion | 51.59 | 51.59 | 54.61 | 53.1 | E - Nearest node or line 3-5 km | 5.61 | 3.5 | Line: DAVAO CITY - GENSAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3553
4 | 554 | 3554 | 0401029025 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 12 | 13.8753 | 120.9518 | R | 245 | 3.6 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 0.8 | Tier 1B: High GIDA Priority | 47.55 | 47.55 | 58.65 | 53.1 | D - Other node or line within 3 km | 1.62 | 0.8 | Line: LEMERY TO SAN JUAN CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3554
4 | 555 | 3555 | 0603040045 | Region VI (Western Visayas) | Iloilo | San Joaquin | Langca | 10.6483 | 122.08 | R | 384 | 3.8 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.03 | 7.7 | Tier 1B: High GIDA Priority | 34.48 | 34.48 | 71.72 | 53.1 | F - Nearest node and line over 5 km | 20.03 | 7.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3555
4 | 556 | 3556 | 1004309009 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Poblacion | 8.5952 | 124.4068 | R | 3192 | 3.9 | 818 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.27 | Tier 2A: High Commercial ROI | 73.32 | 73.32 | 32.86 | 53.09 | A - Node within 0.5 km | 0.31 | 0.13 | Line: CDO - ILIGAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3556
4 | 557 | 3557 | 1102403022 | Region XI (Davao Region) | Davao del Sur | City of Digos | San Miguel | 6.7353 | 125.3437 | U | 17939 | 3.4 | 5276 | 1583 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.3 | 1.22 | Tier 2A: High Commercial ROI | 72.44 | 72.44 | 33.74 | 53.09 | D - Other node or line within 3 km | 2.3 | 1.72 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3557
4 | 558 | 3558 | 0401004005 | Region IV-A (CALABARZON) | Batangas | Balete | Makina | 14.0201 | 121.1016 | R | 3732 | 3.6 | 1037 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 6.5 | Tier 2A: High Commercial ROI | 71.96 | 71.96 | 34.21 | 53.09 | B - Node 0.5-1 km | 0.55 | 6.48 | Node: BEB002 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 3558
4 | 559 | 3559 | 0201525011 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Simpatuyo | 18.2478 | 121.8957 | R | 2746 | 3.9 | 704 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 67.75 | 67.75 | 38.42 | 53.09 | C - Line within 0.5 km; node over 1 km | 1.63 | 0.06 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3559
4 | 560 | 3560 | 0301410026 | Region III (Central Luzon) | Bulacan | City of Malolos | Look 1st | 14.885 | 120.81 | U | 10046 | 3.5 | 2870 | 861 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.42 | 1.76 | Tier 2B: Moderate GIDA Inclusion | 64.82 | 64.82 | 41.36 | 53.09 | D - Other node or line within 3 km | 3.42 | 1.77 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3560
4 | 561 | 3561 | 0301411009 | Region III (Central Luzon) | Bulacan | Marilao | Poblacion I | 14.7538 | 120.9494 | U | 1483 | 3.5 | 424 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 49.53 | 49.53 | 56.66 | 53.09 | B - Node 0.5-1 km | 0.89 | 0.49 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 3561
4 | 562 | 3562 | 0402117014 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong IV | 14.4146 | 120.8713 | R | 3117 | 3.4 | 917 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.08 | 0.9 | Tier 2B: Moderate GIDA Inclusion | 67.87 | 67.87 | 38.29 | 53.08 | D - Other node or line within 3 km | 2.08 | 0.94 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3562
4 | 563 | 3563 | 0305409011 | Region III (Central Luzon) | Pampanga | Mabalacat City | Lakandula | 15.1758 | 120.5829 | U | 8899 | 4 | 2225 | 668 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 67.27 | 67.27 | 38.88 | 53.08 | B - Node 0.5-1 km | 0.56 | 0.49 | Line: 48 CORE (6X8) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3563
4 | 564 | 3564 | 0403405046 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Punta | 14.1771 | 121.1178 | U | 8025 | 3.3 | 2432 | 730 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 66.88 | 66.88 | 39.29 | 53.08 | B - Node 0.5-1 km | 0.99 | 0.17 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3564
4 | 565 | 3565 | 0305413013 | Region III (Central Luzon) | Pampanga | Mexico | Lagundi | 15.056 | 120.711 | U | 5092 | 4 | 1273 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.77 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 60.72 | 60.72 | 45.44 | 53.08 | C - Line within 0.5 km; node over 1 km | 2.77 | 0.2 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3565
4 | 566 | 3566 | 0401029009 | Region IV-A (CALABARZON) | Batangas | Taal | Caysasay | 13.8842 | 120.9217 | R | 690 | 3.6 | 192 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.07 | 1.32 | Tier 2B: Moderate GIDA Inclusion | 50.29 | 50.29 | 55.88 | 53.08 | D - Other node or line within 3 km | 1.07 | 1.32 | Node: TLB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3566
4 | 567 | 3567 | 1102506011 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Pundaguitan | 6.3768 | 126.1648 | R | 2544 | 3.6 | 707 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.17 | 56.1 | Tier 1B: High GIDA Priority | 44.35 | 44.35 | 61.81 | 53.08 | F - Nearest node and line over 5 km | 60.17 | 999999 | Node: LND001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3567
4 | 568 | 3568 | 0601902016 | Region VI (Western Visayas) | Capiz | Dao | Matagnop | 11.3806 | 122.7031 | R | 4158 | 3.8 | 1094 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 3.03 | Tier 2A: High Commercial ROI | 72.15 | 72.15 | 33.99 | 53.07 | D - Other node or line within 3 km | 2.52 | 3.02 | Node: DOZ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3568
4 | 569 | 3569 | 1004325010 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Poblacion | 8.9988 | 124.8815 | U | 5516 | 3.9 | 1414 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.2 | Tier 2A: High Commercial ROI | 72 | 72 | 34.13 | 53.07 | A - Node within 0.5 km | 0.12 | 0.13 | Node: TSM001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3569
4 | 570 | 3570 | 1102404020 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Paligue | 6.6623 | 125.3573 | R | 3353 | 3.4 | 986 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 68.11 | 68.11 | 38.04 | 53.07 | D - Other node or line within 3 km | 3.32 | 0.99 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3570
4 | 571 | 3571 | 0990101023 | Region IX (Zamboanga Peninsula) | City of Isabela (Not a Province) | City of Isabela | Lampinigan | 6.6873 | 121.8776 | R | 1811 | 4.4 | 412 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.92 | 32.92 | Tier 1B: High GIDA Priority | 36.91 | 36.91 | 69.22 | 53.07 | F - Nearest node and line over 5 km | 32.92 | 32.92 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3571
4 | 572 | 3572 | 1380602001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 287 | 11.8169 | 121.0795 | U | 3117 | 4.24 | 736 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.24 | 53.67 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 70.47 | 53.07 | F - Nearest node and line over 5 km | 55.24 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3572
4 | 573 | 3573 | 0103307032 | Region I (Ilocos Region) | La Union | Bauang | Pugo | 16.5274 | 120.3223 | R | 3328 | 3.7 | 899 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 0.81 | Tier 2B: Moderate GIDA Inclusion | 69.76 | 69.76 | 36.37 | 53.06 | B - Node 0.5-1 km | 0.95 | 0.81 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3573
4 | 574 | 3574 | 0300809026 | Region III (Central Luzon) | Bataan | Orani | Kabalutan | 14.8133 | 120.5328 | R | 3154 | 3.6 | 876 | 263 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.87 | Tier 2B: Moderate GIDA Inclusion | 68.49 | 68.49 | 37.64 | 53.06 | D - Other node or line within 3 km | 1.3 | 0.87 | Line: Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3574
4 | 575 | 3575 | 0300803023 | Region III (Central Luzon) | Bataan | City of Balanga | Tuyo | 14.6894 | 120.5106 | U | 12595 | 3.6 | 3499 | 1050 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.18 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 67.01 | 67.01 | 39.11 | 53.06 | D - Other node or line within 3 km | 3.18 | 0.74 | Line: Pipe Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3575
4 | 576 | 3576 | 0103303034 | Region I (Ilocos Region) | La Union | Bacnotan | Poblacion | 16.7226 | 120.3533 | U | 3632 | 3.7 | 982 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 63.5 | 63.5 | 42.63 | 53.06 | B - Node 0.5-1 km | 0.56 | 0.31 | Line: SAN FERNANDO - SUPIDEN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 3576
4 | 577 | 3577 | 1705209015 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Marfrancisco | 13.0342 | 121.4516 | U | 6154 | 3.9 | 1578 | 473 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.78 | 1.71 | Tier 2B: Moderate GIDA Inclusion | 62.89 | 62.89 | 43.22 | 53.06 | D - Other node or line within 3 km | 2.78 | 1.68 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3577
4 | 578 | 3578 | 0301404012 | Region III (Central Luzon) | Bulacan | Bocaue | Igulot | 14.8151 | 120.9321 | R | 1956 | 3.5 | 559 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.78 | 1.67 | Tier 2B: Moderate GIDA Inclusion | 57.7 | 57.7 | 48.42 | 53.06 | D - Other node or line within 3 km | 2.78 | 1.74 | Line: GOTACO TO HH 71 BULACAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3578
4 | 579 | 3579 | 0704612014 | Region VII (Central Visayas) | Negros Oriental | Jimalalud | Eli | 10.0153 | 123.1313 | R | 1779 | 3.8 | 468 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.84 | 8.37 | Tier 1B: High GIDA Priority | 46.31 | 46.31 | 59.81 | 53.06 | F - Nearest node and line over 5 km | 18.84 | 10.38 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3579
4 | 580 | 3580 | 1381100027 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 27 | 14.5053 | 120.9921 | U | 439 | 3.25 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.19 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 37.12 | 37.12 | 68.99 | 53.06 | B - Node 0.5-1 km | 0.82 | 0.19 | Line: Existing 144C via Y-Duct | Survey short node lateral; confirm port/fiber capacity, access and route. | 3580
4 | 581 | 3581 | 0806011019 | Region VIII (Eastern Visayas) | Samar | Matuguinao | San Isidro | 12.1806 | 124.9092 | R | 258 | 4.1 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 100.57 | 100.56 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.44 | 53.06 | F - Nearest node and line over 5 km | 100.57 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3581
4 | 582 | 3582 | 0304908006 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Mangino | 15.3112 | 120.9623 | U | 14084 | 3.5 | 4024 | 1207 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.82 | 0.74 | Tier 2A: High Commercial ROI | 70.45 | 70.45 | 35.66 | 53.05 | C - Line within 0.5 km; node over 1 km | 2.63 | 0.19 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3582
4 | 583 | 3583 | 0405810004 | Region IV-A (CALABARZON) | Rizal | Pililla | Hulo | 14.4924 | 121.3177 | U | 10763 | 3.6 | 2990 | 897 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.2 | 1.43 | Tier 2B: Moderate GIDA Inclusion | 65.27 | 65.27 | 40.82 | 53.05 | D - Other node or line within 3 km | 3.2 | 1.42 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3583
4 | 584 | 3584 | 1381000004 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Dionisio | 14.4942 | 120.989 | U | 69550 | 3.3 | 21090 | 6327 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 0.46 | 0.1 | Tier 1B: High GIDA Priority | 48.65 | 48.65 | 57.46 | 53.05 | A - Node within 0.5 km | 0.46 | 0.1 | Line: UG 288C via Y-Duct | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3584
4 | 585 | 3585 | 0403404018 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Dos | 14.2046 | 121.2969 | U | 1724 | 3.3 | 522 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.17 | 2.93 | Tier 1B: High GIDA Priority | 45.15 | 45.15 | 60.95 | 53.05 | D - Other node or line within 3 km | 3.17 | 2.93 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3585
4 | 586 | 3586 | 1403213020 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Lucog | 17.3991 | 121.2994 | R | 1575 | 4.3 | 366 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.26 | 0.63 | Tier 1B: High GIDA Priority | 42.88 | 42.88 | 63.22 | 53.05 | D - Other node or line within 3 km | 15.26 | 0.58 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3586
4 | 587 | 3587 | 0806013001 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Bangon | 11.5914 | 124.9871 | R | 1499 | 4.1 | 366 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.15 | 42.21 | Tier 1B: High GIDA Priority | 41.62 | 41.62 | 64.48 | 53.05 | F - Nearest node and line over 5 km | 39.15 | 42.2 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3587
4 | 588 | 3588 | 0600608015 | Region VI (Western Visayas) | Antique | Hamtic | Cantulan | 10.6752 | 122.0505 | R | 206 | 3.9 | 53 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.65 | 7.27 | Tier 1B: High GIDA Priority | 36.15 | 36.15 | 69.96 | 53.05 | F - Nearest node and line over 5 km | 15.65 | 7.27 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3588
4 | 589 | 3589 | 1381100115 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 115 | 14.4643 | 121.128 | U | 1279 | 3.17 | 403 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.44 | 6.25 | Tier 1B: High GIDA Priority | 34.68 | 34.68 | 71.42 | 53.05 | F - Nearest node and line over 5 km | 6.44 | 6.22 | Line: Aerial 24C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3589
4 | 590 | 3590 | 1381100084 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 84 | 14.4771 | 120.9178 | U | 810 | 2.65 | 306 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.26 | 3.1 | Tier 1B: High GIDA Priority | 34.44 | 34.44 | 71.67 | 53.05 | E - Nearest node or line 3-5 km | 3.26 | 3.1 | Line: PSG001 RELIANCE TO NCC001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3590
4 | 591 | 3591 | 0301415012 | Region III (Central Luzon) | Bulacan | Pandi | Mapulang Lupa | 14.8803 | 120.9651 | U | 31602 | 3.5 | 9029 | 2709 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.13 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 66.68 | 66.68 | 39.4 | 53.04 | C - Line within 0.5 km; node over 1 km | 1.13 | 0.05 | Line: PANDI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3591
4 | 592 | 3592 | 1908823004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Darampua | 17.255 | 122.2291 | R | 2646 | 4.7 | 563 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 39.34 | 39.34 | 66.74 | 53.04 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3592
4 | 593 | 3593 | 1380614072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 879 | 12.5827 | 121.5606 | U | 544 | 2.94 | 185 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.56 | 0.53 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.66 | 35.66 | 70.42 | 53.04 | D - Other node or line within 3 km | 2.56 | 2.58 | Node: RSM001 - TYPE 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3593
4 | 594 | 3594 | 1380601002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 2 | 13.8594 | 122.1903 | U | 1666 | 3.54 | 471 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.36 | 4.57 | Tier 1B: High GIDA Priority | 35.03 | 35.03 | 71.06 | 53.04 | E - Nearest node or line 3-5 km | 8.36 | 4.57 | Line: GCQ001 TO TKQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3594
4 | 595 | 3595 | 0304924001 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Buliran | 15.2706 | 120.8646 | R | 5048 | 3.5 | 1442 | 433 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.88 | Tier 2A: High Commercial ROI | 71.64 | 71.64 | 34.42 | 53.03 | B - Node 0.5-1 km | 0.94 | 0.88 | Line: SANTA ROSA TO ARAYAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 3595
4 | 596 | 3596 | 0304930053 | Region III (Central Luzon) | Nueva Ecija | Talavera | Sibul | 15.1684 | 121.0635 | R | 3531 | 3.5 | 1009 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 68.71 | 68.71 | 37.35 | 53.03 | D - Other node or line within 3 km | 1.87 | 9.3 | Node: SMB004 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3596
4 | 597 | 3597 | 0305415022 | Region III (Central Luzon) | Pampanga | Porac | Palat | 15.0424 | 120.5365 | R | 4696 | 4 | 1174 | 352 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.51 | 1.03 | Tier 2B: Moderate GIDA Inclusion | 68.27 | 68.27 | 37.79 | 53.03 | D - Other node or line within 3 km | 2.51 | 1 | Line: 48 CORE (4X12) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3597
4 | 598 | 3598 | 0304928028 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Isla | 15.4175 | 120.9273 | R | 2736 | 3.5 | 782 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.93 | Tier 2B: Moderate GIDA Inclusion | 66.71 | 66.71 | 39.34 | 53.03 | B - Node 0.5-1 km | 0.92 | 0.9 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3598
4 | 599 | 3599 | 0702234010 | Region VII (Central Visayas) | Cebu | City of Naga | Inoburan | 10.1906 | 123.7376 | U | 7587 | 3.8 | 1997 | 599 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.51 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 63.82 | 63.82 | 42.24 | 53.03 | C - Line within 0.5 km; node over 1 km | 4.51 | 0.28 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3599
4 | 600 | 3600 | 0102903029 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Tay-ac | 17.2405 | 120.5373 | R | 2644 | 3.8 | 696 | 209 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 62.65 | 62.65 | 43.4 | 53.03 | C - Line within 0.5 km; node over 1 km | 1.89 | 0.04 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3600
4 | 601 | 3601 | 0405623029 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 1 | 14.1264 | 121.5267 | R | 2486 | 3.8 | 654 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 59.15 | 59.15 | 46.91 | 53.03 | C - Line within 0.5 km; node over 1 km | 3.67 | 0.14 | Line: LILIW - LUCENA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3601
4 | 602 | 3602 | 0103314045 | Region I (Ilocos Region) | La Union | City of San Fernando | Parian | 16.6474 | 120.3691 | U | 3573 | 3.7 | 966 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.33 | 4.18 | Tier 2B: Moderate GIDA Inclusion | 54.66 | 54.66 | 51.39 | 53.03 | E - Nearest node or line 3-5 km | 4.33 | 4.15 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3602
4 | 603 | 3603 | 0403413010 | Region IV-A (CALABARZON) | Laguna | Lumban | Primera Parang | 14.2862 | 121.4627 | R | 1140 | 3.3 | 345 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.06 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 54.48 | 54.48 | 51.58 | 53.03 | D - Other node or line within 3 km | 1.06 | 0.51 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3603
4 | 604 | 3604 | 1204712004 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Balatican | 7.0899 | 124.6842 | R | 2019 | 3.8 | 531 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.65 | 13.75 | Tier 1B: High GIDA Priority | 43.13 | 43.13 | 62.93 | 53.03 | F - Nearest node and line over 5 km | 17.65 | 13.71 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3604
4 | 605 | 3605 | 1903638026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Malingon | 17.26 | 122.2469 | R | 1202 | 5.7 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.26 | 36.29 | Tier 1B: High GIDA Priority | 34.45 | 34.45 | 71.61 | 53.03 | F - Nearest node and line over 5 km | 31.26 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3605
4 | 606 | 3606 | 0603036011 | Region VI (Western Visayas) | Iloilo | Pavia | Jibao-an | 10.7517 | 122.5075 | U | 11658 | 3.8 | 3068 | 920 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.66 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 66.41 | 66.41 | 39.63 | 53.02 | C - Line within 0.5 km; node over 1 km | 4.66 | 0.07 | Line: 7,092 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3606
4 | 607 | 3607 | 0405627006 | Region IV-A (CALABARZON) | Quezon | Mauban | Cagbalete I | 14.2802 | 121.8319 | R | 3091 | 3.8 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.61 | 29.96 | Tier 2B: Moderate GIDA Inclusion | 50.43 | 50.43 | 55.61 | 53.02 | F - Nearest node and line over 5 km | 16.61 | 29.91 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3607
4 | 608 | 3608 | 0405647049 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Diego Zone I | 14.0277 | 121.5738 | R | 385 | 3.8 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.17 | 1.45 | Tier 1B: High GIDA Priority | 46.68 | 46.68 | 59.36 | 53.02 | D - Other node or line within 3 km | 2.17 | 1.45 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3608
4 | 609 | 3609 | 0806013007 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Canlobo | 11.5182 | 125.1119 | R | 388 | 4.1 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.2 | 35.79 | Tier 1B: High GIDA Priority | 37.13 | 37.13 | 68.92 | 53.02 | F - Nearest node and line over 5 km | 33.2 | 35.78 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3609
4 | 610 | 3610 | 0806004014 | Region VIII (Eastern Visayas) | Samar | Calbiga | Daligan | 11.6445 | 125.0938 | R | 182 | 4.1 | 44 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.11 | 48.91 | Tier 1B: High GIDA Priority | 36.78 | 36.78 | 69.26 | 53.02 | F - Nearest node and line over 5 km | 46.11 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3610
4 | 611 | 3611 | 0806011008 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Del Rosario | 12.1447 | 124.8851 | R | 156 | 4.1 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.34 | 96.3 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.36 | 53.02 | F - Nearest node and line over 5 km | 96.34 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3611
4 | 612 | 3612 | 0806011020 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Santa Cruz | 12.1449 | 124.8851 | R | 187 | 4.1 | 46 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.36 | 96.31 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.35 | 53.02 | F - Nearest node and line over 5 km | 96.36 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3612
4 | 613 | 3613 | 0806011006 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Carolina | 12.1526 | 124.8721 | R | 153 | 4.1 | 37 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.89 | 96.85 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.36 | 53.02 | F - Nearest node and line over 5 km | 96.89 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3613
4 | 614 | 3614 | 0806011014 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Mahayag | 12.1608 | 124.8728 | R | 161 | 4.1 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 97.8 | 97.76 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.36 | 53.02 | F - Nearest node and line over 5 km | 97.8 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3614
4 | 615 | 3615 | 1004317008 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Consuelo | 8.9155 | 125.1874 | R | 4051 | 3.9 | 1039 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.05 | Tier 2A: High Commercial ROI | 78.08 | 78.08 | 27.94 | 53.01 | A - Node within 0.5 km | 0.3 | 0.05 | Line: CDO - BUENAVISTA via GINGOOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3615
4 | 616 | 3616 | 0305403013 | Region III (Central Luzon) | Pampanga | Arayat | Mangga-Cacutud | 15.1471 | 120.7628 | U | 11667 | 4 | 2917 | 875 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 68.35 | 68.35 | 37.66 | 53.01 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.02 | Line: EXISTING | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3616
4 | 617 | 3617 | 0301409025 | Region III (Central Luzon) | Bulacan | Hagonoy | Tampok | 14.8493 | 120.7349 | R | 3147 | 3.5 | 899 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 1.65 | Tier 2B: Moderate GIDA Inclusion | 67.81 | 67.81 | 38.2 | 53.01 | D - Other node or line within 3 km | 2.1 | 6.83 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3617
4 | 618 | 3618 | 1705313008 | MIMAROPA Region | Palawan | Linapacan | New Culaylayan | 11.4226 | 119.7584 | R | 1697 | 3.9 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.59 | 72.09 | Tier 1B: High GIDA Priority | 43.07 | 43.07 | 62.95 | 53.01 | F - Nearest node and line over 5 km | 25.59 | 999999 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3618
4 | 619 | 3619 | 0702214001 | Region VII (Central Visayas) | Cebu | City of Carcar | Bolinawan | 10.0896 | 123.6331 | U | 13804 | 3.8 | 3633 | 1090 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.36 | 0.39 | Tier 2A: High Commercial ROI | 71.87 | 71.87 | 34.12 | 53 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.19 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3619
4 | 620 | 3620 | 1102414018 | Region XI (Davao Region) | Davao del Sur | Sulop | Poblacion | 6.5983 | 125.3439 | U | 8316 | 3.4 | 2446 | 734 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.07 | 0.11 | Tier 2A: High Commercial ROI | 70.45 | 70.45 | 35.54 | 53 | A - Node within 0.5 km | 0.07 | 0.11 | Node: SUD001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3620
4 | 621 | 3621 | 0300807001 | Region III (Central Luzon) | Bataan | Mariveles | Alas-asin | 14.4612 | 120.533 | U | 19710 | 3.6 | 5475 | 1642 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.27 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 67.11 | 67.11 | 38.89 | 53 | C - Line within 0.5 km; node over 1 km | 4.27 | 0.07 | Line: PIPE ORION-MARIVELES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3621
4 | 622 | 3622 | 0307112006 | Region III (Central Luzon) | Zambales | San Narciso | La Paz | 15.0136 | 120.0684 | R | 4532 | 3.8 | 1193 | 358 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.13 | 1.19 | Tier 2B: Moderate GIDA Inclusion | 70.26 | 70.26 | 35.72 | 52.99 | D - Other node or line within 3 km | 5.13 | 1.19 | Line: BACKBONE ROUTE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3622
4 | 623 | 3623 | 0305410015 | Region III (Central Luzon) | Pampanga | Macabebe | San Roque | 14.908 | 120.7159 | R | 4379 | 4 | 1095 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 1.96 | Tier 2B: Moderate GIDA Inclusion | 68.63 | 68.63 | 37.36 | 52.99 | D - Other node or line within 3 km | 2.09 | 5.38 | Node: MSP001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3623
4 | 624 | 3624 | 0806011022 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Inubod | 12.1448 | 124.8851 | R | 260 | 4.1 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.35 | 96.3 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.29 | 52.99 | F - Nearest node and line over 5 km | 96.35 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3624
4 | 625 | 3625 | 1380601050 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 50 | 12.5701 | 120.3417 | U | 3806 | 4.94 | 771 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 62.22 | 80.93 | Tier 1B: High GIDA Priority | 36.54 | 36.54 | 69.44 | 52.99 | F - Nearest node and line over 5 km | 62.22 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3625
4 | 626 | 3626 | 0304927013 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | San Roque | 15.3267 | 120.9254 | R | 3588 | 3.5 | 1025 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.22 | 1.3 | Tier 2B: Moderate GIDA Inclusion | 68.22 | 68.22 | 37.74 | 52.98 | D - Other node or line within 3 km | 2.54 | 1.3 | Line: SANTA ROSA TO ARAYAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3626
4 | 627 | 3627 | 0402108028 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Tapia | 14.3644 | 120.8794 | R | 5173 | 3.4 | 1521 | 456 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 3.27 | Tier 2B: Moderate GIDA Inclusion | 65.32 | 65.32 | 40.65 | 52.98 | D - Other node or line within 3 km | 2.73 | 3.26 | Node: TZC002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3627
4 | 628 | 3628 | 0401005107 | Region IV-A (CALABARZON) | Batangas | Batangas City | Tabangao Ambulong | 13.7184 | 121.0742 | U | 6217 | 3.6 | 1727 | 518 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 4.44 | Tier 2B: Moderate GIDA Inclusion | 57.34 | 57.34 | 48.63 | 52.98 | E - Nearest node or line 3-5 km | 3.71 | 4.42 | Node: BCY004 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3628
4 | 629 | 3629 | 1380601051 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 51 | 12.769 | 123.0714 | U | 2614 | 3.29 | 795 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.01 | 48.45 | Tier 1B: High GIDA Priority | 37.15 | 37.15 | 68.81 | 52.98 | F - Nearest node and line over 5 km | 41.01 | 999999 | Node: LOA004-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3629
4 | 630 | 3630 | 0804809012 | Region VIII (Eastern Visayas) | Northern Samar | Lapinig | Palanas | 12.2795 | 125.3063 | R | 267 | 4.3 | 62 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 120.27 | 122.98 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.28 | 52.98 | F - Nearest node and line over 5 km | 120.27 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3630
4 | 631 | 3631 | 0701233001 | Region VII (Central Visayas) | Bohol | Panglao | Bil-isan | 9.595 | 123.7626 | R | 4041 | 4 | 1010 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 10.83 | Tier 2A: High Commercial ROI | 72.55 | 72.55 | 33.39 | 52.97 | D - Other node or line within 3 km | 1.11 | 11.43 | Node: POB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3631
4 | 632 | 3632 | 0401029044 | Region IV-A (CALABARZON) | Batangas | Taal | Seiran | 13.8866 | 120.9216 | R | 3104 | 3.6 | 862 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 1.09 | Tier 2B: Moderate GIDA Inclusion | 68.26 | 68.26 | 37.69 | 52.97 | D - Other node or line within 3 km | 1.23 | 1.09 | Line: LEMERY TO SAN JUAN CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3632
4 | 633 | 3633 | 0300808001 | Region III (Central Luzon) | Bataan | Morong | Binaritan | 14.6824 | 120.268 | U | 7440 | 3.6 | 2067 | 620 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 67.39 | 67.39 | 38.55 | 52.97 | A - Node within 0.5 km | 0.28 | 0.17 | Line: Subic- Morong AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3633
4 | 634 | 3634 | 0301406013 | Region III (Central Luzon) | Bulacan | Bustos | Tanawan | 14.9327 | 120.9208 | U | 2855 | 3.5 | 816 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 58.82 | 58.82 | 47.11 | 52.97 | D - Other node or line within 3 km | 1.62 | 0.71 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3634
4 | 635 | 3635 | 0301410041 | Region III (Central Luzon) | Bulacan | City of Malolos | San Agustin | 14.848 | 120.8095 | U | 2033 | 3.5 | 581 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.78 | Tier 2B: Moderate GIDA Inclusion | 53.71 | 53.71 | 52.22 | 52.97 | B - Node 0.5-1 km | 0.91 | 0.86 | Line: 24 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 3635
4 | 636 | 3636 | 1381300025 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Culiat | 14.6665 | 121.0574 | U | 69377 | 3.43 | 20232 | 6070 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 1.04 | 0.12 | Tier 1B: High GIDA Priority | 48.56 | 48.56 | 57.39 | 52.97 | C - Line within 0.5 km; node over 1 km | 1.04 | 0.12 | Line: UG 144C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3636
4 | 637 | 3637 | 1608501002 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Catadman | 9.9898 | 125.5353 | R | 879 | 3.8 | 231 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.87 | 22.87 | Tier 1B: High GIDA Priority | 38.87 | 38.87 | 67.07 | 52.97 | F - Nearest node and line over 5 km | 22.87 | 22.75 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3637
4 | 638 | 3638 | 0401009007 | Region IV-A (CALABARZON) | Batangas | Cuenca | Dita | 13.917 | 121.0731 | R | 4793 | 3.6 | 1331 | 399 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.3 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 72.05 | 72.05 | 33.86 | 52.96 | C - Line within 0.5 km; node over 1 km | 3.3 | 0.04 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3638
4 | 639 | 3639 | 0301407015 | Region III (Central Luzon) | Bulacan | Calumpit | Longos | 14.8757 | 120.7859 | R | 4458 | 3.5 | 1274 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.92 | 0.79 | Tier 2B: Moderate GIDA Inclusion | 66.96 | 66.96 | 38.97 | 52.96 | D - Other node or line within 3 km | 3.92 | 0.79 | Line: CALUMPIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3639
4 | 640 | 3640 | 0403426005 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Duhat | 14.2467 | 121.3793 | U | 8104 | 3.3 | 2456 | 737 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.53 | 65.53 | 40.39 | 52.96 | C - Line within 0.5 km; node over 1 km | 1.81 | 0.15 | Line: UG SCL001 TO PLL001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3640
4 | 641 | 3641 | 0501706014 | Region V (Bicol Region) | Camarines Sur | Bula | Lanipga | 13.5303 | 123.3413 | R | 1681 | 4.2 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.73 | 1.43 | Tier 2B: Moderate GIDA Inclusion | 53.34 | 53.34 | 52.59 | 52.96 | D - Other node or line within 3 km | 4.73 | 1.43 | Line: HH-001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3641
4 | 642 | 3642 | 0201510023 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Tagum | 18.2905 | 121.6839 | R | 233 | 3.9 | 60 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 3.49 | Tier 1B: High GIDA Priority | 46.44 | 46.44 | 59.48 | 52.96 | E - Nearest node or line 3-5 km | 3.35 | 3.26 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3642
4 | 643 | 3643 | 1906613007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Bud Bunga | 17.2555 | 122.2295 | R | 2238 | 6 | 373 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 34.36 | 34.36 | 71.56 | 52.96 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3643
4 | 644 | 3644 | 0105546034 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | San Vicente | 15.9803 | 120.5701 | U | 9856 | 3.6 | 2738 | 821 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.31 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 65.8 | 65.8 | 40.11 | 52.95 | C - Line within 0.5 km; node over 1 km | 2.31 | 0.15 | Line: BINALONAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3644
4 | 645 | 3645 | 1003514019 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Matampay | 8.0429 | 124.0936 | R | 1649 | 4.2 | 393 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.23 | 15.76 | Tier 1B: High GIDA Priority | 43.46 | 43.46 | 62.44 | 52.95 | F - Nearest node and line over 5 km | 20.23 | 15.74 | Line: 216f feeder iligan completed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3645
4 | 646 | 3646 | 1400120001 | Cordillera Administrative Region (CAR) | Abra | Sallapadan | Bazar | 17.4656 | 120.8127 | R | 506 | 3.8 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.92 | 23.81 | Tier 1B: High GIDA Priority | 34.86 | 34.86 | 71.04 | 52.95 | F - Nearest node and line over 5 km | 24.92 | 23.81 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3646
4 | 647 | 3647 | 0806022011 | Region VIII (Eastern Visayas) | Samar | Paranas | Casandig I | 11.831 | 125.0972 | R | 684 | 4.1 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.57 | 69.44 | Tier 1B: High GIDA Priority | 32.43 | 32.43 | 73.47 | 52.95 | F - Nearest node and line over 5 km | 66.57 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3647
4 | 648 | 3648 | 0604528011 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Efigenio Lizares | 10.7454 | 122.998 | R | 4695 | 3.7 | 1269 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.36 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 70.57 | 70.57 | 35.3 | 52.94 | C - Line within 0.5 km; node over 1 km | 3.36 | 0.27 | Line: TALISAY - BACOLOD (REDUNDANCY) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3648
4 | 649 | 3649 | 0403415007 | Region IV-A (CALABARZON) | Laguna | Magdalena | Buenavista | 14.2246 | 121.4288 | R | 2699 | 3.3 | 818 | 245 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.9 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 68.97 | 68.97 | 36.9 | 52.94 | C - Line within 0.5 km; node over 1 km | 2.9 | 0.06 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3649
4 | 650 | 3650 | 0301415016 | Region III (Central Luzon) | Bulacan | Pandi | Poblacion | 14.8664 | 120.9562 | U | 9072 | 3.5 | 2592 | 778 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 37.01 | 52.94 | A - Node within 0.5 km | 0.33 | 0.08 | Line: 48 CORE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3650
4 | 651 | 3651 | 0103313030 | Region I (Ilocos Region) | La Union | Rosario | Tabtabungao | 16.2244 | 120.4666 | R | 3264 | 3.7 | 882 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 67.89 | 67.89 | 38 | 52.94 | C - Line within 0.5 km; node over 1 km | 1.76 | 0.17 | Line: RSU001 TO AGU001 SECONDARY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3651
4 | 652 | 3652 | 0305415017 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Libutad | 15.1075 | 120.5624 | U | 5916 | 4 | 1479 | 444 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 63.28 | 63.28 | 42.59 | 52.94 | C - Line within 0.5 km; node over 1 km | 1.48 | 0.06 | Line: 24 CORE (3X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3652
4 | 653 | 3653 | 1705204015 | MIMAROPA Region | Oriental Mindoro | Bulalacao | San Juan | 12.3717 | 121.387 | R | 3776 | 3.9 | 968 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.61 | 2.3 | Tier 2B: Moderate GIDA Inclusion | 61.95 | 61.95 | 43.93 | 52.94 | D - Other node or line within 3 km | 6.61 | 2.3 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3653
4 | 654 | 3654 | 0103306009 | Region I (Ilocos Region) | La Union | Bangar | Consuegra | 16.8793 | 120.4287 | R | 1342 | 3.7 | 363 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 54.14 | 54.14 | 51.75 | 52.94 | D - Other node or line within 3 km | 1.6 | 0.8 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3654
4 | 655 | 3655 | 0405647055 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Isidro Zone III | 13.9776 | 121.6204 | R | 1042 | 3.8 | 274 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.86 | 1.1 | Tier 1B: High GIDA Priority | 48.6 | 48.6 | 57.28 | 52.94 | D - Other node or line within 3 km | 3.86 | 1.1 | Line: AE LCQ001 TO TYQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3655
4 | 656 | 3656 | 0907311006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Bualan | 7.7131 | 123.1397 | R | 1007 | 3.9 | 258 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.51 | 5.03 | Tier 1B: High GIDA Priority | 45.38 | 45.38 | 60.5 | 52.94 | F - Nearest node and line over 5 km | 9.51 | 5.03 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3656
4 | 657 | 3657 | 1380601250 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 249 | 13.6103 | 121.1451 | U | 1750 | 4.16 | 421 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.76 | 18.54 | Tier 1B: High GIDA Priority | 35.41 | 35.41 | 70.47 | 52.94 | F - Nearest node and line over 5 km | 5.76 | 18.54 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3657
4 | 658 | 3658 | 1380611031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 817 | 13.5866 | 121.0489 | U | 1395 | 3.24 | 430 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.48 | 13.92 | Tier 1B: High GIDA Priority | 35.36 | 35.36 | 70.52 | 52.94 | F - Nearest node and line over 5 km | 6.48 | 13.91 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3658
4 | 659 | 3659 | 1906614017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kanmangon | 17.2556 | 122.2297 | R | 1204 | 6 | 201 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 34.32 | 34.32 | 71.55 | 52.94 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3659
4 | 660 | 3660 | 0907216002 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Basak | 7.2878 | 122.0392 | R | 159 | 3.6 | 44 | 13 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.99 | 22.74 | Tier 1B: High GIDA Priority | 30.37 | 30.37 | 75.5 | 52.94 | F - Nearest node and line over 5 km | 24.99 | 22.72 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3660
4 | 661 | 3661 | 0403410029 | Region IV-A (CALABARZON) | Laguna | Liliw | Mojon | 14.2099 | 121.3986 | R | 4875 | 3.3 | 1477 | 443 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.7 | 3.16 | Tier 2B: Moderate GIDA Inclusion | 68.58 | 68.58 | 37.29 | 52.93 | E - Nearest node or line 3-5 km | 3.7 | 3.14 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3661
4 | 662 | 3662 | 0300812012 | Region III (Central Luzon) | Bataan | Samal | Tabing Ilog | 14.7554 | 120.5134 | R | 2391 | 3.6 | 664 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.74 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 62.42 | 62.42 | 43.43 | 52.93 | D - Other node or line within 3 km | 5.74 | 1.09 | Line: Pipe Dinalupian to Orion | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3662
4 | 663 | 3663 | 0102903003 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Balaleng | 17.5867 | 120.385 | U | 3074 | 3.8 | 809 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.79 | Tier 2B: Moderate GIDA Inclusion | 59.82 | 59.82 | 46.03 | 52.93 | B - Node 0.5-1 km | 0.96 | 0.39 | Line: SEGMENT 3 (VIGAN - BATAC) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3663
4 | 664 | 3664 | 1403215008 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Bugnay | 17.1965 | 121.0905 | R | 1193 | 4.3 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.89 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 52.34 | 52.34 | 53.52 | 52.93 | D - Other node or line within 3 km | 5.89 | 0.54 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3664
4 | 665 | 3665 | 1003502026 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Sangcad | 8.1329 | 124.2419 | R | 1848 | 4.2 | 440 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.61 | 2.89 | Tier 1B: High GIDA Priority | 45.29 | 45.29 | 60.56 | 52.93 | D - Other node or line within 3 km | 10.61 | 2.88 | Line: 216f feeder iligan completed | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3665
4 | 666 | 3666 | 1906614003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Banting | 17.2557 | 122.2297 | R | 1200 | 6 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 34.32 | 34.32 | 71.54 | 52.93 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3666
4 | 667 | 3667 | 0301423018 | Region III (Central Luzon) | Bulacan | Santa Maria | San Gabriel | 14.8069 | 120.9585 | U | 10066 | 3.5 | 2876 | 863 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 69.78 | 69.78 | 36.05 | 52.92 | A - Node within 0.5 km | 0.31 | 0.42 | Node: SMR006 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3667
4 | 668 | 3668 | 0601916017 | Region VI (Western Visayas) | Capiz | Sigma | Parian | 11.4764 | 122.6956 | R | 3447 | 3.8 | 907 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.96 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 69.04 | 69.04 | 36.8 | 52.92 | C - Line within 0.5 km; node over 1 km | 4.96 | 0.17 | Line: ROXAS - ILOILO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3668
4 | 669 | 3669 | 0601915009 | Region VI (Western Visayas) | Capiz | Sapi-An | Maninang | 11.4782 | 122.5881 | R | 3032 | 3.8 | 798 | 239 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 68.92 | 68.92 | 36.92 | 52.92 | D - Other node or line within 3 km | 2.59 | 0.7 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3669
4 | 670 | 3670 | 0403423005 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 2 | 14.113 | 121.3947 | R | 2020 | 3.6 | 561 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 66.22 | 66.22 | 39.61 | 52.92 | A - Node within 0.5 km | 0.35 | 0.35 | Line: SAN PABLO - LUCBAN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3670
4 | 671 | 3671 | 0304907011 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Malinao | 15.483 | 121.3325 | R | 2759 | 3.5 | 788 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 23.21 | Tier 2B: Moderate GIDA Inclusion | 64.96 | 64.96 | 40.85 | 52.91 | A - Node within 0.5 km | 0.1 | 23.2 | Node: GBN001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3671
4 | 672 | 3672 | 0401011022 | Region IV-A (CALABARZON) | Batangas | Laurel | San Gregorio | 14.0407 | 120.864 | R | 3907 | 3.6 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.37 | 2.78 | Tier 2B: Moderate GIDA Inclusion | 64.47 | 64.47 | 41.36 | 52.91 | D - Other node or line within 3 km | 2.37 | 2.77 | Node: LYB002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3672
4 | 673 | 3673 | 0105503019 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Palamis | 16.15 | 119.976 | U | 4745 | 3.6 | 1318 | 395 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.92 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 42.02 | 52.91 | B - Node 0.5-1 km | 0.92 | 0.2 | Line: ALAMINOS | Survey short node lateral; confirm port/fiber capacity, access and route. | 3673
4 | 674 | 3674 | 0301401019 | Region III (Central Luzon) | Bulacan | Angat | Taboc | 14.9376 | 120.9868 | R | 4133 | 3.5 | 1181 | 354 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.6 | 5.33 | Tier 2B: Moderate GIDA Inclusion | 63.49 | 63.49 | 42.33 | 52.91 | E - Nearest node or line 3-5 km | 3.6 | 5.32 | Node: SRB003 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3674
4 | 675 | 3675 | 0403405051 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Saimsim | 14.167 | 121.1461 | U | 6759 | 3.3 | 2048 | 614 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.37 | 0.91 | Tier 2B: Moderate GIDA Inclusion | 62.18 | 62.18 | 43.64 | 52.91 | D - Other node or line within 3 km | 3.37 | 0.91 | Line: AE LBL001-STB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3675
4 | 676 | 3676 | 1900703027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Canibungan | 7.5687 | 121.8183 | R | 2486 | 5.1 | 487 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.91 | 56.22 | Tier 1B: High GIDA Priority | 36.64 | 36.64 | 69.18 | 52.91 | F - Nearest node and line over 5 km | 60.91 | 999999 | Node: ZCZ002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3676
4 | 677 | 3677 | 0907313011 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Luanan | 7.7181 | 123.15 | R | 522 | 3.9 | 134 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.54 | 4.48 | Tier 1B: High GIDA Priority | 36.63 | 36.63 | 69.18 | 52.91 | E - Nearest node or line 3-5 km | 10.54 | 4.48 | Line: PAGADIAN - BUUG | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3677
4 | 678 | 3678 | 1380601053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 53 | 13.5901 | 122.9179 | U | 3218 | 4.73 | 680 | 204 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.3 | 13.91 | Tier 1B: High GIDA Priority | 35.99 | 35.99 | 69.83 | 52.91 | F - Nearest node and line over 5 km | 13.3 | 14.3 | Node: LBC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3678
4 | 679 | 3679 | 0205006010 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Poblacion | 16.6604 | 121.3652 | R | 3966 | 3.8 | 1044 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.09 | Tier 2A: High Commercial ROI | 76.06 | 76.06 | 29.74 | 52.9 | A - Node within 0.5 km | 0.38 | 0.07 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3679
4 | 680 | 3680 | 0105510021 | Region I (Ilocos Region) | Pangasinan | Bautista | Baluyot | 15.8011 | 120.4637 | R | 3735 | 3.6 | 1038 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.93 | 0.69 | Tier 2A: High Commercial ROI | 73.19 | 73.19 | 32.61 | 52.9 | D - Other node or line within 3 km | 1.93 | 0.53 | Line: AERIAL 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3680
4 | 681 | 3681 | 0405610046 | Region IV-A (CALABARZON) | Quezon | Catanauan | Barangay 10 | 13.6613 | 122.2862 | R | 3707 | 3.8 | 976 | 293 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.03 | 4.84 | Tier 2B: Moderate GIDA Inclusion | 62.23 | 62.23 | 43.58 | 52.9 | E - Nearest node or line 3-5 km | 4.03 | 4.84 | Node: CTQ004 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3681
4 | 682 | 3682 | 0402108006 | Region IV-A (CALABARZON) | Cavite | City of General Trias | San Gabriel Pob. | 14.3217 | 120.8972 | R | 1677 | 3.4 | 493 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.36 | 3.33 | Tier 2B: Moderate GIDA Inclusion | 51.62 | 51.62 | 54.17 | 52.9 | E - Nearest node or line 3-5 km | 3.36 | 3.52 | Node: TRC002 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3682
4 | 683 | 3683 | 0401019007 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 2 | 14.0856 | 120.6807 | U | 1481 | 3.6 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.29 | 1.97 | Tier 1B: High GIDA Priority | 43.71 | 43.71 | 62.09 | 52.9 | D - Other node or line within 3 km | 5.29 | 1.97 | Line: NCC001 TO NSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3683
4 | 684 | 3684 | 0401005064 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 18 | 13.7083 | 121.1069 | U | 338 | 3.6 | 94 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.4 | 7.17 | Tier 1B: High GIDA Priority | 34.11 | 34.11 | 71.7 | 52.9 | E - Nearest node or line 3-5 km | 3.4 | 7.17 | Node: BCY007-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3684
4 | 685 | 3685 | 1380601111 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 111 | 12.4943 | 120.52 | U | 2676 | 4.59 | 583 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.25 | 60.08 | Tier 1B: High GIDA Priority | 31.65 | 31.65 | 74.15 | 52.9 | F - Nearest node and line over 5 km | 61.25 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3685
4 | 686 | 3686 | 0304928036 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Tagpos | 15.436 | 121.0117 | R | 3783 | 3.5 | 1081 | 324 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.89 | Tier 2A: High Commercial ROI | 70.73 | 70.73 | 35.05 | 52.89 | D - Other node or line within 3 km | 7.43 | 0.86 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3686
4 | 687 | 3687 | 0205703003 | Region II (Cagayan Valley) | Quirino | Diffun | Aurora West | 16.5874 | 121.5023 | R | 2574 | 3.9 | 660 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 7.08 | Tier 2B: Moderate GIDA Inclusion | 61.31 | 61.31 | 44.47 | 52.89 | A - Node within 0.5 km | 0.21 | 7.08 | Node: DFQ001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3687
4 | 688 | 3688 | 1908701001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Barira | 17.2541 | 122.2281 | U | 14412 | 4.3 | 3352 | 1006 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 48.74 | 48.74 | 57.04 | 52.89 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3688
4 | 689 | 3689 | 1903626046 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tamparan | Salongabanding | 13.482 | 123.0435 | R | 854 | 5.7 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.34 | 2.45 | Tier 1B: High GIDA Priority | 47.02 | 47.02 | 58.75 | 52.89 | D - Other node or line within 3 km | 2.34 | 2.33 | Line: PASACAO CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3689
4 | 690 | 3690 | 1380601045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 45 | 13.989 | 122.1882 | U | 2312 | 4.9 | 472 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.23 | 8.37 | Tier 1B: High GIDA Priority | 32.14 | 32.14 | 73.63 | 52.89 | F - Nearest node and line over 5 km | 11.23 | 8.32 | Line: GCQ001 TO TKQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3690
4 | 691 | 3691 | 0103311010 | Region I (Ilocos Region) | La Union | Naguilian | Baraoas Sur | 16.545 | 120.3896 | R | 3554 | 3.7 | 961 | 288 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 1.61 | Tier 2B: Moderate GIDA Inclusion | 68.21 | 68.21 | 37.56 | 52.88 | D - Other node or line within 3 km | 2.1 | 4.41 | Node: NGU001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3691
4 | 692 | 3692 | 1380800006 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Putatan | 14.4015 | 121.0442 | U | 102146 | 4.11 | 24859 | 7458 | Band n50 (1.5 GHz, 100 MHz TDD) | 8 | 1 | 0.56 | 0.31 | Tier 1B: High GIDA Priority | 48.14 | 48.14 | 57.63 | 52.88 | B - Node 0.5-1 km | 0.56 | 0.31 | Line: RELIANCE PSG001 TO BÑL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3692
4 | 693 | 3693 | 0300809006 | Region III (Central Luzon) | Bataan | Orani | Centro II | 14.8011 | 120.5129 | R | 453 | 3.6 | 126 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.53 | 0.39 | Tier 1B: High GIDA Priority | 46.44 | 46.44 | 59.32 | 52.88 | C - Line within 0.5 km; node over 1 km | 2.53 | 0.38 | Line: ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3693
4 | 694 | 3694 | 0405632003 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Kilogan | 14.8178 | 122.1826 | R | 1112 | 3.8 | 293 | 88 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.01 | 72.78 | Tier 1B: High GIDA Priority | 37.26 | 37.26 | 68.5 | 52.88 | F - Nearest node and line over 5 km | 56.01 | 999999 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3694
4 | 695 | 3695 | 0806016030 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Panaruan | 12.0634 | 124.6942 | R | 120 | 4.1 | 29 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.91 | 84.71 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 69.08 | 52.88 | F - Nearest node and line over 5 km | 84.91 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3695
4 | 696 | 3696 | 1380601211 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 210 | 11.6307 | 121.2433 | U | 3106 | 4.37 | 710 | 213 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 76.1 | 72.3 | Tier 1B: High GIDA Priority | 34.96 | 34.96 | 70.8 | 52.88 | F - Nearest node and line over 5 km | 76.1 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3696
4 | 697 | 3697 | 0103309002 | Region I (Ilocos Region) | La Union | Caba | Gana | 16.4288 | 120.3547 | R | 2255 | 3.7 | 609 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 66.66 | 66.66 | 39.09 | 52.87 | B - Node 0.5-1 km | 0.84 | 0.23 | Line: AGOO - SAN FERNANDO AERIAL_SEGMENT 0 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3697
4 | 698 | 3698 | 0102910005 | Region I (Ilocos Region) | Ilocos Sur | Gregorio del Pilar | Matue-Butarag | 17.1515 | 120.5975 | R | 700 | 3.8 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.36 | 5.32 | Tier 1B: High GIDA Priority | 45.71 | 45.71 | 60.03 | 52.87 | F - Nearest node and line over 5 km | 6.36 | 5.26 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3698
4 | 699 | 3699 | 1907010003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tonggusong Banaran | 17.2558 | 122.2299 | U | 6606 | 5.8 | 1139 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 42.19 | 42.19 | 63.56 | 52.87 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3699
4 | 700 | 3700 | 1408104018 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Musimut | 17.9854 | 121.0778 | R | 857 | 4.2 | 204 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.56 | 15.89 | Tier 1B: High GIDA Priority | 37.54 | 37.54 | 68.21 | 52.87 | F - Nearest node and line over 5 km | 11.56 | 33.33 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3700
4 | 701 | 3701 | 0201529010 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 8 | 17.6141 | 121.7438 | U | 185 | 3.9 | 47 | 14 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.15 | 0.43 | Tier 1B: High GIDA Priority | 37.14 | 37.14 | 68.6 | 52.87 | C - Line within 0.5 km; node over 1 km | 4.15 | 0.43 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3701
4 | 702 | 3702 | 1380601216 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 215 | 12.1081 | 120.6437 | U | 3147 | 4.95 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.55 | 52.99 | Tier 1B: High GIDA Priority | 33.04 | 33.04 | 72.7 | 52.87 | F - Nearest node and line over 5 km | 44.55 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3702
4 | 703 | 3703 | 0506209002 | Region V (Bicol Region) | Sorsogon | Irosin | Bacolod | 12.7014 | 124.0359 | R | 4737 | 4 | 1184 | 355 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 0.13 | Tier 2A: High Commercial ROI | 75.68 | 75.68 | 30.03 | 52.86 | A - Node within 0.5 km | 0.1 | 0.06 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3703
4 | 704 | 3704 | 0301420010 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Sapang Palay | 14.8388 | 121.0434 | U | 6067 | 3.5 | 1733 | 520 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.94 | Tier 2B: Moderate GIDA Inclusion | 65.33 | 65.33 | 40.38 | 52.86 | B - Node 0.5-1 km | 0.78 | 4.13 | Node: SJD005 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 3704
4 | 705 | 3705 | 0103314027 | Region I (Ilocos Region) | La Union | City of San Fernando | Ilocanos Norte | 16.6202 | 120.3148 | R | 1151 | 3.7 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 52.24 | 52.24 | 53.47 | 52.86 | C - Line within 0.5 km; node over 1 km | 1.88 | 0.2 | Line: SAN FERNANDO - SUPIDEN AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3705
4 | 706 | 3706 | 0405637023 | Region IV-A (CALABARZON) | Quezon | Quezon | Villa Gomez | 14.0782 | 122.132 | R | 434 | 3.8 | 114 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.13 | 16.66 | Tier 1B: High GIDA Priority | 41.67 | 41.67 | 64.04 | 52.86 | F - Nearest node and line over 5 km | 9.13 | 16.66 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3706
4 | 707 | 3707 | 0806022043 | Region VIII (Eastern Visayas) | Samar | Paranas | Tapul | 11.901 | 125.0795 | R | 424 | 4.1 | 103 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74.02 | 76.94 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 73.53 | 52.86 | F - Nearest node and line over 5 km | 74.02 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3707
4 | 708 | 3708 | 1908806021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Puya | 17.255 | 122.229 | R | 1003 | 4.7 | 213 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.43 | 34.31 | Tier 1B: High GIDA Priority | 30.18 | 30.18 | 75.54 | 52.86 | F - Nearest node and line over 5 km | 29.43 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3708
4 | 709 | 3709 | 0401009010 | Region IV-A (CALABARZON) | Batangas | Cuenca | Ibabao | 13.9087 | 121.0723 | R | 3935 | 3.6 | 1093 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 0.18 | Tier 2A: High Commercial ROI | 72.01 | 72.01 | 33.69 | 52.85 | C - Line within 0.5 km; node over 1 km | 2.73 | 0.18 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3709
4 | 710 | 3710 | 0301423025 | Region III (Central Luzon) | Bulacan | Santa Maria | Tumana | 14.8131 | 120.9736 | U | 10877 | 3.5 | 3108 | 932 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.21 | Tier 2A: High Commercial ROI | 70.05 | 70.05 | 35.64 | 52.85 | B - Node 0.5-1 km | 0.51 | 0.02 | Line: STA MARIA | Survey short node lateral; confirm port/fiber capacity, access and route. | 3710
4 | 711 | 3711 | 0401017013 | Region IV-A (CALABARZON) | Batangas | Malvar | San Fernando | 14.0261 | 121.1635 | U | 5844 | 3.6 | 1623 | 487 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 65.07 | 65.07 | 40.63 | 52.85 | B - Node 0.5-1 km | 0.64 | 0.15 | Line: UG_TNB001 TO DIVERSION RD | Survey short node lateral; confirm port/fiber capacity, access and route. | 3711
4 | 712 | 3712 | 0405804014 | Region IV-A (CALABARZON) | Rizal | Binangonan | Kalawaan | 14.491 | 121.185 | U | 37983 | 3.6 | 10551 | 3165 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.73 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 65.06 | 65.06 | 40.63 | 52.85 | B - Node 0.5-1 km | 0.73 | 0.11 | Line: TAYTAY TO SNL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3712
4 | 713 | 3713 | 0402118064 | Region IV-A (CALABARZON) | Cavite | Silang | San Vicente II | 14.2318 | 120.9627 | U | 4835 | 3.4 | 1422 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.05 | 1.36 | Tier 2B: Moderate GIDA Inclusion | 57.9 | 57.9 | 47.8 | 52.85 | D - Other node or line within 3 km | 7.05 | 1.34 | Line: SILANG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3713
4 | 714 | 3714 | 0102805036 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Quiling Sur | 18.0659 | 120.5515 | R | 3317 | 3.7 | 896 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.95 | Tier 2B: Moderate GIDA Inclusion | 69.48 | 69.48 | 36.21 | 52.84 | D - Other node or line within 3 km | 1.05 | 0.92 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3714
4 | 715 | 3715 | 0301404001 | Region III (Central Luzon) | Bulacan | Bocaue | Antipona | 14.8027 | 120.9413 | R | 1815 | 3.5 | 519 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 1.13 | Tier 2B: Moderate GIDA Inclusion | 57.91 | 57.91 | 47.77 | 52.84 | D - Other node or line within 3 km | 1.88 | 1.13 | Line: STA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3715
4 | 716 | 3716 | 0403429010 | Region IV-A (CALABARZON) | Laguna | Siniloan | Laguio | 14.4661 | 121.4783 | R | 874 | 3.3 | 265 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.86 | 4.43 | Tier 1B: High GIDA Priority | 47.42 | 47.42 | 58.26 | 52.84 | D - Other node or line within 3 km | 1.86 | 4.43 | Node: FYL001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3716
4 | 717 | 3717 | 1401104010 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Tikey | 16.5225 | 120.7993 | R | 615 | 3.5 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.59 | 5.35 | Tier 1B: High GIDA Priority | 46.38 | 46.38 | 59.31 | 52.84 | F - Nearest node and line over 5 km | 5.59 | 5.29 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3717
4 | 718 | 3718 | 0504117021 | Region V (Bicol Region) | Masbate | Placer | Naboctot | 11.8578 | 123.7675 | R | 1361 | 4.1 | 332 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.55 | 28.62 | Tier 1B: High GIDA Priority | 40.17 | 40.17 | 65.5 | 52.84 | F - Nearest node and line over 5 km | 15.55 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3718
4 | 719 | 3719 | 0405809001 | Region IV-A (CALABARZON) | Rizal | Morong | Bombongan | 14.5059 | 121.2197 | R | 3722 | 3.6 | 1034 | 310 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 36.78 | 52.83 | D - Other node or line within 3 km | 1.67 | 1.54 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3719
4 | 720 | 3720 | 0403405029 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Masili | 14.1824 | 121.2003 | R | 4195 | 3.3 | 1271 | 381 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.54 | 1 | Tier 2B: Moderate GIDA Inclusion | 66.19 | 66.19 | 39.47 | 52.83 | D - Other node or line within 3 km | 4.54 | 1 | Line: CLB001 TO SCL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3720
4 | 721 | 3721 | 1907003005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Mapun | Guppah | 17.2557 | 122.2298 | R | 2470 | 5.8 | 426 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.55 | 34.42 | Tier 1B: High GIDA Priority | 40.25 | 40.25 | 65.41 | 52.83 | F - Nearest node and line over 5 km | 29.55 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3721
4 | 722 | 3722 | 1380610012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 697 | 12.4207 | 122.7837 | U | 3568 | 4.43 | 805 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59.83 | 67.58 | Tier 1B: High GIDA Priority | 37.5 | 37.5 | 68.16 | 52.83 | F - Nearest node and line over 5 km | 59.83 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3722
4 | 723 | 3723 | 0603013074 | Region VI (Western Visayas) | Iloilo | Calinog | Supanga | 11.1919 | 122.3987 | R | 913 | 3.8 | 240 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.85 | 18.3 | Tier 1B: High GIDA Priority | 34.93 | 34.93 | 70.72 | 52.83 | F - Nearest node and line over 5 km | 27.85 | 22.97 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3723
4 | 724 | 3724 | 1380606118 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 512 | 13.5955 | 122.8227 | U | 2560 | 3.66 | 700 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.67 | 20.66 | Tier 1B: High GIDA Priority | 34.7 | 34.7 | 70.95 | 52.83 | F - Nearest node and line over 5 km | 20.67 | 20.57 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3724
4 | 725 | 3725 | 1380601133 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 133 | 11.9459 | 121.1032 | U | 2317 | 3.87 | 599 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.68 | 39.11 | Tier 1B: High GIDA Priority | 32.08 | 32.08 | 73.57 | 52.83 | F - Nearest node and line over 5 km | 40.68 | 999999 | Node: MYM001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3725
4 | 726 | 3726 | 0405646037 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Santa Cecilia | 13.9669 | 122.5354 | R | 3763 | 3.8 | 990 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.41 | Tier 2A: High Commercial ROI | 70.37 | 70.37 | 35.28 | 52.82 | B - Node 0.5-1 km | 0.77 | 0.4 | Line: CALAUAG - SIPOCOT | Survey short node lateral; confirm port/fiber capacity, access and route. | 3726
4 | 727 | 3727 | 0403429005 | Region IV-A (CALABARZON) | Laguna | Siniloan | Buhay | 14.4286 | 121.4486 | R | 1217 | 3.3 | 369 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.79 | 0.75 | Tier 2B: Moderate GIDA Inclusion | 55.64 | 55.64 | 50.01 | 52.82 | B - Node 0.5-1 km | 0.79 | 0.73 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3727
4 | 728 | 3728 | 1903614033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Pagayonan | 17.2546 | 122.2287 | R | 1084 | 5.7 | 190 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.38 | 34.27 | Tier 1B: High GIDA Priority | 34.07 | 34.07 | 71.56 | 52.82 | F - Nearest node and line over 5 km | 29.38 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3728
4 | 729 | 3729 | 0806022019 | Region VIII (Eastern Visayas) | Samar | Paranas | Maylobe | 11.9384 | 125.0608 | R | 347 | 4.1 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 77.96 | 80.92 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 73.46 | 52.82 | F - Nearest node and line over 5 km | 77.96 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3729
4 | 730 | 3730 | 1908806017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Mao | 17.255 | 122.229 | R | 994 | 4.7 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.43 | 34.31 | Tier 1B: High GIDA Priority | 30.09 | 30.09 | 75.55 | 52.82 | F - Nearest node and line over 5 km | 29.43 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3730
4 | 731 | 3731 | 0105511016 | Region I (Ilocos Region) | Pangasinan | Bayambang | Bical Norte | 15.8134 | 120.4381 | R | 3690 | 3.6 | 1025 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 1.83 | Tier 2B: Moderate GIDA Inclusion | 68.82 | 68.82 | 36.8 | 52.81 | D - Other node or line within 3 km | 1.83 | 1.83 | Line: AERIAL 96C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3731
4 | 732 | 3732 | 0704602009 | Region VII (Central Visayas) | Negros Oriental | Ayungon | Carol-an | 9.8579 | 122.9803 | R | 3514 | 3.8 | 925 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.49 | 8.14 | Tier 2B: Moderate GIDA Inclusion | 53.52 | 53.52 | 52.11 | 52.81 | F - Nearest node and line over 5 km | 15.49 | 8.13 | Line: KABANGKALAN - BACONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3732
4 | 733 | 3733 | 0300809009 | Region III (Central Luzon) | Bataan | Orani | Masantol | 14.7876 | 120.505 | R | 554 | 3.6 | 154 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 0.88 | Tier 1B: High GIDA Priority | 45.66 | 45.66 | 59.95 | 52.81 | D - Other node or line within 3 km | 3.74 | 0.87 | Line: 96C DONA TO ORANI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3733
4 | 734 | 3734 | 1108205009 | Region XI (Davao Region) | Davao de Oro | Maragusan | Katipunan | 7.4135 | 126.1456 | R | 1697 | 3.7 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.55 | 27.08 | Tier 1B: High GIDA Priority | 38.83 | 38.83 | 66.79 | 52.81 | F - Nearest node and line over 5 km | 32.55 | 27.06 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3734
4 | 735 | 3735 | 0405627021 | Region IV-A (CALABARZON) | Quezon | Mauban | Sadsaran | 14.1887 | 121.7328 | R | 4090 | 3.8 | 1076 | 323 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.86 | 19.5 | Tier 2B: Moderate GIDA Inclusion | 65.21 | 65.21 | 40.4 | 52.8 | D - Other node or line within 3 km | 1.86 | 19.5 | Node: MBQ001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3735
4 | 736 | 3736 | 0304902023 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Santor | 15.6105 | 121.1661 | U | 6590 | 3.5 | 1883 | 565 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.58 | 2.04 | Tier 2B: Moderate GIDA Inclusion | 59.33 | 59.33 | 46.26 | 52.8 | D - Other node or line within 3 km | 2.58 | 2.04 | Line: Proposed AE F1-6 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3736
4 | 737 | 3737 | 0402120036 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan II | 14.4044 | 120.8466 | R | 1060 | 3.4 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.8 | 1.51 | Tier 2B: Moderate GIDA Inclusion | 52.3 | 52.3 | 53.3 | 52.8 | D - Other node or line within 3 km | 1.8 | 1.48 | Line: PSG001 RELIANCE TO NCC001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3737
4 | 738 | 3738 | 0405647008 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angustias Zone II | 14.0264 | 121.5911 | R | 253 | 3.8 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 49.85 | 49.85 | 55.75 | 52.8 | A - Node within 0.5 km | 0.4 | 0.11 | Line: LUCENA - LUCBAN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3738
4 | 739 | 3739 | 1906612006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Bulansing Tara | 16.3682 | 122.1267 | R | 866 | 6 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.41 | 1.58 | Tier 1B: High GIDA Priority | 40.93 | 40.93 | 64.68 | 52.8 | F - Nearest node and line over 5 km | 8.41 | 999999 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3739
4 | 740 | 3740 | 1906606002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Bubuan | 17.2553 | 122.2293 | R | 1133 | 6 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.36 | Tier 1B: High GIDA Priority | 34.06 | 34.06 | 71.54 | 52.8 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3740
4 | 741 | 3741 | 0506216006 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Bibincahan | 12.9841 | 124.0101 | U | 21026 | 4 | 5256 | 1577 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.74 | 0.89 | Tier 2A: High Commercial ROI | 75.3 | 75.3 | 30.29 | 52.79 | D - Other node or line within 3 km | 1.74 | 0.88 | Line: FOC-7,512m | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3741
4 | 742 | 3742 | 0105526029 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Tebag | 16.0803 | 120.407 | R | 3084 | 3.6 | 857 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.48 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 37.93 | 52.79 | D - Other node or line within 3 km | 1.48 | 1.03 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3742
4 | 743 | 3743 | 1102301009 | Region XI (Davao Region) | Davao del Norte | Asuncion | Camansa | 7.7159 | 125.9006 | R | 1580 | 3.7 | 427 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.15 | 9.93 | Tier 1B: High GIDA Priority | 39.53 | 39.53 | 66.05 | 52.79 | F - Nearest node and line over 5 km | 21.15 | 9.93 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3743
4 | 744 | 3744 | 1400109005 | Cordillera Administrative Region (CAR) | Abra | Lacub | Pacoc | 17.6668 | 120.9556 | R | 689 | 3.8 | 181 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.63 | 30.61 | Tier 1B: High GIDA Priority | 35.44 | 35.44 | 70.14 | 52.79 | F - Nearest node and line over 5 km | 30.63 | 30.59 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3744
4 | 745 | 3745 | 1001304022 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Sur | 7.6777 | 124.9943 | U | 12727 | 3.8 | 3349 | 1005 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.2 | 0.22 | Tier 2A: High Commercial ROI | 72.64 | 72.64 | 32.92 | 52.78 | A - Node within 0.5 km | 0.2 | 0.21 | Node: DCR001- BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3745
4 | 746 | 3746 | 0301421041 | Region III (Central Luzon) | Bulacan | San Miguel | Salangan | 15.1341 | 120.9593 | U | 5606 | 3.5 | 1602 | 481 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 65.58 | 65.58 | 39.98 | 52.78 | A - Node within 0.5 km | 0.47 | 0.38 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3746
4 | 747 | 3747 | 0405625001 | Region IV-A (CALABARZON) | Quezon | Macalelon | Amontay | 13.7328 | 122.1585 | R | 828 | 3.8 | 218 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 52.72 | 52.72 | 52.85 | 52.78 | D - Other node or line within 3 km | 2.81 | 1.45 | Line: UNISAN TO MULANAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3747
4 | 748 | 3748 | 1705301020 | MIMAROPA Region | Palawan | Aborlan | Culandanum | 9.5556 | 118.2971 | R | 1789 | 3.9 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 52.08 | 54.03 | Tier 1B: High GIDA Priority | 38.14 | 38.14 | 67.43 | 52.78 | F - Nearest node and line over 5 km | 52.08 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3748
4 | 749 | 3749 | 1900710010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Mohammad Ajul | Sulutan Matangal | 17.2542 | 122.2282 | R | 2295 | 5.1 | 450 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.31 | 34.21 | Tier 1B: High GIDA Priority | 36.38 | 36.38 | 69.17 | 52.78 | F - Nearest node and line over 5 km | 29.31 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3749
4 | 750 | 3750 | 0702208009 | Region VII (Central Visayas) | Cebu | Balamban | Cambuhawe | 10.5 | 123.719 | R | 3845 | 3.8 | 1012 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.4 | Tier 2A: High Commercial ROI | 71.59 | 71.59 | 33.95 | 52.77 | C - Line within 0.5 km; node over 1 km | 1.13 | 0.37 | Line: 104.3km-96FOC-toledo-san remigio | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3750
4 | 751 | 3751 | 0307706009 | Region III (Central Luzon) | Aurora | Dipaculao | Dinadiawan | 16.0772 | 121.7706 | R | 3215 | 3.8 | 846 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 69.63 | 69.63 | 35.92 | 52.77 | A - Node within 0.5 km | 0.31 | 0.08 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3751
4 | 752 | 3752 | 0105546022 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Mabanogbog | 15.9755 | 120.5515 | R | 3498 | 3.6 | 972 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.99 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 67.04 | 67.04 | 38.5 | 52.77 | C - Line within 0.5 km; node over 1 km | 2.99 | 0.12 | Line: URDANETA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3752
4 | 753 | 3753 | 0401005003 | Region IV-A (CALABARZON) | Batangas | Batangas City | Balagtas | 13.8013 | 121.0705 | U | 10517 | 3.6 | 2921 | 876 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.58 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 63.74 | 63.74 | 41.8 | 52.77 | C - Line within 0.5 km; node over 1 km | 4.58 | 0.26 | Line: CLB001 TO BCY01 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3753
4 | 754 | 3754 | 0501730018 | Region V (Bicol Region) | Camarines Sur | Ragay | Inandawa | 13.8092 | 122.7966 | R | 380 | 4.2 | 90 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 51.95 | 51.95 | 53.59 | 52.77 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.05 | Line: CALAUAG - SIPOCOT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3754
4 | 755 | 3755 | 1906607023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Lunggang | 17.2611 | 122.248 | R | 1160 | 6 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.44 | 36.45 | Tier 1B: High GIDA Priority | 34 | 34 | 71.54 | 52.77 | F - Nearest node and line over 5 km | 31.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3755
4 | 756 | 3756 | 0304907004 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Bitulok | 15.4566 | 121.336 | R | 3180 | 3.5 | 909 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 23.53 | Tier 2B: Moderate GIDA Inclusion | 63.28 | 63.28 | 42.24 | 52.76 | E - Nearest node or line 3-5 km | 3.05 | 23.51 | Node: GBN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3756
4 | 757 | 3757 | 1705309004 | MIMAROPA Region | Palawan | Coron | Buenavista | 12.1636 | 120.2405 | R | 1517 | 3.9 | 389 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.87 | 91.53 | Tier 1B: High GIDA Priority | 39.74 | 39.74 | 65.77 | 52.76 | F - Nearest node and line over 5 km | 16.87 | 999999 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3757
4 | 758 | 3758 | 1906610011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Patian | 17.2556 | 122.2296 | R | 1108 | 6 | 185 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 33.97 | 33.97 | 71.54 | 52.76 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3758
4 | 759 | 3759 | 1906613028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Liu-Bud Pantao | 17.2555 | 122.2295 | R | 1364 | 6 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 30.52 | 30.52 | 75 | 52.76 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3759
4 | 760 | 3760 | 0600407003 | Region VI (Western Visayas) | Aklan | Kalibo | Bachaw Sur | 11.6919 | 122.3734 | R | 3705 | 3.9 | 950 | 285 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.73 | Tier 2A: High Commercial ROI | 70.54 | 70.54 | 34.97 | 52.75 | B - Node 0.5-1 km | 0.93 | 0.73 | Line: IVISAN - KALIBO | Survey short node lateral; confirm port/fiber capacity, access and route. | 3760
4 | 761 | 3761 | 1401105013 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Poblacion | 16.7835 | 120.8244 | R | 3192 | 3.5 | 912 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.25 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 67.88 | 67.88 | 37.62 | 52.75 | D - Other node or line within 3 km | 2.25 | 0.93 | Line: LA TRINIDAD-SAGADA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3761
4 | 762 | 3762 | 0105533025 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tocok | 16.1416 | 120.4198 | R | 3807 | 3.6 | 1058 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.61 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 66.6 | 66.6 | 38.89 | 52.75 | C - Line within 0.5 km; node over 1 km | 3.61 | 0.02 | Line: SAN FABIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3762
4 | 763 | 3763 | 0301407022 | Region III (Central Luzon) | Bulacan | Calumpit | Pungo | 14.9018 | 120.79 | U | 9959 | 3.5 | 2845 | 854 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.44 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 65.95 | 65.95 | 39.55 | 52.75 | C - Line within 0.5 km; node over 1 km | 2.44 | 0.45 | Line: Calumpit-Baliuag Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3763
4 | 764 | 3764 | 0403408020 | Region IV-A (CALABARZON) | Laguna | Famy | Tunhac | 14.4387 | 121.4499 | U | 2145 | 3.3 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 61.16 | 61.16 | 44.33 | 52.75 | A - Node within 0.5 km | 0.36 | 0.34 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3764
4 | 765 | 3765 | 0300805023 | Region III (Central Luzon) | Bataan | Hermosa | Tipo | 14.8139 | 120.3472 | U | 7181 | 3.6 | 1995 | 598 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.78 | 3.45 | Tier 2B: Moderate GIDA Inclusion | 57.43 | 57.43 | 48.07 | 52.75 | E - Nearest node or line 3-5 km | 4.78 | 3.45 | Line: SEGMENT 44 (DINALUPIHAN - OLONGAPO) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3765
4 | 766 | 3766 | 1381300080 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pasong Tamo | 14.6755 | 121.0455 | U | 113319 | 3.74 | 30306 | 9092 | Band n50 (1.5 GHz, 100 MHz TDD) | 10 | 1 | 0.63 | 0.06 | Tier 1B: High GIDA Priority | 48 | 48 | 57.49 | 52.75 | B - Node 0.5-1 km | 0.63 | 0.32 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 3766
4 | 767 | 3767 | 1102504008 | Region XI (Davao Region) | Davao Oriental | Caraga | Palma Gil | 7.3954 | 126.4739 | R | 1932 | 3.6 | 537 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.55 | 56.01 | Tier 1B: High GIDA Priority | 40.23 | 40.23 | 65.26 | 52.75 | F - Nearest node and line over 5 km | 56.55 | 999999 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3767
4 | 768 | 3768 | 1705314006 | MIMAROPA Region | Palawan | Magsaysay | Emilod | 10.8463 | 121.059 | R | 776 | 3.9 | 199 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 96.46 | 96.44 | Tier 1B: High GIDA Priority | 36.1 | 36.1 | 69.41 | 52.75 | F - Nearest node and line over 5 km | 96.46 | 999999 | Node: SBV001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3768
4 | 769 | 3769 | 0806002019 | Region VIII (Eastern Visayas) | Samar | Basey | Inuntan | 11.3553 | 125.145 | R | 652 | 4.1 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.18 | 21.48 | Tier 1B: High GIDA Priority | 34.52 | 34.52 | 70.98 | 52.75 | F - Nearest node and line over 5 km | 20.18 | 21.71 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3769
4 | 770 | 3770 | 0402113002 | Region IV-A (CALABARZON) | Cavite | Maragondon | Bucal I | 14.2729 | 120.7412 | R | 3478 | 3.4 | 1023 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.11 | Tier 2A: High Commercial ROI | 70.96 | 70.96 | 34.52 | 52.74 | B - Node 0.5-1 km | 0.53 | 0.11 | Line: NCC001 TO NSB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3770
4 | 771 | 3771 | 0401019013 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 8 | 14.0799 | 120.6885 | R | 1118 | 3.6 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.96 | 2.91 | Tier 1B: High GIDA Priority | 44.63 | 44.63 | 60.85 | 52.74 | D - Other node or line within 3 km | 5.96 | 2.91 | Line: ALFONSO - TUY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3771
4 | 772 | 3772 | 1380606145 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 539 | 13.5518 | 120.9524 | U | 2015 | 4.31 | 467 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.85 | 5.32 | Tier 1B: High GIDA Priority | 36.59 | 36.59 | 68.89 | 52.74 | F - Nearest node and line over 5 km | 5.85 | 5.32 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3772
4 | 773 | 3773 | 1380612036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 870 | 11.5399 | 121.714 | U | 3139 | 4.1 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 51.96 | 49.69 | Tier 1B: High GIDA Priority | 36.45 | 36.45 | 69.04 | 52.74 | F - Nearest node and line over 5 km | 51.96 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3773
4 | 774 | 3774 | 1906613056 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Upper Laus | 17.2554 | 122.2295 | R | 1221 | 6 | 204 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 29.91 | 29.91 | 75.57 | 52.74 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3774
4 | 775 | 3775 | 1380601081 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 81 | 13.8704 | 121.4536 | U | 1848 | 4.83 | 383 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.95 | 2.39 | Tier 1B: High GIDA Priority | 34.93 | 34.93 | 70.53 | 52.73 | D - Other node or line within 3 km | 4.95 | 2.39 | Line: SAN JUAN TO UNISAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3775
4 | 776 | 3776 | 1903609012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Ganassi | Macaguiling | 17.2547 | 122.2287 | R | 1045 | 5.7 | 183 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.39 | 34.28 | Tier 1B: High GIDA Priority | 33.9 | 33.9 | 71.56 | 52.73 | F - Nearest node and line over 5 km | 29.39 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3776
4 | 777 | 3777 | 0301417014 | Region III (Central Luzon) | Bulacan | Plaridel | Parulan | 14.8913 | 120.8758 | U | 9340 | 3.5 | 2669 | 801 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.97 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 64.73 | 64.73 | 40.71 | 52.72 | D - Other node or line within 3 km | 2.97 | 0.63 | Line: 48 CORE (6X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3777
4 | 778 | 3778 | 0105526004 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Banaoang | 16.0603 | 120.4092 | U | 5904 | 3.6 | 1640 | 492 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.12 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 64.4 | 64.4 | 41.04 | 52.72 | D - Other node or line within 3 km | 1.12 | 0.74 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3778
4 | 779 | 3779 | 0401009018 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 4 | 13.9061 | 121.06 | R | 1038 | 3.6 | 288 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 56.67 | 56.67 | 48.76 | 52.72 | C - Line within 0.5 km; node over 1 km | 1.44 | 0.34 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3779
4 | 780 | 3780 | 0806417012 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Kahupian | 10.4812 | 125.0025 | R | 1526 | 4.1 | 372 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.8 | 0.1 | Tier 1B: High GIDA Priority | 47.82 | 47.82 | 57.61 | 52.72 | F - Nearest node and line over 5 km | 31.11 | 28.46 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3780
4 | 781 | 3781 | 1380601163 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 163 | 11.523 | 122.1469 | U | 3850 | 5.42 | 710 | 213 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.75 | 23.87 | Tier 1B: High GIDA Priority | 34.96 | 34.96 | 70.47 | 52.72 | F - Nearest node and line over 5 km | 19.75 | 23.87 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3781
4 | 782 | 3782 | 1400109004 | Cordillera Administrative Region (CAR) | Abra | Lacub | Lan-ag | 17.7368 | 120.8938 | R | 433 | 3.8 | 114 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.49 | 23.17 | Tier 1B: High GIDA Priority | 34.77 | 34.77 | 70.67 | 52.72 | F - Nearest node and line over 5 km | 25.49 | 23.71 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3782
4 | 783 | 3783 | 0806017014 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Igang-igang | 11.4655 | 124.8615 | R | 721 | 4.1 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.3 | 25.25 | Tier 1B: High GIDA Priority | 33.7 | 33.7 | 71.75 | 52.72 | F - Nearest node and line over 5 km | 26.3 | 25.25 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3783
4 | 784 | 3784 | 1380601073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 73 | 11.66 | 121.4966 | U | 2394 | 4.58 | 523 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 58.47 | 57.31 | Tier 1B: High GIDA Priority | 30.07 | 30.07 | 75.37 | 52.72 | F - Nearest node and line over 5 km | 58.47 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3784
4 | 785 | 3785 | 1004314003 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Kibaghot | 8.5893 | 124.4533 | R | 4147 | 3.9 | 1063 | 319 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 2.07 | Tier 2A: High Commercial ROI | 71.5 | 71.5 | 33.91 | 52.71 | D - Other node or line within 3 km | 2.02 | 2.03 | Node: LGD001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3785
4 | 786 | 3786 | 0301418011 | Region III (Central Luzon) | Bulacan | Pulilan | Lumbac | 14.916 | 120.8345 | R | 4982 | 3.5 | 1423 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.31 | 0.95 | Tier 2B: Moderate GIDA Inclusion | 69.3 | 69.3 | 36.11 | 52.71 | D - Other node or line within 3 km | 2.31 | 0.95 | Line: CALUMPIT - BALIUAG LINK | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3786
4 | 787 | 3787 | 0600416014 | Region VI (Western Visayas) | Aklan | Numancia | Marianos | 11.7114 | 122.3386 | R | 1210 | 3.9 | 310 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.91 | Tier 2B: Moderate GIDA Inclusion | 59.7 | 59.7 | 45.73 | 52.71 | D - Other node or line within 3 km | 1.47 | 2.29 | Node: NUK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3787
4 | 788 | 3788 | 0401006024 | Region IV-A (CALABARZON) | Batangas | Bauan | New Danglayan | 13.7837 | 121.003 | R | 1521 | 3.6 | 422 | 127 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 1.09 | Tier 2B: Moderate GIDA Inclusion | 56.3 | 56.3 | 49.13 | 52.71 | D - Other node or line within 3 km | 1.21 | 1.09 | Line: UG BUN001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3788
4 | 789 | 3789 | 0600614011 | Region VI (Western Visayas) | Antique | San Remigio | Bulan-bulan | 10.8894 | 122.181 | R | 727 | 3.9 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.07 | 22.95 | Tier 1B: High GIDA Priority | 33.53 | 33.53 | 71.9 | 52.71 | F - Nearest node and line over 5 km | 30.07 | 22.84 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3789
4 | 790 | 3790 | 1907007048 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Salamat | 14.4102 | 121.7712 | R | 965 | 5.8 | 166 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.64 | 31.52 | Tier 1B: High GIDA Priority | 30.98 | 30.98 | 74.44 | 52.71 | F - Nearest node and line over 5 km | 18.64 | 31.52 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3790
4 | 791 | 3791 | 1907006023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Nusa-nusa | 15.424 | 122.0019 | R | 458 | 5.8 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 60.06 | 59.85 | Tier 1B: High GIDA Priority | 27.41 | 27.41 | 78.01 | 52.71 | F - Nearest node and line over 5 km | 60.06 | 999999 | Node: BLA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3791
4 | 792 | 3792 | 1907006008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bubuan | 5.4095 | 120.5883 | R | 749 | 5.8 | 129 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 234.13 | 234.13 | Tier 1B: High GIDA Priority | 27.39 | 27.39 | 78.02 | 52.71 | F - Nearest node and line over 5 km | 234.13 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3792
4 | 793 | 3793 | 1004307016 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Taytay | 8.5424 | 124.5408 | R | 4450 | 3.9 | 1141 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 0.23 | Tier 2A: High Commercial ROI | 70.08 | 70.08 | 35.31 | 52.7 | C - Line within 0.5 km; node over 1 km | 2.46 | 0.23 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3793
4 | 794 | 3794 | 0305406017 | Region III (Central Luzon) | Pampanga | Floridablanca | Nabuclod | 14.9971 | 120.4475 | R | 4682 | 4 | 1170 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.66 | 6.26 | Tier 2B: Moderate GIDA Inclusion | 61.46 | 61.46 | 43.94 | 52.7 | F - Nearest node and line over 5 km | 6.66 | 6.25 | Line: 48 CORE (4X12) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3794
4 | 795 | 3795 | 1906618003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Hambilan | 17.2556 | 122.2297 | R | 5944 | 6 | 991 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.4 | Tier 2B: Moderate GIDA Inclusion | 53.75 | 53.75 | 51.66 | 52.7 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3795
4 | 796 | 3796 | 0600609010 | Region VI (Western Visayas) | Antique | Laua-An | Guiamon | 11.1641 | 122.1125 | R | 242 | 3.9 | 62 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.57 | 42.14 | Tier 1B: High GIDA Priority | 36.75 | 36.75 | 68.64 | 52.7 | F - Nearest node and line over 5 km | 48.57 | 41.79 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3796
4 | 797 | 3797 | 1903638024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Bagoaingud | 17.2616 | 122.2122 | R | 1002 | 5.7 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.59 | 32.84 | Tier 1B: High GIDA Priority | 33.8 | 33.8 | 71.61 | 52.7 | F - Nearest node and line over 5 km | 28.59 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3797
4 | 798 | 3798 | 1908824011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Marader | 16.1104 | 122.4791 | R | 1472 | 4.7 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.21 | 41.78 | Tier 1B: High GIDA Priority | 32.23 | 32.23 | 73.16 | 52.7 | F - Nearest node and line over 5 km | 42.21 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3798
4 | 799 | 3799 | 1108206011 | Region XI (Davao Region) | Davao de Oro | Mawab | Tuboran | 7.4915 | 125.8961 | R | 3314 | 3.7 | 896 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.05 | 1.25 | Tier 2B: Moderate GIDA Inclusion | 61.48 | 61.48 | 43.9 | 52.69 | D - Other node or line within 3 km | 9.05 | 1.23 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3799
4 | 800 | 3800 | 0103301004 | Region I (Ilocos Region) | La Union | Agoo | Consolacion | 16.3251 | 120.3695 | U | 1720 | 3.7 | 465 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 52.1 | 52.1 | 53.28 | 52.69 | A - Node within 0.5 km | 0.21 | 0.08 | Line: AGOO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3800
4 | 801 | 3801 | 0401019014 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 9 | 14.1017 | 120.6663 | U | 768 | 3.6 | 213 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.89 | 0.24 | Tier 1B: High GIDA Priority | 38.61 | 38.61 | 66.77 | 52.69 | C - Line within 0.5 km; node over 1 km | 4.89 | 0.08 | Line: NCC001 TO NSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3801
4 | 802 | 3802 | 1381100071 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 71 | 14.6228 | 121.0388 | U | 680 | 3.8 | 179 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.91 | 0.06 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 36.42 | 36.42 | 68.95 | 52.69 | C - Line within 0.5 km; node over 1 km | 1.91 | 0.02 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3802
4 | 803 | 3803 | 1001321001 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Bagontaas | 7.946 | 125.1027 | U | 14291 | 3.8 | 3761 | 1128 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.85 | 0.14 | Tier 2A: High Commercial ROI | 72.41 | 72.41 | 32.95 | 52.68 | B - Node 0.5-1 km | 0.85 | 0.17 | Line: MALAYBALAY - KITAOTAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 3803
4 | 804 | 3804 | 1404408008 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Demang | 17.1714 | 121.0239 | R | 845 | 3.7 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.25 | 2.43 | Tier 2B: Moderate GIDA Inclusion | 50.9 | 50.9 | 54.47 | 52.68 | D - Other node or line within 3 km | 2.25 | 2.02 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3804
4 | 805 | 3805 | 0600404008 | Region VI (Western Visayas) | Aklan | Batan | Ipil | 11.5806 | 122.4691 | R | 575 | 3.9 | 147 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.5 | 3.32 | Tier 2B: Moderate GIDA Inclusion | 48.37 | 48.37 | 57 | 52.68 | E - Nearest node or line 3-5 km | 5.5 | 3.32 | Line: IVISAN - KALIBO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3805
4 | 806 | 3806 | 1907004007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Ubol | 17.2558 | 122.2299 | R | 1993 | 5.8 | 344 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.43 | Tier 1B: High GIDA Priority | 38.07 | 38.07 | 67.29 | 52.68 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3806
4 | 807 | 3807 | 1381300140 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Holy Spirit | 14.6893 | 121.0817 | U | 113614 | 3.93 | 28902 | 8671 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 0.44 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 48.4 | 48.4 | 56.94 | 52.67 | A - Node within 0.5 km | 0.44 | 0.25 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3807
4 | 808 | 3808 | 0804814021 | Region VIII (Eastern Visayas) | Northern Samar | Palapag | Nipa | 12.573 | 125.1502 | R | 1295 | 4.3 | 301 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 112.04 | 110.95 | Tier 1B: High GIDA Priority | 35.42 | 35.42 | 69.92 | 52.67 | F - Nearest node and line over 5 km | 112.04 | 999999 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3808
4 | 809 | 3809 | 1206312016 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Magsaysay | 6.2153 | 125.0576 | U | 14447 | 3.6 | 4013 | 1204 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.86 | 1.28 | Tier 2A: High Commercial ROI | 73.07 | 73.07 | 32.25 | 52.66 | B - Node 0.5-1 km | 0.86 | 1.28 | Node: PMK001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3809
4 | 810 | 3810 | 1401111011 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Sapid | 16.8535 | 120.7842 | R | 2956 | 3.5 | 845 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 1 | Tier 2B: Moderate GIDA Inclusion | 67.96 | 67.96 | 37.37 | 52.66 | D - Other node or line within 3 km | 1.13 | 0.99 | Line: PROPOSED 96C FOC - BUGIAS TO CERVANTES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3810
4 | 811 | 3811 | 0102804012 | Region I (Ilocos Region) | Ilocos Norte | Bangui | San Lorenzo | 18.5383 | 120.7636 | R | 2295 | 3.7 | 620 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 67.53 | 67.53 | 37.8 | 52.66 | B - Node 0.5-1 km | 0.54 | 0.24 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3811
4 | 812 | 3812 | 0501603015 | Region V (Bicol Region) | Camarines Norte | Daet | Lag-On | 14.1182 | 122.9421 | U | 6015 | 4 | 1504 | 451 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 66.56 | 66.56 | 38.75 | 52.66 | C - Line within 0.5 km; node over 1 km | 1.31 | 0.45 | Line: PAGBILAO - NAGA (UG + Aerial) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3812
4 | 813 | 3813 | 0201505030 | Region II (Cagayan Valley) | Cagayan | Aparri | Maura | 18.3547 | 121.6483 | U | 8322 | 3.9 | 2134 | 640 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 11.21 | Tier 2B: Moderate GIDA Inclusion | 62.07 | 62.07 | 43.24 | 52.66 | D - Other node or line within 3 km | 1.3 | 11.18 | Node: ARC001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3813
4 | 814 | 3814 | 1403213012 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Calanan | 17.4085 | 121.4138 | R | 1722 | 4.3 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.08 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 53.35 | 53.35 | 51.97 | 52.66 | C - Line within 0.5 km; node over 1 km | 3.08 | 0.08 | Line: Tabuk-Conner | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3814
4 | 815 | 3815 | 1705318017 | MIMAROPA Region | Palawan | Roxas | Rizal | 10.233 | 119.2616 | R | 1099 | 3.9 | 282 | 85 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.07 | 4.76 | Tier 1B: High GIDA Priority | 39.14 | 39.14 | 66.18 | 52.66 | E - Nearest node or line 3-5 km | 13.07 | 4.76 | Line: TAYTAY - PUERTO PRINCESA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3815
4 | 816 | 3816 | 0304927008 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Mambangnan | 15.3471 | 120.9562 | U | 9370 | 3.5 | 2677 | 803 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.84 | 1.87 | Tier 2B: Moderate GIDA Inclusion | 64.91 | 64.91 | 40.39 | 52.65 | D - Other node or line within 3 km | 2.84 | 1.87 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3816
4 | 817 | 3817 | 0203109022 | Region II (Cagayan Valley) | Isabela | Cordon | Turod Sur | 16.6685 | 121.4684 | R | 4396 | 3.8 | 1157 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.82 | 0.67 | Tier 2B: Moderate GIDA Inclusion | 64.87 | 64.87 | 40.44 | 52.65 | D - Other node or line within 3 km | 6.82 | 0.67 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3817
4 | 818 | 3818 | 0401031037 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 6 | 14.0868 | 121.1439 | U | 3654 | 3.6 | 1015 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 63.1 | 63.1 | 42.19 | 52.65 | B - Node 0.5-1 km | 0.69 | 0.57 | Line: AE TNB001 TO STB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3818
4 | 819 | 3819 | 0304902014 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Magtanggol | 15.6344 | 121.1479 | R | 1566 | 3.5 | 447 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 57.15 | 57.15 | 48.14 | 52.65 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.38 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3819
4 | 820 | 3820 | 0803710070 | Region VIII (Eastern Visayas) | Leyte | Burauen | Toloyao | 10.9053 | 124.7221 | R | 408 | 3.8 | 107 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 1.76 | Tier 2B: Moderate GIDA Inclusion | 51.15 | 51.15 | 54.14 | 52.65 | D - Other node or line within 3 km | 1.83 | 1.76 | Line: ORMOC - BAYBAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3820
4 | 821 | 3821 | 1380606085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 479 | 12.1105 | 120.8336 | U | 3179 | 4.54 | 700 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.66 | 36.67 | Tier 1B: High GIDA Priority | 34.7 | 34.7 | 70.6 | 52.65 | F - Nearest node and line over 5 km | 36.66 | 36.66 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3821
4 | 822 | 3822 | 1906613011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Gata | 17.2554 | 122.2295 | R | 2104 | 6 | 351 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.5 | 34.38 | Tier 1B: High GIDA Priority | 33.75 | 33.75 | 71.56 | 52.65 | F - Nearest node and line over 5 km | 29.5 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3822
4 | 823 | 3823 | 0907216011 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Litawan | 7.4044 | 122.1391 | R | 673 | 3.6 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.61 | 16.58 | Tier 1B: High GIDA Priority | 32.18 | 32.18 | 73.12 | 52.65 | F - Nearest node and line over 5 km | 22.61 | 16.54 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3823
4 | 824 | 3824 | 0702216011 | Region VII (Central Visayas) | Cebu | Catmon | Catmondaan | 10.6858 | 124.0145 | R | 3423 | 3.8 | 901 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.08 | Tier 2A: High Commercial ROI | 73.96 | 73.96 | 31.32 | 52.64 | B - Node 0.5-1 km | 0.91 | 0.08 | Line: BOGO - DANAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 3824
4 | 825 | 3825 | 0301415006 | Region III (Central Luzon) | Bulacan | Pandi | Cacarong Bata | 14.9036 | 120.9673 | U | 15301 | 3.5 | 4372 | 1312 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.54 | 1.15 | Tier 2A: High Commercial ROI | 71.92 | 71.92 | 33.36 | 52.64 | D - Other node or line within 3 km | 1.54 | 1.15 | Line: PB HH24-25 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3825
4 | 826 | 3826 | 0304911009 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bantug | 15.6445 | 120.762 | R | 4791 | 3.5 | 1369 | 411 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 0.86 | Tier 2A: High Commercial ROI | 70.27 | 70.27 | 35.01 | 52.64 | D - Other node or line within 3 km | 1.58 | 0.84 | Line: 38,161m. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3826
4 | 827 | 3827 | 0304921003 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Las Piñas | 15.3729 | 120.9964 | R | 3664 | 3.5 | 1047 | 314 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.08 | 6 | Tier 2B: Moderate GIDA Inclusion | 68.16 | 68.16 | 37.12 | 52.64 | E - Nearest node or line 3-5 km | 3.08 | 6 | Node: PRN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3827
4 | 828 | 3828 | 0306910027 | Region III (Central Luzon) | Tarlac | Paniqui | Salumague | 15.6662 | 120.5656 | R | 3681 | 3.9 | 944 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.31 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 67.84 | 67.84 | 37.44 | 52.64 | C - Line within 0.5 km; node over 1 km | 2.31 | 0.05 | Line: 20,642 mtrs. | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3828
4 | 829 | 3829 | 0402108002 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Bacao I | 14.3269 | 120.9023 | U | 16731 | 3.4 | 4921 | 1476 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.74 | 3.72 | Tier 2B: Moderate GIDA Inclusion | 64.47 | 64.47 | 40.8 | 52.64 | E - Nearest node or line 3-5 km | 3.74 | 3.94 | Node: TRC002 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3829
4 | 830 | 3830 | 0500502028 | Region V (Bicol Region) | Albay | Camalig | Miti | 13.1335 | 123.607 | R | 942 | 4.1 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 6.07 | Tier 2B: Moderate GIDA Inclusion | 50.46 | 50.46 | 54.81 | 52.64 | D - Other node or line within 3 km | 1.16 | 6.04 | Node: GNA002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3830
4 | 831 | 3831 | 0401029049 | Region IV-A (CALABARZON) | Batangas | Taal | Tatlong Maria | 13.9062 | 120.965 | R | 1253 | 3.6 | 348 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.99 | 2.74 | Tier 1B: High GIDA Priority | 48.04 | 48.04 | 57.24 | 52.64 | D - Other node or line within 3 km | 2.99 | 2.74 | Line: LEMERY TO SAN JUAN CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3831
4 | 832 | 3832 | 1381300016 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Blue Ridge B | 14.6548 | 121.0441 | U | 1215 | 4.42 | 275 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.88 | 0.28 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 40.67 | 40.67 | 64.61 | 52.64 | B - Node 0.5-1 km | 0.88 | 0.28 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 3832
4 | 833 | 3833 | 1380601214 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 213 | 12.2542 | 123.0066 | U | 3037 | 4.4 | 690 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.6 | 46.76 | Tier 1B: High GIDA Priority | 34.44 | 34.44 | 70.84 | 52.64 | F - Nearest node and line over 5 km | 32.6 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3833
4 | 834 | 3834 | 0907313005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Dansal | 7.649 | 123.222 | R | 879 | 3.9 | 225 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.47 | 14.8 | Tier 1B: High GIDA Priority | 33.74 | 33.74 | 71.54 | 52.64 | F - Nearest node and line over 5 km | 20.47 | 14.76 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3834
4 | 835 | 3835 | 1380601042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 42 | 12.7297 | 122.943 | U | 2196 | 4.44 | 495 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.52 | 58.44 | Tier 1B: High GIDA Priority | 29.29 | 29.29 | 76 | 52.64 | F - Nearest node and line over 5 km | 54.52 | 999999 | Node: LOA004-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3835
4 | 836 | 3836 | 1380601264 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 263 | 12.3603 | 121.1391 | U | 1317 | 4.29 | 307 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 1.33 | Tier 1B: High GIDA Priority | 35.9 | 35.9 | 69.35 | 52.63 | D - Other node or line within 3 km | 5.83 | 1.33 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3836
4 | 837 | 3837 | 1903631012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Diragun | 15.6523 | 122.537 | R | 1160 | 5.7 | 204 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.33 | 80.12 | Tier 1B: High GIDA Priority | 33.71 | 33.71 | 71.54 | 52.63 | F - Nearest node and line over 5 km | 81.33 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3837
4 | 838 | 3838 | 0802617044 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Trinidad | 12.1622 | 125.368 | R | 730 | 3.9 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 110.04 | 112.6 | Tier 1B: High GIDA Priority | 32.88 | 32.88 | 72.39 | 52.63 | F - Nearest node and line over 5 km | 110.04 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3838
4 | 839 | 3839 | 1004311013 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Solana | 8.6254 | 124.7646 | R | 4715 | 3.9 | 1209 | 363 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.94 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 69.64 | 69.64 | 35.59 | 52.62 | C - Line within 0.5 km; node over 1 km | 2.94 | 0.09 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3839
4 | 840 | 3840 | 0301409011 | Region III (Central Luzon) | Bulacan | Hagonoy | San Jose | 14.8307 | 120.7326 | R | 4469 | 3.5 | 1277 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.24 | 3.62 | Tier 2B: Moderate GIDA Inclusion | 65.46 | 65.46 | 39.78 | 52.62 | D - Other node or line within 3 km | 2.24 | 8.39 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3840
4 | 841 | 3841 | 0403429021 | Region IV-A (CALABARZON) | Laguna | Siniloan | Salubungan | 14.4626 | 121.4598 | R | 2134 | 3.3 | 647 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.19 | 3.2 | Tier 2B: Moderate GIDA Inclusion | 55.99 | 55.99 | 49.26 | 52.62 | E - Nearest node or line 3-5 km | 3.19 | 3.2 | Node: SNL001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3841
4 | 842 | 3842 | 1204701005 | Region XII (SOCCSKSARGEN) | Cotabato | Alamada | Guiling | 7.476 | 124.6609 | U | 4968 | 3.8 | 1307 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.61 | 17.76 | Tier 1B: High GIDA Priority | 45.6 | 45.6 | 59.64 | 52.62 | F - Nearest node and line over 5 km | 30.61 | 17.72 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3842
4 | 843 | 3843 | 1403211005 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Kinama | 17.5783 | 121.516 | R | 1011 | 3.6 | 281 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.29 | 8.82 | Tier 1B: High GIDA Priority | 45.19 | 45.19 | 60.06 | 52.62 | F - Nearest node and line over 5 km | 10.29 | 8.74 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3843
4 | 844 | 3844 | 0305409021 | Region III (Central Luzon) | Pampanga | Mabalacat City | San Francisco | 15.2165 | 120.5788 | U | 15556 | 4 | 3889 | 1167 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.78 | 0.2 | Tier 2A: High Commercial ROI | 70.11 | 70.11 | 35.11 | 52.61 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.19 | Line: PIPE HH1-HH38 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3844
4 | 845 | 3845 | 0403428020 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Santo Domingo | 14.2289 | 121.048 | U | 7523 | 3.3 | 2280 | 684 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 63.85 | 63.85 | 41.37 | 52.61 | C - Line within 0.5 km; node over 1 km | 2.59 | 0.27 | Line: TGY001 TO CLB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3845
4 | 846 | 3846 | 1408102003 | Cordillera Administrative Region (CAR) | Apayao | Conner | Caglayan | 17.7953 | 121.3232 | R | 2435 | 4.2 | 580 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 62.85 | 62.85 | 42.37 | 52.61 | A - Node within 0.5 km | 0.21 | 0.03 | Line: Tabuk-Conner | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3846
4 | 847 | 3847 | 1705302002 | MIMAROPA Region | Palawan | Agutaya | Algeciras | 11.4186 | 120.812 | R | 5867 | 3.9 | 1504 | 451 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 89.47 | 104.8 | Tier 2B: Moderate GIDA Inclusion | 57.07 | 57.07 | 48.15 | 52.61 | F - Nearest node and line over 5 km | 89.47 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3847
4 | 848 | 3848 | 0405813004 | Region IV-A (CALABARZON) | Rizal | Taytay | San Juan | 14.5443 | 121.1201 | U | 122533 | 3.6 | 34037 | 10211 | Band n50 (1.5 GHz, 100 MHz TDD) | 11 | 1 | 1.58 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 50.61 | 50.61 | 54.6 | 52.61 | C - Line within 0.5 km; node over 1 km | 1.58 | 0.4 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3848
4 | 849 | 3849 | 1381300120 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Tandang Sora | 14.6784 | 121.0352 | U | 86005 | 3.43 | 25079 | 7524 | Band n50 (1.5 GHz, 100 MHz TDD) | 8 | 1 | 0.58 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 48.11 | 48.11 | 57.12 | 52.61 | B - Node 0.5-1 km | 0.58 | 0.34 | Line: UG 144C | Survey short node lateral; confirm port/fiber capacity, access and route. | 3849
4 | 850 | 3850 | 1380614099 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 754 | 14.1327 | 122.0006 | U | 2595 | 3.65 | 710 | 213 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.76 | 16.7 | Tier 1B: High GIDA Priority | 34.96 | 34.96 | 70.26 | 52.61 | F - Nearest node and line over 5 km | 16.76 | 16.68 | Line: LBQ001 TO GCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3850
4 | 851 | 3851 | 1380601026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 26 | 12.1109 | 122.8017 | U | 2340 | 4.03 | 580 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.85 | 38.24 | Tier 1B: High GIDA Priority | 31.56 | 31.56 | 73.66 | 52.61 | F - Nearest node and line over 5 km | 47.85 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3851
4 | 852 | 3852 | 1705320007 | MIMAROPA Region | Palawan | Taytay | Busy Bees | 10.824 | 119.497 | R | 1590 | 3.9 | 408 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 57.03 | 57.03 | 48.16 | 52.6 | D - Other node or line within 3 km | 1.08 | 0.73 | Line: TAYTAY - PUERTO PRINCESA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3852
4 | 853 | 3853 | 1001313010 | Region X (Northern Mindanao) | Bukidnon | Malitbog | Silo-o | 8.4942 | 124.9644 | R | 2870 | 3.8 | 755 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.71 | 11.91 | Tier 2B: Moderate GIDA Inclusion | 49.92 | 49.92 | 55.28 | 52.6 | F - Nearest node and line over 5 km | 14.71 | 11.9 | Line: CAGAYAN DE ORO - MALAYBALAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3853
4 | 854 | 3854 | 0401029028 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 4 | 13.9075 | 120.9495 | R | 310 | 3.6 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 2.53 | Tier 1B: High GIDA Priority | 42.72 | 42.72 | 62.47 | 52.6 | D - Other node or line within 3 km | 2.49 | 2.51 | Node: SNB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3854
4 | 855 | 3855 | 1906614030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Sayli | 17.2562 | 122.2231 | R | 1048 | 6 | 175 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.04 | 33.76 | Tier 1B: High GIDA Priority | 33.67 | 33.67 | 71.54 | 52.6 | F - Nearest node and line over 5 km | 29.04 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3855
4 | 856 | 3856 | 0907313019 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Pantad | 7.6603 | 123.1676 | R | 428 | 3.9 | 110 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.61 | 11.15 | Tier 1B: High GIDA Priority | 33.65 | 33.65 | 71.55 | 52.6 | F - Nearest node and line over 5 km | 14.61 | 11.14 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3856
4 | 857 | 3857 | 1206312024 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Cannery Site | 6.2443 | 125.0886 | U | 25412 | 3.6 | 7059 | 2118 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 4.06 | 4.33 | Tier 2B: Moderate GIDA Inclusion | 64.84 | 64.84 | 40.35 | 52.59 | E - Nearest node or line 3-5 km | 4.06 | 4.33 | Node: PMK001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3857
4 | 858 | 3858 | 0305411020 | Region III (Central Luzon) | Pampanga | Magalang | Santa Cruz | 15.2103 | 120.6621 | U | 7765 | 4 | 1941 | 582 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 63.46 | 63.46 | 41.73 | 52.59 | C - Line within 0.5 km; node over 1 km | 2.26 | 0.05 | Line: Path Measure | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3858
4 | 859 | 3859 | 0203129002 | Region II (Cagayan Valley) | Isabela | San Isidro | Cebu | 16.7542 | 121.5943 | R | 2992 | 3.8 | 787 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.36 | 6.5 | Tier 2B: Moderate GIDA Inclusion | 63.17 | 63.17 | 42.01 | 52.59 | E - Nearest node or line 3-5 km | 4.36 | 6.5 | Node: ISI001 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3859
4 | 860 | 3860 | 1907002019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Montay Montay | 14.51 | 121.6808 | R | 1812 | 5.8 | 312 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.62 | 25 | Tier 1B: High GIDA Priority | 43.7 | 43.7 | 61.47 | 52.59 | F - Nearest node and line over 5 km | 5.62 | 25 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3860
4 | 861 | 3861 | 1907001012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Karaha | 17.2557 | 122.2297 | R | 1736 | 5.8 | 299 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 32.44 | 32.44 | 72.74 | 52.59 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3861
4 | 862 | 3862 | 0702223044 | Region VII (Central Visayas) | Cebu | Danao City | Tuburan Sur | 10.5136 | 124.0171 | U | 8162 | 3.8 | 2148 | 644 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.96 | Tier 2B: Moderate GIDA Inclusion | 68.1 | 68.1 | 37.06 | 52.58 | D - Other node or line within 3 km | 1.36 | 0.92 | Line: 9.3km FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3862
4 | 863 | 3863 | 0304915008 | Region III (Central Luzon) | Nueva Ecija | Llanera | General Ricarte | 15.6289 | 121.0117 | R | 2725 | 3.5 | 779 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.18 | 0.92 | Tier 2B: Moderate GIDA Inclusion | 66.64 | 66.64 | 38.52 | 52.58 | D - Other node or line within 3 km | 4.18 | 0.92 | Line: Proposed AE F1-6 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3863
4 | 864 | 3864 | 0203137005 | Region II (Cagayan Valley) | Isabela | Tumauini | Arcon | 17.2754 | 121.8238 | R | 2264 | 3.8 | 596 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 61.58 | 61.58 | 43.58 | 52.58 | B - Node 0.5-1 km | 0.95 | 0.12 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3864
4 | 865 | 3865 | 0405630011 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Ikirin | 13.9722 | 121.7016 | U | 3271 | 3.8 | 861 | 258 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.12 | 0.83 | Tier 2B: Moderate GIDA Inclusion | 59.22 | 59.22 | 45.95 | 52.58 | D - Other node or line within 3 km | 2.12 | 0.81 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3865
4 | 866 | 3866 | 0604528025 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 9 | 10.7178 | 123.0143 | R | 996 | 3.7 | 269 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.69 | 2.03 | Tier 1B: High GIDA Priority | 46.32 | 46.32 | 58.84 | 52.58 | D - Other node or line within 3 km | 5.69 | 2.03 | Line: TALISAY - BACOLOD (REDUNDANCY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3866
4 | 867 | 3867 | 1380606016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 410 | 13.3506 | 122.9401 | U | 2565 | 3.7 | 694 | 208 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.9 | 19.85 | Tier 1B: High GIDA Priority | 34.53 | 34.53 | 70.64 | 52.58 | F - Nearest node and line over 5 km | 19.9 | 19.85 | Line: PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3867
4 | 868 | 3868 | 1903638042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Tagoloan Poblacion | 17.2513 | 122.2037 | R | 928 | 5.7 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.14 | 31.63 | Tier 1B: High GIDA Priority | 33.61 | 33.61 | 71.55 | 52.58 | F - Nearest node and line over 5 km | 27.14 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3868
4 | 869 | 3869 | 1907007012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Lahay-lahay | 14.4209 | 121.7894 | R | 979 | 5.8 | 169 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.69 | 33.69 | Tier 1B: High GIDA Priority | 30.73 | 30.73 | 74.44 | 52.58 | F - Nearest node and line over 5 km | 19.69 | 33.69 | Node: RLQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3869
4 | 870 | 3870 | 0604532004 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Igmaya-an | 10.5582 | 123.1957 | R | 4474 | 3.7 | 1209 | 363 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.27 | Tier 2A: High Commercial ROI | 79.14 | 79.14 | 26 | 52.57 | B - Node 0.5-1 km | 0.62 | 0.23 | Line: SAN CARLOS CITY - TALISAY CITY | Survey short node lateral; confirm port/fiber capacity, access and route. | 3870
4 | 871 | 3871 | 0305406026 | Region III (Central Luzon) | Pampanga | Floridablanca | San Jose | 14.9853 | 120.511 | U | 9350 | 4 | 2338 | 701 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 67.72 | 67.72 | 37.41 | 52.57 | B - Node 0.5-1 km | 0.51 | 0.31 | Line: 48 CORE (4X12) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3871
4 | 872 | 3872 | 0102906041 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Pedro | 17.178 | 120.4715 | R | 731 | 3.8 | 192 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.06 | 2.82 | Tier 1B: High GIDA Priority | 43.98 | 43.98 | 61.17 | 52.57 | D - Other node or line within 3 km | 3.06 | 2.82 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3872
4 | 873 | 3873 | 0205005025 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Salvacion | 16.4791 | 121.1499 | R | 4495 | 3.8 | 1183 | 355 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.98 | Tier 2A: High Commercial ROI | 70.74 | 70.74 | 34.39 | 52.56 | B - Node 0.5-1 km | 1 | 0.98 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3873
4 | 874 | 3874 | 0105521001 | Region I (Ilocos Region) | Pangasinan | Labrador | Bolo | 15.9855 | 120.1835 | R | 4652 | 3.6 | 1292 | 388 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.71 | 1.52 | Tier 2B: Moderate GIDA Inclusion | 69.82 | 69.82 | 35.31 | 52.56 | D - Other node or line within 3 km | 6.71 | 1.52 | Line: LABRADOR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3874
4 | 875 | 3875 | 1401113011 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Tadiangan | 16.426 | 120.5423 | U | 8585 | 3.5 | 2453 | 736 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.12 | 0.84 | Tier 2B: Moderate GIDA Inclusion | 65.63 | 65.63 | 39.5 | 52.56 | D - Other node or line within 3 km | 2.12 | 0.83 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3875
4 | 876 | 3876 | 0300801007 | Region III (Central Luzon) | Bataan | Abucay | Mabatang | 14.7426 | 120.5364 | U | 10080 | 3.6 | 2800 | 840 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.43 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 62.49 | 62.49 | 42.62 | 52.56 | C - Line within 0.5 km; node over 1 km | 6.43 | 0.21 | Line: 48 CORE 4X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3876
4 | 877 | 3877 | 0506203065 | Region V (Bicol Region) | Sorsogon | Bulan | Zone VIII Pob. | 12.6689 | 123.8811 | R | 2226 | 4 | 556 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 61.78 | 61.78 | 43.35 | 52.56 | B - Node 0.5-1 km | 0.9 | 0.3 | Line: 14,546 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3877
4 | 878 | 3878 | 1381300122 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Teachers Village East | 14.7414 | 121.0492 | U | 3067 | 4.45 | 689 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.7 | 0.61 | Tier 2B: Moderate GIDA Inclusion | 50.12 | 50.12 | 55.01 | 52.56 | D - Other node or line within 3 km | 1.7 | 0.54 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3878
4 | 879 | 3879 | 0504101033 | Region V (Bicol Region) | Masbate | Aroroy | San Agustin | 12.4781 | 123.3469 | R | 1824 | 4.1 | 445 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.68 | 10.52 | Tier 2B: Moderate GIDA Inclusion | 49.87 | 49.87 | 55.25 | 52.56 | F - Nearest node and line over 5 km | 6.68 | 29.14 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3879
4 | 880 | 3880 | 0501711004 | Region V (Bicol Region) | Camarines Sur | Caramoan | Bahay | 13.8104 | 123.8091 | R | 546 | 4.2 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.11 | 36.65 | Tier 1B: High GIDA Priority | 43.23 | 43.23 | 61.88 | 52.56 | F - Nearest node and line over 5 km | 7.11 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3880
4 | 881 | 3881 | 0403406002 | Region IV-A (CALABARZON) | Laguna | Calauan | Bangyas | 14.174 | 121.3169 | R | 3213 | 3.3 | 974 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.13 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 66.65 | 66.65 | 38.45 | 52.55 | C - Line within 0.5 km; node over 1 km | 3.13 | 0.34 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3881
4 | 882 | 3882 | 0301413033 | Region III (Central Luzon) | Bulacan | Norzagaray | Friendship Village Resources | 14.8629 | 121.0455 | U | 14851 | 3.5 | 4243 | 1273 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.48 | 3.62 | Tier 2B: Moderate GIDA Inclusion | 66.64 | 66.64 | 38.47 | 52.55 | D - Other node or line within 3 km | 2.48 | 4.75 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3882
4 | 883 | 3883 | 0403430004 | Region IV-A (CALABARZON) | Laguna | Victoria | Nanhaya | 14.2308 | 121.33 | U | 7975 | 3.3 | 2417 | 725 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.14 | 3.31 | Tier 2B: Moderate GIDA Inclusion | 64.58 | 64.58 | 40.52 | 52.55 | E - Nearest node or line 3-5 km | 3.14 | 3.31 | Node: VTL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3883
4 | 884 | 3884 | 1600301014 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Panaytay | 8.704 | 125.7952 | R | 625 | 3.9 | 160 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.38 | 0.68 | Tier 1B: High GIDA Priority | 47.01 | 47.01 | 58.09 | 52.55 | D - Other node or line within 3 km | 4.38 | 0.66 | Line: TRENTO - BUENAVISTA CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3884
4 | 885 | 3885 | 1381100160 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 160 | 14.3407 | 120.9672 | U | 1101 | 3.27 | 337 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.84 | 4.58 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.72 | 35.72 | 69.37 | 52.55 | D - Other node or line within 3 km | 2.84 | 4.5 | Node: DMC005 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3885
4 | 886 | 3886 | 0603020021 | Region VI (Western Visayas) | Iloilo | Guimbal | Igcocolo | 10.6943 | 122.3191 | R | 3287 | 3.8 | 865 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.99 | 3.26 | Tier 2B: Moderate GIDA Inclusion | 63.7 | 63.7 | 41.37 | 52.54 | E - Nearest node or line 3-5 km | 6.99 | 3.25 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3886
4 | 887 | 3887 | 1906607016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Kan-Sipat | 17.2556 | 122.2296 | R | 1021 | 6 | 170 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.4 | Tier 1B: High GIDA Priority | 33.54 | 33.54 | 71.54 | 52.54 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3887
4 | 888 | 3888 | 1906610001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Andalan | 17.2519 | 122.2331 | R | 1020 | 6 | 170 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.63 | Tier 1B: High GIDA Priority | 33.53 | 33.53 | 71.54 | 52.54 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3888
4 | 889 | 3889 | 1401103005 | Cordillera Administrative Region (CAR) | Benguet | Bakun | Gambang | 16.7419 | 120.7976 | R | 3886 | 3.5 | 1110 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 68.11 | 68.11 | 36.96 | 52.53 | C - Line within 0.5 km; node over 1 km | 2.89 | 0.12 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3889
4 | 890 | 3890 | 0603003002 | Region VI (Western Visayas) | Iloilo | Anilao | Badiang | 10.9671 | 122.7132 | R | 2817 | 3.8 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.7 | 1.74 | Tier 2B: Moderate GIDA Inclusion | 63.99 | 63.99 | 41.08 | 52.53 | D - Other node or line within 3 km | 7.7 | 1.64 | Line: ANILAO RISER 2-ANILAO BASEPAD | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3890
4 | 891 | 3891 | 0301414005 | Region III (Central Luzon) | Bulacan | Obando | Salambao | 14.714 | 120.9069 | R | 1646 | 3.5 | 470 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.24 | 5 | Tier 2B: Moderate GIDA Inclusion | 51.22 | 51.22 | 53.84 | 52.53 | E - Nearest node or line 3-5 km | 3.24 | 5 | Node: OBB001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3891
4 | 892 | 3892 | 1606812006 | Region XIII (Caraga) | Surigao del Sur | Lingig | Mahayahay | 8.0884 | 126.3919 | R | 2595 | 4.1 | 633 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.53 | 35.8 | Tier 1B: High GIDA Priority | 42.85 | 42.85 | 62.21 | 52.53 | F - Nearest node and line over 5 km | 36.53 | 35.76 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3892
4 | 893 | 3893 | 1608507004 | Region XIII (Caraga) | Dinagat Islands | Tubajon | Navarro | 10.2899 | 125.5899 | R | 436 | 3.8 | 115 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 56.77 | 56.77 | Tier 1B: High GIDA Priority | 35.2 | 35.2 | 69.86 | 52.53 | F - Nearest node and line over 5 km | 56.77 | 999999 | Node: SRO001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3893
4 | 894 | 3894 | 0203111012 | Region II (Cagayan Valley) | Isabela | Divilacan | Dibulos | 17.307 | 122.3277 | R | 219 | 3.8 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.25 | 46.08 | Tier 1B: High GIDA Priority | 28.65 | 28.65 | 76.41 | 52.53 | F - Nearest node and line over 5 km | 41.25 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3894
4 | 895 | 3895 | 1003511003 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Daan Campo | 8.0271 | 123.8965 | R | 780 | 4.2 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.86 | 8.66 | Tier 1B: High GIDA Priority | 43.41 | 43.41 | 61.63 | 52.52 | F - Nearest node and line over 5 km | 10.86 | 8.66 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3895
4 | 896 | 3896 | 1206502016 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Columbio | Lomoyon | 6.7092 | 124.9355 | R | 1861 | 3.8 | 490 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.4 | 8.39 | Tier 1B: High GIDA Priority | 40.4 | 40.4 | 64.63 | 52.52 | F - Nearest node and line over 5 km | 24.4 | 8.38 | Line: QUIRINO - KIDAPAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3896
4 | 897 | 3897 | 1380601233 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 232 | 13.4262 | 120.894 | U | 1871 | 4.02 | 465 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.6 | 7.97 | Tier 1B: High GIDA Priority | 34.65 | 34.65 | 70.39 | 52.52 | F - Nearest node and line over 5 km | 8.6 | 7.87 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3897
4 | 898 | 3898 | 0305409013 | Region III (Central Luzon) | Pampanga | Mabalacat City | Macapagal Village | 15.2108 | 120.5376 | R | 4458 | 4 | 1114 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.2 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 67.22 | 67.22 | 37.79 | 52.51 | D - Other node or line within 3 km | 3.2 | 0.6 | Line: PIPE HH52-HH59 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3898
4 | 899 | 3899 | 0702218009 | Region VII (Central Visayas) | Cebu | Compostela | Estaca | 10.4375 | 124.0071 | U | 7394 | 3.8 | 1946 | 584 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.72 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 67 | 67 | 38.03 | 52.51 | C - Line within 0.5 km; node over 1 km | 1.72 | 0.18 | Line: 6.035km FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3899
4 | 900 | 3900 | 0304928001 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Cojuangco | 15.4891 | 120.971 | U | 2838 | 3.5 | 811 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.34 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 59.11 | 59.11 | 45.91 | 52.51 | C - Line within 0.5 km; node over 1 km | 1.34 | 0.38 | Line: MULTINET - SANTA ROSA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3900
4 | 901 | 3901 | 0405623006 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 3 | 14.1101 | 121.56 | R | 1547 | 3.8 | 407 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.46 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 57.32 | 57.32 | 47.71 | 52.51 | A - Node within 0.5 km | 0.46 | 0.2 | Line: LILIW TO LUCENA AE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3901
4 | 902 | 3902 | 0601903017 | Region VI (Western Visayas) | Capiz | Dumalag | Santa Teresa | 11.2908 | 122.5944 | R | 801 | 3.8 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.74 | 1.33 | Tier 2B: Moderate GIDA Inclusion | 49.68 | 49.68 | 55.33 | 52.51 | D - Other node or line within 3 km | 9.74 | 1.3 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3902
4 | 903 | 3903 | 0401005056 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 10 | 13.7152 | 121.076 | U | 271 | 3.6 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.45 | 4.83 | Tier 1B: High GIDA Priority | 34.06 | 34.06 | 70.95 | 52.51 | E - Nearest node or line 3-5 km | 3.45 | 4.82 | Node: BCY004 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3903
4 | 904 | 3904 | 0604530013 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Palaka | 10.404 | 122.8763 | R | 3358 | 3.7 | 908 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.58 | 1.86 | Tier 2B: Moderate GIDA Inclusion | 70.22 | 70.22 | 34.78 | 52.5 | D - Other node or line within 3 km | 3.58 | 1.84 | Line: TALISAY CITY - KABANGKALAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3904
4 | 905 | 3905 | 0305403020 | Region III (Central Luzon) | Pampanga | Arayat | San Agustin Norte | 15.1636 | 120.7791 | R | 3848 | 4 | 962 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.5 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 37.36 | 52.5 | C - Line within 0.5 km; node over 1 km | 2.5 | 0.05 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3905
4 | 906 | 3906 | 0405647037 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Lalo | 14.0406 | 121.5712 | R | 4149 | 3.8 | 1092 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.05 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 67.12 | 67.12 | 37.88 | 52.5 | D - Other node or line within 3 km | 3.05 | 0.53 | Line: LBQ001 TO GCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3906
4 | 907 | 3907 | 0405630018 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Pinagbayanan | 13.977 | 121.7124 | R | 4405 | 3.8 | 1159 | 348 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.34 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 66.99 | 66.99 | 38.02 | 52.5 | D - Other node or line within 3 km | 3.34 | 0.52 | Line: LBQ001 TO GCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3907
4 | 908 | 3908 | 0304913020 | Region III (Central Luzon) | Nueva Ecija | Laur | San Juan | 15.5705 | 121.2031 | R | 2654 | 3.5 | 758 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.48 | 7.42 | Tier 2B: Moderate GIDA Inclusion | 63.33 | 63.33 | 41.66 | 52.5 | A - Node within 0.5 km | 0.48 | 7.33 | Node: LRN001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3908
4 | 909 | 3909 | 1403211002 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Calaocan | 17.5023 | 121.6029 | R | 1439 | 3.6 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 61 | 61 | 44 | 52.5 | C - Line within 0.5 km; node over 1 km | 1 | 0.09 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3909
4 | 910 | 3910 | 0405630020 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 2 Daungan | 13.9707 | 121.6914 | R | 2040 | 3.8 | 537 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.02 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 59.74 | 59.74 | 45.25 | 52.5 | C - Line within 0.5 km; node over 1 km | 1.02 | 0.28 | Line: LBQ001 TO GCQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3910
4 | 911 | 3911 | 0405622065 | Region IV-A (CALABARZON) | Quezon | Lopez | San Francisco B | 13.7668 | 122.3084 | R | 2761 | 3.8 | 727 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.2 | 8.61 | Tier 2B: Moderate GIDA Inclusion | 54.61 | 54.61 | 50.39 | 52.5 | F - Nearest node and line over 5 km | 8.2 | 8.6 | Node: CTQ004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3911
4 | 912 | 3912 | 0203123015 | Region II (Cagayan Valley) | Isabela | Quirino | Santiago | 17.1859 | 121.7487 | R | 1635 | 3.9 | 419 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.73 | 7.92 | Tier 2B: Moderate GIDA Inclusion | 52.37 | 52.37 | 52.63 | 52.5 | F - Nearest node and line over 5 km | 5.73 | 7.65 | Node: QRI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3912
4 | 913 | 3913 | 1381300133 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | West Triangle | 14.7455 | 121.0807 | U | 2486 | 3.63 | 685 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 49.17 | 49.17 | 55.82 | 52.5 | C - Line within 0.5 km; node over 1 km | 2.26 | 0.1 | Line: UG 144C via Y-Duct | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3913
4 | 914 | 3914 | 1402708010 | Cordillera Administrative Region (CAR) | Ifugao | Aguinaldo | Majlong | 16.9639 | 121.3138 | R | 532 | 3.9 | 136 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 27.35 | Tier 1B: High GIDA Priority | 43.93 | 43.93 | 61.07 | 52.5 | D - Other node or line within 3 km | 2.32 | 27.27 | Node: AOF001-PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3914
4 | 915 | 3915 | 1380612005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 837 | 12.8213 | 120.4023 | U | 3188 | 4.32 | 738 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 88.9 | 86.97 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 69.33 | 52.5 | F - Nearest node and line over 5 km | 88.9 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3915
4 | 916 | 3916 | 1906608001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Alu Bunah | 17.2554 | 122.2294 | R | 1002 | 6 | 167 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.37 | Tier 1B: High GIDA Priority | 33.45 | 33.45 | 71.54 | 52.5 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3916
4 | 917 | 3917 | 0401005060 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 14 | 13.7284 | 121.072 | U | 240 | 3.6 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.11 | 3.3 | Tier 1B: High GIDA Priority | 33.41 | 33.41 | 71.6 | 52.5 | E - Nearest node or line 3-5 km | 4.11 | 3.28 | Line: AE TO ELIMINATE COMMON 96C | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3917
4 | 918 | 3918 | 1380601161 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 161 | 13.3117 | 121.3308 | U | 876 | 4.36 | 201 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.31 | 8.75 | Tier 1B: High GIDA Priority | 31.59 | 31.59 | 73.41 | 52.5 | E - Nearest node or line 3-5 km | 3.31 | 8.71 | Node: NJM001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3918
4 | 919 | 3919 | 0806408007 | Region VIII (Eastern Visayas) | Southern Leyte | Macrohon | Ichon | 10.1104 | 124.9005 | R | 3843 | 4.1 | 937 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 0.13 | Tier 2A: High Commercial ROI | 76.14 | 76.14 | 28.83 | 52.49 | C - Line within 0.5 km; node over 1 km | 8.19 | 0.31 | Line: INOPACAN (BAYBAY) - MAASIN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3919
4 | 920 | 3920 | 0304908015 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Norte | 15.2853 | 120.9476 | U | 6716 | 3.5 | 1919 | 576 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.03 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 67.51 | 67.51 | 37.47 | 52.49 | B - Node 0.5-1 km | 0.67 | 0.03 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 3920
4 | 921 | 3921 | 0306902007 | Region III (Central Luzon) | Tarlac | Bamban | Lourdes | 15.2796 | 120.526 | U | 6958 | 3.9 | 1784 | 535 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 1.88 | Tier 2B: Moderate GIDA Inclusion | 64.81 | 64.81 | 40.17 | 52.49 | D - Other node or line within 3 km | 1.14 | 1.51 | Node: BBT002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3921
4 | 922 | 3922 | 0403410033 | Region IV-A (CALABARZON) | Laguna | Liliw | Palayan | 14.1267 | 121.4454 | R | 1153 | 3.3 | 349 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.46 | 0.73 | Tier 2B: Moderate GIDA Inclusion | 58.36 | 58.36 | 46.62 | 52.49 | D - Other node or line within 3 km | 1.46 | 0.72 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3922
4 | 923 | 3923 | 0702211021 | Region VII (Central Visayas) | Cebu | City of Bogo | Pandan | 11.0336 | 123.9908 | R | 1919 | 3.8 | 505 | 152 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.36 | 1.1 | Tier 2B: Moderate GIDA Inclusion | 58.24 | 58.24 | 46.74 | 52.49 | D - Other node or line within 3 km | 2.36 | 1.1 | Line: BOGO - DANAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3923
4 | 924 | 3924 | 0506213011 | Region V (Bicol Region) | Sorsogon | Pilar | Calongay | 12.9409 | 123.6719 | R | 1958 | 4 | 490 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 9.35 | Tier 2B: Moderate GIDA Inclusion | 56.63 | 56.63 | 48.35 | 52.49 | B - Node 0.5-1 km | 0.98 | 9.31 | Node: PRS001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3924
4 | 925 | 3925 | 1001304006 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Embayao | 7.753 | 124.8852 | R | 1161 | 3.8 | 306 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.92 | 13.02 | Tier 1B: High GIDA Priority | 45.03 | 45.03 | 59.95 | 52.49 | F - Nearest node and line over 5 km | 7.92 | 12.88 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3925
4 | 926 | 3926 | 1408102018 | Cordillera Administrative Region (CAR) | Apayao | Conner | Banban | 17.7043 | 121.3923 | R | 1199 | 4.2 | 285 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.6 | 3.68 | Tier 1B: High GIDA Priority | 44.31 | 44.31 | 60.66 | 52.49 | E - Nearest node or line 3-5 km | 6.6 | 3.65 | Line: Tabuk-Conner | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3926
4 | 927 | 3927 | 1400109001 | Cordillera Administrative Region (CAR) | Abra | Lacub | Bacag | 17.6955 | 120.9117 | R | 273 | 3.8 | 72 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.25 | 26.08 | Tier 1B: High GIDA Priority | 34.67 | 34.67 | 70.31 | 52.49 | F - Nearest node and line over 5 km | 26.25 | 26.07 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3927
4 | 928 | 3928 | 0908301014 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Alicia | Litayon | 7.4599 | 122.9671 | R | 1165 | 4.2 | 277 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.54 | 20.55 | Tier 1B: High GIDA Priority | 33.42 | 33.42 | 71.55 | 52.49 | F - Nearest node and line over 5 km | 31.54 | 20.55 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3928
4 | 929 | 3929 | 1705205029 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Lazareto | 13.4283 | 121.1996 | R | 4858 | 3.9 | 1246 | 374 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 6.85 | Tier 2B: Moderate GIDA Inclusion | 69.29 | 69.29 | 35.67 | 52.48 | B - Node 0.5-1 km | 0.73 | 6.84 | Node: CLM002 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 3929
4 | 930 | 3930 | 0403404017 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Uno | 14.2504 | 121.3124 | U | 4045 | 3.3 | 1226 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.95 | 5.94 | Tier 2B: Moderate GIDA Inclusion | 54.19 | 54.19 | 50.77 | 52.48 | F - Nearest node and line over 5 km | 5.95 | 5.87 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3930
4 | 931 | 3931 | 0102820006 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Cayetano | 18.1473 | 120.5956 | R | 860 | 3.7 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.58 | 1.23 | Tier 2B: Moderate GIDA Inclusion | 49.17 | 49.17 | 55.8 | 52.48 | D - Other node or line within 3 km | 2.58 | 1.21 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3931
4 | 932 | 3932 | 1381600011 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Gen. T. De Leon | 14.712 | 120.9845 | U | 99317 | 3.5 | 28415 | 8524 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 1.4 | 0.19 | Tier 1B: High GIDA Priority | 46.56 | 46.56 | 58.4 | 52.48 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.07 | Line: Existing MTF | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3932
4 | 933 | 3933 | 1380611039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 824 | 13.4491 | 121.1899 | U | 1378 | 4.02 | 343 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.91 | 8.48 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 35.82 | 35.82 | 69.15 | 52.48 | D - Other node or line within 3 km | 2.91 | 8.46 | Node: CLM002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3933
4 | 934 | 3934 | 1380601150 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 150 | 14.0388 | 121.5104 | U | 1922 | 4.11 | 468 | 140 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.7 | 6.55 | Tier 1B: High GIDA Priority | 34.53 | 34.53 | 70.43 | 52.48 | F - Nearest node and line over 5 km | 8.7 | 6.55 | Line: LILIW TO LUCENA AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3934
4 | 935 | 3935 | 1003515020 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Panganapan | 7.7863 | 123.8855 | R | 663 | 4.2 | 158 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.08 | 17.69 | Tier 1B: High GIDA Priority | 31.63 | 31.63 | 73.33 | 52.48 | F - Nearest node and line over 5 km | 30.08 | 17.64 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3935
4 | 936 | 3936 | 0403406016 | Region IV-A (CALABARZON) | Laguna | Calauan | San Isidro | 14.1555 | 121.3158 | R | 3915 | 3.3 | 1186 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 0.69 | Tier 2A: High Commercial ROI | 70.38 | 70.38 | 34.56 | 52.47 | D - Other node or line within 3 km | 1.08 | 0.69 | Line: AE SPO001 TO LBL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3936
4 | 937 | 3937 | 0702216016 | Region VII (Central Visayas) | Cebu | Catmon | Tabili | 10.6957 | 123.9619 | R | 859 | 3.8 | 226 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.69 | 5.45 | Tier 2B: Moderate GIDA Inclusion | 49.85 | 49.85 | 55.09 | 52.47 | F - Nearest node and line over 5 km | 5.69 | 5.45 | Line: BOGO - DANAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3937
4 | 938 | 3938 | 0102916006 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Boguibog | 17.0767 | 120.5336 | R | 660 | 3.8 | 174 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.14 | 8.05 | Tier 1B: High GIDA Priority | 44.28 | 44.28 | 60.65 | 52.47 | F - Nearest node and line over 5 km | 8.14 | 8.05 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3938
4 | 939 | 3939 | 1380611007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 673 | 12.2301 | 120.6198 | U | 2539 | 3.32 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 47.6 | 49.82 | Tier 1B: High GIDA Priority | 36.45 | 36.45 | 68.5 | 52.47 | F - Nearest node and line over 5 km | 47.6 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3939
4 | 940 | 3940 | 1906615001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Bakkaan | 17.2557 | 122.2297 | R | 1845 | 6 | 308 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 32.61 | 32.61 | 72.33 | 52.47 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3940
4 | 941 | 3941 | 0304922001 | Region III (Central Luzon) | Nueva Ecija | Quezon | Bertese | 15.5748 | 120.8151 | R | 4278 | 3.8 | 1126 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 1.52 | Tier 2A: High Commercial ROI | 73.55 | 73.55 | 31.37 | 52.46 | D - Other node or line within 3 km | 1.88 | 1.52 | Line: 38,161m. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3941
4 | 942 | 3942 | 0604528007 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Concepcion | 10.7701 | 122.9636 | U | 12720 | 3.7 | 3438 | 1031 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.98 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 68.98 | 68.98 | 35.94 | 52.46 | C - Line within 0.5 km; node over 1 km | 3.3 | 0.49 | Line: TALISAY - VICTORIAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3942
4 | 943 | 3943 | 0403405058 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Turbina | 14.1832 | 121.1343 | U | 6871 | 3.3 | 2082 | 625 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 64.06 | 64.06 | 40.85 | 52.46 | C - Line within 0.5 km; node over 1 km | 2.01 | 0.07 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3943
4 | 944 | 3944 | 0301405013 | Region III (Central Luzon) | Bulacan | Bulacan | Santa Ana | 14.787 | 120.8839 | U | 8360 | 3.5 | 2389 | 717 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 4.19 | Tier 2B: Moderate GIDA Inclusion | 63.06 | 63.06 | 41.87 | 52.46 | D - Other node or line within 3 km | 1.19 | 4.19 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3944
4 | 945 | 3945 | 1401104006 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Karao | 16.5119 | 120.8459 | R | 1141 | 3.5 | 326 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.34 | 5.63 | Tier 2B: Moderate GIDA Inclusion | 51.15 | 51.15 | 53.77 | 52.46 | E - Nearest node or line 3-5 km | 4.34 | 5.55 | Node: BKB001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3945
4 | 946 | 3946 | 1906616002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Panglima Estino | Gata-gata | 17.2556 | 122.2296 | R | 3892 | 6 | 649 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 46.1 | 46.1 | 58.83 | 52.46 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3946
4 | 947 | 3947 | 1903631032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Calumbog | 15.6777 | 122.5658 | R | 1078 | 5.7 | 189 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.3 | 80.24 | Tier 1B: High GIDA Priority | 33.36 | 33.36 | 71.55 | 52.46 | F - Nearest node and line over 5 km | 81.3 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3947
4 | 948 | 3948 | 0301420030 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Yakal | 14.8088 | 121.0518 | R | 3889 | 3.5 | 1111 | 333 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 69.08 | 69.08 | 35.83 | 52.45 | D - Other node or line within 3 km | 1.83 | 1.38 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3948
4 | 949 | 3949 | 0301418006 | Region III (Central Luzon) | Bulacan | Pulilan | Dampol II-A | 14.9057 | 120.816 | U | 5118 | 3.5 | 1462 | 439 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 60.21 | 60.21 | 44.7 | 52.45 | C - Line within 0.5 km; node over 1 km | 3.74 | 0.26 | Line: 24 CORE (3X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3949
4 | 950 | 3950 | 1705320014 | MIMAROPA Region | Palawan | Taytay | Meytegued | 11.0283 | 119.5982 | R | 1165 | 3.9 | 299 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.3 | 24.91 | Tier 1B: High GIDA Priority | 42.85 | 42.85 | 62.05 | 52.45 | F - Nearest node and line over 5 km | 9.3 | 24.76 | Node: TYW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3950
4 | 951 | 3951 | 1380605018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 316 | 12.4882 | 121.437 | U | 856 | 3.42 | 250 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.62 | 1.4 | Tier 1B: High GIDA Priority | 36.07 | 36.07 | 68.83 | 52.45 | D - Other node or line within 3 km | 3.62 | 1.4 | Line: ROXAS - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3951
4 | 952 | 3952 | 0301422032 | Region III (Central Luzon) | Bulacan | San Rafael | Tambubong | 14.9689 | 120.9263 | U | 8068 | 3.5 | 2305 | 692 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.57 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 65.63 | 65.63 | 39.24 | 52.44 | D - Other node or line within 3 km | 1.57 | 1.13 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3952
4 | 953 | 3953 | 0201514019 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Progressive | 18.2863 | 122.0171 | R | 2474 | 3.9 | 634 | 190 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.19 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 59.19 | 59.19 | 45.68 | 52.44 | C - Line within 0.5 km; node over 1 km | 3.19 | 0.11 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3953
4 | 954 | 3954 | 0604528041 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 2 | 10.7438 | 122.9641 | U | 2184 | 3.7 | 590 | 177 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 56.4 | 56.4 | 48.47 | 52.44 | B - Node 0.5-1 km | 0.52 | 0.07 | Line: FH TALISAY, NEGROS OCCIDENTAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 3954
4 | 955 | 3955 | 1003516021 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Pantao Marug | 8.0394 | 124.1809 | R | 1415 | 4.2 | 337 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.79 | 8.65 | Tier 1B: High GIDA Priority | 47.12 | 47.12 | 57.77 | 52.44 | F - Nearest node and line over 5 km | 10.79 | 8.58 | Line: Pantar Done Layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3955
4 | 956 | 3956 | 1400121001 | Cordillera Administrative Region (CAR) | Abra | San Isidro | Cabayogan | 17.4953 | 120.5967 | R | 336 | 3.8 | 88 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.69 | 6.52 | Tier 1B: High GIDA Priority | 44.33 | 44.33 | 60.56 | 52.44 | F - Nearest node and line over 5 km | 7.69 | 6.42 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3956
4 | 957 | 3957 | 1108603001 | Region XI (Davao Region) | Davao Occidental | Malita | Bito | 6.3372 | 125.5957 | R | 2033 | 3.6 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.06 | 32.04 | Tier 1B: High GIDA Priority | 41.33 | 41.33 | 63.55 | 52.44 | F - Nearest node and line over 5 km | 34.06 | 32.04 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3957
4 | 958 | 3958 | 0603043061 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Barangay Zone VI | 10.7785 | 122.5486 | R | 3583 | 3.8 | 943 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 3.71 | Tier 2B: Moderate GIDA Inclusion | 67.28 | 67.28 | 37.59 | 52.43 | B - Node 0.5-1 km | 0.73 | 3.67 | Node: PVI001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3958
4 | 959 | 3959 | 0403429016 | Region IV-A (CALABARZON) | Laguna | Siniloan | Macatad | 14.4528 | 121.4621 | R | 3326 | 3.3 | 1008 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 2.36 | Tier 2B: Moderate GIDA Inclusion | 64.29 | 64.29 | 40.56 | 52.43 | D - Other node or line within 3 km | 2.32 | 2.34 | Node: SNL001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3959
4 | 960 | 3960 | 0401019011 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 6 | 14.0884 | 120.6704 | R | 2744 | 3.6 | 762 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.38 | 0.82 | Tier 2B: Moderate GIDA Inclusion | 61.5 | 61.5 | 43.35 | 52.43 | D - Other node or line within 3 km | 4.38 | 0.82 | Line: NCC001 TO NSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3960
4 | 961 | 3961 | 0402118036 | Region IV-A (CALABARZON) | Cavite | Silang | Barangay V | 14.2206 | 120.9712 | U | 2303 | 3.4 | 677 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.7 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 50.76 | 50.76 | 54.1 | 52.43 | C - Line within 0.5 km; node over 1 km | 5.7 | 0.29 | Line: SILANG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3961
4 | 962 | 3962 | 0403426015 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay II | 14.2775 | 121.4192 | U | 1403 | 3.3 | 425 | 128 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 49.89 | 49.89 | 54.96 | 52.43 | B - Node 0.5-1 km | 0.69 | 0.3 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3962
4 | 963 | 3963 | 0803751020 | Region VIII (Eastern Visayas) | Leyte | Villaba | New Balanac | 11.1831 | 124.4857 | R | 721 | 3.8 | 190 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 8.1 | Tier 1B: High GIDA Priority | 45.23 | 45.23 | 59.63 | 52.43 | E - Nearest node or line 3-5 km | 4.59 | 8.1 | Node: MOL001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3963
4 | 964 | 3964 | 1380601192 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 192 | 13.7945 | 121.2322 | U | 1771 | 4.23 | 419 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.56 | 4.74 | Tier 1B: High GIDA Priority | 36.18 | 36.18 | 68.68 | 52.43 | E - Nearest node or line 3-5 km | 4.56 | 4.73 | Node: TAB002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3964
4 | 965 | 3965 | 1102509020 | Region XI (Davao Region) | Davao Oriental | City of Mati | Matiao | 6.9396 | 126.2324 | U | 16620 | 3.6 | 4617 | 1385 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 3.35 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 71 | 71 | 33.84 | 52.42 | D - Other node or line within 3 km | 3.35 | 0.56 | Line: PANTUKAN - MATI SEGMENT 5 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3965
4 | 966 | 3966 | 0702234003 | Region VII (Central Visayas) | Cebu | City of Naga | Balirong | 10.2566 | 123.7109 | U | 5268 | 3.8 | 1386 | 416 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 68.66 | 68.66 | 36.18 | 52.42 | A - Node within 0.5 km | 0.12 | 0.03 | Line: CEBU - TOLEDO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3966
4 | 967 | 3967 | 0305403012 | Region III (Central Luzon) | Pampanga | Arayat | Lacquios | 15.1677 | 120.7734 | R | 3964 | 4 | 991 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.84 | 0.75 | Tier 2B: Moderate GIDA Inclusion | 67.28 | 67.28 | 37.56 | 52.42 | D - Other node or line within 3 km | 2.84 | 0.73 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3967
4 | 968 | 3968 | 0301405016 | Region III (Central Luzon) | Bulacan | Bulacan | Tibig | 14.8024 | 120.8681 | R | 3318 | 3.5 | 948 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.27 | 2.97 | Tier 2B: Moderate GIDA Inclusion | 66.02 | 66.02 | 38.83 | 52.42 | D - Other node or line within 3 km | 1.27 | 2.95 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3968
4 | 969 | 3969 | 0105517009 | Region I (Ilocos Region) | Pangasinan | Calasiao | Gabon | 16.0114 | 120.3617 | R | 3050 | 3.6 | 847 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 65.41 | 65.41 | 39.42 | 52.42 | C - Line within 0.5 km; node over 1 km | 2.8 | 0.06 | Line: CALASIAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3969
4 | 970 | 3970 | 0405623008 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 5 | 14.1159 | 121.5732 | R | 2399 | 3.8 | 631 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 1.11 | Tier 2B: Moderate GIDA Inclusion | 61.19 | 61.19 | 43.64 | 52.42 | D - Other node or line within 3 km | 1.64 | 1.09 | Line: LUCENA - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3970
4 | 971 | 3971 | 0604528020 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 5 | 10.7278 | 122.9938 | R | 2248 | 3.7 | 608 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.18 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 59.42 | 59.42 | 45.41 | 52.42 | C - Line within 0.5 km; node over 1 km | 3.18 | 0.42 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3971
4 | 972 | 3972 | 1908819011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Tabungao | 17.2552 | 122.2292 | R | 3569 | 4.7 | 759 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 44.48 | 44.48 | 60.35 | 52.42 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3972
4 | 973 | 3973 | 1380614074 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 881 | 11.732 | 121.4028 | U | 2443 | 3.3 | 741 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 63.81 | 62.77 | Tier 1B: High GIDA Priority | 35.75 | 35.75 | 69.08 | 52.42 | F - Nearest node and line over 5 km | 63.81 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3973
4 | 974 | 3974 | 1903610018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Pagalongan | 17.2544 | 122.2285 | R | 887 | 5.7 | 156 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 33.2 | 33.2 | 71.63 | 52.42 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3974
4 | 975 | 3975 | 0304924011 | Region III (Central Luzon) | Nueva Ecija | San Antonio | San Francisco | 15.3665 | 120.8509 | U | 16684 | 3.5 | 4767 | 1430 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.85 | 8.05 | Tier 2B: Moderate GIDA Inclusion | 67.41 | 67.41 | 37.41 | 52.41 | D - Other node or line within 3 km | 1.85 | 8.05 | Node: JNN002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3975
4 | 976 | 3976 | 0501603025 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay II | 14.1062 | 122.9535 | R | 2919 | 4 | 730 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 65.6 | 65.6 | 39.22 | 52.41 | B - Node 0.5-1 km | 0.93 | 0.6 | Line: PAGBILAO - NAGA (UG + Aerial) | Survey short node lateral; confirm port/fiber capacity, access and route. | 3976
4 | 977 | 3977 | 1102319015 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Pandapan | 7.4828 | 125.8764 | R | 2546 | 3.7 | 688 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.68 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 58.52 | 58.52 | 46.3 | 52.41 | D - Other node or line within 3 km | 6.68 | 1.83 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3977
4 | 978 | 3978 | 0501714006 | Region V (Bicol Region) | Camarines Sur | Garchitorena | Cagnipa | 13.9578 | 123.666 | R | 720 | 4.2 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 35.09 | Tier 1B: High GIDA Priority | 37.7 | 37.7 | 67.12 | 52.41 | F - Nearest node and line over 5 km | 29.51 | 34.86 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3978
4 | 979 | 3979 | 1380611010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 676 | 13.7392 | 121.6185 | U | 2564 | 3.74 | 685 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.06 | 17.18 | Tier 1B: High GIDA Priority | 34.35 | 34.35 | 70.46 | 52.41 | F - Nearest node and line over 5 km | 18.06 | 17.18 | Line: SJB002 TO LCQ001 LUCBITZ AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3979
4 | 980 | 3980 | 1380611040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 825 | 12.7865 | 121.4707 | U | 463 | 3.36 | 138 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.06 | 0.3 | Tier 1B: High GIDA Priority | 31.89 | 31.89 | 72.93 | 52.41 | C - Line within 0.5 km; node over 1 km | 5.06 | 0.3 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3980
4 | 981 | 3981 | 0702218007 | Region VII (Central Visayas) | Cebu | Compostela | Cogon | 10.4553 | 124.0092 | U | 8155 | 3.8 | 2146 | 644 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.46 | Tier 2B: Moderate GIDA Inclusion | 69.99 | 69.99 | 34.81 | 52.4 | A - Node within 0.5 km | 0.39 | 0.07 | Line: 6.035km FOC | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 3981
4 | 982 | 3982 | 0601915006 | Region VI (Western Visayas) | Capiz | Sapi-An | Dapdapan | 11.4933 | 122.6356 | R | 2954 | 3.8 | 777 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.27 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 37.16 | 52.4 | C - Line within 0.5 km; node over 1 km | 3.27 | 0.3 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3982
4 | 983 | 3983 | 0402115005 | Region IV-A (CALABARZON) | Cavite | Naic | Bucana Sasahan | 14.3227 | 120.7599 | U | 6274 | 3.4 | 1845 | 554 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.28 | 1.27 | Tier 2B: Moderate GIDA Inclusion | 64.55 | 64.55 | 40.24 | 52.4 | D - Other node or line within 3 km | 1.28 | 1.27 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3983
4 | 984 | 3984 | 1004317021 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Tulang | 9.0259 | 125.2215 | R | 526 | 3.9 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.62 | 1.87 | Tier 2B: Moderate GIDA Inclusion | 51.83 | 51.83 | 52.96 | 52.4 | D - Other node or line within 3 km | 3.62 | 1.83 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3984
4 | 985 | 3985 | 1380610018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 703 | 12.9156 | 121.4944 | U | 848 | 2.66 | 319 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.2 | 3.06 | Tier 1B: High GIDA Priority | 33.11 | 33.11 | 71.7 | 52.4 | E - Nearest node or line 3-5 km | 5.2 | 3.05 | Line: MINDORO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3985
4 | 986 | 3986 | 0304912029 | Region III (Central Luzon) | Nueva Ecija | Jaen | Sapang | 15.324 | 120.9057 | R | 4479 | 3.5 | 1280 | 384 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.93 | 1.66 | Tier 2A: High Commercial ROI | 71.16 | 71.16 | 33.62 | 52.39 | B - Node 0.5-1 km | 0.93 | 1.65 | Node: JNN001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 3986
4 | 987 | 3987 | 1402706022 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Mapawoy | 16.9626 | 121.2116 | R | 893 | 3.9 | 229 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.54 | 16.68 | Tier 2B: Moderate GIDA Inclusion | 52.08 | 52.08 | 52.7 | 52.39 | D - Other node or line within 3 km | 1.54 | 18.46 | Node: MOF001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3987
4 | 988 | 3988 | 1208002016 | Region XII (SOCCSKSARGEN) | Sarangani | Glan | Kaltuad | 5.736 | 125.3532 | R | 2318 | 3.9 | 594 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.86 | 46.39 | Tier 1B: High GIDA Priority | 41.73 | 41.73 | 63.05 | 52.39 | F - Nearest node and line over 5 km | 41.86 | 999999 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3988
4 | 989 | 3989 | 0401005059 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 13 | 13.7066 | 121.0941 | U | 358 | 3.6 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.98 | 6.5 | Tier 1B: High GIDA Priority | 33.53 | 33.53 | 71.24 | 52.39 | E - Nearest node or line 3-5 km | 3.98 | 6.5 | Node: BCY004 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3989
4 | 990 | 3990 | 1908806011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Lomoyon | 17.2552 | 122.2293 | R | 1271 | 4.7 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.48 | 34.35 | Tier 1B: High GIDA Priority | 31.66 | 31.66 | 73.13 | 52.39 | F - Nearest node and line over 5 km | 29.48 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3990
4 | 991 | 3991 | 0307112002 | Region III (Central Luzon) | Zambales | San Narciso | Beddeng | 14.9871 | 120.0831 | R | 3409 | 3.8 | 897 | 269 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.17 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 69.8 | 69.8 | 34.97 | 52.38 | C - Line within 0.5 km; node over 1 km | 4.17 | 0.15 | Line: BACKBONE ROUTE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3991
4 | 992 | 3992 | 0306905032 | Region III (Central Luzon) | Tarlac | Concepcion | San Jose | 15.3264 | 120.6605 | U | 10904 | 3.9 | 2796 | 839 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 69.12 | 69.12 | 35.63 | 52.38 | B - Node 0.5-1 km | 0.51 | 0.17 | Line: 24 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 3992
4 | 993 | 3993 | 0102908015 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | San Juan | 16.9837 | 120.7196 | R | 2189 | 3.8 | 576 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.81 | 1.7 | Tier 2B: Moderate GIDA Inclusion | 65.81 | 65.81 | 38.96 | 52.38 | B - Node 0.5-1 km | 0.81 | 1.52 | Node: CVI001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 3993
4 | 994 | 3994 | 1402705016 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Bimpal | 16.7336 | 121.1731 | R | 1755 | 3.9 | 450 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 1.13 | Tier 2B: Moderate GIDA Inclusion | 61.19 | 61.19 | 43.56 | 52.38 | D - Other node or line within 3 km | 1.63 | 1.06 | Line: FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3994
4 | 995 | 3995 | 1900712001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Muhtamad | Baluk-baluk | 6.7236 | 121.5889 | R | 2284 | 5.1 | 448 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.42 | 57.42 | Tier 1B: High GIDA Priority | 35.6 | 35.6 | 69.17 | 52.38 | F - Nearest node and line over 5 km | 57.42 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3995
4 | 996 | 3996 | 0600614002 | Region VI (Western Visayas) | Antique | San Remigio | Alegria | 10.8715 | 122.1586 | R | 583 | 3.9 | 149 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.98 | 19.93 | Tier 1B: High GIDA Priority | 33.15 | 33.15 | 71.61 | 52.38 | F - Nearest node and line over 5 km | 26.98 | 19.82 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3996
4 | 997 | 3997 | 0105506014 | Region I (Ilocos Region) | Pangasinan | Asingan | Macalong | 16.0109 | 120.6602 | R | 3976 | 3.6 | 1104 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 1.3 | Tier 2A: High Commercial ROI | 70.1 | 70.1 | 34.65 | 52.37 | D - Other node or line within 3 km | 1.21 | 1.3 | Node: ANP001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3997
4 | 998 | 3998 | 0701216001 | Region VII (Central Visayas) | Bohol | Cortes | De la Paz | 9.701 | 123.8677 | R | 2987 | 4 | 747 | 224 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 67.89 | 67.89 | 36.85 | 52.37 | C - Line within 0.5 km; node over 1 km | 2.52 | 0.05 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 3998
4 | 999 | 3999 | 0201529006 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 4 | 17.6218 | 121.7383 | U | 608 | 3.9 | 156 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.42 | 0.79 | Tier 1B: High GIDA Priority | 38.58 | 38.58 | 66.15 | 52.37 | D - Other node or line within 3 km | 3.42 | 0.61 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 3999
4 | 1000 | 4000 | 0907315015 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Mahayag | Malubo | 8.1853 | 123.4376 | R | 877 | 3.9 | 225 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.62 | 30.48 | Tier 1B: High GIDA Priority | 32.18 | 32.18 | 72.56 | 52.37 | F - Nearest node and line over 5 km | 30.62 | 30.48 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4000
4 | 1001 | 4001 | 0702208012 | Region VII (Central Visayas) | Cebu | Balamban | Cantuod | 10.5157 | 123.7274 | R | 5099 | 3.8 | 1342 | 403 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 1.17 | Tier 2A: High Commercial ROI | 73.16 | 73.16 | 31.56 | 52.36 | D - Other node or line within 3 km | 1.61 | 1.16 | Line: 104.3km-96FOC-toledo-san remigio | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4001
4 | 1002 | 4002 | 0305420004 | Region III (Central Luzon) | Pampanga | Santa Rita | San Basilio | 15.0343 | 120.5821 | U | 12544 | 4 | 3136 | 941 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.37 | 1.46 | Tier 2B: Moderate GIDA Inclusion | 68.52 | 68.52 | 36.2 | 52.36 | D - Other node or line within 3 km | 5.37 | 1.46 | Line: 24 CORE (2X12) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4002
4 | 1003 | 4003 | 0306916097 | Region III (Central Luzon) | Tarlac | City of Tarlac | Salapungan | 15.5119 | 120.5989 | R | 2102 | 3.9 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 56.11 | 56.11 | 48.6 | 52.36 | C - Line within 0.5 km; node over 1 km | 3.71 | 0.29 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4003
4 | 1004 | 4004 | 0103306013 | Region I (Ilocos Region) | La Union | Bangar | General Terrero | 16.897 | 120.423 | R | 1150 | 3.7 | 311 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 54.82 | 54.82 | 49.91 | 52.36 | A - Node within 0.5 km | 0.47 | 0.27 | Line: SAN FERNANDO - SUPIDEN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4004
4 | 1005 | 4005 | 1001304010 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Kawilihan | 7.7263 | 124.9756 | R | 1206 | 3.8 | 317 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.93 | 3.85 | Tier 1B: High GIDA Priority | 46.9 | 46.9 | 57.81 | 52.36 | E - Nearest node or line 3-5 km | 4.93 | 3.81 | Line: DAMULOG - VALENCIA - QUEZON | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4005
4 | 1006 | 4006 | 1102414015 | Region XI (Davao Region) | Davao del Sur | Sulop | Osmeña | 6.5874 | 125.3048 | R | 631 | 3.4 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.5 | 4.2 | Tier 1B: High GIDA Priority | 44.07 | 44.07 | 60.66 | 52.36 | E - Nearest node or line 3-5 km | 4.5 | 4.54 | Node: SUD001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4006
4 | 1007 | 4007 | 0806023020 | Region VIII (Eastern Visayas) | Samar | Zumarraga | San Isidro | 11.6848 | 124.8285 | R | 1436 | 4.1 | 350 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.42 | 45.36 | Tier 1B: High GIDA Priority | 41.14 | 41.14 | 63.58 | 52.36 | F - Nearest node and line over 5 km | 45.42 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4007
4 | 1008 | 4008 | 0305420002 | Region III (Central Luzon) | Pampanga | Santa Rita | Dila-dila | 15.0156 | 120.5801 | U | 11087 | 4 | 2772 | 832 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.72 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 66.81 | 66.81 | 37.88 | 52.35 | C - Line within 0.5 km; node over 1 km | 6.72 | 0.16 | Line: 24 CORE (2X12) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4008
4 | 1009 | 4009 | 0907307049 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Sumadat | 7.8178 | 123.3695 | R | 3176 | 3.9 | 814 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.82 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 65.45 | 65.45 | 39.24 | 52.35 | C - Line within 0.5 km; node over 1 km | 7.82 | 0.13 | Line: PAGADIAN - BUUG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4009
4 | 1010 | 4010 | 0305408019 | Region III (Central Luzon) | Pampanga | Lubao | San Juan | 14.9209 | 120.5559 | R | 2744 | 4 | 686 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 1.36 | Tier 2B: Moderate GIDA Inclusion | 63.66 | 63.66 | 41.03 | 52.35 | D - Other node or line within 3 km | 1.13 | 1.35 | Node: LOP001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4010
4 | 1011 | 4011 | 1600308017 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 3 | 8.5072 | 125.9725 | U | 3575 | 3.9 | 917 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.39 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 63.57 | 63.57 | 41.13 | 52.35 | A - Node within 0.5 km | 0.39 | 0.22 | Line: TRENTO - BUENAVISTA CLS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4011
4 | 1012 | 4012 | 1402710010 | Cordillera Administrative Region (CAR) | Ifugao | Tinoc | Tukucan | 16.7364 | 120.9291 | R | 1720 | 3.9 | 441 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.03 | 9.92 | Tier 2B: Moderate GIDA Inclusion | 48.69 | 48.69 | 56 | 52.35 | F - Nearest node and line over 5 km | 11.03 | 9.79 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4012
4 | 1013 | 4013 | 0405622068 | Region IV-A (CALABARZON) | Quezon | Lopez | San Miguel | 13.747 | 122.2962 | R | 1675 | 3.8 | 441 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.71 | 11.16 | Tier 2B: Moderate GIDA Inclusion | 48.3 | 48.3 | 56.4 | 52.35 | F - Nearest node and line over 5 km | 5.71 | 11.15 | Node: CTQ004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4013
4 | 1014 | 4014 | 1705315003 | MIMAROPA Region | Palawan | Narra | Batang-batang | 9.1811 | 118.3376 | R | 1488 | 3.9 | 382 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.87 | 78.16 | Tier 1B: High GIDA Priority | 36.18 | 36.18 | 68.52 | 52.35 | F - Nearest node and line over 5 km | 75.87 | 999999 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4014
4 | 1015 | 4015 | 0600614037 | Region VI (Western Visayas) | Antique | San Remigio | Panpanan II | 10.9024 | 122.2536 | R | 575 | 3.9 | 147 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.45 | 21.64 | Tier 1B: High GIDA Priority | 32.99 | 32.99 | 71.72 | 52.35 | F - Nearest node and line over 5 km | 28.45 | 21.37 | Line: 7,761 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4015
4 | 1016 | 4016 | 1907007026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Naungan | 5.2461 | 120.355 | R | 1415 | 5.8 | 244 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 265.25 | 265.25 | Tier 1B: High GIDA Priority | 30.26 | 30.26 | 74.45 | 52.35 | F - Nearest node and line over 5 km | 265.25 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4016
4 | 1017 | 4017 | 1102403003 | Region XI (Davao Region) | Davao del Sur | City of Digos | San Jose | 6.7335 | 125.3568 | U | 7263 | 3.4 | 2136 | 641 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 67.72 | 67.72 | 36.96 | 52.34 | B - Node 0.5-1 km | 0.97 | 0.62 | Line: DAVAO CITY - GENSAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 4017
4 | 1018 | 4018 | 1705209006 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Cacawan | 13.0452 | 121.4824 | U | 6819 | 3.9 | 1748 | 524 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 66.49 | 66.49 | 38.2 | 52.34 | B - Node 0.5-1 km | 0.83 | 0.74 | Line: MINDORO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4018
4 | 1019 | 4019 | 0301420027 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Guijo | 14.8144 | 121.0617 | U | 7288 | 3.5 | 2082 | 625 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 1.56 | Tier 2B: Moderate GIDA Inclusion | 65.77 | 65.77 | 38.9 | 52.34 | D - Other node or line within 3 km | 1.11 | 2.36 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4019
4 | 1020 | 4020 | 0304926024 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Porais | 15.7529 | 121.0433 | R | 3744 | 3.5 | 1070 | 321 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.54 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 64.39 | 64.39 | 40.28 | 52.34 | C - Line within 0.5 km; node over 1 km | 7.54 | 0.11 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4020
4 | 1021 | 4021 | 0105522018 | Region I (Ilocos Region) | Pangasinan | Lingayen | Libsong West | 16.03 | 120.2406 | U | 5327 | 3.6 | 1480 | 444 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 63.86 | 63.86 | 40.82 | 52.34 | D - Other node or line within 3 km | 1.15 | 0.63 | Line: DAGUPAN - ALAMINOS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4021
4 | 1022 | 4022 | 0300801003 | Region III (Central Luzon) | Bataan | Abucay | Capitangan | 14.7061 | 120.5378 | U | 7605 | 3.6 | 2112 | 634 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.38 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 40.87 | 52.34 | C - Line within 0.5 km; node over 1 km | 2.38 | 0.04 | Line: 60 CORE 5X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4022
4 | 1023 | 4023 | 0401019018 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Bunducan | 14.0947 | 120.6452 | R | 2399 | 3.6 | 666 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.92 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 60.36 | 60.36 | 44.33 | 52.34 | D - Other node or line within 3 km | 2.92 | 1.95 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4023
4 | 1024 | 4024 | 0203118020 | Region II (Cagayan Valley) | Isabela | Delfin Albano | San Juan | 17.2913 | 121.7843 | R | 2091 | 3.8 | 550 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.06 | 2.26 | Tier 2B: Moderate GIDA Inclusion | 58.09 | 58.09 | 46.58 | 52.34 | D - Other node or line within 3 km | 3.06 | 2.26 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4024
4 | 1025 | 4025 | 0405814010 | Region IV-A (CALABARZON) | Rizal | Teresa | Calumpang Santo Cristo | 14.5544 | 121.2169 | R | 1394 | 3.6 | 387 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 57.21 | 57.21 | 47.47 | 52.34 | A - Node within 0.5 km | 0.25 | 0.23 | Line: Aerial 24C | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4025
4 | 1026 | 4026 | 0300810017 | Region III (Central Luzon) | Bataan | Orion | Lati | 14.6093 | 120.571 | R | 1346 | 3.6 | 374 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.66 | Tier 2B: Moderate GIDA Inclusion | 55.26 | 55.26 | 49.41 | 52.34 | D - Other node or line within 3 km | 1.11 | 0.66 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4026
4 | 1027 | 4027 | 1400113009 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Poblacion | 17.608 | 120.9053 | R | 272 | 3.8 | 72 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26 | 25.97 | Tier 1B: High GIDA Priority | 34.7 | 34.7 | 69.98 | 52.34 | F - Nearest node and line over 5 km | 26 | 25.95 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4027
4 | 1028 | 4028 | 1906615006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Luuk | 17.2557 | 122.2297 | R | 1963 | 6 | 327 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.41 | Tier 1B: High GIDA Priority | 33.13 | 33.13 | 71.55 | 52.34 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4028
4 | 1029 | 4029 | 0402120012 | Region IV-A (CALABARZON) | Cavite | Tanza | Mulawin | 14.3676 | 120.8504 | U | 12931 | 3.4 | 3803 | 1141 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.45 | 1.58 | Tier 2A: High Commercial ROI | 72.18 | 72.18 | 32.48 | 52.33 | A - Node within 0.5 km | 0.45 | 1.57 | Node: TZC002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4029
4 | 1030 | 4030 | 1204704039 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Sudapin | 7.019 | 125.0935 | U | 9293 | 3.8 | 2446 | 734 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.25 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68.07 | 68.07 | 36.58 | 52.33 | C - Line within 0.5 km; node over 1 km | 1.25 | 0.18 | Line: QUIRINO - KIDAPAWAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4030
4 | 1031 | 4031 | 0102813009 | Region I (Ilocos Region) | Ilocos Norte | Marcos | Lydia | 18.0441 | 120.6745 | R | 2298 | 3.7 | 621 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 64.57 | 64.57 | 40.09 | 52.33 | C - Line within 0.5 km; node over 1 km | 2.23 | 0.18 | Line: SEGMENT 4 MARCOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4031
4 | 1032 | 4032 | 0402106019 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone IV | 14.3231 | 120.9547 | U | 3969 | 3.4 | 1167 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 2.38 | Tier 2B: Moderate GIDA Inclusion | 58.29 | 58.29 | 46.37 | 52.33 | D - Other node or line within 3 km | 1.67 | 2.3 | Node: DMC004 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4032
4 | 1033 | 4033 | 0405630007 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Bukal | 13.9128 | 121.5448 | U | 9000 | 3.8 | 2368 | 710 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.64 | 3.62 | Tier 2B: Moderate GIDA Inclusion | 57.85 | 57.85 | 46.8 | 52.33 | E - Nearest node or line 3-5 km | 5.64 | 3.58 | Line: SJB002 TO LCQ001 LUCBITZ AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4033
4 | 1034 | 4034 | 1705311006 | MIMAROPA Region | Palawan | Dumaran | Culasian | 10.605 | 119.6531 | R | 1123 | 3.9 | 288 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.21 | 20.55 | Tier 1B: High GIDA Priority | 39.85 | 39.85 | 64.81 | 52.33 | F - Nearest node and line over 5 km | 12.21 | 20.54 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4034
4 | 1035 | 4035 | 0501714022 | Region V (Bicol Region) | Camarines Sur | Garchitorena | Tamiawon | 13.9536 | 123.6293 | R | 850 | 4.2 | 202 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.07 | 32.65 | Tier 1B: High GIDA Priority | 38.7 | 38.7 | 65.96 | 52.33 | F - Nearest node and line over 5 km | 27.07 | 32.44 | Node: TCC002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4035
4 | 1036 | 4036 | 0304911061 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santo Cristo District | 15.6578 | 120.7601 | U | 4141 | 3.5 | 1183 | 355 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.71 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 63.8 | 63.8 | 40.84 | 52.32 | B - Node 0.5-1 km | 0.71 | 0.78 | Node: GUN001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4036
4 | 1037 | 4037 | 0201506006 | Region II (Cagayan Valley) | Cagayan | Baggao | Asinga-Via | 17.8758 | 121.9045 | R | 2645 | 3.9 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4 | 19.56 | Tier 2B: Moderate GIDA Inclusion | 56.02 | 56.02 | 48.63 | 52.32 | E - Nearest node or line 3-5 km | 4 | 19.54 | Node: BOC002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4037
4 | 1038 | 4038 | 1380606125 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 519 | 13.2864 | 122.4966 | U | 1385 | 3.06 | 453 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.05 | 28.63 | Tier 1B: High GIDA Priority | 35.8 | 35.8 | 68.85 | 52.32 | F - Nearest node and line over 5 km | 7.05 | 28.63 | Node: SFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4038
4 | 1039 | 4039 | 1380614030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 774 | 13.7675 | 120.7801 | U | 2909 | 4.27 | 682 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.12 | 17.5 | Tier 1B: High GIDA Priority | 35 | 35 | 69.64 | 52.32 | F - Nearest node and line over 5 km | 15.12 | 17.5 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4039
4 | 1040 | 4040 | 1903631004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Bitayan | 15.6589 | 122.5425 | R | 1027 | 5.7 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 81.16 | 79.99 | Tier 1B: High GIDA Priority | 33.1 | 33.1 | 71.54 | 52.32 | F - Nearest node and line over 5 km | 81.16 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4040
4 | 1041 | 4041 | 0203111004 | Region II (Cagayan Valley) | Isabela | Divilacan | Dicaroyan | 17.3431 | 122.2561 | R | 371 | 3.8 | 98 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.32 | 40.79 | Tier 1B: High GIDA Priority | 28.72 | 28.72 | 75.92 | 52.32 | F - Nearest node and line over 5 km | 38.32 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4041
4 | 1042 | 4042 | 1102303022 | Region XI (Davao Region) | Davao del Norte | Carmen | Tuganay | 7.3693 | 125.7222 | R | 5049 | 3.7 | 1365 | 410 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.8 | 0.06 | Tier 2A: High Commercial ROI | 70.25 | 70.25 | 34.36 | 52.31 | C - Line within 0.5 km; node over 1 km | 2.8 | 0.06 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4042
4 | 1043 | 4043 | 0401033012 | Region IV-A (CALABARZON) | Batangas | Tingloy | San Jose | 13.6666 | 120.8538 | R | 1497 | 3.6 | 416 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.06 | 18.73 | Tier 2B: Moderate GIDA Inclusion | 52.55 | 52.55 | 52.08 | 52.31 | F - Nearest node and line over 5 km | 5.06 | 18.72 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4043
4 | 1044 | 4044 | 1903614012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Liangan | 17.2546 | 122.2287 | R | 1120 | 5.7 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.38 | 34.27 | Tier 1B: High GIDA Priority | 34.25 | 34.25 | 70.38 | 52.31 | F - Nearest node and line over 5 km | 29.38 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4044
4 | 1045 | 4045 | 1380601178 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 178 | 13.6234 | 121.2398 | U | 1324 | 3.94 | 336 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.26 | 23.26 | Tier 1B: High GIDA Priority | 34.24 | 34.24 | 70.39 | 52.31 | E - Nearest node or line 3-5 km | 4.26 | 23.26 | Node: LBB001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4045
4 | 1046 | 4046 | 1380601142 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 142 | 13.6434 | 122.4314 | U | 1721 | 3.99 | 431 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.66 | 5.05 | Tier 1B: High GIDA Priority | 33.61 | 33.61 | 71.01 | 52.31 | E - Nearest node or line 3-5 km | 8.66 | 4.98 | Line: LZQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4046
4 | 1047 | 4047 | 1906612060 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Sipanding | 17.2555 | 122.2295 | R | 1929 | 6 | 322 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 33.05 | 33.05 | 71.57 | 52.31 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4047
4 | 1048 | 4048 | 1003515024 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Raraban | 7.7893 | 123.9152 | R | 637 | 4.2 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.96 | 20.06 | Tier 1B: High GIDA Priority | 31.48 | 31.48 | 73.14 | 52.31 | F - Nearest node and line over 5 km | 30.96 | 20.04 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4048
4 | 1049 | 4049 | 1600303037 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Guibonon | 8.6312 | 125.3112 | R | 330 | 3.9 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.07 | 28.4 | Tier 1B: High GIDA Priority | 31.42 | 31.42 | 73.21 | 52.31 | F - Nearest node and line over 5 km | 29.07 | 28.4 | Line: CDO - BUENAVISTA via GINGOOG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4049
4 | 1050 | 4050 | 0501710002 | Region V (Bicol Region) | Camarines Sur | Canaman | Del Rosario | 13.6316 | 123.1702 | R | 3735 | 4.2 | 889 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 1.78 | Tier 2A: High Commercial ROI | 73 | 73 | 31.6 | 52.3 | D - Other node or line within 3 km | 1.31 | 1.77 | Node: CLC001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4050
4 | 1051 | 4051 | 0604531015 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XII | 10.8875 | 123.0761 | R | 4320 | 3.7 | 1168 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 1.37 | Tier 2A: High Commercial ROI | 72.71 | 72.71 | 31.88 | 52.3 | D - Other node or line within 3 km | 1.6 | 1.25 | Line: TALISAY - VICTORIAS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4051
4 | 1052 | 4052 | 0304911003 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bacayao | 15.6625 | 120.7533 | R | 3022 | 3.5 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 1.86 | Tier 2B: Moderate GIDA Inclusion | 67.74 | 67.74 | 36.86 | 52.3 | D - Other node or line within 3 km | 1.52 | 1.59 | Node: GUN001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4052
4 | 1053 | 4053 | 0306914012 | Region III (Central Luzon) | Tarlac | San Manuel | San Miguel | 15.8044 | 120.6072 | R | 2552 | 3.9 | 654 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 67.73 | 67.73 | 36.87 | 52.3 | B - Node 0.5-1 km | 0.89 | 0.04 | Line: SAN MANUEL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4053
4 | 1054 | 4054 | 0305408044 | Region III (Central Luzon) | Pampanga | Lubao | Santo Niño | 14.8726 | 120.5039 | R | 4087 | 4 | 1022 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.84 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 66.27 | 66.27 | 38.33 | 52.3 | C - Line within 0.5 km; node over 1 km | 3.84 | 0.04 | Line: LUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4054
4 | 1055 | 4055 | 0102906017 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Calongbuyan | 17.1741 | 120.4348 | R | 2944 | 3.8 | 775 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.34 | 0.83 | Tier 2B: Moderate GIDA Inclusion | 64.05 | 64.05 | 40.54 | 52.3 | D - Other node or line within 3 km | 2.34 | 0.8 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4055
4 | 1056 | 4056 | 0304916017 | Region III (Central Luzon) | Nueva Ecija | Lupao | Namulandayan | 15.8824 | 120.9049 | R | 2243 | 3.5 | 641 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.8 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 63.05 | 63.05 | 41.55 | 52.3 | B - Node 0.5-1 km | 0.8 | 1.12 | Node: LPN001 - TYPE 4 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4056
4 | 1057 | 4057 | 0401011008 | Region IV-A (CALABARZON) | Batangas | Laurel | Buso-buso | 14.0212 | 120.9511 | R | 2801 | 3.6 | 778 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.03 | 8.32 | Tier 2B: Moderate GIDA Inclusion | 58.67 | 58.67 | 45.92 | 52.3 | E - Nearest node or line 3-5 km | 4.03 | 8.31 | Node: LRB002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4057
4 | 1058 | 4058 | 1906617009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Laha | 17.2555 | 122.2295 | R | 1721 | 6 | 287 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 36.59 | 36.59 | 68 | 52.3 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4058
4 | 1059 | 4059 | 1380606055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 449 | 13.3726 | 122.4961 | U | 1360 | 3.6 | 378 | 113 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.86 | 19.98 | Tier 1B: High GIDA Priority | 35.65 | 35.65 | 68.94 | 52.3 | E - Nearest node or line 3-5 km | 3.86 | 19.98 | Node: SFQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4059
4 | 1060 | 4060 | 0600614022 | Region VI (Western Visayas) | Antique | San Remigio | Orquia | 10.911 | 122.1586 | R | 214 | 3.9 | 55 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.21 | 21.93 | Tier 1B: High GIDA Priority | 32.91 | 32.91 | 71.68 | 52.3 | F - Nearest node and line over 5 km | 29.21 | 21.76 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4060
4 | 1061 | 4061 | 1003515012 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Liangan | 7.803 | 123.9143 | R | 621 | 4.2 | 148 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 19.12 | Tier 1B: High GIDA Priority | 31.43 | 31.43 | 73.17 | 52.3 | F - Nearest node and line over 5 km | 29.54 | 19.12 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4061
4 | 1062 | 4062 | 0307112009 | Region III (Central Luzon) | Zambales | San Narciso | Natividad | 15.009 | 120.0968 | R | 4443 | 3.8 | 1169 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.31 | 1.74 | Tier 2B: Moderate GIDA Inclusion | 69.58 | 69.58 | 34.99 | 52.29 | D - Other node or line within 3 km | 6.31 | 1.74 | Line: SAN NARCISO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4062
4 | 1063 | 4063 | 0305410003 | Region III (Central Luzon) | Pampanga | Macabebe | Candelaria | 14.8837 | 120.7204 | R | 3215 | 4 | 804 | 241 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 65.84 | 65.84 | 38.75 | 52.29 | D - Other node or line within 3 km | 1.69 | 5.65 | Node: MSP001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4063
4 | 1064 | 4064 | 1404404005 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Bontoc Ili | 17.0872 | 120.9756 | R | 4395 | 3.7 | 1188 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.96 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 64.71 | 64.71 | 39.87 | 52.29 | C - Line within 0.5 km; node over 1 km | 7.96 | 0.13 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4064
4 | 1065 | 4065 | 1003515015 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Malaig | 7.795 | 123.9271 | R | 605 | 4.2 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.96 | 20.79 | Tier 1B: High GIDA Priority | 31.26 | 31.26 | 73.33 | 52.29 | F - Nearest node and line over 5 km | 30.96 | 20.79 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4065
4 | 1066 | 4066 | 0301409012 | Region III (Central Luzon) | Bulacan | Hagonoy | San Juan | 14.8659 | 120.7422 | R | 3868 | 3.5 | 1105 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.13 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 67.29 | 67.29 | 37.28 | 52.28 | E - Nearest node or line 3-5 km | 3.13 | 5.01 | Node: HGB001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4066
4 | 1067 | 4067 | 0500502021 | Region V (Bicol Region) | Albay | Camalig | Libod | 13.18 | 123.6372 | R | 3551 | 4.1 | 866 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.68 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 64.73 | 64.73 | 39.84 | 52.28 | C - Line within 0.5 km; node over 1 km | 3.68 | 0.06 | Line: IRIGA - LEGAZPI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4067
4 | 1068 | 4068 | 1001312028 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Miglamin | 7.8974 | 124.97 | R | 2905 | 3.8 | 764 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.82 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 62.17 | 62.17 | 42.38 | 52.28 | C - Line within 0.5 km; node over 1 km | 3.82 | 0.32 | Line: DAMULOG - VALENCIA - QUEZON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4068
4 | 1069 | 4069 | 1908702014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Piers | 17.2539 | 122.2279 | R | 3123 | 4.3 | 726 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.27 | 34.17 | Tier 1B: High GIDA Priority | 43.63 | 43.63 | 60.93 | 52.28 | F - Nearest node and line over 5 km | 29.27 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4069
4 | 1070 | 4070 | 0205014001 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Sur | 16.5783 | 121.1888 | R | 3354 | 3.8 | 883 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.32 | 5.97 | Tier 2A: High Commercial ROI | 71.6 | 71.6 | 32.95 | 52.27 | A - Node within 0.5 km | 0.32 | 5.83 | Node: VLV001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4070
4 | 1071 | 4071 | 0702208027 | Region VII (Central Visayas) | Cebu | Balamban | Baliwagan | 10.5066 | 123.7145 | U | 6280 | 3.8 | 1653 | 496 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68.98 | 68.98 | 35.56 | 52.27 | A - Node within 0.5 km | 0.28 | 0.13 | Line: 104.3km-96FOC-toledo-san remigio | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4071
4 | 1072 | 4072 | 0301416002 | Region III (Central Luzon) | Bulacan | Paombong | Kapitangan | 14.8645 | 120.7876 | R | 4921 | 3.5 | 1406 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.37 | 1.46 | Tier 2B: Moderate GIDA Inclusion | 67.93 | 67.93 | 36.61 | 52.27 | D - Other node or line within 3 km | 3.37 | 1.45 | Line: Mnla Pipe | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4072
4 | 1073 | 4073 | 0306916059 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Francisco | 15.4239 | 120.5974 | R | 3004 | 3.9 | 770 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 67.05 | 67.05 | 37.49 | 52.27 | B - Node 0.5-1 km | 0.55 | 0.22 | Line: 6 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 4073
4 | 1074 | 4074 | 0504101006 | Region V (Bicol Region) | Masbate | Aroroy | Balete | 12.3955 | 123.4396 | R | 1664 | 4.1 | 406 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.51 | 7.52 | Tier 1B: High GIDA Priority | 45.33 | 45.33 | 59.2 | 52.27 | F - Nearest node and line over 5 km | 10.51 | 15.65 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4074
4 | 1075 | 4075 | 0504113007 | Region V (Bicol Region) | Masbate | Mobo | Guintorelan | 12.2488 | 123.6078 | R | 420 | 4.1 | 102 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.16 | 7.39 | Tier 1B: High GIDA Priority | 43.62 | 43.62 | 60.91 | 52.27 | F - Nearest node and line over 5 km | 11.16 | 7.38 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4075
4 | 1076 | 4076 | 1903620035 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Padas | 17.2547 | 122.2287 | R | 1363 | 5.7 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.39 | 34.27 | Tier 1B: High GIDA Priority | 35.38 | 35.38 | 69.16 | 52.27 | F - Nearest node and line over 5 km | 29.39 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4076
4 | 1077 | 4077 | 1380614033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 777 | 12.0203 | 122.8247 | U | 3100 | 4.55 | 681 | 204 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.48 | 27.85 | Tier 1B: High GIDA Priority | 34.18 | 34.18 | 70.36 | 52.27 | F - Nearest node and line over 5 km | 45.48 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4077
4 | 1078 | 4078 | 1381100131 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 131 | 14.6237 | 120.8556 | U | 1605 | 3.28 | 489 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.42 | 10.95 | Tier 1B: High GIDA Priority | 33.31 | 33.31 | 71.24 | 52.27 | F - Nearest node and line over 5 km | 10.42 | 10.95 | Node: NAV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4078
4 | 1079 | 4079 | 0806017007 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Cabunga-an | 11.469 | 124.8829 | R | 517 | 4.1 | 126 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.27 | 26.98 | Tier 1B: High GIDA Priority | 33.01 | 33.01 | 71.53 | 52.27 | F - Nearest node and line over 5 km | 28.27 | 26.98 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4079
4 | 1080 | 4080 | 0804808020 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Candawid | 12.6417 | 125.0585 | R | 776 | 4.3 | 180 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 101.01 | 99.81 | Tier 1B: High GIDA Priority | 32.73 | 32.73 | 71.82 | 52.27 | F - Nearest node and line over 5 km | 101.01 | 999999 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4080
4 | 1081 | 4081 | 1907010008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Latuan | 17.2558 | 122.2298 | R | 1314 | 5.8 | 227 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 30.52 | 30.52 | 74.03 | 52.27 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4081
4 | 1082 | 4082 | 0304928018 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Santo Rosario | 15.4338 | 120.8894 | R | 3179 | 3.5 | 908 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.34 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 66.38 | 66.38 | 38.13 | 52.26 | C - Line within 0.5 km; node over 1 km | 4.62 | 0.03 | Line: LINK - 1 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4082
4 | 1083 | 4083 | 0304932020 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Isidro | 15.4485 | 120.8005 | U | 6681 | 3.5 | 1909 | 573 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 65.12 | 65.12 | 39.41 | 52.26 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.06 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4083
4 | 1084 | 4084 | 0403417002 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Alibungbungan | 14.139 | 121.4181 | R | 2161 | 3.3 | 655 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.35 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 64.27 | 64.27 | 40.25 | 52.26 | A - Node within 0.5 km | 0.35 | 0.1 | Line: UG SCL001 TO NGL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4084
4 | 1085 | 4085 | 0600613006 | Region VI (Western Visayas) | Antique | San Jose | Barangay 4 | 10.7406 | 121.9379 | R | 3026 | 3.9 | 776 | 233 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 64.21 | 64.21 | 40.3 | 52.26 | D - Other node or line within 3 km | 2.41 | 0.55 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4085
4 | 1086 | 4086 | 1903626013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tamparan | Linuk Oriental | 13.4956 | 123.0557 | R | 824 | 5.7 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.07 | 1.98 | Tier 2B: Moderate GIDA Inclusion | 50.83 | 50.83 | 53.7 | 52.26 | D - Other node or line within 3 km | 2.07 | 1.98 | Line: PASACAO CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4086
4 | 1087 | 4087 | 0501727008 | Region V (Bicol Region) | Camarines Sur | Pasacao | Macad | 13.5519 | 122.9924 | R | 1819 | 4.2 | 433 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.17 | 5.16 | Tier 2B: Moderate GIDA Inclusion | 50.29 | 50.29 | 54.23 | 52.26 | F - Nearest node and line over 5 km | 5.17 | 5.5 | Node: PCC001 - PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4087
4 | 1088 | 4088 | 1001308034 | Region X (Northern Mindanao) | Bukidnon | Kibawe | Tumaras | 7.515 | 125.0259 | R | 985 | 3.8 | 259 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.26 | 7.16 | Tier 1B: High GIDA Priority | 44.5 | 44.5 | 60.02 | 52.26 | F - Nearest node and line over 5 km | 7.26 | 7.15 | Line: DAMULOG - VALENCIA - QUEZON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4088
4 | 1089 | 4089 | 0803710015 | Region VIII (Eastern Visayas) | Leyte | Burauen | Candag-on | 10.9814 | 124.7495 | R | 258 | 3.8 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.55 | 8.49 | Tier 1B: High GIDA Priority | 39.68 | 39.68 | 64.85 | 52.26 | F - Nearest node and line over 5 km | 10.55 | 8.49 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4089
4 | 1090 | 4090 | 0201509003 | Region II (Cagayan Valley) | Cagayan | Calayan | Dadao | 19.2562 | 121.4885 | R | 2099 | 3.9 | 538 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 82.01 | 79.27 | Tier 1B: High GIDA Priority | 39.46 | 39.46 | 65.05 | 52.26 | F - Nearest node and line over 5 km | 82.01 | 999999 | Node: SMC001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4090
4 | 1091 | 4091 | 1400116005 | Cordillera Administrative Region (CAR) | Abra | Manabo | San Jose Norte | 17.4223 | 120.7007 | R | 547 | 3.8 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.75 | 18.31 | Tier 1B: High GIDA Priority | 36.56 | 36.56 | 67.97 | 52.26 | F - Nearest node and line over 5 km | 18.75 | 18.2 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4091
4 | 1092 | 4092 | 1907011004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Hadji Mohtar Sulayman | 17.2558 | 122.2299 | R | 2516 | 5.8 | 434 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 35.92 | 35.92 | 68.59 | 52.26 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4092
4 | 1093 | 4093 | 1380611018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 684 | 12.9361 | 120.4494 | U | 2685 | 3.72 | 722 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 80.08 | 78.74 | Tier 1B: High GIDA Priority | 35.31 | 35.31 | 69.2 | 52.26 | F - Nearest node and line over 5 km | 80.08 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4093
4 | 1094 | 4094 | 1380601153 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 153 | 13.6362 | 120.9271 | U | 1658 | 4.17 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.86 | 14.43 | Tier 1B: High GIDA Priority | 34.37 | 34.37 | 70.16 | 52.26 | F - Nearest node and line over 5 km | 6.86 | 14.38 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4094
4 | 1095 | 4095 | 0401029045 | Region IV-A (CALABARZON) | Batangas | Taal | Laguile | 13.8975 | 120.9164 | R | 3320 | 3.6 | 922 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 70 | 70 | 34.51 | 52.25 | B - Node 0.5-1 km | 0.85 | 0.05 | Line: AE BYB001 TO LYB001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4095
4 | 1096 | 4096 | 0105526016 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Lanas | 16.0775 | 120.3867 | R | 3366 | 3.6 | 935 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 68.29 | 68.29 | 36.2 | 52.25 | D - Other node or line within 3 km | 1.99 | 1.4 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4096
4 | 1097 | 4097 | 0305408016 | Region III (Central Luzon) | Pampanga | Lubao | San Isidro | 14.8847 | 120.5243 | R | 4453 | 4 | 1113 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.31 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 66.12 | 66.12 | 38.38 | 52.25 | C - Line within 0.5 km; node over 1 km | 4.31 | 0.14 | Line: LUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4097
4 | 1098 | 4098 | 0307106008 | Region III (Central Luzon) | Zambales | Masinloc | San Salvador | 15.5108 | 119.913 | R | 2668 | 3.8 | 702 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.15 | 5.16 | Tier 2B: Moderate GIDA Inclusion | 55.85 | 55.85 | 48.66 | 52.25 | F - Nearest node and line over 5 km | 5.15 | 5.16 | Node: MSZ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4098
4 | 1099 | 4099 | 1907010002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Lookan Banaran | 5.0126 | 120.1272 | R | 2578 | 5.8 | 444 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 35.49 | 35.49 | 69.01 | 52.25 | F - Nearest node and line over 5 km | 301.44 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4099
4 | 1100 | 4100 | 1380610029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 714 | 12.4303 | 121.0504 | U | 1617 | 3.58 | 452 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.98 | 6.42 | Tier 1B: High GIDA Priority | 33.86 | 33.86 | 70.64 | 52.25 | F - Nearest node and line over 5 km | 8.98 | 6.42 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4100
4 | 1101 | 4101 | 0401020001 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Banaba | 13.8858 | 121.2177 | R | 3949 | 3.6 | 1097 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.37 | Tier 2A: High Commercial ROI | 71.16 | 71.16 | 33.31 | 52.24 | B - Node 0.5-1 km | 0.54 | 0.37 | Line: AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4101
4 | 1102 | 4102 | 0403415021 | Region IV-A (CALABARZON) | Laguna | Magdalena | Salasad | 14.2032 | 121.4063 | R | 3340 | 3.3 | 1012 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.69 | 2.48 | Tier 2B: Moderate GIDA Inclusion | 68.31 | 68.31 | 36.18 | 52.24 | D - Other node or line within 3 km | 2.69 | 2.48 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4102
4 | 1103 | 4103 | 1208004012 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Nomoh | 5.9592 | 124.9201 | R | 3223 | 3.9 | 826 | 248 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.47 | 30.6 | Tier 2B: Moderate GIDA Inclusion | 48.15 | 48.15 | 56.33 | 52.24 | F - Nearest node and line over 5 km | 27.47 | 30.6 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4103
4 | 1104 | 4104 | 1705108005 | MIMAROPA Region | Occidental Mindoro | Rizal | Pitogo | 12.4966 | 121.0672 | R | 2325 | 3.6 | 646 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.21 | 13.74 | Tier 1B: High GIDA Priority | 46.45 | 46.45 | 58.02 | 52.24 | F - Nearest node and line over 5 km | 16.21 | 13.74 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4104
4 | 1105 | 4105 | 1102508013 | Region XI (Davao Region) | Davao Oriental | Manay | San Fermin | 7.2698 | 126.4413 | R | 1137 | 3.6 | 316 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.93 | 42 | Tier 1B: High GIDA Priority | 35 | 35 | 69.48 | 52.24 | F - Nearest node and line over 5 km | 42.93 | 999999 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4105
4 | 1106 | 4106 | 1380601146 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 146 | 13.1091 | 120.4396 | U | 2724 | 4.09 | 666 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.8 | 65.32 | Tier 1B: High GIDA Priority | 33.83 | 33.83 | 70.65 | 52.24 | F - Nearest node and line over 5 km | 66.8 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4106
4 | 1107 | 4107 | 1903638027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Mama-an Pagalongan | 17.2373 | 122.2181 | R | 600 | 5.7 | 105 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.3 | 32.67 | Tier 1B: High GIDA Priority | 32.81 | 32.81 | 71.67 | 52.24 | F - Nearest node and line over 5 km | 27.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4107
4 | 1108 | 4108 | 0600614007 | Region VI (Western Visayas) | Antique | San Remigio | Banbanan | 10.966 | 122.1903 | R | 282 | 3.9 | 72 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.29 | 28.33 | Tier 1B: High GIDA Priority | 32.53 | 32.53 | 71.96 | 52.24 | F - Nearest node and line over 5 km | 35.29 | 28.12 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4108
4 | 1109 | 4109 | 0401013005 | Region IV-A (CALABARZON) | Batangas | Lian | Bungahan | 14.0489 | 120.6382 | U | 5267 | 3.6 | 1463 | 439 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.47 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 61.5 | 61.5 | 42.96 | 52.23 | D - Other node or line within 3 km | 2.47 | 0.87 | Line: TGY001 TO NSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4109
4 | 1110 | 4110 | 0203124005 | Region II (Cagayan Valley) | Isabela | Ramon | Burgos | 16.8054 | 121.5292 | R | 2967 | 3.8 | 781 | 234 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 12.46 | Tier 2B: Moderate GIDA Inclusion | 61.16 | 61.16 | 43.29 | 52.23 | D - Other node or line within 3 km | 2.04 | 12.45 | Node: RNI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4110
4 | 1111 | 4111 | 1381300112 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sienna | 14.6485 | 120.9753 | U | 2928 | 5.66 | 517 | 155 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.27 | 0.4 | Tier 2B: Moderate GIDA Inclusion | 48.3 | 48.3 | 56.17 | 52.23 | A - Node within 0.5 km | 0.27 | 0.42 | Node: CCS004 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4111
4 | 1112 | 4112 | 1380606106 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 500 | 13.8147 | 120.8951 | U | 1404 | 3.4 | 413 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.09 | 9.08 | Tier 1B: High GIDA Priority | 35.62 | 35.62 | 68.84 | 52.23 | F - Nearest node and line over 5 km | 5.09 | 9.08 | Node: SUB001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4112
4 | 1113 | 4113 | 0907303022 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Matun-og | 7.871 | 123.0822 | R | 492 | 3.9 | 126 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.98 | 10.7 | Tier 1B: High GIDA Priority | 32.94 | 32.94 | 71.53 | 52.23 | F - Nearest node and line over 5 km | 15.98 | 10.68 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4113
4 | 1114 | 4114 | 0702211028 | Region VII (Central Visayas) | Cebu | City of Bogo | Taytayan | 11.0433 | 123.9909 | R | 4892 | 3.8 | 1287 | 386 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 0.59 | Tier 2A: High Commercial ROI | 72.59 | 72.59 | 31.86 | 52.22 | D - Other node or line within 3 km | 1.87 | 0.57 | Line: CABLE ROUTE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4114
4 | 1115 | 4115 | 0105522033 | Region I (Ilocos Region) | Pangasinan | Lingayen | Tonton | 16.0272 | 120.25 | R | 4826 | 3.6 | 1341 | 402 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.91 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 69.65 | 69.65 | 34.78 | 52.22 | C - Line within 0.5 km; node over 1 km | 1.91 | 0.08 | Line: DAGUPAN - ALAMINOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4115
4 | 1116 | 4116 | 1102403005 | Region XI (Davao Region) | Davao del Sur | City of Digos | Cogon | 6.7589 | 125.3694 | U | 10000 | 3.4 | 2941 | 882 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.54 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 68.91 | 68.91 | 35.53 | 52.22 | D - Other node or line within 3 km | 1.54 | 0.54 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4116
4 | 1117 | 4117 | 0307113018 | Region III (Central Luzon) | Zambales | Santa Cruz | Pagatpat | 15.7816 | 119.9006 | R | 3733 | 3.8 | 982 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.8 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 68.74 | 68.74 | 35.7 | 52.22 | C - Line within 0.5 km; node over 1 km | 1.8 | 0.24 | Line: SANTA CRUZ TO ALAMINOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4117
4 | 1118 | 4118 | 0402120041 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan VII | 14.3356 | 120.8638 | R | 2681 | 3.4 | 789 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.8 | 1.72 | Tier 2B: Moderate GIDA Inclusion | 62.75 | 62.75 | 41.68 | 52.22 | D - Other node or line within 3 km | 3.8 | 1.72 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4118
4 | 1119 | 4119 | 0401018016 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Santol | 13.9685 | 121.1046 | R | 2166 | 3.6 | 602 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 3.73 | Tier 2B: Moderate GIDA Inclusion | 61.36 | 61.36 | 43.08 | 52.22 | D - Other node or line within 3 km | 1.71 | 3.73 | Node: MKB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4119
4 | 1120 | 4120 | 0103306021 | Region I (Ilocos Region) | La Union | Bangar | Nagsabaran | 16.8951 | 120.4158 | R | 1487 | 3.7 | 402 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 56.3 | 56.3 | 48.14 | 52.22 | B - Node 0.5-1 km | 0.99 | 0.84 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4120
4 | 1121 | 4121 | 0907220010 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sirawai | Danganon | 7.587 | 122.1391 | R | 638 | 3.6 | 177 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.89 | 24.6 | Tier 1B: High GIDA Priority | 35.28 | 35.28 | 69.15 | 52.22 | F - Nearest node and line over 5 km | 31.89 | 24.48 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4121
4 | 1122 | 4122 | 0205705004 | Region II (Cagayan Valley) | Quirino | Saguday | Rizal | 16.5446 | 121.5631 | R | 2953 | 3.9 | 757 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.09 | 0.1 | Tier 2A: High Commercial ROI | 72.18 | 72.18 | 32.25 | 52.21 | A - Node within 0.5 km | 0.09 | 0.1 | Node: SGQ001 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4122
4 | 1123 | 4123 | 0203120019 | Region II (Cagayan Valley) | Isabela | Naguilian | San Manuel | 17.0218 | 121.8651 | R | 2683 | 3.8 | 706 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 69.81 | 69.81 | 34.61 | 52.21 | B - Node 0.5-1 km | 0.57 | 0.53 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4123
4 | 1124 | 4124 | 1606819022 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Telaje | 9.0741 | 126.1964 | U | 7962 | 4.1 | 1942 | 583 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 68.51 | 68.51 | 35.91 | 52.21 | A - Node within 0.5 km | 0.33 | 0.22 | Line: Route | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4124
4 | 1125 | 4125 | 1102504010 | Region XI (Davao Region) | Davao Oriental | Caraga | Poblacion | 7.3318 | 126.567 | U | 5614 | 3.6 | 1559 | 468 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.16 | 55.61 | Tier 1B: High GIDA Priority | 45.71 | 45.71 | 58.72 | 52.21 | F - Nearest node and line over 5 km | 57.16 | 999999 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4125
4 | 1126 | 4126 | 0300809016 | Region III (Central Luzon) | Bataan | Orani | Centro I | 14.7905 | 120.4946 | R | 513 | 3.6 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.67 | 0.33 | Tier 1B: High GIDA Priority | 44.58 | 44.58 | 59.85 | 52.21 | C - Line within 0.5 km; node over 1 km | 4.67 | 0.25 | Line: ORANI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4126
4 | 1127 | 4127 | 1908710029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Panatan | 17.254 | 122.228 | R | 2317 | 3.8 | 610 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 40.57 | 40.57 | 63.84 | 52.21 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4127
4 | 1128 | 4128 | 1906607002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Bakud | 17.2519 | 122.2331 | R | 1483 | 6 | 247 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.64 | Tier 1B: High GIDA Priority | 35.54 | 35.54 | 68.87 | 52.21 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4128
4 | 1129 | 4129 | 1903638025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Malinao | 17.2544 | 122.2285 | R | 808 | 5.7 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 32.85 | 32.85 | 71.56 | 52.21 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4129
4 | 1130 | 4130 | 0601912021 | Region VI (Western Visayas) | Capiz | Pontevedra | Rizal | 11.4369 | 122.8389 | R | 4445 | 3.8 | 1170 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 69.17 | 69.17 | 35.22 | 52.2 | C - Line within 0.5 km; node over 1 km | 4.59 | 0.14 | Line: ROXAS - SARA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4130
4 | 1131 | 4131 | 0305406031 | Region III (Central Luzon) | Pampanga | Floridablanca | Sta. Monica | 14.965 | 120.5118 | R | 4159 | 4 | 1040 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 35.53 | 52.2 | D - Other node or line within 3 km | 1.83 | 1.52 | Line: 48 CORE (4X12) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4131
4 | 1132 | 4132 | 0300804036 | Region III (Central Luzon) | Bataan | Dinalupihan | San Ramon | 14.8692 | 120.4626 | U | 3953 | 3.6 | 1098 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 63.57 | 63.57 | 40.83 | 52.2 | B - Node 0.5-1 km | 0.7 | 0.16 | Line: Path Measure | Survey short node lateral; confirm port/fiber capacity, access and route. | 4132
4 | 1133 | 4133 | 1001311011 | Region X (Northern Mindanao) | Bukidnon | Libona | Pongol | 8.2426 | 124.8008 | R | 4590 | 3.8 | 1208 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.45 | 15.42 | Tier 2B: Moderate GIDA Inclusion | 58.12 | 58.12 | 46.27 | 52.2 | F - Nearest node and line over 5 km | 12.45 | 15.4 | Node: MFB002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4133
4 | 1134 | 4134 | 1705309011 | MIMAROPA Region | Palawan | Coron | Lajala | 11.9772 | 120.1955 | R | 2199 | 3.9 | 564 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.44 | 102.99 | Tier 2B: Moderate GIDA Inclusion | 51.92 | 51.92 | 52.47 | 52.2 | F - Nearest node and line over 5 km | 6.44 | 999999 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4134
4 | 1135 | 4135 | 0501711046 | Region V (Bicol Region) | Camarines Sur | Caramoan | Tabiguian | 13.835 | 123.7952 | R | 1020 | 4.2 | 243 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10 | 36.49 | Tier 1B: High GIDA Priority | 42.17 | 42.17 | 62.23 | 52.2 | F - Nearest node and line over 5 km | 10 | 36.44 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4135
4 | 1136 | 4136 | 0704607008 | Region VII (Central Visayas) | Negros Oriental | Bindoy | Danao | 9.8018 | 123.0882 | R | 1265 | 3.8 | 333 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.32 | 4.97 | Tier 1B: High GIDA Priority | 38.67 | 38.67 | 65.73 | 52.2 | F - Nearest node and line over 5 km | 19.32 | 11.49 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4136
4 | 1137 | 4137 | 0403402011 | Region IV-A (CALABARZON) | Laguna | Bay | San Isidro | 14.1856 | 121.2858 | R | 3019 | 3.3 | 915 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.69 | Tier 2A: High Commercial ROI | 70.13 | 70.13 | 34.25 | 52.19 | B - Node 0.5-1 km | 0.77 | 0.69 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4137
4 | 1138 | 4138 | 0301410001 | Region III (Central Luzon) | Bulacan | City of Malolos | Anilao | 14.8425 | 120.7977 | R | 3149 | 3.5 | 900 | 270 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 2.15 | Tier 2B: Moderate GIDA Inclusion | 65.11 | 65.11 | 39.27 | 52.19 | D - Other node or line within 3 km | 1.59 | 2.23 | Node: MSB003 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4138
4 | 1139 | 4139 | 1001312032 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Manalog | 7.9718 | 125.0394 | R | 1158 | 3.8 | 305 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.78 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 48.72 | 48.72 | 55.66 | 52.19 | F - Nearest node and line over 5 km | 7.78 | 7.21 | Line: DAMULOG - VALENCIA - QUEZON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4139
4 | 1140 | 4140 | 0600409003 | Region VI (Western Visayas) | Aklan | Libacao | Batobato | 11.4228 | 122.2794 | R | 474 | 3.9 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.25 | 18.19 | Tier 1B: High GIDA Priority | 35.05 | 35.05 | 69.34 | 52.19 | F - Nearest node and line over 5 km | 18.25 | 18.19 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4140
4 | 1141 | 4141 | 0200903001 | Region II (Cagayan Valley) | Batanes | Ivana | Radiwan | 20.3679 | 121.9144 | R | 391 | 3 | 130 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 213.4 | 208.97 | Tier 1B: High GIDA Priority | 33 | 33 | 71.39 | 52.19 | F - Nearest node and line over 5 km | 212.06 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4141
4 | 1142 | 4142 | 1903631029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Sarang | 15.6455 | 122.5681 | R | 966 | 5.7 | 169 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.1 | 82.96 | Tier 1B: High GIDA Priority | 32.84 | 32.84 | 71.54 | 52.19 | F - Nearest node and line over 5 km | 84.1 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4142
4 | 1143 | 4143 | 1004315005 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Poblacion | 8.5593 | 124.3527 | U | 5423 | 3.9 | 1391 | 417 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.13 | Tier 2A: High Commercial ROI | 71.74 | 71.74 | 32.63 | 52.18 | A - Node within 0.5 km | 0.21 | 0.13 | Line: CDO - ILIGAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4143
4 | 1144 | 4144 | 0105519014 | Region I (Ilocos Region) | Pangasinan | Dasol | Poblacion | 15.9898 | 119.8798 | R | 3471 | 3.6 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.56 | Tier 2A: High Commercial ROI | 71.11 | 71.11 | 33.25 | 52.18 | A - Node within 0.5 km | 0.47 | 0.53 | Node: DSP001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4144
4 | 1145 | 4145 | 1004314008 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Poblacion | 8.5755 | 124.445 | U | 3866 | 3.9 | 991 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.24 | 0.3 | Tier 2A: High Commercial ROI | 70.18 | 70.18 | 34.18 | 52.18 | A - Node within 0.5 km | 0.24 | 0.28 | Node: LGD001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4145
4 | 1146 | 4146 | 0105516007 | Region I (Ilocos Region) | Pangasinan | Burgos | Poblacion | 16.0548 | 119.8647 | U | 3491 | 3.6 | 970 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 68.55 | 68.55 | 35.81 | 52.18 | A - Node within 0.5 km | 0.28 | 0.07 | Line: BURGOS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4146
4 | 1147 | 4147 | 0306909016 | Region III (Central Luzon) | Tarlac | Moncada | Capaoayan | 15.7304 | 120.5669 | R | 3371 | 3.9 | 864 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 68.44 | 68.44 | 35.91 | 52.18 | D - Other node or line within 3 km | 1.13 | 0.54 | Line: MONCADA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4147
4 | 1148 | 4148 | 0306916023 | Region III (Central Luzon) | Tarlac | City of Tarlac | Burot | 15.4141 | 120.6006 | U | 8013 | 3.9 | 2055 | 616 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.12 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 67.71 | 67.71 | 36.66 | 52.18 | A - Node within 0.5 km | 0.12 | 0.05 | Line: HH55A Pipe | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4148
4 | 1149 | 4149 | 1206317001 | Region XII (SOCCSKSARGEN) | South Cotabato | Tupi | Acmonan | 6.3414 | 124.9974 | U | 4641 | 3.6 | 1289 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.46 | 7.89 | Tier 2B: Moderate GIDA Inclusion | 56.65 | 56.65 | 47.71 | 52.18 | F - Nearest node and line over 5 km | 5.46 | 7.89 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4149
4 | 1150 | 4150 | 0401006008 | Region IV-A (CALABARZON) | Batangas | Bauan | Barangay II | 13.7999 | 120.9689 | U | 3073 | 3.6 | 854 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 2.96 | Tier 2B: Moderate GIDA Inclusion | 55.27 | 55.27 | 49.08 | 52.18 | D - Other node or line within 3 km | 2.3 | 2.96 | Node: BUN002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4150
4 | 1151 | 4151 | 1208007007 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Datal Batong | 6.3749 | 125.1248 | R | 3095 | 3.9 | 794 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.04 | 15.41 | Tier 2B: Moderate GIDA Inclusion | 50.21 | 50.21 | 54.14 | 52.18 | F - Nearest node and line over 5 km | 16.04 | 15.4 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4151
4 | 1152 | 4152 | 0405647058 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Roque Zone II | 13.982 | 121.5785 | R | 869 | 3.8 | 229 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.59 | 2.19 | Tier 1B: High GIDA Priority | 44.19 | 44.19 | 60.16 | 52.18 | D - Other node or line within 3 km | 3.59 | 2.19 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4152
4 | 1153 | 4153 | 0205703016 | Region II (Cagayan Valley) | Quirino | Diffun | Ifugao Village | 16.4542 | 121.4283 | R | 1340 | 3.9 | 344 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.7 | 14.49 | Tier 1B: High GIDA Priority | 39.97 | 39.97 | 64.38 | 52.18 | F - Nearest node and line over 5 km | 12.7 | 14.48 | Node: CBQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4153
4 | 1154 | 4154 | 0205013013 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Roxas | 16.5178 | 121.1851 | U | 9738 | 3.8 | 2563 | 769 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.55 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 68.31 | 68.31 | 36.03 | 52.17 | B - Node 0.5-1 km | 0.55 | 0.19 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4154
4 | 1155 | 4155 | 0405806007 | Region IV-A (CALABARZON) | Rizal | Cardona | Calahan | 14.4908 | 121.2345 | U | 5775 | 3.6 | 1604 | 481 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.77 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 64.76 | 64.76 | 39.59 | 52.17 | B - Node 0.5-1 km | 0.77 | 0.1 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Survey short node lateral; confirm port/fiber capacity, access and route. | 4155
4 | 1156 | 4156 | 0405812009 | Region IV-A (CALABARZON) | Rizal | Tanay | Pinagkamaligan | 14.5741 | 121.3443 | R | 3471 | 3.6 | 964 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.18 | 9.51 | Tier 2B: Moderate GIDA Inclusion | 62.05 | 62.05 | 42.28 | 52.17 | E - Nearest node or line 3-5 km | 4.18 | 9.5 | Node: TNR001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4156
4 | 1157 | 4157 | 1206312011 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Maligo | 6.2736 | 125.1344 | R | 3622 | 3.6 | 1006 | 302 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.96 | 8.81 | Tier 2B: Moderate GIDA Inclusion | 59.68 | 59.68 | 44.66 | 52.17 | F - Nearest node and line over 5 km | 9.96 | 10.09 | Node: PMK001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4157
4 | 1158 | 4158 | 1001313007 | Region X (Northern Mindanao) | Bukidnon | Malitbog | Sampiano | 8.4898 | 124.8704 | R | 1406 | 3.8 | 370 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.06 | 9.24 | Tier 1B: High GIDA Priority | 41.63 | 41.63 | 62.7 | 52.17 | F - Nearest node and line over 5 km | 13.06 | 9.23 | Line: CAGAYAN DE ORO - MALAYBALAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4158
4 | 1159 | 4159 | 0600614040 | Region VI (Western Visayas) | Antique | San Remigio | Rizal | 10.9237 | 122.1767 | R | 357 | 3.9 | 92 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.65 | 24.36 | Tier 1B: High GIDA Priority | 32.72 | 32.72 | 71.61 | 52.17 | F - Nearest node and line over 5 km | 31.65 | 24.19 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4159
4 | 1160 | 4160 | 0501710012 | Region V (Bicol Region) | Camarines Sur | Canaman | San Agustin | 13.6455 | 123.183 | R | 3184 | 4.2 | 758 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.08 | Tier 2A: High Commercial ROI | 70.25 | 70.25 | 34.07 | 52.16 | C - Line within 0.5 km; node over 1 km | 1.18 | 0.08 | Line: EE07-HH08 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4160
4 | 1161 | 4161 | 1401105002 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Amgaleyguey | 16.7362 | 120.8065 | R | 3224 | 3.5 | 921 | 276 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.87 | 0.57 | Tier 2B: Moderate GIDA Inclusion | 67.22 | 67.22 | 37.09 | 52.16 | D - Other node or line within 3 km | 2.87 | 0.57 | Line: LA TRINIDAD-SAGADA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4161
4 | 1162 | 4162 | 0300806014 | Region III (Central Luzon) | Bataan | Limay | San Francisco de Asis | 14.5686 | 120.5955 | U | 6571 | 3.6 | 1825 | 548 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.83 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 65.51 | 65.51 | 38.81 | 52.16 | B - Node 0.5-1 km | 0.83 | 0.07 | Line: 36 CORE 3X12 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4162
4 | 1163 | 4163 | 0301419026 | Region III (Central Luzon) | Bulacan | San Ildefonso | Poblacion | 15.0792 | 120.944 | U | 5123 | 3.5 | 1464 | 439 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 64.9 | 64.9 | 39.42 | 52.16 | B - Node 0.5-1 km | 0.59 | 0.32 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4163
4 | 1164 | 4164 | 0405814007 | Region IV-A (CALABARZON) | Rizal | Teresa | Prinza | 14.5363 | 121.2172 | U | 7180 | 3.6 | 1994 | 598 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 64.1 | 64.1 | 40.22 | 52.16 | D - Other node or line within 3 km | 1.81 | 0.53 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4164
4 | 1165 | 4165 | 0401011006 | Region IV-A (CALABARZON) | Batangas | Laurel | Bugaan East | 14.0428 | 120.9391 | R | 2217 | 3.6 | 616 | 185 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 5.84 | Tier 2B: Moderate GIDA Inclusion | 57.91 | 57.91 | 46.42 | 52.16 | D - Other node or line within 3 km | 1.3 | 5.84 | Node: LRB002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4165
4 | 1166 | 4166 | 1903639009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Matimos | 17.2546 | 122.2286 | R | 792 | 5.7 | 139 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.37 | 34.26 | Tier 1B: High GIDA Priority | 32.77 | 32.77 | 71.56 | 52.16 | F - Nearest node and line over 5 km | 29.37 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4166
4 | 1167 | 4167 | 1906612066 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | South Silumpak | 17.2555 | 122.2295 | R | 1861 | 6 | 310 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 32.7 | 32.7 | 71.62 | 52.16 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4167
4 | 1168 | 4168 | 0702215016 | Region VII (Central Visayas) | Cebu | Carmen | Poblacion | 10.5851 | 124.0161 | U | 5569 | 3.8 | 1466 | 440 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 67.08 | 67.08 | 37.22 | 52.15 | B - Node 0.5-1 km | 0.98 | 0.16 | Line: BOGO - DANAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4168
4 | 1169 | 4169 | 0103307015 | Region I (Ilocos Region) | La Union | Bauang | Central West | 16.5105 | 120.3381 | U | 4014 | 3.7 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.74 | 0.83 | Tier 2B: Moderate GIDA Inclusion | 60.2 | 60.2 | 44.1 | 52.15 | D - Other node or line within 3 km | 2.74 | 0.83 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4169
4 | 1170 | 4170 | 0300801006 | Region III (Central Luzon) | Bataan | Abucay | Laon | 14.7221 | 120.5349 | R | 2523 | 3.6 | 701 | 210 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.18 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 59.99 | 59.99 | 44.31 | 52.15 | C - Line within 0.5 km; node over 1 km | 4.18 | 0.08 | Line: 48 CORE 4X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4170
4 | 1171 | 4171 | 0203121009 | Region II (Cagayan Valley) | Isabela | Palanan | Marikit | 17.0693 | 122.4451 | R | 959 | 3.8 | 252 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.66 | 56.16 | Tier 1B: High GIDA Priority | 31.91 | 31.91 | 72.38 | 52.15 | F - Nearest node and line over 5 km | 45.66 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4171
4 | 1172 | 4172 | 0401022029 | Region IV-A (CALABARZON) | Batangas | San Jose | Santo Cristo | 13.8698 | 121.1136 | U | 3271 | 3.6 | 909 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 1.25 | Tier 2B: Moderate GIDA Inclusion | 61.45 | 61.45 | 42.82 | 52.14 | D - Other node or line within 3 km | 1.4 | 1.24 | Line: UG SSB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4172
4 | 1173 | 4173 | 0804805021 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Gebalagnan | 12.3769 | 124.6814 | R | 427 | 4.3 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.15 | 68.77 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 72.09 | 52.14 | F - Nearest node and line over 5 km | 69.15 | 999999 | Node: MGS001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4173
4 | 1174 | 4174 | 1380606199 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 592 | 12.0575 | 122.6944 | U | 2119 | 3.78 | 560 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 50 | 27.37 | Tier 1B: High GIDA Priority | 31.04 | 31.04 | 73.25 | 52.14 | F - Nearest node and line over 5 km | 52.44 | 999999 | Node: RCZ001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4174
4 | 1175 | 4175 | 0300802002 | Region III (Central Luzon) | Bataan | Bagac | Banawang | 14.62 | 120.3867 | R | 3614 | 3.6 | 1004 | 301 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 68.49 | 68.49 | 35.77 | 52.13 | D - Other node or line within 3 km | 2 | 0.57 | Line: Subic-Bagac AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4175
4 | 1176 | 4176 | 0304924017 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Tikiw | 15.3105 | 120.8623 | R | 3172 | 3.5 | 906 | 272 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.49 | 3.09 | Tier 2B: Moderate GIDA Inclusion | 67.35 | 67.35 | 36.9 | 52.13 | A - Node within 0.5 km | 0.49 | 3.09 | Node: SAN001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4176
4 | 1177 | 4177 | 0403404016 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Diezmo | 14.228 | 121.2713 | U | 7259 | 3.3 | 2200 | 660 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.32 | 5.45 | Tier 2B: Moderate GIDA Inclusion | 57.52 | 57.52 | 46.74 | 52.13 | F - Nearest node and line over 5 km | 5.32 | 5.45 | Node: BAY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4177
4 | 1178 | 4178 | 0102822008 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Darasdas | 18.1115 | 120.7787 | R | 1502 | 3.7 | 406 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 1.45 | Tier 2B: Moderate GIDA Inclusion | 55.45 | 55.45 | 48.81 | 52.13 | D - Other node or line within 3 km | 1.51 | 1.42 | Line: SEGMENT 2 SOLSONA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4178
4 | 1179 | 4179 | 0103301018 | Region I (Ilocos Region) | La Union | Agoo | San Joaquin Sur | 16.3378 | 120.3582 | R | 1511 | 3.7 | 408 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 54.78 | 54.78 | 49.47 | 52.13 | C - Line within 0.5 km; node over 1 km | 1.92 | 0.48 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4179
4 | 1180 | 4180 | 0405811016 | Region IV-A (CALABARZON) | Rizal | San Mateo | Silangan | 14.6577 | 121.1511 | U | 56529 | 3.6 | 15702 | 4711 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 3.24 | 2.49 | Tier 2B: Moderate GIDA Inclusion | 50.99 | 50.99 | 53.26 | 52.13 | D - Other node or line within 3 km | 3.24 | 2.2 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4180
4 | 1181 | 4181 | 1381000011 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Moonwalk | 14.4928 | 121.0039 | U | 71860 | 3.26 | 22027 | 6608 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 1.57 | 0.52 | Tier 1B: High GIDA Priority | 46.26 | 46.26 | 58.01 | 52.13 | D - Other node or line within 3 km | 1.57 | 0.52 | Line: Existing 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4181
4 | 1182 | 4182 | 1900704004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Maluso | Guanan North | 6.5483 | 121.866 | R | 1300 | 5.1 | 255 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 46.34 | 46.33 | Tier 1B: High GIDA Priority | 35.1 | 35.1 | 69.16 | 52.13 | F - Nearest node and line over 5 km | 46.34 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4182
4 | 1183 | 4183 | 1381100116 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 116 | 14.5159 | 120.8572 | U | 1348 | 3.5 | 385 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.62 | 9.85 | Tier 1B: High GIDA Priority | 34.61 | 34.61 | 69.65 | 52.13 | F - Nearest node and line over 5 km | 5.62 | 9.82 | Node: CVC001 -TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4183
4 | 1184 | 4184 | 1600307001 | Region XIII (Caraga) | Agusan del Sur | Rosario | Bayugan 3 | 8.3022 | 126.0044 | U | 14871 | 3.9 | 3813 | 1144 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.26 | 0.29 | Tier 2A: High Commercial ROI | 73.77 | 73.77 | 30.47 | 52.12 | A - Node within 0.5 km | 0.26 | 0.05 | Line: TRENTO - BUENAVISTA CLS | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4184
4 | 1185 | 4185 | 0403406001 | Region IV-A (CALABARZON) | Laguna | Calauan | Balayhangin | 14.1411 | 121.3099 | U | 6106 | 3.3 | 1850 | 555 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 65.65 | 65.65 | 38.59 | 52.12 | B - Node 0.5-1 km | 0.7 | 0.29 | Line: AE SPO001 TO CLL001-NEW | Survey short node lateral; confirm port/fiber capacity, access and route. | 4185
4 | 1186 | 4186 | 0103314054 | Region I (Ilocos Region) | La Union | City of San Fernando | Santiago Norte | 16.6151 | 120.3359 | R | 4099 | 3.7 | 1108 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 2.01 | Tier 2B: Moderate GIDA Inclusion | 64.83 | 64.83 | 39.41 | 52.12 | D - Other node or line within 3 km | 2.32 | 2.01 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4186
4 | 1187 | 4187 | 0403425014 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Antonio | 14.1094 | 121.392 | U | 65077 | 3.3 | 19720 | 5916 | Band n50 (1.5 GHz, 100 MHz TDD) | 6 | 1 | 0.15 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 54.38 | 54.38 | 49.86 | 52.12 | A - Node within 0.5 km | 0.15 | 0.14 | Line: AE NGL001 TO SPO001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4187
4 | 1188 | 4188 | 0201529037 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 12 | 17.6369 | 121.7113 | U | 2338 | 3.9 | 599 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.09 | 1.61 | Tier 2B: Moderate GIDA Inclusion | 49.87 | 49.87 | 54.36 | 52.12 | D - Other node or line within 3 km | 4.09 | 1.59 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4188
4 | 1189 | 4189 | 1380606178 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 572 | 13.484 | 122.6594 | U | 1617 | 4.23 | 382 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.86 | 14.53 | Tier 1B: High GIDA Priority | 34.99 | 34.99 | 69.24 | 52.12 | E - Nearest node or line 3-5 km | 4.86 | 14.53 | Node: SNQ003-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4189
4 | 1190 | 4190 | 1108202036 | Region XI (Davao Region) | Davao de Oro | Laak | Panamoren | 7.8362 | 125.6966 | R | 1073 | 3.7 | 290 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.62 | 24.79 | Tier 1B: High GIDA Priority | 34.42 | 34.42 | 69.82 | 52.12 | F - Nearest node and line over 5 km | 39.62 | 34.58 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4190
4 | 1191 | 4191 | 1903610031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Kibolos | 17.2544 | 122.2284 | R | 768 | 5.7 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 71.64 | 52.12 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4191
4 | 1192 | 4192 | 1903610037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Macadar | 17.2544 | 122.2284 | R | 715 | 5.7 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.35 | 34.24 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 71.63 | 52.12 | F - Nearest node and line over 5 km | 29.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4192
4 | 1193 | 4193 | 0501709001 | Region V (Bicol Region) | Camarines Sur | Camaligan | Dugcal | 13.6262 | 123.1607 | R | 4830 | 4.2 | 1150 | 345 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.41 | 2.86 | Tier 2A: High Commercial ROI | 74 | 74 | 30.23 | 52.11 | D - Other node or line within 3 km | 1.41 | 2.71 | Node: CLC001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4193
4 | 1194 | 4194 | 1705318013 | MIMAROPA Region | Palawan | Roxas | New Barbacan | 10.3291 | 119.3496 | R | 5417 | 3.9 | 1389 | 417 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.43 | Tier 2A: High Commercial ROI | 71.98 | 71.98 | 32.24 | 52.11 | C - Line within 0.5 km; node over 1 km | 1.38 | 0.43 | Line: TAYTAY - PUERTO PRINCESA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4194
4 | 1195 | 4195 | 0103317010 | Region I (Ilocos Region) | La Union | Santo Tomas | Damortis | 16.2442 | 120.405 | R | 2712 | 3.7 | 733 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.6 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 64.39 | 64.39 | 39.83 | 52.11 | C - Line within 0.5 km; node over 1 km | 5.6 | 0.05 | Line: SANTO TOMAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4195
4 | 1196 | 4196 | 0504101029 | Region V (Bicol Region) | Masbate | Aroroy | Panique | 12.4585 | 123.3916 | U | 6477 | 4.1 | 1580 | 474 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 8.04 | Tier 2B: Moderate GIDA Inclusion | 58.43 | 58.43 | 45.79 | 52.11 | F - Nearest node and line over 5 km | 5.83 | 23.97 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4196
4 | 1197 | 4197 | 1903626080 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tamparan | Pindolonan Mariatao Sarip | 13.5261 | 123.0282 | R | 783 | 5.7 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 1.55 | Tier 2B: Moderate GIDA Inclusion | 51.3 | 51.3 | 52.91 | 52.11 | D - Other node or line within 3 km | 1.61 | 1.55 | Line: PASACAO CLS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4197
4 | 1198 | 4198 | 0504102010 | Region V (Bicol Region) | Masbate | Baleno | Gabi | 12.4251 | 123.4661 | R | 646 | 4.1 | 158 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.18 | 4.3 | Tier 2B: Moderate GIDA Inclusion | 48.05 | 48.05 | 56.16 | 52.11 | F - Nearest node and line over 5 km | 6.18 | 15.42 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4198
4 | 1199 | 4199 | 1900709013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Al-Barka | Lookbisaya | 7.5877 | 122.1837 | R | 1994 | 5.1 | 391 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.98 | 20.34 | Tier 1B: High GIDA Priority | 35.06 | 35.06 | 69.17 | 52.11 | F - Nearest node and line over 5 km | 26.98 | 20.19 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4199
4 | 1200 | 4200 | 1903638041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Sigayan | 17.2415 | 122.2477 | R | 656 | 5.7 | 115 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.11 | 35.85 | Tier 1B: High GIDA Priority | 32.54 | 32.54 | 71.69 | 52.11 | F - Nearest node and line over 5 km | 30.11 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4200
4 | 1201 | 4201 | 0802609057 | Region VIII (Eastern Visayas) | Eastern Samar | Guiuan | Victory Island | 11.0413 | 125.6949 | R | 592 | 3.9 | 152 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74 | 71.62 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 72.03 | 52.11 | F - Nearest node and line over 5 km | 74 | 999999 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4201
4 | 1202 | 4202 | 0301407016 | Region III (Central Luzon) | Bulacan | Calumpit | Meysulao | 14.9079 | 120.7396 | R | 4474 | 3.5 | 1278 | 383 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.04 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 67.91 | 67.91 | 36.28 | 52.1 | D - Other node or line within 3 km | 3.04 | 2.92 | Line: 24 CORE (3X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4202
4 | 1203 | 4203 | 0405608012 | Region IV-A (CALABARZON) | Quezon | Candelaria | Masalukot I | 14.2544 | 121.4261 | U | 6103 | 3.8 | 1606 | 482 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.08 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 61.15 | 61.15 | 43.05 | 52.1 | D - Other node or line within 3 km | 3.08 | 0.99 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4203
4 | 1204 | 4204 | 0102815014 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Saguigui | 18.5599 | 120.8245 | R | 917 | 3.7 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.43 | 1.72 | Tier 2B: Moderate GIDA Inclusion | 50.89 | 50.89 | 53.3 | 52.1 | D - Other node or line within 3 km | 6.43 | 1.72 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4204
4 | 1205 | 4205 | 1705104008 | MIMAROPA Region | Occidental Mindoro | Lubang | Vigo | 13.8246 | 120.1822 | R | 1961 | 3.9 | 503 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.33 | 48.42 | Tier 1B: High GIDA Priority | 43.74 | 43.74 | 60.45 | 52.1 | F - Nearest node and line over 5 km | 48.33 | 999999 | Node: CTG001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4205
4 | 1206 | 4206 | 1907011013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Taungoh | 4.7063 | 119.492 | R | 3655 | 5.8 | 630 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 40.37 | 40.37 | 63.82 | 52.1 | F - Nearest node and line over 5 km | 376.33 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4206
4 | 1207 | 4207 | 1903631023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Paigoay Coda | 15.6412 | 122.5387 | R | 930 | 5.7 | 163 | 49 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 82.39 | 81.16 | Tier 1B: High GIDA Priority | 32.66 | 32.66 | 71.54 | 52.1 | F - Nearest node and line over 5 km | 82.39 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4207
4 | 1208 | 4208 | 1903638018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Kitaon | 17.2399 | 122.2348 | R | 428 | 5.7 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.88 | 34.46 | Tier 1B: High GIDA Priority | 32.65 | 32.65 | 71.56 | 52.1 | F - Nearest node and line over 5 km | 28.88 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4208
4 | 1209 | 4209 | 0702216020 | Region VII (Central Visayas) | Cebu | Catmon | Flores | 10.7178 | 124.0124 | R | 3458 | 3.8 | 910 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.66 | 0.13 | Tier 2A: High Commercial ROI | 71.38 | 71.38 | 32.8 | 52.09 | C - Line within 0.5 km; node over 1 km | 2.66 | 0.13 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4209
4 | 1210 | 4210 | 0301416010 | Region III (Central Luzon) | Bulacan | Paombong | San Isidro II | 14.8364 | 120.7713 | U | 12555 | 3.5 | 3587 | 1076 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.16 | 4.03 | Tier 2B: Moderate GIDA Inclusion | 65.1 | 65.1 | 39.08 | 52.09 | D - Other node or line within 3 km | 2.16 | 4.82 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4210
4 | 1211 | 4211 | 0307110008 | Region III (Central Luzon) | Zambales | San Felipe | Rosete | 15.0643 | 120.0838 | R | 1582 | 3.8 | 416 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.53 | 1.54 | Tier 2B: Moderate GIDA Inclusion | 60.18 | 60.18 | 44.01 | 52.09 | D - Other node or line within 3 km | 1.53 | 1.54 | Node: SFZ001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4211
4 | 1212 | 4212 | 0201520004 | Region II (Cagayan Valley) | Cagayan | Piat | Gumarueng | 17.7757 | 121.455 | R | 2101 | 3.9 | 539 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.99 | 5.91 | Tier 2B: Moderate GIDA Inclusion | 57.91 | 57.91 | 46.26 | 52.09 | D - Other node or line within 3 km | 2.99 | 5.68 | Node: PTC001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4212
4 | 1213 | 4213 | 1003516022 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Tangcal | 8.0482 | 124.1757 | R | 1343 | 4.2 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.66 | 8.65 | Tier 1B: High GIDA Priority | 45.97 | 45.97 | 58.21 | 52.09 | F - Nearest node and line over 5 km | 11.66 | 8.59 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4213
4 | 1214 | 4214 | 0201506049 | Region II (Cagayan Valley) | Cagayan | Baggao | C. Verzosa | 17.9948 | 121.9345 | R | 767 | 3.9 | 197 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.49 | 25.75 | Tier 1B: High GIDA Priority | 41.52 | 41.52 | 62.65 | 52.09 | F - Nearest node and line over 5 km | 6.49 | 26.94 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4214
4 | 1215 | 4215 | 0907311005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Bolisong | 7.7766 | 123.2122 | R | 908 | 3.9 | 233 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.08 | 2.28 | Tier 1B: High GIDA Priority | 39.17 | 39.17 | 65.02 | 52.09 | D - Other node or line within 3 km | 18.08 | 2.28 | Line: PAGADIAN - BUUG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4215
4 | 1216 | 4216 | 1705318025 | MIMAROPA Region | Palawan | Roxas | Taradungan | 10.3696 | 119.5308 | R | 1497 | 3.9 | 384 | 115 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.19 | 16.89 | Tier 1B: High GIDA Priority | 38.16 | 38.16 | 66.02 | 52.09 | F - Nearest node and line over 5 km | 21.19 | 16.88 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4216
4 | 1217 | 4217 | 1380605047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 345 | 12.3393 | 121.3089 | U | 1332 | 4.34 | 307 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.8 | 2.84 | Tier 1B: High GIDA Priority | 33.88 | 33.88 | 70.3 | 52.09 | D - Other node or line within 3 km | 3.8 | 2.83 | Line: ROXAS - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4217
4 | 1218 | 4218 | 0802606016 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | Libertad | 12.185 | 125.2495 | R | 670 | 3.9 | 172 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 108.51 | 111.26 | Tier 1B: High GIDA Priority | 32.58 | 32.58 | 71.61 | 52.09 | F - Nearest node and line over 5 km | 108.51 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4218
4 | 1219 | 4219 | 1903638029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Marawi | 17.2751 | 122.2237 | R | 596 | 5.7 | 105 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.49 | 34.49 | Tier 1B: High GIDA Priority | 32.51 | 32.51 | 71.67 | 52.09 | F - Nearest node and line over 5 km | 30.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4219
4 | 1220 | 4220 | 1380601070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 70 | 13.5307 | 120.7258 | U | 2405 | 4.04 | 595 | 178 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.73 | 18.34 | Tier 1B: High GIDA Priority | 31.91 | 31.91 | 72.28 | 52.09 | F - Nearest node and line over 5 km | 19.73 | 17.9 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4220
4 | 1221 | 4221 | 0702247010 | Region VII (Central Visayas) | Cebu | Sogod | Damolog | 10.7691 | 124.0037 | R | 3987 | 3.8 | 1049 | 315 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.91 | 0.3 | Tier 2A: High Commercial ROI | 75.59 | 75.59 | 28.58 | 52.08 | C - Line within 0.5 km; node over 1 km | 1.91 | 0.2 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4221
4 | 1222 | 4222 | 0603043004 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Balabag | 10.8257 | 122.5432 | R | 3784 | 3.8 | 996 | 299 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.96 | 0.96 | Tier 2A: High Commercial ROI | 71.53 | 71.53 | 32.62 | 52.08 | B - Node 0.5-1 km | 0.96 | 0.96 | Node: SBI001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4222
4 | 1223 | 4223 | 0105520005 | Region I (Ilocos Region) | Pangasinan | Infanta | Cato | 15.8387 | 119.915 | R | 4888 | 3.6 | 1358 | 407 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.49 | 0.22 | Tier 2A: High Commercial ROI | 70.39 | 70.39 | 33.77 | 52.08 | C - Line within 0.5 km; node over 1 km | 1.49 | 0.22 | Line: SANTA CRUZ TO ALAMINOS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4223
4 | 1224 | 4224 | 1001312018 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Indalaza | 7.9 | 124.9882 | R | 2214 | 3.8 | 583 | 175 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 60.29 | 60.29 | 43.87 | 52.08 | D - Other node or line within 3 km | 1.84 | 0.52 | Line: DAMULOG - VALENCIA - QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4224
4 | 1225 | 4225 | 0405619026 | Region IV-A (CALABARZON) | Quezon | Gumaca | Mabini | 13.9183 | 122.0961 | R | 1988 | 3.8 | 523 | 157 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 58.77 | 58.77 | 45.39 | 52.08 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.06 | Line: AE UNQ001 TO CDQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4225
4 | 1226 | 4226 | 1204712060 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Tinutulan | 7.1312 | 124.7078 | U | 4988 | 3.8 | 1313 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.63 | 10.56 | Tier 2B: Moderate GIDA Inclusion | 50.78 | 50.78 | 53.37 | 52.08 | F - Nearest node and line over 5 km | 12.63 | 10.56 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4226
4 | 1227 | 4227 | 0205009006 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Bua | 16.279 | 121.2403 | R | 1646 | 3.8 | 433 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.12 | 17.89 | Tier 2B: Moderate GIDA Inclusion | 47.72 | 47.72 | 56.45 | 52.08 | F - Nearest node and line over 5 km | 7.12 | 17.89 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4227
4 | 1228 | 4228 | 1906618006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Lapak | 17.2556 | 122.2297 | R | 2754 | 6 | 459 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 41.12 | 41.12 | 63.03 | 52.08 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4228
4 | 1229 | 4229 | 1903638002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Bantalan | 17.2508 | 122.232 | R | 674 | 5.7 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.38 | 34.48 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 71.56 | 52.08 | F - Nearest node and line over 5 km | 29.38 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4229
4 | 1230 | 4230 | 1907010005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Dalo-dalo | 17.2558 | 122.2298 | R | 1679 | 5.8 | 289 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 32.17 | 32.17 | 71.98 | 52.08 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4230
4 | 1231 | 4231 | 1380601100 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 100 | 12.0163 | 122.5856 | U | 2340 | 4.96 | 472 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.69 | 18.18 | Tier 1B: High GIDA Priority | 28.77 | 28.77 | 75.4 | 52.08 | F - Nearest node and line over 5 km | 42.69 | 999999 | Node: KOK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4231
4 | 1232 | 4232 | 0803714016 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone II | 11.2931 | 124.6381 | R | 4790 | 3.8 | 1261 | 378 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.14 | Tier 2A: High Commercial ROI | 79.96 | 79.96 | 24.18 | 52.07 | A - Node within 0.5 km | 0.29 | 0.13 | Line: ORMOC CLS - CAPOOCAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4232
4 | 1233 | 4233 | 0306904004 | Region III (Central Luzon) | Tarlac | Capas | Cutcut 1st | 15.3276 | 120.5908 | U | 12578 | 3.9 | 3225 | 968 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.16 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 67.5 | 67.5 | 36.64 | 52.07 | C - Line within 0.5 km; node over 1 km | 2.16 | 0.06 | Line: PIPE 23-51 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4233
4 | 1234 | 4234 | 0601905014 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Sur | 11.5309 | 122.6811 | R | 2503 | 3.8 | 659 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.79 | 1.68 | Tier 2B: Moderate GIDA Inclusion | 67.03 | 67.03 | 37.1 | 52.07 | D - Other node or line within 3 km | 1.79 | 1.68 | Line: ROXAS - ILOILO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4234
4 | 1235 | 4235 | 1204702028 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Palanggalan | 7.2366 | 124.7217 | R | 2684 | 3.8 | 706 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.1 | 7.71 | Tier 2B: Moderate GIDA Inclusion | 53.32 | 53.32 | 50.83 | 52.07 | F - Nearest node and line over 5 km | 9.1 | 7.71 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4235
4 | 1236 | 4236 | 1001316008 | Region X (Northern Mindanao) | Bukidnon | Pangantucan | Kipadukan | 7.6566 | 124.8367 | R | 1668 | 3.8 | 439 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.7 | 17.47 | Tier 1B: High GIDA Priority | 46.19 | 46.19 | 57.95 | 52.07 | F - Nearest node and line over 5 km | 9.7 | 17.43 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4236
4 | 1237 | 4237 | 0806025028 | Region VIII (Eastern Visayas) | Samar | San Jorge | Gayondato | 12.0388 | 124.8965 | R | 252 | 4.1 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 85.21 | 85.16 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.45 | 52.07 | F - Nearest node and line over 5 km | 85.21 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4237
4 | 1238 | 4238 | 0907313012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Lubusan | 7.6727 | 123.2212 | R | 1170 | 3.9 | 300 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.38 | 12.68 | Tier 1B: High GIDA Priority | 35.97 | 35.97 | 68.17 | 52.07 | F - Nearest node and line over 5 km | 19.38 | 12.62 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4238
4 | 1239 | 4239 | 0401005063 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 17 | 13.7418 | 121.0832 | U | 119 | 3.6 | 33 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.16 | 2.73 | Tier 1B: High GIDA Priority | 34.38 | 34.38 | 69.77 | 52.07 | D - Other node or line within 3 km | 3.16 | 2.73 | Line: BAUAN - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4239
4 | 1240 | 4240 | 1381100093 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 93 | 14.5061 | 120.8898 | U | 506 | 3.44 | 147 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 7.12 | Tier 1B: High GIDA Priority | 29.99 | 29.99 | 74.14 | 52.07 | E - Nearest node or line 3-5 km | 3.5 | 7.1 | Node: CVC001 -TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4240
4 | 1241 | 4241 | 0305410014 | Region III (Central Luzon) | Pampanga | Macabebe | San Rafael | 14.9058 | 120.7042 | R | 3811 | 4 | 953 | 286 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.62 | 2.64 | Tier 2B: Moderate GIDA Inclusion | 65.44 | 65.44 | 38.68 | 52.06 | D - Other node or line within 3 km | 1.62 | 6.56 | Node: MSP001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4241
4 | 1242 | 4242 | 0304930035 | Region III (Central Luzon) | Nueva Ecija | Talavera | Maestrang Kikay | 15.5834 | 120.9206 | U | 4291 | 3.5 | 1226 | 368 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 64.98 | 64.98 | 39.14 | 52.06 | A - Node within 0.5 km | 0.21 | 0.09 | Line: SEGMENT 17 (ZARAGOSA - SAN JOSE) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4242
4 | 1243 | 4243 | 1004321014 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Poblacion | 8.5205 | 124.5718 | U | 3486 | 3.9 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 63.13 | 63.13 | 40.99 | 52.06 | A - Node within 0.5 km | 0.33 | 0.25 | Line: Implem. 96f aerial FOC | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4243
4 | 1244 | 4244 | 1903638007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Dimalama | 17.2631 | 122.2226 | R | 675 | 5.7 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 33.94 | Tier 1B: High GIDA Priority | 32.59 | 32.59 | 71.53 | 52.06 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4244
4 | 1245 | 4245 | 1903613049 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Bacayawan | 17.235 | 122.2041 | R | 576 | 5.7 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 25.98 | 31.17 | Tier 1B: High GIDA Priority | 28.48 | 28.48 | 75.64 | 52.06 | F - Nearest node and line over 5 km | 25.98 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4245
4 | 1246 | 4246 | 0403416037 | Region IV-A (CALABARZON) | Laguna | Majayjay | Santa Catalina | 14.1472 | 121.4711 | R | 2238 | 3.3 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 69.15 | 69.15 | 34.96 | 52.05 | A - Node within 0.5 km | 0.47 | 0.31 | Line: LILIW - LUCENA | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4246
4 | 1247 | 4247 | 0301417005 | Region III (Central Luzon) | Bulacan | Plaridel | Bintog | 14.9015 | 120.8906 | R | 4793 | 3.5 | 1369 | 411 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.3 | 0.77 | Tier 2B: Moderate GIDA Inclusion | 66.91 | 66.91 | 37.19 | 52.05 | D - Other node or line within 3 km | 4.3 | 0.77 | Line: PLARIDEL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4247
4 | 1248 | 4248 | 0305403028 | Region III (Central Luzon) | Pampanga | Arayat | San Nicolas | 15.1248 | 120.7833 | U | 9371 | 4 | 2343 | 703 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.31 | 0.8 | Tier 2B: Moderate GIDA Inclusion | 64.61 | 64.61 | 39.49 | 52.05 | D - Other node or line within 3 km | 2.31 | 0.8 | Line: EXISTING | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4248
4 | 1249 | 4249 | 0405619047 | Region IV-A (CALABARZON) | Quezon | Gumaca | Tabing Dagat | 13.9277 | 122.1062 | U | 2559 | 3.8 | 673 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.53 | Tier 2B: Moderate GIDA Inclusion | 56.86 | 56.86 | 47.24 | 52.05 | B - Node 0.5-1 km | 0.57 | 0.53 | Line: UG GCQ001 TO LZQ001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4249
4 | 1250 | 4250 | 0802611007 | Region VIII (Eastern Visayas) | Eastern Samar | Jipapad | Cagmanaba | 12.2636 | 125.1877 | R | 918 | 3.9 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 115.63 | 118.48 | Tier 1B: High GIDA Priority | 38.42 | 38.42 | 65.67 | 52.05 | F - Nearest node and line over 5 km | 115.63 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4250
4 | 1251 | 4251 | 0304930009 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bantug | 15.5555 | 120.9128 | R | 5367 | 3.5 | 1533 | 460 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.02 | 1.4 | Tier 2B: Moderate GIDA Inclusion | 68.71 | 68.71 | 35.37 | 52.04 | D - Other node or line within 3 km | 3.02 | 1.39 | Line: TALAVERA CABLE SYSTEMS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4251
4 | 1252 | 4252 | 0600613017 | Region VI (Western Visayas) | Antique | San Jose | Funda-Dalipe | 10.7602 | 121.9317 | U | 7419 | 3.9 | 1902 | 571 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 35.4 | 52.04 | B - Node 0.5-1 km | 0.73 | 0.66 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Survey short node lateral; confirm port/fiber capacity, access and route. | 4252
4 | 1253 | 4253 | 0305411013 | Region III (Central Luzon) | Pampanga | Magalang | San Nicolas 1st | 15.2162 | 120.6601 | U | 3794 | 4 | 948 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 60.11 | 60.11 | 43.97 | 52.04 | C - Line within 0.5 km; node over 1 km | 2.49 | 0.18 | Line: EXISTING | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4253
4 | 1254 | 4254 | 0405637006 | Region IV-A (CALABARZON) | Quezon | Quezon | Del Pilar | 14.0923 | 122.1151 | R | 395 | 3.8 | 104 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.81 | 17.73 | Tier 1B: High GIDA Priority | 39.97 | 39.97 | 64.11 | 52.04 | F - Nearest node and line over 5 km | 10.81 | 17.73 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4254
4 | 1255 | 4255 | 1903602022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Balabagan | Buenavista | 17.2516 | 122.2405 | R | 755 | 5.7 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.15 | 35.38 | Tier 1B: High GIDA Priority | 32.54 | 32.54 | 71.54 | 52.04 | F - Nearest node and line over 5 km | 30.15 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4255
4 | 1256 | 4256 | 0203111003 | Region II (Cagayan Valley) | Isabela | Divilacan | Dicambangan | 17.3063 | 122.3193 | R | 369 | 3.8 | 97 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.5 | 45.22 | Tier 1B: High GIDA Priority | 28.67 | 28.67 | 75.41 | 52.04 | F - Nearest node and line over 5 km | 40.5 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4256
4 | 1257 | 4257 | 1004320008 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Poblacion | 8.4326 | 124.2948 | U | 5900 | 3.9 | 1513 | 454 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.49 | 0.45 | Tier 2A: High Commercial ROI | 71.48 | 71.48 | 32.59 | 52.03 | A - Node within 0.5 km | 0.49 | 0.45 | Line: CDO - ILIGAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4257
4 | 1258 | 4258 | 0305422012 | Region III (Central Luzon) | Pampanga | Sasmuan | Santo Tomas | 14.9474 | 120.6232 | R | 3424 | 4 | 856 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.92 | 1.95 | Tier 2A: High Commercial ROI | 70.03 | 70.03 | 34.03 | 52.03 | D - Other node or line within 3 km | 2.92 | 1.93 | Line: foc | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4258
4 | 1259 | 4259 | 0501737038 | Region V (Bicol Region) | Camarines Sur | Tinambac | San Vicente | 13.8173 | 123.3266 | R | 695 | 4.2 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 52.29 | 52.29 | 51.78 | 52.03 | C - Line within 0.5 km; node over 1 km | 1.3 | 0.16 | Line: BACKBONE 96C AE - 64,646m | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4259
4 | 1260 | 4260 | 1003508006 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Inudaran | 8.0984 | 123.8866 | R | 407 | 4.2 | 97 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.43 | 0.88 | Tier 1B: High GIDA Priority | 45.39 | 45.39 | 58.67 | 52.03 | D - Other node or line within 3 km | 11.43 | 0.88 | Line: ILIGAN - PAGADIAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4260
4 | 1261 | 4261 | 0806025033 | Region VIII (Eastern Visayas) | Samar | San Jorge | Cabugao | 12.0293 | 124.8961 | R | 132 | 4.1 | 32 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.19 | 84.14 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.37 | 52.03 | F - Nearest node and line over 5 km | 84.19 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4261
4 | 1262 | 4262 | 1380606091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 485 | 13.3218 | 121.0621 | U | 1800 | 4.38 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.56 | 5.46 | Tier 1B: High GIDA Priority | 35.25 | 35.25 | 68.8 | 52.03 | F - Nearest node and line over 5 km | 5.56 | 5.44 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4262
4 | 1263 | 4263 | 1903633017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Buadiposo-Buntong | Lumbatan Manacab | 17.2679 | 122.2336 | R | 455 | 5.7 | 80 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.73 | 35.21 | Tier 1B: High GIDA Priority | 32.49 | 32.49 | 71.57 | 52.03 | F - Nearest node and line over 5 km | 30.73 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4263
4 | 1264 | 4264 | 1004313004 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Kabulawan | 8.8166 | 124.7911 | R | 3661 | 3.9 | 939 | 282 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.28 | 0.19 | Tier 2A: High Commercial ROI | 74.4 | 74.4 | 29.63 | 52.02 | C - Line within 0.5 km; node over 1 km | 1.28 | 0.19 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4264
4 | 1265 | 4265 | 0401005082 | Region IV-A (CALABARZON) | Batangas | Batangas City | Sampaga | 13.7549 | 121.1037 | R | 4590 | 3.6 | 1275 | 382 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 4.19 | Tier 2B: Moderate GIDA Inclusion | 68.11 | 68.11 | 35.92 | 52.02 | B - Node 0.5-1 km | 0.59 | 4.14 | Node: BCY003 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4265
4 | 1266 | 4266 | 0405647043 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Mateuna | 14.0242 | 121.596 | U | 5954 | 3.8 | 1567 | 470 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 65.66 | 65.66 | 38.38 | 52.02 | A - Node within 0.5 km | 0.28 | 0.13 | Line: LBQ001 TO GCQ001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4266
4 | 1267 | 4267 | 0600417012 | Region VI (Western Visayas) | Aklan | Tangalan | Tamalagon | 11.7532 | 122.2588 | R | 2897 | 3.9 | 743 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.6 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 64.99 | 64.99 | 39.05 | 52.02 | F - Nearest node and line over 5 km | 5.6 | 11.63 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4267
4 | 1268 | 4268 | 0601913016 | Region VI (Western Visayas) | Capiz | President Roxas | Pinamihagan | 11.4294 | 122.9481 | R | 399 | 3.8 | 105 | 32 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.56 | 1.24 | Tier 1B: High GIDA Priority | 45.33 | 45.33 | 58.7 | 52.02 | D - Other node or line within 3 km | 13.56 | 1.24 | Line: ROXAS - SARA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4268
4 | 1269 | 4269 | 0603030113 | Region VI (Western Visayas) | Iloilo | Miagao | Tigmalapad | 10.7106 | 122.1821 | R | 529 | 3.8 | 139 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.03 | 8.41 | Tier 1B: High GIDA Priority | 33.97 | 33.97 | 70.07 | 52.02 | F - Nearest node and line over 5 km | 22.03 | 8.41 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4269
4 | 1270 | 4270 | 0802606044 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | Tanauan | 12.0458 | 125.4202 | R | 642 | 3.9 | 165 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 100.53 | 102.9 | Tier 1B: High GIDA Priority | 32.43 | 32.43 | 71.61 | 52.02 | F - Nearest node and line over 5 km | 100.53 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4270
4 | 1271 | 4271 | 0201529017 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Capatan | 17.6176 | 121.7498 | R | 3901 | 3.9 | 1000 | 300 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.76 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 66.28 | 66.28 | 37.73 | 52.01 | D - Other node or line within 3 km | 3.76 | 0.81 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4271
4 | 1272 | 4272 | 0306903027 | Region III (Central Luzon) | Tarlac | Camiling | Malacampa | 15.6402 | 120.4118 | U | 6156 | 3.9 | 1578 | 473 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 65.83 | 65.83 | 38.2 | 52.01 | A - Node within 0.5 km | 0.31 | 0.06 | Line: 33,700 mtrs. | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4272
4 | 1273 | 4273 | 1208006001 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Daan Suyan | 6.069 | 125.3951 | R | 4159 | 3.9 | 1066 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.55 | 22.33 | Tier 2B: Moderate GIDA Inclusion | 56.98 | 56.98 | 47.03 | 52.01 | F - Nearest node and line over 5 km | 13.55 | 22.33 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4273
4 | 1274 | 4274 | 0205703006 | Region II (Cagayan Valley) | Quirino | Diffun | Bannawag | 16.6002 | 121.5701 | R | 2107 | 3.9 | 540 | 162 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.31 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 54.34 | 54.34 | 49.67 | 52.01 | C - Line within 0.5 km; node over 1 km | 6.31 | 0.03 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4274
4 | 1275 | 4275 | 0402108013 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Corregidor Pob. | 14.3441 | 120.9039 | R | 1180 | 3.4 | 347 | 104 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.91 | 5.33 | Tier 2B: Moderate GIDA Inclusion | 47.05 | 47.05 | 56.97 | 52.01 | E - Nearest node or line 3-5 km | 3.91 | 5.33 | Node: DMC006 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4275
4 | 1276 | 4276 | 1606818008 | Region XIII (Caraga) | Surigao del Sur | Tago | Camagong | 8.9994 | 126.1933 | R | 1070 | 4.1 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.63 | 1.84 | Tier 1B: High GIDA Priority | 46.51 | 46.51 | 57.5 | 52.01 | D - Other node or line within 3 km | 8.63 | 1.84 | Line: Route | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4276
4 | 1277 | 4277 | 0806004042 | Region VIII (Eastern Visayas) | Samar | Calbiga | Hindang | 11.5492 | 125.1021 | R | 125 | 4.1 | 30 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 36.1 | 38.78 | Tier 1B: High GIDA Priority | 37 | 37 | 67.02 | 52.01 | F - Nearest node and line over 5 km | 36.1 | 38.78 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4277
4 | 1278 | 4278 | 0804812010 | Region VIII (Eastern Visayas) | Northern Samar | Mapanas | Naparasan | 12.4231 | 125.2345 | R | 526 | 4.3 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 124.99 | 124.16 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.33 | 52.01 | F - Nearest node and line over 5 km | 124.99 | 999999 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4278
4 | 1279 | 4279 | 0502004004 | Region V (Bicol Region) | Catanduanes | Caramoran | Buenavista | 13.9877 | 124.1824 | R | 605 | 4.2 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.83 | 79.83 | Tier 1B: High GIDA Priority | 32.34 | 32.34 | 71.68 | 52.01 | F - Nearest node and line over 5 km | 41.83 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4279
4 | 1280 | 4280 | 0704603002 | Region VII (Central Visayas) | Negros Oriental | Bacong | Banilad | 9.2708 | 123.2885 | U | 5739 | 3.8 | 1510 | 453 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.45 | Tier 2B: Moderate GIDA Inclusion | 69.93 | 69.93 | 34.07 | 52 | C - Line within 0.5 km; node over 1 km | 2.01 | 0.45 | Line: KABANGKALAN - BACONG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4280
4 | 1281 | 4281 | 0105517004 | Region I (Ilocos Region) | Pangasinan | Calasiao | Bued | 16.0175 | 120.3831 | U | 5943 | 3.6 | 1651 | 495 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 65.46 | 65.46 | 38.53 | 52 | B - Node 0.5-1 km | 0.59 | 0.09 | Line: CALASIAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4281
4 | 1282 | 4282 | 0403423011 | Region IV-A (CALABARZON) | Laguna | Rizal | Tuy | 14.12 | 121.387 | R | 2025 | 3.6 | 562 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.99 | Tier 2B: Moderate GIDA Inclusion | 64.6 | 64.6 | 39.4 | 52 | D - Other node or line within 3 km | 1.22 | 0.99 | Line: SPO001 TO LBQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4282
4 | 1283 | 4283 | 0304927015 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tagumpay | 15.3608 | 120.9421 | R | 1295 | 3.5 | 370 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 55.97 | 55.97 | 48.03 | 52 | B - Node 0.5-1 km | 0.7 | 0.27 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 4283
4 | 1284 | 4284 | 1380606079 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 473 | 13.5747 | 122.2732 | U | 1395 | 4.24 | 329 | 99 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.32 | 3.66 | Tier 1B: High GIDA Priority | 32.8 | 32.8 | 71.19 | 52 | E - Nearest node or line 3-5 km | 6.32 | 3.65 | Line: AE CTQ001 TO MCQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4284
4 | 1285 | 4285 | 0205701005 | Region II (Cagayan Valley) | Quirino | Aglipay | Ligaya | 16.4934 | 121.5859 | R | 1795 | 3.9 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.03 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 56.06 | 56.06 | 47.92 | 51.99 | C - Line within 0.5 km; node over 1 km | 2.03 | 0.12 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4285
4 | 1286 | 4286 | 0604531006 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay III | 10.8672 | 123.1 | R | 1523 | 3.7 | 412 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.82 | 4.55 | Tier 2B: Moderate GIDA Inclusion | 50.07 | 50.07 | 53.9 | 51.99 | E - Nearest node or line 3-5 km | 4.82 | 4.55 | Line: TALISAY - VICTORIAS | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4286
4 | 1287 | 4287 | 1003520006 | Region X (Northern Mindanao) | Lanao del Norte | Tagoloan | Malimbato | 8.1193 | 124.2623 | R | 1432 | 4.2 | 341 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.23 | 3.43 | Tier 1B: High GIDA Priority | 46 | 46 | 57.98 | 51.99 | E - Nearest node or line 3-5 km | 12.23 | 3.18 | Line: BALOI | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4287
4 | 1288 | 4288 | 1380601092 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 92 | 13.2097 | 120.5107 | U | 2519 | 4.74 | 531 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.76 | 52.25 | Tier 1B: High GIDA Priority | 30.25 | 30.25 | 73.73 | 51.99 | F - Nearest node and line over 5 km | 53.76 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4288
4 | 1289 | 4289 | 0702211013 | Region VII (Central Visayas) | Cebu | City of Bogo | La Paz | 10.9983 | 123.9822 | R | 4204 | 3.8 | 1106 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.08 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 68.12 | 68.12 | 35.85 | 51.98 | C - Line within 0.5 km; node over 1 km | 6.08 | 0.1 | Line: 9697 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4289
4 | 1290 | 4290 | 0600413009 | Region VI (Western Visayas) | Aklan | Malinao | Kinalangay Viejo | 11.6024 | 122.2778 | R | 2084 | 3.9 | 534 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.08 | 7.43 | Tier 2B: Moderate GIDA Inclusion | 58.9 | 58.9 | 45.05 | 51.98 | E - Nearest node or line 3-5 km | 3.08 | 7.41 | Node: MLK001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4290
4 | 1291 | 4291 | 1908819010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Sapakan | 17.2552 | 122.2292 | R | 3419 | 4.7 | 727 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 43.61 | 43.61 | 60.36 | 51.98 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4291
4 | 1292 | 4292 | 1403214017 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Mangali Centro | 17.3008 | 121.2372 | R | 265 | 4.3 | 62 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.25 | 7.81 | Tier 1B: High GIDA Priority | 41.4 | 41.4 | 62.56 | 51.98 | F - Nearest node and line over 5 km | 10.25 | 7.59 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4292
4 | 1293 | 4293 | 0804805053 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Tinowaran | 12.4394 | 124.6605 | R | 566 | 4.3 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.43 | 63.83 | Tier 1B: High GIDA Priority | 32.2 | 32.2 | 71.77 | 51.98 | F - Nearest node and line over 5 km | 64.43 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4293
4 | 1294 | 4294 | 1380601174 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 174 | 12.5331 | 121.5012 | U | 751 | 4.32 | 174 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.88 | 1.95 | Tier 1B: High GIDA Priority | 32.01 | 32.01 | 71.96 | 51.98 | D - Other node or line within 3 km | 6.88 | 1.9 | Line: ROXAS - SAN JOSE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4294
4 | 1295 | 4295 | 0607902002 | Region VI (Western Visayas) | Guimaras | Jordan | Alaguisoc | 10.6221 | 122.5931 | R | 3299 | 3.8 | 868 | 260 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.41 | 9.23 | Tier 2B: Moderate GIDA Inclusion | 56.77 | 56.77 | 47.17 | 51.97 | F - Nearest node and line over 5 km | 9.41 | 9.23 | Line: ROXAS - ILOILO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4295
4 | 1296 | 4296 | 0205009024 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Wangal | 16.3418 | 121.3914 | R | 1418 | 3.8 | 373 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.74 | 25.57 | Tier 1B: High GIDA Priority | 42.37 | 42.37 | 61.57 | 51.97 | F - Nearest node and line over 5 km | 10.74 | 25.55 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4296
4 | 1297 | 4297 | 1380610045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 730 | 12.066 | 121.3395 | U | 2443 | 3.37 | 726 | 218 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.46 | 25.07 | Tier 1B: High GIDA Priority | 35.4 | 35.4 | 68.54 | 51.97 | F - Nearest node and line over 5 km | 29.46 | 24.99 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4297
4 | 1298 | 4298 | 0802617002 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Bagacay | 12.0774 | 125.4335 | R | 234 | 3.9 | 60 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 104.32 | 106.7 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 71.75 | 51.97 | F - Nearest node and line over 5 km | 104.32 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4298
4 | 1299 | 4299 | 0604527002 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 2 | 9.7489 | 122.4091 | R | 4282 | 3.7 | 1157 | 347 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.09 | Tier 2A: High Commercial ROI | 74.38 | 74.38 | 29.54 | 51.96 | B - Node 0.5-1 km | 0.68 | 0.09 | Line: SIPALAY TO BAYAWAN-84,748m | Survey short node lateral; confirm port/fiber capacity, access and route. | 4299
4 | 1300 | 4300 | 0402115028 | Region IV-A (CALABARZON) | Cavite | Naic | San Roque | 14.3099 | 120.7719 | R | 4809 | 3.4 | 1414 | 424 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.12 | Tier 2A: High Commercial ROI | 70.67 | 70.67 | 33.25 | 51.96 | C - Line within 0.5 km; node over 1 km | 1.3 | 0.1 | Line: MARAGONDON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4300
4 | 1301 | 4301 | 0702247004 | Region VII (Central Visayas) | Cebu | Sogod | Bawo | 10.7406 | 124.0087 | R | 2884 | 3.8 | 759 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 0.24 | Tier 2A: High Commercial ROI | 70.01 | 70.01 | 33.9 | 51.96 | C - Line within 0.5 km; node over 1 km | 1.35 | 0.02 | Line: BOGO - DANAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4301
4 | 1302 | 4302 | 0203126021 | Region II (Cagayan Valley) | Isabela | Roxas | San Rafael | 17.1025 | 121.6136 | R | 3848 | 3.8 | 1013 | 304 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.5 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 69.32 | 69.32 | 34.59 | 51.96 | C - Line within 0.5 km; node over 1 km | 1.5 | 0.25 | Line: ROXAS - CABATUAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4302
4 | 1303 | 4303 | 0405812020 | Region IV-A (CALABARZON) | Rizal | Tanay | Wawa | 14.4928 | 121.285 | U | 8036 | 3.6 | 2232 | 670 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.5 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 67.25 | 67.25 | 36.68 | 51.96 | A - Node within 0.5 km | 0.5 | 0.47 | Line: TAYTAY TO SNL001 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4303
4 | 1304 | 4304 | 0304926012 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Malasin | 15.8074 | 121.0007 | U | 9389 | 3.5 | 2683 | 805 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 66.13 | 66.13 | 37.8 | 51.96 | C - Line within 0.5 km; node over 1 km | 1.98 | 0.16 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4304
4 | 1305 | 4305 | 0305403017 | Region III (Central Luzon) | Pampanga | Arayat | Plazang Luma | 15.151 | 120.7672 | U | 5689 | 4 | 1422 | 427 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.09 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 63.81 | 63.81 | 40.11 | 51.96 | C - Line within 0.5 km; node over 1 km | 1.09 | 0.16 | Line: 24 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4305
4 | 1306 | 4306 | 0403419013 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Barangay II | 14.2752 | 121.4533 | U | 2128 | 3.3 | 645 | 194 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.37 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 56.56 | 56.56 | 47.36 | 51.96 | A - Node within 0.5 km | 0.37 | 0.15 | Line: SEGMENT 23 (FAMY - STA CRUZ) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4306
4 | 1307 | 4307 | 1908709024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Tagudtongan | 17.2541 | 122.2282 | R | 5123 | 4.3 | 1191 | 357 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 49.86 | 49.86 | 54.07 | 51.96 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4307
4 | 1308 | 4308 | 1381300010 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagong Silangan | 14.6969 | 121.1098 | U | 113572 | 4.04 | 28109 | 8433 | Band n50 (1.5 GHz, 100 MHz TDD) | 9 | 1 | 1.15 | 1.1 | Tier 2B: Moderate GIDA Inclusion | 47 | 47 | 56.93 | 51.96 | D - Other node or line within 3 km | 1.15 | 1.09 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4308
4 | 1309 | 4309 | 0405646035 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Roque | 13.9818 | 122.4331 | R | 305 | 3.8 | 80 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.13 | 5.11 | Tier 1B: High GIDA Priority | 40.13 | 40.13 | 63.78 | 51.96 | F - Nearest node and line over 5 km | 5.13 | 5.11 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4309
4 | 1310 | 4310 | 0806025016 | Region VIII (Eastern Visayas) | Samar | San Jorge | Libertad | 12.0487 | 124.9173 | R | 168 | 4.1 | 41 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 86.9 | 86.85 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.23 | 51.96 | F - Nearest node and line over 5 km | 86.9 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4310
4 | 1311 | 4311 | 0907315018 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Mahayag | Paraiso | 8.2225 | 123.4132 | R | 912 | 3.9 | 234 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.55 | 35.41 | Tier 1B: High GIDA Priority | 32.07 | 32.07 | 71.84 | 51.96 | F - Nearest node and line over 5 km | 35.55 | 46.09 | Node: AUZ001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4311
4 | 1312 | 4312 | 0307105010 | Region III (Central Luzon) | Zambales | Iba | Lipay-Dingin-Panibuatan | 15.3217 | 119.977 | R | 3572 | 3.8 | 940 | 282 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.6 | 0.53 | Tier 2A: High Commercial ROI | 70.78 | 70.78 | 33.11 | 51.95 | B - Node 0.5-1 km | 0.6 | 0.53 | Line: IBA MUNICIPALITY | Survey short node lateral; confirm port/fiber capacity, access and route. | 4312
4 | 1313 | 4313 | 0405615005 | Region IV-A (CALABARZON) | Quezon | Dolores | Bungoy | 13.9956 | 121.369 | R | 3668 | 3.8 | 965 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.18 | 3.73 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 35.02 | 51.95 | D - Other node or line within 3 km | 2.18 | 3.74 | Node: DLQ002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4313
4 | 1314 | 4314 | 0103314050 | Region I (Ilocos Region) | La Union | City of San Fernando | Sagayad | 16.5938 | 120.3326 | R | 3174 | 3.7 | 858 | 257 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 1.32 | Tier 2B: Moderate GIDA Inclusion | 66.92 | 66.92 | 36.99 | 51.95 | D - Other node or line within 3 km | 1.92 | 1.32 | Line: AGOO - SAN FERNANDO AERIAL_SEGMENT 0 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4314
4 | 1315 | 4315 | 0307103018 | Region III (Central Luzon) | Zambales | Candelaria | Uacon | 15.6751 | 119.937 | R | 4038 | 3.8 | 1063 | 319 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.74 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 65.01 | 65.01 | 38.89 | 51.95 | C - Line within 0.5 km; node over 1 km | 5.74 | 0.05 | Line: IBA TO SANTA CRUZ | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4315
4 | 1316 | 4316 | 0403418005 | Region IV-A (CALABARZON) | Laguna | Paete | Ibaba del Sur | 14.3696 | 121.515 | R | 2496 | 3.3 | 756 | 227 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 3.77 | Tier 2B: Moderate GIDA Inclusion | 62.98 | 62.98 | 40.93 | 51.95 | E - Nearest node or line 3-5 km | 3.67 | 3.77 | Node: KYL002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4316
4 | 1317 | 4317 | 1004319011 | Region X (Northern Mindanao) | Misamis Oriental | Medina | North Poblacion | 8.9136 | 125.0142 | U | 5827 | 3.9 | 1494 | 448 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.19 | 0.48 | Tier 2A: High Commercial ROI | 70.06 | 70.06 | 33.81 | 51.94 | C - Line within 0.5 km; node over 1 km | 1.19 | 0.48 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4317
4 | 1318 | 4318 | 0305411014 | Region III (Central Luzon) | Pampanga | Magalang | San Nicolas 2nd | 15.2284 | 120.6765 | R | 4550 | 4 | 1138 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.34 | 1.62 | Tier 2B: Moderate GIDA Inclusion | 66.17 | 66.17 | 37.7 | 51.94 | D - Other node or line within 3 km | 4.34 | 1.61 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4318
4 | 1319 | 4319 | 0203130011 | Region II (Cagayan Valley) | Isabela | San Manuel | District 1 | 17.0153 | 121.6087 | R | 2932 | 3.8 | 772 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.25 | 2.6 | Tier 2B: Moderate GIDA Inclusion | 62.9 | 62.9 | 40.98 | 51.94 | D - Other node or line within 3 km | 4.25 | 2.6 | Line: ROXAS - CABATUAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4319
4 | 1320 | 4320 | 0701245005 | Region VII (Central Visayas) | Bohol | Tubigon | Bilangbilangan | 9.9877 | 123.8824 | R | 477 | 4 | 119 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.29 | 9.17 | Tier 1B: High GIDA Priority | 33.91 | 33.91 | 69.97 | 51.94 | F - Nearest node and line over 5 km | 22.29 | 9.16 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4320
4 | 1321 | 4321 | 0102934004 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay II | 17.5564 | 120.3833 | U | 482 | 3.8 | 127 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.2 | 2.8 | Tier 1B: High GIDA Priority | 33.59 | 33.59 | 70.28 | 51.94 | D - Other node or line within 3 km | 4.2 | 2.8 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4321
4 | 1322 | 4322 | 1102408014 | Region XI (Davao Region) | Davao del Sur | Malalag | New Baclayon | 6.5831 | 125.3702 | R | 4267 | 3.4 | 1255 | 376 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.41 | 1.59 | Tier 2B: Moderate GIDA Inclusion | 69.22 | 69.22 | 34.63 | 51.93 | D - Other node or line within 3 km | 3.41 | 1.58 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4322
4 | 1323 | 4323 | 0304928019 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Soledad | 15.4286 | 120.9949 | U | 7394 | 3.5 | 2113 | 634 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.04 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 68.06 | 68.06 | 35.8 | 51.93 | C - Line within 0.5 km; node over 1 km | 6.81 | 0.06 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4323
4 | 1324 | 4324 | 0702234015 | Region VII (Central Visayas) | Cebu | City of Naga | Lutac | 10.2486 | 123.725 | U | 5622 | 3.8 | 1479 | 444 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.76 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 65.75 | 65.75 | 38.1 | 51.93 | C - Line within 0.5 km; node over 1 km | 1.76 | 0.02 | Line: CEBU - TOLEDO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4324
4 | 1325 | 4325 | 0203106025 | Region II (Cagayan Valley) | Isabela | Cabagan | Masipi East | 16.9748 | 121.8122 | R | 2418 | 3.8 | 636 | 191 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.44 | 1.84 | Tier 2B: Moderate GIDA Inclusion | 61.76 | 61.76 | 42.1 | 51.93 | D - Other node or line within 3 km | 1.44 | 1.84 | Node: CNI002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4325
4 | 1326 | 4326 | 0203118022 | Region II (Cagayan Valley) | Isabela | Delfin Albano | San Nicolas | 17.2545 | 121.7994 | R | 904 | 3.8 | 238 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 55.62 | 55.62 | 48.24 | 51.93 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.05 | Line: Ilagan-Tumauini Segment | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4326
4 | 1327 | 4327 | 0102821008 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Isidro | 18.1457 | 120.6399 | R | 1120 | 3.7 | 303 | 91 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 5.61 | Tier 2B: Moderate GIDA Inclusion | 54.18 | 54.18 | 49.69 | 51.93 | D - Other node or line within 3 km | 1.22 | 5.61 | Node: SRI001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4327
4 | 1328 | 4328 | 1705320012 | MIMAROPA Region | Palawan | Taytay | Depla | 11.0858 | 119.5817 | R | 1509 | 3.9 | 387 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.41 | 30.36 | Tier 2B: Moderate GIDA Inclusion | 47.24 | 47.24 | 56.61 | 51.93 | F - Nearest node and line over 5 km | 7.41 | 30.19 | Node: TYW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4328
4 | 1329 | 4329 | 0806025026 | Region VIII (Eastern Visayas) | Samar | San Jorge | Sinit-an | 11.8986 | 124.8784 | R | 165 | 4.1 | 40 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.69 | 69.64 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.16 | 51.93 | F - Nearest node and line over 5 km | 69.69 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4329
4 | 1330 | 4330 | 0804808001 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Abaton | 12.4808 | 125.0406 | R | 518 | 4.3 | 120 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 102.98 | 102.14 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 71.68 | 51.93 | F - Nearest node and line over 5 km | 102.98 | 999999 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4330
4 | 1331 | 4331 | 0802617029 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Naga | 12.1738 | 125.3685 | R | 441 | 3.9 | 113 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 111.26 | 113.83 | Tier 1B: High GIDA Priority | 32.19 | 32.19 | 71.67 | 51.93 | F - Nearest node and line over 5 km | 111.26 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4331
4 | 1332 | 4332 | 0301419019 | Region III (Central Luzon) | Bulacan | San Ildefonso | Makapilapil | 15.0891 | 120.9416 | R | 2868 | 3.5 | 819 | 246 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 66.3 | 66.3 | 37.54 | 51.92 | C - Line within 0.5 km; node over 1 km | 1.69 | 0.27 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4332
4 | 1333 | 4333 | 0306904021 | Region III (Central Luzon) | Tarlac | Capas | Santo Rosario | 15.3217 | 120.5705 | U | 7292 | 3.9 | 1870 | 561 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.72 | 1.31 | Tier 2B: Moderate GIDA Inclusion | 61.47 | 61.47 | 42.38 | 51.92 | D - Other node or line within 3 km | 3.72 | 1.3 | Line: BAMBAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4333
4 | 1334 | 4334 | 1908819008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Pidsandawan | 17.2552 | 122.2292 | R | 2669 | 4.7 | 568 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.47 | 34.34 | Tier 1B: High GIDA Priority | 39.42 | 39.42 | 64.41 | 51.92 | F - Nearest node and line over 5 km | 29.47 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4334
4 | 1335 | 4335 | 0806009002 | Region VIII (Eastern Visayas) | Samar | Jiabong | Bugho | 11.8976 | 125.0216 | R | 282 | 4.1 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 73.19 | 75.56 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.15 | 51.92 | F - Nearest node and line over 5 km | 73.19 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4335
4 | 1336 | 4336 | 0806025017 | Region VIII (Eastern Visayas) | Samar | San Jorge | Lincoro | 11.9792 | 124.8861 | R | 267 | 4.1 | 65 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 78.53 | 78.48 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.16 | 51.92 | F - Nearest node and line over 5 km | 78.53 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4336
4 | 1337 | 4337 | 0806025031 | Region VIII (Eastern Visayas) | Samar | San Jorge | Bay-ang | 12.0148 | 124.9494 | R | 157 | 4.1 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 84.4 | 84.34 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.16 | 51.92 | F - Nearest node and line over 5 km | 84.4 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4337
4 | 1338 | 4338 | 1903612038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumbatan | Pantar | 17.2548 | 122.2288 | R | 1515 | 5.7 | 266 | 80 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.41 | 34.29 | Tier 1B: High GIDA Priority | 36.08 | 36.08 | 67.77 | 51.92 | F - Nearest node and line over 5 km | 29.41 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4338
4 | 1339 | 4339 | 1380606200 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 593 | 13.7796 | 122.2545 | U | 1628 | 4.16 | 391 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.63 | 9.69 | Tier 1B: High GIDA Priority | 31.48 | 31.48 | 72.36 | 51.92 | F - Nearest node and line over 5 km | 9.63 | 9.69 | Node: CTQ004 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4339
4 | 1340 | 4340 | 1380601046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 46 | 12.446 | 120.7 | U | 2173 | 4.34 | 501 | 150 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.99 | 39.85 | Tier 1B: High GIDA Priority | 29.46 | 29.46 | 74.38 | 51.92 | F - Nearest node and line over 5 km | 40.99 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4340
4 | 1341 | 4341 | 0504101001 | Region V (Bicol Region) | Masbate | Aroroy | Ambolong | 12.5106 | 123.3969 | R | 4642 | 4.1 | 1132 | 340 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.21 | 4.23 | Tier 2A: High Commercial ROI | 71.82 | 71.82 | 31.99 | 51.91 | A - Node within 0.5 km | 0.21 | 27.46 | Node: AYM001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4341
4 | 1342 | 4342 | 0301421037 | Region III (Central Luzon) | Bulacan | San Miguel | Poblacion | 15.1443 | 120.9769 | R | 3269 | 3.5 | 934 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.16 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 69.68 | 69.68 | 34.14 | 51.91 | C - Line within 0.5 km; node over 1 km | 1.16 | 0.15 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4342
4 | 1343 | 4343 | 0701219007 | Region VII (Central Visayas) | Bohol | Dauis | Poblacion | 9.6241 | 123.8573 | R | 3015 | 4 | 754 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 1.41 | Tier 2B: Moderate GIDA Inclusion | 68.32 | 68.32 | 35.49 | 51.91 | D - Other node or line within 3 km | 3.79 | 1.61 | Line: 11,428 mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4343
4 | 1344 | 4344 | 1380300030 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Urdaneta | 14.5651 | 121.052 | U | 4720 | 4.67 | 1011 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.92 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 56.41 | 56.41 | 47.42 | 51.91 | C - Line within 0.5 km; node over 1 km | 1.92 | 0.17 | Line: UG 144C via V-DUCT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4344
4 | 1345 | 4345 | 0402111020 | Region IV-A (CALABARZON) | Cavite | Kawit | Tabon II | 14.4422 | 120.904 | R | 1478 | 3.4 | 435 | 130 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.67 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 54.31 | 54.31 | 49.5 | 51.91 | D - Other node or line within 3 km | 2.67 | 0.62 | Line: KAWIT | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4345
4 | 1346 | 4346 | 0803708069 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Poblacion Zone 13 | 10.6746 | 124.8036 | R | 221 | 3.8 | 58 | 17 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 53.42 | 53.42 | 50.4 | 51.91 | B - Node 0.5-1 km | 0.58 | 0.34 | Line: ORMOC - BAYBAY | Survey short node lateral; confirm port/fiber capacity, access and route. | 4346
4 | 1347 | 4347 | 0907215005 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Siayan | Diongan | 8.1603 | 123.1298 | R | 2712 | 3.6 | 753 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 48.58 | 37.31 | Tier 1B: High GIDA Priority | 45.42 | 45.42 | 58.41 | 51.91 | F - Nearest node and line over 5 km | 48.58 | 37.31 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4347
4 | 1348 | 4348 | 1907002031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Silubog | 14.4794 | 121.6655 | R | 1849 | 5.8 | 319 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.9 | 22.31 | Tier 1B: High GIDA Priority | 44.32 | 44.32 | 59.51 | 51.91 | E - Nearest node or line 3-5 km | 4.9 | 22.28 | Node: RLQ003 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4348
4 | 1349 | 4349 | 0603046009 | Region VI (Western Visayas) | Iloilo | Tubungan | Bantayanan | 10.7858 | 122.2884 | R | 392 | 3.8 | 103 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.59 | 12.83 | Tier 1B: High GIDA Priority | 40.68 | 40.68 | 63.14 | 51.91 | F - Nearest node and line over 5 km | 15.59 | 12.7 | Line: 17,509 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4349
4 | 1350 | 4350 | 1380610046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 731 | 11.6012 | 121.4226 | U | 2933 | 4.1 | 715 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 68.8 | 67.59 | Tier 1B: High GIDA Priority | 35.05 | 35.05 | 68.77 | 51.91 | F - Nearest node and line over 5 km | 68.8 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4350
4 | 1351 | 4351 | 1402701016 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Poblacion | 16.9141 | 121.0601 | R | 2686 | 3.9 | 689 | 207 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.37 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 69.86 | 69.86 | 33.93 | 51.9 | A - Node within 0.5 km | 0.37 | 4.42 | Node: BEF001 - TYPE 2 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4351
4 | 1352 | 4352 | 0105521004 | Region I (Ilocos Region) | Pangasinan | Labrador | Laois | 16.0364 | 120.1381 | R | 2855 | 3.6 | 793 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.33 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 69.1 | 69.1 | 34.71 | 51.9 | C - Line within 0.5 km; node over 1 km | 2.33 | 0.21 | Line: LABRADOR | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4352
4 | 1353 | 4353 | 0304915016 | Region III (Central Luzon) | Nueva Ecija | Llanera | Bagumbayan | 15.6955 | 121.0379 | R | 3870 | 3.5 | 1106 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.86 | 5.26 | Tier 2B: Moderate GIDA Inclusion | 67.51 | 67.51 | 36.3 | 51.9 | E - Nearest node or line 3-5 km | 3.86 | 5.26 | Node: LLN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4353
4 | 1354 | 4354 | 0401031035 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 4 | 14.0884 | 121.1134 | U | 5389 | 3.6 | 1497 | 449 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 3.83 | Tier 2B: Moderate GIDA Inclusion | 60.39 | 60.39 | 43.42 | 51.9 | D - Other node or line within 3 km | 1.05 | 3.78 | Node: TNB002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4354
4 | 1355 | 4355 | 0102821017 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Nicolas | 18.1602 | 120.6496 | R | 1774 | 3.7 | 479 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 4.76 | Tier 2B: Moderate GIDA Inclusion | 59.95 | 59.95 | 43.84 | 51.9 | B - Node 0.5-1 km | 0.69 | 4.76 | Node: SRI001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4355
4 | 1356 | 4356 | 1908701011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Nabalawag | 17.2541 | 122.2281 | R | 7126 | 4.3 | 1657 | 497 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 51.23 | 51.23 | 52.57 | 51.9 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4356
4 | 1357 | 4357 | 0401005096 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Rita Aplaya | 13.7695 | 121.0304 | U | 1848 | 3.6 | 513 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 1.36 | Tier 2B: Moderate GIDA Inclusion | 50.94 | 50.94 | 52.85 | 51.9 | D - Other node or line within 3 km | 1.38 | 1.37 | Line: WP BYB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4357
4 | 1358 | 4358 | 0806021015 | Region VIII (Eastern Visayas) | Samar | Villareal | Lawa-an | 11.5066 | 124.9039 | R | 278 | 4.1 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.57 | 31.68 | Tier 1B: High GIDA Priority | 37.23 | 37.23 | 66.57 | 51.9 | F - Nearest node and line over 5 km | 31.57 | 31.68 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4358
4 | 1359 | 4359 | 1380601035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 35 | 11.7878 | 122.2379 | U | 2289 | 4.67 | 490 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.01 | 2.53 | Tier 1B: High GIDA Priority | 33.71 | 33.71 | 70.08 | 51.9 | F - Nearest node and line over 5 km | 10.01 | 15.35 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4359
4 | 1360 | 4360 | 0105520012 | Region I (Ilocos Region) | Pangasinan | Infanta | Poblacion | 15.8224 | 119.9069 | R | 3276 | 3.6 | 910 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.53 | 0.48 | Tier 2A: High Commercial ROI | 70.84 | 70.84 | 32.94 | 51.89 | B - Node 0.5-1 km | 0.53 | 0.37 | Line: SANTA CRUZ TO ALAMINOS | Survey short node lateral; confirm port/fiber capacity, access and route. | 4360
4 | 1361 | 4361 | 0105524062 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Poblacion | 15.9233 | 120.4127 | U | 8389 | 3.6 | 2330 | 699 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 68.08 | 68.08 | 35.7 | 51.89 | A - Node within 0.5 km | 0.33 | 0.37 | Node: MQP001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4361
4 | 1362 | 4362 | 1705105003 | MIMAROPA Region | Occidental Mindoro | Magsaysay | Caguray | 12.2834 | 121.1163 | R | 3630 | 3.9 | 931 | 279 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.6 | 4.45 | Tier 2B: Moderate GIDA Inclusion | 62.11 | 62.11 | 41.66 | 51.89 | E - Nearest node or line 3-5 km | 4.6 | 4.44 | Line: AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4362
4 | 1363 | 4363 | 0301407027 | Region III (Central Luzon) | Bulacan | Calumpit | Santo Niño | 14.9058 | 120.7808 | U | 2659 | 3.5 | 760 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 57.67 | 57.67 | 46.11 | 51.89 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.12 | Line: Calumpit-Baliuag Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4363
4 | 1364 | 4364 | 1380800009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | New Alabang Village | 14.5492 | 120.7995 | U | 22850 | 6.05 | 3778 | 1133 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 12.58 | 15.99 | Tier 2B: Moderate GIDA Inclusion | 51.57 | 51.57 | 52.22 | 51.89 | F - Nearest node and line over 5 km | 12.58 | 15.98 | Node: CVC001 -TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4364
4 | 1365 | 4365 | 1206502024 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Columbio | Polomolok | 6.2428 | 125.0883 | R | 1715 | 3.8 | 451 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.92 | 4.18 | Tier 2B: Moderate GIDA Inclusion | 50.96 | 50.96 | 52.82 | 51.89 | E - Nearest node or line 3-5 km | 3.92 | 4.18 | Node: PMK001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4365
4 | 1366 | 4366 | 0806025011 | Region VIII (Eastern Visayas) | Samar | San Jorge | Guadalupe | 11.8982 | 124.8857 | R | 133 | 4.1 | 32 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 69.89 | 69.84 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.09 | 51.89 | F - Nearest node and line over 5 km | 69.89 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4366
4 | 1367 | 4367 | 0806025012 | Region VIII (Eastern Visayas) | Samar | San Jorge | Hernandez | 11.9006 | 124.8949 | R | 120 | 4.1 | 29 | 9 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 70.45 | 70.4 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.09 | 51.89 | F - Nearest node and line over 5 km | 70.45 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4367
4 | 1368 | 4368 | 1380606201 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 594 | 12.6942 | 121.4084 | U | 686 | 3.67 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.19 | 8.22 | Tier 1B: High GIDA Priority | 25.59 | 25.59 | 78.18 | 51.89 | F - Nearest node and line over 5 km | 10.19 | 8.21 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4368
4 | 1369 | 4369 | 0105538003 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Banaoang | 15.9935 | 120.4316 | R | 4513 | 3.6 | 1254 | 376 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.2 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 36.11 | 51.88 | C - Line within 0.5 km; node over 1 km | 3.2 | 0.03 | Line: SANTA BARBARA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4369
4 | 1370 | 4370 | 1400126009 | Cordillera Administrative Region (CAR) | Abra | Tubo | Wayangan | 17.257 | 120.7054 | R | 470 | 3.8 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.64 | 7.56 | Tier 1B: High GIDA Priority | 38.71 | 38.71 | 65.06 | 51.88 | F - Nearest node and line over 5 km | 13.64 | 7.51 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4370
4 | 1371 | 4371 | 0304932025 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santa Lucia Young | 15.46 | 120.7952 | R | 4124 | 3.5 | 1178 | 353 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 1.19 | Tier 2A: High Commercial ROI | 70.58 | 70.58 | 33.17 | 51.87 | D - Other node or line within 3 km | 1.08 | 1.05 | Line: 24 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4371
4 | 1372 | 4372 | 1600209009 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Kinabjangan | 8.9744 | 125.3601 | R | 3980 | 4.1 | 971 | 291 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.07 | Tier 2A: High Commercial ROI | 70.29 | 70.29 | 33.44 | 51.87 | C - Line within 0.5 km; node over 1 km | 1.47 | 0.07 | Line: CDO - BUENAVISTA via GINGOOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4372
4 | 1373 | 4373 | 0403422012 | Region IV-A (CALABARZON) | Laguna | Pila | Pinagbayanan | 14.2498 | 121.36 | U | 6680 | 3.3 | 2024 | 607 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 64.61 | 64.61 | 39.13 | 51.87 | D - Other node or line within 3 km | 1.55 | 1.15 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4373
4 | 1374 | 4374 | 1401105004 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Baculongan Norte | 16.7723 | 120.8444 | R | 3055 | 3.5 | 873 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.25 | 1.26 | Tier 2B: Moderate GIDA Inclusion | 64.55 | 64.55 | 39.18 | 51.87 | D - Other node or line within 3 km | 4.25 | 1.18 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4374
4 | 1375 | 4375 | 1705320015 | MIMAROPA Region | Palawan | Taytay | New Guinlo | 10.783 | 119.4446 | R | 4296 | 3.9 | 1102 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.21 | 6.12 | Tier 2B: Moderate GIDA Inclusion | 61.48 | 61.48 | 42.27 | 51.87 | F - Nearest node and line over 5 km | 8.21 | 6.05 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4375
4 | 1376 | 4376 | 0403413014 | Region IV-A (CALABARZON) | Laguna | Lumban | Segunda Pulo | 14.3086 | 121.4694 | R | 1742 | 3.3 | 528 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.71 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 58.27 | 58.27 | 45.48 | 51.87 | C - Line within 0.5 km; node over 1 km | 1.71 | 0.11 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4376
4 | 1377 | 4377 | 0401012047 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ilaya | 13.8757 | 120.9136 | R | 1499 | 3.6 | 416 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 2.31 | Tier 2B: Moderate GIDA Inclusion | 54.29 | 54.29 | 49.46 | 51.87 | A - Node within 0.5 km | 0.36 | 2.31 | Node: TLB001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4377
4 | 1378 | 4378 | 0300804018 | Region III (Central Luzon) | Bataan | Dinalupihan | Mabini Ext. | 14.8641 | 120.4454 | R | 758 | 3.6 | 211 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 50.63 | 50.63 | 53.12 | 51.87 | C - Line within 0.5 km; node over 1 km | 1.24 | 0.06 | Line: Path Measure | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4378
4 | 1379 | 4379 | 0401019012 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 7 | 14.108 | 120.6874 | R | 1477 | 3.6 | 410 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.09 | 1.6 | Tier 2B: Moderate GIDA Inclusion | 50.46 | 50.46 | 53.27 | 51.87 | D - Other node or line within 3 km | 7.09 | 1.54 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4379
4 | 1380 | 4380 | 0504102009 | Region V (Bicol Region) | Masbate | Baleno | Eastern Capsay | 12.4419 | 123.4427 | R | 1058 | 4.1 | 258 | 77 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.67 | 5.99 | Tier 2B: Moderate GIDA Inclusion | 50.11 | 50.11 | 53.62 | 51.87 | F - Nearest node and line over 5 km | 6.67 | 18.56 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4380
4 | 1381 | 4381 | 0103314006 | Region I (Ilocos Region) | La Union | City of San Fernando | Barangay I | 16.6182 | 120.3427 | U | 1903 | 3.7 | 514 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.12 | 2.72 | Tier 1B: High GIDA Priority | 45.04 | 45.04 | 58.71 | 51.87 | D - Other node or line within 3 km | 3.12 | 2.7 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4381
4 | 1382 | 4382 | 1608501014 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Puerto Princesa | 10.1046 | 125.4821 | R | 1995 | 3.8 | 525 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 35.23 | 35.23 | Tier 1B: High GIDA Priority | 44.81 | 44.81 | 58.94 | 51.87 | F - Nearest node and line over 5 km | 35.23 | 999999 | Node: SRO001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4382
4 | 1383 | 4383 | 0304927004 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Castellano | 15.3195 | 120.9345 | U | 6047 | 3.5 | 1728 | 518 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.64 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 63.76 | 63.76 | 39.96 | 51.86 | C - Line within 0.5 km; node over 1 km | 3.22 | 0.28 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4383
4 | 1384 | 4384 | 0405812018 | Region IV-A (CALABARZON) | Rizal | Tanay | Tandang Kutyo | 14.5936 | 121.3076 | U | 19868 | 3.6 | 5519 | 1656 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.55 | 9.05 | Tier 2B: Moderate GIDA Inclusion | 62.97 | 62.97 | 40.74 | 51.86 | E - Nearest node or line 3-5 km | 4.55 | 9.04 | Node: BSR004 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4384
4 | 1385 | 4385 | 0201529033 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Tanza | 17.63 | 121.7385 | U | 5582 | 3.9 | 1431 | 429 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.55 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 61.5 | 61.5 | 42.22 | 51.86 | C - Line within 0.5 km; node over 1 km | 2.55 | 0.05 | Line: TUGEGARAO FOC | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4385
4 | 1386 | 4386 | 0806020002 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Awang | 11.8967 | 124.7621 | R | 161 | 4.1 | 39 | 12 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.85 | 66.82 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.02 | 51.86 | F - Nearest node and line over 5 km | 66.85 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4386
4 | 1387 | 4387 | 0806025021 | Region VIII (Eastern Visayas) | Samar | San Jorge | Ranera | 11.9508 | 124.8736 | R | 334 | 4.1 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 75.12 | 75.07 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.02 | 51.86 | F - Nearest node and line over 5 km | 75.12 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4387
4 | 1388 | 4388 | 0806025013 | Region VIII (Eastern Visayas) | Samar | San Jorge | Himay | 11.9603 | 124.8899 | R | 425 | 4.1 | 104 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 76.62 | 76.57 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.03 | 51.86 | F - Nearest node and line over 5 km | 76.62 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4388
4 | 1389 | 4389 | 0806012006 | Region VIII (Eastern Visayas) | Samar | Motiong | Beri | 11.9947 | 124.9626 | R | 87 | 4.1 | 21 | 6 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 82.81 | 82.74 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 67.04 | 51.86 | F - Nearest node and line over 5 km | 82.81 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4389
4 | 1390 | 4390 | 0603013037 | Region VI (Western Visayas) | Iloilo | Calinog | Hilwan | 11.2915 | 122.33 | R | 544 | 3.8 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.95 | 25.42 | Tier 1B: High GIDA Priority | 32.85 | 32.85 | 70.86 | 51.86 | F - Nearest node and line over 5 km | 29.95 | 29.07 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4390
4 | 1391 | 4391 | 0704603016 | Region VII (Central Visayas) | Negros Oriental | Bacong | San Miguel | 9.2241 | 123.2858 | U | 4958 | 3.8 | 1305 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 1.76 | Tier 2B: Moderate GIDA Inclusion | 69.28 | 69.28 | 34.42 | 51.85 | D - Other node or line within 3 km | 3.2 | 2.05 | Line: FRONTHAUL-BACONG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4391
4 | 1392 | 4392 | 0402106010 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sabang | 14.344 | 120.9264 | U | 18243 | 3.4 | 5366 | 1610 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.6 | 5.54 | Tier 2B: Moderate GIDA Inclusion | 66.71 | 66.71 | 37 | 51.85 | D - Other node or line within 3 km | 1.6 | 5.5 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4392
4 | 1393 | 4393 | 0601916020 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Sur | 11.4219 | 122.6617 | R | 1889 | 3.8 | 497 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 65.29 | 65.29 | 38.4 | 51.85 | B - Node 0.5-1 km | 0.72 | 0.5 | Line: ROXAS - ILOILO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4393
4 | 1394 | 4394 | 1380601082 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 82 | 13.469 | 122.9353 | U | 2662 | 5.48 | 486 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.43 | 10.43 | Tier 1B: High GIDA Priority | 33.21 | 33.21 | 70.48 | 51.85 | F - Nearest node and line over 5 km | 10.43 | 10.71 | Node: PCC001 - PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4394
4 | 1395 | 4395 | 1903601024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Rorowan | 17.2547 | 122.2288 | R | 564 | 5.7 | 99 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.4 | 34.28 | Tier 1B: High GIDA Priority | 28.1 | 28.1 | 75.59 | 51.85 | F - Nearest node and line over 5 km | 29.4 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4395
4 | 1396 | 4396 | 0603026019 | Region VI (Western Visayas) | Iloilo | Leganes | Poblacion | 10.7882 | 122.5899 | U | 3436 | 3.8 | 904 | 271 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.29 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 67.8 | 67.8 | 35.88 | 51.84 | A - Node within 0.5 km | 0.29 | 0.03 | Line: ROXAS - ILOILO | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4396
4 | 1397 | 4397 | 0304907001 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Bagong Sikat | 15.4813 | 121.3073 | R | 3203 | 3.5 | 915 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.76 | 20.51 | Tier 2B: Moderate GIDA Inclusion | 63.65 | 63.65 | 40.02 | 51.84 | D - Other node or line within 3 km | 2.76 | 20.5 | Node: GBN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4397
4 | 1398 | 4398 | 0304904023 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Polilio | 15.2496 | 120.8539 | R | 1646 | 3.5 | 470 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.01 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 56.35 | 56.35 | 47.33 | 51.84 | C - Line within 0.5 km; node over 1 km | 2.01 | 0.45 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4398
4 | 1399 | 4399 | 0403413007 | Region IV-A (CALABARZON) | Laguna | Lumban | Maracta | 14.2997 | 121.4706 | R | 1171 | 3.3 | 355 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 54.53 | 54.53 | 49.15 | 51.84 | D - Other node or line within 3 km | 1.13 | 0.61 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4399
4 | 1400 | 4400 | 1408104007 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Cabetayan | 17.999 | 121.1738 | R | 608 | 4.2 | 145 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 7.9 | Tier 1B: High GIDA Priority | 44.07 | 44.07 | 59.61 | 51.84 | D - Other node or line within 3 km | 2.41 | 27.52 | Node: KOY001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4400
4 | 1401 | 4401 | 0806021011 | Region VIII (Eastern Visayas) | Samar | Villareal | Inarumbacan | 11.5117 | 124.8971 | R | 565 | 4.1 | 138 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 32.36 | 31.69 | Tier 1B: High GIDA Priority | 37.18 | 37.18 | 66.5 | 51.84 | F - Nearest node and line over 5 km | 32.36 | 31.68 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4401
4 | 1402 | 4402 | 0203118017 | Region II (Cagayan Valley) | Isabela | Delfin Albano | San Antonio | 17.2732 | 121.7916 | R | 3331 | 3.8 | 877 | 263 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.89 | Tier 2A: High Commercial ROI | 73.7 | 73.7 | 29.96 | 51.83 | B - Node 0.5-1 km | 0.91 | 0.88 | Line: Ilagan-Tumauini Segment | Survey short node lateral; confirm port/fiber capacity, access and route. | 4402
4 | 1403 | 4403 | 0402106014 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin I | 14.3139 | 120.9507 | U | 12602 | 3.4 | 3706 | 1112 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.62 | 1.39 | Tier 2B: Moderate GIDA Inclusion | 69.68 | 69.68 | 33.99 | 51.83 | D - Other node or line within 3 km | 1.62 | 1.33 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4403
4 | 1404 | 4404 | 0304921001 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Callos | 15.3377 | 121.0347 | R | 3825 | 3.5 | 1093 | 328 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 8.74 | Tier 2B: Moderate GIDA Inclusion | 68.91 | 68.91 | 34.74 | 51.83 | D - Other node or line within 3 km | 2.59 | 8.37 | Node: PRN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4404
4 | 1405 | 4405 | 0501709002 | Region V (Bicol Region) | Camarines Sur | Camaligan | Marupit | 13.627 | 123.1688 | U | 5025 | 4.2 | 1196 | 359 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.85 | 2.14 | Tier 2B: Moderate GIDA Inclusion | 67.64 | 67.64 | 36.02 | 51.83 | B - Node 0.5-1 km | 0.85 | 2.07 | Node: CLC001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4405
4 | 1406 | 4406 | 1705205031 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Lumangbayan | 13.3613 | 121.2022 | U | 5295 | 3.9 | 1358 | 407 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.47 | 3.56 | Tier 2B: Moderate GIDA Inclusion | 57.04 | 57.04 | 46.63 | 51.83 | E - Nearest node or line 3-5 km | 4.47 | 3.54 | Line: MINDORO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4406
4 | 1407 | 4407 | 1908815004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagagawan | Dungguan | 11.2735 | 122.6317 | U | 6808 | 4.7 | 1449 | 435 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.25 | 2.7 | Tier 2B: Moderate GIDA Inclusion | 54.23 | 54.23 | 49.43 | 51.83 | D - Other node or line within 3 km | 5.25 | 2.69 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4407
4 | 1408 | 4408 | 0405644017 | Region IV-A (CALABARZON) | Quezon | San Narciso | Punta | 13.523 | 122.6073 | R | 2389 | 3.8 | 629 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.46 | 7.44 | Tier 2B: Moderate GIDA Inclusion | 53.62 | 53.62 | 50.05 | 51.83 | F - Nearest node and line over 5 km | 5.46 | 7.44 | Node: SNQ003-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4408
4 | 1409 | 4409 | 1381100196 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 196 | 14.7838 | 120.9818 | U | 1570 | 3.46 | 454 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.54 | 1.16 | Tier 1B: High GIDA Priority | 42.67 | 42.67 | 60.98 | 51.83 | D - Other node or line within 3 km | 2.54 | 2.98 | Node: MEB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4409
4 | 1410 | 4410 | 1102509005 | Region XI (Davao Region) | Davao Oriental | City of Mati | Central | 6.9663 | 126.208 | U | 35778 | 3.6 | 9938 | 2981 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 0.77 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 69.65 | 69.65 | 33.99 | 51.82 | B - Node 0.5-1 km | 0.77 | 0.55 | Line: PANTUKAN - MATI SEGMENT 5 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4410
4 | 1411 | 4411 | 0401019042 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Putat | 14.0821 | 120.6669 | R | 3688 | 3.6 | 1024 | 307 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.76 | 0.88 | Tier 2B: Moderate GIDA Inclusion | 66.12 | 66.12 | 37.51 | 51.82 | D - Other node or line within 3 km | 3.76 | 0.84 | Line: NCC001 TO NSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4411
4 | 1412 | 4412 | 0506203032 | Region V (Bicol Region) | Sorsogon | Bulan | Managanaga | 12.6771 | 123.925 | R | 3413 | 4 | 853 | 256 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.72 | 1.32 | Tier 2B: Moderate GIDA Inclusion | 62.89 | 62.89 | 40.74 | 51.82 | D - Other node or line within 3 km | 5.72 | 1.32 | Line: 14,546 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4412
4 | 1413 | 4413 | 0301422014 | Region III (Central Luzon) | Bulacan | San Rafael | Maguinao | 15.0236 | 120.9342 | U | 5164 | 3.5 | 1475 | 442 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.8 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 62.73 | 62.73 | 40.9 | 51.82 | C - Line within 0.5 km; node over 1 km | 1.8 | 0.06 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4413
4 | 1414 | 4414 | 0201508016 | Region II (Cagayan Valley) | Cagayan | Buguey | Pattao | 18.2481 | 121.8158 | R | 3799 | 3.9 | 974 | 292 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.3 | 0.3 | Tier 2A: High Commercial ROI | 71.51 | 71.51 | 32.11 | 51.81 | A - Node within 0.5 km | 0.3 | 0.3 | Line: SEGMENT 30 (LAL-LO - STA ANA) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4414
4 | 1415 | 4415 | 0702219021 | Region VII (Central Visayas) | Cebu | Consolacion | Tugbongan | 10.3637 | 123.9618 | U | 8866 | 3.8 | 2333 | 700 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 1.14 | Tier 2B: Moderate GIDA Inclusion | 68.4 | 68.4 | 35.22 | 51.81 | D - Other node or line within 3 km | 1.47 | 1.1 | Line: DANAO - CEBU | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4415
4 | 1416 | 4416 | 0300809020 | Region III (Central Luzon) | Bataan | Orani | Talimundoc | 14.8179 | 120.5177 | R | 2623 | 3.6 | 729 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.66 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 62.44 | 62.44 | 41.17 | 51.81 | C - Line within 0.5 km; node over 1 km | 2.66 | 0.03 | Line: Dinalupian to Orion | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4416
4 | 1417 | 4417 | 0105546005 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Bayaoas | 15.975 | 120.5567 | U | 5835 | 3.6 | 1621 | 486 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 62.11 | 62.11 | 41.52 | 51.81 | C - Line within 0.5 km; node over 1 km | 2.52 | 0.03 | Line: URDANETA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4417
4 | 1418 | 4418 | 0301420051 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael IV | 14.8552 | 121.0474 | U | 6739 | 3.5 | 1925 | 578 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.84 | 2.81 | Tier 2B: Moderate GIDA Inclusion | 60.55 | 60.55 | 43.08 | 51.81 | D - Other node or line within 3 km | 1.84 | 5.16 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4418
4 | 1419 | 4419 | 0402113015 | Region IV-A (CALABARZON) | Cavite | Maragondon | Patungan | 14.2195 | 120.6221 | R | 2667 | 3.4 | 784 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.14 | 9.07 | Tier 2B: Moderate GIDA Inclusion | 53.99 | 53.99 | 49.64 | 51.81 | F - Nearest node and line over 5 km | 10.14 | 9.07 | Line: NCC001 TO NSB001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4419
4 | 1420 | 4420 | 1204702025 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Manili | 7.2999 | 124.8117 | R | 2593 | 3.8 | 682 | 205 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.93 | 2.95 | Tier 2B: Moderate GIDA Inclusion | 50.91 | 50.91 | 52.71 | 51.81 | D - Other node or line within 3 km | 10.93 | 2.94 | Line: MATALAM - CARMEN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4420
4 | 1421 | 4421 | 1381300014 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bayanihan | 14.6642 | 121.0392 | U | 777 | 3.48 | 223 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 0.6 | Tier 1B: High GIDA Priority | 39.88 | 39.88 | 63.75 | 51.81 | B - Node 0.5-1 km | 0.62 | 0.48 | Line: Aerial 24C | Survey short node lateral; confirm port/fiber capacity, access and route. | 4421
4 | 1422 | 4422 | 1380601228 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 227 | 13.7339 | 122.3876 | U | 1726 | 4.6 | 375 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.74 | 6.61 | Tier 1B: High GIDA Priority | 33.29 | 33.29 | 70.34 | 51.81 | F - Nearest node and line over 5 km | 7.74 | 6.45 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4422
4 | 1423 | 4423 | 0500517005 | Region V (Bicol Region) | Albay | City of Tabaco | Baranghawon | 13.3523 | 123.723 | R | 4803 | 4.1 | 1171 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.45 | Tier 2A: High Commercial ROI | 73.99 | 73.99 | 29.61 | 51.8 | B - Node 0.5-1 km | 0.9 | 0.38 | Line: TABACO - LIGAO AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4423
4 | 1424 | 4424 | 0105517025 | Region I (Ilocos Region) | Pangasinan | Calasiao | Talibaew | 16.0053 | 120.3728 | R | 4866 | 3.6 | 1352 | 406 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 1.29 | Tier 2B: Moderate GIDA Inclusion | 69.72 | 69.72 | 33.88 | 51.8 | D - Other node or line within 3 km | 1.89 | 1.26 | Line: CALASIAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4424
4 | 1425 | 4425 | 0102934001 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Ayusan Norte | 17.5616 | 120.3885 | R | 3593 | 3.8 | 946 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.56 | 2.11 | Tier 2B: Moderate GIDA Inclusion | 62.82 | 62.82 | 40.77 | 51.8 | D - Other node or line within 3 km | 3.56 | 2.11 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4425
4 | 1426 | 4426 | 0601904030 | Region VI (Western Visayas) | Capiz | Dumarao | Sagrada Familia | 11.2103 | 122.8339 | R | 2788 | 3.8 | 734 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.46 | 3.36 | Tier 2B: Moderate GIDA Inclusion | 58.46 | 58.46 | 45.13 | 51.8 | E - Nearest node or line 3-5 km | 3.46 | 3.36 | Line: SARA - PASSI | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4426
4 | 1427 | 4427 | 0601903007 | Region VI (Western Visayas) | Capiz | Dumalag | San Agustin | 11.3255 | 122.5927 | R | 707 | 3.8 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.93 | 3.89 | Tier 1B: High GIDA Priority | 43.67 | 43.67 | 59.92 | 51.8 | E - Nearest node or line 3-5 km | 11.93 | 3.85 | Line: CABLE LAYED | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4427
4 | 1428 | 4428 | 1108604005 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kisulad | 6.5297 | 125.5625 | R | 1420 | 3.6 | 394 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.59 | 21.07 | Tier 1B: High GIDA Priority | 39.47 | 39.47 | 64.14 | 51.8 | F - Nearest node and line over 5 km | 18.59 | 21.05 | Node: MGD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4428
4 | 1429 | 4429 | 1705208070 | MIMAROPA Region | Oriental Mindoro | Naujan | Caburo | 13.1675 | 121.1461 | R | 470 | 3.9 | 121 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.49 | 14.18 | Tier 1B: High GIDA Priority | 34.68 | 34.68 | 68.92 | 51.8 | F - Nearest node and line over 5 km | 14.49 | 14.18 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4429
4 | 1430 | 4430 | 1907001008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tabunan | 17.2557 | 122.2297 | R | 1387 | 5.8 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.55 | 34.41 | Tier 1B: High GIDA Priority | 30.87 | 30.87 | 72.74 | 51.8 | F - Nearest node and line over 5 km | 29.55 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4430
4 | 1431 | 4431 | 0307104012 | Region III (Central Luzon) | Zambales | Castillejos | San Nicolas | 14.927 | 120.2016 | R | 4602 | 3.8 | 1211 | 363 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 0.33 | Tier 2A: High Commercial ROI | 72.21 | 72.21 | 31.38 | 51.79 | A - Node within 0.5 km | 0.31 | 0.29 | Line: BACKBONE ROUTE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4431
4 | 1432 | 4432 | 0600613002 | Region VI (Western Visayas) | Antique | San Jose | Badiang | 10.7652 | 121.9435 | R | 3647 | 3.9 | 935 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.56 | Tier 2A: High Commercial ROI | 70.66 | 70.66 | 32.92 | 51.79 | B - Node 0.5-1 km | 0.68 | 0.56 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Survey short node lateral; confirm port/fiber capacity, access and route. | 4432
4 | 1433 | 4433 | 0601910013 | Region VI (Western Visayas) | Capiz | Panitan | Cogon | 11.4594 | 122.8175 | R | 3953 | 3.8 | 1040 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.72 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 69.71 | 69.71 | 33.87 | 51.79 | C - Line within 0.5 km; node over 1 km | 2.72 | 0.19 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4433
4 | 1434 | 4434 | 1600201015 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Poblacion 3 | 8.9751 | 125.4078 | U | 3797 | 4.1 | 926 | 278 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.52 | Tier 2B: Moderate GIDA Inclusion | 62.33 | 62.33 | 41.24 | 51.79 | D - Other node or line within 3 km | 1.14 | 0.52 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4434
4 | 1435 | 4435 | 0405814008 | Region IV-A (CALABARZON) | Rizal | Teresa | San Gabriel | 14.5638 | 121.2121 | U | 2526 | 3.6 | 702 | 211 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.31 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 56.26 | 56.26 | 47.33 | 51.79 | D - Other node or line within 3 km | 1.31 | 0.62 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4435
4 | 1436 | 4436 | 1102408015 | Region XI (Davao Region) | Davao del Sur | Malalag | Pitu | 6.5137 | 125.4182 | R | 2056 | 3.4 | 605 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.43 | 5.82 | Tier 2B: Moderate GIDA Inclusion | 51.68 | 51.68 | 51.9 | 51.79 | F - Nearest node and line over 5 km | 8.43 | 5.77 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4436
4 | 1437 | 4437 | 0103301041 | Region I (Ilocos Region) | La Union | Agoo | Santa Barbara | 16.3245 | 120.3559 | U | 1751 | 3.7 | 473 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 1.16 | Tier 2B: Moderate GIDA Inclusion | 50.03 | 50.03 | 53.56 | 51.79 | D - Other node or line within 3 km | 1.35 | 1.15 | Line: AGOO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4437
4 | 1438 | 4438 | 1003502025 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Sandor | 8.0847 | 124.1901 | R | 2068 | 4.2 | 492 | 148 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.45 | 4.74 | Tier 1B: High GIDA Priority | 45.07 | 45.07 | 58.51 | 51.79 | E - Nearest node or line 3-5 km | 12.45 | 4.68 | Line: 216f feeder iligan completed | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4438
4 | 1439 | 4439 | 1606813011 | Region XIII (Caraga) | Surigao del Sur | Madrid | San Vicente | 9.2728 | 126.0052 | R | 766 | 4.1 | 187 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.27 | 4.11 | Tier 1B: High GIDA Priority | 42.25 | 42.25 | 61.33 | 51.79 | E - Nearest node or line 3-5 km | 12.27 | 4.11 | Line: Route | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4439
4 | 1440 | 4440 | 0401005055 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 1 | 13.7182 | 121.0996 | U | 794 | 3.6 | 221 | 66 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 5.82 | Tier 1B: High GIDA Priority | 36.46 | 36.46 | 67.13 | 51.79 | E - Nearest node or line 3-5 km | 3.55 | 5.82 | Node: BCY007-PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4440
4 | 1441 | 4441 | 0907220026 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sirawai | Pisa Itom | 7.5416 | 122.1749 | R | 470 | 3.6 | 131 | 39 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.69 | 19.03 | Tier 1B: High GIDA Priority | 34.42 | 34.42 | 69.16 | 51.79 | F - Nearest node and line over 5 km | 28.69 | 18.95 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4441
4 | 1442 | 4442 | 0203121003 | Region II (Cagayan Valley) | Isabela | Palanan | Dicadyuan | 17.0098 | 122.4271 | R | 818 | 3.8 | 215 | 64 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.12 | 55.67 | Tier 1B: High GIDA Priority | 30.86 | 30.86 | 72.73 | 51.79 | F - Nearest node and line over 5 km | 44.12 | 999999 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4442
4 | 1443 | 4443 | 0301418034 | Region III (Central Luzon) | Bulacan | Pulilan | Tabon | 14.9106 | 120.827 | R | 5154 | 3.5 | 1473 | 442 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.7 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 68.92 | 68.92 | 34.63 | 51.78 | C - Line within 0.5 km; node over 1 km | 2.7 | 0.16 | Line: Calumpit-Baliuag Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4443
4 | 1444 | 4444 | 0306916076 | Region III (Central Luzon) | Tarlac | City of Tarlac | Santa Cruz | 15.5372 | 120.5968 | R | 4449 | 3.9 | 1141 | 342 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.15 | 0.36 | Tier 2B: Moderate GIDA Inclusion | 66.34 | 66.34 | 37.21 | 51.78 | C - Line within 0.5 km; node over 1 km | 4.15 | 0.36 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4444
4 | 1445 | 4445 | 0603018040 | Region VI (Western Visayas) | Iloilo | Dumangas | Tabucan | 10.8193 | 122.7007 | R | 2389 | 3.8 | 629 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 62.8 | 62.8 | 40.77 | 51.78 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.06 | Line: ZARRAGA CLS-DUMANGAS CO (DSI001) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4445
4 | 1446 | 4446 | 0300806003 | Region III (Central Luzon) | Bataan | Limay | Kitang 2 & Luz | 14.5514 | 120.5971 | U | 6415 | 3.6 | 1782 | 535 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.52 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 62.61 | 62.61 | 40.96 | 51.78 | C - Line within 0.5 km; node over 1 km | 2.52 | 0.06 | Line: 24 CORE 2X12 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4446
4 | 1447 | 4447 | 0403417043 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Silangan Ilaya | 14.1289 | 121.3672 | R | 2614 | 3.3 | 792 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.43 | 2.25 | Tier 2B: Moderate GIDA Inclusion | 59.72 | 59.72 | 43.83 | 51.78 | D - Other node or line within 3 km | 3.43 | 2.23 | Line: SPO001 TO LBQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4447
4 | 1448 | 4448 | 1403215022 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Old Tinglayan | 17.259 | 121.147 | R | 286 | 4.3 | 67 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.57 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 54.88 | 54.88 | 48.68 | 51.78 | B - Node 0.5-1 km | 0.57 | 0.29 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 4448
4 | 1449 | 4449 | 0601904033 | Region VI (Western Visayas) | Capiz | Dumarao | Sibariwan | 11.2469 | 122.8164 | R | 1502 | 3.8 | 395 | 118 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.65 | 7.65 | Tier 2B: Moderate GIDA Inclusion | 48.27 | 48.27 | 55.29 | 51.78 | F - Nearest node and line over 5 km | 7.65 | 7.64 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4449
4 | 1450 | 4450 | 0806417009 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Hindangan | 10.4253 | 124.9274 | R | 155 | 4.1 | 38 | 11 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.42 | 7.02 | Tier 1B: High GIDA Priority | 43.17 | 43.17 | 60.4 | 51.78 | F - Nearest node and line over 5 km | 31.43 | 18.17 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4450
4 | 1451 | 4451 | 0305409017 | Region III (Central Luzon) | Pampanga | Mabalacat City | Marcos Village | 15.2031 | 120.4951 | R | 5259 | 4 | 1315 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.33 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 66.72 | 66.72 | 36.83 | 51.77 | D - Other node or line within 3 km | 4.33 | 1.46 | Line: Aerial 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4451
4 | 1452 | 4452 | 0301409009 | Region III (Central Luzon) | Bulacan | Hagonoy | San Isidro | 14.8602 | 120.7394 | U | 8873 | 3.5 | 2535 | 760 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.67 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 64.7 | 64.7 | 38.85 | 51.77 | D - Other node or line within 3 km | 2.67 | 5.66 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4452
4 | 1453 | 4453 | 1381100170 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 170 | 14.3555 | 120.8931 | U | 880 | 3.24 | 272 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.14 | 5.04 | Tier 1B: High GIDA Priority | 33.7 | 33.7 | 69.84 | 51.77 | E - Nearest node or line 3-5 km | 3.14 | 5.04 | Node: TRC006 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4453
4 | 1454 | 4454 | 0704601004 | Region VII (Central Visayas) | Negros Oriental | Amlan | Mag-abo | 9.4642 | 123.2206 | R | 2265 | 3.8 | 596 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.34 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 68.31 | 68.31 | 35.2 | 51.76 | A - Node within 0.5 km | 0.34 | 0.11 | Line: KABANGKALAN - BACONG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4454
4 | 1455 | 4455 | 0105513007 | Region I (Ilocos Region) | Pangasinan | Binmaley | Biec | 16.0213 | 120.2727 | R | 3360 | 3.6 | 933 | 280 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.28 | 0.56 | Tier 2B: Moderate GIDA Inclusion | 65.6 | 65.6 | 37.92 | 51.76 | C - Line within 0.5 km; node over 1 km | 4.28 | 0.47 | Line: BINMALEY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4455
4 | 1456 | 4456 | 0300810008 | Region III (Central Luzon) | Bataan | Orion | Bilolo | 14.6152 | 120.5617 | U | 8178 | 3.6 | 2272 | 682 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.87 | 1.07 | Tier 2B: Moderate GIDA Inclusion | 65.05 | 65.05 | 38.47 | 51.76 | D - Other node or line within 3 km | 1.87 | 1.07 | Line: 48 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4456
4 | 1457 | 4457 | 0603043038 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Inangayan | 10.8014 | 122.5132 | R | 3596 | 3.8 | 946 | 284 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 3.72 | Tier 2B: Moderate GIDA Inclusion | 62.98 | 62.98 | 40.54 | 51.76 | E - Nearest node or line 3-5 km | 3.71 | 3.55 | Line: Santa Barbara - Janiuay 18.361km | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4457
4 | 1458 | 4458 | 0405804019 | Region IV-A (CALABARZON) | Rizal | Binangonan | Kinagatan | 14.3855 | 121.2232 | R | 1407 | 3.6 | 391 | 117 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.7 | 9.73 | Tier 2B: Moderate GIDA Inclusion | 46.53 | 46.53 | 56.99 | 51.76 | F - Nearest node and line over 5 km | 6.7 | 9.6 | Node: BIR003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4458
4 | 1459 | 4459 | 1907002025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Paniongan | 14.5037 | 121.6597 | R | 1210 | 5.8 | 209 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 22.63 | Tier 1B: High GIDA Priority | 42.85 | 42.85 | 60.68 | 51.76 | E - Nearest node or line 3-5 km | 3.33 | 22.63 | Node: RLQ003 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4459
4 | 1460 | 4460 | 1908811006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Gen. S.K. Pendatun | Lasangan | 17.255 | 122.2291 | R | 2163 | 4.7 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.44 | 34.32 | Tier 1B: High GIDA Priority | 36.63 | 36.63 | 66.88 | 51.76 | F - Nearest node and line over 5 km | 29.44 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4460
4 | 1461 | 4461 | 1004307001 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Amoros | 8.5274 | 124.5463 | R | 5055 | 3.9 | 1296 | 389 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.24 | 0.82 | Tier 2B: Moderate GIDA Inclusion | 69.53 | 69.53 | 33.97 | 51.75 | D - Other node or line within 3 km | 3.24 | 0.82 | Line: CDO - ILIGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4461
4 | 1462 | 4462 | 0702241015 | Region VII (Central Visayas) | Cebu | San Fernando | Pitalo | 10.1757 | 123.7217 | U | 8064 | 3.8 | 2122 | 637 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.11 | 0.3 | Tier 2B: Moderate GIDA Inclusion | 66.83 | 66.83 | 36.67 | 51.75 | C - Line within 0.5 km; node over 1 km | 2.11 | 0.12 | Line: 216F | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4462
4 | 1463 | 4463 | 0500509010 | Region V (Bicol Region) | Albay | Malilipot | San Antonio Santicon | 13.3468 | 123.6783 | R | 789 | 4.1 | 192 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.88 | 0.12 | Tier 2B: Moderate GIDA Inclusion | 56.42 | 56.42 | 47.07 | 51.75 | C - Line within 0.5 km; node over 1 km | 1.88 | 0.12 | Line: TABACO - LIGAO AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4463
4 | 1464 | 4464 | 0907219009 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Siocon | Candiz | 7.6868 | 122.3267 | R | 3658 | 3.6 | 1016 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.63 | 14.34 | Tier 2B: Moderate GIDA Inclusion | 54.88 | 54.88 | 48.63 | 51.75 | F - Nearest node and line over 5 km | 14.63 | 14.33 | Line: IPIL - TUNGAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4464
4 | 1465 | 4465 | 0405646006 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Bukal | 13.9728 | 122.5897 | R | 521 | 3.8 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.16 | 3.74 | Tier 1B: High GIDA Priority | 40.34 | 40.34 | 63.15 | 51.75 | E - Nearest node or line 3-5 km | 5.16 | 3.73 | Line: LZQ001 TO DEL GALLEGO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4465
4 | 1466 | 4466 | 1400111005 | Cordillera Administrative Region (CAR) | Abra | Lagayan | Pang-ot | 17.7531 | 120.7402 | R | 320 | 3.8 | 84 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.81 | 7.1 | Tier 1B: High GIDA Priority | 39.26 | 39.26 | 64.23 | 51.75 | F - Nearest node and line over 5 km | 12.81 | 7.44 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4466
4 | 1467 | 4467 | 1380606080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 474 | 13.8551 | 121.774 | U | 1614 | 3.83 | 421 | 126 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.12 | 7.63 | Tier 1B: High GIDA Priority | 34.01 | 34.01 | 69.5 | 51.75 | F - Nearest node and line over 5 km | 8.12 | 7.61 | Line: SAN JUAN TO UNISAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4467
4 | 1468 | 4468 | 0201507020 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Santa Cruz | 18.4012 | 121.5264 | R | 3836 | 3.9 | 984 | 295 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 6.75 | Tier 2B: Moderate GIDA Inclusion | 69.95 | 69.95 | 33.53 | 51.74 | D - Other node or line within 3 km | 1.67 | 6.71 | Node: BLC001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4468
4 | 1469 | 4469 | 0403402003 | Region IV-A (CALABARZON) | Laguna | Bay | Dila | 14.1809 | 121.2864 | U | 7412 | 3.3 | 2246 | 674 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 67 | 67 | 36.48 | 51.74 | B - Node 0.5-1 km | 0.64 | 0.19 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4469
4 | 1470 | 4470 | 0304904004 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Concepcion | 15.2214 | 120.8316 | R | 4735 | 3.5 | 1353 | 406 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.94 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.8 | 65.8 | 37.68 | 51.74 | C - Line within 0.5 km; node over 1 km | 5.94 | 0.15 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4470
4 | 1471 | 4471 | 0103317018 | Region I (Ilocos Region) | La Union | Santo Tomas | Patac | 16.2748 | 120.3935 | U | 3416 | 3.7 | 923 | 277 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 65.26 | 65.26 | 38.21 | 51.74 | C - Line within 0.5 km; node over 1 km | 1.99 | 0.06 | Line: SANTO TOMAS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4471
4 | 1472 | 4472 | 0301422009 | Region III (Central Luzon) | Bulacan | San Rafael | Capihan | 14.9975 | 120.9304 | U | 6405 | 3.5 | 1830 | 549 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 64.94 | 64.94 | 38.53 | 51.74 | C - Line within 0.5 km; node over 1 km | 1.14 | 0.07 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4472
4 | 1473 | 4473 | 0603043036 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Gen. Martin T. Delgado | 10.8321 | 122.5324 | R | 1933 | 3.8 | 509 | 153 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 61.36 | 61.36 | 42.12 | 51.74 | B - Node 0.5-1 km | 0.58 | 0.26 | Line: Santa Barbara - Janiuay 18.361km | Survey short node lateral; confirm port/fiber capacity, access and route. | 4473
4 | 1474 | 4474 | 0102809020 | Region I (Ilocos Region) | Ilocos Norte | Dingras | San Marcelino | 18.0353 | 120.7617 | R | 4115 | 3.7 | 1112 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.04 | 6.65 | Tier 2B: Moderate GIDA Inclusion | 61.18 | 61.18 | 42.3 | 51.74 | F - Nearest node and line over 5 km | 7.04 | 6.65 | Line: SEGMENT 2 SOLSONA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4474
4 | 1475 | 4475 | 0105501013 | Region I (Ilocos Region) | Pangasinan | Agno | Patar | 16.149 | 119.8171 | R | 1073 | 3.6 | 298 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.55 | 6.28 | Tier 1B: High GIDA Priority | 45.3 | 45.3 | 58.17 | 51.74 | E - Nearest node or line 3-5 km | 4.55 | 6.17 | Node: AGP001 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4475
4 | 1476 | 4476 | 0401022022 | Region IV-A (CALABARZON) | Batangas | San Jose | Pinagtung-Ulan | 13.9235 | 121.0832 | R | 4879 | 3.6 | 1355 | 406 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 66.71 | 66.71 | 36.74 | 51.73 | C - Line within 0.5 km; node over 1 km | 4.22 | 0.42 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4476
4 | 1477 | 4477 | 0103320001 | Region I (Ilocos Region) | La Union | Tubao | Amallapay | 16.3278 | 120.4087 | R | 2032 | 3.7 | 549 | 165 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 65.59 | 65.59 | 37.87 | 51.73 | B - Node 0.5-1 km | 0.56 | 0.56 | Line: TUBAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4477
4 | 1478 | 4478 | 0306905035 | Region III (Central Luzon) | Tarlac | Concepcion | San Nicolas | 15.3261 | 120.6544 | U | 5092 | 3.9 | 1306 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.22 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.22 | 65.22 | 38.25 | 51.73 | A - Node within 0.5 km | 0.22 | 0.23 | Node: CCT002 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4478
4 | 1479 | 4479 | 1402706035 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Bato-Alatbang | 16.9493 | 121.2219 | R | 906 | 3.9 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.58 | 17.58 | Tier 2B: Moderate GIDA Inclusion | 50.61 | 50.61 | 52.86 | 51.73 | D - Other node or line within 3 km | 2.58 | 18.26 | Node: MOF001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4479
4 | 1480 | 4480 | 0300804026 | Region III (Central Luzon) | Bataan | Dinalupihan | Pinulot | 14.8501 | 120.3895 | R | 4758 | 3.6 | 1322 | 397 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.05 | Tier 2A: High Commercial ROI | 71.4 | 71.4 | 32.03 | 51.72 | B - Node 0.5-1 km | 0.87 | 0.03 | Line: Layac - Olongapo AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4480
4 | 1481 | 4481 | 0203126011 | Region II (Cagayan Valley) | Isabela | Roxas | Rizal | 17.1225 | 121.6194 | U | 6490 | 3.8 | 1708 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.1 | 65.1 | 38.34 | 51.72 | B - Node 0.5-1 km | 0.86 | 0.23 | Line: ROXAS - GAMU | Survey short node lateral; confirm port/fiber capacity, access and route. | 4481
4 | 1482 | 4482 | 0702207027 | Region VII (Central Visayas) | Cebu | Badian | Tigbao | 9.8984 | 123.4417 | R | 1039 | 3.8 | 273 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.81 | 4.06 | Tier 1B: High GIDA Priority | 45.94 | 45.94 | 57.49 | 51.72 | E - Nearest node or line 3-5 km | 6.81 | 4.04 | Line: Segment 6 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4482
4 | 1483 | 4483 | 0500515033 | Region V (Bicol Region) | Albay | Rapu-Rapu | Tinocawan | 13.2522 | 123.9303 | R | 647 | 4.1 | 158 | 47 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.72 | 16.68 | Tier 1B: High GIDA Priority | 36.13 | 36.13 | 67.31 | 51.72 | F - Nearest node and line over 5 km | 15.72 | 16.5 | Node: MNT001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4483
4 | 1484 | 4484 | 1907004005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tonggosong | 4.9235 | 119.8193 | R | 1675 | 5.8 | 289 | 87 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 35.98 | 35.98 | 67.47 | 51.72 | F - Nearest node and line over 5 km | 333.14 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4484
4 | 1485 | 4485 | 1903631027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Puracan | 15.679 | 122.5442 | R | 705 | 5.7 | 124 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 79.62 | 78.51 | Tier 1B: High GIDA Priority | 31.89 | 31.89 | 71.54 | 51.72 | F - Nearest node and line over 5 km | 79.62 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4485
4 | 1486 | 4486 | 0301417008 | Region III (Central Luzon) | Bulacan | Plaridel | Dampol | 14.8993 | 120.8196 | R | 3633 | 3.5 | 1038 | 311 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 1.04 | Tier 2B: Moderate GIDA Inclusion | 66.83 | 66.83 | 36.59 | 51.71 | D - Other node or line within 3 km | 3.35 | 1.01 | Line: Calumpit-Baliuag Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4486
4 | 1487 | 4487 | 0603036004 | Region VI (Western Visayas) | Iloilo | Pavia | Balabag | 10.7679 | 122.5177 | U | 14522 | 3.8 | 3822 | 1147 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.89 | 2.01 | Tier 2B: Moderate GIDA Inclusion | 66.58 | 66.58 | 36.84 | 51.71 | D - Other node or line within 3 km | 2.89 | 2 | Line: 7,092 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4487
4 | 1488 | 4488 | 0600416011 | Region VI (Western Visayas) | Aklan | Numancia | Joyao-joyao | 11.7208 | 122.3338 | R | 2225 | 3.9 | 571 | 171 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 64.61 | 64.61 | 38.8 | 51.71 | D - Other node or line within 3 km | 2.04 | 2.77 | Node: NUK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4488
4 | 1489 | 4489 | 0305411017 | Region III (Central Luzon) | Pampanga | Magalang | San Pedro II | 15.2109 | 120.6487 | U | 5721 | 4 | 1430 | 429 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 63.45 | 63.45 | 39.97 | 51.71 | C - Line within 0.5 km; node over 1 km | 1.29 | 0.34 | Line: Pipe Epza to Magalang | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4489
4 | 1490 | 4490 | 0105535007 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Norte | 16.0707 | 120.6533 | U | 5411 | 3.6 | 1503 | 451 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.75 | 1.11 | Tier 2B: Moderate GIDA Inclusion | 62.9 | 62.9 | 40.52 | 51.71 | D - Other node or line within 3 km | 1.75 | 1.11 | Line: BINALONAN - UMINGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4490
4 | 1491 | 4491 | 0102822009 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Juan | 18.1108 | 120.7859 | R | 2438 | 3.7 | 659 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.95 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 61.56 | 61.56 | 41.85 | 51.71 | D - Other node or line within 3 km | 1.95 | 1.94 | Line: SEGMENT 2 SOLSONA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4491
4 | 1492 | 4492 | 1908706005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Ganta | 17.2541 | 122.2281 | R | 2917 | 4.3 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 1B: High GIDA Priority | 42.31 | 42.31 | 61.1 | 51.71 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4492
4 | 1493 | 4493 | 1908713021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Rifao | 17.254 | 122.2281 | U | 2647 | 4.3 | 616 | 185 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.29 | 34.19 | Tier 1B: High GIDA Priority | 33.25 | 33.25 | 70.18 | 51.71 | F - Nearest node and line over 5 km | 29.29 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4493
4 | 1494 | 4494 | 0301403002 | Region III (Central Luzon) | Bulacan | Baliuag | Barangca | 14.9876 | 120.8958 | R | 3538 | 3.5 | 1011 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.42 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 67.89 | 67.89 | 35.5 | 51.7 | C - Line within 0.5 km; node over 1 km | 2.42 | 0.34 | Line: SanLuis-Candaba Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4494
4 | 1495 | 4495 | 1102319003 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Bincungan | 7.3741 | 125.7778 | R | 4113 | 3.7 | 1112 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.13 | 2.33 | Tier 2B: Moderate GIDA Inclusion | 65.65 | 65.65 | 37.75 | 51.7 | D - Other node or line within 3 km | 3.13 | 2.33 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4495
4 | 1496 | 4496 | 0304921012 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Santo Tomas | 15.3595 | 120.9928 | U | 8398 | 3.5 | 2399 | 720 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.68 | 5.7 | Tier 2B: Moderate GIDA Inclusion | 65.27 | 65.27 | 38.13 | 51.7 | D - Other node or line within 3 km | 2.68 | 5.7 | Node: PRN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4496
4 | 1497 | 4497 | 0304908018 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Makabaclay | 15.2941 | 121.0447 | R | 3101 | 3.5 | 886 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.25 | 9.72 | Tier 2B: Moderate GIDA Inclusion | 59.91 | 59.91 | 43.5 | 51.7 | F - Nearest node and line over 5 km | 7.25 | 9.19 | Node: PRN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4497
4 | 1498 | 4498 | 0200903004 | Region II (Cagayan Valley) | Batanes | Ivana | Tuhel | 20.3727 | 121.9102 | R | 385 | 3 | 128 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 213.75 | 209.54 | Tier 1B: High GIDA Priority | 32.99 | 32.99 | 70.41 | 51.7 | F - Nearest node and line over 5 km | 212.63 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4498
4 | 1499 | 4499 | 0200903003 | Region II (Cagayan Valley) | Batanes | Ivana | San Vicente | 20.3807 | 121.9213 | R | 269 | 3 | 90 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 214.99 | 210.29 | Tier 1B: High GIDA Priority | 32.99 | 32.99 | 70.4 | 51.7 | F - Nearest node and line over 5 km | 213.39 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4499
4 | 1500 | 4500 | 0702239012 | Region VII (Central Visayas) | Cebu | Ronda | Santa Cruz | 10.0124 | 123.4126 | R | 3654 | 3.8 | 962 | 289 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 0.2 | Tier 2A: High Commercial ROI | 74.36 | 74.36 | 29.01 | 51.69 | C - Line within 0.5 km; node over 1 km | 1.47 | 0.04 | Line: Segment 9 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4500
4 | 1501 | 4501 | 1108204026 | Region XI (Davao Region) | Davao de Oro | Maco | Poblacion | 7.3612 | 125.859 | U | 8701 | 3.7 | 2352 | 706 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.61 | 0.6 | Tier 2B: Moderate GIDA Inclusion | 69.04 | 69.04 | 34.35 | 51.69 | B - Node 0.5-1 km | 0.61 | 0.6 | Line: TAGUM - PANTUKAN SEGMENT 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4501
4 | 1502 | 4502 | 0501606024 | Region V (Bicol Region) | Camarines Norte | Labo | Exciban | 14.1843 | 122.6564 | R | 3671 | 4 | 918 | 275 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.32 | 1.82 | Tier 2B: Moderate GIDA Inclusion | 66.23 | 66.23 | 37.16 | 51.69 | D - Other node or line within 3 km | 3.32 | 1.82 | Line: PAGBILAO - NAGA (UG + Aerial) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4502
4 | 1503 | 4503 | 0304929031 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | San Fabian | 15.5969 | 120.9067 | R | 2828 | 3.5 | 808 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.14 | 1.42 | Tier 2B: Moderate GIDA Inclusion | 65.24 | 65.24 | 38.13 | 51.69 | D - Other node or line within 3 km | 2.14 | 1.42 | Line: Existing UG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4503
4 | 1504 | 4504 | 0305413043 | Region III (Central Luzon) | Pampanga | Mexico | Santo Rosario | 15.0702 | 120.7241 | U | 4417 | 4 | 1104 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 0.47 | Tier 2B: Moderate GIDA Inclusion | 63.1 | 63.1 | 40.28 | 51.69 | B - Node 0.5-1 km | 0.94 | 0.47 | Line: Path Measure1 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4504
4 | 1505 | 4505 | 0405627002 | Region IV-A (CALABARZON) | Quezon | Mauban | Alitap | 14.1337 | 121.7506 | R | 520 | 3.8 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6 | 14.54 | Tier 1B: High GIDA Priority | 39.88 | 39.88 | 63.49 | 51.69 | F - Nearest node and line over 5 km | 6 | 14.45 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4505
4 | 1506 | 4506 | 1380606131 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 525 | 13.8971 | 121.6827 | U | 1673 | 4.1 | 408 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.46 | 7.4 | Tier 1B: High GIDA Priority | 34.49 | 34.49 | 68.89 | 51.69 | F - Nearest node and line over 5 km | 7.46 | 7.4 | Line: LUCENA - PAGBILAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4506
4 | 1507 | 4507 | 0200904002 | Region II (Cagayan Valley) | Batanes | Mahatao | Kaumbakan | 20.4066 | 121.9561 | R | 449 | 3 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 218.92 | 212.77 | Tier 1B: High GIDA Priority | 33.54 | 33.54 | 69.84 | 51.69 | F - Nearest node and line over 5 km | 215.87 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4507
4 | 1508 | 4508 | 1380611035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 820 | 13.6798 | 122.114 | U | 1362 | 4.08 | 334 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.65 | 6.65 | Tier 1B: High GIDA Priority | 32.77 | 32.77 | 70.6 | 51.69 | F - Nearest node and line over 5 km | 6.65 | 6.61 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4508
4 | 1509 | 4509 | 0203121017 | Region II (Cagayan Valley) | Isabela | Palanan | San Isidro | 17.134 | 122.5081 | R | 895 | 3.8 | 236 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 52.59 | 62.24 | Tier 1B: High GIDA Priority | 31.41 | 31.41 | 71.96 | 51.69 | F - Nearest node and line over 5 km | 52.59 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4509
4 | 1510 | 4510 | 0403420010 | Region IV-A (CALABARZON) | Laguna | Pakil | Rizal | 14.3751 | 121.4351 | R | 3431 | 3.3 | 1040 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 4.49 | Tier 2B: Moderate GIDA Inclusion | 67.44 | 67.44 | 35.93 | 51.68 | E - Nearest node or line 3-5 km | 3.5 | 4.49 | Node: PKL002 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4510
4 | 1511 | 4511 | 0504101003 | Region V (Bicol Region) | Masbate | Aroroy | Amotag | 12.3759 | 123.2643 | R | 2063 | 4.1 | 503 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.53 | 24.3 | Tier 1B: High GIDA Priority | 45.82 | 45.82 | 57.54 | 51.68 | F - Nearest node and line over 5 km | 12.53 | 30.46 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4511
4 | 1512 | 4512 | 1208005012 | Region XII (SOCCSKSARGEN) | Sarangani | Maitum | Pangi | 6.0413 | 124.5203 | R | 1121 | 3.9 | 287 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.3 | 56.9 | Tier 1B: High GIDA Priority | 34.16 | 34.16 | 69.2 | 51.68 | F - Nearest node and line over 5 km | 57.3 | 999999 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4512
4 | 1513 | 4513 | 1903631024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Pasayanan | 17.2548 | 122.2289 | R | 853 | 5.7 | 150 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.41 | 34.3 | Tier 1B: High GIDA Priority | 33.02 | 33.02 | 70.33 | 51.68 | F - Nearest node and line over 5 km | 29.41 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4513
4 | 1514 | 4514 | 1380610062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 737 | 12.9814 | 122.9666 | U | 2615 | 4.33 | 604 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.47 | 58.48 | Tier 1B: High GIDA Priority | 32.17 | 32.17 | 71.19 | 51.68 | F - Nearest node and line over 5 km | 38.47 | 999999 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4514
4 | 1515 | 4515 | 0704625010 | Region VII (Central Visayas) | Negros Oriental | Zamboanguita | Poblacion | 9.101 | 123.1991 | U | 6716 | 3.8 | 1767 | 530 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 16.48 | Tier 2A: High Commercial ROI | 70.15 | 70.15 | 33.18 | 51.67 | A - Node within 0.5 km | 0.33 | 18.68 | Node: ZAN001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4515
4 | 1516 | 4516 | 0600416002 | Region VI (Western Visayas) | Aklan | Numancia | Aliputos | 11.6993 | 122.335 | R | 2643 | 3.9 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.9 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 68.96 | 68.96 | 34.39 | 51.67 | B - Node 0.5-1 km | 0.9 | 3.24 | Node: NUK001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4516
4 | 1517 | 4517 | 0405809008 | Region IV-A (CALABARZON) | Rizal | Morong | San Pedro | 14.5105 | 121.2415 | U | 5797 | 3.6 | 1610 | 483 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.24 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 63.88 | 63.88 | 39.45 | 51.67 | C - Line within 0.5 km; node over 1 km | 1.24 | 0.39 | Line: Aerial 24C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4517
4 | 1518 | 4518 | 0402106016 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone I | 14.319 | 120.9667 | U | 4441 | 3.4 | 1306 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.74 | 2.35 | Tier 2B: Moderate GIDA Inclusion | 60.41 | 60.41 | 42.93 | 51.67 | B - Node 0.5-1 km | 0.74 | 2.3 | Node: DMC004 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4518
4 | 1519 | 4519 | 0803739022 | Region VIII (Eastern Visayas) | Leyte | Palo | Cavite West | 11.1583 | 124.9881 | R | 2036 | 3.8 | 536 | 161 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 60.02 | 60.02 | 43.32 | 51.67 | C - Line within 0.5 km; node over 1 km | 1.63 | 0.26 | Line: CAPOOCAN - TACLOBAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4519
4 | 1520 | 4520 | 1102407019 | Region XI (Davao Region) | Davao del Sur | Magsaysay | Tagaytay | 6.7536 | 125.0887 | R | 1685 | 3.4 | 496 | 149 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.98 | 21.97 | Tier 2B: Moderate GIDA Inclusion | 50.32 | 50.32 | 53.03 | 51.67 | F - Nearest node and line over 5 km | 6.98 | 21.94 | Node: MYD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4520
4 | 1521 | 4521 | 1705208058 | MIMAROPA Region | Oriental Mindoro | Naujan | San Nicolas | 13.2626 | 121.1845 | R | 1115 | 3.9 | 286 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.92 | 4.18 | Tier 1B: High GIDA Priority | 45.23 | 45.23 | 58.12 | 51.67 | E - Nearest node or line 3-5 km | 5.92 | 4.17 | Line: MINDORO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4521
4 | 1522 | 4522 | 1907002043 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Ungus-ungus | 14.4934 | 121.6513 | R | 1323 | 5.8 | 228 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.77 | 21.37 | Tier 1B: High GIDA Priority | 43.95 | 43.95 | 59.39 | 51.67 | D - Other node or line within 3 km | 2.77 | 21.37 | Node: RLQ003 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4522
4 | 1523 | 4523 | 0601906012 | Region VI (Western Visayas) | Capiz | Jamindan | Igang | 11.4691 | 122.4728 | R | 450 | 3.8 | 118 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.39 | 6.77 | Tier 1B: High GIDA Priority | 43.17 | 43.17 | 60.17 | 51.67 | F - Nearest node and line over 5 km | 7.39 | 6.77 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4523
4 | 1524 | 4524 | 1400119010 | Cordillera Administrative Region (CAR) | Abra | Pilar | Nagcanasan | 17.3682 | 120.5642 | R | 259 | 3.8 | 68 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.82 | 8.76 | Tier 1B: High GIDA Priority | 42.91 | 42.91 | 60.43 | 51.67 | F - Nearest node and line over 5 km | 8.82 | 8.75 | Line: SEGMENT 2 (CANDON - VIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4524
4 | 1525 | 4525 | 0401018009 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Calingatan | 13.9616 | 121.1212 | R | 3220 | 3.6 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 2.06 | Tier 2A: High Commercial ROI | 70.86 | 70.86 | 32.45 | 51.66 | B - Node 0.5-1 km | 0.82 | 2.06 | Node: MKB001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4525
4 | 1526 | 4526 | 0306916093 | Region III (Central Luzon) | Tarlac | City of Tarlac | Ungot | 15.4605 | 120.6137 | R | 4178 | 3.9 | 1071 | 321 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.28 | 1.56 | Tier 2B: Moderate GIDA Inclusion | 68.27 | 68.27 | 35.04 | 51.66 | D - Other node or line within 3 km | 2.28 | 1.54 | Line: PIPE 73-92 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4526
4 | 1527 | 4527 | 0403417040 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | San Francisco | 14.1064 | 121.4235 | R | 3008 | 3.3 | 912 | 274 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.34 | 1.05 | Tier 2B: Moderate GIDA Inclusion | 66.22 | 66.22 | 37.09 | 51.66 | D - Other node or line within 3 km | 3.34 | 1.03 | Line: SAN PABLO - LUCBAN AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4527
4 | 1528 | 4528 | 0405806008 | Region IV-A (CALABARZON) | Rizal | Cardona | Dalig | 14.4804 | 121.2343 | U | 6801 | 3.6 | 1889 | 567 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.69 | 0.55 | Tier 2B: Moderate GIDA Inclusion | 65.79 | 65.79 | 37.54 | 51.66 | B - Node 0.5-1 km | 0.69 | 0.55 | Line: TAYTAY TO SNL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4528
4 | 1529 | 4529 | 0205005026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | San Nicolas North | 16.4878 | 121.1501 | R | 2608 | 3.8 | 686 | 206 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.33 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 65.27 | 65.27 | 38.04 | 51.66 | A - Node within 0.5 km | 0.33 | 0.23 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4529
4 | 1530 | 4530 | 0102914024 | Region I (Ilocos Region) | Ilocos Sur | Narvacan | Quinarayan | 17.4449 | 120.4717 | R | 2782 | 3.8 | 732 | 220 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.2 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 64.8 | 64.8 | 38.51 | 51.66 | C - Line within 0.5 km; node over 1 km | 1.2 | 0.03 | Line: CABLE LAYED | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4530
4 | 1531 | 4531 | 0102805002 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Baay | 18.1161 | 120.5723 | R | 3290 | 3.7 | 889 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.43 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 63.74 | 63.74 | 39.59 | 51.66 | C - Line within 0.5 km; node over 1 km | 6.43 | 0.07 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4531
4 | 1532 | 4532 | 1401113007 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Poblacion | 16.3626 | 120.5522 | U | 8790 | 3.5 | 2511 | 753 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.92 | 1.45 | Tier 2B: Moderate GIDA Inclusion | 63.62 | 63.62 | 39.69 | 51.66 | D - Other node or line within 3 km | 3.92 | 1.45 | Line: TUBA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4532
4 | 1533 | 4533 | 0403404001 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Baclaran | 14.2274 | 121.2991 | U | 16011 | 3.3 | 4852 | 1456 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 5.55 | 5.48 | Tier 2B: Moderate GIDA Inclusion | 63.18 | 63.18 | 40.14 | 51.66 | F - Nearest node and line over 5 km | 5.55 | 5.48 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4533
4 | 1534 | 4534 | 0301405012 | Region III (Central Luzon) | Bulacan | Bulacan | San Nicolas | 14.7974 | 120.8681 | U | 6563 | 3.5 | 1875 | 562 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 3.51 | Tier 2B: Moderate GIDA Inclusion | 61.69 | 61.69 | 41.62 | 51.66 | D - Other node or line within 3 km | 1.08 | 3.49 | Node: BUB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4534
4 | 1535 | 4535 | 0301417006 | Region III (Central Luzon) | Bulacan | Plaridel | Bulihan | 14.8793 | 120.8999 | U | 7061 | 3.5 | 2017 | 605 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.68 | 2.11 | Tier 2B: Moderate GIDA Inclusion | 56.94 | 56.94 | 46.37 | 51.66 | D - Other node or line within 3 km | 5.68 | 2.09 | Line: PLARIDEL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4535
4 | 1536 | 4536 | 1402710003 | Cordillera Administrative Region (CAR) | Ifugao | Tinoc | Binablayan | 16.7329 | 120.9815 | R | 1550 | 3.9 | 397 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.17 | 15.38 | Tier 2B: Moderate GIDA Inclusion | 46.62 | 46.62 | 56.7 | 51.66 | F - Nearest node and line over 5 km | 12.17 | 15.36 | Node: KNF001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4536
4 | 1537 | 4537 | 0603013050 | Region VI (Western Visayas) | Iloilo | Calinog | Manaripay | 11.2373 | 122.3884 | R | 501 | 3.8 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.52 | 18.54 | Tier 1B: High GIDA Priority | 32.73 | 32.73 | 70.58 | 51.66 | F - Nearest node and line over 5 km | 31.52 | 22.79 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4537
4 | 1538 | 4538 | 0301415007 | Region III (Central Luzon) | Bulacan | Pandi | Cacarong Matanda | 14.9036 | 120.9673 | U | 13060 | 3.5 | 3731 | 1119 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.55 | 1.15 | Tier 2A: High Commercial ROI | 70 | 70 | 33.3 | 51.65 | D - Other node or line within 3 km | 1.55 | 1.15 | Line: PB HH24-25 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4538
4 | 1539 | 4539 | 0306914002 | Region III (Central Luzon) | Tarlac | San Manuel | Lanat | 15.7923 | 120.6061 | R | 2429 | 3.9 | 623 | 187 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.51 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 67.69 | 67.69 | 35.62 | 51.65 | B - Node 0.5-1 km | 0.51 | 0.1 | Line: Pipe 224-224A | Survey short node lateral; confirm port/fiber capacity, access and route. | 4539
4 | 1540 | 4540 | 0401011011 | Region IV-A (CALABARZON) | Batangas | Laurel | Gulod | 14.0331 | 120.9411 | R | 3182 | 3.6 | 884 | 265 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.38 | 6.91 | Tier 2B: Moderate GIDA Inclusion | 63.48 | 63.48 | 39.82 | 51.65 | D - Other node or line within 3 km | 2.38 | 6.91 | Node: LRB002 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4540
4 | 1541 | 4541 | 0402120008 | Region IV-A (CALABARZON) | Cavite | Tanza | Capipisa | 14.3583 | 120.7925 | U | 7841 | 3.4 | 2306 | 692 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.52 | 1.06 | Tier 2B: Moderate GIDA Inclusion | 62.82 | 62.82 | 40.49 | 51.65 | D - Other node or line within 3 km | 3.52 | 0.99 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4541
4 | 1542 | 4542 | 0405802010 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mambugan | 14.6184 | 121.1358 | U | 52920 | 3.6 | 14700 | 4410 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 1.82 | 0.7 | Tier 2B: Moderate GIDA Inclusion | 57.72 | 57.72 | 45.58 | 51.65 | D - Other node or line within 3 km | 1.82 | 0.67 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4542
4 | 1543 | 4543 | 0102906008 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Bagani Ubbog | 17.192 | 120.4589 | R | 1741 | 3.8 | 458 | 137 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 57.17 | 57.17 | 46.14 | 51.65 | D - Other node or line within 3 km | 1.3 | 1.13 | Line: SEGMENT 2 (CANDON - VIGAN) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4543
4 | 1544 | 4544 | 1705303008 | MIMAROPA Region | Palawan | Araceli | Mauringuen | 10.5555 | 119.8239 | R | 1088 | 3.9 | 279 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.93 | 39.67 | Tier 1B: High GIDA Priority | 38.68 | 38.68 | 64.61 | 51.65 | F - Nearest node and line over 5 km | 30.93 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4544
4 | 1545 | 4545 | 1908824008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Kedati | 16.1046 | 122.4657 | R | 1096 | 4.7 | 233 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.23 | 40.88 | Tier 1B: High GIDA Priority | 30.16 | 30.16 | 73.14 | 51.65 | F - Nearest node and line over 5 km | 41.23 | 999999 | Node: CSA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4545
4 | 1546 | 4546 | 1001314006 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Diclum | 8.3736 | 124.8495 | R | 5043 | 3.8 | 1327 | 398 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.37 | 0.19 | Tier 2A: High Commercial ROI | 74.22 | 74.22 | 29.06 | 51.64 | A - Node within 0.5 km | 0.37 | 0.09 | Line: CAGAYAN DE ORO - MALAYBALAY | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4546
4 | 1547 | 4547 | 0405647007 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angustias Zone I | 14.0171 | 121.6203 | R | 368 | 3.8 | 97 | 29 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.98 | 1.73 | Tier 1B: High GIDA Priority | 45.59 | 45.59 | 57.68 | 51.64 | D - Other node or line within 3 km | 2.98 | 1.73 | Line: LILIW - LUCENA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4547
4 | 1548 | 4548 | 1906618007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Malanta | 17.2556 | 122.2297 | R | 1805 | 6 | 301 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 34.4 | Tier 1B: High GIDA Priority | 36.94 | 36.94 | 66.35 | 51.64 | F - Nearest node and line over 5 km | 29.54 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4548
4 | 1549 | 4549 | 1380603016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 307 | 13.6851 | 121.5135 | U | 1399 | 3.44 | 407 | 122 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.77 | 14.24 | Tier 1B: High GIDA Priority | 32.87 | 32.87 | 70.41 | 51.64 | F - Nearest node and line over 5 km | 8.77 | 18.19 | Node: SJB003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4549
4 | 1550 | 4550 | 0307105018 | Region III (Central Luzon) | Zambales | Iba | Santo Rosario | 15.3311 | 119.9654 | R | 4578 | 3.8 | 1205 | 362 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.4 | 0.09 | Tier 2A: High Commercial ROI | 70.08 | 70.08 | 33.17 | 51.63 | C - Line within 0.5 km; node over 1 km | 1.4 | 0.09 | Line: IBA TO SANTA CRUZ | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4550
4 | 1551 | 4551 | 0403403009 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Langkiwa | 14.2999 | 121.0602 | U | 43327 | 3.3 | 13129 | 3939 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 0.55 | 1.37 | Tier 2B: Moderate GIDA Inclusion | 62.08 | 62.08 | 41.18 | 51.63 | B - Node 0.5-1 km | 0.55 | 1.32 | Node: BNL003 - TYPE 4A | Survey short node lateral; confirm port/fiber capacity, access and route. | 4551
4 | 1552 | 4552 | 0301422027 | Region III (Central Luzon) | Bulacan | San Rafael | Sampaloc | 14.9801 | 120.9297 | U | 4683 | 3.5 | 1338 | 401 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 61.92 | 61.92 | 41.34 | 51.63 | C - Line within 0.5 km; node over 1 km | 2.05 | 0.37 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4552
4 | 1553 | 4553 | 0102820010 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Guillermo | 18.1531 | 120.5955 | U | 1703 | 3.7 | 460 | 138 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.93 | 1.03 | Tier 2B: Moderate GIDA Inclusion | 48.71 | 48.71 | 54.55 | 51.63 | D - Other node or line within 3 km | 1.93 | 0.99 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4553
4 | 1554 | 4554 | 1906607007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Bulangsi | 17.2556 | 122.2296 | R | 1808 | 6 | 301 | 90 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.39 | Tier 1B: High GIDA Priority | 36.94 | 36.94 | 66.32 | 51.63 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4554
4 | 1555 | 4555 | 1381100069 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 69 | 14.504 | 120.922 | U | 1193 | 3.52 | 339 | 102 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.93 | 5.96 | Tier 1B: High GIDA Priority | 33.81 | 33.81 | 69.46 | 51.63 | E - Nearest node or line 3-5 km | 4.93 | 5.96 | Node: CVC001 -TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4555
4 | 1556 | 4556 | 0301422007 | Region III (Central Luzon) | Bulacan | San Rafael | Diliman I | 15.0259 | 120.9491 | R | 3799 | 3.5 | 1085 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.05 | 1.55 | Tier 2B: Moderate GIDA Inclusion | 68.66 | 68.66 | 34.57 | 51.62 | D - Other node or line within 3 km | 2.05 | 1.55 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4556
4 | 1557 | 4557 | 0403427002 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Bagong Pook | 14.4708 | 121.4295 | R | 2532 | 3.3 | 767 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.99 | 2.98 | Tier 2B: Moderate GIDA Inclusion | 67.07 | 67.07 | 36.17 | 51.62 | B - Node 0.5-1 km | 0.99 | 2.98 | Node: SML001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4557
4 | 1558 | 4558 | 0203122010 | Region II (Cagayan Valley) | Isabela | Quezon | Minagbag | 17.3868 | 121.6045 | R | 3083 | 3.8 | 811 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.39 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 65.81 | 65.81 | 37.43 | 51.62 | C - Line within 0.5 km; node over 1 km | 7.39 | 0.16 | Line: QUEZON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4558
4 | 1559 | 4559 | 0304930042 | Region III (Central Luzon) | Nueva Ecija | Talavera | Pag-asa | 15.5846 | 120.9168 | U | 5626 | 3.5 | 1607 | 482 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.4 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 65.73 | 65.73 | 37.52 | 51.62 | A - Node within 0.5 km | 0.4 | 0.33 | Line: SEGMENT 17 (ZARAGOSA - SAN JOSE) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4559
4 | 1560 | 4560 | 1705318003 | MIMAROPA Region | Palawan | Roxas | Bagong Bayan | 10.4307 | 119.567 | R | 1265 | 3.9 | 324 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.4 | 20.95 | Tier 1B: High GIDA Priority | 35.59 | 35.59 | 67.64 | 51.62 | F - Nearest node and line over 5 km | 27.4 | 20.89 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4560
4 | 1561 | 4561 | 1380606015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 409 | 11.8072 | 121.774 | U | 1673 | 2.72 | 616 | 185 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.41 | 23.02 | Tier 1B: High GIDA Priority | 32.52 | 32.52 | 70.72 | 51.62 | F - Nearest node and line over 5 km | 24.41 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4561
4 | 1562 | 4562 | 1001314005 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Damilag | 8.3695 | 124.8545 | U | 18241 | 3.8 | 4800 | 1440 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.08 | 0.24 | Tier 2A: High Commercial ROI | 74.82 | 74.82 | 28.41 | 51.61 | C - Line within 0.5 km; node over 1 km | 1.08 | 0.23 | Line: CAGAYAN DE ORO - MALAYBALAY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4562
4 | 1563 | 4563 | 0402114022 | Region IV-A (CALABARZON) | Cavite | Mendez | Galicia III | 14.1498 | 120.8929 | R | 4462 | 3.4 | 1312 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 6.47 | Tier 2A: High Commercial ROI | 71.07 | 71.07 | 32.15 | 51.61 | D - Other node or line within 3 km | 1.47 | 6.44 | Node: MZC001 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4563
4 | 1564 | 4564 | 0401029002 | Region IV-A (CALABARZON) | Batangas | Taal | Balisong | 13.8788 | 120.9329 | R | 3638 | 3.6 | 1011 | 303 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.74 | 1.1 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 34.53 | 51.61 | D - Other node or line within 3 km | 1.74 | 1.1 | Line: WP BYB001 TO BCY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4564
4 | 1565 | 4565 | 0403415013 | Region IV-A (CALABARZON) | Laguna | Magdalena | Ibabang Butnong | 14.2199 | 121.4358 | R | 2187 | 3.3 | 663 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.43 | 0.84 | Tier 2B: Moderate GIDA Inclusion | 65.4 | 65.4 | 37.82 | 51.61 | D - Other node or line within 3 km | 2.43 | 0.84 | Line: SEGMENT 26 (PAGSANJAN - LILIW) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4565
4 | 1566 | 4566 | 0402115014 | Region IV-A (CALABARZON) | Cavite | Naic | Kanluran | 14.3008 | 120.7758 | R | 1856 | 3.4 | 546 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.36 | 1.12 | Tier 2B: Moderate GIDA Inclusion | 57.83 | 57.83 | 45.39 | 51.61 | D - Other node or line within 3 km | 2.36 | 1.12 | Line: MARAGONDON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4566
4 | 1567 | 4567 | 1906618009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | North Manubul | 5.473 | 120.799 | R | 5354 | 6 | 892 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 213.08 | 213.07 | Tier 2B: Moderate GIDA Inclusion | 51.76 | 51.76 | 51.46 | 51.61 | F - Nearest node and line over 5 km | 213.08 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4567
4 | 1568 | 4568 | 0500513029 | Region V (Bicol Region) | Albay | Pio Duran | Salvacion | 13.0836 | 123.5056 | R | 603 | 4.1 | 147 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.59 | 15.73 | Tier 1B: High GIDA Priority | 43.82 | 43.82 | 59.41 | 51.61 | F - Nearest node and line over 5 km | 5.59 | 15.63 | Node: PDA001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4568
4 | 1569 | 4569 | 0401029051 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 14 | 13.9232 | 120.916 | R | 512 | 3.6 | 142 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.59 | 2.79 | Tier 1B: High GIDA Priority | 43.01 | 43.01 | 60.22 | 51.61 | D - Other node or line within 3 km | 2.59 | 2.79 | Node: ALB001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4569
4 | 1570 | 4570 | 1380606213 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 606 | 13.0597 | 121.4543 | U | 443 | 4.39 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.21 | 1.12 | Tier 1B: High GIDA Priority | 33.46 | 33.46 | 69.76 | 51.61 | D - Other node or line within 3 km | 3.21 | 1.11 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4570
4 | 1571 | 4571 | 0200903002 | Region II (Cagayan Valley) | Batanes | Ivana | Salagao | 20.3685 | 121.9205 | R | 370 | 3 | 123 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 213.67 | 208.95 | Tier 1B: High GIDA Priority | 32.99 | 32.99 | 70.22 | 51.61 | F - Nearest node and line over 5 km | 212.04 | 999999 | Node: SAC001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4571
4 | 1572 | 4572 | 0806022014 | Region VIII (Eastern Visayas) | Samar | Paranas | Cawayan | 11.7921 | 125.0322 | R | 352 | 4.1 | 86 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 61.52 | 64.5 | Tier 1B: High GIDA Priority | 32.2 | 32.2 | 71.02 | 51.61 | F - Nearest node and line over 5 km | 61.52 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4572
4 | 1573 | 4573 | 0105533030 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw Vidal | 16.1492 | 120.4241 | R | 3605 | 3.6 | 1001 | 300 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.56 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 65.57 | 65.57 | 37.63 | 51.6 | C - Line within 0.5 km; node over 1 km | 4.56 | 0.05 | Line: SAN FABIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4573
4 | 1574 | 4574 | 0301420033 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc East | 14.8394 | 121.081 | U | 5619 | 3.5 | 1605 | 482 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.95 | 4.18 | Tier 2B: Moderate GIDA Inclusion | 61.12 | 61.12 | 42.08 | 51.6 | B - Node 0.5-1 km | 0.95 | 5.1 | Node: SJD002 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4574
4 | 1575 | 4575 | 0203134011 | Region II (Cagayan Valley) | Isabela | Santa Maria | Naganacan | 17.4296 | 121.6674 | R | 1821 | 3.8 | 479 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.67 | 2.35 | Tier 2B: Moderate GIDA Inclusion | 49.81 | 49.81 | 53.39 | 51.6 | D - Other node or line within 3 km | 10.67 | 2.31 | Line: SANTA MARIA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4575
4 | 1576 | 4576 | 1204702005 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Cadiis | 7.4562 | 124.8218 | R | 2932 | 3.8 | 772 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.84 | 4.74 | Tier 2B: Moderate GIDA Inclusion | 48.61 | 48.61 | 54.58 | 51.6 | E - Nearest node or line 3-5 km | 18.84 | 4.72 | Line: MATALAM - CARMEN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4576
4 | 1577 | 4577 | 0307702004 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 4 | 16.2296 | 122.0953 | R | 232 | 3.8 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.26 | 2.48 | Tier 1B: High GIDA Priority | 39.81 | 39.81 | 63.4 | 51.6 | F - Nearest node and line over 5 km | 6.26 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4577
4 | 1578 | 4578 | 1907004008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Doh-Tong | 17.2559 | 122.2299 | R | 1946 | 5.8 | 336 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.57 | 34.44 | Tier 1B: High GIDA Priority | 37.89 | 37.89 | 65.3 | 51.6 | F - Nearest node and line over 5 km | 29.57 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4578
4 | 1579 | 4579 | 1906612030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Manta | 17.2555 | 122.2295 | R | 1621 | 6 | 270 | 81 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 31.65 | 31.65 | 71.55 | 51.6 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4579
4 | 1580 | 4580 | 0702235014 | Region VII (Central Visayas) | Cebu | Oslob | Lagunde | 9.5257 | 123.4359 | R | 3347 | 3.8 | 881 | 264 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.68 | 0.06 | Tier 2A: High Commercial ROI | 73.96 | 73.96 | 29.22 | 51.59 | B - Node 0.5-1 km | 0.68 | 0.06 | Line: Boljoon-Oslob | Survey short node lateral; confirm port/fiber capacity, access and route. | 4580
4 | 1581 | 4581 | 0306905019 | Region III (Central Luzon) | Tarlac | Concepcion | Minane | 15.3201 | 120.6508 | R | 3879 | 3.9 | 995 | 298 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.56 | 0.19 | Tier 2A: High Commercial ROI | 71.03 | 71.03 | 32.14 | 51.59 | B - Node 0.5-1 km | 0.56 | 0.19 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 4581
4 | 1582 | 4582 | 0301417019 | Region III (Central Luzon) | Bulacan | Plaridel | Santo Niño | 14.8831 | 120.8387 | U | 11206 | 3.5 | 3202 | 961 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 66.97 | 66.97 | 36.2 | 51.59 | C - Line within 0.5 km; node over 1 km | 2.49 | 0.06 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4582
4 | 1583 | 4583 | 1400118012 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Poblacion East | 17.5693 | 120.5903 | R | 1656 | 3.8 | 436 | 131 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 0.66 | Tier 2B: Moderate GIDA Inclusion | 58.6 | 58.6 | 44.57 | 51.59 | D - Other node or line within 3 km | 3.25 | 0.62 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4583
4 | 1584 | 4584 | 0501712005 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Domagondong | 13.9044 | 122.6657 | R | 383 | 4.2 | 91 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.2 | 1.4 | Tier 2B: Moderate GIDA Inclusion | 51.21 | 51.21 | 51.97 | 51.59 | D - Other node or line within 3 km | 7.2 | 1.4 | Line: CALAUAG TO RAGAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4584
4 | 1585 | 4585 | 1380601096 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 96 | 13.4484 | 120.7636 | U | 2230 | 4.54 | 491 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.54 | 14.94 | Tier 1B: High GIDA Priority | 29.25 | 29.25 | 73.93 | 51.59 | F - Nearest node and line over 5 km | 16.54 | 14.46 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4585
4 | 1586 | 4586 | 0306916026 | Region III (Central Luzon) | Tarlac | City of Tarlac | Carangian | 15.4816 | 120.5705 | U | 10634 | 3.9 | 2727 | 818 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.02 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 63.79 | 63.79 | 39.37 | 51.58 | C - Line within 0.5 km; node over 1 km | 4.02 | 0.04 | Line: 48 CORE (8X6) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4586
4 | 1587 | 4587 | 0401009021 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 7 | 13.9056 | 121.0483 | U | 2231 | 3.6 | 620 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.89 | Tier 2B: Moderate GIDA Inclusion | 59.39 | 59.39 | 43.76 | 51.58 | B - Node 0.5-1 km | 0.82 | 0.83 | Node: CUE001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4587
4 | 1588 | 4588 | 1208007004 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Banahaw | 6.301 | 125.2821 | R | 2087 | 3.9 | 535 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.29 | 3.13 | Tier 2B: Moderate GIDA Inclusion | 53.63 | 53.63 | 49.53 | 51.58 | E - Nearest node or line 3-5 km | 3.29 | 3.13 | Line: DAVAO CITY - GENSAN | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4588
4 | 1589 | 4589 | 1705208034 | MIMAROPA Region | Oriental Mindoro | Naujan | Montelago | 13.2254 | 121.376 | R | 2082 | 3.9 | 534 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.54 | 11.36 | Tier 2B: Moderate GIDA Inclusion | 48.43 | 48.43 | 54.74 | 51.58 | F - Nearest node and line over 5 km | 9.54 | 11.36 | Node: NJM003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4589
4 | 1590 | 4590 | 1907005016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Datu Baguinda Putih | 17.2558 | 122.2299 | R | 3403 | 5.8 | 587 | 176 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 39.94 | 39.94 | 63.23 | 51.58 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4590
4 | 1591 | 4591 | 0802607022 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | San Roque | 11.222 | 125.4933 | R | 105 | 3.9 | 27 | 8 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 52.79 | 51.66 | Tier 1B: High GIDA Priority | 36.73 | 36.73 | 66.44 | 51.58 | F - Nearest node and line over 5 km | 52.79 | 999999 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4591
4 | 1592 | 4592 | 1380614020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 764 | 12.2809 | 122.7381 | U | 2073 | 3.32 | 625 | 188 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59.37 | 51.5 | Tier 1B: High GIDA Priority | 32.78 | 32.78 | 70.37 | 51.58 | F - Nearest node and line over 5 km | 59.37 | 999999 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4592
4 | 1593 | 4593 | 0604509002 | Region VI (Western Visayas) | Negros Occidental | City of Escalante | Balintawak | 10.8394 | 123.4969 | U | 14659 | 3.7 | 3962 | 1189 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.41 | 0.08 | Tier 2A: High Commercial ROI | 74.55 | 74.55 | 28.6 | 51.57 | A - Node within 0.5 km | 0.41 | 0.08 | Line: VICTORIAS(MANAPLA) - ESCALANTE | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4593
4 | 1594 | 4594 | 1606801015 | Region XIII (Caraga) | Surigao del Sur | Barobo | Poblacion | 8.5333 | 126.1225 | U | 14683 | 4.1 | 3581 | 1074 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 0.56 | 0.14 | Tier 2A: High Commercial ROI | 72.51 | 72.51 | 30.63 | 51.57 | B - Node 0.5-1 km | 0.56 | 0.14 | Line: Route | Survey short node lateral; confirm port/fiber capacity, access and route. | 4594
4 | 1595 | 4595 | 0203113009 | Region II (Cagayan Valley) | Isabela | Gamu | Guibang | 17.0561 | 121.8561 | R | 3122 | 3.8 | 822 | 247 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 0.17 | Tier 2A: High Commercial ROI | 70.41 | 70.41 | 32.72 | 51.57 | C - Line within 0.5 km; node over 1 km | 1.99 | 0.15 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4595
4 | 1596 | 4596 | 0301409014 | Region III (Central Luzon) | Bulacan | Hagonoy | San Nicolas | 14.8276 | 120.7297 | R | 4852 | 3.5 | 1386 | 416 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.67 | 4.05 | Tier 2B: Moderate GIDA Inclusion | 65.2 | 65.2 | 37.93 | 51.57 | D - Other node or line within 3 km | 2.67 | 8.85 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4596
4 | 1597 | 4597 | 0201529021 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Cataggaman Nuevo | 17.6009 | 121.7109 | U | 9807 | 3.9 | 2515 | 754 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.59 | 1.4 | Tier 2B: Moderate GIDA Inclusion | 62.66 | 62.66 | 40.48 | 51.57 | D - Other node or line within 3 km | 4.59 | 1.4 | Line: TUGEGARAO FOC | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4597
4 | 1598 | 4598 | 1108207002 | Region XI (Davao Region) | Davao de Oro | Monkayo | Babag | 7.7467 | 126.07 | R | 2869 | 3.7 | 775 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.1 | 6.57 | Tier 2B: Moderate GIDA Inclusion | 54.94 | 54.94 | 48.21 | 51.57 | F - Nearest node and line over 5 km | 9.1 | 6.54 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4598
4 | 1599 | 4599 | 0102929005 | Region I (Ilocos Region) | Ilocos Sur | Sigay | San Elias | 17.0308 | 120.5839 | R | 474 | 3.8 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.14 | 12.28 | Tier 1B: High GIDA Priority | 44.36 | 44.36 | 58.79 | 51.57 | F - Nearest node and line over 5 km | 6.14 | 11.89 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4599
4 | 1600 | 4600 | 1705318002 | MIMAROPA Region | Palawan | Roxas | Antonino | 10.4353 | 119.4969 | R | 1504 | 3.9 | 386 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.19 | 13.27 | Tier 1B: High GIDA Priority | 38.24 | 38.24 | 64.89 | 51.57 | F - Nearest node and line over 5 km | 21.19 | 13.21 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4600
4 | 1601 | 4601 | 1003515023 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Rarab | 7.8092 | 123.8894 | R | 1019 | 4.2 | 243 | 73 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.83 | 16.46 | Tier 1B: High GIDA Priority | 33.95 | 33.95 | 69.19 | 51.57 | F - Nearest node and line over 5 km | 27.83 | 16.46 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4601
4 | 1602 | 4602 | 1380606133 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 527 | 13.6896 | 122.6048 | U | 2424 | 4.36 | 556 | 167 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.03 | 11.67 | Tier 1B: High GIDA Priority | 33.67 | 33.67 | 69.46 | 51.57 | F - Nearest node and line over 5 km | 12.03 | 11.67 | Line: AE LZQ001 TO SNQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4602
4 | 1603 | 4603 | 1381100122 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 122 | 14.4192 | 121.1002 | U | 1205 | 3.43 | 351 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.61 | 5.39 | Tier 1B: High GIDA Priority | 33.65 | 33.65 | 69.49 | 51.57 | F - Nearest node and line over 5 km | 5.61 | 5.38 | Line: Aerial 24C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4603
4 | 1604 | 4604 | 1381100173 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 173 | 14.5124 | 120.7802 | U | 1708 | 3.15 | 543 | 163 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.29 | 14.37 | Tier 1B: High GIDA Priority | 33.12 | 33.12 | 70.01 | 51.57 | F - Nearest node and line over 5 km | 12.29 | 14.37 | Node: CVC001 -TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4604
4 | 1605 | 4605 | 1908801008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Ampatuan | Saniag | 6.8319 | 124.4569 | R | 1470 | 4.7 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 28.67 | 28.61 | Tier 1B: High GIDA Priority | 32.87 | 32.87 | 70.28 | 51.57 | F - Nearest node and line over 5 km | 28.67 | 28.61 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4605
4 | 1606 | 4606 | 1380612037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 871 | 12.2215 | 120.7141 | U | 2480 | 4.07 | 609 | 183 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.7 | 40.46 | Tier 1B: High GIDA Priority | 32.35 | 32.35 | 70.8 | 51.57 | F - Nearest node and line over 5 km | 40.7 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4606
4 | 1607 | 4607 | 0405810009 | Region IV-A (CALABARZON) | Rizal | Pililla | Wawa | 14.4546 | 121.3256 | R | 4180 | 3.6 | 1161 | 348 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.1 | 0.97 | Tier 2A: High Commercial ROI | 70.25 | 70.25 | 32.86 | 51.56 | D - Other node or line within 3 km | 1.1 | 0.97 | Line: TAYTAY TO SNL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4607
4 | 1608 | 4608 | 0105503009 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Bued | 16.1599 | 119.9989 | R | 3741 | 3.6 | 1039 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.81 | 1.79 | Tier 2B: Moderate GIDA Inclusion | 68.89 | 68.89 | 34.23 | 51.56 | D - Other node or line within 3 km | 1.81 | 1.74 | Line: ALAMINOS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4608
4 | 1609 | 4609 | 1102315027 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Quezon | 7.3325 | 125.6792 | U | 7049 | 3.7 | 1905 | 572 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.49 | 1.52 | Tier 2B: Moderate GIDA Inclusion | 63.42 | 63.42 | 39.7 | 51.56 | D - Other node or line within 3 km | 3.49 | 1.52 | Line: DAVAO CITY - TRENTO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4609
4 | 1610 | 4610 | 0300803027 | Region III (Central Luzon) | Bataan | City of Balanga | Lote | 14.6694 | 120.5132 | R | 2789 | 3.6 | 775 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.33 | 1.43 | Tier 2B: Moderate GIDA Inclusion | 62.8 | 62.8 | 40.33 | 51.56 | D - Other node or line within 3 km | 3.33 | 1.43 | Line: Bagac-Pilar AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4610
4 | 1611 | 4611 | 0304930051 | Region III (Central Luzon) | Nueva Ecija | Talavera | San Pascual | 15.612 | 120.9158 | U | 7130 | 3.5 | 2037 | 611 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 62.36 | 62.36 | 40.76 | 51.56 | C - Line within 0.5 km; node over 1 km | 3.35 | 0.08 | Line: Existing UG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4611
4 | 1612 | 4612 | 0403413002 | Region IV-A (CALABARZON) | Laguna | Lumban | Balimbingan | 14.2956 | 121.4578 | R | 1153 | 3.3 | 349 | 105 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.34 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 56.03 | 56.03 | 47.09 | 51.56 | A - Node within 0.5 km | 0.34 | 0.46 | Node: LML002 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4612
4 | 1613 | 4613 | 1380614097 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 904 | 13.8766 | 122.048 | U | 1799 | 4.66 | 386 | 116 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.25 | 3.67 | Tier 1B: High GIDA Priority | 32.98 | 32.98 | 70.14 | 51.56 | E - Nearest node or line 3-5 km | 8.25 | 3.66 | Line: UNISAN TO MULANAY | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4613
4 | 1614 | 4614 | 1380601069 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 69 | 12.5527 | 120.7102 | U | 2143 | 4.37 | 490 | 147 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.56 | 42.84 | Tier 1B: High GIDA Priority | 29.2 | 29.2 | 73.91 | 51.56 | F - Nearest node and line over 5 km | 44.56 | 999999 | Node: JOM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4614
4 | 1615 | 4615 | 1380601036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 36 | 12.9819 | 120.5759 | U | 2267 | 4.71 | 481 | 144 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 68.05 | 66.81 | Tier 1B: High GIDA Priority | 28.94 | 28.94 | 74.19 | 51.56 | F - Nearest node and line over 5 km | 68.05 | 999999 | Node: PGM002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4615
4 | 1616 | 4616 | 0403405005 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bubuyan | 14.1719 | 121.104 | R | 3500 | 3.3 | 1061 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.61 | 0.5 | Tier 2A: High Commercial ROI | 70.89 | 70.89 | 32.2 | 51.55 | B - Node 0.5-1 km | 0.61 | 0.5 | Line: Untitled Path | Survey short node lateral; confirm port/fiber capacity, access and route. | 4616
4 | 1617 | 4617 | 1600306004 | Region XIII (Caraga) | Agusan del Sur | Prosperidad | Poblacion | 8.6214 | 125.9051 | U | 13580 | 3.9 | 3482 | 1045 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.78 | 0.46 | Tier 2A: High Commercial ROI | 70.01 | 70.01 | 33.09 | 51.55 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.42 | Line: TRENTO - BUENAVISTA CLS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4617
4 | 1618 | 4618 | 0201518010 | Region II (Cagayan Valley) | Cagayan | Pamplona | Curva | 18.3899 | 121.3931 | R | 4010 | 3.9 | 1028 | 308 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 0.63 | Tier 2B: Moderate GIDA Inclusion | 69.36 | 69.36 | 33.75 | 51.55 | D - Other node or line within 3 km | 5.83 | 0.63 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4618
4 | 1619 | 4619 | 1003522019 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | Poblacion | 8.0513 | 123.7939 | U | 11654 | 4.2 | 2775 | 832 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.1 | 0.54 | Tier 2B: Moderate GIDA Inclusion | 69.24 | 69.24 | 33.87 | 51.55 | D - Other node or line within 3 km | 1.1 | 0.52 | Line: ILIGAN - PAGADIAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4619
4 | 1620 | 4620 | 0702208022 | Region VII (Central Visayas) | Cebu | Balamban | Pondol | 10.4906 | 123.7166 | U | 10482 | 3.8 | 2758 | 827 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.07 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 68.5 | 68.5 | 34.61 | 51.55 | C - Line within 0.5 km; node over 1 km | 2.07 | 0.39 | Line: 104.3km-96FOC-toledo-san remigio | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4620
4 | 1621 | 4621 | 0306916082 | Region III (Central Luzon) | Tarlac | City of Tarlac | Sapang Tagalog | 15.4218 | 120.5992 | U | 5451 | 3.9 | 1398 | 419 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.26 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 65.4 | 65.4 | 37.71 | 51.55 | A - Node within 0.5 km | 0.26 | 0.06 | Line: PIPE 53-64 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4621
4 | 1622 | 4622 | 0402118007 | Region IV-A (CALABARZON) | Cavite | Silang | Biga I | 14.2499 | 120.9764 | U | 8042 | 3.4 | 2365 | 710 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.55 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 62.06 | 62.06 | 41.04 | 51.55 | C - Line within 0.5 km; node over 1 km | 4.55 | 0.09 | Line: SILANG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4622
4 | 1623 | 4623 | 0403420013 | Region IV-A (CALABARZON) | Laguna | Pakil | Tavera | 14.3792 | 121.4231 | R | 1984 | 3.3 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 5.57 | Tier 2B: Moderate GIDA Inclusion | 60.34 | 60.34 | 42.76 | 51.55 | D - Other node or line within 3 km | 2.32 | 5.57 | Node: PKL002 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4623
4 | 1624 | 4624 | 0306909013 | Region III (Central Luzon) | Tarlac | Moncada | Camposanto 1 - Norte | 15.7413 | 120.5741 | R | 1676 | 3.9 | 430 | 129 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.1 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 55.14 | 55.14 | 47.97 | 51.55 | C - Line within 0.5 km; node over 1 km | 2.1 | 0.16 | Line: Pipe 202-202A | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4624
4 | 1625 | 4625 | 0102805009 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Ben-agan | 18.0569 | 120.5833 | R | 725 | 3.7 | 196 | 59 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.28 | 2.59 | Tier 1B: High GIDA Priority | 43.81 | 43.81 | 59.29 | 51.55 | D - Other node or line within 3 km | 3.28 | 2.58 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4625
4 | 1626 | 4626 | 1380614085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 892 | 13.2828 | 121.1835 | U | 1294 | 4.13 | 313 | 94 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.67 | 2.54 | Tier 1B: High GIDA Priority | 34.17 | 34.17 | 68.93 | 51.55 | D - Other node or line within 3 km | 3.67 | 2.54 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4626
4 | 1627 | 4627 | 0806407066 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Combado | 10.1344 | 124.8288 | U | 5919 | 4.1 | 1444 | 433 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.17 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 68.7 | 68.7 | 34.38 | 51.54 | A - Node within 0.5 km | 0.17 | 0.18 | Node: MSL001 - TYPE 2 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4627
4 | 1628 | 4628 | 0304921013 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Sinasajan | 15.3494 | 121.0168 | U | 5591 | 3.5 | 1597 | 479 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 7.51 | Tier 2B: Moderate GIDA Inclusion | 66.55 | 66.55 | 36.53 | 51.54 | A - Node within 0.5 km | 0.47 | 7.25 | Node: PRN001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4628
4 | 1629 | 4629 | 0401031034 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 3 | 14.1001 | 121.0961 | U | 5284 | 3.6 | 1468 | 440 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.28 | 5.01 | Tier 2B: Moderate GIDA Inclusion | 61.86 | 61.86 | 41.23 | 51.54 | A - Node within 0.5 km | 0.28 | 5.01 | Node: TNB003 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4629
4 | 1630 | 4630 | 0401029050 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 13 | 13.8526 | 120.9213 | R | 247 | 3.6 | 69 | 21 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.31 | 4.2 | Tier 2B: Moderate GIDA Inclusion | 46.53 | 46.53 | 56.55 | 51.54 | A - Node within 0.5 km | 0.31 | 4.2 | Node: SUB001 - TYPE 4 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4630
4 | 1631 | 4631 | 1204712057 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Talitay | 7.026 | 124.7058 | R | 2002 | 3.8 | 527 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.06 | 14.87 | Tier 1B: High GIDA Priority | 41.74 | 41.74 | 61.34 | 51.54 | F - Nearest node and line over 5 km | 22.06 | 14.77 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4631
4 | 1632 | 4632 | 0701248002 | Region VII (Central Visayas) | Bohol | Bien Unido | Bilangbilangan Diot | 10.2437 | 124.4656 | R | 745 | 4 | 186 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.66 | 33.43 | Tier 1B: High GIDA Priority | 37.53 | 37.53 | 65.55 | 51.54 | F - Nearest node and line over 5 km | 41.66 | 33.42 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4632
4 | 1633 | 4633 | 0907303009 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Dagum | 7.9006 | 123.1005 | R | 389 | 3.9 | 100 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.64 | 13.38 | Tier 1B: High GIDA Priority | 31.54 | 31.54 | 71.54 | 51.54 | F - Nearest node and line over 5 km | 19.64 | 13.35 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4633
4 | 1634 | 4634 | 0105526005 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bantayan | 16.09 | 120.3897 | R | 3840 | 3.6 | 1067 | 320 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 67.55 | 67.55 | 35.52 | 51.53 | C - Line within 0.5 km; node over 1 km | 2.81 | 0.22 | Line: MANGALDAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4634
4 | 1635 | 4635 | 0401017019 | Region IV-A (CALABARZON) | Batangas | Malvar | San Pioquinto | 14.0543 | 121.1555 | U | 8042 | 3.6 | 2234 | 670 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 62.89 | 62.89 | 40.18 | 51.53 | C - Line within 0.5 km; node over 1 km | 3.25 | 0.01 | Line: UG_TNB001 TO DIVERSION RD | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4635
4 | 1636 | 4636 | 1001322002 | Region X (Northern Mindanao) | Bukidnon | Cabanglasan | Canangaan | 8.066 | 125.3477 | R | 3172 | 3.8 | 835 | 250 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 18.07 | 15.83 | Tier 2B: Moderate GIDA Inclusion | 50.34 | 50.34 | 52.73 | 51.53 | F - Nearest node and line over 5 km | 18.07 | 23.17 | Node: MBB004 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4636
4 | 1637 | 4637 | 1402703008 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Dalligan | 16.835 | 121.0558 | R | 293 | 3.9 | 75 | 22 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.79 | 2.47 | Tier 2B: Moderate GIDA Inclusion | 46.6 | 46.6 | 56.47 | 51.53 | D - Other node or line within 3 km | 3.79 | 2.47 | Line: HINGYON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4637
4 | 1638 | 4638 | 1900713001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Babag | 6.342 | 121.9541 | R | 2870 | 5.1 | 563 | 169 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.57 | 64.56 | Tier 1B: High GIDA Priority | 38.64 | 38.64 | 64.42 | 51.53 | F - Nearest node and line over 5 km | 64.57 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4638
4 | 1639 | 4639 | 0304920012 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Poblacion East | 15.8056 | 121.1447 | R | 4095 | 3.5 | 1170 | 351 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 10.99 | Tier 2B: Moderate GIDA Inclusion | 68.77 | 68.77 | 34.26 | 51.52 | A - Node within 0.5 km | 0.23 | 10.99 | Node: PTN001 - TYPE 2 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4639
4 | 1640 | 4640 | 0306910028 | Region III (Central Luzon) | Tarlac | Paniqui | Samput | 15.6498 | 120.5829 | U | 6522 | 3.9 | 1672 | 502 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.08 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 62.9 | 62.9 | 40.14 | 51.52 | C - Line within 0.5 km; node over 1 km | 2.08 | 0.37 | Line: PANIQUI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4640
4 | 1641 | 4641 | 1705209004 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Banilad | 13.0833 | 121.5475 | R | 1957 | 3.9 | 502 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.9 | 8.85 | Tier 2B: Moderate GIDA Inclusion | 51.23 | 51.23 | 51.8 | 51.52 | E - Nearest node or line 3-5 km | 4.9 | 8.81 | Node: PYM002 - TYPE 4 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4641
4 | 1642 | 4642 | 0803751010 | Region VIII (Eastern Visayas) | Leyte | Villaba | Capinyahan | 11.2179 | 124.4674 | R | 760 | 3.8 | 200 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.16 | 10.74 | Tier 1B: High GIDA Priority | 43.27 | 43.27 | 59.78 | 51.52 | F - Nearest node and line over 5 km | 8.16 | 10.74 | Node: MOL001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4642
4 | 1643 | 4643 | 0501737006 | Region V (Bicol Region) | Camarines Sur | Tinambac | Bani | 13.9644 | 123.3288 | R | 592 | 4.2 | 141 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.37 | 16.31 | Tier 1B: High GIDA Priority | 39.84 | 39.84 | 63.2 | 51.52 | F - Nearest node and line over 5 km | 10.37 | 16.31 | Node: TCC002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4643
4 | 1644 | 4644 | 1903631011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Canibongan | 15.6553 | 122.5607 | R | 1361 | 5.7 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 82.76 | 81.62 | Tier 1B: High GIDA Priority | 34.67 | 34.67 | 68.37 | 51.52 | F - Nearest node and line over 5 km | 82.76 | 999999 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4644
4 | 1645 | 4645 | 1380605001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 297 | 13.5865 | 122.638 | U | 2015 | 4.24 | 475 | 142 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.32 | 9.32 | Tier 1B: High GIDA Priority | 34 | 34 | 69.05 | 51.52 | F - Nearest node and line over 5 km | 9.32 | 9.32 | Line: UG SNQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4645
4 | 1646 | 4646 | 1380610020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 705 | 13.0477 | 123.0831 | U | 2696 | 4.51 | 598 | 179 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 24.04 | 45.74 | Tier 1B: High GIDA Priority | 32 | 32 | 71.04 | 51.52 | F - Nearest node and line over 5 km | 24.04 | 45.7 | Node: OSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4646
4 | 1647 | 4647 | 1906612059 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Siowing | 17.2555 | 122.2295 | R | 1582 | 6 | 264 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.51 | 34.38 | Tier 1B: High GIDA Priority | 31.48 | 31.48 | 71.56 | 51.52 | F - Nearest node and line over 5 km | 29.51 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4647
4 | 1648 | 4648 | 1400125003 | Cordillera Administrative Region (CAR) | Abra | Tineg | Anayan | 17.8941 | 120.9613 | R | 231 | 3.8 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.12 | 27.17 | Tier 1B: High GIDA Priority | 30.06 | 30.06 | 72.98 | 51.52 | F - Nearest node and line over 5 km | 27.12 | 28.89 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4648
4 | 1649 | 4649 | 0305420010 | Region III (Central Luzon) | Pampanga | Santa Rita | Santa Monica | 14.9922 | 120.609 | R | 3250 | 4 | 812 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.06 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 68.69 | 68.69 | 34.32 | 51.51 | D - Other node or line within 3 km | 3.06 | 0.83 | Line: 24 CORE (2X12) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4649
4 | 1650 | 4650 | 0600412005 | Region VI (Western Visayas) | Aklan | Malay | Caticlan | 11.9238 | 121.9519 | U | 8476 | 3.9 | 2173 | 652 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.81 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 66.01 | 66.01 | 37.02 | 51.51 | D - Other node or line within 3 km | 2.81 | 999999 | Node: MYK001 - TYPE 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4650
4 | 1651 | 4651 | 0500518007 | Region V (Bicol Region) | Albay | Tiwi | Cale | 13.4639 | 123.6536 | U | 6012 | 4.1 | 1466 | 440 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.57 | 0.75 | Tier 2B: Moderate GIDA Inclusion | 64.52 | 64.52 | 38.49 | 51.51 | D - Other node or line within 3 km | 2.57 | 0.73 | Line: EE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4651
4 | 1652 | 4652 | 0403422001 | Region IV-A (CALABARZON) | Laguna | Pila | Aplaya | 14.2594 | 121.3546 | R | 3621 | 3.3 | 1097 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.76 | 2.28 | Tier 2B: Moderate GIDA Inclusion | 63.98 | 63.98 | 39.03 | 51.51 | D - Other node or line within 3 km | 2.76 | 2.26 | Line: UG SCL001 TO PLL001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4652
4 | 1653 | 4653 | 0301419020 | Region III (Central Luzon) | Bulacan | San Ildefonso | Malipampang | 15.0562 | 120.939 | U | 6904 | 3.5 | 1973 | 592 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 63.9 | 63.9 | 39.11 | 51.51 | C - Line within 0.5 km; node over 1 km | 2.02 | 0.1 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4653
4 | 1654 | 4654 | 1206503021 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Esperanza | Pamantingan | 6.7196 | 124.469 | R | 4413 | 3.8 | 1161 | 348 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.84 | 22.8 | Tier 2B: Moderate GIDA Inclusion | 53.7 | 53.7 | 49.31 | 51.51 | F - Nearest node and line over 5 km | 22.84 | 22.8 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4654
4 | 1655 | 4655 | 1108602022 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Marabutuan | 5.9138 | 125.5717 | R | 4626 | 3.6 | 1285 | 386 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 38.82 | 47.6 | Tier 2B: Moderate GIDA Inclusion | 52.66 | 52.66 | 50.37 | 51.51 | F - Nearest node and line over 5 km | 38.82 | 47.57 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4655
4 | 1656 | 4656 | 1606818010 | Region XIII (Caraga) | Surigao del Sur | Tago | Cayale | 8.9833 | 126.1211 | R | 1933 | 4.1 | 471 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.36 | 5.42 | Tier 1B: High GIDA Priority | 43.86 | 43.86 | 59.16 | 51.51 | F - Nearest node and line over 5 km | 13.36 | 5.42 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4656
4 | 1657 | 4657 | 1001805006 | Region X (Northern Mindanao) | Camiguin | Sagay | Cuna | 9.1253 | 124.7446 | R | 896 | 3.9 | 230 | 69 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.64 | 15.79 | Tier 1B: High GIDA Priority | 40.76 | 40.76 | 62.26 | 51.51 | F - Nearest node and line over 5 km | 16.64 | 15.79 | Line: CDO - BUENAVISTA via GINGOOG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4657
4 | 1658 | 4658 | 0701243017 | Region VII (Central Visayas) | Bohol | Talibon | Nocnocan | 10.2459 | 124.4049 | R | 1809 | 4 | 452 | 136 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.49 | 40.06 | Tier 1B: High GIDA Priority | 38.96 | 38.96 | 64.05 | 51.51 | F - Nearest node and line over 5 km | 44.49 | 40.06 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4658
4 | 1659 | 4659 | 1908823010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Papakan | 17.255 | 122.2291 | R | 1662 | 4.7 | 354 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.32 | Tier 1B: High GIDA Priority | 33.84 | 33.84 | 69.18 | 51.51 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4659
4 | 1660 | 4660 | 0401003038 | Region IV-A (CALABARZON) | Batangas | Balayan | Navotas | 13.9309 | 120.7208 | R | 4235 | 3.6 | 1176 | 353 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.6 | 1.03 | Tier 2B: Moderate GIDA Inclusion | 69.43 | 69.43 | 33.57 | 51.5 | D - Other node or line within 3 km | 1.6 | 1.03 | Line: UG NSB001 TO BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4660
4 | 1661 | 4661 | 0403426020 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Juan | 14.2439 | 121.4069 | R | 4354 | 3.3 | 1319 | 396 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.97 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 66.84 | 66.84 | 36.17 | 51.5 | D - Other node or line within 3 km | 3.97 | 1.9 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4661
4 | 1662 | 4662 | 0304913022 | Region III (Central Luzon) | Nueva Ecija | Laur | Siclong | 15.58 | 121.223 | R | 3705 | 3.5 | 1059 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.38 | 8.94 | Tier 2B: Moderate GIDA Inclusion | 64.6 | 64.6 | 38.4 | 51.5 | D - Other node or line within 3 km | 2.38 | 8.77 | Node: LRN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4662
4 | 1663 | 4663 | 0600411014 | Region VI (Western Visayas) | Aklan | Makato | Mantiguib | 11.7061 | 122.3096 | R | 2051 | 3.9 | 526 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2 | 0.41 | Tier 2B: Moderate GIDA Inclusion | 63.7 | 63.7 | 39.3 | 51.5 | D - Other node or line within 3 km | 2 | 5.49 | Node: NUK001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4663
4 | 1664 | 4664 | 0305413030 | Region III (Central Luzon) | Pampanga | Mexico | San Jose Matulid | 15.049 | 120.7162 | U | 7242 | 4 | 1810 | 543 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.89 | 0.64 | Tier 2B: Moderate GIDA Inclusion | 62.22 | 62.22 | 40.79 | 51.5 | D - Other node or line within 3 km | 2.89 | 0.64 | Line: EXISTING | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4664
4 | 1665 | 4665 | 1404407011 | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | Napua | 16.9288 | 120.905 | R | 661 | 3.7 | 179 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.4 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 52.95 | 52.95 | 50.05 | 51.5 | C - Line within 0.5 km; node over 1 km | 2.4 | 0.41 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4665
4 | 1666 | 4666 | 0401034004 | Region IV-A (CALABARZON) | Batangas | Tuy | Dalima | 14.0282 | 120.697 | R | 1217 | 3.6 | 338 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.47 | 1.44 | Tier 2B: Moderate GIDA Inclusion | 50.72 | 50.72 | 52.27 | 51.5 | D - Other node or line within 3 km | 3.47 | 1.33 | Line: TGY001 TO BYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4666
4 | 1667 | 4667 | 0405622077 | Region IV-A (CALABARZON) | Quezon | Lopez | Santa Rosa | 13.8178 | 122.3296 | R | 304 | 3.8 | 80 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.61 | 2.52 | Tier 1B: High GIDA Priority | 35.66 | 35.66 | 67.34 | 51.5 | D - Other node or line within 3 km | 10.61 | 2.51 | Line: LZQ001 TO MCQ001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4667
4 | 1668 | 4668 | 1380614006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 749 | 12.5915 | 121.5031 | U | 673 | 4.01 | 168 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.46 | 0.33 | Tier 1B: High GIDA Priority | 32.43 | 32.43 | 70.57 | 51.5 | C - Line within 0.5 km; node over 1 km | 5.46 | 0.33 | Line: ROXAS - SAN JOSE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4668
4 | 1669 | 4669 | 0907303001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Baking | 7.8757 | 123.1595 | R | 372 | 3.9 | 95 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.89 | 8.8 | Tier 1B: High GIDA Priority | 31.47 | 31.47 | 71.53 | 51.5 | F - Nearest node and line over 5 km | 19.89 | 8.76 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4669
4 | 1670 | 4670 | 0301420034 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc West | 14.7995 | 121.0611 | U | 9287 | 3.5 | 2653 | 796 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1 | 0.83 | Tier 2B: Moderate GIDA Inclusion | 67.71 | 67.71 | 35.27 | 51.49 | B - Node 0.5-1 km | 1 | 0.81 | Line: 48 CORE | Survey short node lateral; confirm port/fiber capacity, access and route. | 4670
4 | 1671 | 4671 | 0203122005 | Region II (Cagayan Valley) | Isabela | Quezon | Barucboc Norte | 17.256 | 121.6063 | R | 3224 | 3.8 | 848 | 254 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.91 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 67.28 | 67.28 | 35.69 | 51.49 | D - Other node or line within 3 km | 5.91 | 0.56 | Line: QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4671
4 | 1672 | 4672 | 0304930046 | Region III (Central Luzon) | Nueva Ecija | Talavera | Poblacion Sur | 15.5763 | 120.9178 | U | 3979 | 3.5 | 1137 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 63.77 | 63.77 | 39.22 | 51.49 | B - Node 0.5-1 km | 0.66 | 0.29 | Line: TALAVERA CABLE SYSTEMS | Survey short node lateral; confirm port/fiber capacity, access and route. | 4672
4 | 1673 | 4673 | 0304913017 | Region III (Central Luzon) | Nueva Ecija | Laur | San Fernando | 15.5928 | 121.218 | R | 3469 | 3.5 | 991 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.18 | 7.94 | Tier 2B: Moderate GIDA Inclusion | 63.37 | 63.37 | 39.62 | 51.49 | E - Nearest node or line 3-5 km | 3.18 | 7.86 | Node: LRN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4673
4 | 1674 | 4674 | 0301414006 | Region III (Central Luzon) | Bulacan | Obando | Paco | 14.7297 | 120.9231 | U | 7398 | 3.5 | 2114 | 634 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.68 | 3.9 | Tier 2B: Moderate GIDA Inclusion | 59.9 | 59.9 | 43.09 | 51.49 | D - Other node or line within 3 km | 2.68 | 3.87 | Node: OBB001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4674
4 | 1675 | 4675 | 1001312022 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Kulaman | 7.9215 | 124.9603 | R | 1444 | 3.8 | 380 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.61 | 2.83 | Tier 2B: Moderate GIDA Inclusion | 48.02 | 48.02 | 54.96 | 51.49 | D - Other node or line within 3 km | 5.61 | 2.8 | Line: DAMULOG - VALENCIA - QUEZON | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4675
4 | 1676 | 4676 | 0305422004 | Region III (Central Luzon) | Pampanga | Sasmuan | Mabuanbuan | 14.8294 | 120.6009 | R | 955 | 4 | 239 | 72 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.58 | 7.59 | Tier 2B: Moderate GIDA Inclusion | 46.82 | 46.82 | 56.15 | 51.49 | F - Nearest node and line over 5 km | 7.58 | 7.56 | Line: 96CORE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4676
4 | 1677 | 4677 | 1001319002 | Region X (Northern Mindanao) | Bukidnon | Sumilao | Culasi | 8.2742 | 124.9212 | R | 690 | 3.8 | 182 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.19 | 7.59 | Tier 1B: High GIDA Priority | 45.01 | 45.01 | 57.97 | 51.49 | F - Nearest node and line over 5 km | 9.19 | 7.58 | Line: CAGAYAN DE ORO - MALAYBALAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4677
4 | 1678 | 4678 | 1903623037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pualas | Yaran | 17.2548 | 122.2289 | R | 977 | 5.7 | 171 | 51 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.42 | 34.3 | Tier 1B: High GIDA Priority | 33.55 | 33.55 | 69.44 | 51.49 | F - Nearest node and line over 5 km | 29.42 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4678
4 | 1679 | 4679 | 1003515021 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Pantar | 7.8088 | 123.9257 | R | 882 | 4.2 | 210 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.54 | 19.87 | Tier 1B: High GIDA Priority | 32.97 | 32.97 | 70.01 | 51.49 | F - Nearest node and line over 5 km | 29.54 | 19.85 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4679
4 | 1680 | 4680 | 1380606185 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 579 | 13.1775 | 122.7427 | U | 1468 | 4.41 | 333 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.12 | 47.74 | Tier 1B: High GIDA Priority | 32.64 | 32.64 | 70.35 | 51.49 | F - Nearest node and line over 5 km | 7.12 | 999999 | Node: SDQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4680
4 | 1681 | 4681 | 0203111016 | Region II (Cagayan Valley) | Isabela | Divilacan | Sapinit | 17.2999 | 122.2357 | R | 299 | 3.8 | 79 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.35 | 36.72 | Tier 1B: High GIDA Priority | 28.93 | 28.93 | 74.06 | 51.49 | F - Nearest node and line over 5 km | 33.35 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4681
4 | 1682 | 4682 | 0401020017 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Cawongan | 13.871 | 121.2265 | R | 4376 | 3.6 | 1216 | 365 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 1.48 | Tier 2B: Moderate GIDA Inclusion | 69.26 | 69.26 | 33.71 | 51.48 | D - Other node or line within 3 km | 1.78 | 1.35 | Line: AERIAL | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4682
4 | 1683 | 4683 | 1401111009 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Palasaan | 16.8357 | 120.7966 | R | 3052 | 3.5 | 872 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.98 | 0.92 | Tier 2B: Moderate GIDA Inclusion | 67.23 | 67.23 | 35.73 | 51.48 | D - Other node or line within 3 km | 1.98 | 0.76 | Line: PROPOSED 96C FOC - BUGIAS TO CERVANTES | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4683
4 | 1684 | 4684 | 0305411012 | Region III (Central Luzon) | Pampanga | Magalang | San Miguel | 15.2253 | 120.658 | R | 2960 | 4 | 740 | 222 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 0.39 | Tier 2B: Moderate GIDA Inclusion | 63.17 | 63.17 | 39.78 | 51.48 | C - Line within 0.5 km; node over 1 km | 2.32 | 0.39 | Line: Path Measure | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4684
4 | 1685 | 4685 | 0405603039 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tagbakin | 13.9964 | 121.912 | U | 5639 | 3.8 | 1484 | 445 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 63.01 | 63.01 | 39.94 | 51.48 | C - Line within 0.5 km; node over 1 km | 1.52 | 0.07 | Line: UG LCQ001 TO ATQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4685
4 | 1686 | 4686 | 0304927009 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Nieves | 15.3301 | 120.9489 | U | 6281 | 3.5 | 1795 | 538 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.49 | 1.19 | Tier 2B: Moderate GIDA Inclusion | 62.68 | 62.68 | 40.29 | 51.48 | D - Other node or line within 3 km | 4.15 | 1.19 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4686
4 | 1687 | 4687 | 0401022008 | Region IV-A (CALABARZON) | Batangas | San Jose | Banaybanay II | 13.9212 | 121.106 | U | 4648 | 3.6 | 1291 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.28 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 61.23 | 61.23 | 41.74 | 51.48 | C - Line within 0.5 km; node over 1 km | 2.28 | 0.06 | Line: UG BUN001 TO SSB001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4687
4 | 1688 | 4688 | 0103320002 | Region I (Ilocos Region) | La Union | Tubao | Anduyan | 16.3455 | 120.4428 | R | 2138 | 3.7 | 578 | 173 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.15 | 0.98 | Tier 2B: Moderate GIDA Inclusion | 61.19 | 61.19 | 41.77 | 51.48 | D - Other node or line within 3 km | 4.15 | 0.96 | Line: TUBAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4688
4 | 1689 | 4689 | 1705311014 | MIMAROPA Region | Palawan | Dumaran | Santo Tomas | 10.5038 | 119.8196 | R | 1242 | 3.9 | 318 | 95 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.49 | 41.94 | Tier 1B: High GIDA Priority | 34.94 | 34.94 | 68.03 | 51.48 | F - Nearest node and line over 5 km | 33.49 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4689
4 | 1690 | 4690 | 1380606113 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 507 | 13.193 | 122.6569 | U | 1526 | 4.23 | 361 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.87 | 42.91 | Tier 1B: High GIDA Priority | 34.37 | 34.37 | 68.59 | 51.48 | E - Nearest node or line 3-5 km | 4.87 | 999999 | Node: SDQ002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4690
4 | 1691 | 4691 | 1380601246 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 245 | 12.8542 | 121.4752 | U | 318 | 3.93 | 81 | 24 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.72 | 1.74 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 34.05 | 34.05 | 68.9 | 51.48 | D - Other node or line within 3 km | 2.72 | 1.74 | Line: AE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4691
4 | 1692 | 4692 | 0201515010 | Region II (Cagayan Valley) | Cagayan | Iguig | Santa Teresa | 17.704 | 121.7477 | R | 3476 | 3.9 | 891 | 267 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.32 | 0.05 | Tier 2B: Moderate GIDA Inclusion | 68.77 | 68.77 | 34.17 | 51.47 | C - Line within 0.5 km; node over 1 km | 5.32 | 0.05 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4692
4 | 1693 | 4693 | 0307105012 | Region III (Central Luzon) | Zambales | Iba | Palanginan | 15.3171 | 119.9916 | U | 11507 | 3.8 | 3028 | 908 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.85 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 67.38 | 67.38 | 35.57 | 51.47 | C - Line within 0.5 km; node over 1 km | 1.85 | 0.28 | Line: IBA MUNICIPALITY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4693
4 | 1694 | 4694 | 1102303019 | Region XI (Davao Region) | Davao del Norte | Carmen | Santo Niño | 7.3358 | 125.6952 | U | 6314 | 3.7 | 1706 | 512 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.99 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 64.81 | 64.81 | 38.13 | 51.47 | C - Line within 0.5 km; node over 1 km | 1.99 | 0.06 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4694
4 | 1695 | 4695 | 0102906040 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Nicolas | 17.2115 | 120.4474 | U | 2741 | 3.8 | 721 | 216 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.19 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 55.32 | 55.32 | 47.61 | 51.47 | D - Other node or line within 3 km | 2.19 | 0.69 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4695
4 | 1696 | 4696 | 1380612031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 863 | 12.0052 | 121.9729 | U | 1492 | 4.12 | 362 | 109 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.97 | 5.74 | Tier 1B: High GIDA Priority | 33.46 | 33.46 | 69.48 | 51.47 | F - Nearest node and line over 5 km | 6.97 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4696
4 | 1697 | 4697 | 0306914003 | Region III (Central Luzon) | Tarlac | San Manuel | Legaspi | 15.8193 | 120.6067 | R | 2982 | 3.9 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.54 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 68.1 | 68.1 | 34.83 | 51.46 | C - Line within 0.5 km; node over 1 km | 2.54 | 0.07 | Line: P-4 pipe installed | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4697
4 | 1698 | 4698 | 0401019002 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Balaytigui | 14.1315 | 120.5976 | R | 4708 | 3.6 | 1308 | 392 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.15 | 6.51 | Tier 2B: Moderate GIDA Inclusion | 67.11 | 67.11 | 35.8 | 51.46 | D - Other node or line within 3 km | 1.15 | 6.51 | Node: NSB004 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4698
4 | 1699 | 4699 | 1401105001 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Abatan | 16.8037 | 120.8233 | U | 3644 | 3.5 | 1041 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.23 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 64.91 | 64.91 | 38.01 | 51.46 | A - Node within 0.5 km | 0.23 | 0.18 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4699
4 | 1700 | 4700 | 0304907014 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | South Poblacion | 15.4503 | 121.3364 | R | 5109 | 3.5 | 1460 | 438 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.74 | 23.62 | Tier 2B: Moderate GIDA Inclusion | 64.19 | 64.19 | 38.72 | 51.46 | E - Nearest node or line 3-5 km | 3.74 | 23.59 | Node: GBN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4700
4 | 1701 | 4701 | 0305408013 | Region III (Central Luzon) | Pampanga | Lubao | San Agustin | 14.925 | 120.5769 | R | 2967 | 4 | 742 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.94 | 0.5 | Tier 2B: Moderate GIDA Inclusion | 62.45 | 62.45 | 40.47 | 51.46 | C - Line within 0.5 km; node over 1 km | 2.94 | 0.49 | Line: LUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4701
4 | 1702 | 4702 | 0402108016 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Navarro | 14.3866 | 120.9036 | U | 50641 | 3.4 | 14894 | 4468 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.86 | 3.39 | Tier 2B: Moderate GIDA Inclusion | 55.65 | 55.65 | 47.27 | 51.46 | B - Node 0.5-1 km | 0.86 | 3.39 | Node: TRC006 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4702
4 | 1703 | 4703 | 0502010014 | Region V (Bicol Region) | Catanduanes | Viga | Pedro Vera | 13.8108 | 124.2637 | R | 1577 | 4.2 | 375 | 112 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 43.41 | 73.97 | Tier 1B: High GIDA Priority | 41.69 | 41.69 | 61.24 | 51.46 | F - Nearest node and line over 5 km | 43.41 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4703
4 | 1704 | 4704 | 0305406009 | Region III (Central Luzon) | Pampanga | Floridablanca | Consuelo | 14.97 | 120.4974 | R | 3829 | 4 | 957 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.36 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 67.82 | 67.82 | 35.08 | 51.45 | C - Line within 0.5 km; node over 1 km | 2.36 | 0.1 | Line: 48 CORE (4X12) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4704
4 | 1705 | 4705 | 0405627020 | Region IV-A (CALABARZON) | Quezon | Mauban | Bagong Bayan | 14.1889 | 121.7535 | U | 7834 | 3.8 | 2062 | 619 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 20.28 | Tier 2B: Moderate GIDA Inclusion | 58.21 | 58.21 | 44.69 | 51.45 | E - Nearest node or line 3-5 km | 3.88 | 20.2 | Node: MBQ001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4705
4 | 1706 | 4706 | 0301420047 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin III | 14.8598 | 121.0546 | U | 3862 | 3.5 | 1103 | 331 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.73 | 3.52 | Tier 2B: Moderate GIDA Inclusion | 56.76 | 56.76 | 46.13 | 51.45 | D - Other node or line within 3 km | 2.73 | 5.76 | Node: SJD005 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4706
4 | 1707 | 4707 | 0403412014 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Jose | 14.1845 | 121.5116 | R | 1024 | 3.3 | 310 | 93 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.66 | 4.18 | Tier 2B: Moderate GIDA Inclusion | 55.26 | 55.26 | 47.65 | 51.45 | B - Node 0.5-1 km | 0.66 | 4.16 | Node: LSL001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4707
4 | 1708 | 4708 | 1404404004 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Bayyo | 17.0069 | 121.0165 | R | 329 | 3.7 | 89 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.69 | 0.4 | Tier 1B: High GIDA Priority | 40.96 | 40.96 | 61.95 | 51.45 | F - Nearest node and line over 5 km | 9.69 | 8.17 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4708
4 | 1709 | 4709 | 1600208001 | Region XIII (Caraga) | Agusan del Norte | Magallanes | Buhang | 9.0354 | 125.525 | R | 4178 | 4.1 | 1019 | 306 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 7.06 | Tier 2A: High Commercial ROI | 74.65 | 74.65 | 28.24 | 51.44 | A - Node within 0.5 km | 0.25 | 7.06 | Node: MSA001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4709
4 | 1710 | 4710 | 0102908004 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Concepcion | 16.9834 | 120.7197 | R | 2080 | 3.8 | 547 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.81 | 1.71 | Tier 2B: Moderate GIDA Inclusion | 65 | 65 | 37.89 | 51.44 | B - Node 0.5-1 km | 0.81 | 1.55 | Node: CVI001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4710
4 | 1711 | 4711 | 1102404007 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Guihing | 6.6933 | 125.3758 | U | 11853 | 3.4 | 3486 | 1046 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 5.14 | 2.83 | Tier 2B: Moderate GIDA Inclusion | 62.86 | 62.86 | 40.02 | 51.44 | D - Other node or line within 3 km | 5.14 | 2.84 | Line: DAVAO CITY - GENSAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4711
4 | 1712 | 4712 | 0301420004 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Kaypian | 14.8221 | 121.0519 | U | 48130 | 3.5 | 13751 | 4125 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 2.28 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 58.73 | 58.73 | 44.15 | 51.44 | D - Other node or line within 3 km | 2.28 | 2.82 | Node: SJD003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4712
4 | 1713 | 4713 | 0604531014 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XI | 10.7945 | 123.1814 | R | 2496 | 3.7 | 675 | 202 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.78 | 15.93 | Tier 2B: Moderate GIDA Inclusion | 47.23 | 47.23 | 55.65 | 51.44 | F - Nearest node and line over 5 km | 16.78 | 15.89 | Line: TALISAY - VICTORIAS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4713
4 | 1714 | 4714 | 1705313011 | MIMAROPA Region | Palawan | Linapacan | San Nicolas | 11.3848 | 119.8125 | R | 1267 | 3.9 | 325 | 98 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.28 | 70.81 | Tier 1B: High GIDA Priority | 39.98 | 39.98 | 62.9 | 51.44 | F - Nearest node and line over 5 km | 29.28 | 999999 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4714
4 | 1715 | 4715 | 0803721005 | Region VIII (Eastern Visayas) | Leyte | Inopacan | Caulisihan | 10.5408 | 124.8814 | R | 352 | 3.8 | 93 | 28 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 17.71 | 8.19 | Tier 1B: High GIDA Priority | 39.75 | 39.75 | 63.13 | 51.44 | F - Nearest node and line over 5 km | 17.71 | 12.43 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4715
4 | 1716 | 4716 | 0802623002 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Beto | 11.9487 | 125.3832 | R | 299 | 3.9 | 77 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 89.09 | 91.43 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 66.2 | 51.44 | F - Nearest node and line over 5 km | 89.09 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4716
4 | 1717 | 4717 | 1380601049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 49 | 12.1452 | 122.672 | U | 2184 | 3.31 | 660 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 59.82 | 34.8 | Tier 1B: High GIDA Priority | 33.65 | 33.65 | 69.23 | 51.44 | F - Nearest node and line over 5 km | 59.82 | 999999 | Node: KOK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4717
4 | 1718 | 4718 | 0701245023 | Region VII (Central Visayas) | Bohol | Tubigon | Pangapasan | 9.998 | 123.9411 | R | 574 | 4 | 144 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.56 | 5.76 | Tier 1B: High GIDA Priority | 33.2 | 33.2 | 69.68 | 51.44 | F - Nearest node and line over 5 km | 26.56 | 5.71 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4718
4 | 1719 | 4719 | 0301403021 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Niño | 14.986 | 120.8917 | R | 4520 | 3.5 | 1291 | 387 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.66 | 0.15 | Tier 2B: Moderate GIDA Inclusion | 68.43 | 68.43 | 34.43 | 51.43 | C - Line within 0.5 km; node over 1 km | 2.66 | 0.15 | Line: SanLuis-Candaba Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4719
4 | 1720 | 4720 | 0300807004 | Region III (Central Luzon) | Bataan | Mariveles | Cabcaben | 14.4546 | 120.5889 | U | 8007 | 3.6 | 2224 | 667 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.82 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 64.98 | 64.98 | 37.89 | 51.43 | C - Line within 0.5 km; node over 1 km | 1.82 | 0.24 | Line: PIPE ORION-MARIVELES | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4720
4 | 1721 | 4721 | 1206312014 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Poblacion | 6.2184 | 125.0694 | U | 53313 | 3.6 | 14809 | 4443 | Band n50 (1.5 GHz, 100 MHz TDD) | 5 | 1 | 0.52 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 64.51 | 64.51 | 38.34 | 51.43 | B - Node 0.5-1 km | 0.52 | 0.85 | Node: PMK001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4721
4 | 1722 | 4722 | 0103307016 | Region I (Ilocos Region) | La Union | Bauang | Dili | 16.5281 | 120.334 | R | 2249 | 3.7 | 608 | 182 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 62.1 | 62.1 | 40.76 | 51.43 | B - Node 0.5-1 km | 0.82 | 0.18 | Line: 66 meters | Survey short node lateral; confirm port/fiber capacity, access and route. | 4722
4 | 1723 | 4723 | 0306916025 | Region III (Central Luzon) | Tarlac | City of Tarlac | Capehan | 15.433 | 120.6013 | R | 2335 | 3.9 | 599 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.51 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 60.66 | 60.66 | 42.2 | 51.43 | C - Line within 0.5 km; node over 1 km | 1.51 | 0.27 | Line: 6 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4723
4 | 1724 | 4724 | 1705319003 | MIMAROPA Region | Palawan | San Vicente | Caruray | 10.4253 | 119.0231 | R | 5388 | 3.9 | 1382 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.54 | 27.14 | Tier 2B: Moderate GIDA Inclusion | 52.85 | 52.85 | 50.01 | 51.43 | F - Nearest node and line over 5 km | 30.54 | 27.12 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4724
4 | 1725 | 4725 | 1705314008 | MIMAROPA Region | Palawan | Magsaysay | Lacaren | 10.8385 | 121.0482 | R | 475 | 3.9 | 122 | 37 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 97.56 | 97.54 | Tier 1B: High GIDA Priority | 34.6 | 34.6 | 68.26 | 51.43 | F - Nearest node and line over 5 km | 97.56 | 999999 | Node: SBV001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4725
4 | 1726 | 4726 | 0307105017 | Region III (Central Luzon) | Zambales | Iba | Santa Barbara | 15.3319 | 119.9991 | R | 4746 | 3.8 | 1249 | 375 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 1.81 | Tier 2B: Moderate GIDA Inclusion | 68.72 | 68.72 | 34.12 | 51.42 | D - Other node or line within 3 km | 2.35 | 1.78 | Line: IBA MUNICIPALITY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4726
4 | 1727 | 4727 | 0702223016 | Region VII (Central Visayas) | Cebu | Danao City | Guinsay | 10.5476 | 124.0235 | U | 10629 | 3.8 | 2797 | 839 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.88 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 67.49 | 67.49 | 35.34 | 51.42 | C - Line within 0.5 km; node over 1 km | 2.88 | 0.02 | Line: UPLINK 2 CRM001- DOC001 via AE BACKBONE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4727
4 | 1728 | 4728 | 1004311007 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Lower Jasaan | 8.6575 | 124.754 | U | 6140 | 3.9 | 1574 | 472 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 0.65 | Tier 2B: Moderate GIDA Inclusion | 66.4 | 66.4 | 36.43 | 51.42 | B - Node 0.5-1 km | 0.86 | 0.58 | Line: CDO - BUENAVISTA via GINGOOG | Survey short node lateral; confirm port/fiber capacity, access and route. | 4728
4 | 1729 | 4729 | 0105546018 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Dilan Paurido | 15.9747 | 120.5817 | U | 7450 | 3.6 | 2069 | 621 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.82 | 1.16 | Tier 2B: Moderate GIDA Inclusion | 64.51 | 64.51 | 38.33 | 51.42 | D - Other node or line within 3 km | 1.82 | 1.15 | Line: URDANETA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4729
4 | 1730 | 4730 | 0103313013 | Region I (Ilocos Region) | La Union | Rosario | Cataguingtingan | 16.2237 | 120.4501 | R | 2859 | 3.7 | 773 | 232 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.51 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 62.61 | 62.61 | 40.24 | 51.42 | C - Line within 0.5 km; node over 1 km | 3.51 | 0.08 | Line: RSU001 TO AGU001 SECONDARY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4730
4 | 1731 | 4731 | 0702211001 | Region VII (Central Visayas) | Cebu | City of Bogo | Cogon | 11.0435 | 124.0037 | U | 2857 | 3.8 | 752 | 226 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.58 | 0.32 | Tier 2B: Moderate GIDA Inclusion | 59.32 | 59.32 | 43.51 | 51.42 | B - Node 0.5-1 km | 0.58 | 0.22 | Line: BOGO - DANAO | Survey short node lateral; confirm port/fiber capacity, access and route. | 4731
4 | 1732 | 4732 | 0304928031 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Mabini | 15.4466 | 120.9472 | R | 1983 | 3.5 | 567 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.2 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 58.68 | 58.68 | 44.17 | 51.42 | C - Line within 0.5 km; node over 1 km | 2.96 | 0.28 | Line: MULTINET - SANTA ROSA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4732
4 | 1733 | 4733 | 1400118001 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Alinaya | 17.5491 | 120.5655 | R | 999 | 3.8 | 263 | 79 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.87 | 0.85 | Tier 2B: Moderate GIDA Inclusion | 57.68 | 57.68 | 45.16 | 51.42 | B - Node 0.5-1 km | 0.87 | 0.73 | Line: CABLE LAYED | Survey short node lateral; confirm port/fiber capacity, access and route. | 4733
4 | 1734 | 4734 | 0401033008 | Region IV-A (CALABARZON) | Batangas | Tingloy | Barangay 13 | 13.6457 | 120.8925 | R | 1281 | 3.6 | 356 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.83 | 15.6 | Tier 2B: Moderate GIDA Inclusion | 51.06 | 51.06 | 51.78 | 51.42 | E - Nearest node or line 3-5 km | 4.83 | 15.59 | Node: MBN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4734
4 | 1735 | 4735 | 0501703012 | Region V (Bicol Region) | Camarines Sur | Bato | Lubigan | 13.3552 | 123.3262 | R | 210 | 4.2 | 50 | 15 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.26 | 4.22 | Tier 1B: High GIDA Priority | 44.74 | 44.74 | 58.09 | 51.42 | E - Nearest node or line 3-5 km | 4.26 | 4.19 | Line: IRIGA - LEGAZPI | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4735
4 | 1736 | 4736 | 1381100105 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 105 | 14.4129 | 120.9863 | U | 574 | 3.05 | 188 | 56 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.17 | 3.31 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 32.71 | 32.71 | 70.13 | 51.42 | D - Other node or line within 3 km | 2.17 | 3.28 | Node: BRC002-TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4736
4 | 1737 | 4737 | 1380610040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 725 | 12.0395 | 121.5829 | U | 1990 | 3.31 | 602 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 40.75 | 28.47 | Tier 1B: High GIDA Priority | 32.17 | 32.17 | 70.66 | 51.42 | F - Nearest node and line over 5 km | 40.75 | 39.35 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4737
4 | 1738 | 4738 | 0603026012 | Region VI (Western Visayas) | Iloilo | Leganes | Guihaman | 10.7768 | 122.5843 | R | 2324 | 3.8 | 612 | 184 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.13 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 67.1 | 67.1 | 35.72 | 51.41 | C - Line within 0.5 km; node over 1 km | 1.13 | 0.07 | Line: 1241 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4738
4 | 1739 | 4739 | 0701205016 | Region VII (Central Visayas) | Bohol | Baclayon | Taguihon | 9.6264 | 123.9116 | R | 2119 | 4 | 530 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.37 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 66.76 | 66.76 | 36.06 | 51.41 | A - Node within 0.5 km | 0.37 | 0.21 | Line: 11,428 mtrs. | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4739
4 | 1740 | 4740 | 0403413003 | Region IV-A (CALABARZON) | Laguna | Lumban | Balubad | 14.2885 | 121.463 | R | 2336 | 3.3 | 708 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.82 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 64.77 | 64.77 | 38.05 | 51.41 | B - Node 0.5-1 km | 0.82 | 0.46 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4740
4 | 1741 | 4741 | 1401105006 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Bangao | 16.8184 | 120.8334 | U | 5463 | 3.5 | 1561 | 468 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.11 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 63 | 63 | 39.82 | 51.41 | C - Line within 0.5 km; node over 1 km | 2.11 | 0.11 | Line: LA TRINIDAD-SAGADA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4741
4 | 1742 | 4742 | 0601916016 | Region VI (Western Visayas) | Capiz | Sigma | Pagbunitan | 11.4332 | 122.6691 | R | 1308 | 3.8 | 344 | 103 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.3 | 0.79 | Tier 2B: Moderate GIDA Inclusion | 60.75 | 60.75 | 42.07 | 51.41 | D - Other node or line within 3 km | 1.3 | 0.69 | Line: ROXAS - ILOILO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4742
4 | 1743 | 4743 | 1705303014 | MIMAROPA Region | Palawan | Araceli | Tudela | 10.6417 | 120.2489 | R | 2753 | 3.9 | 706 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 74.32 | 82.04 | Tier 2B: Moderate GIDA Inclusion | 48.76 | 48.76 | 54.06 | 51.41 | F - Nearest node and line over 5 km | 74.32 | 999999 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4743
4 | 1744 | 4744 | 1408104021 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Tuyangan | 18.1065 | 121.1164 | R | 227 | 4.2 | 54 | 16 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 11.85 | 20.92 | Tier 1B: High GIDA Priority | 35.48 | 35.48 | 67.33 | 51.41 | F - Nearest node and line over 5 km | 11.85 | 41.1 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4744
4 | 1745 | 4745 | 1380605025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 323 | 13.3019 | 121.2578 | U | 1076 | 3.93 | 274 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.23 | 2.95 | Tier 1B: High GIDA Priority | 32.6 | 32.6 | 70.22 | 51.41 | D - Other node or line within 3 km | 4.23 | 2.94 | Line: MINDORO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4745
4 | 1746 | 4746 | 0600416016 | Region VI (Western Visayas) | Aklan | Numancia | Poblacion | 11.7047 | 122.3274 | R | 1829 | 3.9 | 469 | 141 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.35 | Tier 2B: Moderate GIDA Inclusion | 65.87 | 65.87 | 36.93 | 51.4 | A - Node within 0.5 km | 0.16 | 3.68 | Node: NUK001 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4746
4 | 1747 | 4747 | 1004326003 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Dayawan | 8.5708 | 124.7848 | U | 9334 | 3.9 | 2393 | 718 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.02 | 1.53 | Tier 2B: Moderate GIDA Inclusion | 65.28 | 65.28 | 37.52 | 51.4 | D - Other node or line within 3 km | 3.02 | 1.52 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4747
4 | 1748 | 4748 | 0603034028 | Region VI (Western Visayas) | Iloilo | Oton | San Antonio | 10.693 | 122.4915 | R | 2471 | 3.8 | 650 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.23 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 63.25 | 63.25 | 39.54 | 51.4 | C - Line within 0.5 km; node over 1 km | 1.23 | 0.08 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4748
4 | 1749 | 4749 | 1906618013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | South Manubul | 16.2387 | 122.1117 | R | 2491 | 6 | 415 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.68 | 3.34 | Tier 2B: Moderate GIDA Inclusion | 51.42 | 51.42 | 51.39 | 51.4 | E - Nearest node or line 3-5 km | 4.68 | 999999 | Node: CSA001 - TYPE 4A | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4749
4 | 1750 | 4750 | 0501711001 | Region V (Bicol Region) | Camarines Sur | Caramoan | Agaas | 13.8104 | 123.8032 | R | 432 | 4.2 | 103 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.65 | 36.08 | Tier 1B: High GIDA Priority | 42.96 | 42.96 | 59.84 | 51.4 | F - Nearest node and line over 5 km | 7.65 | 999999 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4750
4 | 1751 | 4751 | 1003502003 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Angandog | 8.1066 | 124.1922 | R | 1597 | 4.2 | 380 | 114 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.04 | 3 | Tier 1B: High GIDA Priority | 41.24 | 41.24 | 61.56 | 51.4 | D - Other node or line within 3 km | 14.04 | 2.85 | Line: 216f feeder iligan completed | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4751
4 | 1752 | 4752 | 0907216004 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Dinulan | 7.3246 | 122.0944 | R | 364 | 3.6 | 101 | 30 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 20.58 | 18.28 | Tier 1B: High GIDA Priority | 31.28 | 31.28 | 71.53 | 51.4 | F - Nearest node and line over 5 km | 20.58 | 18.25 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4752
4 | 1753 | 4753 | 0402108032 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Buenavista II | 14.305 | 120.8977 | U | 11946 | 3.4 | 3514 | 1054 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.79 | 1.73 | Tier 2B: Moderate GIDA Inclusion | 68.81 | 68.81 | 33.97 | 51.39 | D - Other node or line within 3 km | 1.79 | 1.73 | Line: NCC001 TO TGY001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4753
4 | 1754 | 4754 | 0405809003 | Region IV-A (CALABARZON) | Rizal | Morong | Lagundi | 14.5274 | 121.2544 | U | 9646 | 3.6 | 2679 | 804 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.37 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 66.94 | 66.94 | 35.83 | 51.39 | C - Line within 0.5 km; node over 1 km | 1.37 | 0.21 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4754
4 | 1755 | 4755 | 1401112006 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Bayabas | 16.475 | 120.4861 | R | 2532 | 3.5 | 723 | 217 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.66 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 66.84 | 66.84 | 35.94 | 51.39 | D - Other node or line within 3 km | 2.66 | 1.48 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4755
4 | 1756 | 4756 | 1004307003 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Bolobolo | 8.5561 | 124.5333 | U | 4752 | 3.9 | 1218 | 365 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.09 | Tier 2B: Moderate GIDA Inclusion | 65.06 | 65.06 | 37.71 | 51.39 | C - Line within 0.5 km; node over 1 km | 1.05 | 0.09 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4756
4 | 1757 | 4757 | 1108209008 | Region XI (Davao Region) | Davao de Oro | Nabunturan | Linda | 7.5896 | 125.9408 | R | 2938 | 3.7 | 794 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.53 | 0.18 | Tier 2B: Moderate GIDA Inclusion | 52.38 | 52.38 | 50.41 | 51.39 | C - Line within 0.5 km; node over 1 km | 19.53 | 0.17 | Line: DAVAO CITY - TRENTO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4757
4 | 1758 | 4758 | 1906618012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Siganggang | 17.2556 | 122.2297 | R | 5176 | 6 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.4 | Tier 2B: Moderate GIDA Inclusion | 51.68 | 51.68 | 51.11 | 51.39 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4758
4 | 1759 | 4759 | 0506216050 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Osiao | 13.0872 | 123.9936 | U | 3144 | 4 | 786 | 236 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.47 | 11.36 | Tier 2B: Moderate GIDA Inclusion | 49.8 | 49.8 | 52.98 | 51.39 | F - Nearest node and line over 5 km | 7.47 | 11.3 | Node: SCS003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4759
4 | 1760 | 4760 | 0405808009 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Isidro | 14.7614 | 121.1584 | U | 152796 | 3.6 | 42443 | 12733 | Band n50 (1.5 GHz, 100 MHz TDD) | 13 | 1 | 2.92 | 0.58 | Tier 2B: Moderate GIDA Inclusion | 48.67 | 48.67 | 54.12 | 51.39 | C - Line within 0.5 km; node over 1 km | 2.92 | 0.35 | Line: Aerial 216C | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4760
4 | 1761 | 4761 | 1906603004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Kalingalan Caluang | Kanlagay | 17.2555 | 122.2296 | R | 2665 | 4.3 | 620 | 186 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.52 | 34.39 | Tier 1B: High GIDA Priority | 45.31 | 45.31 | 57.46 | 51.39 | F - Nearest node and line over 5 km | 29.52 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4761
4 | 1762 | 4762 | 0806019011 | Region VIII (Eastern Visayas) | Samar | Talalora | Victory | 11.5097 | 124.8304 | R | 272 | 4.1 | 66 | 20 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.96 | 27.71 | Tier 1B: High GIDA Priority | 37.54 | 37.54 | 65.24 | 51.39 | F - Nearest node and line over 5 km | 27.96 | 27.71 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4762
4 | 1763 | 4763 | 1705310007 | MIMAROPA Region | Palawan | Cuyo | Funda | 10.8127 | 120.984 | R | 751 | 3.9 | 193 | 58 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 104.35 | 104.34 | Tier 1B: High GIDA Priority | 35.93 | 35.93 | 66.84 | 51.39 | F - Nearest node and line over 5 km | 104.35 | 999999 | Node: SBV001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4763
4 | 1764 | 4764 | 0506216001 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Abuyog | 12.9463 | 124.0524 | R | 4670 | 4 | 1168 | 350 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.1 | 0.31 | Tier 2A: High Commercial ROI | 75.66 | 75.66 | 27.11 | 51.38 | A - Node within 0.5 km | 0.1 | 0.06 | Line: SORSOGON - MATNOG | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4764
4 | 1765 | 4765 | 0600416007 | Region VI (Western Visayas) | Aklan | Numancia | Camanci Norte | 11.7318 | 122.3549 | R | 3461 | 3.9 | 887 | 266 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.04 | 1.73 | Tier 2B: Moderate GIDA Inclusion | 69.32 | 69.32 | 33.43 | 51.38 | D - Other node or line within 3 km | 4.04 | 1.73 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4765
4 | 1766 | 4766 | 0306906027 | Region III (Central Luzon) | Tarlac | Gerona | Pinasling | 15.6015 | 120.5893 | R | 3860 | 3.9 | 990 | 297 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.83 | 1.1 | Tier 2B: Moderate GIDA Inclusion | 68.71 | 68.71 | 34.05 | 51.38 | D - Other node or line within 3 km | 1.83 | 1.1 | Line: GERONA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4766
4 | 1767 | 4767 | 0401031016 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Darasa | 14.0692 | 121.1533 | U | 24699 | 3.6 | 6861 | 2058 | Band n50 (1.5 GHz, 100 MHz TDD) | 3 | 1 | 1.6 | 0.29 | Tier 2B: Moderate GIDA Inclusion | 68.27 | 68.27 | 34.5 | 51.38 | C - Line within 0.5 km; node over 1 km | 1.6 | 0.09 | Line: UG_TNB001 TO DIVERSION RD | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4767
4 | 1768 | 4768 | 0306916015 | Region III (Central Luzon) | Tarlac | City of Tarlac | Baras-baras | 15.5181 | 120.5652 | U | 5396 | 3.9 | 1384 | 415 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 65.57 | 65.57 | 37.19 | 51.38 | A - Node within 0.5 km | 0.16 | 0.25 | Node: TCT005 - TYPE 3 | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4768
4 | 1769 | 4769 | 0806020031 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Marabut | 11.8915 | 124.7571 | R | 251 | 4.1 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.21 | 66.18 | Tier 1B: High GIDA Priority | 36.7 | 36.7 | 66.07 | 51.38 | F - Nearest node and line over 5 km | 66.21 | 999999 | Node: CAL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4769
4 | 1770 | 4770 | 1004205022 | Region X (Northern Mindanao) | Misamis Occidental | Clarin | Penacio | 8.257 | 123.7923 | R | 397 | 3.9 | 102 | 31 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 23.81 | 18.43 | Tier 1B: High GIDA Priority | 36.6 | 36.6 | 66.15 | 51.38 | F - Nearest node and line over 5 km | 23.81 | 18.38 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4770
4 | 1771 | 4771 | 0907318036 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Midsalip | Guitalos | 8.0603 | 123.2475 | R | 711 | 3.9 | 182 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.12 | 23.38 | Tier 1B: High GIDA Priority | 35.38 | 35.38 | 67.38 | 51.38 | F - Nearest node and line over 5 km | 33.12 | 23.38 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4771
4 | 1772 | 4772 | 1903631015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Mantailoco | 17.2548 | 122.2289 | R | 958 | 5.7 | 168 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.41 | 34.3 | Tier 1B: High GIDA Priority | 33.46 | 33.46 | 69.31 | 51.38 | F - Nearest node and line over 5 km | 29.41 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4772
4 | 1773 | 4773 | 1108204011 | Region XI (Davao Region) | Davao de Oro | Maco | Hijo | 7.3717 | 125.8363 | R | 4308 | 3.7 | 1164 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.75 | 0.68 | Tier 2B: Moderate GIDA Inclusion | 69.75 | 69.75 | 32.98 | 51.37 | D - Other node or line within 3 km | 2.75 | 0.67 | Line: TAGUM - PANTUKAN SEGMENT 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4773
4 | 1774 | 4774 | 0702233015 | Region VII (Central Visayas) | Cebu | Moalboal | Tunga | 9.9539 | 123.4001 | R | 2927 | 3.8 | 770 | 231 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.79 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 69.5 | 69.5 | 33.24 | 51.37 | C - Line within 0.5 km; node over 1 km | 1.79 | 0.08 | Line: Segment 7 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4774
4 | 1775 | 4775 | 0300811027 | Region III (Central Luzon) | Bataan | Pilar | Wawa | 14.6714 | 120.5626 | R | 2391 | 3.6 | 664 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 0.82 | Tier 2B: Moderate GIDA Inclusion | 61.13 | 61.13 | 41.6 | 51.37 | D - Other node or line within 3 km | 2.3 | 0.81 | Line: Pipe 2 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4775
4 | 1776 | 4776 | 0305419006 | Region III (Central Luzon) | Pampanga | Santa Ana | San Juan | 15.0827 | 120.7716 | R | 2995 | 4 | 749 | 225 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.42 | 0.83 | Tier 2B: Moderate GIDA Inclusion | 61.13 | 61.13 | 41.6 | 51.37 | D - Other node or line within 3 km | 4.42 | 0.83 | Line: .26 km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4776
4 | 1777 | 4777 | 0403410027 | Region IV-A (CALABARZON) | Laguna | Liliw | Masikap | 14.1737 | 121.4054 | R | 1806 | 3.3 | 547 | 164 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 2.6 | Tier 2B: Moderate GIDA Inclusion | 57.04 | 57.04 | 45.7 | 51.37 | D - Other node or line within 3 km | 3.88 | 2.6 | Line: PAGSANJAN TO LILIW | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4777
4 | 1778 | 4778 | 0301407009 | Region III (Central Luzon) | Bulacan | Calumpit | Corazon | 14.912 | 120.7683 | U | 2273 | 3.5 | 649 | 195 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 56.15 | 56.15 | 46.59 | 51.37 | B - Node 0.5-1 km | 0.63 | 0.19 | Line: Mnla Pipe | Survey short node lateral; confirm port/fiber capacity, access and route. | 4778
4 | 1779 | 4779 | 0907307057 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Anonang | 7.8188 | 123.3848 | R | 1164 | 3.9 | 298 | 89 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.15 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 52.76 | 52.76 | 49.97 | 51.37 | C - Line within 0.5 km; node over 1 km | 6.15 | 0.04 | Line: ILIGAN - PAGADIAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4779
4 | 1780 | 4780 | 1606818011 | Region XIII (Caraga) | Surigao del Sur | Tago | Dayo-an | 9.0161 | 126.1797 | R | 1460 | 4.1 | 356 | 107 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.04 | 0.24 | Tier 2B: Moderate GIDA Inclusion | 50.4 | 50.4 | 52.34 | 51.37 | C - Line within 0.5 km; node over 1 km | 7.04 | 0.24 | Line: Route | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4780
4 | 1781 | 4781 | 0601913019 | Region VI (Western Visayas) | Capiz | President Roxas | Quiajo | 11.4622 | 122.918 | R | 700 | 3.8 | 184 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.32 | 3.54 | Tier 2B: Moderate GIDA Inclusion | 46.03 | 46.03 | 56.71 | 51.37 | E - Nearest node or line 3-5 km | 9.32 | 3.5 | Line: ROXAS - SARA | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4781
4 | 1782 | 4782 | 1705915008 | MIMAROPA Region | Romblon | Santa Fe | Mat-i | 12.187 | 121.9851 | R | 1249 | 3.7 | 338 | 101 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 26.88 | 6.36 | Tier 1B: High GIDA Priority | 40.49 | 40.49 | 62.25 | 51.37 | F - Nearest node and line over 5 km | 26.88 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4782
4 | 1783 | 4783 | 1906605008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Maimbung | Gulangan | 17.2553 | 122.2294 | R | 1007 | 6 | 168 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.49 | 34.36 | Tier 1B: High GIDA Priority | 33.45 | 33.45 | 69.29 | 51.37 | F - Nearest node and line over 5 km | 29.49 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4783
4 | 1784 | 4784 | 1380606017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 411 | 12.2292 | 122.6436 | U | 2182 | 4.2 | 520 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 66.34 | 41.64 | Tier 1B: High GIDA Priority | 29.99 | 29.99 | 72.76 | 51.37 | F - Nearest node and line over 5 km | 66.34 | 999999 | Node: KOK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4784
4 | 1785 | 4785 | 0405647030 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Ipilan | 14.024 | 121.587 | R | 4041 | 3.8 | 1063 | 319 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.7 | 0.59 | Tier 2A: High Commercial ROI | 70.72 | 70.72 | 31.99 | 51.36 | B - Node 0.5-1 km | 0.7 | 0.59 | Line: LUCENA - LUCBAN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4785
4 | 1786 | 4786 | 0601903004 | Region VI (Western Visayas) | Capiz | Dumalag | Duran | 11.2713 | 122.6033 | R | 3581 | 3.8 | 942 | 283 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.17 | 0.8 | Tier 2B: Moderate GIDA Inclusion | 67.94 | 67.94 | 34.78 | 51.36 | D - Other node or line within 3 km | 8.17 | 0.77 | Line: CABLE LAYED | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4786
4 | 1787 | 4787 | 0105526023 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Osiem | 16.0595 | 120.422 | R | 3375 | 3.6 | 938 | 281 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 1.95 | Tier 2B: Moderate GIDA Inclusion | 67.85 | 67.85 | 34.87 | 51.36 | D - Other node or line within 3 km | 2.3 | 1.95 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4787
4 | 1788 | 4788 | 0105535013 | Region I (Ilocos Region) | Pangasinan | San Manuel | San Bonifacio | 16.0919 | 120.6631 | R | 3739 | 3.6 | 1039 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.97 | 3.29 | Tier 2B: Moderate GIDA Inclusion | 63.77 | 63.77 | 38.94 | 51.36 | D - Other node or line within 3 km | 2.97 | 3.29 | Node: SMP001 - TYPE 4 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4788
4 | 1789 | 4789 | 1102317046 | Region XI (Davao Region) | Davao del Norte | Island Garden City of Samal | Toril | 7.1316 | 125.7176 | R | 4168 | 3.7 | 1126 | 338 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.97 | 6.17 | Tier 2B: Moderate GIDA Inclusion | 62.33 | 62.33 | 40.39 | 51.36 | F - Nearest node and line over 5 km | 7.97 | 6.66 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4789
4 | 1790 | 4790 | 0300804040 | Region III (Central Luzon) | Bataan | Dinalupihan | Santa Isabel | 14.8599 | 120.4714 | U | 2819 | 3.6 | 783 | 235 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.54 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 59.93 | 59.93 | 42.79 | 51.36 | B - Node 0.5-1 km | 0.54 | 0.03 | Line: 12 CORE (2X6) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4790
4 | 1791 | 4791 | 1206316018 | Region XII (SOCCSKSARGEN) | South Cotabato | T'Boli | Lambuling | 6.2537 | 124.8917 | R | 4740 | 3.6 | 1317 | 395 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.66 | 13.04 | Tier 2B: Moderate GIDA Inclusion | 59.9 | 59.9 | 42.81 | 51.36 | F - Nearest node and line over 5 km | 10.66 | 13.04 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4791
4 | 1792 | 4792 | 0500508050 | Region V (Bicol Region) | Albay | City of Ligao | Tinampo | 13.2275 | 123.5127 | R | 3026 | 4.1 | 738 | 221 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.79 | 2.32 | Tier 2B: Moderate GIDA Inclusion | 59.32 | 59.32 | 43.4 | 51.36 | D - Other node or line within 3 km | 2.79 | 2.29 | Line: IRIGA - LEGAZPI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4792
4 | 1793 | 4793 | 0304928024 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Burgos | 15.4363 | 120.975 | R | 1550 | 3.5 | 443 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.91 | 0.92 | Tier 2B: Moderate GIDA Inclusion | 57.52 | 57.52 | 45.2 | 51.36 | D - Other node or line within 3 km | 4.84 | 0.92 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4793
4 | 1794 | 4794 | 1705318006 | MIMAROPA Region | Palawan | Roxas | Iraan | 10.4386 | 119.3577 | R | 777 | 3.9 | 199 | 60 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.52 | 1.71 | Tier 1B: High GIDA Priority | 40.26 | 40.26 | 62.45 | 51.36 | D - Other node or line within 3 km | 13.52 | 1.7 | Line: TAYTAY - PUERTO PRINCESA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4794
4 | 1795 | 4795 | 1381100045 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 45 | 14.5093 | 120.9524 | U | 1157 | 3.59 | 322 | 97 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.28 | 4.25 | Tier 1B: High GIDA Priority | 33.87 | 33.87 | 68.84 | 51.36 | E - Nearest node or line 3-5 km | 4.28 | 4.25 | Line: Existing 144C via Y-Duct | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4795
4 | 1796 | 4796 | 0601905015 | Region VI (Western Visayas) | Capiz | Ivisan | Santa Cruz | 11.5206 | 122.7094 | R | 2123 | 3.8 | 559 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.68 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 64.96 | 64.96 | 37.75 | 51.35 | C - Line within 0.5 km; node over 1 km | 1.68 | 0.42 | Line: ROXAS - IVISAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4796
4 | 1797 | 4797 | 0304907016 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Tagumpay | 15.4837 | 121.3153 | R | 2801 | 3.5 | 800 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.89 | 21.38 | Tier 2B: Moderate GIDA Inclusion | 61.94 | 61.94 | 40.77 | 51.35 | D - Other node or line within 3 km | 1.89 | 21.37 | Node: GBN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4797
4 | 1798 | 4798 | 0300807011 | Region III (Central Luzon) | Bataan | Mariveles | Sisiman | 14.427 | 120.5177 | U | 7591 | 3.6 | 2109 | 633 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.29 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 60.95 | 60.95 | 41.76 | 51.35 | C - Line within 0.5 km; node over 1 km | 5.29 | 0.04 | Line: 24 CORE 3X8 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4798
4 | 1799 | 4799 | 0203125017 | Region II (Cagayan Valley) | Isabela | Reina Mercedes | Tallungan | 16.9976 | 121.8083 | U | 1946 | 3.8 | 512 | 154 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.97 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 56.3 | 56.3 | 46.4 | 51.35 | B - Node 0.5-1 km | 0.97 | 0.5 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Survey short node lateral; confirm port/fiber capacity, access and route. | 4799
4 | 1800 | 4800 | 0405627027 | Region IV-A (CALABARZON) | Quezon | Mauban | Rosario | 13.9391 | 122.0518 | R | 637 | 3.8 | 168 | 50 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.71 | 0.34 | Tier 2B: Moderate GIDA Inclusion | 45.84 | 45.84 | 56.85 | 51.35 | C - Line within 0.5 km; node over 1 km | 3.71 | 0.3 | Line: PAGBILAO - NAGA (UG + Aerial) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4800
4 | 1801 | 4801 | 0704613008 | Region VII (Central Visayas) | Negros Oriental | La Libertad | Eli | 10.0559 | 123.1381 | R | 1696 | 3.8 | 446 | 134 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 15.88 | 10.46 | Tier 1B: High GIDA Priority | 42.55 | 42.55 | 60.15 | 51.35 | F - Nearest node and line over 5 km | 15.88 | 10.6 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4801
4 | 1802 | 4802 | 0702214009 | Region VII (Central Visayas) | Cebu | City of Carcar | Perrelos | 10.1141 | 123.6751 | U | 17198 | 3.8 | 4526 | 1358 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.2 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 70.48 | 70.48 | 32.2 | 51.34 | C - Line within 0.5 km; node over 1 km | 4.2 | 0.03 | Line: 216f | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4802
4 | 1803 | 4803 | 0304909005 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Belen | 15.5814 | 121.0484 | R | 2552 | 3.5 | 729 | 219 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.29 | 1.97 | Tier 2B: Moderate GIDA Inclusion | 69.05 | 69.05 | 33.62 | 51.34 | D - Other node or line within 3 km | 1.29 | 1.97 | Node: GMN001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4803
4 | 1804 | 4804 | 0102921007 | Region I (Ilocos Region) | Ilocos Sur | San Vicente | San Sebastian | 17.6224 | 120.3656 | R | 3453 | 3.8 | 909 | 273 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.14 | 2.96 | Tier 2B: Moderate GIDA Inclusion | 66.65 | 66.65 | 36.03 | 51.34 | D - Other node or line within 3 km | 4.14 | 2.88 | Line: SEGMENT 3 (VIGAN - BATAC) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4804
4 | 1805 | 4805 | 1606808002 | Region XIII (Caraga) | Surigao del Sur | Cortes | Burgos | 9.2547 | 126.1733 | R | 3668 | 4.1 | 895 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.94 | 0.21 | Tier 2B: Moderate GIDA Inclusion | 59.19 | 59.19 | 43.49 | 51.34 | C - Line within 0.5 km; node over 1 km | 19.94 | 0.21 | Line: Route | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4805
4 | 1806 | 4806 | 0301420023 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima II | 14.8408 | 121.0595 | R | 1976 | 3.5 | 565 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 2.17 | Tier 2B: Moderate GIDA Inclusion | 54.87 | 54.87 | 47.81 | 51.34 | D - Other node or line within 3 km | 2.41 | 5.03 | Node: SJD002 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4806
4 | 1807 | 4807 | 0205001010 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Dulli | 16.5486 | 121.0762 | R | 2022 | 3.8 | 532 | 160 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.14 | 8.99 | Tier 2B: Moderate GIDA Inclusion | 51.75 | 51.75 | 50.94 | 51.34 | F - Nearest node and line over 5 km | 10.14 | 8.99 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4807
4 | 1808 | 4808 | 1380604015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 282 | 12.0011 | 120.8727 | U | 2503 | 3.79 | 660 | 198 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.13 | 44.13 | Tier 1B: High GIDA Priority | 33.65 | 33.65 | 69.02 | 51.34 | F - Nearest node and line over 5 km | 44.13 | 44.12 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4808
4 | 1809 | 4809 | 0702224035 | Region VII (Central Visayas) | Cebu | Dumanjug | Tapon | 10.0621 | 123.4444 | R | 4211 | 3.8 | 1108 | 332 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.32 | Tier 2A: High Commercial ROI | 73.43 | 73.43 | 29.23 | 51.33 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.06 | Line: TOLEDO CLS - DUMANJOG | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4809
4 | 1810 | 4810 | 0500503031 | Region V (Bicol Region) | Albay | Daraga | Malabog | 13.172 | 123.6851 | R | 4458 | 4.1 | 1087 | 326 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.97 | 0.21 | Tier 2A: High Commercial ROI | 71.81 | 71.81 | 30.84 | 51.33 | C - Line within 0.5 km; node over 1 km | 1.97 | 0.21 | Line: IRIGA - LEGAZPI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4810
4 | 1811 | 4811 | 0402120043 | Region IV-A (CALABARZON) | Cavite | Tanza | Paradahan II | 14.3248 | 120.8592 | R | 5133 | 3.4 | 1510 | 453 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.82 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 66.72 | 66.72 | 35.94 | 51.33 | D - Other node or line within 3 km | 4.82 | 0.51 | Line: TANZA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4811
4 | 1812 | 4812 | 0603036017 | Region VI (Western Visayas) | Iloilo | Pavia | Tigum | 10.7806 | 122.5481 | R | 2646 | 3.8 | 696 | 209 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.84 | 3.87 | Tier 2B: Moderate GIDA Inclusion | 61.52 | 61.52 | 41.13 | 51.33 | B - Node 0.5-1 km | 0.84 | 3.86 | Node: PVI001 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4812
4 | 1813 | 4813 | 0301423014 | Region III (Central Luzon) | Bulacan | Santa Maria | Manggahan | 14.8528 | 120.9575 | U | 2905 | 3.5 | 830 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.22 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 59.87 | 59.87 | 42.78 | 51.33 | C - Line within 0.5 km; node over 1 km | 1.22 | 0.08 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4813
4 | 1814 | 4814 | 0604528043 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Katilingban | 10.7103 | 123.0929 | R | 2820 | 3.7 | 762 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.08 | 10.57 | Tier 2B: Moderate GIDA Inclusion | 56.01 | 56.01 | 46.66 | 51.33 | F - Nearest node and line over 5 km | 8.08 | 10.57 | Node: BDN004 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4814
4 | 1815 | 4815 | 1403209010 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Katabbogan | 17.6517 | 121.4004 | R | 1783 | 4.3 | 415 | 124 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 55.81 | 55.81 | 46.86 | 51.33 | C - Line within 0.5 km; node over 1 km | 1.59 | 0.1 | Line: Tabuk-Conner | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4815
4 | 1816 | 4816 | 0301410023 | Region III (Central Luzon) | Bulacan | City of Malolos | Liang | 14.8396 | 120.8178 | U | 1399 | 3.5 | 400 | 120 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 1.23 | Tier 2B: Moderate GIDA Inclusion | 49.49 | 49.49 | 53.17 | 51.33 | B - Node 0.5-1 km | 0.59 | 1.24 | Node: MSB003 - TYPE 3 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4816
4 | 1817 | 4817 | 0804815005 | Region VIII (Eastern Visayas) | Northern Samar | Pambujan | Cagbigajo | 12.4179 | 124.9103 | R | 582 | 4.3 | 135 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 90.93 | 90.21 | Tier 1B: High GIDA Priority | 36.69 | 36.69 | 65.98 | 51.33 | F - Nearest node and line over 5 km | 90.93 | 999999 | Node: SMS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4817
4 | 1818 | 4818 | 1003515006 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Inayawan | 7.7864 | 123.9207 | R | 943 | 4.2 | 225 | 68 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.51 | 20.74 | Tier 1B: High GIDA Priority | 33.23 | 33.23 | 69.43 | 51.33 | F - Nearest node and line over 5 km | 31.51 | 20.73 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4818
4 | 1819 | 4819 | 0105523018 | Region I (Ilocos Region) | Pangasinan | Mabini | Tagudin | 16.0831 | 119.954 | R | 4246 | 3.6 | 1179 | 354 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.95 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 67.72 | 67.72 | 34.92 | 51.32 | C - Line within 0.5 km; node over 1 km | 2.95 | 0.06 | Line: MABINI | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4819
4 | 1820 | 4820 | 0603036014 | Region VI (Western Visayas) | Iloilo | Pavia | Pandac | 10.7513 | 122.521 | U | 7512 | 3.8 | 1977 | 593 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 1.11 | Tier 2B: Moderate GIDA Inclusion | 64.65 | 64.65 | 37.98 | 51.32 | D - Other node or line within 3 km | 3.55 | 1.06 | Line: 7,092 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4820
4 | 1821 | 4821 | 0301410038 | Region III (Central Luzon) | Bulacan | City of Malolos | Panasahan | 14.8219 | 120.827 | U | 9913 | 3.5 | 2832 | 850 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.08 | 2.77 | Tier 2B: Moderate GIDA Inclusion | 64.6 | 64.6 | 38.04 | 51.32 | D - Other node or line within 3 km | 1.08 | 2.76 | Node: MSB002 - TYPE4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4821
4 | 1822 | 4822 | 0803738082 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Isidro | 11.0271 | 124.5948 | U | 6373 | 3.8 | 1677 | 503 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.59 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 68.38 | 68.38 | 34.24 | 51.31 | C - Line within 0.5 km; node over 1 km | 1.79 | 0.13 | Line: ORMOC - PALOMPON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4822
4 | 1823 | 4823 | 0601916002 | Region VI (Western Visayas) | Capiz | Sigma | Amaga | 11.4431 | 122.6833 | R | 2576 | 3.8 | 678 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.9 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 65.83 | 65.83 | 36.79 | 51.31 | C - Line within 0.5 km; node over 1 km | 2.9 | 0.05 | Line: ROXAS - ILOILO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4823
4 | 1824 | 4824 | 0405804012 | Region IV-A (CALABARZON) | Rizal | Binangonan | Ithan | 14.4317 | 121.2143 | R | 3597 | 3.6 | 999 | 300 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 4.67 | Tier 2B: Moderate GIDA Inclusion | 65.52 | 65.52 | 37.1 | 51.31 | D - Other node or line within 3 km | 1.52 | 4.52 | Node: BIR003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4824
4 | 1825 | 4825 | 0304927014 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tabuating | 15.3903 | 120.9405 | U | 5055 | 3.5 | 1444 | 433 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.72 | 0.1 | Tier 2B: Moderate GIDA Inclusion | 61.31 | 61.31 | 41.31 | 51.31 | C - Line within 0.5 km; node over 1 km | 2.72 | 0.1 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4825
4 | 1826 | 4826 | 0403416004 | Region IV-A (CALABARZON) | Laguna | Majayjay | Balanac | 14.1487 | 121.4707 | R | 56 | 3.3 | 17 | 5 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.63 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 53.85 | 53.85 | 48.77 | 51.31 | B - Node 0.5-1 km | 0.63 | 0.48 | Line: SAN PABLO - LUCBAN AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4826
4 | 1827 | 4827 | 0504104008 | Region V (Bicol Region) | Masbate | Batuan | Matabao | 12.3163 | 123.8065 | R | 545 | 4.1 | 133 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.29 | 19.87 | Tier 1B: High GIDA Priority | 44.42 | 44.42 | 58.19 | 51.31 | F - Nearest node and line over 5 km | 10.29 | 21.08 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4827
4 | 1828 | 4828 | 1906612020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Kud-kud | 17.2556 | 122.2297 | R | 1487 | 6 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.4 | Tier 1B: High GIDA Priority | 31.04 | 31.04 | 71.57 | 51.31 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4828
4 | 1829 | 4829 | 0601905008 | Region VI (Western Visayas) | Capiz | Ivisan | Malocloc Norte | 11.5056 | 122.6797 | R | 2526 | 3.8 | 665 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.32 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 66.38 | 66.38 | 36.21 | 51.3 | C - Line within 0.5 km; node over 1 km | 2.32 | 0.02 | Line: IVISAN - KALIBO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4829
4 | 1830 | 4830 | 0401002016 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Poblacion West | 13.88 | 121.0191 | R | 2672 | 3.6 | 742 | 223 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.83 | 1.37 | Tier 2B: Moderate GIDA Inclusion | 65.95 | 65.95 | 36.65 | 51.3 | D - Other node or line within 3 km | 3.83 | 1.35 | Line: UG BUN001 TO SSB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4830
4 | 1831 | 4831 | 0304930052 | Region III (Central Luzon) | Nueva Ecija | Talavera | San Ricardo | 15.5927 | 120.9724 | R | 3018 | 3.5 | 862 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.81 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 63.28 | 63.28 | 39.32 | 51.3 | C - Line within 0.5 km; node over 1 km | 5.81 | 0.38 | Line: Proposed AE F1-6 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4831
4 | 1832 | 4832 | 0304907002 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Bagting | 15.5552 | 121.2483 | R | 3842 | 3.5 | 1098 | 329 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.77 | 12.5 | Tier 2B: Moderate GIDA Inclusion | 62.21 | 62.21 | 40.38 | 51.3 | E - Nearest node or line 3-5 km | 4.77 | 12.37 | Node: LRN001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4832
4 | 1833 | 4833 | 1001315013 | Region X (Northern Mindanao) | Bukidnon | Maramag | Panalsalan | 7.8594 | 124.9771 | R | 2741 | 3.8 | 721 | 216 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.12 | 0.19 | Tier 2B: Moderate GIDA Inclusion | 60.07 | 60.07 | 42.53 | 51.3 | C - Line within 0.5 km; node over 1 km | 5.12 | 0.12 | Line: DAMULOG - VALENCIA - QUEZON | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4833
4 | 1834 | 4834 | 0401019045 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Talangan | 14.1 | 120.7004 | R | 2844 | 3.6 | 790 | 237 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.13 | 3.14 | Tier 2B: Moderate GIDA Inclusion | 57.65 | 57.65 | 44.94 | 51.3 | E - Nearest node or line 3-5 km | 6.13 | 3.14 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4834
4 | 1835 | 4835 | 0501603031 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VIII | 14.1143 | 122.9625 | U | 2819 | 4 | 705 | 212 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.94 | 1.73 | Tier 2B: Moderate GIDA Inclusion | 57.56 | 57.56 | 45.05 | 51.3 | B - Node 0.5-1 km | 0.94 | 1.73 | Node: DEC001 - TYPE 2 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4835
4 | 1836 | 4836 | 0300804034 | Region III (Central Luzon) | Bataan | Dinalupihan | San Isidro | 14.8727 | 120.4519 | R | 939 | 3.6 | 261 | 78 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.78 | 0.74 | Tier 2B: Moderate GIDA Inclusion | 52.85 | 52.85 | 49.75 | 51.3 | B - Node 0.5-1 km | 0.78 | 0.74 | Line: Layac - Olongapo AERIAL | Survey short node lateral; confirm port/fiber capacity, access and route. | 4836
4 | 1837 | 4837 | 0603016005 | Region VI (Western Visayas) | Iloilo | Dingle | Bongloy | 10.9878 | 122.6465 | R | 1087 | 3.8 | 286 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.67 | 1.67 | Tier 2B: Moderate GIDA Inclusion | 50.84 | 50.84 | 51.75 | 51.3 | D - Other node or line within 3 km | 4.67 | 1.66 | Line: ROXAS - ILOILO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4837
4 | 1838 | 4838 | 0301410042 | Region III (Central Luzon) | Bulacan | City of Malolos | San Gabriel | 14.8301 | 120.8226 | U | 2103 | 3.5 | 601 | 180 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.35 | 2.05 | Tier 2B: Moderate GIDA Inclusion | 49.93 | 49.93 | 52.66 | 51.3 | D - Other node or line within 3 km | 1.35 | 2.05 | Node: MSB002 - TYPE4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4838
4 | 1839 | 4839 | 0603027024 | Region VI (Western Visayas) | Iloilo | Lemery | San Diego | 11.2458 | 122.8546 | R | 769 | 3.8 | 202 | 61 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.85 | 6.33 | Tier 2B: Moderate GIDA Inclusion | 48.24 | 48.24 | 54.36 | 51.3 | F - Nearest node and line over 5 km | 7.85 | 6.27 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4839
4 | 1840 | 4840 | 1381100030 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 30 | 14.5268 | 120.9635 | U | 993 | 3.56 | 279 | 84 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.62 | 3.61 | Tier 1B: High GIDA Priority | 33.35 | 33.35 | 69.25 | 51.3 | E - Nearest node or line 3-5 km | 3.62 | 3.61 | Line: Aerial 216C MTF | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4840
4 | 1841 | 4841 | 0603018028 | Region VI (Western Visayas) | Iloilo | Dumangas | Pd Monfort North | 10.8474 | 122.6995 | R | 4633 | 3.8 | 1219 | 366 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.63 | 1.66 | Tier 2A: High Commercial ROI | 71.32 | 71.32 | 31.26 | 51.29 | D - Other node or line within 3 km | 2.63 | 1.65 | Line: DUMANGAS CO-BAROTAC NUEVO CO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4841
4 | 1842 | 4842 | 0403417048 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Talangan | 14.1437 | 121.4138 | R | 2234 | 3.3 | 677 | 203 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 64.12 | 64.12 | 38.47 | 51.29 | B - Node 0.5-1 km | 0.73 | 0.71 | Line: UG SCL001 TO NGL001 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4842
4 | 1843 | 4843 | 0305406003 | Region III (Central Luzon) | Pampanga | Floridablanca | Basa Air Base | 14.9787 | 120.4997 | R | 2657 | 4 | 664 | 199 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.55 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 62.3 | 62.3 | 40.27 | 51.29 | C - Line within 0.5 km; node over 1 km | 1.55 | 0.36 | Line: 48 CORE (4X12) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4843
4 | 1844 | 4844 | 0603044040 | Region VI (Western Visayas) | Iloilo | Sara | Tady | 11.2639 | 122.9982 | R | 1663 | 3.8 | 438 | 131 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.26 | 1.28 | Tier 2B: Moderate GIDA Inclusion | 56.81 | 56.81 | 45.77 | 51.29 | D - Other node or line within 3 km | 2.26 | 1.28 | Line: SARA - PASSI | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4844
4 | 1845 | 4845 | 0702211029 | Region VII (Central Visayas) | Cebu | City of Bogo | Sudlonon | 11.0104 | 124.0026 | R | 944 | 3.8 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.11 | 1.15 | Tier 2B: Moderate GIDA Inclusion | 50.4 | 50.4 | 52.17 | 51.29 | D - Other node or line within 3 km | 4.11 | 1.15 | Line: BOGO - DANAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4845
4 | 1846 | 4846 | 1403209024 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Taggay | 17.6328 | 121.3554 | R | 1184 | 4.3 | 275 | 82 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.63 | 5.23 | Tier 2B: Moderate GIDA Inclusion | 45.92 | 45.92 | 56.66 | 51.29 | E - Nearest node or line 3-5 km | 3.63 | 5.2 | Node: PKK003 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4846
4 | 1847 | 4847 | 0401006032 | Region IV-A (CALABARZON) | Batangas | Bauan | San Andres Uno | 13.8066 | 120.9594 | R | 624 | 3.6 | 173 | 52 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.25 | 3.91 | Tier 1B: High GIDA Priority | 43 | 43 | 59.57 | 51.29 | E - Nearest node or line 3-5 km | 3.25 | 3.92 | Node: BUN002 - PM | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4847
4 | 1848 | 4848 | 1380606221 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 614 | 13.0598 | 121.5101 | U | 406 | 4.51 | 90 | 27 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.62 | 4.03 | Tier 1A: Strategic Prime (Critical GIDA + Direct Fiber) | 34.02 | 34.02 | 68.56 | 51.29 | B - Node 0.5-1 km | 0.62 | 4 | Node: PYM002 - TYPE 4 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4848
4 | 1849 | 4849 | 0203130002 | Region II (Cagayan Valley) | Isabela | San Manuel | Babanuang | 17.0502 | 121.6282 | R | 3136 | 3.8 | 825 | 248 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.16 | 0.3 | Tier 2A: High Commercial ROI | 73.92 | 73.92 | 28.65 | 51.28 | A - Node within 0.5 km | 0.16 | 0.3 | Node: MNI001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4849
4 | 1850 | 4850 | 0702201006 | Region VII (Central Visayas) | Cebu | Alcantara | Palanas | 9.9849 | 123.4103 | R | 3312 | 3.8 | 872 | 262 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.69 | 0.35 | Tier 2A: High Commercial ROI | 71.97 | 71.97 | 30.6 | 51.28 | C - Line within 0.5 km; node over 1 km | 1.69 | 0.32 | Line: Segment 9 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4850
4 | 1851 | 4851 | 0401008028 | Region IV-A (CALABARZON) | Batangas | Calatagan | Tanagan | 13.8182 | 120.6421 | R | 4734 | 3.6 | 1315 | 394 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.58 | 1.68 | Tier 2B: Moderate GIDA Inclusion | 69.88 | 69.88 | 32.69 | 51.28 | D - Other node or line within 3 km | 1.58 | 1.65 | Node: CTG001 - PM | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4851
4 | 1852 | 4852 | 0300804007 | Region III (Central Luzon) | Bataan | Dinalupihan | Colo | 14.848 | 120.4125 | R | 3814 | 3.6 | 1059 | 318 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 0.08 | Tier 2B: Moderate GIDA Inclusion | 69.25 | 69.25 | 33.31 | 51.28 | C - Line within 0.5 km; node over 1 km | 1.63 | 0.07 | Line: Path Measure | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4852
4 | 1853 | 4853 | 0301420008 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Poblacion | 14.8124 | 121.0456 | R | 2376 | 3.5 | 679 | 204 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.56 | 0.31 | Tier 2B: Moderate GIDA Inclusion | 62.74 | 62.74 | 39.82 | 51.28 | D - Other node or line within 3 km | 1.56 | 1.58 | Node: SJD001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4853
4 | 1854 | 4854 | 0405647039 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Lita | 14.0518 | 121.613 | R | 3641 | 3.8 | 958 | 287 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.76 | 3.45 | Tier 2B: Moderate GIDA Inclusion | 62.42 | 62.42 | 40.14 | 51.28 | E - Nearest node or line 3-5 km | 3.76 | 3.42 | Line: LILIW TO LUCENA AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4854
4 | 1855 | 4855 | 0403410031 | Region IV-A (CALABARZON) | Laguna | Liliw | Oples | 14.1343 | 121.4016 | R | 1606 | 3.3 | 487 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 1.51 | Tier 2B: Moderate GIDA Inclusion | 61.98 | 61.98 | 40.58 | 51.28 | D - Other node or line within 3 km | 1.52 | 1.49 | Line: AE NGL001 TO SPO001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4855
4 | 1856 | 4856 | 0105517001 | Region I (Ilocos Region) | Pangasinan | Calasiao | Ambonao | 16.0264 | 120.3695 | U | 6934 | 3.6 | 1926 | 578 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.35 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 63.28 | 63.28 | 39.25 | 51.27 | D - Other node or line within 3 km | 2.35 | 0.97 | Line: CALASIAO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4856
4 | 1857 | 4857 | 0103314012 | Region I (Ilocos Region) | La Union | City of San Fernando | Biday | 16.6167 | 120.3323 | U | 4436 | 3.7 | 1199 | 360 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.13 | 1.62 | Tier 2B: Moderate GIDA Inclusion | 61.39 | 61.39 | 41.15 | 51.27 | D - Other node or line within 3 km | 2.13 | 1.61 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4857
4 | 1858 | 4858 | 0203104001 | Region II (Cagayan Valley) | Isabela | Benito Soliven | Andabuen | 16.8679 | 121.9721 | R | 2548 | 3.8 | 671 | 201 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.03 | 20.85 | Tier 2B: Moderate GIDA Inclusion | 53.05 | 53.05 | 49.48 | 51.27 | F - Nearest node and line over 5 km | 13.03 | 20.85 | Node: BLI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4858
4 | 1859 | 4859 | 0401019008 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 3 | 14.1032 | 120.6766 | U | 1153 | 3.6 | 320 | 96 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.83 | 0.69 | Tier 1B: High GIDA Priority | 40.96 | 40.96 | 61.58 | 51.27 | D - Other node or line within 3 km | 5.83 | 0.68 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4859
4 | 1860 | 4860 | 1003506019 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Mabuhay | 7.7902 | 123.7138 | R | 508 | 4.2 | 121 | 36 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 22.88 | 11.11 | Tier 1B: High GIDA Priority | 32.28 | 32.28 | 70.27 | 51.27 | F - Nearest node and line over 5 km | 22.88 | 11.09 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4860
4 | 1861 | 4861 | 1380606241 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 634 | 13.6193 | 121.4202 | U | 960 | 2.88 | 333 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.67 | 18.9 | Tier 1B: High GIDA Priority | 31.07 | 31.07 | 71.47 | 51.27 | F - Nearest node and line over 5 km | 8.67 | 22.57 | Node: SJB003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4861
4 | 1862 | 4862 | 0401008016 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 1 | 13.8459 | 120.6323 | R | 4186 | 3.6 | 1163 | 349 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 69.1 | 69.1 | 33.41 | 51.26 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.05 | Line: BALAYAN - CALATAGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4862
4 | 1863 | 4863 | 0102816011 | Region I (Ilocos Region) | Ilocos Norte | Paoay | Nagbacalan | 18.1144 | 120.5239 | R | 3243 | 3.7 | 876 | 263 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.11 | 4.87 | Tier 2B: Moderate GIDA Inclusion | 64.17 | 64.17 | 38.34 | 51.26 | E - Nearest node or line 3-5 km | 7.11 | 4.78 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4863
4 | 1864 | 4864 | 0103317007 | Region I (Ilocos Region) | La Union | Santo Tomas | Casantaan | 16.2606 | 120.3961 | R | 2421 | 3.7 | 654 | 196 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.56 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 63.82 | 63.82 | 38.7 | 51.26 | D - Other node or line within 3 km | 3.56 | 0.5 | Line: SANTO TOMAS | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4864
4 | 1865 | 4865 | 0405634001 | Region IV-A (CALABARZON) | Quezon | Pitogo | Amontay | 13.8303 | 122.1018 | R | 945 | 3.8 | 249 | 75 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.9 | 0.03 | Tier 2B: Moderate GIDA Inclusion | 54.91 | 54.91 | 47.6 | 51.26 | C - Line within 0.5 km; node over 1 km | 1.9 | 0.03 | Line: AE UNQ001 TO CDQ001 | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4865
4 | 1866 | 4866 | 0103301002 | Region I (Ilocos Region) | La Union | Agoo | Balawarte | 16.3198 | 120.3408 | R | 1922 | 3.7 | 519 | 156 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.99 | 2.83 | Tier 2B: Moderate GIDA Inclusion | 52.87 | 52.87 | 49.64 | 51.26 | D - Other node or line within 3 km | 2.99 | 2.83 | Line: AGOO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4866
4 | 1867 | 4867 | 1907004013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Sukah-Bulan | 4.9217 | 119.7931 | R | 1945 | 5.8 | 335 | 100 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 999 | 999 | Tier 1B: High GIDA Priority | 37.11 | 37.11 | 65.41 | 51.26 | F - Nearest node and line over 5 km | 335.44 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4867
4 | 1868 | 4868 | 0304914009 | Region III (Central Luzon) | Nueva Ecija | Licab | Santa Maria | 15.5243 | 120.7935 | R | 4738 | 3.5 | 1354 | 406 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.2 | 3.55 | Tier 2B: Moderate GIDA Inclusion | 67.95 | 67.95 | 34.56 | 51.25 | E - Nearest node or line 3-5 km | 4.2 | 3.55 | Line: 38,161m. | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4868
4 | 1869 | 4869 | 0702232006 | Region VII (Central Visayas) | Cebu | Minglanilla | Guindaruhan | 10.2674 | 123.7568 | R | 3969 | 3.8 | 1044 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.88 | 3.93 | Tier 2B: Moderate GIDA Inclusion | 64.98 | 64.98 | 37.52 | 51.25 | E - Nearest node or line 3-5 km | 4.62 | 3.93 | Line: CEBU - TOLEDO | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4869
4 | 1870 | 4870 | 0105526028 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Salay | 16.0794 | 120.3977 | U | 5931 | 3.6 | 1648 | 494 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 63.95 | 63.95 | 38.55 | 51.25 | D - Other node or line within 3 km | 1.38 | 0.98 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4870
4 | 1871 | 4871 | 0304904021 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Santa Rita | 15.2323 | 120.8421 | U | 9200 | 3.5 | 2629 | 789 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.29 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 63.25 | 63.25 | 39.25 | 51.25 | C - Line within 0.5 km; node over 1 km | 4.29 | 0.04 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4871
4 | 1872 | 4872 | 1380606203 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 596 | 11.6634 | 121.6648 | U | 2467 | 4.3 | 574 | 172 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.04 | 42.33 | Tier 1B: High GIDA Priority | 31.38 | 31.38 | 71.12 | 51.25 | F - Nearest node and line over 5 km | 44.04 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4872
4 | 1873 | 4873 | 0603043023 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Cabugao Sur | 10.8417 | 122.5324 | R | 1708 | 3.8 | 449 | 135 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.61 | 0.97 | Tier 2B: Moderate GIDA Inclusion | 58.1 | 58.1 | 44.38 | 51.24 | D - Other node or line within 3 km | 1.61 | 0.94 | Line: Santa Barbara - Janiuay 18.361km | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4873
4 | 1874 | 4874 | 0601912003 | Region VI (Western Visayas) | Capiz | Pontevedra | Ameligan | 11.4942 | 122.8458 | R | 1387 | 3.8 | 365 | 110 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.23 | 1.87 | Tier 2B: Moderate GIDA Inclusion | 55.28 | 55.28 | 47.2 | 51.24 | D - Other node or line within 3 km | 2.23 | 1.87 | Line: ROXAS - SARA | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4874
4 | 1875 | 4875 | 0600609042 | Region VI (Western Visayas) | Antique | Laua-An | Virginia | 11.1289 | 122.1236 | R | 247 | 3.9 | 63 | 19 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 45.52 | 38.89 | Tier 1B: High GIDA Priority | 36.78 | 36.78 | 65.69 | 51.24 | F - Nearest node and line over 5 km | 45.52 | 38.55 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4875
4 | 1876 | 4876 | 1381100096 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 96 | 14.6096 | 120.9024 | U | 941 | 2.67 | 352 | 106 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.55 | 6.67 | Tier 1B: High GIDA Priority | 33.33 | 33.33 | 69.15 | 51.24 | F - Nearest node and line over 5 km | 6.55 | 7.16 | Node: MNL045 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4876
4 | 1877 | 4877 | 0501704001 | Region V (Bicol Region) | Camarines Sur | Bombon | San Antonio | 13.6911 | 123.2138 | R | 4362 | 4.2 | 1039 | 312 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.8 | 1.4 | Tier 2A: High Commercial ROI | 75.53 | 75.53 | 26.93 | 51.23 | D - Other node or line within 3 km | 1.8 | 1.4 | Line: EE23-HH24 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4877
4 | 1878 | 4878 | 0301421033 | Region III (Central Luzon) | Bulacan | San Miguel | Paliwasan | 15.1199 | 120.9673 | R | 3387 | 3.5 | 968 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.52 | 1.41 | Tier 2B: Moderate GIDA Inclusion | 69.15 | 69.15 | 33.3 | 51.23 | D - Other node or line within 3 km | 1.52 | 1.42 | Line: Untitled Path | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4878
4 | 1879 | 4879 | 0307106012 | Region III (Central Luzon) | Zambales | Masinloc | Taltal | 15.5745 | 119.9476 | R | 5041 | 3.8 | 1327 | 398 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.3 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 66.78 | 66.78 | 35.68 | 51.23 | C - Line within 0.5 km; node over 1 km | 4.3 | 0.32 | Line: MASINLOC MUNICIPALITY | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4879
4 | 1880 | 4880 | 1705205041 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Pachoca | 13.3779 | 121.1957 | R | 3966 | 3.9 | 1017 | 305 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.64 | 3.09 | Tier 2B: Moderate GIDA Inclusion | 64.34 | 64.34 | 38.12 | 51.23 | E - Nearest node or line 3-5 km | 3.64 | 3.09 | Line: AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4880
4 | 1881 | 4881 | 0301418018 | Region III (Central Luzon) | Bulacan | Pulilan | Paltao | 14.9201 | 120.8472 | U | 6749 | 3.5 | 1928 | 578 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.02 | 1.97 | Tier 2B: Moderate GIDA Inclusion | 63.77 | 63.77 | 38.69 | 51.23 | D - Other node or line within 3 km | 2.02 | 1.97 | Line: 24 CORE (3X8) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4881
4 | 1882 | 4882 | 0304928030 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Luna | 15.4248 | 120.9695 | R | 2032 | 3.5 | 581 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.36 | 0.37 | Tier 2B: Moderate GIDA Inclusion | 62.33 | 62.33 | 40.13 | 51.23 | C - Line within 0.5 km; node over 1 km | 4.08 | 0.37 | Line: Untitled Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4882
4 | 1883 | 4883 | 0102805010 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Bil-loca | 18.0886 | 120.5678 | R | 2822 | 3.7 | 763 | 229 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.94 | 0.23 | Tier 2B: Moderate GIDA Inclusion | 61.91 | 61.91 | 40.55 | 51.23 | C - Line within 0.5 km; node over 1 km | 3.94 | 0.04 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4883
4 | 1884 | 4884 | 0403417038 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Palina | 14.1075 | 121.3957 | R | 1685 | 3.3 | 511 | 153 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 60.12 | 60.12 | 42.35 | 51.23 | A - Node within 0.5 km | 0.47 | 0.21 | Line: SAN PABLO - LUCBAN AERIAL | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4884
4 | 1885 | 4885 | 0600403014 | Region VI (Western Visayas) | Aklan | Banga | Mambog | 11.6153 | 122.3228 | R | 2065 | 3.9 | 529 | 159 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.62 | 2.62 | Tier 2B: Moderate GIDA Inclusion | 54.91 | 54.91 | 47.56 | 51.23 | D - Other node or line within 3 km | 2.62 | 2.6 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4885
4 | 1886 | 4886 | 1908706017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Upper Taviran | 17.2541 | 122.2281 | R | 4543 | 4.3 | 1057 | 317 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 49.46 | 49.46 | 52.99 | 51.23 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4886
4 | 1887 | 4887 | 0405802008 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Jose | 14.6925 | 121.3 | U | 122171 | 3.6 | 33936 | 10181 | Band n50 (1.5 GHz, 100 MHz TDD) | 11 | 1 | 7.35 | 14.86 | Tier 1B: High GIDA Priority | 42.22 | 42.22 | 60.24 | 51.23 | F - Nearest node and line over 5 km | 7.35 | 14.73 | Node: ANR009 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4887
4 | 1888 | 4888 | 1404401006 | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | Lias Kanluran | 17.0839 | 121.1433 | R | 311 | 3.7 | 84 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 13.99 | 10.8 | Tier 1B: High GIDA Priority | 38.49 | 38.49 | 63.97 | 51.23 | F - Nearest node and line over 5 km | 13.99 | 10.73 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4888
4 | 1889 | 4889 | 1906617008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Kutah Parang | 5.705 | 120.8564 | R | 1056 | 6 | 176 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 189.91 | 189.9 | Tier 1B: High GIDA Priority | 33.01 | 33.01 | 69.44 | 51.23 | F - Nearest node and line over 5 km | 189.91 | 999999 | Node: ZCZ001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4889
4 | 1890 | 4890 | 1380612010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 842 | 13.3259 | 123.0316 | U | 2831 | 4.88 | 580 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 19.62 | 19.7 | Tier 1B: High GIDA Priority | 31.56 | 31.56 | 70.9 | 51.23 | F - Nearest node and line over 5 km | 19.62 | 19.61 | Line: PASACAO CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4890
4 | 1891 | 4891 | 1004320002 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Linangkayan | 8.4115 | 124.2918 | R | 3118 | 3.9 | 799 | 240 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.17 | Tier 2A: High Commercial ROI | 70.86 | 70.86 | 31.58 | 51.22 | C - Line within 0.5 km; node over 1 km | 1.36 | 0.13 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4891
4 | 1892 | 4892 | 0305415024 | Region III (Central Luzon) | Pampanga | Porac | Pio | 15.0837 | 120.5499 | U | 19317 | 4 | 4829 | 1449 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 2.31 | 0.41 | Tier 2A: High Commercial ROI | 70.14 | 70.14 | 32.31 | 51.22 | C - Line within 0.5 km; node over 1 km | 2.31 | 0.06 | Line: 24 CORE (3X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4892
4 | 1893 | 4893 | 1004320005 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Maputi | 8.4477 | 124.293 | R | 3099 | 3.9 | 795 | 238 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.82 | 0.11 | Tier 2B: Moderate GIDA Inclusion | 69.92 | 69.92 | 32.52 | 51.22 | C - Line within 0.5 km; node over 1 km | 1.82 | 0.07 | Line: CDO - ILIGAN | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4893
4 | 1894 | 4894 | 0103314030 | Region I (Ilocos Region) | La Union | City of San Fernando | Lingsat | 16.6377 | 120.3125 | U | 7553 | 3.7 | 2041 | 612 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.84 | 0.07 | Tier 2B: Moderate GIDA Inclusion | 61.87 | 61.87 | 40.58 | 51.22 | C - Line within 0.5 km; node over 1 km | 3.84 | 0.06 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4894
4 | 1895 | 4895 | 1705204002 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Balatasan | 12.2957 | 121.3823 | R | 2462 | 3.9 | 631 | 189 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.81 | 5.19 | Tier 2B: Moderate GIDA Inclusion | 53.86 | 53.86 | 48.58 | 51.22 | F - Nearest node and line over 5 km | 5.81 | 5.12 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4895
4 | 1896 | 4896 | 0600417007 | Region VI (Western Visayas) | Aklan | Tangalan | Napatag | 11.7644 | 122.2372 | R | 297 | 3.9 | 76 | 23 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 8.15 | 0.16 | Tier 2B: Moderate GIDA Inclusion | 50.3 | 50.3 | 52.14 | 51.22 | F - Nearest node and line over 5 km | 8.15 | 14.26 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4896
4 | 1897 | 4897 | 0402108030 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Arnaldo Pob. | 14.3361 | 120.917 | R | 734 | 3.4 | 216 | 65 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.92 | 4.72 | Tier 1B: High GIDA Priority | 44.59 | 44.59 | 57.86 | 51.22 | D - Other node or line within 3 km | 2.92 | 4.88 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4897
4 | 1898 | 4898 | 1907010020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Sapaat | 17.2558 | 122.2299 | R | 861 | 5.8 | 148 | 44 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 28.42 | 28.42 | 74.02 | 51.22 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4898
4 | 1899 | 4899 | 0203113025 | Region II (Cagayan Valley) | Isabela | Gamu | Upi | 17.0693 | 121.8597 | U | 5347 | 3.8 | 1407 | 422 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.05 | 0.26 | Tier 2B: Moderate GIDA Inclusion | 68.33 | 68.33 | 34.1 | 51.21 | C - Line within 0.5 km; node over 1 km | 1.05 | 0.25 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4899
4 | 1900 | 4900 | 1705213005 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Lumangbayan | 13.4179 | 121.0336 | R | 2611 | 3.9 | 669 | 201 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.47 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 65.87 | 65.87 | 36.55 | 51.21 | C - Line within 0.5 km; node over 1 km | 2.47 | 0.13 | Line: MINDORO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4900
4 | 1901 | 4901 | 0603037027 | Region VI (Western Visayas) | Iloilo | Pototan | Jamabalud | 10.8896 | 122.6171 | R | 3095 | 3.8 | 814 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.41 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 65.05 | 65.05 | 37.37 | 51.21 | D - Other node or line within 3 km | 2.41 | 0.62 | Line: ROXAS - ILOILO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4901
4 | 1902 | 4902 | 0301419028 | Region III (Central Luzon) | Bulacan | San Ildefonso | San Juan | 15.0833 | 120.9393 | U | 5212 | 3.5 | 1489 | 447 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.06 | Tier 2B: Moderate GIDA Inclusion | 63.97 | 63.97 | 38.45 | 51.21 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.05 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4902
4 | 1903 | 4903 | 0102815013 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Poblacion 2 | 18.5646 | 120.7878 | U | 3308 | 3.7 | 894 | 268 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.68 | 0.22 | Tier 2B: Moderate GIDA Inclusion | 62.67 | 62.67 | 39.74 | 51.21 | C - Line within 0.5 km; node over 1 km | 3.68 | 0.22 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4903
4 | 1904 | 4904 | 0103320005 | Region I (Ilocos Region) | La Union | Tubao | Francia West | 16.3466 | 120.4107 | R | 1859 | 3.7 | 502 | 151 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.78 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 62.11 | 62.11 | 40.31 | 51.21 | C - Line within 0.5 km; node over 1 km | 1.78 | 0.42 | Line: TUBAO | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4904
4 | 1905 | 4905 | 0102918007 | Region I (Ilocos Region) | Ilocos Sur | San Esteban | San Nicolas | 17.3203 | 120.4435 | R | 1093 | 3.8 | 288 | 86 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.43 | 0.33 | Tier 2B: Moderate GIDA Inclusion | 56.85 | 56.85 | 45.57 | 51.21 | C - Line within 0.5 km; node over 1 km | 1.43 | 0.22 | Line: SEGMENT 2 (CANDON - VIGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4905
4 | 1906 | 4906 | 0401012001 | Region IV-A (CALABARZON) | Batangas | Lemery | Anak-Dagat | 13.9325 | 120.8904 | R | 1756 | 3.6 | 488 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.89 | 2.45 | Tier 2B: Moderate GIDA Inclusion | 50.07 | 50.07 | 52.35 | 51.21 | D - Other node or line within 3 km | 4.89 | 2.45 | Line: UG NSB001 TO BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4906
4 | 1907 | 4907 | 0203104023 | Region II (Cagayan Valley) | Isabela | Benito Soliven | Sinipit | 16.8771 | 121.9475 | R | 501 | 3.8 | 132 | 40 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.05 | 18.37 | Tier 1B: High GIDA Priority | 39.29 | 39.29 | 63.13 | 51.21 | F - Nearest node and line over 5 km | 12.05 | 18.37 | Node: BLI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4907
4 | 1908 | 4908 | 0802607008 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Osmeña | 11.2539 | 125.5115 | R | 239 | 3.9 | 61 | 18 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.95 | 53.87 | Tier 1B: High GIDA Priority | 36.72 | 36.72 | 65.7 | 51.21 | F - Nearest node and line over 5 km | 54.95 | 999999 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4908
4 | 1909 | 4909 | 0402106015 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Jose | 14.3366 | 120.9302 | U | 12554 | 3.4 | 3692 | 1108 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.85 | 4.62 | Tier 2B: Moderate GIDA Inclusion | 65.77 | 65.77 | 36.64 | 51.2 | D - Other node or line within 3 km | 1.85 | 4.58 | Node: DMC006 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4909
4 | 1910 | 4910 | 0301417002 | Region III (Central Luzon) | Bulacan | Plaridel | Bagong Silang | 14.8678 | 120.8799 | R | 4429 | 3.5 | 1265 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.39 | 2.04 | Tier 2B: Moderate GIDA Inclusion | 63.03 | 63.03 | 39.38 | 51.2 | D - Other node or line within 3 km | 4.39 | 2.03 | Line: 16 CORE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4910
4 | 1911 | 4911 | 0405802011 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Bagong Nayon | 14.6297 | 121.1677 | U | 47008 | 3.6 | 13058 | 3917 | Band n50 (1.5 GHz, 100 MHz TDD) | 4 | 1 | 1.01 | 0.84 | Tier 2B: Moderate GIDA Inclusion | 61.26 | 61.26 | 41.14 | 51.2 | D - Other node or line within 3 km | 1.01 | 0.74 | Line: Aerial 24C | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4911
4 | 1912 | 4912 | 1908706003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Dadtumog | 17.2541 | 122.2281 | R | 4486 | 4.3 | 1043 | 313 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.3 | 34.2 | Tier 2B: Moderate GIDA Inclusion | 49.42 | 49.42 | 52.97 | 51.2 | F - Nearest node and line over 5 km | 29.3 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4912
4 | 1913 | 4913 | 0205008013 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Biruk | 16.0969 | 121.1963 | R | 1366 | 3.8 | 359 | 108 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.86 | 26.33 | Tier 1B: High GIDA Priority | 45.18 | 45.18 | 57.23 | 51.2 | F - Nearest node and line over 5 km | 7.86 | 26.32 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4913
4 | 1914 | 4914 | 0506206002 | Region V (Bicol Region) | Sorsogon | Castilla | Bagalayag | 12.9393 | 123.8769 | R | 640 | 4 | 160 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.37 | 4.89 | Tier 1B: High GIDA Priority | 44.03 | 44.03 | 58.37 | 51.2 | E - Nearest node or line 3-5 km | 5.37 | 4.88 | Line: FOC-7,512m | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4914
4 | 1915 | 4915 | 0306911002 | Region III (Central Luzon) | Tarlac | Pura | Buenavista | 15.6295 | 120.6731 | R | 3239 | 3.9 | 831 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.46 | 2.45 | Tier 2B: Moderate GIDA Inclusion | 66.41 | 66.41 | 35.97 | 51.19 | D - Other node or line within 3 km | 2.46 | 2.45 | Line: (GRT 393) Gerona to Pura 6433mtrs. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4915
4 | 1916 | 4916 | 0304911022 | Region III (Central Luzon) | Nueva Ecija | Guimba | Cavite | 15.6783 | 120.7711 | R | 4435 | 3.5 | 1267 | 380 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.3 | 2.57 | Tier 2B: Moderate GIDA Inclusion | 65.34 | 65.34 | 37.03 | 51.19 | D - Other node or line within 3 km | 2.3 | 2.27 | Line: 38,161m. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4916
4 | 1917 | 4917 | 0105526010 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Embarcadero | 16.0724 | 120.4163 | R | 2740 | 3.6 | 761 | 228 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.59 | 1.37 | Tier 2B: Moderate GIDA Inclusion | 64.85 | 64.85 | 37.53 | 51.19 | D - Other node or line within 3 km | 1.59 | 1.33 | Line: MANGALDAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4917
4 | 1918 | 4918 | 0401005112 | Region IV-A (CALABARZON) | Batangas | Batangas City | Talumpok Kanluran | 13.7337 | 121.1364 | R | 2986 | 3.6 | 829 | 249 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.86 | 7.58 | Tier 2B: Moderate GIDA Inclusion | 64.56 | 64.56 | 37.82 | 51.19 | B - Node 0.5-1 km | 0.86 | 7.58 | Node: BCY007-PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 4918
4 | 1919 | 4919 | 0403405060 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Uwisan | 14.2377 | 121.1721 | R | 3257 | 3.3 | 987 | 296 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.26 | 2.39 | Tier 2B: Moderate GIDA Inclusion | 63.04 | 63.04 | 39.34 | 51.19 | D - Other node or line within 3 km | 3.26 | 2.38 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4919
4 | 1920 | 4920 | 0402108014 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Javalera | 14.2564 | 120.9162 | U | 6597 | 3.4 | 1940 | 582 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.25 | 3.91 | Tier 2B: Moderate GIDA Inclusion | 57.5 | 57.5 | 44.88 | 51.19 | E - Nearest node or line 3-5 km | 4.25 | 3.91 | Line: TRECE MARTIRES | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4920
4 | 1921 | 4921 | 0304926020 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Ferdinand E. Marcos Pob. | 15.7856 | 120.9832 | U | 1689 | 3.5 | 483 | 145 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.11 | 0.42 | Tier 2B: Moderate GIDA Inclusion | 50.72 | 50.72 | 51.65 | 51.19 | C - Line within 0.5 km; node over 1 km | 1.11 | 0.4 | Line: SEGMENT 17 (ZARAGOSA - SAN JOSE) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4921
4 | 1922 | 4922 | 0405647056 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Isidro Zone IV | 14.0446 | 121.5692 | R | 679 | 3.8 | 179 | 54 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.5 | 0.44 | Tier 2B: Moderate GIDA Inclusion | 46.42 | 46.42 | 55.97 | 51.19 | C - Line within 0.5 km; node over 1 km | 3.5 | 0.44 | Line: LILIW - LUCENA | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4922
4 | 1923 | 4923 | 1906611014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Latih | 17.2554 | 122.2294 | U | 9441 | 6 | 1574 | 472 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.5 | 34.37 | Tier 1B: High GIDA Priority | 43.47 | 43.47 | 58.9 | 51.19 | F - Nearest node and line over 5 km | 29.5 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4923
4 | 1924 | 4924 | 1400114007 | Cordillera Administrative Region (CAR) | Abra | Luba | Nagbukel-Tuquipa | 17.3293 | 120.6595 | R | 543 | 3.8 | 143 | 43 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 16.87 | 12.14 | Tier 1B: High GIDA Priority | 37.27 | 37.27 | 65.11 | 51.19 | F - Nearest node and line over 5 km | 16.87 | 12.03 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4924
4 | 1925 | 4925 | 0806012019 | Region VIII (Eastern Visayas) | Samar | Motiong | Inalad | 11.8203 | 125.0367 | R | 728 | 4.1 | 178 | 53 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 64.68 | 67.66 | Tier 1B: High GIDA Priority | 37.16 | 37.16 | 65.23 | 51.19 | F - Nearest node and line over 5 km | 64.68 | 999999 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4925
4 | 1926 | 4926 | 1380601083 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 83 | 13.2896 | 122.5817 | U | 1658 | 4.48 | 370 | 111 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 9.24 | 30.86 | Tier 1B: High GIDA Priority | 31.38 | 31.38 | 71 | 51.19 | F - Nearest node and line over 5 km | 9.24 | 30.86 | Node: SFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4926
4 | 1927 | 4927 | 0105539023 | Region I (Ilocos Region) | Pangasinan | Santa Maria | San Vicente | 15.9873 | 120.7081 | R | 4140 | 3.6 | 1150 | 345 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.65 | 0.65 | Tier 2A: High Commercial ROI | 75.82 | 75.82 | 26.53 | 51.18 | B - Node 0.5-1 km | 0.65 | 0.65 | Node: SRP001 - PM | Survey short node lateral; confirm port/fiber capacity, access and route. | 4927
4 | 1928 | 4928 | 0504111021 | Region V (Bicol Region) | Masbate | City of Masbate | Malinta | 12.3757 | 123.6287 | R | 4661 | 4.1 | 1137 | 341 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 0.06 | Tier 2A: High Commercial ROI | 71.43 | 71.43 | 30.93 | 51.18 | D - Other node or line within 3 km | 2.39 | 2.23 | Line: MASBATE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4928
4 | 1929 | 4929 | 0402115031 | Region IV-A (CALABARZON) | Cavite | Naic | Timalan Balsahan | 14.3308 | 120.8013 | U | 19137 | 3.4 | 5629 | 1689 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 1.38 | 1.45 | Tier 2A: High Commercial ROI | 70.24 | 70.24 | 32.12 | 51.18 | D - Other node or line within 3 km | 1.38 | 1.45 | Node: NCC003 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4929
4 | 1930 | 4930 | 0203120012 | Region II (Cagayan Valley) | Isabela | Naguilian | Palattao | 17.0044 | 121.8259 | R | 2714 | 3.8 | 714 | 214 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.14 | 0.04 | Tier 2B: Moderate GIDA Inclusion | 68.87 | 68.87 | 33.48 | 51.18 | C - Line within 0.5 km; node over 1 km | 1.14 | 0.04 | Line: SEGMENT 11 (CAUAYAN - ILAGAN) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4930
4 | 1931 | 4931 | 0105526007 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bateng | 16.0626 | 120.4085 | R | 2912 | 3.6 | 809 | 243 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.89 | 0.51 | Tier 2B: Moderate GIDA Inclusion | 67.46 | 67.46 | 34.91 | 51.18 | B - Node 0.5-1 km | 0.89 | 0.51 | Line: MANGALDAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 4931
4 | 1932 | 4932 | 0301409022 | Region III (Central Luzon) | Bulacan | Hagonoy | Santa Monica | 14.8391 | 120.7378 | U | 8538 | 3.5 | 2439 | 732 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.47 | 2.55 | Tier 2B: Moderate GIDA Inclusion | 62.72 | 62.72 | 39.65 | 51.18 | D - Other node or line within 3 km | 1.47 | 7.36 | Node: HGB001 - TYPE 3 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4932
4 | 1933 | 4933 | 0403414010 | Region IV-A (CALABARZON) | Laguna | Mabitac | Maligaya | 14.4264 | 121.4315 | R | 362 | 3.3 | 110 | 33 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.64 | 1.49 | Tier 2B: Moderate GIDA Inclusion | 53.84 | 53.84 | 48.53 | 51.18 | B - Node 0.5-1 km | 0.64 | 1.48 | Node: MCL001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4933
4 | 1934 | 4934 | 0102820021 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Silvestre | 18.139 | 120.5868 | R | 870 | 3.7 | 235 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.55 | 0.25 | Tier 2B: Moderate GIDA Inclusion | 48 | 48 | 54.35 | 51.18 | C - Line within 0.5 km; node over 1 km | 3.55 | 0.25 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4934
4 | 1935 | 4935 | 1402703005 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Bokiawan | 16.8122 | 121.0733 | R | 436 | 3.9 | 112 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.91 | 2.8 | Tier 2B: Moderate GIDA Inclusion | 46.49 | 46.49 | 55.87 | 51.18 | D - Other node or line within 3 km | 3.91 | 2.79 | Line: LAGAWE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4935
4 | 1936 | 4936 | 1906612074 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Tonglabah | 17.2556 | 122.2297 | R | 1423 | 6 | 237 | 71 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.53 | 34.4 | Tier 1B: High GIDA Priority | 30.78 | 30.78 | 71.58 | 51.18 | F - Nearest node and line over 5 km | 29.53 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4936
4 | 1937 | 4937 | 1004303003 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Baukbauk Pob. | 8.9874 | 124.8463 | R | 2911 | 3.9 | 746 | 224 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.9 | 1.84 | Tier 2B: Moderate GIDA Inclusion | 68.68 | 68.68 | 33.66 | 51.17 | D - Other node or line within 3 km | 1.9 | 1.84 | Line: CDO - BUENAVISTA via GINGOOG | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4937
4 | 1938 | 4938 | 0604525006 | Region VI (Western Visayas) | Negros Occidental | San Enrique | Poblacion | 10.4127 | 122.8525 | U | 7663 | 3.7 | 2071 | 621 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.75 | 0.14 | Tier 2B: Moderate GIDA Inclusion | 68.32 | 68.32 | 34.01 | 51.17 | C - Line within 0.5 km; node over 1 km | 4.75 | 0.13 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4938
4 | 1939 | 4939 | 0403405031 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Maunong | 14.1691 | 121.1539 | R | 4818 | 3.3 | 1460 | 438 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.24 | 1.77 | Tier 2B: Moderate GIDA Inclusion | 68.03 | 68.03 | 34.32 | 51.17 | D - Other node or line within 3 km | 3.24 | 1.77 | Line: AE LBL001-STB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4939
4 | 1940 | 4940 | 0301403018 | Region III (Central Luzon) | Bulacan | Baliuag | San Roque | 14.997 | 120.8915 | R | 4147 | 3.5 | 1185 | 356 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.11 | 0.13 | Tier 2B: Moderate GIDA Inclusion | 67.55 | 67.55 | 34.79 | 51.17 | C - Line within 0.5 km; node over 1 km | 3.11 | 0.13 | Line: SanLuis-Candaba Path | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4940
4 | 1941 | 4941 | 0307102019 | Region III (Central Luzon) | Zambales | Cabangan | San Isidro | 15.1689 | 120.0455 | R | 2434 | 3.8 | 641 | 192 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.21 | 0.88 | Tier 2B: Moderate GIDA Inclusion | 66.76 | 66.76 | 35.57 | 51.17 | D - Other node or line within 3 km | 1.21 | 0.88 | Line: BOTOLAN - CABANGAN | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4941
4 | 1942 | 4942 | 0600411007 | Region VI (Western Visayas) | Aklan | Makato | Cajilo | 11.7222 | 122.2957 | R | 2061 | 3.9 | 528 | 158 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.73 | 1.26 | Tier 2B: Moderate GIDA Inclusion | 65.94 | 65.94 | 36.39 | 51.17 | B - Node 0.5-1 km | 0.73 | 6.9 | Node: MOK001 - BP | Survey short node lateral; confirm port/fiber capacity, access and route. | 4942
4 | 1943 | 4943 | 0301410056 | Region III (Central Luzon) | Bulacan | City of Malolos | Cofradia | 14.8422 | 120.8316 | U | 4817 | 3.5 | 1376 | 413 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.09 | 0.49 | Tier 2B: Moderate GIDA Inclusion | 61.99 | 61.99 | 40.35 | 51.17 | C - Line within 0.5 km; node over 1 km | 2.09 | 0.48 | Line: 48 CORE (6X8) | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4943
4 | 1944 | 4944 | 0306904005 | Region III (Central Luzon) | Tarlac | Capas | Cutcut 2nd | 15.3113 | 120.5249 | U | 8568 | 3.9 | 2197 | 659 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.39 | 2.69 | Tier 2B: Moderate GIDA Inclusion | 60.55 | 60.55 | 41.8 | 51.17 | D - Other node or line within 3 km | 2.39 | 2.52 | Node: BBT002 - TYPE 4A | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4944
4 | 1945 | 4945 | 0305403036 | Region III (Central Luzon) | Pampanga | Arayat | Kaledian | 15.1691 | 120.7966 | U | 6106 | 4 | 1526 | 458 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4 | 0.27 | Tier 2B: Moderate GIDA Inclusion | 60.15 | 60.15 | 42.2 | 51.17 | C - Line within 0.5 km; node over 1 km | 4 | 0.27 | Line: 48 CORE | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4945
4 | 1946 | 4946 | 0305412013 | Region III (Central Luzon) | Pampanga | Masantol | Nigui | 14.8271 | 120.6822 | R | 2660 | 4 | 665 | 200 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.56 | 7.64 | Tier 2B: Moderate GIDA Inclusion | 53.85 | 53.85 | 48.49 | 51.17 | F - Nearest node and line over 5 km | 7.56 | 12.68 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4946
4 | 1947 | 4947 | 1705311013 | MIMAROPA Region | Palawan | Dumaran | Santa Teresita | 10.5021 | 119.6523 | R | 3771 | 3.9 | 967 | 290 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 21.55 | 28.07 | Tier 2B: Moderate GIDA Inclusion | 52.65 | 52.65 | 49.69 | 51.17 | F - Nearest node and line over 5 km | 21.55 | 28.06 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4947
4 | 1948 | 4948 | 1380601168 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 168 | 13.4268 | 121.1051 | U | 1154 | 4.15 | 278 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 7.57 | 7.04 | Tier 1B: High GIDA Priority | 30.98 | 30.98 | 71.35 | 51.17 | F - Nearest node and line over 5 km | 7.57 | 7.04 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4948
4 | 1949 | 4949 | 0504111024 | Region V (Bicol Region) | Masbate | City of Masbate | Nursery | 12.3639 | 123.6276 | U | 12680 | 4.1 | 3093 | 928 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.36 | 0.4 | Tier 2A: High Commercial ROI | 70.51 | 70.51 | 31.81 | 51.16 | D - Other node or line within 3 km | 1.36 | 1.28 | Line: MASBATE | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4949
4 | 1950 | 4950 | 0205014009 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Norte | 16.5828 | 121.1891 | R | 3059 | 3.8 | 805 | 242 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.19 | 5.77 | Tier 2B: Moderate GIDA Inclusion | 69.82 | 69.82 | 32.5 | 51.16 | A - Node within 0.5 km | 0.19 | 5.52 | Node: VLV001 - BP | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4950
4 | 1951 | 4951 | 1102403007 | Region XI (Davao Region) | Davao del Sur | City of Digos | Dawis | 6.7293 | 125.3649 | U | 6025 | 3.4 | 1772 | 532 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.98 | 0.48 | Tier 2B: Moderate GIDA Inclusion | 66.71 | 66.71 | 35.61 | 51.16 | B - Node 0.5-1 km | 0.98 | 0.4 | Line: DAVAO CITY - GENSAN | Survey short node lateral; confirm port/fiber capacity, access and route. | 4951
4 | 1952 | 4952 | 0305415002 | Region III (Central Luzon) | Pampanga | Porac | Babo Sacan | 15.0683 | 120.5428 | U | 6277 | 4 | 1569 | 471 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.47 | 0.17 | Tier 2B: Moderate GIDA Inclusion | 65.46 | 65.46 | 36.85 | 51.16 | A - Node within 0.5 km | 0.47 | 0.16 | Line: 48 CORE (4X12) | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4952
4 | 1953 | 4953 | 0600404002 | Region VI (Western Visayas) | Aklan | Batan | Angas | 11.534 | 122.5181 | R | 1601 | 3.9 | 411 | 123 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.43 | 1.6 | Tier 2B: Moderate GIDA Inclusion | 59.24 | 59.24 | 43.09 | 51.16 | D - Other node or line within 3 km | 3.43 | 1.6 | Line: IVISAN - KALIBO | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4953
4 | 1954 | 4954 | 1206313031 | Region XII (SOCCSKSARGEN) | South Cotabato | Surallah | Upper Sepaka | 6.3914 | 124.6537 | R | 4005 | 3.6 | 1112 | 334 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 33.23 | 22.87 | Tier 2B: Moderate GIDA Inclusion | 52.4 | 52.4 | 49.91 | 51.16 | F - Nearest node and line over 5 km | 33.23 | 22.87 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4954
4 | 1955 | 4955 | 1001305015 | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Sayawan | 8.3772 | 125.003 | R | 1682 | 3.8 | 443 | 133 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.14 | 2.63 | Tier 2B: Moderate GIDA Inclusion | 51.62 | 51.62 | 50.7 | 51.16 | D - Other node or line within 3 km | 3.14 | 2.48 | Line: CAGAYAN DE ORO - MALAYBALAY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4955
4 | 1956 | 4956 | 1404403007 | Cordillera Administrative Region (CAR) | Mountain Province | Besao | Gueday | 17.1192 | 120.8684 | R | 589 | 3.7 | 159 | 48 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.17 | 5.16 | Tier 2B: Moderate GIDA Inclusion | 46.18 | 46.18 | 56.13 | 51.16 | F - Nearest node and line over 5 km | 5.17 | 5.16 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4956
4 | 1957 | 4957 | 0403404009 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Mamatid | 14.2446 | 121.3008 | U | 66959 | 3.3 | 20291 | 6087 | Band n50 (1.5 GHz, 100 MHz TDD) | 7 | 1 | 6.54 | 6.68 | Tier 1B: High GIDA Priority | 42.68 | 42.68 | 59.65 | 51.16 | F - Nearest node and line over 5 km | 6.54 | 6.66 | Node: VTL001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4957
4 | 1958 | 4958 | 1903620045 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Rangiran | 17.2486 | 122.2166 | R | 862 | 5.7 | 151 | 45 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 27.97 | 32.85 | Tier 1B: High GIDA Priority | 33.16 | 33.16 | 69.15 | 51.16 | F - Nearest node and line over 5 km | 27.97 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4958
4 | 1959 | 4959 | 1380606243 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 636 | 11.734 | 121.7227 | U | 2025 | 3.43 | 591 | 177 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 34.02 | 32.4 | Tier 1B: High GIDA Priority | 31.82 | 31.82 | 70.49 | 51.16 | F - Nearest node and line over 5 km | 34.02 | 999999 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4959
4 | 1960 | 4960 | 1380601034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 34 | 13.0171 | 120.7038 | U | 1930 | 4.8 | 402 | 121 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 57.03 | 55.14 | Tier 1B: High GIDA Priority | 26.93 | 26.93 | 75.38 | 51.16 | F - Nearest node and line over 5 km | 57.03 | 999999 | Node: BCM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4960
4 | 1961 | 4961 | 0102802050 | Region I (Ilocos Region) | Ilocos Norte | Bacarra | Tambidao | 18.2577 | 120.6326 | R | 825 | 3.7 | 223 | 67 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.61 | 1.45 | Tier 2B: Moderate GIDA Inclusion | 48.85 | 48.85 | 53.46 | 51.15 | D - Other node or line within 3 km | 2.61 | 1.26 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4961
4 | 1962 | 4962 | 0806001025 | Region VIII (Eastern Visayas) | Samar | Almagro | Imelda | 11.9326 | 124.2985 | R | 469 | 4.1 | 114 | 34 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 42.85 | 75.74 | Tier 1B: High GIDA Priority | 36.82 | 36.82 | 65.47 | 51.15 | F - Nearest node and line over 5 km | 42.85 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4962
4 | 1963 | 4963 | 1380612007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 839 | 12.6408 | 122.8792 | U | 2052 | 3.54 | 580 | 174 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 58.23 | 61.92 | Tier 1B: High GIDA Priority | 31.56 | 31.56 | 70.74 | 51.15 | F - Nearest node and line over 5 km | 58.23 | 999999 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4963
4 | 1964 | 4964 | 1102509022 | Region XI (Davao Region) | Davao Oriental | City of Mati | Sainz | 6.9602 | 126.2244 | U | 10624 | 3.6 | 2951 | 885 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.63 | 1.09 | Tier 2B: Moderate GIDA Inclusion | 68.78 | 68.78 | 33.5 | 51.14 | D - Other node or line within 3 km | 1.63 | 1.02 | Line: PANTUKAN - MATI SEGMENT 5 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4964
4 | 1965 | 4965 | 0401003001 | Region IV-A (CALABARZON) | Batangas | Balayan | Baclaran | 13.9298 | 120.7721 | R | 2753 | 3.6 | 765 | 230 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.04 | 1.16 | Tier 2B: Moderate GIDA Inclusion | 64.29 | 64.29 | 37.99 | 51.14 | D - Other node or line within 3 km | 2.04 | 1.16 | Line: AE BYB001 TO LYB001 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4965
4 | 1966 | 4966 | 0205701022 | Region II (Cagayan Valley) | Quirino | Aglipay | Pinaripad Norte | 16.4783 | 121.5996 | R | 1084 | 3.9 | 278 | 83 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.25 | 0.28 | Tier 2B: Moderate GIDA Inclusion | 54.38 | 54.38 | 47.9 | 51.14 | A - Node within 0.5 km | 0.25 | 0.26 | Node: AYQ001 - PM | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4966
4 | 1967 | 4967 | 1903620037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Paigoay | 17.2516 | 122.2405 | R | 883 | 5.7 | 155 | 46 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 30.16 | 35.39 | Tier 1B: High GIDA Priority | 33.05 | 33.05 | 69.23 | 51.14 | F - Nearest node and line over 5 km | 30.16 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4967
4 | 1968 | 4968 | 0304902022 | Region III (Central Luzon) | Nueva Ecija | Bongabon | San Roque | 15.628 | 121.163 | R | 3022 | 3.5 | 863 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.82 | 1.74 | Tier 2B: Moderate GIDA Inclusion | 67.26 | 67.26 | 34.99 | 51.13 | D - Other node or line within 3 km | 1.82 | 1.71 | Line: Proposed AE F1-6 | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4968
4 | 1969 | 4969 | 0506213050 | Region V (Bicol Region) | Sorsogon | Pilar | San Rafael | 12.9074 | 123.6955 | R | 3378 | 4 | 844 | 253 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.22 | 10.68 | Tier 2B: Moderate GIDA Inclusion | 60.19 | 60.19 | 42.06 | 51.13 | E - Nearest node or line 3-5 km | 4.22 | 10.68 | Node: PRS001 - TYPE 3 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4969
4 | 1970 | 4970 | 0702201005 | Region VII (Central Visayas) | Cebu | Alcantara | Manga | 9.9532 | 123.4863 | R | 2149 | 3.8 | 566 | 170 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.04 | 9.15 | Tier 2B: Moderate GIDA Inclusion | 53.88 | 53.88 | 48.37 | 51.13 | F - Nearest node and line over 5 km | 10.04 | 9.1 | Line: Segment 8 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4970
4 | 1971 | 4971 | 0201519013 | Region II (Cagayan Valley) | Cagayan | Peñablanca | Lapi | 17.7136 | 121.8968 | R | 3170 | 3.9 | 813 | 244 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 12.36 | 15.5 | Tier 2B: Moderate GIDA Inclusion | 52.89 | 52.89 | 49.36 | 51.13 | F - Nearest node and line over 5 km | 12.36 | 15.5 | Node: PÑC001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4971
4 | 1972 | 4972 | 0803738051 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Don Felipe Larrazabal | 11.0112 | 124.6042 | U | 1669 | 3.8 | 439 | 132 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.38 | 0.38 | Tier 2B: Moderate GIDA Inclusion | 52.72 | 52.72 | 49.54 | 51.13 | A - Node within 0.5 km | 0.38 | 0.37 | Line: ORMOC ADDITIONAL LINK | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4972
4 | 1973 | 4973 | 0506204006 | Region V (Bicol Region) | Sorsogon | Bulusan | Lalud | 12.7007 | 124.1326 | R | 547 | 4 | 137 | 41 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 6.28 | 4.86 | Tier 2B: Moderate GIDA Inclusion | 47.99 | 47.99 | 54.27 | 51.13 | F - Nearest node and line over 5 km | 6.28 | 5.37 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4973
4 | 1974 | 4974 | 0803707022 | Region VIII (Eastern Visayas) | Leyte | Bato | Plaridel | 10.353 | 124.8937 | R | 444 | 3.8 | 117 | 35 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.37 | 7.82 | Tier 1B: High GIDA Priority | 44.35 | 44.35 | 57.91 | 51.13 | F - Nearest node and line over 5 km | 25.47 | 11.72 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4974
4 | 1975 | 4975 | 1705104009 | MIMAROPA Region | Occidental Mindoro | Lubang | Sorville | 13.8427 | 120.1205 | R | 124 | 3.9 | 32 | 10 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 55.01 | 54.86 | Tier 1B: High GIDA Priority | 34.63 | 34.63 | 67.64 | 51.13 | F - Nearest node and line over 5 km | 55.01 | 999999 | Node: CTG001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4975
4 | 1976 | 4976 | 1908806022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Salendab | 17.2552 | 122.2293 | R | 1199 | 4.7 | 255 | 76 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.48 | 34.35 | Tier 1B: High GIDA Priority | 31.22 | 31.22 | 71.03 | 51.13 | F - Nearest node and line over 5 km | 29.48 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4976
4 | 1977 | 4977 | 1907010011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tabunan Likud Sikubong | 17.2558 | 122.2298 | R | 813 | 5.8 | 140 | 42 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.56 | 34.43 | Tier 1B: High GIDA Priority | 28.25 | 28.25 | 74.02 | 51.13 | F - Nearest node and line over 5 km | 29.56 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4977
4 | 1978 | 4978 | 0304902001 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Antipolo | 15.6178 | 121.189 | R | 5105 | 3.5 | 1459 | 438 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 4.6 | 4.33 | Tier 2B: Moderate GIDA Inclusion | 63.45 | 63.45 | 38.79 | 51.12 | E - Nearest node or line 3-5 km | 4.6 | 4.32 | Line: Proposed AE F1-6 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4978
4 | 1979 | 4979 | 1903626037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tamparan | Poblacion I | 13.4985 | 123.0433 | R | 1087 | 5.7 | 191 | 57 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.72 | 0.71 | Tier 2B: Moderate GIDA Inclusion | 54.31 | 54.31 | 47.93 | 51.12 | B - Node 0.5-1 km | 0.72 | 0.69 | Line: PASACAO CLS | Survey short node lateral; confirm port/fiber capacity, access and route. | 4979
4 | 1980 | 4980 | 0304902026 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Social | 15.6276 | 121.1406 | R | 867 | 3.5 | 248 | 74 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.75 | 0.75 | Tier 2B: Moderate GIDA Inclusion | 52.54 | 52.54 | 49.7 | 51.12 | B - Node 0.5-1 km | 0.75 | 0.65 | Line: Proposed AE F1-6 | Survey short node lateral; confirm port/fiber capacity, access and route. | 4980
4 | 1981 | 4981 | 1908822005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Kuya | 17.2551 | 122.2291 | U | 6770 | 4.7 | 1440 | 432 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 29.45 | 34.33 | Tier 1B: High GIDA Priority | 43.08 | 43.08 | 59.15 | 51.12 | F - Nearest node and line over 5 km | 29.45 | 999999 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4981
4 | 1982 | 4982 | 0405622070 | Region IV-A (CALABARZON) | Quezon | Lopez | San Rafael | 13.8483 | 122.2239 | R | 323 | 3.8 | 85 | 26 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.99 | 4.41 | Tier 1B: High GIDA Priority | 39.66 | 39.66 | 62.58 | 51.12 | E - Nearest node or line 3-5 km | 5.99 | 4.4 | Line: LCQ001 TO LZQ001 | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4982
4 | 1983 | 4983 | 1705307010 | MIMAROPA Region | Palawan | Busuanga | Quezon | 12.2663 | 119.9357 | R | 1192 | 3.9 | 306 | 92 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 14.98 | 122.41 | Tier 1B: High GIDA Priority | 38.57 | 38.57 | 63.67 | 51.12 | F - Nearest node and line over 5 km | 14.98 | 999999 | Node: BSW001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4983
4 | 1984 | 4984 | 0806001004 | Region VIII (Eastern Visayas) | Samar | Almagro | Biasong I | 11.9255 | 124.2908 | R | 511 | 4.1 | 125 | 38 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 41.9 | 74.59 | Tier 1B: High GIDA Priority | 36.84 | 36.84 | 65.4 | 51.12 | F - Nearest node and line over 5 km | 41.9 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4984
4 | 1985 | 4985 | 1380606031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 425 | 12.4926 | 122.8651 | U | 1792 | 2.98 | 602 | 181 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 54.44 | 61.97 | Tier 1B: High GIDA Priority | 32.17 | 32.17 | 70.06 | 51.12 | F - Nearest node and line over 5 km | 54.44 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4985
4 | 1986 | 4986 | 1380614084 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 891 | 12.5508 | 121.4366 | U | 931 | 4.43 | 210 | 63 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 3.35 | 3.05 | Tier 1B: High GIDA Priority | 31.8 | 31.8 | 70.43 | 51.12 | E - Nearest node or line 3-5 km | 3.35 | 3 | Line: AE | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4986
4 | 1987 | 4987 | 1380611036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 821 | 12.0416 | 121.0526 | U | 2474 | 4.42 | 560 | 168 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 31.55 | 30.83 | Tier 1B: High GIDA Priority | 31.04 | 31.04 | 71.21 | 51.12 | F - Nearest node and line over 5 km | 31.55 | 30.71 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4987
4 | 1988 | 4988 | 1380607003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 639 | 13.111 | 121.5151 | U | 475 | 2.61 | 182 | 55 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 5.27 | 8.87 | Tier 1B: High GIDA Priority | 29.48 | 29.48 | 72.76 | 51.12 | F - Nearest node and line over 5 km | 5.27 | 8.87 | Node: PYM002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4988
4 | 1989 | 4989 | 1380601094 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 94 | 12.344 | 122.8297 | U | 2117 | 4.36 | 486 | 146 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 53.14 | 62.21 | Tier 1B: High GIDA Priority | 29.11 | 29.11 | 73.12 | 51.12 | F - Nearest node and line over 5 km | 53.14 | 999999 | Node: MNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4989
4 | 1990 | 4990 | 0307110011 | Region III (Central Luzon) | Zambales | San Felipe | Sto. Niño | 15.0819 | 120.0797 | R | 5134 | 3.8 | 1351 | 405 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.66 | 1.45 | Tier 2A: High Commercial ROI | 73.11 | 73.11 | 29.11 | 51.11 | D - Other node or line within 3 km | 2.66 | 1.45 | Line: SAN FELIPE MUNICIPALITY | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4990
4 | 1991 | 4991 | 0403427005 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Cabooan | 14.4598 | 121.4269 | R | 2172 | 3.3 | 658 | 197 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 1.73 | Tier 2B: Moderate GIDA Inclusion | 66.87 | 66.87 | 35.35 | 51.11 | D - Other node or line within 3 km | 1.38 | 1.73 | Node: SML001 - BP | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4991
4 | 1992 | 4992 | 1102508018 | Region XI (Davao Region) | Davao Oriental | Manay | Lambog | 7.228 | 126.4478 | R | 836 | 3.6 | 232 | 70 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 39.77 | 38.46 | Tier 1B: High GIDA Priority | 33.04 | 33.04 | 69.18 | 51.11 | F - Nearest node and line over 5 km | 39.77 | 999999 | Node: MID001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4992
4 | 1993 | 4993 | 1380612024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 856 | 12.3311 | 120.9703 | U | 1733 | 4.16 | 417 | 125 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 10.48 | 10.12 | Tier 1B: High GIDA Priority | 31.34 | 31.34 | 70.88 | 51.11 | F - Nearest node and line over 5 km | 10.48 | 10.12 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4993
4 | 1994 | 4994 | 0401010006 | Region IV-A (CALABARZON) | Batangas | Ibaan | Coliat | 13.8149 | 121.1279 | R | 4448 | 3.6 | 1236 | 371 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 0.14 | 0.11 | Tier 2A: High Commercial ROI | 72.46 | 72.46 | 29.75 | 51.1 | A - Node within 0.5 km | 0.14 | 0.1 | Line: BATANGAS - SAN JUAN | First survey: confirm node handoff, spare capacity and short route; co-location not established. | 4994
4 | 1995 | 4995 | 0304914005 | Region III (Central Luzon) | Nueva Ecija | Licab | San Casimiro | 15.5519 | 120.7822 | R | 3500 | 3.5 | 1000 | 300 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 2.95 | 2.83 | Tier 2B: Moderate GIDA Inclusion | 68.17 | 68.17 | 34.03 | 51.1 | D - Other node or line within 3 km | 2.95 | 2.83 | Line: 38,161m. | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4995
4 | 1996 | 4996 | 0500503035 | Region V (Bicol Region) | Albay | Daraga | Maroroy | 13.1504 | 123.724 | U | 5443 | 4.1 | 1328 | 398 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.38 | 0.43 | Tier 2B: Moderate GIDA Inclusion | 66.01 | 66.01 | 36.2 | 51.1 | C - Line within 0.5 km; node over 1 km | 1.38 | 0.38 | Line: LEGAZP - TIWI AERIAL | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4996
4 | 1997 | 4997 | 0403404007 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Gulod | 14.2251 | 121.2838 | U | 18870 | 3.3 | 5718 | 1715 | Band n50 (1.5 GHz, 100 MHz TDD) | 2 | 1 | 4.92 | 5.05 | Tier 2B: Moderate GIDA Inclusion | 62.44 | 62.44 | 39.76 | 51.1 | E - Nearest node or line 3-5 km | 4.92 | 5.05 | Node: BAY001 - BP | Review before committing: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4997
4 | 1998 | 4998 | 0304904006 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Maligaya | 15.2492 | 120.8599 | U | 3018 | 3.5 | 862 | 259 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.67 | 0.2 | Tier 2B: Moderate GIDA Inclusion | 60 | 60 | 42.19 | 51.1 | C - Line within 0.5 km; node over 1 km | 1.67 | 0.2 | Line: SANTA ROSA TO ARAYAT | Locate authorized closure or handhole and confirm splicing/capacity; nearby cable alone is insufficient. | 4998
4 | 1999 | 4999 | 0403413013 | Region IV-A (CALABARZON) | Laguna | Lumban | Segunda Parang | 14.289 | 121.4524 | R | 1314 | 3.3 | 398 | 119 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 1.18 | 0.62 | Tier 2B: Moderate GIDA Inclusion | 55.63 | 55.63 | 46.57 | 51.1 | D - Other node or line within 3 km | 1.18 | 0.62 | Line: SEGMENT 23 (FAMY - STA CRUZ) | Design route options: compare actual node lateral with approved line tap; measure path/crossings. | 4999
4 | 2000 | 5000 | 0806001026 | Region VIII (Eastern Visayas) | Samar | Almagro | Biasong II | 11.9315 | 124.3128 | R | 340 | 4.1 | 83 | 25 | Band n50 (1.5 GHz, 100 MHz TDD) | 1 | 1 | 44.36 | 75.04 | Tier 1B: High GIDA Priority | 36.8 | 36.8 | 65.4 | 51.1 | F - Nearest node and line over 5 km | 44.36 | 999999 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 5000

## Provincial Summary
5G FWA Barangay Rollout Plan — Combined Hybrid Dual Optimization (Provincial Summary)
Region | Province | Total Sites | Phase 1 Sites | Total Population | Target Subs | Peak BTS | Node <=1km (A+B) | Line <=500m (C) | Remote >3km (E+F)
National Capital Region (NCR) | First District (Not a Province) | 345 | 25 | 1182889 | 89145 | 355 | 6 | 11 | 272
Region IV-A (CALABARZON) | Laguna | 284 | 78 | 2731034 | 248184 | 417 | 88 | 54 | 35
Region III (Central Luzon) | Bulacan | 275 | 39 | 2296565 | 196853 | 354 | 67 | 60 | 13
National Capital Region (NCR) | Fourth District (Not a Province) | 253 | 77 | 2552727 | 217081 | 405 | 98 | 52 | 37
Region IV-A (CALABARZON) | Cavite | 242 | 118 | 1940936 | 171260 | 316 | 61 | 24 | 15
National Capital Region (NCR) | Second District (Not a Province) | 230 | 143 | 4853933 | 393957 | 516 | 123 | 62 | 0
Region IV-A (CALABARZON) | Batangas | 179 | 20 | 613183 | 51095 | 187 | 30 | 28 | 32
Region IV-A (CALABARZON) | Quezon | 125 | 16 | 253195 | 19988 | 127 | 18 | 21 | 47
Region III (Central Luzon) | Nueva Ecija | 124 | 4 | 610296 | 52251 | 130 | 34 | 42 | 12
Region VIII (Eastern Visayas) | Samar | 117 | 3 | 63069 | 4616 | 117 | 0 | 0 | 117
Region IV-A (CALABARZON) | Rizal | 110 | 36 | 2644298 | 220360 | 284 | 43 | 30 | 6
Region III (Central Luzon) | Bataan | 108 | 20 | 545739 | 45478 | 117 | 29 | 40 | 2
Region VII (Central Visayas) | Cebu | 106 | 16 | 824829 | 65126 | 130 | 28 | 43 | 10
Region II (Cagayan Valley) | Cagayan | 84 | 24 | 217937 | 16770 | 84 | 5 | 21 | 26
Region III (Central Luzon) | Pampanga | 84 | 4 | 574172 | 43063 | 96 | 16 | 28 | 10
Region VI (Western Visayas) | Aklan | 81 | 34 | 215139 | 16550 | 83 | 10 | 8 | 43
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | 79 | 1 | 177631 | 9114 | 79 | 0 | 0 | 79
MIMAROPA Region | Palawan | 78 | 9 | 198150 | 15344 | 79 | 3 | 2 | 70
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | 77 | 17 | 412865 | 28855 | 80 | 0 | 0 | 77
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | 71 | 3 | 175560 | 9081 | 71 | 0 | 1 | 69
Region I (Ilocos Region) | Pangasinan | 70 | 4 | 309404 | 25786 | 71 | 18 | 21 | 7
National Capital Region (NCR) | Third District (Not a Province) | 69 | 54 | 1305903 | 111167 | 151 | 42 | 14 | 0
Region X (Northern Mindanao) | Lanao del Norte | 67 | 3 | 86851 | 6201 | 67 | 0 | 4 | 54
Region I (Ilocos Region) | Ilocos Norte | 65 | 25 | 99206 | 8042 | 65 | 12 | 11 | 17
Region I (Ilocos Region) | Ilocos Sur | 63 | 20 | 75909 | 5989 | 63 | 3 | 7 | 23
Region III (Central Luzon) | Tarlac | 63 | 4 | 435910 | 33533 | 72 | 22 | 25 | 1
Region II (Cagayan Valley) | Isabela | 62 | 11 | 182370 | 14393 | 63 | 11 | 11 | 24
Region X (Northern Mindanao) | Misamis Oriental | 60 | 7 | 273647 | 21050 | 64 | 19 | 16 | 6
Region I (Ilocos Region) | La Union | 59 | 4 | 164110 | 13304 | 59 | 13 | 13 | 14
Cordillera Administrative Region (CAR) | Kalinga | 57 | 22 | 77401 | 5507 | 58 | 4 | 7 | 34
Region VI (Western Visayas) | Iloilo | 57 | 2 | 138521 | 10939 | 58 | 7 | 6 | 26
Region II (Cagayan Valley) | Nueva Vizcaya | 54 | 15 | 92108 | 7272 | 54 | 8 | 2 | 36
Cordillera Administrative Region (CAR) | Benguet | 53 | 16 | 218206 | 18707 | 56 | 11 | 9 | 20
Region VI (Western Visayas) | Capiz | 53 | 3 | 94309 | 7445 | 53 | 3 | 10 | 28
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | 53 | 0 | 53540 | 2819 | 53 | 1 | 0 | 49
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | 48 | 4 | 162681 | 10381 | 48 | 0 | 0 | 46
Region VI (Western Visayas) | Negros Occidental | 43 | 2 | 205852 | 16690 | 47 | 11 | 8 | 14
Region V (Bicol Region) | Masbate | 43 | 2 | 93572 | 6847 | 43 | 2 | 1 | 36
Cordillera Administrative Region (CAR) | Abra | 42 | 4 | 22873 | 1805 | 42 | 2 | 0 | 35
Region V (Bicol Region) | Camarines Sur | 39 | 3 | 60100 | 4294 | 39 | 6 | 5 | 20
Region VI (Western Visayas) | Antique | 37 | 0 | 40329 | 3108 | 37 | 3 | 2 | 29
Region X (Northern Mindanao) | Bukidnon | 36 | 0 | 189105 | 14928 | 43 | 5 | 4 | 18
Region XI (Davao Region) | Davao del Norte | 35 | 11 | 448021 | 36329 | 57 | 4 | 8 | 11
Region XI (Davao Region) | Davao de Oro | 35 | 8 | 118664 | 9622 | 37 | 1 | 2 | 28
Region XI (Davao Region) | Davao Oriental | 35 | 4 | 161221 | 13435 | 39 | 2 | 0 | 29
Region IX (Zamboanga Peninsula) | Zamboanga del Sur | 34 | 0 | 31824 | 2447 | 34 | 0 | 2 | 27
Region V (Bicol Region) | Albay | 33 | 10 | 69888 | 5113 | 33 | 3 | 8 | 14
Region V (Bicol Region) | Sorsogon | 33 | 7 | 69899 | 5243 | 34 | 8 | 0 | 15
Cordillera Administrative Region (CAR) | Ifugao | 33 | 9 | 33398 | 2569 | 33 | 2 | 1 | 19
Region XI (Davao Region) | Davao Occidental | 32 | 9 | 93579 | 7735 | 32 | 0 | 0 | 32
Region VIII (Eastern Visayas) | Leyte | 31 | 2 | 58654 | 4630 | 31 | 8 | 5 | 17
Cordillera Administrative Region (CAR) | Apayao | 28 | 4 | 22700 | 1620 | 28 | 2 | 2 | 21
Region VIII (Eastern Visayas) | Eastern Samar | 28 | 0 | 14226 | 1096 | 28 | 0 | 0 | 28
Region XI (Davao Region) | Davao del Sur | 27 | 4 | 190058 | 16773 | 33 | 9 | 1 | 9
Region III (Central Luzon) | Zambales | 26 | 3 | 142356 | 11240 | 28 | 4 | 10 | 4
Region II (Cagayan Valley) | Quirino | 26 | 9 | 34569 | 2659 | 26 | 5 | 4 | 16
Region VIII (Eastern Visayas) | Northern Samar | 25 | 0 | 13479 | 943 | 25 | 0 | 0 | 25
Cordillera Administrative Region (CAR) | Mountain Province | 24 | 8 | 31651 | 2565 | 24 | 1 | 5 | 11
MIMAROPA Region | Oriental Mindoro | 22 | 1 | 83883 | 6452 | 22 | 2 | 4 | 8
Region VII (Central Visayas) | Negros Oriental | 22 | 0 | 76884 | 6073 | 22 | 3 | 4 | 12
Region VIII (Eastern Visayas) | Southern Leyte | 20 | 2 | 20521 | 1501 | 20 | 1 | 2 | 17
Region XII (SOCCSKSARGEN) | Sarangani | 19 | 6 | 74021 | 5694 | 19 | 0 | 0 | 19
Region III (Central Luzon) | Aurora | 18 | 5 | 19759 | 1560 | 18 | 3 | 3 | 10
Region V (Bicol Region) | Camarines Norte | 17 | 1 | 52041 | 3904 | 17 | 4 | 1 | 9
Region XIII (Caraga) | Surigao del Sur | 15 | 0 | 45574 | 3334 | 16 | 2 | 2 | 8
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | 15 | 0 | 42418 | 2494 | 15 | 0 | 0 | 15
Region XIII (Caraga) | Agusan del Sur | 14 | 0 | 82837 | 6372 | 18 | 7 | 1 | 4
Region XII (SOCCSKSARGEN) | Cotabato | 13 | 1 | 71685 | 5660 | 14 | 1 | 2 | 9
Region VII (Central Visayas) | Bohol | 13 | 1 | 30169 | 2263 | 13 | 1 | 1 | 6
Region II (Cagayan Valley) | Batanes | 11 | 3 | 11436 | 1143 | 11 | 0 | 0 | 11
Region V (Bicol Region) | Catanduanes | 11 | 0 | 8066 | 576 | 11 | 0 | 0 | 11
Region IX (Zamboanga Peninsula) | Zamboanga del Norte | 10 | 0 | 15091 | 1257 | 10 | 0 | 0 | 10
MIMAROPA Region | Occidental Mindoro | 9 | 0 | 36697 | 2839 | 10 | 0 | 1 | 7
Region XII (SOCCSKSARGEN) | South Cotabato | 9 | 0 | 116570 | 9716 | 16 | 2 | 0 | 7
Region X (Northern Mindanao) | Misamis Occidental | 7 | 0 | 3397 | 262 | 7 | 0 | 0 | 7
Region XII (SOCCSKSARGEN) | Sultan Kudarat | 6 | 0 | 16832 | 1327 | 6 | 0 | 0 | 6
Region XIII (Caraga) | Dinagat Islands | 4 | 0 | 4541 | 358 | 4 | 0 | 0 | 4
Region XIII (Caraga) | Surigao del Norte | 3 | 0 | 2265 | 166 | 3 | 0 | 0 | 2
Region XIII (Caraga) | Agusan del Norte | 3 | 0 | 11955 | 875 | 3 | 1 | 1 | 0
MIMAROPA Region | Marinduque | 2 | 0 | 1464 | 116 | 2 | 0 | 0 | 2
Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | 2 | 0 | 3157 | 225 | 2 | 0 | 0 | 2
Region VI (Western Visayas) | Guimaras | 2 | 0 | 5228 | 412 | 2 | 0 | 0 | 2
Region IX (Zamboanga Peninsula) | City of Isabela (Not a Province) | 1 | 0 | 1811 | 124 | 1 | 0 | 0 | 1
Region X (Northern Mindanao) | Camiguin | 1 | 0 | 896 | 69 | 1 | 0 | 0 | 1
MIMAROPA Region | Romblon | 1 | 0 | 1249 | 101 | 1 | 0 | 0 | 1