## Master Register (Q001 - Q100)
COMCLARK NETWORK & TECHNOLOGY CORP. / TELTECH 5G FWA NATIONWIDE TURNKEY TENDER
MASTER CLARIFICATIONS REGISTER — CONSOLIDATED INQUIRIES & OFFICIAL RESPONSES (Q001 – Q100)
Item No. | Question ID | Domain Classification | Document Reference | Section / Chapter Reference | Prospective Bidder Inquiry | Comclark / TelTech Official Response | Procurement Ruling Status
1 | Q001 | Other Business Matters | 01_RFP_5G_FWA_Master_Tender_Document | 5. TENDER SUBMISSION STRUCTURE & COMPLIANCE REQUIREMENTS | Kindly provide this Form A. | CONFIRMED & PROVIDED. The official Form A template (Bid Submission Letter & Consortium Structure) is provided as Attachment 1 to Bid Bulletin No. 1 and is available for download directly in the online RFP portal (Document Library Tab 1). | Binding Ruling (Bid Bulletin No. 1)
2 | Q002 | OSS & BSS Integration | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is billing considered in scope? | CLARIFICATION OF BILLING SCOPE: In Phase 1, real-time Convergent Charging (CCS/CHF via 3GPP Nchf/Diameter Ro) for prepaid FWA balance management, session cutoff, and quota tracking is the mandatory turnkey scope. Complex postpaid cyclic invoice generation and accounts receivable (A/R) are handled by Comclark/TelTech's enterprise billing system via standard CDR/API export, or may be proposed as an optional modular add-on. | Binding Ruling (Bid Bulletin No. 1)
3 | Q003 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | the Contractor / Prospective Bidder system support many kinds of product but need help to detail your offering requirment. Such as: 1. These offerings need group management (such as family package) or not? 2. These offerings need rollover feature (such as unused data rollove to next cycle) or not? 3. These offerings should support auto upgrade (such as 599 not enough of this cycle automatical upgrade to 700 for next cycle) or not? | CLARIFICATION OF PRODUCT OFFERINGS: 1. Group Management: Optional roadmap feature; single-account per CPE is baseline for Phase 1. 2. Rollover Feature: Supported in product catalog configuration (unused high-speed data quota rolls over into the subsequent 30-day renewal cycle upon prompt re-subscription). 3. Auto-Upgrade: Speed-cap throttling (e.g. throttle to 1 Mbps upon quota exhaustion with option for customer to purchase speed-boost add-on) is the required policy, rather than forced tariff upgrade. | Binding Ruling (Bid Bulletin No. 1)
4 | Q004 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | the Contractor / Prospective Bidder system support standard 3GPP protocal and real-time balanace rating and charging process. some concerns: 1. We assume BSS will support 5G SA network only. 2. Smart quota, dynamic granted quota feature should enable or not? | CLARIFICATION OF CHARGING REQUIREMENTS: 1. Network Architecture: Confirmed 5G Standalone (SA) only. 2. Quota Management: Standard 3GPP dynamic granted quota (DCC) and threshold notification alerts (at 80% and 100% quota consumption via SMS / self-care push notification) must be enabled. | Binding Ruling (Bid Bulletin No. 1)
5 | Q005 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | the Contractor / Prospective Bidder system can open the REST API for payment. some concerns： 1. Should support Voucher recharge or not(3rd party send voucher no and PIN as example)? 2. Should consider Recharge tax or not(When feedback the message to 3rd party or notification to end-subscribers)? 3. Should consider Recharge promotion or not(When feedback the message to 3rd party or notification to end-subscribers)? | CLARIFICATION OF DIGITAL PAYMENT RECHARGE: 1. Voucher Recharge: Omnichannel digital recharge via GCash, Maya, and QR Ph is primary. Third-party electronic voucher PIN recharge is supported as an optional secondary channel. 2. Taxation: BSS catalog must support Philippine 12% Value Added Tax (VAT) calculation and display on payment confirmations and receipts. 3. Promotions: The charging system must natively support marketing promotional rules (e.g., bonus data allowances, referral credits, or promotional validity extensions). | Binding Ruling (Bid Bulletin No. 1)
6 | Q006 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | What's the FWA service scenario shall be supported by the BSS? For example: New Registration, SIM Location Locking, Address Change, Transfer Owership, Contract Lifecycle Management, CPE/WIFI Router Installment | MANDATORY FWA SERVICE SCENARIOS: The turnkey BSS/OSS must support: 1. New Customer Digital Registration & KYC. 2. Strict SIM-IMEI & Cell-ID Location Locking (binding the FWA service to the authorized installation address to prevent nomadic/mobile unauthorized usage). 3. Relocation / Address Change workflow (manual or automated cell unbinding upon authorized relocation request). 4. Transfer of Ownership & Account Termination. 5. Contract / Subscription Lifecycle Management. 6. CPE Inventory Assignment and Remote FOTA Management. | Binding Ruling (Bid Bulletin No. 1)
7 | Q007 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | What's the payment mode shall be supported by the BSS? Prepaid, Postpaid, Hybrid? If need postpaid, and hybrid, does it meant the vendor need to provide the billing, invoice relevant components? | PAYMENT MODE ARCHITECTURE: The primary business model for Phase 1 is 100% Prepaid with 30-day recurring subscription validity. Postpaid hybrid invoicing is handled via integration with Comclark/TelTech's enterprise billing platform; bidders / suppliers are only required to provide the real-time prepaid CHF/CCS engine and payment gateway connectors. | Binding Ruling (Bid Bulletin No. 1)
8 | Q008 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the listed systems, shall the new BSS integrate with ERP Finance system, DWH/BI? Is there data streaming requirement for real-time data synchronization? | ENTERPRISE INTEGRATIONS: The BSS must support standard daily accounting journal export (GL feed) to Comclark/TelTech's SAP ERP and daily CDR/event extraction to the enterprise Data Warehouse (DWH). Real-time Kafka-based event streaming is preferred for operational analytics. | Binding Ruling (Bid Bulletin No. 1)
9 | Q009 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the self-care channels, shall the vendor provide the retail portal which can be used by the in-shop agent or call center agent? | RETAIL & AGENT PORTAL SCOPE: CONFIRMED. Supplier must provide a secure, web-based Customer Service Representative (CSR) and Authorized Dealer Portal for retail store agents, partner distribution dealers, and call center hotlines to perform customer onboarding, balance lookups, and troubleshooting. | Binding Ruling (Bid Bulletin No. 1)
10 | Q010 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the CPE inventory management, shall the new BSS/OSS system manage the MSISDN and SIM card resource? | RESOURCE MANAGEMENT SCOPE: CONFIRMED. The turnkey BSS must incorporate a unified resource inventory management module for SIM cards (ICCID), MSISDNs, and CPE hardware serial numbers (IMEI / MAC). | Binding Ruling (Bid Bulletin No. 1)
11 | Q011 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Does the exisiting network have PCF (Policy Control Function)? Does the BSS need to integrate with this? | POLICY CONTROL (PCF) INTEGRATION: Under Lot 3 (5G Core Network), the supplier is delivering the turnkey 5G SA Core, which includes the Policy Control Function (PCF). The BSS will integrate directly with the supplier's supplied PCF via standard 3GPP N7 / N28 interfaces. | Binding Ruling (Bid Bulletin No. 1)
12 | Q012 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 3. RF PROPAGATION & CELL DIMENSIONING GUIDELINES | The coverage radius is too large. It is recommended that the coverage radius be 1 km in suburban areas and 1.5 km in rural areas. | CONFIRMED ACCEPTABLE. The revised planning criteria are formally adopted: - Suburban / Dense Urban: Nominal reliable cell radius of 1.0 km. - Rural / Semi-Rural: Nominal reliable cell radius of 1.5 – 2.0 km. These guidelines ensure 95% indoor/outdoor coverage reliability across Band n50 and will govern the updated link budget benchmarks in Document 05. | Binding Ruling (Bid Bulletin No. 1)
13 | Q013 | Wireless and Delivery | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3.1 Core Radio KPIs (Calculated 24/7/365 Nationwide) | In the case of multiple users, the environment is complex and the attenuation is large. It is recommended that the average cell traffic be controlled within 40 Mbps/10 MHz. | CONFIRMED ACCEPTABLE. The recommended engineering planning baseline of 40 Mbps average cell throughput per 10 MHz of spectrum (yielding ~240 Mbps average cell throughput on a 60 MHz Band n50 TDD carrier with 4:1 DL:UL frame structure) is endorsed as realistic busy-hour design criteria for multi-user FWA deployment. | Binding Ruling (Bid Bulletin No. 1)
14 | Q014 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines | 2.2 Tower Structure & Loading Audit (Co-Location Sites) | For TowerCo tower, the tower structural Loading verification usually under TowerCo Scope ( Operator provide the equipment list and loading info to TowerCo, TowerCo to provide result). 1. Please kindly suggest if we need to provide structural loading verification service or not. Or we quote this service in a seperate item. 2. If Loading Verification fail, Please suggest the next step (build new tower, or request towerco retrofit tower) Suggest: TowerCo do the structural loading verification. | STRUCTURAL LOADING RESPONSIBILITY: 1. For the 897 TowerCo co-location sites, Tower Structural Loading Verification is the responsibility of the Operator and the TowerCo under the executed Master Lease Agreement (MLA). The supplier provides equipment weights, dimensions, wind load surface area, and cable routing details. 2. If loading verification fails, the TowerCo is obligated under the MLA to perform structural retrofitting, or the Operator will reassign an alternative candidate tower from the pre-approved pool. | Binding Ruling (Bid Bulletin No. 1)
15 | Q015 | Site, civil work, and managed services | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages |  | Whats the acceptance standard and procedure for Tower, Civil and Power part? Suggest: the Contractor / Prospective Bidder can propose if needed. | ACCEPTANCE STANDARDS: Acceptance standards and checklists for Civil, Tower, and Power are detailed in Document 05 ('05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf') and Document 04 (Appendix C). Supplier's standard QA/QC procedure and handover templates are acceptable subject to Joint Technical Committee approval. | Binding Ruling (Bid Bulletin No. 1)
16 | Q016 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines 03_Appendix_B_Commercial_Proposal_BoQ_Templates | 2.3 Power Infrastructure & Utility Audit TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For New Site, the BOQ not include the commerical power application and installation (From COOP to Site). Do we need to quote this part? If the commerical power not ready, does huawei need to provide the temporary power to turn on the site? Suggest: Commerical power shall included and temporary power can consider as VO when needed. | COMMERCIAL POWER & TEMPORARY POWER: 1. Official electric cooperative (EC/DU) application fees and power connection contracts are Operator scope. 2. Turnkey on-site civil and electrical installation (service entrance, meter base, disconnect, ACPDB) is Supplier scope. 3. If commercial utility power is delayed by the power utility, the site will be provisionally accepted using temporary generator power where expedited on-air is mutually agreed, with generator runtime costs handled via established Variation Order (VO). | Binding Ruling (Bid Bulletin No. 1)
17 | Q017 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | 1. Do you have Type approved brand for Tower, Genset, Aviation light, ACPDB and other power or civil material? 2. Can you provide Typical Design drawing for Tower, Fence and foundation? Or the Contractor / Prospective Bidder to propose the solution. Suggest: the Contractor / Prospective Bidder can propose if needed. | TYPE-APPROVED BRANDS & CIVIL DESIGNS: 1. Civil and electrical materials must comply with Philippine Electrical Code (PEC), ASTM, and PNS standards (Class A hot-dip galvanized steel, NEMA 3R/4 outdoor enclosures, Schneider/ABB/Eaton breakers). 2. Typical structural and foundation drawings are provided in Document 05. Bidders may propose their type-approved standard foundation, fence, and monopole designs in their technical submission. | Binding Ruling (Bid Bulletin No. 1)
18 | Q018 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | 1. For the TowerCo site, Is it TelTech Scope to rent and negotiate with TowerCo? Suggest: For towerco site, should be TelTech's responsibility for site renting and negoitate with towerco. 2. If the site hunting fail, whats the next step? (TelTech to provide another site for hunting to swap the fail site? or cancel the site). Suggest: the Contractor / Prospective Bidder will hunt each site with 5 options, if site still failed, suggest customer change the site or provide VO for new option hunting. | SITE ACQUISITION & TOWERCO LEASE NEGOTIATION: 1. For the 897 Co-location sites, lease agreements, space reservation, and commercial negotiations with TowerCos (PhilTower, EdgePoint, EDOTCO, Unity) are strictly the Operator's responsibility under Master Lease Agreements (MLA). 2. For the 103 Greenfield sites, the supplier performs primary site hunting with up to 3 candidate parcels. If site hunting fails due to zoning, legal, or title defects, the Operator will provide a replacement candidate site without bidder penalty. | Binding Ruling (Bid Bulletin No. 1)
19 | Q019 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | the Contractor / Prospective Bidder suggest put the Genset and fuel tank in a equipment pad. no need to build shelter for genset. | GENSET INSTALLATION STANDARD: CONFIRMED ACCEPTABLE. Outdoor soundproof weatherproof canopy gensets installed directly on an elevated concrete equipment pad (without an enclosed brick/steel shelter building) are fully acceptable. | Binding Ruling (Bid Bulletin No. 1)
20 | Q020 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Is it TelTech scope for Fiber or the Contractor / Prospective Bidder need to do? | FIBER BACKHAUL RESPONSIBILITY: Comclark/TelTech provides the core optical distribution network, terrestrial fiber drop cable up to the site boundary/ODF, and Starlink satellite terminals. The supplier is responsible for optical transceivers, patchcords, and joint I&C testing from the demarcation box to the BBU. | Binding Ruling (Bid Bulletin No. 1)
21 | Q021 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | For the non-standard and special construction reuqirment, such as manul hauling, retaining wall and others, Can huawei claim seperately as VO? | VARIATION ORDER (VO) ELIGIBILITY: CONFIRMED. Non-standard civil construction conditions (such as hard rock excavation requiring pneumatic breakers/blasting, manual material hauling exceeding 500 meters across unpaved/mountainous terrain, and engineered retaining walls) are recognized as eligible for Variation Orders based on pre-agreed unit rates in Appendix B (Lot 5 BoQ). | Binding Ruling (Bid Bulletin No. 1)
22 | Q022 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For TowerCo Power part, Usually Towerco will provide AC and DC, Please suggest if the Contractor / Prospective Bidder need to provide the meter and releated power material to tap to existing power system. | TOWERCO POWER EQUIPMENT: Where TowerCo supplies regulated -48V DC power directly, supplier needs only connect to the designated DC distribution breaker. Where TowerCo provides raw AC utility power, supplier supplies the submeter, ACPDB, and surge suppression. | Binding Ruling (Bid Bulletin No. 1)
23 | Q023 | Testing / KPI | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf; 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | Section 5 SSV — Ping RTT acceptance; KPI-RAN-07 Radio Round-Trip Latency | For the 17 Starlink backhaul sites, should the RTT KPI threshold be adjusted (e.g., relaxed to <= 50 ms maximum) given the inherent LEO satellite latency? Or are these sites exempt from KPI-RAN-07? Please confirm whether a separate KPI schedule applies to satellite backhaul sites. | STARLINK SATELLITE RTT LATENCY KPI: CONFIRMED & ADOPTED. For the 17 remote/island candidate sites backhauled via Starlink LEO satellite, the Ping RTT SLA is relaxed to <= 60 ms target (<= 80 ms maximum) during SSV and cluster acceptance, reflecting satellite orbital propagation latency. | Binding Ruling (Bid Bulletin No. 1)
24 | Q024 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document | 2.3 Transmission & Backhaul Topology / App.C 3.1 KPI-RAN-07 | 1. Please provide the verified per-site fiber node/segment list (optical node ID, connection class A-D, committed bandwidth) after on-ground verification — the site list shows all Starlink-fed sites have dist-to-node > 20 km. 2. Please confirm that backhaul resources (TelTech fiber SLA, Starlink links) are Operator/third-party provided, and TelTech is responsible for their availability, bandwidth and latency. 3. Do you accept media-tiered RTT KPIs: fiber-fed sites bound by <= 30ms, while satellite-fed sites follow their link physics (e.g. <= 100ms)? 4. Please confirm backhaul outage time is excluded from KPI assessment (RAN availability, end-to-end availability, packet loss). Expected: written confirmation + per-site backhaul list. | BACKHAUL RESOURCES & SLA EXCLUSIONS: 1. Candidate site list in Document 07 provides audited fiber distance classes (Class A <= 0.5km to Class D). 2. Confirmed: Backhaul transport facilities (Comclark/TelTech terrestrial FOC and Starlink links) are Operator-provided. 3. Media-tiered RTT KPIs are formally confirmed: Fiber sites <= 30 ms maximum; Satellite sites <= 80 ms maximum. 4. Confirmed: Downtime caused by upstream third-party transmission outages or fiber cuts outside the site compound is excluded from supplier RAN availability penalty assessments. | Binding Ruling (Bid Bulletin No. 1)
25 | Q025 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Site Infrastructure & Tower Strategy | 1. Please provide TowerCo lease confirmations / ownership proofs for all co-location sites before NTP. 2. Please provide a tower-readiness schedule per site (lease signed, structural audit, access) feeding the 1,000-sites/365-day plan. 3. Do you agree to back-to-back liability — delays caused by TowerCo approval, access or structural defects are excluded from the Contractor / Prospective Bidder's schedule liability with automatic time extension? Expected: written commitment + schedule. | TOWERCO LEASE READINESS & SCHEDULE COMMITMENTS: 1. Operator will provide TowerCo Site Access Authorizations prior to Notice to Proceed (NTP) for each site batch. 2. Confirmed: Schedule milestones commence upon formal Site Handover with approved TowerCo access. Delays caused exclusively by TowerCo structural retrofit or access permit delays will receive day-for-day time extensions without liquidated damages. | Binding Ruling (Bid Bulletin No. 1)
26 | Q026 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Deployment Typology / App.C 2.1 Milestones M1-M4 | 1. Please confirm an 'Excluded Sites' mechanism — sites blocked by permits (LGU/Barangay/CAAP), land, power connection, TowerCo or coverage issues are deducted from milestone counts. 2. May Milestone-1 TSSR be submitted in phasing (first 200 sites in 45 days, then 300 sites every 30 days), given typical permitting and TowerCo access cycles in the Philippines? 3. Do you accept the 365-day milestone counted in net working days (or auto-extended by the same number of days of Operator/third-party delays)? 4. Please confirm permit fees and utility connection application costs are pass-through (CCP). Expected: written confirmation + revised milestone wording. | MILESTONES & PERMITTING CLAUSES: 1. Blocked Sites Mechanism: Sites blocked by LGU moratorium, right-of-way disputes, or power utility delays beyond 45 days will be swapped with approved reserve sites without schedule penalty. 2. Phased TSSR Submissions: Submitting TSSRs in progressive monthly batches (e.g. 150–200 sites per month) is fully acceptable. 3. Project schedule will account for approved force majeure and Operator/third-party delay extensions. 4. Official LGU building permit statutory fees and utility interconnection fees are pass-through to Operator. | Binding Ruling (Bid Bulletin No. 1)
27 | Q027 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | LOT 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | Can you accept not requiring a drone, as long as the photos can reflect the 360° surrounding environment, and AGL refer to TowerCo provided height for FWA project? | DRONE SURVEY WAIVER: CONFIRMED ACCEPTABLE. Where drone flight permits cannot be secured from CAAP or local authorities within 14 days, high-resolution 360-degree panoramic telephoto ground photography combined with verified TowerCo structural engineering drawings is accepted for TSSR approval. | Binding Ruling (Bid Bulletin No. 1)
28 | Q028 | Power system and delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE | 1. Do they have Blade requirement ? 2. Can we request room layout or site pictures if available for Lithium Battery Approval? 3. Is there existing rectifier cabinet in existing sites? 4. If SAT requirement is one per equipment or the whole quantity? 5. What is the Total actual DC power for single rectifier requipment? | POWER SYSTEM & BATTERY SPECIFICATIONS: 1. Standard 19" rack-mount modular switchmode rectifiers and 19" rack-mount 48V 100Ah LiFePO4 battery modules are required. 2. Typical site DC load is ~2.8 to 3.2 kW continuous. Sizing requirement is 12.0 kW installed capacity (4 × 3 kW modules, N+1 redundancy). 3. Site layout and equipment pad drawings are provided in Document 05. | Binding Ruling (Bid Bulletin No. 1)
29 | Q029 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | 1. According to ITU-R M.2159-0, the 1518–1525 MHz frequency band is used for maritime communications satellites. If the frequency range of the RRU includes 1512–1517 MHz, it cannot ensure a -30 dB suppression within the 1518–1523 MHz band. Therefore, please confirm whether the NTC allows the use of the 1512–1517 MHz spectrum. 2. We understand that the 1427–1457 MHz frequency band will be allocated by the NTC as spectrum for enterprises. Please consider whether TelTech intends to use the 1457–1467 MHz band. It is recommended to refer to the NTC's spectrum usage regulations to determine whether a guard band is required. Therefore, please confirm whether the NTC allows the use of the 1457–1467 MHz spectrum. | SPECTRUM PHYSICS & FILTERING (1457–1517 MHz): 1. Standard 3GPP Band n50 Category B filtering guarantees required suppression (-30 dBm/MHz) into the adjacent 1518–1525 MHz band (maritime satellite). Use of the 1457–1517 MHz band is formally authorized under NTC demonstration permit. 2. In NCR, operation is continuous 60 MHz (1457–1517 MHz); digital filtering within the RRU prevents out-of-band emissions below 1457 MHz. | Binding Ruling (Bid Bulletin No. 1)
30 | Q030 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | overall | Besides interference analysis with maritime communication satellites, suggest to carry out frequency clearance scan before commercial network deployment. | FREQUENCY CLEARANCE TEST: CONFIRMED & AGREED. Supplier and Operator RF teams will conduct joint baseline spectrum clearance sweeps prior to site commercial on-air to identify and resolve any legacy co-channel or adjacent interference. | Binding Ruling (Bid Bulletin No. 1)
31 | Q031 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | Is there Dl &UL speed requirement at near, Mid, and Far/Edge? | CONFIRMED. Phase 1 deployment is strictly 5G NR Standalone (SA) in Band n50. NSA operation is not required. | Binding Ruling (Bid Bulletin No. 1)
32 | Q032 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Currently, only n50 is planned for FWA development, and NSA networks should not be involved | CONFIRMED. Native Band n50 (1432 – 1517 MHz, 60 MHz TDD) is mandatory. Fallback sub-6 GHz bands (n1, n3, n78) are optional for the Philippine market. | Binding Ruling (Bid Bulletin No. 1)
33 | Q033 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Currently, only the n50 band is planned for FWA development. Is it mandatory for other sub-6 GHz frequency bands? | CONFIRMED ACCEPTABLE. For Indoor CPE, an integrated antenna array gain of 5.0 – 6.0 dBi across Band n50 is accepted as compliant due to favorable propagation characteristics of 1.5 GHz L-Band compared to 3.5 GHz. For Outdoor CPE, >= 12.0 dBi remains mandatory. | Binding Ruling (Bid Bulletin No. 1)
34 | Q034 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | The N50 low-frequency system does not need to rely on extremely high antenna gain to compensate for spatial attenuation as high-frequency systems do. Whether 5-6 dBi is sufficient? | CPE ETHERNET INTERFACES: - Outdoor CPE: 1x 2.5GE PoE input port + companion indoor Wi-Fi 6 router is standard. - Indoor CPE: At least 1x 2.5GE or 1x 1GE LAN port + integrated Wi-Fi 6 is acceptable for consumer FWA tiers; multi-port is preferred for SME tiers. | Binding Ruling (Bid Bulletin No. 1)
35 | Q035 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | The network port is seldom used and is mainly used for network configuration and commissioning. Can only one network port be reserved for the product? | CONFIRMED. Physical Nano-SIM (4FF) with anti-theft locking slot is mandatory for mass-market deployment. eSIM (MFF2) is an acceptable optional enhancement. | Binding Ruling (Bid Bulletin No. 1)
36 | Q036 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Can it only support the eSIM MFF2 solution? | CONFIRMED. For synchronized TDD systems, Operating Band Unwanted Emissions (OBUE) per 3GPP TS 38.104 is the primary RF compliance benchmark. Passive Intermodulation (PIM <= -150 dBc) applies to external RF components (antennas, jumpers, connectors) to avoid receiver desensitization. | Binding Ruling (Bid Bulletin No. 1)
37 | Q037 | Wireless and Delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | PIM is an indicator that is mainly concerned in FDD mode and does not need to be concerned in TDD mode. Is it necessary to change it to an OBUE (Operating Band Unwanted Emissions)indicator? | CONFIRMED. Candidate site coordinates (Lat/Long) and nominal tower heights are provided in Document 07. | Binding Ruling (Bid Bulletin No. 1)
38 | Q038 | Wireless and Delivery | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | We note that the distance from the planned site to the nearest tower ranges from 0.16 km to 1.94 km. Could the specific tower locations be provided for simulation calculations? | OSS INTEGRATION: Supplier must deliver EMS/NMS for domain element management, equipped with open northbound interfaces (REST APIs, SNMPv3, Kafka) for integration into Comclark/TelTech's enterprise monitoring umbrella (AUTIN). | Binding Ruling (Bid Bulletin No. 1)
39 | Q039 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Will a separate monitoring platform be deployed, or can it be integrated with the existing AUTIN platform? | CONFIRMED. In Phase 1, NEF (Network Exposure) and SEPP (Security Edge Protection Proxy) are treated as optional roadmap functions and can be licensed in Phase 2 when enterprise API exposure and international roaming are activated. | Binding Ruling (Bid Bulletin No. 1)
40 | Q040 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | The NEF is responsible for network capability exposure, and there are currently no commercial use cases. The SEPP is responsible for signaling security protection and topology hiding across PLMNs. Based on the experience of other projects, this function is also not mandatory. Therefore, it is recommended that the NEF and SEPP functions be treated as optional requirements or removed from the current RFP. | UPF DEPLOYMENT ARCHITECTURE: In Phase 1, 5G Core control plane and central UPF are co-deployed at the Tier-3 primary datacenter (Clark/Metro Manila). Edge UPF deployment is optional for future ultra-low-latency enterprise zones. Standard 2U, 4U, or 8U server form factors are acceptable. | Binding Ruling (Bid Bulletin No. 1)
41 | Q041 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | Please Clarify whether the UPF needs to be deployed at the edge or co-deployed with the 5G Core at the central site. If the UPF needs to be deployed at the edge, specify the number of edge UPFs. It is recommended that the UPF form be not limited.Either 2U/4U/8U is ok | CONFIRMED ACCEPTABLE. Carrier-grade server hardware with equivalent compute and throughput capabilities (including Enterprise ARM architecture (e.g. Kunpeng/Ampere) ARM architecture running certified carrier-grade Linux / Kubernetes) is fully acceptable for 5GC NFV infrastructure. | Binding Ruling (Bid Bulletin No. 1)
42 | Q042 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | or hardware with the same capabilities such as Kunpeng server（E9000H-4/8） |  | Binding Ruling (Bid Bulletin No. 1)
43 | Q043 | General Technical | 01_RFP_5G_FWA_Master_Tender_Document | General Technical Baseline | Inquiry harmonized and addressed under Round 2 comprehensive technical directives. | Clarified and incorporated into the unified baseline promulgated under Bid Bulletin No. 2. | Binding Ruling (Bid Bulletin No. 2)
44 | Q044 | General Technical | 01_RFP_5G_FWA_Master_Tender_Document | General Technical Baseline | Inquiry harmonized and addressed under Round 2 comprehensive technical directives. | Clarified and incorporated into the unified baseline promulgated under Bid Bulletin No. 2. | Binding Ruling (Bid Bulletin No. 2)
45 | Q045 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 1.2 ProgramLOT 3: CLOUD-NATIVE 5G CORE (5GC SA) & DATACENTER INFRASTRUCTURE | Please specify how much throughput is required for 1 million users in the first phase, and how much total throughput will be needed for 3 million users in the future. | For Phase 1 (1,000,000 registered subscribers / initial 300,000 active broadband households), the cloud-native 5G SA Core User Plane Function (UPF) must be dimensioned for an aggregated throughput of 300 Gbps to 500 Gbps, based on an average busy-hour throughput (ABHT) of 1.5–2.0 Mbps per active subscriber with a 15–20% peak concurrency factor. For the future 3,000,000 subscriber expansion, the 5G Core architecture must support horizontal auto-scaling of containerized UPF instances up to a total aggregated throughput of 1.5 Tbps without control plane redesign. | Binding Ruling (Bid Bulletin No. 2)
46 | Q046 | Wireless and Delivery | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | We have obtained the latest document and found that column T in the table only contains tower IDs without specific latitude and longitude coordinates. Could you provide these tower's latitude and longitude coordinates to support simulation and construction evaluation? | Confirmed. High-precision WGS84 geographic coordinates (6 decimal places) for all nearest towers have been populated in Document 07 (07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx) across Tab 'All 5,000 Sites' and Batch 1 through Batch 5. As noted, these tower coordinates constitute confidential operator assets provided strictly under the RFP Non-Disclosure Agreement (NDA) solely for RF propagation modeling, link simulation, and construction feasibility assessment. | Binding Ruling (Bid Bulletin No. 2)
47 | Q047 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | The current capability does not support the frequency range of 1512~1517 MHz. the Contractor / Prospective Bidder requires more detailed RF specifications to conduct an evaluation. It is recommended to forward the NTC's demonstration spectrum requirements to the Contractor / Prospective Bidder, including the following information: the suppression level requirements for RF signals in the 1432~1457 MHz range and the suppression level requirements for RF signals above 1517 MHz. | Clarified and Directed. In accordance with National Telecommunications Commission (NTC) Memorandum Circular No. 006-11-2025 (https://ntc.gov.ph/wp-content/uploads/2025/MEMORANDUM_CIRCULAR/006-11-2025.pdf), applicable 3GPP specifications (TS 38.104 / TS 38.141), and international radio regulations, the technical baselines, boundary conditions, and mandatory RF conformance test requirements are established as follows: 1. Operational Channel Placement & Bandwidth Efficiency: - Operational Passband: 1457.0 MHz to 1517.0 MHz (single contiguous 60.0 MHz TDD carrier, Band n50). - Center Frequency: 1487.0 MHz (aligned on the standard 100 kHz 3GPP RF reference raster). - Transmission Numerology: 162 Physical Resource Blocks (PRBs) configured at 30 kHz Subcarrier Spacing (SCS), occupying 58.32 MHz active transmission bandwidth. - Spectral Efficiency: A single 60.0 MHz carrier provides 162 PRBs (97.2% frequency utilization), capturing +5.9% higher usable capacity and eliminating carrier aggregation complexity and inter-carrier guardband loss compared to 3x 20 MHz (153 PRBs total, 91.8% utilization). 2. Upper Boundary Separation & Satellite Protection (> 1517.0 MHz): - 1.0 MHz External Guardband: The 1517.0–1518.0 MHz block is reserved as an external guardband between the carrier edge (1517.0 MHz) and the NTC allocation ceiling (1518.0 MHz). - Effective Transition Margin: Combined with the internal 3GPP channel guardband of 840 kHz (for 60 MHz @ 30 kHz SCS), the physical separation from the outermost active subcarrier (1516.16 MHz) to the sensitive satellite downlink boundary (1518.0 MHz) is 1.84 MHz. - Mobile-Satellite Service (MSS) Protection: Out-of-band emissions (OOBE) into the adjacent maritime mobile-satellite service downlink band (1518.0–1525.0 MHz) must not exceed -30 dBm/MHz at the gNodeB antenna connector, strictly compliant with ITU-R M.2159-0 / WRC-15 Resolution 223 and 3GPP TS 38.104 Category B. 3. Lower Boundary Protection for Adjacent NPN (1432.0–1457.0 MHz): - Non-Public Networks Coexistence: Per NTC MC No. 006-11-2025, 1427.0–1457.0 MHz is allocated to Non-Public Networks (NPN). Unwanted emissions in the adjacent 1432.0–1457.0 MHz block must strictly meet 3GPP TS 38.104 Category B standards with an Adjacent Channel Leakage Ratio (ACLR >= 45 dB). 4. In-Band BSS Coexistence (1452.0–1492.0 MHz): - Pursuant to Section IV of NTC MC No. 006-11-2025, deployments overlapping the 1452.0–1492.0 MHz primary Broadcasting-Satellite Service (BSS) allocation must support remote power control, electrical downtilt adjustments (eRET), and interference coordination to avoid detrimental interference to licensed satellite earth stations. 5. Mandatory RF Conformance Test Requirements in Tender Submissions: - Shortlisted RAN bidders must submit certified third-party / factory laboratory RF conformance test reports under 3GPP TS 38.141-1 (Conducted) and TS 38.141-2 (Radiated) demonstrating: (a) Spectrum Emission Mask (SEM) compliance at maximum rated conducted power (+55 dBm / 320 W conducted); (b) ACLR measured at full 100% PRB load; (c) Operating Band Unwanted Emissions (OBUE) spectral mask plots across 1517.0–1559.0 MHz (proving the <= -30 dBm/MHz limit above 1518.0 MHz); (d) Spurious emissions across out-of-band ranges; (e) Manufacturer declaration of any required power de-rating / back-off or external high-Q cavity bandpass filtering needed to meet limits at full rated power, including link budget coverage impacts. 6. Mandatory Equipment Wideband Hardware Capability: - All proposed Baseband Units (BBU), Remote Radio Units (RRU) / Active Antenna Units (AAU), and Customer Premises Equipment (CPE) RF front-ends must natively support the full 3GPP Band n50 tuning range (1432.0–1517.0 MHz, 85 MHz Instantaneous Bandwidth / IBW) in hardware, reconfigurable via software without hardware swaps or tower truck rolls. | Binding Ruling (Bid Bulletin No. 2)
48 | Q048 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | There is no ODU N50 product yet, and will take a long while for development. will we consider to launch the indoor N50 first | Confirmed. TelTech authorizes a phased CPE rollout: Bidders are permitted to offer high-performance 5G Indoor Units (IDU) with high-gain internal antennas (minimum 8–10 dBi equivalent) and external antenna port capability for initial Phase 1 deployments. Bidders must concurrently commit to a roadmap delivery for high-gain Outdoor Units (ODU, >= 12 dBi gain, IP67 weather-proofed) within 6 to 9 months of contract award. | Binding Ruling (Bid Bulletin No. 2)
49 | Q049 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is there an existing BI/reporting system? If yes, please confirm if BSS doesn't need to provide basic report anymore. | Confirmed. The BSS/OSS platform must include native, automated BI reporting dashboards capable of generating scheduled reports (daily, weekly, monthly) in CSV, XLSX, and PDF formats for all operational, revenue, provisioning, and SLA metrics. Additionally, the platform must provide open REST APIs / secure database views to enable automated data pipeline ingestion into TelTech's enterprise analytics repository. | Binding Ruling (Bid Bulletin No. 2)
50 | Q050 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is there an existing contact center? Is there a need for a separate customer ticketing system? | Confirmed. TelTech is deploying a cloud-based Contact Center as a Service (CCaaS) platform. The Bidder's BSS/CRM solution must provide standard RESTful open APIs (supporting TM Forum Open APIs including TMF621 Customer Management, TMF622 Product Ordering, and TMF632 Party Management) to integrate seamlessly with TelTech's contact center for single-pane customer service, automated CTI screen-pops, and unified trouble ticketing. | Binding Ruling (Bid Bulletin No. 2)
51 | Q051 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | How about VAS system? Does BSS need to integrate with existing SMS? | The BSS platform must include standard out-of-the-box integration capabilities (via standard SMPP v3.4 and RESTful SMS API) to interface with SMSC / SMS gateways for automated transactional messaging (one-time passwords [OTP], billing alerts, provisioning status, payment reminders, and outage notifications). Third-party SMS gateway connectivity and termination aggregators will be provided by TelTech. | Binding Ruling (Bid Bulletin No. 2)
52 | Q052 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | LOT 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | We note your confirmation that the drone survey waiver is accepted. To align execution, please confirm the following: (a) TSSR photographic evidence shall be obtained 360° panoramic photography only via target installation height from towerco. Drone survey is not required for TSSR. (b) The acceptance criterion for site photographs is that they clearly depict the 360° surrounding environment (including neighbouring structures, potential obstructions, and general terrain) at a level sufficient for line-of-sight assessment. No specific camera resolution, focal length, or equipment type is required; standard photographic equipment available to the site survey team is acceptable. | Confirmed. For sites with existing towers (Class T1–T3), drone surveys shall be conducted to capture 360° panoramic photographic sweeps at antenna mounting height (and 20m, 30m, 40m AGL) to assess line-of-sight and structural clearances. Where local aviation restrictions (CAAP no-fly zones, military airspace, or adverse local weather) prohibit drone flights, manual panoramic photography taken by qualified tower riggers from the tower mounting platform is acceptable. | Binding Ruling (Bid Bulletin No. 2)
53 | Q053 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 4. CIVIL WORKS & STRUCTURAL ENGINEERING (CLASS T4 GREENFIELD SITES) | For 103 sites, Do we need to consider elevated foundation in the commercial directly? If Yes, please confirm the required height. If No, Is it will be consider as VO. | Clarified. Equipment pad foundation design for the 103 Class T4 Greenfield Monopole sites shall be determined by the site-specific hydrological survey and historical flood levels: (1) Standard Non-Flood Zone: Standard reinforced concrete equipment plinth with elevation of 300 mm (0.30 m) above finished grade level. (2) Flood-Prone Areas (50-year flood zone history): Elevated equipment platform raised 1.0 m to 1.5 m above finished grade. Civil construction works exceeding standard 300 mm plinth height necessitated by extreme local flood conditions shall be priced per the Master Rate Card (Appendix E) as an approved scope adjustment. | Binding Ruling (Bid Bulletin No. 2)
54 | Q054 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | 1. Please suggest the refuel of fuel tank scope is under the Contractor / Prospective Bidder or not before we handover the site to TelTech (Finish acceptance). 2. If Yes, When we handover the site to TelTech, do we need to refuel the fuel tank to full. | Confirmed. Bidders are not required to provide a fully filled diesel fuel tank upon final site handover. The contractor is only responsible for supplying commissioning fuel necessary to perform the mandatory on-site load bank and generator acceptance testing (minimum 4-hour full-load burn-in). Following Provisional Acceptance Certificate (PAC), routine fuel replenishment transitions to TelTech's managed operations. | Binding Ruling (Bid Bulletin No. 2)
55 | Q055 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 2.4 Backhaul Transmission Path Survey | Do we need to provide a seperate mouting Pole for the Starlink? If yes, please speficy the size or diemension for the pole. | Confirmed. Where Starlink LEO satellite backhaul is designated for hybrid resilience, bidders shall provide a dedicated hot-dip galvanized mounting pipe (minimum 60 mm / 2.375 inch outer diameter, 2.5 mm wall thickness) with unobstructed sky visibility. For ground-based Greenfield sites, an integrated standoff arm on the equipment gantry or perimeter fence post is acceptable; for tower sites, a tower-leg standoff clamp shall be utilized. | Binding Ruling (Bid Bulletin No. 2)
56 | Q056 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 4. CIVIL WORKS & STRUCTURAL ENGINEERING (CLASS T4 GREENFIELD SITES) | Please suggest how many RRU and MW need to be consider in the monopole design. and please also provide the dimension and weight for the Antenna、RRU、MW which need to be consider in the design. | Confirmed. The Class T4 Greenfield Monopole structural design shall be calculated per NSCP 2015 (EIA/TIA-222-G) for 270 km/h wind gusts, accommodating a minimum design payload of: 6x 5G Remote Radio Units (RRUs), 1x Active Antenna Unit (AAU) or 3x directional sector antennas (approx. 2.0 m length each), up to 1.2 m² total projected windward surface area for microwave transmission antennas (equivalent to 1x 1.2m or 2x 0.6m parabolic dishes), and associated feeder cables, mounting brackets, and lightning protection rod. | Binding Ruling (Bid Bulletin No. 2)
57 | Q057 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines 03_Appendix_B_Commercial_Proposal_BoQ_Templates | 2.3 Power Infrastructure & Utility Audit TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For the New monopole sites, please suggest the AC capacity we need to apply from Coop. | Confirmed. The electrical service entrance shall be dimensioned for a 100A, 230V single-phase (or 3-phase where commercially available) service drop. The contractor's scope of work includes installation of the weatherhead, service mast, utility-grade meter base, manual transfer switch (MTS), main AC distribution panel with Class I+II surge protective devices (SPD), and grounding grid. Final electric cooperative (EC/Meralco) utility energization and monthly power billing accounts shall be arranged and paid directly by TelTech. | Binding Ruling (Bid Bulletin No. 2)
58 | Q058 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Regarding the CPE recovery rate (>= 70%), the Contractor / Prospective Bidder's 2-year warranty period allows for free replacement if any issues arise. Is such a service acceptable? The CPE recovery rate cannot be controlled. | Accepted and clarified. The >= 70% CPE Recovery Rate defined in the RFP applies strictly to churned subscriber recovery and reverse logistics (i.e. retrieving TelTech-owned CPE hardware from canceled or disconnected subscriber premises by field force teams), not OEM factory warranty returns. For defective CPE units under the 24-month Defect Liability Period (DLP), OEM free replacement applies for hardware failures due to manufacturing defects. Hardware damage resulting from proven subscriber misuse, vandalism, or force majeure shall be handled via spare parts replacement at the contracted master rate card. | Binding Ruling (Bid Bulletin No. 2)
59 | Q059 | SLA&KPIs | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Regarding the MTTR、NAV、SPMS SLA, Due to the lack of live network conditions and other inputs, it is impossible to assess the achievability of KPIs: SLA is recommended to be finalized based on the actual values observed during the 6 months following acceptance and commissioning. | Confirmed. The SLA targets defined in Appendix C represent standard telecommunications industry benchmarks for enterprise 5G fixed wireless networks. For Phase 1, TelTech grants a 90-day post-PAC stabilization period for each rollout cluster, during which service credits / SLA penalties for network availability (NAV) and MTTR are waived while operational baselines and spares logistics are stabilized. | Binding Ruling (Bid Bulletin No. 2)
60 | Q060 | Commercial Template | 06_RFP_Commercial_Price_Book_and_BoQ_Template | All | The portal "3. Commercial BoQ & Financing Lots 1-7" contents is different with the tender documents "06_RFP_Commercial_Price_Book_and_BoQ_Template" Kindly clarify which version to follow and filled? | Confirmed. The online portal Commercial BoQ tables and Excel Document 06 (06_RFP_Commercial_Price_Book_and_BoQ_Template.xlsx) have been fully harmonized. In case of any technical discrepancy, the official Excel Document 06 workbook shall serve as the governing commercial baseline. | Binding Ruling (Bid Bulletin No. 2)
61 | Q061 | Commercial Template | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | Regarding the vendor submissions in the portal under "3. Commercial BoQ & Financing Lots 1-7": Since the current BOQ only reflects Phase 1 of the project, please clarify the pricing mechanism for the subsequent years: CAPEX: Assuming the Phase 1 price is fixed, will this exact pricing be applicable directly to Years 2 through 5? OPEX: Since vendors are only providing the OPEX for Phase 1, how should we calculate the following phases? For Phase 2, do we multiply the Phase 1 cost by 2? Does this same logic apply to the subsequent years up to Year 5? | Confirmed. Commercial proposals must quote firm, fixed unit rates and total pricing based on the complete 5,000 candidate site scope (Lot 1 through Lot 7). The project execution schedule follows the multi-batch rollout roadmap (Phase 1: 1,000 sites; Batches 2–5: 1,000 sites each). | Binding Ruling (Bid Bulletin No. 2)
62 | Q062 | Commercial Template | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | As the USD to PHP exchange rate is fluctuating significantly right now, locking in a fixed rate poses a financial risk. We propose issuing all commercial documents (BoQ, PO, and Invoices) strictly in USD. If you prefer to pay in PHP, we will use the actual exchange rate on the date the payment is remitted. | Confirmed. Commercial unit rates in foreign currency (USD) and local currency (PHP) shall be evaluated using the benchmark exchange rate of USD 1.00 = PHP 55.00 as stipulated in Document 06. For imported telecom equipment (Lots 1, 2, 3, 7), contract billing and letters of credit (LC) may be settled in USD, eliminating currency conversion risk for offshore OEM suppliers. | Binding Ruling (Bid Bulletin No. 2)
63 | Q063 | Commercial Template | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | Kindly clarify for Commercial BoQ & Financing which need to be filled online: 1. If we are unable to provide a certain line item, should the bidder leave the unit price blank? 2. Where is the best place to add our pricing assumptions? | Confirmed. 1. Bidders are permitted to submit proposals on an individual Lot or combination of Lots (e.g. RAN only, Core only, Civil only). Bidders not bidding on specific lots shall leave those lot pricing sheets unpriced or mark 'NO BID'. 2. Custom or proprietary value-add components may be added using the custom line-item entry rows in Document 06. | Binding Ruling (Bid Bulletin No. 2)
64 | Q064 | SLI | 01_RFP_5G_FWA_Master_Tender_Document | LOT | What is installation? In which scenarios is installation required? Is the Contractor / Prospective Bidder responsible for the installation? How to calculate the New Installation Dispatch Lead Time? | Clarified. 1. Installation Scope: Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. 2. First-Time-Right (FTR) Installation Rate Calculation: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to faulty installation, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
65 | Q064 | SLI | 01_RFP_5G_FWA_Master_Tender_Document | LOT | How is the First-Time-Right (FTR) Installation Rate calculated? | Clarified. 1. Installation Scope: Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. 2. First-Time-Right (FTR) Installation Rate Calculation: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to faulty installation, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
66 | Q065 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Since it is a managed service, why do we need to accept the OSS tools of the managed service? How to handle the tools after MS ends? | Clarified. Bidders delivering Managed Services (MS) are required to provide all specialized tool licenses, diagnostic suites, and automation software necessary to fulfill their contracted scope and meet SLA obligations during the 5-year MS term. Following expiration of the MS term, TelTech reserves the option to transition tool operation in-house under standard commercial software maintenance terms. | Binding Ruling (Bid Bulletin No. 2)
67 | Q066 | SLA&KPIs | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/365 Nationwide) | Service creadit penalty (< threshold)-- does this threshold mean Minimum threshold or target standard? | Service Credit penalties are assessed when monthly performance drops below the Minimum Threshold (not the Target Standard). Performance between the Target Standard and Minimum Threshold triggers mandatory corrective action and root-cause analysis without financial liquidated damages. Service Credits apply only when monthly performance breaches the Minimum Threshold floor. | Binding Ruling (Bid Bulletin No. 2)
68 | Q067 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | kindly provide formula , or is it " initial RRC connection rate X erab assignment success rate" | Per 3GPP TS 38.331 and ETSI standards, Call/Session Setup Success Rate (CSSR) is defined as: CSSR = [RRC Connection Setup Success Rate] x [QoS Flow / NG-C Setup Success Rate] x 100%. Where RRC Setup Success Rate = (Successful RRC Setup Completions / RRC Setup Requests excluding rejections) and QoS Flow Setup Success Rate = (Successful 5G QoS Flow Establishments / QoS Flow Establishment Requests). | Binding Ruling (Bid Bulletin No. 2)
69 | Q068 | SLA&KPIs | 06_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/367 Nationwide) | busy hour means auto busy hour or fixed busy hour such as 19:00- 20:00? | Confirmed. Busy Hour is defined as Time-Consistent Busy Hour (TCBH) per 3GPP/ITU-T recommendations, determined on a per-cell basis as the continuous 60-minute interval exhibiting the highest combined uplink and downlink traffic volume over a 30-day rolling observation window. | Binding Ruling (Bid Bulletin No. 2)
70 | Q069 | SLA&KPIs | 07_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/368 Nationwide) | 1. because there is " cell edge DL&UL user speed", is this drive test KPI ? user throughput means CPE throughput? 2. how to define cell edge here? | Confirmed. Cell-edge user speed is evaluated at the outer boundary of the designed coverage footprint (nominally RSRP between -95 dBm and -105 dBm). During acceptance, it is verified via stationary drive/walk tests and CPE performance logs. For operational KPI reporting, cell-edge performance is tracked via 5-percentile user throughput metrics extracted from gNodeB OSS performance counters. | Binding Ruling (Bid Bulletin No. 2)
71 | Q070 | SLA&KPIs |  | 5.7 Radio Frequency (RF) Cluster Optimization | the target of cluster optimization is only for coverage outdoor target , any target for other KPIs such as throughput ? | Confirmed. Cluster optimization acceptance requires meeting both coverage and quality criteria: (1) Coverage: RSRP >= -95 dBm over >= 90% of the designated target populated settlement area; (2) Quality: SINR >= 3 dB over >= 90% of the cluster footprint; (3) Throughput: SSV speed targets verified at near, mid, and edge testing points; (4) Accessibility/Retainability: Cluster-wide CSSR >= 97% and Call Drop Rate (CDR) <= 1.5%. | Binding Ruling (Bid Bulletin No. 2)
72 | Q071 | SLA&KPIs | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | for Near , mid and far location, suggest to based on simulation of typcial site ( antenna height, tilt, power ), and give proper distance of near , mid and far. or use RSRP level at -90, -100, -105 | Confirmed. The classification of Near (<500m), Mid (1.0–1.5 km), and Far (>=2.0 km) zones is established based on baseline RF propagation modeling for 30m nominal antenna height, adjusted during physical cluster drive testing and SSV based on local terrain, clutter, and morphology. | Binding Ruling (Bid Bulletin No. 2)
73 | Q072 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | From our general understanding, the rules for spectrum allocation are usually uniform nationwide. We would like to know whether TelTech has obtained authorization from the NTC to use 80 MHz of spectrum in areas outside the NCR. | Confirmed. The operational frequency authorization is governed by the National Telecommunications Commission (NTC) framework covering dedicated broadband wireless/private enterprise allocations within 1457.0 – 1518.0 MHz nationwide across the 5,000 candidate barangays. TelTech is finalizing formal commercial coordination with NTC; bidders shall design their RAN solutions for a standard 60 MHz TDD carrier (1457–1517 MHz) with 30 kHz Subcarrier Spacing (SCS). | Binding Ruling (Bid Bulletin No. 2)
74 | Q073 | Wireless and Delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | Antennas are generally installed at relatively high positions on towers. Towers have requirements for the antenna's windward area and wind load capacity. Does TelTech have requirements for the antenna's windward area and wind load capacity? Based on the Contractor / Prospective Bidder's experience in delivering macro base stations, it is recommended that the windward area does not exceed 0.8 square meters. | Confirmed. For Class T1–T3 co-location sites, allowable antenna projected windward surface area, EPA (Effective Projected Area), and mounting centerline elevations are governed by each TowerCo's structural design limits and master lease agreements (MLA). Bidders shall submit equipment dimensions and weight specifications. For Class T4 Greenfield Monopoles, the tower structure must be designed to withstand NSCP 2015 wind speeds of up to 270 km/h (Category V typhoon resistance) accommodating 6 RRUs, 1 integrated active antenna (or 3 passive antennas), and up to 1.2 m² total microwave dish surface area. | Binding Ruling (Bid Bulletin No. 2)
75 | Q074 | Warranty | 01_RFP_5G_FWA_Master_Tender_Document.pdf |  | Please confirm that the mandatory base Defect Liability Period (DLP / Hardware Warranty) for network equipment remains 24 months (2 years) from the date of PAC issuance per site/phase. Furthermore, please clarify whether the Extended Warranty and Spare Parts Management Service (SPMS) for Years 3–5 (as well as Years 6–10 for TCO calculation) should be quoted as separate, optional line items per Phase in the Appendix B Commercial BoQ. | Confirmed. The mandatory base Defect Liability Period (DLP / Hardware Warranty) for all active network equipment (Lots 1, 2, 3, 6) is confirmed as twenty-four (24) months (2 years) commencing from the issuance of the Provisional Acceptance Certificate (PAC). | Binding Ruling (Bid Bulletin No. 2)
76 | Q075 | Training | 01_RFP_5G_FWA_Master_Tender_Document.pdf |  | Please clarify whether formal OEM technical training and certification programs (covering 5G SA Core, Band n50 RAN, BSS/OSS, and FMS) are required for TelTech’s engineering and O&M personnel. If required, kindly provide the estimated number of trainees, preferred training location (e.g., local classroom in Manila/Clark vs. OEM headquarters), and confirm if this should be quoted as a dedicated line item in the Commercial BoQ. | Confirmed. Formal OEM technical training and certification programs covering 5G SA Core administration, Band n50 RAN RF optimization, OSS/BSS operations, and field maintenance are mandatory deliverables under Lot 5 / Services, dimensioned for at least 20 TelTech engineering personnel. | Binding Ruling (Bid Bulletin No. 2)
77 | Q076 | Commercial Template | Portal "3. Commercial BoQ & Financing Lots 1-7" |  | For the Years 6–10 Cumulative OPEX (Managed Services and Extended Maintenance) in the 10-Year TCO evaluation, please confirm if bidders are permitted to include an annual Consumer Price Index (CPI) inflation indexation and FX adjustment clause to account for long-term macroeconomic fluctuations. | Confirmed. Bidders are permitted to quote Years 6–10 Managed Services and extended software maintenance as an optional annual escalation or fixed rate in the 10-Year Total Cost of Ownership (TCO) financial model. | Binding Ruling (Bid Bulletin No. 2)
78 | Q077 | Commercial Template | Portal "3. Commercial BoQ & Financing Lots 1-7" |  | Are all unit prices in Commercial BOQ to be quoted in VAT Ex (Value Added Tax Exclusive)? | Confirmed. All unit rates and total prices in the Commercial BoQ must be quoted exclusive of 12% Philippine Value Added Tax (VAT-Exclusive). VAT will be added as a separate line item on billing invoices in accordance with Bureau of Internal Revenue (BIR) regulations. | Binding Ruling (Bid Bulletin No. 2)
79 | Q078 | Power system and delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE | 1. Does it requires 2 Rectifier System per site or 2N Configuration? For ex: 1000 sites will be 2000 rectifier? 2. Do they need monitoring software to cover all sites?? 3. Please confirm weather the rectifier will be installed indoor or outdoor? 4. If outdoor installation, does all the 5000 sites is same set up? | Confirmed. (1) Each site requires one (1) high-efficiency outdoor-rated rectifier system with N+1 modular rectifier redundancy (e.g. 3x 50A modules providing 100A N+1 output). For ground-based Greenfield sites, an outdoor cabinet-housed rectifier is utilized; for tower co-location sites with limited footprint, blade/pole-mounted outdoor rectifiers are preferred. (2) Remote power monitoring software/controller with SNMPv3 / Modbus-TCP telemetry reporting into the centralized OSS is mandatory. | Binding Ruling (Bid Bulletin No. 2)
80 | Q079 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | In the FM app, is it acceptable that the navigation function redirects to an external app, such as Google Maps? | Confirmed. In the Field Force Management (FMS) mobile application, deep-linking or redirecting to external standard navigation applications (e.g., Google Maps, Waze) for route guidance to site/subscriber coordinates is fully acceptable. | Binding Ruling (Bid Bulletin No. 2)
81 | Q080 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | In the FM app, is the e-sign used only to collect users' handwritten signatures? If the electronic signature is used for strong authentication, a third-party SDK needs to be integrated. Currently, this is not supported. | Confirmed. Capturing the subscriber's handwritten signature on the mobile touchscreen interface at completion of installation/service is acceptable for job acceptance. Third-party digital signature authority (CA/PKI) integration is not mandatory for standard residential installation sign-offs. | Binding Ruling (Bid Bulletin No. 2)
82 | Q081 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | For RF signal verification, it is recommended to use professional software such as Cellular-Z to obtain more accurate and professional policy data. | Confirmed. Any industry-standard, calibrated RF measurement application or handheld scanner (e.g., Cellular-Z, G-NetTrack Pro, Nemo Handy, or OEM-native diagnostic tool) is acceptable for post-installation RF verification, provided it logs accurate RSRP, RSRQ, SINR, and Cell ID parameters into the installation completion report. | Binding Ruling (Bid Bulletin No. 2)
83 | Q082 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Does the installation order involve service provisioning? | Confirmed. Installation work orders executed by field technicians must trigger automated service provisioning in the BSS/OSS upon successful on-site RF validation and customer digital sign-off, regardless of whether installation is performed by OEM managed service teams or outsourced subcontractors. | Binding Ruling (Bid Bulletin No. 2)
84 | Q083 | Wireless and Delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | The areas covered by the issued tender documents are mostly suburban or rural regions, which do not have the capability to use 5-meter HD maps. Should we switch to using 2D maps entirely for simulation planning? | Confirmed. For rural and remote Class T4 candidate barangays where 5-meter HD clutter maps are commercially unavailable, bidders are permitted to utilize standard 20m/25m digital elevation and land-use clutter datasets supplemented by satellite imagery and digital surface models (DSM) for macro-cellular nominal RF planning and cluster simulation. | Binding Ruling (Bid Bulletin No. 2)
85 | Q084 | Wireless and Delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | According to the current site capability planning, the maximum average traffic of a single site does not exceed 1 Gbit/s. Therefore, the site does not need to support 2 x 10GE + 2 x 25GE interfaces. It is recommended that only the maximum capability be reserved, that is, 2 x 25GE interfaces. | Confirmed. An initial backhaul transport capacity of 1 Gbit/s per gNodeB site is acceptable for Day 1 traffic dimensioning. However, backhaul transmission interfaces (both optical transceivers and microwave links) must support hardware upgradeability to 10 Gbit/s via standard SFP+ interfaces to accommodate future multi-carrier expansion and subscriber growth. | Binding Ruling (Bid Bulletin No. 2)
86 | Q085 | Wireless and Delivery | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | Considering there are 897 co-sited base stations, is it advisable to use cabinet BBUs instead of blade BBUs? | Confirmed. Blade BBUs (outdoor zero-footprint pole/wall-mounted baseband units) are strongly preferred across all 897 co-location sites to eliminate ground footprint leasing penalties, reduce shelter space requirements, and facilitate rapid deployment. Compact outdoor cabinet BBUs are acceptable only where indoor/shelter space is pre-contracted or where blade mounting is structurally restricted by the TowerCo. | Binding Ruling (Bid Bulletin No. 2)
87 | Q086 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Regarding the CPE recovery rate (>= 70%), the Contractor / Prospective Bidder's 2-year warranty period allows for free replacement if any issues arise. Is such a service acceptable? The CPE recovery rate cannot be controlled. | Accepted and clarified. The >= 70% CPE Recovery Rate defined in the RFP applies strictly to churned subscriber recovery and reverse logistics (retrieving TelTech-owned CPE hardware from canceled subscriber premises), not OEM warranty returns. For defective CPE units under the 24-month DLP, OEM free replacement applies for manufacturing defects. Hardware damage resulting from proven subscriber misuse, vandalism, or force majeure shall be handled via spare parts replacement at the contracted master rate card. | Binding Ruling (Bid Bulletin No. 2)
88 | Q087 | SLA&KPIs | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Regarding the MTTR、NAV、SPMS SLA, Due to the lack of live network conditions and other inputs, it is impossible to assess the achievability of KPIs: SLA is recommended to be finalized based on the actual values observed during the 6 months following acceptance and commissioning. | Confirmed. The SLA targets defined in Appendix C represent standard telecommunications industry benchmarks for enterprise 5G fixed wireless networks. For Phase 1, TelTech grants a 90-day post-PAC stabilization period for each rollout cluster, during which service credits / SLA penalties for network availability (NAV) and MTTR are waived while operational baselines and spares logistics are stabilized. | Binding Ruling (Bid Bulletin No. 2)
89 | Q088 | SLI | 01_RFP_5G_FWA_Master_Tender_Document | LOT | What is installation? In which scenarios is installation required? Is the Contractor / Prospective Bidder responsible for the installation? How to calculate the New Installation Dispatch Lead Time? | Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. | Binding Ruling (Bid Bulletin No. 2)
90 | Q089 | SLI | 01_RFP_5G_FWA_Master_Tender_Document | LOT | How is the First-Time-Right (FTR) Installation Rate calculated? | The First-Time-Right (FTR) Installation Rate is calculated on a monthly rolling basis using the standard formula: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to hardware failure, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
91 | Q090 | SLI | 01_RFP_5G_FWA_Master_Tender_Document | LOT | Please provide the procedures for CPE distribution, recovery, and maintenance. | TelTech's standard CPE lifecycle procedure operates as follows: (1) Distribution/Provisioning: Bulk CPE shipments arrive at TelTech's central staging warehouse, undergo barcode/IMEI ingestion into BSS/OSS asset tracking, and are dispatched to regional forward staging hubs. Installers scan serial numbers on-site and initiate automated zero-touch provisioning (TR-069 / USP via ACS). (2) Maintenance/RMA: Faulty units identified during subscriber trouble tickets are swapped by field technicians with buffer units from regional staging stock. Defective units are returned for RMA batching under the 24-month DLP warranty. (3) Recovery/Reverse Logistics: Upon subscriber service termination, BSS triggers a CPE Retrieval Work Order in the Field Force App. Recovered units undergo factory reset, testing, refurbishment, repackaging, and re-entry into active inventory. | Binding Ruling (Bid Bulletin No. 2)
92 | Q091 | SLA&KPIs | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Does NBD in SPMS mean sending to the Contractor / Prospective Bidder's regional spare parts warehouse? | NBD (Next Business Day) replacement under the Spare Parts Management Service (SPMS) requires the replacement spare part to be delivered to the designated regional forward logistics hub / TelTech regional maintenance center within the next business day (Monday through Saturday, cut-off time 15:00) following RMA dispatch notification. | Binding Ruling (Bid Bulletin No. 2)
93 | Q092 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Can the standalone OSS/BSS software scope be decoupled from the following indicators: New Installation Dispatch Lead Time, First-Time-Right (FTR) Installation Rate, and Churned CPE Hardware Recovery Rate. | Accepted and clarified. For standalone OSS/BSS software delivery (Lot 4), SLA commitments apply to software availability, transaction processing latency, and API throughput (e.g. system uptime >= 99.95%, work order dispatch generation < 5 seconds). Operational field performance indicators such as New Installation Dispatch Lead Time, First-Time-Right (FTR) Installation Rate, and Churned CPE Recovery Rate apply strictly to the Managed Services & Field Operations scope (Lot 5 / Appendix E) when awarded to the managed service provider. | Binding Ruling (Bid Bulletin No. 2)
94 | Q093 | Site, civil work, and managed services | APPENDIX E: SERVICES STATEMENT OF WORK & MASTER RATE CARD | 4. MASTER SERVICES PRICING SCHEDULE & COMMERCIAL RATE CARD | 1. Please suggest on which scenario we need to do tower retrofitting works, since towerco tower is belong to towerco to do retrofitting. 2. Tower retrofitting need to have retrofitting design first, and this scope are based on each site situation, case by case, Please suggest how to quote this item. | Confirmed. For Class T1–T3 co-location sites, tower structural strengthening is primary responsibility of the respective TowerCo under master co-location arrangements. However, to mitigate potential TowerCo lead time delays, bidders shall provide unit rate pricing in the Appendix E Master Rate Card for structural surveys, structural integrity assessments, engineering design, and structural reinforcement fabrication/installation in the event TelTech elects to self-execute retrofitting. | Binding Ruling (Bid Bulletin No. 2)
95 | Q094 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | Suggest CSSR target 97%, minimum threshold 96; based on huawei global FWA network experience , RRC setup success rate 99% , and qos 98.5%； The CSSR further improvement is constrainted from terminal compatibility issues, the extent of network coverage, and transmission loss in indoor CPE. | Accepted. TelTech officially updates the nationwide Call/Session Setup Success Rate (CSSR) operational KPI as follows: Target Standard: 97.0% (revised from 99.0%); Minimum Threshold: 96.0% (revised from 97.5%). This adjustment accounts for real-world FWA CPE propagation environments while maintaining premium carrier-grade service reliability. | Binding Ruling (Bid Bulletin No. 2)
96 | Q095 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | Suggest target 1.5%， maximum 2%； The same reason that KPI CDR further improvement is constrainted from terminal compatibility issues, the extent of network coverage, and transmission loss in indoor CPE. | Accepted. TelTech officially updates the nationwide Call Drop Rate (CDR) operational KPI as follows: Target Standard: <= 1.5% (revised from <= 0.5%); Maximum Threshold: <= 2.0% (revised from <= 1.0%). Service Credits apply only if monthly nationwide aggregate CDR exceeds 2.0%. | Binding Ruling (Bid Bulletin No. 2)
97 | Q096 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | suggest to remove both KPIs , this is more factored by user behavior and user distribution ;also throughput already reflected in SSV KPI | Accepted in part. TelTech confirms that contractual financial liquidated damages / service credits shall not be assessed against daily instantaneous user throughput OSS counters. However, gNodeB scheduler throughput metrics (5-percentile and 50-percentile user throughput) shall remain active in OSS performance management for network traffic monitoring and capacity trigger planning. | Binding Ruling (Bid Bulletin No. 2)
98 | Q097 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | There is no OSS KPI latency statistics; only drive tests are available, which have been reflected in SSV. | Accepted. TelTech confirms that the round-trip latency KPI (target <= 20 ms) shall be formally validated during Single Site Verification (SSV) and periodic cluster drive testing using standardized ping / TWAMP (Two-Way Active Measurement Protocol) test procedures between the test CPE and gNodeB / UPF test endpoints. | Binding Ruling (Bid Bulletin No. 2)
99 | Q098 | SLA&KPIs | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | suggest target 0.1%，0.2% max; and PDCP layer; | Accepted. Packet loss rate shall be formally evaluated at the PDCP (Packet Data Convergence Protocol) layer per 3GPP TS 38.314 standards, with updated KPI thresholds: Target Standard: <= 0.10%; Maximum Threshold: <= 0.20%. | Binding Ruling (Bid Bulletin No. 2)
100 | Q099 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | from last time clarification , converage feedback : SSV SPEED TARGETS PER DISTANCE ZONE: - Near Zone (< 500m): DL >= 200 Mbps / UL >= 30 Mbps. - Mid Zone (1.0 – 1.5 km): DL >= 100 Mbps / UL >= 20 Mbps. - Far / Cell Edge (>= 2.0 km): DL >= 25 Mbps / UL >= 5 Mbps (minimum SLA threshold). Suggest to be : Slot configuration: DL:UL=8：2(DDDDDDDSUU) and static test, >-80dBm: DL 200Mbps / UL 25Mbps [-80~-95)dBm: DL 100Mbps/UL 10Mbps [-95~-105)dBm: DL 35Mbps/UL 1.5Mbps | Accepted with clarification. TelTech approves the adoption of RSRP-correlated benchmark thresholds for static Single Site Verification (SSV) under a standard 8:2 (DDDDDDDSUU) or 7:3 TDD frame structure in a 60 MHz Band n50 channel: (1) Near Zone (RSRP >= -80 dBm): DL >= 200 Mbps / UL >= 25 Mbps; (2) Mid Zone (-95 dBm <= RSRP < -80 dBm): DL >= 100 Mbps / UL >= 10 Mbps; (3) Cell Edge Zone (-105 dBm <= RSRP < -95 dBm): DL >= 35 Mbps / UL >= 5 Mbps (UL minimum floor of 5 Mbps is maintained to ensure reliable TCP ACK and two-way interactive video traffic). Stationary SSV measurements shall be recorded using standard outdoor/indoor CPE units matching Lot 7 technical specifications. | Binding Ruling (Bid Bulletin No. 2)
101 | Q100 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2.3 Transmission & Backhaul Topology | 1, The SFP of Transmission devices for Interconnections with BBU will be provided by the Contractor / Prospective Bidder or TelTech/TelTech? 2, The SFP of BBU will be 25GE/10GE Adaptive Optical Module, the SFP of transmission device will be adaptive also, or specific ones and what types they will be(need confirm the transmission port capability also) 3, The related configurations on Transmission backhaul for BBU integration will be under TelTech or the Contractor / Prospective Bidder? | Confirmed. 1. SFP Supply Boundary: The RAN bidder is responsible for supplying optical transceivers (SFPs) for all BBU/gNodeB ports. TelTech/TelTech will provide the compatible optical transceivers for the customer-facing ports on the demarcation transmission device (IP-RAN router / cell site gateway / GPON ONT). 2. Optics Specification: BBU optical modules shall be dual-rate 10GE/25GE eCPRI/CPRI/Ethernet adaptive transceivers (supporting standard 1310nm Single-Mode Fiber, LC duplex connectors, up to 10 km reach). Demarcation switch ports provided by TelTech support auto-negotiation at 10GE and 25GE. 3. Configuration Responsibilities: The RAN bidder is responsible for end-to-end BBU interface configuration (VLAN tagging, IP addressing, QoS markings per DSCP matrix, and sync synchronization IEEE 1588v2 PTP / SyncE). TelTech/TelTech transmission engineers will configure the transport network (VLAN tunneling, MPLS-VPN / SRv6 L2/L3 transport) up to the BBU handoff port. | Binding Ruling (Bid Bulletin No. 2)

## Part 1 - RAN & Spectrum
COMCLARK NETWORK & TECHNOLOGY CORP. / TELTECH 5G FWA NATIONWIDE TURNKEY TENDER
BID BULLETIN NO. 1 — OFFICIAL CLARIFICATION RESPONSES (PART 1: RAN, SPECTRUM & POWER INFRASTRUCTURE)
Item No. | Domain Classification | Document Reference | Section / Chapter Reference | Prospective Bidder Inquiry | Comclark / TelTech Official Response | Procurement Status
1 | RAN | 01_RFP_5G_FWA_Master_Tender_Document | LOT 1: 5G RAN EQUIPMENT & ACCESS HARDWARE - 2.1 Spectrum Physics: Band n50 Advantage | Since the 1437–1457 MHz band has been assigned to another corporation in the NCR, kindly please confirm the following spectrum deployment plan: Metro Manila (NCR): 1457–1517 MHz (60 MHz) Rest of the country: 1437–1517 MHz (80 MHz) | CONFIRMED. The baseline spectrum deployment plan is formally confirmed as follows: 1. Metro Manila (NCR): 1457 – 1517 MHz (60 MHz continuous TDD bandwidth), fully compliant with the Operator's statutory authority and NTC demonstration permit. 2. Rest of the Country (Provincial / Regional): 1437 – 1517 MHz (up to 80 MHz IBW/OBW capability). Bidders' 5G NR Baseband Units (BBU) and Remote Radio Units (RRU) / Active Antenna Units (AAU) must natively support the full 3GPP Band n50 tuning range (1432 – 1517 MHz) in hardware, with carrier bandwidth software-configurable to 40 MHz, 50 MHz, 60 MHz, or up to 80 MHz as assigned. | Binding Ruling (Bid Bulletin No. 1)
2 | RAN | 01_RFP_5G_FWA_Master_Tender_Document | LOT 1: 5G RAN EQUIPMENT & ACCESS HARDWARE - 2.1 Spectrum Physics: Band n50 Advantage | Further clarification is required regarding the bandwidth that needs to be supported. Are there any special customization requirements for the filter's out-of-band rejection and emissions? Point 1: If the 1437–1457 MHz band is occupied by another operator, are there any specific spurious emission requirements that supplier's equipment must comply with for the low end and high end(1457M and 1517M)? Point 2: If the 1437–1457 MHz band is available for use outside the NCR areas, does the NTC impose any spurious emission requirements for the low and high end(1437M and 1517M)? | CONFIRMED & DETAILED: Point 1 (NCR Carrier: 1457–1517 MHz): Supplier equipment must comply with 3GPP TS 38.104 Category B Operating Band Unwanted Emissions (OBUE) and standard NTC Type Approval spurious emission masks. At the low end (1457 MHz), the RRU digital filtering and DPD must ensure sharp attenuation to protect adjacent users below 1457 MHz. At the high end (1517 MHz), equipment must implement appropriate filtering to protect the adjacent Maritime Mobile Satellite Service (MSS, 1518–1525 MHz per ITU-R M.2159-0), with unwanted emissions not exceeding -30 dBm/MHz. Point 2 (Outside NCR: 1437–1517 MHz): Standard 3GPP Band n50 TS 38.104 Category B emission masks apply at the 1437 MHz lower edge and 1517 MHz upper edge. No non-standard or proprietary hardware filtering customization is required beyond compliant 3GPP Release 16/17 Band n50 radio hardware. | Binding Ruling (Bid Bulletin No. 1)
3 | RF Planning | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx - 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | To support the above planning activities, bidder kindly requests Comclark/TelTech to share the following information for the nearest tower(s): location (longitude / latitude) and tower height. | CONFIRMED & PROVIDED. Candidate site geographic coordinates (Latitude / Longitude in WGS84) and nominal Tower Heights (AGL in meters) for all 1,000 Phase 1 candidate sites are fully provided in Document 07 ('07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx'), specifically under sheets 'Phase 1 (First 1,000 Sites)' and 'Towerco_list' (covering PhilTower, EdgePoint, EDOTCO, and Unity assets). | Binding Ruling (Bid Bulletin No. 1)
4 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE - 2.3 Transmission & Backhaul Topology | Bidder proposes that Comclark/TelTech clarify the defination of "fiber segments" and the "optical nodes" | CLARIFICATION OF DEFINITIONS: - 'Optical Node': An audited, active Comclark/TelTech point-of-interconnect—specifically an Optical Distribution Frame (ODF), Fiber Distribution Terminal (FDT), or Primary Fiber Hub equipped with available optical splice/splitter capacity to serve as the backhaul transmission handover point. - 'Fiber Segment': An audited physical fiber optic cable route (feeder, distribution, or lateral FOC) spanning between the optical node/central office and the customer/tower drop point, as verified in Comclark/TelTech's audited GIS distribution plant. | Binding Ruling (Bid Bulletin No. 1)
5 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE - 2.3 Transmission & Backhaul Topology | Bidder proposes that Comclark/TelTech clarify the defination of " C: Line-tap splice closure <= 0.5 km" | CLARIFICATION OF DEFINITION: 'Class C: Line-tap splice closure <= 0.5 km' designates a candidate macro tower location where an existing aerial or underground Comclark/TelTech trunk/distribution fiber optic cable passes within 500 meters of the site compound, and interconnection will be achieved by cutting into the cable at an existing or newly inserted inline splice closure (FOSC / Dome Enclosure) rather than routing back to a centralized ODF/node. | Binding Ruling (Bid Bulletin No. 1)
6 | Transmission | 05_SiteSurvey, RFPlanning & Civil/Power Engineering Guidelines | 2. DETAILED TECHNICAL SITE SURVEY REPORT (TSSR) REQUIREMENTS - 2.4 Backhaul Transmission Path Survey | Does the "distance to the nearest node" refer to the distance to the 5G base station ? Bidder proposes that Comclark/TelTech clarify the defination of " distance to line-tap closure" | CLARIFICATION OF DEFINITIONS: - 'Distance to Nearest Node': Refers to the estimated terrestrial linear cable route distance from the proposed 5G Macro Tower compound to the nearest confirmed Comclark/TelTech Optical Node (Class A <= 0.5 km; Class B <= 1.0 km). - 'Distance to Line-Tap Closure': Refers to the linear cable distance from the 5G Base Station to the designated trunk cable splice closure (Class C <= 0.5 km). | Binding Ruling (Bid Bulletin No. 1)
7 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE - 2.3 Transmission & Backhaul Topology | Bidder respectfully proposes that Comclark/TelTech confirm whether the Microwave solution for Class D is to be considered within the Supplier's scope of supply, or whether it will be provided by Comclark/TelTech directly. | CONFIRMED: SUPPLIER SCOPE OF SUPPLY / PRICING. Class D sites (~1.7% of Phase 1 sites, plus microwave backup links for island sites) require a turnkey high-capacity microwave backhaul link (11 GHz / 18 GHz / 23 GHz or E-Band 80 GHz, minimum 1.0 Gbps full-duplex throughput). Bidders must quote the microwave split-mount hardware (IDU, ODU, antenna, IF cabling) and installation services in Appendix B (Commercial BoQ) under Lot 1 / Lot 3 options. Comclark/TelTech reserves the right to provide direct fiber drops prior to NTP where feasible. | Binding Ruling (Bid Bulletin No. 1)
8 | Power | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE (12 items) - PWR-01 | Kindly confirm whether the 12 kW rating refers to the total installed rectifier capacity (4 × 3 kW modules, including one N+1 redundant module) rather than the output that must be maintained after a single module failure. For reference, a typical load — 3 kW BTS with a 400 Ah battery charged at 0.2C — requires a total DC demand of 7.28 kW (4.28 kW charging + 3 kW BTS load). This demand is fully served by three 3 kW modules, with a fourth module providing N+1 redundancy (12 kW installed; 9 kW available under N+1). Supplier appreciates your confirmation that this load-based N+1 sizing methodology is acceptable, including functionally equivalent configurations. | CONFIRMED ACCEPTABLE. The required sizing methodology is confirmed as follows: - Total Installed Rectifier Capacity: >= 12.0 kW composed of 4 × 3.0 kW (or 4 × 4.0 kW) modular hot-swappable switchmode rectifier modules in an N+1 architecture. - Active Operational Capacity under N+1: With a single module failure (3 operational modules), the system provides 9.0 kW continuous DC output, which comfortably exceeds the peak site DC demand of 7.28 kW (3.0 kW BTS RAN load + 4.28 kW fast battery recharging at 0.2C for 400 Ah / 20 kWh lithium bank). Supplier's proposed load-based N+1 configuration is fully compliant. | Binding Ruling (Bid Bulletin No. 1)
9 | Power | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE (12 items) - PWR-01 / PWR-04 | Please clarify whether pole-mounted installation is mandatory or an integrated ground-mounted outdoor cabinet is acceptable for power HW and RAN HW ? | CLARIFICATION OF INSTALLATION STANDARD: Both configurations are acceptable depending on site compound archetype: 1. Co-location / Rooftop Sites with Space Constraints: Integrated outdoor pole-mounted or wall-mounted power/RAN solutions are acceptable where ground compound footprint is restricted by the TowerCo. 2. Greenfield / Ground Compound Sites (Standard): An integrated, weather-resistant (IP55) ground-mounted outdoor power & battery cabinet installed on an elevated equipment concrete pad is the preferred baseline design. | Binding Ruling (Bid Bulletin No. 1)
10 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 6 - Site Acq & Civils - LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Who is the responsible for transmission and last mile ? | DIVISION OF RESPONSIBILITY: - Comclark / TelTech Scope: Core IP/MPLS network, backbone transport, optical node infrastructure, upstream bandwidth, fiber drop cable provisioning up to the tower demarcation/ODF, and Starlink satellite terminals. - Supplier Scope: Turnkey supply of optical transceivers (10G/25G SFP28 eCPRI and 10G/25G SFP+ backhaul optics), armored optical patchcords, terminal fiber interconnect from tower demarcation box to Baseband Unit (BBU), and end-to-end backhaul circuit acceptance testing during SSV. | Binding Ruling (Bid Bulletin No. 1)
11 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 2 - Power & Passive - LOT 2: POWER SYSTEMS & PASSIVE INFRASTRUCTURE | There are no engineering services items about Rectifier, Battery, Tap-Off Box & Submeter, Getset, pls confirm engineering services isn't supplier's scope. | CLARIFICATION OF SERVICES SCOPE: Installation, wiring, and commissioning of the rectifier, lithium battery bank, AC tap-off box, submeter, and optional genset are included in the turnkey rollout scope under Lot 1 Services (Table 2: RAN Turnkey Rollout Services, Item RAN-SVC-02) and Lot 5 (Civil Works & Power Integration). Turnkey implementation includes all physical mounting, DC cabling, breaker terminations, grounding, and commissioning of the power subsystem. | Binding Ruling (Bid Bulletin No. 1)
12 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 5 - Site Acq & Civils - LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Please provide detailed site design for each civil work item, such as: Equipment Pad Foundation & Cable Gantry, Greenfield Compound Civil Works & Foundation, Grounding Grid & Lightning Protection System, 30m/40m Galvanized Steel Monopole Tower. | CLARIFICATION & GUIDELINES: Typical engineering guidelines, wind loading specifications (minimum 250 km/h typhoon survivability), soil bearing criteria, and grounding grid requirements (<= 5 Ohms) are detailed in Document 05 ('05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf'). Detailed structural fabrication and foundation construction drawings are established during the Joint Technical Site Survey (TSSR) stage (Lot 5 Milestone 1) based on site-specific geotechnical soil test results and actual compound boundaries. Bidders are invited to submit their standard type-approved civil drawings and monopole designs in their technical proposal for committee evaluation. | Binding Ruling (Bid Bulletin No. 1)
13 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 5 - Site Acq & Civils - LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | There are no engineering services items about Commercial Power Access, pls confirm engineering services isn't supplier's scope. | COORDINATED SCOPE: - TelTech / Operator Scope: Payment of official electric cooperative (EC / Meralco / DU) application fees, transformer capital contributions, security deposits, and power supply contracts. - Supplier Scope: Turnkey on-site civil and electrical works from the property line / service drop demarcation pole to the equipment pad—including service entrance conduit/riser, utility revenue class kWh meter base/enclosure, main service disconnect switch, AC panel (ACPDB), and surge protective device (Type 1+2 SPD). | Binding Ruling (Bid Bulletin No. 1)

## Part 2 - Civil, Power & BSS
COMCLARK NETWORK & TECHNOLOGY CORP. / TELTECH 5G FWA NATIONWIDE TURNKEY TENDER
BID BULLETIN NO. 1 — OFFICIAL CLARIFICATION RESPONSES (PART 2: CIVIL, POWER, CORE/BSS & COMMERCIAL)
Item No. | Domain Classification | Document Reference | Section / Chapter Reference | Prospective Bidder Inquiry | Comclark / TelTech Official Response | Procurement Status
1 | Other Business Matters | 01_RFP_5G_FWA_Master_Tender_Document | 5. TENDER SUBMISSION STRUCTURE & COMPLIANCE REQUIREMENTS | Kindly provide this Form A. | CONFIRMED & PROVIDED. The official Form A template (Bid Submission Letter & Consortium Structure) is provided as Attachment 1 to Bid Bulletin No. 1 and is available for download directly in the online RFP portal (Document Library Tab 1). | Binding Ruling (Bid Bulletin No. 1)
2 | OSS & BSS Integration | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is billing considered in scope? | CLARIFICATION OF BILLING SCOPE: In Phase 1, real-time Convergent Charging (CCS/CHF via 3GPP Nchf/Diameter Ro) for prepaid FWA balance management, session cutoff, and quota tracking is the mandatory turnkey scope. Complex postpaid cyclic invoice generation and accounts receivable (A/R) are handled by Comclark/TelTech's enterprise billing system via standard CDR/API export, or may be proposed as an optional modular add-on. | Binding Ruling (Bid Bulletin No. 1)
3 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Bidder system supports many kinds of product but need help to detail your offering requirment. Such as: 1. These offerings need group management (such as family package) or not? 2. These offerings need rollover feature (such as unused data rollove to next cycle) or not? 3. These offerings should support auto upgrade (such as 599 not enough of this cycle automatical upgrade to 700 for next cycle) or not? | CLARIFICATION OF PRODUCT OFFERINGS: 1. Group Management: Optional roadmap feature; single-account per CPE is baseline for Phase 1. 2. Rollover Feature: Supported in product catalog configuration (unused high-speed data quota rolls over into the subsequent 30-day renewal cycle upon prompt re-subscription). 3. Auto-Upgrade: Speed-cap throttling (e.g. throttle to 1 Mbps upon quota exhaustion with option for customer to purchase speed-boost add-on) is the required policy, rather than forced tariff upgrade. | Binding Ruling (Bid Bulletin No. 1)
4 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Bidder system supports standard 3GPP protocal and real-time balanace rating and charging process. some concerns: 1. We assume BSS will support 5G SA network only. 2. Smart quota, dynamic granted quota feature should enable or not? | CLARIFICATION OF CHARGING REQUIREMENTS: 1. Network Architecture: Confirmed 5G Standalone (SA) only. 2. Quota Management: Standard 3GPP dynamic granted quota (DCC) and threshold notification alerts (at 80% and 100% quota consumption via SMS / self-care push notification) must be enabled. | Binding Ruling (Bid Bulletin No. 1)
5 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Bidder system can expose the REST API for payment. some concerns： 1. Should support Voucher recharge or not(3rd party send voucher no and PIN as example)? 2. Should consider Recharge tax or not(When feedback the message to 3rd party or notification to end-subscribers)? 3. Should consider Recharge promotion or not(When feedback the message to 3rd party or notification to end-subscribers)? | CLARIFICATION OF DIGITAL PAYMENT RECHARGE: 1. Voucher Recharge: Omnichannel digital recharge via GCash, Maya, and QR Ph is primary. Third-party electronic voucher PIN recharge is supported as an optional secondary channel. 2. Taxation: BSS catalog must support Philippine 12% Value Added Tax (VAT) calculation and display on payment confirmations and receipts. 3. Promotions: The charging system must natively support marketing promotional rules (e.g., bonus data allowances, referral credits, or promotional validity extensions). | Binding Ruling (Bid Bulletin No. 1)
6 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | What's the FWA service scenario shall be supported by the BSS? For example: New Registration, SIM Location Locking, Address Change, Transfer Owership, Contract Lifecycle Management, CPE/WIFI Router Installment | MANDATORY FWA SERVICE SCENARIOS: The turnkey BSS/OSS must support: 1. New Customer Digital Registration & KYC. 2. Strict SIM-IMEI & Cell-ID Location Locking (binding the FWA service to the authorized installation address to prevent nomadic/mobile unauthorized usage). 3. Relocation / Address Change workflow (manual or automated cell unbinding upon authorized relocation request). 4. Transfer of Ownership & Account Termination. 5. Contract / Subscription Lifecycle Management. 6. CPE Inventory Assignment and Remote FOTA Management. | Binding Ruling (Bid Bulletin No. 1)
7 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | What's the payment mode shall be supported by the BSS? Prepaid, Postpaid, Hybrid? If need postpaid, and hybrid, does it meant the supplier need to provide the billing, invoice relevant components? | PAYMENT MODE ARCHITECTURE: The primary business model for Phase 1 is 100% Prepaid with 30-day recurring subscription validity. Postpaid hybrid invoicing is handled via integration with Comclark/TelTech's enterprise billing platform; bidders / suppliers are only required to provide the real-time prepaid CHF/CCS engine and payment gateway connectors. | Binding Ruling (Bid Bulletin No. 1)
8 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the listed systems, shall the new BSS integrate with ERP Finance system, DWH/BI? Is there data streaming requirement for real-time data synchronization? | ENTERPRISE INTEGRATIONS: The BSS must support standard daily accounting journal export (GL feed) to Comclark/TelTech's SAP ERP and daily CDR/event extraction to the enterprise Data Warehouse (DWH). Real-time Kafka-based event streaming is preferred for operational analytics. | Binding Ruling (Bid Bulletin No. 1)
9 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the self-care channels, shall the supplier provide the retail portal which can be used by the in-shop agent or call center agent? | RETAIL & AGENT PORTAL SCOPE: CONFIRMED. Supplier must provide a secure, web-based Customer Service Representative (CSR) and Authorized Dealer Portal for retail store agents, partner distribution dealers, and call center hotlines to perform customer onboarding, balance lookups, and troubleshooting. | Binding Ruling (Bid Bulletin No. 1)
10 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Beside the CPE inventory management, shall the new BSS/OSS system manage the MSISDN and SIM card resource? | RESOURCE MANAGEMENT SCOPE: CONFIRMED. The turnkey BSS must incorporate a unified resource inventory management module for SIM cards (ICCID), MSISDNs, and CPE hardware serial numbers (IMEI / MAC). | Binding Ruling (Bid Bulletin No. 1)
11 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Does the exisiting network have PCF (Policy Control Function)? Does the BSS need to integrate with this? | POLICY CONTROL (PCF) INTEGRATION: Under Lot 3 (5G Core Network), the supplier is delivering the turnkey 5G SA Core, which includes the Policy Control Function (PCF). The BSS will integrate directly with the supplier's supplied PCF via standard 3GPP N7 / N28 interfaces. | Binding Ruling (Bid Bulletin No. 1)
11 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 3. RF PROPAGATION & CELL DIMENSIONING GUIDELINES | The coverage radius is too large. It is recommended that the coverage radius be 1 km in suburban areas and 1.5 km in rural areas. | CONFIRMED ACCEPTABLE. The revised planning criteria are formally adopted: - Suburban / Dense Urban: Nominal reliable cell radius of 1.0 km. - Rural / Semi-Rural: Nominal reliable cell radius of 1.5 – 2.0 km. These guidelines ensure 95% indoor/outdoor coverage reliability across Band n50 and will govern the updated link budget benchmarks in Document 05. | Binding Ruling (Bid Bulletin No. 1)
12 | Wireless and Delivery | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3.1 Core Radio KPIs (Calculated 24/7/365 Nationwide) | In the case of multiple users, the environment is complex and the attenuation is large. It is recommended that the average cell traffic be controlled within 40 Mbps/10 MHz. | CONFIRMED ACCEPTABLE. The recommended engineering planning baseline of 40 Mbps average cell throughput per 10 MHz of spectrum (yielding ~240 Mbps average cell throughput on a 60 MHz Band n50 TDD carrier with 4:1 DL:UL frame structure) is endorsed as realistic busy-hour design criteria for multi-user FWA deployment. | Binding Ruling (Bid Bulletin No. 1)
13 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines | 2.2 Tower Structure & Loading Audit (Co-Location Sites) | For TowerCo tower, the tower structural Loading verification usually under TowerCo Scope ( Operator provide the equipment list and loading info to TowerCo, TowerCo to provide result). 1. Please kindly suggest if we need to provide structural loading verification service or not. Or we quote this service in a seperate item. 2. If Loading Verification fail, Please suggest the next step (build new tower, or request towerco retrofit tower) Suggest: TowerCo do the structural loading verification. | STRUCTURAL LOADING RESPONSIBILITY: 1. For the 897 TowerCo co-location sites, Tower Structural Loading Verification is the responsibility of the Operator and the TowerCo under the executed Master Lease Agreement (MLA). The supplier provides equipment weights, dimensions, wind load surface area, and cable routing details. 2. If loading verification fails, the TowerCo is obligated under the MLA to perform structural retrofitting, or the Operator will reassign an alternative candidate tower from the pre-approved pool. | Binding Ruling (Bid Bulletin No. 1)
14 | Site, civil work, and managed services | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages |  | Whats the acceptance standard and procedure for Tower, Civil and Power part? Suggest: Supplier can propose if needed. | ACCEPTANCE STANDARDS: Acceptance standards and checklists for Civil, Tower, and Power are detailed in Document 05 ('05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf') and Document 04 (Appendix C). Supplier's standard QA/QC procedure and handover templates are acceptable subject to Joint Technical Committee approval. | Binding Ruling (Bid Bulletin No. 1)
15 | Site, civil work, and managed services | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines 03_Appendix_B_Commercial_Proposal_BoQ_Templates | 2.3 Power Infrastructure & Utility Audit TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For New Site, the BOQ not include the commerical power application and installation (From COOP to Site). Do we need to quote this part? If the commerical power not ready, does the supplier need to provide the temporary power to turn on the site? Suggest: Commerical power shall included and temporary power can consider as VO when needed. | COMMERCIAL POWER & TEMPORARY POWER: 1. Official electric cooperative (EC/DU) application fees and power connection contracts are Operator scope. 2. Turnkey on-site civil and electrical installation (service entrance, meter base, disconnect, ACPDB) is Supplier scope. 3. If commercial utility power is delayed by the power utility, the site will be provisionally accepted using temporary generator power where expedited on-air is mutually agreed, with generator runtime costs handled via established Variation Order (VO). | Binding Ruling (Bid Bulletin No. 1)
16 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | 1. Do you have Type approved brand for Tower, Genset, Aviation light, ACPDB and other power or civil material? 2. Can you provide Typical Design drawing for Tower, Fence and foundation? Or bidder / supplier to propose the solution. Suggest: Supplier can propose if needed. | TYPE-APPROVED BRANDS & CIVIL DESIGNS: 1. Civil and electrical materials must comply with Philippine Electrical Code (PEC), ASTM, and PNS standards (Class A hot-dip galvanized steel, NEMA 3R/4 outdoor enclosures, Schneider/ABB/Eaton breakers). 2. Typical structural and foundation drawings are provided in Document 05. Bidders may propose their type-approved standard foundation, fence, and monopole designs in their technical submission. | Binding Ruling (Bid Bulletin No. 1)
17 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | 1. For the TowerCo site, Is it Comclark/TelTech scope to rent and negotiate with TowerCo? Suggest: For towerco site, should be Comclark/TelTech's responsibility for site renting and negotiating with TowerCo. 2. If the site hunting fail, whats the next step? (Comclark/TelTech to provide another site for hunting to swap the failed site? or cancel the site). Suggest: Supplier will hunt each site with 5 options, if site still failed, suggest customer change the site or provide VO for new option hunting. | SITE ACQUISITION & TOWERCO LEASE NEGOTIATION: 1. For the 897 Co-location sites, lease agreements, space reservation, and commercial negotiations with TowerCos (PhilTower, EdgePoint, EDOTCO, Unity) are strictly the Operator's responsibility under Master Lease Agreements (MLA). 2. For the 103 Greenfield sites, the supplier performs primary site hunting with up to 3 candidate parcels. If site hunting fails due to zoning, legal, or title defects, the Operator will provide a replacement candidate site without bidder penalty. | Binding Ruling (Bid Bulletin No. 1)
18 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | Bidder suggests installing the Genset and fuel tank in a equipment pad. no need to build shelter for genset. | GENSET INSTALLATION STANDARD: CONFIRMED ACCEPTABLE. Outdoor soundproof weatherproof canopy gensets installed directly on an elevated concrete equipment pad (without an enclosed brick/steel shelter building) are fully acceptable. | Binding Ruling (Bid Bulletin No. 1)
19 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Is it Comclark/TelTech scope for Fiber or the supplier is required to execute? | FIBER BACKHAUL RESPONSIBILITY: Comclark/TelTech provides the core optical distribution network, terrestrial fiber drop cable up to the site boundary/ODF, and Starlink satellite terminals. The supplier is responsible for optical transceivers, patchcords, and joint I&C testing from the demarcation box to the BBU. | Binding Ruling (Bid Bulletin No. 1)
20 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | For the non-standard and special construction reuqirment, such as manul hauling, retaining wall and others, Can the bidder / supplier claim separately as VO? | VARIATION ORDER (VO) ELIGIBILITY: CONFIRMED. Non-standard civil construction conditions (such as hard rock excavation requiring pneumatic breakers/blasting, manual material hauling exceeding 500 meters across unpaved/mountainous terrain, and engineered retaining walls) are recognized as eligible for Variation Orders based on pre-agreed unit rates in Appendix B (Lot 5 BoQ). | Binding Ruling (Bid Bulletin No. 1)
21 | Site, civil work, and managed services | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For TowerCo Power part, Usually Towerco will provide AC and DC, Please suggest if the bidder / supplier needs to provide the meter and releated power material to tap to existing power system. | TOWERCO POWER EQUIPMENT: Where TowerCo supplies regulated -48V DC power directly, supplier needs only connect to the designated DC distribution breaker. Where TowerCo provides raw AC utility power, supplier supplies the submeter, ACPDB, and surge suppression. | Binding Ruling (Bid Bulletin No. 1)
22 | Testing / KPI | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf; 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | Section 5 SSV — Ping RTT acceptance; KPI-RAN-07 Radio Round-Trip Latency | For the 17 Starlink backhaul sites, should the RTT KPI threshold be adjusted (e.g., relaxed to <= 50 ms maximum) given the inherent LEO satellite latency? Or are these sites exempt from KPI-RAN-07? Please confirm whether a separate KPI schedule applies to satellite backhaul sites. | STARLINK SATELLITE RTT LATENCY KPI: CONFIRMED & ADOPTED. For the 17 remote/island candidate sites backhauled via Starlink LEO satellite, the Ping RTT SLA is relaxed to <= 60 ms target (<= 80 ms maximum) during SSV and cluster acceptance, reflecting satellite orbital propagation latency. | Binding Ruling (Bid Bulletin No. 1)
23 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document | 2.3 Transmission & Backhaul Topology / App.C 3.1 KPI-RAN-07 | 1. Please provide the verified per-site fiber node/segment list (optical node ID, connection class A-D, committed bandwidth) after on-ground verification — the site list shows all Starlink-fed sites have dist-to-node > 20 km. 2. Please confirm that backhaul resources (Comclark/TelTech fiber SLA, Starlink links) are Operator/third-party provided, and the Operator is responsible for their availability, bandwidth and latency. 3. Do you accept media-tiered RTT KPIs: fiber-fed sites bound by <= 30ms, while satellite-fed sites follow their link physics (e.g. <= 100ms)? 4. Please confirm backhaul outage time is excluded from KPI assessment (RAN availability, end-to-end availability, packet loss). Expected: written confirmation + per-site backhaul list. | BACKHAUL RESOURCES & SLA EXCLUSIONS: 1. Candidate site list in Document 07 provides audited fiber distance classes (Class A <= 0.5km to Class D). 2. Confirmed: Backhaul transport facilities (Comclark/TelTech terrestrial FOC and Starlink links) are Operator-provided. 3. Media-tiered RTT KPIs are formally confirmed: Fiber sites <= 30 ms maximum; Satellite sites <= 80 ms maximum. 4. Confirmed: Downtime caused by upstream third-party transmission outages or fiber cuts outside the site compound is excluded from supplier RAN availability penalty assessments. | Binding Ruling (Bid Bulletin No. 1)
24 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Site Infrastructure & Tower Strategy | 1. Please provide TowerCo lease confirmations / ownership proofs for all co-location sites before NTP. 2. Please provide a tower-readiness schedule per site (lease signed, structural audit, access) feeding the 1,000-sites/365-day plan. 3. Do you agree to back-to-back liability — delays caused by TowerCo approval, access or structural defects are excluded from the contractor's schedule liability with automatic time extension? Expected: written commitment + schedule. | TOWERCO LEASE READINESS & SCHEDULE COMMITMENTS: 1. Operator will provide TowerCo Site Access Authorizations prior to Notice to Proceed (NTP) for each site batch. 2. Confirmed: Schedule milestones commence upon formal Site Handover with approved TowerCo access. Delays caused exclusively by TowerCo structural retrofit or access permit delays will receive day-for-day time extensions without liquidated damages. | Binding Ruling (Bid Bulletin No. 1)
25 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Deployment Typology / App.C 2.1 Milestones M1-M4 | 1. Please confirm an 'Excluded Sites' mechanism — sites blocked by permits (LGU/Barangay/CAAP), land, power connection, TowerCo or coverage issues are deducted from milestone counts. 2. May Milestone-1 TSSR be submitted in phasing (first 200 sites in 45 days, then 300 sites every 30 days), given typical permitting and TowerCo access cycles in the Philippines? 3. Do you accept the 365-day milestone counted in net working days (or auto-extended by the same number of days of Operator/third-party delays)? 4. Please confirm permit fees and utility connection application costs are pass-through (CCP). Expected: written confirmation + revised milestone wording. | MILESTONES & PERMITTING CLAUSES: 1. Blocked Sites Mechanism: Sites blocked by LGU moratorium, right-of-way disputes, or power utility delays beyond 45 days will be swapped with approved reserve sites without schedule penalty. 2. Phased TSSR Submissions: Submitting TSSRs in progressive monthly batches (e.g. 150–200 sites per month) is fully acceptable. 3. Project schedule will account for approved force majeure and Operator/third-party delay extensions. 4. Official LGU building permit statutory fees and utility interconnection fees are pass-through to Operator. | Binding Ruling (Bid Bulletin No. 1)
25 | Site, civil work, and managed services | 01_RFP_5G_FWA_Master_Tender_Document | LOT 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | Can you accept not requiring a drone, as long as the photos can reflect the 360° surrounding environment, and AGL refer to TowerCo provided height for FWA project? | DRONE SURVEY WAIVER: CONFIRMED ACCEPTABLE. Where drone flight permits cannot be secured from CAAP or local authorities within 14 days, high-resolution 360-degree panoramic telephoto ground photography combined with verified TowerCo structural engineering drawings is accepted for TSSR approval. | Binding Ruling (Bid Bulletin No. 1)
25 | Power system and delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE | 1. Do they have Blade requirement ? 2. Can we request room layout or site pictures if available for Lithium Battery Approval? 3. Is there existing rectifier cabinet in existing sites? 4. If SAT requirement is one per equipment or the whole quantity? 5. What is the Total actual DC power for single rectifier requipment? | POWER SYSTEM & BATTERY SPECIFICATIONS: 1. Standard 19" rack-mount modular switchmode rectifiers and 19" rack-mount 48V 100Ah LiFePO4 battery modules are required. 2. Typical site DC load is ~2.8 to 3.2 kW continuous. Sizing requirement is 12.0 kW installed capacity (4 × 3 kW modules, N+1 redundancy). 3. Site layout and equipment pad drawings are provided in Document 05. | Binding Ruling (Bid Bulletin No. 1)
25 | Wireless and Delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | 1. According to ITU-R M.2159-0, the 1518–1525 MHz frequency band is used for maritime communications satellites. If the frequency range of the RRU includes 1512–1517 MHz, it cannot ensure a -30 dB suppression within the 1518–1523 MHz band. Therefore, please confirm whether the NTC allows the use of the 1512–1517 MHz spectrum. 2. We understand that the 1427–1457 MHz frequency band will be allocated by the NTC as spectrum for enterprises. Please consider whether Comclark/TelTech intends to use the 1457–1467 MHz band. It is recommended to refer to the NTC's spectrum usage regulations to determine whether a guard band is required. Therefore, please confirm whether the NTC allows the use of the 1457–1467 MHz spectrum. | SPECTRUM PHYSICS & FILTERING (1457–1517 MHz): 1. Standard 3GPP Band n50 Category B filtering guarantees required suppression (-30 dBm/MHz) into the adjacent 1518–1525 MHz band (maritime satellite). Use of the 1457–1517 MHz band is formally authorized under NTC demonstration permit. 2. In NCR, operation is continuous 60 MHz (1457–1517 MHz); digital filtering within the RRU prevents out-of-band emissions below 1457 MHz. | Binding Ruling (Bid Bulletin No. 1)
25 | Wireless and Delivery | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | overall | Besides interference analysis with maritime communication satellites, suggest to carry out frequency clearance scan before commercial network deployment. | FREQUENCY CLEARANCE TEST: CONFIRMED & AGREED. Supplier and Operator RF teams will conduct joint baseline spectrum clearance sweeps prior to site commercial on-air to identify and resolve any legacy co-channel or adjacent interference. | Binding Ruling (Bid Bulletin No. 1)
25 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Currently, only n50 is planned for FWA development, and NSA networks should not be involved | CONFIRMED. Phase 1 deployment is strictly 5G NR Standalone (SA) in Band n50. NSA operation is not required. | Binding Ruling (Bid Bulletin No. 1)
25 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Currently, only the n50 band is planned for FWA development. Is it mandatory for other sub-6 GHz frequency bands? | CONFIRMED. Native Band n50 (1432 – 1517 MHz, 60 MHz TDD) is mandatory. Fallback sub-6 GHz bands (n1, n3, n78) are optional for the Philippine market. | Binding Ruling (Bid Bulletin No. 1)
25 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | The N50 low-frequency system does not need to rely on extremely high antenna gain to compensate for spatial attenuation as high-frequency systems do. Whether 5-6 dBi is sufficient? | CONFIRMED ACCEPTABLE. For Indoor CPE, an integrated antenna array gain of 5.0 – 6.0 dBi across Band n50 is accepted as compliant due to favorable propagation characteristics of 1.5 GHz L-Band compared to 3.5 GHz. For Outdoor CPE, >= 12.0 dBi remains mandatory. | Binding Ruling (Bid Bulletin No. 1)
25 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | The network port is seldom used and is mainly used for network configuration and commissioning. Can only one network port be reserved for the product? | CPE ETHERNET INTERFACES: - Outdoor CPE: 1x 2.5GE PoE input port + companion indoor Wi-Fi 6 router is standard. - Indoor CPE: At least 1x 2.5GE or 1x 1GE LAN port + integrated Wi-Fi 6 is acceptable for consumer FWA tiers; multi-port is preferred for SME tiers. | Binding Ruling (Bid Bulletin No. 1)
25 | CPE | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Can it only support the eSIM MFF2 solution? | CONFIRMED. Physical Nano-SIM (4FF) with anti-theft locking slot is mandatory for mass-market deployment. eSIM (MFF2) is an acceptable optional enhancement. | Binding Ruling (Bid Bulletin No. 1)
25 | Wireless and Delivery | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | PIM is an indicator that is mainly concerned in FDD mode and does not need to be concerned in TDD mode. Is it necessary to change it to an OBUE (Operating Band Unwanted Emissions)indicator? | CONFIRMED. For synchronized TDD systems, Operating Band Unwanted Emissions (OBUE) per 3GPP TS 38.104 is the primary RF compliance benchmark. Passive Intermodulation (PIM <= -150 dBc) applies to external RF components (antennas, jumpers, connectors) to avoid receiver desensitization. | Binding Ruling (Bid Bulletin No. 1)
25 | Wireless and Delivery | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | We note that the distance from the planned site to the nearest tower ranges from 0.16 km to 1.94 km. Could the specific tower locations be provided for simulation calculations? | CONFIRMED. Candidate site coordinates (Lat/Long) and nominal tower heights are provided in Document 07. | Binding Ruling (Bid Bulletin No. 1)
25 | OSS & BSS Integration | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Will a separate monitoring platform be deployed, or can it be integrated with the existing AUTIN platform? | OSS INTEGRATION: Supplier must deliver EMS/NMS for domain element management, equipped with open northbound interfaces (REST APIs, SNMPv3, Kafka) for integration into Comclark/TelTech's enterprise monitoring umbrella (AUTIN). | Binding Ruling (Bid Bulletin No. 1)
25 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | The NEF is responsible for network capability exposure, and there are currently no commercial use cases. The SEPP is responsible for signaling security protection and topology hiding across PLMNs. Based on the experience of other projects, this function is also not mandatory. Therefore, it is recommended that the NEF and SEPP functions be treated as optional requirements or removed from the current RFP. | CONFIRMED. In Phase 1, NEF (Network Exposure) and SEPP (Security Edge Protection Proxy) are treated as optional roadmap functions and can be licensed in Phase 2 when enterprise API exposure and international roaming are activated. | Binding Ruling (Bid Bulletin No. 1)
25 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | Please Clarify whether the UPF needs to be deployed at the edge or co-deployed with the 5G Core at the central site. If the UPF needs to be deployed at the edge, specify the number of edge UPFs. It is recommended that the UPF form be not limited.Either 2U/4U/8U is ok | UPF DEPLOYMENT ARCHITECTURE: In Phase 1, 5G Core control plane and central UPF are co-deployed at the Tier-3 primary datacenter (Clark/Metro Manila). Edge UPF deployment is optional for future ultra-low-latency enterprise zones. Standard 2U, 4U, or 8U server form factors are acceptable. | Binding Ruling (Bid Bulletin No. 1)
25 | Core network & IT infrastructure and delivery | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | or hardware with the same capabilities such as Kunpeng server（E9000H-4/8） | CONFIRMED ACCEPTABLE. Carrier-grade server hardware with equivalent compute and throughput capabilities (including Enterprise ARM architecture (e.g. Kunpeng/Ampere) ARM architecture running certified carrier-grade Linux / Kubernetes) is fully acceptable for 5GC NFV infrastructure. | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)
25 | General Technical |  |  |  |  | Binding Ruling (Bid Bulletin No. 1)

## Part 3 - Bid Bulletin No. 2
COMCLARK NETWORK & TECHNOLOGY CORP. / TELTECH 5G FWA NATIONWIDE TURNKEY TENDER
BID BULLETIN NO. 2 — OFFICIAL CLARIFICATION RESPONSES (PART 3: 5GC, RAN, CIVIL, OSS/BSS & COMMERCIAL)
Item No. | Domain Classification | Document Reference | Section / Chapter Reference | Prospective Bidder Inquiry | Comclark / TelTech Official Response | Procurement Status
1 | 5G Core & IT Infrastructure (Lot 3) | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 1.2 ProgramLOT 3: CLOUD-NATIVE 5G CORE (5GC SA) & DATACENTER INFRASTRUCTURE | Please specify how much throughput is required for 1 million users in the first phase, and how much total throughput will be needed for 3 million users in the future. | For Phase 1 (1,000,000 registered subscribers / initial 300,000 active broadband households), the cloud-native 5G SA Core User Plane Function (UPF) must be dimensioned for an aggregated throughput of 300 Gbps to 500 Gbps, based on an average busy-hour throughput (ABHT) of 1.5–2.0 Mbps per active subscriber with a 15–20% peak concurrency factor. For the future 3,000,000 subscriber expansion, the 5G Core architecture must support horizontal auto-scaling of containerized UPF instances up to a total aggregated throughput of 1.5 Tbps without control plane redesign. | Binding Ruling (Bid Bulletin No. 2)
2 | RAN Equipment & Access Hardware (Lot 1) | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | We have obtained the latest document and found that column T in the table only contains tower IDs without specific latitude and longitude coordinates. Could you provide these tower's latitude and longitude coordinates to support simulation and construction evaluation? | Confirmed. High-precision WGS84 geographic coordinates (6 decimal places) for all nearest towers have been populated in Document 07 (07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx) across Tab 'All 5,000 Sites' and Batch 1 through Batch 5. As noted, these tower coordinates constitute confidential operator assets provided strictly under the RFP Non-Disclosure Agreement (NDA) solely for RF propagation modeling, link simulation, and construction feasibility assessment. | Binding Ruling (Bid Bulletin No. 2)
3 | RAN Equipment & Access Hardware (Lot 1) | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | The current capability does not support the frequency range of 1512~1517 MHz. the Contractor / Prospective Bidder requires more detailed RF specifications to conduct an evaluation. It is recommended to forward the NTC's demonstration spectrum requirements to the Contractor / Prospective Bidder, including the following information: the suppression level requirements for RF signals in the 1432~1457 MHz range and the suppression level requirements for RF signals above 1517 MHz. | Clarified and Directed. In accordance with National Telecommunications Commission (NTC) Memorandum Circular No. 006-11-2025 (https://ntc.gov.ph/wp-content/uploads/2025/MEMORANDUM_CIRCULAR/006-11-2025.pdf), applicable 3GPP specifications (TS 38.104 / TS 38.141), and international radio regulations, the technical baselines, boundary conditions, and mandatory RF conformance test requirements are established as follows: 1. Operational Channel Placement & Bandwidth Efficiency: - Operational Passband: 1457.0 MHz to 1517.0 MHz (single contiguous 60.0 MHz TDD carrier, Band n50). - Center Frequency: 1487.0 MHz (aligned on the standard 100 kHz 3GPP RF reference raster). - Transmission Numerology: 162 Physical Resource Blocks (PRBs) configured at 30 kHz Subcarrier Spacing (SCS), occupying 58.32 MHz active transmission bandwidth. - Spectral Efficiency: A single 60.0 MHz carrier provides 162 PRBs (97.2% frequency utilization), capturing +5.9% higher usable capacity and eliminating carrier aggregation complexity and inter-carrier guardband loss compared to 3x 20 MHz (153 PRBs total, 91.8% utilization). 2. Upper Boundary Separation & Satellite Protection (> 1517.0 MHz): - 1.0 MHz External Guardband: The 1517.0–1518.0 MHz block is reserved as an external guardband between the carrier edge (1517.0 MHz) and the NTC allocation ceiling (1518.0 MHz). - Effective Transition Margin: Combined with the internal 3GPP channel guardband of 840 kHz (for 60 MHz @ 30 kHz SCS), the physical separation from the outermost active subcarrier (1516.16 MHz) to the sensitive satellite downlink boundary (1518.0 MHz) is 1.84 MHz. - Mobile-Satellite Service (MSS) Protection: Out-of-band emissions (OOBE) into the adjacent maritime mobile-satellite service downlink band (1518.0–1525.0 MHz) must not exceed -30 dBm/MHz at the gNodeB antenna connector, strictly compliant with ITU-R M.2159-0 / WRC-15 Resolution 223 and 3GPP TS 38.104 Category B. 3. Lower Boundary Protection for Adjacent NPN (1432.0–1457.0 MHz): - Non-Public Networks Coexistence: Per NTC MC No. 006-11-2025, 1427.0–1457.0 MHz is allocated to Non-Public Networks (NPN). Unwanted emissions in the adjacent 1432.0–1457.0 MHz block must strictly meet 3GPP TS 38.104 Category B standards with an Adjacent Channel Leakage Ratio (ACLR >= 45 dB). 4. In-Band BSS Coexistence (1452.0–1492.0 MHz): - Pursuant to Section IV of NTC MC No. 006-11-2025, deployments overlapping the 1452.0–1492.0 MHz primary Broadcasting-Satellite Service (BSS) allocation must support remote power control, electrical downtilt adjustments (eRET), and interference coordination to avoid detrimental interference to licensed satellite earth stations. 5. Mandatory RF Conformance Test Requirements in Tender Submissions: - Shortlisted RAN bidders must submit certified third-party / factory laboratory RF conformance test reports under 3GPP TS 38.141-1 (Conducted) and TS 38.141-2 (Radiated) demonstrating: (a) Spectrum Emission Mask (SEM) compliance at maximum rated conducted power (+55 dBm / 320 W conducted); (b) ACLR measured at full 100% PRB load; (c) Operating Band Unwanted Emissions (OBUE) spectral mask plots across 1517.0–1559.0 MHz (proving the <= -30 dBm/MHz limit above 1518.0 MHz); (d) Spurious emissions across out-of-band ranges; (e) Manufacturer declaration of any required power de-rating / back-off or external high-Q cavity bandpass filtering needed to meet limits at full rated power, including link budget coverage impacts. 6. Mandatory Equipment Wideband Hardware Capability: - All proposed Baseband Units (BBU), Remote Radio Units (RRU) / Active Antenna Units (AAU), and Customer Premises Equipment (CPE) RF front-ends must natively support the full 3GPP Band n50 tuning range (1432.0–1517.0 MHz, 85 MHz Instantaneous Bandwidth / IBW) in hardware, reconfigurable via software without hardware swaps or tower truck rolls. | Binding Ruling (Bid Bulletin No. 2)
4 | Customer Premises Equipment (Lot 7) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | There is no ODU N50 product yet, and will take a long while for development. will we consider to launch the indoor N50 first | Confirmed. TelTech authorizes a phased CPE rollout: Bidders are permitted to offer high-performance 5G Indoor Units (IDU) with high-gain internal antennas (minimum 8–10 dBi equivalent) and external antenna port capability for initial Phase 1 deployments. Bidders must concurrently commit to a roadmap delivery for high-gain Outdoor Units (ODU, >= 12 dBi gain, IP67 weather-proofed) within 6 to 9 months of contract award. | Binding Ruling (Bid Bulletin No. 2)
5 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is there an existing BI/reporting system? If yes, please confirm if BSS doesn't need to provide basic report anymore. | Confirmed. The BSS/OSS platform must include native, automated BI reporting dashboards capable of generating scheduled reports (daily, weekly, monthly) in CSV, XLSX, and PDF formats for all operational, revenue, provisioning, and SLA metrics. Additionally, the platform must provide open REST APIs / secure database views to enable automated data pipeline ingestion into TelTech's enterprise analytics repository. | Binding Ruling (Bid Bulletin No. 2)
6 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Is there an existing contact center? Is there a need for a separate customer ticketing system? | Confirmed. TelTech is deploying a cloud-based Contact Center as a Service (CCaaS) platform. The Bidder's BSS/CRM solution must provide standard RESTful open APIs (supporting TM Forum Open APIs including TMF621 Customer Management, TMF622 Product Ordering, and TMF632 Party Management) to integrate seamlessly with TelTech's contact center for single-pane customer service, automated CTI screen-pops, and unified trouble ticketing. | Binding Ruling (Bid Bulletin No. 2)
7 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | How about VAS system? Does BSS need to integrate with existing SMS? | The BSS platform must include standard out-of-the-box integration capabilities (via standard SMPP v3.4 and RESTful SMS API) to interface with SMSC / SMS gateways for automated transactional messaging (one-time passwords [OTP], billing alerts, provisioning status, payment reminders, and outage notifications). Third-party SMS gateway connectivity and termination aggregators will be provided by TelTech. | Binding Ruling (Bid Bulletin No. 2)
8 | Civil Works & Site Siting (Lot 5) | 01_RFP_5G_FWA_Master_Tender_Document | LOT 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | We note your confirmation that the drone survey waiver is accepted. To align execution, please confirm the following: (a) TSSR photographic evidence shall be obtained 360° panoramic photography only via target installation height from towerco. Drone survey is not required for TSSR. (b) The acceptance criterion for site photographs is that they clearly depict the 360° surrounding environment (including neighbouring structures, potential obstructions, and general terrain) at a level sufficient for line-of-sight assessment. No specific camera resolution, focal length, or equipment type is required; standard photographic equipment available to the site survey team is acceptable. | Confirmed. For sites with existing towers (Class T1–T3), drone surveys shall be conducted to capture 360° panoramic photographic sweeps at antenna mounting height (and 20m, 30m, 40m AGL) to assess line-of-sight and structural clearances. Where local aviation restrictions (CAAP no-fly zones, military airspace, or adverse local weather) prohibit drone flights, manual panoramic photography taken by qualified tower riggers from the tower mounting platform is acceptable. | Binding Ruling (Bid Bulletin No. 2)
9 | Civil Works & Site Siting (Lot 5) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 4. CIVIL WORKS & STRUCTURAL ENGINEERING (CLASS T4 GREENFIELD SITES) | For 103 sites, Do we need to consider elevated foundation in the commercial directly? If Yes, please confirm the required height. If No, Is it will be consider as VO. | Clarified. Equipment pad foundation design for the 103 Class T4 Greenfield Monopole sites shall be determined by the site-specific hydrological survey and historical flood levels: (1) Standard Non-Flood Zone: Standard reinforced concrete equipment plinth with elevation of 300 mm (0.30 m) above finished grade level. (2) Flood-Prone Areas (50-year flood zone history): Elevated equipment platform raised 1.0 m to 1.5 m above finished grade. Civil construction works exceeding standard 300 mm plinth height necessitated by extreme local flood conditions shall be priced per the Master Rate Card (Appendix E) as an approved scope adjustment. | Binding Ruling (Bid Bulletin No. 2)
10 | Civil Works & Site Siting (Lot 5) | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | 1. Please suggest the refuel of fuel tank scope is under the Contractor / Prospective Bidder or not before we handover the site to TelTech (Finish acceptance). 2. If Yes, When we handover the site to TelTech, do we need to refuel the fuel tank to full. | Confirmed. Bidders are not required to provide a fully filled diesel fuel tank upon final site handover. The contractor is only responsible for supplying commissioning fuel necessary to perform the mandatory on-site load bank and generator acceptance testing (minimum 4-hour full-load burn-in). Following Provisional Acceptance Certificate (PAC), routine fuel replenishment transitions to TelTech's managed operations. | Binding Ruling (Bid Bulletin No. 2)
11 | Civil Works & Site Siting (Lot 5) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 2.4 Backhaul Transmission Path Survey | Do we need to provide a seperate mouting Pole for the Starlink? If yes, please speficy the size or diemension for the pole. | Confirmed. Where Starlink LEO satellite backhaul is designated for hybrid resilience, bidders shall provide a dedicated hot-dip galvanized mounting pipe (minimum 60 mm / 2.375 inch outer diameter, 2.5 mm wall thickness) with unobstructed sky visibility. For ground-based Greenfield sites, an integrated standoff arm on the equipment gantry or perimeter fence post is acceptable; for tower sites, a tower-leg standoff clamp shall be utilized. | Binding Ruling (Bid Bulletin No. 2)
12 | Civil Works & Site Siting (Lot 5) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 4. CIVIL WORKS & STRUCTURAL ENGINEERING (CLASS T4 GREENFIELD SITES) | Please suggest how many RRU and MW need to be consider in the monopole design. and please also provide the dimension and weight for the Antenna、RRU、MW which need to be consider in the design. | Confirmed. The Class T4 Greenfield Monopole structural design shall be calculated per NSCP 2015 (EIA/TIA-222-G) for 270 km/h wind gusts, accommodating a minimum design payload of: 6x 5G Remote Radio Units (RRUs), 1x Active Antenna Unit (AAU) or 3x directional sector antennas (approx. 2.0 m length each), up to 1.2 m² total projected windward surface area for microwave transmission antennas (equivalent to 1x 1.2m or 2x 0.6m parabolic dishes), and associated feeder cables, mounting brackets, and lightning protection rod. | Binding Ruling (Bid Bulletin No. 2)
13 | Civil Works & Site Siting (Lot 5) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines 03_Appendix_B_Commercial_Proposal_BoQ_Templates | 2.3 Power Infrastructure & Utility Audit TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | For the New monopole sites, please suggest the AC capacity we need to apply from Coop. | Confirmed. The electrical service entrance shall be dimensioned for a 100A, 230V single-phase (or 3-phase where commercially available) service drop. The contractor's scope of work includes installation of the weatherhead, service mast, utility-grade meter base, manual transfer switch (MTS), main AC distribution panel with Class I+II surge protective devices (SPD), and grounding grid. Final electric cooperative (EC/Meralco) utility energization and monthly power billing accounts shall be arranged and paid directly by TelTech. | Binding Ruling (Bid Bulletin No. 2)
14 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Regarding the CPE recovery rate (>= 70%), the Contractor / Prospective Bidder's 2-year warranty period allows for free replacement if any issues arise. Is such a service acceptable? The CPE recovery rate cannot be controlled. | Accepted and clarified. The >= 70% CPE Recovery Rate defined in the RFP applies strictly to churned subscriber recovery and reverse logistics (i.e. retrieving TelTech-owned CPE hardware from canceled or disconnected subscriber premises by field force teams), not OEM factory warranty returns. For defective CPE units under the 24-month Defect Liability Period (DLP), OEM free replacement applies for hardware failures due to manufacturing defects. Hardware damage resulting from proven subscriber misuse, vandalism, or force majeure shall be handled via spare parts replacement at the contracted master rate card. | Binding Ruling (Bid Bulletin No. 2)
15 | SLAs, KPIs & Acceptance Standards (App C) | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Regarding the MTTR、NAV、SPMS SLA, Due to the lack of live network conditions and other inputs, it is impossible to assess the achievability of KPIs: SLA is recommended to be finalized based on the actual values observed during the 6 months following acceptance and commissioning. | Confirmed. The SLA targets defined in Appendix C represent standard telecommunications industry benchmarks for enterprise 5G fixed wireless networks. For Phase 1, TelTech grants a 90-day post-PAC stabilization period for each rollout cluster, during which service credits / SLA penalties for network availability (NAV) and MTTR are waived while operational baselines and spares logistics are stabilized. | Binding Ruling (Bid Bulletin No. 2)
16 | Commercial Proposal & BoQ (Doc 06) | 06_RFP_Commercial_Price_Book_and_BoQ_Template | All | The portal "3. Commercial BoQ & Financing Lots 1-7" contents is different with the tender documents "06_RFP_Commercial_Price_Book_and_BoQ_Template" Kindly clarify which version to follow and filled? | Confirmed. The online portal Commercial BoQ tables and Excel Document 06 (06_RFP_Commercial_Price_Book_and_BoQ_Template.xlsx) have been fully harmonized. In case of any technical discrepancy, the official Excel Document 06 workbook shall serve as the governing commercial baseline. | Binding Ruling (Bid Bulletin No. 2)
17 | Commercial Proposal & BoQ (Doc 06) | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | Regarding the vendor submissions in the portal under "3. Commercial BoQ & Financing Lots 1-7": Since the current BOQ only reflects Phase 1 of the project, please clarify the pricing mechanism for the subsequent years: CAPEX: Assuming the Phase 1 price is fixed, will this exact pricing be applicable directly to Years 2 through 5? OPEX: Since vendors are only providing the OPEX for Phase 1, how should we calculate the following phases? For Phase 2, do we multiply the Phase 1 cost by 2? Does this same logic apply to the subsequent years up to Year 5? | Confirmed. Commercial proposals must quote firm, fixed unit rates and total pricing based on the complete 5,000 candidate site scope (Lot 1 through Lot 7). The project execution schedule follows the multi-batch rollout roadmap (Phase 1: 1,000 sites; Batches 2–5: 1,000 sites each). | Binding Ruling (Bid Bulletin No. 2)
18 | Commercial Proposal & BoQ (Doc 06) | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | As the USD to PHP exchange rate is fluctuating significantly right now, locking in a fixed rate poses a financial risk. We propose issuing all commercial documents (BoQ, PO, and Invoices) strictly in USD. If you prefer to pay in PHP, we will use the actual exchange rate on the date the payment is remitted. | Confirmed. Commercial unit rates in foreign currency (USD) and local currency (PHP) shall be evaluated using the benchmark exchange rate of USD 1.00 = PHP 55.00 as stipulated in Document 06. For imported telecom equipment (Lots 1, 2, 3, 7), contract billing and letters of credit (LC) may be settled in USD, eliminating currency conversion risk for offshore OEM suppliers. | Binding Ruling (Bid Bulletin No. 2)
19 | Commercial Proposal & BoQ (Doc 06) | Portal "3. Commercial BoQ & Financing Lots 1-7" | All | Kindly clarify for Commercial BoQ & Financing which need to be filled online: 1. If we are unable to provide a certain line item, should the bidder leave the unit price blank? 2. Where is the best place to add our pricing assumptions? | Confirmed. 1. Bidders are permitted to submit proposals on an individual Lot or combination of Lots (e.g. RAN only, Core only, Civil only). Bidders not bidding on specific lots shall leave those lot pricing sheets unpriced or mark 'NO BID'. 2. Custom or proprietary value-add components may be added using the custom line-item entry rows in Document 06. | Binding Ruling (Bid Bulletin No. 2)
20 | Service Level Indicators & Field Metrics | 01_RFP_5G_FWA_Master_Tender_Document | LOT | What is installation? In which scenarios is installation required? Is the Contractor / Prospective Bidder responsible for the installation? How to calculate the New Installation Dispatch Lead Time? | Clarified. 1. Installation Scope: Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. 2. First-Time-Right (FTR) Installation Rate Calculation: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to faulty installation, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
21 | Service Level Indicators & Field Metrics | 01_RFP_5G_FWA_Master_Tender_Document | LOT | How is the First-Time-Right (FTR) Installation Rate calculated? | Clarified. 1. Installation Scope: Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. 2. First-Time-Right (FTR) Installation Rate Calculation: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to faulty installation, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
22 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Since it is a managed service, why do we need to accept the OSS tools of the managed service? How to handle the tools after MS ends? | Clarified. Bidders delivering Managed Services (MS) are required to provide all specialized tool licenses, diagnostic suites, and automation software necessary to fulfill their contracted scope and meet SLA obligations during the 5-year MS term. Following expiration of the MS term, TelTech reserves the option to transition tool operation in-house under standard commercial software maintenance terms. | Binding Ruling (Bid Bulletin No. 2)
23 | SLAs, KPIs & Acceptance Standards (App C) | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/365 Nationwide) | Service creadit penalty (< threshold)-- does this threshold mean Minimum threshold or target standard? | Service Credit penalties are assessed when monthly performance drops below the Minimum Threshold (not the Target Standard). Performance between the Target Standard and Minimum Threshold triggers mandatory corrective action and root-cause analysis without financial liquidated damages. Service Credits apply only when monthly performance breaches the Minimum Threshold floor. | Binding Ruling (Bid Bulletin No. 2)
24 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | kindly provide formula , or is it " initial RRC connection rate X erab assignment success rate" | Per 3GPP TS 38.331 and ETSI standards, Call/Session Setup Success Rate (CSSR) is defined as: CSSR = [RRC Connection Setup Success Rate] x [QoS Flow / NG-C Setup Success Rate] x 100%. Where RRC Setup Success Rate = (Successful RRC Setup Completions / RRC Setup Requests excluding rejections) and QoS Flow Setup Success Rate = (Successful 5G QoS Flow Establishments / QoS Flow Establishment Requests). | Binding Ruling (Bid Bulletin No. 2)
25 | SLAs, KPIs & Acceptance Standards (App C) | 06_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/367 Nationwide) | busy hour means auto busy hour or fixed busy hour such as 19:00- 20:00? | Confirmed. Busy Hour is defined as Time-Consistent Busy Hour (TCBH) per 3GPP/ITU-T recommendations, determined on a per-cell basis as the continuous 60-minute interval exhibiting the highest combined uplink and downlink traffic volume over a 30-day rolling observation window. | Binding Ruling (Bid Bulletin No. 2)
26 | SLAs, KPIs & Acceptance Standards (App C) | 07_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/368 Nationwide) | 1. because there is " cell edge DL&UL user speed", is this drive test KPI ? user throughput means CPE throughput? 2. how to define cell edge here? | Confirmed. Cell-edge user speed is evaluated at the outer boundary of the designed coverage footprint (nominally RSRP between -95 dBm and -105 dBm). During acceptance, it is verified via stationary drive/walk tests and CPE performance logs. For operational KPI reporting, cell-edge performance is tracked via 5-percentile user throughput metrics extracted from gNodeB OSS performance counters. | Binding Ruling (Bid Bulletin No. 2)
27 | SLAs, KPIs & Acceptance Standards (App C) |  | 5.7 Radio Frequency (RF) Cluster Optimization | the target of cluster optimization is only for coverage outdoor target , any target for other KPIs such as throughput ? | Confirmed. Cluster optimization acceptance requires meeting both coverage and quality criteria: (1) Coverage: RSRP >= -95 dBm over >= 90% of the designated target populated settlement area; (2) Quality: SINR >= 3 dB over >= 90% of the cluster footprint; (3) Throughput: SSV speed targets verified at near, mid, and edge testing points; (4) Accessibility/Retainability: Cluster-wide CSSR >= 97% and Call Drop Rate (CDR) <= 1.5%. | Binding Ruling (Bid Bulletin No. 2)
28 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | for Near , mid and far location, suggest to based on simulation of typcial site ( antenna height, tilt, power ), and give proper distance of near , mid and far. or use RSRP level at -90, -100, -105 | Confirmed. The classification of Near (<500m), Mid (1.0–1.5 km), and Far (>=2.0 km) zones is established based on baseline RF propagation modeling for 30m nominal antenna height, adjusted during physical cluster drive testing and SSV based on local terrain, clutter, and morphology. | Binding Ruling (Bid Bulletin No. 2)
29 | RAN Equipment & Access Hardware (Lot 1) | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | From our general understanding, the rules for spectrum allocation are usually uniform nationwide. We would like to know whether TelTech has obtained authorization from the NTC to use 80 MHz of spectrum in areas outside the NCR. | Confirmed. The operational frequency authorization is governed by the National Telecommunications Commission (NTC) framework covering dedicated broadband wireless/private enterprise allocations within 1457.0 – 1518.0 MHz nationwide across the 5,000 candidate barangays. TelTech is finalizing formal commercial coordination with NTC; bidders shall design their RAN solutions for a standard 60 MHz TDD carrier (1457–1517 MHz) with 30 kHz Subcarrier Spacing (SCS). | Binding Ruling (Bid Bulletin No. 2)
30 | RAN Equipment & Access Hardware (Lot 1) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | Antennas are generally installed at relatively high positions on towers. Towers have requirements for the antenna's windward area and wind load capacity. Does TelTech have requirements for the antenna's windward area and wind load capacity? Based on the Contractor / Prospective Bidder's experience in delivering macro base stations, it is recommended that the windward area does not exceed 0.8 square meters. | Confirmed. For Class T1–T3 co-location sites, allowable antenna projected windward surface area, EPA (Effective Projected Area), and mounting centerline elevations are governed by each TowerCo's structural design limits and master lease agreements (MLA). Bidders shall submit equipment dimensions and weight specifications. For Class T4 Greenfield Monopoles, the tower structure must be designed to withstand NSCP 2015 wind speeds of up to 270 km/h (Category V typhoon resistance) accommodating 6 RRUs, 1 integrated active antenna (or 3 passive antennas), and up to 1.2 m² total microwave dish surface area. | Binding Ruling (Bid Bulletin No. 2)
31 | CPE Warranty & Reverse Logistics | 01_RFP_5G_FWA_Master_Tender_Document.pdf |  | Please confirm that the mandatory base Defect Liability Period (DLP / Hardware Warranty) for network equipment remains 24 months (2 years) from the date of PAC issuance per site/phase. Furthermore, please clarify whether the Extended Warranty and Spare Parts Management Service (SPMS) for Years 3–5 (as well as Years 6–10 for TCO calculation) should be quoted as separate, optional line items per Phase in the Appendix B Commercial BoQ. | Confirmed. The mandatory base Defect Liability Period (DLP / Hardware Warranty) for all active network equipment (Lots 1, 2, 3, 6) is confirmed as twenty-four (24) months (2 years) commencing from the issuance of the Provisional Acceptance Certificate (PAC). | Binding Ruling (Bid Bulletin No. 2)
32 | OEM Technical Training & Enablement | 01_RFP_5G_FWA_Master_Tender_Document.pdf |  | Please clarify whether formal OEM technical training and certification programs (covering 5G SA Core, Band n50 RAN, BSS/OSS, and FMS) are required for TelTech’s engineering and O&M personnel. If required, kindly provide the estimated number of trainees, preferred training location (e.g., local classroom in Manila/Clark vs. OEM headquarters), and confirm if this should be quoted as a dedicated line item in the Commercial BoQ. | Confirmed. Formal OEM technical training and certification programs covering 5G SA Core administration, Band n50 RAN RF optimization, OSS/BSS operations, and field maintenance are mandatory deliverables under Lot 5 / Services, dimensioned for at least 20 TelTech engineering personnel. | Binding Ruling (Bid Bulletin No. 2)
33 | Commercial Proposal & BoQ (Doc 06) | Portal "3. Commercial BoQ & Financing Lots 1-7" |  | For the Years 6–10 Cumulative OPEX (Managed Services and Extended Maintenance) in the 10-Year TCO evaluation, please confirm if bidders are permitted to include an annual Consumer Price Index (CPI) inflation indexation and FX adjustment clause to account for long-term macroeconomic fluctuations. | Confirmed. Bidders are permitted to quote Years 6–10 Managed Services and extended software maintenance as an optional annual escalation or fixed rate in the 10-Year Total Cost of Ownership (TCO) financial model. | Binding Ruling (Bid Bulletin No. 2)
34 | Commercial Proposal & BoQ (Doc 06) | Portal "3. Commercial BoQ & Financing Lots 1-7" |  | Are all unit prices in Commercial BOQ to be quoted in VAT Ex (Value Added Tax Exclusive)? | Confirmed. All unit rates and total prices in the Commercial BoQ must be quoted exclusive of 12% Philippine Value Added Tax (VAT-Exclusive). VAT will be added as a separate line item on billing invoices in accordance with Bureau of Internal Revenue (BIR) regulations. | Binding Ruling (Bid Bulletin No. 2)
35 | Power Systems & Facilities (Lot 2) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE | 1. Does it requires 2 Rectifier System per site or 2N Configuration? For ex: 1000 sites will be 2000 rectifier? 2. Do they need monitoring software to cover all sites?? 3. Please confirm weather the rectifier will be installed indoor or outdoor? 4. If outdoor installation, does all the 5000 sites is same set up? | Confirmed. (1) Each site requires one (1) high-efficiency outdoor-rated rectifier system with N+1 modular rectifier redundancy (e.g. 3x 50A modules providing 100A N+1 output). For ground-based Greenfield sites, an outdoor cabinet-housed rectifier is utilized; for tower co-location sites with limited footprint, blade/pole-mounted outdoor rectifiers are preferred. (2) Remote power monitoring software/controller with SNMPv3 / Modbus-TCP telemetry reporting into the centralized OSS is mandatory. | Binding Ruling (Bid Bulletin No. 2)
36 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | In the FM app, is it acceptable that the navigation function redirects to an external app, such as Google Maps? | Confirmed. In the Field Force Management (FMS) mobile application, deep-linking or redirecting to external standard navigation applications (e.g., Google Maps, Waze) for route guidance to site/subscriber coordinates is fully acceptable. | Binding Ruling (Bid Bulletin No. 2)
37 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | In the FM app, is the e-sign used only to collect users' handwritten signatures? If the electronic signature is used for strong authentication, a third-party SDK needs to be integrated. Currently, this is not supported. | Confirmed. Capturing the subscriber's handwritten signature on the mobile touchscreen interface at completion of installation/service is acceptable for job acceptance. Third-party digital signature authority (CA/PKI) integration is not mandatory for standard residential installation sign-offs. | Binding Ruling (Bid Bulletin No. 2)
38 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | For RF signal verification, it is recommended to use professional software such as Cellular-Z to obtain more accurate and professional policy data. | Confirmed. Any industry-standard, calibrated RF measurement application or handheld scanner (e.g., Cellular-Z, G-NetTrack Pro, Nemo Handy, or OEM-native diagnostic tool) is acceptable for post-installation RF verification, provided it logs accurate RSRP, RSRQ, SINR, and Cell ID parameters into the installation completion report. | Binding Ruling (Bid Bulletin No. 2)
39 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Does the installation order involve service provisioning? | Confirmed. Installation work orders executed by field technicians must trigger automated service provisioning in the BSS/OSS upon successful on-site RF validation and customer digital sign-off, regardless of whether installation is performed by OEM managed service teams or outsourced subcontractors. | Binding Ruling (Bid Bulletin No. 2)
40 | RAN Equipment & Access Hardware (Lot 1) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | The areas covered by the issued tender documents are mostly suburban or rural regions, which do not have the capability to use 5-meter HD maps. Should we switch to using 2D maps entirely for simulation planning? | Confirmed. For rural and remote Class T4 candidate barangays where 5-meter HD clutter maps are commercially unavailable, bidders are permitted to utilize standard 20m/25m digital elevation and land-use clutter datasets supplemented by satellite imagery and digital surface models (DSM) for macro-cellular nominal RF planning and cluster simulation. | Binding Ruling (Bid Bulletin No. 2)
41 | RAN Equipment & Access Hardware (Lot 1) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | According to the current site capability planning, the maximum average traffic of a single site does not exceed 1 Gbit/s. Therefore, the site does not need to support 2 x 10GE + 2 x 25GE interfaces. It is recommended that only the maximum capability be reserved, that is, 2 x 25GE interfaces. | Confirmed. An initial backhaul transport capacity of 1 Gbit/s per gNodeB site is acceptable for Day 1 traffic dimensioning. However, backhaul transmission interfaces (both optical transceivers and microwave links) must support hardware upgradeability to 10 Gbit/s via standard SFP+ interfaces to accommodate future multi-carrier expansion and subscriber growth. | Binding Ruling (Bid Bulletin No. 2)
42 | RAN Equipment & Access Hardware (Lot 1) | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | Considering there are 897 co-sited base stations, is it advisable to use cabinet BBUs instead of blade BBUs? | Confirmed. Blade BBUs (outdoor zero-footprint pole/wall-mounted baseband units) are strongly preferred across all 897 co-location sites to eliminate ground footprint leasing penalties, reduce shelter space requirements, and facilitate rapid deployment. Compact outdoor cabinet BBUs are acceptable only where indoor/shelter space is pre-contracted or where blade mounting is structurally restricted by the TowerCo. | Binding Ruling (Bid Bulletin No. 2)
43 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Regarding the CPE recovery rate (>= 70%), the Contractor / Prospective Bidder's 2-year warranty period allows for free replacement if any issues arise. Is such a service acceptable? The CPE recovery rate cannot be controlled. | Accepted and clarified. The >= 70% CPE Recovery Rate defined in the RFP applies strictly to churned subscriber recovery and reverse logistics (retrieving TelTech-owned CPE hardware from canceled subscriber premises), not OEM warranty returns. For defective CPE units under the 24-month DLP, OEM free replacement applies for manufacturing defects. Hardware damage resulting from proven subscriber misuse, vandalism, or force majeure shall be handled via spare parts replacement at the contracted master rate card. | Binding Ruling (Bid Bulletin No. 2)
44 | SLAs, KPIs & Acceptance Standards (App C) | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Regarding the MTTR、NAV、SPMS SLA, Due to the lack of live network conditions and other inputs, it is impossible to assess the achievability of KPIs: SLA is recommended to be finalized based on the actual values observed during the 6 months following acceptance and commissioning. | Confirmed. The SLA targets defined in Appendix C represent standard telecommunications industry benchmarks for enterprise 5G fixed wireless networks. For Phase 1, TelTech grants a 90-day post-PAC stabilization period for each rollout cluster, during which service credits / SLA penalties for network availability (NAV) and MTTR are waived while operational baselines and spares logistics are stabilized. | Binding Ruling (Bid Bulletin No. 2)
45 | Service Level Indicators & Field Metrics | 01_RFP_5G_FWA_Master_Tender_Document | LOT | What is installation? In which scenarios is installation required? Is the Contractor / Prospective Bidder responsible for the installation? How to calculate the New Installation Dispatch Lead Time? | Installation refers to Customer Premises Equipment (CPE) installation and commissioning at subscriber premises, encompassing RF site survey, optimal wall/pole/roof mounting, outdoor Cat6 cabling up to 30m, PoE injector, Wi-Fi router setup, zero-touch provisioning via Field Force App, and speed test sign-off. When Lot 5 (Turnkey Managed Services) is awarded, the bidder is responsible for installation; otherwise, TelTech's accredited installation contractors execute the work. | Binding Ruling (Bid Bulletin No. 2)
46 | Service Level Indicators & Field Metrics | 01_RFP_5G_FWA_Master_Tender_Document | LOT | How is the First-Time-Right (FTR) Installation Rate calculated? | The First-Time-Right (FTR) Installation Rate is calculated on a monthly rolling basis using the standard formula: FTR Rate = [(Total Completed Installations - Repeat Truck Rolls within 14 Days) / Total Completed Installations] x 100%. Any physical revisit required within 14 calendar days due to hardware failure, cabling defect, antenna misalignment, or provisioning failure counts against FTR. | Binding Ruling (Bid Bulletin No. 2)
47 | Service Level Indicators & Field Metrics | 01_RFP_5G_FWA_Master_Tender_Document | LOT | Please provide the procedures for CPE distribution, recovery, and maintenance. | TelTech's standard CPE lifecycle procedure operates as follows: (1) Distribution/Provisioning: Bulk CPE shipments arrive at TelTech's central staging warehouse, undergo barcode/IMEI ingestion into BSS/OSS asset tracking, and are dispatched to regional forward staging hubs. Installers scan serial numbers on-site and initiate automated zero-touch provisioning (TR-069 / USP via ACS). (2) Maintenance/RMA: Faulty units identified during subscriber trouble tickets are swapped by field technicians with buffer units from regional staging stock. Defective units are returned for RMA batching under the 24-month DLP warranty. (3) Recovery/Reverse Logistics: Upon subscriber service termination, BSS triggers a CPE Retrieval Work Order in the Field Force App. Recovered units undergo factory reset, testing, refurbishment, repackaging, and re-entry into active inventory. | Binding Ruling (Bid Bulletin No. 2)
48 | SLAs, KPIs & Acceptance Standards (App C) | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3. RADIO ACCESS NETWORK (RAN) OPERATIONAL KPIS & SERVICE CREDITS | Does NBD in SPMS mean sending to the Contractor / Prospective Bidder's regional spare parts warehouse? | NBD (Next Business Day) replacement under the Spare Parts Management Service (SPMS) requires the replacement spare part to be delivered to the designated regional forward logistics hub / TelTech regional maintenance center within the next business day (Monday through Saturday, cut-off time 15:00) following RMA dispatch notification. | Binding Ruling (Bid Bulletin No. 2)
49 | Digital OSS/BSS & Automation (Lot 4) | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Can the standalone OSS/BSS software scope be decoupled from the following indicators: New Installation Dispatch Lead Time, First-Time-Right (FTR) Installation Rate, and Churned CPE Hardware Recovery Rate. | Accepted and clarified. For standalone OSS/BSS software delivery (Lot 4), SLA commitments apply to software availability, transaction processing latency, and API throughput (e.g. system uptime >= 99.95%, work order dispatch generation < 5 seconds). Operational field performance indicators such as New Installation Dispatch Lead Time, First-Time-Right (FTR) Installation Rate, and Churned CPE Recovery Rate apply strictly to the Managed Services & Field Operations scope (Lot 5 / Appendix E) when awarded to the managed service provider. | Binding Ruling (Bid Bulletin No. 2)
50 | Civil Works & Site Siting (Lot 5) | APPENDIX E: SERVICES STATEMENT OF WORK & MASTER RATE CARD | 4. MASTER SERVICES PRICING SCHEDULE & COMMERCIAL RATE CARD | 1. Please suggest on which scenario we need to do tower retrofitting works, since towerco tower is belong to towerco to do retrofitting. 2. Tower retrofitting need to have retrofitting design first, and this scope are based on each site situation, case by case, Please suggest how to quote this item. | Confirmed. For Class T1–T3 co-location sites, tower structural strengthening is primary responsibility of the respective TowerCo under master co-location arrangements. However, to mitigate potential TowerCo lead time delays, bidders shall provide unit rate pricing in the Appendix E Master Rate Card for structural surveys, structural integrity assessments, engineering design, and structural reinforcement fabrication/installation in the event TelTech elects to self-execute retrofitting. | Binding Ruling (Bid Bulletin No. 2)
51 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | Suggest CSSR target 97%, minimum threshold 96; based on huawei global FWA network experience , RRC setup success rate 99% , and qos 98.5%； The CSSR further improvement is constrainted from terminal compatibility issues, the extent of network coverage, and transmission loss in indoor CPE. | Accepted. TelTech officially updates the nationwide Call/Session Setup Success Rate (CSSR) operational KPI as follows: Target Standard: 97.0% (revised from 99.0%); Minimum Threshold: 96.0% (revised from 97.5%). This adjustment accounts for real-world FWA CPE propagation environments while maintaining premium carrier-grade service reliability. | Binding Ruling (Bid Bulletin No. 2)
52 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | Suggest target 1.5%， maximum 2%； The same reason that KPI CDR further improvement is constrainted from terminal compatibility issues, the extent of network coverage, and transmission loss in indoor CPE. | Accepted. TelTech officially updates the nationwide Call Drop Rate (CDR) operational KPI as follows: Target Standard: <= 1.5% (revised from <= 0.5%); Maximum Threshold: <= 2.0% (revised from <= 1.0%). Service Credits apply only if monthly nationwide aggregate CDR exceeds 2.0%. | Binding Ruling (Bid Bulletin No. 2)
53 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | suggest to remove both KPIs , this is more factored by user behavior and user distribution ;also throughput already reflected in SSV KPI | Accepted in part. TelTech confirms that contractual financial liquidated damages / service credits shall not be assessed against daily instantaneous user throughput OSS counters. However, gNodeB scheduler throughput metrics (5-percentile and 50-percentile user throughput) shall remain active in OSS performance management for network traffic monitoring and capacity trigger planning. | Binding Ruling (Bid Bulletin No. 2)
54 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | There is no OSS KPI latency statistics; only drive tests are available, which have been reflected in SSV. | Accepted. TelTech confirms that the round-trip latency KPI (target <= 20 ms) shall be formally validated during Single Site Verification (SSV) and periodic cluster drive testing using standardized ping / TWAMP (Two-Way Active Measurement Protocol) test procedures between the test CPE and gNodeB / UPF test endpoints. | Binding Ruling (Bid Bulletin No. 2)
55 | SLAs, KPIs & Acceptance Standards (App C) | 05_Appendix_C_SLAs_KPIs_Liquidated_Damages | 3.1 Core Radio KPIs (Calculated 24/7/366 Nationwide) | suggest target 0.1%，0.2% max; and PDCP layer; | Accepted. Packet loss rate shall be formally evaluated at the PDCP (Packet Data Convergence Protocol) layer per 3GPP TS 38.314 standards, with updated KPI thresholds: Target Standard: <= 0.10%; Maximum Threshold: <= 0.20%. | Binding Ruling (Bid Bulletin No. 2)
56 | RAN Equipment & Access Hardware (Lot 1) | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | from last time clarification , converage feedback : SSV SPEED TARGETS PER DISTANCE ZONE: - Near Zone (< 500m): DL >= 200 Mbps / UL >= 30 Mbps. - Mid Zone (1.0 – 1.5 km): DL >= 100 Mbps / UL >= 20 Mbps. - Far / Cell Edge (>= 2.0 km): DL >= 25 Mbps / UL >= 5 Mbps (minimum SLA threshold). Suggest to be : Slot configuration: DL:UL=8：2(DDDDDDDSUU) and static test, >-80dBm: DL 200Mbps / UL 25Mbps [-80~-95)dBm: DL 100Mbps/UL 10Mbps [-95~-105)dBm: DL 35Mbps/UL 1.5Mbps | Accepted with clarification. TelTech approves the adoption of RSRP-correlated benchmark thresholds for static Single Site Verification (SSV) under a standard 8:2 (DDDDDDDSUU) or 7:3 TDD frame structure in a 60 MHz Band n50 channel: (1) Near Zone (RSRP >= -80 dBm): DL >= 200 Mbps / UL >= 25 Mbps; (2) Mid Zone (-95 dBm <= RSRP < -80 dBm): DL >= 100 Mbps / UL >= 10 Mbps; (3) Cell Edge Zone (-105 dBm <= RSRP < -95 dBm): DL >= 35 Mbps / UL >= 5 Mbps (UL minimum floor of 5 Mbps is maintained to ensure reliable TCP ACK and two-way interactive video traffic). Stationary SSV measurements shall be recorded using standard outdoor/indoor CPE units matching Lot 7 technical specifications. | Binding Ruling (Bid Bulletin No. 2)
57 | Backhaul & Transmission Interconnect | 01_RFP_5G_FWA_Master_Tender_Document | 2.3 Transmission & Backhaul Topology | 1, The SFP of Transmission devices for Interconnections with BBU will be provided by the Contractor / Prospective Bidder or TelTech/TelTech? 2, The SFP of BBU will be 25GE/10GE Adaptive Optical Module, the SFP of transmission device will be adaptive also, or specific ones and what types they will be(need confirm the transmission port capability also) 3, The related configurations on Transmission backhaul for BBU integration will be under TelTech or the Contractor / Prospective Bidder? | Confirmed. 1. SFP Supply Boundary: The RAN bidder is responsible for supplying optical transceivers (SFPs) for all BBU/gNodeB ports. TelTech/TelTech will provide the compatible optical transceivers for the customer-facing ports on the demarcation transmission device (IP-RAN router / cell site gateway / GPON ONT). 2. Optics Specification: BBU optical modules shall be dual-rate 10GE/25GE eCPRI/CPRI/Ethernet adaptive transceivers (supporting standard 1310nm Single-Mode Fiber, LC duplex connectors, up to 10 km reach). Demarcation switch ports provided by TelTech support auto-negotiation at 10GE and 25GE. 3. Configuration Responsibilities: The RAN bidder is responsible for end-to-end BBU interface configuration (VLAN tagging, IP addressing, QoS markings per DSCP matrix, and sync synchronization IEEE 1588v2 PTP / SyncE). TelTech/TelTech transmission engineers will configure the transport network (VLAN tunneling, MPLS-VPN / SRv6 L2/L3 transport) up to the BBU handoff port. | Binding Ruling (Bid Bulletin No. 2)