## Read Me
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA (Revision 2 Audited)
Author & Lead Architect: OLIVER TUNGOL ¦ Date: September 28, 2026 ¦ Comclark Network & Technology Corp. / TelTech
Overview | This Revision 2 workbook integrates Codex's independent spatial audit of Converge ICT's optical backbone (2,405 nodes & 4,401 fiber lines from the November 2024 KMZ).
Audited Fiber Screening | Every site is categorized into Classes A through F based on verified node candidates (1,296 points) and continuous screened cable routes:
Class A | Node <= 0.5 km: Direct drop connection candidate. First survey priority.
Class B | Node > 0.5 km and <= 1.0 km: Short node lateral candidate.
Class C | Line <= 0.5 km; Node > 1.0 km: Splice closure / line-tap survey candidate.
Class D | Other node or line <= 3.0 km: Route options evaluation (lateral vs line-tap).
Class E | Nearest node or line > 3.0 km and <= 5.0 km: Intermediate review candidate.
Class F | Nearest node and line > 5.0 km: Prime Starlink LEO satellite backhaul candidate.
BTS Radio Model | Standardized on Band n50 (1.5 GHz, 100 MHz TDD) with 3-Sector 8T8R MIMO AAUs / RRUs + Distributed BBU, sized @ 1,000 subscribers per BTS.
Rollout Sequencing | Batch 1 is 100% Fiber-First (919 Class A + 81 Class B sites in Commercial) ensuring immediate fiber proximity.
Dynamic Formulas | Dynamic workbook features live formula links for demand take-up, BTS capacity sizing, and screening classification.

## Executive Summary
5G FWA Executive Dashboard — DICT / UNDP GIDA (Rev 2 Audited)
Strategic 5-Batch Rollout Program ¦ Band n50 100 MHz ¦ 3-Sector 8T8R MIMO ¦ 1,000 Subs/BTS
TOTAL SITES |  | BATCH 1 POPULATION |  | BATCH 1 TARGET SUBS |  | PROGRAM TARGET SUBS |  | PEAK BTS CAPACITY
5,000 |  | 2,247,393 |  | 176,704 |  | 1,357,667 |  | 5,554
1,000 per Batch (5 Batches) |  | Phase 1 Direct Reach |  | @ 30% Market Take-Rate |  | Across Full 5,000 Sites |  | @ 1,000 Subs / 8T8R BTS
PHASE-BY-PHASE ROLLOUT & AUDITED TRANSMISSION PROFILE
Phase | Barangays | 2024 Population | 2024 Households | Subs @ 30% | Day 1 BTS | Peak BTS | Node <=1km (A+B) | Line <=500m (C) | Other <=3km (D) | Remote >3km (E+F)
Phase 1 (Batch 1) | 1000 | 2247393 | 588733 | 176704 | 1000 | 1031 | 189 | 89 | 191 | 531
Phase 2 (Batch 2) | 1000 | 2913679 | 760033 | 228053 | 1000 | 1076 | 351 | 88 | 98 | 463
Phase 3 (Batch 3) | 1000 | 2143214 | 563361 | 169087 | 1000 | 1020 | 559 | 133 | 95 | 213
Phase 4 (Batch 4) | 1000 | 3959964 | 1077334 | 323288 | 1000 | 1153 | 244 | 121 | 171 | 464
Phase 5 (Batch 5) | 1000 | 5575226 | 1534952 | 460535 | 1000 | 1274 | 169 | 124 | 201 | 506
TOTAL (5,000 SITES) | 5000 | 16839476 | 4524413 | 1357667 | 5000 | 5554 | 1512 | 555 | 756 | 2177

## Batch 1 (First 1,000)
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA — Batch 1 (First 1,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
1 | 1 | 1 | 0102817011 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Dilavo | 18.4314 | 120.5882 | R | 651 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.17 | 0.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 90.35 | 63.17 | 90.35 |  | C - Line within 0.5 km; node over 1 km | 3.17 | 0.03 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1
1 | 2 | 2 | 0102815010 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pancian | 18.5645 | 120.7878 | R | 2434 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 0.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 90.26 | 63.1 | 90.26 |  | C - Line within 0.5 km; node over 1 km | 3.67 | 0.22 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2
1 | 3 | 3 | 0102814010 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Santo Niño | 17.926 | 120.6727 | R | 1202 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.74 | 5.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 90.07 | 62.97 | 90.07 |  | D - Other node or line within 3 km | 1.63 | 1.49 | Line: SEGMENT 5 BANNA | Route options survey candidate: compare actual node lateral with approved line tap. | 3
1 | 4 | 4 | 0205704021 | Region II (Cagayan Valley) | Quirino | Maddela | San Dionisio I | 16.4081 | 121.8013 | R | 561 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.81 | 13.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 88.54 | 61.9 | 88.54 |  | F - Nearest node and line over 5 km | 12.81 | 13.92 | Node: GTI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4
1 | 5 | 5 | 1401113001 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Ansagan | 16.2119 | 120.5984 | R | 2370 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.04 | 9.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 88.51 | 61.88 | 88.51 |  | F - Nearest node and line over 5 km | 11.04 | 9.02 | Line: POZORRUBIO - ROSARIO PANGASINAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 5
1 | 6 | 6 | 0102931005 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Danac | 16.7793 | 120.5395 | R | 605 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.91 | 12.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 88.16 | 61.63 | 88.16 |  | F - Nearest node and line over 5 km | 14.91 | 12.82 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 6
1 | 7 | 7 | 1401105003 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Amlimay | 16.7039 | 120.8306 | R | 2411 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.78 | 4.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.95 | 61.49 | 87.95 |  | D - Other node or line within 3 km | 1.78 | 4.54 | Node: BGB002 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 7
1 | 8 | 8 | 0102814001 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Acnam | 17.9073 | 120.6337 | R | 779 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.87 | 61.43 | 87.87 |  | D - Other node or line within 3 km | 2.99 | 2.99 | Node: NEI001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 8
1 | 9 | 9 | 0403418006 | Region IV-A (CALABARZON) | Laguna | Paete | Ilaya del Norte | 14.3671 | 121.5212 | R | 2622 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.25 | 4.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.69 | 61.3 | 87.69 |  | E - Nearest node or line 3-5 km | 3.25 | 4.25 | Node: KYL002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 9
1 | 10 | 10 | 0102807001 | Region I (Ilocos Region) | Ilocos Norte | Carasi | Angset | 18.1398 | 120.8215 | R | 179 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.61 | 5.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.57 | 61.22 | 87.57 |  | F - Nearest node and line over 5 km | 6.9 | 6.88 | Line: SEGMENT 2 SOLSONA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 10
1 | 11 | 11 | 0102818011 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Estancia | 18.1589 | 120.7616 | R | 1853 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.95 | 3.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.46 | 61.15 | 87.46 |  | E - Nearest node or line 3-5 km | 4.95 | 3.77 | Line: SEGMENT 1 PIDDIG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 11
1 | 12 | 12 | 0102814006 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Caray | 17.9335 | 120.6862 | R | 837 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.28 | 2.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.45 | 61.13 | 87.45 |  | D - Other node or line within 3 km | 3.28 | 2.94 | Line: SEGMENT 5 BANNA | Route options survey candidate: compare actual node lateral with approved line tap. | 12
1 | 13 | 13 | 0102815011 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pasaleng | 18.5487 | 120.9363 | R | 1820 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.34 | 61.06 | 87.34 |  | B - Node 0.5-1 km | 0.98 | 0.04 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 13
1 | 14 | 14 | 0102818008 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Calambeg | 18.188 | 120.7249 | R | 1351 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 2.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.31 | 61.04 | 87.31 |  | D - Other node or line within 3 km | 2.8 | 2.63 | Line: SEGMENT 1 PIDDIG | Route options survey candidate: compare actual node lateral with approved line tap. | 14
1 | 15 | 15 | 0102814005 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Cabittauran | 17.9445 | 120.7063 | R | 1091 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.74 | 4.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.24 | 60.99 | 87.24 |  | E - Nearest node or line 3-5 km | 5.74 | 4.84 | Line: SEGMENT 5 BANNA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 15
1 | 16 | 16 | 0307104013 | Region III (Central Luzon) | Zambales | Castillejos | San Pablo | 14.9605 | 120.2527 | U | 11681 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.53 | 5.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.12 | 60.91 | 87.12 |  | F - Nearest node and line over 5 km | 6.53 | 5.31 | Line: SUBIC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 16
1 | 17 | 17 | 0102822012 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Maananteng | 18.1012 | 120.8113 | R | 1314 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.19 | 4.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 87.03 | 60.84 | 87.03 |  | E - Nearest node or line 3-5 km | 4.19 | 4.24 | Node: SSI001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 17
1 | 18 | 18 | 0102822013 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Manalpac | 18.0981 | 120.8115 | R | 2162 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.22 | 4.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.98 | 60.8 | 86.98 |  | E - Nearest node or line 3-5 km | 4.22 | 4.26 | Node: SSI001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 18
1 | 19 | 19 | 0307702022 | Region III (Central Luzon) | Aurora | Casiguran | Ditinagyan | 16.2154 | 122.0607 | R | 404 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.55 | 2.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.97 | 60.8 | 86.97 |  | D - Other node or line within 3 km | 2.23 | 30.49 | Node: CSA002 - TYPE 4 | Route options survey candidate: compare actual node lateral with approved line tap. | 19
1 | 20 | 20 | 0307702019 | Region III (Central Luzon) | Aurora | Casiguran | Bianuan | 16.2056 | 122.0424 | R | 2790 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.2 | 0.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.82 | 60.7 | 86.82 |  | A - Node within 0.5 km | 0.2 | 28.29 | Node: CSA002 - TYPE 4 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 20
1 | 21 | 21 | 0102817001 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Batuli | 18.3154 | 120.6153 | R | 459 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 0.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.65 | 60.58 | 86.65 |  | B - Node 0.5-1 km | 0.67 | 0.58 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 21
1 | 22 | 22 | 0102810003 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Kalaw | 18.5231 | 120.8064 | R | 654 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.28 | 1.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.63 | 60.57 | 86.63 |  | D - Other node or line within 3 km | 4.29 | 1.5 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 22
1 | 23 | 23 | 0102810004 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Quibel | 18.5245 | 120.8096 | R | 984 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.55 | 1.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.63 | 60.57 | 86.63 |  | D - Other node or line within 3 km | 4.55 | 1.72 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 23
1 | 24 | 24 | 0102810001 | Region I (Ilocos Region) | Ilocos Norte | Dumalneg | Cabaritan | 18.5224 | 120.8061 | R | 455 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.52 | 2.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.63 | 60.57 | 86.63 |  | D - Other node or line within 3 km | 4.28 | 1.52 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 24
1 | 25 | 25 | 0405627026 | Region IV-A (CALABARZON) | Quezon | Mauban | Remedios II | 14.1905 | 121.6642 | R | 404 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.22 | 13.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.5 | 60.48 | 86.5 |  | E - Nearest node or line 3-5 km | 4.22 | 13.77 | Node: SPQ001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 25
1 | 26 | 26 | 1401104005 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Ekip | 16.5249 | 120.8768 | R | 988 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.58 | 8.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.49 | 60.47 | 86.49 |  | F - Nearest node and line over 5 km | 7.58 | 8.79 | Node: BKB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 26
1 | 27 | 27 | 0405627030 | Region IV-A (CALABARZON) | Quezon | Mauban | San Jose | 14.1067 | 121.7921 | R | 596 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.18 | 10.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.42 | 60.41 | 86.42 |  | F - Nearest node and line over 5 km | 11.18 | 10.46 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 27
1 | 28 | 28 | 0405627001 | Region IV-A (CALABARZON) | Quezon | Mauban | Abo-abo | 14.1083 | 121.6969 | R | 196 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.02 | 20.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.16 | 60.24 | 86.16 |  | F - Nearest node and line over 5 km | 8.14 | 12.46 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 28
1 | 29 | 29 | 0307703004 | Region III (Central Luzon) | Aurora | Dilasag | Dimaseset | 16.3773 | 122.1566 | R | 1085 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.18 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 86.04 | 60.15 | 86.04 |  | F - Nearest node and line over 5 km | 5.18 | 46.91 | Node: DLA001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 29
1 | 30 | 30 | 0307704009 | Region III (Central Luzon) | Aurora | Dinalungan | Simbahan | 16.129 | 121.895 | R | 1295 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.07 | 0.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.97 | 60.1 | 85.97 |  | A - Node within 0.5 km | 0.07 | 11.17 | Node: DNA001 - TYPE 4A | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 30
1 | 31 | 31 | 0102803025 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Nagrebcan | 17.9094 | 120.5247 | R | 536 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.93 | 1.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.54 | 59.8 | 85.54 |  | E - Nearest node or line 3-5 km | 4.65 | 3.95 | Line: SEGMENT 3 (VIGAN - BATAC) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 31
1 | 32 | 32 | 1401113009 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Tabaan Norte | 16.3366 | 120.5093 | R | 1327 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.4 | 1.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.42 | 59.72 | 85.42 |  | D - Other node or line within 3 km | 3.4 | 1.39 | Line: TUBA | Route options survey candidate: compare actual node lateral with approved line tap. | 32
1 | 33 | 33 | 0205006015 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Rosario | 16.6152 | 121.3264 | R | 363 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.69 | 0.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.25 | 59.6 | 85.25 |  | C - Line within 0.5 km; node over 1 km | 6.69 | 0.01 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 33
1 | 34 | 34 | 0105536013 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Fianza | 16.1948 | 120.7777 | R | 988 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.55 | 17.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.23 | 59.59 | 85.23 |  | F - Nearest node and line over 5 km | 17.55 | 17.16 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 34
1 | 35 | 35 | PH0000035 | VI | Iloilo | Iloilo City | Gloria | 10.6966 | 122.5848 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.76 | 1.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.18 | 59.55 | 85.18 |  | D - Other node or line within 3 km | 2.65 | 1.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 35
1 | 36 | 36 | PH0000036 | VI | Iloilo | Iloilo City | Poblacion Molo | 10.687 | 122.5397 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 1.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.15 | 59.53 | 85.15 |  | B - Node 0.5-1 km | 0.53 | 3.55 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 36
1 | 37 | 37 | 0201517002 | Region II (Cagayan Valley) | Cagayan | Lasam | Alannay | 18.0602 | 121.5678 | R | 2212 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.21 | 6.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.05 | 59.46 | 85.05 |  | E - Nearest node or line 3-5 km | 4.21 | 6.93 | Node: LSC001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 37
1 | 38 | 38 | 0102814002 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Barangobong | 17.8417 | 120.5756 | R | 450 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.33 | 9.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.04 | 59.45 | 85.04 |  | F - Nearest node and line over 5 km | 12.33 | 9.35 | Line: SEGMENT 6 NUEVA ERA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 38
1 | 39 | 39 | 0201514014 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Magrafil | 18.2762 | 122.075 | R | 1256 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.15 | 4.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85.03 | 59.44 | 85.03 |  | E - Nearest node or line 3-5 km | 8.15 | 4.8 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 39
1 | 40 | 40 | 0105536005 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Cacabugaoan | 16.0706 | 120.7916 | R | 1415 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.99 | 7.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 85 | 59.42 | 85 |  | F - Nearest node and line over 5 km | 6.99 | 6.88 | Line: BINALONAN - UMINGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 40
1 | 41 | 41 | 0102915001 | Region I (Ilocos Region) | Ilocos Sur | Quirino | Banoen | 17.1573 | 120.6805 | R | 596 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.26 | 2.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.97 | 59.4 | 84.97 |  | D - Other node or line within 3 km | 2.26 | 1.91 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 41
1 | 42 | 42 | PH0000042 | VI | Iloilo | Iloilo City | San Jose | 10.6892 | 122.5171 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 2.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.77 | 59.26 | 84.77 |  | D - Other node or line within 3 km | 2.8 | 2.08 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 42
1 | 43 | 43 | 0102903022 | Region I (Ilocos Region) | Ilocos Sur | Bantay | San Mariano | 17.5525 | 120.4879 | R | 365 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.94 | 2.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.76 | 59.26 | 84.76 |  | D - Other node or line within 3 km | 7.94 | 2.61 | Line: SEGMENT 2 (CANDON - VIGAN) | Route options survey candidate: compare actual node lateral with approved line tap. | 43
1 | 44 | 44 | 0405647001 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Alitao | 13.9876 | 121.6288 | R | 133 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.16 | 0.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.74 | 59.24 | 84.74 |  | D - Other node or line within 3 km | 4.17 | 1.84 | Line: LILIW TO LUCENA AE | Route options survey candidate: compare actual node lateral with approved line tap. | 44
1 | 45 | 45 | 0201511024 | Region II (Cagayan Valley) | Cagayan | Claveria | Santiago | 18.5871 | 121.1149 | R | 364 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.01 | 2.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.66 | 59.19 | 84.66 |  | D - Other node or line within 3 km | 5.01 | 2.88 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Route options survey candidate: compare actual node lateral with approved line tap. | 45
1 | 46 | 46 | PH0000046 | VI | Iloilo | Iloilo City | San Felix | 10.7657 | 122.5645 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.63 | 59.17 | 84.63 |  | D - Other node or line within 3 km | 2.27 | 1.46 | Line: 3,477 | Route options survey candidate: compare actual node lateral with approved line tap. | 46
1 | 47 | 47 | 0403416007 | Region IV-A (CALABARZON) | Laguna | Majayjay | Banilad | 14.1365 | 121.5048 | R | 224 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.14 | 0.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.63 | 59.16 | 84.63 |  | C - Line within 0.5 km; node over 1 km | 3.81 | 0 | Line: SAN PABLO - LUCBAN AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 47
1 | 48 | 48 | 0205007018 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | New Gumiad | 16.0209 | 121.3026 | R | 650 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.75 | 24.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.41 | 59.01 | 84.41 |  | F - Nearest node and line over 5 km | 20.75 | 24.55 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 48
1 | 49 | 49 | 0102814011 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Uguis | 17.8944 | 120.5712 | R | 1111 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.74 | 9.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.25 | 58.9 | 84.25 |  | F - Nearest node and line over 5 km | 7.74 | 9.1 | Node: PNI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 49
1 | 50 | 50 | 0405623021 | Region IV-A (CALABARZON) | Quezon | Lucban | Mahabang Parang | 14.1179 | 121.5465 | R | 226 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.76 | 0.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.16 | 58.83 | 84.16 |  | C - Line within 0.5 km; node over 1 km | 1.34 | 0 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 50
1 | 51 | 51 | PH0000051 | VI | Iloilo | Iloilo City | Jalandoni-Wilson | 10.4947 | 122.0265 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.29 | 8.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.15 | 58.83 | 84.15 |  | F - Nearest node and line over 5 km | 31.29 | 8.18 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 51
1 | 52 | 52 | 0307101032 | Region III (Central Luzon) | Zambales | Botolan | Owaog-Nebloc | 15.2864 | 120.0781 | R | 440 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.56 | 4.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 84.13 | 58.82 | 84.13 |  | E - Nearest node or line 3-5 km | 11.67 | 4.77 | Line: BOTOLAN - CABANGAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 52
1 | 53 | 53 | 0403416008 | Region IV-A (CALABARZON) | Laguna | Majayjay | Banti | 14.1665 | 121.453 | R | 90 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.96 | 58.7 | 83.96 |  | D - Other node or line within 3 km | 3.2 | 1.97 | Line: PAGSANJAN TO LILIW | Route options survey candidate: compare actual node lateral with approved line tap. | 53
1 | 54 | 54 | 0405810005 | Region IV-A (CALABARZON) | Rizal | Pililla | Imatong | 14.4 | 121.3401 | R | 916 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 1.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.95 | 58.69 | 83.95 |  | E - Nearest node or line 3-5 km | 4.63 | 6.47 | Node: PLR002 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 54
1 | 55 | 55 | 0201511041 | Region II (Cagayan Valley) | Cagayan | Claveria | Taggat Sur | 18.6028 | 121.0582 | R | 2210 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 0.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.85 | 58.62 | 83.85 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.06 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 55
1 | 56 | 56 | 0102817034 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Tadao | 18.3823 | 120.694 | R | 395 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.18 | 9.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.85 | 58.62 | 83.85 |  | F - Nearest node and line over 5 km | 11.18 | 9.23 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 56
1 | 57 | 57 | 0102815007 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Dampig | 18.5404 | 120.8199 | R | 1041 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.43 | 2.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.84 | 58.61 | 83.84 |  | D - Other node or line within 3 km | 5.43 | 2.51 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Route options survey candidate: compare actual node lateral with approved line tap. | 57
1 | 58 | 58 | 0105527020 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cabaluyan 2nd | 15.6903 | 120.3343 | R | 1128 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.93 | 8.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.77 | 58.57 | 83.77 |  | E - Nearest node or line 3-5 km | 3.93 | 8.65 | Node: SCT001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 58
1 | 59 | 59 | 0102916004 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Baluarte | 17.0999 | 120.5209 | R | 671 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.83 | 6.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.76 | 58.56 | 83.76 |  | F - Nearest node and line over 5 km | 5.83 | 6.59 | Node: SDI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 59
1 | 60 | 60 | PH0000060 | II | Nueva Vizcaya | Dupax Del Norte | Binnuangan | 16.1847 | 121.2544 | R | 2485 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.1 | 24.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.68 | 58.5 | 83.68 |  | E - Nearest node or line 3-5 km | 4.1 | 24.89 | Node: DNV002 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 60
1 | 61 | 61 | 0601917030 | Region VI (Western Visayas) | Capiz | Tapaz | Minan | 11.2519 | 122.3664 | R | 555 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.85 | 20.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.65 | 58.48 | 83.65 |  | F - Nearest node and line over 5 km | 33.85 | 25.01 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 61
1 | 62 | 62 | 0205005019 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Bansing | 16.4597 | 121.1787 | R | 1083 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.59 | 3.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.44 | 58.34 | 83.44 |  | E - Nearest node or line 3-5 km | 4.59 | 3.99 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 62
1 | 63 | 63 | 0205007023 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Parai | 16.3117 | 121.1702 | R | 975 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.06 | 9.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.44 | 58.34 | 83.44 |  | F - Nearest node and line over 5 km | 7.06 | 9.71 | Node: DNV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 63
1 | 64 | 64 | 0304904026 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Santa Ines | 15.2344 | 120.8566 | R | 2373 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.32 | 1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.44 | 58.34 | 83.44 |  | D - Other node or line within 3 km | 3.32 | 1 | Line: SANTA ROSA TO ARAYAT | Route options survey candidate: compare actual node lateral with approved line tap. | 64
1 | 65 | 65 | 0102814007 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Garnaden | 17.9163 | 120.6235 | R | 722 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.79 | 3.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.42 | 58.32 | 83.42 |  | E - Nearest node or line 3-5 km | 3.79 | 3.7 | Line: SEGMENT 5 BANNA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 65
1 | 66 | 66 | 0401001007 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Barigon | 14.0001 | 120.9138 | R | 1872 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.29 | 9.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.41 | 58.31 | 83.41 |  | F - Nearest node and line over 5 km | 6.29 | 9.79 | Node: LRB002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 66
1 | 67 | 67 | 0600413005 | Region VI (Western Visayas) | Aklan | Malinao | Capataga | 13.3602 | 123.659 | R | 55 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.52 | 4.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.4 | 58.31 | 83.4 |  | D - Other node or line within 3 km | 2.17 | 1.93 | Line: TABACO - LIGAO AERIAL | Route options survey candidate: compare actual node lateral with approved line tap. | 67
1 | 68 | 68 | 0102817027 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Santa Catalina | 18.3064 | 120.6713 | R | 860 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.51 | 6.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.38 | 58.29 | 83.38 |  | E - Nearest node or line 3-5 km | 4.51 | 6.27 | Node: VNI001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 68
1 | 69 | 69 | 0401030016 | Region IV-A (CALABARZON) | Batangas | Talisay | Poblacion Barangay 6 | 14.1446 | 122.9444 | R | 420 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.19 | 5.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.36 | 58.27 | 83.36 |  | D - Other node or line within 3 km | 3.49 | 1.79 | Line: PAGBILAO - NAGA (UG + Aerial) | Route options survey candidate: compare actual node lateral with approved line tap. | 69
1 | 70 | 70 | 0102817028 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Santa Matilde | 18.3257 | 120.6833 | R | 427 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.99 | 6.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.35 | 58.27 | 83.35 |  | F - Nearest node and line over 5 km | 6.99 | 6.86 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 70
1 | 71 | 71 | 0102916005 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Baybayading | 17.1167 | 120.5711 | R | 193 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.1 | 8.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.33 | 58.25 | 83.33 |  | F - Nearest node and line over 5 km | 5.1 | 8.8 | Node: SDI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 71
1 | 72 | 72 | 0205704038 | Region II (Cagayan Valley) | Quirino | Maddela | Jose Ancheta | 16.3204 | 121.6471 | R | 1069 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.95 | 0.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.23 | 58.19 | 83.23 |  | D - Other node or line within 3 km | 3.95 | 0.95 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Route options survey candidate: compare actual node lateral with approved line tap. | 72
1 | 73 | 73 | PH0000073 | VI | Iloilo | Iloilo City | Divinagracia | 10.7105 | 122.5723 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.6 | 0.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.23 | 58.19 | 83.23 |  | B - Node 0.5-1 km | 0.6 | 0.55 | Line: 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 73
1 | 74 | 74 | 0201514006 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Cabiraoan | 18.3101 | 122.1093 | R | 3878 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.26 | 4.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.2 | 58.16 | 83.2 |  | E - Nearest node or line 3-5 km | 5.26 | 4.82 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 74
1 | 75 | 75 | PH0000075 | VI | Iloilo | Iloilo City | Seminario | 10.6941 | 122.5594 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 2.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.19 | 58.16 | 83.19 |  | D - Other node or line within 3 km | 1.86 | 1.32 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 75
1 | 76 | 76 | PH0000076 | VI | Iloilo | Iloilo City | East Timawa | 10.7501 | 122.5693 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 1.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.14 | 58.12 | 83.14 |  | B - Node 0.5-1 km | 0.59 | 0.05 | Line: 3,477 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 76
1 | 77 | 77 | 0201513056 | Region II (Cagayan Valley) | Cagayan | Gattaran | Bolos Point | 18.0294 | 122.1773 | R | 945 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.5 | 32.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.13 | 58.11 | 83.13 |  | F - Nearest node and line over 5 km | 31.5 | 32.08 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 77
1 | 78 | 78 | PH0000078 | VI | Iloilo | Iloilo City | Desamparados | 10.7695 | 122.5843 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.92 | 0.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.09 | 58.09 | 83.09 |  | C - Line within 0.5 km; node over 1 km | 1.91 | 0.15 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 78
1 | 79 | 79 | PH0000079 | VI | Iloilo | Iloilo City | Bakhaw | 10.7183 | 122.5545 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 83.05 | 58.06 | 83.05 |  | D - Other node or line within 3 km | 1.55 | 0.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 79
1 | 80 | 80 | 0601909026 | Region VI (Western Visayas) | Capiz | Panay | Lat-Asan | 11.5457 | 122.8632 | R | 823 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.46 | 7.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.96 | 58 | 82.96 |  | F - Nearest node and line over 5 km | 7.46 | 7.04 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 80
1 | 81 | 81 | 1404407002 | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | Bun-ayan | 16.9734 | 120.9094 | R | 761 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.56 | 0.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.96 | 58 | 82.96 |  | C - Line within 0.5 km; node over 1 km | 4.56 | 0.21 | Line: LA TRINIDAD-SAGADA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 81
1 | 82 | 82 | 0102911006 | Region I (Ilocos Region) | Ilocos Sur | Lidlidda | Labut | 17.2355 | 120.578 | R | 309 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.2 | 2.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.95 | 57.99 | 82.95 |  | C - Line within 0.5 km; node over 1 km | 6.05 | 0.03 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 82
1 | 83 | 83 | 1403208007 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Colayo | 17.3274 | 121.0294 | R | 371 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.53 | 13.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.94 | 57.99 | 82.94 |  | F - Nearest node and line over 5 km | 14.53 | 13.2 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 83
1 | 84 | 84 | 0500503038 | Region V (Bicol Region) | Albay | Daraga | Mi-isi | 13.1467 | 123.7168 | R | 1123 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.96 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.91 | 57.96 | 82.91 |  | B - Node 0.5-1 km | 0.56 | 0.24 | Line: BNANTAYANDA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 84
1 | 85 | 85 | PH0000085 | VI | Iloilo | Iloilo City | Macarthur | 10.6941 | 122.5594 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 2.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.88 | 57.94 | 82.88 |  | D - Other node or line within 3 km | 1.86 | 1.32 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 85
1 | 86 | 86 | PH0000086 | VI | Iloilo | Iloilo City | Liberation | 10.6933 | 122.5609 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.01 | 0.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.87 | 57.93 | 82.87 |  | D - Other node or line within 3 km | 2 | 1.27 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 86
1 | 87 | 87 | 1403201001 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Ababa-an | 17.5143 | 121.2842 | R | 420 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.65 | 11.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.84 | 57.91 | 82.84 |  | F - Nearest node and line over 5 km | 7.65 | 11.26 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 87
1 | 88 | 88 | PH0000088 | VI | Iloilo | Iloilo City | Villa Anita | 10.695 | 122.5636 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.6 | 1.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.8 | 57.89 | 82.8 |  | D - Other node or line within 3 km | 2.14 | 0.93 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 88
1 | 89 | 89 | 1404407005 | Cordillera Administrative Region (CAR) | Mountain Province | Sabangan | Capinitan | 16.95 | 120.9087 | R | 582 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.47 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.8 | 57.88 | 82.8 |  | C - Line within 0.5 km; node over 1 km | 4.47 | 0.05 | Line: LA TRINIDAD-SAGADA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 89
1 | 90 | 90 | 0307708009 | Region III (Central Luzon) | Aurora | San Luis | Dikapinisan | 15.5787 | 121.5381 | R | 1359 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.18 | 18.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.79 | 57.88 | 82.79 |  | F - Nearest node and line over 5 km | 18.18 | 18.18 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 90
1 | 91 | 91 | 0600406032 | Region VI (Western Visayas) | Aklan | Ibajay | Tagbaya | 11.8109 | 122.1309 | R | 1740 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.6 | 0.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.78 | 57.87 | 82.78 |  | F - Nearest node and line over 5 km | 20.6 | 26.93 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 91
1 | 92 | 92 | PH0000092 | VI | Iloilo | Iloilo City | Rizal (La Paz) | 10.6979 | 122.5488 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.37 | 2.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.74 | 57.85 | 82.74 |  | D - Other node or line within 3 km | 1.04 | 2.17 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 92
1 | 93 | 93 | 0405627034 | Region IV-A (CALABARZON) | Quezon | Mauban | San Roque | 14.2926 | 121.8185 | R | 160 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 19.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.73 | 57.83 | 82.73 |  | F - Nearest node and line over 5 km | 16.61 | 31.16 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 93
1 | 94 | 94 | 0600410013 | Region VI (Western Visayas) | Aklan | Madalag | Maria Cristina | 11.5232 | 122.2275 | R | 1171 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.41 | 15.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.63 | 57.77 | 82.63 |  | F - Nearest node and line over 5 km | 13.41 | 15.52 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 94
1 | 95 | 95 | 0102916014 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Madarang | 17.1592 | 120.5787 | R | 259 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.47 | 7.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.58 | 57.73 | 82.58 |  | E - Nearest node or line 3-5 km | 4.47 | 7.25 | Node: SDI001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 95
1 | 96 | 96 | PH0000096 | VI | Iloilo | Iloilo City | Delgado-Jalandoni-Bagumbayan | 10.6973 | 122.5174 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.47 | 0.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.58 | 57.73 | 82.58 |  | D - Other node or line within 3 km | 2.87 | 2.09 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Route options survey candidate: compare actual node lateral with approved line tap. | 96
1 | 97 | 97 | 0307708010 | Region III (Central Luzon) | Aurora | San Luis | Dimanayat | 15.5277 | 121.4959 | R | 978 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.13 | 23.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.57 | 57.73 | 82.57 |  | F - Nearest node and line over 5 km | 18.13 | 23.43 | Node: GBN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 97
1 | 98 | 98 | PH0000098 | VI | Iloilo | Iloilo City | Malipayon-Delgado | 10.6951 | 122.5421 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 3.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.56 | 57.72 | 82.56 |  | A - Node within 0.5 km | 0.49 | 2.96 | Node: ICI002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 98
1 | 99 | 99 | PH0000099 | VI | Iloilo | Iloilo City | Muelle Loney-Montes | 10.6855 | 122.5451 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 1.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.44 | 57.64 | 82.44 |  | B - Node 0.5-1 km | 0.63 | 3.14 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 99
1 | 100 | 100 | 1403209001 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Aciga | 17.607 | 121.3059 | R | 1010 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.66 | 10.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.43 | 57.62 | 82.43 |  | F - Nearest node and line over 5 km | 6.66 | 10.69 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 100
1 | 101 | 101 | PH0000101 | VI | Iloilo | Iloilo City | Edganzon | 10.7715 | 122.5702 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 0.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.39 | 57.6 | 82.39 |  | D - Other node or line within 3 km | 2.55 | 1.28 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 101
1 | 102 | 102 | 0205704037 | Region II (Cagayan Valley) | Quirino | Maddela | Villa Jose V Ylanan | 16.3626 | 121.754 | R | 467 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.4 | 7.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.39 | 57.6 | 82.39 |  | F - Nearest node and line over 5 km | 8.4 | 7.69 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 102
1 | 103 | 103 | PH0000103 | VI | Iloilo | Iloilo City | Mabolo-Delgado | 10.6888 | 122.5177 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.81 | 3.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.38 | 57.59 | 82.38 |  | D - Other node or line within 3 km | 2.74 | 2.16 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 103
1 | 104 | 104 | 0405627038 | Region IV-A (CALABARZON) | Quezon | Mauban | Santo Niño | 14.1895 | 121.7281 | R | 385 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.34 | 8.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.36 | 57.58 | 82.36 |  | D - Other node or line within 3 km | 1.58 | 19.14 | Node: MBQ001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 104
1 | 105 | 105 | 0201522009 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Kittag | 18.5066 | 121.2153 | R | 341 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.17 | 5.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.31 | 57.55 | 82.31 |  | F - Nearest node and line over 5 km | 6.17 | 5.86 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 105
1 | 106 | 106 | PH0000106 | X | Misamis Oriental | Cagayan De Oro City | Barangay 29 (Pob.) | 8.4802 | 124.6461 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.31 | 57.55 | 82.31 |  | D - Other node or line within 3 km | 1.09 | 0.75 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 106
1 | 107 | 107 | PH0000107 | VI | Iloilo | Iloilo City | Legaspi dela Rama | 10.7508 | 122.5903 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 0.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.31 | 57.54 | 82.31 |  | D - Other node or line within 3 km | 2.63 | 1.79 | Line: 3,477 | Route options survey candidate: compare actual node lateral with approved line tap. | 107
1 | 108 | 108 | PH0000108 | VI | Iloilo | Iloilo City | El 98 Castilla | 10.6932 | 122.5768 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 2.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.31 | 57.54 | 82.31 |  | D - Other node or line within 3 km | 2.49 | 1.18 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 108
1 | 109 | 109 | 1400116008 | Cordillera Administrative Region (CAR) | Abra | Manabo | San Juan Sur | 17.4382 | 120.691 | R | 705 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.88 | 19.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.28 | 57.52 | 82.28 |  | F - Nearest node and line over 5 km | 17.55 | 16.16 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 109
1 | 110 | 110 | PH0000110 | VI | Iloilo | Iloilo City | San Vicente | 10.7501 | 122.5693 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.36 | 1.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.24 | 57.5 | 82.24 |  | B - Node 0.5-1 km | 0.59 | 0.05 | Line: 3,477 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 110
1 | 111 | 111 | 0500502001 | Region V (Bicol Region) | Albay | Camalig | Anoling | 13.1984 | 123.6389 | R | 1060 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.41 | 5.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.19 | 57.46 | 82.19 |  | D - Other node or line within 3 km | 3.86 | 1.9 | Line: IRIGA - LEGAZPI | Route options survey candidate: compare actual node lateral with approved line tap. | 111
1 | 112 | 112 | PH0000112 | VI | Iloilo | Iloilo City | Inday | 10.6992 | 122.5475 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 1.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.19 | 57.46 | 82.19 |  | D - Other node or line within 3 km | 1.08 | 2.28 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 112
1 | 113 | 113 | PH0000113 | VI | Iloilo | Iloilo City | Sinikway | 10.6979 | 122.5554 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.9 | 2.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.12 | 57.41 | 82.12 |  | D - Other node or line within 3 km | 1.6 | 1.48 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 113
1 | 114 | 114 | PH0000114 | X | Misamis Oriental | Cagayan De Oro City | Barangay 9 (Pob.) | 8.4819 | 124.6094 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 1.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.11 | 57.4 | 82.11 |  | C - Line within 0.5 km; node over 1 km | 2.54 | 0.05 | Line: cdo-talakag | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 114
1 | 115 | 115 | PH0000115 | IV-B | Palawan | Puerto Princesa City | Model (Pob.) | 9.7386 | 118.7367 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 2.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.06 | 57.37 | 82.06 |  | A - Node within 0.5 km | 0.41 | 1.93 | Node: PPW002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 115
1 | 116 | 116 | 0102910007 | Region I (Ilocos Region) | Ilocos Sur | Gregorio del Pilar | Poblacion Norte | 17.1507 | 120.6116 | R | 571 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.32 | 3.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.05 | 57.36 | 82.05 |  | E - Nearest node or line 3-5 km | 7.26 | 3.79 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 116
1 | 117 | 117 | 1400101010 | Cordillera Administrative Region (CAR) | Abra | Bangued | Dangdangla | 17.599 | 120.6287 | R | 2037 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.23 | 0.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.03 | 57.35 | 82.03 |  | D - Other node or line within 3 km | 1.23 | 0.75 | Line: Bangued | Route options survey candidate: compare actual node lateral with approved line tap. | 117
1 | 118 | 118 | 0205703010 | Region II (Cagayan Valley) | Quirino | Diffun | Don Mariano Perez, Sr. | 16.4814 | 121.3772 | R | 712 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.48 | 15.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82.02 | 57.34 | 82.02 |  | F - Nearest node and line over 5 km | 7.48 | 15.16 | Node: QZV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 118
1 | 119 | 119 | 1403209006 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ballayangon | 17.5565 | 121.3176 | R | 1341 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.45 | 11.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 82 | 57.33 | 82 |  | D - Other node or line within 3 km | 2.45 | 11.53 | Node: PKK002 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 119
1 | 120 | 120 | PH0000120 | X | Misamis Oriental | Cagayan De Oro City | Barangay 17 (Pob.) | 8.4305 | 124.6697 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.96 | 57.3 | 81.96 |  | A - Node within 0.5 km | 0.42 | 4.71 | Node: COM011 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 120
1 | 121 | 121 | 1403209003 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ammacian | 17.6089 | 121.3447 | R | 1731 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.77 | 6.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.95 | 57.29 | 81.95 |  | F - Nearest node and line over 5 km | 5.77 | 6.59 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 121
1 | 122 | 122 | 0201514008 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Calayan | 18.282 | 122.0101 | R | 2054 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.94 | 57.28 | 81.94 |  | C - Line within 0.5 km; node over 1 km | 2.38 | 0.07 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 122
1 | 123 | 123 | 1403209014 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Limos | 17.5011 | 121.2912 | R | 936 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.15 | 9.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.92 | 57.27 | 81.92 |  | F - Nearest node and line over 5 km | 8.15 | 9.87 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 123
1 | 124 | 124 | PH0000124 | VI | Iloilo | Iloilo City | Roxas Village | 10.6944 | 122.5764 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 1.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.92 | 57.27 | 81.92 |  | D - Other node or line within 3 km | 2.34 | 1.04 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 124
1 | 125 | 125 | 0205704023 | Region II (Cagayan Valley) | Quirino | Maddela | San Martin | 16.3913 | 121.7801 | R | 958 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.28 | 11.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.9 | 57.26 | 81.9 |  | F - Nearest node and line over 5 km | 12.28 | 11.13 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 125
1 | 126 | 126 | 0401005085 | Region IV-A (CALABARZON) | Batangas | Batangas City | San Agustin Silangan, Isla Verde | 13.5614 | 121.0598 | R | 739 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.97 | 13.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.81 | 57.19 | 81.81 |  | F - Nearest node and line over 5 km | 7.97 | 13.2 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 126
1 | 127 | 127 | PH0000127 | VI | Iloilo | Iloilo City | Nonoy | 10.6826 | 122.5302 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.91 | 1.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.8 | 57.18 | 81.8 |  | D - Other node or line within 3 km | 1.63 | 3.67 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 127
1 | 128 | 128 | 0601917052 | Region VI (Western Visayas) | Capiz | Tapaz | Siya | 11.236 | 122.3444 | R | 827 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.46 | 23.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.79 | 57.18 | 81.79 |  | F - Nearest node and line over 5 km | 35.46 | 27.56 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 128
1 | 129 | 129 | 0307708007 | Region III (Central Luzon) | Aurora | San Luis | Dibayabay | 15.6338 | 121.583 | R | 746 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.53 | 14.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.76 | 57.16 | 81.76 |  | F - Nearest node and line over 5 km | 13.53 | 14.12 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 129
1 | 130 | 130 | 0405619025 | Region IV-A (CALABARZON) | Quezon | Gumaca | Laguna | 13.8685 | 122.1136 | R | 491 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.27 | 2.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.75 | 57.15 | 81.75 |  | C - Line within 0.5 km; node over 1 km | 6.07 | 0.05 | Line: AE UNQ001 TO CDQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 130
1 | 131 | 131 | 0405622045 | Region IV-A (CALABARZON) | Quezon | Lopez | Mabini | 13.8614 | 122.3177 | R | 105 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.54 | 3.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.7 | 57.12 | 81.7 |  | D - Other node or line within 3 km | 6.65 | 0.88 | Line: LZQ001 TO MCQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 131
1 | 132 | 132 | 0307113012 | Region III (Central Luzon) | Zambales | Santa Cruz | Lomboy | 15.7784 | 119.9426 | R | 1889 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.75 | 3.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.66 | 57.09 | 81.66 |  | E - Nearest node or line 3-5 km | 3.75 | 3.71 | Line: STA CRUZ MUNICIPALITY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 132
1 | 133 | 133 | PH0000133 | VI | Iloilo | Iloilo City | Kauswagan | 10.6951 | 122.5639 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.45 | 2.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.61 | 57.05 | 81.61 |  | D - Other node or line within 3 km | 2.12 | 0.9 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 133
1 | 134 | 134 | PH0000134 | X | Misamis Oriental | Cagayan De Oro City | Barangay 12 (Pob.) | 8.4804 | 124.6466 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 1.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.61 | 57.05 | 81.61 |  | D - Other node or line within 3 km | 1.04 | 0.71 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 134
1 | 135 | 135 | PH0000135 | VI | Iloilo | Iloilo City | Monica Blumentritt | 10.7097 | 122.5726 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.28 | 2.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.6 | 57.05 | 81.6 |  | B - Node 0.5-1 km | 0.68 | 0.61 | Line: 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 135
1 | 136 | 136 | 0405607084 | Region IV-A (CALABARZON) | Quezon | Calauag | Tamis | 14.1891 | 122.2595 | R | 612 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.34 | 13.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.59 | 57.04 | 81.59 |  | F - Nearest node and line over 5 km | 7.34 | 13.22 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 136
1 | 137 | 137 | PH0000137 | II | Isabela | Ilagan City | Villa Imelda | 17.108 | 122.0138 | R | 2276 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.48 | 10.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.58 | 57.03 | 81.58 |  | D - Other node or line within 3 km | 2.48 | 10.49 | Node: IGI003 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 137
1 | 138 | 138 | PH0000138 | IV-B | Palawan | Puerto Princesa City | Manggahan (Pob.) | 9.7378 | 118.7376 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 2.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.56 | 57.02 | 81.56 |  | B - Node 0.5-1 km | 0.53 | 1.94 | Node: PPW002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 138
1 | 139 | 139 | 0205703033 | Region II (Cagayan Valley) | Quirino | Diffun | Don Faustino Pagaduan | 16.5987 | 121.3896 | R | 521 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.13 | 4.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.52 | 56.99 | 81.52 |  | E - Nearest node or line 3-5 km | 7.13 | 4.79 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 139
1 | 140 | 140 | PH0000140 | X | Misamis Oriental | Cagayan De Oro City | Barangay 24 (Pob.) | 8.4589 | 124.7225 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 1.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.51 | 56.98 | 81.51 |  | D - Other node or line within 3 km | 5.29 | 1.92 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 140
1 | 141 | 141 | 1403213008 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao | 17.4077 | 121.4451 | U | 20300 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 0.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.51 | 56.98 | 81.51 |  | B - Node 0.5-1 km | 0.64 | 0.49 | Line: Untitled Path | Short node lateral candidate; confirm port/fiber capacity, access and route. | 141
1 | 142 | 142 | PH0000142 | X | Misamis Oriental | Cagayan De Oro City | Barangay 1 (Pob.) | 8.474 | 124.6252 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.49 | 56.97 | 81.49 |  | D - Other node or line within 3 km | 1.43 | 1.7 | Node: COM005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 142
1 | 143 | 143 | PH0000143 | X | Misamis Oriental | Cagayan De Oro City | Barangay 5 (Pob.) | 8.5028 | 124.6163 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 2.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.48 | 56.96 | 81.48 |  | A - Node within 0.5 km | 0.21 | 0.04 | Line: cdo-talakag | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 143
1 | 144 | 144 | PH0000144 | VI | Iloilo | Iloilo City | Osmeña | 10.6992 | 122.5475 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.63 | 4.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.46 | 56.95 | 81.46 |  | D - Other node or line within 3 km | 1.08 | 2.28 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 144
1 | 145 | 145 | PH0000145 | VI | Iloilo | Iloilo City | Tanza-Esperanza | 10.694 | 122.5592 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 1.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.46 | 56.95 | 81.46 |  | D - Other node or line within 3 km | 1.83 | 1.34 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 145
1 | 146 | 146 | 1401108002 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Beleng-Belis | 16.6489 | 120.6401 | R | 793 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.49 | 12.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.41 | 56.91 | 81.41 |  | F - Nearest node and line over 5 km | 5.49 | 12.87 | Node: KIB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 146
1 | 147 | 147 | 1404404007 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Dalican | 17.1225 | 120.9357 | R | 884 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.63 | 3.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.41 | 56.91 | 81.41 |  | E - Nearest node or line 3-5 km | 5.63 | 3.98 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 147
1 | 148 | 148 | 0401003039 | Region IV-A (CALABARZON) | Batangas | Balayan | Patugo | 14.0041 | 120.7845 | R | 2450 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.35 | 5.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.39 | 56.9 | 81.39 |  | F - Nearest node and line over 5 km | 6.35 | 5.91 | Line: TGY001 TO BYB001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 148
1 | 149 | 149 | PH0000149 | VI | Iloilo | Iloilo City | San Nicolas | 10.7389 | 122.5792 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.23 | 1.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.37 | 56.88 | 81.37 |  | D - Other node or line within 3 km | 1.53 | 1.23 | Line: 3,477 | Route options survey candidate: compare actual node lateral with approved line tap. | 149
1 | 150 | 150 | PH0000150 | VI | Iloilo | Iloilo City | Our Lady Of Lourdes | 10.71 | 122.5535 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 1.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.36 | 56.88 | 81.36 |  | D - Other node or line within 3 km | 1.64 | 1.19 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 150
1 | 151 | 151 | PH0000151 | X | Misamis Oriental | Cagayan De Oro City | Barangay 36 (Pob.) | 8.4497 | 124.6969 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.35 | 56.87 | 81.35 |  | D - Other node or line within 3 km | 3.81 | 2.33 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 151
1 | 152 | 152 | PH0000152 | VI | Iloilo | Iloilo City | Magsaysay | 10.7301 | 122.5449 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.28 | 1.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.32 | 56.85 | 81.32 |  | D - Other node or line within 3 km | 2.94 | 1.45 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 152
1 | 153 | 153 | PH0000153 | VI | Iloilo | Iloilo City | Flores | 10.7477 | 122.5633 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.61 | 0.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.28 | 56.82 | 81.28 |  | A - Node within 0.5 km | 0.45 | 0.44 | Line: 3,477 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 153
1 | 154 | 154 | 1402706015 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Inwaloy | 16.9737 | 121.1939 | R | 393 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.96 | 14.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.25 | 56.81 | 81.25 |  | D - Other node or line within 3 km | 2.96 | 17.78 | Node: MOF001 - TYPE 4 | Route options survey candidate: compare actual node lateral with approved line tap. | 154
1 | 155 | 155 | 0201516034 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Sta. Maria | 18.1829 | 121.6603 | R | 2451 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.87 | 1.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.25 | 56.8 | 81.25 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.04 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 155
1 | 156 | 156 | PH0000156 | X | Misamis Oriental | Cagayan De Oro City | Barangay 25 (Pob.) | 8.4758 | 124.6828 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.32 | 1.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.25 | 56.8 | 81.25 |  | B - Node 0.5-1 km | 0.97 | 0.16 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 156
1 | 157 | 157 | PH0000157 | X | Misamis Oriental | Cagayan De Oro City | Barangay 34 (Pob.) | 8.4758 | 124.6828 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.46 | 2.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.24 | 56.8 | 81.24 |  | B - Node 0.5-1 km | 0.97 | 0.16 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 157
1 | 158 | 158 | 0205008023 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Talbek | 16.0239 | 121.2118 | R | 542 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.16 | 25.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.19 | 56.76 | 81.19 |  | F - Nearest node and line over 5 km | 16.16 | 25.54 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 158
1 | 159 | 159 | 0307708008 | Region III (Central Luzon) | Aurora | San Luis | Dibut | 15.6676 | 121.5981 | R | 577 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11 | 10.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.18 | 56.76 | 81.18 |  | F - Nearest node and line over 5 km | 11 | 10.83 | Line: SEGMENT 49 (DIPACULAO - BALER) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 159
1 | 160 | 160 | PH0000160 | X | Misamis Oriental | Cagayan De Oro City | Consolacion | 8.4912 | 124.6458 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 0.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.18 | 56.75 | 81.18 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.42 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 160
1 | 161 | 161 | PH0000161 | VI | Iloilo | Iloilo City | Our Lady Of Fatima | 10.7235 | 122.5526 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.06 | 3.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.16 | 56.74 | 81.16 |  | D - Other node or line within 3 km | 2 | 0.55 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 161
1 | 162 | 162 | 0205701020 | Region II (Cagayan Valley) | Quirino | Aglipay | Diodol | 16.4385 | 121.5976 | R | 922 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.3 | 3.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.12 | 56.71 | 81.12 |  | E - Nearest node or line 3-5 km | 4.3 | 3.51 | Line: SEGMENT 47 (SANTIAGO - MADDELA) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 162
1 | 163 | 163 | PH0000163 | VI | Iloilo | Iloilo City | Alalasan Lapuz | 10.7036 | 122.5477 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.53 | 0.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.12 | 56.71 | 81.12 |  | D - Other node or line within 3 km | 1.53 | 2.1 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 163
1 | 164 | 164 | 0600410019 | Region VI (Western Visayas) | Aklan | Madalag | Panipiason | 11.4095 | 122.2485 | R | 1877 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.48 | 21.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.11 | 56.71 | 81.11 |  | F - Nearest node and line over 5 km | 21.48 | 21.32 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 164
1 | 165 | 165 | PH0000165 | X | Misamis Oriental | Cagayan De Oro City | Barangay 26 (Pob.) | 8.4305 | 124.6697 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.08 | 56.68 | 81.08 |  | A - Node within 0.5 km | 0.42 | 4.71 | Node: COM011 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 165
1 | 166 | 166 | 1003508027 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Sucodan | 8.0947 | 123.8849 | R | 826 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.06 | 1.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.06 | 56.67 | 81.06 |  | D - Other node or line within 3 km | 11.06 | 1.09 | Line: ILIGAN - PAGADIAN | Route options survey candidate: compare actual node lateral with approved line tap. | 166
1 | 167 | 167 | 1003508010 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Lumbac | 8.1112 | 123.8851 | R | 611 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.2 | 0.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.05 | 56.66 | 81.05 |  | C - Line within 0.5 km; node over 1 km | 12.13 | 0.11 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 167
1 | 168 | 168 | PH0000168 | X | Misamis Oriental | Cagayan De Oro City | Barangay 7 (Pob.) | 8.4857 | 124.6226 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 2.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.02 | 56.64 | 81.02 |  | D - Other node or line within 3 km | 2.13 | 1.32 | Line: cdo-talakag | Route options survey candidate: compare actual node lateral with approved line tap. | 168
1 | 169 | 169 | PH0000169 | X | Misamis Oriental | Cagayan De Oro City | Barangay 27 (Pob.) | 8.4497 | 124.6969 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 0.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.02 | 56.64 | 81.02 |  | D - Other node or line within 3 km | 3.81 | 2.33 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 169
1 | 170 | 170 | PH0000170 | X | Misamis Oriental | Cagayan De Oro City | Barangay 31 (Pob.) | 8.4702 | 124.7029 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.01 | 56.64 | 81.01 |  | C - Line within 0.5 km; node over 1 km | 3.23 | 0.04 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 170
1 | 171 | 171 | PH0000171 | VIII | Samar (Western Samar) | Catbalogan City | Manguehay | 11.811 | 124.8979 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.8 | 33.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 81.01 | 56.63 | 81.01 |  | F - Nearest node and line over 5 km | 61.22 | 61.15 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 171
1 | 172 | 172 | PH0000172 | VIII | Samar (Western Samar) | Catbalogan City | Cagutian | 11.8793 | 124.911 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.64 | 32.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.99 | 56.62 | 80.99 |  | F - Nearest node and line over 5 km | 68.81 | 68.75 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 172
1 | 173 | 173 | PH0000173 | X | Misamis Oriental | Cagayan De Oro City | Barangay 4 (Pob.) | 8.4805 | 124.591 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.08 | 3.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.98 | 56.61 | 80.98 |  | D - Other node or line within 3 km | 3.71 | 0.89 | Line: cdo-talakag | Route options survey candidate: compare actual node lateral with approved line tap. | 173
1 | 174 | 174 | PH0000174 | X | Misamis Oriental | Cagayan De Oro City | Barangay 35 (Pob.) | 8.4305 | 124.6697 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.47 | 1.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.96 | 56.6 | 80.96 |  | A - Node within 0.5 km | 0.42 | 4.71 | Node: COM011 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 174
1 | 175 | 175 | PH0000175 | VI | Iloilo | Iloilo City | Aguinaldo | 10.7474 | 122.5643 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.17 | 3.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.93 | 56.58 | 80.93 |  | A - Node within 0.5 km | 0.34 | 0.33 | Line: 3,477 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 175
1 | 176 | 176 | PH0000176 | VI | Iloilo | Iloilo City | Zamora-Melliza | 10.6936 | 122.576 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 1.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.92 | 56.57 | 80.92 |  | D - Other node or line within 3 km | 2.41 | 1.09 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 176
1 | 177 | 177 | 1403209005 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Ba-ay | 17.4833 | 121.2753 | R | 525 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.75 | 7.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.9 | 56.56 | 80.9 |  | F - Nearest node and line over 5 km | 10.75 | 7.78 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 177
1 | 178 | 178 | PH0000178 | III | Aurora | Maria | Ponglo | 9.2034 | 123.6206 | R | 483 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.72 | 20.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.9 | 56.56 | 80.9 |  | F - Nearest node and line over 5 km | 36.54 | 35.97 | Line: FRONTHAUL-BACONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 178
1 | 179 | 179 | PH0000179 | X | Misamis Oriental | Cagayan De Oro City | Barangay 8 (Pob.) | 8.4721 | 124.5925 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.31 | 2.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.9 | 56.55 | 80.9 |  | D - Other node or line within 3 km | 4.32 | 0.56 | Line: cdo-talakag | Route options survey candidate: compare actual node lateral with approved line tap. | 179
1 | 180 | 180 | PH0000180 | II | Nueva Vizcaya | Kasibu | Tokod | 16.3912 | 121.4419 | R | 1559 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.72 | 17.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.89 | 56.55 | 80.89 |  | F - Nearest node and line over 5 km | 16.72 | 17.88 | Node: CBQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 180
1 | 181 | 181 | PH0000181 | III | Nueva Ecija | Cabanatuan City | Barrera District (Pob.) | 15.4807 | 120.9674 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 0.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.89 | 56.55 | 80.89 |  | B - Node 0.5-1 km | 0.68 | 0.36 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 181
1 | 182 | 182 | 1003512004 | Region X (Northern Mindanao) | Lanao del Norte | Maigo | Inoma | 8.1315 | 123.9311 | R | 786 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.77 | 2.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.88 | 56.54 | 80.88 |  | C - Line within 0.5 km; node over 1 km | 17.55 | 0.05 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 182
1 | 183 | 183 | PH0000183 | VI | Iloilo | Iloilo City | Railway | 10.6824 | 122.5296 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.13 | 3.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.88 | 56.54 | 80.88 |  | D - Other node or line within 3 km | 1.7 | 3.61 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 183
1 | 184 | 184 | PH0000184 | VI | Iloilo | Iloilo City | Calubihan | 10.6982 | 122.5858 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 2.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.87 | 56.54 | 80.87 |  | D - Other node or line within 3 km | 2.61 | 1.64 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 184
1 | 185 | 185 | 0307706005 | Region III (Central Luzon) | Aurora | Dipaculao | Dianed | 16.0128 | 121.6723 | R | 577 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.53 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.86 | 56.53 | 80.86 |  | C - Line within 0.5 km; node over 1 km | 12.53 | 0.15 | Line: Route | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 185
1 | 186 | 186 | PH0000186 | X | Misamis Oriental | Cagayan De Oro City | Barangay 2 (Pob.) | 8.4739 | 124.6365 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 2.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.81 | 56.5 | 80.81 |  | A - Node within 0.5 km | 0.19 | 1.72 | Node: COM005 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 186
1 | 187 | 187 | 1403209022 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Taga | 17.5733 | 121.3647 | R | 2397 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.12 | 6.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.81 | 56.49 | 80.81 |  | E - Nearest node or line 3-5 km | 3.12 | 6.49 | Node: PKK002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 187
1 | 188 | 188 | PH0000188 | X | Misamis Oriental | Cagayan De Oro City | Barangay 30 (Pob.) | 8.4804 | 124.6466 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.43 | 0.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.81 | 56.49 | 80.81 |  | D - Other node or line within 3 km | 1.04 | 0.71 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 188
1 | 189 | 189 | 0401025018 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Alas-as | 16.0786 | 120.7759 | R | 2568 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 3.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.79 | 56.48 | 80.79 |  | F - Nearest node and line over 5 km | 6.71 | 6.91 | Node: TYP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 189
1 | 190 | 190 | PH0000190 | X | Misamis Oriental | Cagayan De Oro City | Barangay 32 (Pob.) | 8.4812 | 124.6631 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 4.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.78 | 56.48 | 80.78 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.22 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 190
1 | 191 | 191 | PH0000191 | VI | Iloilo | Iloilo City | Arsenal Aduana | 10.7 | 122.5655 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.51 | 3.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.78 | 56.48 | 80.78 |  | C - Line within 0.5 km; node over 1 km | 1.56 | 0.39 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 191
1 | 192 | 192 | PH0000192 | IV-A | Batangas | Lipa City | Poblacion Barangay 4 | 13.8943 | 121.1476 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.74 | 56.45 | 80.74 |  | C - Line within 0.5 km; node over 1 km | 4.9 | 0.24 | Line: TANAUAN - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 192
1 | 193 | 193 | 0201515021 | Region II (Cagayan Valley) | Cagayan | Iguig | San Lorenzo | 17.7479 | 121.7344 | R | 482 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.81 | 0.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.74 | 56.44 | 80.74 |  | C - Line within 0.5 km; node over 1 km | 5.8 | 0.3 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 193
1 | 194 | 194 | PH0000194 | X | Misamis Oriental | Cagayan De Oro City | Barangay 18 (Pob.) | 8.4497 | 124.6969 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.58 | 0.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.74 | 56.44 | 80.74 |  | D - Other node or line within 3 km | 3.81 | 2.33 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 194
1 | 195 | 195 | 1403214003 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Dacalan | 17.2276 | 121.2258 | R | 348 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.11 | 8.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.72 | 56.43 | 80.72 |  | F - Nearest node and line over 5 km | 9.11 | 8.9 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 195
1 | 196 | 196 | PH0000196 | X | Misamis Oriental | Cagayan De Oro City | Barangay 11 (Pob.) | 8.5092 | 124.6488 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 1.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.71 | 56.43 | 80.71 |  | D - Other node or line within 3 km | 1.42 | 0.64 | Line: HDD | Route options survey candidate: compare actual node lateral with approved line tap. | 196
1 | 197 | 197 | PH0000197 | VI | Iloilo | Iloilo City | Yulo-Arroyo | 10.682 | 122.5303 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 2.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.68 | 56.4 | 80.68 |  | D - Other node or line within 3 km | 1.66 | 3.7 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 197
1 | 198 | 198 | 1704005026 | MIMAROPA Region | Marinduque | Santa Cruz | Kinyaman | 13.0352 | 120.7928 | R | 380 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.89 | 27.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.66 | 56.39 | 80.66 |  | F - Nearest node and line over 5 km | 48.75 | 47.55 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 198
1 | 199 | 199 | 0201501002 | Region II (Cagayan Valley) | Cagayan | Abulug | Bagu | 18.4345 | 121.4687 | R | 2054 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.47 | 9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.64 | 56.38 | 80.64 |  | F - Nearest node and line over 5 km | 5.47 | 8.98 | Node: BLC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 199
1 | 200 | 200 | 0401025019 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Pulang-Bato | 14.5969 | 120.9714 | R | 2568 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 3.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.62 | 56.36 | 80.62 |  | D - Other node or line within 3 km | 1.12 | 1.02 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 200
1 | 201 | 201 | 0201501001 | Region II (Cagayan Valley) | Cagayan | Abulug | Alinunu | 18.4313 | 121.459 | R | 1211 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.23 | 7.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.61 | 56.35 | 80.61 |  | F - Nearest node and line over 5 km | 6.23 | 7.91 | Node: BLC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 201
1 | 202 | 202 | PH0000202 | X | Misamis Oriental | Cagayan De Oro City | Barangay 28 (Pob.) | 8.4921 | 124.743 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.1 | 4.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.6 | 56.35 | 80.6 |  | B - Node 0.5-1 km | 0.97 | 0.05 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 202
1 | 203 | 203 | PH0000203 | VI | Iloilo | Iloilo City | Kahirupan | 10.6816 | 122.5011 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 1.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.59 | 56.34 | 80.59 |  | D - Other node or line within 3 km | 2.61 | 1.36 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 203
1 | 204 | 204 | PH0000204 | VI | Iloilo | Iloilo City | Timawa Tanza II | 10.6974 | 122.551 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 5.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.57 | 56.33 | 80.57 |  | D - Other node or line within 3 km | 1.17 | 1.96 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 204
1 | 205 | 205 | PH0000205 | X | Misamis Oriental | Cagayan De Oro City | Barangay 33 (Pob.) | 8.4589 | 124.7225 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.7 | 2.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.57 | 56.32 | 80.57 |  | D - Other node or line within 3 km | 5.29 | 1.92 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 205
1 | 206 | 206 | PH0000206 | III | Aurora | Maria | Suguit | 9.228 | 123.6665 | R | 483 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.58 | 19.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.55 | 56.31 | 80.55 |  | F - Nearest node and line over 5 km | 40.69 | 40.48 | Line: PROPOSED AERIAL FOC- 58.765km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 206
1 | 207 | 207 | 1401111005 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Colalo | 16.9129 | 120.7664 | R | 1676 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.27 | 0.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.54 | 56.31 | 80.54 |  | C - Line within 0.5 km; node over 1 km | 7.27 | 0.16 | Line: PROPOSED 96C FOC - BUGIAS TO CERVANTES | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 207
1 | 208 | 208 | 1403211016 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Bulbol | 17.5416 | 121.5767 | R | 1062 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.24 | 5.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.52 | 56.29 | 80.52 |  | F - Nearest node and line over 5 km | 5.24 | 5.1 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 208
1 | 209 | 209 | PH0000209 | VI | Iloilo | Iloilo City | Infante | 10.767 | 122.58 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.7 | 1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.49 | 56.27 | 80.49 |  | C - Line within 0.5 km; node over 1 km | 2.31 | 0.11 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 209
1 | 210 | 210 | PH0000210 | III | Aurora | Maria | Dialatman | 9.1624 | 123.6645 | R | 483 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.86 | 21.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.47 | 56.26 | 80.47 |  | F - Nearest node and line over 5 km | 42.35 | 41.48 | Line: FRONTHAUL-BACONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 210
1 | 211 | 211 | 1380400007 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Flores | 14.6621 | 120.9488 | U | 3925 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.47 | 56.26 | 80.47 |  | B - Node 0.5-1 km | 0.71 | 0.88 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 211
1 | 212 | 212 | 1403213027 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Naneng | 17.4054 | 121.2692 | R | 734 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18 | 0.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.47 | 56.25 | 80.47 |  | D - Other node or line within 3 km | 18 | 0.66 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 212
1 | 213 | 213 | 1403214007 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Lubo | 17.2621 | 121.231 | R | 497 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.72 | 7.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.46 | 56.25 | 80.46 |  | F - Nearest node and line over 5 km | 8.72 | 7.65 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 213
1 | 214 | 214 | PH0000214 | X | Misamis Oriental | Cagayan De Oro City | Barangay 19 (Pob.) | 8.4921 | 124.743 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.54 | 2.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.45 | 56.24 | 80.45 |  | B - Node 0.5-1 km | 0.97 | 0.05 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 214
1 | 215 | 215 | 1403214011 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Poblacion | 17.3 | 121.2333 | R | 295 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.83 | 7.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.45 | 56.24 | 80.45 |  | F - Nearest node and line over 5 km | 9.83 | 7.18 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 215
1 | 216 | 216 | 0307706004 | Region III (Central Luzon) | Aurora | Dipaculao | Calaocan | 16.1287 | 121.7909 | R | 620 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.14 | 0.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.44 | 56.24 | 80.44 |  | C - Line within 0.5 km; node over 1 km | 6.14 | 0.14 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 216
1 | 217 | 217 | 0600406008 | Region VI (Western Visayas) | Aklan | Ibajay | Batuan | 11.7988 | 122.1371 | R | 1266 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.35 | 1.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.44 | 56.23 | 80.44 |  | F - Nearest node and line over 5 km | 19.35 | 25.81 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 217
1 | 218 | 218 | 1403214014 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Anggacan Sur | 17.3014 | 121.2398 | R | 174 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.52 | 8.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.43 | 56.23 | 80.43 |  | F - Nearest node and line over 5 km | 10.52 | 7.86 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 218
1 | 219 | 219 | PH0000219 | NIR | Negros Occidental | Bacolod City | Barangay 38 (Pob.) | 10.6463 | 122.9546 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.78 | 1.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.4 | 56.21 | 80.4 |  | D - Other node or line within 3 km | 2.31 | 0.8 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 219
1 | 220 | 220 | PH0000220 | VI | Iloilo | Iloilo City | Jalandoni Estate-Lapuz | 10.7026 | 122.575 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.35 | 56.17 | 80.35 |  | C - Line within 0.5 km; node over 1 km | 1.46 | 0.4 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 220
1 | 221 | 221 | 1705314003 | MIMAROPA Region | Palawan | Magsaysay | Canipo | 10.9805 | 120.9635 | R | 1217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 109.15 | 109.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.31 | 56.15 | 80.31 |  | F - Nearest node and line over 5 km | 109.15 | 109.1 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 221
1 | 222 | 222 | 1403214006 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Taloctoc | 17.2759 | 121.3784 | R | 365 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.46 | 12.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.29 | 56.13 | 80.29 |  | F - Nearest node and line over 5 km | 11.51 | 14.26 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 222
1 | 223 | 223 | 1705305004 | MIMAROPA Region | Palawan | Bataraza | Culandanum | 8.644 | 117.4618 | R | 5613 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 185.36 | 187.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.28 | 56.13 | 80.28 |  | F - Nearest node and line over 5 km | 185.36 | 187.37 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 223
1 | 224 | 224 | PH0000224 | VI | Iloilo | Iloilo City | Lapuz Norte | 10.6973 | 122.5489 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.45 | 3.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.28 | 56.12 | 80.28 |  | B - Node 0.5-1 km | 1 | 2.18 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 224
1 | 225 | 225 | 1400118019 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Yuyeng | 17.5528 | 120.5697 | R | 423 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.26 | 56.11 | 80.26 |  | B - Node 0.5-1 km | 0.84 | 0.42 | Line: CABLE LAYED | Short node lateral candidate; confirm port/fiber capacity, access and route. | 225
1 | 226 | 226 | 1705314001 | MIMAROPA Region | Palawan | Magsaysay | Alcoba | 11.0102 | 120.8193 | R | 809 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 125.23 | 125.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.24 | 56.09 | 80.24 |  | F - Nearest node and line over 5 km | 125.23 | 125.18 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 226
1 | 227 | 227 | PH0000227 | X | Misamis Oriental | Cagayan De Oro City | Barangay 14 (Pob.) | 8.4812 | 124.6631 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.94 | 0.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.23 | 56.09 | 80.23 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.22 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 227
1 | 228 | 228 | PH0000228 | NIR | Negros Occidental | Bacolod City | Barangay 19 (Pob.) | 10.6578 | 122.9344 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.13 | 0.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.21 | 56.07 | 80.21 |  | D - Other node or line within 3 km | 2.2 | 0.58 | Line: TALISAY CITY - KABANGKALAN | Route options survey candidate: compare actual node lateral with approved line tap. | 228
1 | 229 | 229 | PH0000229 | X | Lanao Del Norte | Iligan City | Kalilangan | 8.1978 | 124.3897 | R | 2318 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.77 | 15.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.2 | 56.07 | 80.2 |  | F - Nearest node and line over 5 km | 16.77 | 15.26 | Line: CDO - ILIGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 229
1 | 230 | 230 | PH0000230 | VI | Iloilo | Iloilo City | Libertad-Lapuz | 10.6974 | 122.551 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.44 | 1.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.2 | 56.06 | 80.2 |  | D - Other node or line within 3 km | 1.17 | 1.96 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 230
1 | 231 | 231 | 0601917028 | Region VI (Western Visayas) | Capiz | Tapaz | Maliao | 11.3526 | 122.3585 | R | 850 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.82 | 22.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.19 | 56.06 | 80.19 |  | F - Nearest node and line over 5 km | 22.82 | 22.41 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 231
1 | 232 | 232 | PH0000232 | VI | Iloilo | Iloilo City | Laguda | 10.719 | 122.5429 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.44 | 1.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.18 | 56.06 | 80.18 |  | D - Other node or line within 3 km | 2.8 | 1.69 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 232
1 | 233 | 233 | 0600412013 | Region VI (Western Visayas) | Aklan | Malay | Napaan | 11.8956 | 121.923 | R | 968 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.37 | 4.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.17 | 56.04 | 80.17 |  | F - Nearest node and line over 5 km | 6.37 | 51.44 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 233
1 | 234 | 234 | 0201514002 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Batangan | 18.2825 | 122.0027 | R | 2268 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.16 | 0.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.13 | 56.02 | 80.13 |  | D - Other node or line within 3 km | 2.16 | 0.77 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Route options survey candidate: compare actual node lateral with approved line tap. | 234
1 | 235 | 235 | PH0000235 | X | Misamis Oriental | Cagayan De Oro City | Barangay 20 (Pob.) | 8.5092 | 124.6488 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.68 | 0.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.1 | 56 | 80.1 |  | D - Other node or line within 3 km | 1.42 | 0.64 | Line: HDD | Route options survey candidate: compare actual node lateral with approved line tap. | 235
1 | 236 | 236 | PH0000236 | VI | Iloilo | Iloilo City | Timawa Tanza I | 10.6928 | 122.5489 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.34 | 4.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.08 | 55.99 | 80.08 |  | B - Node 0.5-1 km | 0.71 | 2.36 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 236
1 | 237 | 237 | 0201516025 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Maxingal | 18.2119 | 121.6657 | R | 2741 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 0.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.08 | 55.99 | 80.08 |  | C - Line within 0.5 km; node over 1 km | 1.85 | 0.05 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 237
1 | 238 | 238 | PH0000238 | X | Misamis Oriental | Cagayan De Oro City | Barangay 16 (Pob.) | 8.4758 | 124.6828 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 5.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.07 | 55.97 | 80.07 |  | B - Node 0.5-1 km | 0.97 | 0.16 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 238
1 | 239 | 239 | 1403214008 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Upper Lubo | 17.3093 | 121.2378 | R | 333 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.51 | 12.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.06 | 55.97 | 80.06 |  | F - Nearest node and line over 5 km | 10.71 | 7.49 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 239
1 | 240 | 240 | 0201514009 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Caroan | 18.2682 | 121.9154 | R | 1293 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.36 | 2.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.04 | 55.96 | 80.04 |  | D - Other node or line within 3 km | 2.36 | 2.32 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Route options survey candidate: compare actual node lateral with approved line tap. | 240
1 | 241 | 241 | 0205008021 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Sanguit | 16.1396 | 121.1557 | R | 1147 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.96 | 20.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.02 | 55.94 | 80.02 |  | E - Nearest node or line 3-5 km | 3.96 | 20.28 | Node: DSV001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 241
1 | 242 | 242 | 0105527061 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Pacalat | 15.7425 | 120.2765 | R | 1026 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.63 | 15.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.02 | 55.94 | 80.02 |  | F - Nearest node and line over 5 km | 7.63 | 15.98 | Node: MMP001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 242
1 | 243 | 243 | 0603023008 | Region VI (Western Visayas) | Iloilo | Janiuay | Barasalon | 11.0104 | 122.3566 | R | 1537 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.55 | 17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.01 | 55.94 | 80.01 |  | F - Nearest node and line over 5 km | 18.55 | 16.94 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 243
1 | 244 | 244 | 0806417010 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Hipantag | 10.4859 | 124.98 | R | 251 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.1 | 1.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80.01 | 55.93 | 80.01 |  | F - Nearest node and line over 5 km | 29.03 | 23.97 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 244
1 | 245 | 245 | 0603023006 | Region VI (Western Visayas) | Iloilo | Janiuay | Atimonan | 11.0512 | 122.3587 | R | 1064 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.57 | 19.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80 | 55.93 | 80 |  | F - Nearest node and line over 5 km | 20.57 | 19.29 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 245
1 | 246 | 246 | PH0000246 | NIR | Negros Occidental | Bacolod City | Barangay 21 (Pob.) | 10.5996 | 122.9733 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 1.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 80 | 55.93 | 80 |  | E - Nearest node or line 3-5 km | 3.73 | 3.49 | Line: SAN CARLOS CITY - TALISAY CITY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 246
1 | 247 | 247 | 0205015002 | Region II (Cagayan Valley) | Nueva Vizcaya | Alfonso Castaneda | Galintuja | 15.8114 | 121.3238 | R | 1036 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.46 | 2.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.99 | 55.92 | 79.99 |  | D - Other node or line within 3 km | 16.46 | 2.4 | Line: BALER - PANTABANGAN | Route options survey candidate: compare actual node lateral with approved line tap. | 247
1 | 248 | 248 | 0600406005 | Region VI (Western Visayas) | Aklan | Ibajay | Aquino | 11.8161 | 122.119 | R | 3505 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22 | 0.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.99 | 55.92 | 79.99 |  | F - Nearest node and line over 5 km | 22 | 28.35 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 248
1 | 249 | 249 | 1705309032 | MIMAROPA Region | Palawan | Coron | Barangay VI | 12.0505 | 120.1531 | U | 5280 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 104.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.98 | 55.92 | 79.98 |  | D - Other node or line within 3 km | 1.2 | 104.26 | Node: CNW002-BP | Route options survey candidate: compare actual node lateral with approved line tap. | 249
1 | 250 | 250 | PH0000250 | NIR | Negros Occidental | Bacolod City | Barangay 15 (Pob.) | 10.6401 | 122.9679 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.97 | 55.9 | 79.97 |  | B - Node 0.5-1 km | 0.98 | 0.74 | Line: TALISAY - BACOLOD (REDUNDANCY) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 250
1 | 251 | 251 | PH0000251 | VI | Iloilo | Iloilo City | Sampaguita | 10.7005 | 122.5653 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.96 | 55.9 | 79.96 |  | C - Line within 0.5 km; node over 1 km | 1.5 | 0.37 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 251
1 | 252 | 252 | PH0000252 | IV-A | Batangas | Lipa City | Poblacion Barangay 9 | 13.9129 | 121.146 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.26 | 0.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.93 | 55.88 | 79.93 |  | C - Line within 0.5 km; node over 1 km | 3.85 | 0.17 | Line: TANAUAN - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 252
1 | 253 | 253 | 0105527025 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cacaoiten | 15.6701 | 120.3242 | R | 522 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.21 | 9.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.92 | 55.87 | 79.92 |  | F - Nearest node and line over 5 km | 6.21 | 9.2 | Node: SCT001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 253
1 | 254 | 254 | PH0000254 | NIR | Negros Occidental | Bacolod City | Barangay 37 (Pob.) | 10.6578 | 122.9344 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 0.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.92 | 55.87 | 79.92 |  | D - Other node or line within 3 km | 2.2 | 0.58 | Line: TALISAY CITY - KABANGKALAN | Route options survey candidate: compare actual node lateral with approved line tap. | 254
1 | 255 | 255 | 0405619056 | Region IV-A (CALABARZON) | Quezon | Gumaca | Villa Tañada | 13.9112 | 122.1818 | R | 135 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.43 | 1.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.92 | 55.87 | 79.92 |  | C - Line within 0.5 km; node over 1 km | 8.09 | 0.03 | Line: GCQ001 TO TKQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 255
1 | 256 | 256 | 0806010014 | Region VIII (Eastern Visayas) | Samar | Marabut | Tinabanan | 11.2076 | 125.1874 | R | 2034 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.42 | 18.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.91 | 55.87 | 79.91 |  | F - Nearest node and line over 5 km | 19.42 | 19.41 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 256
1 | 257 | 257 | PH0000257 | IX | Zamboanga Del Sur | Zamboanga City | Pangapuyan | 6.9178 | 122.1815 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.93 | 6.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.91 | 55.86 | 79.91 |  | F - Nearest node and line over 5 km | 11.93 | 6.91 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 257
1 | 258 | 258 | PH0000258 | VI | Iloilo | Iloilo City | President Roxas | 10.7558 | 122.573 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.66 | 2.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.9 | 55.86 | 79.9 |  | C - Line within 0.5 km; node over 1 km | 1.34 | 0.08 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 258
1 | 259 | 259 | PH0000259 | VI | Iloilo | Iloilo City | Cuartero | 10.7494 | 122.5692 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.87 | 55.84 | 79.87 |  | B - Node 0.5-1 km | 0.51 | 0.02 | Line: 3,477 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 259
1 | 260 | 260 | 1400126002 | Cordillera Administrative Region (CAR) | Abra | Tubo | Amtuagan | 17.3064 | 120.7302 | R | 511 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.61 | 13.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.87 | 55.84 | 79.87 |  | F - Nearest node and line over 5 km | 19.61 | 13.3 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 260
1 | 261 | 261 | PH0000261 | II | Nueva Vizcaya | Alfonso Castaneda | Cauayan | 15.9722 | 121.3565 | R | 1594 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.65 | 20.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.85 | 55.82 | 79.85 |  | F - Nearest node and line over 5 km | 23.65 | 20.22 | Line: BALER - PANTABANGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 261
1 | 262 | 262 | 0205006009 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Pinya | 16.6844 | 121.3232 | R | 787 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.57 | 4.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.83 | 55.81 | 79.83 |  | E - Nearest node or line 3-5 km | 5.57 | 4.46 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 262
1 | 263 | 263 | 1403214013 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Upper Taloctoc | 17.3383 | 121.2262 | R | 348 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.66 | 5.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.79 | 55.78 | 79.79 |  | F - Nearest node and line over 5 km | 11.66 | 5.04 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 263
1 | 264 | 264 | 0203133007 | Region II (Cagayan Valley) | Isabela | San Pablo | Caddangan/Limbauan | 17.431 | 121.8574 | R | 1703 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.92 | 6.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.79 | 55.78 | 79.79 |  | F - Nearest node and line over 5 km | 8.92 | 6.01 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 264
1 | 265 | 265 | 0205706004 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Guino | 16.1514 | 121.244 | R | 1563 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.97 | 26.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.78 | 55.77 | 79.78 |  | F - Nearest node and line over 5 km | 6.97 | 26.61 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 265
1 | 266 | 266 | PH0000266 | III | Nueva Ecija | Cabanatuan City | Quezon District (Pob.) | 15.5026 | 120.9559 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.57 | 0.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.78 | 55.77 | 79.78 |  | D - Other node or line within 3 km | 2.39 | 0.78 | Line: TALAVERA - MULTI NET | Route options survey candidate: compare actual node lateral with approved line tap. | 266
1 | 267 | 267 | 0203130017 | Region II (Cagayan Valley) | Isabela | San Manuel | Sandiat East | 17.0721 | 121.6412 | R | 1432 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.95 | 1.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.76 | 55.76 | 79.76 |  | D - Other node or line within 3 km | 2.95 | 1.83 | Line: ROXAS - CABATUAN | Route options survey candidate: compare actual node lateral with approved line tap. | 267
1 | 268 | 268 | 0300803010 | Region III (Central Luzon) | Bataan | City of Balanga | Dangcol | 14.6637 | 120.4686 | R | 1855 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.89 | 3.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.75 | 55.75 | 79.75 |  | E - Nearest node or line 3-5 km | 7.89 | 3.5 | Line: Bagac-Pilar AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 268
1 | 269 | 269 | 1401108010 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Gasweling | 16.5787 | 120.5082 | R | 1032 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.18 | 8.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.72 | 55.73 | 79.72 |  | F - Nearest node and line over 5 km | 9.18 | 8.28 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 269
1 | 270 | 270 | 1108204033 | Region XI (Davao Region) | Davao de Oro | Maco | New Leyte | 7.4043 | 126.0561 | R | 2939 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.68 | 18.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.71 | 55.73 | 79.71 |  | F - Nearest node and line over 5 km | 22.68 | 18.81 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 270
1 | 271 | 271 | 1403209023 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pinococ | 17.6505 | 121.4687 | R | 800 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.11 | 5.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.71 | 55.72 | 79.71 |  | F - Nearest node and line over 5 km | 5.11 | 5 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 271
1 | 272 | 272 | PH0000272 | VI | Iloilo | Iloilo City | Lopez Jaena Sur | 10.7106 | 122.5719 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.71 | 55.72 | 79.71 |  | B - Node 0.5-1 km | 0.56 | 0.51 | Line: 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 272
1 | 273 | 273 | PH0000273 | X | Misamis Oriental | Cagayan De Oro City | Barangay 23 (Pob.) | 8.4812 | 124.6631 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.49 | 2.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.68 | 55.7 | 79.68 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.22 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 273
1 | 274 | 274 | 1380601018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 18 | 14.6017 | 120.9642 | U | 2042 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.5 | 39.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.66 | 55.69 | 79.66 |  | B - Node 0.5-1 km | 0.82 | 0.8 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 274
1 | 275 | 275 | PH0000275 | VI | Iloilo | Iloilo City | West Timawa | 10.6912 | 122.5348 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.68 | 2.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.66 | 55.69 | 79.66 |  | B - Node 0.5-1 km | 0.87 | 3.86 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 275
1 | 276 | 276 | 0201514013 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Isca | 18.236 | 121.9773 | R | 1572 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.81 | 1.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.62 | 55.67 | 79.62 |  | D - Other node or line within 3 km | 3.81 | 1.24 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Route options survey candidate: compare actual node lateral with approved line tap. | 276
1 | 277 | 277 | PH0000277 | IV-B | Palawan | Puerto Princesa City | Masikap (Pob.) | 9.5472 | 118.644 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.53 | 3.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.61 | 55.65 | 79.61 |  | F - Nearest node and line over 5 km | 23.65 | 25.47 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 277
1 | 278 | 278 | 1381400002 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Balong-Bato | 14.6063 | 121.0224 | U | 7657 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.42 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.59 | 55.64 | 79.59 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.24 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 278
1 | 279 | 279 | PH0000279 | VI | Iloilo | Iloilo City | Punong-Lapuz | 10.7188 | 122.554 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.83 | 5.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.58 | 55.63 | 79.58 |  | D - Other node or line within 3 km | 1.62 | 0.61 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 279
1 | 280 | 280 | 0203131023 | Region II (Cagayan Valley) | Isabela | San Mariano | Minanga | 17.0004 | 122.0312 | R | 4822 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 18.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.58 | 55.63 | 79.58 |  | D - Other node or line within 3 km | 2.56 | 18.3 | Node: SOI001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 280
1 | 281 | 281 | 0203131012 | Region II (Cagayan Valley) | Isabela | San Mariano | Dibuluan | 16.9981 | 122.1082 | R | 1948 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.22 | 25.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.58 | 55.63 | 79.58 |  | F - Nearest node and line over 5 km | 10.22 | 25.39 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 281
1 | 282 | 282 | PH0000282 | X | Misamis Oriental | Cagayan De Oro City | Barangay 37 (Pob.) | 8.4921 | 124.743 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 1.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.55 | 55.61 | 79.55 |  | B - Node 0.5-1 km | 0.97 | 0.05 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 282
1 | 283 | 283 | PH0000283 | NIR | Negros Occidental | Bacolod City | Barangay 18 (Pob.) | 10.6506 | 122.9478 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.15 | 2.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.54 | 55.61 | 79.54 |  | D - Other node or line within 3 km | 1.88 | 0.97 | Line: FOC 144C FROM HH-0022 TO HH-0041 | Route options survey candidate: compare actual node lateral with approved line tap. | 283
1 | 284 | 284 | PH0000284 | VI | Iloilo | Iloilo City | Luna (La Paz) | 10.715 | 122.5645 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.4 | 0.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.53 | 55.6 | 79.53 |  | A - Node within 0.5 km | 0.4 | 0.12 | Line: 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 284
1 | 285 | 285 | PH0000285 | IV-A | Batangas | Lipa City | Poblacion Barangay 5 | 13.9122 | 121.1574 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.25 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.52 | 55.6 | 79.52 |  | D - Other node or line within 3 km | 3.7 | 1.32 | Line: TANAUAN - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 285
1 | 286 | 286 | 1404401010 | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | Ogo-og | 17.0436 | 121.192 | R | 454 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.52 | 16.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.51 | 55.58 | 79.51 |  | F - Nearest node and line over 5 km | 8.52 | 17.52 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 286
1 | 287 | 287 | 1403214001 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Anggacan | 17.31 | 121.2381 | R | 244 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.78 | 7.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.51 | 55.58 | 79.51 |  | F - Nearest node and line over 5 km | 10.78 | 7.48 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 287
1 | 288 | 288 | PH0000288 | VI | Iloilo | Iloilo City | Progreso-Lapuz | 10.7237 | 122.5549 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.58 | 3.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.5 | 55.58 | 79.5 |  | C - Line within 0.5 km; node over 1 km | 1.81 | 0.31 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 288
1 | 289 | 289 | 1408103006 | Cordillera Administrative Region (CAR) | Apayao | Flora | Balluyan | 18.1265 | 121.4565 | R | 1415 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.8 | 11.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.48 | 55.56 | 79.48 |  | F - Nearest node and line over 5 km | 10.8 | 13.53 | Node: FAY001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 289
1 | 290 | 290 | PH0000290 | NIR | Negros Occidental | Bacolod City | Barangay 11 (Pob.) | 10.6307 | 122.9742 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.06 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.42 | 55.52 | 79.42 |  | A - Node within 0.5 km | 0.29 | 0.06 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 290
1 | 291 | 291 | 1403209018 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Mapaco | 17.5683 | 121.4314 | R | 932 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.16 | 0.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.41 | 55.52 | 79.41 |  | C - Line within 0.5 km; node over 1 km | 5.16 | 0.06 | Line: Tabuk-Conner | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 291
1 | 292 | 292 | 1907009005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Languyan Proper | 17.2558 | 122.2298 | U | 4399 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.4 | 55.51 | 79.4 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 292
1 | 293 | 293 | PH0000293 | II | Nueva Vizcaya | Kasibu | Nantawacan | 16.314 | 121.195 | R | 1559 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.73 | 11.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.37 | 55.49 | 79.37 |  | F - Nearest node and line over 5 km | 9.73 | 11.71 | Node: DNV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 293
1 | 294 | 294 | PH0000294 | NIR | Negros Occidental | Bacolod City | Barangay 24 (Pob.) | 10.6401 | 122.9679 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 0.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.37 | 55.49 | 79.37 |  | B - Node 0.5-1 km | 0.98 | 0.74 | Line: TALISAY - BACOLOD (REDUNDANCY) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 294
1 | 295 | 295 | 1705309005 | MIMAROPA Region | Palawan | Coron | Bulalacao | 11.6636 | 120.1087 | U | 4226 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.77 | 114.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.36 | 55.48 | 79.36 |  | F - Nearest node and line over 5 km | 40.77 | 114.07 | Node: CNW001 - CORON CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 295
1 | 296 | 296 | 0201514003 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Baua | 18.3495 | 122.0908 | R | 2350 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 0.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.34 | 55.46 | 79.34 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.03 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 296
1 | 297 | 297 | PH0000297 | NIR | Negros Occidental | Bacolod City | Barangay 25 (Pob.) | 10.6183 | 123.0044 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.77 | 0.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.31 | 55.45 | 79.31 |  | D - Other node or line within 3 km | 3.76 | 0.51 | Line: SAN CARLOS CITY - TALISAY CITY | Route options survey candidate: compare actual node lateral with approved line tap. | 297
1 | 298 | 298 | PH0000298 | VI | Iloilo | Iloilo City | Taal | 10.6965 | 122.5503 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 2.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.28 | 55.42 | 79.28 |  | D - Other node or line within 3 km | 1.05 | 2.06 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 298
1 | 299 | 299 | 0603018031 | Region VI (Western Visayas) | Iloilo | Dumangas | Nanding Lopez | 10.8805 | 122.7712 | R | 1878 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.44 | 6.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.27 | 55.42 | 79.27 |  | F - Nearest node and line over 5 km | 7.44 | 6.29 | Line: DUMANGAS CO-BAROTAC NUEVO CO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 299
1 | 300 | 300 | 1108205002 | Region XI (Davao Region) | Davao de Oro | Maragusan | Mapawa | 7.3076 | 126.2432 | U | 6057 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.09 | 30.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.27 | 55.42 | 79.27 |  | F - Nearest node and line over 5 km | 38.87 | 38.7 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 300
1 | 301 | 301 | 0205002021 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Latar-Nocnoc-San Francisco | 16.2643 | 121.0395 | R | 708 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.84 | 2.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.27 | 55.41 | 79.27 |  | D - Other node or line within 3 km | 8.17 | 2.36 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Route options survey candidate: compare actual node lateral with approved line tap. | 301
1 | 302 | 302 | 0600413015 | Region VI (Western Visayas) | Aklan | Malinao | Poblacion | 11.643 | 122.309 | R | 1665 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 2.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.26 | 55.41 | 79.26 |  | D - Other node or line within 3 km | 2.6 | 2.84 | Node: MLK001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 302
1 | 303 | 303 | 0205703031 | Region II (Cagayan Valley) | Quirino | Diffun | Aklan Village | 16.5019 | 121.4604 | R | 898 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.37 | 9.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.23 | 55.39 | 79.23 |  | F - Nearest node and line over 5 km | 7.37 | 9.47 | Node: CBQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 303
1 | 304 | 304 | 0205015001 | Region II (Cagayan Valley) | Nueva Vizcaya | Alfonso Castaneda | Abuyo | 15.8483 | 121.2299 | R | 1613 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.27 | 6.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.16 | 55.34 | 79.16 |  | F - Nearest node and line over 5 km | 10.27 | 6.22 | Line: BALER - PANTABANGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 304
1 | 305 | 305 | PH0000305 | VI | Iloilo | Iloilo City | San Pedro | 10.6987 | 122.548 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 2.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.14 | 55.33 | 79.14 |  | D - Other node or line within 3 km | 1.06 | 2.24 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 305
1 | 306 | 306 | PH0000306 | VI | Iloilo | Iloilo City | East Baluarte | 10.6925 | 122.5481 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 2.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.12 | 55.32 | 79.12 |  | B - Node 0.5-1 km | 0.62 | 2.46 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 306
1 | 307 | 307 | PH0000307 | VI | Iloilo | Iloilo City | Taytay Zone II | 10.6888 | 122.5177 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.03 | 4.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.11 | 55.3 | 79.11 |  | D - Other node or line within 3 km | 2.74 | 2.16 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 307
1 | 308 | 308 | PH0000308 | VI | Iloilo | Iloilo City | Lapuz Sur | 10.6916 | 122.5758 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.48 | 0.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.08 | 55.28 | 79.08 |  | D - Other node or line within 3 km | 2.61 | 1.29 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 308
1 | 309 | 309 | PH0000309 | VI | Iloilo | Iloilo City | Magdalo | 10.7039 | 122.5336 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.75 | 0.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.07 | 55.28 | 79.07 |  | D - Other node or line within 3 km | 1.77 | 3.38 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 309
1 | 310 | 310 | 0806010003 | Region VIII (Eastern Visayas) | Samar | Marabut | Canyoyo | 11.1713 | 125.1963 | R | 612 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.59 | 19.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.07 | 55.27 | 79.07 |  | F - Nearest node and line over 5 km | 20.59 | 20.85 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 310
1 | 311 | 311 | PH0000311 | II | Nueva Vizcaya | Kayapa | Tubongan | 16.362 | 120.8778 | R | 988 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.44 | 0.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.05 | 55.27 | 79.05 |  | C - Line within 0.5 km; node over 1 km | 1.44 | 0.27 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 311
1 | 312 | 312 | 0205002016 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Anayo | 16.1959 | 121.0746 | R | 507 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.8 | 9.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.05 | 55.26 | 79.05 |  | F - Nearest node and line over 5 km | 11.8 | 9.59 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 312
1 | 313 | 313 | 1404403002 | Cordillera Administrative Region (CAR) | Mountain Province | Besao | Ambaguio | 17.12 | 120.8453 | R | 176 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.1 | 7.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 79.02 | 55.24 | 79.02 |  | F - Nearest node and line over 5 km | 7.1 | 7.09 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 313
1 | 314 | 314 | 0806010021 | Region VIII (Eastern Visayas) | Samar | Marabut | Panan-awan | 11.1081 | 125.2128 | R | 385 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.27 | 20.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.98 | 55.22 | 78.98 |  | F - Nearest node and line over 5 km | 21.05 | 24.26 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 314
1 | 315 | 315 | PH0000315 | IV-A | Batangas | Lipa City | Poblacion Barangay 11 | 13.9382 | 121.1616 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.7 | 0.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.97 | 55.21 | 78.97 |  | B - Node 0.5-1 km | 0.85 | 0.2 | Line: AE ROS001 TO LPB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 315
1 | 316 | 316 | 1381600012 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Isla | 14.7063 | 120.9504 | U | 5234 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 1.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.95 | 55.19 | 78.95 |  | D - Other node or line within 3 km | 1.05 | 1.05 | Line: Existing 24F | Route options survey candidate: compare actual node lateral with approved line tap. | 316
1 | 317 | 317 | 0600406014 | Region VI (Western Visayas) | Aklan | Ibajay | Laguinbanua | 11.7081 | 122.3481 | R | 3333 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.93 | 55.18 | 78.93 |  | D - Other node or line within 3 km | 2.27 | 1.52 | Line: IVISAN - KALIBO | Route options survey candidate: compare actual node lateral with approved line tap. | 317
1 | 318 | 318 | PH0000318 | NIR | Negros Occidental | Bacolod City | Barangay 32 (Pob.) | 10.6081 | 122.9652 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.93 | 55.18 | 78.93 |  | D - Other node or line within 3 km | 2.93 | 2.69 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 318
1 | 319 | 319 | 1403206003 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Mabongtot | 17.3382 | 121.1906 | R | 601 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.39 | 1.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.92 | 55.17 | 78.92 |  | D - Other node or line within 3 km | 9.39 | 1.62 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 319
1 | 320 | 320 | 1907004009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Luuk Datan | 17.2558 | 122.2299 | R | 2275 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.9 | 55.16 | 78.9 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 320
1 | 321 | 321 | 1907004012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Panglima Mastul | 17.2558 | 122.2299 | R | 2029 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.9 | 55.16 | 78.9 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 321
1 | 322 | 322 | 0201514004 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Cabanbanan Norte | 18.2573 | 121.9458 | R | 722 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.83 | 1.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.89 | 55.15 | 78.89 |  | D - Other node or line within 3 km | 3.83 | 1.17 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Route options survey candidate: compare actual node lateral with approved line tap. | 322
1 | 323 | 323 | 0205008020 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Kinabuan | 16.2016 | 121.2013 | R | 1412 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 19.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.89 | 55.15 | 78.89 |  | E - Nearest node or line 3-5 km | 3.5 | 19.42 | Node: DNV002 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 323
1 | 324 | 324 | 0403418007 | Region IV-A (CALABARZON) | Laguna | Paete | Ilaya del Sur | 14.3618 | 121.4836 | R | 1722 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.93 | 3.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.89 | 55.15 | 78.89 |  | A - Node within 0.5 km | 0.41 | 0.38 | Line: SEGMENT 23 (FAMY - STA CRUZ) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 324
1 | 325 | 325 | 0806010015 | Region VIII (Eastern Visayas) | Samar | Marabut | Amantillo | 11.108 | 125.215 | R | 626 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.28 | 20.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.89 | 55.15 | 78.89 |  | F - Nearest node and line over 5 km | 21.28 | 24.49 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 325
1 | 326 | 326 | PH0000326 | NIR | Negros Occidental | Bacolod City | Barangay 29 (Pob.) | 10.6463 | 122.9546 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.33 | 2.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.87 | 55.14 | 78.87 |  | D - Other node or line within 3 km | 2.31 | 0.8 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 326
1 | 327 | 327 | 0806010013 | Region VIII (Eastern Visayas) | Samar | Marabut | Tagalag | 11.2478 | 125.1835 | R | 974 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.39 | 18.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.84 | 55.12 | 78.84 |  | F - Nearest node and line over 5 km | 19.39 | 19.4 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 327
1 | 328 | 328 | 1381400013 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Pedro Cruz | 14.6055 | 121.0262 | U | 4396 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.83 | 55.11 | 78.83 |  | C - Line within 0.5 km; node over 1 km | 1.72 | 0.17 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 328
1 | 329 | 329 | 0205008010 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Lukidnon | 15.9444 | 121.1842 | R | 358 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.83 | 17.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.81 | 55.1 | 78.81 |  | F - Nearest node and line over 5 km | 15.83 | 17.98 | Node: PTN001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 329
1 | 330 | 330 | 1408101013 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Don Roque Ablan Sr. | 18.376 | 120.9617 | R | 227 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.93 | 28.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.77 | 55.07 | 78.77 |  | F - Nearest node and line over 5 km | 19.69 | 19.32 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 330
1 | 331 | 331 | 0806010020 | Region VIII (Eastern Visayas) | Samar | Marabut | Odoc | 11.2302 | 125.1769 | R | 299 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.42 | 19.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.75 | 55.05 | 78.75 |  | F - Nearest node and line over 5 km | 18.38 | 18.38 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 331
1 | 332 | 332 | 0600417006 | Region VI (Western Visayas) | Aklan | Tangalan | Lanipga | 11.739 | 122.2105 | R | 342 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.38 | 2.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.75 | 55.05 | 78.75 |  | F - Nearest node and line over 5 km | 9.38 | 16.34 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 332
1 | 333 | 333 | 0102915002 | Region I (Ilocos Region) | Ilocos Sur | Quirino | Cayus | 17.1521 | 120.6684 | R | 761 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.99 | 1.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.74 | 55.05 | 78.74 |  | D - Other node or line within 3 km | 1.99 | 1.03 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 333
1 | 334 | 334 | PH0000334 | X | Misamis Oriental | Cagayan De Oro City | Barangay 13 (Pob.) | 8.4702 | 124.7029 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.99 | 3.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.74 | 55.05 | 78.74 |  | C - Line within 0.5 km; node over 1 km | 3.23 | 0.04 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 334
1 | 335 | 335 | 1705303010 | MIMAROPA Region | Palawan | Araceli | San Jose De Oro | 10.5904 | 119.8683 | R | 717 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.04 | 42.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.72 | 55.03 | 78.72 |  | F - Nearest node and line over 5 km | 34.04 | 42.88 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 335
1 | 336 | 336 | 1705303012 | MIMAROPA Region | Palawan | Araceli | Taloto | 10.6011 | 119.8953 | R | 634 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.58 | 45.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.72 | 55.03 | 78.72 |  | F - Nearest node and line over 5 km | 36.58 | 45.41 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 336
1 | 337 | 337 | PH0000337 | X | Misamis Oriental | Cagayan De Oro City | Barangay 10 (Pob.) | 8.5001 | 124.639 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.11 | 1.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.72 | 55.03 | 78.72 |  | B - Node 0.5-1 km | 0.86 | 0.38 | Line: HDD | Short node lateral candidate; confirm port/fiber capacity, access and route. | 337
1 | 338 | 338 | 1402701025 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Pula | 16.9761 | 121.1063 | R | 479 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.71 | 5.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.7 | 55.02 | 78.7 |  | F - Nearest node and line over 5 km | 8.71 | 12.24 | Node: BEF001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 338
1 | 339 | 339 | 0201512026 | Region II (Cagayan Valley) | Cagayan | Enrile | Roma Sur | 17.5095 | 121.6991 | R | 1391 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.86 | 1.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.7 | 55.02 | 78.7 |  | D - Other node or line within 3 km | 5.86 | 1.5 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 339
1 | 340 | 340 | PH0000340 | X | Misamis Oriental | Cagayan De Oro City | Barangay 15 (Pob.) | 8.4589 | 124.7225 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 3.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.68 | 55 | 78.68 |  | D - Other node or line within 3 km | 5.29 | 1.92 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 340
1 | 341 | 341 | 0203110004 | Region II (Cagayan Valley) | Isabela | Dinapigue | Dibulo | 16.5057 | 122.2349 | R | 1196 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.8 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.67 | 55 | 78.67 |  | E - Nearest node or line 3-5 km | 3.8 | 61.05 | Node: DPI001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 341
1 | 342 | 342 | 0203110001 | Region II (Cagayan Valley) | Isabela | Dinapigue | Ayod | 16.5816 | 122.2698 | R | 324 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.26 | 6.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.67 | 55 | 78.67 |  | F - Nearest node and line over 5 km | 6.26 | 62.71 | Node: DPI001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 342
1 | 343 | 343 | 0803731005 | Region VIII (Eastern Visayas) | Leyte | Mahaplag | Hinaguimitan | 10.593 | 125.0059 | R | 506 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.15 | 4.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.67 | 55 | 78.67 |  | F - Nearest node and line over 5 km | 24.3 | 22.66 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 343
1 | 344 | 344 | 0203111013 | Region II (Cagayan Valley) | Isabela | Divilacan | Ditarum | 17.2476 | 122.4158 | R | 351 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.5 | 45.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.67 | 55 | 78.67 |  | F - Nearest node and line over 5 km | 46.14 | 53.46 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 344
1 | 345 | 345 | 0201509011 | Region II (Cagayan Valley) | Cagayan | Calayan | Dalupiri | 19.0605 | 121.2463 | R | 638 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.23 | 50.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.67 | 55 | 78.67 |  | F - Nearest node and line over 5 km | 54.23 | 50.16 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 345
1 | 346 | 346 | 0600410012 | Region VI (Western Visayas) | Aklan | Madalag | Mamba | 11.4942 | 122.2729 | R | 877 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.2 | 12.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.65 | 54.99 | 78.65 |  | F - Nearest node and line over 5 km | 13.2 | 12.66 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 346
1 | 347 | 347 | 1907009012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Tumbagaan | 17.2558 | 122.2298 | R | 1979 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.65 | 54.98 | 78.65 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 347
1 | 348 | 348 | 1108211013 | Region XI (Davao Region) | Davao de Oro | Pantukan | Araibo | 7.2497 | 126.1565 | R | 2585 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.17 | 29.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.65 | 54.98 | 78.65 |  | F - Nearest node and line over 5 km | 31.17 | 29.36 | Line: PANTUKAN - MATI SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 348
1 | 349 | 349 | PH0000349 | VI | Iloilo | Iloilo City | Bonifacio Tanza | 10.7167 | 122.5776 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.85 | 6.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.65 | 54.98 | 78.65 |  | D - Other node or line within 3 km | 1.11 | 1.09 | Line: 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 349
1 | 350 | 350 | PH0000350 | IV-B | Palawan | Puerto Princesa City | Magkakaibigan (Pob.) | 9.7385 | 118.7339 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.24 | 2.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.62 | 54.97 | 78.62 |  | A - Node within 0.5 km | 0.24 | 2.14 | Node: PPW002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 350
1 | 351 | 351 | 0201505025 | Region II (Cagayan Valley) | Cagayan | Aparri | Fuga Island | 18.8861 | 121.4133 | R | 1994 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.94 | 39.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.62 | 54.96 | 78.62 |  | F - Nearest node and line over 5 km | 40.94 | 39.47 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 351
1 | 352 | 352 | 1705305020 | MIMAROPA Region | Palawan | Bataraza | Tagolango | 8.4802 | 117.2199 | R | 1216 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 217.39 | 219.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.62 | 54.96 | 78.62 |  | F - Nearest node and line over 5 km | 217.39 | 219.41 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 352
1 | 353 | 353 | 0600406011 | Region VI (Western Visayas) | Aklan | Ibajay | Cabugao | 11.737 | 122.1693 | R | 274 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.71 | 5.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.61 | 54.96 | 78.61 |  | F - Nearest node and line over 5 km | 13.71 | 20.76 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 353
1 | 354 | 354 | 1380604008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 275 | 14.5957 | 120.9742 | U | 20411 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.71 | 29.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.56 | 54.92 | 78.56 |  | D - Other node or line within 3 km | 1.23 | 0.73 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 354
1 | 355 | 355 | 1705305019 | MIMAROPA Region | Palawan | Bataraza | Tagnato | 8.4094 | 117.2564 | R | 1114 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 219.59 | 221.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.55 | 54.92 | 78.55 |  | F - Nearest node and line over 5 km | 219.59 | 221.6 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 355
1 | 356 | 356 | 0201506038 | Region II (Cagayan Valley) | Cagayan | Baggao | Santa Margarita | 17.9524 | 122.076 | U | 5147 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.67 | 34.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.54 | 54.91 | 78.54 |  | F - Nearest node and line over 5 km | 19.67 | 34.35 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 356
1 | 357 | 357 | PH0000357 | VI | Iloilo | Iloilo City | Cochero | 10.7377 | 122.5511 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.85 | 0.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.53 | 54.9 | 78.53 |  | D - Other node or line within 3 km | 1.92 | 1.09 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 357
1 | 358 | 358 | 0405628013 | Region IV-A (CALABARZON) | Quezon | Mulanay | Buenavista | 13.5073 | 122.4569 | R | 1369 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.72 | 6.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.52 | 54.89 | 78.52 |  | F - Nearest node and line over 5 km | 6.72 | 6.19 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 358
1 | 359 | 359 | 0600410014 | Region VI (Western Visayas) | Aklan | Madalag | Medina | 11.4658 | 122.2568 | R | 934 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.45 | 16.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.51 | 54.88 | 78.51 |  | F - Nearest node and line over 5 km | 16.45 | 16.04 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 359
1 | 360 | 360 | 0405625013 | Region IV-A (CALABARZON) | Quezon | Macalelon | Olongtao Ilaya | 13.7202 | 122.1985 | R | 747 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.06 | 1.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.5 | 54.88 | 78.5 |  | D - Other node or line within 3 km | 4.06 | 1.9 | Line: LZQ001 TO MCQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 360
1 | 361 | 361 | 0405622057 | Region IV-A (CALABARZON) | Quezon | Lopez | Pisipis | 13.8969 | 122.3695 | R | 717 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.47 | 5.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.49 | 54.87 | 78.49 |  | F - Nearest node and line over 5 km | 8.47 | 5.88 | Line: AE LZQ001 TO SNQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 361
1 | 362 | 362 | 0502011020 | Region V (Bicol Region) | Catanduanes | Virac | Dugui San Vicente | 13.6574 | 124.1547 | R | 628 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.04 | 55.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.48 | 54.86 | 78.48 |  | F - Nearest node and line over 5 km | 34.04 | 55.59 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 362
1 | 363 | 363 | 0102916012 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Kinmarin | 17.0386 | 120.5412 | R | 377 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.15 | 9.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.47 | 54.86 | 78.47 |  | F - Nearest node and line over 5 km | 7.15 | 9.3 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 363
1 | 364 | 364 | PH0000364 | VI | Iloilo | Iloilo City | Kasingkasing | 10.7396 | 122.542 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.31 | 4.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.47 | 54.86 | 78.47 |  | D - Other node or line within 3 km | 2.79 | 2.11 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 364
1 | 365 | 365 | PH0000365 | VI | Iloilo | Iloilo City | Don Esteban-Lapuz | 10.7184 | 122.5547 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.15 | 3.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.45 | 54.84 | 78.45 |  | D - Other node or line within 3 km | 1.54 | 0.57 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 365
1 | 366 | 366 | PH0000366 | X | Misamis Oriental | Cagayan De Oro City | Barangay 6 (Pob.) | 8.4601 | 124.6078 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.7 | 1.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.44 | 54.84 | 78.44 |  | D - Other node or line within 3 km | 2.98 | 0.53 | Line: cdo-talakag | Route options survey candidate: compare actual node lateral with approved line tap. | 366
1 | 367 | 367 | 0600410003 | Region VI (Western Visayas) | Aklan | Madalag | Bacyang | 11.5387 | 122.285 | R | 567 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.44 | 9.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.42 | 54.83 | 78.42 |  | F - Nearest node and line over 5 km | 9.44 | 9.05 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 367
1 | 368 | 368 | 0502011023 | Region V (Bicol Region) | Catanduanes | Virac | Dugui Too | 13.6479 | 124.1836 | R | 1416 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.33 | 58.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.42 | 54.82 | 78.42 |  | F - Nearest node and line over 5 km | 37.33 | 58.07 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 368
1 | 369 | 369 | 0600410004 | Region VI (Western Visayas) | Aklan | Madalag | Balactasan | 11.5354 | 122.2895 | R | 865 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.5 | 8.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.36 | 54.78 | 78.36 |  | F - Nearest node and line over 5 km | 9.5 | 8.75 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 369
1 | 370 | 370 | 0600410011 | Region VI (Western Visayas) | Aklan | Madalag | Logohon | 11.5317 | 122.2969 | R | 511 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.9 | 8.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.35 | 54.78 | 78.35 |  | F - Nearest node and line over 5 km | 8.9 | 8.2 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 370
1 | 371 | 371 | 0600410022 | Region VI (Western Visayas) | Aklan | Madalag | Singay | 11.5372 | 122.2981 | R | 336 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.55 | 7.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.35 | 54.77 | 78.35 |  | F - Nearest node and line over 5 km | 8.55 | 7.82 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 371
1 | 372 | 372 | 0307708006 | Region III (Central Luzon) | Aurora | San Luis | Dibalo | 15.6648 | 121.5632 | R | 135 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.5 | 10.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.34 | 54.77 | 78.34 |  | F - Nearest node and line over 5 km | 9.5 | 10.34 | Node: SLA001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 372
1 | 373 | 373 | 1380400003 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Bayan-bayanan | 14.687 | 120.9545 | U | 6871 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.33 | 54.76 | 78.33 |  | B - Node 0.5-1 km | 0.82 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 373
1 | 374 | 374 | PH0000374 | NIR | Negros Occidental | Bacolod City | Barangay 13 (Pob.) | 10.6627 | 122.954 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.26 | 0.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.31 | 54.74 | 78.31 |  | B - Node 0.5-1 km | 0.5 | 0.66 | Node: BDN002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 374
1 | 375 | 375 | PH0000375 | IV-A | Batangas | Lipa City | Poblacion Barangay 3 | 13.9301 | 121.1426 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.31 | 54.74 | 78.31 |  | D - Other node or line within 3 km | 2.55 | 0.88 | Line: TANAUAN - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 375
1 | 376 | 376 | 1403209011 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Dugpa | 17.5156 | 121.3789 | R | 1263 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.14 | 6.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.3 | 54.74 | 78.3 |  | F - Nearest node and line over 5 km | 6.14 | 6.45 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 376
1 | 377 | 377 | 1907006010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Lookan | 5.2168 | 120.6701 | R | 1548 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.49 | 59.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.3 | 54.74 | 78.3 |  | F - Nearest node and line over 5 km | 244.03 | 244.02 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 377
1 | 378 | 378 | 1705318032 | MIMAROPA Region | Palawan | Roxas | Barangay V Pob. | 11.5074 | 122.7373 | R | 2951 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.12 | 1.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.29 | 54.73 | 78.29 |  | C - Line within 0.5 km; node over 1 km | 2.58 | 0.29 | Line: ROXAS - IVISAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 378
1 | 379 | 379 | PH0000379 | VI | Iloilo | Iloilo City | Katilingban | 10.696 | 122.543 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 2.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.28 | 54.73 | 78.28 |  | B - Node 0.5-1 km | 0.59 | 2.84 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 379
1 | 380 | 380 | 0806403039 | Region VIII (Eastern Visayas) | Southern Leyte | Hinunangan | Upper Bantawon | 10.355 | 125.1534 | R | 146 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.45 | 20.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.27 | 54.72 | 78.27 |  | F - Nearest node and line over 5 km | 43.22 | 38.72 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 380
1 | 381 | 381 | PH0000381 | VI | Iloilo | Iloilo City | Baybay Tanza | 10.7494 | 122.5665 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.02 | 3.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.25 | 54.71 | 78.25 |  | A - Node within 0.5 km | 0.44 | 0.26 | Line: 3,477 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 381
1 | 382 | 382 | PH0000382 | VI | Iloilo | Iloilo City | Danao | 10.7336 | 122.5552 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.71 | 6.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.24 | 54.7 | 78.24 |  | D - Other node or line within 3 km | 1.82 | 0.53 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 382
1 | 383 | 383 | 0501720004 | Region V (Bicol Region) | Camarines Sur | Magarao | Carigsa | 13.6662 | 123.2447 | R | 229 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.7 | 0.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.24 | 54.7 | 78.24 |  | E - Nearest node or line 3-5 km | 4.81 | 4.27 | Line: EE18-HH19 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 383
1 | 384 | 384 | 1108202008 | Region XI (Davao Region) | Davao de Oro | Laak | Kidawa | 7.8726 | 125.7507 | R | 3785 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.21 | 15.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.23 | 54.69 | 78.23 |  | F - Nearest node and line over 5 km | 34.03 | 30.88 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 384
1 | 385 | 385 | 1108204019 | Region XI (Davao Region) | Davao de Oro | Maco | Malamodao | 7.3685 | 125.9713 | R | 2703 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.78 | 12.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.21 | 54.68 | 78.21 |  | F - Nearest node and line over 5 km | 12.78 | 12.67 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 385
1 | 386 | 386 | 1402706003 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Ayangan | 16.9011 | 121.1892 | R | 499 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.84 | 12.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.21 | 54.68 | 78.21 |  | D - Other node or line within 3 km | 2.84 | 12.3 | Node: BEF002 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 386
1 | 387 | 387 | 1003519005 | Region X (Northern Mindanao) | Lanao del Norte | Sapad | Gamal | 7.8464 | 123.8029 | R | 593 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.77 | 11.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.21 | 54.68 | 78.21 |  | F - Nearest node and line over 5 km | 21.86 | 6.46 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 387
1 | 388 | 388 | 1380606201 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 594 | 14.6043 | 121.0118 | U | 655 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.24 | 27.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.18 | 54.66 | 78.18 |  | B - Node 0.5-1 km | 0.82 | 0.2 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 388
1 | 389 | 389 | PH0000389 | NIR | Negros Occidental | Bacolod City | Barangay 22 (Pob.) | 10.6627 | 122.954 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 0.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.18 | 54.66 | 78.18 |  | B - Node 0.5-1 km | 0.5 | 0.66 | Node: BDN002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 389
1 | 390 | 390 | 0304918009 | Region III (Central Luzon) | Nueva Ecija | Nampicuan | Edy | 15.7333 | 120.6348 | R | 140 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.87 | 8.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.18 | 54.65 | 78.18 |  | F - Nearest node and line over 5 km | 6.03 | 5.78 | Line: MONCADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 390
1 | 391 | 391 | 0307706025 | Region III (Central Luzon) | Aurora | Dipaculao | Diamanen | 15.8899 | 121.5218 | R | 298 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.25 | 2.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.17 | 54.65 | 78.17 |  | D - Other node or line within 3 km | 6.25 | 2.9 | Line: Route | Route options survey candidate: compare actual node lateral with approved line tap. | 391
1 | 392 | 392 | PH0000392 | NIR | Negros Occidental | Bacolod City | Barangay 26 (Pob.) | 10.6262 | 122.9735 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.05 | 1.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.16 | 54.64 | 78.16 |  | B - Node 0.5-1 km | 0.78 | 0.57 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Short node lateral candidate; confirm port/fiber capacity, access and route. | 392
1 | 393 | 393 | 0205009010 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Didipio | 16.3363 | 121.4545 | R | 3856 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.24 | 21.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.15 | 54.64 | 78.15 |  | F - Nearest node and line over 5 km | 17.24 | 21.48 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 393
1 | 394 | 394 | 0403403001 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Biñan | 14.3158 | 121.0769 | U | 7786 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.15 | 54.64 | 78.15 |  | D - Other node or line within 3 km | 1.5 | 0.91 | Line: AE CRC005-BNL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 394
1 | 395 | 395 | 1907006011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Center | 17.2559 | 122.2299 | R | 914 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.12 | 54.61 | 78.12 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 395
1 | 396 | 396 | PH0000396 | VI | Iloilo | Iloilo City | Rizal Ibarra | 10.75 | 122.569 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.59 | 3.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.11 | 54.61 | 78.11 |  | B - Node 0.5-1 km | 0.56 | 0.07 | Line: 3,477 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 396
1 | 397 | 397 | 1380400005 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Concepcion | 14.6676 | 120.9496 | U | 13018 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.8 | 0.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.11 | 54.6 | 78.11 |  | B - Node 0.5-1 km | 0.8 | 0.31 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 397
1 | 398 | 398 | PH0000398 | VI | Iloilo | Iloilo City | Javellana | 10.6975 | 122.5495 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.1 | 54.6 | 78.1 |  | D - Other node or line within 3 km | 1.06 | 2.11 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 398
1 | 399 | 399 | 1907006033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Tubig Dayang Center | 17.2568 | 122.2306 | R | 1198 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.37 | 58.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.1 | 54.6 | 78.1 |  | F - Nearest node and line over 5 km | 29.69 | 34.52 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 399
1 | 400 | 400 | 1381400015 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Rivera | 10.2591 | 125.1862 | U | 2531 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.09 | 54.59 | 78.09 |  | F - Nearest node and line over 5 km | 41.5 | 35.61 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 400
1 | 401 | 401 | PH0000401 | VI | Iloilo | Iloilo City | Luna (Jaro) | 10.715 | 122.5645 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.74 | 7.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.05 | 54.57 | 78.05 |  | A - Node within 0.5 km | 0.4 | 0.12 | Line: 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 401
1 | 402 | 402 | PH0000402 | NIR | Negros Occidental | Bacolod City | Barangay 12 (Pob.) | 10.5996 | 122.9733 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.97 | 0.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.05 | 54.57 | 78.05 |  | E - Nearest node or line 3-5 km | 3.73 | 3.49 | Line: SAN CARLOS CITY - TALISAY CITY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 402
1 | 403 | 403 | 1704006011 | MIMAROPA Region | Marinduque | Torrijos | Makawayan | 13.2619 | 122.0456 | R | 1084 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.52 | 45.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.04 | 54.56 | 78.04 |  | F - Nearest node and line over 5 km | 46.52 | 45.8 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 403
1 | 404 | 404 | 0600405002 | Region VI (Western Visayas) | Aklan | Buruanga | Bagongbayan | 11.8116 | 121.883 | R | 1018 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.67 | 14.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.04 | 54.56 | 78.04 |  | F - Nearest node and line over 5 km | 16.67 | 52.79 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 404
1 | 405 | 405 | 1907006034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Tubig Dayang Riverside | 5.4088 | 120.588 | R | 1070 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.13 | 58.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.03 | 54.55 | 78.03 |  | F - Nearest node and line over 5 km | 234.21 | 234.2 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 405
1 | 406 | 406 | 1907006006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bintawlan | 17.2558 | 122.2299 | R | 1493 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.03 | 54.55 | 78.03 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 406
1 | 407 | 407 | 0600402008 | Region VI (Western Visayas) | Aklan | Balete | Guanko | 11.5328 | 122.3765 | R | 1216 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.71 | 2.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.02 | 54.55 | 78.02 |  | D - Other node or line within 3 km | 2.71 | 2.48 | Line: IVISAN - KALIBO | Route options survey candidate: compare actual node lateral with approved line tap. | 407
1 | 408 | 408 | 1907006009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bunay Bunay Tong | 17.256 | 122.2301 | R | 1072 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.46 | 59.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.02 | 54.54 | 78.02 |  | F - Nearest node and line over 5 km | 29.59 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 408
1 | 409 | 409 | 0600406025 | Region VI (Western Visayas) | Aklan | Ibajay | Polo | 11.8024 | 122.1234 | R | 1288 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.3 | 3.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.02 | 54.54 | 78.02 |  | F - Nearest node and line over 5 km | 20.86 | 27.35 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 409
1 | 410 | 410 | PH0000410 | X | Misamis Oriental | Cagayan De Oro City | Barangay 38 (Pob.) | 8.4613 | 124.7817 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.81 | 1.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.02 | 54.54 | 78.02 |  | D - Other node or line within 3 km | 5.62 | 0.99 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 410
1 | 411 | 411 | 1907006008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Bubuan | 5.4095 | 120.5883 | R | 749 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 234.13 | 234.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.02 | 54.54 | 78.02 |  | F - Nearest node and line over 5 km | 234.13 | 234.13 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 411
1 | 412 | 412 | 1907006023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Nusa-nusa | 17.2558 | 122.23 | R | 458 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.85 | 57.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.01 | 54.54 | 78.01 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 412
1 | 413 | 413 | 0203110003 | Region II (Cagayan Valley) | Isabela | Dinapigue | Bucal Norte | 16.5256 | 122.2664 | R | 293 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.7 | 0.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78.01 | 54.54 | 78.01 |  | A - Node within 0.5 km | 0.26 | 65.07 | Node: DPI001 - TYPE 4A | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 413
1 | 414 | 414 | 0600414003 | Region VI (Western Visayas) | Aklan | Nabas | Buenafortuna | 11.8267 | 122.0646 | R | 1432 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.71 | 1.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 78 | 54.53 | 78 |  | F - Nearest node and line over 5 km | 18.71 | 34.28 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 414
1 | 415 | 415 | PH0000415 | III | Nueva Ecija | Cabanatuan City | General Luna (Pob.) | 15.4466 | 120.9226 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.08 | 0.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.98 | 54.52 | 77.98 |  | D - Other node or line within 3 km | 2.61 | 1.84 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 415
1 | 416 | 416 | 0500504012 | Region V (Bicol Region) | Albay | Guinobatan | Doña Tomasa | 13.1268 | 123.5437 | R | 1298 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.74 | 3.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.95 | 54.49 | 77.95 |  | F - Nearest node and line over 5 km | 5.89 | 9.32 | Node: GNA002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 416
1 | 417 | 417 | 1402706025 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Nalbu | 16.9261 | 121.2392 | R | 284 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.48 | 18.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.93 | 54.48 | 77.93 |  | F - Nearest node and line over 5 km | 5.48 | 18.29 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 417
1 | 418 | 418 | 0600414010 | Region VI (Western Visayas) | Aklan | Nabas | Matabana | 11.8746 | 122.0282 | R | 1010 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.15 | 0.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.93 | 54.48 | 77.93 |  | F - Nearest node and line over 5 km | 12.15 | 40.04 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 418
1 | 419 | 419 | 0806412022 | Region VIII (Eastern Visayas) | Southern Leyte | Saint Bernard | Malinao | 10.3671 | 125.0937 | R | 42 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.36 | 11.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.93 | 54.48 | 77.93 |  | F - Nearest node and line over 5 km | 38.93 | 33.48 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 419
1 | 420 | 420 | 0600402010 | Region VI (Western Visayas) | Aklan | Balete | Oquendo | 11.5304 | 122.3872 | R | 1064 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.24 | 2.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.88 | 54.45 | 77.88 |  | D - Other node or line within 3 km | 3.24 | 2.78 | Line: IVISAN - KALIBO | Route options survey candidate: compare actual node lateral with approved line tap. | 420
1 | 421 | 421 | 1402706020 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Maga | 16.9759 | 121.1722 | R | 425 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.28 | 12.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.87 | 54.44 | 77.87 |  | F - Nearest node and line over 5 km | 5.28 | 16.21 | Node: MOF001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 421
1 | 422 | 422 | 0601917034 | Region VI (Western Visayas) | Capiz | Tapaz | Rizal Sur | 11.3159 | 122.3863 | R | 443 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.62 | 20.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.87 | 54.44 | 77.87 |  | F - Nearest node and line over 5 km | 26.62 | 23.38 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 422
1 | 423 | 423 | 1402706036 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Epeng | 16.9605 | 121.1803 | R | 497 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.73 | 13.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.87 | 54.44 | 77.87 |  | E - Nearest node or line 3-5 km | 3.73 | 15.72 | Node: MOF002 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 423
1 | 424 | 424 | PH0000424 | VI | Iloilo | Iloilo City | San Jose | 10.6892 | 122.5171 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.22 | 2.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.86 | 54.43 | 77.86 |  | D - Other node or line within 3 km | 2.8 | 2.08 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 424
1 | 425 | 425 | PH0000425 | IV-A | Batangas | Lipa City | Poblacion Barangay 9-A | 13.9755 | 121.1671 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 0.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.84 | 54.42 | 77.84 |  | C - Line within 0.5 km; node over 1 km | 3.48 | 0.04 | Line: CLB001 TO BCY01 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 425
1 | 426 | 426 | 0806412017 | Region VIII (Eastern Visayas) | Southern Leyte | Saint Bernard | Magatas | 10.3053 | 125.1145 | R | 89 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.03 | 15.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.84 | 54.42 | 77.84 |  | F - Nearest node and line over 5 km | 36.63 | 31.87 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 426
1 | 427 | 427 | 0601909015 | Region VI (Western Visayas) | Capiz | Panay | Butacal | 11.5172 | 122.9147 | R | 1221 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.83 | 8.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.83 | 54.41 | 77.83 |  | F - Nearest node and line over 5 km | 9.83 | 8.19 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 427
1 | 428 | 428 | PH0000428 | XI | Davao Del Sur | Davao City | Gumitan | 7.4393 | 125.3477 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.01 | 9.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.83 | 54.41 | 77.83 |  | F - Nearest node and line over 5 km | 12.01 | 9.9 | Line: KITAOTAO - DAVAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 428
1 | 429 | 429 | 1402706018 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Langayan | 16.954 | 121.2383 | R | 487 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.71 | 19.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.8 | 54.39 | 77.8 |  | D - Other node or line within 3 km | 2.71 | 19.94 | Node: MOF001 - TYPE 4 | Route options survey candidate: compare actual node lateral with approved line tap. | 429
1 | 430 | 430 | 1408103008 | Cordillera Administrative Region (CAR) | Apayao | Flora | Malayugan | 18.1069 | 121.4545 | R | 1277 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.59 | 11.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.79 | 54.38 | 77.79 |  | F - Nearest node and line over 5 km | 11.59 | 15.04 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 430
1 | 431 | 431 | PH0000431 | VI | Iloilo | Iloilo City | North Baluarte | 10.7143 | 122.5642 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.69 | 6.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.77 | 54.37 | 77.77 |  | A - Node within 0.5 km | 0.42 | 0.05 | Line: 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 431
1 | 432 | 432 | 1907009001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Bakong | 17.2558 | 122.2298 | R | 1989 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.76 | 54.36 | 77.76 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 432
1 | 433 | 433 | 1907009003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Basnunuk | 17.2558 | 122.2298 | R | 1984 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.76 | 54.36 | 77.76 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 433
1 | 434 | 434 | 0601917011 | Region VI (Western Visayas) | Capiz | Tapaz | Buri | 11.2066 | 122.4021 | R | 668 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.41 | 17.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.75 | 54.36 | 77.75 |  | F - Nearest node and line over 5 km | 28.41 | 22.08 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 434
1 | 435 | 435 | 0601917055 | Region VI (Western Visayas) | Capiz | Tapaz | Tacayan | 11.2275 | 122.4381 | R | 434 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.23 | 13.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.75 | 54.35 | 77.75 |  | F - Nearest node and line over 5 km | 26.23 | 17.68 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 435
1 | 436 | 436 | 1907009019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Kiniktal | 17.2558 | 122.2298 | R | 1755 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.75 | 54.35 | 77.75 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 436
1 | 437 | 437 | 0601917033 | Region VI (Western Visayas) | Capiz | Tapaz | Rizal Norte | 11.2667 | 122.5333 | R | 327 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.68 | 3.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.75 | 54.35 | 77.75 |  | F - Nearest node and line over 5 km | 15.68 | 6.76 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 437
1 | 438 | 438 | 1907009002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Bas-bas Proper | 17.2558 | 122.2298 | R | 1467 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.74 | 54.35 | 77.74 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 438
1 | 439 | 439 | 1408106027 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Lt. Balag | 18.2386 | 121.3663 | R | 210 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.03 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.72 | 54.33 | 77.72 |  | B - Node 0.5-1 km | 0.8 | 12.57 | Node: PLY001 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 439
1 | 440 | 440 | 0603030036 | Region VI (Western Visayas) | Iloilo | Miagao | Dalije | 10.6788 | 122.1669 | R | 1649 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.41 | 6.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.72 | 54.33 | 77.72 |  | F - Nearest node and line over 5 km | 23.41 | 6.01 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 440
1 | 441 | 441 | PH0000441 | II | Nueva Vizcaya | Quezon N Vizcaya | Bonifacio | 16.5161 | 121.315 | R | 2464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.67 | 4.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.71 | 54.33 | 77.71 |  | E - Nearest node or line 3-5 km | 3.38 | 8.56 | Node: QZV001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 441
1 | 442 | 442 | 1381400003 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Batis | 16.6685 | 120.34 | U | 10049 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.6 | 0.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.7 | 54.32 | 77.7 |  | C - Line within 0.5 km; node over 1 km | 5.7 | 0.26 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 442
1 | 443 | 443 | 0601917054 | Region VI (Western Visayas) | Capiz | Tapaz | Tabon | 11.3106 | 122.4316 | R | 635 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.58 | 15.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.69 | 54.31 | 77.69 |  | F - Nearest node and line over 5 km | 25.58 | 18.42 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 443
1 | 444 | 444 | PH0000444 | VI | Iloilo | Iloilo City | Rizal Palapala I | 10.7049 | 122.5622 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.31 | 1.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.68 | 54.31 | 77.68 |  | D - Other node or line within 3 km | 1.17 | 0.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 444
1 | 445 | 445 | 1380608014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 663-A | 14.5853 | 120.9857 | U | 415 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.02 | 41.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.67 | 54.3 | 77.67 |  | B - Node 0.5-1 km | 0.61 | 0.2 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 445
1 | 446 | 446 | 1705320006 | MIMAROPA Region | Palawan | Taytay | Beton | 10.8106 | 119.6326 | R | 1739 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.82 | 13.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.67 | 54.3 | 77.67 |  | F - Nearest node and line over 5 km | 13.82 | 13.72 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 446
1 | 447 | 447 | 0802623024 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | San Pablo | 11.879 | 125.3611 | R | 712 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.12 | 83.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.67 | 54.3 | 77.67 |  | F - Nearest node and line over 5 km | 81.12 | 83.43 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 447
1 | 448 | 448 | 1380601019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 19 | 14.6005 | 120.9621 | U | 2341 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.85 | 24.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.66 | 54.29 | 77.66 |  | B - Node 0.5-1 km | 0.74 | 1.06 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 448
1 | 449 | 449 | 0601917057 | Region VI (Western Visayas) | Capiz | Tapaz | Taganghin | 11.2222 | 122.3861 | R | 644 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.83 | 18.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.66 | 54.29 | 77.66 |  | F - Nearest node and line over 5 km | 30.83 | 23.33 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 449
1 | 450 | 450 | 0601913014 | Region VI (Western Visayas) | Capiz | President Roxas | Pandan | 11.4739 | 122.9183 | R | 720 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.21 | 4.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.66 | 54.29 | 77.66 |  | E - Nearest node or line 3-5 km | 9.21 | 4.35 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 450
1 | 451 | 451 | 1004322001 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Alipuaton | 8.8468 | 124.7893 | R | 1103 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 2.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.66 | 54.29 | 77.66 |  | C - Line within 0.5 km; node over 1 km | 1.17 | 0.02 | Line: CDO - BUENAVISTA via GINGOOG | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 451
1 | 452 | 452 | 0601917051 | Region VI (Western Visayas) | Capiz | Tapaz | Senonod | 11.2667 | 122.5333 | R | 230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.68 | 3.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.66 | 54.29 | 77.66 |  | F - Nearest node and line over 5 km | 15.68 | 6.76 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 452
1 | 453 | 453 | 0603030086 | Region VI (Western Visayas) | Iloilo | Miagao | Ongyod | 10.6395 | 122.2488 | R | 211 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.31 | 2.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.65 | 54.28 | 77.65 |  | C - Line within 0.5 km; node over 1 km | 15.12 | 0.21 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 453
1 | 454 | 454 | 0603030024 | Region VI (Western Visayas) | Iloilo | Miagao | Cabalaunan | 10.709 | 122.2043 | R | 262 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.34 | 3.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.62 | 54.26 | 77.62 |  | F - Nearest node and line over 5 km | 19.6 | 7.76 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 454
1 | 455 | 455 | 0601917031 | Region VI (Western Visayas) | Capiz | Tapaz | Nayawan | 11.2442 | 122.4221 | R | 416 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.8 | 14.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.61 | 54.26 | 77.61 |  | F - Nearest node and line over 5 km | 27.8 | 19.04 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 455
1 | 456 | 456 | 0403403016 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Poblacion | 14.32 | 121.067 | U | 5494 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.59 | 54.25 | 77.59 |  | B - Node 0.5-1 km | 0.98 | 0.25 | Line: AE CRC005-BNL001-CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 456
1 | 457 | 457 | 1408103005 | Cordillera Administrative Region (CAR) | Apayao | Flora | Balasi | 18.1757 | 121.4026 | R | 292 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.87 | 4.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.56 | 54.22 | 77.56 |  | E - Nearest node or line 3-5 km | 4.87 | 16.61 | Node: FAY001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 457
1 | 458 | 458 | 1401107018 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Tawangan | 16.6565 | 120.9108 | R | 1037 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.46 | 12.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.56 | 54.22 | 77.56 |  | F - Nearest node and line over 5 km | 8.46 | 12.97 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 458
1 | 459 | 459 | 1705320026 | MIMAROPA Region | Palawan | Taytay | Baras | 10.6809 | 119.6373 | R | 977 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.37 | 16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.52 | 54.2 | 77.52 |  | F - Nearest node and line over 5 km | 7.37 | 15.99 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 459
1 | 460 | 460 | 0806002012 | Region VIII (Eastern Visayas) | Samar | Basey | Catadman | 11.2702 | 125.1544 | R | 679 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.92 | 16.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.52 | 54.19 | 77.52 |  | F - Nearest node and line over 5 km | 16.92 | 17.08 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 460
1 | 461 | 461 | 1381400014 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Progreso | 17.6766 | 120.7394 | U | 1774 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.2 | 0.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.51 | 54.19 | 77.51 |  | F - Nearest node and line over 5 km | 7.9 | 7.86 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 461
1 | 462 | 462 | PH0000462 | IV-A | Batangas | Lipa City | Poblacion Barangay 6 | 13.8937 | 121.1625 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.14 | 0.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.5 | 54.18 | 77.5 |  | D - Other node or line within 3 km | 5.64 | 1.29 | Line: TANAUAN - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 462
1 | 463 | 463 | 0105536016 | Region I (Ilocos Region) | Pangasinan | San Nicolas | Malico | 16.1759 | 120.8682 | R | 351 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.67 | 7.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.47 | 54.16 | 77.47 |  | F - Nearest node and line over 5 km | 7.67 | 7.39 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 463
1 | 464 | 464 | 0203110002 | Region II (Cagayan Valley) | Isabela | Dinapigue | Bucal Sur | 16.541 | 122.2644 | R | 891 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 1.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.46 | 54.15 | 77.46 |  | D - Other node or line within 3 km | 1.72 | 64.51 | Node: DPI001 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 464
1 | 465 | 465 | 1380900018 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tanza 2 | 14.6641 | 120.9647 | U | 15975 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.39 | 0.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.46 | 54.15 | 77.46 |  | B - Node 0.5-1 km | 0.54 | 0.43 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 465
1 | 466 | 466 | PH0000466 | NIR | Negros Occidental | Bacolod City | Barangay 9 (Pob.) | 10.6329 | 122.9334 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.03 | 1.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.46 | 54.15 | 77.46 |  | C - Line within 0.5 km; node over 1 km | 2.05 | 0.47 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 466
1 | 467 | 467 | 1906613047 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Samak | 17.2554 | 122.2295 | R | 1990 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.39 | 54.11 | 77.39 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 467
1 | 468 | 468 | 1403215001 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Ambato Legleg | 17.2719 | 121.1562 | R | 410 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.19 | 0.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.39 | 54.1 | 77.39 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.18 | Line: Untitled Path | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 468
1 | 469 | 469 | 1402701009 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Cambulo | 16.952 | 121.1281 | R | 1156 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.19 | 7.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.37 | 54.09 | 77.37 |  | F - Nearest node and line over 5 km | 6.19 | 11.09 | Node: MOF002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 469
1 | 470 | 470 | 0701230015 | Region VII (Central Visayas) | Bohol | Loon | Cabadug | 9.7964 | 123.8026 | R | 320 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.77 | 1.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.35 | 54.07 | 77.35 |  | D - Other node or line within 3 km | 1.09 | 0.97 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Route options survey candidate: compare actual node lateral with approved line tap. | 470
1 | 471 | 471 | PH0000471 | NIR | Negros Occidental | Bacolod City | Barangay 28 (Pob.) | 10.6661 | 122.952 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.09 | 0.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.33 | 54.06 | 77.33 |  | A - Node within 0.5 km | 0.09 | 0.31 | Node: BDN002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 471
1 | 472 | 472 | 1380606202 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 595 | 14.6031 | 121.0097 | U | 4325 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.67 | 35.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.32 | 54.05 | 77.32 |  | B - Node 0.5-1 km | 0.57 | 0.09 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 472
1 | 473 | 473 | 0203111008 | Region II (Cagayan Valley) | Isabela | Divilacan | Dimapnat | 17.3112 | 122.3965 | R | 1050 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.94 | 44.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.32 | 54.05 | 77.32 |  | F - Nearest node and line over 5 km | 47.57 | 53.14 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 473
1 | 474 | 474 | 1380606192 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 586 | 14.6046 | 121.01 | U | 5260 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.79 | 34.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.31 | 54.05 | 77.31 |  | B - Node 0.5-1 km | 0.65 | 0.25 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 474
1 | 475 | 475 | 1004315008 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Tangcub | 8.5305 | 124.372 | R | 1075 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.9 | 3.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.31 | 54.05 | 77.31 |  | E - Nearest node or line 3-5 km | 3.9 | 3.94 | Node: LDM001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 475
1 | 476 | 476 | 1400126010 | Cordillera Administrative Region (CAR) | Abra | Tubo | Tabacda | 17.2666 | 120.845 | R | 279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.1 | 20.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.31 | 54.05 | 77.31 |  | F - Nearest node and line over 5 km | 21.1 | 20.8 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 476
1 | 477 | 477 | PH0000477 | VI | Iloilo | Iloilo City | San Agustin | 10.6997 | 122.5647 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 0.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.31 | 54.05 | 77.31 |  | C - Line within 0.5 km; node over 1 km | 1.61 | 0.48 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 477
1 | 478 | 478 | 1381400008 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Kabayanan | 14.5987 | 121.0323 | U | 5954 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.19 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.31 | 54.05 | 77.31 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.38 | Line: UG 288C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 478
1 | 479 | 479 | PH0000479 | II | Isabela | Ilagan City | Sindon Bayabo | 17.0692 | 122.0216 | R | 2276 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 13.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.28 | 54.03 | 77.28 |  | D - Other node or line within 3 km | 1.95 | 13.36 | Node: IGI003 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 479
1 | 480 | 480 | 0201516035 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Tucalana | 18.1826 | 121.6601 | R | 1572 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.27 | 54.02 | 77.27 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.05 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 480
1 | 481 | 481 | 0600406013 | Region VI (Western Visayas) | Aklan | Ibajay | Colongcolong | 11.8192 | 122.1692 | R | 1174 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.73 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.26 | 54.01 | 77.26 |  | F - Nearest node and line over 5 km | 17.73 | 23.58 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 481
1 | 482 | 482 | 1408104002 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Baliwanan | 18.13 | 121.1397 | R | 475 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.04 | 18.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.25 | 54.01 | 77.25 |  | F - Nearest node and line over 5 km | 13.04 | 37.54 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 482
1 | 483 | 483 | 1102301004 | Region XI (Davao Region) | Davao del Norte | Asuncion | Binancian | 7.6541 | 125.8035 | R | 2366 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.62 | 11.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.25 | 54 | 77.25 |  | F - Nearest node and line over 5 km | 21.54 | 16.61 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 483
1 | 484 | 484 | PH0000484 | X | Misamis Oriental | Cagayan De Oro City | Barangay 3 (Pob.) | 8.4675 | 124.5731 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.33 | 6.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.23 | 53.99 | 77.23 |  | D - Other node or line within 3 km | 5.87 | 2.73 | Line: cdo-talakag | Route options survey candidate: compare actual node lateral with approved line tap. | 484
1 | 485 | 485 | PH0000485 | NIR | Negros Occidental | Bacolod City | Barangay 30 (Pob.) | 10.5996 | 122.9733 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.23 | 53.99 | 77.23 |  | E - Nearest node or line 3-5 km | 3.73 | 3.49 | Line: SAN CARLOS CITY - TALISAY CITY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 485
1 | 486 | 486 | 1403215014 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Poblacion | 17.265 | 121.149 | R | 861 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.14 | 0.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.21 | 53.98 | 77.21 |  | A - Node within 0.5 km | 0.14 | 0.08 | Line: Untitled Path | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 486
1 | 487 | 487 | 0205706012 | Region II (Cagayan Valley) | Quirino | Nagtipunan | San Pugo | 16.1313 | 121.4946 | R | 503 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.66 | 21.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.2 | 53.97 | 77.2 |  | F - Nearest node and line over 5 km | 14.66 | 21.8 | Node: NTQ001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 487
1 | 488 | 488 | 0600611025 | Region VI (Western Visayas) | Antique | Pandan | Perfecta | 11.7273 | 122.1258 | R | 214 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.3 | 9.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.19 | 53.97 | 77.19 |  | F - Nearest node and line over 5 km | 18.3 | 24.78 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 488
1 | 489 | 489 | 0200901005 | Region II (Cagayan Valley) | Batanes | Basco | Chanarian | 20.4328 | 121.9589 | R | 451 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 221.77 | 215.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.17 | 53.95 | 77.17 |  | F - Nearest node and line over 5 km | 218.75 | 215.65 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 489
1 | 490 | 490 | 0806002005 | Region VIII (Eastern Visayas) | Samar | Basey | Basiao | 11.2614 | 125.1613 | R | 1451 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.43 | 16.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.16 | 53.95 | 77.16 |  | F - Nearest node and line over 5 km | 17.43 | 17.44 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 490
1 | 491 | 491 | PH0000491 | VIII | Samar (Western Samar) | Catbalogan City | Totoringon | 11.8542 | 124.9255 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.85 | 33.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.15 | 53.94 | 77.15 |  | F - Nearest node and line over 5 km | 66.8 | 66.73 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 491
1 | 492 | 492 | 1380900012 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Roque | 14.6693 | 120.9378 | U | 19778 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.85 | 0.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.12 | 53.92 | 77.12 |  | B - Node 0.5-1 km | 0.85 | 0.85 | Node: MAL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 492
1 | 493 | 493 | 0405625024 | Region IV-A (CALABARZON) | Quezon | Macalelon | San Jose | 13.7971 | 122.1805 | R | 212 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.25 | 1.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.1 | 53.9 | 77.1 |  | E - Nearest node or line 3-5 km | 7.41 | 4.43 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 493
1 | 494 | 494 | PH0000494 | VI | Iloilo | Iloilo City | Montinola | 10.7399 | 122.541 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.1 | 53.9 | 77.1 |  | D - Other node or line within 3 km | 2.89 | 2.22 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 494
1 | 495 | 495 | 1402701007 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Banao | 16.8814 | 121.1886 | R | 517 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.89 | 11.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.07 | 53.88 | 77.07 |  | E - Nearest node or line 3-5 km | 3.89 | 11.23 | Node: BEF002 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 495
1 | 496 | 496 | 1004303002 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Dahilig | 8.9592 | 124.8463 | R | 335 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 2.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.07 | 53.88 | 77.07 |  | E - Nearest node or line 3-5 km | 5.01 | 4.9 | Line: CDO - BUENAVISTA via GINGOOG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 496
1 | 497 | 497 | 0205008019 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Kimbutan | 16.1657 | 121.2272 | R | 1561 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.99 | 24.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.05 | 53.87 | 77.05 |  | E - Nearest node or line 3-5 km | 4.99 | 24.22 | Node: DSV001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 497
1 | 498 | 498 | PH0000498 | X | Misamis Oriental | Cagayan De Oro City | Barangay 39 (Pob.) | 8.5038 | 124.7535 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.6 | 4.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.05 | 53.87 | 77.05 |  | B - Node 0.5-1 km | 0.79 | 0.01 | Line: CDO - BUENAVISTA via GINGOOG | Short node lateral candidate; confirm port/fiber capacity, access and route. | 498
1 | 499 | 499 | 0405625010 | Region IV-A (CALABARZON) | Quezon | Macalelon | Malabahay | 13.7548 | 122.2445 | R | 720 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.6 | 7.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.05 | 53.86 | 77.05 |  | F - Nearest node and line over 5 km | 7.6 | 7.42 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 499
1 | 500 | 500 | 1380601110 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 110 | 14.6193 | 120.96 | U | 2758 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.5 | 23.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.04 | 53.86 | 77.04 |  | A - Node within 0.5 km | 0.33 | 1.16 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 500
1 | 501 | 501 | PH0000501 | III | Nueva Ecija | Cabanatuan City | Bernardo District (Pob.) | 15.4924 | 120.9268 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.35 | 0.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.04 | 53.86 | 77.04 |  | D - Other node or line within 3 km | 3.87 | 2.16 | Line: SEGMENT 17 (ZARAGOSA - SAN JOSE) | Route options survey candidate: compare actual node lateral with approved line tap. | 501
1 | 502 | 502 | 1403201016 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Tawang | 17.5905 | 121.2204 | R | 836 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.28 | 19.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.03 | 53.85 | 77.03 |  | F - Nearest node and line over 5 km | 13.28 | 19.7 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 502
1 | 503 | 503 | 0200901003 | Region II (Cagayan Valley) | Batanes | Basco | San Antonio | 20.4505 | 121.9682 | R | 2260 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 223.95 | 217.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.03 | 53.85 | 77.03 |  | F - Nearest node and line over 5 km | 220.62 | 217.52 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 503
1 | 504 | 504 | PH0000504 | IV-A | Batangas | Lipa City | Poblacion Barangay 1 | 13.9422 | 121.1568 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.02 | 53.85 | 77.02 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.1 | Line: CLB001 TO BCY01 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 504
1 | 505 | 505 | PH0000505 | II | Nueva Vizcaya | Quezon N Vizcaya | Dagupan | 16.5341 | 121.3562 | R | 2464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.76 | 3.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77.01 | 53.84 | 77.01 |  | F - Nearest node and line over 5 km | 7.42 | 8.9 | Node: QZV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 505
1 | 506 | 506 | 0201529029 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Namabbalan Norte | 17.6157 | 121.6945 | R | 1566 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.39 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77 | 53.83 | 77 |  | C - Line within 0.5 km; node over 1 km | 4.15 | 0.24 | Line: TUGEGARAO FOC | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 506
1 | 507 | 507 | 1380601012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 12 | 14.6105 | 120.9686 | U | 2202 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.53 | 42.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 77 | 53.83 | 77 |  | A - Node within 0.5 km | 0.43 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 507
1 | 508 | 508 | 1380900006 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Navotas East | 14.6578 | 120.9482 | U | 2172 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 1.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.98 | 53.82 | 76.98 |  | A - Node within 0.5 km | 0.27 | 1.33 | Node: NAV001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 508
1 | 509 | 509 | 1400108013 | Cordillera Administrative Region (CAR) | Abra | La Paz | Udangan | 17.639 | 120.6141 | R | 549 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.18 | 1.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.97 | 53.81 | 76.97 |  | D - Other node or line within 3 km | 5.18 | 1.31 | Line: CABLE LAYED | Route options survey candidate: compare actual node lateral with approved line tap. | 509
1 | 510 | 510 | 0205009001 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Antutot | 16.3938 | 121.2154 | R | 1876 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.02 | 10.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.96 | 53.81 | 76.96 |  | F - Nearest node and line over 5 km | 12.02 | 10.16 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 510
1 | 511 | 511 | 0500518020 | Region V (Bicol Region) | Albay | Tiwi | Misibis | 13.509 | 123.6092 | R | 2262 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 0.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.96 | 53.8 | 76.96 |  | A - Node within 0.5 km | 0.17 | 0.03 | Line: EE | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 511
1 | 512 | 512 | 0405617013 | Region IV-A (CALABARZON) | Quezon | General Nakar | Pagsangahan | 14.6073 | 121.4506 | R | 1547 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.75 | 18.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.96 | 53.8 | 76.96 |  | F - Nearest node and line over 5 km | 11.75 | 18.31 | Node: TNR001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 512
1 | 513 | 513 | 1381400010 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Maytunas | 17.7043 | 120.7259 | U | 2950 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.94 | 53.79 | 76.94 |  | F - Nearest node and line over 5 km | 7.87 | 6.59 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 513
1 | 514 | 514 | 1907003014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Mapun | Liyubud | 17.2567 | 122.2305 | R | 3686 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.94 | 53.79 | 76.94 |  | F - Nearest node and line over 5 km | 29.68 | 34.51 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 514
1 | 515 | 515 | 0200901006 | Region II (Cagayan Valley) | Batanes | Basco | Kayhuvokan | 20.432 | 121.9583 | R | 1899 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 222.96 | 216.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.93 | 53.78 | 76.93 |  | F - Nearest node and line over 5 km | 218.67 | 215.56 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 515
1 | 516 | 516 | 1381400017 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | San Perfecto | 14.6031 | 121.0231 | U | 4909 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.77 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.92 | 53.78 | 76.92 |  | D - Other node or line within 3 km | 1.77 | 0.55 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 516
1 | 517 | 517 | 0600602029 | Region VI (Western Visayas) | Antique | Barbaza | Mayabay | 11.2745 | 122.1354 | R | 272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.9 | 40.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.91 | 53.77 | 76.91 |  | F - Nearest node and line over 5 km | 40.9 | 40.73 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 517
1 | 518 | 518 | 1108205012 | Region XI (Davao Region) | Davao de Oro | Maragusan | Mabugnao | 7.3411 | 126.112 | R | 415 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.6 | 24.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.89 | 53.76 | 76.89 |  | F - Nearest node and line over 5 km | 28.28 | 27.92 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 518
1 | 519 | 519 | 0307112017 | Region III (Central Luzon) | Zambales | San Narciso | Omaya | 15.0045 | 120.161 | R | 641 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.93 | 3.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.89 | 53.75 | 76.89 |  | D - Other node or line within 3 km | 2.93 | 3.41 | Node: SMZ002 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 519
1 | 520 | 520 | PH0000520 | IV-B | Palawan | Puerto Princesa City | Tagumpay (Pob.) | 9.8536 | 118.7049 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.97 | 2.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.88 | 53.75 | 76.88 |  | D - Other node or line within 3 km | 3.72 | 2.89 | Line: TAYTAY - PUERTO PRINCESA | Route options survey candidate: compare actual node lateral with approved line tap. | 520
1 | 521 | 521 | 0500518018 | Region V (Bicol Region) | Albay | Tiwi | Maynonong | 13.4975 | 123.6175 | R | 990 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.86 | 53.74 | 76.86 |  | C - Line within 0.5 km; node over 1 km | 1.46 | 0.11 | Line: LEGAZP - TIWI AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 521
1 | 522 | 522 | PH0000522 | VI | Iloilo | Iloilo City | Arguelles | 10.7004 | 122.5648 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.12 | 8.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.85 | 53.73 | 76.85 |  | C - Line within 0.5 km; node over 1 km | 1.53 | 0.43 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 522
1 | 523 | 523 | PH0000523 | VIII | Samar (Western Samar) | Catbalogan City | Canhawan Gote | 11.8261 | 124.7263 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.44 | 33.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.85 | 53.73 | 76.85 |  | F - Nearest node and line over 5 km | 58.66 | 58.63 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 523
1 | 524 | 524 | 0205010012 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Kayapa Proper East | 16.2834 | 120.8685 | R | 254 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.56 | 8.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.84 | 53.72 | 76.84 |  | F - Nearest node and line over 5 km | 8.56 | 8.21 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 524
1 | 525 | 525 | 0403403020 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Jose | 14.3458 | 121.0817 | U | 7234 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.84 | 53.72 | 76.84 |  | D - Other node or line within 3 km | 1.03 | 0.76 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 525
1 | 526 | 526 | PH0000526 | NIR | Negros Occidental | Bacolod City | Barangay 40 (Pob.) | 10.6627 | 122.954 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.83 | 53.72 | 76.83 |  | B - Node 0.5-1 km | 0.5 | 0.66 | Node: BDN002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 526
1 | 527 | 527 | 1403201007 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Gawa-an | 17.5162 | 121.2066 | R | 1006 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.92 | 12.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.82 | 53.71 | 76.82 |  | F - Nearest node and line over 5 km | 14.92 | 12.18 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 527
1 | 528 | 528 | 0600602015 | Region VI (Western Visayas) | Antique | Barbaza | Idao | 11.2736 | 122.1345 | R | 255 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.03 | 46.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.81 | 53.7 | 76.81 |  | F - Nearest node and line over 5 km | 41.04 | 40.87 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 528
1 | 529 | 529 | 1404405004 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Banawal | 17.1114 | 121.2952 | R | 2142 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 22.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.81 | 53.7 | 76.81 |  | D - Other node or line within 3 km | 1.64 | 22.49 | Node: NNV001 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 529
1 | 530 | 530 | 0806022022 | Region VIII (Eastern Visayas) | Samar | Paranas | Pabanog | 11.7853 | 125.0161 | R | 1888 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.61 | 58.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.81 | 53.69 | 76.81 |  | F - Nearest node and line over 5 km | 60.69 | 63.69 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 530
1 | 531 | 531 | 0600406021 | Region VI (Western Visayas) | Aklan | Ibajay | Naisud | 11.8057 | 122.1941 | R | 3304 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.71 | 0.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.8 | 53.69 | 76.8 |  | F - Nearest node and line over 5 km | 14.71 | 20.48 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 531
1 | 532 | 532 | PH0000532 | NIR | Negros Occidental | Bacolod City | Barangay 17 (Pob.) | 10.6406 | 123.008 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.72 | 2.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.79 | 53.68 | 76.79 |  | D - Other node or line within 3 km | 3.85 | 1.98 | Line: SAN CARLOS CITY - TALISAY CITY | Route options survey candidate: compare actual node lateral with approved line tap. | 532
1 | 533 | 533 | 0401033003 | Region IV-A (CALABARZON) | Batangas | Tingloy | Gamao | 13.654 | 120.9341 | R | 1065 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.79 | 16.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.78 | 53.68 | 76.78 |  | F - Nearest node and line over 5 km | 5.79 | 16.38 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 533
1 | 534 | 534 | 1908704013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Tubuan | 17.2541 | 122.2282 | R | 6357 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.77 | 53.67 | 76.77 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 534
1 | 535 | 535 | PH0000535 | VI | Iloilo | Iloilo City | Rizal Palapala II | 10.7049 | 122.5328 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7 | 2.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.76 | 53.67 | 76.76 |  | D - Other node or line within 3 km | 1.91 | 3.39 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 535
1 | 536 | 536 | PH0000536 | III | Nueva Ecija | Cabanatuan City | Dicarma (Pob.) | 15.4843 | 120.9713 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.13 | 0.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.72 | 53.63 | 76.72 |  | C - Line within 0.5 km; node over 1 km | 1.13 | 0.14 | Line: MULTINET - SANTA ROSA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 536
1 | 537 | 537 | 1400127003 | Cordillera Administrative Region (CAR) | Abra | Villaviciosa | Cal-lao | 17.4148 | 120.6421 | R | 925 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.83 | 16.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.72 | 53.63 | 76.72 |  | F - Nearest node and line over 5 km | 12.83 | 16.07 | Node: NKI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 537
1 | 538 | 538 | 0500518019 | Region V (Bicol Region) | Albay | Tiwi | Mayong | 13.52 | 123.5996 | R | 1693 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 0.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.72 | 53.63 | 76.72 |  | C - Line within 0.5 km; node over 1 km | 1.71 | 0.05 | Line: LEGAZP - TIWI AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 538
1 | 539 | 539 | 0205010023 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Alang Salacsac | 16.2827 | 120.8492 | R | 701 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.4 | 9.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.71 | 53.63 | 76.71 |  | F - Nearest node and line over 5 km | 9.4 | 9.12 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 539
1 | 540 | 540 | 0205010010 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Cabalatan Alang | 16.2495 | 120.8833 | R | 232 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.98 | 8.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.7 | 53.62 | 76.7 |  | F - Nearest node and line over 5 km | 9.98 | 8.4 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 540
1 | 541 | 541 | 1403213002 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Amlao | 17.3944 | 121.3188 | R | 852 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.27 | 1.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.7 | 53.62 | 76.7 |  | D - Other node or line within 3 km | 13.27 | 1.1 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 541
1 | 542 | 542 | 0600602031 | Region VI (Western Visayas) | Antique | Barbaza | Nalusdan | 11.206 | 122.0589 | R | 182 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.4 | 47.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.69 | 53.61 | 76.69 |  | F - Nearest node and line over 5 km | 51.07 | 44.86 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 542
1 | 543 | 543 | 0205009023 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Tadji | 16.3902 | 121.3966 | R | 1104 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.65 | 21.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.68 | 53.61 | 76.68 |  | F - Nearest node and line over 5 km | 13.65 | 21.35 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 543
1 | 544 | 544 | PH0000544 | IV-A | Batangas | Lipa City | Poblacion Barangay 8 | 13.8703 | 121.1605 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.68 | 53.61 | 76.68 |  | D - Other node or line within 3 km | 5.27 | 1.02 | Line: TANAUAN - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 544
1 | 545 | 545 | 1403209019 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pakawit | 17.5677 | 121.3945 | R | 1030 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.48 | 3.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.67 | 53.6 | 76.67 |  | E - Nearest node or line 3-5 km | 5.48 | 3.97 | Line: Tabuk-Conner | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 545
1 | 546 | 546 | 0205706015 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Wasid | 16.1368 | 121.5388 | R | 1278 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.94 | 18.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.66 | 53.6 | 76.66 |  | F - Nearest node and line over 5 km | 10.94 | 18.01 | Node: NTQ001-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 546
1 | 547 | 547 | 1108205023 | Region XI (Davao Region) | Davao de Oro | Maragusan | Tandik | 7.3191 | 126.1175 | R | 770 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.74 | 21.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.66 | 53.59 | 76.66 |  | F - Nearest node and line over 5 km | 28.91 | 28.55 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 547
1 | 548 | 548 | 0403403019 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Antonio | 14.3364 | 121.0882 | U | 39641 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.63 | 53.58 | 76.63 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.19 | Line: RELIANCE TO SAN PABLO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 548
1 | 549 | 549 | 0600602017 | Region VI (Western Visayas) | Antique | Barbaza | Igtunarum | 11.215 | 122.0495 | R | 76 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.14 | 47.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.63 | 53.57 | 76.63 |  | F - Nearest node and line over 5 km | 51.79 | 45.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 549
1 | 550 | 550 | 0200901002 | Region II (Cagayan Valley) | Batanes | Basco | Ihubok I | 20.4337 | 121.9596 | U | 1778 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 223.03 | 216.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.62 | 53.57 | 76.62 |  | F - Nearest node and line over 5 km | 218.84 | 215.74 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 550
1 | 551 | 551 | 1380601044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 44 | 14.618 | 120.9704 | U | 824 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.23 | 26.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.61 | 53.56 | 76.61 |  | B - Node 0.5-1 km | 0.82 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 551
1 | 552 | 552 | PH0000552 | III | Nueva Ecija | Cabanatuan City | Dimasalang (Pob.) | 15.5072 | 120.9749 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.82 | 0.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.6 | 53.55 | 76.6 |  | C - Line within 0.5 km; node over 1 km | 3.19 | 0.26 | Line: TALAVERA - MULTI NET | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 552
1 | 553 | 553 | 1403201005 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Buaya | 17.5793 | 121.2572 | R | 981 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.19 | 16.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.58 | 53.54 | 76.58 |  | F - Nearest node and line over 5 km | 9.19 | 16.36 | Node: PKK002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 553
1 | 554 | 554 | 0205706005 | Region II (Cagayan Valley) | Quirino | Nagtipunan | La Conwap | 16.2168 | 121.5997 | R | 442 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 7.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.57 | 53.53 | 76.57 |  | A - Node within 0.5 km | 0.17 | 7.1 | Node: NTQ001-BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 554
1 | 555 | 555 | 1380601105 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 105 | 14.6261 | 120.9616 | U | 25729 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.93 | 30.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.53 | 53.51 | 76.53 |  | B - Node 0.5-1 km | 0.91 | 1.16 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 555
1 | 556 | 556 | 1606805008 | Region XIII (Caraga) | Surigao del Sur | Cantilan | General Island | 9.4223 | 126.0105 | R | 971 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.09 | 9.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.52 | 53.49 | 76.52 |  | F - Nearest node and line over 5 km | 9.09 | 9.09 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 556
1 | 557 | 557 | 0600602038 | Region VI (Western Visayas) | Antique | Barbaza | Tabongtabong | 11.1664 | 122.0775 | R | 530 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.44 | 41.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.5 | 53.48 | 76.5 |  | F - Nearest node and line over 5 km | 47.44 | 40.97 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 557
1 | 558 | 558 | 0405805019 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Niño | 14.5863 | 121.1082 | U | 6105 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.6 | 0.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.49 | 53.47 | 76.49 |  | C - Line within 0.5 km; node over 1 km | 1.68 | 0.13 | Line: RELIANCE TO SINILOAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 558
1 | 559 | 559 | 0201509009 | Region II (Cagayan Valley) | Cagayan | Calayan | Babuyan Claro | 19.4962 | 121.9323 | R | 1964 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 115.99 | 112.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.49 | 53.47 | 76.49 |  | F - Nearest node and line over 5 km | 115.99 | 112.93 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 559
1 | 560 | 560 | 1404406007 | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | Buringal | 17.2175 | 121.4963 | R | 2560 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.69 | 12.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.47 | 53.46 | 76.47 |  | F - Nearest node and line over 5 km | 10.69 | 12.07 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 560
1 | 561 | 561 | 1381600021 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Palasan | 14.7064 | 120.9459 | U | 6692 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 1.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.46 | 53.45 | 76.46 |  | D - Other node or line within 3 km | 1.05 | 1.35 | Node: OBB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 561
1 | 562 | 562 | PH0000562 | IV-A | Laguna | San Pablo City | Barangay II-E (Pob.) | 14.0642 | 121.3244 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.77 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.45 | 53.44 | 76.45 |  | B - Node 0.5-1 km | 0.77 | 0.07 | Line: AE NGL001 TO SPO001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 562
1 | 563 | 563 | 0203104019 | Region II (Cagayan Valley) | Isabela | Benito Soliven | San Francisco | 16.939 | 121.9856 | R | 648 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.66 | 16.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.44 | 53.44 | 76.44 |  | F - Nearest node and line over 5 km | 5.66 | 16.31 | Node: BLI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 563
1 | 564 | 564 | 0600602010 | Region VI (Western Visayas) | Antique | Barbaza | Calapadan | 11.2375 | 122.0712 | R | 155 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.83 | 46.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.42 | 53.43 | 76.42 |  | F - Nearest node and line over 5 km | 48.62 | 48.37 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 564
1 | 565 | 565 | 1380601030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 30 | 14.6012 | 120.9623 | U | 171 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.53 | 40.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.42 | 53.42 | 76.42 |  | B - Node 0.5-1 km | 0.82 | 1 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 565
1 | 566 | 566 | 0203111012 | Region II (Cagayan Valley) | Isabela | Divilacan | Dibulos | 17.3099 | 122.3964 | R | 218 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.3 | 45.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.41 | 53.42 | 76.41 |  | F - Nearest node and line over 5 km | 47.48 | 53.09 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 566
1 | 567 | 567 | 1108204037 | Region XI (Davao Region) | Davao de Oro | Maco | Teresa | 7.3767 | 126.0259 | R | 2094 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.86 | 18.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.38 | 53.4 | 76.38 |  | F - Nearest node and line over 5 km | 18.86 | 18.38 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 567
1 | 568 | 568 | 1004325016 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Sibantang | 8.9827 | 124.9022 | R | 896 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.94 | 0.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.37 | 53.39 | 76.37 |  | C - Line within 0.5 km; node over 1 km | 2.94 | 0.2 | Line: CDO - BUENAVISTA via GINGOOG | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 568
1 | 569 | 569 | 0200901001 | Region II (Cagayan Valley) | Batanes | Basco | Ihubok II | 20.4522 | 121.9663 | U | 2641 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 223.93 | 217.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.37 | 53.39 | 76.37 |  | F - Nearest node and line over 5 km | 220.82 | 217.72 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 569
1 | 570 | 570 | 1380900002 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bagumbayan North | 14.6592 | 120.9487 | U | 1713 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.35 | 53.38 | 76.35 |  | A - Node within 0.5 km | 0.42 | 1.18 | Node: NAV001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 570
1 | 571 | 571 | PH0000571 | VIII | Samar (Western Samar) | Catbalogan City | Cagusipan | 11.9057 | 124.9261 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.48 | 32.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.34 | 53.37 | 76.34 |  | F - Nearest node and line over 5 km | 72.14 | 72.08 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 571
1 | 572 | 572 | 0205009011 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Dine | 16.2839 | 121.362 | R | 1215 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.09 | 29.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.34 | 53.37 | 76.34 |  | F - Nearest node and line over 5 km | 8.09 | 29.13 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 572
1 | 573 | 573 | 1380601112 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 112 | 14.6169 | 120.9604 | U | 5763 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.42 | 23.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.33 | 53.36 | 76.33 |  | A - Node within 0.5 km | 0.28 | 1.06 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 573
1 | 574 | 574 | 0203137044 | Region II (Cagayan Valley) | Isabela | Tumauini | San Vicente | 17.32 | 121.8254 | R | 1798 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.35 | 2.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.3 | 53.34 | 76.3 |  | D - Other node or line within 3 km | 5.35 | 2.17 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Route options survey candidate: compare actual node lateral with approved line tap. | 574
1 | 575 | 575 | 0806405001 | Region VIII (Eastern Visayas) | Southern Leyte | Libagon | Biasong | 10.3536 | 125.03 | R | 552 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.67 | 7.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.27 | 53.32 | 76.27 |  | F - Nearest node and line over 5 km | 32.93 | 26.36 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 575
1 | 576 | 576 | 0102911003 | Region I (Ilocos Region) | Ilocos Sur | Lidlidda | Bugui | 17.2679 | 120.5196 | R | 244 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 1.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.27 | 53.32 | 76.27 |  | D - Other node or line within 3 km | 1.92 | 1.71 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 576
1 | 577 | 577 | 0205009008 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Capisaan | 16.3322 | 121.3937 | R | 1477 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.75 | 26.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.26 | 53.31 | 76.26 |  | F - Nearest node and line over 5 km | 10.75 | 26.22 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 577
1 | 578 | 578 | 0205009016 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Malabing | 16.3468 | 121.3753 | R | 887 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.28 | 26.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.26 | 53.31 | 76.26 |  | F - Nearest node and line over 5 km | 9.28 | 26.31 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 578
1 | 579 | 579 | 0806407016 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Cagnituan | 10.159 | 124.9152 | R | 360 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.67 | 5.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.25 | 53.31 | 76.25 |  | F - Nearest node and line over 5 km | 9.84 | 5.02 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 579
1 | 580 | 580 | 0506204013 | Region V (Bicol Region) | Sorsogon | Bulusan | Salvacion | 12.7216 | 124.0962 | R | 488 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.76 | 1.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.25 | 53.3 | 76.25 |  | F - Nearest node and line over 5 km | 5.76 | 6.89 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 580
1 | 581 | 581 | PH0000581 | VI | Iloilo | Iloilo City | Rizal Estanzuela | 10.6931 | 122.5604 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 1.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.23 | 53.3 | 76.23 |  | D - Other node or line within 3 km | 1.95 | 1.32 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 581
1 | 582 | 582 | 0405622032 | Region IV-A (CALABARZON) | Quezon | Lopez | Esperanza Ilaya | 13.8978 | 122.2562 | R | 263 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.54 | 3.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.23 | 53.29 | 76.23 |  | D - Other node or line within 3 km | 1.34 | 1.31 | Line: LZQ001 TO DEL GALLEGO | Route options survey candidate: compare actual node lateral with approved line tap. | 582
1 | 583 | 583 | PH0000583 | VIII | Leyte | Tacloban City | Barangay 7 | 11.3026 | 124.9518 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.23 | 6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.23 | 53.29 | 76.23 |  | F - Nearest node and line over 5 km | 8.92 | 11.81 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 583
1 | 584 | 584 | 0806002022 | Region VIII (Eastern Visayas) | Samar | Basey | Mabini | 11.4211 | 125.142 | R | 2868 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.27 | 27.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.2 | 53.27 | 76.2 |  | F - Nearest node and line over 5 km | 25.27 | 27.33 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 584
1 | 585 | 585 | 1003514001 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Bacayawan | 8.0798 | 124.0634 | R | 1212 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.64 | 16.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.18 | 53.26 | 76.18 |  | F - Nearest node and line over 5 km | 24.49 | 11.64 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 585
1 | 586 | 586 | 1208004009 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Lumasal | 5.8883 | 124.85 | R | 4847 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.12 | 41.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.18 | 53.26 | 76.18 |  | F - Nearest node and line over 5 km | 38.12 | 41.53 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 586
1 | 587 | 587 | 0603002030 | Region VI (Western Visayas) | Iloilo | Alimodian | Lico | 10.8563 | 122.417 | R | 330 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.64 | 3.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.17 | 53.25 | 76.17 |  | E - Nearest node or line 3-5 km | 13.23 | 4.45 | Line: 7,761 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 587
1 | 588 | 588 | 1380601101 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 101 | 14.6257 | 120.9609 | U | 15824 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.47 | 39.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.16 | 53.24 | 76.16 |  | B - Node 0.5-1 km | 0.88 | 1.23 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 588
1 | 589 | 589 | 1380601020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 20 | 14.6023 | 120.9624 | U | 47162 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.98 | 30.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.14 | 53.23 | 76.14 |  | B - Node 0.5-1 km | 0.93 | 0.93 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 589
1 | 590 | 590 | 0205706007 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Mataddi | 16.2679 | 121.4062 | R | 556 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.12 | 25.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.13 | 53.22 | 76.13 |  | F - Nearest node and line over 5 km | 13.12 | 25.78 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 590
1 | 591 | 591 | 1108201010 | Region XI (Davao Region) | Davao de Oro | Compostela | Panansalan | 7.6792 | 126.074 | R | 1104 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.59 | 9.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.12 | 53.21 | 76.12 |  | F - Nearest node and line over 5 km | 16.59 | 9.53 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 591
1 | 592 | 592 | 0403429015 | Region IV-A (CALABARZON) | Laguna | Siniloan | Magsaysay | 14.4994 | 121.5219 | R | 2603 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.13 | 10.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.11 | 53.21 | 76.11 |  | E - Nearest node or line 3-5 km | 4.13 | 10.05 | Node: FYL001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 592
1 | 593 | 593 | 1208004013 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Pananag | 5.8837 | 124.8637 | R | 1725 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.13 | 40.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.11 | 53.21 | 76.11 |  | F - Nearest node and line over 5 km | 37.13 | 40.68 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 593
1 | 594 | 594 | 0203133017 | Region II (Cagayan Valley) | Isabela | San Pablo | Tupa | 17.481 | 121.8766 | R | 2482 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.35 | 7.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.1 | 53.2 | 76.1 |  | F - Nearest node and line over 5 km | 12.35 | 7.65 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 594
1 | 595 | 595 | 1408106017 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | San Antonio | 18.2511 | 121.3487 | R | 245 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.44 | 0.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.1 | 53.2 | 76.1 |  | E - Nearest node or line 3-5 km | 3.11 | 12.32 | Node: PLY001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 595
1 | 596 | 596 | 1401109007 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Tacadang | 16.7361 | 120.5799 | R | 1701 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.15 | 17.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.09 | 53.19 | 76.09 |  | F - Nearest node and line over 5 km | 9.15 | 17.94 | Node: KIB001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 596
1 | 597 | 597 | 0600618022 | Region VI (Western Visayas) | Antique | Valderrama | Alon | 11.0566 | 122.2169 | R | 193 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.61 | 32.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.04 | 53.16 | 76.04 |  | F - Nearest node and line over 5 km | 34.61 | 32.92 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 597
1 | 598 | 598 | PH0000598 | II | Nueva Vizcaya | Kasibu | Pacquet | 16.2736 | 121.3443 | R | 1559 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.17 | 27.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.04 | 53.16 | 76.04 |  | F - Nearest node and line over 5 km | 7.17 | 27.86 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 598
1 | 599 | 599 | 1400115007 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Lat-ey | 17.5835 | 121.0674 | R | 216 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.12 | 25.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76.02 | 53.14 | 76.02 |  | F - Nearest node and line over 5 km | 29.12 | 25.64 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 599
1 | 600 | 600 | 1380601042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 42 | 14.6157 | 120.9699 | U | 2207 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.46 | 24.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76 | 53.13 | 76 |  | B - Node 0.5-1 km | 0.81 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 600
1 | 601 | 601 | 0205002022 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Ocao-Capiniaan | 16.2029 | 121.0051 | R | 1053 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.8 | 3.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76 | 53.13 | 76 |  | E - Nearest node or line 3-5 km | 8.8 | 3.83 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 601
1 | 602 | 602 | PH0000602 | VI | Iloilo | Iloilo City | Magsaysay Village | 10.4945 | 122.0258 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.24 | 2.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 76 | 53.13 | 76 |  | F - Nearest node and line over 5 km | 31.29 | 8.22 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 602
1 | 603 | 603 | 0205706009 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Old Gumiad | 16.1272 | 121.3939 | R | 962 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.88 | 28.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.99 | 53.12 | 75.99 |  | F - Nearest node and line over 5 km | 19.88 | 28.32 | Node: DNV002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 603
1 | 604 | 604 | PH0000604 | X | Misamis Oriental | Cagayan De Oro City | Barangay 40 (Pob.) | 8.4702 | 124.7029 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.98 | 53.12 | 75.98 |  | C - Line within 0.5 km; node over 1 km | 3.23 | 0.04 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 604
1 | 605 | 605 | 1400102005 | Cordillera Administrative Region (CAR) | Abra | Boliney | Dumagas | 17.412 | 120.765 | R | 506 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.35 | 23.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.98 | 53.11 | 75.98 |  | F - Nearest node and line over 5 km | 25.35 | 23.29 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 605
1 | 606 | 606 | 1380601029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 29 | 14.6024 | 120.9644 | U | 4540 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.69 | 44.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.97 | 53.11 | 75.97 |  | B - Node 0.5-1 km | 0.75 | 0.74 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 606
1 | 607 | 607 | 0205009007 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Biyoy | 16.2367 | 121.4072 | R | 2296 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.97 | 25.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.97 | 53.11 | 75.97 |  | F - Nearest node and line over 5 km | 14.97 | 25.86 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 607
1 | 608 | 608 | 1380601107 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 107 | 14.6187 | 120.9607 | U | 7216 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.25 | 23.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.96 | 53.11 | 75.96 |  | A - Node within 0.5 km | 0.23 | 1.07 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 608
1 | 609 | 609 | PH0000609 | II | Nueva Vizcaya | Kasibu | Seguem | 16.2785 | 121.3112 | R | 1559 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.6 | 24.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.96 | 53.1 | 75.96 |  | E - Nearest node or line 3-5 km | 4.6 | 24.45 | Node: KSV001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 609
1 | 610 | 610 | PH0000610 | NIR | Negros Occidental | Bacolod City | Barangay 10 (Pob.) | 10.6624 | 123.0799 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 0.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.95 | 53.09 | 75.95 |  | E - Nearest node or line 3-5 km | 4.77 | 7.39 | Node: BDN004 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 610
1 | 611 | 611 | 0103315002 | Region I (Ilocos Region) | La Union | San Gabriel | Amontoc | 16.6569 | 120.4658 | R | 2058 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.88 | 13.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.93 | 53.09 | 75.93 |  | F - Nearest node and line over 5 km | 7.88 | 13.32 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 611
1 | 612 | 612 | PH0000612 | NIR | Negros Occidental | Bacolod City | Barangay 23 (Pob.) | 10.6081 | 122.9652 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.29 | 0.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.93 | 53.08 | 75.93 |  | D - Other node or line within 3 km | 2.93 | 2.69 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 612
1 | 613 | 613 | 1003511006 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lamigadato | 12.3926 | 121.2039 | R | 689 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.99 | 9.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.93 | 53.08 | 75.93 |  | F - Nearest node and line over 5 km | 11.01 | 8.19 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 613
1 | 614 | 614 | 0806017027 | Region VIII (Eastern Visayas) | Samar | Santa Rita | San Pascual | 11.4037 | 124.9964 | R | 1016 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.26 | 21.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.92 | 53.08 | 75.92 |  | F - Nearest node and line over 5 km | 18.26 | 21.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 614
1 | 615 | 615 | 0203111004 | Region II (Cagayan Valley) | Isabela | Divilacan | Dicaroyan | 17.3431 | 122.2561 | R | 370 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.32 | 40.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.92 | 53.07 | 75.92 |  | F - Nearest node and line over 5 km | 38.32 | 40.79 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 615
1 | 616 | 616 | 1380604007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 274 | 14.5969 | 120.9717 | U | 2003 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.26 | 34.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.9 | 53.06 | 75.9 |  | D - Other node or line within 3 km | 1.12 | 1.01 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 616
1 | 617 | 617 | 1907011008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Nunukan | 17.2563 | 122.2294 | R | 2665 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.27 | 29.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.9 | 53.06 | 75.9 |  | F - Nearest node and line over 5 km | 29.56 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 617
1 | 618 | 618 | 1208003005 | Region XII (SOCCSKSARGEN) | Sarangani | Kiamba | Katubao | 5.8951 | 124.8297 | U | 5601 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.66 | 42.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.89 | 53.06 | 75.89 |  | F - Nearest node and line over 5 km | 39.66 | 42.88 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 618
1 | 619 | 619 | 1108211009 | Region XI (Davao Region) | Davao de Oro | Pantukan | Tagdangua | 7.2067 | 125.8825 | U | 4866 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.26 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.88 | 53.05 | 75.88 |  | C - Line within 0.5 km; node over 1 km | 8.26 | 0.05 | Line: TAGUM - PANTUKAN SEGMENT 4 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 619
1 | 620 | 620 | 0803730010 | Region VIII (Eastern Visayas) | Leyte | Macarthur | Lanawan | 10.8573 | 124.8591 | R | 353 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.98 | 11.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.87 | 53.04 | 75.87 |  | F - Nearest node and line over 5 km | 16.98 | 11.39 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 620
1 | 621 | 621 | 0803730013 | Region VIII (Eastern Visayas) | Leyte | Macarthur | Oguisan | 10.8234 | 124.8633 | R | 157 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.35 | 10.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.87 | 53.04 | 75.87 |  | F - Nearest node and line over 5 km | 17.35 | 10.1 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 621
1 | 622 | 622 | 1381600024 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pasolo | 14.7054 | 120.9543 | U | 8266 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.85 | 53.02 | 75.85 |  | B - Node 0.5-1 km | 0.7 | 0.68 | Line: 48 CORE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 622
1 | 623 | 623 | PH0000623 | VI | Iloilo | Iloilo City | Libertad, Santa Isabel | 10.6901 | 122.5771 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.93 | 6.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.84 | 53.02 | 75.84 |  | D - Other node or line within 3 km | 2.82 | 1.5 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 623
1 | 624 | 624 | 1400112006 | Cordillera Administrative Region (CAR) | Abra | Langiden | Malapaao | 17.6267 | 120.5525 | R | 821 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.89 | 6.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.82 | 53.01 | 75.82 |  | F - Nearest node and line over 5 km | 7.89 | 6.93 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 624
1 | 625 | 625 | 0601909024 | Region VI (Western Visayas) | Capiz | Panay | Jamul-awon | 11.5325 | 122.8611 | R | 831 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.75 | 5.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.81 | 53 | 75.81 |  | F - Nearest node and line over 5 km | 6.75 | 5.72 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 625
1 | 626 | 626 | 0600618008 | Region VI (Western Visayas) | Antique | Valderrama | Busog | 11.071 | 122.2418 | R | 203 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.74 | 31.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.79 | 52.99 | 75.79 |  | F - Nearest node and line over 5 km | 32.74 | 31.16 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 626
1 | 627 | 627 | 0205009005 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Binogawan | 16.3746 | 121.3939 | R | 891 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.43 | 22.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.77 | 52.97 | 75.77 |  | F - Nearest node and line over 5 km | 12.43 | 22.73 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 627
1 | 628 | 628 | PH0000628 | IV-A | Laguna | San Pablo City | Barangay VII-E (Pob.) | 14.0322 | 121.3653 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 0.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.75 | 52.96 | 75.75 |  | D - Other node or line within 3 km | 3.29 | 2.46 | Line: STO. TOMAS - CANDELARIA | Route options survey candidate: compare actual node lateral with approved line tap. | 628
1 | 629 | 629 | 1705313002 | MIMAROPA Region | Palawan | Linapacan | Cabunlawan | 11.3838 | 120.098 | R | 841 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.68 | 89.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.73 | 52.94 | 75.73 |  | F - Nearest node and line over 5 km | 59.68 | 89.6 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 629
1 | 630 | 630 | 0500518001 | Region V (Bicol Region) | Albay | Tiwi | Bagumbayan | 13.4525 | 123.6619 | R | 2758 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 1.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.72 | 52.93 | 75.72 |  | D - Other node or line within 3 km | 1.59 | 1.23 | Line: EE | Route options survey candidate: compare actual node lateral with approved line tap. | 630
1 | 631 | 631 | 0600406003 | Region VI (Western Visayas) | Aklan | Ibajay | Antipolo | 11.8015 | 122.1226 | R | 844 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.88 | 1.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.71 | 52.93 | 75.71 |  | F - Nearest node and line over 5 km | 20.88 | 27.39 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 631
1 | 632 | 632 | 0806017004 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Bagolibas | 11.3943 | 125.0012 | R | 703 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.2 | 20.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.7 | 52.92 | 75.7 |  | F - Nearest node and line over 5 km | 17.2 | 20.23 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 632
1 | 633 | 633 | 0501727014 | Region V (Bicol Region) | Camarines Sur | Pasacao | San Antonio | 13.5886 | 122.9318 | R | 612 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.35 | 12.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.7 | 52.92 | 75.7 |  | F - Nearest node and line over 5 km | 12.35 | 11.92 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 633
1 | 634 | 634 | 1380601039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 39 | 14.6193 | 120.9716 | U | 2395 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.83 | 36.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.7 | 52.92 | 75.7 |  | B - Node 0.5-1 km | 0.86 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 634
1 | 635 | 635 | 0907224007 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Baliguian | Linay | 7.774 | 122.3643 | R | 2277 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.39 | 17.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.69 | 52.92 | 75.69 |  | F - Nearest node and line over 5 km | 20.39 | 17.3 | Line: IPIL - TUNGAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 635
1 | 636 | 636 | 0806405012 | Region VIII (Eastern Visayas) | Southern Leyte | Libagon | Punta | 10.2966 | 125.052 | R | 249 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.63 | 6.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.69 | 52.92 | 75.69 |  | F - Nearest node and line over 5 km | 30.42 | 26.29 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 636
1 | 637 | 637 | 0600618009 | Region VI (Western Visayas) | Antique | Valderrama | Cananghan | 11.025 | 122.1841 | R | 308 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.98 | 32.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.69 | 52.91 | 75.69 |  | F - Nearest node and line over 5 km | 36.98 | 32.16 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 637
1 | 638 | 638 | 1380601118 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 118 | 14.6114 | 120.9632 | U | 11169 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.22 | 21.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.68 | 52.91 | 75.68 |  | B - Node 0.5-1 km | 0.74 | 0.65 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 638
1 | 639 | 639 | 1705313006 | MIMAROPA Region | Palawan | Linapacan | Maroyogroyog | 11.4714 | 119.7725 | R | 2160 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.94 | 77.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.68 | 52.91 | 75.68 |  | F - Nearest node and line over 5 km | 29.94 | 77.55 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 639
1 | 640 | 640 | 1380601017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 17 | 14.6029 | 120.9617 | U | 1212 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.51 | 43.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.67 | 52.9 | 75.67 |  | B - Node 0.5-1 km | 0.96 | 0.97 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 640
1 | 641 | 641 | PH0000641 | NIR | Negros Occidental | Bacolod City | Barangay 31 (Pob.) | 10.6627 | 122.9541 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.65 | 52.89 | 75.65 |  | B - Node 0.5-1 km | 0.5 | 0.67 | Node: BDN002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 641
1 | 642 | 642 | 1108202022 | Region XI (Davao Region) | Davao de Oro | Laak | Bullucan | 7.9037 | 125.9097 | R | 1345 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.43 | 24.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.65 | 52.88 | 75.65 |  | F - Nearest node and line over 5 km | 18.23 | 15.91 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 642
1 | 643 | 643 | 1903613049 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Bacayawan | 17.2554 | 122.2291 | R | 576 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.64 | 52.88 | 75.64 |  | F - Nearest node and line over 5 km | 29.47 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 643
1 | 644 | 644 | 0405606011 | Region IV-A (CALABARZON) | Quezon | Burdeos | Palasan | 14.8532 | 122.0502 | R | 1151 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.78 | 78.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.64 | 52.88 | 75.64 |  | F - Nearest node and line over 5 km | 42.78 | 78.76 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 644
1 | 645 | 645 | 1380601121 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 121 | 14.6124 | 120.9615 | U | 4648 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.06 | 27.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.64 | 52.88 | 75.64 |  | B - Node 0.5-1 km | 0.63 | 0.85 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 645
1 | 646 | 646 | 0600409009 | Region VI (Western Visayas) | Aklan | Libacao | Dalagsa-an | 11.2802 | 122.2721 | R | 2150 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.8 | 31.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.64 | 52.88 | 75.64 |  | F - Nearest node and line over 5 km | 32.8 | 32.68 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 646
1 | 647 | 647 | 1380601016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 16 | 14.6041 | 120.9638 | U | 1522 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.75 | 27.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.63 | 52.87 | 75.63 |  | B - Node 0.5-1 km | 0.7 | 0.71 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 647
1 | 648 | 648 | 0205001009 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Tiblac | 16.5201 | 121.0763 | R | 2624 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.36 | 6.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.63 | 52.87 | 75.63 |  | F - Nearest node and line over 5 km | 8.36 | 6.64 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 648
1 | 649 | 649 | 0600410007 | Region VI (Western Visayas) | Aklan | Madalag | Catabana | 11.5391 | 122.302 | R | 465 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.08 | 7.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.63 | 52.87 | 75.63 |  | F - Nearest node and line over 5 km | 8.08 | 7.34 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 649
1 | 650 | 650 | PH0000650 | IV-A | Laguna | San Pablo City | Barangay II-B (Pob.) | 14.0648 | 121.3215 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.62 | 52.87 | 75.62 |  | C - Line within 0.5 km; node over 1 km | 1.06 | 0.03 | Line: AE NGL001 TO SPO001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 650
1 | 651 | 651 | PH0000651 | IV-B | Palawan | Puerto Princesa City | Matahimik (Pob.) | 10 | 118.8949 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.3 | 4.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.62 | 52.86 | 75.62 |  | C - Line within 0.5 km; node over 1 km | 4.73 | 0.45 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 651
1 | 652 | 652 | 0600612023 | Region VI (Western Visayas) | Antique | Patnongon | Quezon | 10.9333 | 122.0807 | R | 319 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.59 | 17.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.61 | 52.86 | 75.61 |  | F - Nearest node and line over 5 km | 24.59 | 17.13 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 652
1 | 653 | 653 | 1380400015 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Potrero | 14.6695 | 120.998 | U | 43357 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.31 | 0.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.61 | 52.86 | 75.61 |  | D - Other node or line within 3 km | 1.31 | 1.07 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 653
1 | 654 | 654 | 0806008010 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Osmeña | 11.6904 | 125.0545 | R | 492 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.89 | 58.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.61 | 52.86 | 75.61 |  | F - Nearest node and line over 5 km | 50.44 | 53.36 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 654
1 | 655 | 655 | 1903621012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Katumbacan | 17.2545 | 122.2285 | R | 744 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 37.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.61 | 52.86 | 75.61 |  | F - Nearest node and line over 5 km | 29.36 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 655
1 | 656 | 656 | 1903601024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Rorowan | 17.2555 | 122.2292 | R | 564 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.59 | 52.85 | 75.59 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 656
1 | 657 | 657 | 1906611013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Langhub | 17.2554 | 122.2295 | R | 1366 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.59 | 52.85 | 75.59 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 657
1 | 658 | 658 | 0907216006 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Lakiki | 7.2746 | 122.0837 | R | 648 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.89 | 17.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.58 | 52.84 | 75.58 |  | F - Nearest node and line over 5 km | 19.89 | 17.7 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 658
1 | 659 | 659 | 1908822002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Bongo | 17.2551 | 122.2291 | R | 2565 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.58 | 52.84 | 75.58 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 659
1 | 660 | 660 | 1906613056 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Upper Laus | 17.2554 | 122.2295 | R | 1221 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.57 | 52.83 | 75.57 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 660
1 | 661 | 661 | 0600410025 | Region VI (Western Visayas) | Aklan | Madalag | Tigbawan | 11.5081 | 122.2958 | R | 742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.26 | 9.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.57 | 52.83 | 75.57 |  | F - Nearest node and line over 5 km | 10.26 | 9.74 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 661
1 | 662 | 662 | 1906613036 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Lumping Pigih Daho | 17.2554 | 122.2295 | U | 1800 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.56 | 52.82 | 75.56 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 662
1 | 663 | 663 | 1003514033 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Tamparan | 7.9952 | 124.0893 | R | 1989 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.76 | 16.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.55 | 52.82 | 75.55 |  | F - Nearest node and line over 5 km | 20.44 | 18.91 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 663
1 | 664 | 664 | 1906613009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Buroh | 17.2554 | 122.2295 | R | 1451 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.55 | 52.82 | 75.55 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 664
1 | 665 | 665 | PH0000665 | BARMM (LaMa+SGA) | Lanao Del Sur | Sultan Gumander (Picong) | Anas | 17.2545 | 122.228 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.55 | 52.82 | 75.55 |  | F - Nearest node and line over 5 km | 29.32 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 665
1 | 666 | 666 | 1908806017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Mao | 17.255 | 122.229 | R | 994 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.55 | 52.81 | 75.55 |  | F - Nearest node and line over 5 km | 29.43 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 666
1 | 667 | 667 | 1908806021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Puya | 17.255 | 122.229 | R | 1003 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 29.43 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 667
1 | 668 | 668 | 1003516009 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Culubun | 8.0348 | 124.1419 | R | 1499 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.84 | 12.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 14.84 | 12.34 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 668
1 | 669 | 669 | 1003514013 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lininding | 7.9956 | 124.0887 | R | 1863 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.5 | 19.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 20.5 | 18.97 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 669
1 | 670 | 670 | 1003514011 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lindongan | 7.9964 | 124.0891 | R | 1280 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.47 | 16.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 20.45 | 18.93 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 670
1 | 671 | 671 | 0600612032 | Region VI (Western Visayas) | Antique | Patnongon | Villa Flores | 10.9274 | 122.0752 | R | 240 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.69 | 16.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 23.69 | 16.24 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 671
1 | 672 | 672 | 1003514014 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lumba-Bayabao | 7.9948 | 124.0881 | R | 1585 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.12 | 17.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | F - Nearest node and line over 5 km | 20.57 | 19.04 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 672
1 | 673 | 673 | 1003511014 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Pelingkingan | 9.0068 | 125.2067 | R | 1040 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.86 | 8.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.54 | 52.81 | 75.54 |  | C - Line within 0.5 km; node over 1 km | 3.08 | 0.02 | Line: CDO - BUENAVISTA via GINGOOG | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 673
1 | 674 | 674 | 1906613057 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Upper Sinumaan | 17.2555 | 122.2295 | U | 1715 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.53 | 52.81 | 75.53 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 674
1 | 675 | 675 | 1908806015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Mangadeg | 17.255 | 122.229 | R | 1344 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.53 | 52.81 | 75.53 |  | F - Nearest node and line over 5 km | 29.43 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 675
1 | 676 | 676 | 0907333010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Matalang | 7.8548 | 123.1511 | R | 753 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.47 | 7.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.53 | 52.8 | 75.53 |  | F - Nearest node and line over 5 km | 17.47 | 7.87 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 676
1 | 677 | 677 | 1705313009 | MIMAROPA Region | Palawan | Linapacan | Pical | 11.2663 | 119.6739 | R | 1771 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.51 | 52.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.53 | 52.8 | 75.53 |  | F - Nearest node and line over 5 km | 13.51 | 52.4 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 677
1 | 678 | 678 | 1003514012 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Lingco-an | 8.0785 | 124.0633 | R | 1011 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.83 | 15.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.53 | 52.8 | 75.53 |  | F - Nearest node and line over 5 km | 24.45 | 11.79 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 678
1 | 679 | 679 | 1903638013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Kalilangan | 17.2535 | 122.2276 | R | 545 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | F - Nearest node and line over 5 km | 29.21 | 34.11 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 679
1 | 680 | 680 | 1003521010 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Lindongan | 8.0469 | 123.9448 | R | 411 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.6 | 11.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | F - Nearest node and line over 5 km | 16.04 | 8.9 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 680
1 | 681 | 681 | 0907307007 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Banta-ao | 7.8061 | 123.338 | R | 389 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.49 | 1.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | D - Other node or line within 3 km | 11.49 | 1.55 | Line: PAGADIAN - BUUG | Route options survey candidate: compare actual node lateral with approved line tap. | 681
1 | 682 | 682 | 0600410020 | Region VI (Western Visayas) | Aklan | Madalag | Poblacion | 11.5275 | 122.3058 | R | 1870 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.24 | 7.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | F - Nearest node and line over 5 km | 8.24 | 7.59 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 682
1 | 683 | 683 | 0907344002 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Busol | 7.8539 | 123.2388 | R | 752 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.23 | 1.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | D - Other node or line within 3 km | 22.23 | 1.56 | Line: PAGADIAN - BUUG | Route options survey candidate: compare actual node lateral with approved line tap. | 683
1 | 684 | 684 | 1903610032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Kining | 17.2544 | 122.2284 | R | 869 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.8 | 75.52 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 684
1 | 685 | 685 | 1906605010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Maimbung | Kandang | 17.2551 | 122.2287 | R | 1147 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.31 | 11.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.79 | 75.52 |  | F - Nearest node and line over 5 km | 29.42 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 685
1 | 686 | 686 | 1003514025 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Pantaon | 8.0787 | 124.0639 | R | 675 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.77 | 16.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.52 | 52.79 | 75.52 |  | F - Nearest node and line over 5 km | 24.4 | 11.76 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 686
1 | 687 | 687 | 1003514031 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Tagoranao | 7.996 | 124.0879 | R | 452 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.26 | 17.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.51 | 52.79 | 75.51 |  | F - Nearest node and line over 5 km | 20.58 | 19.06 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 687
1 | 688 | 688 | 1705313004 | MIMAROPA Region | Palawan | Linapacan | Decabaitot | 11.6484 | 119.9636 | R | 875 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.27 | 104.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.51 | 52.79 | 75.51 |  | F - Nearest node and line over 5 km | 48.27 | 104.28 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 688
1 | 689 | 689 | 1380601037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 37 | 14.6021 | 120.9615 | U | 2119 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.7 | 43.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.51 | 52.79 | 75.51 |  | B - Node 0.5-1 km | 0.92 | 1.02 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 689
1 | 690 | 690 | 0600410018 | Region VI (Western Visayas) | Aklan | Madalag | Paningayan | 11.5393 | 122.3137 | R | 1060 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.88 | 6.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.5 | 52.78 | 75.5 |  | F - Nearest node and line over 5 km | 6.88 | 6.18 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 690
1 | 691 | 691 | 0907216002 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Basak | 7.3251 | 122.0939 | R | 159 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.99 | 22.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.5 | 52.78 | 75.5 |  | F - Nearest node and line over 5 km | 20.66 | 18.32 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 691
1 | 692 | 692 | 1380601123 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 123 | 14.6111 | 120.9621 | U | 8923 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.79 | 20.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.5 | 52.78 | 75.5 |  | B - Node 0.5-1 km | 0.77 | 0.76 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 692
1 | 693 | 693 | 0806022044 | Region VIII (Eastern Visayas) | Samar | Paranas | Tenani | 11.7504 | 125.0591 | R | 2197 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.79 | 68.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.5 | 52.78 | 75.5 |  | F - Nearest node and line over 5 km | 57.13 | 60.05 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 693
1 | 694 | 694 | 0600410016 | Region VI (Western Visayas) | Aklan | Madalag | Napnot | 11.5182 | 122.3192 | R | 535 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.51 | 7.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.78 | 75.49 |  | F - Nearest node and line over 5 km | 7.51 | 7.09 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 694
1 | 695 | 695 | 0600410006 | Region VI (Western Visayas) | Aklan | Madalag | Cabilawan | 11.5379 | 122.2935 | R | 515 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.01 | 8.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.78 | 75.49 |  | F - Nearest node and line over 5 km | 9.01 | 8.24 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 695
1 | 696 | 696 | 1108202029 | Region XI (Davao Region) | Davao de Oro | Laak | Inacayan | 7.7977 | 125.8068 | R | 1095 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.97 | 25.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.78 | 75.49 |  | F - Nearest node and line over 5 km | 27.67 | 21.71 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 696
1 | 697 | 697 | 0502002012 | Region V (Bicol Region) | Catanduanes | Baras | J. M. Alberto | 13.7139 | 124.3845 | R | 764 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.08 | 78.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.78 | 75.49 |  | F - Nearest node and line over 5 km | 56.69 | 80.85 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 697
1 | 698 | 698 | 1380601038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 38 | 14.6159 | 120.9737 | U | 2957 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.65 | 38.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.77 | 75.49 |  | B - Node 0.5-1 km | 0.99 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 698
1 | 699 | 699 | 0600410009 | Region VI (Western Visayas) | Aklan | Madalag | Galicia | 11.5475 | 122.2782 | R | 386 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.62 | 9.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.49 | 52.77 | 75.49 |  | F - Nearest node and line over 5 km | 8.62 | 9.4 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 699
1 | 700 | 700 | 0405805020 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Domingo | 14.5833 | 121.1112 | U | 45228 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.47 | 52.76 | 75.47 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.35 | Line: RELIANCE TO SINILOAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 700
1 | 701 | 701 | 0600609018 | Region VI (Western Visayas) | Antique | Laua-An | Laua-an | 11.0799 | 122.0548 | R | 399 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.31 | 36.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.46 | 52.76 | 75.46 |  | F - Nearest node and line over 5 km | 37.55 | 31.04 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 701
1 | 702 | 702 | PH0000702 | VI | Iloilo | Iloilo City | Burgos-Mabini-Plaza | 10.7173 | 122.5656 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.46 | 0.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.45 | 52.75 | 75.45 |  | A - Node within 0.5 km | 0.46 | 0.36 | Line: 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 702
1 | 703 | 703 | 1403214016 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lay-asan | 17.2836 | 121.3906 | R | 714 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.11 | 13.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.42 | 52.72 | 75.42 |  | F - Nearest node and line over 5 km | 12.11 | 13.36 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 703
1 | 704 | 704 | 0405617007 | Region IV-A (CALABARZON) | Quezon | General Nakar | Mahabang Lalim | 14.6897 | 121.5509 | R | 701 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.1 | 30.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.41 | 52.72 | 75.41 |  | F - Nearest node and line over 5 km | 8.1 | 30.19 | Node: RLQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 704
1 | 705 | 705 | 1400113010 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Subagan | 17.5461 | 120.8932 | R | 605 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.29 | 27.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.41 | 52.72 | 75.41 |  | F - Nearest node and line over 5 km | 27.25 | 27.19 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 705
1 | 706 | 706 | 0203111003 | Region II (Cagayan Valley) | Isabela | Divilacan | Dicambangan | 17.3302 | 122.2959 | R | 368 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.71 | 44.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.41 | 52.72 | 75.41 |  | F - Nearest node and line over 5 km | 40.29 | 43.93 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 706
1 | 707 | 707 | 1400113004 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Domenglay | 17.5471 | 120.8689 | R | 443 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.91 | 29.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.41 | 52.72 | 75.41 |  | F - Nearest node and line over 5 km | 24.96 | 24.89 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 707
1 | 708 | 708 | 0205706016 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Asaklat | 16.2726 | 121.6053 | R | 1262 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.38 | 4.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.4 | 52.71 | 75.4 |  | E - Nearest node or line 3-5 km | 6.38 | 4.6 | Line: NAGTIPUNAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 708
1 | 709 | 709 | 1380601100 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 100 | 14.6236 | 120.9614 | U | 2289 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.32 | 32.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.4 | 52.71 | 75.4 |  | B - Node 0.5-1 km | 0.64 | 1.16 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 709
1 | 710 | 710 | 0600609025 | Region VI (Western Visayas) | Antique | Laua-An | Magyapo | 11.0874 | 122.0864 | R | 209 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.37 | 36.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.4 | 52.71 | 75.4 |  | F - Nearest node and line over 5 km | 39.61 | 32.8 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 710
1 | 711 | 711 | 1380900001 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Sipac-Almacen | 14.6583 | 120.9483 | U | 9360 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.4 | 52.71 | 75.4 |  | A - Node within 0.5 km | 0.31 | 1.28 | Node: NAV001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 711
1 | 712 | 712 | 0600609040 | Region VI (Western Visayas) | Antique | Laua-An | Tibacan | 11.127 | 122.041 | R | 169 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.28 | 36.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.39 | 52.71 | 75.39 |  | F - Nearest node and line over 5 km | 42.09 | 35.88 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 712
1 | 713 | 713 | 0600609015 | Region VI (Western Visayas) | Antique | Laua-An | Jinalinan | 11.1592 | 122.0396 | R | 193 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.57 | 35.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.39 | 52.71 | 75.39 |  | F - Nearest node and line over 5 km | 45.51 | 39.4 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 713
1 | 714 | 714 | 1403214005 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Lower Mangali | 17.3079 | 121.2301 | R | 262 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.93 | 6.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.38 | 52.7 | 75.38 |  | F - Nearest node and line over 5 km | 9.93 | 6.83 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 714
1 | 715 | 715 | 1380601034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 34 | 14.6011 | 120.9632 | U | 1910 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.27 | 21.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.38 | 52.7 | 75.38 |  | B - Node 0.5-1 km | 0.82 | 0.93 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 715
1 | 716 | 716 | PH0000716 | VIII | Samar (Western Samar) | Catbalogan City | Libas | 11.8457 | 124.9043 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.63 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.38 | 52.7 | 75.38 |  | F - Nearest node and line over 5 km | 65.07 | 65 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 716
1 | 717 | 717 | 1380601106 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 106 | 14.6241 | 120.9611 | U | 2589 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.02 | 45.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.37 | 52.69 | 75.37 |  | B - Node 0.5-1 km | 0.7 | 1.21 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 717
1 | 718 | 718 | 1380601073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 73 | 14.6109 | 120.9635 | U | 2553 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.82 | 22.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.37 | 52.69 | 75.37 |  | B - Node 0.5-1 km | 0.79 | 0.61 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 718
1 | 719 | 719 | 1381701005 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | San Pedro | 14.5468 | 121.0674 | U | 2289 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.26 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.37 | 52.69 | 75.37 |  | A - Node within 0.5 km | 0.26 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 719
1 | 720 | 720 | PH0000720 | VIII | Leyte | Tacloban City | Barangay 17 | 11.245 | 125.0045 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.37 | 7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.37 | 52.69 | 75.37 |  | B - Node 0.5-1 km | 0.64 | 3.65 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 720
1 | 721 | 721 | 1400115002 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Binasaran | 17.5937 | 120.9637 | R | 174 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.39 | 32.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.35 | 52.68 | 75.35 |  | F - Nearest node and line over 5 km | 32.39 | 32.34 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 721
1 | 722 | 722 | 1102503001 | Region XI (Davao Region) | Davao Oriental | Boston | Cabasagan | 7.8112 | 126.3519 | R | 1983 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.62 | 31.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.33 | 52.67 | 75.33 |  | F - Nearest node and line over 5 km | 32.62 | 31.05 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 722
1 | 723 | 723 | 0201528010 | Region II (Cagayan Valley) | Cagayan | Tuao | Bulagao | 17.6868 | 121.491 | R | 3867 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.85 | 5.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.33 | 52.66 | 75.33 |  | D - Other node or line within 3 km | 2.85 | 5.49 | Node: TUC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 723
1 | 724 | 724 | 1400115010 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Pacgued | 17.6258 | 121.0432 | R | 283 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.03 | 29.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.32 | 52.65 | 75.32 |  | F - Nearest node and line over 5 km | 32.45 | 30.97 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 724
1 | 725 | 725 | 1400115001 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Bayabas | 17.6392 | 120.9884 | R | 218 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.2 | 34.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.31 | 52.65 | 75.31 |  | F - Nearest node and line over 5 km | 34.2 | 34.16 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 725
1 | 726 | 726 | 0500518005 | Region V (Bicol Region) | Albay | Tiwi | Biyong | 13.4481 | 123.6496 | R | 1705 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3 | 2.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.31 | 52.65 | 75.31 |  | D - Other node or line within 3 km | 3 | 2.42 | Line: EE | Route options survey candidate: compare actual node lateral with approved line tap. | 726
1 | 727 | 727 | 1403208010 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Galdang | 17.3951 | 121.1487 | R | 380 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.6 | 3.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.31 | 52.65 | 75.31 |  | E - Nearest node or line 3-5 km | 14.6 | 3.81 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 727
1 | 728 | 728 | 0502002025 | Region V (Bicol Region) | Catanduanes | Baras | San Lorenzo | 13.6596 | 124.3696 | R | 157 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.15 | 76.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.29 | 52.63 | 75.29 |  | F - Nearest node and line over 5 km | 56.15 | 76.65 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 728
1 | 729 | 729 | PH0000729 | VIII | Leyte | Tacloban City | Barangay 21 | 11.1969 | 125.0165 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 6.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.28 | 52.63 | 75.28 |  | D - Other node or line within 3 km | 1.89 | 1.13 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 729
1 | 730 | 730 | PH0000730 | IV-B | Palawan | Puerto Princesa City | Tanglaw (Pob.) | 9.6829 | 118.7536 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.77 | 2.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.28 | 52.63 | 75.28 |  | F - Nearest node and line over 5 km | 6.78 | 7.72 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 730
1 | 731 | 731 | 0402113016 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pinagsanhan I A | 14.2766 | 120.7348 | R | 1651 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.74 | 1.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.26 | 52.62 | 75.26 |  | A - Node within 0.5 km | 0.29 | 0.26 | Line: NCC001 TO NSB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 731
1 | 732 | 732 | 0403403023 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Domingo | 14.336 | 121.0809 | U | 6751 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.26 | 52.61 | 75.26 |  | B - Node 0.5-1 km | 0.63 | 0.15 | Line: EXISTING | Short node lateral candidate; confirm port/fiber capacity, access and route. | 732
1 | 733 | 733 | PH0000733 | NIR | Negros Occidental | Bacolod City | Barangay 27 (Pob.) | 10.6724 | 122.9523 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 0.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.25 | 52.61 | 75.25 |  | B - Node 0.5-1 km | 0.62 | 0.08 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Short node lateral candidate; confirm port/fiber capacity, access and route. | 733
1 | 734 | 734 | 1403214015 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Dupligan | 17.3317 | 121.3608 | R | 1904 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.51 | 8.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.24 | 52.6 | 75.24 |  | F - Nearest node and line over 5 km | 12.51 | 8.11 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 734
1 | 735 | 735 | 0600606042 | Region VI (Western Visayas) | Antique | Culasi | Simbola | 11.4055 | 122.0525 | R | 182 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.84 | 37.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.24 | 52.6 | 75.24 |  | F - Nearest node and line over 5 km | 35.96 | 38.3 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 735
1 | 736 | 736 | PH0000736 | NIR | Negros Occidental | Bacolod City | Barangay 33 (Pob.) | 10.6401 | 122.9679 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.74 | 0.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.24 | 52.6 | 75.24 |  | B - Node 0.5-1 km | 0.98 | 0.74 | Line: TALISAY - BACOLOD (REDUNDANCY) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 736
1 | 737 | 737 | 0402118055 | Region IV-A (CALABARZON) | Cavite | Silang | Banaba | 14.1991 | 121.0021 | U | 6648 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.57 | 1.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.23 | 52.6 | 75.23 |  | D - Other node or line within 3 km | 1.7 | 1.8 | Node: SGC004 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 737
1 | 738 | 738 | 1380900007 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Navotas West | 14.6632 | 120.9527 | U | 6504 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.73 | 1.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.23 | 52.59 | 75.23 |  | B - Node 0.5-1 km | 0.56 | 0.86 | Node: MAL004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 738
1 | 739 | 739 | 0806022048 | Region VIII (Eastern Visayas) | Samar | Paranas | Casandig II | 11.7708 | 125.0636 | R | 1293 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.47 | 67.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.23 | 52.59 | 75.23 |  | F - Nearest node and line over 5 km | 59.44 | 62.36 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 739
1 | 740 | 740 | PH0000740 | VI | Iloilo | Iloilo City | Benedicto | 10.6893 | 122.5785 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 2.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.22 | 52.59 | 75.22 |  | D - Other node or line within 3 km | 2.96 | 1.65 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 740
1 | 741 | 741 | PH0000741 | NCR | Metro Manila | Caloocan City | Barangay 123 | 14.6111 | 120.9621 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.62 | 73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.22 | 52.59 | 75.22 |  | B - Node 0.5-1 km | 0.77 | 0.76 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 741
1 | 742 | 742 | PH0000742 | IV-A | Laguna | San Pablo City | Barangay II-C (Pob.) | 14.0976 | 121.3317 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 1.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.2 | 52.58 | 75.2 |  | D - Other node or line within 3 km | 2.47 | 1.78 | Line: SPO001 TO LBQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 742
1 | 743 | 743 | 1108602001 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Buguis | 5.5709 | 125.4073 | R | 1415 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.31 | 55.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.18 | 52.56 | 75.18 |  | F - Nearest node and line over 5 km | 61.09 | 65.63 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 743
1 | 744 | 744 | PH0000744 | IV-A | Cavite | Imus City | Palico II | 14.4067 | 120.927 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.18 | 52.56 | 75.18 |  | D - Other node or line within 3 km | 1.47 | 4.05 | Node: IMC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 744
1 | 745 | 745 | 1102505001 | Region XI (Davao Region) | Davao Oriental | Cateel | Abijod | 7.7822 | 126.4154 | R | 2136 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.89 | 38.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.17 | 52.55 | 75.17 |  | F - Nearest node and line over 5 km | 39.89 | 38.54 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 745
1 | 746 | 746 | 1102501014 | Region XI (Davao Region) | Davao Oriental | Baganga | Salingcomot | 7.6334 | 126.5365 | R | 3085 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.15 | 56.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.16 | 52.55 | 75.16 |  | F - Nearest node and line over 5 km | 57.15 | 56.76 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 746
1 | 747 | 747 | 0806022015 | Region VIII (Eastern Visayas) | Samar | Paranas | Lawaan I | 11.7704 | 125.0624 | R | 1494 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.14 | 73.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.16 | 52.54 | 75.16 |  | F - Nearest node and line over 5 km | 59.39 | 62.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 747
1 | 748 | 748 | PH0000748 | VI | Capiz | Roxas City | Poblacion IX | 11.5851 | 122.7733 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.95 | 0.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.15 | 52.54 | 75.15 |  | C - Line within 0.5 km; node over 1 km | 2.75 | 0.02 | Line: ROXAS - SARA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 748
1 | 749 | 749 | PH0000749 | NIR | Negros Occidental | Bacolod City | Barangay 20 (Pob.) | 10.6307 | 122.9742 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.6 | 2.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.15 | 52.54 | 75.15 |  | A - Node within 0.5 km | 0.29 | 0.06 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 749
1 | 750 | 750 | 1400115004 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Dulao | 17.6131 | 121.0256 | R | 248 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.97 | 31.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.15 | 52.54 | 75.15 |  | F - Nearest node and line over 5 km | 33.97 | 30.95 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 750
1 | 751 | 751 | 1408102009 | Cordillera Administrative Region (CAR) | Apayao | Conner | Katablangan | 17.818 | 121.1761 | R | 662 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.85 | 8.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.13 | 52.53 | 75.13 |  | F - Nearest node and line over 5 km | 15.85 | 15.38 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 751
1 | 752 | 752 | PH0000752 | VI | Iloilo | Iloilo City | Gustilo | 10.7485 | 122.5683 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.33 | 8.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.12 | 52.52 | 75.12 |  | A - Node within 0.5 km | 0.38 | 0.04 | Line: 3,477 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 752
1 | 753 | 753 | PH0000753 | VIII | Leyte | Tacloban City | Barangay 23 | 11.2437 | 124.999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 3.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.12 | 52.52 | 75.12 |  | B - Node 0.5-1 km | 0.59 | 3.64 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 753
1 | 754 | 754 | 1400115003 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Buanao | 17.5843 | 121.0678 | R | 339 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.14 | 30.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.11 | 52.51 | 75.11 |  | F - Nearest node and line over 5 km | 29.09 | 25.69 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 754
1 | 755 | 755 | 0803722005 | Region VIII (Eastern Visayas) | Leyte | Isabel | Benog | 10.8852 | 124.4724 | R | 627 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.81 | 0.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.06 | 52.48 | 75.06 |  | C - Line within 0.5 km; node over 1 km | 5.81 | 0.48 | Line: ORMOC - PALOMPON | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 755
1 | 756 | 756 | 0806022049 | Region VIII (Eastern Visayas) | Samar | Paranas | Lawaan II | 11.75 | 125.0579 | R | 368 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.81 | 67.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.06 | 52.48 | 75.06 |  | F - Nearest node and line over 5 km | 57.07 | 59.99 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 756
1 | 757 | 757 | 1380601125 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 125 | 14.6123 | 120.9624 | U | 4647 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.16 | 31.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.04 | 52.46 | 75.04 |  | B - Node 0.5-1 km | 0.64 | 0.75 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 757
1 | 758 | 758 | 1381600026 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pulo | 14.6824 | 120.9821 | U | 1142 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.43 | 0.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.04 | 52.46 | 75.04 |  | B - Node 0.5-1 km | 0.62 | 0.34 | Line: EXISTING 216 C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 758
1 | 759 | 759 | 1003505026 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Kidalos | 7.8493 | 123.7747 | R | 1174 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.7 | 4.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.03 | 52.46 | 75.03 |  | E - Nearest node or line 3-5 km | 21.7 | 4.66 | Line: ILIGAN - PAGADIAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 759
1 | 760 | 760 | 1380601043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 43 | 14.6192 | 120.9725 | U | 3464 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.83 | 39.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75.02 | 52.44 | 75.02 |  | B - Node 0.5-1 km | 0.86 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 760
1 | 761 | 761 | 1906613028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Liu-Bud Pantao | 17.2555 | 122.2295 | R | 1364 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 75 | 52.43 | 75 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 761
1 | 762 | 762 | PH0000762 | VIII | Leyte | Tacloban City | Barangay 20 | 11.3163 | 124.9554 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 5.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.98 | 52.42 | 74.98 |  | F - Nearest node and line over 5 km | 9.95 | 12.95 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 762
1 | 763 | 763 | 1380604019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 286 | 14.5961 | 120.973 | U | 4853 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.88 | 19.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.98 | 52.42 | 74.98 |  | D - Other node or line within 3 km | 1.24 | 0.87 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 763
1 | 764 | 764 | PH0000764 | IV-A | Laguna | San Pablo City | Barangay II-D (Pob.) | 14.122 | 121.3418 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.98 | 52.42 | 74.98 |  | E - Nearest node or line 3-5 km | 4.03 | 3.04 | Line: SPO001 TO LBQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 764
1 | 765 | 765 | 1380601104 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 104 | 14.6226 | 120.959 | U | 5915 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.44 | 42.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.97 | 52.41 | 74.97 |  | B - Node 0.5-1 km | 0.65 | 1.35 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 765
1 | 766 | 766 | 1907010023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tup-tup Banaran | 17.255 | 122.2292 | R | 1649 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.42 | 5.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.95 | 52.4 | 74.95 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 766
1 | 767 | 767 | 1408102008 | Cordillera Administrative Region (CAR) | Apayao | Conner | Karikitan | 17.7478 | 121.3646 | R | 1935 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.94 | 0.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.94 | 52.39 | 74.94 |  | C - Line within 0.5 km; node over 1 km | 6.94 | 0.04 | Line: Tabuk-Conner | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 767
1 | 768 | 768 | PH0000768 | III | Nueva Ecija | Cabanatuan City | Sangitan | 15.4903 | 120.9704 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.37 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.93 | 52.38 | 74.93 |  | D - Other node or line within 3 km | 1.37 | 0.51 | Line: MULTINET - SANTA ROSA | Route options survey candidate: compare actual node lateral with approved line tap. | 768
1 | 769 | 769 | PH0000769 | III | Nueva Ecija | Cabanatuan City | Sanbermicristi (Pob.) | 15.5046 | 121.0791 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.91 | 0.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.92 | 52.38 | 74.92 |  | D - Other node or line within 3 km | 6.29 | 1.76 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 769
1 | 770 | 770 | 0806418026 | Region VIII (Eastern Visayas) | Southern Leyte | Tomas Oppus | San Roque | 10.2543 | 124.986 | R | 347 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.78 | 1.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.91 | 52.37 | 74.91 |  | F - Nearest node and line over 5 km | 21.83 | 18.13 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 770
1 | 771 | 771 | 0806010019 | Region VIII (Eastern Visayas) | Samar | Marabut | Malobago | 11.1156 | 125.2443 | R | 527 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.51 | 23.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.9 | 52.36 | 74.9 |  | F - Nearest node and line over 5 km | 24.51 | 27.3 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 771
1 | 772 | 772 | PH0000772 | VIII | Leyte | Tacloban City | Barangay 23-A | 11.2007 | 125.0208 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.88 | 7.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.89 | 52.36 | 74.89 |  | D - Other node or line within 3 km | 1.81 | 1.47 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 772
1 | 773 | 773 | PH0000773 | VIII | Leyte | Tacloban City | Barangay 14 | 11.2294 | 124.9922 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.64 | 5.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.88 | 52.35 | 74.88 |  | D - Other node or line within 3 km | 1.59 | 2.64 | Node: TCL002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 773
1 | 774 | 774 | PH0000774 | VI | Iloilo | Iloilo City | Habog-habog Salvacion | 10.6996 | 122.5487 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.53 | 1.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.88 | 52.35 | 74.88 |  | D - Other node or line within 3 km | 1.19 | 2.15 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 774
1 | 775 | 775 | PH0000775 | VI | Iloilo | Iloilo City | Bantud | 10.6966 | 122.5848 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 2.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.86 | 52.33 | 74.86 |  | D - Other node or line within 3 km | 2.65 | 1.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 775
1 | 776 | 776 | 1004312008 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Kagumahan | 8.9425 | 124.8218 | R | 250 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.51 | 1.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.85 | 52.33 | 74.85 |  | E - Nearest node or line 3-5 km | 3.97 | 3.63 | Line: CDO - BUENAVISTA via GINGOOG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 776
1 | 777 | 777 | 1380601102 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 102 | 14.6245 | 120.9635 | U | 4283 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.65 | 27.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.85 | 52.33 | 74.85 |  | B - Node 0.5-1 km | 0.73 | 0.98 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 777
1 | 778 | 778 | 1380601103 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 103 | 14.6238 | 120.9611 | U | 4917 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.38 | 23.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.84 | 52.32 | 74.84 |  | B - Node 0.5-1 km | 0.67 | 1.2 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 778
1 | 779 | 779 | 1381701004 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Poblacion | 14.5416 | 121.071 | U | 2064 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.43 | 0.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.82 | 52.31 | 74.82 |  | A - Node within 0.5 km | 0.44 | 0.4 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 779
1 | 780 | 780 | 1380400018 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tañong | 14.6535 | 120.9529 | U | 14818 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.79 | 52.29 | 74.79 |  | B - Node 0.5-1 km | 0.74 | 1.91 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 780
1 | 781 | 781 | 1380601011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 11 | 14.6071 | 120.966 | U | 2842 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.94 | 46.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.78 | 52.28 | 74.78 |  | A - Node within 0.5 km | 0.39 | 0.35 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 781
1 | 782 | 782 | PH0000782 | X | Misamis Oriental | Cagayan De Oro City | Carmen | 8.4683 | 124.6314 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 1.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.78 | 52.28 | 74.78 |  | B - Node 0.5-1 km | 1 | 1.4 | Node: COM005 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 782
1 | 783 | 783 | PH0000783 | VI | Iloilo | Iloilo City | Fajardo | 10.7035 | 122.5441 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.82 | 10.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.77 | 52.27 | 74.77 |  | D - Other node or line within 3 km | 1.43 | 2.44 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 783
1 | 784 | 784 | 0102901011 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Dalawa | 16.9164 | 120.5199 | R | 1448 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.65 | 6.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.75 | 52.26 | 74.75 |  | F - Nearest node and line over 5 km | 6.65 | 5.92 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 784
1 | 785 | 785 | 0501609006 | Region V (Bicol Region) | Camarines Norte | San Vicente | Man-Ogob | 14.1014 | 122.8721 | R | 3172 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.98 | 4.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.75 | 52.26 | 74.75 |  | E - Nearest node or line 3-5 km | 6.98 | 4.31 | Line: PAGBILAO - NAGA (UG + Aerial) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 785
1 | 786 | 786 | 1705303004 | MIMAROPA Region | Palawan | Araceli | Dagman | 10.5255 | 119.9617 | R | 934 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.06 | 54.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.75 | 52.26 | 74.75 |  | F - Nearest node and line over 5 km | 46.06 | 54.87 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 786
1 | 787 | 787 | 1908816005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Galakit | 7.0696 | 124.7099 | R | 2798 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.63 | 11.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.74 | 52.25 | 74.74 |  | F - Nearest node and line over 5 km | 17.63 | 11.72 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 787
1 | 788 | 788 | 1380601108 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 108 | 14.617 | 120.9595 | U | 5555 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.81 | 19.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.74 | 52.25 | 74.74 |  | A - Node within 0.5 km | 0.36 | 1.16 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 788
1 | 789 | 789 | 1102501006 | Region XI (Davao Region) | Davao Oriental | Baganga | Bobonao | 7.4818 | 126.578 | R | 942 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.17 | 68.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.73 | 52.24 | 74.73 |  | F - Nearest node and line over 5 km | 69.17 | 68.18 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 789
1 | 790 | 790 | PH0000790 | NCR | Metro Manila | Caloocan City | Barangay 106 | 14.6241 | 120.9611 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.79 | 0.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.73 | 52.24 | 74.73 |  | B - Node 0.5-1 km | 0.7 | 1.21 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 790
1 | 791 | 791 | 0205702014 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Dingasan | 16.3413 | 121.5177 | R | 1393 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.54 | 14.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.72 | 52.24 | 74.72 |  | F - Nearest node and line over 5 km | 16.54 | 14.91 | Line: SEGMENT 48 (MADDELA - DIPACULAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 791
1 | 792 | 792 | 0806411009 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Dan-an | 9.9885 | 125.2097 | R | 494 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.72 | 21.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.72 | 52.24 | 74.72 |  | F - Nearest node and line over 5 km | 38.37 | 36.78 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 792
1 | 793 | 793 | 1903639014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Tabuan | 17.2546 | 122.2286 | R | 984 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.72 | 52.24 | 74.72 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 793
1 | 794 | 794 | PH0000794 | VIII | Leyte | Tacloban City | Barangay 27 | 11.2169 | 125.0033 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.54 | 6.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.71 | 52.23 | 74.71 |  | B - Node 0.5-1 km | 0.83 | 0.81 | Line: CAPOOCAN - TACLOBAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 794
1 | 795 | 795 | 0102931007 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Pangotan | 16.8593 | 120.5186 | R | 381 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.66 | 7.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.7 | 52.22 | 74.7 |  | F - Nearest node and line over 5 km | 10.66 | 7.82 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 795
1 | 796 | 796 | 1907004003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Mongkay | 4.9239 | 119.8057 | R | 2260 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.7 | 52.22 | 74.7 |  | F - Nearest node and line over 5 km | 334.23 | 334.23 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 796
1 | 797 | 797 | 0405802017 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Santa Cruz | 14.6153 | 121.1708 | U | 62537 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.69 | 52.21 | 74.69 |  | B - Node 0.5-1 km | 0.63 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 797
1 | 798 | 798 | 0806411014 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Nueva Estrella Sur | 9.949 | 125.2683 | R | 420 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.07 | 25.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.68 | 52.21 | 74.68 |  | F - Nearest node and line over 5 km | 30.59 | 30.16 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 798
1 | 799 | 799 | PH0000799 | III | Nueva Ecija | Cabanatuan City | Mabini Extension | 15.4857 | 120.9742 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.47 | 0.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.67 | 52.2 | 74.67 |  | C - Line within 0.5 km; node over 1 km | 1.47 | 0.12 | Line: MULTINET - SANTA ROSA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 799
1 | 800 | 800 | 0803726022 | Region VIII (Eastern Visayas) | Leyte | Kananga | Tongonan | 11.1306 | 124.6411 | U | 1652 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.64 | 5.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.67 | 52.2 | 74.67 |  | F - Nearest node and line over 5 km | 7.64 | 5.89 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 800
1 | 801 | 801 | 0402118011 | Region IV-A (CALABARZON) | Cavite | Silang | Bulihan | 14.2802 | 120.9962 | U | 26302 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 3.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.67 | 52.2 | 74.67 |  | B - Node 0.5-1 km | 0.68 | 3.28 | Node: MAC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 801
1 | 802 | 802 | 1402708016 | Cordillera Administrative Region (CAR) | Ifugao | Aguinaldo | Buwag | 16.9349 | 121.3128 | R | 390 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.18 | 25.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.66 | 52.2 | 74.66 |  | F - Nearest node and line over 5 km | 5.18 | 25.16 | Node: AOF001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 802
1 | 803 | 803 | 1408101003 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Langnao | 18.2487 | 120.9952 | R | 234 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.46 | 22.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.66 | 52.2 | 74.66 |  | F - Nearest node and line over 5 km | 28.86 | 28.85 | Line: SEGMENT 2 SOLSONA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 803
1 | 804 | 804 | PH0000804 | IV-A | Laguna | San Pablo City | Barangay III-A (Pob.) | 17.4938 | 121.8324 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.48 | 1.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.66 | 52.19 | 74.66 |  | D - Other node or line within 3 km | 8.33 | 2.88 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Route options survey candidate: compare actual node lateral with approved line tap. | 804
1 | 805 | 805 | 1907005022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | North Larap | 17.2561 | 122.229 | R | 3176 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.61 | 20.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.65 | 52.19 | 74.65 |  | F - Nearest node and line over 5 km | 29.51 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 805
1 | 806 | 806 | 1380900003 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bagumbayan South | 14.6512 | 120.9486 | U | 4424 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.64 | 52.18 | 74.64 |  | B - Node 0.5-1 km | 0.58 | 2.06 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 806
1 | 807 | 807 | 1408101002 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Cadaclan | 18.1301 | 121.0736 | R | 957 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.57 | 13.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.64 | 52.18 | 74.64 |  | F - Nearest node and line over 5 km | 16.75 | 32.13 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 807
1 | 808 | 808 | 1380900010 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Jose | 14.6625 | 120.9438 | U | 24466 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.64 | 52.18 | 74.64 |  | B - Node 0.5-1 km | 0.78 | 0.86 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 808
1 | 809 | 809 | 1907005023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Panglima Alari | 17.2558 | 122.2299 | U | 9227 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.61 | 52.16 | 74.61 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 809
1 | 810 | 810 | 1380601014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 14 | 14.6018 | 120.9633 | U | 2133 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.03 | 36.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.61 | 52.16 | 74.61 |  | B - Node 0.5-1 km | 0.88 | 0.87 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 810
1 | 811 | 811 | PH0000811 | IV-A | Laguna | San Pablo City | Barangay VII-B (Pob.) | 14.0005 | 121.3092 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.61 | 52.16 | 74.61 |  | D - Other node or line within 3 km | 2.47 | 2.63 | Node: SPO003 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 811
1 | 812 | 812 | PH0000812 | VIII | Leyte | Tacloban City | Barangay 24 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.56 | 7.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.58 | 52.14 | 74.58 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 812
1 | 813 | 813 | 0806016037 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Napuro II | 12.0352 | 124.6678 | R | 1112 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.49 | 83.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.57 | 52.14 | 74.57 |  | F - Nearest node and line over 5 km | 81.81 | 81.3 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 813
1 | 814 | 814 | 0405632001 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Amaga | 14.828 | 122.1423 | R | 555 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.89 | 75.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.56 | 52.13 | 74.56 |  | F - Nearest node and line over 5 km | 51.89 | 75.35 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 814
1 | 815 | 815 | 0802615015 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 3 | 11.5318 | 125.4741 | R | 988 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.12 | 55.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.56 | 52.13 | 74.56 |  | F - Nearest node and line over 5 km | 60.82 | 61.87 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 815
1 | 816 | 816 | PH0000816 | VIII | Leyte | Tacloban City | Barangay 21-A | 11.2463 | 125.0046 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 4.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.53 | 52.1 | 74.53 |  | B - Node 0.5-1 km | 0.78 | 3.79 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 816
1 | 817 | 817 | 0806411023 | Region VIII (Eastern Visayas) | Southern Leyte | Pintuyan | Pociano D. Equipilag | 9.9407 | 125.2499 | R | 400 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.75 | 27.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.53 | 52.1 | 74.53 |  | F - Nearest node and line over 5 km | 31.75 | 31.21 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 817
1 | 818 | 818 | 1003506013 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Ditago | 7.7732 | 123.7328 | R | 955 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.13 | 11.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.51 | 52.09 | 74.51 |  | F - Nearest node and line over 5 km | 25.66 | 12.61 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 818
1 | 819 | 819 | 1907005025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Sipangkot | 16.09 | 120.39 | U | 7560 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.5 | 52.08 | 74.5 |  | C - Line within 0.5 km; node over 1 km | 2.8 | 0.18 | Line: MANGALDAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 819
1 | 820 | 820 | PH0000820 | VIII | Leyte | Tacloban City | Barangay 31 | 11.2715 | 124.9509 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.63 | 8.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.49 | 52.08 | 74.49 |  | F - Nearest node and line over 5 km | 6.65 | 9.14 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 820
1 | 821 | 821 | 0806008001 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Bagacay | 11.8177 | 125.232 | R | 1374 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.97 | 71.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.48 | 52.07 | 74.48 |  | F - Nearest node and line over 5 km | 68.97 | 71.53 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 821
1 | 822 | 822 | 1380601116 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 116 | 14.6091 | 120.9627 | U | 6123 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.91 | 34.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.47 | 52.07 | 74.47 |  | B - Node 0.5-1 km | 0.79 | 0.68 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 822
1 | 823 | 823 | 1907005021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Imam Sapie | 17.2558 | 122.2299 | R | 5021 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.46 | 52.06 | 74.46 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 823
1 | 824 | 824 | 1907007050 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Tandubato | 17.2559 | 122.2299 | R | 1801 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.46 | 52.05 | 74.46 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 824
1 | 825 | 825 | 1907007002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Baliungan | 17.2566 | 122.23 | R | 1925 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.89 | 33.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.46 | 52.05 | 74.46 |  | F - Nearest node and line over 5 km | 29.63 | 34.46 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 825
1 | 826 | 826 | PH0000826 | III | Nueva Ecija | Cabanatuan City | San Roque Norte | 15.5093 | 120.9651 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 1.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.45 | 52.05 | 74.45 |  | C - Line within 0.5 km; node over 1 km | 3.09 | 0.23 | Line: TALAVERA - MULTI NET | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 826
1 | 827 | 827 | 1907007026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Naungan | 5.2461 | 120.355 | R | 1415 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 265.25 | 265.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.45 | 52.05 | 74.45 |  | F - Nearest node and line over 5 km | 265.25 | 265.25 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 827
1 | 828 | 828 | 1907005004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Sitangkai Poblacion | 17.2558 | 122.2299 | R | 4093 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.45 | 52.05 | 74.45 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 828
1 | 829 | 829 | 1907007048 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Salamat | 5.123 | 120.3288 | R | 965 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.73 | 32.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.44 | 52.04 | 74.44 |  | F - Nearest node and line over 5 km | 277.01 | 277 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 829
1 | 830 | 830 | 1907007012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Tandubas | Lahay-lahay | 17.2564 | 122.2294 | R | 979 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.69 | 33.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.44 | 52.04 | 74.44 |  | F - Nearest node and line over 5 km | 29.56 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 830
1 | 831 | 831 | 1907002005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Ipil | 17.2552 | 122.2301 | R | 1713 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.6 | 24.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.42 | 52.03 | 74.42 |  | F - Nearest node and line over 5 km | 29.54 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 831
1 | 832 | 832 | 0102908017 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Malaya | 16.9742 | 120.6997 | R | 1893 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.18 | 3.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.42 | 52.03 | 74.42 |  | E - Nearest node or line 3-5 km | 3.18 | 3.51 | Node: CVI001 - TYPE 2 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 832
1 | 833 | 833 | 1380400008 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Hulong Duhat | 14.6768 | 120.9412 | U | 12186 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.14 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.42 | 52.03 | 74.42 |  | A - Node within 0.5 km | 0.14 | 0.12 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 833
1 | 834 | 834 | 1108204029 | Region XI (Davao Region) | Davao de Oro | Maco | Sangab | 7.4442 | 125.9221 | R | 595 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.42 | 5.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.41 | 52.02 | 74.41 |  | F - Nearest node and line over 5 km | 11.42 | 5.87 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 834
1 | 835 | 835 | 1108602023 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Meybio | 5.9511 | 125.6341 | R | 2462 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.37 | 53.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.41 | 52.02 | 74.41 |  | F - Nearest node and line over 5 km | 42.94 | 51.78 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 835
1 | 836 | 836 | 0702252012 | Region VII (Central Visayas) | Cebu | Tuburan | Kan-an | 10.5962 | 123.8821 | R | 250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.13 | 11.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.41 | 52.02 | 74.41 |  | F - Nearest node and line over 5 km | 15.13 | 11.83 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 836
1 | 837 | 837 | 0102931002 | Region I (Ilocos Region) | Ilocos Sur | Sugpon | Caoayan | 16.8067 | 120.5418 | R | 748 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.68 | 13.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.4 | 52.01 | 74.4 |  | F - Nearest node and line over 5 km | 14.68 | 13.27 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 837
1 | 838 | 838 | 1380601046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 46 | 14.6156 | 120.9708 | U | 2151 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.29 | 18.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.38 | 52 | 74.38 |  | B - Node 0.5-1 km | 0.91 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 838
1 | 839 | 839 | 0402123004 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 3 Poblacion | 14.2993 | 121.0082 | R | 2589 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.62 | 3.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.36 | 51.99 | 74.36 |  | D - Other node or line within 3 km | 1.99 | 4.68 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 839
1 | 840 | 840 | 0601912009 | Region VI (Western Visayas) | Capiz | Pontevedra | Gabuc | 11.4534 | 122.8835 | R | 646 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.05 | 4.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.35 | 51.98 | 74.35 |  | E - Nearest node or line 3-5 km | 6.05 | 4.02 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 840
1 | 841 | 841 | 1108602021 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Mangile | 5.6941 | 125.4801 | R | 3502 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.74 | 53.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.34 | 51.97 | 74.34 |  | F - Nearest node and line over 5 km | 50.87 | 57.29 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 841
1 | 842 | 842 | 0103304004 | Region I (Ilocos Region) | La Union | Bagulin | Cardiz | 16.6233 | 120.4861 | R | 1434 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.41 | 11.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.34 | 51.97 | 74.34 |  | F - Nearest node and line over 5 km | 11.41 | 12.82 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 842
1 | 843 | 843 | 1380601033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 33 | 14.6023 | 120.9606 | U | 4206 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.04 | 46.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.34 | 51.97 | 74.34 |  | B - Node 0.5-1 km | 0.94 | 1.1 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 843
1 | 844 | 844 | PH0000844 | VI | Iloilo | Iloilo City | Democracia | 10.6928 | 122.5754 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.15 | 1.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.34 | 51.97 | 74.34 |  | D - Other node or line within 3 km | 2.47 | 1.14 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 844
1 | 845 | 845 | 1380601095 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 95 | 14.62 | 120.964 | U | 5711 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.89 | 23.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.33 | 51.97 | 74.33 |  | A - Node within 0.5 km | 0.26 | 0.75 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 845
1 | 846 | 846 | 0102930024 | Region I (Ilocos Region) | Ilocos Sur | Sinait | Nagcullooban | 17.8643 | 120.4583 | R | 446 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 1.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.32 | 51.96 | 74.32 |  | A - Node within 0.5 km | 0.37 | 0.16 | Line: SEGMENT 3 (VIGAN - BATAC) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 846
1 | 847 | 847 | 0405607068 | Region IV-A (CALABARZON) | Quezon | Calauag | Salvacion | 13.9289 | 122.378 | R | 255 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.21 | 5.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.31 | 51.95 | 74.31 |  | F - Nearest node and line over 5 km | 5.86 | 6.02 | Node: GYQ003 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 847
1 | 848 | 848 | 1003506030 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Rebucon | 7.8129 | 123.696 | R | 1592 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.1 | 11.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.27 | 51.92 | 74.27 |  | F - Nearest node and line over 5 km | 19.68 | 9.54 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 848
1 | 849 | 849 | 0702252013 | Region VII (Central Visayas) | Cebu | Tuburan | Kanlunsing | 10.6189 | 123.8922 | R | 201 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.64 | 11.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.27 | 51.92 | 74.27 |  | F - Nearest node and line over 5 km | 14.64 | 11.35 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 849
1 | 850 | 850 | 0802615014 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 2 | 11.4988 | 125.5026 | R | 552 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.67 | 61.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.24 | 51.9 | 74.24 |  | F - Nearest node and line over 5 km | 61.67 | 62.49 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 850
1 | 851 | 851 | 0506209009 | Region V (Bicol Region) | Sorsogon | Irosin | Cawayan | 12.6943 | 124.0863 | R | 474 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.57 | 3.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.24 | 51.9 | 74.24 |  | E - Nearest node or line 3-5 km | 5.57 | 4.94 | Line: STA MAGDALENA CLS | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 851
1 | 852 | 852 | PH0000852 | VI | Iloilo | Iloilo City | Rima-Rizal | 10.7679 | 122.5833 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.04 | 6.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.23 | 51.9 | 74.23 |  | C - Line within 0.5 km; node over 1 km | 2.11 | 0.14 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 852
1 | 853 | 853 | 1102509012 | Region XI (Davao Region) | Davao Oriental | City of Mati | Don Salvador Lopez, Sr. | 7.0774 | 126.2578 | R | 4799 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.14 | 14.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.23 | 51.9 | 74.23 |  | F - Nearest node and line over 5 km | 14.14 | 14.05 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 853
1 | 854 | 854 | 1380606010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 404 | 14.6068 | 120.9901 | U | 745 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.46 | 27.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.23 | 51.89 | 74.23 |  | A - Node within 0.5 km | 0.42 | 0.11 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 854
1 | 855 | 855 | 0806022001 | Region VIII (Eastern Visayas) | Samar | Paranas | Anagasi | 11.8119 | 125.1541 | R | 206 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.86 | 82.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.23 | 51.89 | 74.23 |  | F - Nearest node and line over 5 km | 65.75 | 68.49 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 855
1 | 856 | 856 | 0802607007 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Magsaysay | 11.2825 | 125.4403 | R | 146 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.63 | 46.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.21 | 51.88 | 74.21 |  | F - Nearest node and line over 5 km | 47.63 | 47.64 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 856
1 | 857 | 857 | 0702252002 | Region VII (Central Visayas) | Cebu | Tuburan | Amatugan | 10.6758 | 123.8876 | R | 953 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.96 | 8.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.21 | 51.88 | 74.21 |  | F - Nearest node and line over 5 km | 13.96 | 8.53 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 857
1 | 858 | 858 | 1381200024 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Cruz | 14.563 | 121.0791 | U | 5958 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.33 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.2 | 51.88 | 74.2 |  | A - Node within 0.5 km | 0.33 | 0.27 | Line: Aerial 216C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 858
1 | 859 | 859 | 1380601036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 36 | 14.6033 | 120.9636 | U | 2299 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.55 | 42.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.19 | 51.86 | 74.19 |  | B - Node 0.5-1 km | 0.76 | 0.76 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 859
1 | 860 | 860 | 1380601015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 15 | 14.6006 | 120.9612 | U | 1153 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.39 | 17.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.18 | 51.86 | 74.18 |  | B - Node 0.5-1 km | 0.75 | 1.13 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 860
1 | 861 | 861 | PH0000861 | VI | Iloilo | Iloilo City | West Habog-habog | 10.7101 | 122.5719 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.22 | 4.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.17 | 51.85 | 74.17 |  | B - Node 0.5-1 km | 0.6 | 0.52 | Line: 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 861
1 | 862 | 862 | 0806022046 | Region VIII (Eastern Visayas) | Samar | Paranas | Tula | 11.8059 | 125.1289 | R | 419 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.58 | 79.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.16 | 51.84 | 74.16 |  | F - Nearest node and line over 5 km | 64.46 | 67.25 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 862
1 | 863 | 863 | 1380601111 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 111 | 14.6181 | 120.9625 | U | 2742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.55 | 41.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.15 | 51.84 | 74.15 |  | A - Node within 0.5 km | 0.02 | 0.86 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 863
1 | 864 | 864 | 1380604009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 276 | 14.5991 | 120.9721 | U | 2620 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 28.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.15 | 51.84 | 74.15 |  | B - Node 0.5-1 km | 0.89 | 0.78 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 864
1 | 865 | 865 | 1102509013 | Region XI (Davao Region) | Davao Oriental | City of Mati | Langka | 6.3561 | 126.1989 | R | 1281 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.51 | 58.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.14 | 51.83 | 74.14 |  | F - Nearest node and line over 5 km | 63.51 | 58.89 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 865
1 | 866 | 866 | 0501606002 | Region V (Bicol Region) | Camarines Norte | Labo | Awitan | 14.12 | 122.7152 | R | 720 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.3 | 5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.14 | 51.83 | 74.14 |  | F - Nearest node and line over 5 km | 10.09 | 8.2 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 866
1 | 867 | 867 | 1381100093 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 93 | 14.5461 | 120.9966 | U | 393 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 0.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.14 | 51.83 | 74.14 |  | A - Node within 0.5 km | 0.29 | 0.25 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 867
1 | 868 | 868 | 1108204035 | Region XI (Davao Region) | Davao de Oro | Maco | Panangan | 7.4113 | 125.9486 | R | 724 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.88 | 10.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.12 | 51.82 | 74.12 |  | F - Nearest node and line over 5 km | 11.88 | 10.3 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 868
1 | 869 | 869 | 1380601109 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 109 | 14.6205 | 120.9621 | U | 3353 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.28 | 19.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.12 | 51.82 | 74.12 |  | A - Node within 0.5 km | 0.29 | 0.96 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 869
1 | 870 | 870 | 0806022040 | Region VIII (Eastern Visayas) | Samar | Paranas | Santo Niño | 11.9017 | 125.0796 | R | 206 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.13 | 80.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.1 | 51.8 | 74.1 |  | F - Nearest node and line over 5 km | 74.1 | 77.01 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 870
1 | 871 | 871 | 1381400004 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Corazon De Jesus | 14.6059 | 121.0292 | U | 8371 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.92 | 0.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.09 | 51.8 | 74.09 |  | C - Line within 0.5 km; node over 1 km | 1.92 | 0.1 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 871
1 | 872 | 872 | 1108602033 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Sugal | 6.003 | 125.6858 | R | 3173 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.46 | 54.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.09 | 51.8 | 74.09 |  | F - Nearest node and line over 5 km | 46.5 | 53.93 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 872
1 | 873 | 873 | 1108202011 | Region XI (Davao Region) | Davao de Oro | Laak | Langtud | 7.9786 | 125.8519 | R | 3066 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.58 | 18.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.08 | 51.79 | 74.08 |  | F - Nearest node and line over 5 km | 24.4 | 22.91 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 873
1 | 874 | 874 | 0501711012 | Region V (Bicol Region) | Camarines Sur | Caramoan | Gogon | 13.9445 | 123.8292 | R | 1595 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.29 | 46.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.07 | 51.78 | 74.07 |  | F - Nearest node and line over 5 km | 19.29 | 45.98 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 874
1 | 875 | 875 | 1380601124 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 124 | 14.6088 | 120.9599 | U | 164 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.1 | 19.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.06 | 51.78 | 74.06 |  | D - Other node or line within 3 km | 1.06 | 0.99 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 875
1 | 876 | 876 | 0201526028 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Santa Felicitas | 17.9067 | 121.5825 | R | 410 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.91 | 6.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.06 | 51.78 | 74.06 |  | D - Other node or line within 3 km | 2.91 | 6.13 | Node: SÑC001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 876
1 | 877 | 877 | 0203111016 | Region II (Cagayan Valley) | Isabela | Divilacan | Sapinit | 17.2999 | 122.2357 | R | 299 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.35 | 36.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.06 | 51.77 | 74.06 |  | F - Nearest node and line over 5 km | 33.35 | 36.72 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 877
1 | 878 | 878 | 1108602026 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Patulang | 5.5982 | 125.4276 | R | 1662 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.19 | 58.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.06 | 51.77 | 74.06 |  | F - Nearest node and line over 5 km | 58.74 | 63.73 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 878
1 | 879 | 879 | 1380601072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 72 | 14.6121 | 120.9656 | U | 3331 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.65 | 33.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.05 | 51.77 | 74.05 |  | B - Node 0.5-1 km | 0.72 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 879
1 | 880 | 880 | PH0000880 | IV-A | Laguna | San Pablo City | Barangay VII-D (Pob.) | 14.0645 | 121.3321 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.61 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.05 | 51.77 | 74.05 |  | B - Node 0.5-1 km | 0.64 | 0.49 | Line: SPO001 TO LBQ001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 880
1 | 881 | 881 | 1907010013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Mantabuan Tabunan | 5.0244 | 120.2109 | R | 1984 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.04 | 51.76 | 74.04 |  | F - Nearest node and line over 5 km | 293.97 | 293.97 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 881
1 | 882 | 882 | 1907010017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Lookan Latuan | 17.2563 | 122.2293 | R | 1500 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.57 | 5.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.03 | 51.76 | 74.03 |  | F - Nearest node and line over 5 km | 29.56 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 882
1 | 883 | 883 | 1907010001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Baldatal Islam | 17.2558 | 122.2298 | R | 1818 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.03 | 51.75 | 74.03 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 883
1 | 884 | 884 | 1907010008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Latuan | 17.2558 | 122.2298 | R | 1314 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.03 | 51.75 | 74.03 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 884
1 | 885 | 885 | 1907010020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Sapaat | 17.2558 | 122.2299 | R | 861 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.02 | 51.75 | 74.02 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 885
1 | 886 | 886 | 1907010011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tabunan Likud Sikubong | 17.2558 | 122.2298 | R | 813 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.02 | 51.75 | 74.02 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 886
1 | 887 | 887 | 1907010007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Kohec | 17.2565 | 122.2302 | R | 407 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.74 | 5.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.01 | 51.74 | 74.01 |  | F - Nearest node and line over 5 km | 29.64 | 34.47 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 887
1 | 888 | 888 | 1004217003 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Lake Duminagat | 8.3251 | 123.6365 | R | 156 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.12 | 33.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74.01 | 51.74 | 74.01 |  | F - Nearest node and line over 5 km | 36.12 | 33.73 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 888
1 | 889 | 889 | PH0000889 | IV-A | Laguna | San Pablo City | Barangay VII-C (Pob.) | 14.0699 | 121.3307 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 1.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 74 | 51.74 | 74 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.12 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 889
1 | 890 | 890 | 1908820008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Aguak | Poblacion I | 17.2551 | 122.2292 | R | 3711 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.46 | 50.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.99 | 51.72 | 73.99 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 890
1 | 891 | 891 | 0102823005 | Region I (Ilocos Region) | Ilocos Norte | Vintar | Bago | 18.3257 | 120.6832 | R | 400 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.98 | 6.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.98 | 51.72 | 73.98 |  | F - Nearest node and line over 5 km | 6.98 | 6.85 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 891
1 | 892 | 892 | 1380601031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 31 | 14.6 | 120.9602 | U | 2968 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.52 | 37.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.98 | 51.72 | 73.98 |  | B - Node 0.5-1 km | 0.7 | 1.26 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 892
1 | 893 | 893 | 1380601028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 28 | 14.6036 | 120.9618 | U | 2872 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.28 | 16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.98 | 51.72 | 73.98 |  | B - Node 0.5-1 km | 0.91 | 0.92 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 893
1 | 894 | 894 | PH0000894 | VIII | Samar (Western Samar) | Catbalogan City | Cagudalo | 11.8541 | 124.8778 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.28 | 32.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.98 | 51.72 | 73.98 |  | F - Nearest node and line over 5 km | 64.96 | 64.91 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 894
1 | 895 | 895 | 1108202020 | Region XI (Davao Region) | Davao de Oro | Laak | Bagong Silang | 7.5296 | 126.039 | R | 968 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.87 | 17.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.97 | 51.71 | 73.97 |  | F - Nearest node and line over 5 km | 25.32 | 11.54 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 895
1 | 896 | 896 | PH0000896 | VIII | Leyte | Tacloban City | Barangay 18 | 11.2169 | 125.0033 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.16 | 6.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.96 | 51.7 | 73.96 |  | B - Node 0.5-1 km | 0.83 | 0.81 | Line: CAPOOCAN - TACLOBAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 896
1 | 897 | 897 | 1108602009 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Caburan Big | 5.5723 | 125.355 | R | 5203 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.61 | 50.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.95 | 51.7 | 73.95 |  | F - Nearest node and line over 5 km | 59.84 | 63.57 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 897
1 | 898 | 898 | 1380601097 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 97 | 14.6258 | 120.96 | U | 3744 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.01 | 46.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.95 | 51.7 | 73.95 |  | B - Node 0.5-1 km | 0.92 | 1.33 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 898
1 | 899 | 899 | 1380601096 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 96 | 14.6188 | 120.9666 | U | 2164 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.93 | 23.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.69 | 73.93 |  | A - Node within 0.5 km | 0.42 | 0.45 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 899
1 | 900 | 900 | PH0000900 | IV-A | Batangas | Lipa City | Poblacion Barangay 2 | 13.9422 | 121.1573 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.69 | 73.93 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.11 | Line: CLB001 TO BCY01 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 900
1 | 901 | 901 | PH0000901 | VIII | Leyte | Tacloban City | Barangay 19 | 11.2013 | 125.0207 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.04 | 5.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.69 | 73.93 |  | D - Other node or line within 3 km | 1.75 | 1.44 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 901
1 | 902 | 902 | 1108601006 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Talagutong | 6.2574 | 125.6601 | U | 7486 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.61 | 42.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.68 | 73.93 |  | F - Nearest node and line over 5 km | 44.61 | 42.9 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 902
1 | 903 | 903 | 0501711037 | Region V (Bicol Region) | Camarines Sur | Caramoan | Pili-Centro | 13.7646 | 123.8513 | R | 951 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.7 | 37.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.68 | 73.93 |  | D - Other node or line within 3 km | 1.7 | 37.31 | Node: COC001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 903
1 | 904 | 904 | 1380601013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 13 | 14.603 | 120.9608 | U | 2443 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.37 | 23.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.93 | 51.68 | 73.93 |  | D - Other node or line within 3 km | 1.02 | 1.05 | Node: MNL068 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 904
1 | 905 | 905 | PH0000905 | VI | Iloilo | Iloilo City | Dungon A | 10.7244 | 122.5534 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.83 | 3.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.92 | 51.68 | 73.92 |  | C - Line within 0.5 km; node over 1 km | 1.98 | 0.44 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 905
1 | 906 | 906 | 1380601069 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 69 | 14.6111 | 120.9672 | U | 2028 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.68 | 47.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.91 | 51.67 | 73.91 |  | B - Node 0.5-1 km | 0.54 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 906
1 | 907 | 907 | 1380601129 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 129 | 14.6121 | 120.9633 | U | 5890 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.66 | 15.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.91 | 51.67 | 73.91 |  | B - Node 0.5-1 km | 0.65 | 0.65 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 907
1 | 908 | 908 | 0304918001 | Region III (Central Luzon) | Nueva Ecija | Nampicuan | Alemania | 15.6997 | 120.6852 | R | 134 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.48 | 7.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.9 | 51.66 | 73.9 |  | F - Nearest node and line over 5 km | 9.15 | 9.22 | Node: CYN001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 908
1 | 909 | 909 | 1108202035 | Region XI (Davao Region) | Davao de Oro | Laak | New Bethlehem | 7.9792 | 125.6614 | R | 787 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.74 | 29.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.89 | 51.66 | 73.89 |  | F - Nearest node and line over 5 km | 42.71 | 42.2 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 909
1 | 910 | 910 | 0203131015 | Region II (Cagayan Valley) | Isabela | San Mariano | Disulap | 16.9678 | 122.0702 | R | 3022 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.38 | 23.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.88 | 51.65 | 73.88 |  | F - Nearest node and line over 5 km | 6.38 | 23.13 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 910
1 | 911 | 911 | 1381200010 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Malinao | 14.543 | 121.1024 | U | 5116 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.88 | 51.65 | 73.88 |  | A - Node within 0.5 km | 0.36 | 0.28 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 911
1 | 912 | 912 | PH0000912 | VIII | Leyte | Tacloban City | Barangay 16 | 11.1952 | 125.0075 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.81 | 8.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.87 | 51.64 | 73.87 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.26 | Line: CAPOOCAN - TACLOBAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 912
1 | 913 | 913 | 1380900011 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | San Rafael Village | 14.6371 | 120.9644 | U | 3564 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.49 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.87 | 51.64 | 73.87 |  | D - Other node or line within 3 km | 1.49 | 1.45 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 913
1 | 914 | 914 | 0501711033 | Region V (Bicol Region) | Camarines Sur | Caramoan | Pagolinan | 13.7175 | 123.8505 | R | 467 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.46 | 33.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.85 | 51.63 | 73.85 |  | F - Nearest node and line over 5 km | 6.46 | 33.94 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 914
1 | 915 | 915 | 1903621007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Bubong Tawa-an | 17.2545 | 122.2286 | R | 811 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.85 | 51.63 | 73.85 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 915
1 | 916 | 916 | 0504106005 | Region V (Bicol Region) | Masbate | Cawayan | Calapayan | 11.9939 | 123.8181 | R | 1426 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17 | 41.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.84 | 51.62 | 73.84 |  | F - Nearest node and line over 5 km | 17 | 41.88 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 916
1 | 917 | 917 | 1108211014 | Region XI (Davao Region) | Davao de Oro | Pantukan | Tag-Ugpo | 7.2624 | 126.0911 | U | 4093 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.53 | 23.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.84 | 51.62 | 73.84 |  | F - Nearest node and line over 5 km | 25.53 | 23.46 | Line: TAGUM - PANTUKAN SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 917
1 | 918 | 918 | 1380601032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 32 | 14.6035 | 120.9627 | U | 2286 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.84 | 39.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.84 | 51.62 | 73.84 |  | B - Node 0.5-1 km | 0.83 | 0.84 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 918
1 | 919 | 919 | 1108601011 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Lapuan | 6.1537 | 125.6885 | U | 5455 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.71 | 48.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.83 | 51.61 | 73.83 |  | F - Nearest node and line over 5 km | 45.71 | 48.72 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 919
1 | 920 | 920 | 1381100097 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 97 | 14.5415 | 121.0038 | U | 1400 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.82 | 51.61 | 73.82 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.39 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 920
1 | 921 | 921 | 1380900005 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Daanghari | 14.6658 | 120.9405 | U | 14657 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.81 | 51.6 | 73.81 |  | B - Node 0.5-1 km | 0.97 | 0.8 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 921
1 | 922 | 922 | 1380601164 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 164 | 14.6272 | 120.9761 | U | 1862 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.44 | 31.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.81 | 51.6 | 73.81 |  | A - Node within 0.5 km | 0.3 | 0.05 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 922
1 | 923 | 923 | PH0000923 | X | Misamis Occidental | Oroquieta City | Sebucal | 8.4842 | 123.8088 | R | 2217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.84 | 39.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.79 | 51.58 | 73.79 |  | F - Nearest node and line over 5 km | 49.07 | 39.51 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 923
1 | 924 | 924 | 1705305003 | MIMAROPA Region | Palawan | Bataraza | Buliluyan | 8.3331 | 117.2018 | R | 2478 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 229.75 | 232.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.77 | 51.57 | 73.77 |  | F - Nearest node and line over 5 km | 229.75 | 231.76 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 924
1 | 925 | 925 | 1102506007 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Monserrat | 6.6005 | 126.0908 | R | 2052 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.01 | 31.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.76 | 51.57 | 73.76 |  | F - Nearest node and line over 5 km | 34.01 | 31 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 925
1 | 926 | 926 | 1381701001 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Aguho | 14.544 | 121.0615 | U | 7557 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 0.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.75 | 51.56 | 73.75 |  | B - Node 0.5-1 km | 0.74 | 0.15 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 926
1 | 927 | 927 | 1907009016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | BasLikud | 17.2558 | 122.2298 | R | 1901 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.75 | 51.56 | 73.75 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 927
1 | 928 | 928 | 1208005019 | Region XII (SOCCSKSARGEN) | Sarangani | Maitum | Zion | 6.0855 | 124.5286 | R | 1705 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.89 | 52.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.75 | 51.56 | 73.75 |  | F - Nearest node and line over 5 km | 53.89 | 52.99 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 928
1 | 929 | 929 | 1381200002 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bagong Katipunan | 14.616 | 121.0954 | U | 934 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 0.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.74 | 51.55 | 73.74 |  | C - Line within 0.5 km; node over 1 km | 1.71 | 0.12 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 929
1 | 930 | 930 | 1380601092 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 92 | 14.6189 | 120.9657 | U | 2719 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.19 | 16.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.73 | 51.55 | 73.73 |  | A - Node within 0.5 km | 0.33 | 0.55 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 930
1 | 931 | 931 | 1380601026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 26 | 14.6014 | 120.9614 | U | 2633 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.89 | 50.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.66 | 51.5 | 73.66 |  | B - Node 0.5-1 km | 0.83 | 1.07 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 931
1 | 932 | 932 | 0502002027 | Region V (Bicol Region) | Catanduanes | Baras | Santa Maria | 13.6999 | 124.3898 | R | 185 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.45 | 80.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.66 | 51.49 | 73.66 |  | F - Nearest node and line over 5 km | 57.45 | 80.61 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 932
1 | 933 | 933 | PH0000933 | VI | Iloilo | Iloilo City | Tap-oc | 10.685 | 122.5455 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.48 | 9.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.65 | 51.49 | 73.65 |  | B - Node 0.5-1 km | 0.7 | 3.14 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 933
1 | 934 | 934 | PH0000934 | VIII | Leyte | Tacloban City | Barangay 35 | 11.245 | 125.0045 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 4.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.64 | 51.48 | 73.64 |  | B - Node 0.5-1 km | 0.64 | 3.65 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 934
1 | 935 | 935 | PH0000935 | VI | Iloilo | Iloilo City | South Baluarte | 10.7469 | 122.5647 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.72 | 4.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.64 | 51.48 | 73.64 |  | A - Node within 0.5 km | 0.27 | 0.26 | Line: 3,477 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 935
1 | 936 | 936 | 1380612038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 872 | 14.5848 | 121.0058 | U | 1921 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.35 | 20.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.64 | 51.48 | 73.64 |  | A - Node within 0.5 km | 0.33 | 0.36 | Node: MNL004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 936
1 | 937 | 937 | PH0000937 | IV-B | Palawan | Puerto Princesa City | Montible (Pob.) | 9.8168 | 118.5575 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.71 | 3.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.63 | 51.48 | 73.63 |  | F - Nearest node and line over 5 km | 19.68 | 18.66 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 937
1 | 938 | 938 | 1380601045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 45 | 14.6168 | 120.9729 | U | 2333 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.56 | 29.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.63 | 51.48 | 73.63 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.08 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 938
1 | 939 | 939 | 1380604006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 273 | 14.6233 | 120.9847 | U | 850 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.86 | 41.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.63 | 51.48 | 73.63 |  | B - Node 0.5-1 km | 0.78 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 939
1 | 940 | 940 | 0402123013 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Gavino Maderan | 14.2984 | 121.0074 | U | 9052 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.91 | 4.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.62 | 51.47 | 73.62 |  | D - Other node or line within 3 km | 1.87 | 4.79 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 940
1 | 941 | 941 | 0405616013 | Region IV-A (CALABARZON) | Quezon | General Luna | Magsaysay | 13.6985 | 122.2717 | R | 679 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 6.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.62 | 51.47 | 73.62 |  | D - Other node or line within 3 km | 1.2 | 6.03 | Node: CTQ004 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 941
1 | 942 | 942 | 1381600025 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Poblacion | 14.7336 | 120.9911 | U | 224 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 0.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.62 | 51.47 | 73.62 |  | C - Line within 0.5 km; node over 1 km | 2.49 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 942
1 | 943 | 943 | 1102510007 | Region XI (Davao Region) | Davao Oriental | San Isidro | La Union | 6.7187 | 126.1125 | R | 4594 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.64 | 17.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.62 | 51.46 | 73.62 |  | F - Nearest node and line over 5 km | 22.64 | 17.77 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 943
1 | 944 | 944 | 1102401021 | Region XI (Davao Region) | Davao del Sur | Bansalan | Sibayan | 6.8362 | 125.2508 | R | 733 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.02 | 14.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.61 | 51.46 | 73.61 |  | F - Nearest node and line over 5 km | 7.02 | 14.13 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 944
1 | 945 | 945 | 1380604005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 272 | 14.6245 | 120.9822 | U | 1096 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.46 | 15.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.59 | 51.45 | 73.59 |  | B - Node 0.5-1 km | 0.89 | 0.08 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 945
1 | 946 | 946 | PH0000946 | X | Misamis Oriental | Cagayan De Oro City | Barangay 21 (Pob.) | 8.4804 | 124.6466 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.09 | 1.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.59 | 51.45 | 73.59 |  | D - Other node or line within 3 km | 1.04 | 0.71 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 946
1 | 947 | 947 | 1403213021 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Magnao | 17.434 | 121.3196 | R | 1158 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.93 | 3.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.58 | 51.44 | 73.58 |  | E - Nearest node or line 3-5 km | 11.93 | 3.02 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 947
1 | 948 | 948 | 1380601133 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 133 | 14.6297 | 120.9696 | U | 2179 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.15 | 45.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.57 | 51.44 | 73.57 |  | B - Node 0.5-1 km | 0.52 | 0.46 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 948
1 | 949 | 949 | 1108603013 | Region XI (Davao Region) | Davao Occidental | Malita | Kinangan | 6.2912 | 125.5821 | R | 3123 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.35 | 33.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.57 | 51.43 | 73.57 |  | F - Nearest node and line over 5 km | 35.35 | 33.78 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 949
1 | 950 | 950 | PH0000950 | VIII | Leyte | Tacloban City | Barangay 34 | 11.1952 | 125.0075 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.91 | 8.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.57 | 51.43 | 73.57 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.26 | Line: CAPOOCAN - TACLOBAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 950
1 | 951 | 951 | 1108602034 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Tabayon | 5.5986 | 125.4288 | R | 3658 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.18 | 54.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.57 | 51.43 | 73.57 |  | F - Nearest node and line over 5 km | 58.73 | 63.75 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 951
1 | 952 | 952 | 0102917004 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Matibuey | 17.2121 | 120.6624 | R | 1080 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.52 | 0.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.56 | 51.43 | 73.56 |  | D - Other node or line within 3 km | 8.52 | 0.86 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 952
1 | 953 | 953 | 0201528020 | Region II (Cagayan Valley) | Cagayan | Tuao | Mambacag | 17.6739 | 121.5351 | R | 1447 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 10.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.56 | 51.43 | 73.56 |  | D - Other node or line within 3 km | 2.47 | 10.31 | Node: TUC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 953
1 | 954 | 954 | 1381701008 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santo Rosario-Kanluran | 14.5522 | 121.0689 | U | 5516 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.55 | 51.42 | 73.55 |  | B - Node 0.5-1 km | 0.84 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 954
1 | 955 | 955 | 1380601067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 67 | 14.6135 | 120.9668 | U | 4207 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.83 | 24.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.55 | 51.42 | 73.55 |  | B - Node 0.5-1 km | 0.66 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 955
1 | 956 | 956 | 1102506018 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Tiblawan | 6.4967 | 126.1194 | R | 4646 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.97 | 42.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.54 | 51.41 | 73.54 |  | F - Nearest node and line over 5 km | 45.97 | 42.46 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 956
1 | 957 | 957 | PH0000957 | IV-A | Laguna | San Pablo City | Barangay VII-A (Pob.) | 14.0706 | 121.3215 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.53 | 51.41 | 73.53 |  | C - Line within 0.5 km; node over 1 km | 1.29 | 0.12 | Line: SPO001 TO LCQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 957
1 | 958 | 958 | 0806022043 | Region VIII (Eastern Visayas) | Samar | Paranas | Tapul | 11.9126 | 125.0414 | R | 423 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.02 | 76.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.53 | 51.4 | 73.53 |  | F - Nearest node and line over 5 km | 74.95 | 77.92 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 958
1 | 959 | 959 | 0205010029 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Lawigan | 16.2057 | 120.7778 | R | 905 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.86 | 17.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.52 | 51.4 | 73.52 |  | F - Nearest node and line over 5 km | 17.86 | 17.57 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 959
1 | 960 | 960 | 1108601003 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | North Lamidan | 6.0954 | 125.703 | R | 2195 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.01 | 52.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.51 | 51.39 | 73.51 |  | F - Nearest node and line over 5 km | 47.01 | 51.99 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 960
1 | 961 | 961 | 0806011005 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Camonoan | 12.1248 | 124.8882 | R | 142 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.66 | 96.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.51 | 51.39 | 73.51 |  | F - Nearest node and line over 5 km | 94.25 | 94.21 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 961
1 | 962 | 962 | 1380601047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 47 | 14.619 | 120.9734 | U | 1157 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.26 | 19.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.5 | 51.39 | 73.5 |  | B - Node 0.5-1 km | 0.87 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 962
1 | 963 | 963 | 1380601152 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 152 | 14.6292 | 120.9748 | U | 6407 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.96 | 51.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.5 | 51.39 | 73.5 |  | A - Node within 0.5 km | 0.3 | 0.29 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 963
1 | 964 | 964 | 0806012009 | Region VIII (Eastern Visayas) | Samar | Motiong | Calapi | 11.9416 | 125.0206 | R | 2682 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.08 | 79.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.5 | 51.38 | 73.5 |  | F - Nearest node and line over 5 km | 78.08 | 79.88 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 964
1 | 965 | 965 | 0603040086 | Region VI (Western Visayas) | Iloilo | San Joaquin | Torocadan | 10.6086 | 122.12 | R | 227 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.15 | 0.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.49 | 51.38 | 73.49 |  | D - Other node or line within 3 km | 26.22 | 2.14 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Route options survey candidate: compare actual node lateral with approved line tap. | 965
1 | 966 | 966 | 0603040075 | Region VI (Western Visayas) | Iloilo | San Joaquin | Santiago | 10.5782 | 122.0965 | R | 130 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.08 | 1.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.49 | 51.37 | 73.49 |  | C - Line within 0.5 km; node over 1 km | 26.81 | 0.16 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 966
1 | 967 | 967 | 1380601099 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 99 | 14.6234 | 120.9605 | U | 6502 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.22 | 15.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.49 | 51.37 | 73.49 |  | B - Node 0.5-1 km | 0.66 | 1.24 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 967
1 | 968 | 968 | 1381200023 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Nicolas | 14.5615 | 121.0788 | U | 2764 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.26 | 0.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.48 | 51.37 | 73.48 |  | A - Node within 0.5 km | 0.26 | 0.23 | Line: Aerial 216C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 968
1 | 969 | 969 | 0806022011 | Region VIII (Eastern Visayas) | Samar | Paranas | Casandig I | 11.7714 | 125.0859 | R | 682 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.57 | 69.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.47 | 51.36 | 73.47 |  | F - Nearest node and line over 5 km | 59.83 | 62.7 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 969
1 | 970 | 970 | 1380605076 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 373 | 14.6303 | 120.9847 | U | 3903 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.31 | 36.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.46 | 51.36 | 73.46 |  | C - Line within 0.5 km; node over 1 km | 1.28 | 0.22 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 970
1 | 971 | 971 | 0806022019 | Region VIII (Eastern Visayas) | Samar | Paranas | Maylobe | 11.887 | 125.0619 | R | 345 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.96 | 80.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.46 | 51.36 | 73.46 |  | F - Nearest node and line over 5 km | 72.28 | 75.21 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 971
1 | 972 | 972 | 0205010028 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Latbang | 16.4877 | 120.9828 | R | 1027 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.9 | 13.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.45 | 51.35 | 73.45 |  | F - Nearest node and line over 5 km | 16.9 | 13.86 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 972
1 | 973 | 973 | 1380606024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 418 | 14.604 | 121.001 | U | 2921 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.67 | 35.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.45 | 51.35 | 73.45 |  | A - Node within 0.5 km | 0.44 | 0.04 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 973
1 | 974 | 974 | PH0000974 | VIII | Leyte | Tacloban City | Barangay 13 | 11.2715 | 124.9509 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.68 | 7.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.44 | 51.34 | 73.44 |  | F - Nearest node and line over 5 km | 6.65 | 9.14 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 974
1 | 975 | 975 | 0600406010 | Region VI (Western Visayas) | Aklan | Ibajay | Bugtongbato | 11.7733 | 122.216 | R | 1761 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.56 | 0.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.43 | 51.33 | 73.43 |  | F - Nearest node and line over 5 km | 10.56 | 16.77 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 975
1 | 976 | 976 | 1380601085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 85 | 14.6145 | 120.9691 | U | 4154 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.01 | 12.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.42 | 51.33 | 73.42 |  | B - Node 0.5-1 km | 0.79 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 976
1 | 977 | 977 | 0806022045 | Region VIII (Eastern Visayas) | Samar | Paranas | Tigbawon | 11.806 | 125.1294 | R | 1075 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.76 | 58.71 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.42 | 51.33 | 73.42 |  | F - Nearest node and line over 5 km | 64.48 | 67.27 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 977
1 | 978 | 978 | 0603040040 | Region VI (Western Visayas) | Iloilo | San Joaquin | Igdagmay | 10.6703 | 122.0935 | R | 191 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.83 | 9.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.42 | 51.33 | 73.42 |  | F - Nearest node and line over 5 km | 19.83 | 9.59 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 978
1 | 979 | 979 | PH0000979 | VI | Capiz | Roxas City | Poblacion VIII | 11.5755 | 122.7549 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.66 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.41 | 51.32 | 73.41 |  | C - Line within 0.5 km; node over 1 km | 1.66 | 0.16 | Line: ROXAS - IVISAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 979
1 | 980 | 980 | 1380601161 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 161 | 14.6278 | 120.9754 | U | 1034 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49 | 50.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.41 | 51.32 | 73.41 |  | A - Node within 0.5 km | 0.25 | 0.13 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 980
1 | 981 | 981 | 0200901004 | Region II (Cagayan Valley) | Batanes | Basco | San Joaquin | 20.4412 | 121.9888 | R | 543 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 223.73 | 216.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.4 | 51.31 | 73.4 |  | F - Nearest node and line over 5 km | 219.41 | 216.3 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 981
1 | 982 | 982 | 1380601004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 4 | 14.6086 | 120.9681 | U | 1742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.91 | 19.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.39 | 51.31 | 73.39 |  | A - Node within 0.5 km | 0.26 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 982
1 | 983 | 983 | PH0000983 | VIII | Leyte | Tacloban City | Barangay 28 | 11.2445 | 125.0067 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.72 | 3.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.39 | 51.3 | 73.39 |  | B - Node 0.5-1 km | 0.72 | 3.56 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 983
1 | 984 | 984 | 1108602035 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Tanuman | 5.5703 | 125.3542 | R | 2420 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.33 | 54.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.38 | 51.3 | 73.38 |  | F - Nearest node and line over 5 km | 60.05 | 63.75 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 984
1 | 985 | 985 | 1380601130 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 130 | 14.6287 | 120.9666 | U | 1811 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.86 | 24.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.37 | 51.3 | 73.37 |  | B - Node 0.5-1 km | 0.76 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 985
1 | 986 | 986 | 1381100085 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 85 | 14.5449 | 120.9977 | U | 1322 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.49 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.37 | 51.29 | 73.37 |  | A - Node within 0.5 km | 0.35 | 0.16 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 986
1 | 987 | 987 | 0102917008 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | San Miliano | 17.2057 | 120.555 | R | 689 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.06 | 3.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.37 | 51.29 | 73.37 |  | E - Nearest node or line 3-5 km | 6.06 | 3.53 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 987
1 | 988 | 988 | 0502004010 | Region V (Bicol Region) | Catanduanes | Caramoran | Guiamlong | 13.799 | 124.1364 | R | 757 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.61 | 61.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.36 | 51.29 | 73.36 |  | F - Nearest node and line over 5 km | 29.61 | 61.92 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 988
1 | 989 | 989 | 0603040013 | Region VI (Western Visayas) | Iloilo | San Joaquin | Cadluman | 10.6128 | 122.145 | R | 197 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.7 | 1.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.35 | 51.28 | 73.35 |  | D - Other node or line within 3 km | 26.84 | 2.06 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Route options survey candidate: compare actual node lateral with approved line tap. | 989
1 | 990 | 990 | 0603040073 | Region VI (Western Visayas) | Iloilo | San Joaquin | San Mateo Norte | 10.5683 | 122.0386 | R | 192 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.2 | 0.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.35 | 51.28 | 73.35 |  | C - Line within 0.5 km; node over 1 km | 24.21 | 0.02 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 990
1 | 991 | 991 | 0603040043 | Region VI (Western Visayas) | Iloilo | San Joaquin | Igpayong | 10.6192 | 122.0679 | R | 127 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.47 | 2.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.35 | 51.28 | 73.35 |  | E - Nearest node or line 3-5 km | 21.32 | 4.77 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 991
1 | 992 | 992 | PH0000992 | VIII | Leyte | Tacloban City | Barangay 43-A | 11.2483 | 124.9642 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.83 | 4.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.34 | 51.27 | 73.34 |  | E - Nearest node or line 3-5 km | 4.28 | 6.32 | Node: TCL002 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 992
1 | 993 | 993 | 1003515020 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Panganapan | 7.783 | 123.8872 | R | 663 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.21 | 20.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.33 | 51.27 | 73.33 |  | F - Nearest node and line over 5 km | 30.49 | 18.03 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 993
1 | 994 | 994 | 1003515015 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Malaig | 7.7885 | 123.9146 | R | 605 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.36 | 18.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.33 | 51.26 | 73.33 |  | F - Nearest node and line over 5 km | 31.02 | 20.04 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 994
1 | 995 | 995 | 1380601119 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 119 | 14.6102 | 120.9611 | U | 2416 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.59 | 46.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.32 | 51.26 | 73.32 |  | B - Node 0.5-1 km | 0.89 | 0.86 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 995
1 | 996 | 996 | 1380607012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 648 | 14.595 | 120.9608 | U | 5805 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.64 | 12.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.31 | 51.25 | 73.31 |  | A - Node within 0.5 km | 0.14 | 1.58 | Node: MNL068 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 996
1 | 997 | 997 | 1380614056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 800 | 14.5705 | 120.9997 | U | 1605 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.45 | 43.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.31 | 51.25 | 73.31 |  | B - Node 0.5-1 km | 0.61 | 0.39 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 997
1 | 998 | 998 | 1908702013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Pantawan | 17.2541 | 122.2281 | R | 4001 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.31 | 51.25 | 73.31 |  | F - Nearest node and line over 5 km | 29.3 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 998
1 | 999 | 999 | 1380601025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 25 | 14.6026 | 120.9635 | U | 2622 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 27.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.31 | 51.25 | 73.31 |  | B - Node 0.5-1 km | 0.81 | 0.81 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 999
1 | 1000 | 1000 | 1380601128 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 128 | 14.6133 | 120.9608 | U | 24422 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.98 | 14.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.31 | 51.25 | 73.31 |  | B - Node 0.5-1 km | 0.56 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1000

## Batch 2 (1,001 - 2,000)
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA — Batch 2 (1,001 - 2,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
2 | 1 | 1001 | 1108205016 | Region XI (Davao Region) | Davao de Oro | Maragusan | New Katipunan | 7.3257 | 126.0998 | R | 3073 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.3 | 27.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.28 | 51.23 | 73.28 |  | F - Nearest node and line over 5 km | 27 | 26.61 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1001
2 | 2 | 1002 | 0802615011 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Omawas | 11.5311 | 125.474 | R | 1082 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.77 | 61.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.28 | 51.23 | 73.28 |  | F - Nearest node and line over 5 km | 60.77 | 61.81 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1002
2 | 3 | 1003 | PH0001003 | VI | Capiz | Roxas City | Poblacion IV | 11.5188 | 122.7749 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.34 | 1.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.27 | 51.22 | 73.27 |  | D - Other node or line within 3 km | 1.84 | 1.1 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 1003
2 | 4 | 1004 | 0806008009 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Lim-ao | 11.7129 | 125.0901 | R | 306 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.49 | 56.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.27 | 51.22 | 73.27 |  | F - Nearest node and line over 5 km | 53.49 | 56.33 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1004
2 | 5 | 1005 | 1381200004 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Buting | 14.5555 | 121.066 | U | 10991 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.23 | 0.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.26 | 51.21 | 73.26 |  | C - Line within 0.5 km; node over 1 km | 1.23 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1005
2 | 6 | 1006 | 1380606199 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 592 | 14.6021 | 121.0113 | U | 2443 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.91 | 54.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.25 | 51.21 | 73.25 |  | B - Node 0.5-1 km | 0.73 | 0.04 | Line: UG 288C via V-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1006
2 | 7 | 1007 | 1908702010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Minabay | 17.2539 | 122.2279 | R | 5213 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.25 | 51.21 | 73.25 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1007
2 | 8 | 1008 | 1108601007 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Baluntaya | 6.2461 | 125.6403 | R | 2604 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.01 | 41.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.24 | 51.2 | 73.24 |  | F - Nearest node and line over 5 km | 43.01 | 41.92 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1008
2 | 9 | 1009 | 1380604016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 283 | 14.6001 | 120.9689 | U | 1386 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.35 | 16.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.24 | 51.2 | 73.24 |  | B - Node 0.5-1 km | 0.75 | 0.66 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1009
2 | 10 | 1010 | 0803734019 | Region VIII (Eastern Visayas) | Leyte | Matalom | President Garcia | 10.2493 | 124.8171 | R | 874 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.87 | 4.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.23 | 51.19 | 73.23 |  | E - Nearest node or line 3-5 km | 13 | 4.48 | Line: INOPACAN (BAYBAY) - MAASIN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1010
2 | 11 | 1011 | 1003515008 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Kaludan | 7.7984 | 123.9241 | R | 1052 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.48 | 20.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.23 | 51.19 | 73.23 |  | F - Nearest node and line over 5 km | 30.48 | 20.31 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1011
2 | 12 | 1012 | 1705320004 | MIMAROPA Region | Palawan | Taytay | Batas | 11.1526 | 119.6072 | R | 1440 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.09 | 38.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.22 | 51.19 | 73.22 |  | F - Nearest node and line over 5 km | 14.09 | 38.09 | Node: TYW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1012
2 | 13 | 1013 | 0501727013 | Region V (Bicol Region) | Camarines Sur | Pasacao | Salvacion | 13.6033 | 122.9375 | R | 993 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.75 | 12.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.21 | 51.18 | 73.21 |  | F - Nearest node and line over 5 km | 10.75 | 10.57 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1013
2 | 14 | 1014 | 1380601117 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 117 | 14.6126 | 120.9606 | U | 4286 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.99 | 32.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.21 | 51.18 | 73.21 |  | B - Node 0.5-1 km | 0.64 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1014
2 | 15 | 1015 | 1600303037 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Guibonon | 8.6312 | 125.3112 | R | 330 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.07 | 28.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.21 | 51.18 | 73.21 |  | F - Nearest node and line over 5 km | 29.07 | 28.4 | Line: CDO - BUENAVISTA via GINGOOG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1015
2 | 16 | 1016 | 1380601134 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 134 | 14.6285 | 120.9675 | U | 1090 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.64 | 39.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.21 | 51.18 | 73.21 |  | B - Node 0.5-1 km | 0.66 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1016
2 | 17 | 1017 | 1380603017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 308 | 14.6113 | 120.995 | U | 1064 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.08 | 11.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.18 | 51.16 | 73.18 |  | B - Node 0.5-1 km | 0.95 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1017
2 | 18 | 1018 | 1108210013 | Region XI (Davao Region) | Davao de Oro | New Bataan | Andap | 7.513 | 126.1584 | U | 6839 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.73 | 23.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.18 | 51.16 | 73.18 |  | F - Nearest node and line over 5 km | 36.73 | 23.66 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1018
2 | 19 | 1019 | 1906603010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Kalingalan Caluang | Pang | 17.2555 | 122.2296 | U | 5469 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.18 | 51.16 | 73.18 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1019
2 | 20 | 1020 | 1908704010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Sedem | 17.2541 | 122.2282 | R | 2947 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.17 | 51.15 | 73.17 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1020
2 | 21 | 1021 | 1003515012 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Liangan | 7.788 | 123.9095 | R | 621 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.49 | 19.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.17 | 51.15 | 73.17 |  | F - Nearest node and line over 5 km | 30.84 | 19.61 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1021
2 | 22 | 1022 | 1900707025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Mahawid | 6.6038 | 122.1934 | R | 2719 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.56 | 36.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.16 | 51.14 | 73.16 |  | F - Nearest node and line over 5 km | 36.56 | 36.55 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1022
2 | 23 | 1023 | 1908824011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Marader | 17.2552 | 122.2293 | R | 1472 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.45 | 41.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.16 | 51.14 | 73.16 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1023
2 | 24 | 1024 | 0402103046 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino III | 14.3976 | 120.9775 | U | 63684 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.15 | 51.14 | 73.15 |  | A - Node within 0.5 km | 0.28 | 5.04 | Node: BRC002-TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1024
2 | 25 | 1025 | 1903639007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Kapatagan | 17.2546 | 122.2286 | R | 1794 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.14 | 73.14 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1025
2 | 26 | 1026 | 1908824008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Kedati | 17.2548 | 122.23 | R | 1096 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.28 | 39.89 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | F - Nearest node and line over 5 km | 29.5 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1026
2 | 27 | 1027 | 1003515024 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Raraban | 7.7893 | 123.9152 | R | 637 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.96 | 20.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | F - Nearest node and line over 5 km | 30.96 | 20.04 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1027
2 | 28 | 1028 | 1903639010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Minimao | 17.2546 | 122.2286 | R | 1522 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | F - Nearest node and line over 5 km | 29.38 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1028
2 | 29 | 1029 | 1906604029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Luuk | Guimbaun | 17.2562 | 122.2297 | R | 2065 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 34.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | F - Nearest node and line over 5 km | 29.58 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1029
2 | 30 | 1030 | 0506210007 | Region V (Bicol Region) | Sorsogon | Juban | Calateo | 12.8053 | 123.986 | R | 771 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.27 | 1.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | D - Other node or line within 3 km | 3.27 | 1.5 | Line: SORSOGON - MATNOG | Route options survey candidate: compare actual node lateral with approved line tap. | 1030
2 | 31 | 1031 | 1908806016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Manindolo | 17.2552 | 122.2293 | R | 1527 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.48 | 34.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.14 | 51.13 | 73.14 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1031
2 | 32 | 1032 | 1908806011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Lomoyon | 17.2552 | 122.2293 | R | 1271 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.48 | 34.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.13 | 51.13 | 73.13 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1032
2 | 33 | 1033 | 0907216011 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Litawan | 7.4044 | 122.1391 | R | 673 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.61 | 16.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.12 | 51.12 | 73.12 |  | F - Nearest node and line over 5 km | 22.61 | 16.54 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1033
2 | 34 | 1034 | 1380601094 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 94 | 14.6212 | 120.9661 | U | 2244 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.27 | 49.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.12 | 51.12 | 73.12 |  | B - Node 0.5-1 km | 0.51 | 0.59 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1034
2 | 35 | 1035 | 1380601080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 80 | 14.6159 | 120.9703 | U | 2631 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.86 | 20.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.12 | 51.12 | 73.12 |  | B - Node 0.5-1 km | 0.85 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1035
2 | 36 | 1036 | 0603038016 | Region VI (Western Visayas) | Iloilo | San Dionisio | Naborot | 11.3662 | 123.1341 | R | 160 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.09 | 1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.11 | 51.11 | 73.11 |  | E - Nearest node or line 3-5 km | 6.65 | 3.26 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1036
2 | 37 | 1037 | 1380611038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 823 | 14.5828 | 120.9979 | U | 3093 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.79 | 19.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.11 | 51.11 | 73.11 |  | B - Node 0.5-1 km | 0.56 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1037
2 | 38 | 1038 | 0405805018 | Region IV-A (CALABARZON) | Rizal | Cainta | Santa Rosa | 14.5821 | 121.1181 | R | 1550 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 0.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.1 | 51.1 | 73.1 |  | B - Node 0.5-1 km | 0.6 | 0.26 | Line: RELIANCE TO SINILOAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1038
2 | 39 | 1039 | 1380900008 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | North Bay Boulevard North | 14.6738 | 120.9349 | U | 15061 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.09 | 51.1 | 73.09 |  | B - Node 0.5-1 km | 0.79 | 0.79 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1039
2 | 40 | 1040 | 1381600022 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Pariancillo Villa | 14.6885 | 121.0056 | U | 1977 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.4 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.08 | 51.09 | 73.08 |  | B - Node 0.5-1 km | 0.95 | 0.42 | Line: Aerial 96C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1040
2 | 41 | 1041 | 0806010022 | Region VIII (Eastern Visayas) | Samar | Marabut | Roño | 11.1423 | 125.2052 | R | 525 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.86 | 20.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.08 | 51.09 | 73.08 |  | F - Nearest node and line over 5 km | 20.63 | 22.48 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1041
2 | 42 | 1042 | 1401109002 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Lubo | 16.6681 | 120.716 | R | 1437 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.11 | 6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.06 | 51.08 | 73.06 |  | F - Nearest node and line over 5 km | 7.11 | 5.96 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1042
2 | 43 | 1043 | PH0001043 | I | Ilocos Norte | Laoag City | Bgy. No. 11, Santa Balbina (Pob.) | 18.1918 | 120.6111 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.06 | 51.08 | 73.06 |  | D - Other node or line within 3 km | 3.03 | 1.81 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 1043
2 | 44 | 1044 | PH0001044 | VIII | Leyte | Tacloban City | Barangay 47 | 11.2383 | 124.9999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.86 | 9.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.05 | 51.07 | 73.05 |  | A - Node within 0.5 km | 0.31 | 3.04 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1044
2 | 45 | 1045 | PH0001045 | IV-B | Palawan | Puerto Princesa City | Tanabag | 9.9961 | 118.989 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.39 | 0.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.04 | 51.06 | 73.04 |  | C - Line within 0.5 km; node over 1 km | 6.39 | 0.04 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1045
2 | 46 | 1046 | 1401112005 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Banengbeng | 16.5102 | 120.5474 | R | 913 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.66 | 4.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73.01 | 51.04 | 73.01 |  | E - Nearest node or line 3-5 km | 6.66 | 4.75 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1046
2 | 47 | 1047 | 1400115012 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Umnap | 17.5824 | 121.0552 | R | 278 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.4 | 26.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 73 | 51.03 | 73 |  | F - Nearest node and line over 5 km | 30.4 | 26.33 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1047
2 | 48 | 1048 | PH0001048 | VI | Iloilo | Iloilo City | Simon Ledesma | 10.7051 | 122.5628 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 0.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.99 | 51.03 | 72.99 |  | D - Other node or line within 3 km | 1.12 | 0.53 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 1048
2 | 49 | 1049 | 1400125003 | Cordillera Administrative Region (CAR) | Abra | Tineg | Anayan | 17.8941 | 120.9613 | R | 231 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.12 | 27.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.98 | 51.02 | 72.98 |  | F - Nearest node and line over 5 km | 27.12 | 28.89 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1049
2 | 50 | 1050 | PH0001050 | VIII | Leyte | Tacloban City | Barangay 26 | 11.245 | 125.0045 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.28 | 5.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.97 | 51.01 | 72.97 |  | B - Node 0.5-1 km | 0.64 | 3.65 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1050
2 | 51 | 1051 | 1380612034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 867 | 14.5815 | 121.007 | U | 2180 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.45 | 51.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.96 | 51.01 | 72.96 |  | B - Node 0.5-1 km | 0.56 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1051
2 | 52 | 1052 | PH0001052 | III | Nueva Ecija | Cabanatuan City | Padre Crisostomo | 15.5173 | 120.9738 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.95 | 51 | 72.95 |  | D - Other node or line within 3 km | 4.18 | 1.32 | Line: TALAVERA - MULTI NET | Route options survey candidate: compare actual node lateral with approved line tap. | 1052
2 | 53 | 1053 | 0506216049 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Maricrum | 13.0125 | 124.0166 | R | 1659 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.06 | 3.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.95 | 51 | 72.95 |  | E - Nearest node or line 3-5 km | 3.06 | 3.43 | Node: SCS003 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1053
2 | 54 | 1054 | PH0001054 | VIII | Leyte | Tacloban City | Barangay 29 | 11.2383 | 124.9999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.52 | 6.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.95 | 51 | 72.95 |  | A - Node within 0.5 km | 0.31 | 3.04 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1054
2 | 55 | 1055 | 1381100118 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 118 | 14.5483 | 121.0053 | U | 1680 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.94 | 50.99 | 72.94 |  | B - Node 0.5-1 km | 0.68 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1055
2 | 56 | 1056 | PH0001056 | VIII | Leyte | Tacloban City | Barangay 30 | 11.1969 | 125.0165 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.41 | 9.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.93 | 50.99 | 72.93 |  | D - Other node or line within 3 km | 1.89 | 1.13 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 1056
2 | 57 | 1057 | 1380611040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 825 | 14.5804 | 120.9983 | U | 400 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.52 | 11.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.93 | 50.98 | 72.93 |  | B - Node 0.5-1 km | 0.65 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1057
2 | 58 | 1058 | 0603028040 | Region VI (Western Visayas) | Iloilo | Leon | Danao | 10.8531 | 122.2849 | R | 360 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.01 | 16.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.92 | 50.98 | 72.92 |  | F - Nearest node and line over 5 km | 22.01 | 16.24 | Line: 7,761 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1058
2 | 59 | 1059 | 0806417004 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Cabadbaran | 10.4039 | 124.9396 | R | 220 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.08 | 4.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.91 | 50.97 | 72.91 |  | F - Nearest node and line over 5 km | 32.46 | 18.33 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1059
2 | 60 | 1060 | 1380601132 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 132 | 14.6309 | 120.967 | U | 953 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.91 | 40.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.91 | 50.97 | 72.91 |  | B - Node 0.5-1 km | 0.82 | 0.75 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1060
2 | 61 | 1061 | 1102503008 | Region XI (Davao Region) | Davao Oriental | Boston | Simulao | 7.8812 | 126.2504 | R | 1194 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.22 | 18.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.91 | 50.97 | 72.91 |  | F - Nearest node and line over 5 km | 22.22 | 18.81 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1061
2 | 62 | 1062 | 1381400007 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Isabelita | 14.6038 | 121.0296 | U | 1654 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 0.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.91 | 50.97 | 72.91 |  | C - Line within 0.5 km; node over 1 km | 1.83 | 0.05 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1062
2 | 63 | 1063 | 1903601025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Sugod | 17.2545 | 122.2281 | U | 1259 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.89 | 50.96 | 72.89 |  | F - Nearest node and line over 5 km | 29.32 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1063
2 | 64 | 1064 | 1208006003 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Kinam | 5.9507 | 125.4321 | U | 12767 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.18 | 32.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.89 | 50.96 | 72.89 |  | F - Nearest node and line over 5 km | 24.18 | 32.55 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1064
2 | 65 | 1065 | 1381400019 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Tibagan | 17.7355 | 120.4546 | U | 4058 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.86 | 50.94 | 72.86 |  | C - Line within 0.5 km; node over 1 km | 5.76 | 0.14 | Line: SEGMENT 3 (VIGAN - BATAC) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1065
2 | 66 | 1066 | PH0001066 | XI | Davao Del Sur | Davao City | Barangay 31-D (Pob.) | 7.1722 | 125.4513 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 1.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.85 | 50.93 | 72.85 |  | D - Other node or line within 3 km | 1.59 | 1.03 | Line: 31,493 FOC | Route options survey candidate: compare actual node lateral with approved line tap. | 1066
2 | 67 | 1067 | PH0001067 | VI | Iloilo | Iloilo City | Buhang Taft North | 10.7184 | 122.5547 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.89 | 9.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.85 | 50.93 | 72.85 |  | D - Other node or line within 3 km | 1.54 | 0.57 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 1067
2 | 68 | 1068 | PH0001068 | III | Nueva Ecija | Cabanatuan City | Caridad | 15.5212 | 121.0246 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.98 | 1.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.83 | 50.92 | 72.83 |  | F - Nearest node and line over 5 km | 8.1 | 5.43 | Line: TALAVERA - MULTI NET | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1068
2 | 69 | 1069 | 1380605078 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 375 | 14.6279 | 120.9851 | U | 4028 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.29 | 32.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.83 | 50.91 | 72.83 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1069
2 | 70 | 1070 | 1907001018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tundon | 17.2554 | 122.2306 | R | 3035 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.81 | 50.9 | 72.81 |  | F - Nearest node and line over 5 km | 29.6 | 34.49 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1070
2 | 71 | 1071 | PH0001071 | VIII | Leyte | Tacloban City | Barangay 32 | 11.2294 | 124.9922 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 2.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.81 | 50.9 | 72.81 |  | D - Other node or line within 3 km | 1.59 | 2.64 | Node: TCL002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1071
2 | 72 | 1072 | 0504102005 | Region V (Bicol Region) | Masbate | Baleno | Cagpandan | 12.5135 | 123.4372 | R | 1191 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.18 | 0.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.81 | 50.9 | 72.81 |  | E - Nearest node or line 3-5 km | 4.18 | 24.55 | Node: AYM001 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1072
2 | 73 | 1073 | 0203131016 | Region II (Cagayan Valley) | Isabela | San Mariano | Disusuan | 16.9834 | 122.0562 | R | 655 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.6 | 21.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.8 | 50.89 | 72.8 |  | E - Nearest node or line 3-5 km | 4.6 | 21.26 | Node: SOI001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1073
2 | 74 | 1074 | 1907001003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Buan | 17.2549 | 122.2291 | R | 4393 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.8 | 50.89 | 72.8 |  | F - Nearest node and line over 5 km | 29.44 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1074
2 | 75 | 1075 | 0806008008 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Dalosdoson | 11.6827 | 125.0723 | R | 332 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.85 | 52.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.79 | 50.88 | 72.79 |  | F - Nearest node and line over 5 km | 49.85 | 52.72 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1075
2 | 76 | 1076 | PH0001076 | I | Ilocos Norte | Laoag City | Bgy. No. 13, Nstra. Sra. De Visitacion (Pob.) | 18.2199 | 120.6057 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 1.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.78 | 50.88 | 72.78 |  | C - Line within 0.5 km; node over 1 km | 2.61 | 0.01 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1076
2 | 77 | 1077 | 0403403004 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Canlalay | 14.3425 | 121.072 | U | 22311 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.77 | 50.88 | 72.77 |  | B - Node 0.5-1 km | 0.59 | 0.18 | Line: RELIANCE PSG001 TO BÑL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1077
2 | 78 | 1078 | 1381100178 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 178 | 14.5345 | 120.9978 | U | 4000 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 0.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.77 | 50.88 | 72.77 |  | B - Node 0.5-1 km | 0.74 | 0.06 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1078
2 | 79 | 1079 | 1907001011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Belatan Halu | 17.2561 | 122.2289 | R | 3579 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.77 | 50.87 | 72.77 |  | F - Nearest node and line over 5 km | 29.51 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1079
2 | 80 | 1080 | 1907001009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tungbangkaw | 17.2551 | 122.2297 | R | 3589 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.77 | 50.87 | 72.77 |  | F - Nearest node and line over 5 km | 29.5 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1080
2 | 81 | 1081 | 1380606017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 411 | 14.602 | 120.9945 | U | 1961 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.88 | 10.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.76 | 50.87 | 72.76 |  | A - Node within 0.5 km | 0.37 | 0.08 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1081
2 | 82 | 1082 | 1380607003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 639 | 14.5962 | 120.9922 | U | 505 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.23 | 54.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.76 | 50.87 | 72.76 |  | B - Node 0.5-1 km | 0.78 | 0.51 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1082
2 | 83 | 1083 | 1907001014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Liyaburan | 5.0735 | 119.8883 | R | 2636 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.76 | 50.86 | 72.76 |  | F - Nearest node and line over 5 km | 316.42 | 316.42 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1083
2 | 84 | 1084 | 1907001005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Luuk Buntal | 17.2556 | 122.2293 | R | 2290 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.75 | 50.86 | 72.75 |  | F - Nearest node and line over 5 km | 29.51 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1084
2 | 85 | 1085 | 1907001004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Dungon | 17.2561 | 122.2289 | R | 2240 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.75 | 50.86 | 72.75 |  | F - Nearest node and line over 5 km | 29.51 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1085
2 | 86 | 1086 | 1381600003 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Balangkas | 14.7114 | 120.9422 | U | 14522 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 1.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.75 | 50.86 | 72.75 |  | B - Node 0.5-1 km | 0.64 | 1.73 | Node: OBB001 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1086
2 | 87 | 1087 | 1381100032 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 32 | 14.5612 | 120.9968 | U | 1960 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.39 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.75 | 50.86 | 72.75 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.14 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1087
2 | 88 | 1088 | 1907001012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Karaha | 17.2555 | 122.229 | R | 1736 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.74 | 50.86 | 72.74 |  | F - Nearest node and line over 5 km | 29.47 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1088
2 | 89 | 1089 | 1907001008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Tabunan | 17.2551 | 122.2297 | R | 1387 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.74 | 50.85 | 72.74 |  | F - Nearest node and line over 5 km | 29.5 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1089
2 | 90 | 1090 | 0203121003 | Region II (Cagayan Valley) | Isabela | Palanan | Dicadyuan | 17.0098 | 122.4271 | R | 817 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.12 | 55.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.73 | 50.85 | 72.73 |  | F - Nearest node and line over 5 km | 44.12 | 55.67 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1090
2 | 91 | 1091 | 1401107003 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Ballay | 16.6789 | 120.8366 | R | 3093 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.63 | 6.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.73 | 50.84 | 72.73 |  | E - Nearest node or line 3-5 km | 4.63 | 6.43 | Node: BGB002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1091
2 | 92 | 1092 | PH0001092 | XI | Davao Del Sur | Davao City | Barangay 21-C (Pob.) | 7.1747 | 125.4649 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 1.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.7 | 50.83 | 72.7 |  | C - Line within 0.5 km; node over 1 km | 1.68 | 0.42 | Line: KITAOTAO - DAVAO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1092
2 | 93 | 1093 | 1380601216 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 215 | 14.6277 | 120.9832 | U | 3200 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.8 | 15.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.7 | 50.83 | 72.7 |  | C - Line within 0.5 km; node over 1 km | 1.06 | 0.01 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1093
2 | 94 | 1094 | 1908704002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Laguitan | 17.2541 | 122.2282 | R | 3528 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.7 | 50.82 | 72.7 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1094
2 | 95 | 1095 | PH0001095 | VIII | Leyte | Tacloban City | Barangay 8-A | 11.2089 | 124.9949 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.41 | 9.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.7 | 50.82 | 72.7 |  | D - Other node or line within 3 km | 1.63 | 1.5 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 1095
2 | 96 | 1096 | 0806008017 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Yabon | 11.6906 | 125.1073 | R | 433 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.43 | 54.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.69 | 50.82 | 72.69 |  | F - Nearest node and line over 5 km | 51.43 | 54.22 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1096
2 | 97 | 1097 | 1380606205 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 598 | 14.5962 | 121.0188 | U | 12392 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.94 | 27.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.69 | 50.82 | 72.69 |  | D - Other node or line within 3 km | 1.67 | 0.82 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1097
2 | 98 | 1098 | 0205001006 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Napo | 16.5584 | 120.9647 | R | 1642 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.45 | 17.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.66 | 50.8 | 72.66 |  | F - Nearest node and line over 5 km | 15.45 | 17.81 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1098
2 | 99 | 1099 | 0205010003 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Ansipsip | 16.3419 | 120.8209 | R | 129 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.62 | 6.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.66 | 50.79 | 72.66 |  | F - Nearest node and line over 5 km | 7.62 | 6.23 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1099
2 | 100 | 1100 | 0701243024 | Region VII (Central Visayas) | Bohol | Talibon | Sag | 10.2104 | 124.352 | R | 930 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.75 | 39.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.65 | 50.79 | 72.65 |  | F - Nearest node and line over 5 km | 39.75 | 41.94 | Node: LUC002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1100
2 | 101 | 1101 | 0806008005 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Canano | 11.6845 | 125.0882 | R | 286 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.34 | 53.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.64 | 50.79 | 72.64 |  | F - Nearest node and line over 5 km | 50.34 | 53.18 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1101
2 | 102 | 1102 | 1403206008 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Antonio Canao | 17.3501 | 121.1872 | R | 827 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.42 | 1.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.64 | 50.78 | 72.64 |  | D - Other node or line within 3 km | 10.42 | 0.81 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 1102
2 | 103 | 1103 | 1380400016 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | San Agustin | 14.6622 | 120.9525 | U | 11071 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.63 | 50.77 | 72.63 |  | B - Node 0.5-1 km | 0.51 | 0.96 | Node: MAL004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1103
2 | 104 | 1104 | 0806008004 | Region VIII (Eastern Visayas) | Samar | Hinabangan | Cabalagnan | 11.7077 | 125.099 | R | 402 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.1 | 55.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.62 | 50.77 | 72.62 |  | F - Nearest node and line over 5 km | 53.1 | 55.92 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1104
2 | 105 | 1105 | 0804819030 | Region VIII (Eastern Visayas) | Northern Samar | San Jose | Barangay West | 15.7982 | 120.9901 | R | 1055 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.29 | 43.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.62 | 50.77 | 72.62 |  | A - Node within 0.5 km | 0.47 | 0.42 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1105
2 | 106 | 1106 | 0401005068 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 21 | 13.7443 | 121.0595 | R | 698 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.42 | 5.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.61 | 50.76 | 72.61 |  | D - Other node or line within 3 km | 2.03 | 1.33 | Line: AE TO ELIMINATE COMMON 96C | Route options survey candidate: compare actual node lateral with approved line tap. | 1106
2 | 107 | 1107 | 0102901006 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Batbato | 16.913 | 120.565 | R | 577 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.16 | 10.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.59 | 50.75 | 72.59 |  | F - Nearest node and line over 5 km | 8.16 | 10.67 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1107
2 | 108 | 1108 | 1102506013 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Surop | 6.4444 | 126.1321 | R | 2719 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.96 | 48.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.59 | 50.75 | 72.59 |  | F - Nearest node and line over 5 km | 51.96 | 48.32 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1108
2 | 109 | 1109 | 1408103012 | Cordillera Administrative Region (CAR) | Apayao | Flora | Mallig | 18.1197 | 121.414 | R | 720 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.15 | 7.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.58 | 50.74 | 72.58 |  | F - Nearest node and line over 5 km | 7.15 | 17.76 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1109
2 | 110 | 1110 | 0907315015 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Mahayag | Malubo | 8.1853 | 123.4376 | R | 877 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.62 | 30.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.56 | 50.73 | 72.56 |  | F - Nearest node and line over 5 km | 30.62 | 30.48 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1110
2 | 111 | 1111 | PH0001111 | IV-B | Palawan | Puerto Princesa City | Kalipay (Pob.) | 9.6697 | 118.7055 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.33 | 4.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.56 | 50.72 | 72.56 |  | F - Nearest node and line over 5 km | 8.47 | 10.27 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1111
2 | 112 | 1112 | 1381100028 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 28 | 14.6162 | 120.9811 | U | 1272 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.56 | 50.72 | 72.56 |  | A - Node within 0.5 km | 0.2 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1112
2 | 113 | 1113 | PH0001113 | VI | Iloilo | Iloilo City | Maria Clara | 10.7429 | 122.565 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.41 | 3.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.55 | 50.72 | 72.55 |  | A - Node within 0.5 km | 0.34 | 0 | Line: 24c | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1113
2 | 114 | 1114 | 1380601173 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 173 | 14.6285 | 120.9728 | U | 1665 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47 | 45.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.54 | 50.71 | 72.54 |  | A - Node within 0.5 km | 0.19 | 0.2 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1114
2 | 115 | 1115 | 0603001025 | Region VI (Western Visayas) | Iloilo | Ajuy | Punta Buri | 11.1376 | 123.1199 | R | 1336 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.25 | 11.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.53 | 50.7 | 72.53 |  | F - Nearest node and line over 5 km | 17.25 | 11.42 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1115
2 | 116 | 1116 | 1380601001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 1 | 14.6098 | 120.9684 | U | 3086 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.14 | 10.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.53 | 50.7 | 72.53 |  | A - Node within 0.5 km | 0.36 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1116
2 | 117 | 1117 | 1380609003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 656 | 14.5903 | 120.9797 | U | 375 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.67 | 47.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.52 | 50.7 | 72.52 |  | A - Node within 0.5 km | 0.5 | 0.25 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1117
2 | 118 | 1118 | 0301412020 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Poblacion | 14.7716 | 120.9937 | R | 318 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.52 | 1.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.51 | 50.7 | 72.51 |  | D - Other node or line within 3 km | 1.46 | 2.74 | Node: MEB001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1118
2 | 119 | 1119 | 1380601126 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 126 | 14.6111 | 120.9603 | U | 1197 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.93 | 23.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.51 | 50.69 | 72.51 |  | B - Node 0.5-1 km | 0.81 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1119
2 | 120 | 1120 | 1906612067 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Southwestern Bulikullul | 17.2549 | 122.2294 | R | 897 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.41 | 1.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.51 | 50.69 | 72.51 |  | F - Nearest node and line over 5 km | 29.46 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1120
2 | 121 | 1121 | 1381200026 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santo Tomas | 14.5641 | 121.0833 | U | 13706 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.49 | 50.68 | 72.49 |  | A - Node within 0.5 km | 0.19 | 0.17 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1121
2 | 122 | 1122 | 0504107014 | Region V (Bicol Region) | Masbate | Claveria | Osmeña | 12.214 | 123.7692 | R | 3207 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.09 | 39.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.48 | 50.67 | 72.48 |  | D - Other node or line within 3 km | 2.92 | 22.95 | Node: UNM001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 1122
2 | 123 | 1123 | PH0001123 | NIR | Negros Occidental | Bacolod City | Barangay 14 (Pob.) | 10.6652 | 122.9423 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.48 | 50.67 | 72.48 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.41 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1123
2 | 124 | 1124 | PH0001124 | VIII | Leyte | Tacloban City | Barangay 46 | 11.2013 | 125.0207 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.44 | 7.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.48 | 50.67 | 72.48 |  | D - Other node or line within 3 km | 1.75 | 1.44 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 1124
2 | 125 | 1125 | 1380605012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 310 | 14.609 | 120.9908 | U | 14015 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.89 | 14.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.46 | 50.66 | 72.46 |  | B - Node 0.5-1 km | 0.65 | 0.1 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1125
2 | 126 | 1126 | PH0001126 | VI | Iloilo | Iloilo City | Nabitasan | 10.7049 | 122.5623 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 0.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.46 | 50.66 | 72.46 |  | D - Other node or line within 3 km | 1.17 | 0.59 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 1126
2 | 127 | 1127 | PH0001127 | IV-A | Laguna | San Pablo City | Barangay V-D (Pob.) | 17.4678 | 121.8405 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.46 | 50.66 | 72.46 |  | E - Nearest node or line 3-5 km | 8.29 | 4.24 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1127
2 | 128 | 1128 | 1606808009 | Region XIII (Caraga) | Surigao del Sur | Cortes | Tag-Anongan | 9.2315 | 126.1919 | R | 916 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.2 | 2.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.46 | 50.65 | 72.46 |  | D - Other node or line within 3 km | 17.2 | 2.44 | Line: Route | Route options survey candidate: compare actual node lateral with approved line tap. | 1128
2 | 129 | 1129 | 1380614101 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 818-A | 14.5804 | 121.0027 | U | 1622 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.2 | 56.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.45 | 50.65 | 72.45 |  | A - Node within 0.5 km | 0.44 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1129
2 | 130 | 1130 | 0806008020 | Region VIII (Eastern Visayas) | Samar | Hinabangan | San Jose | 11.761 | 125.2298 | R | 799 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.06 | 58.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.45 | 50.65 | 72.45 |  | F - Nearest node and line over 5 km | 63.05 | 65.55 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1130
2 | 131 | 1131 | 0102934040 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay IX | 17.5669 | 120.3868 | R | 2598 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3 | 1.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.44 | 50.65 | 72.44 |  | D - Other node or line within 3 km | 3 | 1.58 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 1131
2 | 132 | 1132 | PH0001132 | VI | Capiz | Roxas City | Poblacion III | 12.6392 | 121.4645 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.19 | 0.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.44 | 50.64 | 72.44 |  | D - Other node or line within 3 km | 10.24 | 2.22 | Line: MINDORO | Route options survey candidate: compare actual node lateral with approved line tap. | 1132
2 | 133 | 1133 | 1102501007 | Region XI (Davao Region) | Davao Oriental | Baganga | Campawan | 7.574 | 126.56 | R | 2164 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.26 | 62.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.43 | 50.64 | 72.43 |  | F - Nearest node and line over 5 km | 62.26 | 62.12 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1133
2 | 134 | 1134 | 0401033014 | Region IV-A (CALABARZON) | Batangas | Tingloy | San Pedro | 13.6571 | 120.9148 | R | 515 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.19 | 16.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.43 | 50.63 | 72.43 |  | E - Nearest node or line 3-5 km | 4.19 | 16.74 | Node: MBN002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1134
2 | 135 | 1135 | 0102934003 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay I | 17.5693 | 120.4098 | U | 400 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.56 | 2.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.42 | 50.63 | 72.42 |  | D - Other node or line within 3 km | 3.39 | 1.77 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 1135
2 | 136 | 1136 | 1908804003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Mapayag | 17.2552 | 122.2292 | R | 4141 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.41 | 50.62 | 72.41 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1136
2 | 137 | 1137 | 1102504018 | Region XI (Davao Region) | Davao Oriental | Caraga | Sobrecarey | 7.3551 | 126.3894 | U | 5177 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.24 | 48.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.41 | 50.62 | 72.41 |  | F - Nearest node and line over 5 km | 48.24 | 48.15 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1137
2 | 138 | 1138 | PH0001138 | XI | Davao Del Sur | Davao City | Barangay 3-A (Pob.) | 7.3076 | 125.4345 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.12 | 2.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.41 | 50.62 | 72.41 |  | F - Nearest node and line over 5 km | 13.7 | 7.48 | Line: KITAOTAO - DAVAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1138
2 | 139 | 1139 | PH0001139 | VIII | Leyte | Tacloban City | Barangay 8 | 11.3227 | 124.9545 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.44 | 5.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.4 | 50.62 | 72.4 |  | F - Nearest node and line over 5 km | 10.61 | 13.62 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1139
2 | 140 | 1140 | 1381100119 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 119 | 14.5476 | 121.0073 | U | 1668 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.4 | 50.62 | 72.4 |  | B - Node 0.5-1 km | 0.5 | 0.3 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1140
2 | 141 | 1141 | 1908804001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Adaon | 17.2552 | 122.2292 | R | 4333 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.39 | 50.61 | 72.39 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1141
2 | 142 | 1142 | 1908824012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Talayan | 17.2551 | 122.2291 | U | 5829 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.39 | 50.61 | 72.39 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1142
2 | 143 | 1143 | 0802617044 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Trinidad | 12.1622 | 125.368 | R | 730 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 110.04 | 112.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.39 | 50.6 | 72.39 |  | F - Nearest node and line over 5 km | 110.04 | 112.59 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1143
2 | 144 | 1144 | PH0001144 | NCR | Metro Manila | Caloocan City | Barangay 2 | 14.6086 | 120.9663 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.27 | 34.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | A - Node within 0.5 km | 0.41 | 0.3 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1144
2 | 145 | 1145 | 1908820009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Aguak | Poblacion II | 6.8654 | 124.4418 | R | 2856 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.94 | 51.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | F - Nearest node and line over 5 km | 32.2 | 32.13 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1145
2 | 146 | 1146 | 0405607024 | Region IV-A (CALABARZON) | Quezon | Calauag | Dominlog | 13.9708 | 122.2317 | R | 466 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.16 | 6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | F - Nearest node and line over 5 km | 6.16 | 5.95 | Line: WP CLQ001 TO MLQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1146
2 | 147 | 1147 | 1600305014 | Region XIII (Caraga) | Agusan del Sur | Loreto | Katipunan | 8.1853 | 125.8978 | R | 634 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.39 | 10.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | F - Nearest node and line over 5 km | 10.39 | 10.51 | Node: BWA001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1147
2 | 148 | 1148 | 1381200028 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Sumilang | 14.5566 | 121.0906 | U | 4603 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.33 | 0.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | C - Line within 0.5 km; node over 1 km | 1 | 0.14 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1148
2 | 149 | 1149 | 0203121009 | Region II (Cagayan Valley) | Isabela | Palanan | Marikit | 17.0693 | 122.4451 | R | 958 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.66 | 56.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.38 | 50.6 | 72.38 |  | F - Nearest node and line over 5 km | 45.66 | 56.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1149
2 | 150 | 1150 | 1380601062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 62 | 14.6098 | 120.9642 | U | 2027 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.96 | 11.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.37 | 50.59 | 72.37 |  | B - Node 0.5-1 km | 0.68 | 0.52 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1150
2 | 151 | 1151 | 1208001008 | Region XII (SOCCSKSARGEN) | Sarangani | Alabel | Pag-asa | 6.1229 | 125.409 | U | 8455 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.62 | 20.68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.36 | 50.59 | 72.36 |  | F - Nearest node and line over 5 km | 14.62 | 20.68 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1151
2 | 152 | 1152 | 1102501004 | Region XI (Davao Region) | Davao Oriental | Baganga | Batiano | 7.574 | 126.56 | R | 2886 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.26 | 62.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.36 | 50.59 | 72.36 |  | F - Nearest node and line over 5 km | 62.26 | 62.12 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1152
2 | 153 | 1153 | 1380606200 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 593 | 14.6055 | 121.0092 | U | 1829 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.54 | 35.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.36 | 50.59 | 72.36 |  | B - Node 0.5-1 km | 0.64 | 0.36 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1153
2 | 154 | 1154 | 1400125008 | Cordillera Administrative Region (CAR) | Abra | Tineg | Lanec | 17.7888 | 120.9153 | R | 159 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.9 | 24.56 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.35 | 50.58 | 72.35 |  | F - Nearest node and line over 5 km | 29.9 | 25.95 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1154
2 | 155 | 1155 | 1380601079 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 79 | 14.6171 | 120.9678 | U | 1566 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.9 | 36.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.35 | 50.58 | 72.35 |  | B - Node 0.5-1 km | 0.55 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1155
2 | 156 | 1156 | PH0001156 | III | Pampanga | Angeles City | Lourdes Sur | 15.153 | 120.5817 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.33 | 50.57 | 72.33 |  | D - Other node or line within 3 km | 1.12 | 1.12 | Line: ANGELES | Route options survey candidate: compare actual node lateral with approved line tap. | 1156
2 | 157 | 1157 | PH0001157 | VIII | Leyte | Tacloban City | Barangay 25 | 11.2424 | 125.0059 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.49 | 3.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.33 | 50.57 | 72.33 |  | A - Node within 0.5 km | 0.49 | 3.34 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1157
2 | 158 | 1158 | 1906615001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Bakkaan | 17.2557 | 122.2297 | R | 1845 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.33 | 50.56 | 72.33 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1158
2 | 159 | 1159 | 1400125005 | Cordillera Administrative Region (CAR) | Abra | Tineg | Belaat | 17.8079 | 120.937 | R | 239 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.87 | 26.78 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | F - Nearest node and line over 5 km | 31.87 | 27.91 | Line: SEGMENT 6 NUEVA ERA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1159
2 | 160 | 1160 | 1908704011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Sinipak | 17.2541 | 122.2282 | R | 3261 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1160
2 | 161 | 1161 | 1380603007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 387 | 14.592 | 120.9879 | U | 2735 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.01 | 7.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | A - Node within 0.5 km | 0.42 | 0.3 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1161
2 | 162 | 1162 | PH0001162 | IV-B | Palawan | Puerto Princesa City | Princesa (Pob.) | 9.9847 | 118.968 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.04 | 1.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | C - Line within 0.5 km; node over 1 km | 3.87 | 0.15 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1162
2 | 163 | 1163 | 1381100061 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 61 | 14.5507 | 121.0003 | U | 2574 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | B - Node 0.5-1 km | 0.94 | 0.23 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1163
2 | 164 | 1164 | 1380601232 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 231 | 14.6233 | 120.9824 | U | 1945 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.71 | 54.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | B - Node 0.5-1 km | 0.76 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1164
2 | 165 | 1165 | 0804824016 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Roxas | 12.3075 | 124.7039 | R | 193 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.35 | 74.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | F - Nearest node and line over 5 km | 74.35 | 74.32 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1165
2 | 166 | 1166 | 0802615012 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Patag | 11.4873 | 125.3362 | R | 373 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.64 | 46.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.31 | 50.55 | 72.31 |  | F - Nearest node and line over 5 km | 45.64 | 46.95 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1166
2 | 167 | 1167 | 0205001004 | Region II (Cagayan Valley) | Nueva Vizcaya | Ambaguio | Camandag | 16.593 | 121.0421 | R | 1574 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.71 | 15.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.3 | 50.55 | 72.3 |  | F - Nearest node and line over 5 km | 15.71 | 15.12 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1167
2 | 168 | 1168 | PH0001168 | VIII | Leyte | Tacloban City | Barangay 15 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.87 | 10.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.3 | 50.55 | 72.3 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1168
2 | 169 | 1169 | 1380606025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 419 | 14.6075 | 121.0036 | U | 1748 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.46 | 16.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.3 | 50.54 | 72.3 |  | A - Node within 0.5 km | 0.39 | 0.36 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1169
2 | 170 | 1170 | 0802619005 | Region VIII (Eastern Visayas) | Eastern Samar | Salcedo | Balud | 11.1135 | 125.6797 | R | 336 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 71.99 | 70.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.3 | 50.54 | 72.3 |  | F - Nearest node and line over 5 km | 71.99 | 73.91 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1170
2 | 171 | 1171 | 0504106032 | Region V (Bicol Region) | Masbate | Cawayan | Lague-lague | 12.0829 | 123.7365 | R | 1042 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.33 | 28.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.29 | 50.54 | 72.29 |  | F - Nearest node and line over 5 km | 17.33 | 28.96 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1171
2 | 172 | 1172 | 1102503002 | Region XI (Davao Region) | Davao Oriental | Boston | Caatihan | 7.8946 | 126.2873 | R | 1654 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.53 | 22.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.29 | 50.54 | 72.29 |  | F - Nearest node and line over 5 km | 26.53 | 22.83 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1172
2 | 173 | 1173 | 1380601071 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 71 | 14.6133 | 120.9677 | U | 3521 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.25 | 21.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.28 | 50.53 | 72.28 |  | B - Node 0.5-1 km | 0.74 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1173
2 | 174 | 1174 | 1380601070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 70 | 14.6145 | 120.9651 | U | 2415 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.46 | 50.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.28 | 50.53 | 72.28 |  | A - Node within 0.5 km | 0.46 | 0.51 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1174
2 | 175 | 1175 | PH0001175 | XI | Davao Del Sur | Davao City | Barangay 24-C (Pob.) | 7.2539 | 125.6705 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.07 | 0.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.28 | 50.53 | 72.28 |  | D - Other node or line within 3 km | 5.31 | 1.58 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 1175
2 | 176 | 1176 | 0802610002 | Region VIII (Eastern Visayas) | Eastern Samar | Hernani | Cacatmonan | 11.3101 | 125.5746 | R | 102 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.58 | 61.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.27 | 50.53 | 72.27 |  | F - Nearest node and line over 5 km | 62.58 | 62.59 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1176
2 | 177 | 1177 | 0402104009 | Region IV-A (CALABARZON) | Cavite | Carmona | Mabuhay | 14.3103 | 121.0505 | U | 13384 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.08 | 0.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.27 | 50.53 | 72.27 |  | A - Node within 0.5 km | 0.08 | 0.08 | Line: AE CRC005-BNL001-CLB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1177
2 | 178 | 1178 | PH0001178 | IV-A | Cavite | Imus City | Palico IV | 14.4281 | 120.947 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 0.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.26 | 50.52 | 72.26 |  | A - Node within 0.5 km | 0.27 | 2.01 | Node: IMC002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1178
2 | 179 | 1179 | 0506203019 | Region V (Bicol Region) | Sorsogon | Bulan | Daganas | 12.7064 | 123.9468 | R | 431 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.99 | 4.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.26 | 50.52 | 72.26 |  | E - Nearest node or line 3-5 km | 8.99 | 4.54 | Line: 30,000m | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1179
2 | 180 | 1180 | 0603002035 | Region VI (Western Visayas) | Iloilo | Alimodian | Manasa | 10.8671 | 122.3744 | R | 162 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.23 | 4.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.26 | 50.52 | 72.26 |  | F - Nearest node and line over 5 km | 17.41 | 8.11 | Line: 7,761 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1180
2 | 181 | 1181 | 1908816007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Kalbugan | 17.255 | 122.229 | R | 4943 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.25 | 50.51 | 72.25 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1181
2 | 182 | 1182 | PH0001182 | XI | Davao Del Sur | Davao City | Barangay 36-D (Pob.) | 7.5311 | 125.5093 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 1.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.25 | 50.51 | 72.25 |  | F - Nearest node and line over 5 km | 29.45 | 28.48 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1182
2 | 183 | 1183 | PH0001183 | XI | Davao Del Sur | Davao City | Barangay 33-D (Pob.) | 7.4529 | 125.5465 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.49 | 2.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.25 | 50.51 | 72.25 |  | F - Nearest node and line over 5 km | 20.83 | 20.37 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1183
2 | 184 | 1184 | 1380610033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 718 | 14.5717 | 120.9903 | U | 1190 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.89 | 7.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.25 | 50.51 | 72.25 |  | A - Node within 0.5 km | 0.42 | 0.16 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1184
2 | 185 | 1185 | 1001318021 | Region X (Northern Mindanao) | Bukidnon | San Fernando | Palacpacan | 7.7835 | 125.369 | R | 1651 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.68 | 2.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.25 | 50.51 | 72.25 |  | F - Nearest node and line over 5 km | 26.68 | 27.87 | Node: VCB003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1185
2 | 186 | 1186 | 0506211024 | Region V (Bicol Region) | Sorsogon | Magallanes | Malbog | 12.8079 | 123.895 | R | 366 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.17 | 2.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.24 | 50.5 | 72.24 |  | D - Other node or line within 3 km | 6.17 | 2.36 | Line: 30,000m | Route options survey candidate: compare actual node lateral with approved line tap. | 1186
2 | 187 | 1187 | 1381300127 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Unang Sigaw | 14.6583 | 120.9994 | U | 6781 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 1.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.24 | 50.5 | 72.24 |  | D - Other node or line within 3 km | 1.15 | 1.3 | Node: CCS005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1187
2 | 188 | 1188 | 0501730024 | Region V (Bicol Region) | Camarines Sur | Ragay | Lower Santa Cruz | 13.8166 | 122.7976 | R | 1448 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.23 | 50.5 | 72.23 |  | C - Line within 0.5 km; node over 1 km | 1 | 0.09 | Line: CALAUAG - SIPOCOT | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1188
2 | 189 | 1189 | 0804816012 | Region VIII (Eastern Visayas) | Northern Samar | Rosario | Kailingan | 12.5036 | 124.4485 | R | 341 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.41 | 39.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.23 | 50.5 | 72.23 |  | F - Nearest node and line over 5 km | 40.41 | 39.78 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1189
2 | 190 | 1190 | PH0001190 | BARMM (LaMa+SGA) | North Cotabato | Kabacan | Simbuhay | 7.2153 | 124.8672 | R | 4702 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.89 | 7.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.23 | 50.5 | 72.23 |  | F - Nearest node and line over 5 km | 7.89 | 7.89 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1190
2 | 191 | 1191 | 1380610043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 728 | 14.569 | 120.9879 | U | 866 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.22 | 44.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.22 | 50.49 | 72.22 |  | B - Node 0.5-1 km | 0.76 | 0.43 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1191
2 | 192 | 1192 | 1380601131 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 131 | 14.6275 | 120.9691 | U | 1670 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.4 | 28.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.21 | 50.48 | 72.21 |  | A - Node within 0.5 km | 0.46 | 0.37 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1192
2 | 193 | 1193 | 1400102006 | Cordillera Administrative Region (CAR) | Abra | Boliney | Kilong-Olao | 17.3742 | 120.8658 | R | 273 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.84 | 28.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.2 | 50.48 | 72.2 |  | F - Nearest node and line over 5 km | 29.84 | 28.74 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1193
2 | 194 | 1194 | 1908704006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Nalkan | 6.9879 | 123.9872 | R | 5106 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.72 | 82.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.2 | 50.47 | 72.2 |  | F - Nearest node and line over 5 km | 82.72 | 82.66 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1194
2 | 195 | 1195 | 1606818017 | Region XIII (Caraga) | Surigao del Sur | Tago | Mercedes | 9.0176 | 126.2227 | R | 334 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.16 | 2.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.19 | 50.46 | 72.19 |  | D - Other node or line within 3 km | 7.16 | 2.35 | Line: Route | Route options survey candidate: compare actual node lateral with approved line tap. | 1195
2 | 196 | 1196 | PH0001196 | I | Ilocos Norte | Laoag City | Bgy. No. 10, San Jose (Pob.) | 18.1755 | 120.5644 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.27 | 0.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.18 | 50.46 | 72.18 |  | D - Other node or line within 3 km | 3.11 | 2.77 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Route options survey candidate: compare actual node lateral with approved line tap. | 1196
2 | 197 | 1197 | 1380606206 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 599 | 14.595 | 121.0167 | U | 4402 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.97 | 9.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.17 | 50.46 | 72.17 |  | D - Other node or line within 3 km | 1.52 | 0.88 | Line: UG 288C via V-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1197
2 | 198 | 1198 | 1381100142 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 142 | 14.5484 | 121.0055 | U | 327 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.72 | 0.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.17 | 50.45 | 72.17 |  | B - Node 0.5-1 km | 0.65 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1198
2 | 199 | 1199 | PH0001199 | XI | Davao Del Sur | Davao City | Barangay 32-D (Pob.) | 7.2539 | 125.6705 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.16 | 50.45 | 72.16 |  | D - Other node or line within 3 km | 5.31 | 1.58 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 1199
2 | 200 | 1200 | 1380606208 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 601 | 14.5973 | 121.0172 | U | 7995 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.59 | 58.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.16 | 50.45 | 72.16 |  | D - Other node or line within 3 km | 1.46 | 0.65 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1200
2 | 201 | 1201 | 1908706002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Buterin | 17.254 | 122.2279 | R | 3136 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.14 | 50.43 | 72.14 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1201
2 | 202 | 1202 | 1380603014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 394 | 14.6006 | 120.9839 | U | 1477 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.04 | 12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.12 | 50.42 | 72.12 |  | B - Node 0.5-1 km | 0.84 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1202
2 | 203 | 1203 | 0804807010 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Dao | 12.4025 | 125.3227 | R | 1026 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 133.92 | 133.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.11 | 50.41 | 72.11 |  | F - Nearest node and line over 5 km | 133.92 | 133.94 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1203
2 | 204 | 1204 | 0504101022 | Region V (Bicol Region) | Masbate | Aroroy | Manamoc | 12.3499 | 123.4421 | R | 1119 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.84 | 9.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.1 | 50.41 | 72.1 |  | F - Nearest node and line over 5 km | 14.84 | 13.31 | Line: AERIAL FOC 96_CORE - 11,192 METERS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1204
2 | 205 | 1205 | 0802615010 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Maytigbao | 11.4729 | 125.4691 | R | 232 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.11 | 57.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.1 | 50.41 | 72.1 |  | F - Nearest node and line over 5 km | 57.11 | 57.89 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1205
2 | 206 | 1206 | PH0001206 | V | Camarines Sur | Naga City | Dinaga | 7.8487 | 122.6795 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.77 | 1.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.1 | 50.41 | 72.1 |  | E - Nearest node or line 3-5 km | 13.04 | 4.33 | Line: BUUG - IPIL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1206
2 | 207 | 1207 | 1380601165 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 165 | 14.6263 | 120.974 | U | 1045 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.37 | 30.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.1 | 50.4 | 72.1 |  | A - Node within 0.5 km | 0.1 | 0.03 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1207
2 | 208 | 1208 | 0802615008 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Malobago | 11.5024 | 125.4196 | R | 499 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.05 | 54.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.1 | 50.4 | 72.1 |  | F - Nearest node and line over 5 km | 54.05 | 55.13 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1208
2 | 209 | 1209 | 0804805021 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Gebalagnan | 12.3769 | 124.6814 | R | 427 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.15 | 68.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.09 | 50.4 | 72.09 |  | F - Nearest node and line over 5 km | 69.15 | 68.68 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1209
2 | 210 | 1210 | 1906619003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Omar | Capual Island | 17.2555 | 122.2296 | U | 8706 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.09 | 50.4 | 72.09 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1210
2 | 211 | 1211 | 0405801009 | Region IV-A (CALABARZON) | Rizal | Angono | San Isidro | 14.5295 | 121.1543 | U | 32767 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.23 | 0.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.08 | 50.39 | 72.08 |  | A - Node within 0.5 km | 0.23 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1211
2 | 212 | 1212 | 1208001011 | Region XII (SOCCSKSARGEN) | Sarangani | Alabel | Spring | 6.076 | 125.3154 | U | 5630 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.24 | 14.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.07 | 50.38 | 72.07 |  | F - Nearest node and line over 5 km | 5.24 | 13.99 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1212
2 | 213 | 1213 | 1381100098 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 98 | 14.5408 | 121.0024 | U | 1529 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.06 | 50.38 | 72.06 |  | B - Node 0.5-1 km | 0.95 | 0.22 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1213
2 | 214 | 1214 | 1381100036 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 36 | 14.5618 | 120.9945 | U | 3907 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.6 | 0.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.06 | 50.38 | 72.06 |  | B - Node 0.5-1 km | 1 | 0.07 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1214
2 | 215 | 1215 | 1380604003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 270 | 14.6222 | 120.9817 | U | 946 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.9 | 42.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.06 | 50.38 | 72.06 |  | B - Node 0.5-1 km | 0.65 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1215
2 | 216 | 1216 | 1908822009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Pilar | 17.2551 | 122.2291 | U | 6086 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.06 | 50.38 | 72.06 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1216
2 | 217 | 1217 | 1380601147 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 147 | 14.6288 | 120.9679 | U | 2344 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.3 | 52.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.05 | 50.37 | 72.05 |  | B - Node 0.5-1 km | 0.62 | 0.54 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1217
2 | 218 | 1218 | PH0001218 | III | Pampanga | Angeles City | Agapito del Rosario | 15.1488 | 120.5916 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.05 | 50.37 | 72.05 |  | A - Node within 0.5 km | 0.31 | 0.18 | Line: ANGELES | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1218
2 | 219 | 1219 | PH0001219 | VIII | Leyte | Tacloban City | Barangay 33 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.39 | 3.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.05 | 50.37 | 72.05 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1219
2 | 220 | 1220 | 1380607007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 643 | 14.596 | 120.9931 | U | 677 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.92 | 19.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.05 | 50.37 | 72.05 |  | B - Node 0.5-1 km | 0.82 | 0.55 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1220
2 | 221 | 1221 | 0500510007 | Region V (Bicol Region) | Albay | Malinao | Bulang | 13.361 | 123.6243 | R | 1018 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 4.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.04 | 50.36 | 72.04 |  | E - Nearest node or line 3-5 km | 4.65 | 4.49 | Line: TABACO - LIGAO AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1221
2 | 222 | 1222 | 0802609057 | Region VIII (Eastern Visayas) | Eastern Samar | Guiuan | Victory Island | 11.0413 | 125.6949 | R | 592 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74 | 71.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.03 | 50.36 | 72.03 |  | F - Nearest node and line over 5 km | 74 | 77.07 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1222
2 | 223 | 1223 | 0504113010 | Region V (Bicol Region) | Masbate | Mobo | Lomocloc | 12.2537 | 123.6229 | R | 652 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.02 | 8.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.03 | 50.36 | 72.03 |  | F - Nearest node and line over 5 km | 10.02 | 8.64 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1223
2 | 224 | 1224 | 0802605028 | Region VIII (Eastern Visayas) | Eastern Samar | Can-Avid | Salvacion | 11.9706 | 125.3111 | R | 468 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 87.97 | 90.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.03 | 50.35 | 72.03 |  | F - Nearest node and line over 5 km | 87.97 | 90.48 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1224
2 | 225 | 1225 | 0603015011 | Region VI (Western Visayas) | Iloilo | Concepcion | Igbon | 11.215 | 123.1885 | R | 2503 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.24 | 12.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.03 | 50.35 | 72.03 |  | F - Nearest node and line over 5 km | 19.24 | 12.13 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1225
2 | 226 | 1226 | 0802614012 | Region VIII (Eastern Visayas) | Eastern Samar | Maslog | Tangbo | 12.1429 | 125.2659 | R | 204 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.46 | 107.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.02 | 50.35 | 72.02 |  | F - Nearest node and line over 5 km | 104.46 | 107.16 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1226
2 | 227 | 1227 | 1908704005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Meti | 17.2541 | 122.2282 | R | 4330 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.02 | 50.35 | 72.02 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1227
2 | 228 | 1228 | 1380606003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 397 | 14.6016 | 120.9869 | U | 4302 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.11 | 15.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.02 | 50.35 | 72.02 |  | A - Node within 0.5 km | 0.5 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1228
2 | 229 | 1229 | PH0001229 | XI | Davao Del Sur | Davao City | Barangay 35-D (Pob.) | 7.2617 | 125.6488 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 3.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.01 | 50.34 | 72.01 |  | C - Line within 0.5 km; node over 1 km | 5.55 | 0.48 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1229
2 | 230 | 1230 | 0704622003 | Region VII (Central Visayas) | Negros Oriental | Tayasan | Banga | 9.9398 | 123.1413 | R | 976 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.09 | 3.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72.01 | 50.34 | 72.01 |  | F - Nearest node and line over 5 km | 24.09 | 12.28 | Line: OPENTRENCHING (505m) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1230
2 | 231 | 1231 | 1906614014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kalang | 17.2557 | 122.2297 | R | 3332 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 72 | 50.33 | 72 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1231
2 | 232 | 1232 | 1705321004 | MIMAROPA Region | Palawan | Kalayaan | Pag-Asa | 9.4482 | 118.3879 | R | 228 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.94 | 52.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.99 | 50.33 | 71.99 |  | F - Nearest node and line over 5 km | 49.94 | 51.95 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1232
2 | 233 | 1233 | 1408104009 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Kumao | 18.1027 | 121.1568 | R | 585 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.59 | 16.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.99 | 50.33 | 71.99 |  | F - Nearest node and line over 5 km | 9.59 | 38.19 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1233
2 | 234 | 1234 | 1102501015 | Region XI (Davao Region) | Davao Oriental | Baganga | San Isidro | 7.574 | 126.5601 | R | 2186 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.27 | 62.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.99 | 50.33 | 71.99 |  | F - Nearest node and line over 5 km | 62.27 | 62.14 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1234
2 | 235 | 1235 | PH0001235 | VIII | Leyte | Tacloban City | Barangay 42 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.28 | 6.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1235
2 | 236 | 1236 | 1102401002 | Region XI (Davao Region) | Davao del Sur | Bansalan | Alta Vista | 6.7834 | 125.1933 | R | 1049 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.54 | 16.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | D - Other node or line within 3 km | 1.86 | 18.94 | Node: BND001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 1236
2 | 237 | 1237 | 1907010005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Dalo-dalo | 17.2558 | 122.2298 | R | 1679 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1237
2 | 238 | 1238 | 1908709007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Guiday T. Biruar | 17.254 | 122.228 | R | 8250 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | F - Nearest node and line over 5 km | 29.28 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1238
2 | 239 | 1239 | 1907010015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tapian Bohe North | 17.2558 | 122.2299 | R | 1108 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1239
2 | 240 | 1240 | 1380610024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 709 | 14.5686 | 120.9906 | U | 4280 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.79 | 56.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.98 | 50.32 | 71.98 |  | B - Node 0.5-1 km | 0.55 | 0.18 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1240
2 | 241 | 1241 | 0401005069 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 22 | 13.7109 | 121.0927 | U | 97 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.36 | 4.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.97 | 50.32 | 71.97 |  | E - Nearest node or line 3-5 km | 4.14 | 6.02 | Node: BCY004 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1241
2 | 242 | 1242 | 1906612041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | North Silumpak | 17.2561 | 122.2293 | R | 740 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.16 | 2.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.97 | 50.32 | 71.97 |  | F - Nearest node and line over 5 km | 29.54 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1242
2 | 243 | 1243 | 0500511007 | Region V (Bicol Region) | Albay | Manito | Cawayan | 13.0584 | 123.8214 | R | 1873 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.93 | 8.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.97 | 50.32 | 71.97 |  | F - Nearest node and line over 5 km | 8.93 | 8.01 | Line: FOC-7,512m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1243
2 | 244 | 1244 | 0806002052 | Region VIII (Eastern Visayas) | Samar | Basey | Bulao | 11.3383 | 125.1028 | R | 1340 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.5 | 17.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.97 | 50.32 | 71.97 |  | F - Nearest node and line over 5 km | 15.5 | 17.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1244
2 | 245 | 1245 | 0203121017 | Region II (Cagayan Valley) | Isabela | Palanan | San Isidro | 17.134 | 122.5081 | R | 894 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.59 | 62.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.31 | 71.96 |  | F - Nearest node and line over 5 km | 52.59 | 62.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1245
2 | 246 | 1246 | 1380601010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 10 | 14.6083 | 120.9681 | U | 165 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.32 | 7.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.31 | 71.96 |  | A - Node within 0.5 km | 0.23 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1246
2 | 247 | 1247 | 0600614007 | Region VI (Western Visayas) | Antique | San Remigio | Banbanan | 10.966 | 122.1903 | R | 282 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.29 | 28.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.31 | 71.96 |  | F - Nearest node and line over 5 km | 35.29 | 28.12 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1247
2 | 248 | 1248 | 1380601174 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 174 | 14.6267 | 120.9725 | U | 737 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.91 | 40.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.31 | 71.96 |  | A - Node within 0.5 km | 0.09 | 0 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1248
2 | 249 | 1249 | PH0001249 | VI | Iloilo | Iloilo City | Concepcion-Montes | 10.6833 | 122.5304 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.97 | 10.05 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.31 | 71.96 |  | D - Other node or line within 3 km | 1.57 | 3.66 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1249
2 | 250 | 1250 | 1606710006 | Region XIII (Caraga) | Surigao del Norte | General Luna | Daku | 9.7419 | 126.1571 | R | 536 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.45 | 39.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.3 | 71.96 |  | F - Nearest node and line over 5 km | 47.45 | 39.83 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1250
2 | 251 | 1251 | 1380612021 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 853 | 14.5902 | 121.004 | U | 520 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.67 | 32.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.3 | 71.96 |  | B - Node 0.5-1 km | 0.66 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1251
2 | 252 | 1252 | 0804824012 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Maghipid | 12.3286 | 124.6073 | R | 458 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.88 | 63.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.96 | 50.3 | 71.96 |  | F - Nearest node and line over 5 km | 63.88 | 63.85 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1252
2 | 253 | 1253 | 0804824021 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Somoroy | 12.3202 | 124.725 | R | 166 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.86 | 75.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | F - Nearest node and line over 5 km | 75.86 | 75.83 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1253
2 | 254 | 1254 | 1381100015 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 15 | 14.5603 | 120.992 | U | 2394 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.21 | 0.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | B - Node 0.5-1 km | 0.78 | 0.37 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1254
2 | 255 | 1255 | 0806012011 | Region VIII (Eastern Visayas) | Samar | Motiong | Canvais | 11.9649 | 125.0462 | R | 303 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.79 | 83.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | F - Nearest node and line over 5 km | 80.79 | 83.44 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1255
2 | 256 | 1256 | 0403403005 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Casile | 14.3426 | 121.0895 | R | 4648 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | D - Other node or line within 3 km | 1.55 | 0.57 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 1256
2 | 257 | 1257 | 0203111011 | Region II (Cagayan Valley) | Isabela | Divilacan | Dipudo | 17.3293 | 122.2969 | R | 324 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.58 | 44.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | F - Nearest node and line over 5 km | 40.3 | 43.98 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1257
2 | 258 | 1258 | 1380601189 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 189 | 14.6341 | 120.9796 | U | 1526 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.33 | 5.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.95 | 50.3 | 71.95 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.19 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1258
2 | 259 | 1259 | 1400121013 | Cordillera Administrative Region (CAR) | Abra | San Isidro | Tangbao | 17.4432 | 120.5941 | R | 650 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.26 | 10.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.93 | 50.29 | 71.93 |  | F - Nearest node and line over 5 km | 7.26 | 10.56 | Node: NKI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1259
2 | 260 | 1260 | PH0001260 | VIII | Leyte | Tacloban City | Barangay 22 | 11.2715 | 124.9509 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.65 | 9.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.93 | 50.29 | 71.93 |  | F - Nearest node and line over 5 km | 6.65 | 9.14 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1260
2 | 261 | 1261 | 0405603028 | Region IV-A (CALABARZON) | Quezon | Atimonan | Montes Kallagan | 13.9526 | 121.8653 | R | 221 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 1.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.93 | 50.29 | 71.93 |  | E - Nearest node or line 3-5 km | 6.72 | 4.08 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1261
2 | 262 | 1262 | 1380610061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 736 | 14.5658 | 121.0061 | U | 3922 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.33 | 58.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.93 | 50.29 | 71.93 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.23 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1262
2 | 263 | 1263 | 1380601171 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 171 | 14.6303 | 120.9741 | U | 1158 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.7 | 11.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.93 | 50.29 | 71.93 |  | A - Node within 0.5 km | 0.39 | 0.41 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1263
2 | 264 | 1264 | PH0001264 | VIII | Leyte | Tacloban City | Barangay 5-A | 11.3189 | 124.9422 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 2.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.92 | 50.28 | 71.92 |  | F - Nearest node and line over 5 km | 11 | 13.91 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1264
2 | 265 | 1265 | 0603015008 | Region VI (Western Visayas) | Iloilo | Concepcion | Botlog | 11.2294 | 123.1554 | R | 464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.38 | 8.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.92 | 50.28 | 71.92 |  | F - Nearest node and line over 5 km | 15.38 | 8.22 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1265
2 | 266 | 1266 | 0102934005 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay III | 17.5752 | 120.3857 | U | 1150 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.1 | 0.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.92 | 50.28 | 71.92 |  | D - Other node or line within 3 km | 2.1 | 0.77 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 1266
2 | 267 | 1267 | 1381200025 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Rosa | 14.5744 | 121.0956 | U | 1078 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.9 | 50.27 | 71.9 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1267
2 | 268 | 1268 | 0506212021 | Region V (Bicol Region) | Sorsogon | Matnog | Genablan Oriental | 12.5394 | 124.0354 | R | 1116 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.23 | 7.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.9 | 50.26 | 71.9 |  | F - Nearest node and line over 5 km | 7.23 | 7.23 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1268
2 | 269 | 1269 | 0600614011 | Region VI (Western Visayas) | Antique | San Remigio | Bulan-bulan | 10.8894 | 122.181 | R | 727 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.07 | 22.95 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.9 | 50.26 | 71.9 |  | F - Nearest node and line over 5 km | 30.07 | 22.84 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1269
2 | 270 | 1270 | 0502004018 | Region V (Bicol Region) | Catanduanes | Caramoran | Maysuran | 13.9796 | 124.163 | R | 1099 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.59 | 77.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | F - Nearest node and line over 5 km | 39.59 | 77.74 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1270
2 | 271 | 1271 | 0405805017 | Region IV-A (CALABARZON) | Rizal | Cainta | San Roque | 14.5763 | 121.1173 | U | 9850 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.04 | 0.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1271
2 | 272 | 1272 | 0504113004 | Region V (Bicol Region) | Masbate | Mobo | Barag | 12.2157 | 123.6476 | R | 526 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.13 | 12.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | F - Nearest node and line over 5 km | 12.13 | 12.99 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1272
2 | 273 | 1273 | 0802615004 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Canloterio | 11.4759 | 125.4032 | R | 506 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.99 | 51.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | F - Nearest node and line over 5 km | 50.99 | 51.98 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1273
2 | 274 | 1274 | 1908704008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Pura | 17.2541 | 122.2282 | R | 5430 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1274
2 | 275 | 1275 | 0506212001 | Region V (Bicol Region) | Sorsogon | Matnog | Balocawe | 12.5998 | 124.0661 | R | 1026 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 0.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.89 | 50.26 | 71.89 |  | C - Line within 0.5 km; node over 1 km | 2.25 | 0.49 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1275
2 | 276 | 1276 | 0804802004 | Region VIII (Eastern Visayas) | Northern Samar | Biri | Kauswagan | 12.6709 | 124.3914 | R | 772 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 28.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.88 | 50.25 | 71.88 |  | F - Nearest node and line over 5 km | 29.43 | 29.92 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1276
2 | 277 | 1277 | 0501610010 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Villa San Isidro | 14.1683 | 122.2155 | R | 268 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.49 | 17.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.88 | 50.25 | 71.88 |  | F - Nearest node and line over 5 km | 6.49 | 17.73 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1277
2 | 278 | 1278 | 1380610063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 734 | 14.5682 | 121.0056 | U | 929 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.46 | 25.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.88 | 50.25 | 71.88 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1278
2 | 279 | 1279 | 1381100152 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 152 | 14.5357 | 121.0066 | U | 1254 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 0.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.88 | 50.25 | 71.88 |  | C - Line within 0.5 km; node over 1 km | 1.34 | 0.33 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1279
2 | 280 | 1280 | PH0001280 | VIII | Samar (Western Samar) | Calbayog City | Manuel Barral, Sr. | 12.2236 | 124.4938 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.25 | 60.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.88 | 50.25 | 71.88 |  | F - Nearest node and line over 5 km | 60.25 | 60.22 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1280
2 | 281 | 1281 | PH0001281 | V | Camarines Sur | Naga City | San Francisco (Pob.) | 10.23 | 123.7005 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.77 | 1.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.87 | 50.25 | 71.87 |  | D - Other node or line within 3 km | 3.04 | 2.35 | Line: CEBU - TOLEDO | Route options survey candidate: compare actual node lateral with approved line tap. | 1281
2 | 282 | 1282 | 1381200018 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Sagad | 14.5661 | 121.0796 | U | 6411 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.87 | 50.24 | 71.87 |  | B - Node 0.5-1 km | 0.62 | 0.08 | Line: Aerial 216C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1282
2 | 283 | 1283 | 0501610012 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Guitol | 14.1043 | 122.4067 | R | 378 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5 | 2.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.87 | 50.24 | 71.87 |  | D - Other node or line within 3 km | 5 | 2.7 | Line: PAGBILAO - NAGA (UG + Aerial) | Route options survey candidate: compare actual node lateral with approved line tap. | 1283
2 | 284 | 1284 | 1108601015 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | West Lamidan | 6.0923 | 125.6551 | R | 3216 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.72 | 47.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.87 | 50.24 | 71.87 |  | F - Nearest node and line over 5 km | 41.72 | 47.01 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1284
2 | 285 | 1285 | 1004206006 | Region X (Northern Mindanao) | Misamis Occidental | Concepcion | Lingatongan | 11.2004 | 123.1623 | R | 246 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.2 | 43.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.86 | 50.24 | 71.86 |  | F - Nearest node and line over 5 km | 16.99 | 10.88 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1285
2 | 286 | 1286 | 1400125009 | Cordillera Administrative Region (CAR) | Abra | Tineg | Lapat-Balantay | 17.764 | 120.9286 | R | 389 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30 | 26.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.86 | 50.24 | 71.86 |  | F - Nearest node and line over 5 km | 30 | 27.42 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1286
2 | 287 | 1287 | 1705101010 | MIMAROPA Region | Occidental Mindoro | Abra De Ilog | Santa Maria | 13.4884 | 120.6768 | R | 2156 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.29 | 21.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.86 | 50.24 | 71.86 |  | F - Nearest node and line over 5 km | 24.83 | 22.82 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1287
2 | 288 | 1288 | PH0001288 | VIII | Samar (Western Samar) | Calbayog City | Longsob | 12.1554 | 124.5263 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.04 | 68.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.86 | 50.24 | 71.86 |  | F - Nearest node and line over 5 km | 68.04 | 68.01 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1288
2 | 289 | 1289 | 0504120006 | Region V (Bicol Region) | Masbate | San Pascual | Iniwaran | 13.1534 | 122.8733 | R | 2365 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.86 | 42.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.86 | 50.23 | 71.86 |  | F - Nearest node and line over 5 km | 20.86 | 42.66 | Node: SDQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1289
2 | 290 | 1290 | 0102908010 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Pilipil | 16.9396 | 120.7574 | R | 502 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.22 | 0.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.85 | 50.23 | 71.85 |  | C - Line within 0.5 km; node over 1 km | 6.22 | 0.14 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1290
2 | 291 | 1291 | 0102934007 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay V | 17.5761 | 120.3864 | U | 706 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.34 | 2.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.85 | 50.23 | 71.85 |  | D - Other node or line within 3 km | 1.99 | 0.65 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 1291
2 | 292 | 1292 | 1108601013 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Mabuhay | 6.2348 | 125.6912 | R | 2305 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.91 | 47.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.85 | 50.23 | 71.85 |  | F - Nearest node and line over 5 km | 47.91 | 47.16 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1292
2 | 293 | 1293 | 1380611017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 683 | 14.581 | 120.9956 | U | 808 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.98 | 48.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.85 | 50.23 | 71.85 |  | B - Node 0.5-1 km | 0.86 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1293
2 | 294 | 1294 | 0401033016 | Region IV-A (CALABARZON) | Batangas | Tingloy | Talahib | 13.6568 | 120.9085 | R | 1100 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.9 | 16.72 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.85 | 50.23 | 71.85 |  | E - Nearest node or line 3-5 km | 3.9 | 16.71 | Node: MBN002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1294
2 | 295 | 1295 | 0907315018 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Mahayag | Paraiso | 8.2225 | 123.4132 | R | 912 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.55 | 35.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.84 | 50.22 | 71.84 |  | F - Nearest node and line over 5 km | 35.55 | 35.4 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1295
2 | 296 | 1296 | 1102506009 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Oregon | 6.556 | 126.1246 | R | 1214 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.82 | 35.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.84 | 50.22 | 71.84 |  | F - Nearest node and line over 5 km | 39.82 | 35.89 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1296
2 | 297 | 1297 | 0806017037 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Gumamela Pob. | 11.4633 | 124.9799 | R | 1311 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.99 | 28.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.84 | 50.22 | 71.84 |  | F - Nearest node and line over 5 km | 24.99 | 28.06 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1297
2 | 298 | 1298 | 1004217010 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Petianan | 8.3051 | 123.5807 | R | 871 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.38 | 32.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.84 | 50.22 | 71.84 |  | F - Nearest node and line over 5 km | 37.78 | 36.08 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1298
2 | 299 | 1299 | 1908706013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Payan | 17.2538 | 122.2291 | R | 1470 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.38 | 14.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.83 | 50.22 | 71.83 |  | F - Nearest node and line over 5 km | 29.36 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1299
2 | 300 | 1300 | 0600618001 | Region VI (Western Visayas) | Antique | Valderrama | Bakiang | 11.0907 | 122.1801 | R | 580 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.77 | 38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 39.77 | 37.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1300
2 | 301 | 1301 | 1004217001 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Bagong Clarin | 8.1537 | 123.5665 | R | 750 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.44 | 33.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 22.47 | 22.4 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1301
2 | 302 | 1302 | 0804824005 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Curry | 12.3284 | 124.678 | R | 892 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.82 | 70.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 70.82 | 70.79 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1302
2 | 303 | 1303 | 0907313010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Linokmadalum | 7.6576 | 123.1454 | R | 918 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.21 | 11.47 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 12.79 | 10.45 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1303
2 | 304 | 1304 | 0804808020 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Candawid | 12.6417 | 125.0585 | R | 776 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 101.01 | 99.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 101.01 | 102.26 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1304
2 | 305 | 1305 | 0201521026 | Region II (Cagayan Valley) | Cagayan | Rizal | Battut | 8.5723 | 117.2641 | R | 523 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 8.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 207.12 | 209.13 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1305
2 | 306 | 1306 | 0804822013 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Giguimitan | 12.3063 | 124.7993 | R | 423 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.92 | 83.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.82 | 50.21 | 71.82 |  | F - Nearest node and line over 5 km | 83.92 | 83.66 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1306
2 | 307 | 1307 | 0804807016 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Malidong | 12.3766 | 125.23 | R | 532 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 125.65 | 124.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.81 | 50.21 | 71.81 |  | F - Nearest node and line over 5 km | 125.65 | 124.79 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1307
2 | 308 | 1308 | 0501602017 | Region V (Bicol Region) | Camarines Norte | Capalonga | San Isidro | 14.3349 | 122.5327 | R | 215 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.99 | 16.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.81 | 50.2 | 71.81 |  | F - Nearest node and line over 5 km | 11.99 | 16.4 | Node: CCA001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1308
2 | 309 | 1309 | 1404406006 | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | Bunot | 17.1956 | 121.3406 | R | 1658 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.26 | 21.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.81 | 50.2 | 71.81 |  | F - Nearest node and line over 5 km | 7.26 | 21.19 | Node: PSV001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1309
2 | 310 | 1310 | 0806023027 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Talib | 11.6706 | 124.8891 | R | 241 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.63 | 46.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.8 | 50.2 | 71.8 |  | F - Nearest node and line over 5 km | 46.63 | 46.53 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1310
2 | 311 | 1311 | 1903601019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Orong | 17.2539 | 122.2282 | R | 1032 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.8 | 50.19 | 71.8 |  | F - Nearest node and line over 5 km | 29.29 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1311
2 | 312 | 1312 | 1903601015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Liawao | 17.2541 | 122.2288 | R | 501 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.8 | 50.19 | 71.8 |  | F - Nearest node and line over 5 km | 29.35 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1312
2 | 313 | 1313 | 0401005062 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 16 | 13.7603 | 121.0613 | U | 104 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.64 | 4.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.79 | 50.19 | 71.79 |  | B - Node 0.5-1 km | 0.53 | 0.21 | Line: UG SSB001 TO BCY001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1313
2 | 314 | 1314 | 1705304021 | MIMAROPA Region | Palawan | Balabac | Salang | 8.057 | 117.0659 | R | 3223 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 261.93 | 264.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.79 | 50.19 | 71.79 |  | F - Nearest node and line over 5 km | 261.93 | 263.94 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1314
2 | 315 | 1315 | 0402106022 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima I | 14.3083 | 120.9485 | U | 7140 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.27 | 1.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.78 | 50.18 | 71.78 |  | D - Other node or line within 3 km | 1.43 | 0.87 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 1315
2 | 316 | 1316 | 1705304020 | MIMAROPA Region | Palawan | Balabac | Ramos | 8.1196 | 117.0208 | R | 3097 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 260.54 | 262.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.78 | 50.18 | 71.78 |  | F - Nearest node and line over 5 km | 260.54 | 262.55 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1316
2 | 317 | 1317 | 0804805053 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Tinowaran | 12.4394 | 124.6605 | R | 566 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.43 | 63.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.77 | 50.17 | 71.77 |  | F - Nearest node and line over 5 km | 64.43 | 63.74 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1317
2 | 318 | 1318 | 1381300070 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Novaliches Proper | 14.7186 | 121.035 | U | 16117 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.83 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.77 | 50.17 | 71.77 |  | B - Node 0.5-1 km | 0.83 | 0.35 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1318
2 | 319 | 1319 | 1381100051 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 51 | 14.552 | 121.0025 | U | 2220 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.79 | 1.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.76 | 50.17 | 71.76 |  | B - Node 0.5-1 km | 0.99 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1319
2 | 320 | 1320 | 0506215012 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Rafael | 12.6636 | 124.1285 | R | 1362 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.18 | 1.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.76 | 50.17 | 71.76 |  | D - Other node or line within 3 km | 3.18 | 1.67 | Line: STA MAGDALENA CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 1320
2 | 321 | 1321 | 1908822008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Pandan | 17.2551 | 122.2291 | R | 5222 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.76 | 50.17 | 71.76 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1321
2 | 322 | 1322 | 0600614021 | Region VI (Western Visayas) | Antique | San Remigio | General Luna | 10.8685 | 122.0835 | R | 830 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.8 | 12.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.76 | 50.16 | 71.76 |  | F - Nearest node and line over 5 km | 19.8 | 12.31 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1322
2 | 323 | 1323 | 0802617002 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Bagacay | 12.0774 | 125.4335 | R | 234 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.32 | 106.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | F - Nearest node and line over 5 km | 104.32 | 106.69 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1323
2 | 324 | 1324 | PH0001324 | VIII | Leyte | Tacloban City | Barangay 45 | 11.2169 | 125.0033 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.81 | 11.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | B - Node 0.5-1 km | 0.83 | 0.81 | Line: CAPOOCAN - TACLOBAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1324
2 | 325 | 1325 | 0806017014 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Igang-igang | 11.4655 | 124.8615 | R | 718 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.3 | 25.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | F - Nearest node and line over 5 km | 26.3 | 25.25 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1325
2 | 326 | 1326 | 1381100043 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 43 | 14.5554 | 120.9961 | U | 2694 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.34 | 0.09 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | B - Node 0.5-1 km | 0.53 | 0.07 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1326
2 | 327 | 1327 | 1906612007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Bulihkullul | 17.2555 | 122.2295 | R | 1038 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1327
2 | 328 | 1328 | 0804824002 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Bonifacio | 12.2735 | 124.6083 | R | 867 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.94 | 66.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | F - Nearest node and line over 5 km | 66.94 | 66.91 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1328
2 | 329 | 1329 | 0806012013 | Region VIII (Eastern Visayas) | Samar | Motiong | Candomacol | 11.8266 | 125.0222 | R | 392 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.3 | 68.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.75 | 50.16 | 71.75 |  | F - Nearest node and line over 5 km | 65.3 | 68.29 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1329
2 | 330 | 1330 | 1381300067 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Milagrosa | 14.6218 | 121.0682 | U | 7059 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.16 | 71.74 |  | B - Node 0.5-1 km | 0.53 | 0.09 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1330
2 | 331 | 1331 | 0806023005 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Botaera | 11.6681 | 124.841 | R | 660 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.16 | 44.1 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.16 | 71.74 |  | F - Nearest node and line over 5 km | 44.16 | 44.1 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1331
2 | 332 | 1332 | 0201521022 | Region II (Cagayan Valley) | Cagayan | Rizal | Pasingan | 12.4968 | 121.0677 | R | 206 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 8.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | F - Nearest node and line over 5 km | 16.23 | 13.76 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1332
2 | 333 | 1333 | 0806012022 | Region VIII (Eastern Visayas) | Samar | Motiong | Malonoy | 11.9436 | 125.0471 | R | 158 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.43 | 81.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | F - Nearest node and line over 5 km | 78.43 | 81.38 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1333
2 | 334 | 1334 | 0804824017 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Sampaguita | 12.3067 | 124.6387 | R | 154 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.01 | 68 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | F - Nearest node and line over 5 km | 68.01 | 67.98 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1334
2 | 335 | 1335 | 1380601093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 93 | 14.62 | 120.9658 | U | 4080 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.52 | 4.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | A - Node within 0.5 km | 0.4 | 0.57 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1335
2 | 336 | 1336 | 0804807014 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Lonoy | 12.3575 | 125.2107 | R | 145 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 124.16 | 123.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | F - Nearest node and line over 5 km | 124.16 | 123.33 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1336
2 | 337 | 1337 | 0401005061 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 15 | 13.6631 | 121.106 | U | 201 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.77 | 5.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.74 | 50.15 | 71.74 |  | E - Nearest node or line 3-5 km | 4.44 | 11.39 | Node: BCY005 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1337
2 | 338 | 1338 | 0802607027 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Macapagal | 11.2416 | 125.4527 | R | 114 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.46 | 47.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.73 | 50.15 | 71.73 |  | F - Nearest node and line over 5 km | 48.46 | 48.46 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1338
2 | 339 | 1339 | 1004217007 | Region X (Northern Mindanao) | Misamis Occidental | Don Victoriano Chiongbian | Maramara | 8.154 | 123.5656 | R | 522 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.51 | 22.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.73 | 50.15 | 71.73 |  | F - Nearest node and line over 5 km | 22.51 | 22.44 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1339
2 | 340 | 1340 | 1381100011 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 11 | 14.5597 | 120.9908 | U | 420 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.73 | 50.15 | 71.73 |  | B - Node 0.5-1 km | 0.71 | 0.51 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1340
2 | 341 | 1341 | 1380601068 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 68 | 14.6124 | 120.9656 | U | 1149 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.01 | 49.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.72 | 50.14 | 71.72 |  | B - Node 0.5-1 km | 0.69 | 0.42 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1341
2 | 342 | 1342 | 0103304009 | Region I (Ilocos Region) | La Union | Bagulin | Tio-angan | 16.5943 | 120.5138 | R | 998 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.95 | 10.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.72 | 50.14 | 71.72 |  | F - Nearest node and line over 5 km | 9.95 | 10.11 | Node: KPB001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1342
2 | 343 | 1343 | 1380612018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 850 | 14.5891 | 121.001 | U | 2531 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.03 | 23.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.72 | 50.14 | 71.72 |  | B - Node 0.5-1 km | 0.56 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1343
2 | 344 | 1344 | 0603040045 | Region VI (Western Visayas) | Iloilo | San Joaquin | Langca | 10.6483 | 122.08 | R | 383 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.03 | 7.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.72 | 50.14 | 71.72 |  | F - Nearest node and line over 5 km | 20.04 | 7.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1344
2 | 345 | 1345 | 0600614037 | Region VI (Western Visayas) | Antique | San Remigio | Panpanan II | 10.9024 | 122.2536 | R | 575 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.45 | 21.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.72 | 50.14 | 71.72 |  | F - Nearest node and line over 5 km | 28.45 | 21.37 | Line: 7,761 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1345
2 | 346 | 1346 | 0806020021 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Catan-agan | 11.8827 | 124.8222 | R | 67 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.85 | 66.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.71 | 50.13 | 71.71 |  | F - Nearest node and line over 5 km | 66.41 | 66.37 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1346
2 | 347 | 1347 | 1380610018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 703 | 14.5707 | 120.9891 | U | 117 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.28 | 9.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.7 | 50.13 | 71.7 |  | B - Node 0.5-1 km | 0.57 | 0.25 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1347
2 | 348 | 1348 | 0506211007 | Region V (Bicol Region) | Sorsogon | Magallanes | Biga | 12.8313 | 123.8215 | R | 1330 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 1.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.7 | 50.13 | 71.7 |  | D - Other node or line within 3 km | 2.25 | 1.31 | Line: 28,000 m | Route options survey candidate: compare actual node lateral with approved line tap. | 1348
2 | 349 | 1349 | 1003511017 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Rarab | 12.2741 | 121.1838 | R | 749 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.16 | 8.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.7 | 50.13 | 71.7 |  | D - Other node or line within 3 km | 5.36 | 1.66 | Line: ROXAS - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 1349
2 | 350 | 1350 | 0401005064 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 18 | 13.8088 | 121.0898 | U | 337 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.04 | 3.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.7 | 50.12 | 71.7 |  | D - Other node or line within 3 km | 4.2 | 1.51 | Line: BAUAN - SAN JOSE | Route options survey candidate: compare actual node lateral with approved line tap. | 1350
2 | 351 | 1351 | 1705304009 | MIMAROPA Region | Palawan | Balabac | Melville | 7.832 | 117.0018 | R | 1969 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 285.05 | 999 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.69 | 50.12 | 71.69 |  | F - Nearest node and line over 5 km | 285.05 | 287.05 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1351
2 | 352 | 1352 | 0102901005 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Apaya | 16.8814 | 120.5826 | R | 609 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.13 | 12.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.69 | 50.12 | 71.69 |  | F - Nearest node and line over 5 km | 12.13 | 12.86 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1352
2 | 353 | 1353 | 1903638041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Sigayan | 17.2551 | 122.2286 | R | 656 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.86 | 33.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.69 | 50.12 | 71.69 |  | F - Nearest node and line over 5 km | 29.41 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1353
2 | 354 | 1354 | 0704607009 | Region VII (Central Visayas) | Negros Oriental | Bindoy | Danawan | 9.7765 | 123.1432 | R | 1180 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.3 | 7.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.69 | 50.12 | 71.69 |  | F - Nearest node and line over 5 km | 20.83 | 6.12 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1354
2 | 355 | 1355 | 0600409013 | Region VI (Western Visayas) | Aklan | Libacao | Luctoga | 11.399 | 122.2914 | R | 1487 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.84 | 19.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 19.84 | 19.75 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1355
2 | 356 | 1356 | 1705304002 | MIMAROPA Region | Palawan | Balabac | Bugsuk | 8.3475 | 117.3147 | U | 1219 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 219.71 | 222.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 219.71 | 221.72 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1356
2 | 357 | 1357 | 1908816002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Buliok | 17.255 | 122.229 | R | 5559 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1357
2 | 358 | 1358 | 0806024007 | Region VIII (Eastern Visayas) | Samar | Tagapul-An | Nipa | 12.0764 | 124.1946 | R | 1016 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.53 | 58.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 38.53 | 57.98 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1358
2 | 359 | 1359 | 0804808001 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Abaton | 12.4808 | 125.0406 | R | 518 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 102.98 | 102.14 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 102.98 | 102.18 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1359
2 | 360 | 1360 | 0804807021 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | Rizal | 12.3713 | 125.2083 | R | 485 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 123.51 | 122.75 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 123.51 | 122.67 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1360
2 | 361 | 1361 | 0600614022 | Region VI (Western Visayas) | Antique | San Remigio | Orquia | 10.911 | 122.1586 | R | 214 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.21 | 21.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 29.21 | 21.76 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1361
2 | 362 | 1362 | 0502004004 | Region V (Bicol Region) | Catanduanes | Caramoran | Buenavista | 13.9877 | 124.1824 | R | 605 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.83 | 79.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 41.83 | 79.82 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1362
2 | 363 | 1363 | 1705304012 | MIMAROPA Region | Palawan | Balabac | Pasig | 7.8604 | 117.0012 | R | 489 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 282.75 | 999 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.68 | 50.11 | 71.68 |  | F - Nearest node and line over 5 km | 282.75 | 284.74 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1363
2 | 364 | 1364 | 1381100084 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 84 | 14.5456 | 120.9957 | U | 739 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 1.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | A - Node within 0.5 km | 0.18 | 0.16 | Line: Existing 216C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1364
2 | 365 | 1365 | 0802617029 | Region VIII (Eastern Visayas) | Eastern Samar | Oras | Naga | 12.1738 | 125.3685 | R | 441 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 111.26 | 113.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 111.26 | 113.82 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1365
2 | 366 | 1366 | 1903638027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Mama-an Pagalongan | 17.2543 | 122.228 | R | 600 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.2 | 35.04 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1366
2 | 367 | 1367 | 1380601184 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 184 | 14.6313 | 120.974 | U | 3412 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.95 | 62.02 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | B - Node 0.5-1 km | 0.5 | 0.52 | Node: MNL036 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1367
2 | 368 | 1368 | 0806023012 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Maga-an | 11.667 | 124.8926 | R | 606 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.45 | 46.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 46.45 | 46.34 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1368
2 | 369 | 1369 | 0804824003 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Cagamesarag | 12.3275 | 124.5883 | R | 161 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.09 | 62.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 62.09 | 62.06 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1369
2 | 370 | 1370 | 0806012023 | Region VIII (Eastern Visayas) | Samar | Motiong | Mararangsi | 11.8296 | 125.0018 | R | 241 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.6 | 67.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 65.6 | 67.87 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1370
2 | 371 | 1371 | 1903638029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Marawi | 17.2549 | 122.228 | R | 596 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.59 | 33.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.11 | 71.67 |  | F - Nearest node and line over 5 km | 29.34 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1371
2 | 372 | 1372 | 0806012004 | Region VIII (Eastern Visayas) | Samar | Motiong | Barayong | 11.962 | 124.9917 | R | 173 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.33 | 80.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.1 | 71.67 |  | F - Nearest node and line over 5 km | 80.33 | 80.58 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1372
2 | 373 | 1373 | 0804824018 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | San Francisco | 12.2921 | 125.1374 | R | 137 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 117.95 | 118.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.1 | 71.67 |  | F - Nearest node and line over 5 km | 117.95 | 117.97 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1373
2 | 374 | 1374 | 0806012020 | Region VIII (Eastern Visayas) | Samar | Motiong | Linonoban | 11.8397 | 125.003 | R | 156 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.73 | 68.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.1 | 71.67 |  | F - Nearest node and line over 5 km | 66.73 | 68.92 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1374
2 | 375 | 1375 | 1903613034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Tamporong | 17.2553 | 122.2288 | R | 956 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.89 | 33.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.67 | 50.1 | 71.67 |  | F - Nearest node and line over 5 km | 29.44 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1375
2 | 376 | 1376 | 1380400002 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Baritan | 14.6717 | 120.9493 | U | 12448 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.49 | 0.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.66 | 50.1 | 71.66 |  | A - Node within 0.5 km | 0.49 | 0.14 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1376
2 | 377 | 1377 | 1380601226 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 225 | 14.6259 | 120.9811 | U | 2492 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.78 | 9.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.66 | 50.1 | 71.66 |  | B - Node 0.5-1 km | 0.84 | 0.18 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1377
2 | 378 | 1378 | 1380601138 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 138 | 14.6284 | 120.9684 | U | 3028 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.79 | 35.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.66 | 50.1 | 71.66 |  | B - Node 0.5-1 km | 0.56 | 0.48 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1378
2 | 379 | 1379 | 1381100052 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 52 | 14.5513 | 121.0011 | U | 2460 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 1.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.66 | 50.1 | 71.66 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.33 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1379
2 | 380 | 1380 | 1908704004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Blah T. Sinsuat | Matuber | 17.2541 | 122.2282 | R | 7440 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.66 | 50.1 | 71.66 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1380
2 | 381 | 1381 | 1004206003 | Region X (Northern Mindanao) | Misamis Occidental | Concepcion | New Casul | 15.4143 | 120.6501 | R | 455 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.14 | 44.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.65 | 50.09 | 71.65 |  | F - Nearest node and line over 5 km | 5.22 | 5.19 | Line: PIPE 53-64 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1381
2 | 382 | 1382 | 0301412022 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saint Francis (Gasak) | 14.733 | 120.9567 | R | 1372 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.4 | 0.52 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.65 | 50.09 | 71.65 |  | D - Other node or line within 3 km | 1.4 | 0.5 | Line: 48 CORE | Route options survey candidate: compare actual node lateral with approved line tap. | 1382
2 | 383 | 1383 | 0806020026 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Lahong | 11.9333 | 124.7635 | R | 237 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.91 | 70.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.65 | 50.09 | 71.65 |  | F - Nearest node and line over 5 km | 70.91 | 70.88 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1383
2 | 384 | 1384 | 0806020007 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Bangon Gote | 11.9585 | 124.7117 | R | 145 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.29 | 73.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.09 | 71.64 |  | F - Nearest node and line over 5 km | 73.29 | 73.26 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1384
2 | 385 | 1385 | 1381100009 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 9 | 14.5576 | 120.9902 | U | 264 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.04 | 1.86 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.09 | 71.64 |  | B - Node 0.5-1 km | 0.51 | 0.5 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1385
2 | 386 | 1386 | 1380601172 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 172 | 14.6291 | 120.972 | U | 1247 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.3 | 38.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | A - Node within 0.5 km | 0.28 | 0.27 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1386
2 | 387 | 1387 | 1903610031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Kibolos | 17.2544 | 122.2284 | R | 768 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1387
2 | 388 | 1388 | 1208006012 | Region XII (SOCCSKSARGEN) | Sarangani | Malapatan | Upper Suyan | 6.0743 | 125.4503 | R | 4980 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.36 | 27.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | F - Nearest node and line over 5 km | 19.36 | 27.46 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1388
2 | 389 | 1389 | 0803705004 | Region VIII (Eastern Visayas) | Leyte | Babatngon | Malibago | 11.4107 | 124.9241 | R | 870 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.85 | 23.92 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | F - Nearest node and line over 5 km | 20.85 | 23.91 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1389
2 | 390 | 1390 | 1906615015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Tattalan | 17.2557 | 122.2297 | R | 2792 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1390
2 | 391 | 1391 | PH0001391 | VII | Cebu | Talisay City | Cansojong | 10.2503 | 123.8543 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.35 | 10.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | C - Line within 0.5 km; node over 1 km | 1.98 | 0.11 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1391
2 | 392 | 1392 | 1903610029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Dilabayan | 17.2544 | 122.2285 | R | 1279 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.64 | 50.08 | 71.64 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1392
2 | 393 | 1393 | 1003511015 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lower Caningag | 12.252 | 121.1173 | R | 396 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.59 | 9.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.08 | 71.63 |  | F - Nearest node and line over 5 km | 7.23 | 6.74 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1393
2 | 394 | 1394 | 1903610037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Macadar | 17.2544 | 122.2284 | R | 715 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.08 | 71.63 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1394
2 | 395 | 1395 | 1903610038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Pantaon | 17.2544 | 122.2284 | R | 1585 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.08 | 71.63 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1395
2 | 396 | 1396 | 1903610018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Pagalongan | 17.2544 | 122.2285 | R | 887 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.08 | 71.63 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1396
2 | 397 | 1397 | 1108604014 | Region XI (Davao Region) | Davao Occidental | Santa Maria | San Juan | 6.4045 | 125.4183 | R | 1641 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.3 | 11.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.08 | 71.63 |  | F - Nearest node and line over 5 km | 13.3 | 11.96 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1397
2 | 398 | 1398 | 1381100024 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 24 | 14.6156 | 120.9799 | U | 724 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.07 | 71.63 |  | A - Node within 0.5 km | 0.34 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1398
2 | 399 | 1399 | 1108604004 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kidadan | 6.5005 | 125.4404 | R | 1168 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.52 | 8.67 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.63 | 50.07 | 71.63 |  | F - Nearest node and line over 5 km | 10.52 | 8.62 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1399
2 | 400 | 1400 | 1903601023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Raya | 17.2544 | 122.2297 | R | 734 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 29.45 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1400
2 | 401 | 1401 | 1003511001 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Babasalon | 8.0463 | 123.9011 | R | 810 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.83 | 7.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 11.23 | 6.74 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1401
2 | 402 | 1402 | 1003511022 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Tawinian | 12.3396 | 121.1774 | R | 830 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.85 | 9.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | E - Nearest node or line 3-5 km | 4.55 | 3.73 | Line: AE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1402
2 | 403 | 1403 | 1381100185 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 185 | 14.534 | 121.0005 | U | 4771 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.16 | 0.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | B - Node 0.5-1 km | 0.77 | 0.19 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1403
2 | 404 | 1404 | 1906612066 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | South Silumpak | 17.2555 | 122.2295 | R | 1861 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1404
2 | 405 | 1405 | 1903613029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Raya | 17.2546 | 122.2287 | R | 895 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1405
2 | 406 | 1406 | 1102510015 | Region XI (Davao Region) | Davao Oriental | San Isidro | Santo Rosario | 6.8141 | 126.154 | R | 930 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.3 | 8.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 17.3 | 8.55 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1406
2 | 407 | 1407 | 1906612042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Punungan | 17.2555 | 122.2295 | R | 1114 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.62 | 50.07 | 71.62 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1407
2 | 408 | 1408 | 1903638026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Malingon | 17.2538 | 122.2285 | R | 1202 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 33.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 29.31 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1408
2 | 409 | 1409 | 1380300018 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Pio Del Pilar | 14.5504 | 121.0089 | U | 24955 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.27 | 0.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | A - Node within 0.5 km | 0.27 | 0.04 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1409
2 | 410 | 1410 | 0600614002 | Region VI (Western Visayas) | Antique | San Remigio | Alegria | 10.8715 | 122.1586 | R | 583 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.98 | 19.93 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 26.98 | 19.82 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1410
2 | 411 | 1411 | 1903613030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Riray | 17.2553 | 122.2288 | R | 682 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.23 | 35.07 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 29.44 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1411
2 | 412 | 1412 | 0804807011 | Region VIII (Eastern Visayas) | Northern Samar | Gamay | G. M. Osias | 12.3618 | 125.2234 | R | 715 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 125.37 | 124.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 125.37 | 124.53 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1412
2 | 413 | 1413 | 0802606016 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | Libertad | 12.185 | 125.2495 | R | 670 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 108.51 | 111.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 108.51 | 111.25 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1413
2 | 414 | 1414 | PH0001414 | VII | Bohol | Pres. Carlos P. Garcia (Pitogo) | Butan | 10.164 | 124.4993 | R | 2229 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.28 | 29.57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 36.28 | 29.56 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1414
2 | 415 | 1415 | 0802606044 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | Tanauan | 12.0458 | 125.4202 | R | 642 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 100.53 | 102.9 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 100.53 | 102.9 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1415
2 | 416 | 1416 | 0600614040 | Region VI (Western Visayas) | Antique | San Remigio | Rizal | 10.9237 | 122.1767 | R | 357 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.65 | 24.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 31.65 | 24.19 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1416
2 | 417 | 1417 | 0504121028 | Region V (Bicol Region) | Masbate | Uson | San Isidro | 12.127 | 123.7534 | R | 854 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.28 | 27.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 12.28 | 27.92 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1417
2 | 418 | 1418 | 1108601008 | Region XI (Davao Region) | Davao Occidental | Don Marcelino | Dalupan | 6.1927 | 125.6364 | R | 3750 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.81 | 42.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 40.81 | 42.22 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1418
2 | 419 | 1419 | PH0001419 | NCR | Metro Manila | Caloocan City | Barangay 21 | 14.6027 | 120.9626 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.12 | 17.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | B - Node 0.5-1 km | 0.89 | 0.89 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1419
2 | 420 | 1420 | 1903638024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Bagoaingud | 17.2537 | 122.2282 | R | 1002 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.12 | 35.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 29.27 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1420
2 | 421 | 1421 | PH0001421 | VIII | Leyte | Tacloban City | Barangay 35-A | 11.2869 | 124.9594 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.98 | 6.49 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | F - Nearest node and line over 5 km | 7.05 | 9.9 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1421
2 | 422 | 1422 | 1003511024 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Tombador | 12.2839 | 121.1318 | R | 544 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.43 | 9.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.61 | 50.06 | 71.61 |  | E - Nearest node or line 3-5 km | 3.39 | 3.02 | Line: AE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1422
2 | 423 | 1423 | 0501703025 | Region V (Bicol Region) | Camarines Sur | Bato | San Isidro | 13.5742 | 124.3333 | R | 211 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.75 | 4.59 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 55.43 | 69.34 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1423
2 | 424 | 1424 | 0806023014 | Region VIII (Eastern Visayas) | Samar | Zumarraga | Monbon | 11.6429 | 124.8413 | R | 682 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.59 | 41.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 41.59 | 41.51 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1424
2 | 425 | 1425 | 1903621015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Lininding | 17.2549 | 122.2277 | R | 1346 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.4 | 38.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 29.32 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1425
2 | 426 | 1426 | 1908708011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Tumaguinting | 17.2545 | 122.2275 | R | 7177 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.42 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 29.27 | 34.14 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1426
2 | 427 | 1427 | 0506207004 | Region V (Bicol Region) | Sorsogon | Donsol | Bandi | 12.9886 | 123.5854 | R | 372 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.33 | 14.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 9.33 | 14.34 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1427
2 | 428 | 1428 | 1381100016 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 16 | 14.5595 | 120.9906 | U | 436 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.53 | 2.54 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | B - Node 0.5-1 km | 0.71 | 0.54 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1428
2 | 429 | 1429 | 1908816008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Kilangan | 17.255 | 122.229 | U | 6210 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1429
2 | 430 | 1430 | 0802623004 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Bongdo | 11.9384 | 125.4014 | R | 266 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 89.04 | 91.3 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.06 | 71.6 |  | F - Nearest node and line over 5 km | 89.04 | 91.32 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1430
2 | 431 | 1431 | 0506207029 | Region V (Bicol Region) | Sorsogon | Donsol | Parina | 12.9667 | 123.5667 | R | 231 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.45 | 17.01 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.05 | 71.6 |  | F - Nearest node and line over 5 km | 7.45 | 16.92 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1431
2 | 432 | 1432 | 1908822004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Kigan | 17.2551 | 122.2291 | R | 3234 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.05 | 71.6 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1432
2 | 433 | 1433 | 1380608002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 659-A | 14.5854 | 120.9848 | U | 2686 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.2 | 3.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.05 | 71.6 |  | B - Node 0.5-1 km | 0.58 | 0.29 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1433
2 | 434 | 1434 | 0401005060 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 14 | 13.7765 | 121.0441 | U | 239 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.55 | 5.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.05 | 71.6 |  | C - Line within 0.5 km; node over 1 km | 1.35 | 0.05 | Line: LEMERY TO SAN JUAN CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1434
2 | 435 | 1435 | 0506207024 | Region V (Bicol Region) | Sorsogon | Donsol | New Maguisa | 12.9128 | 123.5976 | R | 376 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.35 | 15.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.6 | 50.05 | 71.6 |  | B - Node 0.5-1 km | 0.96 | 16.99 | Node: DLS001 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1435
2 | 436 | 1436 | 1380601058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 58 | 14.6082 | 120.9724 | U | 3832 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.18 | 57 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.59 | 50.05 | 71.59 |  | A - Node within 0.5 km | 0.33 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1436
2 | 437 | 1437 | PH0001437 | VIII | Samar (Western Samar) | Catbalogan City | Buluan | 11.8179 | 124.7385 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.49 | 33.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.59 | 50.05 | 71.59 |  | F - Nearest node and line over 5 km | 57.86 | 57.83 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1437
2 | 438 | 1438 | 1208002009 | Region XII (SOCCSKSARGEN) | Sarangani | Glan | Congan | 5.8117 | 125.2776 | R | 2344 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.58 | 35.61 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.59 | 50.05 | 71.59 |  | F - Nearest node and line over 5 km | 32.58 | 35.61 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1438
2 | 439 | 1439 | 1906608012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Patutol | 17.2554 | 122.2294 | R | 1480 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.59 | 50.05 | 71.59 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1439
2 | 440 | 1440 | 1381100189 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 189 | 14.5346 | 121.0017 | U | 2500 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.59 | 50.05 | 71.59 |  | B - Node 0.5-1 km | 0.89 | 0.21 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1440
2 | 441 | 1441 | 1908701014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Togaig | 17.2541 | 122.2281 | R | 7196 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1441
2 | 442 | 1442 | 1705213002 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Calangatan | 13.3701 | 120.9657 | R | 2758 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.32 | 8.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 9.32 | 8.02 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1442
2 | 443 | 1443 | 1906612025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Latung | 17.2555 | 122.2295 | R | 3526 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 29.51 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1443
2 | 444 | 1444 | 1903619033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Mulondo | Lumbaca Ingud | 17.2542 | 122.2283 | R | 690 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.32 | 34.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 29.32 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1444
2 | 445 | 1445 | 1381100146 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 146 | 14.549 | 121.0067 | U | 1065 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | B - Node 0.5-1 km | 0.51 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1445
2 | 446 | 1446 | 1900708006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Paguengan | 6.6041 | 122.2372 | R | 2326 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.83 | 56.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 38.54 | 38.52 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1446
2 | 447 | 1447 | 1003516013 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Lomidong | 8.042 | 124.1543 | R | 1672 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.38 | 7.85 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 13.69 | 10.79 | Line: BALOI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1447
2 | 448 | 1448 | PH0001448 | XI | Davao Del Sur | Davao City | Barangay 28-C (Pob.) | 7.0723 | 125.6191 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | B - Node 0.5-1 km | 0.86 | 0.81 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1448
2 | 449 | 1449 | 1906612074 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Tonglabah | 17.2556 | 122.2297 | R | 1423 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.58 | 50.04 | 71.58 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1449
2 | 450 | 1450 | 1380605003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 299 | 14.6128 | 120.9953 | U | 1339 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.44 | 14.34 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | B - Node 0.5-1 km | 0.94 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1450
2 | 451 | 1451 | 1906612020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Kud-kud | 17.2556 | 122.2297 | R | 1487 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1451
2 | 452 | 1452 | 1908708004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Guiawa | 17.2532 | 122.2274 | R | 3925 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.79 | 33.53 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | F - Nearest node and line over 5 km | 29.17 | 34.08 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1452
2 | 453 | 1453 | 1102506012 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Sergio Osmeña | 6.6758 | 126.1297 | R | 2020 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.37 | 38.69 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | F - Nearest node and line over 5 km | 27.74 | 22.63 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1453
2 | 454 | 1454 | 1908708010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Sabaken | 17.2536 | 122.2286 | R | 5719 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.13 | 34.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | F - Nearest node and line over 5 km | 29.3 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1454
2 | 455 | 1455 | 1908706004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Gambar | 17.2535 | 122.2282 | R | 5001 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.04 | 71.57 |  | F - Nearest node and line over 5 km | 29.26 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1455
2 | 456 | 1456 | 1108603041 | Region XI (Davao Region) | Davao Occidental | Malita | Pangaleon | 6.3316 | 125.525 | R | 2435 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.61 | 26.08 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 27.61 | 26.07 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1456
2 | 457 | 1457 | 1903633017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Buadiposo-Buntong | Lumbatan Manacab | 17.2543 | 122.228 | R | 455 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.48 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.3 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1457
2 | 458 | 1458 | 1906612060 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Sipanding | 17.2555 | 122.2295 | R | 1929 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.51 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1458
2 | 459 | 1459 | 1908701012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Panggao | 17.254 | 122.2278 | R | 3009 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.81 | 22.13 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.27 | 34.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1459
2 | 460 | 1460 | 1903639008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Lusain | 17.2546 | 122.2286 | R | 1230 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1460
2 | 461 | 1461 | 0907312008 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Labangan | Cogonan | 7.9485 | 123.3146 | R | 2018 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.97 | 11.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 18.97 | 11.8 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1461
2 | 462 | 1462 | 1906606008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Pag-asinan | 17.2558 | 122.2289 | R | 1919 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.48 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1462
2 | 463 | 1463 | 1906612057 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Siolakan | 17.2555 | 122.2295 | R | 2422 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1463
2 | 464 | 1464 | 1906612048 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Ratag | 17.2555 | 122.2295 | R | 2525 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1464
2 | 465 | 1465 | 0102901010 | Region I (Ilocos Region) | Ilocos Sur | Alilem | Daddaay | 16.9092 | 120.6013 | R | 713 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.94 | 14.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 10.94 | 14.51 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1465
2 | 466 | 1466 | 1906608010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Panducan | 17.2553 | 122.2294 | R | 3077 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1466
2 | 467 | 1467 | 0806025005 | Region VIII (Eastern Visayas) | Samar | San Jorge | Bungliw | 11.9026 | 124.9051 | R | 253 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 71.02 | 70.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 71.02 | 70.96 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1467
2 | 468 | 1468 | 1108605002 | Region XI (Davao Region) | Davao Occidental | Sarangani | Konel | 5.4312 | 125.3926 | R | 2140 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.98 | 79.79 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 75.98 | 79.79 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1468
2 | 469 | 1469 | 0907333004 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Bululawan | 7.867 | 123.1039 | R | 1352 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.18 | 9.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.57 | 50.03 | 71.57 |  | F - Nearest node and line over 5 km | 16.18 | 9.6 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1469
2 | 470 | 1470 | 1381200001 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bagong Ilog | 14.5637 | 121.0713 | U | 21608 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.11 | Line: RELIANCE PSG001 TO BÑL001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1470
2 | 471 | 1471 | 1003511008 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Lubo | 8.9359 | 125.2251 | R | 1184 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.96 | 7.66 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | E - Nearest node or line 3-5 km | 4.95 | 4.1 | Line: CDO - BUENAVISTA via GINGOOG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1471
2 | 472 | 1472 | 1908701010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Minabay | 17.2541 | 122.2282 | R | 4580 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.31 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1472
2 | 473 | 1473 | 1903638018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Kitaon | 17.2539 | 122.2288 | R | 428 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.93 | 32.82 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.34 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1473
2 | 474 | 1474 | 1906613021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Kuhaw | 17.2554 | 122.2295 | R | 2766 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1474
2 | 475 | 1475 | 1908711003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Mastura | Bungabong | 17.2541 | 122.2281 | R | 2814 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.19 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1475
2 | 476 | 1476 | 1108605011 | Region XI (Davao Region) | Davao Occidental | Sarangani | Tagen | 5.3799 | 125.3516 | R | 1396 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.34 | 84.18 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 80.34 | 84.18 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1476
2 | 477 | 1477 | 1903639009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Matimos | 17.2546 | 122.2286 | R | 792 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1477
2 | 478 | 1478 | 1903609012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Ganassi | Macaguiling | 17.2547 | 122.2287 | R | 1045 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.39 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1478
2 | 479 | 1479 | 1906614016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kamaunggi | 17.2556 | 122.2297 | R | 2069 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1479
2 | 480 | 1480 | 0907312010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Labangan | Dipaya | 7.9232 | 123.434 | R | 1191 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.29 | 8.97 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 10.29 | 8.97 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1480
2 | 481 | 1481 | 1906615012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Tainga-Bakkao | 17.2557 | 122.2297 | R | 2763 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1481
2 | 482 | 1482 | 1108605007 | Region XI (Davao Region) | Davao Occidental | Sarangani | Tinina | 5.3778 | 125.3964 | R | 1438 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.91 | 85.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 81.91 | 85.61 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1482
2 | 483 | 1483 | 1903614033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Pagayonan | 17.2546 | 122.2287 | R | 1084 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1483
2 | 484 | 1484 | 1906617016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Sibul | 17.2555 | 122.2295 | R | 1563 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1484
2 | 485 | 1485 | 1208007022 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Panamin | 6.3745 | 125.3792 | R | 1683 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.71 | 9.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 12.71 | 9.74 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1485
2 | 486 | 1486 | 1908816006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Inug-ug | 17.255 | 122.229 | R | 2498 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1486
2 | 487 | 1487 | 1906613011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Gata | 17.2554 | 122.2295 | R | 2104 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1487
2 | 488 | 1488 | 1903611054 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumba-Bayabao | Lobo Basara | 17.2544 | 122.2287 | R | 1279 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.21 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.37 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1488
2 | 489 | 1489 | 1003511013 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Pangao | 6.8348 | 125.1553 | R | 1060 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.56 | 10.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 7.93 | 16.21 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1489
2 | 490 | 1490 | 1906613007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Bud Bunga | 17.2555 | 122.2295 | R | 2238 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1490
2 | 491 | 1491 | 1380601170 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 170 | 14.6233 | 120.9721 | U | 1420 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.87 | 18.77 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | A - Node within 0.5 km | 0.41 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1491
2 | 492 | 1492 | 1908708005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Indatuan | 17.2536 | 122.2286 | R | 4501 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.52 | 33.74 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.3 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1492
2 | 493 | 1493 | 1906610014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Sangkap | 17.2556 | 122.2296 | R | 2444 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1493
2 | 494 | 1494 | 1906610015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Timuddas | 17.2556 | 122.2296 | R | 2397 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1494
2 | 495 | 1495 | 1906612011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Duhol Tara | 17.2556 | 122.2296 | R | 1323 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1495
2 | 496 | 1496 | 0907344012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Mate | 7.8773 | 123.2289 | R | 1111 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.75 | 4.23 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | E - Nearest node or line 3-5 km | 23.75 | 4.2 | Line: PAGADIAN - BUUG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1496
2 | 497 | 1497 | 1903638025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Malinao | 17.2544 | 122.2285 | R | 808 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1497
2 | 498 | 1498 | 1908708002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Damatog | 17.2539 | 122.2276 | R | 4229 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 33.88 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 29.24 | 34.13 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1498
2 | 499 | 1499 | 1900708004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Mangalut | 6.6035 | 122.2107 | R | 2298 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.32 | 37.31 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.03 | 71.56 |  | F - Nearest node and line over 5 km | 37.32 | 37.31 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1499
2 | 500 | 1500 | 1906610003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Daungdong | 17.2555 | 122.2296 | R | 2408 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.02 | 71.56 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1500
2 | 501 | 1501 | 1906612059 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Siowing | 17.2555 | 122.2295 | R | 1582 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.02 | 71.56 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1501
2 | 502 | 1502 | 1903638002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Bantalan | 17.254 | 122.2291 | R | 674 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.74 | 35.22 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.56 | 50.02 | 71.56 |  | F - Nearest node and line over 5 km | 29.37 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1502
2 | 503 | 1503 | 1903631017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Marogong East | 17.2557 | 122.2296 | R | 2587 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.22 | 81.06 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1503
2 | 504 | 1504 | 1906614035 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Tulakan | 17.2557 | 122.2297 | R | 2038 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1504
2 | 505 | 1505 | 1906610005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kanjarang | 17.2556 | 122.2296 | R | 1808 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1505
2 | 506 | 1506 | 1908706015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Pened | 17.2545 | 122.2273 | R | 1779 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.27 | 34.12 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1506
2 | 507 | 1507 | 1003511010 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Malabaogan | 12.3194 | 121.2002 | R | 523 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.74 | 7.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | C - Line within 0.5 km; node over 1 km | 5.61 | 0.4 | Line: ROXAS - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1507
2 | 508 | 1508 | 1906610007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kiput | 17.2556 | 122.2296 | R | 1916 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1508
2 | 509 | 1509 | 1903638042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Tagoloan Poblacion | 17.2542 | 122.2277 | R | 928 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.88 | 34.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.28 | 34.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1509
2 | 510 | 1510 | 1906615006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Luuk | 17.2557 | 122.2297 | R | 1963 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1510
2 | 511 | 1511 | 1906614013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Alu-Kabingaan | 17.2553 | 122.2303 | R | 2105 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.56 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1511
2 | 512 | 1512 | 0907333012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Sebuguey | 7.8855 | 123.1084 | R | 776 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.28 | 11.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 18.28 | 11.58 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1512
2 | 513 | 1513 | 1906606003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Kabuukan | 17.2553 | 122.2293 | R | 2973 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1513
2 | 514 | 1514 | 1908708006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Kapimpilan | 17.2548 | 122.2284 | R | 3410 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.05 | 35.29 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.37 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1514
2 | 515 | 1515 | 1108604022 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Datu Intan | 6.4622 | 125.4004 | R | 1659 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.08 | 6.44 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 9.08 | 6.44 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1515
2 | 516 | 1516 | 1906614010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Hawan | 17.2556 | 122.2297 | R | 1481 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1516
2 | 517 | 1517 | 0907313019 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Pantad | 7.6603 | 123.1676 | R | 428 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.61 | 11.15 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 14.61 | 11.14 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1517
2 | 518 | 1518 | 1906610006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Kayawan | 17.2555 | 122.2296 | R | 2268 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1518
2 | 519 | 1519 | 1906614017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kanmangon | 17.2556 | 122.2297 | R | 1204 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1519
2 | 520 | 1520 | 1003523029 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Tawanan | 8.0939 | 124.2662 | R | 959 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.12 | 1.25 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | D - Other node or line within 3 km | 9.37 | 2.08 | Line: PANTAR | Route options survey candidate: compare actual node lateral with approved line tap. | 1520
2 | 521 | 1521 | 1906612030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Manta | 17.2555 | 122.2295 | R | 1621 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1521
2 | 522 | 1522 | 1903606023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bubong | Dibarosan | 17.2547 | 122.2292 | R | 685 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.61 | 36.73 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.43 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1522
2 | 523 | 1523 | 0907333005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Dagum | 7.918 | 123.1422 | R | 555 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.03 | 13.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 23.03 | 13.6 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1523
2 | 524 | 1524 | 0908306027 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Kabasalan | Shiolan | 7.9324 | 122.8394 | R | 519 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.74 | 16.96 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 32.74 | 16.96 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1524
2 | 525 | 1525 | 1906614025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Pagatpat | 17.2556 | 122.2297 | R | 1371 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1525
2 | 526 | 1526 | 1906608016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Suang Bunah | 17.2554 | 122.2294 | R | 1851 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1526
2 | 527 | 1527 | 1903610017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Malna Proper | 17.2544 | 122.2284 | R | 1325 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1527
2 | 528 | 1528 | 1903631032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Calumbog | 17.2545 | 122.2298 | R | 1078 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.16 | 79.99 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.47 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1528
2 | 529 | 1529 | 0908301014 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Alicia | Litayon | 7.4599 | 122.9671 | R | 1161 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.54 | 20.55 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 31.54 | 20.55 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1529
2 | 530 | 1530 | 0907325006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | San Pablo | Kalilangan | 7.6483 | 123.4212 | R | 1042 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.39 | 19.45 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 20.39 | 19.41 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1530
2 | 531 | 1531 | 1906614033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Tangkapaan | 17.2556 | 122.2297 | R | 1871 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.55 | 50.02 | 71.55 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1531
2 | 532 | 1532 | 1906612018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Kabubu | 17.2556 | 122.2297 | R | 1277 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1532
2 | 533 | 1533 | 1906612056 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Singko | 17.2556 | 122.2297 | R | 1116 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1533
2 | 534 | 1534 | 0907303009 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Dagum | 7.9006 | 123.1005 | R | 389 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.64 | 13.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 19.64 | 13.35 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1534
2 | 535 | 1535 | 1906614028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Puok | 17.2557 | 122.2297 | R | 1600 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1535
2 | 536 | 1536 | 1906608017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Tonggasang | 17.2553 | 122.2294 | R | 1562 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1536
2 | 537 | 1537 | 1906612065 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | South Musu Laud | 5.5421 | 120.8149 | R | 881 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 206.18 | 206.17 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 206.18 | 206.17 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1537
2 | 538 | 1538 | 1108604023 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kinilidan | 6.446 | 125.4476 | R | 1329 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.51 | 11.94 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 14.51 | 11.94 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1538
2 | 539 | 1539 | 1906612075 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Tubig Kutah | 17.2556 | 122.2297 | R | 1081 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1539
2 | 540 | 1540 | 0907313005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Dansal | 7.649 | 123.222 | R | 879 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.47 | 14.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.02 | 71.54 |  | F - Nearest node and line over 5 km | 20.47 | 14.76 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1540
2 | 541 | 1541 | 1003514015 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Madaya | 8.0797 | 124.0631 | R | 844 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.78 | 15.03 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 24.52 | 11.65 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1541
2 | 542 | 1542 | 1906607023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Lunggang | 17.2554 | 122.2289 | R | 1160 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.64 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.45 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1542
2 | 543 | 1543 | 1906607016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Kan-Sipat | 17.2556 | 122.2296 | R | 1021 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1543
2 | 544 | 1544 | 1903631029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Sarang | 17.2544 | 122.2295 | R | 966 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.73 | 80.6 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.43 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1544
2 | 545 | 1545 | 1903631023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Paigoay Coda | 17.2552 | 122.2281 | R | 930 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.29 | 81.11 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.38 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1545
2 | 546 | 1546 | 1903631027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Puracan | 17.254 | 122.2283 | R | 705 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.53 | 79.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.31 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1546
2 | 547 | 1547 | 1903613022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Lilitun | 17.2549 | 122.2294 | R | 529 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.63 | 33.83 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.47 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1547
2 | 548 | 1548 | 1906612015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Ipil | 17.2555 | 122.2295 | R | 909 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1548
2 | 549 | 1549 | 1906606002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Hadji Panglima Tahil | Bubuan | 17.2547 | 122.2294 | R | 1133 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.44 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1549
2 | 550 | 1550 | 1906614030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Sayli | 17.2554 | 122.229 | R | 1048 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.04 | 33.76 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.47 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1550
2 | 551 | 1551 | 1906610001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Andalan | 17.2563 | 122.23 | R | 1020 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.63 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.61 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1551
2 | 552 | 1552 | 1903602022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Balabagan | Buenavista | 17.2549 | 122.2294 | R | 755 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.46 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1552
2 | 553 | 1553 | 1003521006 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Big Meladoc | 8.0455 | 123.9444 | R | 624 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.5 | 10.87 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 15.99 | 9 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1553
2 | 554 | 1554 | 1380612032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 864 | 14.5861 | 121.0068 | U | 838 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.91 | 55.5 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | A - Node within 0.5 km | 0.47 | 0.48 | Node: MNL004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1554
2 | 555 | 1555 | 1906618016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Laud Sibaud | 17.2561 | 122.2292 | R | 990 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.65 | 3.51 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.53 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1555
2 | 556 | 1556 | 1380606239 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 632 | 14.6024 | 121.0044 | U | 262 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.27 | 3.16 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | A - Node within 0.5 km | 0.04 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1556
2 | 557 | 1557 | 1906614003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Banting | 17.2557 | 122.2297 | R | 1200 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1557
2 | 558 | 1558 | 1906608001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Alu Bunah | 17.2554 | 122.2294 | R | 1002 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.37 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1558
2 | 559 | 1559 | 1906610011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Patian | 17.2556 | 122.2296 | R | 1108 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.52 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1559
2 | 560 | 1560 | 1903631004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Bitayan | 17.2544 | 122.2295 | R | 1027 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.76 | 81.62 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.43 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1560
2 | 561 | 1561 | 1903631012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Diragun | 17.254 | 122.2283 | R | 1160 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.33 | 80.12 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.31 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1561
2 | 562 | 1562 | 1906614018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tapul | Kanaway | 17.2556 | 122.2297 | R | 1503 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1562
2 | 563 | 1563 | 1906618008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Mamanok | 17.256 | 122.2289 | R | 1052 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.65 | 2.39 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.54 | 50.01 | 71.54 |  | F - Nearest node and line over 5 km | 29.5 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1563
2 | 564 | 1564 | 1908806007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Elbebe | 17.2552 | 122.2293 | R | 778 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.48 | 34.35 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1564
2 | 565 | 1565 | 0806017007 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Cabunga-an | 11.469 | 124.8829 | R | 516 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.27 | 26.98 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 28.27 | 26.98 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1565
2 | 566 | 1566 | 1906612026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Luuk Tara | 17.2548 | 122.2291 | R | 914 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.72 | 1.65 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 29.43 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1566
2 | 567 | 1567 | 1903638007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Dimalama | 17.2543 | 122.2281 | R | 675 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.59 | 32.84 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 29.31 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1567
2 | 568 | 1568 | 1903634016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Maguing | Cambong | 17.2534 | 122.2276 | R | 691 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.36 | 34.46 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 29.21 | 34.12 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1568
2 | 569 | 1569 | 0907303022 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Matun-og | 7.871 | 123.0822 | R | 492 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.98 | 10.7 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 15.98 | 10.68 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1569
2 | 570 | 1570 | 0501607001 | Region V (Bicol Region) | Camarines Norte | Mercedes | Apuao | 14.0806 | 123.0945 | R | 610 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.24 | 14.33 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 9.24 | 14.33 | Node: BDC002 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1570
2 | 571 | 1571 | 0907343014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Guipos | Magting | 7.7581 | 123.3002 | R | 334 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.33 | 8.27 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 17.33 | 8.22 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1571
2 | 572 | 1572 | 0907303001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Baking | 7.8757 | 123.1595 | R | 372 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.89 | 8.8 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | F - Nearest node and line over 5 km | 19.89 | 8.76 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1572
2 | 573 | 1573 | 0506207015 | Region V (Bicol Region) | Sorsogon | Donsol | Girawan | 12.9348 | 123.5873 | R | 375 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.38 | 16.58 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50.01 | 71.53 |  | E - Nearest node or line 3-5 km | 3.38 | 16.41 | Node: DLS001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1573
2 | 574 | 1574 | 0802623015 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Pangabutan | 11.9578 | 125.3931 | R | 229 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.49 | 92.81 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50 | 71.53 |  | F - Nearest node and line over 5 km | 90.49 | 92.82 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1574
2 | 575 | 1575 | 0506207026 | Region V (Bicol Region) | Sorsogon | Donsol | Old Maguisa | 13.0051 | 123.5686 | R | 235 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.45 | 15.91 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50 | 71.53 |  | F - Nearest node and line over 5 km | 11.45 | 15.79 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1575
2 | 576 | 1576 | 0907216004 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Dinulan | 7.3246 | 122.0944 | R | 364 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.58 | 18.28 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.53 | 50 | 71.53 |  | F - Nearest node and line over 5 km | 20.58 | 18.25 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1576
2 | 577 | 1577 | 1380606066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 460 | 14.6102 | 120.9921 | U | 813 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.86 | 45.36 | Tier 1 Critical GIDA (Score ≥ 50.0) | 71.52 | 50 | 71.52 |  | B - Node 0.5-1 km | 0.79 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1577
2 | 578 | 1578 | PH0001578 | CAR | Benguet | Baguio City | Padre Burgos | 16.4273 | 120.5945 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.16 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 71.52 | 50 | 71.52 |  | A - Node within 0.5 km | 0.21 | 1.41 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1578
2 | 579 | 1579 | 1381300046 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Kaligayahan | 14.7327 | 121.0532 | U | 62999 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 71.52 | 50 | 71.52 |  | B - Node 0.5-1 km | 0.93 | 0.13 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1579
2 | 580 | 1580 | 1380500007 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Burol | 14.5776 | 121.0297 | U | 2900 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.31 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 71.52 | 50 | 71.52 |  | B - Node 0.5-1 km | 0.69 | 0.28 | Line: Aerial 216C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1580
2 | 581 | 1581 | 1380300015 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Palanan | 14.5606 | 121.0015 | U | 5718 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 0.57 | Tier 2 High GIDA (Score 40.0–49.9) | 71.52 | 50 | 71.52 |  | C - Line within 0.5 km; node over 1 km | 1.33 | 0.49 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1581
2 | 582 | 1582 | 1108204020 | Region XI (Davao Region) | Davao de Oro | Maco | Manipongol | 7.3564 | 125.9074 | R | 590 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.66 | 5.53 | Tier 2 High GIDA (Score 40.0–49.9) | 71.51 | 49.99 | 71.51 |  | F - Nearest node and line over 5 km | 5.66 | 5.5 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1582
2 | 583 | 1583 | 1380601064 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 64 | 14.612 | 120.9646 | U | 510 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.96 | 27.82 | Tier 2 High GIDA (Score 40.0–49.9) | 71.51 | 49.99 | 71.51 |  | B - Node 0.5-1 km | 0.69 | 0.51 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1583
2 | 584 | 1584 | 0806016010 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Camperito | 12.1239 | 124.744 | R | 244 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.44 | 88.43 | Tier 2 High GIDA (Score 40.0–49.9) | 71.5 | 49.99 | 71.5 |  | F - Nearest node and line over 5 km | 88.44 | 88.4 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1584
2 | 585 | 1585 | PH0001585 | VIII | Samar (Western Samar) | Calbayog City | Mantaong | 12.1862 | 124.5151 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.77 | 64.77 | Tier 2 High GIDA (Score 40.0–49.9) | 71.5 | 49.98 | 71.5 |  | F - Nearest node and line over 5 km | 64.77 | 64.74 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1585
2 | 586 | 1586 | 0401001010 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Mabini | 13.9346 | 120.9131 | R | 1343 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.54 | 6 | Tier 2 High GIDA (Score 40.0–49.9) | 71.49 | 49.98 | 71.49 |  | D - Other node or line within 3 km | 2.43 | 3.84 | Node: ALB001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 1586
2 | 587 | 1587 | 0806025019 | Region VIII (Eastern Visayas) | Samar | San Jorge | Mobo-ob | 11.9731 | 124.9191 | R | 184 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.94 | 78.88 | Tier 2 High GIDA (Score 40.0–49.9) | 71.49 | 49.98 | 71.49 |  | F - Nearest node and line over 5 km | 78.94 | 78.88 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1587
2 | 588 | 1588 | 0806002010 | Region VIII (Eastern Visayas) | Samar | Basey | Cancaiyas | 11.35 | 125.0836 | R | 615 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.13 | 17.29 | Tier 2 High GIDA (Score 40.0–49.9) | 71.47 | 49.96 | 71.47 |  | F - Nearest node and line over 5 km | 15.13 | 17.3 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1588
2 | 589 | 1589 | 1380601157 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 157 | 14.6278 | 120.9736 | U | 1551 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.19 | 3.78 | Tier 2 High GIDA (Score 40.0–49.9) | 71.47 | 49.96 | 71.47 |  | A - Node within 0.5 km | 0.11 | 0.14 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1589
2 | 590 | 1590 | 1380606241 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 634 | 14.5981 | 121.0017 | U | 1359 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.02 | 62.95 | Tier 2 High GIDA (Score 40.0–49.9) | 71.47 | 49.96 | 71.47 |  | B - Node 0.5-1 km | 0.54 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1590
2 | 591 | 1591 | 1380300024 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | San Isidro | 14.5554 | 121.0071 | U | 3000 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 71.47 | 49.96 | 71.47 |  | B - Node 0.5-1 km | 0.78 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1591
2 | 592 | 1592 | 1380300001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Bangkal | 14.5428 | 121.0083 | U | 8647 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 71.46 | 49.96 | 71.46 |  | B - Node 0.5-1 km | 0.84 | 0.5 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1592
2 | 593 | 1593 | PH0001593 | NCR | Metro Manila | Taguig City | Comembo | 14.6341 | 120.9805 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.26 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 71.46 | 49.96 | 71.46 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1593
2 | 594 | 1594 | 1381100166 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 166 | 14.5359 | 121.0059 | U | 1224 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 71.46 | 49.96 | 71.46 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.25 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1594
2 | 595 | 1595 | PH0001595 | NCR | Metro Manila | Caloocan City | Barangay 23 | 14.6003 | 120.963 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.78 | 50.79 | Tier 2 High GIDA (Score 40.0–49.9) | 71.46 | 49.95 | 71.46 |  | B - Node 0.5-1 km | 0.74 | 0.99 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1595
2 | 596 | 1596 | 1380614073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 880 | 14.5862 | 121.0159 | U | 3521 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.77 | 7.78 | Tier 2 High GIDA (Score 40.0–49.9) | 71.45 | 49.95 | 71.45 |  | C - Line within 0.5 km; node over 1 km | 1.34 | 0.25 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1596
2 | 597 | 1597 | PH0001597 | NCR | Metro Manila | City of San Juan | Saint Joseph (Halo-halo) | 14.6341 | 120.9805 | R | 6395 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 71.45 | 49.95 | 71.45 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1597
2 | 598 | 1598 | 1380700006 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Nangka | 14.6732 | 121.1084 | U | 44819 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.44 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.44 | 49.94 | 71.44 |  | C - Line within 0.5 km; node over 1 km | 1.44 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1598
2 | 599 | 1599 | 0405811001 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid I | 14.6778 | 121.1168 | U | 26178 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.41 | Tier 2 High GIDA (Score 40.0–49.9) | 71.44 | 49.94 | 71.44 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.41 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1599
2 | 600 | 1600 | 0405805014 | Region IV-A (CALABARZON) | Rizal | Cainta | San Andres | 14.5741 | 121.1106 | U | 115400 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 71.43 | 49.94 | 71.43 |  | B - Node 0.5-1 km | 0.66 | 0.47 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1600
2 | 601 | 1601 | 0405811012 | Region IV-A (CALABARZON) | Rizal | San Mateo | Banaba | 14.6726 | 121.1128 | U | 26718 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 71.43 | 49.94 | 71.43 |  | C - Line within 0.5 km; node over 1 km | 1.62 | 0.38 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1601
2 | 602 | 1602 | 1380300013 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Magallanes | 14.5683 | 121.0281 | U | 2591 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.43 | 49.94 | 71.43 |  | A - Node within 0.5 km | 0.22 | 0.01 | Line: UG 144C via V-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1602
2 | 603 | 1603 | 0806016011 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Campeig | 12.0323 | 124.6987 | R | 84 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.94 | 83.77 | Tier 2 High GIDA (Score 40.0–49.9) | 71.43 | 49.94 | 71.43 |  | F - Nearest node and line over 5 km | 81.46 | 81.33 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1603
2 | 604 | 1604 | 0300807008 | Region III (Central Luzon) | Bataan | Mariveles | Poblacion | 14.4361 | 120.4841 | U | 8835 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.56 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 71.42 | 49.93 | 71.42 |  | C - Line within 0.5 km; node over 1 km | 1.56 | 0.29 | Line: 24 CORE 3X8 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1604
2 | 605 | 1605 | 0300811021 | Region III (Central Luzon) | Bataan | Pilar | Poblacion | 14.6674 | 120.5584 | R | 1369 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 71.42 | 49.93 | 71.42 |  | C - Line within 0.5 km; node over 1 km | 2.3 | 0.21 | Line: Pipe 2 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1605
2 | 606 | 1606 | PH0001606 | NCR | Metro Manila | Caloocan City | Barangay 3 | 14.6074 | 120.9689 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.67 | 21.44 | Tier 2 High GIDA (Score 40.0–49.9) | 71.42 | 49.93 | 71.42 |  | A - Node within 0.5 km | 0.1 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1606
2 | 607 | 1607 | 1381100115 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 115 | 14.5439 | 121.0016 | U | 1275 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 1.07 | Tier 2 High GIDA (Score 40.0–49.9) | 71.42 | 49.93 | 71.42 |  | B - Node 0.5-1 km | 0.78 | 0.21 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1607
2 | 608 | 1608 | 1381100147 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 147 | 14.5359 | 121.0068 | U | 1500 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.62 | 3.61 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | C - Line within 0.5 km; node over 1 km | 1.37 | 0.35 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1608
2 | 609 | 1609 | 0405801013 | Region IV-A (CALABARZON) | Rizal | Angono | Santo Niño | 14.5446 | 121.1552 | R | 2316 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 1.16 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | D - Other node or line within 3 km | 1.9 | 1 | Line: TAYTAY TO SNL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 1609
2 | 610 | 1610 | 0600409008 | Region VI (Western Visayas) | Aklan | Libacao | Casit-an | 11.4719 | 122.308 | R | 360 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12 | 11.94 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | F - Nearest node and line over 5 km | 12 | 11.92 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1610
2 | 611 | 1611 | 1380610044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 729 | 14.5725 | 120.9905 | U | 897 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.91 | 29.79 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | A - Node within 0.5 km | 0.41 | 0.2 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1611
2 | 612 | 1612 | 0806014015 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Hibaca-an | 12.0161 | 124.9935 | R | 449 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.26 | 86.19 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | F - Nearest node and line over 5 km | 86.26 | 86.19 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1612
2 | 613 | 1613 | PH0001613 | XI | Davao Del Sur | Davao City | Barangay 38-D (Pob.) | 7.5745 | 125.4478 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.04 | 1.17 | Tier 2 High GIDA (Score 40.0–49.9) | 71.41 | 49.92 | 71.41 |  | F - Nearest node and line over 5 km | 24.64 | 22.83 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1613
2 | 614 | 1614 | 0102934038 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VII | 17.5731 | 120.3826 | R | 1628 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.42 | 1.25 | Tier 2 High GIDA (Score 40.0–49.9) | 71.4 | 49.91 | 71.4 |  | D - Other node or line within 3 km | 2.42 | 1.13 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 1614
2 | 615 | 1615 | PH0001615 | VI | Iloilo | Iloilo City | Jereos | 10.7706 | 122.5908 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.01 | 0.77 | Tier 2 High GIDA (Score 40.0–49.9) | 71.4 | 49.91 | 71.4 |  | D - Other node or line within 3 km | 1.76 | 0.72 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 1615
2 | 616 | 1616 | 0102934039 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VIII | 17.5711 | 120.3608 | U | 1234 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.63 | 1.16 | Tier 2 High GIDA (Score 40.0–49.9) | 71.39 | 49.91 | 71.39 |  | E - Nearest node or line 3-5 km | 4.01 | 3.08 | Line: SEGMENT 3 (VIGAN - BATAC) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1616
2 | 617 | 1617 | 0200903001 | Region II (Cagayan Valley) | Batanes | Ivana | Radiwan | 20.3679 | 121.9144 | R | 391 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 213.4 | 208.97 | Tier 2 High GIDA (Score 40.0–49.9) | 71.39 | 49.91 | 71.39 |  | F - Nearest node and line over 5 km | 212.06 | 208.97 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1617
2 | 618 | 1618 | 1380300029 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Tejeros | 14.5643 | 121.0502 | U | 7440 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.09 | 0.03 | Tier 2 High GIDA (Score 40.0–49.9) | 71.37 | 49.9 | 71.37 |  | C - Line within 0.5 km; node over 1 km | 2.01 | 0.34 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1618
2 | 619 | 1619 | 1380500021 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Pag-asa | 14.586 | 121.0527 | U | 4591 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.29 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 71.36 | 49.89 | 71.36 |  | A - Node within 0.5 km | 0.43 | 0.36 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1619
2 | 620 | 1620 | 0806016036 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Matayonas | 12.1239 | 124.744 | R | 122 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.43 | 88.42 | Tier 2 High GIDA (Score 40.0–49.9) | 71.36 | 49.89 | 71.36 |  | F - Nearest node and line over 5 km | 88.43 | 88.4 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1620
2 | 621 | 1621 | 1380612019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 851 | 14.5879 | 121.0036 | U | 1084 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.01 | 45.63 | Tier 2 High GIDA (Score 40.0–49.9) | 71.36 | 49.89 | 71.36 |  | A - Node within 0.5 km | 0.4 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1621
2 | 622 | 1622 | 0806025018 | Region VIII (Eastern Visayas) | Samar | San Jorge | Matalud | 11.9995 | 124.9016 | R | 536 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.17 | 81.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.36 | 49.89 | 71.36 |  | F - Nearest node and line over 5 km | 81.17 | 81.12 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1622
2 | 623 | 1623 | 1380606057 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 451 | 14.6062 | 120.9971 | U | 1058 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.72 | 1.74 | Tier 2 High GIDA (Score 40.0–49.9) | 71.36 | 49.88 | 71.36 |  | B - Node 0.5-1 km | 0.72 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1623
2 | 624 | 1624 | 1381100184 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 184 | 14.5254 | 121.0144 | U | 14613 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 71.35 | 49.88 | 71.35 |  | A - Node within 0.5 km | 0.41 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1624
2 | 625 | 1625 | 0402106042 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Fe | 14.2802 | 120.9657 | U | 6647 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 1.46 | Tier 2 High GIDA (Score 40.0–49.9) | 71.35 | 49.88 | 71.35 |  | C - Line within 0.5 km; node over 1 km | 2.34 | 0.27 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1625
2 | 626 | 1626 | 1380601168 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 168 | 14.625 | 120.9733 | U | 1429 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.13 | 54.32 | Tier 2 High GIDA (Score 40.0–49.9) | 71.35 | 49.88 | 71.35 |  | A - Node within 0.5 km | 0.21 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1626
2 | 627 | 1627 | 1906603018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Kalingalan Caluang | Masjid Punjungan | 17.2555 | 122.2296 | R | 3769 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 71.34 | 49.87 | 71.34 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1627
2 | 628 | 1628 | 0600409007 | Region VI (Western Visayas) | Aklan | Libacao | Can-Awan | 11.4726 | 122.3081 | R | 437 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.76 | 14.65 | Tier 2 High GIDA (Score 40.0–49.9) | 71.34 | 49.87 | 71.34 |  | F - Nearest node and line over 5 km | 11.93 | 11.85 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1628
2 | 629 | 1629 | PH0001629 | CAR | Benguet | Baguio City | Magsaysay Private Road | 16.4157 | 120.6157 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.34 | 49.87 | 71.34 |  | C - Line within 0.5 km; node over 1 km | 1.65 | 0.03 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1629
2 | 630 | 1630 | 0402123002 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 1 Poblacion | 14.2974 | 121.0078 | U | 6913 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.78 | 4.79 | Tier 2 High GIDA (Score 40.0–49.9) | 71.34 | 49.87 | 71.34 |  | D - Other node or line within 3 km | 1.78 | 4.79 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1630
2 | 631 | 1631 | 1380610037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 722 | 14.5716 | 120.9912 | U | 660 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.22 | 18.14 | Tier 2 High GIDA (Score 40.0–49.9) | 71.33 | 49.87 | 71.33 |  | A - Node within 0.5 km | 0.33 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1631
2 | 632 | 1632 | 1381100143 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 143 | 14.5477 | 121.0075 | U | 1430 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 71.33 | 49.87 | 71.33 |  | A - Node within 0.5 km | 0.47 | 0.29 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1632
2 | 633 | 1633 | 1381100081 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 81 | 14.4401 | 121.0037 | U | 2190 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.19 | 2.86 | Tier 2 High GIDA (Score 40.0–49.9) | 71.33 | 49.87 | 71.33 |  | A - Node within 0.5 km | 0.34 | 0.16 | Line: UG | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1633
2 | 634 | 1634 | 0405622087 | Region IV-A (CALABARZON) | Quezon | Lopez | Vergaña | 13.8339 | 122.3722 | R | 874 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.08 | 2.67 | Tier 2 High GIDA (Score 40.0–49.9) | 71.33 | 49.86 | 71.33 |  | D - Other node or line within 3 km | 11.36 | 0.77 | Line: AE LZQ001 TO SNQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 1634
2 | 635 | 1635 | PH0001635 | XI | Davao Del Sur | Davao City | Barangay 29-C (Pob.) | 7.5228 | 125.5242 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 71.32 | 49.86 | 71.32 |  | F - Nearest node and line over 5 km | 27.61 | 26.93 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1635
2 | 636 | 1636 | 1380606197 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 590 | 14.6045 | 121.0109 | U | 3306 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.69 | 11.67 | Tier 2 High GIDA (Score 40.0–49.9) | 71.32 | 49.86 | 71.32 |  | B - Node 0.5-1 km | 0.74 | 0.23 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1636
2 | 637 | 1637 | PH0001637 | VIII | Samar (Western Samar) | Calbayog City | Ba-ay | 12.1516 | 124.4516 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.87 | 62.86 | Tier 2 High GIDA (Score 40.0–49.9) | 71.31 | 49.86 | 71.31 |  | F - Nearest node and line over 5 km | 62.87 | 62.83 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1637
2 | 638 | 1638 | 1380603010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 390 | 14.6007 | 120.9876 | U | 816 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.52 | 62.23 | Tier 2 High GIDA (Score 40.0–49.9) | 71.31 | 49.85 | 71.31 |  | A - Node within 0.5 km | 0.47 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1638
2 | 639 | 1639 | 1380614087 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 894 | 14.587 | 121.0176 | U | 1942 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.97 | 4.32 | Tier 2 High GIDA (Score 40.0–49.9) | 71.31 | 49.85 | 71.31 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.21 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1639
2 | 640 | 1640 | 1380607004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 640 | 14.5996 | 120.9948 | U | 2210 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.89 | 40.63 | Tier 2 High GIDA (Score 40.0–49.9) | 71.31 | 49.85 | 71.31 |  | B - Node 0.5-1 km | 0.55 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1640
2 | 641 | 1641 | 0401005067 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 20 | 13.7552 | 121.0545 | U | 393 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.85 | 71.3 |  | B - Node 0.5-1 km | 0.84 | 0.43 | Line: BCY001 TO LCQ001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1641
2 | 642 | 1642 | 1381300068 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Nagkaisang Nayon | 14.7236 | 121.025 | U | 56038 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.85 | 71.3 |  | C - Line within 0.5 km; node over 1 km | 1.85 | 0.21 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1642
2 | 643 | 1643 | 0806009018 | Region VIII (Eastern Visayas) | Samar | Jiabong | Malino | 11.845 | 124.9822 | R | 867 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.35 | 68.4 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.85 | 71.3 |  | F - Nearest node and line over 5 km | 67.35 | 68.4 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1643
2 | 644 | 1644 | 1381100149 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 149 | 14.5344 | 121.0074 | U | 790 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.74 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.85 | 71.3 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.4 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1644
2 | 645 | 1645 | 1381300079 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pasong Putik Proper | 14.7418 | 121.0655 | U | 41570 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.7 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.85 | 71.3 |  | D - Other node or line within 3 km | 1.3 | 0.7 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1645
2 | 646 | 1646 | 1381100046 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 46 | 14.5567 | 120.9987 | U | 5947 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 1.87 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.84 | 71.3 |  | B - Node 0.5-1 km | 0.85 | 0.21 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1646
2 | 647 | 1647 | 0205007022 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Macabenga | 16.2108 | 121.2328 | R | 1807 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 21.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.3 | 49.84 | 71.3 |  | A - Node within 0.5 km | 0.41 | 21.28 | Node: DNV002 - TYPE 4A | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1647
2 | 648 | 1648 | 0806016013 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Canmoros | 12.0562 | 124.7307 | R | 217 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.23 | 84.21 | Tier 2 High GIDA (Score 40.0–49.9) | 71.29 | 49.84 | 71.29 |  | F - Nearest node and line over 5 km | 84.23 | 84.2 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1648
2 | 649 | 1649 | 1381100151 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 151 | 14.5365 | 121.008 | U | 1208 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 71.29 | 49.84 | 71.29 |  | C - Line within 0.5 km; node over 1 km | 1.51 | 0.49 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1649
2 | 650 | 1650 | 0806009013 | Region VIII (Eastern Visayas) | Samar | Jiabong | Hinaga | 11.7624 | 124.9502 | R | 289 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.4 | 58.64 | Tier 2 High GIDA (Score 40.0–49.9) | 71.29 | 49.84 | 71.29 |  | F - Nearest node and line over 5 km | 58.4 | 58.64 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1650
2 | 651 | 1651 | 1380900004 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Bangculasi | 14.6512 | 120.9527 | U | 8524 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.85 | 0.66 | Tier 2 High GIDA (Score 40.0–49.9) | 71.29 | 49.84 | 71.29 |  | B - Node 0.5-1 km | 0.85 | 2.16 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1651
2 | 652 | 1652 | 1380606060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 454 | 14.6072 | 121.0001 | U | 1188 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.24 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 71.28 | 49.83 | 71.28 |  | B - Node 0.5-1 km | 0.57 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1652
2 | 653 | 1653 | 1380612025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 857 | 14.59 | 121.0049 | U | 1952 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 71.28 | 49.83 | 71.28 |  | B - Node 0.5-1 km | 0.67 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1653
2 | 654 | 1654 | 0806009011 | Region VIII (Eastern Visayas) | Samar | Jiabong | Dogongan | 11.9107 | 124.9939 | R | 496 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.63 | 75.51 | Tier 2 High GIDA (Score 40.0–49.9) | 71.27 | 49.83 | 71.27 |  | F - Nearest node and line over 5 km | 74.63 | 75.51 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1654
2 | 655 | 1655 | 1381100037 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 37 | 14.5611 | 120.9966 | U | 1572 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 71.27 | 49.83 | 71.27 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.11 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1655
2 | 656 | 1656 | 0402106069 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco II | 14.3505 | 121.0012 | R | 3540 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 2.35 | Tier 2 High GIDA (Score 40.0–49.9) | 71.27 | 49.82 | 71.27 |  | B - Node 0.5-1 km | 0.92 | 4.05 | Node: MUN048 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1656
2 | 657 | 1657 | 0401005076 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 7 | 13.7609 | 121.0613 | U | 463 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 71.26 | 49.82 | 71.26 |  | B - Node 0.5-1 km | 0.51 | 0.23 | Line: UG SSB001 TO BCY001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1657
2 | 658 | 1658 | 1380601148 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 148 | 14.6322 | 120.9658 | U | 2404 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.18 | 61.89 | Tier 2 High GIDA (Score 40.0–49.9) | 71.26 | 49.82 | 71.26 |  | D - Other node or line within 3 km | 1.01 | 0.94 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1658
2 | 659 | 1659 | 1380200008 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Uno | 14.4385 | 121.0024 | U | 43154 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.36 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 71.26 | 49.82 | 71.26 |  | A - Node within 0.5 km | 0.36 | 0.07 | Line: UG 144C via B-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1659
2 | 660 | 1660 | 0401005078 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 9 | 13.7449 | 121.0882 | U | 264 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.45 | 4.83 | Tier 2 High GIDA (Score 40.0–49.9) | 71.25 | 49.81 | 71.25 |  | D - Other node or line within 3 km | 2.53 | 3.01 | Node: BCY003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1660
2 | 661 | 1661 | PH0001661 | NCR | Metro Manila | Caloocan City | Barangay 76 | 14.612 | 120.9665 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.19 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 71.25 | 49.81 | 71.25 |  | B - Node 0.5-1 km | 0.67 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1661
2 | 662 | 1662 | 1381200021 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Jose | 14.5649 | 121.0662 | U | 1927 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.89 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 71.25 | 49.81 | 71.25 |  | C - Line within 0.5 km; node over 1 km | 1.65 | 0.34 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1662
2 | 663 | 1663 | 1380606132 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 526 | 14.611 | 120.9987 | U | 814 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.54 | 9.1 | Tier 2 High GIDA (Score 40.0–49.9) | 71.25 | 49.81 | 71.25 |  | B - Node 0.5-1 km | 0.54 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1663
2 | 664 | 1664 | 1408104016 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Magabta | 18.028 | 121.1999 | R | 194 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.2 | 9.04 | Tier 2 High GIDA (Score 40.0–49.9) | 71.24 | 49.8 | 71.24 |  | D - Other node or line within 3 km | 2.2 | 28.91 | Node: KOY001 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 1664
2 | 665 | 1665 | 1381100002 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 2 | 14.5592 | 120.9899 | U | 1365 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.72 | 4.73 | Tier 2 High GIDA (Score 40.0–49.9) | 71.24 | 49.8 | 71.24 |  | B - Node 0.5-1 km | 0.68 | 0.63 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1665
2 | 666 | 1666 | 1381100087 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 87 | 14.5435 | 120.9948 | U | 651 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.94 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 71.24 | 49.8 | 71.24 |  | A - Node within 0.5 km | 0.12 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1666
2 | 667 | 1667 | 1381100131 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 131 | 14.5494 | 121.0074 | U | 1468 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.6 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 71.24 | 49.8 | 71.24 |  | A - Node within 0.5 km | 0.43 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1667
2 | 668 | 1668 | 0401005059 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 13 | 13.7109 | 121.0927 | U | 357 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.86 | 4.05 | Tier 2 High GIDA (Score 40.0–49.9) | 71.24 | 49.8 | 71.24 |  | E - Nearest node or line 3-5 km | 4.14 | 6.02 | Node: BCY004 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1668
2 | 669 | 1669 | 1381100089 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 89 | 14.5455 | 120.9954 | U | 1032 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.19 | 1.57 | Tier 2 High GIDA (Score 40.0–49.9) | 71.23 | 49.8 | 71.23 |  | A - Node within 0.5 km | 0.15 | 0.13 | Line: Existing 216C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1669
2 | 670 | 1670 | 1102504006 | Region XI (Davao Region) | Davao Oriental | Caraga | Manorigao | 7.4019 | 126.5492 | R | 1700 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.83 | 60.75 | Tier 2 High GIDA (Score 40.0–49.9) | 71.23 | 49.79 | 71.23 |  | F - Nearest node and line over 5 km | 61.83 | 60.58 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1670
2 | 671 | 1671 | 0402118052 | Region IV-A (CALABARZON) | Cavite | Silang | Narra I | 14.2824 | 120.9602 | R | 3334 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.68 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 71.22 | 49.79 | 71.22 |  | C - Line within 0.5 km; node over 1 km | 1.97 | 0.08 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1671
2 | 672 | 1672 | 1380610019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 704 | 14.5699 | 120.9872 | U | 5460 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.34 | 23.36 | Tier 2 High GIDA (Score 40.0–49.9) | 71.22 | 49.79 | 71.22 |  | B - Node 0.5-1 km | 0.8 | 0.47 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1672
2 | 673 | 1673 | 1380606193 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 587 | 14.6034 | 121.0125 | U | 3009 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.56 | 53.13 | Tier 2 High GIDA (Score 40.0–49.9) | 71.22 | 49.79 | 71.22 |  | B - Node 0.5-1 km | 0.88 | 0.09 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1673
2 | 674 | 1674 | 1381100186 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 186 | 14.5333 | 120.999 | U | 3548 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 71.22 | 49.79 | 71.22 |  | B - Node 0.5-1 km | 0.63 | 0.12 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1674
2 | 675 | 1675 | 1380603018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 309 | 14.6102 | 120.9929 | U | 1186 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.06 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 71.21 | 49.78 | 71.21 |  | B - Node 0.5-1 km | 0.8 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1675
2 | 676 | 1676 | 1381100055 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 55 | 14.5526 | 121.0002 | U | 856 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.28 | 4.25 | Tier 2 High GIDA (Score 40.0–49.9) | 71.21 | 49.78 | 71.21 |  | B - Node 0.5-1 km | 0.92 | 0.25 | Line: Existing 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1676
2 | 677 | 1677 | 1380611036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 821 | 14.5806 | 120.9974 | U | 2056 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.2 | 50.69 | Tier 2 High GIDA (Score 40.0–49.9) | 71.21 | 49.78 | 71.21 |  | B - Node 0.5-1 km | 0.72 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1677
2 | 678 | 1678 | 1380610025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 710 | 14.572 | 120.9885 | U | 576 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.83 | 22.55 | Tier 2 High GIDA (Score 40.0–49.9) | 71.2 | 49.78 | 71.2 |  | B - Node 0.5-1 km | 0.61 | 0.35 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1678
2 | 679 | 1679 | 1381100039 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 39 | 14.5631 | 120.9972 | U | 1327 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 71.2 | 49.78 | 71.2 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.04 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1679
2 | 680 | 1680 | 1381100017 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 17 | 14.5588 | 120.9926 | U | 1013 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.4 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 71.2 | 49.78 | 71.2 |  | B - Node 0.5-1 km | 0.62 | 0.35 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1680
2 | 681 | 1681 | 1380606079 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 473 | 14.6132 | 120.9926 | U | 1425 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 4.03 | Tier 2 High GIDA (Score 40.0–49.9) | 71.19 | 49.77 | 71.19 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.24 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1681
2 | 682 | 1682 | 0806014008 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Hiduroma | 12.0011 | 125.0337 | R | 280 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.74 | 86.46 | Tier 2 High GIDA (Score 40.0–49.9) | 71.19 | 49.77 | 71.19 |  | F - Nearest node and line over 5 km | 84.74 | 86.46 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1682
2 | 683 | 1683 | 1380610062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 737 | 14.5693 | 121.004 | U | 2276 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.68 | 67 | Tier 2 High GIDA (Score 40.0–49.9) | 71.19 | 49.77 | 71.19 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.18 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1683
2 | 684 | 1684 | 1381300062 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Marilag | 14.6255 | 121.0696 | U | 13082 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.13 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.19 | 49.77 | 71.19 |  | A - Node within 0.5 km | 0.13 | 0.04 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1684
2 | 685 | 1685 | 1380606109 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 503 | 14.6206 | 120.9959 | U | 1219 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.96 | 3.87 | Tier 2 High GIDA (Score 40.0–49.9) | 71.18 | 49.76 | 71.18 |  | D - Other node or line within 3 km | 1.37 | 0.74 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1685
2 | 686 | 1686 | 1380611042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 827 | 14.5822 | 120.9986 | U | 2742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.15 | 35.08 | Tier 2 High GIDA (Score 40.0–49.9) | 71.18 | 49.76 | 71.18 |  | B - Node 0.5-1 km | 0.51 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1686
2 | 687 | 1687 | 1381100091 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 91 | 14.5441 | 120.996 | U | 1934 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.04 | 5.1 | Tier 2 High GIDA (Score 40.0–49.9) | 71.18 | 49.76 | 71.18 |  | A - Node within 0.5 km | 0.18 | 0.17 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1687
2 | 688 | 1688 | 0401005070 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 23 | 13.7765 | 121.0441 | U | 717 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.98 | 6.5 | Tier 2 High GIDA (Score 40.0–49.9) | 71.18 | 49.76 | 71.18 |  | C - Line within 0.5 km; node over 1 km | 1.35 | 0.05 | Line: LEMERY TO SAN JUAN CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1688
2 | 689 | 1689 | 1381100083 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 83 | 14.5464 | 120.9971 | U | 817 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 71.17 | 49.76 | 71.17 |  | A - Node within 0.5 km | 0.35 | 0.19 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1689
2 | 690 | 1690 | PH0001690 | XI | Davao de Oro | Mabini Compostela Valley | Cabuyuan | 7.3146 | 125.8755 | R | 2247 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.7 | 19.19 | Tier 2 High GIDA (Score 40.0–49.9) | 71.17 | 49.76 | 71.17 |  | D - Other node or line within 3 km | 2.29 | 1.9 | Line: TAGUM - PANTUKAN SEGMENT 2 | Route options survey candidate: compare actual node lateral with approved line tap. | 1690
2 | 691 | 1691 | 1380601135 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 135 | 14.6273 | 120.9654 | U | 1994 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.57 | 41.96 | Tier 2 High GIDA (Score 40.0–49.9) | 71.17 | 49.75 | 71.17 |  | B - Node 0.5-1 km | 0.86 | 0.76 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1691
2 | 692 | 1692 | 1380611048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 686 | 14.5821 | 120.9939 | U | 3349 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.77 | 0.84 | Tier 2 High GIDA (Score 40.0–49.9) | 71.17 | 49.75 | 71.17 |  | B - Node 0.5-1 km | 0.98 | 0.36 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1692
2 | 693 | 1693 | 1380606058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 452 | 14.605 | 120.9997 | U | 1071 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.42 | 59.55 | Tier 2 High GIDA (Score 40.0–49.9) | 71.16 | 49.75 | 71.16 |  | B - Node 0.5-1 km | 0.62 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1693
2 | 694 | 1694 | 1381100158 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 158 | 14.5349 | 121.0084 | U | 988 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.13 | 0.7 | Tier 2 High GIDA (Score 40.0–49.9) | 71.15 | 49.74 | 71.15 |  | D - Other node or line within 3 km | 1.44 | 0.51 | Line: Existing 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1694
2 | 695 | 1695 | 1907011016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Ungus-ungus | 17.2556 | 122.2292 | R | 2621 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.12 | 28.9 | Tier 2 High GIDA (Score 40.0–49.9) | 71.15 | 49.74 | 71.15 |  | F - Nearest node and line over 5 km | 29.49 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1695
2 | 696 | 1696 | 1380606134 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 528 | 14.6132 | 120.9992 | U | 1477 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.06 | 13.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.15 | 49.74 | 71.15 |  | B - Node 0.5-1 km | 0.56 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1696
2 | 697 | 1697 | 1380611030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 816 | 14.5782 | 121.0023 | U | 805 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.25 | 16.3 | Tier 2 High GIDA (Score 40.0–49.9) | 71.14 | 49.74 | 71.14 |  | B - Node 0.5-1 km | 0.69 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1697
2 | 698 | 1698 | 1704001055 | MIMAROPA Region | Marinduque | Boac | Tambunan | 13.3074 | 121.9855 | R | 544 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.93 | 44.96 | Tier 2 High GIDA (Score 40.0–49.9) | 71.14 | 49.74 | 71.14 |  | F - Nearest node and line over 5 km | 45.93 | 44.9 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1698
2 | 699 | 1699 | 1381300043 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Gulod | 14.7179 | 121.0395 | U | 65167 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 71.14 | 49.74 | 71.14 |  | A - Node within 0.5 km | 0.5 | 0.06 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1699
2 | 700 | 1700 | 0102929002 | Region I (Ilocos Region) | Ilocos Sur | Sigay | Mabileg | 17.0336 | 120.5828 | R | 321 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.92 | 12.19 | Tier 2 High GIDA (Score 40.0–49.9) | 71.14 | 49.73 | 71.14 |  | F - Nearest node and line over 5 km | 5.92 | 11.8 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1700
2 | 701 | 1701 | 0103305019 | Region I (Ilocos Region) | La Union | Balaoan | Nagsabaran Sur | 16.7785 | 120.3842 | R | 1223 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.42 | 2.23 | Tier 2 High GIDA (Score 40.0–49.9) | 71.14 | 49.73 | 71.14 |  | D - Other node or line within 3 km | 4.42 | 2.22 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Route options survey candidate: compare actual node lateral with approved line tap. | 1701
2 | 702 | 1702 | 1381100138 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 138 | 14.5478 | 121.0078 | U | 1060 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.13 | 49.73 | 71.13 |  | A - Node within 0.5 km | 0.45 | 0.28 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1702
2 | 703 | 1703 | 1380614064 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 866 | 14.5826 | 121.0071 | U | 3951 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.77 | 60.74 | Tier 2 High GIDA (Score 40.0–49.9) | 71.13 | 49.72 | 71.13 |  | B - Node 0.5-1 km | 0.51 | 0.27 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1703
2 | 704 | 1704 | 1381400011 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Onse | 14.6018 | 121.0302 | U | 3972 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.6 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | C - Line within 0.5 km; node over 1 km | 1.6 | 0.22 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1704
2 | 705 | 1705 | 1380606203 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 596 | 14.594 | 121.0183 | U | 2447 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.15 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | D - Other node or line within 3 km | 1.56 | 0.71 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1705
2 | 706 | 1706 | 1381100117 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 117 | 14.546 | 121.0022 | U | 962 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.23 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | B - Node 0.5-1 km | 0.85 | 0.24 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1706
2 | 707 | 1707 | 1381100012 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 12 | 14.5589 | 120.9894 | U | 555 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.87 | 6.84 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | B - Node 0.5-1 km | 0.68 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1707
2 | 708 | 1708 | PH0001708 | III | Nueva Ecija | Cabanatuan City | City Supermarket (Pob.) | 15.4754 | 120.9608 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.54 | 1.29 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | B - Node 0.5-1 km | 0.71 | 0.29 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1708
2 | 709 | 1709 | 1380601141 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 141 | 14.6313 | 120.9666 | U | 545 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.43 | 46.17 | Tier 2 High GIDA (Score 40.0–49.9) | 71.12 | 49.72 | 71.12 |  | B - Node 0.5-1 km | 0.88 | 0.82 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1709
2 | 710 | 1710 | 1380601255 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 254 | 14.6113 | 120.9767 | U | 3826 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.75 | 29.47 | Tier 2 High GIDA (Score 40.0–49.9) | 71.11 | 49.72 | 71.11 |  | B - Node 0.5-1 km | 0.88 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1710
2 | 711 | 1711 | 1381100042 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 42 | 14.561 | 120.9963 | U | 1878 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 71.11 | 49.71 | 71.11 |  | B - Node 0.5-1 km | 0.99 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1711
2 | 712 | 1712 | PH0001712 | CAR | Benguet | Baguio City | Teodora Alonzo | 16.4251 | 120.6089 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.08 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 71.11 | 49.71 | 71.11 |  | D - Other node or line within 3 km | 1.62 | 1.11 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 1712
2 | 713 | 1713 | PH0001713 | XI | Davao Del Sur | Davao City | Barangay 23-C (Pob.) | 7.0716 | 125.6257 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 71.11 | 49.71 | 71.11 |  | D - Other node or line within 3 km | 1.5 | 1.49 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 1713
2 | 714 | 1714 | PH0001714 | IV-B | Palawan | Puerto Princesa City | Maligaya (Pob.) | 9.9076 | 118.7 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.87 | 4.35 | Tier 2 High GIDA (Score 40.0–49.9) | 71.1 | 49.71 | 71.1 |  | C - Line within 0.5 km; node over 1 km | 4.14 | 0.39 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1714
2 | 715 | 1715 | 1381100059 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 59 | 14.5522 | 120.9997 | U | 1704 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.44 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.1 | 49.71 | 71.1 |  | B - Node 0.5-1 km | 0.87 | 0.2 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1715
2 | 716 | 1716 | 1381100134 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 134 | 14.5472 | 121.0066 | U | 1734 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 3.33 | Tier 2 High GIDA (Score 40.0–49.9) | 71.09 | 49.7 | 71.09 |  | B - Node 0.5-1 km | 0.59 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1716
2 | 717 | 1717 | PH0001717 | XI | Davao Del Sur | Davao City | Barangay 34-D (Pob.) | 7.5586 | 125.4768 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.36 | 3.54 | Tier 2 High GIDA (Score 40.0–49.9) | 71.09 | 49.7 | 71.09 |  | F - Nearest node and line over 5 km | 26.92 | 25.42 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1717
2 | 718 | 1718 | 1381100156 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 156 | 14.5363 | 121.0078 | U | 3641 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 71.09 | 49.7 | 71.09 |  | C - Line within 0.5 km; node over 1 km | 1.48 | 0.46 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1718
2 | 719 | 1719 | 1380601063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 63 | 14.612 | 120.9664 | U | 1492 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.18 | 2.08 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.7 | 71.08 |  | B - Node 0.5-1 km | 0.68 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1719
2 | 720 | 1720 | 1380606076 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 470 | 14.6121 | 120.9943 | U | 2329 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.36 | 66.74 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.7 | 71.08 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1720
2 | 721 | 1721 | PH0001721 | VIII | Samar (Western Samar) | Calbayog City | Bugtong | 12.2569 | 124.3691 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.13 | 48.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.69 | 71.08 |  | F - Nearest node and line over 5 km | 48.13 | 48.1 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1721
2 | 722 | 1722 | 1381100090 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 90 | 14.5448 | 120.9975 | U | 1661 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 3.2 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.69 | 71.08 |  | A - Node within 0.5 km | 0.33 | 0.19 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1722
2 | 723 | 1723 | 1380606240 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 633 | 14.5989 | 121 | U | 461 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.32 | 3.75 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.69 | 71.08 |  | B - Node 0.5-1 km | 0.6 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1723
2 | 724 | 1724 | 1380700003 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Concepcion Uno | 14.6478 | 121.1035 | U | 46179 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.69 | 71.08 |  | B - Node 0.5-1 km | 0.9 | 0.25 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1724
2 | 725 | 1725 | 1380606237 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 630 | 14.6002 | 121.0039 | U | 4802 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.76 | 28.81 | Tier 2 High GIDA (Score 40.0–49.9) | 71.08 | 49.69 | 71.08 |  | A - Node within 0.5 km | 0.22 | 0.17 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1725
2 | 726 | 1726 | 0603014004 | Region VI (Western Visayas) | Iloilo | Carles | Bancal | 11.5586 | 123.1532 | U | 5937 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.55 | 11.48 | Tier 2 High GIDA (Score 40.0–49.9) | 71.07 | 49.69 | 71.07 |  | F - Nearest node and line over 5 km | 11.55 | 11.45 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1726
2 | 727 | 1727 | 1381100049 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 49 | 14.5581 | 120.9979 | U | 298 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 71.07 | 49.69 | 71.07 |  | B - Node 0.5-1 km | 0.85 | 0.18 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1727
2 | 728 | 1728 | 1380611034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 819 | 14.5792 | 121.0006 | U | 2068 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.73 | 50.13 | Tier 2 High GIDA (Score 40.0–49.9) | 71.06 | 49.68 | 71.06 |  | B - Node 0.5-1 km | 0.62 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1728
2 | 729 | 1729 | 1380601127 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 127 | 14.6099 | 120.9629 | U | 582 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 3.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.06 | 49.68 | 71.06 |  | B - Node 0.5-1 km | 0.81 | 0.66 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1729
2 | 730 | 1730 | 1380601002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 2 | 14.6086 | 120.9663 | U | 1944 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.77 | 56.21 | Tier 2 High GIDA (Score 40.0–49.9) | 71.06 | 49.68 | 71.06 |  | A - Node within 0.5 km | 0.41 | 0.3 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1730
2 | 731 | 1731 | 1380605041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 339 | 14.6193 | 120.9864 | U | 1303 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.34 | 16.86 | Tier 2 High GIDA (Score 40.0–49.9) | 71.06 | 49.68 | 71.06 |  | A - Node within 0.5 km | 0.49 | 0.24 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1731
2 | 732 | 1732 | 1908701006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Barira | Liong | 17.2539 | 122.2279 | R | 5838 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 71.05 | 49.67 | 71.05 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1732
2 | 733 | 1733 | 1380700007 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Parang | 14.666 | 121.1179 | U | 41587 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 0.68 | Tier 2 High GIDA (Score 40.0–49.9) | 71.05 | 49.67 | 71.05 |  | D - Other node or line within 3 km | 1.61 | 0.64 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1733
2 | 734 | 1734 | 1380610020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 705 | 14.5687 | 120.9897 | U | 2764 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.27 | 8.87 | Tier 2 High GIDA (Score 40.0–49.9) | 71.04 | 49.67 | 71.04 |  | B - Node 0.5-1 km | 0.61 | 0.26 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1734
2 | 735 | 1735 | 1400120001 | Cordillera Administrative Region (CAR) | Abra | Sallapadan | Bazar | 17.4656 | 120.8127 | R | 506 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.92 | 23.81 | Tier 2 High GIDA (Score 40.0–49.9) | 71.04 | 49.67 | 71.04 |  | F - Nearest node and line over 5 km | 24.92 | 23.81 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1735
2 | 736 | 1736 | 1381600016 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Malanday | 14.717 | 120.9556 | U | 19332 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 71.04 | 49.67 | 71.04 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.18 | Line: 48 CORE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1736
2 | 737 | 1737 | 1381701009 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santo Rosario-Silangan | 14.5474 | 121.0722 | U | 4844 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.76 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 71.04 | 49.66 | 71.04 |  | B - Node 0.5-1 km | 0.52 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1737
2 | 738 | 1738 | 1381100080 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 80 | 14.5425 | 120.9975 | U | 1242 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.85 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 71.04 | 49.66 | 71.04 |  | A - Node within 0.5 km | 0.4 | 0.24 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1738
2 | 739 | 1739 | 1381100050 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 50 | 14.5527 | 121.0005 | U | 492 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.4 | 7.61 | Tier 2 High GIDA (Score 40.0–49.9) | 71.03 | 49.66 | 71.03 |  | B - Node 0.5-1 km | 0.95 | 0.24 | Line: Existing 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1739
2 | 740 | 1740 | 1705304006 | MIMAROPA Region | Palawan | Balabac | Catagupan | 7.9807 | 116.9719 | R | 3097 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 275.24 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 71.03 | 49.66 | 71.03 |  | F - Nearest node and line over 5 km | 275.24 | 277.24 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1740
2 | 741 | 1741 | 1908806022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Salendab | 17.2552 | 122.2293 | R | 1199 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.48 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 71.03 | 49.66 | 71.03 |  | F - Nearest node and line over 5 km | 29.48 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1741
2 | 742 | 1742 | 1380500012 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Harapin Ang Bukas | 14.5793 | 121.0432 | U | 4644 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 71.03 | 49.65 | 71.03 |  | B - Node 0.5-1 km | 0.93 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1742
2 | 743 | 1743 | 0102806007 | Region I (Ilocos Region) | Ilocos Norte | Burgos | Buduan | 18.5014 | 120.6309 | R | 954 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.15 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 71.02 | 49.65 | 71.02 |  | D - Other node or line within 3 km | 2.15 | 1.12 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 1743
2 | 744 | 1744 | 0806022014 | Region VIII (Eastern Visayas) | Samar | Paranas | Cawayan | 11.7747 | 125.0212 | R | 351 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.52 | 64.5 | Tier 2 High GIDA (Score 40.0–49.9) | 71.02 | 49.65 | 71.02 |  | F - Nearest node and line over 5 km | 59.54 | 62.52 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1744
2 | 745 | 1745 | PH0001745 | CAR | Benguet | Baguio City | Camdas Subdivision | 16.3902 | 120.5939 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 71.02 | 49.65 | 71.02 |  | D - Other node or line within 3 km | 1.36 | 1.18 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 1745
2 | 746 | 1746 | PH0001746 | CAR | Benguet | Baguio City | Magsaysay, Lower | 16.4219 | 120.5953 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.1 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 71.02 | 49.65 | 71.02 |  | A - Node within 0.5 km | 0.44 | 0.81 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1746
2 | 747 | 1747 | 1381000001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Baclaran | 14.5298 | 120.9989 | U | 34500 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 71.02 | 49.65 | 71.02 |  | A - Node within 0.5 km | 0.28 | 0.19 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1747
2 | 748 | 1748 | 1381300088 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 3-A | 14.6906 | 121.0991 | U | 1115 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 71.01 | 49.65 | 71.01 |  | B - Node 0.5-1 km | 0.87 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1748
2 | 749 | 1749 | 1380610034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 719 | 14.5705 | 120.9882 | U | 6893 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.33 | 2.18 | Tier 2 High GIDA (Score 40.0–49.9) | 71.01 | 49.64 | 71.01 |  | B - Node 0.5-1 km | 0.67 | 0.35 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1749
2 | 750 | 1750 | 1381100044 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 44 | 14.5567 | 120.9971 | U | 1457 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 71.01 | 49.64 | 71.01 |  | B - Node 0.5-1 km | 0.69 | 0.06 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1750
2 | 751 | 1751 | 1380601142 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 142 | 14.6301 | 120.9691 | U | 1762 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.9 | 40.84 | Tier 2 High GIDA (Score 40.0–49.9) | 71.01 | 49.64 | 71.01 |  | B - Node 0.5-1 km | 0.58 | 0.53 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1751
2 | 752 | 1752 | 1380601224 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 223 | 14.6236 | 120.9806 | U | 1678 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.69 | 37.74 | Tier 2 High GIDA (Score 40.0–49.9) | 71.01 | 49.64 | 71.01 |  | B - Node 0.5-1 km | 0.83 | 0.15 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1752
2 | 753 | 1753 | 1380601083 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 83 | 14.6169 | 120.9687 | U | 1518 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.45 | 5.34 | Tier 2 High GIDA (Score 40.0–49.9) | 71 | 49.64 | 71 |  | B - Node 0.5-1 km | 0.65 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1753
2 | 754 | 1754 | 1381100014 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 14 | 14.5575 | 120.99 | U | 4905 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 71 | 49.64 | 71 |  | B - Node 0.5-1 km | 0.5 | 0.49 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1754
2 | 755 | 1755 | 1380601218 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 217 | 14.6215 | 120.9793 | U | 1301 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.94 | 61.54 | Tier 2 High GIDA (Score 40.0–49.9) | 71 | 49.64 | 71 |  | B - Node 0.5-1 km | 0.68 | 0.06 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1755
2 | 756 | 1756 | 1380400009 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Ibaba | 14.6654 | 120.9506 | U | 8240 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 71 | 49.63 | 71 |  | B - Node 0.5-1 km | 0.9 | 0.57 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1756
2 | 757 | 1757 | 1380611043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 828 | 14.5815 | 120.9967 | U | 2739 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.7 | 7.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.99 | 49.63 | 70.99 |  | B - Node 0.5-1 km | 0.73 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1757
2 | 758 | 1758 | 1381100190 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 190 | 14.5339 | 121.0002 | U | 4459 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.57 | 0.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.99 | 49.63 | 70.99 |  | B - Node 0.5-1 km | 0.75 | 0.18 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1758
2 | 759 | 1759 | 0806002019 | Region VIII (Eastern Visayas) | Samar | Basey | Inuntan | 11.3553 | 125.145 | R | 649 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.18 | 21.48 | Tier 2 High GIDA (Score 40.0–49.9) | 70.98 | 49.62 | 70.98 |  | F - Nearest node and line over 5 km | 20.18 | 21.71 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1759
2 | 760 | 1760 | 1380612013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 845 | 14.5883 | 121.0003 | U | 1349 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.94 | 21.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.98 | 49.62 | 70.98 |  | B - Node 0.5-1 km | 0.51 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1760
2 | 761 | 1761 | 1380601247 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 246 | 14.6114 | 120.9787 | U | 1292 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.55 | 58.43 | Tier 2 High GIDA (Score 40.0–49.9) | 70.98 | 49.62 | 70.98 |  | B - Node 0.5-1 km | 0.72 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1761
2 | 762 | 1762 | PH0001762 | XI | Davao Del Sur | Davao City | Barangay 25-C (Pob.) | 7.1887 | 125.4511 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.98 | 49.62 | 70.98 |  | B - Node 0.5-1 km | 0.51 | 0.28 | Line: 31,493 FOC | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1762
2 | 763 | 1763 | 0506210013 | Region V (Bicol Region) | Sorsogon | Juban | Embarcadero | 12.8549 | 123.9884 | R | 1368 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.38 | 0.71 | Tier 2 High GIDA (Score 40.0–49.9) | 70.97 | 49.62 | 70.97 |  | D - Other node or line within 3 km | 3.38 | 0.7 | Line: SORSOGON - MATNOG | Route options survey candidate: compare actual node lateral with approved line tap. | 1763
2 | 764 | 1764 | 1380612011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 843 | 14.586 | 120.9998 | U | 9010 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.49 | 3.83 | Tier 2 High GIDA (Score 40.0–49.9) | 70.97 | 49.62 | 70.97 |  | A - Node within 0.5 km | 0.36 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1764
2 | 765 | 1765 | 1381100040 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 40 | 14.5624 | 120.9957 | U | 2377 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.97 | 49.62 | 70.97 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1765
2 | 766 | 1766 | 1381100076 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 76 | 14.5419 | 120.9963 | U | 20161 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 1.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.97 | 49.62 | 70.97 |  | A - Node within 0.5 km | 0.36 | 0.15 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1766
2 | 767 | 1767 | 0203102053 | Region II (Cagayan Valley) | Isabela | Angadanan | San Vicente | 16.713 | 121.7821 | R | 513 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.11 | 9.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.97 | 49.61 | 70.97 |  | F - Nearest node and line over 5 km | 5.11 | 9.96 | Node: ANI002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1767
2 | 768 | 1768 | 1900707021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Duga-a | 6.6054 | 122.2022 | R | 4167 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.75 | 36.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.96 | 49.61 | 70.96 |  | F - Nearest node and line over 5 km | 36.75 | 36.74 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1768
2 | 769 | 1769 | PH0001769 | XI | Davao Del Sur | Davao City | Barangay 30-C (Pob.) | 7.0662 | 125.5981 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.4 | 2.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.96 | 49.61 | 70.96 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.33 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1769
2 | 770 | 1770 | 1380614014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 758 | 14.5673 | 121.0064 | U | 411 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.26 | 51.97 | Tier 2 High GIDA (Score 40.0–49.9) | 70.96 | 49.61 | 70.96 |  | C - Line within 0.5 km; node over 1 km | 1.41 | 0.06 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1770
2 | 771 | 1771 | 1381100145 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 145 | 14.5463 | 121.0047 | U | 9007 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.93 | 5.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | B - Node 0.5-1 km | 0.82 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1771
2 | 772 | 1772 | 1380605071 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 368 | 14.627 | 120.9859 | U | 1378 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.87 | 24.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.04 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1772
2 | 773 | 1773 | 0401005056 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 10 | 13.7333 | 121.1535 | U | 270 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.11 | 3.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | D - Other node or line within 3 km | 2.53 | 8.62 | Node: BCY007-PM | Route options survey candidate: compare actual node lateral with approved line tap. | 1773
2 | 774 | 1774 | 1380606118 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 512 | 14.6222 | 120.9975 | U | 2548 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | D - Other node or line within 3 km | 1.42 | 0.78 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 1774
2 | 775 | 1775 | 1380614059 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 803 | 14.5798 | 121.0016 | U | 1757 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.86 | 69.23 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | B - Node 0.5-1 km | 0.52 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1775
2 | 776 | 1776 | 1380603006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 386 | 14.5936 | 120.9891 | U | 1250 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | B - Node 0.5-1 km | 0.62 | 0.52 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1776
2 | 777 | 1777 | 1380601149 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 149 | 14.631 | 120.9684 | U | 1601 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.73 | 34.78 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | B - Node 0.5-1 km | 0.71 | 0.65 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1777
2 | 778 | 1778 | 0405622014 | Region IV-A (CALABARZON) | Quezon | Lopez | Binahian C | 13.8289 | 122.2906 | R | 166 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.7 | 4.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.95 | 49.6 | 70.95 |  | E - Nearest node or line 3-5 km | 7.17 | 4.95 | Line: LZQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1778
2 | 779 | 1779 | 0401005057 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 11 | 13.7609 | 121.0605 | R | 357 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.94 | 49.6 | 70.94 |  | A - Node within 0.5 km | 0.42 | 0.32 | Line: UG SSB001 TO BCY001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1779
2 | 780 | 1780 | 1381100140 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 140 | 14.5464 | 121.0049 | U | 607 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.91 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.94 | 49.6 | 70.94 |  | B - Node 0.5-1 km | 0.79 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1780
2 | 781 | 1781 | PH0001781 | I | Pangasinan | Dagupan City | Barangay IV | 16.0428 | 120.3338 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.16 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 70.93 | 49.59 | 70.93 |  | C - Line within 0.5 km; node over 1 km | 2.46 | 0.03 | Line: DAGUPAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1781
2 | 782 | 1782 | PH0001782 | CAR | Benguet | Baguio City | Happy Homes | 16.43 | 120.59 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 70.93 | 49.59 | 70.93 |  | B - Node 0.5-1 km | 0.63 | 1.67 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1782
2 | 783 | 1783 | 1380606084 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 478 | 14.6118 | 120.9915 | U | 1163 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.46 | 46.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.92 | 49.58 | 70.92 |  | B - Node 0.5-1 km | 0.97 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1783
2 | 784 | 1784 | 0102811022 | Region I (Ilocos Region) | Ilocos Norte | Banna | Binacag | 18.0163 | 120.6368 | R | 967 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 2.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.92 | 49.58 | 70.92 |  | E - Nearest node or line 3-5 km | 4.43 | 3.72 | Line: SEGMENT 5 BANNA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1784
2 | 785 | 1785 | 1400109002 | Cordillera Administrative Region (CAR) | Abra | Lacub | Buneg | 17.6673 | 120.9712 | R | 851 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.29 | 32.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.92 | 49.58 | 70.92 |  | F - Nearest node and line over 5 km | 32.29 | 32.24 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1785
2 | 786 | 1786 | 1381100048 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 48 | 14.5553 | 120.9959 | U | 523 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.13 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 70.92 | 49.58 | 70.92 |  | A - Node within 0.5 km | 0.5 | 0.1 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1786
2 | 787 | 1787 | 1380612035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 868 | 14.5803 | 121.0049 | U | 2937 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.45 | 5.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.92 | 49.58 | 70.92 |  | B - Node 0.5-1 km | 0.51 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1787
2 | 788 | 1788 | 0401005058 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 12 | 13.7443 | 121.0595 | U | 1431 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.67 | 5.71 | Tier 2 High GIDA (Score 40.0–49.9) | 70.91 | 49.57 | 70.91 |  | D - Other node or line within 3 km | 2.03 | 1.33 | Line: AE TO ELIMINATE COMMON 96C | Route options survey candidate: compare actual node lateral with approved line tap. | 1788
2 | 789 | 1789 | 1381100086 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 86 | 14.5442 | 120.9963 | U | 1428 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.61 | 5.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.91 | 49.57 | 70.91 |  | A - Node within 0.5 km | 0.2 | 0.2 | Node: PSY022 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1789
2 | 790 | 1790 | 1381100067 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 67 | 14.543 | 120.995 | U | 1135 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.74 | Tier 2 High GIDA (Score 40.0–49.9) | 70.91 | 49.57 | 70.91 |  | A - Node within 0.5 km | 0.18 | 0.04 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1790
2 | 791 | 1791 | 1380605007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 303 | 14.6127 | 120.9915 | U | 660 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.59 | 57.09 | Tier 2 High GIDA (Score 40.0–49.9) | 70.91 | 49.57 | 70.91 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1791
2 | 792 | 1792 | 1380606198 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 591 | 14.6033 | 121.0088 | U | 2574 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.62 | 10.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.57 | 70.9 |  | A - Node within 0.5 km | 0.48 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1792
2 | 793 | 1793 | 1381300107 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Teresita | 14.7142 | 121.0974 | U | 12270 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.57 | 70.9 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.06 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1793
2 | 794 | 1794 | 1380612017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 849 | 14.5903 | 121.0031 | U | 1905 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.32 | 14.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.57 | 70.9 |  | B - Node 0.5-1 km | 0.66 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1794
2 | 795 | 1795 | 1380601098 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 98 | 14.6246 | 120.9626 | U | 1957 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.67 | 66.58 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.57 | 70.9 |  | B - Node 0.5-1 km | 0.74 | 1.07 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1795
2 | 796 | 1796 | 1380605039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 337 | 14.605 | 120.9809 | U | 1428 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.2 | 2.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.57 | 70.9 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1796
2 | 797 | 1797 | 1380612010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 842 | 14.5872 | 121.0019 | U | 2897 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.97 | 46.9 | Tier 2 High GIDA (Score 40.0–49.9) | 70.9 | 49.56 | 70.9 |  | A - Node within 0.5 km | 0.33 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1797
2 | 798 | 1798 | 1102502004 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Causwagan | 7.0099 | 126.015 | R | 831 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.18 | 2.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | D - Other node or line within 3 km | 5.18 | 2.01 | Line: PANTUKAN - MATI SEGMENT 2 | Route options survey candidate: compare actual node lateral with approved line tap. | 1798
2 | 799 | 1799 | PH0001799 | CAR | Benguet | Baguio City | Slaughter House Area | 16.4147 | 120.5742 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | A - Node within 0.5 km | 0.43 | 0.16 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1799
2 | 800 | 1800 | 0402106051 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima II | 14.3002 | 120.9203 | U | 4532 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.6 | 0.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | D - Other node or line within 3 km | 1.3 | 0.89 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 1800
2 | 801 | 1801 | 1381100150 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 150 | 14.5372 | 121.0095 | U | 681 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | D - Other node or line within 3 km | 1.41 | 0.64 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1801
2 | 802 | 1802 | 1381100078 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 78 | 14.5439 | 120.9969 | U | 508 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | A - Node within 0.5 km | 0.28 | 0.26 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1802
2 | 803 | 1803 | 1380611047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 832 | 14.5825 | 120.9945 | U | 2976 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.4 | 33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.89 | 49.56 | 70.89 |  | B - Node 0.5-1 km | 0.91 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1803
2 | 804 | 1804 | 1381100058 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 58 | 14.5503 | 120.9999 | U | 1421 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.45 | 2.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.56 | 70.88 |  | B - Node 0.5-1 km | 0.88 | 0.18 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1804
2 | 805 | 1805 | 1381100075 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 75 | 14.5426 | 120.9978 | U | 1364 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.61 | 9.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.56 | 70.88 |  | A - Node within 0.5 km | 0.42 | 0.21 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1805
2 | 806 | 1806 | 1380601061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 61 | 14.6144 | 120.9696 | U | 1053 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.7 | 6.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.55 | 70.88 |  | B - Node 0.5-1 km | 0.84 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1806
2 | 807 | 1807 | 1381300033 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Don Manuel | 14.7283 | 121.1185 | U | 1801 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.55 | 70.88 |  | C - Line within 0.5 km; node over 1 km | 2.35 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1807
2 | 808 | 1808 | 1380612024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 856 | 14.5866 | 121.0024 | U | 1660 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.47 | 61.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.55 | 70.88 |  | A - Node within 0.5 km | 0.25 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1808
2 | 809 | 1809 | 1380606065 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 459 | 14.6114 | 120.9942 | U | 775 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.55 | 2.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.55 | 70.88 |  | B - Node 0.5-1 km | 0.97 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1809
2 | 810 | 1810 | 0401005071 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 24 | 13.6631 | 121.106 | R | 1449 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 6.07 | Tier 2 High GIDA (Score 40.0–49.9) | 70.88 | 49.55 | 70.88 |  | E - Nearest node or line 3-5 km | 4.44 | 11.39 | Node: BCY005 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1810
2 | 811 | 1811 | 1380606242 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 635 | 14.5965 | 121.0005 | U | 680 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.14 | 28.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.87 | 49.55 | 70.87 |  | B - Node 0.5-1 km | 0.76 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1811
2 | 812 | 1812 | PH0001812 | V | Camarines Sur | Naga City | Lerma | 10.4028 | 123.9248 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 2.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.87 | 49.55 | 70.87 |  | C - Line within 0.5 km; node over 1 km | 3.7 | 0.15 | Line: Route 11.925km | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1812
2 | 813 | 1813 | 1381100172 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 172 | 14.5333 | 121.0141 | U | 5059 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.87 | 49.54 | 70.87 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.47 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1813
2 | 814 | 1814 | PH0001814 | VII | Cebu | Talisay City | Tabunoc | 10.2634 | 123.8406 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.38 | 10.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | A - Node within 0.5 km | 0.16 | 0.11 | Line: CEBU - TOLEDO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1814
2 | 815 | 1815 | 1381100079 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 79 | 14.5432 | 120.9955 | U | 696 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.34 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | A - Node within 0.5 km | 0.18 | 0.09 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1815
2 | 816 | 1816 | 1380606018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 412 | 14.5999 | 120.9949 | U | 1947 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.88 | 55.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | B - Node 0.5-1 km | 0.54 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1816
2 | 817 | 1817 | 1381100038 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 38 | 14.5604 | 120.9951 | U | 2023 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.26 | 3.37 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | B - Node 0.5-1 km | 0.87 | 0.05 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1817
2 | 818 | 1818 | 1381100013 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 13 | 14.5582 | 120.9914 | U | 2721 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 1.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | B - Node 0.5-1 km | 0.55 | 0.49 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1818
2 | 819 | 1819 | 0603013037 | Region VI (Western Visayas) | Iloilo | Calinog | Hilwan | 11.2915 | 122.33 | R | 543 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.95 | 25.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | F - Nearest node and line over 5 km | 29.95 | 29.07 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1819
2 | 820 | 1820 | PH0001820 | VI | Iloilo | Iloilo City | Maria Cristina | 10.7104 | 122.5547 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.77 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | D - Other node or line within 3 km | 1.5 | 1.05 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 1820
2 | 821 | 1821 | 1381100047 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 47 | 14.556 | 120.9973 | U | 1241 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.26 | 3.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | B - Node 0.5-1 km | 0.67 | 0.07 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1821
2 | 822 | 1822 | 1381100092 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 92 | 14.5468 | 120.9981 | U | 482 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | A - Node within 0.5 km | 0.47 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1822
2 | 823 | 1823 | 1381100159 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 159 | 14.5342 | 121.007 | U | 1338 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 1.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.35 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1823
2 | 824 | 1824 | 1381300032 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Doña Josefa | 14.6894 | 121.0426 | U | 1935 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.86 | 49.54 | 70.86 |  | D - Other node or line within 3 km | 1.38 | 1.21 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 1824
2 | 825 | 1825 | 0601912018 | Region VI (Western Visayas) | Capiz | Pontevedra | Manapao | 11.4594 | 122.8978 | R | 675 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.25 | 4.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.85 | 49.53 | 70.85 |  | E - Nearest node or line 3-5 km | 7.25 | 4.13 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1825
2 | 826 | 1826 | 1381100144 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 144 | 14.547 | 121.0061 | U | 2275 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.65 | 9.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.85 | 49.53 | 70.85 |  | B - Node 0.5-1 km | 0.65 | 0.3 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1826
2 | 827 | 1827 | 1380700013 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Marikina Heights | 14.6489 | 121.1186 | U | 44192 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.46 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 70.85 | 49.53 | 70.85 |  | A - Node within 0.5 km | 0.46 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1827
2 | 828 | 1828 | 1381100010 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 10 | 14.5604 | 120.9923 | U | 1445 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.85 | 49.53 | 70.85 |  | B - Node 0.5-1 km | 0.79 | 0.34 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1828
2 | 829 | 1829 | 1381100169 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 169 | 14.532 | 121.0115 | U | 2905 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 1.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.85 | 49.53 | 70.85 |  | D - Other node or line within 3 km | 1.2 | 0.57 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1829
2 | 830 | 1830 | 1380601214 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 213 | 14.6254 | 120.9827 | U | 3329 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.43 | 7.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70.84 | 49.53 | 70.84 |  | B - Node 0.5-1 km | 0.99 | 0.03 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1830
2 | 831 | 1831 | 1380601139 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 139 | 14.6291 | 120.9661 | U | 382 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.26 | 54.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.84 | 49.53 | 70.84 |  | B - Node 0.5-1 km | 0.81 | 0.73 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1831
2 | 832 | 1832 | 0401005066 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 2 | 13.7982 | 121.0878 | U | 515 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.16 | 2.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.84 | 49.52 | 70.84 |  | C - Line within 0.5 km; node over 1 km | 4.77 | 0.42 | Line: UG ROS001 TO BSY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1832
2 | 833 | 1833 | 1381100106 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 106 | 14.5435 | 121.0007 | U | 1191 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.84 | 49.52 | 70.84 |  | B - Node 0.5-1 km | 0.68 | 0.1 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1833
2 | 834 | 1834 | 1380612004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 836 | 14.5892 | 121.0129 | U | 5478 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.71 | 18.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | D - Other node or line within 3 km | 1.21 | 0.7 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1834
2 | 835 | 1835 | 1381701002 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Magtanggol | 14.5471 | 121.066 | U | 1433 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.92 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | A - Node within 0.5 km | 0.37 | 0.28 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1835
2 | 836 | 1836 | 1003514029 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Sandigamunai | 8.0786 | 124.0636 | R | 1067 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.23 | 18.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | F - Nearest node and line over 5 km | 24.43 | 11.78 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1836
2 | 837 | 1837 | 1381100033 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 33 | 14.5605 | 120.9954 | U | 1011 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.08 | 4.9 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | B - Node 0.5-1 km | 0.89 | 0.02 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1837
2 | 838 | 1838 | 1380606238 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 631 | 14.6005 | 121.0039 | U | 1292 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.53 | 7.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | A - Node within 0.5 km | 0.19 | 0.14 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1838
2 | 839 | 1839 | PH0001839 | IV-A | Laguna | San Pablo City | Barangay III-B (Pob.) | 17.4805 | 121.8352 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.83 | 49.52 | 70.83 |  | E - Nearest node or line 3-5 km | 8.37 | 3.29 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1839
2 | 840 | 1840 | PH0001840 | VIII | Leyte | Tacloban City | Barangay 50 | 11.2294 | 124.9922 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.44 | 4.82 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | D - Other node or line within 3 km | 1.59 | 2.64 | Node: TCL002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1840
2 | 841 | 1841 | 1381300007 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagumbuhay | 14.6253 | 121.0642 | U | 6961 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | B - Node 0.5-1 km | 0.55 | 0.2 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1841
2 | 842 | 1842 | 1380604018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 285 | 14.5975 | 120.9714 | U | 2129 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61 | 72.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | D - Other node or line within 3 km | 1.05 | 0.95 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1842
2 | 843 | 1843 | 1380606195 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 588 | 14.6022 | 121.0104 | U | 1019 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.46 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | B - Node 0.5-1 km | 0.64 | 0.01 | Line: UG 144C via V-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1843
2 | 844 | 1844 | 1380601213 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 212 | 14.6266 | 120.9802 | U | 2756 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.03 | 41.07 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | B - Node 0.5-1 km | 0.74 | 0.13 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1844
2 | 845 | 1845 | 1380610004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 689 | 14.5745 | 120.9941 | U | 755 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.75 | 42.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | A - Node within 0.5 km | 0.27 | 0.04 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1845
2 | 846 | 1846 | PH0001846 | NCR | Metro Manila | Caloocan City | Barangay 40 | 14.6181 | 120.9741 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.8 | 65.32 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | B - Node 0.5-1 km | 0.96 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1846
2 | 847 | 1847 | 1380601055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 55 | 14.6172 | 120.972 | U | 2568 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.66 | 8.98 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | C - Line within 0.5 km; node over 1 km | 1 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1847
2 | 848 | 1848 | 0201519004 | Region II (Cagayan Valley) | Cagayan | Peñablanca | Bical | 17.5631 | 121.8248 | R | 1936 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.26 | 4.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | E - Nearest node or line 3-5 km | 12.26 | 4.6 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1848
2 | 849 | 1849 | 1381100023 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 23 | 14.6171 | 120.9813 | U | 1459 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.18 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.82 | 49.51 | 70.82 |  | A - Node within 0.5 km | 0.18 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1849
2 | 850 | 1850 | 1381100180 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 180 | 14.5365 | 120.9984 | U | 2118 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 7.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.51 | 70.81 |  | B - Node 0.5-1 km | 0.97 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1850
2 | 851 | 1851 | 1380601176 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 176 | 14.6289 | 120.9729 | U | 1317 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.12 | 55.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.5 | 70.81 |  | A - Node within 0.5 km | 0.24 | 0.24 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1851
2 | 852 | 1852 | 1380606204 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 597 | 14.5974 | 121.0162 | U | 1723 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.89 | 4.93 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.5 | 70.81 |  | D - Other node or line within 3 km | 1.36 | 0.6 | Line: UG 288C via V-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1852
2 | 853 | 1853 | 1400127002 | Cordillera Administrative Region (CAR) | Abra | Villaviciosa | Bol-lilising | 17.3532 | 120.5985 | R | 278 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.66 | 12.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.5 | 70.81 |  | F - Nearest node and line over 5 km | 12.66 | 12.59 | Line: SEGMENT 2 (CANDON - VIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1853
2 | 854 | 1854 | 1380610028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 713 | 14.5684 | 120.9869 | U | 2024 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.66 | 21.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.5 | 70.81 |  | B - Node 0.5-1 km | 0.89 | 0.56 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1854
2 | 855 | 1855 | 1380606233 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 626 | 14.5895 | 121.0166 | U | 1324 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.83 | 64.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.81 | 49.5 | 70.81 |  | C - Line within 0.5 km; node over 1 km | 1.4 | 0.48 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1855
2 | 856 | 1856 | 1380612037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 871 | 14.5814 | 121.0079 | U | 2480 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.19 | 8.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.5 | 70.8 |  | B - Node 0.5-1 km | 0.65 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1856
2 | 857 | 1857 | 1381100139 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 139 | 14.5471 | 121.0063 | U | 1095 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.5 | 70.8 |  | B - Node 0.5-1 km | 0.62 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1857
2 | 858 | 1858 | 1907006032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Tong Tampakan | 17.2559 | 122.2299 | R | 1265 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.5 | 70.8 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1858
2 | 859 | 1859 | 1380601204 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 203 | 14.6274 | 120.9763 | U | 2537 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.24 | 53.13 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.49 | 70.8 |  | A - Node within 0.5 km | 0.33 | 0.08 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1859
2 | 860 | 1860 | 1380601211 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 210 | 14.6265 | 120.9818 | U | 3310 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.77 | 27.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.49 | 70.8 |  | B - Node 0.5-1 km | 0.91 | 0.14 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1860
2 | 861 | 1861 | 1380500002 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Bagong Silang | 14.584 | 121.0443 | U | 5405 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 70.8 | 49.49 | 70.8 |  | B - Node 0.5-1 km | 0.77 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1861
2 | 862 | 1862 | 1380606056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 450 | 14.6074 | 120.9992 | U | 1891 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | B - Node 0.5-1 km | 0.63 | 0.27 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1862
2 | 863 | 1863 | 1380603015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 306 | 14.6091 | 120.9945 | U | 1286 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.58 | 63.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | B - Node 0.5-1 km | 0.75 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1863
2 | 864 | 1864 | 1380611016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 682 | 14.5776 | 120.993 | U | 847 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.79 | 4.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | B - Node 0.5-1 km | 0.63 | 0.06 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1864
2 | 865 | 1865 | 1380603008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 388 | 14.5954 | 120.9905 | U | 1298 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.64 | 34.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | B - Node 0.5-1 km | 0.86 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1865
2 | 866 | 1866 | 1381100167 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 167 | 14.5352 | 121.0079 | U | 776 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.39 | 0.04 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.47 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1866
2 | 867 | 1867 | 1380606127 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 521 | 14.6182 | 120.9968 | U | 2312 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.77 | 52.19 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.46 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1867
2 | 868 | 1868 | 1380614039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 783 | 14.582 | 121.0119 | U | 2210 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.5 | 11.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.79 | 49.49 | 70.79 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1868
2 | 869 | 1869 | 1381100041 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 41 | 14.5616 | 120.9959 | U | 1636 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 70.78 | 49.48 | 70.78 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.05 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1869
2 | 870 | 1870 | 0806012029 | Region VIII (Eastern Visayas) | Samar | Motiong | Santo Niño | 11.9314 | 125.0479 | R | 90 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.89 | 83.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.78 | 49.48 | 70.78 |  | F - Nearest node and line over 5 km | 77.08 | 80.05 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1870
2 | 871 | 1871 | PH0001871 | X | Misamis Oriental | Cagayan De Oro City | Barangay 22 (Pob.) | 8.4905 | 124.6538 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 70.77 | 49.48 | 70.77 |  | A - Node within 0.5 km | 0.45 | 0.56 | Node: COM004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1871
2 | 872 | 1872 | 0405605040 | Region IV-A (CALABARZON) | Quezon | Buenavista | Villa Magsaysay | 13.7389 | 122.3899 | R | 576 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.43 | 6.01 | Tier 2 High GIDA (Score 40.0–49.9) | 70.77 | 49.48 | 70.77 |  | F - Nearest node and line over 5 km | 7.43 | 5.84 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1872
2 | 873 | 1873 | 1380601181 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 181 | 14.6303 | 120.971 | U | 2857 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.62 | 51.74 | Tier 2 High GIDA (Score 40.0–49.9) | 70.77 | 49.47 | 70.77 |  | A - Node within 0.5 km | 0.46 | 0.43 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1873
2 | 874 | 1874 | 0907311019 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Mahayahay | 7.7481 | 123.1442 | R | 822 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.03 | 1.11 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | D - Other node or line within 3 km | 10.03 | 1.11 | Line: PAGADIAN - BUUG | Route options survey candidate: compare actual node lateral with approved line tap. | 1874
2 | 875 | 1875 | 0403405040 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 3 | 14.2074 | 121.1622 | U | 4973 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.07 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | C - Line within 0.5 km; node over 1 km | 2.07 | 0.05 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1875
2 | 876 | 1876 | PH0001876 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Piagma | 17.2546 | 122.2291 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.88 | 64.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | F - Nearest node and line over 5 km | 29.42 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1876
2 | 877 | 1877 | 1380606070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 464 | 14.61 | 120.9929 | U | 3044 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.38 | 11.77 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | B - Node 0.5-1 km | 0.79 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1877
2 | 878 | 1878 | PH0001878 | VIII | Leyte | Tacloban City | Barangay 44-A | 11.2869 | 124.9594 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.58 | 11.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | F - Nearest node and line over 5 km | 7.05 | 9.9 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1878
2 | 879 | 1879 | 1380601217 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 216 | 14.6227 | 120.9814 | U | 2505 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.02 | 13.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | B - Node 0.5-1 km | 0.71 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1879
2 | 880 | 1880 | PH0001880 | NCR | Metro Manila | Caloocan City | Barangay 135 | 14.6273 | 120.9654 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.3 | 13.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | B - Node 0.5-1 km | 0.86 | 0.76 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1880
2 | 881 | 1881 | PH0001881 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Lico | 17.2552 | 122.229 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.77 | 63.78 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | F - Nearest node and line over 5 km | 29.45 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1881
2 | 882 | 1882 | 1380612027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 859 | 14.5875 | 121.0033 | U | 1396 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.86 | 72.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.76 | 49.47 | 70.76 |  | A - Node within 0.5 km | 0.35 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1882
2 | 883 | 1883 | 1704001048 | MIMAROPA Region | Marinduque | Boac | Sabong | 13.3727 | 121.8721 | R | 130 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.25 | 44.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | F - Nearest node and line over 5 km | 48.26 | 48.19 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1883
2 | 884 | 1884 | 1908702001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Ampuan | 17.2541 | 122.2281 | R | 2691 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | F - Nearest node and line over 5 km | 29.3 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1884
2 | 885 | 1885 | 1908702002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Aratuc | 17.2539 | 122.2279 | R | 2757 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1885
2 | 886 | 1886 | 0402106021 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado I | 14.3113 | 120.9721 | U | 8424 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 2.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | B - Node 0.5-1 km | 0.71 | 1.99 | Node: DMC004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1886
2 | 887 | 1887 | 1380606119 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 513 | 14.621 | 120.9954 | U | 2095 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.97 | 4.4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | D - Other node or line within 3 km | 1.44 | 0.8 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1887
2 | 888 | 1888 | PH0001888 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Sagua-an | 17.2536 | 122.228 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.5 | 64.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.75 | 49.46 | 70.75 |  | F - Nearest node and line over 5 km | 29.25 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1888
2 | 889 | 1889 | 1380614083 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 890 | 14.5835 | 121.0135 | U | 1081 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.54 | 47.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.74 | 49.46 | 70.74 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.12 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1889
2 | 890 | 1890 | 1380612007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 839 | 14.5902 | 121.0131 | U | 2068 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.66 | 37.86 | Tier 2 High GIDA (Score 40.0–49.9) | 70.74 | 49.45 | 70.74 |  | D - Other node or line within 3 km | 1.28 | 0.79 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1890
2 | 891 | 1891 | 1380606235 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 628 | 14.6026 | 121.0035 | U | 15664 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.93 | 11.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.73 | 49.45 | 70.73 |  | A - Node within 0.5 km | 0.13 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1891
2 | 892 | 1892 | PH0001892 | IV-A | Cavite | Imus City | Palico III | 14.3742 | 120.9247 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.73 | 49.44 | 70.73 |  | D - Other node or line within 3 km | 1.9 | 6.05 | Node: IMC003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1892
2 | 893 | 1893 | 0603013074 | Region VI (Western Visayas) | Iloilo | Calinog | Supanga | 11.1919 | 122.3987 | R | 912 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.85 | 18.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | F - Nearest node and line over 5 km | 27.85 | 22.97 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1893
2 | 894 | 1894 | PH0001894 | III | Nueva Ecija | Cabanatuan City | Zulueta District (Pob.) | 15.4871 | 120.9586 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | B - Node 0.5-1 km | 0.65 | 0.65 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1894
2 | 895 | 1895 | 1380601169 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 169 | 14.6245 | 120.9742 | U | 942 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.8 | 55.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | A - Node within 0.5 km | 0.27 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1895
2 | 896 | 1896 | 1380608005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 661 | 14.583 | 120.9852 | U | 454 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.55 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | B - Node 0.5-1 km | 0.85 | 0.32 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1896
2 | 897 | 1897 | 1380606015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 409 | 14.6054 | 120.9889 | U | 1979 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.23 | 27.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | A - Node within 0.5 km | 0.36 | 0.09 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1897
2 | 898 | 1898 | 0601903009 | Region VI (Western Visayas) | Capiz | Dumalag | San Martin | 11.3203 | 122.5804 | R | 449 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.66 | 4.77 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | E - Nearest node or line 3-5 km | 12.66 | 4.77 | Line: CABLE LAYED | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1898
2 | 899 | 1899 | 1381300073 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paang Bundok | 15.6169 | 120.8211 | U | 5008 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.19 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.72 | 49.44 | 70.72 |  | E - Nearest node or line 3-5 km | 6.56 | 3.95 | Line: 38,161m. | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 1899
2 | 900 | 1900 | 1380601162 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 162 | 14.6265 | 120.9771 | U | 573 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.32 | 61.72 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.44 | 70.71 |  | A - Node within 0.5 km | 0.4 | 0.02 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1900
2 | 901 | 1901 | 1380604017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 284 | 14.5978 | 120.9703 | U | 990 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.93 | 12.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.44 | 70.71 |  | B - Node 0.5-1 km | 1 | 0.9 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1901
2 | 902 | 1902 | 1380606082 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 476 | 14.6096 | 120.991 | U | 1307 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.38 | 49.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.44 | 70.71 |  | B - Node 0.5-1 km | 0.72 | 0.13 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1902
2 | 903 | 1903 | PH0001903 | CAR | Benguet | Baguio City | A. Bonifacio-Caguioa-Rimando | 16.411 | 120.5611 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.44 | 70.71 |  | B - Node 0.5-1 km | 0.57 | 0.07 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1903
2 | 904 | 1904 | 1381300110 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santol | 14.6126 | 121.0154 | U | 6679 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.43 | 70.71 |  | B - Node 0.5-1 km | 0.53 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1904
2 | 905 | 1905 | 0300803016 | Region III (Central Luzon) | Bataan | City of Balanga | San Jose | 14.6752 | 120.5385 | U | 7018 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.43 | 70.71 |  | D - Other node or line within 3 km | 1.07 | 0.58 | Line: 60 CORE 5X12 | Route options survey candidate: compare actual node lateral with approved line tap. | 1905
2 | 906 | 1906 | 1380614025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 769 | 14.5681 | 121.0065 | U | 2058 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.88 | 21.93 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.43 | 70.71 |  | C - Line within 0.5 km; node over 1 km | 1.39 | 0 | Line: UG 288C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1906
2 | 907 | 1907 | 1403215006 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Belong Manubal | 17.2977 | 121.1341 | R | 495 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.08 | 2.44 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.43 | 70.71 |  | D - Other node or line within 3 km | 4.08 | 2.39 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 1907
2 | 908 | 1908 | 1380614007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 750 | 14.5676 | 121.0046 | U | 1141 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.99 | 4.78 | Tier 2 High GIDA (Score 40.0–49.9) | 70.71 | 49.43 | 70.71 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1908
2 | 909 | 1909 | 1380614082 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 889 | 14.5842 | 121.0155 | U | 890 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.57 | 66.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.7 | 49.43 | 70.7 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1909
2 | 910 | 1910 | 1380601156 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 156 | 14.629 | 120.9757 | U | 1664 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.88 | 1.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.7 | 49.43 | 70.7 |  | A - Node within 0.5 km | 0.35 | 0.25 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1910
2 | 911 | 1911 | 1381100031 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 31 | 14.6175 | 120.9802 | U | 3645 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.55 | 6.67 | Tier 2 High GIDA (Score 40.0–49.9) | 70.7 | 49.42 | 70.7 |  | A - Node within 0.5 km | 0.3 | 0.09 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1911
2 | 912 | 1912 | 0402106068 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua II | 14.3143 | 120.9066 | R | 3223 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 2.02 | Tier 2 High GIDA (Score 40.0–49.9) | 70.69 | 49.42 | 70.69 |  | D - Other node or line within 3 km | 2.27 | 2.49 | Node: TRC002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1912
2 | 913 | 1913 | 1380612015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 847 | 14.5859 | 121.0007 | U | 2971 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.35 | 41.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.69 | 49.42 | 70.69 |  | A - Node within 0.5 km | 0.27 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1913
2 | 914 | 1914 | 1380603009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 389 | 14.6019 | 120.9851 | U | 1210 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.24 | 48.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.69 | 49.42 | 70.69 |  | B - Node 0.5-1 km | 0.67 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1914
2 | 915 | 1915 | 1380606008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 402 | 14.6045 | 120.9896 | U | 2842 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.17 | 49.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.69 | 49.42 | 70.69 |  | A - Node within 0.5 km | 0.23 | 0.15 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1915
2 | 916 | 1916 | 1380606108 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 502 | 14.6218 | 120.9933 | U | 840 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.1 | 4.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.68 | 49.41 | 70.68 |  | D - Other node or line within 3 km | 1.27 | 0.59 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1916
2 | 917 | 1917 | 1380611045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 830 | 14.5834 | 120.9956 | U | 5349 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.87 | 20.82 | Tier 2 High GIDA (Score 40.0–49.9) | 70.68 | 49.41 | 70.68 |  | B - Node 0.5-1 km | 0.78 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1917
2 | 918 | 1918 | 1380606194 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 587-A | 14.6034 | 121.0125 | U | 1316 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.34 | 70.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.68 | 49.41 | 70.68 |  | B - Node 0.5-1 km | 0.88 | 0.09 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1918
2 | 919 | 1919 | 1400109004 | Cordillera Administrative Region (CAR) | Abra | Lacub | Lan-ag | 17.7368 | 120.8938 | R | 433 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.49 | 23.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | F - Nearest node and line over 5 km | 25.49 | 23.71 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1919
2 | 920 | 1920 | 0402103045 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino II | 14.4152 | 120.972 | U | 44630 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 1.72 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | D - Other node or line within 3 km | 1.23 | 3.91 | Node: BRC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1920
2 | 921 | 1921 | 0402106035 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Mateo | 14.3341 | 120.9401 | R | 5211 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | D - Other node or line within 3 km | 1.83 | 3.82 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1921
2 | 922 | 1922 | 1380601263 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 262 | 14.606 | 120.9765 | U | 1789 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.35 | 10.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | B - Node 0.5-1 km | 0.74 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1922
2 | 923 | 1923 | 1380612012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 844 | 14.5848 | 121.0024 | U | 3606 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.18 | 50.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | A - Node within 0.5 km | 0.06 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1923
2 | 924 | 1924 | 1380606041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 435 | 14.6068 | 120.9982 | U | 610 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.24 | 32.8 | Tier 2 High GIDA (Score 40.0–49.9) | 70.67 | 49.4 | 70.67 |  | B - Node 0.5-1 km | 0.76 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1924
2 | 925 | 1925 | 1380606123 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 517 | 14.6209 | 120.9963 | U | 1060 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.54 | 5.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | D - Other node or line within 3 km | 1.36 | 0.75 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1925
2 | 926 | 1926 | 1380611019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 685 | 14.5786 | 120.996 | U | 1076 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.2 | 56.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | B - Node 0.5-1 km | 0.76 | 0 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1926
2 | 927 | 1927 | 1380602006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 292 | 14.5982 | 120.9697 | U | 2932 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.38 | 5.98 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | B - Node 0.5-1 km | 0.95 | 0.86 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1927
2 | 928 | 1928 | 1380606026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 420 | 14.6063 | 121.0015 | U | 3229 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31 | 34.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | B - Node 0.5-1 km | 0.57 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1928
2 | 929 | 1929 | 1380612020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 852 | 14.5867 | 121.0015 | U | 1152 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.38 | 58.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | A - Node within 0.5 km | 0.3 | 0.04 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1929
2 | 930 | 1930 | 1380610040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 725 | 14.5726 | 120.9896 | U | 1452 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.86 | 16.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | B - Node 0.5-1 km | 0.51 | 0.29 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1930
2 | 931 | 1931 | 1380606068 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 462 | 14.6124 | 120.9925 | U | 1574 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.12 | 46.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.66 | 49.4 | 70.66 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.17 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1931
2 | 932 | 1932 | PH0001932 | XI | Davao Del Sur | Davao City | Barangay 37-D (Pob.) | 7.0633 | 125.6141 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.65 | 49.39 | 70.65 |  | B - Node 0.5-1 km | 0.55 | 1.23 | Node: DCD007 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1932
2 | 933 | 1933 | PH0001933 | VIII | Leyte | Tacloban City | Barangay 40 | 11.2715 | 124.9509 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 1.68 | Tier 2 High GIDA (Score 40.0–49.9) | 70.65 | 49.39 | 70.65 |  | F - Nearest node and line over 5 km | 6.65 | 9.14 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1933
2 | 934 | 1934 | 1380601146 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 146 | 14.63 | 120.9654 | U | 2983 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.85 | 15.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.65 | 49.39 | 70.65 |  | B - Node 0.5-1 km | 0.92 | 0.84 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1934
2 | 935 | 1935 | 1380608013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 663 | 14.5853 | 120.9857 | U | 622 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.76 | 11.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.39 | 70.64 |  | B - Node 0.5-1 km | 0.61 | 0.2 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1935
2 | 936 | 1936 | 1380610029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 714 | 14.5719 | 120.9894 | U | 1413 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.55 | 71.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.39 | 70.64 |  | B - Node 0.5-1 km | 0.52 | 0.25 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1936
2 | 937 | 1937 | PH0001937 | VIII | Leyte | Tacloban City | Barangay 44 | 11.245 | 125.0045 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.04 | 8.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.39 | 70.64 |  | B - Node 0.5-1 km | 0.64 | 3.65 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1937
2 | 938 | 1938 | PH0001938 | IV-B | Palawan | Puerto Princesa City | Bagong Silang (Pob.) | 9.7304 | 118.7424 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.49 | 2.92 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.38 | 70.64 |  | D - Other node or line within 3 km | 1.49 | 2.48 | Node: PPW002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 1938
2 | 939 | 1939 | PH0001939 | NCR | Metro Manila | Caloocan City | Barangay 49 | 14.6166 | 120.9738 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.8 | 67.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.38 | 70.64 |  | B - Node 0.5-1 km | 0.97 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1939
2 | 940 | 1940 | 1380606016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 410 | 14.5986 | 120.9966 | U | 2498 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.35 | 3.05 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.38 | 70.64 |  | B - Node 0.5-1 km | 0.77 | 0.23 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1940
2 | 941 | 1941 | 1380603013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 393 | 14.6018 | 120.986 | U | 4197 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.19 | 48.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.38 | 70.64 |  | B - Node 0.5-1 km | 0.58 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1941
2 | 942 | 1942 | 1380614086 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 893 | 14.5882 | 121.0197 | U | 682 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.34 | 43.82 | Tier 2 High GIDA (Score 40.0–49.9) | 70.64 | 49.38 | 70.64 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.15 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1942
2 | 943 | 1943 | PH0001943 | NCR | Metro Manila | Caloocan City | Barangay 33 | 14.6023 | 120.9606 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.12 | 0.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | B - Node 0.5-1 km | 0.94 | 1.1 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1943
2 | 944 | 1944 | 1380610038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 723 | 14.5704 | 120.9891 | U | 556 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.18 | 16.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | B - Node 0.5-1 km | 0.58 | 0.26 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1944
2 | 945 | 1945 | PH0001945 | VIII | Leyte | Tacloban City | Barangay 43 | 11.1952 | 125.0075 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.59 | 9.47 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.26 | Line: CAPOOCAN - TACLOBAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1945
2 | 946 | 1946 | 1380610021 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 706 | 14.5722 | 120.9876 | U | 305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.68 | 48.56 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | B - Node 0.5-1 km | 0.71 | 0.44 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1946
2 | 947 | 1947 | 1381100005 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 5 | 14.5605 | 120.9925 | U | 6254 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | B - Node 0.5-1 km | 0.81 | 0.32 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1947
2 | 948 | 1948 | 1380606081 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 475 | 14.6108 | 120.9931 | U | 1715 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.21 | 2.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.63 | 49.38 | 70.63 |  | B - Node 0.5-1 km | 0.88 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1948
2 | 949 | 1949 | PH0001949 | NCR | Metro Manila | Caloocan City | Barangay 30 | 14.6012 | 120.9623 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.03 | 42.78 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | B - Node 0.5-1 km | 0.82 | 1 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1949
2 | 950 | 1950 | 1380606207 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 600 | 14.5938 | 121.0146 | U | 6071 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.25 | 27.98 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | D - Other node or line within 3 km | 1.42 | 0.98 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1950
2 | 951 | 1951 | PH0001951 | NCR | Metro Manila | Caloocan City | Barangay 28 | 14.642 | 120.9692 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.19 | 58.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | B - Node 0.5-1 km | 0.9 | 1.4 | Node: CCS004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1951
2 | 952 | 1952 | 1380605036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 334 | 14.6086 | 120.9779 | U | 1505 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.81 | 68.37 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | B - Node 0.5-1 km | 0.91 | 0.24 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1952
2 | 953 | 1953 | 1380601231 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 230 | 14.6245 | 120.9799 | U | 2436 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.4 | 16.37 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | B - Node 0.5-1 km | 0.75 | 0.06 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1953
2 | 954 | 1954 | 1380610006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 691 | 14.5767 | 120.9946 | U | 421 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.52 | 45.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.62 | 49.37 | 70.62 |  | B - Node 0.5-1 km | 0.53 | 0.17 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1954
2 | 955 | 1955 | 1380611008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 674 | 14.5794 | 120.9935 | U | 1440 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.57 | 27.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.61 | 49.37 | 70.61 |  | B - Node 0.5-1 km | 0.82 | 0.12 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1955
2 | 956 | 1956 | 1380605002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 298 | 14.6094 | 120.9927 | U | 1051 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.1 | 0.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.61 | 49.37 | 70.61 |  | B - Node 0.5-1 km | 0.72 | 0.01 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1956
2 | 957 | 1957 | 1380606085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 479 | 14.6111 | 120.9931 | U | 2377 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.81 | 60.19 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.36 | 70.6 |  | B - Node 0.5-1 km | 0.91 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1957
2 | 958 | 1958 | 1380606042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 436 | 14.6056 | 120.9961 | U | 993 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.19 | 7.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.36 | 70.6 |  | B - Node 0.5-1 km | 0.59 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1958
2 | 959 | 1959 | 1380606030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 424 | 14.6061 | 121.0024 | U | 1958 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.94 | 41.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.36 | 70.6 |  | B - Node 0.5-1 km | 0.51 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1959
2 | 960 | 1960 | 1380611035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 820 | 14.5818 | 120.9995 | U | 1460 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.03 | 54.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.36 | 70.6 |  | A - Node within 0.5 km | 0.46 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1960
2 | 961 | 1961 | 1380601254 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 253 | 14.6123 | 120.9779 | U | 1369 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.91 | 19.21 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.35 | 70.6 |  | B - Node 0.5-1 km | 0.7 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1961
2 | 962 | 1962 | 1380601227 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 226 | 14.6247 | 120.9836 | U | 1609 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.26 | 43.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.6 | 49.35 | 70.6 |  | B - Node 0.5-1 km | 0.91 | 0.06 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1962
2 | 963 | 1963 | PH0001963 | NCR | Metro Manila | Caloocan City | Barangay 31 | 14.6399 | 120.9738 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.68 | 2.36 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | D - Other node or line within 3 km | 1.04 | 1.02 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1963
2 | 964 | 1964 | 0403425016 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Vicente | 14.3415 | 121.0438 | U | 30211 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.55 | 5.48 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | B - Node 0.5-1 km | 0.5 | 0.23 | Line: AE SPL002 TO SPL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1964
2 | 965 | 1965 | 1380611025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 811 | 14.5795 | 121.0035 | U | 2403 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.87 | 9.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | B - Node 0.5-1 km | 0.55 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1965
2 | 966 | 1966 | 1381300135 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Balong Bato | 14.6636 | 121.0031 | U | 7284 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.23 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | D - Other node or line within 3 km | 1.23 | 0.61 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 1966
2 | 967 | 1967 | PH0001967 | NCR | Metro Manila | Caloocan City | Barangay 1 | 14.6098 | 120.9684 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.32 | 15.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | A - Node within 0.5 km | 0.36 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1967
2 | 968 | 1968 | 1381100022 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 22 | 14.617 | 120.9828 | U | 734 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.81 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | A - Node within 0.5 km | 0.06 | 0 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1968
2 | 969 | 1969 | 1380605055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 353 | 14.5482 | 121.008 | U | 2300 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.77 | 17.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | A - Node within 0.5 km | 0.4 | 0.23 | Line: Existing 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1969
2 | 970 | 1970 | 1380606001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 395 | 14.5994 | 120.9864 | U | 1259 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.96 | 77.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.59 | 49.35 | 70.59 |  | B - Node 0.5-1 km | 0.66 | 0.33 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1970
2 | 971 | 1971 | 1381300037 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa I | 15.5321 | 120.8474 | U | 2199 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.38 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.35 | 70.58 |  | D - Other node or line within 3 km | 4.13 | 2.24 | Line: 38,161m. | Route options survey candidate: compare actual node lateral with approved line tap. | 1971
2 | 972 | 1972 | 1380606074 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 468 | 14.6099 | 120.9938 | U | 1339 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.74 | 8.72 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.35 | 70.58 |  | B - Node 0.5-1 km | 0.8 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1972
2 | 973 | 1973 | 0603013050 | Region VI (Western Visayas) | Iloilo | Calinog | Manaripay | 11.2373 | 122.3884 | R | 501 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.52 | 18.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | F - Nearest node and line over 5 km | 31.52 | 22.79 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1973
2 | 974 | 1974 | 1380606035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 429 | 14.6047 | 120.9968 | U | 2899 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.45 | 49.43 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | B - Node 0.5-1 km | 0.63 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1974
2 | 975 | 1975 | 1380611009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 675 | 14.5839 | 120.9948 | U | 2048 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.11 | 36.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | B - Node 0.5-1 km | 0.86 | 0.3 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1975
2 | 976 | 1976 | 1380601151 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 151 | 14.6257 | 120.9769 | U | 1689 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.37 | 10.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | A - Node within 0.5 km | 0.41 | 0.11 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1976
2 | 977 | 1977 | 1381300059 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Mangga | 17.2945 | 121.6284 | U | 951 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | D - Other node or line within 3 km | 2.77 | 2.36 | Line: QUEZON | Route options survey candidate: compare actual node lateral with approved line tap. | 1977
2 | 978 | 1978 | 1380606209 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 602 | 14.5961 | 121.0151 | U | 2061 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.99 | 49.77 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | D - Other node or line within 3 km | 1.31 | 0.74 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 1978
2 | 979 | 1979 | 1380606130 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 524 | 14.6134 | 120.9983 | U | 891 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.26 | 7.9 | Tier 2 High GIDA (Score 40.0–49.9) | 70.58 | 49.34 | 70.58 |  | B - Node 0.5-1 km | 0.65 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1979
2 | 980 | 1980 | 1380601220 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 219 | 14.6238 | 120.9797 | U | 1113 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.86 | 34.86 | Tier 2 High GIDA (Score 40.0–49.9) | 70.57 | 49.34 | 70.57 |  | B - Node 0.5-1 km | 0.77 | 0.05 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1980
2 | 981 | 1981 | 1380614006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 749 | 14.5688 | 121.0067 | U | 635 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.19 | 65.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.57 | 49.34 | 70.57 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1981
2 | 982 | 1982 | 1380610031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 716 | 14.5695 | 120.9899 | U | 948 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.49 | 20.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.57 | 49.34 | 70.57 |  | B - Node 0.5-1 km | 0.55 | 0.21 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1982
2 | 983 | 1983 | 0405811011 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid II | 14.6871 | 121.1147 | U | 4458 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.16 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | A - Node within 0.5 km | 0.16 | 0.17 | Node: SMT001-TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1983
2 | 984 | 1984 | 1705306012 | MIMAROPA Region | Palawan | Brooke'S Point | Malis | 8.7185 | 117.7017 | R | 4279 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 160.45 | 162.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | F - Nearest node and line over 5 km | 160.45 | 162.45 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 1984
2 | 985 | 1985 | 1380611037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 822 | 14.584 | 121 | U | 924 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.93 | 41.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | A - Node within 0.5 km | 0.3 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1985
2 | 986 | 1986 | 1380601059 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 59 | 14.6158 | 120.969 | U | 1146 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.77 | 21.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | B - Node 0.5-1 km | 0.72 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1986
2 | 987 | 1987 | PH0001987 | NCR | Metro Manila | Caloocan City | Barangay 80 | 14.6159 | 120.9703 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.66 | 31.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | B - Node 0.5-1 km | 0.85 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1987
2 | 988 | 1988 | 1381100148 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 148 | 14.5351 | 121.0089 | U | 3254 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.82 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | D - Other node or line within 3 km | 1.5 | 0.57 | Line: Existing 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 1988
2 | 989 | 1989 | 1380612023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 855 | 14.5884 | 121.0027 | U | 2207 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.25 | 7.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.56 | 49.33 | 70.56 |  | A - Node within 0.5 km | 0.44 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1989
2 | 990 | 1990 | 1380603004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 384 | 14.5956 | 120.9896 | U | 3618 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.77 | 65.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.55 | 49.32 | 70.55 |  | B - Node 0.5-1 km | 0.8 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1990
2 | 991 | 1991 | 0401005072 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 3 | 13.7861 | 121.0792 | U | 268 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.4 | 7.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.32 | 70.54 |  | D - Other node or line within 3 km | 3.58 | 0.7 | Line: BATANGAS - SAN JUAN | Route options survey candidate: compare actual node lateral with approved line tap. | 1991
2 | 992 | 1992 | 1380614071 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 878 | 14.5839 | 121.0155 | U | 989 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.62 | 1.4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.32 | 70.54 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.06 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1992
2 | 993 | 1993 | 1380606090 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 484 | 14.6093 | 120.9928 | U | 1831 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45 | 48.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.32 | 70.54 |  | B - Node 0.5-1 km | 0.71 | 0.02 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1993
2 | 994 | 1994 | PH0001994 | IV-A | Cavite | Imus City | Palico I | 14.3895 | 120.9421 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 0.77 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.31 | 70.54 |  | B - Node 0.5-1 km | 0.72 | 6.31 | Node: IMC003 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1994
2 | 995 | 1995 | 1380610036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 721 | 14.5728 | 120.9887 | U | 595 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.3 | 46.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.31 | 70.54 |  | B - Node 0.5-1 km | 0.6 | 0.37 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1995
2 | 996 | 1996 | 1380611049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 687 | 14.5809 | 120.9965 | U | 1478 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.1 | 21.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.54 | 49.31 | 70.54 |  | B - Node 0.5-1 km | 0.78 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 1996
2 | 997 | 1997 | 1380614038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 782 | 14.5785 | 121.014 | U | 1528 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.62 | 42.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | C - Line within 0.5 km; node over 1 km | 1.37 | 0.34 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1997
2 | 998 | 1998 | 1380606075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 469 | 14.6133 | 120.9917 | U | 2015 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.21 | 5.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.18 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 1998
2 | 999 | 1999 | 1380610007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 692 | 14.5755 | 120.9925 | U | 1369 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.82 | 22.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | A - Node within 0.5 km | 0.43 | 0.26 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 1999
2 | 1000 | 2000 | 1380606009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 403 | 14.6033 | 120.9875 | U | 649 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.22 | 75.4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | A - Node within 0.5 km | 0.4 | 0 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2000

## Batch 3 (2,001 - 3,000)
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA — Batch 3 (2,001 - 3,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
3 | 1 | 2001 | 1380607011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 647 | 14.591 | 120.9905 | U | 2514 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.72 | 16.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | B - Node 0.5-1 km | 0.66 | 0.48 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2001
3 | 2 | 2002 | 1380601081 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 81 | 14.6146 | 120.9682 | U | 1870 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.38 | 42.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.53 | 49.31 | 70.53 |  | B - Node 0.5-1 km | 0.7 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2002
3 | 3 | 2003 | 0500507009 | Region V (Bicol Region) | Albay | Libon | Zone VI | 13.3089 | 123.4449 | R | 561 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.16 | 9.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.52 | 49.3 | 70.52 |  | D - Other node or line within 3 km | 1.23 | 0.72 | Line: IRIGA - LEGAZPI | Route options survey candidate: compare actual node lateral with approved line tap. | 2003
3 | 4 | 2004 | 1380612014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 846 | 14.5871 | 121.0028 | U | 1904 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.06 | 29.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.52 | 49.3 | 70.52 |  | A - Node within 0.5 km | 0.3 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2004
3 | 5 | 2005 | 1380602003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 289 | 14.5972 | 120.9714 | U | 1048 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.63 | 4.37 | Tier 2 High GIDA (Score 40.0–49.9) | 70.52 | 49.3 | 70.52 |  | D - Other node or line within 3 km | 1.09 | 0.98 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2005
3 | 6 | 2006 | 1380611031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 817 | 14.577 | 121.0002 | U | 1768 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.84 | 53.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.52 | 49.3 | 70.52 |  | B - Node 0.5-1 km | 0.84 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2006
3 | 7 | 2007 | PH0002007 | IV-A | Cavite | Imus City | Poblacion II-A (Pob.) | 14.4416 | 120.923 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 1.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.52 | 49.3 | 70.52 |  | D - Other node or line within 3 km | 2.76 | 0.85 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 2007
3 | 8 | 2008 | 1380606067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 461 | 14.609 | 120.9946 | U | 889 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.28 | 12.23 | Tier 2 High GIDA (Score 40.0–49.9) | 70.51 | 49.3 | 70.51 |  | B - Node 0.5-1 km | 0.75 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2008
3 | 9 | 2009 | PH0002009 | NCR | Metro Manila | Caloocan City | Barangay 84 | 14.6157 | 120.9666 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.75 | 34.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.51 | 49.29 | 70.51 |  | A - Node within 0.5 km | 0.48 | 0.39 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2009
3 | 10 | 2010 | 1380606038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 432 | 14.6056 | 120.9979 | U | 3540 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.68 | 42.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.51 | 49.29 | 70.51 |  | B - Node 0.5-1 km | 0.77 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2010
3 | 11 | 2011 | 0501602018 | Region V (Bicol Region) | Camarines Norte | Capalonga | San Roque | 14.3292 | 122.5521 | R | 1011 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.19 | 16.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | F - Nearest node and line over 5 km | 11.19 | 16.18 | Node: CCA001-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2011
3 | 12 | 2012 | 1380601166 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 166 | 14.6248 | 120.9719 | U | 909 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.01 | 59.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | A - Node within 0.5 km | 0.28 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2012
3 | 13 | 2013 | 1380606077 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 471 | 14.6109 | 120.9922 | U | 1458 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.88 | 24.82 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | B - Node 0.5-1 km | 0.87 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2013
3 | 14 | 2014 | 1380601006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 6 | 14.6084 | 120.9672 | U | 794 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.43 | 38.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | A - Node within 0.5 km | 0.32 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2014
3 | 15 | 2015 | 1380605043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 341 | 14.6169 | 120.9822 | U | 1507 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41 | 13.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | A - Node within 0.5 km | 0.09 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2015
3 | 16 | 2016 | PH0002016 | NCR | Metro Manila | Caloocan City | Barangay 34 | 14.6011 | 120.9632 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.65 | 59.67 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | B - Node 0.5-1 km | 0.82 | 0.93 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2016
3 | 17 | 2017 | 1380605077 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 374 | 14.6291 | 120.9826 | U | 3377 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.77 | 10.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.29 | 70.5 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2017
3 | 18 | 2018 | PH0002018 | NCR | Metro Manila | Caloocan City | Barangay 115 | 14.6179 | 120.9588 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.51 | 10.78 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.28 | 70.5 |  | A - Node within 0.5 km | 0.43 | 1.26 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2018
3 | 19 | 2019 | PH0002019 | NCR | Metro Manila | Caloocan City | Barangay 114 | 14.6191 | 120.9609 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.48 | 27.85 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.28 | 70.5 |  | A - Node within 0.5 km | 0.24 | 1.06 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2019
3 | 20 | 2020 | PH0002020 | NCR | Metro Manila | Caloocan City | Barangay 83 | 14.6613 | 120.9888 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.9 | 86.97 | Tier 2 High GIDA (Score 40.0–49.9) | 70.5 | 49.28 | 70.5 |  | A - Node within 0.5 km | 0.05 | 0.56 | Node: CCS005 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2020
3 | 21 | 2021 | 0405618045 | Region IV-A (CALABARZON) | Quezon | Guinayangan | San Pedro II | 13.9801 | 122.3526 | R | 266 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 10.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | D - Other node or line within 3 km | 1.42 | 2.94 | Node: GYQ003 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 2021
3 | 22 | 2022 | 1380605044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 342 | 14.6203 | 120.9847 | U | 1684 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.95 | 6.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | A - Node within 0.5 km | 0.47 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2022
3 | 23 | 2023 | 1380614015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 759 | 14.5661 | 121.0043 | U | 811 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.72 | 48.72 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | C - Line within 0.5 km; node over 1 km | 1.26 | 0.1 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2023
3 | 24 | 2024 | 1380606243 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 636 | 14.5999 | 121.003 | U | 2200 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.61 | 38.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | A - Node within 0.5 km | 0.29 | 0.19 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2024
3 | 25 | 2025 | PH0002025 | III | Nueva Ecija | Cabanatuan City | Padre Burgos (Pob.) | 15.5005 | 120.9716 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | D - Other node or line within 3 km | 2.37 | 0.55 | Line: TALAVERA - MULTI NET | Route options survey candidate: compare actual node lateral with approved line tap. | 2025
3 | 26 | 2026 | 0402106029 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco I | 14.335 | 120.9558 | R | 3262 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 3.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | D - Other node or line within 3 km | 2.45 | 3.63 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2026
3 | 27 | 2027 | 1380601137 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 137 | 14.6288 | 120.9675 | U | 939 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.44 | 17.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.49 | 49.28 | 70.49 |  | B - Node 0.5-1 km | 0.67 | 0.59 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2027
3 | 28 | 2028 | 1380601082 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 82 | 14.6181 | 120.9708 | U | 2722 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.35 | 42.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | B - Node 0.5-1 km | 0.87 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2028
3 | 29 | 2029 | 1381100056 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 56 | 14.5518 | 121.0028 | U | 879 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.3 | 4.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | B - Node 0.5-1 km | 0.95 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2029
3 | 30 | 2030 | 1380601086 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 86 | 14.618 | 120.967 | U | 1458 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.87 | 9.23 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | A - Node within 0.5 km | 0.46 | 0.39 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2030
3 | 31 | 2031 | PH0002031 | NCR | Metro Manila | Caloocan City | Barangay 50 | 14.6154 | 120.9717 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.71 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | B - Node 0.5-1 km | 0.99 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2031
3 | 32 | 2032 | PH0002032 | NCR | Metro Manila | Caloocan City | Barangay 95 | 14.62 | 120.964 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.96 | 49.69 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | A - Node within 0.5 km | 0.26 | 0.75 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2032
3 | 33 | 2033 | 1380601230 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 229 | 14.6257 | 120.982 | U | 1592 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.52 | 29.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | B - Node 0.5-1 km | 0.94 | 0.12 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2033
3 | 34 | 2034 | 1380607010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 646 | 14.5931 | 120.989 | U | 946 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.26 | 72.21 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | B - Node 0.5-1 km | 0.57 | 0.46 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2034
3 | 35 | 2035 | 1108210002 | Region XI (Davao Region) | Davao de Oro | New Bataan | Batinao | 7.5714 | 126.0617 | R | 1378 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.47 | 11.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.48 | 49.27 | 70.48 |  | F - Nearest node and line over 5 km | 28.47 | 11.28 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2035
3 | 36 | 2036 | 1380606040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 434 | 14.6033 | 120.9956 | U | 1209 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.12 | 24.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.27 | 70.47 |  | A - Node within 0.5 km | 0.48 | 0.26 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2036
3 | 37 | 2037 | 1380610011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 696 | 14.5754 | 120.9934 | U | 2493 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.91 | 36.74 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.27 | 70.47 |  | A - Node within 0.5 km | 0.39 | 0.17 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2037
3 | 38 | 2038 | 1380610009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 694 | 14.5778 | 120.9929 | U | 1320 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.93 | 22.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.27 | 70.47 |  | B - Node 0.5-1 km | 0.66 | 0.05 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2038
3 | 39 | 2039 | 1380603005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 385 | 14.5944 | 120.9875 | U | 3509 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.27 | 70.47 |  | B - Node 0.5-1 km | 0.55 | 0.47 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2039
3 | 40 | 2040 | 1380606196 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 589 | 14.601 | 121.0083 | U | 680 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.56 | 58.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.27 | 70.47 |  | A - Node within 0.5 km | 0.43 | 0.13 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2040
3 | 41 | 2041 | 1380601163 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 163 | 14.6284 | 120.9735 | U | 3957 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.84 | 3.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.26 | 70.47 |  | A - Node within 0.5 km | 0.17 | 0.19 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2041
3 | 42 | 2042 | 1381100181 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 181 | 14.5358 | 120.997 | U | 1937 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.11 | 11.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.26 | 70.47 |  | B - Node 0.5-1 km | 0.88 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2042
3 | 43 | 2043 | 1380601206 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 205 | 14.625 | 120.9768 | U | 1813 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.02 | 48.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.26 | 70.47 |  | A - Node within 0.5 km | 0.42 | 0.18 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2043
3 | 44 | 2044 | 1380602001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 287 | 14.5996 | 120.9709 | U | 2623 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.91 | 50.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.26 | 70.47 |  | B - Node 0.5-1 km | 0.81 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2044
3 | 45 | 2045 | 1380601250 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 249 | 14.6125 | 120.977 | U | 1659 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.4 | 27.09 | Tier 2 High GIDA (Score 40.0–49.9) | 70.47 | 49.26 | 70.47 |  | B - Node 0.5-1 km | 0.77 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2045
3 | 46 | 2046 | 1380611010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 676 | 14.5827 | 120.9973 | U | 1474 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.11 | 35.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.61 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2046
3 | 47 | 2047 | PH0002047 | NCR | Metro Manila | Caloocan City | Barangay 136 | 14.6308 | 120.9679 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.01 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.73 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2047
3 | 48 | 2048 | 1380606236 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 629 | 14.6014 | 121.006 | U | 1683 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.46 | 4.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | A - Node within 0.5 km | 0.18 | 0.06 | Line: UG 144C via W-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2048
3 | 49 | 2049 | 1380601140 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 140 | 14.6307 | 120.9673 | U | 559 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.81 | 15.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.78 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2049
3 | 50 | 2050 | 1380601182 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 182 | 14.6312 | 120.972 | U | 4056 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.11 | 80.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.5 | 0.5 | Node: MNL036 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2050
3 | 51 | 2051 | 1380601236 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 235 | 14.6232 | 120.9833 | U | 1604 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.87 | 14.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.74 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2051
3 | 52 | 2052 | 1380606063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 457 | 14.6091 | 120.9937 | U | 2519 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.14 | 41.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.72 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2052
3 | 53 | 2053 | 1380610016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 701 | 14.5689 | 120.9888 | U | 2777 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.37 | 29.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.46 | 49.26 | 70.46 |  | B - Node 0.5-1 km | 0.68 | 0.34 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2053
3 | 54 | 2054 | 1380606228 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 621 | 14.5909 | 121.0178 | U | 1841 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.7 | 11.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | D - Other node or line within 3 km | 1.37 | 0.5 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2054
3 | 55 | 2055 | 1380605048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 346 | 14.6191 | 120.9844 | U | 1557 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.88 | 46.04 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | A - Node within 0.5 km | 0.34 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2055
3 | 56 | 2056 | 1380601187 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 187 | 14.6324 | 120.9723 | U | 913 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.44 | 16.56 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | B - Node 0.5-1 km | 0.62 | 0.63 | Node: MNL036 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2056
3 | 57 | 2057 | PH0002057 | CAR | Benguet | Baguio City | Legarda-Burnham-Kisad | 16.4073 | 120.5973 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | B - Node 0.5-1 km | 0.59 | 0.32 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2057
3 | 58 | 2058 | PH0002058 | NCR | Metro Manila | Caloocan City | Barangay 16 | 14.6041 | 120.9638 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.35 | 38.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | B - Node 0.5-1 km | 0.7 | 0.71 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2058
3 | 59 | 2059 | 1380606022 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 416 | 14.6007 | 120.9933 | U | 846 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.22 | 37.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | A - Node within 0.5 km | 0.35 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2059
3 | 60 | 2060 | 1381100163 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 163 | 14.5346 | 121.0067 | U | 1509 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.94 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.33 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2060
3 | 61 | 2061 | 1380614063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 807 | 14.5797 | 121.0025 | U | 2071 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.77 | 64.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.45 | 49.25 | 70.45 |  | B - Node 0.5-1 km | 0.53 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2061
3 | 62 | 2062 | 1380500009 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Daang Bakal | 14.5703 | 121.0357 | U | 4956 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.25 | 70.44 |  | B - Node 0.5-1 km | 0.87 | 0.05 | Line: UG 144C via W-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2062
3 | 63 | 2063 | 1380601041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 41 | 14.6169 | 120.972 | U | 3941 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.44 | 29.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.25 | 70.44 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2063
3 | 64 | 2064 | 1380614070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 877 | 14.5835 | 121.0092 | U | 1868 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.62 | 32.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.25 | 70.44 |  | B - Node 0.5-1 km | 0.7 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2064
3 | 65 | 2065 | 1380601185 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 185 | 14.6301 | 120.9719 | U | 3639 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.6 | 15.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | A - Node within 0.5 km | 0.4 | 0.39 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2065
3 | 66 | 2066 | 1380606136 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 530 | 14.6135 | 121.0047 | U | 498 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.88 | 3.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | A - Node within 0.5 km | 0.3 | 0.24 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2066
3 | 67 | 2067 | 1380605014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 312 | 14.6063 | 120.9773 | U | 3429 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.13 | 4.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | B - Node 0.5-1 km | 0.82 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2067
3 | 68 | 2068 | 1380606087 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 481 | 14.6129 | 120.9945 | U | 1034 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.84 | 46.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.15 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2068
3 | 69 | 2069 | PH0002069 | NCR | Metro Manila | Caloocan City | Barangay 78 | 14.6142 | 120.9669 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.55 | 52.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | B - Node 0.5-1 km | 0.62 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2069
3 | 70 | 2070 | 1380601009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 9 | 14.6095 | 120.9702 | U | 461 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61 | 42.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | A - Node within 0.5 km | 0.3 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2070
3 | 71 | 2071 | 1380606062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 456 | 14.6103 | 120.9912 | U | 1576 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.74 | 24.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | B - Node 0.5-1 km | 0.8 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2071
3 | 72 | 2072 | PH0002072 | NCR | Metro Manila | Caloocan City | Barangay 81 | 14.6146 | 120.9682 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.12 | 25.81 | Tier 2 High GIDA (Score 40.0–49.9) | 70.44 | 49.24 | 70.44 |  | B - Node 0.5-1 km | 0.7 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2072
3 | 73 | 2073 | 1380601197 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 197 | 14.6341 | 120.9805 | U | 539 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.96 | 35.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2073
3 | 74 | 2074 | 1380610042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 727 | 14.5702 | 120.99 | U | 1844 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.24 | 4.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | A - Node within 0.5 km | 0.5 | 0.17 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2074
3 | 75 | 2075 | 1380606234 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 627 | 14.5883 | 121.0191 | U | 1654 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.98 | 23.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.2 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2075
3 | 76 | 2076 | 0403416039 | Region IV-A (CALABARZON) | Laguna | Majayjay | Tanawan | 14.1657 | 121.4525 | R | 93 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.8 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | D - Other node or line within 3 km | 3.16 | 1.9 | Line: PAGSANJAN TO LILIW | Route options survey candidate: compare actual node lateral with approved line tap. | 2076
3 | 77 | 2077 | 1380601177 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 177 | 14.6288 | 120.97 | U | 3408 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.47 | 78.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | A - Node within 0.5 km | 0.42 | 0.36 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2077
3 | 78 | 2078 | 1380601167 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 167 | 14.6269 | 120.9738 | U | 954 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.37 | 23.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | A - Node within 0.5 km | 0.05 | 0.04 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2078
3 | 79 | 2079 | 1380601150 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 150 | 14.6298 | 120.9663 | U | 2346 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.7 | 34.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | B - Node 0.5-1 km | 0.83 | 0.75 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2079
3 | 80 | 2080 | 1380604002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 269 | 14.6234 | 120.9838 | U | 931 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.61 | 21.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | B - Node 0.5-1 km | 0.78 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2080
3 | 81 | 2081 | 1380614084 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 891 | 14.5823 | 121.0161 | U | 783 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.89 | 7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.43 | 49.24 | 70.43 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.13 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2081
3 | 82 | 2082 | 1380614072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 879 | 14.5827 | 121.0134 | U | 554 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.98 | 51.92 | Tier 2 High GIDA (Score 40.0–49.9) | 70.42 | 49.23 | 70.42 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2082
3 | 83 | 2083 | PH0002083 | VI | Iloilo | Iloilo City | Mansaya-Lapuz | 10.7426 | 122.5641 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.02 | 11.67 | Tier 2 High GIDA (Score 40.0–49.9) | 70.42 | 49.23 | 70.42 |  | A - Node within 0.5 km | 0.43 | 0.07 | Line: 24c | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2083
3 | 84 | 2084 | 1380605042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 340 | 14.6181 | 120.9843 | U | 2070 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.59 | 7.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.23 | 70.41 |  | A - Node within 0.5 km | 0.23 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2084
3 | 85 | 2085 | 1380603012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 392 | 14.603 | 120.9881 | U | 716 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.68 | 41.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.23 | 70.41 |  | A - Node within 0.5 km | 0.34 | 0.06 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2085
3 | 86 | 2086 | PH0002086 | NCR | Metro Manila | Caloocan City | Barangay 77 | 14.6108 | 120.9644 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.91 | 10.69 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.72 | 0.51 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2086
3 | 87 | 2087 | 1380603016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 307 | 14.6112 | 120.993 | U | 1420 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.56 | 56.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.92 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2087
3 | 88 | 2088 | 1380605027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 325 | 14.6109 | 120.9797 | U | 538 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.11 | 32.83 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.71 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2088
3 | 89 | 2089 | PH0002089 | IV-A | Cavite | Imus City | Tanzang Luma I | 14.3929 | 120.92 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | D - Other node or line within 3 km | 2.34 | 4.71 | Node: IMC003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2089
3 | 90 | 2090 | 1380606002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 396 | 14.6028 | 120.9843 | U | 1717 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.2 | 30.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.74 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2090
3 | 91 | 2091 | 1380614094 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 901 | 14.5858 | 121.009 | U | 1659 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.14 | 6.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.69 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2091
3 | 92 | 2092 | 0200903004 | Region II (Cagayan Valley) | Batanes | Ivana | Tuhel | 20.3675 | 121.9142 | R | 385 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 213.67 | 208.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | F - Nearest node and line over 5 km | 212.01 | 208.92 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2092
3 | 93 | 2093 | 1380602007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 293 | 14.597 | 120.9723 | U | 3673 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.31 | 8.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | D - Other node or line within 3 km | 1.12 | 0.95 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2093
3 | 94 | 2094 | PH0002094 | NCR | Metro Manila | Caloocan City | Barangay 18 | 14.6017 | 120.9642 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.53 | 52.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.41 | 49.22 | 70.41 |  | B - Node 0.5-1 km | 0.82 | 0.8 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2094
3 | 95 | 2095 | 1380610008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 693 | 14.5743 | 120.9904 | U | 527 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.53 | 74.85 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | A - Node within 0.5 km | 0.49 | 0.34 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2095
3 | 96 | 2096 | 1380601179 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 179 | 14.6311 | 120.9704 | U | 1052 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.47 | 12.98 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | B - Node 0.5-1 km | 0.56 | 0.53 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2096
3 | 97 | 2097 | 1380601065 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 65 | 14.6108 | 120.9672 | U | 1681 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.07 | 40.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | B - Node 0.5-1 km | 0.52 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2097
3 | 98 | 2098 | 1380603011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 391 | 14.6013 | 120.9858 | U | 2636 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.76 | 32.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | B - Node 0.5-1 km | 0.61 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2098
3 | 99 | 2099 | 1380610059 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 688 | 14.5797 | 120.9944 | U | 1249 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.81 | 19.11 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | B - Node 0.5-1 km | 0.85 | 0.13 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2099
3 | 100 | 2100 | 0103304006 | Region I (Ilocos Region) | La Union | Bagulin | Libbo | 16.57 | 120.5244 | R | 961 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.64 | 8.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | F - Nearest node and line over 5 km | 8.64 | 8.14 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2100
3 | 101 | 2101 | 1380601091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 91 | 14.6195 | 120.9682 | U | 4690 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.37 | 38.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | B - Node 0.5-1 km | 0.61 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2101
3 | 102 | 2102 | PH0002102 | NCR | Metro Manila | Caloocan City | Barangay 35 | 14.6379 | 120.9731 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.83 | 5.88 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.22 | 70.4 |  | D - Other node or line within 3 km | 1.23 | 0.99 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2102
3 | 103 | 2103 | PH0002103 | NCR | Metro Manila | Caloocan City | Barangay 4 | 14.6086 | 120.9681 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.1 | 72.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.21 | 70.4 |  | A - Node within 0.5 km | 0.26 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2103
3 | 104 | 2104 | 1380601088 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 88 | 14.6156 | 120.9675 | U | 1129 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.5 | 13.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.21 | 70.4 |  | B - Node 0.5-1 km | 0.58 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2104
3 | 105 | 2105 | 0200903003 | Region II (Cagayan Valley) | Batanes | Ivana | San Vicente | 20.3807 | 121.9213 | R | 269 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 214.99 | 210.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.21 | 70.4 |  | F - Nearest node and line over 5 km | 213.39 | 210.29 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2105
3 | 106 | 2106 | 1380601145 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 145 | 14.6312 | 120.9675 | U | 1060 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.74 | 32.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.21 | 70.4 |  | B - Node 0.5-1 km | 0.79 | 0.73 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2106
3 | 107 | 2107 | 1380613002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 650 | 14.5926 | 120.9612 | U | 5360 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.47 | 71.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.4 | 49.21 | 70.4 |  | A - Node within 0.5 km | 0.14 | 1.77 | Node: MNL068 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2107
3 | 108 | 2108 | 1380602005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 291 | 14.5994 | 120.9718 | U | 2348 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.18 | 31.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | B - Node 0.5-1 km | 0.85 | 0.74 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2108
3 | 109 | 2109 | PH0002109 | NCR | Metro Manila | Caloocan City | Barangay 20 | 14.6489 | 120.9686 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.69 | 1.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | A - Node within 0.5 km | 0.47 | 1 | Node: CCS004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2109
3 | 110 | 2110 | 1380614004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 747 | 14.5666 | 121.0062 | U | 380 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.19 | 28.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.15 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2110
3 | 111 | 2111 | 1380606037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 431 | 14.6069 | 120.9973 | U | 721 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.21 | 13.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | B - Node 0.5-1 km | 0.78 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2111
3 | 112 | 2112 | 1380603003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 383 | 14.5921 | 120.987 | U | 2336 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.5 | 4.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | A - Node within 0.5 km | 0.34 | 0.24 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2112
3 | 113 | 2113 | PH0002113 | IV-A | Laguna | San Pablo City | Barangay II-A (Pob.) | 14.0623 | 121.3201 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.34 | Line: AE NGL001 TO SPO001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2113
3 | 114 | 2114 | 1380601233 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 232 | 14.6221 | 120.9803 | U | 1832 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.9 | 59.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | B - Node 0.5-1 km | 0.68 | 0.14 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2114
3 | 115 | 2115 | 1380601178 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 178 | 14.6276 | 120.9725 | U | 1565 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.69 | 1.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | A - Node within 0.5 km | 0.12 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2115
3 | 116 | 2116 | 1380605074 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 371 | 14.6281 | 120.9842 | U | 868 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.06 | 43.43 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.02 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2116
3 | 117 | 2117 | PH0002117 | NCR | Metro Manila | Caloocan City | Barangay 134 | 14.6285 | 120.9675 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.6 | 46.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | B - Node 0.5-1 km | 0.66 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2117
3 | 118 | 2118 | 1380610056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 742 | 14.5679 | 121.0074 | U | 832 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.17 | 47.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | C - Line within 0.5 km; node over 1 km | 1.49 | 0.03 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2118
3 | 119 | 2119 | 0205009018 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Pao | 16.2313 | 121.3495 | R | 1508 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.16 | 30.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | F - Nearest node and line over 5 km | 11.16 | 30.58 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2119
3 | 120 | 2120 | 1380612033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 865 | 14.5839 | 121.0065 | U | 81 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.51 | 28.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.39 | 49.21 | 70.39 |  | A - Node within 0.5 km | 0.41 | 0.43 | Node: MNL004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2120
3 | 121 | 2121 | 1903614012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Liangan | 17.2546 | 122.2287 | R | 1120 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.38 | 49.2 | 70.38 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2121
3 | 122 | 2122 | 0405603031 | Region IV-A (CALABARZON) | Quezon | Atimonan | San Andres Bundok | 13.9527 | 121.8657 | R | 283 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.76 | 4.13 | Tier 2 High GIDA (Score 40.0–49.9) | 70.38 | 49.2 | 70.38 |  | E - Nearest node or line 3-5 km | 6.76 | 4.13 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2122
3 | 123 | 2123 | PH0002123 | XI | Davao Del Sur | Davao City | Barangay 27-C (Pob.) | 7.2617 | 125.6488 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.34 | 2.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.38 | 49.2 | 70.38 |  | C - Line within 0.5 km; node over 1 km | 5.55 | 0.48 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2123
3 | 124 | 2124 | 1381300100 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Jose | 14.5637 | 121.0473 | U | 6089 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.03 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.38 | 49.2 | 70.38 |  | C - Line within 0.5 km; node over 1 km | 2.03 | 0.44 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2124
3 | 125 | 2125 | 1380601234 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 233 | 14.6256 | 120.9829 | U | 757 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.25 | 4.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.38 | 49.2 | 70.38 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.02 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2125
3 | 126 | 2126 | PH0002126 | NCR | Metro Manila | Caloocan City | Barangay 138 | 14.6284 | 120.9684 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.64 | 70.44 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.2 | 70.37 |  | B - Node 0.5-1 km | 0.56 | 0.48 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2126
3 | 127 | 2127 | 1380612001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 833 | 14.5813 | 120.9971 | U | 1550 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.71 | 17.62 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.2 | 70.37 |  | B - Node 0.5-1 km | 0.7 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2127
3 | 128 | 2128 | 1380601160 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 160 | 14.6289 | 120.9766 | U | 1294 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.13 | 84.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.2 | 70.37 |  | A - Node within 0.5 km | 0.42 | 0.24 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2128
3 | 129 | 2129 | PH0002129 | NCR | Metro Manila | Caloocan City | Barangay 39 | 14.6193 | 120.9716 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.94 | 1.03 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.2 | 70.37 |  | B - Node 0.5-1 km | 0.86 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2129
3 | 130 | 2130 | 1380601007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 7 | 14.6072 | 120.9698 | U | 1607 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.99 | 22.11 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.2 | 70.37 |  | A - Node within 0.5 km | 0.05 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2130
3 | 131 | 2131 | 1380614020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 764 | 14.5694 | 121.0077 | U | 2083 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.65 | 32.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.37 | 49.19 | 70.37 |  | C - Line within 0.5 km; node over 1 km | 1.48 | 0.08 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2131
3 | 132 | 2132 | 1380605019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 317 | 14.6067 | 120.9869 | U | 1589 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.53 | 23.11 | Tier 2 High GIDA (Score 40.0–49.9) | 70.36 | 49.19 | 70.36 |  | B - Node 0.5-1 km | 0.61 | 0.11 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2132
3 | 133 | 2133 | 1380601210 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 209 | 14.6245 | 120.9824 | U | 5229 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.79 | 14.8 | Tier 2 High GIDA (Score 40.0–49.9) | 70.36 | 49.19 | 70.36 |  | B - Node 0.5-1 km | 0.9 | 0.06 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2133
3 | 134 | 2134 | 1380614033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 777 | 14.576 | 121.0067 | U | 3102 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.16 | 44.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.36 | 49.19 | 70.36 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.39 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2134
3 | 135 | 2135 | PH0002135 | NCR | Metro Manila | Caloocan City | Barangay 139 | 14.6598 | 120.9984 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.89 | 31.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.36 | 49.19 | 70.36 |  | D - Other node or line within 3 km | 1.01 | 1.27 | Node: CCS005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2135
3 | 136 | 2136 | 1380605067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 365 | 14.5554 | 120.9925 | U | 1317 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.87 | 14.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.36 | 49.19 | 70.36 |  | A - Node within 0.5 km | 0.25 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2136
3 | 137 | 2137 | 1380605013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 311 | 14.6075 | 120.9794 | U | 2474 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.6 | 35.4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.35 | 49.18 | 70.35 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.32 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2137
3 | 138 | 2138 | 1380605053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 351 | 14.546 | 121.0076 | U | 3504 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.56 | 63.02 | Tier 2 High GIDA (Score 40.0–49.9) | 70.35 | 49.18 | 70.35 |  | B - Node 0.5-1 km | 0.59 | 0.37 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2138
3 | 139 | 2139 | 1402706019 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Liwo | 16.9813 | 121.2622 | R | 196 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.42 | 22.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.35 | 49.18 | 70.35 |  | E - Nearest node or line 3-5 km | 4.42 | 23.84 | Node: MOF001 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2139
3 | 140 | 2140 | 1380606185 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 579 | 14.6037 | 121.0107 | U | 1755 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.38 | 37.66 | Tier 2 High GIDA (Score 40.0–49.9) | 70.35 | 49.18 | 70.35 |  | B - Node 0.5-1 km | 0.69 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2140
3 | 141 | 2141 | 1380606088 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 482 | 14.6117 | 120.9924 | U | 722 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.77 | 25.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.35 | 49.18 | 70.35 |  | B - Node 0.5-1 km | 0.96 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2141
3 | 142 | 2142 | 1380612039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 869 | 14.5838 | 121.0074 | U | 2071 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.61 | 8.9 | Tier 2 High GIDA (Score 40.0–49.9) | 70.34 | 49.18 | 70.34 |  | B - Node 0.5-1 km | 0.51 | 0.39 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2142
3 | 143 | 2143 | 1381100008 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 8 | 14.5583 | 120.9917 | U | 1193 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 3.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.34 | 49.17 | 70.34 |  | B - Node 0.5-1 km | 0.56 | 0.46 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2143
3 | 144 | 2144 | 1381100054 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 54 | 14.5521 | 121.0011 | U | 1521 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.34 | 49.17 | 70.34 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.27 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2144
3 | 145 | 2145 | 1380601228 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 227 | 14.6235 | 120.9815 | U | 1892 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.23 | 2.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.34 | 49.17 | 70.34 |  | B - Node 0.5-1 km | 0.79 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2145
3 | 146 | 2146 | 0402106073 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel II | 14.2827 | 120.9092 | R | 2717 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.98 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | D - Other node or line within 3 km | 1.28 | 1.01 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2146
3 | 147 | 2147 | PH0002147 | XI | Davao de Oro | Mabini Compostela Valley | Libodon | 7.2973 | 126.0083 | R | 2247 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.39 | 13.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | F - Nearest node and line over 5 km | 16.89 | 16.67 | Line: TAGUM - PANTUKAN SEGMENT 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2147
3 | 148 | 2148 | 1903631024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Pasayanan | 17.2548 | 122.2289 | R | 853 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | F - Nearest node and line over 5 km | 29.41 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2148
3 | 149 | 2149 | 1380602008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 294 | 14.5958 | 120.9702 | U | 1938 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.54 | 68.88 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | B - Node 0.5-1 km | 0.97 | 1.12 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2149
3 | 150 | 2150 | 1380601239 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 238 | 14.6117 | 120.9769 | U | 375 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.5 | 6.85 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | B - Node 0.5-1 km | 0.83 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2150
3 | 151 | 2151 | 1380605057 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 355 | 14.5539 | 120.994 | U | 999 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.28 | 37.83 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | A - Node within 0.5 km | 0.26 | 0.03 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2151
3 | 152 | 2152 | 1381100108 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 108 | 14.5455 | 121.0013 | U | 2129 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.17 | 70.33 |  | B - Node 0.5-1 km | 0.74 | 0.21 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2152
3 | 153 | 2153 | 1380601136 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 136 | 14.6308 | 120.9679 | U | 1233 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.25 | 37.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.33 | 49.16 | 70.33 |  | B - Node 0.5-1 km | 0.73 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2153
3 | 154 | 2154 | 1380605056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 354 | 14.5547 | 120.9924 | U | 1865 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.73 | 27.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.32 | 49.16 | 70.32 |  | A - Node within 0.5 km | 0.17 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2154
3 | 155 | 2155 | 1380605046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 344 | 14.6179 | 120.9852 | U | 552 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.25 | 30.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.32 | 49.16 | 70.32 |  | A - Node within 0.5 km | 0.29 | 0.08 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2155
3 | 156 | 2156 | PH0002156 | CAR | Benguet | Baguio City | Cresencia Village | 16.4196 | 120.588 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.32 | 49.16 | 70.32 |  | B - Node 0.5-1 km | 0.5 | 0.61 | Node: BGC002 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2156
3 | 157 | 2157 | 1380601196 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 196 | 14.6338 | 120.9805 | U | 1681 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.8 | 11.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.16 | 70.31 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.08 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2157
3 | 158 | 2158 | 0405634040 | Region IV-A (CALABARZON) | Quezon | Pitogo | Sumag Weste | 13.7869 | 122.0865 | R | 258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 1.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.16 | 70.31 |  | E - Nearest node or line 3-5 km | 3.24 | 3.22 | Line: UNISAN TO MULANAY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2158
3 | 159 | 2159 | PH0002159 | XI | Davao de Oro | Mabini Compostela Valley | Cadunan | 7.3309 | 125.8579 | R | 2247 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.67 | 46.71 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.16 | 70.31 |  | C - Line within 0.5 km; node over 1 km | 2.47 | 0.07 | Line: TAGUM - PANTUKAN SEGMENT 2 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2159
3 | 160 | 2160 | 1400109001 | Cordillera Administrative Region (CAR) | Abra | Lacub | Bacag | 17.6955 | 120.9117 | R | 273 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.25 | 26.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.16 | 70.31 |  | F - Nearest node and line over 5 km | 26.25 | 26.07 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2160
3 | 161 | 2161 | 1380610055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 741 | 14.5691 | 121.0049 | U | 1244 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.65 | 27.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.16 | 70.31 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2161
3 | 162 | 2162 | 1380601003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 3 | 14.6074 | 120.9689 | U | 1382 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.61 | 78.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.15 | 70.31 |  | A - Node within 0.5 km | 0.1 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2162
3 | 163 | 2163 | 1380601078 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 78 | 14.6142 | 120.9669 | U | 1258 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.87 | 25.9 | Tier 2 High GIDA (Score 40.0–49.9) | 70.31 | 49.15 | 70.31 |  | B - Node 0.5-1 km | 0.62 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2163
3 | 164 | 2164 | 1380601120 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 120 | 14.609 | 120.9636 | U | 3991 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.95 | 25.36 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.15 | 70.3 |  | B - Node 0.5-1 km | 0.69 | 0.59 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2164
3 | 165 | 2165 | PH0002165 | NCR | Metro Manila | Caloocan City | Barangay 41 | 14.6169 | 120.972 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.9 | 14.01 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.15 | 70.3 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2165
3 | 166 | 2166 | 1380610060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 735 | 14.567 | 121.0035 | U | 2126 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.97 | 13.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.15 | 70.3 |  | C - Line within 0.5 km; node over 1 km | 1.14 | 0.02 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2166
3 | 167 | 2167 | PH0002167 | VII | Cebu | Talisay City | San Roque | 10.2565 | 123.8604 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.99 | 11.58 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.15 | 70.3 |  | C - Line within 0.5 km; node over 1 km | 2.25 | 0.01 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2167
3 | 168 | 2168 | 1380601056 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 56 | 14.6103 | 120.9709 | U | 3562 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.21 | 11.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.15 | 70.3 |  | A - Node within 0.5 km | 0.41 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2168
3 | 169 | 2169 | PH0002169 | XI | Davao Del Sur | Davao City | Barangay 26-C (Pob.) | 7.5586 | 125.4768 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.14 | 70.3 |  | F - Nearest node and line over 5 km | 26.92 | 25.42 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2169
3 | 170 | 2170 | 1380606214 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 607 | 14.5947 | 121.0185 | U | 1836 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.62 | 52.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.14 | 70.3 |  | D - Other node or line within 3 km | 1.61 | 0.76 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2170
3 | 171 | 2171 | 1380605047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 345 | 14.6214 | 120.9831 | U | 1184 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.78 | 6.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.14 | 70.3 |  | B - Node 0.5-1 km | 0.54 | 0.01 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2171
3 | 172 | 2172 | PH0002172 | CAR | Benguet | Baguio City | Padre Zamora | 16.4042 | 120.5668 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.14 | 1.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70.3 | 49.14 | 70.3 |  | B - Node 0.5-1 km | 0.59 | 0.6 | Node: BGC008 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2172
3 | 173 | 2173 | 0102908006 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Dinwede West | 16.9055 | 120.6042 | R | 843 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.45 | 14.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | F - Nearest node and line over 5 km | 11.45 | 14.82 | Node: SUI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2173
3 | 174 | 2174 | 1380601240 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 239 | 14.6105 | 120.9748 | U | 1839 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.94 | 35.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | B - Node 0.5-1 km | 0.69 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2174
3 | 175 | 2175 | 1380610052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 738 | 14.5681 | 121.0065 | U | 3140 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.92 | 53.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | C - Line within 0.5 km; node over 1 km | 1.39 | 0 | Line: UG 288C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2175
3 | 176 | 2176 | PH0002176 | NCR | Metro Manila | Caloocan City | Barangay 85 | 14.6145 | 120.9691 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.14 | 45.07 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | B - Node 0.5-1 km | 0.79 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2176
3 | 177 | 2177 | 1380601005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 5 | 14.6096 | 120.9693 | U | 1327 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.47 | 40.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | A - Node within 0.5 km | 0.32 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2177
3 | 178 | 2178 | 1381100129 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 129 | 14.5474 | 121.0068 | U | 1243 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.57 | 2.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | B - Node 0.5-1 km | 0.56 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2178
3 | 179 | 2179 | PH0002179 | NCR | Metro Manila | Caloocan City | Barangay 5 | 14.6566 | 120.9736 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.75 | 58.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.29 | 49.14 | 70.29 |  | B - Node 0.5-1 km | 0.82 | 0.37 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2179
3 | 180 | 2180 | PH0002180 | NCR | Metro Manila | Caloocan City | Barangay 53 | 14.6165 | 120.9701 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.37 | 25.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | B - Node 0.5-1 km | 0.81 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2180
3 | 181 | 2181 | PH0002181 | NCR | Metro Manila | Caloocan City | Barangay 125 | 14.6457 | 120.9899 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 14.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | B - Node 0.5-1 km | 0.64 | 0.54 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2181
3 | 182 | 2182 | 1102315017 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Lower Panaga | 7.4467 | 125.5621 | R | 1625 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.01 | 18.56 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | F - Nearest node and line over 5 km | 19.01 | 18.54 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2182
3 | 183 | 2183 | 0102934004 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay II | 17.5552 | 120.3652 | U | 482 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.2 | 2.8 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | E - Nearest node or line 3-5 km | 5.03 | 3.81 | Line: SEGMENT 3 (VIGAN - BATAC) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2183
3 | 184 | 2184 | 1908801008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Ampatuan | Saniag | 6.8319 | 124.4569 | R | 1470 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.67 | 28.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | F - Nearest node and line over 5 km | 28.67 | 28.61 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2184
3 | 185 | 2185 | 1380606032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 426 | 14.6037 | 121.0028 | U | 1840 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.67 | 22.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.28 | 49.13 | 70.28 |  | A - Node within 0.5 km | 0.26 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2185
3 | 186 | 2186 | 1380601209 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 208 | 14.6257 | 120.9798 | U | 654 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.27 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.13 | 70.27 |  | B - Node 0.5-1 km | 0.71 | 0.04 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2186
3 | 187 | 2187 | 1380606099 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 493 | 14.6233 | 120.9936 | U | 1206 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.04 | 12.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.13 | 70.27 |  | D - Other node or line within 3 km | 1.39 | 0.5 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2187
3 | 188 | 2188 | 1380605016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 314 | 14.6063 | 120.9791 | U | 2127 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.27 | 78.95 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.13 | 70.27 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.18 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2188
3 | 189 | 2189 | 1380601267 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 266 | 14.6224 | 120.9855 | U | 1716 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.3 | 15.16 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.13 | 70.27 |  | B - Node 0.5-1 km | 0.71 | 0.28 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2189
3 | 190 | 2190 | 0402123024 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Gabriel | 14.2826 | 121.0011 | U | 9168 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.11 | 3.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.12 | 70.27 |  | A - Node within 0.5 km | 0.11 | 3.87 | Node: MAC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2190
3 | 191 | 2191 | 1003506019 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Mabuhay | 7.8401 | 123.6291 | R | 508 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.63 | 11 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.12 | 70.27 |  | E - Nearest node or line 3-5 km | 13.37 | 4.47 | Line: ILIGAN - PAGADIAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2191
3 | 192 | 2192 | 1380614069 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 876 | 14.5847 | 121.0067 | U | 591 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.44 | 31.93 | Tier 2 High GIDA (Score 40.0–49.9) | 70.27 | 49.12 | 70.27 |  | A - Node within 0.5 km | 0.42 | 0.46 | Node: MNL004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2192
3 | 193 | 2193 | 1380605038 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 336 | 14.6062 | 120.9784 | U | 2199 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.95 | 27.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | B - Node 0.5-1 km | 0.94 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2193
3 | 194 | 2194 | 1380605021 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 319 | 14.6089 | 120.9874 | U | 1246 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.01 | 22.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | B - Node 0.5-1 km | 0.76 | 0.15 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2194
3 | 195 | 2195 | 1380605009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 305 | 14.6103 | 120.992 | U | 665 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.42 | 36.28 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | B - Node 0.5-1 km | 0.8 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2195
3 | 196 | 2196 | PH0002196 | NCR | Metro Manila | Caloocan City | Barangay 22 | 14.6015 | 120.9605 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.09 | 78.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | B - Node 0.5-1 km | 0.86 | 1.15 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2196
3 | 197 | 2197 | 1380614099 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 754 | 14.5675 | 121.0055 | U | 2662 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.43 | 21.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | C - Line within 0.5 km; node over 1 km | 1.31 | 0.06 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2197
3 | 198 | 2198 | 1380605037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 335 | 14.6074 | 120.9805 | U | 1391 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.64 | 30.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.19 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2198
3 | 199 | 2199 | 1381100174 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 174 | 14.5335 | 121.0129 | U | 1878 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.6 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | D - Other node or line within 3 km | 1.32 | 0.58 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2199
3 | 200 | 2200 | 1380601180 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 180 | 14.6296 | 120.9719 | U | 2210 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.38 | 68.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | A - Node within 0.5 km | 0.34 | 0.32 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2200
3 | 201 | 2201 | 1380601048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 48 | 14.6178 | 120.9713 | U | 4194 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.56 | 33.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70.26 | 49.12 | 70.26 |  | B - Node 0.5-1 km | 0.92 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2201
3 | 202 | 2202 | PH0002202 | NCR | Metro Manila | Caloocan City | Barangay 27 | 14.6002 | 120.9639 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.34 | 7.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.25 | 49.11 | 70.25 |  | B - Node 0.5-1 km | 0.75 | 0.93 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2202
3 | 203 | 2203 | 1380611028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 814 | 14.5806 | 121.0018 | U | 2263 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.46 | 19.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.25 | 49.11 | 70.25 |  | A - Node within 0.5 km | 0.44 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2203
3 | 204 | 2204 | 1381100019 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 19 | 14.5574 | 120.9898 | U | 835 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.33 | 4.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.25 | 49.11 | 70.25 |  | B - Node 0.5-1 km | 0.5 | 0.49 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2204
3 | 205 | 2205 | 1380614055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 799 | 14.5717 | 120.9971 | U | 561 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.48 | 4.68 | Tier 2 High GIDA (Score 40.0–49.9) | 70.25 | 49.11 | 70.25 |  | A - Node within 0.5 km | 0.31 | 0.09 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2205
3 | 206 | 2206 | 1380605035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 333 | 14.6051 | 120.98 | U | 904 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 2.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.25 | 49.11 | 70.25 |  | C - Line within 0.5 km; node over 1 km | 1.13 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2206
3 | 207 | 2207 | 1380602002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 288 | 14.5984 | 120.9735 | U | 2615 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.23 | 62.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.11 | 70.24 |  | D - Other node or line within 3 km | 1.02 | 0.8 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2207
3 | 208 | 2208 | 1381100176 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 176 | 14.5339 | 121.0119 | U | 1663 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.73 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.11 | 70.24 |  | D - Other node or line within 3 km | 1.39 | 0.66 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2208
3 | 209 | 2209 | 1380605022 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 320 | 14.6077 | 120.9853 | U | 1339 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.8 | 2.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | B - Node 0.5-1 km | 0.82 | 0.08 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2209
3 | 210 | 2210 | 1381100004 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 4 | 14.5577 | 120.9905 | U | 2145 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.76 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | B - Node 0.5-1 km | 0.51 | 0.5 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2210
3 | 211 | 2211 | 0402106043 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Lucia | 14.2871 | 120.9802 | U | 5826 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 2.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | D - Other node or line within 3 km | 2.41 | 1.99 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2211
3 | 212 | 2212 | 1903612039 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumbatan | Picotaan | 17.2548 | 122.2288 | R | 2403 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | F - Nearest node and line over 5 km | 29.41 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2212
3 | 213 | 2213 | 1381100006 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 6 | 14.5598 | 120.9911 | U | 476 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.54 | 10.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | B - Node 0.5-1 km | 0.73 | 0.49 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2213
3 | 214 | 2214 | 1381100182 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 182 | 14.5234 | 121.0138 | U | 2989 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 70.24 | 49.1 | 70.24 |  | A - Node within 0.5 km | 0.26 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2214
3 | 215 | 2215 | 0402106050 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado II | 14.299 | 120.9987 | R | 2943 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 3.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.23 | 49.1 | 70.23 |  | D - Other node or line within 3 km | 1.88 | 4.3 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2215
3 | 216 | 2216 | 1380601155 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 155 | 14.6256 | 120.9732 | U | 3356 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.6 | 36.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.23 | 49.1 | 70.23 |  | A - Node within 0.5 km | 0.14 | 0 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2216
3 | 217 | 2217 | 1380601225 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 224 | 14.6224 | 120.9832 | U | 1101 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.61 | 43.36 | Tier 2 High GIDA (Score 40.0–49.9) | 70.23 | 49.1 | 70.23 |  | B - Node 0.5-1 km | 0.66 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2217
3 | 218 | 2218 | 1380605075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 372 | 14.6269 | 120.9821 | U | 4262 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.11 | 35.44 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | B - Node 0.5-1 km | 0.94 | 0.1 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2218
3 | 219 | 2219 | PH0002219 | NCR | Metro Manila | Caloocan City | Barangay 12 | 14.6105 | 120.9686 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.82 | 63.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | A - Node within 0.5 km | 0.43 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2219
3 | 220 | 2220 | 1380614067 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 874 | 14.5824 | 121.0062 | U | 2077 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.19 | 22.23 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | A - Node within 0.5 km | 0.43 | 0.28 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2220
3 | 221 | 2221 | 0502006027 | Region V (Bicol Region) | Catanduanes | Pandan | Wagdas | 14.0485 | 124.1385 | R | 638 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.47 | 84.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | F - Nearest node and line over 5 km | 42.56 | 80.31 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2221
3 | 222 | 2222 | 1380601222 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 221 | 14.626 | 120.9802 | U | 3455 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.36 | 11.14 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | B - Node 0.5-1 km | 0.74 | 0.09 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2222
3 | 223 | 2223 | 1380610057 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 743 | 14.5667 | 121.0053 | U | 1656 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.83 | 22.68 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | C - Line within 0.5 km; node over 1 km | 1.33 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2223
3 | 224 | 2224 | 1403213038 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Lacnog | 17.398 | 121.5131 | R | 3315 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.49 | 4.47 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | D - Other node or line within 3 km | 2.49 | 4.42 | Node: TKK004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 2224
3 | 225 | 2225 | 1380605025 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 323 | 14.6133 | 120.9792 | U | 1092 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.2 | 85.32 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | B - Node 0.5-1 km | 0.53 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2225
3 | 226 | 2226 | 0200903002 | Region II (Cagayan Valley) | Batanes | Ivana | Salagao | 20.3688 | 121.9151 | R | 370 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 213.75 | 209.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | F - Nearest node and line over 5 km | 212.15 | 209.06 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2226
3 | 227 | 2227 | 1380614054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 798 | 14.5683 | 120.9992 | U | 1609 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.58 | 17.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.22 | 49.09 | 70.22 |  | B - Node 0.5-1 km | 0.68 | 0.36 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2227
3 | 228 | 2228 | 1380200018 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Tres | 14.4407 | 121.004 | U | 33466 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.37 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.21 | 49.09 | 70.21 |  | A - Node within 0.5 km | 0.37 | 0.23 | Line: UG | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2228
3 | 229 | 2229 | 1380614079 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 886 | 14.5836 | 121.0173 | U | 396 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.01 | 24.02 | Tier 2 High GIDA (Score 40.0–49.9) | 70.21 | 49.09 | 70.21 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2229
3 | 230 | 2230 | 0405632004 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Luod | 14.8285 | 122.1019 | R | 1004 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.61 | 77.12 | Tier 2 High GIDA (Score 40.0–49.9) | 70.21 | 49.08 | 70.21 |  | F - Nearest node and line over 5 km | 47.61 | 77.1 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2230
3 | 231 | 2231 | 1380605049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 347 | 14.619 | 120.9835 | U | 1304 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.63 | 16.91 | Tier 2 High GIDA (Score 40.0–49.9) | 70.21 | 49.08 | 70.21 |  | A - Node within 0.5 km | 0.29 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2231
3 | 232 | 2232 | 1380601251 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 250 | 14.6113 | 120.9749 | U | 1218 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.46 | 19.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.2 | 49.08 | 70.2 |  | B - Node 0.5-1 km | 0.76 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2232
3 | 233 | 2233 | PH0002233 | NCR | Metro Manila | Caloocan City | Barangay 131 | 14.6275 | 120.9691 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.33 | 10.39 | Tier 2 High GIDA (Score 40.0–49.9) | 70.2 | 49.08 | 70.2 |  | A - Node within 0.5 km | 0.46 | 0.37 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2233
3 | 234 | 2234 | 1380601144 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 144 | 14.6324 | 120.9696 | U | 907 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.98 | 45.07 | Tier 2 High GIDA (Score 40.0–49.9) | 70.2 | 49.08 | 70.2 |  | B - Node 0.5-1 km | 0.74 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2234
3 | 235 | 2235 | 1380607008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 644 | 14.5946 | 120.9875 | U | 751 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.1 | 12.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.2 | 49.08 | 70.2 |  | B - Node 0.5-1 km | 0.56 | 0.46 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2235
3 | 236 | 2236 | 1380605050 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 348 | 14.6178 | 120.9861 | U | 1287 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.66 | 28.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.19 | 49.07 | 70.19 |  | A - Node within 0.5 km | 0.37 | 0.07 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2236
3 | 237 | 2237 | 1380606222 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 615 | 14.5944 | 121.0156 | U | 1884 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.98 | 57.69 | Tier 2 High GIDA (Score 40.0–49.9) | 70.18 | 49.07 | 70.18 |  | D - Other node or line within 3 km | 1.47 | 0.92 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2237
3 | 238 | 2238 | 1380601260 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 259 | 14.6064 | 120.9756 | U | 2153 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.86 | 42.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.18 | 49.06 | 70.18 |  | B - Node 0.5-1 km | 0.64 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2238
3 | 239 | 2239 | 1908713021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Rifao | 17.254 | 122.2281 | U | 2647 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 70.18 | 49.06 | 70.18 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2239
3 | 240 | 2240 | 1380601122 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 122 | 14.6112 | 120.9641 | U | 3940 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.21 | 17.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.18 | 49.06 | 70.18 |  | B - Node 0.5-1 km | 0.77 | 0.55 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2240
3 | 241 | 2241 | 1380601087 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 87 | 14.6167 | 120.9696 | U | 1683 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.52 | 0.79 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.06 | 70.17 |  | B - Node 0.5-1 km | 0.75 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2241
3 | 242 | 2242 | PH0002242 | NCR | Metro Manila | Caloocan City | Barangay 19 | 14.6005 | 120.9621 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.83 | 32.77 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.06 | 70.17 |  | B - Node 0.5-1 km | 0.74 | 1.06 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2242
3 | 243 | 2243 | 1380601208 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 207 | 14.6269 | 120.9819 | U | 1588 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.22 | 5.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.06 | 70.17 |  | B - Node 0.5-1 km | 0.93 | 0.12 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2243
3 | 244 | 2244 | 1380614091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 898 | 14.5869 | 121.0185 | U | 7827 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.25 | 7.4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.06 | 70.17 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.13 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2244
3 | 245 | 2245 | 1380612006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 838 | 14.5914 | 121.0134 | U | 3059 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 28.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.06 | 70.17 |  | D - Other node or line within 3 km | 1.38 | 0.88 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2245
3 | 246 | 2246 | 1108208006 | Region XI (Davao Region) | Davao de Oro | Montevista | Camantangan | 7.7299 | 125.9691 | R | 994 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.47 | 2.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.17 | 49.05 | 70.17 |  | D - Other node or line within 3 km | 14.47 | 2.53 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 2246
3 | 247 | 2247 | 1381100074 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 74 | 14.5433 | 120.9957 | U | 473 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.16 | 3.47 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | A - Node within 0.5 km | 0.19 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2247
3 | 248 | 2248 | 1380601143 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 143 | 14.6289 | 120.967 | U | 1444 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.7 | 33.59 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | B - Node 0.5-1 km | 0.72 | 0.63 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2248
3 | 249 | 2249 | 1380601153 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 153 | 14.628 | 120.9774 | U | 2113 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.49 | 31.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | A - Node within 0.5 km | 0.45 | 0.14 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2249
3 | 250 | 2250 | 1380601186 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 186 | 14.6289 | 120.9698 | U | 1729 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.76 | 27.75 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | A - Node within 0.5 km | 0.45 | 0.38 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2250
3 | 251 | 2251 | 1381100157 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 157 | 14.5356 | 121.0064 | U | 2306 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | C - Line within 0.5 km; node over 1 km | 1.31 | 0.3 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2251
3 | 252 | 2252 | PH0002252 | NCR | Metro Manila | Caloocan City | Barangay 86 | 14.618 | 120.967 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.29 | 59.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | A - Node within 0.5 km | 0.46 | 0.39 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2252
3 | 253 | 2253 | 1380605040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 338 | 14.6205 | 120.9838 | U | 1420 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.51 | 20.69 | Tier 2 High GIDA (Score 40.0–49.9) | 70.16 | 49.05 | 70.16 |  | A - Node within 0.5 km | 0.46 | 0.1 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2253
3 | 254 | 2254 | PH0002254 | NCR | Metro Manila | Caloocan City | Barangay 109 | 14.6476 | 120.9856 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.38 | 13.33 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | A - Node within 0.5 km | 0.14 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2254
3 | 255 | 2255 | 1380605045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 343 | 14.6191 | 120.9826 | U | 2276 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.67 | 27.93 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | A - Node within 0.5 km | 0.3 | 0.03 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2255
3 | 256 | 2256 | PH0002256 | NCR | Metro Manila | Caloocan City | Barangay 25 | 14.6026 | 120.9635 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.49 | 3.84 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | B - Node 0.5-1 km | 0.81 | 0.81 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2256
3 | 257 | 2257 | PH0002257 | NCR | Metro Manila | Caloocan City | Barangay 120 | 14.609 | 120.9636 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.3 | 43.3 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | B - Node 0.5-1 km | 0.69 | 0.59 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2257
3 | 258 | 2258 | 1381100132 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 132 | 14.548 | 121.0063 | U | 5233 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | B - Node 0.5-1 km | 0.58 | 0.24 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2258
3 | 259 | 2259 | 0403415022 | Region IV-A (CALABARZON) | Laguna | Magdalena | Tanawan | 14.1807 | 121.4273 | R | 322 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.47 | Tier 2 High GIDA (Score 40.0–49.9) | 70.15 | 49.04 | 70.15 |  | C - Line within 0.5 km; node over 1 km | 2 | 0.11 | Line: PAGSANJAN TO LILIW | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2259
3 | 260 | 2260 | 1380614097 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 904 | 14.5869 | 121.012 | U | 1852 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.57 | 74.67 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | D - Other node or line within 3 km | 1.03 | 0.53 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2260
3 | 261 | 2261 | 1380614088 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 895 | 14.5879 | 121.0186 | U | 573 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.13 | 24.65 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.2 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2261
3 | 262 | 2262 | 1400109005 | Cordillera Administrative Region (CAR) | Abra | Lacub | Pacoc | 17.6668 | 120.9556 | R | 689 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.63 | 30.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | F - Nearest node and line over 5 km | 30.63 | 30.59 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2262
3 | 263 | 2263 | PH0002263 | NCR | Metro Manila | Caloocan City | Barangay 94 | 14.6212 | 120.9661 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.44 | 24.97 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | B - Node 0.5-1 km | 0.51 | 0.59 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2263
3 | 264 | 2264 | PH0002264 | NCR | Metro Manila | Caloocan City | Barangay 116 | 14.6091 | 120.9627 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.04 | 68.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | B - Node 0.5-1 km | 0.79 | 0.68 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2264
3 | 265 | 2265 | 0806014001 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Aguingayan | 12.116 | 125.0397 | R | 390 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 97.54 | 98.38 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.04 | 70.14 |  | F - Nearest node and line over 5 km | 97.54 | 98.38 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2265
3 | 266 | 2266 | 1380612016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 848 | 14.5847 | 120.9986 | U | 1634 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.3 | 16.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.03 | 70.14 |  | A - Node within 0.5 km | 0.45 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2266
3 | 267 | 2267 | 1381100188 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 188 | 14.5319 | 120.9997 | U | 2154 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.44 | 6.25 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.03 | 70.14 |  | B - Node 0.5-1 km | 0.52 | 0.27 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2267
3 | 268 | 2268 | 1380614095 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 902 | 14.5858 | 121.0108 | U | 1368 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.14 | 5.79 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.03 | 70.14 |  | B - Node 0.5-1 km | 0.87 | 0.49 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2268
3 | 269 | 2269 | 0102903035 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Barangay 6 | 17.585 | 120.406 | R | 500 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.34 | 2.2 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.03 | 70.14 |  | C - Line within 0.5 km; node over 1 km | 1.91 | 0.03 | Line: SEGMENT 3 (VIGAN - BATAC) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2269
3 | 270 | 2270 | 1380611041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 826 | 14.5839 | 121.0009 | U | 1813 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.63 | 10.55 | Tier 2 High GIDA (Score 40.0–49.9) | 70.14 | 49.03 | 70.14 |  | A - Node within 0.5 km | 0.21 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2270
3 | 271 | 2271 | 1380605054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 352 | 14.5463 | 121.0076 | U | 1383 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.81 | 55.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.03 | 70.13 |  | B - Node 0.5-1 km | 0.56 | 0.36 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2271
3 | 272 | 2272 | PH0002272 | NCR | Metro Manila | Caloocan City | Barangay 55 | 14.6172 | 120.972 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.14 | 3.76 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.03 | 70.13 |  | C - Line within 0.5 km; node over 1 km | 1 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2272
3 | 273 | 2273 | 1380601158 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 158 | 14.6266 | 120.9762 | U | 1993 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.5 | 3.32 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.03 | 70.13 |  | A - Node within 0.5 km | 0.31 | 0.01 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2273
3 | 274 | 2274 | 1381100105 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 105 | 14.5442 | 121.0021 | U | 583 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.62 | 9.85 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.03 | 70.13 |  | B - Node 0.5-1 km | 0.83 | 0.26 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2274
3 | 275 | 2275 | 1380605023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 321 | 14.611 | 120.9788 | U | 247 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.09 | 31.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.02 | 70.13 |  | B - Node 0.5-1 km | 0.75 | 0.28 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2275
3 | 276 | 2276 | 1380614078 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 885 | 14.5848 | 121.0147 | U | 642 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.51 | 46.63 | Tier 2 High GIDA (Score 40.0–49.9) | 70.13 | 49.02 | 70.13 |  | C - Line within 0.5 km; node over 1 km | 1.29 | 0.19 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2276
3 | 277 | 2277 | 1380300027 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Singkamas | 14.573 | 121.0103 | U | 3551 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.12 | 49.02 | 70.12 |  | C - Line within 0.5 km; node over 1 km | 1.51 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2277
3 | 278 | 2278 | 1380605084 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 381 | 14.63 | 120.9865 | U | 1639 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.82 | 43.96 | Tier 2 High GIDA (Score 40.0–49.9) | 70.12 | 49.02 | 70.12 |  | C - Line within 0.5 km; node over 1 km | 1.46 | 0.34 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2278
3 | 279 | 2279 | 1380614002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 745 | 14.569 | 121.0058 | U | 2076 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.74 | 14.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.12 | 49.02 | 70.12 |  | C - Line within 0.5 km; node over 1 km | 1.29 | 0.03 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2279
3 | 280 | 2280 | 1380614031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 775 | 14.5738 | 121.0063 | U | 12451 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.58 | 9.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.12 | 49.02 | 70.12 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.36 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2280
3 | 281 | 2281 | 1380605033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 331 | 14.6075 | 120.9796 | U | 952 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.46 | 15.05 | Tier 2 High GIDA (Score 40.0–49.9) | 70.12 | 49.02 | 70.12 |  | C - Line within 0.5 km; node over 1 km | 1.06 | 0.29 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2281
3 | 282 | 2282 | PH0002282 | NCR | Metro Manila | Caloocan City | Barangay 9 | 14.6095 | 120.9702 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.08 | 32.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70.11 | 49.01 | 70.11 |  | A - Node within 0.5 km | 0.3 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2282
3 | 283 | 2283 | 1380601066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 66 | 14.6147 | 120.9642 | U | 3046 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.27 | 84.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.11 | 49.01 | 70.11 |  | A - Node within 0.5 km | 0.4 | 0.61 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2283
3 | 284 | 2284 | 1380601008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 8 | 14.6107 | 120.9677 | U | 151 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.66 | 8.92 | Tier 2 High GIDA (Score 40.0–49.9) | 70.11 | 49.01 | 70.11 |  | A - Node within 0.5 km | 0.48 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2284
3 | 285 | 2285 | PH0002285 | III | Pampanga | Angeles City | Sto. Domingo | 15.1379 | 120.5944 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.1 | 49.01 | 70.1 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.13 | Line: 56 CORE (7X8) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2285
3 | 286 | 2286 | 1380605004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 300 | 14.6116 | 120.9932 | U | 1011 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.09 | 23.55 | Tier 2 High GIDA (Score 40.0–49.9) | 70.1 | 49.01 | 70.1 |  | B - Node 0.5-1 km | 0.97 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2286
3 | 287 | 2287 | 1600311008 | Region XIII (Caraga) | Agusan del Sur | Talacogon | Sabang Gibung | 8.3228 | 125.8906 | R | 834 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.72 | 12.06 | Tier 2 High GIDA (Score 40.0–49.9) | 70.1 | 49.01 | 70.1 |  | F - Nearest node and line over 5 km | 12.72 | 12.03 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2287
3 | 288 | 2288 | 1380610027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 712 | 14.5696 | 120.989 | U | 1100 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.33 | 23.7 | Tier 2 High GIDA (Score 40.0–49.9) | 70.1 | 49 | 70.1 |  | B - Node 0.5-1 km | 0.63 | 0.3 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2288
3 | 289 | 2289 | 0402106026 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua I | 14.3201 | 120.9565 | U | 3587 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.31 | 2.07 | Tier 2 High GIDA (Score 40.0–49.9) | 70.09 | 49 | 70.09 |  | D - Other node or line within 3 km | 1.31 | 2 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2289
3 | 290 | 2290 | 0300803013 | Region III (Central Luzon) | Bataan | City of Balanga | Poblacion | 14.6632 | 120.4689 | U | 769 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.88 | 1.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.09 | 49 | 70.09 |  | E - Nearest node or line 3-5 km | 7.85 | 3.44 | Line: Bagac-Pilar AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2290
3 | 291 | 2291 | 1380605058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 356 | 14.5523 | 120.9928 | U | 520 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.39 | 27.87 | Tier 2 High GIDA (Score 40.0–49.9) | 70.09 | 49 | 70.09 |  | A - Node within 0.5 km | 0.16 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2291
3 | 292 | 2292 | PH0002292 | NCR | Metro Manila | Caloocan City | Barangay 87 | 14.6167 | 120.9696 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.62 | 83.5 | Tier 2 High GIDA (Score 40.0–49.9) | 70.09 | 49 | 70.09 |  | B - Node 0.5-1 km | 0.75 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2292
3 | 293 | 2293 | 1380601207 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 206 | 14.6285 | 120.9793 | U | 2507 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.14 | 37.04 | Tier 2 High GIDA (Score 40.0–49.9) | 70.09 | 49 | 70.09 |  | B - Node 0.5-1 km | 0.67 | 0.16 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2293
3 | 294 | 2294 | 1380605060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 358 | 14.5545 | 120.9933 | U | 1060 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.82 | 20.64 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | A - Node within 0.5 km | 0.22 | 0.11 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2294
3 | 295 | 2295 | 1380601201 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 201 | 14.6312 | 120.9781 | U | 1187 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.84 | 21.85 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | B - Node 0.5-1 km | 0.71 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2295
3 | 296 | 2296 | 0504101026 | Region V (Bicol Region) | Masbate | Aroroy | Matongog | 12.5708 | 123.2449 | R | 1360 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18 | 21.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | F - Nearest node and line over 5 km | 18 | 44.2 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2296
3 | 297 | 2297 | 1380612002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 834 | 14.5848 | 120.995 | U | 1786 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.87 | 63.36 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | B - Node 0.5-1 km | 0.84 | 0.34 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2297
3 | 298 | 2298 | PH0002298 | XI | Davao Del Sur | Davao City | Barangay 14-B (Pob.) | 7.0598 | 125.6021 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.89 | 4.46 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | C - Line within 0.5 km; node over 1 km | 1.48 | 0.47 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2298
3 | 299 | 2299 | 1380601035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 35 | 14.6045 | 120.9611 | U | 2334 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.08 | 34.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.08 | 48.99 | 70.08 |  | B - Node 0.5-1 km | 0.96 | 0.95 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2299
3 | 300 | 2300 | PH0002300 | NCR | Metro Manila | Caloocan City | Barangay 48 | 14.6178 | 120.9713 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.81 | 5.86 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.99 | 70.07 |  | B - Node 0.5-1 km | 0.92 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2300
3 | 301 | 2301 | 1380610026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 711 | 14.5708 | 120.9911 | U | 1333 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.05 | 11.58 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.99 | 70.07 |  | A - Node within 0.5 km | 0.37 | 0.04 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2301
3 | 302 | 2302 | PH0002302 | V | Camarines Sur | Naga City | Triangulo | 13.6195 | 123.1959 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.1 | 0.94 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.99 | 70.07 |  | D - Other node or line within 3 km | 1.1 | 0.5 | Line: PAGBILAO - NAGA (UG + Aerial) | Route options survey candidate: compare actual node lateral with approved line tap. | 2302
3 | 303 | 2303 | 1380605034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 332 | 14.6063 | 120.9775 | U | 600 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.99 | 4.15 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.99 | 70.07 |  | B - Node 0.5-1 km | 0.84 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2303
3 | 304 | 2304 | 1380605069 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 366 | 14.5542 | 120.9951 | U | 1229 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.15 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.99 | 70.07 |  | A - Node within 0.5 km | 0.37 | 0.04 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2304
3 | 305 | 2305 | 1380606072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 466 | 14.6123 | 120.9934 | U | 1275 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.05 | 66.89 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.18 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2305
3 | 306 | 2306 | 0603030113 | Region VI (Western Visayas) | Iloilo | Miagao | Tigmalapad | 10.7106 | 122.1821 | R | 528 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.03 | 8.41 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | F - Nearest node and line over 5 km | 22.03 | 8.41 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2306
3 | 307 | 2307 | 1380601241 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 240 | 14.6093 | 120.9773 | U | 58 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.14 | 1.16 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | B - Node 0.5-1 km | 0.87 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2307
3 | 308 | 2308 | PH0002308 | NCR | Metro Manila | Caloocan City | Barangay 88 | 14.6156 | 120.9675 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.91 | 45.49 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | B - Node 0.5-1 km | 0.58 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2308
3 | 309 | 2309 | 1381100065 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 65 | 14.5513 | 120.998 | U | 3015 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.89 | 0.88 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | B - Node 0.5-1 km | 0.71 | 0.01 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2309
3 | 310 | 2310 | 1380606069 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 463 | 14.6112 | 120.9951 | U | 855 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.32 | 27.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | B - Node 0.5-1 km | 0.94 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2310
3 | 311 | 2311 | 1108603003 | Region XI (Davao Region) | Davao Occidental | Malita | Buhangin | 6.4896 | 125.5436 | R | 4998 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.85 | 19.73 | Tier 2 High GIDA (Score 40.0–49.9) | 70.07 | 48.98 | 70.07 |  | F - Nearest node and line over 5 km | 18.85 | 19.7 | Node: MGD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2311
3 | 312 | 2312 | 1380601194 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 194 | 14.6353 | 120.9788 | U | 799 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.35 | 35.57 | Tier 2 High GIDA (Score 40.0–49.9) | 70.06 | 48.98 | 70.06 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.32 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2312
3 | 313 | 2313 | 1380601090 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 90 | 14.6178 | 120.9679 | U | 649 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.23 | 39.67 | Tier 2 High GIDA (Score 40.0–49.9) | 70.06 | 48.98 | 70.06 |  | B - Node 0.5-1 km | 0.56 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2313
3 | 314 | 2314 | 1908709019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Pinantao | 17.254 | 122.228 | R | 5143 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.06 | 48.98 | 70.06 |  | F - Nearest node and line over 5 km | 29.28 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2314
3 | 315 | 2315 | PH0002315 | NCR | Metro Manila | Caloocan City | Barangay 119 | 14.6452 | 120.9839 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.79 | 8.71 | Tier 2 High GIDA (Score 40.0–49.9) | 70.06 | 48.98 | 70.06 |  | A - Node within 0.5 km | 0.4 | 0.04 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2315
3 | 316 | 2316 | 1380606031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 425 | 14.6049 | 121.0003 | U | 2150 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.55 | 18.79 | Tier 2 High GIDA (Score 40.0–49.9) | 70.06 | 48.98 | 70.06 |  | B - Node 0.5-1 km | 0.56 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2316
3 | 317 | 2317 | PH0002317 | I | Pangasinan | Dagupan City | Pogo Chico | 16.0421 | 120.3331 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.24 | 0.62 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | C - Line within 0.5 km; node over 1 km | 2.37 | 0.08 | Line: DAGUPAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2317
3 | 318 | 2318 | 1380601203 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 202-A | 14.633 | 120.9795 | U | 1250 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.15 | 19.65 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | B - Node 0.5-1 km | 0.95 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2318
3 | 319 | 2319 | 0401005074 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 5 | 13.774 | 121.0456 | R | 584 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 4.27 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | C - Line within 0.5 km; node over 1 km | 1.63 | 0.04 | Line: BAUAN - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2319
3 | 320 | 2320 | 1908707003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bugasan Norte | 17.254 | 122.228 | R | 10312 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | F - Nearest node and line over 5 km | 29.28 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2320
3 | 321 | 2321 | PH0002321 | NCR | Metro Manila | Caloocan City | Barangay 10 | 14.6541 | 120.9698 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.71 | 42.34 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | B - Node 0.5-1 km | 0.64 | 0.75 | Node: CCS004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2321
3 | 322 | 2322 | 1380601057 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 57 | 14.6094 | 120.9698 | U | 909 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.21 | 26.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.05 | 48.97 | 70.05 |  | A - Node within 0.5 km | 0.29 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2322
3 | 323 | 2323 | 1380614093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 900 | 14.587 | 121.0111 | U | 8842 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.26 | 82.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.97 | 70.04 |  | B - Node 0.5-1 km | 0.94 | 0.59 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2323
3 | 324 | 2324 | PH0002324 | VII | Cebu | Cebu City | Day-as | 10.3415 | 123.889 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.1 | 4 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.97 | 70.04 |  | D - Other node or line within 3 km | 1.5 | 3.66 | Node: CCY003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2324
3 | 325 | 2325 | 1381100064 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 64 | 14.5521 | 120.9994 | U | 1627 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.11 | 2.79 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.97 | 70.04 |  | B - Node 0.5-1 km | 0.84 | 0.18 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2325
3 | 326 | 2326 | 1380614043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 787 | 14.5818 | 121.0128 | U | 3732 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.26 | 15.74 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.96 | 70.04 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2326
3 | 327 | 2327 | 1380611029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 815 | 14.5794 | 121.0044 | U | 1416 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.26 | 15.26 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.96 | 70.04 |  | B - Node 0.5-1 km | 0.58 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2327
3 | 328 | 2328 | PH0002328 | CAR | Benguet | Baguio City | Dizon Subdivision | 16.3701 | 120.5768 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.1 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 70.04 | 48.96 | 70.04 |  | D - Other node or line within 3 km | 4.15 | 2.08 | Line: TUBA | Route options survey candidate: compare actual node lateral with approved line tap. | 2328
3 | 329 | 2329 | PH0002329 | IV-A | Laguna | San Pablo City | Barangay III-F (Pob.) | 17.4674 | 121.8412 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.06 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 70.03 | 48.96 | 70.03 |  | E - Nearest node or line 3-5 km | 8.33 | 4.33 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2329
3 | 330 | 2330 | 1380606096 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 490 | 14.6223 | 120.9953 | U | 485 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.79 | 12.45 | Tier 2 High GIDA (Score 40.0–49.9) | 70.03 | 48.96 | 70.03 |  | D - Other node or line within 3 km | 1.48 | 0.72 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2330
3 | 331 | 2331 | 1380611044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 829 | 14.5815 | 120.9962 | U | 4354 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.29 | 17.17 | Tier 2 High GIDA (Score 40.0–49.9) | 70.03 | 48.96 | 70.03 |  | B - Node 0.5-1 km | 0.78 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2331
3 | 332 | 2332 | 1380606097 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 491 | 14.6211 | 120.9932 | U | 838 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.84 | 48.18 | Tier 2 High GIDA (Score 40.0–49.9) | 70.03 | 48.96 | 70.03 |  | D - Other node or line within 3 km | 1.22 | 0.65 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2332
3 | 333 | 2333 | 1380605059 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 357 | 14.5557 | 120.9954 | U | 758 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.93 | 12.23 | Tier 2 High GIDA (Score 40.0–49.9) | 70.03 | 48.96 | 70.03 |  | A - Node within 0.5 km | 0.48 | 0.14 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2333
3 | 334 | 2334 | 1381300074 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pag-ibig Sa Nayon | 14.6466 | 120.9965 | U | 6166 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 1.02 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | D - Other node or line within 3 km | 1.08 | 0.97 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2334
3 | 335 | 2335 | 1381100003 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 3 | 14.5585 | 120.9919 | U | 847 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.21 | 6.72 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | B - Node 0.5-1 km | 0.58 | 0.43 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2335
3 | 336 | 2336 | 1381100137 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 137 | 14.5486 | 121.0057 | U | 3079 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | B - Node 0.5-1 km | 0.62 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2336
3 | 337 | 2337 | 1381100161 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 161 | 14.5355 | 121.0079 | U | 2915 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.44 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | C - Line within 0.5 km; node over 1 km | 1.44 | 0.47 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2337
3 | 338 | 2338 | 1380601054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 54 | 14.6153 | 120.9726 | U | 1698 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.14 | 22.54 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | B - Node 0.5-1 km | 1 | 0.25 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2338
3 | 339 | 2339 | PH0002339 | NCR | Metro Manila | Caloocan City | Barangay 45 | 14.6168 | 120.9729 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.12 | 58.22 | Tier 2 High GIDA (Score 40.0–49.9) | 70.02 | 48.95 | 70.02 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.08 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2339
3 | 340 | 2340 | 0301412008 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Hulo | 14.7425 | 120.9708 | U | 2804 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.57 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.95 | 70.01 |  | B - Node 0.5-1 km | 0.52 | 1.16 | Node: MEB003 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2340
3 | 341 | 2341 | 1003515021 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Pantar | 7.787 | 123.9103 | R | 882 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.53 | 20 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.94 | 70.01 |  | F - Nearest node and line over 5 km | 30.98 | 19.74 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2341
3 | 342 | 2342 | 0402106048 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol II | 14.2806 | 120.9647 | U | 6343 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.94 | 70.01 |  | C - Line within 0.5 km; node over 1 km | 2.26 | 0.21 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2342
3 | 343 | 2343 | 1381100173 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 173 | 14.5326 | 121.0127 | U | 1866 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 0.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.94 | 70.01 |  | D - Other node or line within 3 km | 1.22 | 0.65 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2343
3 | 344 | 2344 | PH0002344 | NCR | Metro Manila | Caloocan City | Barangay 126 | 14.6111 | 120.9603 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.54 | 29.1 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.94 | 70.01 |  | B - Node 0.5-1 km | 0.81 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2344
3 | 345 | 2345 | 1380606033 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 427 | 14.6072 | 121.0007 | U | 510 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.62 | 51.52 | Tier 2 High GIDA (Score 40.0–49.9) | 70.01 | 48.94 | 70.01 |  | B - Node 0.5-1 km | 0.53 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2345
3 | 346 | 2346 | 1380606103 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 497 | 14.6232 | 120.9945 | U | 1534 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.55 | 45.99 | Tier 2 High GIDA (Score 40.0–49.9) | 70 | 48.94 | 70 |  | D - Other node or line within 3 km | 1.46 | 0.59 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2346
3 | 347 | 2347 | 0806014006 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Gusa | 12.1077 | 125.0526 | R | 393 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.68 | 98.08 | Tier 2 High GIDA (Score 40.0–49.9) | 70 | 48.94 | 70 |  | F - Nearest node and line over 5 km | 96.68 | 98.08 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2347
3 | 348 | 2348 | 1908707006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Langco | 17.2533 | 122.2277 | R | 5853 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 70 | 48.94 | 70 |  | F - Nearest node and line over 5 km | 29.21 | 34.12 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2348
3 | 349 | 2349 | 1380605008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 304 | 14.6115 | 120.9941 | U | 307 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.57 | 8.55 | Tier 2 High GIDA (Score 40.0–49.9) | 70 | 48.93 | 70 |  | B - Node 0.5-1 km | 0.98 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2349
3 | 350 | 2350 | 1380601261 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 260 | 14.6084 | 120.976 | U | 1695 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.53 | 8.53 | Tier 2 High GIDA (Score 40.0–49.9) | 70 | 48.93 | 70 |  | B - Node 0.5-1 km | 0.71 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2350
3 | 351 | 2351 | PH0002351 | CAR | Benguet | Baguio City | Alfonso Tabora | 16.4221 | 120.6016 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.99 | 48.93 | 69.99 |  | B - Node 0.5-1 km | 0.93 | 1.1 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2351
3 | 352 | 2352 | 1908709023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Samberen | 17.2532 | 122.2273 | R | 2286 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.38 | 35.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.99 | 48.93 | 69.99 |  | F - Nearest node and line over 5 km | 29.17 | 34.07 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2352
3 | 353 | 2353 | PH0002353 | NCR | Metro Manila | Caloocan City | Barangay 124 | 14.6088 | 120.9599 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.43 | 3.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.99 | 48.93 | 69.99 |  | D - Other node or line within 3 km | 1.06 | 0.99 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2353
3 | 354 | 2354 | 1380605052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 350 | 14.5472 | 121.0097 | U | 6982 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.91 | 8.48 | Tier 2 High GIDA (Score 40.0–49.9) | 69.99 | 48.93 | 69.99 |  | A - Node within 0.5 km | 0.34 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2354
3 | 355 | 2355 | 1380604004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 271 | 14.621 | 120.9843 | U | 652 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.85 | 78.84 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.93 | 69.98 |  | B - Node 0.5-1 km | 0.52 | 0.15 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2355
3 | 356 | 2356 | PH0002356 | NCR | Metro Manila | Caloocan City | Barangay 7 | 14.6072 | 120.9698 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.47 | 65.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | A - Node within 0.5 km | 0.05 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2356
3 | 357 | 2357 | 0504106011 | Region V (Bicol Region) | Masbate | Cawayan | Itombato | 11.9713 | 123.7726 | R | 1160 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.7 | 38.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | F - Nearest node and line over 5 km | 18.7 | 39.72 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2357
3 | 358 | 2358 | 0402106023 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Luzviminda I | 14.3279 | 120.9656 | R | 3753 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.45 | 3.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | D - Other node or line within 3 km | 1.71 | 3.11 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2358
3 | 359 | 2359 | 1400113009 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Poblacion | 17.6117 | 120.9263 | R | 272 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26 | 25.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | F - Nearest node and line over 5 km | 28.09 | 28.03 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2359
3 | 360 | 2360 | 1102406007 | Region XI (Davao Region) | Davao del Sur | Kiblawan | Bonifacio | 6.4627 | 125.2603 | R | 1495 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.54 | 0.66 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | F - Nearest node and line over 5 km | 6.54 | 5.45 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2360
3 | 361 | 2361 | 1381100099 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 99 | 14.5399 | 121.0025 | U | 1143 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.98 | 48.92 | 69.98 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.21 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2361
3 | 362 | 2362 | 1381100120 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 120 | 14.5469 | 121.0059 | U | 341 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.61 | 5.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.97 | 48.92 | 69.97 |  | B - Node 0.5-1 km | 0.68 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2362
3 | 363 | 2363 | 0701245005 | Region VII (Central Visayas) | Bohol | Tubigon | Bilangbilangan | 9.9877 | 123.8824 | R | 477 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.29 | 9.17 | Tier 2 High GIDA (Score 40.0–49.9) | 69.97 | 48.92 | 69.97 |  | F - Nearest node and line over 5 km | 22.29 | 9.16 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2363
3 | 364 | 2364 | 0600608042 | Region VI (Western Visayas) | Antique | Hamtic | Pili 1, 2, 3 | 10.6751 | 122.0362 | R | 352 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.46 | 6.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.97 | 48.91 | 69.97 |  | F - Nearest node and line over 5 km | 14.46 | 6.15 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2364
3 | 365 | 2365 | 0600608015 | Region VI (Western Visayas) | Antique | Hamtic | Cantulan | 10.6752 | 122.0505 | R | 206 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.65 | 7.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.96 | 48.91 | 69.96 |  | F - Nearest node and line over 5 km | 15.65 | 7.27 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2365
3 | 366 | 2366 | 0600608051 | Region VI (Western Visayas) | Antique | Hamtic | Suloc | 10.7091 | 121.977 | R | 125 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.88 | 2.21 | Tier 2 High GIDA (Score 40.0–49.9) | 69.96 | 48.91 | 69.96 |  | C - Line within 0.5 km; node over 1 km | 7.29 | 0.21 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2366
3 | 367 | 2367 | PH0002367 | NCR | Metro Manila | Caloocan City | Barangay 154 | 14.6268 | 120.9753 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.54 | 4.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.96 | 48.91 | 69.96 |  | A - Node within 0.5 km | 0.21 | 0.01 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2367
3 | 368 | 2368 | 1381100007 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 7 | 14.5591 | 120.9896 | U | 2752 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.26 | 13.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.96 | 48.91 | 69.96 |  | B - Node 0.5-1 km | 0.68 | 0.65 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2368
3 | 369 | 2369 | PH0002369 | NCR | Metro Manila | Caloocan City | Barangay 118 | 14.6114 | 120.9632 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.4 | 78.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.96 | 48.91 | 69.96 |  | B - Node 0.5-1 km | 0.74 | 0.65 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2369
3 | 370 | 2370 | 0402118061 | Region IV-A (CALABARZON) | Cavite | Silang | Narra III | 14.1855 | 120.9843 | R | 3393 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.08 | 1.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.95 | 48.9 | 69.95 |  | D - Other node or line within 3 km | 2.5 | 2.33 | Line: TGY001 TO CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2370
3 | 371 | 2371 | PH0002371 | NCR | Metro Manila | Caloocan City | Barangay 13 | 14.603 | 120.9608 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.96 | 3.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.95 | 48.9 | 69.95 |  | D - Other node or line within 3 km | 1.02 | 1.05 | Node: MNL068 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 2371
3 | 372 | 2372 | 1381100179 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 179 | 14.5356 | 120.9983 | U | 6882 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 69.95 | 48.9 | 69.95 |  | B - Node 0.5-1 km | 0.86 | 0.09 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2372
3 | 373 | 2373 | PH0002373 | NCR | Metro Manila | Caloocan City | Barangay 26 | 14.6014 | 120.9614 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.34 | 41.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.94 | 48.9 | 69.94 |  | B - Node 0.5-1 km | 0.83 | 1.07 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2373
3 | 374 | 2374 | PH0002374 | NCR | Metro Manila | Caloocan City | Barangay 15 | 14.6504 | 120.9744 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.99 | 69.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.94 | 48.9 | 69.94 |  | A - Node within 0.5 km | 0.21 | 0.36 | Node: CCS004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2374
3 | 375 | 2375 | 1102505004 | Region XI (Davao Region) | Davao Oriental | Cateel | Aragon | 7.7655 | 126.3669 | R | 2252 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.92 | 33.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.94 | 48.9 | 69.94 |  | F - Nearest node and line over 5 km | 34.92 | 33.88 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2375
3 | 376 | 2376 | 1380606168 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 562 | 14.6065 | 121.0052 | U | 2661 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.83 | 1.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.93 | 48.89 | 69.93 |  | A - Node within 0.5 km | 0.5 | 0.35 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2376
3 | 377 | 2377 | 1380606191 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 585 | 14.6012 | 121.0121 | U | 1123 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.34 | 19.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.92 | 48.88 | 69.92 |  | B - Node 0.5-1 km | 0.82 | 0.14 | Line: UG 288C via V-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2377
3 | 378 | 2378 | PH0002378 | NCR | Metro Manila | Caloocan City | Barangay 91 | 14.6195 | 120.9682 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.81 | 6.09 | Tier 2 High GIDA (Score 40.0–49.9) | 69.92 | 48.88 | 69.92 |  | B - Node 0.5-1 km | 0.61 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2378
3 | 379 | 2379 | 1381100082 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 82 | 14.5436 | 120.9951 | U | 570 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.92 | 48.88 | 69.92 |  | A - Node within 0.5 km | 0.12 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2379
3 | 380 | 2380 | 0804814021 | Region VIII (Eastern Visayas) | Northern Samar | Palapag | Nipa | 12.573 | 125.1502 | R | 1295 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 112.04 | 110.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.92 | 48.88 | 69.92 |  | F - Nearest node and line over 5 km | 112.04 | 112.58 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2380
3 | 381 | 2381 | 1380605015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 313 | 14.6051 | 120.9798 | U | 2934 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.55 | 24.84 | Tier 2 High GIDA (Score 40.0–49.9) | 69.91 | 48.88 | 69.91 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2381
3 | 382 | 2382 | PH0002382 | NCR | Metro Manila | Caloocan City | Barangay 51 | 14.6189 | 120.9743 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.75 | 23.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.91 | 48.87 | 69.91 |  | B - Node 0.5-1 km | 0.89 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2382
3 | 383 | 2383 | 1381100020 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 20 | 14.5601 | 120.9918 | U | 641 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.61 | 6.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.91 | 48.87 | 69.91 |  | B - Node 0.5-1 km | 0.76 | 0.4 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2383
3 | 384 | 2384 | PH0002384 | XI | Davao Del Sur | Davao City | Barangay 22-C (Pob.) | 7.0598 | 125.6021 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.28 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.91 | 48.87 | 69.91 |  | C - Line within 0.5 km; node over 1 km | 1.48 | 0.47 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2384
3 | 385 | 2385 | 1380605085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 382 | 14.6288 | 120.9844 | U | 923 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.74 | 35.96 | Tier 2 High GIDA (Score 40.0–49.9) | 69.91 | 48.87 | 69.91 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2385
3 | 386 | 2386 | 1380614040 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 784 | 14.5808 | 121.0144 | U | 3489 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.05 | 28.63 | Tier 2 High GIDA (Score 40.0–49.9) | 69.9 | 48.87 | 69.9 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.16 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2386
3 | 387 | 2387 | 1380612028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 860 | 14.5863 | 121.0059 | U | 3312 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.04 | 29.57 | Tier 2 High GIDA (Score 40.0–49.9) | 69.9 | 48.87 | 69.9 |  | A - Node within 0.5 km | 0.39 | 0.38 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2387
3 | 388 | 2388 | 0603027031 | Region VI (Western Visayas) | Iloilo | Lemery | Yawyawan | 11.2754 | 122.8745 | R | 625 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.08 | 7.96 | Tier 2 High GIDA (Score 40.0–49.9) | 69.89 | 48.86 | 69.89 |  | F - Nearest node and line over 5 km | 8.08 | 7.96 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2388
3 | 389 | 2389 | 1380601253 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 252 | 14.6135 | 120.9754 | U | 938 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.67 | 18.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.89 | 48.86 | 69.89 |  | B - Node 0.5-1 km | 0.87 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2389
3 | 390 | 2390 | 1380601175 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 175 | 14.6301 | 120.975 | U | 1018 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.21 | 70.65 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.86 | 69.88 |  | A - Node within 0.5 km | 0.41 | 0.39 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2390
3 | 391 | 2391 | 1380605017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 315 | 14.608 | 120.9853 | U | 1840 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29 | 26.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.85 | 69.88 |  | B - Node 0.5-1 km | 0.84 | 0.06 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2391
3 | 392 | 2392 | 1380601159 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 159 | 14.6301 | 120.9741 | U | 1605 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.55 | 7.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.85 | 69.88 |  | A - Node within 0.5 km | 0.37 | 0.39 | Node: MNL036 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2392
3 | 393 | 2393 | 1381100018 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 18 | 14.5588 | 120.991 | U | 1048 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.85 | 69.88 |  | B - Node 0.5-1 km | 0.62 | 0.52 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2393
3 | 394 | 2394 | 0402106033 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis I | 14.3336 | 120.9772 | R | 4172 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.93 | 2.37 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.85 | 69.88 |  | D - Other node or line within 3 km | 1.61 | 4.28 | Node: DMC005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2394
3 | 395 | 2395 | 1380605065 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 363 | 14.5532 | 120.9921 | U | 576 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.13 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 69.88 | 48.85 | 69.88 |  | A - Node within 0.5 km | 0.04 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2395
3 | 396 | 2396 | 1380614034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 778 | 14.5748 | 121.0093 | U | 1904 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.56 | 5.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.87 | 48.85 | 69.87 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.2 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2396
3 | 397 | 2397 | 1608507004 | Region XIII (Caraga) | Dinagat Islands | Tubajon | Navarro | 10.2899 | 125.5899 | R | 436 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.77 | 56.77 | Tier 2 High GIDA (Score 40.0–49.9) | 69.86 | 48.84 | 69.86 |  | F - Nearest node and line over 5 km | 56.77 | 56.65 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2397
3 | 398 | 2398 | 1380614098 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 905 | 14.5857 | 121.0099 | U | 7609 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.76 | 60.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.86 | 48.84 | 69.86 |  | B - Node 0.5-1 km | 0.78 | 0.52 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2398
3 | 399 | 2399 | 1380612030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 862 | 14.5882 | 121.0053 | U | 2492 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.94 | 6.23 | Tier 2 High GIDA (Score 40.0–49.9) | 69.85 | 48.84 | 69.85 |  | B - Node 0.5-1 km | 0.5 | 0.34 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2399
3 | 400 | 2400 | PH0002400 | VIII | Northern Samar | Victoria N Samar | Buenasuerte | 12.4467 | 124.3796 | R | 2223 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.46 | 77.78 | Tier 2 High GIDA (Score 40.0–49.9) | 69.85 | 48.83 | 69.85 |  | F - Nearest node and line over 5 km | 35.89 | 35.86 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2400
3 | 401 | 2401 | PH0002401 | CAR | Benguet | Baguio City | New Lucban | 16.4225 | 120.5948 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.36 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.85 | 48.83 | 69.85 |  | A - Node within 0.5 km | 0.36 | 0.88 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2401
3 | 402 | 2402 | 1381100170 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 170 | 14.5347 | 121.0135 | U | 1616 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 1.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.84 | 48.83 | 69.84 |  | C - Line within 0.5 km; node over 1 km | 1.44 | 0.46 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2402
3 | 403 | 2403 | 0200904002 | Region II (Cagayan Valley) | Batanes | Mahatao | Kaumbakan | 20.4159 | 121.9476 | R | 449 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 218.92 | 212.77 | Tier 2 High GIDA (Score 40.0–49.9) | 69.84 | 48.82 | 69.84 |  | F - Nearest node and line over 5 km | 216.98 | 213.88 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2403
3 | 404 | 2404 | 1381100109 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 109 | 14.5448 | 121.0033 | U | 1154 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.33 | 2.1 | Tier 2 High GIDA (Score 40.0–49.9) | 69.84 | 48.82 | 69.84 |  | B - Node 0.5-1 km | 0.95 | 0.38 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2404
3 | 405 | 2405 | 1380601053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 53 | 14.6165 | 120.9701 | U | 3005 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.68 | 25.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | B - Node 0.5-1 km | 0.81 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2405
3 | 406 | 2406 | 1380601200 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 200 | 14.6308 | 120.979 | U | 1717 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.43 | 39.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | B - Node 0.5-1 km | 0.75 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2406
3 | 407 | 2407 | PH0002407 | XI | Davao Del Sur | Davao City | Barangay 2-A (Pob.) | 7.0631 | 125.6076 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | B - Node 0.5-1 km | 0.78 | 0.7 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2407
3 | 408 | 2408 | 1380607001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 637 | 14.5987 | 121.0009 | U | 1334 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.62 | 9.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | B - Node 0.5-1 km | 0.54 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2408
3 | 409 | 2409 | 1380500019 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | New Zañiga | 14.5686 | 121.0344 | U | 9240 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.77 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | B - Node 0.5-1 km | 0.66 | 0.01 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2409
3 | 410 | 2410 | 0803717030 | Region VIII (Eastern Visayas) | Leyte | Dagami | Lobe-lobe | 11.0466 | 124.9057 | R | 145 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.67 | 13.5 | Tier 2 High GIDA (Score 40.0–49.9) | 69.83 | 48.82 | 69.83 |  | F - Nearest node and line over 5 km | 14.07 | 14.92 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2410
3 | 411 | 2411 | 1380606027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 421 | 14.6051 | 121.004 | U | 1519 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.1 | 17.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.82 | 48.81 | 69.82 |  | A - Node within 0.5 km | 0.34 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2411
3 | 412 | 2412 | PH0002412 | NCR | Metro Manila | Caloocan City | Barangay 110 | 14.6193 | 120.96 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.83 | 22.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.82 | 48.81 | 69.82 |  | A - Node within 0.5 km | 0.33 | 1.16 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2412
3 | 413 | 2413 | 1380606187 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 581 | 14.6033 | 121.0106 | U | 2536 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.78 | 20.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.82 | 48.81 | 69.82 |  | B - Node 0.5-1 km | 0.67 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2413
3 | 414 | 2414 | 1108202036 | Region XI (Davao Region) | Davao de Oro | Laak | Panamoren | 7.7789 | 125.7454 | R | 1073 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.62 | 24.79 | Tier 2 High GIDA (Score 40.0–49.9) | 69.82 | 48.81 | 69.82 |  | F - Nearest node and line over 5 km | 34.66 | 27.7 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2414
3 | 415 | 2415 | PH0002415 | CAR | Benguet | Baguio City | Harrison-Claudio Carantes | 16.4259 | 120.6058 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 0.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.8 | 48.79 | 69.8 |  | D - Other node or line within 3 km | 1.29 | 1.4 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 2415
3 | 416 | 2416 | 1381100123 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 123 | 14.5482 | 121.005 | U | 1321 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.12 | 6.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.8 | 48.79 | 69.8 |  | B - Node 0.5-1 km | 0.71 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2416
3 | 417 | 2417 | PH0002417 | VI | Iloilo | Iloilo City | San Pedro | 10.6987 | 122.548 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.26 | 1.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.79 | 48.79 | 69.79 |  | D - Other node or line within 3 km | 1.06 | 2.24 | Node: ICI002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2417
3 | 418 | 2418 | PH0002418 | NCR | Metro Manila | Caloocan City | Barangay 90 | 14.6178 | 120.9679 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.6 | 31.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.79 | 48.79 | 69.79 |  | B - Node 0.5-1 km | 0.56 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2418
3 | 419 | 2419 | 1381100135 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 135 | 14.5465 | 121.0051 | U | 2847 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 1.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.79 | 48.79 | 69.79 |  | B - Node 0.5-1 km | 0.77 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2419
3 | 420 | 2420 | 1606718002 | Region XIII (Caraga) | Surigao del Norte | San Benito | Maribojoc | 9.9329 | 125.9627 | R | 1241 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.73 | 45.59 | Tier 2 High GIDA (Score 40.0–49.9) | 69.78 | 48.79 | 69.78 |  | F - Nearest node and line over 5 km | 53.73 | 45.53 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2420
3 | 421 | 2421 | PH0002421 | NCR | Metro Manila | Caloocan City | Barangay 71 | 14.6133 | 120.9677 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.83 | 66.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.78 | 48.78 | 69.78 |  | B - Node 0.5-1 km | 0.74 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2421
3 | 422 | 2422 | PH0002422 | VI | Capiz | Roxas City | Inzo Arnaldo Village | 11.586 | 122.7541 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 69.78 | 48.78 | 69.78 |  | B - Node 0.5-1 km | 0.71 | 0 | Line: ROXAS - SARA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2422
3 | 423 | 2423 | PH0002423 | VI | Iloilo | Iloilo City | San Antonio | 10.7134 | 122.5853 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.45 | 4.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.77 | 48.78 | 69.77 |  | D - Other node or line within 3 km | 1.9 | 1.88 | Line: 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 2423
3 | 424 | 2424 | 0401005063 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 17 | 13.831 | 121.083 | U | 119 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.7 | 4.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.77 | 48.78 | 69.77 |  | C - Line within 0.5 km; node over 1 km | 5.12 | 0.16 | Line: UG_LPB001 TO BCY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2424
3 | 425 | 2425 | 1908713001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Bantek | 17.254 | 122.2281 | R | 3237 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.76 | 48.77 | 69.76 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2425
3 | 426 | 2426 | 1380606213 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 606 | 14.5959 | 121.016 | U | 548 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.5 | 90.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.76 | 48.77 | 69.76 |  | D - Other node or line within 3 km | 1.4 | 0.76 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2426
3 | 427 | 2427 | 1380614096 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 903 | 14.5881 | 121.0094 | U | 3803 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.98 | 6.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.76 | 48.77 | 69.76 |  | B - Node 0.5-1 km | 0.82 | 0.78 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2427
3 | 428 | 2428 | 0304902007 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Digmala | 15.6252 | 121.1543 | R | 1683 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.78 | Tier 2 High GIDA (Score 40.0–49.9) | 69.75 | 48.76 | 69.75 |  | B - Node 0.5-1 km | 0.84 | 0.73 | Line: Proposed AE F1-6 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2428
3 | 429 | 2429 | 1381100130 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 130 | 14.5466 | 121.0054 | U | 4157 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 1.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.75 | 48.76 | 69.75 |  | B - Node 0.5-1 km | 0.74 | 0.27 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2429
3 | 430 | 2430 | 1381100062 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 62 | 14.55 | 120.9988 | U | 1263 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.42 | 10.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.75 | 48.76 | 69.75 |  | B - Node 0.5-1 km | 0.77 | 0.06 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2430
3 | 431 | 2431 | PH0002431 | NCR | Metro Manila | Caloocan City | Barangay 6 | 14.6084 | 120.9672 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.85 | 18.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.75 | 48.76 | 69.75 |  | A - Node within 0.5 km | 0.32 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2431
3 | 432 | 2432 | 0502009021 | Region V (Bicol Region) | Catanduanes | San Miguel | San Marcos | 13.7163 | 124.2516 | R | 240 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.42 | 67.82 | Tier 2 High GIDA (Score 40.0–49.9) | 69.74 | 48.76 | 69.74 |  | F - Nearest node and line over 5 km | 42.42 | 67.82 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2432
3 | 433 | 2433 | PH0002433 | NCR | Metro Manila | Caloocan City | Barangay 58 | 14.6082 | 120.9724 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38 | 17.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.74 | 48.76 | 69.74 |  | A - Node within 0.5 km | 0.33 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2433
3 | 434 | 2434 | 0806014005 | Region VIII (Eastern Visayas) | Samar | San Jose De Buan | Cataydongan | 12.0067 | 125.0381 | R | 323 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.39 | 87.22 | Tier 2 High GIDA (Score 40.0–49.9) | 69.74 | 48.75 | 69.74 |  | F - Nearest node and line over 5 km | 85.39 | 87.22 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2434
3 | 435 | 2435 | 1380606146 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 540 | 14.6155 | 121.0023 | U | 2010 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.41 | 15.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.73 | 48.75 | 69.73 |  | B - Node 0.5-1 km | 0.53 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2435
3 | 436 | 2436 | PH0002436 | V | Camarines Sur | Naga City | Tabuco | 13.6175 | 123.1838 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.73 | 48.75 | 69.73 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.27 | Line: PAGBILAO - NAGA (UG + Aerial) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2436
3 | 437 | 2437 | 0504121008 | Region V (Bicol Region) | Masbate | Uson | Campana | 12.0759 | 123.8042 | R | 932 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.68 | 35.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.73 | 48.75 | 69.73 |  | F - Nearest node and line over 5 km | 18.68 | 35.66 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2437
3 | 438 | 2438 | PH0002438 | NCR | Metro Manila | Caloocan City | Barangay 113 | 14.6203 | 120.963 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.35 | 60.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.72 | 48.74 | 69.72 |  | A - Node within 0.5 km | 0.26 | 0.87 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2438
3 | 439 | 2439 | PH0002439 | NCR | Metro Manila | Caloocan City | Barangay 54 | 14.6153 | 120.9726 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.74 | 7.66 | Tier 2 High GIDA (Score 40.0–49.9) | 69.72 | 48.74 | 69.72 |  | B - Node 0.5-1 km | 1 | 0.25 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2439
3 | 440 | 2440 | 1380601183 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 183 | 14.6325 | 120.9714 | U | 8680 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.17 | 16.11 | Tier 2 High GIDA (Score 40.0–49.9) | 69.72 | 48.74 | 69.72 |  | B - Node 0.5-1 km | 0.66 | 0.66 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2440
3 | 441 | 2441 | PH0002441 | CAR | Benguet | Baguio City | Quirino-Magsaysay, Upper | 16.4125 | 120.5895 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 1.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.72 | 48.74 | 69.72 |  | A - Node within 0.5 km | 0.3 | 0.12 | Line: BAGUIO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2441
3 | 442 | 2442 | 0802613014 | Region VIII (Eastern Visayas) | Eastern Samar | Llorente | Mina-anod | 11.4332 | 125.5499 | R | 421 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.45 | 63.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.74 | 69.71 |  | F - Nearest node and line over 5 km | 63.45 | 63.84 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2442
3 | 443 | 2443 | 0405622089 | Region IV-A (CALABARZON) | Quezon | Lopez | Villa Aurora | 13.8242 | 122.3685 | R | 820 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.41 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.73 | 69.71 |  | C - Line within 0.5 km; node over 1 km | 12.41 | 0.1 | Line: AE LZQ001 TO SNQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2443
3 | 444 | 2444 | 1380601199 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 199 | 14.6348 | 120.9789 | U | 3576 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.72 | 25.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.73 | 69.71 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.29 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2444
3 | 445 | 2445 | PH0002445 | NCR | Metro Manila | Caloocan City | Barangay 117 | 14.6126 | 120.9606 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.95 | 28.02 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.73 | 69.71 |  | B - Node 0.5-1 km | 0.64 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2445
3 | 446 | 2446 | PH0002446 | NCR | Metro Manila | Caloocan City | Barangay 132 | 14.6309 | 120.967 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.76 | 61.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.73 | 69.71 |  | B - Node 0.5-1 km | 0.82 | 0.75 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2446
3 | 447 | 2447 | 0504113014 | Region V (Bicol Region) | Masbate | Mobo | Mapuyo | 12.2286 | 123.6424 | R | 570 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.16 | 11.77 | Tier 2 High GIDA (Score 40.0–49.9) | 69.71 | 48.73 | 69.71 |  | F - Nearest node and line over 5 km | 12.16 | 11.76 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2447
3 | 448 | 2448 | 0401005077 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 8 | 13.6814 | 121.1381 | R | 491 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.9 | 7.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.7 | 48.73 | 69.7 |  | F - Nearest node and line over 5 km | 5.28 | 11.65 | Node: BCY007-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2448
3 | 449 | 2449 | 0806004019 | Region VIII (Eastern Visayas) | Samar | Calbiga | Mahangcao | 11.6118 | 125.0798 | R | 356 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.24 | 45.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.69 | 48.72 | 69.69 |  | F - Nearest node and line over 5 km | 42.24 | 45.06 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2449
3 | 450 | 2450 | 1381100187 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 187 | 14.5332 | 121.0006 | U | 4761 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.7 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.69 | 48.72 | 69.69 |  | B - Node 0.5-1 km | 0.7 | 0.26 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2450
3 | 451 | 2451 | 1381100110 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 110 | 14.5441 | 121.0019 | U | 1879 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 69.69 | 48.72 | 69.69 |  | B - Node 0.5-1 km | 0.8 | 0.24 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2451
3 | 452 | 2452 | 0806004039 | Region VIII (Eastern Visayas) | Samar | Calbiga | Sinalangtan | 11.5728 | 125.0783 | R | 154 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.96 | 40.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.72 | 69.68 |  | F - Nearest node and line over 5 km | 37.96 | 40.75 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2452
3 | 453 | 2453 | 1381100066 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 66 | 14.5437 | 120.9965 | U | 2877 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.33 | 2.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.71 | 69.68 |  | A - Node within 0.5 km | 0.24 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2453
3 | 454 | 2454 | 0701245023 | Region VII (Central Visayas) | Bohol | Tubigon | Pangapasan | 9.998 | 123.9411 | R | 574 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.56 | 5.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.71 | 69.68 |  | F - Nearest node and line over 5 km | 26.56 | 5.71 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2454
3 | 455 | 2455 | 1380610022 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 707 | 14.571 | 120.9902 | U | 1084 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.26 | 40.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.71 | 69.68 |  | A - Node within 0.5 km | 0.45 | 0.14 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2455
3 | 456 | 2456 | PH0002456 | NCR | Metro Manila | Caloocan City | Barangay 72 | 14.6121 | 120.9656 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.09 | 26.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.71 | 69.68 |  | B - Node 0.5-1 km | 0.72 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2456
3 | 457 | 2457 | PH0002457 | VIII | Leyte | Tacloban City | Barangay 43-B | 11.2869 | 124.9594 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.26 | 3.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.68 | 48.71 | 69.68 |  | F - Nearest node and line over 5 km | 7.05 | 9.9 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2457
3 | 458 | 2458 | 1380601195 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 195 | 14.6362 | 120.9809 | U | 1444 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.99 | 21.55 | Tier 2 High GIDA (Score 40.0–49.9) | 69.67 | 48.71 | 69.67 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.15 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2458
3 | 459 | 2459 | 1380601154 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 154 | 14.6268 | 120.9753 | U | 977 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.77 | 14.24 | Tier 2 High GIDA (Score 40.0–49.9) | 69.67 | 48.7 | 69.67 |  | A - Node within 0.5 km | 0.21 | 0.01 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2459
3 | 460 | 2460 | 0300808004 | Region III (Central Luzon) | Bataan | Morong | Poblacion | 14.6777 | 120.268 | U | 7656 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 0.41 | Tier 2 High GIDA (Score 40.0–49.9) | 69.66 | 48.7 | 69.66 |  | A - Node within 0.5 km | 0.41 | 0.23 | Line: Subic-Bagac AERIAL | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2460
3 | 461 | 2461 | 1381100164 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 164 | 14.5338 | 121.0053 | U | 1799 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.41 | Tier 2 High GIDA (Score 40.0–49.9) | 69.66 | 48.7 | 69.66 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.17 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2461
3 | 462 | 2462 | 0103315012 | Region I (Ilocos Region) | La Union | San Gabriel | Lacong | 16.7343 | 120.4334 | R | 1545 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.54 | 4.56 | Tier 2 High GIDA (Score 40.0–49.9) | 69.66 | 48.7 | 69.66 |  | E - Nearest node or line 3-5 km | 7.54 | 4.56 | Line: SAN FERNANDO - SUPIDEN AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2462
3 | 463 | 2463 | PH0002463 | VIII | Leyte | Tacloban City | Barangay 5 | 11.1995 | 124.9983 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.96 | 12.79 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.7 | 69.65 |  | D - Other node or line within 3 km | 1.89 | 0.84 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 2463
3 | 464 | 2464 | 1380611001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 662 | 14.5818 | 120.9831 | U | 1650 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.64 | 58.43 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | B - Node 0.5-1 km | 0.98 | 0.58 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2464
3 | 465 | 2465 | 1380601084 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 84 | 14.6157 | 120.9666 | U | 1176 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.28 | 38.75 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | A - Node within 0.5 km | 0.48 | 0.39 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2465
3 | 466 | 2466 | 1380606180 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 574 | 14.606 | 121.0079 | U | 1524 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.32 | 3.66 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | B - Node 0.5-1 km | 0.57 | 0.43 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2466
3 | 467 | 2467 | 1381100072 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 72 | 14.5413 | 120.9951 | U | 1463 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.56 | 6.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | A - Node within 0.5 km | 0.37 | 0.01 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2467
3 | 468 | 2468 | 1380601198 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 198 | 14.636 | 120.981 | U | 5185 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.72 | 11.86 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | C - Line within 0.5 km; node over 1 km | 1.31 | 0.14 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2468
3 | 469 | 2469 | 1381100116 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 116 | 14.5432 | 121.0002 | U | 1239 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.31 | 12.99 | Tier 2 High GIDA (Score 40.0–49.9) | 69.65 | 48.69 | 69.65 |  | B - Node 0.5-1 km | 0.63 | 0.04 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2469
3 | 470 | 2470 | 1380614030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 774 | 14.575 | 121.0084 | U | 2965 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.57 | 7.04 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.28 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2470
3 | 471 | 2471 | 0702216002 | Region VII (Central Visayas) | Cebu | Catmon | Amancion | 10.6375 | 123.9181 | R | 195 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.22 | 11.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | F - Nearest node and line over 5 km | 12.22 | 11.46 | Line: BOGO - DANAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2471
3 | 472 | 2472 | 1380606107 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 501 | 14.623 | 120.9954 | U | 871 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.98 | 72.86 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | D - Other node or line within 3 km | 1.54 | 0.69 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2472
3 | 473 | 2473 | 0806011023 | Region VIII (Eastern Visayas) | Samar | Matuguinao | San Roque | 12.145 | 124.8853 | R | 200 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.89 | 96.85 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | F - Nearest node and line over 5 km | 96.37 | 96.33 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2473
3 | 474 | 2474 | 1380400021 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tugatog | 14.6606 | 120.9676 | U | 26157 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.75 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | B - Node 0.5-1 km | 0.87 | 0.85 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2474
3 | 475 | 2475 | 1380606172 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 566 | 14.6063 | 121.0061 | U | 2226 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.71 | 2.56 | Tier 2 High GIDA (Score 40.0–49.9) | 69.64 | 48.69 | 69.64 |  | B - Node 0.5-1 km | 0.51 | 0.39 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2475
3 | 476 | 2476 | PH0002476 | NCR | Metro Manila | Caloocan City | Barangay 61 | 14.6144 | 120.9696 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.6 | 4.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.63 | 48.68 | 69.63 |  | B - Node 0.5-1 km | 0.84 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2476
3 | 477 | 2477 | 0806004008 | Region VIII (Eastern Visayas) | Samar | Calbiga | Buluan | 11.6256 | 125.1354 | R | 640 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.3 | 47.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.63 | 48.68 | 69.63 |  | F - Nearest node and line over 5 km | 45.3 | 47.94 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2477
3 | 478 | 2478 | 1381100103 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 103 | 14.5456 | 121.0015 | U | 976 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.63 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.63 | 48.68 | 69.63 |  | B - Node 0.5-1 km | 0.77 | 0.23 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2478
3 | 479 | 2479 | 1380614032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 776 | 14.576 | 121.0085 | U | 4731 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.24 | 18.92 | Tier 2 High GIDA (Score 40.0–49.9) | 69.63 | 48.68 | 69.63 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.26 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2479
3 | 480 | 2480 | 0305415011 | Region III (Central Luzon) | Pampanga | Porac | Diaz | 15.0509 | 120.5456 | R | 470 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 1.04 | Tier 2 High GIDA (Score 40.0–49.9) | 69.62 | 48.67 | 69.62 |  | D - Other node or line within 3 km | 1.5 | 1.04 | Line: 48 CORE (4X12) | Route options survey candidate: compare actual node lateral with approved line tap. | 2480
3 | 481 | 2481 | 1381100127 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 127 | 14.5488 | 121.0062 | U | 1850 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.01 | 2.01 | Tier 2 High GIDA (Score 40.0–49.9) | 69.62 | 48.67 | 69.62 |  | B - Node 0.5-1 km | 0.57 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2481
3 | 482 | 2482 | PH0002482 | NCR | Metro Manila | Caloocan City | Barangay 62 | 14.6504 | 120.9806 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.58 | 54.99 | Tier 2 High GIDA (Score 40.0–49.9) | 69.62 | 48.67 | 69.62 |  | A - Node within 0.5 km | 0.49 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2482
3 | 483 | 2483 | 0806004009 | Region VIII (Eastern Visayas) | Samar | Calbiga | Caamlongan | 11.5681 | 125.1155 | R | 231 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.55 | 41.2 | Tier 2 High GIDA (Score 40.0–49.9) | 69.61 | 48.67 | 69.61 |  | F - Nearest node and line over 5 km | 38.55 | 41.2 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2483
3 | 484 | 2484 | 0300803011 | Region III (Central Luzon) | Bataan | City of Balanga | Ibayo | 14.6691 | 120.5437 | U | 2379 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 0.58 | Tier 2 High GIDA (Score 40.0–49.9) | 69.61 | 48.66 | 69.61 |  | D - Other node or line within 3 km | 1.63 | 0.63 | Line: PILAR | Route options survey candidate: compare actual node lateral with approved line tap. | 2484
3 | 485 | 2485 | 0506203011 | Region V (Bicol Region) | Sorsogon | Bulan | Bical | 12.7349 | 123.9377 | R | 686 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.39 | 3.36 | Tier 2 High GIDA (Score 40.0–49.9) | 69.6 | 48.66 | 69.6 |  | E - Nearest node or line 3-5 km | 7.39 | 3.35 | Line: 30,000m | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2485
3 | 486 | 2486 | 1003518021 | Region X (Northern Mindanao) | Lanao del Norte | Salvador | Pawak | 7.8773 | 123.8823 | R | 1156 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.92 | 10.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.6 | 48.66 | 69.6 |  | F - Nearest node and line over 5 km | 20.57 | 12.6 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2486
3 | 487 | 2487 | 1381100183 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 183 | 14.5239 | 121.0131 | U | 38435 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.35 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.6 | 48.66 | 69.6 |  | A - Node within 0.5 km | 0.35 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2487
3 | 488 | 2488 | 0402106041 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz I | 14.3128 | 120.9607 | U | 5381 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 1.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.59 | 48.65 | 69.59 |  | B - Node 0.5-1 km | 0.55 | 1.36 | Node: DMC004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2488
3 | 489 | 2489 | 1380606128 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 522 | 14.612 | 120.9989 | U | 1124 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.56 | 27.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.59 | 48.65 | 69.59 |  | B - Node 0.5-1 km | 0.54 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2489
3 | 490 | 2490 | 1908702011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Nuyo | 17.2541 | 122.2281 | R | 6458 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.59 | 48.65 | 69.59 |  | F - Nearest node and line over 5 km | 29.3 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2490
3 | 491 | 2491 | 1380612009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 841 | 14.5862 | 121.0007 | U | 2318 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.41 | 44.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.59 | 48.65 | 69.59 |  | A - Node within 0.5 km | 0.3 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2491
3 | 492 | 2492 | PH0002492 | NCR | Metro Manila | Caloocan City | Barangay 38 | 14.6159 | 120.9737 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.71 | 12.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.59 | 48.65 | 69.59 |  | B - Node 0.5-1 km | 0.99 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2492
3 | 493 | 2493 | 1380610047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 732 | 14.5689 | 120.9888 | U | 2034 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.86 | 19.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.65 | 69.58 |  | B - Node 0.5-1 km | 0.68 | 0.34 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2493
3 | 494 | 2494 | 0806007072 | Region VIII (Eastern Visayas) | Samar | Gandara | San Antonio | 12.1424 | 124.8261 | R | 581 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 94.74 | 94.73 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | F - Nearest node and line over 5 km | 94.74 | 94.71 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2494
3 | 495 | 2495 | 1381300106 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Monica | 14.7227 | 121.0469 | U | 54009 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | B - Node 0.5-1 km | 0.53 | 0.33 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2495
3 | 496 | 2496 | 1381100133 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 133 | 14.548 | 121.008 | U | 2284 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.96 | 5.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | A - Node within 0.5 km | 0.42 | 0.26 | Line: Existing 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2496
3 | 497 | 2497 | PH0002497 | VI | Iloilo | Iloilo City | Molo Boulevard | 10.7143 | 122.5642 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.35 | 8.04 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | A - Node within 0.5 km | 0.42 | 0.05 | Line: 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2497
3 | 498 | 2498 | 1380601229 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 228 | 14.6223 | 120.9794 | U | 3101 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.75 | 28.47 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | B - Node 0.5-1 km | 0.74 | 0.04 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2498
3 | 499 | 2499 | 1380500024 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Poblacion | 14.5865 | 121.0249 | U | 17873 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.47 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 69.58 | 48.64 | 69.58 |  | A - Node within 0.5 km | 0.47 | 0.38 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2499
3 | 500 | 2500 | 1380601258 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 257 | 14.6073 | 120.9777 | U | 1348 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.44 | 20.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | B - Node 0.5-1 km | 0.86 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2500
3 | 501 | 2501 | 1381100111 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 111 | 14.5433 | 121.0004 | U | 1315 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 2.29 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | B - Node 0.5-1 km | 0.66 | 0.07 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2501
3 | 502 | 2502 | 1381100171 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 171 | 14.7513 | 120.9555 | U | 3486 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.46 | 3.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | A - Node within 0.5 km | 0.21 | 0.01 | Line: 48 CORE | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2502
3 | 503 | 2503 | 0806011010 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Ligaya | 12.1812 | 124.909 | R | 87 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 97.63 | 97.59 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | F - Nearest node and line over 5 km | 100.52 | 100.49 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2503
3 | 504 | 2504 | 1381300109 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santo Niño | 14.5644 | 121.0474 | U | 7367 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | C - Line within 0.5 km; node over 1 km | 2.03 | 0.37 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2504
3 | 505 | 2505 | 1380601268 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 267 | 14.6212 | 120.9834 | U | 2011 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.11 | 79.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | B - Node 0.5-1 km | 0.52 | 0.05 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2505
3 | 506 | 2506 | PH0002506 | V | Camarines Sur | Iriga City | Antipolo | 13.5339 | 123.4851 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.51 | 5.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.64 | 69.57 |  | F - Nearest node and line over 5 km | 8.51 | 5.41 | Line: EXTG.HH | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2506
3 | 507 | 2507 | 0702232002 | Region VII (Central Visayas) | Cebu | Minglanilla | Calajo-an | 10.2397 | 123.8028 | U | 13251 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.97 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.63 | 69.57 |  | B - Node 0.5-1 km | 0.97 | 0.01 | Line: 96c | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2507
3 | 508 | 2508 | 0103319006 | Region I (Ilocos Region) | La Union | Sudipen | Maliclico | 16.5102 | 120.2936 | R | 850 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.54 | 3.92 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.63 | 69.57 |  | E - Nearest node or line 3-5 km | 4.54 | 3.91 | Line: SEGMENT 0 (AGOO - SAN FERNANDO) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2508
3 | 509 | 2509 | 1380614022 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 766 | 14.567 | 121.0035 | U | 3195 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.88 | 18.43 | Tier 2 High GIDA (Score 40.0–49.9) | 69.57 | 48.63 | 69.57 |  | C - Line within 0.5 km; node over 1 km | 1.14 | 0.02 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2509
3 | 510 | 2510 | 1380612029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 861 | 14.5897 | 121.0038 | U | 1105 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.65 | 6.65 | Tier 2 High GIDA (Score 40.0–49.9) | 69.56 | 48.63 | 69.56 |  | B - Node 0.5-1 km | 0.6 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2510
3 | 511 | 2511 | 1381100057 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 57 | 14.552 | 121.0016 | U | 1400 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 69.56 | 48.63 | 69.56 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.24 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2511
3 | 512 | 2512 | PH0002512 | NCR | Metro Manila | Caloocan City | Barangay 133 | 14.6297 | 120.9696 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.26 | 77.96 | Tier 2 High GIDA (Score 40.0–49.9) | 69.55 | 48.62 | 69.55 |  | B - Node 0.5-1 km | 0.52 | 0.46 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2512
3 | 513 | 2513 | 0103315016 | Region I (Ilocos Region) | La Union | San Gabriel | Lipay Sur | 16.7061 | 120.4446 | R | 1000 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.18 | 7.6 | Tier 2 High GIDA (Score 40.0–49.9) | 69.55 | 48.62 | 69.55 |  | F - Nearest node and line over 5 km | 6.18 | 7.6 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2513
3 | 514 | 2514 | 1380606186 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 580 | 14.6025 | 121.0086 | U | 2069 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.36 | 8.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.55 | 48.62 | 69.55 |  | A - Node within 0.5 km | 0.45 | 0.03 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2514
3 | 515 | 2515 | 0806004001 | Region VIII (Eastern Visayas) | Samar | Calbiga | Antol | 11.5446 | 125.1213 | R | 256 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.3 | 38.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.54 | 48.62 | 69.54 |  | F - Nearest node and line over 5 km | 36.3 | 38.89 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2515
3 | 516 | 2516 | 1380602009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 295 | 14.5993 | 120.9727 | U | 1577 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.98 | 13.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.54 | 48.62 | 69.54 |  | B - Node 0.5-1 km | 0.9 | 0.79 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2516
3 | 517 | 2517 | PH0002517 | IV-A | Cavite | Imus City | Mariano Espeleta I | 14.4256 | 120.8748 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.18 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 69.54 | 48.61 | 69.54 |  | B - Node 0.5-1 km | 0.99 | 0.96 | Line: NOVELETA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2517
3 | 518 | 2518 | 1380606086 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 480 | 14.6094 | 120.9919 | U | 835 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.13 | 52.01 | Tier 2 High GIDA (Score 40.0–49.9) | 69.53 | 48.61 | 69.53 |  | B - Node 0.5-1 km | 0.7 | 0.05 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2518
3 | 519 | 2519 | 1380606059 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 453 | 14.6038 | 120.9976 | U | 1537 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.38 | 15.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.53 | 48.61 | 69.53 |  | B - Node 0.5-1 km | 0.69 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2519
3 | 520 | 2520 | 0306918007 | Region III (Central Luzon) | Tarlac | San Jose | Maamot | 15.3915 | 120.3497 | R | 2740 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.71 | 23.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.53 | 48.61 | 69.53 |  | F - Nearest node and line over 5 km | 20.71 | 22.79 | Node: CPT002 -BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2520
3 | 521 | 2521 | 1380606142 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 536 | 14.6156 | 121.006 | U | 973 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.06 | 17.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.53 | 48.61 | 69.53 |  | B - Node 0.5-1 km | 0.57 | 0.27 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2521
3 | 522 | 2522 | 1380607005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 641 | 14.598 | 120.9925 | U | 786 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.26 | 45.61 | Tier 2 High GIDA (Score 40.0–49.9) | 69.53 | 48.61 | 69.53 |  | B - Node 0.5-1 km | 0.59 | 0.33 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2522
3 | 523 | 2523 | PH0002523 | NCR | Metro Manila | Caloocan City | Barangay 130 | 14.6287 | 120.9666 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 3.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.52 | 48.6 | 69.52 |  | B - Node 0.5-1 km | 0.76 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2523
3 | 524 | 2524 | 1380601060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 60 | 14.6146 | 120.9716 | U | 4640 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.2 | 51.66 | Tier 2 High GIDA (Score 40.0–49.9) | 69.52 | 48.6 | 69.52 |  | B - Node 0.5-1 km | 0.89 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2524
3 | 525 | 2525 | 0405622050 | Region IV-A (CALABARZON) | Quezon | Lopez | Mandoog | 13.8066 | 122.4095 | R | 262 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.85 | 2.7 | Tier 2 High GIDA (Score 40.0–49.9) | 69.52 | 48.6 | 69.52 |  | D - Other node or line within 3 km | 8.34 | 1.32 | Line: AE LZQ001 TO SNQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2525
3 | 526 | 2526 | PH0002526 | NCR | Metro Manila | Caloocan City | Barangay 144 | 14.6324 | 120.9696 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.85 | 37.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.6 | 69.51 |  | B - Node 0.5-1 km | 0.74 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2526
3 | 527 | 2527 | 1381200008 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kapasigan | 14.5762 | 121.0797 | U | 5071 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.6 | 69.51 |  | B - Node 0.5-1 km | 0.53 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2527
3 | 528 | 2528 | 1381100035 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 35 | 14.5625 | 120.996 | U | 617 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.6 | 69.51 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.04 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2528
3 | 529 | 2529 | 1380605006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 302 | 14.6092 | 120.9936 | U | 674 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | B - Node 0.5-1 km | 0.73 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2529
3 | 530 | 2530 | 1380611011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 677 | 14.5815 | 120.9952 | U | 1639 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.6 | 17.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | B - Node 0.5-1 km | 0.87 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2530
3 | 531 | 2531 | PH0002531 | CAR | Benguet | Baguio City | Quezon Hill Proper | 16.4151 | 120.5736 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.48 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | A - Node within 0.5 km | 0.48 | 0.21 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2531
3 | 532 | 2532 | 0806007064 | Region VIII (Eastern Visayas) | Samar | Gandara | Purog | 12.1372 | 124.7778 | R | 465 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.62 | 90.61 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | F - Nearest node and line over 5 km | 90.62 | 90.59 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2532
3 | 533 | 2533 | 1381100073 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 73 | 14.5426 | 120.9961 | U | 719 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | A - Node within 0.5 km | 0.28 | 0.14 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2533
3 | 534 | 2534 | PH0002534 | NCR | Metro Manila | Caloocan City | Barangay 68 | 14.6124 | 120.9656 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.22 | 80.93 | Tier 2 High GIDA (Score 40.0–49.9) | 69.51 | 48.59 | 69.51 |  | B - Node 0.5-1 km | 0.69 | 0.42 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2534
3 | 535 | 2535 | 1908713023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Tinungkaan | 17.254 | 122.2281 | R | 5842 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.5 | 48.59 | 69.5 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2535
3 | 536 | 2536 | 1381100094 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 94 | 14.5402 | 121.0012 | U | 2443 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.19 | 4.93 | Tier 2 High GIDA (Score 40.0–49.9) | 69.5 | 48.59 | 69.5 |  | B - Node 0.5-1 km | 0.88 | 0.08 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2536
3 | 537 | 2537 | 0506210026 | Region V (Bicol Region) | Sorsogon | Juban | Tinago | 12.8523 | 123.94 | R | 934 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.31 | 3.14 | Tier 2 High GIDA (Score 40.0–49.9) | 69.5 | 48.59 | 69.5 |  | D - Other node or line within 3 km | 8.31 | 2.99 | Line: 28,000 m | Route options survey candidate: compare actual node lateral with approved line tap. | 2537
3 | 538 | 2538 | PH0002538 | NCR | Metro Manila | Caloocan City | Barangay 73 | 14.6109 | 120.9635 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.48 | 10.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.5 | 48.59 | 69.5 |  | B - Node 0.5-1 km | 0.79 | 0.61 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2538
3 | 539 | 2539 | 1380606080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 474 | 14.612 | 120.9952 | U | 1705 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.1 | 16.8 | Tier 2 High GIDA (Score 40.0–49.9) | 69.5 | 48.58 | 69.5 |  | B - Node 0.5-1 km | 0.93 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2539
3 | 540 | 2540 | 1381100122 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 122 | 14.5489 | 121.0065 | U | 1218 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.85 | 15.2 | Tier 2 High GIDA (Score 40.0–49.9) | 69.49 | 48.58 | 69.49 |  | B - Node 0.5-1 km | 0.54 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2540
3 | 541 | 2541 | 1705315011 | MIMAROPA Region | Palawan | Narra | Ipilan | 9.1735 | 118.0939 | R | 2144 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 94.34 | 96.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.49 | 48.58 | 69.49 |  | F - Nearest node and line over 5 km | 94.34 | 96.35 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2541
3 | 542 | 2542 | 1380612031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 863 | 14.5873 | 121.0042 | U | 1526 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.34 | 85.72 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.58 | 69.48 |  | A - Node within 0.5 km | 0.36 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2542
3 | 543 | 2543 | 1381100063 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 63 | 14.5528 | 121.0009 | U | 698 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.58 | 69.48 |  | B - Node 0.5-1 km | 0.99 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2543
3 | 544 | 2544 | 1380607009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 645 | 14.5934 | 120.99 | U | 1756 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 1.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.57 | 69.48 |  | B - Node 0.5-1 km | 0.69 | 0.57 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2544
3 | 545 | 2545 | 0405603027 | Region IV-A (CALABARZON) | Quezon | Atimonan | Montes Balaon | 13.9492 | 121.8814 | R | 178 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.44 | 3.96 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.57 | 69.48 |  | E - Nearest node or line 3-5 km | 7.44 | 3.95 | Line: SAN JUAN TO UNISAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2545
3 | 546 | 2546 | 0806004038 | Region VIII (Eastern Visayas) | Samar | Calbiga | San Mauricio | 11.5933 | 125.0447 | R | 301 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.6 | 42.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.57 | 69.48 |  | F - Nearest node and line over 5 km | 39.6 | 42.51 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2546
3 | 547 | 2547 | 1102508013 | Region XI (Davao Region) | Davao Oriental | Manay | San Fermin | 7.2698 | 126.4413 | R | 1137 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.93 | 42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.57 | 69.48 |  | F - Nearest node and line over 5 km | 42.93 | 41.83 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2547
3 | 548 | 2548 | 1381100128 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 128 | 14.5481 | 121.0048 | U | 1680 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.88 | 6.85 | Tier 2 High GIDA (Score 40.0–49.9) | 69.48 | 48.57 | 69.48 |  | B - Node 0.5-1 km | 0.74 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2548
3 | 549 | 2549 | 0806004005 | Region VIII (Eastern Visayas) | Samar | Calbiga | Binanggaran | 11.6087 | 125.1227 | R | 158 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.08 | 45.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.47 | 48.57 | 69.47 |  | F - Nearest node and line over 5 km | 43.08 | 45.75 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2549
3 | 550 | 2550 | 1381100107 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 107 | 14.5462 | 121.0027 | U | 1605 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 2.1 | Tier 2 High GIDA (Score 40.0–49.9) | 69.47 | 48.57 | 69.47 |  | B - Node 0.5-1 km | 0.91 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2550
3 | 551 | 2551 | PH0002551 | VIII | Leyte | Tacloban City | Barangay 6 | 11.2448 | 125.0057 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 3.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.47 | 48.56 | 69.47 |  | B - Node 0.5-1 km | 0.67 | 3.6 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2551
3 | 552 | 2552 | 1381100141 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 141 | 14.5492 | 121.0069 | U | 478 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.53 | 2.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | A - Node within 0.5 km | 0.49 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2552
3 | 553 | 2553 | PH0002553 | I | Ilocos Norte | Laoag City | Bgy. No. 16, San Jacinto (Pob.) | 18.1852 | 120.5292 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.87 | 1.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | F - Nearest node and line over 5 km | 6.4 | 6.13 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2553
3 | 554 | 2554 | 1381100069 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 69 | 14.545 | 120.9956 | U | 1186 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.12 | 10.1 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | A - Node within 0.5 km | 0.14 | 0.15 | Node: PSY022 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2554
3 | 555 | 2555 | 1381100153 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 153 | 14.535 | 121.0086 | U | 1406 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 1.49 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | D - Other node or line within 3 km | 1.47 | 0.54 | Line: Existing 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2555
3 | 556 | 2556 | 1381100021 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 21 | 14.6177 | 120.9807 | U | 812 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.79 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | A - Node within 0.5 km | 0.27 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2556
3 | 557 | 2557 | 1380606133 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 527 | 14.6098 | 120.9966 | U | 2199 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.18 | 10.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.46 | 48.56 | 69.46 |  | B - Node 0.5-1 km | 0.78 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2557
3 | 558 | 2558 | 1380606225 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 618 | 14.5898 | 121.0194 | U | 762 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.04 | 15.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.56 | 69.45 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.29 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2558
3 | 559 | 2559 | PH0002559 | NCR | Metro Manila | Caloocan City | Barangay 36 | 14.6033 | 120.9636 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.4 | 42.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | B - Node 0.5-1 km | 0.76 | 0.76 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2559
3 | 560 | 2560 | 1380614035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 779 | 14.5783 | 121.0072 | U | 4579 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.27 | 34.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | B - Node 0.5-1 km | 0.83 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2560
3 | 561 | 2561 | 1380606224 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 617 | 14.5967 | 121.0161 | U | 949 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.24 | 30.86 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | D - Other node or line within 3 km | 1.38 | 0.68 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2561
3 | 562 | 2562 | PH0002562 | II | Nueva Vizcaya | Santa Fe N Vizcaya | Santa Rosa | 16.1931 | 120.8927 | R | 2464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.04 | 2.75 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | F - Nearest node and line over 5 km | 6.2 | 5.69 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2562
3 | 563 | 2563 | 1102508007 | Region XI (Davao Region) | Davao Oriental | Manay | Guza | 7.2151 | 126.5402 | R | 798 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.23 | 44.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | F - Nearest node and line over 5 km | 46.23 | 43.85 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2563
3 | 564 | 2564 | 1380607002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 638 | 14.5974 | 120.9943 | U | 562 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.41 | 31.2 | Tier 2 High GIDA (Score 40.0–49.9) | 69.45 | 48.55 | 69.45 |  | B - Node 0.5-1 km | 0.72 | 0.39 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2564
3 | 565 | 2565 | 1908824005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Fugotan | 17.2542 | 122.2282 | R | 993 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.31 | 40.85 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.55 | 69.44 |  | F - Nearest node and line over 5 km | 29.31 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2565
3 | 566 | 2566 | 1906617008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Kutah Parang | 5.705 | 120.8564 | R | 1056 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 189.91 | 189.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.55 | 69.44 |  | F - Nearest node and line over 5 km | 189.91 | 189.9 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2566
3 | 567 | 2567 | 1380601050 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 50 | 14.6154 | 120.9717 | U | 4345 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 9.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.55 | 69.44 |  | B - Node 0.5-1 km | 0.99 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2567
3 | 568 | 2568 | 1380606121 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 515 | 14.6204 | 120.9962 | U | 2232 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.25 | 66.82 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | D - Other node or line within 3 km | 1.33 | 0.71 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2568
3 | 569 | 2569 | 0806011019 | Region VIII (Eastern Visayas) | Samar | Matuguinao | San Isidro | 12.1806 | 124.9092 | R | 257 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 100.57 | 100.56 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | F - Nearest node and line over 5 km | 100.57 | 100.54 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2569
3 | 570 | 2570 | 1903623037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pualas | Yaran | 17.2548 | 122.2289 | R | 977 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | F - Nearest node and line over 5 km | 29.42 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2570
3 | 571 | 2571 | 0506209022 | Region V (Bicol Region) | Sorsogon | Irosin | San Isidro | 12.6939 | 124.0058 | R | 785 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.37 | 0.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | D - Other node or line within 3 km | 3.37 | 0.73 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Route options survey candidate: compare actual node lateral with approved line tap. | 2571
3 | 572 | 2572 | 0806011012 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Maduroto Pob. | 12.1732 | 124.8645 | R | 1739 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 95.98 | 95.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | F - Nearest node and line over 5 km | 96.64 | 96.61 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2572
3 | 573 | 2573 | PH0002573 | NCR | Metro Manila | Caloocan City | Barangay 102 | 14.6245 | 120.9635 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.36 | 3.47 | Tier 2 High GIDA (Score 40.0–49.9) | 69.44 | 48.54 | 69.44 |  | B - Node 0.5-1 km | 0.73 | 0.98 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2573
3 | 574 | 2574 | 1003515018 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Notongan | 7.7986 | 123.9246 | R | 532 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 18.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.43 | 48.54 | 69.43 |  | F - Nearest node and line over 5 km | 30.49 | 20.34 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2574
3 | 575 | 2575 | 0806007103 | Region VIII (Eastern Visayas) | Samar | Gandara | Sidmon | 12.0463 | 124.8027 | R | 304 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.92 | 83.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.43 | 48.54 | 69.43 |  | F - Nearest node and line over 5 km | 83.92 | 83.89 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2575
3 | 576 | 2576 | 1003515006 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Inayawan | 7.7991 | 123.9242 | R | 943 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.51 | 20.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.43 | 48.54 | 69.43 |  | F - Nearest node and line over 5 km | 30.42 | 20.28 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2576
3 | 577 | 2577 | 1380614047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 791 | 14.5702 | 120.9986 | U | 2091 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.01 | 31.59 | Tier 2 High GIDA (Score 40.0–49.9) | 69.43 | 48.54 | 69.43 |  | B - Node 0.5-1 km | 0.51 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2577
3 | 578 | 2578 | 1705208065 | MIMAROPA Region | Oriental Mindoro | Naujan | Tigkan | 13.2879 | 121.1851 | R | 816 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.11 | 1.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.43 | 48.54 | 69.43 |  | D - Other node or line within 3 km | 3.11 | 1.98 | Line: AE | Route options survey candidate: compare actual node lateral with approved line tap. | 2578
3 | 579 | 2579 | 0402104019 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 8 | 14.3137 | 121.0538 | R | 3290 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.42 | 48.53 | 69.42 |  | B - Node 0.5-1 km | 0.51 | 0.18 | Line: AE CRC005-BNL001-CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2579
3 | 580 | 2580 | 1003515003 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Canibongan | 7.7979 | 123.9244 | R | 589 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.83 | 18.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.42 | 48.53 | 69.42 |  | F - Nearest node and line over 5 km | 30.55 | 20.37 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2580
3 | 581 | 2581 | 1381100113 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 113 | 14.5454 | 121.001 | U | 1851 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.62 | 10.61 | Tier 2 High GIDA (Score 40.0–49.9) | 69.42 | 48.53 | 69.42 |  | B - Node 0.5-1 km | 0.71 | 0.18 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2581
3 | 582 | 2582 | 0907311015 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Kitaan Dagat | 7.8021 | 123.1421 | R | 511 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.52 | 3.29 | Tier 2 High GIDA (Score 40.0–49.9) | 69.42 | 48.53 | 69.42 |  | E - Nearest node or line 3-5 km | 12.52 | 3.25 | Line: PAGADIAN - BUUG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2582
3 | 583 | 2583 | 1380601266 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 265 | 14.623 | 120.9837 | U | 129 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.55 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.42 | 48.53 | 69.42 |  | B - Node 0.5-1 km | 0.72 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2583
3 | 584 | 2584 | 0301416004 | Region III (Central Luzon) | Bulacan | Paombong | Masukol | 14.7642 | 120.7707 | R | 1452 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.9 | 10.85 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.53 | 69.41 |  | F - Nearest node and line over 5 km | 7.9 | 10.93 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2584
3 | 585 | 2585 | 1380611006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 672 | 14.5818 | 120.993 | U | 3228 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.97 | 5.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.53 | 69.41 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.35 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2585
3 | 586 | 2586 | 1380606167 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 561 | 14.603 | 121.0073 | U | 2403 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.58 | 1.63 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.53 | 69.41 |  | A - Node within 0.5 km | 0.32 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2586
3 | 587 | 2587 | PH0002587 | IV-B | Palawan | Puerto Princesa City | Matiyaga (Pob.) | 9.9801 | 118.9298 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.32 | 3.8 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.52 | 69.41 |  | A - Node within 0.5 km | 0.34 | 0.02 | Line: TAYTAY - PUERTO PRINCESA | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2587
3 | 588 | 2588 | 1705314006 | MIMAROPA Region | Palawan | Magsaysay | Emilod | 10.8463 | 121.059 | R | 773 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.46 | 96.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.52 | 69.41 |  | F - Nearest node and line over 5 km | 96.46 | 96.44 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2588
3 | 589 | 2589 | 1380610017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 702 | 14.5723 | 120.9914 | U | 3443 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.72 | 64.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.41 | 48.52 | 69.41 |  | A - Node within 0.5 km | 0.31 | 0.12 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2589
3 | 590 | 2590 | 1380614053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 797 | 14.5695 | 120.9967 | U | 251 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.6 | 10.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.4 | 48.52 | 69.4 |  | A - Node within 0.5 km | 0.38 | 0.29 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2590
3 | 591 | 2591 | 1403213016 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Guilayon | 17.4616 | 121.3395 | R | 901 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.39 | 6.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.4 | 48.52 | 69.4 |  | F - Nearest node and line over 5 km | 9.39 | 6.26 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2591
3 | 592 | 2592 | 1381300013 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Balingasa | 14.6521 | 121.0013 | U | 20068 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 1.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.4 | 48.52 | 69.4 |  | D - Other node or line within 3 km | 1.57 | 1.51 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2592
3 | 593 | 2593 | 1380605032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 330 | 14.6071 | 120.9794 | U | 2312 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.49 | 16.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.4 | 48.51 | 69.4 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.27 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2593
3 | 594 | 2594 | 1381100177 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 177 | 14.5352 | 120.9992 | U | 6412 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | B - Node 0.5-1 km | 0.85 | 0.01 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2594
3 | 595 | 2595 | 1705305012 | MIMAROPA Region | Palawan | Bataraza | Puring | 8.3856 | 117.2259 | R | 1641 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 223.85 | 226.14 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | F - Nearest node and line over 5 km | 223.85 | 225.87 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2595
3 | 596 | 2596 | 1381701007 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Santa Ana | 14.5466 | 121.0718 | U | 30632 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.43 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | A - Node within 0.5 km | 0.43 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2596
3 | 597 | 2597 | 1380300011 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Kasilawan | 14.5599 | 121.0498 | U | 2375 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | D - Other node or line within 3 km | 2.39 | 0.73 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2597
3 | 598 | 2598 | PH0002598 | CAR | Benguet | Baguio City | Kayang Extension | 16.372 | 120.5784 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.96 | 1.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | D - Other node or line within 3 km | 3.89 | 1.91 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 2598
3 | 599 | 2599 | 1380611046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 831 | 14.5837 | 120.9966 | U | 3452 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.26 | 32.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.39 | 48.51 | 69.39 |  | B - Node 0.5-1 km | 0.67 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2599
3 | 600 | 2600 | 1380606227 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 620 | 14.5874 | 121.0152 | U | 747 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.36 | 53.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.38 | 48.51 | 69.38 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.41 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2600
3 | 601 | 2601 | 1001320025 | Region X (Northern Mindanao) | Bukidnon | Talakag | Salucot | 8.0498 | 124.6424 | R | 1959 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.36 | 1.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.38 | 48.5 | 69.38 |  | F - Nearest node and line over 5 km | 21.36 | 21.37 | Node: TKB001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2601
3 | 602 | 2602 | 1003515004 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Karcum | 7.7894 | 123.9154 | R | 732 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 19.12 | Tier 2 High GIDA (Score 40.0–49.9) | 69.38 | 48.5 | 69.38 |  | F - Nearest node and line over 5 km | 30.96 | 20.05 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2602
3 | 603 | 2603 | 1380614092 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 899 | 14.5836 | 121.0085 | U | 1609 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.05 | 11.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.37 | 48.5 | 69.37 |  | B - Node 0.5-1 km | 0.62 | 0.34 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2603
3 | 604 | 2604 | PH0002604 | NCR | Metro Manila | Caloocan City | Barangay 145 | 14.6312 | 120.9675 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.13 | 44.81 | Tier 2 High GIDA (Score 40.0–49.9) | 69.37 | 48.5 | 69.37 |  | B - Node 0.5-1 km | 0.79 | 0.73 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2604
3 | 605 | 2605 | 1381100160 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 160 | 14.5369 | 121.009 | U | 1280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.54 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.37 | 48.5 | 69.37 |  | D - Other node or line within 3 km | 1.45 | 0.6 | Line: Existing 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2605
3 | 606 | 2606 | 0804814026 | Region VIII (Eastern Visayas) | Northern Samar | Palapag | Sangay | 12.5358 | 125.1282 | R | 793 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 110.55 | 109.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.37 | 48.49 | 69.37 |  | F - Nearest node and line over 5 km | 110.55 | 110.62 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2606
3 | 607 | 2607 | 1380614051 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 795 | 14.5719 | 121.0009 | U | 1192 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.1 | 26.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.37 | 48.49 | 69.37 |  | B - Node 0.5-1 km | 0.71 | 0.48 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2607
3 | 608 | 2608 | PH0002608 | VIII | Northern Samar | Victoria N Samar | Lungib | 12.4622 | 124.3565 | R | 2223 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.3 | 76.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 32.88 | 32.85 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2608
3 | 609 | 2609 | 0500512033 | Region V (Bicol Region) | Albay | Oas | Mayag | 13.168 | 123.3985 | R | 453 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.69 | 14.99 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 6.69 | 14.93 | Node: LOA003 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2609
3 | 610 | 2610 | 1381100175 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 175 | 14.5346 | 121.0133 | U | 2008 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | C - Line within 0.5 km; node over 1 km | 1.43 | 0.49 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2610
3 | 611 | 2611 | 1380611005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 671 | 14.5813 | 120.9929 | U | 1264 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.26 | 23.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.3 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2611
3 | 612 | 2612 | 1003515027 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Taraka | 7.7977 | 123.9238 | R | 701 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.44 | 21.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 30.54 | 20.32 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2612
3 | 613 | 2613 | 0806007050 | Region VIII (Eastern Visayas) | Samar | Gandara | Macugo | 12.0514 | 124.7984 | R | 397 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.42 | 84.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 84.42 | 84.39 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2613
3 | 614 | 2614 | 0806011014 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Mahayag | 12.1264 | 124.8893 | R | 160 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 97.8 | 97.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 94.45 | 94.41 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2614
3 | 615 | 2615 | 0806011008 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Del Rosario | 12.1447 | 124.8851 | R | 155 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.34 | 96.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 96.34 | 96.3 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2615
3 | 616 | 2616 | 0806011006 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Carolina | 12.1602 | 124.8647 | R | 153 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.93 | 96.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.36 | 48.49 | 69.36 |  | F - Nearest node and line over 5 km | 97.36 | 97.33 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2616
3 | 617 | 2617 | 1381300094 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Salvacion | 13.3575 | 121.1015 | U | 6961 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.49 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.49 | 69.35 |  | B - Node 0.5-1 km | 0.61 | 0.01 | Line: MINDORO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2617
3 | 618 | 2618 | 0603014003 | Region VI (Western Visayas) | Iloilo | Carles | Asluman | 11.6187 | 123.3489 | R | 3442 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.1 | 20.48 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.49 | 69.35 |  | F - Nearest node and line over 5 km | 30.1 | 31.1 | Node: ECI001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2618
3 | 619 | 2619 | PH0002619 | NCR | Metro Manila | Caloocan City | Barangay 143 | 14.6289 | 120.967 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.88 | 65.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.49 | 69.35 |  | B - Node 0.5-1 km | 0.72 | 0.63 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2619
3 | 620 | 2620 | 1003515026 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Songgod | 7.7823 | 123.8889 | R | 558 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 17.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.48 | 69.35 |  | F - Nearest node and line over 5 km | 30.62 | 18.22 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2620
3 | 621 | 2621 | PH0002621 | III | Nueva Ecija | Cabanatuan City | Nabao (Pob.) | 15.4793 | 120.9278 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.45 | 1.84 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.48 | 69.35 |  | E - Nearest node or line 3-5 km | 3.58 | 3.11 | Line: MULTINET - SANTA ROSA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2621
3 | 622 | 2622 | 0806011020 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Santa Cruz | 12.1449 | 124.8851 | R | 186 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.36 | 96.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.48 | 69.35 |  | F - Nearest node and line over 5 km | 96.36 | 96.31 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2622
3 | 623 | 2623 | 1380601264 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 263 | 14.6213 | 120.9825 | U | 1346 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.65 | 83.55 | Tier 2 High GIDA (Score 40.0–49.9) | 69.35 | 48.48 | 69.35 |  | B - Node 0.5-1 km | 0.54 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2623
3 | 624 | 2624 | 1380614049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 793 | 14.5696 | 121.0004 | U | 1774 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.56 | 11.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.34 | 48.48 | 69.34 |  | B - Node 0.5-1 km | 0.72 | 0.43 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2624
3 | 625 | 2625 | 0806007049 | Region VIII (Eastern Visayas) | Samar | Gandara | Mabuhay | 12.0847 | 124.8937 | R | 258 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.07 | 90.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.34 | 48.48 | 69.34 |  | F - Nearest node and line over 5 km | 90.07 | 90.03 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2625
3 | 626 | 2626 | PH0002626 | NCR | Metro Manila | Caloocan City | Barangay 142 | 14.6644 | 120.9928 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.03 | 34.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.34 | 48.48 | 69.34 |  | B - Node 0.5-1 km | 0.52 | 0.93 | Node: CCS005 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2626
3 | 627 | 2627 | 0600409003 | Region VI (Western Visayas) | Aklan | Libacao | Batobato | 11.4228 | 122.2794 | R | 474 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.25 | 18.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.34 | 48.48 | 69.34 |  | F - Nearest node and line over 5 km | 18.25 | 18.19 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2627
3 | 628 | 2628 | 1380606019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 413 | 14.5996 | 120.9949 | U | 1754 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.52 | 8.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.34 | 48.47 | 69.34 |  | B - Node 0.5-1 km | 0.56 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2628
3 | 629 | 2629 | 1380612005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 837 | 14.588 | 121.0108 | U | 3131 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.96 | 6.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.33 | 48.47 | 69.33 |  | B - Node 0.5-1 km | 0.95 | 0.7 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2629
3 | 630 | 2630 | 1004322003 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Bunal | 8.8333 | 124.833 | R | 497 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.63 | 4.5 | Tier 2 High GIDA (Score 40.0–49.9) | 69.33 | 48.47 | 69.33 |  | E - Nearest node or line 3-5 km | 5.63 | 4.45 | Line: CDO - BUENAVISTA via GINGOOG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2630
3 | 631 | 2631 | 1381100126 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 126 | 14.5495 | 121.0077 | U | 746 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.94 | 8.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.33 | 48.47 | 69.33 |  | A - Node within 0.5 km | 0.4 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2631
3 | 632 | 2632 | 1380606102 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 496 | 14.622 | 120.9942 | U | 1213 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.01 | 22.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.33 | 48.47 | 69.33 |  | D - Other node or line within 3 km | 1.37 | 0.65 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2632
3 | 633 | 2633 | 1380606020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 414 | 14.5984 | 120.9928 | U | 1768 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.87 | 42.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.33 | 48.47 | 69.33 |  | B - Node 0.5-1 km | 0.55 | 0.31 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2633
3 | 634 | 2634 | 1380606139 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 533 | 14.6146 | 121.003 | U | 941 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 25.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.32 | 48.47 | 69.32 |  | A - Node within 0.5 km | 0.41 | 0.32 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2634
3 | 635 | 2635 | PH0002635 | VII | Cebu | Talisay City | Bulacao | 10.2711 | 123.8424 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.98 | 9.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.32 | 48.46 | 69.32 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.31 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2635
3 | 636 | 2636 | 1380601052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 52 | 14.6177 | 120.9722 | U | 2815 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.75 | 10.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.32 | 48.46 | 69.32 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2636
3 | 637 | 2637 | 1380607006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 642 | 14.5972 | 120.9906 | U | 1318 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.61 | 53.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.32 | 48.46 | 69.32 |  | B - Node 0.5-1 km | 0.66 | 0.37 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2637
3 | 638 | 2638 | 1380611024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 810 | 14.5807 | 121.0009 | U | 2363 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.54 | 45.1 | Tier 2 High GIDA (Score 40.0–49.9) | 69.32 | 48.46 | 69.32 |  | A - Node within 0.5 km | 0.46 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2638
3 | 639 | 2639 | 1903631015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Mantailoco | 17.2548 | 122.2289 | R | 958 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.31 | 48.46 | 69.31 |  | F - Nearest node and line over 5 km | 29.41 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2639
3 | 640 | 2640 | 0907311017 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Limamawan | 7.7982 | 123.1703 | R | 326 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.8 | 1.57 | Tier 2 High GIDA (Score 40.0–49.9) | 69.31 | 48.45 | 69.31 |  | D - Other node or line within 3 km | 14.8 | 1.57 | Line: PAGADIAN - BUUG | Route options survey candidate: compare actual node lateral with approved line tap. | 2640
3 | 641 | 2641 | PH0002641 | NCR | Metro Manila | Caloocan City | Barangay 43 | 14.6192 | 120.9725 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.78 | 9.41 | Tier 2 High GIDA (Score 40.0–49.9) | 69.31 | 48.45 | 69.31 |  | B - Node 0.5-1 km | 0.86 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2641
3 | 642 | 2642 | PH0002642 | NCR | Metro Manila | Caloocan City | Barangay 29 | 14.6024 | 120.9644 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.75 | 79.22 | Tier 2 High GIDA (Score 40.0–49.9) | 69.3 | 48.45 | 69.3 |  | B - Node 0.5-1 km | 0.75 | 0.74 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2642
3 | 643 | 2643 | 1380606171 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 565 | 14.6029 | 121.0082 | U | 2539 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 3.22 | Tier 2 High GIDA (Score 40.0–49.9) | 69.3 | 48.45 | 69.3 |  | A - Node within 0.5 km | 0.41 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2643
3 | 644 | 2644 | 0504117022 | Region V (Bicol Region) | Masbate | Placer | Nagarao | 11.8184 | 123.8447 | R | 835 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.13 | 31.85 | Tier 2 High GIDA (Score 40.0–49.9) | 69.3 | 48.45 | 69.3 |  | F - Nearest node and line over 5 km | 9.13 | 57.58 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2644
3 | 645 | 2645 | 1380606047 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 441 | 14.6042 | 120.9995 | U | 882 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.78 | 10.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | B - Node 0.5-1 km | 0.59 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2645
3 | 646 | 2646 | 1381100124 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 124 | 14.5475 | 121.0071 | U | 1713 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.46 | 16.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | B - Node 0.5-1 km | 0.53 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2646
3 | 647 | 2647 | 1102508016 | Region XI (Davao Region) | Davao Oriental | Manay | New Taokanga | 7.2635 | 126.3908 | R | 3025 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.26 | 38.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | F - Nearest node and line over 5 km | 39.26 | 38.68 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2647
3 | 648 | 2648 | 1906605008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Maimbung | Gulangan | 17.2553 | 122.2294 | R | 1007 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2648
3 | 649 | 2649 | 0806011022 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Inubod | 12.1448 | 124.8851 | R | 259 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.35 | 96.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | F - Nearest node and line over 5 km | 96.35 | 96.3 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2649
3 | 650 | 2650 | 0806007055 | Region VIII (Eastern Visayas) | Samar | Gandara | Nalihugan | 12.0724 | 124.8179 | R | 325 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 87.04 | 87.01 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | F - Nearest node and line over 5 km | 87.04 | 87.01 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2650
3 | 651 | 2651 | 1381100104 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 104 | 14.5449 | 121.0019 | U | 1159 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.8 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | B - Node 0.5-1 km | 0.8 | 0.26 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2651
3 | 652 | 2652 | 0806007073 | Region VIII (Eastern Visayas) | Samar | Gandara | San Enrique | 11.9699 | 124.7177 | R | 122 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.79 | 83.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.29 | 48.44 | 69.29 |  | F - Nearest node and line over 5 km | 74.57 | 74.54 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2652
3 | 653 | 2653 | 1380606220 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 613 | 14.5968 | 121.0152 | U | 585 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.71 | 9.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.28 | 48.44 | 69.28 |  | D - Other node or line within 3 km | 1.29 | 0.65 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2653
3 | 654 | 2654 | 1381100165 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 165 | 14.5366 | 121.0073 | U | 5628 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.77 | 3.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.28 | 48.44 | 69.28 |  | C - Line within 0.5 km; node over 1 km | 1.46 | 0.42 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2654
3 | 655 | 2655 | 0804809012 | Region VIII (Eastern Visayas) | Northern Samar | Lapinig | Palanas | 12.2795 | 125.3063 | R | 267 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 120.27 | 122.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.28 | 48.43 | 69.28 |  | F - Nearest node and line over 5 km | 120.27 | 122.97 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2655
3 | 656 | 2656 | 1380606189 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 583 | 14.6036 | 121.0116 | U | 1317 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.5 | 10.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.28 | 48.43 | 69.28 |  | B - Node 0.5-1 km | 0.78 | 0.12 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2656
3 | 657 | 2657 | PH0002657 | IV-A | Laguna | San Pablo City | Barangay I-B (Pob.) | 14.0691 | 121.3161 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | C - Line within 0.5 km; node over 1 km | 1.33 | 0.16 | Line: AE NGL001 TO SPO001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2657
3 | 658 | 2658 | 1380614050 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 794 | 14.5684 | 120.9983 | U | 732 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.98 | 9.7 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | B - Node 0.5-1 km | 0.59 | 0.42 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2658
3 | 659 | 2659 | 1380601215 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 214 | 14.6289 | 120.9806 | U | 1625 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.76 | 18.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | B - Node 0.5-1 km | 0.82 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2659
3 | 660 | 2660 | 1381100112 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 112 | 14.5461 | 121.0025 | U | 658 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.84 | 4.58 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | B - Node 0.5-1 km | 0.88 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2660
3 | 661 | 2661 | 1380611012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 678 | 14.5824 | 120.9963 | U | 1333 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.43 | 44.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | B - Node 0.5-1 km | 0.73 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2661
3 | 662 | 2662 | 1908824007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Katibpuan | 17.2551 | 122.2291 | R | 3559 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2662
3 | 663 | 2663 | 1380614075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 882 | 14.5838 | 121.0164 | U | 1337 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.83 | 20.73 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.43 | 69.27 |  | C - Line within 0.5 km; node over 1 km | 1.26 | 0 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2663
3 | 664 | 2664 | 1380606229 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 622 | 14.5897 | 121.0157 | U | 1233 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.13 | 37.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.27 | 48.42 | 69.27 |  | D - Other node or line within 3 km | 1.49 | 0.56 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2664
3 | 665 | 2665 | 1380606141 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 535 | 14.6168 | 121.0035 | U | 1066 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.19 | 12.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | B - Node 0.5-1 km | 0.65 | 0.24 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2665
3 | 666 | 2666 | 1381100029 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 29 | 14.6155 | 120.9796 | U | 1470 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.03 | 6.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | A - Node within 0.5 km | 0.37 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2666
3 | 667 | 2667 | PH0002667 | I | Pangasinan | Dagupan City | Barangay II | 16.044 | 120.3303 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.37 | 0.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | C - Line within 0.5 km; node over 1 km | 2.56 | 0.32 | Line: DAGUPAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2667
3 | 668 | 2668 | 0806004014 | Region VIII (Eastern Visayas) | Samar | Calbiga | Daligan | 11.6445 | 125.0938 | R | 181 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.11 | 48.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | F - Nearest node and line over 5 km | 46.11 | 48.9 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2668
3 | 669 | 2669 | 1908819002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Bakat | 17.2552 | 122.2292 | R | 2579 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2669
3 | 670 | 2670 | 0300809015 | Region III (Central Luzon) | Bataan | Orani | Parang Parang | 14.797 | 120.5385 | U | 1363 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | B - Node 0.5-1 km | 0.62 | 0.09 | Line: 36 CORE 3X12 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2670
3 | 671 | 2671 | 1404405003 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Banao | 17.0715 | 121.2126 | R | 295 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.27 | 18.01 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | F - Nearest node and line over 5 km | 8.27 | 17.91 | Node: NNV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2671
3 | 672 | 2672 | 1381100053 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 53 | 14.5506 | 120.9996 | U | 810 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 1.13 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | B - Node 0.5-1 km | 0.88 | 0.16 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2672
3 | 673 | 2673 | 0102934006 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay IV | 17.5742 | 120.3836 | R | 2081 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 1.09 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | D - Other node or line within 3 km | 2.27 | 0.97 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 2673
3 | 674 | 2674 | 1380606045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 439 | 14.6066 | 120.9991 | U | 1084 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.43 | 76.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.26 | 48.42 | 69.26 |  | B - Node 0.5-1 km | 0.7 | 0.21 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2674
3 | 675 | 2675 | 1381100034 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 34 | 14.5633 | 120.9974 | U | 966 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.38 | 7.21 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.42 | 69.25 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.04 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2675
3 | 676 | 2676 | 1381100030 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 30 | 14.6182 | 120.9817 | U | 991 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | A - Node within 0.5 km | 0.23 | 0.13 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2676
3 | 677 | 2677 | 1380606188 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 582 | 14.6048 | 121.0091 | U | 1610 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.2 | 25.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | B - Node 0.5-1 km | 0.58 | 0.28 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2677
3 | 678 | 2678 | 1380614029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 773 | 14.5762 | 121.0105 | U | 2831 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.47 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2678
3 | 679 | 2679 | 1380614052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 796 | 14.5707 | 120.9988 | U | 650 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.43 | 0.47 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | B - Node 0.5-1 km | 0.51 | 0.3 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2679
3 | 680 | 2680 | 1380614037 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 781 | 14.5797 | 121.0114 | U | 4405 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.01 | 11.79 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.16 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2680
3 | 681 | 2681 | 1380606021 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 415 | 14.6019 | 120.9954 | U | 911 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.31 | 56.47 | Tier 2 High GIDA (Score 40.0–49.9) | 69.25 | 48.41 | 69.25 |  | A - Node within 0.5 km | 0.47 | 0.1 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2681
3 | 682 | 2682 | 1380606178 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 572 | 14.6038 | 121.0075 | U | 1912 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.84 | 20.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | A - Node within 0.5 km | 0.37 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2682
3 | 683 | 2683 | 1380614026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 770 | 14.5751 | 121.0075 | U | 9944 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.3 | 11.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | C - Line within 0.5 km; node over 1 km | 1.15 | 0.36 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2683
3 | 684 | 2684 | 1380606147 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 541 | 14.6143 | 121.0048 | U | 500 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.79 | 39.6 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | A - Node within 0.5 km | 0.38 | 0.29 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2684
3 | 685 | 2685 | PH0002685 | VIII | Leyte | Tacloban City | Barangay 41 | 11.2294 | 124.9922 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.63 | 5.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | D - Other node or line within 3 km | 1.59 | 2.64 | Node: TCL002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2685
3 | 686 | 2686 | 1380610053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 739 | 14.5669 | 121.0044 | U | 4668 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.31 | 58.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.03 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2686
3 | 687 | 2687 | PH0002687 | IV-B | Palawan | Puerto Princesa City | Masigla (Pob.) | 9.7401 | 118.7299 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.97 | 2.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | A - Node within 0.5 km | 0.41 | 2.37 | Node: PPW002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2687
3 | 688 | 2688 | 1380606175 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 569 | 14.6027 | 121.0045 | U | 2149 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 2.57 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.41 | 69.24 |  | A - Node within 0.5 km | 0.08 | 0.04 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2688
3 | 689 | 2689 | 1908804005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Nunangan | 17.2552 | 122.2292 | R | 4564 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.4 | 69.24 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2689
3 | 690 | 2690 | 0500511008 | Region V (Bicol Region) | Albay | Manito | Cawit | 13.1293 | 123.8626 | R | 1143 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.89 | 11.91 | Tier 2 High GIDA (Score 40.0–49.9) | 69.24 | 48.4 | 69.24 |  | B - Node 0.5-1 km | 0.89 | 11.9 | Node: MNT001 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2690
3 | 691 | 2691 | 0907214028 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sergio Osmeña Sr. | San Antonio | 8.2495 | 123.3123 | R | 626 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.72 | 44.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | F - Nearest node and line over 5 km | 44.72 | 44.54 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2691
3 | 692 | 2692 | 1380605080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 377 | 14.6302 | 120.9856 | U | 596 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.44 | 23.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | C - Line within 0.5 km; node over 1 km | 1.37 | 0.28 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2692
3 | 693 | 2693 | 1380606061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 455 | 14.606 | 120.998 | U | 1313 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.76 | 18.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.8 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2693
3 | 694 | 2694 | 0401005075 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 6 | 13.7603 | 121.0637 | R | 1859 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.78 | 0.01 | Line: BAUAN - SAN JOSE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2694
3 | 695 | 2695 | 1380601049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 49 | 14.6166 | 120.9738 | U | 2183 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.93 | 79.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.97 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2695
3 | 696 | 2696 | 1380200001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Almanza Uno | 14.4319 | 121.0133 | U | 36785 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | A - Node within 0.5 km | 0.5 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2696
3 | 697 | 2697 | 0704624002 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Bairan | 10.3946 | 123.2925 | R | 635 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.69 | 2.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | E - Nearest node or line 3-5 km | 4.69 | 12.51 | Node: VHN001-BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2697
3 | 698 | 2698 | 1380601075 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 75 | 14.6132 | 120.9639 | U | 1391 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.48 | 10.12 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.55 | 0.61 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2698
3 | 699 | 2699 | PH0002699 | NCR | Metro Manila | Caloocan City | Barangay 151 | 14.6257 | 120.9769 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.78 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | A - Node within 0.5 km | 0.41 | 0.11 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2699
3 | 700 | 2700 | PH0002700 | CAR | Benguet | Baguio City | Sanitary Camp, South | 16.4206 | 120.6009 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.72 | 0.78 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.92 | 0.92 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2700
3 | 701 | 2701 | 1903620037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Paigoay | 17.2539 | 122.2281 | R | 883 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | F - Nearest node and line over 5 km | 29.28 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2701
3 | 702 | 2702 | 1380614090 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 897 | 14.5881 | 121.0206 | U | 2232 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 2.22 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | B - Node 0.5-1 km | 0.94 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2702
3 | 703 | 2703 | 1908713017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Ranao Pilayan | 17.254 | 122.2281 | R | 2384 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.23 | 48.4 | 69.23 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2703
3 | 704 | 2704 | 1380605020 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 318 | 14.6101 | 120.9848 | U | 762 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.58 | 6.83 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | B - Node 0.5-1 km | 0.74 | 0.13 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2704
3 | 705 | 2705 | 1380601190 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 190 | 14.6375 | 120.9775 | U | 1269 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.4 | 33.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | D - Other node or line within 3 km | 1.27 | 0.55 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2705
3 | 706 | 2706 | 0806007059 | Region VIII (Eastern Visayas) | Samar | Gandara | Palambrag | 12.0817 | 124.8634 | R | 256 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.99 | 88.95 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 88.99 | 88.95 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2706
3 | 707 | 2707 | 0806007002 | Region VIII (Eastern Visayas) | Samar | Gandara | Balocawe | 12.1329 | 124.7625 | R | 363 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 89.51 | 89.5 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 89.51 | 89.47 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2707
3 | 708 | 2708 | 0806013019 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Manaing | 11.4956 | 125.0623 | R | 311 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.2 | 32.01 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 29.2 | 32 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2708
3 | 709 | 2709 | 0806007099 | Region VIII (Eastern Visayas) | Samar | Gandara | Hetebac | 12.0403 | 124.8123 | R | 267 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.09 | 84.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 83.43 | 83.39 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2709
3 | 710 | 2710 | 0990101023 | Region IX (Zamboanga Peninsula) | City of Isabela (Not a Province) | City of Isabela | Lampinigan | 6.6873 | 121.8776 | R | 1811 | 4.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.92 | 32.92 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 32.92 | 32.92 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2710
3 | 711 | 2711 | 0806007024 | Region VIII (Eastern Visayas) | Samar | Gandara | Caranas | 12.0144 | 124.8104 | R | 255 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.75 | 84.72 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | F - Nearest node and line over 5 km | 80.55 | 80.52 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2711
3 | 712 | 2712 | 1380610054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 740 | 14.5657 | 121.007 | U | 4264 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.3 | 33.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | C - Line within 0.5 km; node over 1 km | 1.54 | 0.25 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2712
3 | 713 | 2713 | 1380606151 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 545 | 14.6141 | 121.0057 | U | 910 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.37 | 34.57 | Tier 2 High GIDA (Score 40.0–49.9) | 69.22 | 48.39 | 69.22 |  | A - Node within 0.5 km | 0.41 | 0.2 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2713
3 | 714 | 2714 | 1908803005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Abdullah Sangki | Maganoy | 17.2552 | 122.2292 | R | 2909 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.39 | 69.21 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2714
3 | 715 | 2715 | PH0002715 | BARMM (LaMa+SGA) | Lanao Del Sur | Sultan Gumander (Picong) | Tuca | 17.2547 | 122.2287 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.39 | 69.21 |  | F - Nearest node and line over 5 km | 29.39 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2715
3 | 716 | 2716 | 0806007085 | Region VIII (Eastern Visayas) | Samar | Gandara | Senibaran | 12.085 | 124.8945 | R | 89 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.14 | 83.11 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.39 | 69.21 |  | F - Nearest node and line over 5 km | 90.13 | 90.08 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2716
3 | 717 | 2717 | 1380606148 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 542 | 14.6131 | 121.0027 | U | 826 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.72 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.39 | 69.21 |  | A - Node within 0.5 km | 0.26 | 0.17 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2717
3 | 718 | 2718 | 1380601245 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 244 | 14.6092 | 120.9782 | U | 659 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.94 | 62.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.39 | 69.21 |  | B - Node 0.5-1 km | 0.95 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2718
3 | 719 | 2719 | 1908819007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Panadtaban | 17.2552 | 122.2292 | R | 2997 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.38 | 69.21 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2719
3 | 720 | 2720 | 1380500015 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Mabini-J. Rizal | 14.5855 | 121.0212 | U | 8625 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.77 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.21 | 48.38 | 69.21 |  | B - Node 0.5-1 km | 0.77 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2720
3 | 721 | 2721 | PH0002721 | NCR | Metro Manila | Caloocan City | Barangay 148 | 14.6322 | 120.9658 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.5 | 73.82 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | D - Other node or line within 3 km | 1.01 | 0.94 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2721
3 | 722 | 2722 | 1380611018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 684 | 14.5799 | 120.9935 | U | 2813 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.11 | 38.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | B - Node 0.5-1 km | 0.87 | 0.17 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2722
3 | 723 | 2723 | 1208005012 | Region XII (SOCCSKSARGEN) | Sarangani | Maitum | Pangi | 6.0413 | 124.5203 | R | 1121 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.3 | 56.9 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | F - Nearest node and line over 5 km | 57.3 | 56.9 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2723
3 | 724 | 2724 | 1380606083 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 477 | 14.613 | 120.9935 | U | 1077 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.71 | 9.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.23 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2724
3 | 725 | 2725 | 1380606028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 422 | 14.6057 | 121.0022 | U | 2374 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.65 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | A - Node within 0.5 km | 0.47 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2725
3 | 726 | 2726 | PH0002726 | NCR | Metro Manila | Caloocan City | Barangay 37 | 14.6021 | 120.9615 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.54 | 4.65 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | B - Node 0.5-1 km | 0.92 | 1.02 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2726
3 | 727 | 2727 | 0600409004 | Region VI (Western Visayas) | Aklan | Libacao | Bonza | 11.4803 | 122.3303 | R | 431 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.86 | 9.78 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | F - Nearest node and line over 5 km | 9.86 | 9.78 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2727
3 | 728 | 2728 | 1908702008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Kulimpang | 17.2541 | 122.2281 | R | 5281 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2728
3 | 729 | 2729 | 1908812003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Guindulungan | Datalpandan | 17.2554 | 122.23 | R | 2245 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.92 | 25.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.38 | 69.2 |  | F - Nearest node and line over 5 km | 29.55 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2729
3 | 730 | 2730 | PH0002730 | I | Ilocos Norte | Laoag City | Bgy. No. 15, San Guillermo (Pob.) | 18.1495 | 120.5329 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.63 | 1.63 | Tier 2 High GIDA (Score 40.0–49.9) | 69.2 | 48.37 | 69.2 |  | F - Nearest node and line over 5 km | 6.8 | 5.32 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2730
3 | 731 | 2731 | 1380604014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 281 | 14.5978 | 120.9709 | U | 2357 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.41 | 1.04 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | D - Other node or line within 3 km | 1.01 | 0.91 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2731
3 | 732 | 2732 | 1908824010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Linamunan | 17.2551 | 122.2291 | R | 3100 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2732
3 | 733 | 2733 | 1003515023 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Rarab | 7.7977 | 123.9238 | R | 1019 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.96 | 20.79 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | F - Nearest node and line over 5 km | 30.54 | 20.32 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2733
3 | 734 | 2734 | PH0002734 | CAR | Benguet | Baguio City | Kagitingan | 16.4177 | 120.6159 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.85 | 1.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | C - Line within 0.5 km; node over 1 km | 1.74 | 0.02 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2734
3 | 735 | 2735 | 1003515013 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Lupitan | 7.7818 | 123.8874 | R | 883 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.05 | 19.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | F - Nearest node and line over 5 km | 30.62 | 18.13 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2735
3 | 736 | 2736 | 1003515014 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Mangan | 7.7872 | 123.9109 | R | 797 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.38 | 17.81 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | F - Nearest node and line over 5 km | 30.98 | 19.78 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2736
3 | 737 | 2737 | 1380606023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 417 | 14.6052 | 121.0031 | U | 2072 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 66.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | A - Node within 0.5 km | 0.38 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2737
3 | 738 | 2738 | 1380611032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 818 | 14.5804 | 121.0027 | U | 1430 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.28 | 16.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.19 | 48.37 | 69.19 |  | A - Node within 0.5 km | 0.44 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2738
3 | 739 | 2739 | 1102508018 | Region XI (Davao Region) | Davao Oriental | Manay | Lambog | 7.228 | 126.4478 | R | 836 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.77 | 38.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | F - Nearest node and line over 5 km | 39.77 | 38.28 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2739
3 | 740 | 2740 | PH0002740 | NCR | Metro Manila | Caloocan City | Barangay 146 | 14.63 | 120.9654 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.32 | 27.92 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | B - Node 0.5-1 km | 0.92 | 0.84 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2740
3 | 741 | 2741 | 1900708002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Akbar | Linongan | 6.7296 | 122.2563 | R | 3410 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.46 | 28.29 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | F - Nearest node and line over 5 km | 28.46 | 28.27 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2741
3 | 742 | 2742 | PH0002742 | III | Pampanga | Angeles City | Lourdes Sur East | 15.1445 | 120.5936 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | B - Node 0.5-1 km | 0.81 | 0.21 | Line: ANGELES | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2742
3 | 743 | 2743 | 1903619028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Mulondo | Lilod | 17.2549 | 122.2284 | R | 642 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.46 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | F - Nearest node and line over 5 km | 29.38 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2743
3 | 744 | 2744 | 1908823010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Papakan | 17.2551 | 122.2293 | R | 1662 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2744
3 | 745 | 2745 | PH0002745 | BARMM (LaMa+SGA) | Lanao Del Sur | Sultan Gumander (Picong) | Torogan | 17.2545 | 122.228 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.9 | 33.63 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.37 | 69.18 |  | F - Nearest node and line over 5 km | 29.32 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2745
3 | 746 | 2746 | 0402106072 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis II | 14.3043 | 121.019 | R | 4565 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 1.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | D - Other node or line within 3 km | 2.57 | 3.42 | Node: CRC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 2746
3 | 747 | 2747 | 0907311014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Gusom | 7.6992 | 123.0878 | R | 823 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.96 | 4.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | E - Nearest node or line 3-5 km | 4.96 | 4.15 | Line: PAGADIAN - BUUG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2747
3 | 748 | 2748 | 1380606154 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 548 | 14.6152 | 121.0041 | U | 772 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.12 | 7.63 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | A - Node within 0.5 km | 0.47 | 0.34 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2748
3 | 749 | 2749 | 1908804007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Tulunan | 17.2552 | 122.2292 | R | 2657 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2749
3 | 750 | 2750 | 1900703027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Canibungan | 6.5946 | 121.8954 | R | 2486 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.82 | 55.96 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | F - Nearest node and line over 5 km | 40.25 | 40.25 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2750
3 | 751 | 2751 | 0907313011 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Luanan | 7.7181 | 123.15 | R | 522 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.54 | 4.48 | Tier 2 High GIDA (Score 40.0–49.9) | 69.18 | 48.36 | 69.18 |  | E - Nearest node or line 3-5 km | 10.55 | 4.48 | Line: PAGADIAN - BUUG | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2751
3 | 752 | 2752 | 1900712006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Muhtamad | Palahangan | 6.8343 | 121.5526 | R | 2792 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.42 | 57.42 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 58.15 | 58.15 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2752
3 | 753 | 2753 | PH0002753 | CAR | Benguet | Baguio City | Bagong Lipunan | 16.4195 | 120.5876 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 2.2 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | B - Node 0.5-1 km | 0.5 | 0.62 | Node: BGC002 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2753
3 | 754 | 2754 | 1908823011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Tugal | 17.2558 | 122.2295 | R | 1115 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 29.53 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2754
3 | 755 | 2755 | PH0002755 | BARMM (LaMa+SGA) | Lanao Del Sur | Sultan Gumander (Picong) | Mimbalawag | 17.2538 | 122.2278 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.24 | 35.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 29.25 | 34.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2755
3 | 756 | 2756 | 1900710010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Mohammad Ajul | Sulutan Matangal | 17.2542 | 122.2282 | R | 2295 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.21 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 29.31 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2756
3 | 757 | 2757 | 1900712001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Muhtamad | Baluk-baluk | 6.8337 | 121.5535 | R | 2284 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.25 | 58.25 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 58.06 | 58.06 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2757
3 | 758 | 2758 | 0401015014 | Region IV-A (CALABARZON) | Batangas | Lobo | Malalim Na Sanog | 13.687 | 121.2718 | R | 255 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 19.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 8.02 | 16.27 | Node: LBB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2758
3 | 759 | 2759 | 1003515011 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Cabasaran | 7.7976 | 123.9235 | R | 732 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.84 | 22.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 30.53 | 20.3 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2759
3 | 760 | 2760 | 1380612026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 858 | 14.5888 | 121.0028 | U | 685 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.19 | 25.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | A - Node within 0.5 km | 0.49 | 0.09 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2760
3 | 761 | 2761 | 0907324008 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | San Miguel | Dumalian | 7.7227 | 123.2407 | R | 742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.47 | 9.03 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 20.47 | 9.03 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2761
3 | 762 | 2762 | 1900709013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Al-Barka | Lookbisaya | 6.4776 | 122.1898 | R | 1994 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.35 | 20.12 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | F - Nearest node and line over 5 km | 49.79 | 49.79 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2762
3 | 763 | 2763 | 1380606043 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 437 | 14.6044 | 120.9986 | U | 926 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.99 | 55.09 | Tier 2 High GIDA (Score 40.0–49.9) | 69.17 | 48.36 | 69.17 |  | B - Node 0.5-1 km | 0.69 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2763
3 | 764 | 2764 | 1908712003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Talitay | Kiladap | 17.2551 | 122.2291 | R | 3337 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2764
3 | 765 | 2765 | PH0002765 | VIII | Leyte | Tacloban City | Barangay 42-A | 11.2377 | 125 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.51 | 4.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | A - Node within 0.5 km | 0.34 | 2.97 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2765
3 | 766 | 2766 | 1381100155 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 155 | 14.5371 | 121.0092 | U | 942 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | D - Other node or line within 3 km | 1.43 | 0.62 | Line: Existing 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2766
3 | 767 | 2767 | 1380614077 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 884 | 14.586 | 121.0168 | U | 2283 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.81 | 10.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.19 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2767
3 | 768 | 2768 | 1908824003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Boboguiron | 17.2546 | 122.2294 | R | 1076 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.23 | 40.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 29.44 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2768
3 | 769 | 2769 | 0907220026 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sirawai | Pisa Itom | 7.601 | 122.1275 | R | 470 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.11 | 20.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 33.13 | 26.32 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2769
3 | 770 | 2770 | 1003515002 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Bangco | 7.7869 | 123.91 | R | 767 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.08 | 17.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 30.98 | 19.72 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2770
3 | 771 | 2771 | 1003515005 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Dimayon | 7.7823 | 123.8889 | R | 821 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 19.87 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 30.62 | 18.22 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2771
3 | 772 | 2772 | 1903620035 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Padas | 17.2538 | 122.2278 | R | 1363 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 29.25 | 34.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2772
3 | 773 | 2773 | 1903628017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Guiarong | 17.2548 | 122.2285 | R | 796 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 29.38 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2773
3 | 774 | 2774 | 1900704004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Maluso | Guanan North | 6.5483 | 121.866 | R | 1300 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.34 | 46.33 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 46.34 | 46.33 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2774
3 | 775 | 2775 | 1900703031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Lawi-lawi | 6.5956 | 121.809 | R | 1301 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.6 | 45.6 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 45.6 | 45.6 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2775
3 | 776 | 2776 | 1900703021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Suba-an | 6.616 | 121.8163 | R | 622 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.35 | 43.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 43.35 | 43.34 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2776
3 | 777 | 2777 | 1908820006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Aguak | Malingao | 17.2551 | 122.2292 | R | 1043 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.38 | 51.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2777
3 | 778 | 2778 | 1380606053 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 447 | 14.6063 | 120.9962 | U | 1498 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.9 | 36.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | B - Node 0.5-1 km | 0.65 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2778
3 | 779 | 2779 | 1900703026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Calugusan | 6.8242 | 121.5452 | R | 963 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.96 | 57.13 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | F - Nearest node and line over 5 km | 59.13 | 59.13 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2779
3 | 780 | 2780 | 1380606231 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 624 | 14.5897 | 121.0175 | U | 1472 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6 | 13.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.16 | 48.35 | 69.16 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.43 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2780
3 | 781 | 2781 | 1380611039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 824 | 14.5816 | 121.0004 | U | 1342 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.33 | 75.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.35 | 69.15 |  | A - Node within 0.5 km | 0.4 | 0.3 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2781
3 | 782 | 2782 | 1900709016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Al-Barka | Sangkahan | 6.4733 | 122.1512 | R | 1392 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.38 | 21.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.35 | 69.15 |  | F - Nearest node and line over 5 km | 49.35 | 49.34 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2782
3 | 783 | 2783 | 1903620045 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Rangiran | 17.2547 | 122.2286 | R | 862 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.89 | 33.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.35 | 69.15 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2783
3 | 784 | 2784 | 0806007041 | Region VIII (Eastern Visayas) | Samar | Gandara | Hinayagan | 12.1297 | 124.8392 | R | 376 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 93.72 | 93.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.35 | 69.15 |  | F - Nearest node and line over 5 km | 93.72 | 93.69 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2784
3 | 785 | 2785 | 1381100096 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 96 | 14.5387 | 121.0018 | U | 849 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.42 | 15.5 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.11 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2785
3 | 786 | 2786 | 1380606211 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 604 | 14.5937 | 121.0155 | U | 1522 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.89 | 20.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | D - Other node or line within 3 km | 1.5 | 0.9 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2786
3 | 787 | 2787 | 1900712005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Hadji Muhtamad | Mananggal | 6.6598 | 121.5877 | R | 1278 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.81 | 56.81 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 60.47 | 60.47 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2787
3 | 788 | 2788 | PH0002788 | BARMM (LaMa+SGA) | Maguindanao del Norte | Cotabato City | Rosary Heights IV | 7.2131 | 124.2456 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.82 | 59.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 60.82 | 59.85 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2788
3 | 789 | 2789 | 1900703004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Bulanza | 6.6495 | 121.8702 | R | 1099 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.69 | 36.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 36.69 | 36.68 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2789
3 | 790 | 2790 | 0806007076 | Region VIII (Eastern Visayas) | Samar | Gandara | San Isidro | 12.1278 | 124.8233 | R | 426 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 93.22 | 93.18 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 93.22 | 93.18 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2790
3 | 791 | 2791 | PH0002791 | NCR | Metro Manila | Caloocan City | Barangay 153 | 14.628 | 120.9774 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.28 | 69.25 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | A - Node within 0.5 km | 0.45 | 0.14 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2791
3 | 792 | 2792 | 1900703037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Calayan | 6.5877 | 121.8459 | R | 710 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.82 | 43.82 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 43.82 | 43.82 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2792
3 | 793 | 2793 | 0806007035 | Region VIII (Eastern Visayas) | Samar | Gandara | Giaboc | 12.1209 | 124.8404 | R | 211 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 92.78 | 92.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 92.78 | 92.74 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2793
3 | 794 | 2794 | PH0002794 | XI | Davao Del Sur | Davao City | Barangay 4-A (Pob.) | 7.0707 | 125.6099 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | A - Node within 0.5 km | 0.41 | 0.31 | Line: DAVAO CITY - TRENTO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2794
3 | 795 | 2795 | 1900703036 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Luuk-Maluha | 6.667 | 121.8699 | R | 1462 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.15 | 56.07 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 35.2 | 35.19 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2795
3 | 796 | 2796 | 1381300063 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Masagana | 9.2298 | 117.9965 | U | 4341 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 98.8 | 100.81 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2796
3 | 797 | 2797 | 0806007091 | Region VIII (Eastern Visayas) | Samar | Gandara | Tigbawon | 12.0927 | 124.8424 | R | 250 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.01 | 84.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 89.73 | 89.69 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2797
3 | 798 | 2798 | 1900703029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Lantawan | Landugan | 6.5905 | 121.8318 | R | 811 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.48 | 44.48 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 44.48 | 44.48 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2798
3 | 799 | 2799 | 1381100068 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 68 | 14.5458 | 120.9971 | U | 876 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.25 | 2.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | A - Node within 0.5 km | 0.32 | 0.21 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2799
3 | 800 | 2800 | 0907220010 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sirawai | Danganon | 7.587 | 122.1391 | R | 638 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.89 | 24.6 | Tier 2 High GIDA (Score 40.0–49.9) | 69.15 | 48.34 | 69.15 |  | F - Nearest node and line over 5 km | 31.89 | 24.48 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2800
3 | 801 | 2801 | PH0002801 | VII | Cebu | Talisay City | Tangke | 10.2505 | 123.8594 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.3 | 11.1 | Tier 2 High GIDA (Score 40.0–49.9) | 69.14 | 48.34 | 69.14 |  | C - Line within 0.5 km; node over 1 km | 2.41 | 0.01 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2801
3 | 802 | 2802 | 1380612003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 835 | 14.5904 | 121.015 | U | 2788 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.46 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 69.14 | 48.34 | 69.14 |  | D - Other node or line within 3 km | 1.48 | 0.67 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2802
3 | 803 | 2803 | 1381100077 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 77 | 14.5412 | 120.9949 | U | 1138 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.14 | 5.04 | Tier 2 High GIDA (Score 40.0–49.9) | 69.14 | 48.34 | 69.14 |  | A - Node within 0.5 km | 0.38 | 0.02 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2803
3 | 804 | 2804 | 1380601193 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 193 | 14.6339 | 120.9805 | U | 1009 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.57 | 2.53 | Tier 2 High GIDA (Score 40.0–49.9) | 69.14 | 48.34 | 69.14 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2804
3 | 805 | 2805 | 1380605051 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 349 | 14.6212 | 120.984 | U | 812 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.47 | 22.24 | Tier 2 High GIDA (Score 40.0–49.9) | 69.14 | 48.33 | 69.14 |  | B - Node 0.5-1 km | 0.54 | 0.11 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2805
3 | 806 | 2806 | PH0002806 | NCR | Metro Manila | Caloocan City | Barangay 32 | 14.6035 | 120.9627 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.84 | 6.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.13 | 48.33 | 69.13 |  | B - Node 0.5-1 km | 0.83 | 0.84 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2806
3 | 807 | 2807 | 1380606157 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 551 | 14.6162 | 121.0024 | U | 988 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.12 | 47.74 | Tier 2 High GIDA (Score 40.0–49.9) | 69.13 | 48.33 | 69.13 |  | B - Node 0.5-1 km | 0.6 | 0.37 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2807
3 | 808 | 2808 | PH0002808 | NCR | Metro Manila | Caloocan City | Barangay 11 | 14.6071 | 120.966 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11 | 10.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.13 | 48.33 | 69.13 |  | A - Node within 0.5 km | 0.39 | 0.35 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2808
3 | 809 | 2809 | 1381100154 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 154 | 14.5343 | 121.0072 | U | 764 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.21 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 69.13 | 48.33 | 69.13 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.38 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2809
3 | 810 | 2810 | 1381100114 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 114 | 14.5447 | 121.0031 | U | 1080 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.77 | 5.65 | Tier 2 High GIDA (Score 40.0–49.9) | 69.12 | 48.32 | 69.12 |  | B - Node 0.5-1 km | 0.93 | 0.38 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2810
3 | 811 | 2811 | PH0002811 | IV-A | Cavite | City of Bacoor | Real | 14.3884 | 120.9845 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.12 | 48.32 | 69.12 |  | D - Other node or line within 3 km | 1.03 | 5.27 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 2811
3 | 812 | 2812 | 1381100102 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 102 | 14.5463 | 121.0029 | U | 849 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.29 | 14.37 | Tier 2 High GIDA (Score 40.0–49.9) | 69.12 | 48.32 | 69.12 |  | B - Node 0.5-1 km | 0.94 | 0.21 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2812
3 | 813 | 2813 | PH0002813 | NCR | Metro Manila | Caloocan City | Barangay 152 | 14.6292 | 120.9748 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.36 | 36.43 | Tier 2 High GIDA (Score 40.0–49.9) | 69.11 | 48.32 | 69.11 |  | A - Node within 0.5 km | 0.3 | 0.29 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2813
3 | 814 | 2814 | 1380606159 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 553 | 14.6138 | 121.0029 | U | 1473 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.4 | 28.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.11 | 48.31 | 69.11 |  | A - Node within 0.5 km | 0.33 | 0.24 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2814
3 | 815 | 2815 | PH0002815 | NCR | Metro Manila | Caloocan City | Barangay 155 | 14.6256 | 120.9732 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.09 | 19.68 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.31 | 69.1 |  | A - Node within 0.5 km | 0.14 | 0 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2815
3 | 816 | 2816 | 1380606089 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 483 | 14.6105 | 120.9949 | U | 1411 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.07 | 3.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.31 | 69.1 |  | B - Node 0.5-1 km | 0.91 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2816
3 | 817 | 2817 | 1380606004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 398 | 14.6004 | 120.9848 | U | 3161 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.97 | 47.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.31 | 69.1 |  | B - Node 0.5-1 km | 0.76 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2817
3 | 818 | 2818 | 1380606164 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 558 | 14.602 | 121.0043 | U | 1298 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.23 | 52.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.31 | 69.1 |  | A - Node within 0.5 km | 0.02 | 0.01 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2818
3 | 819 | 2819 | 1380614066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 873 | 14.5836 | 121.0083 | U | 1286 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.66 | 5.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.3 | 69.1 |  | B - Node 0.5-1 km | 0.61 | 0.35 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2819
3 | 820 | 2820 | 1380601257 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 256 | 14.6134 | 120.9763 | U | 1061 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.66 | 14.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.1 | 48.3 | 69.1 |  | B - Node 0.5-1 km | 0.79 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2820
3 | 821 | 2821 | 1380606161 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 555 | 14.6056 | 121.006 | U | 1173 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.48 | 13.92 | Tier 2 High GIDA (Score 40.0–49.9) | 69.09 | 48.3 | 69.09 |  | A - Node within 0.5 km | 0.42 | 0.32 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2821
3 | 822 | 2822 | PH0002822 | XI | Davao Del Sur | Davao City | Barangay 9-A (Pob.) | 7.0725 | 125.6085 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.09 | 48.3 | 69.09 |  | B - Node 0.5-1 km | 0.66 | 0.05 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2822
3 | 823 | 2823 | 0806016030 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Panaruan | 12.0634 | 124.6942 | R | 120 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.91 | 84.71 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.3 | 69.08 |  | F - Nearest node and line over 5 km | 84.91 | 84.71 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2823
3 | 824 | 2824 | 1380601188 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 188 | 14.6353 | 120.977 | U | 891 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.16 | 77.55 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.3 | 69.08 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.49 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2824
3 | 825 | 2825 | 0907311027 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Suminalum | 7.8343 | 123.1256 | R | 1109 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.98 | 5.89 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | F - Nearest node and line over 5 km | 13.98 | 5.88 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2825
3 | 826 | 2826 | 1380610048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 733 | 14.5723 | 120.9914 | U | 4434 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.39 | 15.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | A - Node within 0.5 km | 0.31 | 0.12 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2826
3 | 827 | 2827 | 1380606169 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 563 | 14.6053 | 121.0078 | U | 1572 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | B - Node 0.5-1 km | 0.5 | 0.35 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2827
3 | 828 | 2828 | 1381100121 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 121 | 14.5496 | 121.0079 | U | 1036 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 1.34 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | A - Node within 0.5 km | 0.38 | 0.09 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2828
3 | 829 | 2829 | PH0002829 | NCR | Metro Manila | Caloocan City | Barangay 157 | 14.6676 | 121.0016 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.44 | 74.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | D - Other node or line within 3 km | 1.14 | 0.65 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 2829
3 | 830 | 2830 | 1380601074 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 74 | 14.6144 | 120.966 | U | 1071 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.65 | 10.93 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | B - Node 0.5-1 km | 0.54 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2830
3 | 831 | 2831 | 1380601212 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 211 | 14.6275 | 120.9812 | U | 2068 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.08 | 43.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | B - Node 0.5-1 km | 0.85 | 0.2 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2831
3 | 832 | 2832 | 1380614074 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 881 | 14.585 | 121.0138 | U | 2396 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.7 | 23.76 | Tier 2 High GIDA (Score 40.0–49.9) | 69.08 | 48.29 | 69.08 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.25 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2832
3 | 833 | 2833 | PH0002833 | NCR | Metro Manila | Caloocan City | Barangay 42 | 14.6157 | 120.9699 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.98 | 4.05 | Tier 2 High GIDA (Score 40.0–49.9) | 69.07 | 48.29 | 69.07 |  | B - Node 0.5-1 km | 0.81 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2833
3 | 834 | 2834 | 1380606078 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 472 | 14.6097 | 120.9947 | U | 1156 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.81 | 44.27 | Tier 2 High GIDA (Score 40.0–49.9) | 69.07 | 48.29 | 69.07 |  | B - Node 0.5-1 km | 0.83 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2834
3 | 835 | 2835 | 1380606039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 433 | 14.6045 | 120.9977 | U | 478 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.9 | 3.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.07 | 48.29 | 69.07 |  | B - Node 0.5-1 km | 0.72 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2835
3 | 836 | 2836 | 1381100095 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 95 | 14.5394 | 121.0032 | U | 1164 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 3.5 | Tier 2 High GIDA (Score 40.0–49.9) | 69.07 | 48.29 | 69.07 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.2 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2836
3 | 837 | 2837 | 1380614023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 767 | 14.5658 | 121.0061 | U | 5594 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.59 | 72.13 | Tier 2 High GIDA (Score 40.0–49.9) | 69.06 | 48.28 | 69.06 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.23 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2837
3 | 838 | 2838 | 1380606182 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 576 | 14.6027 | 121.0124 | U | 3712 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.4 | 33.54 | Tier 2 High GIDA (Score 40.0–49.9) | 69.06 | 48.28 | 69.06 |  | B - Node 0.5-1 km | 0.85 | 0.01 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2838
3 | 839 | 2839 | 1381100125 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 125 | 14.5468 | 121.0056 | U | 1551 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.33 | 10.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.06 | 48.28 | 69.06 |  | B - Node 0.5-1 km | 0.71 | 0.28 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2839
3 | 840 | 2840 | PH0002840 | NCR | Metro Manila | Caloocan City | Barangay 56 | 14.6103 | 120.9709 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.63 | 21.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.06 | 48.28 | 69.06 |  | A - Node within 0.5 km | 0.41 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2840
3 | 841 | 2841 | 1380606152 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 546 | 14.6129 | 121.0036 | U | 919 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.63 | 9.69 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.28 | 69.05 |  | A - Node within 0.5 km | 0.22 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2841
3 | 842 | 2842 | PH0002842 | NCR | Metro Manila | Caloocan City | Barangay 150 | 14.6298 | 120.9663 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.64 | 94.17 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | B - Node 0.5-1 km | 0.83 | 0.75 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2842
3 | 843 | 2843 | 1408103017 | Cordillera Administrative Region (CAR) | Apayao | Flora | Upper Atok | 18.0813 | 121.3552 | R | 315 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.06 | 1.21 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | F - Nearest node and line over 5 km | 5.06 | 25.27 | Node: PLY002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2843
3 | 844 | 2844 | PH0002844 | IV-B | Palawan | Puerto Princesa City | Pagkakaisa (Pob.) | 9.8543 | 118.7051 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.41 | 5.36 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | D - Other node or line within 3 km | 3.73 | 2.82 | Line: TAYTAY - PUERTO PRINCESA | Route options survey candidate: compare actual node lateral with approved line tap. | 2844
3 | 845 | 2845 | 1380605001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 297 | 14.6106 | 120.9948 | U | 2066 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.01 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | B - Node 0.5-1 km | 0.92 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2845
3 | 846 | 2846 | PH0002846 | NCR | Metro Manila | Caloocan City | Barangay 97 | 14.6258 | 120.96 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.26 | 13.72 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | B - Node 0.5-1 km | 0.92 | 1.33 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2846
3 | 847 | 2847 | 0401008015 | Region IV-A (CALABARZON) | Batangas | Calatagan | Paraiso | 13.9132 | 120.6679 | R | 1422 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3 | 3 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | D - Other node or line within 3 km | 3 | 3 | Node: CTG002 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 2847
3 | 848 | 2848 | 1380601248 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 247 | 14.6102 | 120.9766 | U | 759 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.6 | 7.97 | Tier 2 High GIDA (Score 40.0–49.9) | 69.05 | 48.27 | 69.05 |  | B - Node 0.5-1 km | 0.84 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2848
3 | 849 | 2849 | 1380606049 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 443 | 14.6065 | 121 | U | 1424 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.66 | 55.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.27 | 69.04 |  | B - Node 0.5-1 km | 0.64 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2849
3 | 850 | 2850 | 1380612036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 870 | 14.5826 | 121.0053 | U | 3142 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.54 | 24.78 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.27 | 69.04 |  | A - Node within 0.5 km | 0.34 | 0.32 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2850
3 | 851 | 2851 | 1380605082 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 379 | 14.6278 | 120.986 | U | 674 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.46 | 7.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.27 | 69.04 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.12 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2851
3 | 852 | 2852 | 1380614060 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 804 | 14.5786 | 121.0042 | U | 1289 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.05 | 32.98 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.26 | 69.04 |  | B - Node 0.5-1 km | 0.66 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2852
3 | 853 | 2853 | 1380614045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 789 | 14.5698 | 120.9995 | U | 1669 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.75 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.26 | 69.04 |  | B - Node 0.5-1 km | 0.62 | 0.43 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2853
3 | 854 | 2854 | 1380606116 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 510 | 14.62 | 120.9971 | U | 1168 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.43 | 30 | Tier 2 High GIDA (Score 40.0–49.9) | 69.04 | 48.26 | 69.04 |  | D - Other node or line within 3 km | 1.23 | 0.64 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2854
3 | 855 | 2855 | 1381100088 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 88 | 14.5452 | 120.9965 | U | 985 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.23 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 69.03 | 48.26 | 69.03 |  | A - Node within 0.5 km | 0.23 | 0.24 | Node: PSY022 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2855
3 | 856 | 2856 | 1381100168 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 168 | 14.5344 | 121.0065 | U | 536 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 69.03 | 48.26 | 69.03 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.3 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2856
3 | 857 | 2857 | 1381701010 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Tabacalera | 14.5476 | 121.0678 | U | 2895 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 69.03 | 48.26 | 69.03 |  | A - Node within 0.5 km | 0.33 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2857
3 | 858 | 2858 | 1381300004 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Aurora | 14.6161 | 121.0084 | U | 4398 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.03 | 48.26 | 69.03 |  | B - Node 0.5-1 km | 0.75 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2858
3 | 859 | 2859 | 1380601223 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 222 | 14.6248 | 120.9827 | U | 2102 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.68 | 10.11 | Tier 2 High GIDA (Score 40.0–49.9) | 69.03 | 48.26 | 69.03 |  | B - Node 0.5-1 km | 0.93 | 0.03 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2859
3 | 860 | 2860 | PH0002860 | IV-A | Cavite | Imus City | Mariano Espeleta III | 14.4077 | 120.9352 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.1 | 1.08 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | B - Node 0.5-1 km | 0.59 | 4.44 | Node: IMC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2860
3 | 861 | 2861 | PH0002861 | IV-A | Batangas | Lipa City | San Sebastian | 13.9351 | 121.1549 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | C - Line within 0.5 km; node over 1 km | 1.61 | 0.16 | Line: TANAUAN - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2861
3 | 862 | 2862 | 1380606104 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 498 | 14.622 | 120.9924 | U | 1064 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.1 | 70.49 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | D - Other node or line within 3 km | 1.2 | 0.52 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2862
3 | 863 | 2863 | 0803726005 | Region VIII (Eastern Visayas) | Leyte | Kananga | Libertad | 11.2277 | 124.5419 | R | 2021 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.21 | 3.31 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | E - Nearest node or line 3-5 km | 5.21 | 3.31 | Line: ORMOC CLS - CAPOOCAN | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2863
3 | 864 | 2864 | 1380604015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 282 | 14.5978 | 120.9727 | U | 2533 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20 | 19.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | D - Other node or line within 3 km | 1.05 | 0.88 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 2864
3 | 865 | 2865 | 1380606179 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 573 | 14.6026 | 121.0054 | U | 976 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.25 | 3.67 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | A - Node within 0.5 km | 0.11 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2865
3 | 866 | 2866 | 1380601077 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 77 | 14.6108 | 120.9644 | U | 1414 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.66 | 2.86 | Tier 2 High GIDA (Score 40.0–49.9) | 69.02 | 48.25 | 69.02 |  | B - Node 0.5-1 km | 0.72 | 0.51 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2866
3 | 867 | 2867 | 1380606112 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 506 | 14.6201 | 120.9962 | U | 688 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.04 | 31.94 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.25 | 69.01 |  | D - Other node or line within 3 km | 1.31 | 0.68 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2867
3 | 868 | 2868 | 1907010002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Lookan Banaran | 5.0126 | 120.1272 | R | 2578 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.25 | 69.01 |  | F - Nearest node and line over 5 km | 301.44 | 301.44 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2868
3 | 869 | 2869 | 1381100060 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 60 | 14.5511 | 120.9993 | U | 1466 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.85 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | B - Node 0.5-1 km | 0.85 | 0.14 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2869
3 | 870 | 2870 | 1380606190 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 584 | 14.6024 | 121.0095 | U | 3515 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.31 | 38.88 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | B - Node 0.5-1 km | 0.54 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2870
3 | 871 | 2871 | 1380611004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 664-A | 14.5841 | 120.9836 | U | 659 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.57 | 38.51 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | B - Node 0.5-1 km | 0.73 | 0.46 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2871
3 | 872 | 2872 | 1380606163 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 557 | 14.6032 | 121.0064 | U | 1300 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.95 | 2.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | A - Node within 0.5 km | 0.24 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2872
3 | 873 | 2873 | 1380300012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | La Paz | 14.5694 | 121.0067 | U | 3122 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.38 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2873
3 | 874 | 2874 | PH0002874 | NCR | Metro Manila | Caloocan City | Barangay 149 | 14.631 | 120.9684 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.33 | 56.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69.01 | 48.24 | 69.01 |  | B - Node 0.5-1 km | 0.71 | 0.65 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2874
3 | 875 | 2875 | 1380614046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 790 | 14.5686 | 120.9974 | U | 1794 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.12 | 57.28 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | B - Node 0.5-1 km | 0.51 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2875
3 | 876 | 2876 | 1380611014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 680 | 14.58 | 120.9972 | U | 997 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.51 | 47.4 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | B - Node 0.5-1 km | 0.77 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2876
3 | 877 | 2877 | 1381100136 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 136 | 14.5493 | 121.0072 | U | 2229 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.94 | 2.12 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | A - Node within 0.5 km | 0.46 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2877
3 | 878 | 2878 | PH0002878 | NCR | Metro Manila | Caloocan City | Barangay 70 | 14.6145 | 120.9651 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.51 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | A - Node within 0.5 km | 0.46 | 0.51 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2878
3 | 879 | 2879 | 1380606111 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 505 | 14.6229 | 120.9963 | U | 1236 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.74 | 6.61 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | D - Other node or line within 3 km | 1.55 | 0.78 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2879
3 | 880 | 2880 | 1606810010 | Region XIII (Caraga) | Surigao del Sur | Lanuza | Mampi | 17.105 | 122.2741 | R | 940 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.53 | 37.62 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | F - Nearest node and line over 5 km | 27.53 | 37.6 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2880
3 | 881 | 2881 | 1380606181 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 575 | 14.6048 | 121.0058 | U | 1038 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.07 | 9.52 | Tier 2 High GIDA (Score 40.0–49.9) | 69 | 48.24 | 69 |  | A - Node within 0.5 km | 0.34 | 0.26 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2881
3 | 882 | 2882 | 0405619042 | Region IV-A (CALABARZON) | Quezon | Gumaca | San Isidro Kanluran | 13.8999 | 122.2066 | R | 192 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 1.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.99 | 48.23 | 68.99 |  | C - Line within 0.5 km; node over 1 km | 6.16 | 0.18 | Line: GCQ001 TO TKQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2882
3 | 883 | 2883 | 1381100070 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 70 | 14.5442 | 120.9957 | U | 2262 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.15 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 68.99 | 48.23 | 68.99 |  | A - Node within 0.5 km | 0.15 | 0.15 | Node: PSY022 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2883
3 | 884 | 2884 | 1380610030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 715 | 14.5707 | 120.9873 | U | 185 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.85 | 5.32 | Tier 2 High GIDA (Score 40.0–49.9) | 68.99 | 48.23 | 68.99 |  | B - Node 0.5-1 km | 0.76 | 0.45 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2884
3 | 885 | 2885 | 1381100162 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 162 | 14.5353 | 121.0065 | U | 1952 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 68.99 | 48.23 | 68.99 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.31 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2885
3 | 886 | 2886 | 1381100027 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 27 | 14.6169 | 120.9825 | U | 281 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 1.07 | Tier 2 High GIDA (Score 40.0–49.9) | 68.99 | 48.23 | 68.99 |  | A - Node within 0.5 km | 0.06 | 0 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2886
3 | 887 | 2887 | PH0002887 | NCR | Metro Manila | Caloocan City | Barangay 8 | 14.6107 | 120.9677 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.29 | 31.73 | Tier 2 High GIDA (Score 40.0–49.9) | 68.98 | 48.22 | 68.98 |  | A - Node within 0.5 km | 0.48 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2887
3 | 888 | 2888 | 1380606011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 405 | 14.6056 | 120.988 | U | 1029 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.69 | 67.41 | Tier 2 High GIDA (Score 40.0–49.9) | 68.98 | 48.22 | 68.98 |  | A - Node within 0.5 km | 0.44 | 0 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2888
3 | 889 | 2889 | 0405622079 | Region IV-A (CALABARZON) | Quezon | Lopez | Santo Niño Ilaya | 13.8893 | 122.2245 | R | 1087 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.04 | 6.19 | Tier 2 High GIDA (Score 40.0–49.9) | 68.97 | 48.22 | 68.97 |  | C - Line within 0.5 km; node over 1 km | 4.07 | 0.13 | Line: GCQ001 TO TKQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2889
3 | 890 | 2890 | PH0002890 | NCR | Metro Manila | Caloocan City | Barangay 52 | 14.6462 | 120.977 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.31 | 66.21 | Tier 2 High GIDA (Score 40.0–49.9) | 68.97 | 48.21 | 68.97 |  | B - Node 0.5-1 km | 0.56 | 0.62 | Node: CCS004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2890
3 | 891 | 2891 | 1380601089 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 89 | 14.6165 | 120.9685 | U | 742 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.03 | 23.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.96 | 48.21 | 68.96 |  | B - Node 0.5-1 km | 0.65 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2891
3 | 892 | 2892 | 1380606216 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 609 | 14.597 | 121.019 | U | 1078 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.96 | 48.21 | 68.96 |  | D - Other node or line within 3 km | 1.65 | 0.75 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2892
3 | 893 | 2893 | 1380606110 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 504 | 14.6241 | 120.9938 | U | 1352 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.32 | 18.15 | Tier 2 High GIDA (Score 40.0–49.9) | 68.96 | 48.21 | 68.96 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.47 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2893
3 | 894 | 2894 | PH0002894 | CAR | Benguet | Baguio City | Magsaysay, Upper | 16.431 | 120.582 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.26 | 1.49 | Tier 2 High GIDA (Score 40.0–49.9) | 68.96 | 48.21 | 68.96 |  | D - Other node or line within 3 km | 1.38 | 1.54 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 2894
3 | 895 | 2895 | PH0002895 | NCR | Metro Manila | Caloocan City | Barangay 17 | 14.6029 | 120.9617 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.3 | 37.85 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.21 | 68.95 |  | B - Node 0.5-1 km | 0.96 | 0.97 | Node: MNL005- TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2895
3 | 896 | 2896 | 1380606014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 408 | 14.6066 | 120.991 | U | 1822 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.03 | 55.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.2 | 68.95 |  | A - Node within 0.5 km | 0.39 | 0.05 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2896
3 | 897 | 2897 | 1380606144 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 538 | 14.6132 | 121.0018 | U | 846 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.86 | 14.53 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.2 | 68.95 |  | A - Node within 0.5 km | 0.33 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2897
3 | 898 | 2898 | 1381100071 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 71 | 14.5436 | 120.9962 | U | 704 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.38 | 5.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.2 | 68.95 |  | A - Node within 0.5 km | 0.22 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2898
3 | 899 | 2899 | 1380606005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 399 | 14.6035 | 120.9913 | U | 1100 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.52 | 45.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.2 | 68.95 |  | A - Node within 0.5 km | 0.04 | 0 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2899
3 | 900 | 2900 | 1380606174 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 568 | 14.6039 | 121.0066 | U | 1903 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.56 | 4.74 | Tier 2 High GIDA (Score 40.0–49.9) | 68.95 | 48.2 | 68.95 |  | A - Node within 0.5 km | 0.3 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2900
3 | 901 | 2901 | 1381100026 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 26 | 14.6176 | 120.9805 | U | 959 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.84 | 19.29 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.2 | 68.94 |  | A - Node within 0.5 km | 0.29 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2901
3 | 902 | 2902 | 1380606064 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 458 | 14.6126 | 120.9916 | U | 1506 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.47 | 68.2 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.2 | 68.94 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2902
3 | 903 | 2903 | 1380606158 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 552 | 14.615 | 121.005 | U | 965 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.23 | 30.03 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.2 | 68.94 |  | A - Node within 0.5 km | 0.47 | 0.33 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2903
3 | 904 | 2904 | 1380606055 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 449 | 14.6039 | 120.9967 | U | 1445 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.36 | 4.57 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.2 | 68.94 |  | B - Node 0.5-1 km | 0.6 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2904
3 | 905 | 2905 | 1380606137 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 531 | 14.617 | 121.0026 | U | 985 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.05 | 7.38 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.19 | 68.94 |  | B - Node 0.5-1 km | 0.68 | 0.32 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2905
3 | 906 | 2906 | PH0002906 | NCR | Metro Manila | Caloocan City | Barangay 98 | 14.6246 | 120.9626 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.68 | 9.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.94 | 48.19 | 68.94 |  | B - Node 0.5-1 km | 0.74 | 1.07 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2906
3 | 907 | 2907 | 1380614085 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 892 | 14.5857 | 121.014 | U | 1179 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.2 | 16.9 | Tier 2 High GIDA (Score 40.0–49.9) | 68.93 | 48.19 | 68.93 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.31 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2907
3 | 908 | 2908 | 1380605070 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 367 | 14.6282 | 120.9833 | U | 1760 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.34 | 44.69 | Tier 2 High GIDA (Score 40.0–49.9) | 68.93 | 48.19 | 68.93 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.02 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2908
3 | 909 | 2909 | 1380606165 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 559 | 14.6054 | 121.0069 | U | 1324 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.7 | 34.26 | Tier 2 High GIDA (Score 40.0–49.9) | 68.93 | 48.19 | 68.93 |  | A - Node within 0.5 km | 0.45 | 0.37 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2909
3 | 910 | 2910 | 1380606166 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 560 | 14.6042 | 121.0048 | U | 1136 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.16 | 1.74 | Tier 2 High GIDA (Score 40.0–49.9) | 68.93 | 48.19 | 68.93 |  | A - Node within 0.5 km | 0.24 | 0.13 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2910
3 | 911 | 2911 | 1380606170 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 564 | 14.6041 | 121.0057 | U | 1473 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.34 | 41.64 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | A - Node within 0.5 km | 0.26 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2911
3 | 912 | 2912 | 1380614076 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 883 | 14.5826 | 121.0143 | U | 2266 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.9 | 61.63 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | C - Line within 0.5 km; node over 1 km | 1.25 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2912
3 | 913 | 2913 | 1380614061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 805 | 14.5774 | 121.0021 | U | 1275 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.36 | 3.47 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | B - Node 0.5-1 km | 0.78 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2913
3 | 914 | 2914 | 0806013007 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Canlobo | 11.5182 | 125.1119 | R | 387 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.2 | 35.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | F - Nearest node and line over 5 km | 33.2 | 35.78 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2914
3 | 915 | 2915 | 1380614010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 753 | 14.5687 | 121.0076 | U | 2452 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.41 | 23.02 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | C - Line within 0.5 km; node over 1 km | 1.48 | 0.04 | Line: UG 288C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2915
3 | 916 | 2916 | 1380606093 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 487 | 14.6103 | 120.9912 | U | 1501 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.03 | 9.92 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | B - Node 0.5-1 km | 0.8 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2916
3 | 917 | 2917 | 1380606092 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 486 | 14.6115 | 120.9933 | U | 998 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.97 | 67.99 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | B - Node 0.5-1 km | 0.96 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2917
3 | 918 | 2918 | PH0002918 | VII | Cebu | Cebu City | Kalubihan (Pob.) | 10.3206 | 123.884 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.25 | 4.73 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | D - Other node or line within 3 km | 1.8 | 1.36 | Line: 96c | Route options survey candidate: compare actual node lateral with approved line tap. | 2918
3 | 919 | 2919 | 1705208070 | MIMAROPA Region | Oriental Mindoro | Naujan | Caburo | 13.1675 | 121.1461 | R | 470 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.49 | 14.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.92 | 48.18 | 68.92 |  | F - Nearest node and line over 5 km | 14.49 | 14.18 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2919
3 | 920 | 2920 | PH0002920 | III | Nueva Ecija | Cabanatuan City | M. S. Garcia | 15.4772 | 120.9631 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.54 | 0.55 | Tier 2 High GIDA (Score 40.0–49.9) | 68.91 | 48.18 | 68.91 |  | B - Node 0.5-1 km | 0.54 | 0.43 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2920
3 | 921 | 2921 | 1380605072 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 369 | 14.6305 | 120.9838 | U | 1438 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.94 | 22.92 | Tier 2 High GIDA (Score 40.0–49.9) | 68.91 | 48.17 | 68.91 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.16 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2921
3 | 922 | 2922 | 1380400013 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Niugan | 14.6675 | 120.955 | U | 7370 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 68.9 | 48.17 | 68.9 |  | B - Node 0.5-1 km | 0.87 | 0.38 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2922
3 | 923 | 2923 | 1380606115 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 509 | 14.6212 | 120.9945 | U | 1298 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.27 | 4.07 | Tier 2 High GIDA (Score 40.0–49.9) | 68.9 | 48.17 | 68.9 |  | D - Other node or line within 3 km | 1.36 | 0.73 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2923
3 | 924 | 2924 | 1380601246 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 245 | 14.6126 | 120.9761 | U | 290 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 2.81 | Tier 2 High GIDA (Score 40.0–49.9) | 68.9 | 48.17 | 68.9 |  | B - Node 0.5-1 km | 0.84 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2924
3 | 925 | 2925 | 1380608001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 659 | 14.5854 | 120.9848 | U | 372 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.03 | 42.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68.9 | 48.17 | 68.9 |  | B - Node 0.5-1 km | 0.58 | 0.29 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2925
3 | 926 | 2926 | 1380606145 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 539 | 14.6167 | 121.0044 | U | 1902 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.73 | 30.28 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | B - Node 0.5-1 km | 0.64 | 0.18 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2926
3 | 927 | 2927 | 1380601256 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 255 | 14.6099 | 120.9784 | U | 1119 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.47 | 48.54 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | B - Node 0.5-1 km | 0.87 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2927
3 | 928 | 2928 | 1380604001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 268 | 14.6246 | 120.9859 | U | 504 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.9 | 2.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | B - Node 0.5-1 km | 0.96 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2928
3 | 929 | 2929 | 1380601191 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 191 | 14.6363 | 120.98 | U | 724 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.83 | 67.58 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.25 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2929
3 | 930 | 2930 | 1380601076 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 76 | 14.612 | 120.9665 | U | 1900 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.56 | 42.84 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | B - Node 0.5-1 km | 0.67 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2930
3 | 931 | 2931 | 1381300099 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Isidro Labrador | 14.6929 | 121.0429 | U | 6509 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | D - Other node or line within 3 km | 1.3 | 1.17 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2931
3 | 932 | 2932 | 1380606131 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 525 | 14.6122 | 121.0008 | U | 1838 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.45 | 1.91 | Tier 2 High GIDA (Score 40.0–49.9) | 68.89 | 48.16 | 68.89 |  | A - Node within 0.5 km | 0.35 | 0.09 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2932
3 | 933 | 2933 | 1380300014 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Olympia | 14.5729 | 121.0218 | U | 9178 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.88 | 48.16 | 68.88 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.04 | Line: UG 288C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2933
3 | 934 | 2934 | PH0002934 | NCR | Metro Manila | Caloocan City | Barangay 156 | 14.629 | 120.9757 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.09 | 67.49 | Tier 2 High GIDA (Score 40.0–49.9) | 68.88 | 48.15 | 68.88 |  | A - Node within 0.5 km | 0.35 | 0.25 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2934
3 | 935 | 2935 | 0802604046 | Region VIII (Eastern Visayas) | Eastern Samar | City of Borongan | San Andres | 11.6405 | 125.383 | R | 382 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.89 | 62.45 | Tier 2 High GIDA (Score 40.0–49.9) | 68.88 | 48.15 | 68.88 |  | F - Nearest node and line over 5 km | 60.89 | 62.64 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2935
3 | 936 | 2936 | 1380606122 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 516 | 14.6221 | 120.9984 | U | 1120 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.63 | 5.2 | Tier 2 High GIDA (Score 40.0–49.9) | 68.87 | 48.15 | 68.87 |  | D - Other node or line within 3 km | 1.36 | 0.68 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 2936
3 | 937 | 2937 | 1380606046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 440 | 14.6054 | 120.997 | U | 1034 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.32 | 3.9 | Tier 2 High GIDA (Score 40.0–49.9) | 68.87 | 48.15 | 68.87 |  | B - Node 0.5-1 km | 0.67 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2937
3 | 938 | 2938 | 1906607002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Bakud | 17.2551 | 122.2299 | R | 1483 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.03 | 33.75 | Tier 2 High GIDA (Score 40.0–49.9) | 68.87 | 48.15 | 68.87 |  | F - Nearest node and line over 5 km | 29.51 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2938
3 | 939 | 2939 | 1381300098 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Isidro | 7.6907 | 125.0662 | U | 6825 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 68.86 | 48.14 | 68.86 |  | E - Nearest node or line 3-5 km | 5.41 | 4.3 | Line: DAMULOG - VALENCIA - QUEZON | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 2939
3 | 940 | 2940 | 1908706009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Lower Taviran | 17.254 | 122.2282 | R | 4891 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 68.86 | 48.14 | 68.86 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2940
3 | 941 | 2941 | 1381300136 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Capri | 14.7272 | 121.1171 | U | 13444 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.84 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | C - Line within 0.5 km; node over 1 km | 2.53 | 0.06 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2941
3 | 942 | 2942 | 0102934008 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barangay VI | 17.5697 | 120.4255 | R | 1370 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.48 | 1.5 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | D - Other node or line within 3 km | 4.57 | 2.33 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 2942
3 | 943 | 2943 | 1380611026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 812 | 14.5785 | 121.0023 | U | 1755 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.23 | 55.87 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | B - Node 0.5-1 km | 0.66 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2943
3 | 944 | 2944 | 1380601249 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 248 | 14.609 | 120.9745 | U | 518 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.55 | 30.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | B - Node 0.5-1 km | 0.58 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2944
3 | 945 | 2945 | 1380606126 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 520 | 14.6197 | 120.9953 | U | 650 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 1.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | D - Other node or line within 3 km | 1.34 | 0.67 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2945
3 | 946 | 2946 | PH0002946 | NCR | Metro Manila | Caloocan City | Barangay 59 | 14.6158 | 120.969 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.01 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | B - Node 0.5-1 km | 0.72 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2946
3 | 947 | 2947 | 1380606105 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 499 | 14.6208 | 120.995 | U | 1543 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.3 | 25.64 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | D - Other node or line within 3 km | 1.39 | 0.79 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2947
3 | 948 | 2948 | 1380605028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 326 | 14.6143 | 120.9822 | U | 850 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.21 | 66.62 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | A - Node within 0.5 km | 0.25 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2948
3 | 949 | 2949 | 1380606125 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 519 | 14.6163 | 120.9974 | U | 1351 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.32 | 9.32 | Tier 2 High GIDA (Score 40.0–49.9) | 68.85 | 48.13 | 68.85 |  | B - Node 0.5-1 km | 0.91 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2949
3 | 950 | 2950 | 1380614044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 788 | 14.5806 | 121.0107 | U | 998 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.03 | 38.2 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.13 | 68.84 |  | B - Node 0.5-1 km | 0.95 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2950
3 | 951 | 2951 | 1381100100 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 100 | 14.5393 | 121.003 | U | 1258 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.11 | 5.06 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.13 | 68.84 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.19 | Line: Existing 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2951
3 | 952 | 2952 | 1380605066 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 364 | 14.552 | 120.9946 | U | 2045 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.53 | 2.58 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.13 | 68.84 |  | A - Node within 0.5 km | 0.34 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2952
3 | 953 | 2953 | 1380606177 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 571 | 14.605 | 121.0049 | U | 2161 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.23 | 61.92 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.13 | 68.84 |  | A - Node within 0.5 km | 0.33 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2953
3 | 954 | 2954 | 1380500018 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Namayan | 14.5803 | 121.0186 | U | 8393 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.13 | 68.84 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.46 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2954
3 | 955 | 2955 | 1381100045 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 45 | 14.5575 | 120.9967 | U | 1720 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 2.97 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.12 | 68.84 |  | B - Node 0.5-1 km | 0.71 | 0.04 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2955
3 | 956 | 2956 | 1381100025 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 25 | 14.6183 | 120.9819 | U | 612 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 4.65 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.12 | 68.84 |  | A - Node within 0.5 km | 0.23 | 0.1 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2956
3 | 957 | 2957 | 1380606094 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 488 | 14.62 | 120.9948 | U | 807 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.69 | 29.13 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.12 | 68.84 |  | D - Other node or line within 3 km | 1.35 | 0.73 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2957
3 | 958 | 2958 | 1380606106 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 500 | 14.6242 | 120.9929 | U | 2640 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 1.23 | Tier 2 High GIDA (Score 40.0–49.9) | 68.84 | 48.12 | 68.84 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.38 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2958
3 | 959 | 2959 | PH0002959 | CAR | Benguet | Baguio City | Aurora Hill Proper | 16.4073 | 120.5834 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 0.82 | Tier 2 High GIDA (Score 40.0–49.9) | 68.83 | 48.12 | 68.83 |  | B - Node 0.5-1 km | 0.89 | 0.13 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2959
3 | 960 | 2960 | 1380605018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 316 | 14.6079 | 120.9844 | U | 854 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.28 | 10.39 | Tier 2 High GIDA (Score 40.0–49.9) | 68.83 | 48.12 | 68.83 |  | B - Node 0.5-1 km | 0.9 | 0.16 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2960
3 | 961 | 2961 | PH0002961 | NCR | Metro Manila | Caloocan City | Barangay 128 | 14.6133 | 120.9608 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.22 | 87.21 | Tier 2 High GIDA (Score 40.0–49.9) | 68.83 | 48.12 | 68.83 |  | B - Node 0.5-1 km | 0.56 | 0.95 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2961
3 | 962 | 2962 | PH0002962 | NCR | Metro Manila | Caloocan City | Barangay 75 | 14.6132 | 120.9639 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.12 | 3.13 | Tier 2 High GIDA (Score 40.0–49.9) | 68.82 | 48.12 | 68.82 |  | B - Node 0.5-1 km | 0.55 | 0.61 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2962
3 | 963 | 2963 | 1380606073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 467 | 14.6111 | 120.9913 | U | 1195 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.66 | 28.27 | Tier 2 High GIDA (Score 40.0–49.9) | 68.82 | 48.11 | 68.82 |  | B - Node 0.5-1 km | 0.88 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2963
3 | 964 | 2964 | PH0002964 | III | Pampanga | Angeles City | Pulungbulu | 15.1363 | 120.5945 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 68.82 | 48.11 | 68.82 |  | B - Node 0.5-1 km | 0.91 | 0.15 | Line: 72 CORE (6X12) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2964
3 | 965 | 2965 | 1380606143 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 537 | 14.6147 | 121.0039 | U | 1118 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.98 | 34.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.82 | 48.11 | 68.82 |  | A - Node within 0.5 km | 0.42 | 0.34 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2965
3 | 966 | 2966 | 1380614048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 792 | 14.5708 | 120.9979 | U | 2637 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.38 | 43.07 | Tier 2 High GIDA (Score 40.0–49.9) | 68.82 | 48.11 | 68.82 |  | A - Node within 0.5 km | 0.41 | 0.22 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2966
3 | 967 | 2967 | 1380605064 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 362 | 14.5544 | 120.9942 | U | 260 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.26 | 2.07 | Tier 2 High GIDA (Score 40.0–49.9) | 68.81 | 48.11 | 68.81 |  | A - Node within 0.5 km | 0.29 | 0.07 | Line: Existing 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2967
3 | 968 | 2968 | 1102315029 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Francisco | 7.3033 | 125.6813 | U | 14187 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.32 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 68.81 | 48.1 | 68.81 |  | A - Node within 0.5 km | 0.32 | 0.03 | Line: DAVAO CITY - TRENTO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2968
3 | 969 | 2969 | 1380601051 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 51 | 14.6189 | 120.9743 | U | 2658 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.37 | 51.5 | Tier 2 High GIDA (Score 40.0–49.9) | 68.81 | 48.1 | 68.81 |  | B - Node 0.5-1 km | 0.89 | 0.18 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2969
3 | 970 | 2970 | 1380606091 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 485 | 14.6127 | 120.9954 | U | 1378 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.7 | 56.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | B - Node 0.5-1 km | 0.93 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2970
3 | 971 | 2971 | PH0002971 | IV-A | Laguna | San Pablo City | Barangay V-B (Pob.) | 17.469 | 121.7897 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 1.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | C - Line within 0.5 km; node over 1 km | 3.56 | 0.46 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2971
3 | 972 | 2972 | 1380601252 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 251 | 14.6101 | 120.9775 | U | 1217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 2.72 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | B - Node 0.5-1 km | 0.92 | 0.16 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2972
3 | 973 | 2973 | 1380606153 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 547 | 14.6164 | 121.0062 | U | 1091 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.78 | 19.3 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | B - Node 0.5-1 km | 0.65 | 0.19 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2973
3 | 974 | 2974 | 1380614080 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 887 | 14.5824 | 121.0152 | U | 685 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.86 | 14.43 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | C - Line within 0.5 km; node over 1 km | 1.35 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2974
3 | 975 | 2975 | 1380606218 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 611 | 14.5946 | 121.0148 | U | 833 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.68 | 29.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.8 | 48.1 | 68.8 |  | D - Other node or line within 3 km | 1.38 | 0.9 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 2975
3 | 976 | 2976 | PH0002976 | NCR | Metro Manila | Caloocan City | Barangay 47 | 14.619 | 120.9734 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.42 | 34.86 | Tier 2 High GIDA (Score 40.0–49.9) | 68.79 | 48.09 | 68.79 |  | B - Node 0.5-1 km | 0.87 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2976
3 | 977 | 2977 | 1380606006 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 400 | 14.6069 | 120.9892 | U | 1550 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.49 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.79 | 48.09 | 68.79 |  | A - Node within 0.5 km | 0.47 | 0.17 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2977
3 | 978 | 2978 | PH0002978 | CAR | Benguet | Baguio City | Guisad Central | 16.4267 | 120.5946 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 68.79 | 48.09 | 68.79 |  | A - Node within 0.5 km | 0.15 | 1.34 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2978
3 | 979 | 2979 | 0300803005 | Region III (Central Luzon) | Bataan | City of Balanga | Cataning | 14.6603 | 120.4939 | U | 10211 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.15 | 2.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.79 | 48.09 | 68.79 |  | D - Other node or line within 3 km | 5.15 | 2.68 | Line: Bagac-Pilar AERIAL | Route options survey candidate: compare actual node lateral with approved line tap. | 2979
3 | 980 | 2980 | 1380606129 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 523 | 14.6099 | 121.0004 | U | 1149 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.34 | 9.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.78 | 48.09 | 68.78 |  | A - Node within 0.5 km | 0.38 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2980
3 | 981 | 2981 | 1380614027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 771 | 14.5739 | 121.01 | U | 1868 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.79 | 54.55 | Tier 2 High GIDA (Score 40.0–49.9) | 68.78 | 48.08 | 68.78 |  | C - Line within 0.5 km; node over 1 km | 1.4 | 0.07 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2981
3 | 982 | 2982 | 0405619043 | Region IV-A (CALABARZON) | Quezon | Gumaca | San Isidro Silangan | 13.8394 | 122.0551 | R | 91 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.59 | 2.04 | Tier 2 High GIDA (Score 40.0–49.9) | 68.78 | 48.08 | 68.78 |  | C - Line within 0.5 km; node over 1 km | 5.49 | 0.14 | Line: LCQ001 TO MCQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2982
3 | 983 | 2983 | 1380614100 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 808 | 14.5785 | 121.0005 | U | 2249 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.57 | 22.92 | Tier 2 High GIDA (Score 40.0–49.9) | 68.78 | 48.08 | 68.78 |  | B - Node 0.5-1 km | 0.7 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2983
3 | 984 | 2984 | 1380605031 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 329 | 14.6053 | 120.9791 | U | 452 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.3 | 53.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68.78 | 48.08 | 68.78 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2984
3 | 985 | 2985 | PH0002985 | CAR | Benguet | Baguio City | Trancoville | 16.4208 | 120.6015 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 1.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.77 | 48.08 | 68.77 |  | B - Node 0.5-1 km | 0.95 | 0.98 | Node: BGC003 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2985
3 | 986 | 2986 | 1380601265 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 264 | 14.6248 | 120.985 | U | 2517 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.77 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.77 | 48.08 | 68.77 |  | B - Node 0.5-1 km | 0.95 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2986
3 | 987 | 2987 | 1380610046 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 731 | 14.5701 | 120.9909 | U | 3005 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.44 | 61.97 | Tier 2 High GIDA (Score 40.0–49.9) | 68.77 | 48.07 | 68.77 |  | A - Node within 0.5 km | 0.42 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 2987
3 | 988 | 2988 | PH0002988 | NCR | Metro Manila | Caloocan City | Barangay 63 | 14.612 | 120.9664 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.93 | 79.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.76 | 48.07 | 68.76 |  | B - Node 0.5-1 km | 0.68 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2988
3 | 989 | 2989 | PH0002989 | CAR | Benguet | Baguio City | Modern Site, West | 16.4061 | 120.5846 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.09 | 2.86 | Tier 2 High GIDA (Score 40.0–49.9) | 68.76 | 48.07 | 68.76 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.05 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 2989
3 | 990 | 2990 | 1380614068 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 875 | 14.5812 | 121.0088 | U | 1053 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.99 | 39.85 | Tier 2 High GIDA (Score 40.0–49.9) | 68.76 | 48.07 | 68.76 |  | B - Node 0.5-1 km | 0.74 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2990
3 | 991 | 2991 | 1380611015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 681 | 14.5799 | 120.9953 | U | 1127 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 1.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.75 | 48.07 | 68.75 |  | B - Node 0.5-1 km | 0.88 | 0.13 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2991
3 | 992 | 2992 | 1380610023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 708 | 14.5698 | 120.9881 | U | 776 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.45 | 2.04 | Tier 2 High GIDA (Score 40.0–49.9) | 68.75 | 48.06 | 68.75 |  | B - Node 0.5-1 km | 0.71 | 0.38 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2992
3 | 993 | 2993 | 1380602004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 290 | 14.596 | 120.9693 | U | 1126 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.54 | 14.94 | Tier 2 High GIDA (Score 40.0–49.9) | 68.75 | 48.06 | 68.75 |  | B - Node 0.5-1 km | 0.88 | 1.11 | Node: MNL068 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2993
3 | 994 | 2994 | 1380606101 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 495 | 14.6209 | 120.9941 | U | 1964 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.12 | 43.91 | Tier 2 High GIDA (Score 40.0–49.9) | 68.75 | 48.06 | 68.75 |  | D - Other node or line within 3 km | 1.3 | 0.72 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2994
3 | 995 | 2995 | 1380606138 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 532 | 14.6158 | 121.0051 | U | 1017 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.68 | 39.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.75 | 48.06 | 68.75 |  | B - Node 0.5-1 km | 0.55 | 0.25 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2995
3 | 996 | 2996 | 1380606210 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 603 | 14.5949 | 121.0176 | U | 734 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.29 | 1.48 | Tier 2 High GIDA (Score 40.0–49.9) | 68.74 | 48.06 | 68.74 |  | D - Other node or line within 3 km | 1.62 | 0.84 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 2996
3 | 997 | 2997 | 1380608015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 664 | 14.5841 | 120.9836 | U | 470 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 59.82 | 34.8 | Tier 2 High GIDA (Score 40.0–49.9) | 68.74 | 48.06 | 68.74 |  | B - Node 0.5-1 km | 0.73 | 0.46 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2997
3 | 998 | 2998 | 1907009006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Maraning | 17.2558 | 122.2298 | R | 1937 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 68.74 | 48.05 | 68.74 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 2998
3 | 999 | 2999 | 1380606036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 430 | 14.6035 | 120.9994 | U | 523 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.23 | 71.03 | Tier 2 High GIDA (Score 40.0–49.9) | 68.74 | 48.05 | 68.74 |  | B - Node 0.5-1 km | 0.58 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 2999
3 | 1000 | 3000 | 1380606117 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 511 | 14.6188 | 120.995 | U | 1379 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.03 | 11.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.73 | 48.05 | 68.73 |  | D - Other node or line within 3 km | 1.29 | 0.6 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3000

## Batch 4 (3,001 - 4,000)
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA — Batch 4 (3,001 - 4,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
4 | 1 | 3001 | PH0003001 | CAR | Benguet | Baguio City | Andres Bonifacio | 16.4161 | 120.5742 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 68.73 | 48.05 | 68.73 |  | A - Node within 0.5 km | 0.4 | 0.32 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3001
4 | 2 | 3002 | 1380614019 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 763 | 14.5678 | 121.0055 | U | 1833 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.02 | 32.4 | Tier 2 High GIDA (Score 40.0–49.9) | 68.73 | 48.05 | 68.73 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.04 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3002
4 | 3 | 3003 | 1380606050 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 444 | 14.6053 | 120.9979 | U | 970 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.03 | 2.96 | Tier 2 High GIDA (Score 40.0–49.9) | 68.73 | 48.05 | 68.73 |  | B - Node 0.5-1 km | 0.76 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3003
4 | 4 | 3004 | 1380606226 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 619 | 14.5886 | 121.0173 | U | 1322 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.52 | 58.44 | Tier 2 High GIDA (Score 40.0–49.9) | 68.72 | 48.05 | 68.72 |  | C - Line within 0.5 km; node over 1 km | 1.28 | 0.36 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3004
4 | 5 | 3005 | 1380606135 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 529 | 14.612 | 120.9971 | U | 963 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.56 | 31.41 | Tier 2 High GIDA (Score 40.0–49.9) | 68.72 | 48.04 | 68.72 |  | B - Node 0.5-1 km | 0.73 | 0.11 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3005
4 | 6 | 3006 | PH0003006 | CAR | Benguet | Baguio City | Rizal Monument Area | 16.414 | 120.5902 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 68.72 | 48.04 | 68.72 |  | A - Node within 0.5 km | 0.18 | 0.06 | Line: BAGUIO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3006
4 | 7 | 3007 | 1903601013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Ilian | 17.2549 | 122.2293 | R | 1174 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 68.72 | 48.04 | 68.72 |  | F - Nearest node and line over 5 km | 29.45 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3007
4 | 8 | 3008 | 0102934020 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Mindoro | 17.5599 | 120.3518 | R | 1575 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.55 | 4.8 | Tier 2 High GIDA (Score 40.0–49.9) | 68.72 | 48.04 | 68.72 |  | E - Nearest node or line 3-5 km | 5.55 | 4.52 | Line: SEGMENT 3 (VIGAN - BATAC) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3008
4 | 9 | 3009 | 1380614089 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 896 | 14.5893 | 121.018 | U | 1303 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.48 | 5.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.04 | 68.71 |  | C - Line within 0.5 km; node over 1 km | 1.25 | 0.35 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3009
4 | 10 | 3010 | 1380601238 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 237 | 14.6254 | 120.9838 | U | 466 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.93 | 7.95 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.04 | 68.71 |  | B - Node 0.5-1 km | 1 | 0.08 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3010
4 | 11 | 3011 | 1380606120 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 514 | 14.6198 | 120.998 | U | 2352 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.74 | 40.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.04 | 68.71 |  | D - Other node or line within 3 km | 1.17 | 0.61 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3011
4 | 12 | 3012 | 1903601014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Lama | 17.2542 | 122.2291 | U | 917 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.04 | 68.71 |  | F - Nearest node and line over 5 km | 29.39 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3012
4 | 13 | 3013 | 1380606051 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 445 | 14.6041 | 120.9958 | U | 959 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.21 | 24.59 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.04 | 68.71 |  | B - Node 0.5-1 km | 0.51 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3013
4 | 14 | 3014 | 1380606155 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 549 | 14.614 | 121.002 | U | 893 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.95 | 52.69 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.03 | 68.71 |  | A - Node within 0.5 km | 0.39 | 0.28 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3014
4 | 15 | 3015 | 1380606140 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 534 | 14.6134 | 121.0056 | U | 1129 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.16 | 2.6 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.03 | 68.71 |  | A - Node within 0.5 km | 0.33 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3015
4 | 16 | 3016 | 1380611023 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 809 | 14.5773 | 121.003 | U | 1225 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.14 | 62.21 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.03 | 68.71 |  | B - Node 0.5-1 km | 0.79 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3016
4 | 17 | 3017 | 1380606173 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 567 | 14.6051 | 121.0087 | U | 2388 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.25 | 52.6 | Tier 2 High GIDA (Score 40.0–49.9) | 68.71 | 48.03 | 68.71 |  | B - Node 0.5-1 km | 0.56 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3017
4 | 18 | 3018 | 1380610035 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 720 | 14.5693 | 120.9908 | U | 1276 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.03 | 6.25 | Tier 2 High GIDA (Score 40.0–49.9) | 68.7 | 48.03 | 68.7 |  | A - Node within 0.5 km | 0.48 | 0.13 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3018
4 | 19 | 3019 | 1380606029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 423 | 14.6073 | 121.0045 | U | 1347 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.25 | 14.88 | Tier 2 High GIDA (Score 40.0–49.9) | 68.7 | 48.03 | 68.7 |  | A - Node within 0.5 km | 0.41 | 0.41 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3019
4 | 20 | 3020 | 0205009012 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Kakiduguen | 16.2223 | 121.379 | R | 1165 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.84 | 29.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.7 | 48.03 | 68.7 |  | F - Nearest node and line over 5 km | 13.84 | 29.07 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3020
4 | 21 | 3021 | 1380606156 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 550 | 14.6128 | 121.0045 | U | 1022 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.99 | 12.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.7 | 48.03 | 68.7 |  | A - Node within 0.5 km | 0.22 | 0.16 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3021
4 | 22 | 3022 | 1380610005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 690 | 14.5779 | 120.992 | U | 511 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.47 | 58.48 | Tier 2 High GIDA (Score 40.0–49.9) | 68.69 | 48.02 | 68.69 |  | B - Node 0.5-1 km | 0.7 | 0.08 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3022
4 | 23 | 3023 | 1380605026 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 324 | 14.6121 | 120.9818 | U | 623 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.08 | 37.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.02 | 68.68 |  | B - Node 0.5-1 km | 0.51 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3023
4 | 24 | 3024 | PH0003024 | NCR | Metro Manila | Caloocan City | Barangay 147 | 14.6647 | 120.995 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.78 | 1.89 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.02 | 68.68 |  | B - Node 0.5-1 km | 0.73 | 1.17 | Node: CCS005 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3024
4 | 25 | 3025 | PH0003025 | NCR | Metro Manila | Caloocan City | Barangay 74 | 14.657 | 120.9775 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.68 | 31.94 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.02 | 68.68 |  | B - Node 0.5-1 km | 1 | 0.11 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3025
4 | 26 | 3026 | 0907216017 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Paniran | 7.248 | 121.9873 | R | 934 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.17 | 26.63 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.02 | 68.68 |  | F - Nearest node and line over 5 km | 30.17 | 26.59 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3026
4 | 27 | 3027 | PH0003027 | NCR | Metro Manila | Caloocan City | Barangay 101 | 14.6257 | 120.9609 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.48 | 15.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.01 | 68.68 |  | B - Node 0.5-1 km | 0.88 | 1.23 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3027
4 | 28 | 3028 | 1380601192 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 192 | 14.6351 | 120.9779 | U | 1935 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.11 | 5.03 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.01 | 68.68 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.4 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3028
4 | 29 | 3029 | 1380606183 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 577 | 14.6015 | 121.0103 | U | 1015 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.69 | 18.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.01 | 68.68 |  | B - Node 0.5-1 km | 0.62 | 0.1 | Line: UG 144C via V-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3029
4 | 30 | 3030 | PH0003030 | NCR | Metro Manila | Caloocan City | Barangay 129 | 14.6406 | 120.988 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.06 | 31.53 | Tier 2 High GIDA (Score 40.0–49.9) | 68.68 | 48.01 | 68.68 |  | B - Node 0.5-1 km | 0.96 | 0.48 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3030
4 | 31 | 3031 | 1381300015 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Blue Ridge A | 14.7283 | 121.0668 | U | 1598 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 1.03 | Tier 2 High GIDA (Score 40.0–49.9) | 68.67 | 48.01 | 68.67 |  | B - Node 0.5-1 km | 0.62 | 0.59 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3031
4 | 32 | 3032 | 1380606149 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 543 | 14.6165 | 121.0053 | U | 847 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.05 | 66.81 | Tier 2 High GIDA (Score 40.0–49.9) | 68.67 | 48.01 | 68.67 |  | B - Node 0.5-1 km | 0.64 | 0.16 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3032
4 | 33 | 3033 | PH0003033 | NCR | Metro Manila | Caloocan City | Barangay 66 | 14.6147 | 120.9642 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.29 | 73.23 | Tier 2 High GIDA (Score 40.0–49.9) | 68.67 | 48.01 | 68.67 |  | A - Node within 0.5 km | 0.4 | 0.61 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3033
4 | 34 | 3034 | 1380608003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 660 | 14.5833 | 120.9852 | U | 342 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.12 | 19.15 | Tier 2 High GIDA (Score 40.0–49.9) | 68.67 | 48 | 68.67 |  | B - Node 0.5-1 km | 0.81 | 0.31 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3034
4 | 35 | 3035 | 1380614036 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 780 | 14.5771 | 121.0097 | U | 2386 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.49 | 47.44 | Tier 2 High GIDA (Score 40.0–49.9) | 68.66 | 48 | 68.66 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3035
4 | 36 | 3036 | 1380605083 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 380 | 14.6312 | 120.9839 | U | 949 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 2.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.66 | 48 | 68.66 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.23 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3036
4 | 37 | 3037 | 1380606114 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 508 | 14.6224 | 120.9966 | U | 1037 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.2 | 54.05 | Tier 2 High GIDA (Score 40.0–49.9) | 68.66 | 48 | 68.66 |  | D - Other node or line within 3 km | 1.48 | 0.83 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3037
4 | 38 | 3038 | 1380614008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 751 | 14.5664 | 121.0071 | U | 1588 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.53 | 38.91 | Tier 2 High GIDA (Score 40.0–49.9) | 68.66 | 48 | 68.66 |  | C - Line within 0.5 km; node over 1 km | 1.52 | 0.18 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3038
4 | 39 | 3039 | 1380606217 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 610 | 14.5953 | 121.0167 | U | 997 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.23 | 8.37 | Tier 2 High GIDA (Score 40.0–49.9) | 68.66 | 48 | 68.66 |  | D - Other node or line within 3 km | 1.51 | 0.84 | Line: UG 288C via V-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3039
4 | 40 | 3040 | 1380606054 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 448 | 14.6051 | 120.9988 | U | 1417 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.01 | 2.53 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 48 | 68.65 |  | B - Node 0.5-1 km | 0.71 | 0.08 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3040
4 | 41 | 3041 | PH0003041 | IV-B | Palawan | Puerto Princesa City | Maunlad (Pob.) | 9.8387 | 118.5761 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.54 | 2.1 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 47.99 | 68.65 |  | F - Nearest node and line over 5 km | 17.48 | 15.91 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3041
4 | 42 | 3042 | 1380606034 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 428 | 14.6059 | 120.9989 | U | 1344 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.58 | 27 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 47.99 | 68.65 |  | B - Node 0.5-1 km | 0.74 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3042
4 | 43 | 3043 | 1380605030 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 328 | 14.6119 | 120.9827 | U | 700 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.04 | 31.72 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 47.99 | 68.65 |  | B - Node 0.5-1 km | 0.51 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3043
4 | 44 | 3044 | 1380614042 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 786 | 14.5799 | 121.0123 | U | 1483 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.76 | 48.56 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 47.99 | 68.65 |  | C - Line within 0.5 km; node over 1 km | 1.14 | 0.17 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3044
4 | 45 | 3045 | 1380606012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 406 | 14.6056 | 120.9898 | U | 463 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.7 | 6.55 | Tier 2 High GIDA (Score 40.0–49.9) | 68.65 | 47.99 | 68.65 |  | A - Node within 0.5 km | 0.31 | 0.09 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3045
4 | 46 | 3046 | PH0003046 | NCR | Metro Manila | Caloocan City | Barangay 65 | 14.6108 | 120.9672 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.03 | 24.04 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.99 | 68.64 |  | B - Node 0.5-1 km | 0.52 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3046
4 | 47 | 3047 | 1380606223 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 616 | 14.5932 | 121.0182 | U | 938 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.73 | 45.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.99 | 68.64 |  | D - Other node or line within 3 km | 1.51 | 0.66 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3047
4 | 48 | 3048 | PH0003048 | IV-B | Palawan | Puerto Princesa City | Mabuhay (Pob.) | 9.8255 | 118.6983 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.43 | 3.99 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.99 | 68.64 |  | E - Nearest node or line 3-5 km | 4.37 | 4.43 | Node: PPW003 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3048
4 | 49 | 3049 | 0600609010 | Region VI (Western Visayas) | Antique | Laua-An | Guiamon | 11.1641 | 122.1125 | R | 242 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.57 | 42.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.99 | 68.64 |  | F - Nearest node and line over 5 km | 48.57 | 41.79 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3049
4 | 50 | 3050 | 1380606007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 401 | 14.6057 | 120.9917 | U | 2404 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.42 | 66.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.98 | 68.64 |  | A - Node within 0.5 km | 0.29 | 0.07 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 614 m | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3050
4 | 51 | 3051 | PH0003051 | VIII | Leyte | Tacloban City | Barangay 6-A | 11.2467 | 125.0048 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.83 | 3.84 | Tier 2 High GIDA (Score 40.0–49.9) | 68.64 | 47.98 | 68.64 |  | B - Node 0.5-1 km | 0.83 | 3.83 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3051
4 | 52 | 3052 | 1380300005 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Carmona | 14.5775 | 121.0175 | U | 1351 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.63 | Tier 2 High GIDA (Score 40.0–49.9) | 68.63 | 47.98 | 68.63 |  | D - Other node or line within 3 km | 1.32 | 0.59 | Line: UG 144C via Y-duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3052
4 | 53 | 3053 | PH0003053 | NCR | Metro Manila | Caloocan City | Barangay 127 | 14.6099 | 120.9629 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.81 | 7.06 | Tier 2 High GIDA (Score 40.0–49.9) | 68.63 | 47.98 | 68.63 |  | B - Node 0.5-1 km | 0.81 | 0.66 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3053
4 | 54 | 3054 | PH0003054 | NCR | Metro Manila | Caloocan City | Barangay 82 | 14.6181 | 120.9708 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 94.29 | 92.81 | Tier 2 High GIDA (Score 40.0–49.9) | 68.63 | 47.98 | 68.63 |  | B - Node 0.5-1 km | 0.87 | 0.01 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3054
4 | 55 | 3055 | 1380614028 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 772 | 14.5774 | 121.0079 | U | 2500 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.59 | 11.91 | Tier 2 High GIDA (Score 40.0–49.9) | 68.63 | 47.98 | 68.63 |  | B - Node 0.5-1 km | 0.96 | 0.19 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3055
4 | 56 | 3056 | 1380606124 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 518 | 14.6175 | 120.9948 | U | 1966 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.67 | 29.26 | Tier 2 High GIDA (Score 40.0–49.9) | 68.63 | 47.98 | 68.63 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.5 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3056
4 | 57 | 3057 | 1380606176 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 570 | 14.6042 | 121.0066 | U | 2063 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.14 | 12.75 | Tier 2 High GIDA (Score 40.0–49.9) | 68.62 | 47.98 | 68.62 |  | A - Node within 0.5 km | 0.33 | 0.24 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3057
4 | 58 | 3058 | PH0003058 | IV-A | Laguna | San Pablo City | Barangay I-A (Pob.) | 17.4583 | 121.7948 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 2.77 | Tier 2 High GIDA (Score 40.0–49.9) | 68.62 | 47.97 | 68.62 |  | C - Line within 0.5 km; node over 1 km | 3.91 | 0.04 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3058
4 | 59 | 3059 | 1381200003 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Bambang | 14.5547 | 121.0781 | U | 22093 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 68.62 | 47.97 | 68.62 |  | B - Node 0.5-1 km | 0.74 | 0.2 | Line: Aerial 216C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3059
4 | 60 | 3060 | 1380602010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 296 | 14.5981 | 120.9706 | U | 1231 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.46 | 58.61 | Tier 2 High GIDA (Score 40.0–49.9) | 68.62 | 47.97 | 68.62 |  | B - Node 0.5-1 km | 0.98 | 0.87 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3060
4 | 61 | 3061 | 1380601202 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 202 | 14.633 | 120.9795 | U | 1463 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.66 | 36.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.62 | 47.97 | 68.62 |  | B - Node 0.5-1 km | 0.95 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3061
4 | 62 | 3062 | 1380200019 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Kuatro | 14.435 | 121.0036 | U | 21080 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.37 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.97 | 68.61 |  | A - Node within 0.5 km | 0.37 | 0.34 | Line: UG | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3062
4 | 63 | 3063 | 1380610010 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 695 | 14.5758 | 120.9925 | U | 674 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.48 | 7.49 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.97 | 68.61 |  | A - Node within 0.5 km | 0.46 | 0.27 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3063
4 | 64 | 3064 | 1380601259 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 258 | 14.6061 | 120.9756 | U | 1217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.37 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.96 | 68.61 |  | B - Node 0.5-1 km | 0.64 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3064
4 | 65 | 3065 | 1380606160 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 554 | 14.6021 | 121.0081 | U | 1598 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.23 | 52.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.96 | 68.61 |  | A - Node within 0.5 km | 0.38 | 0 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3065
4 | 66 | 3066 | 1381300034 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Duyan-duyan | 14.631 | 121.0668 | U | 3498 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.96 | 68.61 |  | B - Node 0.5-1 km | 0.55 | 0.26 | Line: UG 144C via R-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3066
4 | 67 | 3067 | 0500501010 | Region V (Bicol Region) | Albay | Bacacay | Cagbulacao | 13.2852 | 123.888 | R | 896 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.72 | 13.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.61 | 47.96 | 68.61 |  | F - Nearest node and line over 5 km | 11.72 | 13.02 | Node: BYY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3067
4 | 68 | 3068 | 1380606162 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 556 | 14.6044 | 121.0085 | U | 847 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.61 | 19.61 | Tier 2 High GIDA (Score 40.0–49.9) | 68.6 | 47.96 | 68.6 |  | B - Node 0.5-1 km | 0.5 | 0.24 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3068
4 | 69 | 3069 | PH0003069 | I | Ilocos Norte | Laoag City | Bry. No. 18, San Quirino (Pob.) | 18.1931 | 120.5963 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 68.6 | 47.96 | 68.6 |  | C - Line within 0.5 km; node over 1 km | 1.86 | 0.36 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3069
4 | 70 | 3070 | 0201529010 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 8 | 17.6546 | 121.7254 | U | 185 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.4 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 68.6 | 47.96 | 68.6 |  | D - Other node or line within 3 km | 2.34 | 1.89 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3070
4 | 71 | 3071 | 1380606113 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 507 | 14.6189 | 120.9941 | U | 1579 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.81 | 62.77 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | D - Other node or line within 3 km | 1.24 | 0.67 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3071
4 | 72 | 3072 | PH0003072 | NCR | Metro Manila | Caloocan City | Barangay 24 | 14.644 | 120.9735 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 1.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | B - Node 0.5-1 km | 0.58 | 0.95 | Node: CCS004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3072
4 | 73 | 3073 | 0402106037 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas I | 14.3151 | 120.9685 | R | 2180 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 2.06 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | A - Node within 0.5 km | 0.42 | 2.06 | Node: DMC004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3073
4 | 74 | 3074 | PH0003074 | NCR | Metro Manila | Caloocan City | Barangay 93 | 14.62 | 120.9658 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.89 | 70.77 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | A - Node within 0.5 km | 0.4 | 0.57 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3074
4 | 75 | 3075 | 1003511005 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Ilihan | 6.751 | 125.1817 | R | 480 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.42 | 9.08 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | E - Nearest node or line 3-5 km | 3.3 | 19.15 | Node: MYD001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3075
4 | 76 | 3076 | 0804808022 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Canyomanao | 12.5537 | 125.0516 | R | 536 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 102 | 100.99 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | F - Nearest node and line over 5 km | 102 | 102.13 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3076
4 | 77 | 3077 | 0402118060 | Region IV-A (CALABARZON) | Cavite | Silang | Narra II | 14.1694 | 120.9531 | R | 2291 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.64 | 1.61 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | B - Node 0.5-1 km | 0.99 | 0.67 | Line: NCC001 TO TGY001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3077
4 | 78 | 3078 | 1907011004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Hadji Mohtar Sulayman | 17.2558 | 122.2299 | R | 2516 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 68.59 | 47.95 | 68.59 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3078
4 | 79 | 3079 | 1380610032 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 717 | 14.5729 | 120.9878 | U | 494 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.3 | 7.42 | Tier 2 High GIDA (Score 40.0–49.9) | 68.58 | 47.95 | 68.58 |  | B - Node 0.5-1 km | 0.7 | 0.46 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3079
4 | 80 | 3080 | 1380606044 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 438 | 14.6078 | 120.9965 | U | 734 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.96 | 57.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.58 | 47.95 | 68.58 |  | B - Node 0.5-1 km | 0.78 | 0.14 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3080
4 | 81 | 3081 | 1380609002 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 655 | 14.5915 | 120.9771 | U | 1656 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.02 | 49.88 | Tier 2 High GIDA (Score 40.0–49.9) | 68.58 | 47.94 | 68.58 |  | B - Node 0.5-1 km | 0.78 | 0.51 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3081
4 | 82 | 3082 | 1380609001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 654 | 14.5881 | 120.9792 | U | 1074 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.12 | 1.78 | Tier 2 High GIDA (Score 40.0–49.9) | 68.57 | 47.94 | 68.57 |  | B - Node 0.5-1 km | 0.61 | 0.41 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3082
4 | 83 | 3083 | PH0003083 | NCR | Metro Manila | Caloocan City | Barangay 111 | 14.6181 | 120.9625 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 1.43 | Tier 2 High GIDA (Score 40.0–49.9) | 68.57 | 47.94 | 68.57 |  | A - Node within 0.5 km | 0.02 | 0.86 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3083
4 | 84 | 3084 | 1380601244 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 243 | 14.6104 | 120.9757 | U | 449 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.58 | 11.63 | Tier 2 High GIDA (Score 40.0–49.9) | 68.57 | 47.94 | 68.57 |  | B - Node 0.5-1 km | 0.76 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3084
4 | 85 | 3085 | 1380605081 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 378 | 14.6291 | 120.9844 | U | 620 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.73 | 18.34 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3085
4 | 86 | 3086 | 1380606215 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 608 | 14.5935 | 121.0164 | U | 779 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.98 | 46.06 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | D - Other node or line within 3 km | 1.59 | 0.82 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3086
4 | 87 | 3087 | 1381300040 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa IV | 7.6775 | 125.1653 | U | 1914 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.24 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | F - Nearest node and line over 5 km | 6.01 | 5.84 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3087
4 | 88 | 3088 | 1380606221 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 614 | 14.5956 | 121.0178 | U | 416 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.01 | 45.17 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | D - Other node or line within 3 km | 1.59 | 0.84 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3088
4 | 89 | 3089 | 0405628028 | Region IV-A (CALABARZON) | Quezon | Mulanay | Sagongon | 13.453 | 122.5233 | R | 397 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.79 | 4.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | D - Other node or line within 3 km | 2.05 | 12.99 | Node: MLQ002 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3089
4 | 90 | 3090 | PH0003090 | NCR | Metro Manila | Caloocan City | Barangay 99 | 14.6234 | 120.9605 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.05 | 18.65 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | B - Node 0.5-1 km | 0.66 | 1.24 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3090
4 | 91 | 3091 | 1380610041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 726 | 14.5714 | 120.9875 | U | 613 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.52 | 8.9 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | B - Node 0.5-1 km | 0.73 | 0.44 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3091
4 | 92 | 3092 | 0201522017 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Santiago | 18.5231 | 121.2358 | R | 262 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.93 | 3.16 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | E - Nearest node or line 3-5 km | 3.93 | 3.16 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3092
4 | 93 | 3093 | 1380614009 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 752 | 14.5699 | 121.005 | U | 786 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50 | 27.37 | Tier 2 High GIDA (Score 40.0–49.9) | 68.56 | 47.93 | 68.56 |  | C - Line within 0.5 km; node over 1 km | 1.18 | 0.16 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3093
4 | 94 | 3094 | 0403425029 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Lorenzo Ruiz | 14.3348 | 121.0607 | U | 6358 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.71 | 5.82 | Tier 2 High GIDA (Score 40.0–49.9) | 68.55 | 47.93 | 68.55 |  | D - Other node or line within 3 km | 1.68 | 0.99 | Line: AE SPL002 TO SPL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3094
4 | 95 | 3095 | PH0003095 | NCR | Metro Manila | Caloocan City | Barangay 46 | 14.6156 | 120.9708 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.97 | 71.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.55 | 47.92 | 68.55 |  | B - Node 0.5-1 km | 0.91 | 0.07 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3095
4 | 96 | 3096 | 0600406009 | Region VI (Western Visayas) | Aklan | Ibajay | Buenavista | 11.8055 | 122.1735 | R | 557 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.42 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 68.54 | 47.92 | 68.54 |  | F - Nearest node and line over 5 km | 16.42 | 22.47 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3096
4 | 97 | 3097 | 1381000013 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Isidro | 14.4715 | 121.0122 | U | 80897 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 68.54 | 47.92 | 68.54 |  | C - Line within 0.5 km; node over 1 km | 2.41 | 0.28 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3097
4 | 98 | 3098 | 1380610045 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 730 | 14.5713 | 120.9884 | U | 1586 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16 | 14.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.54 | 47.91 | 68.54 |  | B - Node 0.5-1 km | 0.64 | 0.34 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3098
4 | 99 | 3099 | PH0003099 | NCR | Metro Manila | Caloocan City | Barangay 44 | 14.618 | 120.9704 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.36 | 21.34 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | B - Node 0.5-1 km | 0.82 | 0.03 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3099
4 | 100 | 3100 | 1380614016 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 760 | 14.5696 | 121.0068 | U | 1073 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.04 | 42.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3100
4 | 101 | 3101 | 1380606095 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 489 | 14.6235 | 120.9927 | U | 1177 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.8 | 1.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.42 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3101
4 | 102 | 3102 | PH0003102 | CAR | Benguet | Baguio City | Abanao-Zandueta-Kayong-Chugum-Otek | 16.4166 | 120.5624 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.75 | 2.16 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | B - Node 0.5-1 km | 0.9 | 0.38 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3102
4 | 103 | 3103 | 1380606212 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 605 | 14.5971 | 121.0181 | U | 1804 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.64 | 49.08 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | D - Other node or line within 3 km | 1.55 | 0.69 | Line: UG 288C via W-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3103
4 | 104 | 3104 | 1380610058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 744 | 14.5655 | 121.0032 | U | 1260 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.7 | 40.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.53 | 47.91 | 68.53 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.1 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3104
4 | 105 | 3105 | 1705315003 | MIMAROPA Region | Palawan | Narra | Batang-batang | 9.1811 | 118.3376 | R | 1484 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.87 | 78.16 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.91 | 68.52 |  | F - Nearest node and line over 5 km | 75.87 | 77.81 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3105
4 | 106 | 3106 | 1380614057 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 801 | 14.5693 | 120.9976 | U | 633 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.86 | 14.35 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | A - Node within 0.5 km | 0.47 | 0.34 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3106
4 | 107 | 3107 | 1380605024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 322 | 14.6145 | 120.9813 | U | 823 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.17 | 8.23 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | A - Node within 0.5 km | 0.28 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3107
4 | 108 | 3108 | 1380606052 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 446 | 14.6075 | 120.9983 | U | 1032 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.01 | 39.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | B - Node 0.5-1 km | 0.7 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3108
4 | 109 | 3109 | 1102401022 | Region XI (Davao Region) | Davao del Sur | Bansalan | Tinongtongan | 6.813 | 125.2595 | R | 1056 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.17 | 12.87 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | F - Nearest node and line over 5 km | 6.17 | 12.86 | Node: BND001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3109
4 | 110 | 3110 | 1380606230 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 623 | 14.5885 | 121.0182 | U | 983 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.9 | 19.85 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | C - Line within 0.5 km; node over 1 km | 1.19 | 0.28 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3110
4 | 111 | 3111 | 1380605079 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 376 | 14.6314 | 120.983 | U | 958 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.46 | 57.58 | Tier 2 High GIDA (Score 40.0–49.9) | 68.52 | 47.9 | 68.52 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.17 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3111
4 | 112 | 3112 | 1380605063 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 361 | 14.5556 | 120.9963 | U | 737 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.59 | 5.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.51 | 47.89 | 68.51 |  | B - Node 0.5-1 km | 0.55 | 0.05 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3112
4 | 113 | 3113 | 1380606048 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 442 | 14.6077 | 120.9974 | U | 690 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.48 | 53.15 | Tier 2 High GIDA (Score 40.0–49.9) | 68.51 | 47.89 | 68.51 |  | B - Node 0.5-1 km | 0.77 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3113
4 | 114 | 3114 | 1380606071 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 465 | 14.6088 | 120.9908 | U | 785 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.3 | 62.69 | Tier 2 High GIDA (Score 40.0–49.9) | 68.51 | 47.89 | 68.51 |  | B - Node 0.5-1 km | 0.63 | 0.08 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3114
4 | 115 | 3115 | 1380614021 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 765 | 14.5682 | 121.0056 | U | 2138 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.73 | 8.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.5 | 47.89 | 68.5 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3115
4 | 116 | 3116 | 0405632003 | Region IV-A (CALABARZON) | Quezon | Patnanungan | Kilogan | 14.8178 | 122.1826 | R | 1112 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.01 | 72.78 | Tier 2 High GIDA (Score 40.0–49.9) | 68.5 | 47.89 | 68.5 |  | F - Nearest node and line over 5 km | 56.01 | 72.78 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3116
4 | 117 | 3117 | 0802615017 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 5 | 11.455 | 125.4084 | R | 841 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.42 | 54.82 | Tier 2 High GIDA (Score 40.0–49.9) | 68.5 | 47.89 | 68.5 |  | F - Nearest node and line over 5 km | 50.32 | 51.18 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3117
4 | 118 | 3118 | 1380611007 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 673 | 14.5806 | 120.9909 | U | 2848 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.98 | 24.8 | Tier 2 High GIDA (Score 40.0–49.9) | 68.5 | 47.88 | 68.5 |  | C - Line within 0.5 km; node over 1 km | 1.02 | 0.12 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3118
4 | 119 | 3119 | 1906613052 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Tinggah | 17.2554 | 122.2295 | R | 1956 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.38 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3119
4 | 120 | 3120 | 1380606013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 407 | 14.6078 | 120.9884 | U | 1619 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.34 | 22.05 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | B - Node 0.5-1 km | 0.6 | 0.23 | Line: Visayas Ave-Espanya Core Ring, AE, MNL (EAGLENET) 344 m | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3120
4 | 121 | 3121 | 1380606100 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 494 | 14.6221 | 120.9962 | U | 2388 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.64 | 58.1 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | D - Other node or line within 3 km | 1.49 | 0.81 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3121
4 | 122 | 3122 | 1380612008 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 840 | 14.585 | 121.0015 | U | 2618 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.13 | 44.13 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | A - Node within 0.5 km | 0.15 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3122
4 | 123 | 3123 | PH0003123 | NCR | Metro Manila | Caloocan City | Barangay 64 | 14.612 | 120.9646 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.36 | 2.71 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | B - Node 0.5-1 km | 0.69 | 0.51 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3123
4 | 124 | 3124 | 1908801009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Ampatuan | Tomicor | 17.2549 | 122.229 | R | 1442 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.31 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | F - Nearest node and line over 5 km | 29.43 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3124
4 | 125 | 3125 | 1380601221 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 220 | 14.6238 | 120.9815 | U | 1309 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.42 | 12.61 | Tier 2 High GIDA (Score 40.0–49.9) | 68.49 | 47.88 | 68.49 |  | B - Node 0.5-1 km | 0.82 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3125
4 | 126 | 3126 | 1380606219 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 612 | 14.5934 | 121.0173 | U | 724 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.49 | 9.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.48 | 47.88 | 68.48 |  | D - Other node or line within 3 km | 1.59 | 0.74 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3126
4 | 127 | 3127 | PH0003127 | NCR | Metro Manila | Caloocan City | Barangay 141 | 14.6313 | 120.9666 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.27 | 51.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.48 | 47.88 | 68.48 |  | B - Node 0.5-1 km | 0.88 | 0.82 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3127
4 | 128 | 3128 | PH0003128 | NCR | Metro Manila | Caloocan City | Barangay 69 | 14.6111 | 120.9672 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.7 | 15.87 | Tier 2 High GIDA (Score 40.0–49.9) | 68.48 | 47.87 | 68.48 |  | B - Node 0.5-1 km | 0.54 | 0.22 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3128
4 | 129 | 3129 | 1380605073 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 370 | 14.6293 | 120.9863 | U | 795 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.02 | 65.65 | Tier 2 High GIDA (Score 40.0–49.9) | 68.48 | 47.87 | 68.48 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.26 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3129
4 | 130 | 3130 | 1380601262 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 261 | 14.6072 | 120.9739 | U | 757 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.67 | 20.66 | Tier 2 High GIDA (Score 40.0–49.9) | 68.47 | 47.87 | 68.47 |  | A - Node within 0.5 km | 0.46 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3130
4 | 131 | 3131 | 1380614003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 746 | 14.5678 | 121.0037 | U | 1714 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.47 | 57.31 | Tier 2 High GIDA (Score 40.0–49.9) | 68.47 | 47.87 | 68.47 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.08 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3131
4 | 132 | 3132 | 1381100101 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 101 | 14.5386 | 121.0016 | U | 566 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 2.78 | Tier 2 High GIDA (Score 40.0–49.9) | 68.47 | 47.87 | 68.47 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.08 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3132
4 | 133 | 3133 | 1381100001 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 1 | 14.5599 | 120.9913 | U | 2340 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.29 | 11.1 | Tier 2 High GIDA (Score 40.0–49.9) | 68.45 | 47.85 | 68.45 |  | B - Node 0.5-1 km | 0.74 | 0.46 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3133
4 | 134 | 3134 | 1380606184 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 578 | 14.6049 | 121.0128 | U | 1133 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.98 | 1.98 | Tier 2 High GIDA (Score 40.0–49.9) | 68.45 | 47.85 | 68.45 |  | B - Node 0.5-1 km | 0.95 | 0.15 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3134
4 | 135 | 3135 | 1380605029 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 327 | 14.6125 | 120.9809 | U | 1277 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.64 | 47.41 | Tier 2 High GIDA (Score 40.0–49.9) | 68.44 | 47.85 | 68.44 |  | A - Node within 0.5 km | 0.49 | 0.19 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3135
4 | 136 | 3136 | PH0003136 | CAR | Benguet | Baguio City | Campo Filipino | 16.431 | 120.591 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 68.44 | 47.85 | 68.44 |  | B - Node 0.5-1 km | 0.66 | 1.67 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3136
4 | 137 | 3137 | 1380606098 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 492 | 14.6199 | 120.9957 | U | 1141 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.52 | 48.85 | Tier 2 High GIDA (Score 40.0–49.9) | 68.44 | 47.84 | 68.44 |  | D - Other node or line within 3 km | 1.32 | 0.67 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3137
4 | 138 | 3138 | PH0003138 | NCR | Metro Manila | Caloocan City | Barangay 122 | 14.6112 | 120.9641 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.03 | 83.31 | Tier 2 High GIDA (Score 40.0–49.9) | 68.43 | 47.84 | 68.43 |  | B - Node 0.5-1 km | 0.77 | 0.55 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3138
4 | 139 | 3139 | 1380601205 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 204 | 14.6268 | 120.9771 | U | 2766 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.94 | 7.38 | Tier 2 High GIDA (Score 40.0–49.9) | 68.43 | 47.84 | 68.43 |  | A - Node within 0.5 km | 0.4 | 0.02 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3139
4 | 140 | 3140 | PH0003140 | NCR | Metro Manila | Caloocan City | Barangay 105 | 14.6472 | 120.9923 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.88 | 6.97 | Tier 2 High GIDA (Score 40.0–49.9) | 68.43 | 47.84 | 68.43 |  | B - Node 0.5-1 km | 0.83 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3140
4 | 141 | 3141 | PH0003141 | CAR | Benguet | Baguio City | Military Cut-off | 16.4038 | 120.6033 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.7 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.41 | 47.83 | 68.41 |  | B - Node 0.5-1 km | 0.7 | 0.08 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3141
4 | 142 | 3142 | 1380614012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 756 | 14.5697 | 121.0059 | U | 743 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.77 | 6.32 | Tier 2 High GIDA (Score 40.0–49.9) | 68.41 | 47.83 | 68.41 |  | C - Line within 0.5 km; node over 1 km | 1.28 | 0.08 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3142
4 | 143 | 3143 | 1380611027 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 813 | 14.5771 | 121.0039 | U | 1031 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.23 | 28.66 | Tier 2 High GIDA (Score 40.0–49.9) | 68.41 | 47.83 | 68.41 |  | B - Node 0.5-1 km | 0.82 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3143
4 | 144 | 3144 | PH0003144 | NCR | Metro Manila | Caloocan City | Barangay 108 | 14.617 | 120.9595 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.99 | 28.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.41 | 47.83 | 68.41 |  | A - Node within 0.5 km | 0.36 | 1.16 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3144
4 | 145 | 3145 | 1380601235 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 234 | 14.6244 | 120.9808 | U | 2004 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.27 | 33.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.41 | 47.82 | 68.41 |  | B - Node 0.5-1 km | 0.85 | 0.16 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3145
4 | 146 | 3146 | 1380601219 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 218 | 14.625 | 120.9818 | U | 331 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.24 | 53.67 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | B - Node 0.5-1 km | 0.94 | 0.13 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3146
4 | 147 | 3147 | 1380606150 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 544 | 14.6153 | 121.0032 | U | 169 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.55 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | A - Node within 0.5 km | 0.49 | 0.38 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3147
4 | 148 | 3148 | 1903615071 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Calibagat | 17.2546 | 122.2286 | R | 1112 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.79 | 40.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | F - Nearest node and line over 5 km | 29.38 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3148
4 | 149 | 3149 | PH0003149 | VI | Iloilo | Iloilo City | North Avanceña | 10.7396 | 122.542 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.4 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | D - Other node or line within 3 km | 2.79 | 2.11 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 3149
4 | 150 | 3150 | 1380606232 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 625 | 14.5897 | 121.0175 | U | 1058 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.85 | 38.24 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.43 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3150
4 | 151 | 3151 | 1108605004 | Region XI (Davao Region) | Davao Occidental | Sarangani | Mabila | 5.411 | 125.4217 | U | 5248 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.79 | 82.9 | Tier 2 High GIDA (Score 40.0–49.9) | 68.4 | 47.82 | 68.4 |  | F - Nearest node and line over 5 km | 78.79 | 82.9 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3151
4 | 152 | 3152 | 1380614018 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 762 | 14.5672 | 121.0073 | U | 376 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.52 | 76.58 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | C - Line within 0.5 km; node over 1 km | 1.5 | 0.1 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3152
4 | 153 | 3153 | 1380614011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 755 | 14.5663 | 121.0034 | U | 1414 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.35 | 5.7 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | C - Line within 0.5 km; node over 1 km | 1.17 | 0.04 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3153
4 | 154 | 3154 | 1908705034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Tenonggos | 17.2533 | 122.2279 | R | 2630 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | F - Nearest node and line over 5 km | 29.23 | 34.14 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3154
4 | 155 | 3155 | 1908705016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Kenebeka | 17.2538 | 122.2276 | R | 3364 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | F - Nearest node and line over 5 km | 29.24 | 34.12 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3155
4 | 156 | 3156 | 1408104017 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Maragat | 17.912 | 121.0656 | R | 281 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.09 | 15.99 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | F - Nearest node and line over 5 km | 17.09 | 29.98 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3156
4 | 157 | 3157 | 1903615027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Inandayan | 17.2549 | 122.2295 | R | 957 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.63 | 41.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | F - Nearest node and line over 5 km | 29.47 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3157
4 | 158 | 3158 | 1380605005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 301 | 14.6105 | 120.9911 | U | 462 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.73 | 39.39 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | B - Node 0.5-1 km | 0.82 | 0.09 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3158
4 | 159 | 3159 | 1906611028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Tugas | 17.2548 | 122.2295 | R | 846 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.27 | 32.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.39 | 47.81 | 68.39 |  | F - Nearest node and line over 5 km | 29.46 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3159
4 | 160 | 3160 | 0102934033 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Jose | 17.5712 | 120.3944 | R | 915 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.55 | 2.09 | Tier 2 High GIDA (Score 40.0–49.9) | 68.38 | 47.8 | 68.38 |  | D - Other node or line within 3 km | 2.53 | 1 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 3160
4 | 161 | 3161 | 1380614013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 757 | 14.5685 | 121.0038 | U | 491 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.09 | 9.08 | Tier 2 High GIDA (Score 40.0–49.9) | 68.38 | 47.8 | 68.38 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.13 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3161
4 | 162 | 3162 | 1380614058 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 802 | 14.5764 | 121.0037 | U | 1841 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.01 | 48.45 | Tier 2 High GIDA (Score 40.0–49.9) | 68.37 | 47.8 | 68.37 |  | B - Node 0.5-1 km | 0.9 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3162
4 | 163 | 3163 | 1380614081 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 888 | 14.5859 | 121.0177 | U | 862 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.59 | 44.56 | Tier 2 High GIDA (Score 40.0–49.9) | 68.37 | 47.8 | 68.37 |  | C - Line within 0.5 km; node over 1 km | 1.14 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3163
4 | 164 | 3164 | 1380611013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 679 | 14.5838 | 120.9957 | U | 959 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.76 | 16.7 | Tier 2 High GIDA (Score 40.0–49.9) | 68.37 | 47.8 | 68.37 |  | B - Node 0.5-1 km | 0.77 | 0.21 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3164
4 | 165 | 3165 | 1903631011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Canibongan | 17.2543 | 122.2292 | R | 1361 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.92 | 79.81 | Tier 2 High GIDA (Score 40.0–49.9) | 68.37 | 47.8 | 68.37 |  | F - Nearest node and line over 5 km | 29.4 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3165
4 | 166 | 3166 | 1903632042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Calanogas | Pagalongan | 17.2545 | 122.228 | R | 818 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.37 | 47.8 | 68.37 |  | F - Nearest node and line over 5 km | 29.32 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3166
4 | 167 | 3167 | 1380610039 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 724 | 14.5692 | 120.987 | U | 2409 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.88 | 9.62 | Tier 2 High GIDA (Score 40.0–49.9) | 68.36 | 47.79 | 68.36 |  | B - Node 0.5-1 km | 0.84 | 0.51 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3167
4 | 168 | 3168 | PH0003168 | NCR | Metro Manila | Caloocan City | Barangay 60 | 14.6146 | 120.9716 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.18 | 91.56 | Tier 2 High GIDA (Score 40.0–49.9) | 68.36 | 47.79 | 68.36 |  | B - Node 0.5-1 km | 0.89 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3168
4 | 169 | 3169 | 1380605062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 360 | 14.5521 | 120.9937 | U | 764 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.76 | 52.25 | Tier 2 High GIDA (Score 40.0–49.9) | 68.35 | 47.78 | 68.35 |  | A - Node within 0.5 km | 0.25 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3169
4 | 170 | 3170 | PH0003170 | CAR | Benguet | Baguio City | Lourdes Subdivision Extension | 16.3967 | 120.6291 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.42 | 2.6 | Tier 2 High GIDA (Score 40.0–49.9) | 68.34 | 47.78 | 68.34 |  | D - Other node or line within 3 km | 2.1 | 1.82 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3170
4 | 171 | 3171 | 1380614062 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 806 | 14.5762 | 121 | U | 1652 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.43 | 10.43 | Tier 2 High GIDA (Score 40.0–49.9) | 68.34 | 47.77 | 68.34 |  | B - Node 0.5-1 km | 0.78 | 0.28 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3171
4 | 172 | 3172 | PH0003172 | VI | Iloilo | Iloilo City | Ortiz | 10.6989 | 122.5641 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.67 | 11.45 | Tier 2 High GIDA (Score 40.0–49.9) | 68.33 | 47.77 | 68.33 |  | D - Other node or line within 3 km | 1.71 | 0.58 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3172
4 | 173 | 3173 | 1003521016 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Pelingkingan | 8.0443 | 123.9462 | R | 1283 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.86 | 11.22 | Tier 2 High GIDA (Score 40.0–49.9) | 68.33 | 47.77 | 68.33 |  | F - Nearest node and line over 5 km | 16.19 | 9.23 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3173
4 | 174 | 3174 | PH0003174 | NCR | Metro Manila | Caloocan City | Barangay 121 | 14.6124 | 120.9615 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.2 | 13.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.32 | 47.77 | 68.32 |  | B - Node 0.5-1 km | 0.63 | 0.85 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3174
4 | 175 | 3175 | 0402106067 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres II | 14.28 | 120.9992 | R | 3585 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 4.1 | Tier 2 High GIDA (Score 40.0–49.9) | 68.32 | 47.76 | 68.32 |  | A - Node within 0.5 km | 0.41 | 3.57 | Node: MAC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3175
4 | 176 | 3176 | PH0003176 | NCR | Metro Manila | Caloocan City | Barangay 100 | 14.6524 | 120.9922 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.28 | 52.65 | Tier 2 High GIDA (Score 40.0–49.9) | 68.32 | 47.76 | 68.32 |  | B - Node 0.5-1 km | 0.9 | 0.67 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3176
4 | 177 | 3177 | 1380614017 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 761 | 14.5684 | 121.0047 | U | 1094 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.5 | 67.27 | Tier 2 High GIDA (Score 40.0–49.9) | 68.32 | 47.76 | 68.32 |  | C - Line within 0.5 km; node over 1 km | 1.2 | 0.05 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3177
4 | 178 | 3178 | 1380614041 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 785 | 14.5796 | 121.0123 | U | 960 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.28 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 68.31 | 47.75 | 68.31 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.2 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3178
4 | 179 | 3179 | 1380601237 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 236 | 14.622 | 120.9812 | U | 825 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.62 | 54.85 | Tier 2 High GIDA (Score 40.0–49.9) | 68.3 | 47.75 | 68.3 |  | B - Node 0.5-1 km | 0.63 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3179
4 | 180 | 3180 | 1380610013 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 698 | 14.5776 | 120.9938 | U | 1789 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.25 | 60.08 | Tier 2 High GIDA (Score 40.0–49.9) | 68.3 | 47.75 | 68.3 |  | B - Node 0.5-1 km | 0.63 | 0.07 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3180
4 | 181 | 3181 | 1380614005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 748 | 14.57 | 121.0041 | U | 837 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.61 | 4.51 | Tier 2 High GIDA (Score 40.0–49.9) | 68.3 | 47.75 | 68.3 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.22 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3181
4 | 182 | 3182 | PH0003182 | CAR | Benguet | Baguio City | MRR-Queen Of Peace | 16.4046 | 120.6037 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.86 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 68.29 | 47.74 | 68.29 |  | B - Node 0.5-1 km | 0.76 | 0.01 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3182
4 | 183 | 3183 | PH0003183 | NCR | Metro Manila | Caloocan City | Barangay 89 | 14.6165 | 120.9685 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.45 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.29 | 47.74 | 68.29 |  | B - Node 0.5-1 km | 0.65 | 0.2 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3183
4 | 184 | 3184 | PH0003184 | III | Nueva Ecija | Cabanatuan City | Villa Ofelia-Caridad | 15.459 | 120.9343 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.8 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 68.28 | 47.73 | 68.28 |  | D - Other node or line within 3 km | 3.82 | 1.55 | Line: MULTINET - SANTA ROSA | Route options survey candidate: compare actual node lateral with approved line tap. | 3184
4 | 185 | 3185 | 1380601243 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 242 | 14.6116 | 120.9778 | U | 462 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.89 | 21.44 | Tier 2 High GIDA (Score 40.0–49.9) | 68.27 | 47.73 | 68.27 |  | B - Node 0.5-1 km | 0.77 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3185
4 | 186 | 3186 | 1380605061 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 359 | 14.5533 | 120.9958 | U | 422 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.14 | 24.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.27 | 47.73 | 68.27 |  | A - Node within 0.5 km | 0.44 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3186
4 | 187 | 3187 | PH0003187 | IV-A | Laguna | San Pablo City | Barangay VI-A (Pob.) | 14.0718 | 121.3233 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 68.26 | 47.72 | 68.26 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.08 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3187
4 | 188 | 3188 | 1705314008 | MIMAROPA Region | Palawan | Magsaysay | Lacaren | 10.8385 | 121.0482 | R | 473 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 97.56 | 97.54 | Tier 2 High GIDA (Score 40.0–49.9) | 68.26 | 47.72 | 68.26 |  | F - Nearest node and line over 5 km | 97.56 | 97.54 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3188
4 | 189 | 3189 | PH0003189 | CAR | Benguet | Baguio City | Balsigan | 16.4075 | 120.5877 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.42 | 1.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.25 | 47.71 | 68.25 |  | B - Node 0.5-1 km | 0.81 | 0.06 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3189
4 | 190 | 3190 | 1403209008 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Wagud | 17.576 | 121.3415 | R | 1057 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.1 | 8.22 | Tier 2 High GIDA (Score 40.0–49.9) | 68.25 | 47.71 | 68.25 |  | D - Other node or line within 3 km | 2.1 | 8.22 | Node: PKK002 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3190
4 | 191 | 3191 | 1381600015 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Mabolo | 14.7064 | 120.9458 | U | 843 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.05 | Tier 2 High GIDA (Score 40.0–49.9) | 68.25 | 47.71 | 68.25 |  | D - Other node or line within 3 km | 1.04 | 1.35 | Node: OBB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3191
4 | 192 | 3192 | 0504118012 | Region V (Bicol Region) | Masbate | San Fernando | Lahong | 12.4939 | 123.6693 | R | 392 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.2 | 13.74 | Tier 2 High GIDA (Score 40.0–49.9) | 68.24 | 47.71 | 68.24 |  | F - Nearest node and line over 5 km | 16.2 | 15.88 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3192
4 | 193 | 3193 | 1381300142 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | North Fairview | 14.7085 | 121.066 | U | 46272 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.21 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 68.23 | 47.7 | 68.23 |  | C - Line within 0.5 km; node over 1 km | 1.21 | 0.24 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3193
4 | 194 | 3194 | 1380614024 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 768 | 14.5693 | 121.004 | U | 1182 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.04 | 45.74 | Tier 2 High GIDA (Score 40.0–49.9) | 68.21 | 47.69 | 68.21 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.18 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3194
4 | 195 | 3195 | 1408104018 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Musimut | 17.9854 | 121.0778 | R | 857 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.56 | 15.89 | Tier 2 High GIDA (Score 40.0–49.9) | 68.21 | 47.69 | 68.21 |  | F - Nearest node and line over 5 km | 11.56 | 33.33 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3195
4 | 196 | 3196 | PH0003196 | CAR | Benguet | Baguio City | Camp Allen | 16.4039 | 120.606 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.3 | 4.19 | Tier 2 High GIDA (Score 40.0–49.9) | 68.21 | 47.69 | 68.21 |  | B - Node 0.5-1 km | 0.98 | 0.02 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3196
4 | 197 | 3197 | PH0003197 | NCR | Metro Manila | Caloocan City | Barangay 104 | 14.6226 | 120.959 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.69 | 72.22 | Tier 2 High GIDA (Score 40.0–49.9) | 68.21 | 47.69 | 68.21 |  | B - Node 0.5-1 km | 0.65 | 1.35 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3197
4 | 198 | 3198 | PH0003198 | NCR | Metro Manila | Caloocan City | Barangay 57 | 14.6094 | 120.9698 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.9 | 42.92 | Tier 2 High GIDA (Score 40.0–49.9) | 68.2 | 47.68 | 68.2 |  | A - Node within 0.5 km | 0.29 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3198
4 | 199 | 3199 | PH0003199 | NCR | Metro Manila | Caloocan City | Barangay 140 | 14.6307 | 120.9673 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.86 | 0.62 | Tier 2 High GIDA (Score 40.0–49.9) | 68.19 | 47.67 | 68.19 |  | B - Node 0.5-1 km | 0.78 | 0.71 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3199
4 | 200 | 3200 | 1381600010 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Dalandanan | 14.7046 | 120.9642 | U | 23977 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 68.19 | 47.67 | 68.19 |  | B - Node 0.5-1 km | 0.66 | 0.27 | Line: Mnla Pipe | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3200
4 | 201 | 3201 | PH0003201 | NCR | Metro Manila | Caloocan City | Barangay 96 | 14.6188 | 120.9666 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.12 | 80.54 | Tier 2 High GIDA (Score 40.0–49.9) | 68.18 | 47.67 | 68.18 |  | A - Node within 0.5 km | 0.42 | 0.45 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3201
4 | 202 | 3202 | PH0003202 | IV-B | Palawan | Puerto Princesa City | Seaside (Pob.) | 9.7401 | 118.7299 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.7 | 5.17 | Tier 2 High GIDA (Score 40.0–49.9) | 68.18 | 47.67 | 68.18 |  | A - Node within 0.5 km | 0.41 | 2.37 | Node: PPW002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3202
4 | 203 | 3203 | 0504106027 | Region V (Bicol Region) | Masbate | Cawayan | Taberna | 12.0701 | 123.7169 | R | 1588 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.11 | 27.98 | Tier 2 High GIDA (Score 40.0–49.9) | 68.17 | 47.66 | 68.17 |  | F - Nearest node and line over 5 km | 19.11 | 27.99 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3203
4 | 204 | 3204 | 0907313012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Lubusan | 7.6727 | 123.2212 | R | 1170 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.38 | 12.68 | Tier 2 High GIDA (Score 40.0–49.9) | 68.17 | 47.65 | 68.17 |  | F - Nearest node and line over 5 km | 19.38 | 12.62 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3204
4 | 205 | 3205 | PH0003205 | NCR | Metro Manila | Caloocan City | Barangay 137 | 14.6288 | 120.9675 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 9.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68.16 | 47.65 | 68.16 |  | B - Node 0.5-1 km | 0.67 | 0.59 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3205
4 | 206 | 3206 | 1380610012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 697 | 14.5742 | 120.9913 | U | 2027 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.36 | 51.87 | Tier 2 High GIDA (Score 40.0–49.9) | 68.16 | 47.65 | 68.16 |  | A - Node within 0.5 km | 0.4 | 0.26 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3206
4 | 207 | 3207 | 0205009020 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Pudi | 16.295 | 121.3092 | R | 1973 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.88 | 23.46 | Tier 2 High GIDA (Score 40.0–49.9) | 68.15 | 47.64 | 68.15 |  | D - Other node or line within 3 km | 2.88 | 23.46 | Node: KSV001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3207
4 | 208 | 3208 | 0402106074 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel II | 14.3385 | 120.9496 | R | 2392 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 4.11 | Tier 2 High GIDA (Score 40.0–49.9) | 68.14 | 47.64 | 68.14 |  | D - Other node or line within 3 km | 1.72 | 4.04 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3208
4 | 209 | 3209 | PH0003209 | NCR | Metro Manila | Caloocan City | Barangay 92 | 14.6189 | 120.9657 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.34 | 84.7 | Tier 2 High GIDA (Score 40.0–49.9) | 68.14 | 47.64 | 68.14 |  | A - Node within 0.5 km | 0.33 | 0.55 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3209
4 | 210 | 3210 | PH0003210 | III | Nueva Ecija | Cabanatuan City | Matadero (Pob.) | 15.507 | 120.9743 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.18 | 1.33 | Tier 2 High GIDA (Score 40.0–49.9) | 68.14 | 47.63 | 68.14 |  | C - Line within 0.5 km; node over 1 km | 3.14 | 0.22 | Line: TALAVERA - MULTI NET | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3210
4 | 211 | 3211 | 0201503025 | Region II (Cagayan Valley) | Cagayan | Allacapan | Tamboli | 18.2647 | 121.5756 | R | 843 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.8 | 2.34 | Tier 2 High GIDA (Score 40.0–49.9) | 68.13 | 47.63 | 68.13 |  | D - Other node or line within 3 km | 3.8 | 2.33 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3211
4 | 212 | 3212 | 0501705012 | Region V (Bicol Region) | Camarines Sur | Buhi | Ibayugan | 13.487 | 123.5195 | R | 1957 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.91 | 7.59 | Tier 2 High GIDA (Score 40.0–49.9) | 68.12 | 47.62 | 68.12 |  | F - Nearest node and line over 5 km | 7.91 | 7.59 | Line: SAGNAY - PATITINAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3212
4 | 213 | 3213 | 0405607088 | Region IV-A (CALABARZON) | Quezon | Calauag | Villa San Isidro | 14.1681 | 122.2155 | R | 992 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.47 | 17.73 | Tier 2 High GIDA (Score 40.0–49.9) | 68.11 | 47.62 | 68.11 |  | F - Nearest node and line over 5 km | 6.47 | 17.73 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3213
4 | 214 | 3214 | 0803701004 | Region VIII (Eastern Visayas) | Leyte | Abuyog | Bagacay | 10.6 | 125.1728 | R | 410 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.61 | 22.22 | Tier 2 High GIDA (Score 40.0–49.9) | 68.11 | 47.62 | 68.11 |  | F - Nearest node and line over 5 km | 41.5 | 40.36 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3214
4 | 215 | 3215 | PH0003215 | CAR | Benguet | Baguio City | Malcolm Square-Perfecto | 16.4302 | 120.5905 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.44 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 68.11 | 47.61 | 68.11 |  | B - Node 0.5-1 km | 0.61 | 1.69 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3215
4 | 216 | 3216 | 0203111006 | Region II (Cagayan Valley) | Isabela | Divilacan | Bicobian | 17.247 | 122.416 | R | 716 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.14 | 53.48 | Tier 2 High GIDA (Score 40.0–49.9) | 68.1 | 47.61 | 68.1 |  | F - Nearest node and line over 5 km | 46.14 | 53.47 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3216
4 | 217 | 3217 | 0402103047 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino IV | 14.3818 | 120.9763 | U | 70412 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.97 | 7.49 | Tier 2 High GIDA (Score 40.0–49.9) | 68.1 | 47.61 | 68.1 |  | D - Other node or line within 3 km | 1.5 | 6.4 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3217
4 | 218 | 3218 | 1003517002 | Region X (Northern Mindanao) | Lanao del Norte | Poona Piagapo | Bubong-Dinaig | 8.0916 | 124.127 | R | 1134 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.85 | 8.77 | Tier 2 High GIDA (Score 40.0–49.9) | 68.09 | 47.6 | 68.09 |  | F - Nearest node and line over 5 km | 18.58 | 9.82 | Line: 216f feeder iligan completed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3218
4 | 219 | 3219 | PH0003219 | NCR | Metro Manila | Caloocan City | Barangay 112 | 14.6169 | 120.9604 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.72 | 0.77 | Tier 2 High GIDA (Score 40.0–49.9) | 68.09 | 47.6 | 68.09 |  | A - Node within 0.5 km | 0.28 | 1.06 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3219
4 | 220 | 3220 | PH0003220 | IV-A | Cavite | Imus City | Poblacion IV-D | 14.3885 | 120.9291 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.12 | 1.72 | Tier 2 High GIDA (Score 40.0–49.9) | 68.08 | 47.6 | 68.08 |  | D - Other node or line within 3 km | 1.24 | 5.79 | Node: IMC003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3220
4 | 221 | 3221 | 1381300026 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Damar | 14.6968 | 121.1094 | U | 992 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.08 | 47.59 | 68.08 |  | D - Other node or line within 3 km | 1.14 | 1.12 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3221
4 | 222 | 3222 | 1380601242 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 241 | 14.6128 | 120.9752 | U | 461 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.16 | 16.79 | Tier 2 High GIDA (Score 40.0–49.9) | 68.08 | 47.59 | 68.08 |  | B - Node 0.5-1 km | 0.9 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3222
4 | 223 | 3223 | PH0003223 | III | Pampanga | Angeles City | Claro M. Recto | 15.1452 | 120.5927 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 68.08 | 47.59 | 68.08 |  | B - Node 0.5-1 km | 0.71 | 0.26 | Line: ANGELES | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3223
4 | 224 | 3224 | 1003521008 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Lamaosa | 8.0458 | 123.9453 | R | 815 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.11 | 12.02 | Tier 2 High GIDA (Score 40.0–49.9) | 68.07 | 47.59 | 68.07 |  | F - Nearest node and line over 5 km | 16.09 | 9.03 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3224
4 | 225 | 3225 | PH0003225 | IV-A | Cavite | City of Bacoor | Zapote 1 | 14.4588 | 120.9365 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.15 | 2.12 | Tier 2 High GIDA (Score 40.0–49.9) | 68.05 | 47.58 | 68.05 |  | D - Other node or line within 3 km | 1.9 | 1.1 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 3225
4 | 226 | 3226 | 1403201010 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Maling | 17.4591 | 121.2235 | R | 439 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.53 | 5.66 | Tier 2 High GIDA (Score 40.0–49.9) | 68.04 | 47.56 | 68.04 |  | F - Nearest node and line over 5 km | 16.53 | 5.65 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3226
4 | 227 | 3227 | PH0003227 | VI | Iloilo | Iloilo City | Tabuc Suba | 10.7333 | 122.5544 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.91 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 68.03 | 47.56 | 68.03 |  | D - Other node or line within 3 km | 1.91 | 0.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3227
4 | 228 | 3228 | 1705311014 | MIMAROPA Region | Palawan | Dumaran | Santo Tomas | 10.5038 | 119.8196 | R | 1238 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.49 | 41.94 | Tier 2 High GIDA (Score 40.0–49.9) | 68.03 | 47.56 | 68.03 |  | F - Nearest node and line over 5 km | 33.49 | 41.94 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3228
4 | 229 | 3229 | PH0003229 | NCR | Metro Manila | Caloocan City | Barangay 172 | 14.7439 | 121.036 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.45 | 27.5 | Tier 2 High GIDA (Score 40.0–49.9) | 68.02 | 47.55 | 68.02 |  | C - Line within 0.5 km; node over 1 km | 1.63 | 0.14 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3229
4 | 230 | 3230 | 1705109023 | MIMAROPA Region | Occidental Mindoro | Sablayan | Malisbong | 12.7712 | 120.8421 | R | 4495 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.62 | 50.14 | Tier 2 High GIDA (Score 40.0–49.9) | 68.02 | 47.55 | 68.02 |  | F - Nearest node and line over 5 km | 52.62 | 50.14 | Line: ROXAS - SAN JOSE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3230
4 | 231 | 3231 | PH0003231 | NCR | Metro Manila | Caloocan City | Barangay 103 | 14.6238 | 120.9611 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.87 | 79.26 | Tier 2 High GIDA (Score 40.0–49.9) | 68 | 47.54 | 68 |  | B - Node 0.5-1 km | 0.67 | 1.2 | Node: MNL045 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3231
4 | 232 | 3232 | 0401005073 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 4 | 13.761 | 121.0607 | U | 1682 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.65 | 1.83 | Tier 2 High GIDA (Score 40.0–49.9) | 68 | 47.54 | 68 |  | A - Node within 0.5 km | 0.44 | 0.3 | Line: UG SSB001 TO BCY001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3232
4 | 233 | 3233 | 1906617009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Laha | 17.2555 | 122.2295 | R | 1721 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 2 High GIDA (Score 40.0–49.9) | 68 | 47.54 | 68 |  | F - Nearest node and line over 5 km | 29.51 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3233
4 | 234 | 3234 | PH0003234 | VII | Cebu | Talisay City | San Isidro | 10.2564 | 123.839 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.47 | 11.39 | Tier 2 High GIDA (Score 40.0–49.9) | 67.99 | 47.53 | 67.99 |  | B - Node 0.5-1 km | 0.65 | 0.65 | Line: CEBU - TOLEDO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3234
4 | 235 | 3235 | 0401005084 | Region IV-A (CALABARZON) | Batangas | Batangas City | San Agustin Kanluran, Isla Verde | 13.5593 | 121.0494 | R | 687 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.75 | 12.12 | Tier 2 High GIDA (Score 40.0–49.9) | 67.99 | 47.53 | 67.99 |  | F - Nearest node and line over 5 km | 8.75 | 12.12 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3235
4 | 236 | 3236 | PH0003236 | NCR | Metro Manila | Caloocan City | Barangay 79 | 14.6171 | 120.9678 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.64 | 6.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.99 | 47.53 | 67.99 |  | B - Node 0.5-1 km | 0.55 | 0.29 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3236
4 | 237 | 3237 | 0401005037 | Region IV-A (CALABARZON) | Batangas | Batangas City | Liponpon, Isla Verde | 13.5616 | 121.0915 | R | 682 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.05 | 15.77 | Tier 2 High GIDA (Score 40.0–49.9) | 67.98 | 47.52 | 67.98 |  | F - Nearest node and line over 5 km | 7.05 | 15.71 | Node: BCY005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3237
4 | 238 | 3238 | 0908310009 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Olutanga | Galas | 7.3677 | 122.7945 | R | 1984 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.06 | 34.23 | Tier 2 High GIDA (Score 40.0–49.9) | 67.97 | 47.52 | 67.97 |  | F - Nearest node and line over 5 km | 48.06 | 34.1 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3238
4 | 239 | 3239 | 1400116005 | Cordillera Administrative Region (CAR) | Abra | Manabo | San Jose Norte | 17.4422 | 120.7107 | R | 547 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.75 | 18.31 | Tier 2 High GIDA (Score 40.0–49.9) | 67.97 | 47.52 | 67.97 |  | F - Nearest node and line over 5 km | 19.35 | 16.98 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3239
4 | 240 | 3240 | PH0003240 | NCR | Metro Manila | Caloocan City | Barangay 107 | 14.6187 | 120.9607 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.46 | 20.24 | Tier 2 High GIDA (Score 40.0–49.9) | 67.97 | 47.52 | 67.97 |  | A - Node within 0.5 km | 0.23 | 1.07 | Node: MNL045 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3240
4 | 241 | 3241 | PH0003241 | III | Nueva Ecija | Cabanatuan City | Melojavilla (Pob.) | 15.509 | 120.9642 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.92 | 2.39 | Tier 2 High GIDA (Score 40.0–49.9) | 67.96 | 47.51 | 67.96 |  | C - Line within 0.5 km; node over 1 km | 3.05 | 0.17 | Line: TALAVERA - MULTI NET | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3241
4 | 242 | 3242 | 0402106047 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol I | 14.3262 | 120.96 | U | 18198 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 2.81 | Tier 2 High GIDA (Score 40.0–49.9) | 67.94 | 47.5 | 67.94 |  | D - Other node or line within 3 km | 1.65 | 2.73 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3242
4 | 243 | 3243 | PH0003243 | NCR | Metro Manila | Caloocan City | Barangay 67 | 14.6135 | 120.9668 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.83 | 30.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.93 | 47.49 | 67.93 |  | B - Node 0.5-1 km | 0.66 | 0.31 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3243
4 | 244 | 3244 | 1380700012 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Concepcion Dos | 14.6399 | 121.1213 | U | 24827 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.92 | 47.49 | 67.92 |  | C - Line within 0.5 km; node over 1 km | 1.2 | 0.05 | Line: Aerial 96C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3244
4 | 245 | 3245 | 0500501055 | Region V (Bicol Region) | Albay | Bacacay | Tanagan | 13.3132 | 123.8642 | R | 1153 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.2 | 11.55 | Tier 2 High GIDA (Score 40.0–49.9) | 67.92 | 47.48 | 67.92 |  | F - Nearest node and line over 5 km | 9.2 | 11.55 | Node: BYY001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3245
4 | 246 | 3246 | 0403425010 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Nueva | 14.3389 | 121.0401 | U | 4698 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.9 | 5.9 | Tier 2 High GIDA (Score 40.0–49.9) | 67.91 | 47.47 | 67.91 |  | B - Node 0.5-1 km | 0.62 | 0.51 | Line: AE SPL002 TO SPL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3246
4 | 247 | 3247 | PH0003247 | VIII | Samar (Western Samar) | Calbayog City | Danao II | 12.1992 | 124.4225 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.77 | 56.77 | Tier 2 High GIDA (Score 40.0–49.9) | 67.9 | 47.47 | 67.9 |  | F - Nearest node and line over 5 km | 56.77 | 56.74 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3247
4 | 248 | 3248 | 0402106025 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres I | 14.3216 | 120.9445 | R | 4484 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.4 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 67.9 | 47.47 | 67.9 |  | D - Other node or line within 3 km | 2.5 | 2.36 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3248
4 | 249 | 3249 | PH0003249 | IV-A | Laguna | San Pablo City | Barangay V-C (Pob.) | 17.5016 | 121.8327 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.24 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 67.89 | 47.47 | 67.89 |  | E - Nearest node or line 3-5 km | 8.64 | 3.07 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3249
4 | 250 | 3250 | 1705318026 | MIMAROPA Region | Palawan | Roxas | Tinitian | 10.0455 | 119.1778 | R | 2334 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.17 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 67.89 | 47.46 | 67.89 |  | C - Line within 0.5 km; node over 1 km | 12.17 | 0.13 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3250
4 | 251 | 3251 | 1404408001 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Anabel | 17.1328 | 121.0645 | R | 793 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.35 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.89 | 47.46 | 67.89 |  | D - Other node or line within 3 km | 4.35 | 0.76 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 3251
4 | 252 | 3252 | 0402123016 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Jacinto Lumbreras | 14.2906 | 121.002 | R | 4497 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 4.29 | Tier 2 High GIDA (Score 40.0–49.9) | 67.88 | 47.46 | 67.88 |  | B - Node 0.5-1 km | 0.91 | 4.29 | Node: MAC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3252
4 | 253 | 3253 | PH0003253 | VIII | Leyte | Tacloban City | Barangay 39 | 11.2489 | 124.9641 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.95 | 12.05 | Tier 2 High GIDA (Score 40.0–49.9) | 67.87 | 47.45 | 67.87 |  | E - Nearest node or line 3-5 km | 4.3 | 6.37 | Node: TCL002 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3253
4 | 254 | 3254 | 0405805015 | Region IV-A (CALABARZON) | Rizal | Cainta | San Isidro | 14.6362 | 121.1086 | U | 83020 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 67.87 | 47.45 | 67.87 |  | C - Line within 0.5 km; node over 1 km | 1.55 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3254
4 | 255 | 3255 | 0405622043 | Region IV-A (CALABARZON) | Quezon | Lopez | Lourdes | 13.9578 | 122.2261 | R | 293 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.58 | 6.32 | Tier 2 High GIDA (Score 40.0–49.9) | 67.86 | 47.44 | 67.86 |  | F - Nearest node and line over 5 km | 6.58 | 6.28 | Line: WP CLQ001 TO MLQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3255
4 | 256 | 3256 | 0402118049 | Region IV-A (CALABARZON) | Cavite | Silang | Acacia | 14.1825 | 120.9622 | U | 10181 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.24 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 67.86 | 47.44 | 67.86 |  | C - Line within 0.5 km; node over 1 km | 2.31 | 0.11 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3256
4 | 257 | 3257 | 0102917006 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Sibsibbu | 17.2978 | 120.5731 | R | 633 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.41 | 6.5 | Tier 2 High GIDA (Score 40.0–49.9) | 67.85 | 47.44 | 67.85 |  | F - Nearest node and line over 5 km | 7.41 | 6.49 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3257
4 | 258 | 3258 | PH0003258 | VIII | Samar (Western Samar) | Calbayog City | Roxas I | 12.2846 | 124.5122 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.55 | 57.54 | Tier 2 High GIDA (Score 40.0–49.9) | 67.85 | 47.44 | 67.85 |  | F - Nearest node and line over 5 km | 57.55 | 57.52 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3258
4 | 259 | 3259 | PH0003259 | IV-A | Cavite | City of Bacoor | Aniban 2 | 14.4488 | 120.9346 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.41 | 0.67 | Tier 2 High GIDA (Score 40.0–49.9) | 67.83 | 47.42 | 67.83 |  | C - Line within 0.5 km; node over 1 km | 1.53 | 0.03 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3259
4 | 260 | 3260 | PH0003260 | CAR | Benguet | Baguio City | Kabayanihan | 16.4164 | 120.5832 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.38 | 1.6 | Tier 2 High GIDA (Score 40.0–49.9) | 67.82 | 47.41 | 67.82 |  | B - Node 0.5-1 km | 0.55 | 0.39 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3260
4 | 261 | 3261 | 0203131018 | Region II (Cagayan Valley) | Isabela | San Mariano | Ibujan | 16.8346 | 122.0731 | R | 757 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.93 | 30.88 | Tier 2 High GIDA (Score 40.0–49.9) | 67.81 | 47.4 | 67.81 |  | F - Nearest node and line over 5 km | 17.93 | 30.88 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3261
4 | 262 | 3262 | 0702232010 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward I | 10.2443 | 123.7983 | U | 2358 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 67.81 | 47.4 | 67.81 |  | A - Node within 0.5 km | 0.45 | 0.2 | Line: CEBU - TOLEDO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3262
4 | 263 | 3263 | PH0003263 | VIII | Samar (Western Samar) | Calbayog City | San Rufino | 12.2273 | 124.566 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.04 | 66.03 | Tier 2 High GIDA (Score 40.0–49.9) | 67.8 | 47.4 | 67.8 |  | F - Nearest node and line over 5 km | 66.04 | 66.01 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3263
4 | 264 | 3264 | PH0003264 | I | Ilocos Norte | Laoag City | Bgy. No. 9, Santa Angela (Pob.) | 18.1861 | 120.5817 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.53 | 2.48 | Tier 2 High GIDA (Score 40.0–49.9) | 67.8 | 47.4 | 67.8 |  | D - Other node or line within 3 km | 2.14 | 0.75 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Route options survey candidate: compare actual node lateral with approved line tap. | 3264
4 | 265 | 3265 | 0402106040 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina I | 14.3219 | 120.971 | R | 3481 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 2.85 | Tier 2 High GIDA (Score 40.0–49.9) | 67.8 | 47.4 | 67.8 |  | D - Other node or line within 3 km | 1.2 | 2.83 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3265
4 | 266 | 3266 | 1380700016 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Tumana | 14.6484 | 121.1189 | U | 49057 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.18 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 67.79 | 47.39 | 67.79 |  | A - Node within 0.5 km | 0.49 | 0.11 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3266
4 | 267 | 3267 | 0403404014 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Sala | 14.2713 | 121.1262 | U | 11951 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.43 | 4.43 | Tier 2 High GIDA (Score 40.0–49.9) | 67.78 | 47.39 | 67.78 |  | C - Line within 0.5 km; node over 1 km | 2.45 | 0.25 | Line: AE SRL007-CBL001-CLB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3267
4 | 268 | 3268 | 1903612038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumbatan | Pantar | 17.2548 | 122.2288 | R | 1515 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 67.77 | 47.37 | 67.77 |  | F - Nearest node and line over 5 km | 29.41 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3268
4 | 269 | 3269 | 0402106034 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel I | 14.2878 | 120.9617 | R | 2971 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 3.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.76 | 47.37 | 67.76 |  | C - Line within 0.5 km; node over 1 km | 1.4 | 0.26 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3269
4 | 270 | 3270 | 1408104005 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Dagara | 17.9253 | 121.0897 | R | 445 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.26 | 13.41 | Tier 2 High GIDA (Score 40.0–49.9) | 67.76 | 47.37 | 67.76 |  | F - Nearest node and line over 5 km | 14.26 | 28.45 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3270
4 | 271 | 3271 | PH0003271 | IV-A | Laguna | San Pablo City | Santo Cristo | 14.0646 | 121.3325 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 0.54 | Tier 2 High GIDA (Score 40.0–49.9) | 67.75 | 47.37 | 67.75 |  | B - Node 0.5-1 km | 0.67 | 0.52 | Line: SPO001 TO LBQ001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3271
4 | 272 | 3272 | PH0003272 | CAR | Benguet | Baguio City | City Camp Proper | 16.4204 | 120.5884 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.54 | 1.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.75 | 47.36 | 67.75 |  | B - Node 0.5-1 km | 0.58 | 0.67 | Node: BGC002 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3272
4 | 273 | 3273 | PH0003273 | IV-A | Cavite | Imus City | Poblacion IV-C | 14.4265 | 120.9335 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 1.6 | Tier 2 High GIDA (Score 40.0–49.9) | 67.75 | 47.36 | 67.75 |  | D - Other node or line within 3 km | 1.38 | 2.47 | Node: IMC002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3273
4 | 274 | 3274 | PH0003274 | VIII | Samar (Western Samar) | Calbayog City | Macatingog | 12.2964 | 124.4853 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.42 | 54.41 | Tier 2 High GIDA (Score 40.0–49.9) | 67.75 | 47.36 | 67.75 |  | F - Nearest node and line over 5 km | 54.42 | 54.38 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3274
4 | 275 | 3275 | 0102934009 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Barraca | 17.5594 | 120.3521 | R | 300 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.25 | 3.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.74 | 47.36 | 67.74 |  | E - Nearest node or line 3-5 km | 5.57 | 4.53 | Line: SEGMENT 3 (VIGAN - BATAC) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3275
4 | 276 | 3276 | 1380610015 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 700 | 14.5701 | 120.9909 | U | 142 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.86 | 20.08 | Tier 2 High GIDA (Score 40.0–49.9) | 67.73 | 47.35 | 67.73 |  | A - Node within 0.5 km | 0.42 | 0.08 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3276
4 | 277 | 3277 | 0504111030 | Region V (Bicol Region) | Masbate | City of Masbate | Usab | 12.3307 | 123.5803 | R | 3146 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.97 | 0.48 | Tier 2 High GIDA (Score 40.0–49.9) | 67.73 | 47.35 | 67.73 |  | C - Line within 0.5 km; node over 1 km | 4.97 | 0.45 | Line: MASBATE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3277
4 | 278 | 3278 | PH0003278 | III | Nueva Ecija | Cabanatuan City | Fatima (Pob.) | 15.4999 | 120.9717 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.52 | 1.52 | Tier 2 High GIDA (Score 40.0–49.9) | 67.71 | 47.34 | 67.71 |  | D - Other node or line within 3 km | 2.32 | 0.54 | Line: TALAVERA - MULTI NET | Route options survey candidate: compare actual node lateral with approved line tap. | 3278
4 | 279 | 3279 | 1381300056 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Maharlika | 14.6872 | 121.0259 | U | 4532 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.04 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 67.71 | 47.33 | 67.71 |  | B - Node 0.5-1 km | 0.83 | 0.08 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3279
4 | 280 | 3280 | 0405622090 | Region IV-A (CALABARZON) | Quezon | Lopez | Villa Espina | 13.8574 | 122.3794 | R | 916 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.14 | 3.17 | Tier 2 High GIDA (Score 40.0–49.9) | 67.7 | 47.33 | 67.7 |  | E - Nearest node or line 3-5 km | 9.14 | 3.11 | Line: AE LZQ001 TO SNQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3280
4 | 281 | 3281 | PH0003281 | CAR | Benguet | Baguio City | Fairview Village | 16.4159 | 120.5837 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.49 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 67.68 | 47.32 | 67.68 |  | A - Node within 0.5 km | 0.49 | 0.37 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3281
4 | 282 | 3282 | 1408104012 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Lucab | 18.0299 | 121.132 | R | 575 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.32 | 13.49 | Tier 2 High GIDA (Score 40.0–49.9) | 67.68 | 47.32 | 67.68 |  | F - Nearest node and line over 5 km | 5.32 | 32.89 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3282
4 | 283 | 3283 | PH0003283 | VIII | Leyte | Tacloban City | Barangay 48-A | 11.2002 | 124.9985 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.83 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 67.68 | 47.31 | 67.68 |  | D - Other node or line within 3 km | 1.81 | 0.85 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3283
4 | 284 | 3284 | PH0003284 | VIII | Samar (Western Samar) | Calbayog City | Cag-anahaw | 12.2498 | 124.5341 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.76 | 61.75 | Tier 2 High GIDA (Score 40.0–49.9) | 67.68 | 47.31 | 67.68 |  | F - Nearest node and line over 5 km | 61.76 | 61.73 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3284
4 | 285 | 3285 | 0402103014 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino I | 14.4226 | 120.9757 | U | 17504 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.24 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 67.67 | 47.31 | 67.67 |  | D - Other node or line within 3 km | 1.08 | 2.99 | Node: BRC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3285
4 | 286 | 3286 | 1102501012 | Region XI (Davao Region) | Davao Oriental | Baganga | Mahanub | 7.6316 | 126.5395 | R | 4568 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 57.54 | 57.14 | Tier 2 High GIDA (Score 40.0–49.9) | 67.67 | 47.31 | 67.67 |  | F - Nearest node and line over 5 km | 57.54 | 57.14 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3286
4 | 287 | 3287 | PH0003287 | VIII | Samar (Western Samar) | Calbayog City | Lapaan | 12.2043 | 124.5983 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.38 | 70.37 | Tier 2 High GIDA (Score 40.0–49.9) | 67.67 | 47.31 | 67.67 |  | F - Nearest node and line over 5 km | 70.38 | 70.35 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3287
4 | 288 | 3288 | PH0003288 | VIII | Samar (Western Samar) | Calbayog City | Higasaan | 12.2281 | 124.7806 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.73 | 85.72 | Tier 2 High GIDA (Score 40.0–49.9) | 67.66 | 47.3 | 67.66 |  | F - Nearest node and line over 5 km | 85.73 | 85.7 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3288
4 | 289 | 3289 | PH0003289 | VIII | Samar (Western Samar) | Calbayog City | Cangomaod | 12.22 | 124.406 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.85 | 53.85 | Tier 2 High GIDA (Score 40.0–49.9) | 67.66 | 47.3 | 67.66 |  | F - Nearest node and line over 5 km | 53.85 | 53.82 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3289
4 | 290 | 3290 | 0402103048 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino V | 14.4679 | 120.946 | U | 6908 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.9 | 3.35 | Tier 2 High GIDA (Score 40.0–49.9) | 67.66 | 47.3 | 67.66 |  | D - Other node or line within 3 km | 1.81 | 1.73 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3290
4 | 291 | 3291 | 1705104009 | MIMAROPA Region | Occidental Mindoro | Lubang | Sorville | 13.8474 | 120.1502 | R | 124 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.01 | 54.86 | Tier 2 High GIDA (Score 40.0–49.9) | 67.64 | 47.29 | 67.64 |  | F - Nearest node and line over 5 km | 51.82 | 51.62 | Line: BALAYAN - CALATAGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3291
4 | 292 | 3292 | 0803720016 | Region VIII (Eastern Visayas) | Leyte | Hindang | Mahilum | 10.4759 | 124.836 | R | 321 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.87 | 9.89 | Tier 2 High GIDA (Score 40.0–49.9) | 67.64 | 47.29 | 67.64 |  | F - Nearest node and line over 5 km | 22.95 | 9.88 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3292
4 | 293 | 3293 | 1381300117 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Tagumpay | 14.6515 | 121.0013 | U | 2352 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 67.64 | 47.29 | 67.64 |  | D - Other node or line within 3 km | 1.5 | 1.44 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3293
4 | 294 | 3294 | 1705318003 | MIMAROPA Region | Palawan | Roxas | Bagong Bayan | 10.4307 | 119.567 | R | 1261 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.4 | 20.95 | Tier 2 High GIDA (Score 40.0–49.9) | 67.64 | 47.29 | 67.64 |  | F - Nearest node and line over 5 km | 27.4 | 20.89 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3294
4 | 295 | 3295 | 1402706027 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Palaad | 16.9157 | 121.2081 | R | 314 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.22 | 15.02 | Tier 2 High GIDA (Score 40.0–49.9) | 67.63 | 47.28 | 67.63 |  | E - Nearest node or line 3-5 km | 3.22 | 14.86 | Node: MOF002 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3295
4 | 296 | 3296 | PH0003296 | CAR | Benguet | Baguio City | Brookside | 16.4215 | 120.6018 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 1.15 | Tier 2 High GIDA (Score 40.0–49.9) | 67.63 | 47.28 | 67.63 |  | B - Node 0.5-1 km | 0.98 | 1.06 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3296
4 | 297 | 3297 | 1908810006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Meta | 6.8881 | 124.4338 | R | 3810 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.46 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 67.62 | 47.27 | 67.62 |  | F - Nearest node and line over 5 km | 34.46 | 34.39 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3297
4 | 298 | 3298 | 1108202024 | Region XI (Davao Region) | Davao de Oro | Laak | Datu Ampunan | 7.873 | 125.7519 | R | 1777 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.77 | 35.61 | Tier 2 High GIDA (Score 40.0–49.9) | 67.6 | 47.26 | 67.6 |  | F - Nearest node and line over 5 km | 33.9 | 30.79 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3298
4 | 299 | 3299 | 0403425011 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Poblacion | 14.3638 | 121.058 | U | 6326 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.82 | 4.83 | Tier 2 High GIDA (Score 40.0–49.9) | 67.6 | 47.26 | 67.6 |  | C - Line within 0.5 km; node over 1 km | 1.71 | 0.23 | Line: RELIANCE PSG001 TO BÑL001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3299
4 | 300 | 3300 | 1908810004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Maitumaig | 17.2551 | 122.2292 | R | 2669 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 67.6 | 47.26 | 67.6 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3300
4 | 301 | 3301 | 0403428023 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Tagapo | 14.3189 | 121.1032 | U | 46153 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.16 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 67.6 | 47.26 | 67.6 |  | D - Other node or line within 3 km | 2.16 | 0.54 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 3301
4 | 302 | 3302 | PH0003302 | VIII | Samar (Western Samar) | Calbayog City | Dinawacan | 12.175 | 124.7952 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 89.99 | 89.98 | Tier 2 High GIDA (Score 40.0–49.9) | 67.6 | 47.26 | 67.6 |  | F - Nearest node and line over 5 km | 89.99 | 89.96 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3302
4 | 303 | 3303 | PH0003303 | VIII | Samar (Western Samar) | Calbayog City | Esperanza | 12.1848 | 124.6613 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.19 | 77.18 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.26 | 67.59 |  | F - Nearest node and line over 5 km | 77.19 | 77.15 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3303
4 | 304 | 3304 | PH0003304 | VIII | Samar (Western Samar) | Calbayog City | Hibabngan | 12.2355 | 124.6354 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 71.69 | 71.68 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 71.69 | 71.65 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3304
4 | 305 | 3305 | PH0003305 | VIII | Samar (Western Samar) | Calbayog City | Kalilihan | 12.2478 | 124.7213 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.01 | 79 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 79.01 | 78.98 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3305
4 | 306 | 3306 | PH0003306 | VIII | Samar (Western Samar) | Calbayog City | Hibatang | 12.1809 | 124.655 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.88 | 76.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 76.88 | 76.85 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3306
4 | 307 | 3307 | PH0003307 | VIII | Samar (Western Samar) | Calbayog City | Gasdo | 12.2731 | 124.663 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.11 | 72.09 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 72.11 | 72.07 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3307
4 | 308 | 3308 | PH0003308 | VIII | Samar (Western Samar) | Calbayog City | Nag-uma | 12.2562 | 124.7209 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.53 | 78.52 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 78.53 | 78.5 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3308
4 | 309 | 3309 | 1903610034 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Babayog | 17.254 | 122.2291 | R | 809 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.78 | 26.08 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 29.37 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3309
4 | 310 | 3310 | 0103315003 | Region I (Ilocos Region) | La Union | San Gabriel | Apayao | 16.6689 | 120.4999 | R | 988 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.21 | 14.69 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | F - Nearest node and line over 5 km | 11.21 | 14.69 | Node: SGU001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3310
4 | 311 | 3311 | 1404402004 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Balintaugan | 17.0522 | 120.8778 | R | 150 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.34 | 2.82 | Tier 2 High GIDA (Score 40.0–49.9) | 67.59 | 47.25 | 67.59 |  | D - Other node or line within 3 km | 4.34 | 2.73 | Line: LA TRINIDAD-SAGADA | Route options survey candidate: compare actual node lateral with approved line tap. | 3311
4 | 312 | 3312 | 0402106044 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Maria | 14.3406 | 120.9502 | U | 5335 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.13 | 3.85 | Tier 2 High GIDA (Score 40.0–49.9) | 67.58 | 47.25 | 67.58 |  | D - Other node or line within 3 km | 1.59 | 4.27 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3312
4 | 313 | 3313 | PH0003313 | VIII | Leyte | Tacloban City | Barangay 48 | 11.2489 | 124.9641 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.63 | 10.41 | Tier 2 High GIDA (Score 40.0–49.9) | 67.58 | 47.25 | 67.58 |  | E - Nearest node or line 3-5 km | 4.3 | 6.37 | Node: TCL002 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3313
4 | 314 | 3314 | PH0003314 | VII | Cebu | Talisay City | Lawaan III | 10.2651 | 123.8286 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.03 | 9.39 | Tier 2 High GIDA (Score 40.0–49.9) | 67.57 | 47.24 | 67.57 |  | D - Other node or line within 3 km | 1.37 | 0.64 | Line: CEBU - TOLEDO | Route options survey candidate: compare actual node lateral with approved line tap. | 3314
4 | 315 | 3315 | 0402106039 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Simon | 14.3213 | 120.9714 | U | 6571 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 2.82 | Tier 2 High GIDA (Score 40.0–49.9) | 67.57 | 47.24 | 67.57 |  | D - Other node or line within 3 km | 1.17 | 2.81 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3315
4 | 316 | 3316 | PH0003316 | CAR | Benguet | Baguio City | Rock Quarry, Lower | 16.4172 | 120.6164 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.68 | Tier 2 High GIDA (Score 40.0–49.9) | 67.56 | 47.23 | 67.56 |  | C - Line within 0.5 km; node over 1 km | 1.77 | 0.04 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3316
4 | 317 | 3317 | PH0003317 | IV-A | Cavite | Imus City | Mariano Espeleta II | 14.4021 | 120.9398 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 67.55 | 47.23 | 67.55 |  | B - Node 0.5-1 km | 0.55 | 4.99 | Node: IMC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3317
4 | 318 | 3318 | PH0003318 | XI | Davao Del Sur | Davao City | Barangay 15-B (Pob.) | 7.265 | 125.6665 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.84 | 1.57 | Tier 2 High GIDA (Score 40.0–49.9) | 67.54 | 47.22 | 67.54 |  | C - Line within 0.5 km; node over 1 km | 4.25 | 0.32 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3318
4 | 319 | 3319 | 0405811005 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan I | 14.6953 | 121.1209 | U | 33621 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.47 | Tier 2 High GIDA (Score 40.0–49.9) | 67.54 | 47.22 | 67.54 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.02 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3319
4 | 320 | 3320 | PH0003320 | IV-A | Batangas | Lipa City | Poblacion Barangay 10 | 13.9435 | 121.1686 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 67.54 | 47.22 | 67.54 |  | A - Node within 0.5 km | 0.25 | 0.16 | Line: CLB001 TO BCY01 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3320
4 | 321 | 3321 | 1381300105 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Santa Lucia | 14.7073 | 121.0526 | U | 29399 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 67.54 | 47.21 | 67.54 |  | D - Other node or line within 3 km | 1.95 | 0.92 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3321
4 | 322 | 3322 | PH0003322 | VIII | Samar (Western Samar) | Calbayog City | San Isidro | 12.1854 | 124.6285 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.27 | 74.26 | Tier 2 High GIDA (Score 40.0–49.9) | 67.53 | 47.21 | 67.53 |  | F - Nearest node and line over 5 km | 74.27 | 74.23 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3322
4 | 323 | 3323 | 1206512016 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Sen. Ninoy Aquino | Midtungok | 6.4019 | 124.2522 | R | 3412 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.49 | 56.42 | Tier 2 High GIDA (Score 40.0–49.9) | 67.53 | 47.21 | 67.53 |  | F - Nearest node and line over 5 km | 56.49 | 56.42 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3323
4 | 324 | 3324 | PH0003324 | VIII | Samar (Western Samar) | Calbayog City | Palanogan | 12.1856 | 124.6472 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.88 | 75.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.53 | 47.21 | 67.53 |  | F - Nearest node and line over 5 km | 75.88 | 75.85 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3324
4 | 325 | 3325 | PH0003325 | VIII | Samar (Western Samar) | Calbayog City | Helino | 12.2161 | 124.7028 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.03 | 79.02 | Tier 2 High GIDA (Score 40.0–49.9) | 67.53 | 47.21 | 67.53 |  | F - Nearest node and line over 5 km | 79.03 | 79 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3325
4 | 326 | 3326 | PH0003326 | VIII | Samar (Western Samar) | Calbayog City | San Antonio | 12.1609 | 124.7522 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.85 | 86.84 | Tier 2 High GIDA (Score 40.0–49.9) | 67.52 | 47.21 | 67.52 |  | F - Nearest node and line over 5 km | 86.85 | 86.82 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3326
4 | 327 | 3327 | PH0003327 | IV-A | Cavite | Imus City | Poblacion I-A (Pob.) | 14.4269 | 120.9391 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 0.99 | Tier 2 High GIDA (Score 40.0–49.9) | 67.52 | 47.2 | 67.52 |  | B - Node 0.5-1 km | 0.8 | 2.31 | Node: IMC002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3327
4 | 328 | 3328 | 0402106031 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Juan | 14.3014 | 120.9795 | R | 3860 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.49 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 67.52 | 47.2 | 67.52 |  | D - Other node or line within 3 km | 1.93 | 2.25 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3328
4 | 329 | 3329 | PH0003329 | CAR | Benguet | Baguio City | Rock Quarry, Upper | 16.3974 | 120.5749 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.3 | 4.56 | Tier 2 High GIDA (Score 40.0–49.9) | 67.52 | 47.2 | 67.52 |  | D - Other node or line within 3 km | 1.63 | 0.62 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 3329
4 | 330 | 3330 | 0402123020 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Marcelino Memije | 14.2943 | 121.0343 | R | 5213 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.19 | 3.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.51 | 47.2 | 67.51 |  | D - Other node or line within 3 km | 2.02 | 2.51 | Node: CRC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3330
4 | 331 | 3331 | PH0003331 | VIII | Leyte | Tacloban City | Barangay 2 | 11.2607 | 124.9203 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.33 | 8.67 | Tier 2 High GIDA (Score 40.0–49.9) | 67.51 | 47.2 | 67.51 |  | F - Nearest node and line over 5 km | 9.26 | 8.07 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3331
4 | 332 | 3332 | 0201529022 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Cataggaman Viejo | 17.5968 | 121.7072 | R | 4626 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.04 | 1.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.49 | 47.19 | 67.49 |  | D - Other node or line within 3 km | 4.04 | 1.85 | Line: TUGEGARAO FOC | Route options survey candidate: compare actual node lateral with approved line tap. | 3332
4 | 333 | 3333 | 0200906003 | Region II (Cagayan Valley) | Batanes | Uyugan | Itbud | 20.3675 | 121.9626 | R | 533 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 215.09 | 208.37 | Tier 2 High GIDA (Score 40.0–49.9) | 67.48 | 47.18 | 67.48 |  | F - Nearest node and line over 5 km | 211.47 | 208.37 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3333
4 | 334 | 3334 | PH0003334 | VIII | Samar (Western Samar) | Calbayog City | Jimautan | 12.144 | 124.6092 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.52 | 75.51 | Tier 2 High GIDA (Score 40.0–49.9) | 67.48 | 47.18 | 67.48 |  | F - Nearest node and line over 5 km | 75.52 | 75.49 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3334
4 | 335 | 3335 | 1380400020 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tonsuya | 14.6636 | 120.9575 | U | 41165 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.43 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 67.47 | 47.17 | 67.47 |  | A - Node within 0.5 km | 0.43 | 0.77 | Node: MAL004 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3335
4 | 336 | 3336 | 1907004005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tonggosong | 4.9235 | 119.8193 | R | 1675 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 67.47 | 47.17 | 67.47 |  | F - Nearest node and line over 5 km | 333.14 | 333.13 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3336
4 | 337 | 3337 | PH0003337 | NIR | Negros Occidental | Bacolod City | Barangay 8 (Pob.) | 10.6881 | 122.9686 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 1.77 | Tier 2 High GIDA (Score 40.0–49.9) | 67.46 | 47.16 | 67.46 |  | D - Other node or line within 3 km | 2.95 | 1.06 | Line: TALISAY CITY - KABANGKALAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3337
4 | 338 | 3338 | PH0003338 | VIII | Samar (Western Samar) | Calbayog City | Tanval | 12.1862 | 124.6953 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.14 | 80.13 | Tier 2 High GIDA (Score 40.0–49.9) | 67.46 | 47.16 | 67.46 |  | F - Nearest node and line over 5 km | 80.14 | 80.11 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3338
4 | 339 | 3339 | PH0003339 | VIII | Samar (Western Samar) | Calbayog City | Pinamorotan | 12.1982 | 124.7884 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.06 | 88.05 | Tier 2 High GIDA (Score 40.0–49.9) | 67.46 | 47.16 | 67.46 |  | F - Nearest node and line over 5 km | 88.06 | 88.03 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3339
4 | 340 | 3340 | PH0003340 | VIII | Samar (Western Samar) | Calbayog City | Bagong Lipunan | 12.1842 | 124.6588 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77 | 76.99 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.16 | 67.45 |  | F - Nearest node and line over 5 km | 77 | 76.97 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3340
4 | 341 | 3341 | PH0003341 | VIII | Samar (Western Samar) | Calbayog City | Mancol | 12.2263 | 124.6915 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 77.4 | 77.38 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.16 | 67.45 |  | F - Nearest node and line over 5 km | 77.4 | 77.36 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3341
4 | 342 | 3342 | 0403405038 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 1 | 14.2049 | 121.1584 | U | 6383 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.16 | 67.45 |  | C - Line within 0.5 km; node over 1 km | 1.57 | 0.16 | Line: CLB001 TO SCL001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3342
4 | 343 | 3343 | 0403425024 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Fatima | 14.3332 | 121.0479 | U | 7115 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.62 | 6.73 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.16 | 67.45 |  | D - Other node or line within 3 km | 1.5 | 1.12 | Line: AE SPL002 TO SPL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3343
4 | 344 | 3344 | PH0003344 | VIII | Samar (Western Samar) | Calbayog City | Jacinto | 12.2141 | 124.6485 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.19 | 74.18 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.16 | 67.45 |  | F - Nearest node and line over 5 km | 74.19 | 74.15 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3344
4 | 345 | 3345 | PH0003345 | XI | Davao Del Sur | Davao City | Barangay 40-D (Pob.) | 7.265 | 125.6665 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.49 | 4.13 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.15 | 67.45 |  | C - Line within 0.5 km; node over 1 km | 4.25 | 0.32 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3345
4 | 346 | 3346 | PH0003346 | VIII | Samar (Western Samar) | Calbayog City | Buenavista | 12.2359 | 124.6568 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.62 | 73.61 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.15 | 67.45 |  | F - Nearest node and line over 5 km | 73.62 | 73.59 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3346
4 | 347 | 3347 | 0806025028 | Region VIII (Eastern Visayas) | Samar | San Jorge | Gayondato | 12.0388 | 124.8965 | R | 251 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.21 | 85.16 | Tier 2 High GIDA (Score 40.0–49.9) | 67.45 | 47.15 | 67.45 |  | F - Nearest node and line over 5 km | 85.21 | 85.16 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3347
4 | 348 | 3348 | PH0003348 | VI | Iloilo | Iloilo City | Santo Rosario-Duran | 10.6925 | 122.5767 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.55 | 1.24 | Tier 2 High GIDA (Score 40.0–49.9) | 67.44 | 47.15 | 67.44 |  | D - Other node or line within 3 km | 2.55 | 1.24 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3348
4 | 349 | 3349 | 1408104004 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Bulu | 17.9856 | 121.2829 | R | 408 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.41 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 67.44 | 47.15 | 67.44 |  | F - Nearest node and line over 5 km | 11.41 | 21.57 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3349
4 | 350 | 3350 | 1908822003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Itaw | 17.2551 | 122.2291 | R | 1755 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 67.44 | 47.15 | 67.44 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3350
4 | 351 | 3351 | 1907004010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Maruwa | 17.2558 | 122.2298 | R | 1150 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.05 | 69.18 | Tier 2 High GIDA (Score 40.0–49.9) | 67.44 | 47.15 | 67.44 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3351
4 | 352 | 3352 | 1705301020 | MIMAROPA Region | Palawan | Aborlan | Culandanum | 9.5556 | 118.2971 | R | 1784 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.08 | 54.03 | Tier 2 High GIDA (Score 40.0–49.9) | 67.43 | 47.14 | 67.43 |  | F - Nearest node and line over 5 km | 52.08 | 54.02 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3352
4 | 353 | 3353 | 0102820008 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Fernando | 13.9158 | 120.9391 | R | 1148 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.13 | 1.53 | Tier 2 High GIDA (Score 40.0–49.9) | 67.41 | 47.13 | 67.41 |  | D - Other node or line within 3 km | 2.07 | 2.61 | Node: SNB001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3353
4 | 354 | 3354 | 1907004006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tubig Indangan | 17.2559 | 122.2299 | R | 4140 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.44 | Tier 2 High GIDA (Score 40.0–49.9) | 67.41 | 47.13 | 67.41 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3354
4 | 355 | 3355 | PH0003355 | CAR | Benguet | Baguio City | Market Subdivision, Upper | 16.4321 | 120.5834 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 2.15 | Tier 2 High GIDA (Score 40.0–49.9) | 67.4 | 47.12 | 67.4 |  | D - Other node or line within 3 km | 1.31 | 1.44 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3355
4 | 356 | 3356 | 0907318036 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Midsalip | Guitalos | 8.0603 | 123.2475 | R | 711 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.12 | 23.38 | Tier 2 High GIDA (Score 40.0–49.9) | 67.38 | 47.11 | 67.38 |  | F - Nearest node and line over 5 km | 33.12 | 23.38 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3356
4 | 357 | 3357 | 0205703026 | Region II (Cagayan Valley) | Quirino | Diffun | Ricarte Sur | 16.5329 | 121.5005 | R | 597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.4 | 5.36 | Tier 2 High GIDA (Score 40.0–49.9) | 67.38 | 47.1 | 67.38 |  | E - Nearest node or line 3-5 km | 3.4 | 5.35 | Node: CBQ001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3357
4 | 358 | 3358 | 0806025033 | Region VIII (Eastern Visayas) | Samar | San Jorge | Cabugao | 12.0293 | 124.8961 | R | 132 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.19 | 84.14 | Tier 2 High GIDA (Score 40.0–49.9) | 67.37 | 47.1 | 67.37 |  | F - Nearest node and line over 5 km | 84.19 | 84.14 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3358
4 | 359 | 3359 | 0402123005 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 4 Poblacion | 14.3119 | 121.0215 | R | 4992 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 4.16 | Tier 2 High GIDA (Score 40.0–49.9) | 67.37 | 47.09 | 67.37 |  | D - Other node or line within 3 km | 2.19 | 3.07 | Node: CRC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3359
4 | 360 | 3360 | 0802606041 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | San Vicente | 12.1154 | 125.2708 | R | 466 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 101.68 | 104.37 | Tier 2 High GIDA (Score 40.0–49.9) | 67.35 | 47.09 | 67.35 |  | F - Nearest node and line over 5 km | 101.68 | 104.36 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3360
4 | 361 | 3361 | 0200906002 | Region II (Cagayan Valley) | Batanes | Uyugan | Imnajbu | 20.3775 | 121.9696 | R | 178 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 216.4 | 209.42 | Tier 2 High GIDA (Score 40.0–49.9) | 67.35 | 47.09 | 67.35 |  | F - Nearest node and line over 5 km | 212.52 | 209.42 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3361
4 | 362 | 3362 | 0307702003 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 3 | 16.1288 | 122.0595 | R | 177 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.76 | 1.42 | Tier 2 High GIDA (Score 40.0–49.9) | 67.34 | 47.08 | 67.34 |  | F - Nearest node and line over 5 km | 8.93 | 28.75 | Node: CSA002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3362
4 | 363 | 3363 | 0405622077 | Region IV-A (CALABARZON) | Quezon | Lopez | Santa Rosa | 13.8818 | 122.2403 | R | 304 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.09 | 2.98 | Tier 2 High GIDA (Score 40.0–49.9) | 67.34 | 47.07 | 67.34 |  | C - Line within 0.5 km; node over 1 km | 2.44 | 0.37 | Line: GCQ001 TO TKQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3363
4 | 364 | 3364 | 1408104021 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Tuyangan | 18.1065 | 121.1164 | R | 227 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.85 | 20.92 | Tier 2 High GIDA (Score 40.0–49.9) | 67.33 | 47.07 | 67.33 |  | F - Nearest node and line over 5 km | 11.85 | 36.48 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3364
4 | 365 | 3365 | 0804812010 | Region VIII (Eastern Visayas) | Northern Samar | Mapanas | Naparasan | 12.4231 | 125.2345 | R | 526 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 124.99 | 124.16 | Tier 2 High GIDA (Score 40.0–49.9) | 67.33 | 47.07 | 67.33 |  | F - Nearest node and line over 5 km | 124.99 | 124.09 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3365
4 | 366 | 3366 | 0806022024 | Region VIII (Eastern Visayas) | Samar | Paranas | Pagsa-ogan | 11.8662 | 125.082 | R | 419 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.46 | 59.4 | Tier 2 High GIDA (Score 40.0–49.9) | 67.32 | 47.07 | 67.32 |  | F - Nearest node and line over 5 km | 70.21 | 73.12 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3366
4 | 367 | 3367 | 0500515033 | Region V (Bicol Region) | Albay | Rapu-Rapu | Tinocawan | 13.2522 | 123.9303 | R | 647 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.72 | 16.68 | Tier 2 High GIDA (Score 40.0–49.9) | 67.31 | 47.06 | 67.31 |  | F - Nearest node and line over 5 km | 15.72 | 16.5 | Node: MNT001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3367
4 | 368 | 3368 | 0403425027 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 2 | 14.3306 | 121.0315 | U | 13146 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5 | 4.91 | Tier 2 High GIDA (Score 40.0–49.9) | 67.31 | 47.05 | 67.31 |  | D - Other node or line within 3 km | 1.81 | 1.56 | Line: AE SPL002 TO SPL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3368
4 | 369 | 3369 | 1380900014 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tanza 1 | 14.6446 | 120.954 | U | 15649 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.51 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 67.3 | 47.05 | 67.3 |  | D - Other node or line within 3 km | 1.51 | 2.64 | Node: NAV001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3369
4 | 370 | 3370 | 1108210009 | Region XI (Davao Region) | Davao de Oro | New Bataan | Pagsabangan | 7.6319 | 126.2261 | R | 517 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.68 | 26.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.3 | 47.05 | 67.3 |  | F - Nearest node and line over 5 km | 28.68 | 26.87 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3370
4 | 371 | 3371 | 1907004007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Ubol | 17.2558 | 122.2299 | R | 1993 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3371
4 | 372 | 3372 | PH0003372 | CAR | Benguet | Baguio City | Middle Quezon Hill Subdivision | 16.4278 | 120.5811 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.86 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | D - Other node or line within 3 km | 1.34 | 1.62 | Node: BGC007 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3372
4 | 373 | 3373 | 1108603039 | Region XI (Davao Region) | Davao Occidental | Malita | Tingolo | 6.3535 | 125.6301 | R | 2289 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.07 | 34.55 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | F - Nearest node and line over 5 km | 36.07 | 34.55 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3373
4 | 374 | 3374 | 1401103007 | Cordillera Administrative Region (CAR) | Benguet | Bakun | Kayapa | 16.7574 | 120.6991 | R | 1508 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 8.55 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | B - Node 0.5-1 km | 0.68 | 8.52 | Node: KIB002 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3374
4 | 375 | 3375 | 0200906001 | Region II (Cagayan Valley) | Batanes | Uyugan | Kayvaluganan | 20.3508 | 121.9387 | R | 371 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 212.47 | 206.78 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | F - Nearest node and line over 5 km | 209.88 | 206.78 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3375
4 | 376 | 3376 | 1705323011 | MIMAROPA Region | Palawan | Rizal | Taburi | 8.7258 | 117.3748 | U | 5624 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 187.01 | 189.26 | Tier 2 High GIDA (Score 40.0–49.9) | 67.29 | 47.04 | 67.29 |  | F - Nearest node and line over 5 km | 187.01 | 189.02 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3376
4 | 377 | 3377 | 1908713006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Bungcog | 17.254 | 122.2281 | R | 5316 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 67.28 | 47.04 | 67.28 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3377
4 | 378 | 3378 | 0300806007 | Region III (Central Luzon) | Bataan | Limay | Poblacion | 14.5561 | 120.5981 | R | 682 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.43 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 67.28 | 47.03 | 67.28 |  | C - Line within 0.5 km; node over 1 km | 2.08 | 0.25 | Line: 24 CORE 2X12 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3378
4 | 379 | 3379 | 1908709011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Limbayan | 17.2541 | 122.2282 | R | 5270 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 67.27 | 47.03 | 67.27 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3379
4 | 380 | 3380 | 1705318033 | MIMAROPA Region | Palawan | Roxas | Barangay VI Pob. | 10.2526 | 119.384 | R | 712 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.44 | 8.44 | Tier 2 High GIDA (Score 40.0–49.9) | 67.26 | 47.02 | 67.26 |  | F - Nearest node and line over 5 km | 8.44 | 8.4 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3380
4 | 381 | 3381 | PH0003381 | VII | Cebu | Cebu City | Kamagayan (Pob.) | 10.2996 | 123.8961 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.53 | 4.56 | Tier 2 High GIDA (Score 40.0–49.9) | 67.25 | 47.01 | 67.25 |  | A - Node within 0.5 km | 0.34 | 0.03 | Line: DANAO - CEBU | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3381
4 | 382 | 3382 | 1908709003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Cotongan | 17.2541 | 122.2282 | R | 4067 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 67.24 | 47.01 | 67.24 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3382
4 | 383 | 3383 | 0401005065 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 19 | 13.7798 | 121.0421 | U | 411 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.66 | 7.2 | Tier 2 High GIDA (Score 40.0–49.9) | 67.24 | 47.01 | 67.24 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.23 | Line: LEMERY TO SAN JUAN CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3383
4 | 384 | 3384 | 1381300086 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-B | 14.6327 | 121.0613 | U | 4103 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 67.23 | 47 | 67.23 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.1 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3384
4 | 385 | 3385 | 0806025016 | Region VIII (Eastern Visayas) | Samar | San Jorge | Libertad | 12.0487 | 124.9173 | R | 167 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.9 | 86.85 | Tier 2 High GIDA (Score 40.0–49.9) | 67.23 | 47 | 67.23 |  | F - Nearest node and line over 5 km | 86.9 | 86.85 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3385
4 | 386 | 3386 | 0102934018 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | Capangpangan | 17.5719 | 120.3947 | R | 1764 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.46 | 1 | Tier 2 High GIDA (Score 40.0–49.9) | 67.23 | 47 | 67.23 |  | D - Other node or line within 3 km | 2.46 | 0.92 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 3386
4 | 387 | 3387 | 0405801005 | Region IV-A (CALABARZON) | Rizal | Angono | Kalayaan | 14.5297 | 121.1536 | U | 19309 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.27 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 67.22 | 46.99 | 67.22 |  | A - Node within 0.5 km | 0.27 | 0.02 | Line: TAYTAY TO SNL001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3387
4 | 388 | 3388 | 1206506008 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Lebak | Kalamongog | 6.7285 | 124.0768 | R | 2967 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.04 | 66.01 | Tier 2 High GIDA (Score 40.0–49.9) | 67.21 | 46.99 | 67.21 |  | F - Nearest node and line over 5 km | 66.04 | 66.01 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3388
4 | 389 | 3389 | PH0003389 | I | Ilocos Norte | Laoag City | Bgy. No. 14, Santo Tomas (Pob.) | 18.1947 | 120.5937 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 67.21 | 46.99 | 67.21 |  | C - Line within 0.5 km; node over 1 km | 1.55 | 0.08 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3389
4 | 390 | 3390 | PH0003390 | IV-A | Laguna | San Pablo City | Barangay III-C (Pob.) | 14.0687 | 121.3305 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 67.21 | 46.99 | 67.21 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.13 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3390
4 | 391 | 3391 | 0200906004 | Region II (Cagayan Valley) | Batanes | Uyugan | Kayuganan | 20.3493 | 121.9383 | R | 306 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 212.31 | 206.63 | Tier 2 High GIDA (Score 40.0–49.9) | 67.19 | 46.98 | 67.19 |  | F - Nearest node and line over 5 km | 209.73 | 206.63 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3391
4 | 392 | 3392 | PH0003392 | NCR | Metro Manila | Caloocan City | Barangay 177 | 14.7465 | 121.0505 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.47 | 17.23 | Tier 2 High GIDA (Score 40.0–49.9) | 67.18 | 46.96 | 67.18 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.34 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3392
4 | 393 | 3393 | 0405647047 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Pook | 14.0256 | 121.5905 | R | 238 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 67.17 | 46.96 | 67.17 |  | A - Node within 0.5 km | 0.39 | 0.22 | Line: LILIW TO LUCENA AE | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3393
4 | 394 | 3394 | 0806025017 | Region VIII (Eastern Visayas) | Samar | San Jorge | Lincoro | 11.9792 | 124.8861 | R | 266 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 78.53 | 78.48 | Tier 2 High GIDA (Score 40.0–49.9) | 67.16 | 46.95 | 67.16 |  | F - Nearest node and line over 5 km | 78.53 | 78.48 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3394
4 | 395 | 3395 | 0806025031 | Region VIII (Eastern Visayas) | Samar | San Jorge | Bay-ang | 12.0148 | 124.9494 | R | 156 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.4 | 84.34 | Tier 2 High GIDA (Score 40.0–49.9) | 67.16 | 46.95 | 67.16 |  | F - Nearest node and line over 5 km | 84.4 | 84.34 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3395
4 | 396 | 3396 | 1381300038 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa II | 7.7911 | 125.1434 | U | 1754 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 67.16 | 46.95 | 67.16 |  | F - Nearest node and line over 5 km | 8.21 | 6.98 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3396
4 | 397 | 3397 | 0806025026 | Region VIII (Eastern Visayas) | Samar | San Jorge | Sinit-an | 11.8986 | 124.8784 | R | 164 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.69 | 69.64 | Tier 2 High GIDA (Score 40.0–49.9) | 67.16 | 46.95 | 67.16 |  | F - Nearest node and line over 5 km | 69.69 | 69.64 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3397
4 | 398 | 3398 | 0806009002 | Region VIII (Eastern Visayas) | Samar | Jiabong | Bugho | 11.8976 | 125.0216 | R | 281 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.19 | 75.56 | Tier 2 High GIDA (Score 40.0–49.9) | 67.15 | 46.95 | 67.15 |  | F - Nearest node and line over 5 km | 73.19 | 75.56 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3398
4 | 399 | 3399 | 0501711019 | Region V (Bicol Region) | Camarines Sur | Caramoan | Haponan | 13.84 | 123.8486 | R | 781 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.48 | 41.93 | Tier 2 High GIDA (Score 40.0–49.9) | 67.15 | 46.94 | 67.15 |  | F - Nearest node and line over 5 km | 7.48 | 41.9 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3399
4 | 400 | 3400 | 0402106076 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina II | 14.2597 | 120.9899 | R | 3690 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.76 | 4.86 | Tier 2 High GIDA (Score 40.0–49.9) | 67.14 | 46.94 | 67.14 |  | D - Other node or line within 3 km | 2.85 | 1.69 | Line: SILANG | Route options survey candidate: compare actual node lateral with approved line tap. | 3400
4 | 401 | 3401 | 0401005055 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 1 | 13.8163 | 121.0892 | U | 792 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.66 | 6.1 | Tier 2 High GIDA (Score 40.0–49.9) | 67.13 | 46.93 | 67.13 |  | D - Other node or line within 3 km | 4.18 | 1.52 | Line: UG_LPB001 TO BCY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3401
4 | 402 | 3402 | 1381300095 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Agustin | 14.7297 | 121.0352 | U | 26419 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 67.13 | 46.93 | 67.13 |  | C - Line within 0.5 km; node over 1 km | 1.17 | 0.15 | Line: Aerial 216C MTF | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3402
4 | 403 | 3403 | 0201528033 | Region II (Cagayan Valley) | Cagayan | Tuao | Malalinta | 17.6591 | 121.4887 | R | 970 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.79 | 6.28 | Tier 2 High GIDA (Score 40.0–49.9) | 67.12 | 46.92 | 67.12 |  | D - Other node or line within 3 km | 2.79 | 6.21 | Node: TUC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3403
4 | 404 | 3404 | 1903601012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Gurain | 17.2542 | 122.2291 | U | 471 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 67.12 | 46.92 | 67.12 |  | F - Nearest node and line over 5 km | 29.39 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3404
4 | 405 | 3405 | 0501714006 | Region V (Bicol Region) | Camarines Sur | Garchitorena | Cagnipa | 13.9578 | 123.666 | R | 720 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 35.09 | Tier 2 High GIDA (Score 40.0–49.9) | 67.12 | 46.92 | 67.12 |  | F - Nearest node and line over 5 km | 29.51 | 34.86 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3405
4 | 406 | 3406 | 1908711008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Mastura | Simuay/Seashore | 17.2541 | 122.2281 | R | 4505 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 67.1 | 46.91 | 67.1 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3406
4 | 407 | 3407 | 0501606017 | Region V (Bicol Region) | Camarines Norte | Labo | Cabatuhan | 14.1189 | 122.5375 | R | 1650 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.92 | 5.5 | Tier 2 High GIDA (Score 40.0–49.9) | 67.1 | 46.91 | 67.1 |  | F - Nearest node and line over 5 km | 10.92 | 5.5 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3407
4 | 408 | 3408 | PH0003408 | IV-A | Cavite | Imus City | Bayan Luma I | 14.4128 | 120.9302 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.33 | 2.3 | Tier 2 High GIDA (Score 40.0–49.9) | 67.1 | 46.91 | 67.1 |  | D - Other node or line within 3 km | 1.3 | 3.65 | Node: IMC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3408
4 | 409 | 3409 | 0806025012 | Region VIII (Eastern Visayas) | Samar | San Jorge | Hernandez | 11.9006 | 124.8949 | R | 120 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.45 | 70.4 | Tier 2 High GIDA (Score 40.0–49.9) | 67.09 | 46.9 | 67.09 |  | F - Nearest node and line over 5 km | 70.45 | 70.4 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3409
4 | 410 | 3410 | 0806025011 | Region VIII (Eastern Visayas) | Samar | San Jorge | Guadalupe | 11.8982 | 124.8857 | R | 133 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.89 | 69.84 | Tier 2 High GIDA (Score 40.0–49.9) | 67.09 | 46.9 | 67.09 |  | F - Nearest node and line over 5 km | 69.89 | 69.84 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3410
4 | 411 | 3411 | 1608501002 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Catadman | 10.0871 | 125.5808 | R | 879 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.87 | 22.87 | Tier 2 High GIDA (Score 40.0–49.9) | 67.07 | 46.89 | 67.07 |  | F - Nearest node and line over 5 km | 34.56 | 34.46 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3411
4 | 412 | 3412 | 1102319016 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo Poblacion | 7.4294 | 125.8013 | U | 2994 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 67.06 | 46.88 | 67.06 |  | D - Other node or line within 3 km | 1.32 | 0.51 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 3412
4 | 413 | 3413 | PH0003413 | III | Pampanga | San Fernando City | Lourdes | 15.0314 | 120.6878 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.14 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 67.06 | 46.88 | 67.06 |  | C - Line within 0.5 km; node over 1 km | 1.25 | 0.14 | Line: 24 CORE (3X8) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3413
4 | 414 | 3414 | 1381600033 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Canumay East | 14.7371 | 120.9896 | U | 14866 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 67.06 | 46.88 | 67.06 |  | C - Line within 0.5 km; node over 1 km | 2.28 | 0.02 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3414
4 | 415 | 3415 | PH0003415 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Natangcopan | 17.2543 | 122.2283 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 67.06 | 46.88 | 67.06 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3415
4 | 416 | 3416 | 1408104015 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Madduang | 18.0128 | 121.1267 | R | 637 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.8 | 12.82 | Tier 2 High GIDA (Score 40.0–49.9) | 67.06 | 46.88 | 67.06 |  | F - Nearest node and line over 5 km | 5.8 | 31.77 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3416
4 | 417 | 3417 | 1408105019 | Cordillera Administrative Region (CAR) | Apayao | Luna | Luyon | 18.351 | 121.3693 | R | 452 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 2.19 | Tier 2 High GIDA (Score 40.0–49.9) | 67.05 | 46.87 | 67.05 |  | D - Other node or line within 3 km | 2.23 | 3.86 | Node: LAY001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3417
4 | 418 | 3418 | PH0003418 | CAR | Benguet | Baguio City | General Emilio F. Aguinaldo | 16.3947 | 120.5967 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.43 | 4.35 | Tier 2 High GIDA (Score 40.0–49.9) | 67.04 | 46.87 | 67.04 |  | B - Node 0.5-1 km | 0.82 | 0.78 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3418
4 | 419 | 3419 | 0806012006 | Region VIII (Eastern Visayas) | Samar | Motiong | Beri | 11.9947 | 124.9626 | R | 87 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.81 | 82.74 | Tier 2 High GIDA (Score 40.0–49.9) | 67.04 | 46.87 | 67.04 |  | F - Nearest node and line over 5 km | 82.81 | 82.74 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3419
4 | 420 | 3420 | 0806025013 | Region VIII (Eastern Visayas) | Samar | San Jorge | Himay | 11.9603 | 124.8899 | R | 424 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.62 | 76.57 | Tier 2 High GIDA (Score 40.0–49.9) | 67.03 | 46.86 | 67.03 |  | F - Nearest node and line over 5 km | 76.62 | 76.57 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3420
4 | 421 | 3421 | PH0003421 | CAR | Benguet | Baguio City | Lourdes Subdivision, Lower | 16.4269 | 120.5933 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.23 | 1.8 | Tier 2 High GIDA (Score 40.0–49.9) | 67.02 | 46.86 | 67.02 |  | A - Node within 0.5 km | 0.15 | 1.34 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3421
4 | 422 | 3422 | 0806025021 | Region VIII (Eastern Visayas) | Samar | San Jorge | Ranera | 11.9508 | 124.8736 | R | 333 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 75.12 | 75.07 | Tier 2 High GIDA (Score 40.0–49.9) | 67.02 | 46.86 | 67.02 |  | F - Nearest node and line over 5 km | 75.12 | 75.07 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3422
4 | 423 | 3423 | 0806004042 | Region VIII (Eastern Visayas) | Samar | Calbiga | Hindang | 11.5492 | 125.1021 | R | 125 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.1 | 38.78 | Tier 2 High GIDA (Score 40.0–49.9) | 67.02 | 46.85 | 67.02 |  | F - Nearest node and line over 5 km | 36.1 | 38.78 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3423
4 | 424 | 3424 | PH0003424 | X | Misamis Oriental | Cagayan De Oro City | Puntod | 8.4998 | 124.6572 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 1.64 | Tier 2 High GIDA (Score 40.0–49.9) | 67.02 | 46.85 | 67.02 |  | D - Other node or line within 3 km | 1.53 | 1.64 | Node: COM004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3424
4 | 425 | 3425 | 0806020002 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Awang | 11.8993 | 124.7455 | R | 160 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.2 | 67.17 | Tier 2 High GIDA (Score 40.0–49.9) | 67.02 | 46.85 | 67.02 |  | F - Nearest node and line over 5 km | 66.95 | 66.92 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3425
4 | 426 | 3426 | 1903605002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Baguiangun | 17.2547 | 122.2284 | R | 1053 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.53 | Tier 2 High GIDA (Score 40.0–49.9) | 67.01 | 46.85 | 67.01 |  | F - Nearest node and line over 5 km | 29.36 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3426
4 | 427 | 3427 | PH0003427 | CAR | Benguet | Baguio City | San Antonio Village | 16.3997 | 120.5869 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 2.61 | Tier 2 High GIDA (Score 40.0–49.9) | 67.01 | 46.84 | 67.01 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.02 | Line: BAGUIO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3427
4 | 428 | 3428 | 0405811006 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan II | 14.685 | 121.1271 | U | 18821 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.34 | 0.99 | Tier 2 High GIDA (Score 40.0–49.9) | 67 | 46.84 | 67 |  | D - Other node or line within 3 km | 1.19 | 0.59 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3428
4 | 429 | 3429 | PH0003429 | IV-B | Palawan | Puerto Princesa City | Bagong Pag-Asa (Pob.) | 10.0189 | 118.7949 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 0.69 | Tier 2 High GIDA (Score 40.0–49.9) | 66.99 | 46.83 | 66.99 |  | F - Nearest node and line over 5 km | 8.24 | 5.86 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3429
4 | 430 | 3430 | 0403425017 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Santo Niño | 14.3678 | 121.0593 | R | 4266 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.92 | 5.05 | Tier 2 High GIDA (Score 40.0–49.9) | 66.99 | 46.83 | 66.99 |  | D - Other node or line within 3 km | 2.09 | 0.66 | Line: RELIANCE PSG001 TO BÑL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3430
4 | 431 | 3431 | 0402123022 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Pantaleon Granados | 14.3041 | 120.9909 | R | 3651 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.86 | 4.02 | Tier 2 High GIDA (Score 40.0–49.9) | 66.99 | 46.83 | 66.99 |  | D - Other node or line within 3 km | 1.99 | 3.51 | Node: DMC005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3431
4 | 432 | 3432 | 0504102007 | Region V (Bicol Region) | Masbate | Baleno | Canjunday | 12.3988 | 123.5189 | R | 838 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.62 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 66.99 | 46.83 | 66.99 |  | F - Nearest node and line over 5 km | 8.62 | 9.35 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3432
4 | 433 | 3433 | 1380608004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 660-A | 14.5833 | 120.9852 | U | 2532 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.08 | 78.74 | Tier 2 High GIDA (Score 40.0–49.9) | 66.97 | 46.82 | 66.97 |  | B - Node 0.5-1 km | 0.81 | 0.31 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3433
4 | 434 | 3434 | 1380300023 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | San Antonio | 14.5621 | 121.0082 | U | 8607 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 66.97 | 46.82 | 66.97 |  | C - Line within 0.5 km; node over 1 km | 1.41 | 0.28 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3434
4 | 435 | 3435 | 0402123006 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 5 Poblacion | 14.3041 | 121.0076 | U | 17917 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.48 | 4.63 | Tier 2 High GIDA (Score 40.0–49.9) | 66.97 | 46.82 | 66.97 |  | D - Other node or line within 3 km | 2.48 | 4.63 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3435
4 | 436 | 3436 | PH0003436 | IV-A | Cavite | City of Bacoor | Aniban 1 | 14.4617 | 120.9428 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 4.47 | Tier 2 High GIDA (Score 40.0–49.9) | 66.96 | 46.81 | 66.96 |  | D - Other node or line within 3 km | 1.78 | 1.55 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 3436
4 | 437 | 3437 | 1381600005 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Bignay | 14.7457 | 121.0021 | U | 50425 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.02 | Tier 2 High GIDA (Score 40.0–49.9) | 66.95 | 46.8 | 66.95 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0 | Line: Aerial 96C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3437
4 | 438 | 3438 | 0607903006 | Region VI (Western Visayas) | Guimaras | Nueva Valencia | Guiwanon | 10.3913 | 122.6153 | R | 1929 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.25 | 23.94 | Tier 2 High GIDA (Score 40.0–49.9) | 66.95 | 46.8 | 66.95 |  | F - Nearest node and line over 5 km | 24.25 | 23.93 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3438
4 | 439 | 3439 | 1381300042 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | N.S. Amoranto | 17.3538 | 121.6036 | U | 6202 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.94 | 46.8 | 66.94 |  | C - Line within 0.5 km; node over 1 km | 4.98 | 0.07 | Line: QUEZON | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3439
4 | 440 | 3440 | 1003507005 | Region X (Northern Mindanao) | Lanao del Norte | Kauswagan | Inudaran | 8.1862 | 124.0932 | R | 951 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.69 | 1.5 | Tier 2 High GIDA (Score 40.0–49.9) | 66.94 | 46.8 | 66.94 |  | C - Line within 0.5 km; node over 1 km | 16.87 | 0.08 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3440
4 | 441 | 3441 | PH0003441 | NCR | Metro Manila | Caloocan City | Barangay 168 | 14.7411 | 121.0219 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 80.01 | 80.76 | Tier 2 High GIDA (Score 40.0–49.9) | 66.94 | 46.79 | 66.94 |  | A - Node within 0.5 km | 0.12 | 0.06 | Line: Aerial 216C MTF | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3441
4 | 442 | 3442 | 0402123003 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 2 Poblacion | 14.3035 | 121.0187 | R | 4382 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.77 | 2.6 | Tier 2 High GIDA (Score 40.0–49.9) | 66.93 | 46.79 | 66.93 |  | D - Other node or line within 3 km | 2.62 | 3.47 | Node: CRC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3442
4 | 443 | 3443 | 0504118025 | Region V (Bicol Region) | Masbate | San Fernando | Talisay | 12.4803 | 123.6874 | R | 641 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.66 | 13.05 | Tier 2 High GIDA (Score 40.0–49.9) | 66.93 | 46.79 | 66.93 |  | F - Nearest node and line over 5 km | 15.66 | 15.44 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3443
4 | 444 | 3444 | 0806006016 | Region VIII (Eastern Visayas) | Samar | Daram | Calawan-an | 11.5734 | 124.7785 | R | 910 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.94 | 31.88 | Tier 2 High GIDA (Score 40.0–49.9) | 66.92 | 46.78 | 66.92 |  | F - Nearest node and line over 5 km | 31.94 | 31.88 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3444
4 | 445 | 3445 | 1908710012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Inawan | 17.2532 | 122.2275 | R | 610 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 66.92 | 46.78 | 66.92 |  | F - Nearest node and line over 5 km | 29.18 | 34.09 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3445
4 | 446 | 3446 | 1903601001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Ampao | 17.2547 | 122.2287 | U | 1080 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 66.88 | 46.76 | 66.88 |  | F - Nearest node and line over 5 km | 29.39 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3446
4 | 447 | 3447 | 1908811006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Gen. S.K. Pendatun | Lasangan | 17.255 | 122.2291 | R | 2163 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.88 | 46.76 | 66.88 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3447
4 | 448 | 3448 | 0103318004 | Region I (Ilocos Region) | La Union | Santol | Lettac Sur | 16.7382 | 120.454 | R | 1348 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.23 | 6.06 | Tier 2 High GIDA (Score 40.0–49.9) | 66.87 | 46.75 | 66.87 |  | F - Nearest node and line over 5 km | 9.23 | 6.05 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3448
4 | 449 | 3449 | 1903601004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Balut | 17.2546 | 122.2284 | R | 689 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 29.36 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3449
4 | 450 | 3450 | 1608501008 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Geotina | 10.0618 | 125.5988 | R | 1231 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.72 | 34.73 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 32.5 | 32.42 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3450
4 | 451 | 3451 | 1903605003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Balut Maito | 17.2548 | 122.2288 | R | 697 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3451
4 | 452 | 3452 | 1903628012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Campo | 17.2549 | 122.2289 | R | 785 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 29.42 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3452
4 | 453 | 3453 | 1903628046 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Metadicop | 17.2546 | 122.2298 | R | 593 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.27 | 35.1 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 29.47 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3453
4 | 454 | 3454 | 1903628031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Polo | 17.2549 | 122.2289 | R | 1097 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.42 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 66.86 | 46.74 | 66.86 |  | F - Nearest node and line over 5 km | 29.42 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3454
4 | 455 | 3455 | 1381300141 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Greater Lagro | 14.7306 | 121.0662 | U | 24558 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 66.85 | 46.74 | 66.85 |  | A - Node within 0.5 km | 0.5 | 0.5 | Node: QCY093 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3455
4 | 456 | 3456 | 0205006014 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Lurad | 16.601 | 121.3601 | R | 674 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.59 | 2.44 | Tier 2 High GIDA (Score 40.0–49.9) | 66.85 | 46.73 | 66.85 |  | D - Other node or line within 3 km | 6.59 | 2.44 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Route options survey candidate: compare actual node lateral with approved line tap. | 3456
4 | 457 | 3457 | 1380400011 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Maysilo | 14.6827 | 120.9617 | U | 10703 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.2 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 66.85 | 46.73 | 66.85 |  | A - Node within 0.5 km | 0.2 | 0.59 | Node: MAL005 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3457
4 | 458 | 3458 | 1204716006 | Region XII (SOCCSKSARGEN) | Cotabato | Banisilan | Kalawaig | 7.5713 | 124.7451 | R | 575 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.22 | 19.62 | Tier 2 High GIDA (Score 40.0–49.9) | 66.84 | 46.73 | 66.84 |  | F - Nearest node and line over 5 km | 18.22 | 19.59 | Node: KDB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3458
4 | 459 | 3459 | 1903628038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Wago | 17.2544 | 122.2292 | R | 687 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.66 | 33.86 | Tier 2 High GIDA (Score 40.0–49.9) | 66.84 | 46.73 | 66.84 |  | F - Nearest node and line over 5 km | 29.41 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3459
4 | 460 | 3460 | 1705310007 | MIMAROPA Region | Palawan | Cuyo | Funda | 10.8127 | 120.984 | R | 748 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.35 | 104.34 | Tier 2 High GIDA (Score 40.0–49.9) | 66.84 | 46.72 | 66.84 |  | F - Nearest node and line over 5 km | 104.35 | 104.33 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3460
4 | 461 | 3461 | 0804806030 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | Osang | 12.309 | 125.1753 | R | 352 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 120.39 | 121.33 | Tier 2 High GIDA (Score 40.0–49.9) | 66.83 | 46.72 | 66.83 |  | F - Nearest node and line over 5 km | 120.39 | 121.24 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3461
4 | 462 | 3462 | 1908709004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Datu Macarimbang Biruar | 17.2541 | 122.2282 | R | 3883 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 66.83 | 46.72 | 66.83 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3462
4 | 463 | 3463 | 1903605009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Dansalan Dacsula | 17.255 | 122.2293 | R | 882 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.91 | 33.64 | Tier 2 High GIDA (Score 40.0–49.9) | 66.83 | 46.72 | 66.83 |  | F - Nearest node and line over 5 km | 29.46 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3463
4 | 464 | 3464 | PH0003464 | BARMM (LaMa+SGA) | Maguindanao del Norte | Cotabato City | Rosary Heights II | 7.2201 | 124.2598 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.21 | 20.3 | Tier 2 High GIDA (Score 40.0–49.9) | 66.82 | 46.71 | 66.82 |  | F - Nearest node and line over 5 km | 59.27 | 58.16 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3464
4 | 465 | 3465 | 1003516019 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Pansor | 8.0429 | 124.1939 | R | 1502 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.58 | 7.19 | Tier 2 High GIDA (Score 40.0–49.9) | 66.82 | 46.71 | 66.82 |  | F - Nearest node and line over 5 km | 9.58 | 7.11 | Line: Pantar Done Layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3465
4 | 466 | 3466 | 1903605028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Soldaroro | 17.2548 | 122.2288 | R | 1105 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.71 | 66.81 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3466
4 | 467 | 3467 | 0402106028 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Esteban | 14.2972 | 120.9503 | R | 4825 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 1.99 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.71 | 66.81 |  | B - Node 0.5-1 km | 0.97 | 0.17 | Line: NCC001 TO TGY001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3467
4 | 468 | 3468 | 1908709025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Tuca-Maror | 17.2541 | 122.2282 | R | 4924 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.71 | 66.81 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3468
4 | 469 | 3469 | 0402106024 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Saint Peter I | 14.2998 | 120.9667 | R | 2408 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.51 | 3.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.71 | 66.81 |  | B - Node 0.5-1 km | 0.86 | 0.86 | Node: DMC002 - TYPE 2 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3469
4 | 470 | 3470 | 1204716007 | Region XII (SOCCSKSARGEN) | Cotabato | Banisilan | Kiaring | 7.3755 | 124.6771 | R | 1749 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.31 | 11.6 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.71 | 66.81 |  | F - Nearest node and line over 5 km | 23.31 | 11.6 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3470
4 | 471 | 3471 | 1403201012 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Poswoy | 17.5321 | 121.1481 | R | 977 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.61 | 16.53 | Tier 2 High GIDA (Score 40.0–49.9) | 66.81 | 46.7 | 66.81 |  | F - Nearest node and line over 5 km | 20.61 | 16.37 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3471
4 | 472 | 3472 | 1705312009 | MIMAROPA Region | Palawan | El Nido | New Ibajay | 11.3264 | 119.4932 | R | 4144 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.66 | 37.92 | Tier 2 High GIDA (Score 40.0–49.9) | 66.8 | 46.7 | 66.8 |  | F - Nearest node and line over 5 km | 5.23 | 55.83 | Node: ENW002 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3472
4 | 473 | 3473 | 1908709009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Kabuan | 17.2541 | 122.2281 | R | 3495 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 66.8 | 46.7 | 66.8 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3473
4 | 474 | 3474 | 0907203010 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Katipunan | Malasay | 8.3732 | 123.2432 | R | 1331 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.11 | 58.17 | Tier 2 High GIDA (Score 40.0–49.9) | 66.8 | 46.7 | 66.8 |  | F - Nearest node and line over 5 km | 60.11 | 58.17 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3474
4 | 475 | 3475 | 1903605018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Masolun | 17.2555 | 122.2289 | R | 1063 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.25 | 35.08 | Tier 2 High GIDA (Score 40.0–49.9) | 66.8 | 46.7 | 66.8 |  | F - Nearest node and line over 5 km | 29.46 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3475
4 | 476 | 3476 | 1903634020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Maguing | Dilimbayan | 17.2542 | 122.2282 | R | 1110 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.32 | 34.21 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.7 | 66.79 |  | F - Nearest node and line over 5 km | 29.32 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3476
4 | 477 | 3477 | 0201528026 | Region II (Cagayan Valley) | Cagayan | Tuao | San Juan | 17.6063 | 121.5246 | R | 1045 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.3 | 10.01 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.7 | 66.79 |  | F - Nearest node and line over 5 km | 7.3 | 9.89 | Node: TUC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3477
4 | 478 | 3478 | 1903609009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Ganassi | Linuk | 17.2542 | 122.2292 | R | 945 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.43 | 45.78 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.7 | 66.79 |  | F - Nearest node and line over 5 km | 29.4 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3478
4 | 479 | 3479 | 1108205009 | Region XI (Davao Region) | Davao de Oro | Maragusan | Katipunan | 7.2626 | 126.127 | R | 1697 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.55 | 27.08 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.69 | 66.79 |  | F - Nearest node and line over 5 km | 28.91 | 27.24 | Line: TAGUM - PANTUKAN SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3479
4 | 480 | 3480 | 1903604007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Bialaan | 17.2547 | 122.2288 | R | 635 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.69 | 66.79 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3480
4 | 481 | 3481 | PH0003481 | CAR | Benguet | Baguio City | Palma-Urbano | 16.4134 | 120.5904 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.25 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.69 | 66.79 |  | A - Node within 0.5 km | 0.25 | 0.03 | Line: BAGUIO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3481
4 | 482 | 3482 | PH0003482 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Sumugot | 17.2543 | 122.2283 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 66.79 | 46.69 | 66.79 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3482
4 | 483 | 3483 | 1903606058 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bubong | Dimayon | 17.2541 | 122.2293 | R | 455 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.45 | 35.57 | Tier 2 High GIDA (Score 40.0–49.9) | 66.78 | 46.69 | 66.78 |  | F - Nearest node and line over 5 km | 29.39 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3483
4 | 484 | 3484 | PH0003484 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Poblacion | 17.2538 | 122.2286 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.86 | 64.87 | Tier 2 High GIDA (Score 40.0–49.9) | 66.78 | 46.68 | 66.78 |  | F - Nearest node and line over 5 km | 29.32 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3484
4 | 485 | 3485 | PH0003485 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Pagonayan | 17.2543 | 122.2282 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.23 | 63.23 | Tier 2 High GIDA (Score 40.0–49.9) | 66.78 | 46.68 | 66.78 |  | F - Nearest node and line over 5 km | 29.32 | 34.2 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3485
4 | 486 | 3486 | 1400126006 | Cordillera Administrative Region (CAR) | Abra | Tubo | Supo | 17.2465 | 120.6862 | R | 766 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.19 | 5.29 | Tier 2 High GIDA (Score 40.0–49.9) | 66.78 | 46.68 | 66.78 |  | F - Nearest node and line over 5 km | 12.19 | 5.22 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3486
4 | 487 | 3487 | PH0003487 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Bagumbayan | 7.7453 | 124.6634 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.5 | 65.5 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 28.74 | 31.56 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3487
4 | 488 | 3488 | 1402706011 | Cordillera Administrative Region (CAR) | Ifugao | Mayoyao | Chumang | 16.9742 | 121.233 | R | 1064 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 19.09 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | D - Other node or line within 3 km | 1.22 | 20.99 | Node: MOF001 - TYPE 4 | Route options survey candidate: compare actual node lateral with approved line tap. | 3488
4 | 489 | 3489 | 0401019014 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 9 | 14.0615 | 120.658 | U | 766 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6 | 2.34 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | D - Other node or line within 3 km | 2.78 | 1.11 | Line: NSB001 TO BYB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3489
4 | 490 | 3490 | PH0003490 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Ranao-Baning | 17.2549 | 122.2281 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.83 | 63.84 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.35 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3490
4 | 491 | 3491 | 1903628041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Gaput | 17.2549 | 122.2288 | R | 642 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.58 | 34.01 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.41 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3491
4 | 492 | 3492 | 1381000012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | San Antonio | 14.4608 | 121.0307 | U | 71481 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | B - Node 0.5-1 km | 0.84 | 0.14 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3492
4 | 493 | 3493 | 1903628042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Madaya | 17.2556 | 122.229 | R | 816 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.19 | 35.41 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.48 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3493
4 | 494 | 3494 | 1903628016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Dinaigan | 17.2557 | 122.2293 | R | 641 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28 | 32.88 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.51 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3494
4 | 495 | 3495 | PH0003495 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Bandara-Ingud | 17.2535 | 122.2277 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.77 | 63.76 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.22 | 34.13 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3495
4 | 496 | 3496 | 1908811019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Gen. S.K. Pendatun | Upper Lasangan | 17.255 | 122.2291 | R | 770 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.77 | 46.68 | 66.77 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3496
4 | 497 | 3497 | 1903634038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Maguing | Panayangan | 17.2547 | 122.2277 | R | 427 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.83 | 33.57 | Tier 2 High GIDA (Score 40.0–49.9) | 66.76 | 46.67 | 66.76 |  | F - Nearest node and line over 5 km | 29.31 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3497
4 | 498 | 3498 | PH0003498 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Salam | 17.2543 | 122.2283 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 66.76 | 46.67 | 66.76 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3498
4 | 499 | 3499 | PH0003499 | IV-A | Laguna | San Pablo City | Barangay VI-E (Pob.) | 13.9837 | 121.313 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.96 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 66.74 | 46.66 | 66.74 |  | D - Other node or line within 3 km | 1.46 | 1.4 | Line: STO. TOMAS - CANDELARIA | Route options survey candidate: compare actual node lateral with approved line tap. | 3499
4 | 500 | 3500 | 1908823004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Darampua | 17.2545 | 122.2294 | R | 2646 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.74 | 46.65 | 66.74 |  | F - Nearest node and line over 5 km | 29.43 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3500
4 | 501 | 3501 | 0907307001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumalinao | Bag-ong Misamis | 6.9445 | 122.1003 | R | 250 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.25 | 6.45 | Tier 2 High GIDA (Score 40.0–49.9) | 66.73 | 46.65 | 66.73 |  | C - Line within 0.5 km; node over 1 km | 4.8 | 0.18 | Line: CABLE INSTALLED | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3501
4 | 502 | 3502 | 1908713004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Borongotan | 17.254 | 122.2281 | R | 8927 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 66.73 | 46.65 | 66.73 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3502
4 | 503 | 3503 | 0402106038 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Roque | 14.2947 | 120.9363 | R | 3006 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.66 | 2.96 | Tier 2 High GIDA (Score 40.0–49.9) | 66.71 | 46.64 | 66.71 |  | C - Line within 0.5 km; node over 1 km | 2.49 | 0.14 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3503
4 | 504 | 3504 | 0402104015 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 4 | 14.3045 | 121.0451 | R | 684 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 1.34 | Tier 2 High GIDA (Score 40.0–49.9) | 66.71 | 46.64 | 66.71 |  | B - Node 0.5-1 km | 0.8 | 0.89 | Node: CRC002 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3504
4 | 505 | 3505 | 1380200015 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pilar | 14.4123 | 121.0059 | U | 30235 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.87 | 1.87 | Tier 2 High GIDA (Score 40.0–49.9) | 66.7 | 46.63 | 66.7 |  | D - Other node or line within 3 km | 1.87 | 1.8 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3505
4 | 506 | 3506 | PH0003506 | CAR | Benguet | Baguio City | Session Road Area | 16.4008 | 120.5867 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.22 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 66.7 | 46.63 | 66.7 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.11 | Line: BAGUIO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3506
4 | 507 | 3507 | 1381300097 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Bartolome | 14.7102 | 121.0319 | U | 53294 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 0.79 | Tier 2 High GIDA (Score 40.0–49.9) | 66.68 | 46.62 | 66.68 |  | D - Other node or line within 3 km | 1.67 | 0.78 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 3507
4 | 508 | 3508 | 0201525004 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Dungeg | 18.2349 | 121.9205 | R | 636 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 0.67 | Tier 2 High GIDA (Score 40.0–49.9) | 66.68 | 46.62 | 66.68 |  | D - Other node or line within 3 km | 1.72 | 0.67 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3508
4 | 509 | 3509 | 0201503007 | Region II (Cagayan Valley) | Cagayan | Allacapan | Capanickian Norte | 18.2144 | 121.5035 | R | 1222 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.95 | 5.49 | Tier 2 High GIDA (Score 40.0–49.9) | 66.68 | 46.61 | 66.68 |  | F - Nearest node and line over 5 km | 5.95 | 5.48 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3509
4 | 510 | 3510 | 1907004002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Manuk Mangkaw | 17.2558 | 122.2299 | R | 4168 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 66.66 | 46.6 | 66.66 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3510
4 | 511 | 3511 | PH0003511 | VII | Cebu | Cebu City | Inayawan | 10.2718 | 123.856 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.54 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 66.64 | 46.59 | 66.64 |  | C - Line within 0.5 km; node over 1 km | 1.54 | 0.06 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3511
4 | 512 | 3512 | 1403213043 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Ipil | 17.439 | 121.4846 | R | 3410 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.57 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 66.64 | 46.59 | 66.64 |  | D - Other node or line within 3 km | 4.57 | 0.95 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 3512
4 | 513 | 3513 | 1102319024 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo North | 7.4653 | 125.8138 | U | 8739 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 66.63 | 46.58 | 66.63 |  | B - Node 0.5-1 km | 0.82 | 0.81 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3513
4 | 514 | 3514 | 0301412006 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Calvario | 14.7335 | 120.961 | U | 5304 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.05 | Tier 2 High GIDA (Score 40.0–49.9) | 66.62 | 46.57 | 66.62 |  | B - Node 0.5-1 km | 0.96 | 0.04 | Line: 48 CORE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3514
4 | 515 | 3515 | 0403425026 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 1 | 14.3533 | 121.0598 | U | 24752 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.54 | 6.68 | Tier 2 High GIDA (Score 40.0–49.9) | 66.62 | 46.57 | 66.62 |  | B - Node 0.5-1 km | 0.63 | 0.25 | Line: RELIANCE PSG001 TO BÑL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3515
4 | 516 | 3516 | 1381200030 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santa Lucia | 14.5869 | 121.0983 | U | 46467 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 66.61 | 46.56 | 66.61 |  | C - Line within 0.5 km; node over 1 km | 1.61 | 0.23 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3516
4 | 517 | 3517 | PH0003517 | III | Pampanga | San Fernando City | San Jose | 15.04 | 120.6999 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.59 | 0.48 | Tier 2 High GIDA (Score 40.0–49.9) | 66.59 | 46.56 | 66.59 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.06 | Line: EXISTING | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3517
4 | 518 | 3518 | PH0003518 | CAR | Benguet | Baguio City | Honeymoon | 16.4247 | 120.606 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.54 | Tier 2 High GIDA (Score 40.0–49.9) | 66.59 | 46.55 | 66.59 |  | D - Other node or line within 3 km | 1.31 | 1.3 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3518
4 | 519 | 3519 | 0300811023 | Region III (Central Luzon) | Bataan | Pilar | Santa Rosa | 14.6772 | 120.5473 | U | 7499 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 66.58 | 46.55 | 66.58 |  | B - Node 0.5-1 km | 0.75 | 0.26 | Line: PILAR | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3519
4 | 520 | 3520 | 0806021015 | Region VIII (Eastern Visayas) | Samar | Villareal | Lawa-an | 11.5066 | 124.9039 | R | 278 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.57 | 31.68 | Tier 2 High GIDA (Score 40.0–49.9) | 66.57 | 46.54 | 66.57 |  | F - Nearest node and line over 5 km | 31.57 | 31.68 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3520
4 | 521 | 3521 | 0102916013 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Lucbuban | 17.1293 | 120.5434 | R | 562 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 9.55 | Tier 2 High GIDA (Score 40.0–49.9) | 66.57 | 46.54 | 66.57 |  | D - Other node or line within 3 km | 2.35 | 9.55 | Node: SDI001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3521
4 | 522 | 3522 | 0402106045 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Cristo | 14.3394 | 120.9556 | R | 4791 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.12 | 4.2 | Tier 2 High GIDA (Score 40.0–49.9) | 66.57 | 46.54 | 66.57 |  | D - Other node or line within 3 km | 2.12 | 4.13 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3522
4 | 523 | 3523 | 1381600028 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Rincon | 14.6993 | 120.9579 | U | 7039 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 66.54 | 46.52 | 66.54 |  | D - Other node or line within 3 km | 1.06 | 0.52 | Line: Existing 216F | Route options survey candidate: compare actual node lateral with approved line tap. | 3523
4 | 524 | 3524 | 1381200016 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Pineda | 14.5656 | 121.0665 | U | 20710 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.56 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 66.54 | 46.52 | 66.54 |  | C - Line within 0.5 km; node over 1 km | 1.56 | 0.36 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3524
4 | 525 | 3525 | 1402710008 | Cordillera Administrative Region (CAR) | Ifugao | Tinoc | Luhong | 16.6537 | 120.9581 | R | 1486 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.15 | 16.71 | Tier 2 High GIDA (Score 40.0–49.9) | 66.54 | 46.52 | 66.54 |  | F - Nearest node and line over 5 km | 13.15 | 16.71 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3525
4 | 526 | 3526 | 1381701003 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | Martires Del 96 | 14.5438 | 121.0621 | U | 5188 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 66.5 | 46.49 | 66.5 |  | B - Node 0.5-1 km | 0.68 | 0.21 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3526
4 | 527 | 3527 | 0806021011 | Region VIII (Eastern Visayas) | Samar | Villareal | Inarumbacan | 11.5117 | 124.8971 | R | 563 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.36 | 31.69 | Tier 2 High GIDA (Score 40.0–49.9) | 66.5 | 46.49 | 66.5 |  | F - Nearest node and line over 5 km | 32.36 | 31.68 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3527
4 | 528 | 3528 | 0102916007 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Bulala-Leguey | 17.1302 | 120.5755 | R | 301 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.56 | 8.2 | Tier 2 High GIDA (Score 40.0–49.9) | 66.5 | 46.49 | 66.5 |  | E - Nearest node or line 3-5 km | 4.56 | 8.06 | Node: SDI001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3528
4 | 529 | 3529 | 0402104016 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 5 | 14.3113 | 121.0398 | R | 560 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.92 | 1.47 | Tier 2 High GIDA (Score 40.0–49.9) | 66.49 | 46.49 | 66.49 |  | A - Node within 0.5 km | 0.22 | 1.1 | Node: CRC002 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3529
4 | 530 | 3530 | 1402704008 | Cordillera Administrative Region (CAR) | Ifugao | Lagawe | Buyabuyan | 16.7817 | 121.2014 | R | 504 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.64 | 6.51 | Tier 2 High GIDA (Score 40.0–49.9) | 66.48 | 46.47 | 66.48 |  | F - Nearest node and line over 5 km | 7.64 | 6.51 | Line: FOC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3530
4 | 531 | 3531 | PH0003531 | CAR | Benguet | Baguio City | Rock Quarry, Middle | 16.4283 | 120.5817 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.18 | 6.07 | Tier 2 High GIDA (Score 40.0–49.9) | 66.47 | 46.47 | 66.47 |  | D - Other node or line within 3 km | 1.32 | 1.69 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3531
4 | 532 | 3532 | 1380500011 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Hagdang Bato Libis | 14.5864 | 121.0245 | U | 7348 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 66.46 | 46.46 | 66.46 |  | A - Node within 0.5 km | 0.49 | 0.36 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3532
4 | 533 | 3533 | PH0003533 | NCR | Metro Manila | Caloocan City | Barangay 170 | 14.6233 | 120.9721 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.04 | 9.9 | Tier 2 High GIDA (Score 40.0–49.9) | 66.44 | 46.45 | 66.44 |  | A - Node within 0.5 km | 0.41 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3533
4 | 534 | 3534 | 0403407019 | Region IV-A (CALABARZON) | Laguna | Cavinti | Tibatib | 14.2788 | 121.5372 | R | 218 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.47 | 9.98 | Tier 2 High GIDA (Score 40.0–49.9) | 66.44 | 46.45 | 66.44 |  | A - Node within 0.5 km | 0.11 | 7.94 | Node: CVL003 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3534
4 | 535 | 3535 | 0201524005 | Region II (Cagayan Valley) | Cagayan | Santa Praxedes | Macatel | 18.5624 | 120.9896 | R | 151 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.28 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 66.44 | 46.45 | 66.44 |  | A - Node within 0.5 km | 0.27 | 0.15 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3535
4 | 536 | 3536 | 0802607022 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | San Roque | 11.222 | 125.4933 | R | 105 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.79 | 51.66 | Tier 2 High GIDA (Score 40.0–49.9) | 66.44 | 46.45 | 66.44 |  | F - Nearest node and line over 5 km | 52.79 | 52.79 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3536
4 | 537 | 3537 | PH0003537 | CAR | Benguet | Baguio City | Kayang-Hilltop | 16.3947 | 120.6071 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.98 | 1.23 | Tier 2 High GIDA (Score 40.0–49.9) | 66.44 | 46.45 | 66.44 |  | D - Other node or line within 3 km | 1.36 | 0.91 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 3537
4 | 538 | 3538 | 0402106036 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel | 14.3131 | 120.9906 | R | 4335 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 1.33 | Tier 2 High GIDA (Score 40.0–49.9) | 66.43 | 46.44 | 66.43 |  | D - Other node or line within 3 km | 1.13 | 3.78 | Node: DMC005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3538
4 | 539 | 3539 | 1903636012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumbayanague | Dilimbayan | 17.2542 | 122.2289 | R | 936 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.54 | Tier 2 High GIDA (Score 40.0–49.9) | 66.41 | 46.43 | 66.41 |  | F - Nearest node and line over 5 km | 29.37 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3539
4 | 540 | 3540 | 0301412025 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Zamora | 14.7352 | 120.9543 | U | 2477 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 66.41 | 46.43 | 66.41 |  | D - Other node or line within 3 km | 1.57 | 0.74 | Line: 48 CORE | Route options survey candidate: compare actual node lateral with approved line tap. | 3540
4 | 541 | 3541 | PH0003541 | III | Pampanga | San Fernando City | Santo Rosario (Pob.) | 15.0296 | 120.6913 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.65 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 66.41 | 46.43 | 66.41 |  | C - Line within 0.5 km; node over 1 km | 1.63 | 0.04 | Line: 24 CORE (3X8) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3541
4 | 542 | 3542 | 1903610026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Kasayanan West | 17.2544 | 122.2285 | R | 1171 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 2 High GIDA (Score 40.0–49.9) | 66.41 | 46.43 | 66.41 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3542
4 | 543 | 3543 | 1206505013 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Kalamansig | Obial | 6.5789 | 124.0873 | R | 2464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.91 | 65.9 | Tier 2 High GIDA (Score 40.0–49.9) | 66.41 | 46.43 | 66.41 |  | F - Nearest node and line over 5 km | 65.91 | 65.9 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3543
4 | 544 | 3544 | PH0003544 | CAR | Benguet | Baguio City | Modern Site, East | 16.4218 | 120.605 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 1.31 | Tier 2 High GIDA (Score 40.0–49.9) | 66.4 | 46.42 | 66.4 |  | D - Other node or line within 3 km | 1.15 | 1.22 | Node: BGC003 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3544
4 | 545 | 3545 | 1403211019 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | San Pedro | 17.5634 | 121.5475 | R | 751 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.86 | 8.81 | Tier 2 High GIDA (Score 40.0–49.9) | 66.4 | 46.42 | 66.4 |  | F - Nearest node and line over 5 km | 8.86 | 8.81 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3545
4 | 546 | 3546 | 0405813003 | Region IV-A (CALABARZON) | Rizal | Taytay | San Isidro | 14.5728 | 121.1314 | U | 39685 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 66.39 | 46.41 | 66.39 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.22 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3546
4 | 547 | 3547 | PH0003547 | I | Ilocos Norte | Laoag City | Bgy. No. 12, San Isidro (Pob.) | 18.1838 | 120.5374 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 1.07 | Tier 2 High GIDA (Score 40.0–49.9) | 66.38 | 46.41 | 66.38 |  | F - Nearest node and line over 5 km | 5.67 | 5.38 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3547
4 | 548 | 3548 | 0601917005 | Region VI (Western Visayas) | Capiz | Tapaz | Aglupacan | 11.209 | 122.521 | R | 182 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.45 | 5.62 | Tier 2 High GIDA (Score 40.0–49.9) | 66.35 | 46.39 | 66.35 |  | F - Nearest node and line over 5 km | 17.79 | 10.29 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3548
4 | 549 | 3549 | 1906618007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Malanta | 17.2556 | 122.2297 | R | 1805 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 66.35 | 46.38 | 66.35 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3549
4 | 550 | 3550 | 1907009021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Sikullis | 17.2558 | 122.2298 | R | 1346 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 66.35 | 46.38 | 66.35 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3550
4 | 551 | 3551 | PH0003551 | IV-A | Cavite | City of Bacoor | Talaba 3 | 14.4573 | 120.939 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.31 | 4.02 | Tier 2 High GIDA (Score 40.0–49.9) | 66.34 | 46.38 | 66.34 |  | D - Other node or line within 3 km | 1.61 | 0.99 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 3551
4 | 552 | 3552 | 1908705019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Labungan | 17.254 | 122.2282 | R | 6968 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 66.34 | 46.38 | 66.34 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3552
4 | 553 | 3553 | 1903631002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Bagumbayan | 7.6765 | 124.15 | R | 1156 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.32 | 82.15 | Tier 2 High GIDA (Score 40.0–49.9) | 66.34 | 46.38 | 66.34 |  | F - Nearest node and line over 5 km | 39.53 | 37.3 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3553
4 | 554 | 3554 | PH0003554 | VIII | Leyte | Tacloban City | Barangay 49 | 11.2398 | 124.9986 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 3.25 | Tier 2 High GIDA (Score 40.0–49.9) | 66.34 | 46.38 | 66.34 |  | A - Node within 0.5 km | 0.41 | 3.24 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3554
4 | 555 | 3555 | PH0003555 | XI | Davao Del Sur | Davao City | Barangay 39-D (Pob.) | 7.3887 | 125.4706 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 1.03 | Tier 2 High GIDA (Score 40.0–49.9) | 66.32 | 46.37 | 66.32 |  | F - Nearest node and line over 5 km | 21.58 | 17.25 | Line: KITAOTAO - DAVAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3555
4 | 556 | 3556 | 1906607007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Bulangsi | 17.2556 | 122.2296 | R | 1808 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 66.32 | 46.36 | 66.32 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3556
4 | 557 | 3557 | PH0003557 | IV-A | Cavite | City of Bacoor | Talaba 2 | 14.4591 | 120.9266 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.13 | 3.21 | Tier 2 High GIDA (Score 40.0–49.9) | 66.32 | 46.36 | 66.32 |  | D - Other node or line within 3 km | 2.77 | 0.95 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 3557
4 | 558 | 3558 | PH0003558 | IV-B | Palawan | Puerto Princesa City | Liwanag (Pob.) | 9.7404 | 118.729 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 2.68 | Tier 2 High GIDA (Score 40.0–49.9) | 66.32 | 46.36 | 66.32 |  | B - Node 0.5-1 km | 0.5 | 2.44 | Node: PPW002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3558
4 | 559 | 3559 | 1705322009 | MIMAROPA Region | Palawan | Culion | Malaking Patag | 11.8218 | 119.9468 | R | 2085 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.77 | 120.98 | Tier 2 High GIDA (Score 40.0–49.9) | 66.31 | 46.36 | 66.31 |  | F - Nearest node and line over 5 km | 32.77 | 120.83 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3559
4 | 560 | 3560 | PH0003560 | CAR | Benguet | Baguio City | City Camp Central | 16.4205 | 120.5993 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.36 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 66.3 | 46.35 | 66.3 |  | B - Node 0.5-1 km | 0.82 | 0.82 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3560
4 | 561 | 3561 | 1206509039 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Palimbang | Mina | 6.1239 | 124.3306 | R | 966 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.9 | 66.42 | Tier 2 High GIDA (Score 40.0–49.9) | 66.29 | 46.35 | 66.29 |  | F - Nearest node and line over 5 km | 72.14 | 68.71 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3561
4 | 562 | 3562 | 1108602014 | Region XI (Davao Region) | Davao Occidental | Jose Abad Santos | Culaman | 5.7224 | 125.5005 | R | 3519 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.36 | 53.95 | Tier 2 High GIDA (Score 40.0–49.9) | 66.28 | 46.34 | 66.28 |  | F - Nearest node and line over 5 km | 49.14 | 56.07 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3562
4 | 563 | 3563 | 1380500010 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Hagdang Bato Itaas | 14.5896 | 121.0308 | U | 11235 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.72 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 66.26 | 46.33 | 66.26 |  | B - Node 0.5-1 km | 0.72 | 0.23 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3563
4 | 564 | 3564 | 0504101034 | Region V (Bicol Region) | Masbate | Aroroy | San Isidro | 12.4291 | 123.3667 | R | 1177 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.69 | 12.27 | Tier 2 High GIDA (Score 40.0–49.9) | 66.25 | 46.32 | 66.25 |  | F - Nearest node and line over 5 km | 9.69 | 24.38 | Node: AYM001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3564
4 | 565 | 3565 | PH0003565 | NCR | Metro Manila | Caloocan City | Barangay 167 | 14.7333 | 121.0127 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.52 | 10.71 | Tier 2 High GIDA (Score 40.0–49.9) | 66.24 | 46.31 | 66.24 |  | C - Line within 0.5 km; node over 1 km | 1.23 | 0.06 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3565
4 | 566 | 3566 | 1381300085 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-A | 14.6907 | 121.0945 | U | 4816 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.06 | 1.67 | Tier 2 High GIDA (Score 40.0–49.9) | 66.23 | 46.3 | 66.23 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.07 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3566
4 | 567 | 3567 | PH0003567 | IV-A | Cavite | Imus City | Toclong I-B | 14.3452 | 121.0151 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.21 | 1.71 | Tier 2 High GIDA (Score 40.0–49.9) | 66.23 | 46.3 | 66.23 |  | D - Other node or line within 3 km | 1.12 | 2.48 | Node: MUN048 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3567
4 | 568 | 3568 | PH0003568 | III | Pampanga | Angeles City | Salapungan | 15.148 | 120.5983 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 66.21 | 46.29 | 66.21 |  | B - Node 0.5-1 km | 0.78 | 0.41 | Line: 80 CORE (8X10) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3568
4 | 569 | 3569 | 0802623002 | Region VIII (Eastern Visayas) | Eastern Samar | Taft | Beto | 11.9487 | 125.3832 | R | 299 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 89.09 | 91.43 | Tier 2 High GIDA (Score 40.0–49.9) | 66.2 | 46.28 | 66.2 |  | F - Nearest node and line over 5 km | 89.09 | 91.43 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3569
4 | 570 | 3570 | 1705318017 | MIMAROPA Region | Palawan | Roxas | Rizal | 10.233 | 119.2616 | R | 1096 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.07 | 4.76 | Tier 2 High GIDA (Score 40.0–49.9) | 66.18 | 46.26 | 66.18 |  | E - Nearest node or line 3-5 km | 13.07 | 4.76 | Line: TAYTAY - PUERTO PRINCESA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3570
4 | 571 | 3571 | 1380608011 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 669 | 14.58 | 120.9881 | U | 3017 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.06 | 9.32 | Tier 2 High GIDA (Score 40.0–49.9) | 66.18 | 46.26 | 66.18 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.18 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3571
4 | 572 | 3572 | 0402111016 | Region IV-A (CALABARZON) | Cavite | Kawit | Congbalay-Legaspi | 14.4513 | 120.9226 | R | 4597 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.85 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 66.17 | 46.26 | 66.17 |  | C - Line within 0.5 km; node over 1 km | 2.85 | 0.18 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3572
4 | 573 | 3573 | 1704005021 | MIMAROPA Region | Marinduque | Santa Cruz | Kaganhao | 13.4447 | 122.0251 | R | 533 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.9 | 30.46 | Tier 2 High GIDA (Score 40.0–49.9) | 66.17 | 46.26 | 66.17 |  | F - Nearest node and line over 5 km | 31.9 | 30.46 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3573
4 | 574 | 3574 | PH0003574 | VI | Iloilo | Iloilo City | San Roque | 10.74 | 122.5413 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.1 | 2.18 | Tier 2 High GIDA (Score 40.0–49.9) | 66.17 | 46.26 | 66.17 |  | D - Other node or line within 3 km | 2.85 | 2.19 | Line: 24c | Route options survey candidate: compare actual node lateral with approved line tap. | 3574
4 | 575 | 3575 | 1380400012 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Muzon | 14.6765 | 120.95 | U | 6054 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 66.16 | 46.26 | 66.16 |  | B - Node 0.5-1 km | 0.64 | 0.6 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3575
4 | 576 | 3576 | 1004205022 | Region X (Northern Mindanao) | Misamis Occidental | Clarin | Penacio | 9.959 | 124.0274 | R | 397 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.1 | 15.59 | Tier 2 High GIDA (Score 40.0–49.9) | 66.15 | 46.25 | 66.15 |  | C - Line within 0.5 km; node over 1 km | 30.4 | 0.22 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3576
4 | 577 | 3577 | 0201529006 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 4 | 17.6111 | 121.7297 | U | 608 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.42 | 0.79 | Tier 2 High GIDA (Score 40.0–49.9) | 66.15 | 46.24 | 66.15 |  | C - Line within 0.5 km; node over 1 km | 4.84 | 0.45 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3577
4 | 578 | 3578 | PH0003578 | VII | Cebu | Cebu City | Bulacao | 10.276 | 123.8497 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.54 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 66.14 | 46.24 | 66.14 |  | C - Line within 0.5 km; node over 1 km | 1.54 | 0.15 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3578
4 | 579 | 3579 | 1705103002 | MIMAROPA Region | Occidental Mindoro | Looc | Ambil | 13.7931 | 120.2751 | R | 1819 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.53 | 38.6 | Tier 2 High GIDA (Score 40.0–49.9) | 66.14 | 46.24 | 66.14 |  | F - Nearest node and line over 5 km | 38.53 | 38.52 | Line: BALAYAN - CALATAGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3579
4 | 580 | 3580 | 0403428015 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Kanluran | 14.2957 | 121.0959 | U | 4643 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 66.12 | 46.22 | 66.12 |  | D - Other node or line within 3 km | 1.04 | 0.52 | Line: AE SRL007-CBL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3580
4 | 581 | 3581 | PH0003581 | CAR | Benguet | Baguio City | San Roque Village | 16.3971 | 120.6303 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.09 | 3.23 | Tier 2 High GIDA (Score 40.0–49.9) | 66.11 | 46.22 | 66.11 |  | D - Other node or line within 3 km | 1.99 | 1.85 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3581
4 | 582 | 3582 | 1401114002 | Cordillera Administrative Region (CAR) | Benguet | Tublay | Ambongdolan | 16.5342 | 120.6038 | R | 1083 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.65 | 6.55 | Tier 2 High GIDA (Score 40.0–49.9) | 66.11 | 46.21 | 66.11 |  | E - Nearest node or line 3-5 km | 4.65 | 6.47 | Node: KPB001 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3582
4 | 583 | 3583 | 1704005014 | MIMAROPA Region | Marinduque | Santa Cruz | Dating Bayan | 13.5077 | 121.9597 | R | 366 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.96 | 30.96 | Tier 2 High GIDA (Score 40.0–49.9) | 66.1 | 46.21 | 66.1 |  | F - Nearest node and line over 5 km | 30.96 | 30.95 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3583
4 | 584 | 3584 | 0402103004 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Bayanan | 14.4254 | 120.9746 | U | 11757 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.56 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 66.09 | 46.21 | 66.09 |  | B - Node 0.5-1 km | 0.94 | 2.75 | Node: BRC006 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3584
4 | 585 | 3585 | 0301407020 | Region III (Central Luzon) | Bulacan | Calumpit | Pio Cruzcosa | 14.9048 | 120.7667 | U | 4874 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 1.01 | Tier 2 High GIDA (Score 40.0–49.9) | 66.09 | 46.21 | 66.09 |  | A - Node within 0.5 km | 0.21 | 0.15 | Line: GOTACO TO HH 71 BULACAN | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3585
4 | 586 | 3586 | PH0003586 | IV-A | Cavite | Imus City | Tanzang Luma II | 14.403 | 120.9406 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.77 | Tier 2 High GIDA (Score 40.0–49.9) | 66.08 | 46.19 | 66.08 |  | A - Node within 0.5 km | 0.44 | 4.88 | Node: IMC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3586
4 | 587 | 3587 | 0806020031 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Marabut | 11.8784 | 124.7848 | R | 250 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.8 | 67.77 | Tier 2 High GIDA (Score 40.0–49.9) | 66.07 | 46.19 | 66.07 |  | F - Nearest node and line over 5 km | 65.18 | 65.15 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3587
4 | 588 | 3588 | 1380200020 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Talon Singko | 14.42 | 120.9922 | U | 39275 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.4 | 2.4 | Tier 2 High GIDA (Score 40.0–49.9) | 66.06 | 46.19 | 66.06 |  | D - Other node or line within 3 km | 2.4 | 2.37 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3588
4 | 589 | 3589 | 1381400009 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Little Baguio | 13.7475 | 121.3968 | U | 6671 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.48 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 66.06 | 46.18 | 66.06 |  | F - Nearest node and line over 5 km | 6.92 | 8.18 | Node: SJB003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3589
4 | 590 | 3590 | 1102301009 | Region XI (Davao Region) | Davao del Norte | Asuncion | Camansa | 7.5942 | 125.7494 | R | 1580 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.15 | 9.93 | Tier 2 High GIDA (Score 40.0–49.9) | 66.05 | 46.18 | 66.05 |  | F - Nearest node and line over 5 km | 16.72 | 16.23 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3590
4 | 591 | 3591 | PH0003591 | XI | Davao Del Sur | Davao City | Barangay 7-A (Pob.) | 7.3005 | 125.3392 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.96 | 4.39 | Tier 2 High GIDA (Score 40.0–49.9) | 66.05 | 46.18 | 66.05 |  | E - Nearest node or line 3-5 km | 4.09 | 3.65 | Line: KITAOTAO - DAVAO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3591
4 | 592 | 3592 | PH0003592 | VI | Iloilo | Iloilo City | Lopez Jaena Norte | 10.6999 | 122.565 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.35 | 3.33 | Tier 2 High GIDA (Score 40.0–49.9) | 66.04 | 46.17 | 66.04 |  | C - Line within 0.5 km; node over 1 km | 1.57 | 0.43 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3592
4 | 593 | 3593 | PH0003593 | VI | Capiz | Roxas City | Poblacion XI | 11.5851 | 122.7733 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.47 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 66.04 | 46.17 | 66.04 |  | C - Line within 0.5 km; node over 1 km | 2.75 | 0.02 | Line: ROXAS - SARA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3593
4 | 594 | 3594 | PH0003594 | NCR | Metro Manila | Caloocan City | Barangay 178 | 14.7566 | 121.0568 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 81.08 | 104.98 | Tier 2 High GIDA (Score 40.0–49.9) | 66.03 | 46.16 | 66.03 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.34 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3594
4 | 595 | 3595 | 0403404019 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Tres | 14.2495 | 121.1186 | U | 4685 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.13 | 6.34 | Tier 2 High GIDA (Score 40.0–49.9) | 66.03 | 46.16 | 66.03 |  | D - Other node or line within 3 km | 1.23 | 1.12 | Line: AE SRL007-CBL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3595
4 | 596 | 3596 | 1705318025 | MIMAROPA Region | Palawan | Roxas | Taradungan | 10.3696 | 119.5308 | R | 1492 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.19 | 16.89 | Tier 2 High GIDA (Score 40.0–49.9) | 66.02 | 46.15 | 66.02 |  | F - Nearest node and line over 5 km | 21.19 | 16.88 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3596
4 | 597 | 3597 | PH0003597 | NCR | Metro Manila | Caloocan City | Barangay 14 | 14.6506 | 120.9653 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.17 | 6.31 | Tier 2 High GIDA (Score 40.0–49.9) | 66.01 | 46.15 | 66.01 |  | B - Node 0.5-1 km | 0.84 | 1.3 | Node: CCS004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3597
4 | 598 | 3598 | 1380610014 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 699 | 14.5764 | 120.9917 | U | 3290 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.33 | 52.59 | Tier 2 High GIDA (Score 40.0–49.9) | 66.01 | 46.15 | 66.01 |  | B - Node 0.5-1 km | 0.56 | 0.24 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3598
4 | 599 | 3599 | PH0003599 | CAR | Benguet | Baguio City | Holy Ghost Extension | 16.4179 | 120.6046 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.95 | Tier 2 High GIDA (Score 40.0–49.9) | 66.01 | 46.15 | 66.01 |  | B - Node 0.5-1 km | 0.75 | 0.93 | Node: BGC003 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3599
4 | 600 | 3600 | 1908808004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Buayan | 17.2559 | 122.2294 | R | 1732 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.59 | Tier 2 High GIDA (Score 40.0–49.9) | 65.99 | 46.14 | 65.99 |  | F - Nearest node and line over 5 km | 29.53 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3600
4 | 601 | 3601 | 1906609012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Duyan Kabao | 17.2543 | 122.2288 | R | 1323 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29 | 33.72 | Tier 2 High GIDA (Score 40.0–49.9) | 65.99 | 46.13 | 65.99 |  | F - Nearest node and line over 5 km | 29.37 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3601
4 | 602 | 3602 | 0702232011 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward II | 10.2387 | 123.7821 | U | 3639 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 1.58 | Tier 2 High GIDA (Score 40.0–49.9) | 65.99 | 46.13 | 65.99 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.08 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3602
4 | 603 | 3603 | 1908813011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Mamasapano | Pimbalakan | 17.2552 | 122.2293 | R | 1527 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.99 | 46.13 | 65.99 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3603
4 | 604 | 3604 | PH0003604 | I | Ilocos Norte | Laoag City | Bgy. No. 17, San Francisco (Pob.) | 18.2116 | 120.5679 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.15 | 0.89 | Tier 2 High GIDA (Score 40.0–49.9) | 65.99 | 46.13 | 65.99 |  | D - Other node or line within 3 km | 1.95 | 1.89 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Route options survey candidate: compare actual node lateral with approved line tap. | 3604
4 | 605 | 3605 | 0804815005 | Region VIII (Eastern Visayas) | Northern Samar | Pambujan | Cagbigajo | 12.4179 | 124.9103 | R | 582 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.93 | 90.21 | Tier 2 High GIDA (Score 40.0–49.9) | 65.98 | 46.13 | 65.98 |  | F - Nearest node and line over 5 km | 90.93 | 90.13 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3605
4 | 606 | 3606 | 0806417037 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | San Juan | 10.4428 | 125.0288 | R | 731 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.1 | 2.11 | Tier 2 High GIDA (Score 40.0–49.9) | 65.97 | 46.12 | 65.97 |  | F - Nearest node and line over 5 km | 36.18 | 29 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3606
4 | 607 | 3607 | 1900704008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Maluso | Muslim Area | 6.4674 | 121.8244 | R | 2187 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 28.15 | Tier 2 High GIDA (Score 40.0–49.9) | 65.97 | 46.12 | 65.97 |  | F - Nearest node and line over 5 km | 56.43 | 56.43 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3607
4 | 608 | 3608 | 0501714022 | Region V (Bicol Region) | Camarines Sur | Garchitorena | Tamiawon | 13.9536 | 123.6293 | R | 850 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.07 | 32.65 | Tier 2 High GIDA (Score 40.0–49.9) | 65.96 | 46.11 | 65.96 |  | F - Nearest node and line over 5 km | 27.07 | 32.44 | Node: TCC002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3608
4 | 609 | 3609 | 1003506021 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Mahayahay | 7.6993 | 123.8196 | R | 446 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.24 | 12.58 | Tier 2 High GIDA (Score 40.0–49.9) | 65.95 | 46.11 | 65.95 |  | F - Nearest node and line over 5 km | 38.13 | 22.06 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3609
4 | 610 | 3610 | 0403425005 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Landayan | 14.3535 | 121.0679 | U | 36431 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.58 | 4.31 | Tier 2 High GIDA (Score 40.0–49.9) | 65.94 | 46.1 | 65.94 |  | B - Node 0.5-1 km | 0.57 | 0.53 | Line: RELIANCE PSG001 TO BÑL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3610
4 | 611 | 3611 | 0201507005 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Cabayu | 18.2901 | 121.4785 | R | 942 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.25 | 4.84 | Tier 2 High GIDA (Score 40.0–49.9) | 65.93 | 46.09 | 65.93 |  | E - Nearest node or line 3-5 km | 4.25 | 4.84 | Node: SMY001 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3611
4 | 612 | 3612 | PH0003612 | I | Pangasinan | Dagupan City | Barangay I | 16.0581 | 120.3231 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.39 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 65.92 | 46.08 | 65.92 |  | D - Other node or line within 3 km | 4.21 | 1.96 | Line: DAGUPAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3612
4 | 613 | 3613 | 0403405043 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 6 | 14.2121 | 121.1636 | U | 1856 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 65.91 | 46.08 | 65.91 |  | C - Line within 0.5 km; node over 1 km | 2.5 | 0.04 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3613
4 | 614 | 3614 | PH0003614 | IV-A | Laguna | San Pablo City | Barangay IV-B (Pob.) | 14.0625 | 121.348 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.49 | 1.44 | Tier 2 High GIDA (Score 40.0–49.9) | 65.91 | 46.08 | 65.91 |  | D - Other node or line within 3 km | 2.02 | 1.6 | Line: SPO001 TO SAN JUAN CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 3614
4 | 615 | 3615 | 0102903034 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Barangay 5 | 17.5804 | 120.3906 | U | 677 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.47 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 65.91 | 46.08 | 65.91 |  | C - Line within 0.5 km; node over 1 km | 1.47 | 0.04 | Line: SEGMENT 3 (VIGAN - BATAC) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3615
4 | 616 | 3616 | 0102902008 | Region I (Ilocos Region) | Ilocos Sur | Banayoyo | Elefante | 17.2218 | 120.4915 | R | 630 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.1 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 65.91 | 46.07 | 65.91 |  | D - Other node or line within 3 km | 4.69 | 1.69 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 3616
4 | 617 | 3617 | 1004317024 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Tama | 8.0342 | 123.915 | R | 783 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.94 | 2.42 | Tier 2 High GIDA (Score 40.0–49.9) | 65.9 | 46.07 | 65.9 |  | F - Nearest node and line over 5 km | 12.79 | 8.59 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3617
4 | 618 | 3618 | 1400125002 | Cordillera Administrative Region (CAR) | Abra | Tineg | Alaoa | 17.7529 | 120.8261 | R | 824 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.71 | 15.78 | Tier 2 High GIDA (Score 40.0–49.9) | 65.9 | 46.07 | 65.9 |  | F - Nearest node and line over 5 km | 19.71 | 16.52 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3618
4 | 619 | 3619 | 1903630010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Wao | Christian Village | 17.2543 | 122.2283 | R | 2097 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 65.9 | 46.07 | 65.9 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3619
4 | 620 | 3620 | 1900707040 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Katipunan | 10.7119 | 123.8285 | R | 2207 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.1 | 37.09 | Tier 2 High GIDA (Score 40.0–49.9) | 65.89 | 46.06 | 65.89 |  | D - Other node or line within 3 km | 19.71 | 1.34 | Line: 104.3km-96FOC-toledo-san remigio | Route options survey candidate: compare actual node lateral with approved line tap. | 3620
4 | 621 | 3621 | 0802615016 | Region VIII (Eastern Visayas) | Eastern Samar | Maydolong | Barangay Poblacion 4 | 11.5042 | 125.4976 | R | 1706 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 61.47 | 61.72 | Tier 2 High GIDA (Score 40.0–49.9) | 65.87 | 46.05 | 65.87 |  | F - Nearest node and line over 5 km | 61.47 | 62.33 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3621
4 | 622 | 3622 | PH0003622 | IV-A | Cavite | Imus City | Poblacion IV-B | 14.4296 | 120.928 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.86 | 1.87 | Tier 2 High GIDA (Score 40.0–49.9) | 65.87 | 46.05 | 65.87 |  | D - Other node or line within 3 km | 1.92 | 2.17 | Node: IMC002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3622
4 | 623 | 3623 | PH0003623 | CAR | Benguet | Baguio City | Aurora Hill, South Central | 16.425 | 120.6051 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.21 | 1.5 | Tier 2 High GIDA (Score 40.0–49.9) | 65.86 | 46.04 | 65.86 |  | D - Other node or line within 3 km | 1.21 | 1.39 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3623
4 | 624 | 3624 | 0601906002 | Region VI (Western Visayas) | Capiz | Jamindan | Agbun-od | 11.4712 | 122.4276 | R | 988 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.51 | 7.39 | Tier 2 High GIDA (Score 40.0–49.9) | 65.86 | 46.04 | 65.86 |  | F - Nearest node and line over 5 km | 9.51 | 7.32 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3624
4 | 625 | 3625 | PH0003625 | CAR | Benguet | Baguio City | Guisad Sorong | 16.3776 | 120.6124 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.63 | 1.48 | Tier 2 High GIDA (Score 40.0–49.9) | 65.86 | 46.04 | 65.86 |  | D - Other node or line within 3 km | 3.18 | 2.9 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 3625
4 | 626 | 3626 | PH0003626 | I | Pangasinan | Dagupan City | Herrero | 16.0606 | 120.3116 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.47 | 1.51 | Tier 2 High GIDA (Score 40.0–49.9) | 65.85 | 46.04 | 65.85 |  | D - Other node or line within 3 km | 4.83 | 3 | Line: DAGUPAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3626
4 | 627 | 3627 | 0604507012 | Region VI (Western Visayas) | Negros Occidental | Cauayan | Camindangan | 9.8328 | 122.5721 | R | 2781 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.77 | 18.92 | Tier 2 High GIDA (Score 40.0–49.9) | 65.85 | 46.03 | 65.85 |  | F - Nearest node and line over 5 km | 20.77 | 18.88 | Line: SIPALAY TO BAYAWAN-84,748m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3627
4 | 628 | 3628 | PH0003628 | X | Misamis Oriental | Cagayan De Oro City | Lapasan | 8.4814 | 124.6638 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 65.84 | 46.03 | 65.84 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.18 | Line: CAGAYAN DE ORO - MALAYBALAY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3628
4 | 629 | 3629 | 1907004015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Bagid* | 17.2558 | 122.2299 | R | 878 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 65.84 | 46.03 | 65.84 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3629
4 | 630 | 3630 | PH0003630 | IV-A | Cavite | Cavite City | Barangay 54-A | 14.4827 | 120.911 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.37 | 3.58 | Tier 2 High GIDA (Score 40.0–49.9) | 65.82 | 46.02 | 65.82 |  | D - Other node or line within 3 km | 2.67 | 3.87 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3630
4 | 631 | 3631 | PH0003631 | I | Ilocos Norte | Laoag City | Bgy. No. 7-B, Nstra. Sra. De Natividad (Pob.) | 18.2029 | 120.5934 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.92 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 65.81 | 46.01 | 65.81 |  | B - Node 0.5-1 km | 0.92 | 0.02 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3631
4 | 632 | 3632 | 0402104006 | Region IV-A (CALABARZON) | Cavite | Carmona | Cabilang Baybay | 14.3177 | 121.0498 | U | 8144 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.76 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 65.81 | 46.01 | 65.81 |  | B - Node 0.5-1 km | 0.76 | 0.75 | Line: AE CRC005-BNL001-CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3632
4 | 633 | 3633 | PH0003633 | VI | Iloilo | Iloilo City | Bolilao | 10.7109 | 122.5544 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.52 | 1.09 | Tier 2 High GIDA (Score 40.0–49.9) | 65.79 | 46 | 65.79 |  | D - Other node or line within 3 km | 1.52 | 1.05 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3633
4 | 634 | 3634 | 0504106023 | Region V (Bicol Region) | Masbate | Cawayan | Pulot | 12.0694 | 123.7551 | R | 842 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.69 | 31.46 | Tier 2 High GIDA (Score 40.0–49.9) | 65.78 | 45.99 | 65.78 |  | F - Nearest node and line over 5 km | 18.69 | 31.47 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3634
4 | 635 | 3635 | 1705309004 | MIMAROPA Region | Palawan | Coron | Buenavista | 12.1636 | 120.2405 | R | 1512 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.87 | 91.53 | Tier 2 High GIDA (Score 40.0–49.9) | 65.77 | 45.98 | 65.77 |  | F - Nearest node and line over 5 km | 16.87 | 91.53 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3635
4 | 636 | 3636 | 0301416001 | Region III (Central Luzon) | Bulacan | Paombong | Binakod | 14.7825 | 120.785 | R | 1971 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.36 | 8.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.77 | 45.98 | 65.77 |  | F - Nearest node and line over 5 km | 5.36 | 8.42 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3636
4 | 637 | 3637 | 0405646033 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Francisco | 14.0157 | 122.4884 | R | 978 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.18 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 65.74 | 45.96 | 65.74 |  | C - Line within 0.5 km; node over 1 km | 2.18 | 0.03 | Line: GCQ001 TO TKQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3637
4 | 638 | 3638 | 0405644019 | Region IV-A (CALABARZON) | Quezon | San Narciso | San Isidro | 13.571 | 122.5628 | R | 1053 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 1.06 | Tier 2 High GIDA (Score 40.0–49.9) | 65.74 | 45.96 | 65.74 |  | D - Other node or line within 3 km | 1.07 | 1.06 | Line: UG SNQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3638
4 | 639 | 3639 | 1705309022 | MIMAROPA Region | Palawan | Coron | San Jose | 12.1768 | 120.091 | R | 1910 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.7 | 107.08 | Tier 2 High GIDA (Score 40.0–49.9) | 65.73 | 45.95 | 65.73 |  | F - Nearest node and line over 5 km | 15.7 | 107.08 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3639
4 | 640 | 3640 | 0704607008 | Region VII (Central Visayas) | Negros Oriental | Bindoy | Danao | 9.7591 | 123.1165 | R | 1265 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.32 | 4.97 | Tier 2 High GIDA (Score 40.0–49.9) | 65.73 | 45.95 | 65.73 |  | F - Nearest node and line over 5 km | 18.8 | 5.91 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3640
4 | 641 | 3641 | 1907004004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Tampakan | 4.9182 | 119.7905 | R | 3019 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 65.73 | 45.95 | 65.73 |  | F - Nearest node and line over 5 km | 335.91 | 335.91 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3641
4 | 642 | 3642 | 0405805016 | Region IV-A (CALABARZON) | Rizal | Cainta | San Juan | 14.5398 | 121.1109 | U | 99685 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 65.71 | 45.94 | 65.71 |  | B - Node 0.5-1 km | 0.63 | 0.26 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3642
4 | 643 | 3643 | 0405601002 | Region IV-A (CALABARZON) | Quezon | Agdangan | Dayap | 13.9103 | 121.9361 | R | 306 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.51 | 4.21 | Tier 2 High GIDA (Score 40.0–49.9) | 65.71 | 45.94 | 65.71 |  | E - Nearest node or line 3-5 km | 4.51 | 4.13 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3643
4 | 644 | 3644 | PH0003644 | IV-A | Cavite | Cavite City | Barangay 47-B | 14.4823 | 120.8927 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 4.54 | Tier 2 High GIDA (Score 40.0–49.9) | 65.7 | 45.93 | 65.7 |  | B - Node 0.5-1 km | 0.99 | 4.61 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3644
4 | 645 | 3645 | 0802607008 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Osmeña | 11.3027 | 125.4838 | R | 239 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.95 | 53.87 | Tier 2 High GIDA (Score 40.0–49.9) | 65.7 | 45.93 | 65.7 |  | F - Nearest node and line over 5 km | 52.7 | 52.71 | Node: TCL001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3645
4 | 646 | 3646 | PH0003646 | III | Pampanga | Angeles City | San Jose | 15.1436 | 120.5866 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 65.69 | 45.93 | 65.69 |  | D - Other node or line within 3 km | 1.06 | 0.92 | Line: ANGELES | Route options survey candidate: compare actual node lateral with approved line tap. | 3646
4 | 647 | 3647 | PH0003647 | XIII | Agusan Del Norte | Butuan City | New Society Village Pob. | 8.9865 | 125.6419 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.86 | 9.09 | Tier 2 High GIDA (Score 40.0–49.9) | 65.69 | 45.92 | 65.69 |  | D - Other node or line within 3 km | 5.4 | 2.98 | Line: 22,382 | Route options survey candidate: compare actual node lateral with approved line tap. | 3647
4 | 648 | 3648 | 0600609042 | Region VI (Western Visayas) | Antique | Laua-An | Virginia | 11.1289 | 122.1236 | R | 247 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.52 | 38.89 | Tier 2 High GIDA (Score 40.0–49.9) | 65.69 | 45.92 | 65.69 |  | F - Nearest node and line over 5 km | 45.52 | 38.55 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3648
4 | 649 | 3649 | 0402106027 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Dionisio | 14.3199 | 120.9786 | U | 7096 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 5.41 | Tier 2 High GIDA (Score 40.0–49.9) | 65.69 | 45.92 | 65.69 |  | B - Node 0.5-1 km | 0.51 | 3.16 | Node: DMC005 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3649
4 | 650 | 3650 | PH0003650 | IV-A | Cavite | Imus City | Poblacion I-B | 14.393 | 120.9203 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.53 | 2.45 | Tier 2 High GIDA (Score 40.0–49.9) | 65.68 | 45.92 | 65.68 |  | D - Other node or line within 3 km | 2.32 | 4.74 | Node: IMC003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3650
4 | 651 | 3651 | 1705305016 | MIMAROPA Region | Palawan | Bataraza | Sarong | 8.5177 | 117.4838 | R | 2839 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 193.18 | 195.47 | Tier 2 High GIDA (Score 40.0–49.9) | 65.67 | 45.91 | 65.67 |  | F - Nearest node and line over 5 km | 193.18 | 195.18 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3651
4 | 652 | 3652 | 0802611007 | Region VIII (Eastern Visayas) | Eastern Samar | Jipapad | Cagmanaba | 12.2636 | 125.1877 | R | 918 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 115.63 | 118.48 | Tier 2 High GIDA (Score 40.0–49.9) | 65.67 | 45.91 | 65.67 |  | F - Nearest node and line over 5 km | 115.63 | 118.47 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3652
4 | 653 | 3653 | 1381600001 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Arkong Bato | 14.6988 | 120.9493 | U | 11520 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.58 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 65.65 | 45.89 | 65.65 |  | C - Line within 0.5 km; node over 1 km | 1.58 | 0.45 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3653
4 | 654 | 3654 | 1907004014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Timundon | 17.2558 | 122.2299 | R | 5264 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 65.64 | 45.89 | 65.64 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3654
4 | 655 | 3655 | 1108202005 | Region XI (Davao Region) | Davao de Oro | Laak | Il Papa | 7.7881 | 125.8378 | R | 1214 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.04 | 23.91 | Tier 2 High GIDA (Score 40.0–49.9) | 65.63 | 45.88 | 65.63 |  | F - Nearest node and line over 5 km | 24.45 | 18.13 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3655
4 | 656 | 3656 | 0403425028 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Rosario | 14.3684 | 121.0369 | U | 6479 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.38 | 6.52 | Tier 2 High GIDA (Score 40.0–49.9) | 65.59 | 45.86 | 65.59 |  | B - Node 0.5-1 km | 0.75 | 1.36 | Node: SPL003 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3656
4 | 657 | 3657 | 0402106030 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Isidro Labrador I | 14.3407 | 120.9506 | R | 5089 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 4.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.59 | 45.85 | 65.59 |  | D - Other node or line within 3 km | 1.61 | 4.28 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3657
4 | 658 | 3658 | 1408102012 | Cordillera Administrative Region (CAR) | Apayao | Conner | Nabuangan | 17.7258 | 121.1855 | R | 588 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.68 | 13.99 | Tier 2 High GIDA (Score 40.0–49.9) | 65.58 | 45.84 | 65.58 |  | F - Nearest node and line over 5 km | 16.68 | 15.74 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3658
4 | 659 | 3659 | PH0003659 | NCR | Metro Manila | Caloocan City | Barangay 176 | 14.6438 | 120.9854 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.66 | 66.27 | Tier 2 High GIDA (Score 40.0–49.9) | 65.57 | 45.84 | 65.57 |  | B - Node 0.5-1 km | 0.55 | 0.13 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3659
4 | 660 | 3660 | PH0003660 | IV-A | Cavite | Cavite City | Barangay 56 | 14.4813 | 120.9006 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.97 | 4.32 | Tier 2 High GIDA (Score 40.0–49.9) | 65.56 | 45.83 | 65.56 |  | D - Other node or line within 3 km | 1.58 | 4.1 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3660
4 | 661 | 3661 | 0403405042 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 5 | 14.2104 | 121.1676 | U | 6421 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.73 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 65.55 | 45.83 | 65.55 |  | C - Line within 0.5 km; node over 1 km | 2.73 | 0.38 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3661
4 | 662 | 3662 | 0402104014 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 3 | 14.3072 | 121.0518 | R | 916 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 65.55 | 45.83 | 65.55 |  | A - Node within 0.5 km | 0.45 | 0.44 | Line: AE CRC005-BNL001-CLB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3662
4 | 663 | 3663 | 0701248002 | Region VII (Central Visayas) | Bohol | Bien Unido | Bilangbilangan Diot | 10.2437 | 124.4656 | R | 745 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.66 | 33.43 | Tier 2 High GIDA (Score 40.0–49.9) | 65.55 | 45.82 | 65.55 |  | F - Nearest node and line over 5 km | 41.66 | 33.42 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3663
4 | 664 | 3664 | PH0003664 | I | Ilocos Norte | Laoag City | Bgy. No. 19, Santa Marcela (Pob.) | 18.1927 | 120.5971 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 0.64 | Tier 2 High GIDA (Score 40.0–49.9) | 65.54 | 45.82 | 65.54 |  | C - Line within 0.5 km; node over 1 km | 1.95 | 0.45 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3664
4 | 665 | 3665 | PH0003665 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 13 | 11.7795 | 124.9147 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.43 | 33.92 | Tier 2 High GIDA (Score 40.0–49.9) | 65.54 | 45.82 | 65.54 |  | F - Nearest node and line over 5 km | 58.72 | 58.64 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3665
4 | 666 | 3666 | 1004318013 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Upper Malubog | 8.3642 | 124.4039 | R | 677 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.3 | 12.86 | Tier 2 High GIDA (Score 40.0–49.9) | 65.53 | 45.81 | 65.53 |  | F - Nearest node and line over 5 km | 12.3 | 12.83 | Node: OLM002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3666
4 | 667 | 3667 | 0402104001 | Region IV-A (CALABARZON) | Cavite | Carmona | Bancal | 14.282 | 121.0072 | U | 17076 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.57 | 4.49 | Tier 2 High GIDA (Score 40.0–49.9) | 65.52 | 45.81 | 65.52 |  | B - Node 0.5-1 km | 0.57 | 4.47 | Node: MAC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3667
4 | 668 | 3668 | 0201510028 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Dammang Sur | 18.2484 | 121.6962 | R | 264 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 1.15 | Tier 2 High GIDA (Score 40.0–49.9) | 65.52 | 45.8 | 65.52 |  | D - Other node or line within 3 km | 1.61 | 1.15 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Route options survey candidate: compare actual node lateral with approved line tap. | 3668
4 | 669 | 3669 | 1380700015 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Fortune | 14.6592 | 121.1264 | U | 39917 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 65.51 | 45.8 | 65.51 |  | B - Node 0.5-1 km | 0.96 | 0.06 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3669
4 | 670 | 3670 | 1381600006 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Bisig | 14.725 | 120.9449 | U | 1452 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 65.51 | 45.8 | 65.51 |  | D - Other node or line within 3 km | 1.95 | 1.51 | Line: 48 CORE | Route options survey candidate: compare actual node lateral with approved line tap. | 3670
4 | 671 | 3671 | 0504117021 | Region V (Bicol Region) | Masbate | Placer | Naboctot | 11.8578 | 123.7675 | R | 1361 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.55 | 28.62 | Tier 2 High GIDA (Score 40.0–49.9) | 65.5 | 45.79 | 65.5 |  | F - Nearest node and line over 5 km | 15.55 | 49.01 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3671
4 | 672 | 3672 | PH0003672 | VI | Iloilo | Iloilo City | Dungon B | 10.7297 | 122.5457 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.89 | 1.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.5 | 45.79 | 65.5 |  | D - Other node or line within 3 km | 2.89 | 1.35 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3672
4 | 673 | 3673 | 0402106070 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Isidro Labrador II | 14.2646 | 120.9683 | R | 2593 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.88 | 4.37 | Tier 2 High GIDA (Score 40.0–49.9) | 65.49 | 45.79 | 65.49 |  | C - Line within 0.5 km; node over 1 km | 4.08 | 0.04 | Line: NCC001 TO TGY001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3673
4 | 674 | 3674 | 0403403021 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Vicente | 14.3296 | 121.0779 | U | 10124 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 65.49 | 45.78 | 65.49 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.03 | Line: AE CRC005-BNL001-CLB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3674
4 | 675 | 3675 | 0702232012 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward III | 10.2621 | 123.7623 | U | 2742 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.58 | 2.33 | Tier 2 High GIDA (Score 40.0–49.9) | 65.48 | 45.78 | 65.48 |  | E - Nearest node or line 3-5 km | 3.82 | 3.12 | Line: CEBU - TOLEDO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3675
4 | 676 | 3676 | PH0003676 | VIII | Leyte | Tacloban City | Barangay 51-A | 11.2377 | 125 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.87 | 2.81 | Tier 2 High GIDA (Score 40.0–49.9) | 65.48 | 45.78 | 65.48 |  | A - Node within 0.5 km | 0.34 | 2.97 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3676
4 | 677 | 3677 | PH0003677 | V | Camarines Sur | Naga City | Sabang | 13.6203 | 123.1805 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 65.48 | 45.77 | 65.48 |  | B - Node 0.5-1 km | 0.91 | 0.71 | Line: PAGBILAO - NAGA (UG + Aerial) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3677
4 | 678 | 3678 | 0806001025 | Region VIII (Eastern Visayas) | Samar | Almagro | Imelda | 11.9326 | 124.2985 | R | 467 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.85 | 75.74 | Tier 2 High GIDA (Score 40.0–49.9) | 65.47 | 45.77 | 65.47 |  | F - Nearest node and line over 5 km | 42.85 | 75.74 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3678
4 | 679 | 3679 | 1403209015 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Magaogao | 17.5974 | 121.4462 | R | 749 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.59 | 1.7 | Tier 2 High GIDA (Score 40.0–49.9) | 65.44 | 45.75 | 65.44 |  | D - Other node or line within 3 km | 3.59 | 1.53 | Line: Tabuk-Conner | Route options survey candidate: compare actual node lateral with approved line tap. | 3679
4 | 680 | 3680 | PH0003680 | VII | Cebu | Cebu City | Lorega | 10.3388 | 123.8798 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 3.57 | Tier 2 High GIDA (Score 40.0–49.9) | 65.44 | 45.75 | 65.44 |  | D - Other node or line within 3 km | 2.09 | 3.44 | Node: CCY003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3680
4 | 681 | 3681 | 0405649017 | Region IV-A (CALABARZON) | Quezon | Unisan | Mairok Ilaya | 13.88 | 122.0287 | R | 172 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.97 | 1.5 | Tier 2 High GIDA (Score 40.0–49.9) | 65.44 | 45.75 | 65.44 |  | E - Nearest node or line 3-5 km | 7.02 | 4.35 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3681
4 | 682 | 3682 | PH0003682 | NCR | Metro Manila | Caloocan City | Barangay 169 | 14.6245 | 120.9742 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.31 | 2.3 | Tier 2 High GIDA (Score 40.0–49.9) | 65.43 | 45.74 | 65.43 |  | A - Node within 0.5 km | 0.27 | 0.14 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3682
4 | 683 | 3683 | 0402103021 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas I | 14.4464 | 120.968 | U | 8425 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 65.42 | 45.73 | 65.42 |  | D - Other node or line within 3 km | 1.57 | 1.09 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 3683
4 | 684 | 3684 | 1908705020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Linek | 17.2548 | 122.2287 | R | 4505 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 65.42 | 45.73 | 65.42 |  | F - Nearest node and line over 5 km | 29.4 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3684
4 | 685 | 3685 | PH0003685 | IV-A | Cavite | Cavite City | Barangay 44 | 14.4827 | 120.9046 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.95 | 3.4 | Tier 2 High GIDA (Score 40.0–49.9) | 65.42 | 45.73 | 65.42 |  | D - Other node or line within 3 km | 2.04 | 4.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3685
4 | 686 | 3686 | 1907003005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Mapun | Guppah | 17.2555 | 122.2307 | R | 2470 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 65.41 | 45.73 | 65.41 |  | F - Nearest node and line over 5 km | 29.61 | 34.49 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3686
4 | 687 | 3687 | 1907004013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Sukah-Bulan | 4.9217 | 119.7931 | R | 1945 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 65.41 | 45.73 | 65.41 |  | F - Nearest node and line over 5 km | 335.44 | 335.44 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3687
4 | 688 | 3688 | 0806001004 | Region VIII (Eastern Visayas) | Samar | Almagro | Biasong I | 11.9255 | 124.2908 | R | 510 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.9 | 74.59 | Tier 2 High GIDA (Score 40.0–49.9) | 65.4 | 45.72 | 65.4 |  | F - Nearest node and line over 5 km | 41.9 | 75.36 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3688
4 | 689 | 3689 | 0806001026 | Region VIII (Eastern Visayas) | Samar | Almagro | Biasong II | 11.9434 | 124.3354 | R | 339 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.35 | 74.21 | Tier 2 High GIDA (Score 40.0–49.9) | 65.4 | 45.72 | 65.4 |  | F - Nearest node and line over 5 km | 47.01 | 75.35 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3689
4 | 690 | 3690 | PH0003690 | IV-A | Cavite | Imus City | Poblacion II-B | 14.4031 | 120.9409 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.27 | 2.45 | Tier 2 High GIDA (Score 40.0–49.9) | 65.38 | 45.71 | 65.38 |  | A - Node within 0.5 km | 0.43 | 4.86 | Node: IMC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3690
4 | 691 | 3691 | 1906613002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Bagsak | 17.2554 | 122.2295 | R | 2454 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.38 | Tier 2 High GIDA (Score 40.0–49.9) | 65.37 | 45.7 | 65.37 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3691
4 | 692 | 3692 | 0401019004 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 10 | 14.068 | 120.7341 | U | 935 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.25 | 1.2 | Tier 2 High GIDA (Score 40.0–49.9) | 65.37 | 45.7 | 65.37 |  | C - Line within 0.5 km; node over 1 km | 2.06 | 0.11 | Line: ALFONSO - TUY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3692
4 | 693 | 3693 | 1907004011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Pagasinan | 17.2558 | 122.2299 | R | 1446 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 65.36 | 45.69 | 65.36 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3693
4 | 694 | 3694 | PH0003694 | IV-A | Cavite | Cavite City | Barangay 19 | 14.4739 | 120.8868 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.54 | 5.26 | Tier 2 High GIDA (Score 40.0–49.9) | 65.35 | 45.69 | 65.35 |  | A - Node within 0.5 km | 0.13 | 4.29 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3694
4 | 695 | 3695 | 1380900009 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Kaunlaran | 14.6742 | 120.9319 | U | 22388 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 2.06 | Tier 2 High GIDA (Score 40.0–49.9) | 65.35 | 45.69 | 65.35 |  | D - Other node or line within 3 km | 1.1 | 1.09 | Line: UG 288C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 3695
4 | 696 | 3696 | 1705306024 | MIMAROPA Region | Palawan | Brooke'S Point | Samareñana | 8.7399 | 117.7182 | R | 4252 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 142.86 | 145.16 | Tier 2 High GIDA (Score 40.0–49.9) | 65.33 | 45.67 | 65.33 |  | F - Nearest node and line over 5 km | 157.48 | 159.49 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3696
4 | 697 | 3697 | 1907004001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Bakong | 17.2558 | 122.2299 | R | 3352 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 65.31 | 45.66 | 65.31 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3697
4 | 698 | 3698 | 0200904001 | Region II (Cagayan Valley) | Batanes | Mahatao | Hañib | 20.4168 | 121.9484 | R | 406 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 219.59 | 213.88 | Tier 2 High GIDA (Score 40.0–49.9) | 65.31 | 45.66 | 65.31 |  | F - Nearest node and line over 5 km | 217.07 | 213.97 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3698
4 | 699 | 3699 | PH0003699 | IV-A | Cavite | Imus City | Poblacion I-C | 14.3824 | 120.9366 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.31 | 45.65 | 65.31 |  | A - Node within 0.5 km | 0.33 | 6.78 | Node: IMC003 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3699
4 | 700 | 3700 | 1003514002 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Balabacun | 8.0788 | 124.0623 | R | 1320 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.89 | 15.61 | Tier 2 High GIDA (Score 40.0–49.9) | 65.3 | 45.65 | 65.3 |  | F - Nearest node and line over 5 km | 24.57 | 11.76 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3700
4 | 701 | 3701 | 1907004008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Simunul | Doh-Tong | 17.2559 | 122.2299 | R | 1946 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.44 | Tier 2 High GIDA (Score 40.0–49.9) | 65.3 | 45.65 | 65.3 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3701
4 | 702 | 3702 | 0405801008 | Region IV-A (CALABARZON) | Rizal | Angono | Poblacion Itaas | 14.5387 | 121.1546 | R | 538 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.99 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 65.3 | 45.65 | 65.3 |  | D - Other node or line within 3 km | 1.24 | 0.57 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Route options survey candidate: compare actual node lateral with approved line tap. | 3702
4 | 703 | 3703 | 1908815006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagagawan | Maridagao | 14.6015 | 120.9822 | R | 3398 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.72 | 32.93 | Tier 2 High GIDA (Score 40.0–49.9) | 65.3 | 45.65 | 65.3 |  | B - Node 0.5-1 km | 0.98 | 0.05 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3703
4 | 704 | 3704 | 1705302007 | MIMAROPA Region | Palawan | Agutaya | Abagat | 11.1591 | 120.9615 | R | 490 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 113.04 | 119.51 | Tier 2 High GIDA (Score 40.0–49.9) | 65.29 | 45.64 | 65.29 |  | F - Nearest node and line over 5 km | 115.38 | 114.88 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3704
4 | 705 | 3705 | 0403403018 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Niño | 14.328 | 121.0823 | U | 8480 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.37 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 65.28 | 45.64 | 65.28 |  | C - Line within 0.5 km; node over 1 km | 1.37 | 0.45 | Line: AE CRC005-BNL001-CLB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3705
4 | 706 | 3706 | 0600616038 | Region VI (Western Visayas) | Antique | Sibalom | Indag-an | 10.7657 | 122.0864 | R | 324 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.22 | 11.11 | Tier 2 High GIDA (Score 40.0–49.9) | 65.27 | 45.63 | 65.27 |  | F - Nearest node and line over 5 km | 16.22 | 10.94 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3706
4 | 707 | 3707 | 1102504008 | Region XI (Davao Region) | Davao Oriental | Caraga | Palma Gil | 7.3954 | 126.4739 | R | 1932 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.55 | 56.01 | Tier 2 High GIDA (Score 40.0–49.9) | 65.26 | 45.62 | 65.26 |  | F - Nearest node and line over 5 km | 56.55 | 55.85 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3707
4 | 708 | 3708 | 0802605001 | Region VIII (Eastern Visayas) | Eastern Samar | Can-Avid | Balagon | 11.9131 | 125.2528 | R | 305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.7 | 82.3 | Tier 2 High GIDA (Score 40.0–49.9) | 65.25 | 45.62 | 65.25 |  | F - Nearest node and line over 5 km | 79.7 | 82.29 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3708
4 | 709 | 3709 | PH0003709 | IV-A | Cavite | City of Bacoor | Niog | 14.4581 | 120.9382 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.05 | 2.6 | Tier 2 High GIDA (Score 40.0–49.9) | 65.25 | 45.62 | 65.25 |  | D - Other node or line within 3 km | 1.72 | 1.06 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 3709
4 | 710 | 3710 | 0604513013 | Region VI (Western Visayas) | Negros Occidental | Ilog | Pinggot | 9.7239 | 122.6775 | R | 3513 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.51 | 24.35 | Tier 2 High GIDA (Score 40.0–49.9) | 65.25 | 45.61 | 65.25 |  | F - Nearest node and line over 5 km | 27.51 | 24.35 | Line: SIPALAY TO BAYAWAN-84,748m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3710
4 | 711 | 3711 | 0405636020 | Region IV-A (CALABARZON) | Quezon | Polillo | Tamulaya-Anitong | 14.7756 | 121.9216 | R | 505 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.61 | 62.56 | Tier 2 High GIDA (Score 40.0–49.9) | 65.24 | 45.61 | 65.24 |  | F - Nearest node and line over 5 km | 27.61 | 62.54 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3711
4 | 712 | 3712 | 0806019011 | Region VIII (Eastern Visayas) | Samar | Talalora | Victory | 11.5097 | 124.8304 | R | 272 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.96 | 27.71 | Tier 2 High GIDA (Score 40.0–49.9) | 65.24 | 45.61 | 65.24 |  | F - Nearest node and line over 5 km | 27.96 | 27.71 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3712
4 | 713 | 3713 | 0806012019 | Region VIII (Eastern Visayas) | Samar | Motiong | Inalad | 11.8203 | 125.0367 | R | 725 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.68 | 67.66 | Tier 2 High GIDA (Score 40.0–49.9) | 65.23 | 45.6 | 65.23 |  | F - Nearest node and line over 5 km | 64.68 | 67.65 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3713
4 | 714 | 3714 | PH0003714 | CAR | Benguet | Baguio City | Lopez Jaena | 16.4057 | 120.5853 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 5.13 | Tier 2 High GIDA (Score 40.0–49.9) | 65.23 | 45.6 | 65.23 |  | C - Line within 0.5 km; node over 1 km | 1.06 | 0.04 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3714
4 | 715 | 3715 | PH0003715 | III | Pampanga | Angeles City | Malabañas | 15.1571 | 120.5945 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.55 | Tier 2 High GIDA (Score 40.0–49.9) | 65.22 | 45.6 | 65.22 |  | B - Node 0.5-1 km | 0.67 | 0.22 | Line: 88 CORE (11X8) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3715
4 | 716 | 3716 | 1908706010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Maitong | 17.254 | 122.2282 | R | 3868 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 65.22 | 45.6 | 65.22 |  | F - Nearest node and line over 5 km | 29.3 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3716
4 | 717 | 3717 | PH0003717 | I | Ilocos Norte | Laoag City | Bgy. No. 21, San Pedro (Pob.) | 18.1882 | 120.553 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.69 | 2.67 | Tier 2 High GIDA (Score 40.0–49.9) | 65.22 | 45.59 | 65.22 |  | E - Nearest node or line 3-5 km | 3.98 | 3.67 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3717
4 | 718 | 3718 | 0402106046 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño I | 14.3323 | 120.9927 | R | 3010 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.92 | Tier 2 High GIDA (Score 40.0–49.9) | 65.21 | 45.59 | 65.21 |  | D - Other node or line within 3 km | 1.66 | 5.03 | Node: DMC005 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3718
4 | 719 | 3719 | PH0003719 | I | Pangasinan | Dagupan City | Poblacion Oeste | 16.0432 | 120.3332 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.5 | 0.02 | Tier 2 High GIDA (Score 40.0–49.9) | 65.19 | 45.57 | 65.19 |  | C - Line within 0.5 km; node over 1 km | 2.5 | 0.01 | Line: DAGUPAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3719
4 | 720 | 3720 | PH0003720 | III | Pampanga | Angeles City | Virgen Delos Remedios | 15.1494 | 120.5926 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.25 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 65.19 | 45.57 | 65.19 |  | A - Node within 0.5 km | 0.25 | 0.06 | Line: ANGELES | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3720
4 | 721 | 3721 | 0306916041 | Region III (Central Luzon) | Tarlac | City of Tarlac | Ligtasan | 15.4798 | 120.5987 | U | 2478 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 65.18 | 45.57 | 65.18 |  | C - Line within 0.5 km; node over 1 km | 1.43 | 0.37 | Line: 48 CORE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3721
4 | 722 | 3722 | 0201509007 | Region II (Cagayan Valley) | Cagayan | Calayan | Naguilian | 18.8887 | 121.8701 | R | 1662 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.84 | 52.24 | Tier 2 High GIDA (Score 40.0–49.9) | 65.18 | 45.57 | 65.18 |  | F - Nearest node and line over 5 km | 54.84 | 52.24 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3722
4 | 723 | 3723 | 1381100192 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 192 | 14.3106 | 121.0675 | U | 4337 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 1.54 | Tier 2 High GIDA (Score 40.0–49.9) | 65.17 | 45.56 | 65.17 |  | A - Node within 0.5 km | 0.44 | 0.23 | Line: AE CRC005-BNL001-CLB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3723
4 | 724 | 3724 | 1705320031 | MIMAROPA Region | Palawan | Taytay | Paglaum | 10.6561 | 119.5024 | R | 2532 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.41 | 4.61 | Tier 2 High GIDA (Score 40.0–49.9) | 65.17 | 45.56 | 65.17 |  | E - Nearest node or line 3-5 km | 6.41 | 4.61 | Line: TAYTAY - PUERTO PRINCESA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3724
4 | 725 | 3725 | 1403201006 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Dao-angan | 17.4806 | 121.2513 | R | 569 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.74 | 7.17 | Tier 2 High GIDA (Score 40.0–49.9) | 65.17 | 45.56 | 65.17 |  | F - Nearest node and line over 5 km | 12.74 | 7.17 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3725
4 | 726 | 3726 | PH0003726 | VIII | Leyte | Tacloban City | Barangay 48-B | 11.245 | 125.0058 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.81 | 13.85 | Tier 2 High GIDA (Score 40.0–49.9) | 65.17 | 45.56 | 65.17 |  | B - Node 0.5-1 km | 0.7 | 3.63 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3726
4 | 727 | 3727 | 0403428008 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Labas | 14.3064 | 121.1113 | U | 23335 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.92 | Tier 2 High GIDA (Score 40.0–49.9) | 65.15 | 45.54 | 65.15 |  | D - Other node or line within 3 km | 1.05 | 0.89 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 3727
4 | 728 | 3728 | 1908823006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Kulambog | 17.255 | 122.229 | R | 3701 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 65.14 | 45.54 | 65.14 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3728
4 | 729 | 3729 | PH0003729 | IV-A | Cavite | Imus City | Poblacion III-B | 14.3672 | 120.8542 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 1.09 | Tier 2 High GIDA (Score 40.0–49.9) | 65.14 | 45.54 | 65.14 |  | A - Node within 0.5 km | 0.16 | 1.55 | Node: TZC002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3729
4 | 730 | 3730 | 1903628039 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tubaran | Bagiangun | 17.2547 | 122.2282 | R | 748 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.81 | 35.28 | Tier 2 High GIDA (Score 40.0–49.9) | 65.13 | 45.53 | 65.13 |  | F - Nearest node and line over 5 km | 29.35 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3730
4 | 731 | 3731 | PH0003731 | VII | Cebu | Cebu City | Cogon Pardo | 10.3101 | 123.8386 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.44 | 5.52 | Tier 2 High GIDA (Score 40.0–49.9) | 65.12 | 45.53 | 65.12 |  | E - Nearest node or line 3-5 km | 3.66 | 3.61 | Line: CEBU - TOLEDO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3731
4 | 732 | 3732 | 0203110006 | Region II (Cagayan Valley) | Isabela | Dinapigue | Dimaluade | 16.5238 | 122.2648 | R | 300 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 1.51 | Tier 2 High GIDA (Score 40.0–49.9) | 65.12 | 45.53 | 65.12 |  | A - Node within 0.5 km | 0.22 | 64.82 | Node: DPI001 - TYPE 4A | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3732
4 | 733 | 3733 | 1400114007 | Cordillera Administrative Region (CAR) | Abra | Luba | Nagbukel-Tuquipa | 17.3293 | 120.6595 | R | 543 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.87 | 12.14 | Tier 2 High GIDA (Score 40.0–49.9) | 65.11 | 45.52 | 65.11 |  | F - Nearest node and line over 5 km | 16.87 | 12.03 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3733
4 | 734 | 3734 | 0403405053 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Cristobal | 14.2226 | 121.1456 | U | 16312 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.78 | 0.61 | Tier 2 High GIDA (Score 40.0–49.9) | 65.11 | 45.52 | 65.11 |  | D - Other node or line within 3 km | 2.78 | 0.61 | Line: AE SPL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3734
4 | 735 | 3735 | 1403201003 | Cordillera Administrative Region (CAR) | Kalinga | Balbalan | Balbalan Proper | 17.441 | 121.2016 | R | 1040 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.61 | 5.15 | Tier 2 High GIDA (Score 40.0–49.9) | 65.11 | 45.52 | 65.11 |  | E - Nearest node or line 3-5 km | 19.61 | 4.94 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3735
4 | 736 | 3736 | PH0003736 | IV-A | Quezon | Lucena City | Barangay 7 (Pob.) | 13.9326 | 121.6106 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.12 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 65.11 | 45.52 | 65.11 |  | A - Node within 0.5 km | 0.12 | 0.07 | Line: UG LCQ001 TO SJB002 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3736
4 | 737 | 3737 | 0301407018 | Region III (Central Luzon) | Bulacan | Calumpit | Palimbang | 14.8984 | 120.7863 | R | 1760 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 1.21 | Tier 2 High GIDA (Score 40.0–49.9) | 65.1 | 45.51 | 65.1 |  | D - Other node or line within 3 km | 2.18 | 0.77 | Line: Calumpit-Baliuag Path | Route options survey candidate: compare actual node lateral with approved line tap. | 3737
4 | 738 | 3738 | PH0003738 | III | Pampanga | Angeles City | Sto. Rosario (Pob.) | 15.1597 | 120.5721 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 65.09 | 45.5 | 65.09 |  | D - Other node or line within 3 km | 1.39 | 0.68 | Line: 48 CORE | Route options survey candidate: compare actual node lateral with approved line tap. | 3738
4 | 739 | 3739 | PH0003739 | VII | Cebu | Cebu City | Sambag I (Pob.) | 10.2994 | 123.8956 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.4 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 65.08 | 45.5 | 65.08 |  | A - Node within 0.5 km | 0.4 | 0.03 | Line: DANAO - CEBU | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3739
4 | 740 | 3740 | 0402123008 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Bernardo Pulido | 14.3122 | 121.0201 | U | 15115 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 3.23 | Tier 2 High GIDA (Score 40.0–49.9) | 65.07 | 45.49 | 65.07 |  | D - Other node or line within 3 km | 2.35 | 3.23 | Node: CRC002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 3740
4 | 741 | 3741 | 0301407024 | Region III (Central Luzon) | Bulacan | Calumpit | San Marcos | 14.8978 | 120.7787 | U | 2792 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 65.06 | 45.49 | 65.06 |  | C - Line within 0.5 km; node over 1 km | 1.51 | 0.26 | Line: 24 CORE (3X8) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3741
4 | 742 | 3742 | 1400126009 | Cordillera Administrative Region (CAR) | Abra | Tubo | Wayangan | 17.257 | 120.7054 | R | 470 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.64 | 7.56 | Tier 2 High GIDA (Score 40.0–49.9) | 65.06 | 45.48 | 65.06 |  | F - Nearest node and line over 5 km | 13.64 | 7.51 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3742
4 | 743 | 3743 | 0201509003 | Region II (Cagayan Valley) | Cagayan | Calayan | Dadao | 19.2562 | 121.4885 | R | 2099 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.01 | 79.27 | Tier 2 High GIDA (Score 40.0–49.9) | 65.05 | 45.48 | 65.05 |  | F - Nearest node and line over 5 km | 82.01 | 79.26 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3743
4 | 744 | 3744 | PH0003744 | V | Camarines Sur | Naga City | Igualdad Interior | 7.839 | 122.7136 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 1.15 | Tier 2 High GIDA (Score 40.0–49.9) | 65.04 | 45.47 | 65.04 |  | E - Nearest node or line 3-5 km | 15.75 | 3.35 | Line: BUUG - IPIL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3744
4 | 745 | 3745 | 0907311005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Bolisong | 7.7766 | 123.2122 | R | 908 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.08 | 2.28 | Tier 2 High GIDA (Score 40.0–49.9) | 65.02 | 45.45 | 65.02 |  | D - Other node or line within 3 km | 18.08 | 2.28 | Line: PAGADIAN - BUUG | Route options survey candidate: compare actual node lateral with approved line tap. | 3745
4 | 746 | 3746 | 1906612021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Kungtad West | 17.2558 | 122.2303 | R | 1775 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.17 | 1.98 | Tier 2 High GIDA (Score 40.0–49.9) | 65.01 | 45.45 | 65.01 |  | F - Nearest node and line over 5 km | 29.6 | 34.46 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3746
4 | 747 | 3747 | 0804810029 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Palanas | 12.2919 | 124.9989 | R | 572 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.65 | 104.07 | Tier 2 High GIDA (Score 40.0–49.9) | 65.01 | 45.45 | 65.01 |  | F - Nearest node and line over 5 km | 104.65 | 103.98 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3747
4 | 748 | 3748 | PH0003748 | NCR | Metro Manila | Caloocan City | Barangay 175 | 14.7568 | 121.0562 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.85 | 20.88 | Tier 2 High GIDA (Score 40.0–49.9) | 65.01 | 45.45 | 65.01 |  | C - Line within 0.5 km; node over 1 km | 1.22 | 0.27 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3748
4 | 749 | 3749 | 0806025014 | Region VIII (Eastern Visayas) | Samar | San Jorge | Janipon | 11.9241 | 124.89 | R | 278 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.78 | 72.72 | Tier 2 High GIDA (Score 40.0–49.9) | 65 | 45.44 | 65 |  | F - Nearest node and line over 5 km | 72.78 | 72.72 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3749
4 | 750 | 3750 | 1906612046 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Pislong | 17.2556 | 122.2296 | R | 1178 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 65 | 45.44 | 65 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3750
4 | 751 | 3751 | 0403405039 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 2 | 14.1982 | 121.1382 | U | 11649 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.42 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 64.99 | 45.43 | 64.99 |  | B - Node 0.5-1 km | 0.87 | 0.08 | Line: Untitled Path | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3751
4 | 752 | 3752 | 0200904004 | Region II (Cagayan Valley) | Batanes | Mahatao | Uvoy | 20.3995 | 121.9637 | R | 375 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 218.46 | 211.91 | Tier 2 High GIDA (Score 40.0–49.9) | 64.99 | 45.43 | 64.99 |  | F - Nearest node and line over 5 km | 215.01 | 211.91 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3752
4 | 753 | 3753 | 1401108003 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Boklaoan | 16.6236 | 120.6583 | R | 478 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.75 | 9.74 | Tier 2 High GIDA (Score 40.0–49.9) | 64.97 | 45.42 | 64.97 |  | F - Nearest node and line over 5 km | 7.75 | 9.64 | Node: KPB001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3753
4 | 754 | 3754 | PH0003754 | NCR | Metro Manila | Caloocan City | Barangay 174 | 14.7621 | 121.0492 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.28 | 74.62 | Tier 2 High GIDA (Score 40.0–49.9) | 64.96 | 45.42 | 64.96 |  | B - Node 0.5-1 km | 0.85 | 0.49 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3754
4 | 755 | 3755 | 1380400004 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Catmon | 14.6647 | 120.9623 | U | 45977 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 0.47 | Tier 2 High GIDA (Score 40.0–49.9) | 64.96 | 45.42 | 64.96 |  | B - Node 0.5-1 km | 0.66 | 0.41 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3755
4 | 756 | 3756 | PH0003756 | IV-A | Quezon | Lucena City | Barangay 5 (Pob.) | 13.9358 | 121.6095 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.37 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 64.94 | 45.4 | 64.94 |  | A - Node within 0.5 km | 0.37 | 0.03 | Line: UG | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3756
4 | 757 | 3757 | 0402111017 | Region IV-A (CALABARZON) | Cavite | Kawit | Manggahan-Lawin | 14.4504 | 120.8917 | R | 4886 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.23 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 64.94 | 45.4 | 64.94 |  | D - Other node or line within 3 km | 2.5 | 2.05 | Line: KAWIT | Route options survey candidate: compare actual node lateral with approved line tap. | 3757
4 | 758 | 3758 | 1400119012 | Cordillera Administrative Region (CAR) | Abra | Pilar | Narnara | 10.7737 | 124.5151 | R | 297 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.22 | 11.15 | Tier 2 High GIDA (Score 40.0–49.9) | 64.94 | 45.4 | 64.94 |  | F - Nearest node and line over 5 km | 18.89 | 10.85 | Line: ORMOC - PALOMPON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3758
4 | 759 | 3759 | PH0003759 | CAR | Benguet | Baguio City | Bal-Marcoville | 16.4135 | 120.5912 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 64.93 | 45.39 | 64.93 |  | A - Node within 0.5 km | 0.29 | 0.05 | Line: BAGUIO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3759
4 | 760 | 3760 | PH0003760 | CAR | Benguet | Baguio City | BGH Compound | 16.4042 | 120.5668 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.99 | Tier 2 High GIDA (Score 40.0–49.9) | 64.91 | 45.38 | 64.91 |  | B - Node 0.5-1 km | 0.59 | 0.6 | Node: BGC008 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3760
4 | 761 | 3761 | 1907011006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Imam Hadji Mohammad | 17.2552 | 122.2299 | R | 1921 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.06 | 30.06 | Tier 2 High GIDA (Score 40.0–49.9) | 64.91 | 45.38 | 64.91 |  | F - Nearest node and line over 5 km | 29.52 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3761
4 | 762 | 3762 | PH0003762 | IV-A | Laguna | San Pablo City | Barangay IV-C (Pob.) | 14.0146 | 121.3379 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 0.05 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | C - Line within 0.5 km; node over 1 km | 5.05 | 0.06 | Line: SPO001 TO SAN JUAN CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3762
4 | 763 | 3763 | PH0003763 | VIII | Leyte | Tacloban City | Barangay 50-A | 11.2369 | 125.0006 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.36 | 2.88 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | A - Node within 0.5 km | 0.36 | 2.86 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3763
4 | 764 | 3764 | 1705304005 | MIMAROPA Region | Palawan | Balabac | Indalawan | 7.8467 | 117.0611 | R | 1323 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 279.51 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | F - Nearest node and line over 5 km | 279.51 | 281.49 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3764
4 | 765 | 3765 | PH0003765 | XI | Davao Del Sur | Davao City | Agdao | 7.0897 | 125.6275 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.46 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | D - Other node or line within 3 km | 2.46 | 1.08 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 3765
4 | 766 | 3766 | 0301416014 | Region III (Central Luzon) | Bulacan | Paombong | Santa Cruz | 14.7609 | 120.7916 | R | 1449 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.04 | 10.4 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | F - Nearest node and line over 5 km | 7.04 | 10.42 | Node: MSB002 - TYPE4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3766
4 | 767 | 3767 | 0403404011 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Niugan | 14.263 | 121.1286 | U | 42286 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.03 | 1.29 | Tier 2 High GIDA (Score 40.0–49.9) | 64.9 | 45.37 | 64.9 |  | C - Line within 0.5 km; node over 1 km | 1.87 | 0.12 | Line: BÑL001 TO CLB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3767
4 | 768 | 3768 | 1705318002 | MIMAROPA Region | Palawan | Roxas | Antonino | 10.4353 | 119.4969 | R | 1499 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.19 | 13.27 | Tier 2 High GIDA (Score 40.0–49.9) | 64.89 | 45.37 | 64.89 |  | F - Nearest node and line over 5 km | 21.19 | 13.21 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3768
4 | 769 | 3769 | PH0003769 | III | Nueva Ecija | Cabanatuan City | Vijandre District (Pob.) | 15.477 | 120.9542 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.29 | 2.62 | Tier 2 High GIDA (Score 40.0–49.9) | 64.89 | 45.37 | 64.89 |  | B - Node 0.5-1 km | 0.91 | 0.42 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3769
4 | 770 | 3770 | PH0003770 | III | Nueva Ecija | Cabanatuan City | Imelda District | 15.4755 | 120.9612 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 64.88 | 45.36 | 64.88 |  | B - Node 0.5-1 km | 0.69 | 0.33 | Line: MULTINET - SANTA ROSA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3770
4 | 771 | 3771 | 0804806020 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | Claro M. Recto | 12.394 | 125.0988 | R | 480 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 111.37 | 110.61 | Tier 2 High GIDA (Score 40.0–49.9) | 64.87 | 45.35 | 64.87 |  | F - Nearest node and line over 5 km | 111.37 | 110.53 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3771
4 | 772 | 3772 | 1705323007 | MIMAROPA Region | Palawan | Rizal | Latud | 8.6707 | 117.3217 | R | 2499 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 195.37 | 197.62 | Tier 2 High GIDA (Score 40.0–49.9) | 64.87 | 45.35 | 64.87 |  | F - Nearest node and line over 5 km | 195.37 | 197.38 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3772
4 | 773 | 3773 | PH0003773 | CAR | Benguet | Baguio City | Engineers' Hill | 16.4269 | 120.5803 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.02 | 6.74 | Tier 2 High GIDA (Score 40.0–49.9) | 64.86 | 45.35 | 64.86 |  | D - Other node or line within 3 km | 1.22 | 1.51 | Node: BGC007 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 3773
4 | 774 | 3774 | 0200904003 | Region II (Cagayan Valley) | Batanes | Mahatao | Panatayan | 20.4154 | 121.9461 | R | 483 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 219.48 | 213.84 | Tier 2 High GIDA (Score 40.0–49.9) | 64.86 | 45.34 | 64.86 |  | F - Nearest node and line over 5 km | 216.94 | 213.84 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3774
4 | 775 | 3775 | 1400120002 | Cordillera Administrative Region (CAR) | Abra | Sallapadan | Bilabila | 17.4934 | 120.7618 | R | 581 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.73 | 17.59 | Tier 2 High GIDA (Score 40.0–49.9) | 64.86 | 45.34 | 64.86 |  | F - Nearest node and line over 5 km | 18.73 | 17.59 | Line: Bangued | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3775
4 | 776 | 3776 | 0803710015 | Region VIII (Eastern Visayas) | Leyte | Burauen | Candag-on | 10.9071 | 124.8355 | R | 258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.08 | 10.95 | Tier 2 High GIDA (Score 40.0–49.9) | 64.85 | 45.34 | 64.85 |  | F - Nearest node and line over 5 km | 13.93 | 11.86 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3776
4 | 777 | 3777 | PH0003777 | I | Ilocos Norte | Laoag City | Bgy. No. 7-A, Nstra. Sra. De Natividad (Pob.) | 18.2049 | 120.5842 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 64.85 | 45.34 | 64.85 |  | A - Node within 0.5 km | 0.21 | 0.03 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3777
4 | 778 | 3778 | PH0003778 | XIII | Agusan Del Norte | Butuan City | Diego Silang Pob. | 8.9461 | 125.5428 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 64.84 | 45.33 | 64.84 |  | B - Node 0.5-1 km | 0.72 | 0.13 | Line: TRENTO - BUENAVISTA CLS | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3778
4 | 779 | 3779 | 1380200011 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | B. F. International Village | 14.4603 | 120.9989 | U | 82987 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 64.83 | 45.32 | 64.83 |  | B - Node 0.5-1 km | 0.59 | 0.44 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3779
4 | 780 | 3780 | 0601917006 | Region VI (Western Visayas) | Capiz | Tapaz | Agpalali | 11.2899 | 122.4619 | R | 719 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.72 | 11.53 | Tier 2 High GIDA (Score 40.0–49.9) | 64.83 | 45.32 | 64.83 |  | F - Nearest node and line over 5 km | 23.72 | 14.78 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3780
4 | 781 | 3781 | 1908822006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Lamud | 17.2551 | 122.2291 | R | 2242 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 64.83 | 45.32 | 64.83 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3781
4 | 782 | 3782 | 0405811010 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santa Ana | 14.6963 | 121.116 | U | 10398 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.58 | Tier 2 High GIDA (Score 40.0–49.9) | 64.82 | 45.32 | 64.82 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.5 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3782
4 | 783 | 3783 | 0804822011 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Gebolwangan | 12.2866 | 124.8057 | R | 805 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 85.4 | 85.38 | Tier 2 High GIDA (Score 40.0–49.9) | 64.81 | 45.31 | 64.81 |  | F - Nearest node and line over 5 km | 85.4 | 85.31 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3783
4 | 784 | 3784 | 1705311006 | MIMAROPA Region | Palawan | Dumaran | Culasian | 10.605 | 119.6531 | R | 1119 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.21 | 20.55 | Tier 2 High GIDA (Score 40.0–49.9) | 64.81 | 45.31 | 64.81 |  | F - Nearest node and line over 5 km | 12.21 | 20.54 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3784
4 | 785 | 3785 | PH0003785 | VI | Iloilo | Iloilo City | Lopez Jaena | 10.6933 | 122.5609 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.88 | 12.69 | Tier 2 High GIDA (Score 40.0–49.9) | 64.81 | 45.31 | 64.81 |  | D - Other node or line within 3 km | 2 | 1.27 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3785
4 | 786 | 3786 | 0300803021 | Region III (Central Luzon) | Bataan | City of Balanga | Tenejero | 14.6787 | 120.533 | U | 9639 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 64.81 | 45.31 | 64.81 |  | D - Other node or line within 3 km | 1 | 0.95 | Line: 60 CORE 5X12 | Route options survey candidate: compare actual node lateral with approved line tap. | 3786
4 | 787 | 3787 | 1705320010 | MIMAROPA Region | Palawan | Taytay | Cataban | 10.985 | 119.3967 | R | 1482 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.79 | 21.71 | Tier 2 High GIDA (Score 40.0–49.9) | 64.8 | 45.3 | 64.8 |  | F - Nearest node and line over 5 km | 9.79 | 21.53 | Node: ENW004 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3787
4 | 788 | 3788 | 0300803019 | Region III (Central Luzon) | Bataan | City of Balanga | Talisay | 14.6811 | 120.5454 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 64.79 | 45.3 | 64.79 |  | A - Node within 0.5 km | 0.28 | 0.1 | Line: CITY OF BALANGA | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3788
4 | 789 | 3789 | 0305412027 | Region III (Central Luzon) | Pampanga | Masantol | Sapang Kawayan | 14.8053 | 120.6858 | U | 3449 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8 | 8.83 | Tier 2 High GIDA (Score 40.0–49.9) | 64.79 | 45.3 | 64.79 |  | F - Nearest node and line over 5 km | 8 | 14.02 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3789
4 | 790 | 3790 | 0600609029 | Region VI (Western Visayas) | Antique | Laua-An | Necesito | 11.0901 | 122.1058 | R | 276 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.25 | 37.1 | Tier 2 High GIDA (Score 40.0–49.9) | 64.79 | 45.29 | 64.79 |  | F - Nearest node and line over 5 km | 40.8 | 33.83 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3790
4 | 791 | 3791 | 0402118051 | Region IV-A (CALABARZON) | Cavite | Silang | Ipil I | 14.2739 | 120.9947 | R | 3128 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.23 | 2.95 | Tier 2 High GIDA (Score 40.0–49.9) | 64.78 | 45.29 | 64.78 |  | D - Other node or line within 3 km | 1.23 | 2.94 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3791
4 | 792 | 3792 | 0401019005 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 11 | 14.0893 | 120.7753 | U | 3402 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.67 | 1.99 | Tier 2 High GIDA (Score 40.0–49.9) | 64.78 | 45.29 | 64.78 |  | C - Line within 0.5 km; node over 1 km | 2.98 | 0.08 | Line: TGY001 TO NSB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3792
4 | 793 | 3793 | PH0003793 | VIII | Leyte | Tacloban City | Barangay 53 | 11.2341 | 125.0034 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 2.49 | Tier 2 High GIDA (Score 40.0–49.9) | 64.76 | 45.28 | 64.76 |  | B - Node 0.5-1 km | 0.63 | 2.48 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3793
4 | 794 | 3794 | PH0003794 | I | Pangasinan | Dagupan City | Pantal | 16.0499 | 120.3402 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 64.76 | 45.27 | 64.76 |  | D - Other node or line within 3 km | 3.39 | 0.52 | Line: DAGUPAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3794
4 | 795 | 3795 | PH0003795 | VIII | Leyte | Tacloban City | Barangay 37 | 11.2013 | 125.0207 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.33 | 2.92 | Tier 2 High GIDA (Score 40.0–49.9) | 64.76 | 45.27 | 64.76 |  | D - Other node or line within 3 km | 1.75 | 1.44 | Line: CAPOOCAN - TACLOBAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3795
4 | 796 | 3796 | 1907009018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Kalupag | 17.2558 | 122.2298 | R | 1420 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 64.75 | 45.27 | 64.75 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3796
4 | 797 | 3797 | 0804806014 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | Hiparayan | 12.419 | 125.0356 | R | 735 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.03 | 103.26 | Tier 2 High GIDA (Score 40.0–49.9) | 64.74 | 45.26 | 64.74 |  | F - Nearest node and line over 5 km | 104.03 | 103.18 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3797
4 | 798 | 3798 | 0306916078 | Region III (Central Luzon) | Tarlac | City of Tarlac | Santo Cristo | 15.4883 | 120.5944 | U | 3012 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.05 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 64.74 | 45.26 | 64.74 |  | C - Line within 0.5 km; node over 1 km | 2.05 | 0.08 | Line: 33,700 mtrs. | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3798
4 | 799 | 3799 | 0804810008 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Cuenco | 12.2436 | 124.9225 | R | 314 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 98.96 | 98.86 | Tier 2 High GIDA (Score 40.0–49.9) | 64.74 | 45.26 | 64.74 |  | F - Nearest node and line over 5 km | 98.96 | 98.76 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3799
4 | 800 | 3800 | 0804822020 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | San Isidro | 12.282 | 124.849 | R | 409 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 89.94 | 89.8 | Tier 2 High GIDA (Score 40.0–49.9) | 64.73 | 45.25 | 64.73 |  | F - Nearest node and line over 5 km | 89.94 | 89.7 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3800
4 | 801 | 3801 | 0804806032 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | P. Rebadulla | 12.4545 | 125.087 | R | 464 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 108.6 | 107.77 | Tier 2 High GIDA (Score 40.0–49.9) | 64.73 | 45.25 | 64.73 |  | F - Nearest node and line over 5 km | 108.6 | 107.69 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3801
4 | 802 | 3802 | 0804822001 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Balud | 12.2743 | 124.8101 | R | 300 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.38 | 86.37 | Tier 2 High GIDA (Score 40.0–49.9) | 64.73 | 45.25 | 64.73 |  | F - Nearest node and line over 5 km | 86.38 | 86.35 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3802
4 | 803 | 3803 | 0806012012 | Region VIII (Eastern Visayas) | Samar | Motiong | Canatuan | 11.8348 | 125.0146 | R | 254 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.2 | 69.03 | Tier 2 High GIDA (Score 40.0–49.9) | 64.73 | 45.25 | 64.73 |  | F - Nearest node and line over 5 km | 66.2 | 69.03 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3803
4 | 804 | 3804 | 0804810038 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Rufino | 12.2842 | 124.9917 | R | 226 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 104.25 | 103.69 | Tier 2 High GIDA (Score 40.0–49.9) | 64.73 | 45.25 | 64.73 |  | F - Nearest node and line over 5 km | 104.25 | 103.59 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3804
4 | 805 | 3805 | PH0003805 | CAR | Benguet | Baguio City | Ferdinand | 16.4051 | 120.6205 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.31 | 0.84 | Tier 2 High GIDA (Score 40.0–49.9) | 64.71 | 45.24 | 64.71 |  | D - Other node or line within 3 km | 2.26 | 0.64 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3805
4 | 806 | 3806 | 0403426017 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay IV | 13.0549 | 120.756 | U | 1071 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 0.71 | Tier 2 High GIDA (Score 40.0–49.9) | 64.71 | 45.24 | 64.71 |  | F - Nearest node and line over 5 km | 50.01 | 48.21 | Line: MINDORO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3806
4 | 807 | 3807 | 0702216003 | Region VII (Central Visayas) | Cebu | Catmon | Anapog | 10.6617 | 123.9071 | R | 287 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.21 | 11.03 | Tier 2 High GIDA (Score 40.0–49.9) | 64.71 | 45.24 | 64.71 |  | F - Nearest node and line over 5 km | 12.21 | 11.03 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3807
4 | 808 | 3808 | 0504103024 | Region V (Bicol Region) | Masbate | Balud | Sampad | 11.9871 | 123.2123 | R | 503 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.68 | 10.74 | Tier 2 High GIDA (Score 40.0–49.9) | 64.7 | 45.23 | 64.7 |  | F - Nearest node and line over 5 km | 9.68 | 41.22 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3808
4 | 809 | 3809 | 0305412021 | Region III (Central Luzon) | Pampanga | Masantol | Sta. Cruz | 14.8271 | 120.6821 | R | 2602 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.01 | 3.59 | Tier 2 High GIDA (Score 40.0–49.9) | 64.7 | 45.23 | 64.7 |  | F - Nearest node and line over 5 km | 7.57 | 12.68 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3809
4 | 810 | 3810 | 1408101005 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Naguilian | 18.1759 | 121.0685 | R | 388 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.51 | 28.55 | Tier 2 High GIDA (Score 40.0–49.9) | 64.69 | 45.23 | 64.69 |  | F - Nearest node and line over 5 km | 21.07 | 32.52 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3810
4 | 811 | 3811 | 1906612006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | Bulansing Tara | 17.2562 | 122.2294 | R | 866 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.76 | 3.02 | Tier 2 High GIDA (Score 40.0–49.9) | 64.68 | 45.22 | 64.68 |  | F - Nearest node and line over 5 km | 29.56 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3811
4 | 812 | 3812 | PH0003812 | I | Ilocos Norte | Laoag City | Bgy. No. 8, San Vicente (Pob.) | 18.2133 | 120.6126 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.17 | 2.5 | Tier 2 High GIDA (Score 40.0–49.9) | 64.67 | 45.21 | 64.67 |  | D - Other node or line within 3 km | 2.96 | 0.91 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 3812
4 | 813 | 3813 | 0804824004 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Cag-aguingay | 12.3523 | 124.5839 | R | 346 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.43 | 60.42 | Tier 2 High GIDA (Score 40.0–49.9) | 64.67 | 45.21 | 64.67 |  | F - Nearest node and line over 5 km | 60.43 | 60.4 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3813
4 | 814 | 3814 | 0402106077 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz II | 14.291 | 120.9741 | R | 2251 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.06 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 64.67 | 45.21 | 64.67 |  | D - Other node or line within 3 km | 1.94 | 1.63 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3814
4 | 815 | 3815 | 0806013002 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Barangay I | 11.6127 | 124.9846 | R | 680 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.54 | 44.59 | Tier 2 High GIDA (Score 40.0–49.9) | 64.67 | 45.21 | 64.67 |  | F - Nearest node and line over 5 km | 41.54 | 44.58 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3815
4 | 816 | 3816 | 0804806023 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | Magongon | 12.37 | 125.0429 | R | 451 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 106.25 | 105.54 | Tier 2 High GIDA (Score 40.0–49.9) | 64.66 | 45.21 | 64.66 |  | F - Nearest node and line over 5 km | 106.25 | 105.46 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3816
4 | 817 | 3817 | 1003523021 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Pitubo | 8.0643 | 124.2814 | R | 768 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.75 | 0.79 | Tier 2 High GIDA (Score 40.0–49.9) | 64.66 | 45.2 | 64.66 |  | D - Other node or line within 3 km | 6.09 | 1.55 | Line: SAGUIARAN | Route options survey candidate: compare actual node lateral with approved line tap. | 3817
4 | 818 | 3818 | 0804810047 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | San Jose | 12.2663 | 125.033 | R | 259 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 109.16 | 108.6 | Tier 2 High GIDA (Score 40.0–49.9) | 64.66 | 45.2 | 64.66 |  | F - Nearest node and line over 5 km | 109.16 | 108.5 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3818
4 | 819 | 3819 | 0804822007 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Camaya-an | 12.2897 | 124.8351 | R | 196 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.22 | 88.07 | Tier 2 High GIDA (Score 40.0–49.9) | 64.66 | 45.2 | 64.66 |  | F - Nearest node and line over 5 km | 88.22 | 87.97 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3819
4 | 820 | 3820 | PH0003820 | IV-A | Quezon | Lucena City | Market View | 13.9338 | 121.6179 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 64.65 | 45.2 | 64.65 |  | B - Node 0.5-1 km | 0.69 | 0.25 | Line: ug to ae | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3820
4 | 821 | 3821 | 0301414002 | Region III (Central Luzon) | Bulacan | Obando | Catanghalan | 14.7069 | 120.9412 | U | 3385 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.57 | 1.65 | Tier 2 High GIDA (Score 40.0–49.9) | 64.64 | 45.19 | 64.64 |  | B - Node 0.5-1 km | 0.57 | 1.62 | Node: OBB001 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3821
4 | 822 | 3822 | 1206502016 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Columbio | Lomoyon | 6.7092 | 124.9355 | R | 1861 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.4 | 8.39 | Tier 2 High GIDA (Score 40.0–49.9) | 64.63 | 45.18 | 64.63 |  | F - Nearest node and line over 5 km | 24.4 | 8.38 | Line: QUIRINO - KIDAPAWAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3822
4 | 823 | 3823 | 0804808030 | Region VIII (Eastern Visayas) | Northern Samar | Laoang | Inamlan | 12.6092 | 124.9992 | R | 918 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 95.2 | 94.09 | Tier 2 High GIDA (Score 40.0–49.9) | 64.62 | 45.17 | 64.62 |  | F - Nearest node and line over 5 km | 95.2 | 95.95 | Node: BSS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3823
4 | 824 | 3824 | 1381400018 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Santa Lucia | 14.5978 | 121.0353 | U | 8602 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.99 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 64.61 | 45.17 | 64.61 |  | B - Node 0.5-1 km | 0.99 | 0.2 | Line: UG 288C via V-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3824
4 | 825 | 3825 | 1381300016 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Blue Ridge B | 14.7139 | 121.0939 | U | 1116 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 0.73 | Tier 2 High GIDA (Score 40.0–49.9) | 64.61 | 45.17 | 64.61 |  | C - Line within 0.5 km; node over 1 km | 1.06 | 0.01 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3825
4 | 826 | 3826 | 1705303008 | MIMAROPA Region | Palawan | Araceli | Mauringuen | 10.5555 | 119.8239 | R | 1085 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.93 | 39.67 | Tier 2 High GIDA (Score 40.0–49.9) | 64.61 | 45.17 | 64.61 |  | F - Nearest node and line over 5 km | 30.93 | 39.67 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3826
4 | 827 | 3827 | 0804824019 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | San Jose | 12.2482 | 124.6563 | R | 400 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.86 | 72.85 | Tier 2 High GIDA (Score 40.0–49.9) | 64.59 | 45.16 | 64.59 |  | F - Nearest node and line over 5 km | 72.86 | 72.83 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3827
4 | 828 | 3828 | 0300803001 | Region III (Central Luzon) | Bataan | City of Balanga | Bagumbayan | 14.6796 | 120.5464 | R | 2159 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.47 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 64.59 | 45.15 | 64.59 |  | A - Node within 0.5 km | 0.47 | 0.3 | Line: CITY OF BALANGA | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3828
4 | 829 | 3829 | 0804810051 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Tagan-ayan | 12.2719 | 125.0075 | R | 341 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 106.37 | 105.81 | Tier 2 High GIDA (Score 40.0–49.9) | 64.59 | 45.15 | 64.59 |  | F - Nearest node and line over 5 km | 106.37 | 105.72 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3829
4 | 830 | 3830 | 0804810039 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Sag-od | 12.25 | 125.0086 | R | 197 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 107.39 | 106.92 | Tier 2 High GIDA (Score 40.0–49.9) | 64.59 | 45.15 | 64.59 |  | F - Nearest node and line over 5 km | 107.39 | 106.83 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3830
4 | 831 | 3831 | 1600304013 | Region XIII (Caraga) | Agusan del Sur | La Paz | Sabang Adgawan | 8.3086 | 125.8767 | R | 1861 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.03 | 12.64 | Tier 2 High GIDA (Score 40.0–49.9) | 64.59 | 45.15 | 64.59 |  | F - Nearest node and line over 5 km | 14.03 | 12.63 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3831
4 | 832 | 3832 | 1906607017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Kawasan | 17.2556 | 122.2295 | R | 980 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.38 | 35.19 | Tier 2 High GIDA (Score 40.0–49.9) | 64.58 | 45.15 | 64.58 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3832
4 | 833 | 3833 | 0402103064 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas II | 14.4332 | 120.9745 | U | 12673 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 1.11 | Tier 2 High GIDA (Score 40.0–49.9) | 64.56 | 45.13 | 64.56 |  | D - Other node or line within 3 km | 1.33 | 1.95 | Node: BRC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3833
4 | 834 | 3834 | 1401105014 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Baculongan Sur | 16.752 | 120.8859 | R | 3798 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.24 | 5.17 | Tier 2 High GIDA (Score 40.0–49.9) | 64.55 | 45.13 | 64.55 |  | F - Nearest node and line over 5 km | 7.24 | 5.04 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3834
4 | 835 | 3835 | 1401107014 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Lusod | 16.6014 | 120.9534 | R | 896 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.59 | 19.71 | Tier 2 High GIDA (Score 40.0–49.9) | 64.53 | 45.11 | 64.53 |  | F - Nearest node and line over 5 km | 12.59 | 19.49 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3835
4 | 836 | 3836 | 0804810054 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | H. Jolejole | 12.2933 | 125.0692 | R | 410 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 111.69 | 111.08 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | F - Nearest node and line over 5 km | 111.69 | 110.99 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3836
4 | 837 | 3837 | 0804810024 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Macarthur | 12.272 | 125.0078 | R | 307 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 107.49 | 106.91 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | F - Nearest node and line over 5 km | 106.38 | 105.73 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3837
4 | 838 | 3838 | 0307702013 | Region III (Central Luzon) | Aurora | Casiguran | Dibet | 16.215 | 122.0615 | R | 849 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | D - Other node or line within 3 km | 2.3 | 30.55 | Node: CSA002 - TYPE 4 | Route options survey candidate: compare actual node lateral with approved line tap. | 3838
4 | 839 | 3839 | 0804822010 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Gebonawan | 12.3589 | 124.6947 | R | 251 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 87.79 | 87.48 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | F - Nearest node and line over 5 km | 71.2 | 70.88 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3839
4 | 840 | 3840 | 0804810006 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Caputoan | 12.252 | 124.946 | R | 335 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 100.96 | 100.7 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | F - Nearest node and line over 5 km | 100.96 | 100.61 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3840
4 | 841 | 3841 | 0804806025 | Region VIII (Eastern Visayas) | Northern Samar | Catubig | Manering | 12.435 | 125.0816 | R | 328 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 108.48 | 107.68 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.11 | 64.52 |  | F - Nearest node and line over 5 km | 108.48 | 107.6 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3841
4 | 842 | 3842 | 1004316001 | Region X (Northern Mindanao) | Misamis Oriental | Lugait | Aya-aya | 8.3387 | 124.3088 | R | 1697 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.14 | 5.28 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.1 | 64.52 |  | F - Nearest node and line over 5 km | 7.14 | 5.27 | Line: CDO - ILIGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3842
4 | 843 | 3843 | 0804822022 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Tobgon | 12.2828 | 124.8494 | R | 126 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.62 | 86.31 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.1 | 64.52 |  | F - Nearest node and line over 5 km | 89.95 | 89.7 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3843
4 | 844 | 3844 | 0804810020 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Lakandula | 12.2738 | 124.9325 | R | 316 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 98.72 | 98.32 | Tier 2 High GIDA (Score 40.0–49.9) | 64.52 | 45.1 | 64.52 |  | F - Nearest node and line over 5 km | 98.72 | 98.23 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3844
4 | 845 | 3845 | PH0003845 | VI | Iloilo | Iloilo City | North San Jose | 10.7238 | 122.5535 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.77 | 3.07 | Tier 2 High GIDA (Score 40.0–49.9) | 64.51 | 45.1 | 64.51 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.45 | Line: ROXAS - ILOILO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3845
4 | 846 | 3846 | 1908705023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Mompong | 7.1773 | 124.2149 | R | 3495 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 64.51 | 45.1 | 64.51 |  | F - Nearest node and line over 5 km | 64.26 | 64.01 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3846
4 | 847 | 3847 | 1908801010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Ampatuan | Tubak | 17.2549 | 122.229 | R | 1401 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.43 | 34.31 | Tier 2 High GIDA (Score 40.0–49.9) | 64.5 | 45.09 | 64.5 |  | F - Nearest node and line over 5 km | 29.43 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3847
4 | 848 | 3848 | 0102820020 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Rufino | 16.1244 | 120.7245 | R | 1162 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 64.5 | 45.09 | 64.5 |  | F - Nearest node and line over 5 km | 8.83 | 8.95 | Node: SMP001 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3848
4 | 849 | 3849 | 1381200022 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Miguel | 14.5669 | 121.0847 | U | 42696 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.34 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 64.5 | 45.09 | 64.5 |  | A - Node within 0.5 km | 0.34 | 0.1 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3849
4 | 850 | 3850 | PH0003850 | III | Nueva Ecija | Cabanatuan City | San Juan Pob. | 15.4718 | 120.9582 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 64.49 | 45.09 | 64.49 |  | C - Line within 0.5 km; node over 1 km | 1.15 | 0.2 | Line: MULTINET - SANTA ROSA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3850
4 | 851 | 3851 | PH0003851 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 12 | 11.8372 | 124.9186 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.46 | 31.26 | Tier 2 High GIDA (Score 40.0–49.9) | 64.49 | 45.08 | 64.49 |  | F - Nearest node and line over 5 km | 64.77 | 64.7 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3851
4 | 852 | 3852 | 1908821003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Saydona Mustapha | Dasawao | 17.2552 | 122.2292 | R | 1730 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 64.49 | 45.08 | 64.49 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3852
4 | 853 | 3853 | PH0003853 | IV-A | Quezon | Lucena City | Barangay 4 (Pob.) | 13.9366 | 121.6161 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 64.49 | 45.08 | 64.49 |  | B - Node 0.5-1 km | 0.63 | 0.07 | Line: ug to ae | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3853
4 | 854 | 3854 | 1907011007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Ligayan | 17.2558 | 122.2299 | R | 2759 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 64.48 | 45.08 | 64.48 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3854
4 | 855 | 3855 | 0601917018 | Region VI (Western Visayas) | Capiz | Tapaz | Da-an Sur | 11.2622 | 122.4467 | R | 879 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.09 | 12.33 | Tier 2 High GIDA (Score 40.0–49.9) | 64.48 | 45.08 | 64.48 |  | F - Nearest node and line over 5 km | 25.09 | 16.21 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3855
4 | 856 | 3856 | 0806013001 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | Bangon | 11.5914 | 124.9871 | R | 1494 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.15 | 42.21 | Tier 2 High GIDA (Score 40.0–49.9) | 64.48 | 45.08 | 64.48 |  | F - Nearest node and line over 5 km | 39.15 | 42.2 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3856
4 | 857 | 3857 | 0601909009 | Region VI (Western Visayas) | Capiz | Panay | Bantique | 11.4937 | 122.8898 | R | 1408 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.34 | 6.21 | Tier 2 High GIDA (Score 40.0–49.9) | 64.48 | 45.08 | 64.48 |  | F - Nearest node and line over 5 km | 6.34 | 6.2 | Line: ROXAS - SARA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3857
4 | 858 | 3858 | 1381300039 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Escopa III | 14.7176 | 121.028 | U | 8320 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.08 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 64.47 | 45.07 | 64.47 |  | C - Line within 0.5 km; node over 1 km | 1.57 | 0.28 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3858
4 | 859 | 3859 | PH0003859 | VIII | Leyte | Tacloban City | Barangay 52 | 11.1952 | 125.0075 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.31 | 6.22 | Tier 2 High GIDA (Score 40.0–49.9) | 64.47 | 45.07 | 64.47 |  | C - Line within 0.5 km; node over 1 km | 1.93 | 0.26 | Line: CAPOOCAN - TACLOBAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3859
4 | 860 | 3860 | 0405804002 | Region IV-A (CALABARZON) | Rizal | Binangonan | Batingan | 14.4726 | 121.1968 | U | 15585 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 64.46 | 45.07 | 64.46 |  | B - Node 0.5-1 km | 0.5 | 0.04 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3860
4 | 861 | 3861 | 0804822023 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Victory | 12.2946 | 124.8019 | R | 566 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.67 | 84.62 | Tier 2 High GIDA (Score 40.0–49.9) | 64.46 | 45.06 | 64.46 |  | F - Nearest node and line over 5 km | 84.67 | 84.52 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3861
4 | 862 | 3862 | PH0003862 | IV-A | Quezon | Lucena City | Barangay 3 (Pob.) | 13.9103 | 121.6178 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.65 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 64.45 | 45.06 | 64.45 |  | D - Other node or line within 3 km | 2.63 | 2.56 | Line: UG | Route options survey candidate: compare actual node lateral with approved line tap. | 3862
4 | 863 | 3863 | 1908808015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Penditen | 17.2552 | 122.2293 | R | 1217 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 64.45 | 45.06 | 64.45 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3863
4 | 864 | 3864 | 1908808002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Andavit | 17.2552 | 122.2293 | R | 1208 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 64.45 | 45.06 | 64.45 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3864
4 | 865 | 3865 | 1380613001 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 649 | 14.5936 | 120.9614 | U | 66716 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.35 | 6.39 | Tier 2 High GIDA (Score 40.0–49.9) | 64.45 | 45.05 | 64.45 |  | A - Node within 0.5 km | 0.02 | 1.66 | Node: MNL068 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3865
4 | 866 | 3866 | PH0003866 | IV-A | Cavite | Imus City | Poblacion III-A (Pob.) | 14.4087 | 120.9422 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.08 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 64.45 | 45.05 | 64.45 |  | A - Node within 0.5 km | 0.25 | 4.22 | Node: IMC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3866
4 | 867 | 3867 | 0600601021 | Region VI (Western Visayas) | Antique | Anini-Y | San Ramon | 10.4393 | 121.9531 | R | 405 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.95 | 17.05 | Tier 2 High GIDA (Score 40.0–49.9) | 64.44 | 45.05 | 64.44 |  | F - Nearest node and line over 5 km | 35.95 | 17 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3867
4 | 868 | 3868 | 0601917010 | Region VI (Western Visayas) | Capiz | Tapaz | Bato-bato | 11.2587 | 122.3938 | R | 401 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.85 | 18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.44 | 45.05 | 64.44 |  | F - Nearest node and line over 5 km | 30.85 | 21.99 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3868
4 | 869 | 3869 | PH0003869 | VIII | Leyte | Tacloban City | Barangay 38 | 11.2383 | 124.9999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.02 | 11.93 | Tier 2 High GIDA (Score 40.0–49.9) | 64.44 | 45.05 | 64.44 |  | A - Node within 0.5 km | 0.31 | 3.04 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3869
4 | 870 | 3870 | PH0003870 | VII | Cebu | Talisay City | Lagtang | 10.288 | 123.8244 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.19 | 12.24 | Tier 2 High GIDA (Score 40.0–49.9) | 64.43 | 45.04 | 64.43 |  | E - Nearest node or line 3-5 km | 3.39 | 3.03 | Line: CEBU - TOLEDO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3870
4 | 871 | 3871 | 1908705008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Bongued | 17.2543 | 122.2272 | R | 4061 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.43 | 45.04 | 64.43 |  | F - Nearest node and line over 5 km | 29.24 | 34.1 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3871
4 | 872 | 3872 | 1900713012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Tong-Umus | 6.297 | 121.9728 | R | 3541 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 69.1 | 69.1 | Tier 2 High GIDA (Score 40.0–49.9) | 64.43 | 45.04 | 64.43 |  | F - Nearest node and line over 5 km | 69.1 | 69.1 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3872
4 | 873 | 3873 | 0305422002 | Region III (Central Luzon) | Pampanga | Sasmuan | Batang 2nd | 14.8183 | 120.6196 | R | 1297 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.11 | 9.12 | Tier 2 High GIDA (Score 40.0–49.9) | 64.42 | 45.04 | 64.42 |  | F - Nearest node and line over 5 km | 9.13 | 9.1 | Line: 96CORE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3873
4 | 874 | 3874 | PH0003874 | BARMM (LaMa+SGA) | North Cotabato | Pigkawayan | Libungan Torreta | 7.1671 | 124.3644 | R | 1951 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.86 | 47.76 | Tier 2 High GIDA (Score 40.0–49.9) | 64.42 | 45.04 | 64.42 |  | F - Nearest node and line over 5 km | 47.86 | 47.75 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3874
4 | 875 | 3875 | 1900713001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Babag | 6.342 | 121.9541 | R | 2870 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 64.57 | 64.56 | Tier 2 High GIDA (Score 40.0–49.9) | 64.42 | 45.03 | 64.42 |  | F - Nearest node and line over 5 km | 64.57 | 64.56 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3875
4 | 876 | 3876 | 1908705001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Ambolodto | 17.2533 | 122.228 | R | 3188 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.42 | 45.03 | 64.42 |  | F - Nearest node and line over 5 km | 29.23 | 34.15 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3876
4 | 877 | 3877 | 1908705004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Bagoenged | 17.2531 | 122.2274 | R | 4600 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.42 | 45.03 | 64.42 |  | F - Nearest node and line over 5 km | 29.17 | 34.08 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3877
4 | 878 | 3878 | PH0003878 | BARMM (LaMa+SGA) | North Cotabato | Pigkawayan | Buricain | 7.2154 | 124.385 | R | 1951 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.45 | 44.88 | Tier 2 High GIDA (Score 40.0–49.9) | 64.41 | 45.03 | 64.41 |  | F - Nearest node and line over 5 km | 45.45 | 44.88 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3878
4 | 879 | 3879 | 1908819008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Pidsandawan | 17.2552 | 122.2292 | R | 2669 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 64.41 | 45.03 | 64.41 |  | F - Nearest node and line over 5 km | 29.47 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3879
4 | 880 | 3880 | 1903615073 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Macuranding | 17.2546 | 122.2287 | R | 1155 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 64.41 | 45.03 | 64.41 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3880
4 | 881 | 3881 | 1908813010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Mamasapano | Pidsandawan | 17.2552 | 122.2293 | R | 998 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.58 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.03 | 64.4 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3881
4 | 882 | 3882 | 1900713010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Sulloh | 6.2893 | 121.9623 | R | 2338 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 70.14 | 70.14 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 70.14 | 70.14 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3882
4 | 883 | 3883 | 1906609041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Tukay | 17.2554 | 122.2294 | R | 1763 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 29.5 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3883
4 | 884 | 3884 | 1900713011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tabuan-Lasa | Tambulig Buton | 6.31 | 121.9681 | R | 2079 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.77 | 67.76 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 67.77 | 67.76 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3884
4 | 885 | 3885 | 1903607016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Butig | Coloyan Tambo | 17.2548 | 122.2288 | R | 1355 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3885
4 | 886 | 3886 | 1204711041 | Region XII (SOCCSKSARGEN) | Cotabato | Pigkawayan | Cabpangi | 7.2345 | 124.4379 | R | 1013 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.75 | 38.73 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 39.75 | 38.7 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3886
4 | 887 | 3887 | 1900705032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Sumisip | Mahatalang | 6.5093 | 122.0432 | R | 1639 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.72 | 44.71 | Tier 2 High GIDA (Score 40.0–49.9) | 64.4 | 45.02 | 64.4 |  | F - Nearest node and line over 5 km | 44.72 | 44.71 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3887
4 | 888 | 3888 | PH0003888 | CAR | Benguet | Baguio City | Victoria Village | 16.4032 | 120.6049 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.42 | 1.13 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.02 | 64.39 |  | B - Node 0.5-1 km | 0.86 | 0 | Line: BAGUIO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3888
4 | 889 | 3889 | 1900705051 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Sumisip | Kaumpamatsakem | 6.5061 | 122.029 | R | 1650 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.22 | 45.22 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.02 | 64.39 |  | F - Nearest node and line over 5 km | 45.22 | 45.22 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3889
4 | 890 | 3890 | PH0003890 | BARMM (LaMa+SGA) | North Cotabato | Pigkawayan | Lower Pangangkalan | 7.1721 | 124.3419 | R | 1951 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.29 | 50.16 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.02 | 64.39 |  | F - Nearest node and line over 5 km | 50.29 | 50.16 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3890
4 | 891 | 3891 | PH0003891 | BARMM (LaMa+SGA) | North Cotabato | Pigkawayan | Lower Baguer | 7.2921 | 124.3831 | R | 1951 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 42.16 | 39.74 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.02 | 64.39 |  | F - Nearest node and line over 5 km | 46.7 | 43.46 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3891
4 | 892 | 3892 | 1908821008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Shariff Saydona Mustapha | Inaladan | 17.2547 | 122.2296 | R | 1306 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.59 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.02 | 64.39 |  | F - Nearest node and line over 5 km | 29.46 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3892
4 | 893 | 3893 | 1908808001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Alonganan | 17.2544 | 122.2287 | R | 733 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.32 | 35.14 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3893
4 | 894 | 3894 | 0201518011 | Region II (Cagayan Valley) | Cagayan | Pamplona | Gattu | 13.5907 | 123.0789 | R | 484 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | A - Node within 0.5 km | 0.22 | 1.68 | Node: PAC002 - TYPE 4 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3894
4 | 895 | 3895 | 1903631020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Mayaman | 17.2552 | 122.2281 | R | 1736 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.93 | 78.75 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | F - Nearest node and line over 5 km | 29.37 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3895
4 | 896 | 3896 | 1903615019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Betayan | 17.255 | 122.2278 | R | 821 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.79 | 41.74 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | F - Nearest node and line over 5 km | 29.34 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3896
4 | 897 | 3897 | 1903602051 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Balabagan | Ilian | 17.2546 | 122.2286 | R | 826 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3897
4 | 898 | 3898 | 1908808009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Kalipapa | 17.2544 | 122.2287 | R | 620 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.72 | 33.91 | Tier 2 High GIDA (Score 40.0–49.9) | 64.39 | 45.01 | 64.39 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3898
4 | 899 | 3899 | 1908707001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bayanga Norte | 17.254 | 122.228 | R | 9210 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 29.28 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3899
4 | 900 | 3900 | 1381600030 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Ugong | 14.6952 | 121.0117 | U | 56285 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 1.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | D - Other node or line within 3 km | 1.22 | 1.15 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3900
4 | 901 | 3901 | 0205703016 | Region II (Cagayan Valley) | Quirino | Diffun | Ifugao Village | 16.4542 | 121.4283 | R | 1340 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.7 | 14.49 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 12.7 | 14.48 | Node: CBQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3901
4 | 902 | 3902 | 0804822004 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Cagda-o | 12.3557 | 124.8802 | R | 273 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.04 | 89.44 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 90.04 | 89.35 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3902
4 | 903 | 3903 | 1908808006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Dado | 17.2553 | 122.2295 | R | 639 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.64 | 34.05 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 29.5 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3903
4 | 904 | 3904 | 1903615029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Calumbog | 17.2546 | 122.2287 | R | 599 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3904
4 | 905 | 3905 | 0804822006 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Camanggaran | 12.2799 | 124.8361 | R | 195 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 88.73 | 88.67 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 88.73 | 88.57 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3905
4 | 906 | 3906 | 1908808008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Duaminanga | 17.2556 | 122.2285 | R | 533 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.24 | 35.46 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 29.44 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3906
4 | 907 | 3907 | 0802606005 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | Caglao-an | 12.0619 | 125.3762 | R | 1097 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 100.09 | 102.56 | Tier 2 High GIDA (Score 40.0–49.9) | 64.38 | 45.01 | 64.38 |  | F - Nearest node and line over 5 km | 100.09 | 102.55 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3907
4 | 908 | 3908 | 1908808010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Liong | 17.2549 | 122.2302 | R | 233 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.06 | 32.92 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.53 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3908
4 | 909 | 3909 | 1908808017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Tee | 17.2552 | 122.2293 | R | 487 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3909
4 | 910 | 3910 | 1908808007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Damabalas | 17.2556 | 122.2285 | R | 556 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.86 | 35.33 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.43 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3910
4 | 911 | 3911 | 0500503021 | Region V (Bicol Region) | Albay | Daraga | Ibaugan | 13.1606 | 123.6927 | R | 727 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.75 | 9.72 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | D - Other node or line within 3 km | 2.54 | 0.57 | Line: IRIGA - LEGAZPI | Route options survey candidate: compare actual node lateral with approved line tap. | 3911
4 | 912 | 3912 | 1908808012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Masigay | 17.2561 | 122.23 | R | 276 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29 | 34.57 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.59 | 34.44 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3912
4 | 913 | 3913 | 1908808003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Salibo | Balanakan | 17.255 | 122.2286 | R | 261 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.71 | 32.95 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.4 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3913
4 | 914 | 3914 | 0305422001 | Region III (Central Luzon) | Pampanga | Sasmuan | Batang 1st | 14.8562 | 120.6205 | R | 317 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.41 | 5.32 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 9.39 | 8.46 | Line: 48 CORE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3914
4 | 915 | 3915 | 1908705024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Datu Odin Sinsuat | Nekitan | 17.2531 | 122.2274 | R | 4632 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 64.37 | 45 | 64.37 |  | F - Nearest node and line over 5 km | 29.17 | 34.08 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3915
4 | 916 | 3916 | 1907009013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Parang Pantay | 17.2558 | 122.2298 | R | 2363 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 64.36 | 44.99 | 64.36 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3916
4 | 917 | 3917 | PH0003917 | IX | Zamboanga Del Sur | Zamboanga City | Baliwasan | 6.915 | 122.0602 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.58 | 1.59 | Tier 2 High GIDA (Score 40.0–49.9) | 64.36 | 44.99 | 64.36 |  | D - Other node or line within 3 km | 1.58 | 1.59 | Node: ZCZ001-TYPE 2 | Route options survey candidate: compare actual node lateral with approved line tap. | 3917
4 | 918 | 3918 | PH0003918 | VII | Cebu | Cebu City | Kinasang-an Pardo | 10.2786 | 123.8563 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.84 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 64.35 | 44.98 | 64.35 |  | B - Node 0.5-1 km | 0.84 | 0.05 | Line: 96c | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3918
4 | 919 | 3919 | PH0003919 | VI | Iloilo | Iloilo City | Tabuc Suba | 10.7333 | 122.5544 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.5 | 9.33 | Tier 2 High GIDA (Score 40.0–49.9) | 64.35 | 44.98 | 64.35 |  | D - Other node or line within 3 km | 1.91 | 0.6 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 3919
4 | 920 | 3920 | PH0003920 | IV-A | Cavite | Cavite City | Barangay 25 | 14.4811 | 120.8929 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.26 | 3.31 | Tier 2 High GIDA (Score 40.0–49.9) | 64.3 | 44.95 | 64.3 |  | B - Node 0.5-1 km | 0.9 | 4.48 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3920
4 | 921 | 3921 | PH0003921 | I | Ilocos Norte | Laoag City | Bgy. No. 20, San Miguel (Pob.) | 18.2521 | 120.5598 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 2.3 | Tier 2 High GIDA (Score 40.0–49.9) | 64.3 | 44.95 | 64.3 |  | E - Nearest node or line 3-5 km | 5.77 | 4.72 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3921
4 | 922 | 3922 | 0401005029 | Region IV-A (CALABARZON) | Batangas | Batangas City | Gulod Labak | 13.6982 | 121.0963 | U | 2480 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.84 | 3.17 | Tier 2 High GIDA (Score 40.0–49.9) | 64.3 | 44.95 | 64.3 |  | E - Nearest node or line 3-5 km | 3.76 | 7.44 | Node: BCY004 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3922
4 | 923 | 3923 | 0402104018 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 7 | 14.2815 | 121.0075 | R | 746 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.65 | 2.03 | Tier 2 High GIDA (Score 40.0–49.9) | 64.29 | 44.95 | 64.29 |  | B - Node 0.5-1 km | 0.61 | 4.48 | Node: MAC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3923
4 | 924 | 3924 | 0200905002 | Region II (Cagayan Valley) | Batanes | Sabtang | Malakdang | 20.3351 | 121.872 | R | 279 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 208.5 | 205.45 | Tier 2 High GIDA (Score 40.0–49.9) | 64.28 | 44.94 | 64.28 |  | F - Nearest node and line over 5 km | 208.5 | 205.45 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3924
4 | 925 | 3925 | 1907006038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | South Ubian | Likud Dampong | 17.2563 | 122.2296 | R | 741 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.12 | 59.91 | Tier 2 High GIDA (Score 40.0–49.9) | 64.27 | 44.93 | 64.27 |  | F - Nearest node and line over 5 km | 29.57 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3925
4 | 926 | 3926 | 0300803025 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang North | 14.6841 | 120.5194 | R | 2656 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.04 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 64.27 | 44.93 | 64.27 |  | C - Line within 0.5 km; node over 1 km | 2.19 | 0.14 | Line: Bagac-Pilar AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3926
4 | 927 | 3927 | 0402111022 | Region IV-A (CALABARZON) | Cavite | Kawit | Tramo-Bantayan | 14.4461 | 120.9162 | U | 3563 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.48 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 64.27 | 44.93 | 64.27 |  | C - Line within 0.5 km; node over 1 km | 3.48 | 0.1 | Line: KAWIT | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3927
4 | 928 | 3928 | 0306916073 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Roque | 15.4845 | 120.5896 | U | 6267 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.43 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 64.27 | 44.93 | 64.27 |  | C - Line within 0.5 km; node over 1 km | 2.43 | 0.27 | Line: (TCT 395)San Vicente 1188mtrs. | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3928
4 | 929 | 3929 | 1400111005 | Cordillera Administrative Region (CAR) | Abra | Lagayan | Pang-ot | 17.7531 | 120.7402 | R | 320 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.81 | 7.1 | Tier 2 High GIDA (Score 40.0–49.9) | 64.23 | 44.9 | 64.23 |  | F - Nearest node and line over 5 km | 12.81 | 7.44 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3929
4 | 930 | 3930 | PH0003930 | CAR | Benguet | Baguio City | General Luna, Lower | 16.4061 | 120.6295 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.96 | 2.87 | Tier 2 High GIDA (Score 40.0–49.9) | 64.23 | 44.9 | 64.23 |  | D - Other node or line within 3 km | 1.35 | 1.11 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 3930
4 | 931 | 3931 | 1908713015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Upi | Nangi | 17.254 | 122.2281 | R | 8566 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 64.21 | 44.89 | 64.21 |  | F - Nearest node and line over 5 km | 29.29 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3931
4 | 932 | 3932 | PH0003932 | III | Nueva Ecija | Cabanatuan City | Rizdelis (Pob.) | 15.4969 | 120.9388 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.37 | 2.07 | Tier 2 High GIDA (Score 40.0–49.9) | 64.19 | 44.87 | 64.19 |  | D - Other node or line within 3 km | 2.94 | 2.53 | Line: TALAVERA - MULTI NET | Route options survey candidate: compare actual node lateral with approved line tap. | 3932
4 | 933 | 3933 | PH0003933 | VII | Cebu | Cebu City | Pardo (Pob.) | 10.2779 | 123.8569 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 64.18 | 44.87 | 64.18 |  | B - Node 0.5-1 km | 0.87 | 0.06 | Line: 96c | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3933
4 | 934 | 3934 | PH0003934 | VII | Cebu | Cebu City | Cogon Ramos (Pob.) | 10.3328 | 123.8713 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.5 | 3.92 | Tier 2 High GIDA (Score 40.0–49.9) | 64.18 | 44.87 | 64.18 |  | D - Other node or line within 3 km | 2.82 | 3.17 | Node: CCY003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3934
4 | 935 | 3935 | PH0003935 | VI | Iloilo | Iloilo City | Veterans Village | 10.684 | 122.5181 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.68 | 4.2 | Tier 2 High GIDA (Score 40.0–49.9) | 64.16 | 44.85 | 64.16 |  | D - Other node or line within 3 km | 2.79 | 2.39 | Line: 2,172 | Route options survey candidate: compare actual node lateral with approved line tap. | 3935
4 | 936 | 3936 | PH0003936 | CAR | Benguet | Baguio City | Sanitary Camp, North | 16.3717 | 120.5778 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.79 | 2.04 | Tier 2 High GIDA (Score 40.0–49.9) | 64.15 | 44.85 | 64.15 |  | D - Other node or line within 3 km | 3.94 | 1.94 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 3936
4 | 937 | 3937 | 1108604005 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Kisulad | 6.5297 | 125.5625 | R | 1420 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.59 | 21.07 | Tier 2 High GIDA (Score 40.0–49.9) | 64.14 | 44.84 | 64.14 |  | F - Nearest node and line over 5 km | 18.59 | 21.05 | Node: MGD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3937
4 | 938 | 3938 | PH0003938 | CAR | Benguet | Baguio City | Salud Mitra | 16.4104 | 120.601 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.21 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 64.14 | 44.84 | 64.14 |  | A - Node within 0.5 km | 0.21 | 0.1 | Line: BAGUIO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3938
4 | 939 | 3939 | 0806001024 | Region VIII (Eastern Visayas) | Samar | Almagro | Tonga-tonga | 11.9058 | 124.3118 | R | 197 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.91 | 72.45 | Tier 2 High GIDA (Score 40.0–49.9) | 64.14 | 44.84 | 64.14 |  | F - Nearest node and line over 5 km | 43.91 | 72.44 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3939
4 | 940 | 3940 | 0403428002 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Balibago | 14.2963 | 121.1045 | U | 23640 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 64.13 | 44.84 | 64.13 |  | A - Node within 0.5 km | 0.28 | 0.02 | Line: AE SRL007-CBL001-CLB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3940
4 | 941 | 3941 | 0501711036 | Region V (Bicol Region) | Camarines Sur | Caramoan | Patag-Belen | 13.7779 | 123.7837 | R | 470 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.7 | 38.84 | Tier 2 High GIDA (Score 40.0–49.9) | 64.13 | 44.83 | 64.13 |  | F - Nearest node and line over 5 km | 8.62 | 32.65 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3941
4 | 942 | 3942 | 0301412010 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Langka | 14.7395 | 120.9806 | U | 4515 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.31 | 0.93 | Tier 2 High GIDA (Score 40.0–49.9) | 64.12 | 44.82 | 64.12 |  | D - Other node or line within 3 km | 1.31 | 0.93 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3942
4 | 943 | 3943 | 0702232009 | Region VII (Central Visayas) | Cebu | Minglanilla | Pakigne | 10.2591 | 123.7922 | U | 14675 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 2.13 | Tier 2 High GIDA (Score 40.0–49.9) | 64.11 | 44.82 | 64.11 |  | D - Other node or line within 3 km | 1.51 | 1.57 | Node: MLL001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3943
4 | 944 | 3944 | 0405637006 | Region IV-A (CALABARZON) | Quezon | Quezon | Del Pilar | 14.0923 | 122.1151 | R | 395 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.81 | 17.73 | Tier 2 High GIDA (Score 40.0–49.9) | 64.11 | 44.82 | 64.11 |  | F - Nearest node and line over 5 km | 10.81 | 17.73 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3944
4 | 945 | 3945 | 1401112002 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Bagong | 16.5332 | 120.5519 | R | 739 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.41 | 7.21 | Tier 2 High GIDA (Score 40.0–49.9) | 64.1 | 44.82 | 64.1 |  | F - Nearest node and line over 5 km | 7.41 | 7.08 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3945
4 | 946 | 3946 | 1907009015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Bakaw-bakaw | 17.2558 | 122.2298 | R | 1420 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 64.1 | 44.81 | 64.1 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3946
4 | 947 | 3947 | 1705320028 | MIMAROPA Region | Palawan | Taytay | Minapla | 10.8347 | 119.2606 | R | 765 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.57 | 26.02 | Tier 2 High GIDA (Score 40.0–49.9) | 64.1 | 44.81 | 64.1 |  | F - Nearest node and line over 5 km | 17.57 | 26.01 | Node: TYW006 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3947
4 | 948 | 3948 | 0403428009 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Macabling | 14.2986 | 121.0975 | U | 22368 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 64.07 | 44.79 | 64.07 |  | B - Node 0.5-1 km | 0.81 | 0.65 | Line: TGY001 TO CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3948
4 | 949 | 3949 | 1380800007 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Sucat | 14.4442 | 121.0421 | U | 57264 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 64.07 | 44.79 | 64.07 |  | C - Line within 0.5 km; node over 1 km | 1.43 | 0.31 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3949
4 | 950 | 3950 | 1907009011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Tumahubong | 17.2558 | 122.2298 | R | 1342 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 64.06 | 44.79 | 64.06 |  | F - Nearest node and line over 5 km | 29.56 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3950
4 | 951 | 3951 | 1381100200 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 200 | 14.5082 | 121.0013 | U | 611 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 64.06 | 44.78 | 64.06 |  | B - Node 0.5-1 km | 0.96 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3951
4 | 952 | 3952 | 0102820004 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Baltazar | 18.1731 | 120.5958 | U | 816 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.52 | 1.48 | Tier 2 High GIDA (Score 40.0–49.9) | 64.05 | 44.78 | 64.05 |  | A - Node within 0.5 km | 0.4 | 0.15 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3952
4 | 953 | 3953 | PH0003953 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 11 | 11.8476 | 124.8738 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.07 | 34.89 | Tier 2 High GIDA (Score 40.0–49.9) | 64.05 | 44.78 | 64.05 |  | F - Nearest node and line over 5 km | 64.14 | 64.09 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3953
4 | 954 | 3954 | 0701243017 | Region VII (Central Visayas) | Bohol | Talibon | Nocnocan | 10.2459 | 124.4049 | R | 1809 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.49 | 40.06 | Tier 2 High GIDA (Score 40.0–49.9) | 64.05 | 44.78 | 64.05 |  | F - Nearest node and line over 5 km | 44.49 | 40.06 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3954
4 | 955 | 3955 | PH0003955 | IV-A | Quezon | Lucena City | Barangay 6 (Pob.) | 13.9347 | 121.6157 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.48 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 64.05 | 44.77 | 64.05 |  | A - Node within 0.5 km | 0.48 | 0.02 | Line: ug to ae | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3955
4 | 956 | 3956 | 0205006018 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Villa Aurora | 16.6307 | 121.4012 | R | 592 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.73 | 2.16 | Tier 2 High GIDA (Score 40.0–49.9) | 64.04 | 44.77 | 64.04 |  | D - Other node or line within 3 km | 4.73 | 2.15 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Route options survey candidate: compare actual node lateral with approved line tap. | 3956
4 | 957 | 3957 | 0405637023 | Region IV-A (CALABARZON) | Quezon | Quezon | Villa Gomez | 14.0782 | 122.132 | R | 434 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.13 | 16.66 | Tier 2 High GIDA (Score 40.0–49.9) | 64.04 | 44.77 | 64.04 |  | F - Nearest node and line over 5 km | 9.13 | 16.66 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3957
4 | 958 | 3958 | PH0003958 | XI | Davao Del Sur | Davao City | Bucana | 7.057 | 125.6107 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.26 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 64.04 | 44.77 | 64.04 |  | D - Other node or line within 3 km | 1.26 | 1.32 | Node: DCD007 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3958
4 | 959 | 3959 | PH0003959 | VI | Iloilo | Iloilo City | San Juan | 10.6849 | 122.5453 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.7 | 3.16 | Tier 2 High GIDA (Score 40.0–49.9) | 64.04 | 44.77 | 64.04 |  | B - Node 0.5-1 km | 0.7 | 3.16 | Node: ICI002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3959
4 | 960 | 3960 | 0806020028 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Libucan Gote | 11.9124 | 124.6299 | R | 407 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 68.43 | 67.32 | Tier 2 High GIDA (Score 40.0–49.9) | 64.01 | 44.75 | 64.01 |  | F - Nearest node and line over 5 km | 68.43 | 67.3 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3960
4 | 961 | 3961 | 1381300131 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Villa Maria Clara | 16.4196 | 121.2758 | U | 2544 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.64 | Tier 2 High GIDA (Score 40.0–49.9) | 64 | 44.75 | 64 |  | F - Nearest node and line over 5 km | 8.17 | 13.9 | Node: QZV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3961
4 | 962 | 3962 | 1907011012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Tandu Banak | 4.7182 | 119.4961 | R | 3003 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 64 | 44.74 | 64 |  | F - Nearest node and line over 5 km | 375.12 | 375.12 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3962
4 | 963 | 3963 | 1004211013 | Region X (Northern Mindanao) | Misamis Occidental | Panaon | San Juan | 8.3552 | 123.8096 | R | 760 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.7 | 27.53 | Tier 2 High GIDA (Score 40.0–49.9) | 64 | 44.74 | 64 |  | F - Nearest node and line over 5 km | 34.74 | 27.2 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3963
4 | 964 | 3964 | 0405811003 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 2 | 14.6808 | 121.137 | U | 12514 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.19 | 0.75 | Tier 2 High GIDA (Score 40.0–49.9) | 63.99 | 44.73 | 63.99 |  | D - Other node or line within 3 km | 2.34 | 0.98 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 3964
4 | 965 | 3965 | PH0003965 | NIR | Negros Occidental | Bacolod City | Barangay 6 (Pob.) | 10.6145 | 122.9425 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.35 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 63.98 | 44.73 | 63.98 |  | D - Other node or line within 3 km | 1.33 | 1.57 | Node: BDN003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3965
4 | 966 | 3966 | PH0003966 | IV-A | Cavite | Cavite City | Barangay 16 | 14.4811 | 120.8929 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.33 | 4.4 | Tier 2 High GIDA (Score 40.0–49.9) | 63.98 | 44.73 | 63.98 |  | B - Node 0.5-1 km | 0.9 | 4.48 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3966
4 | 967 | 3967 | 0403404015 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | San Isidro | 14.2408 | 121.1397 | U | 25567 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.62 | 8.6 | Tier 2 High GIDA (Score 40.0–49.9) | 63.98 | 44.73 | 63.98 |  | D - Other node or line within 3 km | 1.25 | 0.75 | Line: AE SPL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 3967
4 | 968 | 3968 | 1404401006 | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | Lias Kanluran | 17.0839 | 121.1433 | R | 306 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.99 | 10.8 | Tier 2 High GIDA (Score 40.0–49.9) | 63.97 | 44.72 | 63.97 |  | F - Nearest node and line over 5 km | 13.99 | 10.73 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3968
4 | 969 | 3969 | PH0003969 | III | Pampanga | Angeles City | Lourdes North West | 15.1454 | 120.5847 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.04 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 63.97 | 44.72 | 63.97 |  | D - Other node or line within 3 km | 1.04 | 1.01 | Line: ANGELES | Route options survey candidate: compare actual node lateral with approved line tap. | 3969
4 | 970 | 3970 | 1381300006 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bagbag | 14.6909 | 121.0317 | U | 67366 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.4 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 63.97 | 44.72 | 63.97 |  | A - Node within 0.5 km | 0.4 | 0.29 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3970
4 | 971 | 3971 | 0600616003 | Region VI (Western Visayas) | Antique | Sibalom | Valentin Grasparil | 10.7113 | 122.1053 | R | 539 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.14 | 12.78 | Tier 2 High GIDA (Score 40.0–49.9) | 63.96 | 44.72 | 63.96 |  | F - Nearest node and line over 5 km | 19.14 | 12.78 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3971
4 | 972 | 3972 | 0806011009 | Region VIII (Eastern Visayas) | Samar | Matuguinao | Libertad | 12.1498 | 124.8722 | R | 218 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.6 | 96.56 | Tier 2 High GIDA (Score 40.0–49.9) | 63.96 | 44.71 | 63.96 |  | F - Nearest node and line over 5 km | 96.6 | 96.56 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3972
4 | 973 | 3973 | PH0003973 | XI | Davao Del Sur | Davao City | Barangay 11-B (Pob.) | 7.0577 | 125.5678 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.95 | 2.18 | Tier 2 High GIDA (Score 40.0–49.9) | 63.95 | 44.71 | 63.95 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.16 | Line: KITAOTAO - DAVAO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3973
4 | 974 | 3974 | 1408104006 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Dibagat | 18.0784 | 121.1006 | R | 627 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.73 | 19.6 | Tier 2 High GIDA (Score 40.0–49.9) | 63.95 | 44.7 | 63.95 |  | F - Nearest node and line over 5 km | 10.73 | 34.89 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3974
4 | 975 | 3975 | 1705917006 | MIMAROPA Region | Romblon | Santa Maria | San Isidro | 12.398 | 122.0764 | R | 559 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.98 | 31.68 | Tier 2 High GIDA (Score 40.0–49.9) | 63.93 | 44.69 | 63.93 |  | F - Nearest node and line over 5 km | 51.98 | 61.43 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3975
4 | 976 | 3976 | 0600616071 | Region VI (Western Visayas) | Antique | Sibalom | Tig-Ohot | 10.7199 | 122.0422 | R | 544 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.33 | 7.01 | Tier 2 High GIDA (Score 40.0–49.9) | 63.93 | 44.69 | 63.93 |  | F - Nearest node and line over 5 km | 12.33 | 7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3976
4 | 977 | 3977 | PH0003977 | IV-A | Cavite | Imus City | Bayan Luma II | 14.3739 | 120.9663 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.7 | 3.27 | Tier 2 High GIDA (Score 40.0–49.9) | 63.92 | 44.69 | 63.92 |  | D - Other node or line within 3 km | 2.18 | 7.77 | Node: IMC004 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3977
4 | 978 | 3978 | 0402111014 | Region IV-A (CALABARZON) | Cavite | Kawit | Balsahan-Bisita | 14.4418 | 120.9046 | U | 2024 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.52 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 63.92 | 44.69 | 63.92 |  | D - Other node or line within 3 km | 2.7 | 0.54 | Line: KAWIT | Route options survey candidate: compare actual node lateral with approved line tap. | 3978
4 | 979 | 3979 | 0601917027 | Region VI (Western Visayas) | Capiz | Tapaz | Mabini | 11.2665 | 122.5333 | R | 294 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.67 | 3.42 | Tier 2 High GIDA (Score 40.0–49.9) | 63.92 | 44.68 | 63.92 |  | F - Nearest node and line over 5 km | 15.67 | 6.76 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3979
4 | 980 | 3980 | 1381100193 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 193 | 14.5317 | 120.9994 | U | 7641 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.44 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 63.91 | 44.68 | 63.91 |  | A - Node within 0.5 km | 0.49 | 0.26 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 3980
4 | 981 | 3981 | PH0003981 | VII | Cebu | Cebu City | T. Padilla | 10.3432 | 123.9072 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.52 | 4.34 | Tier 2 High GIDA (Score 40.0–49.9) | 63.89 | 44.66 | 63.89 |  | D - Other node or line within 3 km | 1.81 | 1.96 | Node: CCY003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 3981
4 | 982 | 3982 | 0804815010 | Region VIII (Eastern Visayas) | Northern Samar | Pambujan | Ge-adgawan | 12.4247 | 124.9266 | R | 807 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 92.43 | 91.69 | Tier 2 High GIDA (Score 40.0–49.9) | 63.89 | 44.66 | 63.89 |  | F - Nearest node and line over 5 km | 92.43 | 91.61 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3982
4 | 983 | 3983 | 1381600031 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Viente Reales | 14.709 | 120.9654 | U | 24747 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.6 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 63.89 | 44.66 | 63.89 |  | B - Node 0.5-1 km | 0.6 | 0.24 | Line: Existing MTF | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3983
4 | 984 | 3984 | 1908804006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Tugal | 17.2552 | 122.2292 | R | 4470 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 63.89 | 44.66 | 63.89 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3984
4 | 985 | 3985 | 0200905003 | Region II (Cagayan Valley) | Batanes | Sabtang | Nakanmuan | 20.3252 | 121.8388 | R | 135 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 206.37 | 203.19 | Tier 2 High GIDA (Score 40.0–49.9) | 63.88 | 44.66 | 63.88 |  | F - Nearest node and line over 5 km | 206.37 | 203.18 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3985
4 | 986 | 3986 | 1903604041 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Samporna | 17.2547 | 122.2288 | R | 633 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.88 | 44.66 | 63.88 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3986
4 | 987 | 3987 | PH0003987 | IV-A | Laguna | San Pablo City | Barangay III-E (Pob.) | 17.5012 | 121.8315 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.13 | 2.05 | Tier 2 High GIDA (Score 40.0–49.9) | 63.87 | 44.65 | 63.87 |  | D - Other node or line within 3 km | 8.5 | 2.94 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Route options survey candidate: compare actual node lateral with approved line tap. | 3987
4 | 988 | 3988 | 1907009009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Languyan | Simalak | 5.2456 | 119.9621 | R | 1825 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 63.87 | 44.65 | 63.87 |  | F - Nearest node and line over 5 km | 297.95 | 297.95 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3988
4 | 989 | 3989 | 0600606034 | Region VI (Western Visayas) | Antique | Culasi | Salde | 11.4558 | 122.0753 | R | 143 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.37 | 38.34 | Tier 2 High GIDA (Score 40.0–49.9) | 63.87 | 44.65 | 63.87 |  | F - Nearest node and line over 5 km | 30.46 | 33.7 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3989
4 | 990 | 3990 | 0403428011 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Malusak | 14.3142 | 121.1126 | U | 3185 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.02 | 1.36 | Tier 2 High GIDA (Score 40.0–49.9) | 63.87 | 44.65 | 63.87 |  | D - Other node or line within 3 km | 1.02 | 1.31 | Node: SRL004 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 3990
4 | 991 | 3991 | 1908710029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Panatan | 17.2546 | 122.2279 | R | 2317 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 63.84 | 44.63 | 63.84 |  | F - Nearest node and line over 5 km | 29.31 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3991
4 | 992 | 3992 | 1705309023 | MIMAROPA Region | Palawan | Coron | San Nicolas | 12.0798 | 120.1931 | R | 3804 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.64 | 99.08 | Tier 2 High GIDA (Score 40.0–49.9) | 63.84 | 44.63 | 63.84 |  | F - Nearest node and line over 5 km | 6.64 | 99.08 | Node: CNW002-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3992
4 | 993 | 3993 | 1381100199 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 199 | 14.5094 | 121.0019 | U | 2102 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.85 | 15.84 | Tier 2 High GIDA (Score 40.0–49.9) | 63.84 | 44.63 | 63.84 |  | B - Node 0.5-1 km | 0.85 | 0.02 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3993
4 | 994 | 3994 | 1907011013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Taungoh | 4.7063 | 119.492 | R | 3655 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 63.82 | 44.62 | 63.82 |  | F - Nearest node and line over 5 km | 376.33 | 376.32 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 3994
4 | 995 | 3995 | PH0003995 | VIII | Leyte | Tacloban City | Barangay 57 | 11.2489 | 124.9641 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.67 | 1.94 | Tier 2 High GIDA (Score 40.0–49.9) | 63.82 | 44.62 | 63.82 |  | E - Nearest node or line 3-5 km | 4.3 | 6.37 | Node: TCL002 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 3995
4 | 996 | 3996 | PH0003996 | I | Ilocos Norte | Laoag City | Bgy. No. 5, San Pedro (Pob.) | 18.2037 | 120.5927 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.07 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 63.82 | 44.62 | 63.82 |  | B - Node 0.5-1 km | 0.81 | 0.03 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 3996
4 | 997 | 3997 | PH0003997 | IV-A | Laguna | San Pablo City | Barangay V-A (Pob.) | 17.4461 | 121.7983 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 63.82 | 44.62 | 63.82 |  | C - Line within 0.5 km; node over 1 km | 3.22 | 0.21 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3997
4 | 998 | 3998 | 0403403006 | Region IV-A (CALABARZON) | Laguna | City of Biñan | De La Paz | 14.3482 | 121.085 | U | 35999 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.46 | 1.02 | Tier 2 High GIDA (Score 40.0–49.9) | 63.81 | 44.61 | 63.81 |  | D - Other node or line within 3 km | 1.46 | 1.02 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 3998
4 | 999 | 3999 | 0403405020 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lecheria | 14.2033 | 121.1614 | U | 11956 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.78 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 63.81 | 44.61 | 63.81 |  | C - Line within 0.5 km; node over 1 km | 1.78 | 0.2 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 3999
4 | 1000 | 4000 | 1102501003 | Region XI (Davao Region) | Davao Oriental | Baganga | Batawan | 7.4784 | 126.5426 | R | 734 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.17 | 64.5 | Tier 2 High GIDA (Score 40.0–49.9) | 63.8 | 44.6 | 63.8 |  | F - Nearest node and line over 5 km | 66.17 | 64.49 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4000

## Batch 5 (4,001 - 5,000)
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA — Batch 5 (4,001 - 5,000)
31-Column Audited Fiber Siting Master Roster ¦ 8T8R MIMO 1,000 Subs/BTS ¦ Zero Duplicate Coordinates
Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Avg HH Size | Households | Subs @ 30% | Carrier Spectrum | Peak Demand (BTS) | Day 1 BTS | Dist to Node (km) | Dist to Line (km) | Deploy Tier | Ease Score (35%) | Viability Score (35%) | Necessity Score (30%) | Composite Score | Screening Class | Screened Node (km) | Screened Line (km) | Nearest Audited Asset | Field Action / Recommendation | Fiber Survey Priority
5 | 1 | 4001 | PH0004001 | NCR | Metro Manila | Taguig City | Post Proper Northside | 14.6341 | 120.9805 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 63.78 | 44.59 | 63.78 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4001
5 | 2 | 4002 | 0405646035 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Roque | 13.9818 | 122.4331 | R | 305 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.13 | 5.11 | Tier 2 High GIDA (Score 40.0–49.9) | 63.78 | 44.59 | 63.78 |  | F - Nearest node and line over 5 km | 5.13 | 5.1 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4002
5 | 3 | 4003 | 1003503004 | Region X (Northern Mindanao) | Lanao del Norte | Baroy | Bato | 8.007 | 123.7807 | R | 419 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.26 | 4.02 | Tier 2 High GIDA (Score 40.0–49.9) | 63.78 | 44.59 | 63.78 |  | C - Line within 0.5 km; node over 1 km | 4.49 | 0.08 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4003
5 | 4 | 4004 | 0405802018 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Muntingdilaw | 14.5974 | 121.1262 | U | 12938 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 1.53 | Tier 2 High GIDA (Score 40.0–49.9) | 63.77 | 44.58 | 63.77 |  | D - Other node or line within 3 km | 1.57 | 1.53 | Line: PSG001 TO TAYTAY | Route options survey candidate: compare actual node lateral with approved line tap. | 4004
5 | 5 | 4005 | 1903609052 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Ganassi | Pantaon | 17.2547 | 122.2287 | R | 850 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.76 | 44.58 | 63.76 |  | F - Nearest node and line over 5 km | 29.39 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4005
5 | 6 | 4006 | PH0004006 | IV-A | Cavite | Cavite City | Barangay 9 | 14.4873 | 120.8961 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.55 | 5.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.75 | 44.57 | 63.75 |  | D - Other node or line within 3 km | 1.66 | 4.92 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4006
5 | 7 | 4007 | PH0004007 | NCR | Metro Manila | Caloocan City | Barangay 173 | 14.7541 | 121.0326 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.57 | 36.85 | Tier 2 High GIDA (Score 40.0–49.9) | 63.75 | 44.57 | 63.75 |  | D - Other node or line within 3 km | 1.3 | 0.72 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4007
5 | 8 | 4008 | 1381300014 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Bayanihan | 14.6926 | 121.042 | U | 639 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.16 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 63.75 | 44.57 | 63.75 |  | D - Other node or line within 3 km | 1.21 | 1.1 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 4008
5 | 9 | 4009 | 0504103011 | Region V (Bicol Region) | Masbate | Balud | Jangan | 12.0162 | 123.2738 | R | 866 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.02 | 8.58 | Tier 2 High GIDA (Score 40.0–49.9) | 63.74 | 44.56 | 63.74 |  | F - Nearest node and line over 5 km | 7.02 | 34.02 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4009
5 | 10 | 4010 | 0702234019 | Region VII (Central Visayas) | Cebu | City of Naga | North Poblacion | 7.8427 | 122.6777 | R | 3151 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.78 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 63.74 | 44.56 | 63.74 |  | E - Nearest node or line 3-5 km | 12.5 | 3.63 | Line: BUUG - IPIL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4010
5 | 11 | 4011 | 1903639006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Kabaniakawan | 7.9185 | 123.7724 | R | 705 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.51 | Tier 2 High GIDA (Score 40.0–49.9) | 63.73 | 44.55 | 63.73 |  | C - Line within 0.5 km; node over 1 km | 14.15 | 0.03 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4011
5 | 12 | 4012 | PH0004012 | VIII | Leyte | Tacloban City | Barangay 51 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.97 | 13.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.72 | 44.55 | 63.72 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4012
5 | 13 | 4013 | 0702252011 | Region VII (Central Visayas) | Cebu | Tuburan | Kamansi | 10.6453 | 123.9013 | R | 578 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.45 | 10.91 | Tier 2 High GIDA (Score 40.0–49.9) | 63.72 | 44.55 | 63.72 |  | F - Nearest node and line over 5 km | 13.45 | 10.9 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4013
5 | 14 | 4014 | PH0004014 | VIII | Leyte | Tacloban City | Barangay 36 | 11.2169 | 125.0033 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.1 | 7.32 | Tier 2 High GIDA (Score 40.0–49.9) | 63.72 | 44.54 | 63.72 |  | B - Node 0.5-1 km | 0.83 | 0.81 | Line: CAPOOCAN - TACLOBAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4014
5 | 15 | 4015 | 1908702015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Rumidas | 17.2539 | 122.2279 | R | 4409 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 63.71 | 44.54 | 63.71 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4015
5 | 16 | 4016 | PH0004016 | VII | Cebu | Cebu City | San Antonio (Pob.) | 10.322 | 123.8844 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.44 | 4.24 | Tier 2 High GIDA (Score 40.0–49.9) | 63.7 | 44.54 | 63.7 |  | D - Other node or line within 3 km | 1.67 | 1.51 | Line: 96c | Route options survey candidate: compare actual node lateral with approved line tap. | 4016
5 | 17 | 4017 | 1705307010 | MIMAROPA Region | Palawan | Busuanga | Quezon | 12.2663 | 119.9357 | R | 1189 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.98 | 122.41 | Tier 2 High GIDA (Score 40.0–49.9) | 63.67 | 44.51 | 63.67 |  | F - Nearest node and line over 5 km | 14.98 | 122.4 | Node: BSW001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4017
5 | 18 | 4018 | 1606803016 | Region XIII (Caraga) | Surigao del Sur | City of Bislig | San Jose | 8.1454 | 126.333 | R | 4834 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.74 | 31.66 | Tier 2 High GIDA (Score 40.0–49.9) | 63.65 | 44.5 | 63.65 |  | F - Nearest node and line over 5 km | 31.74 | 31.65 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4018
5 | 19 | 4019 | 0402116003 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo I | 14.4285 | 120.8763 | R | 1999 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.73 | 0.7 | Tier 2 High GIDA (Score 40.0–49.9) | 63.65 | 44.5 | 63.65 |  | B - Node 0.5-1 km | 0.73 | 0.7 | Line: NOVELETA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4019
5 | 20 | 4020 | 0301412012 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Libtong | 14.7442 | 120.9804 | U | 13319 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 1.05 | Tier 2 High GIDA (Score 40.0–49.9) | 63.65 | 44.5 | 63.65 |  | D - Other node or line within 3 km | 1.45 | 1.05 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4020
5 | 21 | 4021 | PH0004021 | VII | Cebu | Cebu City | Quiot Pardo | 10.2881 | 123.8563 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.62 | Tier 2 High GIDA (Score 40.0–49.9) | 63.65 | 44.5 | 63.65 |  | B - Node 0.5-1 km | 0.56 | 0.54 | Line: CEBU - TOLEDO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4021
5 | 22 | 4022 | 1907005001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | South Larap | 17.2558 | 122.2299 | R | 2177 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 63.64 | 44.49 | 63.64 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4022
5 | 23 | 4023 | 1381300113 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sikatuna Village | 15.6 | 120.8197 | U | 6378 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.52 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 63.64 | 44.49 | 63.64 |  | E - Nearest node or line 3-5 km | 4.7 | 3.1 | Line: 38,161m. | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4023
5 | 24 | 4024 | 1004318002 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Balintad | 8.3699 | 124.3784 | R | 631 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.42 | 10.01 | Tier 2 High GIDA (Score 40.0–49.9) | 63.63 | 44.48 | 63.63 |  | F - Nearest node and line over 5 km | 10.42 | 9.98 | Line: CDO - ILIGAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4024
5 | 25 | 4025 | 0806007006 | Region VIII (Eastern Visayas) | Samar | Gandara | Beslig | 12.1196 | 124.7676 | R | 161 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 90.81 | 90.8 | Tier 2 High GIDA (Score 40.0–49.9) | 63.63 | 44.48 | 63.63 |  | F - Nearest node and line over 5 km | 90.81 | 90.77 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4025
5 | 26 | 4026 | PH0004026 | VII | Cebu | Talisay City | Lawaan II | 10.2661 | 123.8339 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.31 | 10.11 | Tier 2 High GIDA (Score 40.0–49.9) | 63.62 | 44.47 | 63.62 |  | B - Node 0.5-1 km | 0.87 | 0.56 | Line: CEBU - TOLEDO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4026
5 | 27 | 4027 | PH0004027 | IV-A | Cavite | Imus City | Medicion I-A | 14.3894 | 120.9608 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.68 | 1.44 | Tier 2 High GIDA (Score 40.0–49.9) | 63.61 | 44.47 | 63.61 |  | B - Node 0.5-1 km | 0.61 | 6.27 | Node: IMC004 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4027
5 | 28 | 4028 | 1908810001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Bulayan | 17.2558 | 122.2293 | R | 776 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 96.68 | 95.35 | Tier 2 High GIDA (Score 40.0–49.9) | 63.6 | 44.47 | 63.6 |  | F - Nearest node and line over 5 km | 29.52 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4028
5 | 29 | 4029 | PH0004029 | NCR | Metro Manila | Caloocan City | Barangay 171 | 14.7482 | 121.0227 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.11 | 5.48 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | B - Node 0.5-1 km | 0.82 | 0.16 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4029
5 | 30 | 4030 | PH0004030 | IV-A | Cavite | Cavite City | Barangay 55 | 14.4739 | 120.8868 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2 | 2.38 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | A - Node within 0.5 km | 0.13 | 4.29 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4030
5 | 31 | 4031 | 0401003012 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 7 | 13.9829 | 120.7564 | R | 340 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | E - Nearest node or line 3-5 km | 5.26 | 3.18 | Line: TUY - STA. TERESITA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4031
5 | 32 | 4032 | 1400112001 | Cordillera Administrative Region (CAR) | Abra | Langiden | Baac | 17.6011 | 120.5764 | R | 362 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.63 | 4.23 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | E - Nearest node or line 3-5 km | 4.63 | 4.12 | Line: CABLE LAYED | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4032
5 | 33 | 4033 | 0806023020 | Region VIII (Eastern Visayas) | Samar | Zumarraga | San Isidro | 11.6848 | 124.8285 | R | 1432 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.42 | 45.36 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | F - Nearest node and line over 5 km | 45.42 | 45.36 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4033
5 | 34 | 4034 | 0201529009 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 7 | 17.6309 | 121.7224 | U | 320 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.11 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 63.58 | 44.45 | 63.58 |  | C - Line within 0.5 km; node over 1 km | 3.48 | 0.44 | Line: TUGEGARAO FOC | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4034
5 | 35 | 4035 | PH0004035 | CAR | Benguet | Baguio City | Lourdes Subdivision, Proper | 16.3901 | 120.5941 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.46 | 7.82 | Tier 2 High GIDA (Score 40.0–49.9) | 63.57 | 44.44 | 63.57 |  | D - Other node or line within 3 km | 1.37 | 1.21 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 4035
5 | 36 | 4036 | 1903601020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Pindolonan | 17.255 | 122.2296 | R | 571 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.57 | 44.44 | 63.57 |  | F - Nearest node and line over 5 km | 29.48 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4036
5 | 37 | 4037 | 1381300057 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Malaya | 14.6347 | 121.0569 | U | 2714 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 63.56 | 44.44 | 63.56 |  | C - Line within 0.5 km; node over 1 km | 1.2 | 0.19 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4037
5 | 38 | 4038 | 1907010003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Tonggusong Banaran | 17.2558 | 122.2299 | U | 6606 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 63.56 | 44.44 | 63.56 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4038
5 | 39 | 4039 | PH0004039 | IV-A | Cavite | Cavite City | Barangay 45-A | 14.4827 | 120.911 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 5.76 | Tier 2 High GIDA (Score 40.0–49.9) | 63.56 | 44.44 | 63.56 |  | D - Other node or line within 3 km | 2.67 | 3.87 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4039
5 | 40 | 4040 | PH0004040 | IV-A | Cavite | Cavite City | Barangay 14 | 14.4934 | 120.9051 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.17 | 4.03 | Tier 2 High GIDA (Score 40.0–49.9) | 63.56 | 44.43 | 63.56 |  | D - Other node or line within 3 km | 2.81 | 5.2 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4040
5 | 41 | 4041 | 1400126008 | Cordillera Administrative Region (CAR) | Abra | Tubo | Tubtuba | 17.1677 | 120.7446 | R | 424 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.8 | 7.7 | Tier 2 High GIDA (Score 40.0–49.9) | 63.55 | 44.43 | 63.55 |  | F - Nearest node and line over 5 km | 7.8 | 7.66 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4041
5 | 42 | 4042 | 1108603001 | Region XI (Davao Region) | Davao Occidental | Malita | Bito | 6.3372 | 125.5957 | R | 2033 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.06 | 32.04 | Tier 2 High GIDA (Score 40.0–49.9) | 63.55 | 44.43 | 63.55 |  | F - Nearest node and line over 5 km | 34.06 | 32.04 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4042
5 | 43 | 4043 | 0300803012 | Region III (Central Luzon) | Bataan | City of Balanga | Malabia | 14.6642 | 120.4681 | R | 757 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.67 | 1.72 | Tier 2 High GIDA (Score 40.0–49.9) | 63.52 | 44.41 | 63.52 |  | E - Nearest node or line 3-5 km | 7.95 | 3.57 | Line: Bagac-Pilar AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4043
5 | 44 | 4044 | PH0004044 | VI | Capiz | Roxas City | Poblacion I | 10.3963 | 119.2636 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.43 | 0.58 | Tier 2 High GIDA (Score 40.0–49.9) | 63.52 | 44.41 | 63.52 |  | F - Nearest node and line over 5 km | 12.43 | 9.42 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4044
5 | 45 | 4045 | 0702252027 | Region VII (Central Visayas) | Cebu | Tuburan | Kaorasan | 10.6208 | 123.912 | R | 237 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.69 | 12.04 | Tier 2 High GIDA (Score 40.0–49.9) | 63.51 | 44.4 | 63.51 |  | F - Nearest node and line over 5 km | 12.69 | 12.04 | Line: BOGO - DANAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4045
5 | 46 | 4046 | 0401019049 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 1 | 14.0828 | 120.667 | R | 1440 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.29 | 1.97 | Tier 2 High GIDA (Score 40.0–49.9) | 63.51 | 44.4 | 63.51 |  | D - Other node or line within 3 km | 3.8 | 0.73 | Line: NCC001 TO NSB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4046
5 | 47 | 4047 | 1381300035 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | E. Rodriguez | 14.6225 | 121.051 | U | 18092 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.77 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 63.51 | 44.4 | 63.51 |  | B - Node 0.5-1 km | 0.77 | 0.05 | Line: UG 144C via R-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4047
5 | 48 | 4048 | 1906613032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Lower Sinumaan | 17.2546 | 122.2289 | R | 2367 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.62 | Tier 2 High GIDA (Score 40.0–49.9) | 63.5 | 44.4 | 63.5 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4048
5 | 49 | 4049 | 1403206009 | Cordillera Administrative Region (CAR) | Kalinga | Lubuagan | Uma del Norte | 17.3495 | 121.1343 | R | 1145 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.65 | 3.49 | Tier 2 High GIDA (Score 40.0–49.9) | 63.5 | 44.39 | 63.5 |  | E - Nearest node or line 3-5 km | 9.65 | 3.45 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4049
5 | 50 | 4050 | PH0004050 | XIII | Agusan Del Norte | Butuan City | Lapu-lapu Pob. | 8.8852 | 125.5654 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.72 | 8.45 | Tier 2 High GIDA (Score 40.0–49.9) | 63.5 | 44.39 | 63.5 |  | D - Other node or line within 3 km | 7.89 | 2.28 | Line: FOC 96C | Route options survey candidate: compare actual node lateral with approved line tap. | 4050
5 | 51 | 4051 | 0401003045 | Region IV-A (CALABARZON) | Batangas | Balayan | San Juan | 13.9377 | 120.7321 | R | 2013 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.7 | 0.51 | Tier 2 High GIDA (Score 40.0–49.9) | 63.5 | 44.39 | 63.5 |  | B - Node 0.5-1 km | 0.78 | 0.15 | Line: Untitled Path | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4051
5 | 52 | 4052 | 0405627002 | Region IV-A (CALABARZON) | Quezon | Mauban | Alitap | 14.1337 | 121.7506 | R | 520 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6 | 14.54 | Tier 2 High GIDA (Score 40.0–49.9) | 63.49 | 44.38 | 63.49 |  | F - Nearest node and line over 5 km | 6 | 14.45 | Node: MBQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4052
5 | 53 | 4053 | 0200905005 | Region II (Cagayan Valley) | Batanes | Sabtang | Sinakan | 20.3339 | 121.8733 | R | 566 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 208.42 | 205.38 | Tier 2 High GIDA (Score 40.0–49.9) | 63.49 | 44.38 | 63.49 |  | F - Nearest node and line over 5 km | 208.42 | 205.38 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4053
5 | 54 | 4054 | 0601912006 | Region VI (Western Visayas) | Capiz | Pontevedra | Bantigue | 10.3576 | 122.9619 | R | 515 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.66 | 2.45 | Tier 2 High GIDA (Score 40.0–49.9) | 63.48 | 44.38 | 63.48 |  | F - Nearest node and line over 5 km | 7.6 | 10.08 | Node: LCL001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4054
5 | 55 | 4055 | 0601912001 | Region VI (Western Visayas) | Capiz | Pontevedra | Agbanog | 11.4717 | 122.8633 | R | 963 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.28 | 3.05 | Tier 2 High GIDA (Score 40.0–49.9) | 63.48 | 44.38 | 63.48 |  | E - Nearest node or line 3-5 km | 3.28 | 3.05 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4055
5 | 56 | 4056 | 0205010024 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Balete | 16.5503 | 120.9446 | R | 1143 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.13 | 15.75 | Tier 2 High GIDA (Score 40.0–49.9) | 63.47 | 44.38 | 63.47 |  | F - Nearest node and line over 5 km | 14.13 | 15.74 | Node: KYB001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4056
5 | 57 | 4057 | 0402106071 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz II | 14.3589 | 120.9252 | R | 4500 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.42 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 63.47 | 44.37 | 63.47 |  | D - Other node or line within 3 km | 1.82 | 7.01 | Node: DMC006 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4057
5 | 58 | 4058 | 1381300114 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Silangan | 7.7911 | 125.1434 | U | 5034 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 1.02 | Tier 2 High GIDA (Score 40.0–49.9) | 63.45 | 44.36 | 63.45 |  | F - Nearest node and line over 5 km | 8.21 | 6.98 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4058
5 | 59 | 4059 | 1906611019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Panglayahan | 17.2552 | 122.2287 | R | 764 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.21 | 32.82 | Tier 2 High GIDA (Score 40.0–49.9) | 63.44 | 44.35 | 63.44 |  | F - Nearest node and line over 5 km | 29.43 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4059
5 | 60 | 4060 | 0307702005 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 5 | 16.3091 | 122.0957 | R | 324 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.6 | 2.32 | Tier 2 High GIDA (Score 40.0–49.9) | 63.42 | 44.34 | 63.42 |  | E - Nearest node or line 3-5 km | 4.58 | 37.97 | Node: CSA001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4060
5 | 61 | 4061 | 1208004015 | Region XII (SOCCSKSARGEN) | Sarangani | Maasim | Seven Hills | 5.8715 | 125.0299 | R | 515 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.42 | 30.31 | Tier 2 High GIDA (Score 40.0–49.9) | 63.42 | 44.33 | 63.42 |  | F - Nearest node and line over 5 km | 25.42 | 30.31 | Node: GSS003 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4061
5 | 62 | 4062 | 0307702004 | Region III (Central Luzon) | Aurora | Casiguran | Barangay 4 | 16.3072 | 122.1457 | R | 232 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.26 | 2.48 | Tier 2 High GIDA (Score 40.0–49.9) | 63.4 | 44.32 | 63.4 |  | E - Nearest node or line 3-5 km | 3.86 | 42.89 | Node: CSA001 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4062
5 | 63 | 4063 | 1903601026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Tambo | 17.2556 | 122.2295 | R | 922 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 63.39 | 44.31 | 63.39 |  | F - Nearest node and line over 5 km | 29.52 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4063
5 | 64 | 4064 | 1705320016 | MIMAROPA Region | Palawan | Taytay | Old Guinlo | 10.7993 | 119.4363 | R | 1229 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.2 | 6.78 | Tier 2 High GIDA (Score 40.0–49.9) | 63.39 | 44.31 | 63.39 |  | F - Nearest node and line over 5 km | 8.2 | 6.71 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4064
5 | 65 | 4065 | 1400113007 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Mogao | 17.9246 | 121.2156 | R | 261 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.05 | 28.02 | Tier 2 High GIDA (Score 40.0–49.9) | 63.38 | 44.31 | 63.38 |  | F - Nearest node and line over 5 km | 11.17 | 18.23 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4065
5 | 66 | 4066 | PH0004066 | CAR | Benguet | Baguio City | Holy Ghost Proper | 16.4211 | 120.6047 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.78 | 3.57 | Tier 2 High GIDA (Score 40.0–49.9) | 63.38 | 44.31 | 63.38 |  | D - Other node or line within 3 km | 1.07 | 1.21 | Node: BGC003 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4066
5 | 67 | 4067 | 1381200005 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Caniogan | 14.5718 | 121.0785 | U | 29831 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 63.37 | 44.3 | 63.37 |  | B - Node 0.5-1 km | 0.81 | 0.41 | Line: Aerial 216C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4067
5 | 68 | 4068 | PH0004068 | IV-B | Palawan | Puerto Princesa City | Masipag (Pob.) | 9.8387 | 118.5761 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.14 | 5.76 | Tier 2 High GIDA (Score 40.0–49.9) | 63.37 | 44.3 | 63.37 |  | F - Nearest node and line over 5 km | 17.48 | 15.91 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4068
5 | 69 | 4069 | 1908810007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Unsay | Panangeti | 17.2547 | 122.2295 | R | 1076 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 95.66 | 94.31 | Tier 2 High GIDA (Score 40.0–49.9) | 63.37 | 44.3 | 63.37 |  | F - Nearest node and line over 5 km | 29.45 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4069
5 | 70 | 4070 | PH0004070 | I | Ilocos Norte | Laoag City | Bgy. No. 6, San Agustin (Pob.) | 18.1577 | 120.546 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.68 | 3.64 | Tier 2 High GIDA (Score 40.0–49.9) | 63.37 | 44.3 | 63.37 |  | E - Nearest node or line 3-5 km | 5.2 | 4.1 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4070
5 | 71 | 4071 | PH0004071 | XI | Davao Del Sur | Davao City | Barangay 13-B (Pob.) | 7.0662 | 125.5981 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.14 | 0.64 | Tier 2 High GIDA (Score 40.0–49.9) | 63.36 | 44.29 | 63.36 |  | C - Line within 0.5 km; node over 1 km | 1.38 | 0.33 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4071
5 | 72 | 4072 | 0200905001 | Region II (Cagayan Valley) | Batanes | Sabtang | Chavayan | 20.2839 | 121.8704 | R | 162 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 203.07 | 200.1 | Tier 2 High GIDA (Score 40.0–49.9) | 63.35 | 44.29 | 63.35 |  | F - Nearest node and line over 5 km | 203.07 | 200.1 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4072
5 | 73 | 4073 | PH0004073 | NCR | Metro Manila | Taguig City | Lower Bicutan | 14.4992 | 121.0605 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 63.35 | 44.29 | 63.35 |  | B - Node 0.5-1 km | 0.87 | 0.29 | Line: Aerial 216C MTF | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4073
5 | 74 | 4074 | 1907003008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Mapun | Sikub | 17.2563 | 122.2296 | R | 1690 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 34.42 | Tier 2 High GIDA (Score 40.0–49.9) | 63.34 | 44.28 | 63.34 |  | F - Nearest node and line over 5 km | 29.58 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4074
5 | 75 | 4075 | 0402106075 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas II | 14.3726 | 120.9766 | R | 4817 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.4 | 5.09 | Tier 2 High GIDA (Score 40.0–49.9) | 63.34 | 44.28 | 63.34 |  | D - Other node or line within 3 km | 2.52 | 7.21 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4075
5 | 76 | 4076 | 1903639003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Bongabong | 17.2546 | 122.2286 | R | 1520 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.26 | Tier 2 High GIDA (Score 40.0–49.9) | 63.33 | 44.28 | 63.33 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4076
5 | 77 | 4077 | PH0004077 | VII | Cebu | Cebu City | Pari-an | 10.2903 | 123.8742 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 2.76 | Tier 2 High GIDA (Score 40.0–49.9) | 63.32 | 44.27 | 63.32 |  | C - Line within 0.5 km; node over 1 km | 1.63 | 0.01 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4077
5 | 78 | 4078 | 0600601010 | Region VI (Western Visayas) | Antique | Anini-Y | Igtumarom | 10.4541 | 121.9583 | R | 470 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.35 | 15.37 | Tier 2 High GIDA (Score 40.0–49.9) | 63.32 | 44.27 | 63.32 |  | F - Nearest node and line over 5 km | 34.35 | 15.32 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4078
5 | 79 | 4079 | PH0004079 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 10 | 11.7976 | 124.9177 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.75 | 32.14 | Tier 2 High GIDA (Score 40.0–49.9) | 63.3 | 44.25 | 63.3 |  | F - Nearest node and line over 5 km | 60.69 | 60.61 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4079
5 | 80 | 4080 | 1380700014 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Industrial Valley | 14.6216 | 121.0804 | U | 17012 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 1.31 | Tier 2 High GIDA (Score 40.0–49.9) | 63.26 | 44.23 | 63.26 |  | D - Other node or line within 3 km | 1.32 | 0.96 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 4080
5 | 81 | 4081 | 0403428012 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Market Area | 14.3151 | 121.1114 | U | 17557 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.18 | 1.25 | Tier 2 High GIDA (Score 40.0–49.9) | 63.26 | 44.22 | 63.26 |  | D - Other node or line within 3 km | 1.18 | 1.22 | Node: SRL004 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 4081
5 | 82 | 4082 | 0403403012 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Malaban | 14.3461 | 121.0888 | U | 39450 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.63 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 63.26 | 44.22 | 63.26 |  | D - Other node or line within 3 km | 1.63 | 0.85 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 4082
5 | 83 | 4083 | PH0004083 | CAR | Benguet | Baguio City | Camp 8 | 16.425 | 120.6047 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 1.54 | Tier 2 High GIDA (Score 40.0–49.9) | 63.25 | 44.22 | 63.25 |  | D - Other node or line within 3 km | 1.17 | 1.43 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4083
5 | 84 | 4084 | 0403405041 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 4 | 14.1847 | 121.1303 | R | 3618 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.92 | 0.86 | Tier 2 High GIDA (Score 40.0–49.9) | 63.25 | 44.22 | 63.25 |  | C - Line within 0.5 km; node over 1 km | 2.21 | 0.28 | Line: Untitled Path | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4084
5 | 85 | 4085 | 0701247027 | Region VII (Central Visayas) | Bohol | Valencia | Pangi-an | 9.6561 | 124.2581 | R | 404 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.45 | 17.39 | Tier 2 High GIDA (Score 40.0–49.9) | 63.25 | 44.22 | 63.25 |  | F - Nearest node and line over 5 km | 38 | 17.35 | Line: CARMEN TO TAGBILARAN VIA LOBOC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4085
5 | 86 | 4086 | PH0004086 | I | Pangasinan | Dagupan City | Pogo Grande | 16.0337 | 120.3383 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.66 | 0.73 | Tier 2 High GIDA (Score 40.0–49.9) | 63.24 | 44.21 | 63.24 |  | D - Other node or line within 3 km | 1.66 | 0.71 | Line: DAGUPAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4086
5 | 87 | 4087 | 0604528038 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12 | 10.7394 | 122.9686 | R | 2653 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 63.24 | 44.21 | 63.24 |  | A - Node within 0.5 km | 0.17 | 0.11 | Line: TALISAY CITY - KABANGKALAN | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4087
5 | 88 | 4088 | 1906601028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Indanan | Panglima Misuari | 17.2553 | 122.2293 | R | 1833 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.48 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 63.24 | 44.21 | 63.24 |  | F - Nearest node and line over 5 km | 29.48 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4088
5 | 89 | 4089 | 1380700010 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Santo Niño | 14.639 | 121.0958 | U | 29815 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 63.24 | 44.21 | 63.24 |  | A - Node within 0.5 km | 0.28 | 0.17 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4089
5 | 90 | 4090 | 1380400017 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Santolan | 14.6854 | 120.9589 | U | 13794 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.4 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 63.23 | 44.21 | 63.23 |  | A - Node within 0.5 km | 0.4 | 0.18 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4090
5 | 91 | 4091 | 1380700008 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | San Roque | 14.6228 | 121.0971 | U | 17516 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 63.23 | 44.21 | 63.23 |  | C - Line within 0.5 km; node over 1 km | 1.62 | 0.14 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4091
5 | 92 | 4092 | 1907005016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Datu Baguinda Putih | 17.2558 | 122.2299 | R | 3403 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 63.23 | 44.2 | 63.23 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4092
5 | 93 | 4093 | 0201505032 | Region II (Cagayan Valley) | Cagayan | Aparri | Navagan | 18.3554 | 121.5705 | R | 1184 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.62 | 4.97 | Tier 2 High GIDA (Score 40.0–49.9) | 63.23 | 44.2 | 63.23 |  | E - Nearest node or line 3-5 km | 6.62 | 4.93 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4093
5 | 94 | 4094 | PH0004094 | IV-A | Cavite | Cavite City | Barangay 24 | 14.4761 | 120.893 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.39 | 3.44 | Tier 2 High GIDA (Score 40.0–49.9) | 63.22 | 44.2 | 63.22 |  | B - Node 0.5-1 km | 0.61 | 4.03 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4094
5 | 95 | 4095 | 1400113005 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Lenneng | 17.571 | 120.8991 | R | 327 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.35 | 20.33 | Tier 2 High GIDA (Score 40.0–49.9) | 63.22 | 44.2 | 63.22 |  | F - Nearest node and line over 5 km | 26.63 | 26.57 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4095
5 | 96 | 4096 | 0806415010 | Region VIII (Eastern Visayas) | Southern Leyte | San Ricardo | San Ramon | 10.0433 | 125.2432 | R | 423 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.5 | 23.72 | Tier 2 High GIDA (Score 40.0–49.9) | 63.22 | 44.2 | 63.22 |  | F - Nearest node and line over 5 km | 39.57 | 38.57 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4096
5 | 97 | 4097 | 1403213020 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Lucog | 17.3991 | 121.2994 | R | 1575 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.26 | 0.63 | Tier 2 High GIDA (Score 40.0–49.9) | 63.22 | 44.19 | 63.22 |  | D - Other node or line within 3 km | 15.26 | 0.58 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 4097
5 | 98 | 4098 | 1003515019 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Petadun | 7.7875 | 123.91 | R | 1244 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.91 | 19.71 | Tier 2 High GIDA (Score 40.0–49.9) | 63.21 | 44.19 | 63.21 |  | F - Nearest node and line over 5 km | 30.91 | 19.68 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4098
5 | 99 | 4099 | PH0004099 | XIII | Surigao Del Norte | Surigao City | Bilabid | 9.7561 | 125.6333 | R | 2328 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.59 | 7.84 | Tier 2 High GIDA (Score 40.0–49.9) | 63.21 | 44.19 | 63.21 |  | F - Nearest node and line over 5 km | 15.59 | 7.83 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4099
5 | 100 | 4100 | 0501711041 | Region V (Bicol Region) | Camarines Sur | Caramoan | San Roque | 13.7525 | 123.8437 | R | 772 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.22 | 35.81 | Tier 2 High GIDA (Score 40.0–49.9) | 63.21 | 44.19 | 63.21 |  | E - Nearest node or line 3-5 km | 3.22 | 35.8 | Node: COC001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4100
5 | 101 | 4101 | 0501737006 | Region V (Bicol Region) | Camarines Sur | Tinambac | Bani | 13.9644 | 123.3288 | R | 592 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.37 | 16.31 | Tier 2 High GIDA (Score 40.0–49.9) | 63.2 | 44.18 | 63.2 |  | F - Nearest node and line over 5 km | 10.37 | 16.31 | Node: TCC002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4101
5 | 102 | 4102 | 0803728004 | Region VIII (Eastern Visayas) | Leyte | La Paz | Bocawon | 17.6499 | 120.6687 | R | 256 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.51 | 7.33 | Tier 2 High GIDA (Score 40.0–49.9) | 63.2 | 44.18 | 63.2 |  | D - Other node or line within 3 km | 1.34 | 1.27 | Line: CABLE LAYED | Route options survey candidate: compare actual node lateral with approved line tap. | 4102
5 | 103 | 4103 | 1903615043 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Malabang | Mananayo | 17.2546 | 122.2287 | R | 1227 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 63.2 | 44.18 | 63.2 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4103
5 | 104 | 4104 | 0402106032 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz I | 14.3112 | 120.9361 | R | 3486 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.67 | 3.33 | Tier 2 High GIDA (Score 40.0–49.9) | 63.19 | 44.18 | 63.19 |  | D - Other node or line within 3 km | 2.74 | 1.94 | Line: NCC001 TO TGY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4104
5 | 105 | 4105 | 1906611002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Bakong | 17.2551 | 122.2304 | R | 882 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.8 | 32.91 | Tier 2 High GIDA (Score 40.0–49.9) | 63.19 | 44.18 | 63.19 |  | F - Nearest node and line over 5 km | 29.55 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4105
5 | 106 | 4106 | 1907011002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Datu Amilhamja Jaafar | 17.2558 | 122.2299 | R | 1688 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 63.16 | 44.16 | 63.16 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4106
5 | 107 | 4107 | 1400125001 | Cordillera Administrative Region (CAR) | Abra | Tineg | Poblacion | 17.7825 | 120.9435 | R | 701 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.26 | 27.59 | Tier 2 High GIDA (Score 40.0–49.9) | 63.15 | 44.15 | 63.15 |  | F - Nearest node and line over 5 km | 32.26 | 29.01 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4107
5 | 108 | 4108 | 0405646006 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Bukal | 13.9728 | 122.5897 | R | 521 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.16 | 3.74 | Tier 2 High GIDA (Score 40.0–49.9) | 63.15 | 44.15 | 63.15 |  | E - Nearest node or line 3-5 km | 5.16 | 3.73 | Line: LZQ001 TO DEL GALLEGO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4108
5 | 109 | 4109 | 1908822001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Biarong | 17.2551 | 122.2291 | R | 1530 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 63.14 | 44.14 | 63.14 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4109
5 | 110 | 4110 | PH0004110 | XIII | Surigao Del Norte | Surigao City | Alegria | 9.5363 | 125.5585 | R | 2328 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.9 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 63.14 | 44.14 | 63.14 |  | C - Line within 0.5 km; node over 1 km | 8.9 | 0.45 | Line: ALEGRIA - SURIGAO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4110
5 | 111 | 4111 | 0603046009 | Region VI (Western Visayas) | Iloilo | Tubungan | Bantayanan | 10.7862 | 122.3031 | R | 391 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.78 | 11.29 | Tier 2 High GIDA (Score 40.0–49.9) | 63.14 | 44.14 | 63.14 |  | F - Nearest node and line over 5 km | 14.63 | 11.13 | Line: 17,509 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4111
5 | 112 | 4112 | 0907344013 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Nangan-nangan | 7.916 | 123.2044 | R | 732 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.45 | 9.3 | Tier 2 High GIDA (Score 40.0–49.9) | 63.14 | 44.14 | 63.14 |  | F - Nearest node and line over 5 km | 26.45 | 9.27 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4112
5 | 113 | 4113 | 0803721005 | Region VIII (Eastern Visayas) | Leyte | Inopacan | Caulisihan | 10.5408 | 124.8814 | R | 352 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.71 | 8.19 | Tier 2 High GIDA (Score 40.0–49.9) | 63.13 | 44.14 | 63.13 |  | F - Nearest node and line over 5 km | 17.71 | 12.43 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4113
5 | 114 | 4114 | PH0004114 | NCR | Metro Manila | Taguig City | East Rembo | 14.6341 | 120.9805 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.62 | Tier 2 High GIDA (Score 40.0–49.9) | 63.13 | 44.14 | 63.13 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4114
5 | 115 | 4115 | 0203104023 | Region II (Cagayan Valley) | Isabela | Benito Soliven | Sinipit | 16.8771 | 121.9475 | R | 501 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.05 | 18.37 | Tier 2 High GIDA (Score 40.0–49.9) | 63.13 | 44.13 | 63.13 |  | F - Nearest node and line over 5 km | 12.05 | 18.37 | Node: BLI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4115
5 | 116 | 4116 | PH0004116 | XI | Davao Del Sur | Davao City | Barangay 16-B (Pob.) | 7.2539 | 125.6705 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.27 | 5.59 | Tier 2 High GIDA (Score 40.0–49.9) | 63.12 | 44.13 | 63.12 |  | D - Other node or line within 3 km | 5.31 | 1.58 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 4116
5 | 117 | 4117 | PH0004117 | CAR | Benguet | Baguio City | Imelda Village | 16.4225 | 120.5952 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.91 | 2.9 | Tier 2 High GIDA (Score 40.0–49.9) | 63.12 | 44.13 | 63.12 |  | A - Node within 0.5 km | 0.38 | 0.88 | Node: BGC004 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4117
5 | 118 | 4118 | 0600601023 | Region VI (Western Visayas) | Antique | Anini-Y | Tagaytay | 10.4614 | 121.9431 | R | 369 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.47 | 15.75 | Tier 2 High GIDA (Score 40.0–49.9) | 63.12 | 44.13 | 63.12 |  | F - Nearest node and line over 5 km | 33.47 | 15.7 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4118
5 | 119 | 4119 | 0702232015 | Region VII (Central Visayas) | Cebu | Minglanilla | Tulay | 10.2391 | 123.7927 | U | 12101 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.28 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 63.12 | 44.13 | 63.12 |  | C - Line within 0.5 km; node over 1 km | 1.28 | 0.03 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4119
5 | 120 | 4120 | 0301412009 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Iba | 14.7539 | 120.9818 | U | 9791 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 1.48 | Tier 2 High GIDA (Score 40.0–49.9) | 63.12 | 44.13 | 63.12 |  | B - Node 0.5-1 km | 0.91 | 1.48 | Node: MEB001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4120
5 | 121 | 4121 | 0401003013 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 8 | 13.9431 | 120.7362 | R | 2164 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 0.98 | Tier 2 High GIDA (Score 40.0–49.9) | 63.09 | 44.11 | 63.09 |  | B - Node 0.5-1 km | 0.88 | 0.04 | Line: UG NSB001 TO BYB001 TO LYB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4121
5 | 122 | 4122 | 0704602002 | Region VII (Central Visayas) | Negros Oriental | Ayungon | Jandalamanon | 9.8441 | 123.0865 | R | 1153 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.58 | 4.98 | Tier 2 High GIDA (Score 40.0–49.9) | 63.09 | 44.11 | 63.09 |  | F - Nearest node and line over 5 km | 21.58 | 15.48 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4122
5 | 123 | 4123 | PH0004123 | IV-A | Cavite | City of Bacoor | Mambog 1 | 14.4246 | 120.974 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.33 | 5.98 | Tier 2 High GIDA (Score 40.0–49.9) | 63.08 | 44.1 | 63.08 |  | B - Node 0.5-1 km | 0.87 | 2.86 | Node: BRC006 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4123
5 | 124 | 4124 | 1402702004 | Cordillera Administrative Region (CAR) | Ifugao | Hungduan | Bangbang | 16.8319 | 121.0253 | R | 603 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.03 | 5.22 | Tier 2 High GIDA (Score 40.0–49.9) | 63.08 | 44.1 | 63.08 |  | F - Nearest node and line over 5 km | 7.03 | 5.17 | Line: HINGYON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4124
5 | 125 | 4125 | 0300809022 | Region III (Central Luzon) | Bataan | Orani | Tenejero | 14.7965 | 120.5395 | R | 1747 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.01 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 63.08 | 44.1 | 63.08 |  | B - Node 0.5-1 km | 0.71 | 0.18 | Line: 36 CORE 3X12 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4125
5 | 126 | 4126 | PH0004126 | V | Camarines Sur | Naga City | Santa Cruz | 13.6263 | 123.182 | R | 2195 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 1.06 | Tier 2 High GIDA (Score 40.0–49.9) | 63.06 | 44.09 | 63.06 |  | D - Other node or line within 3 km | 1.29 | 1.05 | Line: HH05-EE05 | Route options survey candidate: compare actual node lateral with approved line tap. | 4126
5 | 127 | 4127 | PH0004127 | IX | Zamboanga Del Sur | Zamboanga City | Tumitus | 7.3904 | 122.3778 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.06 | 6.52 | Tier 2 High GIDA (Score 40.0–49.9) | 63.06 | 44.09 | 63.06 |  | F - Nearest node and line over 5 km | 21.06 | 6.5 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4127
5 | 128 | 4128 | 0405801011 | Region IV-A (CALABARZON) | Rizal | Angono | San Roque | 14.5325 | 121.1614 | U | 12209 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 63.06 | 44.09 | 63.06 |  | B - Node 0.5-1 km | 0.91 | 0.85 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4128
5 | 129 | 4129 | 0200905004 | Region II (Cagayan Valley) | Batanes | Sabtang | Savidug | 20.3098 | 121.8879 | R | 202 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 206.39 | 202.92 | Tier 2 High GIDA (Score 40.0–49.9) | 63.05 | 44.08 | 63.05 |  | F - Nearest node and line over 5 km | 206 | 202.92 | Line: SEGMENT 42 (STA ANA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4129
5 | 130 | 4130 | 1208002016 | Region XII (SOCCSKSARGEN) | Sarangani | Glan | Kaltuad | 5.736 | 125.3532 | R | 2318 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.86 | 46.39 | Tier 2 High GIDA (Score 40.0–49.9) | 63.05 | 44.08 | 63.05 |  | F - Nearest node and line over 5 km | 41.86 | 46.38 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4130
5 | 131 | 4131 | PH0004131 | IX | Zamboanga Del Sur | Zamboanga City | San Jose Cawa-cawa | 7.246 | 122.2346 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.77 | 5.97 | Tier 2 High GIDA (Score 40.0–49.9) | 63.03 | 44.07 | 63.03 |  | D - Other node or line within 3 km | 2.93 | 2.3 | Line: CABLE INSTALLED | Route options survey candidate: compare actual node lateral with approved line tap. | 4131
5 | 132 | 4132 | 1906613031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Lower Laus | 17.2554 | 122.2295 | R | 1645 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 2 High GIDA (Score 40.0–49.9) | 63.03 | 44.06 | 63.03 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4132
5 | 133 | 4133 | 1906618006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Lapak | 17.2556 | 122.2297 | R | 2754 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 63.03 | 44.06 | 63.03 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4133
5 | 134 | 4134 | 1903614004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Balagunun | 17.2548 | 122.2292 | R | 1284 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.51 | Tier 2 High GIDA (Score 40.0–49.9) | 63.02 | 44.06 | 63.02 |  | F - Nearest node and line over 5 km | 29.44 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4134
5 | 135 | 4135 | PH0004135 | IV-A | Cavite | Cavite City | Barangay 47-A | 14.4773 | 120.8928 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.86 | 6.4 | Tier 2 High GIDA (Score 40.0–49.9) | 63.02 | 44.06 | 63.02 |  | B - Node 0.5-1 km | 0.63 | 4.15 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4135
5 | 136 | 4136 | 1705205051 | MIMAROPA Region | Oriental Mindoro | City of Calapan | San Vicente East | 13.4085 | 121.1803 | U | 586 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 3.9 | Tier 2 High GIDA (Score 40.0–49.9) | 63.02 | 44.06 | 63.02 |  | D - Other node or line within 3 km | 2.3 | 3.89 | Node: CLM002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4136
5 | 137 | 4137 | 1705303001 | MIMAROPA Region | Palawan | Araceli | Balogo | 10.5538 | 119.8524 | R | 882 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.83 | 42.61 | Tier 2 High GIDA (Score 40.0–49.9) | 62.98 | 44.03 | 62.98 |  | F - Nearest node and line over 5 km | 33.83 | 42.61 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4137
5 | 138 | 4138 | 0301412011 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Lawa | 14.7348 | 120.9778 | U | 16298 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 1.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.98 | 44.03 | 62.98 |  | D - Other node or line within 3 km | 1.08 | 1.3 | Node: MEB003 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4138
5 | 139 | 4139 | PH0004139 | IV-A | Laguna | San Pablo City | Barangay III-D (Pob.) | 14.0698 | 121.3305 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 62.98 | 44.03 | 62.98 |  | C - Line within 0.5 km; node over 1 km | 1.17 | 0.1 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4139
5 | 140 | 4140 | PH0004140 | IV-A | Quezon | Lucena City | Barangay 9 (Pob.) | 13.9394 | 121.62 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.52 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 62.97 | 44.02 | 62.97 |  | C - Line within 0.5 km; node over 1 km | 1.15 | 0.01 | Line: LCQ001 TO LZQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4140
5 | 141 | 4141 | 1705323004 | MIMAROPA Region | Palawan | Rizal | Canipaan | 8.5743 | 117.2658 | R | 2842 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 206.83 | 209.1 | Tier 2 High GIDA (Score 40.0–49.9) | 62.97 | 44.02 | 62.97 |  | F - Nearest node and line over 5 km | 206.83 | 208.85 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4141
5 | 142 | 4142 | PH0004142 | BARMM (LaMa+SGA) | Maguindanao del Norte | Cotabato City | Poblacion V | 7.2187 | 124.2386 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.88 | 21.01 | Tier 2 High GIDA (Score 40.0–49.9) | 62.96 | 44.02 | 62.96 |  | F - Nearest node and line over 5 km | 61.6 | 60.47 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4142
5 | 143 | 4143 | PH0004143 | IV-A | Cavite | City of Bacoor | P.F. Espiritu 6 | 14.3815 | 120.9772 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.35 | 5.17 | Tier 2 High GIDA (Score 40.0–49.9) | 62.96 | 44.01 | 62.96 |  | D - Other node or line within 3 km | 1.52 | 6.36 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4143
5 | 144 | 4144 | 0405811007 | Region IV-A (CALABARZON) | Rizal | San Mateo | Malanday | 14.7046 | 121.125 | U | 13906 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.1 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 62.96 | 44.01 | 62.96 |  | C - Line within 0.5 km; node over 1 km | 2.1 | 0.36 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4144
5 | 145 | 4145 | 1705313008 | MIMAROPA Region | Palawan | Linapacan | New Culaylayan | 11.4226 | 119.7584 | R | 1692 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.59 | 72.09 | Tier 2 High GIDA (Score 40.0–49.9) | 62.95 | 44.01 | 62.95 |  | F - Nearest node and line over 5 km | 25.59 | 71.94 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4145
5 | 146 | 4146 | 0203121001 | Region II (Cagayan Valley) | Isabela | Palanan | Bisag | 17.0123 | 122.3825 | R | 909 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.41 | 51.04 | Tier 2 High GIDA (Score 40.0–49.9) | 62.95 | 44.01 | 62.95 |  | F - Nearest node and line over 5 km | 39.41 | 51.03 | Node: SOI001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4146
5 | 147 | 4147 | 1380800002 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Bayanan | 14.407 | 121.0453 | U | 39783 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.13 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 62.94 | 44 | 62.94 |  | C - Line within 0.5 km; node over 1 km | 1.13 | 0.15 | Line: RELIANCE PSG001 TO BÑL001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4147
5 | 148 | 4148 | 1380900016 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Proper | 14.6494 | 120.9521 | U | 18610 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 62.94 | 44 | 62.94 |  | B - Node 0.5-1 km | 0.95 | 2.33 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4148
5 | 149 | 4149 | 1204712004 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Balatican | 7.0899 | 124.6842 | R | 2019 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.65 | 13.75 | Tier 2 High GIDA (Score 40.0–49.9) | 62.93 | 44 | 62.93 |  | F - Nearest node and line over 5 km | 17.65 | 13.71 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4149
5 | 150 | 4150 | 0403403025 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Tubigan | 14.3288 | 121.07 | U | 6848 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 62.93 | 43.99 | 62.93 |  | D - Other node or line within 3 km | 1.25 | 0.61 | Line: AE CRC005-BNL001-CLB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4150
5 | 151 | 4151 | 0402111015 | Region IV-A (CALABARZON) | Cavite | Kawit | Binakayan-Aplaya | 14.4286 | 120.914 | R | 3521 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.72 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 62.92 | 43.99 | 62.92 |  | D - Other node or line within 3 km | 3.33 | 1.24 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4151
5 | 152 | 4152 | 0504104015 | Region V (Bicol Region) | Masbate | Batuan | Sawang | 12.3672 | 123.767 | R | 1008 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.25 | 14.5 | Tier 2 High GIDA (Score 40.0–49.9) | 62.92 | 43.99 | 62.92 |  | F - Nearest node and line over 5 km | 12.25 | 16.33 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4152
5 | 153 | 4153 | 1705313011 | MIMAROPA Region | Palawan | Linapacan | San Nicolas | 11.3848 | 119.8125 | R | 1263 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 70.81 | Tier 2 High GIDA (Score 40.0–49.9) | 62.9 | 43.97 | 62.9 |  | F - Nearest node and line over 5 km | 29.28 | 70.67 | Node: ENW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4153
5 | 154 | 4154 | PH0004154 | II | Nueva Vizcaya | Kayapa | Amilong Labeng | 16.299 | 120.8855 | R | 988 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.52 | 6.04 | Tier 2 High GIDA (Score 40.0–49.9) | 62.89 | 43.97 | 62.89 |  | F - Nearest node and line over 5 km | 6.52 | 5.95 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4154
5 | 155 | 4155 | 0405622078 | Region IV-A (CALABARZON) | Quezon | Lopez | Santo Niño Ibaba | 13.793 | 122.3675 | R | 552 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 62.89 | 43.97 | 62.89 |  | D - Other node or line within 3 km | 11.22 | 2.04 | Line: LZQ001 TO MCQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4155
5 | 156 | 4156 | 0300803022 | Region III (Central Luzon) | Bataan | City of Balanga | Tortugas | 14.6928 | 120.5601 | R | 2979 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 1.65 | Tier 2 High GIDA (Score 40.0–49.9) | 62.89 | 43.97 | 62.89 |  | D - Other node or line within 3 km | 1.89 | 1.64 | Line: CITY OF BALANGA | Route options survey candidate: compare actual node lateral with approved line tap. | 4156
5 | 157 | 4157 | 0402106065 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin II | 14.318 | 120.9524 | U | 12308 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.56 | 1.82 | Tier 2 High GIDA (Score 40.0–49.9) | 62.89 | 43.97 | 62.89 |  | D - Other node or line within 3 km | 1.56 | 1.75 | Node: DMC004 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4157
5 | 158 | 4158 | PH0004158 | NCR | Metro Manila | Caloocan City | Barangay 164 | 14.6858 | 121.0186 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 66.85 | 66.91 | Tier 2 High GIDA (Score 40.0–49.9) | 62.88 | 43.96 | 62.88 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.42 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4158
5 | 159 | 4159 | 0401029023 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 1 | 13.8788 | 120.9192 | R | 392 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.41 | 1.98 | Tier 2 High GIDA (Score 40.0–49.9) | 62.88 | 43.96 | 62.88 |  | A - Node within 0.5 km | 0.41 | 1.95 | Node: TLB001 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4159
5 | 160 | 4160 | 1381701006 | National Capital Region (NCR) | Fourth District (Not a Province) | Pateros | San Roque | 14.5421 | 121.0707 | U | 4901 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.38 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 62.88 | 43.96 | 62.88 |  | A - Node within 0.5 km | 0.38 | 0.37 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4160
5 | 161 | 4161 | PH0004161 | IX | Zamboanga Del Sur | Zamboanga City | Taguiti | 7.3063 | 122.2821 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.67 | 2.01 | Tier 2 High GIDA (Score 40.0–49.9) | 62.88 | 43.96 | 62.88 |  | D - Other node or line within 3 km | 7.67 | 1.94 | Line: CABLE INSTALLED | Route options survey candidate: compare actual node lateral with approved line tap. | 4161
5 | 162 | 4162 | 0402103049 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino VI | 14.4138 | 120.9824 | U | 21186 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.89 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 62.86 | 43.95 | 62.86 |  | D - Other node or line within 3 km | 2.13 | 3.52 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4162
5 | 163 | 4163 | 1003506035 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Topocon | 7.7422 | 123.8133 | R | 998 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.44 | 10.7 | Tier 2 High GIDA (Score 40.0–49.9) | 62.85 | 43.94 | 62.85 |  | F - Nearest node and line over 5 km | 33.48 | 17.3 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4163
5 | 164 | 4164 | 1381000007 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | B. F. Homes | 14.452 | 121.0406 | U | 94534 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.62 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 62.85 | 43.94 | 62.85 |  | B - Node 0.5-1 km | 0.62 | 0.33 | Line: Aerial 216C MTF | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4164
5 | 165 | 4165 | 0500504011 | Region V (Bicol Region) | Albay | Guinobatan | Doña Mercedes | 13.1291 | 123.5904 | R | 1476 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.31 | 3.98 | Tier 2 High GIDA (Score 40.0–49.9) | 62.85 | 43.94 | 62.85 |  | B - Node 0.5-1 km | 0.85 | 6.7 | Node: GNA002 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4165
5 | 166 | 4166 | 0301412005 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bayugo | 14.7329 | 120.9536 | U | 20064 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 62.85 | 43.94 | 62.85 |  | D - Other node or line within 3 km | 1.71 | 0.83 | Line: 48 CORE | Route options survey candidate: compare actual node lateral with approved line tap. | 4166
5 | 167 | 4167 | 1908803001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Abdullah Sangki | Banaba | 17.2552 | 122.2292 | R | 4337 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.84 | 43.93 | 62.84 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4167
5 | 168 | 4168 | 1705311004 | MIMAROPA Region | Palawan | Dumaran | Capayas | 10.4472 | 119.6251 | R | 1668 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.38 | 27.3 | Tier 2 High GIDA (Score 40.0–49.9) | 62.83 | 43.93 | 62.83 |  | F - Nearest node and line over 5 km | 26.38 | 27.25 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4168
5 | 169 | 4169 | 1381300102 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | San Roque | 14.6171 | 121.0632 | U | 19894 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 62.83 | 43.92 | 62.83 |  | B - Node 0.5-1 km | 0.67 | 0.23 | Line: UG 144C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4169
5 | 170 | 4170 | 1906601033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Indanan | Tubig Parang | 17.2557 | 122.2285 | R | 2371 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.6 | Tier 2 High GIDA (Score 40.0–49.9) | 62.83 | 43.92 | 62.83 |  | F - Nearest node and line over 5 km | 29.44 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4170
5 | 171 | 4171 | 1102315034 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Santo Niño | 7.304 | 125.6814 | U | 5242 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.89 | 5.88 | Tier 2 High GIDA (Score 40.0–49.9) | 62.83 | 43.92 | 62.83 |  | A - Node within 0.5 km | 0.4 | 0.05 | Line: DAVAO CITY - TRENTO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4171
5 | 172 | 4172 | 1003508004 | Region X (Northern Mindanao) | Lanao del Norte | Kolambugan | Bubong | 8.1253 | 123.9155 | R | 196 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.61 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 62.83 | 43.92 | 62.83 |  | C - Line within 0.5 km; node over 1 km | 15.75 | 0.01 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4172
5 | 173 | 4173 | 1381300128 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Valencia | 9.2111 | 118.0432 | U | 11357 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.14 | 1.15 | Tier 2 High GIDA (Score 40.0–49.9) | 62.82 | 43.92 | 62.82 |  | F - Nearest node and line over 5 km | 95.92 | 97.93 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4173
5 | 174 | 4174 | PH0004174 | CAR | Benguet | Baguio City | Cabinet Hill-Teacher's Camp | 16.4157 | 120.5884 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.53 | 5.86 | Tier 2 High GIDA (Score 40.0–49.9) | 62.82 | 43.92 | 62.82 |  | A - Node within 0.5 km | 0.1 | 0.27 | Node: BGC002 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4174
5 | 175 | 4175 | 0102805017 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Caunayan | 18.0896 | 120.5666 | U | 1122 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.1 | 2.55 | Tier 2 High GIDA (Score 40.0–49.9) | 62.82 | 43.91 | 62.82 |  | C - Line within 0.5 km; node over 1 km | 3.99 | 0.19 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4175
5 | 176 | 4176 | 0300811003 | Region III (Central Luzon) | Bataan | Pilar | Bagumbayan | 14.666 | 120.5645 | R | 1531 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.85 | 0.55 | Tier 2 High GIDA (Score 40.0–49.9) | 62.82 | 43.91 | 62.82 |  | D - Other node or line within 3 km | 2.85 | 0.5 | Line: Pipe 2 | Route options survey candidate: compare actual node lateral with approved line tap. | 4176
5 | 177 | 4177 | 1003502012 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Landa | 8.0866 | 124.228 | R | 3451 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.49 | 1.02 | Tier 2 High GIDA (Score 40.0–49.9) | 62.81 | 43.91 | 62.81 |  | D - Other node or line within 3 km | 9.93 | 1.58 | Line: PANTAR | Route options survey candidate: compare actual node lateral with approved line tap. | 4177
5 | 178 | 4178 | PH0004178 | X | Misamis Oriental | Cagayan De Oro City | Kauswagan | 8.5012 | 124.6309 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 62.81 | 43.91 | 62.81 |  | B - Node 0.5-1 km | 0.88 | 0.16 | Line: CAGAYAN DE ORO - MALAYBALAY | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4178
5 | 179 | 4179 | PH0004179 | X | Misamis Oriental | Cagayan De Oro City | Camaman-an | 8.4729 | 124.659 | R | 2272 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 1.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.8 | 43.9 | 62.8 |  | D - Other node or line within 3 km | 1.61 | 1.22 | Line: CAGAYAN DE ORO - MALAYBALAY | Route options survey candidate: compare actual node lateral with approved line tap. | 4179
5 | 180 | 4180 | 1906607042 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Tubig Gantang | 17.2551 | 122.2299 | R | 1575 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.77 | 33.96 | Tier 2 High GIDA (Score 40.0–49.9) | 62.78 | 43.89 | 62.78 |  | F - Nearest node and line over 5 km | 29.52 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4180
5 | 181 | 4181 | 1381300036 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | East Kamias | 14.6215 | 121.0616 | U | 6663 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.54 | Tier 2 High GIDA (Score 40.0–49.9) | 62.78 | 43.89 | 62.78 |  | A - Node within 0.5 km | 0.45 | 0.06 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4181
5 | 182 | 4182 | 1380700005 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Malanday | 14.6502 | 121.0944 | U | 55690 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 62.76 | 43.88 | 62.76 |  | C - Line within 0.5 km; node over 1 km | 1.15 | 0.38 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4182
5 | 183 | 4183 | 0201501015 | Region II (Cagayan Valley) | Cagayan | Abulug | Siguiran | 18.4704 | 121.4163 | R | 1415 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.04 | 7.41 | Tier 2 High GIDA (Score 40.0–49.9) | 62.76 | 43.87 | 62.76 |  | F - Nearest node and line over 5 km | 8.04 | 7.36 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4183
5 | 184 | 4184 | 0501714012 | Region V (Bicol Region) | Camarines Sur | Garchitorena | Mansangat | 13.9568 | 123.6477 | R | 820 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.48 | 33.94 | Tier 2 High GIDA (Score 40.0–49.9) | 62.75 | 43.87 | 62.75 |  | F - Nearest node and line over 5 km | 28.48 | 33.72 | Node: LYC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4184
5 | 185 | 4185 | 1704001059 | MIMAROPA Region | Marinduque | Boac | Tumagabok | 13.3586 | 121.9971 | R | 403 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.79 | 39.64 | Tier 2 High GIDA (Score 40.0–49.9) | 62.74 | 43.86 | 62.74 |  | F - Nearest node and line over 5 km | 40.79 | 39.62 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4185
5 | 186 | 4186 | 0402117008 | Region IV-A (CALABARZON) | Cavite | Rosario | Poblacion | 14.4172 | 120.8559 | U | 2210 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.21 | 2.44 | Tier 2 High GIDA (Score 40.0–49.9) | 62.74 | 43.86 | 62.74 |  | D - Other node or line within 3 km | 2.21 | 2.44 | Node: TRC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4186
5 | 187 | 4187 | 1381300041 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Fairview | 14.7102 | 121.0652 | U | 64407 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 62.72 | 43.85 | 62.72 |  | C - Line within 0.5 km; node over 1 km | 1.35 | 0.34 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4187
5 | 188 | 4188 | PH0004188 | III | Pampanga | San Fernando City | Santa Teresita | 12.4966 | 123.716 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.34 | 0.8 | Tier 2 High GIDA (Score 40.0–49.9) | 62.72 | 43.85 | 62.72 |  | F - Nearest node and line over 5 km | 18.83 | 18.68 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4188
5 | 189 | 4189 | 0103314007 | Region I (Ilocos Region) | La Union | City of San Fernando | Barangay II | 13.4733 | 123.1224 | U | 443 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.66 | 3.43 | Tier 2 High GIDA (Score 40.0–49.9) | 62.71 | 43.84 | 62.71 |  | F - Nearest node and line over 5 km | 9.7 | 9.35 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4189
5 | 190 | 4190 | 1001313007 | Region X (Northern Mindanao) | Bukidnon | Malitbog | Sampiano | 8.4898 | 124.8704 | R | 1406 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.06 | 9.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.7 | 43.84 | 62.7 |  | F - Nearest node and line over 5 km | 13.06 | 9.23 | Line: CAGAYAN DE ORO - MALAYBALAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4190
5 | 191 | 4191 | PH0004191 | III | Nueva Ecija | Cabanatuan City | Magsaysay South | 15.5039 | 121.0297 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.87 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 62.7 | 43.84 | 62.7 |  | F - Nearest node and line over 5 km | 7.75 | 5.33 | Line: TALAVERA - MULTI NET | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4191
5 | 192 | 4192 | 0102805018 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Valdez Pob. | 18.053 | 120.5651 | R | 820 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 0.86 | Tier 2 High GIDA (Score 40.0–49.9) | 62.69 | 43.83 | 62.69 |  | D - Other node or line within 3 km | 1.41 | 0.86 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 4192
5 | 193 | 4193 | 0203102037 | Region II (Cagayan Valley) | Isabela | Angadanan | Macaniao | 16.8079 | 121.8815 | R | 627 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.9 | 14.5 | Tier 2 High GIDA (Score 40.0–49.9) | 62.69 | 43.82 | 62.69 |  | F - Nearest node and line over 5 km | 12.9 | 14.5 | Node: ANI002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4193
5 | 194 | 4194 | 0103311003 | Region I (Ilocos Region) | La Union | Naguilian | Al-alinao Sur | 16.5036 | 120.4225 | R | 1000 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.72 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 62.68 | 43.82 | 62.68 |  | E - Nearest node or line 3-5 km | 3.72 | 5.12 | Node: NGU001 - TYPE 4 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4194
5 | 195 | 4195 | 1003515017 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Poblacion | 7.7888 | 123.9155 | R | 1071 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.46 | 21.48 | Tier 2 High GIDA (Score 40.0–49.9) | 62.68 | 43.82 | 62.68 |  | F - Nearest node and line over 5 km | 31.03 | 20.1 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4195
5 | 196 | 4196 | PH0004196 | VIII | Leyte | Tacloban City | Barangay 50-B | 11.2377 | 125 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.77 | 2.37 | Tier 2 High GIDA (Score 40.0–49.9) | 62.67 | 43.82 | 62.67 |  | A - Node within 0.5 km | 0.34 | 2.97 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4196
5 | 197 | 4197 | 0501734038 | Region V (Bicol Region) | Camarines Sur | Sipocot | San Vicente | 13.7641 | 122.9755 | R | 1166 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.23 | 1 | Tier 2 High GIDA (Score 40.0–49.9) | 62.67 | 43.81 | 62.67 |  | A - Node within 0.5 km | 0.23 | 0.18 | Line: PAGBILAO - NAGA (UG + Aerial) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4197
5 | 198 | 4198 | 1903634024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Maguing | Ilalag | 17.2536 | 122.2282 | R | 1019 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.17 | 35.01 | Tier 2 High GIDA (Score 40.0–49.9) | 62.66 | 43.81 | 62.66 |  | F - Nearest node and line over 5 km | 29.27 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4198
5 | 199 | 4199 | 1705202003 | MIMAROPA Region | Oriental Mindoro | Bansud | Bato | 12.7507 | 121.3175 | R | 885 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.06 | 16.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.66 | 43.81 | 62.66 |  | F - Nearest node and line over 5 km | 18.06 | 16.24 | Line: AE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4199
5 | 200 | 4200 | PH0004200 | NIR | Negros Occidental | Bacolod City | Barangay 39 (Pob.) | 10.6314 | 122.9566 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.01 | 1.72 | Tier 2 High GIDA (Score 40.0–49.9) | 62.66 | 43.81 | 62.66 |  | C - Line within 0.5 km; node over 1 km | 1.86 | 0.39 | Line: FOC 144C TALISAY CLS TO SAN CARLOS CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4200
5 | 201 | 4201 | 0201506049 | Region II (Cagayan Valley) | Cagayan | Baggao | C. Verzosa | 17.9948 | 121.9345 | R | 767 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.49 | 25.75 | Tier 2 High GIDA (Score 40.0–49.9) | 62.65 | 43.8 | 62.65 |  | F - Nearest node and line over 5 km | 6.49 | 25.75 | Node: BOC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4201
5 | 202 | 4202 | 0907319005 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Molave | Bagong Gutlang | 8.2387 | 123.462 | R | 851 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.62 | 34.5 | Tier 2 High GIDA (Score 40.0–49.9) | 62.65 | 43.8 | 62.65 |  | F - Nearest node and line over 5 km | 34.62 | 34.5 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4202
5 | 203 | 4203 | 0603027010 | Region VI (Western Visayas) | Iloilo | Lemery | Dapdapan | 11.2222 | 122.981 | R | 587 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.38 | 2.53 | Tier 2 High GIDA (Score 40.0–49.9) | 62.64 | 43.79 | 62.64 |  | D - Other node or line within 3 km | 5.38 | 2.52 | Line: SARA - PASSI | Route options survey candidate: compare actual node lateral with approved line tap. | 4203
5 | 204 | 4204 | 1381600017 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Malinta | 14.6911 | 120.9658 | U | 52850 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.2 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 62.62 | 43.78 | 62.62 |  | C - Line within 0.5 km; node over 1 km | 1.2 | 0.16 | Line: 48 CORE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4204
5 | 205 | 4205 | 0806408004 | Region VIII (Eastern Visayas) | Southern Leyte | Macrohon | Cambaro | 10.094 | 124.9611 | R | 382 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.13 | 2.88 | Tier 2 High GIDA (Score 40.0–49.9) | 62.62 | 43.78 | 62.62 |  | F - Nearest node and line over 5 km | 15.07 | 7.2 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4205
5 | 206 | 4206 | PH0004206 | XI | Davao Del Sur | Davao City | Pandaitan | 7.385 | 125.5407 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.03 | 17.87 | Tier 2 High GIDA (Score 40.0–49.9) | 62.62 | 43.78 | 62.62 |  | F - Nearest node and line over 5 km | 18.03 | 17.87 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4206
5 | 207 | 4207 | 0402106049 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol III | 14.3494 | 120.9436 | U | 11497 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.97 | 1.72 | Tier 2 High GIDA (Score 40.0–49.9) | 62.6 | 43.76 | 62.6 |  | A - Node within 0.5 km | 0.45 | 5.35 | Node: DMC006 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4207
5 | 208 | 4208 | 0102805023 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Ablan Pob. | 18.1161 | 120.5722 | R | 751 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.95 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 62.59 | 43.76 | 62.59 |  | C - Line within 0.5 km; node over 1 km | 6.43 | 0.05 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4208
5 | 209 | 4209 | PH0004209 | VII | Cebu | Talisay City | Poblacion | 10.2455 | 123.8446 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.4 | 10.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.59 | 43.76 | 62.59 |  | C - Line within 0.5 km; node over 1 km | 1.89 | 0.04 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4209
5 | 210 | 4210 | 1381100194 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 194 | 14.5095 | 121.0021 | U | 4652 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 4.77 | Tier 2 High GIDA (Score 40.0–49.9) | 62.59 | 43.76 | 62.59 |  | B - Node 0.5-1 km | 0.84 | 0 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4210
5 | 211 | 4211 | PH0004211 | VII | Cebu | Cebu City | Zapatera | 10.3036 | 123.9021 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.47 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 62.59 | 43.76 | 62.59 |  | A - Node within 0.5 km | 0.47 | 0.09 | Line: DANAO - CEBU | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4211
5 | 212 | 4212 | PH0004212 | IV-A | Cavite | Cavite City | Barangay 42-B | 14.4815 | 120.9067 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.18 | 2 | Tier 2 High GIDA (Score 40.0–49.9) | 62.58 | 43.75 | 62.58 |  | D - Other node or line within 3 km | 2.19 | 3.9 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4212
5 | 213 | 4213 | 0405622070 | Region IV-A (CALABARZON) | Quezon | Lopez | San Rafael | 13.8483 | 122.2239 | R | 323 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.99 | 4.41 | Tier 2 High GIDA (Score 40.0–49.9) | 62.58 | 43.75 | 62.58 |  | E - Nearest node or line 3-5 km | 5.99 | 4.4 | Line: LCQ001 TO LZQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4213
5 | 214 | 4214 | 1403214017 | Cordillera Administrative Region (CAR) | Kalinga | Tanudan | Mangali Centro | 17.3008 | 121.2372 | R | 265 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.25 | 7.81 | Tier 2 High GIDA (Score 40.0–49.9) | 62.56 | 43.74 | 62.56 |  | F - Nearest node and line over 5 km | 10.25 | 7.59 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4214
5 | 215 | 4215 | 1908707002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Matanog | Bayanga Sur | 17.254 | 122.228 | R | 9894 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.28 | 34.18 | Tier 2 High GIDA (Score 40.0–49.9) | 62.56 | 43.73 | 62.56 |  | F - Nearest node and line over 5 km | 29.28 | 34.17 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4215
5 | 216 | 4216 | 0603023003 | Region VI (Western Visayas) | Iloilo | Janiuay | Aglobong | 11.047 | 122.3793 | R | 798 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.48 | 17.3 | Tier 2 High GIDA (Score 40.0–49.9) | 62.56 | 43.73 | 62.56 |  | F - Nearest node and line over 5 km | 18.48 | 17.29 | Line: Santa Barbara - Janiuay 18.361km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4216
5 | 217 | 4217 | 0802608017 | Region VIII (Eastern Visayas) | Eastern Samar | Giporlos | San Miguel | 11.1754 | 125.4664 | R | 134 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.33 | 48.56 | Tier 2 High GIDA (Score 40.0–49.9) | 62.55 | 43.73 | 62.55 |  | F - Nearest node and line over 5 km | 49.33 | 49.99 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4217
5 | 218 | 4218 | PH0004218 | IV-A | Laguna | San Pablo City | Bagong Pook VI-C (Pob.) | 14.073 | 121.3212 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 62.55 | 43.73 | 62.55 |  | C - Line within 0.5 km; node over 1 km | 1.03 | 0.1 | Line: SPO001 TO SAN JUAN CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4218
5 | 219 | 4219 | 0804805020 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Guba | 12.4292 | 124.5575 | R | 518 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.53 | 54.15 | Tier 2 High GIDA (Score 40.0–49.9) | 62.55 | 43.73 | 62.55 |  | F - Nearest node and line over 5 km | 54.53 | 54.06 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4219
5 | 220 | 4220 | 0405605023 | Region IV-A (CALABARZON) | Quezon | Buenavista | Maligaya | 13.707 | 122.3936 | R | 876 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.13 | 7.86 | Tier 2 High GIDA (Score 40.0–49.9) | 62.55 | 43.73 | 62.55 |  | F - Nearest node and line over 5 km | 8.13 | 7.85 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4220
5 | 221 | 4221 | 1380300026 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Santa Cruz | 14.5679 | 121.0172 | U | 3116 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.55 | 43.73 | 62.55 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.34 | Line: UG 288C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4221
5 | 222 | 4222 | 0600402005 | Region VI (Western Visayas) | Aklan | Balete | Cortes | 11.5286 | 122.3974 | R | 3645 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.98 | 3.39 | Tier 2 High GIDA (Score 40.0–49.9) | 62.54 | 43.72 | 62.54 |  | E - Nearest node or line 3-5 km | 3.98 | 3.39 | Line: IVISAN - KALIBO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4222
5 | 223 | 4223 | 1401106002 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Dalupirip | 16.3233 | 120.7228 | R | 2940 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.87 | 10.18 | Tier 2 High GIDA (Score 40.0–49.9) | 62.53 | 43.72 | 62.53 |  | F - Nearest node and line over 5 km | 5.87 | 10.02 | Node: ITB004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4223
5 | 224 | 4224 | PH0004224 | VI | Iloilo | Iloilo City | Abeto Mirasol Taft South | 10.7185 | 122.5434 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 1.7 | Tier 2 High GIDA (Score 40.0–49.9) | 62.53 | 43.72 | 62.53 |  | D - Other node or line within 3 km | 2.74 | 1.65 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 4224
5 | 225 | 4225 | 1903607046 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Butig | Ragayan | 17.2548 | 122.2288 | R | 1319 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 62.5 | 43.7 | 62.5 |  | F - Nearest node and line over 5 km | 29.41 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4225
5 | 226 | 4226 | 1102504004 | Region XI (Davao Region) | Davao Oriental | Caraga | Don Leon Balante | 7.3298 | 126.5171 | R | 1059 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 53.33 | 52.11 | Tier 2 High GIDA (Score 40.0–49.9) | 62.5 | 43.69 | 62.5 |  | F - Nearest node and line over 5 km | 53.33 | 51.93 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4226
5 | 227 | 4227 | 0102934035 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Julian Sur | 17.5741 | 120.3832 | R | 1387 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 62.48 | 43.68 | 62.48 |  | D - Other node or line within 3 km | 2.29 | 0.99 | Line: SEGMENT 3 (VIGAN - BATAC) | Route options survey candidate: compare actual node lateral with approved line tap. | 4227
5 | 228 | 4228 | 1400113003 | Cordillera Administrative Region (CAR) | Abra | Licuan-Baay | Cawayan | 17.5484 | 120.8749 | R | 419 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.74 | 26.72 | Tier 2 High GIDA (Score 40.0–49.9) | 62.48 | 43.68 | 62.48 |  | F - Nearest node and line over 5 km | 25.43 | 25.37 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4228
5 | 229 | 4229 | PH0004229 | IV-A | Laguna | San Pablo City | Barangay II-F (Pob.) | 14.0601 | 121.323 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.47 | Tier 2 High GIDA (Score 40.0–49.9) | 62.48 | 43.68 | 62.48 |  | B - Node 0.5-1 km | 0.71 | 0.38 | Line: AE NGL001 TO SPO001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4229
5 | 230 | 4230 | PH0004230 | VII | Cebu | Cebu City | Santa Cruz (Pob.) | 10.3675 | 123.8315 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.15 | 5.83 | Tier 2 High GIDA (Score 40.0–49.9) | 62.48 | 43.68 | 62.48 |  | D - Other node or line within 3 km | 2.89 | 8.9 | Node: CCY005 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4230
5 | 231 | 4231 | 0401029028 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 4 | 13.892 | 120.9199 | R | 309 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.93 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 62.47 | 43.67 | 62.47 |  | B - Node 0.5-1 km | 0.77 | 0.63 | Line: TUY - STA. TERESITA | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4231
5 | 232 | 4232 | 0601901015 | Region VI (Western Visayas) | Capiz | Cuartero | Malagab-i | 11.325 | 122.6921 | R | 1776 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.78 | 2.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.46 | 43.67 | 62.46 |  | D - Other node or line within 3 km | 7.78 | 2.34 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 4232
5 | 233 | 4233 | 1907011015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Tongsibalo | 17.2558 | 122.2299 | R | 2530 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 62.46 | 43.67 | 62.46 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4233
5 | 234 | 4234 | PH0004234 | VIII | Leyte | Tacloban City | Barangay 56 | 11.2383 | 124.9999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.33 | 14.44 | Tier 2 High GIDA (Score 40.0–49.9) | 62.46 | 43.67 | 62.46 |  | A - Node within 0.5 km | 0.31 | 3.04 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4234
5 | 235 | 4235 | 0806403009 | Region VIII (Eastern Visayas) | Southern Leyte | Hinunangan | Calinao | 10.381 | 125.1246 | R | 220 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.57 | 13.6 | Tier 2 High GIDA (Score 40.0–49.9) | 62.46 | 43.67 | 62.46 |  | F - Nearest node and line over 5 km | 42.49 | 37.07 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4235
5 | 236 | 4236 | 1705318006 | MIMAROPA Region | Palawan | Roxas | Iraan | 10.4386 | 119.3577 | R | 774 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.52 | 1.71 | Tier 2 High GIDA (Score 40.0–49.9) | 62.45 | 43.66 | 62.45 |  | D - Other node or line within 3 km | 13.52 | 1.7 | Line: TAYTAY - PUERTO PRINCESA | Route options survey candidate: compare actual node lateral with approved line tap. | 4236
5 | 237 | 4237 | 1403211017 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Romualdez | 17.4318 | 121.6154 | R | 834 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.65 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 62.44 | 43.65 | 62.44 |  | C - Line within 0.5 km; node over 1 km | 7.65 | 0.12 | Line: RIZAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4237
5 | 238 | 4238 | 1003514019 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Matampay | 7.9959 | 124.0895 | R | 1649 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.23 | 15.76 | Tier 2 High GIDA (Score 40.0–49.9) | 62.44 | 43.65 | 62.44 |  | F - Nearest node and line over 5 km | 20.41 | 18.89 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4238
5 | 239 | 4239 | 1381100198 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 198 | 14.5067 | 120.9998 | U | 1958 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.26 | 3.3 | Tier 2 High GIDA (Score 40.0–49.9) | 62.44 | 43.65 | 62.44 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.12 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4239
5 | 240 | 4240 | 0907308017 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Dumingag | Licabang | 8.2017 | 123.2548 | R | 1335 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.82 | 39.07 | Tier 2 High GIDA (Score 40.0–49.9) | 62.43 | 43.65 | 62.43 |  | F - Nearest node and line over 5 km | 45.82 | 39.07 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4240
5 | 241 | 4241 | PH0004241 | VII | Cebu | Talisay City | Dumlog | 10.2405 | 123.8407 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.71 | 12.23 | Tier 2 High GIDA (Score 40.0–49.9) | 62.43 | 43.64 | 62.43 |  | D - Other node or line within 3 km | 2.39 | 0.74 | Line: 96c | Route options survey candidate: compare actual node lateral with approved line tap. | 4241
5 | 242 | 4242 | 1903620029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Madang | 17.2545 | 122.228 | R | 946 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.24 | 35.07 | Tier 2 High GIDA (Score 40.0–49.9) | 62.42 | 43.64 | 62.42 |  | F - Nearest node and line over 5 km | 29.32 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4242
5 | 243 | 4243 | PH0004243 | CAR | Benguet | Baguio City | General Luna, Upper | 16.4 | 120.5878 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.23 | 3.15 | Tier 2 High GIDA (Score 40.0–49.9) | 62.41 | 43.63 | 62.41 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.01 | Line: BAGUIO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4243
5 | 244 | 4244 | 0200905006 | Region II (Cagayan Valley) | Batanes | Sabtang | Sumnanga | 20.3004 | 121.8437 | R | 362 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 203.91 | 200.8 | Tier 2 High GIDA (Score 40.0–49.9) | 62.4 | 43.62 | 62.4 |  | F - Nearest node and line over 5 km | 203.91 | 200.79 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4244
5 | 245 | 4245 | 0402116002 | Region IV-A (CALABARZON) | Cavite | Noveleta | Poblacion | 14.4264 | 120.8802 | R | 2291 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.46 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 62.38 | 43.61 | 62.38 |  | A - Node within 0.5 km | 0.46 | 0.45 | Line: NOVELETA | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4245
5 | 246 | 4246 | 0201512001 | Region II (Cagayan Valley) | Cagayan | Enrile | Alibago | 17.5727 | 121.7428 | R | 2285 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.09 | 2.47 | Tier 2 High GIDA (Score 40.0–49.9) | 62.38 | 43.61 | 62.38 |  | D - Other node or line within 3 km | 5.09 | 2.43 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Route options survey candidate: compare actual node lateral with approved line tap. | 4246
5 | 247 | 4247 | PH0004247 | VI | Capiz | Roxas City | Poblacion VI | 11.5188 | 122.7749 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 0.84 | Tier 2 High GIDA (Score 40.0–49.9) | 62.38 | 43.61 | 62.38 |  | D - Other node or line within 3 km | 1.84 | 1.1 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 4247
5 | 248 | 4248 | PH0004248 | VII | Cebu | Talisay City | Lawaan I | 10.2586 | 123.8222 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.09 | 8.6 | Tier 2 High GIDA (Score 40.0–49.9) | 62.38 | 43.61 | 62.38 |  | C - Line within 0.5 km; node over 1 km | 2.06 | 0.01 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4248
5 | 249 | 4249 | 1380300010 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Guadalupe Viejo | 14.5673 | 121.0403 | U | 6347 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 62.38 | 43.61 | 62.38 |  | C - Line within 0.5 km; node over 1 km | 1.25 | 0.02 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4249
5 | 250 | 4250 | 0403405037 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Parian | 14.2142 | 121.1515 | U | 28016 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.97 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 62.37 | 43.6 | 62.37 |  | C - Line within 0.5 km; node over 1 km | 1.97 | 0.08 | Line: AE SRL007-CBL001-CLB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4250
5 | 251 | 4251 | 1704004035 | MIMAROPA Region | Marinduque | Mogpog | Silangan | 13.5639 | 121.8559 | R | 625 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.36 | 32.89 | Tier 2 High GIDA (Score 40.0–49.9) | 62.37 | 43.6 | 62.37 |  | F - Nearest node and line over 5 km | 33.36 | 32.88 | Line: UNISAN TO MULANAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4251
5 | 252 | 4252 | 0500517026 | Region V (Bicol Region) | Albay | City of Tabaco | Oson | 13.3205 | 123.6835 | R | 1266 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.25 | 3.08 | Tier 2 High GIDA (Score 40.0–49.9) | 62.35 | 43.59 | 62.35 |  | E - Nearest node or line 3-5 km | 3.25 | 3.08 | Line: TABACO - LIGAO AERIAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4252
5 | 253 | 4253 | 1903613028 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madalum | Punud | 17.2543 | 122.2296 | R | 596 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 33.97 | Tier 2 High GIDA (Score 40.0–49.9) | 62.35 | 43.59 | 62.35 |  | F - Nearest node and line over 5 km | 29.43 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4253
5 | 254 | 4254 | 1705305014 | MIMAROPA Region | Palawan | Bataraza | Sandoval | 8.5948 | 117.4538 | R | 4111 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 189.65 | 191.94 | Tier 2 High GIDA (Score 40.0–49.9) | 62.35 | 43.59 | 62.35 |  | F - Nearest node and line over 5 km | 189.65 | 191.66 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4254
5 | 255 | 4255 | 0702252047 | Region VII (Central Visayas) | Cebu | Tuburan | Tomugpa | 10.6273 | 123.8921 | R | 293 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.97 | 10.84 | Tier 2 High GIDA (Score 40.0–49.9) | 62.35 | 43.59 | 62.35 |  | F - Nearest node and line over 5 km | 14.97 | 10.83 | Line: 104.3km-96FOC-toledo-san remigio | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4255
5 | 256 | 4256 | 0600402007 | Region VI (Western Visayas) | Aklan | Balete | Fulgencio | 11.5882 | 122.3687 | R | 3736 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.77 | 1.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.33 | 43.58 | 62.33 |  | D - Other node or line within 3 km | 2.77 | 1.22 | Line: IVISAN - KALIBO | Route options survey candidate: compare actual node lateral with approved line tap. | 4256
5 | 257 | 4257 | 1380609004 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 657 | 14.5893 | 120.9785 | U | 1012 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.61 | 40.29 | Tier 2 High GIDA (Score 40.0–49.9) | 62.33 | 43.57 | 62.33 |  | B - Node 0.5-1 km | 0.64 | 0.41 | Line: PSG001 RELIANCE TO NCC001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4257
5 | 258 | 4258 | 0600402006 | Region VI (Western Visayas) | Aklan | Balete | Feliciano | 11.5835 | 122.3572 | U | 2950 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.74 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 62.32 | 43.56 | 62.32 |  | C - Line within 0.5 km; node over 1 km | 2.74 | 0.03 | Line: IVISAN - KALIBO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4258
5 | 259 | 4259 | PH0004259 | VIII | Leyte | Tacloban City | El Reposo | 11.2459 | 125.0042 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.39 | 0.91 | Tier 2 High GIDA (Score 40.0–49.9) | 62.31 | 43.56 | 62.31 |  | B - Node 0.5-1 km | 0.72 | 3.75 | Node: TCL002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4259
5 | 260 | 4260 | 0405646008 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Cagascas | 14.0159 | 122.4652 | R | 181 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.35 | 2.25 | Tier 2 High GIDA (Score 40.0–49.9) | 62.31 | 43.56 | 62.31 |  | A - Node within 0.5 km | 0.49 | 0.02 | Line: GCQ001 TO TKQ001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4260
5 | 261 | 4261 | 1705205053 | MIMAROPA Region | Oriental Mindoro | City of Calapan | San Vicente South | 13.4106 | 121.1774 | U | 465 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 3.99 | Tier 2 High GIDA (Score 40.0–49.9) | 62.3 | 43.56 | 62.3 |  | D - Other node or line within 3 km | 2.38 | 3.97 | Node: CLM002 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4261
5 | 262 | 4262 | 1381200012 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Maybunga | 14.5786 | 121.0837 | U | 48385 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.3 | 43.56 | 62.3 |  | A - Node within 0.5 km | 0.31 | 0.15 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4262
5 | 263 | 4263 | 0405619031 | Region IV-A (CALABARZON) | Quezon | Gumaca | Mataas Na Bundok | 13.9151 | 122.1262 | R | 170 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.6 | 1.83 | Tier 2 High GIDA (Score 40.0–49.9) | 62.3 | 43.55 | 62.3 |  | C - Line within 0.5 km; node over 1 km | 2.17 | 0.02 | Line: LCQ001 TO LZQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4263
5 | 264 | 4264 | 0806409009 | Region VIII (Eastern Visayas) | Southern Leyte | Malitbog | Caraatan | 10.1141 | 124.9719 | R | 243 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.08 | 3.96 | Tier 2 High GIDA (Score 40.0–49.9) | 62.3 | 43.55 | 62.3 |  | F - Nearest node and line over 5 km | 15.76 | 8.14 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4264
5 | 265 | 4265 | 1906609024 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Alu Layag-Layag | 17.2554 | 122.2294 | R | 5473 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 2 High GIDA (Score 40.0–49.9) | 62.3 | 43.55 | 62.3 |  | F - Nearest node and line over 5 km | 29.5 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4265
5 | 266 | 4266 | PH0004266 | VII | Cebu | Cebu City | Basak Pardo | 10.2909 | 123.8656 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.87 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.29 | 43.55 | 62.29 |  | B - Node 0.5-1 km | 0.87 | 0.24 | Line: CEBU - TOLEDO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4266
5 | 267 | 4267 | 0501705010 | Region V (Bicol Region) | Camarines Sur | Buhi | Ipil | 13.453 | 123.5342 | R | 1529 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.64 | 4.89 | Tier 2 High GIDA (Score 40.0–49.9) | 62.29 | 43.55 | 62.29 |  | E - Nearest node or line 3-5 km | 4.64 | 9.94 | Node: BIC001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4267
5 | 268 | 4268 | 0405619011 | Region IV-A (CALABARZON) | Quezon | Gumaca | Bungahan | 13.8398 | 122.1587 | R | 221 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.7 | 2.4 | Tier 2 High GIDA (Score 40.0–49.9) | 62.28 | 43.54 | 62.28 |  | E - Nearest node or line 3-5 km | 7.12 | 3.85 | Line: AE UNQ001 TO CDQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4268
5 | 269 | 4269 | 1003521021 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Somiorang | 8.0118 | 124.0029 | R | 733 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.7 | 15.54 | Tier 2 High GIDA (Score 40.0–49.9) | 62.28 | 43.54 | 62.28 |  | F - Nearest node and line over 5 km | 22.7 | 15.53 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4269
5 | 270 | 4270 | 0907222011 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Jose Dalman | Labakid | 8.4506 | 123.0222 | R | 1218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.26 | 65.07 | Tier 2 High GIDA (Score 40.0–49.9) | 62.28 | 43.54 | 62.28 |  | F - Nearest node and line over 5 km | 67.93 | 71.68 | Node: SIA001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4270
5 | 271 | 4271 | PH0004271 | VIII | Leyte | Tacloban City | Barangay 54 | 11.2169 | 125.0033 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.14 | 8.54 | Tier 2 High GIDA (Score 40.0–49.9) | 62.28 | 43.54 | 62.28 |  | B - Node 0.5-1 km | 0.83 | 0.81 | Line: CAPOOCAN - TACLOBAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4271
5 | 272 | 4272 | PH0004272 | NCR | Metro Manila | Caloocan City | Barangay 187 | 14.7665 | 121.0607 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.29 | 1.93 | Tier 2 High GIDA (Score 40.0–49.9) | 62.27 | 43.53 | 62.27 |  | B - Node 0.5-1 km | 0.91 | 0.1 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4272
5 | 273 | 4273 | 1408106024 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Doña Loreta | 18.2178 | 121.3604 | R | 758 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.99 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 62.26 | 43.53 | 62.26 |  | D - Other node or line within 3 km | 2.29 | 14.92 | Node: PLY001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4273
5 | 274 | 4274 | 1381300030 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Dioquino Zobel | 14.6249 | 121.0696 | U | 1881 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.12 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 62.26 | 43.53 | 62.26 |  | A - Node within 0.5 km | 0.19 | 0.11 | Line: UG 144C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4274
5 | 275 | 4275 | 1001805006 | Region X (Northern Mindanao) | Camiguin | Sagay | Cuna | 9.1253 | 124.7446 | R | 896 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.64 | 15.79 | Tier 2 High GIDA (Score 40.0–49.9) | 62.26 | 43.52 | 62.26 |  | F - Nearest node and line over 5 km | 16.64 | 15.79 | Line: CDO - BUENAVISTA via GINGOOG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4275
5 | 276 | 4276 | 1705915008 | MIMAROPA Region | Romblon | Santa Fe | Mat-i | 12.187 | 121.9851 | R | 1249 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.88 | 6.36 | Tier 2 High GIDA (Score 40.0–49.9) | 62.25 | 43.52 | 62.25 |  | F - Nearest node and line over 5 km | 26.88 | 66.1 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4276
5 | 277 | 4277 | PH0004277 | IV-A | Cavite | Imus City | Poblacion IV-A (Pob.) | 14.4054 | 120.9271 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.88 | 1.63 | Tier 2 High GIDA (Score 40.0–49.9) | 62.25 | 43.52 | 62.25 |  | D - Other node or line within 3 km | 1.47 | 4.19 | Node: IMC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4277
5 | 278 | 4278 | 1903604055 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Bubong Raya | 17.2547 | 122.2288 | R | 421 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 62.25 | 43.52 | 62.25 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4278
5 | 279 | 4279 | 1903621038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Udalo | 17.2545 | 122.2285 | R | 1591 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.36 | 34.25 | Tier 2 High GIDA (Score 40.0–49.9) | 62.25 | 43.52 | 62.25 |  | F - Nearest node and line over 5 km | 29.36 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4279
5 | 280 | 4280 | PH0004280 | VI | Iloilo | Iloilo City | General Hughes-Montes | 10.7124 | 122.5861 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 2.14 | Tier 2 High GIDA (Score 40.0–49.9) | 62.24 | 43.51 | 62.24 |  | D - Other node or line within 3 km | 1.99 | 1.97 | Line: ROXAS - ILOILO | Route options survey candidate: compare actual node lateral with approved line tap. | 4280
5 | 281 | 4281 | 0405804037 | Region IV-A (CALABARZON) | Rizal | Binangonan | Layunan | 14.4695 | 121.1934 | U | 2465 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 62.24 | 43.51 | 62.24 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.03 | Line: TAYTAY TO SNL001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4281
5 | 282 | 4282 | 0501711046 | Region V (Bicol Region) | Camarines Sur | Caramoan | Tabiguian | 13.835 | 123.7952 | R | 1020 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10 | 36.49 | Tier 2 High GIDA (Score 40.0–49.9) | 62.23 | 43.51 | 62.23 |  | F - Nearest node and line over 5 km | 10 | 36.44 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4282
5 | 283 | 4283 | 1606812006 | Region XIII (Caraga) | Surigao del Sur | Lingig | Mahayahay | 8.0884 | 126.3919 | R | 2595 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.53 | 35.8 | Tier 2 High GIDA (Score 40.0–49.9) | 62.21 | 43.49 | 62.21 |  | F - Nearest node and line over 5 km | 36.53 | 35.76 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4283
5 | 284 | 4284 | 0402103065 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas III | 14.4074 | 120.993 | U | 39437 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.35 | 1.8 | Tier 2 High GIDA (Score 40.0–49.9) | 62.21 | 43.49 | 62.21 |  | D - Other node or line within 3 km | 2.11 | 3.07 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4284
5 | 285 | 4285 | 1402709005 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Mompolia | 16.8721 | 121.1447 | R | 1271 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.31 | 6.73 | Tier 2 High GIDA (Score 40.0–49.9) | 62.2 | 43.48 | 62.2 |  | E - Nearest node or line 3-5 km | 4.31 | 6.58 | Node: BEF002 - TYPE 4A | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4285
5 | 286 | 4286 | 0405801010 | Region IV-A (CALABARZON) | Rizal | Angono | San Pedro | 14.527 | 121.1594 | U | 1739 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.98 | 1.83 | Tier 2 High GIDA (Score 40.0–49.9) | 62.19 | 43.48 | 62.19 |  | B - Node 0.5-1 km | 0.51 | 0.5 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4286
5 | 287 | 4287 | 0401006037 | Region IV-A (CALABARZON) | Batangas | Bauan | San Roque | 13.7943 | 120.9851 | U | 6537 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.92 | 1.53 | Tier 2 High GIDA (Score 40.0–49.9) | 62.19 | 43.47 | 62.19 |  | D - Other node or line within 3 km | 1.92 | 1.51 | Line: UG BUN001 TO SSB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4287
5 | 288 | 4288 | 0702234009 | Region VII (Central Visayas) | Cebu | City of Naga | East Poblacion | 13.6176 | 123.184 | U | 415 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.69 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 62.18 | 43.47 | 62.18 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.27 | Line: PAGBILAO - NAGA (UG + Aerial) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4288
5 | 289 | 4289 | 0401033001 | Region IV-A (CALABARZON) | Batangas | Tingloy | Corona | 13.6308 | 120.9293 | R | 1033 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.5 | 13.83 | Tier 2 High GIDA (Score 40.0–49.9) | 62.18 | 43.47 | 62.18 |  | F - Nearest node and line over 5 km | 7.5 | 13.78 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4289
5 | 290 | 4290 | 0304928003 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Liwayway | 15.4435 | 121.0651 | R | 4402 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.07 | 0.09 | Tier 2 High GIDA (Score 40.0–49.9) | 62.17 | 43.46 | 62.17 |  | C - Line within 0.5 km; node over 1 km | 1.78 | 0.08 | Line: Untitled Path | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4290
5 | 291 | 4291 | PH0004291 | CAR | Benguet | Baguio City | Quirino Hill, East | 16.3898 | 120.5839 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.73 | 3.66 | Tier 2 High GIDA (Score 40.0–49.9) | 62.16 | 43.46 | 62.16 |  | D - Other node or line within 3 km | 1.95 | 0.55 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 4291
5 | 292 | 4292 | 0300804044 | Region III (Central Luzon) | Bataan | Dinalupihan | Aquino | 14.8618 | 120.4405 | R | 119 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 62.16 | 43.45 | 62.16 |  | C - Line within 0.5 km; node over 1 km | 1.82 | 0.06 | Line: Layac - Olongapo AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4292
5 | 293 | 4293 | 0600406018 | Region VI (Western Visayas) | Aklan | Ibajay | Mina-a | 11.6617 | 122.1776 | R | 730 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.69 | 12.09 | Tier 2 High GIDA (Score 40.0–49.9) | 62.15 | 43.45 | 62.15 |  | F - Nearest node and line over 5 km | 13.69 | 17.3 | Node: MLK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4293
5 | 294 | 4294 | PH0004294 | XI | Davao Del Sur | Davao City | Barangay 12-B (Pob.) | 7.0809 | 125.6125 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.42 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 62.15 | 43.45 | 62.15 |  | C - Line within 0.5 km; node over 1 km | 1.42 | 0.02 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4294
5 | 295 | 4295 | 0402118054 | Region IV-A (CALABARZON) | Cavite | Silang | Anahaw II | 14.1768 | 121.0058 | R | 3770 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.05 | 2.62 | Tier 2 High GIDA (Score 40.0–49.9) | 62.15 | 43.45 | 62.15 |  | A - Node within 0.5 km | 0.23 | 0.13 | Line: TGY001 TO CLB001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4295
5 | 296 | 4296 | 0401032005 | Region IV-A (CALABARZON) | Batangas | Taysan | Guinhawa | 13.7212 | 121.2628 | R | 1433 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.99 | 12.38 | Tier 2 High GIDA (Score 40.0–49.9) | 62.14 | 43.44 | 62.14 |  | F - Nearest node and line over 5 km | 6.99 | 12.38 | Node: TAB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4296
5 | 297 | 4297 | 1003521009 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Linao | 8.0449 | 123.9461 | R | 786 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.56 | 10.21 | Tier 2 High GIDA (Score 40.0–49.9) | 62.14 | 43.44 | 62.14 |  | F - Nearest node and line over 5 km | 16.18 | 9.17 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4297
5 | 298 | 4298 | 1704006003 | MIMAROPA Region | Marinduque | Torrijos | Bolo | 13.38 | 122.0938 | R | 443 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.55 | 31.85 | Tier 2 High GIDA (Score 40.0–49.9) | 62.14 | 43.44 | 62.14 |  | F - Nearest node and line over 5 km | 32.55 | 31.85 | Line: LZQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4298
5 | 299 | 4299 | 1381200029 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Ugong | 14.5791 | 121.0787 | U | 30522 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 62.13 | 43.44 | 62.13 |  | B - Node 0.5-1 km | 0.53 | 0.34 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4299
5 | 300 | 4300 | PH0004300 | IV-A | Cavite | Imus City | Carsadang Bago I | 14.4295 | 120.9278 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.84 | 2.93 | Tier 2 High GIDA (Score 40.0–49.9) | 62.13 | 43.44 | 62.13 |  | D - Other node or line within 3 km | 1.94 | 2.16 | Node: IMC002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4300
5 | 301 | 4301 | PH0004301 | IV-A | Cavite | Cavite City | Barangay 38-A | 14.4773 | 120.8928 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 5.17 | Tier 2 High GIDA (Score 40.0–49.9) | 62.12 | 43.43 | 62.12 |  | B - Node 0.5-1 km | 0.63 | 4.15 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4301
5 | 302 | 4302 | 1600303030 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Tandang Sora | 8.5765 | 125.7009 | R | 855 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.42 | 9.96 | Tier 2 High GIDA (Score 40.0–49.9) | 62.12 | 43.43 | 62.12 |  | F - Nearest node and line over 5 km | 16.42 | 9.96 | Line: FOC-96C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4302
5 | 303 | 4303 | PH0004303 | VIII | Samar (Western Samar) | Catbalogan City | Palanyogon | 11.8682 | 124.8642 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.29 | 32.15 | Tier 2 High GIDA (Score 40.0–49.9) | 62.11 | 43.42 | 62.11 |  | F - Nearest node and line over 5 km | 66.02 | 65.97 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4303
5 | 304 | 4304 | 0702252007 | Region VII (Central Visayas) | Cebu | Tuburan | Bangkito | 10.6015 | 123.8998 | R | 283 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.32 | 12.98 | Tier 2 High GIDA (Score 40.0–49.9) | 62.11 | 43.42 | 62.11 |  | F - Nearest node and line over 5 km | 13.32 | 12.97 | Line: BOGO - DANAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4304
5 | 305 | 4305 | 0201528029 | Region II (Cagayan Valley) | Cagayan | Tuao | Taribubu | 17.6043 | 121.5091 | R | 1697 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.39 | 8.35 | Tier 2 High GIDA (Score 40.0–49.9) | 62.1 | 43.41 | 62.1 |  | F - Nearest node and line over 5 km | 7.39 | 8.23 | Node: TUC002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4305
5 | 306 | 4306 | PH0004306 | XIII | Agusan Del Norte | Butuan City | Mandamo | 8.7608 | 125.6032 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.37 | 2.04 | Tier 2 High GIDA (Score 40.0–49.9) | 62.1 | 43.41 | 62.1 |  | D - Other node or line within 3 km | 12.37 | 1.92 | Line: FOC-96C | Route options survey candidate: compare actual node lateral with approved line tap. | 4306
5 | 307 | 4307 | 0804822009 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Deit De Turag | 12.3424 | 124.9094 | R | 610 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 93.53 | 92.93 | Tier 2 High GIDA (Score 40.0–49.9) | 62.1 | 43.41 | 62.1 |  | F - Nearest node and line over 5 km | 93.53 | 92.84 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4307
5 | 308 | 4308 | PH0004308 | III | Pampanga | Angeles City | Sta. Teresita | 15.1494 | 120.5999 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.79 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 62.09 | 43.41 | 62.09 |  | B - Node 0.5-1 km | 0.88 | 0.63 | Line: 80 CORE (8X10) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4308
5 | 309 | 4309 | 0401019007 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 2 | 14.0679 | 120.7338 | U | 1477 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.83 | 0.69 | Tier 2 High GIDA (Score 40.0–49.9) | 62.09 | 43.41 | 62.09 |  | C - Line within 0.5 km; node over 1 km | 2.1 | 0.11 | Line: ALFONSO - TUY | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4309
5 | 310 | 4310 | 1908708008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Northern Kabuntalan | Montay | 17.2537 | 122.2289 | R | 4773 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.86 | 32.76 | Tier 2 High GIDA (Score 40.0–49.9) | 62.09 | 43.41 | 62.09 |  | F - Nearest node and line over 5 km | 29.33 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4310
5 | 311 | 4311 | 0403404003 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banlic | 14.2316 | 121.1371 | U | 22631 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.45 | 2.4 | Tier 2 High GIDA (Score 40.0–49.9) | 62.09 | 43.4 | 62.09 |  | C - Line within 0.5 km; node over 1 km | 1.82 | 0.04 | Line: RELIANCE TO SAN PABLO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4311
5 | 312 | 4312 | PH0004312 | IV-A | Cavite | Imus City | Medicion II-C | 14.4623 | 120.978 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.4 | 2.56 | Tier 2 High GIDA (Score 40.0–49.9) | 62.08 | 43.4 | 62.08 |  | B - Node 0.5-1 km | 0.79 | 0.63 | Line: Aerial 216C MTF | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4312
5 | 313 | 4313 | 1907011001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Ambulong Sapal | 4.706 | 119.4929 | R | 2209 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.49 | 28.34 | Tier 2 High GIDA (Score 40.0–49.9) | 62.07 | 43.4 | 62.07 |  | F - Nearest node and line over 5 km | 376.27 | 376.27 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4313
5 | 314 | 4314 | 0804810012 | Region VIII (Eastern Visayas) | Northern Samar | Las Navas | Epaw | 12.27 | 125.0389 | R | 303 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 109.58 | 109.01 | Tier 2 High GIDA (Score 40.0–49.9) | 62.07 | 43.4 | 62.07 |  | F - Nearest node and line over 5 km | 109.58 | 108.92 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4314
5 | 315 | 4315 | 1408101012 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Tubang | 18.4368 | 121.1854 | R | 476 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.88 | 28.21 | Tier 2 High GIDA (Score 40.0–49.9) | 62.07 | 43.39 | 62.07 |  | F - Nearest node and line over 5 km | 14.54 | 13.76 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4315
5 | 316 | 4316 | PH0004316 | CAR | Benguet | Baguio City | DPS Area | 16.4142 | 120.578 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.29 | 0.74 | Tier 2 High GIDA (Score 40.0–49.9) | 62.06 | 43.39 | 62.06 |  | A - Node within 0.5 km | 0.1 | 0.09 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4316
5 | 317 | 4317 | 1907011010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Sibutu | 4.7071 | 119.4924 | R | 1211 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.76 | 29.39 | Tier 2 High GIDA (Score 40.0–49.9) | 62.06 | 43.39 | 62.06 |  | F - Nearest node and line over 5 km | 376.24 | 376.23 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4317
5 | 318 | 4318 | 0806022023 | Region VIII (Eastern Visayas) | Samar | Paranas | Paco | 11.7741 | 125.0213 | R | 247 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.85 | 77.83 | Tier 2 High GIDA (Score 40.0–49.9) | 62.06 | 43.39 | 62.06 |  | F - Nearest node and line over 5 km | 59.47 | 62.46 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4318
5 | 319 | 4319 | 1705320014 | MIMAROPA Region | Palawan | Taytay | Meytegued | 11.0283 | 119.5982 | R | 1162 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.3 | 24.91 | Tier 2 High GIDA (Score 40.0–49.9) | 62.05 | 43.38 | 62.05 |  | F - Nearest node and line over 5 km | 9.3 | 24.76 | Node: TYW003 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4319
5 | 320 | 4320 | 1381300087 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Quirino 2-C | 14.6897 | 121.0809 | U | 3323 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.45 | Tier 2 High GIDA (Score 40.0–49.9) | 62.05 | 43.38 | 62.05 |  | B - Node 0.5-1 km | 0.53 | 0.35 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4320
5 | 321 | 4321 | 1903631009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Marogong | Cahera | 17.2548 | 122.2289 | R | 935 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.41 | 34.3 | Tier 2 High GIDA (Score 40.0–49.9) | 62.05 | 43.38 | 62.05 |  | F - Nearest node and line over 5 km | 29.41 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4321
5 | 322 | 4322 | 0403403015 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Platero | 14.3205 | 121.0916 | U | 16227 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.64 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 62.04 | 43.38 | 62.04 |  | D - Other node or line within 3 km | 2.64 | 0.5 | Line: UG SPL001 TO CBL001 (STA ROSA CABUYAO BOUNDERY) | Route options survey candidate: compare actual node lateral with approved line tap. | 4322
5 | 323 | 4323 | 1606807002 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Babuyan | 9.3466 | 125.9 | R | 768 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.84 | 4.47 | Tier 2 High GIDA (Score 40.0–49.9) | 62.03 | 43.37 | 62.03 |  | E - Nearest node or line 3-5 km | 5.84 | 4.46 | Line: SURIGAO - CARASCAL | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4323
5 | 324 | 4324 | PH0004324 | IV-A | Quezon | Lucena City | Barangay 8 (Pob.) | 13.9301 | 121.6114 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.34 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 62.03 | 43.36 | 62.03 |  | A - Node within 0.5 km | 0.34 | 0.28 | Line: UG | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4324
5 | 325 | 4325 | 0102802046 | Region I (Ilocos Region) | Ilocos Norte | Bacarra | Santa Rita | 18.2513 | 120.6093 | R | 1136 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.14 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 62.01 | 43.35 | 62.01 |  | D - Other node or line within 3 km | 5.14 | 0.68 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 4325
5 | 326 | 4326 | PH0004326 | IV-A | Cavite | Cavite City | Barangay 10 | 14.48 | 120.8904 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.86 | 5.54 | Tier 2 High GIDA (Score 40.0–49.9) | 62.01 | 43.35 | 62.01 |  | B - Node 0.5-1 km | 0.65 | 4.54 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4326
5 | 327 | 4327 | 0600402011 | Region VI (Western Visayas) | Aklan | Balete | Poblacion | 11.5573 | 122.3783 | R | 899 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 62 | 43.35 | 62 |  | A - Node within 0.5 km | 0.31 | 0.22 | Line: IVISAN - KALIBO | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4327
5 | 328 | 4328 | PH0004328 | IV-A | Cavite | Cavite City | Barangay 60 | 14.4761 | 120.893 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.68 | 1.96 | Tier 2 High GIDA (Score 40.0–49.9) | 61.99 | 43.34 | 61.99 |  | B - Node 0.5-1 km | 0.61 | 4.03 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4328
5 | 329 | 4329 | 1906608006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pangutaran | Lantong Babag | 17.2553 | 122.2294 | R | 2410 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.49 | 34.36 | Tier 2 High GIDA (Score 40.0–49.9) | 61.99 | 43.34 | 61.99 |  | F - Nearest node and line over 5 km | 29.49 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4329
5 | 330 | 4330 | 0907215006 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Siayan | Domogok | 8.2779 | 123.1576 | R | 1494 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 58.59 | 48.86 | Tier 2 High GIDA (Score 40.0–49.9) | 61.99 | 43.34 | 61.99 |  | F - Nearest node and line over 5 km | 58.59 | 48.85 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4330
5 | 331 | 4331 | 0600609007 | Region VI (Western Visayas) | Antique | Laua-An | Capnayan | 11.0898 | 122.105 | R | 376 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.73 | 34.11 | Tier 2 High GIDA (Score 40.0–49.9) | 61.99 | 43.34 | 61.99 |  | F - Nearest node and line over 5 km | 40.73 | 33.77 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4331
5 | 332 | 4332 | 0402123023 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Ramon Cruz | 14.2832 | 121.0009 | U | 8083 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.09 | 4.91 | Tier 2 High GIDA (Score 40.0–49.9) | 61.99 | 43.33 | 61.99 |  | A - Node within 0.5 km | 0.15 | 3.87 | Node: MAC001 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4332
5 | 333 | 4333 | 0403425015 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Roque | 14.3665 | 121.0617 | U | 7850 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.87 | 5.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.98 | 43.33 | 61.98 |  | D - Other node or line within 3 km | 1.89 | 0.72 | Line: RELIANCE PSG001 TO BÑL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4333
5 | 334 | 4334 | PH0004334 | CAR | Benguet | Baguio City | Quirino Hill, Middle | 16.4302 | 120.5906 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.61 | 1.7 | Tier 2 High GIDA (Score 40.0–49.9) | 61.98 | 43.33 | 61.98 |  | B - Node 0.5-1 km | 0.61 | 1.69 | Node: BGC004 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4334
5 | 335 | 4335 | 0702207030 | Region VII (Central Visayas) | Cebu | Badian | Zaragosa | 9.882 | 123.3825 | R | 2105 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.44 | 1.94 | Tier 2 High GIDA (Score 40.0–49.9) | 61.98 | 43.33 | 61.98 |  | D - Other node or line within 3 km | 6.44 | 1.94 | Line: Segment 6 | Route options survey candidate: compare actual node lateral with approved line tap. | 4335
5 | 336 | 4336 | 1381200014 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Palatiw | 14.5646 | 121.083 | U | 29207 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.24 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 61.98 | 43.33 | 61.98 |  | A - Node within 0.5 km | 0.24 | 0.21 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4336
5 | 337 | 4337 | 1003515010 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Katubuan | 7.7826 | 123.888 | R | 881 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.56 | 18.18 | Tier 2 High GIDA (Score 40.0–49.9) | 61.96 | 43.32 | 61.96 |  | F - Nearest node and line over 5 km | 30.56 | 18.13 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4337
5 | 338 | 4338 | 1907011005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Hadji Taha | 17.2565 | 122.23 | R | 2008 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.81 | 29.69 | Tier 2 High GIDA (Score 40.0–49.9) | 61.95 | 43.31 | 61.95 |  | F - Nearest node and line over 5 km | 29.62 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4338
5 | 339 | 4339 | 0401019019 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Butucan | 14.1131 | 120.6743 | R | 2609 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.4 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 61.95 | 43.31 | 61.95 |  | C - Line within 0.5 km; node over 1 km | 6.4 | 0.1 | Line: SEGMENT 46 (MARAGONDON - NASUGBU) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4339
5 | 340 | 4340 | PH0004340 | IV-A | Quezon | Lucena City | Barangay 2 (Pob.) | 13.9384 | 121.616 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 61.95 | 43.31 | 61.95 |  | B - Node 0.5-1 km | 0.75 | 0.08 | Line: SAN JUAN TO UNISAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4340
5 | 341 | 4341 | 1404404004 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Bayyo | 17.0069 | 121.0165 | R | 323 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.69 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 61.95 | 43.31 | 61.95 |  | F - Nearest node and line over 5 km | 9.69 | 8.17 | Line: LA TRINIDAD-SAGADA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4341
5 | 342 | 4342 | 0604503001 | Region VI (Western Visayas) | Negros Occidental | Binalbagan | Amontay | 10.1286 | 123.0796 | R | 3162 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.89 | 15.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.94 | 43.3 | 61.94 |  | F - Nearest node and line over 5 km | 20.89 | 20.34 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4342
5 | 343 | 4343 | 1206502028 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | Columbio | Sucob | 6.6719 | 125.0279 | R | 1323 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.42 | 19.31 | Tier 2 High GIDA (Score 40.0–49.9) | 61.94 | 43.3 | 61.94 |  | F - Nearest node and line over 5 km | 16.42 | 19.31 | Node: MYD001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4343
5 | 344 | 4344 | PH0004344 | I | Ilocos Norte | Laoag City | Bgy. No. 3, Nstra. Sra. Del Rosario (Pob.) | 18.2012 | 120.6322 | R | 2233 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.84 | 1.25 | Tier 2 High GIDA (Score 40.0–49.9) | 61.93 | 43.29 | 61.93 |  | E - Nearest node or line 3-5 km | 4.97 | 3.31 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4344
5 | 345 | 4345 | PH0004345 | VIII | Leyte | Tacloban City | Barangay 36-A | 11.2595 | 124.9205 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.88 | 11.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.92 | 43.29 | 61.92 |  | F - Nearest node and line over 5 km | 9.21 | 7.94 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4345
5 | 346 | 4346 | PH0004346 | NIR | Negros Oriental | Dumaguete City | Poblacion No. 2 | 9.2983 | 123.3101 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 1.05 | Tier 2 High GIDA (Score 40.0–49.9) | 61.92 | 43.29 | 61.92 |  | D - Other node or line within 3 km | 1.05 | 0.72 | Line: KABANGKALAN - BACONG | Route options survey candidate: compare actual node lateral with approved line tap. | 4346
5 | 347 | 4347 | PH0004347 | CAR | Benguet | Baguio City | Dominican Hill-Mirador | 16.4066 | 120.5833 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.95 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.9 | 43.27 | 61.9 |  | B - Node 0.5-1 km | 0.95 | 0.06 | Line: SEGMENT 50 (BAUANG - BAGUIO) (BAGUIO PORTION) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4347
5 | 348 | 4348 | PH0004348 | IV-A | Cavite | City of Bacoor | P.F. Espiritu 1 | 14.4261 | 120.9747 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 1.7 | Tier 2 High GIDA (Score 40.0–49.9) | 61.9 | 43.27 | 61.9 |  | B - Node 0.5-1 km | 0.96 | 2.68 | Node: BRC006 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4348
5 | 349 | 4349 | 0300809010 | Region III (Central Luzon) | Bataan | Orani | Mulawin | 14.8052 | 120.5009 | R | 4958 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.94 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.89 | 43.27 | 61.89 |  | D - Other node or line within 3 km | 3.51 | 1.13 | Line: ORANI | Route options survey candidate: compare actual node lateral with approved line tap. | 4349
5 | 350 | 4350 | 0403405019 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lawa | 14.207 | 121.1453 | U | 13423 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 61.89 | 43.27 | 61.89 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.27 | Line: Untitled Path | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4350
5 | 351 | 4351 | 1903621023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Palao | 17.2545 | 122.2286 | R | 813 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.37 | 34.25 | Tier 2 High GIDA (Score 40.0–49.9) | 61.88 | 43.26 | 61.88 |  | F - Nearest node and line over 5 km | 29.37 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4351
5 | 352 | 4352 | PH0004352 | IV-A | Cavite | Cavite City | Barangay 11 | 14.4822 | 120.905 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.96 | 7.15 | Tier 2 High GIDA (Score 40.0–49.9) | 61.88 | 43.26 | 61.88 |  | D - Other node or line within 3 km | 2.05 | 4.03 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4352
5 | 353 | 4353 | 0501711004 | Region V (Bicol Region) | Camarines Sur | Caramoan | Bahay | 13.8104 | 123.8091 | R | 546 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.11 | 36.65 | Tier 2 High GIDA (Score 40.0–49.9) | 61.88 | 43.26 | 61.88 |  | F - Nearest node and line over 5 km | 7.11 | 36.62 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4353
5 | 354 | 4354 | PH0004354 | II | Nueva Vizcaya | Santa Fe N Vizcaya | Atbu | 16.1355 | 120.956 | R | 2464 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.24 | 6.7 | Tier 2 High GIDA (Score 40.0–49.9) | 61.85 | 43.24 | 61.85 |  | D - Other node or line within 3 km | 3.15 | 2.16 | Line: SEGMENT 16 (ARITAO - SAN JOSE) | Route options survey candidate: compare actual node lateral with approved line tap. | 4354
5 | 355 | 4355 | 0102803007 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Camanga | 17.9074 | 120.571 | R | 1231 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.6 | 8.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.85 | 43.24 | 61.85 |  | F - Nearest node and line over 5 km | 6.6 | 8.51 | Node: PNI001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4355
5 | 356 | 4356 | 1381300017 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Botocan | 14.0923 | 122.115 | U | 7816 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.38 | 1.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.84 | 43.23 | 61.84 |  | F - Nearest node and line over 5 km | 10.83 | 17.73 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4356
5 | 357 | 4357 | PH0004357 | IV-A | Cavite | Imus City | Toclong I-C | 14.4384 | 120.9322 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.54 | 2.07 | Tier 2 High GIDA (Score 40.0–49.9) | 61.83 | 43.23 | 61.83 |  | D - Other node or line within 3 km | 1.73 | 1.21 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4357
5 | 358 | 4358 | PH0004358 | IV-A | Laguna | San Pablo City | Barangay IV-A (Pob.) | 14.1022 | 121.3621 | R | 2412 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.43 | 1.45 | Tier 2 High GIDA (Score 40.0–49.9) | 61.83 | 43.23 | 61.83 |  | C - Line within 0.5 km; node over 1 km | 3.43 | 0 | Line: SPO001 TO LBQ001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4358
5 | 359 | 4359 | 0803708030 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Kabungaan | 10.5756 | 124.8901 | R | 865 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.06 | 6.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.83 | 43.22 | 61.83 |  | F - Nearest node and line over 5 km | 15.06 | 12.3 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4359
5 | 360 | 4360 | 1907011011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Talisay | 17.2558 | 122.2299 | R | 2013 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 61.82 | 43.22 | 61.82 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4360
5 | 361 | 4361 | PH0004361 | IV-A | Cavite | Imus City | Bayan Luma III | 14.4392 | 120.919 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.14 | 1.01 | Tier 2 High GIDA (Score 40.0–49.9) | 61.82 | 43.22 | 61.82 |  | D - Other node or line within 3 km | 3.05 | 0.75 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4361
5 | 362 | 4362 | 0802613007 | Region VIII (Eastern Visayas) | Eastern Samar | Llorente | Candoros | 11.3526 | 125.4586 | R | 574 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.3 | 50.53 | Tier 2 High GIDA (Score 40.0–49.9) | 61.81 | 43.21 | 61.81 |  | F - Nearest node and line over 5 km | 51.3 | 51.41 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4362
5 | 363 | 4363 | 1102506011 | Region XI (Davao Region) | Davao Oriental | Governor Generoso | Pundaguitan | 6.3768 | 126.1648 | R | 2544 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 60.17 | 56.1 | Tier 2 High GIDA (Score 40.0–49.9) | 61.81 | 43.21 | 61.81 |  | F - Nearest node and line over 5 km | 60.17 | 56.1 | Line: PANTUKAN - MATI SEGMENT 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4363
5 | 364 | 4364 | PH0004364 | VIII | Leyte | Tacloban City | Barangay 65 | 11.2383 | 124.9999 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.76 | 0.69 | Tier 2 High GIDA (Score 40.0–49.9) | 61.8 | 43.2 | 61.8 |  | A - Node within 0.5 km | 0.31 | 3.04 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4364
5 | 365 | 4365 | 1600309004 | Region XIII (Caraga) | Agusan del Sur | San Luis | Culi | 8.4983 | 125.7661 | R | 1144 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.52 | 19.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.8 | 43.2 | 61.8 |  | F - Nearest node and line over 5 km | 20.52 | 19.31 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4365
5 | 366 | 4366 | 0405631008 | Region IV-A (CALABARZON) | Quezon | Panukulan | Matangkap | 15.0306 | 121.8814 | R | 820 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.56 | 80.61 | Tier 2 High GIDA (Score 40.0–49.9) | 61.8 | 43.2 | 61.8 |  | F - Nearest node and line over 5 km | 38.56 | 80.61 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4366
5 | 367 | 4367 | 0806016021 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Jolacao | 12.0795 | 124.689 | R | 107 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.42 | 84.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.79 | 43.2 | 61.79 |  | F - Nearest node and line over 5 km | 86.7 | 86.42 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4367
5 | 368 | 4368 | 0806020022 | Region VIII (Eastern Visayas) | Samar | Tarangnan | Dapdap | 11.9462 | 124.7479 | R | 706 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 72.16 | 72.13 | Tier 2 High GIDA (Score 40.0–49.9) | 61.79 | 43.2 | 61.79 |  | F - Nearest node and line over 5 km | 72.16 | 72.13 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4368
5 | 369 | 4369 | 0402123026 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Severino De Las Alas | 14.2807 | 121.0165 | U | 8000 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.56 | 3.38 | Tier 2 High GIDA (Score 40.0–49.9) | 61.79 | 43.2 | 61.79 |  | D - Other node or line within 3 km | 1.57 | 4.94 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4369
5 | 370 | 4370 | 0403404013 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pulo | 14.2423 | 121.1318 | U | 38490 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.88 | 1.88 | Tier 2 High GIDA (Score 40.0–49.9) | 61.78 | 43.19 | 61.78 |  | B - Node 0.5-1 km | 0.5 | 0 | Line: AE SPL001-CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4370
5 | 371 | 4371 | 0702236001 | Region VII (Central Visayas) | Cebu | Pilar | Biasong | 10.7554 | 124.5176 | R | 415 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.84 | 8.62 | Tier 2 High GIDA (Score 40.0–49.9) | 61.78 | 43.19 | 61.78 |  | F - Nearest node and line over 5 km | 20.84 | 12.89 | Line: ORMOC - PALOMPON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4371
5 | 372 | 4372 | 1606722003 | Region XIII (Caraga) | Surigao del Norte | Sison | Gacepan | 9.6805 | 125.4926 | R | 488 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.96 | 1.97 | Tier 2 High GIDA (Score 40.0–49.9) | 61.77 | 43.18 | 61.77 |  | D - Other node or line within 3 km | 11.96 | 1.97 | Line: ALEGRIA - SURIGAO | Route options survey candidate: compare actual node lateral with approved line tap. | 4372
5 | 373 | 4373 | 0702232013 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward IV | 10.2539 | 123.7872 | U | 4414 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.55 | 1.17 | Tier 2 High GIDA (Score 40.0–49.9) | 61.77 | 43.18 | 61.77 |  | D - Other node or line within 3 km | 1.55 | 1.17 | Line: CEBU - TOLEDO | Route options survey candidate: compare actual node lateral with approved line tap. | 4373
5 | 374 | 4374 | 0600607015 | Region VI (Western Visayas) | Antique | Tobias Fornier | Danawan | 10.5826 | 121.9678 | R | 526 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.27 | 13.21 | Tier 2 High GIDA (Score 40.0–49.9) | 61.77 | 43.18 | 61.77 |  | F - Nearest node and line over 5 km | 20.25 | 5.68 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4374
5 | 375 | 4375 | 0601904003 | Region VI (Western Visayas) | Capiz | Dumarao | Aglanot | 11.2396 | 122.8401 | R | 1928 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.79 | 6.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.76 | 43.18 | 61.76 |  | F - Nearest node and line over 5 km | 6.79 | 6.5 | Line: SARA - PASSI | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4375
5 | 376 | 4376 | 1381300053 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Libis | 14.6169 | 121.0715 | U | 4385 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.1 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.76 | 43.17 | 61.76 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.3 | Line: UG 144C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4376
5 | 377 | 4377 | 1903614016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Madamba | Palao | 17.2546 | 122.2287 | R | 890 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.38 | 34.27 | Tier 2 High GIDA (Score 40.0–49.9) | 61.76 | 43.17 | 61.76 |  | F - Nearest node and line over 5 km | 29.38 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4377
5 | 378 | 4378 | 0301412004 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Banga | 14.7275 | 120.9607 | U | 2638 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.47 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.75 | 43.17 | 61.75 |  | C - Line within 0.5 km; node over 1 km | 1.47 | 0.05 | Line: Mnla Pipe | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4378
5 | 379 | 4379 | 1705318018 | MIMAROPA Region | Palawan | Roxas | Salvacion | 10.2148 | 119.2212 | R | 892 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.68 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.75 | 43.17 | 61.75 |  | C - Line within 0.5 km; node over 1 km | 17.68 | 0.06 | Line: TAYTAY - PUERTO PRINCESA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4379
5 | 380 | 4380 | PH0004380 | III | Nueva Ecija | Cabanatuan City | Bantug Bulalo | 15.4899 | 120.9758 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.82 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 61.75 | 43.17 | 61.75 |  | C - Line within 0.5 km; node over 1 km | 1.82 | 0.07 | Line: MULTINET - SANTA ROSA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4380
5 | 381 | 4381 | 1380700002 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Calumpang | 14.6222 | 121.0903 | U | 16124 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.71 | 0.82 | Tier 2 High GIDA (Score 40.0–49.9) | 61.75 | 43.17 | 61.75 |  | D - Other node or line within 3 km | 1.71 | 0.82 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4381
5 | 382 | 4382 | PH0004382 | XII | South Cotabato | General Santos City (Dadiangas) | Dadiangas West | 6.1097 | 125.169 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 1.04 | Tier 2 High GIDA (Score 40.0–49.9) | 61.75 | 43.17 | 61.75 |  | D - Other node or line within 3 km | 1.61 | 1.03 | Line: DAVAO CITY - GENSAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4382
5 | 383 | 4383 | 1381300093 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Saint Peter | 14.6627 | 121.0346 | U | 4219 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.9 | 0.74 | Tier 2 High GIDA (Score 40.0–49.9) | 61.74 | 43.16 | 61.74 |  | A - Node within 0.5 km | 0.25 | 0.4 | Node: QCY088 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4383
5 | 384 | 4384 | 1108209026 | Region XI (Davao Region) | Davao de Oro | Nabunturan | Tagnocon | 7.5149 | 126.0365 | R | 2988 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 24.62 | 12.5 | Tier 2 High GIDA (Score 40.0–49.9) | 61.74 | 43.16 | 61.74 |  | F - Nearest node and line over 5 km | 24.62 | 12.5 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4384
5 | 385 | 4385 | PH0004385 | IV-A | Cavite | Cavite City | Barangay 5 | 14.4705 | 120.8888 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.13 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.73 | 43.15 | 61.73 |  | A - Node within 0.5 km | 0.5 | 3.87 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4385
5 | 386 | 4386 | 1906609003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Bagsak | 17.2554 | 122.2294 | R | 2545 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 2 High GIDA (Score 40.0–49.9) | 61.73 | 43.15 | 61.73 |  | F - Nearest node and line over 5 km | 29.5 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4386
5 | 387 | 4387 | 1906613020 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Kiutaan | 17.256 | 122.229 | R | 2074 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.01 | 33.73 | Tier 2 High GIDA (Score 40.0–49.9) | 61.72 | 43.15 | 61.72 |  | F - Nearest node and line over 5 km | 29.5 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4387
5 | 388 | 4388 | 1381200027 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Santolan | 14.615 | 121.0823 | U | 61532 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.73 | 1.08 | Tier 2 High GIDA (Score 40.0–49.9) | 61.72 | 43.15 | 61.72 |  | B - Node 0.5-1 km | 0.73 | 1.07 | Node: PSG002 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4388
5 | 389 | 4389 | PH0004389 | IV-A | Cavite | City of Bacoor | P.F. Espiritu 3 | 14.4565 | 120.9558 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.11 | 1.08 | Tier 2 High GIDA (Score 40.0–49.9) | 61.71 | 43.14 | 61.71 |  | A - Node within 0.5 km | 0.31 | 0.23 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4389
5 | 390 | 4390 | 0401029029 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 5 | 13.8791 | 120.92 | R | 2093 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.99 | 0.7 | Tier 2 High GIDA (Score 40.0–49.9) | 61.71 | 43.14 | 61.71 |  | A - Node within 0.5 km | 0.49 | 1.87 | Node: TLB001 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4390
5 | 391 | 4391 | 1903607022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Butig | Dolangan | 17.2548 | 122.2288 | R | 921 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 61.7 | 43.14 | 61.7 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4391
5 | 392 | 4392 | 1380500005 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Ilaya | 14.5716 | 121.0447 | U | 24440 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.39 | 0.05 | Tier 2 High GIDA (Score 40.0–49.9) | 61.7 | 43.13 | 61.7 |  | C - Line within 0.5 km; node over 1 km | 1.39 | 0.02 | Line: UG 144C via W-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4392
5 | 393 | 4393 | 1380500022 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Plainview | 14.5782 | 121.0297 | U | 32148 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.63 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 61.68 | 43.12 | 61.68 |  | B - Node 0.5-1 km | 0.63 | 0.23 | Line: Aerial 216C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4393
5 | 394 | 4394 | 0804805028 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Liberty | 12.3627 | 124.6228 | R | 625 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.81 | 63.8 | Tier 2 High GIDA (Score 40.0–49.9) | 61.68 | 43.12 | 61.68 |  | F - Nearest node and line over 5 km | 63.81 | 63.78 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4394
5 | 395 | 4395 | 1381100195 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 195 | 14.5088 | 121.0007 | U | 2519 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.54 | 1.16 | Tier 2 High GIDA (Score 40.0–49.9) | 61.67 | 43.11 | 61.67 |  | B - Node 0.5-1 km | 0.89 | 0.12 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4395
5 | 396 | 4396 | 1906613023 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Kulamboh | 17.2552 | 122.2288 | R | 1802 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.36 | 35.17 | Tier 2 High GIDA (Score 40.0–49.9) | 61.66 | 43.11 | 61.66 |  | F - Nearest node and line over 5 km | 29.43 | 34.29 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4396
5 | 397 | 4397 | 0403405013 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Halang | 14.1978 | 121.1603 | U | 9407 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.52 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 61.66 | 43.1 | 61.66 |  | C - Line within 0.5 km; node over 1 km | 1.52 | 0.13 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4397
5 | 398 | 4398 | 1907011009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Sheik Makdum | 4.7244 | 119.497 | R | 3381 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 61.65 | 43.1 | 61.65 |  | F - Nearest node and line over 5 km | 374.6 | 374.6 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4398
5 | 399 | 4399 | 1381200015 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Pinagbuhatan | 14.5525 | 121.0995 | U | 173760 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.65 | 43.1 | 61.65 |  | C - Line within 0.5 km; node over 1 km | 1.33 | 0.09 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4399
5 | 400 | 4400 | 1401109004 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Palina | 16.7528 | 120.6998 | R | 1481 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 8.22 | Tier 2 High GIDA (Score 40.0–49.9) | 61.63 | 43.09 | 61.63 |  | B - Node 0.5-1 km | 0.66 | 8.19 | Node: KIB002 - PM | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4400
5 | 401 | 4401 | 1003511003 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Daan Campo | 8.9363 | 125.1892 | R | 780 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.97 | 10.35 | Tier 2 High GIDA (Score 40.0–49.9) | 61.63 | 43.09 | 61.63 |  | C - Line within 0.5 km; node over 1 km | 2.62 | 0.22 | Line: CDO - BUENAVISTA via GINGOOG | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4401
5 | 402 | 4402 | 1381200006 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Dela Paz | 14.615 | 121.0953 | U | 21034 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 61.62 | 43.08 | 61.62 |  | C - Line within 0.5 km; node over 1 km | 1.64 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4402
5 | 403 | 4403 | 1903633037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Buadiposo-Buntong | Lunduban | 17.2549 | 122.2279 | R | 374 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.85 | 33.58 | Tier 2 High GIDA (Score 40.0–49.9) | 61.62 | 43.08 | 61.62 |  | F - Nearest node and line over 5 km | 29.34 | 34.19 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4403
5 | 404 | 4404 | 1908712008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Talitay | Pageda | 17.2551 | 122.2291 | R | 4332 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 61.61 | 43.07 | 61.61 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4404
5 | 405 | 4405 | 0102820002 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Ildefonso | 18.1728 | 120.5946 | R | 1769 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.3 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 61.6 | 43.06 | 61.6 |  | A - Node within 0.5 km | 0.3 | 0.04 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4405
5 | 406 | 4406 | 1907011003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sibutu | Hadji Imam Bidin | 17.2559 | 122.2301 | R | 1486 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.19 | 27.99 | Tier 2 High GIDA (Score 40.0–49.9) | 61.59 | 43.06 | 61.59 |  | F - Nearest node and line over 5 km | 29.59 | 34.44 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4406
5 | 407 | 4407 | 0806019010 | Region VIII (Eastern Visayas) | Samar | Talalora | Tatabunan | 11.4955 | 124.8318 | R | 1124 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.73 | 26.38 | Tier 2 High GIDA (Score 40.0–49.9) | 61.58 | 43.05 | 61.58 |  | F - Nearest node and line over 5 km | 26.73 | 26.37 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4407
5 | 408 | 4408 | 0401019008 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 3 | 14.0892 | 120.7769 | U | 1150 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.44 | 2.96 | Tier 2 High GIDA (Score 40.0–49.9) | 61.58 | 43.05 | 61.58 |  | C - Line within 0.5 km; node over 1 km | 3.13 | 0.03 | Line: TGY001 TO NSB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4408
5 | 409 | 4409 | 1908709010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Landasan | 7.3406 | 124.2491 | U | 38559 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 62.32 | 58.09 | Tier 2 High GIDA (Score 40.0–49.9) | 61.58 | 43.05 | 61.58 |  | F - Nearest node and line over 5 km | 62.32 | 58.04 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4409
5 | 410 | 4410 | 0205009024 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Wangal | 16.3418 | 121.3914 | R | 1418 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.74 | 25.57 | Tier 2 High GIDA (Score 40.0–49.9) | 61.57 | 43.05 | 61.57 |  | F - Nearest node and line over 5 km | 10.74 | 25.55 | Node: KSV001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4410
5 | 411 | 4411 | 0405647005 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone III | 14.0654 | 121.6798 | R | 187 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.31 | 1.75 | Tier 2 High GIDA (Score 40.0–49.9) | 61.57 | 43.04 | 61.57 |  | F - Nearest node and line over 5 km | 10.4 | 9.57 | Line: SAN JUAN TO UNISAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4411
5 | 412 | 4412 | PH0004412 | VII | Cebu | Cebu City | Tejero | 10.3007 | 123.9066 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.82 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 61.57 | 43.04 | 61.57 |  | B - Node 0.5-1 km | 0.82 | 0.5 | Line: DANAO - CEBU | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4412
5 | 413 | 4413 | 1003521011 | Region X (Northern Mindanao) | Lanao del Norte | Tangcal | Lingco-an | 8.0435 | 123.9457 | R | 661 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.48 | 12.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.57 | 43.04 | 61.57 |  | F - Nearest node and line over 5 km | 16.14 | 9.27 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4413
5 | 414 | 4414 | 1381400012 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Pasadeña | 17.7234 | 120.4522 | U | 4695 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.04 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 61.57 | 43.04 | 61.57 |  | C - Line within 0.5 km; node over 1 km | 7.13 | 0.06 | Line: SEGMENT 3 (VIGAN - BATAC) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4414
5 | 415 | 4415 | 1003502003 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Angandog | 8.1066 | 124.1922 | R | 1597 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.04 | 3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.56 | 43.03 | 61.56 |  | D - Other node or line within 3 km | 14.04 | 2.85 | Line: 216f feeder iligan completed | Route options survey candidate: compare actual node lateral with approved line tap. | 4415
5 | 416 | 4416 | 0806013025 | Region VIII (Eastern Visayas) | Samar | Pinabacdao | San Isidro | 11.6007 | 124.968 | R | 393 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.33 | 43.41 | Tier 2 High GIDA (Score 40.0–49.9) | 61.56 | 43.03 | 61.56 |  | F - Nearest node and line over 5 km | 40.33 | 43.4 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4416
5 | 417 | 4417 | 1908816011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Pagalungan | Linandangan | 17.255 | 122.229 | R | 2770 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 61.55 | 43.03 | 61.55 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4417
5 | 418 | 4418 | 0701230013 | Region VII (Central Visayas) | Bohol | Loon | Bugho | 9.7937 | 123.8332 | R | 212 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.06 | 4.03 | Tier 2 High GIDA (Score 40.0–49.9) | 61.55 | 43.03 | 61.55 |  | E - Nearest node or line 3-5 km | 4.06 | 4 | Line: TAGBILARAN TO CARMEN VIA TUBIGON | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4418
5 | 419 | 4419 | 1381200011 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Manggahan | 14.6002 | 121.0949 | U | 93549 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.37 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 61.55 | 43.03 | 61.55 |  | A - Node within 0.5 km | 0.37 | 0.32 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4419
5 | 420 | 4420 | 1380609005 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 658 | 14.5879 | 120.9801 | U | 2172 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.6 | 49.82 | Tier 2 High GIDA (Score 40.0–49.9) | 61.54 | 43.03 | 61.54 |  | B - Node 0.5-1 km | 0.54 | 0.36 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4420
5 | 421 | 4421 | 1380500016 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Malamig | 14.5848 | 121.0376 | U | 13191 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.58 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 61.54 | 43.02 | 61.54 |  | A - Node within 0.5 km | 0.49 | 0.33 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4421
5 | 422 | 4422 | 0402103034 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay II | 14.4064 | 120.9641 | U | 12515 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.01 | 5.13 | Tier 2 High GIDA (Score 40.0–49.9) | 61.54 | 43.02 | 61.54 |  | D - Other node or line within 3 km | 1.44 | 4.5 | Node: IMC004 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4422
5 | 423 | 4423 | 1380700004 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Jesus De La Peña | 14.6353 | 121.09 | U | 10542 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.53 | 43.02 | 61.53 |  | A - Node within 0.5 km | 0.49 | 0.48 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4423
5 | 424 | 4424 | 1380900013 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tangos South | 14.6555 | 120.9582 | U | 18755 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.49 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 61.52 | 43.01 | 61.52 |  | B - Node 0.5-1 km | 0.51 | 1.52 | Node: MAL004 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4424
5 | 425 | 4425 | 1380300031 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Valenzuela | 14.5637 | 121.0476 | U | 2642 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.26 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 61.51 | 43 | 61.51 |  | C - Line within 0.5 km; node over 1 km | 2.06 | 0.46 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4425
5 | 426 | 4426 | 1907010018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Nunuk Likud Sikubong | 17.2566 | 122.2302 | R | 1007 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.6 | 4.82 | Tier 2 High GIDA (Score 40.0–49.9) | 61.5 | 43 | 61.5 |  | F - Nearest node and line over 5 km | 29.65 | 34.48 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4426
5 | 427 | 4427 | PH0004427 | XIII | Agusan Del Norte | Butuan City | Sikatuna Pob. | 8.9769 | 125.517 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.02 | 9.84 | Tier 2 High GIDA (Score 40.0–49.9) | 61.5 | 43 | 61.5 |  | E - Nearest node or line 3-5 km | 3.72 | 3.55 | Line: FOC 96C | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4427
5 | 428 | 4428 | 1906609006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Bukid | 17.2552 | 122.2287 | R | 1062 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.35 | 35.17 | Tier 2 High GIDA (Score 40.0–49.9) | 61.5 | 43 | 61.5 |  | F - Nearest node and line over 5 km | 29.43 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4428
5 | 429 | 4429 | PH0004429 | VIII | Samar (Western Samar) | Catbalogan City | Basiao | 11.6894 | 124.902 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.7 | 35.31 | Tier 2 High GIDA (Score 40.0–49.9) | 61.5 | 42.99 | 61.5 |  | F - Nearest node and line over 5 km | 49.12 | 49.02 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4429
5 | 430 | 4430 | 0802609026 | Region VIII (Eastern Visayas) | Eastern Samar | Guiuan | Inapulangan | 10.7731 | 125.6633 | R | 543 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 79.36 | 71.96 | Tier 2 High GIDA (Score 40.0–49.9) | 61.49 | 42.99 | 61.49 |  | F - Nearest node and line over 5 km | 79.36 | 84.89 | Node: TAL001-TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4430
5 | 431 | 4431 | 0403404002 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banaybanay | 14.254 | 121.1309 | U | 37555 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.86 | 9.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.49 | 42.99 | 61.49 |  | B - Node 0.5-1 km | 0.88 | 0.23 | Line: BÑL001 TO CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4431
5 | 432 | 4432 | 1907002019 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Montay Montay | 17.256 | 122.2306 | R | 1812 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.45 | 23.33 | Tier 2 High GIDA (Score 40.0–49.9) | 61.47 | 42.97 | 61.47 |  | F - Nearest node and line over 5 km | 29.64 | 34.5 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4432
5 | 433 | 4433 | 0301412003 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bancal | 14.7207 | 120.9618 | U | 13261 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.47 | 42.97 | 61.47 |  | C - Line within 0.5 km; node over 1 km | 1.35 | 0.3 | Line: GOTACO TO HH 71 BULACAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4433
5 | 434 | 4434 | 1381200007 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kalawaan | 14.5514 | 121.0837 | U | 34142 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.08 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.47 | 42.97 | 61.47 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.19 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4434
5 | 435 | 4435 | 1906618002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Bud Sibaud | 17.2556 | 122.2297 | R | 1484 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 61.46 | 42.97 | 61.46 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4435
5 | 436 | 4436 | 0401033007 | Region IV-A (CALABARZON) | Batangas | Tingloy | Pisa | 13.6342 | 120.9392 | R | 704 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.79 | 14.27 | Tier 2 High GIDA (Score 40.0–49.9) | 61.46 | 42.97 | 61.46 |  | F - Nearest node and line over 5 km | 7.79 | 14.2 | Node: MBN002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4436
5 | 437 | 4437 | 1906618011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Sibaud Proper | 17.2556 | 122.2297 | R | 1298 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 61.45 | 42.96 | 61.45 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4437
5 | 438 | 4438 | 1381200017 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Rosario | 14.5844 | 121.085 | U | 78574 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 61.45 | 42.96 | 61.45 |  | B - Node 0.5-1 km | 0.93 | 0.32 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4438
5 | 439 | 4439 | 0907303013 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Deporehan | 7.9579 | 123.0514 | R | 730 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.37 | 20.94 | Tier 2 High GIDA (Score 40.0–49.9) | 61.44 | 42.96 | 61.44 |  | F - Nearest node and line over 5 km | 25.37 | 20.91 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4439
5 | 440 | 4440 | 1903639002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Barao | 7.8849 | 123.7461 | R | 1036 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.88 | 33.61 | Tier 2 High GIDA (Score 40.0–49.9) | 61.44 | 42.95 | 61.44 |  | C - Line within 0.5 km; node over 1 km | 18.52 | 0.24 | Line: ILIGAN - PAGADIAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4440
5 | 441 | 4441 | 1381200009 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Kapitolyo | 14.5678 | 121.0631 | U | 9775 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 61.44 | 42.95 | 61.44 |  | C - Line within 0.5 km; node over 1 km | 1.61 | 0.48 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4441
5 | 442 | 4442 | PH0004442 | CAR | Benguet | Baguio City | Bayan Park Village | 16.3912 | 120.5936 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.33 | 1.2 | Tier 2 High GIDA (Score 40.0–49.9) | 61.43 | 42.95 | 61.43 |  | D - Other node or line within 3 km | 1.26 | 1.08 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 4442
5 | 443 | 4443 | 0806001027 | Region VIII (Eastern Visayas) | Samar | Almagro | Costa Rica II | 11.9312 | 124.3247 | R | 300 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.36 | 75.04 | Tier 2 High GIDA (Score 40.0–49.9) | 61.42 | 42.94 | 61.42 |  | F - Nearest node and line over 5 km | 45.64 | 74.51 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4443
5 | 444 | 4444 | PH0004444 | IV-A | Cavite | Imus City | Medicion I-C | 14.4348 | 120.9308 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.21 | 3.93 | Tier 2 High GIDA (Score 40.0–49.9) | 61.42 | 42.94 | 61.42 |  | D - Other node or line within 3 km | 1.69 | 1.63 | Line: PSG001 RELIANCE TO NCC001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4444
5 | 445 | 4445 | 0907216023 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sibuco | Culaguan | 7.2951 | 122.0988 | R | 479 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.85 | 17.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.42 | 42.94 | 61.42 |  | F - Nearest node and line over 5 km | 18.85 | 17.38 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4445
5 | 446 | 4446 | PH0004446 | III | Nueva Ecija | Cabanatuan City | Kapitan Pepe (Pob.) | 15.4878 | 120.9769 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.34 | 3.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.41 | 42.93 | 61.41 |  | C - Line within 0.5 km; node over 1 km | 1.82 | 0.24 | Line: MULTINET - SANTA ROSA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4446
5 | 447 | 4447 | 1380700009 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Santa Elena | 14.6312 | 121.0976 | U | 7651 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 61.41 | 42.93 | 61.41 |  | B - Node 0.5-1 km | 0.75 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4447
5 | 448 | 4448 | 0401019006 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 12 | 14.0499 | 120.6813 | R | 2376 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.38 | 0.82 | Tier 2 High GIDA (Score 40.0–49.9) | 61.41 | 42.93 | 61.41 |  | C - Line within 0.5 km; node over 1 km | 5.6 | 0 | Line: TGY001 TO NSB001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4448
5 | 449 | 4449 | PH0004449 | VII | Cebu | Cebu City | San Nicolas Central | 10.294 | 123.8903 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.22 | 0.46 | Tier 2 High GIDA (Score 40.0–49.9) | 61.4 | 42.92 | 61.4 |  | C - Line within 0.5 km; node over 1 km | 1.22 | 0.4 | Line: DANAO - CEBU | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4449
5 | 450 | 4450 | PH0004450 | VIII | Leyte | Tacloban City | Barangay 59-A | 11.3033 | 124.952 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13 | 15.94 | Tier 2 High GIDA (Score 40.0–49.9) | 61.4 | 42.92 | 61.4 |  | F - Nearest node and line over 5 km | 8.97 | 11.87 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4450
5 | 451 | 4451 | PH0004451 | NCR | Metro Manila | Caloocan City | Barangay 188 | 14.6483 | 120.9771 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 95.4 | 92.81 | Tier 2 High GIDA (Score 40.0–49.9) | 61.39 | 42.92 | 61.39 |  | A - Node within 0.5 km | 0.47 | 0.39 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4451
5 | 452 | 4452 | 1206302013 | Region XII (SOCCSKSARGEN) | South Cotabato | Banga | Lampari | 6.2907 | 124.8897 | R | 2769 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.93 | 10.59 | Tier 2 High GIDA (Score 40.0–49.9) | 61.39 | 42.92 | 61.39 |  | F - Nearest node and line over 5 km | 7.93 | 8.11 | Node: TIP001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4452
5 | 453 | 4453 | PH0004453 | VI | Capiz | Roxas City | Poblacion VII | 11.5825 | 122.7471 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.72 | 0.03 | Tier 2 High GIDA (Score 40.0–49.9) | 61.39 | 42.91 | 61.39 |  | B - Node 0.5-1 km | 0.72 | 0.02 | Line: ROXAS - IVISAN | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4453
5 | 454 | 4454 | 1906611009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Kabbon Takas | 17.2554 | 122.2295 | R | 1141 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 2 High GIDA (Score 40.0–49.9) | 61.38 | 42.91 | 61.38 |  | F - Nearest node and line over 5 km | 29.5 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4454
5 | 455 | 4455 | 1705308007 | MIMAROPA Region | Palawan | Cagayancillo | Mampio | 9.635 | 121.226 | R | 976 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 129.61 | 129.68 | Tier 2 High GIDA (Score 40.0–49.9) | 61.38 | 42.91 | 61.38 |  | F - Nearest node and line over 5 km | 129.61 | 129.68 | Node: SPN001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4455
5 | 456 | 4456 | PH0004456 | VIII | Leyte | Tacloban City | Libertad | 11.1961 | 125.0083 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.01 | 5.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.38 | 42.91 | 61.38 |  | C - Line within 0.5 km; node over 1 km | 1.83 | 0.31 | Line: CAPOOCAN - TACLOBAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4456
5 | 457 | 4457 | 1400115011 | Cordillera Administrative Region (CAR) | Abra | Malibcong | Taripan | 17.5747 | 121.0077 | R | 207 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.35 | 28.88 | Tier 2 High GIDA (Score 40.0–49.9) | 61.38 | 42.91 | 61.38 |  | F - Nearest node and line over 5 km | 35.35 | 28.71 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4457
5 | 458 | 4458 | 1906611016 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Patikul | Maligay | 17.2558 | 122.2287 | R | 1026 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.34 | 31.67 | Tier 2 High GIDA (Score 40.0–49.9) | 61.38 | 42.91 | 61.38 |  | F - Nearest node and line over 5 km | 29.47 | 34.3 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4458
5 | 459 | 4459 | 1705904004 | MIMAROPA Region | Romblon | Calatrava | Pagsangahan | 12.6003 | 122.0747 | R | 862 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.76 | 45.78 | Tier 2 High GIDA (Score 40.0–49.9) | 61.37 | 42.91 | 61.37 |  | F - Nearest node and line over 5 km | 56.76 | 56.79 | Node: RSM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4459
5 | 460 | 4460 | 0402111019 | Region IV-A (CALABARZON) | Cavite | Kawit | Samala-Marquez | 14.4487 | 120.9259 | U | 6789 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.54 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 61.37 | 42.9 | 61.37 |  | C - Line within 0.5 km; node over 1 km | 2.45 | 0.18 | Line: BACOOR | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4460
5 | 461 | 4461 | 1380400019 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Tinajeros | 14.6713 | 120.9699 | U | 18866 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.45 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 61.37 | 42.9 | 61.37 |  | A - Node within 0.5 km | 0.45 | 0.18 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4461
5 | 462 | 4462 | 0405802003 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dela Paz | 14.5975 | 121.1726 | U | 73910 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 61.36 | 42.9 | 61.36 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4462
5 | 463 | 4463 | PH0004463 | CAR | Benguet | Baguio City | Pinget | 16.4319 | 120.5835 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 1.45 | Tier 2 High GIDA (Score 40.0–49.9) | 61.36 | 42.9 | 61.36 |  | D - Other node or line within 3 km | 1.3 | 1.45 | Node: BGC004 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4463
5 | 464 | 4464 | 0600607020 | Region VI (Western Visayas) | Antique | Tobias Fornier | Igbangcal-A | 10.4987 | 121.9505 | R | 509 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.7 | 8.62 | Tier 2 High GIDA (Score 40.0–49.9) | 61.36 | 42.9 | 61.36 |  | F - Nearest node and line over 5 km | 29.34 | 12.05 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4464
5 | 465 | 4465 | 1380400001 | National Capital Region (NCR) | Third District (Not a Province) | City of Malabon | Acacia | 14.6675 | 120.9689 | U | 5082 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.23 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 61.36 | 42.89 | 61.36 |  | A - Node within 0.5 km | 0.23 | 0.18 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4465
5 | 466 | 4466 | 1380200014 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pamplona Tres | 14.4539 | 120.9794 | U | 35634 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.34 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 61.35 | 42.89 | 61.35 |  | C - Line within 0.5 km; node over 1 km | 1.34 | 0.3 | Line: Aerial 216C MTF | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4466
5 | 467 | 4467 | 1906612038 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Siasi | North Manta | 17.2558 | 122.2301 | R | 894 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.61 | 0.76 | Tier 2 High GIDA (Score 40.0–49.9) | 61.35 | 42.89 | 61.35 |  | F - Nearest node and line over 5 km | 29.58 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4467
5 | 468 | 4468 | 0601911022 | Region VI (Western Visayas) | Capiz | Pilar | San Silvestre | 11.4428 | 123.0425 | R | 824 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.02 | 4.74 | Tier 2 High GIDA (Score 40.0–49.9) | 61.35 | 42.89 | 61.35 |  | E - Nearest node or line 3-5 km | 6.02 | 4.74 | Line: ROXAS - SARA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4468
5 | 469 | 4469 | 1204712057 | Region XII (SOCCSKSARGEN) | Cotabato | Pikit | Talitay | 7.026 | 124.7058 | R | 2002 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.06 | 14.87 | Tier 2 High GIDA (Score 40.0–49.9) | 61.34 | 42.88 | 61.34 |  | F - Nearest node and line over 5 km | 22.06 | 14.77 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4469
5 | 470 | 4470 | 0907225006 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Godod | Guisapong | 8.0331 | 122.7759 | R | 622 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.21 | 25.15 | Tier 2 High GIDA (Score 40.0–49.9) | 61.34 | 42.88 | 61.34 |  | F - Nearest node and line over 5 km | 35.21 | 25.14 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4470
5 | 471 | 4471 | PH0004471 | IV-A | Cavite | Cavite City | Barangay 17 | 14.4827 | 120.9046 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.32 | 3.41 | Tier 2 High GIDA (Score 40.0–49.9) | 61.33 | 42.88 | 61.33 |  | D - Other node or line within 3 km | 2.04 | 4.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4471
5 | 472 | 4472 | 1606813011 | Region XIII (Caraga) | Surigao del Sur | Madrid | San Vicente | 9.2728 | 126.0052 | R | 766 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.27 | 4.11 | Tier 2 High GIDA (Score 40.0–49.9) | 61.33 | 42.88 | 61.33 |  | E - Nearest node or line 3-5 km | 12.27 | 4.11 | Line: Route | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4472
5 | 473 | 4473 | 1600303039 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Kinamaybay | 8.6011 | 125.9153 | R | 886 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.27 | Tier 2 High GIDA (Score 40.0–49.9) | 61.33 | 42.88 | 61.33 |  | B - Node 0.5-1 km | 0.88 | 0.27 | Line: TRENTO - BUENAVISTA CLS | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4473
5 | 474 | 4474 | 0203112027 | Region II (Cagayan Valley) | Isabela | Echague | Madadamian | 16.6319 | 121.8401 | R | 995 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.65 | 19.25 | Tier 2 High GIDA (Score 40.0–49.9) | 61.32 | 42.87 | 61.32 |  | F - Nearest node and line over 5 km | 14.65 | 19.25 | Node: JNI002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4474
5 | 475 | 4475 | PH0004475 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 3 | 11.7455 | 124.8762 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.91 | 30.67 | Tier 2 High GIDA (Score 40.0–49.9) | 61.31 | 42.86 | 61.31 |  | F - Nearest node and line over 5 km | 53.58 | 53.51 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4475
5 | 476 | 4476 | 0907318042 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Midsalip | Pili | 8.0762 | 123.1776 | R | 530 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.69 | 26.71 | Tier 2 High GIDA (Score 40.0–49.9) | 61.31 | 42.86 | 61.31 |  | F - Nearest node and line over 5 km | 39.69 | 26.7 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4476
5 | 477 | 4477 | 0402104017 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 6 | 14.2995 | 121.0572 | R | 767 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.22 | 1.1 | Tier 2 High GIDA (Score 40.0–49.9) | 61.3 | 42.86 | 61.3 |  | B - Node 0.5-1 km | 0.53 | 1.41 | Node: BNL003 - TYPE 4A | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4477
5 | 478 | 4478 | 0405607041 | Region IV-A (CALABARZON) | Quezon | Calauag | Kuyaoyao | 13.942 | 122.3394 | R | 425 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.31 | 7.13 | Tier 2 High GIDA (Score 40.0–49.9) | 61.3 | 42.86 | 61.3 |  | D - Other node or line within 3 km | 2.54 | 1.77 | Line: PP SEC001 TO LZQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4478
5 | 479 | 4479 | 1606819009 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Mabuhay | 17.1051 | 122.2743 | R | 821 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.55 | 37.63 | Tier 2 High GIDA (Score 40.0–49.9) | 61.3 | 42.85 | 61.3 |  | F - Nearest node and line over 5 km | 27.55 | 37.62 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4479
5 | 480 | 4480 | PH0004480 | II | Isabela | Ilagan City | Cabeseria 3 | 17.0559 | 121.9496 | R | 2276 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.3 | 8.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.27 | 42.83 | 61.27 |  | E - Nearest node or line 3-5 km | 4.3 | 8.47 | Node: IGI004 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4480
5 | 481 | 4481 | PH0004481 | VIII | Leyte | Tacloban City | Barangay 60 | 11.2365 | 125.0012 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.22 | 3.64 | Tier 2 High GIDA (Score 40.0–49.9) | 61.26 | 42.83 | 61.26 |  | A - Node within 0.5 km | 0.37 | 2.8 | Node: TCL002 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4481
5 | 482 | 4482 | PH0004482 | XI | Davao Del Sur | Davao City | Barangay 1-A (Pob.) | 7.0637 | 125.6074 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 61.26 | 42.83 | 61.26 |  | B - Node 0.5-1 km | 0.75 | 0.66 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4482
5 | 483 | 4483 | PH0004483 | CAR | Benguet | Baguio City | Santa Escolastica | 16.4018 | 120.6251 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.86 | 9.16 | Tier 2 High GIDA (Score 40.0–49.9) | 61.25 | 42.82 | 61.25 |  | D - Other node or line within 3 km | 2 | 1.12 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 4483
5 | 484 | 4484 | 0405631009 | Region IV-A (CALABARZON) | Quezon | Panukulan | Milawid | 14.9275 | 121.8447 | R | 741 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.28 | 68.96 | Tier 2 High GIDA (Score 40.0–49.9) | 61.25 | 42.82 | 61.25 |  | F - Nearest node and line over 5 km | 27.28 | 68.96 | Node: IFQ001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4484
5 | 485 | 4485 | 0502010014 | Region V (Bicol Region) | Catanduanes | Viga | Pedro Vera | 13.8108 | 124.2637 | R | 1577 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 43.41 | 73.97 | Tier 2 High GIDA (Score 40.0–49.9) | 61.24 | 42.81 | 61.24 |  | F - Nearest node and line over 5 km | 43.41 | 73.97 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4485
5 | 486 | 4486 | PH0004486 | IV-A | Cavite | Cavite City | Barangay 58-A | 14.4839 | 120.9044 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.3 | 7.21 | Tier 2 High GIDA (Score 40.0–49.9) | 61.24 | 42.81 | 61.24 |  | D - Other node or line within 3 km | 2.08 | 4.22 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4486
5 | 487 | 4487 | 0908310014 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Olutanga | Matim | 7.3189 | 122.8538 | R | 1033 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.8 | 37.04 | Tier 2 High GIDA (Score 40.0–49.9) | 61.23 | 42.81 | 61.23 |  | F - Nearest node and line over 5 km | 50.8 | 36.97 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4487
5 | 488 | 4488 | 1907005012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Tongusong | 17.2558 | 122.2299 | R | 3615 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 61.23 | 42.81 | 61.23 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4488
5 | 489 | 4489 | PH0004489 | VII | Cebu | Cebu City | Pahina Central (Pob.) | 10.2976 | 123.8924 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 61.23 | 42.81 | 61.23 |  | B - Node 0.5-1 km | 0.81 | 0.09 | Line: DANAO - CEBU | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4489
5 | 490 | 4490 | 0102805030 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Ricarte Pob. | 18.0632 | 120.5622 | U | 777 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.28 | 2.59 | Tier 2 High GIDA (Score 40.0–49.9) | 61.21 | 42.79 | 61.21 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.26 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4490
5 | 491 | 4491 | 0806015015 | Region VIII (Eastern Visayas) | Samar | San Sebastian | Hita-asan II | 11.6891 | 125.0501 | R | 421 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.99 | 52.97 | Tier 2 High GIDA (Score 40.0–49.9) | 61.21 | 42.79 | 61.21 |  | F - Nearest node and line over 5 km | 50.25 | 53.17 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4491
5 | 492 | 4492 | 1907005010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sitangkai | Tongmageng | 17.2558 | 122.2299 | R | 2639 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.57 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 61.2 | 42.78 | 61.2 |  | F - Nearest node and line over 5 km | 29.57 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4492
5 | 493 | 4493 | 0300809018 | Region III (Central Luzon) | Bataan | Orani | Silahis | 14.8184 | 120.5172 | R | 609 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.53 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.2 | 42.78 | 61.2 |  | C - Line within 0.5 km; node over 1 km | 2.74 | 0.01 | Line: Dinalupian to Orion | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4493
5 | 494 | 4494 | 1381300090 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Roxas | 14.628 | 121.0226 | U | 11118 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 1.14 | Tier 2 High GIDA (Score 40.0–49.9) | 61.19 | 42.78 | 61.19 |  | D - Other node or line within 3 km | 1.27 | 1.08 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 4494
5 | 495 | 4495 | 0603040004 | Region VI (Western Visayas) | Iloilo | San Joaquin | Bad-as | 10.7054 | 122.0882 | R | 268 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.59 | 11.62 | Tier 2 High GIDA (Score 40.0–49.9) | 61.19 | 42.78 | 61.19 |  | F - Nearest node and line over 5 km | 17.59 | 11.62 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4495
5 | 496 | 4496 | 0205006019 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Villa Florentino | 16.6316 | 121.4306 | R | 738 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.29 | 2.51 | Tier 2 High GIDA (Score 40.0–49.9) | 61.19 | 42.78 | 61.19 |  | D - Other node or line within 3 km | 7.29 | 2.51 | Line: SEGMENT 13 (SANTIAGO - BAYOMBONG) | Route options survey candidate: compare actual node lateral with approved line tap. | 4496
5 | 497 | 4497 | 0102906041 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Pedro | 17.2125 | 120.4082 | R | 731 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.94 | Tier 2 High GIDA (Score 40.0–49.9) | 61.17 | 42.76 | 61.17 |  | E - Nearest node or line 3-5 km | 4.69 | 4.65 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4497
5 | 498 | 4498 | 1400102001 | Cordillera Administrative Region (CAR) | Abra | Boliney | Amti | 17.3905 | 120.9027 | R | 452 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.06 | 27.49 | Tier 2 High GIDA (Score 40.0–49.9) | 61.17 | 42.76 | 61.17 |  | F - Nearest node and line over 5 km | 29.06 | 27.34 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4498
5 | 499 | 4499 | 1108604002 | Region XI (Davao Region) | Davao Occidental | Santa Maria | Buca | 6.4618 | 125.4786 | R | 2611 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.25 | 14.52 | Tier 2 High GIDA (Score 40.0–49.9) | 61.16 | 42.75 | 61.16 |  | F - Nearest node and line over 5 km | 16.25 | 14.47 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4499
5 | 500 | 4500 | 1908710017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Katidtuan | 17.2545 | 122.2275 | R | 2978 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 61.15 | 42.75 | 61.15 |  | F - Nearest node and line over 5 km | 29.28 | 34.14 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4500
5 | 501 | 4501 | PH0004501 | IV-A | Cavite | Cavite City | Barangay 34 | 14.4811 | 120.8929 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.5 | 0.56 | Tier 2 High GIDA (Score 40.0–49.9) | 61.15 | 42.75 | 61.15 |  | B - Node 0.5-1 km | 0.9 | 4.48 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4501
5 | 502 | 4502 | PH0004502 | IV-A | Cavite | Cavite City | Barangay 42-A | 14.493 | 120.9071 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.08 | 6.65 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.75 | 61.14 |  | D - Other node or line within 3 km | 2.92 | 5.1 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4502
5 | 503 | 4503 | PH0004503 | IV-A | Cavite | Cavite City | Barangay 37-A | 14.4927 | 120.9049 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.13 | 5.21 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.74 | 61.14 |  | D - Other node or line within 3 km | 2.73 | 5.14 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4503
5 | 504 | 4504 | 1381100197 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 197 | 14.5074 | 121.0013 | U | 3964 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.86 | 10.23 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.74 | 61.14 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4504
5 | 505 | 4505 | 0803710071 | Region VIII (Eastern Visayas) | Leyte | Burauen | Villa Aurora | 10.9196 | 124.8034 | R | 625 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.84 | 10.29 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.74 | 61.14 |  | F - Nearest node and line over 5 km | 10.69 | 10.16 | Line: ORMOC - BAYBAY | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4505
5 | 506 | 4506 | 0401029033 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 9 | 13.8837 | 120.922 | R | 860 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.74 | 61.14 |  | D - Other node or line within 3 km | 1.04 | 1.33 | Node: TLB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4506
5 | 507 | 4507 | 0600607021 | Region VI (Western Visayas) | Antique | Tobias Fornier | Igbangcal-B | 10.4846 | 121.924 | R | 565 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.43 | 14.24 | Tier 2 High GIDA (Score 40.0–49.9) | 61.14 | 42.74 | 61.14 |  | F - Nearest node and line over 5 km | 30.92 | 15.21 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4507
5 | 508 | 4508 | 1404401012 | Cordillera Administrative Region (CAR) | Mountain Province | Barlig | Lias Silangan | 17.0841 | 121.1437 | R | 354 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.01 | 10.83 | Tier 2 High GIDA (Score 40.0–49.9) | 61.13 | 42.74 | 61.13 |  | F - Nearest node and line over 5 km | 14.01 | 10.75 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4508
5 | 509 | 4509 | PH0004509 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 4 | 11.7505 | 124.8716 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.59 | 34.45 | Tier 2 High GIDA (Score 40.0–49.9) | 61.13 | 42.74 | 61.13 |  | F - Nearest node and line over 5 km | 53.9 | 53.84 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4509
5 | 510 | 4510 | 1003515001 | Region X (Northern Mindanao) | Lanao del Norte | Nunungan | Abaga | 7.7976 | 123.9235 | R | 550 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.83 | 16.46 | Tier 2 High GIDA (Score 40.0–49.9) | 61.13 | 42.73 | 61.13 |  | F - Nearest node and line over 5 km | 30.53 | 20.3 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4510
5 | 511 | 4511 | 1907002014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Luuk Pandan | 17.2558 | 122.23 | R | 3101 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.74 | 24.78 | Tier 2 High GIDA (Score 40.0–49.9) | 61.12 | 42.73 | 61.12 |  | F - Nearest node and line over 5 km | 29.57 | 34.43 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4511
5 | 512 | 4512 | 1004208027 | Region X (Northern Mindanao) | Misamis Occidental | Lopez Jaena | Don Andres Soriano | 8.4727 | 123.6688 | R | 309 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 49.89 | 45.75 | Tier 2 High GIDA (Score 40.0–49.9) | 61.11 | 42.72 | 61.11 |  | F - Nearest node and line over 5 km | 49.89 | 45.73 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4512
5 | 513 | 4513 | 1908814007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Mangudadatu | Tinambulan | 17.255 | 122.2285 | R | 2730 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.59 | Tier 2 High GIDA (Score 40.0–49.9) | 61.1 | 42.72 | 61.1 |  | F - Nearest node and line over 5 km | 29.4 | 34.26 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4513
5 | 514 | 4514 | 0402106078 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño II | 14.3389 | 121.0218 | R | 2881 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.29 | 5.84 | Tier 2 High GIDA (Score 40.0–49.9) | 61.1 | 42.71 | 61.1 |  | D - Other node or line within 3 km | 2.08 | 1.81 | Line: AE SPL002 TO SPL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4514
5 | 515 | 4515 | 1908706005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Kabuntalan | Ganta | 7.1011 | 124.4325 | R | 2917 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.3 | 34.2 | Tier 2 High GIDA (Score 40.0–49.9) | 61.1 | 42.71 | 61.1 |  | F - Nearest node and line over 5 km | 41.75 | 41.12 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4515
5 | 516 | 4516 | PH0004516 | XIII | Surigao Del Norte | Surigao City | Baybay | 9.7571 | 125.5142 | R | 2328 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.04 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 61.09 | 42.71 | 61.09 |  | C - Line within 0.5 km; node over 1 km | 4.04 | 0.05 | Line: SURIGAO - CARASCAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4516
5 | 517 | 4517 | 1402708010 | Cordillera Administrative Region (CAR) | Ifugao | Aguinaldo | Majlong | 16.9639 | 121.3138 | R | 532 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.32 | 27.35 | Tier 2 High GIDA (Score 40.0–49.9) | 61.07 | 42.7 | 61.07 |  | D - Other node or line within 3 km | 2.32 | 27.27 | Node: AOF001-PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4517
5 | 518 | 4518 | 1381300054 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Lourdes | 14.6298 | 120.9993 | U | 4713 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.6 | Tier 2 High GIDA (Score 40.0–49.9) | 61.07 | 42.7 | 61.07 |  | B - Node 0.5-1 km | 0.93 | 0.38 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4518
5 | 519 | 4519 | PH0004519 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 2 | 11.7779 | 124.8807 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.49 | 33.09 | Tier 2 High GIDA (Score 40.0–49.9) | 61.06 | 42.68 | 61.06 |  | F - Nearest node and line over 5 km | 57.11 | 57.04 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4519
5 | 520 | 4520 | 0702244011 | Region VII (Central Visayas) | Cebu | Santa Fe | Talisay | 11.1659 | 123.8052 | U | 3232 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.96 | 5.41 | Tier 2 High GIDA (Score 40.0–49.9) | 61.05 | 42.68 | 61.05 |  | F - Nearest node and line over 5 km | 17.36 | 15.45 | Line: 10742 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4520
5 | 521 | 4521 | 1908813007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Mamasapano | Lusay | 17.2552 | 122.2293 | R | 1000 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.35 | Tier 2 High GIDA (Score 40.0–49.9) | 61.04 | 42.67 | 61.04 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4521
5 | 522 | 4522 | PH0004522 | II | Isabela | Ilagan City | Salindingan | 17.071 | 121.9088 | R | 2276 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.17 | 5.35 | Tier 2 High GIDA (Score 40.0–49.9) | 61.04 | 42.67 | 61.04 |  | F - Nearest node and line over 5 km | 6.17 | 5.35 | Line: SEGMENT 10 (TUGUEGARAO - ILIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4522
5 | 523 | 4523 | 1408104011 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Lenneng | 17.9235 | 121.2147 | R | 2618 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.25 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 61.04 | 42.67 | 61.04 |  | F - Nearest node and line over 5 km | 11.25 | 18.19 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4523
5 | 524 | 4524 | PH0004524 | VII | Cebu | Cebu City | Sawang Calero (Pob.) | 10.2907 | 123.8909 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 0.81 | Tier 2 High GIDA (Score 40.0–49.9) | 61.03 | 42.67 | 61.03 |  | D - Other node or line within 3 km | 1.43 | 0.77 | Line: DANAO - CEBU | Route options survey candidate: compare actual node lateral with approved line tap. | 4524
5 | 525 | 4525 | 1906604007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Luuk | Kan-Bulak | 17.2555 | 122.2296 | R | 2403 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.03 | 42.67 | 61.03 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4525
5 | 526 | 4526 | 1906617003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Bas Lugus | 17.2555 | 122.2295 | R | 1174 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 61.03 | 42.66 | 61.03 |  | F - Nearest node and line over 5 km | 29.51 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4526
5 | 527 | 4527 | 0405813002 | Region IV-A (CALABARZON) | Rizal | Taytay | Muzon | 14.5432 | 121.1444 | U | 32623 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.97 | 0.03 | Tier 2 High GIDA (Score 40.0–49.9) | 61.02 | 42.66 | 61.02 |  | C - Line within 0.5 km; node over 1 km | 1.97 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4527
5 | 528 | 4528 | PH0004528 | IV-A | Quezon | Lucena City | Barangay 1 (Pob.) | 13.9391 | 121.6107 | R | 1964 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.66 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 61.01 | 42.65 | 61.01 |  | B - Node 0.5-1 km | 0.66 | 0.06 | Line: BCY001 TO LCQ001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4528
5 | 529 | 4529 | 1906618014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pandami | Suba-suba | 17.2556 | 122.2297 | R | 2477 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 61.01 | 42.65 | 61.01 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4529
5 | 530 | 4530 | 1381600014 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Lingunan | 14.7201 | 120.9757 | U | 24431 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.13 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 61 | 42.64 | 61 |  | C - Line within 0.5 km; node over 1 km | 2.13 | 0.42 | Line: Existing MTF | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4530
5 | 531 | 4531 | PH0004531 | XI | Davao Del Sur | Davao City | San Antonio | 7.1411 | 125.6249 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.45 | 1.32 | Tier 2 High GIDA (Score 40.0–49.9) | 61 | 42.64 | 61 |  | D - Other node or line within 3 km | 2.31 | 1.95 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 4531
5 | 532 | 4532 | 1381600023 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Paso De Blas | 14.7054 | 120.9911 | U | 12709 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.32 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 61 | 42.64 | 61 |  | C - Line within 0.5 km; node over 1 km | 1.32 | 0.14 | Line: UG 288C via Brown Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4532
5 | 533 | 4533 | 1380300009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Makati | Guadalupe Nuevo | 14.5644 | 121.0479 | U | 10102 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.04 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 60.99 | 42.64 | 60.99 |  | C - Line within 0.5 km; node over 1 km | 2.04 | 0.38 | Line: UG 144C via V-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4533
5 | 534 | 4534 | PH0004534 | IV-B | Palawan | Puerto Princesa City | Marufinas | 10.2408 | 118.9566 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.1 | 27.3 | Tier 2 High GIDA (Score 40.0–49.9) | 60.99 | 42.64 | 60.99 |  | F - Nearest node and line over 5 km | 28.1 | 27.27 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4534
5 | 535 | 4535 | 0403428004 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dila | 14.2895 | 121.1091 | U | 43294 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.85 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.98 | 42.63 | 60.98 |  | B - Node 0.5-1 km | 0.85 | 0.03 | Line: RELIANCE TO SAN PABLO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4535
5 | 536 | 4536 | 1381100196 | National Capital Region (NCR) | Fourth District (Not a Province) | Pasay City | Barangay 196 | 14.5081 | 121.0027 | U | 1542 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.92 | 5.06 | Tier 2 High GIDA (Score 40.0–49.9) | 60.98 | 42.63 | 60.98 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.11 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4536
5 | 537 | 4537 | 1380500020 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Old Zañiga | 14.5865 | 121.0247 | U | 7262 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 60.98 | 42.63 | 60.98 |  | A - Node within 0.5 km | 0.48 | 0.37 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4537
5 | 538 | 4538 | 1004212027 | Region X (Northern Mindanao) | Misamis Occidental | Plaridel | Quirino | 8.5314 | 123.6743 | R | 394 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 56.02 | 47.05 | Tier 2 High GIDA (Score 40.0–49.9) | 60.98 | 42.63 | 60.98 |  | F - Nearest node and line over 5 km | 56.02 | 51.49 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4538
5 | 539 | 4539 | 1705320022 | MIMAROPA Region | Palawan | Taytay | San Jose | 10.9309 | 119.2518 | R | 2951 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.13 | 29.79 | Tier 2 High GIDA (Score 40.0–49.9) | 60.96 | 42.62 | 60.96 |  | F - Nearest node and line over 5 km | 19.13 | 29.79 | Node: TYW006 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4539
5 | 540 | 4540 | PH0004540 | XI | Davao Del Sur | Davao City | Barangay 17-B (Pob.) | 7.4529 | 125.5465 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.57 | 2.95 | Tier 2 High GIDA (Score 40.0–49.9) | 60.96 | 42.61 | 60.96 |  | F - Nearest node and line over 5 km | 20.83 | 20.37 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4540
5 | 541 | 4541 | PH0004541 | NCR | Metro Manila | Caloocan City | Barangay 158 | 14.6266 | 120.9762 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.49 | 13.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.95 | 42.61 | 60.95 |  | A - Node within 0.5 km | 0.31 | 0.01 | Line: UG 144C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4541
5 | 542 | 4542 | 0806017034 | Region VIII (Eastern Visayas) | Samar | Santa Rita | Union | 11.463 | 125.057 | R | 2533 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.54 | 28.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.95 | 42.61 | 60.95 |  | F - Nearest node and line over 5 km | 25.54 | 28.33 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4542
5 | 543 | 4543 | 0403404018 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Dos | 14.2767 | 121.1268 | U | 1724 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 0.67 | Tier 2 High GIDA (Score 40.0–49.9) | 60.95 | 42.61 | 60.95 |  | D - Other node or line within 3 km | 1.96 | 0.72 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 4543
5 | 544 | 4544 | 0405605031 | Region IV-A (CALABARZON) | Quezon | Buenavista | San Isidro Ibaba | 13.7453 | 122.4308 | R | 409 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3 | 2.19 | Tier 2 High GIDA (Score 40.0–49.9) | 60.94 | 42.61 | 60.94 |  | D - Other node or line within 3 km | 3 | 2.14 | Line: LZQ001 TO MCQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4544
5 | 545 | 4545 | 1381300061 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Mariblo | 14.0923 | 122.115 | U | 3577 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.96 | 0.19 | Tier 2 High GIDA (Score 40.0–49.9) | 60.94 | 42.6 | 60.94 |  | F - Nearest node and line over 5 km | 10.83 | 17.73 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4545
5 | 546 | 4546 | 0301409006 | Region III (Central Luzon) | Bulacan | Hagonoy | Pugad | 14.7679 | 120.7432 | R | 1710 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.98 | 10.37 | Tier 2 High GIDA (Score 40.0–49.9) | 60.94 | 42.6 | 60.94 |  | F - Nearest node and line over 5 km | 7.98 | 12.23 | Node: HGB001 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4546
5 | 547 | 4547 | 1908702014 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Buldon | Piers | 17.2539 | 122.2279 | R | 3123 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.27 | 34.17 | Tier 2 High GIDA (Score 40.0–49.9) | 60.93 | 42.6 | 60.93 |  | F - Nearest node and line over 5 km | 29.27 | 34.16 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4547
5 | 548 | 4548 | 0502006018 | Region V (Bicol Region) | Catanduanes | Pandan | Panuto | 14.0024 | 124.1704 | R | 388 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 41.73 | 80.18 | Tier 2 High GIDA (Score 40.0–49.9) | 60.93 | 42.6 | 60.93 |  | F - Nearest node and line over 5 km | 41.73 | 80.17 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4548
5 | 549 | 4549 | 0803739026 | Region VIII (Eastern Visayas) | Leyte | Palo | San Agustin | 11.1275 | 124.9371 | R | 1190 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.34 | 5.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.92 | 42.59 | 60.92 |  | F - Nearest node and line over 5 km | 7.34 | 5.43 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4549
5 | 550 | 4550 | 0504113007 | Region V (Bicol Region) | Masbate | Mobo | Guintorelan | 12.2488 | 123.6078 | R | 420 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.16 | 7.39 | Tier 2 High GIDA (Score 40.0–49.9) | 60.91 | 42.58 | 60.91 |  | F - Nearest node and line over 5 km | 11.16 | 7.38 | Line: MASBATE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4550
5 | 551 | 4551 | PH0004551 | VII | Cebu | Cebu City | Ermita (Pob.) | 10.325 | 123.8992 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.18 | 3.41 | Tier 2 High GIDA (Score 40.0–49.9) | 60.9 | 42.58 | 60.9 |  | B - Node 0.5-1 km | 0.66 | 1.88 | Node: CCY003 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4551
5 | 552 | 4552 | PH0004552 | VII | Cebu | Cebu City | Central (Pob.) | 10.4562 | 123.9183 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.24 | 3.23 | Tier 2 High GIDA (Score 40.0–49.9) | 60.9 | 42.58 | 60.9 |  | E - Nearest node or line 3-5 km | 4.51 | 6.03 | Node: CCY006 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4552
5 | 553 | 4553 | 1004208021 | Region X (Northern Mindanao) | Misamis Occidental | Lopez Jaena | Peniel | 8.4162 | 123.6498 | R | 164 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 44.64 | 41.17 | Tier 2 High GIDA (Score 40.0–49.9) | 60.9 | 42.58 | 60.9 |  | F - Nearest node and line over 5 km | 44.64 | 41.16 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4553
5 | 554 | 4554 | PH0004554 | XI | Davao Del Sur | Davao City | Kap. Tomas Monteverde, Sr. | 7.1338 | 125.5424 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.42 | 4.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.9 | 42.57 | 60.9 |  | F - Nearest node and line over 5 km | 5.02 | 6.37 | Node: DCD014 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4554
5 | 555 | 4555 | 1906616003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Panglima Estino | Kamih-Pungud | 17.2561 | 122.2291 | R | 1962 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 60.9 | 42.57 | 60.9 |  | F - Nearest node and line over 5 km | 29.52 | 34.35 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4555
5 | 556 | 4556 | 0600607022 | Region VI (Western Visayas) | Antique | Tobias Fornier | Igbangcal-C | 10.4996 | 121.9896 | R | 298 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 27.08 | 8.98 | Tier 2 High GIDA (Score 40.0–49.9) | 60.89 | 42.57 | 60.89 |  | F - Nearest node and line over 5 km | 29.75 | 9.21 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4556
5 | 557 | 4557 | PH0004557 | IV-A | Cavite | Cavite City | Barangay 61 | 14.4818 | 120.9058 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.11 | 3.98 | Tier 2 High GIDA (Score 40.0–49.9) | 60.89 | 42.57 | 60.89 |  | D - Other node or line within 3 km | 2.11 | 3.96 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4557
5 | 558 | 4558 | PH0004558 | IV-A | Cavite | City of Bacoor | P.F. Espiritu 4 | 14.4418 | 120.9719 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.58 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 60.88 | 42.56 | 60.88 |  | D - Other node or line within 3 km | 2.02 | 1.27 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 4558
5 | 559 | 4559 | 1381300002 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Amihan | 14.6324 | 121.0705 | U | 3660 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.67 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 60.87 | 42.56 | 60.87 |  | B - Node 0.5-1 km | 0.67 | 0.22 | Line: UG 144C via R-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4559
5 | 560 | 4560 | 0300809005 | Region III (Central Luzon) | Bataan | Orani | Paking-Carbonero | 14.8026 | 120.5423 | R | 968 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.74 | 0.88 | Tier 2 High GIDA (Score 40.0–49.9) | 60.87 | 42.56 | 60.87 |  | B - Node 0.5-1 km | 0.64 | 0.61 | Line: 96CORE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4560
5 | 561 | 4561 | PH0004561 | IV-A | Cavite | Cavite City | Barangay 21 | 14.4884 | 120.8975 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.61 | 1.39 | Tier 2 High GIDA (Score 40.0–49.9) | 60.87 | 42.55 | 60.87 |  | D - Other node or line within 3 km | 1.85 | 4.96 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4561
5 | 562 | 4562 | PH0004562 | XII | South Cotabato | General Santos City (Dadiangas) | Dadiangas East (Pob.) | 6.1159 | 125.1771 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.86 | 42.55 | 60.86 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.34 | Line: DAVAO CITY - GENSAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4562
5 | 563 | 4563 | 1381200020 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Joaquin | 14.5514 | 121.0759 | U | 14682 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.03 | Tier 2 High GIDA (Score 40.0–49.9) | 60.86 | 42.54 | 60.86 |  | C - Line within 0.5 km; node over 1 km | 1.11 | 0.03 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4563
5 | 564 | 4564 | 0907214021 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Sergio Osmeña Sr. | Pedagan | 8.2402 | 123.4151 | R | 589 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.11 | 36.98 | Tier 2 High GIDA (Score 40.0–49.9) | 60.85 | 42.54 | 60.85 |  | F - Nearest node and line over 5 km | 37.11 | 36.97 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4564
5 | 565 | 4565 | 0401019013 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 8 | 14.0794 | 120.6829 | R | 1115 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.09 | 1.6 | Tier 2 High GIDA (Score 40.0–49.9) | 60.85 | 42.54 | 60.85 |  | D - Other node or line within 3 km | 5.35 | 2.44 | Line: NCC001 TO NSB001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4565
5 | 566 | 4566 | 0403426018 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay V | 14.2852 | 121.4187 | U | 425 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.1 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 60.85 | 42.54 | 60.85 |  | B - Node 0.5-1 km | 0.91 | 0.6 | Line: UG SCL001 TO LWL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4566
5 | 567 | 4567 | PH0004567 | XII | South Cotabato | General Santos City (Dadiangas) | Dadiangas North | 6.1156 | 125.1669 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 60.84 | 42.54 | 60.84 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.36 | Line: DAVAO CITY - GENSAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4567
5 | 568 | 4568 | 1381300132 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | West Kamias | 14.6306 | 121.0369 | U | 4225 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 1.15 | Tier 2 High GIDA (Score 40.0–49.9) | 60.83 | 42.53 | 60.83 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.29 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4568
5 | 569 | 4569 | PH0004569 | III | Nueva Ecija | Cabanatuan City | Bonifacio District (Pob.) | 15.5013 | 120.9849 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 60.83 | 42.53 | 60.83 |  | D - Other node or line within 3 km | 3.35 | 0.64 | Line: MULTINET - SANTA ROSA | Route options survey candidate: compare actual node lateral with approved line tap. | 4569
5 | 570 | 4570 | 1381300078 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Paraiso | 14.0783 | 122.1322 | U | 3685 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.37 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.83 | 42.53 | 60.83 |  | F - Nearest node and line over 5 km | 9.11 | 16.67 | Node: CLQ005 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4570
5 | 571 | 4571 | 0802621008 | Region VIII (Eastern Visayas) | Eastern Samar | San Policarpo | Natividad | 12.2604 | 125.435 | R | 618 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 122.89 | 125.41 | Tier 2 High GIDA (Score 40.0–49.9) | 60.83 | 42.52 | 60.83 |  | F - Nearest node and line over 5 km | 122.89 | 125.4 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4571
5 | 572 | 4572 | 0802603010 | Region VIII (Eastern Visayas) | Eastern Samar | Balangkayan | General Malvar | 11.4323 | 125.4237 | R | 104 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.68 | 50.71 | Tier 2 High GIDA (Score 40.0–49.9) | 60.82 | 42.52 | 60.82 |  | F - Nearest node and line over 5 km | 50.68 | 51.37 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4572
5 | 573 | 4573 | 0907313033 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lapuyan | Tugaya | 7.6929 | 123.1692 | R | 431 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.23 | 7.72 | Tier 2 High GIDA (Score 40.0–49.9) | 60.82 | 42.52 | 60.82 |  | F - Nearest node and line over 5 km | 13.23 | 7.71 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4573
5 | 574 | 4574 | 0907317010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Margosatubig | Digon | 7.5656 | 123.1359 | R | 1523 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.31 | 19.74 | Tier 2 High GIDA (Score 40.0–49.9) | 60.81 | 42.51 | 60.81 |  | F - Nearest node and line over 5 km | 20.31 | 19.72 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4574
5 | 575 | 4575 | 1400112008 | Cordillera Administrative Region (CAR) | Abra | Langiden | Quillat | 17.5872 | 120.5847 | R | 866 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.7 | 2.57 | Tier 2 High GIDA (Score 40.0–49.9) | 60.81 | 42.51 | 60.81 |  | D - Other node or line within 3 km | 3.7 | 2.46 | Line: CABLE LAYED | Route options survey candidate: compare actual node lateral with approved line tap. | 4575
5 | 576 | 4576 | 0600611001 | Region VI (Western Visayas) | Antique | Pandan | Aracay | 11.719 | 122.1584 | R | 211 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.71 | 7.75 | Tier 2 High GIDA (Score 40.0–49.9) | 60.8 | 42.51 | 60.8 |  | F - Nearest node and line over 5 km | 14.71 | 21.16 | Node: MOK001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4576
5 | 577 | 4577 | 0806016002 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Arapison | 12.0572 | 124.677 | R | 223 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 84.24 | 83.84 | Tier 2 High GIDA (Score 40.0–49.9) | 60.79 | 42.5 | 60.79 |  | F - Nearest node and line over 5 km | 84.24 | 83.84 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4577
5 | 578 | 4578 | 0806016017 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Hindang | 12.0788 | 124.6889 | R | 83 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 86.62 | 86.35 | Tier 2 High GIDA (Score 40.0–49.9) | 60.77 | 42.48 | 60.77 |  | F - Nearest node and line over 5 km | 86.62 | 86.35 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4578
5 | 579 | 4579 | PH0004579 | IV-A | Batangas | Lipa City | Balintawak | 13.954 | 121.161 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.24 | 0.35 | Tier 2 High GIDA (Score 40.0–49.9) | 60.75 | 42.47 | 60.75 |  | C - Line within 0.5 km; node over 1 km | 1.24 | 0.22 | Line: TANAUAN - SAN JOSE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4579
5 | 580 | 4580 | 1906610012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Pata | Pisak-pisak | 17.2556 | 122.2296 | R | 2561 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 60.75 | 42.47 | 60.75 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4580
5 | 581 | 4581 | 0405802002 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Cupang | 14.6388 | 121.1331 | U | 129296 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.51 | 1.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.74 | 42.46 | 60.74 |  | D - Other node or line within 3 km | 1.51 | 1.2 | Line: Aerial 96C | Route options survey candidate: compare actual node lateral with approved line tap. | 4581
5 | 582 | 4582 | 1903621005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Piagapo | Basak | 17.2544 | 122.2285 | R | 1125 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.74 | 42.46 | 60.74 |  | F - Nearest node and line over 5 km | 29.35 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4582
5 | 583 | 4583 | PH0004583 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Mansilano | 17.2535 | 122.2277 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 65.91 | 65.92 | Tier 2 High GIDA (Score 40.0–49.9) | 60.73 | 42.46 | 60.73 |  | F - Nearest node and line over 5 km | 29.22 | 34.13 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4583
5 | 584 | 4584 | 0603040046 | Region VI (Western Visayas) | Iloilo | San Joaquin | Languanan | 10.4765 | 122.0273 | R | 286 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 26.71 | 0.84 | Tier 2 High GIDA (Score 40.0–49.9) | 60.73 | 42.46 | 60.73 |  | F - Nearest node and line over 5 km | 33.25 | 10.17 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4584
5 | 585 | 4585 | 0501712003 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Cabasag | 13.9254 | 122.6052 | R | 892 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 60.72 | 42.45 | 60.72 |  | B - Node 0.5-1 km | 0.74 | 0.32 | Line: LZQ001 TO DEL GALLEGO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4585
5 | 586 | 4586 | 0806022025 | Region VIII (Eastern Visayas) | Samar | Paranas | Pagsanjan | 11.9145 | 125.0715 | R | 264 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 76.76 | 79.69 | Tier 2 High GIDA (Score 40.0–49.9) | 60.72 | 42.45 | 60.72 |  | F - Nearest node and line over 5 km | 75.42 | 78.35 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4586
5 | 587 | 4587 | PH0004587 | IV-B | Palawan | Puerto Princesa City | New Panggangan | 10.2727 | 118.9623 | R | 2597 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.08 | 26.84 | Tier 2 High GIDA (Score 40.0–49.9) | 60.71 | 42.44 | 60.71 |  | F - Nearest node and line over 5 km | 31.08 | 26.73 | Line: TAYTAY - PUERTO PRINCESA | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4587
5 | 588 | 4588 | 0201509001 | Region II (Cagayan Valley) | Cagayan | Calayan | Cabudadan | 19.2723 | 121.4735 | R | 815 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 83.21 | 80.3 | Tier 2 High GIDA (Score 40.0–49.9) | 60.7 | 42.43 | 60.7 |  | F - Nearest node and line over 5 km | 83.21 | 80.3 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4588
5 | 589 | 4589 | 1102412019 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone II | 6.8521 | 125.3964 | U | 6310 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.87 | 1.85 | Tier 2 High GIDA (Score 40.0–49.9) | 60.7 | 42.43 | 60.7 |  | D - Other node or line within 3 km | 1.87 | 1.85 | Line: DAVAO CITY - GENSAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4589
5 | 590 | 4590 | PH0004590 | VI | Iloilo | Iloilo City | PHHC Block 22 NHA | 10.731 | 122.5231 | R | 2230 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.33 | 13.18 | Tier 2 High GIDA (Score 40.0–49.9) | 60.69 | 42.43 | 60.69 |  | D - Other node or line within 3 km | 4.96 | 1.61 | Line: 7,092 | Route options survey candidate: compare actual node lateral with approved line tap. | 4590
5 | 591 | 4591 | 0200902010 | Region II (Cagayan Valley) | Batanes | Itbayat | Santa Rosa | 20.7281 | 121.8031 | R | 838 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 60.69 | 42.43 | 60.69 |  | F - Nearest node and line over 5 km | 248.45 | 244.46 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4591
5 | 592 | 4592 | 0402104011 | Region IV-A (CALABARZON) | Cavite | Carmona | Milagrosa | 14.3083 | 121.0494 | U | 25103 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.29 | 0.29 | Tier 2 High GIDA (Score 40.0–49.9) | 60.68 | 42.42 | 60.68 |  | A - Node within 0.5 km | 0.29 | 0.29 | Node: CRC005 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4592
5 | 593 | 4593 | 1907002025 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Paniongan | 5.0466 | 119.7428 | R | 1210 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.26 | 23.51 | Tier 2 High GIDA (Score 40.0–49.9) | 60.68 | 42.42 | 60.68 |  | F - Nearest node and line over 5 km | 330.75 | 330.75 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4593
5 | 594 | 4594 | 0402123007 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Benjamin Tirona | 14.2983 | 121.0137 | R | 3078 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 3.69 | Tier 2 High GIDA (Score 40.0–49.9) | 60.68 | 42.42 | 60.68 |  | D - Other node or line within 3 km | 2.17 | 4.16 | Node: MAC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4594
5 | 595 | 4595 | PH0004595 | VII | Cebu | Lapu-Lapu City (Opon) | Basak | 10.296 | 123.9627 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.9 | 5.01 | Tier 2 High GIDA (Score 40.0–49.9) | 60.67 | 42.41 | 60.67 |  | D - Other node or line within 3 km | 1.9 | 5.01 | Node: LUC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4595
5 | 596 | 4596 | 0201529035 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 2 | 17.6423 | 121.7395 | U | 609 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.61 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 60.67 | 42.41 | 60.67 |  | C - Line within 0.5 km; node over 1 km | 1.29 | 0.03 | Line: SEGMENT 9 (LAL-LO - TUGUEGARAO) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4596
5 | 597 | 4597 | 1408102018 | Cordillera Administrative Region (CAR) | Apayao | Conner | Banban | 17.7043 | 121.3923 | R | 1199 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.6 | 3.68 | Tier 2 High GIDA (Score 40.0–49.9) | 60.66 | 42.41 | 60.66 |  | E - Nearest node or line 3-5 km | 6.6 | 3.65 | Line: Tabuk-Conner | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4597
5 | 598 | 4598 | 1102414015 | Region XI (Davao Region) | Davao del Sur | Sulop | Osmeña | 6.5216 | 125.2848 | R | 631 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.68 | 3.7 | Tier 2 High GIDA (Score 40.0–49.9) | 60.66 | 42.41 | 60.66 |  | F - Nearest node and line over 5 km | 6.69 | 6.39 | Line: DAVAO CITY - GENSAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4598
5 | 599 | 4599 | 0102916006 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Boguibog | 17.0767 | 120.5336 | R | 660 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.14 | 8.05 | Tier 2 High GIDA (Score 40.0–49.9) | 60.65 | 42.4 | 60.65 |  | F - Nearest node and line over 5 km | 8.14 | 8.05 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4599
5 | 600 | 4600 | 0201508023 | Region II (Cagayan Valley) | Cagayan | Buguey | Tabbac | 18.2307 | 121.7992 | R | 1146 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.83 | 2.38 | Tier 2 High GIDA (Score 40.0–49.9) | 60.63 | 42.39 | 60.63 |  | D - Other node or line within 3 km | 2.83 | 2.38 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Route options survey candidate: compare actual node lateral with approved line tap. | 4600
5 | 601 | 4601 | 1908806003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Paglas | Bulod | 17.2551 | 122.2292 | R | 1281 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.62 | 42.38 | 60.62 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4601
5 | 602 | 4602 | PH0004602 | IV-A | Cavite | Cavite City | Barangay 47 | 14.4813 | 120.9006 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.49 | 8.41 | Tier 2 High GIDA (Score 40.0–49.9) | 60.62 | 42.38 | 60.62 |  | D - Other node or line within 3 km | 1.58 | 4.1 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4602
5 | 603 | 4603 | PH0004603 | CAR | Benguet | Baguio City | Aurora Hill, North Central | 16.4044 | 120.6203 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.08 | 1.74 | Tier 2 High GIDA (Score 40.0–49.9) | 60.61 | 42.37 | 60.61 |  | D - Other node or line within 3 km | 2.26 | 0.71 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Route options survey candidate: compare actual node lateral with approved line tap. | 4603
5 | 604 | 4604 | PH0004604 | XI | Davao Del Sur | Davao City | Wilfredo Aquino | 7.0907 | 125.6259 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.27 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 60.6 | 42.37 | 60.6 |  | D - Other node or line within 3 km | 2.27 | 0.92 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 4604
5 | 605 | 4605 | 0405647050 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Diego Zone II | 14.052 | 121.616 | R | 366 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.01 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 60.6 | 42.36 | 60.6 |  | E - Nearest node or line 3-5 km | 3.97 | 3.7 | Line: LILIW TO LUCENA AE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4605
5 | 606 | 4606 | PH0004606 | CAR | Benguet | Baguio City | Santo Rosario | 16.4002 | 120.5869 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 60.59 | 42.36 | 60.59 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.07 | Line: BAGUIO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4606
5 | 607 | 4607 | PH0004607 | XI | Davao Del Sur | Davao City | Barangay 18-B (Pob.) | 7.5586 | 125.4768 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 60.59 | 42.36 | 60.59 |  | F - Nearest node and line over 5 km | 26.92 | 25.42 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4607
5 | 608 | 4608 | 0402104010 | Region IV-A (CALABARZON) | Cavite | Carmona | Maduya | 14.3169 | 121.0608 | U | 11154 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 60.59 | 42.36 | 60.59 |  | B - Node 0.5-1 km | 0.64 | 0.16 | Line: AE CRC005-BNL001-CLB001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4608
5 | 609 | 4609 | PH0004609 | IV-A | Cavite | Cavite City | Barangay 45 | 14.4649 | 120.8848 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.47 | 1.65 | Tier 2 High GIDA (Score 40.0–49.9) | 60.57 | 42.34 | 60.57 |  | D - Other node or line within 3 km | 1.14 | 3.69 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4609
5 | 610 | 4610 | 1380900015 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | NBBS Dagat-dagatan | 14.6373 | 120.9645 | U | 33385 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.67 | 1.67 | Tier 2 High GIDA (Score 40.0–49.9) | 60.57 | 42.34 | 60.57 |  | D - Other node or line within 3 km | 1.5 | 1.45 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4610
5 | 611 | 4611 | PH0004611 | IV-A | Cavite | Cavite City | Barangay 27 | 14.4649 | 120.8848 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.49 | 4.83 | Tier 2 High GIDA (Score 40.0–49.9) | 60.56 | 42.34 | 60.56 |  | D - Other node or line within 3 km | 1.14 | 3.69 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4611
5 | 612 | 4612 | 1400121001 | Cordillera Administrative Region (CAR) | Abra | San Isidro | Cabayogan | 17.4953 | 120.5967 | R | 336 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.69 | 6.52 | Tier 2 High GIDA (Score 40.0–49.9) | 60.56 | 42.34 | 60.56 |  | F - Nearest node and line over 5 km | 7.69 | 6.42 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4612
5 | 613 | 4613 | 1003502026 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Sangcad | 8.1329 | 124.2419 | R | 1848 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.61 | 2.89 | Tier 2 High GIDA (Score 40.0–49.9) | 60.56 | 42.34 | 60.56 |  | D - Other node or line within 3 km | 10.61 | 2.88 | Line: 216f feeder iligan completed | Route options survey candidate: compare actual node lateral with approved line tap. | 4613
5 | 614 | 4614 | PH0004614 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 7 | 11.7743 | 124.8837 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.67 | 30.51 | Tier 2 High GIDA (Score 40.0–49.9) | 60.56 | 42.33 | 60.56 |  | F - Nearest node and line over 5 km | 56.85 | 56.78 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4614
5 | 615 | 4615 | 0402111001 | Region IV-A (CALABARZON) | Cavite | Kawit | Binakayan-Kanluran | 14.4443 | 120.8995 | R | 2655 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.98 | 1.54 | Tier 2 High GIDA (Score 40.0–49.9) | 60.55 | 42.33 | 60.55 |  | D - Other node or line within 3 km | 2.42 | 1.05 | Line: KAWIT | Route options survey candidate: compare actual node lateral with approved line tap. | 4615
5 | 616 | 4616 | 0102820018 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Paulo | 13.9167 | 120.938 | R | 959 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.58 | 1.23 | Tier 2 High GIDA (Score 40.0–49.9) | 60.54 | 42.32 | 60.54 |  | D - Other node or line within 3 km | 2.07 | 2.64 | Node: SNB001 - PM | Route options survey candidate: compare actual node lateral with approved line tap. | 4616
5 | 617 | 4617 | 0403428016 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pook | 14.3024 | 121.1096 | U | 61062 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 60.5 | 42.3 | 60.5 |  | B - Node 0.5-1 km | 0.64 | 0.57 | Line: RELIANCE TO SAN PABLO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4617
5 | 618 | 4618 | 0203117001 | Region II (Cagayan Valley) | Isabela | Maconacon | Diana | 17.3868 | 122.2366 | R | 199 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.21 | 42.82 | Tier 2 High GIDA (Score 40.0–49.9) | 60.5 | 42.3 | 60.5 |  | F - Nearest node and line over 5 km | 40.44 | 41.66 | Node: TMI002-PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4618
5 | 619 | 4619 | 0907311006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Bualan | 7.7131 | 123.1397 | R | 1007 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.51 | 5.03 | Tier 2 High GIDA (Score 40.0–49.9) | 60.5 | 42.3 | 60.5 |  | F - Nearest node and line over 5 km | 9.51 | 5.03 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4619
5 | 620 | 4620 | 0405647057 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Roque Zone I | 14.0597 | 121.635 | R | 145 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.17 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 60.49 | 42.29 | 60.49 |  | F - Nearest node and line over 5 km | 6 | 5.8 | Line: LBQ001 TO GCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4620
5 | 621 | 4621 | PH0004621 | III | Nueva Ecija | Cabanatuan City | Aduas Sur | 15.4964 | 120.9672 | R | 2398 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.76 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 60.49 | 42.29 | 60.49 |  | D - Other node or line within 3 km | 1.76 | 0.96 | Line: MULTINET - SANTA ROSA | Route options survey candidate: compare actual node lateral with approved line tap. | 4621
5 | 622 | 4622 | 1403208002 | Cordillera Administrative Region (CAR) | Kalinga | Pasil | Balatoc | 17.3558 | 121.0928 | R | 1621 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.84 | 7.37 | Tier 2 High GIDA (Score 40.0–49.9) | 60.49 | 42.29 | 60.49 |  | F - Nearest node and line over 5 km | 11.84 | 7.35 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4622
5 | 623 | 4623 | 0401005101 | Region IV-A (CALABARZON) | Batangas | Batangas City | Simlong | 13.6671 | 121.0544 | U | 4301 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.39 | 9.91 | Tier 2 High GIDA (Score 40.0–49.9) | 60.49 | 42.29 | 60.49 |  | D - Other node or line within 3 km | 2.39 | 9.91 | Node: BCY004 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4623
5 | 624 | 4624 | PH0004624 | III | Pampanga | Angeles City | Sto. Cristo | 15.166 | 120.5933 | R | 2334 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.19 | 0.18 | Tier 2 High GIDA (Score 40.0–49.9) | 60.48 | 42.28 | 60.48 |  | A - Node within 0.5 km | 0.19 | 0.01 | Line: 104 CORE 13X8 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4624
5 | 625 | 4625 | 1001301001 | Region X (Northern Mindanao) | Bukidnon | Baungon | Balintad | 8.2472 | 124.6983 | R | 732 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.77 | 10.67 | Tier 2 High GIDA (Score 40.0–49.9) | 60.47 | 42.28 | 60.47 |  | F - Nearest node and line over 5 km | 10.77 | 10.81 | Node: TKB001-TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4625
5 | 626 | 4626 | PH0004626 | IV-A | Cavite | Cavite City | Barangay 23 | 14.4934 | 120.9051 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.71 | 7.49 | Tier 2 High GIDA (Score 40.0–49.9) | 60.47 | 42.28 | 60.47 |  | D - Other node or line within 3 km | 2.81 | 5.2 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4626
5 | 627 | 4627 | 0500511011 | Region V (Bicol Region) | Albay | Manito | Malobago | 13.0805 | 123.835 | R | 822 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.07 | 9.98 | Tier 2 High GIDA (Score 40.0–49.9) | 60.47 | 42.28 | 60.47 |  | F - Nearest node and line over 5 km | 6.07 | 9.91 | Node: MNT001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4627
5 | 628 | 4628 | 1903620015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Diampaca | 17.2539 | 122.2281 | R | 778 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.63 | 33.84 | Tier 2 High GIDA (Score 40.0–49.9) | 60.47 | 42.27 | 60.47 |  | F - Nearest node and line over 5 km | 29.28 | 34.18 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4628
5 | 629 | 4629 | 0403403008 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Francisco | 14.3311 | 121.056 | U | 43047 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.25 | 1.36 | Tier 2 High GIDA (Score 40.0–49.9) | 60.47 | 42.27 | 60.47 |  | D - Other node or line within 3 km | 2.25 | 1.31 | Line: AE SPL002 TO SPL001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4629
5 | 630 | 4630 | 1381300119 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Talipapa | 14.687 | 121.0254 | U | 40584 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.86 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 60.46 | 42.27 | 60.46 |  | B - Node 0.5-1 km | 0.86 | 0.05 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4630
5 | 631 | 4631 | 1903606037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bubong | Palao | 17.2546 | 122.2289 | R | 1104 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 37.62 | 36.63 | Tier 2 High GIDA (Score 40.0–49.9) | 60.45 | 42.26 | 60.45 |  | F - Nearest node and line over 5 km | 29.39 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4631
5 | 632 | 4632 | 1381200019 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | San Antonio | 14.5668 | 121.0846 | U | 12455 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.18 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 60.45 | 42.26 | 60.45 |  | A - Node within 0.5 km | 0.33 | 0.12 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4632
5 | 633 | 4633 | 1705104008 | MIMAROPA Region | Occidental Mindoro | Lubang | Vigo | 13.8246 | 120.1822 | R | 1961 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.33 | 48.42 | Tier 2 High GIDA (Score 40.0–49.9) | 60.45 | 42.26 | 60.45 |  | F - Nearest node and line over 5 km | 48.33 | 48.34 | Node: CTG001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4633
5 | 634 | 4634 | 0403405049 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Real | 14.1985 | 121.1492 | U | 17945 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.36 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 60.45 | 42.26 | 60.45 |  | A - Node within 0.5 km | 0.36 | 0.03 | Line: CLB001 TO SCL001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4634
5 | 635 | 4635 | 0203123013 | Region II (Cagayan Valley) | Isabela | Quirino | Santa Catalina | 17.1619 | 121.6775 | R | 802 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.93 | 6.74 | Tier 2 High GIDA (Score 40.0–49.9) | 60.45 | 42.26 | 60.45 |  | F - Nearest node and line over 5 km | 6.93 | 6.74 | Line: ROXAS - GAMU | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4635
5 | 636 | 4636 | 1004201028 | Region X (Northern Mindanao) | Misamis Occidental | Aloran | Roxas | 8.3832 | 123.7303 | R | 143 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.59 | 33.94 | Tier 2 High GIDA (Score 40.0–49.9) | 60.44 | 42.25 | 60.44 |  | F - Nearest node and line over 5 km | 38.59 | 33.91 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4636
5 | 637 | 4637 | 1400119010 | Cordillera Administrative Region (CAR) | Abra | Pilar | Nagcanasan | 17.3682 | 120.5642 | R | 259 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.82 | 8.76 | Tier 2 High GIDA (Score 40.0–49.9) | 60.43 | 42.25 | 60.43 |  | F - Nearest node and line over 5 km | 8.82 | 8.75 | Line: SEGMENT 2 (CANDON - VIGAN) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4637
5 | 638 | 4638 | PH0004638 | XI | Davao Del Sur | Davao City | Barangay 6-A (Pob.) | 7.0725 | 125.6011 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 0.48 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.47 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4638
5 | 639 | 4639 | 0402108025 | Region IV-A (CALABARZON) | Cavite | City of General Trias | San Juan I | 14.3826 | 120.8773 | U | 5496 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.43 | 1.88 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | D - Other node or line within 3 km | 1.43 | 1.88 | Node: TZC003 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4639
5 | 640 | 4640 | 0405628019 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ibabang Yuni | 13.4251 | 122.4707 | R | 2454 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.6 | 13.59 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | F - Nearest node and line over 5 km | 6.6 | 13.59 | Node: MLQ002 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4640
5 | 641 | 4641 | 0806016012 | Region VIII (Eastern Visayas) | Samar | Santa Margarita | Can-ipulan | 12.0443 | 124.6854 | R | 295 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 82.78 | 82.5 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | F - Nearest node and line over 5 km | 82.78 | 82.49 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4641
5 | 642 | 4642 | 1380200009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Zapote | 14.4639 | 120.9708 | U | 21169 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.28 | 0.21 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | A - Node within 0.5 km | 0.28 | 0.08 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4642
5 | 643 | 4643 | 1907010021 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Sapa-Sapa | Sukah-sukah | 17.2558 | 122.2298 | R | 1198 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.56 | 34.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.42 | 42.24 | 60.42 |  | F - Nearest node and line over 5 km | 29.56 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4643
5 | 644 | 4644 | PH0004644 | IV-A | Cavite | Cavite City | Barangay 57 | 14.4593 | 120.8807 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.88 | 0.16 | Tier 2 High GIDA (Score 40.0–49.9) | 60.41 | 42.24 | 60.41 |  | D - Other node or line within 3 km | 1.88 | 3.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4644
5 | 645 | 4645 | PH0004645 | XI | Davao Del Sur | Davao City | Barangay 5-A (Pob.) | 7.0715 | 125.5962 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 0.8 | Tier 2 High GIDA (Score 40.0–49.9) | 60.41 | 42.24 | 60.41 |  | D - Other node or line within 3 km | 1.57 | 0.79 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 4645
5 | 646 | 4646 | 1903634015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Maguing | Camalig | 17.2534 | 122.2275 | R | 975 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.57 | 33.78 | Tier 2 High GIDA (Score 40.0–49.9) | 60.41 | 42.23 | 60.41 |  | F - Nearest node and line over 5 km | 29.2 | 34.1 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4646
5 | 647 | 4647 | 0405811002 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 1 | 14.7002 | 121.1226 | U | 5006 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.64 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.4 | 42.23 | 60.4 |  | C - Line within 0.5 km; node over 1 km | 1.64 | 0.23 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4647
5 | 648 | 4648 | 0806417009 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Hindangan | 10.4253 | 124.9274 | R | 155 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.42 | 7.02 | Tier 2 High GIDA (Score 40.0–49.9) | 60.4 | 42.22 | 60.4 |  | F - Nearest node and line over 5 km | 31.43 | 18.17 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4648
5 | 649 | 4649 | PH0004649 | VII | Cebu | Lapu-Lapu City (Opon) | Pajo | 10.3109 | 123.9666 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.76 | 3.91 | Tier 2 High GIDA (Score 40.0–49.9) | 60.39 | 42.22 | 60.39 |  | B - Node 0.5-1 km | 0.76 | 3.91 | Node: LUC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4649
5 | 650 | 4650 | 1380500008 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Buayang Bato | 14.5683 | 121.0514 | U | 3188 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 60.39 | 42.22 | 60.39 |  | C - Line within 0.5 km; node over 1 km | 1.57 | 0.1 | Line: UG 144C via V-DUCT | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4650
5 | 651 | 4651 | 0806026013 | Region VIII (Eastern Visayas) | Samar | Pagsanghan | Canlapwas | 11.9642 | 124.7197 | R | 1100 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 73.96 | 73.94 | Tier 2 High GIDA (Score 40.0–49.9) | 60.39 | 42.22 | 60.39 |  | F - Nearest node and line over 5 km | 73.96 | 73.93 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4651
5 | 652 | 4652 | 0300809003 | Region III (Central Luzon) | Bataan | Orani | Bayan | 14.7902 | 120.5197 | U | 6663 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 1.04 | Tier 2 High GIDA (Score 40.0–49.9) | 60.38 | 42.21 | 60.38 |  | D - Other node or line within 3 km | 2.23 | 1.01 | Line: 96C DONA TO ORANI | Route options survey candidate: compare actual node lateral with approved line tap. | 4652
5 | 653 | 4653 | 0603040072 | Region VI (Western Visayas) | Iloilo | San Joaquin | San Luis | 10.5327 | 122.0518 | R | 653 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.4 | 4.19 | Tier 2 High GIDA (Score 40.0–49.9) | 60.37 | 42.2 | 60.37 |  | E - Nearest node or line 3-5 km | 28.4 | 4.07 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4653
5 | 654 | 4654 | 1908819010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Sapakan | 17.2552 | 122.2292 | R | 3419 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.36 | 42.2 | 60.36 |  | F - Nearest node and line over 5 km | 29.47 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4654
5 | 655 | 4655 | 0200902006 | Region II (Cagayan Valley) | Batanes | Itbayat | Raele | 20.729 | 121.804 | R | 475 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 60.36 | 42.2 | 60.36 |  | F - Nearest node and line over 5 km | 248.57 | 244.58 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4655
5 | 656 | 4656 | 0504110007 | Region V (Bicol Region) | Masbate | Mandaon | Cagmasoso | 12.1627 | 123.2309 | R | 484 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.36 | 21.55 | Tier 2 High GIDA (Score 40.0–49.9) | 60.36 | 42.19 | 60.36 |  | F - Nearest node and line over 5 km | 10.36 | 30.74 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4656
5 | 657 | 4657 | PH0004657 | XIII | Agusan Del Norte | Butuan City | Silongan Pob. | 8.9897 | 125.5604 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.45 | 8.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.35 | 42.19 | 60.35 |  | E - Nearest node or line 3-5 km | 4.92 | 4 | Line: TRENTO - BUENAVISTA CLS | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4657
5 | 658 | 4658 | PH0004658 | IV-A | Cavite | City of Bacoor | Salinas 1 | 14.4568 | 120.9548 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.58 | 5.78 | Tier 2 High GIDA (Score 40.0–49.9) | 60.35 | 42.19 | 60.35 |  | A - Node within 0.5 km | 0.41 | 0.34 | Line: PSG001 RELIANCE TO NCC001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4658
5 | 659 | 4659 | 0402118050 | Region IV-A (CALABARZON) | Cavite | Silang | Anahaw I | 14.2511 | 121.0534 | U | 5504 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.77 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 60.35 | 42.19 | 60.35 |  | A - Node within 0.5 km | 0.09 | 1 | Node: SGC005 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4659
5 | 660 | 4660 | 1908819011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Tabungao | 17.2552 | 122.2292 | R | 3569 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.35 | 42.19 | 60.35 |  | F - Nearest node and line over 5 km | 29.47 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4660
5 | 661 | 4661 | 0103314008 | Region I (Ilocos Region) | La Union | City of San Fernando | Barangay III | 16.6241 | 120.3423 | U | 308 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.68 | 2.62 | Tier 2 High GIDA (Score 40.0–49.9) | 60.34 | 42.18 | 60.34 |  | D - Other node or line within 3 km | 3.47 | 2.61 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Route options survey candidate: compare actual node lateral with approved line tap. | 4661
5 | 662 | 4662 | PH0004662 | IV-A | Cavite | Cavite City | Barangay 37 | 14.4739 | 120.8868 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.59 | 8.58 | Tier 2 High GIDA (Score 40.0–49.9) | 60.33 | 42.18 | 60.33 |  | A - Node within 0.5 km | 0.13 | 4.29 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4662
5 | 663 | 4663 | 1380500003 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Barangka Drive | 14.5733 | 121.0381 | U | 16933 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.27 | 0.31 | Tier 2 High GIDA (Score 40.0–49.9) | 60.33 | 42.18 | 60.33 |  | C - Line within 0.5 km; node over 1 km | 1.27 | 0.31 | Line: Aerial 216C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4663
5 | 664 | 4664 | 1004204015 | Region X (Northern Mindanao) | Misamis Occidental | Calamba | Singalat | 8.4196 | 123.6366 | R | 228 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 45.54 | 42.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.33 | 42.18 | 60.33 |  | F - Nearest node and line over 5 km | 45.54 | 42.25 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4664
5 | 665 | 4665 | 1381200013 | National Capital Region (NCR) | Second District (Not a Province) | City of Pasig | Oranbo | 14.5757 | 121.0657 | U | 3470 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.92 | 0.41 | Tier 2 High GIDA (Score 40.0–49.9) | 60.32 | 42.17 | 60.32 |  | B - Node 0.5-1 km | 0.92 | 0.4 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4665
5 | 666 | 4666 | 0201529036 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Centro 3 | 17.6139 | 121.7252 | U | 355 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.77 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 60.32 | 42.17 | 60.32 |  | C - Line within 0.5 km; node over 1 km | 4.77 | 0.03 | Line: TUGEGARAO FOC | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4666
5 | 667 | 4667 | 1102504002 | Region XI (Davao Region) | Davao Oriental | Caraga | Caningag | 7.2846 | 126.4727 | R | 1175 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 46.35 | 45.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.31 | 42.17 | 60.31 |  | F - Nearest node and line over 5 km | 46.35 | 45.04 | Line: PANTUKAN - MATI SEGMENT 5 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4667
5 | 668 | 4668 | PH0004668 | XI | Davao Del Sur | Davao City | Panacan | 7.1545 | 125.6598 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.6 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 60.31 | 42.16 | 60.31 |  | C - Line within 0.5 km; node over 1 km | 4.6 | 0.22 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4668
5 | 669 | 4669 | 0301412001 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bagbaguin | 14.8189 | 120.9555 | U | 8807 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 60.3 | 42.16 | 60.3 |  | B - Node 0.5-1 km | 0.71 | 0.27 | Line: 48 CORE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4669
5 | 670 | 4670 | 1600304009 | Region XIII (Caraga) | Agusan del Sur | La Paz | Angeles | 8.2579 | 125.7886 | R | 1021 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.99 | 20.77 | Tier 2 High GIDA (Score 40.0–49.9) | 60.3 | 42.16 | 60.3 |  | F - Nearest node and line over 5 km | 23.99 | 20.77 | Line: TRENTO - BUENAVISTA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4670
5 | 671 | 4671 | 1705303011 | MIMAROPA Region | Palawan | Araceli | Santo Niño | 10.5545 | 119.8525 | R | 578 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.87 | 47.71 | Tier 2 High GIDA (Score 40.0–49.9) | 60.3 | 42.15 | 60.3 |  | F - Nearest node and line over 5 km | 33.81 | 42.59 | Node: TYW007 - TYPE 4 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4671
5 | 672 | 4672 | 1906613026 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Lambanah | 17.2555 | 122.2295 | U | 2428 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.51 | 34.38 | Tier 2 High GIDA (Score 40.0–49.9) | 60.29 | 42.15 | 60.29 |  | F - Nearest node and line over 5 km | 29.51 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4672
5 | 673 | 4673 | 1705910008 | MIMAROPA Region | Romblon | Romblon | Alad | 12.6214 | 122.2408 | R | 2026 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 74.8 | 62.04 | Tier 2 High GIDA (Score 40.0–49.9) | 60.29 | 42.15 | 60.29 |  | F - Nearest node and line over 5 km | 74.8 | 74.83 | Node: RSM001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4673
5 | 674 | 4674 | PH0004674 | VII | Cebu | Talisay City | Mohon | 10.2492 | 123.8264 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.37 | 11.7 | Tier 2 High GIDA (Score 40.0–49.9) | 60.26 | 42.13 | 60.26 |  | C - Line within 0.5 km; node over 1 km | 2.11 | 0.48 | Line: 96c | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4674
5 | 675 | 4675 | 1408101016 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Kabugawan | 18.2564 | 121.0433 | R | 458 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.12 | 27.1 | Tier 2 High GIDA (Score 40.0–49.9) | 60.26 | 42.13 | 60.26 |  | F - Nearest node and line over 5 km | 30.09 | 32.32 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4675
5 | 676 | 4676 | 1001321014 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Lourdes | 9.6626 | 124.2261 | R | 2187 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.19 | 0.59 | Tier 2 High GIDA (Score 40.0–49.9) | 60.26 | 42.12 | 60.26 |  | F - Nearest node and line over 5 km | 34.6 | 13.99 | Line: CARMEN TO TAGBILARAN VIA LOBOC | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4676
5 | 677 | 4677 | 1380608012 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 670 | 14.5806 | 120.9863 | U | 2858 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.35 | 19.72 | Tier 2 High GIDA (Score 40.0–49.9) | 60.24 | 42.11 | 60.24 |  | C - Line within 0.5 km; node over 1 km | 1.13 | 0.33 | Line: UG 288C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4677
5 | 678 | 4678 | 0405802008 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Jose | 14.6925 | 121.3 | U | 122171 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.35 | 14.86 | Tier 2 High GIDA (Score 40.0–49.9) | 60.24 | 42.11 | 60.24 |  | F - Nearest node and line over 5 km | 7.35 | 14.73 | Node: ANR009 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4678
5 | 679 | 4679 | 1381000009 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Marcelo Green Village | 14.4587 | 121.0425 | U | 38296 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 60.23 | 42.11 | 60.23 |  | B - Node 0.5-1 km | 0.71 | 0.32 | Line: RELIANCE PSG001 TO BÑL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4679
5 | 680 | 4680 | 0401029051 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 14 | 13.8977 | 120.9169 | R | 510 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.59 | 1.16 | Tier 2 High GIDA (Score 40.0–49.9) | 60.22 | 42.1 | 60.22 |  | B - Node 0.5-1 km | 0.8 | 0.03 | Line: Untitled Path | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4680
5 | 681 | 4681 | 0600616042 | Region VI (Western Visayas) | Antique | Sibalom | Lagdo | 10.8329 | 122.0105 | R | 595 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.15 | 3.88 | Tier 2 High GIDA (Score 40.0–49.9) | 60.21 | 42.09 | 60.21 |  | E - Nearest node or line 3-5 km | 11.15 | 3.61 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4681
5 | 682 | 4682 | 1001316016 | Region X (Northern Mindanao) | Bukidnon | Pangantucan | Payad | 7.5642 | 124.8543 | R | 1257 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.26 | 11.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.21 | 42.09 | 60.21 |  | F - Nearest node and line over 5 km | 7.26 | 11.21 | Node: KDB001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4682
5 | 683 | 4683 | 1903604018 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Linao | 17.2547 | 122.2288 | R | 784 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 60.21 | 42.09 | 60.21 |  | F - Nearest node and line over 5 km | 29.4 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4683
5 | 684 | 4684 | PH0004684 | IX | Zamboanga Del Sur | Zamboanga City | Camino Nuevo | 6.9206 | 122.0414 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.82 | 7.13 | Tier 2 High GIDA (Score 40.0–49.9) | 60.21 | 42.09 | 60.21 |  | E - Nearest node or line 3-5 km | 3.75 | 3.75 | Node: ZCZ001-TYPE 2 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4684
5 | 685 | 4685 | 0405622012 | Region IV-A (CALABARZON) | Quezon | Lopez | Binahian A | 13.8268 | 122.2708 | R | 370 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.78 | 6.44 | Tier 2 High GIDA (Score 40.0–49.9) | 60.2 | 42.09 | 60.2 |  | F - Nearest node and line over 5 km | 6.78 | 6.41 | Line: UG GCQ001 TO LZQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4685
5 | 686 | 4686 | PH0004686 | VII | Cebu | Lapu-Lapu City (Opon) | Cawhagan | 10.2026 | 124.0184 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.19 | 16.86 | Tier 2 High GIDA (Score 40.0–49.9) | 60.2 | 42.09 | 60.2 |  | F - Nearest node and line over 5 km | 10.19 | 16.79 | Node: CDV001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4686
5 | 687 | 4687 | 1381600007 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Canumay West | 14.7331 | 120.9291 | U | 27285 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.06 | 0.42 | Tier 2 High GIDA (Score 40.0–49.9) | 60.2 | 42.09 | 60.2 |  | D - Other node or line within 3 km | 2.75 | 3.37 | Node: OBB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4687
5 | 688 | 4688 | 0402116009 | Region IV-A (CALABARZON) | Cavite | Noveleta | Santa Rosa I | 14.4281 | 120.893 | U | 5192 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.3 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 60.2 | 42.09 | 60.2 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.02 | Line: PSG001 RELIANCE TO NCC001 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4688
5 | 689 | 4689 | PH0004689 | XI | Davao Del Sur | Davao City | Barangay 20-B (Pob.) | 7.0866 | 125.613 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.01 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.19 | 42.08 | 60.19 |  | C - Line within 0.5 km; node over 1 km | 1.01 | 0.22 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4689
5 | 690 | 4690 | 0702232007 | Region VII (Central Visayas) | Cebu | Minglanilla | Linao | 10.255 | 123.8103 | U | 16506 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.36 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 60.19 | 42.08 | 60.19 |  | C - Line within 0.5 km; node over 1 km | 1.36 | 0.02 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4690
5 | 691 | 4691 | 0405617005 | Region IV-A (CALABARZON) | Quezon | General Nakar | Canaway | 15.0012 | 121.5452 | R | 1452 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.44 | 49.9 | Tier 2 High GIDA (Score 40.0–49.9) | 60.18 | 42.07 | 60.18 |  | F - Nearest node and line over 5 km | 28.44 | 49.72 | Node: GNQ001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4691
5 | 692 | 4692 | 1903630029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Wao | Milaya | 17.2543 | 122.2283 | R | 2454 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.18 | 42.07 | 60.18 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4692
5 | 693 | 4693 | PH0004693 | IX | Zamboanga Del Sur | Zamboanga City | Latuan | 7.2316 | 122.2062 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.1 | 3.62 | Tier 2 High GIDA (Score 40.0–49.9) | 60.17 | 42.06 | 60.17 |  | E - Nearest node or line 3-5 km | 6.1 | 3.62 | Line: CABLE INSTALLED | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4693
5 | 694 | 4694 | 0200902007 | Region II (Cagayan Valley) | Batanes | Itbayat | San Rafael | 20.7837 | 121.8379 | R | 902 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 60.17 | 42.06 | 60.17 |  | F - Nearest node and line over 5 km | 255.34 | 251.44 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4694
5 | 695 | 4695 | 0601906012 | Region VI (Western Visayas) | Capiz | Jamindan | Igang | 11.4691 | 122.4728 | R | 450 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.39 | 6.77 | Tier 2 High GIDA (Score 40.0–49.9) | 60.17 | 42.06 | 60.17 |  | F - Nearest node and line over 5 km | 7.39 | 6.77 | Line: IVISAN - KALIBO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4695
5 | 696 | 4696 | 1908803002 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Abdullah Sangki | Dimampao | 17.2552 | 122.2292 | R | 2550 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.46 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.17 | 42.06 | 60.17 |  | F - Nearest node and line over 5 km | 29.46 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4696
5 | 697 | 4697 | 1108208001 | Region XI (Davao Region) | Davao de Oro | Montevista | Banagbanag | 7.6492 | 126.0255 | R | 1387 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.09 | 4.77 | Tier 2 High GIDA (Score 40.0–49.9) | 60.16 | 42.06 | 60.16 |  | E - Nearest node or line 3-5 km | 20.09 | 4.77 | Line: DAVAO CITY - TRENTO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4697
5 | 698 | 4698 | 0405647058 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Roque Zone II | 14.0524 | 121.6172 | R | 869 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.98 | 1.73 | Tier 2 High GIDA (Score 40.0–49.9) | 60.16 | 42.05 | 60.16 |  | E - Nearest node or line 3-5 km | 4.09 | 3.84 | Line: LILIW TO LUCENA AE | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4698
5 | 699 | 4699 | 1380700001 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Barangka | 14.6332 | 121.0819 | U | 17196 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.39 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 60.15 | 42.05 | 60.15 |  | D - Other node or line within 3 km | 1.39 | 0.83 | Line: UG 288C | Route options survey candidate: compare actual node lateral with approved line tap. | 4699
5 | 700 | 4700 | 0704613008 | Region VII (Central Visayas) | Negros Oriental | La Libertad | Eli | 10.0559 | 123.1381 | R | 1696 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 15.88 | 10.46 | Tier 2 High GIDA (Score 40.0–49.9) | 60.15 | 42.05 | 60.15 |  | F - Nearest node and line over 5 km | 15.88 | 10.6 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4700
5 | 701 | 4701 | 1908811001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Gen. S.K. Pendatun | Badak | 17.255 | 122.2291 | R | 5081 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.44 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 60.14 | 42.04 | 60.14 |  | F - Nearest node and line over 5 km | 29.44 | 34.31 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4701
5 | 702 | 4702 | 1908709006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Parang | Gadunganpedpandaran | 17.2548 | 122.2282 | R | 2172 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 35.22 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.14 | 42.04 | 60.14 |  | F - Nearest node and line over 5 km | 29.35 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4702
5 | 703 | 4703 | PH0004703 | VII | Cebu | Lapu-Lapu City (Opon) | Gun-ob | 10.3017 | 123.9519 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.53 | 3.78 | Tier 2 High GIDA (Score 40.0–49.9) | 60.13 | 42.04 | 60.13 |  | D - Other node or line within 3 km | 1.53 | 3.78 | Node: LUC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4703
5 | 704 | 4704 | 0806006019 | Region VIII (Eastern Visayas) | Samar | Daram | Canloloy | 11.5473 | 124.7963 | R | 205 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.89 | 29.82 | Tier 2 High GIDA (Score 40.0–49.9) | 60.13 | 42.03 | 60.13 |  | F - Nearest node and line over 5 km | 29.89 | 29.82 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4704
5 | 705 | 4705 | 0405647003 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone I | 14.0223 | 121.5959 | R | 1781 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.04 | Tier 2 High GIDA (Score 40.0–49.9) | 60.12 | 42.03 | 60.12 |  | A - Node within 0.5 km | 0.31 | 0.04 | Line: AE LCQ001 TO TYQ001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4705
5 | 706 | 4706 | 0403426026 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Sur | 14.2812 | 121.4113 | U | 4457 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.3 | 0.3 | Tier 2 High GIDA (Score 40.0–49.9) | 60.12 | 42.03 | 60.12 |  | A - Node within 0.5 km | 0.3 | 0.3 | Line: SNL001 TO SCL001 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4706
5 | 707 | 4707 | PH0004707 | IV-A | Cavite | Cavite City | Barangay 41 | 14.483 | 120.8971 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.37 | 4.45 | Tier 2 High GIDA (Score 40.0–49.9) | 60.11 | 42.03 | 60.11 |  | D - Other node or line within 3 km | 1.37 | 4.45 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4707
5 | 708 | 4708 | 0401029026 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 2 | 13.8815 | 120.925 | U | 388 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 1.4 | Tier 2 High GIDA (Score 40.0–49.9) | 60.11 | 42.02 | 60.11 |  | D - Other node or line within 3 km | 1.07 | 1.35 | Node: TLB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4708
5 | 709 | 4709 | PH0004709 | BARMM (LaMa+SGA) | Lanao Del Sur | Bumbaran | Frankfort | 17.2543 | 122.2283 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.33 | 34.22 | Tier 2 High GIDA (Score 40.0–49.9) | 60.11 | 42.02 | 60.11 |  | F - Nearest node and line over 5 km | 29.33 | 34.21 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4709
5 | 710 | 4710 | 1381600008 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Karuhatan | 14.6911 | 120.9761 | U | 41864 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.1 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 60.1 | 42.02 | 60.1 |  | C - Line within 0.5 km; node over 1 km | 1.1 | 0.16 | Line: EXISTING 216 C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4710
5 | 711 | 4711 | 1906607003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Bangday | 17.255 | 122.2296 | R | 1176 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.69 | 34.1 | Tier 2 High GIDA (Score 40.0–49.9) | 60.1 | 42.02 | 60.1 |  | F - Nearest node and line over 5 km | 29.48 | 34.37 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4711
5 | 712 | 4712 | 0405640001 | Region IV-A (CALABARZON) | Quezon | San Andres | Alibihaban | 13.3276 | 122.716 | R | 1552 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.21 | 31.73 | Tier 2 High GIDA (Score 40.0–49.9) | 60.09 | 42.01 | 60.09 |  | E - Nearest node or line 3-5 km | 4.21 | 31.73 | Node: SDQ001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4712
5 | 713 | 4713 | PH0004713 | XI | Davao Del Sur | Davao City | Matina Crossing | 7.0795 | 125.574 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.25 | 2.35 | Tier 2 High GIDA (Score 40.0–49.9) | 60.09 | 42.01 | 60.09 |  | D - Other node or line within 3 km | 1.25 | 2.35 | Node: DCD028 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4713
5 | 714 | 4714 | PH0004714 | IV-A | Cavite | Imus City | Tanzang Luma IV | 14.4295 | 120.9277 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.23 | 4.56 | Tier 2 High GIDA (Score 40.0–49.9) | 60.08 | 42 | 60.08 |  | D - Other node or line within 3 km | 1.95 | 2.15 | Node: IMC002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4714
5 | 715 | 4715 | 1381300083 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Pinagkaisahan | 14.6274 | 121.0466 | U | 4549 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.45 | 0.37 | Tier 2 High GIDA (Score 40.0–49.9) | 60.08 | 42 | 60.08 |  | C - Line within 0.5 km; node over 1 km | 1.45 | 0.36 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4715
5 | 716 | 4716 | 1381300130 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Veterans Village | 14.6541 | 121.0247 | U | 13290 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.04 | 0.48 | Tier 2 High GIDA (Score 40.0–49.9) | 60.08 | 42 | 60.08 |  | C - Line within 0.5 km; node over 1 km | 1.04 | 0.48 | Line: UG 144C via Y-Duct | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4716
5 | 717 | 4717 | PH0004717 | NIR | Negros Oriental | Dumaguete City | Poblacion No. 6 | 9.292 | 123.2744 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.28 | 2.2 | Tier 2 High GIDA (Score 40.0–49.9) | 60.08 | 42 | 60.08 |  | D - Other node or line within 3 km | 3.58 | 2.27 | Line: KABANGKALAN - BACONG | Route options survey candidate: compare actual node lateral with approved line tap. | 4717
5 | 718 | 4718 | PH0004718 | IV-A | Cavite | Cavite City | Barangay 13 | 14.4732 | 120.8867 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.2 | 4.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.07 | 41.99 | 60.07 |  | A - Node within 0.5 km | 0.2 | 4.25 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4718
5 | 719 | 4719 | 0600606027 | Region VI (Western Visayas) | Antique | Culasi | Maniguin | 11.5981 | 121.6957 | R | 793 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.52 | 45.45 | Tier 2 High GIDA (Score 40.0–49.9) | 60.07 | 41.99 | 60.07 |  | F - Nearest node and line over 5 km | 47.52 | 69.75 | Node: MYK001 - TYPE 2 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4719
5 | 720 | 4720 | 1403211005 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Kinama | 17.5783 | 121.516 | R | 1011 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.29 | 8.82 | Tier 2 High GIDA (Score 40.0–49.9) | 60.06 | 41.99 | 60.06 |  | F - Nearest node and line over 5 km | 10.29 | 8.74 | Line: Tabuk-Conner | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4720
5 | 721 | 4721 | 0405603034 | Region IV-A (CALABARZON) | Quezon | Atimonan | San Jose Balatok | 13.9526 | 121.8653 | R | 62 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.02 | 0.98 | Tier 2 High GIDA (Score 40.0–49.9) | 60.06 | 41.99 | 60.06 |  | E - Nearest node or line 3-5 km | 6.72 | 4.08 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4721
5 | 722 | 4722 | 1001307013 | Region X (Northern Mindanao) | Bukidnon | Kalilangan | Ninoy Aquino | 7.7686 | 124.7857 | R | 5005 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.02 | 18.67 | Tier 2 High GIDA (Score 40.0–49.9) | 60.06 | 41.99 | 60.06 |  | F - Nearest node and line over 5 km | 17.02 | 18.54 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4722
5 | 723 | 4723 | PH0004723 | NIR | Negros Occidental | Bacolod City | Barangay 7 (Pob.) | 10.6619 | 122.9441 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.2 | Tier 2 High GIDA (Score 40.0–49.9) | 60.05 | 41.98 | 60.05 |  | C - Line within 0.5 km; node over 1 km | 1.05 | 0.13 | Line: FOC 144C TALISAY CLS TO BACONG CLS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4723
5 | 724 | 4724 | 0300803026 | Region III (Central Luzon) | Bataan | City of Balanga | Doña Francisca | 14.6895 | 120.557 | U | 2426 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.19 | 0.34 | Tier 2 High GIDA (Score 40.0–49.9) | 60.05 | 41.98 | 60.05 |  | D - Other node or line within 3 km | 1.41 | 1.16 | Line: CITY OF BALANGA | Route options survey candidate: compare actual node lateral with approved line tap. | 4724
5 | 725 | 4725 | 1381600018 | National Capital Region (NCR) | Third District (Not a Province) | City of Valenzuela | Mapulang Lupa | 14.7019 | 121.0007 | U | 30793 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.73 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 60.05 | 41.98 | 60.05 |  | B - Node 0.5-1 km | 0.73 | 0.05 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4725
5 | 726 | 4726 | 0103314022 | Region I (Ilocos Region) | La Union | City of San Fernando | Catbangen | 16.6126 | 120.3124 | U | 9670 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.15 | 0.4 | Tier 2 High GIDA (Score 40.0–49.9) | 60.05 | 41.98 | 60.05 |  | C - Line within 0.5 km; node over 1 km | 1.15 | 0.4 | Line: SAN FERNANDO - SUPIDEN AERIAL | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4726
5 | 727 | 4727 | 0203111010 | Region II (Cagayan Valley) | Isabela | Divilacan | Dimasalansan | 17.3104 | 122.3961 | R | 381 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 47.48 | 53.08 | Tier 2 High GIDA (Score 40.0–49.9) | 60.04 | 41.98 | 60.04 |  | F - Nearest node and line over 5 km | 47.48 | 53.07 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4727
5 | 728 | 4728 | 1606818020 | Region XIII (Caraga) | Surigao del Sur | Tago | Umbay | 8.9776 | 126.1773 | R | 454 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.26 | 2.09 | Tier 2 High GIDA (Score 40.0–49.9) | 60.04 | 41.97 | 60.04 |  | D - Other node or line within 3 km | 11.26 | 1.44 | Line: Route | Route options survey candidate: compare actual node lateral with approved line tap. | 4728
5 | 729 | 4729 | PH0004729 | NCR | Metro Manila | Caloocan City | Barangay 161 | 14.6734 | 121.0017 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.17 | 25.39 | Tier 2 High GIDA (Score 40.0–49.9) | 60.03 | 41.97 | 60.03 |  | D - Other node or line within 3 km | 1.09 | 0.95 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 4729
5 | 730 | 4730 | 0102910005 | Region I (Ilocos Region) | Ilocos Sur | Gregorio del Pilar | Matue-Butarag | 17.1402 | 120.6034 | R | 700 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.36 | 5.32 | Tier 2 High GIDA (Score 40.0–49.9) | 60.03 | 41.97 | 60.03 |  | E - Nearest node or line 3-5 km | 6.74 | 4.95 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4730
5 | 731 | 4731 | 1381300091 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sacred Heart | 14.6298 | 121.0366 | U | 6345 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.16 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 60.03 | 41.97 | 60.03 |  | C - Line within 0.5 km; node over 1 km | 1.16 | 0.25 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4731
5 | 732 | 4732 | 1001308034 | Region X (Northern Mindanao) | Bukidnon | Kibawe | Tumaras | 7.5174 | 125.0049 | R | 985 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.78 | 6.54 | Tier 2 High GIDA (Score 40.0–49.9) | 60.02 | 41.96 | 60.02 |  | F - Nearest node and line over 5 km | 5.77 | 5.24 | Line: DAMULOG - VALENCIA - QUEZON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4732
5 | 733 | 4733 | 0504107013 | Region V (Bicol Region) | Masbate | Claveria | Nonoc | 12.9212 | 123.1743 | R | 1634 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.8 | 51.58 | Tier 2 High GIDA (Score 40.0–49.9) | 60.02 | 41.96 | 60.02 |  | F - Nearest node and line over 5 km | 21.8 | 51.54 | Node: LOA004-BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4733
5 | 734 | 4734 | 1400109003 | Cordillera Administrative Region (CAR) | Abra | Lacub | Guinguinabang | 17.6613 | 120.9503 | R | 311 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.02 | 30.96 | Tier 2 High GIDA (Score 40.0–49.9) | 60.01 | 41.95 | 60.01 |  | F - Nearest node and line over 5 km | 30.07 | 30.02 | Line: CABLE LAYED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4734
5 | 735 | 4735 | 0305405028 | Region III (Central Luzon) | Pampanga | Candaba | Salapungan | 15.1381 | 120.9345 | U | 5325 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.17 | 2.28 | Tier 2 High GIDA (Score 40.0–49.9) | 60 | 41.95 | 60 |  | D - Other node or line within 3 km | 3.17 | 2.27 | Line: SEGMENT 18 (BALIUAG - ZARAGOZA) | Route options survey candidate: compare actual node lateral with approved line tap. | 4735
5 | 736 | 4736 | 0405803006 | Region IV-A (CALABARZON) | Rizal | Baras | Concepcion | 14.5215 | 121.2679 | R | 1095 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 59.99 | 41.94 | 59.99 |  | B - Node 0.5-1 km | 0.56 | 0.05 | Line: SEGMENT 22 (TAYTAY - FAMY) - DONE PAT | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4736
5 | 737 | 4737 | 0402117018 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa IV | 14.4031 | 120.8658 | R | 1019 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.76 | 1.77 | Tier 2 High GIDA (Score 40.0–49.9) | 59.99 | 41.94 | 59.99 |  | B - Node 0.5-1 km | 0.68 | 0.69 | Node: TRC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4737
5 | 738 | 4738 | PH0004738 | BARMM (LaMa+SGA) | Lanao Del Sur | Sultan Gumander (Picong) | Biasong | 17.2547 | 122.2287 | R | 2518 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.39 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.99 | 41.94 | 59.99 |  | F - Nearest node and line over 5 km | 29.39 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4738
5 | 739 | 4739 | 0501711002 | Region V (Bicol Region) | Camarines Sur | Caramoan | Antolon | 13.7935 | 123.7599 | R | 595 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.39 | 31.05 | Tier 2 High GIDA (Score 40.0–49.9) | 59.99 | 41.94 | 59.99 |  | F - Nearest node and line over 5 km | 11.39 | 31.02 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4739
5 | 740 | 4740 | 1408104008 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Karagawan | 17.917 | 121.1611 | R | 688 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.6 | 5.88 | Tier 2 High GIDA (Score 40.0–49.9) | 59.98 | 41.94 | 59.98 |  | F - Nearest node and line over 5 km | 11.6 | 21.69 | Node: KOY001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4740
5 | 741 | 4741 | 1402711003 | Cordillera Administrative Region (CAR) | Ifugao | Asipulo | Camandag | 16.5765 | 121.0149 | R | 4217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.2 | 15.7 | Tier 2 High GIDA (Score 40.0–49.9) | 59.98 | 41.94 | 59.98 |  | F - Nearest node and line over 5 km | 17.2 | 15.7 | Line: SEGMENT 14 (BAYOMBONG - ARITAO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4741
5 | 742 | 4742 | 0200902008 | Region II (Cagayan Valley) | Batanes | Itbayat | Santa Lucia | 20.7828 | 121.837 | R | 440 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 59.98 | 41.93 | 59.98 |  | F - Nearest node and line over 5 km | 255.22 | 251.32 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4742
5 | 743 | 4743 | 1903601008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bacolod-Kalawi | Dilabayan | 17.254 | 122.2285 | R | 829 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.98 | 41.93 | 59.98 |  | F - Nearest node and line over 5 km | 29.32 | 34.22 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4743
5 | 744 | 4744 | 1380200010 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Almanza Dos | 14.4186 | 121.0178 | U | 38003 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.11 | 0.96 | Tier 2 High GIDA (Score 40.0–49.9) | 59.97 | 41.93 | 59.97 |  | D - Other node or line within 3 km | 1.11 | 0.75 | Line: UG 144C via Y-Duct | Route options survey candidate: compare actual node lateral with approved line tap. | 4744
5 | 745 | 4745 | 0704613005 | Region VII (Central Visayas) | Negros Oriental | La Libertad | Busilak | 10.0727 | 123.1277 | R | 1425 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.29 | 12.47 | Tier 2 High GIDA (Score 40.0–49.9) | 59.96 | 41.92 | 59.96 |  | F - Nearest node and line over 5 km | 16.29 | 12.48 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4745
5 | 746 | 4746 | PH0004746 | IX | Zamboanga Del Sur | Zamboanga City | Barangay Zone II (Pob.) | 7.2037 | 122.2112 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.74 | 6.04 | Tier 2 High GIDA (Score 40.0–49.9) | 59.95 | 41.91 | 59.95 |  | D - Other node or line within 3 km | 6.84 | 1.57 | Line: CABLE INSTALLED | Route options survey candidate: compare actual node lateral with approved line tap. | 4746
5 | 747 | 4747 | 0300809009 | Region III (Central Luzon) | Bataan | Orani | Masantol | 14.8183 | 120.542 | R | 554 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.51 | 1.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.95 | 41.91 | 59.95 |  | D - Other node or line within 3 km | 1.91 | 1.92 | Node: ORB001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4747
5 | 748 | 4748 | 1001304006 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Embayao | 7.753 | 124.8852 | R | 1161 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.92 | 13.02 | Tier 2 High GIDA (Score 40.0–49.9) | 59.95 | 41.91 | 59.95 |  | F - Nearest node and line over 5 km | 7.92 | 12.88 | Node: DCR002 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4748
5 | 749 | 4749 | 0102805039 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | San Julian | 18.0891 | 120.5673 | R | 472 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.83 | 2.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.93 | 41.9 | 59.93 |  | C - Line within 0.5 km; node over 1 km | 3.97 | 0.11 | Line: SEGMENT 4 (BATAC - LAOAG CITY) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4749
5 | 750 | 4750 | 1381300089 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Ramon Magsaysay | 14.6616 | 121.0218 | U | 14922 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 59.93 | 41.9 | 59.93 |  | A - Node within 0.5 km | 0.17 | 0.16 | Line: UG 288C via Y-Duct | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4750
5 | 751 | 4751 | 1102319023 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo East | 7.4497 | 125.8167 | U | 16035 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.31 | 0.49 | Tier 2 High GIDA (Score 40.0–49.9) | 59.93 | 41.9 | 59.93 |  | C - Line within 0.5 km; node over 1 km | 1.31 | 0.47 | Line: DAVAO CITY - TRENTO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4751
5 | 752 | 4752 | 0601903007 | Region VI (Western Visayas) | Capiz | Dumalag | San Agustin | 11.3255 | 122.5927 | R | 707 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.93 | 3.89 | Tier 2 High GIDA (Score 40.0–49.9) | 59.92 | 41.89 | 59.92 |  | E - Nearest node or line 3-5 km | 11.93 | 3.85 | Line: CABLE LAYED | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4752
5 | 753 | 4753 | 1903611039 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Lumba-Bayabao | Gadongan | 7.869 | 124.3646 | R | 1235 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.31 | 34.21 | Tier 2 High GIDA (Score 40.0–49.9) | 59.92 | 41.89 | 59.92 |  | F - Nearest node and line over 5 km | 18.56 | 17.84 | Line: marawi new route 4km | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4753
5 | 754 | 4754 | PH0004754 | NCR | Metro Manila | Taguig City | Rizal | 14.6341 | 120.9805 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.88 | 0.85 | Tier 2 High GIDA (Score 40.0–49.9) | 59.91 | 41.88 | 59.91 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4754
5 | 755 | 4755 | 1380800003 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Buli | 14.9567 | 120.0885 | U | 13557 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.75 | 0.58 | Tier 2 High GIDA (Score 40.0–49.9) | 59.91 | 41.88 | 59.91 |  | B - Node 0.5-1 km | 0.75 | 0.02 | Line: BACKBONE ROUTE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4755
5 | 756 | 4756 | 0405647054 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Isidro Zone II | 14.0253 | 121.5849 | R | 432 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.5 | Tier 2 High GIDA (Score 40.0–49.9) | 59.9 | 41.88 | 59.9 |  | B - Node 0.5-1 km | 0.94 | 0.64 | Line: LBQ001 TO GCQ001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4756
5 | 757 | 4757 | 1380200016 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Pulang Lupa Dos | 14.4586 | 120.9867 | U | 32981 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.71 | 0.72 | Tier 2 High GIDA (Score 40.0–49.9) | 59.9 | 41.88 | 59.9 |  | B - Node 0.5-1 km | 0.71 | 0.56 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4757
5 | 758 | 4758 | 1381300139 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Batasan Hills | 14.6899 | 121.0941 | U | 173562 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.98 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.9 | 41.87 | 59.9 |  | B - Node 0.5-1 km | 0.98 | 0.04 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4758
5 | 759 | 4759 | 1001308019 | Region X (Northern Mindanao) | Bukidnon | Kibawe | Mascariñas | 7.4702 | 125.0253 | R | 844 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.48 | 8.8 | Tier 2 High GIDA (Score 40.0–49.9) | 59.89 | 41.87 | 59.89 |  | F - Nearest node and line over 5 km | 11.48 | 8.79 | Line: DAMULOG - VALENCIA - QUEZON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4759
5 | 760 | 4760 | 0603040039 | Region VI (Western Visayas) | Iloilo | San Joaquin | Igcores | 10.506 | 122.0387 | R | 586 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.55 | 6.91 | Tier 2 High GIDA (Score 40.0–49.9) | 59.89 | 41.87 | 59.89 |  | F - Nearest node and line over 5 km | 30.55 | 6.83 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4760
5 | 761 | 4761 | 0806019003 | Region VIII (Eastern Visayas) | Samar | Talalora | Mallorga | 11.5384 | 124.8671 | R | 429 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.86 | 32.42 | Tier 2 High GIDA (Score 40.0–49.9) | 59.89 | 41.87 | 59.89 |  | F - Nearest node and line over 5 km | 32.86 | 32.41 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4761
5 | 762 | 4762 | PH0004762 | IV-A | Cavite | Cavite City | Barangay 15 | 14.4761 | 120.893 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.71 | 3.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.87 | 41.86 | 59.87 |  | B - Node 0.5-1 km | 0.61 | 4.03 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4762
5 | 763 | 4763 | PH0004763 | IX | Zamboanga Del Sur | Zamboanga City | Barangay Zone III (Pob.) | 6.9598 | 122.0903 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.03 | 6.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.87 | 41.85 | 59.87 |  | D - Other node or line within 3 km | 5.8 | 1.82 | Line: CABLE INSTALLED | Route options survey candidate: compare actual node lateral with approved line tap. | 4763
5 | 764 | 4764 | PH0004764 | IV-A | Cavite | Cavite City | Barangay 1 | 14.4647 | 120.8842 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.2 | 2.17 | Tier 2 High GIDA (Score 40.0–49.9) | 59.86 | 41.85 | 59.86 |  | D - Other node or line within 3 km | 1.18 | 3.66 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4764
5 | 765 | 4765 | 1906607013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Kan Ukol | 17.2556 | 122.2296 | R | 1338 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 59.86 | 41.85 | 59.86 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4765
5 | 766 | 4766 | 0301412015 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Malhacan | 14.7399 | 120.9637 | U | 22515 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.55 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 59.86 | 41.85 | 59.86 |  | B - Node 0.5-1 km | 0.55 | 0.35 | Line: BOCAUE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4766
5 | 767 | 4767 | PH0004767 | IV-A | Cavite | Cavite City | Barangay 58 | 14.4707 | 120.8894 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.02 | 9.36 | Tier 2 High GIDA (Score 40.0–49.9) | 59.86 | 41.85 | 59.86 |  | A - Node within 0.5 km | 0.5 | 3.84 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4767
5 | 768 | 4768 | 0405622073 | Region IV-A (CALABARZON) | Quezon | Lopez | Santa Elena | 13.8201 | 122.2133 | R | 213 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.14 | 7.75 | Tier 2 High GIDA (Score 40.0–49.9) | 59.86 | 41.85 | 59.86 |  | F - Nearest node and line over 5 km | 9.14 | 7.73 | Line: LCQ001 TO LZQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4768
5 | 769 | 4769 | PH0004769 | NCR | Metro Manila | Taguig City | South Daang Hari | 14.6341 | 120.9805 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.46 | 0.06 | Tier 2 High GIDA (Score 40.0–49.9) | 59.85 | 41.84 | 59.85 |  | C - Line within 0.5 km; node over 1 km | 1.12 | 0.1 | Line: Aerial 24C | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4769
5 | 770 | 4770 | 0300809016 | Region III (Central Luzon) | Bataan | Orani | Centro I | 14.7893 | 120.5188 | R | 513 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.17 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.85 | 41.84 | 59.85 |  | D - Other node or line within 3 km | 2.36 | 1.06 | Line: 96C DONA TO ORANI | Route options survey candidate: compare actual node lateral with approved line tap. | 4770
5 | 771 | 4771 | PH0004771 | VIII | Leyte | Tacloban City | Barangay 91 | 11.2366 | 124.9845 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.98 | 3.81 | Tier 2 High GIDA (Score 40.0–49.9) | 59.85 | 41.84 | 59.85 |  | D - Other node or line within 3 km | 1.98 | 3.8 | Node: TCL002 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4771
5 | 772 | 4772 | 1380500025 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | San Jose | 14.58 | 121.0292 | U | 9283 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.85 | 41.84 | 59.85 |  | A - Node within 0.5 km | 0.42 | 0.06 | Line: Aerial 216C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4772
5 | 773 | 4773 | 1600309019 | Region XIII (Caraga) | Agusan del Sur | San Luis | Policarpo | 8.4396 | 125.6812 | R | 613 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.56 | 24.79 | Tier 2 High GIDA (Score 40.0–49.9) | 59.85 | 41.84 | 59.85 |  | F - Nearest node and line over 5 km | 31.56 | 24.72 | Line: FOC-96C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4773
5 | 774 | 4774 | 0501711001 | Region V (Bicol Region) | Camarines Sur | Caramoan | Agaas | 13.8104 | 123.8032 | R | 432 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.65 | 36.08 | Tier 2 High GIDA (Score 40.0–49.9) | 59.84 | 41.84 | 59.84 |  | F - Nearest node and line over 5 km | 7.65 | 36.05 | Node: COC001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4774
5 | 775 | 4775 | PH0004775 | XIII | Agusan Del Norte | Butuan City | Humabon Pob. | 8.7881 | 125.5888 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.69 | 9.04 | Tier 2 High GIDA (Score 40.0–49.9) | 59.84 | 41.84 | 59.84 |  | D - Other node or line within 3 km | 12.31 | 2.24 | Line: FOC-96C | Route options survey candidate: compare actual node lateral with approved line tap. | 4775
5 | 776 | 4776 | PH0004776 | CAR | Benguet | Baguio City | Phil-Am | 16.4 | 120.5862 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.44 | 1.26 | Tier 2 High GIDA (Score 40.0–49.9) | 59.84 | 41.83 | 59.84 |  | C - Line within 0.5 km; node over 1 km | 1.17 | 0 | Line: BAGUIO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4776
5 | 777 | 4777 | 1380900017 | National Capital Region (NCR) | Third District (Not a Province) | City of Navotas | Tangos North | 14.6621 | 120.9433 | U | 17891 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.54 | 0.43 | Tier 2 High GIDA (Score 40.0–49.9) | 59.83 | 41.83 | 59.83 |  | B - Node 0.5-1 km | 0.76 | 0.92 | Node: NAV001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4777
5 | 778 | 4778 | 1908824006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Talayan | Fukol | 6.9806 | 124.373 | R | 1079 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 39.95 | 39.5 | Tier 2 High GIDA (Score 40.0–49.9) | 59.83 | 41.83 | 59.83 |  | F - Nearest node and line over 5 km | 46.34 | 46.27 | Line: GENSAN - TACURONG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4778
5 | 779 | 4779 | PH0004779 | IV-A | Cavite | Cavite City | Barangay 18 | 14.4649 | 120.8848 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.4 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 59.83 | 41.83 | 59.83 |  | D - Other node or line within 3 km | 1.14 | 3.69 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4779
5 | 780 | 4780 | 1606813010 | Region XIII (Caraga) | Surigao del Sur | Madrid | San Roque | 9.22 | 125.9297 | R | 614 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.58 | 5.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.82 | 41.82 | 59.82 |  | F - Nearest node and line over 5 km | 16.58 | 5.97 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4780
5 | 781 | 4781 | PH0004781 | IV-A | Cavite | Cavite City | Barangay 38 | 14.4817 | 120.8929 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.95 | 4.54 | Tier 2 High GIDA (Score 40.0–49.9) | 59.81 | 41.82 | 59.81 |  | B - Node 0.5-1 km | 0.95 | 4.54 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4781
5 | 782 | 4782 | 1004213027 | Region X (Northern Mindanao) | Misamis Occidental | Sapang Dalaga | Disoy | 8.4487 | 123.5939 | R | 306 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 50.46 | 47.56 | Tier 2 High GIDA (Score 40.0–49.9) | 59.81 | 41.81 | 59.81 |  | F - Nearest node and line over 5 km | 50.46 | 47.55 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4782
5 | 783 | 4783 | 1004207023 | Region X (Northern Mindanao) | Misamis Occidental | Jimenez | Seti | 8.3143 | 123.775 | R | 498 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.29 | 25.07 | Tier 2 High GIDA (Score 40.0–49.9) | 59.81 | 41.81 | 59.81 |  | F - Nearest node and line over 5 km | 30.29 | 25.02 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4783
5 | 784 | 4784 | 0704612014 | Region VII (Central Visayas) | Negros Oriental | Jimalalud | Eli | 10.0153 | 123.1313 | R | 1779 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.84 | 8.37 | Tier 2 High GIDA (Score 40.0–49.9) | 59.81 | 41.81 | 59.81 |  | F - Nearest node and line over 5 km | 18.84 | 10.38 | Line: OPENTRENCHING 505m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4784
5 | 785 | 4785 | 1903604017 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Bubong Lilod | 17.2547 | 122.2288 | R | 967 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.8 | 41.81 | 59.8 |  | F - Nearest node and line over 5 km | 29.4 | 34.27 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4785
5 | 786 | 4786 | PH0004786 | IV-A | Cavite | Cavite City | Barangay 20 | 14.4765 | 120.8924 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.56 | 4.1 | Tier 2 High GIDA (Score 40.0–49.9) | 59.8 | 41.81 | 59.8 |  | B - Node 0.5-1 km | 0.56 | 4.1 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4786
5 | 787 | 4787 | 0401029027 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 3 | 13.8906 | 120.9406 | R | 729 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 59.8 | 41.81 | 59.8 |  | C - Line within 0.5 km; node over 1 km | 1.91 | 0.41 | Line: TUY - STA. TERESITA | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4787
5 | 788 | 4788 | 0403425008 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Magsaysay | 14.3391 | 121.0332 | U | 14023 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.71 | 3.82 | Tier 2 High GIDA (Score 40.0–49.9) | 59.8 | 41.81 | 59.8 |  | B - Node 0.5-1 km | 0.96 | 0.68 | Line: AE SPL002 TO SPL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4788
5 | 789 | 4789 | 1900707005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | Tuburan | Lahi-lahi | 10.6558 | 123.7916 | R | 3386 | 5.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.19 | 36.18 | Tier 2 High GIDA (Score 40.0–49.9) | 59.8 | 41.81 | 59.8 |  | C - Line within 0.5 km; node over 1 km | 18.37 | 0.03 | Line: 104.3km-96FOC-toledo-san remigio | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4789
5 | 790 | 4790 | 0803751010 | Region VIII (Eastern Visayas) | Leyte | Villaba | Capinyahan | 11.2179 | 124.4674 | R | 760 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.16 | 10.74 | Tier 2 High GIDA (Score 40.0–49.9) | 59.78 | 41.8 | 59.78 |  | F - Nearest node and line over 5 km | 8.16 | 10.74 | Node: MOL001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4790
5 | 791 | 4791 | 1381300027 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Damayan | 14.6386 | 121.0148 | U | 6259 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.89 | 0.22 | Tier 2 High GIDA (Score 40.0–49.9) | 59.78 | 41.79 | 59.78 |  | B - Node 0.5-1 km | 0.89 | 0.17 | Line: UG 288C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4791
5 | 792 | 4792 | PH0004792 | IV-A | Batangas | Lipa City | Bugtong na Pulo | 14.0004 | 121.1675 | R | 2259 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.3 | 0.24 | Tier 2 High GIDA (Score 40.0–49.9) | 59.78 | 41.79 | 59.78 |  | C - Line within 0.5 km; node over 1 km | 2.3 | 0.05 | Line: CLB001 TO BCY01 | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4792
5 | 793 | 4793 | 0205706003 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Dissimungal | 16.176 | 121.7657 | R | 2074 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.88 | 0.04 | Tier 2 High GIDA (Score 40.0–49.9) | 59.77 | 41.79 | 59.77 |  | C - Line within 0.5 km; node over 1 km | 10.88 | 0.02 | Line: NAGTIPUNAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4793
5 | 794 | 4794 | PH0004794 | VII | Cebu | Cebu City | Carreta | 10.3075 | 123.9088 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.3 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 59.76 | 41.78 | 59.76 |  | C - Line within 0.5 km; node over 1 km | 1.3 | 0.22 | Line: DANAO - CEBU | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4794
5 | 795 | 4795 | 1906616008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Panglima Estino | Tiptipon | 17.2558 | 122.2301 | R | 2476 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 59.75 | 41.77 | 59.75 |  | F - Nearest node and line over 5 km | 29.58 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4795
5 | 796 | 4796 | PH0004796 | IV-A | Cavite | Cavite City | Barangay 7 | 14.4926 | 120.9078 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.83 | 6.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.75 | 41.77 | 59.75 |  | D - Other node or line within 3 km | 2.94 | 5.03 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4796
5 | 797 | 4797 | 0603040042 | Region VI (Western Visayas) | Iloilo | San Joaquin | Iglilico | 10.6015 | 122.0469 | R | 265 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.23 | 1.74 | Tier 2 High GIDA (Score 40.0–49.9) | 59.74 | 41.77 | 59.74 |  | D - Other node or line within 3 km | 21.48 | 2.28 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Route options survey candidate: compare actual node lateral with approved line tap. | 4797
5 | 798 | 4798 | 1906609032 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Parang | Paugan | 17.2554 | 122.2294 | R | 970 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.5 | 34.37 | Tier 2 High GIDA (Score 40.0–49.9) | 59.74 | 41.76 | 59.74 |  | F - Nearest node and line over 5 km | 29.5 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4798
5 | 799 | 4799 | 1380800001 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Muntinlupa | Alabang | 14.9528 | 120.0891 | U | 72223 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.31 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 59.74 | 41.76 | 59.74 |  | A - Node within 0.5 km | 0.31 | 0.01 | Line: BACKBONE ROUTE | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4799
5 | 800 | 4800 | PH0004800 | XIII | Agusan Del Norte | Butuan City | San Ignacio Pob. | 8.8314 | 125.5964 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.71 | 9.9 | Tier 2 High GIDA (Score 40.0–49.9) | 59.73 | 41.76 | 59.73 |  | E - Nearest node or line 3-5 km | 8.08 | 4.19 | Line: FOC 96C | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4800
5 | 801 | 4801 | 1908819001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Rajah Buayan | Baital | 17.2552 | 122.2292 | R | 3124 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.72 | 41.75 | 59.72 |  | F - Nearest node and line over 5 km | 29.47 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4801
5 | 802 | 4802 | 1381400005 | National Capital Region (NCR) | Second District (Not a Province) | City of San Juan | Ermitaño | 16.6812 | 120.3534 | U | 6762 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 0.1 | Tier 2 High GIDA (Score 40.0–49.9) | 59.7 | 41.74 | 59.7 |  | D - Other node or line within 3 km | 4.21 | 1.36 | Line: SEGMENT 1 (SAN FERNANDO - CANDON) | Route options survey candidate: compare actual node lateral with approved line tap. | 4802
5 | 803 | 4803 | 1381300045 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Immaculate Concepcion | 9.2117 | 117.936 | U | 8512 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.32 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 59.7 | 41.74 | 59.7 |  | F - Nearest node and line over 5 km | 105.41 | 107.41 | Node: PPW002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4803
5 | 804 | 4804 | 1001318027 | Region X (Northern Mindanao) | Bukidnon | San Fernando | Bulalang | 7.7458 | 125.3658 | R | 911 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.17 | 2.86 | Tier 2 High GIDA (Score 40.0–49.9) | 59.7 | 41.73 | 59.7 |  | F - Nearest node and line over 5 km | 28.17 | 24.71 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4804
5 | 805 | 4805 | PH0004805 | VII | Cebu | Cebu City | Basak San Nicolas | 10.286 | 123.8707 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.13 | 0.44 | Tier 2 High GIDA (Score 40.0–49.9) | 59.69 | 41.73 | 59.69 |  | C - Line within 0.5 km; node over 1 km | 1.13 | 0.43 | Line: CEBU - TOLEDO | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4805
5 | 806 | 4806 | PH0004806 | IV-A | Cavite | Cavite City | Barangay 26 | 14.4827 | 120.9046 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6 | 5.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.69 | 41.73 | 59.69 |  | D - Other node or line within 3 km | 2.04 | 4.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4806
5 | 807 | 4807 | 1003516023 | Region X (Northern Mindanao) | Lanao del Norte | Pantao Ragat | Tongcopan | 8.0595 | 124.2027 | R | 1421 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.62 | 5.64 | Tier 2 High GIDA (Score 40.0–49.9) | 59.69 | 41.73 | 59.69 |  | F - Nearest node and line over 5 km | 9.62 | 5.57 | Line: PANTAR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4807
5 | 808 | 4808 | 1003518015 | Region X (Northern Mindanao) | Lanao del Norte | Salvador | Pagalongan | 7.9246 | 123.8987 | R | 862 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.05 | 9.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.68 | 41.72 | 59.68 |  | F - Nearest node and line over 5 km | 17.12 | 13.78 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4808
5 | 809 | 4809 | 0402103028 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row West | 14.4157 | 120.9527 | U | 11169 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.13 | 3.04 | Tier 2 High GIDA (Score 40.0–49.9) | 59.68 | 41.72 | 59.68 |  | D - Other node or line within 3 km | 1.62 | 3.29 | Node: IMC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4809
5 | 810 | 4810 | PH0004810 | IV-A | Cavite | Cavite City | Barangay 12 | 14.4706 | 120.8892 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 3.85 | Tier 2 High GIDA (Score 40.0–49.9) | 59.68 | 41.72 | 59.68 |  | B - Node 0.5-1 km | 0.5 | 3.85 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4810
5 | 811 | 4811 | 0907323002 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Ramon Magsaysay | Bambong Daku | 8.0202 | 123.4231 | R | 749 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.15 | 16.94 | Tier 2 High GIDA (Score 40.0–49.9) | 59.67 | 41.72 | 59.67 |  | F - Nearest node and line over 5 km | 19.49 | 19.27 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4811
5 | 812 | 4812 | 1408101001 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Butao | 18.378 | 120.9632 | R | 806 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.27 | 26.43 | Tier 2 High GIDA (Score 40.0–49.9) | 59.66 | 41.71 | 59.66 |  | F - Nearest node and line over 5 km | 19.51 | 19.13 | Line: SEGMENT 6 (BANGUI - CLAVERIA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4812
5 | 813 | 4813 | PH0004813 | VIII | Leyte | Tacloban City | Barangay 59 | 11.2601 | 124.9204 | R | 2258 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.54 | 14.52 | Tier 2 High GIDA (Score 40.0–49.9) | 59.66 | 41.71 | 59.66 |  | F - Nearest node and line over 5 km | 9.24 | 8.01 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4813
5 | 814 | 4814 | 0504113024 | Region V (Bicol Region) | Masbate | Mobo | Sawmill | 12.2549 | 123.6672 | R | 1068 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.15 | 12.64 | Tier 2 High GIDA (Score 40.0–49.9) | 59.66 | 41.71 | 59.66 |  | F - Nearest node and line over 5 km | 9.15 | 12.6 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4814
5 | 815 | 4815 | 0401003014 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 9 | 13.9334 | 120.7319 | R | 1825 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.59 | 0.14 | Tier 2 High GIDA (Score 40.0–49.9) | 59.65 | 41.7 | 59.65 |  | D - Other node or line within 3 km | 1.2 | 0.55 | Line: WP BYB001 TO BCY001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4815
5 | 816 | 4816 | 0403404009 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Mamatid | 14.2344 | 121.1584 | U | 66959 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.77 | 5.59 | Tier 2 High GIDA (Score 40.0–49.9) | 59.65 | 41.7 | 59.65 |  | D - Other node or line within 3 km | 2.91 | 2.16 | Line: RELIANCE TO SAN PABLO | Route options survey candidate: compare actual node lateral with approved line tap. | 4816
5 | 817 | 4817 | 0401029030 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 6 | 13.8818 | 120.9248 | R | 912 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.49 | 0.25 | Tier 2 High GIDA (Score 40.0–49.9) | 59.65 | 41.7 | 59.65 |  | D - Other node or line within 3 km | 1.08 | 1.32 | Node: TLB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4817
5 | 818 | 4818 | 1004325006 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Mahayag | 8.9634 | 124.949 | R | 403 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.4 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.65 | 41.7 | 59.65 |  | B - Node 0.5-1 km | 0.66 | 0.19 | Line: CDO - BUENAVISTA via GINGOOG | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4818
5 | 819 | 4819 | 1001309025 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Panganan | 7.5987 | 125.3553 | R | 1890 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.96 | 11.42 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.7 | 59.64 |  | F - Nearest node and line over 5 km | 17.96 | 14.65 | Line: MALAYBALAY - KITAOTAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4819
5 | 820 | 4820 | 0504103030 | Region V (Bicol Region) | Masbate | Balud | Tonga | 12.0681 | 123.2379 | R | 1044 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.29 | 14.62 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.7 | 59.64 |  | A - Node within 0.5 km | 0.29 | 33.81 | Node: BDM001 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4820
5 | 821 | 4821 | 1404408004 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Bekigan | 17.1824 | 121.0127 | R | 499 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.79 | 3.92 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.7 | 59.64 |  | E - Nearest node or line 3-5 km | 3.79 | 3.62 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4821
5 | 822 | 4822 | 0402104012 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 1 | 14.2989 | 121.049 | R | 3303 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.53 | 1.49 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.69 | 59.64 |  | D - Other node or line within 3 km | 1.17 | 1.34 | Node: BNL003 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 4822
5 | 823 | 4823 | PH0004823 | IV-A | Cavite | Cavite City | Barangay 54 | 14.4808 | 120.9011 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.6 | 4.04 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.69 | 59.64 |  | D - Other node or line within 3 km | 1.6 | 4.03 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4823
5 | 824 | 4824 | 1204701005 | Region XII (SOCCSKSARGEN) | Cotabato | Alamada | Guiling | 7.476 | 124.6609 | U | 4968 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.61 | 17.76 | Tier 2 High GIDA (Score 40.0–49.9) | 59.64 | 41.69 | 59.64 |  | F - Nearest node and line over 5 km | 30.61 | 17.72 | Line: MATALAM - CARMEN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4824
5 | 825 | 4825 | 1380500026 | National Capital Region (NCR) | Second District (Not a Province) | City of Mandaluyong | Vergara | 14.5772 | 121.0251 | U | 4768 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.78 | 0.52 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.69 | 59.63 |  | B - Node 0.5-1 km | 0.78 | 0.52 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4825
5 | 826 | 4826 | PH0004826 | IV-A | Cavite | Imus City | Toclong I-A | 14.3734 | 120.9667 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.63 | 0.69 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.69 | 59.63 |  | D - Other node or line within 3 km | 2.24 | 7.78 | Node: IMC004 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4826
5 | 827 | 4827 | 1903603001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Balindong | Abaga | 7.882 | 124.2091 | R | 875 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.34 | 34.23 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.69 | 59.63 |  | F - Nearest node and line over 5 km | 15.94 | 13.64 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4827
5 | 828 | 4828 | PH0004828 | XIII | Agusan Del Norte | Butuan City | Leon Kilat Pob. | 17.1045 | 122.2746 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.29 | 7.54 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.69 | 59.63 |  | F - Nearest node and line over 5 km | 27.58 | 37.66 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4828
5 | 829 | 4829 | 0803751020 | Region VIII (Eastern Visayas) | Leyte | Villaba | New Balanac | 11.1831 | 124.4857 | R | 721 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.59 | 8.1 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.69 | 59.63 |  | E - Nearest node or line 3-5 km | 4.59 | 8.1 | Node: MOL001 - BP | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4829
5 | 830 | 4830 | PH0004830 | IV-A | Cavite | City of Bacoor | Mambog 2 | 14.4042 | 120.9975 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.09 | 2.46 | Tier 2 High GIDA (Score 40.0–49.9) | 59.63 | 41.68 | 59.63 |  | D - Other node or line within 3 km | 2.33 | 3.03 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4830
5 | 831 | 4831 | 0506204018 | Region V (Bicol Region) | Sorsogon | Bulusan | San Jose | 12.7601 | 124.1265 | R | 1023 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.95 | 0.97 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | B - Node 0.5-1 km | 0.95 | 11.7 | Node: BSS001 - BP | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4831
5 | 832 | 4832 | 0405622061 | Region IV-A (CALABARZON) | Quezon | Lopez | Samat | 13.8596 | 122.2966 | R | 241 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.82 | 2.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | D - Other node or line within 3 km | 4.82 | 2.37 | Line: LZQ001 TO MCQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4832
5 | 833 | 4833 | 0806006052 | Region VIII (Eastern Visayas) | Samar | Daram | Tugas | 11.5431 | 124.803 | R | 768 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.75 | 29.68 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | F - Nearest node and line over 5 km | 29.75 | 29.68 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4833
5 | 834 | 4834 | PH0004834 | IV-A | Cavite | City of Bacoor | Ligas 2 | 14.3727 | 120.981 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.5 | 1.63 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | D - Other node or line within 3 km | 2.52 | 6.89 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4834
5 | 835 | 4835 | 0405646005 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Bosigon | 14.0803 | 122.5383 | R | 390 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.64 | 7.36 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | F - Nearest node and line over 5 km | 10.64 | 7.36 | Line: CALAUAG - SIPOCOT | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4835
5 | 836 | 4836 | PH0004836 | VIII | Samar (Western Samar) | Catbalogan City | Muñoz | 11.7798 | 124.8844 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.51 | 36.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.62 | 41.68 | 59.62 |  | F - Nearest node and line over 5 km | 57.45 | 57.38 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4836
5 | 837 | 4837 | 1408104007 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Cabetayan | 17.999 | 121.1738 | R | 608 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.41 | 7.9 | Tier 2 High GIDA (Score 40.0–49.9) | 59.61 | 41.68 | 59.61 |  | D - Other node or line within 3 km | 2.41 | 27.52 | Node: KOY001 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 4837
5 | 838 | 4838 | 1906604012 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Luuk | Lambago | 17.2555 | 122.2296 | R | 2589 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.52 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.61 | 41.68 | 59.61 |  | F - Nearest node and line over 5 km | 29.52 | 34.38 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4838
5 | 839 | 4839 | 1208002021 | Region XII (SOCCSKSARGEN) | Sarangani | Glan | New Aklan | 5.7636 | 125.3396 | R | 1809 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.57 | 42.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.61 | 41.67 | 59.61 |  | F - Nearest node and line over 5 km | 38.57 | 42.97 | Node: ALS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4839
5 | 840 | 4840 | PH0004840 | VII | Bohol | Jetafe | Alumar | 10.1912 | 124.2043 | R | 2229 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.24 | 1.99 | Tier 2 High GIDA (Score 40.0–49.9) | 59.6 | 41.67 | 59.6 |  | F - Nearest node and line over 5 km | 25.77 | 29.27 | Node: LUC002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4840
5 | 841 | 4841 | 0405802009 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Roque | 14.5844 | 121.1737 | U | 67126 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.35 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 59.6 | 41.67 | 59.6 |  | A - Node within 0.5 km | 0.35 | 0.07 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4841
5 | 842 | 4842 | 1003506036 | Region X (Northern Mindanao) | Lanao del Norte | Sultan Naga Dimaporo | Dalama | 7.7101 | 123.8104 | R | 930 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 25.66 | 11.84 | Tier 2 High GIDA (Score 40.0–49.9) | 59.6 | 41.66 | 59.6 |  | F - Nearest node and line over 5 km | 36.55 | 20.63 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4842
5 | 843 | 4843 | 1003517013 | Region X (Northern Mindanao) | Lanao del Norte | Poona Piagapo | Lupitan | 8.0933 | 124.1469 | R | 1019 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 16.02 | 9.22 | Tier 2 High GIDA (Score 40.0–49.9) | 59.6 | 41.66 | 59.6 |  | F - Nearest node and line over 5 km | 16.81 | 7.77 | Line: 216f feeder iligan completed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4843
5 | 844 | 4844 | 1381300118 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Talayan | 14.0649 | 122.0838 | U | 4587 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.2 | 0.23 | Tier 2 High GIDA (Score 40.0–49.9) | 59.59 | 41.66 | 59.59 |  | F - Nearest node and line over 5 km | 13.83 | 13.76 | Line: PAGBILAO - NAGA (UG + Aerial) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4844
5 | 845 | 4845 | 0405603024 | Region IV-A (CALABARZON) | Quezon | Atimonan | Manggalayan Bundok | 13.9343 | 121.9154 | R | 148 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.62 | 3.99 | Tier 2 High GIDA (Score 40.0–49.9) | 59.59 | 41.66 | 59.59 |  | E - Nearest node or line 3-5 km | 6.62 | 3.91 | Line: LCQ001 TO MCQ001 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4845
5 | 846 | 4846 | PH0004846 | XI | Davao Del Sur | Davao City | Leon Garcia, Sr. | 7.0824 | 125.6268 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.23 | 0.26 | Tier 2 High GIDA (Score 40.0–49.9) | 59.59 | 41.66 | 59.59 |  | D - Other node or line within 3 km | 2.23 | 1.56 | Line: DAVAO CITY - TRENTO | Route options survey candidate: compare actual node lateral with approved line tap. | 4846
5 | 847 | 4847 | 1381300022 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Commonwealth | 14.69 | 121.0992 | U | 222177 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.81 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 59.58 | 41.65 | 59.58 |  | B - Node 0.5-1 km | 0.81 | 0.17 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4847
5 | 848 | 4848 | 0401029024 | Region IV-A (CALABARZON) | Batangas | Taal | Poblacion 10 | 13.871 | 120.9401 | R | 786 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.83 | 1.57 | Tier 2 High GIDA (Score 40.0–49.9) | 59.58 | 41.65 | 59.58 |  | D - Other node or line within 3 km | 2.55 | 1.41 | Line: LEMERY TO SAN JUAN CLS | Route options survey candidate: compare actual node lateral with approved line tap. | 4848
5 | 849 | 4849 | 1907001013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Kulape | 17.256 | 122.2305 | R | 2676 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 2 High GIDA (Score 40.0–49.9) | 59.58 | 41.65 | 59.58 |  | F - Nearest node and line over 5 km | 29.63 | 34.49 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4849
5 | 850 | 4850 | PH0004850 | VI | Capiz | Roxas City | Poblacion II | 11.5941 | 122.7822 | R | 2282 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.1 | 1.62 | Tier 2 High GIDA (Score 40.0–49.9) | 59.58 | 41.65 | 59.58 |  | D - Other node or line within 3 km | 3.73 | 1.01 | Line: ROXAS - SARA | Route options survey candidate: compare actual node lateral with approved line tap. | 4850
5 | 851 | 4851 | 0401006032 | Region IV-A (CALABARZON) | Batangas | Bauan | San Andres Uno | 13.8001 | 120.9434 | R | 622 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.05 | 2.08 | Tier 2 High GIDA (Score 40.0–49.9) | 59.57 | 41.65 | 59.57 |  | E - Nearest node or line 3-5 km | 3.7 | 5.67 | Node: BUN002 - PM | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4851
5 | 852 | 4852 | 1908814003 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Mangudadatu | Luayan | 17.2558 | 122.229 | R | 3132 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.98 | 33.7 | Tier 2 High GIDA (Score 40.0–49.9) | 59.57 | 41.64 | 59.57 |  | F - Nearest node and line over 5 km | 29.5 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4852
5 | 853 | 4853 | PH0004853 | NIR | Negros Oriental | Dumaguete City | Poblacion No. 7 | 9.3091 | 123.3044 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.38 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 59.56 | 41.64 | 59.56 |  | A - Node within 0.5 km | 0.38 | 0.11 | Line: DUMAGUETE UPLINK | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4853
5 | 854 | 4854 | 0402103027 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row East | 14.4384 | 120.9811 | U | 19338 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.63 | 0.75 | Tier 2 High GIDA (Score 40.0–49.9) | 59.56 | 41.64 | 59.56 |  | D - Other node or line within 3 km | 2.24 | 1.15 | Line: Aerial 216C MTF | Route options survey candidate: compare actual node lateral with approved line tap. | 4854
5 | 855 | 4855 | 1906616004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Panglima Estino | Lihbug Kabaw | 17.256 | 122.2288 | R | 2498 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.56 | 41.64 | 59.56 |  | F - Nearest node and line over 5 km | 29.49 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4855
5 | 856 | 4856 | 0702206019 | Region VII (Central Visayas) | Cebu | Asturias | Saksak | 10.5346 | 123.8708 | R | 322 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.21 | 14.74 | Tier 2 High GIDA (Score 40.0–49.9) | 59.55 | 41.63 | 59.55 |  | F - Nearest node and line over 5 km | 12.21 | 14.69 | Node: CCY006 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4856
5 | 857 | 4857 | 1906607040 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Tinah | 17.2563 | 122.2297 | R | 717 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.3 | 35.51 | Tier 2 High GIDA (Score 40.0–49.9) | 59.55 | 41.63 | 59.55 |  | F - Nearest node and line over 5 km | 29.59 | 34.42 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4857
5 | 858 | 4858 | 0907317008 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Margosatubig | Kolot | 7.5578 | 123.1229 | R | 509 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.53 | 19.91 | Tier 2 High GIDA (Score 40.0–49.9) | 59.54 | 41.63 | 59.54 |  | F - Nearest node and line over 5 km | 20.53 | 19.9 | Line: BUUG - IPIL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4858
5 | 859 | 4859 | 1907001015 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Magsaggaw | 17.2549 | 122.2291 | R | 3479 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 2 High GIDA (Score 40.0–49.9) | 59.54 | 41.62 | 59.54 |  | F - Nearest node and line over 5 km | 29.44 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4859
5 | 860 | 4860 | PH0004860 | XI | Davao Del Sur | Davao City | Buhangin (Pob.) | 7.1131 | 125.6312 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.99 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 59.52 | 41.61 | 59.52 |  | B - Node 0.5-1 km | 0.99 | 0.09 | Line: DAVAO CITY - TRENTO | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4860
5 | 861 | 4861 | 0201505004 | Region II (Cagayan Valley) | Cagayan | Aparri | Bisagu | 18.348 | 121.6187 | R | 1830 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.06 | 8.33 | Tier 2 High GIDA (Score 40.0–49.9) | 59.51 | 41.61 | 59.51 |  | D - Other node or line within 3 km | 2.06 | 8.33 | Node: ARC001 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4861
5 | 862 | 4862 | 1600303027 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Taganahaw | 8.696 | 125.6724 | R | 403 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.45 | 3.4 | Tier 2 High GIDA (Score 40.0–49.9) | 59.51 | 41.61 | 59.51 |  | E - Nearest node or line 3-5 km | 9.45 | 3.4 | Line: FOC-96C | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4862
5 | 863 | 4863 | 1907002031 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Silubog | 17.2565 | 122.2302 | R | 1849 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.43 | 23.72 | Tier 2 High GIDA (Score 40.0–49.9) | 59.51 | 41.6 | 59.51 |  | F - Nearest node and line over 5 km | 29.64 | 34.47 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4863
5 | 864 | 4864 | 1001311009 | Region X (Northern Mindanao) | Bukidnon | Libona | Palabucan | 8.3989 | 124.7815 | R | 1829 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.15 | 4.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.51 | 41.6 | 59.51 |  | E - Nearest node or line 3-5 km | 6.15 | 4.48 | Line: CAGAYAN DE ORO - MALAYBALAY | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4864
5 | 865 | 4865 | PH0004865 | IX | Zamboanga Del Sur | Zamboanga City | Barangay Zone IV (Pob.) | 7.1266 | 121.9167 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 20.7 | 7.4 | Tier 2 High GIDA (Score 40.0–49.9) | 59.51 | 41.6 | 59.51 |  | F - Nearest node and line over 5 km | 29.64 | 28.23 | Line: CABLE INSTALLED | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4865
5 | 866 | 4866 | 1606710005 | Region XIII (Caraga) | Surigao del Norte | General Luna | Corazon | 9.8143 | 126.1071 | R | 500 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.59 | 41.25 | Tier 2 High GIDA (Score 40.0–49.9) | 59.5 | 41.6 | 59.5 |  | F - Nearest node and line over 5 km | 52.59 | 41.24 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4866
5 | 867 | 4867 | PH0004867 | I | Pangasinan | San Carlos City | Burgos Padlan (Pob.) | 15.9455 | 120.3231 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.59 | 2.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.5 | 41.6 | 59.5 |  | E - Nearest node or line 3-5 km | 3.35 | 3.35 | Node: SCP001 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4867
5 | 868 | 4868 | 0506207022 | Region V (Bicol Region) | Sorsogon | Donsol | Malinao | 12.9775 | 123.5425 | R | 284 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.77 | 19.2 | Tier 2 High GIDA (Score 40.0–49.9) | 59.49 | 41.59 | 59.49 |  | F - Nearest node and line over 5 km | 9.77 | 19.14 | Node: DLS001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4868
5 | 869 | 4869 | 0706101011 | Region VII (Central Visayas) | Siquijor | Enrique Villanueva | Olave | 9.2957 | 123.6214 | R | 217 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.6 | 25.96 | Tier 2 High GIDA (Score 40.0–49.9) | 59.49 | 41.59 | 59.49 |  | F - Nearest node and line over 5 km | 32.47 | 32.19 | Line: Oslob-Santander | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4869
5 | 870 | 4870 | 0804824008 | Region VIII (Eastern Visayas) | Northern Samar | Lope De Vega | Getigo | 12.2748 | 124.6112 | R | 932 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 67.14 | 67.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.49 | 41.59 | 59.49 |  | F - Nearest node and line over 5 km | 67.14 | 67.11 | Line: PROPOSED 96CCORE AERIAL PROTECTION FOC LINK FROM GUBAT TO STA. MAGDALENA SORSOGON | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4870
5 | 871 | 4871 | PH0004871 | XIII | Agusan Del Norte | Butuan City | Urduja Pob. | 17.104 | 122.2731 | R | 2294 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.84 | 10.3 | Tier 2 High GIDA (Score 40.0–49.9) | 59.49 | 41.59 | 59.49 |  | F - Nearest node and line over 5 km | 27.42 | 37.51 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4871
5 | 872 | 4872 | 0803728034 | Region VIII (Eastern Visayas) | Leyte | La Paz | Tabang | 17.6306 | 120.6207 | R | 75 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.45 | 8.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.48 | 41.59 | 59.48 |  | C - Line within 0.5 km; node over 1 km | 4.22 | 0.14 | Line: CABLE LAYED | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4872
5 | 873 | 4873 | PH0004873 | NIR | Negros Oriental | Dumaguete City | Poblacion No. 5 | 9.2767 | 123.2874 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.05 | 0.9 | Tier 2 High GIDA (Score 40.0–49.9) | 59.48 | 41.59 | 59.48 |  | D - Other node or line within 3 km | 2.68 | 0.6 | Line: KABANGKALAN - BACONG | Route options survey candidate: compare actual node lateral with approved line tap. | 4873
5 | 874 | 4874 | 0201510023 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Tagum | 18.2513 | 121.686 | R | 233 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.74 | 0.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.48 | 41.58 | 59.48 |  | C - Line within 0.5 km; node over 1 km | 1.08 | 0.02 | Line: SEGMENT 30 (LAL-LO - STA ANA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4874
5 | 875 | 4875 | 0205008003 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Banila | 16.2072 | 121.0972 | R | 915 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.01 | 10.92 | Tier 2 High GIDA (Score 40.0–49.9) | 59.47 | 41.58 | 59.47 |  | F - Nearest node and line over 5 km | 10.01 | 10.92 | Node: DSV001 - TYPE 4A | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4875
5 | 876 | 4876 | 0907303006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Camp Blessing | 7.8848 | 123.0683 | R | 482 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.29 | 12.7 | Tier 2 High GIDA (Score 40.0–49.9) | 59.47 | 41.58 | 59.47 |  | F - Nearest node and line over 5 km | 17.29 | 12.69 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4876
5 | 877 | 4877 | 0301412026 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Caingin | 14.7268 | 120.9688 | U | 7207 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.29 | 0.82 | Tier 2 High GIDA (Score 40.0–49.9) | 59.46 | 41.57 | 59.46 |  | D - Other node or line within 3 km | 1.29 | 0.82 | Line: GOTACO TO HH 71 BULACAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4877
5 | 878 | 4878 | 1903604027 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Bayang | Cadingilan Occidental | 17.2548 | 122.2285 | R | 909 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.24 | 42.88 | Tier 2 High GIDA (Score 40.0–49.9) | 59.46 | 41.57 | 59.46 |  | F - Nearest node and line over 5 km | 29.38 | 34.25 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4878
5 | 879 | 4879 | 0907328002 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tambulig | Bag-ong Kauswagan | 8.126 | 123.2979 | R | 745 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.34 | 30.94 | Tier 2 High GIDA (Score 40.0–49.9) | 59.46 | 41.57 | 59.46 |  | F - Nearest node and line over 5 km | 36.34 | 30.92 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4879
5 | 880 | 4880 | 0704602015 | Region VII (Central Visayas) | Negros Oriental | Ayungon | Maaslum | 9.8594 | 123.0948 | R | 1813 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 23.34 | 4.66 | Tier 2 High GIDA (Score 40.0–49.9) | 59.46 | 41.57 | 59.46 |  | F - Nearest node and line over 5 km | 23.34 | 16.59 | Line: OPEN TRENCH 1,645m | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4880
5 | 881 | 4881 | 0103314009 | Region I (Ilocos Region) | La Union | City of San Fernando | Barangay IV | 10.1329 | 123.6888 | U | 613 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.12 | 4.03 | Tier 2 High GIDA (Score 40.0–49.9) | 59.45 | 41.56 | 59.45 |  | C - Line within 0.5 km; node over 1 km | 3.89 | 0.1 | Line: 216f | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4881
5 | 882 | 4882 | 1380700011 | National Capital Region (NCR) | Second District (Not a Province) | City of Marikina | Tañong | 14.6341 | 121.0854 | U | 9200 | 4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1 | 0.38 | Tier 2 High GIDA (Score 40.0–49.9) | 59.45 | 41.56 | 59.45 |  | D - Other node or line within 3 km | 1.01 | 0.99 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4882
5 | 883 | 4883 | 1102315041 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Pedro | 7.2975 | 125.7109 | U | 3465 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.39 | 3.23 | Tier 2 High GIDA (Score 40.0–49.9) | 59.44 | 41.56 | 59.44 |  | E - Nearest node or line 3-5 km | 3.39 | 3.22 | Line: DAVAO CITY - TRENTO | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4883
5 | 884 | 4884 | 1907001001 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Panglima Sugala | Balimbing Proper | 17.2556 | 122.2293 | U | 5731 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 2 High GIDA (Score 40.0–49.9) | 59.44 | 41.56 | 59.44 |  | F - Nearest node and line over 5 km | 29.51 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4884
5 | 885 | 4885 | 1408101010 | Cordillera Administrative Region (CAR) | Apayao | Calanasan | Tubongan | 18.4337 | 121.2621 | R | 398 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 18.09 | 26.82 | Tier 2 High GIDA (Score 40.0–49.9) | 59.44 | 41.56 | 59.44 |  | F - Nearest node and line over 5 km | 8.94 | 8.39 | Line: SEGMENT 8 (PAMPLONA - LAL-LO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4885
5 | 886 | 4886 | PH0004886 | IV-A | Cavite | Cavite City | Barangay 49 | 14.4248 | 120.8919 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.09 | 0.15 | Tier 2 High GIDA (Score 40.0–49.9) | 59.44 | 41.55 | 59.44 |  | C - Line within 0.5 km; node over 1 km | 1.09 | 0.15 | Line: KAWIT | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4886
5 | 887 | 4887 | 1381000008 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Parañaque | Don Bosco | 14.4886 | 121.0261 | U | 55229 | 3.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.54 | 0.17 | Tier 2 High GIDA (Score 40.0–49.9) | 59.44 | 41.55 | 59.44 |  | B - Node 0.5-1 km | 0.54 | 0.13 | Line: UG 144C via Y-Duct | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4887
5 | 888 | 4888 | 0301411016 | Region III (Central Luzon) | Bulacan | Marilao | Tabing Ilog | 14.7649 | 120.9489 | U | 8421 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.42 | 41.54 | 59.42 |  | C - Line within 0.5 km; node over 1 km | 1.07 | 0.28 | Line: GOTACO TO HH 71 BULACAN | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4888
5 | 889 | 4889 | PH0004889 | NIR | Negros Oriental | Dumaguete City | Poblacion No. 3 | 9.2814 | 123.2741 | R | 2279 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.01 | 1.18 | Tier 2 High GIDA (Score 40.0–49.9) | 59.42 | 41.54 | 59.42 |  | D - Other node or line within 3 km | 3.3 | 2.1 | Line: KABANGKALAN - BACONG | Route options survey candidate: compare actual node lateral with approved line tap. | 4889
5 | 890 | 4890 | 0802607020 | Region VIII (Eastern Visayas) | Eastern Samar | General Macarthur | Quirino | 11.2178 | 125.5173 | R | 218 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 55.4 | 54.26 | Tier 2 High GIDA (Score 40.0–49.9) | 59.42 | 41.54 | 59.42 |  | F - Nearest node and line over 5 km | 55.4 | 55.4 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4890
5 | 891 | 4891 | 1906613029 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Talipao | Lower Binuang | 17.2551 | 122.2304 | R | 1758 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.75 | 33.94 | Tier 2 High GIDA (Score 40.0–49.9) | 59.41 | 41.53 | 59.41 |  | F - Nearest node and line over 5 km | 29.56 | 34.45 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4891
5 | 892 | 4892 | 0405813005 | Region IV-A (CALABARZON) | Rizal | Taytay | Santa Ana | 14.5372 | 121.1093 | U | 102828 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.68 | 0.58 | Tier 2 High GIDA (Score 40.0–49.9) | 59.41 | 41.53 | 59.41 |  | B - Node 0.5-1 km | 0.68 | 0.57 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4892
5 | 893 | 4893 | 0500513029 | Region V (Bicol Region) | Albay | Pio Duran | Salvacion | 13.0836 | 123.5056 | R | 603 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.59 | 15.73 | Tier 2 High GIDA (Score 40.0–49.9) | 59.41 | 41.53 | 59.41 |  | F - Nearest node and line over 5 km | 5.59 | 15.63 | Node: PDA001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4893
5 | 894 | 4894 | 1903610009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapai | Doronan | 17.2544 | 122.2284 | R | 1464 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.35 | 34.24 | Tier 2 High GIDA (Score 40.0–49.9) | 59.4 | 41.53 | 59.4 |  | F - Nearest node and line over 5 km | 29.35 | 34.23 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4894
5 | 895 | 4895 | 0405802004 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mayamot | 14.6297 | 121.1209 | U | 50271 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.24 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.4 | 41.53 | 59.4 |  | A - Node within 0.5 km | 0.24 | 0.12 | Line: Aerial 96C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4895
5 | 896 | 4896 | 0405647009 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angustias Zone III | 14.0003 | 121.5686 | R | 381 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.45 | 2.24 | Tier 2 High GIDA (Score 40.0–49.9) | 59.4 | 41.52 | 59.4 |  | D - Other node or line within 3 km | 3.75 | 2.78 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 4896
5 | 897 | 4897 | 0200902009 | Region II (Cagayan Valley) | Batanes | Itbayat | Santa Maria | 20.7872 | 121.8417 | R | 491 | 3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 59.4 | 41.52 | 59.4 |  | F - Nearest node and line over 5 km | 255.81 | 251.93 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4897
5 | 898 | 4898 | 1907002043 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Ungus-ungus | 17.2555 | 122.2291 | R | 1323 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.44 | 25.06 | Tier 2 High GIDA (Score 40.0–49.9) | 59.39 | 41.52 | 59.39 |  | F - Nearest node and line over 5 km | 29.48 | 34.33 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4898
5 | 899 | 4899 | 0504113022 | Region V (Bicol Region) | Masbate | Mobo | Sambulawan | 12.2831 | 123.6222 | R | 379 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.16 | 7.46 | Tier 2 High GIDA (Score 40.0–49.9) | 59.39 | 41.52 | 59.39 |  | F - Nearest node and line over 5 km | 7.16 | 7.41 | Node: MOM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4899
5 | 900 | 4900 | 1903620011 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pagayawan | Biala-an | 17.255 | 122.2295 | R | 526 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.55 | 33.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.39 | 41.52 | 59.39 |  | F - Nearest node and line over 5 km | 29.48 | 34.36 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4900
5 | 901 | 4901 | PH0004901 | IV-A | Cavite | City of Bacoor | P.F. Espiritu 2 | 14.4038 | 120.9963 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.33 | 3 | Tier 2 High GIDA (Score 40.0–49.9) | 59.38 | 41.51 | 59.38 |  | D - Other node or line within 3 km | 2.2 | 3.15 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4901
5 | 902 | 4902 | 0401012033 | Region IV-A (CALABARZON) | Batangas | Lemery | District II | 13.8853 | 120.9144 | U | 622 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.89 | 2.45 | Tier 2 High GIDA (Score 40.0–49.9) | 59.38 | 41.51 | 59.38 |  | D - Other node or line within 3 km | 1.09 | 1.25 | Node: TLB001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4902
5 | 903 | 4903 | 1907002046 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Pagatpat | 5.0329 | 119.7735 | R | 1104 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 999 | 999 | Tier 2 High GIDA (Score 40.0–49.9) | 59.38 | 41.51 | 59.38 |  | F - Nearest node and line over 5 km | 329.07 | 329.07 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4903
5 | 904 | 4904 | PH0004904 | IV-A | Cavite | Cavite City | Barangay 59 | 14.4829 | 120.8967 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.16 | 10.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.37 | 41.51 | 59.37 |  | D - Other node or line within 3 km | 1.33 | 4.46 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4904
5 | 905 | 4905 | PH0004905 | IV-A | Cavite | City of Bacoor | Talaba 1 | 14.4076 | 120.9931 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.4 | 7.38 | Tier 2 High GIDA (Score 40.0–49.9) | 59.36 | 41.5 | 59.36 |  | D - Other node or line within 3 km | 2.14 | 3.04 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4905
5 | 906 | 4906 | 1903605022 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Picalilangan | 17.2548 | 122.2288 | R | 1032 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 59.36 | 41.5 | 59.36 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4906
5 | 907 | 4907 | 0402116008 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose I | 14.4313 | 120.8793 | R | 1532 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.91 | 0.87 | Tier 2 High GIDA (Score 40.0–49.9) | 59.36 | 41.5 | 59.36 |  | A - Node within 0.5 km | 0.44 | 0.41 | Line: NOVELETA | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4907
5 | 908 | 4908 | 0405647049 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Diego Zone I | 14.0593 | 121.6338 | R | 385 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.06 | 0.62 | Tier 2 High GIDA (Score 40.0–49.9) | 59.36 | 41.5 | 59.36 |  | F - Nearest node and line over 5 km | 5.88 | 5.67 | Line: LBQ001 TO GCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4908
5 | 909 | 4909 | 0402108003 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Gov. Ferrer Pob. | 14.3875 | 120.8786 | R | 261 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.74 | 3.72 | Tier 2 High GIDA (Score 40.0–49.9) | 59.36 | 41.5 | 59.36 |  | D - Other node or line within 3 km | 1.51 | 1.52 | Node: TZC003 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4909
5 | 910 | 4910 | 0402108010 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Prinza Pob. | 14.3465 | 120.881 | U | 540 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.53 | 3.59 | Tier 2 High GIDA (Score 40.0–49.9) | 59.35 | 41.49 | 59.35 |  | E - Nearest node or line 3-5 km | 3.77 | 3.63 | Line: TANZA | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4910
5 | 911 | 4911 | PH0004911 | XII | South Cotabato | General Santos City (Dadiangas) | Lagao | 6.1313 | 125.185 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.72 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.35 | 41.49 | 59.35 |  | D - Other node or line within 3 km | 1.72 | 0.61 | Line: DAVAO CITY - GENSAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4911
5 | 912 | 4912 | 0201509004 | Region II (Cagayan Valley) | Cagayan | Calayan | Dibay | 19.3764 | 121.3981 | R | 1706 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 92.54 | 88.42 | Tier 2 High GIDA (Score 40.0–49.9) | 59.35 | 41.49 | 59.35 |  | F - Nearest node and line over 5 km | 92.54 | 88.41 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4912
5 | 913 | 4913 | PH0004913 | CAR | Benguet | Baguio City | Bayan Park West | 16.4116 | 120.6005 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.75 | 4.99 | Tier 2 High GIDA (Score 40.0–49.9) | 59.34 | 41.49 | 59.34 |  | A - Node within 0.5 km | 0.08 | 0.14 | Node: BGC003 - BP | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4913
5 | 914 | 4914 | PH0004914 | XI | Davao Del Sur | Davao City | Gov. Vicente Duterte | 7.2101 | 125.4055 | R | 2280 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.57 | 6.14 | Tier 2 High GIDA (Score 40.0–49.9) | 59.34 | 41.49 | 59.34 |  | D - Other node or line within 3 km | 6.06 | 1.22 | Line: KITAOTAO - DAVAO | Route options survey candidate: compare actual node lateral with approved line tap. | 4914
5 | 915 | 4915 | 1204718014 | Region XII (SOCCSKSARGEN) | Cotabato | Arakan | Kinawayan | 7.3872 | 125.1729 | R | 933 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12.99 | 7.55 | Tier 2 High GIDA (Score 40.0–49.9) | 59.34 | 41.48 | 59.34 |  | F - Nearest node and line over 5 km | 12.99 | 7.45 | Line: KITAOTAO - DAVAO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4915
5 | 916 | 4916 | PH0004916 | IV-A | Cavite | Cavite City | Barangay 36 | 14.4649 | 120.8848 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.41 | 1.17 | Tier 2 High GIDA (Score 40.0–49.9) | 59.33 | 41.48 | 59.33 |  | D - Other node or line within 3 km | 1.14 | 3.69 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4916
5 | 917 | 4917 | PH0004917 | IV-A | Cavite | Cavite City | Barangay 29-A | 14.4773 | 120.8928 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.52 | 4.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.33 | 41.48 | 59.33 |  | B - Node 0.5-1 km | 0.63 | 4.15 | Node: CVC001 -TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4917
5 | 918 | 4918 | 0102917003 | Region I (Ilocos Region) | Ilocos Sur | San Emilio | Lancuas | 17.2515 | 120.5914 | R | 950 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.23 | 1.82 | Tier 2 High GIDA (Score 40.0–49.9) | 59.33 | 41.48 | 59.33 |  | D - Other node or line within 3 km | 7.23 | 1.78 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Route options survey candidate: compare actual node lateral with approved line tap. | 4918
5 | 919 | 4919 | 0402104013 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 2 | 14.3088 | 121.0489 | R | 705 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.83 | 2.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.33 | 41.48 | 59.33 |  | A - Node within 0.5 km | 0.26 | 0.26 | Node: CRC005 - TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4919
5 | 920 | 4920 | 0300809006 | Region III (Central Luzon) | Bataan | Orani | Centro II | 14.7654 | 120.4455 | R | 453 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.67 | 0.33 | Tier 2 High GIDA (Score 40.0–49.9) | 59.32 | 41.47 | 59.32 |  | F - Nearest node and line over 5 km | 8.9 | 5.33 | Line: AE 48C | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4920
5 | 921 | 4921 | 1401104010 | Cordillera Administrative Region (CAR) | Benguet | Bokod | Tikey | 16.5225 | 120.7993 | R | 615 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.59 | 5.35 | Tier 2 High GIDA (Score 40.0–49.9) | 59.31 | 41.46 | 59.31 |  | F - Nearest node and line over 5 km | 5.59 | 5.29 | Line: SEGMENT 15 (ARITAO - BAGUIO) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4921
5 | 922 | 4922 | 1608501019 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Benglen | 10.1147 | 125.5321 | R | 734 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 40.64 | 40.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.31 | 41.46 | 59.31 |  | F - Nearest node and line over 5 km | 36.54 | 36.41 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4922
5 | 923 | 4923 | 1903605033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Binidayan | Timbangan | 17.2548 | 122.2288 | R | 956 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.4 | 34.29 | Tier 2 High GIDA (Score 40.0–49.9) | 59.31 | 41.46 | 59.31 |  | F - Nearest node and line over 5 km | 29.4 | 34.28 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4923
5 | 924 | 4924 | 0103308007 | Region I (Ilocos Region) | La Union | Burgos | Libtong | 16.0746 | 119.8913 | R | 697 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.83 | 0.99 | Tier 2 High GIDA (Score 40.0–49.9) | 59.3 | 41.46 | 59.3 |  | C - Line within 0.5 km; node over 1 km | 3.38 | 0.25 | Line: SANTA CRUZ TO ALAMINOS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4924
5 | 925 | 4925 | 1903623005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Pualas | Bolinsong | 17.2541 | 122.2286 | R | 761 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.73 | 40.77 | Tier 2 High GIDA (Score 40.0–49.9) | 59.3 | 41.46 | 59.3 |  | F - Nearest node and line over 5 km | 29.34 | 34.24 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4925
5 | 926 | 4926 | 1404408002 | Cordillera Administrative Region (CAR) | Mountain Province | Sadanga | Belwang | 17.1799 | 121.0106 | R | 857 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.88 | 4.03 | Tier 2 High GIDA (Score 40.0–49.9) | 59.29 | 41.45 | 59.29 |  | E - Nearest node or line 3-5 km | 3.88 | 3.69 | Line: Untitled Path | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4926
5 | 927 | 4927 | 1003514016 | Region X (Northern Mindanao) | Lanao del Norte | Munai | Maganding | 7.9947 | 124.0878 | R | 753 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 22.98 | 18.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.29 | 41.45 | 59.29 |  | F - Nearest node and line over 5 km | 20.61 | 19.07 | Line: Undone layed | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4927
5 | 928 | 4928 | 0102805009 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Ben-agan | 18.0531 | 120.5564 | R | 725 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.05 | 1.24 | Tier 2 High GIDA (Score 40.0–49.9) | 59.29 | 41.45 | 59.29 |  | B - Node 0.5-1 km | 0.59 | 0.31 | Line: SEGMENT 3 (VIGAN - BATAC) | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4928
5 | 929 | 4929 | PH0004929 | IV-A | Cavite | Cavite City | Barangay 46 | 14.4739 | 120.8868 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.51 | 8.67 | Tier 2 High GIDA (Score 40.0–49.9) | 59.28 | 41.44 | 59.28 |  | A - Node within 0.5 km | 0.13 | 4.29 | Node: CVC001 -TYPE 3 | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4929
5 | 930 | 4930 | 0301412021 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saluysoy | 14.7435 | 120.9556 | U | 11523 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.69 | 0.36 | Tier 2 High GIDA (Score 40.0–49.9) | 59.28 | 41.44 | 59.28 |  | B - Node 0.5-1 km | 0.69 | 0.3 | Line: BOCAUE | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4930
5 | 931 | 4931 | 0405607078 | Region IV-A (CALABARZON) | Quezon | Calauag | Sinag | 14.2106 | 122.2663 | R | 518 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.8 | 13.19 | Tier 2 High GIDA (Score 40.0–49.9) | 59.28 | 41.44 | 59.28 |  | F - Nearest node and line over 5 km | 9.8 | 13.19 | Node: CLQ004 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4931
5 | 932 | 4932 | PH0004932 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 5 | 11.7605 | 124.8881 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.27 | 30.61 | Tier 2 High GIDA (Score 40.0–49.9) | 59.27 | 41.44 | 59.27 |  | F - Nearest node and line over 5 km | 55.62 | 55.55 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4932
5 | 933 | 4933 | 1906615009 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Tongkil | Sigumbal | 17.2557 | 122.2297 | R | 3650 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.54 | 34.41 | Tier 2 High GIDA (Score 40.0–49.9) | 59.27 | 41.44 | 59.27 |  | F - Nearest node and line over 5 km | 29.54 | 34.4 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4933
5 | 934 | 4934 | 0806024015 | Region VIII (Eastern Visayas) | Samar | Tagapul-An | Trinidad | 12.0627 | 124.1584 | R | 331 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.48 | 58.83 | Tier 2 High GIDA (Score 40.0–49.9) | 59.27 | 41.43 | 59.27 |  | F - Nearest node and line over 5 km | 34.48 | 58.79 | Node: PRM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4934
5 | 935 | 4935 | 1903639013 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Kapatagan | Sigayan | 7.8805 | 123.7099 | R | 1127 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.22 | 35.06 | Tier 2 High GIDA (Score 40.0–49.9) | 59.27 | 41.43 | 59.27 |  | D - Other node or line within 3 km | 15.79 | 2.85 | Line: ILIGAN - PAGADIAN | Route options survey candidate: compare actual node lateral with approved line tap. | 4935
5 | 936 | 4936 | 1606812008 | Region XIII (Caraga) | Surigao del Sur | Lingig | Mansa-ilao | 7.9437 | 126.3758 | R | 529 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.26 | 31.78 | Tier 2 High GIDA (Score 40.0–49.9) | 59.26 | 41.43 | 59.26 |  | F - Nearest node and line over 5 km | 36.26 | 31.78 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4936
5 | 937 | 4937 | 1004204013 | Region X (Northern Mindanao) | Misamis Occidental | Calamba | San Isidro | 8.5119 | 123.66 | R | 505 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 54.34 | 49.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.26 | 41.43 | 59.26 |  | F - Nearest node and line over 5 km | 54.34 | 50.09 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4937
5 | 938 | 4938 | 0804822015 | Region VIII (Eastern Visayas) | Northern Samar | Silvino Lobos | Geparayan De Turag | 12.3219 | 124.8944 | R | 867 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 92.88 | 92.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.25 | 41.42 | 59.25 |  | F - Nearest node and line over 5 km | 92.88 | 92.23 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4938
5 | 939 | 4939 | 1381300111 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Sauyo | 14.6896 | 121.0433 | U | 79491 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.44 | 1.3 | Tier 2 High GIDA (Score 40.0–49.9) | 59.24 | 41.41 | 59.24 |  | D - Other node or line within 3 km | 1.44 | 1.29 | Line: UG 144C | Route options survey candidate: compare actual node lateral with approved line tap. | 4939
5 | 940 | 4940 | 0403425004 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | G.S.I.S. | 14.3441 | 121.0451 | R | 3100 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.85 | 7.99 | Tier 2 High GIDA (Score 40.0–49.9) | 59.24 | 41.41 | 59.24 |  | B - Node 0.5-1 km | 0.53 | 0.02 | Line: AE SPL002 TO SPL001 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4940
5 | 941 | 4941 | PH0004941 | VIII | Samar (Western Samar) | Catbalogan City | Poblacion 6 | 11.7556 | 124.9017 | R | 2229 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 33.03 | 32.92 | Tier 2 High GIDA (Score 40.0–49.9) | 59.23 | 41.41 | 59.23 |  | F - Nearest node and line over 5 km | 55.72 | 55.64 | Line: CAPOOCAN - TACLOBAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4941
5 | 942 | 4942 | 0301410015 | Region III (Central Luzon) | Bulacan | City of Malolos | Guinhawa | 14.8354 | 120.8277 | U | 4408 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.74 | 1.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.22 | 41.4 | 59.22 |  | D - Other node or line within 3 km | 1.74 | 1.32 | Line: 48 CORE (6X8) | Route options survey candidate: compare actual node lateral with approved line tap. | 4942
5 | 943 | 4943 | 0403405006 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bucal | 14.1887 | 121.1689 | U | 15663 | 3.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.62 | 0.07 | Tier 2 High GIDA (Score 40.0–49.9) | 59.21 | 41.4 | 59.21 |  | C - Line within 0.5 km; node over 1 km | 2.62 | 0.05 | Line: SEGMENT 27 (STA CRUZ - CALAMBA) | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4943
5 | 944 | 4944 | 0402123018 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Koronel Jose P. Elises | 14.2901 | 121.0051 | R | 4747 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.84 | 4.46 | Tier 2 High GIDA (Score 40.0–49.9) | 59.21 | 41.4 | 59.21 |  | B - Node 0.5-1 km | 0.91 | 4.57 | Node: MAC001 - TYPE 3 | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4944
5 | 945 | 4945 | 0201509005 | Region II (Cagayan Valley) | Cagayan | Calayan | Dilam | 19.3691 | 121.483 | R | 1855 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 93.81 | 90.61 | Tier 2 High GIDA (Score 40.0–49.9) | 59.21 | 41.39 | 59.21 |  | F - Nearest node and line over 5 km | 93.81 | 90.6 | Line: SEGMENT 7 (CLAVERIA - PAMPLONA) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4945
5 | 946 | 4946 | 0504101006 | Region V (Bicol Region) | Masbate | Aroroy | Balete | 12.3955 | 123.4396 | R | 1664 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.51 | 7.52 | Tier 2 High GIDA (Score 40.0–49.9) | 59.2 | 41.39 | 59.2 |  | F - Nearest node and line over 5 km | 10.51 | 15.65 | Node: BOM001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4946
5 | 947 | 4947 | 1401107002 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Anchukey | 16.617 | 120.85 | R | 298 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.62 | 8.64 | Tier 2 High GIDA (Score 40.0–49.9) | 59.2 | 41.38 | 59.2 |  | D - Other node or line within 3 km | 1.62 | 8.4 | Node: KYB001 - TYPE 4A | Route options survey candidate: compare actual node lateral with approved line tap. | 4947
5 | 948 | 4948 | 0103308006 | Region I (Ilocos Region) | La Union | Burgos | Imelda | 18.4954 | 120.6688 | R | 480 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.89 | 0.78 | Tier 2 High GIDA (Score 40.0–49.9) | 59.19 | 41.38 | 59.19 |  | D - Other node or line within 3 km | 3.04 | 2.58 | Line: SEGMENT 5 (LAOAG CITY - BANGUI) | Route options survey candidate: compare actual node lateral with approved line tap. | 4948
5 | 949 | 4949 | 1004208004 | Region X (Northern Mindanao) | Misamis Occidental | Lopez Jaena | Bonifacio | 8.489 | 123.6755 | R | 253 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 52.95 | 46.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.19 | 41.38 | 59.19 |  | F - Nearest node and line over 5 km | 51.43 | 47.09 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4949
5 | 950 | 4950 | PH0004950 | XII | South Cotabato | General Santos City (Dadiangas) | Labangal | 6.0921 | 125.1469 | R | 2278 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.38 | 2.94 | Tier 2 High GIDA (Score 40.0–49.9) | 59.18 | 41.37 | 59.18 |  | D - Other node or line within 3 km | 2.38 | 2.94 | Node: GSS003 - TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4950
5 | 951 | 4951 | 0907208009 | Region IX (Zamboanga Peninsula) | Zamboanga del Norte | Mutia | Paso Rio | 8.4165 | 123.4807 | R | 336 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 48.86 | 47.66 | Tier 2 High GIDA (Score 40.0–49.9) | 59.17 | 41.37 | 59.17 |  | F - Nearest node and line over 5 km | 52.88 | 52.62 | Line: ILIGAN - PAGADIAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4951
5 | 952 | 4952 | PH0004952 | VII | Cebu | Cordoba | Gilutongan | 10.2073 | 123.9884 | R | 2250 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 9.72 | 9.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.17 | 41.37 | 59.17 |  | F - Nearest node and line over 5 km | 7.55 | 14.16 | Node: CDV001 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4952
5 | 953 | 4953 | 1108208019 | Region XI (Davao Region) | Davao de Oro | Montevista | Prosperidad | 7.8276 | 125.9473 | R | 2708 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 12 | 9.42 | Tier 2 High GIDA (Score 40.0–49.9) | 59.17 | 41.37 | 59.17 |  | F - Nearest node and line over 5 km | 11.99 | 9.41 | Line: DAVAO CITY - TRENTO | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4953
5 | 954 | 4954 | 0802606038 | Region VIII (Eastern Visayas) | Eastern Samar | Dolores | San Isidro | 12.0631 | 125.4092 | R | 474 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 101.72 | 104.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.16 | 41.36 | 59.16 |  | F - Nearest node and line over 5 km | 101.72 | 104.12 | Node: TCL002 - TYPE 3 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4954
5 | 955 | 4955 | 0102908002 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Comillas North | 16.9702 | 120.7482 | R | 2377 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.98 | 0.11 | Tier 2 High GIDA (Score 40.0–49.9) | 59.16 | 41.36 | 59.16 |  | C - Line within 0.5 km; node over 1 km | 2.98 | 0.03 | Line: Buguias To Cervantes (CVI308) 39,014mtrs. | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4955
5 | 956 | 4956 | 1606818010 | Region XIII (Caraga) | Surigao del Sur | Tago | Cayale | 8.9833 | 126.1211 | R | 1933 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 13.36 | 5.42 | Tier 2 High GIDA (Score 40.0–49.9) | 59.16 | 41.36 | 59.16 |  | F - Nearest node and line over 5 km | 13.36 | 5.42 | Line: Route | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4956
5 | 957 | 4957 | 1608501011 | Region XIII (Caraga) | Dinagat Islands | Basilisa | Montag | 10.0877 | 125.5727 | R | 1269 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 36.5 | 36.5 | Tier 2 High GIDA (Score 40.0–49.9) | 59.16 | 41.36 | 59.16 |  | F - Nearest node and line over 5 km | 34.39 | 34.29 | Line: SURIGAO - CARASCAL | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4957
5 | 958 | 4958 | PH0004958 | IV-A | Cavite | Imus City | Magdalo | 14.4534 | 120.9315 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.12 | 0.05 | Tier 2 High GIDA (Score 40.0–49.9) | 59.16 | 41.36 | 59.16 |  | C - Line within 0.5 km; node over 1 km | 2 | 0.4 | Line: BACOOR | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4958
5 | 959 | 4959 | 1003511018 | Region X (Northern Mindanao) | Lanao del Norte | Magsaysay | Somiorang | 6.7779 | 125.1465 | R | 434 | 4.2 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 10.91 | 6.55 | Tier 2 High GIDA (Score 40.0–49.9) | 59.15 | 41.35 | 59.15 |  | D - Other node or line within 3 km | 2.79 | 21.62 | Node: MYD001 - BP | Route options survey candidate: compare actual node lateral with approved line tap. | 4959
5 | 960 | 4960 | 0804805001 | Region VIII (Eastern Visayas) | Northern Samar | Catarman | Aguinaldo | 12.4357 | 124.6471 | R | 463 | 4.3 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 63.23 | 62.65 | Tier 2 High GIDA (Score 40.0–49.9) | 59.15 | 41.35 | 59.15 |  | F - Nearest node and line over 5 km | 63.23 | 62.56 | Line: STA MAGDALENA CLS | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4960
5 | 961 | 4961 | 1908822005 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | South Upi | Kuya | 17.2551 | 122.2291 | U | 6770 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.33 | Tier 2 High GIDA (Score 40.0–49.9) | 59.15 | 41.35 | 59.15 |  | F - Nearest node and line over 5 km | 29.45 | 34.32 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4961
5 | 962 | 4962 | PH0004962 | I | Pangasinan | San Carlos City | Perez Boulevard (Pob.) | 10.5118 | 123.4275 | R | 2218 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.11 | 2.98 | Tier 2 High GIDA (Score 40.0–49.9) | 59.14 | 41.34 | 59.14 |  | C - Line within 0.5 km; node over 1 km | 3.7 | 0.03 | Line: ESCALANTE - SAN CARLOS | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4962
5 | 963 | 4963 | 0504121004 | Region V (Bicol Region) | Masbate | Uson | Badling | 12.194 | 123.8234 | R | 800 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 8.69 | 28.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.14 | 41.34 | 59.14 |  | F - Nearest node and line over 5 km | 8.69 | 28.85 | Node: UNM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4963
5 | 964 | 4964 | PH0004964 | IX | Zamboanga Del Sur | Zamboanga City | Santa Catalina | 6.9088 | 122.0878 | R | 2305 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.56 | 1.12 | Tier 2 High GIDA (Score 40.0–49.9) | 59.13 | 41.34 | 59.13 |  | D - Other node or line within 3 km | 1.56 | 1.05 | Line: Untitled Path | Route options survey candidate: compare actual node lateral with approved line tap. | 4964
5 | 965 | 4965 | 0405804022 | Region IV-A (CALABARZON) | Rizal | Binangonan | Lunsad | 14.4621 | 121.1955 | U | 11246 | 3.6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.57 | 0.74 | Tier 2 High GIDA (Score 40.0–49.9) | 59.13 | 41.34 | 59.13 |  | D - Other node or line within 3 km | 1.57 | 0.58 | Line: Aerial 24C | Route options survey candidate: compare actual node lateral with approved line tap. | 4965
5 | 966 | 4966 | 1908710033 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | Sultan Kudarat | Pingping | 17.2539 | 122.2276 | R | 1062 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.29 | 34.19 | Tier 2 High GIDA (Score 40.0–49.9) | 59.13 | 41.34 | 59.13 |  | F - Nearest node and line over 5 km | 29.24 | 34.13 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4966
5 | 967 | 4967 | 1380200012 | National Capital Region (NCR) | Fourth District (Not a Province) | City of Las Piñas | Manuyo Dos | 14.4703 | 120.9914 | U | 45028 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.93 | 0.6 | Tier 2 High GIDA (Score 40.0–49.9) | 59.13 | 41.33 | 59.13 |  | B - Node 0.5-1 km | 0.93 | 0.6 | Line: Aerial 24C | Short node lateral candidate; confirm port/fiber capacity, access and route. | 4967
5 | 968 | 4968 | PH0004968 | IV-A | Cavite | Cavite City | Barangay 22 | 14.4834 | 120.9112 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.19 | 2.36 | Tier 2 High GIDA (Score 40.0–49.9) | 59.12 | 41.33 | 59.12 |  | D - Other node or line within 3 km | 2.72 | 3.94 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4968
5 | 969 | 4969 | PH0004969 | IV-A | Cavite | Cavite City | Barangay 62 | 14.4827 | 120.9046 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 6.3 | 9.37 | Tier 2 High GIDA (Score 40.0–49.9) | 59.12 | 41.33 | 59.12 |  | D - Other node or line within 3 km | 2.04 | 4.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4969
5 | 970 | 4970 | 0803713005 | Region VIII (Eastern Visayas) | Leyte | Calubian | Bunacan | 11.4856 | 124.3449 | R | 604 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 38.18 | 31.53 | Tier 2 High GIDA (Score 40.0–49.9) | 59.12 | 41.33 | 59.12 |  | F - Nearest node and line over 5 km | 38.18 | 31.53 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4970
5 | 971 | 4971 | 0102820011 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Jose | 16.0548 | 120.7695 | R | 1474 | 3.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.64 | 0.12 | Tier 2 High GIDA (Score 40.0–49.9) | 59.12 | 41.33 | 59.12 |  | E - Nearest node or line 3-5 km | 4.11 | 4.24 | Node: TYP001 - TYPE 3 | Review candidate: examine alternative BTS location, updated fiber inventory or Starlink backhaul. | 4971
5 | 972 | 4972 | PH0004972 | CAR | Benguet | Baguio City | Greenwater Village | 16.3902 | 120.5939 | R | 2260 | 3.5 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.22 | 4.35 | Tier 2 High GIDA (Score 40.0–49.9) | 59.12 | 41.33 | 59.12 |  | D - Other node or line within 3 km | 1.36 | 1.18 | Line: BAGUIO | Route options survey candidate: compare actual node lateral with approved line tap. | 4972
5 | 973 | 4973 | 0803731020 | Region VIII (Eastern Visayas) | Leyte | Mahaplag | San Juan | 10.5482 | 124.9181 | R | 483 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 19.34 | 4.11 | Tier 2 High GIDA (Score 40.0–49.9) | 59.11 | 41.32 | 59.11 |  | F - Nearest node and line over 5 km | 19.37 | 16.47 | Line: INOPACAN (BAYBAY) - MAASIN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4973
5 | 974 | 4974 | 0803738019 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Danao | 11.0898 | 124.682 | R | 2115 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 11.61 | 9.49 | Tier 2 High GIDA (Score 40.0–49.9) | 59.11 | 41.32 | 59.11 |  | F - Nearest node and line over 5 km | 11.87 | 9.48 | Line: ORMOC CLS - CAPOOCAN | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4974
5 | 975 | 4975 | 0907338006 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Pitogo | Limbayan | 7.3659 | 123.3995 | R | 1271 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 51.88 | 50.26 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | F - Nearest node and line over 5 km | 51.88 | 50.16 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4975
5 | 976 | 4976 | 0405647004 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone II | 14.0765 | 121.7388 | U | 826 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.42 | 0.08 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | F - Nearest node and line over 5 km | 11.51 | 9.48 | Line: UG LCQ001 TO ATQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4976
5 | 977 | 4977 | PH0004977 | IV-A | Cavite | Cavite City | Barangay 40 | 14.4834 | 120.9112 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.52 | 3.45 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | D - Other node or line within 3 km | 2.72 | 3.94 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4977
5 | 978 | 4978 | 1908804004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Datu Anggal Midtimbang | Midtimbang | 17.2552 | 122.2292 | R | 4384 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.47 | 34.34 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | F - Nearest node and line over 5 km | 29.47 | 34.34 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4978
5 | 979 | 4979 | 1606804005 | Region XIII (Caraga) | Surigao del Sur | Cagwait | Tawagan | 8.9167 | 126.3004 | R | 568 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 21.11 | 0.54 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | D - Other node or line within 3 km | 21.11 | 0.54 | Line: Route | Route options survey candidate: compare actual node lateral with approved line tap. | 4979
5 | 980 | 4980 | 0504103014 | Region V (Bicol Region) | Masbate | Balud | Mapitogo | 12.076 | 123.2866 | R | 425 | 4.1 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 5.13 | 10.48 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.32 | 59.1 |  | F - Nearest node and line over 5 km | 5.13 | 28.84 | Node: BDM001 - BP | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4980
5 | 981 | 4981 | 0402103026 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row Central | 14.3977 | 120.9896 | U | 6419 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.07 | 0.39 | Tier 2 High GIDA (Score 40.0–49.9) | 59.1 | 41.31 | 59.1 |  | D - Other node or line within 3 km | 1.28 | 4.13 | Node: BRC002-TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4981
5 | 982 | 4982 | 0600402009 | Region VI (Western Visayas) | Aklan | Balete | Morales | 11.5452 | 122.3735 | R | 3496 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.35 | 1.21 | Tier 2 High GIDA (Score 40.0–49.9) | 59.08 | 41.31 | 59.08 |  | D - Other node or line within 3 km | 1.35 | 1.21 | Line: IVISAN - KALIBO | Route options survey candidate: compare actual node lateral with approved line tap. | 4982
5 | 983 | 4983 | PH0004983 | IV-A | Cavite | City of Bacoor | Zapote 2 | 14.4626 | 120.9436 | R | 9584 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.26 | 0.28 | Tier 2 High GIDA (Score 40.0–49.9) | 59.07 | 41.3 | 59.07 |  | D - Other node or line within 3 km | 1.73 | 1.66 | Line: BACOOR | Route options survey candidate: compare actual node lateral with approved line tap. | 4983
5 | 984 | 4984 | 1400102004 | Cordillera Administrative Region (CAR) | Abra | Boliney | Dao-angan | 17.3747 | 120.8559 | R | 439 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 30.56 | 28.2 | Tier 2 High GIDA (Score 40.0–49.9) | 59.07 | 41.29 | 59.07 |  | F - Nearest node and line over 5 km | 30.56 | 28.14 | Line: HLD_PROPOSED 96F AERIAL BACKBONE FOC FROM CERVANTES TO CANDON, ILOCOS SUR | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4984
5 | 985 | 4985 | 1906607030 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Old Panamao | Pugad Manaul | 17.2556 | 122.2296 | R | 1441 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.53 | 34.4 | Tier 2 High GIDA (Score 40.0–49.9) | 59.06 | 41.29 | 59.06 |  | F - Nearest node and line over 5 km | 29.53 | 34.39 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4985
5 | 986 | 4986 | 1381300115 | National Capital Region (NCR) | Second District (Not a Province) | Quezon City | Socorro | 14.6214 | 121.0583 | U | 23160 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 0.17 | 0.13 | Tier 2 High GIDA (Score 40.0–49.9) | 59.06 | 41.29 | 59.06 |  | A - Node within 0.5 km | 0.17 | 0.05 | Line: Aerial 24C | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4986
5 | 987 | 4987 | 0405647006 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone IV | 13.9973 | 121.6111 | R | 919 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 3.6 | 2.83 | Tier 2 High GIDA (Score 40.0–49.9) | 59.05 | 41.28 | 59.05 |  | C - Line within 0.5 km; node over 1 km | 3.5 | 0.25 | Line: LILIW TO LUCENA AE | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 4987
5 | 988 | 4988 | 0907303018 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Bayog | Kanipaan | 7.8837 | 123.086 | R | 670 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 17.45 | 11.91 | Tier 2 High GIDA (Score 40.0–49.9) | 59.05 | 41.28 | 59.05 |  | F - Nearest node and line over 5 km | 17.45 | 11.87 | Line: PAGADIAN - BUUG | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4988
5 | 989 | 4989 | PH0004989 | IV-A | Cavite | Cavite City | Barangay 35 | 14.4827 | 120.9046 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.92 | 1.41 | Tier 2 High GIDA (Score 40.0–49.9) | 59.05 | 41.28 | 59.05 |  | D - Other node or line within 3 km | 2.04 | 4.09 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4989
5 | 990 | 4990 | PH0004990 | IV-A | Cavite | Cavite City | Barangay 31 | 14.4834 | 120.9112 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 7.73 | 11.51 | Tier 2 High GIDA (Score 40.0–49.9) | 59.05 | 41.28 | 59.05 |  | D - Other node or line within 3 km | 2.72 | 3.94 | Node: CVC001 -TYPE 3 | Route options survey candidate: compare actual node lateral with approved line tap. | 4990
5 | 991 | 4991 | 1906617006 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | Lugus | Huwit-huwit Proper | 5.7058 | 120.8568 | R | 722 | 6 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 14.8 | 14.07 | Tier 2 High GIDA (Score 40.0–49.9) | 59.04 | 41.28 | 59.04 |  | F - Nearest node and line over 5 km | 189.82 | 189.81 | Line: Untitled Path | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4991
5 | 992 | 4992 | 0600601008 | Region VI (Western Visayas) | Antique | Anini-Y | Igbarabatuan | 10.4507 | 121.9736 | R | 346 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 34.87 | 14.82 | Tier 2 High GIDA (Score 40.0–49.9) | 59.03 | 41.27 | 59.03 |  | F - Nearest node and line over 5 km | 34.87 | 14.76 | Line: OTON, ILOILO - SAN JOSE DE BUENAVISTA, ANTIQUE | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4992
5 | 993 | 4993 | 1903638004 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | Tagoloan Ii | Bayog | 17.2536 | 122.2278 | R | 629 | 5.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 31.26 | 36.29 | Tier 2 High GIDA (Score 40.0–49.9) | 59.03 | 41.27 | 59.03 |  | F - Nearest node and line over 5 km | 29.24 | 34.14 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4993
5 | 994 | 4994 | 1908823007 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | Sultan Sa Barongis | Langgapanan | 17.2553 | 122.2299 | R | 836 | 4.7 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 29.45 | 34.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.03 | 41.27 | 59.03 |  | F - Nearest node and line over 5 km | 29.53 | 34.41 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4994
5 | 995 | 4995 | 1907002037 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | Bongao | Tarawakan | 17.2565 | 122.2302 | R | 3238 | 5.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 4.12 | 22.54 | Tier 2 High GIDA (Score 40.0–49.9) | 59.03 | 41.27 | 59.03 |  | F - Nearest node and line over 5 km | 29.64 | 34.48 | Node: IGI003 - PM | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4995
5 | 996 | 4996 | 0704622017 | Region VII (Central Visayas) | Negros Oriental | Tayasan | Numnum | 9.8995 | 123.1262 | R | 485 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 28.73 | 2.32 | Tier 2 High GIDA (Score 40.0–49.9) | 59.02 | 41.26 | 59.02 |  | F - Nearest node and line over 5 km | 28.73 | 16.62 | Line: OPENTRENCHING (505m) | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4996
5 | 997 | 4997 | 0405647051 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | San Diego Zone III | 14.0115 | 121.6186 | R | 260 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 2.36 | 1.1 | Tier 2 High GIDA (Score 40.0–49.9) | 59.02 | 41.26 | 59.02 |  | D - Other node or line within 3 km | 3.04 | 1.24 | Line: AE LCQ001 TO TYQ001 | Route options survey candidate: compare actual node lateral with approved line tap. | 4997
5 | 998 | 4998 | 1704006004 | MIMAROPA Region | Marinduque | Torrijos | Bonliw | 13.372 | 122.1154 | R | 1212 | 3.8 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 32.17 | 31.58 | Tier 2 High GIDA (Score 40.0–49.9) | 59.01 | 41.26 | 59.01 |  | F - Nearest node and line over 5 km | 32.17 | 31.41 | Line: AE CTQ001 TO MCQ001 | Remote site candidate: deploy Starlink LEO satellite backhaul or long microwave hop. | 4998
5 | 999 | 4999 | 1380613003 | National Capital Region (NCR) | First District (Not a Province) | City of Manila | Barangay 651 | 14.5914 | 120.9591 | U | 2634 | 3.9 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.23 | 0.78 | Tier 2 High GIDA (Score 40.0–49.9) | 59.01 | 41.25 | 59.01 |  | A - Node within 0.5 km | 0.36 | 2 | Node: MNL068 - PM | First survey candidate: confirm node handoff, spare capacity and short route; co-location not established. | 4999
5 | 1000 | 5000 | PH0005000 | IV-A | Cavite | Cavite City | Barangay 42-C | 14.4536 | 120.9815 | R | 2316 | 3.4 |  |  | Band n50 (1.5 GHz, 100 MHz TDD) |  | 1 | 1.03 | 0.53 | Tier 2 High GIDA (Score 40.0–49.9) | 59 | 41.24 | 59 |  | C - Line within 0.5 km; node over 1 km | 1.29 | 0.39 | Line: Aerial 216C MTF | Splice closure / line-tap survey candidate; locate closure and confirm splicing/capacity. | 5000

## Provincial Summary
5G FWA Barangay Rollout Plan — DICT / UNDP GIDA (Provincial Summary)
Region | Province | Total Sites | Phase 1 Sites | Total Population | Target Subs | Peak BTS | Node <=1km (A+B) | Line <=500m (C) | Remote >3km (E+F)
BARMM (LaMa+SGA) | Lanao Del Sur | 18 | 1 | 45324 | 2376 | 18 | 0 | 0 | 18
BARMM (LaMa+SGA) | Maguindanao del Norte | 3 | 0 | 6837 | 540 | 3 | 0 | 0 | 3
BARMM (LaMa+SGA) | North Cotabato | 5 | 0 | 12506 | 987 | 5 | 0 | 0 | 5
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Basilan | 29 | 0 | 59606 | 3502 | 29 | 0 | 1 | 27
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | 138 | 7 | 132726 | 6974 | 138 | 0 | 2 | 135
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Norte | 72 | 2 | 359386 | 25133 | 74 | 0 | 0 | 72
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Maguindanao del Sur | 84 | 6 | 199274 | 12708 | 84 | 1 | 0 | 83
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Sulu | 123 | 8 | 224935 | 11419 | 123 | 0 | 0 | 123
Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Tawi-Tawi | 105 | 39 | 243326 | 12571 | 105 | 0 | 1 | 104
CAR | Benguet | 85 | 0 | 192100 | 16490 | 85 | 45 | 10 | 0
Cordillera Administrative Region (CAR) | Abra | 52 | 17 | 24515 | 1928 | 52 | 1 | 0 | 48
Cordillera Administrative Region (CAR) | Apayao | 35 | 11 | 23237 | 1657 | 35 | 1 | 1 | 29
Cordillera Administrative Region (CAR) | Benguet | 22 | 9 | 32614 | 2795 | 22 | 2 | 1 | 16
Cordillera Administrative Region (CAR) | Ifugao | 19 | 10 | 15314 | 1176 | 19 | 0 | 0 | 14
Cordillera Administrative Region (CAR) | Kalinga | 53 | 35 | 68402 | 4817 | 54 | 2 | 3 | 37
Cordillera Administrative Region (CAR) | Mountain Province | 16 | 7 | 12794 | 1034 | 16 | 0 | 2 | 11
I | Ilocos Norte | 19 | 0 | 42427 | 3439 | 19 | 3 | 4 | 7
I | Pangasinan | 10 | 0 | 22180 | 1850 | 10 | 0 | 5 | 1
II | Isabela | 4 | 2 | 9104 | 716 | 4 | 0 | 0 | 2
II | Nueva Vizcaya | 12 | 9 | 22147 | 1746 | 12 | 0 | 1 | 10
III | Aurora | 3 | 3 | 1449 | 114 | 3 | 0 | 0 | 3
III | Nueva Ecija | 30 | 10 | 71940 | 6180 | 30 | 6 | 9 | 3
III | Pampanga | 18 | 0 | 42012 | 3150 | 18 | 9 | 4 | 1
IV-A | Batangas | 14 | 10 | 31626 | 2632 | 14 | 2 | 8 | 0
IV-A | Cavite | 105 | 1 | 374004 | 32958 | 105 | 38 | 4 | 0
IV-A | Laguna | 30 | 10 | 72360 | 6570 | 30 | 4 | 14 | 5
IV-A | Quezon | 10 | 0 | 19640 | 1550 | 10 | 8 | 1 | 0
IV-B | Palawan | 24 | 8 | 62328 | 4800 | 24 | 7 | 4 | 10
IX | Zamboanga Del Sur | 11 | 1 | 25355 | 1947 | 11 | 0 | 0 | 5
MIMAROPA Region | Marinduque | 10 | 2 | 5720 | 451 | 10 | 0 | 0 | 10
MIMAROPA Region | Occidental Mindoro | 5 | 0 | 10555 | 812 | 5 | 0 | 0 | 5
MIMAROPA Region | Oriental Mindoro | 6 | 0 | 5980 | 460 | 6 | 0 | 0 | 3
MIMAROPA Region | Palawan | 71 | 18 | 132946 | 10291 | 71 | 0 | 3 | 66
MIMAROPA Region | Romblon | 4 | 0 | 4696 | 380 | 4 | 0 | 0 | 4
NCR | Metro Manila | 181 | 2 | 416615 | 32933 | 181 | 157 | 15 | 0
NIR | Negros Occidental | 31 | 26 | 70649 | 5580 | 31 | 12 | 4 | 4
NIR | Negros Oriental | 5 | 0 | 11395 | 900 | 5 | 1 | 0 | 0
National Capital Region (NCR) | First District (Not a Province) | 892 | 83 | 1896481 | 145786 | 906 | 682 | 140 | 0
National Capital Region (NCR) | Fourth District (Not a Province) | 247 | 7 | 1616954 | 137866 | 330 | 180 | 52 | 0
National Capital Region (NCR) | Second District (Not a Province) | 161 | 13 | 3133263 | 256129 | 348 | 70 | 50 | 18
National Capital Region (NCR) | Third District (Not a Province) | 59 | 21 | 992453 | 84302 | 117 | 38 | 9 | 0
Region I (Ilocos Region) | Ilocos Norte | 41 | 25 | 40450 | 3275 | 41 | 5 | 6 | 17
Region I (Ilocos Region) | Ilocos Sur | 49 | 18 | 41512 | 3269 | 49 | 1 | 5 | 25
Region I (Ilocos Region) | La Union | 17 | 2 | 25616 | 2076 | 17 | 0 | 3 | 11
Region I (Ilocos Region) | Pangasinan | 6 | 6 | 5430 | 453 | 6 | 0 | 0 | 6
Region II (Cagayan Valley) | Batanes | 29 | 6 | 18940 | 1893 | 29 | 0 | 0 | 29
Region II (Cagayan Valley) | Cagayan | 60 | 28 | 85281 | 6561 | 60 | 2 | 13 | 27
Region II (Cagayan Valley) | Isabela | 34 | 18 | 33563 | 2648 | 34 | 2 | 0 | 28
Region II (Cagayan Valley) | Nueva Vizcaya | 42 | 29 | 48418 | 3818 | 42 | 1 | 1 | 34
Region II (Cagayan Valley) | Quirino | 19 | 16 | 18078 | 1389 | 19 | 1 | 1 | 16
Region III (Central Luzon) | Aurora | 16 | 12 | 12446 | 981 | 16 | 2 | 2 | 9
Region III (Central Luzon) | Bataan | 28 | 1 | 90645 | 7553 | 28 | 7 | 6 | 4
Region III (Central Luzon) | Bulacan | 26 | 0 | 174435 | 14951 | 31 | 8 | 4 | 4
Region III (Central Luzon) | Nueva Ecija | 5 | 3 | 8732 | 747 | 5 | 1 | 1 | 2
Region III (Central Luzon) | Pampanga | 6 | 0 | 13460 | 1009 | 6 | 0 | 0 | 4
Region III (Central Luzon) | Tarlac | 4 | 0 | 14497 | 1116 | 4 | 0 | 3 | 1
Region III (Central Luzon) | Zambales | 4 | 4 | 14651 | 1156 | 4 | 0 | 0 | 3
Region IV-A (CALABARZON) | Batangas | 68 | 7 | 78107 | 6507 | 68 | 12 | 13 | 21
Region IV-A (CALABARZON) | Cavite | 112 | 5 | 870969 | 76847 | 146 | 36 | 11 | 1
Region IV-A (CALABARZON) | Laguna | 69 | 10 | 1077349 | 97933 | 140 | 22 | 19 | 3
Region IV-A (CALABARZON) | Quezon | 86 | 23 | 47213 | 3719 | 86 | 4 | 11 | 54
Region IV-A (CALABARZON) | Rizal | 37 | 4 | 1306028 | 108831 | 131 | 14 | 14 | 2
Region IX (Zamboanga Peninsula) | City of Isabela (Not a Province) | 1 | 0 | 1811 | 123 | 1 | 0 | 0 | 1
Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | 4 | 0 | 4697 | 336 | 4 | 0 | 0 | 4
Region IX (Zamboanga Peninsula) | Zamboanga del Norte | 16 | 3 | 12858 | 1071 | 16 | 0 | 0 | 16
Region IX (Zamboanga Peninsula) | Zamboanga del Sur | 44 | 3 | 34999 | 2690 | 44 | 0 | 1 | 38
Region V (Bicol Region) | Albay | 21 | 8 | 25527 | 1863 | 21 | 4 | 2 | 10
Region V (Bicol Region) | Camarines Norte | 8 | 2 | 8024 | 602 | 8 | 0 | 0 | 7
Region V (Bicol Region) | Camarines Sur | 23 | 5 | 19648 | 1402 | 23 | 2 | 1 | 19
Region V (Bicol Region) | Catanduanes | 12 | 6 | 8454 | 602 | 12 | 0 | 0 | 12
Region V (Bicol Region) | Masbate | 34 | 1 | 37519 | 2743 | 34 | 1 | 1 | 31
Region V (Bicol Region) | Sorsogon | 21 | 2 | 15692 | 1175 | 21 | 2 | 1 | 11
Region VI (Western Visayas) | Aklan | 47 | 35 | 61322 | 4709 | 47 | 1 | 1 | 38
Region VI (Western Visayas) | Antique | 47 | 17 | 16708 | 1282 | 47 | 0 | 1 | 46
Region VI (Western Visayas) | Capiz | 32 | 16 | 23428 | 1847 | 32 | 0 | 0 | 31
Region VI (Western Visayas) | Guimaras | 1 | 0 | 1929 | 152 | 1 | 0 | 0 | 1
Region VI (Western Visayas) | Iloilo | 35 | 13 | 29685 | 2339 | 35 | 0 | 3 | 28
Region VI (Western Visayas) | Negros Occidental | 4 | 0 | 12109 | 981 | 4 | 1 | 0 | 3
Region VII (Central Visayas) | Bohol | 8 | 1 | 5471 | 411 | 8 | 0 | 0 | 7
Region VII (Central Visayas) | Cebu | 23 | 3 | 82603 | 6519 | 26 | 2 | 4 | 14
Region VII (Central Visayas) | Negros Oriental | 10 | 0 | 12407 | 979 | 10 | 0 | 0 | 10
Region VII (Central Visayas) | Siquijor | 1 | 0 | 217 | 17 | 1 | 0 | 0 | 1
Region VIII (Eastern Visayas) | Eastern Samar | 40 | 4 | 19562 | 1500 | 40 | 0 | 0 | 40
Region VIII (Eastern Visayas) | Leyte | 23 | 5 | 16240 | 1278 | 23 | 0 | 2 | 20
Region VIII (Eastern Visayas) | Northern Samar | 63 | 0 | 30805 | 2143 | 63 | 1 | 0 | 62
Region VIII (Eastern Visayas) | Samar | 159 | 29 | 80867 | 5901 | 159 | 0 | 0 | 159
Region VIII (Eastern Visayas) | Southern Leyte | 18 | 11 | 5724 | 416 | 18 | 0 | 0 | 18
Region X (Northern Mindanao) | Bukidnon | 13 | 0 | 21817 | 1723 | 13 | 0 | 0 | 13
Region X (Northern Mindanao) | Camiguin | 1 | 0 | 896 | 69 | 1 | 0 | 0 | 1
Region X (Northern Mindanao) | Lanao del Norte | 82 | 21 | 77685 | 5540 | 82 | 0 | 8 | 66
Region X (Northern Mindanao) | Misamis Occidental | 17 | 1 | 6957 | 533 | 17 | 0 | 1 | 16
Region X (Northern Mindanao) | Misamis Oriental | 11 | 5 | 8347 | 642 | 11 | 1 | 2 | 8
Region XI (Davao Region) | Davao Occidental | 31 | 12 | 88953 | 7345 | 31 | 0 | 0 | 31
Region XI (Davao Region) | Davao Oriental | 32 | 9 | 70253 | 5851 | 32 | 0 | 0 | 31
Region XI (Davao Region) | Davao de Oro | 31 | 18 | 66226 | 5365 | 31 | 0 | 1 | 29
Region XI (Davao Region) | Davao del Norte | 9 | 1 | 56233 | 4559 | 11 | 3 | 1 | 4
Region XI (Davao Region) | Davao del Sur | 6 | 1 | 11274 | 995 | 6 | 0 | 0 | 4
Region XII (SOCCSKSARGEN) | Cotabato | 7 | 0 | 13259 | 1046 | 7 | 0 | 0 | 7
Region XII (SOCCSKSARGEN) | Sarangani | 14 | 4 | 55500 | 4268 | 14 | 0 | 0 | 14
Region XII (SOCCSKSARGEN) | South Cotabato | 1 | 0 | 2769 | 231 | 1 | 0 | 0 | 1
Region XII (SOCCSKSARGEN) | Sultan Kudarat | 6 | 0 | 12993 | 1024 | 6 | 0 | 0 | 6
Region XIII (Caraga) | Agusan del Sur | 10 | 0 | 8581 | 659 | 10 | 1 | 0 | 9
Region XIII (Caraga) | Dinagat Islands | 5 | 0 | 4549 | 358 | 5 | 0 | 0 | 5
Region XIII (Caraga) | Surigao del Norte | 4 | 0 | 2765 | 202 | 4 | 0 | 0 | 3
Region XIII (Caraga) | Surigao del Sur | 14 | 1 | 17043 | 1246 | 14 | 0 | 0 | 10
V | Camarines Sur | 9 | 0 | 19755 | 1413 | 9 | 1 | 2 | 3
VI | Capiz | 10 | 2 | 22820 | 1800 | 10 | 2 | 3 | 1
VI | Iloilo | 123 | 96 | 274290 | 21648 | 123 | 30 | 13 | 2
VII | Bohol | 2 | 0 | 4458 | 334 | 2 | 0 | 0 | 2
VII | Cebu | 44 | 0 | 99000 | 7832 | 44 | 14 | 13 | 5
VIII | Leyte | 72 | 19 | 162576 | 12816 | 72 | 34 | 5 | 19
VIII | Northern Samar | 2 | 0 | 4446 | 310 | 2 | 0 | 0 | 2
VIII | Samar (Western Samar) | 52 | 7 | 115908 | 8476 | 52 | 0 | 0 | 52
X | Lanao Del Norte | 1 | 1 | 2318 | 165 | 1 | 0 | 0 | 1
X | Misamis Occidental | 1 | 1 | 2217 | 170 | 1 | 0 | 0 | 1
X | Misamis Oriental | 46 | 41 | 104512 | 8050 | 46 | 16 | 9 | 0
XI | Davao Del Sur | 49 | 1 | 111720 | 9849 | 49 | 8 | 14 | 14
XI | Davao de Oro | 3 | 0 | 6741 | 546 | 3 | 0 | 1 | 1
XII | South Cotabato | 5 | 0 | 11390 | 950 | 5 | 0 | 2 | 0
XIII | Agusan Del Norte | 10 | 0 | 22940 | 1680 | 10 | 1 | 0 | 5
XIII | Surigao Del Norte | 3 | 0 | 6984 | 510 | 3 | 0 | 2 | 1