## CLARIFICATION(Summary)
NO. | Date of Clarification | Requested by (Team) | Reference Bid Document (Main Bid Document, Annexes) | Reference Chapter/Annex/Template | Reference Section | Quotation from the Bid Document | Vendor's Clarification | Converge's Response | Remark
1 | OCT.19 | RAN | 01_RFP_5G_FWA_Master_Tender_Document | LOT 1: 5G RAN EQUIPMENT & ACCESS HARDWARE | 2.1 Spectrum Physics: Band n50 Advantage | The Operator, a duly franchised telecommunications entity operating pursuant to statutory authority and holding National Telecommunications Commission (NTC) Provisional Authority (PA Case No. 2017-084 for Broadband Data Services and PA Case No. 2017-291 for Nationwide Cellular Mobile Telephone System), has been officially granted a Temporary Permit to Propagate / Demonstrate (Permit No. RB-09-01-2026/DEMO, issued in reference to CPCN No. 2017-084) to conduct test broadcast, propagation, and technology demonstration in Band n50 (1457 – 1517 MHz, 60 MHz channel bandwidth). | Since the 1437–1457 MHz band has been assigned to another corporation in the NCR, kindly please confirm the following spectrum deployment plan: Metro Manila (NCR): 1457–1517 MHz (60 MHz) Rest of the country: 1437–1517 MHz (80 MHz) | CONFIRMED. The baseline spectrum deployment plan is formally confirmed as follows: 1. Metro Manila (NCR): 1457 – 1517 MHz (60 MHz continuous TDD bandwidth), fully compliant with the Operator's statutory authority and NTC demonstration permit. 2. Rest of the Country (Provincial / Regional): 1437 – 1517 MHz (up to 80 MHz IBW/OBW capability). Bidders' 5G NR Baseband Units (BBU) and Remote Radio Units (RRU) / Active Antenna Units (AAU) must natively support the full 3GPP Band n50 tuning range (1432 – 1517 MHz) in hardware, with carrier bandwidth software-configurable to 40 MHz, 50 MHz, 60 MHz, or up to 80 MHz as assigned. | Official Response issued via Bid Bulletin No. 1
2 | OCT.19 | RAN | 01_RFP_5G_FWA_Master_Tender_Document | LOT 1: 5G RAN EQUIPMENT & ACCESS HARDWARE | 2.1 Spectrum Physics: Band n50 Advantage | Operating Frequency: Band n50 (1432 – 1517 MHz), full 60 MHz IBW (Instantaneous Bandwidth) and OBW (Occupied Bandwidth). | Further clarification is required regarding the bandwidth that needs to be supported. Are there any special customization requirements for the filter's out-of-band rejection and emissions? Point 1: If the 1437–1457 MHz band is occupied by another operator, are there any specific spurious emission requirements that vendor's equipment must comply with for the low end and high end(1457M and 1517M)? Point 2: If the 1437–1457 MHz band is available for use outside the NCR areas, does the NTC impose any spurious emission requirements for the low and high end(1437M and 1517M)? | CONFIRMED & DETAILED: Point 1 (NCR Carrier: 1457–1517 MHz): Vendor equipment must comply with 3GPP TS 38.104 Category B Operating Band Unwanted Emissions (OBUE) and standard NTC Type Approval spurious emission masks. At the low end (1457 MHz), the RRU digital filtering and DPD must ensure sharp attenuation to protect adjacent users below 1457 MHz. At the high end (1517 MHz), equipment must implement appropriate filtering to protect the adjacent Maritime Mobile Satellite Service (MSS, 1518–1525 MHz per ITU-R M.2159-0), with unwanted emissions not exceeding -30 dBm/MHz. Point 2 (Outside NCR: 1437–1517 MHz): Standard 3GPP Band n50 TS 38.104 Category B emission masks apply at the 1437 MHz lower edge and 1517 MHz upper edge. No non-standard or proprietary hardware filtering customization is required beyond compliant 3GPP Release 16/17 Band n50 radio hardware. | Official Response issued via Bid Bulletin No. 1
3 | OCT.20 | RF Planning | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 -5 sitelist | To support the above planning activities, vendor kindly requests Converge to share the following information for the nearest tower(s): location (longitude / latitude) and tower height. | CONFIRMED & PROVIDED. Candidate site geographic coordinates (Latitude / Longitude in WGS84) and nominal Tower Heights (AGL in meters) for all 1,000 Phase 1 candidate sites are fully provided in Document 07 ('07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx'), specifically under sheets 'Phase 1 (First 1,000 Sites)' and 'Towerco_list' (covering PhilTower, EdgePoint, EDOTCO, and Unity assets). | Official Response issued via Bid Bulletin No. 1
4 | OCT.20 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE | 2.3 Transmission & Backhaul Topology | Fiber Baseline Reconciliation Note: The preliminary raw GIS planning dataset identified 2,405 spatial markers; following ground-truth fiber audit filtering against operational distribution plant, 1,296 confirmed optical nodes and 4,401 fiber segments were verified as immediate interconnect targets (subject to joint site survey verification on the ground). | Vendor proposes that Converge may clarify the defination of "fiber segments" and the "optical nodes" | CLARIFICATION OF DEFINITIONS: - 'Optical Node': An audited, active Converge point-of-interconnect—specifically an Optical Distribution Frame (ODF), Fiber Distribution Terminal (FDT), or Primary Fiber Hub equipped with available optical splice/splitter capacity to serve as the backhaul transmission handover point. - 'Fiber Segment': An audited physical fiber optic cable route (feeder, distribution, or lateral FOC) spanning between the optical node/central office and the customer/tower drop point, as verified in Converge's audited GIS distribution plant. | Official Response issued via Bid Bulletin No. 1
5 | OCT.20 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE | 2.3 Transmission & Backhaul Topology | Terrestrial Fiber Optic Cable (FOC): 98.3% of Phase 1 sites connect via terrestrial fiber drops (Class A: Node <= 0.5 km; Class B: Node <= 1.0 km; Class C: Line-tap splice closure <= 0.5 km; Class D: Lateral/Microwave <= 3.0 km). | Vendor proposes that Converge may clarify the defination of " C: Line-tap splice closure <= 0.5 km" | CLARIFICATION OF DEFINITION: 'Class C: Line-tap splice closure <= 0.5 km' designates a candidate macro tower location where an existing aerial or underground Converge trunk/distribution fiber optic cable passes within 500 meters of the site compound, and interconnection will be achieved by cutting into the cable at an existing or newly inserted inline splice closure (FOSC / Dome Enclosure) rather than routing back to a centralized ODF/node. | Official Response issued via Bid Bulletin No. 1
6 | OCT.20 | Transmission | 05_SiteSurvey, RFPlanning & Civil/Power Engineering Guidelines | 2. DETAILED TECHNICAL SITE SURVEY REPORT (TSSR) REQUIREMENTS | 2.4 Backhaul Transmission Path Survey | Audited Converge Fiber Network Match (subject to verification on the ground): Distance to nearest confirmed node candidate (Class A <= 0.5 km, Class B <= 1.0 km) or line-tap closure (Class C <= 0.5 km). | Does the "distance to the nearest node" refer to the distance to the 5G base station ? Vendor proposes that Converge may clarify the defination of " distance to line-tap closure" | CLARIFICATION OF DEFINITIONS: - 'Distance to Nearest Node': Refers to the estimated terrestrial linear cable route distance from the proposed 5G Macro Tower compound to the nearest confirmed Converge Optical Node (Class A <= 0.5 km; Class B <= 1.0 km). - 'Distance to Line-Tap Closure': Refers to the linear cable distance from the 5G Base Station to the designated trunk cable splice closure (Class C <= 0.5 km). | Official Response issued via Bid Bulletin No. 1
7 | OCT.20 | Transmission | 01_RFP_5G_FWA_Master_Tender_Document | 2. PROJECT BACKGROUND, OPERATING ENVIRONMENT & TECHNICAL BASELINE | 2.3 Transmission & Backhaul Topology | 98.3% of Phase 1 sites connect via terrestrial fiber drops (Class A: Node <= 0.5 km; Class B: Node <= 1.0 km; Class C: Line-tap splice closure <= 0.5 km; Class D: Lateral/Microwave <= 3.0 km). | Vendor respectfully proposes that Converge confirm whether the Microwave solution for Class D is to be considered within the Vendor's scope of supply, or whether it will be provided by Converge directly. | CONFIRMED: VENDOR SCOPE OF SUPPLY / PRICING. Class D sites (~1.7% of Phase 1 sites, plus microwave backup links for island sites) require a turnkey high-capacity microwave backhaul link (11 GHz / 18 GHz / 23 GHz or E-Band 80 GHz, minimum 1.0 Gbps full-duplex throughput). Bidders must quote the microwave split-mount hardware (IDU, ODU, antenna, IF cabling) and installation services in Appendix B (Commercial BoQ) under Lot 1 / Lot 3 options. Converge reserves the right to provide direct fiber drops prior to NTP where feasible. | Official Response issued via Bid Bulletin No. 1
8 | OCT.20 | Power | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE (12 items) | PWR-01 | 19" 3U/4U modular high-efficiency switchmode rectifier system; continuous rating >= 12.0 kW @ -48V DC (4 x 3.0 kW modules in N+1 redundancy). | Kindly confirm whether the 12 kW rating refers to the total installed rectifier capacity (4 × 3 kW modules, including one N+1 redundant module) rather than the output that must be maintained after a single module failure. For reference, a typical load — 3 kW BTS with a 400 Ah battery charged at 0.2C — requires a total DC demand of 7.28 kW (4.28 kW charging + 3 kW BTS load). This demand is fully served by three 3 kW modules, with a fourth module providing N+1 redundancy (12 kW installed; 9 kW available under N+1). Vendor appreciates your confirmation that this load-based N+1 sizing methodology is acceptable, including functionally equivalent configurations. | CONFIRMED ACCEPTABLE. The required sizing methodology is confirmed as follows: - Total Installed Rectifier Capacity: >= 12.0 kW composed of 4 × 3.0 kW (or 4 × 4.0 kW) modular hot-swappable switchmode rectifier modules in an N+1 architecture. - Active Operational Capacity under N+1: With a single module failure (3 operational modules), the system provides 9.0 kW continuous DC output, which comfortably exceeds the peak site DC demand of 7.28 kW (3.0 kW BTS RAN load + 4.28 kW fast battery recharging at 0.2C for 400 Ah / 20 kWh lithium bank). Vendor's proposed load-based N+1 configuration is fully compliant. | Official Response issued via Bid Bulletin No. 1
9 | OCT.20 | Power | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE (12 items) | PWR-01 / PWR-04 | 19" 3U/4U modular high-efficiency switchmode rectifier system; continuous rating >= 12.0 kW @ -48V DC (4 x 3.0 kW modules in N+1 redundancy). Lithium Iron Phosphate (LiFePO4 / LFP) battery energy storage system ... (minimum >= 20.0 kWh nominal installed capacity, minimum 400 Ah to 450 Ah @ 48V ...). | Please clarify whether pole-mounted installation is mandatory or an integrated ground-mounted outdoor cabinet is acceptable for power HW and RAN HW ? | CLARIFICATION OF INSTALLATION STANDARD: Both configurations are acceptable depending on site compound archetype: 1. Co-location / Rooftop Sites with Space Constraints: Integrated outdoor pole-mounted or wall-mounted power/RAN solutions are acceptable where ground compound footprint is restricted by the TowerCo. 2. Greenfield / Ground Compound Sites (Standard): An integrated, weather-resistant (IP55) ground-mounted outdoor power & battery cabinet installed on an elevated equipment concrete pad is the preferred baseline design. | Official Response issued via Bid Bulletin No. 1
10 | OCT.20 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 6 - Site Acq & Civils | LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS |  | Who is the responsible for transmission and last mile ? | DIVISION OF RESPONSIBILITY: - Converge / TelTech Scope: Core IP/MPLS network, backbone transport, optical node infrastructure, upstream bandwidth, fiber drop cable provisioning up to the tower demarcation/ODF, and Starlink satellite terminals. - Vendor Scope: Turnkey supply of optical transceivers (10G/25G SFP28 eCPRI and 10G/25G SFP+ backhaul optics), armored optical patchcords, terminal fiber interconnect from tower demarcation box to Baseband Unit (BBU), and end-to-end backhaul circuit acceptance testing during SSV. | Official Response issued via Bid Bulletin No. 1
11 | OCT.20 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 2 - Power & Passive | LOT 2: POWER SYSTEMS & PASSIVE INFRASTRUCTURE |  | There are no engineering services items about Rectifier, Battery, Tap-Off Box & Submeter, Getset, pls confirm engineering services isn't vendor's scope. | CLARIFICATION OF SERVICES SCOPE: Installation, wiring, and commissioning of the rectifier, lithium battery bank, AC tap-off box, submeter, and optional genset are included in the turnkey rollout scope under Lot 1 Services (Table 2: RAN Turnkey Rollout Services, Item RAN-SVC-02) and Lot 5 (Civil Works & Power Integration). Turnkey implementation includes all physical mounting, DC cabling, breaker terminations, grounding, and commissioning of the power subsystem. | Official Response issued via Bid Bulletin No. 1
12 | OCT.20 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 5 - Site Acq & Civils | LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS |  | Please provide detailed site design for each civil work item, such as: Equipment Pad Foundation & Cable Gantry, Greenfield Compound Civil Works & Foundation, Grounding Grid & Lightning Protection System, 30m/40m Galvanized Steel Monopole Tower. | CLARIFICATION & GUIDELINES: Typical engineering guidelines, wind loading specifications (minimum 250 km/h typhoon survivability), soil bearing criteria, and grounding grid requirements (<= 5 Ohms) are detailed in Document 05 ('05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf'). Detailed structural fabrication and foundation construction drawings are established during the Joint Technical Site Survey (TSSR) stage (Lot 5 Milestone 1) based on site-specific geotechnical soil test results and actual compound boundaries. Bidders are invited to submit their standard type-approved civil drawings and monopole designs in their technical proposal for committee evaluation. | Official Response issued via Bid Bulletin No. 1
13 | OCT.20 | Project | 06_RFP_Commercial_Price_Book_and_BoQ_Template | Lot 5 - Site Acq & Civils | LOT 5: SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS |  | There are no engineering services items about Commercial Power Access, pls confirm engineering services isn't vendor's scope. | COORDINATED SCOPE: - TelTech / Operator Scope: Payment of official electric cooperative (EC / Meralco / DU) application fees, transformer capital contributions, security deposits, and power supply contracts. - Vendor Scope: Turnkey on-site civil and electrical works from the property line / service drop demarcation pole to the equipment pad—including service entrance conduit/riser, utility revenue class kWh meter base/enclosure, main service disconnect switch, AC panel (ACPDB), and surge protective device (Type 1+2 SPD). | Official Response issued via Bid Bulletin No. 1