## Sheet1
No. |  | Docs Name | Chapter Number | Description From RFP Files | Domain Classification | Clarification Question | Converge's Response | Remark
1 | 1 | 01_RFP_5G_FWA_Master_Tender_Document | 5. TENDER SUBMISSION STRUCTURE & COMPLIANCE REQUIREMENTS | Form A — Bid Submission Letter & Consortium Structure: Executed by authorized corporate officers. | Other Business Matters | Kindly provide this Form A. | CONFIRMED & PROVIDED. The official Form A template (Bid Submission Letter & Consortium Structure) is provided as Attachment 1 to Bid Bulletin No. 1 and is available for download directly in the online RFP portal (Document Library Tab 1). | Official Response issued via Bid Bulletin No. 1
2 | 2 | 01_RFP_5G_FWA_Master_Tender_Document | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-02 Real-time convergent charging system (CCS/CHF) integrated via 3GPP Nchf/Diameter Ro, supporting real-time balance rating and session cutoff. | OSS & BSS Integration | Is billing considered in scope? | CLARIFICATION OF BILLING SCOPE: In Phase 1, real-time Convergent Charging (CCS/CHF via 3GPP Nchf/Diameter Ro) for prepaid FWA balance management, session cutoff, and quota tracking is the mandatory turnkey scope. Complex postpaid cyclic invoice generation and accounts receivable (A/R) are handled by Converge's enterprise billing system via standard CDR/API export, or may be proposed as an optional modular add-on. | Official Response issued via Bid Bulletin No. 1
3 | 3 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-01 Product Catalog & Tariffs Configurable telecom product catalog supporting 4 consumer FWA plans (₱599, ₱799, ₱999, ₱1,299), SME tiers, and flexible speed-cap policies. | OSS & BSS Integration | Huawei system support many kinds of product but need help to detail your offering requirment. Such as: 1. These offerings need group management (such as family package) or not? 2. These offerings need rollover feature (such as unused data rollove to next cycle) or not? 3. These offerings should support auto upgrade (such as 599 not enough of this cycle automatical upgrade to 700 for next cycle) or not? | CLARIFICATION OF PRODUCT OFFERINGS: 1. Group Management: Optional roadmap feature; single-account per CPE is baseline for Phase 1. 2. Rollover Feature: Supported in product catalog configuration (unused high-speed data quota rolls over into the subsequent 30-day renewal cycle upon prompt re-subscription). 3. Auto-Upgrade: Speed-cap throttling (e.g. throttle to 1 Mbps upon quota exhaustion with option for customer to purchase speed-boost add-on) is the required policy, rather than forced tariff upgrade. | Official Response issued via Bid Bulletin No. 1
4 | 4 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-02 Prepaid Charging (CHF) Real-time convergent charging system (CCS/CHF) integrated via 3GPP Nchf/Diameter Ro, supporting real-time balance rating and session cutoff. | OSS & BSS Integration | Huawei system support standard 3GPP protocal and real-time balanace rating and charging process. some concerns: 1. We assume BSS will support 5G SA network only. 2. Smart quota, dynamic granted quota feature should enable or not? | CLARIFICATION OF CHARGING REQUIREMENTS: 1. Network Architecture: Confirmed 5G Standalone (SA) only. 2. Quota Management: Standard 3GPP dynamic granted quota (DCC) and threshold notification alerts (at 80% and 100% quota consumption via SMS / self-care push notification) must be enabled. | Official Response issued via Bid Bulletin No. 1
5 | 5 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-03 Omnichannel Payments Native REST API integration with Philippine payment gateways: GCash, Maya (PayMaya), 7-Eleven CLiQQ OTC, Bayad Center, and QR Ph. | OSS & BSS Integration | Huawei system can open the REST API for payment. some concerns： 1. Should support Voucher recharge or not(3rd party send voucher no and PIN as example)? 2. Should consider Recharge tax or not(When feedback the message to 3rd party or notification to end-subscribers)? 3. Should consider Recharge promotion or not(When feedback the message to 3rd party or notification to end-subscribers)? | CLARIFICATION OF DIGITAL PAYMENT RECHARGE: 1. Voucher Recharge: Omnichannel digital recharge via GCash, Maya, and QR Ph is primary. Third-party electronic voucher PIN recharge is supported as an optional secondary channel. 2. Taxation: BSS catalog must support Philippine 12% Value Added Tax (VAT) calculation and display on payment confirmations and receipts. 3. Promotions: The charging system must natively support marketing promotional rules (e.g., bonus data allowances, referral credits, or promotional validity extensions). | Official Response issued via Bid Bulletin No. 1
6 | 6 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION |  | OSS & BSS Integration | What's the FWA service scenario shall be supported by the BSS? For example: New Registration, SIM Location Locking, Address Change, Transfer Owership, Contract Lifecycle Management, CPE/WIFI Router Installment | MANDATORY FWA SERVICE SCENARIOS: The turnkey BSS/OSS must support: 1. New Customer Digital Registration & KYC. 2. Strict SIM-IMEI & Cell-ID Location Locking (binding the FWA service to the authorized installation address to prevent nomadic/mobile unauthorized usage). 3. Relocation / Address Change workflow (manual or automated cell unbinding upon authorized relocation request). 4. Transfer of Ownership & Account Termination. 5. Contract / Subscription Lifecycle Management. 6. CPE Inventory Assignment and Remote FOTA Management. | Official Response issued via Bid Bulletin No. 1
7 | 7 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION |  | OSS & BSS Integration | What's the payment mode shall be supported by the BSS? Prepaid, Postpaid, Hybrid? If need postpaid, and hybrid, does it meant the vendor need to provide the billing, invoice relevant components? | PAYMENT MODE ARCHITECTURE: The primary business model for Phase 1 is 100% Prepaid with 30-day recurring subscription validity. Postpaid hybrid invoicing is handled via integration with Converge's enterprise billing platform; vendors are only required to provide the real-time prepaid CHF/CCS engine and payment gateway connectors. | Official Response issued via Bid Bulletin No. 1
8 | 8 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-03 Omnichannel Payments Native REST API integration with Philippine payment gateways: GCash, Maya (PayMaya), 7-Eleven CLiQQ OTC, Bayad Center, and QR Ph. | OSS & BSS Integration | Beside the listed systems, shall the new BSS integrate with ERP Finance system, DWH/BI? Is there data streaming requirement for real-time data synchronization? | ENTERPRISE INTEGRATIONS: The BSS must support standard daily accounting journal export (GL feed) to Converge's SAP ERP and daily CDR/event extraction to the enterprise Data Warehouse (DWH). Real-time Kafka-based event streaming is preferred for operational analytics. | Official Response issued via Bid Bulletin No. 1
9 | 9 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | BSS-04 Subscriber Portal & App Native Android/iOS subscriber self-care mobile app and responsive web portal for balance checking, online top-up, and speed-test diagnostics. | OSS & BSS Integration | Beside the self-care channels, shall the vendor provide the retail portal which can be used by the in-shop agent or call center agent? | RETAIL & AGENT PORTAL SCOPE: CONFIRMED. Vendor must provide a secure, web-based Customer Service Representative (CSR) and Authorized Dealer Portal for retail store agents, partner distribution dealers, and call center hotlines to perform customer onboarding, balance lookups, and troubleshooting. | Official Response issued via Bid Bulletin No. 1
10 | 10 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION |  | OSS & BSS Integration | Beside the CPE inventory management, shall the new BSS/OSS system manage the MSISDN and SIM card resource? | RESOURCE MANAGEMENT SCOPE: CONFIRMED. The turnkey BSS must incorporate a unified resource inventory management module for SIM cards (ICCID), MSISDNs, and CPE hardware serial numbers (IMEI / MAC). | Official Response issued via Bid Bulletin No. 1
11 | 11 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION |  | OSS & BSS Integration | Does the exisiting network have PCF (Policy Control Function)? Does the BSS need to integrate with this? | POLICY CONTROL (PCF) INTEGRATION: Under Lot 3 (5G Core Network), the vendor is delivering the turnkey 5G SA Core, which includes the Policy Control Function (PCF). The BSS will integrate directly with the vendor's supplied PCF via standard 3GPP N7 / N28 interfaces. | Official Response issued via Bid Bulletin No. 1
11 | 12 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 3. RF PROPAGATION & CELL DIMENSIONING GUIDELINES | Calculated Reliable Cell Radius | Wireless and Delivery | The coverage radius is too large. It is recommended that the coverage radius be 1 km in suburban areas and 1.5 km in rural areas. | CONFIRMED ACCEPTABLE. The revised planning criteria are formally adopted: - Suburban / Dense Urban: Nominal reliable cell radius of 1.0 km. - Rural / Semi-Rural: Nominal reliable cell radius of 1.5 – 2.0 km. These guidelines ensure 95% indoor/outdoor coverage reliability across Band n50 and will govern the updated link budget benchmarks in Document 05. | Official Response issued via Bid Bulletin No. 1
12 | 13 | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | 3.1 Core Radio KPIs (Calculated 24/7/365 Nationwide) | KPI-RAN-04 | Wireless and Delivery | In the case of multiple users, the environment is complex and the attenuation is large. It is recommended that the average cell traffic be controlled within 40 Mbps/10 MHz. | CONFIRMED ACCEPTABLE. The recommended engineering planning baseline of 40 Mbps average cell throughput per 10 MHz of spectrum (yielding ~240 Mbps average cell throughput on a 60 MHz Band n50 TDD carrier with 4:1 DL:UL frame structure) is endorsed as realistic busy-hour design criteria for multi-user FWA deployment. | Official Response issued via Bid Bulletin No. 1
13 | 14 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines | 2.2 Tower Structure & Loading Audit (Co-Location Sites) | Structural Loading Verification: Confirmation that existing tower members and foundation can accommodate additional 3x 8T8R RRUs/AAUs (< 45 kg each) and wind load profile of 250 km/h | Site, civil work, and managed services | For TowerCo tower, the tower structural Loading verification usually under TowerCo Scope ( Operator provide the equipment list and loading info to TowerCo, TowerCo to provide result). 1. Please kindly suggest if we need to provide structural loading verification service or not. Or we quote this service in a seperate item. 2. If Loading Verification fail, Please suggest the next step (build new tower, or request towerco retrofit tower) Suggest: TowerCo do the structural loading verification. | STRUCTURAL LOADING RESPONSIBILITY: 1. For the 897 TowerCo co-location sites, Tower Structural Loading Verification is the responsibility of the Operator and the TowerCo under the executed Master Lease Agreement (MLA). The vendor provides equipment weights, dimensions, wind load surface area, and cable routing details. 2. If loading verification fails, the TowerCo is obligated under the MLA to perform structural retrofitting, or the Operator will reassign an alternative candidate tower from the pre-approved pool. | Official Response issued via Bid Bulletin No. 1
14 | 15 | 04_Appendix_C_SLAs_KPIs_Liquidated_Damages |  | Acceptance Standard and procedure for Civil and Power Part | Site, civil work, and managed services | Whats the acceptance standard and procedure for Tower, Civil and Power part? Suggest: Huawei can propose if needed. | ACCEPTANCE STANDARDS: Acceptance standards and checklists for Civil, Tower, and Power are detailed in Document 05 ('05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf') and Document 04 (Appendix C). Vendor's standard QA/QC procedure and handover templates are acceptable subject to Joint Technical Committee approval. | Official Response issued via Bid Bulletin No. 1
15 | 16 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines 03_Appendix_B_Commercial_Proposal_BoQ_Templates | 2.3 Power Infrastructure & Utility Audit TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | Existing Commercial AC Utility Power: Electric Cooperative / Distribution Utility name (e.g., MERALCO, PELCO, BENECO, CAPELCO, ILPI). Service Entrance Capacity: Transformer rating (kVA), service voltage (230V / 400V, 60 Hz), breaker rating, and phase balance | Site, civil work, and managed services | For New Site, the BOQ not include the commerical power application and installation (From COOP to Site). Do we need to quote this part? If the commerical power not ready, does huawei need to provide the temporary power to turn on the site? Suggest: Commerical power shall included and temporary power can consider as VO when needed. | COMMERCIAL POWER & TEMPORARY POWER: 1. Official electric cooperative (EC/DU) application fees and power connection contracts are Operator scope. 2. Turnkey on-site civil and electrical installation (service entrance, meter base, disconnect, ACPDB) is Vendor scope. 3. If commercial utility power is delayed by the power utility, the site will be provisionally accepted using temporary generator power where expedited on-air is mutually agreed, with generator runtime costs handled via established Variation Order (VO). | Official Response issued via Bid Bulletin No. 1
16 | 17 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Standard design and type approved brand for Civil and power | Site, civil work, and managed services | 1. Do you have Type approved brand for Tower, Genset, Aviation light, ACPDB and other power or civil material? 2. Can you provide Typical Design drawing for Tower, Fence and foundation? Or Huawei to propose the solution. Suggest: Huawei can propose if needed. | TYPE-APPROVED BRANDS & CIVIL DESIGNS: 1. Civil and electrical materials must comply with Philippine Electrical Code (PEC), ASTM, and PNS standards (Class A hot-dip galvanized steel, NEMA 3R/4 outdoor enclosures, Schneider/ABB/Eaton breakers). 2. Typical structural and foundation drawings are provided in Document 05. Bidders may propose their type-approved standard foundation, fence, and monopole designs in their technical submission. | Official Response issued via Bid Bulletin No. 1
17 | 18 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Site Acquisition & Permitting Support | Site, civil work, and managed services | 1. For the TowerCo site, Is it Converge Scope to rent and negotiate with TowerCo? Suggest: For towerco site, should be converge's responsibility for site renting and negoitate with towerco. 2. If the site hunting fail, whats the next step? (Converge to provide another site for hunting to swap the fail site? or cancel the site). Suggest: Huawei will hunt each site with 5 options, if site still failed, suggest customer change the site or provide VO for new option hunting. | SITE ACQUISITION & TOWERCO LEASE NEGOTIATION: 1. For the 897 Co-location sites, lease agreements, space reservation, and commercial negotiations with TowerCos (PhilTower, EdgePoint, EDOTCO, Unity) are strictly the Operator's responsibility under Master Lease Agreements (MLA). 2. For the 103 Greenfield sites, the vendor performs primary site hunting with up to 3 candidate parcels. If site hunting fails due to zoning, legal, or title defects, the Operator will provide a replacement candidate site without vendor penalty. | Official Response issued via Bid Bulletin No. 1
18 | 19 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | PWR-EQ 04 15 kVA Diesel Generator Set Soundproof canopy, 500L–1000L tank, ATS, auto-start | Site, civil work, and managed services | Huawei suggest put the Genset and fuel tank in a equipment pad. no need to build shelter for genset. | GENSET INSTALLATION STANDARD: CONFIRMED ACCEPTABLE. Outdoor soundproof weatherproof canopy gensets installed directly on an elevated concrete equipment pad (without an enclosed brick/steel shelter building) are fully acceptable. | Official Response issued via Bid Bulletin No. 1
19 | 20 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | Fiber to Site Scope | Site, civil work, and managed services | Is it Converge scope for Fiber or Huawei need to do? | FIBER BACKHAUL RESPONSIBILITY: Converge provides the core optical distribution network, terrestrial fiber drop cable up to the site boundary/ODF, and Starlink satellite terminals. The vendor is responsible for optical transceivers, patchcords, and joint I&C testing from the demarcation box to the BBU. | Official Response issued via Bid Bulletin No. 1
20 | 21 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 6: LOT 5 — SITE ACQUISITION, DETAILED SITE SURVEY (TSSR), RF DESIGN & CIVIL WORKS | VO procedure | Site, civil work, and managed services | For the non-standard and special construction reuqirment, such as manul hauling, retaining wall and others, Can huawei claim seperately as VO? | VARIATION ORDER (VO) ELIGIBILITY: CONFIRMED. Non-standard civil construction conditions (such as hard rock excavation requiring pneumatic breakers/blasting, manual material hauling exceeding 500 meters across unpaved/mountainous terrain, and engineered retaining walls) are recognized as eligible for Variation Orders based on pre-agreed unit rates in Appendix B (Lot 5 BoQ). | Official Response issued via Bid Bulletin No. 1
21 | 22 | 03_Appendix_B_Commercial_Proposal_BoQ_Templates | TABLE 3: LOT 2 — POWER SYSTEMS & PASSIVE INFRASTRUCTURE | DC tap enclosure, revenue Class 1.0 kWh meter, SPD Type 2 | Site, civil work, and managed services | For TowerCo Power part, Usually Towerco will provide AC and DC, Please suggest if Huawei need to provide the meter and releated power material to tap to existing power system. | TOWERCO POWER EQUIPMENT: Where TowerCo supplies regulated -48V DC power directly, vendor needs only connect to the designated DC distribution breaker. Where TowerCo provides raw AC utility power, vendor supplies the submeter, ACPDB, and surge suppression. | Official Response issued via Bid Bulletin No. 1
22 | 23 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf; 04_Appendix_C_SLAs_KPIs_Liquidated_Damages.pdf | Section 5 SSV — Ping RTT acceptance; KPI-RAN-07 Radio Round-Trip Latency | SSV requires "Ping RTT <= 18 ms target (<= 30 ms maximum contractual limit) to local UPF IP address over fiber backhaul." KPI-RAN-07 sets the same 18 ms Target Standard / 30 ms Minimum Threshold. However, 17 Starlink backhaul sites have inherent satellite RTT of 25-50 ms (Starlink Business typical), which exceeds the 30 ms contractual maximum. | Testing / KPI | For the 17 Starlink backhaul sites, should the RTT KPI threshold be adjusted (e.g., relaxed to <= 50 ms maximum) given the inherent LEO satellite latency? Or are these sites exempt from KPI-RAN-07? Please confirm whether a separate KPI schedule applies to satellite backhaul sites. | STARLINK SATELLITE RTT LATENCY KPI: CONFIRMED & ADOPTED. For the 17 remote/island candidate sites backhauled via Starlink LEO satellite, the Ping RTT SLA is relaxed to <= 60 ms target (<= 80 ms maximum) during SSV and cluster acceptance, reflecting satellite orbital propagation latency. | Official Response issued via Bid Bulletin No. 1
23 | 24 | 01_RFP_5G_FWA_Master_Tender_Document | 2.3 Transmission & Backhaul Topology / App.C 3.1 KPI-RAN-07 | 98.3% of Phase 1 sites connect via terrestrial fiber drops (1,296 confirmed optical nodes and 4,401 fiber segments, subject to verification on the ground); 1.7% use Starlink Business arrays. KPI: End-to-End User Latency (RTT) <= 30ms Max / <= 18ms Target, CPE to local UPF. | Wireless and Delivery | 1. Please provide the verified per-site fiber node/segment list (optical node ID, connection class A-D, committed bandwidth) after on-ground verification — the site list shows all Starlink-fed sites have dist-to-node > 20 km. 2. Please confirm that backhaul resources (Converge fiber SLA, Starlink links) are Operator/third-party provided, and the Operator is responsible for their availability, bandwidth and latency. 3. Do you accept media-tiered RTT KPIs: fiber-fed sites bound by <= 30ms, while satellite-fed sites follow their link physics (e.g. <= 100ms)? 4. Please confirm backhaul outage time is excluded from KPI assessment (RAN availability, end-to-end availability, packet loss). Expected: written confirmation + per-site backhaul list. | BACKHAUL RESOURCES & SLA EXCLUSIONS: 1. Candidate site list in Document 07 provides audited fiber distance classes (Class A <= 0.5km to Class D). 2. Confirmed: Backhaul transport facilities (Converge terrestrial FOC and Starlink links) are Operator-provided. 3. Media-tiered RTT KPIs are formally confirmed: Fiber sites <= 30 ms maximum; Satellite sites <= 80 ms maximum. 4. Confirmed: Downtime caused by upstream third-party transmission outages or fiber cuts outside the site compound is excluded from vendor RAN availability penalty assessments. | Official Response issued via Bid Bulletin No. 1
24 | 25 | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Site Infrastructure & Tower Strategy | Siting overlay matched against 13,746 verified operational cell towers spanning six tower portfolios (PTCI/MIDC, FTAP Globe, EdgePoint, FTAP Smart, LBS, FTAP BTS). | Site, civil work, and managed services | 1. Please provide TowerCo lease confirmations / ownership proofs for all co-location sites before NTP. 2. Please provide a tower-readiness schedule per site (lease signed, structural audit, access) feeding the 1,000-sites/365-day plan. 3. Do you agree to back-to-back liability — delays caused by TowerCo approval, access or structural defects are excluded from Huawei's schedule liability with automatic time extension? Expected: written commitment + schedule. | TOWERCO LEASE READINESS & SCHEDULE COMMITMENTS: 1. Operator will provide TowerCo Site Access Authorizations prior to Notice to Proceed (NTP) for each site batch. 2. Confirmed: Schedule milestones commence upon formal Site Handover with approved TowerCo access. Delays caused exclusively by TowerCo structural retrofit or access permit delays will receive day-for-day time extensions without liquidated damages. | Official Response issued via Bid Bulletin No. 1
25 | 26 | 01_RFP_5G_FWA_Master_Tender_Document | 2.2 Deployment Typology / App.C 2.1 Milestones M1-M4 | Class T4 (Greenfield Monopole Required): 10.3% of Phase 1 sites (103 sites) requires self-constructed 30m/40m monopole, civil shelter, utility transformer drop, backup diesel/solar. Milestone 1: TSSR & Nominal Engineering Approval within 45 calendar days for all 1,000 priority sites; Milestone 4: 1,000 sites within 365 days. | Site, civil work, and managed services | 1. Please confirm an 'Excluded Sites' mechanism — sites blocked by permits (LGU/Barangay/CAAP), land, power connection, TowerCo or coverage issues are deducted from milestone counts. 2. May Milestone-1 TSSR be submitted in phasing (first 200 sites in 45 days, then 300 sites every 30 days), given typical permitting and TowerCo access cycles in the Philippines? 3. Do you accept the 365-day milestone counted in net working days (or auto-extended by the same number of days of Operator/third-party delays)? 4. Please confirm permit fees and utility connection application costs are pass-through (CCP). Expected: written confirmation + revised milestone wording. | MILESTONES & PERMITTING CLAUSES: 1. Blocked Sites Mechanism: Sites blocked by LGU moratorium, right-of-way disputes, or power utility delays beyond 45 days will be swapped with approved reserve sites without schedule penalty. 2. Phased TSSR Submissions: Submitting TSSRs in progressive monthly batches (e.g. 150–200 sites per month) is fully acceptable. 3. Project schedule will account for approved force majeure and Operator/third-party delay extensions. 4. Official LGU building permit statutory fees and utility interconnection fees are pass-through to Operator. | Official Response issued via Bid Bulletin No. 1
25 | 27 | 01_RFP_5G_FWA_Master_Tender_Document | LOT 5: RF PLANNING, SITE SURVEY & CLUSTER OPTIMIZATION | Technical Site Survey Report (TSSR) for each assigned candidate barangay: Detailed structural load analysis on existing towers, antenna mounting space, azimuthal line-of-sight (LOS) drone photographic sweeps (360° at 20m, 30m, 40m AGL) | Site, civil work, and managed services | Can you accept not requiring a drone, as long as the photos can reflect the 360° surrounding environment, and AGL refer to TowerCo provided height for FWA project? | DRONE SURVEY WAIVER: CONFIRMED ACCEPTABLE. Where drone flight permits cannot be secured from CAAP or local authorities within 14 days, high-resolution 360-degree panoramic telephoto ground photography combined with verified TowerCo structural engineering drawings is accepted for TSSR approval. | Official Response issued via Bid Bulletin No. 1
25 | 28 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 2: POWER SYSTEMS & PASSIVE SITE INFRASTRUCTURE | SOC requirement | Power system and delivery | 1. Do they have Blade requirement ? 2. Can we request room layout or site pictures if available for Lithium Battery Approval? 3. Is there existing rectifier cabinet in existing sites? 4. If SAT requirement is one per equipment or the whole quantity? 5. What is the Total actual DC power for single rectifier requipment? | POWER SYSTEM & BATTERY SPECIFICATIONS: 1. Standard 19" rack-mount modular switchmode rectifiers and 19" rack-mount 48V 100Ah LiFePO4 battery modules are required. 2. Typical site DC load is ~2.8 to 3.2 kW continuous. Sizing requirement is 12.0 kW installed capacity (4 × 3 kW modules, N+1 redundancy). 3. Site layout and equipment pad drawings are provided in Document 05. | Official Response issued via Bid Bulletin No. 1
25 | 29 | 01_RFP_5G_FWA_Master_Tender_Document.pdf | 2.1 Spectrum Physics: Band n50 Advantage | Band n50 operates in the 1.5 GHz L-Band (1432 – 1517 MHz), providing superior propagation characteristics over mid band frequencies (e.g., 3.5 GHz Band n78): | Wireless and Delivery | 1. According to ITU-R M.2159-0, the 1518–1525 MHz frequency band is used for maritime communications satellites. If the frequency range of the RRU includes 1512–1517 MHz, it cannot ensure a -30 dB suppression within the 1518–1523 MHz band. Therefore, please confirm whether the NTC allows the use of the 1512–1517 MHz spectrum. 2. We understand that the 1427–1457 MHz frequency band will be allocated by the NTC as spectrum for enterprises. Please consider whether Converge intends to use the 1457–1467 MHz band. It is recommended to refer to the NTC's spectrum usage regulations to determine whether a guard band is required. Therefore, please confirm whether the NTC allows the use of the 1457–1467 MHz spectrum. | SPECTRUM PHYSICS & FILTERING (1457–1517 MHz): 1. Standard 3GPP Band n50 Category B filtering guarantees required suppression (-30 dBm/MHz) into the adjacent 1518–1525 MHz band (maritime satellite). Use of the 1457–1517 MHz band is formally authorized under NTC demonstration permit. 2. In NCR, operation is continuous 60 MHz (1457–1517 MHz); digital filtering within the RRU prevents out-of-band emissions below 1457 MHz. | Official Response issued via Bid Bulletin No. 1
25 | 30 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | overall | if need to do frequency clearance test to ensure the frequency is clean for network deployment | Wireless and Delivery | Besides interference analysis with maritime communication satellites, suggest to carry out frequency clearance scan before commercial network deployment. | FREQUENCY CLEARANCE TEST: CONFIRMED & AGREED. Vendor and Operator RF teams will conduct joint baseline spectrum clearance sweeps prior to site commercial on-air to identify and resolve any legacy co-channel or adjacent interference. | Official Response issued via Bid Bulletin No. 1
| 31 | 05_Appendix_D_Site_Survey_RF_Planning_Civil_Power_Guidelines.pdf | 5.. SINGLE SITE VERIFICATION (SSV) & CLUSTER ACCEPTANCE CRITERIA | 5 stationary measurement points per sector (Near: 500m, Mid: 1.5 km, Far/Edge: 3.0 km). | Wireless and Delivery | Is there Dl &UL speed requirement at near, Mid, and Far/Edge? | SSV SPEED TARGETS PER DISTANCE ZONE: - Near Zone (< 500m): DL >= 200 Mbps / UL >= 30 Mbps. - Mid Zone (1.0 – 1.5 km): DL >= 100 Mbps / UL >= 20 Mbps. - Far / Cell Edge (>= 2.0 km): DL >= 25 Mbps / UL >= 5 Mbps (minimum SLA threshold). | Official Response issued via Bid Bulletin No. 1
25 | 32 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | 3GPP Release 16/17 compliant 5G NR sub-6 GHz Standalone (SA) and Non-Standalone (NSA) operation. | CPE | Currently, only n50 is planned for FWA development, and NSA networks should not be involved | CONFIRMED. Phase 1 deployment is strictly 5G NR Standalone (SA) in Band n50. NSA operation is not required. | Official Response issued via Bid Bulletin No. 1
25 | 33 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Native Band n50 (1432 – 1517 MHz, 60 MHz channel bandwidth) plus fallback sub-6 GHz bands (n1, n3, n7, n28, n41, n77, n78). | CPE | Currently, only the n50 band is planned for FWA development. Is it mandatory for other sub-6 GHz frequency bands? | CONFIRMED. Native Band n50 (1432 – 1517 MHz, 60 MHz TDD) is mandatory. Fallback sub-6 GHz bands (n1, n3, n78) are optional for the Philippine market. | Official Response issued via Bid Bulletin No. 1
25 | 34 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | High-gain omnidirectional multi-element internal antenna array (minimum >= 8.0 dBi gain across Band n50); 4x4 MIMO DL, 2x2 MIMO UL. | CPE | The N50 low-frequency system does not need to rely on extremely high antenna gain to compensate for spatial attenuation as high-frequency systems do. Whether 5-6 dBi is sufficient? | CONFIRMED ACCEPTABLE. For Indoor CPE, an integrated antenna array gain of 5.0 – 6.0 dBi across Band n50 is accepted as compliant due to favorable propagation characteristics of 1.5 GHz L-Band compared to 3.5 GHz. For Outdoor CPE, >= 12.0 dBi remains mandatory. | Official Response issued via Bid Bulletin No. 1
25 | 35 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Indoor CPE: Minimum 1x 2.5GE + 2x 1GE RJ-45 LAN ports. Outdoor CPE: 1x 2.5GE PoE input port plus companion indoor Wi-Fi 6 router/gateway and 802.3at PoE injector included in kit. | CPE | The network port is seldom used and is mainly used for network configuration and commissioning. Can only one network port be reserved for the product? | CPE ETHERNET INTERFACES: - Outdoor CPE: 1x 2.5GE PoE input port + companion indoor Wi-Fi 6 router is standard. - Indoor CPE: At least 1x 2.5GE or 1x 1GE LAN port + integrated Wi-Fi 6 is acceptable for consumer FWA tiers; multi-port is preferred for SME tiers. | Official Response issued via Bid Bulletin No. 1
25 | 36 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 7: 5G CUSTOMER PREMISES EQUIPMENT (CPE - LOT 7) | Standard Nano-SIM (4FF) slot with anti-theft locking cover and optional GSMA-compliant eSIM MFF2 footprint. | CPE | Can it only support the eSIM MFF2 solution? | CONFIRMED. Physical Nano-SIM (4FF) with anti-theft locking slot is mandatory for mass-market deployment. eSIM (MFF2) is an acceptable optional enhancement. | Official Response issued via Bid Bulletin No. 1
25 | 37 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 1: RADIO ACCESS NETWORK (RAN) TECHNICAL SPECIFICATIONS | RAN-20 PIM Performance | Wireless and Delivery | PIM is an indicator that is mainly concerned in FDD mode and does not need to be concerned in TDD mode. Is it necessary to change it to an OBUE (Operating Band Unwanted Emissions)indicator? | CONFIRMED. For synchronized TDD systems, Operating Band Unwanted Emissions (OBUE) per 3GPP TS 38.104 is the primary RF compliance benchmark. Passive Intermodulation (PIM <= -150 dBc) applies to external RF components (antennas, jumpers, connectors) to avoid receiver desensitization. | Official Response issued via Bid Bulletin No. 1
25 | 38 | 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx | Phase 1 (First 1,000 Sites) | Site location and tower location. | Wireless and Delivery | We note that the distance from the planned site to the nearest tower ranges from 0.16 km to 1.94 km. Could the specific tower locations be provided for simulation calculations? | CONFIRMED. Candidate site coordinates (Lat/Long) and nominal tower heights are provided in Document 07. | Official Response issued via Bid Bulletin No. 1
25 | 39 | 02_Appendix_A_Technical_Specifications_Compliance_Matrix.xlsx | SECTION 4: CONVERGED DIGITAL OSS/BSS & FIELD FORCE AUTOMATION | Fault & Performance OSS | OSS & BSS Integration | Will a separate monitoring platform be deployed, or can it be integrated with the existing AUTIN platform? | OSS INTEGRATION: Vendor must deliver EMS/NMS for domain element management, equipped with open northbound interfaces (REST APIs, SNMPv3, Kafka) for integration into Converge's enterprise monitoring umbrella (AUTIN). | Official Response issued via Bid Bulletin No. 1
25 | 40 | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | Network Functions | Core network & IT infrastructure and delivery | The NEF is responsible for network capability exposure, and there are currently no commercial use cases. The SEPP is responsible for signaling security protection and topology hiding across PLMNs. Based on the experience of other projects, this function is also not mandatory. Therefore, it is recommended that the NEF and SEPP functions be treated as optional requirements or removed from the current RFP. | CONFIRMED. In Phase 1, NEF (Network Exposure) and SEPP (Security Edge Protection Proxy) are treated as optional roadmap functions and can be licensed in Phase 2 when enterprise API exposure and international roaming are activated. | Official Response issued via Bid Bulletin No. 1
25 | 41 | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | UPF Throughput | Core network & IT infrastructure and delivery | Please Clarify whether the UPF needs to be deployed at the edge or co-deployed with the 5G Core at the central site. If the UPF needs to be deployed at the edge, specify the number of edge UPFs. It is recommended that the UPF form be not limited.Either 2U/4U/8U is ok | UPF DEPLOYMENT ARCHITECTURE: In Phase 1, 5G Core control plane and central UPF are co-deployed at the Tier-3 primary datacenter (Clark/Metro Manila). Edge UPF deployment is optional for future ultra-low-latency enterprise zones. Standard 2U, 4U, or 8U server form factors are acceptable. | Official Response issued via Bid Bulletin No. 1
25 | 42 | 01_RFP_5G_FWA_Master_Tender_Document.pdf | SECTION 3: 5G CORE NETWORK (5GC SA) & DATACENTER INFRASTRUCTURE | Datacenter Compute | Core network & IT infrastructure and delivery | or hardware with the same capabilities such as Kunpeng server（E9000H-4/8） | CONFIRMED ACCEPTABLE. Carrier-grade server hardware with equivalent compute and throughput capabilities (including Huawei Kunpeng ARM architecture running certified carrier-grade Linux / Kubernetes) is fully acceptable for 5GC NFV infrastructure. | Official Response issued via Bid Bulletin No. 1
25 | 43
25 | 44
25 | 45
25 | 46
25 | 47
25 | 48
25 | 49
25 | 50
25 | 51

## Sheet2
分类
Wireless and Delivery
Power system and delivery
Core network & IT infrastructure and delivery
OSS & BSS Integration
Site, civil work, and managed services
CPE
Commercial BoQ & TCO
Other Business Matters
finance and economy