## Site Schedule Summary
Telecommunications Technology Solutions Incorporated (TelTech)
5G Fixed Wireless Access (FWA) — Candidate Site List & Siting Schedule
Document Reference: 07_RFP_5G_FWA_Candidate_Site_List_and_Rollout_Schedule.xlsx ¦ Issue Date: October 14, 2026
1. PHASE 1 (1,000 SITES) ENGINEERING & INFRASTRUCTURE BREAKDOWN
Infrastructure & Engineering Dimension | Phase 1 Scope | Percentage (%) | Contractual Bidding & Pricing Reference
Total Target Macro Base Station Sites | 1000 | 100.0% | Lot 1 (RAN Equipment) & Lot 2 (Power/Passive Facilities)
Co-location on Existing TowerCo Assets (Class T1: <= 0.5 km) | 551 | 55.1% | Lot 5 (Civil Works & Site Acquisition - Co-location Services)
Co-location on Existing TowerCo Assets (Class T2: 0.5 - 1.0 km) | 255 | 25.5% | Lot 5 (Civil Works & Site Acquisition - Co-location Services)
Co-location on Existing TowerCo Assets (Class T3: 1.0 - 2.0 km) | 87 | 8.7% | Lot 5 (Civil Works & Site Acquisition - Co-location Services)
Greenfield Monopole Structures (Class T4: > 2.0 km from existing tower) | 107 | 10.7% | Lot 2 (CIV-01 / CIV-02 30m Monopoles) & Lot 5 (CIV-SVC-01/02 Greenfield Acquisition)
Terrestrial Optical Fiber Drop Backhaul (Classes A, B, C) | 1000 | 100.0% | TelTech Infrastructure / Leased Fiber Drops (Lot 1 SOW Integration)
Satellite LEO High-Throughput Backhaul (Starlink Business 4-Terminal Array) | 0 | 0.0% | Phase 1 100% Fiber-Fed; Satellite Backhaul reallocated to Phase 2 / Expansion Batches
Commercial 220V AC Grid + 4h LiFePO4 Energy Storage (>=19.0 kWh nominal) | 1000 | 100.0% | Lot 2 (PWR-01 / PWR-02 LiFePO4 & Rectifier System)
Total Initial Addressable Subscriber Capacity (Runway to 1,000 subs/BTS) |  | - | Lot 7 (Customer Premises Equipment - 350k Indoor / 15k Outdoor)
NOTE ON EVALUATED COMMERCIAL QUANTITIES VS. DESKTOP GIS SCREENING:
1. Commercial Evaluated Baseline: Across all tender documents (Master Tender §2.1, BoQ Table 6, Appendix D, and Bulletin 01), the contractual evaluated baseline is formally established at 897 Co-Location Sites (89.7%) and 103 Greenfield Sites (10.3%). Bidders must quote exactly these quantities in their commercial submissions. 2. Desktop GIS Screening: Following the executive fiber-priority rollout swap of 17 remote non-fiber sites to Batch 2, preliminary spatial proximity screening against the tower inventory classifies 893 sites within <= 2.0 km (Co-location) and 107 sites beyond 2.0 km (Greenfield) for Phase 1. Within applicable search rings (500m urban / 1,000m rural), 718 sites have an immediate mapped tower candidate. 3. Milestone 1 Siting True-Up: Actual contractor compensation will be trued up at Milestone 1 (TSSR Approval). If an evaluated co-location site converts to Tier 2 B2S or Tier 3 Greenfield (or vice-versa), contract adjustments shall be calculated strictly using the pre-agreed Lot 5 unit rates (Item LOT5-COLO, LOT5-B2S, LOT5-GF30/GF40) via an administrative contract variation order, ensuring cost certainty without altering tender competitiveness.
2. NATIONWIDE DEPLOYMENT PHASING (5,000 SITES ACROSS 5 BATCHES)
Rollout Phase | Scope Description | Target Sites | Target Barangays | 2024 Population Reach | Addressable Households | Target Subscribers
Batch 1 (Phase 1) | Primary Commercial Launch & Urban/Dense Siting | 1000 | 1000
Batch 2 (Phase 2) | Nationwide Regional Expansion (Priority Tranche 2) | 1000 | 1000
Batch 3 (Phase 3) | Provincial & Semi-Urban Expansion | 1000 | 1000
Batch 4 (Phase 4) | Regional Rural & Underserved Infill | 1000 | 1000
Batch 5 (Phase 5) | Nationwide Universal Coverage & Border Reach | 1000 | 1000
Total Network | Full Multi-Year Macro Siting Universe | 5000 | 5000
3. SITE SCHEDULE COLUMN DICTIONARY
Column Header | Engineering Definition & Application
Site ID | Unique site identifier generated for the FWA network rollout (e.g., FWA-SITE-0001).
Priority Rank / Overall Rank | Deployment priority ranking based on demographic density, commercial demand, and infrastructure accessibility.
PSGC Code | Official 10-digit Philippine Standard Geographic Code issued by the Philippine Statistics Authority (PSA).
Region / Province / Municipality / Barangay | Official geographic administrative hierarchy corresponding to 2024 PSA boundary rosters.
Latitude / Longitude | Exact spatial centroid coordinates (WGS84 decimal degrees) of the candidate site / demand center.
Terrain Classification | Urban (U) or Rural (R) demographic classification pursuant to official 2024 PSA criteria.
Civil Infrastructure Category | Primary civil classification: 'Co-location (Existing Tower)' or 'Greenfield Monopole (New Build)'.
Tower Screening Class | Proximity to audited operational towers: Class T1 (<=0.5km), Class T2 (0.5-1.0km), Class T3 (1.0-2.0km), Class T4 (>2.0km Greenfield).
Nearest Tower ID & TowerCo | Asset identifier and operator/owner of the nearest audited cell site structure (Globe FTAP, Smart FTAP, MIDC, Edgepoint, etc.).
Distance to Tower (km) | Geodesic physical distance from candidate centroid to the nearest operational tower structure.
Transmission Medium | Primary backhaul technology: 'Terrestrial Optical Fiber Drop' or 'Satellite LEO Backhaul (Starlink Business)'.
Distance to Node / Line (km) | Indicative physical distance to the nearest optical distribution node or fiber backbone cable.
Power Supply Configuration | Standardized power arrangement: Commercial 220V AC utility grid connection paired with 4h LiFePO4 ESS.

## Siting_Provenance_Traceability
Site ID | Batch | PSGC Code | Region | Province | Municipality | Barangay | Nominal Latitude | Nominal Longitude | Search Ring Radius | Siting Anchor Classification | DepEd School ID | DepEd School Name / Anchor Identity | DepEd Masterfile Row Reference | DepEd Audit Status / Ground-Truth Validation | Siting Governance & TSSR Hunting Rule
FWA-SITE-0001 | 1 | 0501705020 | Region V (Bicol Region) | Camarines Sur | Buhi | Sagrada Familia | 13.416 | 123.5142 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112409 | Sagrada ES | Row 25750 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0002 | 1 | 0401024016 | Region IV-A (CALABARZON) | Batangas | San Luis | Muzon | 13.8594 | 120.9871 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107650 | Muzon Elementary School | Row 16917 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0003 | 1 | 0405803001 | Region IV-A (CALABARZON) | Rizal | Baras | Evangelista | 14.517 | 121.2766 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109426 | Evangelista ES | Row 18639 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0004 | 1 | 0401032019 | Region IV-A (CALABARZON) | Batangas | Taysan | Santo Niño | 13.7571 | 121.21 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107801 | Sto. Nino Elementary School | Row 17063 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0005 | 1 | 0102933035 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Quirino | 16.937 | 120.4448 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300086 | Tagudin NHS | Row 9725 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0006 | 1 | 1030500063 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Puerto | 8.4993 | 124.7484 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127952 | Puerto Elementary School | Row 42288 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0007 | 1 | 0600403019 | Region VI (Western Visayas) | Aklan | Banga | Poblacion | 11.6975 | 122.3674 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114660 | Banga ES | Row 28838 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0008 | 1 | 0500508037 | Region V (Bicol Region) | Albay | City of Ligao | Paulba | 13.1838 | 123.4585 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111826 | Paulba ES | Row 25189 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0009 | 1 | 0701242002 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Booy | 9.6572 | 123.8505 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 118702 | Booy Elementary School | Row 33603 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1004 | 1 | 0300804040 | Region III (Central Luzon) | Bataan | Dinalupihan | Santa Isabel | 14.8599 | 120.4714 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 104600 | Sta. Isabel ES | Row 12952 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0011 | 1 | 0105521010 | Region I (Ilocos Region) | Pangasinan | Labrador | Uyong | 16.05 | 120.1208 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101480 | Uyong Elementary School | Row 8761 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0012 | 1 | 0401015026 | Region IV-A (CALABARZON) | Batangas | Lobo | Poblacion | 13.6479 | 121.209 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107436 | Lobo Central School | Row 16709 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0013 | 1 | 1705210010 | MIMAROPA Region | Oriental Mindoro | Pola | Casiligan | 13.1177 | 121.4251 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110594 | Casiligan ES | Row 20764 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0014 | 1 | 0304909010 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Mag-asawang Sampaloc | 15.5922 | 121.052 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105354 | Mag-Asawang Sampaloc ES | Row 13663 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0015 | 1 | 1731500010 | MIMAROPA Region | Palawan | City of Puerto Princesa | Binduyan | 10.0141 | 119.071 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111509 | Binduyan Elementary School | Row 21659 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0016 | 1 | 0403403003 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Tomas | 14.3113 | 121.0635 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108230 | Sto. Tomas ES | Row 17483 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0017 | 1 | 0300805024 | Region III (Central Luzon) | Bataan | Hermosa | Judge Roman Cruz Sr. | 14.8341 | 120.4884 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 137097 | Mandama Elementary School | Row 15376 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0018 | 1 | 0307114014 | Region III (Central Luzon) | Zambales | Subic | Mangan-Vaca | 14.8886 | 120.2376 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107012 | Mangan -Vaca Elementary School | Row 15218 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0019 | 1 | 0600415013 | Region VI (Western Visayas) | Aklan | New Washington | Poblacion | 11.6482 | 122.434 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114907 | New Washington ES | Row 29058 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0020 | 1 | 0501707006 | Region V (Bicol Region) | Camarines Sur | Cabusao | New Poblacion | 13.7265 | 123.1135 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112458 | Cabusao Central School | Row 25798 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0021 | 1 | 0501601025 | Region V (Bicol Region) | Camarines Norte | Basud | San Felipe | 14.0124 | 122.9305 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112103 | San Felipe Elementary School | Row 25461 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0022 | 1 | 1606807004 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Baybay | 9.4195 | 125.8877 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Baybay Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0023 | 1 | 0401027002 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Bihis | 13.8777 | 120.9665 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107691 | Mohon Elementary School | Row 16958 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0024 | 1 | 0403407003 | Region IV-A (CALABARZON) | Laguna | Cavinti | Bukal | 14.2385 | 121.5444 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108270 | BUKAL ES | Row 17522 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0025 | 1 | 0304901005 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Bucot | 15.5025 | 120.8716 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105174 | Bucot ES | Row 13495 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1014 | 1 | 0307109006 | Region III (Central Luzon) | Zambales | San Antonio | Luna | 14.9491 | 120.0882 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Luna Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0027 | 1 | 0402101006 | Region IV-A (CALABARZON) | Cavite | Alfonso | Barangay V | 14.1362 | 120.8562 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107839 | Alfonso Central School | Row 17101 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0028 | 1 | 1600210005 | Region XIII (Caraga) | Agusan del Norte | Santiago | La Paz | 9.267 | 125.5588 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved La Paz Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0029 | 1 | 0203102020 | Region II (Cagayan Valley) | Isabela | Angadanan | Consular | 16.7878 | 121.7604 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103056 | Consular Elementary School | Row 10948 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0030 | 1 | 0307704009 | Region III (Central Luzon) | Aurora | Dinalungan | Simbahan | 16.129 | 121.895 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104450 | Paulino L. Bautista ES | Row 12820 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0031 | 1 | 0201504045 | Region II (Cagayan Valley) | Cagayan | Amulung | Palayag | 17.811 | 121.6759 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102440 | Palayag ES | Row 10363 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0032 | 1 | 0500517032 | Region V (Bicol Region) | Albay | City of Tabaco | Quinastillojan | 13.3411 | 123.6615 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114597 | Quinastillojan ES | Row 27837 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0033 | 1 | 1705213007 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Poblacion | 13.4356 | 121.019 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110662 | San Teodoro CS | Row 20830 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0034 | 1 | 0506202019 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Norte | 12.8702 | 124.1423 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302184 | Barcelona National Comprehensive High School | Row 28401 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0035 | 1 | 0431200026 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Isabang | 13.9497 | 121.5812 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109740 | Isabang Elementary School | Row 18935 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0036 | 1 | 1102414018 | Region XI (Davao Region) | Davao del Sur | Sulop | Poblacion | 6.5983 | 125.3439 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129146 | Sulop Central Elementary School | Row 44161 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0037 | 1 | 0201518009 | Region II (Cagayan Valley) | Cagayan | Pamplona | Centro | 18.4648 | 121.3397 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102791 | Pamplona CS | Row 10699 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0038 | 1 | 0304904014 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Sur | 15.2632 | 120.8669 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105225 | San Fernando Sur Elem. School | Row 13545 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0039 | 1 | 0201527003 | Region II (Cagayan Valley) | Cagayan | Solana | Bangag | 17.7087 | 121.6973 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 502307 | Bangag Integrated School | Row 12768 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0040 | 1 | 0401023004 | Region IV-A (CALABARZON) | Batangas | San Juan | Bataan | 13.6957 | 121.4333 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107604 | Bataan Elementary School | Row 16872 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0041 | 1 | 0506210006 | Region V (Bicol Region) | Sorsogon | Juban | Buraburan | 12.7757 | 123.9907 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114268 | SANGKAYON ELEMENTARY SCHOOL | Row 27526 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0042 | 1 | 1130700126 | Region XI (Davao Region) | Davao del Sur | City of Davao | Toril | 7.0127 | 125.4995 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129548 | Don Juan Dela Cruz CES | Row 44509 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0043 | 1 | 1430300008 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Bayan Park West | 16.4073 | 120.5973 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 305269 | Baguio City High School - Main (Brgy LEGARDA-BURNHAM-KISAD) | Row 4284 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay LEGARDA-BURNHAM-KISAD anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0044 | 1 | 0105527023 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cabayaoasan | 15.7697 | 120.3885 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101581 | Cabayaoasan ES | Row 8856 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0045 | 1 | 1403209004 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Apatan | 17.5571 | 121.34 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136062 | Tappo Elementary School | Row 3609 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0046 | 1 | 1130700026 | Region XI (Davao Region) | Davao del Sur | City of Davao | Calinan | 7.1861 | 125.4555 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129531 | Calinan Central ES | Row 44493 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0047 | 1 | 0201506035 | Region II (Cagayan Valley) | Cagayan | Baggao | San Jose | 17.8914 | 121.8712 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102527 | Baggao South Central School | Row 10447 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0048 | 1 | 0506215005 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion III | 12.6457 | 124.105 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114415 | Sta. Magdalena CS | Row 27667 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0049 | 1 | 0402104009 | Region IV-A (CALABARZON) | Cavite | Carmona | Mabuhay | 14.3103 | 121.0505 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107896 | Mabuhay Elementary School | Row 17158 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0050 | 1 | 0401013004 | Region IV-A (CALABARZON) | Batangas | Lian | Binubusan | 13.9603 | 120.6382 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107399 | Binubusan Elementary School | Row 16674 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0051 | 1 | 0506213005 | Region V (Bicol Region) | Sorsogon | Pilar | Bayasong | 12.9876 | 123.6834 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114365 | Bayasong Elementary School | Row 27618 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0052 | 1 | 0405607042 | Region IV-A (CALABARZON) | Quezon | Calauag | Lagay | 14.0912 | 122.2153 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108602 | Lagay ES | Row 17844 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1009 | 1 | 0500518028 | Region V (Bicol Region) | Albay | Tiwi | Tigbi | 13.4532 | 123.68 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112081 | Tiwi Central School | Row 25440 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0054 | 1 | 1600210010 | Region XIII (Caraga) | Agusan del Norte | Santiago | Estanislao Morgado | 9.2663 | 125.5587 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Estanislao Morgado Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0055 | 1 | 1402705009 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Nayon | 16.7195 | 121.1718 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135907 | Nayon ES | Row 3460 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0056 | 1 | 1600212001 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | Poblacion I | 9.0535 | 125.5878 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion I Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0057 | 1 | 1705201029 | MIMAROPA Region | Oriental Mindoro | Baco | Poblacion | 13.3591 | 121.0953 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110320 | Benito R. Villar MS | Row 20494 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0058 | 1 | 0803726015 | Region VIII (Eastern Visayas) | Leyte | Kananga | Poblacion | 11.1858 | 124.5612 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 121538 | Kananga Central School | Row 37393 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0059 | 1 | 0203124004 | Region II (Cagayan Valley) | Isabela | Ramon | Bugallon Norte | 16.7877 | 121.532 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103597 | Bugallon Norte Elementary School | Row 11443 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0060 | 1 | 0704619018 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion I | 9.0622 | 123.0312 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120459 | Felipe Tayko MCES | Row 35227 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0061 | 1 | 1401110001 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Alapang | 16.4685 | 120.5985 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 135613 | Don Pulas ES (formerly Alapang Camp Dangwa ES) | Row 3192 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1018 | 1 | 0304917027 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion North | 15.7205 | 120.904 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105553 | Munoz North CS | Row 13848 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0063 | 1 | 1600212006 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | San Antonio | 9.0535 | 125.5878 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Antonio Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0064 | 1 | 0630200024 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 28 | 10.6661 | 122.952 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 28 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0065 | 1 | 0205705004 | Region II (Cagayan Valley) | Quirino | Saguday | Rizal | 16.5446 | 121.5631 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104377 | SAGUDAY CENTRAL SCHOOL | Row 12118 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0066 | 1 | 1004304007 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Poblacion | 8.9186 | 124.7853 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127716 | Binuangan CS | Row 42088 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0067 | 1 | 0504102020 | Region V (Bicol Region) | Masbate | Baleno | Poblacion | 12.4737 | 123.4955 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113420 | Baleno Central School | Row 26730 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0068 | 1 | 1600205001 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Baleguian | 9.3577 | 125.5537 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Baleguian Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0069 | 1 | 0506216001 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Abuyog | 12.9463 | 124.0524 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114552 | Abuyog Elementary School | Row 27797 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0070 | 1 | 1381300011 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbayan | 14.6078 | 121.0827 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136552 | Bagumbayan ES | Row 6682 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0071 | 1 | 0301419009 | Region III (Central Luzon) | Bulacan | San Ildefonso | Bubulong Malaki | 15.0877 | 120.995 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105029 | Bubulong Malaki ES | Row 13351 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0072 | 1 | 1381300096 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | San Antonio | 14.647 | 121.0164 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136503 | Sinag-Tala ES | Row 6633 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0073 | 1 | 0403404006 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Casile | 14.1696 | 121.0193 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108240 | Casile ES | Row 17493 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0074 | 1 | 0301422030 | Region III (Central Luzon) | Bulacan | San Rafael | San Roque | 15.0084 | 120.9324 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105134 | San Roque ES | Row 13456 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0075 | 1 | 0401014058 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Celestino | 13.9174 | 121.2247 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109650 | San Celestino ES | Row 18851 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0076 | 1 | 1430300029 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | DPS Area | 16.4072 | 120.5974 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved DPS Area Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0077 | 1 | 0305412019 | Region III (Central Luzon) | Pampanga | Masantol | San Nicolas | 14.8906 | 120.7072 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106152 | Masantol ES | Row 14421 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0078 | 1 | 0304919013 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Atate | 15.5607 | 121.1003 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105574 | Atate ES | Row 13867 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0079 | 1 | 1430300013 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cabinet Hill-Teacher's Camp | 16.4074 | 120.5971 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Cabinet Hill-Teacher's Camp Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0080 | 1 | 0405804027 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pantok | 14.4945 | 121.1801 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109312 | Doña Susana Madrigal Elementary School | Row 18528 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0081 | 1 | 0402102004 | Region IV-A (CALABARZON) | Cavite | Amadeo | Halang | 14.1992 | 120.9319 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 301195 | Halang Banaybanay Integrated School (Brgy BANAYBANAY) | Row 19301 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BANAYBANAY anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0082 | 1 | 0405605019 | Region IV-A (CALABARZON) | Quezon | Buenavista | Lilukin | 13.7435 | 122.4591 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301296 | Buenavista NHS | Row 19400 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0083 | 1 | 0405603004 | Region IV-A (CALABARZON) | Quezon | Atimonan | Barangay Zone 1 | 14.0003 | 121.9245 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108511 | Atimonan CS - Annex | Row 17758 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0084 | 1 | 0203123014 | Region II (Cagayan Valley) | Isabela | Quirino | Santa Lucia | 17.1349 | 121.7371 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103580 | Quirino Central School | Row 11429 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0085 | 1 | 1102407015 | Region XI (Davao Region) | Davao del Sur | Magsaysay | Poblacion | 6.7532 | 125.151 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 128936 | Magsaysay Central Elementary School | Row 43962 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1021 | 1 | 0803739025 | Region VIII (Eastern Visayas) | Leyte | Palo | Salvacion | 11.1543 | 124.9981 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121744 | Salvacion Elementary School | Row 37598 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0087 | 1 | 0506209002 | Region V (Bicol Region) | Sorsogon | Irosin | Bacolod | 12.7014 | 124.0359 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114248 | Bacolod Elementary School | Row 27507 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0088 | 1 | 0501734041 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Villazar | 13.8554 | 122.9516 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113074 | South Villazar ES | Row 26398 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0089 | 1 | 0803733012 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | Talisay | 11.1446 | 124.4718 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121666 | Matag-ob Central School | Row 37520 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0090 | 1 | 0702215007 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Norte | 10.5766 | 124.0181 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119189 | Dawis Norte ES | Row 34062 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0091 | 1 | 0402123024 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Gabriel | 14.2826 | 121.0011 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 107937 | Bulihan Elementary School | Row 17199 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0092 | 1 | 0305403025 | Region III (Central Luzon) | Pampanga | Arayat | San Jose Mesulo | 15.1425 | 120.7707 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105906 | Mesulo ES | Row 14178 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0093 | 1 | 0500512024 | Region V (Bicol Region) | Albay | Oas | Ilaor Norte | 13.2628 | 123.4965 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111919 | Oas North Central School | Row 25280 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0094 | 1 | 1705318015 | MIMAROPA Region | Palawan | Roxas | Barangay 1 | 10.3169 | 119.345 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 111136 | Andres Soriano Memorial Elementary School | Row 21294 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0095 | 1 | 0304905030 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Minuli | 16.0728 | 120.9429 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105248 | Minuli ES | Row 13565 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0096 | 1 | 0203103022 | Region II (Cagayan Valley) | Isabela | Aurora | San Andres | 16.9635 | 121.5885 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 103091 | San Andres-Ramon Elementary School (Brgy SAN RAMON) | Row 10977 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAN RAMON anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0097 | 1 | 1380300021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Post Proper Northside | 14.5636 | 121.0336 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136690 | Makati ES (Brgy POBLACION) | Row 6805 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0098 | 1 | 0702241018 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion South | 10.1621 | 123.707 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119630 | South Poblacion Elementary School | Row 34443 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0099 | 1 | 0102906006 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Bagani Gabor | 17.1881 | 120.4461 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bagani Gabor Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0100 | 1 | 0306906036 | Region III (Central Luzon) | Tarlac | Gerona | San Antonio | 15.5983 | 120.6051 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106481 | San Antonio Elementary School | Row 14737 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0101 | 1 | 0306916023 | Region III (Central Luzon) | Tarlac | City of Tarlac | Burot | 15.4141 | 120.6006 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500556 | Burot Integrated School | Row 16322 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0102 | 1 | 0307113017 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion North | 15.7688 | 119.9092 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106979 | Don Marcelo C. Marty Elementary School | Row 15190 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0103 | 1 | 0307110005 | Region III (Central Luzon) | Zambales | San Felipe | Feria | 15.0603 | 120.0712 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106936 | San Felipe Elementary School (East) | Row 15150 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0104 | 1 | 0201527019 | Region II (Cagayan Valley) | Cagayan | Solana | Nangalisan | 17.648 | 121.6734 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102889 | Nangalisan ES | Row 10791 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0105 | 1 | 0403406013 | Region IV-A (CALABARZON) | Laguna | Calauan | Kanluran | 14.147 | 121.3136 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108255 | Calauan CES | Row 17507 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1022 | 1 | 1102315009 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Gredu | 7.2961 | 125.6784 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129783 | Gredu ES | Row 44713 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0107 | 1 | 0405608008 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Norte | 13.9308 | 121.4386 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108619 | MALABANBAN NORTE ES | Row 17861 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0108 | 1 | 0702234003 | Region VII (Central Visayas) | Cebu | City of Naga | Balirong | 10.2566 | 123.7109 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119503 | Balirong Elementary School | Row 34326 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0109 | 1 | 1381500015 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Upper Bicutan | 14.4866 | 121.0475 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136884 | Daanghari Elementary School | Row 6987 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0110 | 1 | 1004312011 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Poblacion | 8.9826 | 124.7938 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127726 | Kinoguitan CS | Row 42096 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0111 | 1 | 0501604008 | Region V (Bicol Region) | Camarines Norte | San Lorenzo Ruiz | Matacong | 14.0361 | 122.8655 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 112263 | Imelda Elementary School | Row 25612 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0112 | 1 | 0201523008 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Palawig | 18.4751 | 122.1519 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102905 | Palawig ES | Row 10805 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0113 | 1 | 0431200010 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 7 | 13.9326 | 121.6106 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109708 | Lucena East II Elementary School | Row 18903 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0114 | 1 | 1381500017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Wawa | 14.5201 | 121.0736 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136873 | Eusebio C. Santos Elementary School | Row 6979 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0115 | 1 | 0405644001 | Region IV-A (CALABARZON) | Quezon | San Narciso | Abuyon | 13.6223 | 122.519 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109137 | Abuyon ES | Row 18358 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0116 | 1 | 0304902024 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Sinipit | 15.6246 | 121.1476 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300790 | Bongabon National High School | Row 15712 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0117 | 1 | 1004325010 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Poblacion | 8.9988 | 124.8815 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127874 | Babanlagan ES | Row 42221 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0118 | 1 | 1102412005 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Inawayan | 6.9552 | 125.472 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129081 | Inawayan Elementary School | Row 44098 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0119 | 1 | 0501601001 | Region V (Bicol Region) | Camarines Norte | Basud | Angas | 14.0459 | 123.0178 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112082 | Angas Elementary School | Row 25441 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0120 | 1 | 0403416035 | Region IV-A (CALABARZON) | Laguna | Majayjay | San Miguel | 14.1424 | 121.4711 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108348 | Majayjay Elementary School | Row 17600 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0121 | 1 | 0702231015 | Region VII (Central Visayas) | Cebu | Medellin | Tindog | 11.1249 | 124.0119 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 501361 | Tindog Integrated School | Row 36593 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0122 | 1 | 0403424047 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Francisco | 14.0595 | 121.3284 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109793 | Don Enrique Bautista Elementary School | Row 18983 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0123 | 1 | 1381300062 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Marilag | 14.6255 | 121.0696 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136565 | Teodora Alonzo Elementary School | Row 6693 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0124 | 1 | 0500504017 | Region V (Bicol Region) | Albay | Guinobatan | Iraya | 13.1894 | 123.603 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 111710 | Guinobatan East Central School | Row 25079 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0125 | 1 | 0603045011 | Region VI (Western Visayas) | Iloilo | Tigbauan | Barangay 4 | 10.6794 | 122.3823 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302578 | Tigbauan NHS | Row 32302 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0126 | 1 | 1001317029 | Region X (Northern Mindanao) | Bukidnon | Quezon | Puntian | 7.6083 | 125.112 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 126740 | Puntian ES | Row 41283 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0127 | 1 | 0405638008 | Region IV-A (CALABARZON) | Quezon | Real | Maragondon | 14.5336 | 121.5746 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109071 | Maragondon ES | Row 18293 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0128 | 1 | 0501610019 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Tabugon | 14.0727 | 122.3721 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 173012 | Tabugon Elementary School | Row 27911 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0129 | 1 | 0201501010 | Region II (Cagayan Valley) | Cagayan | Abulug | Libertad | 18.3416 | 121.4173 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102341 | Libertad Elementary School | Row 10268 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0130 | 1 | 0405622007 | Region IV-A (CALABARZON) | Quezon | Lopez | Magsaysay | 13.8871 | 122.261 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108805 | Don Emilio Salumbides ES | Row 18037 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0131 | 1 | 0405618034 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Manlayo | 13.9029 | 122.4511 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108733 | Don Guillermo Eleazar ES | Row 17969 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0132 | 1 | 1004323008 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Poblacion | 8.9556 | 124.7883 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127738 | Sugbongcogon CS | Row 42108 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0133 | 1 | 0201510006 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Bantay | 18.2484 | 121.6962 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 300460 | Felipe Tuzon Agr'l. School (Brgy DAMMANG SUR (FELIPE TUZON*)) | Row 12316 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay DAMMANG SUR (FELIPE TUZON*) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0134 | 1 | 0203114079 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Centro - San Antonio | 17.0918 | 121.9637 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103406 | San Antonio ES | Row 11270 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0135 | 1 | 0501715028 | Region V (Bicol Region) | Camarines Sur | Goa | San Juan Bautista | 13.6961 | 123.4873 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112621 | Goa Central School | Row 25954 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1024 | 1 | 0301411001 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Norte | 14.7743 | 120.944 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104900 | Abangan Norte ES | Row 13232 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0137 | 1 | 0403407017 | Region IV-A (CALABARZON) | Laguna | Cavinti | Silangan Talaongan | 14.2793 | 121.5369 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108281 | Talaongan East ES | Row 17533 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0138 | 1 | 1030500068 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Taglimao | 8.3939 | 124.5222 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127984 | Taglimao Elementary School | Row 42316 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0139 | 1 | 0500517048 | Region V (Bicol Region) | Albay | City of Tabaco | Tagas | 13.3486 | 123.7125 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136936 | Guinobat Elementary School (Brgy GUINOBAT) | Row 27867 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay GUINOBAT anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0140 | 1 | 0506215003 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion I | 12.6445 | 124.1051 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302245 | Sta. Magdalena National High School | Row 28462 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0141 | 1 | 0304902028 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Tulay na Bato | 15.6239 | 121.1453 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105198 | Jesus C. Ilagan (Bongabon East ES) | Row 13518 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0142 | 1 | 0401010006 | Region IV-A (CALABARZON) | Batangas | Ibaan | Coliat | 13.8149 | 121.1279 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107353 | Coliat Elementary School | Row 16635 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0143 | 1 | 0702213015 | Region VII (Central Visayas) | Cebu | Borbon | Poblacion | 10.835 | 124.0258 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119141 | Borbon Central ES | Row 34016 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0144 | 1 | 1403215014 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Poblacion | 17.265 | 121.149 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136150 | Tinglayan Central School | Row 3690 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0145 | 1 | 0731300004 | Region VII (Central Visayas) | Cebu | City of Mandaue | Basak | 10.354 | 123.9499 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119998 | Basak ES | Row 34769 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0146 | 1 | 0203101005 | Region II (Cagayan Valley) | Isabela | Alicia | Bagnos | 16.8076 | 121.6285 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103009 | Bagnos Elementary School | Row 10905 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0147 | 1 | 1380400008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Hulong Duhat | 14.6768 | 120.9412 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136830 | Malabon ES | Row 6939 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0148 | 1 | 0730600065 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag II | 10.3011 | 123.8955 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 303128 | Abellana NHS (Day & NIght) (Brgy SAMBAG I (POB.)) | Row 35966 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAMBAG I (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0149 | 1 | 0401017020 | Region IV-A (CALABARZON) | Batangas | Malvar | Santiago | 14.0193 | 121.1631 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107473 | Payapa Elementary School | Row 16745 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0150 | 1 | 0205706014 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Sangbay | 16.2519 | 121.6655 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500100 | Sangbay IS | Row 12649 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0151 | 1 | 1731500001 | MIMAROPA Region | Palawan | City of Puerto Princesa | Babuyan | 9.981 | 118.9323 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111504 | Anilawan Elementary School | Row 21654 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0152 | 1 | 0402107013 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Poblacion III | 14.1818 | 120.7994 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 301191 | Gen. Emilio Aguinaldo-Bailen Integrated School (Brgy CASTAÃ‘OS CERCA) | Row 19297 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay CASTAÃ‘OS CERCA anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0153 | 1 | 0702202006 | Region VII (Central Visayas) | Cebu | Alcoy | Poblacion | 9.7097 | 123.5073 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 118872 | Alcoy Central ES | Row 33766 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0154 | 1 | 0401018004 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | District IV | 13.9583 | 121.1158 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107487 | Paaralang Sentral ng Mataasnakahoy | Row 16759 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0155 | 1 | 0201514020 | Region II (Cagayan Valley) | Cagayan | Gonzaga | San Jose | 18.3579 | 122.103 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102704 | San Jose ES | Row 10617 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0156 | 1 | 0305416036 | Region III (Central Luzon) | Pampanga | City of San Fernando | Sindalan | 15.0774 | 120.6418 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107190 | Sindalan Elementary School | Row 15353 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0157 | 1 | 0403402002 | Region IV-A (CALABARZON) | Laguna | Bay | Calo | 14.182 | 121.2796 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108202 | Calo ES | Row 17455 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0158 | 1 | 0405802007 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Isidro | 14.6182 | 121.1857 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109320 | Bagong Nayon II ES | Row 18536 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0159 | 1 | 1401108013 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Paykek | 16.5747 | 120.6049 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135577 | Lomon ES | Row 3162 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0160 | 1 | 0403404017 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Uno | 14.2767 | 121.1268 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 108239 | Cabuyao Cs (Brgy BARANGAY DOS (POB.)) | Row 17492 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BARANGAY DOS (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0161 | 1 | 0405808010 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Jose | 14.7456 | 121.1294 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 109461 | Amityville Elementary School | Row 18670 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0162 | 1 | 0730600004 | Region VII (Central Visayas) | Cebu | City of Cebu | Babag | 10.3803 | 123.856 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500223 | Babag Elementary | Row 36494 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0163 | 1 | 0504113016 | Region V (Bicol Region) | Masbate | Mobo | Nasunduan | 12.338 | 123.6591 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 174502 | Jose B. Gamora ES | Row 27974 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0164 | 1 | 0401022013 | Region IV-A (CALABARZON) | Batangas | San Jose | Don Luis | 13.8836 | 121.0982 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 301155 | Taysan San Jose Integrated National High School (Brgy TAYSAN) | Row 19261 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay TAYSAN anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1027 | 1 | 0402103008 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay I | 14.4487 | 120.9441 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107870 | Habay Elementary School | Row 17132 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1028 | 1 | 0301412015 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Malhacan | 14.7399 | 120.9637 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 345349 | City of Meycauayan Vocational Senior High School | Row 16254 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0167 | 1 | 0402118016 | Region IV-A (CALABARZON) | Cavite | Silang | Inchican | 14.2504 | 121.0533 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108122 | Inchican Elementary School | Row 17378 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0168 | 1 | 0402121009 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I A | 14.2847 | 120.7193 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301221 | Ternate Integrated National High School | Row 19327 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0169 | 1 | 1430300003 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Atok Trail | 16.4075 | 120.5975 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Atok Trail Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0170 | 1 | 0402109090 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-B | 14.4265 | 120.9335 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 107973 | Cayetano Topacio Elementary School (Brgy POBLACION IV-C) | Row 17235 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION IV-C anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0171 | 1 | 0403420003 | Region IV-A (CALABARZON) | Laguna | Pakil | Burgos | 14.3803 | 121.4778 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108401 | Pakil ES | Row 17652 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0172 | 1 | 0730600030 | Region VII (Central Visayas) | Cebu | City of Cebu | Guba | 10.4251 | 123.8901 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119900 | Guba Elementary School | Row 34678 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0173 | 1 | 0304911011 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bulakid | 15.6577 | 120.7602 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bulakid Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0174 | 1 | 0501723030 | Region V (Bicol Region) | Camarines Sur | Nabua | San Miguel | 13.4043 | 123.3749 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 302001 | Nabua National High School | Row 28227 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0175 | 1 | 0600416016 | Region VI (Western Visayas) | Aklan | Numancia | Poblacion | 11.7047 | 122.3274 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500035 | Numancia Integrated School | Row 32650 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0176 | 1 | 0702243013 | Region VII (Central Visayas) | Cebu | San Remigio | Kinawahan | 10.9472 | 123.9205 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500920 | Kinawahan Integrated School | Row 36563 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0177 | 1 | 0405601006 | Region IV-A (CALABARZON) | Quezon | Agdangan | Kanlurang Maligaya | 13.8603 | 121.9375 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 301293 | Binagbag Integrated High School (Brgy BINAGBAG) | Row 19398 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BINAGBAG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0178 | 1 | 0403415002 | Region IV-A (CALABARZON) | Laguna | Magdalena | Malaking Ambling | 14.1973 | 121.4298 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 307937 | Magdalena NHS (Buenavista Annex) | Row 19761 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0179 | 1 | 0403421008 | Region IV-A (CALABARZON) | Laguna | Pangil | Sulib | 14.4049 | 121.4638 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108404 | Sulib ES | Row 17655 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0180 | 1 | 0501724008 | Region V (Bicol Region) | Camarines Sur | City of Naga | Carolina | 13.6641 | 123.2877 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114498 | Carolina Elementary School | Row 27745 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0181 | 1 | 0405811011 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid II | 14.6871 | 121.1147 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109489 | Justice Vicente Santiago Elementary School | Row 18697 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0182 | 1 | 0702250016 | Region VII (Central Visayas) | Cebu | City of Talisay | Tabunoc | 10.2634 | 123.8406 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119803 | Tabunoc Central School | Row 34592 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0183 | 1 | 0203130002 | Region II (Cagayan Valley) | Isabela | San Manuel | Babanuang | 17.0502 | 121.6282 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103710 | Babanuang Elementary School | Row 11545 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0184 | 1 | 0306916015 | Region III (Central Luzon) | Tarlac | City of Tarlac | Baras-baras | 15.5181 | 120.5652 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106714 | Baras-Baras ES | Row 14952 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0185 | 1 | 0102916017 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Poblacion Norte | 17.1512 | 120.5377 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 300073 | Salcedo NHS | Row 9714 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0186 | 1 | 0405630014 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Ilayang Polo | 13.9304 | 121.7759 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108975 | Polo North ES | Row 18199 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0187 | 1 | 0704624006 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Macapso | 10.38 | 123.3322 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 120632 | Macapso Elementary School | Row 35396 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0188 | 1 | 0105538026 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tebag West | 15.9821 | 120.4599 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101653 | Tebag Elementary School | Row 8928 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0189 | 1 | 0601912026 | Region VI (Western Visayas) | Capiz | Pontevedra | Tacas | 11.4767 | 122.8347 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Tacas Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0190 | 1 | 0402109095 | Region IV-A (CALABARZON) | Cavite | City of Imus | Tanzang Luma III | 14.4152 | 120.9453 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 107979 | Tanzang Luma ES (Brgy TANZANG LUMA V) | Row 17240 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay TANZANG LUMA V anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0191 | 1 | 1004326011 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Looc | 8.5943 | 124.7735 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127905 | Looc ES | Row 42248 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0192 | 1 | 0201521012 | Region II (Cagayan Valley) | Cagayan | Rizal | Illuru Norte | 17.8426 | 121.3894 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102838 | Illuru ES | Row 10742 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0193 | 1 | 0405615013 | Region IV-A (CALABARZON) | Quezon | Dolores | San Mateo | 13.9902 | 121.3873 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108673 | Rosendo Algenio ES | Row 17914 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0194 | 1 | 0203114082 | Region II (Cagayan Valley) | Isabela | City of Ilagan | San Isidro | 17.1668 | 121.9157 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103382 | Tangcul-San Isidro ES | Row 11249 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0195 | 1 | 0806407066 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Combado | 10.1344 | 124.8288 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 303467 | Maasin Vocational High School | Row 40335 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0196 | 1 | 0307706014 | Region III (Central Luzon) | Aurora | Dipaculao | Lipit | 15.8337 | 121.5344 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 502271 | Lipit Integrated School | Row 16468 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0197 | 1 | 0402118023 | Region IV-A (CALABARZON) | Cavite | Silang | Lumil | 14.1828 | 121.0116 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108126 | Lumil Elementary School | Row 17382 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0198 | 1 | 0500518020 | Region V (Bicol Region) | Albay | Tiwi | Misibis | 13.509 | 123.6092 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112074 | Misibis Elementary School | Row 25433 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0199 | 1 | 1400118018 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Suyo | 17.5566 | 120.5643 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 135146 | Suyo Pilot ES | Row 2783 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0200 | 1 | 1381300089 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Ramon Magsaysay | 14.6616 | 121.0218 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136504 | Bago Bantay ES | Row 6634 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0201 | 1 | 0604528038 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12 | 10.7394 | 122.9686 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Zone 12 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0202 | 1 | 0102811016 | Region I (Ilocos Region) | Ilocos Norte | Banna | Marcos | 17.9818 | 120.6554 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 100059 | Banna Central Elementary School | Row 7436 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0203 | 1 | 0201508005 | Region II (Cagayan Valley) | Cagayan | Buguey | Centro | 18.2883 | 121.8347 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102556 | Buguey North CS | Row 10475 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0204 | 1 | 0504112019 | Region V (Bicol Region) | Masbate | Milagros | Poblacion East | 12.2177 | 123.5102 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113700 | Milagros East CS | Row 26991 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0205 | 1 | 0402106058 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran II | 14.3494 | 120.9406 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107924 | Salitran Elementary | Row 17186 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0206 | 1 | 1381300115 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Socorro | 14.6214 | 121.0583 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136566 | 15th Avenue Elementary School | Row 6694 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0207 | 1 | 1401109005 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Poblacion | 16.697 | 120.6564 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135597 | Kibungan CS | Row 3179 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0208 | 1 | 0601905013 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Norte | 11.5223 | 122.6948 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Norte Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0209 | 1 | 1102502012 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Poblacion | 6.962 | 126.0125 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129177 | Banaybanay Central Elementary School | Row 44189 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0210 | 1 | 0201522003 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Centro I | 18.559 | 121.2347 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102861 | Sanchez Mira Central Elementary School | Row 10764 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0211 | 1 | 0604526016 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Rizal | 10.8039 | 122.9779 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Rizal Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0212 | 1 | 1403213040 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | New Tanglag | 17.4627 | 121.4264 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136177 | New Tanglag Elementary School | Row 3714 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0213 | 1 | 0201516021 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Logac | 18.1542 | 121.6091 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102747 | Logac ES | Row 10659 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0214 | 1 | 0405649025 | Region IV-A (CALABARZON) | Quezon | Unisan | F. De Jesus | 13.839 | 121.9777 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109306 | Unisan CES | Row 18522 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0215 | 1 | 0403423010 | Region IV-A (CALABARZON) | Laguna | Rizal | Talaga | 14.1112 | 121.3913 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108364 | Rizal ES | Row 17616 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0216 | 1 | 0401005053 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pinamucan Ibaba | 13.6875 | 121.0623 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109622 | Pinamukan Ibaba ES | Row 18825 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1029 | 1 | 0402103029 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban II | 14.4609 | 120.9643 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107877 | Aniban Central School | Row 17139 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0218 | 1 | 1408105008 | Cordillera Administrative Region (CAR) | Apayao | Luna | Quirino | 18.3367 | 121.3865 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135339 | Quirino Elementary School | Row 2958 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0219 | 1 | 0603009016 | Region VI (Western Visayas) | Iloilo | Batad | Malico | 11.4193 | 123.1092 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Malico Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0220 | 1 | 1404402012 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Mabaay | 16.917 | 120.8873 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136215 | Mabaay Elementary School | Row 3751 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0221 | 1 | 1401113004 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Camp 4 | 16.3099 | 120.6163 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 135689 | Camp 4 ES | Row 3260 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0222 | 1 | 0304929017 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Malasin | 15.591 | 120.8782 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105786 | Sto. Domingo CS | Row 14062 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0223 | 1 | 0401014010 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Banaybanay | 13.9357 | 121.1185 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109697 | Rafael M. Lojo MS | Row 18893 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0224 | 1 | 1004308003 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Anakan | 8.8416 | 125.1564 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 128007 | Anakan Central School | Row 42339 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0225 | 1 | 0402121005 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion III | 14.2849 | 120.7186 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion III Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0226 | 1 | 0501606005 | Region V (Bicol Region) | Camarines Norte | Labo | Bagong Silang I | 14.1769 | 122.6252 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112208 | Felix Asis Elementary School | Row 25562 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0227 | 1 | 0330100027 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Cristo | 15.1425 | 120.5986 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 107024 | Belen Homesite ES (Brgy SANTO CRISTO) | Row 15228 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SANTO CRISTO anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0228 | 1 | 0205014009 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Norte | 16.5828 | 121.1891 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104213 | Bintawan North Elementary School | Row 11996 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0229 | 1 | 0205701015 | Region II (Cagayan Valley) | Quirino | Aglipay | Victoria | 16.4379 | 121.6367 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104247 | Victoria North ES | Row 12024 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0230 | 1 | 0306903011 | Region III (Central Luzon) | Tarlac | Camiling | Bobon Caarosipan | 15.6875 | 120.4205 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bobon Caarosipan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0231 | 1 | 0401030006 | Region IV-A (CALABARZON) | Batangas | Talisay | Buco | 14.0839 | 120.9969 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 301071 | Balas Buco Sta. Maria National High School (Brgy BALAS) | Row 19177 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BALAS anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0232 | 1 | 0500516017 | Region V (Bicol Region) | Albay | Santo Domingo | Nagsiya Pob. | 13.2383 | 123.776 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 112062 | Sto. Domingo Central School | Row 25421 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0233 | 1 | 0401034015 | Region IV-A (CALABARZON) | Batangas | Tuy | Rizal | 14.0217 | 120.7301 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107826 | Gregorio Paradero Elementary School | Row 17088 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0234 | 1 | 1130700198 | Region XI (Davao Region) | Davao del Sur | City of Davao | Vicente Hizon Sr. | 7.165 | 125.4713 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 129541 | Riverside ES (Brgy RIVERSIDE) | Row 44502 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay RIVERSIDE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0235 | 1 | 0306903044 | Region III (Central Luzon) | Tarlac | Camiling | Poblacion B | 15.6889 | 120.4133 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106330 | Camiling North ES | Row 14593 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0236 | 1 | 0102821012 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Leandro | 18.1546 | 120.6446 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100271 | Sarrat Central School | Row 7643 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0237 | 1 | 0402121001 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I | 14.285 | 120.7185 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108172 | Parang Elementary School | Row 17426 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0238 | 1 | 0500507027 | Region V (Bicol Region) | Albay | Libon | Matara | 13.3008 | 123.438 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111768 | Matara Elementary School | Row 25136 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0239 | 1 | 0501721002 | Region V (Bicol Region) | Camarines Sur | Milaor | Amparado | 13.5965 | 123.1783 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112785 | Milaor CS | Row 26114 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0240 | 1 | 0701205011 | Region VII (Central Visayas) | Bohol | Baclayon | Poblacion | 9.6223 | 123.9117 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 117983 | Baclayon Central ES | Row 32907 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0241 | 1 | 0402113012 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pantihan II | 14.2431 | 120.7943 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108044 | Pantihan II Elementary School | Row 17302 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0242 | 1 | 0704603017 | Region VII (Central Visayas) | Negros Oriental | Bacong | South Poblacion | 9.2471 | 123.2958 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved South Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0243 | 1 | 0307102018 | Region III (Central Luzon) | Zambales | Cabangan | San Antonio | 15.1609 | 120.0548 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106826 | Cabangan Elementary School | Row 15050 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0244 | 1 | 0405601012 | Region IV-A (CALABARZON) | Quezon | Agdangan | Poblacion I | 13.8737 | 121.9146 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108944 | Agdangan Central Elementary School | Row 18170 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0245 | 1 | 1380500013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Highway Hills | 14.5824 | 121.0494 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500332 | Highway Hills Integrated School | Row 7355 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0246 | 1 | 0506216035 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Talisay | 12.9683 | 124.0041 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114581 | Sorsogon Pilot Elementary School | Row 27821 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0247 | 1 | 0402114002 | Region IV-A (CALABARZON) | Cavite | Mendez | Asis I | 14.137 | 120.9007 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108053 | Asis Elementary School | Row 17311 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0248 | 1 | 0403410016 | Region IV-A (CALABARZON) | Laguna | Liliw | Ibabang Taykin | 14.1345 | 121.4362 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108301 | Taykin ES | Row 17553 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0249 | 1 | 1001304022 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Sur | 7.6777 | 124.9943 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126344 | Don Carlos Central Elementary School | Row 40934 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0250 | 1 | 0102811014 | Region I (Ilocos Region) | Ilocos Norte | Banna | Lorenzo | 17.9803 | 120.6584 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 300004 | Banna National High School | Row 9645 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0251 | 1 | 0603047004 | Region VI (Western Visayas) | Iloilo | Zarraga | Dawis Centro | 10.828 | 122.6085 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Dawis Centro Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0252 | 1 | 1001321010 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Guinoyuran | 7.8949 | 125.0054 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126840 | Guinuyoran Central ES | Row 41369 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0253 | 1 | 0702212005 | Region VII (Central Visayas) | Cebu | Boljoon | Poblacion | 9.6253 | 123.4801 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119128 | Boljoon Central ES | Row 34004 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0254 | 1 | 0500508032 | Region V (Bicol Region) | Albay | City of Ligao | Nasisi | 13.2591 | 123.5846 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 321701 | Ligao City National Technical Vocational High School | Row 28707 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0255 | 1 | 1380400011 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Maysilo | 14.6827 | 120.9617 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136855 | Maysilo ES | Row 6961 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0256 | 1 | 0402105006 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 13 | 14.4732 | 120.8867 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 109636 | Estansuela ES | Row 18838 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0257 | 1 | 1705319005 | MIMAROPA Region | Palawan | San Vicente | New Agutaya | 10.5394 | 119.2792 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111193 | New Agutaya Elementary School | Row 21350 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0258 | 1 | 0403407006 | Region IV-A (CALABARZON) | Laguna | Cavinti | Duhat | 14.2473 | 121.5011 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108275 | Cavinti Elementary | Row 17527 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0259 | 1 | 0403426021 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Norte | 14.2842 | 121.4181 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Pablo Norte Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0260 | 1 | 0403402004 | Region IV-A (CALABARZON) | Laguna | Bay | Maitim | 14.1793 | 121.2755 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108203 | Maitim ES | Row 17456 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0261 | 1 | 1705212013 | MIMAROPA Region | Oriental Mindoro | Roxas | San Jose | 12.6055 | 121.5526 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110629 | Catalino Dizon Memorial School | Row 20798 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1038 | 1 | 1381300007 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbuhay | 14.6253 | 121.0642 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136562 | Kalantiyaw ES | Row 6690 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0263 | 1 | 0331400006 | Region III (Central Luzon) | Zambales | City of Olongapo | East Tapinac | 14.8336 | 120.2828 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107141 | Tapinac ES | Row 15325 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0264 | 1 | 0803748050 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Santo Niño Pob. | 11.1037 | 125.0208 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 121930 | Sto. Nino Elementary School | Row 37783 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0265 | 1 | 0307702019 | Region III (Central Luzon) | Aurora | Casiguran | Bianuan | 16.2056 | 122.0424 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104420 | Bianoan ES | Row 12791 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0266 | 1 | 0301404013 | Region III (Central Luzon) | Bulacan | Bocaue | Lolomboy | 14.7794 | 120.9337 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104768 | Lolomboy ES | Row 13108 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0267 | 1 | 0603005018 | Region VI (Western Visayas) | Iloilo | Balasan | Poblacion Sur | 11.4721 | 123.088 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Sur Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0268 | 1 | 1408102003 | Cordillera Administrative Region (CAR) | Apayao | Conner | Caglayan | 17.7953 | 121.3232 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 135257 | Caglayan ES | Row 2884 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0269 | 1 | 0102812062 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 1, San Lorenzo | 18.2049 | 120.5843 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102203 | Sta. Maria Elementary School | Row 9438 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0270 | 1 | 0501734040 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Centro | 13.7639 | 122.9755 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 113091 | Sipocot South CS | Row 26415 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0271 | 1 | 1400101023 | Cordillera Administrative Region (CAR) | Abra | Bangued | Sao-atan | 17.5972 | 120.6176 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 134969 | Bangued North ES (Brgy ZONE 4 POB. (TOWN PROPER)) | Row 2616 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay ZONE 4 POB. (TOWN PROPER) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0272 | 1 | 0301407020 | Region III (Central Luzon) | Bulacan | Calumpit | Pio Cruzcosa | 14.8976 | 120.7645 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 158533 | Northville 9 Elementary School (Brgy IBA ESTE) | Row 15440 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay IBA ESTE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0273 | 1 | 0105543015 | Region I (Ilocos Region) | Pangasinan | Tayug | Barangay B | 16.0255 | 120.748 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 300363 | Tayug NHS | Row 9994 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0274 | 1 | 0501608023 | Region V (Bicol Region) | Camarines Norte | Paracale | Poblacion Sur | 14.2801 | 122.7849 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112254 | Paracale Central School | Row 25604 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0275 | 1 | 0103301004 | Region I (Ilocos Region) | La Union | Agoo | Consolacion | 16.3251 | 120.3695 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 100801 | Agoo East CES | Row 8140 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0276 | 1 | 0504101001 | Region V (Bicol Region) | Masbate | Aroroy | Ambolong | 12.5106 | 123.3969 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113374 | Aroroy East CS | Row 26688 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0277 | 1 | 0401024028 | Region IV-A (CALABARZON) | Batangas | San Luis | Poblacion | 13.8547 | 120.9171 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107653 | San Luis Central School | Row 16920 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0278 | 1 | 0403415006 | Region IV-A (CALABARZON) | Laguna | Magdalena | Bucal | 14.2023 | 121.4288 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 108343 | Ricardo A. Pronove ES (Brgy POBLACION) | Row 17595 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0279 | 1 | 0702241013 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion North | 10.1642 | 123.7078 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119629 | San Fernando North Central ES | Row 34442 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0280 | 1 | 0604524001 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Bagonbon | 10.5831 | 123.3983 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bagonbon Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0281 | 1 | 0105526014 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guilig | 16.0666 | 120.4007 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300326 | Mangaldan National High School | Row 9957 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0282 | 1 | 0604517012 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Robles | 10.3187 | 123.0195 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Robles Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0283 | 1 | 1130700040 | Region XI (Davao Region) | Davao del Sur | City of Davao | Daliao | 7.0113 | 125.5014 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129550 | Ramon F. Magsaysay Elementary School | Row 44511 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0284 | 1 | 1381100171 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 171 | 14.5335 | 121.0129 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136599 | Marcela Marcelo ES (Brgy BARANGAY 174) | Row 6724 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BARANGAY 174 anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0285 | 1 | 0304930055 | Region III (Central Luzon) | Nueva Ecija | Talavera | Tabacao | 15.5838 | 120.9188 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105802 | San Jose ES | Row 14077 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0286 | 1 | 0205703003 | Region II (Cagayan Valley) | Quirino | Diffun | Aurora West | 16.5874 | 121.5023 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104300 | Diffun West CS | Row 12064 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0287 | 1 | 0304930035 | Region III (Central Luzon) | Nueva Ecija | Talavera | Maestrang Kikay | 15.5834 | 120.9206 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105806 | Talavera CS | Row 14080 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0288 | 1 | 0731300003 | Region VII (Central Visayas) | Cebu | City of Mandaue | Banilad | 10.3392 | 123.9226 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 312811 | Banilad NHS (Cabancalan NHS Ext.) | Row 36331 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0289 | 1 | 0402114004 | Region IV-A (CALABARZON) | Cavite | Mendez | Palocpoc I | 14.1281 | 120.8789 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108057 | Palocpoc Elementary School | Row 17315 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0290 | 1 | 0203110005 | Region II (Cagayan Valley) | Isabela | Dinapigue | Digumased | 16.5247 | 122.2657 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103551 | Dinapigue Central School | Row 11404 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0291 | 1 | 1705211012 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Poblacion | 13.5011 | 120.9545 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 110619 | Puerto Galera CS | Row 20788 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0292 | 1 | 0103320007 | Region I (Ilocos Region) | La Union | Tubao | Gonzales | 16.3254 | 120.369 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101121 | Gonzales Elementary School | Row 8425 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0293 | 1 | 0403412010 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Antonio | 14.1857 | 121.5062 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108318 | San Antonio ES | Row 17570 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0294 | 1 | 1004315005 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Poblacion | 8.5593 | 124.3527 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127760 | Libertad CS | Row 42129 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0295 | 1 | 1381300009 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagong Pag-asa | 14.6631 | 121.0338 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136507 | Bagong Pag-Asa Elementary School | Row 6637 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0296 | 1 | 0306905035 | Region III (Central Luzon) | Tarlac | Concepcion | San Nicolas | 15.3261 | 120.6544 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106404 | Concepcion North CES | Row 14663 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1041 | 1 | 1130700170 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 37-D | 7.0866 | 125.6128 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 37-D Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0298 | 1 | 0500507036 | Region V (Bicol Region) | Albay | Libon | Sampongan | 13.2599 | 123.3973 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 111765 | Magallang Elementary School (Brgy MAGALLANG) | Row 25133 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay MAGALLANG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0299 | 1 | 0301410050 | Region III (Central Luzon) | Bulacan | City of Malolos | Santo Rosario | 14.8532 | 120.8177 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 345345 | SHS in Malolos City | Row 16253 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0300 | 1 | 0504113020 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. II | 12.3386 | 123.658 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302151 | Mobo National High School | Row 28369 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0301 | 1 | 0305406012 | Region III (Central Luzon) | Pampanga | Floridablanca | Fortuna | 14.9828 | 120.5164 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105988 | Fortuna ES | Row 14260 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0302 | 1 | 0730600081 | Region VII (Central Visayas) | Cebu | City of Cebu | Talamban | 10.3696 | 123.9174 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119904 | Talamban Elementary School | Row 34682 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1042 | 1 | 0205013013 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Roxas | 16.5178 | 121.1851 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 502221 | Solano East CS | Row 12761 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0304 | 1 | 0701216010 | Region VII (Central Visayas) | Bohol | Cortes | Poblacion | 9.7197 | 123.8768 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 118206 | Cortes Central ES | Row 33123 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0305 | 1 | 0501718060 | Region V (Bicol Region) | Camarines Sur | Libmanan | San Isidro | 13.6723 | 123.0088 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112711 | Libmanan South CS | Row 26044 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0306 | 1 | 0205013012 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Quirino | 16.5128 | 121.1825 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104183 | Solano South CS | Row 11968 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0307 | 1 | 0500502019 | Region V (Bicol Region) | Albay | Camalig | Iluluan | 13.1273 | 123.6 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111631 | Iluluan Elementary School | Row 25002 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0308 | 1 | 0201520019 | Region II (Cagayan Valley) | Cagayan | Piat | Poblacion II | 17.7925 | 121.4758 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102827 | Piat CS | Row 10732 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0309 | 1 | 1380300013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Magallanes | 14.5635 | 121.0337 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Magallanes Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0310 | 1 | 0501718006 | Region V (Bicol Region) | Camarines Sur | Libmanan | Bagumbayan | 13.6768 | 123.0323 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 173501 | Aslong ES (Brgy ASLONG) | Row 27919 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay ASLONG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0311 | 1 | 0405629011 | Region IV-A (CALABARZON) | Quezon | Padre Burgos | Burgos | 13.9171 | 121.8175 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108954 | Padre Burgos CS | Row 18180 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0312 | 1 | 0402104016 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 5 | 14.3136 | 121.0539 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 5 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0313 | 1 | 0301422023 | Region III (Central Luzon) | Bulacan | San Rafael | Poblacion | 14.9587 | 120.9685 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 105133 | San Rafael Central School | Row 13455 | Validated (Contiguous Cluster Anchor) | Central elementary school in adjacent Barangay Libis anchoring the contiguous Poblacion-Libis urban settlement core; PTCI/MIDC tower F01103-B07 is located 50m from campus.
FWA-SITE-0314 | 1 | 0305417018 | Region III (Central Luzon) | Pampanga | San Luis | Santo Tomas | 15.0408 | 120.7897 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 306944 | San Luis NHS | Row 16163 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0315 | 1 | 0704603015 | Region VII (Central Visayas) | Negros Oriental | Bacong | Sacsac | 9.2547 | 123.2901 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 120066 | Sacsac ES | Row 34837 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0316 | 1 | 0803739014 | Region VIII (Eastern Visayas) | Leyte | Palo | Cogon | 11.148 | 124.9998 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 121755 | Cogon Elementary School | Row 37609 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0317 | 1 | 0307108015 | Region III (Central Luzon) | Zambales | Palauig | West Poblacion | 15.4341 | 119.9049 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106916 | Palauig Central School | Row 15130 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0318 | 1 | 0105531035 | Region I (Ilocos Region) | Pangasinan | Rosales | Carmay East | 15.8959 | 120.6322 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101892 | Carmay Elementary School | Row 9147 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0319 | 1 | 0331400015 | Region III (Central Luzon) | Zambales | City of Olongapo | New Ilalim | 14.835 | 120.2793 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107138 | Ilalim ES | Row 15322 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0320 | 1 | 1380400001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Acacia | 14.6675 | 120.9689 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136852 | Acacia ES | Row 6959 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0321 | 1 | 0307105009 | Region III (Central Luzon) | Zambales | Iba | Zone 1 Pob. | 15.3285 | 119.9763 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 106875 | Libaba Elementary School | Row 15094 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0322 | 1 | 0304920012 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Poblacion East | 15.8056 | 121.1447 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105604 | Pantabangan East CS | Row 13895 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0323 | 1 | 0501734038 | Region V (Bicol Region) | Camarines Sur | Sipocot | San Vicente | 13.7641 | 122.9755 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113065 | San Vicente ES | Row 26389 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0324 | 1 | 0105506017 | Region I (Ilocos Region) | Pangasinan | Asingan | Poblacion West | 16.0031 | 120.6693 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101715 | Narciso R. Ramos ES SPED Center | Row 8979 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0325 | 1 | 0301421051 | Region III (Central Luzon) | Bulacan | San Miguel | Sapang | 15.1922 | 120.9908 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105086 | Sapang Elementary School | Row 13408 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0326 | 1 | 0600415014 | Region VI (Western Visayas) | Aklan | New Washington | Polo | 11.65 | 122.4341 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114910 | Polo ES | Row 29060 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0327 | 1 | 0501610009 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Santa Elena | 14.1821 | 122.3932 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500634 | Sta. Elena Integrated School | Row 28749 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0328 | 1 | 0305413005 | Region III (Central Luzon) | Pampanga | Mexico | Camuning | 15.1151 | 120.6645 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106166 | Camuning ES | Row 14435 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0329 | 1 | 0504111020 | Region V (Bicol Region) | Masbate | City of Masbate | Kinamaligan | 12.359 | 123.6184 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 113696 | Kinamaligan Elementary School | Row 26987 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0330 | 1 | 1401105001 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Abatan | 16.8037 | 120.8233 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 135457 | Abatan ES | Row 3063 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0331 | 1 | 0103309006 | Region I (Ilocos Region) | La Union | Caba | Poblacion Norte | 16.4312 | 120.3457 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100940 | Caba CES | Row 8264 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0332 | 1 | 0405801009 | Region IV-A (CALABARZON) | Rizal | Angono | San Isidro | 14.5295 | 121.1543 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109307 | Angono Elementary School | Row 18523 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0333 | 1 | 1705320018 | MIMAROPA Region | Palawan | Taytay | Pancol | 10.8707 | 119.4166 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111243 | Pancol Elementary School | Row 21400 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0334 | 1 | 0201516003 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Bagumbayan | 18.1935 | 121.6635 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102724 | Bagumbayan Central School | Row 10637 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0335 | 1 | 0601909036 | Region VI (Western Visayas) | Capiz | Panay | Poblacion Ilawod | 11.5575 | 122.7967 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Ilawod Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0336 | 1 | 0603034020 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion East | 10.6914 | 122.4787 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 116626 | Oton CES | Row 30663 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0337 | 1 | 0702223031 | Region VII (Central Visayas) | Cebu | Danao City | Poblacion | 10.5202 | 124.0277 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119337 | Danao City Central ES | Row 34194 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0338 | 1 | 0203127008 | Region II (Cagayan Valley) | Isabela | San Agustin | Masaya Centro | 16.509 | 121.7457 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103665 | San Agustin Central School | Row 11505 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0339 | 1 | 1381200014 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Palatiw | 14.5646 | 121.083 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136720 | Palatiw Elementary School | Row 6831 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0340 | 1 | 0702233011 | Region VII (Central Visayas) | Cebu | Moalboal | Poblacion West | 9.939 | 123.3927 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119498 | Moalboal Central ES | Row 34321 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0341 | 1 | 0405644013 | Region IV-A (CALABARZON) | Quezon | San Narciso | Pagkakaisa | 13.5679 | 122.5541 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301399 | Godofredo M. Tan Memorial Integrated School of Arts and Trades (Formerly San Narciso Voc. HS) | Row 19501 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0342 | 1 | 0203112036 | Region II (Cagayan Valley) | Isabela | Echague | Pangal Norte | 16.6102 | 121.6771 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103314 | Pangal Norte Elementary School | Row 11187 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0343 | 1 | 1004314008 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Poblacion | 8.5755 | 124.445 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127913 | Laguindingan CS | Row 42254 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0344 | 1 | 1004304005 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Mosangot | 8.9157 | 124.7852 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127733 | Mosangot ES | Row 42103 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0345 | 1 | 0604524015 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay VI | 10.4802 | 123.4187 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay VI Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0346 | 1 | 0501612014 | Region V (Bicol Region) | Camarines Norte | Vinzons | Barangay I | 14.1757 | 122.909 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112316 | Vinzons Pilot Elementary School | Row 25663 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0347 | 1 | 0405639017 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Isidro | 14.1633 | 121.6399 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109086 | Sampaloc ES I | Row 18308 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0348 | 1 | 0304923027 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion Norte | 15.7131 | 121.1036 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105653 | Rizal Central School | Row 13938 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0349 | 1 | 0803750004 | Region VIII (Eastern Visayas) | Leyte | Tunga | San Antonio | 11.2466 | 124.7503 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121961 | Tunga Central School | Row 37814 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0350 | 1 | 1600204011 | Region XIII (Caraga) | Agusan del Norte | Carmen | San Agustin | 9.0564 | 125.2236 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Agustin Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0351 | 1 | 0105523008 | Region I (Ilocos Region) | Pangasinan | Mabini | Calzada | 16.0826 | 119.9275 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101518 | Calzada ES | Row 8794 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0352 | 1 | 1600312006 | Region XIII (Caraga) | Agusan del Sur | Trento | Poblacion | 8.0475 | 126.0633 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0353 | 1 | 0501709013 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Roque | 13.6207 | 123.1741 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112501 | San Roque ES | Row 25841 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0354 | 1 | 0403422004 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Norte | 14.2349 | 121.3655 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108411 | Pila ES | Row 17662 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0355 | 1 | 1030500003 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bulua | 8.5029 | 124.6167 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127998 | Bulua Central School | Row 42330 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0356 | 1 | 0831600108 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 77 | 11.2111 | 125.0077 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 124245 | Dr. AP Banez Memorial School | Row 39981 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0357 | 1 | 0304906023 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VI | 15.7792 | 120.6621 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 105270 | Democrito M. Jose ES | Row 13586 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0358 | 1 | 1600205011 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Poblacion | 9.3486 | 125.5078 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0359 | 1 | 0405802004 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mayamot | 14.6297 | 121.1209 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109331 | Mayamot ES | Row 18547 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0360 | 1 | 0803703015 | Region VIII (Eastern Visayas) | Leyte | Albuera | Tabgas | 10.8976 | 124.7081 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121003 | Tabgas Elementary School | Row 36867 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0361 | 1 | 1004307012 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Poblacion | 8.557 | 124.5216 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127671 | El Salvador City CS | Row 42050 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0362 | 1 | 0604531008 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay V | 10.902 | 123.0753 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302695 | Victorias National High School | Row 32419 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0363 | 1 | 0501706008 | Region V (Bicol Region) | Camarines Sur | Bula | Inoyonan | 13.4698 | 123.2772 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112432 | Felipe P. Panton Elementary School | Row 25773 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0364 | 1 | 0401014041 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 10 | 13.9422 | 121.1574 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 303491 | Lipa City Senior High School (Brgy POBLACION BARANGAY 1) | Row 19630 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION BARANGAY 1 anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0365 | 1 | 0500511010 | Region V (Bicol Region) | Albay | Manito | It-Ba | 13.1261 | 123.8698 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111899 | Manito Central School | Row 25260 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0366 | 1 | 1600208001 | Region XIII (Caraga) | Agusan del Norte | Magallanes | Buhang | 9.0354 | 125.525 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Buhang Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0367 | 1 | 0500507016 | Region V (Bicol Region) | Albay | Libon | Caguscos | 13.2311 | 123.3303 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111791 | Caguscos Elementary School | Row 25156 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0368 | 1 | 0500516012 | Region V (Bicol Region) | Albay | Santo Domingo | San Rafael Pob. | 13.2367 | 123.7794 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 301879 | Sto. Domingo National High School | Row 28106 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0369 | 1 | 0203105007 | Region II (Cagayan Valley) | Isabela | Burgos | Cullalabo San Antonio | 17.0888 | 121.7049 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103135 | San Antonino Elementary School | Row 11015 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0370 | 1 | 0402113008 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I A | 14.2767 | 120.7352 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108043 | Maragondon Elementary School | Row 17301 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0371 | 1 | 1705215020 | MIMAROPA Region | Oriental Mindoro | Victoria | Poblacion III | 13.1669 | 121.2777 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 110699 | Simon Gayutin Memorial Elementary School | Row 20867 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0372 | 1 | 0405814010 | Region IV-A (CALABARZON) | Rizal | Teresa | Calumpang Santo Cristo | 14.5586 | 121.2136 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 109362 | Teresa Elementary School (Brgy DALIG) | Row 18576 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay DALIG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0373 | 1 | 0803733021 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | San Guillermo | 11.1467 | 124.4704 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 303404 | Matag-ob National High School | Row 40273 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0374 | 1 | 0501737008 | Region V (Bicol Region) | Camarines Sur | Tinambac | Binalay | 13.8158 | 123.3409 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113135 | Binalay ES | Row 26459 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0375 | 1 | 0402109008 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-A | 14.4264 | 120.9336 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion III-A Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0376 | 1 | 0102809018 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Medina | 18.0775 | 120.7042 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100123 | Medina Parado ES (Brgy PARADO (BANGAY)) | Row 7500 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay PARADO (BANGAY) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0377 | 1 | 0205701022 | Region II (Cagayan Valley) | Quirino | Aglipay | Pinaripad Norte | 16.4783 | 121.5996 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104236 | Pinaripad Norte ES | Row 12014 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0378 | 1 | 1705207013 | MIMAROPA Region | Oriental Mindoro | Mansalay | Poblacion | 12.5218 | 121.4411 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 110471 | Mansalay CS | Row 20642 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0379 | 1 | 1380500023 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pleasant Hills | 14.5872 | 121.0386 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 224001 | Pleasant HIlls Elementary School | Row 7032 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0380 | 1 | 1400108005 | Cordillera Administrative Region (CAR) | Abra | La Paz | Canan | 17.662 | 120.6689 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 135029 | Canan ES | Row 2674 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0381 | 1 | 0702210038 | Region VII (Central Visayas) | Cebu | Barili | Poblacion | 10.1153 | 123.511 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119073 | Barili I Central ES | Row 33950 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0382 | 1 | 0307104015 | Region III (Central Luzon) | Zambales | Castillejos | Santa Maria | 14.9373 | 120.1983 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Santa Maria Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0383 | 1 | 1004317016 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Poblacion | 9.0213 | 125.1817 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 127785 | Magsaysay CS | Row 42149 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0384 | 1 | 0403415019 | Region IV-A (CALABARZON) | Laguna | Magdalena | Poblacion | 14.1993 | 121.4286 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108341 | Ananias Laico Memorial Elementary School | Row 17593 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0385 | 1 | 0405618012 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Capuluan Tulon | 13.8208 | 122.4877 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108729 | Capuluan Tulon ES | Row 17965 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0386 | 1 | 0603044004 | Region VI (Western Visayas) | Iloilo | Sara | Anoring | 11.2188 | 122.9773 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 180048 | Improgo PS (Brgy IMPROGO) | Row 31968 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay IMPROGO anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0387 | 1 | 1600206011 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Songkoy | 9.4556 | 125.5743 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Songkoy Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0388 | 1 | 0704623020 | Region VII (Central Visayas) | Negros Oriental | Valencia | North Poblacion | 9.2823 | 123.2454 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 120623 | Valencia CES | Row 35388 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0389 | 1 | 0306916082 | Region III (Central Luzon) | Tarlac | City of Tarlac | Sapang Tagalog | 15.4218 | 120.5992 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106747 | Sapang Tagalog ES | Row 14982 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0390 | 1 | 1381500009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Maharlika Village | 14.4978 | 121.0551 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 501954 | Maharlika Integrated School | Row 7375 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0391 | 1 | 0501737004 | Region V (Bicol Region) | Camarines Sur | Tinambac | Banga | 13.8884 | 123.3857 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113114 | Banga Elementary School | Row 26438 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0392 | 1 | 0603039011 | Region VI (Western Visayas) | Iloilo | San Enrique | Dacal | 11.0697 | 122.6567 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 180002 | Dacal PS | Row 31929 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0393 | 1 | 0405628031 | Region IV-A (CALABARZON) | Quezon | Mulanay | Santa Rosa | 13.5289 | 122.3932 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108942 | Santa Rosa ES | Row 18168 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0394 | 1 | 0304906025 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VIII | 15.7803 | 120.662 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 105269 | Cuyapo West CS | Row 13585 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0395 | 1 | 0803736011 | Region VIII (Eastern Visayas) | Leyte | Merida | Libas | 10.9397 | 124.5447 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121723 | Libas Elementary School | Row 37577 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0396 | 1 | 1600307001 | Region XIII (Caraga) | Agusan del Sur | Rosario | Bayugan 3 | 8.386 | 126.0814 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bayugan 3 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0397 | 1 | 0501730029 | Region V (Bicol Region) | Camarines Sur | Ragay | Poblacion Ilaod | 13.8192 | 122.7909 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112969 | Ragay CS | Row 26295 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0398 | 1 | 0304917026 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion East | 15.7143 | 120.9051 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105552 | Munoz CS | Row 13847 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0399 | 1 | 0603009024 | Region VI (Western Visayas) | Iloilo | Batad | Tanao | 11.4191 | 123.111 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Tanao Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0400 | 1 | 0402109084 | Region IV-A (CALABARZON) | Cavite | City of Imus | Palico IV | 14.4281 | 120.947 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 164002 | Palico Elementary School | Row 19084 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0401 | 1 | 1381500001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Tanyag | 14.4801 | 121.0471 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 502057 | Bagong Tanyag Integrated School (Brgy BAGONG TANYAG) | Row 7377 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BAGONG TANYAG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0402 | 1 | 0501603032 | Region V (Bicol Region) | Camarines Norte | Daet | San Isidro | 14.106 | 122.9536 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Isidro Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0403 | 1 | 0401025013 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Poblacion | 13.9281 | 120.9499 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107666 | San Nicolas Central School | Row 16933 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0404 | 1 | 0307109014 | Region III (Central Luzon) | Zambales | San Antonio | Rizal | 14.9492 | 120.0881 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106923 | San Antonio Central School | Row 15137 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0405 | 1 | 1380500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Wack-wack Greenhills | 14.5836 | 121.0338 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 500336 | Addition Hills Integrated School (Brgy ADDITION HILLS) | Row 7359 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay ADDITION HILLS anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0406 | 1 | 0803722019 | Region VIII (Eastern Visayas) | Leyte | Isabel | San Roque | 10.9243 | 124.4398 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121449 | Relocation Elementary School | Row 37305 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0407 | 1 | 0405801005 | Region IV-A (CALABARZON) | Rizal | Angono | Kalayaan | 14.5297 | 121.1536 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109313 | Joaquin Guido Elementary School (Angono ES Unit I) | Row 18529 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0408 | 1 | 0600415002 | Region VI (Western Visayas) | Aklan | New Washington | Cawayan | 11.6503 | 122.4336 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114898 | Cawayan ES | Row 29049 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0409 | 1 | 0803715035 | Region VIII (Eastern Visayas) | Leyte | Carigara | Sawang | 11.3001 | 124.6869 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121254 | Alberto T. Aguja Mem. Central School | Row 37113 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0410 | 1 | 0803738090 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Valencia | 11.1081 | 124.5773 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 124193 | Valencia Central School | Row 39933 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0411 | 1 | 0603009004 | Region VI (Western Visayas) | Iloilo | Batad | Batad Viejo | 11.419 | 123.111 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Batad Viejo Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0412 | 1 | 0604531009 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VI | 10.9091 | 123.0764 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117444 | Salvacion ES | Row 31446 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0413 | 1 | 0307109009 | Region III (Central Luzon) | Zambales | San Antonio | San Gregorio | 14.9519 | 120.0885 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106925 | San Gregorio Elementary School | Row 15139 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0414 | 1 | 0402106008 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan I | 14.3215 | 120.9793 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 342298 | Paliparan III SHS (Brgy PALIPARAN III) | Row 19927 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay PALIPARAN III anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0415 | 1 | 0105526002 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Amansabina | 16.0666 | 120.4001 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102127 | Doña Felisa Navarro ES | Row 9368 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0416 | 1 | 0501602015 | Region V (Bicol Region) | Camarines Norte | Capalonga | Magsaysay | 14.2266 | 122.5522 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112122 | Peter Sawmill Elementary School | Row 25479 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0417 | 1 | 0102812004 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 56-B, Bacsil South | 18.1988 | 120.6558 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 102205 | Bacsil Elementary School (Brgy BGY. NO. 56-A, BACSIL NORTH) | Row 9440 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BGY. NO. 56-A, BACSIL NORTH anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0418 | 1 | 0201504020 | Region II (Cagayan Valley) | Cagayan | Amulung | Centro | 17.8343 | 121.7243 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102403 | Amulung East CS | Row 10326 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0419 | 1 | 0402103046 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino III | 14.3976 | 120.9775 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107886 | Molino Elementary School | Row 17148 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0420 | 1 | 0405607060 | Region IV-A (CALABARZON) | Quezon | Calauag | Pinagkamaligan | 13.9561 | 122.285 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108606 | Pinagkamaligan ES | Row 17848 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0421 | 1 | 0304901021 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Poblacion East I | 15.5011 | 120.8511 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 300783 | Aliaga National High School (Brgy POBLACION EAST II) | Row 15705 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION EAST II anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0422 | 1 | 1606819005 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Bongtod Pob. | 17.1051 | 122.2743 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bongtod Pob. Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0423 | 1 | 0702243020 | Region VII (Central Visayas) | Cebu | San Remigio | Poblacion | 11.081 | 123.9378 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119669 | San Remigio Central ES | Row 34473 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0424 | 1 | 0702248018 | Region VII (Central Visayas) | Cebu | Tabogon | Poblacion | 10.9412 | 124.0281 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119766 | Tabogon Central ES | Row 34560 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0425 | 1 | 0306913005 | Region III (Central Luzon) | Tarlac | San Clemente | Catagudingan | 15.7082 | 120.366 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106617 | Cat-Nag ES | Row 14865 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0426 | 1 | 0401031034 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 3 | 14.1034 | 121.0787 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 230501 | Dayapan Elementary School (Brgy POBLACION BARANGAY 1) | Row 19169 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION BARANGAY 1 anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0427 | 1 | 0201524004 | Region II (Cagayan Valley) | Cagayan | Santa Praxedes | Centro II | 18.5632 | 120.9902 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102921 | Sta. Praxedes CS | Row 10821 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0428 | 1 | 0600401007 | Region VI (Western Visayas) | Aklan | Altavas | Lumaynay | 11.4866 | 122.4282 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114637 | Lumaynay ES, Sang-eayAnnex | Row 28818 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0429 | 1 | 0405625018 | Region IV-A (CALABARZON) | Quezon | Macalelon | Rizal | 13.7477 | 122.1383 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108877 | Macalelon Central Elementary School | Row 18105 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0430 | 1 | 1380200009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Zapote | 14.4639 | 120.9708 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136791 | Zapote Elementary School | Row 6901 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0431 | 1 | 1001321029 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Sinayawan | 7.8732 | 125.1439 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126879 | SINAYAWAN CS | Row 41388 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0432 | 1 | 1380700010 | National Capital Region (NCR) | Metro Manila (NCR) | City of Marikina | Santo Niño | 14.639 | 121.0958 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136687 | Sto. Nino ES | Row 6802 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0433 | 1 | 0803702052 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Milagrosa | 11.2189 | 124.8596 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 120952 | P. Barrantes Primary School (Brgy P. BARRANTES) | Row 36817 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay P. BARRANTES anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0434 | 1 | 1001304004 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Calaocalao | 7.6872 | 124.9182 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 126343 | Calao-calao ES | Row 40933 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0435 | 1 | 0301421050 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Rita Matanda | 15.1336 | 120.9661 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105112 | Sta. Rita Elementary School | Row 13434 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0436 | 1 | 0403428002 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Balibago | 14.2963 | 121.1045 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108470 | Balibago Elementary School | Row 17721 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0437 | 1 | 0300808001 | Region III (Central Luzon) | Bataan | Morong | Binaritan | 14.6824 | 120.268 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104650 | Binaritan ES | Row 12996 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0438 | 1 | 1381000001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Baclaran | 14.5298 | 120.9989 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136767 | Baclaran Elementary School Central | Row 6877 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0439 | 1 | 0702208027 | Region VII (Central Visayas) | Cebu | Balamban | Baliwagan | 10.5066 | 123.7145 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119018 | Balamban Central ES | Row 33904 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0440 | 1 | 0105516007 | Region I (Ilocos Region) | Pangasinan | Burgos | Poblacion | 16.0548 | 119.8647 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101401 | Burgos Central School | Row 8687 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0441 | 1 | 0506216013 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Burabod | 12.9718 | 124.0051 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114563 | Sorsogon East Central School | Row 27806 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0442 | 1 | 0506203009 | Region V (Bicol Region) | Sorsogon | Bulan | Zone V Pob. | 12.6694 | 123.8754 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 114004 | Bulan North CS-B | Row 27270 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0443 | 1 | 0600411009 | Region VI (Western Visayas) | Aklan | Makato | Calimbajan | 11.7215 | 122.2751 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302298 | Dr. Ramon B. Legaspi, Sr. National High School | Row 32025 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0444 | 1 | 0405647043 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Mateuna | 14.0242 | 121.596 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109260 | Tayabas West CS II | Row 18476 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0445 | 1 | 0300803019 | Region III (Central Luzon) | Bataan | City of Balanga | Talisay | 14.6811 | 120.5454 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104552 | Balanga Elementary School | Row 12917 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0446 | 1 | 0203105005 | Region II (Cagayan Valley) | Isabela | Burgos | Catabban | 17.0303 | 121.7419 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103129 | Catabban Elementary School | Row 11009 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0447 | 1 | 0401004009 | Region IV-A (CALABARZON) | Batangas | Balete | Poblacion | 14.02 | 121.0938 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107250 | Balete Central School | Row 16534 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0448 | 1 | 1381300077 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Pansol | 14.6659 | 121.0713 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136553 | Balara ES | Row 6683 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0449 | 1 | 1381000006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Tambo | 14.5167 | 120.9969 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136766 | Tambo Elementary School Main | Row 6876 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0450 | 1 | 1380500004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Barangka Ibaba | 14.5733 | 121.0381 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136670 | Pedro P. Cruz (Mauway) ES (Brgy BARANGKA DRIVE) | Row 6786 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BARANGKA DRIVE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0451 | 1 | 0501733020 | Region V (Bicol Region) | Camarines Sur | San Jose | Salogon | 13.6992 | 123.5183 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113027 | Salogon ES | Row 26352 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0452 | 1 | 0307111003 | Region III (Central Luzon) | Zambales | San Marcelino | Burgos | 14.9791 | 120.1551 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106955 | San Marcelino Elementary School | Row 15168 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0453 | 1 | 0501712020 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Poblacion Zone III | 13.9228 | 122.5968 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112577 | Del Gallego CS | Row 25914 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0454 | 1 | 0405639018 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Roque | 14.1599 | 121.6375 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109085 | Sampaloc Elementary School (Main) | Row 18307 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0455 | 1 | 0603018021 | Region VI (Western Visayas) | Iloilo | Dumangas | Ilaya 1st | 10.827 | 122.7121 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Ilaya 1st Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0456 | 1 | 0504103030 | Region V (Bicol Region) | Masbate | Balud | Tonga | 12.0681 | 123.2379 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113471 | Tonga ES | Row 26774 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0457 | 1 | 0405630021 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 3 Del Carmen | 13.9695 | 121.6834 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108970 | Pagbilao CES (Pagbilao CES & Pabilao East CES) | Row 18194 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0458 | 1 | 0402104011 | Region IV-A (CALABARZON) | Cavite | Carmona | Milagrosa | 14.3083 | 121.0494 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107898 | Milagrosa Elementary School | Row 17160 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0459 | 1 | 0403408001 | Region IV-A (CALABARZON) | Laguna | Famy | Asana | 14.4381 | 121.4495 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108284 | Famy Elementary School | Row 17536 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0460 | 1 | 0103306026 | Region I (Ilocos Region) | La Union | Bangar | Central East No. 2 | 16.8957 | 120.4241 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100893 | Bangar Central Elementary School | Row 8223 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0461 | 1 | 1004324006 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Poblacion | 8.5373 | 124.7553 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127873 | Tagoloan CS | Row 42220 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0462 | 1 | 0803714016 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone II | 11.2931 | 124.6381 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 303341 | Asuncion S. Melgar National High School | Row 40210 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0463 | 1 | 0105535008 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Sur | 16.0636 | 120.6672 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101953 | Juan C. Laya Central School SPED Center | Row 9205 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0464 | 1 | 0603026019 | Region VI (Western Visayas) | Iloilo | Leganes | Poblacion | 10.7882 | 122.5899 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 116477 | Leganes CES | Row 30526 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0465 | 1 | 0702245008 | Region VII (Central Visayas) | Cebu | Santander | Poblacion | 9.4173 | 123.334 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119701 | Santander Central ES | Row 34498 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0466 | 1 | 1102403028 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 1 | 6.7576 | 125.3554 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129750 | Digos City CES | Row 44680 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0467 | 1 | 0102819016 | Region I (Ilocos Region) | Ilocos Norte | Pinili | Pagdilao | 17.9511 | 120.5259 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100241 | Don Mariano Marcos Mem. Sch. | Row 7615 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0468 | 1 | 0701232016 | Region VII (Central Visayas) | Bohol | Maribojoc | Poblacion | 9.7395 | 123.844 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 118550 | Santa Cruz Elementary School | Row 33459 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0469 | 1 | 0401034013 | Region IV-A (CALABARZON) | Batangas | Tuy | Luna | 14.0212 | 120.7311 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 342207 | Tuy Senior High School | Row 19903 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0470 | 1 | 0603017048 | Region VI (Western Visayas) | Iloilo | Dueñas | Poblacion A | 11.0667 | 122.6169 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion A Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0471 | 1 | 0506206029 | Region V (Bicol Region) | Sorsogon | Castilla | San Isidro | 12.9736 | 123.8402 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114114 | San Isidro ES | Row 27377 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0472 | 1 | 0604531007 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay IV | 10.9009 | 123.0777 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 117447 | Victorias North ES | Row 31449 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0473 | 1 | 0501726017 | Region V (Bicol Region) | Camarines Sur | Pamplona | Tambo | 13.5783 | 123.0639 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112879 | Tambo ES | Row 26207 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0474 | 1 | 0405603041 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tinandog | 13.9963 | 121.9121 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Tinandog Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0475 | 1 | 0301423002 | Region III (Central Luzon) | Bulacan | Santa Maria | Balasing | 14.8506 | 121.0019 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105141 | Balasing Elementary School | Row 13463 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0476 | 1 | 1705205049 | MIMAROPA Region | Oriental Mindoro | City of Calapan | San Antonio | 13.4261 | 121.1956 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 111546 | San Antonio Elementary School | Row 21696 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0477 | 1 | 0403426026 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Sur | 14.2812 | 121.4113 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108449 | Santo Angel Sur ES | Row 17700 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0478 | 1 | 0405607017 | Region IV-A (CALABARZON) | Quezon | Calauag | Barangay V | 13.9582 | 122.2897 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108574 | Calauag East CES | Row 17816 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0479 | 1 | 0203131029 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone III | 16.9877 | 122.0143 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 155514 | Angela Elementary School | Row 12208 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0480 | 1 | 0500517007 | Region V (Bicol Region) | Albay | City of Tabaco | Basud | 13.3541 | 123.7289 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114608 | Basud ES | Row 27848 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0481 | 1 | 0300810016 | Region III (Central Luzon) | Bataan | Orion | Kapunitan | 14.6163 | 120.5817 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104678 | Capunitan ES | Row 13021 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0482 | 1 | 0403424036 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Del Remedio | 14.0815 | 121.3137 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109768 | Del Remedio Elementary School | Row 18960 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0483 | 1 | 0405641014 | Region IV-A (CALABARZON) | Quezon | San Antonio | Poblacion | 13.8904 | 121.2872 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109112 | San Antonio CS | Row 18334 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0484 | 1 | 0105527011 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Bogtong Silag | 15.8127 | 120.2812 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101589 | Silag ES | Row 8864 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0485 | 1 | 0304931014 | Region III (Central Luzon) | Nueva Ecija | Talugtug | Osmeña | 15.7783 | 120.8138 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105846 | Talugtug East CS | Row 14118 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0486 | 1 | 0201508016 | Region II (Cagayan Valley) | Cagayan | Buguey | Pattao | 18.2481 | 121.8158 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102570 | Buguey South CS (Pattao ES) | Row 10489 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0487 | 1 | 0102820002 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Ildefonso | 18.1728 | 120.5946 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100260 | San Nicolas ES | Row 7633 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0488 | 1 | 0405618010 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Calimpak | 13.9007 | 122.4515 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301323 | Guinayangan NHS | Row 19427 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0489 | 1 | 1004317008 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Consuelo | 8.9155 | 125.1874 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 127777 | Consuelo ES | Row 42142 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0490 | 1 | 0402116001 | Region IV-A (CALABARZON) | Cavite | Noveleta | Magdiwang | 14.4313 | 120.8798 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Magdiwang Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0491 | 1 | 0500507005 | Region V (Bicol Region) | Albay | Libon | Zone II | 13.2982 | 123.4415 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111762 | Libon East Central School | Row 25130 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0492 | 1 | 0203119006 | Region II (Cagayan Valley) | Isabela | Mallig | Maligaya | 17.1847 | 121.6121 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103495 | Maligaya Elementary School | Row 11353 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0493 | 1 | 0601912020 | Region VI (Western Visayas) | Capiz | Pontevedra | Ilaya | 11.4795 | 122.8317 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Ilaya Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0494 | 1 | 1404409014 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Poblacion | 17.085 | 120.8979 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 136351 | Sagada Central School | Row 3880 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0495 | 1 | 0306911014 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 3 | 15.6242 | 120.6485 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106604 | Pura Community School | Row 14854 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0496 | 1 | 0405647003 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone I | 14.0223 | 121.5959 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109243 | Tayabas East CS | Row 18462 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0497 | 1 | 0401031046 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Talaga | 14.1034 | 121.097 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107780 | Paaralang Sentral ng Talaga | Row 17043 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0498 | 1 | 0103311025 | Region I (Ilocos Region) | La Union | Naguilian | Magungunay | 16.4743 | 120.4064 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100971 | Ambaracao Sur Elementary School (Brgy AMBARACAO SUR) | Row 8292 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay AMBARACAO SUR anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0499 | 1 | 1408106014 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Mataguisi | 18.1287 | 121.3478 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135356 | Mataguisi ES | Row 2975 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0500 | 1 | 1004309009 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Poblacion | 8.5952 | 124.4068 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127758 | Gitagum CS | Row 42127 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0501 | 1 | 0401019009 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 4 | 14.0735 | 120.6335 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107512 | Nasugbu West Central School | Row 16784 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0502 | 1 | 0203126013 | Region II (Cagayan Valley) | Isabela | Roxas | Bantug | 17.1144 | 121.6129 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103640 | Bantug-Lintao Elementary School | Row 11481 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0503 | 1 | 0401029015 | Region IV-A (CALABARZON) | Batangas | Taal | Ilog | 13.8926 | 120.9315 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 107732 | Latag Elementary School (Brgy LATAG) | Row 16995 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay LATAG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0504 | 1 | 0307706009 | Region III (Central Luzon) | Aurora | Dipaculao | Dinadiawan | 16.0772 | 121.7706 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104469 | Dinadiawan ES | Row 12837 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0505 | 1 | 0301423018 | Region III (Central Luzon) | Bulacan | Santa Maria | San Gabriel | 14.8069 | 120.9585 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105161 | San Gabriel ES | Row 13482 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0506 | 1 | 0306903027 | Region III (Central Luzon) | Tarlac | Camiling | Malacampa | 15.6402 | 120.4118 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106346 | Malacampa ES - Main | Row 14608 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0507 | 1 | 0103305012 | Region I (Ilocos Region) | La Union | Balaoan | Cabuaan Oeste | 16.8014 | 120.4186 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100882 | Masupe Elementary School (Brgy MASUPE) | Row 8213 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay MASUPE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0508 | 1 | 0330100001 | Region III (Central Luzon) | Pampanga | City of Angeles | Agapito del Rosario | 15.1494 | 120.5926 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 107051 | Virgen Delos Remedios Elementary School (Brgy VIRGEN DELOS REMEDIOS) | Row 15251 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay VIRGEN DELOS REMEDIOS anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0509 | 1 | 0506207034 | Region V (Bicol Region) | Sorsogon | Donsol | Rawis | 12.9034 | 123.5959 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114150 | Rawis Elementary School | Row 27412 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0510 | 1 | 1705320021 | MIMAROPA Region | Palawan | Taytay | Pularaquen | 10.9559 | 119.4853 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 111221 | Canique Elementary School | Row 21378 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0511 | 1 | 1001320021 | Region X (Northern Mindanao) | Bukidnon | Talakag | Barangay 3 | 8.2347 | 124.6002 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 126826 | Talakag CES | Row 41359 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0512 | 1 | 0600402011 | Region VI (Western Visayas) | Aklan | Balete | Poblacion | 11.5573 | 122.3783 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500543 | Balete Integrated School | Row 32698 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0513 | 1 | 0306907003 | Region III (Central Luzon) | Tarlac | La Paz | Caramutan | 15.4454 | 120.7197 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106497 | Caramutan ES | Row 14752 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0514 | 1 | 0305415033 | Region III (Central Luzon) | Pampanga | Porac | Sinura | 15.1161 | 120.57 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106235 | Siñura Elementary School | Row 14503 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0515 | 1 | 1380900001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Sipac-Almacen | 14.6583 | 120.9483 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136856 | Bagumbayan Elementary School | Row 6962 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0516 | 1 | 0402109075 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion II-B | 14.4051 | 120.9263 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 107982 | Bukandala ES (Brgy BUCANDALA II) | Row 17243 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BUCANDALA II anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0517 | 1 | 0307104012 | Region III (Central Luzon) | Zambales | Castillejos | San Nicolas | 14.927 | 120.2016 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106865 | San Nicolas Primary School | Row 15084 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0518 | 1 | 0401023029 | Region IV-A (CALABARZON) | Batangas | San Juan | Poblacion | 13.8272 | 121.3943 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107632 | San Juan West Central School | Row 16900 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1043 | 1 | 0401006022 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Proper | 13.7944 | 120.9978 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107273 | Manghinao Elementary School | Row 16556 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0520 | 1 | 0701230036 | Region VII (Central Visayas) | Bohol | Loon | Cogon Norte | 9.8033 | 123.8002 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 118498 | Cogon Norte ES | Row 33410 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0521 | 1 | 0305417014 | Region III (Central Luzon) | Pampanga | San Luis | Santa Monica | 15.0364 | 120.7896 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106250 | Sta. Monica ES | Row 14517 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0522 | 1 | 0501736022 | Region V (Bicol Region) | Camarines Sur | Tigaon | Talojongon | 13.6277 | 123.4963 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 113108 | Tigaon CPS | Row 26432 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0523 | 1 | 0205704014 | Region II (Cagayan Valley) | Quirino | Maddela | Lusod | 16.334 | 121.6792 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104328 | Lusod Elementary School | Row 12086 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0524 | 1 | 0702247016 | Region VII (Central Visayas) | Cebu | Sogod | Poblacion | 10.7491 | 124.0048 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119743 | Poblacion ES | Row 34538 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0525 | 1 | 0405627024 | Region IV-A (CALABARZON) | Quezon | Mauban | Polo | 14.1771 | 121.7166 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108913 | Polo ES | Row 18140 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0526 | 1 | 0205014001 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Sur | 16.5783 | 121.1888 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104214 | Bintawan South Elementary School | Row 11997 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0527 | 1 | 0201502010 | Region II (Cagayan Valley) | Cagayan | Alcala | Centro Norte | 17.9027 | 121.6547 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102359 | Alcala East Central School | Row 10286 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0528 | 1 | 0201506019 | Region II (Cagayan Valley) | Cagayan | Baggao | Poblacion | 17.9344 | 121.7718 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 102511 | Baggao West CS | Row 10431 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0529 | 1 | 0304932017 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Vicente | 15.4546 | 120.7904 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105866 | Zaragoza CS | Row 14138 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0530 | 1 | 0301415019 | Region III (Central Luzon) | Bulacan | Pandi | Siling Bata | 14.8924 | 120.97 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104975 | Matias B. Salvador Memorial Elementary School | Row 13300 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0531 | 1 | 1380800004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Muntinlupa | Cupang | 14.4304 | 121.0495 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136913 | Cupang Elementary School - Annex | Row 7012 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0532 | 1 | 0401001015 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Poblacion | 13.934 | 120.9344 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107202 | Agoncillo Central School | Row 16489 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0533 | 1 | 1102315029 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Francisco | 7.3033 | 125.6813 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129784 | Panabo Central Elementary School SPED Center | Row 44714 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0534 | 1 | 0301419001 | Region III (Central Luzon) | Bulacan | San Ildefonso | Akle | 15.0484 | 121.0715 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105048 | Akle ES | Row 13370 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0535 | 1 | 0102818003 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Anao | 18.168 | 120.7195 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Anao Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0536 | 1 | 0501726009 | Region V (Bicol Region) | Camarines Sur | Pamplona | Poblacion | 13.5915 | 123.0795 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112871 | Pamplona Central School | Row 26199 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0537 | 1 | 0402110026 | Region IV-A (CALABARZON) | Cavite | Indang | Barangay 4 | 14.2 | 120.8734 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301201 | Indang National High School | Row 19307 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0538 | 1 | 0201505037 | Region II (Cagayan Valley) | Cagayan | Aparri | Punta | 18.3587 | 121.6344 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102449 | Punta Elementary School | Row 10372 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0539 | 1 | 0501703004 | Region V (Bicol Region) | Camarines Sur | Bato | Caricot | 13.3561 | 123.3639 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112369 | Don Teofilo Landagan PS (Caricot) | Row 25714 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0540 | 1 | 0401004010 | Region IV-A (CALABARZON) | Batangas | Balete | Sala | 14.0199 | 121.1017 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Sala Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0541 | 1 | 0306917025 | Region III (Central Luzon) | Tarlac | Victoria | San Vicente | 15.5775 | 120.6813 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Vicente Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0542 | 1 | 0305417012 | Region III (Central Luzon) | Pampanga | San Luis | Santa Cruz Poblacion | 15.041 | 120.7908 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106245 | San Luis CS | Row 14513 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0543 | 1 | 1381200024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Santa Cruz | 14.563 | 121.0791 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136719 | Liberato Damian Elementary School | Row 6830 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0544 | 1 | 0500510010 | Region V (Bicol Region) | Albay | Malinao | Comun | 13.3437 | 123.6629 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111873 | Comun Elementary School | Row 25235 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0545 | 1 | 0603009003 | Region VI (Western Visayas) | Iloilo | Batad | Banban | 11.4184 | 123.1111 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Banban Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0546 | 1 | 1606819022 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Telaje | 17.105 | 122.2744 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Telaje Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0547 | 1 | 0105524062 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Poblacion | 15.9233 | 120.4127 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101546 | Malasiqui I CS | Row 8822 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0548 | 1 | 1381200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Antonio | 14.5668 | 121.0848 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Antonio Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0549 | 1 | 0301423016 | Region III (Central Luzon) | Bulacan | Santa Maria | Poblacion | 14.822 | 120.9625 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105168 | Sta. Maria Elementary School | Row 13489 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0550 | 1 | 0301403030 | Region III (Central Luzon) | Bulacan | Baliuag | Virgen delas Flores | 14.9458 | 120.886 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104760 | Virgen delas Flores ES | Row 13100 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0551 | 1 | 0504113019 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. I | 12.3373 | 123.6557 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113750 | Mobo CS | Row 27039 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0552 | 1 | 1705206023 | MIMAROPA Region | Oriental Mindoro | Gloria | Narra | 12.9564 | 121.4778 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110449 | Malusak ES | Row 20620 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0553 | 1 | 0405616022 | Region IV-A (CALABARZON) | Quezon | General Luna | San Jose | 13.6937 | 122.1715 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 305767 | General Luna National High School | Row 19661 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0554 | 1 | 0403413015 | Region IV-A (CALABARZON) | Laguna | Lumban | Santo Niño | 14.2985 | 121.4615 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108333 | Santo Niño ES | Row 17585 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0555 | 1 | 0305417006 | Region III (Central Luzon) | Pampanga | San Luis | San Nicolas | 15.041 | 120.7908 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500123 | San Nicolas ES | Row 16268 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0556 | 1 | 0205005026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | San Nicolas North | 16.4878 | 121.1501 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 104002 | Bayombong West ES | Row 11801 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0557 | 1 | 0501706029 | Region V (Bicol Region) | Camarines Sur | Bula | San Roque | 13.4695 | 123.2764 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112427 | Bula Central School | Row 25768 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0558 | 1 | 1004301010 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Poblacion | 8.5731 | 124.473 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127584 | Alubijid CS | Row 41980 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0559 | 1 | 1004322011 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Poblacion | 8.8592 | 124.7901 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127860 | Salay CS | Row 42209 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0560 | 1 | 0702216014 | Region VII (Central Visayas) | Cebu | Catmon | Macaas | 10.6961 | 124.0119 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119219 | Macaas ES | Row 34090 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0561 | 1 | 0301415016 | Region III (Central Luzon) | Bulacan | Pandi | Poblacion | 14.8664 | 120.9562 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104976 | Mamerto C. Bernardo Memorial Central School | Row 13301 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0562 | 1 | 0401027004 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Calayaan | 13.8776 | 120.9666 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Calayaan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0563 | 1 | 0402108015 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Manggahan | 14.2966 | 120.9118 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107951 | Manggahan Elementary School | Row 17213 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0564 | 1 | 0704625010 | Region VII (Central Visayas) | Negros Oriental | Zamboanguita | Poblacion | 9.101 | 123.1991 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120654 | Zamboanguita CES | Row 35418 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0565 | 1 | 1004321014 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Poblacion | 8.5205 | 124.5718 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127846 | Opol CS | Row 42198 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0566 | 1 | 0431200011 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 8 | 13.9301 | 121.6114 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109710 | Lucena East IV Elementary School | Row 18905 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0567 | 1 | 0402122003 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Cabuco | 14.2676 | 120.8472 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107999 | Feliciano Cabuco Elementary School | Row 17258 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0568 | 1 | 0402102011 | Region IV-A (CALABARZON) | Cavite | Amadeo | Barangay I | 14.1672 | 120.924 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107857 | Amadeo Elementary School | Row 17119 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0569 | 1 | 1402703018 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Poblacion | 16.7774 | 121.084 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135871 | Kiangan Central School | Row 3425 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0570 | 1 | 1381100081 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 81 | 14.5433 | 120.9981 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136605 | P. Villanueva Elementary School (Brgy BARANGAY 88) | Row 6730 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BARANGAY 88 anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0571 | 1 | 0203135033 | Region II (Cagayan Valley) | Isabela | City of Santiago | Sinsayon | 16.691 | 121.5246 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103832 | Sinsayon ES | Row 11644 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0572 | 1 | 0401008017 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 2 | 13.8331 | 120.63 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 342211 | Calatagan Senior High School | Row 19905 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0573 | 1 | 1401107017 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Poblacion | 16.623 | 120.8387 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 135554 | Kabayan CS | Row 3143 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0574 | 1 | 0600415008 | Region VI (Western Visayas) | Aklan | New Washington | Lawa-an | 11.6508 | 122.4333 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114905 | Lawa-an ES | Row 29056 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0575 | 1 | 0403413002 | Region IV-A (CALABARZON) | Laguna | Lumban | Balimbingan | 14.2984 | 121.4616 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Balimbingan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0576 | 1 | 1381200022 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Miguel | 14.5669 | 121.0847 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136743 | San Miguel Elementary School | Row 6854 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0577 | 1 | 0601914032 | Region VI (Western Visayas) | Capiz | City of Roxas | Lanot | 11.5177 | 122.7551 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Lanot Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0578 | 1 | 0301418022 | Region III (Central Luzon) | Bulacan | Pulilan | Poblacion | 14.9041 | 120.8481 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105020 | Pulilan Central School | Row 13342 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0579 | 1 | 0704601004 | Region VII (Central Visayas) | Negros Oriental | Amlan | Mag-abo | 9.4642 | 123.2206 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 120020 | Amlan CES | Row 34791 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0580 | 1 | 0105514030 | Region I (Ilocos Region) | Pangasinan | Bolinao | Victory | 16.3866 | 119.8929 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101369 | Victory Elementary School | Row 8657 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0581 | 1 | 0501725016 | Region V (Bicol Region) | Camarines Sur | Ocampo | Poblacion West | 13.5591 | 123.3747 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112859 | Ocampo Central School | Row 26187 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0582 | 1 | 0102806011 | Region I (Ilocos Region) | Ilocos Norte | Burgos | Poblacion | 18.5124 | 120.6439 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100105 | Burgos Central Elementary School | Row 7482 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0583 | 1 | 0203134016 | Region II (Cagayan Valley) | Isabela | Santa Maria | San Antonio | 17.4771 | 121.7575 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103851 | San Antonio-Lingaling Elementary School | Row 11661 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0584 | 1 | 0603009002 | Region VI (Western Visayas) | Iloilo | Batad | Alinsolong | 11.4183 | 123.1111 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Alinsolong Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0585 | 1 | 0501709015 | Region V (Bicol Region) | Camarines Sur | Camaligan | Santo Tomas | 13.621 | 123.1656 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 302052 | Camaligan National High School (formerly: Santo Tomas NHS) (Brgy SAN JOSE-SAN PABLO (POB.)) | Row 28276 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAN JOSE-SAN PABLO (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0586 | 1 | 0304921008 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Poblacion III | 15.3516 | 121.001 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 105614 | Peñaranda CS (Brgy POBLACION II) | Row 13902 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION II anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0587 | 1 | 0300810001 | Region III (Central Luzon) | Bataan | Orion | Arellano | 14.618 | 120.5771 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Arellano Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0588 | 1 | 0405802009 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Roque | 14.5844 | 121.1737 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109327 | Juan Sumulong ES | Row 18543 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0589 | 1 | 0405812005 | Region IV-A (CALABARZON) | Rizal | Tanay | Kaybuto | 14.4976 | 121.2811 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109508 | Marciana P. Catolos Memorial Elementary School | Row 18715 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0590 | 1 | 0105514011 | Region I (Ilocos Region) | Pangasinan | Bolinao | Germinal | 16.3861 | 119.894 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500370 | Bolinao Integrated School | Row 10136 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0591 | 1 | 0403422005 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Sur | 14.234 | 121.3661 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 307905 | DON MANUEL RIVERA MEMORIAL INTEGRATED NATIONAL HIGH SCHOOL | Row 19731 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0592 | 1 | 0405807015 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Special District | 14.3541 | 121.324 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109449 | Jalajala Elemetary School | Row 18658 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0593 | 1 | 0201516023 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Magapit | 18.1285 | 121.6791 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102748 | Magapit ES | Row 10660 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0594 | 1 | 1001306014 | Region X (Northern Mindanao) | Bukidnon | Kadingilan | Poblacion | 7.6014 | 124.91 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126399 | Kadingilan CES | Row 40985 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0595 | 1 | 0306903003 | Region III (Central Luzon) | Tarlac | Camiling | Anoling 3rd | 15.6474 | 120.3884 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 106355 | Anoling ES (Brgy ANOLING 2ND) | Row 14617 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay ANOLING 2ND anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0596 | 1 | 0603026011 | Region VI (Western Visayas) | Iloilo | Leganes | Gua-an | 10.7881 | 122.59 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Gua-an Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0597 | 1 | 0603044033 | Region VI (Western Visayas) | Iloilo | Sara | Poblacion Ilawod | 11.2573 | 123.0194 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Ilawod Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0598 | 1 | 1381100183 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 183 | 14.5239 | 121.0131 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136596 | Villamor Airbase ES | Row 6722 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0599 | 1 | 0201526011 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Centro Sur | 17.8813 | 121.571 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 102953 | Sto. Nino Central Elementary School | Row 10850 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0600 | 1 | 1381500012 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Santa Ana | 14.5255 | 121.0754 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500565 | Taguig Integrated School | Row 7368 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0601 | 1 | 0931700012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Buenavista | 7.2389 | 122.2581 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 501887 | Buenavista IS | Row 24914 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0602 | 1 | 0603019007 | Region VI (Western Visayas) | Iloilo | Estancia | Cano-an | 11.4575 | 123.1296 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Cano-an Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0603 | 1 | 0403417002 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Alibungbungan | 14.139 | 121.4181 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108357 | Crisanto Guysayko MES | Row 17609 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0604 | 1 | 0403423005 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 2 | 14.113 | 121.3947 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 307903 | Cristobal S. Conducto Memorial National High School | Row 19730 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0605 | 1 | 1381300031 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Doña Imelda | 14.6153 | 121.0183 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136584 | Betty Go Belmonte ES | Row 6710 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0606 | 1 | 0402106013 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc I | 14.2986 | 120.9559 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107913 | V. P. Villanueva MS (Palapala) | Row 17175 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0607 | 1 | 0631000098 | Region VI (Western Visayas) | Iloilo | City of Iloilo | M. V. Hechanova | 10.7473 | 122.5641 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 302746 | R. G. Hechanova Memorial NHS | Row 32468 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0608 | 1 | 0731300017 | Region VII (Central Visayas) | Cebu | City of Mandaue | Maguikay | 10.341 | 123.9365 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120013 | Maguikay ES | Row 34784 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0609 | 1 | 0103306031 | Region I (Ilocos Region) | La Union | Bangar | Reyna Regente | 16.8926 | 120.4282 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100904 | RUS Elementary School | Row 8232 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0610 | 1 | 1204704032 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Poblacion | 7.0067 | 125.0899 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 131326 | Kidapawan City Pilot Elementary School | Row 46756 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0611 | 1 | 0203131028 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone II | 16.9825 | 122.0147 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103742 | San Mariano Central School SPED Center | Row 11566 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0612 | 1 | 0704606025 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Tinago | 9.3624 | 122.8083 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 120123 | Bayawan City East Central School | Row 34894 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0613 | 1 | 1430300076 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | New Lucban | 16.4225 | 120.5948 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136392 | Alfonso Tabora ES | Row 3920 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0614 | 1 | 0403405049 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Real | 14.1985 | 121.1492 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109823 | Real Elementary School | Row 19012 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0615 | 1 | 1004308062 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Punong | 8.8423 | 125.1534 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 128020 | Punong Elementary School | Row 42351 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0616 | 1 | 0402121002 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion II | 14.2863 | 120.7176 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 108176 | Ternate Central School | Row 17430 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0617 | 1 | 1380200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Uno | 14.4385 | 121.0024 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136790 | Talon Elementary School | Row 6900 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0618 | 1 | 0102926005 | Region I (Ilocos Region) | Ilocos Sur | Santa Maria | Baliw Laud | 17.3812 | 120.4821 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100710 | Maynganay Elementary School (Brgy MAYNGANAY NORTE) | Row 8057 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay MAYNGANAY NORTE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0619 | 1 | 0402115016 | Region IV-A (CALABARZON) | Cavite | Naic | Latoria | 14.3098 | 120.772 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Latoria Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0620 | 1 | 0403408020 | Region IV-A (CALABARZON) | Laguna | Famy | Tunhac | 14.4387 | 121.4499 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301240 | Famy National Integrated High School | Row 19346 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0621 | 1 | 0402103051 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Niog II | 14.4539 | 120.9581 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107887 | Niog Elementary School | Row 17149 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0622 | 1 | 0105544046 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion East | 15.9267 | 120.8424 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102093 | Umingan CES | Row 9335 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0623 | 1 | 0301406010 | Region III (Central Luzon) | Bulacan | Bustos | Poblacion | 14.9558 | 120.919 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104786 | Bustos Elementary School | Row 13124 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0624 | 1 | 0603009012 | Region VI (Western Visayas) | Iloilo | Batad | Caw-i | 11.4177 | 123.1098 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Caw-i Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0625 | 1 | 0201528023 | Region II (Cagayan Valley) | Cagayan | Tuao | Naruangan | 17.6693 | 121.5151 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102966 | Naruangan Central School | Row 10862 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0626 | 1 | 0803738076 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Punta | 11.009 | 124.5999 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 124198 | Punta Elementary School | Row 39937 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0627 | 1 | 0501724004 | Region V (Bicol Region) | Camarines Sur | City of Naga | Balatas | 13.6311 | 123.2015 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114509 | Mac Mariano Elementary School | Row 27756 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0628 | 1 | 0306914007 | Region III (Central Luzon) | Tarlac | San Manuel | Poblacion | 15.7997 | 120.6081 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106652 | Gabaldon Central ES | Row 14896 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0629 | 1 | 0205702007 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Gundaway | 16.5203 | 121.528 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 300656 | Cabarroguis NSAT | Row 12491 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0630 | 1 | 0631000135 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Quintin Salas | 10.7428 | 122.5648 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 182502 | Quintin Salas Elem. School | Row 32000 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0631 | 1 | 0431200021 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Iyam | 13.9307 | 121.6093 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109737 | Ibabang Iyam Elementary School | Row 18932 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0632 | 1 | 0630200051 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Mansilingan | 10.6195 | 122.9762 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 181003 | Kabugwason ES | Row 31997 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0633 | 1 | 0102820022 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | Santa Asuncion | 18.1725 | 120.596 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 100251 | Asuncion ES | Row 7624 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0634 | 1 | 1130700152 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 19-B | 7.0944 | 125.6036 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129696 | Don Francisco S. Dizon Sr., Elementary School | Row 44631 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0635 | 1 | 0401012047 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ilaya | 13.8757 | 120.9136 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107389 | R. Venturanza Central School | Row 16664 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0636 | 1 | 0102808015 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Pias Norte | 17.9919 | 120.5027 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100117 | Pias-Gaang ES | Row 7494 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0637 | 1 | 0500517015 | Region V (Bicol Region) | Albay | City of Tabaco | Cobo | 13.3508 | 123.7286 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114612 | Cobo ES | Row 27851 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0638 | 1 | 1230800034 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | City Heights | 6.1256 | 125.1742 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 131270 | Dadiangas Heights Elementary School | Row 46701 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0639 | 1 | 0203122002 | Region II (Cagayan Valley) | Isabela | Quezon | Alunan | 17.3118 | 121.6093 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103571 | Quezon Central School | Row 11422 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0640 | 1 | 1403213037 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Dagupan Weste | 17.4739 | 121.4658 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136012 | Tabuk City Central School | Row 3560 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0641 | 1 | 0501736015 | Region V (Bicol Region) | Camarines Sur | Tigaon | Poblacion | 13.6332 | 123.4959 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 113109 | Tigaon North CS | Row 26433 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0642 | 1 | 0403419013 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Barangay II | 14.2752 | 121.4533 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108384 | FRANCISCO BENITEZ MEMORIAL SCHOOL | Row 17636 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0643 | 1 | 0603036003 | Region VI (Western Visayas) | Iloilo | Pavia | Anilao | 10.7776 | 122.5392 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 116643 | Pavia Pilot ES (Brgy PUROK II (POB.)) | Row 30680 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay PUROK II (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0644 | 1 | 1600314024 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Kolambugan | 9.0311 | 125.7891 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Kolambugan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0645 | 1 | 0501721015 | Region V (Bicol Region) | Camarines Sur | Milaor | San Jose | 13.5993 | 123.1779 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112788 | San Jose ES | Row 26117 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0646 | 1 | 0701205016 | Region VII (Central Visayas) | Bohol | Baclayon | Taguihon | 9.625 | 123.9219 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Taguihon Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0647 | 1 | 0908305013 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Lower Ipil Heights | 7.7835 | 122.5843 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Lower Ipil Heights Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0648 | 1 | 0405804021 | Region IV-A (CALABARZON) | Rizal | Binangonan | Limbon-limbon | 14.4414 | 121.2056 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109384 | Limbon-Limbon ES | Row 18598 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0649 | 1 | 0506211001 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Norte | 12.8241 | 123.8424 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302222 | Magallanes National High School | Row 28439 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0650 | 1 | 0402113024 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I B | 14.2768 | 120.7341 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301178 | Cavite Science Integrated School | Row 19284 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0651 | 1 | 0431200008 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 5 | 13.9358 | 121.6095 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109745 | Lucena West IV Elementary School | Row 18940 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0652 | 1 | 1380200018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Tres | 14.4407 | 121.004 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 226503 | Talon 3 Elementary School | Row 7038 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0653 | 1 | 1402701016 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Poblacion | 16.9141 | 121.0601 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135813 | Banaue CS | Row 3371 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0654 | 1 | 0402103039 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi II | 14.4599 | 120.9524 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Maliksi II Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0655 | 1 | 0304924009 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Poblacion | 15.3067 | 120.8554 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105670 | San Antonio CS | Row 13955 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0656 | 1 | 0506211002 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Sur | 12.8187 | 123.841 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114287 | Aguada Elementary School | Row 27544 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0657 | 1 | 0105505014 | Region I (Ilocos Region) | Pangasinan | Anda | Poblacion | 16.2866 | 119.9508 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101219 | San Nicolas Elementary School | Row 8515 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0658 | 1 | 0803715031 | Region VIII (Eastern Visayas) | Leyte | Carigara | Ponong | 11.3015 | 124.6865 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 121260 | Cassidy Elementary School | Row 37119 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0659 | 1 | 0803738068 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Mas-in | 11.0632 | 124.5147 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 501363 | Mas-in Integrated School | Row 40762 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0660 | 1 | 0205010027 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Castillo Village | 16.3547 | 120.8926 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 156011 | Castillo Village ES | Row 12240 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0661 | 1 | 0600413008 | Region VI (Western Visayas) | Aklan | Malinao | Kinalangay Nuevo | 11.6231 | 122.2935 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114863 | Kinalangay Nuevo PS | Row 29017 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0662 | 1 | 0506216010 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Buenavista | 13.039 | 124.1073 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114525 | Buenavista Elementary School | Row 27771 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0663 | 1 | 1380200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Kuatro | 14.435 | 121.0036 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 305435 | Talon Village National High School | Row 7189 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0664 | 1 | 0301420041 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan Proper | 14.8447 | 121.0801 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107149 | Minuyan Elementary School | Row 15330 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0665 | 1 | 1001314006 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Diclum | 8.3736 | 124.8495 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 126627 | Dicklum ES | Row 41186 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0666 | 1 | 0304905015 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Joson | 15.9483 | 120.9778 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 105244 | Digdig-Joson ES | Row 13562 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0667 | 1 | 0300810012 | Region III (Central Luzon) | Bataan | Orion | Daang Bilolo | 14.6181 | 120.577 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104682 | Arellano Elementary School | Row 13025 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0668 | 1 | 0102933019 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Farola | 16.9328 | 120.4475 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 502140 | Tagudin Integrated School (Brgy DEL PILAR (POB.)) | Row 10232 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay DEL PILAR (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0669 | 1 | 0908305009 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Ipil Heights | 7.7836 | 122.5842 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 125618 | Ipil Heights Elementary School | Row 23724 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0670 | 1 | 0405648021 | Region IV-A (CALABARZON) | Quezon | Tiaong | Quipot | 13.9596 | 121.3203 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301380 | Recto MNHS | Row 19482 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0671 | 1 | 0803738051 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Don Felipe Larrazabal | 11.0112 | 124.6042 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 303658 | New Ormoc City National High School | Row 40516 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0672 | 1 | 0301423017 | Region III (Central Luzon) | Bulacan | Santa Maria | Pulong Buhangin | 14.8666 | 120.997 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105144 | CORNELIA M. DE JESUS MEMORIAL CENTRAL SCHOOL | Row 13466 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0673 | 1 | 1381701006 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | San Roque | 14.5421 | 121.0707 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136895 | Paulina Manalo ES | Row 6995 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0674 | 1 | 0405641018 | Region IV-A (CALABARZON) | Quezon | San Antonio | Sampaguita | 13.8889 | 121.2865 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301385 | San Antonio NHS | Row 19487 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0675 | 1 | 0307103003 | Region III (Central Luzon) | Zambales | Candelaria | Catol | 15.621 | 119.9347 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106842 | Catol Elementary School | Row 15064 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0676 | 1 | 0201505002 | Region II (Cagayan Valley) | Cagayan | Aparri | Bangag | 18.2982 | 121.559 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102455 | Bangag Elementary School | Row 10378 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0677 | 1 | 0300811001 | Region III (Central Luzon) | Bataan | Pilar | Ala-uli | 14.6457 | 120.5386 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104688 | Alauli ES | Row 13031 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0678 | 1 | 1381300029 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Del Monte | 14.6445 | 121.0129 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136495 | Dalupan ES | Row 6625 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0679 | 1 | 1001309026 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Poblacion | 7.6342 | 125.0065 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 126475 | Kitaotao CES | Row 41056 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0680 | 1 | 0205006010 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Poblacion | 16.6604 | 121.3652 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104021 | Diadi CS | Row 11819 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0681 | 1 | 0600401009 | Region VI (Western Visayas) | Aklan | Altavas | Man-up | 11.5342 | 122.4758 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Man-up Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0682 | 1 | 0203131027 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone I | 16.9838 | 122.0098 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300592 | San Mariano National High School - Main | Row 12431 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0683 | 1 | 0506215013 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Roque | 12.6456 | 124.1051 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Roque Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0684 | 1 | 0603035039 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilawod | 11.1052 | 122.6427 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Ilawod Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0685 | 1 | 0405808011 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Rafael | 14.7325 | 121.1584 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 109464 | San Rafael ES - Casili ES | Row 18673 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0686 | 1 | 0300806015 | Region III (Central Luzon) | Bataan | Limay | St. Francis II | 14.5719 | 120.5924 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 306616 | St. Francis NHS | Row 16063 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0687 | 1 | 0405808001 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Balite | 14.7325 | 121.1445 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 109466 | Eulogio Rodriguez Jr. Elementary School | Row 18675 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0688 | 1 | 0306909012 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan West | 15.7204 | 120.5705 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106555 | Tagurarit ES | Row 14805 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0689 | 1 | 0403410018 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Palina | 14.134 | 121.4335 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108300 | Pag-asa Elementary School | Row 17552 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0690 | 1 | 1600308017 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 3 | 8.5072 | 125.9725 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 3 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0691 | 1 | 0702218007 | Region VII (Central Visayas) | Cebu | Compostela | Cogon | 10.4553 | 124.0092 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119226 | Compostela Central ES | Row 34094 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0692 | 1 | 0307106011 | Region III (Central Luzon) | Zambales | Masinloc | South Poblacion | 15.5343 | 119.95 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106893 | Masinloc Central Elementary School | Row 15109 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0693 | 1 | 0203137033 | Region II (Cagayan Valley) | Isabela | Tumauini | Namnama | 17.2908 | 121.8706 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103899 | Namnama Elementary School | Row 11704 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0694 | 1 | 0501718013 | Region V (Bicol Region) | Camarines Sur | Libmanan | Begajo Sur | 13.6955 | 123.0674 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112673 | Bigajo Sur Primary School | Row 26006 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0695 | 1 | 0500514014 | Region V (Bicol Region) | Albay | Polangui | Centro Oriental | 13.2948 | 123.4865 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 111995 | Polangui North Central School | Row 25356 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0696 | 1 | 0301420040 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan V | 14.8445 | 121.0802 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Minuyan V Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0697 | 1 | 0501723031 | Region V (Bicol Region) | Camarines Sur | Nabua | San Nicolas | 13.4038 | 123.3709 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112818 | Nabua East Central School (Pilot) | Row 26147 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0698 | 1 | 1402709008 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Piwong | 16.8456 | 121.0932 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135843 | Piwong ES | Row 3400 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0699 | 1 | 1600206001 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Bangayan | 9.3608 | 125.5528 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bangayan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0700 | 1 | 0603039024 | Region VI (Western Visayas) | Iloilo | San Enrique | Poblacion Ilaya | 11.0735 | 122.6593 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 116714 | San Enrique Central School | Row 30748 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0701 | 1 | 1102411007 | Region XI (Davao Region) | Davao del Sur | Padada | N C Ordaneza District | 6.638 | 125.3416 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129049 | Padada Central Elementary School | Row 44071 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0702 | 1 | 0405639013 | Region IV-A (CALABARZON) | Quezon | Sampaloc | Ilayang Owain | 14.1621 | 121.6414 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109087 | Sampaloc ES II (G-Hills) | Row 18309 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0703 | 1 | 0403418009 | Region IV-A (CALABARZON) | Laguna | Paete | Quinale | 14.3617 | 121.4834 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108377 | Quinale Elementary School | Row 17629 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0704 | 1 | 0506202018 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Central | 12.8664 | 124.1436 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 113982 | Barcelona Central School | Row 27248 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0705 | 1 | 0203101010 | Region II (Cagayan Valley) | Isabela | Alicia | Calaocan | 16.7814 | 121.6913 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103006 | Alicia West Central School | Row 10902 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0706 | 1 | 1004310011 | Region X (Northern Mindanao) | Misamis Oriental | Initao | Poblacion | 8.4975 | 124.3062 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127686 | Initao CS | Row 42062 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0707 | 1 | 0201525015 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Centro West | 18.2474 | 121.9073 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102934 | Sta. Teresita Central School | Row 10834 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0708 | 1 | 0203132002 | Region II (Cagayan Valley) | Isabela | San Mateo | Bagong Sikat | 16.8831 | 121.5878 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103768 | Bagong Sikat Elementary School - Main | Row 11584 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0709 | 1 | 0504101031 | Region V (Bicol Region) | Masbate | Aroroy | Poblacion | 12.5107 | 123.3952 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 113395 | Aroroy West ES | Row 26708 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1001 | 1 | 0600411015 | Region VI (Western Visayas) | Aklan | Makato | Poblacion | 11.7125 | 122.29 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500172 | Makato Integrated School | Row 32658 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0711 | 1 | 0506212012 | Region V (Bicol Region) | Sorsogon | Matnog | Caloocan | 12.5835 | 124.0838 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114322 | Matnog CS | Row 27577 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0712 | 1 | 0402109085 | Region IV-A (CALABARZON) | Cavite | City of Imus | Pasong Buaya II | 14.3899 | 120.9649 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 164003 | Pasong Buaya II ES | Row 19085 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0713 | 1 | 0501728005 | Region V (Bicol Region) | Camarines Sur | Pili | Cadlan | 13.5999 | 123.2539 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112917 | Agaton C. Rodriguez Elementary School | Row 26244 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0714 | 1 | 0702223040 | Region VII (Central Visayas) | Cebu | Danao City | Suba | 10.5245 | 124.0287 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119357 | Severo Duterte Memo. ES | Row 34206 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0715 | 1 | 1404409009 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Demang | 17.0843 | 120.8981 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 305265 | Sagada National High School (Brgy POBLACION (PATAY)) | Row 4280 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION (PATAY) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0716 | 1 | 0405622006 | Region IV-A (CALABARZON) | Quezon | Lopez | Gomez | 13.8861 | 122.2587 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108840 | Gomez Elementary School | Row 18069 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0717 | 1 | 0403411012 | Region IV-A (CALABARZON) | Laguna | Los Baños | San Antonio | 14.1768 | 121.2451 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108313 | San Antonio Elementary School | Row 17565 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0718 | 1 | 0203104007 | Region II (Cagayan Valley) | Isabela | Benito Soliven | District II | 16.9865 | 121.9588 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103102 | Benito Soliven Central School | Row 10986 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0719 | 1 | 0105544047 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion West | 15.928 | 120.8393 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 300365 | Umingan Central National High School | Row 9996 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0720 | 1 | 0304930042 | Region III (Central Luzon) | Nueva Ecija | Talavera | Pag-asa | 15.5846 | 120.9168 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 300864 | TALAVERA NATIONAL HIGH SCHOOL | Row 15786 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0721 | 1 | 0702218014 | Region VII (Central Visayas) | Cebu | Compostela | Poblacion | 10.456 | 124.0115 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 303063 | Compostela National High School(Day Class) | Row 35903 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0722 | 1 | 1004321015 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Taboc | 8.517 | 124.5762 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 304094 | Opol NSTS | Row 42850 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0723 | 1 | 0300804013 | Region III (Central Luzon) | Bataan | Dinalupihan | Happy Valley | 14.847 | 120.4009 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104576 | Happy Valley ES | Row 12931 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0724 | 1 | 0306917027 | Region III (Central Luzon) | Tarlac | Victoria | Santa Lucia | 15.5785 | 120.679 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106790 | Gabaldon ES | Row 15023 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0725 | 1 | 1380400017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Santolan | 14.6854 | 120.9589 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136833 | Santulan ES | Row 6942 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0726 | 1 | 0301419036 | Region III (Central Luzon) | Bulacan | San Ildefonso | Upig | 15.025 | 120.9922 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105064 | Upig Elementary School | Row 13386 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0727 | 1 | 0402103030 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban III | 14.4608 | 120.9644 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Aniban III Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0728 | 1 | 1208007005 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Banate | 6.4742 | 125.3216 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 130571 | Banate CES | Row 46188 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0729 | 1 | 0306903064 | Region III (Central Luzon) | Tarlac | Camiling | Surgui 2nd | 15.6761 | 120.4145 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 501938 | Surgui Integrated School | Row 16423 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0730 | 1 | 0102906037 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Isidro | 17.1882 | 120.446 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 100435 | Candon North Central School | Row 7801 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0731 | 1 | 1402709006 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Namulditan | 16.8426 | 121.0866 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135840 | Namulditan ES | Row 3397 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0732 | 1 | 0603027025 | Region VI (Western Visayas) | Iloilo | Lemery | San Jose Moto | 11.227 | 122.925 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Jose Moto Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-1003 | 1 | 0403416011 | Region IV-A (CALABARZON) | Laguna | Majayjay | Botocan | 14.1564 | 121.4907 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 108344 | Bakia-Botocan ES (Brgy BAKIA) | Row 17596 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BAKIA anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0734 | 1 | 0730600064 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag I | 10.2994 | 123.8956 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119874 | City Central ES | Row 34660 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0735 | 1 | 0506204009 | Region V (Bicol Region) | Sorsogon | Bulusan | Madlawon | 12.7606 | 124.1362 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302192 | Bulusan High School | Row 28409 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0736 | 1 | 0402103053 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu II | 14.4562 | 120.955 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107880 | Gov. P. F. Espiritu Elementary School | Row 17142 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0737 | 1 | 0105506013 | Region I (Ilocos Region) | Pangasinan | Asingan | Dupac | 16.0085 | 120.6684 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101721 | Asingan North CS | Row 8985 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0738 | 1 | 0301423020 | Region III (Central Luzon) | Bulacan | Santa Maria | San Vicente | 14.8095 | 121.0127 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105163 | San Vicente (Hulo) ES | Row 13484 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0739 | 1 | 0501701022 | Region V (Bicol Region) | Camarines Sur | Baao | San Ramon | 13.4545 | 123.3683 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112320 | Baao West CS | Row 25667 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0740 | 1 | 0702239010 | Region VII (Central Visayas) | Cebu | Ronda | Palanas | 9.9966 | 123.4094 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 119601 | Ronda Central ES | Row 34420 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0741 | 1 | 0201507008 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Centro East | 18.4099 | 121.5176 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 102536 | Ballesteros CS | Row 10455 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0742 | 1 | 0405628021 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ilayang Yuni | 13.4536 | 122.5231 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 301329 | Ilayang Yuni Junior and Senior Integrated NHS | Row 19433 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0743 | 1 | 0604509002 | Region VI (Western Visayas) | Negros Occidental | City of Escalante | Balintawak | 10.8394 | 123.4969 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117043 | Escalante Central Elementary School | Row 31057 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0744 | 1 | 0203112045 | Region II (Cagayan Valley) | Isabela | Echague | San Fabian | 16.7122 | 121.6819 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103290 | Echague East Central School | Row 11163 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0745 | 1 | 0402116007 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael II | 14.4314 | 120.8797 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108081 | Noveleta Elementary School | Row 17338 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0746 | 1 | 1130700137 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 4-A | 7.0707 | 125.6099 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129557 | Kapt. T. Monteverde Sr. CES | Row 44517 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0747 | 1 | 0300807013 | Region III (Central Luzon) | Bataan | Mariveles | Balon-Anito | 14.4365 | 120.4734 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104637 | Balon ES | Row 12984 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0748 | 1 | 1130700050 | Region XI (Davao Region) | Davao del Sur | City of Davao | Indangan | 7.1616 | 125.5957 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 129513 | Teofilo Fernandez ES | Row 44479 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0749 | 1 | 0803722021 | Region VIII (Eastern Visayas) | Leyte | Isabel | Santo Niño | 10.9285 | 124.4367 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 121443 | Isabel Central School | Row 37299 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0750 | 1 | 0907322039 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Francisco | 7.8272 | 123.4387 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126066 | Pablo Litigio Elementary School | Row 24145 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0751 | 1 | 0931700061 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Barangay Zone I | 6.907 | 122.0722 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 199006 | Zamboanga CS | Row 24475 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0752 | 1 | 0405807008 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Pagkalinawan | 14.3155 | 121.3391 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109454 | Pagkalinawan ES | Row 18663 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0753 | 1 | 1401110006 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Beckel | 16.4363 | 120.6316 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 135619 | Bekkel ES | Row 3198 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0754 | 1 | 0103306010 | Region I (Ilocos Region) | La Union | Bangar | General Prim East | 16.899 | 120.4387 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100896 | General Prim Elementary School (Brgy GENERAL PRIM WEST) | Row 8226 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay GENERAL PRIM WEST anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0755 | 1 | 0300808004 | Region III (Central Luzon) | Bataan | Morong | Poblacion | 14.6777 | 120.268 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104654 | Morong ES | Row 13000 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0756 | 1 | 0402106067 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres II | 14.3179 | 120.9525 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Andres II Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0757 | 1 | 0504101037 | Region V (Bicol Region) | Masbate | Aroroy | Talabaan | 12.5106 | 123.3951 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 305866 | Aroroy Stand Alone Senior High School | Row 28523 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0758 | 1 | 0304916007 | Region III (Central Luzon) | Nueva Ecija | Lupao | Bagong Flores | 15.8879 | 120.9 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105517 | Bagong Flores ES | Row 13816 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0759 | 1 | 1600314015 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Poblacion | 8.8236 | 125.6956 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0760 | 1 | 0704611028 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Poblacion | 10.1191 | 123.2689 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120267 | Guihulngan South CS | Row 35036 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0761 | 1 | 1403209016 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Malagnat | 17.6424 | 121.3897 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136050 | Malagnat Elementary School | Row 3598 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0762 | 1 | 0831600076 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 49 | 11.2398 | 124.9986 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 124256 | City Central School | Row 39992 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0763 | 1 | 0203136024 | Region II (Cagayan Valley) | Isabela | Santo Tomas | San Roque | 17.3876 | 121.7751 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103869 | San Roque Elementary School | Row 11678 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0764 | 1 | 1408103014 | Cordillera Administrative Region (CAR) | Apayao | Flora | Poblacion West | 18.214 | 121.4161 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135289 | Flora CS | Row 2913 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0765 | 1 | 0402106037 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas I | 14.3151 | 120.9685 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107919 | San Nicolas ES (Dasmariñas BBES D) | Row 17181 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0766 | 1 | 0105531033 | Region I (Ilocos Region) | Pangasinan | Rosales | Zone I | 15.8912 | 120.6312 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101883 | Rosales South CS | Row 9138 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0767 | 1 | 0105526013 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guiguilonen | 16.0702 | 120.4057 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Guiguilonen Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0768 | 1 | 0405814001 | Region IV-A (CALABARZON) | Rizal | Teresa | Bagumbayan | 14.5499 | 121.2184 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109346 | Bagumbayan Elementary School | Row 18561 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0769 | 1 | 1380500025 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | San Jose | 14.58 | 121.0292 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136657 | Filemon P. Javier Elementary School | Row 6779 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0770 | 1 | 1004303010 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | San Alonzo | 9.0037 | 124.8389 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127893 | San Alonzo ES | Row 42238 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0771 | 1 | 0300811006 | Region III (Central Luzon) | Bataan | Pilar | Balut II | 14.6866 | 120.5587 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 104690 | Balut ES (Brgy BALUT I) | Row 13033 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BALUT I anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0772 | 1 | 0300803017 | Region III (Central Luzon) | Bataan | City of Balanga | Sibacan | 14.687 | 120.5472 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104563 | M. P. Cuaderno Sr. Memorial Elementary School | Row 12922 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0773 | 1 | 0604520020 | Region VI (Western Visayas) | Negros Occidental | Murcia | Pandanon | 10.6067 | 123.0383 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Pandanon Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0774 | 1 | 0203115007 | Region II (Cagayan Valley) | Isabela | Jones | Barangay II | 16.554 | 121.7005 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 103470 | Jones West Central School-C2 | Row 11331 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0775 | 1 | 0702251007 | Region VII (Central Visayas) | Cebu | City of Toledo | Cabitoonan | 10.3526 | 123.6131 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120744 | Fulgencio Dolino ES | Row 35503 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0776 | 1 | 0306911010 | Region III (Central Luzon) | Tarlac | Pura | Nilasin 1st | 15.6247 | 120.6547 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106602 | Nilasin Ist ES | Row 14852 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0777 | 1 | 0604515025 | Region VI (Western Visayas) | Negros Occidental | City of Kabankalan | Barangay 4 | 9.9883 | 122.8158 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 4 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0778 | 1 | 0102808024 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Victoria | 17.9977 | 120.4999 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 150012 | Wilbur C. Go Elementary School | Row 9558 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0779 | 1 | 1381500003 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Bambang | 14.5118 | 121.0586 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 305463 | Signal Village National High School (Brgy SIGNAL VILLAGE) | Row 7217 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SIGNAL VILLAGE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0780 | 1 | 0405649028 | Region IV-A (CALABARZON) | Quezon | Unisan | R. Magsaysay | 13.8426 | 121.9783 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109305 | Santayana ES | Row 18521 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0781 | 1 | 0501709017 | Region V (Bicol Region) | Camarines Sur | Camaligan | Tarosanan | 13.6165 | 123.1703 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112503 | Tarosanan-San Francisco Elementary School | Row 25843 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0782 | 1 | 0405806027 | Region IV-A (CALABARZON) | Rizal | Cardona | San Roque | 14.4862 | 121.2265 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109417 | Mariano C. San Juan Elementary School | Row 18630 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0783 | 1 | 0201512021 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay III-A | 17.5592 | 121.6934 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 102634 | Enrile West CS | Row 10547 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0784 | 1 | 0501703030 | Region V (Bicol Region) | Camarines Sur | Bato | San Vicente | 13.3621 | 123.3668 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112385 | San Vicente ES | Row 25727 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0785 | 1 | 0306917024 | Region III (Central Luzon) | Tarlac | Victoria | San Nicolas | 15.5776 | 120.6812 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106797 | Victoria West CS | Row 15030 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0786 | 1 | 0205010016 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Pampang | 16.3578 | 120.8865 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104124 | Kayapa CS | Row 11915 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0787 | 1 | 0601916003 | Region VI (Western Visayas) | Capiz | Sigma | Balucuan | 11.4 | 122.6378 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Balucuan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0788 | 1 | 0704610029 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Taclobo | 9.3095 | 123.3037 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119940 | West City Exceptional Child Learning Center | Row 34711 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0789 | 1 | 1380200006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Pamplona Uno | 14.4581 | 120.97 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136787 | Pamplona Elementary School Central | Row 6897 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0790 | 1 | 1380500021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pag-asa | 14.5835 | 121.0339 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Pag-asa Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0791 | 1 | 0306914015 | Region III (Central Luzon) | Tarlac | San Manuel | Santa Maria | 15.798 | 120.6116 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106665 | Sta. Maria ES | Row 14907 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0792 | 1 | 0105522021 | Region I (Ilocos Region) | Pangasinan | Lingayen | Maniboc | 16.0194 | 120.2312 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101483 | Lingayen I CS | Row 8764 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0793 | 1 | 1705208044 | MIMAROPA Region | Oriental Mindoro | Naujan | Pinagsabangan II | 13.2674 | 121.2684 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110539 | Juan Luna MES | Row 20709 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0794 | 1 | 0631000024 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Buhang | 10.7494 | 122.5666 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117601 | M.V. Hechanova MES | Row 31594 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0795 | 1 | 1381701007 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | Santa Ana | 14.5466 | 121.0718 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136893 | Capt. Hipolito Francisco Elementary School - Main | Row 6993 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0796 | 1 | 0105508015 | Region I (Ilocos Region) | Pangasinan | Bani | Poblacion | 16.187 | 119.8595 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101229 | Bani West Central School | Row 8523 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0797 | 1 | 0307707007 | Region III (Central Luzon) | Aurora | Maria Aurora | Barangay III | 15.7972 | 121.4751 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104504 | Maria Aurora CS | Row 12871 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0798 | 1 | 0501608017 | Region V (Bicol Region) | Camarines Norte | Paracale | Mangkasay | 14.2554 | 122.8195 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112258 | Sta. Catalina Elementary School | Row 25608 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0799 | 1 | 0908316005 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | Libertad | 7.6027 | 122.4242 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 125909 | Tungawan Central Elementary School | Row 24012 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0800 | 1 | 0702220013 | Region VII (Central Visayas) | Cebu | Cordova | San Miguel | 10.2609 | 123.9437 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 137085 | San Miguel Primary School | Row 35524 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0801 | 1 | 0601914047 | Region VI (Western Visayas) | Capiz | City of Roxas | Tanque | 11.5874 | 122.752 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117661 | Pres. Manuel Roxas MS - North | Row 31650 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0802 | 1 | 1381100192 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 192 | 14.5332 | 121.0006 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136592 | Don Carlos Village ES (Brgy BARANGAY 187) | Row 6718 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BARANGAY 187 anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0803 | 1 | 0103314057 | Region I (Ilocos Region) | La Union | City of San Fernando | Sevilla | 16.6021 | 120.3216 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101035 | Sevilla Elementary School | Row 8348 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0804 | 1 | 0102930020 | Region I (Ilocos Region) | Ilocos Sur | Sinait | Macabiag | 17.8645 | 120.4566 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100653 | SINAIT WEST CS | Row 8002 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0805 | 1 | 0402110033 | Region IV-A (CALABARZON) | Cavite | Indang | Daine II | 14.1855 | 120.8459 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 108011 | Daine Elementary School (Brgy DAINE I) | Row 17269 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay DAINE I anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0806 | 1 | 0105539014 | Region I (Ilocos Region) | Pangasinan | Santa Maria | Poblacion East | 15.9806 | 120.7009 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500623 | Sta. Maria East Integrated School | Row 10198 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0807 | 1 | 0731300009 | Region VII (Central Visayas) | Cebu | City of Mandaue | Casuntingan | 10.3466 | 123.9408 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Casuntingan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0808 | 1 | 0600403015 | Region VI (Western Visayas) | Aklan | Banga | Mangan | 11.6293 | 122.3444 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114669 | Mangan ES | Row 28845 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0809 | 1 | 1381500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | South Daang Hari | 14.469 | 121.0499 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 136881 | Bagong Tanyag Elementary School - Annex A (Brgy BAGONG TANYAG) | Row 6984 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BAGONG TANYAG anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0810 | 1 | 0307103011 | Region III (Central Luzon) | Zambales | Candelaria | Pamibian | 15.6249 | 119.9363 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500127 | Pamibian Integrated School | Row 16272 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0811 | 1 | 0402116012 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose II | 14.4318 | 120.8864 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108084 | Ambrocio Robles Memorial Elementary School | Row 17341 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0812 | 1 | 0306904020 | Region III (Central Luzon) | Tarlac | Capas | Santo Domingo 2nd | 15.3434 | 120.5952 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106367 | Angelina Dizon Jimenez ES (Sto. Domingo ES) | Row 14629 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0813 | 1 | 0603043008 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Bantay | 10.8692 | 122.5409 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 302468 | Buayahon-Bantay NHS (Brgy BUAYAHON) | Row 32192 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BUAYAHON anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0814 | 1 | 1705209037 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Guinhawa | 13.0665 | 121.5033 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 110561 | Natividad De Joya MS | Row 20731 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0815 | 1 | 1380400019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Tinajeros | 14.6713 | 120.9699 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136850 | Tinajeros ES | Row 6957 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0816 | 1 | 0702222029 | Region VII (Central Visayas) | Cebu | Dalaguete | Poblacion | 9.7583 | 123.5338 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119298 | Dalaguete Central ES | Row 34159 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0817 | 1 | 0305406023 | Region III (Central Luzon) | Pampanga | Floridablanca | Poblacion | 14.9786 | 120.4998 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0818 | 1 | 0105526025 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Poblacion | 16.0703 | 120.4056 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 101815 | Mangaldan Central School | Row 9072 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0819 | 1 | 1030500018 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Barangay 22 | 8.4905 | 124.6538 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127955 | Corrales Elementary School | Row 42291 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0820 | 1 | 0301414008 | Region III (Central Luzon) | Bulacan | Obando | Paliwas | 14.7132 | 120.935 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104964 | Obando Central School | Row 13289 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0821 | 1 | 1380300004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Comembo | 14.5461 | 121.0645 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136692 | Comembo ES | Row 6807 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0822 | 1 | 0731300002 | Region VII (Central Visayas) | Cebu | City of Mandaue | Bakilid | 10.3387 | 123.9342 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 120008 | Bakilid ES | Row 34779 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0823 | 1 | 0402106049 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol III | 14.3244 | 120.9607 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 301186 | Dasmariñas Integrated High School (Brgy BUROL I) | Row 19292 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BUROL I anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0824 | 1 | 0402104014 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 3 | 14.3138 | 121.0535 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 3 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0825 | 1 | 0501703035 | Region V (Bicol Region) | Camarines Sur | Bato | Tres Reyes | 13.3544 | 123.3654 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112364 | Bato North Central School | Row 25709 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0826 | 1 | 0402120012 | Region IV-A (CALABARZON) | Cavite | Tanza | Mulawin | 14.3746 | 120.8542 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Mulawin Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0827 | 1 | 1630400086 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tiniwisan | 8.9472 | 125.5397 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Tiniwisan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0828 | 1 | 0402109004 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-A | 14.3877 | 120.9399 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107969 | Anabu II Elementary School | Row 17231 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0829 | 1 | 0306902005 | Region III (Central Luzon) | Tarlac | Bamban | Dela Cruz | 15.2798 | 120.5682 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106312 | Bamban CS | Row 14576 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0830 | 1 | 1001317019 | Region X (Northern Mindanao) | Bukidnon | Quezon | Merangerang | 7.7026 | 125.1135 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 303979 | Salawagan NHS (Brgy SALAWAGAN) | Row 42735 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SALAWAGAN anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0831 | 1 | 0702232010 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward I | 10.2443 | 123.7983 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119477 | Minglanilla Central ES | Row 34304 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0832 | 1 | 0402118020 | Region IV-A (CALABARZON) | Cavite | Silang | Lalaan II | 14.1581 | 120.9572 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108124 | Lalaan Central School | Row 17380 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0833 | 1 | 0102814009 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Poblacion | 17.9167 | 120.663 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100154 | Nueva Era Central Elementary School | Row 7531 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0834 | 1 | 0405623006 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 3 | 14.1171 | 121.55 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 108866 | Prlng. Elem. Ng Lucban 3A (Brgy AYUTI) | Row 18094 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay AYUTI anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0835 | 1 | 0307110009 | Region III (Central Luzon) | Zambales | San Felipe | San Rafael | 15.0576 | 120.0667 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106938 | San Rafael Elementary School | Row 15152 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0836 | 1 | 0603023020 | Region VI (Western Visayas) | Iloilo | Janiuay | Damo-ong | 10.9418 | 122.5157 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 116393 | Don Jose Locsin MES | Row 30449 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0837 | 1 | 0304923029 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion West | 15.7143 | 121.1016 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105654 | Rizal West Elementary School | Row 13939 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0838 | 1 | 0105530028 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Poblacion III | 16.113 | 120.545 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101860 | Pozorrubio Central School | Row 9115 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0839 | 1 | 0506209024 | Region V (Bicol Region) | Sorsogon | Irosin | San Julian | 12.7063 | 124.0344 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 114235 | Irosin Central School | Row 27495 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0840 | 1 | 0307701011 | Region III (Central Luzon) | Aurora | Baler | Sabang | 15.7599 | 121.5676 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 104416 | Ruperto P. Zubia, Sr. ES | Row 12787 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0841 | 1 | 0405625007 | Region IV-A (CALABARZON) | Quezon | Macalelon | Luctob | 13.7473 | 122.1323 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108878 | Macalelon CES Annex | Row 18106 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0842 | 1 | 0631000099 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Burgos-Mabini-Plaza | 10.7173 | 122.5656 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117605 | Graciano Lopez Jaena ES | Row 31598 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0843 | 1 | 0704610019 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Poblacion No. 1 | 9.3091 | 123.3044 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 119939 | West City Elementary School (Brgy POBLACION NO. 7 (BARANGAY 7)) | Row 34710 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION NO. 7 (BARANGAY 7) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0844 | 1 | 0331400016 | Region III (Central Luzon) | Zambales | City of Olongapo | New Kababae | 14.8315 | 120.2772 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500027 | James L. Gordon IS | Row 16261 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0845 | 1 | 0306913015 | Region III (Central Luzon) | Tarlac | San Clemente | Poblacion Sur | 15.7118 | 120.3605 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 501609 | San Clemente Central Integrated School | Row 16387 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0846 | 1 | 0105530010 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Cablong | 16.1145 | 120.5468 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 300287 | Benigno V. Aldana NHS | Row 9922 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0847 | 1 | 0908302029 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Datu Panas | 7.7369 | 123.0572 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Datu Panas Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0848 | 1 | 0307110007 | Region III (Central Luzon) | Zambales | San Felipe | Manglicmot | 15.0556 | 120.071 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106932 | Bobulon Elementary School | Row 15146 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0849 | 1 | 0402116002 | Region IV-A (CALABARZON) | Cavite | Noveleta | Poblacion | 14.4264 | 120.8802 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108080 | Gen. L. San Miguel Elementary School | Row 17337 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0850 | 1 | 0730600087 | Region VII (Central Visayas) | Cebu | City of Cebu | Zapatera | 10.3036 | 123.9021 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119931 | Zapatera ES (Night/Sped) | Row 34702 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0851 | 1 | 1004325015 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Santa Ines | 8.9688 | 124.9405 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127896 | Sta. Ines ES | Row 42240 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0852 | 1 | 1030500050 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Indahag | 8.4313 | 124.6703 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127945 | Kamakawan Elementary School | Row 42282 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0853 | 1 | 0203115006 | Region II (Cagayan Valley) | Isabela | Jones | Barangay I | 16.5614 | 121.7002 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103469 | Jones West Central School Campus 1 | Row 11330 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0854 | 1 | 1381300129 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Vasra | 14.6589 | 121.0466 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136508 | Mines Elementary School | Row 6638 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0855 | 1 | 0403417038 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Palina | 14.1411 | 121.4132 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 301276 | Talangan NHS (Brgy TALANGAN) | Row 19381 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay TALANGAN anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0856 | 1 | 1102411012 | Region XI (Davao Region) | Davao del Sur | Padada | Quirino District | 6.6444 | 125.3459 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Quirino District Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0857 | 1 | 0702205014 | Region VII (Central Visayas) | Cebu | Argao | Canbanua | 9.8848 | 123.5946 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 118923 | Canbanua ES | Row 33811 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0858 | 1 | 1108207013 | Region XI (Davao Region) | Davao de Oro | Monkayo | Poblacion | 7.8247 | 126.0529 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 128439 | Monkayo CES | Row 43515 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0859 | 1 | 0301421041 | Region III (Central Luzon) | Bulacan | San Miguel | Salangan | 15.1341 | 120.9593 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105099 | Dr. Juan F. Pascual MS | Row 13421 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0860 | 1 | 0405646034 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Isidro | 14.016 | 122.4656 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 109221 | San Isidro ES | Row 18440 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0861 | 1 | 0301420001 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay I | 14.8453 | 121.0483 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bagong Buhay I Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0862 | 1 | 0307104014 | Region III (Central Luzon) | Zambales | Castillejos | San Roque | 14.9297 | 120.2052 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106868 | Villaflor Elementary School | Row 15087 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0863 | 1 | 1380500024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Poblacion | 14.5865 | 121.0249 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136660 | Mandaluyong Elementary School | Row 6780 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0864 | 1 | 0103306013 | Region I (Ilocos Region) | La Union | Bangar | General Terrero | 16.897 | 120.423 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100906 | Ter-Con Elementary School | Row 8234 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0865 | 1 | 0631000016 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Banuyao | 10.7048 | 122.5624 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Banuyao Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0866 | 1 | 0300803001 | Region III (Central Luzon) | Bataan | City of Balanga | Bagumbayan | 14.6796 | 120.5464 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 305619 | Balanga City National Science High School | Row 16001 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0867 | 1 | 0304921013 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Sinasajan | 15.3494 | 121.0168 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105612 | Kapt. Pedro Villanueva Elementary School | Row 13901 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0868 | 1 | 1630400014 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Bading Pob. | 8.9469 | 125.5394 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bading Pob. Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0869 | 1 | 0501717029 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Isidro Norte | 13.7357 | 123.5201 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112660 | Lagonoy South Central School | Row 25993 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0870 | 1 | 0405607080 | Region IV-A (CALABARZON) | Quezon | Calauag | Sumulong | 13.959 | 122.3313 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108612 | Sumulong ES | Row 17854 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0871 | 1 | 0305415002 | Region III (Central Luzon) | Pampanga | Porac | Babo Sacan | 15.0683 | 120.5428 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106213 | Babo Sacan ES | Row 14482 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0872 | 1 | 0403416037 | Region IV-A (CALABARZON) | Laguna | Majayjay | Santa Catalina | 14.1472 | 121.4711 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108349 | Santa Catalina Elementary School | Row 17601 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0873 | 1 | 0401007019 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Dacanlao | 13.9393 | 120.7917 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107292 | Dacanlao G. Agoncillo Elementary School | Row 16575 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0874 | 1 | 0501606009 | Region V (Bicol Region) | Camarines Norte | Labo | Bayabas | 14.1859 | 122.4694 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112201 | Bayabas Elementary School | Row 25557 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0875 | 1 | 0405615004 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin I | 14.0171 | 121.3862 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108674 | Bulakin ES | Row 17915 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0876 | 1 | 1600210008 | Region XIII (Caraga) | Agusan del Norte | Santiago | San Isidro | 9.1576 | 125.5608 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Isidro Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0877 | 1 | 1004311014 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Upper Jasaan | 8.6541 | 124.7541 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 127705 | Jasaan CS | Row 42079 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0878 | 1 | 0601916019 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Norte | 11.4236 | 122.6644 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Norte Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0879 | 1 | 0105519014 | Region I (Ilocos Region) | Pangasinan | Dasol | Poblacion | 15.9898 | 119.8798 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500441 | Dasol Integrated School | Row 10155 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0880 | 1 | 0102928008 | Region I (Ilocos Region) | Ilocos Sur | Santo Domingo | Camestizoan | 17.6387 | 120.4107 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100740 | Sto. Domingo North Central School (Brgy SAN PABLO) | Row 8086 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAN PABLO anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0881 | 1 | 0205007013 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Malasin | 16.3071 | 121.1053 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104042 | Dupax del Norte CS | Row 11839 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0882 | 1 | 0604520025 | Region VI (Western Visayas) | Negros Occidental | Murcia | Talotog | 10.6204 | 123.0644 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 180516 | Smile Village ES (Brgy BLUMENTRITT) | Row 31984 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BLUMENTRITT anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0883 | 1 | 0306909011 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan East | 15.7264 | 120.5717 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106547 | Camangaan PS | Row 14797 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0884 | 1 | 0702235020 | Region VII (Central Visayas) | Cebu | Oslob | Poblacion | 9.5247 | 123.4339 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119538 | Oslob Central ES | Row 34359 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0885 | 1 | 0305415018 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Paralaya | 15.1151 | 120.5671 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106222 | Manibaug Paralaya ES | Row 14491 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0886 | 1 | 0702220002 | Region VII (Central Visayas) | Cebu | Cordova | Bangbang | 10.2589 | 123.9444 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119252 | Bangbang ES | Row 34117 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0887 | 1 | 0401014054 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Sabang | 13.9459 | 121.1706 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 500781 | Gaudencio B. Lontok Memorial Integrated School | Row 19984 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0888 | 1 | 0304913020 | Region III (Central Luzon) | Nueva Ecija | Laur | San Juan | 15.5705 | 121.2031 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105474 | San Juan ES | Row 13775 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0889 | 1 | 0405804028 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pila Pila | 14.4483 | 121.2079 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109371 | Pilapila Elementary School | Row 18585 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0890 | 1 | 0307103015 | Region III (Central Luzon) | Zambales | Candelaria | Poblacion | 15.6275 | 119.9304 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106841 | Candelaria Central School | Row 15063 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0891 | 1 | 0205005016 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | District III Pob. | 16.483 | 121.1515 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved District III Pob. Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0892 | 1 | 0501719016 | Region V (Bicol Region) | Camarines Sur | Lupi | Colacling | 13.7741 | 122.8726 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 112740 | Colacling ES | Row 26072 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0893 | 1 | 0803740050 | Region VIII (Eastern Visayas) | Leyte | Palompon | Pinagdait Pob. | 11.0485 | 124.3829 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 121807 | Seaside Elementary School | Row 37661 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0894 | 1 | 0402103068 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba IV | 14.4612 | 120.9602 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107890 | Talaba Elementary School | Row 17152 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0895 | 1 | 0403425020 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Sampaguita Village | 14.3442 | 121.0358 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108429 | Sampaguita Village ES | Row 17680 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0896 | 1 | 1430300036 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Fairview Village | 16.4159 | 120.5837 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 221506 | Fairview Elementary School | Row 4090 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0897 | 1 | 0702219009 | Region VII (Central Visayas) | Cebu | Consolacion | Nangka | 10.3721 | 123.9591 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119244 | Nangka ES | Row 34109 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0898 | 1 | 0500508013 | Region V (Bicol Region) | Albay | City of Ligao | Binatagan | 13.2412 | 123.5312 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111844 | Ligao West CES (Binatagan) | Row 25207 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0899 | 1 | 1380400002 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Baritan | 14.6717 | 120.9493 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136840 | Amang Rodriguez ES | Row 6948 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0900 | 1 | 0306911013 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 2 | 15.6241 | 120.6486 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion 2 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0901 | 1 | 1402701023 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Tam-an | 16.9068 | 121.0628 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135829 | Tam-an ES | Row 3387 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0902 | 1 | 0102905033 | Region I (Ilocos Region) | Ilocos Sur | Cabugao | Turod-Patac | 17.7889 | 120.458 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100403 | Cabugao South Central School (Brgy BONIFACIO (POB.)) | Row 7769 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BONIFACIO (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0903 | 1 | 0500514022 | Region V (Bicol Region) | Albay | Polangui | Itaran | 13.3295 | 123.5164 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111984 | Itaran Elementary School | Row 25345 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0904 | 1 | 1004320008 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Poblacion | 8.4326 | 124.2948 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 127935 | Naawan CS | Row 42272 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0905 | 1 | 0103307033 | Region I (Ilocos Region) | La Union | Bauang | Quinavite | 16.5378 | 120.3295 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 151002 | Quinavite Elementary School | Row 9591 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0906 | 1 | 0500516022 | Region V (Bicol Region) | Albay | Santo Domingo | San Roque | 13.2534 | 123.768 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 112051 | Bagong San Roque Elementary School (Brgy BAGONG SAN ROQUE) | Row 25411 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BAGONG SAN ROQUE anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0907 | 1 | 0304924017 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Tikiw | 15.3105 | 120.8623 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105678 | Tikiw ES | Row 13963 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0908 | 1 | 0405812020 | Region IV-A (CALABARZON) | Rizal | Tanay | Wawa | 14.4928 | 121.285 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109527 | Wawa Elementary School | Row 18733 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0909 | 1 | 1381300141 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Greater Lagro | 14.7306 | 121.0662 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136534 | Lagro ES | Row 6664 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0910 | 1 | 0704619020 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion III | 9.0597 | 123.0357 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 303268 | Siaton NHS | Row 36103 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0911 | 1 | 0603034021 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion North | 10.6908 | 122.4842 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302542 | Oton National High School | Row 32266 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0912 | 1 | 0501730037 | Region V (Bicol Region) | Camarines Sur | Ragay | F. Simeon | 13.8445 | 122.701 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 112968 | Pugod ES | Row 26294 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0913 | 1 | 0501706021 | Region V (Bicol Region) | Camarines Sur | Bula | Sagrada | 13.4759 | 123.2799 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 301947 | Bula National High School | Row 28173 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0914 | 1 | 0702220011 | Region VII (Central Visayas) | Cebu | Cordova | Pilipog | 10.2663 | 123.9462 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119260 | Pilipog ES | Row 34124 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0915 | 1 | 0402103009 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Kaingin | 14.4416 | 120.9718 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Kaingin Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0916 | 1 | 1430300026 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cresencia Village | 16.4196 | 120.588 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 136393 | Bonifacio Elementary school | Row 3921 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0917 | 1 | 0304932021 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Rafael | 15.454 | 120.794 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | Row 15793 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0918 | 1 | 0402109047 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VIII | 14.4073 | 120.936 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107971 | Bayan Luma II Elementary School | Row 17233 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0919 | 1 | 1705204012 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Poblacion | 12.3264 | 121.3421 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 110414 | Bulalacao CS | Row 20586 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0920 | 1 | 0403425016 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Vicente | 14.3415 | 121.0438 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108419 | Chrysanthemum Village Elementary School | Row 17670 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0921 | 1 | 0403404013 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pulo | 14.2423 | 121.1318 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108249 | Pulo ES | Row 17501 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0922 | 1 | 0403426014 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay I | 14.2788 | 121.4177 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108446 | Santa Cruz CES | Row 17697 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0923 | 1 | 0501707001 | Region V (Bicol Region) | Camarines Sur | Cabusao | Barcelonita | 13.7722 | 123.0446 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112456 | Barcelonita Elementary School | Row 25796 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0924 | 1 | 0305413032 | Region III (Central Luzon) | Pampanga | Mexico | San Lorenzo | 15.0682 | 120.7374 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106193 | San Lorenzo ES | Row 14462 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0925 | 1 | 0702219002 | Region VII (Central Visayas) | Cebu | Consolacion | Cansaga | 10.3788 | 123.9627 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 119236 | Cansaga ES | Row 34101 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0926 | 1 | 0403405032 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mayapa | 14.2113 | 121.1273 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109854 | Mayapa Elementary School | Row 19043 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0927 | 1 | 0500514013 | Region V (Bicol Region) | Albay | Polangui | Centro Occidental | 13.2965 | 123.4865 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301865 | Polangui General Comprehensive High School | Row 28092 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0928 | 1 | 0305406026 | Region III (Central Luzon) | Pampanga | Floridablanca | San Jose | 14.9853 | 120.511 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105993 | San Jose ES | Row 14264 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0929 | 1 | 0405804002 | Region IV-A (CALABARZON) | Rizal | Binangonan | Batingan | 14.4726 | 121.1968 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 301455 | Rizal National Science High School | Row 19556 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0930 | 1 | 0306914002 | Region III (Central Luzon) | Tarlac | San Manuel | Lanat | 15.7923 | 120.6061 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 106661 | San Manuel ES | Row 14903 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0931 | 1 | 1001305013 | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Poblacion | 8.3065 | 125.002 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 126378 | Impasugong CES | Row 40964 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0932 | 1 | 0600413022 | Region VI (Western Visayas) | Aklan | Malinao | Tambuan | 11.6252 | 122.3008 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114876 | Tambuan Elementary School | Row 29029 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0933 | 1 | 0405801010 | Region IV-A (CALABARZON) | Rizal | Angono | San Pedro | 14.5296 | 121.1537 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Pedro Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0934 | 1 | 0402104019 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 8 | 14.3137 | 121.0538 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107894 | Carmona Elementary School | Row 17156 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0935 | 1 | 0500506011 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 15 - Ilawod East Pob. | 13.1488 | 123.7527 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 114479 | Ibalon Central School (Brgy BGY. 34 - ORO SITE-MAGALLANES ST. (POB.)) | Row 27726 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BGY. 34 - ORO SITE-MAGALLANES ST. (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0936 | 1 | 0604527005 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 5 | 9.7526 | 122.4009 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 117350 | Barangay V ES | Row 31354 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0937 | 1 | 0102933025 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Las-ud | 16.939 | 120.4408 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100772 | Las-ud Elementary School | Row 8114 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0938 | 1 | 0306905032 | Region III (Central Luzon) | Tarlac | Concepcion | San Jose | 15.3264 | 120.6605 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 106411 | San Jose ES | Row 14670 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0939 | 1 | 0105531036 | Region I (Ilocos Region) | Pangasinan | Rosales | Don Antonio Village | 15.8915 | 120.6272 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 300341 | Rosales NHS | Row 9972 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0940 | 1 | 1380900013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Tangos South | 14.6582 | 120.9484 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Tangos South Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0941 | 1 | 0105523007 | Region I (Ilocos Region) | Pangasinan | Mabini | Cabinuangan | 16.0817 | 119.9226 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 101517 | Cabinuangan ES | Row 8793 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0942 | 1 | 1600301016 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Poblacion | 8.7144 | 125.7519 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0943 | 1 | 1102401023 | Region XI (Davao Region) | Davao del Sur | Bansalan | Tubod | 6.792 | 125.2119 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 128836 | Villa Doneza Central Elementary School | Row 43867 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0944 | 1 | 0103306005 | Region I (Ilocos Region) | La Union | Bangar | Bangaoilan West | 16.9001 | 120.4476 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 100892 | Bangaoilan ES (Brgy BANGAOILAN EAST) | Row 8222 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay BANGAOILAN EAST anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0945 | 1 | 0501603030 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VII | 14.1164 | 122.958 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112134 | Daet Elementary School | Row 25491 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0946 | 1 | 0301423025 | Region III (Central Luzon) | Bulacan | Santa Maria | Tumana | 14.8131 | 120.9736 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 105170 | Tumana ES | Row 13491 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0947 | 1 | 0403406015 | Region IV-A (CALABARZON) | Laguna | Calauan | Prinza | 14.1424 | 121.3168 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108265 | Prinza ES | Row 17517 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0948 | 1 | 1130700158 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 25-C | 7.0865 | 125.6131 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 25-C Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0949 | 1 | 0506208033 | Region V (Bicol Region) | Sorsogon | Gubat | Pinontingan | 12.9191 | 124.1257 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114192 | Gubat North CS | Row 27453 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0950 | 1 | 0631000040 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Cuartero | 10.7236 | 122.5547 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117598 | Jaro II Elementary School (Cuartero Campus) | Row 31592 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0951 | 1 | 0203126016 | Region II (Cagayan Valley) | Isabela | Roxas | Rang-ayan | 17.1159 | 121.6249 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Rang-ayan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0952 | 1 | 1380400016 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | San Agustin | 14.6622 | 120.9525 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136843 | Dela Paz ES | Row 6950 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0953 | 1 | 0501702013 | Region V (Bicol Region) | Camarines Sur | Balatan | Siramag | 13.3185 | 123.2398 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112344 | Balatan CS | Row 25690 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0954 | 1 | 1102403029 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 2 | 6.7505 | 125.3573 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 304400 | Digos City NHS (Davao Del Sur NHS) | Row 45172 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0955 | 1 | 0600401011 | Region VI (Western Visayas) | Aklan | Altavas | Poblacion | 11.535 | 122.4913 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 302286 | Altavas National School | Row 32014 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0956 | 1 | 0402103002 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban I | 14.461 | 120.9641 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Aniban I Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0957 | 1 | 0402106027 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Dionisio | 14.32 | 120.9566 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Dionisio Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0958 | 1 | 0301411003 | Region III (Central Luzon) | Bulacan | Marilao | Ibayo | 14.753 | 120.9597 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104903 | Ibayo Elementary School | Row 13235 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0959 | 1 | 0501606051 | Region V (Bicol Region) | Camarines Norte | Labo | Talobatib | 14.1816 | 122.7854 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112205 | Claudio Villagen Elementary School | Row 25560 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0960 | 1 | 0405615016 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin II | 14.0169 | 121.3863 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Bulakin II Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0961 | 1 | 0405809004 | Region IV-A (CALABARZON) | Rizal | Morong | Maybancal | 14.5251 | 121.2424 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 109436 | Maybancal ES | Row 18645 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0962 | 1 | 0402120005 | Region IV-A (CALABARZON) | Cavite | Tanza | Bucal | 14.3903 | 120.8622 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108169 | Sta. Cruz Bucal Elementary School | Row 17423 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0963 | 1 | 0501605012 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Parang | 14.2814 | 122.6941 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 112155 | Parang Elementary School | Row 25511 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0964 | 1 | 0908305023 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Poblacion | 7.7802 | 122.5881 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 125617 | Ipil Central Elementary School | Row 23723 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0965 | 1 | 1001321022 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Nabago | 7.9094 | 125.094 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 303988 | Valencia NHS (Brgy POBLACION) | Row 42744 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay POBLACION anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0966 | 1 | 0405809006 | Region IV-A (CALABARZON) | Rizal | Morong | San Jose | 14.525 | 121.2425 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved San Jose Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0967 | 1 | 1206312014 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Poblacion | 6.2184 | 125.0694 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 130737 | Eugenio Llido Rañada Elementary School | Row 46306 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0968 | 1 | 0604528041 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 2 | 10.7438 | 122.9641 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Zone 2 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0969 | 1 | 0402109003 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-A | 14.4023 | 120.9405 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 107968 | Anabu I ES | Row 17230 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0970 | 1 | 0631000032 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Calumpang | 10.687 | 122.5398 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 117620 | Esteban Juntado Sr. Memorial Elem. School | Row 31612 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0971 | 1 | 0301412008 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Hulo | 14.7327 | 120.9569 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 501138 | Meycauayan West Central Integrated School (Brgy SAINT FRANCIS (GASAK)) | Row 16355 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAINT FRANCIS (GASAK) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0972 | 1 | 0305416010 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dolores | 15.0361 | 120.6827 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 345268 | Dolores Stand Alone Senior High School | Row 16250 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0973 | 1 | 1381300084 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Project 6 | 14.6626 | 121.0399 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136509 | Project 6 ES | Row 6639 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0974 | 1 | 0102805044 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Tabug | 18.0543 | 120.5566 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100075 | Catalino Acosta Mem. ES, Special Education Center | Row 7452 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0975 | 1 | 1408107013 | Cordillera Administrative Region (CAR) | Apayao | Santa Marcela | San Carlos | 18.2913 | 121.436 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 135368 | Santa Marcela West Central ES | Row 2986 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0976 | 1 | 0301403005 | Region III (Central Luzon) | Bulacan | Baliuag | Concepcion | 14.9527 | 120.8889 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 104752 | Concepcion ES | Row 13092 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0977 | 1 | 0402113002 | Region IV-A (CALABARZON) | Cavite | Maragondon | Bucal I | 14.2729 | 120.7412 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108038 | Bucal I Elementary School | Row 17296 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0978 | 1 | 0203126025 | Region II (Cagayan Valley) | Isabela | Roxas | Sotero Nuesa | 17.1204 | 121.6137 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 103642 | Nuesa Elementary School | Row 11483 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0979 | 1 | 0403428018 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pulong Santa Cruz | 14.28 | 121.0855 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 108479 | Pulong Sta. Cruz Elementary School | Row 17730 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0980 | 1 | 0105520012 | Region I (Ilocos Region) | Pangasinan | Infanta | Poblacion | 15.8224 | 119.9069 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 500614 | Infanta Integrated School | Row 10189 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0981 | 1 | 0403425004 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | G.S.I.S. | 14.3414 | 121.0439 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved G.S.I.S. Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0982 | 1 | 0102822020 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Santa Ana | 18.1 | 120.7667 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100286 | Sta. Ana ES | Row 7658 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0983 | 1 | 0803738062 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Macabug | 10.9583 | 124.653 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 124161 | Macabug Elementary School | Row 39903 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0984 | 1 | 1381300067 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Milagrosa | 14.6218 | 121.0682 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 136564 | Pura V. Kalaw ES | Row 6692 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0985 | 1 | 0704623008 | Region VII (Central Visayas) | Negros Oriental | Valencia | Bong-ao | 9.2789 | 123.2487 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Parenthetical Barangay Alias) | 120609 | Bong-ao Elementary School | Row 35374 | Validated (Administrative Alias) | Nominal demand centroid anchored on verified school under parenthetical administrative alias; field survey Candidates A/B/C within search ring during TSSR.
FWA-SITE-0986 | 1 | 0501720010 | Region V (Bicol Region) | Camarines Sur | Magarao | San Juan | 13.6624 | 123.1895 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 302034 | Magarao National High School, Magarao (Brgy SAN ISIDRO (POB.)) | Row 28258 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SAN ISIDRO (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0987 | 1 | 1004311009 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Natubo | 8.6573 | 124.7536 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 304073 | Jasaan NHS (Brgy UPPER JASAAN (POB.)) | Row 42829 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay UPPER JASAAN (POB.) anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1011 | 1 | 0102804012 | Region I (Ilocos Region) | Ilocos Norte | Bangui | San Lorenzo | 18.5383 | 120.7636 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 100047 | Bangui CES | Row 7424 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0989 | 1 | 0506215002 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Peñafrancia | 12.6354 | 124.0936 | 1,000m (Rural/Remote) | Contiguous Settlement Cluster School Anchor | 114417 | Uson ES (Brgy PEÃ‘AFRANCIA) | Row 27669 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay PEÃ‘AFRANCIA anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0990 | 1 | 0402104017 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 6 | 14.3139 | 121.054 | 1,000m (Rural/Remote) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Barangay 6 Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0991 | 1 | 1381300110 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Santol | 14.6126 | 121.0154 | 500m (Urban/Suburban) | DepEd Ground-Truth Anchor (Exact School Match) | 305355 | Carlos L. Albert HS | Row 7113 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0992 | 1 | 0105535018 | Region I (Ilocos Region) | Pangasinan | San Manuel | Sto. Domingo | 16.0712 | 120.6397 | 500m (Urban/Suburban) | Contiguous Settlement Cluster School Anchor | 152003 | Silsilay ES (Brgy SANTO DOMINGO) | Row 9623 | Validated (Contiguous Cluster Anchor) | Verified DepEd school campus in adjacent Barangay SANTO DOMINGO anchoring contiguous settlement cluster (coordinates exact to < 1m); field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0993 | 1 | 0603035040 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilaya | 11.1093 | 122.6436 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Poblacion Ilaya Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0994 | 1 | 1381200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Kapasigan | 14.567 | 121.0845 | 500m (Urban/Suburban) | Approved Settlement Demand Proxy (Town Center / Population Centroid) | N/A (Settlement Centroid Proxy) | Approved Kapasigan Settlement Demand Centroid (Non-School Core) | N/A (Approved Demographic Population Centroid) | Settlement Centroid Proxy (Approved RFP Baseline) | Approved settlement demand centroid for household population cluster coverage; field teams survey Candidates A/B/C within designated search ring (500m urban / 1,000m rural) during Milestone 1 TSSR.
FWA-SITE-0995 | 1 | 0501731017 | Region V (Bicol Region) | Camarines Sur | Sagñay | San Isidro | 13.6054 | 123.5246 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 112989 | Sagñay CS | Row 26315 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0996 | 1 | 0401008018 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 3 | 13.8322 | 120.6343 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 107319 | Jacobo Zobel Elementary School | Row 16601 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0997 | 1 | 0500517040 | Region V (Bicol Region) | Albay | City of Tabaco | San Ramon | 13.3479 | 123.7313 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 114622 | San Ramon ES | Row 27860 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0998 | 1 | 0304906044 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | San Jose | 15.7781 | 120.6691 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 105291 | San Jose ES | Row 13607 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-0999 | 1 | 0500510021 | Region V (Bicol Region) | Albay | Malinao | Poblacion | 13.3977 | 123.7059 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 111877 | Malinao Central School | Row 25239 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.
FWA-SITE-1000 | 1 | 0405625023 | Region IV-A (CALABARZON) | Quezon | Macalelon | San Isidro | 13.75 | 122.1333 | 1,000m (Rural/Remote) | DepEd Ground-Truth Anchor (Exact School Match) | 108884 | San Isidro Elementary School | Row 18112 | Validated (DepEd Ground-Truth) | Nominal demand centroid anchored on verified DepEd school campus; field teams survey Candidates A/B/C within designated search ring during TSSR.

## All 5,000 Sites
5G FWA Barangay Rollout Plan — Master Rollout Schedule (All 5,000 Sites)
28-Column Consolidated Candidate Siting & Rollout Schedule ¦ Verified DepEd Siting Anchors & Nearest TowerCo Coordinates ¦ Zero Duplicate Coordinates
Site ID | Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Households | Target Subscribers | Carrier Spectrum | Initial BTS | Civil Siting Category | Tower Screening Class | Nearest Tower ID | Nearest TowerCo | Nearest Tower Latitude | Nearest Tower Longitude | Dist to Tower (km) | Transmission Medium | Dist to Node (km) | Dist to Line (km) | Power Arrangement
FWA-SITE-0001 | 1 | 1 | 1 | 0501705020 | Region V (Bicol Region) | Camarines Sur | Buhi | Sagrada Familia | 13.416 | 123.5142 | R | 4566 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.6 | Terrestrial Optical Fiber Drop | 0.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0002 | 1 | 2 | 2 | 0401024016 | Region IV-A (CALABARZON) | Batangas | San Luis | Muzon | 13.8594 | 120.9871 | R | 2280 | 633 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1310 | FTAP Smart | 13.8604 | 120.9908 | 0.42 | Terrestrial Optical Fiber Drop | 0.03 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0003 | 1 | 3 | 3 | 0405803001 | Region IV-A (CALABARZON) | Rizal | Baras | Evangelista | 14.517 | 121.2766 | R | 4064 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00855-A04 | PTCI/MIDC | 14.5166 | 121.2786 | 0.22 | Terrestrial Optical Fiber Drop | 0.03 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0004 | 1 | 4 | 4 | 0401032019 | Region IV-A (CALABARZON) | Batangas | Taysan | Santo Niño | 13.7571 | 121.21 | R | 2588 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040579 | FTAP Globe | 13.7584 | 121.2072 | 0.33 | Terrestrial Optical Fiber Drop | 0.03 | 9.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0005 | 1 | 5 | 5 | 0102933035 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Quirino | 16.937 | 120.4448 | R | 679 | 178 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.5 | Terrestrial Optical Fiber Drop | 0.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0006 | 1 | 6 | 6 | 1030500063 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Puerto | 8.4993 | 124.7484 | U | 13413 | 3725 | 1118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0035 | PTCI/MIDC | 8.4944 | 124.7476 | 0.55 | Terrestrial Optical Fiber Drop | 0.03 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0007 | 1 | 7 | 7 | 0600403019 | Region VI (Western Visayas) | Aklan | Banga | Poblacion | 11.6975 | 122.3674 | U | 1923 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0005 | PTCI/MIDC | 11.6975 | 122.3768 | 1.02 | Terrestrial Optical Fiber Drop | 0.04 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0008 | 1 | 8 | 8 | 0500508037 | Region V (Bicol Region) | Albay | City of Ligao | Paulba | 13.1838 | 123.4585 | R | 2511 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050165 | FTAP Globe | 13.1979 | 123.4637 | 1.66 | Terrestrial Optical Fiber Drop | 0.04 | 9.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0009 | 1 | 9 | 9 | 0701242002 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Booy | 9.6572 | 123.8505 | U | 10128 | 2532 | 760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070149 | FTAP BTS | 9.658 | 123.8482 | 0.27 | Terrestrial Optical Fiber Drop | 0.04 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1004 | 1 | 10 | 10 | 0300804040 | Region III (Central Luzon) | Bataan | Dinalupihan | Santa Isabel | 14.8599 | 120.4714 | U | 2819 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-02568 | Edgepoint | 14.8582 | 120.4764 | 0.57 | Terrestrial Optical Fiber Drop | 0.54 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0011 | 1 | 11 | 11 | 0105521010 | Region I (Ilocos Region) | Pangasinan | Labrador | Uyong | 16.05 | 120.1208 | R | 2852 | 792 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00427 | Edgepoint | 16.053 | 120.1143 | 0.77 | Terrestrial Optical Fiber Drop | 0.05 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0012 | 1 | 12 | 12 | 0401015026 | Region IV-A (CALABARZON) | Batangas | Lobo | Poblacion | 13.6479 | 121.209 | U | 2733 | 759 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040611 | FTAP Globe | 13.6478 | 121.2124 | 0.37 | Terrestrial Optical Fiber Drop | 0.05 | 19.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0013 | 1 | 13 | 13 | 1705210010 | MIMAROPA Region | Oriental Mindoro | Pola | Casiligan | 13.1177 | 121.4251 | R | 1764 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170090 | FTAP Globe | 13.0951 | 121.4229 | 2.52 | Terrestrial Optical Fiber Drop | 0.05 | 6.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0014 | 1 | 14 | 14 | 0304909010 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Mag-asawang Sampaloc | 15.5922 | 121.052 | R | 1355 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0050 | PTCI/MIDC | 15.5844 | 121.051 | 0.87 | Terrestrial Optical Fiber Drop | 0.05 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0015 | 1 | 15 | 15 | 1731500010 | MIMAROPA Region | Palawan | City of Puerto Princesa | Binduyan | 10.0141 | 119.071 | R | 1565 | 422 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170230 | FTAP Globe | 9.9965 | 118.9862 | 9.49 | Terrestrial Optical Fiber Drop | 0.05 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0016 | 1 | 16 | 16 | 0403403003 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Tomas | 14.3113 | 121.0635 | U | 61000 | 18484 | 5545 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.59 | Terrestrial Optical Fiber Drop | 0.06 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0017 | 1 | 17 | 17 | 0300805024 | Region III (Central Luzon) | Bataan | Hermosa | Judge Roman Cruz Sr. | 14.8341 | 120.4884 | R | 4747 | 1318 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0015 | PTCI/MIDC | 14.8323 | 120.4895 | 0.24 | Terrestrial Optical Fiber Drop | 0.06 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0018 | 1 | 18 | 18 | 0307114014 | Region III (Central Luzon) | Zambales | Subic | Mangan-Vaca | 14.8886 | 120.2376 | U | 14223 | 3742 | 1123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01065 | Edgepoint | 14.8869 | 120.2347 | 0.36 | Terrestrial Optical Fiber Drop | 0.06 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0019 | 1 | 19 | 19 | 0600415013 | Region VI (Western Visayas) | Aklan | New Washington | Poblacion | 11.6482 | 122.434 | U | 6291 | 1613 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 4.06 | Terrestrial Optical Fiber Drop | 0.06 | 7.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0020 | 1 | 20 | 20 | 0501707006 | Region V (Bicol Region) | Camarines Sur | Cabusao | New Poblacion | 13.7265 | 123.1135 | R | 1301 | 309 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050057 | FTAP Globe | 13.7244 | 123.1076 | 0.69 | Terrestrial Optical Fiber Drop | 0.06 | 9.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0021 | 1 | 21 | 21 | 0501601025 | Region V (Bicol Region) | Camarines Norte | Basud | San Felipe | 14.0124 | 122.9305 | R | 3833 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03181-C10 | PTCI/MIDC | 14.0036 | 122.9312 | 0.97 | Terrestrial Optical Fiber Drop | 0.06 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0022 | 1 | 22 | 22 | 1606807004 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Baybay | 9.4195 | 125.8877 | R | 1661 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130055 | FTAP Globe | 9.3679 | 125.9511 | 0.22 | Terrestrial Optical Fiber Drop | 8.8 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0023 | 1 | 23 | 23 | 0401027002 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Bihis | 13.8777 | 120.9665 | R | 1597 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040533 | FTAP Globe | 13.8691 | 120.9761 | 1.41 | Terrestrial Optical Fiber Drop | 0.06 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0024 | 1 | 24 | 24 | 0403407003 | Region IV-A (CALABARZON) | Laguna | Cavinti | Bukal | 14.2385 | 121.5444 | R | 1384 | 419 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040203 | FTAP Globe | 14.2731 | 121.546 | 3.85 | Terrestrial Optical Fiber Drop | 0.06 | 10.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0025 | 1 | 25 | 25 | 0304901005 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Bucot | 15.5025 | 120.8716 | U | 5837 | 1667 | 500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01498-B07 | PTCI/MIDC | 15.5018 | 120.8731 | 0.18 | Terrestrial Optical Fiber Drop | 0.07 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1014 | 1 | 26 | 26 | 0307109006 | Region III (Central Luzon) | Zambales | San Antonio | Luna | 14.9491 | 120.0882 | R | 2805 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.11 | Terrestrial Optical Fiber Drop | 0.26 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0027 | 1 | 27 | 27 | 0402101006 | Region IV-A (CALABARZON) | Cavite | Alfonso | Barangay V | 14.1362 | 120.8562 | U | 1543 | 453 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 0.73 | Terrestrial Optical Fiber Drop | 0.07 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0028 | 1 | 28 | 28 | 1600210005 | Region XIII (Caraga) | Agusan del Norte | Santiago | La Paz | 9.267 | 125.5588 | R | 1969 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 0.43 | Terrestrial Optical Fiber Drop | 0.07 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0029 | 1 | 29 | 29 | 0203102020 | Region II (Cagayan Valley) | Isabela | Angadanan | Consular | 16.7878 | 121.7604 | R | 675 | 177 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01319-B06 | PTCI/MIDC | 16.7923 | 121.7648 | 0.68 | Terrestrial Optical Fiber Drop | 0.07 | 4.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0030 | 1 | 30 | 30 | 0307704009 | Region III (Central Luzon) | Aurora | Dinalungan | Simbahan | 16.129 | 121.895 | R | 1295 | 340 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-AUR-02984 | Edgepoint | 16.1187 | 121.8586 | 4.05 | Terrestrial Optical Fiber Drop | 0.07 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0031 | 1 | 31 | 31 | 0201504045 | Region II (Cagayan Valley) | Cagayan | Amulung | Palayag | 17.811 | 121.6759 | R | 1435 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CAG_0004 | LDIC | 17.7947 | 121.6576 | 2.65 | Terrestrial Optical Fiber Drop | 0.07 | 5.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0032 | 1 | 32 | 32 | 0500517032 | Region V (Bicol Region) | Albay | City of Tabaco | Quinastillojan | 13.3411 | 123.6615 | R | 1915 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 3.53 | Terrestrial Optical Fiber Drop | 0.07 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0033 | 1 | 33 | 33 | 1705213007 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Poblacion | 13.4356 | 121.019 | R | 1576 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170052 | FTAP Globe | 13.4328 | 121.0194 | 0.31 | Terrestrial Optical Fiber Drop | 0.07 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0034 | 1 | 34 | 34 | 0506202019 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Norte | 12.8702 | 124.1423 | R | 1751 | 437 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050219 | FTAP Globe | 12.8603 | 124.1471 | 1.22 | Terrestrial Optical Fiber Drop | 0.07 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0035 | 1 | 35 | 35 | 0431200026 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Isabang | 13.9497 | 121.5812 | U | 14084 | 3521 | 1056 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0004 | PTCI/MIDC | 13.9458 | 121.5774 | 0.6 | Terrestrial Optical Fiber Drop | 0.07 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0036 | 1 | 36 | 36 | 1102414018 | Region XI (Davao Region) | Davao del Sur | Sulop | Poblacion | 6.5983 | 125.3439 | U | 8316 | 2445 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0081 | PTCI/MIDC | 6.5956 | 125.3442 | 0.3 | Terrestrial Optical Fiber Drop | 0.07 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0037 | 1 | 37 | 37 | 0201518009 | Region II (Cagayan Valley) | Cagayan | Pamplona | Centro | 18.4648 | 121.3397 | R | 1091 | 279 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00010 | Edgepoint | 18.4669 | 121.339 | 0.24 | Terrestrial Optical Fiber Drop | 0.07 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0038 | 1 | 38 | 38 | 0304904014 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Sur | 15.2632 | 120.8669 | U | 14187 | 4053 | 1216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02448 | Edgepoint | 15.261 | 120.8642 | 0.38 | Terrestrial Optical Fiber Drop | 0.07 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0039 | 1 | 39 | 39 | 0201527003 | Region II (Cagayan Valley) | Cagayan | Solana | Bangag | 17.7087 | 121.6973 | R | 4656 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020031 | FTAP Globe | 17.7126 | 121.6905 | 0.84 | Terrestrial Optical Fiber Drop | 0.07 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0040 | 1 | 40 | 40 | 0401023004 | Region IV-A (CALABARZON) | Batangas | San Juan | Bataan | 13.6957 | 121.4333 | R | 1962 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040597 | FTAP Globe | 13.7212 | 121.4269 | 2.92 | Terrestrial Optical Fiber Drop | 0.07 | 10.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0041 | 1 | 41 | 41 | 0506210006 | Region V (Bicol Region) | Sorsogon | Juban | Buraburan | 12.7757 | 123.9907 | R | 2263 | 565 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050223 | FTAP Globe | 12.7829 | 123.9944 | 0.9 | Terrestrial Optical Fiber Drop | 0.07 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0042 | 1 | 42 | 42 | 1130700126 | Region XI (Davao Region) | Davao del Sur | City of Davao | Toril | 7.0127 | 125.4995 | U | 12895 | 3792 | 1138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0004 | LDIC | 7.0121 | 125.5013 | 0.21 | Terrestrial Optical Fiber Drop | 0.07 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0043 | 1 | 43 | 43 | 1430300008 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Bayan Park West | 16.4073 | 120.5973 | R | 1486 | 391 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02601-B05 | PTCI/MIDC | 16.4118 | 120.6028 | 0.24 | Terrestrial Optical Fiber Drop | 0.59 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0044 | 1 | 44 | 44 | 0105527023 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cabayaoasan | 15.7697 | 120.3885 | R | 1476 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00578 | Edgepoint | 15.7738 | 120.3905 | 0.51 | Terrestrial Optical Fiber Drop | 0.08 | 6.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0045 | 1 | 45 | 45 | 1403209004 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Apatan | 17.5571 | 121.34 | R | 2121 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | N2029 | FTAP Smart | 17.5707 | 121.3629 | 2.86 | Terrestrial Optical Fiber Drop | 0.08 | 9.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0046 | 1 | 46 | 46 | 1130700026 | Region XI (Davao Region) | Davao del Sur | City of Davao | Calinan | 7.1861 | 125.4555 | U | 25199 | 7411 | 2223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110454 | FTAP Globe | 7.185 | 125.4541 | 0.2 | Terrestrial Optical Fiber Drop | 0.08 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0047 | 1 | 47 | 47 | 0201506035 | Region II (Cagayan Valley) | Cagayan | Baggao | San Jose | 17.8914 | 121.8712 | U | 4663 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01179-B06 | PTCI/MIDC | 17.8906 | 121.8735 | 0.25 | Terrestrial Optical Fiber Drop | 0.08 | 16.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0048 | 1 | 48 | 48 | 0506215005 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion III | 12.6457 | 124.105 | R | 863 | 215 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.55 | Terrestrial Optical Fiber Drop | 0.08 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0049 | 1 | 49 | 49 | 0402104009 | Region IV-A (CALABARZON) | Cavite | Carmona | Mabuhay | 14.3103 | 121.0505 | U | 13384 | 3936 | 1181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040182 | FTAP Globe | 14.3107 | 121.0494 | 0.13 | Terrestrial Optical Fiber Drop | 0.08 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0050 | 1 | 50 | 50 | 0401013004 | Region IV-A (CALABARZON) | Batangas | Lian | Binubusan | 13.9603 | 120.6382 | R | 4668 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040415 | FTAP Globe | 13.9594 | 120.6399 | 0.21 | Terrestrial Optical Fiber Drop | 0.08 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0051 | 1 | 51 | 51 | 0506213005 | Region V (Bicol Region) | Sorsogon | Pilar | Bayasong | 12.9876 | 123.6834 | R | 1768 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050201 | FTAP Globe | 13.0151 | 123.7154 | 4.62 | Terrestrial Optical Fiber Drop | 0.08 | 4.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0052 | 1 | 52 | 52 | 0405607042 | Region IV-A (CALABARZON) | Quezon | Calauag | Lagay | 14.0912 | 122.2153 | R | 731 | 192 | 58 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01941 | Edgepoint | 14.0072 | 122.1816 | 10.02 | Terrestrial Optical Fiber Drop | 0.08 | 14.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1009 | 1 | 53 | 53 | 0500518028 | Region V (Bicol Region) | Albay | Tiwi | Tigbi | 13.4532 | 123.68 | U | 2944 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 0.5 | Terrestrial Optical Fiber Drop | 0.54 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0054 | 1 | 54 | 54 | 1600210010 | Region XIII (Caraga) | Agusan del Norte | Santiago | Estanislao Morgado | 9.2663 | 125.5587 | R | 2114 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 0.38 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0055 | 1 | 55 | 55 | 1402705009 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Nayon | 16.7195 | 121.1718 | R | 1226 | 314 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N2035 | FTAP Smart | 16.7138 | 121.1695 | 0.68 | Terrestrial Optical Fiber Drop | 0.09 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0056 | 1 | 56 | 56 | 1600212001 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | Poblacion I | 9.0535 | 125.5878 | R | 2819 | 687 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 0.3 | Terrestrial Optical Fiber Drop | 0.09 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0057 | 1 | 57 | 57 | 1705201029 | MIMAROPA Region | Oriental Mindoro | Baco | Poblacion | 13.3591 | 121.0953 | R | 2895 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170066 | FTAP Globe | 13.3624 | 121.1001 | 0.63 | Terrestrial Optical Fiber Drop | 0.09 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0058 | 1 | 58 | 58 | 0803726015 | Region VIII (Eastern Visayas) | Leyte | Kananga | Poblacion | 11.1858 | 124.5612 | U | 8692 | 2287 | 686 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 0.82 | Terrestrial Optical Fiber Drop | 0.09 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0059 | 1 | 59 | 59 | 0203124004 | Region II (Cagayan Valley) | Isabela | Ramon | Bugallon Norte | 16.7877 | 121.532 | U | 5967 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00261 | Edgepoint | 16.7869 | 121.528 | 0.43 | Terrestrial Optical Fiber Drop | 0.09 | 10.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0060 | 1 | 60 | 60 | 0704619018 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion I | 9.0622 | 123.0312 | U | 1964 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0045 | PTCI/MIDC | 9.0635 | 123.0334 | 0.28 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0061 | 1 | 61 | 61 | 1401110001 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Alapang | 16.4685 | 120.5985 | U | 5383 | 1538 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C57 | FTAP Smart | 16.463 | 120.5956 | 0.69 | Terrestrial Optical Fiber Drop | 0.09 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1018 | 1 | 62 | 62 | 0304917027 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion North | 15.7205 | 120.904 | R | 2951 | 843 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0180 | FTAP Smart | 15.7184 | 120.9059 | 0.31 | Terrestrial Optical Fiber Drop | 0.55 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0063 | 1 | 63 | 63 | 1600212006 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | San Antonio | 9.0535 | 125.5878 | R | 2351 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 0.3 | Terrestrial Optical Fiber Drop | 0.09 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0064 | 1 | 64 | 64 | 0630200024 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 28 | 10.6661 | 122.952 | U | 1571 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0018 | PTCI/MIDC | 10.6685 | 122.9484 | 0.48 | Terrestrial Optical Fiber Drop | 0.09 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0065 | 1 | 65 | 65 | 0205705004 | Region II (Cagayan Valley) | Quirino | Saguday | Rizal | 16.5446 | 121.5631 | R | 2953 | 757 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01775-B06 | PTCI/MIDC | 16.5455 | 121.5638 | 0.13 | Terrestrial Optical Fiber Drop | 0.09 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0066 | 1 | 66 | 66 | 1004304007 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Poblacion | 8.9186 | 124.7853 | R | 2153 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 3.77 | Terrestrial Optical Fiber Drop | 0.09 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0067 | 1 | 67 | 67 | 0504102020 | Region V (Bicol Region) | Masbate | Baleno | Poblacion | 12.4737 | 123.4955 | R | 4033 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MAS-02159 | Edgepoint | 12.4729 | 123.4959 | 0.1 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0068 | 1 | 68 | 68 | 1600205001 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Baleguian | 9.3577 | 125.5537 | R | 2400 | 585 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 10.45 | Terrestrial Optical Fiber Drop | 0.09 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0069 | 1 | 69 | 69 | 0506216001 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Abuyog | 12.9463 | 124.0524 | R | 4670 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 5.7 | Terrestrial Optical Fiber Drop | 0.1 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0070 | 1 | 70 | 70 | 1381300011 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbayan | 14.6078 | 121.0827 | U | 24092 | 6441 | 1932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00524-A02 | PTCI/MIDC | 14.6095 | 121.0826 | 0.19 | Terrestrial Optical Fiber Drop | 0.1 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0071 | 1 | 71 | 71 | 0301419009 | Region III (Central Luzon) | Bulacan | San Ildefonso | Bubulong Malaki | 15.0877 | 120.995 | R | 2300 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-BUL-03129 | Edgepoint | 120.9721 | 15.1005 | 2.84 | Terrestrial Optical Fiber Drop | 0.1 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0072 | 1 | 72 | 72 | 1381300096 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | San Antonio | 14.647 | 121.0164 | U | 22880 | 6320 | 1896 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000211 | FTAP Globe | 14.6464 | 121.0151 | 0.15 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0073 | 1 | 73 | 73 | 0403404006 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Casile | 14.1696 | 121.0193 | U | 3967 | 1202 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02029-C08 | PTCI/MIDC | 14.1661 | 121.0191 | 0.39 | Terrestrial Optical Fiber Drop | 0.1 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0074 | 1 | 74 | 74 | 0301422030 | Region III (Central Luzon) | Bulacan | San Rafael | San Roque | 15.0084 | 120.9324 | U | 10112 | 2889 | 867 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01021-B07 | PTCI/MIDC | 15.0066 | 120.9375 | 0.58 | Terrestrial Optical Fiber Drop | 0.1 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0075 | 1 | 75 | 75 | 0401014058 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Celestino | 13.9174 | 121.2247 | R | 2388 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040486 | FTAP Globe | 13.9189 | 121.2314 | 0.74 | Terrestrial Optical Fiber Drop | 0.1 | 3.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0076 | 1 | 76 | 76 | 1430300029 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | DPS Area | 16.4072 | 120.5974 | R | 958 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140185 | FTAP Globe | 16.4169 | 120.5768 | 0.33 | Terrestrial Optical Fiber Drop | 0.58 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0077 | 1 | 77 | 77 | 0305412019 | Region III (Central Luzon) | Pampanga | Masantol | San Nicolas | 14.8906 | 120.7072 | R | 3980 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.51 | Terrestrial Optical Fiber Drop | 0.1 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0078 | 1 | 78 | 78 | 0304919013 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Atate | 15.5607 | 121.1003 | R | 4297 | 1227 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030154 | FTAP BTS | 15.5656 | 121.0987 | 0.58 | Terrestrial Optical Fiber Drop | 0.04 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0079 | 1 | 79 | 79 | 1430300013 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cabinet Hill-Teacher's Camp | 16.4074 | 120.5971 | U | 3498 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0024 | PTCI/MIDC | 16.4185 | 120.5888 | 0.32 | Terrestrial Optical Fiber Drop | 0.59 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0080 | 1 | 80 | 80 | 0405804027 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pantok | 14.4945 | 121.1801 | U | 16083 | 4467 | 1340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040080 | FTAP Globe | 14.4946 | 121.1826 | 0.27 | Terrestrial Optical Fiber Drop | 0.1 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0081 | 1 | 81 | 81 | 0402102004 | Region IV-A (CALABARZON) | Cavite | Amadeo | Halang | 14.1992 | 120.9319 | R | 2321 | 682 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02223-C08 | PTCI/MIDC | 14.1743 | 120.9201 | 0.45 | Terrestrial Optical Fiber Drop | 3.28 | 3.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0082 | 1 | 82 | 82 | 0405605019 | Region IV-A (CALABARZON) | Quezon | Buenavista | Lilukin | 13.7435 | 122.4591 | R | 1310 | 344 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02789-C10 | PTCI/MIDC | 13.7448 | 122.4555 | 0.42 | Terrestrial Optical Fiber Drop | 0.1 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0083 | 1 | 83 | 83 | 0405603004 | Region IV-A (CALABARZON) | Quezon | Atimonan | Barangay Zone 1 | 14.0003 | 121.9245 | U | 2938 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 0.04 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0084 | 1 | 84 | 84 | 0203123014 | Region II (Cagayan Valley) | Isabela | Quirino | Santa Lucia | 17.1349 | 121.7371 | R | 1899 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ISA-00178 | Edgepoint | 17.1279 | 121.7205 | 1.93 | Terrestrial Optical Fiber Drop | 0.1 | 5.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0085 | 1 | 85 | 85 | 1102407015 | Region XI (Davao Region) | Davao del Sur | Magsaysay | Poblacion | 6.7532 | 125.151 | U | 8011 | 2356 | 707 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110522 | FTAP Globe | 6.7543 | 125.152 | 0.16 | Terrestrial Optical Fiber Drop | 0.1 | 18.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1021 | 1 | 86 | 86 | 0803739025 | Region VIII (Eastern Visayas) | Leyte | Palo | Salvacion | 11.1543 | 124.9981 | R | 2668 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.3 | Terrestrial Optical Fiber Drop | 0.55 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0087 | 1 | 87 | 87 | 0506209002 | Region V (Bicol Region) | Sorsogon | Irosin | Bacolod | 12.7014 | 124.0359 | R | 4737 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 0.11 | Terrestrial Optical Fiber Drop | 0.1 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0088 | 1 | 88 | 88 | 0501734041 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Villazar | 13.8554 | 122.9516 | R | 2067 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 1.45 | Terrestrial Optical Fiber Drop | 0.1 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0089 | 1 | 89 | 89 | 0803733012 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | Talisay | 11.1446 | 124.4718 | R | 628 | 165 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0037 | PTCI/MIDC | 11.1493 | 124.4693 | 0.59 | Terrestrial Optical Fiber Drop | 0.1 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0090 | 1 | 90 | 90 | 0702215007 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Norte | 10.5766 | 124.0181 | R | 4807 | 1265 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 1.18 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0091 | 1 | 91 | 91 | 0402123024 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Gabriel | 14.2826 | 121.0011 | U | 9168 | 2696 | 809 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.36 | Terrestrial Optical Fiber Drop | 0.11 | 3.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0092 | 1 | 92 | 92 | 0305403025 | Region III (Central Luzon) | Pampanga | Arayat | San Jose Mesulo | 15.1425 | 120.7707 | U | 5717 | 1429 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00850 | Edgepoint | 15.1386 | 120.7722 | 0.47 | Terrestrial Optical Fiber Drop | 0.11 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0093 | 1 | 93 | 93 | 0500512024 | Region V (Bicol Region) | Albay | Oas | Ilaor Norte | 13.2628 | 123.4965 | R | 1480 | 360 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050151 | FTAP Globe | 13.2593 | 123.5008 | 0.6 | Terrestrial Optical Fiber Drop | 0.11 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0094 | 1 | 94 | 94 | 1705318015 | MIMAROPA Region | Palawan | Roxas | Barangay 1 | 10.3169 | 119.345 | U | 5443 | 1395 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 1.52 | Terrestrial Optical Fiber Drop | 0.11 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0095 | 1 | 95 | 95 | 0304905030 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Minuli | 16.0728 | 120.9429 | R | 1949 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH030303 | FTAP Globe | 16.0078 | 120.9617 | 7.5 | Terrestrial Optical Fiber Drop | 0.11 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0096 | 1 | 96 | 96 | 0203103022 | Region II (Cagayan Valley) | Isabela | Aurora | San Andres | 16.9635 | 121.5885 | R | 473 | 124 | 37 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0021 | PTCI/MIDC | 16.9834 | 121.6506 | 0.62 | Terrestrial Optical Fiber Drop | 6.27 | 5.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0097 | 1 | 97 | 97 | 1380300021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Post Proper Northside | 14.5636 | 121.0336 | U | 28506 | 8144 | 2443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03214 | Edgepoint | 14.5544 | 121.022 | 0.09 | Terrestrial Optical Fiber Drop | 0.61 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0098 | 1 | 98 | 98 | 0702241018 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion South | 10.1621 | 123.707 | U | 9150 | 2407 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.75 | Terrestrial Optical Fiber Drop | 0.11 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0099 | 1 | 99 | 99 | 0102906006 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Bagani Gabor | 17.1881 | 120.4461 | R | 548 | 144 | 43 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILS-00162 | Edgepoint | 17.193 | 120.4425 | 0.37 | Terrestrial Optical Fiber Drop | 0.42 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0100 | 1 | 100 | 100 | 0306906036 | Region III (Central Luzon) | Tarlac | Gerona | San Antonio | 15.5983 | 120.6051 | R | 3323 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01807-B07 | PTCI/MIDC | 15.6057 | 120.6012 | 0.92 | Terrestrial Optical Fiber Drop | 0.11 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0101 | 1 | 101 | 101 | 0306916023 | Region III (Central Luzon) | Tarlac | City of Tarlac | Burot | 15.4141 | 120.6006 | U | 8013 | 2054 | 616 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.26 | Terrestrial Optical Fiber Drop | 0.12 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0102 | 1 | 102 | 102 | 0307113017 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion North | 15.7688 | 119.9092 | R | 3317 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 1.67 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0103 | 1 | 103 | 103 | 0307110005 | Region III (Central Luzon) | Zambales | San Felipe | Feria | 15.0603 | 120.0712 | R | 1146 | 301 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00904 | Edgepoint | 15.0611 | 120.0686 | 0.3 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0104 | 1 | 104 | 104 | 0201527019 | Region II (Cagayan Valley) | Cagayan | Solana | Nangalisan | 17.648 | 121.6734 | U | 2964 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01149-B06 | PTCI/MIDC | 17.646 | 121.678 | 0.53 | Terrestrial Optical Fiber Drop | 0.12 | 3.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0105 | 1 | 105 | 105 | 0403406013 | Region IV-A (CALABARZON) | Laguna | Calauan | Kanluran | 14.147 | 121.3136 | R | 1538 | 466 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040288 | FTAP Globe | 14.1455 | 121.3143 | 0.19 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1022 | 1 | 106 | 106 | 1102315009 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Gredu | 7.2961 | 125.6784 | U | 16525 | 4466 | 1340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110294 | FTAP BTS | 7.2974 | 125.6811 | 0.33 | Terrestrial Optical Fiber Drop | 0.55 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0107 | 1 | 107 | 107 | 0405608008 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Norte | 13.9308 | 121.4386 | U | 12010 | 3160 | 948 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1409 | FTAP Smart | 13.9294 | 121.4292 | 1.03 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0108 | 1 | 108 | 108 | 0702234003 | Region VII (Central Visayas) | Cebu | City of Naga | Balirong | 10.2566 | 123.7109 | U | 5268 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 3.11 | Terrestrial Optical Fiber Drop | 0.12 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0109 | 1 | 109 | 109 | 1381500015 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Upper Bicutan | 14.4866 | 121.0475 | U | 47397 | 12706 | 3812 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01879 | Edgepoint | 14.4893 | 121.0471 | 0.31 | Terrestrial Optical Fiber Drop | 0.12 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0110 | 1 | 110 | 110 | 1004312011 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Poblacion | 8.9826 | 124.7938 | R | 2396 | 614 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 0.32 | Terrestrial Optical Fiber Drop | 0.12 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0111 | 1 | 111 | 111 | 0501604008 | Region V (Bicol Region) | Camarines Norte | San Lorenzo Ruiz | Matacong | 14.0361 | 122.8655 | R | 3830 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050028 | FTAP Globe | 14.0401 | 122.876 | 1.21 | Terrestrial Optical Fiber Drop | 0.12 | 7.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0112 | 1 | 112 | 112 | 0201523008 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Palawig | 18.4751 | 122.1519 | R | 3082 | 790 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0080 | LDIC | 122.1517 | 18.4728 | 0.26 | Terrestrial Optical Fiber Drop | 0.12 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0113 | 1 | 113 | 113 | 0431200010 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 7 | 13.9326 | 121.6106 | U | 2240 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02137-C08 | PTCI/MIDC | 13.9336 | 121.6126 | 0.24 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0114 | 1 | 114 | 114 | 1381500017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Wawa | 14.5201 | 121.0736 | U | 15930 | 4002 | 1201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01860 | Edgepoint | 14.5168 | 121.075 | 0.39 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0115 | 1 | 115 | 115 | 0405644001 | Region IV-A (CALABARZON) | Quezon | San Narciso | Abuyon | 13.6223 | 122.519 | U | 4981 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040617 | FTAP Globe | 13.6148 | 122.5239 | 0.99 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0116 | 1 | 116 | 116 | 0304902024 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Sinipit | 15.6246 | 121.1476 | R | 2771 | 791 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.4 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0117 | 1 | 117 | 117 | 1004325010 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Poblacion | 8.9988 | 124.8815 | U | 5516 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0078 | PTCI/MIDC | 8.9948 | 124.8803 | 0.46 | Terrestrial Optical Fiber Drop | 0.12 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0118 | 1 | 118 | 118 | 1102412005 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Inawayan | 6.9552 | 125.472 | U | 8909 | 2620 | 786 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110507 | FTAP Globe | 6.9539 | 125.4714 | 0.16 | Terrestrial Optical Fiber Drop | 0.13 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0119 | 1 | 119 | 119 | 0501601001 | Region V (Bicol Region) | Camarines Norte | Basud | Angas | 14.0459 | 123.0178 | R | 1424 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0015 | PTCI/MIDC | 14.0448 | 123.0232 | 0.6 | Terrestrial Optical Fiber Drop | 0.12 | 6.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0120 | 1 | 120 | 120 | 0403416035 | Region IV-A (CALABARZON) | Laguna | Majayjay | San Miguel | 14.1424 | 121.4711 | R | 4529 | 1372 | 412 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.38 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0121 | 1 | 121 | 121 | 0702231015 | Region VII (Central Visayas) | Cebu | Medellin | Tindog | 11.1249 | 124.0119 | U | 4071 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 5.18 | Terrestrial Optical Fiber Drop | 0.13 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0122 | 1 | 122 | 122 | 0403424047 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Francisco | 14.0595 | 121.3284 | U | 16350 | 4954 | 1486 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02002-C08 | PTCI/MIDC | 14.0573 | 121.336 | 0.86 | Terrestrial Optical Fiber Drop | 0.13 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0123 | 1 | 123 | 123 | 1381300062 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Marilag | 14.6255 | 121.0696 | U | 17891 | 4075 | 1223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR- 02351 | Edgepoint | 14.6259 | 121.0671 | 0.27 | Terrestrial Optical Fiber Drop | 0.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0124 | 1 | 124 | 124 | 0500504017 | Region V (Bicol Region) | Albay | Guinobatan | Iraya | 13.1894 | 123.603 | U | 1454 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 0.41 | Terrestrial Optical Fiber Drop | 0.13 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0125 | 1 | 125 | 125 | 0603045011 | Region VI (Western Visayas) | Iloilo | Tigbauan | Barangay 4 | 10.6794 | 122.3823 | R | 1056 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0075 | PTCI/MIDC | 10.674 | 122.3827 | 0.6 | Terrestrial Optical Fiber Drop | 0.13 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0126 | 1 | 126 | 126 | 1001317029 | Region X (Northern Mindanao) | Bukidnon | Quezon | Puntian | 7.6083 | 125.112 | R | 2488 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 0.89 | Terrestrial Optical Fiber Drop | 0.13 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0127 | 1 | 127 | 127 | 0405638008 | Region IV-A (CALABARZON) | Quezon | Real | Maragondon | 14.5336 | 121.5746 | R | 1993 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040059 | FTAP Globe | 14.5404 | 121.5893 | 1.75 | Terrestrial Optical Fiber Drop | 0.13 | 16.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0128 | 1 | 128 | 128 | 0501610019 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Tabugon | 14.0727 | 122.3721 | R | 1844 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050025 | FTAP Globe | 14.0747 | 122.3729 | 0.23 | Terrestrial Optical Fiber Drop | 0.13 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0129 | 1 | 129 | 129 | 0201501010 | Region II (Cagayan Valley) | Cagayan | Abulug | Libertad | 18.3416 | 121.4173 | U | 4010 | 1028 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0039 | LDIC | 121.4092 | 18.3463 | 1 | Terrestrial Optical Fiber Drop | 0.13 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0130 | 1 | 130 | 130 | 0405622007 | Region IV-A (CALABARZON) | Quezon | Lopez | Magsaysay | 13.8871 | 122.261 | R | 4204 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.14 | Terrestrial Optical Fiber Drop | 0.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0131 | 1 | 131 | 131 | 0405618034 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Manlayo | 13.9029 | 122.4511 | R | 1720 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040512 | FTAP Globe | 13.8986 | 122.4538 | 0.56 | Terrestrial Optical Fiber Drop | 0.13 | 11.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0132 | 1 | 132 | 132 | 1004323008 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Poblacion | 8.9556 | 124.7883 | R | 3746 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 0.51 | Terrestrial Optical Fiber Drop | 0.13 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0133 | 1 | 133 | 133 | 0201510006 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Bantay | 18.2484 | 121.6962 | R | 979 | 251 | 75 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02639-B06 | PTCI/MIDC | 18.2633 | 121.6878 | 0.27 | Terrestrial Optical Fiber Drop | 1.61 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0134 | 1 | 134 | 134 | 0203114079 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Centro - San Antonio | 17.0918 | 121.9637 | R | 4798 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01297-B06 | PTCI/MIDC | 17.0916 | 121.9656 | 0.2 | Terrestrial Optical Fiber Drop | 0.13 | 6.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0135 | 1 | 135 | 135 | 0501715028 | Region V (Bicol Region) | Camarines Sur | Goa | San Juan Bautista | 13.6961 | 123.4873 | R | 1297 | 308 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050065 | FTAP Globe | 13.6979 | 123.4893 | 0.29 | Terrestrial Optical Fiber Drop | 0.13 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1024 | 1 | 136 | 136 | 0301411001 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Norte | 14.7743 | 120.944 | U | 11934 | 3409 | 1023 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01039-B07 | PTCI/MIDC | 14.77 | 120.942 | 0.53 | Terrestrial Optical Fiber Drop | 0.55 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0137 | 1 | 137 | 137 | 0403407017 | Region IV-A (CALABARZON) | Laguna | Cavinti | Silangan Talaongan | 14.2793 | 121.5369 | R | 2219 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040203 | FTAP Globe | 14.2731 | 121.546 | 1.2 | Terrestrial Optical Fiber Drop | 0.13 | 7.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0138 | 1 | 138 | 138 | 1030500068 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Taglimao | 8.3939 | 124.5222 | R | 1416 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0005 | PTCI/MIDC | 8.3963 | 124.594 | 7.91 | Terrestrial Optical Fiber Drop | 0.14 | 9.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0139 | 1 | 139 | 139 | 0500517048 | Region V (Bicol Region) | Albay | City of Tabaco | Tagas | 13.3486 | 123.7125 | U | 2241 | 546 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050132 | FTAP Globe | 13.3504 | 123.734 | 0.39 | Terrestrial Optical Fiber Drop | 2.09 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0140 | 1 | 140 | 140 | 0506215003 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion I | 12.6445 | 124.1051 | R | 1113 | 278 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050230 | FTAP Globe | 12.6485 | 124.1096 | 0.66 | Terrestrial Optical Fiber Drop | 0.14 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0141 | 1 | 141 | 141 | 0304902028 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Tulay na Bato | 15.6239 | 121.1453 | R | 2497 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.33 | Terrestrial Optical Fiber Drop | 0.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0142 | 1 | 142 | 142 | 0401010006 | Region IV-A (CALABARZON) | Batangas | Ibaan | Coliat | 13.8149 | 121.1279 | R | 4448 | 1235 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040559 | FTAP Globe | 13.8144 | 121.1337 | 0.63 | Terrestrial Optical Fiber Drop | 0.14 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0143 | 1 | 143 | 143 | 0702213015 | Region VII (Central Visayas) | Cebu | Borbon | Poblacion | 10.835 | 124.0258 | U | 5405 | 1422 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070309 | FTAP Globe | 10.8085 | 123.9899 | 4.91 | Terrestrial Optical Fiber Drop | 0.14 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0144 | 1 | 144 | 144 | 1403215014 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Poblacion | 17.265 | 121.149 | R | 861 | 200 | 60 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140135 | FTAP Globe | 17.2657 | 121.1491 | 0.07 | Terrestrial Optical Fiber Drop | 0.14 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0145 | 1 | 145 | 145 | 0731300004 | Region VII (Central Visayas) | Cebu | City of Mandaue | Basak | 10.354 | 123.9499 | U | 11789 | 3368 | 1010 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0214 | PTCI/MIDC | 10.352 | 123.9517 | 0.29 | Terrestrial Optical Fiber Drop | 0.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0146 | 1 | 146 | 146 | 0203101005 | Region II (Cagayan Valley) | Isabela | Alicia | Bagnos | 16.8076 | 121.6285 | R | 2297 | 604 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020090 | FTAP Globe | 16.8028 | 121.6133 | 1.7 | Terrestrial Optical Fiber Drop | 0.14 | 8.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0147 | 1 | 147 | 147 | 1380400008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Hulong Duhat | 14.6768 | 120.9412 | U | 12265 | 3555 | 1067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02466 | Edgepoint | 14.6781 | 120.9407 | 0.16 | Terrestrial Optical Fiber Drop | 0.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0148 | 1 | 148 | 148 | 0730600065 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag II | 10.3011 | 123.8955 | U | 12188 | 3808 | 1142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0050 | PTCI/MIDC | 10.3311 | 123.8977 | 0.16 | Terrestrial Optical Fiber Drop | 0.39 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0149 | 1 | 149 | 149 | 0401017020 | Region IV-A (CALABARZON) | Batangas | Malvar | Santiago | 14.0193 | 121.1631 | U | 8479 | 2355 | 707 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040374 | FTAP Globe | 14.0197 | 121.1546 | 0.92 | Terrestrial Optical Fiber Drop | 0.14 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0150 | 1 | 150 | 150 | 0205706014 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Sangbay | 16.2519 | 121.6655 | R | 1853 | 475 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02909-B06 | PTCI/MIDC | 16.2659 | 121.6494 | 2.31 | Terrestrial Optical Fiber Drop | 0.14 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0151 | 1 | 151 | 151 | 1731500001 | MIMAROPA Region | Palawan | City of Puerto Princesa | Babuyan | 9.981 | 118.9323 | R | 3016 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4626 | FTAP Smart | 9.9824 | 118.9396 | 0.82 | Terrestrial Optical Fiber Drop | 0.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0152 | 1 | 152 | 152 | 0402107013 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Poblacion III | 14.1818 | 120.7994 | U | 1337 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.04 | Terrestrial Optical Fiber Drop | 0.39 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0153 | 1 | 153 | 153 | 0702202006 | Region VII (Central Visayas) | Cebu | Alcoy | Poblacion | 9.7097 | 123.5073 | R | 4032 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 4.56 | Terrestrial Optical Fiber Drop | 0.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0154 | 1 | 154 | 154 | 0401018004 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | District IV | 13.9583 | 121.1158 | R | 1791 | 497 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01964-C08 | PTCI/MIDC | 13.9582 | 121.119 | 0.34 | Terrestrial Optical Fiber Drop | 0.14 | 2.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0155 | 1 | 155 | 155 | 0201514020 | Region II (Cagayan Valley) | Cagayan | Gonzaga | San Jose | 18.3579 | 122.103 | R | 1591 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020009 | FTAP Globe | 18.3493 | 122.0877 | 1.88 | Terrestrial Optical Fiber Drop | 0.15 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0156 | 1 | 156 | 156 | 0305416036 | Region III (Central Luzon) | Pampanga | City of San Fernando | Sindalan | 15.0774 | 120.6418 | U | 15912 | 3978 | 1193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00891 | Edgepoint | 15.0791 | 120.6456 | 0.45 | Terrestrial Optical Fiber Drop | 0.15 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0157 | 1 | 157 | 157 | 0403402002 | Region IV-A (CALABARZON) | Laguna | Bay | Calo | 14.182 | 121.2796 | R | 4494 | 1361 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.39 | Terrestrial Optical Fiber Drop | 0.15 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0158 | 1 | 158 | 158 | 0405802007 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Isidro | 14.6182 | 121.1857 | U | 62732 | 17425 | 5228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01616 | Edgepoint | 14.6173 | 121.1835 | 0.26 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0159 | 1 | 159 | 159 | 1401108013 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Paykek | 16.5747 | 120.6049 | R | 1528 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140174 | FTAP Globe | 16.5757 | 120.6022 | 0.31 | Terrestrial Optical Fiber Drop | 0.15 | 10.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0160 | 1 | 160 | 160 | 0403404017 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Uno | 14.2767 | 121.1268 | U | 4045 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02403-C08 | PTCI/MIDC | 14.2496 | 121.129 | 0.48 | Terrestrial Optical Fiber Drop | 1.96 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0161 | 1 | 161 | 161 | 0405808010 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Jose | 14.7456 | 121.1294 | U | 135763 | 37711 | 11313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00832-A04 | PTCI/MIDC | 14.7422 | 121.1314 | 0.44 | Terrestrial Optical Fiber Drop | 0.15 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0162 | 1 | 162 | 162 | 0730600004 | Region VII (Central Visayas) | Cebu | City of Cebu | Babag | 10.3803 | 123.856 | U | 5952 | 1860 | 558 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0266 | PTCI/MIDC | 10.3934 | 123.8485 | 1.68 | Terrestrial Optical Fiber Drop | 0.15 | 6.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0163 | 1 | 163 | 163 | 0504113016 | Region V (Bicol Region) | Masbate | Mobo | Nasunduan | 12.338 | 123.6591 | R | 1402 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.37 | Terrestrial Optical Fiber Drop | 0.15 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0164 | 1 | 164 | 164 | 0401022013 | Region IV-A (CALABARZON) | Batangas | San Jose | Don Luis | 13.8836 | 121.0982 | R | 2162 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1373 | FTAP Smart | 13.8745 | 121.1021 | 0.73 | Terrestrial Optical Fiber Drop | 0.88 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1027 | 1 | 165 | 165 | 0402103008 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay I | 14.4487 | 120.9441 | U | 21018 | 6181 | 1854 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0095 | FTAP Smart | 14.4464 | 120.9456 | 0.3 | Terrestrial Optical Fiber Drop | 0.55 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1028 | 1 | 166 | 166 | 0301412015 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Malhacan | 14.7399 | 120.9637 | U | 22515 | 6432 | 1930 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030621 | FTAP Globe | 14.738 | 120.9621 | 0.27 | Terrestrial Optical Fiber Drop | 0.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0167 | 1 | 167 | 167 | 0402118016 | Region IV-A (CALABARZON) | Cavite | Silang | Inchican | 14.2504 | 121.0533 | U | 6206 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040216 | FTAP Globe | 14.2503 | 121.0524 | 0.1 | Terrestrial Optical Fiber Drop | 0.16 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0168 | 1 | 168 | 168 | 0402121009 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I A | 14.2847 | 120.7193 | R | 2010 | 591 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.78 | Terrestrial Optical Fiber Drop | 0.16 | 2.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0169 | 1 | 169 | 169 | 1430300003 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Atok Trail | 16.4075 | 120.5975 | R | 1944 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1746 | FTAP Smart | 16.4044 | 120.5998 | 0.26 | Terrestrial Optical Fiber Drop | 0.61 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0170 | 1 | 170 | 170 | 0402109090 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-B | 14.4265 | 120.9335 | R | 688 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.54 | Terrestrial Optical Fiber Drop | 1.38 | 2.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0171 | 1 | 171 | 171 | 0403420003 | Region IV-A (CALABARZON) | Laguna | Pakil | Burgos | 14.3803 | 121.4778 | R | 2415 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040132 | FTAP Globe | 14.3864 | 121.4768 | 0.7 | Terrestrial Optical Fiber Drop | 0.16 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0172 | 1 | 172 | 172 | 0730600030 | Region VII (Central Visayas) | Cebu | City of Cebu | Guba | 10.4251 | 123.8901 | U | 5739 | 1793 | 538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0058 | PTCI/MIDC | 10.4161 | 123.8716 | 2.25 | Terrestrial Optical Fiber Drop | 0.16 | 4.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0173 | 1 | 173 | 173 | 0304911011 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bulakid | 15.6577 | 120.7602 | R | 607 | 173 | 52 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00616 | Edgepoint | 15.6577 | 120.7688 | 0.07 | Terrestrial Optical Fiber Drop | 0.7 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0174 | 1 | 174 | 174 | 0501723030 | Region V (Bicol Region) | Camarines Sur | Nabua | San Miguel | 13.4043 | 123.3749 | U | 1706 | 406 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02601 | Edgepoint | 13.4058 | 123.3723 | 0.34 | Terrestrial Optical Fiber Drop | 0.16 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0175 | 1 | 175 | 175 | 0600416016 | Region VI (Western Visayas) | Aklan | Numancia | Poblacion | 11.7047 | 122.3274 | R | 1829 | 468 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0012 | PTCI/MIDC | 11.7264 | 122.3458 | 3.13 | Terrestrial Optical Fiber Drop | 0.16 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0176 | 1 | 176 | 176 | 0702243013 | Region VII (Central Visayas) | Cebu | San Remigio | Kinawahan | 10.9472 | 123.9205 | R | 1225 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0148 | PTCI/MIDC | 10.9719 | 123.9357 | 3.21 | Terrestrial Optical Fiber Drop | 0.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0177 | 1 | 177 | 177 | 0405601006 | Region IV-A (CALABARZON) | Quezon | Agdangan | Kanlurang Maligaya | 13.8603 | 121.9375 | R | 278 | 73 | 22 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.56 | Terrestrial Optical Fiber Drop | 2.82 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0178 | 1 | 178 | 178 | 0403415002 | Region IV-A (CALABARZON) | Laguna | Magdalena | Malaking Ambling | 14.1973 | 121.4298 | R | 813 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.49 | Terrestrial Optical Fiber Drop | 0.16 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0179 | 1 | 179 | 179 | 0403421008 | Region IV-A (CALABARZON) | Laguna | Pangil | Sulib | 14.4049 | 121.4638 | U | 7425 | 2250 | 675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.15 | Terrestrial Optical Fiber Drop | 0.16 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0180 | 1 | 180 | 180 | 0501724008 | Region V (Bicol Region) | Camarines Sur | City of Naga | Carolina | 13.6641 | 123.2877 | U | 6854 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050070 | FTAP Globe | 13.6634 | 123.2777 | 1.07 | Terrestrial Optical Fiber Drop | 0.16 | 6.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0181 | 1 | 181 | 181 | 0405811011 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid II | 14.6871 | 121.1147 | U | 4458 | 1238 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 6564 | FTAP Smart | 14.6857 | 121.1157 | 0.19 | Terrestrial Optical Fiber Drop | 0.16 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0182 | 1 | 182 | 182 | 0702250016 | Region VII (Central Visayas) | Cebu | City of Talisay | Tabunoc | 10.2634 | 123.8406 | U | 17918 | 4715 | 1415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 0.62 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0183 | 1 | 183 | 183 | 0203130002 | Region II (Cagayan Valley) | Isabela | San Manuel | Babanuang | 17.0502 | 121.6282 | R | 3136 | 825 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0053 | LDIC | 121.6307 | 17.0461 | 0.54 | Terrestrial Optical Fiber Drop | 0.16 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0184 | 1 | 184 | 184 | 0306916015 | Region III (Central Luzon) | Tarlac | City of Tarlac | Baras-baras | 15.5181 | 120.5652 | U | 5396 | 1383 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00679 | Edgepoint | 15.5236 | 120.5602 | 0.81 | Terrestrial Optical Fiber Drop | 0.16 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0185 | 1 | 185 | 185 | 0102916017 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Poblacion Norte | 17.1512 | 120.5377 | R | 927 | 243 | 73 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ILS-00172 | Edgepoint | 17.1492 | 120.5195 | 1.95 | Terrestrial Optical Fiber Drop | 0.16 | 9.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0186 | 1 | 186 | 186 | 0405630014 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Ilayang Polo | 13.9304 | 121.7759 | R | 2234 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S0800 | FTAP Smart | 13.9046 | 121.7508 | 3.95 | Terrestrial Optical Fiber Drop | 0.16 | 4.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0187 | 1 | 187 | 187 | 0704624006 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Macapso | 10.38 | 123.3322 | R | 1564 | 411 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070250 | FTAP Globe | 10.3733 | 123.3313 | 0.75 | Terrestrial Optical Fiber Drop | 0.16 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0188 | 1 | 188 | 188 | 0105538026 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tebag West | 15.9821 | 120.4599 | U | 2558 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 0.1 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0189 | 1 | 189 | 189 | 0601912026 | Region VI (Western Visayas) | Capiz | Pontevedra | Tacas | 11.4767 | 122.8347 | R | 4684 | 1232 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAP_0003 | LDIC | 11.4838 | 122.8327 | 0.82 | Terrestrial Optical Fiber Drop | 0.16 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0190 | 1 | 190 | 190 | 0402109095 | Region IV-A (CALABARZON) | Cavite | City of Imus | Tanzang Luma III | 14.4152 | 120.9453 | U | 2098 | 617 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000700 | FTAP Globe | 14.4266 | 121.0283 | 0.16 | Terrestrial Optical Fiber Drop | 1.04 | 3.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0191 | 1 | 191 | 191 | 1004326011 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Looc | 8.5943 | 124.7735 | R | 5071 | 1300 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 1.42 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0192 | 1 | 192 | 192 | 0201521012 | Region II (Cagayan Valley) | Cagayan | Rizal | Illuru Norte | 17.8426 | 121.3894 | R | 658 | 182 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020026 | FTAP Globe | 17.832 | 121.4108 | 2.56 | Terrestrial Optical Fiber Drop | 0.16 | 7.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0193 | 1 | 193 | 193 | 0405615013 | Region IV-A (CALABARZON) | Quezon | Dolores | San Mateo | 13.9902 | 121.3873 | R | 1714 | 451 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03164-C08 | PTCI/MIDC | 13.9739 | 121.3789 | 2.02 | Terrestrial Optical Fiber Drop | 0.16 | 5.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0194 | 1 | 194 | 194 | 0203114082 | Region II (Cagayan Valley) | Isabela | City of Ilagan | San Isidro | 17.1668 | 121.9157 | R | 1603 | 421 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0006 | PTCI/MIDC | 17.1681 | 121.9149 | 0.17 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0195 | 1 | 195 | 195 | 0806407066 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Combado | 10.1344 | 124.8288 | U | 5919 | 1443 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.94 | Terrestrial Optical Fiber Drop | 0.17 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0196 | 1 | 196 | 196 | 0307706014 | Region III (Central Luzon) | Aurora | Dipaculao | Lipit | 15.8337 | 121.5344 | R | 794 | 208 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02886-B06 | PTCI/MIDC | 15.8296 | 121.5263 | 0.99 | Terrestrial Optical Fiber Drop | 0.17 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0197 | 1 | 197 | 197 | 0402118023 | Region IV-A (CALABARZON) | Cavite | Silang | Lumil | 14.1828 | 121.0116 | U | 5440 | 1600 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02221-C08 | PTCI/MIDC | 14.1843 | 121.0128 | 0.2 | Terrestrial Optical Fiber Drop | 0.16 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0198 | 1 | 198 | 198 | 0500518020 | Region V (Bicol Region) | Albay | Tiwi | Misibis | 13.509 | 123.6092 | R | 2262 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050113 | FTAP Globe | 13.4889 | 123.6261 | 2.88 | Terrestrial Optical Fiber Drop | 0.17 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0199 | 1 | 199 | 199 | 1400118018 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Suyo | 17.5566 | 120.5643 | R | 694 | 182 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ABR_0005 | LDIC | 17.5493 | 120.5575 | 1.08 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0200 | 1 | 200 | 200 | 1381300089 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Ramon Magsaysay | 14.6616 | 121.0218 | U | 16641 | 4923 | 1477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00539-A01 | PTCI/MIDC | 14.6603 | 121.0204 | 0.2 | Terrestrial Optical Fiber Drop | 0.17 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0201 | 1 | 201 | 201 | 0604528038 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12 | 10.7394 | 122.9686 | R | 2653 | 717 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060339 | FTAP Globe | 10.7358 | 122.9652 | 0.55 | Terrestrial Optical Fiber Drop | 0.17 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0202 | 1 | 202 | 202 | 0102811016 | Region I (Ilocos Region) | Ilocos Norte | Banna | Marcos | 17.9818 | 120.6554 | R | 1064 | 287 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01214-B05 | PTCI/MIDC | 17.9849 | 120.6531 | 0.42 | Terrestrial Optical Fiber Drop | 0.17 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0203 | 1 | 203 | 203 | 0201508005 | Region II (Cagayan Valley) | Cagayan | Buguey | Centro | 18.2883 | 121.8347 | R | 2315 | 593 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0063 | LDIC | 121.8378 | 18.285 | 0.49 | Terrestrial Optical Fiber Drop | 0.17 | 4.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0204 | 1 | 204 | 204 | 0504112019 | Region V (Bicol Region) | Masbate | Milagros | Poblacion East | 12.2177 | 123.5102 | R | 2648 | 645 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050248 | FTAP Globe | 12.2182 | 123.5128 | 0.29 | Terrestrial Optical Fiber Drop | 0.17 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0205 | 1 | 205 | 205 | 0402106058 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran II | 14.3494 | 120.9406 | U | 12987 | 3819 | 1146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01927-C08 | PTCI/MIDC | 14.3499 | 120.9431 | 0.27 | Terrestrial Optical Fiber Drop | 0.17 | 5.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0206 | 1 | 206 | 206 | 1381300115 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Socorro | 14.6214 | 121.0583 | U | 25177 | 7276 | 2183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01583 | Edgepoint | 14.6241 | 121.0577 | 0.31 | Terrestrial Optical Fiber Drop | 0.17 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0207 | 1 | 207 | 207 | 1401109005 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Poblacion | 16.697 | 120.6564 | R | 2493 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140172 | FTAP Globe | 16.6933 | 120.6569 | 0.41 | Terrestrial Optical Fiber Drop | 0.17 | 11.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0208 | 1 | 208 | 208 | 0601905013 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Norte | 11.5223 | 122.6948 | R | 2776 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060229 | FTAP Globe | 11.5171 | 122.6938 | 0.59 | Terrestrial Optical Fiber Drop | 0.17 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0209 | 1 | 209 | 209 | 1102502012 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Poblacion | 6.962 | 126.0125 | U | 9412 | 2614 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110504 | FTAP Globe | 6.9665 | 126.0107 | 0.53 | Terrestrial Optical Fiber Drop | 0.17 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0210 | 1 | 210 | 210 | 0201522003 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Centro I | 18.559 | 121.2347 | U | 2554 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01125-B05 | PTCI/MIDC | 18.5618 | 121.2361 | 0.35 | Terrestrial Optical Fiber Drop | 0.17 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0211 | 1 | 211 | 211 | 0604526016 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Rizal | 10.8039 | 122.9779 | U | 11084 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0063 | PTCI/MIDC | 10.8009 | 122.9774 | 0.34 | Terrestrial Optical Fiber Drop | 0.17 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0212 | 1 | 212 | 212 | 1403213040 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | New Tanglag | 17.4627 | 121.4264 | R | 1456 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00127 | Edgepoint | 17.4695 | 121.4577 | 3.4 | Terrestrial Optical Fiber Drop | 0.17 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0213 | 1 | 213 | 213 | 0201516021 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Logac | 18.1542 | 121.6091 | R | 2454 | 629 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020015 | FTAP Globe | 18.1593 | 121.6024 | 0.9 | Terrestrial Optical Fiber Drop | 0.18 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0214 | 1 | 214 | 214 | 0405649025 | Region IV-A (CALABARZON) | Quezon | Unisan | F. De Jesus | 13.839 | 121.9777 | R | 2291 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040549 | FTAP Globe | 13.8415 | 121.9735 | 0.52 | Terrestrial Optical Fiber Drop | 0.18 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0215 | 1 | 215 | 215 | 0403423010 | Region IV-A (CALABARZON) | Laguna | Rizal | Talaga | 14.1112 | 121.3913 | R | 2220 | 616 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.45 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0216 | 1 | 216 | 216 | 0401005053 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pinamucan Ibaba | 13.6875 | 121.0623 | R | 1876 | 521 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2244 | FTAP Smart | 13.6816 | 121.0591 | 0.74 | Terrestrial Optical Fiber Drop | 0.18 | 7.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1029 | 1 | 217 | 217 | 0402103029 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban II | 14.4609 | 120.9643 | R | 3451 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03026-C08 | PTCI/MIDC | 14.4623 | 120.9625 | 0.25 | Terrestrial Optical Fiber Drop | 0.55 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0218 | 1 | 218 | 218 | 1408105008 | Cordillera Administrative Region (CAR) | Apayao | Luna | Quirino | 18.3367 | 121.3865 | R | 1484 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CAG_0039 | LDIC | 121.4092 | 18.3463 | 2.63 | Terrestrial Optical Fiber Drop | 0.18 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0219 | 1 | 219 | 219 | 0603009016 | Region VI (Western Visayas) | Iloilo | Batad | Malico | 11.4193 | 123.1092 | R | 463 | 121 | 36 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.43 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0220 | 1 | 220 | 220 | 1404402012 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Mabaay | 16.917 | 120.8873 | R | 1289 | 348 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-MOU-00237 | Edgepoint | 16.8985 | 120.8953 | 2.23 | Terrestrial Optical Fiber Drop | 0.18 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0221 | 1 | 221 | 221 | 1401113004 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Camp 4 | 16.3099 | 120.6163 | U | 7022 | 2006 | 602 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140197 | FTAP Globe | 16.3137 | 120.6188 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 9.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0222 | 1 | 222 | 222 | 0304929017 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Malasin | 15.591 | 120.8782 | U | 2120 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00642 | Edgepoint | 15.5899 | 120.8795 | 0.18 | Terrestrial Optical Fiber Drop | 0.18 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0223 | 1 | 223 | 223 | 0401014010 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Banaybanay | 13.9357 | 121.1185 | U | 13356 | 3710 | 1113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040441 | FTAP Globe | 13.9414 | 121.1139 | 0.81 | Terrestrial Optical Fiber Drop | 0.18 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0224 | 1 | 224 | 224 | 1004308003 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Anakan | 8.8416 | 125.1564 | R | 3773 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100111 | FTAP Globe | 8.8451 | 125.1592 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0225 | 1 | 225 | 225 | 0402121005 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion III | 14.2849 | 120.7186 | R | 1850 | 544 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.95 | Terrestrial Optical Fiber Drop | 0.18 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0226 | 1 | 226 | 226 | 0501606005 | Region V (Bicol Region) | Camarines Norte | Labo | Bagong Silang I | 14.1769 | 122.6252 | R | 3154 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAN-03208 | Edgepoint | 14.1763 | 122.626 | 0.11 | Terrestrial Optical Fiber Drop | 0.19 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0227 | 1 | 227 | 227 | 0330100027 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Cristo | 15.1425 | 120.5986 | U | 4240 | 1177 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00826 | Edgepoint | 15.1639 | 120.5897 | 0.45 | Terrestrial Optical Fiber Drop | 1.23 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0228 | 1 | 228 | 228 | 0205014009 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Norte | 16.5828 | 121.1891 | R | 3059 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-00302 | Edgepoint | 16.5766 | 121.1908 | 0.72 | Terrestrial Optical Fiber Drop | 0.19 | 5.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0229 | 1 | 229 | 229 | 0205701015 | Region II (Cagayan Valley) | Quirino | Aglipay | Victoria | 16.4379 | 121.6367 | R | 1242 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01774-B06 | PTCI/MIDC | 16.4293 | 121.6392 | 1 | Terrestrial Optical Fiber Drop | 0.19 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0230 | 1 | 230 | 230 | 0306903011 | Region III (Central Luzon) | Tarlac | Camiling | Bobon Caarosipan | 15.6875 | 120.4205 | R | 754 | 193 | 58 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00605 | Edgepoint | 15.6807 | 120.415 | 0.49 | Terrestrial Optical Fiber Drop | 0.6 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0231 | 1 | 231 | 231 | 0401030006 | Region IV-A (CALABARZON) | Batangas | Talisay | Buco | 14.0839 | 120.9969 | R | 1096 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.34 | Terrestrial Optical Fiber Drop | 2.53 | 5.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0232 | 1 | 232 | 232 | 0500516017 | Region V (Bicol Region) | Albay | Santo Domingo | Nagsiya Pob. | 13.2383 | 123.776 | R | 1057 | 257 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.86 | Terrestrial Optical Fiber Drop | 0.19 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0233 | 1 | 233 | 233 | 0401034015 | Region IV-A (CALABARZON) | Batangas | Tuy | Rizal | 14.0217 | 120.7301 | R | 1169 | 324 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.39 | Terrestrial Optical Fiber Drop | 0.19 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0234 | 1 | 234 | 234 | 1130700198 | Region XI (Davao Region) | Davao del Sur | City of Davao | Vicente Hizon Sr. | 7.165 | 125.4713 | U | 11674 | 3433 | 1030 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110474 | FTAP Globe | 7.1148 | 125.6545 | 0.63 | Terrestrial Optical Fiber Drop | 2.96 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0235 | 1 | 235 | 235 | 0306903044 | Region III (Central Luzon) | Tarlac | Camiling | Poblacion B | 15.6889 | 120.4133 | R | 1920 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02715 | Edgepoint | 15.6897 | 120.4131 | 0.09 | Terrestrial Optical Fiber Drop | 0.19 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0236 | 1 | 236 | 236 | 0102821012 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Leandro | 18.1546 | 120.6446 | R | 1287 | 347 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01210-B05 | PTCI/MIDC | 18.156 | 120.6512 | 0.72 | Terrestrial Optical Fiber Drop | 0.19 | 5.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0237 | 1 | 237 | 237 | 0402121001 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I | 14.285 | 120.7185 | R | 1999 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.7 | Terrestrial Optical Fiber Drop | 0.19 | 2.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0238 | 1 | 238 | 238 | 0500507027 | Region V (Bicol Region) | Albay | Libon | Matara | 13.3008 | 123.438 | R | 854 | 208 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.42 | Terrestrial Optical Fiber Drop | 0.19 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0239 | 1 | 239 | 239 | 0501721002 | Region V (Bicol Region) | Camarines Sur | Milaor | Amparado | 13.5965 | 123.1783 | R | 420 | 100 | 30 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050093 | FTAP Globe | 13.5996 | 123.1749 | 0.5 | Terrestrial Optical Fiber Drop | 0.19 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0240 | 1 | 240 | 240 | 0701205011 | Region VII (Central Visayas) | Bohol | Baclayon | Poblacion | 9.6223 | 123.9117 | R | 1899 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 4.82 | Terrestrial Optical Fiber Drop | 0.19 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0241 | 1 | 241 | 241 | 0402113012 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pantihan II | 14.2431 | 120.7943 | R | 1216 | 357 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040235 | FTAP Globe | 14.2274 | 120.8012 | 1.89 | Terrestrial Optical Fiber Drop | 0.19 | 2.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0242 | 1 | 242 | 242 | 0704603017 | Region VII (Central Visayas) | Negros Oriental | Bacong | South Poblacion | 9.2471 | 123.2958 | R | 1553 | 408 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 2.78 | Terrestrial Optical Fiber Drop | 0.92 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0243 | 1 | 243 | 243 | 0307102018 | Region III (Central Luzon) | Zambales | Cabangan | San Antonio | 15.1609 | 120.0548 | R | 826 | 217 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00822 | Edgepoint | 15.1674 | 120.0507 | 0.84 | Terrestrial Optical Fiber Drop | 0.2 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0244 | 1 | 244 | 244 | 0405601012 | Region IV-A (CALABARZON) | Quezon | Agdangan | Poblacion I | 13.8737 | 121.9146 | R | 1409 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.41 | Terrestrial Optical Fiber Drop | 0.2 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0245 | 1 | 245 | 245 | 1380500013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Highway Hills | 14.5824 | 121.0494 | U | 49455 | 14631 | 4389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000343 | FTAP Globe | 14.5845 | 121.0497 | 0.23 | Terrestrial Optical Fiber Drop | 0.2 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0246 | 1 | 246 | 246 | 0506216035 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Talisay | 12.9683 | 124.0041 | U | 2686 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.15 | Terrestrial Optical Fiber Drop | 0.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0247 | 1 | 247 | 247 | 0402114002 | Region IV-A (CALABARZON) | Cavite | Mendez | Asis I | 14.137 | 120.9007 | R | 3842 | 1130 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02216-C08 | PTCI/MIDC | 14.1324 | 120.9008 | 0.5 | Terrestrial Optical Fiber Drop | 0.2 | 4.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0248 | 1 | 248 | 248 | 0403410016 | Region IV-A (CALABARZON) | Laguna | Liliw | Ibabang Taykin | 14.1345 | 121.4362 | R | 1106 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02121-C08 | PTCI/MIDC | 14.1337 | 121.4379 | 0.21 | Terrestrial Optical Fiber Drop | 0.2 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0249 | 1 | 249 | 249 | 1001304022 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Sur | 7.6777 | 124.9943 | U | 12727 | 3349 | 1005 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 0.88 | Terrestrial Optical Fiber Drop | 0.2 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0250 | 1 | 250 | 250 | 0102811014 | Region I (Ilocos Region) | Ilocos Norte | Banna | Lorenzo | 17.9803 | 120.6584 | R | 757 | 204 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILN_0007 | LDIC | 120.6603 | 17.9829 | 0.34 | Terrestrial Optical Fiber Drop | 0.2 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0251 | 1 | 251 | 251 | 0603047004 | Region VI (Western Visayas) | Iloilo | Zarraga | Dawis Centro | 10.828 | 122.6085 | R | 257 | 67 | 20 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.78 | Terrestrial Optical Fiber Drop | 0.2 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0252 | 1 | 252 | 252 | 1001321010 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Guinoyuran | 7.8949 | 125.0054 | U | 8132 | 2140 | 642 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100208 | FTAP Globe | 7.8969 | 125.0047 | 0.24 | Terrestrial Optical Fiber Drop | 0.2 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0253 | 1 | 253 | 253 | 0702212005 | Region VII (Central Visayas) | Cebu | Boljoon | Poblacion | 9.6253 | 123.4801 | R | 4263 | 1121 | 336 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 12.36 | Terrestrial Optical Fiber Drop | 0.2 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0254 | 1 | 254 | 254 | 0500508032 | Region V (Bicol Region) | Albay | City of Ligao | Nasisi | 13.2591 | 123.5846 | R | 1989 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.46 | Terrestrial Optical Fiber Drop | 0.2 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0255 | 1 | 255 | 255 | 1380400011 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Maysilo | 14.6827 | 120.9617 | U | 10481 | 3003 | 901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00674-A01 | PTCI/MIDC | 14.6831 | 120.9595 | 0.24 | Terrestrial Optical Fiber Drop | 0.2 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0256 | 1 | 256 | 256 | 0402105006 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 13 | 14.4732 | 120.8867 | R | 1750 | 514 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040089 | FTAP Globe | 14.4741 | 120.8882 | 0.2 | Terrestrial Optical Fiber Drop | 0.2 | 4.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0257 | 1 | 257 | 257 | 1705319005 | MIMAROPA Region | Palawan | San Vicente | New Agutaya | 10.5394 | 119.2792 | R | 5179 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02441-C09 | PTCI/MIDC | 10.5366 | 119.2409 | 4.19 | Terrestrial Optical Fiber Drop | 0.2 | 9.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0258 | 1 | 258 | 258 | 0403407006 | Region IV-A (CALABARZON) | Laguna | Cavinti | Duhat | 14.2473 | 121.5011 | R | 2006 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040218 | FTAP Globe | 14.2498 | 121.5044 | 0.45 | Terrestrial Optical Fiber Drop | 0.2 | 5.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0259 | 1 | 259 | 259 | 0403426021 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Norte | 14.2842 | 121.4181 | R | 3016 | 913 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040201 | FTAP Globe | 14.2743 | 121.4075 | 0.64 | Terrestrial Optical Fiber Drop | 0.78 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0260 | 1 | 260 | 260 | 0403402004 | Region IV-A (CALABARZON) | Laguna | Bay | Maitim | 14.1793 | 121.2755 | U | 5105 | 1546 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02363-C08 | PTCI/MIDC | 14.1757 | 121.2709 | 0.64 | Terrestrial Optical Fiber Drop | 0.2 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0261 | 1 | 261 | 261 | 1705212013 | MIMAROPA Region | Oriental Mindoro | Roxas | San Jose | 12.6055 | 121.5526 | R | 3605 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S87 | FTAP Smart | 12.5916 | 121.5236 | 3.5 | Terrestrial Optical Fiber Drop | 0.2 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1038 | 1 | 262 | 262 | 1381300007 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbuhay | 14.6253 | 121.0642 | U | 6739 | 1643 | 493 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02529-A01 | PTCI/MIDC | 14.6246 | 121.0657 | 0.18 | Terrestrial Optical Fiber Drop | 0.55 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0263 | 1 | 263 | 263 | 0331400006 | Region III (Central Luzon) | Zambales | City of Olongapo | East Tapinac | 14.8336 | 120.2828 | U | 10127 | 2737 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030589 | FTAP Globe | 14.8335 | 120.2862 | 0.37 | Terrestrial Optical Fiber Drop | 0.2 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0264 | 1 | 264 | 264 | 0803748050 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Santo Niño Pob. | 11.1037 | 125.0208 | U | 3845 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0083 | PTCI/MIDC | 11.1054 | 125.0132 | 0.85 | Terrestrial Optical Fiber Drop | 0.2 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0265 | 1 | 265 | 265 | 0307702019 | Region III (Central Luzon) | Aurora | Casiguran | Bianuan | 16.2056 | 122.0424 | R | 2790 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030301 | FTAP Globe | 16.2078 | 122.0393 | 0.41 | Terrestrial Optical Fiber Drop | 0.2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0266 | 1 | 266 | 266 | 0301404013 | Region III (Central Luzon) | Bulacan | Bocaue | Lolomboy | 14.7794 | 120.9337 | U | 15091 | 4311 | 1293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02495 | Edgepoint | 14.7799 | 120.935 | 0.15 | Terrestrial Optical Fiber Drop | 0.2 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0267 | 1 | 267 | 267 | 0603005018 | Region VI (Western Visayas) | Iloilo | Balasan | Poblacion Sur | 11.4721 | 123.088 | U | 2558 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.31 | Terrestrial Optical Fiber Drop | 0.2 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0268 | 1 | 268 | 268 | 1408102003 | Cordillera Administrative Region (CAR) | Apayao | Conner | Caglayan | 17.7953 | 121.3232 | R | 2435 | 579 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03392-B06 | PTCI/MIDC | 17.7968 | 121.3195 | 0.43 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0269 | 1 | 269 | 269 | 0102812062 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 1, San Lorenzo | 18.2049 | 120.5843 | U | 5541 | 1497 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-03234 | Edgepoint | 18.206 | 120.5863 | 0.24 | Terrestrial Optical Fiber Drop | 0.21 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0270 | 1 | 270 | 270 | 0501734040 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Centro | 13.7639 | 122.9755 | U | 6551 | 1559 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 1.58 | Terrestrial Optical Fiber Drop | 0.21 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0271 | 1 | 271 | 271 | 1400101023 | Cordillera Administrative Region (CAR) | Abra | Bangued | Sao-atan | 17.5972 | 120.6176 | R | 1052 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ABR-03102 | Edgepoint | 120.6153 | 17.5944 | 0.47 | Terrestrial Optical Fiber Drop | 0.53 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0272 | 1 | 272 | 272 | 0301407020 | Region III (Central Luzon) | Bulacan | Calumpit | Pio Cruzcosa | 14.8976 | 120.7645 | U | 4874 | 1392 | 418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01097-B07 | PTCI/MIDC | 14.9017 | 120.7697 | 0.48 | Terrestrial Optical Fiber Drop | 1.04 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0273 | 1 | 273 | 273 | 0105543015 | Region I (Ilocos Region) | Pangasinan | Tayug | Barangay B | 16.0255 | 120.748 | U | 1548 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00445 | Edgepoint | 16.0267 | 120.7436 | 0.49 | Terrestrial Optical Fiber Drop | 0.21 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0274 | 1 | 274 | 274 | 0501608023 | Region V (Bicol Region) | Camarines Norte | Paracale | Poblacion Sur | 14.2801 | 122.7849 | R | 1668 | 417 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.31 | Terrestrial Optical Fiber Drop | 0.21 | 9.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0275 | 1 | 275 | 275 | 0103301004 | Region I (Ilocos Region) | La Union | Agoo | Consolacion | 16.3251 | 120.3695 | U | 1720 | 464 | 139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.47 | Terrestrial Optical Fiber Drop | 0.21 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0276 | 1 | 276 | 276 | 0504101001 | Region V (Bicol Region) | Masbate | Aroroy | Ambolong | 12.5106 | 123.3969 | R | 4642 | 1132 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.07 | Terrestrial Optical Fiber Drop | 0.21 | 4.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0277 | 1 | 277 | 277 | 0401024028 | Region IV-A (CALABARZON) | Batangas | San Luis | Poblacion | 13.8547 | 120.9171 | U | 2396 | 665 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040541 | FTAP Globe | 13.8548 | 120.9176 | 0.06 | Terrestrial Optical Fiber Drop | 0.21 | 4.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0278 | 1 | 278 | 278 | 0403415006 | Region IV-A (CALABARZON) | Laguna | Magdalena | Bucal | 14.2023 | 121.4288 | R | 538 | 163 | 49 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.44 | Terrestrial Optical Fiber Drop | 0.47 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0279 | 1 | 279 | 279 | 0702241013 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion North | 10.1642 | 123.7078 | R | 4710 | 1239 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.99 | Terrestrial Optical Fiber Drop | 0.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0280 | 1 | 280 | 280 | 0604524001 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Bagonbon | 10.5831 | 123.3983 | U | 6059 | 1637 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0035 | PTCI/MIDC | 10.564 | 123.4683 | 7.95 | Terrestrial Optical Fiber Drop | 0.21 | 7.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0281 | 1 | 281 | 281 | 0105526014 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guilig | 16.0666 | 120.4007 | R | 3480 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.72 | Terrestrial Optical Fiber Drop | 0.21 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0282 | 1 | 282 | 282 | 0604517012 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Robles | 10.3187 | 123.0195 | U | 21507 | 5812 | 1744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060377 | FTAP Globe | 10.3212 | 123.0205 | 0.3 | Terrestrial Optical Fiber Drop | 0.21 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0283 | 1 | 283 | 283 | 1130700040 | Region XI (Davao Region) | Davao del Sur | City of Davao | Daliao | 7.0113 | 125.5014 | U | 22349 | 6573 | 1972 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0004 | LDIC | 7.0121 | 125.5013 | 0.09 | Terrestrial Optical Fiber Drop | 0.21 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0284 | 1 | 284 | 284 | 1381100171 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 171 | 14.5335 | 121.0129 | U | 3492 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02585 | Edgepoint | 14.7527 | 120.954 | 0.23 | Terrestrial Optical Fiber Drop | 1.32 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0285 | 1 | 285 | 285 | 0304930055 | Region III (Central Luzon) | Nueva Ecija | Talavera | Tabacao | 15.5838 | 120.9188 | R | 4856 | 1387 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030351 | FTAP Globe | 15.5879 | 120.9213 | 0.52 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0286 | 1 | 286 | 286 | 0205703003 | Region II (Cagayan Valley) | Quirino | Diffun | Aurora West | 16.5874 | 121.5023 | R | 2574 | 660 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Y51 | FTAP Smart | 16.5918 | 121.5046 | 0.55 | Terrestrial Optical Fiber Drop | 0.21 | 7.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0287 | 1 | 287 | 287 | 0304930035 | Region III (Central Luzon) | Nueva Ecija | Talavera | Maestrang Kikay | 15.5834 | 120.9206 | U | 4291 | 1226 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030351 | FTAP Globe | 15.5879 | 120.9213 | 0.5 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0288 | 1 | 288 | 288 | 0731300003 | Region VII (Central Visayas) | Cebu | City of Mandaue | Banilad | 10.3392 | 123.9226 | U | 18404 | 5258 | 1577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0116 | PTCI/MIDC | 10.3371 | 123.9196 | 0.69 | Terrestrial Optical Fiber Drop | 0.15 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0289 | 1 | 289 | 289 | 0402114004 | Region IV-A (CALABARZON) | Cavite | Mendez | Palocpoc I | 14.1281 | 120.8789 | R | 1736 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040294 | FTAP Globe | 14.1367 | 120.8759 | 1.01 | Terrestrial Optical Fiber Drop | 0.21 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0290 | 1 | 290 | 290 | 0203110005 | Region II (Cagayan Valley) | Isabela | Dinapigue | Digumased | 16.5247 | 122.2657 | R | 3023 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ISA-00314 | Edgepoint | 16.5292 | 122.2595 | 0.83 | Terrestrial Optical Fiber Drop | 0.21 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0291 | 1 | 291 | 291 | 1705211012 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Poblacion | 13.5011 | 120.9545 | U | 5395 | 1383 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170046 | FTAP Globe | 13.5009 | 120.9529 | 0.18 | Terrestrial Optical Fiber Drop | 0.21 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0292 | 1 | 292 | 292 | 0103320007 | Region I (Ilocos Region) | La Union | Tubao | Gonzales | 16.3254 | 120.369 | R | 1918 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.53 | Terrestrial Optical Fiber Drop | 0.21 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0293 | 1 | 293 | 293 | 0403412010 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Antonio | 14.1857 | 121.5062 | R | 3605 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 0.54 | Terrestrial Optical Fiber Drop | 0.21 | 4.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0294 | 1 | 294 | 294 | 1004315005 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Poblacion | 8.5593 | 124.3527 | U | 5423 | 1390 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 0.35 | Terrestrial Optical Fiber Drop | 0.21 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0295 | 1 | 295 | 295 | 1381300009 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagong Pag-asa | 14.6631 | 121.0338 | U | 28022 | 7983 | 2395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01451 | Edgepoint | 14.6644 | 121.0318 | 0.25 | Terrestrial Optical Fiber Drop | 0.21 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0296 | 1 | 296 | 296 | 0306905035 | Region III (Central Luzon) | Tarlac | Concepcion | San Nicolas | 15.3261 | 120.6544 | U | 5092 | 1305 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.65 | Terrestrial Optical Fiber Drop | 0.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1041 | 1 | 297 | 297 | 1130700170 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 37-D | 7.0866 | 125.6128 | U | 6005 | 1766 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0025 | PTCI/MIDC | 7.0664 | 125.6152 | 0.36 | Terrestrial Optical Fiber Drop | 0.99 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0298 | 1 | 298 | 298 | 0500507036 | Region V (Bicol Region) | Albay | Libon | Sampongan | 13.2599 | 123.3973 | R | 452 | 110 | 33 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.46 | Terrestrial Optical Fiber Drop | 6.29 | 7.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0299 | 1 | 299 | 299 | 0301410050 | Region III (Central Luzon) | Bulacan | City of Malolos | Santo Rosario | 14.8532 | 120.8177 | U | 7665 | 2190 | 657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01088-B07 | PTCI/MIDC | 14.8537 | 120.8194 | 0.2 | Terrestrial Optical Fiber Drop | 0.22 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0300 | 1 | 300 | 300 | 0504113020 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. II | 12.3386 | 123.658 | R | 2067 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.42 | Terrestrial Optical Fiber Drop | 0.22 | 4.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0301 | 1 | 301 | 301 | 0305406012 | Region III (Central Luzon) | Pampanga | Floridablanca | Fortuna | 14.9828 | 120.5164 | U | 5744 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01555-B07 | PTCI/MIDC | 14.981 | 120.5138 | 0.34 | Terrestrial Optical Fiber Drop | 0.22 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0302 | 1 | 302 | 302 | 0730600081 | Region VII (Central Visayas) | Cebu | City of Cebu | Talamban | 10.3696 | 123.9174 | U | 33422 | 10444 | 3133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0120 | PTCI/MIDC | 10.3627 | 123.9271 | 1.32 | Terrestrial Optical Fiber Drop | 0.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1042 | 1 | 303 | 303 | 0205013013 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Roxas | 16.5178 | 121.1851 | U | 9738 | 2562 | 769 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00317 | Edgepoint | 16.5169 | 121.1814 | 0.41 | Terrestrial Optical Fiber Drop | 0.55 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0304 | 1 | 304 | 304 | 0701216010 | Region VII (Central Visayas) | Bohol | Cortes | Poblacion | 9.7197 | 123.8768 | R | 1352 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070415 | FTAP Globe | 9.7203 | 123.8782 | 0.16 | Terrestrial Optical Fiber Drop | 0.22 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0305 | 1 | 305 | 305 | 0501718060 | Region V (Bicol Region) | Camarines Sur | Libmanan | San Isidro | 13.6723 | 123.0088 | R | 3990 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-02607 | Edgepoint | 13.6871 | 122.9969 | 2.09 | Terrestrial Optical Fiber Drop | 0.22 | 3.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0306 | 1 | 306 | 306 | 0205013012 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Quirino | 16.5128 | 121.1825 | U | 7173 | 1887 | 566 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00317 | Edgepoint | 16.5169 | 121.1814 | 0.48 | Terrestrial Optical Fiber Drop | 0.22 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0307 | 1 | 307 | 307 | 0500502019 | Region V (Bicol Region) | Albay | Camalig | Iluluan | 13.1273 | 123.6 | R | 1602 | 390 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050177 | FTAP Globe | 13.1433 | 123.6026 | 1.8 | Terrestrial Optical Fiber Drop | 0.22 | 6.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0308 | 1 | 308 | 308 | 0201520019 | Region II (Cagayan Valley) | Cagayan | Piat | Poblacion II | 17.7925 | 121.4758 | R | 1534 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0059 | LDIC | 121.4784 | 17.7911 | 0.32 | Terrestrial Optical Fiber Drop | 0.22 | 8.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0309 | 1 | 309 | 309 | 1380300013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Magallanes | 14.5635 | 121.0337 | U | 5473 | 1169 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00502-A02 | PTCI/MIDC | 14.5699 | 121.0284 | 0.18 | Terrestrial Optical Fiber Drop | 0.63 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0310 | 1 | 310 | 310 | 0501718006 | Region V (Bicol Region) | Camarines Sur | Libmanan | Bagumbayan | 13.6768 | 123.0323 | U | 1869 | 445 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02607 | Edgepoint | 13.6871 | 122.9969 | 2.14 | Terrestrial Optical Fiber Drop | 2.6 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0311 | 1 | 311 | 311 | 0405629011 | Region IV-A (CALABARZON) | Quezon | Padre Burgos | Burgos | 13.9171 | 121.8175 | R | 805 | 211 | 63 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040480 | FTAP Globe | 13.9209 | 121.8193 | 0.46 | Terrestrial Optical Fiber Drop | 0.22 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0312 | 1 | 312 | 312 | 0402104016 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 5 | 14.3136 | 121.0539 | R | 560 | 164 | 49 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0044 | PTCI/MIDC | 14.3102 | 121.0334 | 0.7 | Terrestrial Optical Fiber Drop | 0.51 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0313 | 1 | 313 | 313 | 0301422023 | Region III (Central Luzon) | Bulacan | San Rafael | Poblacion | 14.9587 | 120.9685 | U | 1714 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0069 | PTCI/MIDC | 11.1801 | 122.8301 | 0.16 | Terrestrial Optical Fiber Drop | 0.77 | 4.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0314 | 1 | 314 | 314 | 0305417018 | Region III (Central Luzon) | Pampanga | San Luis | Santo Tomas | 15.0408 | 120.7897 | U | 2678 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.11 | Terrestrial Optical Fiber Drop | 0.22 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0315 | 1 | 315 | 315 | 0704603015 | Region VII (Central Visayas) | Negros Oriental | Bacong | Sacsac | 9.2547 | 123.2901 | R | 4372 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 2.42 | Terrestrial Optical Fiber Drop | 0.23 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0316 | 1 | 316 | 316 | 0803739014 | Region VIII (Eastern Visayas) | Leyte | Palo | Cogon | 11.148 | 124.9998 | R | 3047 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.88 | Terrestrial Optical Fiber Drop | 0.23 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0317 | 1 | 317 | 317 | 0307108015 | Region III (Central Luzon) | Zambales | Palauig | West Poblacion | 15.4341 | 119.9049 | R | 1240 | 326 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00729 | Edgepoint | 15.4369 | 119.9033 | 0.36 | Terrestrial Optical Fiber Drop | 0.23 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0318 | 1 | 318 | 318 | 0105531035 | Region I (Ilocos Region) | Pangasinan | Rosales | Carmay East | 15.8959 | 120.6322 | U | 3147 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00540 | Edgepoint | 15.8985 | 120.6329 | 0.3 | Terrestrial Optical Fiber Drop | 0.23 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0319 | 1 | 319 | 319 | 0331400015 | Region III (Central Luzon) | Zambales | City of Olongapo | New Ilalim | 14.835 | 120.2793 | R | 1589 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3883 | FTAP Smart | 14.8372 | 120.2825 | 0.42 | Terrestrial Optical Fiber Drop | 0.23 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0320 | 1 | 320 | 320 | 1380400001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Acacia | 14.6675 | 120.9689 | U | 4965 | 1299 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0025 | PTCI/MIDC | 14.667 | 120.9688 | 0.05 | Terrestrial Optical Fiber Drop | 0.23 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0321 | 1 | 321 | 321 | 0307105009 | Region III (Central Luzon) | Zambales | Iba | Zone 1 Pob. | 15.3285 | 119.9763 | U | 2520 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.46 | Terrestrial Optical Fiber Drop | 0.23 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0322 | 1 | 322 | 322 | 0304920012 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Poblacion East | 15.8056 | 121.1447 | R | 4095 | 1170 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01421-B07 | PTCI/MIDC | 15.8043 | 121.149 | 0.48 | Terrestrial Optical Fiber Drop | 0.23 | 10.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0323 | 1 | 323 | 323 | 0501734038 | Region V (Bicol Region) | Camarines Sur | Sipocot | San Vicente | 13.7641 | 122.9755 | R | 1166 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 1.56 | Terrestrial Optical Fiber Drop | 0.23 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0324 | 1 | 324 | 324 | 0105506017 | Region I (Ilocos Region) | Pangasinan | Asingan | Poblacion West | 16.0031 | 120.6693 | U | 1558 | 432 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.84 | Terrestrial Optical Fiber Drop | 0.23 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0325 | 1 | 325 | 325 | 0301421051 | Region III (Central Luzon) | Bulacan | San Miguel | Sapang | 15.1922 | 120.9908 | R | 2087 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01047-B07 | PTCI/MIDC | 15.1819 | 120.9951 | 1.24 | Terrestrial Optical Fiber Drop | 0.23 | 2.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0326 | 1 | 326 | 326 | 0600415014 | Region VI (Western Visayas) | Aklan | New Washington | Polo | 11.65 | 122.4341 | R | 3752 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.92 | Terrestrial Optical Fiber Drop | 0.23 | 7.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0327 | 1 | 327 | 327 | 0501610009 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Santa Elena | 14.1821 | 122.3932 | U | 9627 | 2406 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050008 | FTAP Globe | 14.218 | 122.3945 | 3.99 | Terrestrial Optical Fiber Drop | 0.23 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0328 | 1 | 328 | 328 | 0305413005 | Region III (Central Luzon) | Pampanga | Mexico | Camuning | 15.1151 | 120.6645 | R | 3008 | 752 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00867 | Edgepoint | 15.1183 | 120.6573 | 0.86 | Terrestrial Optical Fiber Drop | 0.23 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0329 | 1 | 329 | 329 | 0504111020 | Region V (Bicol Region) | Masbate | City of Masbate | Kinamaligan | 12.359 | 123.6184 | U | 5390 | 1314 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03057-C10 | PTCI/MIDC | 12.3584 | 123.6151 | 0.36 | Terrestrial Optical Fiber Drop | 0.23 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0330 | 1 | 330 | 330 | 1401105001 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Abatan | 16.8037 | 120.8233 | U | 3644 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 0.88 | Terrestrial Optical Fiber Drop | 0.23 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0331 | 1 | 331 | 331 | 0103309006 | Region I (Ilocos Region) | La Union | Caba | Poblacion Norte | 16.4312 | 120.3457 | R | 1350 | 364 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.29 | Terrestrial Optical Fiber Drop | 0.23 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0332 | 1 | 332 | 332 | 0405801009 | Region IV-A (CALABARZON) | Rizal | Angono | San Isidro | 14.5295 | 121.1543 | U | 32767 | 9101 | 2730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02296-A04 | PTCI/MIDC | 14.5283 | 121.1526 | 0.23 | Terrestrial Optical Fiber Drop | 0.23 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0333 | 1 | 333 | 333 | 1705320018 | MIMAROPA Region | Palawan | Taytay | Pancol | 10.8707 | 119.4166 | R | 3530 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170216 | FTAP Globe | 10.8254 | 119.4866 | 9.16 | Terrestrial Optical Fiber Drop | 0.23 | 10.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0334 | 1 | 334 | 334 | 0201516003 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Bagumbayan | 18.1935 | 121.6635 | R | 2142 | 549 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.19 | Terrestrial Optical Fiber Drop | 0.23 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0335 | 1 | 335 | 335 | 0601909036 | Region VI (Western Visayas) | Capiz | Panay | Poblacion Ilawod | 11.5575 | 122.7967 | R | 520 | 136 | 41 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060227 | FTAP Globe | 11.5586 | 122.7957 | 0.16 | Terrestrial Optical Fiber Drop | 0.24 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0336 | 1 | 336 | 336 | 0603034020 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion East | 10.6914 | 122.4787 | R | 4302 | 1132 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060007 | FTAP BTS | 10.6921 | 122.4753 | 0.39 | Terrestrial Optical Fiber Drop | 0.24 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0337 | 1 | 337 | 337 | 0702223031 | Region VII (Central Visayas) | Cebu | Danao City | Poblacion | 10.5202 | 124.0277 | U | 9928 | 2612 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.36 | Terrestrial Optical Fiber Drop | 0.24 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0338 | 1 | 338 | 338 | 0203127008 | Region II (Cagayan Valley) | Isabela | San Agustin | Masaya Centro | 16.509 | 121.7457 | R | 1576 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01360-B06 | PTCI/MIDC | 16.5141 | 121.7471 | 0.59 | Terrestrial Optical Fiber Drop | 0.24 | 13.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0339 | 1 | 339 | 339 | 1381200014 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Palatiw | 14.5646 | 121.083 | U | 28185 | 7961 | 2388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02350 | Edgepoint | 14.5651 | 121.0814 | 0.18 | Terrestrial Optical Fiber Drop | 0.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0340 | 1 | 340 | 340 | 0702233011 | Region VII (Central Visayas) | Cebu | Moalboal | Poblacion West | 9.939 | 123.3927 | R | 3648 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 1.76 | Terrestrial Optical Fiber Drop | 0.24 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0341 | 1 | 341 | 341 | 0405644013 | Region IV-A (CALABARZON) | Quezon | San Narciso | Pagkakaisa | 13.5679 | 122.5541 | R | 1456 | 383 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040621 | FTAP Globe | 13.5669 | 122.5556 | 0.2 | Terrestrial Optical Fiber Drop | 0.24 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0342 | 1 | 342 | 342 | 0203112036 | Region II (Cagayan Valley) | Isabela | Echague | Pangal Norte | 16.6102 | 121.6771 | R | 1617 | 425 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0023 | LDIC | 121.6823 | 16.6043 | 0.86 | Terrestrial Optical Fiber Drop | 0.24 | 10.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0343 | 1 | 343 | 343 | 1004314008 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Poblacion | 8.5755 | 124.445 | U | 3866 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 0.59 | Terrestrial Optical Fiber Drop | 0.24 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0344 | 1 | 344 | 344 | 1004304005 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Mosangot | 8.9157 | 124.7852 | R | 1418 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 4.1 | Terrestrial Optical Fiber Drop | 0.24 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0345 | 1 | 345 | 345 | 0604524015 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay VI | 10.4802 | 123.4187 | U | 5619 | 1518 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0058 | PTCI/MIDC | 10.4822 | 123.4207 | 0.3 | Terrestrial Optical Fiber Drop | 0.24 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0346 | 1 | 346 | 346 | 0501612014 | Region V (Bicol Region) | Camarines Norte | Vinzons | Barangay I | 14.1757 | 122.909 | R | 2130 | 532 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050015 | FTAP Globe | 14.1707 | 122.912 | 0.64 | Terrestrial Optical Fiber Drop | 0.24 | 3.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0347 | 1 | 347 | 347 | 0405639017 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Isidro | 14.1633 | 121.6399 | R | 1556 | 409 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.18 | Terrestrial Optical Fiber Drop | 0.24 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0348 | 1 | 348 | 348 | 0304923027 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion Norte | 15.7131 | 121.1036 | R | 3213 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 0.66 | Terrestrial Optical Fiber Drop | 0.24 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0349 | 1 | 349 | 349 | 0803750004 | Region VIII (Eastern Visayas) | Leyte | Tunga | San Antonio | 11.2466 | 124.7503 | R | 873 | 229 | 69 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 0.15 | Terrestrial Optical Fiber Drop | 0.24 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0350 | 1 | 350 | 350 | 1600204011 | Region XIII (Caraga) | Agusan del Norte | Carmen | San Agustin | 9.0564 | 125.2236 | R | 1323 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0064 | PTCI/MIDC | 9.059 | 125.1954 | 3.11 | Terrestrial Optical Fiber Drop | 0.24 | 5.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0351 | 1 | 351 | 351 | 0105523008 | Region I (Ilocos Region) | Pangasinan | Mabini | Calzada | 16.0826 | 119.9275 | R | 1899 | 527 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00410 | Edgepoint | 16.0915 | 119.94 | 1.66 | Terrestrial Optical Fiber Drop | 0.24 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0352 | 1 | 352 | 352 | 1600312006 | Region XIII (Caraga) | Agusan del Sur | Trento | Poblacion | 8.0475 | 126.0633 | U | 18953 | 4859 | 1458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130103 | FTAP Globe | 8.0454 | 126.064 | 0.25 | Terrestrial Optical Fiber Drop | 0.24 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0353 | 1 | 353 | 353 | 0501709013 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Roque | 13.6207 | 123.1741 | U | 3091 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.36 | Terrestrial Optical Fiber Drop | 0.24 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0354 | 1 | 354 | 354 | 0403422004 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Norte | 14.2349 | 121.3655 | R | 2537 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.51 | Terrestrial Optical Fiber Drop | 0.24 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0355 | 1 | 355 | 355 | 1030500003 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bulua | 8.5029 | 124.6167 | U | 36039 | 10010 | 3003 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100050 | FTAP BTS | 8.5056 | 124.6153 | 0.33 | Terrestrial Optical Fiber Drop | 0.24 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0356 | 1 | 356 | 356 | 0831600108 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 77 | 11.2111 | 125.0077 | U | 3726 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0066 | PTCI/MIDC | 11.2106 | 125.008 | 0.06 | Terrestrial Optical Fiber Drop | 0.24 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0357 | 1 | 357 | 357 | 0304906023 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VI | 15.7792 | 120.6621 | R | 1936 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0032 | PTCI/MIDC | 15.7841 | 120.6581 | 0.69 | Terrestrial Optical Fiber Drop | 0.24 | 6.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0358 | 1 | 358 | 358 | 1600205011 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Poblacion | 9.3486 | 125.5078 | R | 4175 | 1018 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 9.97 | Terrestrial Optical Fiber Drop | 1.03 | 4.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0359 | 1 | 359 | 359 | 0405802004 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mayamot | 14.6297 | 121.1209 | U | 50271 | 13964 | 4189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02986-A04 | PTCI/MIDC | 14.6287 | 121.1229 | 0.24 | Terrestrial Optical Fiber Drop | 0.24 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0360 | 1 | 360 | 360 | 0803703015 | Region VIII (Eastern Visayas) | Leyte | Albuera | Tabgas | 10.8976 | 124.7081 | R | 3171 | 834 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080133 | FTAP BTS | 10.901 | 124.7063 | 0.42 | Terrestrial Optical Fiber Drop | 0.24 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0361 | 1 | 361 | 361 | 1004307012 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Poblacion | 8.557 | 124.5216 | U | 8953 | 2295 | 689 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100124 (FTAP_GLO_PH100124) | FTAP Globe | 8.5545 | 124.5256 | 0.52 | Terrestrial Optical Fiber Drop | 0.24 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0362 | 1 | 362 | 362 | 0604531008 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay V | 10.902 | 123.0753 | R | 1805 | 487 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.48 | Terrestrial Optical Fiber Drop | 0.25 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0363 | 1 | 363 | 363 | 0501706008 | Region V (Bicol Region) | Camarines Sur | Bula | Inoyonan | 13.4698 | 123.2772 | R | 1302 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.29 | Terrestrial Optical Fiber Drop | 0.25 | 5.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0364 | 1 | 364 | 364 | 0401014041 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 10 | 13.9422 | 121.1574 | R | 3085 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040434 | FTAP Globe | 13.9453 | 121.1715 | 0.37 | Terrestrial Optical Fiber Drop | 1 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0365 | 1 | 365 | 365 | 0500511010 | Region V (Bicol Region) | Albay | Manito | It-Ba | 13.1261 | 123.8698 | R | 3750 | 914 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050186 | FTAP Globe | 13.1258 | 123.8679 | 0.2 | Terrestrial Optical Fiber Drop | 0.25 | 12.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0366 | 1 | 366 | 366 | 1600208001 | Region XIII (Caraga) | Agusan del Norte | Magallanes | Buhang | 9.0354 | 125.525 | R | 4178 | 1019 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130065 | FTAP Globe | 8.9969 | 125.4871 | 5.98 | Terrestrial Optical Fiber Drop | 0.25 | 7.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0367 | 1 | 367 | 367 | 0500507016 | Region V (Bicol Region) | Albay | Libon | Caguscos | 13.2311 | 123.3303 | R | 1034 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050168 | FTAP Globe | 13.1892 | 123.3257 | 4.69 | Terrestrial Optical Fiber Drop | 0.25 | 14.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0368 | 1 | 368 | 368 | 0500516012 | Region V (Bicol Region) | Albay | Santo Domingo | San Rafael Pob. | 13.2367 | 123.7794 | R | 554 | 135 | 41 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 1.23 | Terrestrial Optical Fiber Drop | 0.25 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0369 | 1 | 369 | 369 | 0203105007 | Region II (Cagayan Valley) | Isabela | Burgos | Cullalabo San Antonio | 17.0888 | 121.7049 | R | 3513 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0027 | LDIC | 121.7027 | 17.0894 | 0.24 | Terrestrial Optical Fiber Drop | 0.25 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0370 | 1 | 370 | 370 | 0402113008 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I A | 14.2767 | 120.7352 | R | 1877 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.55 | Terrestrial Optical Fiber Drop | 0.25 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0371 | 1 | 371 | 371 | 1705215020 | MIMAROPA Region | Oriental Mindoro | Victoria | Poblacion III | 13.1669 | 121.2777 | U | 4126 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03226-C09 | PTCI/MIDC | 13.1756 | 121.2763 | 0.98 | Terrestrial Optical Fiber Drop | 0.25 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0372 | 1 | 372 | 372 | 0405814010 | Region IV-A (CALABARZON) | Rizal | Teresa | Calumpang Santo Cristo | 14.5586 | 121.2136 | R | 1394 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00850-A04 | PTCI/MIDC | 14.5535 | 121.2133 | 0.41 | Terrestrial Optical Fiber Drop | 0.71 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0373 | 1 | 373 | 373 | 0803733021 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | San Guillermo | 11.1467 | 124.4704 | R | 630 | 165 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0037 | PTCI/MIDC | 11.1493 | 124.4693 | 0.31 | Terrestrial Optical Fiber Drop | 0.25 | 9.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0374 | 1 | 374 | 374 | 0501737008 | Region V (Bicol Region) | Camarines Sur | Tinambac | Binalay | 13.8158 | 123.3409 | R | 2335 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050046 | FTAP Globe | 13.8167 | 123.3373 | 0.4 | Terrestrial Optical Fiber Drop | 0.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0375 | 1 | 375 | 375 | 0402109008 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-A | 14.4264 | 120.9336 | R | 1136 | 334 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4755 | FTAP Smart | 14.4069 | 120.9425 | 0.21 | Terrestrial Optical Fiber Drop | 1.37 | 2.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0376 | 1 | 376 | 376 | 0102809018 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Medina | 18.0775 | 120.7042 | R | 1318 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 0.31 | Terrestrial Optical Fiber Drop | 2.39 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0377 | 1 | 377 | 377 | 0205701022 | Region II (Cagayan Valley) | Quirino | Aglipay | Pinaripad Norte | 16.4783 | 121.5996 | R | 1084 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020117 | FTAP Globe | 16.4887 | 121.588 | 1.69 | Terrestrial Optical Fiber Drop | 0.25 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0378 | 1 | 378 | 378 | 1705207013 | MIMAROPA Region | Oriental Mindoro | Mansalay | Poblacion | 12.5218 | 121.4411 | U | 4357 | 1117 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170126 | FTAP Globe | 12.5234 | 121.4387 | 0.32 | Terrestrial Optical Fiber Drop | 0.25 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0379 | 1 | 379 | 379 | 1380500023 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pleasant Hills | 14.5872 | 121.0386 | U | 6097 | 1698 | 509 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02647 | Edgepoint | 14.5884 | 121.0398 | 0.18 | Terrestrial Optical Fiber Drop | 0.26 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0380 | 1 | 380 | 380 | 1400108005 | Cordillera Administrative Region (CAR) | Abra | La Paz | Canan | 17.662 | 120.6689 | R | 1507 | 396 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_ABR_0001 | LDIC | 120.6611 | 17.6816 | 2.33 | Terrestrial Optical Fiber Drop | 0.25 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0381 | 1 | 381 | 381 | 0702210038 | Region VII (Central Visayas) | Cebu | Barili | Poblacion | 10.1153 | 123.511 | U | 5196 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 0.35 | Terrestrial Optical Fiber Drop | 0.26 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0382 | 1 | 382 | 382 | 0307104015 | Region III (Central Luzon) | Zambales | Castillejos | Santa Maria | 14.9373 | 120.1983 | R | 2109 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.31 | Terrestrial Optical Fiber Drop | 0.87 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0383 | 1 | 383 | 383 | 1004317016 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Poblacion | 9.0213 | 125.1817 | R | 1713 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0089 | PTCI/MIDC | 9.0209 | 125.184 | 0.25 | Terrestrial Optical Fiber Drop | 0.26 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0384 | 1 | 384 | 384 | 0403415019 | Region IV-A (CALABARZON) | Laguna | Magdalena | Poblacion | 14.1993 | 121.4286 | R | 2735 | 828 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.24 | Terrestrial Optical Fiber Drop | 0.26 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0385 | 1 | 385 | 385 | 0405618012 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Capuluan Tulon | 13.8208 | 122.4877 | R | 937 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-02699 | Edgepoint | 13.8025 | 122.4147 | 8.14 | Terrestrial Optical Fiber Drop | 0.26 | 7.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0386 | 1 | 386 | 386 | 0603044004 | Region VI (Western Visayas) | Iloilo | Sara | Anoring | 11.2188 | 122.9773 | R | 2609 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.4 | Terrestrial Optical Fiber Drop | 5.39 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0387 | 1 | 387 | 387 | 1600206011 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Songkoy | 9.4556 | 125.5743 | R | 2543 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 4.59 | Terrestrial Optical Fiber Drop | 0.26 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0388 | 1 | 388 | 388 | 0704623020 | Region VII (Central Visayas) | Negros Oriental | Valencia | North Poblacion | 9.2823 | 123.2454 | R | 768 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070270 | FTAP Globe | 9.2811 | 123.2423 | 0.37 | Terrestrial Optical Fiber Drop | 0.26 | 5.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0389 | 1 | 389 | 389 | 0306916082 | Region III (Central Luzon) | Tarlac | City of Tarlac | Sapang Tagalog | 15.4218 | 120.5992 | U | 5451 | 1397 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.66 | Terrestrial Optical Fiber Drop | 0.26 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0390 | 1 | 390 | 390 | 1381500009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Maharlika Village | 14.4978 | 121.0551 | U | 26241 | 7809 | 2343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00357-A02 | PTCI/MIDC | 14.4973 | 121.0528 | 0.25 | Terrestrial Optical Fiber Drop | 0.26 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0391 | 1 | 391 | 391 | 0501737004 | Region V (Bicol Region) | Camarines Sur | Tinambac | Banga | 13.8884 | 123.3857 | R | 1188 | 282 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050046 | FTAP Globe | 13.8167 | 123.3373 | 9.54 | Terrestrial Optical Fiber Drop | 0.26 | 9.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0392 | 1 | 392 | 392 | 0603039011 | Region VI (Western Visayas) | Iloilo | San Enrique | Dacal | 11.0697 | 122.6567 | R | 1096 | 288 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.44 | Terrestrial Optical Fiber Drop | 0.26 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0393 | 1 | 393 | 393 | 0405628031 | Region IV-A (CALABARZON) | Quezon | Mulanay | Santa Rosa | 13.5289 | 122.3932 | R | 3511 | 923 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-QUE-03181 | Edgepoint | 13.5248 | 122.4031 | 1.16 | Terrestrial Optical Fiber Drop | 0.26 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0394 | 1 | 394 | 394 | 0304906025 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VIII | 15.7803 | 120.662 | R | 1383 | 395 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0032 | PTCI/MIDC | 15.7841 | 120.6581 | 0.59 | Terrestrial Optical Fiber Drop | 0.26 | 6.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0395 | 1 | 395 | 395 | 0803736011 | Region VIII (Eastern Visayas) | Leyte | Merida | Libas | 10.9397 | 124.5447 | R | 2435 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0041 | PTCI/MIDC | 10.9685 | 124.5339 | 3.42 | Terrestrial Optical Fiber Drop | 0.26 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0396 | 1 | 396 | 396 | 1600307001 | Region XIII (Caraga) | Agusan del Sur | Rosario | Bayugan 3 | 8.386 | 126.0814 | U | 14871 | 3813 | 1144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130097 | FTAP Globe | 8.3116 | 126.0093 | 1.17 | Terrestrial Optical Fiber Drop | 8.66 | 7.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0397 | 1 | 397 | 397 | 0501730029 | Region V (Bicol Region) | Camarines Sur | Ragay | Poblacion Ilaod | 13.8192 | 122.7909 | R | 1812 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050045 | FTAP Globe | 13.8174 | 122.7937 | 0.36 | Terrestrial Optical Fiber Drop | 0.26 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0398 | 1 | 398 | 398 | 0304917026 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion East | 15.7143 | 120.9051 | U | 2186 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0180 | FTAP Smart | 15.7184 | 120.9059 | 0.47 | Terrestrial Optical Fiber Drop | 0.26 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0399 | 1 | 399 | 399 | 0603009024 | Region VI (Western Visayas) | Iloilo | Batad | Tanao | 11.4191 | 123.111 | R | 2058 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.5 | Terrestrial Optical Fiber Drop | 0.26 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0400 | 1 | 400 | 400 | 0402109084 | Region IV-A (CALABARZON) | Cavite | City of Imus | Palico IV | 14.4281 | 120.947 | U | 3871 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01878-C08 | PTCI/MIDC | 14.4292 | 120.9451 | 0.23 | Terrestrial Optical Fiber Drop | 0.27 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0401 | 1 | 401 | 401 | 1381500001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Tanyag | 14.4801 | 121.0471 | U | 24705 | 7744 | 2323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01865 | Edgepoint | 14.5092 | 121.0624 | 0.09 | Terrestrial Optical Fiber Drop | 0.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0402 | 1 | 402 | 402 | 0501603032 | Region V (Bicol Region) | Camarines Norte | Daet | San Isidro | 14.106 | 122.9536 | R | 3341 | 835 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S92 | FTAP Smart | 14.1147 | 122.9549 | 0.13 | Terrestrial Optical Fiber Drop | 0.95 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0403 | 1 | 403 | 403 | 0401025013 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Poblacion | 13.9281 | 120.9499 | R | 3272 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040462 | FTAP Globe | 13.9283 | 120.9517 | 0.19 | Terrestrial Optical Fiber Drop | 0.27 | 4.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0404 | 1 | 404 | 404 | 0307109014 | Region III (Central Luzon) | Zambales | San Antonio | Rizal | 14.9492 | 120.0881 | R | 478 | 125 | 38 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.41 | Terrestrial Optical Fiber Drop | 0.27 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0405 | 1 | 405 | 405 | 1380500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Wack-wack Greenhills | 14.5836 | 121.0338 | U | 13775 | 3625 | 1088 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0115 | PTCI/MIDC | 14.5645 | 121.0253 | 0.16 | Terrestrial Optical Fiber Drop | 0.62 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0406 | 1 | 406 | 406 | 0803722019 | Region VIII (Eastern Visayas) | Leyte | Isabel | San Roque | 10.9243 | 124.4398 | R | 1525 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080356 | FTAP Globe | 10.9258 | 124.4385 | 0.22 | Terrestrial Optical Fiber Drop | 0.27 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0407 | 1 | 407 | 407 | 0405801005 | Region IV-A (CALABARZON) | Rizal | Angono | Kalayaan | 14.5297 | 121.1536 | U | 19309 | 5363 | 1609 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02296-A04 | PTCI/MIDC | 14.5283 | 121.1526 | 0.19 | Terrestrial Optical Fiber Drop | 0.27 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0408 | 1 | 408 | 408 | 0600415002 | Region VI (Western Visayas) | Aklan | New Washington | Cawayan | 11.6503 | 122.4336 | R | 4310 | 1105 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.86 | Terrestrial Optical Fiber Drop | 0.27 | 7.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0409 | 1 | 409 | 409 | 0803715035 | Region VIII (Eastern Visayas) | Leyte | Carigara | Sawang | 11.3001 | 124.6869 | R | 2393 | 629 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 0.98 | Terrestrial Optical Fiber Drop | 0.27 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0410 | 1 | 410 | 410 | 0803738090 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Valencia | 11.1081 | 124.5773 | U | 4374 | 1151 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0029 | PTCI/MIDC | 11.128 | 124.5855 | 2.39 | Terrestrial Optical Fiber Drop | 0.27 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0411 | 1 | 411 | 411 | 0603009004 | Region VI (Western Visayas) | Iloilo | Batad | Batad Viejo | 11.419 | 123.111 | R | 1207 | 317 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.51 | Terrestrial Optical Fiber Drop | 0.27 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0412 | 1 | 412 | 412 | 0604531009 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VI | 10.9091 | 123.0764 | U | 5874 | 1587 | 476 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.47 | Terrestrial Optical Fiber Drop | 0.91 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0413 | 1 | 413 | 413 | 0307109009 | Region III (Central Luzon) | Zambales | San Antonio | San Gregorio | 14.9519 | 120.0885 | R | 1062 | 279 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.7 | Terrestrial Optical Fiber Drop | 0.27 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0414 | 1 | 414 | 414 | 0402106008 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan I | 14.3215 | 120.9793 | U | 10659 | 3135 | 941 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.63 | Terrestrial Optical Fiber Drop | 0.46 | 3.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0415 | 1 | 415 | 415 | 0105526002 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Amansabina | 16.0666 | 120.4001 | U | 2732 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.7 | Terrestrial Optical Fiber Drop | 0.27 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0416 | 1 | 416 | 416 | 0501602015 | Region V (Bicol Region) | Camarines Norte | Capalonga | Magsaysay | 14.2266 | 122.5522 | R | 1956 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050011 | FTAP Globe | 14.191 | 122.5157 | 5.58 | Terrestrial Optical Fiber Drop | 0.27 | 5.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0417 | 1 | 417 | 417 | 0102812004 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 56-B, Bacsil South | 18.1988 | 120.6558 | R | 1366 | 369 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-ILN-03234 | Edgepoint | 18.206 | 120.5863 | 0.36 | Terrestrial Optical Fiber Drop | 4.99 | 5.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0418 | 1 | 418 | 418 | 0201504020 | Region II (Cagayan Valley) | Cagayan | Amulung | Centro | 17.8343 | 121.7243 | U | 2918 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01178-B06 | PTCI/MIDC | 17.8338 | 121.7241 | 0.07 | Terrestrial Optical Fiber Drop | 0.28 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0419 | 1 | 419 | 419 | 0402103046 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino III | 14.3976 | 120.9775 | U | 63684 | 18730 | 5619 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040127 | FTAP Globe | 14.3946 | 120.9746 | 0.46 | Terrestrial Optical Fiber Drop | 0.28 | 5.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0420 | 1 | 420 | 420 | 0405607060 | Region IV-A (CALABARZON) | Quezon | Calauag | Pinagkamaligan | 13.9561 | 122.285 | R | 1843 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0005 | PTCI/MIDC | 13.957 | 122.2821 | 0.33 | Terrestrial Optical Fiber Drop | 0.27 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0421 | 1 | 421 | 421 | 0304901021 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Poblacion East I | 15.5011 | 120.8511 | R | 2597 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01498-B07 | PTCI/MIDC | 15.5018 | 120.8731 | 0.51 | Terrestrial Optical Fiber Drop | 2.15 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0422 | 1 | 422 | 422 | 1606819005 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Bongtod Pob. | 17.1051 | 122.2743 | U | 6121 | 1492 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.64 | Terrestrial Optical Fiber Drop | 27.55 | 37.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0423 | 1 | 423 | 423 | 0702243020 | Region VII (Central Visayas) | Cebu | San Remigio | Poblacion | 11.081 | 123.9378 | U | 5869 | 1544 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070302 | FTAP Globe | 11.08 | 123.9405 | 0.32 | Terrestrial Optical Fiber Drop | 0.28 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0424 | 1 | 424 | 424 | 0702248018 | Region VII (Central Visayas) | Cebu | Tabogon | Poblacion | 10.9412 | 124.0281 | R | 1631 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070306 | FTAP Globe | 10.9458 | 124.0265 | 0.54 | Terrestrial Optical Fiber Drop | 0.28 | 6.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0425 | 1 | 425 | 425 | 0306913005 | Region III (Central Luzon) | Tarlac | San Clemente | Catagudingan | 15.7082 | 120.366 | R | 720 | 184 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01813-B07 | PTCI/MIDC | 15.7092 | 120.3597 | 0.69 | Terrestrial Optical Fiber Drop | 0.28 | 5.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0426 | 1 | 426 | 426 | 0401031034 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 3 | 14.1034 | 121.0787 | U | 5284 | 1467 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040316 | FTAP Globe | 14.1024 | 121.0968 | 0.27 | Terrestrial Optical Fiber Drop | 2.15 | 6.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0427 | 1 | 427 | 427 | 0201524004 | Region II (Cagayan Valley) | Cagayan | Santa Praxedes | Centro II | 18.5632 | 120.9902 | R | 939 | 240 | 72 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0052 | LDIC | 120.9909 | 18.5648 | 0.19 | Terrestrial Optical Fiber Drop | 0.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0428 | 1 | 428 | 428 | 0600401007 | Region VI (Western Visayas) | Aklan | Altavas | Lumaynay | 11.4866 | 122.4282 | R | 1190 | 305 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 3.26 | Terrestrial Optical Fiber Drop | 8.28 | 5.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0429 | 1 | 429 | 429 | 0405625018 | Region IV-A (CALABARZON) | Quezon | Macalelon | Rizal | 13.7477 | 122.1383 | R | 474 | 124 | 37 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.18 | Terrestrial Optical Fiber Drop | 0.28 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0430 | 1 | 430 | 430 | 1380200009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Zapote | 14.4639 | 120.9708 | U | 19994 | 5234 | 1570 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02396-A03 | PTCI/MIDC | 14.4619 | 120.9719 | 0.25 | Terrestrial Optical Fiber Drop | 0.28 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0431 | 1 | 431 | 431 | 1001321029 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Sinayawan | 7.8732 | 125.1439 | U | 8940 | 2352 | 706 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100209 | FTAP Globe | 7.8774 | 125.142 | 0.51 | Terrestrial Optical Fiber Drop | 0.28 | 4.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0432 | 1 | 432 | 432 | 1380700010 | National Capital Region (NCR) | Metro Manila (NCR) | City of Marikina | Santo Niño | 14.639 | 121.0958 | U | 30271 | 8248 | 2474 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00284-A01 | PTCI/MIDC | 14.6371 | 121.0972 | 0.27 | Terrestrial Optical Fiber Drop | 0.28 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0433 | 1 | 433 | 433 | 0803702052 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Milagrosa | 11.2189 | 124.8596 | R | 1125 | 296 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 0.32 | Terrestrial Optical Fiber Drop | 2.38 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0434 | 1 | 434 | 434 | 1001304004 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Calaocalao | 7.6872 | 124.9182 | R | 3163 | 832 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0007 | PTCI/MIDC | 7.6385 | 124.9046 | 5.62 | Terrestrial Optical Fiber Drop | 0.28 | 8.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0435 | 1 | 435 | 435 | 0301421050 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Rita Matanda | 15.1336 | 120.9661 | R | 3118 | 890 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030029 | FTAP BTS | 15.1372 | 120.9654 | 0.41 | Terrestrial Optical Fiber Drop | 0.28 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0436 | 1 | 436 | 436 | 0403428002 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Balibago | 14.2963 | 121.1045 | U | 23640 | 7163 | 2149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040188 | FTAP Globe | 14.2948 | 121.1032 | 0.22 | Terrestrial Optical Fiber Drop | 0.28 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0437 | 1 | 437 | 437 | 0300808001 | Region III (Central Luzon) | Bataan | Morong | Binaritan | 14.6824 | 120.268 | U | 7440 | 2066 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02575 | Edgepoint | 14.6805 | 120.2704 | 0.33 | Terrestrial Optical Fiber Drop | 0.28 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0438 | 1 | 438 | 438 | 1381000001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Baclaran | 14.5298 | 120.9989 | U | 35290 | 14582 | 4375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00585-A02 | PTCI/MIDC | 14.5278 | 120.9978 | 0.25 | Terrestrial Optical Fiber Drop | 0.28 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0439 | 1 | 439 | 439 | 0702208027 | Region VII (Central Visayas) | Cebu | Balamban | Baliwagan | 10.5066 | 123.7145 | U | 6280 | 1652 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 1.12 | Terrestrial Optical Fiber Drop | 0.28 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0440 | 1 | 440 | 440 | 0105516007 | Region I (Ilocos Region) | Pangasinan | Burgos | Poblacion | 16.0548 | 119.8647 | U | 3491 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01737-B07 | PTCI/MIDC | 16.0575 | 119.864 | 0.31 | Terrestrial Optical Fiber Drop | 0.28 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0441 | 1 | 441 | 441 | 0506216013 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Burabod | 12.9718 | 124.0051 | U | 2249 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.31 | Terrestrial Optical Fiber Drop | 0.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0442 | 1 | 442 | 442 | 0506203009 | Region V (Bicol Region) | Sorsogon | Bulan | Zone V Pob. | 12.6694 | 123.8754 | R | 1494 | 373 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.56 | Terrestrial Optical Fiber Drop | 0.28 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0443 | 1 | 443 | 443 | 0600411009 | Region VI (Western Visayas) | Aklan | Makato | Calimbajan | 11.7215 | 122.2751 | R | 2139 | 548 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.1 | Terrestrial Optical Fiber Drop | 2.09 | 9.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0444 | 1 | 444 | 444 | 0405647043 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Mateuna | 14.0242 | 121.596 | U | 5954 | 1566 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1446 | FTAP Smart | 14.0221 | 121.5973 | 0.28 | Terrestrial Optical Fiber Drop | 0.28 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0445 | 1 | 445 | 445 | 0300803019 | Region III (Central Luzon) | Bataan | City of Balanga | Talisay | 14.6811 | 120.5454 | R | 2278 | 632 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N55 | FTAP Smart | 14.6842 | 120.5412 | 0.57 | Terrestrial Optical Fiber Drop | 0.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0446 | 1 | 446 | 446 | 0203105005 | Region II (Cagayan Valley) | Isabela | Burgos | Catabban | 17.0303 | 121.7419 | R | 1768 | 465 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0034 | LDIC | 121.7481 | 17.0468 | 1.95 | Terrestrial Optical Fiber Drop | 0.28 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0447 | 1 | 447 | 447 | 0401004009 | Region IV-A (CALABARZON) | Batangas | Balete | Poblacion | 14.02 | 121.0938 | R | 2357 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 0.92 | Terrestrial Optical Fiber Drop | 0.28 | 7.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0448 | 1 | 448 | 448 | 1381300077 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Pansol | 14.6659 | 121.0713 | U | 35572 | 8915 | 2675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01443 | Edgepoint | 14.6661 | 121.0725 | 0.13 | Terrestrial Optical Fiber Drop | 0.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0449 | 1 | 449 | 449 | 1381000006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Tambo | 14.5167 | 120.9969 | U | 35356 | 9607 | 2882 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | H18 | FTAP Smart | 14.5163 | 120.995 | 0.21 | Terrestrial Optical Fiber Drop | 0.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0450 | 1 | 450 | 450 | 1380500004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Barangka Ibaba | 14.5733 | 121.0381 | U | 9473 | 2794 | 838 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02522 | Edgepoint | 14.5811 | 121.0289 | 0.1 | Terrestrial Optical Fiber Drop | 1.27 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0451 | 1 | 451 | 451 | 0501733020 | Region V (Bicol Region) | Camarines Sur | San Jose | Salogon | 13.6992 | 123.5183 | R | 3170 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 0.36 | Terrestrial Optical Fiber Drop | 0.29 | 2.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0452 | 1 | 452 | 452 | 0307111003 | Region III (Central Luzon) | Zambales | San Marcelino | Burgos | 14.9791 | 120.1551 | R | 2260 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00974 | Edgepoint | 14.9764 | 120.153 | 0.37 | Terrestrial Optical Fiber Drop | 0.28 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0453 | 1 | 453 | 453 | 0501712020 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Poblacion Zone III | 13.9228 | 122.5968 | R | 1521 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050037 | FTAP Globe | 13.9255 | 122.5947 | 0.38 | Terrestrial Optical Fiber Drop | 0.29 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0454 | 1 | 454 | 454 | 0405639018 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Roque | 14.1599 | 121.6375 | R | 2487 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.27 | Terrestrial Optical Fiber Drop | 0.29 | 9.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0455 | 1 | 455 | 455 | 0603018021 | Region VI (Western Visayas) | Iloilo | Dumangas | Ilaya 1st | 10.827 | 122.7121 | R | 682 | 179 | 54 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.03 | Terrestrial Optical Fiber Drop | 0.29 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0456 | 1 | 456 | 456 | 0504103030 | Region V (Bicol Region) | Masbate | Balud | Tonga | 12.0681 | 123.2379 | R | 1044 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050256 | FTAP Globe | 12.0387 | 123.1919 | 5.98 | Terrestrial Optical Fiber Drop | 0.29 | 14.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0457 | 1 | 457 | 457 | 0405630021 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 3 Del Carmen | 13.9695 | 121.6834 | R | 1381 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.18 | Terrestrial Optical Fiber Drop | 0.29 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0458 | 1 | 458 | 458 | 0402104011 | Region IV-A (CALABARZON) | Cavite | Carmona | Milagrosa | 14.3083 | 121.0494 | U | 25103 | 7383 | 2215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040182 | FTAP Globe | 14.3107 | 121.0494 | 0.26 | Terrestrial Optical Fiber Drop | 0.29 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0459 | 1 | 459 | 459 | 0403408001 | Region IV-A (CALABARZON) | Laguna | Famy | Asana | 14.4381 | 121.4495 | R | 582 | 176 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040101 | FTAP Globe | 14.4377 | 121.4463 | 0.35 | Terrestrial Optical Fiber Drop | 0.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0460 | 1 | 460 | 460 | 0103306026 | Region I (Ilocos Region) | La Union | Bangar | Central East No. 2 | 16.8957 | 120.4241 | R | 1049 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.07 | Terrestrial Optical Fiber Drop | 0.29 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0461 | 1 | 461 | 461 | 1004324006 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Poblacion | 8.5373 | 124.7553 | U | 10662 | 2733 | 820 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0098 | PTCI/MIDC | 8.5402 | 124.755 | 0.32 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0462 | 1 | 462 | 462 | 0803714016 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone II | 11.2931 | 124.6381 | R | 4790 | 1260 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 1.89 | Terrestrial Optical Fiber Drop | 0.29 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0463 | 1 | 463 | 463 | 0105535008 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Sur | 16.0636 | 120.6672 | R | 4860 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00422 | Edgepoint | 16.0668 | 120.6701 | 0.47 | Terrestrial Optical Fiber Drop | 0.29 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0464 | 1 | 464 | 464 | 0603026019 | Region VI (Western Visayas) | Iloilo | Leganes | Poblacion | 10.7882 | 122.5899 | U | 3436 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.37 | Terrestrial Optical Fiber Drop | 0.29 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0465 | 1 | 465 | 465 | 0702245008 | Region VII (Central Visayas) | Cebu | Santander | Poblacion | 9.4173 | 123.334 | R | 2968 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0153 | PTCI/MIDC | 9.4196 | 123.3343 | 0.26 | Terrestrial Optical Fiber Drop | 0.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0466 | 1 | 466 | 466 | 1102403028 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 1 | 6.7576 | 125.3554 | U | 17556 | 5163 | 1549 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0071 | PTCI/MIDC | 6.7534 | 125.365 | 1.17 | Terrestrial Optical Fiber Drop | 0.29 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0467 | 1 | 467 | 467 | 0102819016 | Region I (Ilocos Region) | Ilocos Norte | Pinili | Pagdilao | 17.9511 | 120.5259 | R | 1159 | 313 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01219-B05 | PTCI/MIDC | 17.9518 | 120.5224 | 0.37 | Terrestrial Optical Fiber Drop | 0.29 | 3.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0468 | 1 | 468 | 468 | 0701232016 | Region VII (Central Visayas) | Bohol | Maribojoc | Poblacion | 9.7395 | 123.844 | R | 2098 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070413 | FTAP Globe | 9.7455 | 123.842 | 0.7 | Terrestrial Optical Fiber Drop | 0.3 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0469 | 1 | 469 | 469 | 0401034013 | Region IV-A (CALABARZON) | Batangas | Tuy | Luna | 14.0212 | 120.7311 | R | 2745 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.44 | Terrestrial Optical Fiber Drop | 0.29 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0470 | 1 | 470 | 470 | 0603017048 | Region VI (Western Visayas) | Iloilo | Dueñas | Poblacion A | 11.0667 | 122.6169 | R | 1432 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0018 | PTCI/MIDC | 11.065 | 122.622 | 0.58 | Terrestrial Optical Fiber Drop | 0.3 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0471 | 1 | 471 | 471 | 0506206029 | Region V (Bicol Region) | Sorsogon | Castilla | San Isidro | 12.9736 | 123.8402 | R | 4377 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-02708 | Edgepoint | 12.9755 | 123.847 | 0.76 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0472 | 1 | 472 | 472 | 0604531007 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay IV | 10.9009 | 123.0777 | R | 1183 | 319 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.5 | Terrestrial Optical Fiber Drop | 0.51 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0473 | 1 | 473 | 473 | 0501726017 | Region V (Bicol Region) | Camarines Sur | Pamplona | Tambo | 13.5783 | 123.0639 | U | 4221 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050103 | FTAP Globe | 13.5641 | 123.0576 | 1.72 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0474 | 1 | 474 | 474 | 0405603041 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tinandog | 13.9963 | 121.9121 | R | 1260 | 331 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | B55 | FTAP Smart | 13.998 | 121.9283 | 0.33 | Terrestrial Optical Fiber Drop | 1.51 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0475 | 1 | 475 | 475 | 0301423002 | Region III (Central Luzon) | Bulacan | Santa Maria | Balasing | 14.8506 | 121.0019 | U | 10173 | 2906 | 872 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01122 | Edgepoint | 14.8505 | 121.0044 | 0.27 | Terrestrial Optical Fiber Drop | 0.3 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0476 | 1 | 476 | 476 | 1705205049 | MIMAROPA Region | Oriental Mindoro | City of Calapan | San Antonio | 13.4261 | 121.1956 | U | 3564 | 913 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 0.4 | Terrestrial Optical Fiber Drop | 0.3 | 6.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0477 | 1 | 477 | 477 | 0403426026 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Sur | 14.2812 | 121.4113 | U | 4457 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.34 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0478 | 1 | 478 | 478 | 0405607017 | Region IV-A (CALABARZON) | Quezon | Calauag | Barangay V | 13.9582 | 122.2897 | R | 961 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040424 | FTAP Globe | 13.9534 | 122.2876 | 0.58 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0479 | 1 | 479 | 479 | 0203131029 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone III | 16.9877 | 122.0143 | R | 3856 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.83 | Terrestrial Optical Fiber Drop | 0.3 | 16.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0480 | 1 | 480 | 480 | 0500517007 | Region V (Bicol Region) | Albay | City of Tabaco | Basud | 13.3541 | 123.7289 | U | 2697 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050129 | FTAP Globe | 13.3576 | 123.7292 | 0.39 | Terrestrial Optical Fiber Drop | 0.3 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0481 | 1 | 481 | 481 | 0300810016 | Region III (Central Luzon) | Bataan | Orion | Kapunitan | 14.6163 | 120.5817 | R | 4322 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0002 | PTCI/MIDC | 14.6145 | 120.5801 | 0.26 | Terrestrial Optical Fiber Drop | 0.3 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0482 | 1 | 482 | 482 | 0403424036 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Del Remedio | 14.0815 | 121.3137 | U | 19590 | 5936 | 1781 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040337 | FTAP Globe | 14.0845 | 121.3149 | 0.35 | Terrestrial Optical Fiber Drop | 0.3 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0483 | 1 | 483 | 483 | 0405641014 | Region IV-A (CALABARZON) | Quezon | San Antonio | Poblacion | 13.8904 | 121.2872 | R | 2007 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03161-C08 | PTCI/MIDC | 13.8725 | 121.2905 | 2.03 | Terrestrial Optical Fiber Drop | 0.3 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0484 | 1 | 484 | 484 | 0105527011 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Bogtong Silag | 15.8127 | 120.2812 | R | 1901 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-02360 | Edgepoint | 15.8237 | 120.2701 | 1.71 | Terrestrial Optical Fiber Drop | 0.3 | 14.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0485 | 1 | 485 | 485 | 0304931014 | Region III (Central Luzon) | Nueva Ecija | Talugtug | Osmeña | 15.7783 | 120.8138 | R | 1191 | 340 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030317 | FTAP Globe | 15.7792 | 120.8099 | 0.43 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0486 | 1 | 486 | 486 | 0201508016 | Region II (Cagayan Valley) | Cagayan | Buguey | Pattao | 18.2481 | 121.8158 | R | 3799 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0006 | LDIC | 18.2476 | 121.8139 | 0.21 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0487 | 1 | 487 | 487 | 0102820002 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Ildefonso | 18.1728 | 120.5946 | R | 1769 | 478 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.08 | Terrestrial Optical Fiber Drop | 0.3 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0488 | 1 | 488 | 488 | 0405618010 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Calimpak | 13.9007 | 122.4515 | U | 5082 | 1337 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040512 | FTAP Globe | 13.8986 | 122.4538 | 0.34 | Terrestrial Optical Fiber Drop | 0.3 | 11.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0489 | 1 | 489 | 489 | 1004317008 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Consuelo | 8.9155 | 125.1874 | R | 4051 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0062 | PTCI/MIDC | 8.9119 | 125.1864 | 0.41 | Terrestrial Optical Fiber Drop | 0.3 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0490 | 1 | 490 | 490 | 0402116001 | Region IV-A (CALABARZON) | Cavite | Noveleta | Magdiwang | 14.4313 | 120.8798 | U | 2351 | 691 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.29 | Terrestrial Optical Fiber Drop | 0.39 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0491 | 1 | 491 | 491 | 0500507005 | Region V (Bicol Region) | Albay | Libon | Zone II | 13.2982 | 123.4415 | R | 1085 | 264 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.28 | Terrestrial Optical Fiber Drop | 0.3 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0492 | 1 | 492 | 492 | 0203119006 | Region II (Cagayan Valley) | Isabela | Mallig | Maligaya | 17.1847 | 121.6121 | R | 2493 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03318-B06 | PTCI/MIDC | 17.184 | 121.6115 | 0.1 | Terrestrial Optical Fiber Drop | 0.3 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0493 | 1 | 493 | 493 | 0601912020 | Region VI (Western Visayas) | Capiz | Pontevedra | Ilaya | 11.4795 | 122.8317 | R | 972 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAP_0003 | LDIC | 11.4838 | 122.8327 | 0.49 | Terrestrial Optical Fiber Drop | 0.3 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0494 | 1 | 494 | 494 | 1404409014 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Poblacion | 17.085 | 120.8979 | U | 1411 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01407-B05 | PTCI/MIDC | 17.0819 | 120.9043 | 0.77 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0495 | 1 | 495 | 495 | 0306911014 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 3 | 15.6242 | 120.6485 | R | 1243 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.07 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0496 | 1 | 496 | 496 | 0405647003 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone I | 14.0223 | 121.5959 | R | 1781 | 468 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1446 | FTAP Smart | 14.0221 | 121.5973 | 0.15 | Terrestrial Optical Fiber Drop | 0.31 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0497 | 1 | 497 | 497 | 0401031046 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Talaga | 14.1034 | 121.097 | U | 5766 | 1601 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040316 | FTAP Globe | 14.1024 | 121.0968 | 0.11 | Terrestrial Optical Fiber Drop | 0.31 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0498 | 1 | 498 | 498 | 0103311025 | Region I (Ilocos Region) | La Union | Naguilian | Magungunay | 16.4743 | 120.4064 | R | 872 | 235 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 0.82 | Terrestrial Optical Fiber Drop | 6.09 | 7.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0499 | 1 | 499 | 499 | 1408106014 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Mataguisi | 18.1287 | 121.3478 | R | 1114 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140103 | FTAP Globe | 18.1451 | 121.4478 | 10.72 | Terrestrial Optical Fiber Drop | 0.31 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0500 | 1 | 500 | 500 | 1004309009 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Poblacion | 8.5952 | 124.4068 | R | 3192 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100118 | FTAP Globe | 8.5922 | 124.3873 | 2.18 | Terrestrial Optical Fiber Drop | 0.31 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0501 | 1 | 501 | 501 | 0401019009 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 4 | 14.0735 | 120.6335 | R | 1373 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01947-C08 | PTCI/MIDC | 14.0724 | 120.6355 | 0.25 | Terrestrial Optical Fiber Drop | 0.31 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0502 | 1 | 502 | 502 | 0203126013 | Region II (Cagayan Valley) | Isabela | Roxas | Bantug | 17.1144 | 121.6129 | U | 5908 | 1554 | 466 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0060 | PTCI/MIDC | 17.1203 | 121.6155 | 0.72 | Terrestrial Optical Fiber Drop | 0.31 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0503 | 1 | 503 | 503 | 0401029015 | Region IV-A (CALABARZON) | Batangas | Taal | Ilog | 13.8926 | 120.9315 | R | 1437 | 399 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040516 | FTAP Globe | 13.893 | 120.9287 | 0.46 | Terrestrial Optical Fiber Drop | 0.94 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0504 | 1 | 504 | 504 | 0307706009 | Region III (Central Luzon) | Aurora | Dipaculao | Dinadiawan | 16.0772 | 121.7706 | R | 3215 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02908-B06 | PTCI/MIDC | 16.0788 | 121.768 | 0.32 | Terrestrial Optical Fiber Drop | 0.31 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0505 | 1 | 505 | 505 | 0301423018 | Region III (Central Luzon) | Bulacan | Santa Maria | San Gabriel | 14.8069 | 120.9585 | U | 10066 | 2876 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02211 | Edgepoint | 14.8035 | 120.9555 | 0.5 | Terrestrial Optical Fiber Drop | 0.31 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0506 | 1 | 506 | 506 | 0306903027 | Region III (Central Luzon) | Tarlac | Camiling | Malacampa | 15.6402 | 120.4118 | U | 6156 | 1578 | 473 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00623 | Edgepoint | 15.6378 | 120.4097 | 0.35 | Terrestrial Optical Fiber Drop | 0.31 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0507 | 1 | 507 | 507 | 0103305012 | Region I (Ilocos Region) | La Union | Balaoan | Cabuaan Oeste | 16.8014 | 120.4186 | R | 1221 | 330 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00255 | Edgepoint | 16.8196 | 120.4033 | 0.42 | Terrestrial Optical Fiber Drop | 2.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0508 | 1 | 508 | 508 | 0330100001 | Region III (Central Luzon) | Pampanga | City of Angeles | Agapito del Rosario | 15.1494 | 120.5926 | U | 2669 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 538 | FTAP Smart | 15.15 | 120.591 | 0.15 | Terrestrial Optical Fiber Drop | 0.25 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0509 | 1 | 509 | 509 | 0506207034 | Region V (Bicol Region) | Sorsogon | Donsol | Rawis | 12.9034 | 123.5959 | R | 2324 | 581 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050213 | FTAP Globe | 12.9091 | 123.5966 | 0.64 | Terrestrial Optical Fiber Drop | 0.31 | 18.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0510 | 1 | 510 | 510 | 1705320021 | MIMAROPA Region | Palawan | Taytay | Pularaquen | 10.9559 | 119.4853 | R | 3467 | 888 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S2220 | FTAP Smart | 11.02 | 119.4203 | 10.06 | Terrestrial Optical Fiber Drop | 0.31 | 15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0511 | 1 | 511 | 511 | 1001320021 | Region X (Northern Mindanao) | Bukidnon | Talakag | Barangay 3 | 8.2347 | 124.6002 | R | 1641 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0044 | PTCI/MIDC | 8.235 | 124.6022 | 0.22 | Terrestrial Optical Fiber Drop | 0.31 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0512 | 1 | 512 | 512 | 0600402011 | Region VI (Western Visayas) | Aklan | Balete | Poblacion | 11.5573 | 122.3783 | R | 899 | 230 | 69 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 2.48 | Terrestrial Optical Fiber Drop | 0.31 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0513 | 1 | 513 | 513 | 0306907003 | Region III (Central Luzon) | Tarlac | La Paz | Caramutan | 15.4454 | 120.7197 | U | 4566 | 1170 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.92 | Terrestrial Optical Fiber Drop | 0.31 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0514 | 1 | 514 | 514 | 0305415033 | Region III (Central Luzon) | Pampanga | Porac | Sinura | 15.1161 | 120.57 | R | 3859 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01636-B07 | PTCI/MIDC | 15.113 | 120.5717 | 0.39 | Terrestrial Optical Fiber Drop | 0.31 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0515 | 1 | 515 | 515 | 1380900001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Sipac-Almacen | 14.6583 | 120.9483 | U | 9097 | 2614 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000482 | FTAP Globe | 14.6587 | 120.9471 | 0.13 | Terrestrial Optical Fiber Drop | 0.31 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0516 | 1 | 516 | 516 | 0402109075 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion II-B | 14.4051 | 120.9263 | R | 1605 | 472 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.39 | Terrestrial Optical Fiber Drop | 1.56 | 4.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0517 | 1 | 517 | 517 | 0307104012 | Region III (Central Luzon) | Zambales | Castillejos | San Nicolas | 14.927 | 120.2016 | R | 4602 | 1211 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.36 | Terrestrial Optical Fiber Drop | 0.31 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0518 | 1 | 518 | 518 | 0401023029 | Region IV-A (CALABARZON) | Batangas | San Juan | Poblacion | 13.8272 | 121.3943 | U | 3208 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01956-C08 | PTCI/MIDC | 13.8259 | 121.3951 | 0.17 | Terrestrial Optical Fiber Drop | 0.31 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1043 | 1 | 519 | 519 | 0401006022 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Proper | 13.7944 | 120.9978 | U | 11200 | 3111 | 933 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B15 | FTAP Smart | 13.7981 | 120.9984 | 0.41 | Terrestrial Optical Fiber Drop | 0.55 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0520 | 1 | 520 | 520 | 0701230036 | Region VII (Central Visayas) | Bohol | Loon | Cogon Norte | 9.8033 | 123.8002 | R | 2127 | 531 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 1.09 | Terrestrial Optical Fiber Drop | 0.31 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0521 | 1 | 521 | 521 | 0305417014 | Region III (Central Luzon) | Pampanga | San Luis | Santa Monica | 15.0364 | 120.7896 | R | 3403 | 850 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02210 | Edgepoint | 15.0355 | 120.7875 | 0.25 | Terrestrial Optical Fiber Drop | 0.32 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0522 | 1 | 522 | 522 | 0501736022 | Region V (Bicol Region) | Camarines Sur | Tigaon | Talojongon | 13.6277 | 123.4963 | U | 4109 | 978 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 0.74 | Terrestrial Optical Fiber Drop | 0.32 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0523 | 1 | 523 | 523 | 0205704014 | Region II (Cagayan Valley) | Quirino | Maddela | Lusod | 16.334 | 121.6792 | R | 1908 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0003 | LDIC | 121.6809 | 16.3353 | 0.23 | Terrestrial Optical Fiber Drop | 0.32 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0524 | 1 | 524 | 524 | 0702247016 | Region VII (Central Visayas) | Cebu | Sogod | Poblacion | 10.7491 | 124.0048 | R | 3637 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 0.43 | Terrestrial Optical Fiber Drop | 0.32 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0525 | 1 | 525 | 525 | 0405627024 | Region IV-A (CALABARZON) | Quezon | Mauban | Polo | 14.1771 | 121.7166 | U | 3775 | 993 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02130-C08 | PTCI/MIDC | 14.1755 | 121.7259 | 1.02 | Terrestrial Optical Fiber Drop | 0.32 | 17.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0526 | 1 | 526 | 526 | 0205014001 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Sur | 16.5783 | 121.1888 | R | 3354 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00302 | Edgepoint | 16.5766 | 121.1908 | 0.29 | Terrestrial Optical Fiber Drop | 0.32 | 5.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0527 | 1 | 527 | 527 | 0201502010 | Region II (Cagayan Valley) | Cagayan | Alcala | Centro Norte | 17.9027 | 121.6547 | R | 2228 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0061 | LDIC | 121.6537 | 17.9074 | 0.54 | Terrestrial Optical Fiber Drop | 0.32 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0528 | 1 | 528 | 528 | 0201506019 | Region II (Cagayan Valley) | Cagayan | Baggao | Poblacion | 17.9344 | 121.7718 | U | 3504 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01180-B06 | PTCI/MIDC | 17.932 | 121.7711 | 0.27 | Terrestrial Optical Fiber Drop | 0.32 | 9.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0529 | 1 | 529 | 529 | 0304932017 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Vicente | 15.4546 | 120.7904 | R | 1703 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03332-B07 | PTCI/MIDC | 15.445 | 120.791 | 1.07 | Terrestrial Optical Fiber Drop | 0.32 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0530 | 1 | 530 | 530 | 0301415019 | Region III (Central Luzon) | Bulacan | Pandi | Siling Bata | 14.8924 | 120.97 | U | 13147 | 3756 | 1127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030556 | FTAP Globe | 14.8934 | 120.9692 | 0.14 | Terrestrial Optical Fiber Drop | 0.32 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0531 | 1 | 531 | 531 | 1380800004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Muntinlupa | Cupang | 14.4304 | 121.0495 | U | 57482 | 14334 | 4300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.82 | Terrestrial Optical Fiber Drop | 0.28 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0532 | 1 | 532 | 532 | 0401001015 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Poblacion | 13.934 | 120.9344 | U | 1923 | 534 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01944-C08 | PTCI/MIDC | 13.9385 | 120.9342 | 0.49 | Terrestrial Optical Fiber Drop | 0.32 | 4.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0533 | 1 | 533 | 533 | 1102315029 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Francisco | 7.3033 | 125.6813 | U | 14187 | 3834 | 1150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0119 | PTCI/MIDC | 7.304 | 125.6832 | 0.22 | Terrestrial Optical Fiber Drop | 0.32 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0534 | 1 | 534 | 534 | 0301419001 | Region III (Central Luzon) | Bulacan | San Ildefonso | Akle | 15.0484 | 121.0715 | U | 4864 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030489 | FTAP Globe | 15.0501 | 121.062 | 1.03 | Terrestrial Optical Fiber Drop | 0.32 | 6.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0535 | 1 | 535 | 535 | 0102818003 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Anao | 18.168 | 120.7195 | R | 1253 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 3987 | FTAP Smart | 18.1615 | 120.7123 | 0.4 | Terrestrial Optical Fiber Drop | 0.6 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0536 | 1 | 536 | 536 | 0501726009 | Region V (Bicol Region) | Camarines Sur | Pamplona | Poblacion | 13.5915 | 123.0795 | U | 6227 | 1482 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 0.49 | Terrestrial Optical Fiber Drop | 0.32 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0537 | 1 | 537 | 537 | 0402110026 | Region IV-A (CALABARZON) | Cavite | Indang | Barangay 4 | 14.2 | 120.8734 | U | 2496 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0034 | FTAP Smart | 14.1948 | 120.8764 | 0.66 | Terrestrial Optical Fiber Drop | 0.32 | 8.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0538 | 1 | 538 | 538 | 0201505037 | Region II (Cagayan Valley) | Cagayan | Aparri | Punta | 18.3587 | 121.6344 | U | 4977 | 1276 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02764-B06 | PTCI/MIDC | 18.3593 | 121.6365 | 0.23 | Terrestrial Optical Fiber Drop | 0.32 | 10.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0539 | 1 | 539 | 539 | 0501703004 | Region V (Bicol Region) | Camarines Sur | Bato | Caricot | 13.3561 | 123.3639 | R | 542 | 129 | 39 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.47 | Terrestrial Optical Fiber Drop | 0.32 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0540 | 1 | 540 | 540 | 0401004010 | Region IV-A (CALABARZON) | Batangas | Balete | Sala | 14.0199 | 121.1017 | R | 1786 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 1.03 | Terrestrial Optical Fiber Drop | 0.55 | 6.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0541 | 1 | 541 | 541 | 0306917025 | Region III (Central Luzon) | Tarlac | Victoria | San Vicente | 15.5775 | 120.6813 | R | 2286 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.67 | Terrestrial Optical Fiber Drop | 0.43 | 6.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0542 | 1 | 542 | 542 | 0305417012 | Region III (Central Luzon) | Pampanga | San Luis | Santa Cruz Poblacion | 15.041 | 120.7908 | U | 1868 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.21 | Terrestrial Optical Fiber Drop | 0.32 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0543 | 1 | 543 | 543 | 1381200024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Santa Cruz | 14.563 | 121.0791 | U | 5821 | 1653 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02395-A02 | PTCI/MIDC | 14.5632 | 121.0804 | 0.14 | Terrestrial Optical Fiber Drop | 0.33 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0544 | 1 | 544 | 544 | 0500510010 | Region V (Bicol Region) | Albay | Malinao | Comun | 13.3437 | 123.6629 | R | 1845 | 450 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 3.19 | Terrestrial Optical Fiber Drop | 0.33 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0545 | 1 | 545 | 545 | 0603009003 | Region VI (Western Visayas) | Iloilo | Batad | Banban | 11.4184 | 123.1111 | R | 388 | 102 | 31 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.57 | Terrestrial Optical Fiber Drop | 0.33 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0546 | 1 | 546 | 546 | 1606819022 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Telaje | 17.105 | 122.2744 | U | 7962 | 1941 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.13 | Terrestrial Optical Fiber Drop | 27.56 | 37.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0547 | 1 | 547 | 547 | 0105524062 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Poblacion | 15.9233 | 120.4127 | U | 8389 | 2330 | 699 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00528 | Edgepoint | 15.9293 | 120.4132 | 0.67 | Terrestrial Optical Fiber Drop | 0.33 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0548 | 1 | 548 | 548 | 1381200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Antonio | 14.5668 | 121.0848 | U | 14904 | 4151 | 1245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 414 | FTAP Smart | 14.5695 | 121.0843 | 0.3 | Terrestrial Optical Fiber Drop | 0.33 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0549 | 1 | 549 | 549 | 0301423016 | Region III (Central Luzon) | Bulacan | Santa Maria | Poblacion | 14.822 | 120.9625 | U | 13454 | 3844 | 1153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030596 | FTAP Globe | 14.8198 | 120.9635 | 0.26 | Terrestrial Optical Fiber Drop | 0.33 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0550 | 1 | 550 | 550 | 0301403030 | Region III (Central Luzon) | Bulacan | Baliuag | Virgen delas Flores | 14.9458 | 120.886 | U | 7686 | 2196 | 659 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03207-B07 | PTCI/MIDC | 14.9436 | 120.8816 | 0.53 | Terrestrial Optical Fiber Drop | 0.33 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0551 | 1 | 551 | 551 | 0504113019 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. I | 12.3373 | 123.6557 | R | 1891 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.38 | Terrestrial Optical Fiber Drop | 0.33 | 4.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0552 | 1 | 552 | 552 | 1705206023 | MIMAROPA Region | Oriental Mindoro | Gloria | Narra | 12.9564 | 121.4778 | R | 2934 | 752 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 1.69 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0553 | 1 | 553 | 553 | 0405616022 | Region IV-A (CALABARZON) | Quezon | General Luna | San Jose | 13.6937 | 122.1715 | R | 2076 | 546 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040603 | FTAP Globe | 13.6919 | 122.1735 | 0.3 | Terrestrial Optical Fiber Drop | 0.33 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0554 | 1 | 554 | 554 | 0403413015 | Region IV-A (CALABARZON) | Laguna | Lumban | Santo Niño | 14.2985 | 121.4615 | R | 1206 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.16 | Terrestrial Optical Fiber Drop | 0.33 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0555 | 1 | 555 | 555 | 0305417006 | Region III (Central Luzon) | Pampanga | San Luis | San Nicolas | 15.041 | 120.7908 | R | 1941 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.22 | Terrestrial Optical Fiber Drop | 0.33 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0556 | 1 | 556 | 556 | 0205005026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | San Nicolas North | 16.4878 | 121.1501 | R | 2608 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.29 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0557 | 1 | 557 | 557 | 0501706029 | Region V (Bicol Region) | Camarines Sur | Bula | San Roque | 13.4695 | 123.2764 | R | 2440 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.33 | Terrestrial Optical Fiber Drop | 0.33 | 5.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0558 | 1 | 558 | 558 | 1004301010 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Poblacion | 8.5731 | 124.473 | R | 3800 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100122 | FTAP Globe | 8.5696 | 124.4727 | 0.38 | Terrestrial Optical Fiber Drop | 0.33 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0559 | 1 | 559 | 559 | 1004322011 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Poblacion | 8.8592 | 124.7901 | U | 6231 | 1597 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 0.64 | Terrestrial Optical Fiber Drop | 0.33 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0560 | 1 | 560 | 560 | 0702216014 | Region VII (Central Visayas) | Cebu | Catmon | Macaas | 10.6961 | 124.0119 | R | 3612 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070059 | FTAP BTS | 10.7094 | 124.0134 | 1.49 | Terrestrial Optical Fiber Drop | 0.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0561 | 1 | 561 | 561 | 0301415016 | Region III (Central Luzon) | Bulacan | Pandi | Poblacion | 14.8664 | 120.9562 | U | 9072 | 2592 | 778 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01095 | Edgepoint | 14.8658 | 120.955 | 0.15 | Terrestrial Optical Fiber Drop | 0.33 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0562 | 1 | 562 | 562 | 0401027004 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Calayaan | 13.8776 | 120.9666 | R | 2389 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040522 | FTAP Globe | 13.8841 | 120.9487 | 1.78 | Terrestrial Optical Fiber Drop | 0.08 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0563 | 1 | 563 | 563 | 0402108015 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Manggahan | 14.2966 | 120.9118 | U | 20805 | 6119 | 1836 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02219-C08 | PTCI/MIDC | 14.2984 | 120.9147 | 0.37 | Terrestrial Optical Fiber Drop | 0.33 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0564 | 1 | 564 | 564 | 0704625010 | Region VII (Central Visayas) | Negros Oriental | Zamboanguita | Poblacion | 9.101 | 123.1991 | U | 6716 | 1767 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0057 | PTCI/MIDC | 9.0988 | 123.1959 | 0.43 | Terrestrial Optical Fiber Drop | 0.33 | 16.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0565 | 1 | 565 | 565 | 1004321014 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Poblacion | 8.5205 | 124.5718 | U | 3486 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100132 | FTAP Globe | 8.5148 | 124.5755 | 0.75 | Terrestrial Optical Fiber Drop | 0.33 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0566 | 1 | 566 | 566 | 0431200011 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 8 | 13.9301 | 121.6114 | U | 4021 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02698 | Edgepoint | 13.9316 | 121.6129 | 0.22 | Terrestrial Optical Fiber Drop | 0.34 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0567 | 1 | 567 | 567 | 0402122003 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Cabuco | 14.2676 | 120.8472 | U | 40657 | 11957 | 3587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03415-C08 | PTCI/MIDC | 14.274 | 120.8536 | 0.99 | Terrestrial Optical Fiber Drop | 0.34 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0568 | 1 | 568 | 568 | 0402102011 | Region IV-A (CALABARZON) | Cavite | Amadeo | Barangay I | 14.1672 | 120.924 | R | 1633 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02223-C08 | PTCI/MIDC | 14.1743 | 120.9201 | 0.89 | Terrestrial Optical Fiber Drop | 0.34 | 3.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0569 | 1 | 569 | 569 | 1402703018 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Poblacion | 16.7774 | 121.084 | R | 1576 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02598-B05 | PTCI/MIDC | 16.7758 | 121.0866 | 0.33 | Terrestrial Optical Fiber Drop | 0.34 | 3.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0570 | 1 | 570 | 570 | 1381100081 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 81 | 14.5433 | 120.9981 | U | 2479 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00293-A03 | PTCI/MIDC | 14.4377 | 121.0059 | 0.36 | Terrestrial Optical Fiber Drop | 0.41 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0571 | 1 | 571 | 571 | 0203135033 | Region II (Cagayan Valley) | Isabela | City of Santiago | Sinsayon | 16.691 | 121.5246 | U | 3782 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0053 | PTCI/MIDC | 16.6938 | 121.5261 | 0.35 | Terrestrial Optical Fiber Drop | 0.34 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0572 | 1 | 572 | 572 | 0401008017 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 2 | 13.8331 | 120.63 | R | 1446 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 0.38 | Terrestrial Optical Fiber Drop | 0.34 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0573 | 1 | 573 | 573 | 1401107017 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Poblacion | 16.623 | 120.8387 | R | 1970 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N2018 | FTAP Smart | 16.6305 | 120.8313 | 1.14 | Terrestrial Optical Fiber Drop | 0.34 | 7.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0574 | 1 | 574 | 574 | 0600415008 | Region VI (Western Visayas) | Aklan | New Washington | Lawa-an | 11.6508 | 122.4333 | R | 1562 | 400 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.79 | Terrestrial Optical Fiber Drop | 0.34 | 7.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0575 | 1 | 575 | 575 | 0403413002 | Region IV-A (CALABARZON) | Laguna | Lumban | Balimbingan | 14.2984 | 121.4616 | R | 1153 | 349 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.55 | Terrestrial Optical Fiber Drop | 0.32 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0576 | 1 | 576 | 576 | 1381200022 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Miguel | 14.5669 | 121.0847 | U | 44629 | 13087 | 3926 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 414 | FTAP Smart | 14.5695 | 121.0843 | 0.29 | Terrestrial Optical Fiber Drop | 0.34 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0577 | 1 | 577 | 577 | 0601914032 | Region VI (Western Visayas) | Capiz | City of Roxas | Lanot | 11.5177 | 122.7551 | U | 6661 | 1752 | 526 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02814-D13 | PTCI/MIDC | 11.5219 | 122.7569 | 0.51 | Terrestrial Optical Fiber Drop | 0.34 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0578 | 1 | 578 | 578 | 0301418022 | Region III (Central Luzon) | Bulacan | Pulilan | Poblacion | 14.9041 | 120.8481 | U | 13958 | 3988 | 1196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01118-B07 | PTCI/MIDC | 14.9024 | 120.8479 | 0.18 | Terrestrial Optical Fiber Drop | 0.34 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0579 | 1 | 579 | 579 | 0704601004 | Region VII (Central Visayas) | Negros Oriental | Amlan | Mag-abo | 9.4642 | 123.2206 | R | 2265 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070259 | FTAP Globe | 9.4593 | 123.2167 | 0.7 | Terrestrial Optical Fiber Drop | 0.34 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0580 | 1 | 580 | 580 | 0105514030 | Region I (Ilocos Region) | Pangasinan | Bolinao | Victory | 16.3866 | 119.8929 | R | 1415 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00346 | Edgepoint | 16.3802 | 119.8939 | 0.72 | Terrestrial Optical Fiber Drop | 0.34 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0581 | 1 | 581 | 581 | 0501725016 | Region V (Bicol Region) | Camarines Sur | Ocampo | Poblacion West | 13.5591 | 123.3747 | R | 894 | 212 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.72 | Terrestrial Optical Fiber Drop | 0.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0582 | 1 | 582 | 582 | 0102806011 | Region I (Ilocos Region) | Ilocos Norte | Burgos | Poblacion | 18.5124 | 120.6439 | R | 1490 | 402 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-02617 | Edgepoint | 18.5104 | 120.6401 | 0.45 | Terrestrial Optical Fiber Drop | 0.34 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0583 | 1 | 583 | 583 | 0203134016 | Region II (Cagayan Valley) | Isabela | Santa Maria | San Antonio | 17.4771 | 121.7575 | R | 1561 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0016 | LDIC | 121.7628 | 17.4833 | 0.89 | Terrestrial Optical Fiber Drop | 0.34 | 4.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0584 | 1 | 584 | 584 | 0603009002 | Region VI (Western Visayas) | Iloilo | Batad | Alinsolong | 11.4183 | 123.1111 | R | 1335 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.59 | Terrestrial Optical Fiber Drop | 0.34 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0585 | 1 | 585 | 585 | 0501709015 | Region V (Bicol Region) | Camarines Sur | Camaligan | Santo Tomas | 13.621 | 123.1656 | R | 705 | 167 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.5 | Terrestrial Optical Fiber Drop | 0.7 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0586 | 1 | 586 | 586 | 0304921008 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Poblacion III | 15.3516 | 121.001 | R | 1405 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0184 | FTAP Smart | 15.3526 | 121.0171 | 0.46 | Terrestrial Optical Fiber Drop | 1.74 | 6.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0587 | 1 | 587 | 587 | 0300810001 | Region III (Central Luzon) | Bataan | Orion | Arellano | 14.618 | 120.5771 | R | 539 | 149 | 45 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0398 | FTAP Smart | 14.6168 | 120.5791 | 0.42 | Terrestrial Optical Fiber Drop | 0.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0588 | 1 | 588 | 588 | 0405802009 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Roque | 14.5844 | 121.1737 | U | 67126 | 18646 | 5594 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01743 | Edgepoint | 14.5861 | 121.1735 | 0.18 | Terrestrial Optical Fiber Drop | 0.35 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0589 | 1 | 589 | 589 | 0405812005 | Region IV-A (CALABARZON) | Rizal | Tanay | Kaybuto | 14.4976 | 121.2811 | U | 8757 | 2432 | 730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00800-A04 | PTCI/MIDC | 14.4978 | 121.2849 | 0.41 | Terrestrial Optical Fiber Drop | 0.35 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0590 | 1 | 590 | 590 | 0105514011 | Region I (Ilocos Region) | Pangasinan | Bolinao | Germinal | 16.3861 | 119.894 | U | 2899 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00346 | Edgepoint | 16.3802 | 119.8939 | 0.65 | Terrestrial Optical Fiber Drop | 0.35 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0591 | 1 | 591 | 591 | 0403422005 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Sur | 14.234 | 121.3661 | U | 3816 | 1156 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.51 | Terrestrial Optical Fiber Drop | 0.35 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0592 | 1 | 592 | 592 | 0405807015 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Special District | 14.3541 | 121.324 | R | 4320 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01908 | Edgepoint | 14.3513 | 121.3253 | 0.34 | Terrestrial Optical Fiber Drop | 0.35 | 11.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0593 | 1 | 593 | 593 | 0201516023 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Magapit | 18.1285 | 121.6791 | U | 4128 | 1058 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020016 | FTAP Globe | 18.1207 | 121.6801 | 0.87 | Terrestrial Optical Fiber Drop | 0.35 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0594 | 1 | 594 | 594 | 1001306014 | Region X (Northern Mindanao) | Bukidnon | Kadingilan | Poblacion | 7.6014 | 124.91 | U | 7059 | 1857 | 557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0014 | PTCI/MIDC | 7.605 | 124.9048 | 0.7 | Terrestrial Optical Fiber Drop | 0.35 | 8.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0595 | 1 | 595 | 595 | 0306903003 | Region III (Central Luzon) | Tarlac | Camiling | Anoling 3rd | 15.6474 | 120.3884 | R | 1393 | 357 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-TAR-02715 | Edgepoint | 15.6897 | 120.4131 | 0.33 | Terrestrial Optical Fiber Drop | 2.42 | 2.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0596 | 1 | 596 | 596 | 0603026011 | Region VI (Western Visayas) | Iloilo | Leganes | Gua-an | 10.7881 | 122.59 | R | 1299 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.68 | Terrestrial Optical Fiber Drop | 0.29 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0597 | 1 | 597 | 597 | 0603044033 | Region VI (Western Visayas) | Iloilo | Sara | Poblacion Ilawod | 11.2573 | 123.0194 | U | 1790 | 471 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.63 | Terrestrial Optical Fiber Drop | 0.35 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0598 | 1 | 598 | 598 | 1381100183 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 183 | 14.5239 | 121.0131 | U | 41113 | 12420 | 3726 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | A00025-A02 | PTCI/MIDC | 14.5259 | 121.0143 | 0.26 | Terrestrial Optical Fiber Drop | 0.35 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0599 | 1 | 599 | 599 | 0201526011 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Centro Sur | 17.8813 | 121.571 | R | 2542 | 651 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01127-B06 | PTCI/MIDC | 17.8862 | 121.5706 | 0.55 | Terrestrial Optical Fiber Drop | 0.35 | 7.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0600 | 1 | 600 | 600 | 1381500012 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Santa Ana | 14.5255 | 121.0754 | U | 24174 | 6089 | 1827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000618 | FTAP Globe | 14.526 | 121.074 | 0.16 | Terrestrial Optical Fiber Drop | 0.35 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0601 | 1 | 601 | 601 | 0931700012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Buenavista | 7.2389 | 122.2581 | U | 8501 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0080 | PTCI/MIDC | 7.2415 | 122.2622 | 0.54 | Terrestrial Optical Fiber Drop | 0.35 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0602 | 1 | 602 | 602 | 0603019007 | Region VI (Western Visayas) | Iloilo | Estancia | Cano-an | 11.4575 | 123.1296 | U | 2847 | 749 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060014 | FTAP BTS | 11.4586 | 123.1301 | 0.14 | Terrestrial Optical Fiber Drop | 0.35 | 2.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0603 | 1 | 603 | 603 | 0403417002 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Alibungbungan | 14.139 | 121.4181 | R | 2161 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02122-C08 | PTCI/MIDC | 14.1344 | 121.4104 | 0.98 | Terrestrial Optical Fiber Drop | 0.35 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0604 | 1 | 604 | 604 | 0403423005 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 2 | 14.113 | 121.3947 | R | 2020 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.31 | Terrestrial Optical Fiber Drop | 0.35 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0605 | 1 | 605 | 605 | 1381300031 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Doña Imelda | 14.6153 | 121.0183 | U | 17695 | 4390 | 1317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01633 | Edgepoint | 14.6133 | 121.0179 | 0.23 | Terrestrial Optical Fiber Drop | 0.35 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0606 | 1 | 606 | 606 | 0402106013 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc I | 14.2986 | 120.9559 | U | 8066 | 2372 | 712 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.69 | Terrestrial Optical Fiber Drop | 0.35 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0607 | 1 | 607 | 607 | 0631000098 | Region VI (Western Visayas) | Iloilo | City of Iloilo | M. V. Hechanova | 10.7473 | 122.5641 | U | 4301 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.68 | Terrestrial Optical Fiber Drop | 0.35 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0608 | 1 | 608 | 608 | 0731300017 | Region VII (Central Visayas) | Cebu | City of Mandaue | Maguikay | 10.341 | 123.9365 | U | 14971 | 4277 | 1283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070336 | FTAP Globe | 10.3399 | 123.9305 | 0.67 | Terrestrial Optical Fiber Drop | 0.35 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0609 | 1 | 609 | 609 | 0103306031 | Region I (Ilocos Region) | La Union | Bangar | Reyna Regente | 16.8926 | 120.4282 | R | 1122 | 303 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.54 | Terrestrial Optical Fiber Drop | 0.35 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0610 | 1 | 610 | 610 | 1204704032 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Poblacion | 7.0067 | 125.0899 | U | 23166 | 6096 | 1829 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NOC_0003 | LDIC | 7.0053 | 125.0887 | 0.2 | Terrestrial Optical Fiber Drop | 0.36 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0611 | 1 | 611 | 611 | 0203131028 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone II | 16.9825 | 122.0147 | R | 2552 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.59 | Terrestrial Optical Fiber Drop | 0.36 | 17.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0612 | 1 | 612 | 612 | 0704606025 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Tinago | 9.3624 | 122.8083 | U | 3322 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0009 | PTCI/MIDC | 9.3595 | 122.8171 | 1.02 | Terrestrial Optical Fiber Drop | 0.35 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0613 | 1 | 613 | 613 | 1430300076 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | New Lucban | 16.4225 | 120.5948 | R | 2082 | 547 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0023 | PTCI/MIDC | 16.4221 | 120.5951 | 0.06 | Terrestrial Optical Fiber Drop | 0.36 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0614 | 1 | 614 | 614 | 0403405049 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Real | 14.1985 | 121.1492 | U | 17945 | 5437 | 1631 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040256 | FTAP Globe | 14.1944 | 121.147 | 0.52 | Terrestrial Optical Fiber Drop | 0.36 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0615 | 1 | 615 | 615 | 1004308062 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Punong | 8.8423 | 125.1534 | R | 1080 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100111 | FTAP Globe | 8.8451 | 125.1592 | 0.71 | Terrestrial Optical Fiber Drop | 0.36 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0616 | 1 | 616 | 616 | 0402121002 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion II | 14.2863 | 120.7176 | R | 2111 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.59 | Terrestrial Optical Fiber Drop | 0.36 | 2.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0617 | 1 | 617 | 617 | 1380200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Uno | 14.4385 | 121.0024 | U | 42677 | 10999 | 3300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000694 | FTAP Globe | 14.4372 | 121.0013 | 0.19 | Terrestrial Optical Fiber Drop | 0.36 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0618 | 1 | 618 | 618 | 0102926005 | Region I (Ilocos Region) | Ilocos Sur | Santa Maria | Baliw Laud | 17.3812 | 120.4821 | R | 645 | 169 | 51 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01267-B05 | PTCI/MIDC | 17.3721 | 120.4847 | 0.21 | Terrestrial Optical Fiber Drop | 0.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0619 | 1 | 619 | 619 | 0402115016 | Region IV-A (CALABARZON) | Cavite | Naic | Latoria | 14.3098 | 120.772 | R | 2301 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4395 | FTAP Smart | 14.3166 | 120.7682 | 0.42 | Terrestrial Optical Fiber Drop | 1.32 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0620 | 1 | 620 | 620 | 0403408020 | Region IV-A (CALABARZON) | Laguna | Famy | Tunhac | 14.4387 | 121.4499 | U | 2145 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040101 | FTAP Globe | 14.4377 | 121.4463 | 0.41 | Terrestrial Optical Fiber Drop | 0.36 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0621 | 1 | 621 | 621 | 0402103051 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Niog II | 14.4539 | 120.9581 | U | 7376 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.56 | Terrestrial Optical Fiber Drop | 0.36 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0622 | 1 | 622 | 622 | 0105544046 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion East | 15.9267 | 120.8424 | U | 1858 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 0.67 | Terrestrial Optical Fiber Drop | 0.36 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0623 | 1 | 623 | 623 | 0301406010 | Region III (Central Luzon) | Bulacan | Bustos | Poblacion | 14.9558 | 120.919 | U | 8636 | 2467 | 740 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00979-B07 | PTCI/MIDC | 14.956 | 120.921 | 0.21 | Terrestrial Optical Fiber Drop | 0.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0624 | 1 | 624 | 624 | 0603009012 | Region VI (Western Visayas) | Iloilo | Batad | Caw-i | 11.4177 | 123.1098 | R | 905 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.61 | Terrestrial Optical Fiber Drop | 0.36 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0625 | 1 | 625 | 625 | 0201528023 | Region II (Cagayan Valley) | Cagayan | Tuao | Naruangan | 17.6693 | 121.5151 | R | 2164 | 554 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020036 | FTAP Globe | 17.6721 | 121.5173 | 0.39 | Terrestrial Optical Fiber Drop | 0.36 | 8.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0626 | 1 | 626 | 626 | 0803738076 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Punta | 11.009 | 124.5999 | U | 4544 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0045 | PTCI/MIDC | 11.0153 | 124.6014 | 0.72 | Terrestrial Optical Fiber Drop | 0.36 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0627 | 1 | 627 | 627 | 0501724004 | Region V (Bicol Region) | Camarines Sur | City of Naga | Balatas | 13.6311 | 123.2015 | U | 11086 | 2639 | 792 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S95 | FTAP Smart | 13.6322 | 123.1997 | 0.23 | Terrestrial Optical Fiber Drop | 0.36 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0628 | 1 | 628 | 628 | 0306914007 | Region III (Central Luzon) | Tarlac | San Manuel | Poblacion | 15.7997 | 120.6081 | R | 1616 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01805-B07 | PTCI/MIDC | 15.8018 | 120.6063 | 0.29 | Terrestrial Optical Fiber Drop | 0.36 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0629 | 1 | 629 | 629 | 0205702007 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Gundaway | 16.5203 | 121.528 | U | 3953 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQRG0002 | PTCI/MIDC | 16.5179 | 121.5264 | 0.32 | Terrestrial Optical Fiber Drop | 0.36 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0630 | 1 | 630 | 630 | 0631000135 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Quintin Salas | 10.7428 | 122.5648 | U | 5438 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060164 | FTAP BTS | 10.7393 | 122.5632 | 0.43 | Terrestrial Optical Fiber Drop | 0.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0631 | 1 | 631 | 631 | 0431200021 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Iyam | 13.9307 | 121.6093 | U | 28220 | 7055 | 2117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02698 | Edgepoint | 13.9316 | 121.6129 | 0.39 | Terrestrial Optical Fiber Drop | 0.36 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0632 | 1 | 632 | 632 | 0630200051 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Mansilingan | 10.6195 | 122.9762 | U | 53935 | 14981 | 4494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0006 | PTCI/MIDC | 10.6237 | 122.9796 | 0.89 | Terrestrial Optical Fiber Drop | 1.55 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0633 | 1 | 633 | 633 | 0102820022 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | Santa Asuncion | 18.1725 | 120.596 | R | 937 | 253 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.17 | Terrestrial Optical Fiber Drop | 0.37 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0634 | 1 | 634 | 634 | 1130700152 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 19-B | 7.0944 | 125.6036 | U | 31998 | 9411 | 2823 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSR0042 | PTCI/MIDC | 7.1049 | 125.6016 | 1.18 | Terrestrial Optical Fiber Drop | 0.37 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0635 | 1 | 635 | 635 | 0401012047 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ilaya | 13.8757 | 120.9136 | R | 1499 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01950-C08 | PTCI/MIDC | 13.8765 | 120.9183 | 0.51 | Terrestrial Optical Fiber Drop | 0.36 | 2.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0636 | 1 | 636 | 636 | 0102808015 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Pias Norte | 17.9919 | 120.5027 | R | 946 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010029 | FTAP Globe | 18.006 | 120.5028 | 1.57 | Terrestrial Optical Fiber Drop | 0.37 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0637 | 1 | 637 | 637 | 0500517015 | Region V (Bicol Region) | Albay | City of Tabaco | Cobo | 13.3508 | 123.7286 | R | 3451 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ALB-02560 | Edgepoint | 13.3488 | 123.728 | 0.23 | Terrestrial Optical Fiber Drop | 0.37 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0638 | 1 | 638 | 638 | 1230800034 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | City Heights | 6.1256 | 125.1742 | U | 25207 | 6463 | 1939 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0017 | PTCI/MIDC | 6.1297 | 125.1743 | 0.45 | Terrestrial Optical Fiber Drop | 0.37 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0639 | 1 | 639 | 639 | 0203122002 | Region II (Cagayan Valley) | Isabela | Quezon | Alunan | 17.3118 | 121.6093 | R | 1340 | 352 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0003 | LDIC | 121.6055 | 17.3127 | 0.42 | Terrestrial Optical Fiber Drop | 0.37 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0640 | 1 | 640 | 640 | 1403213037 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Dagupan Weste | 17.4739 | 121.4658 | U | 4743 | 1103 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140131 | FTAP Globe | 17.4672 | 121.4677 | 0.78 | Terrestrial Optical Fiber Drop | 0.37 | 3.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0641 | 1 | 641 | 641 | 0501736015 | Region V (Bicol Region) | Camarines Sur | Tigaon | Poblacion | 13.6332 | 123.4959 | U | 3068 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.52 | Terrestrial Optical Fiber Drop | 0.37 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0642 | 1 | 642 | 642 | 0403419013 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Barangay II | 14.2752 | 121.4533 | U | 2128 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.17 | Terrestrial Optical Fiber Drop | 0.37 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0643 | 1 | 643 | 643 | 0603036003 | Region VI (Western Visayas) | Iloilo | Pavia | Anilao | 10.7776 | 122.5392 | R | 1380 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 0.19 | Terrestrial Optical Fiber Drop | 0.54 | 4.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0644 | 1 | 644 | 644 | 1600314024 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Kolambugan | 9.0311 | 125.7891 | R | 2105 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.84 | Terrestrial Optical Fiber Drop | 22.15 | 19.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0645 | 1 | 645 | 645 | 0501721015 | Region V (Bicol Region) | Camarines Sur | Milaor | San Jose | 13.5993 | 123.1779 | U | 2260 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050093 | FTAP Globe | 13.5996 | 123.1749 | 0.33 | Terrestrial Optical Fiber Drop | 0.37 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0646 | 1 | 646 | 646 | 0701205016 | Region VII (Central Visayas) | Bohol | Baclayon | Taguihon | 9.625 | 123.9219 | R | 2119 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070157 | FTAP BTS | 9.654 | 123.8788 | 4.72 | Terrestrial Optical Fiber Drop | 0.99 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0647 | 1 | 647 | 647 | 0908305013 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Lower Ipil Heights | 7.7835 | 122.5843 | R | 1497 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090142 | FTAP Globe | 7.7821 | 122.5819 | 0.38 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0648 | 1 | 648 | 648 | 0405804021 | Region IV-A (CALABARZON) | Rizal | Binangonan | Limbon-limbon | 14.4414 | 121.2056 | R | 1629 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01901 | Edgepoint | 14.4417 | 121.2063 | 0.08 | Terrestrial Optical Fiber Drop | 0.37 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0649 | 1 | 649 | 649 | 0506211001 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Norte | 12.8241 | 123.8424 | R | 1413 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 0.49 | Terrestrial Optical Fiber Drop | 0.37 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0650 | 1 | 650 | 650 | 0402113024 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I B | 14.2768 | 120.7341 | R | 1655 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.45 | Terrestrial Optical Fiber Drop | 0.37 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0651 | 1 | 651 | 651 | 0431200008 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 5 | 13.9358 | 121.6095 | U | 2387 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040447 | FTAP Globe | 13.9371 | 121.6094 | 0.14 | Terrestrial Optical Fiber Drop | 0.37 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0652 | 1 | 652 | 652 | 1380200018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Tres | 14.4407 | 121.004 | U | 33192 | 8298 | 2489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00293-A03 | PTCI/MIDC | 14.4377 | 121.0059 | 0.39 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0653 | 1 | 653 | 653 | 1402701016 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Poblacion | 16.9141 | 121.0601 | R | 2686 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.57 | Terrestrial Optical Fiber Drop | 0.37 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0654 | 1 | 654 | 654 | 0402103039 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi II | 14.4599 | 120.9524 | R | 2928 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00687-A03 | PTCI/MIDC | 14.4623 | 120.969 | 0.31 | Terrestrial Optical Fiber Drop | 0.74 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0655 | 1 | 655 | 655 | 0304924009 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Poblacion | 15.3067 | 120.8554 | R | 2148 | 613 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00768 | Edgepoint | 15.3047 | 120.8562 | 0.24 | Terrestrial Optical Fiber Drop | 0.37 | 3.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0656 | 1 | 656 | 656 | 0506211002 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Sur | 12.8187 | 123.841 | R | 1249 | 312 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 0.16 | Terrestrial Optical Fiber Drop | 0.37 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0657 | 1 | 657 | 657 | 0105505014 | Region I (Ilocos Region) | Pangasinan | Anda | Poblacion | 16.2866 | 119.9508 | U | 3823 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00370 | Edgepoint | 16.2909 | 119.9464 | 0.67 | Terrestrial Optical Fiber Drop | 0.37 | 6.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0658 | 1 | 658 | 658 | 0803715031 | Region VIII (Eastern Visayas) | Leyte | Carigara | Ponong | 11.3015 | 124.6865 | R | 2495 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 1.01 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0659 | 1 | 659 | 659 | 0803738068 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Mas-in | 11.0632 | 124.5147 | R | 1937 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080191 | FTAP BTS | 11.0648 | 124.5167 | 0.28 | Terrestrial Optical Fiber Drop | 0.37 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0660 | 1 | 660 | 660 | 0205010027 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Castillo Village | 16.3547 | 120.8926 | R | 783 | 206 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01524-B05 | PTCI/MIDC | 16.3482 | 120.9094 | 1.93 | Terrestrial Optical Fiber Drop | 0.37 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0661 | 1 | 661 | 661 | 0600413008 | Region VI (Western Visayas) | Aklan | Malinao | Kinalangay Nuevo | 11.6231 | 122.2935 | R | 916 | 234 | 70 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060219 | FTAP Globe | 11.6476 | 122.3063 | 3.05 | Terrestrial Optical Fiber Drop | 0.37 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0662 | 1 | 662 | 662 | 0506216010 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Buenavista | 13.039 | 124.1073 | R | 2073 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03189-C10 | PTCI/MIDC | 13.0209 | 124.102 | 2.1 | Terrestrial Optical Fiber Drop | 0.37 | 9.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0663 | 1 | 663 | 663 | 1380200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Kuatro | 14.435 | 121.0036 | U | 17656 | 4850 | 1455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000694 | FTAP Globe | 14.4372 | 121.0013 | 0.35 | Terrestrial Optical Fiber Drop | 0.37 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0664 | 1 | 664 | 664 | 0301420041 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan Proper | 14.8447 | 121.0801 | U | 48261 | 13788 | 4136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02432-B07 | PTCI/MIDC | 14.8426 | 121.0785 | 0.29 | Terrestrial Optical Fiber Drop | 0.37 | 4.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0665 | 1 | 665 | 665 | 1001314006 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Diclum | 8.3736 | 124.8495 | R | 5043 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 1.6 | Terrestrial Optical Fiber Drop | 0.37 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0666 | 1 | 666 | 666 | 0304905015 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Joson | 15.9483 | 120.9778 | U | 6074 | 1735 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00510 | Edgepoint | 15.9515 | 120.9795 | 0.4 | Terrestrial Optical Fiber Drop | 0.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0667 | 1 | 667 | 667 | 0300810012 | Region III (Central Luzon) | Bataan | Orion | Daang Bilolo | 14.6181 | 120.577 | R | 3206 | 890 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0398 | FTAP Smart | 14.6168 | 120.5791 | 0.27 | Terrestrial Optical Fiber Drop | 0.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0668 | 1 | 668 | 668 | 0102933019 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Farola | 16.9328 | 120.4475 | R | 1027 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.45 | Terrestrial Optical Fiber Drop | 0.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0669 | 1 | 669 | 669 | 0908305009 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Ipil Heights | 7.7836 | 122.5842 | R | 3976 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090142 | FTAP Globe | 7.7821 | 122.5819 | 0.3 | Terrestrial Optical Fiber Drop | 0.38 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0670 | 1 | 670 | 670 | 0405648021 | Region IV-A (CALABARZON) | Quezon | Tiaong | Quipot | 13.9596 | 121.3203 | U | 3810 | 1002 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040409 | FTAP Globe | 13.9631 | 121.3238 | 0.54 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0671 | 1 | 671 | 671 | 0803738051 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Don Felipe Larrazabal | 11.0112 | 124.6042 | U | 1669 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080355 | FTAP Globe | 11.0081 | 124.6074 | 0.48 | Terrestrial Optical Fiber Drop | 0.38 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0672 | 1 | 672 | 672 | 0301423017 | Region III (Central Luzon) | Bulacan | Santa Maria | Pulong Buhangin | 14.8666 | 120.997 | U | 43084 | 12309 | 3693 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00971-B07 | PTCI/MIDC | 14.8646 | 120.9966 | 0.22 | Terrestrial Optical Fiber Drop | 0.38 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0673 | 1 | 673 | 673 | 1381701006 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | San Roque | 14.5421 | 121.0707 | U | 4897 | 1278 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01837 | Edgepoint | 14.5422 | 121.0702 | 0.05 | Terrestrial Optical Fiber Drop | 0.38 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0674 | 1 | 674 | 674 | 0405641018 | Region IV-A (CALABARZON) | Quezon | San Antonio | Sampaguita | 13.8889 | 121.2865 | R | 1978 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03161-C08 | PTCI/MIDC | 13.8725 | 121.2905 | 1.88 | Terrestrial Optical Fiber Drop | 0.38 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0675 | 1 | 675 | 675 | 0307103003 | Region III (Central Luzon) | Zambales | Candelaria | Catol | 15.621 | 119.9347 | R | 1349 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.57 | Terrestrial Optical Fiber Drop | 0.38 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0676 | 1 | 676 | 676 | 0201505002 | Region II (Cagayan Valley) | Cagayan | Aparri | Bangag | 18.2982 | 121.559 | R | 1886 | 483 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020012 | FTAP Globe | 18.2954 | 121.5634 | 0.55 | Terrestrial Optical Fiber Drop | 0.38 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0677 | 1 | 677 | 677 | 0300811001 | Region III (Central Luzon) | Bataan | Pilar | Ala-uli | 14.6457 | 120.5386 | U | 5656 | 1571 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.2 | Terrestrial Optical Fiber Drop | 0.38 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0678 | 1 | 678 | 678 | 1381300029 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Del Monte | 14.6445 | 121.0129 | U | 10819 | 2725 | 818 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02254 | Edgepoint | 14.6418 | 121.013 | 0.3 | Terrestrial Optical Fiber Drop | 0.38 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0679 | 1 | 679 | 679 | 1001309026 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Poblacion | 7.6342 | 125.0065 | R | 5364 | 1411 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100218 | FTAP Globe | 7.6065 | 125.0055 | 3.08 | Terrestrial Optical Fiber Drop | 0.38 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0680 | 1 | 680 | 680 | 0205006010 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Poblacion | 16.6604 | 121.3652 | R | 3966 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NUV_0006 | LDIC | 121.3694 | 16.6623 | 0.49 | Terrestrial Optical Fiber Drop | 0.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0681 | 1 | 681 | 681 | 0600401009 | Region VI (Western Visayas) | Aklan | Altavas | Man-up | 11.5342 | 122.4758 | R | 1148 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 3.16 | Terrestrial Optical Fiber Drop | 1.18 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0682 | 1 | 682 | 682 | 0203131027 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone I | 16.9838 | 122.0098 | R | 1647 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.21 | Terrestrial Optical Fiber Drop | 0.38 | 16.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0683 | 1 | 683 | 683 | 0506215013 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Roque | 12.6456 | 124.1051 | R | 1208 | 302 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.75 | Terrestrial Optical Fiber Drop | 0.07 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0684 | 1 | 684 | 684 | 0603035039 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilawod | 11.1052 | 122.6427 | U | 6043 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.47 | Terrestrial Optical Fiber Drop | 0.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0685 | 1 | 685 | 685 | 0405808011 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Rafael | 14.7325 | 121.1584 | U | 30559 | 8488 | 2546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01253 | Edgepoint | 14.7353 | 121.1563 | 0.38 | Terrestrial Optical Fiber Drop | 0.39 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0686 | 1 | 686 | 686 | 0300806015 | Region III (Central Luzon) | Bataan | Limay | St. Francis II | 14.5719 | 120.5924 | U | 13425 | 3729 | 1119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-03011 | Edgepoint | 120.5896 | 14.5707 | 0.33 | Terrestrial Optical Fiber Drop | 0.39 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0687 | 1 | 687 | 687 | 0405808001 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Balite | 14.7325 | 121.1445 | U | 8169 | 2269 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01264 | Edgepoint | 14.7303 | 121.1441 | 0.25 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0688 | 1 | 688 | 688 | 0306909012 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan West | 15.7204 | 120.5705 | R | 1351 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01796-B07 | PTCI/MIDC | 15.7192 | 120.5771 | 0.71 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0689 | 1 | 689 | 689 | 0403410018 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Palina | 14.134 | 121.4335 | R | 2517 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02121-C08 | PTCI/MIDC | 14.1337 | 121.4379 | 0.48 | Terrestrial Optical Fiber Drop | 0.39 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0690 | 1 | 690 | 690 | 1600308017 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 3 | 8.5072 | 125.9725 | U | 3575 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.91 | Terrestrial Optical Fiber Drop | 0.39 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0691 | 1 | 691 | 691 | 0702218007 | Region VII (Central Visayas) | Cebu | Compostela | Cogon | 10.4553 | 124.0092 | U | 8155 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0061 | PTCI/MIDC | 10.4566 | 124.0086 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0692 | 1 | 692 | 692 | 0307106011 | Region III (Central Luzon) | Zambales | Masinloc | South Poblacion | 15.5343 | 119.95 | R | 4617 | 1215 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0012 | PTCI/MIDC | 15.5354 | 119.9518 | 0.22 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0693 | 1 | 693 | 693 | 0203137033 | Region II (Cagayan Valley) | Isabela | Tumauini | Namnama | 17.2908 | 121.8706 | R | 1672 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0044 | PTCI/MIDC | 17.2915 | 121.8697 | 0.12 | Terrestrial Optical Fiber Drop | 0.39 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0694 | 1 | 694 | 694 | 0501718013 | Region V (Bicol Region) | Camarines Sur | Libmanan | Begajo Sur | 13.6955 | 123.0674 | R | 1097 | 261 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02007 | Edgepoint | 13.6955 | 123.0601 | 0.79 | Terrestrial Optical Fiber Drop | 0.39 | 7.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0695 | 1 | 695 | 695 | 0500514014 | Region V (Bicol Region) | Albay | Polangui | Centro Oriental | 13.2948 | 123.4865 | U | 2019 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 0.81 | Terrestrial Optical Fiber Drop | 0.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0696 | 1 | 696 | 696 | 0301420040 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan V | 14.8445 | 121.0802 | R | 2300 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0009 | LDIC | 14.7988 | 121.0417 | 0.26 | Terrestrial Optical Fiber Drop | 0.39 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0697 | 1 | 697 | 697 | 0501723031 | Region V (Bicol Region) | Camarines Sur | Nabua | San Nicolas | 13.4038 | 123.3709 | R | 1105 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02601 | Edgepoint | 13.4058 | 123.3723 | 0.27 | Terrestrial Optical Fiber Drop | 0.39 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0698 | 1 | 698 | 698 | 1402709008 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Piwong | 16.8456 | 121.0932 | R | 1248 | 320 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-IFU-00249 | Edgepoint | 16.8463 | 121.1071 | 1.49 | Terrestrial Optical Fiber Drop | 0.39 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0699 | 1 | 699 | 699 | 1600206001 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Bangayan | 9.3608 | 125.5528 | R | 1767 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 10.8 | Terrestrial Optical Fiber Drop | 0.39 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0700 | 1 | 700 | 700 | 0603039024 | Region VI (Western Visayas) | Iloilo | San Enrique | Poblacion Ilaya | 11.0735 | 122.6593 | R | 1219 | 320 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 3.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0701 | 1 | 701 | 701 | 1102411007 | Region XI (Davao Region) | Davao del Sur | Padada | N C Ordaneza District | 6.638 | 125.3416 | U | 2238 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.77 | Terrestrial Optical Fiber Drop | 0.39 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0702 | 1 | 702 | 702 | 0405639013 | Region IV-A (CALABARZON) | Quezon | Sampaloc | Ilayang Owain | 14.1621 | 121.6414 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.26 | Terrestrial Optical Fiber Drop | 0.39 | 9.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0703 | 1 | 703 | 703 | 0403418009 | Region IV-A (CALABARZON) | Laguna | Paete | Quinale | 14.3617 | 121.4834 | U | 7953 | 2410 | 723 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.88 | Terrestrial Optical Fiber Drop | 0.39 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0704 | 1 | 704 | 704 | 0506202018 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Central | 12.8664 | 124.1436 | R | 1062 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050219 | FTAP Globe | 12.8603 | 124.1471 | 0.77 | Terrestrial Optical Fiber Drop | 0.39 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0705 | 1 | 705 | 705 | 0203101010 | Region II (Cagayan Valley) | Isabela | Alicia | Calaocan | 16.7814 | 121.6913 | U | 3769 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 0.36 | Terrestrial Optical Fiber Drop | 0.39 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0706 | 1 | 706 | 706 | 1004310011 | Region X (Northern Mindanao) | Misamis Oriental | Initao | Poblacion | 8.4975 | 124.3062 | U | 8103 | 2077 | 623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100140 | FTAP Globe | 8.4972 | 124.3038 | 0.27 | Terrestrial Optical Fiber Drop | 0.4 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0707 | 1 | 707 | 707 | 0201525015 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Centro West | 18.2474 | 121.9073 | R | 1745 | 447 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01129-B06 | PTCI/MIDC | 18.2464 | 121.9084 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0708 | 1 | 708 | 708 | 0203132002 | Region II (Cagayan Valley) | Isabela | San Mateo | Bagong Sikat | 16.8831 | 121.5878 | R | 2602 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01370-B06 | PTCI/MIDC | 16.8794 | 121.5907 | 0.52 | Terrestrial Optical Fiber Drop | 0.39 | 11.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0709 | 1 | 709 | 709 | 0504101031 | Region V (Bicol Region) | Masbate | Aroroy | Poblacion | 12.5107 | 123.3952 | U | 4099 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.24 | Terrestrial Optical Fiber Drop | 0.39 | 4.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1001 | 1 | 710 | 710 | 0600411015 | Region VI (Western Visayas) | Aklan | Makato | Poblacion | 11.7125 | 122.29 | R | 3445 | 883 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.35 | Terrestrial Optical Fiber Drop | 0.54 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0711 | 1 | 711 | 711 | 0506212012 | Region V (Bicol Region) | Sorsogon | Matnog | Caloocan | 12.5835 | 124.0838 | R | 1082 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050233 | FTAP Globe | 12.59 | 124.0937 | 1.3 | Terrestrial Optical Fiber Drop | 0.4 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0712 | 1 | 712 | 712 | 0402109085 | Region IV-A (CALABARZON) | Cavite | City of Imus | Pasong Buaya II | 14.3899 | 120.9649 | U | 37476 | 11022 | 3307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4076 | FTAP Smart | 14.3871 | 120.9619 | 0.45 | Terrestrial Optical Fiber Drop | 0.4 | 6.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0713 | 1 | 713 | 713 | 0501728005 | Region V (Bicol Region) | Camarines Sur | Pili | Cadlan | 13.5999 | 123.2539 | U | 5986 | 1425 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050094 | FTAP Globe | 13.5974 | 123.2574 | 0.47 | Terrestrial Optical Fiber Drop | 0.4 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0714 | 1 | 714 | 714 | 0702223040 | Region VII (Central Visayas) | Cebu | Danao City | Suba | 10.5245 | 124.0287 | U | 7790 | 2050 | 615 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.16 | Terrestrial Optical Fiber Drop | 0.4 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0715 | 1 | 715 | 715 | 1404409009 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Demang | 17.0843 | 120.8981 | R | 702 | 189 | 57 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01407-B05 | PTCI/MIDC | 17.0819 | 120.9043 | 0.48 | Terrestrial Optical Fiber Drop | 0.28 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0716 | 1 | 716 | 716 | 0405622006 | Region IV-A (CALABARZON) | Quezon | Lopez | Gomez | 13.8861 | 122.2587 | U | 3496 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.41 | Terrestrial Optical Fiber Drop | 0.4 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0717 | 1 | 717 | 717 | 0403411012 | Region IV-A (CALABARZON) | Laguna | Los Baños | San Antonio | 14.1768 | 121.2451 | U | 17515 | 5307 | 1592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.31 | Terrestrial Optical Fiber Drop | 0.4 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0718 | 1 | 718 | 718 | 0203104007 | Region II (Cagayan Valley) | Isabela | Benito Soliven | District II | 16.9865 | 121.9588 | R | 2011 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0041 | LDIC | 16.9909 | 121.9458 | 1.47 | Terrestrial Optical Fiber Drop | 0.4 | 11.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0719 | 1 | 719 | 719 | 0105544047 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion West | 15.928 | 120.8393 | U | 2419 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 0.41 | Terrestrial Optical Fiber Drop | 0.4 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0720 | 1 | 720 | 720 | 0304930042 | Region III (Central Luzon) | Nueva Ecija | Talavera | Pag-asa | 15.5846 | 120.9168 | U | 5626 | 1607 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030352 | FTAP Globe | 15.583 | 120.9117 | 0.57 | Terrestrial Optical Fiber Drop | 0.4 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0721 | 1 | 721 | 721 | 0702218014 | Region VII (Central Visayas) | Cebu | Compostela | Poblacion | 10.456 | 124.0115 | U | 12857 | 3383 | 1015 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0061 | PTCI/MIDC | 10.4566 | 124.0086 | 0.33 | Terrestrial Optical Fiber Drop | 0.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0722 | 1 | 722 | 722 | 1004321015 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Taboc | 8.517 | 124.5762 | U | 4039 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100132 | FTAP Globe | 8.5148 | 124.5755 | 0.25 | Terrestrial Optical Fiber Drop | 0.4 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0723 | 1 | 723 | 723 | 0300804013 | Region III (Central Luzon) | Bataan | Dinalupihan | Happy Valley | 14.847 | 120.4009 | R | 1998 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030583 | FTAP Globe | 14.8459 | 120.405 | 0.45 | Terrestrial Optical Fiber Drop | 0.4 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0724 | 1 | 724 | 724 | 0306917027 | Region III (Central Luzon) | Tarlac | Victoria | Santa Lucia | 15.5785 | 120.679 | R | 1640 | 420 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.2 | Terrestrial Optical Fiber Drop | 0.4 | 5.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0725 | 1 | 725 | 725 | 1380400017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Santolan | 14.6854 | 120.9589 | U | 13736 | 3836 | 1151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0023 | PTCI/MIDC | 14.6847 | 120.9593 | 0.09 | Terrestrial Optical Fiber Drop | 0.4 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0726 | 1 | 726 | 726 | 0301419036 | Region III (Central Luzon) | Bulacan | San Ildefonso | Upig | 15.025 | 120.9922 | R | 2853 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-BUL-00932 | Edgepoint | 15.0225 | 120.973 | 2.08 | Terrestrial Optical Fiber Drop | 0.4 | 6.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0727 | 1 | 727 | 727 | 0402103030 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban III | 14.4608 | 120.9644 | R | 881 | 259 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.55 | Terrestrial Optical Fiber Drop | 0.54 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0728 | 1 | 728 | 728 | 1208007005 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Banate | 6.4742 | 125.3216 | R | 3940 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120294 | FTAP Globe | 6.4811 | 125.3261 | 0.91 | Terrestrial Optical Fiber Drop | 0.4 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0729 | 1 | 729 | 729 | 0306903064 | Region III (Central Luzon) | Tarlac | Camiling | Surgui 2nd | 15.6761 | 120.4145 | R | 1574 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00605 | Edgepoint | 15.6807 | 120.415 | 0.51 | Terrestrial Optical Fiber Drop | 0.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0730 | 1 | 730 | 730 | 0102906037 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Isidro | 17.1882 | 120.446 | U | 1868 | 491 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03281-B05 | PTCI/MIDC | 17.1848 | 120.4469 | 0.4 | Terrestrial Optical Fiber Drop | 0.41 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0731 | 1 | 731 | 731 | 1402709006 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Namulditan | 16.8426 | 121.0866 | R | 1012 | 259 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-IFU-00249 | Edgepoint | 16.8463 | 121.1071 | 2.22 | Terrestrial Optical Fiber Drop | 0.4 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0732 | 1 | 732 | 732 | 0603027025 | Region VI (Western Visayas) | Iloilo | Lemery | San Jose Moto | 11.227 | 122.925 | R | 1095 | 288 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0101 | PTCI/MIDC | 11.2258 | 122.9295 | 0.5 | Terrestrial Optical Fiber Drop | 0.4 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1003 | 1 | 733 | 733 | 0403416011 | Region IV-A (CALABARZON) | Laguna | Majayjay | Botocan | 14.1564 | 121.4907 | R | 1021 | 309 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.53 | Terrestrial Optical Fiber Drop | 2.67 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0734 | 1 | 734 | 734 | 0730600064 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag I | 10.2994 | 123.8956 | U | 11540 | 3606 | 1082 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0119 | PTCI/MIDC | 10.2993 | 123.8942 | 0.16 | Terrestrial Optical Fiber Drop | 0.4 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0735 | 1 | 735 | 735 | 0506204009 | Region V (Bicol Region) | Sorsogon | Bulusan | Madlawon | 12.7606 | 124.1362 | R | 1275 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050224 | FTAP Globe | 12.7527 | 124.1332 | 0.94 | Terrestrial Optical Fiber Drop | 0.41 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0736 | 1 | 736 | 736 | 0402103053 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu II | 14.4562 | 120.955 | R | 1833 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.58 | Terrestrial Optical Fiber Drop | 0.4 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0737 | 1 | 737 | 737 | 0105506013 | Region I (Ilocos Region) | Pangasinan | Asingan | Dupac | 16.0085 | 120.6684 | R | 2391 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.82 | Terrestrial Optical Fiber Drop | 0.41 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0738 | 1 | 738 | 738 | 0301423020 | Region III (Central Luzon) | Bulacan | Santa Maria | San Vicente | 14.8095 | 121.0127 | U | 25558 | 7302 | 2191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01013-B07 | PTCI/MIDC | 14.8125 | 121.0117 | 0.35 | Terrestrial Optical Fiber Drop | 0.41 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0739 | 1 | 739 | 739 | 0501701022 | Region V (Bicol Region) | Camarines Sur | Baao | San Ramon | 13.4545 | 123.3683 | R | 458 | 109 | 33 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050118 | FTAP Globe | 13.4568 | 123.3687 | 0.26 | Terrestrial Optical Fiber Drop | 0.41 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0740 | 1 | 740 | 740 | 0702239010 | Region VII (Central Visayas) | Cebu | Ronda | Palanas | 9.9966 | 123.4094 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0264 | PTCI/MIDC | 10.0263 | 123.4161 | 3.38 | Terrestrial Optical Fiber Drop | 0.41 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0741 | 1 | 741 | 741 | 0201507008 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Centro East | 18.4099 | 121.5176 | U | 4291 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00013 | Edgepoint | 18.4074 | 121.515 | 0.39 | Terrestrial Optical Fiber Drop | 0.41 | 7.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0742 | 1 | 742 | 742 | 0405628021 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ilayang Yuni | 13.4536 | 122.5231 | R | 3428 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02052 | Edgepoint | 13.4535 | 122.5227 | 2.29 | Terrestrial Optical Fiber Drop | 1.98 | 12.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0743 | 1 | 743 | 743 | 0604509002 | Region VI (Western Visayas) | Negros Occidental | City of Escalante | Balintawak | 10.8394 | 123.4969 | U | 14659 | 3961 | 1188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0088 | PTCI/MIDC | 10.8432 | 123.499 | 0.49 | Terrestrial Optical Fiber Drop | 0.41 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0744 | 1 | 744 | 744 | 0203112045 | Region II (Cagayan Valley) | Isabela | Echague | San Fabian | 16.7122 | 121.6819 | U | 4156 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020095 | FTAP Globe | 16.7091 | 121.6785 | 0.51 | Terrestrial Optical Fiber Drop | 0.41 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0745 | 1 | 745 | 745 | 0402116007 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael II | 14.4314 | 120.8797 | R | 3707 | 1090 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.43 | Terrestrial Optical Fiber Drop | 0.41 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0746 | 1 | 746 | 746 | 1130700137 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 4-A | 7.0707 | 125.6099 | U | 1761 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110487 | FTAP Globe | 7.0656 | 125.6094 | 0.57 | Terrestrial Optical Fiber Drop | 0.41 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0747 | 1 | 747 | 747 | 0300807013 | Region III (Central Luzon) | Bataan | Mariveles | Balon-Anito | 14.4365 | 120.4734 | U | 16526 | 4590 | 1377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1515 | FTAP Smart | 14.4338 | 120.4754 | 0.37 | Terrestrial Optical Fiber Drop | 0.41 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0748 | 1 | 748 | 748 | 1130700050 | Region XI (Davao Region) | Davao del Sur | City of Davao | Indangan | 7.1616 | 125.5957 | U | 25887 | 7613 | 2284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110320 | FTAP BTS | 7.1611 | 125.5956 | 0.06 | Terrestrial Optical Fiber Drop | 0.41 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0749 | 1 | 749 | 749 | 0803722021 | Region VIII (Eastern Visayas) | Leyte | Isabel | Santo Niño | 10.9285 | 124.4367 | U | 6550 | 1723 | 517 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080137 | FTAP BTS | 10.9299 | 124.4346 | 0.28 | Terrestrial Optical Fiber Drop | 0.41 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0750 | 1 | 750 | 750 | 0907322039 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Francisco | 7.8272 | 123.4387 | U | 3238 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090135 | FTAP Globe | 7.8243 | 123.4374 | 0.35 | Terrestrial Optical Fiber Drop | 0.41 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0751 | 1 | 751 | 751 | 0931700061 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Barangay Zone I | 6.907 | 122.0722 | U | 5011 | 1391 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0109 | PTCI/MIDC | 6.905 | 122.0706 | 0.28 | Terrestrial Optical Fiber Drop | 0.41 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0752 | 1 | 752 | 752 | 0405807008 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Pagkalinawan | 14.3155 | 121.3391 | R | 2030 | 563 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02370-A04 | PTCI/MIDC | 14.3075 | 121.3293 | 1.38 | Terrestrial Optical Fiber Drop | 0.41 | 8.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0753 | 1 | 753 | 753 | 1401110006 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Beckel | 16.4363 | 120.6316 | U | 4684 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00328 | Edgepoint | 16.4361 | 120.6292 | 0.25 | Terrestrial Optical Fiber Drop | 0.41 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0754 | 1 | 754 | 754 | 0103306010 | Region I (Ilocos Region) | La Union | Bangar | General Prim East | 16.899 | 120.4387 | R | 936 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.09 | Terrestrial Optical Fiber Drop | 1.6 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0755 | 1 | 755 | 755 | 0300808004 | Region III (Central Luzon) | Bataan | Morong | Poblacion | 14.6777 | 120.268 | U | 7656 | 2126 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00907-B07 | PTCI/MIDC | 14.6793 | 120.2702 | 0.29 | Terrestrial Optical Fiber Drop | 0.41 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0756 | 1 | 756 | 756 | 0402106067 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres II | 14.3179 | 120.9525 | R | 3585 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.4 | Terrestrial Optical Fiber Drop | 1.55 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0757 | 1 | 757 | 757 | 0504101037 | Region V (Bicol Region) | Masbate | Aroroy | Talabaan | 12.5106 | 123.3951 | R | 1558 | 380 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.26 | Terrestrial Optical Fiber Drop | 0.41 | 4.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0758 | 1 | 758 | 758 | 0304916007 | Region III (Central Luzon) | Nueva Ecija | Lupao | Bagong Flores | 15.8879 | 120.9 | R | 4328 | 1236 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01414-B07 | PTCI/MIDC | 15.8805 | 120.8984 | 0.84 | Terrestrial Optical Fiber Drop | 0.41 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0759 | 1 | 759 | 759 | 1600314015 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Poblacion | 8.8236 | 125.6956 | U | 6338 | 1625 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0004 | PTCI/MIDC | 8.825 | 125.6929 | 0.33 | Terrestrial Optical Fiber Drop | 0.41 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0760 | 1 | 760 | 760 | 0704611028 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Poblacion | 10.1191 | 123.2689 | U | 16827 | 4428 | 1328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0029 | PTCI/MIDC | 10.1381 | 123.2458 | 3.3 | Terrestrial Optical Fiber Drop | 0.41 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0761 | 1 | 761 | 761 | 1403209016 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Malagnat | 17.6424 | 121.3897 | R | 2012 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00102 | Edgepoint | 17.6007 | 121.4263 | 6.04 | Terrestrial Optical Fiber Drop | 0.41 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0762 | 1 | 762 | 762 | 0831600076 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 49 | 11.2398 | 124.9986 | R | 1049 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0072 | PTCI/MIDC | 11.2381 | 125.0038 | 0.59 | Terrestrial Optical Fiber Drop | 0.41 | 3.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0763 | 1 | 763 | 763 | 0203136024 | Region II (Cagayan Valley) | Isabela | Santo Tomas | San Roque | 17.3876 | 121.7751 | R | 1241 | 326 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0036 | PTCI/MIDC | 17.3894 | 121.7832 | 0.89 | Terrestrial Optical Fiber Drop | 0.41 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0764 | 1 | 764 | 764 | 1408103014 | Cordillera Administrative Region (CAR) | Apayao | Flora | Poblacion West | 18.214 | 121.4161 | R | 2167 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_APY_0001 | LDIC | 121.4211 | 18.2128 | 0.54 | Terrestrial Optical Fiber Drop | 0.42 | 4.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0765 | 1 | 765 | 765 | 0402106037 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas I | 14.3151 | 120.9685 | R | 2180 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.41 | Terrestrial Optical Fiber Drop | 0.42 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0766 | 1 | 766 | 766 | 0105531033 | Region I (Ilocos Region) | Pangasinan | Rosales | Zone I | 15.8912 | 120.6312 | R | 1283 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01756-B07 | PTCI/MIDC | 15.8943 | 120.6276 | 0.51 | Terrestrial Optical Fiber Drop | 0.42 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0767 | 1 | 767 | 767 | 0105526013 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guiguilonen | 16.0702 | 120.4057 | U | 3480 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.64 | Terrestrial Optical Fiber Drop | 0.45 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0768 | 1 | 768 | 768 | 0405814001 | Region IV-A (CALABARZON) | Rizal | Teresa | Bagumbayan | 14.5499 | 121.2184 | U | 15588 | 4330 | 1299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00788-A04 | PTCI/MIDC | 14.5507 | 121.221 | 0.29 | Terrestrial Optical Fiber Drop | 0.42 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0769 | 1 | 769 | 769 | 1380500025 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | San Jose | 14.58 | 121.0292 | U | 7888 | 2383 | 715 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02522 | Edgepoint | 14.5811 | 121.0289 | 0.13 | Terrestrial Optical Fiber Drop | 0.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0770 | 1 | 770 | 770 | 1004303010 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | San Alonzo | 9.0037 | 124.8389 | R | 1719 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 1.59 | Terrestrial Optical Fiber Drop | 0.42 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0771 | 1 | 771 | 771 | 0300811006 | Region III (Central Luzon) | Bataan | Pilar | Balut II | 14.6866 | 120.5587 | R | 1360 | 377 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.49 | Terrestrial Optical Fiber Drop | 1.48 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0772 | 1 | 772 | 772 | 0300803017 | Region III (Central Luzon) | Bataan | City of Balanga | Sibacan | 14.687 | 120.5472 | R | 2889 | 802 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.63 | Terrestrial Optical Fiber Drop | 0.42 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0773 | 1 | 773 | 773 | 0604520020 | Region VI (Western Visayas) | Negros Occidental | Murcia | Pandanon | 10.6067 | 123.0383 | R | 3123 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 2.69 | Terrestrial Optical Fiber Drop | 0.42 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0774 | 1 | 774 | 774 | 0203115007 | Region II (Cagayan Valley) | Isabela | Jones | Barangay II | 16.554 | 121.7005 | R | 3289 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0057 | PTCI/MIDC | 16.5544 | 121.7027 | 0.23 | Terrestrial Optical Fiber Drop | 0.42 | 11.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0775 | 1 | 775 | 775 | 0702251007 | Region VII (Central Visayas) | Cebu | City of Toledo | Cabitoonan | 10.3526 | 123.6131 | U | 5607 | 1475 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0168 | PTCI/MIDC | 10.3534 | 123.6102 | 0.33 | Terrestrial Optical Fiber Drop | 0.42 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0776 | 1 | 776 | 776 | 0306911010 | Region III (Central Luzon) | Tarlac | Pura | Nilasin 1st | 15.6247 | 120.6547 | R | 1278 | 327 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01811-B07 | PTCI/MIDC | 15.6262 | 120.6521 | 0.32 | Terrestrial Optical Fiber Drop | 0.42 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0777 | 1 | 777 | 777 | 0604515025 | Region VI (Western Visayas) | Negros Occidental | City of Kabankalan | Barangay 4 | 9.9883 | 122.8158 | R | 1475 | 398 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060388 | FTAP Globe | 9.9942 | 122.8157 | 0.65 | Terrestrial Optical Fiber Drop | 0.42 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0778 | 1 | 778 | 778 | 0102808024 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Victoria | 17.9977 | 120.4999 | R | 913 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010029 | FTAP Globe | 18.006 | 120.5028 | 0.96 | Terrestrial Optical Fiber Drop | 0.42 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0779 | 1 | 779 | 779 | 1381500003 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Bambang | 14.5118 | 121.0586 | U | 15749 | 3850 | 1155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000624 | FTAP Globe | 14.515 | 121.0524 | 0.26 | Terrestrial Optical Fiber Drop | 0.82 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0780 | 1 | 780 | 780 | 0405649028 | Region IV-A (CALABARZON) | Quezon | Unisan | R. Magsaysay | 13.8426 | 121.9783 | R | 672 | 176 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040549 | FTAP Globe | 13.8415 | 121.9735 | 0.53 | Terrestrial Optical Fiber Drop | 0.42 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0781 | 1 | 781 | 781 | 0501709017 | Region V (Bicol Region) | Camarines Sur | Camaligan | Tarosanan | 13.6165 | 123.1703 | R | 2223 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.48 | Terrestrial Optical Fiber Drop | 0.43 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0782 | 1 | 782 | 782 | 0405806027 | Region IV-A (CALABARZON) | Rizal | Cardona | San Roque | 14.4862 | 121.2265 | R | 2945 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00823-A04 | PTCI/MIDC | 14.4814 | 121.2254 | 0.55 | Terrestrial Optical Fiber Drop | 0.42 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0783 | 1 | 783 | 783 | 0201512021 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay III-A | 17.5592 | 121.6934 | R | 2677 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0027 | LDIC | 121.695 | 17.5597 | 0.18 | Terrestrial Optical Fiber Drop | 0.42 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0784 | 1 | 784 | 784 | 0501703030 | Region V (Bicol Region) | Camarines Sur | Bato | San Vicente | 13.3621 | 123.3668 | U | 6695 | 1594 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.73 | Terrestrial Optical Fiber Drop | 0.43 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0785 | 1 | 785 | 785 | 0306917024 | Region III (Central Luzon) | Tarlac | Victoria | San Nicolas | 15.5776 | 120.6812 | R | 2875 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.44 | Terrestrial Optical Fiber Drop | 0.43 | 6.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0786 | 1 | 786 | 786 | 0205010016 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Pampang | 16.3578 | 120.8865 | R | 1298 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01524-B05 | PTCI/MIDC | 16.3482 | 120.9094 | 2.66 | Terrestrial Optical Fiber Drop | 0.43 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0787 | 1 | 787 | 787 | 0601916003 | Region VI (Western Visayas) | Capiz | Sigma | Balucuan | 11.4 | 122.6378 | R | 1190 | 313 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1 | Terrestrial Optical Fiber Drop | 4.09 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0788 | 1 | 788 | 788 | 0704610029 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Taclobo | 9.3095 | 123.3037 | U | 9848 | 2591 | 777 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLR0023 | PTCI/MIDC | 9.3104 | 123.3049 | 0.16 | Terrestrial Optical Fiber Drop | 0.43 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0789 | 1 | 789 | 789 | 1380200006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Pamplona Uno | 14.4581 | 120.97 | U | 19658 | 5284 | 1585 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000677 | FTAP Globe | 14.4591 | 120.9704 | 0.12 | Terrestrial Optical Fiber Drop | 0.43 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0790 | 1 | 790 | 790 | 1380500021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pag-asa | 14.5835 | 121.0339 | U | 4493 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01737 | Edgepoint | 14.5877 | 121.0521 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0791 | 1 | 791 | 791 | 0306914015 | Region III (Central Luzon) | Tarlac | San Manuel | Santa Maria | 15.798 | 120.6116 | R | 1715 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 0.17 | Terrestrial Optical Fiber Drop | 0.43 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0792 | 1 | 792 | 792 | 0105522021 | Region I (Ilocos Region) | Pangasinan | Lingayen | Maniboc | 16.0194 | 120.2312 | U | 8214 | 2281 | 684 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-03115 | Edgepoint | 16.0264 | 120.2268 | 0.91 | Terrestrial Optical Fiber Drop | 0.43 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0793 | 1 | 793 | 793 | 1705208044 | MIMAROPA Region | Oriental Mindoro | Naujan | Pinagsabangan II | 13.2674 | 121.2684 | R | 2782 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S7012 | FTAP Smart | 13.2756 | 121.2396 | 3.25 | Terrestrial Optical Fiber Drop | 0.43 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0794 | 1 | 794 | 794 | 0631000024 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Buhang | 10.7494 | 122.5666 | U | 3938 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.36 | Terrestrial Optical Fiber Drop | 0.44 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0795 | 1 | 795 | 795 | 1381701007 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | Santa Ana | 14.5466 | 121.0718 | U | 30950 | 8102 | 2431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000598 | FTAP Globe | 14.5471 | 121.0723 | 0.08 | Terrestrial Optical Fiber Drop | 0.43 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0796 | 1 | 796 | 796 | 0105508015 | Region I (Ilocos Region) | Pangasinan | Bani | Poblacion | 16.187 | 119.8595 | U | 4855 | 1348 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N5519 | FTAP Smart | 16.1813 | 119.8603 | 0.64 | Terrestrial Optical Fiber Drop | 0.44 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0797 | 1 | 797 | 797 | 0307707007 | Region III (Central Luzon) | Aurora | Maria Aurora | Barangay III | 15.7972 | 121.4751 | R | 779 | 205 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3806 | FTAP Smart | 15.7998 | 121.4765 | 0.33 | Terrestrial Optical Fiber Drop | 0.44 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0798 | 1 | 798 | 798 | 0501608017 | Region V (Bicol Region) | Camarines Norte | Paracale | Mangkasay | 14.2554 | 122.8195 | R | 1461 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050007 | FTAP Globe | 14.2443 | 122.8098 | 1.61 | Terrestrial Optical Fiber Drop | 0.44 | 7.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0799 | 1 | 799 | 799 | 0908316005 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | Libertad | 7.6027 | 122.4242 | U | 5986 | 1425 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090159 | FTAP Globe | 7.6017 | 122.4207 | 0.4 | Terrestrial Optical Fiber Drop | 0.44 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0800 | 1 | 800 | 800 | 0702220013 | Region VII (Central Visayas) | Cebu | Cordova | San Miguel | 10.2609 | 123.9437 | R | 4106 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.49 | Terrestrial Optical Fiber Drop | 0.44 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0801 | 1 | 801 | 801 | 0601914047 | Region VI (Western Visayas) | Capiz | City of Roxas | Tanque | 11.5874 | 122.752 | U | 6144 | 1616 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.89 | Terrestrial Optical Fiber Drop | 0.44 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0802 | 1 | 802 | 802 | 1381100192 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 192 | 14.5332 | 121.0006 | U | 4274 | 1264 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040184 | FTAP Globe | 14.3064 | 121.075 | 0.94 | Terrestrial Optical Fiber Drop | 0.7 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0803 | 1 | 803 | 803 | 0103314057 | Region I (Ilocos Region) | La Union | City of San Fernando | Sevilla | 16.6021 | 120.3216 | U | 11353 | 3068 | 920 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010095 | FTAP Globe | 16.6018 | 120.3189 | 0.29 | Terrestrial Optical Fiber Drop | 0.44 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0804 | 1 | 804 | 804 | 0102930020 | Region I (Ilocos Region) | Ilocos Sur | Sinait | Macabiag | 17.8645 | 120.4566 | R | 902 | 237 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTIRG0006 | PTCI/MIDC | 17.8693 | 120.4588 | 0.58 | Terrestrial Optical Fiber Drop | 0.44 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0805 | 1 | 805 | 805 | 0402110033 | Region IV-A (CALABARZON) | Cavite | Indang | Daine II | 14.1855 | 120.8459 | R | 2449 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0034 | FTAP Smart | 14.1948 | 120.8764 | 0.6 | Terrestrial Optical Fiber Drop | 3.27 | 8.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0806 | 1 | 806 | 806 | 0105539014 | Region I (Ilocos Region) | Pangasinan | Santa Maria | Poblacion East | 15.9806 | 120.7009 | R | 1027 | 285 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01765-B07 | PTCI/MIDC | 15.9765 | 120.6972 | 0.6 | Terrestrial Optical Fiber Drop | 0.44 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0807 | 1 | 807 | 807 | 0731300009 | Region VII (Central Visayas) | Cebu | City of Mandaue | Casuntingan | 10.3466 | 123.9408 | U | 16863 | 4818 | 1445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0118 | PTCI/MIDC | 10.3479 | 123.9486 | 0.56 | Terrestrial Optical Fiber Drop | 0.88 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0808 | 1 | 808 | 808 | 0600403015 | Region VI (Western Visayas) | Aklan | Banga | Mangan | 11.6293 | 122.3444 | R | 1846 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 1.78 | Terrestrial Optical Fiber Drop | 0.44 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0809 | 1 | 809 | 809 | 1381500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | South Daang Hari | 14.469 | 121.0499 | U | 25037 | 6322 | 1897 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01875 | Edgepoint | 14.4936 | 121.0495 | 0.16 | Terrestrial Optical Fiber Drop | 1.48 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0810 | 1 | 810 | 810 | 0307103011 | Region III (Central Luzon) | Zambales | Candelaria | Pamibian | 15.6249 | 119.9363 | R | 1501 | 395 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.27 | Terrestrial Optical Fiber Drop | 0.44 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0811 | 1 | 811 | 811 | 0402116012 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose II | 14.4318 | 120.8864 | R | 1941 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.42 | Terrestrial Optical Fiber Drop | 0.44 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0812 | 1 | 812 | 812 | 0306904020 | Region III (Central Luzon) | Tarlac | Capas | Santo Domingo 2nd | 15.3434 | 120.5952 | U | 7231 | 1854 | 556 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01802-B07 | PTCI/MIDC | 15.342 | 120.5972 | 0.26 | Terrestrial Optical Fiber Drop | 0.44 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0813 | 1 | 813 | 813 | 0603043008 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Bantay | 10.8692 | 122.5409 | R | 434 | 114 | 34 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0072 | PTCI/MIDC | 10.8243 | 122.5364 | 0.82 | Terrestrial Optical Fiber Drop | 4.71 | 3.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0814 | 1 | 814 | 814 | 1705209037 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Guinhawa | 13.0665 | 121.5033 | R | 2263 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170094 | FTAP Globe | 13.0692 | 121.5176 | 1.58 | Terrestrial Optical Fiber Drop | 0.44 | 3.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0815 | 1 | 815 | 815 | 1380400019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Tinajeros | 14.6713 | 120.9699 | U | 18677 | 5351 | 1605 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01420 | Edgepoint | 14.6727 | 120.9686 | 0.21 | Terrestrial Optical Fiber Drop | 0.45 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0816 | 1 | 816 | 816 | 0702222029 | Region VII (Central Visayas) | Cebu | Dalaguete | Poblacion | 9.7583 | 123.5338 | U | 6846 | 1801 | 540 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070368 | FTAP Globe | 9.7578 | 123.5312 | 0.28 | Terrestrial Optical Fiber Drop | 0.45 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0817 | 1 | 817 | 817 | 0305406023 | Region III (Central Luzon) | Pampanga | Floridablanca | Poblacion | 14.9786 | 120.4998 | U | 3751 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01555-B07 | PTCI/MIDC | 14.981 | 120.5138 | 0.69 | Terrestrial Optical Fiber Drop | 1.55 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0818 | 1 | 818 | 818 | 0105526025 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Poblacion | 16.0703 | 120.4056 | U | 4206 | 1168 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00421 | Edgepoint | 16.068 | 120.4097 | 0.51 | Terrestrial Optical Fiber Drop | 0.45 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0819 | 1 | 819 | 819 | 1030500018 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Barangay 22 | 8.4905 | 124.6538 | U | 3384 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLR0026 | PTCI/MIDC | 8.4839 | 124.6532 | 0.74 | Terrestrial Optical Fiber Drop | 0.45 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0820 | 1 | 820 | 820 | 0301414008 | Region III (Central Luzon) | Bulacan | Obando | Paliwas | 14.7132 | 120.935 | U | 5749 | 1642 | 493 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01307 | Edgepoint | 14.712 | 120.9332 | 0.24 | Terrestrial Optical Fiber Drop | 0.45 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0821 | 1 | 821 | 821 | 1380300004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Comembo | 14.5461 | 121.0645 | U | 7776 | 2221 | 666 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01833 | Edgepoint | 14.5455 | 121.0684 | 0.43 | Terrestrial Optical Fiber Drop | 0.45 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0822 | 1 | 822 | 822 | 0731300002 | Region VII (Central Visayas) | Cebu | City of Mandaue | Bakilid | 10.3387 | 123.9342 | U | 4391 | 1254 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070336 | FTAP Globe | 10.3399 | 123.9305 | 0.42 | Terrestrial Optical Fiber Drop | 0.45 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0823 | 1 | 823 | 823 | 0402106049 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol III | 14.3244 | 120.9607 | U | 11497 | 3381 | 1014 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01927-C08 | PTCI/MIDC | 14.3499 | 120.9431 | 0.08 | Terrestrial Optical Fiber Drop | 1.44 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0824 | 1 | 824 | 824 | 0402104014 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 3 | 14.3138 | 121.0535 | R | 916 | 269 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1183 | FTAP Smart | 14.3053 | 121.0487 | 0.39 | Terrestrial Optical Fiber Drop | 0.49 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0825 | 1 | 825 | 825 | 0501703035 | Region V (Bicol Region) | Camarines Sur | Bato | Tres Reyes | 13.3544 | 123.3654 | R | 1545 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.34 | Terrestrial Optical Fiber Drop | 0.45 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0826 | 1 | 826 | 826 | 0402120012 | Region IV-A (CALABARZON) | Cavite | Tanza | Mulawin | 14.3746 | 120.8542 | U | 12931 | 3803 | 1141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.64 | Terrestrial Optical Fiber Drop | 0.67 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0827 | 1 | 827 | 827 | 1630400086 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tiniwisan | 8.9472 | 125.5397 | U | 4188 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.14 | Terrestrial Optical Fiber Drop | 0.45 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0828 | 1 | 828 | 828 | 0402109004 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-A | 14.3877 | 120.9399 | U | 3560 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01924-C08 | PTCI/MIDC | 14.3888 | 120.9378 | 0.26 | Terrestrial Optical Fiber Drop | 0.45 | 6.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0829 | 1 | 829 | 829 | 0306902005 | Region III (Central Luzon) | Tarlac | Bamban | Dela Cruz | 15.2798 | 120.5682 | U | 2483 | 636 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01780-B07 | PTCI/MIDC | 15.2833 | 120.5694 | 0.4 | Terrestrial Optical Fiber Drop | 0.45 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0830 | 1 | 830 | 830 | 1001317019 | Region X (Northern Mindanao) | Bukidnon | Quezon | Merangerang | 7.7026 | 125.1135 | R | 3706 | 975 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.71 | Terrestrial Optical Fiber Drop | 0.55 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0831 | 1 | 831 | 831 | 0702232010 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward I | 10.2443 | 123.7983 | U | 2358 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0128 | PTCI/MIDC | 10.2407 | 123.8002 | 0.45 | Terrestrial Optical Fiber Drop | 0.45 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0832 | 1 | 832 | 832 | 0402118020 | Region IV-A (CALABARZON) | Cavite | Silang | Lalaan II | 14.1581 | 120.9572 | U | 8272 | 2432 | 730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040285 | FTAP Globe | 14.1551 | 120.9563 | 0.35 | Terrestrial Optical Fiber Drop | 0.45 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0833 | 1 | 833 | 833 | 0102814009 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Poblacion | 17.9167 | 120.663 | R | 3255 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILN-02610 | Edgepoint | 17.9183 | 120.6677 | 0.53 | Terrestrial Optical Fiber Drop | 0.45 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0834 | 1 | 834 | 834 | 0405623006 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 3 | 14.1171 | 121.55 | R | 1547 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02806-C08 | PTCI/MIDC | 14.1101 | 121.5584 | 0.16 | Terrestrial Optical Fiber Drop | 0.96 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0835 | 1 | 835 | 835 | 0307110009 | Region III (Central Luzon) | Zambales | San Felipe | San Rafael | 15.0576 | 120.0667 | R | 1224 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00904 | Edgepoint | 15.0611 | 120.0686 | 0.44 | Terrestrial Optical Fiber Drop | 0.46 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0836 | 1 | 836 | 836 | 0603023020 | Region VI (Western Visayas) | Iloilo | Janiuay | Damo-ong | 10.9418 | 122.5157 | R | 1996 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060020 | FTAP BTS | 10.9483 | 122.509 | 1.03 | Terrestrial Optical Fiber Drop | 0.46 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0837 | 1 | 837 | 837 | 0304923029 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion West | 15.7143 | 121.1016 | R | 3651 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03193-B07 | PTCI/MIDC | 15.7165 | 121.0971 | 0.54 | Terrestrial Optical Fiber Drop | 0.46 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0838 | 1 | 838 | 838 | 0105530028 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Poblacion III | 16.113 | 120.545 | R | 1469 | 408 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.55 | Terrestrial Optical Fiber Drop | 0.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0839 | 1 | 839 | 839 | 0506209024 | Region V (Bicol Region) | Sorsogon | Irosin | San Julian | 12.7063 | 124.0344 | U | 2318 | 579 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050226 | FTAP Globe | 12.7081 | 124.0387 | 0.51 | Terrestrial Optical Fiber Drop | 0.46 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0840 | 1 | 840 | 840 | 0307701011 | Region III (Central Luzon) | Aurora | Baler | Sabang | 15.7599 | 121.5676 | R | 3274 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03289-B06 | PTCI/MIDC | 15.7633 | 121.5658 | 0.42 | Terrestrial Optical Fiber Drop | 0.46 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0841 | 1 | 841 | 841 | 0405625007 | Region IV-A (CALABARZON) | Quezon | Macalelon | Luctob | 13.7473 | 122.1323 | R | 1901 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.77 | Terrestrial Optical Fiber Drop | 0.46 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0842 | 1 | 842 | 842 | 0631000099 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Burgos-Mabini-Plaza | 10.7173 | 122.5656 | U | 1865 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0032 | PTCI/MIDC | 10.7162 | 122.5662 | 0.14 | Terrestrial Optical Fiber Drop | 0.46 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0843 | 1 | 843 | 843 | 0704610019 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Poblacion No. 1 | 9.3091 | 123.3044 | R | 2229 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLR0022 | PTCI/MIDC | 9.2995 | 123.3026 | 0.39 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0844 | 1 | 844 | 844 | 0331400016 | Region III (Central Luzon) | Zambales | City of Olongapo | New Kababae | 14.8315 | 120.2772 | R | 2465 | 666 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.32 | Terrestrial Optical Fiber Drop | 0.46 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0845 | 1 | 845 | 845 | 0306913015 | Region III (Central Luzon) | Tarlac | San Clemente | Poblacion Sur | 15.7118 | 120.3605 | R | 1691 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01813-B07 | PTCI/MIDC | 15.7092 | 120.3597 | 0.3 | Terrestrial Optical Fiber Drop | 0.46 | 6.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0846 | 1 | 846 | 846 | 0105530010 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Cablong | 16.1145 | 120.5468 | U | 2413 | 670 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.74 | Terrestrial Optical Fiber Drop | 0.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0847 | 1 | 847 | 847 | 0908302029 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Datu Panas | 7.7369 | 123.0572 | R | 2219 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.66 | Terrestrial Optical Fiber Drop | 0.82 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0848 | 1 | 848 | 848 | 0307110007 | Region III (Central Luzon) | Zambales | San Felipe | Manglicmot | 15.0556 | 120.071 | R | 1827 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0003 | PTCI/MIDC | 15.0546 | 120.0704 | 0.13 | Terrestrial Optical Fiber Drop | 0.47 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0849 | 1 | 849 | 849 | 0402116002 | Region IV-A (CALABARZON) | Cavite | Noveleta | Poblacion | 14.4264 | 120.8802 | R | 2291 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.46 | Terrestrial Optical Fiber Drop | 0.46 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0850 | 1 | 850 | 850 | 0730600087 | Region VII (Central Visayas) | Cebu | City of Cebu | Zapatera | 10.3036 | 123.9021 | U | 2961 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0033 | PTCI/MIDC | 10.303 | 123.8978 | 0.48 | Terrestrial Optical Fiber Drop | 0.47 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0851 | 1 | 851 | 851 | 1004325015 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Santa Ines | 8.9688 | 124.9405 | R | 2015 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100108 | FTAP Globe | 8.9649 | 124.9453 | 0.69 | Terrestrial Optical Fiber Drop | 0.46 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0852 | 1 | 852 | 852 | 1030500050 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Indahag | 8.4313 | 124.6703 | U | 18154 | 5042 | 1513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0007 | PTCI/MIDC | 8.4333 | 124.6676 | 0.36 | Terrestrial Optical Fiber Drop | 0.46 | 4.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0853 | 1 | 853 | 853 | 0203115006 | Region II (Cagayan Valley) | Isabela | Jones | Barangay I | 16.5614 | 121.7002 | U | 2314 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00305 | Edgepoint | 16.5618 | 121.7013 | 0.13 | Terrestrial Optical Fiber Drop | 0.47 | 12.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0854 | 1 | 854 | 854 | 1381300129 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Vasra | 14.6589 | 121.0466 | U | 7883 | 2036 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02667 | Edgepoint | 14.6595 | 121.0502 | 0.39 | Terrestrial Optical Fiber Drop | 0.47 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0855 | 1 | 855 | 855 | 0403417038 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Palina | 14.1411 | 121.4132 | R | 1685 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.31 | Terrestrial Optical Fiber Drop | 0.49 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0856 | 1 | 856 | 856 | 1102411012 | Region XI (Davao Region) | Davao del Sur | Padada | Quirino District | 6.6444 | 125.3459 | R | 1762 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.7 | Terrestrial Optical Fiber Drop | 1.01 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0857 | 1 | 857 | 857 | 0702205014 | Region VII (Central Visayas) | Cebu | Argao | Canbanua | 9.8848 | 123.5946 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070017 | FTAP BTS | 9.8956 | 123.5985 | 1.28 | Terrestrial Optical Fiber Drop | 0.47 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0858 | 1 | 858 | 858 | 1108207013 | Region XI (Davao Region) | Davao de Oro | Monkayo | Poblacion | 7.8247 | 126.0529 | U | 20867 | 5639 | 1692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDOG0003 | PTCI/MIDC | 7.8235 | 126.0516 | 0.19 | Terrestrial Optical Fiber Drop | 0.47 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0859 | 1 | 859 | 859 | 0301421041 | Region III (Central Luzon) | Bulacan | San Miguel | Salangan | 15.1341 | 120.9593 | U | 5606 | 1601 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00858 | Edgepoint | 15.1312 | 120.9589 | 0.33 | Terrestrial Optical Fiber Drop | 0.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0860 | 1 | 860 | 860 | 0405646034 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Isidro | 14.016 | 122.4656 | R | 1231 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0817 | FTAP Smart | 14.0255 | 122.4572 | 1.39 | Terrestrial Optical Fiber Drop | 0.47 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0861 | 1 | 861 | 861 | 0301420001 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay I | 14.8453 | 121.0483 | U | 7593 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0042 | PTCI/MIDC | 14.818 | 121.0664 | 0.22 | Terrestrial Optical Fiber Drop | 1.27 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0862 | 1 | 862 | 862 | 0307104014 | Region III (Central Luzon) | Zambales | Castillejos | San Roque | 14.9297 | 120.2052 | R | 1491 | 392 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.46 | Terrestrial Optical Fiber Drop | 0.47 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0863 | 1 | 863 | 863 | 1380500024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Poblacion | 14.5865 | 121.0249 | U | 16407 | 4728 | 1418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03000-A02 | PTCI/MIDC | 14.5854 | 121.0259 | 0.16 | Terrestrial Optical Fiber Drop | 0.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0864 | 1 | 864 | 864 | 0103306013 | Region I (Ilocos Region) | La Union | Bangar | General Terrero | 16.897 | 120.423 | R | 1150 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.2 | Terrestrial Optical Fiber Drop | 0.47 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0865 | 1 | 865 | 865 | 0631000016 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Banuyao | 10.7048 | 122.5624 | R | 1406 | 334 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0032 | PTCI/MIDC | 10.7162 | 122.5662 | 0.23 | Terrestrial Optical Fiber Drop | 1.17 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0866 | 1 | 866 | 866 | 0300803001 | Region III (Central Luzon) | Bataan | City of Balanga | Bagumbayan | 14.6796 | 120.5464 | R | 2159 | 599 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.61 | Terrestrial Optical Fiber Drop | 0.47 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0867 | 1 | 867 | 867 | 0304921013 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Sinasajan | 15.3494 | 121.0168 | U | 5591 | 1597 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0184 | FTAP Smart | 15.3526 | 121.0171 | 0.35 | Terrestrial Optical Fiber Drop | 0.47 | 7.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0868 | 1 | 868 | 868 | 1630400014 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Bading Pob. | 8.9469 | 125.5394 | U | 5860 | 1429 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.17 | Terrestrial Optical Fiber Drop | 0.47 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0869 | 1 | 869 | 869 | 0501717029 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Isidro Norte | 13.7357 | 123.5201 | R | 1593 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050055 | FTAP Globe | 13.7358 | 123.5217 | 0.18 | Terrestrial Optical Fiber Drop | 0.47 | 5.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0870 | 1 | 870 | 870 | 0405607080 | Region IV-A (CALABARZON) | Quezon | Calauag | Sumulong | 13.959 | 122.3313 | R | 1090 | 286 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | B42 | FTAP Smart | 13.9539 | 122.3 | 3.43 | Terrestrial Optical Fiber Drop | 0.47 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0871 | 1 | 871 | 871 | 0305415002 | Region III (Central Luzon) | Pampanga | Porac | Babo Sacan | 15.0683 | 120.5428 | U | 6277 | 1569 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.1 | Terrestrial Optical Fiber Drop | 0.47 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0872 | 1 | 872 | 872 | 0403416037 | Region IV-A (CALABARZON) | Laguna | Majayjay | Santa Catalina | 14.1472 | 121.4711 | R | 2238 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.32 | Terrestrial Optical Fiber Drop | 0.47 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0873 | 1 | 873 | 873 | 0401007019 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Dacanlao | 13.9393 | 120.7917 | U | 6495 | 1804 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040446 | FTAP Globe | 13.9387 | 120.7992 | 0.82 | Terrestrial Optical Fiber Drop | 0.47 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0874 | 1 | 874 | 874 | 0501606009 | Region V (Bicol Region) | Camarines Norte | Labo | Bayabas | 14.1859 | 122.4694 | R | 1420 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050011 | FTAP Globe | 14.191 | 122.5157 | 5.03 | Terrestrial Optical Fiber Drop | 0.47 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0875 | 1 | 875 | 875 | 0405615004 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin I | 14.0171 | 121.3862 | R | 2719 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040380 | FTAP Globe | 14.0132 | 121.3897 | 0.58 | Terrestrial Optical Fiber Drop | 0.47 | 4.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0876 | 1 | 876 | 876 | 1600210008 | Region XIII (Caraga) | Agusan del Norte | Santiago | San Isidro | 9.1576 | 125.5608 | R | 3099 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130060 | FTAP Globe | 9.1659 | 125.5227 | 4.29 | Terrestrial Optical Fiber Drop | 0.48 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0877 | 1 | 877 | 877 | 1004311014 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Upper Jasaan | 8.6541 | 124.7541 | R | 4469 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.71 | Terrestrial Optical Fiber Drop | 0.48 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0878 | 1 | 878 | 878 | 0601916019 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Norte | 11.4236 | 122.6644 | R | 1267 | 333 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1 | Terrestrial Optical Fiber Drop | 0.47 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0879 | 1 | 879 | 879 | 0105519014 | Region I (Ilocos Region) | Pangasinan | Dasol | Poblacion | 15.9898 | 119.8798 | R | 3471 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.73 | Terrestrial Optical Fiber Drop | 0.47 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0880 | 1 | 880 | 880 | 0102928008 | Region I (Ilocos Region) | Ilocos Sur | Santo Domingo | Camestizoan | 17.6387 | 120.4107 | R | 1181 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01269-B05 | PTCI/MIDC | 17.6374 | 120.4065 | 1.64 | Terrestrial Optical Fiber Drop | 0.9 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0881 | 1 | 881 | 881 | 0205007013 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Malasin | 16.3071 | 121.1053 | U | 5618 | 1478 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01538-B05 | PTCI/MIDC | 16.3062 | 121.1064 | 0.16 | Terrestrial Optical Fiber Drop | 0.48 | 3.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0882 | 1 | 882 | 882 | 0604520025 | Region VI (Western Visayas) | Negros Occidental | Murcia | Talotog | 10.6204 | 123.0644 | R | 2131 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060357 | FTAP Globe | 10.5658 | 123.076 | 0.58 | Terrestrial Optical Fiber Drop | 2.88 | 2.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0883 | 1 | 883 | 883 | 0306909011 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan East | 15.7264 | 120.5717 | R | 1787 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01796-B07 | PTCI/MIDC | 15.7192 | 120.5771 | 0.98 | Terrestrial Optical Fiber Drop | 0.48 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0884 | 1 | 884 | 884 | 0702235020 | Region VII (Central Visayas) | Cebu | Oslob | Poblacion | 9.5247 | 123.4339 | U | 4546 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 0.24 | Terrestrial Optical Fiber Drop | 0.48 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0885 | 1 | 885 | 885 | 0305415018 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Paralaya | 15.1151 | 120.5671 | U | 14310 | 3577 | 1073 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00869 | Edgepoint | 15.1162 | 120.5663 | 0.15 | Terrestrial Optical Fiber Drop | 0.48 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0886 | 1 | 886 | 886 | 0702220002 | Region VII (Central Visayas) | Cebu | Cordova | Bangbang | 10.2589 | 123.9444 | U | 6702 | 1763 | 529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.26 | Terrestrial Optical Fiber Drop | 0.48 | 6.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0887 | 1 | 887 | 887 | 0401014054 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Sabang | 13.9459 | 121.1706 | U | 22810 | 6336 | 1901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040434 | FTAP Globe | 13.9453 | 121.1715 | 0.12 | Terrestrial Optical Fiber Drop | 0.48 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0888 | 1 | 888 | 888 | 0304913020 | Region III (Central Luzon) | Nueva Ecija | Laur | San Juan | 15.5705 | 121.2031 | R | 2654 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03331-B07 | PTCI/MIDC | 15.5639 | 121.1872 | 1.86 | Terrestrial Optical Fiber Drop | 0.48 | 7.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0889 | 1 | 889 | 889 | 0405804028 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pila Pila | 14.4483 | 121.2079 | U | 9034 | 2509 | 753 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040098 | FTAP Globe | 14.4457 | 121.2079 | 0.28 | Terrestrial Optical Fiber Drop | 0.48 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0890 | 1 | 890 | 890 | 0307103015 | Region III (Central Luzon) | Zambales | Candelaria | Poblacion | 15.6275 | 119.9304 | R | 1300 | 342 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.44 | Terrestrial Optical Fiber Drop | 0.48 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0891 | 1 | 891 | 891 | 0205005016 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | District III Pob. | 16.483 | 121.1515 | U | 2564 | 674 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.95 | Terrestrial Optical Fiber Drop | 0.71 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0892 | 1 | 892 | 892 | 0501719016 | Region V (Bicol Region) | Camarines Sur | Lupi | Colacling | 13.7741 | 122.8726 | R | 2738 | 651 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050051 | FTAP Globe | 13.7773 | 122.8741 | 0.38 | Terrestrial Optical Fiber Drop | 0.48 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0893 | 1 | 893 | 893 | 0803740050 | Region VIII (Eastern Visayas) | Leyte | Palompon | Pinagdait Pob. | 11.0485 | 124.3829 | R | 1731 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 9.55 | Terrestrial Optical Fiber Drop | 0.49 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0894 | 1 | 894 | 894 | 0402103068 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba IV | 14.4612 | 120.9602 | U | 3259 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.12 | Terrestrial Optical Fiber Drop | 0.49 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0895 | 1 | 895 | 895 | 0403425020 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Sampaguita Village | 14.3442 | 121.0358 | R | 5416 | 1641 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.54 | Terrestrial Optical Fiber Drop | 0.48 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0896 | 1 | 896 | 896 | 1430300036 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Fairview Village | 16.4159 | 120.5837 | U | 8029 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00335 | Edgepoint | 16.4147 | 120.5826 | 0.17 | Terrestrial Optical Fiber Drop | 0.49 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0897 | 1 | 897 | 897 | 0702219009 | Region VII (Central Visayas) | Cebu | Consolacion | Nangka | 10.3721 | 123.9591 | U | 13307 | 3501 | 1050 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070328 | FTAP Globe | 10.3709 | 123.9588 | 0.14 | Terrestrial Optical Fiber Drop | 0.49 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0898 | 1 | 898 | 898 | 0500508013 | Region V (Bicol Region) | Albay | City of Ligao | Binatagan | 13.2412 | 123.5312 | R | 4002 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 0.93 | Terrestrial Optical Fiber Drop | 0.49 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0899 | 1 | 899 | 899 | 1380400002 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Baritan | 14.6717 | 120.9493 | U | 12461 | 3857 | 1157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00314-A01 | PTCI/MIDC | 14.6731 | 120.9464 | 0.34 | Terrestrial Optical Fiber Drop | 0.49 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0900 | 1 | 900 | 900 | 0306911013 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 2 | 15.6241 | 120.6486 | R | 1260 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.68 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0901 | 1 | 901 | 901 | 1402701023 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Tam-an | 16.9068 | 121.0628 | R | 1481 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.36 | Terrestrial Optical Fiber Drop | 0.49 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0902 | 1 | 902 | 902 | 0102905033 | Region I (Ilocos Region) | Ilocos Sur | Cabugao | Turod-Patac | 17.7889 | 120.458 | R | 968 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILS-00065 | Edgepoint | 17.79 | 120.4556 | 0.3 | Terrestrial Optical Fiber Drop | 0.21 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0903 | 1 | 903 | 903 | 0500514022 | Region V (Bicol Region) | Albay | Polangui | Itaran | 13.3295 | 123.5164 | R | 2247 | 548 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0030 | PTCI/MIDC | 13.3261 | 123.5129 | 0.53 | Terrestrial Optical Fiber Drop | 0.49 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0904 | 1 | 904 | 904 | 1004320008 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Poblacion | 8.4326 | 124.2948 | U | 5900 | 1512 | 454 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0070 | PTCI/MIDC | 8.4298 | 124.2956 | 0.33 | Terrestrial Optical Fiber Drop | 0.49 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0905 | 1 | 905 | 905 | 0103307033 | Region I (Ilocos Region) | La Union | Bauang | Quinavite | 16.5378 | 120.3295 | R | 3893 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 1.19 | Terrestrial Optical Fiber Drop | 0.49 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0906 | 1 | 906 | 906 | 0500516022 | Region V (Bicol Region) | Albay | Santo Domingo | San Roque | 13.2534 | 123.768 | R | 1799 | 438 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.5 | Terrestrial Optical Fiber Drop | 2.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0907 | 1 | 907 | 907 | 0304924017 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Tikiw | 15.3105 | 120.8623 | R | 3172 | 906 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02181 | Edgepoint | 15.3094 | 120.858 | 0.48 | Terrestrial Optical Fiber Drop | 0.49 | 3.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0908 | 1 | 908 | 908 | 0405812020 | Region IV-A (CALABARZON) | Rizal | Tanay | Wawa | 14.4928 | 121.285 | U | 8036 | 2232 | 670 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01876 | Edgepoint | 14.4917 | 121.282 | 0.35 | Terrestrial Optical Fiber Drop | 0.5 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0909 | 1 | 909 | 909 | 1381300141 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Greater Lagro | 14.7306 | 121.0662 | U | 24104 | 6244 | 1873 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00326-A01 | PTCI/MIDC | 14.7312 | 121.067 | 0.11 | Terrestrial Optical Fiber Drop | 0.5 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0910 | 1 | 910 | 910 | 0704619020 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion III | 9.0597 | 123.0357 | R | 3757 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0045 | PTCI/MIDC | 9.0635 | 123.0334 | 0.5 | Terrestrial Optical Fiber Drop | 0.5 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0911 | 1 | 911 | 911 | 0603034021 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion North | 10.6908 | 122.4842 | R | 1342 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060151 | FTAP BTS | 10.6858 | 122.4903 | 0.86 | Terrestrial Optical Fiber Drop | 0.5 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0912 | 1 | 912 | 912 | 0501730037 | Region V (Bicol Region) | Camarines Sur | Ragay | F. Simeon | 13.8445 | 122.701 | R | 3119 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050043 | FTAP Globe | 13.8306 | 122.7251 | 3.03 | Terrestrial Optical Fiber Drop | 0.5 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0913 | 1 | 913 | 913 | 0501706021 | Region V (Bicol Region) | Camarines Sur | Bula | Sagrada | 13.4759 | 123.2799 | R | 2017 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.49 | Terrestrial Optical Fiber Drop | 0.5 | 4.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0914 | 1 | 914 | 914 | 0702220011 | Region VII (Central Visayas) | Cebu | Cordova | Pilipog | 10.2663 | 123.9462 | U | 4765 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0230 | PTCI/MIDC | 10.2681 | 123.9526 | 0.73 | Terrestrial Optical Fiber Drop | 0.5 | 6.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0915 | 1 | 915 | 915 | 0402103009 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Kaingin | 14.4416 | 120.9718 | R | 3688 | 1084 | 325 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040108 | FTAP Globe | 14.4232 | 120.9631 | 0.21 | Terrestrial Optical Fiber Drop | 1.99 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0916 | 1 | 916 | 916 | 1430300026 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cresencia Village | 16.4196 | 120.588 | R | 1680 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0024 | PTCI/MIDC | 16.4185 | 120.5888 | 0.16 | Terrestrial Optical Fiber Drop | 0.5 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0917 | 1 | 917 | 917 | 0304932021 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Rafael | 15.454 | 120.794 | R | 1489 | 425 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.9 | Terrestrial Optical Fiber Drop | 0.5 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0918 | 1 | 918 | 918 | 0402109047 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VIII | 14.4073 | 120.936 | U | 2881 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03245-C08 | PTCI/MIDC | 14.4097 | 120.9383 | 0.36 | Terrestrial Optical Fiber Drop | 0.5 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0919 | 1 | 919 | 919 | 1705204012 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Poblacion | 12.3264 | 121.3421 | U | 3852 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03378-C09 | PTCI/MIDC | 12.32 | 121.3406 | 0.73 | Terrestrial Optical Fiber Drop | 0.5 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0920 | 1 | 920 | 920 | 0403425016 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Vicente | 14.3415 | 121.0438 | U | 30211 | 9154 | 2746 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.38 | Terrestrial Optical Fiber Drop | 0.5 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0921 | 1 | 921 | 921 | 0403404013 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pulo | 14.2423 | 121.1318 | U | 38490 | 11663 | 3499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02046-C08 | PTCI/MIDC | 14.239 | 121.1339 | 0.43 | Terrestrial Optical Fiber Drop | 0.5 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0922 | 1 | 922 | 922 | 0403426014 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay I | 14.2788 | 121.4177 | R | 1367 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.63 | Terrestrial Optical Fiber Drop | 0.5 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0923 | 1 | 923 | 923 | 0501707001 | Region V (Bicol Region) | Camarines Sur | Cabusao | Barcelonita | 13.7722 | 123.0446 | R | 2478 | 590 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050056 | FTAP Globe | 13.7336 | 123.0213 | 4.98 | Terrestrial Optical Fiber Drop | 0.5 | 6.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0924 | 1 | 924 | 924 | 0305413032 | Region III (Central Luzon) | Pampanga | Mexico | San Lorenzo | 15.0682 | 120.7374 | R | 2989 | 747 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01646-B07 | PTCI/MIDC | 15.0675 | 120.7391 | 0.19 | Terrestrial Optical Fiber Drop | 0.5 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0925 | 1 | 925 | 925 | 0702219002 | Region VII (Central Visayas) | Cebu | Consolacion | Cansaga | 10.3788 | 123.9627 | U | 6651 | 1750 | 525 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00111-D12 | PTCI/MIDC | 10.3742 | 123.9666 | 0.67 | Terrestrial Optical Fiber Drop | 0.5 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0926 | 1 | 926 | 926 | 0403405032 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mayapa | 14.2113 | 121.1273 | U | 31024 | 9401 | 2820 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03063-C08 | PTCI/MIDC | 14.21 | 121.1283 | 0.18 | Terrestrial Optical Fiber Drop | 0.5 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0927 | 1 | 927 | 927 | 0500514013 | Region V (Bicol Region) | Albay | Polangui | Centro Occidental | 13.2965 | 123.4865 | U | 3335 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 0.99 | Terrestrial Optical Fiber Drop | 0.5 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0928 | 1 | 928 | 928 | 0305406026 | Region III (Central Luzon) | Pampanga | Floridablanca | San Jose | 14.9853 | 120.511 | U | 9350 | 2337 | 701 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00959 | Edgepoint | 14.988 | 120.5114 | 0.3 | Terrestrial Optical Fiber Drop | 0.51 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0929 | 1 | 929 | 929 | 0405804002 | Region IV-A (CALABARZON) | Rizal | Binangonan | Batingan | 14.4726 | 121.1968 | U | 15585 | 4329 | 1299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0011 | PTCI/MIDC | 14.4723 | 121.1985 | 0.19 | Terrestrial Optical Fiber Drop | 0.5 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0930 | 1 | 930 | 930 | 0306914002 | Region III (Central Luzon) | Tarlac | San Manuel | Lanat | 15.7923 | 120.6061 | R | 2429 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 0.95 | Terrestrial Optical Fiber Drop | 0.51 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0931 | 1 | 931 | 931 | 1001305013 | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Poblacion | 8.3065 | 125.002 | U | 14202 | 3737 | 1121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0012 | PTCI/MIDC | 8.3034 | 124.9993 | 0.45 | Terrestrial Optical Fiber Drop | 0.51 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0932 | 1 | 932 | 932 | 0600413022 | Region VI (Western Visayas) | Aklan | Malinao | Tambuan | 11.6252 | 122.3008 | R | 1277 | 327 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060219 | FTAP Globe | 11.6476 | 122.3063 | 2.56 | Terrestrial Optical Fiber Drop | 0.51 | 4.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0933 | 1 | 933 | 933 | 0405801010 | Region IV-A (CALABARZON) | Rizal | Angono | San Pedro | 14.5296 | 121.1537 | U | 1739 | 483 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 450 | FTAP Smart | 14.5268 | 121.1582 | 0.13 | Terrestrial Optical Fiber Drop | 0.25 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0934 | 1 | 934 | 934 | 0402104019 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 8 | 14.3137 | 121.0538 | R | 3290 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.55 | Terrestrial Optical Fiber Drop | 0.51 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0935 | 1 | 935 | 935 | 0500506011 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 15 - Ilawod East Pob. | 13.1488 | 123.7527 | U | 2206 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0039 | PTCI/MIDC | 13.1354 | 123.7419 | 0.61 | Terrestrial Optical Fiber Drop | 1.85 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0936 | 1 | 936 | 936 | 0604527005 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 5 | 9.7526 | 122.4009 | R | 3304 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060396 | FTAP Globe | 9.7491 | 122.4063 | 0.71 | Terrestrial Optical Fiber Drop | 0.51 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0937 | 1 | 937 | 937 | 0102933025 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Las-ud | 16.939 | 120.4408 | R | 1128 | 296 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.11 | Terrestrial Optical Fiber Drop | 0.51 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0938 | 1 | 938 | 938 | 0306905032 | Region III (Central Luzon) | Tarlac | Concepcion | San Jose | 15.3264 | 120.6605 | U | 10904 | 2795 | 839 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00763 | Edgepoint | 15.323 | 120.6635 | 0.49 | Terrestrial Optical Fiber Drop | 0.51 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0939 | 1 | 939 | 939 | 0105531036 | Region I (Ilocos Region) | Pangasinan | Rosales | Don Antonio Village | 15.8915 | 120.6272 | R | 859 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01756-B07 | PTCI/MIDC | 15.8943 | 120.6276 | 0.32 | Terrestrial Optical Fiber Drop | 0.51 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0940 | 1 | 940 | 940 | 1380900013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Tangos South | 14.6582 | 120.9484 | U | 18971 | 5498 | 1649 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01485 | Edgepoint | 14.6538 | 120.9609 | 0.35 | Terrestrial Optical Fiber Drop | 0.31 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0941 | 1 | 941 | 941 | 0105523007 | Region I (Ilocos Region) | Pangasinan | Mabini | Cabinuangan | 16.0817 | 119.9226 | R | 1568 | 435 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-00410 | Edgepoint | 16.0915 | 119.94 | 2.15 | Terrestrial Optical Fiber Drop | 0.51 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0942 | 1 | 942 | 942 | 1600301016 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Poblacion | 8.7144 | 125.7519 | U | 16880 | 4328 | 1298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0001 | PTCI/MIDC | 8.7141 | 125.7595 | 0.83 | Terrestrial Optical Fiber Drop | 0.51 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0943 | 1 | 943 | 943 | 1102401023 | Region XI (Davao Region) | Davao del Sur | Bansalan | Tubod | 6.792 | 125.2119 | R | 3650 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0001 | PTCI/MIDC | 6.7864 | 125.2163 | 0.79 | Terrestrial Optical Fiber Drop | 0.51 | 16.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0944 | 1 | 944 | 944 | 0103306005 | Region I (Ilocos Region) | La Union | Bangar | Bangaoilan West | 16.9001 | 120.4476 | R | 1049 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.23 | Terrestrial Optical Fiber Drop | 2.53 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0945 | 1 | 945 | 945 | 0501603030 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VII | 14.1164 | 122.958 | U | 1936 | 484 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03029-C10 | PTCI/MIDC | 14.1154 | 122.961 | 0.34 | Terrestrial Optical Fiber Drop | 0.51 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0946 | 1 | 946 | 946 | 0301423025 | Region III (Central Luzon) | Bulacan | Santa Maria | Tumana | 14.8131 | 120.9736 | U | 10877 | 3107 | 932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01171 | Edgepoint | 14.8148 | 120.9767 | 0.39 | Terrestrial Optical Fiber Drop | 0.51 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0947 | 1 | 947 | 947 | 0403406015 | Region IV-A (CALABARZON) | Laguna | Calauan | Prinza | 14.1424 | 121.3168 | R | 3113 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040288 | FTAP Globe | 14.1455 | 121.3143 | 0.44 | Terrestrial Optical Fiber Drop | 0.51 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0948 | 1 | 948 | 948 | 1130700158 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 25-C | 7.0865 | 125.6131 | U | 2000 | 588 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110454 | FTAP Globe | 7.185 | 125.4541 | 0.53 | Terrestrial Optical Fiber Drop | 1.03 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0949 | 1 | 949 | 949 | 0506208033 | Region V (Bicol Region) | Sorsogon | Gubat | Pinontingan | 12.9191 | 124.1257 | R | 1481 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 0.61 | Terrestrial Optical Fiber Drop | 0.51 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0950 | 1 | 950 | 950 | 0631000040 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Cuartero | 10.7236 | 122.5547 | U | 2173 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.07 | Terrestrial Optical Fiber Drop | 1.82 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0951 | 1 | 951 | 951 | 0203126016 | Region II (Cagayan Valley) | Isabela | Roxas | Rang-ayan | 17.1159 | 121.6249 | R | 1511 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01359-B06 | PTCI/MIDC | 17.1149 | 121.6222 | 0.29 | Terrestrial Optical Fiber Drop | 1.03 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0952 | 1 | 952 | 952 | 1380400016 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | San Agustin | 14.6622 | 120.9525 | U | 10993 | 3105 | 932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00261-A01 | PTCI/MIDC | 14.6619 | 120.951 | 0.16 | Terrestrial Optical Fiber Drop | 0.51 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0953 | 1 | 953 | 953 | 0501702013 | Region V (Bicol Region) | Camarines Sur | Balatan | Siramag | 13.3185 | 123.2398 | U | 4957 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050137 | FTAP Globe | 13.3165 | 123.2349 | 0.57 | Terrestrial Optical Fiber Drop | 0.51 | 14.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0954 | 1 | 954 | 954 | 1102403029 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 2 | 6.7505 | 125.3573 | U | 7839 | 2305 | 692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0071 | PTCI/MIDC | 6.7534 | 125.365 | 0.91 | Terrestrial Optical Fiber Drop | 0.52 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0955 | 1 | 955 | 955 | 0600401011 | Region VI (Western Visayas) | Aklan | Altavas | Poblacion | 11.535 | 122.4913 | R | 4795 | 1229 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 4.05 | Terrestrial Optical Fiber Drop | 0.51 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0956 | 1 | 956 | 956 | 0402103002 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban I | 14.461 | 120.9641 | U | 3517 | 1034 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040108 | FTAP Globe | 14.4232 | 120.9631 | 0.76 | Terrestrial Optical Fiber Drop | 0.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0957 | 1 | 957 | 957 | 0402106027 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Dionisio | 14.32 | 120.9566 | U | 7096 | 2087 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0032 | PTCI/MIDC | 14.3181 | 120.9773 | 0.25 | Terrestrial Optical Fiber Drop | 1.29 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0958 | 1 | 958 | 958 | 0301411003 | Region III (Central Luzon) | Bulacan | Marilao | Ibayo | 14.753 | 120.9597 | U | 8686 | 2481 | 744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0008 | PTCI/MIDC | 14.7535 | 120.9607 | 0.12 | Terrestrial Optical Fiber Drop | 0.52 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0959 | 1 | 959 | 959 | 0501606051 | Region V (Bicol Region) | Camarines Norte | Labo | Talobatib | 14.1816 | 122.7854 | R | 3954 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050012 | FTAP Globe | 14.1849 | 122.7842 | 0.39 | Terrestrial Optical Fiber Drop | 0.52 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0960 | 1 | 960 | 960 | 0405615016 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin II | 14.0169 | 121.3863 | R | 2231 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040380 | FTAP Globe | 14.0132 | 121.3897 | 0.68 | Terrestrial Optical Fiber Drop | 0.46 | 4.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0961 | 1 | 961 | 961 | 0405809004 | Region IV-A (CALABARZON) | Rizal | Morong | Maybancal | 14.5251 | 121.2424 | U | 17211 | 4780 | 1434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01858 | Edgepoint | 14.5223 | 121.2408 | 0.36 | Terrestrial Optical Fiber Drop | 0.52 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0962 | 1 | 962 | 962 | 0402120005 | Region IV-A (CALABARZON) | Cavite | Tanza | Bucal | 14.3903 | 120.8622 | U | 17246 | 5072 | 1522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.27 | Terrestrial Optical Fiber Drop | 0.52 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0963 | 1 | 963 | 963 | 0501605012 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Parang | 14.2814 | 122.6941 | U | 6242 | 1560 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050004 | FTAP Globe | 14.2889 | 122.6958 | 0.85 | Terrestrial Optical Fiber Drop | 0.52 | 9.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0964 | 1 | 964 | 964 | 0908305023 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Poblacion | 7.7802 | 122.5881 | U | 4596 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0004 | PTCI/MIDC | 7.7816 | 122.588 | 0.16 | Terrestrial Optical Fiber Drop | 0.52 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0965 | 1 | 965 | 965 | 1001321022 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Nabago | 7.9094 | 125.094 | R | 2872 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 1.2 | Terrestrial Optical Fiber Drop | 0.44 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0966 | 1 | 966 | 966 | 0405809006 | Region IV-A (CALABARZON) | Rizal | Morong | San Jose | 14.525 | 121.2425 | R | 4110 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01858 | Edgepoint | 14.5223 | 121.2408 | 0.35 | Terrestrial Optical Fiber Drop | 0.51 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0967 | 1 | 967 | 967 | 1206312014 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Poblacion | 6.2184 | 125.0694 | U | 53313 | 14809 | 4443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCG0044 | PTCI/MIDC | 6.2191 | 125.075 | 0.63 | Terrestrial Optical Fiber Drop | 0.52 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0968 | 1 | 968 | 968 | 0604528041 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 2 | 10.7438 | 122.9641 | U | 2184 | 590 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060161 | FTAP BTS | 10.7427 | 122.9638 | 0.12 | Terrestrial Optical Fiber Drop | 0.23 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0969 | 1 | 969 | 969 | 0402109003 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-A | 14.4023 | 120.9405 | U | 6594 | 1939 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040121 | FTAP Globe | 14.4038 | 120.9443 | 0.44 | Terrestrial Optical Fiber Drop | 0.52 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0970 | 1 | 970 | 970 | 0631000032 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Calumpang | 10.687 | 122.5398 | U | 16557 | 3942 | 1183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0026 | PTCI/MIDC | 10.6895 | 122.5363 | 0.48 | Terrestrial Optical Fiber Drop | 0.52 | 3.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0971 | 1 | 971 | 971 | 0301412008 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Hulo | 14.7327 | 120.9569 | U | 2804 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01030-B07 | PTCI/MIDC | 14.7397 | 120.9711 | 0.31 | Terrestrial Optical Fiber Drop | 1.39 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0972 | 1 | 972 | 972 | 0305416010 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dolores | 15.0361 | 120.6827 | U | 21795 | 5448 | 1634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02616-B07 | PTCI/MIDC | 15.0339 | 120.6814 | 0.28 | Terrestrial Optical Fiber Drop | 0.52 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0973 | 1 | 973 | 973 | 1381300084 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Project 6 | 14.6626 | 121.0399 | U | 12595 | 4011 | 1203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000183 | FTAP Globe | 14.662 | 121.0414 | 0.18 | Terrestrial Optical Fiber Drop | 0.52 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0974 | 1 | 974 | 974 | 0102805044 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Tabug | 18.0543 | 120.5566 | R | 3406 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00049 | Edgepoint | 18.0553 | 120.5558 | 0.14 | Terrestrial Optical Fiber Drop | 0.52 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0975 | 1 | 975 | 975 | 1408107013 | Cordillera Administrative Region (CAR) | Apayao | Santa Marcela | San Carlos | 18.2913 | 121.436 | R | 1525 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-APA-02247 | Edgepoint | 18.2887 | 121.4356 | 0.3 | Terrestrial Optical Fiber Drop | 0.53 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0976 | 1 | 976 | 976 | 0301403005 | Region III (Central Luzon) | Bulacan | Baliuag | Concepcion | 14.9527 | 120.8889 | U | 10619 | 3034 | 910 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01065-B07 | PTCI/MIDC | 14.9538 | 120.8908 | 0.24 | Terrestrial Optical Fiber Drop | 0.53 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0977 | 1 | 977 | 977 | 0402113002 | Region IV-A (CALABARZON) | Cavite | Maragondon | Bucal I | 14.2729 | 120.7412 | R | 3478 | 1022 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02184-C08 | PTCI/MIDC | 14.2716 | 120.7386 | 0.31 | Terrestrial Optical Fiber Drop | 0.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0978 | 1 | 978 | 978 | 0203126025 | Region II (Cagayan Valley) | Isabela | Roxas | Sotero Nuesa | 17.1204 | 121.6137 | U | 6564 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0060 | PTCI/MIDC | 17.1203 | 121.6155 | 0.19 | Terrestrial Optical Fiber Drop | 0.53 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0979 | 1 | 979 | 979 | 0403428018 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pulong Santa Cruz | 14.28 | 121.0855 | U | 32250 | 9772 | 2932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0009 | PTCI/MIDC | 14.2828 | 121.0916 | 0.73 | Terrestrial Optical Fiber Drop | 0.53 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0980 | 1 | 980 | 980 | 0105520012 | Region I (Ilocos Region) | Pangasinan | Infanta | Poblacion | 15.8224 | 119.9069 | R | 3276 | 910 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00569 | Edgepoint | 15.8208 | 119.9067 | 0.18 | Terrestrial Optical Fiber Drop | 0.53 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0981 | 1 | 981 | 981 | 0403425004 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | G.S.I.S. | 14.3414 | 121.0439 | R | 3100 | 939 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040151 | FTAP Globe | 14.347 | 121.0481 | 0.46 | Terrestrial Optical Fiber Drop | 0.52 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0982 | 1 | 982 | 982 | 0102822020 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Santa Ana | 18.1 | 120.7667 | R | 1302 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01220-B05 | PTCI/MIDC | 18.0958 | 120.7728 | 0.8 | Terrestrial Optical Fiber Drop | 0.53 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0983 | 1 | 983 | 983 | 0803738062 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Macabug | 10.9583 | 124.653 | U | 3817 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0042 | PTCI/MIDC | 10.9609 | 124.652 | 0.3 | Terrestrial Optical Fiber Drop | 0.53 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0984 | 1 | 984 | 984 | 1381300067 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Milagrosa | 14.6218 | 121.0682 | U | 6923 | 1688 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00470-A01 | PTCI/MIDC | 14.6229 | 121.0671 | 0.18 | Terrestrial Optical Fiber Drop | 0.53 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0985 | 1 | 985 | 985 | 0704623008 | Region VII (Central Visayas) | Negros Oriental | Valencia | Bong-ao | 9.2789 | 123.2487 | R | 3361 | 884 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070270 | FTAP Globe | 9.2811 | 123.2423 | 0.74 | Terrestrial Optical Fiber Drop | 0.53 | 4.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0986 | 1 | 986 | 986 | 0501720010 | Region V (Bicol Region) | Camarines Sur | Magarao | San Juan | 13.6624 | 123.1895 | R | 1180 | 280 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 0.88 | Terrestrial Optical Fiber Drop | 1.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0987 | 1 | 987 | 987 | 1004311009 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Natubo | 8.6573 | 124.7536 | R | 2804 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 4.98 | Terrestrial Optical Fiber Drop | 0.84 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1011 | 1 | 988 | 988 | 0102804012 | Region I (Ilocos Region) | Ilocos Norte | Bangui | San Lorenzo | 18.5383 | 120.7636 | R | 2295 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILN-03184 | Edgepoint | 18.5335 | 120.7602 | 0.64 | Terrestrial Optical Fiber Drop | 0.54 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0989 | 1 | 989 | 989 | 0506215002 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Peñafrancia | 12.6354 | 124.0936 | R | 852 | 213 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.13 | Terrestrial Optical Fiber Drop | 1.74 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0990 | 1 | 990 | 990 | 0402104017 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 6 | 14.3139 | 121.054 | R | 767 | 225 | 68 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02005-C08 | PTCI/MIDC | 14.2994 | 121.0588 | 0.17 | Terrestrial Optical Fiber Drop | 0.53 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0991 | 1 | 991 | 991 | 1381300110 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Santol | 14.6126 | 121.0154 | U | 6590 | 1757 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01637 | Edgepoint | 14.6126 | 121.0162 | 0.08 | Terrestrial Optical Fiber Drop | 0.53 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0992 | 1 | 992 | 992 | 0105535018 | Region I (Ilocos Region) | Pangasinan | San Manuel | Sto. Domingo | 16.0712 | 120.6397 | U | 6146 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01761-B07 | PTCI/MIDC | 16.0657 | 120.6724 | 0.27 | Terrestrial Optical Fiber Drop | 3.16 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0993 | 1 | 993 | 993 | 0603035040 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilaya | 11.1093 | 122.6436 | U | 2603 | 685 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060054 | FTAP BTS | 11.1194 | 122.6461 | 1.15 | Terrestrial Optical Fiber Drop | 0.54 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0994 | 1 | 994 | 994 | 1381200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Kapasigan | 14.567 | 121.0845 | U | 4952 | 1519 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01786 | Edgepoint | 14.5755 | 121.0794 | 0.09 | Terrestrial Optical Fiber Drop | 0.34 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0995 | 1 | 995 | 995 | 0501731017 | Region V (Bicol Region) | Camarines Sur | Sagñay | San Isidro | 13.6054 | 123.5246 | R | 1378 | 328 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050090 | FTAP Globe | 13.6036 | 123.5204 | 0.49 | Terrestrial Optical Fiber Drop | 0.54 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0996 | 1 | 996 | 996 | 0401008018 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 3 | 13.8322 | 120.6343 | R | 1065 | 295 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 0.71 | Terrestrial Optical Fiber Drop | 0.53 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0997 | 1 | 997 | 997 | 0500517040 | Region V (Bicol Region) | Albay | City of Tabaco | San Ramon | 13.3479 | 123.7313 | R | 3225 | 786 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ALB-02560 | Edgepoint | 13.3488 | 123.728 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0998 | 1 | 998 | 998 | 0304906044 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | San Jose | 15.7781 | 120.6691 | R | 1437 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01474-B07 | PTCI/MIDC | 15.7777 | 120.6688 | 0.05 | Terrestrial Optical Fiber Drop | 0.54 | 6.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0999 | 1 | 999 | 999 | 0500510021 | Region V (Bicol Region) | Albay | Malinao | Poblacion | 13.3977 | 123.7059 | R | 654 | 159 | 48 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050124 | FTAP Globe | 13.3997 | 123.7064 | 0.23 | Terrestrial Optical Fiber Drop | 0.54 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1000 | 1 | 1000 | 1000 | 0405625023 | Region IV-A (CALABARZON) | Quezon | Macalelon | San Isidro | 13.75 | 122.1333 | R | 784 | 206 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.63 | Terrestrial Optical Fiber Drop | 0.54 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0710 | 2 | 1 | 1001 | 0405642012 | Region IV-A (CALABARZON) | Quezon | San Francisco | Poblacion | 13.3494 | 122.5199 | U | 5458 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040623 | FTAP Globe | 13.3485 | 122.5191 | 0.14 | Satellite LEO Backhaul (Starlink Business) | 0.4 | 23.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1002 | 2 | 2 | 1002 | 0501608019 | Region V (Bicol Region) | Camarines Norte | Paracale | Palanas | 14.2794 | 122.7916 | R | 4124 | 1031 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.43 | Terrestrial Optical Fiber Drop | 0.54 | 9.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0733 | 2 | 3 | 1003 | 0205007022 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Macabenga | 16.2108 | 121.2328 | R | 1807 | 475 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUV-00385 | Edgepoint | 16.1959 | 121.2371 | 1.72 | Satellite LEO Backhaul (Starlink Business) | 0.41 | 21.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0010 | 2 | 4 | 1004 | 0405640007 | Region IV-A (CALABARZON) | Quezon | San Andres | Poblacion | 13.3238 | 122.6769 | U | 5242 | 1379 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02071 | Edgepoint | 13.3259 | 122.6776 | 0.24 | Satellite LEO Backhaul (Starlink Business) | 0.05 | 29.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1005 | 2 | 5 | 1005 | 0401020001 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Banaba | 13.8858 | 121.2177 | R | 3949 | 1096 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 1.17 | Terrestrial Optical Fiber Drop | 0.54 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1006 | 2 | 6 | 1006 | 1380900018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Tanza 2 | 14.6789 | 120.9337 | U | 16184 | 4650 | 1395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02267-A01 | PTCI/MIDC | 14.6624 | 120.9638 | 0.21 | Terrestrial Optical Fiber Drop | 0.96 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1007 | 2 | 7 | 1007 | 0803714015 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone I | 11.2923 | 124.6403 | R | 2449 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 1.65 | Terrestrial Optical Fiber Drop | 0.54 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1008 | 2 | 8 | 1008 | 0102924013 | Region I (Ilocos Region) | Ilocos Sur | Santa Cruz | Casilagan | 17.0693 | 120.4595 | R | 908 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTIRG0007 | PTCI/MIDC | 17.0711 | 120.4566 | 0.48 | Terrestrial Optical Fiber Drop | 0.36 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0053 | 2 | 9 | 1009 | 1705312003 | MIMAROPA Region | Palawan | El Nido | Barotuan | 11.3064 | 119.4504 | U | 2900 | 743 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170207 | FTAP Globe | 11.3359 | 119.4569 | 3.36 | Satellite LEO Backhaul (Starlink Business) | 0.09 | 54.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1010 | 2 | 10 | 1010 | 0304903044 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | M. S. Garcia | 15.4772 | 120.9631 | U | 6701 | 1914 | 574 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00715 | Edgepoint | 15.4745 | 120.967 | 0.52 | Terrestrial Optical Fiber Drop | 0.54 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0988 | 2 | 11 | 1011 | 1705312013 | MIMAROPA Region | Palawan | El Nido | Sibaltan | 11.3032 | 119.561 | R | 2377 | 609 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170208 | FTAP Globe | 11.2711 | 119.5606 | 3.57 | Satellite LEO Backhaul (Starlink Business) | 0.53 | 53.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1012 | 2 | 12 | 1012 | 0203108071 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Union | 16.9596 | 121.816 | R | 1605 | 422 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00215 | Edgepoint | 16.9565 | 121.815 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1013 | 2 | 13 | 1013 | 1004321002 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Bagocboc | 8.4178 | 124.5021 | R | 3374 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100152 | FTAP Globe | 8.4584 | 124.5671 | 8.45 | Terrestrial Optical Fiber Drop | 0.54 | 12.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0026 | 2 | 14 | 1014 | 0201506022 | Region II (Cagayan Valley) | Cagayan | Baggao | Dalla | 17.9546 | 121.8907 | R | 1720 | 441 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020022 | FTAP Globe | 17.9559 | 121.9101 | 2.05 | Satellite LEO Backhaul (Starlink Business) | 0.07 | 21.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1015 | 2 | 15 | 1015 | 0603031019 | Region VI (Western Visayas) | Iloilo | Mina | Talibong Pequeño | 10.9406 | 122.5734 | R | 557 | 146 | 44 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 2.46 | Terrestrial Optical Fiber Drop | 1.73 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1016 | 2 | 16 | 1016 | 0403425021 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Calendola | 14.3428 | 121.0355 | R | 4162 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.55 | Terrestrial Optical Fiber Drop | 0.54 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1017 | 2 | 17 | 1017 | 0203101002 | Region II (Cagayan Valley) | Isabela | Alicia | Antonino | 16.7828 | 121.6977 | U | 4886 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0062 | 2 | 18 | 1018 | 1402707017 | Cordillera Administrative Region (CAR) | Ifugao | Alfonso Lista | Santa Maria | 16.891 | 121.4596 | U | 5445 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-IFU-00229 | Edgepoint | 16.9123 | 121.4906 | 4.06 | Satellite LEO Backhaul (Starlink Business) | 0.09 | 21.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1019 | 2 | 19 | 1019 | 0603047007 | Region VI (Western Visayas) | Iloilo | Zarraga | Gines | 10.7402 | 122.5412 | R | 1344 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.92 | Terrestrial Optical Fiber Drop | 2.85 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1020 | 2 | 20 | 1020 | 0403403009 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Langkiwa | 14.2999 | 121.0602 | U | 43327 | 13129 | 3939 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02005-C08 | PTCI/MIDC | 14.2994 | 121.0588 | 0.16 | Terrestrial Optical Fiber Drop | 0.55 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0086 | 2 | 21 | 1021 | 0304907011 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Malinao | 15.483 | 121.3325 | R | 2759 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02887-B07 | PTCI/MIDC | 15.478 | 121.3066 | 2.83 | Satellite LEO Backhaul (Starlink Business) | 0.1 | 23.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0106 | 2 | 22 | 1022 | 0205009003 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Poblacion | 16.3166 | 121.2954 | R | 2596 | 683 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01522-B05 | PTCI/MIDC | 16.3128 | 121.2922 | 0.54 | Satellite LEO Backhaul (Starlink Business) | 0.12 | 21.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1023 | 2 | 23 | 1023 | 0500506042 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 8 - Bagumbayan | 13.1416 | 123.7354 | U | 2781 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050176 | FTAP Globe | 13.1455 | 123.7378 | 0.5 | Terrestrial Optical Fiber Drop | 0.55 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0136 | 2 | 24 | 1024 | 0405620026 | Region IV-A (CALABARZON) | Quezon | Infanta | Libjo | 14.7545 | 121.6659 | R | 2438 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01234 | Edgepoint | 14.7475 | 121.6479 | 2.09 | Satellite LEO Backhaul (Starlink Business) | 0.13 | 42.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1025 | 2 | 25 | 1025 | 0501728010 | Region V (Bicol Region) | Camarines Sur | Pili | La Purisima | 13.5621 | 123.2864 | R | 3202 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0710 | FTAP Smart | 13.5587 | 123.2775 | 1.04 | Terrestrial Optical Fiber Drop | 0.55 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1026 | 2 | 26 | 1026 | 0402106041 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz I | 14.3128 | 120.9607 | U | 5381 | 1582 | 475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.59 | Terrestrial Optical Fiber Drop | 0.55 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0165 | 2 | 27 | 1027 | 0205008008 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Ganao | 16.1647 | 121.1809 | R | 1373 | 361 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-NUV-00385 | Edgepoint | 16.1959 | 121.2371 | 6.93 | Satellite LEO Backhaul (Starlink Business) | 0.15 | 20.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0166 | 2 | 28 | 1028 | 1404405007 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Poblacion | 17.1081 | 121.2787 | R | 1430 | 386 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140139 | FTAP Globe | 17.111 | 121.2786 | 0.32 | Satellite LEO Backhaul (Starlink Business) | 0.15 | 21.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0217 | 2 | 29 | 1029 | 0501711048 | Region V (Bicol Region) | Camarines Sur | Caramoan | Tawog | 13.7728 | 123.8641 | U | 1800 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050052 | FTAP Globe | 13.77 | 123.8625 | 0.35 | Satellite LEO Backhaul (Starlink Business) | 0.18 | 38.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1030 | 2 | 30 | 1030 | 1408105021 | Cordillera Administrative Region (CAR) | Apayao | Luna | San Isidro Sur | 18.3351 | 121.3808 | R | 1739 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140100 | FTAP Globe | 18.3288 | 121.3546 | 2.85 | Terrestrial Optical Fiber Drop | 0.55 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1031 | 2 | 31 | 1031 | 0401004005 | Region IV-A (CALABARZON) | Batangas | Balete | Makina | 14.0201 | 121.1016 | R | 3732 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 0.98 | Terrestrial Optical Fiber Drop | 0.55 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1032 | 2 | 32 | 1032 | 1705202001 | MIMAROPA Region | Oriental Mindoro | Bansud | Alcadesma | 12.8395 | 121.4598 | R | 1907 | 488 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170107 | FTAP Globe | 12.8565 | 121.4577 | 1.9 | Terrestrial Optical Fiber Drop | 0.55 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1033 | 2 | 33 | 1033 | 0604521003 | Region VI (Western Visayas) | Negros Occidental | Pontevedra | Barangay II | 10.368 | 122.8694 | R | 2056 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060374 | FTAP Globe | 10.3746 | 122.8671 | 0.78 | Terrestrial Optical Fiber Drop | 0.55 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1034 | 2 | 34 | 1034 | 0205006003 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Bugnay | 16.6571 | 121.3731 | R | 1750 | 460 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUV_0006 | LDIC | 121.3694 | 16.6623 | 0.7 | Terrestrial Optical Fiber Drop | 0.55 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1035 | 2 | 35 | 1035 | 0306916059 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Francisco | 15.4239 | 120.5974 | R | 3004 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.96 | Terrestrial Optical Fiber Drop | 0.55 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1036 | 2 | 36 | 1036 | 0301412018 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Pantoc | 14.766 | 120.9839 | U | 13146 | 3756 | 1127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01214 | Edgepoint | 14.7649 | 120.9827 | 0.18 | Terrestrial Optical Fiber Drop | 0.55 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1037 | 2 | 37 | 1037 | 1004308045 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 20 | 8.8269 | 125.1003 | U | 3364 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.33 | Terrestrial Optical Fiber Drop | 0.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0262 | 2 | 38 | 1038 | 0504117036 | Region V (Bicol Region) | Masbate | Placer | Villa Inocencio | 11.8695 | 123.9082 | U | 5173 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03138-C10 | PTCI/MIDC | 11.869 | 123.9056 | 0.28 | Satellite LEO Backhaul (Starlink Business) | 0.2 | 40.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1039 | 2 | 39 | 1039 | 0405810008 | Region IV-A (CALABARZON) | Rizal | Pililla | Quisao | 14.4365 | 121.3356 | U | 16563 | 4600 | 1380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01902 | Edgepoint | 14.438 | 121.3354 | 0.17 | Terrestrial Optical Fiber Drop | 0.55 | 2.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1040 | 2 | 40 | 1040 | 1630400071 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Ong Yiu Pob. | 8.9558 | 125.5369 | U | 5507 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130071 | FTAP Globe | 8.9621 | 125.5348 | 0.74 | Terrestrial Optical Fiber Drop | 0.55 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0297 | 2 | 41 | 1041 | 0405617001 | Region IV-A (CALABARZON) | Quezon | General Nakar | Anoling | 14.7554 | 121.6236 | R | 3791 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040005 | FTAP Globe | 14.7565 | 121.6198 | 0.43 | Satellite LEO Backhaul (Starlink Business) | 0.22 | 40.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0303 | 2 | 42 | 1042 | 0500513006 | Region V (Bicol Region) | Albay | Pio Duran | Binodegahan | 13.0616 | 123.4584 | R | 2590 | 631 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0038 | PTCI/MIDC | 13.0561 | 123.4573 | 0.62 | Satellite LEO Backhaul (Starlink Business) | 0.22 | 20.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0519 | 2 | 43 | 1043 | 0405638004 | Region IV-A (CALABARZON) | Quezon | Real | Kiloloran | 14.6422 | 121.6065 | R | 2230 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01455 | Edgepoint | 14.6633 | 121.6056 | 2.35 | Satellite LEO Backhaul (Starlink Business) | 0.31 | 28.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1044 | 2 | 44 | 1044 | 0105514017 | Region I (Ilocos Region) | Pangasinan | Bolinao | Luciente 1.0 | 16.3892 | 119.9 | U | 5519 | 1533 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1705 | FTAP Smart | 16.389 | 119.8995 | 0.05 | Terrestrial Optical Fiber Drop | 0.55 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1045 | 2 | 45 | 1045 | 1606801015 | Region XIII (Caraga) | Surigao del Sur | Barobo | Poblacion | 17.105 | 122.2742 | U | 14683 | 3581 | 1074 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130030 | FTAP BTS | 8.5393 | 126.1199 | 0.73 | Terrestrial Optical Fiber Drop | 27.54 | 37.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1046 | 2 | 46 | 1046 | 0201502011 | Region II (Cagayan Valley) | Cagayan | Alcala | Centro Sur | 17.9023 | 121.6586 | R | 3026 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0061 | LDIC | 121.6537 | 17.9074 | 0.77 | Terrestrial Optical Fiber Drop | 0.55 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1047 | 2 | 47 | 1047 | 0405803006 | Region IV-A (CALABARZON) | Rizal | Baras | Concepcion | 14.5215 | 121.2679 | R | 1095 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040068 | FTAP Globe | 14.522 | 121.2696 | 0.2 | Terrestrial Optical Fiber Drop | 0.56 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1048 | 2 | 48 | 1048 | 0103301025 | Region I (Ilocos Region) | La Union | Agoo | San Julian West | 16.3214 | 120.347 | R | 2132 | 576 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.64 | Terrestrial Optical Fiber Drop | 2.3 | 2.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1049 | 2 | 49 | 1049 | 0304927016 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tambo Adorable | 15.3658 | 120.9332 | U | 6398 | 1828 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1327 | FTAP Smart | 15.3572 | 120.9313 | 0.98 | Terrestrial Optical Fiber Drop | 0.55 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1050 | 2 | 50 | 1050 | 0306905019 | Region III (Central Luzon) | Tarlac | Concepcion | Minane | 15.3201 | 120.6508 | R | 3879 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.27 | Terrestrial Optical Fiber Drop | 0.56 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1051 | 2 | 51 | 1051 | 0501717030 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Rafael | 13.7276 | 123.519 | R | 2163 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4025 | FTAP Smart | 13.7298 | 123.5199 | 0.26 | Terrestrial Optical Fiber Drop | 0.56 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1052 | 2 | 52 | 1052 | 1380900007 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Navotas West | 14.6583 | 120.948 | U | 6293 | 1787 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01450 | Edgepoint | 14.6645 | 120.9516 | 0.19 | Terrestrial Optical Fiber Drop | 0.3 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1053 | 2 | 53 | 1053 | 0105519015 | Region I (Ilocos Region) | Pangasinan | Dasol | San Vicente | 15.9897 | 119.8806 | R | 1403 | 389 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.67 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1054 | 2 | 54 | 1054 | 0300810022 | Region III (Central Luzon) | Bataan | Orion | San Vicente | 14.6181 | 120.5768 | R | 1391 | 386 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0002 | PTCI/MIDC | 14.6145 | 120.5801 | 0.45 | Terrestrial Optical Fiber Drop | 0.39 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1055 | 2 | 55 | 1055 | 0105519016 | Region I (Ilocos Region) | Pangasinan | Dasol | Tambac | 15.9898 | 119.8806 | R | 891 | 247 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.66 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1056 | 2 | 56 | 1056 | 0301421043 | Region III (Central Luzon) | Bulacan | San Miguel | San Agustin | 15.1378 | 120.9621 | R | 4519 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030029 | FTAP BTS | 15.1372 | 120.9654 | 0.37 | Terrestrial Optical Fiber Drop | 0.56 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1057 | 2 | 57 | 1057 | 0105519007 | Region I (Ilocos Region) | Pangasinan | Dasol | Macalang | 15.9897 | 119.8806 | R | 1955 | 543 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.67 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1058 | 2 | 58 | 1058 | 0203108059 | Region II (Cagayan Valley) | Isabela | City of Cauayan | San Fermin | 16.9373 | 121.7606 | U | 12480 | 3284 | 985 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C20 | FTAP Smart | 16.9396 | 121.7643 | 0.46 | Terrestrial Optical Fiber Drop | 0.56 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1059 | 2 | 59 | 1059 | 0403406006 | Region IV-A (CALABARZON) | Laguna | Calauan | Lamot 1 | 14.1544 | 121.326 | R | 3215 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02343-C08 | PTCI/MIDC | 14.1396 | 121.3118 | 0.33 | Terrestrial Optical Fiber Drop | 1.61 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1060 | 2 | 60 | 1060 | 0105519011 | Region I (Ilocos Region) | Pangasinan | Dasol | Malimpin | 15.9898 | 119.8806 | R | 1659 | 460 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.66 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1061 | 2 | 61 | 1061 | 0702220005 | Region VII (Central Visayas) | Cebu | Cordova | Cogon | 10.2655 | 123.9511 | R | 2980 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0230 | PTCI/MIDC | 10.2681 | 123.9526 | 0.33 | Terrestrial Optical Fiber Drop | 0.56 | 6.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1062 | 2 | 62 | 1062 | 0402122006 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | San Agustin | 14.2875 | 120.8688 | U | 9798 | 2881 | 864 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4408 | FTAP Smart | 14.2836 | 120.8648 | 0.61 | Terrestrial Optical Fiber Drop | 0.56 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1063 | 2 | 63 | 1063 | 0603007014 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Lagubang | 10.8934 | 122.7042 | R | 2863 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 0.49 | Terrestrial Optical Fiber Drop | 0.56 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1064 | 2 | 64 | 1064 | 0401023020 | Region IV-A (CALABARZON) | Batangas | San Juan | Lipahan | 13.8305 | 121.3972 | R | 4248 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BTG-03175 | Edgepoint | 13.8273 | 121.397 | 0.36 | Terrestrial Optical Fiber Drop | 0.56 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1065 | 2 | 65 | 1065 | 0103303034 | Region I (Ilocos Region) | La Union | Bacnotan | Poblacion | 16.7226 | 120.3533 | U | 3632 | 981 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01390-B05 | PTCI/MIDC | 16.7188 | 120.3533 | 0.42 | Terrestrial Optical Fiber Drop | 0.56 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1066 | 2 | 66 | 1066 | 0604520024 | Region VI (Western Visayas) | Negros Occidental | Murcia | Salvacion | 10.6018 | 123.0439 | U | 6825 | 1844 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 3.51 | Terrestrial Optical Fiber Drop | 0.56 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1067 | 2 | 67 | 1067 | 0103320001 | Region I (Ilocos Region) | La Union | Tubao | Amallapay | 16.3278 | 120.4087 | R | 2032 | 549 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01404-B05 | PTCI/MIDC | 16.3395 | 120.406 | 1.33 | Terrestrial Optical Fiber Drop | 0.56 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1068 | 2 | 68 | 1068 | 1004306020 | Region X (Northern Mindanao) | Misamis Oriental | Claveria | Poblacion | 8.6146 | 124.8975 | U | 10929 | 2802 | 841 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100116 | FTAP Globe | 8.6136 | 124.8946 | 0.33 | Terrestrial Optical Fiber Drop | 0.56 | 13.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1069 | 2 | 69 | 1069 | 1381500026 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | San Miguel | 14.5118 | 121.0709 | U | 11833 | 3113 | 934 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01860 | Edgepoint | 14.5168 | 121.075 | 0.31 | Terrestrial Optical Fiber Drop | 0.68 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1070 | 2 | 70 | 1070 | 0631000096 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Lopez Jaena Sur | 10.7106 | 122.5719 | U | 2256 | 537 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0029 | PTCI/MIDC | 10.7118 | 122.5727 | 0.16 | Terrestrial Optical Fiber Drop | 0.56 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1071 | 2 | 71 | 1071 | 0730600063 | Region VII (Central Visayas) | Cebu | City of Cebu | Quiot Pardo | 10.2881 | 123.8563 | U | 28018 | 8755 | 2627 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070025 | FTAP BTS | 10.2911 | 123.8552 | 0.35 | Terrestrial Optical Fiber Drop | 0.56 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1072 | 2 | 72 | 1072 | 0305409011 | Region III (Central Luzon) | Pampanga | Mabalacat City | Lakandula | 15.1758 | 120.5829 | U | 8899 | 2224 | 667 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02981-B07 | PTCI/MIDC | 15.1789 | 120.582 | 0.36 | Terrestrial Optical Fiber Drop | 0.56 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1073 | 2 | 73 | 1073 | 0501608002 | Region V (Bicol Region) | Camarines Norte | Paracale | Bagumbayan | 14.2834 | 122.7833 | U | 5367 | 1341 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.63 | Terrestrial Optical Fiber Drop | 0.57 | 9.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1074 | 2 | 74 | 1074 | 0301415003 | Region III (Central Luzon) | Bulacan | Pandi | Bunsuran III | 14.8626 | 120.9361 | U | 2562 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01092 | Edgepoint | 14.8681 | 120.9559 | 1.28 | Terrestrial Optical Fiber Drop | 2.32 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1075 | 2 | 75 | 1075 | 0103317015 | Region I (Ilocos Region) | La Union | Santo Tomas | Namboongan | 16.2935 | 120.381 | R | 2472 | 668 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010116 | FTAP Globe | 16.2914 | 120.3899 | 0.99 | Terrestrial Optical Fiber Drop | 0.56 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1076 | 2 | 76 | 1076 | 0201503011 | Region II (Cagayan Valley) | Cagayan | Allacapan | Centro West | 18.222 | 121.5558 | R | 1951 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01186-B06 | PTCI/MIDC | 18.2268 | 121.5579 | 0.58 | Terrestrial Optical Fiber Drop | 0.57 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1077 | 2 | 77 | 1077 | 0301422034 | Region III (Central Luzon) | Bulacan | San Rafael | Ulingao | 14.9732 | 120.9174 | U | 3879 | 1108 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030518 | FTAP Globe | 14.9711 | 120.9162 | 0.27 | Terrestrial Optical Fiber Drop | 0.56 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1078 | 2 | 78 | 1078 | 0403425005 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Landayan | 14.3535 | 121.0679 | U | 36431 | 11039 | 3312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0002 | PTCI/MIDC | 14.3522 | 121.0664 | 0.22 | Terrestrial Optical Fiber Drop | 0.57 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1079 | 2 | 79 | 1079 | 0402120027 | Region IV-A (CALABARZON) | Cavite | Tanza | Lambingan | 14.3747 | 120.8538 | R | 2904 | 854 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040136 | FTAP Globe | 14.3739 | 120.827 | 0.44 | Terrestrial Optical Fiber Drop | 0.69 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1080 | 2 | 80 | 1080 | 0405619047 | Region IV-A (CALABARZON) | Quezon | Gumaca | Tabing Dagat | 13.9155 | 122.1256 | U | 2559 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-03196 | Edgepoint | 13.921 | 122.1079 | 0.76 | Terrestrial Optical Fiber Drop | 2.1 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1081 | 2 | 81 | 1081 | 0402104001 | Region IV-A (CALABARZON) | Cavite | Carmona | Bancal | 14.282 | 121.0072 | U | 17076 | 5022 | 1507 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.88 | Terrestrial Optical Fiber Drop | 0.57 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1082 | 2 | 82 | 1082 | 1004318010 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Poblacion | 8.4043 | 124.2908 | U | 9067 | 2324 | 697 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0066 | PTCI/MIDC | 8.4036 | 124.2859 | 0.54 | Terrestrial Optical Fiber Drop | 0.57 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1083 | 2 | 83 | 1083 | 0731300006 | Region VII (Central Visayas) | Cebu | City of Mandaue | Cambaro | 10.3467 | 123.9405 | U | 8999 | 2571 | 771 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070334 | FTAP Globe | 10.3495 | 123.929 | 0.48 | Terrestrial Optical Fiber Drop | 0.86 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1084 | 2 | 84 | 1084 | 0704604001 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Barangay I | 9.5937 | 123.1194 | U | 3621 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0004 | PTCI/MIDC | 9.5938 | 123.1254 | 0.66 | Terrestrial Optical Fiber Drop | 0.57 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1085 | 2 | 85 | 1085 | 0501705023 | Region V (Bicol Region) | Camarines Sur | Buhi | San Buenaventura | 13.4159 | 123.5143 | U | 2359 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCSG0019 | PTCI/MIDC | 13.3969 | 123.5113 | 1.78 | Terrestrial Optical Fiber Drop | 0.04 | 10.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1086 | 2 | 86 | 1086 | 0203120019 | Region II (Cagayan Valley) | Isabela | Naguilian | San Manuel | 17.0218 | 121.8651 | R | 2683 | 706 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ISA-00197 | Edgepoint | 17.0258 | 121.862 | 0.55 | Terrestrial Optical Fiber Drop | 0.57 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1087 | 2 | 87 | 1087 | 0301414002 | Region III (Central Luzon) | Bulacan | Obando | Catanghalan | 14.7069 | 120.9412 | U | 3385 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030623 | FTAP Globe | 14.7059 | 120.9421 | 0.14 | Terrestrial Optical Fiber Drop | 0.57 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1088 | 2 | 88 | 1088 | 0304911049 | Region III (Central Luzon) | Nueva Ecija | Guimba | Saint John District | 15.66 | 120.7716 | R | 1937 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01413-B07 | PTCI/MIDC | 15.6577 | 120.7705 | 0.28 | Terrestrial Optical Fiber Drop | 0.57 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1089 | 2 | 89 | 1089 | 0500503004 | Region V (Bicol Region) | Albay | Daraga | Bagumbayan | 13.144 | 123.7159 | U | 4020 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0036 | PTCI/MIDC | 13.1437 | 123.7182 | 0.25 | Terrestrial Optical Fiber Drop | 0.57 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1090 | 2 | 90 | 1090 | 0105532051 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Mamarlao | 15.9159 | 120.3286 | R | 3147 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00525 | Edgepoint | 15.9336 | 120.3479 | 0.17 | Terrestrial Optical Fiber Drop | 2.5 | 2.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1091 | 2 | 91 | 1091 | 0102812044 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 27, Nstra. Sra. De Soledad | 18.1923 | 120.6108 | R | 1685 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.35 | Terrestrial Optical Fiber Drop | 3.05 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1092 | 2 | 92 | 1092 | 0405812014 | Region IV-A (CALABARZON) | Rizal | Tanay | San Isidro | 14.4956 | 121.2793 | R | 3187 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02631-A04 | PTCI/MIDC | 14.4979 | 121.2773 | 0.33 | Terrestrial Optical Fiber Drop | 0.57 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1093 | 2 | 93 | 1093 | 0600412010 | Region VI (Western Visayas) | Aklan | Malay | Manoc-Manoc | 11.95 | 121.9409 | U | 21135 | 5419 | 1626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060214 | FTAP Globe | 11.9463 | 121.9425 | 0.45 | Terrestrial Optical Fiber Drop | 0.57 | 2.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1094 | 2 | 94 | 1094 | 1705214023 | MIMAROPA Region | Oriental Mindoro | Socorro | Zone IV | 13.0585 | 121.4038 | U | 2287 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170095 | FTAP Globe | 13.0601 | 121.4094 | 0.62 | Terrestrial Optical Fiber Drop | 0.57 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1095 | 2 | 95 | 1095 | 0506214013 | Region V (Bicol Region) | Sorsogon | Prieto Diaz | Rizal | 13.048 | 124.1917 | R | 1095 | 273 | 82 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050197 | FTAP Globe | 13.0399 | 124.192 | 0.9 | Terrestrial Optical Fiber Drop | 0.57 | 15.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1096 | 2 | 96 | 1096 | 0403411004 | Region IV-A (CALABARZON) | Laguna | Los Baños | Batong Malake | 14.1741 | 121.2435 | U | 13788 | 4178 | 1253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.26 | Terrestrial Optical Fiber Drop | 0.58 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1097 | 2 | 97 | 1097 | 0402117010 | Region IV-A (CALABARZON) | Cavite | Rosario | Tejeros Convention | 14.403 | 120.86 | U | 21580 | 6347 | 1904 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040117 | FTAP Globe | 14.409 | 120.8561 | 0.79 | Terrestrial Optical Fiber Drop | 0.57 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1098 | 2 | 98 | 1098 | 0501608004 | Region V (Bicol Region) | Camarines Norte | Paracale | Batobalani | 14.2351 | 122.7453 | U | 5003 | 1250 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050009 | FTAP Globe | 14.2156 | 122.7526 | 2.31 | Terrestrial Optical Fiber Drop | 0.57 | 5.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1099 | 2 | 99 | 1099 | 0405610012 | Region IV-A (CALABARZON) | Quezon | Catanauan | Bolo | 13.6291 | 122.2578 | R | 1367 | 359 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040613 | FTAP Globe | 13.6328 | 122.2423 | 1.72 | Terrestrial Optical Fiber Drop | 0.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1100 | 2 | 100 | 1100 | 1380900003 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Bagumbayan South | 14.6512 | 120.9486 | U | 4489 | 1328 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0024 | PTCI/MIDC | 14.6496 | 120.9492 | 0.19 | Terrestrial Optical Fiber Drop | 0.58 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1101 | 2 | 101 | 1101 | 0301419007 | Region III (Central Luzon) | Bulacan | San Ildefonso | Basuit | 15.0409 | 120.99 | R | 2299 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030486 | FTAP Globe | 15.054 | 121.0004 | 1.84 | Terrestrial Optical Fiber Drop | 0.57 | 5.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1102 | 2 | 102 | 1102 | 0201517013 | Region II (Cagayan Valley) | Cagayan | Lasam | Ignacio Jurado | 18.0655 | 121.6097 | R | 1757 | 450 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03292-B06 | PTCI/MIDC | 18.0629 | 121.6086 | 0.31 | Terrestrial Optical Fiber Drop | 0.58 | 3.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1103 | 2 | 103 | 1103 | 1380500006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Barangka Itaas | 14.5836 | 121.0336 | U | 11354 | 3639 | 1092 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02647 | Edgepoint | 14.5884 | 121.0398 | 0.37 | Terrestrial Optical Fiber Drop | 0.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1104 | 2 | 104 | 1104 | 1102404021 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Poblacion | 6.6839 | 125.3012 | R | 4650 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110527 | FTAP Globe | 6.6897 | 125.2969 | 0.8 | Terrestrial Optical Fiber Drop | 0.58 | 4.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1105 | 2 | 105 | 1105 | 1630400007 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Ampayon | 8.9631 | 125.605 | U | 14288 | 3484 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130073 | FTAP Globe | 8.9578 | 125.5836 | 2.42 | Terrestrial Optical Fiber Drop | 0.58 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1106 | 2 | 106 | 1106 | 0702210027 | Region VII (Central Visayas) | Cebu | Barili | Mantalongon | 10.1252 | 123.5762 | R | 3081 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070364 | FTAP Globe | 10.1317 | 123.5785 | 0.76 | Terrestrial Optical Fiber Drop | 0.58 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1107 | 2 | 107 | 1107 | 0501603027 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay IV | 14.117 | 122.949 | U | 7810 | 1952 | 586 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S92 | FTAP Smart | 14.1147 | 122.9549 | 0.69 | Terrestrial Optical Fiber Drop | 0.58 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1108 | 2 | 108 | 1108 | 0401034010 | Region IV-A (CALABARZON) | Batangas | Tuy | Malibu | 13.9962 | 120.7067 | R | 1458 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.53 | Terrestrial Optical Fiber Drop | 3.66 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1109 | 2 | 109 | 1109 | 0603043036 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Gen. Martin T. Delgado | 10.8321 | 122.5324 | R | 1933 | 508 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0073 | PTCI/MIDC | 10.8367 | 122.5265 | 0.82 | Terrestrial Optical Fiber Drop | 0.58 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1110 | 2 | 110 | 1110 | 0702211001 | Region VII (Central Visayas) | Cebu | City of Bogo | Cogon | 11.0435 | 124.0037 | U | 2857 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070035 | FTAP BTS | 11.041 | 124.0001 | 0.48 | Terrestrial Optical Fiber Drop | 0.58 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1111 | 2 | 111 | 1111 | 1004308048 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 23 | 8.8225 | 125.1006 | R | 3323 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.36 | Terrestrial Optical Fiber Drop | 0.58 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1112 | 2 | 112 | 1112 | 0604528042 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 3 | 10.7437 | 122.9634 | U | 6901 | 1865 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060161 | FTAP BTS | 10.7427 | 122.9638 | 0.12 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1113 | 2 | 113 | 1113 | 1381100132 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 132 | 14.548 | 121.0063 | U | 3967 | 1309 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03189 | Edgepoint | 14.5499 | 121.0084 | 0.31 | Terrestrial Optical Fiber Drop | 0.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1114 | 2 | 114 | 1114 | 0304911062 | Region III (Central Luzon) | Nueva Ecija | Guimba | Saranay District | 15.6592 | 120.772 | U | 2824 | 806 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01413-B07 | PTCI/MIDC | 15.6577 | 120.7705 | 0.23 | Terrestrial Optical Fiber Drop | 0.58 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1115 | 2 | 115 | 1115 | 0500517041 | Region V (Bicol Region) | Albay | City of Tabaco | San Roque | 13.3555 | 123.7359 | U | 5362 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ALB_0001 | LDIC | 13.3557 | 123.7364 | 0.05 | Terrestrial Optical Fiber Drop | 0.58 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1116 | 2 | 116 | 1116 | 0500517019 | Region V (Bicol Region) | Albay | City of Tabaco | Fatima | 13.3492 | 123.7353 | R | 4365 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050132 | FTAP Globe | 13.3504 | 123.734 | 0.19 | Terrestrial Optical Fiber Drop | 0.58 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1117 | 2 | 117 | 1117 | 0306910001 | Region III (Central Luzon) | Tarlac | Paniqui | Abogado | 15.6708 | 120.5917 | R | 4810 | 1233 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 1.14 | Terrestrial Optical Fiber Drop | 0.58 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1118 | 2 | 118 | 1118 | 0401003008 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 3 | 13.9378 | 120.7325 | R | 1519 | 421 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 0.42 | Terrestrial Optical Fiber Drop | 0.79 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1119 | 2 | 119 | 1119 | 0702227008 | Region VII (Central Visayas) | Cebu | Liloan | Poblacion | 10.4023 | 123.9978 | U | 17033 | 4482 | 1345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0227 | PTCI/MIDC | 10.4015 | 123.9905 | 0.81 | Terrestrial Optical Fiber Drop | 0.59 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1120 | 2 | 120 | 1120 | 0301419026 | Region III (Central Luzon) | Bulacan | San Ildefonso | Poblacion | 15.0792 | 120.944 | U | 5123 | 1463 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1619 | FTAP Smart | 15.0772 | 120.9428 | 0.26 | Terrestrial Optical Fiber Drop | 0.59 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1121 | 2 | 121 | 1121 | 0803715020 | Region VIII (Eastern Visayas) | Leyte | Carigara | Jugaban | 11.2991 | 124.6947 | R | 1893 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 0.29 | Terrestrial Optical Fiber Drop | 0.58 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1122 | 2 | 122 | 1122 | 1705319008 | MIMAROPA Region | Palawan | San Vicente | Poblacion | 10.5365 | 119.2823 | U | 7496 | 1922 | 577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02441-C09 | PTCI/MIDC | 10.5366 | 119.2409 | 4.52 | Terrestrial Optical Fiber Drop | 0.59 | 8.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1123 | 2 | 123 | 1123 | 0401005082 | Region IV-A (CALABARZON) | Batangas | Batangas City | Sampaga | 13.7549 | 121.1037 | R | 4590 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03402-C08 | PTCI/MIDC | 13.7631 | 121.1069 | 0.97 | Terrestrial Optical Fiber Drop | 0.59 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1124 | 2 | 124 | 1124 | 0907322054 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Santa Maria | 7.8361 | 123.4388 | U | 4770 | 1223 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 1.04 | Terrestrial Optical Fiber Drop | 0.59 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1125 | 2 | 125 | 1125 | 0402114024 | Region IV-A (CALABARZON) | Cavite | Mendez | Palocpoc II | 14.128 | 120.879 | R | 1290 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040302 | FTAP Globe | 14.1248 | 120.8631 | 1.11 | Terrestrial Optical Fiber Drop | 0.23 | 4.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1126 | 2 | 126 | 1126 | 0300809013 | Region III (Central Luzon) | Bataan | Orani | Pantalan Bago | 14.803 | 120.5417 | R | 2370 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030603 | FTAP Globe | 14.8016 | 120.536 | 0.64 | Terrestrial Optical Fiber Drop | 0.59 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1127 | 2 | 127 | 1127 | 0306903017 | Region III (Central Luzon) | Tarlac | Camiling | Cacamilingan Norte | 15.6876 | 120.4204 | R | 2597 | 665 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030330 | FTAP Globe | 15.6892 | 120.4213 | 0.21 | Terrestrial Optical Fiber Drop | 0.59 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1128 | 2 | 128 | 1128 | 0105517004 | Region I (Ilocos Region) | Pangasinan | Calasiao | Bued | 16.0175 | 120.3831 | U | 5943 | 1650 | 495 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02246-B07 | PTCI/MIDC | 16.0148 | 120.3817 | 0.33 | Terrestrial Optical Fiber Drop | 0.59 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1129 | 2 | 129 | 1129 | 0403420008 | Region IV-A (CALABARZON) | Laguna | Pakil | Kabulusan | 14.3682 | 121.3996 | R | 4746 | 1438 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02564-A04 | PTCI/MIDC | 14.3471 | 121.3751 | 3.53 | Terrestrial Optical Fiber Drop | 0.59 | 7.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1130 | 2 | 130 | 1130 | 0603018013 | Region VI (Western Visayas) | Iloilo | Dumangas | Cali | 10.8311 | 122.7112 | R | 2035 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 1.46 | Terrestrial Optical Fiber Drop | 0.59 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1131 | 2 | 131 | 1131 | 1001319008 | Region X (Northern Mindanao) | Bukidnon | Sumilao | San Vicente | 8.3679 | 124.9779 | U | 3693 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0063 | PTCI/MIDC | 8.3585 | 124.979 | 1.06 | Terrestrial Optical Fiber Drop | 0.59 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1132 | 2 | 132 | 1132 | 0403403004 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Canlalay | 14.3425 | 121.072 | U | 22311 | 6760 | 2028 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S2016 | FTAP Smart | 14.3406 | 121.0722 | 0.22 | Terrestrial Optical Fiber Drop | 0.59 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1133 | 2 | 133 | 1133 | 0501709003 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Francisco | 13.6164 | 123.1704 | R | 872 | 207 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.52 | Terrestrial Optical Fiber Drop | 0.43 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1134 | 2 | 134 | 1134 | 0500510003 | Region V (Bicol Region) | Albay | Malinao | Balading | 13.3882 | 123.7091 | U | 3127 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050126 | FTAP Globe | 13.3795 | 123.7173 | 1.31 | Terrestrial Optical Fiber Drop | 0.59 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1135 | 2 | 135 | 1135 | 0506214010 | Region V (Bicol Region) | Sorsogon | Prieto Diaz | Maningcay De Oro | 13.0402 | 124.1895 | R | 1295 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050197 | FTAP Globe | 13.0399 | 124.192 | 0.27 | Terrestrial Optical Fiber Drop | 0.59 | 14.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1136 | 2 | 136 | 1136 | 0201505038 | Region II (Cagayan Valley) | Cagayan | Aparri | San Antonio | 18.3592 | 121.6407 | U | 4084 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0026 | LDIC | 121.6392 | 18.3577 | 0.23 | Terrestrial Optical Fiber Drop | 0.59 | 10.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1137 | 2 | 137 | 1137 | 1004313008 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Poblacion | 8.8105 | 124.7899 | R | 4238 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.47 | Terrestrial Optical Fiber Drop | 0.6 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1138 | 2 | 138 | 1138 | 0600613005 | Region VI (Western Visayas) | Antique | San Jose | Barangay 3 | 10.7519 | 121.9416 | R | 3574 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170137 | FTAP Globe | 12.3508 | 121.0661 | 0.53 | Terrestrial Optical Fiber Drop | 1.22 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1139 | 2 | 139 | 1139 | 0402106080 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | H-2 | 14.318 | 120.9522 | U | 9797 | 2881 | 864 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01898-C08 | PTCI/MIDC | 14.3775 | 120.9413 | 0.19 | Terrestrial Optical Fiber Drop | 1.58 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1140 | 2 | 140 | 1140 | 1430300002 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Asin Road | 16.4042 | 120.5669 | U | 13901 | 3658 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0006 | LDIC | 16.4046 | 120.5669 | 0.05 | Terrestrial Optical Fiber Drop | 0.6 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1141 | 2 | 141 | 1141 | 0603032023 | Region VI (Western Visayas) | Iloilo | New Lucena | Wari-wari | 10.8837 | 122.6 | R | 1050 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 0.97 | Terrestrial Optical Fiber Drop | 0.6 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1142 | 2 | 142 | 1142 | 0307109003 | Region III (Central Luzon) | Zambales | San Antonio | Burgos | 14.9463 | 120.0943 | U | 6185 | 1627 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.69 | Terrestrial Optical Fiber Drop | 0.59 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1143 | 2 | 143 | 1143 | 0803738081 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Antonio | 10.9643 | 124.6447 | R | 1977 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0042 | PTCI/MIDC | 10.9609 | 124.652 | 0.88 | Terrestrial Optical Fiber Drop | 0.59 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1144 | 2 | 144 | 1144 | 0506208029 | Region V (Bicol Region) | Sorsogon | Gubat | Paradijon | 12.9168 | 124.1202 | R | 1381 | 345 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 0.53 | Terrestrial Optical Fiber Drop | 0.59 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1145 | 2 | 145 | 1145 | 0102809013 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Guerrero | 18.0948 | 120.7057 | R | 1519 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 1.03 | Terrestrial Optical Fiber Drop | 0.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1146 | 2 | 146 | 1146 | 0402106017 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone II | 14.3182 | 120.9526 | R | 1765 | 519 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.95 | Terrestrial Optical Fiber Drop | 1.55 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1147 | 2 | 147 | 1147 | 0506208028 | Region V (Bicol Region) | Sorsogon | Gubat | Panganiban | 12.9139 | 124.1196 | R | 2167 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03159-C10 | PTCI/MIDC | 12.912 | 124.1171 | 0.35 | Terrestrial Optical Fiber Drop | 0.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1148 | 2 | 148 | 1148 | 1004302020 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Barangay 1 | 8.7449 | 124.7801 | R | 1373 | 352 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0002 | PTCI/MIDC | 8.7436 | 124.7779 | 0.28 | Terrestrial Optical Fiber Drop | 0.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1149 | 2 | 149 | 1149 | 0702224024 | Region VII (Central Visayas) | Cebu | Dumanjug | Liong | 10.052 | 123.4328 | R | 2755 | 725 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0084 | PTCI/MIDC | 10.0456 | 123.429 | 0.83 | Terrestrial Optical Fiber Drop | 0.6 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1150 | 2 | 150 | 1150 | 0307105010 | Region III (Central Luzon) | Zambales | Iba | Lipay-Dingin-Panibuatan | 15.3217 | 119.977 | R | 3572 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.66 | Terrestrial Optical Fiber Drop | 0.6 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1151 | 2 | 151 | 1151 | 0500508026 | Region V (Bicol Region) | Albay | City of Ligao | Herrera | 13.2628 | 123.5839 | R | 2721 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.83 | Terrestrial Optical Fiber Drop | 0.6 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1152 | 2 | 152 | 1152 | 0501728013 | Region V (Bicol Region) | Camarines Sur | Pili | Palestina | 13.6075 | 123.2492 | U | 6010 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCSG0006 | PTCI/MIDC | 13.6014 | 123.2473 | 0.71 | Terrestrial Optical Fiber Drop | 0.6 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1153 | 2 | 153 | 1153 | 0702221016 | Region VII (Central Visayas) | Cebu | Daanbantayan | Poblacion | 11.2505 | 124.0005 | U | 8592 | 2261 | 678 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0072 | PTCI/MIDC | 11.2494 | 124.0028 | 0.28 | Terrestrial Optical Fiber Drop | 0.6 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1154 | 2 | 154 | 1154 | 0506209021 | Region V (Bicol Region) | Sorsogon | Irosin | San Agustin | 12.7027 | 124.0411 | R | 2380 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 0.5 | Terrestrial Optical Fiber Drop | 0.6 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1155 | 2 | 155 | 1155 | 0504121034 | Region V (Bicol Region) | Masbate | Uson | Sawang | 12.2322 | 123.7556 | R | 1556 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMSG0001 | PTCI/MIDC | 12.243 | 123.7468 | 1.54 | Terrestrial Optical Fiber Drop | 0.6 | 20.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1156 | 2 | 156 | 1156 | 0405802016 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Luis | 14.6201 | 121.1903 | U | 63518 | 17643 | 5293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00829-A04 | PTCI/MIDC | 14.6207 | 121.1902 | 0.06 | Terrestrial Optical Fiber Drop | 0.6 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1157 | 2 | 157 | 1157 | 0305405009 | Region III (Central Luzon) | Pampanga | Candaba | Dalayap | 15.0153 | 120.8659 | R | 2631 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030502 | FTAP Globe | 15.0168 | 120.8697 | 0.44 | Terrestrial Optical Fiber Drop | 0.6 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1158 | 2 | 158 | 1158 | 0102818007 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Cabaroan | 18.1682 | 120.7194 | R | 975 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 3987 | FTAP Smart | 18.1615 | 120.7123 | 1.06 | Terrestrial Optical Fiber Drop | 0.6 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1159 | 2 | 159 | 1159 | 0405805018 | Region IV-A (CALABARZON) | Rizal | Cainta | Santa Rosa | 14.5798 | 121.1136 | R | 1550 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01758 | Edgepoint | 14.5824 | 121.1199 | 0.2 | Terrestrial Optical Fiber Drop | 1.15 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1160 | 2 | 160 | 1160 | 0304926030 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 1st | 15.7991 | 120.991 | U | 7950 | 2271 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01436-B07 | PTCI/MIDC | 15.8005 | 120.9908 | 0.16 | Terrestrial Optical Fiber Drop | 0.6 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1161 | 2 | 161 | 1161 | 0403413005 | Region IV-A (CALABARZON) | Laguna | Lumban | Concepcion | 14.299 | 121.4566 | R | 4711 | 1427 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.44 | Terrestrial Optical Fiber Drop | 0.6 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1162 | 2 | 162 | 1162 | 1108204026 | Region XI (Davao Region) | Davao de Oro | Maco | Poblacion | 7.3612 | 125.859 | U | 8701 | 2351 | 705 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 0.67 | Terrestrial Optical Fiber Drop | 0.61 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1163 | 2 | 163 | 1163 | 0403425013 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Riverside | 14.3416 | 121.0436 | R | 3319 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040146 | FTAP Globe | 14.3562 | 121.0336 | 0.25 | Terrestrial Optical Fiber Drop | 0.48 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1164 | 2 | 164 | 1164 | 1430300069 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Quirino Hill, Middle | 16.4302 | 120.5906 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1852 | FTAP Smart | 16.4305 | 120.5909 | 0.05 | Terrestrial Optical Fiber Drop | 0.61 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1165 | 2 | 165 | 1165 | 0504112001 | Region V (Bicol Region) | Masbate | Milagros | Bacolod | 12.2245 | 123.5084 | R | 3357 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03140-C10 | PTCI/MIDC | 12.2309 | 123.5058 | 0.77 | Terrestrial Optical Fiber Drop | 0.61 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1166 | 2 | 166 | 1166 | 0402114012 | Region IV-A (CALABARZON) | Cavite | Mendez | Poblacion VI | 14.1348 | 120.9044 | R | 1337 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02216-C08 | PTCI/MIDC | 14.1324 | 120.9008 | 0.48 | Terrestrial Optical Fiber Drop | 0.61 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1167 | 2 | 167 | 1167 | 0103313022 | Region I (Ilocos Region) | La Union | Rosario | Poblacion East | 16.2293 | 120.4882 | U | 2497 | 674 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01398-B05 | PTCI/MIDC | 16.2273 | 120.4884 | 0.23 | Terrestrial Optical Fiber Drop | 0.61 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1168 | 2 | 168 | 1168 | 0305405017 | Region III (Central Luzon) | Pampanga | Candaba | Mangga | 15.016 | 120.8768 | U | 4283 | 1070 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030502 | FTAP Globe | 15.0168 | 120.8697 | 0.77 | Terrestrial Optical Fiber Drop | 0.61 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1169 | 2 | 169 | 1169 | 1401106001 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Ampucao | 16.3253 | 120.6547 | U | 11221 | 3206 | 962 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BEN-00357 | Edgepoint | 16.3305 | 120.6474 | 0.98 | Terrestrial Optical Fiber Drop | 0.61 | 10.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1170 | 2 | 170 | 1170 | 0401012026 | Region IV-A (CALABARZON) | Batangas | Lemery | Mayasang | 14.0162 | 120.8632 | R | 2831 | 786 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1361 | FTAP Smart | 14.0201 | 120.8589 | 0.63 | Terrestrial Optical Fiber Drop | 0.61 | 4.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1171 | 2 | 171 | 1171 | 0402120033 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya VII | 14.3831 | 120.8338 | R | 2698 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.64 | Terrestrial Optical Fiber Drop | 1.87 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1172 | 2 | 172 | 1172 | 0630200023 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 27 | 10.666 | 122.9521 | R | 1800 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0022 | PTCI/MIDC | 10.6747 | 122.9555 | 0.44 | Terrestrial Optical Fiber Drop | 0.1 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1173 | 2 | 173 | 1173 | 0403405005 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bubuyan | 14.1719 | 121.104 | R | 3500 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02067-C08 | PTCI/MIDC | 14.1719 | 121.1028 | 0.13 | Terrestrial Optical Fiber Drop | 0.61 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1174 | 2 | 174 | 1174 | 1381300094 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Salvacion | 14.6588 | 121.0467 | U | 6861 | 1844 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170066 | FTAP Globe | 13.3624 | 121.1001 | 0.56 | Terrestrial Optical Fiber Drop | 0.48 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1175 | 2 | 175 | 1175 | 1705320005 | MIMAROPA Region | Palawan | Taytay | Bato | 10.7121 | 119.4853 | R | 4263 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170219 | FTAP Globe | 10.6697 | 119.4514 | 6 | Terrestrial Optical Fiber Drop | 0.61 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1176 | 2 | 176 | 1176 | 1381200018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Sagad | 14.5661 | 121.0796 | U | 6357 | 1826 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000381 | FTAP Globe | 14.5672 | 121.0801 | 0.13 | Terrestrial Optical Fiber Drop | 0.62 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1177 | 2 | 177 | 1177 | 0500504043 | Region V (Bicol Region) | Albay | Guinobatan | San Francisco | 13.1892 | 123.6095 | U | 3199 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 1.11 | Terrestrial Optical Fiber Drop | 0.62 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1178 | 2 | 178 | 1178 | 0403425010 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Nueva | 14.3417 | 121.044 | U | 4698 | 1423 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0001 | PTCI/MIDC | 14.3376 | 121.0391 | 0.17 | Terrestrial Optical Fiber Drop | 0.51 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1179 | 2 | 179 | 1179 | 0631000052 | Region VI (Western Visayas) | Iloilo | City of Iloilo | East Baluarte | 10.6925 | 122.5481 | R | 1863 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0041 | PTCI/MIDC | 10.6914 | 122.5427 | 0.6 | Terrestrial Optical Fiber Drop | 0.62 | 2.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1180 | 2 | 180 | 1180 | 0403424027 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay VI-D | 14.0776 | 121.321 | R | 1678 | 508 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.37 | Terrestrial Optical Fiber Drop | 0.62 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1181 | 2 | 181 | 1181 | 0102803012 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Gabut Sur | 17.9653 | 120.4745 | R | 908 | 245 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01223-B05 | PTCI/MIDC | 17.9199 | 120.4864 | 0.59 | Terrestrial Optical Fiber Drop | 4.48 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1182 | 2 | 182 | 1182 | 0907302042 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Aurora | Poblacion | 7.9471 | 123.5854 | U | 5108 | 1344 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0001 | PTCI/MIDC | 7.9502 | 123.5859 | 0.35 | Terrestrial Optical Fiber Drop | 0.62 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1183 | 2 | 183 | 1183 | 0604532004 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Igmaya-an | 10.5582 | 123.1957 | R | 4474 | 1209 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0124 | PTCI/MIDC | 10.4742 | 123.1992 | 9.35 | Terrestrial Optical Fiber Drop | 0.62 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1184 | 2 | 184 | 1184 | 0403418004 | Region IV-A (CALABARZON) | Laguna | Paete | Ibaba del Norte | 14.3639 | 121.4792 | R | 3407 | 1032 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.51 | Terrestrial Optical Fiber Drop | 0.62 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1185 | 2 | 185 | 1185 | 0105530032 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Talogtog | 16.1225 | 120.5223 | R | 2264 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00407 | Edgepoint | 16.11 | 120.5398 | 0.21 | Terrestrial Optical Fiber Drop | 2.31 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1186 | 2 | 186 | 1186 | 0603039006 | Region VI (Western Visayas) | Iloilo | San Enrique | Cabugao Viejo | 11.0754 | 122.6605 | R | 1392 | 366 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.35 | Terrestrial Optical Fiber Drop | 0.62 | 3.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1187 | 2 | 187 | 1187 | 0604530015 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Poblacion | 10.4605 | 122.8245 | U | 3790 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 0.96 | Terrestrial Optical Fiber Drop | 0.63 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1188 | 2 | 188 | 1188 | 1001312001 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Aglayan | 8.0547 | 125.1353 | U | 9192 | 2418 | 725 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100192 | FTAP Globe | 8.0534 | 125.1347 | 0.15 | Terrestrial Optical Fiber Drop | 0.63 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1189 | 2 | 189 | 1189 | 0701205013 | Region VII (Central Visayas) | Bohol | Baclayon | San Roque | 9.6251 | 123.9216 | R | 1760 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 4.81 | Terrestrial Optical Fiber Drop | 0.96 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1190 | 2 | 190 | 1190 | 0401028003 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Barangay III | 14.1054 | 121.1425 | R | 2240 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 0.46 | Terrestrial Optical Fiber Drop | 2.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1191 | 2 | 191 | 1191 | 1381500014 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Tuktukan | 14.5117 | 121.0587 | U | 12414 | 3301 | 990 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03000 | Edgepoint | 121.07 | 14.5109 | 0.23 | Terrestrial Optical Fiber Drop | 0.8 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1192 | 2 | 192 | 1192 | 1600203024 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Poblacion 12 | 9.1176 | 125.54 | R | 2577 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 0.73 | Terrestrial Optical Fiber Drop | 0.62 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1193 | 2 | 193 | 1193 | 0405802017 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Santa Cruz | 14.6153 | 121.1708 | U | 62537 | 17371 | 5211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0175 | PTCI/MIDC | 14.6161 | 121.1691 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1194 | 2 | 194 | 1194 | 0403420007 | Region IV-A (CALABARZON) | Laguna | Pakil | Gonzales | 14.3847 | 121.4769 | R | 2865 | 868 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040132 | FTAP Globe | 14.3864 | 121.4768 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1195 | 2 | 195 | 1195 | 0403417053 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Yukos | 14.1321 | 121.413 | U | 5953 | 1803 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02088-C08 | PTCI/MIDC | 14.1299 | 121.4147 | 0.3 | Terrestrial Optical Fiber Drop | 0.63 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1196 | 2 | 196 | 1196 | 0405805016 | Region IV-A (CALABARZON) | Rizal | Cainta | San Juan | 14.5398 | 121.1109 | U | 99685 | 27690 | 8307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03263-A04 | PTCI/MIDC | 14.5411 | 121.112 | 0.18 | Terrestrial Optical Fiber Drop | 0.63 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1197 | 2 | 197 | 1197 | 0431200007 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 4 | 13.9366 | 121.6161 | U | 2925 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.45 | Terrestrial Optical Fiber Drop | 0.63 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1198 | 2 | 198 | 1198 | 0403403023 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Domingo | 14.336 | 121.0809 | U | 6751 | 2045 | 614 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02537-C08 | PTCI/MIDC | 14.3337 | 121.0825 | 0.31 | Terrestrial Optical Fiber Drop | 0.63 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1199 | 2 | 199 | 1199 | 0105501014 | Region I (Ilocos Region) | Pangasinan | Agno | Poblacion East | 16.1183 | 119.7967 | R | 1543 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-02227 | Edgepoint | 16.1209 | 119.8108 | 1.67 | Terrestrial Optical Fiber Drop | 1.12 | 9.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1200 | 2 | 200 | 1200 | 0401005014 | Region IV-A (CALABARZON) | Batangas | Batangas City | Calicanto | 13.7669 | 121.0534 | U | 11089 | 3080 | 924 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6911 | FTAP Smart | 13.7698 | 121.0545 | 0.35 | Terrestrial Optical Fiber Drop | 0.63 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1201 | 2 | 201 | 1201 | 0203115012 | Region II (Cagayan Valley) | Isabela | Jones | Dibuluan | 16.5195 | 121.7611 | R | 2556 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01292-B06 | PTCI/MIDC | 16.5232 | 121.7634 | 0.48 | Terrestrial Optical Fiber Drop | 0.63 | 15.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1202 | 2 | 202 | 1202 | 0403430009 | Region IV-A (CALABARZON) | Laguna | Victoria | San Francisco | 14.2119 | 121.3444 | U | 7217 | 2186 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02113-C08 | PTCI/MIDC | 14.2028 | 121.346 | 1.02 | Terrestrial Optical Fiber Drop | 0.63 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1203 | 2 | 203 | 1203 | 0305412018 | Region III (Central Luzon) | Pampanga | Masantol | San Isidro Matua | 14.8913 | 120.7009 | R | 3735 | 933 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.34 | Terrestrial Optical Fiber Drop | 0.63 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1204 | 2 | 204 | 1204 | 1230800009 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Katangawan | 6.1733 | 125.221 | U | 17971 | 4607 | 1382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0022 | PTCI/MIDC | 6.1749 | 125.2217 | 0.19 | Terrestrial Optical Fiber Drop | 0.63 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1205 | 2 | 205 | 1205 | 0405804040 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pag-Asa | 14.527 | 121.1605 | U | 18644 | 5178 | 1553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 450 | FTAP Smart | 14.5268 | 121.1582 | 0.25 | Terrestrial Optical Fiber Drop | 0.63 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1206 | 2 | 206 | 1206 | 0803748041 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Canramos | 11.1062 | 125.0142 | R | 3407 | 896 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0083 | PTCI/MIDC | 11.1054 | 125.0132 | 0.14 | Terrestrial Optical Fiber Drop | 0.63 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1207 | 2 | 207 | 1207 | 0405808005 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Manggahan | 14.7235 | 121.143 | U | 17089 | 4746 | 1424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-RIZ-01264 | Edgepoint | 14.7303 | 121.1441 | 0.77 | Terrestrial Optical Fiber Drop | 0.63 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1208 | 2 | 208 | 1208 | 0301407009 | Region III (Central Luzon) | Bulacan | Calumpit | Corazon | 14.912 | 120.7683 | U | 2273 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1599 | FTAP Smart | 14.9149 | 120.7688 | 0.32 | Terrestrial Optical Fiber Drop | 0.63 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1209 | 2 | 209 | 1209 | 1705205048 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Salong | 13.4203 | 121.1902 | U | 3831 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 1.24 | Terrestrial Optical Fiber Drop | 0.63 | 5.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1210 | 2 | 210 | 1210 | 0506205001 | Region V (Bicol Region) | Sorsogon | Casiguran | Adovis | 12.8687 | 124.0097 | R | 808 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 0.72 | Terrestrial Optical Fiber Drop | 0.63 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1211 | 2 | 211 | 1211 | 0201525012 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Villa | 18.2476 | 121.917 | R | 2279 | 584 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0073 | LDIC | 121.911 | 18.2439 | 0.76 | Terrestrial Optical Fiber Drop | 0.63 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1212 | 2 | 212 | 1212 | 0403419010 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Maulawin | 14.2697 | 121.4546 | R | 4627 | 1402 | 421 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02115-C08 | PTCI/MIDC | 14.2703 | 121.4567 | 0.24 | Terrestrial Optical Fiber Drop | 0.63 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1213 | 2 | 213 | 1213 | 0603005006 | Region VI (Western Visayas) | Iloilo | Balasan | Camambugan | 11.4731 | 123.0842 | R | 2318 | 610 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.75 | Terrestrial Optical Fiber Drop | 0.63 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1214 | 2 | 214 | 1214 | 0501708039 | Region V (Bicol Region) | Camarines Sur | Calabanga | San Roque | 13.7122 | 123.2108 | U | 6318 | 1504 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050061 | FTAP Globe | 13.7087 | 123.2167 | 0.75 | Terrestrial Optical Fiber Drop | 0.64 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1215 | 2 | 215 | 1215 | 0603014022 | Region VI (Western Visayas) | Iloilo | Carles | Granada | 11.6167 | 123.3433 | R | 3367 | 886 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060345 | FTAP Globe | 10.6647 | 123.0376 | 0.48 | Terrestrial Optical Fiber Drop | 29.48 | 30.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1216 | 2 | 216 | 1216 | 0403425026 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 1 | 14.3494 | 121.0476 | U | 24752 | 7500 | 2250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02019-C08 | PTCI/MIDC | 14.3488 | 121.0601 | 0.5 | Terrestrial Optical Fiber Drop | 0.97 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1217 | 2 | 217 | 1217 | 1403213008 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao | 17.4077 | 121.4451 | U | 20300 | 4720 | 1416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00001-B06 | PTCI/MIDC | 17.4073 | 121.4431 | 0.22 | Terrestrial Optical Fiber Drop | 0.64 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1218 | 2 | 218 | 1218 | 0401006041 | Region IV-A (CALABARZON) | Batangas | Bauan | Santa Maria | 13.7738 | 120.964 | U | 4923 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1336 | FTAP Smart | 13.7759 | 120.9646 | 0.71 | Terrestrial Optical Fiber Drop | 0.91 | 4.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1219 | 2 | 219 | 1219 | 0405648016 | Region IV-A (CALABARZON) | Quezon | Tiaong | Lumingon | 13.9607 | 121.3257 | U | 4592 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040409 | FTAP Globe | 13.9631 | 121.3238 | 0.34 | Terrestrial Optical Fiber Drop | 0.64 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1220 | 2 | 220 | 1220 | 1402701005 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Bocos | 16.9162 | 121.0632 | R | 2621 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.85 | Terrestrial Optical Fiber Drop | 0.64 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1221 | 2 | 221 | 1221 | 0500517004 | Region V (Bicol Region) | Albay | City of Tabaco | Bantayan | 13.3376 | 123.6573 | R | 1637 | 399 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050138 | FTAP Globe | 13.3099 | 123.6425 | 3.47 | Terrestrial Optical Fiber Drop | 0.64 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1222 | 2 | 222 | 1222 | 0403402003 | Region IV-A (CALABARZON) | Laguna | Bay | Dila | 14.1809 | 121.2864 | U | 7412 | 2246 | 674 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.6 | Terrestrial Optical Fiber Drop | 0.64 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1223 | 2 | 223 | 1223 | 0403428016 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pook | 14.3024 | 121.1096 | U | 61062 | 18503 | 5551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0006 | LDIC | 14.3036 | 121.1072 | 0.29 | Terrestrial Optical Fiber Drop | 0.64 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1224 | 2 | 224 | 1224 | 0402103058 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu VII | 14.4561 | 120.9551 | U | 3876 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 386 | FTAP Smart | 14.4378 | 121.0069 | 0.52 | Terrestrial Optical Fiber Drop | 0.4 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1225 | 2 | 225 | 1225 | 0401017013 | Region IV-A (CALABARZON) | Batangas | Malvar | San Fernando | 14.0261 | 121.1635 | U | 5844 | 1623 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.94 | Terrestrial Optical Fiber Drop | 0.64 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1226 | 2 | 226 | 1226 | 0307105008 | Region III (Central Luzon) | Zambales | Iba | Dirita-Baloguen | 15.3326 | 119.9794 | U | 3946 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.65 | Terrestrial Optical Fiber Drop | 0.64 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1227 | 2 | 227 | 1227 | 0402104010 | Region IV-A (CALABARZON) | Cavite | Carmona | Maduya | 14.3169 | 121.0608 | U | 11154 | 3280 | 984 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.38 | Terrestrial Optical Fiber Drop | 0.64 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1228 | 2 | 228 | 1228 | 0300805013 | Region III (Central Luzon) | Bataan | Hermosa | Mambog - Mandama | 14.8335 | 120.4938 | R | 3864 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1510 | FTAP Smart | 14.8334 | 120.4947 | 0.1 | Terrestrial Optical Fiber Drop | 0.64 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1229 | 2 | 229 | 1229 | 0304929026 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Pulong Buli | 15.5942 | 120.8731 | R | 2414 | 689 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01429-B07 | PTCI/MIDC | 15.5935 | 120.8781 | 0.55 | Terrestrial Optical Fiber Drop | 0.64 | 4.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1230 | 2 | 230 | 1230 | 0301423006 | Region III (Central Luzon) | Bulacan | Santa Maria | Catmon | 14.8287 | 121.0014 | U | 16660 | 4760 | 1428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01161 | Edgepoint | 14.8276 | 120.9962 | 0.57 | Terrestrial Optical Fiber Drop | 0.64 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1231 | 2 | 231 | 1231 | 0102820007 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Eugenio | 18.1531 | 120.5955 | R | 1037 | 280 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ILN_0001 | LDIC | 18.161 | 120.5894 | 0.48 | Terrestrial Optical Fiber Drop | 1.93 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1232 | 2 | 232 | 1232 | 0331400002 | Region III (Central Luzon) | Zambales | City of Olongapo | Banicain | 14.8286 | 120.2757 | U | 7696 | 2080 | 624 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.53 | Terrestrial Optical Fiber Drop | 0.65 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1233 | 2 | 233 | 1233 | 0402103056 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu V | 14.4562 | 120.9548 | U | 5937 | 1746 | 524 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040129 | FTAP Globe | 14.3884 | 120.9771 | 0.32 | Terrestrial Optical Fiber Drop | 0.43 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1234 | 2 | 234 | 1234 | 0405646030 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Rizal | 13.9602 | 122.5435 | R | 3375 | 888 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.73 | Terrestrial Optical Fiber Drop | 0.65 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1235 | 2 | 235 | 1235 | 0403421006 | Region IV-A (CALABARZON) | Laguna | Pangil | Natividad | 14.3995 | 121.4712 | R | 2814 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.64 | Terrestrial Optical Fiber Drop | 1.15 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1236 | 2 | 236 | 1236 | 0501716010 | Region V (Bicol Region) | Camarines Sur | City of Iriga | Perpetual Help | 13.4264 | 123.4148 | R | 4380 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-03180 | Edgepoint | 13.428 | 123.4178 | 0.37 | Terrestrial Optical Fiber Drop | 0.65 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1237 | 2 | 237 | 1237 | 1204702032 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Poblacion | 7.2056 | 124.7977 | U | 10414 | 2740 | 822 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0015 | PTCI/MIDC | 8.9888 | 125.2896 | 0.51 | Terrestrial Optical Fiber Drop | 0.34 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1238 | 2 | 238 | 1238 | 0803748046 | Region VIII (Eastern Visayas) | Leyte | Tanauan | San Roque | 11.111 | 125.0213 | R | 3634 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080011 | FTAP BTS | 11.1165 | 125.0165 | 0.81 | Terrestrial Optical Fiber Drop | 0.65 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1239 | 2 | 239 | 1239 | 1401113013 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Taloy Sur | 16.3837 | 120.5304 | R | 3618 | 1033 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00916-B05 | PTCI/MIDC | 16.3864 | 120.5261 | 0.55 | Terrestrial Optical Fiber Drop | 0.65 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1240 | 2 | 240 | 1240 | 0702250014 | Region VII (Central Visayas) | Cebu | City of Talisay | San Isidro | 10.2564 | 123.839 | U | 18044 | 4748 | 1424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 0.41 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1241 | 2 | 241 | 1241 | 0601902019 | Region VI (Western Visayas) | Capiz | Dao | Poblacion Ilaya | 11.3906 | 122.6817 | R | 1995 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 3.18 | Terrestrial Optical Fiber Drop | 0.65 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1242 | 2 | 242 | 1242 | 0103306033 | Region I (Ilocos Region) | La Union | Bangar | San Blas | 16.888 | 120.4221 | R | 1395 | 377 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.32 | Terrestrial Optical Fiber Drop | 0.65 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1243 | 2 | 243 | 1243 | 0304902008 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Curva | 15.6187 | 121.1489 | R | 4163 | 1189 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 1.01 | Terrestrial Optical Fiber Drop | 0.65 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1244 | 2 | 244 | 1244 | 0307108005 | Region III (Central Luzon) | Zambales | Palauig | Garreta | 15.4366 | 119.9019 | R | 1532 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00729 | Edgepoint | 15.4369 | 119.9033 | 0.15 | Terrestrial Optical Fiber Drop | 0.65 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1245 | 2 | 245 | 1245 | 0402108029 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Tejero | 14.3922 | 120.8643 | U | 8578 | 2522 | 757 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040128 | FTAP Globe | 14.3935 | 120.8639 | 0.15 | Terrestrial Optical Fiber Drop | 0.65 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1246 | 2 | 246 | 1246 | 0205005008 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | La Torre North | 16.4877 | 121.1502 | R | 2504 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0017 | PTCI/MIDC | 16.4767 | 121.1461 | 0.84 | Terrestrial Optical Fiber Drop | 0.34 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1247 | 2 | 247 | 1247 | 0105539023 | Region I (Ilocos Region) | Pangasinan | Santa Maria | San Vicente | 15.9873 | 120.7081 | R | 4140 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01765-B07 | PTCI/MIDC | 15.9765 | 120.6972 | 1.67 | Terrestrial Optical Fiber Drop | 0.65 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1248 | 2 | 248 | 1248 | 0506203038 | Region V (Bicol Region) | Sorsogon | Bulan | Obrero | 12.6693 | 123.8788 | R | 2985 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.27 | Terrestrial Optical Fiber Drop | 0.65 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1249 | 2 | 249 | 1249 | 0603017049 | Region VI (Western Visayas) | Iloilo | Dueñas | Poblacion B | 11.0701 | 122.6164 | R | 797 | 209 | 63 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0018 | PTCI/MIDC | 11.065 | 122.622 | 0.82 | Terrestrial Optical Fiber Drop | 0.65 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1250 | 2 | 250 | 1250 | 0402105002 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 10 | 14.4706 | 120.8892 | R | 1380 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040084 | FTAP Globe | 14.4812 | 120.8948 | 0.5 | Terrestrial Optical Fiber Drop | 0.5 | 3.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1251 | 2 | 251 | 1251 | 0402122012 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Gregorio | 14.2877 | 120.8715 | U | 5438 | 1599 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4408 | FTAP Smart | 14.2836 | 120.8648 | 0.85 | Terrestrial Optical Fiber Drop | 0.65 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1252 | 2 | 252 | 1252 | 0402107011 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Tabora | 14.1886 | 120.7921 | R | 2133 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.8 | Terrestrial Optical Fiber Drop | 0.65 | 3.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1253 | 2 | 253 | 1253 | 0603018010 | Region VI (Western Visayas) | Iloilo | Dumangas | Bolilao | 10.8297 | 122.7143 | R | 3144 | 827 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.38 | Terrestrial Optical Fiber Drop | 0.65 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1254 | 2 | 254 | 1254 | 0501702008 | Region V (Bicol Region) | Camarines Sur | Balatan | Duran | 13.3101 | 123.2368 | U | 5460 | 1300 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050137 | FTAP Globe | 13.3165 | 123.2349 | 0.74 | Terrestrial Optical Fiber Drop | 0.66 | 14.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1255 | 2 | 255 | 1255 | 0304930046 | Region III (Central Luzon) | Nueva Ecija | Talavera | Poblacion Sur | 15.5763 | 120.9178 | U | 3979 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0023 | PTCI/MIDC | 15.5775 | 120.9214 | 0.41 | Terrestrial Optical Fiber Drop | 0.66 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1256 | 2 | 256 | 1256 | 0731300018 | Region VII (Central Visayas) | Cebu | City of Mandaue | Mantuyong | 10.3469 | 123.9409 | U | 5493 | 1569 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0113 | PTCI/MIDC | 10.3319 | 123.936 | 0.75 | Terrestrial Optical Fiber Drop | 0.9 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1257 | 2 | 257 | 1257 | 0306903018 | Region III (Central Luzon) | Tarlac | Camiling | Cacamilingan Sur | 15.6876 | 120.4202 | R | 2373 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.23 | Terrestrial Optical Fiber Drop | 0.57 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1258 | 2 | 258 | 1258 | 0500514033 | Region V (Bicol Region) | Albay | Polangui | Maynaga | 13.3391 | 123.52 | R | 1389 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050131 | FTAP Globe | 13.3511 | 123.5258 | 1.48 | Terrestrial Optical Fiber Drop | 0.66 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1259 | 2 | 259 | 1259 | 1705307012 | MIMAROPA Region | Palawan | Busuanga | Salvacion | 12.1328 | 119.9311 | U | 4052 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170200 | FTAP Globe | 12.129 | 119.9382 | 0.88 | Satellite LEO Backhaul (Starlink Business) | 0.65 | 125.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1260 | 2 | 260 | 1260 | 0205705003 | Region II (Cagayan Valley) | Quirino | Saguday | Magsaysay | 16.5383 | 121.5609 | R | 2636 | 675 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0005 | LDIC | 121.5628 | 16.5421 | 0.47 | Terrestrial Optical Fiber Drop | 0.66 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1261 | 2 | 261 | 1261 | 0201507009 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Centro West | 18.4141 | 121.509 | R | 2104 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01193-B06 | PTCI/MIDC | 18.4117 | 121.5126 | 0.46 | Terrestrial Optical Fiber Drop | 0.66 | 7.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1262 | 2 | 262 | 1262 | 0405805014 | Region IV-A (CALABARZON) | Rizal | Cainta | San Andres | 14.5741 | 121.1106 | U | 115400 | 32055 | 9617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02575-A04 | PTCI/MIDC | 14.5718 | 121.1128 | 0.36 | Terrestrial Optical Fiber Drop | 0.66 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1263 | 2 | 263 | 1263 | 1731500067 | MIMAROPA Region | Palawan | City of Puerto Princesa | Tiniguiban | 9.7753 | 118.7379 | U | 13976 | 3777 | 1133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02443-C09 | PTCI/MIDC | 9.7787 | 118.7391 | 0.4 | Terrestrial Optical Fiber Drop | 0.66 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1264 | 2 | 264 | 1264 | 0403412014 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Jose | 14.185 | 121.5152 | R | 1024 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 0.97 | Terrestrial Optical Fiber Drop | 0.99 | 4.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1265 | 2 | 265 | 1265 | 1705309024 | MIMAROPA Region | Palawan | Coron | Tagumpay | 12.0086 | 120.2443 | U | 9745 | 2498 | 749 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170202 | FTAP Globe | 12.0797 | 120.196 | 9.49 | Satellite LEO Backhaul (Starlink Business) | 0.66 | 96.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1266 | 2 | 266 | 1266 | 0402106063 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc IV | 14.3132 | 120.9718 | U | 43875 | 12904 | 3871 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040179 | FTAP Globe | 14.3126 | 120.9715 | 0.08 | Terrestrial Optical Fiber Drop | 0.66 | 2.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1267 | 2 | 267 | 1267 | 1102315025 | Region XI (Davao Region) | Davao del Norte | City of Panabo | New Pandan | 7.2956 | 125.6835 | U | 8693 | 2349 | 705 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110294 | FTAP BTS | 7.2974 | 125.6811 | 0.33 | Terrestrial Optical Fiber Drop | 0.66 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1268 | 2 | 268 | 1268 | 0405634005 | Region IV-A (CALABARZON) | Quezon | Pitogo | Bilucao | 13.8164 | 122.0989 | R | 816 | 214 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040556 | FTAP Globe | 13.8171 | 122.0981 | 0.96 | Terrestrial Optical Fiber Drop | 0.32 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1269 | 2 | 269 | 1269 | 0431200002 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 1 | 13.9391 | 121.6107 | U | 2597 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040447 | FTAP Globe | 13.9371 | 121.6094 | 0.25 | Terrestrial Optical Fiber Drop | 0.66 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1270 | 2 | 270 | 1270 | 1130700142 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 9-A | 7.0725 | 125.6085 | U | 7083 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110485 | FTAP Globe | 7.0759 | 125.6041 | 0.62 | Terrestrial Optical Fiber Drop | 0.66 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1271 | 2 | 271 | 1271 | 0304908015 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Norte | 15.2853 | 120.9476 | U | 6716 | 1918 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030425 | FTAP Globe | 15.2822 | 120.9466 | 0.36 | Terrestrial Optical Fiber Drop | 0.03 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1272 | 2 | 272 | 1272 | 0730600041 | Region VII (Central Visayas) | Cebu | City of Cebu | Lahug | 10.3247 | 123.8984 | U | 45908 | 14346 | 4304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0048 | PTCI/MIDC | 10.3284 | 123.8973 | 0.43 | Terrestrial Optical Fiber Drop | 0.67 | 1.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1273 | 2 | 273 | 1273 | 0102809016 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Madamba | 18.1042 | 120.699 | R | 1991 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 0.23 | Terrestrial Optical Fiber Drop | 0.67 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1274 | 2 | 274 | 1274 | 0330100013 | Region III (Central Luzon) | Pampanga | City of Angeles | Malabañas | 15.1493 | 120.5927 | U | 31164 | 8656 | 2597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3794 | FTAP Smart | 15.1578 | 120.5914 | 0.34 | Terrestrial Optical Fiber Drop | 0.26 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1275 | 2 | 275 | 1275 | 0301410021 | Region III (Central Luzon) | Bulacan | City of Malolos | Catmon | 14.8504 | 120.8136 | U | 2350 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1589 | FTAP Smart | 14.8511 | 120.8139 | 0.09 | Terrestrial Optical Fiber Drop | 0.67 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1276 | 2 | 276 | 1276 | 0506212018 | Region V (Bicol Region) | Sorsogon | Matnog | Gadgaron | 12.5922 | 124.0804 | R | 2576 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050233 | FTAP Globe | 12.59 | 124.0937 | 1.47 | Terrestrial Optical Fiber Drop | 0.67 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1277 | 2 | 277 | 1277 | 1206511013 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Poblacion | 6.6942 | 124.6775 | U | 14133 | 3719 | 1116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120280 | FTAP Globe | 6.6939 | 124.6788 | 0.15 | Terrestrial Optical Fiber Drop | 0.67 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1278 | 2 | 278 | 1278 | 0403424077 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santo Cristo | 14.0646 | 121.3325 | R | 3552 | 1076 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02002-C08 | PTCI/MIDC | 14.0573 | 121.336 | 0.9 | Terrestrial Optical Fiber Drop | 0.67 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1279 | 2 | 279 | 1279 | 0402114025 | Region IV-A (CALABARZON) | Cavite | Mendez | Panungyan II | 14.1358 | 120.8951 | R | 1786 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040293 | FTAP Globe | 14.137 | 120.8946 | 0.14 | Terrestrial Optical Fiber Drop | 0.67 | 4.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1280 | 2 | 280 | 1280 | 0403409001 | Region IV-A (CALABARZON) | Laguna | Kalayaan | Longos | 14.337 | 121.4817 | U | 7487 | 2268 | 680 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040168 | FTAP Globe | 14.3245 | 121.4782 | 1.44 | Terrestrial Optical Fiber Drop | 0.67 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1281 | 2 | 281 | 1281 | 0907322053 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Lumbia | 7.8296 | 123.4452 | U | 4427 | 1135 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 0.33 | Terrestrial Optical Fiber Drop | 0.67 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1282 | 2 | 282 | 1282 | 0203137014 | Region II (Cagayan Valley) | Isabela | Tumauini | Carpentero | 17.2713 | 121.8092 | R | 1107 | 291 | 87 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 1.23 | Terrestrial Optical Fiber Drop | 0.67 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1283 | 2 | 283 | 1283 | 0402103018 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu I | 14.4563 | 120.9552 | U | 4531 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01903-C08 | PTCI/MIDC | 14.4247 | 120.9487 | 0.34 | Terrestrial Optical Fiber Drop | 0.38 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1284 | 2 | 284 | 1284 | 0103309004 | Region I (Ilocos Region) | La Union | Caba | Las-ud | 16.4332 | 120.3419 | R | 1354 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.18 | Terrestrial Optical Fiber Drop | 0.67 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1285 | 2 | 285 | 1285 | 0103306018 | Region I (Ilocos Region) | La Union | Bangar | Maria Cristina East | 16.8918 | 120.431 | R | 948 | 256 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.83 | Terrestrial Optical Fiber Drop | 0.67 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1286 | 2 | 286 | 1286 | 0301405002 | Region III (Central Luzon) | Bulacan | Bulacan | Balubad | 14.8016 | 120.8753 | U | 3907 | 1116 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01116-B07 | PTCI/MIDC | 14.8008 | 120.8762 | 0.13 | Terrestrial Optical Fiber Drop | 0.67 | 2.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1287 | 2 | 287 | 1287 | 0403421007 | Region IV-A (CALABARZON) | Laguna | Pangil | San Jose | 14.3997 | 121.4709 | R | 1440 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.68 | Terrestrial Optical Fiber Drop | 1.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1288 | 2 | 288 | 1288 | 0105544040 | Region I (Ilocos Region) | Pangasinan | Umingan | Nancalabasaan | 15.936 | 120.8432 | R | 2736 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 1.35 | Terrestrial Optical Fiber Drop | 0.68 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1289 | 2 | 289 | 1289 | 0701232010 | Region VII (Central Visayas) | Bohol | Maribojoc | Dipatlong | 9.7464 | 123.8408 | R | 1717 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070413 | FTAP Globe | 9.7455 | 123.842 | 0.16 | Terrestrial Optical Fiber Drop | 0.67 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1290 | 2 | 290 | 1290 | 0307109010 | Region III (Central Luzon) | Zambales | San Antonio | San Juan | 14.945 | 120.0872 | R | 1714 | 451 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.1 | Terrestrial Optical Fiber Drop | 0.68 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1291 | 2 | 291 | 1291 | 0500506017 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 18 - Cabagñan West | 13.1418 | 123.749 | U | 4014 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050181 | FTAP Globe | 13.136 | 123.7293 | 0.55 | Terrestrial Optical Fiber Drop | 1.12 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1292 | 2 | 292 | 1292 | 0405813005 | Region IV-A (CALABARZON) | Rizal | Taytay | Santa Ana | 14.5372 | 121.1093 | U | 102828 | 28563 | 8569 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-02461 | Edgepoint | 14.5378 | 121.1085 | 0.11 | Terrestrial Optical Fiber Drop | 0.68 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1293 | 2 | 293 | 1293 | 0301408006 | Region III (Central Luzon) | Bulacan | Guiguinto | Poblacion | 14.8286 | 120.8791 | U | 3625 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01115-B07 | PTCI/MIDC | 14.8289 | 120.8826 | 0.38 | Terrestrial Optical Fiber Drop | 0.67 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1294 | 2 | 294 | 1294 | 0402103072 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote II | 14.4654 | 120.9642 | U | 5408 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0040 | PTCI/MIDC | 14.467 | 120.9631 | 0.22 | Terrestrial Optical Fiber Drop | 0.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1295 | 2 | 295 | 1295 | 0702219013 | Region VII (Central Visayas) | Cebu | Consolacion | Poblacion Occidental | 10.3727 | 123.954 | U | 6123 | 1611 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0263 | PTCI/MIDC | 10.3701 | 123.9507 | 0.45 | Terrestrial Optical Fiber Drop | 0.68 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1296 | 2 | 296 | 1296 | 0603018023 | Region VI (Western Visayas) | Iloilo | Dumangas | Ilaya 3rd | 10.8269 | 122.7122 | R | 766 | 201 | 60 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.55 | Terrestrial Optical Fiber Drop | 0.29 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1297 | 2 | 297 | 1297 | 0301415018 | Region III (Central Luzon) | Bulacan | Pandi | San Roque | 14.8579 | 120.956 | R | 3025 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01119 | Edgepoint | 14.8516 | 120.9571 | 0.7 | Terrestrial Optical Fiber Drop | 0.68 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1298 | 2 | 298 | 1298 | 0301422026 | Region III (Central Luzon) | Bulacan | San Rafael | Salapungan | 15.0213 | 120.9639 | U | 2553 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02979-B07 | PTCI/MIDC | 15.0224 | 120.963 | 0.15 | Terrestrial Optical Fiber Drop | 0.68 | 3.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1299 | 2 | 299 | 1299 | 0500518014 | Region V (Bicol Region) | Albay | Tiwi | Libtong | 13.453 | 123.6708 | R | 2278 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 1.23 | Terrestrial Optical Fiber Drop | 0.68 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1300 | 2 | 300 | 1300 | 0301420039 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan IV | 14.8474 | 121.0745 | U | 4985 | 1424 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01061-B07 | PTCI/MIDC | 14.8466 | 121.0708 | 0.4 | Terrestrial Optical Fiber Drop | 0.68 | 3.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1301 | 2 | 301 | 1301 | 0201516013 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Centro | 18.2016 | 121.6627 | R | 1463 | 375 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.75 | Terrestrial Optical Fiber Drop | 0.68 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1302 | 2 | 302 | 1302 | 0102820009 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Gregorio | 18.1746 | 120.5888 | R | 2017 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C61 | FTAP Smart | 18.1726 | 120.5935 | 0.55 | Terrestrial Optical Fiber Drop | 0.68 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1303 | 2 | 303 | 1303 | 0402117018 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa IV | 14.4159 | 120.8508 | R | 1019 | 299 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040116 | FTAP Globe | 14.41 | 120.8725 | 1.05 | Terrestrial Optical Fiber Drop | 2.31 | 2.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1304 | 2 | 304 | 1304 | 0402120022 | Region IV-A (CALABARZON) | Cavite | Tanza | Sanja Mayor | 14.3747 | 120.8541 | U | 15472 | 4550 | 1365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 1.37 | Terrestrial Optical Fiber Drop | 0.68 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1305 | 2 | 305 | 1305 | 0405607067 | Region IV-A (CALABARZON) | Quezon | Calauag | Sabang II | 13.9568 | 122.2808 | R | 3981 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0005 | PTCI/MIDC | 13.957 | 122.2821 | 0.14 | Terrestrial Optical Fiber Drop | 0.68 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1306 | 2 | 306 | 1306 | 0702235014 | Region VII (Central Visayas) | Cebu | Oslob | Lagunde | 9.5257 | 123.4359 | R | 3347 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 0.28 | Terrestrial Optical Fiber Drop | 0.68 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1307 | 2 | 307 | 1307 | 0301403017 | Region III (Central Luzon) | Bulacan | Baliuag | San Jose | 14.9484 | 120.8943 | U | 7044 | 2012 | 604 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00966-B07 | PTCI/MIDC | 14.9475 | 120.8906 | 0.41 | Terrestrial Optical Fiber Drop | 0.68 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1308 | 2 | 308 | 1308 | 1705203033 | MIMAROPA Region | Oriental Mindoro | Bongabong | Aplaya | 12.7501 | 121.487 | R | 2735 | 701 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170114 | FTAP Globe | 12.7482 | 121.4852 | 0.29 | Terrestrial Optical Fiber Drop | 0.68 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1309 | 2 | 309 | 1309 | 0300809014 | Region III (Central Luzon) | Bataan | Orani | Pantalan Luma | 14.8014 | 120.5426 | U | 5862 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030603 | FTAP Globe | 14.8016 | 120.536 | 0.71 | Terrestrial Optical Fiber Drop | 0.68 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1310 | 2 | 310 | 1310 | 0402109056 | Region IV-A (CALABARZON) | Cavite | City of Imus | Maharlika | 14.3966 | 120.9593 | U | 6091 | 1791 | 537 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q10 | FTAP Smart | 14.3992 | 120.9596 | 0.28 | Terrestrial Optical Fiber Drop | 0.68 | 5.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1311 | 2 | 311 | 1311 | 0305416037 | Region III (Central Luzon) | Pampanga | City of San Fernando | Telabastagan | 15.1176 | 120.6049 | U | 16571 | 4142 | 1243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030468 | FTAP Globe | 15.1169 | 120.6026 | 0.26 | Terrestrial Optical Fiber Drop | 0.68 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1312 | 2 | 312 | 1312 | 0731100015 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Mactan | 10.3103 | 124.0095 | U | 50985 | 14567 | 4370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070191 | FTAP BTS | 10.3103 | 123.9999 | 1.05 | Terrestrial Optical Fiber Drop | 0.68 | 6.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1313 | 2 | 313 | 1313 | 0304926021 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Canuto Ramos Pob. | 15.7887 | 120.9897 | R | 2255 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01418-B07 | PTCI/MIDC | 15.7875 | 120.9873 | 0.29 | Terrestrial Optical Fiber Drop | 0.68 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1314 | 2 | 314 | 1314 | 0402118011 | Region IV-A (CALABARZON) | Cavite | Silang | Bulihan | 14.2802 | 120.9962 | U | 26302 | 7735 | 2321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.39 | Terrestrial Optical Fiber Drop | 0.68 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1315 | 2 | 315 | 1315 | 0600613002 | Region VI (Western Visayas) | Antique | San Jose | Badiang | 10.7652 | 121.9435 | R | 3647 | 935 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0021 | PTCI/MIDC | 10.7615 | 121.9442 | 0.42 | Terrestrial Optical Fiber Drop | 0.68 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1316 | 2 | 316 | 1316 | 1408103010 | Cordillera Administrative Region (CAR) | Apayao | Flora | Poblacion East | 18.2142 | 121.4245 | R | 2699 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-APA-00028 | Edgepoint | 18.2111 | 121.4232 | 0.37 | Terrestrial Optical Fiber Drop | 0.68 | 4.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1317 | 2 | 317 | 1317 | 0402106056 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan III | 14.3144 | 120.9821 | U | 76791 | 22585 | 6776 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040172 | FTAP Globe | 14.3194 | 120.9838 | 0.59 | Terrestrial Optical Fiber Drop | 0.69 | 3.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1318 | 2 | 318 | 1318 | 0403422010 | Region IV-A (CALABARZON) | Laguna | Pila | Mojon | 14.2202 | 121.383 | R | 1464 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.18 | Terrestrial Optical Fiber Drop | 2.63 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1319 | 2 | 319 | 1319 | 0500508044 | Region V (Bicol Region) | Albay | City of Ligao | Santa Cruz | 13.2334 | 123.5341 | U | 2351 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 1.23 | Terrestrial Optical Fiber Drop | 0.69 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1320 | 2 | 320 | 1320 | 0604502006 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Balingasag | 10.5333 | 122.85 | R | 5052 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0089 | PTCI/MIDC | 10.5344 | 122.8445 | 0.62 | Terrestrial Optical Fiber Drop | 0.68 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1321 | 2 | 321 | 1321 | 0701242004 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Cogon | 9.6529 | 123.8543 | U | 16078 | 4019 | 1206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0056 | PTCI/MIDC | 9.6527 | 123.8555 | 0.13 | Terrestrial Optical Fiber Drop | 0.53 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1322 | 2 | 322 | 1322 | 0402103055 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu IV | 14.4559 | 120.9549 | U | 12310 | 3620 | 1086 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00434-A03 | PTCI/MIDC | 14.4712 | 120.9864 | 0.33 | Terrestrial Optical Fiber Drop | 0.42 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1323 | 2 | 323 | 1323 | 0105508007 | Region I (Ilocos Region) | Pangasinan | Bani | Centro Toma | 16.2528 | 119.8022 | R | 2249 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-00371 | Edgepoint | 16.29 | 119.8146 | 4.35 | Terrestrial Optical Fiber Drop | 0.69 | 6.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1324 | 2 | 324 | 1324 | 0203124022 | Region II (Cagayan Valley) | Isabela | Ramon | Bugallon Proper | 16.7812 | 121.5331 | U | 7599 | 1999 | 600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01358-B06 | PTCI/MIDC | 16.7799 | 121.5383 | 0.57 | Terrestrial Optical Fiber Drop | 0.69 | 9.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1325 | 2 | 325 | 1325 | 0604527002 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 2 | 9.7489 | 122.4091 | R | 4282 | 1157 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060396 | FTAP Globe | 9.7491 | 122.4063 | 0.31 | Terrestrial Optical Fiber Drop | 0.68 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1326 | 2 | 326 | 1326 | 0403414009 | Region IV-A (CALABARZON) | Laguna | Mabitac | Libis ng Nayon | 14.4267 | 121.4321 | R | 1212 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040105 | FTAP Globe | 14.4284 | 121.4288 | 0.4 | Terrestrial Optical Fiber Drop | 0.68 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1327 | 2 | 327 | 1327 | 1004314006 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Mauswagon | 8.5876 | 124.4431 | R | 3634 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 0.39 | Terrestrial Optical Fiber Drop | 1.51 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1328 | 2 | 328 | 1328 | 0102821017 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Nicolas | 18.1602 | 120.6496 | R | 1774 | 479 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01210-B05 | PTCI/MIDC | 18.156 | 120.6512 | 0.49 | Terrestrial Optical Fiber Drop | 0.69 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1329 | 2 | 329 | 1329 | 0304903013 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Barrera District | 15.4807 | 120.9674 | U | 5766 | 1647 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0004 | PTCI/MIDC | 15.481 | 120.9671 | 0.06 | Terrestrial Optical Fiber Drop | 0.68 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1330 | 2 | 330 | 1330 | 0402110036 | Region IV-A (CALABARZON) | Cavite | Indang | Kaytapos | 14.1965 | 120.8857 | R | 1640 | 482 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0062 | PTCI/MIDC | 14.2012 | 120.8889 | 0.63 | Terrestrial Optical Fiber Drop | 0.68 | 8.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1331 | 2 | 331 | 1331 | 0401016022 | Region IV-A (CALABARZON) | Batangas | Mabini | Pulong Niogan | 13.7539 | 120.9424 | R | 2496 | 693 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1355 | FTAP Smart | 13.7545 | 120.943 | 0.09 | Terrestrial Optical Fiber Drop | 0.69 | 7.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1332 | 2 | 332 | 1332 | 1102408016 | Region XI (Davao Region) | Davao del Sur | Malalag | Poblacion | 6.589 | 125.3988 | U | 6711 | 1973 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110153 | FTAP BTS | 6.5862 | 125.4044 | 0.7 | Terrestrial Optical Fiber Drop | 0.69 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1333 | 2 | 333 | 1333 | 0301412021 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saluysoy | 14.7435 | 120.9556 | U | 11523 | 3292 | 988 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02488 | Edgepoint | 14.7447 | 120.9604 | 0.53 | Terrestrial Optical Fiber Drop | 0.69 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1334 | 2 | 334 | 1334 | 0401031037 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 6 | 14.0868 | 121.1439 | U | 3654 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040334 | FTAP Globe | 14.0866 | 121.1381 | 0.63 | Terrestrial Optical Fiber Drop | 0.69 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1335 | 2 | 335 | 1335 | 0431200035 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Market View | 13.9338 | 121.6179 | U | 12596 | 3149 | 945 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.33 | Terrestrial Optical Fiber Drop | 0.69 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1336 | 2 | 336 | 1336 | 0405646029 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Poblacion | 13.9671 | 122.5362 | U | 3983 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.54 | Terrestrial Optical Fiber Drop | 0.69 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1337 | 2 | 337 | 1337 | 1004315001 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Dulong | 8.5644 | 124.3591 | R | 1650 | 423 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 0.91 | Terrestrial Optical Fiber Drop | 0.69 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1338 | 2 | 338 | 1338 | 0105526006 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bari | 16.0616 | 120.4026 | U | 6120 | 1700 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00424 | Edgepoint | 16.0601 | 120.4026 | 0.17 | Terrestrial Optical Fiber Drop | 0.69 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1339 | 2 | 339 | 1339 | 0401028008 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Felix | 14.0792 | 121.1891 | U | 6153 | 1709 | 513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040505 | FTAP Globe | 13.9071 | 121.0424 | 0.55 | Terrestrial Optical Fiber Drop | 2 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1340 | 2 | 340 | 1340 | 1705215018 | MIMAROPA Region | Oriental Mindoro | Victoria | Poblacion I | 13.1731 | 121.2827 | U | 2691 | 690 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170084 | FTAP Globe | 13.1757 | 121.2767 | 0.72 | Terrestrial Optical Fiber Drop | 0.69 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1341 | 2 | 341 | 1341 | 0403425006 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Langgam | 14.3275 | 121.0197 | U | 33922 | 10279 | 3084 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.83 | Terrestrial Optical Fiber Drop | 2.9 | 2.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1342 | 2 | 342 | 1342 | 0730600060 | Region VII (Central Visayas) | Cebu | City of Cebu | Pung-ol-Sibugay | 10.3311 | 123.8907 | R | 2336 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070338 | FTAP Globe | 10.329 | 123.8925 | 0.3 | Terrestrial Optical Fiber Drop | 0.69 | 2.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1343 | 2 | 343 | 1343 | 0301407008 | Region III (Central Luzon) | Bulacan | Calumpit | Caniogan | 14.9044 | 120.7739 | U | 4714 | 1346 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01097-B07 | PTCI/MIDC | 14.9017 | 120.7697 | 0.55 | Terrestrial Optical Fiber Drop | 0.69 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1344 | 2 | 344 | 1344 | 0304903038 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Imelda District | 15.4755 | 120.9612 | U | 3966 | 1133 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00715 | Edgepoint | 15.4745 | 120.967 | 0.64 | Terrestrial Optical Fiber Drop | 0.69 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1345 | 2 | 345 | 1345 | 0702234011 | Region VII (Central Visayas) | Cebu | City of Naga | Inayagan | 10.2361 | 123.7733 | U | 10585 | 2785 | 836 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0236 | PTCI/MIDC | 10.2326 | 123.7762 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1346 | 2 | 346 | 1346 | 0105512002 | Region I (Ilocos Region) | Pangasinan | Binalonan | Bued | 16.0404 | 120.5904 | U | 2858 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 1.1 | Terrestrial Optical Fiber Drop | 0.69 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1347 | 2 | 347 | 1347 | 1004308073 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 18 | 8.8292 | 125.1099 | R | 1432 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0087 | PTCI/MIDC | 8.8252 | 125.1109 | 0.46 | Terrestrial Optical Fiber Drop | 0.69 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1348 | 2 | 348 | 1348 | 0401010023 | Region IV-A (CALABARZON) | Batangas | Ibaan | Sandalan | 13.8292 | 121.1358 | R | 1328 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 0.33 | Terrestrial Optical Fiber Drop | 1.68 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1349 | 2 | 349 | 1349 | 0402103025 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote I | 14.4653 | 120.9643 | U | 6154 | 1810 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040100 | FTAP Globe | 14.4418 | 120.9433 | 0.43 | Terrestrial Optical Fiber Drop | 0.66 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1350 | 2 | 350 | 1350 | 0405806008 | Region IV-A (CALABARZON) | Rizal | Cardona | Dalig | 14.4804 | 121.2343 | U | 6801 | 1889 | 567 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01886 | Edgepoint | 14.4807 | 121.2314 | 0.32 | Terrestrial Optical Fiber Drop | 0.69 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1351 | 2 | 351 | 1351 | 0307102010 | Region III (Central Luzon) | Zambales | Cabangan | Dolores | 15.1688 | 120.0456 | R | 1374 | 361 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00822 | Edgepoint | 15.1674 | 120.0507 | 0.76 | Terrestrial Optical Fiber Drop | 1.2 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1352 | 2 | 352 | 1352 | 0603019017 | Region VI (Western Visayas) | Iloilo | Estancia | Poblacion Zone 1 | 11.456 | 123.1494 | R | 2821 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060014 | FTAP BTS | 11.4586 | 123.1301 | 0.41 | Terrestrial Optical Fiber Drop | 2.51 | 4.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1353 | 2 | 353 | 1353 | 0301420036 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Maharlika | 14.8223 | 121.058 | U | 3195 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0004 | PTCI/MIDC | 14.7931 | 121.063 | 0.27 | Terrestrial Optical Fiber Drop | 1.68 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1354 | 2 | 354 | 1354 | 0304927015 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tagumpay | 15.3608 | 120.9421 | R | 1295 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03195-B07 | PTCI/MIDC | 15.3513 | 120.9393 | 1.1 | Terrestrial Optical Fiber Drop | 0.7 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1355 | 2 | 355 | 1355 | 0300804036 | Region III (Central Luzon) | Bataan | Dinalupihan | San Ramon | 14.8692 | 120.4626 | U | 3953 | 1098 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030571 | FTAP Globe | 14.8719 | 120.4652 | 0.41 | Terrestrial Optical Fiber Drop | 0.7 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1356 | 2 | 356 | 1356 | 0205005021 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Don Mariano Marcos | 16.4831 | 121.1514 | U | 2213 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.37 | Terrestrial Optical Fiber Drop | 0.7 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1357 | 2 | 357 | 1357 | 0403406001 | Region IV-A (CALABARZON) | Laguna | Calauan | Balayhangin | 14.1411 | 121.3099 | U | 6106 | 1850 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02343-C08 | PTCI/MIDC | 14.1396 | 121.3118 | 0.26 | Terrestrial Optical Fiber Drop | 0.7 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1358 | 2 | 358 | 1358 | 0105546027 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Nancayasan | 15.954 | 120.5766 | U | 8812 | 2447 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01769-B07 | PTCI/MIDC | 15.9536 | 120.5749 | 0.19 | Terrestrial Optical Fiber Drop | 0.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1359 | 2 | 359 | 1359 | 1606724048 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Taft | 9.7836 | 125.4986 | U | 20358 | 4965 | 1490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0012 | PTCI/MIDC | 9.7815 | 125.4989 | 0.19 | Terrestrial Optical Fiber Drop | 0.65 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1360 | 2 | 360 | 1360 | 1001315014 | Region X (Northern Mindanao) | Bukidnon | Maramag | North Poblacion | 7.7596 | 125.0075 | U | 16064 | 4227 | 1268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0054 | PTCI/MIDC | 7.7578 | 125.0049 | 0.35 | Terrestrial Optical Fiber Drop | 0.7 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1361 | 2 | 361 | 1361 | 0307106004 | Region III (Central Luzon) | Zambales | Masinloc | Collat | 15.5425 | 119.9526 | R | 3339 | 878 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0012 | PTCI/MIDC | 15.5354 | 119.9518 | 0.8 | Terrestrial Optical Fiber Drop | 0.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1362 | 2 | 362 | 1362 | 0803702054 | Region VIII (Eastern Visayas) | Leyte | Alangalang | San Roque | 11.2086 | 124.8466 | R | 1145 | 301 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 0.44 | Terrestrial Optical Fiber Drop | 0.7 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1363 | 2 | 363 | 1363 | 1030500041 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bugo | 8.5035 | 124.7527 | U | 31796 | 8832 | 2650 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0039 | PTCI/MIDC | 8.5035 | 124.756 | 0.36 | Terrestrial Optical Fiber Drop | 0.7 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1364 | 2 | 364 | 1364 | 0600415006 | Region VI (Western Visayas) | Aklan | New Washington | Jalas | 11.6617 | 122.4007 | R | 1699 | 435 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.93 | Terrestrial Optical Fiber Drop | 3.99 | 4.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1365 | 2 | 365 | 1365 | 0603047015 | Region VI (Western Visayas) | Iloilo | Zarraga | Pajo | 10.7401 | 122.5413 | R | 1279 | 336 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.85 | Terrestrial Optical Fiber Drop | 2.85 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1366 | 2 | 366 | 1366 | 1004313009 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Tabok | 8.801 | 124.7851 | R | 2492 | 638 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.72 | Terrestrial Optical Fiber Drop | 0.7 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1367 | 2 | 367 | 1367 | 0105531029 | Region I (Ilocos Region) | Pangasinan | Rosales | Station District | 15.89 | 120.6345 | R | 2772 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00544 | Edgepoint | 15.8933 | 120.6367 | 0.43 | Terrestrial Optical Fiber Drop | 0.7 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1368 | 2 | 368 | 1368 | 0803748040 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Buntay | 11.1109 | 125.0168 | R | 967 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080011 | FTAP BTS | 11.1165 | 125.0165 | 0.63 | Terrestrial Optical Fiber Drop | 0.7 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1369 | 2 | 369 | 1369 | 0631000156 | Region VI (Western Visayas) | Iloilo | City of Iloilo | San Juan | 10.6849 | 122.5453 | U | 11852 | 2821 | 846 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0041 | PTCI/MIDC | 10.6914 | 122.5427 | 0.78 | Terrestrial Optical Fiber Drop | 0.7 | 3.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1370 | 2 | 370 | 1370 | 1606724068 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Washington | 9.786 | 125.4888 | U | 20439 | 4985 | 1496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0009 | PTCI/MIDC | 9.7834 | 125.4889 | 0.29 | Terrestrial Optical Fiber Drop | 0.7 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1371 | 2 | 371 | 1371 | 0301410043 | Region III (Central Luzon) | Bulacan | City of Malolos | San Juan | 14.8344 | 120.8148 | U | 4773 | 1363 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02258 | Edgepoint | 14.8415 | 120.8115 | 0.86 | Terrestrial Optical Fiber Drop | 0.71 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1372 | 2 | 372 | 1372 | 0405647030 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Ipilan | 14.024 | 121.587 | R | 4041 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B39 | FTAP Smart | 14.0303 | 121.5879 | 0.71 | Terrestrial Optical Fiber Drop | 0.7 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1373 | 2 | 373 | 1373 | 0105522030 | Region I (Ilocos Region) | Pangasinan | Lingayen | Rosario | 15.9453 | 120.2669 | R | 2541 | 705 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00518 | Edgepoint | 15.9402 | 120.2679 | 0.58 | Terrestrial Optical Fiber Drop | 0.71 | 7.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1374 | 2 | 374 | 1374 | 0300809001 | Region III (Central Luzon) | Bataan | Orani | Bagong Paraiso | 14.7999 | 120.5302 | R | 3258 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01183 | Edgepoint | 14.8017 | 120.5308 | 0.22 | Terrestrial Optical Fiber Drop | 0.71 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1375 | 2 | 375 | 1375 | 1001317003 | Region X (Northern Mindanao) | Bukidnon | Quezon | Delapa | 7.7025 | 125.1136 | R | 2898 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.5 | Terrestrial Optical Fiber Drop | 0.54 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1376 | 2 | 376 | 1376 | 0401021025 | Region IV-A (CALABARZON) | Batangas | Rosario | Namuco | 13.8381 | 121.2019 | U | 6065 | 1684 | 505 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 0.98 | Terrestrial Optical Fiber Drop | 0.71 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1377 | 2 | 377 | 1377 | 0402106021 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado I | 14.3202 | 120.9563 | U | 8424 | 2477 | 743 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040179 | FTAP Globe | 14.3126 | 120.9715 | 0.16 | Terrestrial Optical Fiber Drop | 1.33 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1378 | 2 | 378 | 1378 | 0306905055 | Region III (Central Luzon) | Tarlac | Concepcion | Green Village | 15.3244 | 120.6464 | R | 2985 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.87 | Terrestrial Optical Fiber Drop | 0.71 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1379 | 2 | 379 | 1379 | 1403213042 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao Norte | 17.4189 | 121.4444 | U | 5871 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140132 | FTAP Globe | 17.4146 | 121.443 | 0.5 | Terrestrial Optical Fiber Drop | 0.71 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1380 | 2 | 380 | 1380 | 0402109045 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VI | 14.4072 | 120.9361 | R | 2858 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAM0364 | PTCI/MIDC | 14.3883 | 120.8963 | 0.19 | Terrestrial Optical Fiber Drop | 0.49 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1381 | 2 | 381 | 1381 | 0600403026 | Region VI (Western Visayas) | Aklan | Banga | Tabayon | 11.6327 | 122.347 | R | 2005 | 514 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 2.06 | Terrestrial Optical Fiber Drop | 0.71 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1382 | 2 | 382 | 1382 | 1408104020 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Poblacion | 18.0256 | 121.1833 | R | 3210 | 764 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-APA-00050 | Edgepoint | 18.0144 | 121.1855 | 1.26 | Terrestrial Optical Fiber Drop | 0.71 | 9.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1383 | 2 | 383 | 1383 | 0203114013 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Baligatan | 17.1233 | 121.8669 | U | 2812 | 740 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0016 | PTCI/MIDC | 17.1227 | 121.8677 | 0.1 | Terrestrial Optical Fiber Drop | 0.71 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1384 | 2 | 384 | 1384 | 0604524011 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay II | 10.4844 | 123.4169 | U | 6797 | 1837 | 551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0058 | PTCI/MIDC | 10.4822 | 123.4207 | 0.48 | Terrestrial Optical Fiber Drop | 0.71 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1385 | 2 | 385 | 1385 | 0330100005 | Region III (Central Luzon) | Pampanga | City of Angeles | Claro M. Recto | 15.1452 | 120.5927 | U | 5377 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.24 | Terrestrial Optical Fiber Drop | 0.71 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1386 | 2 | 386 | 1386 | 1630400055 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Limaha Pob. | 8.9526 | 125.5323 | U | 5768 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0010 | PTCI/MIDC | 8.947 | 125.5334 | 0.63 | Terrestrial Optical Fiber Drop | 0.71 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1387 | 2 | 387 | 1387 | 0203104016 | Region II (Cagayan Valley) | Isabela | Benito Soliven | District I | 16.979 | 121.9586 | R | 3549 | 933 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0041 | LDIC | 16.9909 | 121.9458 | 1.9 | Terrestrial Optical Fiber Drop | 0.71 | 11.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1388 | 2 | 388 | 1388 | 0301423001 | Region III (Central Luzon) | Bulacan | Santa Maria | Bagbaguin | 14.8188 | 120.9555 | U | 8194 | 2341 | 702 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01054-B07 | PTCI/MIDC | 14.8182 | 120.9565 | 0.13 | Terrestrial Optical Fiber Drop | 0.71 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1389 | 2 | 389 | 1389 | 0401030004 | Region IV-A (CALABARZON) | Batangas | Talisay | Banga | 14.0927 | 121.0119 | U | 4977 | 1382 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.58 | Terrestrial Optical Fiber Drop | 0.71 | 5.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1390 | 2 | 390 | 1390 | 0601914030 | Region VI (Western Visayas) | Capiz | City of Roxas | Inzo Arnaldo Village | 11.586 | 122.7541 | U | 5115 | 1346 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.73 | Terrestrial Optical Fiber Drop | 0.71 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1391 | 2 | 391 | 1391 | 0304911061 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santo Cristo District | 15.6578 | 120.7601 | U | 4141 | 1183 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02875-B07 | PTCI/MIDC | 15.6577 | 120.7609 | 0.09 | Terrestrial Optical Fiber Drop | 0.71 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1392 | 2 | 392 | 1392 | 0301412001 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bagbaguin | 14.8189 | 120.9555 | U | 8807 | 2516 | 755 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01054-B07 | PTCI/MIDC | 14.8182 | 120.9565 | 0.13 | Terrestrial Optical Fiber Drop | 0.71 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1393 | 2 | 393 | 1393 | 0403424010 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-F | 14.0601 | 121.323 | U | 2395 | 725 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02075-C08 | PTCI/MIDC | 14.0549 | 121.3128 | 1.24 | Terrestrial Optical Fiber Drop | 0.71 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1394 | 2 | 394 | 1394 | 0402109031 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-D | 14.3735 | 120.9416 | U | 4030 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01898-C08 | PTCI/MIDC | 14.3775 | 120.9413 | 0.45 | Terrestrial Optical Fiber Drop | 1.15 | 7.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1395 | 2 | 395 | 1395 | 0307707033 | Region III (Central Luzon) | Aurora | Maria Aurora | San Jose | 15.7874 | 121.4786 | R | 1312 | 345 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02889-B06 | PTCI/MIDC | 15.7802 | 121.482 | 0.88 | Terrestrial Optical Fiber Drop | 0.72 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1396 | 2 | 396 | 1396 | 0403414013 | Region IV-A (CALABARZON) | Laguna | Mabitac | Sinagtala | 14.4417 | 121.4005 | R | 968 | 293 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_LAG_0002 | LDIC | 121.4271 | 14.4267 | 0.93 | Terrestrial Optical Fiber Drop | 3.11 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1397 | 2 | 397 | 1397 | 0601916020 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Sur | 11.4219 | 122.6617 | R | 1889 | 497 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1.13 | Terrestrial Optical Fiber Drop | 0.72 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1398 | 2 | 398 | 1398 | 0601914014 | Region VI (Western Visayas) | Capiz | City of Roxas | Poblacion VII | 11.5825 | 122.7471 | R | 2196 | 577 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.74 | Terrestrial Optical Fiber Drop | 0.72 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1399 | 2 | 399 | 1399 | 0402109019 | Region IV-A (CALABARZON) | Cavite | City of Imus | Palico I | 14.4278 | 120.9466 | R | 2175 | 639 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01924-C08 | PTCI/MIDC | 14.3888 | 120.9378 | 0.48 | Terrestrial Optical Fiber Drop | 0.28 | 2.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1400 | 2 | 400 | 1400 | 0401021026 | Region IV-A (CALABARZON) | Batangas | Rosario | Namunga | 13.8454 | 121.1948 | U | 5862 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 0.21 | Terrestrial Optical Fiber Drop | 0.72 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1401 | 2 | 401 | 1401 | 0103314019 | Region I (Ilocos Region) | La Union | City of San Fernando | Camansi | 16.615 | 120.336 | R | 1000 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3087 | FTAP Smart | 16.6106 | 120.321 | 0.55 | Terrestrial Optical Fiber Drop | 2.32 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1402 | 2 | 402 | 1402 | 0201513021 | Region II (Cagayan Valley) | Cagayan | Gattaran | Centro Sur | 18.0605 | 121.6425 | R | 2191 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00048 | Edgepoint | 18.056 | 121.6434 | 0.5 | Terrestrial Optical Fiber Drop | 0.72 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1403 | 2 | 403 | 1403 | 0402103038 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mabolo III | 14.4516 | 120.9291 | R | 2458 | 722 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S3365 | FTAP Smart | 14.4127 | 120.9414 | 0.29 | Terrestrial Optical Fiber Drop | 2.17 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1404 | 2 | 404 | 1404 | 0307113024 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion South | 15.7614 | 119.9107 | U | 3885 | 1022 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0008 | PTCI/MIDC | 15.7531 | 119.9154 | 1.05 | Terrestrial Optical Fiber Drop | 0.72 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1405 | 2 | 405 | 1405 | 0304927003 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Burgos District | 15.3607 | 120.9422 | R | 2367 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1327 | FTAP Smart | 15.3572 | 120.9313 | 0.81 | Terrestrial Optical Fiber Drop | 0.71 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1406 | 2 | 406 | 1406 | 0431200024 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ilayang Iyam | 13.9346 | 121.6051 | U | 12231 | 3057 | 917 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0893 | FTAP Smart | 13.9374 | 121.609 | 0.53 | Terrestrial Optical Fiber Drop | 0.72 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1407 | 2 | 407 | 1407 | 1001317007 | Region X (Northern Mindanao) | Bukidnon | Quezon | Cawayan | 7.7004 | 125.1742 | R | 1078 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.68 | Terrestrial Optical Fiber Drop | 6.55 | 6.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1408 | 2 | 408 | 1408 | 0307111008 | Region III (Central Luzon) | Zambales | San Marcelino | Linasin | 14.9735 | 120.1496 | R | 3215 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00974 | Edgepoint | 14.9764 | 120.153 | 0.49 | Terrestrial Optical Fiber Drop | 0.72 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1409 | 2 | 409 | 1409 | 0500516011 | Region V (Bicol Region) | Albay | Santo Domingo | San Vicente Pob. | 13.2382 | 123.7761 | R | 1357 | 330 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050154 | FTAP Globe | 13.2479 | 123.7822 | 1.57 | Terrestrial Optical Fiber Drop | 0.17 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1410 | 2 | 410 | 1410 | 1705204007 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Campaasan | 12.3365 | 121.3394 | U | 3268 | 837 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03378-C09 | PTCI/MIDC | 12.32 | 121.3406 | 1.84 | Terrestrial Optical Fiber Drop | 0.72 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1411 | 2 | 411 | 1411 | 0405808003 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Geronimo | 14.7325 | 121.1496 | U | 6475 | 1798 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00837-A04 | PTCI/MIDC | 14.7318 | 121.151 | 0.17 | Terrestrial Optical Fiber Drop | 0.72 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1412 | 2 | 412 | 1412 | 0600411007 | Region VI (Western Visayas) | Aklan | Makato | Cajilo | 11.7222 | 122.2957 | R | 2061 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.9 | Terrestrial Optical Fiber Drop | 0.73 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1413 | 2 | 413 | 1413 | 0803740022 | Region VIII (Eastern Visayas) | Leyte | Palompon | Mazawalo Pob. | 11.0458 | 124.389 | R | 4628 | 1217 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 9.33 | Terrestrial Optical Fiber Drop | 0.73 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1414 | 2 | 414 | 1414 | 0604518002 | Region VI (Western Visayas) | Negros Occidental | Manapla | Barangay I | 10.8505 | 123.16 | R | 2253 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060323 | FTAP Globe | 10.9526 | 123.1256 | 0.41 | Terrestrial Optical Fiber Drop | 11.05 | 9.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1415 | 2 | 415 | 1415 | 1030500037 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bayabas | 8.5132 | 124.6388 | U | 14245 | 3956 | 1187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0041 | PTCI/MIDC | 8.5098 | 124.6401 | 0.41 | Terrestrial Optical Fiber Drop | 0.73 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1416 | 2 | 416 | 1416 | 0403405045 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Prinza | 14.2007 | 121.1405 | U | 5792 | 1755 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0010 | LDIC | 14.1974 | 121.1394 | 0.39 | Terrestrial Optical Fiber Drop | 0.73 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1417 | 2 | 417 | 1417 | 0405804014 | Region IV-A (CALABARZON) | Rizal | Binangonan | Kalawaan | 14.491 | 121.185 | U | 37983 | 10550 | 3165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0115 | PTCI/MIDC | 14.4923 | 121.1859 | 0.18 | Terrestrial Optical Fiber Drop | 0.73 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1418 | 2 | 418 | 1418 | 0301422021 | Region III (Central Luzon) | Bulacan | San Rafael | Pasong Intsik | 15.0106 | 120.9694 | R | 1560 | 445 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030507 | FTAP Globe | 15.001 | 120.9731 | 1.14 | Terrestrial Optical Fiber Drop | 0.73 | 3.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1419 | 2 | 419 | 1419 | 0301403019 | Region III (Central Luzon) | Bulacan | Baliuag | Santa Barbara | 14.9419 | 120.8903 | U | 13210 | 3774 | 1132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01008 | Edgepoint | 14.9414 | 120.888 | 0.25 | Terrestrial Optical Fiber Drop | 0.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1420 | 2 | 420 | 1420 | 1705110034 | MIMAROPA Region | Occidental Mindoro | San Jose | Pag-Asa | 12.3443 | 121.0655 | U | 12657 | 3245 | 974 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170137 | FTAP Globe | 12.3508 | 121.0661 | 0.73 | Terrestrial Optical Fiber Drop | 0.73 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1421 | 2 | 421 | 1421 | 0600613017 | Region VI (Western Visayas) | Antique | San Jose | Funda-Dalipe | 10.7602 | 121.9317 | U | 7419 | 1902 | 571 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0020 | PTCI/MIDC | 10.76 | 121.9281 | 0.4 | Terrestrial Optical Fiber Drop | 0.73 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1422 | 2 | 422 | 1422 | 0201505029 | Region II (Cagayan Valley) | Cagayan | Aparri | Macanaya | 18.3506 | 121.6396 | U | 5709 | 1463 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3433 | FTAP Smart | 18.3503 | 121.639 | 0.07 | Terrestrial Optical Fiber Drop | 0.73 | 10.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1423 | 2 | 423 | 1423 | 1705205029 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Lazareto | 13.4283 | 121.1996 | R | 4858 | 1245 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 0.37 | Terrestrial Optical Fiber Drop | 0.73 | 6.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1424 | 2 | 424 | 1424 | 0506203025 | Region V (Bicol Region) | Sorsogon | Bulan | Benigno S. Aquino | 12.6759 | 123.8752 | R | 3631 | 907 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SOR_0002 | LDIC | 12.6765 | 123.8744 | 0.11 | Terrestrial Optical Fiber Drop | 0.73 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1425 | 2 | 425 | 1425 | 0330100003 | Region III (Central Luzon) | Pampanga | City of Angeles | Balibago | 15.1699 | 120.5837 | U | 44148 | 12263 | 3679 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030444 | FTAP Globe | 15.1704 | 120.5779 | 0.62 | Terrestrial Optical Fiber Drop | 0.73 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1426 | 2 | 426 | 1426 | 0402115013 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Silangan | 14.3243 | 120.7778 | U | 11097 | 3263 | 979 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02229-C08 | PTCI/MIDC | 14.3227 | 120.7719 | 0.67 | Terrestrial Optical Fiber Drop | 0.73 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1427 | 2 | 427 | 1427 | 0501723006 | Region V (Bicol Region) | Camarines Sur | Nabua | Inapatan | 13.3991 | 123.3183 | R | 2942 | 700 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03257-C10 | PTCI/MIDC | 13.4086 | 123.3098 | 1.41 | Terrestrial Optical Fiber Drop | 0.73 | 5.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1428 | 2 | 428 | 1428 | 0305403018 | Region III (Central Luzon) | Pampanga | Arayat | Poblacion | 15.1489 | 120.771 | U | 2331 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.15 | Terrestrial Optical Fiber Drop | 0.73 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1429 | 2 | 429 | 1429 | 0500504009 | Region V (Bicol Region) | Albay | Guinobatan | Calzada | 13.1906 | 123.5974 | R | 2600 | 634 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 0.27 | Terrestrial Optical Fiber Drop | 0.73 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1430 | 2 | 430 | 1430 | 0403417048 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Talangan | 14.1437 | 121.4138 | R | 2234 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02122-C08 | PTCI/MIDC | 14.1344 | 121.4104 | 1.1 | Terrestrial Optical Fiber Drop | 0.73 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1431 | 2 | 431 | 1431 | 0203137042 | Region II (Cagayan Valley) | Isabela | Tumauini | San Pedro | 17.2775 | 121.8103 | U | 3086 | 812 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 0.71 | Terrestrial Optical Fiber Drop | 0.73 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1432 | 2 | 432 | 1432 | 0105518008 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Bonuan Boquig | 16.0778 | 120.3583 | U | 15474 | 4298 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00416 | Edgepoint | 16.0777 | 120.3608 | 0.27 | Terrestrial Optical Fiber Drop | 0.73 | 3.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1433 | 2 | 433 | 1433 | 0603043061 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Barangay Zone VI | 10.8219 | 122.5327 | R | 3583 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.18 | Terrestrial Optical Fiber Drop | 0.64 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1434 | 2 | 434 | 1434 | 0402106016 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone I | 14.3203 | 120.9567 | U | 4441 | 1306 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01857-C08 | PTCI/MIDC | 14.3195 | 120.9635 | 0.35 | Terrestrial Optical Fiber Drop | 1.3 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1435 | 2 | 435 | 1435 | 0500504048 | Region V (Bicol Region) | Albay | Guinobatan | Travesia | 13.1892 | 123.6105 | R | 3871 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 1.22 | Terrestrial Optical Fiber Drop | 0.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1436 | 2 | 436 | 1436 | 0405635010 | Region IV-A (CALABARZON) | Quezon | Plaridel | Pampaaralan | 13.9553 | 122.0153 | R | 544 | 143 | 43 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040420 | FTAP Globe | 13.9547 | 122.0232 | 0.85 | Terrestrial Optical Fiber Drop | 0.73 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1437 | 2 | 437 | 1437 | 0603047011 | Region VI (Western Visayas) | Iloilo | Zarraga | Jalaud Norte | 10.8298 | 122.6158 | R | 2460 | 647 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060021 | FTAP BTS | 10.8361 | 122.6092 | 1.01 | Terrestrial Optical Fiber Drop | 0.73 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1438 | 2 | 438 | 1438 | 0306910016 | Region III (Central Luzon) | Tarlac | Paniqui | Estacion | 15.6743 | 120.5847 | U | 4960 | 1271 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.52 | Terrestrial Optical Fiber Drop | 0.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1439 | 2 | 439 | 1439 | 0402116003 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo I | 14.4285 | 120.8763 | R | 1999 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.23 | Terrestrial Optical Fiber Drop | 0.73 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1440 | 2 | 440 | 1440 | 0402103019 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Real I | 14.4333 | 120.9397 | U | 5560 | 1635 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01895-C08 | PTCI/MIDC | 14.433 | 120.9376 | 0.23 | Terrestrial Optical Fiber Drop | 0.74 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1441 | 2 | 441 | 1441 | 0431200030 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Silangan | 13.9513 | 121.6415 | U | 9383 | 2345 | 704 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040414 | FTAP Globe | 13.9597 | 121.6314 | 1.43 | Terrestrial Optical Fiber Drop | 0.74 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1442 | 2 | 442 | 1442 | 0405608009 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Sur | 13.9164 | 121.4306 | U | 8660 | 2278 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1264 | FTAP Smart | 13.9179 | 121.4369 | 0.7 | Terrestrial Optical Fiber Drop | 0.74 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1443 | 2 | 443 | 1443 | 0701232004 | Region VII (Central Visayas) | Bohol | Maribojoc | Anislag | 9.7376 | 123.8501 | R | 1054 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BOH_0006 | LDIC | 9.7452 | 123.8513 | 0.85 | Terrestrial Optical Fiber Drop | 0.74 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1444 | 2 | 444 | 1444 | 0201526010 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Centro Norte | 17.8829 | 121.5712 | R | 3115 | 798 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-02201 | Edgepoint | 17.8863 | 121.5699 | 0.52 | Terrestrial Optical Fiber Drop | 0.25 | 7.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1445 | 2 | 445 | 1445 | 0803702018 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Cavite | 11.2188 | 124.8597 | R | 904 | 237 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0003 | PTCI/MIDC | 11.2031 | 124.8469 | 0.46 | Terrestrial Optical Fiber Drop | 2.39 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1446 | 2 | 446 | 1446 | 0402109001 | Region IV-A (CALABARZON) | Cavite | City of Imus | Alapan I-A | 14.4081 | 120.8967 | U | 14840 | 4364 | 1309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01880-C08 | PTCI/MIDC | 14.3979 | 120.9428 | 0.47 | Terrestrial Optical Fiber Drop | 2.73 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1447 | 2 | 447 | 1447 | 0806407059 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Tagnipa | 10.136 | 124.8353 | U | 3302 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.27 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1448 | 2 | 448 | 1448 | 0402119021 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Tolentino West | 14.132 | 120.9761 | R | 1517 | 446 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1604 | FTAP Smart | 14.1302 | 120.978 | 0.28 | Terrestrial Optical Fiber Drop | 0.74 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1449 | 2 | 449 | 1449 | 1402705007 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Mabatobato | 16.6594 | 121.2071 | R | 2152 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02362-B05 | PTCI/MIDC | 16.6558 | 121.209 | 0.45 | Terrestrial Optical Fiber Drop | 0.74 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1450 | 2 | 450 | 1450 | 0105525039 | Region I (Ilocos Region) | Pangasinan | Manaoag | Poblacion | 16.0452 | 120.4908 | U | 5514 | 1531 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_PNG_0001 | LDIC | 16.0437 | 120.492 | 0.2 | Terrestrial Optical Fiber Drop | 0.74 | 7.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1451 | 2 | 451 | 1451 | 0501725019 | Region V (Bicol Region) | Camarines Sur | Ocampo | San Francisco | 13.5595 | 123.3822 | R | 3182 | 757 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.1 | Terrestrial Optical Fiber Drop | 0.74 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1452 | 2 | 452 | 1452 | 0501716033 | Region V (Bicol Region) | Camarines Sur | City of Iriga | Santa Teresita | 13.484 | 123.4245 | R | 3076 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03173-C10 | PTCI/MIDC | 13.48 | 123.4199 | 0.67 | Terrestrial Optical Fiber Drop | 0.74 | 5.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1453 | 2 | 453 | 1453 | 0403428003 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Caingin | 14.3047 | 121.1255 | U | 26835 | 8131 | 2439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02093-C08 | PTCI/MIDC | 14.3014 | 121.117 | 0.99 | Terrestrial Optical Fiber Drop | 0.74 | 2.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1454 | 2 | 454 | 1454 | 0501705025 | Region V (Bicol Region) | Camarines Sur | Buhi | San Isidro | 13.3789 | 123.5101 | R | 2741 | 652 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.75 | Terrestrial Optical Fiber Drop | 4.16 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1455 | 2 | 455 | 1455 | 0500506008 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 12 - Tula-tula | 13.1406 | 123.7361 | R | 2338 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0039 | PTCI/MIDC | 13.1354 | 123.7419 | 0.32 | Terrestrial Optical Fiber Drop | 0.42 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1456 | 2 | 456 | 1456 | 0105545013 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Malayo | 15.8272 | 120.3429 | R | 2045 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00567 | Edgepoint | 15.8227 | 120.332 | 1.27 | Terrestrial Optical Fiber Drop | 0.74 | 10.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1457 | 2 | 457 | 1457 | 0304911060 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santa Veronica District | 15.663 | 120.7621 | U | 4221 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02875-B07 | PTCI/MIDC | 15.6577 | 120.7609 | 0.61 | Terrestrial Optical Fiber Drop | 0.75 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1458 | 2 | 458 | 1458 | 0401022001 | Region IV-A (CALABARZON) | Batangas | San Jose | Aguila | 13.8835 | 121.0983 | U | 3031 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1014 | FTAP Smart | 13.8783 | 121.0934 | 0.5 | Terrestrial Optical Fiber Drop | 0.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1459 | 2 | 459 | 1459 | 1430300046 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Holy Ghost Extension | 16.4179 | 120.6046 | R | 2945 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0015 | LDIC | 16.4176 | 120.6046 | 0.03 | Terrestrial Optical Fiber Drop | 0.75 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1460 | 2 | 460 | 1460 | 1606819018 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | San Agustin Sur | 9.0775 | 126.1906 | U | 5982 | 1459 | 438 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.77 | Terrestrial Optical Fiber Drop | 0.75 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1461 | 2 | 461 | 1461 | 0403425028 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Rosario | 14.3361 | 121.0486 | U | 6479 | 1963 | 589 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03020-C08 | PTCI/MIDC | 14.3628 | 121.0347 | 0.67 | Terrestrial Optical Fiber Drop | 1.29 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1462 | 2 | 462 | 1462 | 0401022031 | Region IV-A (CALABARZON) | Batangas | San Jose | Taysan | 13.8835 | 121.0996 | U | 3214 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1014 | FTAP Smart | 13.8783 | 121.0934 | 0.88 | Terrestrial Optical Fiber Drop | 0.75 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1463 | 2 | 463 | 1463 | 0306906034 | Region III (Central Luzon) | Tarlac | Gerona | Salapungan | 15.594 | 120.6114 | U | 3181 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00639 | Edgepoint | 15.5983 | 120.6246 | 1.49 | Terrestrial Optical Fiber Drop | 0.75 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1464 | 2 | 464 | 1464 | 0405647045 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Opias | 14.03 | 121.5908 | U | 5490 | 1444 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00120-C08 | PTCI/MIDC | 14.028 | 121.5926 | 0.29 | Terrestrial Optical Fiber Drop | 0.75 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1465 | 2 | 465 | 1465 | 0401029013 | Region IV-A (CALABARZON) | Batangas | Taal | Halang | 13.9006 | 120.9304 | R | 1585 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040516 | FTAP Globe | 13.893 | 120.9287 | 0.86 | Terrestrial Optical Fiber Drop | 0.75 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1466 | 2 | 466 | 1466 | 0401001014 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Pansipit | 13.9286 | 120.9448 | R | 1842 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040462 | FTAP Globe | 13.9283 | 120.9517 | 0.74 | Terrestrial Optical Fiber Drop | 0.75 | 4.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1467 | 2 | 467 | 1467 | 0402107007 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Kaypaaba | 14.1836 | 120.7893 | R | 2213 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.94 | Terrestrial Optical Fiber Drop | 0.75 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1468 | 2 | 468 | 1468 | 0401027006 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Cuta East | 13.8654 | 120.99 | R | 1233 | 342 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1310 | FTAP Smart | 13.8604 | 120.9908 | 0.57 | Terrestrial Optical Fiber Drop | 0.75 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1469 | 2 | 469 | 1469 | 0401034001 | Region IV-A (CALABARZON) | Batangas | Tuy | Acle | 14.0216 | 120.7302 | R | 1207 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.64 | Terrestrial Optical Fiber Drop | 0.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1470 | 2 | 470 | 1470 | 1130700134 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 1-A | 7.0637 | 125.6074 | R | 3214 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0021 | PTCI/MIDC | 7.0614 | 125.6075 | 0.26 | Terrestrial Optical Fiber Drop | 0.75 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1471 | 2 | 471 | 1471 | 0300811023 | Region III (Central Luzon) | Bataan | Pilar | Santa Rosa | 14.6772 | 120.5473 | U | 7499 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.74 | Terrestrial Optical Fiber Drop | 0.75 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1472 | 2 | 472 | 1472 | 0402103012 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi I | 14.46 | 120.9523 | U | 5551 | 1632 | 490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.93 | Terrestrial Optical Fiber Drop | 0.75 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1473 | 2 | 473 | 1473 | 0301405010 | Region III (Central Luzon) | Bulacan | Bulacan | San Jose | 14.7934 | 120.881 | U | 3732 | 1066 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01187 | Edgepoint | 14.7956 | 120.8781 | 0.72 | Terrestrial Optical Fiber Drop | 0.44 | 3.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1474 | 2 | 474 | 1474 | 1130700069 | Region XI (Davao Region) | Davao del Sur | City of Davao | Mandug | 7.1554 | 125.5886 | U | 15916 | 4681 | 1404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110320 | FTAP BTS | 7.1611 | 125.5956 | 1 | Terrestrial Optical Fiber Drop | 0.75 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1475 | 2 | 475 | 1475 | 1401110005 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Balili | 16.4497 | 120.5949 | U | 18238 | 5210 | 1563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140179 | FTAP Globe | 16.4461 | 120.5914 | 0.56 | Terrestrial Optical Fiber Drop | 0.75 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1476 | 2 | 476 | 1476 | 0301421054 | Region III (Central Luzon) | Bulacan | San Miguel | Tartaro | 15.1664 | 121.0398 | U | 6312 | 1803 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030445 | FTAP Globe | 15.1702 | 121.044 | 0.62 | Terrestrial Optical Fiber Drop | 0.75 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1477 | 2 | 477 | 1477 | 1001315008 | Region X (Northern Mindanao) | Bukidnon | Maramag | Dologon | 7.8351 | 125.0421 | U | 15472 | 4071 | 1221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0031 | PTCI/MIDC | 7.835 | 125.045 | 0.33 | Terrestrial Optical Fiber Drop | 0.76 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1478 | 2 | 478 | 1478 | 0402104006 | Region IV-A (CALABARZON) | Cavite | Carmona | Cabilang Baybay | 14.3177 | 121.0498 | U | 8144 | 2395 | 719 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040171 | FTAP Globe | 14.3204 | 121.0566 | 0.79 | Terrestrial Optical Fiber Drop | 0.76 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1479 | 2 | 479 | 1479 | 0506216052 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Rawis | 13.039 | 124.0309 | R | 1682 | 420 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 1.12 | Terrestrial Optical Fiber Drop | 0.76 | 6.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1480 | 2 | 480 | 1480 | 1705318030 | MIMAROPA Region | Palawan | Roxas | Barangay III | 10.3228 | 119.349 | U | 6360 | 1630 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 0.81 | Terrestrial Optical Fiber Drop | 0.76 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1481 | 2 | 481 | 1481 | 0304915015 | Region III (Central Luzon) | Nueva Ecija | Llanera | Plaridel | 15.6788 | 121.0161 | R | 4045 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01467-B07 | PTCI/MIDC | 15.6627 | 121.0175 | 0.98 | Terrestrial Optical Fiber Drop | 1.49 | 6.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1482 | 2 | 482 | 1482 | 0405623001 | Region IV-A (CALABARZON) | Quezon | Lucban | Abang | 14.117 | 121.5501 | R | 2291 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02140-C08 | PTCI/MIDC | 14.1164 | 121.5576 | 0.81 | Terrestrial Optical Fiber Drop | 0.94 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1483 | 2 | 483 | 1483 | 0405638006 | Region IV-A (CALABARZON) | Quezon | Real | Lubayat | 14.4992 | 121.6261 | R | 1709 | 449 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040059 | FTAP Globe | 14.5404 | 121.5893 | 6.05 | Terrestrial Optical Fiber Drop | 0.76 | 19.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1484 | 2 | 484 | 1484 | 0501706026 | Region V (Bicol Region) | Camarines Sur | Bula | San Jose | 13.4738 | 123.2853 | R | 2557 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.91 | Terrestrial Optical Fiber Drop | 0.76 | 4.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1485 | 2 | 485 | 1485 | 0301411002 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Sur | 14.7639 | 120.9426 | U | 11075 | 3164 | 949 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0062 | PTCI/MIDC | 14.7657 | 120.9398 | 0.36 | Terrestrial Optical Fiber Drop | 0.76 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1486 | 2 | 486 | 1486 | 0405803005 | Region IV-A (CALABARZON) | Rizal | Baras | Santiago | 14.5215 | 121.2622 | R | 3964 | 1101 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01857 | Edgepoint | 14.5237 | 121.2629 | 0.25 | Terrestrial Optical Fiber Drop | 0.76 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1487 | 2 | 487 | 1487 | 1600206006 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Poblacion | 9.4546 | 125.5794 | R | 2474 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 4.64 | Terrestrial Optical Fiber Drop | 0.76 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1488 | 2 | 488 | 1488 | 1102509005 | Region XI (Davao Region) | Davao Oriental | City of Mati | Central | 6.9663 | 126.208 | U | 35778 | 9938 | 2981 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110506 | FTAP Globe | 6.9607 | 126.212 | 0.76 | Terrestrial Optical Fiber Drop | 0.77 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1489 | 2 | 489 | 1489 | 0731100019 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Pajo | 10.3109 | 123.9666 | U | 25856 | 7387 | 2216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0099 | PTCI/MIDC | 10.3117 | 123.9593 | 0.81 | Terrestrial Optical Fiber Drop | 0.76 | 3.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1490 | 2 | 490 | 1490 | 0402120004 | Region IV-A (CALABARZON) | Cavite | Tanza | Biwas | 14.3983 | 120.855 | U | 7357 | 2163 | 649 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040123 | FTAP Globe | 14.4014 | 120.8458 | 1.04 | Terrestrial Optical Fiber Drop | 0.76 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1491 | 2 | 491 | 1491 | 0205004020 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | San Antonio North | 16.3671 | 121.1059 | R | 2569 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01534-B05 | PTCI/MIDC | 16.3595 | 121.1042 | 0.86 | Terrestrial Optical Fiber Drop | 0.77 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1492 | 2 | 492 | 1492 | 1600209020 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Triangulo | 8.9734 | 125.3531 | U | 2916 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130068 | FTAP Globe | 8.9748 | 125.3618 | 0.96 | Terrestrial Optical Fiber Drop | 0.76 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1493 | 2 | 493 | 1493 | 1401106007 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Tuding | 16.419 | 120.6406 | U | 10488 | 2996 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BEN-00334 | Edgepoint | 16.4152 | 120.6326 | 0.95 | Terrestrial Optical Fiber Drop | 0.77 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1494 | 2 | 494 | 1494 | 0203108031 | Region II (Cagayan Valley) | Isabela | City of Cauayan | District I | 16.9316 | 121.7715 | U | 11763 | 3095 | 929 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020076 | FTAP Globe | 16.9339 | 121.7741 | 0.38 | Terrestrial Optical Fiber Drop | 0.77 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1495 | 2 | 495 | 1495 | 0405806007 | Region IV-A (CALABARZON) | Rizal | Cardona | Calahan | 14.4908 | 121.2345 | U | 5775 | 1604 | 481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040081 | FTAP Globe | 14.4931 | 121.234 | 0.26 | Terrestrial Optical Fiber Drop | 0.77 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1496 | 2 | 496 | 1496 | 0401029006 | Region IV-A (CALABARZON) | Batangas | Taal | Butong | 13.8691 | 120.9152 | U | 5493 | 1525 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01950-C08 | PTCI/MIDC | 13.8765 | 120.9183 | 0.89 | Terrestrial Optical Fiber Drop | 0.77 | 3.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1497 | 2 | 497 | 1497 | 0501719005 | Region V (Bicol Region) | Camarines Sur | Lupi | Bel-Cruz | 13.7764 | 122.8615 | R | 1023 | 243 | 73 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03080 | Edgepoint | 122.867 | 13.7754 | 0.6 | Terrestrial Optical Fiber Drop | 0.77 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1498 | 2 | 498 | 1498 | 0604502013 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Lag-Asan | 10.525 | 122.8412 | U | 13466 | 3639 | 1092 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0081 | PTCI/MIDC | 10.5207 | 122.8433 | 0.53 | Terrestrial Optical Fiber Drop | 0.77 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1499 | 2 | 499 | 1499 | 0931700021 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Canelar | 6.9155 | 122.0691 | U | 10960 | 3044 | 913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0121 | PTCI/MIDC | 6.9159 | 122.0719 | 0.31 | Terrestrial Optical Fiber Drop | 0.77 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1500 | 2 | 500 | 1500 | 0403402011 | Region IV-A (CALABARZON) | Laguna | Bay | San Isidro | 14.1856 | 121.2858 | R | 3019 | 914 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.4 | Terrestrial Optical Fiber Drop | 0.77 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1501 | 2 | 501 | 1501 | 0304924003 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Julo | 15.304 | 120.8644 | U | 5539 | 1582 | 475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00769 | Edgepoint | 15.3045 | 120.8649 | 0.08 | Terrestrial Optical Fiber Drop | 0.77 | 2.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1502 | 2 | 502 | 1502 | 1430300099 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | San Vicente | 16.3951 | 120.5968 | U | 5346 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0013 | PTCI/MIDC | 16.3965 | 120.5968 | 0.15 | Terrestrial Optical Fiber Drop | 0.77 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1503 | 2 | 503 | 1503 | 0405646037 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Santa Cecilia | 13.9669 | 122.5354 | R | 3763 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.62 | Terrestrial Optical Fiber Drop | 0.77 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1504 | 2 | 504 | 1504 | 0201525003 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Centro East | 18.2529 | 121.9066 | R | 1890 | 484 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01129-B06 | PTCI/MIDC | 18.2464 | 121.9084 | 0.75 | Terrestrial Optical Fiber Drop | 0.77 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1505 | 2 | 505 | 1505 | 0203126020 | Region II (Cagayan Valley) | Isabela | Roxas | San Placido | 17.1212 | 121.62 | U | 3617 | 951 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00180 | Edgepoint | 17.1198 | 121.6225 | 0.31 | Terrestrial Optical Fiber Drop | 0.77 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1506 | 2 | 506 | 1506 | 0201522010 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Langagan | 18.5535 | 121.2414 | R | 2505 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0031 | LDIC | 121.2405 | 18.556 | 0.3 | Terrestrial Optical Fiber Drop | 0.77 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1507 | 2 | 507 | 1507 | 0403424009 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-E | 14.0642 | 121.3244 | U | 2355 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 1.01 | Terrestrial Optical Fiber Drop | 0.77 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1508 | 2 | 508 | 1508 | 0403419015 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sampaloc | 14.2696 | 121.4444 | U | 4667 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040208 | FTAP Globe | 14.2666 | 121.4429 | 0.37 | Terrestrial Optical Fiber Drop | 0.77 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1509 | 2 | 509 | 1509 | 0304922005 | Region III (Central Luzon) | Nueva Ecija | Quezon | Dulong Bayan | 15.5544 | 120.8141 | U | 4184 | 1101 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00659 | Edgepoint | 15.5563 | 120.8126 | 0.27 | Terrestrial Optical Fiber Drop | 0.78 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1510 | 2 | 510 | 1510 | 0402103070 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba VI | 14.4611 | 120.9603 | R | 2729 | 802 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000702 | FTAP Globe | 14.4246 | 121.0236 | 0.29 | Terrestrial Optical Fiber Drop | 0.48 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1511 | 2 | 511 | 1511 | 0506216030 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Sampaloc | 12.9711 | 124.0104 | R | 4685 | 1171 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.6 | Terrestrial Optical Fiber Drop | 0.77 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1512 | 2 | 512 | 1512 | 1001317028 | Region X (Northern Mindanao) | Bukidnon | Quezon | Poblacion | 7.7293 | 125.0979 | U | 15246 | 4012 | 1204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100058 | FTAP BTS | 7.7366 | 125.095 | 0.88 | Terrestrial Optical Fiber Drop | 0.78 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1513 | 2 | 513 | 1513 | 0501709008 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Marcos | 13.6209 | 123.1657 | R | 1491 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.65 | Terrestrial Optical Fiber Drop | 0.69 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1514 | 2 | 514 | 1514 | 0306911007 | Region III (Central Luzon) | Tarlac | Pura | Matindeg | 15.6163 | 120.6527 | R | 1352 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.98 | Terrestrial Optical Fiber Drop | 0.78 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1515 | 2 | 515 | 1515 | 0105503022 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Pocalpocal | 16.1601 | 119.9819 | R | 2800 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N6719 | FTAP Smart | 16.155 | 119.9806 | 0.53 | Terrestrial Optical Fiber Drop | 1 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1516 | 2 | 516 | 1516 | 0501705029 | Region V (Bicol Region) | Camarines Sur | Buhi | San Pascual | 13.416 | 123.514 | R | 1235 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.28 | Terrestrial Optical Fiber Drop | 0.02 | 10.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1517 | 2 | 517 | 1517 | 0402103024 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba I | 14.4612 | 120.96 | R | 1949 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040112 | FTAP Globe | 14.4161 | 120.9742 | 0.59 | Terrestrial Optical Fiber Drop | 0.48 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1518 | 2 | 518 | 1518 | 1102412020 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone III | 6.8377 | 125.4155 | U | 12562 | 3694 | 1108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.17 | Terrestrial Optical Fiber Drop | 0.78 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1519 | 2 | 519 | 1519 | 0401021030 | Region IV-A (CALABARZON) | Batangas | Rosario | Pinagsibaan | 13.8397 | 121.3131 | R | 3648 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040548 | FTAP Globe | 13.8424 | 121.2877 | 2.76 | Terrestrial Optical Fiber Drop | 0.78 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1520 | 2 | 520 | 1520 | 1230800033 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Calumpang | 6.0785 | 125.141 | U | 90831 | 23290 | 6987 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120330 | FTAP Globe | 6.0828 | 125.1436 | 0.56 | Terrestrial Optical Fiber Drop | 0.78 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1521 | 2 | 521 | 1521 | 1130700135 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 2-A | 7.0631 | 125.6076 | U | 3054 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0021 | PTCI/MIDC | 7.0614 | 125.6075 | 0.19 | Terrestrial Optical Fiber Drop | 0.78 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1522 | 2 | 522 | 1522 | 0401005075 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 6 | 13.7603 | 121.0637 | R | 1864 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01986-C08 | PTCI/MIDC | 13.7624 | 121.0631 | 0.24 | Terrestrial Optical Fiber Drop | 0.78 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1523 | 2 | 523 | 1523 | 0702251017 | Region VII (Central Visayas) | Cebu | City of Toledo | Dumlog | 10.3937 | 123.6525 | U | 6743 | 1774 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 0.82 | Terrestrial Optical Fiber Drop | 0.78 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1524 | 2 | 524 | 1524 | 0630200022 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 26 | 10.6661 | 122.9518 | R | 1467 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0006 | PTCI/MIDC | 10.6237 | 122.9796 | 0.72 | Terrestrial Optical Fiber Drop | 0.1 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1525 | 2 | 525 | 1525 | 0330100022 | Region III (Central Luzon) | Pampanga | City of Angeles | Salapungan | 15.148 | 120.5983 | U | 5533 | 1536 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.47 | Terrestrial Optical Fiber Drop | 0.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1526 | 2 | 526 | 1526 | 0702214014 | Region VII (Central Visayas) | Cebu | City of Carcar | Poblacion III | 10.1056 | 123.6439 | U | 7495 | 1972 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0023 | PTCI/MIDC | 10.1027 | 123.6533 | 1.08 | Terrestrial Optical Fiber Drop | 0.78 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1527 | 2 | 527 | 1527 | 0305410021 | Region III (Central Luzon) | Pampanga | Macabebe | Sto. Niño | 14.9072 | 120.6936 | R | 2785 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.64 | Terrestrial Optical Fiber Drop | 2.26 | 7.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1528 | 2 | 528 | 1528 | 0306910025 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Sur | 15.6647 | 120.5807 | U | 4922 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.74 | Terrestrial Optical Fiber Drop | 0.78 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1529 | 2 | 529 | 1529 | 0301420010 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Sapang Palay | 14.8388 | 121.0434 | U | 6067 | 1733 | 520 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02259 | Edgepoint | 14.8402 | 121.044 | 0.17 | Terrestrial Optical Fiber Drop | 0.78 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1530 | 2 | 530 | 1530 | 0301420037 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan II | 14.8447 | 121.0799 | U | 6248 | 1785 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02259 | Edgepoint | 14.8402 | 121.044 | 0.04 | Terrestrial Optical Fiber Drop | 0.38 | 5.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1531 | 2 | 531 | 1531 | 0304928010 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Rizal | 15.4214 | 120.9379 | U | 2270 | 648 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01493-B07 | PTCI/MIDC | 15.4207 | 120.9403 | 0.27 | Terrestrial Optical Fiber Drop | 0.4 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1532 | 2 | 532 | 1532 | 0401029008 | Region IV-A (CALABARZON) | Batangas | Taal | Cawit | 13.8915 | 120.9204 | R | 2563 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0004 | LDIC | 13.8858 | 120.9194 | 0.64 | Terrestrial Optical Fiber Drop | 0.78 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1533 | 2 | 533 | 1533 | 1400101002 | Cordillera Administrative Region (CAR) | Abra | Bangued | Angad | 17.5887 | 120.6252 | R | 2743 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ABR-03102 | Edgepoint | 120.6153 | 17.5944 | 1.23 | Terrestrial Optical Fiber Drop | 0.78 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1534 | 2 | 534 | 1534 | 0203132011 | Region II (Cagayan Valley) | Isabela | San Mateo | Marasat Grande | 16.881 | 121.5803 | R | 1632 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0019 | PTCI/MIDC | 16.8744 | 121.5803 | 0.46 | Terrestrial Optical Fiber Drop | 0.48 | 12.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1535 | 2 | 535 | 1535 | 0201512019 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay IV | 17.5552 | 121.6978 | R | 1229 | 315 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00113 | Edgepoint | 17.5573 | 121.6932 | 0.54 | Terrestrial Optical Fiber Drop | 0.79 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1536 | 2 | 536 | 1536 | 0402103032 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban V | 14.4611 | 120.9645 | R | 2857 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02374-C08 | PTCI/MIDC | 14.4282 | 120.938 | 0.18 | Terrestrial Optical Fiber Drop | 0.52 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1537 | 2 | 537 | 1537 | 0403426022 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Sur | 14.2843 | 121.418 | R | 3508 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0050 | PTCI/MIDC | 14.286 | 121.4191 | 0.22 | Terrestrial Optical Fiber Drop | 0.79 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1538 | 2 | 538 | 1538 | 0501732019 | Region V (Bicol Region) | Camarines Sur | San Fernando | Rizal | 13.5651 | 123.1458 | R | 1530 | 364 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 0.62 | Terrestrial Optical Fiber Drop | 0.79 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1539 | 2 | 539 | 1539 | 0105501011 | Region I (Ilocos Region) | Pangasinan | Agno | Magsaysay | 16.1168 | 119.8 | R | 1560 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010129 | FTAP Globe | 16.122 | 119.8094 | 1.16 | Terrestrial Optical Fiber Drop | 0.79 | 9.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1540 | 2 | 540 | 1540 | 0402120003 | Region IV-A (CALABARZON) | Cavite | Tanza | Biga | 14.3617 | 120.8563 | U | 17918 | 5270 | 1581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.36 | Terrestrial Optical Fiber Drop | 0.79 | 2.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1541 | 2 | 541 | 1541 | 0105504009 | Region I (Ilocos Region) | Pangasinan | Alcala | Kisikis | 15.8439 | 120.5357 | U | 3690 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00561 | Edgepoint | 15.8477 | 120.5232 | 1.32 | Terrestrial Optical Fiber Drop | 1.04 | 7.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1542 | 2 | 542 | 1542 | 0403429005 | Region IV-A (CALABARZON) | Laguna | Siniloan | Buhay | 14.4286 | 121.4486 | R | 1217 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040106 | FTAP Globe | 14.4246 | 121.4454 | 0.56 | Terrestrial Optical Fiber Drop | 0.79 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1543 | 2 | 543 | 1543 | 0402109076 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion II-C | 14.4347 | 120.9309 | R | 1619 | 476 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02396-A03 | PTCI/MIDC | 14.4619 | 120.9719 | 0.66 | Terrestrial Optical Fiber Drop | 1.68 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1544 | 2 | 544 | 1544 | 0600407011 | Region VI (Western Visayas) | Aklan | Kalibo | Mobo | 11.6988 | 122.3599 | R | 1863 | 477 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 1.46 | Terrestrial Optical Fiber Drop | 0.79 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1545 | 2 | 545 | 1545 | 0300807019 | Region III (Central Luzon) | Bataan | Mariveles | Mt. View | 14.4501 | 120.5779 | U | 13666 | 3796 | 1139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1514 | FTAP Smart | 14.4519 | 120.5791 | 0.24 | Terrestrial Optical Fiber Drop | 0.79 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1546 | 2 | 546 | 1546 | 0103307014 | Region I (Ilocos Region) | La Union | Bauang | Central East | 16.5281 | 120.3336 | U | 4199 | 1134 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 0.34 | Terrestrial Optical Fiber Drop | 0.79 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1547 | 2 | 547 | 1547 | 0306910024 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Norte | 15.6718 | 120.5808 | U | 9205 | 2360 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.06 | Terrestrial Optical Fiber Drop | 0.79 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1548 | 2 | 548 | 1548 | 0330100019 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulung Maragul | 15.1586 | 120.6108 | U | 21592 | 5997 | 1799 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02481 | Edgepoint | 15.1613 | 120.6108 | 0.3 | Terrestrial Optical Fiber Drop | 0.79 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1549 | 2 | 549 | 1549 | 0105533018 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw Magliba | 16.1204 | 120.3934 | R | 1779 | 494 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00403 | Edgepoint | 16.1211 | 120.4056 | 1.3 | Terrestrial Optical Fiber Drop | 0.79 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1550 | 2 | 550 | 1550 | 0702210024 | Region VII (Central Visayas) | Cebu | Barili | Maghanoy | 10.1091 | 123.504 | R | 1456 | 383 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 1.25 | Terrestrial Optical Fiber Drop | 0.79 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1551 | 2 | 551 | 1551 | 1600301024 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Taglatawan | 8.7099 | 125.7503 | U | 12652 | 3244 | 973 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0003 | PTCI/MIDC | 8.7151 | 125.7419 | 1.09 | Terrestrial Optical Fiber Drop | 0.79 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1552 | 2 | 552 | 1552 | 0501716019 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Juan | 13.4226 | 123.423 | R | 4462 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03180 | Edgepoint | 13.428 | 123.4178 | 0.82 | Terrestrial Optical Fiber Drop | 0.79 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1553 | 2 | 553 | 1553 | 0506211006 | Region V (Bicol Region) | Sorsogon | Magallanes | Banacud | 12.8279 | 123.8359 | R | 1168 | 292 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 1.12 | Terrestrial Optical Fiber Drop | 0.8 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1554 | 2 | 554 | 1554 | 0301413022 | Region III (Central Luzon) | Bulacan | Norzagaray | Poblacion | 14.9079 | 121.044 | U | 15956 | 4558 | 1367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030543 | FTAP Globe | 14.9106 | 121.0449 | 0.32 | Terrestrial Optical Fiber Drop | 0.79 | 6.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1555 | 2 | 555 | 1555 | 0403405054 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Jose | 14.2006 | 121.1406 | U | 4452 | 1349 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040256 | FTAP Globe | 14.1944 | 121.147 | 0.57 | Terrestrial Optical Fiber Drop | 0.71 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1556 | 2 | 556 | 1556 | 0402101014 | Region IV-A (CALABARZON) | Cavite | Alfonso | Pajo | 14.1437 | 120.8582 | R | 2316 | 681 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 0.27 | Terrestrial Optical Fiber Drop | 0.8 | 6.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1557 | 2 | 557 | 1557 | 1102411003 | Region XI (Davao Region) | Davao del Sur | Padada | Harada Butai | 6.6364 | 125.3369 | R | 2689 | 790 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.74 | Terrestrial Optical Fiber Drop | 0.79 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1558 | 2 | 558 | 1558 | 0305403009 | Region III (Central Luzon) | Pampanga | Arayat | Guemasan | 15.1476 | 120.7767 | R | 4424 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.71 | Terrestrial Optical Fiber Drop | 0.8 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1559 | 2 | 559 | 1559 | 0307103012 | Region III (Central Luzon) | Zambales | Candelaria | Panayonan | 15.6247 | 119.9364 | R | 1275 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03357-B07 | PTCI/MIDC | 15.6183 | 119.9418 | 0.53 | Terrestrial Optical Fiber Drop | 0.45 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1560 | 2 | 560 | 1560 | 0403413008 | Region IV-A (CALABARZON) | Laguna | Lumban | Maytalang I | 14.2889 | 121.4582 | U | 4369 | 1323 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.58 | Terrestrial Optical Fiber Drop | 0.8 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1561 | 2 | 561 | 1561 | 0402103043 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog IV | 14.423 | 120.9582 | U | 14599 | 4293 | 1288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00594-A03 | PTCI/MIDC | 14.4466 | 120.9981 | 0.57 | Terrestrial Optical Fiber Drop | 0.85 | 2.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1562 | 2 | 562 | 1562 | 0304916017 | Region III (Central Luzon) | Nueva Ecija | Lupao | Namulandayan | 15.8824 | 120.9049 | R | 2243 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01414-B07 | PTCI/MIDC | 15.8805 | 120.8984 | 0.73 | Terrestrial Optical Fiber Drop | 0.8 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1563 | 2 | 563 | 1563 | 0306914001 | Region III (Central Luzon) | Tarlac | San Manuel | Colubot | 15.7903 | 120.6041 | R | 1191 | 305 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 1.25 | Terrestrial Optical Fiber Drop | 0.8 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1564 | 2 | 564 | 1564 | 0402115012 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Estacion | 14.3233 | 120.7644 | U | 5324 | 1565 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02143-C08 | PTCI/MIDC | 14.3258 | 120.7645 | 0.28 | Terrestrial Optical Fiber Drop | 0.8 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1565 | 2 | 565 | 1565 | 1401110016 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Wangal | 16.403 | 120.6044 | U | 6933 | 1980 | 594 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0024 | LDIC | 16.4025 | 120.6048 | 0.07 | Terrestrial Optical Fiber Drop | 0.8 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1566 | 2 | 566 | 1566 | 0300811013 | Region III (Central Luzon) | Bataan | Pilar | Landing | 14.6698 | 120.5513 | R | 1375 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.59 | Terrestrial Optical Fiber Drop | 1.67 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1567 | 2 | 567 | 1567 | 1004313006 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Lumbo | 8.8075 | 124.7969 | R | 2878 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.91 | Terrestrial Optical Fiber Drop | 0.8 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1568 | 2 | 568 | 1568 | 0330100012 | Region III (Central Luzon) | Pampanga | City of Angeles | Lourdes Sur East | 15.1445 | 120.5936 | U | 3800 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.17 | Terrestrial Optical Fiber Drop | 0.81 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1569 | 2 | 569 | 1569 | 0600613001 | Region VI (Western Visayas) | Antique | San Jose | Atabay | 10.7569 | 121.9429 | U | 2287 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAQG0021 | PTCI/MIDC | 10.7615 | 121.9442 | 0.53 | Terrestrial Optical Fiber Drop | 0.81 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1570 | 2 | 570 | 1570 | 0402109006 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion I-A | 14.4269 | 120.9391 | R | 2052 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S3369 | FTAP Smart | 14.4253 | 120.9393 | 0.18 | Terrestrial Optical Fiber Drop | 0.8 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1571 | 2 | 571 | 1571 | 0102805035 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Quiling Norte | 18.0658 | 120.5516 | R | 1551 | 419 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01224-B05 | PTCI/MIDC | 18.0488 | 120.5532 | 0.13 | Terrestrial Optical Fiber Drop | 1.04 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1572 | 2 | 572 | 1572 | 0304923007 | Region III (Central Luzon) | Nueva Ecija | Rizal | Calaocan District | 15.7046 | 121.1077 | R | 3678 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 0.38 | Terrestrial Optical Fiber Drop | 0.81 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1573 | 2 | 573 | 1573 | 0301406003 | Region III (Central Luzon) | Bulacan | Bustos | Buisan | 14.9324 | 120.9281 | R | 1961 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-02275 | Edgepoint | 14.9411 | 120.9418 | 1.84 | Terrestrial Optical Fiber Drop | 1.26 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1574 | 2 | 574 | 1574 | 0403428007 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Ibaba | 14.3023 | 121.1097 | U | 8845 | 2680 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4294 | FTAP Smart | 14.2944 | 121.107 | 0.35 | Terrestrial Optical Fiber Drop | 0.64 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1575 | 2 | 575 | 1575 | 0702246021 | Region VII (Central Visayas) | Cebu | Sibonga | Poblacion | 10.0189 | 123.6146 | U | 7421 | 1952 | 586 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070018 | FTAP BTS | 10.0136 | 123.619 | 0.77 | Terrestrial Optical Fiber Drop | 0.81 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1576 | 2 | 576 | 1576 | 1430300007 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Balsigan | 16.407 | 120.5972 | R | 2506 | 659 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0008 | LDIC | 16.4071 | 120.5887 | 0.12 | Terrestrial Optical Fiber Drop | 0.55 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1577 | 2 | 577 | 1577 | 1004323006 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Mangga | 8.9606 | 124.7825 | R | 1552 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 0.94 | Terrestrial Optical Fiber Drop | 0.81 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1578 | 2 | 578 | 1578 | 0305415010 | Region III (Central Luzon) | Pampanga | Porac | Cangatba | 15.0682 | 120.5429 | U | 3116 | 779 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.28 | Terrestrial Optical Fiber Drop | 0.46 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1579 | 2 | 579 | 1579 | 0105512021 | Region I (Ilocos Region) | Pangasinan | Binalonan | Sta. Maria Norte | 16.0613 | 120.5879 | U | 2783 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02466-B07 | PTCI/MIDC | 16.0505 | 120.5941 | 0.65 | Terrestrial Optical Fiber Drop | 1.91 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1580 | 2 | 580 | 1580 | 0403428009 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Macabling | 14.2986 | 121.0975 | U | 22368 | 6778 | 2033 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0027 | PTCI/MIDC | 14.3001 | 121.0996 | 0.28 | Terrestrial Optical Fiber Drop | 0.81 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1581 | 2 | 581 | 1581 | 0403418001 | Region IV-A (CALABARZON) | Laguna | Paete | Bagumbayan | 14.3661 | 121.482 | U | 6032 | 1827 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1582 | 2 | 582 | 1582 | 0501736013 | Region V (Bicol Region) | Camarines Sur | Tigaon | May-Anao | 13.6248 | 123.5024 | R | 3326 | 791 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 1.25 | Terrestrial Optical Fiber Drop | 0.81 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1583 | 2 | 583 | 1583 | 0304928002 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | La Fuente | 15.4297 | 120.9259 | R | 3386 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0006 | PTCI/MIDC | 15.4304 | 120.9236 | 0.26 | Terrestrial Optical Fiber Drop | 0.03 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1584 | 2 | 584 | 1584 | 0102908015 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | San Juan | 16.9837 | 120.7196 | R | 2189 | 576 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010067 | FTAP Globe | 16.982 | 120.7044 | 1.62 | Terrestrial Optical Fiber Drop | 0.81 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1585 | 2 | 585 | 1585 | 1030900048 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Villa Verde | 8.2345 | 124.2446 | U | 5590 | 1471 | 441 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0009 | PTCI/MIDC | 8.2328 | 124.2427 | 0.28 | Terrestrial Optical Fiber Drop | 0.82 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1586 | 2 | 586 | 1586 | 1403213015 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Gobgob | 17.469 | 121.4314 | R | 2123 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00127 | Edgepoint | 17.4695 | 121.4577 | 2.8 | Terrestrial Optical Fiber Drop | 0.82 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1587 | 2 | 587 | 1587 | 0102908004 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Concepcion | 16.9834 | 120.7197 | R | 2080 | 547 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010067 | FTAP Globe | 16.982 | 120.7044 | 1.63 | Terrestrial Optical Fiber Drop | 0.81 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1588 | 2 | 588 | 1588 | 0730600050 | Region VII (Central Visayas) | Cebu | City of Cebu | Pahina Central | 10.2976 | 123.8924 | U | 5646 | 1764 | 529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0119 | PTCI/MIDC | 10.2993 | 123.8942 | 0.28 | Terrestrial Optical Fiber Drop | 0.81 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1589 | 2 | 589 | 1589 | 0102812068 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 5, San Pedro | 18.2037 | 120.5927 | R | 1404 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00029 | Edgepoint | 18.2009 | 120.5898 | 0.44 | Terrestrial Optical Fiber Drop | 0.81 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1590 | 2 | 590 | 1590 | 0603006008 | Region VI (Western Visayas) | Iloilo | Banate | Bularan | 11.0042 | 122.822 | R | 1084 | 285 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02851-D13 | PTCI/MIDC | 10.9969 | 122.7958 | 2.97 | Terrestrial Optical Fiber Drop | 0.82 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1591 | 2 | 591 | 1591 | 0403413003 | Region IV-A (CALABARZON) | Laguna | Lumban | Balubad | 14.2885 | 121.463 | R | 2336 | 707 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.37 | Terrestrial Optical Fiber Drop | 0.82 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1592 | 2 | 592 | 1592 | 0401018009 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Calingatan | 13.9616 | 121.1212 | R | 3220 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01964-C08 | PTCI/MIDC | 13.9582 | 121.119 | 0.45 | Terrestrial Optical Fiber Drop | 0.82 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1593 | 2 | 593 | 1593 | 0306903021 | Region III (Central Luzon) | Tarlac | Camiling | Cayaoan | 15.6965 | 120.4149 | R | 2360 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.45 | Terrestrial Optical Fiber Drop | 0.82 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1594 | 2 | 594 | 1594 | 1102319024 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo North | 7.4653 | 125.8138 | U | 8739 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110338 | FTAP BTS | 7.4641 | 125.8151 | 0.2 | Terrestrial Optical Fiber Drop | 0.82 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1595 | 2 | 595 | 1595 | 0702207004 | Region VII (Central Visayas) | Cebu | Badian | Basak | 10.29 | 123.8659 | R | 1743 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070008 | FTAP BTS | 10.2831 | 123.8687 | 0.82 | Terrestrial Optical Fiber Drop | 0.82 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1596 | 2 | 596 | 1596 | 0300810004 | Region III (Central Luzon) | Bataan | Orion | Balut | 14.6183 | 120.5772 | R | 1461 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 0.16 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1597 | 2 | 597 | 1597 | 0501737039 | Region V (Bicol Region) | Camarines Sur | Tinambac | Santa Cruz | 13.8129 | 123.3319 | R | 3827 | 911 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-01993 | Edgepoint | 123.3311 | 13.8166 | 0.42 | Terrestrial Optical Fiber Drop | 0.82 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1598 | 2 | 598 | 1598 | 0501732006 | Region V (Bicol Region) | Camarines Sur | San Fernando | Buenavista | 13.5654 | 123.1459 | R | 1561 | 371 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 0.67 | Terrestrial Optical Fiber Drop | 0.82 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1599 | 2 | 599 | 1599 | 0701230029 | Region VII (Central Visayas) | Bohol | Loon | Catagbacan Handig | 9.8227 | 123.8109 | R | 1098 | 274 | 82 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 1.71 | Terrestrial Optical Fiber Drop | 2.41 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1600 | 2 | 600 | 1600 | 0103307016 | Region I (Ilocos Region) | La Union | Bauang | Dili | 16.528 | 120.334 | R | 2249 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 0.38 | Terrestrial Optical Fiber Drop | 0.84 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1601 | 2 | 601 | 1601 | 0600415003 | Region VI (Western Visayas) | Aklan | New Washington | Dumaguit | 11.6008 | 122.4811 | R | 2275 | 583 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-AKL-03154 | Edgepoint | 11.6211 | 122.4683 | 3.98 | Terrestrial Optical Fiber Drop | 7.3 | 5.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1602 | 2 | 602 | 1602 | 0401009021 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 7 | 13.9056 | 121.0483 | U | 2231 | 619 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1603 | 2 | 603 | 1603 | 0105530026 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Poblacion I | 16.1128 | 120.5451 | U | 2203 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.75 | Terrestrial Optical Fiber Drop | 0.47 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1604 | 2 | 604 | 1604 | 0402109043 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma IV | 14.4073 | 120.9358 | U | 2851 | 838 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040129 | FTAP Globe | 14.3884 | 120.9771 | 0.32 | Terrestrial Optical Fiber Drop | 0.52 | 4.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1605 | 2 | 605 | 1605 | 0300804014 | Region III (Central Luzon) | Bataan | Dinalupihan | Kataasan | 14.8713 | 120.4628 | R | 3219 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030571 | FTAP Globe | 14.8719 | 120.4652 | 0.26 | Terrestrial Optical Fiber Drop | 0.82 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1606 | 2 | 606 | 1606 | 1630400054 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Libertad | 8.9485 | 125.5076 | U | 26152 | 6378 | 1913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130044 | FTAP BTS | 8.9443 | 125.5078 | 0.47 | Terrestrial Optical Fiber Drop | 0.82 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1607 | 2 | 607 | 1607 | 1903617010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Beyaba-Damag | 8.0032 | 124.2857 | R | 2789 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH150100 | FTAP Globe | 7.9922 | 124.265 | 1.4 | Terrestrial Optical Fiber Drop | 1.47 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1608 | 2 | 608 | 1608 | 0331400001 | Region III (Central Luzon) | Zambales | City of Olongapo | Asinan | 14.8285 | 120.2864 | U | 3546 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01156 | Edgepoint | 14.8305 | 120.288 | 0.28 | Terrestrial Optical Fiber Drop | 0.82 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1609 | 2 | 609 | 1609 | 1430300022 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | City Camp Central | 16.4076 | 120.5971 | R | 1732 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140183 | FTAP Globe | 16.4206 | 120.5975 | 0.19 | Terrestrial Optical Fiber Drop | 0.62 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1610 | 2 | 610 | 1610 | 0306916048 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maliwalo | 15.4821 | 120.6195 | U | 16799 | 4307 | 1292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00708 | Edgepoint | 15.4836 | 120.623 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1611 | 2 | 611 | 1611 | 0305409008 | Region III (Central Luzon) | Pampanga | Mabalacat City | Dau | 15.182 | 120.5854 | U | 66184 | 16546 | 4964 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02294 | Edgepoint | 15.1821 | 120.5833 | 0.23 | Terrestrial Optical Fiber Drop | 0.83 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1612 | 2 | 612 | 1612 | 1130700116 | Region XI (Davao Region) | Davao del Sur | City of Davao | Talomo | 7.0494 | 125.5463 | U | 64198 | 18881 | 5664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSR0013 | PTCI/MIDC | 7.0507 | 125.541 | 0.6 | Terrestrial Optical Fiber Drop | 0.83 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1613 | 2 | 613 | 1613 | 0504112020 | Region V (Bicol Region) | Masbate | Milagros | Poblacion West | 12.2186 | 123.5021 | R | 4014 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050248 | FTAP Globe | 12.2182 | 123.5128 | 1.16 | Terrestrial Optical Fiber Drop | 0.82 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1614 | 2 | 614 | 1614 | 0301410020 | Region III (Central Luzon) | Bulacan | City of Malolos | Caniogan | 14.8462 | 120.817 | U | 5455 | 1558 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0051 | PTCI/MIDC | 14.8438 | 120.8198 | 0.4 | Terrestrial Optical Fiber Drop | 0.83 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1615 | 2 | 615 | 1615 | 0730600083 | Region VII (Central Visayas) | Cebu | City of Cebu | Tejero | 10.3007 | 123.9066 | U | 14101 | 4406 | 1322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCER0033 | PTCI/MIDC | 10.303 | 123.8978 | 1 | Terrestrial Optical Fiber Drop | 0.82 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1616 | 2 | 616 | 1616 | 0908302023 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Bliss | 7.737 | 123.0571 | R | 3169 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.52 | Terrestrial Optical Fiber Drop | 0.83 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1617 | 2 | 617 | 1617 | 0301410045 | Region III (Central Luzon) | Bulacan | City of Malolos | San Vicente | 14.8421 | 120.826 | U | 2511 | 717 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBUG0051 | PTCI/MIDC | 14.8438 | 120.8198 | 0.46 | Terrestrial Optical Fiber Drop | 1.49 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1618 | 2 | 618 | 1618 | 0306903036 | Region III (Central Luzon) | Tarlac | Camiling | Palimbo Caarosipan | 15.6907 | 120.4076 | R | 3626 | 929 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_TAR_0001 | LDIC | 15.6933 | 120.4118 | 0.54 | Terrestrial Optical Fiber Drop | 0.83 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1619 | 2 | 619 | 1619 | 1401110011 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Pico | 16.4409 | 120.5841 | U | 26490 | 7568 | 2270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0012 | PTCI/MIDC | 16.4413 | 120.5819 | 0.24 | Terrestrial Optical Fiber Drop | 0.83 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1620 | 2 | 620 | 1620 | 0301415005 | Region III (Central Luzon) | Bulacan | Pandi | Bunsuran II | 14.8625 | 120.9362 | U | 3816 | 1090 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00982-B07 | PTCI/MIDC | 14.8912 | 120.9541 | 1.13 | Terrestrial Optical Fiber Drop | 2.31 | 2.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1621 | 2 | 621 | 1621 | 0306916007 | Region III (Central Luzon) | Tarlac | City of Tarlac | Atioc | 15.4245 | 120.5816 | R | 2670 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.36 | Terrestrial Optical Fiber Drop | 2.02 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1622 | 2 | 622 | 1622 | 0803740036 | Region VIII (Eastern Visayas) | Leyte | Palompon | San Isidro | 11.0589 | 124.3843 | U | 3841 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 8.63 | Terrestrial Optical Fiber Drop | 0.83 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1623 | 2 | 623 | 1623 | 0301409015 | Region III (Central Luzon) | Bulacan | Hagonoy | San Pablo | 14.8318 | 120.7516 | U | 3627 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02944-B07 | PTCI/MIDC | 14.8395 | 120.7514 | 0.85 | Terrestrial Optical Fiber Drop | 0.83 | 3.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1624 | 2 | 624 | 1624 | 0402121006 | Region IV-A (CALABARZON) | Cavite | Ternate | San Jose | 14.2906 | 120.717 | R | 2061 | 606 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.75 | Terrestrial Optical Fiber Drop | 0.83 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1625 | 2 | 625 | 1625 | 0603032022 | Region VI (Western Visayas) | Iloilo | New Lucena | Poblacion | 10.8754 | 122.5913 | R | 3184 | 837 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 0.74 | Terrestrial Optical Fiber Drop | 0.83 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1626 | 2 | 626 | 1626 | 0307114013 | Region III (Central Luzon) | Zambales | Subic | Ilwas | 14.8821 | 120.2349 | R | 3097 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-01065 | Edgepoint | 14.8869 | 120.2347 | 0.54 | Terrestrial Optical Fiber Drop | 0.83 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1627 | 2 | 627 | 1627 | 0405607073 | Region IV-A (CALABARZON) | Quezon | Calauag | Santa Maria | 13.9572 | 122.2948 | U | 6195 | 1630 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B42 | FTAP Smart | 13.9539 | 122.3 | 0.67 | Terrestrial Optical Fiber Drop | 0.83 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1628 | 2 | 628 | 1628 | 0300806014 | Region III (Central Luzon) | Bataan | Limay | San Francisco de Asis | 14.5686 | 120.5955 | U | 6571 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030629 | FTAP Globe | 14.568 | 120.5957 | 0.08 | Terrestrial Optical Fiber Drop | 0.83 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1629 | 2 | 629 | 1629 | 0730600038 | Region VII (Central Visayas) | Cebu | City of Cebu | Kinasang-an Pardo | 10.2786 | 123.8563 | U | 18779 | 5868 | 1760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.66 | Terrestrial Optical Fiber Drop | 0.84 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1630 | 2 | 630 | 1630 | 1705209006 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Cacawan | 13.0452 | 121.4824 | U | 6819 | 1748 | 524 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMRG0011 | PTCI/MIDC | 13.0381 | 121.4907 | 1.2 | Terrestrial Optical Fiber Drop | 0.83 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1631 | 2 | 631 | 1631 | 1130700193 | Region XI (Davao Region) | Davao del Sur | City of Davao | Santo Niño | 7.0806 | 125.5056 | U | 21782 | 6406 | 1922 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110484 | FTAP Globe | 7.0774 | 125.5149 | 1.08 | Terrestrial Optical Fiber Drop | 0.84 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1632 | 2 | 632 | 1632 | 0405804003 | Region IV-A (CALABARZON) | Rizal | Binangonan | Bilibiran | 14.4995 | 121.1736 | U | 17784 | 4940 | 1482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0136 | PTCI/MIDC | 14.4981 | 121.1739 | 0.15 | Terrestrial Optical Fiber Drop | 0.84 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1633 | 2 | 633 | 1633 | 0403422016 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Norte | 14.2338 | 121.3662 | R | 2742 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 1.1 | Terrestrial Optical Fiber Drop | 0.36 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1634 | 2 | 634 | 1634 | 0105546036 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Santo Domingo | 15.959 | 120.5666 | U | 3639 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01735-B07 | PTCI/MIDC | 15.956 | 120.5666 | 0.33 | Terrestrial Optical Fiber Drop | 0.83 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1635 | 2 | 635 | 1635 | 0401012005 | Region IV-A (CALABARZON) | Batangas | Lemery | Bagong Sikat | 13.8832 | 120.9153 | R | 1354 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0004 | LDIC | 13.8858 | 120.9194 | 0.53 | Terrestrial Optical Fiber Drop | 0.84 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1636 | 2 | 636 | 1636 | 0331400011 | Region III (Central Luzon) | Zambales | City of Olongapo | Kalaklan | 14.8301 | 120.273 | U | 14962 | 4043 | 1213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.77 | Terrestrial Optical Fiber Drop | 0.84 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1637 | 2 | 637 | 1637 | 0401004008 | Region IV-A (CALABARZON) | Batangas | Balete | Palsara | 14.0111 | 121.1001 | R | 1473 | 409 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 1.87 | Terrestrial Optical Fiber Drop | 0.84 | 6.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1638 | 2 | 638 | 1638 | 0401027010 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Poblacion I | 13.8688 | 120.979 | R | 1780 | 494 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040533 | FTAP Globe | 13.8691 | 120.9761 | 0.75 | Terrestrial Optical Fiber Drop | 1.34 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1639 | 2 | 639 | 1639 | 0304902007 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Digmala | 15.6252 | 121.1543 | R | 1683 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 1.04 | Terrestrial Optical Fiber Drop | 0.84 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1640 | 2 | 640 | 1640 | 0501720002 | Region V (Bicol Region) | Camarines Sur | Magarao | Bell | 13.6605 | 123.175 | R | 2490 | 592 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 1.29 | Terrestrial Optical Fiber Drop | 0.84 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1641 | 2 | 641 | 1641 | 0203132012 | Region II (Cagayan Valley) | Isabela | San Mateo | Marasat Pequeño | 16.9056 | 121.6153 | R | 2302 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01370-B06 | PTCI/MIDC | 16.8794 | 121.5907 | 0.36 | Terrestrial Optical Fiber Drop | 4.14 | 7.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1642 | 2 | 642 | 1642 | 0103309002 | Region I (Ilocos Region) | La Union | Caba | Gana | 16.4364 | 120.3601 | R | 2255 | 609 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LU_0033 | LDIC | 16.4309 | 120.358 | 0.42 | Terrestrial Optical Fiber Drop | 1.6 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1643 | 2 | 643 | 1643 | 0831600094 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 64 | 11.216 | 125.0026 | R | 2198 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0099 | PTCI/MIDC | 11.2145 | 124.9956 | 0.78 | Terrestrial Optical Fiber Drop | 0.84 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1644 | 2 | 644 | 1644 | 0102822004 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Barcelona | 18.1061 | 120.7675 | R | 1426 | 385 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01220-B05 | PTCI/MIDC | 18.0958 | 120.7728 | 1.28 | Terrestrial Optical Fiber Drop | 0.84 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1645 | 2 | 645 | 1645 | 0305411008 | Region III (Central Luzon) | Pampanga | Magalang | San Franciso | 15.2062 | 120.6488 | U | 5250 | 1312 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02259-B07 | PTCI/MIDC | 15.2013 | 120.6406 | 1.03 | Terrestrial Optical Fiber Drop | 0.84 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1646 | 2 | 646 | 1646 | 0603036017 | Region VI (Western Visayas) | Iloilo | Pavia | Tigum | 10.7806 | 122.5481 | R | 2646 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.21 | Terrestrial Optical Fiber Drop | 0.84 | 3.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1647 | 2 | 647 | 1647 | 0300802016 | Region III (Central Luzon) | Bataan | Bagac | Atilano L. Ricardo | 14.606 | 120.4058 | R | 3467 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 3934 | FTAP Smart | 14.6029 | 120.3972 | 0.99 | Terrestrial Optical Fiber Drop | 0.84 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1648 | 2 | 648 | 1648 | 0501707005 | Region V (Bicol Region) | Camarines Sur | Cabusao | Castillo | 13.7334 | 123.115 | U | 5092 | 1212 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050057 | FTAP Globe | 13.7244 | 123.1076 | 1.29 | Terrestrial Optical Fiber Drop | 0.85 | 10.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1649 | 2 | 649 | 1649 | 0401009015 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 1 | 13.8988 | 121.0493 | R | 2058 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.92 | Terrestrial Optical Fiber Drop | 0.06 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1650 | 2 | 650 | 1650 | 1001312053 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Barangay 10 | 8.1517 | 125.1236 | U | 3857 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0056 | PTCI/MIDC | 8.1403 | 125.1175 | 1.44 | Terrestrial Optical Fiber Drop | 0.84 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1651 | 2 | 651 | 1651 | 0307701006 | Region III (Central Luzon) | Aurora | Baler | Buhangin | 15.7666 | 121.5584 | U | 4430 | 1165 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03289-B06 | PTCI/MIDC | 15.7633 | 121.5658 | 0.87 | Terrestrial Optical Fiber Drop | 0.85 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1652 | 2 | 652 | 1652 | 0702219012 | Region VII (Central Visayas) | Cebu | Consolacion | Pitogo | 10.3794 | 123.9659 | U | 4392 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00111-D12 | PTCI/MIDC | 10.3742 | 123.9666 | 0.58 | Terrestrial Optical Fiber Drop | 0.85 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1653 | 2 | 653 | 1653 | 0501701025 | Region V (Bicol Region) | Camarines Sur | Baao | Santa Cruz | 13.453 | 123.3721 | R | 2954 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050118 | FTAP Globe | 13.4568 | 123.3687 | 0.56 | Terrestrial Optical Fiber Drop | 0.85 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1654 | 2 | 654 | 1654 | 0501603028 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay V | 14.1212 | 122.9497 | U | 4639 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0003 | PTCI/MIDC | 14.1236 | 122.9559 | 0.72 | Terrestrial Optical Fiber Drop | 0.85 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1655 | 2 | 655 | 1655 | 0402120028 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya II | 14.3832 | 120.8335 | U | 13139 | 3864 | 1159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 1.19 | Terrestrial Optical Fiber Drop | 1.86 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1656 | 2 | 656 | 1656 | 0402107004 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Castaños Lejos | 14.1817 | 120.7995 | U | 2901 | 853 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.92 | Terrestrial Optical Fiber Drop | 0.4 | 4.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1657 | 2 | 657 | 1657 | 0402116005 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan I | 14.4376 | 120.8853 | R | 3130 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02739-C08 | PTCI/MIDC | 14.4354 | 120.8825 | 0.56 | Terrestrial Optical Fiber Drop | 0.93 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1658 | 2 | 658 | 1658 | 0105545018 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Poblacion | 15.8229 | 120.329 | U | 5276 | 1465 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010217 | FTAP Globe | 15.8239 | 120.3269 | 0.25 | Terrestrial Optical Fiber Drop | 0.85 | 11.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1659 | 2 | 659 | 1659 | 1001321001 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Bagontaas | 7.946 | 125.1027 | U | 14291 | 3760 | 1128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100202 | FTAP Globe | 7.9439 | 125.1039 | 0.27 | Terrestrial Optical Fiber Drop | 0.85 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1660 | 2 | 660 | 1660 | 1903617066 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Basak Malutlut | 8.0026 | 124.2723 | R | 3981 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH150100 | FTAP Globe | 7.9922 | 124.265 | 1.41 | Terrestrial Optical Fiber Drop | 0.85 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1661 | 2 | 661 | 1661 | 0501709002 | Region V (Bicol Region) | Camarines Sur | Camaligan | Marupit | 13.627 | 123.1688 | U | 5025 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.72 | Terrestrial Optical Fiber Drop | 0.85 | 2.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1662 | 2 | 662 | 1662 | 1430300097 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | San Luis Village | 16.4057 | 120.5768 | U | 9032 | 2376 | 713 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0027 | PTCI/MIDC | 16.4083 | 120.5779 | 0.31 | Terrestrial Optical Fiber Drop | 0.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1663 | 2 | 663 | 1663 | 0105533020 | Region I (Ilocos Region) | Pangasinan | San Fabian | Poblacion | 16.123 | 120.4022 | U | 3941 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00403 | Edgepoint | 16.1211 | 120.4056 | 0.42 | Terrestrial Optical Fiber Drop | 0.85 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1664 | 2 | 664 | 1664 | 0702247003 | Region VII (Central Visayas) | Cebu | Sogod | Bagatayam | 10.7596 | 124.0037 | R | 2902 | 763 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 0.83 | Terrestrial Optical Fiber Drop | 0.86 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1665 | 2 | 665 | 1665 | 0301420019 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Assumption | 14.8222 | 121.0581 | R | 4559 | 1302 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-03221 | Edgepoint | 14.8111 | 121.0649 | 0.86 | Terrestrial Optical Fiber Drop | 1.67 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1666 | 2 | 666 | 1666 | 0405620030 | Region IV-A (CALABARZON) | Quezon | Infanta | Miswa | 14.7376 | 121.6547 | R | 2193 | 577 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040007 | FTAP Globe | 14.747 | 121.648 | 1.44 | Satellite LEO Backhaul (Starlink Business) | 1.11 | 40.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1667 | 2 | 667 | 1667 | 0402112013 | Region IV-A (CALABARZON) | Cavite | Magallanes | Urdaneta | 14.165 | 120.7323 | R | 2342 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02186-C08 | PTCI/MIDC | 14.1641 | 120.7306 | 0.22 | Terrestrial Optical Fiber Drop | 0.85 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1668 | 2 | 668 | 1668 | 1004311007 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Lower Jasaan | 8.6571 | 124.7537 | U | 6140 | 1574 | 472 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.33 | Terrestrial Optical Fiber Drop | 0.82 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1669 | 2 | 669 | 1669 | 0401005112 | Region IV-A (CALABARZON) | Batangas | Batangas City | Talumpok Kanluran | 13.7337 | 121.1364 | R | 2986 | 829 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040586 | FTAP Globe | 13.7453 | 121.1393 | 1.32 | Terrestrial Optical Fiber Drop | 0.86 | 7.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1670 | 2 | 670 | 1670 | 1130700161 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 28-C | 7.0868 | 125.6132 | U | 3260 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0136 | PTCI/MIDC | 7.0708 | 125.621 | 0.27 | Terrestrial Optical Fiber Drop | 1.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1671 | 2 | 671 | 1671 | 0403428004 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dila | 14.2895 | 121.1091 | U | 43294 | 13119 | 3936 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4294 | FTAP Smart | 14.2944 | 121.107 | 0.59 | Terrestrial Optical Fiber Drop | 0.85 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1672 | 2 | 672 | 1672 | 0403409003 | Region IV-A (CALABARZON) | Laguna | Kalayaan | San Juan | 14.3248 | 121.4766 | U | 7303 | 2213 | 664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040168 | FTAP Globe | 14.3245 | 121.4782 | 0.17 | Terrestrial Optical Fiber Drop | 0.86 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1673 | 2 | 673 | 1673 | 0806407064 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Tunga-tunga | 10.1314 | 124.8369 | U | 1975 | 481 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.07 | Terrestrial Optical Fiber Drop | 0.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1674 | 2 | 674 | 1674 | 0401029045 | Region IV-A (CALABARZON) | Batangas | Taal | Laguile | 13.8975 | 120.9164 | R | 3320 | 922 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01943-C08 | PTCI/MIDC | 13.8964 | 120.9122 | 0.47 | Terrestrial Optical Fiber Drop | 0.85 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1675 | 2 | 675 | 1675 | 0203126011 | Region II (Cagayan Valley) | Isabela | Roxas | Rizal | 17.1225 | 121.6194 | U | 6490 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0045 | PTCI/MIDC | 17.1242 | 121.6215 | 0.28 | Terrestrial Optical Fiber Drop | 0.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1676 | 2 | 676 | 1676 | 1401111010 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Poblacion | 16.8599 | 120.7904 | R | 2256 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 0.39 | Terrestrial Optical Fiber Drop | 0.86 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1677 | 2 | 677 | 1677 | 0401011017 | Region IV-A (CALABARZON) | Batangas | Laurel | Barangay 2 | 14.0551 | 120.9313 | R | 1705 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 0.77 | Terrestrial Optical Fiber Drop | 0.33 | 4.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1678 | 2 | 678 | 1678 | 0402106024 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Saint Peter I | 14.3199 | 120.9565 | R | 2408 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.55 | Terrestrial Optical Fiber Drop | 1.29 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1679 | 2 | 679 | 1679 | 0403426024 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Central | 14.2854 | 121.4084 | R | 5029 | 1523 | 457 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.64 | Terrestrial Optical Fiber Drop | 0.86 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1680 | 2 | 680 | 1680 | 0603031021 | Region VI (Western Visayas) | Iloilo | Mina | Tolarucan | 10.9333 | 122.5674 | R | 1977 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 1.48 | Terrestrial Optical Fiber Drop | 0.86 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1681 | 2 | 681 | 1681 | 0506205007 | Region V (Bicol Region) | Sorsogon | Casiguran | Colambis | 12.8756 | 124.0212 | R | 1350 | 337 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 1.45 | Terrestrial Optical Fiber Drop | 0.86 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1682 | 2 | 682 | 1682 | 0402120021 | Region IV-A (CALABARZON) | Cavite | Tanza | Sahud Ulan | 14.3776 | 120.8246 | U | 23343 | 6865 | 2060 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040136 | FTAP Globe | 14.3739 | 120.827 | 0.49 | Terrestrial Optical Fiber Drop | 0.87 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1683 | 2 | 683 | 1683 | 0402103075 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote V | 14.4688 | 120.9656 | U | 20125 | 5919 | 1776 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00135-A03 | PTCI/MIDC | 14.4672 | 120.9652 | 0.18 | Terrestrial Optical Fiber Drop | 0.86 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1684 | 2 | 684 | 1684 | 0301417012 | Region III (Central Luzon) | Bulacan | Plaridel | Lumang Bayan | 14.8954 | 120.8544 | U | 5863 | 1675 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02950-B07 | PTCI/MIDC | 14.8952 | 120.852 | 0.26 | Terrestrial Optical Fiber Drop | 0.86 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1685 | 2 | 685 | 1685 | 0506207050 | Region V (Bicol Region) | Sorsogon | Donsol | Tupas | 12.9128 | 123.594 | R | 2017 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050213 | FTAP Globe | 12.9091 | 123.5966 | 0.5 | Terrestrial Optical Fiber Drop | 0.87 | 17.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1686 | 2 | 686 | 1686 | 0402109035 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-B | 14.4049 | 120.9264 | U | 8053 | 2368 | 710 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1120 | FTAP Smart | 14.4377 | 120.9409 | 0.23 | Terrestrial Optical Fiber Drop | 1.55 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1687 | 2 | 687 | 1687 | 0601904031 | Region VI (Western Visayas) | Capiz | Dumarao | Salcedo | 11.2556 | 122.6689 | R | 1734 | 456 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060244 | FTAP Globe | 11.2736 | 122.6783 | 2.26 | Terrestrial Optical Fiber Drop | 0.86 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1688 | 2 | 688 | 1688 | 0402108016 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Navarro | 14.3866 | 120.9036 | U | 50641 | 14894 | 4468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01885-C08 | PTCI/MIDC | 14.3896 | 120.9068 | 0.48 | Terrestrial Optical Fiber Drop | 0.86 | 3.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1689 | 2 | 689 | 1689 | 0405809005 | Region IV-A (CALABARZON) | Rizal | Morong | San Guillermo | 14.5233 | 121.2131 | U | 12213 | 3392 | 1018 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3743 | FTAP Smart | 14.5236 | 121.2155 | 0.26 | Terrestrial Optical Fiber Drop | 0.87 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1690 | 2 | 690 | 1690 | 0402103042 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog III | 14.4231 | 120.9581 | U | 22576 | 6640 | 1992 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040107 | FTAP Globe | 14.424 | 120.9533 | 0.52 | Terrestrial Optical Fiber Drop | 0.86 | 2.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1691 | 2 | 691 | 1691 | 0301422015 | Region III (Central Luzon) | Bulacan | San Rafael | Maronquillo | 14.9664 | 121.0011 | R | 4137 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030507 | FTAP Globe | 15.001 | 120.9731 | 1.4 | Terrestrial Optical Fiber Drop | 4.37 | 8.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1692 | 2 | 692 | 1692 | 0105538027 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tuliao | 16.0123 | 120.3954 | U | 6475 | 1798 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTPNG0005 | PTCI/MIDC | 16.0077 | 120.3999 | 0.71 | Terrestrial Optical Fiber Drop | 0.86 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1693 | 2 | 693 | 1693 | 0500518013 | Region V (Bicol Region) | Albay | Tiwi | Libjo | 13.4626 | 123.6715 | U | 3013 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 1.19 | Terrestrial Optical Fiber Drop | 0.87 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1694 | 2 | 694 | 1694 | 1600201013 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Poblacion 1 | 8.975 | 125.4079 | R | 1543 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 0.37 | Terrestrial Optical Fiber Drop | 1.12 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1695 | 2 | 695 | 1695 | 0730600005 | Region VII (Central Visayas) | Cebu | City of Cebu | Basak Pardo | 10.2909 | 123.8656 | U | 17876 | 5586 | 1676 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CEB_0004 | LDIC | 10.2979 | 123.8697 | 0.9 | Terrestrial Optical Fiber Drop | 0.87 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1696 | 2 | 696 | 1696 | 0603037032 | Region VI (Western Visayas) | Iloilo | Pototan | Lopez Jaena Ward | 10.9406 | 122.6342 | R | 1511 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.71 | Terrestrial Optical Fiber Drop | 0.98 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1697 | 2 | 697 | 1697 | 0105504020 | Region I (Ilocos Region) | Pangasinan | Alcala | San Pedro Ili | 15.8482 | 120.5325 | R | 4184 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00561 | Edgepoint | 15.8477 | 120.5232 | 0.99 | Terrestrial Optical Fiber Drop | 0.87 | 7.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1698 | 2 | 698 | 1698 | 1206312016 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Magsaysay | 6.2153 | 125.0576 | U | 14447 | 4013 | 1204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCG0043 | PTCI/MIDC | 6.215 | 125.0629 | 0.59 | Terrestrial Optical Fiber Drop | 0.86 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1699 | 2 | 699 | 1699 | 0402109053 | Region IV-A (CALABARZON) | Cavite | City of Imus | Buhay na Tubig | 14.4001 | 120.9604 | U | 41067 | 12078 | 3623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q10 | FTAP Smart | 14.3992 | 120.9596 | 0.14 | Terrestrial Optical Fiber Drop | 0.87 | 5.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1700 | 2 | 700 | 1700 | 1600308019 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 5 | 8.5043 | 125.9845 | U | 6068 | 1555 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.7 | Terrestrial Optical Fiber Drop | 1.09 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1701 | 2 | 701 | 1701 | 0301419017 | Region III (Central Luzon) | Bulacan | San Ildefonso | Lapnit | 15.078 | 120.936 | U | 3416 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030477 | FTAP Globe | 15.082 | 120.9387 | 0.53 | Terrestrial Optical Fiber Drop | 0.87 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1702 | 2 | 702 | 1702 | 0603026005 | Region VI (Western Visayas) | Iloilo | Leganes | Cagamutan Sur | 10.8121 | 122.6014 | R | 2022 | 532 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.56 | Terrestrial Optical Fiber Drop | 2.13 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1703 | 2 | 703 | 1703 | 0403413001 | Region IV-A (CALABARZON) | Laguna | Lumban | Bagong Silang | 14.2985 | 121.4613 | R | 3248 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.55 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1704 | 2 | 704 | 1704 | 0907322040 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Jose | 7.8328 | 123.4317 | U | 8371 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0089 | PTCI/MIDC | 7.8352 | 123.422 | 1.1 | Terrestrial Optical Fiber Drop | 0.87 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1705 | 2 | 705 | 1705 | 0403426013 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Patimbao | 14.2724 | 121.4172 | U | 10201 | 3091 | 927 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4291 | FTAP Smart | 14.2707 | 121.4145 | 0.34 | Terrestrial Optical Fiber Drop | 0.87 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1706 | 2 | 706 | 1706 | 0403405039 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 2 | 14.2047 | 121.1585 | U | 11649 | 3530 | 1059 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0010 | LDIC | 14.1974 | 121.1394 | 0.16 | Terrestrial Optical Fiber Drop | 1.57 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1707 | 2 | 707 | 1707 | 0301403016 | Region III (Central Luzon) | Bulacan | Baliuag | Sabang | 14.9653 | 120.9092 | U | 13115 | 3747 | 1124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02325-B07 | PTCI/MIDC | 14.9682 | 120.9088 | 0.32 | Terrestrial Optical Fiber Drop | 0.87 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1708 | 2 | 708 | 1708 | 0702250021 | Region VII (Central Visayas) | Cebu | City of Talisay | Lawaan II | 10.2651 | 123.8316 | U | 7003 | 1842 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 1.28 | Terrestrial Optical Fiber Drop | 1.05 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1709 | 2 | 709 | 1709 | 0702234027 | Region VII (Central Visayas) | Cebu | City of Naga | Tuyan | 10.2299 | 123.7682 | U | 13748 | 3617 | 1085 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0236 | PTCI/MIDC | 10.2326 | 123.7762 | 0.92 | Terrestrial Optical Fiber Drop | 0.85 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1710 | 2 | 710 | 1710 | 0730600053 | Region VII (Central Visayas) | Cebu | City of Cebu | Pardo | 10.2779 | 123.8569 | U | 12030 | 3759 | 1128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.56 | Terrestrial Optical Fiber Drop | 0.87 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1711 | 2 | 711 | 1711 | 0306902013 | Region III (Central Luzon) | Tarlac | Bamban | San Roque | 15.2763 | 120.5662 | U | 12502 | 3205 | 962 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03350-B07 | PTCI/MIDC | 15.2745 | 120.5676 | 0.25 | Terrestrial Optical Fiber Drop | 0.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1712 | 2 | 712 | 1712 | 0401031029 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Natatas | 14.0825 | 121.1192 | U | 5962 | 1656 | 497 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1393 | FTAP Smart | 14.0841 | 121.1253 | 0.68 | Terrestrial Optical Fiber Drop | 0.87 | 3.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1713 | 2 | 713 | 1713 | 1030500052 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Kauswagan | 8.5012 | 124.6309 | U | 40969 | 11380 | 3414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLR0038 | PTCI/MIDC | 8.4984 | 124.6309 | 0.31 | Terrestrial Optical Fiber Drop | 0.88 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1714 | 2 | 714 | 1714 | 0600405015 | Region VI (Western Visayas) | Aklan | Buruanga | Tigum | 11.8555 | 121.8921 | R | 1656 | 424 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.23 | Terrestrial Optical Fiber Drop | 11.86 | 53.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1715 | 2 | 715 | 1715 | 0405608011 | Region IV-A (CALABARZON) | Quezon | Candelaria | Mangilag Sur | 13.9317 | 121.4505 | U | 7544 | 1985 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040455 | FTAP Globe | 13.9315 | 121.4483 | 0.24 | Terrestrial Optical Fiber Drop | 0.87 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1716 | 2 | 716 | 1716 | 0201518012 | Region II (Cagayan Valley) | Cagayan | Pamplona | Masi | 18.457 | 121.339 | R | 2308 | 591 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020007 | FTAP Globe | 18.4653 | 121.3439 | 1.06 | Terrestrial Optical Fiber Drop | 0.88 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1717 | 2 | 717 | 1717 | 0401007037 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Salong | 13.9205 | 120.8168 | U | 5026 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040472 | FTAP Globe | 13.9244 | 120.8212 | 0.65 | Terrestrial Optical Fiber Drop | 0.88 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1718 | 2 | 718 | 1718 | 0403404002 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banaybanay | 14.254 | 121.1309 | U | 37555 | 11380 | 3414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02403-C08 | PTCI/MIDC | 14.2496 | 121.129 | 0.53 | Terrestrial Optical Fiber Drop | 0.88 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1719 | 2 | 719 | 1719 | 0301415002 | Region III (Central Luzon) | Bulacan | Pandi | Bagong Barrio | 14.8921 | 120.9544 | U | 16035 | 4581 | 1374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00982-B07 | PTCI/MIDC | 14.8912 | 120.9541 | 0.1 | Terrestrial Optical Fiber Drop | 0.88 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1720 | 2 | 720 | 1720 | 0300804026 | Region III (Central Luzon) | Bataan | Dinalupihan | Pinulot | 14.8501 | 120.3895 | R | 4758 | 1321 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0008 | PTCI/MIDC | 14.8525 | 120.3875 | 0.35 | Terrestrial Optical Fiber Drop | 0.87 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1721 | 2 | 721 | 1721 | 0731300023 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tabok | 10.3467 | 123.9407 | U | 19506 | 5573 | 1672 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0118 | PTCI/MIDC | 10.3479 | 123.9486 | 0.87 | Terrestrial Optical Fiber Drop | 0.88 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1722 | 2 | 722 | 1722 | 0300804016 | Region III (Central Luzon) | Bataan | Dinalupihan | Luacan | 14.8651 | 120.4486 | U | 6219 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0004 | PTCI/MIDC | 14.8608 | 120.4461 | 0.55 | Terrestrial Optical Fiber Drop | 0.87 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1723 | 2 | 723 | 1723 | 1102412021 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone IV | 6.8335 | 125.4108 | U | 7229 | 2126 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.47 | Terrestrial Optical Fiber Drop | 0.88 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1724 | 2 | 724 | 1724 | 0330100025 | Region III (Central Luzon) | Pampanga | City of Angeles | Sta. Teresita | 15.1496 | 120.5855 | U | 9570 | 2658 | 797 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1109 | FTAP Smart | 15.1503 | 120.6022 | 0.26 | Terrestrial Optical Fiber Drop | 0.74 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1725 | 2 | 725 | 1725 | 0501733009 | Region V (Bicol Region) | Camarines Sur | San Jose | Danlog | 13.6947 | 123.5273 | R | 2087 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 1.45 | Terrestrial Optical Fiber Drop | 0.88 | 3.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1726 | 2 | 726 | 1726 | 0405802013 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dalig | 14.561 | 121.1897 | U | 56096 | 15582 | 4675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040050 | FTAP Globe | 14.5625 | 121.1888 | 0.2 | Terrestrial Optical Fiber Drop | 0.88 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1727 | 2 | 727 | 1727 | 0402101012 | Region IV-A (CALABARZON) | Cavite | Alfonso | Marahan I | 14.1328 | 120.8488 | U | 3251 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 1.34 | Terrestrial Optical Fiber Drop | 0.88 | 4.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1728 | 2 | 728 | 1728 | 0504101004 | Region V (Bicol Region) | Masbate | Aroroy | Bagauma | 12.4752 | 123.3812 | R | 2847 | 694 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.9 | Terrestrial Optical Fiber Drop | 4.36 | 26.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1729 | 2 | 729 | 1729 | 0307104010 | Region III (Central Luzon) | Zambales | Castillejos | San Jose | 14.9374 | 120.1982 | R | 3977 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02717 | Edgepoint | 14.9397 | 120.1927 | 0.64 | Terrestrial Optical Fiber Drop | 0.88 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1730 | 2 | 730 | 1730 | 1600206010 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Crossing | 9.4498 | 125.5748 | U | 3506 | 855 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 5.21 | Terrestrial Optical Fiber Drop | 0.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1731 | 2 | 731 | 1731 | 0401003013 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 8 | 13.9377 | 120.7326 | R | 2170 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6852 | FTAP Smart | 13.9412 | 120.7322 | 0.48 | Terrestrial Optical Fiber Drop | 0.81 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1732 | 2 | 732 | 1732 | 0403402013 | Region IV-A (CALABARZON) | Laguna | Bay | Santo Domingo | 14.1768 | 121.266 | U | 10856 | 3289 | 987 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040274 | FTAP Globe | 14.1747 | 121.2663 | 0.24 | Terrestrial Optical Fiber Drop | 0.88 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1733 | 2 | 733 | 1733 | 0305411010 | Region III (Central Luzon) | Pampanga | Magalang | San Isidro | 15.2325 | 120.6362 | U | 28421 | 7105 | 2132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030433 | FTAP Globe | 15.2267 | 120.6323 | 0.77 | Terrestrial Optical Fiber Drop | 0.89 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1734 | 2 | 734 | 1734 | 0306914012 | Region III (Central Luzon) | Tarlac | San Manuel | San Miguel | 15.8044 | 120.6072 | R | 2552 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02478 | Edgepoint | 15.8041 | 120.6062 | 0.11 | Terrestrial Optical Fiber Drop | 0.89 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1735 | 2 | 735 | 1735 | 0402116006 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael I | 14.4314 | 120.8795 | R | 1316 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.62 | Terrestrial Optical Fiber Drop | 0.43 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1736 | 2 | 736 | 1736 | 0500518003 | Region V (Bicol Region) | Albay | Tiwi | Baybay | 13.4603 | 123.6831 | R | 2408 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 0.37 | Terrestrial Optical Fiber Drop | 0.88 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1737 | 2 | 737 | 1737 | 1403209020 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pinukpuk Junction | 17.6153 | 121.4085 | R | 3147 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00102 | Edgepoint | 17.6007 | 121.4263 | 2.49 | Terrestrial Optical Fiber Drop | 0.88 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1738 | 2 | 738 | 1738 | 1705211008 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Santo Niño | 13.503 | 120.9477 | R | 2744 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170046 | FTAP Globe | 13.5009 | 120.9529 | 0.6 | Terrestrial Optical Fiber Drop | 0.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1739 | 2 | 739 | 1739 | 1731500065 | MIMAROPA Region | Palawan | City of Puerto Princesa | Mandaragat | 9.7473 | 118.738 | U | 10559 | 2853 | 856 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170252 | FTAP Globe | 9.7413 | 118.7357 | 0.71 | Terrestrial Optical Fiber Drop | 0.89 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1740 | 2 | 740 | 1740 | 0105526007 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bateng | 16.0703 | 120.4054 | R | 2912 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02521-B07 | PTCI/MIDC | 16.0657 | 120.4078 | 0.36 | Terrestrial Optical Fiber Drop | 0.43 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1741 | 2 | 741 | 1741 | 0300805008 | Region III (Central Luzon) | Bataan | Hermosa | Culis | 14.8396 | 120.4818 | U | 10782 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1505 | FTAP Smart | 14.8402 | 120.4776 | 0.46 | Terrestrial Optical Fiber Drop | 0.89 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1742 | 2 | 742 | 1742 | 1630400085 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tandang Sora Pob. | 8.9475 | 125.5314 | U | 4147 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0010 | PTCI/MIDC | 8.947 | 125.5334 | 0.23 | Terrestrial Optical Fiber Drop | 0.88 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1743 | 2 | 743 | 1743 | 0330100030 | Region III (Central Luzon) | Pampanga | City of Angeles | Sapalibutad | 15.1588 | 120.6255 | U | 14913 | 4142 | 1243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02978-B07 | PTCI/MIDC | 15.1531 | 120.6213 | 0.78 | Terrestrial Optical Fiber Drop | 0.88 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1744 | 2 | 744 | 1744 | 1403211007 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Liwan West | 17.4925 | 121.5885 | R | 3022 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-02200 | Edgepoint | 17.4717 | 121.5708 | 2.98 | Terrestrial Optical Fiber Drop | 0.89 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1745 | 2 | 745 | 1745 | 0103306006 | Region I (Ilocos Region) | La Union | Bangar | Barraca | 16.8984 | 120.4186 | R | 1358 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.69 | Terrestrial Optical Fiber Drop | 0.89 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1746 | 2 | 746 | 1746 | 0702205035 | Region VII (Central Visayas) | Cebu | Argao | Poblacion | 9.877 | 123.6033 | U | 6145 | 1617 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 0.64 | Terrestrial Optical Fiber Drop | 0.89 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1747 | 2 | 747 | 1747 | 0603037012 | Region VI (Western Visayas) | Iloilo | Pototan | Cau-ayan | 10.9415 | 122.6429 | U | 3091 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 1.21 | Terrestrial Optical Fiber Drop | 0.54 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1748 | 2 | 748 | 1748 | 0731300015 | Region VII (Central Visayas) | Cebu | City of Mandaue | Labogon | 10.3541 | 123.9576 | U | 20487 | 5853 | 1756 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0214 | PTCI/MIDC | 10.352 | 123.9517 | 0.68 | Terrestrial Optical Fiber Drop | 0.89 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1749 | 2 | 749 | 1749 | 1102403030 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 3 | 6.7442 | 125.3591 | U | 18722 | 5506 | 1652 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0070 | PTCI/MIDC | 6.7422 | 125.3619 | 0.38 | Terrestrial Optical Fiber Drop | 0.89 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1750 | 2 | 750 | 1750 | 0305415014 | Region III (Central Luzon) | Pampanga | Porac | Jalung | 15.066 | 120.5347 | U | 5096 | 1274 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.96 | Terrestrial Optical Fiber Drop | 0.89 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1751 | 2 | 751 | 1751 | 0401027016 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Tambo Ilaya | 13.8959 | 120.9743 | R | 1123 | 311 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040537 | FTAP Globe | 13.8612 | 120.965 | 1.58 | Terrestrial Optical Fiber Drop | 2.13 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1752 | 2 | 752 | 1752 | 0300809008 | Region III (Central Luzon) | Bataan | Orani | Kaparangan | 14.7943 | 120.5386 | R | 3108 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030611 | FTAP Globe | 14.7884 | 120.5392 | 0.66 | Terrestrial Optical Fiber Drop | 0.9 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1753 | 2 | 753 | 1753 | 0405619060 | Region IV-A (CALABARZON) | Quezon | Gumaca | Lagyo | 13.9226 | 122.116 | R | 1856 | 488 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-03196 | Edgepoint | 13.921 | 122.1079 | 0.89 | Terrestrial Optical Fiber Drop | 0.89 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1754 | 2 | 754 | 1754 | 0304931010 | Region III (Central Luzon) | Nueva Ecija | Talugtug | Magsaysay | 15.7789 | 120.8056 | R | 1657 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00577 | Edgepoint | 15.779 | 120.8098 | 0.45 | Terrestrial Optical Fiber Drop | 0.89 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1755 | 2 | 755 | 1755 | 0702205026 | Region VII (Central Visayas) | Cebu | Argao | Langtad | 9.8887 | 123.6051 | R | 3494 | 919 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 0.75 | Terrestrial Optical Fiber Drop | 0.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1756 | 2 | 756 | 1756 | 0604532002 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Bagong Silang | 10.6056 | 123.2814 | R | 2903 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02854-D13 | PTCI/MIDC | 10.6776 | 123.3415 | 10.36 | Terrestrial Optical Fiber Drop | 0.89 | 3.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1757 | 2 | 757 | 1757 | 0305402014 | Region III (Central Luzon) | Pampanga | Apalit | Sulipan | 14.9402 | 120.7598 | U | 12406 | 3101 | 930 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030532 | FTAP Globe | 14.9371 | 120.7625 | 0.45 | Terrestrial Optical Fiber Drop | 0.9 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1758 | 2 | 758 | 1758 | 1401110008 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Betag | 16.4496 | 120.595 | U | 9549 | 2728 | 818 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140179 | FTAP Globe | 16.4461 | 120.5914 | 0.72 | Terrestrial Optical Fiber Drop | 0.76 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1759 | 2 | 759 | 1759 | 0704603022 | Region VII (Central Visayas) | Negros Oriental | Bacong | West Poblacion | 9.2472 | 123.2957 | R | 687 | 180 | 54 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 2.85 | Terrestrial Optical Fiber Drop | 0.5 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1760 | 2 | 760 | 1760 | 1600201011 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Matabao | 8.9751 | 125.4219 | U | 5798 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 0.45 | Terrestrial Optical Fiber Drop | 0.85 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1761 | 2 | 761 | 1761 | 0330100024 | Region III (Central Luzon) | Pampanga | City of Angeles | San Nicolas | 15.1494 | 120.5924 | U | 5024 | 1395 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00829 | Edgepoint | 15.1615 | 120.5826 | 0.05 | Terrestrial Optical Fiber Drop | 0.24 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1762 | 2 | 762 | 1762 | 1004322008 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Looc | 8.8492 | 124.7885 | R | 3486 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 0.77 | Terrestrial Optical Fiber Drop | 0.9 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1763 | 2 | 763 | 1763 | 0506203065 | Region V (Bicol Region) | Sorsogon | Bulan | Zone VIII Pob. | 12.6689 | 123.8811 | R | 2226 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.22 | Terrestrial Optical Fiber Drop | 0.9 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1764 | 2 | 764 | 1764 | 0500517005 | Region V (Bicol Region) | Albay | City of Tabaco | Baranghawon | 13.3523 | 123.723 | R | 4803 | 1171 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.29 | Terrestrial Optical Fiber Drop | 0.9 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1765 | 2 | 765 | 1765 | 0630200015 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 2 | 10.6835 | 122.9536 | U | 3407 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060346 | FTAP Globe | 10.6547 | 122.9607 | 0.73 | Terrestrial Optical Fiber Drop | 1.85 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1766 | 2 | 766 | 1766 | 0403423004 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 1 | 14.1129 | 121.3948 | R | 1222 | 339 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.74 | Terrestrial Optical Fiber Drop | 0.35 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1767 | 2 | 767 | 1767 | 0304912017 | Region III (Central Luzon) | Nueva Ecija | Jaen | Pakol | 15.3759 | 120.8657 | R | 1909 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03333-B07 | PTCI/MIDC | 15.384 | 120.8662 | 0.91 | Terrestrial Optical Fiber Drop | 0.9 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1768 | 2 | 768 | 1768 | 0305410001 | Region III (Central Luzon) | Pampanga | Macabebe | Batasan | 14.8918 | 120.7151 | R | 4722 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-01067 | Edgepoint | 14.8851 | 120.7075 | 1.1 | Terrestrial Optical Fiber Drop | 0.9 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1769 | 2 | 769 | 1769 | 0402117020 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa II | 14.4118 | 120.8479 | U | 6185 | 1819 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.41 | Terrestrial Optical Fiber Drop | 2.15 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1770 | 2 | 770 | 1770 | 0305416009 | Region III (Central Luzon) | Pampanga | City of San Fernando | Del Rosario | 15.0685 | 120.6394 | U | 8600 | 2150 | 645 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030479 | FTAP Globe | 15.0731 | 120.6443 | 0.74 | Terrestrial Optical Fiber Drop | 0.91 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1771 | 2 | 771 | 1771 | 0402123018 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Koronel Jose P. Elises | 14.3041 | 121.0076 | R | 4747 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.33 | Terrestrial Optical Fiber Drop | 2.48 | 4.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1772 | 2 | 772 | 1772 | 0702216011 | Region VII (Central Visayas) | Cebu | Catmon | Catmondaan | 10.6858 | 124.0145 | R | 3423 | 900 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070313 | FTAP Globe | 10.674 | 124.0182 | 1.38 | Terrestrial Optical Fiber Drop | 0.91 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1773 | 2 | 773 | 1773 | 0600416002 | Region VI (Western Visayas) | Aklan | Numancia | Aliputos | 11.6993 | 122.335 | R | 2643 | 677 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060024 | FTAP BTS | 11.6775 | 122.3507 | 2.97 | Terrestrial Optical Fiber Drop | 0.9 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1774 | 2 | 774 | 1774 | 0301412009 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Iba | 14.7539 | 120.9818 | U | 9791 | 2797 | 839 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00977-B07 | PTCI/MIDC | 14.7557 | 120.9758 | 0.68 | Terrestrial Optical Fiber Drop | 0.91 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1775 | 2 | 775 | 1775 | 0330100020 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulungbulu | 15.1363 | 120.5945 | U | 13602 | 3778 | 1133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0023 | FTAP Smart | 15.1368 | 120.5909 | 0.39 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1776 | 2 | 776 | 1776 | 0402123016 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Jacinto Lumbreras | 14.2906 | 121.002 | R | 4497 | 1322 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.25 | Terrestrial Optical Fiber Drop | 0.91 | 4.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1777 | 2 | 777 | 1777 | 0304929014 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Hulo | 15.5847 | 120.8813 | R | 2196 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0031 | PTCI/MIDC | 15.5809 | 120.8782 | 0.54 | Terrestrial Optical Fiber Drop | 0.91 | 4.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1778 | 2 | 778 | 1778 | 0304903084 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Vijandre District | 15.4903 | 120.9704 | R | 1195 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N2096 | FTAP Smart | 15.478 | 120.9538 | 0.12 | Terrestrial Optical Fiber Drop | 1.37 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1779 | 2 | 779 | 1779 | 0702220012 | Region VII (Central Visayas) | Cebu | Cordova | Poblacion | 10.2541 | 123.95 | U | 10393 | 2735 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.65 | Terrestrial Optical Fiber Drop | 0.91 | 7.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1780 | 2 | 780 | 1780 | 0402116004 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio I | 14.4185 | 120.8859 | U | 5804 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040102 | FTAP Globe | 14.4342 | 120.8769 | 0.36 | Terrestrial Optical Fiber Drop | 1.27 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1781 | 2 | 781 | 1781 | 0201516030 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | San Jose | 18.2036 | 121.6613 | R | 1613 | 413 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.98 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1782 | 2 | 782 | 1782 | 0402106081 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Victoria Reyes | 14.3186 | 120.9752 | U | 14568 | 4284 | 1285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0032 | PTCI/MIDC | 14.3181 | 120.9773 | 0.23 | Terrestrial Optical Fiber Drop | 0.91 | 2.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1783 | 2 | 783 | 1783 | 0300804048 | Region III (Central Luzon) | Bataan | Dinalupihan | Pentor | 14.8711 | 120.4739 | R | 3429 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0007 | PTCI/MIDC | 14.8692 | 120.4753 | 0.26 | Terrestrial Optical Fiber Drop | 0.91 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1784 | 2 | 784 | 1784 | 0405622015 | Region IV-A (CALABARZON) | Quezon | Lopez | Bocboc | 13.8791 | 122.261 | R | 2482 | 653 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.91 | Terrestrial Optical Fiber Drop | 0.91 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1785 | 2 | 785 | 1785 | 1102411001 | Region XI (Davao Region) | Davao del Sur | Padada | Almendras | 6.6446 | 125.3456 | U | 3910 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110530 | FTAP Globe | 6.6448 | 125.3465 | 0.15 | Terrestrial Optical Fiber Drop | 1.02 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1786 | 2 | 786 | 1786 | 0405801011 | Region IV-A (CALABARZON) | Rizal | Angono | San Roque | 14.5325 | 121.1614 | U | 12209 | 3391 | 1017 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02331-A04 | PTCI/MIDC | 14.5317 | 121.1611 | 0.1 | Terrestrial Optical Fiber Drop | 0.91 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1787 | 2 | 787 | 1787 | 0203118017 | Region II (Cagayan Valley) | Isabela | Delfin Albano | San Antonio | 17.2732 | 121.7916 | R | 3331 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020057 | FTAP Globe | 17.2868 | 121.785 | 1.66 | Terrestrial Optical Fiber Drop | 0.91 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1788 | 2 | 788 | 1788 | 0402109067 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-F | 14.4051 | 120.9261 | R | 1538 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.98 | Terrestrial Optical Fiber Drop | 1.58 | 4.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1789 | 2 | 789 | 1789 | 0301421044 | Region III (Central Luzon) | Bulacan | San Miguel | San Jose | 15.1483 | 120.9816 | U | 4822 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1604 | FTAP Smart | 15.1496 | 120.9781 | 0.41 | Terrestrial Optical Fiber Drop | 0.92 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1790 | 2 | 790 | 1790 | 0403423009 | Region IV-A (CALABARZON) | Laguna | Rizal | Tala | 14.1111 | 121.3914 | R | 2885 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.99 | Terrestrial Optical Fiber Drop | 0.16 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1791 | 2 | 791 | 1791 | 0405622008 | Region IV-A (CALABARZON) | Quezon | Lopez | Talolong | 13.879 | 122.2616 | U | 3786 | 996 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.91 | Terrestrial Optical Fiber Drop | 0.92 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1792 | 2 | 792 | 1792 | 0803703002 | Region VIII (Eastern Visayas) | Leyte | Albuera | Balugo | 10.8876 | 124.7111 | U | 5230 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0005 | PTCI/MIDC | 10.8845 | 124.7097 | 0.38 | Terrestrial Optical Fiber Drop | 0.92 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1793 | 2 | 793 | 1793 | 0304928028 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Isla | 15.4175 | 120.9273 | R | 2736 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1331 | FTAP Smart | 15.4259 | 120.9264 | 0.95 | Terrestrial Optical Fiber Drop | 0.9 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1794 | 2 | 794 | 1794 | 0501724025 | Region V (Bicol Region) | Camarines Sur | City of Naga | Sabang | 13.6203 | 123.1805 | U | 6822 | 1624 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 0.53 | Terrestrial Optical Fiber Drop | 0.91 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1795 | 2 | 795 | 1795 | 0403410022 | Region IV-A (CALABARZON) | Laguna | Liliw | Kanlurang Bukal | 14.1286 | 121.4395 | R | 4848 | 1469 | 441 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02072-C08 | PTCI/MIDC | 14.1295 | 121.4404 | 0.13 | Terrestrial Optical Fiber Drop | 0.92 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1796 | 2 | 796 | 1796 | 0501703032 | Region V (Bicol Region) | Camarines Sur | Bato | Santiago | 13.3519 | 123.371 | R | 3579 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.51 | Terrestrial Optical Fiber Drop | 0.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1797 | 2 | 797 | 1797 | 0301423024 | Region III (Central Luzon) | Bulacan | Santa Maria | Tabing Bakod | 14.8017 | 120.9542 | U | 5655 | 1615 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02211 | Edgepoint | 14.8035 | 120.9555 | 0.25 | Terrestrial Optical Fiber Drop | 0.92 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1798 | 2 | 798 | 1798 | 0305411021 | Region III (Central Luzon) | Pampanga | Magalang | Santa Lucia | 15.2234 | 120.6279 | U | 10263 | 2565 | 770 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00795 | Edgepoint | 15.2244 | 120.63 | 0.25 | Terrestrial Optical Fiber Drop | 0.92 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1799 | 2 | 799 | 1799 | 1003522021 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | San Antonio | 8.0372 | 123.8051 | R | 2335 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 1.74 | Terrestrial Optical Fiber Drop | 0.92 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1800 | 2 | 800 | 1800 | 0105503019 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Palamis | 16.15 | 119.976 | U | 4745 | 1318 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N6719 | FTAP Smart | 16.155 | 119.9806 | 0.75 | Terrestrial Optical Fiber Drop | 0.92 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1801 | 2 | 801 | 1801 | 0304926002 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Abar Ist | 15.7895 | 120.9811 | U | 23122 | 6606 | 1982 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0196 | FTAP Smart | 15.7902 | 120.9765 | 0.49 | Terrestrial Optical Fiber Drop | 0.92 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1802 | 2 | 802 | 1802 | 0304924006 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Maugat | 15.3163 | 120.8585 | U | 5867 | 1676 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03335-B07 | PTCI/MIDC | 15.3157 | 120.8564 | 0.23 | Terrestrial Optical Fiber Drop | 0.92 | 3.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1803 | 2 | 803 | 1803 | 0402106069 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco II | 14.3177 | 120.9523 | R | 3540 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000722 | FTAP Globe | 14.3509 | 121.01 | 0.95 | Terrestrial Optical Fiber Drop | 1.55 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1804 | 2 | 804 | 1804 | 0402103010 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Ligas I | 14.4536 | 120.9686 | U | 5049 | 1485 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH000677 | FTAP Globe | 14.4591 | 120.9704 | 0.64 | Terrestrial Optical Fiber Drop | 0.93 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1805 | 2 | 805 | 1805 | 0306916018 | Region III (Central Luzon) | Tarlac | City of Tarlac | Binauganan | 15.4769 | 120.6045 | U | 6040 | 1548 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.33 | Terrestrial Optical Fiber Drop | 0.92 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1806 | 2 | 806 | 1806 | 0506205026 | Region V (Bicol Region) | Sorsogon | Casiguran | Tulay | 12.8729 | 124.0053 | R | 2328 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 0.35 | Terrestrial Optical Fiber Drop | 0.92 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1807 | 2 | 807 | 1807 | 1130700124 | Region XI (Davao Region) | Davao del Sur | City of Davao | Tibungco | 7.189 | 125.6412 | U | 51647 | 15190 | 4557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110453 | FTAP Globe | 7.1893 | 125.6441 | 0.33 | Terrestrial Optical Fiber Drop | 0.92 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1808 | 2 | 808 | 1808 | 0501730026 | Region V (Bicol Region) | Camarines Sur | Ragay | Panaytayan | 13.8231 | 122.7814 | R | 2321 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03249-C10 | PTCI/MIDC | 13.8167 | 122.7702 | 1.41 | Terrestrial Optical Fiber Drop | 0.92 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1809 | 2 | 809 | 1809 | 0205704017 | Region II (Cagayan Valley) | Quirino | Maddela | Poblacion Norte | 16.3436 | 121.685 | U | 2662 | 682 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0010 | LDIC | 16.3416 | 121.6868 | 0.29 | Terrestrial Optical Fiber Drop | 0.93 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1810 | 2 | 810 | 1810 | 0402116014 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael III | 14.4365 | 120.8783 | U | 6490 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040102 | FTAP Globe | 14.4342 | 120.8769 | 0.3 | Terrestrial Optical Fiber Drop | 0.93 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1811 | 2 | 811 | 1811 | 0702220007 | Region VII (Central Visayas) | Cebu | Cordova | Day-as | 10.2543 | 123.944 | R | 5003 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.25 | Terrestrial Optical Fiber Drop | 0.93 | 7.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1812 | 2 | 812 | 1812 | 0405623009 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 6 | 14.1171 | 121.5498 | R | 1646 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0021 | PTCI/MIDC | 14.1109 | 121.5533 | 0.45 | Terrestrial Optical Fiber Drop | 0.98 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1813 | 2 | 813 | 1813 | 0600407007 | Region VI (Western Visayas) | Aklan | Kalibo | Caano | 11.7054 | 122.3643 | R | 1949 | 499 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.59 | Terrestrial Optical Fiber Drop | 0.93 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1814 | 2 | 814 | 1814 | 0103301044 | Region I (Ilocos Region) | La Union | Agoo | Santa Monica | 16.3225 | 120.3659 | R | 1307 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01404-B05 | PTCI/MIDC | 16.3395 | 120.406 | 0.12 | Terrestrial Optical Fiber Drop | 0.3 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1815 | 2 | 815 | 1815 | 0731300005 | Region VII (Central Visayas) | Cebu | City of Mandaue | Cabancalan | 10.3482 | 123.9254 | U | 14856 | 4244 | 1273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070334 | FTAP Globe | 10.3495 | 123.929 | 0.42 | Terrestrial Optical Fiber Drop | 0.93 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1816 | 2 | 816 | 1816 | 0103307027 | Region I (Ilocos Region) | La Union | Bauang | Payocpoc Norte Oeste | 16.5279 | 120.3341 | R | 2015 | 544 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00315 | Edgepoint | 16.5247 | 120.3269 | 0.41 | Terrestrial Optical Fiber Drop | 0.85 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1817 | 2 | 817 | 1817 | 0304912029 | Region III (Central Luzon) | Nueva Ecija | Jaen | Sapang | 15.324 | 120.9057 | R | 4479 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030415 | FTAP Globe | 15.3266 | 120.9075 | 0.35 | Terrestrial Optical Fiber Drop | 0.93 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1818 | 2 | 818 | 1818 | 0401026020 | Region IV-A (CALABARZON) | Batangas | San Pascual | Poblacion | 13.7867 | 121.0259 | U | 11379 | 3160 | 948 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01939-C08 | PTCI/MIDC | 13.7844 | 121.0323 | 0.74 | Terrestrial Optical Fiber Drop | 0.93 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1819 | 2 | 819 | 1819 | 0330100036 | Region III (Central Luzon) | Pampanga | City of Angeles | Ninoy Aquino | 15.1512 | 120.6007 | U | 11840 | 3288 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1109 | FTAP Smart | 15.1503 | 120.6022 | 0.19 | Terrestrial Optical Fiber Drop | 0.93 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1820 | 2 | 820 | 1820 | 1401110009 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Cruz | 16.4497 | 120.5947 | R | 3493 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1845 | FTAP Smart | 16.4542 | 120.5894 | 0.39 | Terrestrial Optical Fiber Drop | 0.73 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1821 | 2 | 821 | 1821 | 0908302017 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Poblacion | 7.7276 | 123.0632 | U | 7772 | 1850 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.96 | Terrestrial Optical Fiber Drop | 0.93 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1822 | 2 | 822 | 1822 | 0501603025 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay II | 14.1062 | 122.9535 | R | 2919 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCNG0009 | PTCI/MIDC | 14.1084 | 122.9523 | 0.28 | Terrestrial Optical Fiber Drop | 0.93 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1823 | 2 | 823 | 1823 | 0103311030 | Region I (Ilocos Region) | La Union | Naguilian | Ortiz | 16.5325 | 120.3916 | U | 2793 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 0.45 | Terrestrial Optical Fiber Drop | 0.93 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1824 | 2 | 824 | 1824 | 0301419021 | Region III (Central Luzon) | Bulacan | San Ildefonso | Matimbubong | 15.0659 | 120.9453 | R | 2933 | 838 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01093-B07 | PTCI/MIDC | 15.0639 | 120.9444 | 0.24 | Terrestrial Optical Fiber Drop | 0.93 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1825 | 2 | 825 | 1825 | 0402123017 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Kapitan Kua | 14.304 | 121.0077 | R | 3595 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCAG0044 | PTCI/MIDC | 14.3102 | 121.0334 | 0.28 | Terrestrial Optical Fiber Drop | 2.47 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1826 | 2 | 826 | 1826 | 0600407003 | Region VI (Western Visayas) | Aklan | Kalibo | Bachaw Sur | 11.7261 | 122.3685 | R | 3705 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0005 | PTCI/MIDC | 11.6975 | 122.3768 | 0.73 | Terrestrial Optical Fiber Drop | 3.19 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1827 | 2 | 827 | 1827 | 0402116013 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan II | 14.4377 | 120.8852 | R | 3488 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0042 | PTCI/MIDC | 14.4397 | 120.8833 | 0.3 | Terrestrial Optical Fiber Drop | 0.94 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1828 | 2 | 828 | 1828 | 0201510018 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Gang-ngo | 18.2646 | 121.6877 | R | 1571 | 402 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020014 | FTAP Globe | 18.2526 | 121.6864 | 0.96 | Terrestrial Optical Fiber Drop | 0.44 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1829 | 2 | 829 | 1829 | 0403419009 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Magdapio | 14.2744 | 121.4589 | R | 2560 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.45 | Terrestrial Optical Fiber Drop | 0.93 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1830 | 2 | 830 | 1830 | 0105515021 | Region I (Ilocos Region) | Pangasinan | Bugallon | Salomague Sur | 15.91 | 120.2278 | U | 3352 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01747-B07 | PTCI/MIDC | 15.9191 | 120.2262 | 1.03 | Terrestrial Optical Fiber Drop | 0.94 | 11.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1831 | 2 | 831 | 1831 | 0103311017 | Region I (Ilocos Region) | La Union | Naguilian | Dal-lipaoen | 16.5307 | 120.3955 | R | 1799 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 1.71 | Terrestrial Optical Fiber Drop | 0.47 | 4.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1832 | 2 | 832 | 1832 | 0304924001 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Buliran | 15.2706 | 120.8646 | R | 5048 | 1442 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-02448 | Edgepoint | 15.261 | 120.8642 | 1.07 | Terrestrial Optical Fiber Drop | 0.94 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1833 | 2 | 833 | 1833 | 0304916022 | Region III (Central Luzon) | Nueva Ecija | Lupao | Poblacion South | 15.8764 | 120.8988 | R | 1853 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 0.43 | Terrestrial Optical Fiber Drop | 0.94 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1834 | 2 | 834 | 1834 | 1102507028 | Region XI (Davao Region) | Davao Oriental | Lupon | Poblacion | 6.8879 | 126.0134 | U | 17775 | 4937 | 1481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110325 | FTAP BTS | 6.8905 | 126.021 | 0.88 | Terrestrial Optical Fiber Drop | 0.94 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1835 | 2 | 835 | 1835 | 0402120034 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya II | 14.3967 | 120.8535 | U | 7228 | 2125 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02478-C08 | PTCI/MIDC | 14.3915 | 120.8482 | 0.81 | Terrestrial Optical Fiber Drop | 0.94 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1836 | 2 | 836 | 1836 | 0600403012 | Region VI (Western Visayas) | Aklan | Banga | Libas | 11.6237 | 122.3451 | R | 1667 | 427 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 2.01 | Terrestrial Optical Fiber Drop | 0.94 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1837 | 2 | 837 | 1837 | 0803739018 | Region VIII (Eastern Visayas) | Leyte | Palo | Naga-naga | 11.1539 | 124.9928 | R | 2731 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.29 | Terrestrial Optical Fiber Drop | 0.94 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1838 | 2 | 838 | 1838 | 0305415032 | Region III (Central Luzon) | Pampanga | Porac | Sepung Bulaon | 15.0684 | 120.5426 | U | 5932 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.53 | Terrestrial Optical Fiber Drop | 0.48 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1839 | 2 | 839 | 1839 | 0401009012 | Region IV-A (CALABARZON) | Batangas | Cuenca | Pinagkaisahan | 13.9062 | 121.0525 | R | 2020 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.48 | Terrestrial Optical Fiber Drop | 0.94 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1840 | 2 | 840 | 1840 | 0731300026 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tipolo | 10.3323 | 123.9275 | U | 15806 | 4516 | 1355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0205 | PTCI/MIDC | 10.3298 | 123.9314 | 0.51 | Terrestrial Optical Fiber Drop | 0.95 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1841 | 2 | 841 | 1841 | 0402109061 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang I-F | 14.4022 | 120.9406 | U | 11100 | 3264 | 979 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040148 | FTAP Globe | 14.3495 | 120.9381 | 0.76 | Terrestrial Optical Fiber Drop | 0.53 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1842 | 2 | 842 | 1842 | 0205005024 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Luyang | 16.4962 | 121.1463 | R | 1690 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNVG0016 | PTCI/MIDC | 16.5005 | 121.1392 | 0.9 | Terrestrial Optical Fiber Drop | 0.95 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1843 | 2 | 843 | 1843 | 1600307006 | Region XIII (Caraga) | Agusan del Sur | Rosario | Poblacion | 8.3826 | 125.9982 | U | 5440 | 1394 | 418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130096 | FTAP Globe | 8.3847 | 126.002 | 0.48 | Terrestrial Optical Fiber Drop | 0.95 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1844 | 2 | 844 | 1844 | 0402103004 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Bayanan | 14.4254 | 120.9746 | U | 11757 | 3457 | 1037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01864-C08 | PTCI/MIDC | 14.4276 | 120.9749 | 0.24 | Terrestrial Optical Fiber Drop | 0.94 | 2.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1845 | 2 | 845 | 1845 | 0501716016 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Francisco | 13.4132 | 123.4118 | U | 6423 | 1529 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02059 | Edgepoint | 123.406 | 13.4185 | 0.87 | Terrestrial Optical Fiber Drop | 0.95 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1846 | 2 | 846 | 1846 | 0504117027 | Region V (Bicol Region) | Masbate | Placer | Poblacion | 11.8689 | 123.9184 | R | 2305 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MAS-02172 | Edgepoint | 11.871 | 123.9194 | 0.26 | Satellite LEO Backhaul (Starlink Business) | 0.94 | 41.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1847 | 2 | 847 | 1847 | 0405806014 | Region IV-A (CALABARZON) | Rizal | Cardona | Looc | 14.4797 | 121.2237 | U | 9929 | 2758 | 827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01885 | Edgepoint | 14.4811 | 121.2241 | 0.17 | Terrestrial Optical Fiber Drop | 0.94 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1848 | 2 | 848 | 1848 | 0401030011 | Region IV-A (CALABARZON) | Batangas | Talisay | Poblacion Barangay 1 | 14.095 | 121.0216 | R | 2088 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040323 | FTAP Globe | 14.0965 | 121.0212 | 0.45 | Terrestrial Optical Fiber Drop | 0.41 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1849 | 2 | 849 | 1849 | 0403413011 | Region IV-A (CALABARZON) | Laguna | Lumban | Primera Pulo | 14.2987 | 121.4617 | R | 2306 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.5 | Terrestrial Optical Fiber Drop | 0.35 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1850 | 2 | 850 | 1850 | 0301420054 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz II | 14.8559 | 121.0516 | R | 3559 | 1016 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01066-B07 | PTCI/MIDC | 14.8065 | 121.0228 | 0.14 | Terrestrial Optical Fiber Drop | 2.2 | 5.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1851 | 2 | 851 | 1851 | 1430300135 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Dominican Hill-Mirador | 16.4066 | 120.5833 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0007 | LDIC | 16.4062 | 120.5863 | 0.32 | Terrestrial Optical Fiber Drop | 0.95 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1852 | 2 | 852 | 1852 | 0603037006 | Region VI (Western Visayas) | Iloilo | Pototan | Bongco | 10.9407 | 122.6339 | R | 1802 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.57 | Terrestrial Optical Fiber Drop | 1 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1853 | 2 | 853 | 1853 | 0402121008 | Region IV-A (CALABARZON) | Cavite | Ternate | Sapang I | 14.2827 | 120.7101 | U | 7797 | 2293 | 688 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.4 | Terrestrial Optical Fiber Drop | 0.94 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1854 | 2 | 854 | 1854 | 0402109044 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma V | 14.4131 | 120.9345 | R | 4905 | 1442 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03245-C08 | PTCI/MIDC | 14.4097 | 120.9383 | 0.55 | Terrestrial Optical Fiber Drop | 0.95 | 3.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1855 | 2 | 855 | 1855 | 0301420033 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc East | 14.7994 | 121.0612 | U | 5619 | 1605 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01019-B07 | PTCI/MIDC | 14.8383 | 121.0824 | 0.2 | Terrestrial Optical Fiber Drop | 0.98 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1856 | 2 | 856 | 1856 | 0305413043 | Region III (Central Luzon) | Pampanga | Mexico | Santo Rosario | 15.0702 | 120.7241 | U | 4417 | 1104 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030482 | FTAP Globe | 15.0664 | 120.7233 | 0.43 | Terrestrial Optical Fiber Drop | 0.94 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1857 | 2 | 857 | 1857 | 0401010009 | Region IV-A (CALABARZON) | Batangas | Ibaan | Lucsuhin | 13.8291 | 121.1359 | R | 1775 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02240-C08 | PTCI/MIDC | 14.096 | 120.881 | 0.37 | Terrestrial Optical Fiber Drop | 1.67 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1858 | 2 | 858 | 1858 | 0401014048 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 7 | 13.9374 | 121.1612 | U | 4742 | 1317 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1300 | FTAP Smart | 13.9384 | 121.1622 | 0.16 | Terrestrial Optical Fiber Drop | 0.95 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1859 | 2 | 859 | 1859 | 0301410016 | Region III (Central Luzon) | Bulacan | City of Malolos | Caingin | 14.8442 | 120.8045 | U | 7681 | 2194 | 658 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01139 | Edgepoint | 14.8407 | 120.8008 | 0.55 | Terrestrial Optical Fiber Drop | 0.94 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1860 | 2 | 860 | 1860 | 0501603031 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VIII | 14.1143 | 122.9625 | U | 2819 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03029-C10 | PTCI/MIDC | 14.1154 | 122.961 | 0.2 | Terrestrial Optical Fiber Drop | 0.94 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1861 | 2 | 861 | 1861 | 1606724005 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Serna | 9.7835 | 125.4987 | R | 1800 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0011 | PTCI/MIDC | 9.7878 | 125.4925 | 0.73 | Terrestrial Optical Fiber Drop | 0.66 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1862 | 2 | 862 | 1862 | 0105511046 | Region I (Ilocos Region) | Pangasinan | Bayambang | Mangayao | 15.7968 | 120.4394 | R | 1277 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00570 | Edgepoint | 15.8173 | 120.45 | 0.4 | Terrestrial Optical Fiber Drop | 2.73 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1863 | 2 | 863 | 1863 | 1204704041 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Magsaysay | 7.0122 | 125.0799 | U | 4720 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNCG0011 | PTCI/MIDC | 7.0064 | 125.0798 | 0.64 | Terrestrial Optical Fiber Drop | 0.95 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1864 | 2 | 864 | 1864 | 0305409006 | Region III (Central Luzon) | Pampanga | Mabalacat City | Camachiles | 15.1929 | 120.5857 | U | 13860 | 3465 | 1040 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01553-B07 | PTCI/MIDC | 15.1914 | 120.5809 | 0.55 | Terrestrial Optical Fiber Drop | 0.95 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1865 | 2 | 865 | 1865 | 0103307032 | Region I (Ilocos Region) | La Union | Bauang | Pugo | 16.5274 | 120.3223 | R | 3328 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00315 | Edgepoint | 16.5247 | 120.3269 | 0.58 | Terrestrial Optical Fiber Drop | 0.95 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1866 | 2 | 866 | 1866 | 0331400012 | Region III (Central Luzon) | Zambales | City of Olongapo | New Kalalake | 14.8305 | 120.2891 | U | 10477 | 2831 | 849 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01156 | Edgepoint | 14.8305 | 120.288 | 0.12 | Terrestrial Optical Fiber Drop | 0.95 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1867 | 2 | 867 | 1867 | 1903617008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Banggolo Poblacion | 8.0033 | 124.2913 | R | 3754 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLSG0004 | PTCI/MIDC | 8.0153 | 124.2885 | 1.33 | Terrestrial Optical Fiber Drop | 2.02 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1868 | 2 | 868 | 1868 | 0201517031 | Region II (Cagayan Valley) | Cagayan | Lasam | Centro II | 18.0638 | 121.5999 | R | 2186 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02351-B06 | PTCI/MIDC | 18.0609 | 121.5987 | 0.35 | Terrestrial Optical Fiber Drop | 0.95 | 4.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1869 | 2 | 869 | 1869 | 1130700079 | Region XI (Davao Region) | Davao del Sur | City of Davao | Mintal | 7.0936 | 125.4999 | U | 19434 | 5715 | 1715 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0005 | LDIC | 7.0922 | 125.4988 | 0.2 | Terrestrial Optical Fiber Drop | 0.95 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1870 | 2 | 870 | 1870 | 0402113025 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pinagsanhan I B | 14.2713 | 120.7297 | R | 4060 | 1194 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.92 | Terrestrial Optical Fiber Drop | 0.95 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1871 | 2 | 871 | 1871 | 0907322041 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Pedro | 7.8237 | 123.4441 | U | 8496 | 2178 | 653 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 0.46 | Terrestrial Optical Fiber Drop | 0.96 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1872 | 2 | 872 | 1872 | 0102903003 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Balaleng | 17.5867 | 120.385 | U | 3074 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02461-B05 | PTCI/MIDC | 17.5829 | 120.3867 | 0.46 | Terrestrial Optical Fiber Drop | 0.96 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1873 | 2 | 873 | 1873 | 0105538005 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Botao | 15.975 | 120.4588 | R | 3428 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010177 | FTAP Globe | 15.9751 | 120.4633 | 0.48 | Terrestrial Optical Fiber Drop | 0.96 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1874 | 2 | 874 | 1874 | 0501734032 | Region V (Bicol Region) | Camarines Sur | Sipocot | North Villazar | 13.8629 | 122.9497 | R | 1629 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 0.6 | Terrestrial Optical Fiber Drop | 0.96 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1875 | 2 | 875 | 1875 | 0203137005 | Region II (Cagayan Valley) | Isabela | Tumauini | Arcon | 17.2754 | 121.8238 | R | 2264 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02341-B06 | PTCI/MIDC | 17.2758 | 121.8225 | 0.15 | Terrestrial Optical Fiber Drop | 0.95 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1876 | 2 | 876 | 1876 | 0401010017 | Region IV-A (CALABARZON) | Batangas | Ibaan | Poblacion | 13.8227 | 121.1338 | U | 2316 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 0.28 | Terrestrial Optical Fiber Drop | 0.96 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1877 | 2 | 877 | 1877 | 0304902020 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Rizal | 15.629 | 121.1392 | R | 3481 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.63 | Terrestrial Optical Fiber Drop | 0.96 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1878 | 2 | 878 | 1878 | 0402103035 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Ligas II | 14.4417 | 120.9715 | U | 5296 | 1557 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0095 | FTAP Smart | 14.4464 | 120.9456 | 0.76 | Terrestrial Optical Fiber Drop | 2 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1879 | 2 | 879 | 1879 | 0330100002 | Region III (Central Luzon) | Pampanga | City of Angeles | Anunas | 15.1555 | 120.5553 | U | 27219 | 7560 | 2268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00833 | Edgepoint | 15.1553 | 120.5521 | 0.34 | Terrestrial Optical Fiber Drop | 0.96 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1880 | 2 | 880 | 1880 | 0405804035 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tatala | 14.4829 | 121.205 | U | 15462 | 4295 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00773-A04 | PTCI/MIDC | 14.4837 | 121.2042 | 0.13 | Terrestrial Optical Fiber Drop | 0.96 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1881 | 2 | 881 | 1881 | 0305408034 | Region III (Central Luzon) | Pampanga | Lubao | Santa Cruz | 14.9104 | 120.5627 | U | 18780 | 4695 | 1409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-01043 | Edgepoint | 14.9083 | 120.5583 | 0.53 | Terrestrial Optical Fiber Drop | 0.96 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1882 | 2 | 882 | 1882 | 0102822010 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Laureta | 18.0912 | 120.7697 | R | 1471 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00044 | Edgepoint | 18.0904 | 120.7705 | 0.11 | Terrestrial Optical Fiber Drop | 0.96 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1883 | 2 | 883 | 1883 | 0402109046 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VII | 14.4074 | 120.9362 | U | 4350 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01919-C08 | PTCI/MIDC | 14.4412 | 120.9522 | 0.45 | Terrestrial Optical Fiber Drop | 0.48 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1884 | 2 | 884 | 1884 | 0102820014 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Lucas | 18.153 | 120.5956 | R | 1299 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.88 | Terrestrial Optical Fiber Drop | 1.94 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1885 | 2 | 885 | 1885 | 0403425008 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Magsaysay | 14.3391 | 121.0332 | U | 14023 | 4249 | 1275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.63 | Terrestrial Optical Fiber Drop | 0.96 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1886 | 2 | 886 | 1886 | 0405603005 | Region IV-A (CALABARZON) | Quezon | Atimonan | Barangay Zone 2 | 14.0011 | 121.9165 | U | 2700 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 0.9 | Terrestrial Optical Fiber Drop | 0.96 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1887 | 2 | 887 | 1887 | 0304929006 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Cabugao | 15.5848 | 120.8747 | R | 2661 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0031 | PTCI/MIDC | 15.5809 | 120.8782 | 0.58 | Terrestrial Optical Fiber Drop | 0.96 | 4.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1888 | 2 | 888 | 1888 | 0403428001 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Aplaya | 14.318 | 121.1211 | U | 17383 | 5267 | 1580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01994-C08 | PTCI/MIDC | 14.3131 | 121.1213 | 0.54 | Terrestrial Optical Fiber Drop | 0.97 | 2.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1889 | 2 | 889 | 1889 | 0603043004 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Balabag | 10.776 | 122.5033 | R | 3784 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0072 | PTCI/MIDC | 10.8243 | 122.5364 | 0.76 | Terrestrial Optical Fiber Drop | 4.35 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1890 | 2 | 890 | 1890 | 1606701001 | Region XIII (Caraga) | Surigao del Norte | Alegria | Poblacion | 9.4662 | 125.5743 | R | 1927 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 3.43 | Terrestrial Optical Fiber Drop | 0.97 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1891 | 2 | 891 | 1891 | 0907322046 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Tuburan | 7.8365 | 123.4459 | U | 9989 | 2561 | 768 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090131 | FTAP Globe | 7.8452 | 123.4458 | 0.97 | Terrestrial Optical Fiber Drop | 0.96 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1892 | 2 | 892 | 1892 | 0500508033 | Region V (Bicol Region) | Albay | City of Ligao | Nabonton | 13.2522 | 123.5911 | R | 2858 | 697 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.59 | Terrestrial Optical Fiber Drop | 0.96 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1893 | 2 | 893 | 1893 | 0403411008 | Region IV-A (CALABARZON) | Laguna | Los Baños | Maahas | 14.1774 | 121.2511 | U | 9630 | 2918 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.67 | Terrestrial Optical Fiber Drop | 0.96 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1894 | 2 | 894 | 1894 | 0301412006 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Calvario | 14.7335 | 120.961 | U | 5304 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01106-B07 | PTCI/MIDC | 14.7353 | 120.9581 | 0.37 | Terrestrial Optical Fiber Drop | 0.96 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1895 | 2 | 895 | 1895 | 0603044003 | Region VI (Western Visayas) | Iloilo | Sara | Alibayog | 11.2533 | 123.0083 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.84 | Terrestrial Optical Fiber Drop | 0.96 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1896 | 2 | 896 | 1896 | 0304925006 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Poblacion | 15.307 | 120.905 | U | 8135 | 2324 | 697 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02257 | Edgepoint | 15.3113 | 120.9036 | 0.5 | Terrestrial Optical Fiber Drop | 0.45 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1897 | 2 | 897 | 1897 | 0702232002 | Region VII (Central Visayas) | Cebu | Minglanilla | Calajo-an | 10.2397 | 123.8028 | U | 13251 | 3487 | 1046 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0128 | PTCI/MIDC | 10.2407 | 123.8002 | 0.31 | Terrestrial Optical Fiber Drop | 0.97 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1898 | 2 | 898 | 1898 | 0102803017 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Lacuben | 17.9309 | 120.4762 | R | 1729 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4944 | FTAP Smart | 17.9248 | 120.4771 | 0.68 | Terrestrial Optical Fiber Drop | 0.97 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1899 | 2 | 899 | 1899 | 0506209025 | Region V (Bicol Region) | Sorsogon | Irosin | San Pedro | 12.7016 | 124.0267 | R | 3332 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 1.1 | Terrestrial Optical Fiber Drop | 0.97 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1900 | 2 | 900 | 1900 | 1705215031 | MIMAROPA Region | Oriental Mindoro | Victoria | San Isidro | 13.1604 | 121.2851 | R | 2054 | 526 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170084 | FTAP Globe | 13.1757 | 121.2767 | 1.93 | Terrestrial Optical Fiber Drop | 0.97 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1901 | 2 | 901 | 1901 | 0301403026 | Region III (Central Luzon) | Bulacan | Baliuag | Tiaong | 14.9442 | 120.8961 | U | 6126 | 1750 | 525 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00966-B07 | PTCI/MIDC | 14.9475 | 120.8906 | 0.69 | Terrestrial Optical Fiber Drop | 0.97 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1902 | 2 | 902 | 1902 | 0501724031 | Region V (Bicol Region) | Camarines Sur | City of Naga | Tinago | 13.6256 | 123.1908 | U | 2897 | 689 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0001 | PTCI/MIDC | 13.6235 | 123.1923 | 0.28 | Terrestrial Optical Fiber Drop | 0.97 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1903 | 2 | 903 | 1903 | 0105522028 | Region I (Ilocos Region) | Pangasinan | Lingayen | Poblacion | 16.0316 | 120.231 | U | 12958 | 3599 | 1080 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010153 | FTAP Globe | 16.0313 | 120.2316 | 0.08 | Terrestrial Optical Fiber Drop | 0.97 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1904 | 2 | 904 | 1904 | 0401005097 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Rita Karsada | 13.7783 | 121.0411 | U | 20924 | 5812 | 1744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03083-C08 | PTCI/MIDC | 13.7803 | 121.0482 | 0.8 | Terrestrial Optical Fiber Drop | 0.97 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1905 | 2 | 905 | 1905 | 0603044026 | Region VI (Western Visayas) | Iloilo | Sara | Labigan | 11.2468 | 123.0188 | R | 1376 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILO_0004 | LDIC | 11.2454 | 123.022 | 0.39 | Terrestrial Optical Fiber Drop | 0.97 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1906 | 2 | 906 | 1906 | 0402106028 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Esteban | 14.3204 | 120.9564 | R | 4825 | 1419 | 426 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0023 | PTCI/MIDC | 14.2938 | 120.9461 | 0.59 | Terrestrial Optical Fiber Drop | 1.34 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1907 | 2 | 907 | 1907 | 0500516003 | Region V (Bicol Region) | Albay | Santo Domingo | Calayucay | 13.2381 | 123.786 | R | 1788 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050154 | FTAP Globe | 13.2479 | 123.7822 | 1.16 | Terrestrial Optical Fiber Drop | 0.97 | 0.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1908 | 2 | 908 | 1908 | 1004321008 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Luyongbonbon | 8.5281 | 124.5707 | U | 3274 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0044 | PTCI/MIDC | 8.5331 | 124.5712 | 0.56 | Terrestrial Optical Fiber Drop | 0.98 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1909 | 2 | 909 | 1909 | 0102820016 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Miguel | 18.1708 | 120.6026 | R | 1725 | 466 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.86 | Terrestrial Optical Fiber Drop | 0.97 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1910 | 2 | 910 | 1910 | 1030500049 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Gusa | 8.4764 | 124.6828 | U | 29500 | 8194 | 2458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0018 | PTCI/MIDC | 8.4727 | 124.6825 | 0.4 | Terrestrial Optical Fiber Drop | 0.97 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1911 | 2 | 911 | 1911 | 1102403003 | Region XI (Davao Region) | Davao del Sur | City of Digos | San Jose | 6.7335 | 125.3568 | U | 7263 | 2136 | 641 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0068 | PTCI/MIDC | 6.7353 | 125.3569 | 0.2 | Terrestrial Optical Fiber Drop | 0.97 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1912 | 2 | 912 | 1912 | 0731100006 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Buaya | 10.3182 | 123.9967 | U | 19086 | 5453 | 1636 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0180 | PTCI/MIDC | 10.3173 | 123.9947 | 0.25 | Terrestrial Optical Fiber Drop | 0.98 | 5.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1913 | 2 | 913 | 1913 | 0604530004 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Batuan | 10.4746 | 122.8216 | R | 1127 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 2.56 | Terrestrial Optical Fiber Drop | 0.98 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1914 | 2 | 914 | 1914 | 1430300012 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Brookside | 16.4215 | 120.6018 | R | 1814 | 477 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0017 | PTCI/MIDC | 16.4226 | 120.6009 | 0.16 | Terrestrial Optical Fiber Drop | 0.98 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1915 | 2 | 915 | 1915 | 0603005010 | Region VI (Western Visayas) | Iloilo | Balasan | Kinalkalan | 11.4765 | 123.0825 | R | 1333 | 350 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 2.06 | Terrestrial Optical Fiber Drop | 0.98 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1916 | 2 | 916 | 1916 | 0506213011 | Region V (Bicol Region) | Sorsogon | Pilar | Calongay | 12.9409 | 123.6719 | R | 1958 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 2.22 | Terrestrial Optical Fiber Drop | 0.98 | 9.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1917 | 2 | 917 | 1917 | 0702215016 | Region VII (Central Visayas) | Cebu | Carmen | Poblacion | 10.5851 | 124.0161 | U | 5569 | 1465 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 0.46 | Terrestrial Optical Fiber Drop | 0.98 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1918 | 2 | 918 | 1918 | 1102403007 | Region XI (Davao Region) | Davao del Sur | City of Digos | Dawis | 6.7293 | 125.3649 | U | 6025 | 1772 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0143 | PTCI/MIDC | 6.7257 | 125.3721 | 0.88 | Terrestrial Optical Fiber Drop | 0.98 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1919 | 2 | 919 | 1919 | 0403403016 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Poblacion | 14.3295 | 121.078 | U | 5494 | 1664 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02089-C08 | PTCI/MIDC | 14.3186 | 121.0757 | 0.96 | Terrestrial Optical Fiber Drop | 1.04 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1920 | 2 | 920 | 1920 | 0701230045 | Region VII (Central Visayas) | Bohol | Loon | Napo | 9.7996 | 123.7911 | R | 1435 | 358 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 0.3 | Terrestrial Optical Fiber Drop | 0.98 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1921 | 2 | 921 | 1921 | 0701205008 | Region VII (Central Visayas) | Bohol | Baclayon | Montana | 9.6251 | 123.9218 | R | 1896 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 3.88 | Terrestrial Optical Fiber Drop | 0.98 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1922 | 2 | 922 | 1922 | 0102815011 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pasaleng | 18.5487 | 120.9363 | R | 1820 | 491 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00007 | Edgepoint | 18.5501 | 120.9325 | 0.43 | Terrestrial Optical Fiber Drop | 0.98 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1923 | 2 | 923 | 1923 | 0301410004 | Region III (Central Luzon) | Bulacan | City of Malolos | Bagna | 14.8271 | 120.8213 | U | 5171 | 1477 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02487 | Edgepoint | 14.8248 | 120.8221 | 0.27 | Terrestrial Optical Fiber Drop | 0.98 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1924 | 2 | 924 | 1924 | 0702215008 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Sur | 10.5679 | 124.0198 | R | 2706 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0024 | PTCI/MIDC | 10.5658 | 124.018 | 0.31 | Terrestrial Optical Fiber Drop | 0.98 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1925 | 2 | 925 | 1925 | 0402118044 | Region IV-A (CALABARZON) | Cavite | Silang | Santol | 14.1694 | 120.9532 | R | 2419 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02172-C08 | PTCI/MIDC | 14.1692 | 120.9623 | 0.98 | Terrestrial Optical Fiber Drop | 0.98 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1926 | 2 | 926 | 1926 | 1430300016 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Camp Allen | 16.4072 | 120.5976 | R | 2343 | 616 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0024 | LDIC | 16.4025 | 120.6048 | 0.2 | Terrestrial Optical Fiber Drop | 0.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1927 | 2 | 927 | 1927 | 0603037036 | Region VI (Western Visayas) | Iloilo | Pototan | Naslo | 10.9502 | 122.6334 | R | 1637 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.39 | Terrestrial Optical Fiber Drop | 0.98 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1928 | 2 | 928 | 1928 | 0506213033 | Region V (Bicol Region) | Sorsogon | Pilar | Marifosque | 12.9247 | 123.6688 | R | 2522 | 630 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 0.48 | Terrestrial Optical Fiber Drop | 0.99 | 10.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1929 | 2 | 929 | 1929 | 0803702035 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Salvacion Poblacion | 11.2082 | 124.8492 | R | 1215 | 319 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0003 | PTCI/MIDC | 11.2031 | 124.8469 | 0.61 | Terrestrial Optical Fiber Drop | 0.98 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1930 | 2 | 930 | 1930 | 0403430001 | Region IV-A (CALABARZON) | Laguna | Victoria | Banca-banca | 14.2024 | 121.3455 | R | 4281 | 1297 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02113-C08 | PTCI/MIDC | 14.2028 | 121.346 | 0.07 | Terrestrial Optical Fiber Drop | 0.99 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1931 | 2 | 931 | 1931 | 0401030008 | Region IV-A (CALABARZON) | Batangas | Talisay | Caloocan | 14.0882 | 120.9794 | R | 1793 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.83 | Terrestrial Optical Fiber Drop | 4.25 | 3.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1932 | 2 | 932 | 1932 | 0401028011 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Isidro Norte | 14.0598 | 121.1806 | R | 2475 | 687 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 1.07 | Terrestrial Optical Fiber Drop | 3.44 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1933 | 2 | 933 | 1933 | 0405622010 | Region IV-A (CALABARZON) | Quezon | Lopez | Bebito | 13.8924 | 122.2695 | R | 1659 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0001 | PTCI/MIDC | 13.8896 | 122.2685 | 0.34 | Terrestrial Optical Fiber Drop | 0.98 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1934 | 2 | 934 | 1934 | 0504111016 | Region V (Bicol Region) | Masbate | City of Masbate | F. Magallanes | 12.3635 | 123.6237 | U | 3376 | 823 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03024-C10 | PTCI/MIDC | 12.359 | 123.6263 | 0.58 | Terrestrial Optical Fiber Drop | 0.98 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1935 | 2 | 935 | 1935 | 0405630022 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 4 Parang | 13.9714 | 121.6911 | R | 2057 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.71 | Terrestrial Optical Fiber Drop | 0.98 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1936 | 2 | 936 | 1936 | 0405618032 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Manggagawa | 13.8948 | 122.4536 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1413 | FTAP Smart | 13.892 | 122.4548 | 0.34 | Terrestrial Optical Fiber Drop | 0.99 | 11.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1937 | 2 | 937 | 1937 | 0603037031 | Region VI (Western Visayas) | Iloilo | Pototan | Primitivo Ledesma Ward | 10.9407 | 122.6341 | R | 2236 | 588 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.71 | Terrestrial Optical Fiber Drop | 0.99 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1938 | 2 | 938 | 1938 | 0402103061 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Salinas II | 14.4384 | 120.9423 | U | 6082 | 1788 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1120 | FTAP Smart | 14.4377 | 120.9409 | 0.17 | Terrestrial Optical Fiber Drop | 0.99 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1939 | 2 | 939 | 1939 | 0402109069 | Region IV-A (CALABARZON) | Cavite | City of Imus | Mariano Espeleta I | 14.4023 | 120.9403 | R | 1474 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.14 | Terrestrial Optical Fiber Drop | 0.52 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1940 | 2 | 940 | 1940 | 0405801007 | Region IV-A (CALABARZON) | Rizal | Angono | Poblacion Ibaba | 14.5297 | 121.1534 | R | 3472 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01844 | Edgepoint | 14.5376 | 121.1542 | 0.13 | Terrestrial Optical Fiber Drop | 0.28 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1941 | 2 | 941 | 1941 | 1130700021 | Region XI (Davao Region) | Davao del Sur | City of Davao | Buhangin | 7.1131 | 125.6312 | U | 70251 | 20662 | 6199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0043 | PTCI/MIDC | 7.1097 | 125.6319 | 0.39 | Terrestrial Optical Fiber Drop | 0.99 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1942 | 2 | 942 | 1942 | 0301408011 | Region III (Central Luzon) | Bulacan | Guiguinto | Tabang | 14.8315 | 120.8641 | U | 11984 | 3424 | 1027 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01151 | Edgepoint | 14.8322 | 120.8602 | 0.43 | Terrestrial Optical Fiber Drop | 0.99 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1943 | 2 | 943 | 1943 | 1705205062 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Suqui | 13.4179 | 121.2021 | R | 3824 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 1.45 | Terrestrial Optical Fiber Drop | 0.99 | 6.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1944 | 2 | 944 | 1944 | 1430300145 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Liwanag-Loakan | 16.4072 | 120.5969 | R | 4868 | 1281 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00357 | Edgepoint | 16.3305 | 120.6474 | 1.75 | Terrestrial Optical Fiber Drop | 0.57 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1945 | 2 | 945 | 1945 | 0103306021 | Region I (Ilocos Region) | La Union | Bangar | Nagsabaran | 16.8951 | 120.4158 | R | 1487 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.92 | Terrestrial Optical Fiber Drop | 0.99 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1946 | 2 | 946 | 1946 | 0506216051 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Poblacion | 13.0401 | 124.041 | R | 4739 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 0.45 | Terrestrial Optical Fiber Drop | 0.99 | 7.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1947 | 2 | 947 | 1947 | 0405801012 | Region IV-A (CALABARZON) | Rizal | Angono | San Vicente | 14.523 | 121.1468 | U | 13646 | 3790 | 1137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00848-A04 | PTCI/MIDC | 14.5239 | 121.1457 | 0.15 | Terrestrial Optical Fiber Drop | 0.99 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1948 | 2 | 948 | 1948 | 0102817014 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Naglicuan | 18.3145 | 120.6034 | R | 1777 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01229-B05 | PTCI/MIDC | 18.3313 | 120.6116 | 2.06 | Terrestrial Optical Fiber Drop | 0.99 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1949 | 2 | 949 | 1949 | 0105538011 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Leet | 15.9913 | 120.4645 | U | 7333 | 2036 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 1.12 | Terrestrial Optical Fiber Drop | 0.99 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1950 | 2 | 950 | 1950 | 0403405046 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Punta | 14.1771 | 121.1178 | U | 8025 | 2431 | 729 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040271 | FTAP Globe | 14.1786 | 121.1216 | 0.43 | Terrestrial Optical Fiber Drop | 0.99 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1951 | 2 | 951 | 1951 | 1731500048 | MIMAROPA Region | Palawan | City of Puerto Princesa | San Pedro | 9.7635 | 118.7347 | U | 26694 | 7214 | 2164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2216 | FTAP Smart | 9.7591 | 118.7398 | 0.74 | Terrestrial Optical Fiber Drop | 0.99 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1952 | 2 | 952 | 1952 | 0402109011 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bucandala I | 14.4052 | 120.9265 | U | 10459 | 3076 | 923 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0004 | LDIC | 14.4037 | 120.95 | 0.39 | Terrestrial Optical Fiber Drop | 1.53 | 4.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1953 | 2 | 953 | 1953 | 0401015002 | Region IV-A (CALABARZON) | Batangas | Lobo | Balatbat | 13.6563 | 121.2066 | R | 2515 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040610 | FTAP Globe | 13.6527 | 121.201 | 0.73 | Terrestrial Optical Fiber Drop | 1 | 18.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1954 | 2 | 954 | 1954 | 0504111011 | Region V (Bicol Region) | Masbate | City of Masbate | Cagay | 12.3647 | 123.6225 | R | 1782 | 434 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03024-C10 | PTCI/MIDC | 12.359 | 123.6263 | 0.76 | Terrestrial Optical Fiber Drop | 1 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1955 | 2 | 955 | 1955 | 0103309015 | Region I (Ilocos Region) | La Union | Caba | Santiago Sur | 16.4269 | 120.338 | R | 2089 | 564 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.8 | Terrestrial Optical Fiber Drop | 0.99 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1956 | 2 | 956 | 1956 | 0105532005 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Antipangol | 15.9313 | 120.2728 | R | 1816 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010191 | FTAP Globe | 15.94 | 120.2689 | 1.06 | Terrestrial Optical Fiber Drop | 1 | 7.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1957 | 2 | 957 | 1957 | 0405601011 | Region IV-A (CALABARZON) | Quezon | Agdangan | Sildora | 13.8602 | 121.9376 | R | 1055 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.99 | Terrestrial Optical Fiber Drop | 2.84 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1958 | 2 | 958 | 1958 | 0403403007 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Ganado | 14.285 | 121.0804 | U | 7085 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01998-C08 | PTCI/MIDC | 14.2831 | 121.0762 | 0.5 | Terrestrial Optical Fiber Drop | 1 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1959 | 2 | 959 | 1959 | 1030500044 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Carmen | 8.4683 | 124.6314 | U | 79167 | 21990 | 6597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0014 | PTCI/MIDC | 8.4674 | 124.6312 | 0.11 | Terrestrial Optical Fiber Drop | 1 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1960 | 2 | 960 | 1960 | 0731300001 | Region VII (Central Visayas) | Cebu | City of Mandaue | Alang-alang | 10.3464 | 123.9407 | U | 11507 | 3287 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0117 | PTCI/MIDC | 10.3409 | 123.9486 | 0.7 | Terrestrial Optical Fiber Drop | 0.85 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1961 | 2 | 961 | 1961 | 0307706023 | Region III (Central Luzon) | Aurora | Dipaculao | South Poblacion | 15.8441 | 121.5357 | R | 1424 | 374 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3804 | FTAP Smart | 15.8454 | 121.5368 | 0.19 | Terrestrial Optical Fiber Drop | 1 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1962 | 2 | 962 | 1962 | 0403427002 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Bagong Pook | 14.4708 | 121.4295 | R | 2532 | 767 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040090 | FTAP Globe | 14.4653 | 121.4312 | 0.64 | Terrestrial Optical Fiber Drop | 0.99 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1963 | 2 | 963 | 1963 | 0205005025 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Salvacion | 16.4791 | 121.1499 | R | 4495 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0017 | PTCI/MIDC | 16.4767 | 121.1461 | 0.49 | Terrestrial Optical Fiber Drop | 1 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1964 | 2 | 964 | 1964 | 0103307037 | Region I (Ilocos Region) | La Union | Bauang | Taberna | 16.528 | 120.3338 | R | 2113 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010100 | FTAP Globe | 16.5519 | 120.3302 | 1.41 | Terrestrial Optical Fiber Drop | 0.82 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1965 | 2 | 965 | 1965 | 0305415019 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Pasig | 15.1088 | 120.5524 | U | 5346 | 1336 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00793 | Edgepoint | 15.2255 | 120.6073 | 0.54 | Terrestrial Optical Fiber Drop | 2.14 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1966 | 2 | 966 | 1966 | 0403404005 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Bigaa | 14.2911 | 121.1285 | U | 14979 | 4539 | 1362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02035-C08 | PTCI/MIDC | 14.2963 | 121.1289 | 0.58 | Terrestrial Optical Fiber Drop | 1 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1967 | 2 | 967 | 1967 | 0600407010 | Region VI (Western Visayas) | Aklan | Kalibo | Mabilo | 11.7061 | 122.3644 | R | 2655 | 680 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.51 | Terrestrial Optical Fiber Drop | 1 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1968 | 2 | 968 | 1968 | 0403425014 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Antonio | 14.3534 | 121.0411 | U | 65077 | 19720 | 5916 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0010 | PTCI/MIDC | 14.3568 | 121.0417 | 0.38 | Terrestrial Optical Fiber Drop | 1 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1969 | 2 | 969 | 1969 | 0301420034 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc West | 14.7995 | 121.0611 | U | 9287 | 2653 | 796 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00992-B07 | PTCI/MIDC | 14.8014 | 121.0618 | 0.23 | Terrestrial Optical Fiber Drop | 1 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1970 | 2 | 970 | 1970 | 0403420002 | Region IV-A (CALABARZON) | Laguna | Pakil | Banilan | 14.3814 | 121.4003 | R | 2020 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S1205 | FTAP Smart | 14.4157 | 121.4066 | 3.88 | Terrestrial Optical Fiber Drop | 1 | 6.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1971 | 2 | 971 | 1971 | 0203114057 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Marana I | 17.1592 | 121.922 | R | 1809 | 476 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020060 | FTAP Globe | 17.1618 | 121.9209 | 0.31 | Terrestrial Optical Fiber Drop | 1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1972 | 2 | 972 | 1972 | 0300803021 | Region III (Central Luzon) | Bataan | City of Balanga | Tenejero | 14.6787 | 120.533 | U | 9639 | 2677 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N2086 | FTAP Smart | 14.6763 | 120.5321 | 0.28 | Terrestrial Optical Fiber Drop | 1 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1973 | 2 | 973 | 1973 | 0405608005 | Region IV-A (CALABARZON) | Quezon | Candelaria | Bukal Sur | 13.9363 | 121.3886 | U | 7573 | 1992 | 598 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0015 | PTCI/MIDC | 13.9343 | 121.391 | 0.35 | Terrestrial Optical Fiber Drop | 2.35 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1974 | 2 | 974 | 1974 | 0401012024 | Region IV-A (CALABARZON) | Batangas | Lemery | Matingain I | 13.909 | 120.8868 | R | 3885 | 1079 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040501 | FTAP Globe | 13.9093 | 120.8899 | 0.34 | Terrestrial Optical Fiber Drop | 4.25 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1975 | 2 | 975 | 1975 | 0401005012 | Region IV-A (CALABARZON) | Batangas | Batangas City | Bolbok | 13.7741 | 121.046 | U | 13167 | 3657 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03083-C08 | PTCI/MIDC | 13.7803 | 121.0482 | 0.73 | Terrestrial Optical Fiber Drop | 1.66 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1976 | 2 | 976 | 1976 | 1630400080 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Sumilihon | 8.9914 | 125.6133 | R | 5102 | 1244 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130066 | FTAP Globe | 8.9937 | 125.6116 | 0.32 | Terrestrial Optical Fiber Drop | 3.72 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1977 | 2 | 977 | 1977 | 0600613023 | Region VI (Western Visayas) | Antique | San Jose | Maybato Norte | 10.7305 | 121.9555 | R | 4778 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0015 | PTCI/MIDC | 10.7278 | 121.9577 | 0.38 | Terrestrial Optical Fiber Drop | 4.02 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1978 | 2 | 978 | 1978 | 0403428005 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dita | 14.2815 | 121.1122 | U | 37982 | 11509 | 3453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02001-C08 | PTCI/MIDC | 14.291 | 121.1178 | 1.21 | Terrestrial Optical Fiber Drop | 1.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1979 | 2 | 979 | 1979 | 0300811019 | Region III (Central Luzon) | Bataan | Pilar | Panilao | 14.6699 | 120.5512 | U | 6118 | 1699 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01437 | Edgepoint | 14.6683 | 120.5477 | 0.41 | Terrestrial Optical Fiber Drop | 1.66 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1980 | 2 | 980 | 1980 | 0300804035 | Region III (Central Luzon) | Bataan | Dinalupihan | San Pablo | 14.8526 | 120.3788 | U | 8080 | 2244 | 673 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030578 | FTAP Globe | 14.8566 | 120.3772 | 0.47 | Terrestrial Optical Fiber Drop | 2.06 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1981 | 2 | 981 | 1981 | 1004317012 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Kibungsod | 9.0065 | 125.2059 | R | 3441 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0063 | PTCI/MIDC | 9.007 | 125.2065 | 0.09 | Terrestrial Optical Fiber Drop | 3.02 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1982 | 2 | 982 | 1982 | 1630400093 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | De Oro | 8.9425 | 125.5157 | R | 2466 | 601 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0011 | PTCI/MIDC | 8.9395 | 125.5155 | 0.33 | Terrestrial Optical Fiber Drop | 1.51 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1983 | 2 | 983 | 1983 | 0600613028 | Region VI (Western Visayas) | Antique | San Jose | San Fernando | 10.7763 | 121.9416 | R | 3396 | 870 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060029 | FTAP BTS | 10.7722 | 121.9445 | 0.56 | Terrestrial Optical Fiber Drop | 1.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1984 | 2 | 984 | 1984 | 0702201007 | Region VII (Central Visayas) | Cebu | Alcantara | Poblacion | 9.9743 | 123.4054 | R | 2773 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 2.43 | Terrestrial Optical Fiber Drop | 2.87 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1985 | 2 | 985 | 1985 | 0401003043 | Region IV-A (CALABARZON) | Batangas | Balayan | Sambat | 13.9508 | 120.7055 | R | 3169 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0870 | FTAP Smart | 13.9497 | 120.7097 | 0.47 | Terrestrial Optical Fiber Drop | 2.57 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1986 | 2 | 986 | 1986 | 0603044002 | Region VI (Western Visayas) | Iloilo | Sara | Aldeguer | 11.2187 | 122.9774 | R | 2046 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 1.14 | Terrestrial Optical Fiber Drop | 5.4 | 2.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1987 | 2 | 987 | 1987 | 0702251029 | Region VII (Central Visayas) | Cebu | City of Toledo | Poog | 10.3219 | 123.6856 | U | 7242 | 1905 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0165 | PTCI/MIDC | 10.3178 | 123.6875 | 0.5 | Terrestrial Optical Fiber Drop | 1.3 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1988 | 2 | 988 | 1988 | 1705205009 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Bucayao | 13.3064 | 121.1921 | R | 2672 | 685 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170072 | FTAP Globe | 13.3066 | 121.1896 | 0.27 | Terrestrial Optical Fiber Drop | 1.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1989 | 2 | 989 | 1989 | 0500510004 | Region V (Bicol Region) | Albay | Malinao | Balza | 13.4015 | 123.7032 | R | 2287 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050124 | FTAP Globe | 13.3997 | 123.7064 | 0.4 | Terrestrial Optical Fiber Drop | 1.02 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1990 | 2 | 990 | 1990 | 0803736018 | Region VIII (Eastern Visayas) | Leyte | Merida | Puerto Bello | 10.9859 | 124.5313 | R | 4484 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080193 | FTAP BTS | 11.0011 | 124.5391 | 1.9 | Terrestrial Optical Fiber Drop | 5.09 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1991 | 2 | 991 | 1991 | 0305421002 | Region III (Central Luzon) | Pampanga | Sto. Tomas | Moras De La Paz | 15.0159 | 120.7103 | U | 5823 | 1455 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00909 | Edgepoint | 15.0517 | 120.6663 | 0.27 | Terrestrial Optical Fiber Drop | 0.88 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1992 | 2 | 992 | 1992 | 1001321028 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Sinabuagan | 7.9093 | 125.0941 | R | 2547 | 670 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100077 | FTAP BTS | 7.9209 | 125.0869 | 0.59 | Terrestrial Optical Fiber Drop | 0.44 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1993 | 2 | 993 | 1993 | 0403423001 | Region IV-A (CALABARZON) | Laguna | Rizal | Antipolo | 14.1108 | 121.3814 | R | 2871 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 1.5 | Terrestrial Optical Fiber Drop | 1.22 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1994 | 2 | 994 | 1994 | 0601905008 | Region VI (Western Visayas) | Capiz | Ivisan | Malocloc Norte | 11.5056 | 122.6797 | R | 2526 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060230 | FTAP Globe | 11.5064 | 122.6843 | 0.51 | Terrestrial Optical Fiber Drop | 2.32 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1995 | 2 | 995 | 1995 | 0702251037 | Region VII (Central Visayas) | Cebu | City of Toledo | Talavera | 10.4124 | 123.6662 | U | 7906 | 2080 | 624 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0174 | PTCI/MIDC | 10.4192 | 123.6706 | 0.9 | Terrestrial Optical Fiber Drop | 1.78 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1996 | 2 | 996 | 1996 | 0702243002 | Region VII (Central Visayas) | Cebu | San Remigio | Argawanon | 11.0703 | 123.9573 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0021 | PTCI/MIDC | 11.0674 | 123.9638 | 0.78 | Terrestrial Optical Fiber Drop | 2.39 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1997 | 2 | 997 | 1997 | 0405647031 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Isabang | 13.9644 | 121.5653 | U | 12686 | 3338 | 1001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040406 | FTAP Globe | 13.9695 | 121.5636 | 0.59 | Terrestrial Optical Fiber Drop | 2.32 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1998 | 2 | 998 | 1998 | 0300806008 | Region III (Central Luzon) | Bataan | Limay | Reformista | 14.5637 | 120.5955 | U | 5400 | 1500 | 450 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030629 | FTAP Globe | 14.568 | 120.5957 | 0.47 | Terrestrial Optical Fiber Drop | 1.21 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1999 | 2 | 999 | 1999 | 0300804021 | Region III (Central Luzon) | Bataan | Dinalupihan | New San Jose | 14.8806 | 120.4618 | U | 6942 | 1928 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0396 | FTAP Smart | 14.8836 | 120.4592 | 0.43 | Terrestrial Optical Fiber Drop | 1.59 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2000 | 2 | 1000 | 2000 | 0702223033 | Region VII (Central Visayas) | Cebu | Danao City | Sabang | 10.4974 | 124.0309 | U | 16515 | 4346 | 1304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0185 | PTCI/MIDC | 10.4925 | 124.0289 | 0.59 | Terrestrial Optical Fiber Drop | 2.76 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2001 | 3 | 1 | 2001 | 0501726001 | Region V (Bicol Region) | Camarines Sur | Pamplona | Batang | 13.5678 | 123.0601 | R | 2324 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050103 | FTAP Globe | 13.5641 | 123.0576 | 0.49 | Terrestrial Optical Fiber Drop | 1.14 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2002 | 3 | 2 | 2002 | 0702250015 | Region VII (Central Visayas) | Cebu | City of Talisay | San Roque | 10.2565 | 123.8604 | U | 22512 | 5924 | 1777 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0160 | PTCI/MIDC | 10.2575 | 123.8595 | 0.15 | Terrestrial Optical Fiber Drop | 2.22 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2003 | 3 | 3 | 2003 | 0501728017 | Region V (Bicol Region) | Camarines Sur | Pili | San Agustin | 13.5679 | 123.267 | U | 5708 | 1359 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03384-C10 | PTCI/MIDC | 13.5661 | 123.2692 | 0.31 | Terrestrial Optical Fiber Drop | 1.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2004 | 3 | 4 | 2004 | 0702250007 | Region VII (Central Visayas) | Cebu | City of Talisay | Lawaan I | 10.2586 | 123.8222 | U | 10935 | 2877 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0159 | PTCI/MIDC | 10.2524 | 123.8198 | 0.73 | Terrestrial Optical Fiber Drop | 1.96 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2005 | 3 | 5 | 2005 | 0401034008 | Region IV-A (CALABARZON) | Batangas | Tuy | Luntal | 14.034 | 120.7094 | R | 3732 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040361 | FTAP Globe | 14.0458 | 120.6994 | 1.69 | Terrestrial Optical Fiber Drop | 2.48 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2006 | 3 | 6 | 2006 | 0702241002 | Region VII (Central Visayas) | Cebu | San Fernando | Balud | 10.1486 | 123.6949 | U | 5062 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 1.26 | Terrestrial Optical Fiber Drop | 2.09 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2007 | 3 | 7 | 2007 | 0401021001 | Region IV-A (CALABARZON) | Batangas | Rosario | Alupay | 13.8441 | 121.2947 | R | 4434 | 1231 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040548 | FTAP Globe | 13.8424 | 121.2877 | 0.77 | Terrestrial Optical Fiber Drop | 2.82 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2008 | 3 | 8 | 2008 | 0305411024 | Region III (Central Luzon) | Pampanga | Magalang | Santo Rosario | 15.2449 | 120.6384 | U | 5554 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00788 | Edgepoint | 15.244 | 120.6364 | 0.23 | Terrestrial Optical Fiber Drop | 2.27 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2009 | 3 | 9 | 2009 | 0803738088 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Pablo | 11.0472 | 124.6061 | U | 6541 | 1721 | 516 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0095 | PTCI/MIDC | 11.0504 | 124.6081 | 0.41 | Terrestrial Optical Fiber Drop | 2.68 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2010 | 3 | 10 | 2010 | 0403406010 | Region IV-A (CALABARZON) | Laguna | Calauan | Masiit | 14.1611 | 121.3057 | U | 5456 | 1653 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02102-C08 | PTCI/MIDC | 14.1591 | 121.3135 | 0.87 | Terrestrial Optical Fiber Drop | 1.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2011 | 3 | 11 | 2011 | 0307106001 | Region III (Central Luzon) | Zambales | Masinloc | Baloganon | 15.5518 | 119.9462 | U | 8165 | 2148 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03362-B07 | PTCI/MIDC | 15.5488 | 119.9474 | 0.36 | Terrestrial Optical Fiber Drop | 1.89 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2012 | 3 | 12 | 2012 | 0803726006 | Region VIII (Eastern Visayas) | Leyte | Kananga | Libongao | 11.1617 | 124.561 | R | 2939 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 1.86 | Terrestrial Optical Fiber Drop | 2.59 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2013 | 3 | 13 | 2013 | 0431200012 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 9 | 13.9309 | 121.6111 | U | 3420 | 855 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.4 | Terrestrial Optical Fiber Drop | 0.25 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2014 | 3 | 14 | 2014 | 0702250017 | Region VII (Central Visayas) | Cebu | City of Talisay | Tangke | 10.2505 | 123.8594 | U | 14376 | 3783 | 1135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0160 | PTCI/MIDC | 10.2575 | 123.8595 | 0.78 | Terrestrial Optical Fiber Drop | 1.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2015 | 3 | 15 | 2015 | 0105522002 | Region I (Ilocos Region) | Pangasinan | Lingayen | Baay | 16.0097 | 120.2236 | U | 5865 | 1629 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00464 | Edgepoint | 16.0091 | 120.2223 | 0.15 | Terrestrial Optical Fiber Drop | 1.77 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2016 | 3 | 16 | 2016 | 0501725023 | Region V (Bicol Region) | Camarines Sur | Ocampo | San Vicente | 13.5594 | 123.3823 | R | 2130 | 507 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.56 | Terrestrial Optical Fiber Drop | 0.75 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2017 | 3 | 17 | 2017 | 0300804008 | Region III (Central Luzon) | Bataan | Dinalupihan | Daang Bago | 14.857 | 120.4794 | R | 3392 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02568 | Edgepoint | 14.8582 | 120.4764 | 0.35 | Terrestrial Optical Fiber Drop | 1.36 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2018 | 3 | 18 | 2018 | 0401020026 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | San Felipe | 13.8852 | 121.2048 | U | 3694 | 1026 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01954-C08 | PTCI/MIDC | 13.893 | 121.1996 | 1.03 | Terrestrial Optical Fiber Drop | 1.93 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2019 | 3 | 19 | 2019 | 0105526028 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Salay | 16.0794 | 120.3977 | U | 5931 | 1647 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00414 | Edgepoint | 16.083 | 120.3977 | 0.4 | Terrestrial Optical Fiber Drop | 1.38 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2020 | 3 | 20 | 2020 | 0405623004 | Region IV-A (CALABARZON) | Quezon | Lucban | Ayuti | 14.1169 | 121.5487 | U | 10218 | 2688 | 806 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0021 | PTCI/MIDC | 14.1109 | 121.5533 | 0.83 | Terrestrial Optical Fiber Drop | 1.08 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2021 | 3 | 21 | 2021 | 0105530024 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Palacpalac | 16.1267 | 120.5339 | R | 3173 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 1.61 | Terrestrial Optical Fiber Drop | 1.49 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2022 | 3 | 22 | 2022 | 0401020014 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Bawi | 13.8868 | 121.233 | R | 4041 | 1122 | 337 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040514 | FTAP Globe | 13.8971 | 121.2443 | 1.67 | Terrestrial Optical Fiber Drop | 1.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2023 | 3 | 23 | 2023 | 0307113015 | Region III (Central Luzon) | Zambales | Santa Cruz | Malabago | 15.7878 | 119.9053 | R | 2916 | 767 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 0.66 | Terrestrial Optical Fiber Drop | 2.27 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2024 | 3 | 24 | 2024 | 0105512019 | Region I (Ilocos Region) | Pangasinan | Binalonan | San Pablo | 16.016 | 120.6016 | R | 1919 | 533 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 0.48 | Terrestrial Optical Fiber Drop | 3.6 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2025 | 3 | 25 | 2025 | 0300811016 | Region III (Central Luzon) | Bataan | Pilar | Nagwaling | 14.6341 | 120.5245 | R | 3730 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030627 | FTAP Globe | 14.6352 | 120.5287 | 0.47 | Terrestrial Optical Fiber Drop | 2.36 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2026 | 3 | 26 | 2026 | 0702210011 | Region VII (Central Visayas) | Cebu | Barili | Guibuangan | 10.1153 | 123.496 | R | 2653 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 1.62 | Terrestrial Optical Fiber Drop | 1.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2027 | 3 | 27 | 2027 | 0401021003 | Region IV-A (CALABARZON) | Batangas | Rosario | Bagong Pook | 13.8449 | 121.221 | U | 6454 | 1792 | 538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBGG0009 | PTCI/MIDC | 13.8479 | 121.2131 | 0.92 | Terrestrial Optical Fiber Drop | 2.11 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2028 | 3 | 28 | 2028 | 0401022008 | Region IV-A (CALABARZON) | Batangas | San Jose | Banaybanay II | 13.9212 | 121.106 | U | 4648 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040460 | FTAP Globe | 13.9286 | 121.1095 | 0.91 | Terrestrial Optical Fiber Drop | 2.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2029 | 3 | 29 | 2029 | 0704601003 | Region VII (Central Visayas) | Negros Oriental | Amlan | Jugno | 9.4596 | 123.2002 | R | 4456 | 1172 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 1.74 | Terrestrial Optical Fiber Drop | 2.37 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2030 | 3 | 30 | 2030 | 0704610016 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Mangnao-Canal | 9.2934 | 123.2985 | U | 3241 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0080 | PTCI/MIDC | 9.2957 | 123.2949 | 0.48 | Terrestrial Optical Fiber Drop | 1.5 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2031 | 3 | 31 | 2031 | 0304919001 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Aulo | 15.5208 | 121.0945 | R | 1405 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01505-B07 | PTCI/MIDC | 15.5057 | 121.0775 | 2.48 | Terrestrial Optical Fiber Drop | 0.01 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2032 | 3 | 32 | 2032 | 0506215011 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Isidro | 12.6502 | 124.0952 | R | 1612 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 1.19 | Terrestrial Optical Fiber Drop | 1.25 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2033 | 3 | 33 | 2033 | 0702232007 | Region VII (Central Visayas) | Cebu | Minglanilla | Linao | 10.255 | 123.8103 | U | 16506 | 4343 | 1303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070359 | FTAP Globe | 10.2495 | 123.8123 | 0.65 | Terrestrial Optical Fiber Drop | 1.36 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2034 | 3 | 34 | 2034 | 0305403013 | Region III (Central Luzon) | Pampanga | Arayat | Mangga-Cacutud | 15.1471 | 120.7628 | U | 11667 | 2916 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01550-B07 | PTCI/MIDC | 15.1477 | 120.7629 | 0.07 | Terrestrial Optical Fiber Drop | 1.08 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2035 | 3 | 35 | 2035 | 0304902012 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Lusok | 15.6039 | 121.1426 | R | 2558 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03157-B07 | PTCI/MIDC | 15.6037 | 121.1431 | 0.05 | Terrestrial Optical Fiber Drop | 2.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2036 | 3 | 36 | 2036 | 0306914003 | Region III (Central Luzon) | Tarlac | San Manuel | Legaspi | 15.8193 | 120.6067 | R | 2982 | 764 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00566 | Edgepoint | 15.8254 | 120.6029 | 0.8 | Terrestrial Optical Fiber Drop | 2.54 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2037 | 3 | 37 | 2037 | 1600203012 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Comagascas | 9.1359 | 125.5585 | R | 4324 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 2.15 | Terrestrial Optical Fiber Drop | 1.95 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2038 | 3 | 38 | 2038 | 0304917003 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Bantug | 15.7201 | 120.9191 | U | 12103 | 3458 | 1037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0028 | PTCI/MIDC | 15.7203 | 120.9237 | 0.5 | Terrestrial Optical Fiber Drop | 1.78 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2039 | 3 | 39 | 2039 | 0402106061 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc II | 14.2833 | 120.9604 | U | 19186 | 5642 | 1693 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.16 | Terrestrial Optical Fiber Drop | 1.88 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2040 | 3 | 40 | 2040 | 0301423009 | Region III (Central Luzon) | Bulacan | Santa Maria | Guyong | 14.837 | 120.977 | U | 17675 | 5050 | 1515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01111-B07 | PTCI/MIDC | 14.8361 | 120.9745 | 0.28 | Terrestrial Optical Fiber Drop | 2.35 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2041 | 3 | 41 | 2041 | 1630400009 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Antongalon | 8.9486 | 125.6212 | R | 4300 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0009 | PTCI/MIDC | 8.9384 | 125.5902 | 3.59 | Terrestrial Optical Fiber Drop | 2.63 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2042 | 3 | 42 | 2042 | 0702232017 | Region VII (Central Visayas) | Cebu | Minglanilla | Tungkop | 10.2403 | 123.7824 | U | 14574 | 3835 | 1151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070362 | FTAP Globe | 10.2441 | 123.7824 | 0.43 | Terrestrial Optical Fiber Drop | 0.92 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2043 | 3 | 43 | 2043 | 0803714002 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Balud | 11.2923 | 124.6508 | R | 2968 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 0.5 | Terrestrial Optical Fiber Drop | 1.65 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2044 | 3 | 44 | 2044 | 0500517042 | Region V (Bicol Region) | Albay | City of Tabaco | San Vicente | 13.3565 | 123.7 | R | 4686 | 1142 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050133 | FTAP Globe | 13.3444 | 123.7023 | 1.37 | Terrestrial Optical Fiber Drop | 3.42 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2045 | 3 | 45 | 2045 | 0702222031 | Region VII (Central Visayas) | Cebu | Dalaguete | Tapun | 9.7734 | 123.5307 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0075 | PTCI/MIDC | 9.7647 | 123.5349 | 1.07 | Terrestrial Optical Fiber Drop | 1.29 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2046 | 3 | 46 | 2046 | 0500503010 | Region V (Bicol Region) | Albay | Daraga | Binitayan | 13.1553 | 123.7162 | U | 4659 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050173 | FTAP Globe | 13.155 | 123.7161 | 0.03 | Terrestrial Optical Fiber Drop | 1.03 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2047 | 3 | 47 | 2047 | 0301410055 | Region III (Central Luzon) | Bulacan | City of Malolos | Tikay | 14.8406 | 120.8539 | U | 13170 | 3762 | 1129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01141 | Edgepoint | 14.8402 | 120.8564 | 0.27 | Terrestrial Optical Fiber Drop | 2.42 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2048 | 3 | 48 | 2048 | 0702231001 | Region VII (Central Visayas) | Cebu | Medellin | Antipolo | 11.1605 | 123.9597 | U | 6680 | 1757 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0124 | PTCI/MIDC | 11.1643 | 123.9534 | 0.81 | Terrestrial Optical Fiber Drop | 2.48 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2049 | 3 | 49 | 2049 | 0307701007 | Region III (Central Luzon) | Aurora | Baler | Calabuanan | 15.7482 | 121.5097 | U | 4098 | 1078 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030320 | FTAP Globe | 15.7547 | 121.4939 | 1.84 | Terrestrial Optical Fiber Drop | 1.74 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2050 | 3 | 50 | 2050 | 0301421046 | Region III (Central Luzon) | Bulacan | San Miguel | San Vicente | 15.1398 | 120.971 | R | 2870 | 820 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01122-B07 | PTCI/MIDC | 15.144 | 120.9745 | 0.6 | Terrestrial Optical Fiber Drop | 1.1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2051 | 3 | 51 | 2051 | 0603035024 | Region VI (Western Visayas) | Iloilo | City of Passi | Imbang Grande | 11.1055 | 122.6624 | R | 2839 | 747 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.44 | Terrestrial Optical Fiber Drop | 1.76 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2052 | 3 | 52 | 2052 | 0702234015 | Region VII (Central Visayas) | Cebu | City of Naga | Lutac | 10.2486 | 123.725 | U | 5622 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 1.91 | Terrestrial Optical Fiber Drop | 1.76 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2053 | 3 | 53 | 2053 | 0601914043 | Region VI (Western Visayas) | Capiz | City of Roxas | Punta Tabuc | 11.5748 | 122.7446 | U | 5999 | 1578 | 473 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060226 | FTAP Globe | 11.5755 | 122.7465 | 0.23 | Terrestrial Optical Fiber Drop | 1.63 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2054 | 3 | 54 | 2054 | 0306904003 | Region III (Central Luzon) | Tarlac | Capas | Cubcub | 15.3324 | 120.5909 | U | 4213 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01802-B07 | PTCI/MIDC | 15.342 | 120.5972 | 1.26 | Terrestrial Optical Fiber Drop | 1.63 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2055 | 3 | 55 | 2055 | 0500517037 | Region V (Bicol Region) | Albay | City of Tabaco | San Carlos | 13.3757 | 123.7189 | R | 4226 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050126 | FTAP Globe | 13.3795 | 123.7173 | 0.45 | Terrestrial Optical Fiber Drop | 2.33 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2056 | 3 | 56 | 2056 | 0402116009 | Region IV-A (CALABARZON) | Cavite | Noveleta | Santa Rosa I | 14.4283 | 120.8764 | U | 5192 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.46 | Terrestrial Optical Fiber Drop | 0.73 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2057 | 3 | 57 | 2057 | 0300810020 | Region III (Central Luzon) | Bataan | Orion | Puting Buhangin | 14.585 | 120.5889 | R | 3189 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00904-B07 | PTCI/MIDC | 14.5834 | 120.5868 | 0.29 | Terrestrial Optical Fiber Drop | 1.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2058 | 3 | 58 | 2058 | 1705211007 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | San Isidro | 13.5039 | 120.9173 | U | 5300 | 1358 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170042 | FTAP Globe | 13.5044 | 120.9155 | 0.2 | Terrestrial Optical Fiber Drop | 1.22 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2059 | 3 | 59 | 2059 | 0201502025 | Region II (Cagayan Valley) | Cagayan | Alcala | Tupang | 17.9055 | 121.6423 | R | 2603 | 667 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0016 | LDIC | 17.9095 | 121.64 | 0.52 | Terrestrial Optical Fiber Drop | 1.31 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2060 | 3 | 60 | 2060 | 1705205006 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Bayanan II | 13.357 | 121.1701 | R | 3122 | 800 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 3.58 | Terrestrial Optical Fiber Drop | 1.91 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2061 | 3 | 61 | 2061 | 0304926003 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Abar 2nd | 15.7817 | 120.9698 | R | 4394 | 1255 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00576 | Edgepoint | 15.7797 | 120.9688 | 0.25 | Terrestrial Optical Fiber Drop | 2.4 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2062 | 3 | 62 | 2062 | 0403414005 | Region IV-A (CALABARZON) | Laguna | Mabitac | Nanguma | 14.445 | 121.4214 | R | 2749 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040099 | FTAP Globe | 14.4448 | 121.4243 | 0.31 | Terrestrial Optical Fiber Drop | 1.8 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2063 | 3 | 63 | 2063 | 0803736010 | Region VIII (Eastern Visayas) | Leyte | Merida | Lamanoc | 10.9267 | 124.5482 | R | 2219 | 583 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0040 | PTCI/MIDC | 10.9068 | 124.5349 | 2.66 | Terrestrial Optical Fiber Drop | 1.75 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2064 | 3 | 64 | 2064 | 0405811005 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan I | 14.6953 | 121.1209 | U | 33621 | 9339 | 2802 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01351 | Edgepoint | 14.6941 | 121.1205 | 0.15 | Terrestrial Optical Fiber Drop | 1.08 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2065 | 3 | 65 | 2065 | 0501724012 | Region V (Bicol Region) | Camarines Sur | City of Naga | Del Rosario | 13.6176 | 123.2379 | U | 10312 | 2455 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-03171 | Edgepoint | 13.6175 | 123.2364 | 0.17 | Terrestrial Optical Fiber Drop | 2.22 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2066 | 3 | 66 | 2066 | 0704620002 | Region VII (Central Visayas) | Negros Oriental | Sibulan | Ajong | 9.3815 | 123.2578 | R | 3691 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0050 | PTCI/MIDC | 9.377 | 123.2563 | 0.52 | Terrestrial Optical Fiber Drop | 9 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2067 | 3 | 67 | 2067 | 0806407002 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Asuncion | 10.1304 | 124.8614 | U | 5120 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080346 | FTAP Globe | 10.1393 | 124.8569 | 1.11 | Terrestrial Optical Fiber Drop | 0.46 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2068 | 3 | 68 | 2068 | 0402118031 | Region IV-A (CALABARZON) | Cavite | Silang | Pasong Langka | 14.1627 | 120.9982 | U | 4059 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02159-C08 | PTCI/MIDC | 14.1651 | 120.9988 | 0.28 | Terrestrial Optical Fiber Drop | 1.99 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2069 | 3 | 69 | 2069 | 0305407019 | Region III (Central Luzon) | Pampanga | Guagua | San Miguel | 14.9821 | 120.6481 | U | 5420 | 1355 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01639-B07 | PTCI/MIDC | 14.9819 | 120.6451 | 0.32 | Terrestrial Optical Fiber Drop | 2.24 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2070 | 3 | 70 | 2070 | 0704621017 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | Polo | 9.482 | 123.18 | R | 3900 | 1026 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 2.08 | Terrestrial Optical Fiber Drop | 5.12 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2071 | 3 | 71 | 2071 | 0300804020 | Region III (Central Luzon) | Bataan | Dinalupihan | Naparing | 14.8459 | 120.4069 | R | 3244 | 901 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02475-B07 | PTCI/MIDC | 14.846 | 120.4054 | 0.16 | Terrestrial Optical Fiber Drop | 1.05 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2072 | 3 | 72 | 2072 | 0306907011 | Region III (Central Luzon) | Tarlac | La Paz | Laungcupang | 15.4545 | 120.703 | R | 2396 | 614 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03433-B07 | PTCI/MIDC | 15.4762 | 120.7074 | 2.46 | Terrestrial Optical Fiber Drop | 1.75 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2073 | 3 | 73 | 2073 | 0304903016 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Bitas | 15.4966 | 120.978 | U | 6009 | 1716 | 515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01412-B07 | PTCI/MIDC | 15.4974 | 120.9762 | 0.21 | Terrestrial Optical Fiber Drop | 2.45 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2074 | 3 | 74 | 2074 | 0305403014 | Region III (Central Luzon) | Pampanga | Arayat | Mapalad | 15.2054 | 120.8102 | R | 4196 | 1049 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00803 | Edgepoint | 15.2038 | 120.8107 | 0.18 | Terrestrial Optical Fiber Drop | 8.15 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2075 | 3 | 75 | 2075 | 1600302010 | Region XIII (Caraga) | Agusan del Sur | Bunawan | San Teodoro | 8.1703 | 125.9994 | U | 7095 | 1819 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0009 | PTCI/MIDC | 8.2105 | 125.9905 | 4.57 | Terrestrial Optical Fiber Drop | 1.37 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2076 | 3 | 76 | 2076 | 0105518031 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Tapuac | 16.0372 | 120.3329 | U | 5044 | 1401 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00437 | Edgepoint | 16.0381 | 120.335 | 0.25 | Terrestrial Optical Fiber Drop | 1.83 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2077 | 3 | 77 | 2077 | 0401021037 | Region IV-A (CALABARZON) | Batangas | Rosario | Quilib | 13.8595 | 121.2064 | U | 6515 | 1809 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1032 | FTAP Smart | 13.8539 | 121.205 | 0.63 | Terrestrial Optical Fiber Drop | 1.75 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2078 | 3 | 78 | 2078 | 0305416030 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Nicolas | 15.0167 | 120.7035 | U | 10503 | 2625 | 788 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00941 | Edgepoint | 15.0162 | 120.7031 | 0.06 | Terrestrial Optical Fiber Drop | 1.33 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2079 | 3 | 79 | 2079 | 0702247004 | Region VII (Central Visayas) | Cebu | Sogod | Bawo | 10.7406 | 124.0087 | R | 2884 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 1.46 | Terrestrial Optical Fiber Drop | 1.35 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2080 | 3 | 80 | 2080 | 0702221005 | Region VII (Central Visayas) | Cebu | Daanbantayan | Bitoon | 11.2337 | 123.9939 | U | 5386 | 1417 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0072 | PTCI/MIDC | 11.2494 | 124.0028 | 1.99 | Terrestrial Optical Fiber Drop | 2.04 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2081 | 3 | 81 | 2081 | 0401003029 | Region IV-A (CALABARZON) | Batangas | Balayan | Gumamela | 13.9453 | 120.7417 | R | 3142 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 1.08 | Terrestrial Optical Fiber Drop | 1.49 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2082 | 3 | 82 | 2082 | 0601914001 | Region VI (Western Visayas) | Capiz | City of Roxas | Adlawan | 11.4972 | 122.7657 | R | 2694 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060231 | FTAP Globe | 11.5001 | 122.7634 | 0.41 | Terrestrial Optical Fiber Drop | 2.52 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2083 | 3 | 83 | 2083 | 0301420003 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gaya-gaya | 14.7959 | 121.05 | U | 59472 | 16992 | 5098 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N64 | FTAP Smart | 14.7956 | 121.0522 | 0.24 | Terrestrial Optical Fiber Drop | 1.57 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2084 | 3 | 84 | 2084 | 0803738058 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Libertad | 11.0346 | 124.5686 | R | 4685 | 1232 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0048 | PTCI/MIDC | 11.0365 | 124.5646 | 0.48 | Terrestrial Optical Fiber Drop | 3.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2085 | 3 | 85 | 2085 | 0401029005 | Region IV-A (CALABARZON) | Batangas | Taal | Buli | 13.8818 | 120.9544 | U | 5872 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040522 | FTAP Globe | 13.8841 | 120.9487 | 0.67 | Terrestrial Optical Fiber Drop | 1.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2086 | 3 | 86 | 2086 | 0702243019 | Region VII (Central Visayas) | Cebu | San Remigio | Mano | 11.0518 | 123.9366 | R | 4438 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0151 | PTCI/MIDC | 11.0425 | 123.9341 | 1.08 | Terrestrial Optical Fiber Drop | 2.97 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2087 | 3 | 87 | 2087 | 0301403018 | Region III (Central Luzon) | Bulacan | Baliuag | San Roque | 14.997 | 120.8915 | R | 4147 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00950 | Edgepoint | 14.9981 | 120.8907 | 0.16 | Terrestrial Optical Fiber Drop | 3.11 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2088 | 3 | 88 | 2088 | 0501734019 | Region V (Bicol Region) | Camarines Sur | Sipocot | Gaongan | 13.759 | 122.9664 | R | 2084 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 2.46 | Terrestrial Optical Fiber Drop | 1.07 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2089 | 3 | 89 | 2089 | 0702246022 | Region VII (Central Visayas) | Cebu | Sibonga | Sabang | 10.0315 | 123.6185 | R | 2978 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070063 | FTAP BTS | 10.0269 | 123.6162 | 0.57 | Terrestrial Optical Fiber Drop | 2.06 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2090 | 3 | 90 | 2090 | 0300805004 | Region III (Central Luzon) | Bataan | Hermosa | Balsic | 14.8637 | 120.4901 | U | 8190 | 2275 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-01088 | Edgepoint | 14.871 | 120.5021 | 1.52 | Terrestrial Optical Fiber Drop | 2.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2091 | 3 | 91 | 2091 | 0306916064 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Juan de Mata | 15.5355 | 120.5288 | R | 4602 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00673 | Edgepoint | 15.528 | 120.5216 | 1.14 | Terrestrial Optical Fiber Drop | 4.28 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2092 | 3 | 92 | 2092 | 0105524031 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Don Pedro | 15.8866 | 120.4304 | R | 3472 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00547 | Edgepoint | 15.89 | 120.4328 | 0.46 | Terrestrial Optical Fiber Drop | 4.22 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2093 | 3 | 93 | 2093 | 0403424041 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Antonio 2 | 13.9973 | 121.3334 | R | 5144 | 1558 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02127-C08 | PTCI/MIDC | 13.9949 | 121.3333 | 0.26 | Terrestrial Optical Fiber Drop | 4.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2094 | 3 | 94 | 2094 | 0307108007 | Region III (Central Luzon) | Zambales | Palauig | Liozon | 15.399 | 119.9327 | R | 3789 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00736 | Edgepoint | 15.4019 | 119.9278 | 0.62 | Terrestrial Optical Fiber Drop | 4.69 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2095 | 3 | 95 | 2095 | 0105533025 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tocok | 16.1416 | 120.4198 | R | 3807 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 2.14 | Terrestrial Optical Fiber Drop | 3.61 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2096 | 3 | 96 | 2096 | 0300806009 | Region III (Central Luzon) | Bataan | Limay | Townsite | 14.561 | 120.5951 | U | 5874 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3935 | FTAP Smart | 14.5589 | 120.5947 | 0.23 | Terrestrial Optical Fiber Drop | 1.45 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2097 | 3 | 97 | 2097 | 0300810013 | Region III (Central Luzon) | Bataan | Orion | Daang Pare | 14.6001 | 120.5794 | U | 8415 | 2337 | 701 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0017 | PTCI/MIDC | 14.5986 | 120.5807 | 0.22 | Terrestrial Optical Fiber Drop | 1.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2098 | 3 | 98 | 2098 | 0403417049 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Taytay | 14.1109 | 121.4141 | U | 3826 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040305 | FTAP Globe | 14.1176 | 121.4176 | 0.84 | Terrestrial Optical Fiber Drop | 2.3 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2099 | 3 | 99 | 2099 | 0305405033 | Region III (Central Luzon) | Pampanga | Candaba | Talang | 15.0191 | 120.8529 | U | 3940 | 985 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02373 | Edgepoint | 15.0195 | 120.8521 | 0.09 | Terrestrial Optical Fiber Drop | 1.99 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2100 | 3 | 100 | 2100 | 0603045005 | Region VI (Western Visayas) | Iloilo | Tigbauan | Bagumbayan | 10.6929 | 122.3872 | R | 2186 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0075 | PTCI/MIDC | 10.674 | 122.3827 | 2.16 | Terrestrial Optical Fiber Drop | 1.66 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2101 | 3 | 101 | 2101 | 1705110027 | MIMAROPA Region | Occidental Mindoro | San Jose | Mabini | 12.3714 | 121.0901 | R | 3710 | 951 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1524 | FTAP Smart | 12.3767 | 121.0856 | 0.76 | Terrestrial Optical Fiber Drop | 3.59 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2102 | 3 | 102 | 2102 | 0402118027 | Region IV-A (CALABARZON) | Cavite | Silang | Malabag | 14.1433 | 120.9646 | U | 5249 | 1543 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040290 | FTAP Globe | 14.1428 | 120.96 | 0.5 | Terrestrial Optical Fiber Drop | 2.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2103 | 3 | 103 | 2103 | 0301404005 | Region III (Central Luzon) | Bulacan | Bocaue | Biñang 1st | 14.7939 | 120.9308 | R | 3560 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01186 | Edgepoint | 14.7982 | 120.93 | 0.49 | Terrestrial Optical Fiber Drop | 1.69 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2104 | 3 | 104 | 2104 | 1705208043 | MIMAROPA Region | Oriental Mindoro | Naujan | Pinagsabangan I | 13.2538 | 121.2684 | R | 2624 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170080 | FTAP Globe | 13.2359 | 121.2697 | 2 | Terrestrial Optical Fiber Drop | 1.24 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2105 | 3 | 105 | 2105 | 0405814005 | Region IV-A (CALABARZON) | Rizal | Teresa | May-Iba | 14.5633 | 121.2067 | U | 5907 | 1640 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00741-A04 | PTCI/MIDC | 14.5655 | 121.2092 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2106 | 3 | 106 | 2106 | 0506205002 | Region V (Bicol Region) | Sorsogon | Casiguran | Boton | 12.9291 | 124.0472 | R | 2415 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 6.35 | Terrestrial Optical Fiber Drop | 2.01 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2107 | 3 | 107 | 2107 | 0300801003 | Region III (Central Luzon) | Bataan | Abucay | Capitangan | 14.7061 | 120.5378 | U | 7605 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030099 | FTAP BTS | 14.7029 | 120.5358 | 0.42 | Terrestrial Optical Fiber Drop | 2.38 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2108 | 3 | 108 | 2108 | 0102914017 | Region I (Ilocos Region) | Ilocos Sur | Narvacan | Margaay | 17.4253 | 120.474 | U | 2657 | 699 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ILS_0021 | LDIC | 17.4195 | 120.4733 | 0.65 | Terrestrial Optical Fiber Drop | 1.05 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2109 | 3 | 109 | 2109 | 0405814004 | Region IV-A (CALABARZON) | Rizal | Teresa | Dulumbayan | 14.5633 | 121.2067 | U | 8898 | 2471 | 741 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00741-A04 | PTCI/MIDC | 14.5655 | 121.2092 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2110 | 3 | 110 | 2110 | 0304901032 | Region III (Central Luzon) | Nueva Ecija | Aliaga | San Juan | 15.5069 | 120.8933 | U | 5728 | 1636 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02883-B07 | PTCI/MIDC | 15.5052 | 120.8868 | 0.72 | Terrestrial Optical Fiber Drop | 2.42 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2111 | 3 | 111 | 2111 | 0405811015 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santo Niño | 14.6694 | 121.1347 | U | 12224 | 3395 | 1019 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01422 | Edgepoint | 14.671 | 121.1347 | 0.18 | Terrestrial Optical Fiber Drop | 2.39 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2112 | 3 | 112 | 2112 | 0701201005 | Region VII (Central Visayas) | Bohol | Alburquerque | East Poblacion | 9.6109 | 123.9568 | R | 2271 | 567 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 0.3 | Terrestrial Optical Fiber Drop | 2.16 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2113 | 3 | 113 | 2113 | 0604527010 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Cayhagan | 9.688 | 122.4477 | R | 3878 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0066 | PTCI/MIDC | 9.7261 | 122.4402 | 4.32 | Terrestrial Optical Fiber Drop | 8.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2114 | 3 | 114 | 2114 | 0405648022 | Region IV-A (CALABARZON) | Quezon | Tiaong | San Agustin | 13.9436 | 121.3178 | R | 2542 | 668 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03369-C08 | PTCI/MIDC | 13.9469 | 121.3102 | 0.89 | Terrestrial Optical Fiber Drop | 2.17 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2115 | 3 | 115 | 2115 | 0401014035 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Pagolingin West | 13.8936 | 121.1623 | R | 2144 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.45 | Terrestrial Optical Fiber Drop | 5.65 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2116 | 3 | 116 | 2116 | 0405808008 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Rosario | 14.7486 | 121.1487 | U | 6573 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00729-A04 | PTCI/MIDC | 14.7456 | 121.164 | 0.27 | Terrestrial Optical Fiber Drop | 1.69 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2117 | 3 | 117 | 2117 | 1004319007 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Maanas | 8.8912 | 125.0322 | R | 4451 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0067 | PTCI/MIDC | 8.8896 | 125.032 | 0.17 | Terrestrial Optical Fiber Drop | 2.52 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2118 | 3 | 118 | 2118 | 0201529018 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Carig | 17.6644 | 121.7495 | U | 5159 | 1322 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02278 | Edgepoint | 17.6685 | 121.7522 | 0.53 | Terrestrial Optical Fiber Drop | 1.48 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2119 | 3 | 119 | 2119 | 0301422014 | Region III (Central Luzon) | Bulacan | San Rafael | Maguinao | 15.0236 | 120.9342 | U | 5164 | 1475 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00926 | Edgepoint | 15.0273 | 120.9352 | 0.42 | Terrestrial Optical Fiber Drop | 1.8 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2120 | 3 | 120 | 2120 | 0501710012 | Region V (Bicol Region) | Camarines Sur | Canaman | San Agustin | 13.6455 | 123.183 | R | 3184 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 0.59 | Terrestrial Optical Fiber Drop | 1.18 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2121 | 3 | 121 | 2121 | 0306910027 | Region III (Central Luzon) | Tarlac | Paniqui | Salumague | 15.6662 | 120.5656 | R | 3681 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00610 | Edgepoint | 15.6665 | 120.5713 | 0.62 | Terrestrial Optical Fiber Drop | 2.31 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2122 | 3 | 122 | 2122 | 0304928018 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Santo Rosario | 15.4338 | 120.8894 | R | 3179 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01513-B07 | PTCI/MIDC | 15.4356 | 120.8836 | 0.65 | Terrestrial Optical Fiber Drop | 3.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2123 | 3 | 123 | 2123 | 0702208021 | Region VII (Central Visayas) | Cebu | Balamban | Nangka | 10.5332 | 123.7194 | U | 7401 | 1947 | 584 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 0.3 | Terrestrial Optical Fiber Drop | 2.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2124 | 3 | 124 | 2124 | 0305409003 | Region III (Central Luzon) | Pampanga | Mabalacat City | Bundagul | 15.212 | 120.5801 | U | 4122 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02973-B07 | PTCI/MIDC | 15.219 | 120.5769 | 0.36 | Terrestrial Optical Fiber Drop | 1.26 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2125 | 3 | 125 | 2125 | 0405805015 | Region IV-A (CALABARZON) | Rizal | Cainta | San Isidro | 14.6362 | 121.1086 | U | 83020 | 23061 | 6918 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01543 | Edgepoint | 14.6353 | 121.1093 | 0.13 | Terrestrial Optical Fiber Drop | 1.55 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2126 | 3 | 126 | 2126 | 0702243017 | Region VII (Central Visayas) | Cebu | San Remigio | Looc | 11.0665 | 123.9368 | R | 2423 | 637 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070033 | FTAP BTS | 11.076 | 123.9377 | 1.06 | Terrestrial Optical Fiber Drop | 1.34 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2127 | 3 | 127 | 2127 | 1130700019 | Region XI (Davao Region) | Davao del Sur | City of Davao | Binugao | 7.1649 | 125.4714 | U | 8991 | 2644 | 793 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110319 | FTAP BTS | 6.9653 | 125.4772 | 1.06 | Terrestrial Optical Fiber Drop | 2.98 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2128 | 3 | 128 | 2128 | 1102502005 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Punta Linao | 7.0624 | 125.9618 | R | 3404 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDLG0038 | PTCI/MIDC | 7.0669 | 125.9606 | 0.51 | Terrestrial Optical Fiber Drop | 10.57 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2129 | 3 | 129 | 2129 | 0403422014 | Region IV-A (CALABARZON) | Laguna | Pila | San Antonio | 14.2179 | 121.3592 | R | 4205 | 1274 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 1.57 | Terrestrial Optical Fiber Drop | 1.32 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2130 | 3 | 130 | 2130 | 1102412011 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone I | 6.8494 | 125.4189 | U | 9351 | 2750 | 825 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.01 | Terrestrial Optical Fiber Drop | 1.37 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2131 | 3 | 131 | 2131 | 0331400019 | Region III (Central Luzon) | Zambales | City of Olongapo | West Bajac-bajac | 14.844 | 120.2894 | U | 8582 | 2319 | 696 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 521 | FTAP Smart | 14.8444 | 120.2929 | 0.39 | Terrestrial Optical Fiber Drop | 1.47 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2132 | 3 | 132 | 2132 | 0305408044 | Region III (Central Luzon) | Pampanga | Lubao | Santo Niño | 14.8726 | 120.5039 | R | 4087 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01088 | Edgepoint | 14.871 | 120.5021 | 0.27 | Terrestrial Optical Fiber Drop | 3.84 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2133 | 3 | 133 | 2133 | 0301406007 | Region III (Central Luzon) | Bulacan | Bustos | Liciada | 14.9092 | 120.9306 | U | 6416 | 1833 | 550 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02547 | Edgepoint | 14.9056 | 120.9286 | 0.45 | Terrestrial Optical Fiber Drop | 1.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2134 | 3 | 134 | 2134 | 0307106005 | Region III (Central Luzon) | Zambales | Masinloc | Inhobol | 15.5289 | 119.9603 | U | 10276 | 2704 | 811 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02455 | Edgepoint | 15.5334 | 119.9561 | 0.67 | Terrestrial Optical Fiber Drop | 1.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2135 | 3 | 135 | 2135 | 1204704005 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Benoligan | 7.0435 | 125.0062 | R | 2857 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120126 | FTAP BTS | 7.0423 | 125.0077 | 0.21 | Terrestrial Optical Fiber Drop | 2.24 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2136 | 3 | 136 | 2136 | 0501723015 | Region V (Bicol Region) | Camarines Sur | Nabua | La Opinion | 13.3809 | 123.3716 | U | 5641 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050125 | FTAP Globe | 13.3818 | 123.3726 | 0.15 | Terrestrial Optical Fiber Drop | 2.48 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2137 | 3 | 137 | 2137 | 0403405062 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Majada Labas | 14.1951 | 121.1064 | U | 11588 | 3511 | 1053 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040253 | FTAP Globe | 14.1964 | 121.1107 | 0.48 | Terrestrial Optical Fiber Drop | 2.32 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2138 | 3 | 138 | 2138 | 0402115026 | Region IV-A (CALABARZON) | Cavite | Naic | Sabang | 14.3146 | 120.7934 | U | 23095 | 6792 | 2038 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040176 | FTAP Globe | 14.3157 | 120.7904 | 0.35 | Terrestrial Optical Fiber Drop | 1.64 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2139 | 3 | 139 | 2139 | 0405805017 | Region IV-A (CALABARZON) | Rizal | Cainta | San Roque | 14.5763 | 121.1173 | U | 9850 | 2736 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01787 | Edgepoint | 14.5753 | 121.1157 | 0.21 | Terrestrial Optical Fiber Drop | 1.04 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2140 | 3 | 140 | 2140 | 0501701014 | Region V (Bicol Region) | Camarines Sur | Baao | Buluang | 13.4699 | 123.3569 | U | 7954 | 1893 | 568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02841-C10 | PTCI/MIDC | 13.4681 | 123.3583 | 0.25 | Terrestrial Optical Fiber Drop | 1.76 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2141 | 3 | 141 | 2141 | 1705206017 | MIMAROPA Region | Oriental Mindoro | Gloria | Maligaya | 12.9686 | 121.4774 | R | 3305 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 0.42 | Terrestrial Optical Fiber Drop | 1.03 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2142 | 3 | 142 | 2142 | 0702251018 | Region VII (Central Visayas) | Cebu | City of Toledo | Ibo | 10.3653 | 123.6192 | R | 4834 | 1272 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0170 | PTCI/MIDC | 10.3695 | 123.626 | 0.88 | Terrestrial Optical Fiber Drop | 1.34 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2143 | 3 | 143 | 2143 | 0305415024 | Region III (Central Luzon) | Pampanga | Porac | Pio | 15.0837 | 120.5499 | U | 19317 | 4829 | 1449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 1.57 | Terrestrial Optical Fiber Drop | 2.31 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2144 | 3 | 144 | 2144 | 0501720009 | Region V (Bicol Region) | Camarines Sur | Magarao | San Isidro | 13.6615 | 123.189 | U | 3104 | 739 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0004 | PTCI/MIDC | 13.6631 | 123.1918 | 0.35 | Terrestrial Optical Fiber Drop | 1.04 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2145 | 3 | 145 | 2145 | 0405804007 | Region IV-A (CALABARZON) | Rizal | Binangonan | Calumpang | 14.4777 | 121.1888 | U | 18277 | 5076 | 1523 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040087 | FTAP Globe | 14.4766 | 121.1901 | 0.18 | Terrestrial Optical Fiber Drop | 1.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2146 | 3 | 146 | 2146 | 0307109013 | Region III (Central Luzon) | Zambales | San Antonio | Santiago | 14.9492 | 120.0879 | R | 1628 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 1.41 | Terrestrial Optical Fiber Drop | 0.29 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2147 | 3 | 147 | 2147 | 0405802003 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dela Paz | 14.5975 | 121.1726 | U | 73910 | 20530 | 6159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01716 | Edgepoint | 14.5948 | 121.1701 | 0.41 | Terrestrial Optical Fiber Drop | 1.12 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2148 | 3 | 148 | 2148 | 1004302005 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Binitinan | 8.7154 | 124.7775 | R | 3972 | 1018 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0001 | PTCI/MIDC | 8.7178 | 124.7811 | 0.48 | Terrestrial Optical Fiber Drop | 3.88 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2149 | 3 | 149 | 2149 | 0402115020 | Region IV-A (CALABARZON) | Cavite | Naic | Malainen Bago | 14.3079 | 120.7681 | U | 9906 | 2913 | 874 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040178 | FTAP Globe | 14.314 | 120.7694 | 0.7 | Terrestrial Optical Fiber Drop | 1.58 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2150 | 3 | 150 | 2150 | 0702206017 | Region VII (Central Visayas) | Cebu | Asturias | Owak | 10.5391 | 123.7179 | R | 5002 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 0.95 | Terrestrial Optical Fiber Drop | 3.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2151 | 3 | 151 | 2151 | 0604518011 | Region VI (Western Visayas) | Negros Occidental | Manapla | Santa Teresa | 10.9489 | 123.1718 | R | 3641 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0030 | PTCI/MIDC | 10.9496 | 123.1816 | 1.07 | Terrestrial Optical Fiber Drop | 4.65 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2152 | 3 | 152 | 2152 | 1208007018 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Malalag Cogon | 6.4053 | 125.289 | R | 4870 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSRG0013 | PTCI/MIDC | 6.4042 | 125.289 | 0.12 | Terrestrial Optical Fiber Drop | 8.09 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2153 | 3 | 153 | 2153 | 0500503045 | Region V (Bicol Region) | Albay | Daraga | Salvacion | 13.1749 | 123.6809 | U | 4365 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050171 | FTAP Globe | 13.1731 | 123.6842 | 0.4 | Terrestrial Optical Fiber Drop | 1.42 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2154 | 3 | 154 | 2154 | 0603045025 | Region VI (Western Visayas) | Iloilo | Tigbauan | Buyu-an | 10.6706 | 122.3575 | R | 3868 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060158 | FTAP BTS | 10.6758 | 122.3662 | 1.11 | Terrestrial Optical Fiber Drop | 2.75 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2155 | 3 | 155 | 2155 | 0203114054 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Manaring | 17.1719 | 121.9021 | R | 2729 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01289-B06 | PTCI/MIDC | 17.1737 | 121.9002 | 0.28 | Terrestrial Optical Fiber Drop | 1.69 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2156 | 3 | 156 | 2156 | 0907322045 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Tiguma | 7.8415 | 123.4568 | U | 13203 | 3385 | 1016 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090132 | FTAP Globe | 7.8421 | 123.4561 | 0.11 | Terrestrial Optical Fiber Drop | 2.27 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2157 | 3 | 157 | 2157 | 0102914024 | Region I (Ilocos Region) | Ilocos Sur | Narvacan | Quinarayan | 17.4449 | 120.4717 | R | 2782 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01266-B05 | PTCI/MIDC | 17.4497 | 120.463 | 1.06 | Terrestrial Optical Fiber Drop | 1.2 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2158 | 3 | 158 | 2158 | 0501736003 | Region V (Bicol Region) | Camarines Sur | Tigaon | Caraycayon | 13.6122 | 123.4855 | U | 4963 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 1.39 | Terrestrial Optical Fiber Drop | 2.39 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2159 | 3 | 159 | 2159 | 0603037004 | Region VI (Western Visayas) | Iloilo | Pototan | Barasan | 10.9558 | 122.6404 | R | 1988 | 523 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.88 | Terrestrial Optical Fiber Drop | 1.09 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2160 | 3 | 160 | 2160 | 0201514003 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Baua | 18.3495 | 122.0908 | R | 2350 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020009 | FTAP Globe | 18.3493 | 122.0877 | 0.32 | Terrestrial Optical Fiber Drop | 1.45 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2161 | 3 | 161 | 2161 | 0702232015 | Region VII (Central Visayas) | Cebu | Minglanilla | Tulay | 10.2391 | 123.7927 | U | 12101 | 3184 | 955 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0126 | PTCI/MIDC | 10.2361 | 123.7871 | 0.7 | Terrestrial Optical Fiber Drop | 1.28 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2162 | 3 | 162 | 2162 | 0304928019 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Soledad | 15.4286 | 120.9949 | U | 7394 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 0.91 | Terrestrial Optical Fiber Drop | 0.04 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2163 | 3 | 163 | 2163 | 0405813002 | Region IV-A (CALABARZON) | Rizal | Taytay | Muzon | 14.5432 | 121.1444 | U | 32623 | 9061 | 2718 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00794-A04 | PTCI/MIDC | 14.5422 | 121.1425 | 0.23 | Terrestrial Optical Fiber Drop | 1.97 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2164 | 3 | 164 | 2164 | 0305405034 | Region III (Central Luzon) | Pampanga | Candaba | Tenejero | 15.0195 | 120.8583 | U | 3465 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030500 | FTAP Globe | 15.019 | 120.8538 | 0.48 | Terrestrial Optical Fiber Drop | 1.42 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2165 | 3 | 165 | 2165 | 0701201001 | Region VII (Central Visayas) | Bohol | Alburquerque | Bahi | 9.6123 | 123.9445 | R | 1063 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 1.06 | Terrestrial Optical Fiber Drop | 0.81 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2166 | 3 | 166 | 2166 | 0330100014 | Region III (Central Luzon) | Pampanga | City of Angeles | Margot | 15.1714 | 120.5379 | U | 12771 | 3547 | 1064 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00784 (EP_PH-TAR-00784 / N1858) | EdgePoint | 15.2672 | 120.565 | 0.27 | Terrestrial Optical Fiber Drop | 1.49 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2167 | 3 | 167 | 2167 | 1001309010 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Kahusayan | 7.6171 | 125.1098 | R | 1688 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 1.21 | Terrestrial Optical Fiber Drop | 1.07 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2168 | 3 | 168 | 2168 | 0601912021 | Region VI (Western Visayas) | Capiz | Pontevedra | Rizal | 11.4369 | 122.8389 | R | 4445 | 1169 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060235 | FTAP Globe | 11.4291 | 122.8426 | 0.96 | Terrestrial Optical Fiber Drop | 4.59 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2169 | 3 | 169 | 2169 | 0301406008 | Region III (Central Luzon) | Bulacan | Bustos | Malamig | 14.9325 | 120.928 | U | 8005 | 2287 | 686 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01102-B07 | PTCI/MIDC | 14.9447 | 120.9241 | 1.42 | Terrestrial Optical Fiber Drop | 1.27 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2170 | 3 | 170 | 2170 | 0702222008 | Region VII (Central Visayas) | Cebu | Dalaguete | Casay | 9.8217 | 123.5503 | R | 4787 | 1259 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0003 | LDIC | 9.8666 | 123.5804 | 5.98 | Terrestrial Optical Fiber Drop | 6.94 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2171 | 3 | 171 | 2171 | 1102303006 | Region XI (Davao Region) | Davao del Norte | Carmen | Guadalupe | 7.3761 | 125.7392 | R | 3203 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110430 | FTAP Globe | 7.3754 | 125.7397 | 0.1 | Terrestrial Optical Fiber Drop | 1.13 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2172 | 3 | 172 | 2172 | 0405804037 | Region IV-A (CALABARZON) | Rizal | Binangonan | Layunan | 14.4695 | 121.1934 | U | 2465 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | G6338 | FTAP Smart | 14.4681 | 121.1914 | 0.27 | Terrestrial Optical Fiber Drop | 1.01 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2173 | 3 | 173 | 2173 | 0304919022 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Bagong Buhay | 15.4622 | 121.1163 | R | 760 | 217 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNEG0002 | PTCI/MIDC | 15.4539 | 121.1051 | 1.51 | Terrestrial Optical Fiber Drop | 0.04 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2174 | 3 | 174 | 2174 | 0305407023 | Region III (Central Luzon) | Pampanga | Guagua | San Pedro | 14.9653 | 120.6242 | U | 5779 | 1444 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030519 | FTAP Globe | 14.9629 | 120.6303 | 0.71 | Terrestrial Optical Fiber Drop | 1.02 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2175 | 3 | 175 | 2175 | 0105538003 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Banaoang | 15.9935 | 120.4316 | R | 4513 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00478 | Edgepoint | 15.9911 | 120.4345 | 0.41 | Terrestrial Optical Fiber Drop | 3.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2176 | 3 | 176 | 2176 | 0403403021 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Vicente | 14.3296 | 121.0779 | U | 10124 | 3067 | 920 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0035 | PTCI/MIDC | 14.3307 | 121.078 | 0.12 | Terrestrial Optical Fiber Drop | 1.03 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2177 | 3 | 177 | 2177 | 0301421004 | Region III (Central Luzon) | Bulacan | San Miguel | Bantog | 15.2112 | 120.9561 | U | 4134 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-00797 | Edgepoint | 15.2222 | 120.9532 | 1.27 | Terrestrial Optical Fiber Drop | 1.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2178 | 3 | 178 | 2178 | 1600301011 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Noli | 8.7428 | 125.7233 | R | 4844 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130083 | FTAP Globe | 8.735 | 125.754 | 3.48 | Terrestrial Optical Fiber Drop | 4.88 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2179 | 3 | 179 | 2179 | 0702202007 | Region VII (Central Visayas) | Cebu | Alcoy | Pugalo | 9.728 | 123.5082 | R | 2729 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 2.6 | Terrestrial Optical Fiber Drop | 2.17 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2180 | 3 | 180 | 2180 | 0401008016 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 1 | 13.8459 | 120.6323 | R | 4186 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 1.09 | Terrestrial Optical Fiber Drop | 1.78 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2181 | 3 | 181 | 2181 | 0103313014 | Region I (Ilocos Region) | La Union | Rosario | Concepcion | 16.2236 | 120.4695 | U | 3845 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02700-B05 | PTCI/MIDC | 16.2244 | 120.4789 | 1.01 | Terrestrial Optical Fiber Drop | 1.5 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2182 | 3 | 182 | 2182 | 0102817009 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Davila | 18.4681 | 120.5784 | R | 4050 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4932 | FTAP Smart | 18.4671 | 120.5793 | 0.15 | Terrestrial Optical Fiber Drop | 1.05 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2183 | 3 | 183 | 2183 | 0307105018 | Region III (Central Luzon) | Zambales | Iba | Santo Rosario | 15.3311 | 119.9654 | R | 4578 | 1204 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0011 | PTCI/MIDC | 15.3368 | 119.9669 | 0.65 | Terrestrial Optical Fiber Drop | 1.4 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2184 | 3 | 184 | 2184 | 0403424006 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-B | 14.0648 | 121.3215 | R | 2031 | 615 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 1.06 | Terrestrial Optical Fiber Drop | 1.06 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2185 | 3 | 185 | 2185 | 0500517027 | Region V (Bicol Region) | Albay | City of Tabaco | Panal | 13.3568 | 123.7195 | U | 3517 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.68 | Terrestrial Optical Fiber Drop | 1.36 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2186 | 3 | 186 | 2186 | 0301415012 | Region III (Central Luzon) | Bulacan | Pandi | Mapulang Lupa | 14.8803 | 120.9651 | U | 31602 | 9029 | 2709 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BUL_0004 | LDIC | 14.8798 | 120.9728 | 0.83 | Terrestrial Optical Fiber Drop | 1.13 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2187 | 3 | 187 | 2187 | 0600407008 | Region VI (Western Visayas) | Aklan | Kalibo | Estancia | 11.6873 | 122.3661 | U | 9882 | 2533 | 760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0016 | PTCI/MIDC | 11.6816 | 122.3635 | 0.69 | Terrestrial Optical Fiber Drop | 1.14 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2188 | 3 | 188 | 2188 | 1705209021 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Panggulayan | 13.0482 | 121.4585 | R | 2823 | 723 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170096 | FTAP Globe | 13.0506 | 121.4483 | 1.14 | Terrestrial Optical Fiber Drop | 2.13 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2189 | 3 | 189 | 2189 | 0501736018 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Antonio | 13.6449 | 123.4997 | R | 2983 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.94 | Terrestrial Optical Fiber Drop | 1.65 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2190 | 3 | 190 | 2190 | 0500506055 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 38 - Gogon | 13.1554 | 123.7449 | U | 6177 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050172 | FTAP Globe | 13.156 | 123.7413 | 0.4 | Terrestrial Optical Fiber Drop | 1.99 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2191 | 3 | 191 | 2191 | 1004301008 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Lumbo | 8.5716 | 124.4591 | R | 2229 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100122 | FTAP Globe | 8.5696 | 124.4727 | 1.51 | Terrestrial Optical Fiber Drop | 1.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2192 | 3 | 192 | 2192 | 0405645040 | Region IV-A (CALABARZON) | Quezon | Sariaya | Sampaloc 2 | 13.9537 | 121.506 | U | 6126 | 1612 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040416 | FTAP Globe | 13.9577 | 121.5077 | 0.48 | Terrestrial Optical Fiber Drop | 1.47 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2193 | 3 | 193 | 2193 | 0702221014 | Region VII (Central Visayas) | Cebu | Daanbantayan | Pajo | 11.2361 | 124.0125 | R | 4554 | 1198 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0070 | PTCI/MIDC | 11.2467 | 124.0163 | 1.25 | Terrestrial Optical Fiber Drop | 1.55 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2194 | 3 | 194 | 2194 | 0402118045 | Region IV-A (CALABARZON) | Cavite | Silang | Tartaria | 14.2036 | 121.0229 | U | 16542 | 4865 | 1460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02231-C08 | PTCI/MIDC | 14.2027 | 121.0216 | 0.17 | Terrestrial Optical Fiber Drop | 2.37 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2195 | 3 | 195 | 2195 | 0305403020 | Region III (Central Luzon) | Pampanga | Arayat | San Agustin Norte | 15.1636 | 120.7791 | R | 3848 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01596-B07 | PTCI/MIDC | 15.1652 | 120.7792 | 0.18 | Terrestrial Optical Fiber Drop | 2.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2196 | 3 | 196 | 2196 | 0803738018 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Curva | 11.0323 | 124.5243 | R | 3396 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0044 | PTCI/MIDC | 11.0146 | 124.5305 | 2.08 | Terrestrial Optical Fiber Drop | 3.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2197 | 3 | 197 | 2197 | 0304917029 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion West | 15.7204 | 120.9041 | U | 3539 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0027 | PTCI/MIDC | 15.7254 | 120.9006 | 0.54 | Terrestrial Optical Fiber Drop | 0.54 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2198 | 3 | 198 | 2198 | 0403424058 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Marcos | 14.1049 | 121.3013 | R | 3021 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040314 | FTAP Globe | 14.1042 | 121.3036 | 0.26 | Terrestrial Optical Fiber Drop | 3.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2199 | 3 | 199 | 2199 | 1600209009 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Kinabjangan | 8.9744 | 125.3601 | R | 3980 | 970 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130068 | FTAP Globe | 8.9748 | 125.3618 | 0.19 | Terrestrial Optical Fiber Drop | 1.47 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2200 | 3 | 200 | 2200 | 0203114003 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Alibagu | 17.1011 | 121.8607 | U | 8201 | 2158 | 647 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00181 | Edgepoint | 17.1003 | 121.8622 | 0.19 | Terrestrial Optical Fiber Drop | 1.9 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2201 | 3 | 201 | 2201 | 0405645027 | Region IV-A (CALABARZON) | Quezon | Sariaya | Manggalang-Bantilan | 13.8361 | 121.4327 | R | 3636 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03252-C08 | PTCI/MIDC | 13.8382 | 121.449 | 1.78 | Terrestrial Optical Fiber Drop | 4.07 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2202 | 3 | 202 | 2202 | 0702218011 | Region VII (Central Visayas) | Cebu | Compostela | Magay | 10.4716 | 124.0188 | R | 3878 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070185 | FTAP BTS | 10.468 | 124.0168 | 0.45 | Terrestrial Optical Fiber Drop | 2.29 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2203 | 3 | 203 | 2203 | 0603026004 | Region VI (Western Visayas) | Iloilo | Leganes | Cagamutan Norte | 10.8122 | 122.6013 | R | 2555 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060040 | FTAP BTS | 10.805 | 122.5973 | 0.91 | Terrestrial Optical Fiber Drop | 2.12 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2204 | 3 | 204 | 2204 | 0501708024 | Region V (Bicol Region) | Camarines Sur | Calabanga | Paolbo | 13.7187 | 123.2502 | R | 4370 | 1040 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-02606 | Edgepoint | 13.7165 | 123.2373 | 1.42 | Terrestrial Optical Fiber Drop | 2.76 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2205 | 3 | 205 | 2205 | 1004308031 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Pangasihan | 8.8611 | 125.1703 | R | 2808 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0094 | PTCI/MIDC | 8.864 | 125.1706 | 0.33 | Terrestrial Optical Fiber Drop | 2.5 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2206 | 3 | 206 | 2206 | 0301421015 | Region III (Central Luzon) | Bulacan | San Miguel | Bulualto | 15.2199 | 120.9539 | R | 3021 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00797 | Edgepoint | 15.2222 | 120.9532 | 0.27 | Terrestrial Optical Fiber Drop | 0.43 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2207 | 3 | 207 | 2207 | 0102804001 | Region I (Ilocos Region) | Ilocos Norte | Bangui | Abaca | 18.5321 | 120.7561 | R | 1870 | 505 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-03184 | Edgepoint | 18.5335 | 120.7602 | 0.46 | Terrestrial Optical Fiber Drop | 1.43 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2208 | 3 | 208 | 2208 | 0300804042 | Region III (Central Luzon) | Bataan | Dinalupihan | Tucop | 14.8973 | 120.4726 | R | 4784 | 1328 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3937 | FTAP Smart | 14.8987 | 120.4736 | 0.19 | Terrestrial Optical Fiber Drop | 3.69 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2209 | 3 | 209 | 2209 | 0301423015 | Region III (Central Luzon) | Bulacan | Santa Maria | Parada | 14.8102 | 120.9865 | U | 9845 | 2812 | 844 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01012-B07 | PTCI/MIDC | 14.8101 | 120.9911 | 0.49 | Terrestrial Optical Fiber Drop | 1.17 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2210 | 3 | 210 | 2210 | 0500501006 | Region V (Bicol Region) | Albay | Bacacay | Bonga | 13.2873 | 123.7573 | U | 8025 | 1957 | 587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050147 | FTAP Globe | 13.2832 | 123.7577 | 0.46 | Terrestrial Optical Fiber Drop | 2.81 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2211 | 3 | 211 | 2211 | 0304908017 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Niño | 15.3051 | 120.9435 | U | 5470 | 1562 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00765 | Edgepoint | 15.3098 | 120.9441 | 0.53 | Terrestrial Optical Fiber Drop | 0.04 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2212 | 3 | 212 | 2212 | 0501727016 | Region V (Bicol Region) | Camarines Sur | Pasacao | Santa Rosa Del Norte | 13.5138 | 123.0427 | U | 4126 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0005 | PTCI/MIDC | 13.5171 | 123.0437 | 0.38 | Terrestrial Optical Fiber Drop | 1.39 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2213 | 3 | 213 | 2213 | 0702250012 | Region VII (Central Visayas) | Cebu | City of Talisay | Poblacion | 10.2455 | 123.8446 | U | 10556 | 2777 | 833 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0228 | PTCI/MIDC | 10.2395 | 123.8406 | 0.8 | Terrestrial Optical Fiber Drop | 0.4 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2214 | 3 | 214 | 2214 | 1600212003 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | Basilisa | 9.0664 | 125.5807 | R | 2410 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 1.57 | Terrestrial Optical Fiber Drop | 1.69 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2215 | 3 | 215 | 2215 | 0304909026 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Talabutab Sur | 15.57 | 121.0645 | R | 2826 | 807 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03339-B07 | PTCI/MIDC | 15.5689 | 121.0628 | 0.22 | Terrestrial Optical Fiber Drop | 2.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2216 | 3 | 216 | 2216 | 0803726008 | Region VIII (Eastern Visayas) | Leyte | Kananga | Lonoy | 11.2078 | 124.5673 | R | 3057 | 804 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 3.33 | Terrestrial Optical Fiber Drop | 2.61 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2217 | 3 | 217 | 2217 | 1004313002 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Dampil | 8.8265 | 124.7905 | R | 3042 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 2.24 | Terrestrial Optical Fiber Drop | 2.38 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2218 | 3 | 218 | 2218 | 1102414024 | Region XI (Davao Region) | Davao del Sur | Sulop | Talas | 6.6165 | 125.3454 | R | 2115 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110531 | FTAP Globe | 6.6039 | 125.3444 | 1.4 | Terrestrial Optical Fiber Drop | 1.96 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2219 | 3 | 219 | 2219 | 0702248008 | Region VII (Central Visayas) | Cebu | Tabogon | Ilihan | 10.9024 | 123.9675 | R | 3904 | 1027 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070307 | FTAP Globe | 10.9294 | 123.9607 | 3.09 | Terrestrial Optical Fiber Drop | 7.16 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2220 | 3 | 220 | 2220 | 0403424059 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Mateo | 14.112 | 121.299 | R | 3443 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040307 | FTAP Globe | 14.1123 | 121.3045 | 0.59 | Terrestrial Optical Fiber Drop | 3.92 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2221 | 3 | 221 | 2221 | 0600402001 | Region VI (Western Visayas) | Aklan | Balete | Aranas | 11.5645 | 122.3961 | U | 5782 | 1482 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 3.87 | Terrestrial Optical Fiber Drop | 2.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2222 | 3 | 222 | 2222 | 1102502007 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Maputi | 7.0432 | 125.9655 | R | 4199 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTDLG0038 | PTCI/MIDC | 7.0669 | 125.9606 | 2.69 | Terrestrial Optical Fiber Drop | 10.33 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2223 | 3 | 223 | 2223 | 0300805014 | Region III (Central Luzon) | Bataan | Hermosa | Palihan | 14.8438 | 120.4732 | U | 6848 | 1902 | 571 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1505 | FTAP Smart | 14.8402 | 120.4776 | 0.62 | Terrestrial Optical Fiber Drop | 1.9 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2224 | 3 | 224 | 2224 | 0105517009 | Region I (Ilocos Region) | Pangasinan | Calasiao | Gabon | 16.0114 | 120.3617 | R | 3050 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01748-B07 | PTCI/MIDC | 16.0133 | 120.3586 | 0.39 | Terrestrial Optical Fiber Drop | 2.8 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2225 | 3 | 225 | 2225 | 0203120012 | Region II (Cagayan Valley) | Isabela | Naguilian | Palattao | 17.0044 | 121.8259 | R | 2714 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01356-B06 | PTCI/MIDC | 17.0051 | 121.8251 | 0.11 | Terrestrial Optical Fiber Drop | 1.14 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2226 | 3 | 226 | 2226 | 0307114009 | Region III (Central Luzon) | Zambales | Subic | Calapandayan | 14.8738 | 120.2355 | U | 10846 | 2854 | 856 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0019 | PTCI/MIDC | 14.8723 | 120.2383 | 0.35 | Terrestrial Optical Fiber Drop | 1.71 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2227 | 3 | 227 | 2227 | 0702215015 | Region VII (Central Visayas) | Cebu | Carmen | Luyang | 10.6009 | 124.0224 | U | 6739 | 1773 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070028 | FTAP BTS | 10.6051 | 124.0252 | 0.56 | Terrestrial Optical Fiber Drop | 2.71 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2228 | 3 | 228 | 2228 | 0702239012 | Region VII (Central Visayas) | Cebu | Ronda | Santa Cruz | 10.0124 | 123.4126 | R | 3654 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0264 | PTCI/MIDC | 10.0263 | 123.4161 | 1.6 | Terrestrial Optical Fiber Drop | 1.47 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2229 | 3 | 229 | 2229 | 0402112014 | Region IV-A (CALABARZON) | Cavite | Magallanes | Kabulusan | 14.1789 | 120.7447 | R | 1952 | 574 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040272 | FTAP Globe | 14.1766 | 120.7389 | 0.68 | Terrestrial Optical Fiber Drop | 1.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2230 | 3 | 230 | 2230 | 0501603021 | Region V (Bicol Region) | Camarines Norte | Daet | Mancruz | 14.0965 | 122.9552 | R | 3490 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAN-03170 | Edgepoint | 14.0939 | 122.9489 | 0.74 | Terrestrial Optical Fiber Drop | 2.01 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2231 | 3 | 231 | 2231 | 0401020021 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Pansol | 13.8861 | 121.2476 | R | 4860 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040514 | FTAP Globe | 13.8971 | 121.2443 | 1.27 | Terrestrial Optical Fiber Drop | 2.69 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2232 | 3 | 232 | 2232 | 0803708057 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Plaridel | 10.5647 | 124.7646 | R | 3711 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0010 | PTCI/MIDC | 10.5624 | 124.7653 | 0.27 | Terrestrial Optical Fiber Drop | 13.39 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2233 | 3 | 233 | 2233 | 0403405004 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barandal | 14.1885 | 121.1302 | U | 19814 | 6004 | 1801 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.35 | Terrestrial Optical Fiber Drop | 1.98 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2234 | 3 | 234 | 2234 | 0401019003 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Banilad | 14.0674 | 120.7343 | U | 5158 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040339 | FTAP Globe | 14.0802 | 120.7249 | 1.75 | Terrestrial Optical Fiber Drop | 2.07 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2235 | 3 | 235 | 2235 | 0301422009 | Region III (Central Luzon) | Bulacan | San Rafael | Capihan | 14.9975 | 120.9304 | U | 6405 | 1830 | 549 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00949 | Edgepoint | 15.0009 | 120.9306 | 0.37 | Terrestrial Optical Fiber Drop | 1.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2236 | 3 | 236 | 2236 | 0105533014 | Region I (Ilocos Region) | Pangasinan | San Fabian | Longos | 16.1059 | 120.3952 | R | 2872 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02184 | Edgepoint | 16.0971 | 120.3938 | 0.99 | Terrestrial Optical Fiber Drop | 1.19 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2237 | 3 | 237 | 2237 | 0403404003 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banlic | 14.2316 | 121.1371 | U | 22631 | 6857 | 2057 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040231 | FTAP Globe | 14.2324 | 121.1364 | 0.11 | Terrestrial Optical Fiber Drop | 1.82 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2238 | 3 | 238 | 2238 | 0702214001 | Region VII (Central Visayas) | Cebu | City of Carcar | Bolinawan | 10.0896 | 123.6331 | U | 13804 | 3632 | 1090 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0022 | PTCI/MIDC | 10.0841 | 123.6309 | 0.66 | Terrestrial Optical Fiber Drop | 1.36 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2239 | 3 | 239 | 2239 | 1402705013 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Poblacion East | 16.65 | 121.2211 | R | 2037 | 522 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_IFU_0002 | LDIC | 121.2223 | 16.654 | 0.47 | Terrestrial Optical Fiber Drop | 1.09 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2240 | 3 | 240 | 2240 | 0401009007 | Region IV-A (CALABARZON) | Batangas | Cuenca | Dita | 13.917 | 121.0731 | R | 4793 | 1331 | 399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4164 | FTAP Smart | 13.9218 | 121.0718 | 0.54 | Terrestrial Optical Fiber Drop | 3.3 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2241 | 3 | 241 | 2241 | 0305413044 | Region III (Central Luzon) | Pampanga | Mexico | Sapang Maisac | 15.1809 | 120.6281 | U | 8578 | 2144 | 643 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01629-B07 | PTCI/MIDC | 15.1801 | 120.6295 | 0.18 | Terrestrial Optical Fiber Drop | 2.45 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2242 | 3 | 242 | 2242 | 1102303007 | Region XI (Davao Region) | Davao del Norte | Carmen | Ising | 7.3598 | 125.7063 | U | 14442 | 3903 | 1171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110326 | FTAP BTS | 7.3553 | 125.708 | 0.54 | Terrestrial Optical Fiber Drop | 1.01 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2243 | 3 | 243 | 2243 | 0301406005 | Region III (Central Luzon) | Bulacan | Bustos | Cambaog | 14.928 | 120.8966 | U | 6899 | 1971 | 591 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01030 | Edgepoint | 14.9277 | 120.8939 | 0.3 | Terrestrial Optical Fiber Drop | 2.41 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2244 | 3 | 244 | 2244 | 0201516034 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Sta. Maria | 18.1471 | 121.6611 | R | 2451 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 1.34 | Terrestrial Optical Fiber Drop | 2.84 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2245 | 3 | 245 | 2245 | 0304926012 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Malasin | 15.8074 | 121.0007 | U | 9389 | 2682 | 805 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0194 | FTAP Smart | 15.8027 | 120.9985 | 0.57 | Terrestrial Optical Fiber Drop | 1.98 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2246 | 3 | 246 | 2246 | 0306907019 | Region III (Central Luzon) | Tarlac | La Paz | San Isidro | 15.4413 | 120.728 | U | 3771 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.09 | Terrestrial Optical Fiber Drop | 1.31 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2247 | 3 | 247 | 2247 | 0307113011 | Region III (Central Luzon) | Zambales | Santa Cruz | Lipay | 15.7492 | 119.9092 | U | 6760 | 1778 | 533 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0008 | PTCI/MIDC | 15.7531 | 119.9154 | 0.79 | Terrestrial Optical Fiber Drop | 2.07 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2248 | 3 | 248 | 2248 | 1108211002 | Region XI (Davao Region) | Davao de Oro | Pantukan | Bongbong | 7.1076 | 125.9083 | R | 4676 | 1263 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCVG0011 | PTCI/MIDC | 7.1283 | 125.8981 | 2.56 | Terrestrial Optical Fiber Drop | 3.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2249 | 3 | 249 | 2249 | 0304911056 | Region III (Central Luzon) | Nueva Ecija | Guimba | San Roque | 15.6578 | 120.7599 | U | 6874 | 1964 | 589 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02180 | Edgepoint | 15.2484 | 120.9527 | 0.77 | Terrestrial Optical Fiber Drop | 0.73 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2250 | 3 | 250 | 2250 | 0931700088 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Tictapul | 7.4044 | 122.315 | R | 3677 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH090167 | FTAP Globe | 7.4165 | 122.325 | 1.73 | Terrestrial Optical Fiber Drop | 19.17 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2251 | 3 | 251 | 2251 | 0105503031 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | San Vicente | 16.14 | 119.9933 | U | 4473 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010127 | FTAP Globe | 16.1319 | 119.9976 | 1.02 | Terrestrial Optical Fiber Drop | 1.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2252 | 3 | 252 | 2252 | 0702245004 | Region VII (Central Visayas) | Cebu | Santander | Liloan | 9.4219 | 123.3091 | R | 2383 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0251 | PTCI/MIDC | 9.444 | 123.3042 | 2.5 | Terrestrial Optical Fiber Drop | 2.5 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2253 | 3 | 253 | 2253 | 0305415017 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Libutad | 15.1075 | 120.5624 | U | 5916 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-00869 | Edgepoint | 15.1162 | 120.5663 | 1.06 | Terrestrial Optical Fiber Drop | 1.48 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2254 | 3 | 254 | 2254 | 0702240011 | Region VII (Central Visayas) | Cebu | Samboan | Poblacion | 9.5325 | 123.3063 | R | 3975 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0143 | PTCI/MIDC | 9.5262 | 123.3076 | 0.71 | Terrestrial Optical Fiber Drop | 12.19 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2255 | 3 | 255 | 2255 | 0304908011 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Nicolas | 15.3037 | 120.9361 | U | 14324 | 4092 | 1228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030051 | FTAP BTS | 15.3014 | 120.9329 | 0.43 | Terrestrial Optical Fiber Drop | 0.04 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2256 | 3 | 256 | 2256 | 0401020023 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Poblacion | 13.8794 | 121.2092 | U | 3461 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 0.82 | Terrestrial Optical Fiber Drop | 1.65 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2257 | 3 | 257 | 2257 | 0304932003 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Carmen | 15.4456 | 120.8278 | R | 3949 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01502-B07 | PTCI/MIDC | 15.4529 | 120.8084 | 2.24 | Terrestrial Optical Fiber Drop | 4.1 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2258 | 3 | 258 | 2258 | 0803702005 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Binongto-an | 11.2159 | 124.8269 | R | 2525 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 1.86 | Terrestrial Optical Fiber Drop | 1.64 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2259 | 3 | 259 | 2259 | 0600407015 | Region VI (Western Visayas) | Aklan | Kalibo | Tigayon | 11.6738 | 122.3609 | U | 6328 | 1622 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0016 | PTCI/MIDC | 11.6816 | 122.3635 | 0.91 | Terrestrial Optical Fiber Drop | 2.71 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2260 | 3 | 260 | 2260 | 0105512024 | Region I (Ilocos Region) | Pangasinan | Binalonan | Sumabnit | 16.0307 | 120.5822 | U | 4988 | 1385 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00450 | Edgepoint | 16.0229 | 120.5792 | 0.92 | Terrestrial Optical Fiber Drop | 1.55 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2261 | 3 | 261 | 2261 | 0401022022 | Region IV-A (CALABARZON) | Batangas | San Jose | Pinagtung-Ulan | 13.9235 | 121.0832 | R | 4879 | 1355 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040466 | FTAP Globe | 13.9262 | 121.0878 | 0.57 | Terrestrial Optical Fiber Drop | 4.22 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2262 | 3 | 262 | 2262 | 0401034016 | Region IV-A (CALABARZON) | Batangas | Tuy | Rillo | 14.0217 | 120.7299 | U | 2660 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1398 | FTAP Smart | 14.0064 | 120.7303 | 0.6 | Terrestrial Optical Fiber Drop | 0.17 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2263 | 3 | 263 | 2263 | 0403415007 | Region IV-A (CALABARZON) | Laguna | Magdalena | Buenavista | 14.2246 | 121.4288 | R | 2699 | 817 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 2.61 | Terrestrial Optical Fiber Drop | 2.9 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2264 | 3 | 264 | 2264 | 0203126014 | Region II (Cagayan Valley) | Isabela | Roxas | Luna | 17.116 | 121.6248 | R | 1583 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01359-B06 | PTCI/MIDC | 17.1149 | 121.6222 | 0.3 | Terrestrial Optical Fiber Drop | 1.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2265 | 3 | 265 | 2265 | 0401008003 | Region IV-A (CALABARZON) | Batangas | Calatagan | Balibago | 13.9271 | 120.6276 | R | 3963 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040474 | FTAP Globe | 13.9239 | 120.6238 | 0.55 | Terrestrial Optical Fiber Drop | 2.69 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2266 | 3 | 266 | 2266 | 0102903029 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Tay-ac | 17.6102 | 120.4458 | R | 2644 | 695 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010054 | FTAP Globe | 17.2614 | 120.5377 | 2.32 | Terrestrial Optical Fiber Drop | 5.35 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2267 | 3 | 267 | 2267 | 0500517036 | Region V (Bicol Region) | Albay | City of Tabaco | San Antonio | 13.3488 | 123.6793 | R | 4907 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 2.32 | Terrestrial Optical Fiber Drop | 2.06 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2268 | 3 | 268 | 2268 | 0702251028 | Region VII (Central Visayas) | Cebu | City of Toledo | Poblacion | 10.3796 | 123.6415 | U | 15924 | 4190 | 1257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0172 | PTCI/MIDC | 10.3817 | 123.6436 | 0.33 | Terrestrial Optical Fiber Drop | 2.76 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2269 | 3 | 269 | 2269 | 0305411020 | Region III (Central Luzon) | Pampanga | Magalang | Santa Cruz | 15.2103 | 120.6621 | U | 7765 | 1941 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03221-B07 | PTCI/MIDC | 15.211 | 120.6581 | 0.44 | Terrestrial Optical Fiber Drop | 2.26 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2270 | 3 | 270 | 2270 | 1001302015 | Region X (Northern Mindanao) | Bukidnon | Damulog | Poblacion | 7.4837 | 124.9439 | R | 5479 | 1441 | 432 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0004 | PTCI/MIDC | 7.4878 | 124.9412 | 0.55 | Terrestrial Optical Fiber Drop | 9.96 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2271 | 3 | 271 | 2271 | 1004314010 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Sinai | 8.5777 | 124.4284 | R | 2506 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 2.18 | Terrestrial Optical Fiber Drop | 1.71 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2272 | 3 | 272 | 2272 | 0105538017 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Minien West | 15.9786 | 120.4727 | U | 5272 | 1464 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00487 | Edgepoint | 15.9796 | 120.4704 | 0.27 | Terrestrial Optical Fiber Drop | 1.49 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2273 | 3 | 273 | 2273 | 0405628018 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ibabang Cambuga | 13.5848 | 122.4592 | R | 3750 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040617 | FTAP Globe | 13.6148 | 122.5239 | 7.74 | Terrestrial Optical Fiber Drop | 2.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2274 | 3 | 274 | 2274 | 0908313029 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Siay | Monching | 7.7282 | 122.8438 | R | 4117 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH090144 | FTAP Globe | 7.7505 | 122.8299 | 2.9 | Terrestrial Optical Fiber Drop | 23.28 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2275 | 3 | 275 | 2275 | 1600302006 | Region XIII (Caraga) | Agusan del Sur | Bunawan | San Andres | 8.2025 | 125.9939 | R | 4413 | 1131 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0009 | PTCI/MIDC | 8.2105 | 125.9905 | 0.96 | Terrestrial Optical Fiber Drop | 2.49 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2276 | 3 | 276 | 2276 | 0307105012 | Region III (Central Luzon) | Zambales | Iba | Palanginan | 15.3171 | 119.9916 | U | 11507 | 3028 | 908 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030417 | FTAP Globe | 15.3178 | 119.9943 | 0.3 | Terrestrial Optical Fiber Drop | 1.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2277 | 3 | 277 | 2277 | 0701216001 | Region VII (Central Visayas) | Bohol | Cortes | De la Paz | 9.701 | 123.8677 | R | 2987 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0011 | PTCI/MIDC | 9.7063 | 123.8715 | 0.72 | Terrestrial Optical Fiber Drop | 2.52 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2278 | 3 | 278 | 2278 | 0301406012 | Region III (Central Luzon) | Bulacan | Bustos | Talampas | 14.9312 | 120.9068 | R | 3802 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01022 | Edgepoint | 14.9338 | 120.9094 | 0.4 | Terrestrial Optical Fiber Drop | 2.69 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2279 | 3 | 279 | 2279 | 1108207004 | Region XI (Davao Region) | Davao de Oro | Monkayo | Baylo | 7.8539 | 126.071 | R | 4017 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0015 | PTCI/MIDC | 7.8475 | 126.0672 | 0.83 | Terrestrial Optical Fiber Drop | 3.37 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2280 | 3 | 280 | 2280 | 1004320005 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Maputi | 8.4477 | 124.293 | R | 3099 | 794 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0071 | PTCI/MIDC | 8.4328 | 124.2889 | 1.71 | Terrestrial Optical Fiber Drop | 1.82 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2281 | 3 | 281 | 2281 | 1606706002 | Region XIII (Caraga) | Surigao del Norte | Claver | Cagdianao | 9.5311 | 125.8618 | R | 4433 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130017 | FTAP BTS | 9.5401 | 125.841 | 2.49 | Terrestrial Optical Fiber Drop | 20.49 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2282 | 3 | 282 | 2282 | 0201525011 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Simpatuyo | 18.2478 | 121.8957 | R | 2746 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0015 | LDIC | 18.2484 | 121.8962 | 0.08 | Terrestrial Optical Fiber Drop | 1.63 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2283 | 3 | 283 | 2283 | 0501715008 | Region V (Bicol Region) | Camarines Sur | Goa | Catagbacan | 13.6727 | 123.5006 | R | 4540 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-02602 | Edgepoint | 13.6957 | 123.4931 | 2.68 | Terrestrial Optical Fiber Drop | 2.85 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2284 | 3 | 284 | 2284 | 0603047014 | Region VI (Western Visayas) | Iloilo | Zarraga | Malunang | 10.8202 | 122.6078 | R | 1479 | 389 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.17 | Terrestrial Optical Fiber Drop | 1.06 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2285 | 3 | 285 | 2285 | 0402118010 | Region IV-A (CALABARZON) | Cavite | Silang | Bucal | 14.283 | 120.9602 | R | 2192 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.18 | Terrestrial Optical Fiber Drop | 1.9 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2286 | 3 | 286 | 2286 | 0402120007 | Region IV-A (CALABARZON) | Cavite | Tanza | Calibuyo | 14.3584 | 120.8068 | U | 6930 | 2038 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02640-C08 | PTCI/MIDC | 14.359 | 120.8103 | 0.38 | Terrestrial Optical Fiber Drop | 2.16 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2287 | 3 | 287 | 2287 | 0301404009 | Region III (Central Luzon) | Bulacan | Bocaue | Bunlo | 14.7882 | 120.932 | U | 4200 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02208 | Edgepoint | 14.7838 | 120.934 | 0.53 | Terrestrial Optical Fiber Drop | 1.04 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2288 | 3 | 288 | 2288 | 1001312025 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Patpat | 8.1954 | 125.0607 | U | 4885 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100176 | FTAP Globe | 8.1951 | 125.0658 | 0.56 | Terrestrial Optical Fiber Drop | 1.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2289 | 3 | 289 | 2289 | 0604529009 | Region VI (Western Visayas) | Negros Occidental | Toboso | Tabun-ac | 10.7284 | 123.4875 | R | 4046 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060338 | FTAP Globe | 10.7452 | 123.4815 | 1.99 | Terrestrial Optical Fiber Drop | 12.71 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2290 | 3 | 290 | 2290 | 1004304001 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Dampias | 8.9082 | 124.7861 | R | 1057 | 271 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 4.93 | Terrestrial Optical Fiber Drop | 1.07 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2291 | 3 | 291 | 2291 | 0702233013 | Region VII (Central Visayas) | Cebu | Moalboal | Tomonoy | 9.9305 | 123.4005 | R | 2694 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 2.52 | Terrestrial Optical Fiber Drop | 1.1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2292 | 3 | 292 | 2292 | 0702252040 | Region VII (Central Visayas) | Cebu | Tuburan | Putat | 10.7987 | 123.8553 | R | 4978 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0178 | PTCI/MIDC | 10.7864 | 123.8481 | 1.57 | Terrestrial Optical Fiber Drop | 17.08 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2293 | 3 | 293 | 2293 | 0306910011 | Region III (Central Luzon) | Tarlac | Paniqui | Carino | 15.6463 | 120.5887 | U | 5420 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00618 | Edgepoint | 15.6463 | 120.5901 | 0.16 | Terrestrial Optical Fiber Drop | 2.42 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2294 | 3 | 294 | 2294 | 0301421037 | Region III (Central Luzon) | Bulacan | San Miguel | Poblacion | 15.1443 | 120.9769 | R | 3269 | 934 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00845 | Edgepoint | 15.1441 | 120.9747 | 0.24 | Terrestrial Optical Fiber Drop | 1.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2295 | 3 | 295 | 2295 | 0500508053 | Region V (Bicol Region) | Albay | City of Ligao | Tuburan | 13.2382 | 123.5512 | U | 6437 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 1.38 | Terrestrial Optical Fiber Drop | 1.73 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2296 | 3 | 296 | 2296 | 0306916068 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Miguel | 15.4376 | 120.5982 | U | 8881 | 2277 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030399 | FTAP Globe | 15.4372 | 120.6017 | 0.38 | Terrestrial Optical Fiber Drop | 2.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2297 | 3 | 297 | 2297 | 0105543010 | Region I (Ilocos Region) | Pangasinan | Tayug | Libertad | 16.018 | 120.7583 | R | 2635 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01767-B07 | PTCI/MIDC | 16.0297 | 120.7499 | 1.58 | Terrestrial Optical Fiber Drop | 1.54 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2298 | 3 | 298 | 2298 | 0603027021 | Region VI (Western Visayas) | Iloilo | Lemery | Poblacion SE Zone | 11.2114 | 122.9108 | R | 2853 | 750 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0048 | PTCI/MIDC | 11.2198 | 122.9209 | 1.44 | Terrestrial Optical Fiber Drop | 2.49 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2299 | 3 | 299 | 2299 | 0403401008 | Region IV-A (CALABARZON) | Laguna | Alaminos | San Andres | 14.0595 | 121.218 | R | 4903 | 1485 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_BAT_0016 | LDIC | 121.1983 | 14.0565 | 2.15 | Terrestrial Optical Fiber Drop | 4.54 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2300 | 3 | 300 | 2300 | 0301419028 | Region III (Central Luzon) | Bulacan | San Ildefonso | San Juan | 15.0833 | 120.9393 | U | 5212 | 1489 | 447 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030477 | FTAP Globe | 15.082 | 120.9387 | 0.16 | Terrestrial Optical Fiber Drop | 1.11 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2301 | 3 | 301 | 2301 | 0300804032 | Region III (Central Luzon) | Bataan | Dinalupihan | Saguing | 14.8618 | 120.4406 | U | 5424 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02573 | Edgepoint | 14.8612 | 120.4383 | 0.26 | Terrestrial Optical Fiber Drop | 1.81 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2302 | 3 | 302 | 2302 | 1102303019 | Region XI (Davao Region) | Davao del Norte | Carmen | Santo Niño | 7.3358 | 125.6952 | U | 6314 | 1706 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0003 | PTCI/MIDC | 7.3381 | 125.6955 | 0.25 | Terrestrial Optical Fiber Drop | 1.99 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2303 | 3 | 303 | 2303 | 0701205005 | Region VII (Central Visayas) | Bohol | Baclayon | Landican | 9.6291 | 123.9055 | R | 1010 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070157 | FTAP BTS | 9.654 | 123.8788 | 4.02 | Terrestrial Optical Fiber Drop | 1.04 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2304 | 3 | 304 | 2304 | 1003512001 | Region X (Northern Mindanao) | Lanao del Norte | Maigo | Balagatasa | 8.1479 | 123.9403 | R | 4786 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100180 | FTAP Globe | 8.1602 | 123.961 | 2.66 | Terrestrial Optical Fiber Drop | 19.43 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2305 | 3 | 305 | 2305 | 0730600057 | Region VII (Central Visayas) | Cebu | City of Cebu | Pit-os | 10.3941 | 123.922 | U | 7761 | 2425 | 728 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070321 | FTAP Globe | 10.3983 | 123.9199 | 0.52 | Terrestrial Optical Fiber Drop | 2.7 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2306 | 3 | 306 | 2306 | 1004310013 | Region X (Northern Mindanao) | Misamis Oriental | Initao | San Pedro | 8.4875 | 124.2968 | R | 3162 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0051 | PTCI/MIDC | 8.477 | 124.2967 | 1.17 | Terrestrial Optical Fiber Drop | 1.9 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2307 | 3 | 307 | 2307 | 0205002004 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Bone South | 16.242 | 120.9934 | R | 4916 | 1293 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00377 | Edgepoint | 16.2448 | 120.9951 | 0.37 | Terrestrial Optical Fiber Drop | 8.59 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2308 | 3 | 308 | 2308 | 0601914036 | Region VI (Western Visayas) | Capiz | City of Roxas | Loctugan | 11.5102 | 122.7661 | R | 2447 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAP-03142 | Edgepoint | 11.5148 | 122.7618 | 0.69 | Terrestrial Optical Fiber Drop | 1.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2309 | 3 | 309 | 2309 | 0631000011 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Balantang | 10.7567 | 122.5739 | U | 4930 | 1173 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.89 | Terrestrial Optical Fiber Drop | 1.47 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2310 | 3 | 310 | 2310 | 1001321020 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Mailag | 7.9717 | 125.1156 | U | 8615 | 2267 | 680 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100198 | FTAP Globe | 7.9734 | 125.1346 | 2.1 | Terrestrial Optical Fiber Drop | 2.36 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2311 | 3 | 311 | 2311 | 0500514032 | Region V (Bicol Region) | Albay | Polangui | Matacon | 13.3258 | 123.4295 | R | 4666 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050135 | FTAP Globe | 13.3317 | 123.4228 | 0.98 | Terrestrial Optical Fiber Drop | 3.11 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2312 | 3 | 312 | 2312 | 0301410047 | Region III (Central Luzon) | Bulacan | City of Malolos | Santisima Trinidad | 14.8758 | 120.8253 | U | 6991 | 1997 | 599 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01080 | Edgepoint | 14.8745 | 120.8238 | 0.22 | Terrestrial Optical Fiber Drop | 2.46 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2313 | 3 | 313 | 2313 | 1003505028 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Lapinig | 7.9229 | 123.6866 | R | 4735 | 1127 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100204 | FTAP Globe | 7.9274 | 123.6714 | 1.74 | Terrestrial Optical Fiber Drop | 11.52 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2314 | 3 | 314 | 2314 | 1600209018 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Santa Ana | 8.9699 | 125.3396 | R | 2930 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0017 | PTCI/MIDC | 8.9849 | 125.3459 | 1.8 | Terrestrial Optical Fiber Drop | 1.06 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2315 | 3 | 315 | 2315 | 0731300022 | Region VII (Central Visayas) | Cebu | City of Mandaue | Subangdaku | 10.3225 | 123.923 | U | 17114 | 4889 | 1467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0106 | PTCI/MIDC | 10.3197 | 123.9204 | 0.42 | Terrestrial Optical Fiber Drop | 1.95 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2316 | 3 | 316 | 2316 | 1731500026 | MIMAROPA Region | Palawan | City of Puerto Princesa | Manalo | 9.7361 | 118.7457 | R | 2877 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170233 | FTAP Globe | 9.9781 | 118.8602 | 3.79 | Terrestrial Optical Fiber Drop | 1.42 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2317 | 3 | 317 | 2317 | 0331400014 | Region III (Central Luzon) | Zambales | City of Olongapo | New Cabalan | 14.8496 | 120.3354 | U | 33937 | 9172 | 2752 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03327-B07 | PTCI/MIDC | 14.8451 | 120.3401 | 0.71 | Terrestrial Optical Fiber Drop | 1.22 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2318 | 3 | 318 | 2318 | 0506211014 | Region V (Bicol Region) | Sorsogon | Magallanes | Caditaan | 12.8042 | 123.8507 | R | 3603 | 900 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSOG0002 | PTCI/MIDC | 12.8037 | 123.8513 | 0.09 | Terrestrial Optical Fiber Drop | 2.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2319 | 3 | 319 | 2319 | 0307110012 | Region III (Central Luzon) | Zambales | San Felipe | Sindol | 15.077 | 120.0663 | R | 2433 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ZMB-00898 | Edgepoint | 15.0678 | 120.0687 | 1.04 | Terrestrial Optical Fiber Drop | 1.96 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2320 | 3 | 320 | 2320 | 0803708038 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Kilim | 10.7127 | 124.7966 | R | 3625 | 953 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080359 | FTAP Globe | 10.7106 | 124.7977 | 0.27 | Terrestrial Optical Fiber Drop | 3.74 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2321 | 3 | 321 | 2321 | 0603037005 | Region VI (Western Visayas) | Iloilo | Pototan | Batuan | 10.9556 | 122.6404 | R | 1936 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.86 | Terrestrial Optical Fiber Drop | 1.06 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2322 | 3 | 322 | 2322 | 0501603023 | Region V (Bicol Region) | Camarines Norte | Daet | Pamorangon | 14.091 | 122.9574 | R | 3299 | 824 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAN-03170 | Edgepoint | 14.0939 | 122.9489 | 0.97 | Terrestrial Optical Fiber Drop | 2.65 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2323 | 3 | 323 | 2323 | 0501610004 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Rizal | 14.1969 | 122.4031 | R | 3062 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050008 | FTAP Globe | 14.218 | 122.3945 | 2.52 | Terrestrial Optical Fiber Drop | 2.18 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2324 | 3 | 324 | 2324 | 0201516025 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Maxingal | 18.2119 | 121.6657 | R | 2741 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 1.93 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2325 | 3 | 325 | 2325 | 0401014012 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Bugtong na Pulo | 14.0004 | 121.1675 | U | 7906 | 2196 | 659 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01963-C08 | PTCI/MIDC | 14.0096 | 121.1646 | 1.08 | Terrestrial Optical Fiber Drop | 2.3 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2326 | 3 | 326 | 2326 | 0105533030 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw Vidal | 16.1203 | 120.3935 | R | 3605 | 1001 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00399 | Edgepoint | 16.1619 | 120.4277 | 1.46 | Terrestrial Optical Fiber Drop | 0.78 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2327 | 3 | 327 | 2327 | 1705204011 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Nasukob | 12.3632 | 121.3441 | R | 3745 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170138 | FTAP Globe | 12.3442 | 121.3679 | 3.34 | Terrestrial Optical Fiber Drop | 3.59 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2328 | 3 | 328 | 2328 | 0403406005 | Region IV-A (CALABARZON) | Laguna | Calauan | Imok | 14.1226 | 121.3031 | R | 2778 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040307 | FTAP Globe | 14.1123 | 121.3045 | 1.16 | Terrestrial Optical Fiber Drop | 2.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2329 | 3 | 329 | 2329 | 0405603039 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tagbakin | 13.9964 | 121.912 | U | 5639 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 1.45 | Terrestrial Optical Fiber Drop | 1.52 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2330 | 3 | 330 | 2330 | 0405619026 | Region IV-A (CALABARZON) | Quezon | Gumaca | Mabini | 13.9183 | 122.0961 | R | 1988 | 523 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1414 | FTAP Smart | 13.9191 | 122.0931 | 0.34 | Terrestrial Optical Fiber Drop | 1.35 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2331 | 3 | 331 | 2331 | 0702213011 | Region VII (Central Visayas) | Cebu | Borbon | Don Gregorio Antigua | 10.8762 | 123.9774 | R | 4071 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070308 | FTAP Globe | 10.8648 | 123.9816 | 1.35 | Terrestrial Optical Fiber Drop | 7 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2332 | 3 | 332 | 2332 | 0603026012 | Region VI (Western Visayas) | Iloilo | Leganes | Guihaman | 10.7768 | 122.5843 | R | 2324 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 1.17 | Terrestrial Optical Fiber Drop | 1.13 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2333 | 3 | 333 | 2333 | 0300804007 | Region III (Central Luzon) | Bataan | Dinalupihan | Colo | 14.848 | 120.4125 | R | 3814 | 1059 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0006 | PTCI/MIDC | 14.8469 | 120.4161 | 0.4 | Terrestrial Optical Fiber Drop | 1.63 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2334 | 3 | 334 | 2334 | 0401021021 | Region IV-A (CALABARZON) | Batangas | Rosario | Masaya | 13.8371 | 121.1846 | U | 4757 | 1321 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 1.32 | Terrestrial Optical Fiber Drop | 1.99 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2335 | 3 | 335 | 2335 | 0304916006 | Region III (Central Luzon) | Nueva Ecija | Lupao | J. U. Tienzo | 15.8723 | 120.9038 | R | 1980 | 565 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 1.05 | Terrestrial Optical Fiber Drop | 1.53 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2336 | 3 | 336 | 2336 | 0304930005 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bakal II | 15.6977 | 120.8986 | U | 4059 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1224 | FTAP Smart | 15.6939 | 120.8967 | 0.47 | Terrestrial Optical Fiber Drop | 2.05 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2337 | 3 | 337 | 2337 | 0304932020 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Isidro | 15.4485 | 120.8005 | U | 6681 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.12 | Terrestrial Optical Fiber Drop | 1.18 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2338 | 3 | 338 | 2338 | 0500509015 | Region V (Bicol Region) | Albay | Malilipot | San Jose | 13.2935 | 123.7581 | U | 5308 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050139 | FTAP Globe | 13.3004 | 123.7597 | 0.78 | Terrestrial Optical Fiber Drop | 2.49 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2339 | 3 | 339 | 2339 | 0931700054 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Muti | 7.2786 | 122.2685 | R | 3566 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0081 | PTCI/MIDC | 7.2909 | 122.2725 | 1.44 | Terrestrial Optical Fiber Drop | 4.29 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2340 | 3 | 340 | 2340 | 1030500057 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Mambuaya | 8.3264 | 124.5973 | U | 6071 | 1686 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100083 | FTAP BTS | 8.3287 | 124.5967 | 0.26 | Terrestrial Optical Fiber Drop | 1.78 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2341 | 3 | 341 | 2341 | 0304908005 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Malimba | 15.2562 | 120.952 | R | 4045 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01439-B07 | PTCI/MIDC | 15.2534 | 120.9527 | 0.32 | Terrestrial Optical Fiber Drop | 0.07 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2342 | 3 | 342 | 2342 | 0205005005 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Busilac | 16.4728 | 121.1156 | R | 3945 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01532-B05 | PTCI/MIDC | 16.4761 | 121.1175 | 0.42 | Terrestrial Optical Fiber Drop | 3.74 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2343 | 3 | 343 | 2343 | 0403405040 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 3 | 14.2074 | 121.1622 | U | 4973 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4230 | FTAP Smart | 14.2081 | 121.1581 | 0.45 | Terrestrial Optical Fiber Drop | 2.07 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2344 | 3 | 344 | 2344 | 0803723013 | Region VIII (Eastern Visayas) | Leyte | Jaro | Hiagsam | 11.2331 | 124.7616 | R | 2161 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 2.09 | Terrestrial Optical Fiber Drop | 1.86 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2345 | 3 | 345 | 2345 | 0201501011 | Region II (Cagayan Valley) | Cagayan | Abulug | Lucban | 18.3367 | 121.4318 | R | 3218 | 825 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CAG_0060 | LDIC | 121.4433 | 18.3357 | 1.22 | Terrestrial Optical Fiber Drop | 1.75 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2346 | 3 | 346 | 2346 | 0401014005 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Antipolo Del Norte | 13.9282 | 121.1699 | U | 6258 | 1738 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040469 | FTAP Globe | 13.9258 | 121.1665 | 0.46 | Terrestrial Optical Fiber Drop | 1.82 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2347 | 3 | 347 | 2347 | 0105517017 | Region I (Ilocos Region) | Pangasinan | Calasiao | Nalsian | 16.0211 | 120.3503 | U | 6961 | 1933 | 580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00451 | Edgepoint | 16.0219 | 120.3511 | 0.12 | Terrestrial Optical Fiber Drop | 2.15 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2348 | 3 | 348 | 2348 | 0702204009 | Region VII (Central Visayas) | Cebu | Aloguinsan | Poblacion | 10.2179 | 123.5514 | R | 3811 | 1002 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0003 | PTCI/MIDC | 10.2277 | 123.5519 | 1.09 | Terrestrial Optical Fiber Drop | 8.89 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2349 | 3 | 349 | 2349 | 0603018040 | Region VI (Western Visayas) | Iloilo | Dumangas | Tabucan | 10.8428 | 122.7017 | R | 2389 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.15 | Terrestrial Optical Fiber Drop | 2.07 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2350 | 3 | 350 | 2350 | 1206315001 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | Bukay Pait | 6.5636 | 124.7689 | R | 4334 | 1203 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120202 | FTAP BTS | 6.5643 | 124.7666 | 0.26 | Terrestrial Optical Fiber Drop | 17.53 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2351 | 3 | 351 | 2351 | 0405619013 | Region IV-A (CALABARZON) | Quezon | Gumaca | Calumangin | 13.9494 | 122.0317 | R | 1939 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040420 | FTAP Globe | 13.9547 | 122.0232 | 1.1 | Terrestrial Optical Fiber Drop | 1.26 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2352 | 3 | 352 | 2352 | 0105520005 | Region I (Ilocos Region) | Pangasinan | Infanta | Cato | 15.8387 | 119.915 | R | 4888 | 1357 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00565 | Edgepoint | 15.8345 | 119.914 | 0.48 | Terrestrial Optical Fiber Drop | 1.49 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2353 | 3 | 353 | 2353 | 0601916014 | Region VI (Western Visayas) | Capiz | Sigma | Mianay | 11.4603 | 122.69 | R | 3912 | 1029 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060230 | FTAP Globe | 11.5064 | 122.6843 | 5.17 | Terrestrial Optical Fiber Drop | 4.92 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2354 | 3 | 354 | 2354 | 0105511062 | Region I (Ilocos Region) | Pangasinan | Bayambang | Tamaro | 15.8276 | 120.4574 | R | 1834 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0003 | LDIC | 15.8219 | 120.4585 | 0.64 | Terrestrial Optical Fiber Drop | 1.29 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2355 | 3 | 355 | 2355 | 1004311013 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Solana | 8.6254 | 124.7646 | R | 4715 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 2.41 | Terrestrial Optical Fiber Drop | 2.94 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2356 | 3 | 356 | 2356 | 0306910005 | Region III (Central Luzon) | Tarlac | Paniqui | Balaoang | 15.6653 | 120.5122 | R | 4549 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00613 | Edgepoint | 15.6634 | 120.5104 | 0.29 | Terrestrial Optical Fiber Drop | 8.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2357 | 3 | 357 | 2357 | 1606811010 | Region XIII (Caraga) | Surigao del Sur | Lianga | Poblacion | 8.632 | 126.0877 | R | 4892 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130030 | FTAP BTS | 8.5393 | 126.1199 | 10.48 | Terrestrial Optical Fiber Drop | 12 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2358 | 3 | 358 | 2358 | 0702210043 | Region VII (Central Visayas) | Cebu | Barili | Tubod | 10.1165 | 123.567 | R | 2543 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070364 | FTAP Globe | 10.1317 | 123.5785 | 2.11 | Terrestrial Optical Fiber Drop | 1.98 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2359 | 3 | 359 | 2359 | 0401013003 | Region IV-A (CALABARZON) | Batangas | Lian | Balibago | 13.9372 | 120.6314 | R | 3749 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040450 | FTAP Globe | 13.934 | 120.6326 | 0.38 | Terrestrial Optical Fiber Drop | 2.15 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2360 | 3 | 360 | 2360 | 0304919011 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Sapang Buho | 15.5912 | 121.1248 | R | 4900 | 1400 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00644 | Edgepoint | 15.5896 | 121.119 | 0.65 | Terrestrial Optical Fiber Drop | 3.96 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2361 | 3 | 361 | 2361 | 0306904004 | Region III (Central Luzon) | Tarlac | Capas | Cutcut 1st | 15.3276 | 120.5908 | U | 12578 | 3225 | 968 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00764 | Edgepoint | 15.3185 | 120.5833 | 1.29 | Terrestrial Optical Fiber Drop | 2.16 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2362 | 3 | 362 | 2362 | 0702233015 | Region VII (Central Visayas) | Cebu | Moalboal | Tunga | 9.9539 | 123.4001 | R | 2927 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 0.09 | Terrestrial Optical Fiber Drop | 1.79 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2363 | 3 | 363 | 2363 | 0702251016 | Region VII (Central Visayas) | Cebu | City of Toledo | Don Andres Soriano | 10.3063 | 123.7116 | U | 19376 | 5098 | 1529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0163 | PTCI/MIDC | 10.3105 | 123.6964 | 1.72 | Terrestrial Optical Fiber Drop | 2.05 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2364 | 3 | 364 | 2364 | 0105511020 | Region I (Ilocos Region) | Pangasinan | Bayambang | Buayaen | 15.7884 | 120.4516 | R | 3137 | 871 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0010 | LDIC | 15.7841 | 120.4494 | 0.53 | Terrestrial Optical Fiber Drop | 3.13 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2365 | 3 | 365 | 2365 | 0105538015 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Maticmatic | 15.9871 | 120.4507 | U | 5157 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 1.03 | Terrestrial Optical Fiber Drop | 1.05 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2366 | 3 | 366 | 2366 | 0401021036 | Region IV-A (CALABARZON) | Batangas | Rosario | Putingkahoy | 13.8292 | 121.329 | R | 3086 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040553 | FTAP Globe | 13.828 | 121.3363 | 0.8 | Terrestrial Optical Fiber Drop | 1.31 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2367 | 3 | 367 | 2367 | 1600308028 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Karaus | 8.4906 | 125.9761 | U | 3723 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 0.06 | Terrestrial Optical Fiber Drop | 2.02 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2368 | 3 | 368 | 2368 | 0702223021 | Region VII (Central Visayas) | Cebu | Danao City | Looc | 10.5066 | 124.0295 | U | 12347 | 3249 | 975 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070319 | FTAP Globe | 10.5049 | 124.0235 | 0.68 | Terrestrial Optical Fiber Drop | 1.72 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2369 | 3 | 369 | 2369 | 0604512004 | Region VI (Western Visayas) | Negros Occidental | Hinoba-an | Barangay I | 9.5673 | 122.6217 | R | 3526 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060124 | FTAP BTS | 9.6057 | 122.4649 | 0.88 | Terrestrial Optical Fiber Drop | 30.87 | 10.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2370 | 3 | 370 | 2370 | 0704605003 | Region VII (Central Visayas) | Negros Oriental | Basay | Bongalonan | 9.4357 | 122.5983 | R | 4357 | 1146 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070260 | FTAP Globe | 9.4071 | 122.6411 | 5.67 | Terrestrial Optical Fiber Drop | 24.77 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2371 | 3 | 371 | 2371 | 0403411014 | Region IV-A (CALABARZON) | Laguna | Los Baños | Timugan | 14.1781 | 121.2224 | U | 6410 | 1942 | 583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02109-C08 | PTCI/MIDC | 14.18 | 121.2259 | 0.44 | Terrestrial Optical Fiber Drop | 2.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2372 | 3 | 372 | 2372 | 0201511041 | Region II (Cagayan Valley) | Cagayan | Claveria | Taggat Sur | 18.6028 | 121.0582 | R | 2210 | 566 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01189-B05 | PTCI/MIDC | 18.6025 | 121.0861 | 2.95 | Terrestrial Optical Fiber Drop | 1.27 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2373 | 3 | 373 | 2373 | 0105523018 | Region I (Ilocos Region) | Pangasinan | Mabini | Tagudin | 16.0831 | 119.954 | R | 4246 | 1179 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010140 | FTAP Globe | 16.0709 | 119.9479 | 1.51 | Terrestrial Optical Fiber Drop | 2.95 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2374 | 3 | 374 | 2374 | 1731500058 | MIMAROPA Region | Palawan | City of Puerto Princesa | Tagburos | 9.8206 | 118.7438 | U | 10122 | 2735 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S2229 | FTAP Smart | 9.8095 | 118.7405 | 1.28 | Terrestrial Optical Fiber Drop | 2.28 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2375 | 3 | 375 | 2375 | 1001304021 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Pinamaloy | 7.6646 | 124.9964 | R | 3621 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 0.59 | Terrestrial Optical Fiber Drop | 1.43 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2376 | 3 | 376 | 2376 | 0105546032 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Poblacion | 15.9752 | 120.5655 | U | 7343 | 2039 | 612 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00491 | Edgepoint | 15.9774 | 120.565 | 0.26 | Terrestrial Optical Fiber Drop | 1.94 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2377 | 3 | 377 | 2377 | 0201510016 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Dugo | 18.2507 | 121.6862 | R | 1847 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020014 | FTAP Globe | 18.2526 | 121.6864 | 0.21 | Terrestrial Optical Fiber Drop | 1.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2378 | 3 | 378 | 2378 | 1102507009 | Region XI (Davao Region) | Davao Oriental | Lupon | Corporacion | 6.9104 | 126.0298 | R | 3421 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDLG0031 | PTCI/MIDC | 6.9029 | 126.0175 | 1.6 | Terrestrial Optical Fiber Drop | 2.51 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2379 | 3 | 379 | 2379 | 0403424035 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Concepcion | 14.0745 | 121.3351 | U | 9089 | 2754 | 826 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 0.95 | Terrestrial Optical Fiber Drop | 1.8 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2380 | 3 | 380 | 2380 | 0702224035 | Region VII (Central Visayas) | Cebu | Dumanjug | Tapon | 10.0621 | 123.4444 | R | 4211 | 1108 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0001 | LDIC | 10.0758 | 123.4523 | 1.75 | Terrestrial Optical Fiber Drop | 1.11 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2381 | 3 | 381 | 2381 | 0500506070 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 56 - Taysan | 13.1166 | 123.7443 | U | 15240 | 3717 | 1115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050188 | FTAP Globe | 13.1173 | 123.7423 | 0.23 | Terrestrial Optical Fiber Drop | 2.49 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2382 | 3 | 382 | 2382 | 0306916088 | Region III (Central Luzon) | Tarlac | City of Tarlac | Tibag | 15.5073 | 120.5707 | U | 18566 | 4760 | 1428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030368 | FTAP Globe | 15.5098 | 120.5775 | 0.78 | Terrestrial Optical Fiber Drop | 1.31 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2383 | 3 | 383 | 2383 | 1401105010 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Loo | 16.7915 | 120.8309 | R | 5014 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 1.25 | Terrestrial Optical Fiber Drop | 1.68 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2384 | 3 | 384 | 2384 | 0300804025 | Region III (Central Luzon) | Bataan | Dinalupihan | Pagalanggang | 14.8934 | 120.4672 | R | 4402 | 1222 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00896-B07 | PTCI/MIDC | 14.894 | 120.4644 | 0.31 | Terrestrial Optical Fiber Drop | 3.13 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2385 | 3 | 385 | 2385 | 1130700049 | Region XI (Davao Region) | Davao del Sur | City of Davao | Ilang | 7.165 | 125.4711 | U | 27210 | 8002 | 2401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110453 | FTAP Globe | 7.1893 | 125.6441 | 1.54 | Terrestrial Optical Fiber Drop | 2.95 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2386 | 3 | 386 | 2386 | 0702205007 | Region VII (Central Visayas) | Cebu | Argao | Bogo | 9.858 | 123.5714 | R | 4057 | 1067 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0003 | LDIC | 9.8666 | 123.5804 | 1.37 | Terrestrial Optical Fiber Drop | 4.13 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2387 | 3 | 387 | 2387 | 0730600006 | Region VII (Central Visayas) | Cebu | City of Cebu | Bacayan | 10.3873 | 123.922 | U | 14477 | 4524 | 1357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0063 | PTCI/MIDC | 10.3895 | 123.9263 | 0.53 | Terrestrial Optical Fiber Drop | 1.96 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2388 | 3 | 388 | 2388 | 0702216018 | Region VII (Central Visayas) | Cebu | Catmon | San Jose Pob. | 10.7283 | 124.0127 | R | 3846 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070312 | FTAP Globe | 10.7253 | 124.014 | 0.37 | Terrestrial Optical Fiber Drop | 2.78 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2389 | 3 | 389 | 2389 | 0301408015 | Region III (Central Luzon) | Bulacan | Guiguinto | Tuktukan | 14.827 | 120.8917 | U | 12398 | 3542 | 1063 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02391-B07 | PTCI/MIDC | 14.8254 | 120.8885 | 0.39 | Terrestrial Optical Fiber Drop | 2.04 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2390 | 3 | 390 | 2390 | 0300812005 | Region III (Central Luzon) | Bataan | Samal | Lalawigan | 14.779 | 120.5426 | R | 5001 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030063 | FTAP BTS | 14.7777 | 120.5416 | 0.18 | Terrestrial Optical Fiber Drop | 2.65 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2391 | 3 | 391 | 2391 | 0803722013 | Region VIII (Eastern Visayas) | Leyte | Isabel | Marvel | 10.9369 | 124.4322 | U | 4160 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080190 | FTAP BTS | 10.9422 | 124.4325 | 0.59 | Terrestrial Optical Fiber Drop | 1.42 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2392 | 3 | 392 | 2392 | 1102303022 | Region XI (Davao Region) | Davao del Norte | Carmen | Tuganay | 7.3693 | 125.7222 | R | 5049 | 1364 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110432 | FTAP Globe | 7.3642 | 125.7133 | 1.13 | Terrestrial Optical Fiber Drop | 2.8 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2393 | 3 | 393 | 2393 | 0730600032 | Region VII (Central Visayas) | Cebu | City of Cebu | Inayawan | 10.2718 | 123.856 | U | 32714 | 10223 | 3067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.33 | Terrestrial Optical Fiber Drop | 1.54 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2394 | 3 | 394 | 2394 | 0305416027 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Jose | 15.04 | 120.6999 | U | 17150 | 4287 | 1286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00001-B07 | PTCI/MIDC | 15.0404 | 120.701 | 0.13 | Terrestrial Optical Fiber Drop | 1.93 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2395 | 3 | 395 | 2395 | 1206317013 | Region XII (SOCCSKSARGEN) | South Cotabato | Tupi | Poblacion | 6.3415 | 124.9417 | U | 15943 | 4428 | 1328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120121 | FTAP BTS | 6.3394 | 124.9432 | 0.28 | Terrestrial Optical Fiber Drop | 1.45 | 6.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2396 | 3 | 396 | 2396 | 0103317018 | Region I (Ilocos Region) | La Union | Santo Tomas | Patac | 16.2748 | 120.3935 | U | 3416 | 923 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-LUN-00375 | Edgepoint | 16.2755 | 120.3824 | 1.19 | Terrestrial Optical Fiber Drop | 1.99 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2397 | 3 | 397 | 2397 | 1204704015 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Lanao | 7.0255 | 125.0814 | U | 7862 | 2068 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNCG0017 | PTCI/MIDC | 7.0271 | 125.085 | 0.43 | Terrestrial Optical Fiber Drop | 1.95 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2398 | 3 | 398 | 2398 | 0105526020 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Malabago | 16.0551 | 120.388 | U | 5172 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00428 | Edgepoint | 16.0514 | 120.3822 | 0.75 | Terrestrial Optical Fiber Drop | 2.08 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2399 | 3 | 399 | 2399 | 0301417015 | Region III (Central Luzon) | Bulacan | Plaridel | Poblacion | 14.8843 | 120.8594 | U | 4054 | 1158 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030563 | FTAP Globe | 14.8814 | 120.8665 | 0.82 | Terrestrial Optical Fiber Drop | 2.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2400 | 3 | 400 | 2400 | 0403405058 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Turbina | 14.1832 | 121.1343 | U | 6871 | 2082 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.74 | Terrestrial Optical Fiber Drop | 2.01 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2401 | 3 | 401 | 2401 | 0401031016 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Darasa | 14.0692 | 121.1533 | U | 24699 | 6860 | 2058 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4114 | FTAP Smart | 14.0627 | 121.1529 | 0.72 | Terrestrial Optical Fiber Drop | 1.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2402 | 3 | 402 | 2402 | 0401014071 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Tambo | 13.9407 | 121.1469 | U | 12945 | 3595 | 1079 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02802-C08 | PTCI/MIDC | 13.9457 | 121.149 | 0.6 | Terrestrial Optical Fiber Drop | 2.15 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2403 | 3 | 403 | 2403 | 0201529044 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Leonarda | 17.6424 | 121.7399 | U | 3353 | 859 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01134-B06 | PTCI/MIDC | 17.6428 | 121.7405 | 0.07 | Terrestrial Optical Fiber Drop | 1.25 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2404 | 3 | 404 | 2404 | 0604512001 | Region VI (Western Visayas) | Negros Occidental | Hinoba-an | Alim | 9.5207 | 122.5407 | R | 5101 | 1378 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0048 | PTCI/MIDC | 9.5664 | 122.4924 | 0.63 | Terrestrial Optical Fiber Drop | 29.49 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2405 | 3 | 405 | 2405 | 0401014031 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Mataas Na Lupa | 13.9421 | 121.1575 | U | 4644 | 1290 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040444 | FTAP Globe | 13.9393 | 121.1666 | 0.47 | Terrestrial Optical Fiber Drop | 0.99 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2406 | 3 | 406 | 2406 | 0702222027 | Region VII (Central Visayas) | Cebu | Dalaguete | Obong | 9.7399 | 123.5109 | R | 3285 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 1.29 | Terrestrial Optical Fiber Drop | 3.36 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2407 | 3 | 407 | 2407 | 0306916056 | Region III (Central Luzon) | Tarlac | City of Tarlac | Paraiso | 15.443 | 120.5987 | R | 3583 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-03013 | Edgepoint | 120.5986 | 15.4446 | 0.18 | Terrestrial Optical Fiber Drop | 2.61 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2408 | 3 | 408 | 2408 | 0306906018 | Region III (Central Luzon) | Tarlac | Gerona | Magaspac | 15.6154 | 120.5979 | R | 5109 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00633 | Edgepoint | 15.6103 | 120.5971 | 0.57 | Terrestrial Optical Fiber Drop | 2.07 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2409 | 3 | 409 | 2409 | 0307114019 | Region III (Central Luzon) | Zambales | Subic | Pamatawan | 14.9241 | 120.2192 | R | 5163 | 1358 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ZMB-01037 | Edgepoint | 14.9175 | 120.2302 | 1.39 | Terrestrial Optical Fiber Drop | 2.07 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2410 | 3 | 410 | 2410 | 1108203002 | Region XI (Davao Region) | Davao de Oro | Mabini | Cadunan | 7.3309 | 125.8579 | U | 4653 | 1257 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110440 | FTAP Globe | 7.3117 | 125.8547 | 2.17 | Terrestrial Optical Fiber Drop | 2.47 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2411 | 3 | 411 | 2411 | 1001314017 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Tankulan | 8.3684 | 124.8643 | U | 10019 | 2636 | 791 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 0.44 | Terrestrial Optical Fiber Drop | 2.11 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2412 | 3 | 412 | 2412 | 0205702008 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Mangandingay | 16.5162 | 121.5475 | R | 3342 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0004 | LDIC | 121.5504 | 16.5144 | 0.37 | Terrestrial Optical Fiber Drop | 2.1 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2413 | 3 | 413 | 2413 | 0301423014 | Region III (Central Luzon) | Bulacan | Santa Maria | Manggahan | 14.8528 | 120.9575 | U | 2905 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01119 | Edgepoint | 14.8516 | 120.9571 | 0.13 | Terrestrial Optical Fiber Drop | 1.22 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2414 | 3 | 414 | 2414 | 1003523012 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Kalanganan East | 8.0828 | 124.2512 | R | 3745 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100189 | FTAP Globe | 8.0656 | 124.2637 | 2.35 | Terrestrial Optical Fiber Drop | 8.49 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2415 | 3 | 415 | 2415 | 0401005035 | Region IV-A (CALABARZON) | Batangas | Batangas City | Kumintang Ilaya | 13.7744 | 121.0656 | U | 11223 | 3117 | 935 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B74 | FTAP Smart | 13.7784 | 121.0676 | 0.49 | Terrestrial Optical Fiber Drop | 1.64 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2416 | 3 | 416 | 2416 | 0431200022 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Talim | 13.9157 | 121.5777 | R | 3834 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02141-C08 | PTCI/MIDC | 13.9298 | 121.5959 | 2.51 | Terrestrial Optical Fiber Drop | 3.8 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2417 | 3 | 417 | 2417 | 0307103016 | Region III (Central Luzon) | Zambales | Candelaria | Sinabacan | 15.6566 | 119.9351 | R | 4096 | 1077 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01832-B07 | PTCI/MIDC | 15.6522 | 119.9312 | 0.64 | Terrestrial Optical Fiber Drop | 3.68 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2418 | 3 | 418 | 2418 | 0403405055 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Juan | 14.2171 | 121.1758 | R | 5290 | 1603 | 481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040241 | FTAP Globe | 14.2171 | 121.1746 | 0.13 | Terrestrial Optical Fiber Drop | 3.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2419 | 3 | 419 | 2419 | 0405645035 | Region IV-A (CALABARZON) | Quezon | Sariaya | Barangay 4 | 13.9625 | 121.5272 | U | 3165 | 832 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q55 | FTAP Smart | 13.9641 | 121.529 | 0.27 | Terrestrial Optical Fiber Drop | 1.06 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2420 | 3 | 420 | 2420 | 0702251022 | Region VII (Central Visayas) | Cebu | City of Toledo | Luray II | 10.381 | 123.644 | U | 4847 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0172 | PTCI/MIDC | 10.3817 | 123.6436 | 0.09 | Terrestrial Optical Fiber Drop | 2.48 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2421 | 3 | 421 | 2421 | 1004303008 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Mantangale | 9.0046 | 124.8574 | R | 1882 | 482 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 0.45 | Terrestrial Optical Fiber Drop | 1.62 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2422 | 3 | 422 | 2422 | 0304925004 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Malapit | 15.3043 | 120.9212 | U | 10459 | 2988 | 896 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0013 | LDIC | 15.3017 | 120.9258 | 0.57 | Terrestrial Optical Fiber Drop | 0.07 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2423 | 3 | 423 | 2423 | 1430300101 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Santo Rosario | 16.4002 | 120.5869 | R | 1920 | 505 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0053 | LDIC | 16.402 | 120.584 | 0.38 | Terrestrial Optical Fiber Drop | 1.09 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2424 | 3 | 424 | 2424 | 1004320002 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Linangkayan | 8.4115 | 124.2918 | R | 3118 | 799 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0102 | PTCI/MIDC | 8.4093 | 124.2918 | 0.25 | Terrestrial Optical Fiber Drop | 1.36 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2425 | 3 | 425 | 2425 | 0931700066 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Quiniput | 7.1795 | 122.1725 | R | 4186 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTZSG0150 | PTCI/MIDC | 7.1844 | 122.2194 | 0.14 | Terrestrial Optical Fiber Drop | 11.87 | 5.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2426 | 3 | 426 | 2426 | 1108207003 | Region XI (Davao Region) | Davao de Oro | Monkayo | Banlag | 7.8263 | 126.0341 | R | 4887 | 1320 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDOG0097 | PTCI/MIDC | 7.8249 | 126.0332 | 0.18 | Terrestrial Optical Fiber Drop | 2.43 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2427 | 3 | 427 | 2427 | 0803721021 | Region VIII (Eastern Visayas) | Leyte | Inopacan | Tinago | 10.4967 | 124.7376 | R | 3158 | 831 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080217 | FTAP BTS | 10.4266 | 124.7271 | 7.88 | Terrestrial Optical Fiber Drop | 21.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2428 | 3 | 428 | 2428 | 0501721009 | Region V (Bicol Region) | Camarines Sur | Milaor | Flordeliz | 13.5899 | 123.1694 | R | 1523 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050098 | FTAP Globe | 13.5913 | 123.1714 | 0.27 | Terrestrial Optical Fiber Drop | 1.05 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2429 | 3 | 429 | 2429 | 0604530011 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Mabini | 10.4939 | 122.8271 | R | 4270 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0081 | PTCI/MIDC | 10.5207 | 122.8433 | 3.46 | Terrestrial Optical Fiber Drop | 3.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2430 | 3 | 430 | 2430 | 1004311002 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Bobontugan | 8.6571 | 124.7464 | U | 7072 | 1813 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.32 | Terrestrial Optical Fiber Drop | 1.19 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2431 | 3 | 431 | 2431 | 1130700068 | Region XI (Davao Region) | Davao del Sur | City of Davao | Manambulan | 7.1034 | 125.4523 | R | 3635 | 1069 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110472 | FTAP Globe | 7.12 | 125.4504 | 1.86 | Terrestrial Optical Fiber Drop | 6.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2432 | 3 | 432 | 2432 | 0506216019 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Macabog | 12.9844 | 123.9912 | R | 4479 | 1119 | 336 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_SOR_0001 | LDIC | 12.9853 | 123.9959 | 0.53 | Terrestrial Optical Fiber Drop | 2.08 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2433 | 3 | 433 | 2433 | 0304903010 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Bantug Bulalo | 15.4899 | 120.9758 | R | 2190 | 625 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00696 | Edgepoint | 15.4906 | 120.9774 | 0.19 | Terrestrial Optical Fiber Drop | 1.82 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2434 | 3 | 434 | 2434 | 0405610033 | Region IV-A (CALABARZON) | Quezon | Catanauan | San Isidro | 13.6311 | 122.2422 | R | 3291 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040613 | FTAP Globe | 13.6328 | 122.2423 | 0.19 | Terrestrial Optical Fiber Drop | 1.14 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2435 | 3 | 435 | 2435 | 1004310006 | Region X (Northern Mindanao) | Misamis Oriental | Initao | Jampason | 8.5148 | 124.3097 | R | 2341 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0052 | PTCI/MIDC | 8.5168 | 124.3105 | 0.25 | Terrestrial Optical Fiber Drop | 1.57 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2436 | 3 | 436 | 2436 | 1004308065 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | San Juan | 8.8273 | 125.0869 | R | 5055 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100112 | FTAP Globe | 8.8252 | 125.0887 | 0.31 | Terrestrial Optical Fiber Drop | 2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2437 | 3 | 437 | 2437 | 0300804002 | Region III (Central Luzon) | Bataan | Dinalupihan | Bangal | 14.8453 | 120.3396 | U | 5278 | 1466 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03327-B07 | PTCI/MIDC | 14.8451 | 120.3401 | 0.06 | Terrestrial Optical Fiber Drop | 1.77 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2438 | 3 | 438 | 2438 | 0601914020 | Region VI (Western Visayas) | Capiz | City of Roxas | Bolo | 11.5388 | 122.7573 | U | 8301 | 2184 | 655 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060228 | FTAP Globe | 11.5361 | 122.7582 | 0.31 | Terrestrial Optical Fiber Drop | 2.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2439 | 3 | 439 | 2439 | 1108208011 | Region XI (Davao Region) | Davao de Oro | Montevista | Linoan | 7.676 | 125.9855 | R | 4272 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0026 | PTCI/MIDC | 7.6833 | 125.9877 | 0.84 | Terrestrial Optical Fiber Drop | 18.54 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2440 | 3 | 440 | 2440 | 0306916074 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Sebastian | 15.4746 | 120.598 | U | 4413 | 1131 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.53 | Terrestrial Optical Fiber Drop | 1.66 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2441 | 3 | 441 | 2441 | 0300810024 | Region III (Central Luzon) | Bataan | Orion | Santo Domingo | 14.6338 | 120.5729 | R | 4590 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 1.46 | Terrestrial Optical Fiber Drop | 2.15 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2442 | 3 | 442 | 2442 | 0201529002 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Atulayan Norte | 17.6351 | 121.7203 | R | 4335 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1008 | FTAP Smart | 17.6126 | 121.7294 | 0.65 | Terrestrial Optical Fiber Drop | 3.37 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2443 | 3 | 443 | 2443 | 0603031006 | Region VI (Western Visayas) | Iloilo | Mina | Cabalabaguan | 10.936 | 122.582 | R | 2262 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 0.31 | Terrestrial Optical Fiber Drop | 2.47 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2444 | 3 | 444 | 2444 | 0500506056 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 62 - Homapon | 13.0912 | 123.7393 | U | 5336 | 1301 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02493-C10 | PTCI/MIDC | 13.0832 | 123.7423 | 0.95 | Terrestrial Optical Fiber Drop | 1.59 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2445 | 3 | 445 | 2445 | 0203135015 | Region II (Cagayan Valley) | Isabela | City of Santiago | Divisoria | 16.6974 | 121.6083 | R | 4366 | 1148 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0020 | LDIC | 121.6084 | 16.6944 | 0.34 | Terrestrial Optical Fiber Drop | 4.78 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2446 | 3 | 446 | 2446 | 0500517039 | Region V (Bicol Region) | Albay | City of Tabaco | San Lorenzo | 13.3365 | 123.7362 | U | 8144 | 1986 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050134 | FTAP Globe | 13.3413 | 123.7311 | 0.77 | Terrestrial Optical Fiber Drop | 1.89 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2447 | 3 | 447 | 2447 | 0403405035 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Palo-Alto | 14.1843 | 121.1073 | U | 20689 | 6269 | 1881 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02049-C08 | PTCI/MIDC | 14.1853 | 121.1088 | 0.2 | Terrestrial Optical Fiber Drop | 1.12 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2448 | 3 | 448 | 2448 | 1001317026 | Region X (Northern Mindanao) | Bukidnon | Quezon | Palacapao | 7.6103 | 125.1308 | R | 2921 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 1.28 | Terrestrial Optical Fiber Drop | 1.97 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2449 | 3 | 449 | 2449 | 0301407027 | Region III (Central Luzon) | Bulacan | Calumpit | Santo Niño | 14.9058 | 120.7808 | U | 2659 | 759 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01049 | Edgepoint | 14.9045 | 120.7807 | 0.15 | Terrestrial Optical Fiber Drop | 1.4 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2450 | 3 | 450 | 2450 | 1004315002 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Gimaylan | 8.5488 | 124.3356 | R | 2386 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100128 | FTAP Globe | 8.5377 | 124.3211 | 2.01 | Terrestrial Optical Fiber Drop | 2.42 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2451 | 3 | 451 | 2451 | 0601912004 | Region VI (Western Visayas) | Capiz | Pontevedra | Bailan | 11.458 | 122.8271 | R | 2921 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCZG0029 | PTCI/MIDC | 11.4484 | 122.8313 | 1.16 | Terrestrial Optical Fiber Drop | 2.34 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2452 | 3 | 452 | 2452 | 0306907020 | Region III (Central Luzon) | Tarlac | La Paz | San Roque | 15.4431 | 120.7334 | U | 8464 | 2170 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.7 | Terrestrial Optical Fiber Drop | 1.78 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2453 | 3 | 453 | 2453 | 0304923035 | Region III (Central Luzon) | Nueva Ecija | Rizal | San Gregorio | 15.7051 | 121.115 | R | 1875 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 1 | Terrestrial Optical Fiber Drop | 1.34 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2454 | 3 | 454 | 2454 | 0501706020 | Region V (Bicol Region) | Camarines Sur | Bula | Pawili | 13.5223 | 123.2961 | R | 2990 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03115-C10 | PTCI/MIDC | 13.519 | 123.297 | 0.39 | Terrestrial Optical Fiber Drop | 1.01 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2455 | 3 | 455 | 2455 | 0501732015 | Region V (Bicol Region) | Camarines Sur | San Fernando | Pamukid | 13.5574 | 123.1236 | U | 6125 | 1458 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050104 | FTAP Globe | 13.5612 | 123.1229 | 0.42 | Terrestrial Optical Fiber Drop | 1.81 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2456 | 3 | 456 | 2456 | 0304909019 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Poblacion | 15.6038 | 121.0509 | R | 4214 | 1204 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01422-B07 | PTCI/MIDC | 15.6038 | 121.0489 | 0.22 | Terrestrial Optical Fiber Drop | 1.25 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2457 | 3 | 457 | 2457 | 0501736019 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Francisco | 13.6406 | 123.4986 | R | 1549 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.5 | Terrestrial Optical Fiber Drop | 1.15 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2458 | 3 | 458 | 2458 | 0403405037 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Parian | 14.2142 | 121.1515 | U | 28016 | 8489 | 2547 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03427-A04 | PTCI/MIDC | 14.2116 | 121.1438 | 0.88 | Terrestrial Optical Fiber Drop | 1.97 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2459 | 3 | 459 | 2459 | 0103301020 | Region I (Ilocos Region) | La Union | Agoo | San Jose Sur | 16.3122 | 120.3706 | R | 1824 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00361 | Edgepoint | 16.3204 | 120.3699 | 0.91 | Terrestrial Optical Fiber Drop | 1.28 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2460 | 3 | 460 | 2460 | 1401110012 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Poblacion | 16.4584 | 120.5796 | U | 13029 | 3722 | 1117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBEG0043 | PTCI/MIDC | 16.4614 | 120.5761 | 0.51 | Terrestrial Optical Fiber Drop | 1.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2461 | 3 | 461 | 2461 | 0704606003 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Banga | 9.3705 | 122.7952 | U | 7880 | 2073 | 622 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0010 | PTCI/MIDC | 9.3759 | 122.7973 | 0.64 | Terrestrial Optical Fiber Drop | 2.01 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2462 | 3 | 462 | 2462 | 0500503008 | Region V (Bicol Region) | Albay | Daraga | Bascaran | 13.1044 | 123.6976 | R | 4825 | 1176 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050190 | FTAP Globe | 13.1008 | 123.6996 | 0.45 | Terrestrial Optical Fiber Drop | 4.12 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2463 | 3 | 463 | 2463 | 0630200056 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Sum-ag | 10.6019 | 122.9199 | U | 21273 | 5909 | 1773 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0002 | PTCI/MIDC | 10.6013 | 122.9168 | 0.39 | Terrestrial Optical Fiber Drop | 1.82 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2464 | 3 | 464 | 2464 | 0704605002 | Region VII (Central Visayas) | Negros Oriental | Basay | Bal-os | 9.428 | 122.6255 | R | 4344 | 1143 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070260 | FTAP Globe | 9.4071 | 122.6411 | 2.89 | Terrestrial Optical Fiber Drop | 21.68 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2465 | 3 | 465 | 2465 | 0405809002 | Region IV-A (CALABARZON) | Rizal | Morong | Can-Cal-Lan | 14.5271 | 121.2499 | R | 4707 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01852 | Edgepoint | 14.5282 | 121.2492 | 0.13 | Terrestrial Optical Fiber Drop | 1.29 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2466 | 3 | 466 | 2466 | 0304928003 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Liwayway | 15.4435 | 121.0651 | R | 4402 | 1257 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1208 | FTAP Smart | 15.446 | 121.0747 | 1.07 | Terrestrial Optical Fiber Drop | 0.07 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2467 | 3 | 467 | 2467 | 1004311001 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Aplaya | 8.6054 | 124.7656 | U | 6221 | 1595 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 0.21 | Terrestrial Optical Fiber Drop | 1.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2468 | 3 | 468 | 2468 | 0702251033 | Region VII (Central Visayas) | Cebu | City of Toledo | Sangi | 10.3868 | 123.6528 | U | 5497 | 1446 | 434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 1.12 | Terrestrial Optical Fiber Drop | 1.48 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2469 | 3 | 469 | 2469 | 0307114004 | Region III (Central Luzon) | Zambales | Subic | Baraca-Camachile | 14.8788 | 120.2336 | U | 3533 | 929 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01076 | Edgepoint | 14.8785 | 120.2313 | 0.25 | Terrestrial Optical Fiber Drop | 1.22 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2470 | 3 | 470 | 2470 | 0506209018 | Region V (Bicol Region) | Sorsogon | Irosin | Monbon | 12.7289 | 124.0169 | R | 4378 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03124-C10 | PTCI/MIDC | 12.733 | 124.0141 | 0.55 | Terrestrial Optical Fiber Drop | 3.58 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2471 | 3 | 471 | 2471 | 0105522033 | Region I (Ilocos Region) | Pangasinan | Lingayen | Tonton | 16.0272 | 120.25 | R | 4826 | 1340 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00442 | Edgepoint | 16.0278 | 120.2507 | 0.1 | Terrestrial Optical Fiber Drop | 1.91 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2472 | 3 | 472 | 2472 | 0803738056 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Ipil | 10.9761 | 124.6345 | U | 9712 | 2555 | 767 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0094 | PTCI/MIDC | 10.9899 | 124.6235 | 1.95 | Terrestrial Optical Fiber Drop | 2.3 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2473 | 3 | 473 | 2473 | 0201523002 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Casambalangan | 18.3764 | 122.1261 | R | 4651 | 1192 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01161-B06 | PTCI/MIDC | 18.375 | 122.1235 | 0.31 | Terrestrial Optical Fiber Drop | 3.33 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2474 | 3 | 474 | 2474 | 0702234018 | Region VII (Central Visayas) | Cebu | City of Naga | Naalad | 10.2094 | 123.7445 | R | 3626 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 1.39 | Terrestrial Optical Fiber Drop | 4.07 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2475 | 3 | 475 | 2475 | 1206315008 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | New Iloilo | 6.5462 | 124.789 | R | 4972 | 1381 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120101 | FTAP BTS | 6.5372 | 124.7964 | 1.28 | Terrestrial Optical Fiber Drop | 20.43 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2476 | 3 | 476 | 2476 | 0803726014 | Region VIII (Eastern Visayas) | Leyte | Kananga | Natubgan | 11.1975 | 124.5654 | R | 3126 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 2.16 | Terrestrial Optical Fiber Drop | 1.45 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2477 | 3 | 477 | 2477 | 0401002011 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Muzon Primero | 13.8482 | 120.9914 | R | 2599 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040546 | FTAP Globe | 13.8434 | 120.99 | 0.56 | Terrestrial Optical Fiber Drop | 1.34 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2478 | 3 | 478 | 2478 | 1001304029 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Sinangguyan | 7.7072 | 125.0037 | R | 4953 | 1303 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100214 | FTAP Globe | 7.7079 | 125.02 | 1.8 | Terrestrial Optical Fiber Drop | 3.41 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2479 | 3 | 479 | 2479 | 0405811013 | Region IV-A (CALABARZON) | Rizal | San Mateo | Gulod Malaya | 14.6735 | 121.1333 | U | 12408 | 3446 | 1034 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0045 | PTCI/MIDC | 14.675 | 121.1345 | 0.21 | Terrestrial Optical Fiber Drop | 2.37 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2480 | 3 | 480 | 2480 | 0603034028 | Region VI (Western Visayas) | Iloilo | Oton | San Antonio | 10.693 | 122.4915 | R | 2471 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060151 | FTAP BTS | 10.6858 | 122.4903 | 0.81 | Terrestrial Optical Fiber Drop | 1.23 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2481 | 3 | 481 | 2481 | 0402103007 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Dulong Bayan | 14.4497 | 120.9355 | U | 7100 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0001 | LDIC | 14.4497 | 120.9334 | 0.22 | Terrestrial Optical Fiber Drop | 1.45 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2482 | 3 | 482 | 2482 | 0931700103 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Victoria | 7.049 | 122.1939 | R | 3537 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0135 | PTCI/MIDC | 7.0578 | 122.1946 | 0.99 | Terrestrial Optical Fiber Drop | 20.33 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2483 | 3 | 483 | 2483 | 0201522015 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Namuac | 18.6058 | 121.1738 | R | 3793 | 972 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0066 | LDIC | 121.1798 | 18.6012 | 0.82 | Terrestrial Optical Fiber Drop | 8.44 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2484 | 3 | 484 | 2484 | 1102315028 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Salvacion | 7.3178 | 125.6887 | U | 10928 | 2953 | 886 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDNG0120 | PTCI/MIDC | 7.3129 | 125.6909 | 0.6 | Terrestrial Optical Fiber Drop | 2.12 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2485 | 3 | 485 | 2485 | 1600210003 | Region XIII (Caraga) | Agusan del Norte | Santiago | Jagupit | 9.2424 | 125.5579 | R | 3315 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ADN_0005 | LDIC | 9.2418 | 125.5594 | 0.18 | Terrestrial Optical Fiber Drop | 2.7 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2486 | 3 | 486 | 2486 | 0205004005 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Almaguer North | 16.363 | 121.0966 | U | 3339 | 878 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01534-B05 | PTCI/MIDC | 16.3595 | 121.1042 | 0.9 | Terrestrial Optical Fiber Drop | 1.36 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2487 | 3 | 487 | 2487 | 0403406004 | Region IV-A (CALABARZON) | Laguna | Calauan | Hanggan | 14.1782 | 121.3023 | R | 3413 | 1034 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040277 | FTAP Globe | 14.1723 | 121.3161 | 1.63 | Terrestrial Optical Fiber Drop | 2.37 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2488 | 3 | 488 | 2488 | 0403419016 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | San Isidro | 14.2798 | 121.4581 | R | 3022 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.62 | Terrestrial Optical Fiber Drop | 1.09 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2489 | 3 | 489 | 2489 | 0604532006 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pandanon | 10.5765 | 123.178 | R | 2908 | 785 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0126 | PTCI/MIDC | 10.6316 | 123.1015 | 10.37 | Terrestrial Optical Fiber Drop | 2.85 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2490 | 3 | 490 | 2490 | 0203101023 | Region II (Cagayan Valley) | Isabela | Alicia | San Antonio | 16.7738 | 121.6997 | R | 2161 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 1.01 | Terrestrial Optical Fiber Drop | 1.39 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2491 | 3 | 491 | 2491 | 0403426008 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Labuin | 14.2683 | 121.4001 | R | 5029 | 1523 | 457 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S4291 | FTAP Smart | 14.2707 | 121.4145 | 0.26 | Terrestrial Optical Fiber Drop | 1.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2492 | 3 | 492 | 2492 | 0702216015 | Region VII (Central Visayas) | Cebu | Catmon | Panalipan | 10.6494 | 124.0239 | R | 4169 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070060 | FTAP BTS | 10.6562 | 124.0212 | 0.81 | Terrestrial Optical Fiber Drop | 5.08 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2493 | 3 | 493 | 2493 | 0501606037 | Region V (Bicol Region) | Camarines Norte | Labo | Malatap | 14.1642 | 122.6174 | R | 2597 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050014 | FTAP Globe | 14.1778 | 122.6227 | 1.62 | Terrestrial Optical Fiber Drop | 1.69 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2494 | 3 | 494 | 2494 | 1001312065 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Sumpong | 8.1641 | 125.1194 | U | 10342 | 2721 | 816 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 1.1 | Terrestrial Optical Fiber Drop | 2.03 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2495 | 3 | 495 | 2495 | 0604520009 | Region VI (Western Visayas) | Negros Occidental | Murcia | Blumentritt | 10.6203 | 123.0645 | U | 12890 | 3483 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 0.92 | Terrestrial Optical Fiber Drop | 2.88 | 2.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2496 | 3 | 496 | 2496 | 0305407031 | Region III (Central Luzon) | Pampanga | Guagua | Santo Cristo | 14.9722 | 120.6182 | U | 3997 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 1.55 | Terrestrial Optical Fiber Drop | 1.21 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2497 | 3 | 497 | 2497 | 0105530001 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Alipangpang | 16.1062 | 120.5631 | U | 6355 | 1765 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00408 | Edgepoint | 16.1087 | 120.5657 | 0.39 | Terrestrial Optical Fiber Drop | 2.43 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2498 | 3 | 498 | 2498 | 0702241015 | Region VII (Central Visayas) | Cebu | San Fernando | Pitalo | 10.1757 | 123.7217 | U | 8064 | 2122 | 637 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0146 | PTCI/MIDC | 10.1738 | 123.7182 | 0.44 | Terrestrial Optical Fiber Drop | 2.11 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2499 | 3 | 499 | 2499 | 0402119035 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Silang Junction North | 14.1307 | 120.9548 | U | 2614 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02196-C08 | PTCI/MIDC | 14.1417 | 120.974 | 0.59 | Terrestrial Optical Fiber Drop | 2.76 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2500 | 3 | 500 | 2500 | 0304903094 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Sumacab Este | 15.4446 | 120.9443 | U | 4923 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0004 | LDIC | 15.4419 | 120.9391 | 0.64 | Terrestrial Optical Fiber Drop | 2.04 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2501 | 3 | 501 | 2501 | 0431200017 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Gulang-gulang | 13.9548 | 121.6119 | U | 28548 | 7137 | 2141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02135-C08 | PTCI/MIDC | 13.9601 | 121.6134 | 0.61 | Terrestrial Optical Fiber Drop | 2.4 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2502 | 3 | 502 | 2502 | 0501715033 | Region V (Bicol Region) | Camarines Sur | Goa | Tagongtong | 13.6949 | 123.4752 | R | 2716 | 646 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050064 | FTAP Globe | 13.6982 | 123.4789 | 0.54 | Terrestrial Optical Fiber Drop | 1.41 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2503 | 3 | 503 | 2503 | 0304904015 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Gregorio | 15.2551 | 120.86 | R | 2344 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.64 | Terrestrial Optical Fiber Drop | 1.11 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2504 | 3 | 504 | 2504 | 0301403027 | Region III (Central Luzon) | Bulacan | Baliuag | Tibag | 14.9555 | 120.9039 | U | 3114 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030523 | FTAP Globe | 14.9547 | 120.9046 | 0.11 | Terrestrial Optical Fiber Drop | 1.55 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2505 | 3 | 505 | 2505 | 0103302014 | Region I (Ilocos Region) | La Union | Aringay | San Benito Norte | 16.4127 | 120.3528 | R | 3012 | 814 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0013 | LDIC | 16.4152 | 120.3518 | 0.3 | Terrestrial Optical Fiber Drop | 1.97 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2506 | 3 | 506 | 2506 | 0307113004 | Region III (Central Luzon) | Zambales | Santa Cruz | Bayto | 15.7275 | 119.9097 | R | 4316 | 1135 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00590 | Edgepoint | 15.7248 | 119.9066 | 0.45 | Terrestrial Optical Fiber Drop | 4.48 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2507 | 3 | 507 | 2507 | 0402119018 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | San Jose | 14.123 | 120.968 | U | 7133 | 2097 | 629 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02153-C08 | PTCI/MIDC | 14.1292 | 120.9715 | 0.79 | Terrestrial Optical Fiber Drop | 1.35 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2508 | 3 | 508 | 2508 | 0305403017 | Region III (Central Luzon) | Pampanga | Arayat | Plazang Luma | 15.151 | 120.7672 | U | 5689 | 1422 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.47 | Terrestrial Optical Fiber Drop | 1.09 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2509 | 3 | 509 | 2509 | 1102319005 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Canocotan | 7.4068 | 125.7784 | U | 9916 | 2680 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0019 | PTCI/MIDC | 7.4089 | 125.7784 | 0.23 | Terrestrial Optical Fiber Drop | 2.24 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2510 | 3 | 510 | 2510 | 0304932027 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Young | 15.4451 | 120.7812 | R | 4233 | 1209 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01419-B07 | PTCI/MIDC | 15.4394 | 120.779 | 0.68 | Terrestrial Optical Fiber Drop | 1.2 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2511 | 3 | 511 | 2511 | 0600401006 | Region VI (Western Visayas) | Aklan | Altavas | Linayasan | 11.5402 | 122.4746 | R | 2068 | 530 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.44 | Terrestrial Optical Fiber Drop | 1.48 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2512 | 3 | 512 | 2512 | 0306916047 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maligaya | 15.4406 | 120.5992 | U | 4331 | 1110 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-03013 | Edgepoint | 120.5986 | 15.4446 | 0.45 | Terrestrial Optical Fiber Drop | 2.35 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2513 | 3 | 513 | 2513 | 1004326012 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Poblacion 2 | 8.5843 | 124.7717 | R | 2792 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0080 | PTCI/MIDC | 8.5798 | 124.7768 | 0.76 | Terrestrial Optical Fiber Drop | 1.18 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2514 | 3 | 514 | 2514 | 0803739017 | Region VIII (Eastern Visayas) | Leyte | Palo | Libertad | 11.1736 | 124.9574 | R | 4363 | 1148 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080146 | FTAP BTS | 11.1554 | 124.9671 | 2.28 | Terrestrial Optical Fiber Drop | 5.38 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2515 | 3 | 515 | 2515 | 0806407040 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Mantahan | 10.1333 | 124.8517 | R | 4152 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 0.57 | Terrestrial Optical Fiber Drop | 0.72 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2516 | 3 | 516 | 2516 | 1130700043 | Region XI (Davao Region) | Davao del Sur | City of Davao | Dumoy | 7.0322 | 125.5124 | U | 20432 | 6009 | 1803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110497 | FTAP Globe | 7.0355 | 125.5126 | 0.37 | Terrestrial Optical Fiber Drop | 2.54 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2517 | 3 | 517 | 2517 | 0403424063 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Rafael | 14.0729 | 121.309 | U | 5121 | 1551 | 465 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01993-C08 | PTCI/MIDC | 14.0703 | 121.3069 | 0.36 | Terrestrial Optical Fiber Drop | 1.21 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2518 | 3 | 518 | 2518 | 0304926031 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 2nd | 15.7975 | 120.9751 | U | 6641 | 1897 | 569 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01506-B07 | PTCI/MIDC | 15.7991 | 120.9771 | 0.28 | Terrestrial Optical Fiber Drop | 1.4 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2519 | 3 | 519 | 2519 | 0702207020 | Region VII (Central Visayas) | Cebu | Badian | Poblacion | 9.8645 | 123.3934 | R | 4388 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070367 | FTAP Globe | 9.7893 | 123.3464 | 9.82 | Terrestrial Optical Fiber Drop | 8.24 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2520 | 3 | 520 | 2520 | 0603031012 | Region VI (Western Visayas) | Iloilo | Mina | Mina East | 10.9302 | 122.5722 | R | 1317 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 1.02 | Terrestrial Optical Fiber Drop | 1.42 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2521 | 3 | 521 | 2521 | 0301419020 | Region III (Central Luzon) | Bulacan | San Ildefonso | Malipampang | 15.0562 | 120.939 | U | 6904 | 1972 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3642 | FTAP Smart | 15.0561 | 120.9369 | 0.22 | Terrestrial Optical Fiber Drop | 2.02 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2522 | 3 | 522 | 2522 | 1004307003 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Bolobolo | 8.5561 | 124.5333 | U | 4752 | 1218 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100124 (FTAP_GLO_PH100124) | FTAP Globe | 8.5545 | 124.5256 | 0.87 | Terrestrial Optical Fiber Drop | 1.05 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2523 | 3 | 523 | 2523 | 0501730024 | Region V (Bicol Region) | Camarines Sur | Ragay | Lower Santa Cruz | 13.8166 | 122.7976 | R | 1448 | 344 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050045 | FTAP Globe | 13.8174 | 122.7937 | 0.43 | Terrestrial Optical Fiber Drop | 1 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2524 | 3 | 524 | 2524 | 0300809021 | Region III (Central Luzon) | Bataan | Orani | Tapulao | 14.8131 | 120.5198 | R | 5148 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00908-B07 | PTCI/MIDC | 14.8084 | 120.5269 | 0.93 | Terrestrial Optical Fiber Drop | 2.16 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2525 | 3 | 525 | 2525 | 1108204003 | Region XI (Davao Region) | Davao de Oro | Maco | Binuangan | 7.3703 | 125.854 | U | 6907 | 1866 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110429 | FTAP Globe | 7.3773 | 125.8398 | 1.75 | Terrestrial Optical Fiber Drop | 1.54 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2526 | 3 | 526 | 2526 | 0601914021 | Region VI (Western Visayas) | Capiz | City of Roxas | Cabugao | 11.5123 | 122.7476 | R | 2513 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 1.16 | Terrestrial Optical Fiber Drop | 1.34 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2527 | 3 | 527 | 2527 | 0402115028 | Region IV-A (CALABARZON) | Cavite | Naic | San Roque | 14.3099 | 120.7719 | R | 4809 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040178 | FTAP Globe | 14.314 | 120.7694 | 0.53 | Terrestrial Optical Fiber Drop | 1.3 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2528 | 3 | 528 | 2528 | 0501736016 | Region V (Bicol Region) | Camarines Sur | Tigaon | Salvacion | 13.6021 | 123.4728 | R | 4195 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050097 | FTAP Globe | 13.5917 | 123.4584 | 1.93 | Terrestrial Optical Fiber Drop | 4.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2529 | 3 | 529 | 2529 | 0401014040 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 1 | 13.9422 | 121.1568 | U | 3616 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040438 | FTAP Globe | 13.9434 | 121.1521 | 0.53 | Terrestrial Optical Fiber Drop | 1.07 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2530 | 3 | 530 | 2530 | 0702211013 | Region VII (Central Visayas) | Cebu | City of Bogo | La Paz | 10.9983 | 123.9822 | R | 4204 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070304 | FTAP Globe | 11.0038 | 123.9821 | 0.6 | Terrestrial Optical Fiber Drop | 6.08 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2531 | 3 | 531 | 2531 | 0201522004 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Centro II | 18.5657 | 121.2284 | R | 2744 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00006 | Edgepoint | 18.5712 | 121.2253 | 0.69 | Terrestrial Optical Fiber Drop | 1.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2532 | 3 | 532 | 2532 | 0403424002 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Bagong Pook VI-C | 14.073 | 121.3212 | R | 2038 | 617 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.4 | Terrestrial Optical Fiber Drop | 1.03 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2533 | 3 | 533 | 2533 | 0500509013 | Region V (Bicol Region) | Albay | Malilipot | San Isidro Ilawod | 13.3311 | 123.7377 | R | 3952 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050136 | FTAP Globe | 13.3221 | 123.7369 | 1.01 | Terrestrial Optical Fiber Drop | 2.51 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2534 | 3 | 534 | 2534 | 0501701001 | Region V (Bicol Region) | Camarines Sur | Baao | Agdangan Pob. | 13.4932 | 123.3249 | R | 4589 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050112 | FTAP Globe | 13.4917 | 123.3276 | 0.33 | Terrestrial Optical Fiber Drop | 3.52 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2535 | 3 | 535 | 2535 | 0907333014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Tubod | 7.8063 | 123.2052 | R | 3976 | 1019 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTZSG0033 | PTCI/MIDC | 7.8339 | 123.2242 | 3.71 | Terrestrial Optical Fiber Drop | 18.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2536 | 3 | 536 | 2536 | 0305404002 | Region III (Central Luzon) | Pampanga | Bacolor | Cabalantian | 15.0204 | 120.6735 | U | 6500 | 1625 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02684 | Edgepoint | 15.0212 | 120.6732 | 0.09 | Terrestrial Optical Fiber Drop | 2.22 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2537 | 3 | 537 | 2537 | 0305406009 | Region III (Central Luzon) | Pampanga | Floridablanca | Consuelo | 14.97 | 120.4974 | R | 3829 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01597-B07 | PTCI/MIDC | 14.9723 | 120.5012 | 0.49 | Terrestrial Optical Fiber Drop | 2.36 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2538 | 3 | 538 | 2538 | 1208007021 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Nagpan | 6.333 | 125.2642 | R | 3494 | 895 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120306 | FTAP Globe | 6.3454 | 125.2651 | 1.38 | Terrestrial Optical Fiber Drop | 3.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2539 | 3 | 539 | 2539 | 0405619037 | Region IV-A (CALABARZON) | Quezon | Gumaca | Progreso | 13.9077 | 122.0878 | R | 3156 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040502 | FTAP Globe | 13.9084 | 122.0941 | 0.69 | Terrestrial Optical Fiber Drop | 2.74 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2540 | 3 | 540 | 2540 | 0105518002 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Bacayao Sur | 16.0222 | 120.3463 | R | 2540 | 705 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00451 | Edgepoint | 16.0219 | 120.3511 | 0.51 | Terrestrial Optical Fiber Drop | 1.73 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2541 | 3 | 541 | 2541 | 0601905007 | Region VI (Western Visayas) | Capiz | Ivisan | Ilaya-Ivisan | 11.5178 | 122.7197 | R | 4049 | 1065 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 2.19 | Terrestrial Optical Fiber Drop | 2.83 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2542 | 3 | 542 | 2542 | 1404404005 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Bontoc Ili | 17.0872 | 120.9756 | R | 4395 | 1187 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MOU-00185 | Edgepoint | 17.0863 | 120.9769 | 0.17 | Terrestrial Optical Fiber Drop | 7.96 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2543 | 3 | 543 | 2543 | 0403414007 | Region IV-A (CALABARZON) | Laguna | Mabitac | Paagahan | 14.4423 | 121.4004 | R | 4432 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040097 | FTAP Globe | 14.4463 | 121.3812 | 2.12 | Terrestrial Optical Fiber Drop | 3.14 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2544 | 3 | 544 | 2544 | 0301403024 | Region III (Central Luzon) | Bulacan | Baliuag | Tangos | 14.9703 | 120.8945 | U | 8119 | 2319 | 696 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02426-B07 | PTCI/MIDC | 14.9694 | 120.896 | 0.19 | Terrestrial Optical Fiber Drop | 1.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2545 | 3 | 545 | 2545 | 0305402010 | Region III (Central Luzon) | Pampanga | Apalit | Sampaloc | 14.9673 | 120.7567 | U | 14226 | 3556 | 1067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1118 | FTAP Smart | 14.9691 | 120.7568 | 0.2 | Terrestrial Optical Fiber Drop | 2.13 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2546 | 3 | 546 | 2546 | 0403424001 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Bagong Bayan II-A | 14.067 | 121.3195 | U | 7093 | 2149 | 645 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.93 | Terrestrial Optical Fiber Drop | 1.39 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2547 | 3 | 547 | 2547 | 1030500001 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Agusan | 8.4914 | 124.7429 | U | 19384 | 5384 | 1615 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0035 | PTCI/MIDC | 8.4944 | 124.7476 | 0.62 | Terrestrial Optical Fiber Drop | 1.04 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2548 | 3 | 548 | 2548 | 0501606041 | Region V (Bicol Region) | Camarines Norte | Labo | Masalong | 14.1693 | 122.8075 | R | 3471 | 867 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03171-C10 | PTCI/MIDC | 14.1738 | 122.81 | 0.57 | Terrestrial Optical Fiber Drop | 3.27 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2549 | 3 | 549 | 2549 | 0203114062 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Naguilian Norte | 17.1644 | 121.8722 | R | 3349 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0006 | LDIC | 17.1613 | 121.8715 | 0.35 | Terrestrial Optical Fiber Drop | 1.14 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2550 | 3 | 550 | 2550 | 0301420057 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz V | 14.856 | 121.0513 | R | 3984 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01200 | Edgepoint | 14.7762 | 121.072 | 0.47 | Terrestrial Optical Fiber Drop | 2.18 | 5.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2551 | 3 | 551 | 2551 | 0201503012 | Region II (Cagayan Valley) | Cagayan | Allacapan | Daan-Ili | 18.2385 | 121.5551 | R | 1923 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CAG_0062 | LDIC | 121.5595 | 18.2277 | 1.28 | Terrestrial Optical Fiber Drop | 1.38 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2552 | 3 | 552 | 2552 | 0603035033 | Region VI (Western Visayas) | Iloilo | City of Passi | Man-it | 11.099 | 122.6362 | R | 4702 | 1237 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.84 | Terrestrial Optical Fiber Drop | 1.3 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2553 | 3 | 553 | 2553 | 0103302010 | Region I (Ilocos Region) | La Union | Aringay | Poblacion | 16.3958 | 120.3557 | R | 3517 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00343 | Edgepoint | 16.3924 | 120.3526 | 0.51 | Terrestrial Optical Fiber Drop | 3.86 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2554 | 3 | 554 | 2554 | 0403415011 | Region IV-A (CALABARZON) | Laguna | Magdalena | Cigaras | 14.2239 | 121.4301 | R | 3939 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 2.54 | Terrestrial Optical Fiber Drop | 2.82 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2555 | 3 | 555 | 2555 | 0301418010 | Region III (Central Luzon) | Bulacan | Pulilan | Longos | 14.8967 | 120.8648 | U | 6080 | 1737 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01059 | Edgepoint | 14.8942 | 120.8668 | 0.36 | Terrestrial Optical Fiber Drop | 1.64 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2556 | 3 | 556 | 2556 | 0304909025 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Talabutab Norte | 15.5998 | 121.0781 | R | 4419 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00637 | Edgepoint | 15.5998 | 121.0747 | 0.37 | Terrestrial Optical Fiber Drop | 2.95 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2557 | 3 | 557 | 2557 | 0401014043 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 2 | 13.9422 | 121.1573 | U | 3253 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.56 | Terrestrial Optical Fiber Drop | 1.01 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2558 | 3 | 558 | 2558 | 0501720013 | Region V (Bicol Region) | Camarines Sur | Magarao | Santa Lucia | 13.6651 | 123.2025 | U | 6463 | 1538 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0002 | PTCI/MIDC | 13.6611 | 123.2033 | 0.45 | Terrestrial Optical Fiber Drop | 2.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2559 | 3 | 559 | 2559 | 0300809025 | Region III (Central Luzon) | Bataan | Orani | Apollo | 14.8013 | 120.5193 | R | 1948 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0016 | PTCI/MIDC | 14.8006 | 120.5268 | 0.27 | Terrestrial Optical Fiber Drop | 1.83 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2560 | 3 | 560 | 2560 | 1004322007 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Inobulan | 8.885 | 124.7911 | R | 3210 | 823 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 3.33 | Terrestrial Optical Fiber Drop | 3.1 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2561 | 3 | 561 | 2561 | 0702250003 | Region VII (Central Visayas) | Cebu | City of Talisay | Cansojong | 10.2503 | 123.8543 | U | 17756 | 4672 | 1402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070360 | FTAP Globe | 10.2466 | 123.8519 | 0.49 | Terrestrial Optical Fiber Drop | 1.37 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2562 | 3 | 562 | 2562 | 0307104003 | Region III (Central Luzon) | Zambales | Castillejos | Del Pilar | 14.9261 | 120.2148 | U | 12730 | 3350 | 1005 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01836-B07 | PTCI/MIDC | 14.9337 | 120.2109 | 0.94 | Terrestrial Optical Fiber Drop | 1.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2563 | 3 | 563 | 2563 | 0305416008 | Region III (Central Luzon) | Pampanga | City of San Fernando | Del Pilar | 15.034 | 120.6953 | U | 11493 | 2873 | 862 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00010-B07 | PTCI/MIDC | 15.0353 | 120.694 | 0.21 | Terrestrial Optical Fiber Drop | 1.65 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2564 | 3 | 564 | 2564 | 0301403021 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Niño | 14.986 | 120.8917 | R | 4520 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02373-B07 | PTCI/MIDC | 14.9881 | 120.8862 | 0.64 | Terrestrial Optical Fiber Drop | 2.66 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2565 | 3 | 565 | 2565 | 0702231002 | Region VII (Central Visayas) | Cebu | Medellin | Curva | 11.139 | 124.0035 | R | 2524 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 4.7 | Terrestrial Optical Fiber Drop | 1.83 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2566 | 3 | 566 | 2566 | 0701205014 | Region VII (Central Visayas) | Bohol | Baclayon | San Vicente | 9.6252 | 123.922 | R | 1417 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 3.6 | Terrestrial Optical Fiber Drop | 1 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2567 | 3 | 567 | 2567 | 0704601008 | Region VII (Central Visayas) | Negros Oriental | Amlan | Tandayag | 9.4478 | 123.2361 | R | 4074 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0070 | PTCI/MIDC | 9.4414 | 123.2359 | 0.71 | Terrestrial Optical Fiber Drop | 2.18 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2568 | 3 | 568 | 2568 | 0803738011 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Cagbuhangin | 11.1003 | 124.5846 | R | 1984 | 522 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080189 | FTAP BTS | 11.0827 | 124.5638 | 3 | Terrestrial Optical Fiber Drop | 1.39 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2569 | 3 | 569 | 2569 | 0501708022 | Region V (Bicol Region) | Camarines Sur | Calabanga | Manguiring | 13.7461 | 123.2783 | U | 4100 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050054 | FTAP Globe | 13.7374 | 123.2697 | 1.34 | Terrestrial Optical Fiber Drop | 1.58 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2570 | 3 | 570 | 2570 | 0604511021 | Region VI (Western Visayas) | Negros Occidental | Hinigaran | Pilar | 10.2489 | 122.8578 | R | 5013 | 1354 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060380 | FTAP Globe | 10.24 | 122.8972 | 4.42 | Terrestrial Optical Fiber Drop | 13.83 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2571 | 3 | 571 | 2571 | 0702234008 | Region VII (Central Visayas) | Cebu | City of Naga | Colon | 10.2213 | 123.7611 | U | 5364 | 1411 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 2.07 | Terrestrial Optical Fiber Drop | 1.83 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2572 | 3 | 572 | 2572 | 0105546022 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Mabanogbog | 15.9755 | 120.5515 | R | 3498 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010178 | FTAP Globe | 15.9724 | 120.5531 | 0.39 | Terrestrial Optical Fiber Drop | 2.99 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2573 | 3 | 573 | 2573 | 0306904008 | Region III (Central Luzon) | Tarlac | Capas | Estrada | 15.3996 | 120.5984 | U | 4234 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01809-B07 | PTCI/MIDC | 15.3957 | 120.5942 | 0.63 | Terrestrial Optical Fiber Drop | 1.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2574 | 3 | 574 | 2574 | 0201512003 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay II | 17.5705 | 121.6781 | R | 2746 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020052 | FTAP Globe | 17.5692 | 121.6685 | 1.02 | Terrestrial Optical Fiber Drop | 2.12 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2575 | 3 | 575 | 2575 | 0704604025 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Panala-an | 9.6076 | 123.0362 | R | 4233 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0007 | PTCI/MIDC | 9.6245 | 123.0979 | 7.03 | Terrestrial Optical Fiber Drop | 9.74 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2576 | 3 | 576 | 2576 | 0704614001 | Region VII (Central Visayas) | Negros Oriental | Mabinay | Abis | 9.7385 | 122.9381 | R | 3751 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0034 | PTCI/MIDC | 9.7257 | 122.9276 | 1.83 | Terrestrial Optical Fiber Drop | 1.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2577 | 3 | 577 | 2577 | 0501701018 | Region V (Bicol Region) | Camarines Sur | Baao | San Juan | 13.4519 | 123.3874 | R | 3794 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050119 | FTAP Globe | 13.4487 | 123.3867 | 0.36 | Terrestrial Optical Fiber Drop | 2.47 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2578 | 3 | 578 | 2578 | 1401105006 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Bangao | 16.8184 | 120.8334 | U | 5463 | 1560 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 2.83 | Terrestrial Optical Fiber Drop | 2.11 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2579 | 3 | 579 | 2579 | 1004312003 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Buko | 8.9939 | 124.8048 | R | 2578 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 1.96 | Terrestrial Optical Fiber Drop | 1.72 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2580 | 3 | 580 | 2580 | 0401002018 | Region IV-A (CALABARZON) | Batangas | Alitagtag | San Jose | 13.8647 | 120.9969 | R | 2513 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03243-C08 | PTCI/MIDC | 13.8652 | 121.0025 | 0.61 | Terrestrial Optical Fiber Drop | 1.23 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2581 | 3 | 581 | 2581 | 0600403013 | Region VI (Western Visayas) | Aklan | Banga | Linabuan Sur | 11.6499 | 122.3444 | R | 4098 | 1050 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0015 | PTCI/MIDC | 11.6564 | 122.3448 | 0.73 | Terrestrial Optical Fiber Drop | 2.15 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2582 | 3 | 582 | 2582 | 1130700036 | Region XI (Davao Region) | Davao del Sur | City of Davao | Crossing Bayabas | 7.0252 | 125.4948 | U | 12909 | 3796 | 1139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110207 | FTAP BTS | 7.028 | 125.4948 | 0.31 | Terrestrial Optical Fiber Drop | 1.5 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2583 | 3 | 583 | 2583 | 0702205010 | Region VII (Central Visayas) | Cebu | Argao | Bulasa | 9.9315 | 123.6177 | R | 4032 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0006 | PTCI/MIDC | 9.9557 | 123.6173 | 2.7 | Terrestrial Optical Fiber Drop | 5.71 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2584 | 3 | 584 | 2584 | 0105546034 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | San Vicente | 15.9803 | 120.5701 | U | 9856 | 2737 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00491 | Edgepoint | 15.9774 | 120.565 | 0.64 | Terrestrial Optical Fiber Drop | 2.31 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2585 | 3 | 585 | 2585 | 0604520011 | Region VI (Western Visayas) | Negros Occidental | Murcia | Caliban | 10.5854 | 123.0719 | R | 3194 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 0.89 | Terrestrial Optical Fiber Drop | 2.22 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2586 | 3 | 586 | 2586 | 0300809023 | Region III (Central Luzon) | Bataan | Orani | Tugatog | 14.8014 | 120.5192 | U | 8501 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030604 | FTAP Globe | 14.8 | 120.5202 | 0.18 | Terrestrial Optical Fiber Drop | 1.84 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2587 | 3 | 587 | 2587 | 0702227014 | Region VII (Central Visayas) | Cebu | Liloan | Yati | 10.3933 | 123.9832 | U | 37883 | 9969 | 2991 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070322 | FTAP Globe | 10.3959 | 123.985 | 0.36 | Terrestrial Optical Fiber Drop | 2.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2588 | 3 | 588 | 2588 | 0304916018 | Region III (Central Luzon) | Nueva Ecija | Lupao | Parista | 15.8631 | 120.9193 | R | 4851 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030307 | FTAP Globe | 15.8633 | 120.9183 | 0.1 | Terrestrial Optical Fiber Drop | 3.32 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2589 | 3 | 589 | 2589 | 0105521009 | Region I (Ilocos Region) | Pangasinan | Labrador | Tobuan | 16.0556 | 120.1097 | R | 3257 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00427 | Edgepoint | 16.053 | 120.1143 | 0.57 | Terrestrial Optical Fiber Drop | 1.39 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2590 | 3 | 590 | 2590 | 0431200028 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Kanluran | 13.9497 | 121.6352 | U | 13027 | 3256 | 977 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0003 | PTCI/MIDC | 13.9492 | 121.6278 | 0.8 | Terrestrial Optical Fiber Drop | 1.42 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2591 | 3 | 591 | 2591 | 0501703027 | Region V (Bicol Region) | Camarines Sur | Bato | San Miguel | 13.3475 | 123.3836 | R | 4379 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02836-C10 | PTCI/MIDC | 13.3486 | 123.3761 | 0.83 | Terrestrial Optical Fiber Drop | 2.29 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2592 | 3 | 592 | 2592 | 0803738082 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Isidro | 11.0271 | 124.5948 | U | 6373 | 1677 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0101 | PTCI/MIDC | 11.0267 | 124.5934 | 0.16 | Terrestrial Optical Fiber Drop | 0.59 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2593 | 3 | 593 | 2593 | 1001317025 | Region X (Northern Mindanao) | Bukidnon | Quezon | Paitan | 7.7027 | 125.1132 | R | 3600 | 947 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 1.35 | Terrestrial Optical Fiber Drop | 0.56 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2594 | 3 | 594 | 2594 | 0305408016 | Region III (Central Luzon) | Pampanga | Lubao | San Isidro | 14.8847 | 120.5243 | R | 4453 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030561 | FTAP Globe | 14.8856 | 120.5198 | 0.49 | Terrestrial Optical Fiber Drop | 4.31 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2595 | 3 | 595 | 2595 | 1108204002 | Region XI (Davao Region) | Davao de Oro | Maco | Anislagan | 7.3458 | 125.8596 | R | 2787 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 1.39 | Terrestrial Optical Fiber Drop | 1.26 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2596 | 3 | 596 | 2596 | 0304903046 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Mabini Extension | 15.4857 | 120.9742 | U | 3497 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030381 | FTAP Globe | 15.486 | 120.9751 | 0.11 | Terrestrial Optical Fiber Drop | 1.47 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2597 | 3 | 597 | 2597 | 0403404011 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Niugan | 14.263 | 121.1286 | U | 42286 | 12813 | 3844 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02105-C08 | PTCI/MIDC | 14.2643 | 121.1272 | 0.21 | Terrestrial Optical Fiber Drop | 1.87 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2598 | 3 | 598 | 2598 | 1401103005 | Cordillera Administrative Region (CAR) | Benguet | Bakun | Gambang | 16.7419 | 120.7976 | R | 3886 | 1110 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140171 | FTAP Globe | 16.7237 | 120.784 | 2.48 | Terrestrial Optical Fiber Drop | 2.89 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2599 | 3 | 599 | 2599 | 1001315018 | Region X (Northern Mindanao) | Bukidnon | Maramag | Tubigon | 7.8357 | 125.0214 | R | 2775 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100053 | FTAP BTS | 7.837 | 125.0323 | 1.21 | Terrestrial Optical Fiber Drop | 2.6 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2600 | 3 | 600 | 2600 | 0405805019 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Niño | 14.5797 | 121.1137 | U | 6105 | 1695 | 509 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040040 | FTAP Globe | 14.5854 | 121.1118 | 0.4 | Terrestrial Optical Fiber Drop | 1.14 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2601 | 3 | 601 | 2601 | 0500516021 | Region V (Bicol Region) | Albay | Santo Domingo | San Isidro | 13.2296 | 123.7683 | R | 3161 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.88 | Terrestrial Optical Fiber Drop | 1.27 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2602 | 3 | 602 | 2602 | 0301403025 | Region III (Central Luzon) | Bulacan | Baliuag | Tarcan | 14.9325 | 120.8792 | U | 9208 | 2630 | 789 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01040-B07 | PTCI/MIDC | 14.9291 | 120.8846 | 0.69 | Terrestrial Optical Fiber Drop | 1.96 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2603 | 3 | 603 | 2603 | 0403405013 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Halang | 14.1978 | 121.1603 | U | 9407 | 2850 | 855 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02120-C08 | PTCI/MIDC | 14.2013 | 121.1654 | 0.68 | Terrestrial Optical Fiber Drop | 1.52 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2604 | 3 | 604 | 2604 | 0500518012 | Region V (Bicol Region) | Albay | Tiwi | Joroan | 13.4912 | 123.6213 | R | 3015 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050113 | FTAP Globe | 13.4889 | 123.6261 | 0.57 | Terrestrial Optical Fiber Drop | 2.27 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2605 | 3 | 605 | 2605 | 0304908016 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Sur | 15.2675 | 120.9499 | R | 4886 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NUE_0012 | LDIC | 15.2678 | 120.9503 | 0.05 | Terrestrial Optical Fiber Drop | 0.13 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2606 | 3 | 606 | 2606 | 1004321003 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Barra | 8.514 | 124.6076 | U | 15306 | 3924 | 1177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0042 | PTCI/MIDC | 8.5124 | 124.6138 | 0.7 | Terrestrial Optical Fiber Drop | 1.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2607 | 3 | 607 | 2607 | 0403424013 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay III-C | 14.0687 | 121.3305 | R | 3040 | 921 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 0.65 | Terrestrial Optical Fiber Drop | 1.05 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2608 | 3 | 608 | 2608 | 0403406007 | Region IV-A (CALABARZON) | Laguna | Calauan | Lamot 2 | 14.1616 | 121.3296 | U | 8226 | 2492 | 748 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040281 | FTAP Globe | 14.1602 | 121.3319 | 0.28 | Terrestrial Optical Fiber Drop | 2.42 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2609 | 3 | 609 | 2609 | 0630200042 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 7 | 10.6619 | 122.9441 | U | 2503 | 695 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0015 | PTCI/MIDC | 10.6614 | 122.9402 | 0.43 | Terrestrial Optical Fiber Drop | 1.05 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2610 | 3 | 610 | 2610 | 0330100028 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Domingo | 15.1265 | 120.6004 | U | 19500 | 5416 | 1625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0023 | FTAP Smart | 15.1368 | 120.5909 | 0.4 | Terrestrial Optical Fiber Drop | 0.41 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2611 | 3 | 611 | 2611 | 0403424070 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Isabel | 14.0868 | 121.35 | R | 4198 | 1272 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040336 | FTAP Globe | 14.0846 | 121.3413 | 0.97 | Terrestrial Optical Fiber Drop | 3.68 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2612 | 3 | 612 | 2612 | 0702241014 | Region VII (Central Visayas) | Cebu | San Fernando | Panadtaran | 10.1514 | 123.6988 | U | 6360 | 1673 | 502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.75 | Terrestrial Optical Fiber Drop | 1.58 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2613 | 3 | 613 | 2613 | 0631000026 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Buntatala | 10.7686 | 122.5836 | U | 4584 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.89 | Terrestrial Optical Fiber Drop | 2.02 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2614 | 3 | 614 | 2614 | 0203126017 | Region II (Cagayan Valley) | Isabela | Roxas | San Antonio | 17.0951 | 121.615 | R | 3658 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0041 | PTCI/MIDC | 17.0989 | 121.6164 | 0.45 | Terrestrial Optical Fiber Drop | 2.31 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2615 | 3 | 615 | 2615 | 0304908010 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Lorenzo | 15.3125 | 120.9538 | U | 6467 | 1847 | 554 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02508 | Edgepoint | 15.3146 | 120.9576 | 0.47 | Terrestrial Optical Fiber Drop | 1.04 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2616 | 3 | 616 | 2616 | 0304908013 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Vicente | 15.3141 | 120.9479 | U | 9910 | 2831 | 849 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030419 | FTAP Globe | 15.3115 | 120.9467 | 0.32 | Terrestrial Optical Fiber Drop | 0.75 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2617 | 3 | 617 | 2617 | 1600302005 | Region XIII (Caraga) | Agusan del Sur | Bunawan | Poblacion | 8.1702 | 125.9995 | R | 4991 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 2.91 | Terrestrial Optical Fiber Drop | 1.39 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2618 | 3 | 618 | 2618 | 0702216020 | Region VII (Central Visayas) | Cebu | Catmon | Flores | 10.7178 | 124.0124 | R | 3458 | 910 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070312 | FTAP Globe | 10.7253 | 124.014 | 0.85 | Terrestrial Optical Fiber Drop | 2.66 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2619 | 3 | 619 | 2619 | 0702224034 | Region VII (Central Visayas) | Cebu | Dumanjug | Tangil | 10.0722 | 123.4493 | R | 3196 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CEB_0001 | LDIC | 10.0758 | 123.4523 | 0.52 | Terrestrial Optical Fiber Drop | 2.28 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2620 | 3 | 620 | 2620 | 0401017006 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Sur | 14.0362 | 121.162 | R | 5100 | 1416 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.59 | Terrestrial Optical Fiber Drop | 1.75 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2621 | 3 | 621 | 2621 | 0600402004 | Region VI (Western Visayas) | Aklan | Balete | Calizo | 11.5682 | 122.3639 | R | 4501 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 0.52 | Terrestrial Optical Fiber Drop | 1.02 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2622 | 3 | 622 | 2622 | 0307701012 | Region III (Central Luzon) | Aurora | Baler | Suclayin | 15.7557 | 121.5486 | U | 4865 | 1280 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-AUR-02563 | Edgepoint | 15.7541 | 121.5528 | 0.48 | Terrestrial Optical Fiber Drop | 1.67 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2623 | 3 | 623 | 2623 | 0403426011 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Pagsawitan | 14.2651 | 121.4252 | U | 11162 | 3382 | 1015 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01991-C08 | PTCI/MIDC | 14.2664 | 121.4208 | 0.49 | Terrestrial Optical Fiber Drop | 2.02 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2624 | 3 | 624 | 2624 | 0704601001 | Region VII (Central Visayas) | Negros Oriental | Amlan | Bio-os | 9.4707 | 123.1956 | R | 4275 | 1125 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 1.39 | Terrestrial Optical Fiber Drop | 3.05 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2625 | 3 | 625 | 2625 | 0301417003 | Region III (Central Luzon) | Bulacan | Plaridel | Banga I | 14.8879 | 120.8711 | U | 6159 | 1759 | 528 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030563 | FTAP Globe | 14.8814 | 120.8665 | 0.51 | Terrestrial Optical Fiber Drop | 2.72 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2626 | 3 | 626 | 2626 | 0702241016 | Region VII (Central Visayas) | Cebu | San Fernando | San Isidro | 10.1725 | 123.7149 | U | 4641 | 1221 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0146 | PTCI/MIDC | 10.1738 | 123.7182 | 0.38 | Terrestrial Optical Fiber Drop | 1.36 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2627 | 3 | 627 | 2627 | 0305416013 | Region III (Central Luzon) | Pampanga | City of San Fernando | Lourdes | 15.0314 | 120.6878 | R | 4292 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00922 | Edgepoint | 15.0321 | 120.6895 | 0.2 | Terrestrial Optical Fiber Drop | 1.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2628 | 3 | 628 | 2628 | 1606724026 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Luna | 9.7668 | 125.4845 | U | 14000 | 3414 | 1024 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130037 | FTAP BTS | 9.7788 | 125.4839 | 1.34 | Terrestrial Optical Fiber Drop | 2.62 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2629 | 3 | 629 | 2629 | 0305421007 | Region III (Central Luzon) | Pampanga | Sto. Tomas | San Vicente | 14.9946 | 120.7044 | U | 10661 | 2665 | 800 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00900 | Edgepoint | 15.0665 | 120.6602 | 0.66 | Terrestrial Optical Fiber Drop | 1.47 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2630 | 3 | 630 | 2630 | 1606819008 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Mabua | 17.1051 | 122.2741 | U | 8562 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 1.72 | Terrestrial Optical Fiber Drop | 27.52 | 37.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2631 | 3 | 631 | 2631 | 0304903031 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Dicarma | 15.4843 | 120.9713 | U | 4735 | 1352 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1236 | FTAP Smart | 15.4805 | 120.9702 | 0.44 | Terrestrial Optical Fiber Drop | 1.13 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2632 | 3 | 632 | 2632 | 0600407006 | Region VI (Western Visayas) | Aklan | Kalibo | Buswang Old | 11.7068 | 122.3645 | U | 3796 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.44 | Terrestrial Optical Fiber Drop | 1.07 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2633 | 3 | 633 | 2633 | 1130700176 | Region XI (Davao Region) | Davao del Sur | City of Davao | Bago Aplaya | 7.0466 | 125.5373 | U | 19697 | 5793 | 1738 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSR0013 | PTCI/MIDC | 7.0507 | 125.541 | 0.62 | Terrestrial Optical Fiber Drop | 1.65 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2634 | 3 | 634 | 2634 | 0300803025 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang North | 14.6751 | 120.5386 | R | 2656 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030624 | FTAP Globe | 14.6886 | 120.5239 | 0.69 | Terrestrial Optical Fiber Drop | 1.08 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2635 | 3 | 635 | 2635 | 0402106038 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Roque | 14.3201 | 120.9569 | R | 3006 | 884 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0023 | PTCI/MIDC | 14.2938 | 120.9461 | 1.06 | Terrestrial Optical Fiber Drop | 1.27 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2636 | 3 | 636 | 2636 | 0601914004 | Region VI (Western Visayas) | Capiz | City of Roxas | Banica | 11.5822 | 122.7594 | U | 9285 | 2443 | 733 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.74 | Terrestrial Optical Fiber Drop | 1.42 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2637 | 3 | 637 | 2637 | 0631000179 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Tagbac | 10.7668 | 122.5795 | U | 5212 | 1240 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.41 | Terrestrial Optical Fiber Drop | 2.36 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2638 | 3 | 638 | 2638 | 1208007014 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Kinabalan | 6.4588 | 125.3111 | R | 2094 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH120294 | FTAP Globe | 6.4811 | 125.3261 | 2.98 | Terrestrial Optical Fiber Drop | 1.68 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2639 | 3 | 639 | 2639 | 0307103007 | Region III (Central Luzon) | Zambales | Candelaria | Malabon | 15.6385 | 119.9349 | R | 3329 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00621 | Edgepoint | 15.6398 | 119.9316 | 0.38 | Terrestrial Optical Fiber Drop | 1.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2640 | 3 | 640 | 2640 | 0402105044 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 49 | 14.4882 | 120.897 | R | 1477 | 434 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.3 | Terrestrial Optical Fiber Drop | 1.8 | 4.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2641 | 3 | 641 | 2641 | 0803707013 | Region VIII (Eastern Visayas) | Leyte | Bato | Dolho | 10.3349 | 124.7857 | R | 3536 | 930 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080139 | FTAP BTS | 10.3279 | 124.7938 | 1.18 | Terrestrial Optical Fiber Drop | 22.26 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2642 | 3 | 642 | 2642 | 1001304005 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Norte | 7.6906 | 124.9977 | U | 8257 | 2172 | 652 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 2.33 | Terrestrial Optical Fiber Drop | 1.48 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2643 | 3 | 643 | 2643 | 0401026025 | Region IV-A (CALABARZON) | Batangas | San Pascual | San Antonio | 13.7871 | 121.0186 | U | 10340 | 2872 | 862 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1335 | FTAP Smart | 13.7873 | 121.0133 | 0.57 | Terrestrial Optical Fiber Drop | 1.64 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2644 | 3 | 644 | 2644 | 0307104005 | Region III (Central Luzon) | Zambales | Castillejos | Magsaysay | 14.9419 | 120.1887 | U | 3852 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-02717 | Edgepoint | 14.9397 | 120.1927 | 0.49 | Terrestrial Optical Fiber Drop | 1.86 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2645 | 3 | 645 | 2645 | 0105512015 | Region I (Ilocos Region) | Pangasinan | Binalonan | Poblacion | 16.0529 | 120.5892 | U | 7412 | 2058 | 617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 0.3 | Terrestrial Optical Fiber Drop | 1.05 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2646 | 3 | 646 | 2646 | 0403426005 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Duhat | 14.2467 | 121.3793 | U | 8104 | 2455 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02018-C08 | PTCI/MIDC | 14.2525 | 121.3876 | 1.1 | Terrestrial Optical Fiber Drop | 1.81 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2647 | 3 | 647 | 2647 | 0103313030 | Region I (Ilocos Region) | La Union | Rosario | Tabtabungao | 16.2406 | 120.4545 | R | 3264 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02700-B05 | PTCI/MIDC | 16.2244 | 120.4789 | 1.31 | Terrestrial Optical Fiber Drop | 3.28 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2648 | 3 | 648 | 2648 | 0304916033 | Region III (Central Luzon) | Nueva Ecija | Lupao | San Roque | 15.8955 | 120.8913 | R | 2098 | 599 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01463-B07 | PTCI/MIDC | 15.8972 | 120.8923 | 0.22 | Terrestrial Optical Fiber Drop | 1.38 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2649 | 3 | 649 | 2649 | 0501603007 | Region V (Bicol Region) | Camarines Norte | Daet | Camambugan | 14.1072 | 122.9475 | U | 9118 | 2279 | 684 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0009 | PTCI/MIDC | 14.1084 | 122.9523 | 0.53 | Terrestrial Optical Fiber Drop | 1.06 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2650 | 3 | 650 | 2650 | 1004303007 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Lapinig | 9.006 | 124.8525 | R | 1463 | 375 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 0.24 | Terrestrial Optical Fiber Drop | 1.1 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2651 | 3 | 651 | 2651 | 0907344001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Begong | 7.8298 | 123.313 | R | 3769 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090134 | FTAP Globe | 7.8313 | 123.3137 | 0.18 | Terrestrial Optical Fiber Drop | 13.92 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2652 | 3 | 652 | 2652 | 0405641015 | Region IV-A (CALABARZON) | Quezon | San Antonio | Pulo | 13.8904 | 121.3151 | R | 2337 | 615 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02132-C08 | PTCI/MIDC | 13.9068 | 121.3032 | 0.91 | Terrestrial Optical Fiber Drop | 2.85 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2653 | 3 | 653 | 2653 | 0702211009 | Region VII (Central Visayas) | Cebu | City of Bogo | Dakit | 11.0294 | 124.0015 | U | 6548 | 1723 | 517 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0015 | PTCI/MIDC | 11.0328 | 124.0006 | 0.38 | Terrestrial Optical Fiber Drop | 2.07 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2654 | 3 | 654 | 2654 | 0603007025 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Tabucan | 10.9041 | 122.6912 | R | 3802 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0005 | PTCI/MIDC | 10.9016 | 122.6874 | 0.5 | Terrestrial Optical Fiber Drop | 1.69 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2655 | 3 | 655 | 2655 | 0203113009 | Region II (Cagayan Valley) | Isabela | Gamu | Guibang | 17.0561 | 121.8561 | R | 3122 | 821 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020067 | FTAP Globe | 17.0544 | 121.8573 | 0.23 | Terrestrial Optical Fiber Drop | 1.99 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2656 | 3 | 656 | 2656 | 0500516023 | Region V (Bicol Region) | Albay | Santo Domingo | Santa Misericordia | 13.2548 | 123.7587 | R | 3256 | 794 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03092-C10 | PTCI/MIDC | 13.2545 | 123.7582 | 0.06 | Terrestrial Optical Fiber Drop | 2.81 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2657 | 3 | 657 | 2657 | 0301403010 | Region III (Central Luzon) | Bulacan | Baliuag | Pagala | 14.9526 | 120.889 | U | 7563 | 2160 | 648 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0006 | PTCI/MIDC | 14.9582 | 120.8893 | 0.38 | Terrestrial Optical Fiber Drop | 0.52 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2658 | 3 | 658 | 2658 | 0401009010 | Region IV-A (CALABARZON) | Batangas | Cuenca | Ibabao | 13.9087 | 121.0723 | R | 3935 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4624 | FTAP Smart | 13.9068 | 121.0708 | 0.26 | Terrestrial Optical Fiber Drop | 2.73 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2659 | 3 | 659 | 2659 | 0301418034 | Region III (Central Luzon) | Bulacan | Pulilan | Tabon | 14.9106 | 120.827 | R | 5154 | 1472 | 442 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02490 | Edgepoint | 14.9094 | 120.8288 | 0.24 | Terrestrial Optical Fiber Drop | 2.7 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2660 | 3 | 660 | 2660 | 0403419014 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sabang | 14.2669 | 121.4578 | R | 4090 | 1239 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040208 | FTAP Globe | 14.2666 | 121.4429 | 0.14 | Terrestrial Optical Fiber Drop | 1.09 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2661 | 3 | 661 | 2661 | 0603037011 | Region VI (Western Visayas) | Iloilo | Pototan | Cato-ogan | 10.937 | 122.6473 | R | 2575 | 677 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.82 | Terrestrial Optical Fiber Drop | 1.2 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2662 | 3 | 662 | 2662 | 0304926006 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Calaocan | 15.786 | 120.9948 | U | 6480 | 1851 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030316 | FTAP Globe | 15.7882 | 120.9994 | 0.55 | Terrestrial Optical Fiber Drop | 1.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2663 | 3 | 663 | 2663 | 0730600015 | Region VII (Central Visayas) | Cebu | City of Cebu | Bulacao | 10.276 | 123.8497 | U | 28710 | 8971 | 2691 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0197 | PTCI/MIDC | 10.2761 | 123.8445 | 0.57 | Terrestrial Optical Fiber Drop | 1.54 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2664 | 3 | 664 | 2664 | 0730600046 | Region VII (Central Visayas) | Cebu | City of Cebu | Mabolo | 10.313 | 123.9153 | U | 21642 | 6763 | 2029 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.38 | Terrestrial Optical Fiber Drop | 2.24 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2665 | 3 | 665 | 2665 | 0306906001 | Region III (Central Luzon) | Tarlac | Gerona | Abagon | 15.6118 | 120.609 | U | 4879 | 1251 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00635 | Edgepoint | 15.6074 | 120.6046 | 0.68 | Terrestrial Optical Fiber Drop | 1.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2666 | 3 | 666 | 2666 | 0500508010 | Region V (Bicol Region) | Albay | City of Ligao | Batang | 13.2507 | 123.5641 | R | 3705 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050155 | FTAP Globe | 13.2473 | 123.5607 | 0.53 | Terrestrial Optical Fiber Drop | 2.28 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2667 | 3 | 667 | 2667 | 0403424004 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay I-B | 14.0691 | 121.3161 | U | 4387 | 1329 | 399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.74 | Terrestrial Optical Fiber Drop | 1.33 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2668 | 3 | 668 | 2668 | 0403405038 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 1 | 14.2049 | 121.1584 | U | 6383 | 1934 | 580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4230 | FTAP Smart | 14.2081 | 121.1581 | 0.36 | Terrestrial Optical Fiber Drop | 1.57 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2669 | 3 | 669 | 2669 | 0405648015 | Region IV-A (CALABARZON) | Quezon | Tiaong | Lalig | 13.9791 | 121.327 | U | 8479 | 2231 | 669 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0014 | PTCI/MIDC | 13.98 | 121.3268 | 0.1 | Terrestrial Optical Fiber Drop | 1.93 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2670 | 3 | 670 | 2670 | 0305416011 | Region III (Central Luzon) | Pampanga | City of San Fernando | Juliana | 15.0346 | 120.6906 | U | 4295 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00922 | Edgepoint | 15.0321 | 120.6895 | 0.31 | Terrestrial Optical Fiber Drop | 1.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2671 | 3 | 671 | 2671 | 1600209005 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Camagong | 8.9702 | 125.3363 | U | 5875 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0017 | PTCI/MIDC | 8.9849 | 125.3459 | 1.94 | Terrestrial Optical Fiber Drop | 1.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2672 | 3 | 672 | 2672 | 0203109003 | Region II (Cagayan Valley) | Isabela | Cordon | Capirpiriwan | 16.6674 | 121.4549 | R | 3762 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03316-B06 | PTCI/MIDC | 16.6644 | 121.4538 | 0.35 | Terrestrial Optical Fiber Drop | 8.22 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2673 | 3 | 673 | 2673 | 0501603015 | Region V (Bicol Region) | Camarines Norte | Daet | Lag-On | 14.1182 | 122.9421 | U | 6015 | 1503 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03030-C10 | PTCI/MIDC | 14.1218 | 122.9428 | 0.41 | Terrestrial Optical Fiber Drop | 1.31 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2674 | 3 | 674 | 2674 | 0203135020 | Region II (Cagayan Valley) | Isabela | City of Santiago | Malvar | 16.6826 | 121.5512 | U | 5125 | 1348 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00283 | Edgepoint | 16.687 | 121.5473 | 0.17 | Terrestrial Optical Fiber Drop | 2.75 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2675 | 3 | 675 | 2675 | 0401023008 | Region IV-A (CALABARZON) | Batangas | San Juan | Calitcalit | 13.8282 | 121.4107 | U | 4903 | 1361 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BTG-03175 | Edgepoint | 13.8273 | 121.397 | 1.49 | Terrestrial Optical Fiber Drop | 1.56 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2676 | 3 | 676 | 2676 | 0401014008 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Sebastian | 13.9351 | 121.1549 | U | 3755 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.59 | Terrestrial Optical Fiber Drop | 1.61 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2677 | 3 | 677 | 2677 | 0501724019 | Region V (Bicol Region) | Camarines Sur | City of Naga | Mabolo | 13.6146 | 123.1811 | U | 8106 | 1930 | 579 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 1 | Terrestrial Optical Fiber Drop | 1.15 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2678 | 3 | 678 | 2678 | 0907311010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Diplo | 7.7828 | 123.1168 | R | 3928 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0132 | PTCI/MIDC | 7.7816 | 123.117 | 0.14 | Terrestrial Optical Fiber Drop | 9 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2679 | 3 | 679 | 2679 | 0403424054 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Juan | 14.0928 | 121.3028 | R | 3679 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02083-C08 | PTCI/MIDC | 14.0881 | 121.3067 | 0.68 | Terrestrial Optical Fiber Drop | 1.97 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2680 | 3 | 680 | 2680 | 1030900008 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Hinaplanon | 8.2439 | 124.2572 | U | 15637 | 4115 | 1235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNR0010 | PTCI/MIDC | 8.2442 | 124.2545 | 0.3 | Terrestrial Optical Fiber Drop | 2.53 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2681 | 3 | 681 | 2681 | 0405804034 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tagpos | 14.5082 | 121.169 | U | 15316 | 4254 | 1276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02301-A04 | PTCI/MIDC | 14.5078 | 121.1693 | 0.06 | Terrestrial Optical Fiber Drop | 1.9 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2682 | 3 | 682 | 2682 | 0403411001 | Region IV-A (CALABARZON) | Laguna | Los Baños | Anos | 14.1798 | 121.2295 | U | 9663 | 2928 | 878 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02109-C08 | PTCI/MIDC | 14.18 | 121.2259 | 0.38 | Terrestrial Optical Fiber Drop | 1.39 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2683 | 3 | 683 | 2683 | 1108209014 | Region XI (Davao Region) | Davao de Oro | Nabunturan | Mipangi | 7.5421 | 125.9196 | R | 4290 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0030 | PTCI/MIDC | 7.5357 | 125.9157 | 0.82 | Terrestrial Optical Fiber Drop | 14.2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2684 | 3 | 684 | 2684 | 0600407013 | Region VI (Western Visayas) | Aklan | Kalibo | Poblacion | 11.7078 | 122.3679 | U | 12369 | 3171 | 951 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.3 | Terrestrial Optical Fiber Drop | 1.15 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2685 | 3 | 685 | 2685 | 0702251019 | Region VII (Central Visayas) | Cebu | City of Toledo | Ilihan | 10.3791 | 123.6576 | R | 4522 | 1190 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0171 | PTCI/MIDC | 10.3758 | 123.6582 | 0.38 | Terrestrial Optical Fiber Drop | 2.28 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2686 | 3 | 686 | 2686 | 0803708034 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Candadam | 10.6902 | 124.8033 | R | 3240 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080212 | FTAP BTS | 10.6869 | 124.8048 | 0.4 | Terrestrial Optical Fiber Drop | 1.21 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2687 | 3 | 687 | 2687 | 0501726006 | Region V (Bicol Region) | Camarines Sur | Pamplona | Del Rosario | 13.5762 | 123.0858 | R | 2668 | 635 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 1.98 | Terrestrial Optical Fiber Drop | 1.62 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2688 | 3 | 688 | 2688 | 0603045046 | Region VI (Western Visayas) | Iloilo | Tigbauan | Parara Sur | 10.6733 | 122.3665 | R | 2818 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060158 | FTAP BTS | 10.6758 | 122.3662 | 0.28 | Terrestrial Optical Fiber Drop | 1.74 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2689 | 3 | 689 | 2689 | 0405645002 | Region IV-A (CALABARZON) | Quezon | Sariaya | Balubal | 13.9678 | 121.5365 | U | 4735 | 1246 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Q55 | FTAP Smart | 13.9641 | 121.529 | 0.91 | Terrestrial Optical Fiber Drop | 2.19 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2690 | 3 | 690 | 2690 | 0203137001 | Region II (Cagayan Valley) | Isabela | Tumauini | Annafunan | 17.2743 | 121.8052 | R | 2094 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 0.83 | Terrestrial Optical Fiber Drop | 1.08 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2691 | 3 | 691 | 2691 | 0600407016 | Region VI (Western Visayas) | Aklan | Kalibo | Tinigaw | 11.7063 | 122.364 | U | 3370 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.52 | Terrestrial Optical Fiber Drop | 1.03 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2692 | 3 | 692 | 2692 | 0305407029 | Region III (Central Luzon) | Pampanga | Guagua | Santa Ines | 14.9804 | 120.649 | R | 4159 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01639-B07 | PTCI/MIDC | 14.9819 | 120.6451 | 0.45 | Terrestrial Optical Fiber Drop | 2.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2693 | 3 | 693 | 2693 | 0702205041 | Region VII (Central Visayas) | Cebu | Argao | Talo-ot | 9.9543 | 123.6171 | R | 4329 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0006 | PTCI/MIDC | 9.9557 | 123.6173 | 0.15 | Terrestrial Optical Fiber Drop | 6.52 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2694 | 3 | 694 | 2694 | 0331400020 | Region III (Central Luzon) | Zambales | City of Olongapo | West Tapinac | 14.8353 | 120.2816 | U | 7305 | 1974 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01123 | Edgepoint | 14.85 | 120.2999 | 0.25 | Terrestrial Optical Fiber Drop | 0.2 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2695 | 3 | 695 | 2695 | 0403422007 | Region IV-A (CALABARZON) | Laguna | Pila | Labuin | 14.246 | 121.3683 | U | 6312 | 1912 | 574 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040225 | FTAP Globe | 14.2383 | 121.3616 | 1.12 | Terrestrial Optical Fiber Drop | 1.03 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2696 | 3 | 696 | 2696 | 0103303007 | Region I (Ilocos Region) | La Union | Bacnotan | Baroro | 16.7102 | 120.3405 | U | 2936 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00274 | Edgepoint | 16.7069 | 120.34 | 0.37 | Terrestrial Optical Fiber Drop | 1.38 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2697 | 3 | 697 | 2697 | 0403424064 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Roque | 14.071 | 121.3123 | U | 3632 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01993-C08 | PTCI/MIDC | 14.0703 | 121.3069 | 0.59 | Terrestrial Optical Fiber Drop | 1.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2698 | 3 | 698 | 2698 | 0203114033 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Calamagui 1st | 17.1378 | 121.8686 | U | 4059 | 1068 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0014 | PTCI/MIDC | 17.1409 | 121.8693 | 0.36 | Terrestrial Optical Fiber Drop | 2.27 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2699 | 3 | 699 | 2699 | 0305407021 | Region III (Central Luzon) | Pampanga | Guagua | San Nicolas 2nd | 14.9748 | 120.6469 | U | 3475 | 868 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00964 | Edgepoint | 14.9817 | 120.6451 | 0.79 | Terrestrial Optical Fiber Drop | 1.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2700 | 3 | 700 | 2700 | 0401017005 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Norte | 14.0388 | 121.158 | R | 4522 | 1256 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.68 | Terrestrial Optical Fiber Drop | 2.09 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2701 | 3 | 701 | 2701 | 0501606024 | Region V (Bicol Region) | Camarines Norte | Labo | Exciban | 14.1843 | 122.6564 | R | 3671 | 917 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050013 | FTAP Globe | 14.1823 | 122.6602 | 0.47 | Terrestrial Optical Fiber Drop | 3.32 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2702 | 3 | 702 | 2702 | 0702243027 | Region VII (Central Visayas) | Cebu | San Remigio | Victoria | 10.9362 | 123.9109 | R | 2258 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0157 | PTCI/MIDC | 10.9044 | 123.895 | 3.94 | Terrestrial Optical Fiber Drop | 1.77 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2703 | 3 | 703 | 2703 | 0803722011 | Region VIII (Eastern Visayas) | Leyte | Isabel | Libertad | 10.9081 | 124.4521 | U | 5324 | 1401 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0024 | PTCI/MIDC | 10.8906 | 124.4556 | 1.98 | Terrestrial Optical Fiber Drop | 2.46 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2704 | 3 | 704 | 2704 | 0105538021 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Poblacion Norte | 16.0007 | 120.4021 | R | 4714 | 1309 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00469 | Edgepoint | 16.0013 | 120.4046 | 0.28 | Terrestrial Optical Fiber Drop | 2.18 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2705 | 3 | 705 | 2705 | 1401112011 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Poblacion | 16.5022 | 120.4757 | R | 2816 | 804 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BEN-00320 | Edgepoint | 16.5044 | 120.4848 | 1 | Terrestrial Optical Fiber Drop | 1.16 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2706 | 3 | 706 | 2706 | 0305413024 | Region III (Central Luzon) | Pampanga | Mexico | Parian | 15.0594 | 120.717 | U | 6107 | 1526 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1617 | FTAP Smart | 15.0585 | 120.7182 | 0.16 | Terrestrial Optical Fiber Drop | 2.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2707 | 3 | 707 | 2707 | 0405619039 | Region IV-A (CALABARZON) | Quezon | Gumaca | Rosario | 13.9301 | 122.0913 | U | 5782 | 1521 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0020 | PTCI/MIDC | 13.9258 | 122.0933 | 0.52 | Terrestrial Optical Fiber Drop | 1.95 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2708 | 3 | 708 | 2708 | 1102411005 | Region XI (Davao Region) | Davao del Sur | Padada | Lower Limonzo | 6.6446 | 125.3458 | R | 1769 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110530 | FTAP Globe | 6.6448 | 125.3465 | 0.08 | Terrestrial Optical Fiber Drop | 1.02 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2709 | 3 | 709 | 2709 | 0806407028 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Ibarra | 10.1283 | 124.8783 | R | 4395 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 1.92 | Terrestrial Optical Fiber Drop | 2.31 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2710 | 3 | 710 | 2710 | 0305413026 | Region III (Central Luzon) | Pampanga | Mexico | San Antonio | 15.0636 | 120.7241 | U | 6110 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030482 | FTAP Globe | 15.0664 | 120.7233 | 0.32 | Terrestrial Optical Fiber Drop | 1.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2711 | 3 | 711 | 2711 | 0501720012 | Region V (Bicol Region) | Camarines Sur | Magarao | San Pantaleon | 13.6623 | 123.1896 | R | 1235 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0004 | PTCI/MIDC | 13.6631 | 123.1918 | 0.23 | Terrestrial Optical Fiber Drop | 1.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2712 | 3 | 712 | 2712 | 0402111004 | Region IV-A (CALABARZON) | Cavite | Kawit | Marulas | 14.4436 | 120.9104 | R | 4054 | 1192 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01875-C08 | PTCI/MIDC | 14.4494 | 120.9205 | 0.72 | Terrestrial Optical Fiber Drop | 3.33 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2713 | 3 | 713 | 2713 | 0501725013 | Region V (Bicol Region) | Camarines Sur | Ocampo | Pinit | 13.5648 | 123.4116 | R | 4259 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050100 | FTAP Globe | 13.5784 | 123.4267 | 2.23 | Terrestrial Optical Fiber Drop | 3.95 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2714 | 3 | 714 | 2714 | 0402109051 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bucandala IV | 14.4048 | 120.9263 | U | 5634 | 1657 | 497 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.81 | Terrestrial Optical Fiber Drop | 1.57 | 4.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2715 | 3 | 715 | 2715 | 0300804033 | Region III (Central Luzon) | Bataan | Dinalupihan | San Benito | 14.848 | 120.4248 | R | 3085 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1508 | FTAP Smart | 14.8488 | 120.4252 | 0.09 | Terrestrial Optical Fiber Drop | 2.95 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2716 | 3 | 716 | 2716 | 0402111019 | Region IV-A (CALABARZON) | Cavite | Kawit | Samala-Marquez | 14.4437 | 120.91 | U | 6789 | 1996 | 599 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01920-C08 | PTCI/MIDC | 14.452 | 120.9266 | 0.38 | Terrestrial Optical Fiber Drop | 3.31 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2717 | 3 | 717 | 2717 | 0304904013 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Norte | 15.2763 | 120.8766 | R | 4166 | 1190 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00783 | Edgepoint | 15.2714 | 120.8765 | 0.55 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2718 | 3 | 718 | 2718 | 0304928026 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Gomez | 15.416 | 120.9374 | R | 2023 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01493-B07 | PTCI/MIDC | 15.4207 | 120.9403 | 0.6 | Terrestrial Optical Fiber Drop | 0.99 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2719 | 3 | 719 | 2719 | 0402111016 | Region IV-A (CALABARZON) | Cavite | Kawit | Congbalay-Legaspi | 14.4513 | 120.9226 | R | 4597 | 1352 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01875-C08 | PTCI/MIDC | 14.4494 | 120.9205 | 0.3 | Terrestrial Optical Fiber Drop | 2.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2720 | 3 | 720 | 2720 | 0305409012 | Region III (Central Luzon) | Pampanga | Mabalacat City | Mabiga | 15.2121 | 120.58 | U | 25509 | 6377 | 1913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01602-B07 | PTCI/MIDC | 15.2096 | 120.5783 | 0.33 | Terrestrial Optical Fiber Drop | 1.27 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2721 | 3 | 721 | 2721 | 0803708016 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Caridad | 10.6462 | 124.8215 | R | 4321 | 1137 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0012 | PTCI/MIDC | 10.8334 | 124.7546 | 0.22 | Terrestrial Optical Fiber Drop | 4.28 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2722 | 3 | 722 | 2722 | 0702218009 | Region VII (Central Visayas) | Cebu | Compostela | Estaca | 10.4375 | 124.0071 | U | 7394 | 1945 | 584 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0060 | PTCI/MIDC | 10.437 | 124.0045 | 0.29 | Terrestrial Optical Fiber Drop | 1.72 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2723 | 3 | 723 | 2723 | 0803739016 | Region VIII (Eastern Visayas) | Leyte | Palo | Guindapunan | 11.167 | 124.9983 | U | 7916 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 1.42 | Terrestrial Optical Fiber Drop | 1.91 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2724 | 3 | 724 | 2724 | 0301423022 | Region III (Central Luzon) | Bulacan | Santa Maria | Sta. Cruz | 14.8421 | 120.9563 | U | 11878 | 3393 | 1018 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01111-B07 | PTCI/MIDC | 14.8361 | 120.9745 | 0.03 | Terrestrial Optical Fiber Drop | 2.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2725 | 3 | 725 | 2725 | 1004313004 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Kabulawan | 8.8166 | 124.7911 | R | 3661 | 938 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 1.16 | Terrestrial Optical Fiber Drop | 1.28 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2726 | 3 | 726 | 2726 | 1030500053 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Lapasan | 8.4814 | 124.6638 | U | 39946 | 11096 | 3329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0028 | PTCI/MIDC | 8.4862 | 124.6626 | 0.55 | Terrestrial Optical Fiber Drop | 1.24 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2727 | 3 | 727 | 2727 | 1204704039 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Sudapin | 7.019 | 125.0935 | U | 9293 | 2445 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNCG0061 | PTCI/MIDC | 7.0176 | 125.0944 | 0.18 | Terrestrial Optical Fiber Drop | 1.25 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2728 | 3 | 728 | 2728 | 1705110003 | MIMAROPA Region | Occidental Mindoro | San Jose | Bagong Sikat | 12.3672 | 121.0631 | U | 8146 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6930 | FTAP Smart | 12.3704 | 121.0662 | 0.49 | Terrestrial Optical Fiber Drop | 1.83 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2729 | 3 | 729 | 2729 | 0304904006 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Maligaya | 15.2492 | 120.8599 | U | 3018 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.09 | Terrestrial Optical Fiber Drop | 1.67 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2730 | 3 | 730 | 2730 | 0103317013 | Region I (Ilocos Region) | La Union | Santo Tomas | Lomboy | 16.2747 | 120.3936 | R | 1542 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-LUN-00374 | Edgepoint | 16.2818 | 120.3824 | 0.59 | Terrestrial Optical Fiber Drop | 2 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2731 | 3 | 731 | 2731 | 0405630026 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Talipan | 13.9631 | 121.6546 | U | 6711 | 1766 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040413 | FTAP Globe | 13.9599 | 121.6568 | 0.42 | Terrestrial Optical Fiber Drop | 1.21 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2732 | 3 | 732 | 2732 | 0403421001 | Region IV-A (CALABARZON) | Laguna | Pangil | Balian | 14.3943 | 121.4749 | U | 7054 | 2137 | 641 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040124 | FTAP Globe | 14.4013 | 121.4743 | 0.79 | Terrestrial Optical Fiber Drop | 1.71 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2733 | 3 | 733 | 2733 | 0601910013 | Region VI (Western Visayas) | Capiz | Panitan | Cogon | 11.4594 | 122.8175 | R | 3953 | 1040 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060102 | FTAP BTS | 11.4732 | 122.8116 | 1.66 | Terrestrial Optical Fiber Drop | 2.72 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2734 | 3 | 734 | 2734 | 1030500047 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Dansolihon | 8.4682 | 124.6315 | U | 6319 | 1755 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100083 | FTAP BTS | 8.3287 | 124.5967 | 3.13 | Terrestrial Optical Fiber Drop | 1 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2735 | 3 | 735 | 2735 | 0501611001 | Region V (Bicol Region) | Camarines Norte | Talisay | Binanuaan | 14.1284 | 122.9365 | R | 2809 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03030-C10 | PTCI/MIDC | 14.1218 | 122.9428 | 1 | Terrestrial Optical Fiber Drop | 2.41 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2736 | 3 | 736 | 2736 | 0402106064 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc V | 14.28 | 120.9649 | R | 3423 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.54 | Terrestrial Optical Fiber Drop | 2.33 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2737 | 3 | 737 | 2737 | 0203126030 | Region II (Cagayan Valley) | Isabela | Roxas | Muñoz West | 17.1579 | 121.6114 | R | 3827 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00171 | Edgepoint | 17.1573 | 121.6124 | 0.13 | Terrestrial Optical Fiber Drop | 2.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2738 | 3 | 738 | 2738 | 0403403019 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Antonio | 14.3364 | 121.0882 | U | 39641 | 12012 | 3604 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02537-C08 | PTCI/MIDC | 14.3337 | 121.0825 | 0.68 | Terrestrial Optical Fiber Drop | 1.36 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2739 | 3 | 739 | 2739 | 0105533024 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tempra-Guilig | 16.1265 | 120.4087 | R | 3955 | 1098 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 0.32 | Terrestrial Optical Fiber Drop | 1.55 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2740 | 3 | 740 | 2740 | 0501724003 | Region V (Bicol Region) | Camarines Sur | City of Naga | Bagumbayan Sur | 13.6333 | 123.1858 | U | 7848 | 1868 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050078 | FTAP Globe | 13.631 | 123.1834 | 0.36 | Terrestrial Optical Fiber Drop | 1.52 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2741 | 3 | 741 | 2741 | 0331400005 | Region III (Central Luzon) | Zambales | City of Olongapo | East Bajac-bajac | 14.8367 | 120.29 | U | 19729 | 5332 | 1600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01146 | Edgepoint | 14.8379 | 120.2895 | 0.14 | Terrestrial Optical Fiber Drop | 1.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2742 | 3 | 742 | 2742 | 1400101006 | Cordillera Administrative Region (CAR) | Abra | Bangued | Calaba | 17.6133 | 120.6191 | U | 4784 | 1258 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00865-B05 | PTCI/MIDC | 17.6127 | 120.6165 | 0.28 | Terrestrial Optical Fiber Drop | 2.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2743 | 3 | 743 | 2743 | 0304908006 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Mangino | 15.3112 | 120.9623 | U | 14084 | 4024 | 1207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-02508 | Edgepoint | 15.3146 | 120.9576 | 0.64 | Terrestrial Optical Fiber Drop | 1.82 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2744 | 3 | 744 | 2744 | 0500506035 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 37 - Bitano | 13.1492 | 123.7448 | U | 7825 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03399-C10 | PTCI/MIDC | 13.1487 | 123.7436 | 0.14 | Terrestrial Optical Fiber Drop | 1.34 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2745 | 3 | 745 | 2745 | 1004301006 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Loguilo | 8.5759 | 124.4941 | R | 3582 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100121 | FTAP Globe | 8.5721 | 124.5078 | 1.56 | Terrestrial Optical Fiber Drop | 2.19 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2746 | 3 | 746 | 2746 | 1705320001 | MIMAROPA Region | Palawan | Taytay | Abongan | 10.679 | 119.4527 | R | 5497 | 1409 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170219 | FTAP Globe | 10.6697 | 119.4514 | 1.04 | Terrestrial Optical Fiber Drop | 2.87 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2747 | 3 | 747 | 2747 | 0306910004 | Region III (Central Luzon) | Tarlac | Paniqui | Apulid | 15.6832 | 120.5816 | R | 4025 | 1032 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00603 | Edgepoint | 15.6812 | 120.5835 | 0.3 | Terrestrial Optical Fiber Drop | 1.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2748 | 3 | 748 | 2748 | 0702227005 | Region VII (Central Visayas) | Cebu | Liloan | Jubay | 10.4188 | 123.9959 | U | 15241 | 4010 | 1203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0104 | PTCI/MIDC | 10.4246 | 123.9957 | 0.64 | Terrestrial Optical Fiber Drop | 0.33 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2749 | 3 | 749 | 2749 | 0305409021 | Region III (Central Luzon) | Pampanga | Mabalacat City | San Francisco | 15.2165 | 120.5788 | U | 15556 | 3889 | 1167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02973-B07 | PTCI/MIDC | 15.219 | 120.5769 | 0.35 | Terrestrial Optical Fiber Drop | 1.78 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2750 | 3 | 750 | 2750 | 0702246004 | Region VII (Central Visayas) | Cebu | Sibonga | Bahay | 9.9911 | 123.6121 | U | 5774 | 1519 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0244 | PTCI/MIDC | 9.9858 | 123.6163 | 0.74 | Terrestrial Optical Fiber Drop | 2.54 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2751 | 3 | 751 | 2751 | 1004307016 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Taytay | 8.5424 | 124.5408 | R | 4450 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0045 | PTCI/MIDC | 8.5357 | 124.5477 | 1.06 | Terrestrial Optical Fiber Drop | 2.46 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2752 | 3 | 752 | 2752 | 0731300008 | Region VII (Central Visayas) | Cebu | City of Mandaue | Casili | 10.3791 | 123.9353 | U | 5408 | 1545 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070327 | FTAP Globe | 10.3761 | 123.9347 | 0.34 | Terrestrial Optical Fiber Drop | 2.02 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2753 | 3 | 753 | 2753 | 1004309007 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Matangad | 8.5752 | 124.372 | R | 4152 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100118 | FTAP Globe | 8.5922 | 124.3873 | 2.53 | Terrestrial Optical Fiber Drop | 2.55 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2754 | 3 | 754 | 2754 | 0500503031 | Region V (Bicol Region) | Albay | Daraga | Malabog | 13.172 | 123.6851 | R | 4458 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050171 | FTAP Globe | 13.1731 | 123.6842 | 0.16 | Terrestrial Optical Fiber Drop | 1.97 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2755 | 3 | 755 | 2755 | 0702219003 | Region VII (Central Visayas) | Cebu | Consolacion | Casili | 10.3791 | 123.9353 | U | 19021 | 5005 | 1502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070327 | FTAP Globe | 10.3761 | 123.9347 | 0.34 | Terrestrial Optical Fiber Drop | 2.02 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2756 | 3 | 756 | 2756 | 0300810021 | Region III (Central Luzon) | Bataan | Orion | Sabatan | 14.6141 | 120.5686 | U | 3931 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03328-B07 | PTCI/MIDC | 14.6114 | 120.5701 | 0.34 | Terrestrial Optical Fiber Drop | 1.14 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2757 | 3 | 757 | 2757 | 0501731012 | Region V (Bicol Region) | Camarines Sur | Sagñay | Nato | 13.6096 | 123.5359 | R | 4071 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050089 | FTAP Globe | 13.6069 | 123.5336 | 0.39 | Terrestrial Optical Fiber Drop | 1.82 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2758 | 3 | 758 | 2758 | 0806407041 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Maria Clara | 10.1215 | 124.8929 | R | 2433 | 593 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 0.22 | Terrestrial Optical Fiber Drop | 1.32 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2759 | 3 | 759 | 2759 | 0702206011 | Region VII (Central Visayas) | Cebu | Asturias | Langub | 10.5811 | 123.7335 | R | 4073 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 5.85 | Terrestrial Optical Fiber Drop | 8.28 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2760 | 3 | 760 | 2760 | 0501736021 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Rafael | 13.6606 | 123.5017 | R | 4172 | 993 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 2.64 | Terrestrial Optical Fiber Drop | 3.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2761 | 3 | 761 | 2761 | 0405809003 | Region IV-A (CALABARZON) | Rizal | Morong | Lagundi | 14.5274 | 121.2544 | U | 9646 | 2679 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01851 | Edgepoint | 14.529 | 121.254 | 0.17 | Terrestrial Optical Fiber Drop | 1.37 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2762 | 3 | 762 | 2762 | 0730600027 | Region VII (Central Visayas) | Cebu | City of Cebu | Duljo | 10.2949 | 123.8857 | U | 15870 | 4959 | 1488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0026 | PTCI/MIDC | 10.2919 | 123.8848 | 0.34 | Terrestrial Optical Fiber Drop | 1.61 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2763 | 3 | 763 | 2763 | 0304903073 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | San Juan Pob. | 15.4718 | 120.9582 | U | 9561 | 2731 | 819 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00717 | Edgepoint | 15.4684 | 120.9565 | 0.41 | Terrestrial Optical Fiber Drop | 1.15 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2764 | 3 | 764 | 2764 | 0604504001 | Region VI (Western Visayas) | Negros Occidental | City of Cadiz | Andres Bonifacio | 10.9041 | 123.2305 | U | 6506 | 1758 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOR0024 | PTCI/MIDC | 10.6784 | 122.9604 | 0.86 | Terrestrial Optical Fiber Drop | 12.19 | 5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2765 | 3 | 765 | 2765 | 0506206019 | Region V (Bicol Region) | Sorsogon | Castilla | Milagrosa | 12.9792 | 123.8517 | R | 1785 | 446 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050205 | FTAP Globe | 12.9754 | 123.8474 | 0.63 | Terrestrial Optical Fiber Drop | 1.1 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2766 | 3 | 766 | 2766 | 0402118019 | Region IV-A (CALABARZON) | Cavite | Silang | Lalaan I | 14.1821 | 120.963 | U | 6436 | 1892 | 568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02158-C08 | PTCI/MIDC | 14.1794 | 120.9616 | 0.33 | Terrestrial Optical Fiber Drop | 2.28 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2767 | 3 | 767 | 2767 | 0702247010 | Region VII (Central Visayas) | Cebu | Sogod | Damolog | 10.7691 | 124.0037 | R | 3987 | 1049 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 1.88 | Terrestrial Optical Fiber Drop | 1.91 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2768 | 3 | 768 | 2768 | 0401006023 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Uno | 13.8027 | 120.9948 | U | 2821 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1334 | FTAP Smart | 13.7999 | 120.9945 | 0.32 | Terrestrial Optical Fiber Drop | 1.26 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2769 | 3 | 769 | 2769 | 0301421020 | Region III (Central Luzon) | Bulacan | San Miguel | Camias | 15.1636 | 120.9731 | U | 8942 | 2554 | 766 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030449 | FTAP Globe | 15.1671 | 120.9765 | 0.53 | Terrestrial Optical Fiber Drop | 1.05 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2770 | 3 | 770 | 2770 | 1705211003 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Dulangan | 13.4677 | 120.9748 | R | 3978 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMRG0009 | PTCI/MIDC | 13.4655 | 120.9692 | 0.65 | Terrestrial Optical Fiber Drop | 4.11 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2771 | 3 | 771 | 2771 | 0403405020 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lecheria | 14.2033 | 121.1614 | U | 11956 | 3623 | 1087 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02120-C08 | PTCI/MIDC | 14.2013 | 121.1654 | 0.48 | Terrestrial Optical Fiber Drop | 1.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2772 | 3 | 772 | 2772 | 0205005003 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Bonfal West | 16.4984 | 121.1664 | U | 5944 | 1564 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00321 | Edgepoint | 16.4983 | 121.1676 | 0.13 | Terrestrial Optical Fiber Drop | 2.39 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2773 | 3 | 773 | 2773 | 0401007033 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Puting Bato West | 13.9228 | 120.8339 | U | 3685 | 1023 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040482 | FTAP Globe | 13.9204 | 120.8358 | 0.35 | Terrestrial Optical Fiber Drop | 2.37 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2774 | 3 | 774 | 2774 | 0403425019 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | United Better Living | 14.3412 | 121.0438 | U | 6801 | 2060 | 618 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02621-C08 | PTCI/MIDC | 14.3435 | 121.0576 | 0.48 | Terrestrial Optical Fiber Drop | 0.52 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2775 | 3 | 775 | 2775 | 1606808002 | Region XIII (Caraga) | Surigao del Sur | Cortes | Burgos | 9.2547 | 126.1733 | R | 3668 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130061 | FTAP Globe | 9.1425 | 126.1699 | 12.48 | Terrestrial Optical Fiber Drop | 19.94 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2776 | 3 | 776 | 2776 | 0500506046 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 41 - Bogtong | 13.1611 | 123.7331 | U | 5099 | 1243 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050174 | FTAP Globe | 13.1521 | 123.7315 | 1.01 | Terrestrial Optical Fiber Drop | 2.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2777 | 3 | 777 | 2777 | 0701242012 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion III | 9.639 | 123.8642 | U | 5103 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0034 | PTCI/MIDC | 9.6382 | 123.8698 | 0.61 | Terrestrial Optical Fiber Drop | 1.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2778 | 3 | 778 | 2778 | 0702210001 | Region VII (Central Visayas) | Cebu | Barili | Azucena | 10.1271 | 123.5216 | R | 2266 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070062 | FTAP BTS | 10.116 | 123.5147 | 1.44 | Terrestrial Optical Fiber Drop | 1.98 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2779 | 3 | 779 | 2779 | 1003507010 | Region X (Northern Mindanao) | Lanao del Norte | Kauswagan | Poblacion | 8.1906 | 124.0869 | R | 4074 | 970 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0015 | PTCI/MIDC | 8.1921 | 124.0889 | 0.27 | Terrestrial Optical Fiber Drop | 17.41 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2780 | 3 | 780 | 2780 | 0401019048 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Wawa | 14.0812 | 120.6246 | U | 15886 | 4412 | 1324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1364 | FTAP Smart | 14.0832 | 120.6249 | 0.22 | Terrestrial Optical Fiber Drop | 1.54 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2781 | 3 | 781 | 2781 | 0402116011 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio II | 14.4186 | 120.8858 | R | 2182 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03036-C08 | PTCI/MIDC | 14.4147 | 120.8819 | 0.6 | Terrestrial Optical Fiber Drop | 1.25 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2782 | 3 | 782 | 2782 | 0105521004 | Region I (Ilocos Region) | Pangasinan | Labrador | Laois | 16.0364 | 120.1381 | R | 2855 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01750-B07 | PTCI/MIDC | 16.0291 | 120.1409 | 0.86 | Terrestrial Optical Fiber Drop | 2.33 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2783 | 3 | 783 | 2783 | 0803708025 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Hipusngo | 10.6583 | 124.8098 | R | 3141 | 826 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00117-D11 | PTCI/MIDC | 10.6643 | 124.807 | 0.74 | Terrestrial Optical Fiber Drop | 2.52 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2784 | 3 | 784 | 2784 | 0105526005 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bantayan | 16.09 | 120.3897 | R | 3840 | 1066 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02184 | Edgepoint | 16.0971 | 120.3938 | 0.9 | Terrestrial Optical Fiber Drop | 2.81 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2785 | 3 | 785 | 2785 | 0203114102 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Imelda Bliss Village | 17.1219 | 121.8754 | U | 8237 | 2167 | 650 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0016 | PTCI/MIDC | 17.1227 | 121.8677 | 0.83 | Terrestrial Optical Fiber Drop | 1.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2786 | 3 | 786 | 2786 | 0201502005 | Region II (Cagayan Valley) | Cagayan | Alcala | Baculod | 17.9091 | 121.6714 | R | 2380 | 610 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-00055 | Edgepoint | 17.9092 | 121.6539 | 1.85 | Terrestrial Optical Fiber Drop | 1.81 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2787 | 3 | 787 | 2787 | 0500506067 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 32 - San Roque | 13.153 | 123.7543 | U | 5759 | 1404 | 421 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03400-C10 | PTCI/MIDC | 13.1476 | 123.7504 | 0.73 | Terrestrial Optical Fiber Drop | 2.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2788 | 3 | 788 | 2788 | 1705211001 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Aninuan | 13.4973 | 120.8985 | U | 3238 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170044 | FTAP Globe | 13.5034 | 120.9011 | 0.74 | Terrestrial Optical Fiber Drop | 1.01 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2789 | 3 | 789 | 2789 | 0405813003 | Region IV-A (CALABARZON) | Rizal | Taytay | San Isidro | 14.5728 | 121.1314 | U | 39685 | 11023 | 3307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0145 | PTCI/MIDC | 14.5742 | 121.1329 | 0.23 | Terrestrial Optical Fiber Drop | 1.36 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2790 | 3 | 790 | 2790 | 0730600021 | Region VII (Central Visayas) | Cebu | City of Cebu | Carreta | 10.3075 | 123.9088 | U | 11412 | 3566 | 1070 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.7 | Terrestrial Optical Fiber Drop | 1.3 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2791 | 3 | 791 | 2791 | 1130700153 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 20-B | 7.0866 | 125.613 | U | 5129 | 1508 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0035 | PTCI/MIDC | 7.0835 | 125.6125 | 0.35 | Terrestrial Optical Fiber Drop | 1.01 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2792 | 3 | 792 | 2792 | 0501715016 | Region V (Bicol Region) | Camarines Sur | Goa | Matacla | 13.6879 | 123.4956 | U | 5571 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02602 | Edgepoint | 13.6957 | 123.4931 | 0.9 | Terrestrial Optical Fiber Drop | 1.14 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2793 | 3 | 793 | 2793 | 0401014009 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Balintawak | 13.954 | 121.161 | U | 19850 | 5513 | 1654 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040430 | FTAP Globe | 13.9477 | 121.1559 | 0.89 | Terrestrial Optical Fiber Drop | 1.24 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2794 | 3 | 794 | 2794 | 0403405001 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bagong Kalsada | 14.2008 | 121.1403 | U | 4266 | 1292 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.24 | Terrestrial Optical Fiber Drop | 0.75 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2795 | 3 | 795 | 2795 | 1600306023 | Region XIII (Caraga) | Agusan del Sur | Prosperidad | San Jose | 8.6931 | 125.8352 | R | 2875 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130084 | FTAP Globe | 8.661 | 125.8901 | 7.01 | Terrestrial Optical Fiber Drop | 1.67 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2796 | 3 | 796 | 2796 | 0103312003 | Region I (Ilocos Region) | La Union | Pugo | Cares | 16.3208 | 120.4686 | R | 2717 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01397-B05 | PTCI/MIDC | 16.3194 | 120.4687 | 0.15 | Terrestrial Optical Fiber Drop | 1.45 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2797 | 3 | 797 | 2797 | 1001314005 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Damilag | 8.3685 | 124.8627 | U | 18241 | 4800 | 1440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 0.89 | Terrestrial Optical Fiber Drop | 1.93 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2798 | 3 | 798 | 2798 | 0306905030 | Region III (Central Luzon) | Tarlac | Concepcion | San Francisco | 15.311 | 120.6424 | U | 9208 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02470 | Edgepoint | 15.3132 | 120.6411 | 0.28 | Terrestrial Optical Fiber Drop | 1.9 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2799 | 3 | 799 | 2799 | 1004308068 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Santiago | 8.8285 | 125.1299 | R | 3582 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0048 | PTCI/MIDC | 8.83 | 125.1208 | 1.01 | Terrestrial Optical Fiber Drop | 2.76 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2800 | 3 | 800 | 2800 | 0103314029 | Region I (Ilocos Region) | La Union | City of San Fernando | Langcuas | 16.6151 | 120.3357 | R | 2067 | 558 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010097 | FTAP Globe | 16.5923 | 120.3211 | 0.42 | Terrestrial Optical Fiber Drop | 2.3 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2801 | 3 | 801 | 2801 | 0306905001 | Region III (Central Luzon) | Tarlac | Concepcion | Alfonso | 15.3299 | 120.6389 | U | 9944 | 2549 | 765 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00761 | Edgepoint | 15.3331 | 120.625 | 1.53 | Terrestrial Optical Fiber Drop | 1.62 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2802 | 3 | 802 | 2802 | 0305407017 | Region III (Central Luzon) | Pampanga | Guagua | San Juan Nepomuceno | 14.9791 | 120.6415 | U | 7045 | 1761 | 528 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00964 | Edgepoint | 14.9817 | 120.6451 | 0.49 | Terrestrial Optical Fiber Drop | 1.45 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2803 | 3 | 803 | 2803 | 0702207016 | Region VII (Central Visayas) | Cebu | Badian | Malhiao | 9.8855 | 123.4039 | R | 3876 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 7.54 | Terrestrial Optical Fiber Drop | 6 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2804 | 3 | 804 | 2804 | 0403425011 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Poblacion | 14.3638 | 121.058 | U | 6326 | 1916 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4284 | FTAP Smart | 14.364 | 121.0585 | 0.06 | Terrestrial Optical Fiber Drop | 1.71 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2805 | 3 | 805 | 2805 | 0702222003 | Region VII (Central Visayas) | Cebu | Dalaguete | Balud | 9.7533 | 123.5217 | R | 3756 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 0.62 | Terrestrial Optical Fiber Drop | 1.48 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2806 | 3 | 806 | 2806 | 0506216008 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Bitan-o/Dalipay | 13.1458 | 123.7456 | U | 3374 | 843 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03399-C10 | PTCI/MIDC | 13.1487 | 123.7436 | 0.39 | Terrestrial Optical Fiber Drop | 1.06 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2807 | 3 | 807 | 2807 | 0300806006 | Region III (Central Luzon) | Bataan | Limay | Landing | 14.5514 | 120.5971 | R | 3333 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-02566 | Edgepoint | 14.5403 | 120.5882 | 0.67 | Terrestrial Optical Fiber Drop | 2.52 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2808 | 3 | 808 | 2808 | 0405811002 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 1 | 14.7002 | 121.1226 | U | 5006 | 1390 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00706-A04 | PTCI/MIDC | 14.6991 | 121.1241 | 0.2 | Terrestrial Optical Fiber Drop | 1.64 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2809 | 3 | 809 | 2809 | 0401021027 | Region IV-A (CALABARZON) | Batangas | Rosario | Natu | 13.8404 | 121.2692 | R | 2905 | 806 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040550 | FTAP Globe | 13.8351 | 121.2595 | 1.2 | Terrestrial Optical Fiber Drop | 2.82 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2810 | 3 | 810 | 2810 | 0501606008 | Region V (Bicol Region) | Camarines Norte | Labo | Bautista | 14.1445 | 122.8456 | R | 2936 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03390-C10 | PTCI/MIDC | 14.1462 | 122.844 | 0.25 | Terrestrial Optical Fiber Drop | 1.5 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2811 | 3 | 811 | 2811 | 0305416023 | Region III (Central Luzon) | Pampanga | City of San Fernando | Saguin | 15.0958 | 120.6221 | U | 8760 | 2190 | 657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4916 | FTAP Smart | 15.096 | 120.6241 | 0.21 | Terrestrial Optical Fiber Drop | 2.38 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2812 | 3 | 812 | 2812 | 0307113018 | Region III (Central Luzon) | Zambales | Santa Cruz | Pagatpat | 15.7816 | 119.9006 | R | 3733 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 0.24 | Terrestrial Optical Fiber Drop | 1.8 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2813 | 3 | 813 | 2813 | 0401022007 | Region IV-A (CALABARZON) | Batangas | San Jose | Banaybanay I | 13.8977 | 121.1069 | U | 6560 | 1822 | 547 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1351 | FTAP Smart | 13.8931 | 121.0981 | 1.08 | Terrestrial Optical Fiber Drop | 2.07 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2814 | 3 | 814 | 2814 | 1003505010 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Butadon | 7.885 | 123.7465 | R | 4433 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0040 | PTCI/MIDC | 7.8874 | 123.7416 | 0.6 | Terrestrial Optical Fiber Drop | 18.5 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2815 | 3 | 815 | 2815 | 0506216037 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Tugos | 12.9713 | 123.9885 | R | 3273 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 1.04 | Terrestrial Optical Fiber Drop | 1.62 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2816 | 3 | 816 | 2816 | 0304903023 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Kapitan Pepe | 15.4902 | 120.9705 | U | 5226 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030381 | FTAP Globe | 15.486 | 120.9751 | 0.28 | Terrestrial Optical Fiber Drop | 1.37 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2817 | 3 | 817 | 2817 | 0203108012 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Cabaruan | 16.9542 | 121.7694 | U | 8540 | 2247 | 674 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0013 | PTCI/MIDC | 16.9538 | 121.7732 | 0.41 | Terrestrial Optical Fiber Drop | 2.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2818 | 3 | 818 | 2818 | 0401007022 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Lumbang Calzada | 13.9271 | 120.8253 | R | 3336 | 926 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040472 | FTAP Globe | 13.9244 | 120.8212 | 0.54 | Terrestrial Optical Fiber Drop | 1.41 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2819 | 3 | 819 | 2819 | 0405808002 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Burgos | 14.7194 | 121.1393 | U | 49247 | 13679 | 4104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01291 | Edgepoint | 14.7179 | 121.1384 | 0.19 | Terrestrial Optical Fiber Drop | 1.19 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2820 | 3 | 820 | 2820 | 0731300013 | Region VII (Central Visayas) | Cebu | City of Mandaue | Ibabao-Estancia | 10.3353 | 123.9436 | U | 7001 | 2000 | 600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0114 | PTCI/MIDC | 10.3327 | 123.9448 | 0.31 | Terrestrial Optical Fiber Drop | 1.36 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2821 | 3 | 821 | 2821 | 0403405033 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Paciano Rizal | 14.2168 | 121.1368 | U | 17187 | 5208 | 1562 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040243 | FTAP Globe | 14.2133 | 121.134 | 0.49 | Terrestrial Optical Fiber Drop | 1.64 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2822 | 3 | 822 | 2822 | 0702250008 | Region VII (Central Visayas) | Cebu | City of Talisay | Linao | 10.2549 | 123.8172 | U | 14807 | 3896 | 1169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0159 | PTCI/MIDC | 10.2524 | 123.8198 | 0.39 | Terrestrial Optical Fiber Drop | 2.03 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2823 | 3 | 823 | 2823 | 0702223042 | Region VII (Central Visayas) | Cebu | Danao City | Taytay | 10.5322 | 124.0275 | R | 4744 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.98 | Terrestrial Optical Fiber Drop | 1.16 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2824 | 3 | 824 | 2824 | 0306902001 | Region III (Central Luzon) | Tarlac | Bamban | Anupul | 15.2937 | 120.5629 | U | 22732 | 5828 | 1748 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00776 | Edgepoint | 15.2875 | 120.5694 | 0.98 | Terrestrial Optical Fiber Drop | 1.24 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2825 | 3 | 825 | 2825 | 0300807004 | Region III (Central Luzon) | Bataan | Mariveles | Cabcaben | 14.4546 | 120.5889 | U | 8007 | 2224 | 667 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030634 | FTAP Globe | 14.448 | 120.5861 | 0.79 | Terrestrial Optical Fiber Drop | 1.82 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2826 | 3 | 826 | 2826 | 0305407013 | Region III (Central Luzon) | Pampanga | Guagua | San Antonio | 14.9648 | 120.6142 | U | 5184 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N50 | FTAP Smart | 14.9641 | 120.6111 | 0.34 | Terrestrial Optical Fiber Drop | 1.87 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2827 | 3 | 827 | 2827 | 0300801008 | Region III (Central Luzon) | Bataan | Abucay | Omboy | 14.7186 | 120.5386 | R | 3538 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-03190 | Edgepoint | 14.7182 | 120.5368 | 0.2 | Terrestrial Optical Fiber Drop | 3.76 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2828 | 3 | 828 | 2828 | 0203126021 | Region II (Cagayan Valley) | Isabela | Roxas | San Rafael | 17.1025 | 121.6136 | R | 3848 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0041 | PTCI/MIDC | 17.0989 | 121.6164 | 0.5 | Terrestrial Optical Fiber Drop | 1.5 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2829 | 3 | 829 | 2829 | 1004325014 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | San Jose | 8.9937 | 124.8888 | R | 3886 | 996 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0078 | PTCI/MIDC | 8.9948 | 124.8803 | 0.94 | Terrestrial Optical Fiber Drop | 1.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2830 | 3 | 830 | 2830 | 1705207020 | MIMAROPA Region | Oriental Mindoro | Mansalay | Santa Teresita | 12.518 | 121.422 | U | 5449 | 1397 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170126 | FTAP Globe | 12.5234 | 121.4387 | 1.91 | Terrestrial Optical Fiber Drop | 1.88 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2831 | 3 | 831 | 2831 | 0603044043 | Region VI (Western Visayas) | Iloilo | Sara | Zerrudo | 11.2442 | 123.0246 | R | 2169 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILO_0004 | LDIC | 11.2454 | 123.022 | 0.32 | Terrestrial Optical Fiber Drop | 1.5 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2832 | 3 | 832 | 2832 | 0305416032 | Region III (Central Luzon) | Pampanga | City of San Fernando | Santa Lucia | 15.0249 | 120.6925 | U | 10706 | 2676 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030497 | FTAP Globe | 15.0278 | 120.6925 | 0.32 | Terrestrial Optical Fiber Drop | 2.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2833 | 3 | 833 | 2833 | 1208007019 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Malandag | 6.2862 | 125.2574 | U | 15960 | 4092 | 1228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120311 | FTAP Globe | 6.2761 | 125.2567 | 1.13 | Terrestrial Optical Fiber Drop | 2.38 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2834 | 3 | 834 | 2834 | 0405608001 | Region IV-A (CALABARZON) | Quezon | Candelaria | Poblacion | 13.9315 | 121.4268 | U | 5761 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0002 | PTCI/MIDC | 13.9297 | 121.4287 | 0.28 | Terrestrial Optical Fiber Drop | 1.24 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2835 | 3 | 835 | 2835 | 0203113025 | Region II (Cagayan Valley) | Isabela | Gamu | Upi | 17.0693 | 121.8597 | U | 5347 | 1407 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020067 | FTAP Globe | 17.0544 | 121.8573 | 1.68 | Terrestrial Optical Fiber Drop | 1.05 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2836 | 3 | 836 | 2836 | 0403404014 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Sala | 14.2713 | 121.1262 | U | 11951 | 3621 | 1086 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02105-C08 | PTCI/MIDC | 14.2643 | 121.1272 | 0.79 | Terrestrial Optical Fiber Drop | 2.45 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2837 | 3 | 837 | 2837 | 0305407027 | Region III (Central Luzon) | Pampanga | Guagua | San Juan | 14.9724 | 120.6181 | R | 2905 | 726 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 0.53 | Terrestrial Optical Fiber Drop | 1.22 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2838 | 3 | 838 | 2838 | 0305408029 | Region III (Central Luzon) | Pampanga | Lubao | San Roque Arbol | 14.8965 | 120.5451 | R | 3613 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01558-B07 | PTCI/MIDC | 14.8999 | 120.5459 | 0.39 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2839 | 3 | 839 | 2839 | 0701242009 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Mansasa | 9.632 | 123.8708 | U | 6609 | 1652 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0055 | PTCI/MIDC | 9.6342 | 123.8691 | 0.32 | Terrestrial Optical Fiber Drop | 2.28 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2840 | 3 | 840 | 2840 | 0500504032 | Region V (Bicol Region) | Albay | Guinobatan | Morera | 13.1986 | 123.5937 | R | 2511 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03382-C10 | PTCI/MIDC | 13.1904 | 123.5935 | 0.92 | Terrestrial Optical Fiber Drop | 1.57 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2841 | 3 | 841 | 2841 | 0702231014 | Region VII (Central Visayas) | Cebu | Medellin | Poblacion | 11.1287 | 123.9607 | U | 6979 | 1836 | 551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 0.97 | Terrestrial Optical Fiber Drop | 1.12 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2842 | 3 | 842 | 2842 | 0205004007 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Banggot | 16.385 | 121.1103 | U | 4827 | 1270 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-02410 | Edgepoint | 16.3852 | 121.1076 | 0.28 | Terrestrial Optical Fiber Drop | 1.49 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2843 | 3 | 843 | 2843 | 1600201024 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Sacol | 8.9727 | 125.3937 | R | 3513 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 1.36 | Terrestrial Optical Fiber Drop | 2.53 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2844 | 3 | 844 | 2844 | 0301407024 | Region III (Central Luzon) | Bulacan | Calumpit | San Marcos | 14.8978 | 120.7787 | U | 2792 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02325 | Edgepoint | 14.8962 | 120.7791 | 0.18 | Terrestrial Optical Fiber Drop | 1.51 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2845 | 3 | 845 | 2845 | 0402106034 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel I | 14.32 | 120.9562 | R | 2971 | 873 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.45 | Terrestrial Optical Fiber Drop | 1.32 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2846 | 3 | 846 | 2846 | 0401028004 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Barangay IV | 14.1053 | 121.1426 | U | 3529 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03100-C08 | PTCI/MIDC | 13.8876 | 121.0401 | 0.85 | Terrestrial Optical Fiber Drop | 2.59 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2847 | 3 | 847 | 2847 | 0702205044 | Region VII (Central Visayas) | Cebu | Argao | Tulic | 9.8747 | 123.5957 | R | 3060 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 1.4 | Terrestrial Optical Fiber Drop | 1.04 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2848 | 3 | 848 | 2848 | 0803739022 | Region VIII (Eastern Visayas) | Leyte | Palo | Cavite West | 11.1583 | 124.9881 | R | 2036 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.89 | Terrestrial Optical Fiber Drop | 1.63 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2849 | 3 | 849 | 2849 | 0301419019 | Region III (Central Luzon) | Bulacan | San Ildefonso | Makapilapil | 15.0891 | 120.9416 | R | 2868 | 819 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00988-B07 | PTCI/MIDC | 15.089 | 120.9374 | 0.45 | Terrestrial Optical Fiber Drop | 1.69 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2850 | 3 | 850 | 2850 | 0403428006 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Don Jose | 14.2549 | 121.0644 | U | 19774 | 5992 | 1798 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Q34 | FTAP Smart | 14.2566 | 121.0577 | 0.75 | Terrestrial Optical Fiber Drop | 1.28 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2851 | 3 | 851 | 2851 | 0908305024 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Sanito | 7.7865 | 122.5957 | U | 9618 | 2290 | 687 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0005 | PTCI/MIDC | 7.7895 | 122.5928 | 0.47 | Terrestrial Optical Fiber Drop | 1.52 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2852 | 3 | 852 | 2852 | 0501724030 | Region V (Bicol Region) | Camarines Sur | City of Naga | Tabuco | 13.6175 | 123.1838 | U | 4230 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 0.61 | Terrestrial Optical Fiber Drop | 1.3 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2853 | 3 | 853 | 2853 | 0403405019 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lawa | 14.207 | 121.1453 | U | 13423 | 4067 | 1220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03427-A04 | PTCI/MIDC | 14.2116 | 121.1438 | 0.54 | Terrestrial Optical Fiber Drop | 1.08 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2854 | 3 | 854 | 2854 | 0306916073 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Roque | 15.4845 | 120.5896 | U | 6267 | 1606 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00703 | Edgepoint | 15.4867 | 120.5874 | 0.34 | Terrestrial Optical Fiber Drop | 2.43 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2855 | 3 | 855 | 2855 | 0803738016 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Cogon Combado | 11.0208 | 124.6052 | U | 6006 | 1580 | 474 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0045 | PTCI/MIDC | 11.0153 | 124.6014 | 0.74 | Terrestrial Optical Fiber Drop | 0.74 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2856 | 3 | 856 | 2856 | 0604526011 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Guinhalaran | 10.78 | 122.9695 | U | 16750 | 4527 | 1358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060337 | FTAP Globe | 10.7768 | 122.9645 | 0.65 | Terrestrial Optical Fiber Drop | 2.66 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2857 | 3 | 857 | 2857 | 0307109005 | Region III (Central Luzon) | Zambales | San Antonio | East Dirita | 14.969 | 120.0887 | R | 4039 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N52 | FTAP Smart | 14.97 | 120.086 | 0.32 | Terrestrial Optical Fiber Drop | 2.09 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2858 | 3 | 858 | 2858 | 0604528011 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Efigenio Lizares | 10.7454 | 122.998 | R | 4695 | 1268 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0070 | PTCI/MIDC | 10.7469 | 122.9872 | 1.19 | Terrestrial Optical Fiber Drop | 3.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2859 | 3 | 859 | 2859 | 0301420011 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Tungkong Mangga | 14.7875 | 121.0718 | U | 17063 | 4875 | 1463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01190 | Edgepoint | 14.788 | 121.0743 | 0.27 | Terrestrial Optical Fiber Drop | 1.16 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2860 | 3 | 860 | 2860 | 0600401010 | Region VI (Western Visayas) | Aklan | Altavas | Odiong | 11.5409 | 122.479 | R | 3364 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.91 | Terrestrial Optical Fiber Drop | 1.12 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2861 | 3 | 861 | 2861 | 0306916069 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Nicolas | 15.4927 | 120.5947 | U | 7100 | 1820 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00694 | Edgepoint | 15.4936 | 120.597 | 0.27 | Terrestrial Optical Fiber Drop | 2.26 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2862 | 3 | 862 | 2862 | 0500503053 | Region V (Bicol Region) | Albay | Daraga | Tagas | 13.1598 | 123.7235 | U | 7662 | 1868 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0035 | PTCI/MIDC | 13.1569 | 123.7229 | 0.33 | Terrestrial Optical Fiber Drop | 1.9 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2863 | 3 | 863 | 2863 | 0431200020 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Dupay | 13.9396 | 121.6255 | U | 28261 | 7065 | 2120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1422 | FTAP Smart | 13.9416 | 121.6241 | 0.26 | Terrestrial Optical Fiber Drop | 1.68 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2864 | 3 | 864 | 2864 | 1004324003 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Gracia | 8.5285 | 124.7531 | U | 3031 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0075 | PTCI/MIDC | 8.5289 | 124.7525 | 0.08 | Terrestrial Optical Fiber Drop | 1.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2865 | 3 | 865 | 2865 | 0401014066 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Sico | 13.9417 | 121.1297 | U | 5360 | 1488 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040436 | FTAP Globe | 13.9441 | 121.1298 | 0.27 | Terrestrial Optical Fiber Drop | 1.2 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2866 | 3 | 866 | 2866 | 0401003026 | Region IV-A (CALABARZON) | Batangas | Balayan | Duhatan | 13.9409 | 120.6606 | R | 1729 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040475 | FTAP Globe | 13.9229 | 120.6613 | 2 | Terrestrial Optical Fiber Drop | 1.21 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2867 | 3 | 867 | 2867 | 0304930001 | Region III (Central Luzon) | Nueva Ecija | Talavera | Andal Alino | 15.5938 | 120.9224 | R | 2294 | 655 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0016 | PTCI/MIDC | 15.5946 | 120.9217 | 0.12 | Terrestrial Optical Fiber Drop | 1.35 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2868 | 3 | 868 | 2868 | 0702251026 | Region VII (Central Visayas) | Cebu | City of Toledo | Media Once | 10.3289 | 123.6749 | U | 9508 | 2502 | 751 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0166 | PTCI/MIDC | 10.3293 | 123.6743 | 0.08 | Terrestrial Optical Fiber Drop | 2.71 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2869 | 3 | 869 | 2869 | 0601914037 | Region VI (Western Visayas) | Capiz | City of Roxas | Lonoy | 11.5078 | 122.7367 | R | 3195 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 0.15 | Terrestrial Optical Fiber Drop | 2.62 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2870 | 3 | 870 | 2870 | 0306916025 | Region III (Central Luzon) | Tarlac | City of Tarlac | Capehan | 15.433 | 120.6013 | R | 2335 | 598 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030399 | FTAP Globe | 15.4372 | 120.6017 | 0.46 | Terrestrial Optical Fiber Drop | 1.51 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2871 | 3 | 871 | 2871 | 0401009013 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Felipe | 13.8914 | 121.0399 | R | 4012 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03100-C08 | PTCI/MIDC | 13.8876 | 121.0401 | 0.42 | Terrestrial Optical Fiber Drop | 1.26 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2872 | 3 | 872 | 2872 | 0403405041 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 4 | 14.2073 | 121.1623 | R | 3618 | 1096 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.64 | Terrestrial Optical Fiber Drop | 2.07 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2873 | 3 | 873 | 2873 | 0701242010 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion I | 9.644 | 123.8585 | U | 2965 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0050 | PTCI/MIDC | 9.6529 | 123.8676 | 0.31 | Terrestrial Optical Fiber Drop | 1.76 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2874 | 3 | 874 | 2874 | 0500506025 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 28 - Victory Village North | 13.1444 | 123.7561 | R | 2467 | 601 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050178 | FTAP Globe | 13.14 | 123.7567 | 0.5 | Terrestrial Optical Fiber Drop | 1.94 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2875 | 3 | 875 | 2875 | 0405630020 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 2 Daungan | 13.9688 | 121.6837 | R | 2040 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.72 | Terrestrial Optical Fiber Drop | 0.38 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2876 | 3 | 876 | 2876 | 0304919012 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Singalat | 15.572 | 121.095 | U | 2799 | 799 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0007 | PTCI/MIDC | 15.5726 | 121.0971 | 0.23 | Terrestrial Optical Fiber Drop | 1.12 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2877 | 3 | 877 | 2877 | 0301411016 | Region III (Central Luzon) | Bulacan | Marilao | Tabing Ilog | 14.7649 | 120.9489 | U | 8421 | 2406 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01213 | Edgepoint | 14.7661 | 120.9455 | 0.39 | Terrestrial Optical Fiber Drop | 1.07 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2878 | 3 | 878 | 2878 | 0500517008 | Region V (Bicol Region) | Albay | City of Tabaco | Bogñabong | 13.3419 | 123.7159 | R | 3219 | 785 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.52 | Terrestrial Optical Fiber Drop | 2.06 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2879 | 3 | 879 | 2879 | 1102509009 | Region XI (Davao Region) | Davao Oriental | City of Mati | Dawan | 6.9075 | 126.167 | R | 4097 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDLG0011 | PTCI/MIDC | 6.9124 | 126.1725 | 0.82 | Terrestrial Optical Fiber Drop | 7.47 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2880 | 3 | 880 | 2880 | 0304930006 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bakal III | 15.7035 | 120.8989 | U | 7145 | 2041 | 612 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01484-B07 | PTCI/MIDC | 15.7038 | 120.9027 | 0.4 | Terrestrial Optical Fiber Drop | 1.42 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2881 | 3 | 881 | 2881 | 0304928021 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Zamora | 15.4342 | 120.9379 | R | 1423 | 406 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3532 | FTAP Smart | 15.4266 | 120.9483 | 1.5 | Terrestrial Optical Fiber Drop | 1.27 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2882 | 3 | 882 | 2882 | 0330100008 | Region III (Central Luzon) | Pampanga | City of Angeles | Cutud | 15.1756 | 120.6265 | U | 25921 | 7200 | 2160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01548-B07 | PTCI/MIDC | 15.1764 | 120.621 | 0.59 | Terrestrial Optical Fiber Drop | 1.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2883 | 3 | 883 | 2883 | 0304927004 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Castellano | 15.3195 | 120.9345 | U | 6047 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01449-B07 | PTCI/MIDC | 15.3191 | 120.9382 | 0.41 | Terrestrial Optical Fiber Drop | 1.64 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2884 | 3 | 884 | 2884 | 0203136019 | Region II (Cagayan Valley) | Isabela | Santo Tomas | Centro | 17.3974 | 121.7644 | R | 2888 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00138 | Edgepoint | 17.3993 | 121.7662 | 0.28 | Terrestrial Optical Fiber Drop | 1.39 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2885 | 3 | 885 | 2885 | 0402111002 | Region IV-A (CALABARZON) | Cavite | Kawit | Gahak | 14.4437 | 120.9103 | R | 3089 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01901-C08 | PTCI/MIDC | 14.4412 | 120.9121 | 0.34 | Terrestrial Optical Fiber Drop | 3.33 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2886 | 3 | 886 | 2886 | 0702250019 | Region VII (Central Visayas) | Cebu | City of Talisay | Biasong | 10.2481 | 123.8337 | U | 10653 | 2803 | 841 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0158 | PTCI/MIDC | 10.2398 | 123.8339 | 0.92 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2887 | 3 | 887 | 2887 | 0401003017 | Region IV-A (CALABARZON) | Batangas | Balayan | Caloocan | 13.9527 | 120.7239 | U | 6470 | 1797 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBGG0059 | PTCI/MIDC | 13.9557 | 120.7255 | 0.37 | Terrestrial Optical Fiber Drop | 1.12 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2888 | 3 | 888 | 2888 | 0702219006 | Region VII (Central Visayas) | Cebu | Consolacion | Jugan | 10.38 | 123.9725 | U | 13063 | 3437 | 1031 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070326 | FTAP Globe | 10.3811 | 123.9709 | 0.2 | Terrestrial Optical Fiber Drop | 1.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2889 | 3 | 889 | 2889 | 0604530017 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Tabao Proper | 10.4451 | 122.8263 | R | 4471 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 0.77 | Terrestrial Optical Fiber Drop | 2.35 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2890 | 3 | 890 | 2890 | 0201529019 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Caritan Norte | 17.6747 | 121.7561 | R | 3683 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02278 | Edgepoint | 17.6685 | 121.7522 | 0.81 | Terrestrial Optical Fiber Drop | 2.77 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2891 | 3 | 891 | 2891 | 0501724024 | Region V (Bicol Region) | Camarines Sur | City of Naga | Peñafrancia | 13.6315 | 123.1895 | U | 4492 | 1069 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050079 | FTAP Globe | 13.6298 | 123.1911 | 0.26 | Terrestrial Optical Fiber Drop | 1.08 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2892 | 3 | 892 | 2892 | 0300807008 | Region III (Central Luzon) | Bataan | Mariveles | Poblacion | 14.4361 | 120.4841 | U | 8835 | 2454 | 736 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0003 | PTCI/MIDC | 14.4309 | 120.4797 | 0.75 | Terrestrial Optical Fiber Drop | 1.56 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2893 | 3 | 893 | 2893 | 0301423010 | Region III (Central Luzon) | Bulacan | Santa Maria | Lalakhan | 14.8151 | 120.9461 | R | 2424 | 692 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01170 | Edgepoint | 14.8149 | 120.9461 | 0.02 | Terrestrial Optical Fiber Drop | 1.36 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2894 | 3 | 894 | 2894 | 0300810008 | Region III (Central Luzon) | Bataan | Orion | Bilolo | 14.6152 | 120.5617 | U | 8178 | 2271 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1518 | FTAP Smart | 14.6186 | 120.5623 | 0.39 | Terrestrial Optical Fiber Drop | 1.87 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2895 | 3 | 895 | 2895 | 0604502024 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Sampinit | 10.5448 | 122.863 | U | 10158 | 2745 | 824 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0089 | PTCI/MIDC | 10.5344 | 122.8445 | 1.37 | Terrestrial Optical Fiber Drop | 2.55 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2896 | 3 | 896 | 2896 | 0401022006 | Region IV-A (CALABARZON) | Batangas | San Jose | Balagtasin I | 13.9018 | 121.0884 | R | 1642 | 456 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1351 | FTAP Smart | 13.8931 | 121.0981 | 0.71 | Terrestrial Optical Fiber Drop | 3.09 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2897 | 3 | 897 | 2897 | 0403422017 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Sur | 14.234 | 121.3659 | U | 6468 | 1960 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 0.63 | Terrestrial Optical Fiber Drop | 0.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2898 | 3 | 898 | 2898 | 0402111013 | Region IV-A (CALABARZON) | Cavite | Kawit | Batong Dalig | 14.4349 | 120.8971 | U | 5412 | 1591 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040103 | FTAP Globe | 14.4337 | 120.9016 | 0.5 | Terrestrial Optical Fiber Drop | 1.63 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2899 | 3 | 899 | 2899 | 0401005009 | Region IV-A (CALABARZON) | Batangas | Batangas City | Banaba Ibaba | 13.7914 | 121.0583 | R | 3509 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040572 | FTAP Globe | 13.7858 | 121.0578 | 0.63 | Terrestrial Optical Fiber Drop | 2.96 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2900 | 3 | 900 | 2900 | 0201516011 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Catayauan | 18.1589 | 121.6538 | R | 4242 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0032 | LDIC | 121.6633 | 18.1613 | 1.54 | Terrestrial Optical Fiber Drop | 4.17 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2901 | 3 | 901 | 2901 | 0301404003 | Region III (Central Luzon) | Bulacan | Bocaue | Bambang | 14.7885 | 120.9286 | U | 9241 | 2640 | 792 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030608 | FTAP Globe | 14.7908 | 120.9227 | 0.68 | Terrestrial Optical Fiber Drop | 1.26 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2902 | 3 | 902 | 2902 | 1400101031 | Cordillera Administrative Region (CAR) | Abra | Bangued | Zone 1 Pob. | 17.6021 | 120.6162 | R | 2266 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02672-B05 | PTCI/MIDC | 17.6009 | 120.618 | 0.24 | Terrestrial Optical Fiber Drop | 1.09 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2903 | 3 | 903 | 2903 | 0305409018 | Region III (Central Luzon) | Pampanga | Mabalacat City | Mawaque | 15.2086 | 120.5911 | U | 3917 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01668-B07 | PTCI/MIDC | 15.2079 | 120.5954 | 0.47 | Terrestrial Optical Fiber Drop | 1.24 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2904 | 3 | 904 | 2904 | 1004313005 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Kauswagan | 8.7881 | 124.7843 | R | 3715 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100040 | FTAP BTS | 8.7788 | 124.7843 | 1.03 | Terrestrial Optical Fiber Drop | 2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2905 | 3 | 905 | 2905 | 0401014038 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Pinagtongulan | 13.9306 | 121.0995 | U | 3916 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03441-C08 | PTCI/MIDC | 13.9276 | 121.0981 | 0.36 | Terrestrial Optical Fiber Drop | 2.3 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2906 | 3 | 906 | 2906 | 0300807020 | Region III (Central Luzon) | Bataan | Mariveles | Townsite | 14.4579 | 120.5944 | U | 7524 | 2090 | 627 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | O00 | FTAP Smart | 14.466 | 120.5989 | 1.03 | Terrestrial Optical Fiber Drop | 2.44 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2907 | 3 | 907 | 2907 | 1705110039 | MIMAROPA Region | Occidental Mindoro | San Jose | San Roque | 12.3586 | 121.0566 | U | 16580 | 4251 | 1275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 4053 | FTAP Smart | 12.3689 | 121.0524 | 1.24 | Terrestrial Optical Fiber Drop | 1.23 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2908 | 3 | 908 | 2908 | 1108203018 | Region XI (Davao Region) | Davao de Oro | Mabini | San Antonio | 7.2922 | 125.8542 | R | 3124 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110444 | FTAP Globe | 7.2844 | 125.8539 | 0.86 | Terrestrial Optical Fiber Drop | 1.86 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2909 | 3 | 909 | 2909 | 0603037023 | Region VI (Western Visayas) | Iloilo | Pototan | Igang | 10.9114 | 122.6269 | R | 4005 | 1053 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 3.55 | Terrestrial Optical Fiber Drop | 4.17 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2910 | 3 | 910 | 2910 | 0306903066 | Region III (Central Luzon) | Tarlac | Camiling | Tambugan | 15.6982 | 120.4191 | R | 1656 | 424 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.89 | Terrestrial Optical Fiber Drop | 1.1 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2911 | 3 | 911 | 2911 | 1004307011 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Molugan | 8.5328 | 124.5622 | U | 13261 | 3400 | 1020 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100057 | FTAP BTS | 8.5349 | 124.5605 | 0.29 | Terrestrial Optical Fiber Drop | 1.97 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2912 | 3 | 912 | 2912 | 0604520003 | Region VI (Western Visayas) | Negros Occidental | Murcia | Amayco | 10.6205 | 123.0642 | R | 2439 | 659 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 0.45 | Terrestrial Optical Fiber Drop | 2.86 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2913 | 3 | 913 | 2913 | 0301412003 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bancal | 14.7207 | 120.9618 | U | 13261 | 3788 | 1136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02506-A01 | PTCI/MIDC | 14.7208 | 120.9665 | 0.51 | Terrestrial Optical Fiber Drop | 1.35 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2914 | 3 | 914 | 2914 | 0301410039 | Region III (Central Luzon) | Bulacan | City of Malolos | Pinagbakahan | 14.8753 | 120.8195 | U | 7905 | 2258 | 677 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030568 | FTAP Globe | 14.8757 | 120.818 | 0.17 | Terrestrial Optical Fiber Drop | 2.25 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2915 | 3 | 915 | 2915 | 0300810003 | Region III (Central Luzon) | Bataan | Orion | Balagtas | 14.6296 | 120.5777 | R | 2084 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 0.81 | Terrestrial Optical Fiber Drop | 1.58 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2916 | 3 | 916 | 2916 | 1108203014 | Region XI (Davao Region) | Davao de Oro | Mabini | Del Pilar | 7.2991 | 125.8591 | R | 2503 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110440 | FTAP Globe | 7.3117 | 125.8547 | 1.48 | Terrestrial Optical Fiber Drop | 1.16 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2917 | 3 | 917 | 2917 | 0600613010 | Region VI (Western Visayas) | Antique | San Jose | Barangay 8 | 10.7453 | 121.9493 | U | 5389 | 1381 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0018 | PTCI/MIDC | 10.7471 | 121.9496 | 0.2 | Terrestrial Optical Fiber Drop | 2.27 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2918 | 3 | 918 | 2918 | 0300802008 | Region III (Central Luzon) | Bataan | Bagac | Pag-asa | 14.6088 | 120.3868 | R | 3895 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F00901-B07 | PTCI/MIDC | 14.602 | 120.3962 | 1.25 | Terrestrial Optical Fiber Drop | 1.25 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2919 | 3 | 919 | 2919 | 0304908001 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Bayanihan | 15.2995 | 120.9449 | U | 5999 | 1714 | 514 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNEG0003 | PTCI/MIDC | 15.307 | 120.9519 | 1.13 | Terrestrial Optical Fiber Drop | 0.31 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2920 | 3 | 920 | 2920 | 1630400027 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Buhangin Pob. | 8.9627 | 125.5379 | U | 5174 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.95 | Terrestrial Optical Fiber Drop | 1.29 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2921 | 3 | 921 | 2921 | 0702250001 | Region VII (Central Visayas) | Cebu | City of Talisay | Bulacao | 10.2711 | 123.8424 | U | 12639 | 3326 | 998 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0197 | PTCI/MIDC | 10.2761 | 123.8445 | 0.6 | Terrestrial Optical Fiber Drop | 1.03 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2922 | 3 | 922 | 2922 | 1204702035 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Tacupan | 7.2163 | 124.7973 | R | 2464 | 648 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120262 | FTAP Globe | 7.2057 | 124.7944 | 1.22 | Terrestrial Optical Fiber Drop | 1.52 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2923 | 3 | 923 | 2923 | 0501716020 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Miguel | 13.4174 | 123.4061 | U | 3306 | 787 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02059 | Edgepoint | 123.406 | 13.4185 | 0.13 | Terrestrial Optical Fiber Drop | 1.13 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2924 | 3 | 924 | 2924 | 1206511004 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Carmen | 6.6721 | 124.6822 | U | 3684 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120127 | FTAP BTS | 6.6711 | 124.6851 | 0.33 | Terrestrial Optical Fiber Drop | 2.17 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2925 | 3 | 925 | 2925 | 0806408007 | Region VIII (Eastern Visayas) | Southern Leyte | Macrohon | Ichon | 10.1104 | 124.9005 | R | 3843 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 1.47 | Terrestrial Optical Fiber Drop | 0.25 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2926 | 3 | 926 | 2926 | 0702206026 | Region VII (Central Visayas) | Cebu | Asturias | Tubigagmanok | 10.6296 | 123.7467 | R | 4967 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0258 | PTCI/MIDC | 10.6781 | 123.8069 | 8.51 | Terrestrial Optical Fiber Drop | 13.86 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2927 | 3 | 927 | 2927 | 1705205057 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Sto. Niño | 13.4062 | 121.1855 | U | 3715 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 3.3 | Terrestrial Optical Fiber Drop | 2.18 | 3.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2928 | 3 | 928 | 2928 | 1130700031 | Region XI (Davao Region) | Davao del Sur | City of Davao | Catalunan Pequeño | 7.0764 | 125.5206 | U | 26806 | 7884 | 2365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110484 | FTAP Globe | 7.0774 | 125.5149 | 0.64 | Terrestrial Optical Fiber Drop | 2.03 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2929 | 3 | 929 | 2929 | 0506203023 | Region V (Bicol Region) | Sorsogon | Bulan | Fabrica | 12.6621 | 123.889 | R | 2771 | 692 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SOR_0003 | LDIC | 12.666 | 123.8894 | 0.44 | Terrestrial Optical Fiber Drop | 1.95 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2930 | 3 | 930 | 2930 | 0305411017 | Region III (Central Luzon) | Pampanga | Magalang | San Pedro II | 15.2109 | 120.6487 | U | 5721 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03221-B07 | PTCI/MIDC | 15.211 | 120.6581 | 1.02 | Terrestrial Optical Fiber Drop | 1.29 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2931 | 3 | 931 | 2931 | 0500503037 | Region V (Bicol Region) | Albay | Daraga | Mayon | 13.0588 | 123.7052 | R | 2054 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050193 | FTAP Globe | 13.0676 | 123.7045 | 0.97 | Terrestrial Optical Fiber Drop | 1.04 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2932 | 3 | 932 | 2932 | 0331400017 | Region III (Central Luzon) | Zambales | City of Olongapo | Pag-asa | 14.8497 | 120.2937 | U | 6709 | 1813 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0018 | PTCI/MIDC | 14.8485 | 120.2913 | 0.29 | Terrestrial Optical Fiber Drop | 2.25 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2933 | 3 | 933 | 2933 | 0307106012 | Region III (Central Luzon) | Zambales | Masinloc | Taltal | 15.5745 | 119.9476 | R | 5041 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030354 | FTAP Globe | 15.5762 | 119.9471 | 0.19 | Terrestrial Optical Fiber Drop | 4.3 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2934 | 3 | 934 | 2934 | 0702201006 | Region VII (Central Visayas) | Cebu | Alcantara | Palanas | 9.9849 | 123.4103 | R | 3312 | 871 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0132 | PTCI/MIDC | 9.9782 | 123.3783 | 3.58 | Terrestrial Optical Fiber Drop | 1.69 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2935 | 3 | 935 | 2935 | 0401009014 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Isidro | 13.905 | 121.0596 | R | 2641 | 733 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040500 | FTAP Globe | 13.9093 | 121.0582 | 0.51 | Terrestrial Optical Fiber Drop | 1.33 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2936 | 3 | 936 | 2936 | 0501726015 | Region V (Bicol Region) | Camarines Sur | Pamplona | San Vicente | 13.5954 | 123.0515 | R | 4250 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 3.45 | Terrestrial Optical Fiber Drop | 2.62 | 2.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2937 | 3 | 937 | 2937 | 0405804020 | Region IV-A (CALABARZON) | Rizal | Binangonan | Libis | 14.4653 | 121.1888 | U | 5653 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01896 | Edgepoint | 14.4645 | 121.1909 | 0.24 | Terrestrial Optical Fiber Drop | 1.69 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2938 | 3 | 938 | 2938 | 0305416015 | Region III (Central Luzon) | Pampanga | City of San Fernando | Maimpis | 15.0689 | 120.6527 | U | 13631 | 3407 | 1022 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00896 | Edgepoint | 15.0727 | 120.65 | 0.52 | Terrestrial Optical Fiber Drop | 1.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2939 | 3 | 939 | 2939 | 0301403002 | Region III (Central Luzon) | Bulacan | Baliuag | Barangca | 14.9876 | 120.8958 | R | 3538 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00964-B07 | PTCI/MIDC | 14.9952 | 120.8923 | 0.93 | Terrestrial Optical Fiber Drop | 2.42 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2940 | 3 | 940 | 2940 | 0731300012 | Region VII (Central Visayas) | Cebu | City of Mandaue | Guizo | 10.3289 | 123.9358 | U | 7265 | 2075 | 623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0113 | PTCI/MIDC | 10.3319 | 123.936 | 0.34 | Terrestrial Optical Fiber Drop | 1.56 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2941 | 3 | 941 | 2941 | 0305415028 | Region III (Central Luzon) | Pampanga | Porac | Pulung Santol | 15.0478 | 120.5576 | U | 7742 | 1935 | 581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.74 | Terrestrial Optical Fiber Drop | 2.42 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2942 | 3 | 942 | 2942 | 0306916052 | Region III (Central Luzon) | Tarlac | City of Tarlac | Matatalaib | 15.4966 | 120.6 | U | 26018 | 6671 | 2001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTTAG0013 | PTCI/MIDC | 15.5002 | 120.5985 | 0.43 | Terrestrial Optical Fiber Drop | 2.16 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2943 | 3 | 943 | 2943 | 0631000012 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Baldoza | 10.7049 | 122.5621 | U | 6365 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0088 | PTCI/MIDC | 10.7259 | 122.5515 | 0.3 | Terrestrial Optical Fiber Drop | 1.18 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2944 | 3 | 944 | 2944 | 1130700112 | Region XI (Davao Region) | Davao del Sur | City of Davao | Tagakpan | 7.1258 | 125.4325 | R | 5156 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0090 | PTCI/MIDC | 7.1261 | 125.4282 | 0.47 | Terrestrial Optical Fiber Drop | 7.14 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2945 | 3 | 945 | 2945 | 0305408012 | Region III (Central Luzon) | Pampanga | Lubao | Remedios | 14.9179 | 120.5797 | R | 4754 | 1188 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030546 | FTAP Globe | 14.9085 | 120.5852 | 1.2 | Terrestrial Optical Fiber Drop | 2.89 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2946 | 3 | 946 | 2946 | 0105524060 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Pasima | 15.9253 | 120.4012 | R | 2743 | 761 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00529 | Edgepoint | 15.9206 | 120.4066 | 0.77 | Terrestrial Optical Fiber Drop | 1.33 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2947 | 3 | 947 | 2947 | 0403406002 | Region IV-A (CALABARZON) | Laguna | Calauan | Bangyas | 14.174 | 121.3169 | R | 3213 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040277 | FTAP Globe | 14.1723 | 121.3161 | 0.2 | Terrestrial Optical Fiber Drop | 3.13 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2948 | 3 | 948 | 2948 | 1705318013 | MIMAROPA Region | Palawan | Roxas | New Barbacan | 10.3291 | 119.3496 | R | 5417 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 0.15 | Terrestrial Optical Fiber Drop | 1.38 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2949 | 3 | 949 | 2949 | 0301403022 | Region III (Central Luzon) | Bulacan | Baliuag | Subic | 14.9635 | 120.9033 | U | 6728 | 1922 | 577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.61 | Terrestrial Optical Fiber Drop | 1.39 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2950 | 3 | 950 | 2950 | 0504111023 | Region V (Bicol Region) | Masbate | City of Masbate | Mayngaran | 12.3496 | 123.5996 | U | 5015 | 1223 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMSG0006 | PTCI/MIDC | 12.3538 | 123.5951 | 0.68 | Terrestrial Optical Fiber Drop | 2.08 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2951 | 3 | 951 | 2951 | 0603007006 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Bungca | 10.9083 | 122.7161 | R | 2410 | 634 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 1.66 | Terrestrial Optical Fiber Drop | 1.6 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2952 | 3 | 952 | 2952 | 0702215001 | Region VII (Central Visayas) | Cebu | Carmen | Baring | 10.5875 | 124.0146 | U | 5732 | 1508 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 0.39 | Terrestrial Optical Fiber Drop | 1.29 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2953 | 3 | 953 | 2953 | 1230800007 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas East | 6.1159 | 125.1771 | U | 3507 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0013 | PTCI/MIDC | 6.1175 | 125.1764 | 0.19 | Terrestrial Optical Fiber Drop | 1.11 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2954 | 3 | 954 | 2954 | 1401105007 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Buyacaoan | 16.776 | 120.8121 | R | 3989 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBEG0006 | PTCI/MIDC | 16.7904 | 120.8171 | 1.69 | Terrestrial Optical Fiber Drop | 3.2 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2955 | 3 | 955 | 2955 | 0702215009 | Region VII (Central Visayas) | Cebu | Carmen | Cogon East | 10.5909 | 124.0212 | R | 3391 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 1.2 | Terrestrial Optical Fiber Drop | 1.58 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2956 | 3 | 956 | 2956 | 0701236013 | Region VII (Central Visayas) | Bohol | Sagbayan | Poblacion | 9.9155 | 124.0955 | R | 4055 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0030 | PTCI/MIDC | 9.9121 | 124.0943 | 0.4 | Terrestrial Optical Fiber Drop | 32.18 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2957 | 3 | 957 | 2957 | 0403424005 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-A | 14.0623 | 121.3201 | R | 3174 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02075-C08 | PTCI/MIDC | 14.0549 | 121.3128 | 1.13 | Terrestrial Optical Fiber Drop | 1.08 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2958 | 3 | 958 | 2958 | 0401021043 | Region IV-A (CALABARZON) | Batangas | Rosario | San Roque | 13.8562 | 121.2089 | U | 4740 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1032 | FTAP Smart | 13.8539 | 121.205 | 0.49 | Terrestrial Optical Fiber Drop | 1.53 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2959 | 3 | 959 | 2959 | 1705203017 | MIMAROPA Region | Oriental Mindoro | Bongabong | Malitbog | 12.7554 | 121.4686 | R | 3313 | 849 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170114 | FTAP Globe | 12.7482 | 121.4852 | 1.97 | Terrestrial Optical Fiber Drop | 2.4 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2960 | 3 | 960 | 2960 | 0330100007 | Region III (Central Luzon) | Pampanga | City of Angeles | Cutcut | 15.1392 | 120.5672 | U | 29551 | 8208 | 2462 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030459 | FTAP Globe | 15.1438 | 120.5664 | 0.52 | Terrestrial Optical Fiber Drop | 1.07 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2961 | 3 | 961 | 2961 | 0630200011 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 16 | 10.665 | 122.9412 | U | 7870 | 2186 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0090 | PTCI/MIDC | 10.6661 | 122.9446 | 0.27 | Terrestrial Optical Fiber Drop | 1.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2962 | 3 | 962 | 2962 | 1430300089 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Poliwes | 16.4077 | 120.5974 | R | 2871 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1846 | FTAP Smart | 16.461 | 120.6138 | 0.58 | Terrestrial Optical Fiber Drop | 0.61 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2963 | 3 | 963 | 2963 | 0603018034 | Region VI (Western Visayas) | Iloilo | Dumangas | Paloc Sool | 10.8333 | 122.7167 | R | 3595 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 0.97 | Terrestrial Optical Fiber Drop | 1.12 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2964 | 3 | 964 | 2964 | 0702205006 | Region VII (Central Visayas) | Cebu | Argao | Binlod | 9.9138 | 123.605 | R | 4159 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070017 | FTAP BTS | 9.8956 | 123.5985 | 2.14 | Terrestrial Optical Fiber Drop | 3.43 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2965 | 3 | 965 | 2965 | 0405805020 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Domingo | 14.5833 | 121.1112 | U | 45228 | 12563 | 3769 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01759 (EP_PH-RIZ-01759) | EdgePoint | 14.5824 | 121.1131 | 0.22 | Terrestrial Optical Fiber Drop | 1.32 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2966 | 3 | 966 | 2966 | 0307101017 | Region III (Central Luzon) | Zambales | Botolan | Porac | 15.252 | 120.0172 | R | 3753 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030429 | FTAP Globe | 15.2536 | 120.0187 | 0.24 | Terrestrial Optical Fiber Drop | 9.35 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2967 | 3 | 967 | 2967 | 1404402015 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Monamon Sur | 16.8814 | 120.8838 | R | 3671 | 992 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-MOU-00237 | Edgepoint | 16.8985 | 120.8953 | 2.27 | Terrestrial Optical Fiber Drop | 1.84 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2968 | 3 | 968 | 2968 | 0701242011 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion II | 9.6435 | 123.8588 | U | 4396 | 1099 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOR0035 | PTCI/MIDC | 9.6414 | 123.8556 | 0.41 | Terrestrial Optical Fiber Drop | 0.48 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2969 | 3 | 969 | 2969 | 0702234029 | Region VII (Central Visayas) | Cebu | City of Naga | West Poblacion | 10.21 | 123.7555 | R | 4169 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 0.73 | Terrestrial Optical Fiber Drop | 3.07 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2970 | 3 | 970 | 2970 | 0704621006 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | Obogon | 9.5094 | 123.1503 | R | 3918 | 1031 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070258 | FTAP Globe | 9.5141 | 123.156 | 0.81 | Terrestrial Optical Fiber Drop | 9.46 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2971 | 3 | 971 | 2971 | 0305406003 | Region III (Central Luzon) | Pampanga | Floridablanca | Basa Air Base | 14.9787 | 120.4997 | R | 2657 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00982 | Edgepoint | 14.973 | 120.5008 | 0.64 | Terrestrial Optical Fiber Drop | 1.55 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2972 | 3 | 972 | 2972 | 0702223014 | Region VII (Central Visayas) | Cebu | Danao City | Dunggoan | 10.5546 | 124.0191 | U | 7478 | 1967 | 590 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0083 | PTCI/MIDC | 10.5494 | 124.0218 | 0.64 | Terrestrial Optical Fiber Drop | 2.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2973 | 3 | 973 | 2973 | 0306916076 | Region III (Central Luzon) | Tarlac | City of Tarlac | Santa Cruz | 15.5372 | 120.5968 | R | 4449 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030362 | FTAP Globe | 15.5405 | 120.5949 | 0.42 | Terrestrial Optical Fiber Drop | 4.15 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2974 | 3 | 974 | 2974 | 0405811007 | Region IV-A (CALABARZON) | Rizal | San Mateo | Malanday | 14.7046 | 121.125 | U | 13906 | 3862 | 1159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIM0002 | PTCI/MIDC | 14.7047 | 121.1282 | 0.35 | Terrestrial Optical Fiber Drop | 2.1 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2975 | 3 | 975 | 2975 | 0730600031 | Region VII (Central Visayas) | Cebu | City of Cebu | Hippodromo | 10.3136 | 123.9072 | U | 9586 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.51 | Terrestrial Optical Fiber Drop | 1.69 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2976 | 3 | 976 | 2976 | 0305415026 | Region III (Central Luzon) | Pampanga | Porac | Poblacion | 15.0724 | 120.5389 | R | 1650 | 412 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.25 | Terrestrial Optical Fiber Drop | 1.01 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2977 | 3 | 977 | 2977 | 0405804025 | Region IV-A (CALABARZON) | Rizal | Binangonan | Mambog | 14.4809 | 121.2124 | U | 10886 | 3023 | 907 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00784-A04 | PTCI/MIDC | 14.4823 | 121.2135 | 0.19 | Terrestrial Optical Fiber Drop | 1.41 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2978 | 3 | 978 | 2978 | 0403424071 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Maria Magdalena | 14.0948 | 121.3073 | R | 3045 | 922 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02083-C08 | PTCI/MIDC | 14.0881 | 121.3067 | 0.75 | Terrestrial Optical Fiber Drop | 1.82 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2979 | 3 | 979 | 2979 | 0105543012 | Region I (Ilocos Region) | Pangasinan | Tayug | Magallanes | 16.0187 | 120.7389 | U | 3525 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00445 | Edgepoint | 16.0267 | 120.7436 | 1.03 | Terrestrial Optical Fiber Drop | 1.08 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2980 | 3 | 980 | 2980 | 1230800035 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas North | 6.1156 | 125.1669 | U | 7042 | 1805 | 542 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCR0011 | PTCI/MIDC | 6.1112 | 125.1712 | 0.68 | Terrestrial Optical Fiber Drop | 1.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2981 | 3 | 981 | 2981 | 0401002012 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Muzon Segundo | 13.8696 | 121.0215 | R | 2362 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03243-C08 | PTCI/MIDC | 13.8652 | 121.0025 | 0.53 | Terrestrial Optical Fiber Drop | 3.91 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2982 | 3 | 982 | 2982 | 0405813004 | Region IV-A (CALABARZON) | Rizal | Taytay | San Juan | 14.5443 | 121.1201 | U | 122533 | 34036 | 10211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00804-A04 | PTCI/MIDC | 14.5436 | 121.1186 | 0.18 | Terrestrial Optical Fiber Drop | 1.58 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2983 | 3 | 983 | 2983 | 0304928030 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Luna | 15.4341 | 120.938 | R | 2032 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 1.89 | Terrestrial Optical Fiber Drop | 1.27 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2984 | 3 | 984 | 2984 | 0501734020 | Region V (Bicol Region) | Camarines Sur | Sipocot | Impig | 13.7764 | 122.9772 | R | 3331 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 0.2 | Terrestrial Optical Fiber Drop | 1.6 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2985 | 3 | 985 | 2985 | 0300812008 | Region III (Central Luzon) | Bataan | Samal | San Juan | 14.7697 | 120.5395 | R | 4655 | 1293 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N95 | FTAP Smart | 14.7656 | 120.5422 | 0.54 | Terrestrial Optical Fiber Drop | 3.62 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2986 | 3 | 986 | 2986 | 0105511068 | Region I (Ilocos Region) | Pangasinan | Bayambang | Telbang | 15.7977 | 120.4535 | R | 2572 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00572 | Edgepoint | 15.8049 | 120.457 | 0.88 | Terrestrial Optical Fiber Drop | 2.07 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2987 | 3 | 987 | 2987 | 0301418020 | Region III (Central Luzon) | Bulacan | Pulilan | Penabatan | 14.904 | 120.8482 | R | 2485 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01048 | Edgepoint | 14.9046 | 120.8412 | 0.3 | Terrestrial Optical Fiber Drop | 0.32 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2988 | 3 | 988 | 2988 | 0702208009 | Region VII (Central Visayas) | Cebu | Balamban | Cambuhawe | 10.5 | 123.719 | R | 3845 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 0.74 | Terrestrial Optical Fiber Drop | 1.13 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2989 | 3 | 989 | 2989 | 0500503044 | Region V (Bicol Region) | Albay | Daraga | Sagpon | 13.1486 | 123.7261 | U | 5321 | 1297 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02799-C10 | PTCI/MIDC | 13.1485 | 123.7198 | 0.68 | Terrestrial Optical Fiber Drop | 1.56 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2990 | 3 | 990 | 2990 | 0304928001 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Cojuangco | 15.4891 | 120.971 | U | 2838 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0040 | PTCI/MIDC | 15.4927 | 120.972 | 0.41 | Terrestrial Optical Fiber Drop | 1.34 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2991 | 3 | 991 | 2991 | 1705318031 | MIMAROPA Region | Palawan | Roxas | Barangay IV | 10.3199 | 119.3333 | U | 7469 | 1915 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 2.03 | Terrestrial Optical Fiber Drop | 1.24 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2992 | 3 | 992 | 2992 | 0301407011 | Region III (Central Luzon) | Bulacan | Calumpit | Gatbuca | 14.9228 | 120.769 | U | 6673 | 1906 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01032 | Edgepoint | 14.9253 | 120.766 | 0.42 | Terrestrial Optical Fiber Drop | 1.84 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2993 | 3 | 993 | 2993 | 0501701017 | Region V (Bicol Region) | Camarines Sur | Baao | San Jose | 13.4877 | 123.3827 | R | 2419 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02841-C10 | PTCI/MIDC | 13.4681 | 123.3583 | 0.49 | Terrestrial Optical Fiber Drop | 4 | 3.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2994 | 3 | 994 | 2994 | 0304925001 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Alua | 15.3097 | 120.8941 | U | 5621 | 1606 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00767 | Edgepoint | 15.3064 | 120.8903 | 0.55 | Terrestrial Optical Fiber Drop | 1.32 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2995 | 3 | 995 | 2995 | 0301408003 | Region III (Central Luzon) | Bulacan | Guiguinto | Ilang-Ilang | 14.8391 | 120.866 | U | 6006 | 1716 | 515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01144 | Edgepoint | 14.8392 | 120.8702 | 0.45 | Terrestrial Optical Fiber Drop | 1.35 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2996 | 3 | 996 | 2996 | 0205004026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Magsaysay Hills | 16.3792 | 121.1114 | R | 2200 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-02410 | Edgepoint | 16.3852 | 121.1076 | 0.78 | Terrestrial Optical Fiber Drop | 1.08 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2997 | 3 | 997 | 2997 | 0305408009 | Region III (Central Luzon) | Pampanga | Lubao | Don Ignacio Dimson | 14.9247 | 120.5687 | U | 6051 | 1512 | 454 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03224-B07 | PTCI/MIDC | 14.9164 | 120.5576 | 0.88 | Terrestrial Optical Fiber Drop | 2.21 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2998 | 3 | 998 | 2998 | 0601902017 | Region VI (Western Visayas) | Capiz | Dao | Nasunogan | 11.3717 | 122.6753 | R | 2942 | 774 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060243 | FTAP Globe | 11.3433 | 122.6758 | 3.15 | Terrestrial Optical Fiber Drop | 2.83 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2999 | 3 | 999 | 2999 | 0301422027 | Region III (Central Luzon) | Bulacan | San Rafael | Sampaloc | 14.9801 | 120.9297 | U | 4683 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030512 | FTAP Globe | 14.9818 | 120.9272 | 0.33 | Terrestrial Optical Fiber Drop | 2.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3000 | 3 | 1000 | 3000 | 0305416005 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dela Paz Norte | 15.0866 | 120.6284 | U | 6120 | 1530 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030476 | FTAP Globe | 15.0875 | 120.6226 | 0.64 | Terrestrial Optical Fiber Drop | 1.88 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3001 | 4 | 1 | 3001 | 0306910028 | Region III (Central Luzon) | Tarlac | Paniqui | Samput | 15.6498 | 120.5829 | U | 6522 | 1672 | 502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00618 | Edgepoint | 15.6463 | 120.5901 | 0.86 | Terrestrial Optical Fiber Drop | 2.08 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3002 | 4 | 2 | 3002 | 0501731023 | Region V (Bicol Region) | Camarines Sur | Sagñay | Turague | 13.5896 | 123.5231 | R | 3620 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050090 | FTAP Globe | 13.6036 | 123.5204 | 1.58 | Terrestrial Optical Fiber Drop | 1.4 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3003 | 4 | 3 | 3003 | 0401022020 | Region IV-A (CALABARZON) | Batangas | San Jose | Natunuan | 13.8837 | 121.098 | R | 1927 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040530 | FTAP Globe | 13.8725 | 121.1036 | 0.57 | Terrestrial Optical Fiber Drop | 0.9 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3004 | 4 | 4 | 3004 | 0401010012 | Region IV-A (CALABARZON) | Batangas | Ibaan | Matala | 13.8292 | 121.1356 | R | 3107 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 1.42 | Terrestrial Optical Fiber Drop | 1.67 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3005 | 4 | 5 | 3005 | 0500503035 | Region V (Bicol Region) | Albay | Daraga | Maroroy | 13.1504 | 123.724 | U | 5443 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02799-C10 | PTCI/MIDC | 13.1485 | 123.7198 | 0.49 | Terrestrial Optical Fiber Drop | 1.38 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3006 | 4 | 6 | 3006 | 0305409027 | Region III (Central Luzon) | Pampanga | Mabalacat City | Sapang Biabas | 15.2058 | 120.607 | U | 30871 | 7717 | 2315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01606-B07 | PTCI/MIDC | 15.2031 | 120.6095 | 0.39 | Terrestrial Optical Fiber Drop | 1.87 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3007 | 4 | 7 | 3007 | 0506203057 | Region V (Bicol Region) | Sorsogon | Bulan | San Vicente | 12.6627 | 123.8813 | U | 5414 | 1353 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.52 | Terrestrial Optical Fiber Drop | 1.21 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3008 | 4 | 8 | 3008 | 0105506004 | Region I (Ilocos Region) | Pangasinan | Asingan | Bantog | 16.0099 | 120.6913 | R | 4368 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01733-B07 | PTCI/MIDC | 16.0117 | 120.6906 | 0.22 | Terrestrial Optical Fiber Drop | 2.35 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3009 | 4 | 9 | 3009 | 1705205017 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Canubing I | 13.3579 | 121.1355 | R | 3998 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170064 | FTAP Globe | 13.3808 | 121.1359 | 2.54 | Terrestrial Optical Fiber Drop | 3.33 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3010 | 4 | 10 | 3010 | 0306909008 | Region III (Central Luzon) | Tarlac | Moncada | Burgos | 15.7357 | 120.5771 | R | 2354 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3011 | 4 | 11 | 3011 | 0304902014 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Magtanggol | 15.6344 | 121.1479 | R | 1566 | 447 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02493 | Edgepoint | 15.6344 | 121.1471 | 0.09 | Terrestrial Optical Fiber Drop | 1.16 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3012 | 4 | 12 | 3012 | 0300804024 | Region III (Central Luzon) | Bataan | Dinalupihan | Pag-asa | 14.8506 | 120.4195 | R | 2576 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0006 | PTCI/MIDC | 14.8469 | 120.4161 | 0.55 | Terrestrial Optical Fiber Drop | 2.4 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3013 | 4 | 13 | 3013 | 0803738109 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Bagong Buhay | 11.0299 | 124.5935 | U | 6059 | 1594 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0101 | PTCI/MIDC | 11.0267 | 124.5934 | 0.35 | Terrestrial Optical Fiber Drop | 0.9 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3014 | 4 | 14 | 3014 | 0405811012 | Region IV-A (CALABARZON) | Rizal | San Mateo | Banaba | 14.6726 | 121.1128 | U | 26718 | 7421 | 2226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00282-A01 | PTCI/MIDC | 14.6721 | 121.1122 | 0.09 | Terrestrial Optical Fiber Drop | 1.62 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3015 | 4 | 15 | 3015 | 0405809008 | Region IV-A (CALABARZON) | Rizal | Morong | San Pedro | 14.5105 | 121.2415 | U | 5797 | 1610 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040071 | FTAP Globe | 14.5114 | 121.2446 | 0.34 | Terrestrial Optical Fiber Drop | 1.24 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3016 | 4 | 16 | 3016 | 0300803004 | Region III (Central Luzon) | Bataan | City of Balanga | Munting Batangas | 14.6829 | 120.5146 | R | 3468 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-01391 | Edgepoint | 14.682 | 120.5099 | 0.52 | Terrestrial Optical Fiber Drop | 2.71 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3017 | 4 | 17 | 3017 | 1606711010 | Region XIII (Caraga) | Surigao del Norte | Gigaquit | San Isidro | 9.5785 | 125.6901 | R | 4262 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130016 | FTAP BTS | 9.5619 | 125.7137 | 2.88 | Terrestrial Optical Fiber Drop | 18.58 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3018 | 4 | 18 | 3018 | 0304904010 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Palasinan | 15.2536 | 120.8563 | R | 3900 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.67 | Terrestrial Optical Fiber Drop | 1.51 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3019 | 4 | 19 | 3019 | 1130700072 | Region XI (Davao Region) | Davao del Sur | City of Davao | Marapangi | 7.0152 | 125.4871 | U | 8284 | 2436 | 731 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110211 | FTAP BTS | 7.0191 | 125.4856 | 0.46 | Terrestrial Optical Fiber Drop | 1.47 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3020 | 4 | 20 | 3020 | 0603018014 | Region VI (Western Visayas) | Iloilo | Dumangas | Cansilayan | 10.8333 | 122.717 | R | 1500 | 394 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 0.97 | Terrestrial Optical Fiber Drop | 1.14 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3021 | 4 | 21 | 3021 | 0402118048 | Region IV-A (CALABARZON) | Cavite | Silang | Ulat | 14.1468 | 120.9886 | R | 3383 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02238-C08 | PTCI/MIDC | 14.1436 | 120.9888 | 0.36 | Terrestrial Optical Fiber Drop | 2.44 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3022 | 4 | 22 | 3022 | 1606814008 | Region XIII (Caraga) | Surigao del Sur | Marihatag | Poblacion | 8.7951 | 126.2949 | R | 4223 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130012 | FTAP BTS | 8.7748 | 126.249 | 4.88 | Terrestrial Optical Fiber Drop | 33.12 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3023 | 4 | 23 | 3023 | 0604505004 | Region VI (Western Visayas) | Negros Occidental | Calatrava | Bantayanon | 10.5846 | 123.4761 | R | 4975 | 1344 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NEC_0009 | LDIC | 10.5884 | 123.4776 | 0.43 | Terrestrial Optical Fiber Drop | 8.32 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3024 | 4 | 24 | 3024 | 1430300088 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Pinsao Proper | 16.4277 | 120.5819 | U | 8408 | 2212 | 664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1849 | FTAP Smart | 16.3797 | 120.5438 | 0.51 | Terrestrial Optical Fiber Drop | 1.28 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3025 | 4 | 25 | 3025 | 0305411012 | Region III (Central Luzon) | Pampanga | Magalang | San Miguel | 15.2253 | 120.658 | R | 2960 | 740 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00799 | Edgepoint | 15.2184 | 120.6592 | 0.78 | Terrestrial Optical Fiber Drop | 2.32 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3026 | 4 | 26 | 3026 | 0304930032 | Region III (Central Luzon) | Nueva Ecija | Talavera | La Torre | 15.5648 | 120.9191 | U | 5315 | 1518 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1217 | FTAP Smart | 15.5622 | 120.9206 | 0.32 | Terrestrial Optical Fiber Drop | 1.92 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3027 | 4 | 27 | 3027 | 0702208022 | Region VII (Central Visayas) | Cebu | Balamban | Pondol | 10.4906 | 123.7166 | U | 10482 | 2758 | 827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 0.77 | Terrestrial Optical Fiber Drop | 2.07 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3028 | 4 | 28 | 3028 | 0402105072 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 42-C | 14.483 | 120.8971 | R | 1888 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMR0008 | PTCI/MIDC | 14.4542 | 120.9788 | 0.3 | Terrestrial Optical Fiber Drop | 1.37 | 4.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3029 | 4 | 29 | 3029 | 0730600068 | Region VII (Central Visayas) | Cebu | City of Cebu | San Nicolas Central | 10.294 | 123.8903 | U | 5333 | 1666 | 500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0028 | PTCI/MIDC | 10.2941 | 123.891 | 0.09 | Terrestrial Optical Fiber Drop | 1.22 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3030 | 4 | 30 | 3030 | 0201523003 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Centro | 18.455 | 122.1441 | U | 6489 | 1663 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01126-B06 | PTCI/MIDC | 18.4557 | 122.1429 | 0.15 | Terrestrial Optical Fiber Drop | 2.27 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3031 | 4 | 31 | 3031 | 0402109055 | Region IV-A (CALABARZON) | Cavite | City of Imus | Magdalo | 14.407 | 120.936 | R | 4715 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0001 | LDIC | 14.4497 | 120.9334 | 0.46 | Terrestrial Optical Fiber Drop | 0.5 | 4.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3032 | 4 | 32 | 3032 | 0603005011 | Region VI (Western Visayas) | Iloilo | Balasan | Lawis | 11.4669 | 123.1128 | R | 2417 | 636 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.48 | Terrestrial Optical Fiber Drop | 1.78 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3033 | 4 | 33 | 3033 | 1004302018 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Mandangoa | 8.7664 | 124.779 | U | 4498 | 1153 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100040 | FTAP BTS | 8.7788 | 124.7843 | 1.5 | Terrestrial Optical Fiber Drop | 1.82 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3034 | 4 | 34 | 3034 | 0305402005 | Region III (Central Luzon) | Pampanga | Apalit | Capalangan | 14.9299 | 120.7674 | U | 7845 | 1961 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02350-B07 | PTCI/MIDC | 14.9296 | 120.7683 | 0.1 | Terrestrial Optical Fiber Drop | 2.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3035 | 4 | 35 | 3035 | 0431200014 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Bocohan | 13.9579 | 121.5936 | U | 6394 | 1598 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040410 | FTAP Globe | 13.9627 | 121.5855 | 1.03 | Terrestrial Optical Fiber Drop | 1.67 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3036 | 4 | 36 | 3036 | 0631000073 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Jalandoni Estate-Lapuz | 10.7026 | 122.575 | R | 1903 | 453 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0087 | PTCI/MIDC | 10.7076 | 122.5713 | 0.69 | Terrestrial Optical Fiber Drop | 1.46 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3037 | 4 | 37 | 3037 | 0304928033 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | San Josep | 15.4341 | 120.9181 | U | 2937 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0006 | PTCI/MIDC | 15.4304 | 120.9236 | 0.71 | Terrestrial Optical Fiber Drop | 0.5 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3038 | 4 | 38 | 3038 | 0103314022 | Region I (Ilocos Region) | La Union | City of San Fernando | Catbangen | 16.6126 | 120.3124 | U | 9670 | 2613 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010094 | FTAP Globe | 16.6084 | 120.309 | 0.59 | Terrestrial Optical Fiber Drop | 1.15 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3039 | 4 | 39 | 3039 | 0405619059 | Region IV-A (CALABARZON) | Quezon | Gumaca | Villa Nava | 13.917 | 122.1 | R | 3091 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040488 | FTAP Globe | 13.9156 | 122.1017 | 0.24 | Terrestrial Optical Fiber Drop | 1.06 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3040 | 4 | 40 | 3040 | 0405811001 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid I | 14.6778 | 121.1168 | U | 26178 | 7271 | 2181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0046 | PTCI/MIDC | 14.6785 | 121.1182 | 0.17 | Terrestrial Optical Fiber Drop | 1.01 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3041 | 4 | 41 | 3041 | 0304919016 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Doña Josefa | 15.4436 | 121.1235 | R | 2206 | 630 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-02328 | Edgepoint | 15.5029 | 121.0799 | 2.33 | Terrestrial Optical Fiber Drop | 4.59 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3042 | 4 | 42 | 3042 | 0205005027 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Santa Rosa | 16.489 | 121.1648 | R | 2959 | 778 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNVG0023 | PTCI/MIDC | 16.4915 | 121.1569 | 0.89 | Terrestrial Optical Fiber Drop | 1.91 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3043 | 4 | 43 | 3043 | 0301403014 | Region III (Central Luzon) | Bulacan | Baliuag | Poblacion | 14.9574 | 120.8988 | U | 11052 | 3157 | 947 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.53 | Terrestrial Optical Fiber Drop | 1.57 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3044 | 4 | 44 | 3044 | 0506216054 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | San Isidro | 13.0014 | 124.0395 | R | 3108 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_SOR_0001 | LDIC | 12.9853 | 123.9959 | 0.82 | Terrestrial Optical Fiber Drop | 3.59 | 2.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3045 | 4 | 45 | 3045 | 0704621019 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | San Jose | 9.5089 | 123.1402 | R | 4338 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0039 | PTCI/MIDC | 9.5016 | 123.1412 | 0.82 | Terrestrial Optical Fiber Drop | 9.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3046 | 4 | 46 | 3046 | 0908305038 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Veteran's Village | 7.7734 | 122.5719 | U | 9384 | 2234 | 670 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0027 | PTCI/MIDC | 7.769 | 122.5718 | 0.49 | Terrestrial Optical Fiber Drop | 1.48 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3047 | 4 | 47 | 3047 | 0306916024 | Region III (Central Luzon) | Tarlac | City of Tarlac | Calingcuan | 15.4876 | 120.6225 | R | 3837 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00708 | Edgepoint | 15.4836 | 120.623 | 0.45 | Terrestrial Optical Fiber Drop | 1.35 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3048 | 4 | 48 | 3048 | 0105522017 | Region I (Ilocos Region) | Pangasinan | Lingayen | Libsong East | 16.0299 | 120.2407 | U | 6519 | 1810 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00464 | Edgepoint | 16.0091 | 120.2223 | 0.54 | Terrestrial Optical Fiber Drop | 1.15 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3049 | 4 | 49 | 3049 | 1130700154 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 21-C | 7.0863 | 125.6129 | U | 7568 | 2225 | 668 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0001 | LDIC | 7.1827 | 125.4633 | 0.91 | Terrestrial Optical Fiber Drop | 1.02 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3050 | 4 | 50 | 3050 | 0301418005 | Region III (Central Luzon) | Bulacan | Pulilan | Dampol I | 14.9021 | 120.833 | U | 7077 | 2022 | 607 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0044 | PTCI/MIDC | 14.9011 | 120.8315 | 0.2 | Terrestrial Optical Fiber Drop | 1.89 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3051 | 4 | 51 | 3051 | 0601905015 | Region VI (Western Visayas) | Capiz | Ivisan | Santa Cruz | 11.5206 | 122.7094 | R | 2123 | 558 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060229 | FTAP Globe | 11.5171 | 122.6938 | 1.75 | Terrestrial Optical Fiber Drop | 1.68 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3052 | 4 | 52 | 3052 | 0500508027 | Region V (Bicol Region) | Albay | City of Ligao | Layon | 13.2411 | 123.5624 | R | 3371 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050155 | FTAP Globe | 13.2473 | 123.5607 | 0.71 | Terrestrial Optical Fiber Drop | 2.94 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3053 | 4 | 53 | 3053 | 1600306004 | Region XIII (Caraga) | Agusan del Sur | Prosperidad | Poblacion | 8.5985 | 125.9134 | U | 13580 | 3482 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130086 | FTAP Globe | 8.6223 | 125.9094 | 0.48 | Terrestrial Optical Fiber Drop | 1.2 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3054 | 4 | 54 | 3054 | 0401009011 | Region IV-A (CALABARZON) | Batangas | Cuenca | Labac | 13.8954 | 121.0582 | R | 2286 | 635 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 1.11 | Terrestrial Optical Fiber Drop | 1.01 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3055 | 4 | 55 | 3055 | 1030500045 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Consolacion | 8.4912 | 124.6458 | U | 9566 | 2657 | 797 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLR0026 | PTCI/MIDC | 8.4839 | 124.6532 | 1.15 | Terrestrial Optical Fiber Drop | 1.02 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3056 | 4 | 56 | 3056 | 1004308049 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 24 | 8.8273 | 125.0957 | R | 3442 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.8 | Terrestrial Optical Fiber Drop | 1.05 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3057 | 4 | 57 | 3057 | 1001308035 | Region X (Northern Mindanao) | Bukidnon | Kibawe | West Kibawe | 7.5751 | 124.9877 | U | 2982 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100062 | FTAP BTS | 7.5747 | 124.9878 | 0.05 | Terrestrial Optical Fiber Drop | 1.29 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3058 | 4 | 58 | 3058 | 0730600008 | Region VII (Central Visayas) | Cebu | City of Cebu | Basak San Nicolas | 10.286 | 123.8707 | U | 39012 | 12191 | 3657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070008 | FTAP BTS | 10.2831 | 123.8687 | 0.39 | Terrestrial Optical Fiber Drop | 1.13 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3059 | 4 | 59 | 3059 | 0301403001 | Region III (Central Luzon) | Bulacan | Baliuag | Bagong Nayon | 14.9597 | 120.8988 | U | 4441 | 1268 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.28 | Terrestrial Optical Fiber Drop | 1.74 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3060 | 4 | 60 | 3060 | 0403421004 | Region IV-A (CALABARZON) | Laguna | Pangil | Isla | 14.3996 | 121.4711 | R | 3151 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040124 | FTAP Globe | 14.4013 | 121.4743 | 0.39 | Terrestrial Optical Fiber Drop | 1.14 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3061 | 4 | 61 | 3061 | 1430300040 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Gibraltar | 16.4186 | 120.6229 | U | 8088 | 2128 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00333 | Edgepoint | 16.4171 | 120.6255 | 0.32 | Terrestrial Optical Fiber Drop | 2.01 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3062 | 4 | 62 | 3062 | 0631000041 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Cubay | 10.7325 | 122.5641 | U | 6979 | 1661 | 498 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060267 | FTAP Globe | 10.7314 | 122.5613 | 0.33 | Terrestrial Optical Fiber Drop | 1.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3063 | 4 | 63 | 3063 | 0301407022 | Region III (Central Luzon) | Bulacan | Calumpit | Pungo | 14.9018 | 120.79 | U | 9959 | 2845 | 854 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030552 | FTAP Globe | 14.8968 | 120.7949 | 0.76 | Terrestrial Optical Fiber Drop | 2.44 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3064 | 4 | 64 | 3064 | 0401005051 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pallocan Kanluran | 13.7542 | 121.0662 | U | 7057 | 1960 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03125-C08 | PTCI/MIDC | 13.756 | 121.0657 | 0.21 | Terrestrial Optical Fiber Drop | 1.36 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3065 | 4 | 65 | 3065 | 0402103066 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba II | 14.4614 | 120.9604 | U | 15394 | 4527 | 1358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000665 | FTAP Globe | 14.4686 | 121.0038 | 0.05 | Terrestrial Optical Fiber Drop | 0.51 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3066 | 4 | 66 | 3066 | 0506216015 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Cambulaga | 12.968 | 123.9899 | R | 5054 | 1263 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 1.42 | Terrestrial Optical Fiber Drop | 1.48 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3067 | 4 | 67 | 3067 | 0600416006 | Region VI (Western Visayas) | Aklan | Numancia | Bulwang | 11.7196 | 122.356 | U | 5334 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060216 | FTAP Globe | 11.7192 | 122.3578 | 0.2 | Terrestrial Optical Fiber Drop | 2.73 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3068 | 4 | 68 | 3068 | 1401111003 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Bulalacao | 16.8422 | 120.8112 | R | 3453 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 2.58 | Terrestrial Optical Fiber Drop | 2.14 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3069 | 4 | 69 | 3069 | 0402120001 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya I | 14.3832 | 120.8337 | U | 14142 | 4159 | 1248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040133 | FTAP Globe | 14.3857 | 120.8304 | 0.45 | Terrestrial Optical Fiber Drop | 1.88 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3070 | 4 | 70 | 3070 | 0704614030 | Region VII (Central Visayas) | Negros Oriental | Mabinay | Poblacion | 9.7208 | 122.9352 | U | 7357 | 1936 | 581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0034 | PTCI/MIDC | 9.7257 | 122.9276 | 1 | Terrestrial Optical Fiber Drop | 1.11 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3071 | 4 | 71 | 3071 | 1705203012 | MIMAROPA Region | Oriental Mindoro | Bongabong | Labasan | 12.778 | 121.4704 | R | 4730 | 1212 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170111 | FTAP Globe | 12.7816 | 121.4714 | 0.45 | Terrestrial Optical Fiber Drop | 4.21 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3072 | 4 | 72 | 3072 | 0305406025 | Region III (Central Luzon) | Pampanga | Floridablanca | San Isidro | 15.0077 | 120.5116 | R | 2657 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01623-B07 | PTCI/MIDC | 15.0122 | 120.5175 | 0.81 | Terrestrial Optical Fiber Drop | 2.06 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3073 | 4 | 73 | 3073 | 0704603002 | Region VII (Central Visayas) | Negros Oriental | Bacong | Banilad | 9.2708 | 123.2885 | U | 5739 | 1510 | 453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 0.65 | Terrestrial Optical Fiber Drop | 2.01 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3074 | 4 | 74 | 3074 | 0304903033 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Dionisio S. Garcia | 15.4722 | 120.9609 | U | 8071 | 2306 | 692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00717 | Edgepoint | 15.4684 | 120.9565 | 0.63 | Terrestrial Optical Fiber Drop | 1.05 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3075 | 4 | 75 | 3075 | 0403403018 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Niño | 14.328 | 121.0823 | U | 8480 | 2569 | 771 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0035 | PTCI/MIDC | 14.3307 | 121.078 | 0.55 | Terrestrial Optical Fiber Drop | 1.37 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3076 | 4 | 76 | 3076 | 0702210012 | Region VII (Central Visayas) | Cebu | Barili | Giwanon | 10.1115 | 123.5274 | R | 2101 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070062 | FTAP BTS | 10.116 | 123.5147 | 0.87 | Terrestrial Optical Fiber Drop | 2.06 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3077 | 4 | 77 | 3077 | 0402111021 | Region IV-A (CALABARZON) | Cavite | Kawit | Tabon III | 14.4422 | 120.904 | R | 2424 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S6811 | FTAP Smart | 14.4193 | 120.8997 | 0.78 | Terrestrial Optical Fiber Drop | 2.67 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3078 | 4 | 78 | 3078 | 0500506005 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 1 - Em's Barrio | 13.1463 | 123.7301 | R | 3334 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050174 | FTAP Globe | 13.1521 | 123.7315 | 0.66 | Terrestrial Optical Fiber Drop | 1.32 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3079 | 4 | 79 | 3079 | 0305416024 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Agustin | 15.0418 | 120.6693 | U | 23914 | 5978 | 1793 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00916 | Edgepoint | 15.0445 | 120.6724 | 0.44 | Terrestrial Optical Fiber Drop | 1.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3080 | 4 | 80 | 3080 | 0402109059 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang I-D | 14.4025 | 120.9407 | R | 4925 | 1448 | 434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAM0355 | PTCI/MIDC | 14.4068 | 120.8907 | 0.98 | Terrestrial Optical Fiber Drop | 0.5 | 4.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3081 | 4 | 81 | 3081 | 0401013014 | Region IV-A (CALABARZON) | Batangas | Lian | Malaruhatan | 14.0378 | 120.6573 | R | 4960 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00132-C08 | PTCI/MIDC | 14.0389 | 120.6568 | 0.13 | Terrestrial Optical Fiber Drop | 4.44 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3082 | 4 | 82 | 3082 | 1600312003 | Region XIII (Caraga) | Agusan del Sur | Trento | Kapatungan | 8.0652 | 126.0171 | R | 5000 | 1282 | 385 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130102 | FTAP Globe | 8.0802 | 126.0361 | 1.39 | Terrestrial Optical Fiber Drop | 5.51 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3083 | 4 | 83 | 3083 | 0402120040 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan VI | 14.4044 | 120.8466 | R | 5236 | 1540 | 462 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02478-C08 | PTCI/MIDC | 14.3915 | 120.8482 | 0.34 | Terrestrial Optical Fiber Drop | 1.8 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3084 | 4 | 84 | 3084 | 0701205006 | Region VII (Central Visayas) | Bohol | Baclayon | Laya | 9.6177 | 123.9299 | R | 1114 | 278 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 2.76 | Terrestrial Optical Fiber Drop | 0.9 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3085 | 4 | 85 | 3085 | 0305416022 | Region III (Central Luzon) | Pampanga | City of San Fernando | Quebiauan | 15.0566 | 120.665 | U | 11673 | 2918 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00909 | Edgepoint | 15.0517 | 120.6663 | 0.56 | Terrestrial Optical Fiber Drop | 2.44 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3086 | 4 | 86 | 3086 | 0300804038 | Region III (Central Luzon) | Bataan | Dinalupihan | Santo Niño | 14.8765 | 120.4591 | R | 3633 | 1009 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030118 | FTAP BTS | 14.8738 | 120.4626 | 0.48 | Terrestrial Optical Fiber Drop | 1.06 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3087 | 4 | 87 | 3087 | 0500517035 | Region V (Bicol Region) | Albay | City of Tabaco | Salvacion | 13.3485 | 123.7126 | U | 3855 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0020 | PTCI/MIDC | 13.3645 | 123.7226 | 0.48 | Terrestrial Optical Fiber Drop | 2.08 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3088 | 4 | 88 | 3088 | 0907322011 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Bulatok | 7.8473 | 123.4459 | U | 5778 | 1481 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090131 | FTAP Globe | 7.8452 | 123.4458 | 0.24 | Terrestrial Optical Fiber Drop | 1.98 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3089 | 4 | 89 | 3089 | 0500503025 | Region V (Bicol Region) | Albay | Daraga | Kilicao | 13.16 | 123.7155 | R | 4947 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050173 | FTAP Globe | 13.155 | 123.7161 | 0.56 | Terrestrial Optical Fiber Drop | 1.48 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3090 | 4 | 90 | 3090 | 0301410056 | Region III (Central Luzon) | Bulacan | City of Malolos | Cofradia | 14.8422 | 120.8316 | U | 4817 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01130 | Edgepoint | 14.8467 | 120.8352 | 0.63 | Terrestrial Optical Fiber Drop | 2.09 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3091 | 4 | 91 | 3091 | 0604518007 | Region VI (Western Visayas) | Negros Occidental | Manapla | Punta Mesa | 10.935 | 123.1131 | U | 7887 | 2131 | 639 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060323 | FTAP Globe | 10.9526 | 123.1256 | 2.38 | Terrestrial Optical Fiber Drop | 2.42 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3092 | 4 | 92 | 3092 | 1030900030 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Tubod | 8.2137 | 124.2427 | U | 33702 | 8868 | 2660 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100173 | FTAP Globe | 8.2092 | 124.2416 | 0.51 | Terrestrial Optical Fiber Drop | 1.65 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3093 | 4 | 93 | 3093 | 0500512010 | Region V (Bicol Region) | Albay | Oas | Bongoran | 13.2534 | 123.5032 | R | 1823 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050151 | FTAP Globe | 13.2593 | 123.5008 | 0.71 | Terrestrial Optical Fiber Drop | 1.17 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3094 | 4 | 94 | 3094 | 0702231009 | Region VII (Central Visayas) | Cebu | Medellin | Caputatan Sur | 11.1237 | 123.9685 | R | 2835 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 0.53 | Terrestrial Optical Fiber Drop | 1.74 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3095 | 4 | 95 | 3095 | 0305420008 | Region III (Central Luzon) | Pampanga | Santa Rita | San Matias | 14.9774 | 120.6207 | R | 3795 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 1.14 | Terrestrial Optical Fiber Drop | 1.06 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3096 | 4 | 96 | 3096 | 0105533017 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw East | 16.1265 | 120.4002 | R | 2555 | 709 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 0.63 | Terrestrial Optical Fiber Drop | 1.18 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3097 | 4 | 97 | 3097 | 1102319023 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo East | 7.4497 | 125.8167 | U | 16035 | 4333 | 1300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0031 | PTCI/MIDC | 7.4488 | 125.8199 | 0.36 | Terrestrial Optical Fiber Drop | 1.31 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3098 | 4 | 98 | 3098 | 1206315006 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | Maibo | 6.5522 | 124.7765 | R | 3398 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120202 | FTAP BTS | 6.5643 | 124.7666 | 1.73 | Terrestrial Optical Fiber Drop | 19.05 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3099 | 4 | 99 | 3099 | 0704604032 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Talungon | 9.6008 | 123.1195 | U | 3867 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0004 | PTCI/MIDC | 9.5938 | 123.1254 | 1.01 | Terrestrial Optical Fiber Drop | 1.25 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3100 | 4 | 100 | 3100 | 0304927011 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Rizal District | 15.3608 | 120.9418 | R | 2606 | 744 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03195-B07 | PTCI/MIDC | 15.3513 | 120.9393 | 0.46 | Terrestrial Optical Fiber Drop | 0.68 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3101 | 4 | 101 | 3101 | 0630200002 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Alijis | 10.6311 | 122.9558 | U | 23511 | 6530 | 1959 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0116 | PTCI/MIDC | 10.6309 | 122.9621 | 0.69 | Terrestrial Optical Fiber Drop | 1.95 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3102 | 4 | 102 | 3102 | 0305407002 | Region III (Central Luzon) | Pampanga | Guagua | Bancal | 14.9612 | 120.6334 | U | 7190 | 1797 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00990 | Edgepoint | 14.9623 | 120.6303 | 0.35 | Terrestrial Optical Fiber Drop | 1.38 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3103 | 4 | 103 | 3103 | 1401111008 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Paco | 16.8672 | 120.7793 | U | 4976 | 1421 | 426 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 3946 | FTAP Smart | 16.8676 | 120.788 | 0.93 | Terrestrial Optical Fiber Drop | 2.25 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3104 | 4 | 104 | 3104 | 0500517029 | Region V (Bicol Region) | Albay | City of Tabaco | Pawa | 13.3656 | 123.7208 | R | 4520 | 1102 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0020 | PTCI/MIDC | 13.3645 | 123.7226 | 0.23 | Terrestrial Optical Fiber Drop | 1.83 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3105 | 4 | 105 | 3105 | 0401014057 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Carlos | 13.9487 | 121.1517 | U | 7989 | 2219 | 666 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02802-C08 | PTCI/MIDC | 13.9457 | 121.149 | 0.44 | Terrestrial Optical Fiber Drop | 1.67 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3106 | 4 | 106 | 3106 | 0702250011 | Region VII (Central Visayas) | Cebu | City of Talisay | Mohon | 10.2492 | 123.8264 | U | 11545 | 3038 | 911 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070361 | FTAP Globe | 10.2444 | 123.8249 | 0.56 | Terrestrial Optical Fiber Drop | 1.71 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3107 | 4 | 107 | 3107 | 0401003003 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 1 | 13.9378 | 120.7323 | R | 2162 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 0.62 | Terrestrial Optical Fiber Drop | 0.78 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3108 | 4 | 108 | 3108 | 1001321035 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Vintar | 7.9095 | 125.0938 | R | 2843 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100202 | FTAP Globe | 7.9439 | 125.1039 | 1.23 | Terrestrial Optical Fiber Drop | 0.43 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3109 | 4 | 109 | 3109 | 1004319002 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Bulwa | 8.9089 | 125.0165 | R | 1914 | 490 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0109 | PTCI/MIDC | 8.8977 | 125.027 | 1.7 | Terrestrial Optical Fiber Drop | 1.03 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3110 | 4 | 110 | 3110 | 1001314018 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | San Miguel | 8.3826 | 124.8341 | U | 6171 | 1623 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100160 | FTAP Globe | 8.3902 | 124.836 | 0.87 | Terrestrial Optical Fiber Drop | 1.6 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3111 | 4 | 111 | 3111 | 1004319011 | Region X (Northern Mindanao) | Misamis Oriental | Medina | North Poblacion | 8.9136 | 125.0142 | U | 5827 | 1494 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0069 | PTCI/MIDC | 8.9279 | 125.0013 | 2.13 | Terrestrial Optical Fiber Drop | 1.19 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3112 | 4 | 112 | 3112 | 0704610013 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Daro | 9.3223 | 123.2948 | U | 6418 | 1688 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070264 | FTAP Globe | 9.3258 | 123.2903 | 0.62 | Terrestrial Optical Fiber Drop | 2.12 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3113 | 4 | 113 | 3113 | 0908305006 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Don Andres | 7.771 | 122.5814 | U | 7016 | 1670 | 501 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0003 | PTCI/MIDC | 7.7721 | 122.5856 | 0.48 | Terrestrial Optical Fiber Drop | 1.05 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3114 | 4 | 114 | 3114 | 0600401005 | Region VI (Western Visayas) | Aklan | Altavas | Ginictan | 11.5344 | 122.4757 | R | 1682 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.35 | Terrestrial Optical Fiber Drop | 1.2 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3115 | 4 | 115 | 3115 | 0401003004 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 10 | 13.9341 | 120.7329 | R | 2777 | 771 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBGG0059 | PTCI/MIDC | 13.9557 | 120.7255 | 0.35 | Terrestrial Optical Fiber Drop | 1.16 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3116 | 4 | 116 | 3116 | 1003503015 | Region X (Northern Mindanao) | Lanao del Norte | Baroy | Poblacion | 8.025 | 123.78 | R | 3018 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0004 | PTCI/MIDC | 8.0239 | 123.7821 | 0.26 | Terrestrial Optical Fiber Drop | 2.9 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3117 | 4 | 117 | 3117 | 0604523008 | Region VI (Western Visayas) | Negros Occidental | City of Sagay | Fabrica | 10.8958 | 123.3549 | R | 5129 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0027 | PTCI/MIDC | 10.894 | 123.3521 | 0.37 | Terrestrial Optical Fiber Drop | 16.87 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3118 | 4 | 118 | 3118 | 0506216022 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Pangpang | 12.9847 | 123.9841 | U | 10402 | 2600 | 780 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 0.69 | Terrestrial Optical Fiber Drop | 2.66 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3119 | 4 | 119 | 3119 | 0604524014 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay V | 10.4791 | 123.411 | U | 7527 | 2034 | 610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060367 | FTAP Globe | 10.4828 | 123.4094 | 0.45 | Terrestrial Optical Fiber Drop | 1.06 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3120 | 4 | 120 | 3120 | 0301414009 | Region III (Central Luzon) | Bulacan | Obando | Panghulo | 14.6979 | 120.9463 | U | 13716 | 3918 | 1175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02514 | Edgepoint | 14.6992 | 120.9457 | 0.16 | Terrestrial Optical Fiber Drop | 1.65 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3121 | 4 | 121 | 3121 | 0730600062 | Region VII (Central Visayas) | Cebu | City of Cebu | Punta Princesa | 10.2944 | 123.872 | U | 22685 | 7089 | 2127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CEB_0004 | LDIC | 10.2979 | 123.8697 | 0.47 | Terrestrial Optical Fiber Drop | 1.65 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3122 | 4 | 122 | 3122 | 0402115030 | Region IV-A (CALABARZON) | Cavite | Naic | Sapa | 14.31 | 120.7717 | R | 1486 | 437 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02229-C08 | PTCI/MIDC | 14.3227 | 120.7719 | 1.14 | Terrestrial Optical Fiber Drop | 1.3 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3123 | 4 | 123 | 3123 | 0301423007 | Region III (Central Luzon) | Bulacan | Santa Maria | Cay Pombo | 14.8523 | 120.9779 | U | 34153 | 9758 | 2927 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02583 | Edgepoint | 14.8531 | 120.9756 | 0.27 | Terrestrial Optical Fiber Drop | 2.32 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3124 | 4 | 124 | 3124 | 0405811010 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santa Ana | 14.6963 | 121.116 | U | 10398 | 2888 | 866 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01354 | Edgepoint | 14.6926 | 121.1157 | 0.42 | Terrestrial Optical Fiber Drop | 1.05 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3125 | 4 | 125 | 3125 | 0604532007 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pinowayan | 10.5713 | 123.2182 | R | 2812 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060364 | FTAP Globe | 10.5112 | 123.2785 | 9.39 | Terrestrial Optical Fiber Drop | 2.27 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3126 | 4 | 126 | 3126 | 0305407012 | Region III (Central Luzon) | Pampanga | Guagua | San Agustin | 14.9929 | 120.6234 | U | 7282 | 1820 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00955 | Edgepoint | 14.9916 | 120.6305 | 0.78 | Terrestrial Optical Fiber Drop | 2.31 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3127 | 4 | 127 | 3127 | 0102812030 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 32-A, La Paz East | 18.205 | 120.5316 | R | 1416 | 382 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01209-B05 | PTCI/MIDC | 18.2087 | 120.5983 | 0.38 | Terrestrial Optical Fiber Drop | 5.7 | 5.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3128 | 4 | 128 | 3128 | 0301403020 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Cristo | 14.9564 | 120.8967 | U | 10035 | 2867 | 860 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1598 | FTAP Smart | 14.9544 | 120.894 | 0.37 | Terrestrial Optical Fiber Drop | 1.33 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3129 | 4 | 129 | 3129 | 0501724032 | Region V (Bicol Region) | Camarines Sur | City of Naga | Triangulo | 13.6195 | 123.1959 | U | 8681 | 2066 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0029 | PTCI/MIDC | 13.6169 | 123.1988 | 0.42 | Terrestrial Optical Fiber Drop | 1.1 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3130 | 4 | 130 | 3130 | 0403415003 | Region IV-A (CALABARZON) | Laguna | Magdalena | Munting Ambling | 14.2022 | 121.4289 | R | 1834 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.74 | Terrestrial Optical Fiber Drop | 0.46 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3131 | 4 | 131 | 3131 | 0304932004 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Concepcion | 15.4445 | 120.7995 | U | 6502 | 1857 | 557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.37 | Terrestrial Optical Fiber Drop | 1.29 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3132 | 4 | 132 | 3132 | 0730600040 | Region VII (Central Visayas) | Cebu | City of Cebu | Labangon | 10.3 | 123.8817 | U | 32865 | 10270 | 3081 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0027 | PTCI/MIDC | 10.294 | 123.8817 | 0.67 | Terrestrial Optical Fiber Drop | 1.91 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3133 | 4 | 133 | 3133 | 1102319016 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo Poblacion | 7.4476 | 125.8017 | U | 2994 | 809 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0124 | PTCI/MIDC | 7.4318 | 125.8027 | 0.31 | Terrestrial Optical Fiber Drop | 2.51 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3134 | 4 | 134 | 3134 | 0403411015 | Region IV-A (CALABARZON) | Laguna | Los Baños | Malinta | 14.1859 | 121.2301 | U | 7159 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02047-C08 | PTCI/MIDC | 14.1865 | 121.2336 | 0.38 | Terrestrial Optical Fiber Drop | 1.52 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3135 | 4 | 135 | 3135 | 0402120043 | Region IV-A (CALABARZON) | Cavite | Tanza | Paradahan II | 14.3248 | 120.8592 | R | 5133 | 1509 | 453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040169 | FTAP Globe | 14.3237 | 120.8601 | 0.15 | Terrestrial Optical Fiber Drop | 4.82 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3136 | 4 | 136 | 3136 | 1003522004 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | Bulod | 8.0479 | 123.811 | R | 2342 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 2.2 | Terrestrial Optical Fiber Drop | 1.41 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3137 | 4 | 137 | 3137 | 0105546003 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Bactad East | 15.9768 | 120.6195 | R | 2192 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTPNG0006 | PTCI/MIDC | 15.9738 | 120.5695 | 0.46 | Terrestrial Optical Fiber Drop | 5.18 | 5.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3138 | 4 | 138 | 3138 | 1600201015 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Poblacion 3 | 8.9751 | 125.4078 | U | 3797 | 926 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0002 | PTCI/MIDC | 8.9795 | 125.4097 | 0.53 | Terrestrial Optical Fiber Drop | 1.14 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3139 | 4 | 139 | 3139 | 0301410051 | Region III (Central Luzon) | Bulacan | City of Malolos | Santor | 14.8391 | 120.8136 | U | 8937 | 2553 | 766 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01114 | Edgepoint | 14.8539 | 120.8364 | 0.77 | Terrestrial Optical Fiber Drop | 0.19 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3140 | 4 | 140 | 3140 | 0405630018 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Pinagbayanan | 13.9713 | 121.6912 | R | 4405 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03053-C10 | PTCI/MIDC | 13.978 | 121.686 | 2.85 | Terrestrial Optical Fiber Drop | 0.99 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3141 | 4 | 141 | 3141 | 1003522019 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | Poblacion | 8.0513 | 123.7939 | U | 11654 | 2774 | 832 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 0.79 | Terrestrial Optical Fiber Drop | 1.1 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3142 | 4 | 142 | 3142 | 1606724096 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Canlanipa | 9.7762 | 125.4951 | U | 12311 | 3002 | 901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0015 | PTCI/MIDC | 9.7735 | 125.496 | 0.32 | Terrestrial Optical Fiber Drop | 1.32 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3143 | 4 | 143 | 3143 | 0201511008 | Region II (Cagayan Valley) | Cagayan | Claveria | Centro I | 18.6069 | 121.0789 | R | 1835 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01189-B05 | PTCI/MIDC | 18.6025 | 121.0861 | 0.9 | Terrestrial Optical Fiber Drop | 1.06 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3144 | 4 | 144 | 3144 | 0731300014 | Region VII (Central Visayas) | Cebu | City of Mandaue | Jagobiao | 10.3647 | 123.9561 | U | 12150 | 3471 | 1041 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0121 | PTCI/MIDC | 10.3645 | 123.9514 | 0.51 | Terrestrial Optical Fiber Drop | 1.35 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3145 | 4 | 145 | 3145 | 0306909015 | Region III (Central Luzon) | Tarlac | Moncada | Camposanto 2 | 15.7345 | 120.5682 | R | 2192 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.6 | Terrestrial Optical Fiber Drop | 1.46 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3146 | 4 | 146 | 3146 | 0301417018 | Region III (Central Luzon) | Bulacan | Plaridel | Santa Ines | 14.8842 | 120.8595 | U | 3054 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02950-B07 | PTCI/MIDC | 14.8952 | 120.852 | 0.66 | Terrestrial Optical Fiber Drop | 2.23 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3147 | 4 | 147 | 3147 | 0403428015 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Kanluran | 14.3024 | 121.1094 | U | 4643 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0029 | PTCI/MIDC | 14.2926 | 121.0962 | 0.34 | Terrestrial Optical Fiber Drop | 0.62 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3148 | 4 | 148 | 3148 | 0105519005 | Region I (Ilocos Region) | Pangasinan | Dasol | Gais-Guipe | 15.9789 | 119.8692 | R | 2646 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01738-B07 | PTCI/MIDC | 15.9818 | 119.8707 | 0.36 | Terrestrial Optical Fiber Drop | 1.35 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3149 | 4 | 149 | 3149 | 1004312015 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Sumalag | 8.9776 | 124.7854 | R | 1056 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 0.99 | Terrestrial Optical Fiber Drop | 1.08 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3150 | 4 | 150 | 3150 | 0331400003 | Region III (Central Luzon) | Zambales | City of Olongapo | Barretto | 14.8564 | 120.2706 | U | 22178 | 5994 | 1798 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030584 | FTAP Globe | 14.8444 | 120.293 | 0.64 | Terrestrial Optical Fiber Drop | 1.12 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3151 | 4 | 151 | 3151 | 1102403005 | Region XI (Davao Region) | Davao del Sur | City of Digos | Cogon | 6.7589 | 125.3694 | U | 10000 | 2941 | 882 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0112 | PTCI/MIDC | 6.7584 | 125.3731 | 0.41 | Terrestrial Optical Fiber Drop | 1.54 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3152 | 4 | 152 | 3152 | 0301410014 | Region III (Central Luzon) | Bulacan | City of Malolos | Dakila | 14.8506 | 120.8354 | U | 7114 | 2032 | 610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01114 | Edgepoint | 14.8539 | 120.8364 | 0.38 | Terrestrial Optical Fiber Drop | 2 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3153 | 4 | 153 | 3153 | 0401003005 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 11 | 13.9343 | 120.7328 | R | 1479 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01973-C08 | PTCI/MIDC | 13.9355 | 120.7354 | 0.32 | Terrestrial Optical Fiber Drop | 1.14 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3154 | 4 | 154 | 3154 | 0501734014 | Region V (Bicol Region) | Camarines Sur | Sipocot | Calagbangan | 13.8372 | 122.9634 | R | 3860 | 919 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 3.8 | Terrestrial Optical Fiber Drop | 2.29 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3155 | 4 | 155 | 3155 | 0105510021 | Region I (Ilocos Region) | Pangasinan | Bautista | Baluyot | 15.8011 | 120.4637 | R | 3735 | 1037 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00572 | Edgepoint | 15.8049 | 120.457 | 0.83 | Terrestrial Optical Fiber Drop | 1.93 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3156 | 4 | 156 | 3156 | 0330100021 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulung Cacutud | 15.1709 | 120.6152 | U | 26510 | 7363 | 2209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02946-B07 | PTCI/MIDC | 15.1703 | 120.6123 | 0.32 | Terrestrial Optical Fiber Drop | 1.1 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3157 | 4 | 157 | 3157 | 1606701007 | Region XIII (Caraga) | Surigao del Norte | Alegria | San Pedro | 9.4799 | 125.574 | R | 2576 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 1.97 | Terrestrial Optical Fiber Drop | 2.49 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3158 | 4 | 158 | 3158 | 1003520004 | Region X (Northern Mindanao) | Lanao del Norte | Tagoloan | Inagongan | 8.1031 | 124.2445 | R | 3770 | 897 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100189 | FTAP Globe | 8.0656 | 124.2637 | 4.67 | Terrestrial Optical Fiber Drop | 10.86 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3159 | 4 | 159 | 3159 | 0405814007 | Region IV-A (CALABARZON) | Rizal | Teresa | Prinza | 14.5363 | 121.2172 | U | 7180 | 1994 | 598 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02990-A04 | PTCI/MIDC | 14.5352 | 121.2159 | 0.19 | Terrestrial Optical Fiber Drop | 1.81 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3160 | 4 | 160 | 3160 | 1030900031 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Bagong Silang | 8.2393 | 124.2549 | U | 6188 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNR0010 | PTCI/MIDC | 8.2442 | 124.2545 | 0.54 | Terrestrial Optical Fiber Drop | 2 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3161 | 4 | 161 | 3161 | 0405647037 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Lalo | 14.0406 | 121.5712 | R | 4149 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02129-C08 | PTCI/MIDC | 14.0285 | 121.5816 | 1.75 | Terrestrial Optical Fiber Drop | 3.05 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3162 | 4 | 162 | 3162 | 0300808005 | Region III (Central Luzon) | Bataan | Morong | Sabang | 14.6912 | 120.2504 | U | 8389 | 2330 | 699 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0020 | PTCI/MIDC | 14.6958 | 120.2519 | 0.53 | Terrestrial Optical Fiber Drop | 2.41 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3163 | 4 | 163 | 3163 | 0306909016 | Region III (Central Luzon) | Tarlac | Moncada | Capaoayan | 15.7304 | 120.5669 | R | 3371 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.91 | Terrestrial Optical Fiber Drop | 1.13 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3164 | 4 | 164 | 3164 | 0300807016 | Region III (Central Luzon) | Bataan | Mariveles | Ipag | 14.4298 | 120.4782 | U | 12016 | 3337 | 1001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0003 | PTCI/MIDC | 14.4309 | 120.4797 | 0.2 | Terrestrial Optical Fiber Drop | 1.17 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3165 | 4 | 165 | 3165 | 0803703012 | Region VIII (Eastern Visayas) | Leyte | Albuera | San Pedro | 10.9128 | 124.7055 | R | 4072 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080134 | FTAP BTS | 10.9117 | 124.6992 | 0.7 | Terrestrial Optical Fiber Drop | 1.96 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3166 | 4 | 166 | 3166 | 0301403006 | Region III (Central Luzon) | Bulacan | Baliuag | Hinukay | 15.0125 | 120.8815 | R | 2327 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02444-B07 | PTCI/MIDC | 15.0175 | 120.8885 | 0.94 | Terrestrial Optical Fiber Drop | 1.2 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3167 | 4 | 167 | 3167 | 0702251014 | Region VII (Central Visayas) | Cebu | City of Toledo | Carmen | 10.3923 | 123.6635 | R | 4967 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 0.43 | Terrestrial Optical Fiber Drop | 1.13 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3168 | 4 | 168 | 3168 | 0304932026 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Old | 15.4407 | 120.7792 | R | 3933 | 1123 | 337 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01419-B07 | PTCI/MIDC | 15.4394 | 120.779 | 0.15 | Terrestrial Optical Fiber Drop | 1.68 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3169 | 4 | 169 | 3169 | 0630200058 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Tangub | 10.6336 | 122.9344 | U | 46530 | 12925 | 3878 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060350 | FTAP Globe | 10.6355 | 122.9397 | 0.62 | Terrestrial Optical Fiber Drop | 2.15 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3170 | 4 | 170 | 3170 | 1108204017 | Region XI (Davao Region) | Davao de Oro | Maco | Lumatab | 7.4278 | 125.9081 | R | 1379 | 372 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 1.66 | Terrestrial Optical Fiber Drop | 9.78 | 7.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3171 | 4 | 171 | 3171 | 0403428023 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Tagapo | 14.3189 | 121.1032 | U | 46153 | 13985 | 4196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0019 | PTCI/MIDC | 14.3211 | 121.1055 | 0.35 | Terrestrial Optical Fiber Drop | 2.16 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3172 | 4 | 172 | 3172 | 0305407024 | Region III (Central Luzon) | Pampanga | Guagua | San Rafael | 14.9618 | 120.6357 | R | 4510 | 1127 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00990 | Edgepoint | 14.9623 | 120.6303 | 0.58 | Terrestrial Optical Fiber Drop | 1.41 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3173 | 4 | 173 | 3173 | 0305416034 | Region III (Central Luzon) | Pampanga | City of San Fernando | Santo Niño | 15.0298 | 120.6809 | U | 11892 | 2973 | 892 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02616-B07 | PTCI/MIDC | 15.0339 | 120.6814 | 0.46 | Terrestrial Optical Fiber Drop | 1.1 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3174 | 4 | 174 | 3174 | 0600613006 | Region VI (Western Visayas) | Antique | San Jose | Barangay 4 | 10.7406 | 121.9379 | R | 3026 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0017 | PTCI/MIDC | 10.7423 | 121.9371 | 0.21 | Terrestrial Optical Fiber Drop | 2.41 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3175 | 4 | 175 | 3175 | 0305405027 | Region III (Central Luzon) | Pampanga | Candaba | Pulong Palazan | 15.0239 | 120.8845 | R | 4100 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01631-B07 | PTCI/MIDC | 15.0268 | 120.8817 | 0.44 | Terrestrial Optical Fiber Drop | 1.62 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3176 | 4 | 176 | 3176 | 0402108031 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Bacao II | 14.4052 | 120.8832 | U | 9416 | 2769 | 831 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAM0355 | PTCI/MIDC | 14.4068 | 120.8907 | 0.83 | Terrestrial Optical Fiber Drop | 2.4 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3177 | 4 | 177 | 3177 | 1430300034 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Quirino Hill, East | 16.4301 | 120.5908 | R | 3517 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0030 | LDIC | 16.3878 | 120.5835 | 0.22 | Terrestrial Optical Fiber Drop | 0.59 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3178 | 4 | 178 | 3178 | 0103307003 | Region I (Ilocos Region) | La Union | Bauang | Baccuit Sur | 16.5411 | 120.3205 | U | 2784 | 752 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00310 | Edgepoint | 16.5486 | 120.3207 | 0.84 | Terrestrial Optical Fiber Drop | 1.21 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3179 | 4 | 179 | 3179 | 0401014024 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Latag | 13.9292 | 121.1749 | U | 9642 | 2678 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1508 | FTAP Smart | 13.9305 | 121.1762 | 0.2 | Terrestrial Optical Fiber Drop | 1.9 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3180 | 4 | 180 | 3180 | 0401022009 | Region IV-A (CALABARZON) | Batangas | San Jose | Bigain I | 13.8875 | 121.0731 | R | 2421 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1014 | FTAP Smart | 13.8783 | 121.0934 | 0.5 | Terrestrial Optical Fiber Drop | 2.83 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3181 | 4 | 181 | 3181 | 0205013008 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Osmeña | 16.5225 | 121.1783 | U | 6383 | 1679 | 504 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0020 | PTCI/MIDC | 16.5206 | 121.1751 | 0.4 | Terrestrial Optical Fiber Drop | 1.26 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3182 | 4 | 182 | 3182 | 1004302032 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Waterfall | 8.7323 | 124.781 | U | 6203 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0097 | PTCI/MIDC | 8.7255 | 124.7903 | 1.28 | Terrestrial Optical Fiber Drop | 1.99 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3183 | 4 | 183 | 3183 | 0630200055 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Singcang-Airport | 10.6571 | 122.9343 | U | 34840 | 9677 | 2903 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0015 | PTCI/MIDC | 10.6614 | 122.9402 | 0.81 | Terrestrial Optical Fiber Drop | 2.25 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3184 | 4 | 184 | 3184 | 0203108001 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Alicaocao | 16.949 | 121.7781 | R | 2445 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00217 | Edgepoint | 16.9485 | 121.7801 | 0.23 | Terrestrial Optical Fiber Drop | 2.02 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3185 | 4 | 185 | 3185 | 0500517024 | Region V (Bicol Region) | Albay | City of Tabaco | Matagbac | 13.3529 | 123.7057 | U | 5427 | 1323 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050133 | FTAP Globe | 13.3444 | 123.7023 | 1.01 | Terrestrial Optical Fiber Drop | 2.77 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3186 | 4 | 186 | 3186 | 0301420031 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Graceville | 14.7869 | 121.061 | U | 44118 | 12605 | 3782 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01053-B07 | PTCI/MIDC | 14.7833 | 121.0584 | 0.49 | Terrestrial Optical Fiber Drop | 1.57 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3187 | 4 | 187 | 3187 | 1004319003 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Cabug | 8.9033 | 125.0239 | R | 2922 | 749 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0109 | PTCI/MIDC | 8.8977 | 125.027 | 0.71 | Terrestrial Optical Fiber Drop | 1.05 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3188 | 4 | 188 | 3188 | 0304917002 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Balante | 15.7302 | 120.907 | R | 2033 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0027 | PTCI/MIDC | 15.7254 | 120.9006 | 0.87 | Terrestrial Optical Fiber Drop | 1.67 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3189 | 4 | 189 | 3189 | 0304911023 | Region III (Central Luzon) | Nueva Ecija | Guimba | Cawayan Bugtong | 15.6495 | 120.779 | U | 5006 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02674 | Edgepoint | 15.6486 | 120.7778 | 0.16 | Terrestrial Optical Fiber Drop | 1.62 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3190 | 4 | 190 | 3190 | 0201529047 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Linao West | 17.6539 | 121.7257 | R | 1945 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-02372 | Edgepoint | 17.653 | 121.7425 | 0.8 | Terrestrial Optical Fiber Drop | 2.3 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3191 | 4 | 191 | 3191 | 0105503021 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Poblacion | 16.1602 | 119.9818 | U | 10961 | 3044 | 913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00400 | Edgepoint | 16.1612 | 119.9829 | 0.16 | Terrestrial Optical Fiber Drop | 1.02 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3192 | 4 | 192 | 3192 | 0306910034 | Region III (Central Luzon) | Tarlac | Paniqui | Tablang | 15.6713 | 120.5681 | R | 3215 | 824 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00610 | Edgepoint | 15.6665 | 120.5713 | 0.64 | Terrestrial Optical Fiber Drop | 2.07 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3193 | 4 | 193 | 3193 | 0405646018 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Magsaysay | 13.9656 | 122.5321 | R | 2409 | 633 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0008 | PTCI/MIDC | 13.9719 | 122.5259 | 0.97 | Terrestrial Optical Fiber Drop | 1.12 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3194 | 4 | 194 | 3194 | 0300802002 | Region III (Central Luzon) | Bataan | Bagac | Banawang | 14.62 | 120.3867 | R | 3614 | 1003 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | 3934 | FTAP Smart | 14.6029 | 120.3972 | 2.21 | Terrestrial Optical Fiber Drop | 2 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3195 | 4 | 195 | 3195 | 0105517006 | Region I (Ilocos Region) | Pangasinan | Calasiao | Cabilocaan | 16.0233 | 120.3783 | R | 3009 | 835 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-02240 | Edgepoint | 16.02 | 120.3779 | 0.37 | Terrestrial Optical Fiber Drop | 1.39 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3196 | 4 | 196 | 3196 | 0301415008 | Region III (Central Luzon) | Bulacan | Pandi | Cupang | 14.8953 | 120.9371 | R | 3099 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02581 | Edgepoint | 14.8983 | 120.94 | 0.45 | Terrestrial Optical Fiber Drop | 2.25 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3197 | 4 | 197 | 3197 | 0403403005 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Casile | 14.3426 | 121.0895 | R | 4648 | 1408 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02024-C08 | PTCI/MIDC | 14.3376 | 121.0953 | 0.83 | Terrestrial Optical Fiber Drop | 1.55 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3198 | 4 | 198 | 3198 | 0702211028 | Region VII (Central Visayas) | Cebu | City of Bogo | Taytayan | 11.0433 | 123.9909 | R | 4892 | 1287 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070038 | FTAP BTS | 11.0402 | 123.9908 | 0.34 | Terrestrial Optical Fiber Drop | 1.87 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3199 | 4 | 199 | 3199 | 0105543023 | Region I (Ilocos Region) | Pangasinan | Tayug | Trenchera | 16.0246 | 120.7555 | R | 4345 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01767-B07 | PTCI/MIDC | 16.0297 | 120.7499 | 0.82 | Terrestrial Optical Fiber Drop | 1.01 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3200 | 4 | 200 | 3200 | 0704610004 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Banilad | 9.2774 | 123.2877 | U | 10062 | 2647 | 794 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 0.28 | Terrestrial Optical Fiber Drop | 2.76 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3201 | 4 | 201 | 3201 | 1401105002 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Amgaleyguey | 16.7362 | 120.8065 | R | 3224 | 921 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140171 | FTAP Globe | 16.7237 | 120.784 | 2.76 | Terrestrial Optical Fiber Drop | 2.87 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3202 | 4 | 202 | 3202 | 0405804022 | Region IV-A (CALABARZON) | Rizal | Binangonan | Lunsad | 14.4621 | 121.1955 | U | 11246 | 3123 | 937 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00811-A04 | PTCI/MIDC | 14.4618 | 121.195 | 0.07 | Terrestrial Optical Fiber Drop | 1.57 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3203 | 4 | 203 | 3203 | 0300803016 | Region III (Central Luzon) | Bataan | City of Balanga | San Jose | 14.6752 | 120.5385 | U | 7018 | 1949 | 585 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00891-B07 | PTCI/MIDC | 14.6774 | 120.5403 | 0.31 | Terrestrial Optical Fiber Drop | 1.07 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3204 | 4 | 204 | 3204 | 1130700143 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 10-A | 7.0791 | 125.6065 | U | 8186 | 2407 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0145 | PTCI/MIDC | 7.082 | 125.6079 | 0.36 | Terrestrial Optical Fiber Drop | 1.4 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3205 | 4 | 205 | 3205 | 0630200059 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Villamonte | 10.6778 | 122.9759 | U | 36386 | 10107 | 3032 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0020 | PTCI/MIDC | 10.6724 | 122.9627 | 0.28 | Terrestrial Optical Fiber Drop | 2.85 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3206 | 4 | 206 | 3206 | 0603007029 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Tubungan | 10.8869 | 122.7113 | R | 1745 | 459 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 1.36 | Terrestrial Optical Fiber Drop | 1.42 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3207 | 4 | 207 | 3207 | 0402111012 | Region IV-A (CALABARZON) | Cavite | Kawit | Wakas I | 14.4441 | 120.899 | R | 2023 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040103 | FTAP Globe | 14.4337 | 120.9016 | 0.73 | Terrestrial Optical Fiber Drop | 2.37 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3208 | 4 | 208 | 3208 | 0301408009 | Region III (Central Luzon) | Bulacan | Guiguinto | Santa Cruz | 14.8398 | 120.8679 | U | 12270 | 3505 | 1052 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01144 | Edgepoint | 14.8392 | 120.8702 | 0.26 | Terrestrial Optical Fiber Drop | 1.33 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3209 | 4 | 209 | 3209 | 0304926033 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Sibut | 15.7894 | 120.9978 | U | 7055 | 2015 | 605 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030316 | FTAP Globe | 15.7882 | 120.9994 | 0.22 | Terrestrial Optical Fiber Drop | 1.22 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3210 | 4 | 210 | 3210 | 0304928034 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Santa Teresita | 15.4343 | 120.9377 | R | 1895 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3532 | FTAP Smart | 15.4266 | 120.9483 | 0.7 | Terrestrial Optical Fiber Drop | 1.26 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3211 | 4 | 211 | 3211 | 0402118013 | Region IV-A (CALABARZON) | Cavite | Silang | Carmen | 14.2276 | 121.0346 | R | 3379 | 993 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02213-C08 | PTCI/MIDC | 14.222 | 121.0357 | 0.63 | Terrestrial Optical Fiber Drop | 3.33 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3212 | 4 | 212 | 3212 | 0307113023 | Region III (Central Luzon) | Zambales | Santa Cruz | San Fernando | 15.7576 | 119.9165 | R | 2723 | 716 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0008 | PTCI/MIDC | 15.7531 | 119.9154 | 0.51 | Terrestrial Optical Fiber Drop | 1.37 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3213 | 4 | 213 | 3213 | 0501701024 | Region V (Bicol Region) | Camarines Sur | Baao | San Vicente | 13.4575 | 123.3829 | R | 4553 | 1084 | 325 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03073-C10 | PTCI/MIDC | 13.4562 | 123.3823 | 0.16 | Terrestrial Optical Fiber Drop | 1.95 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3214 | 4 | 214 | 3214 | 0631000004 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Airport | 10.7051 | 122.5625 | U | 5022 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02811-D13 | PTCI/MIDC | 10.7107 | 122.5574 | 0.74 | Terrestrial Optical Fiber Drop | 1.14 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3215 | 4 | 215 | 3215 | 0702212002 | Region VII (Central Visayas) | Cebu | Boljoon | El Pardo | 9.6665 | 123.4916 | R | 3562 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 9.66 | Terrestrial Optical Fiber Drop | 4.94 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3216 | 4 | 216 | 3216 | 0305409013 | Region III (Central Luzon) | Pampanga | Mabalacat City | Macapagal Village | 15.2108 | 120.5376 | R | 4458 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | U43 | FTAP Smart | 15.1922 | 120.5322 | 2.15 | Terrestrial Optical Fiber Drop | 3.2 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3217 | 4 | 217 | 3217 | 0300805003 | Region III (Central Luzon) | Bataan | Hermosa | Bacong | 14.8527 | 120.4375 | R | 3256 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-02573 | Edgepoint | 14.8612 | 120.4383 | 0.95 | Terrestrial Optical Fiber Drop | 2.6 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3218 | 4 | 218 | 3218 | 0203101029 | Region II (Cagayan Valley) | Isabela | Alicia | Santa Cruz | 16.7717 | 121.704 | R | 2438 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTISG0056 | PTCI/MIDC | 16.7831 | 121.702 | 1.28 | Terrestrial Optical Fiber Drop | 1.85 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3219 | 4 | 219 | 3219 | 0501708023 | Region V (Bicol Region) | Camarines Sur | Calabanga | Pagatpat | 13.703 | 123.2179 | R | 1848 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050061 | FTAP Globe | 13.7087 | 123.2167 | 0.65 | Terrestrial Optical Fiber Drop | 1.03 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3220 | 4 | 220 | 3220 | 0405811006 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan II | 14.6923 | 121.12 | U | 18821 | 5228 | 1568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0059 | PTCI/MIDC | 14.6858 | 121.1272 | 0.08 | Terrestrial Optical Fiber Drop | 0.73 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3221 | 4 | 221 | 3221 | 0631000114 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Nabitasan | 10.7049 | 122.5623 | R | 3396 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILO_0002 | LDIC | 10.701 | 122.5616 | 0.44 | Terrestrial Optical Fiber Drop | 1.17 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3222 | 4 | 222 | 3222 | 0403406016 | Region IV-A (CALABARZON) | Laguna | Calauan | San Isidro | 14.1555 | 121.3158 | R | 3915 | 1186 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02102-C08 | PTCI/MIDC | 14.1591 | 121.3135 | 0.47 | Terrestrial Optical Fiber Drop | 1.08 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3223 | 4 | 223 | 3223 | 1030900025 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Tambacan | 8.2202 | 124.2354 | U | 19527 | 5138 | 1541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0008 | PTCI/MIDC | 8.2236 | 124.234 | 0.41 | Terrestrial Optical Fiber Drop | 1.06 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3224 | 4 | 224 | 3224 | 0631000009 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Bakhaw | 10.7183 | 122.5545 | U | 6778 | 1613 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02811-D13 | PTCI/MIDC | 10.7107 | 122.5574 | 0.9 | Terrestrial Optical Fiber Drop | 1.55 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3225 | 4 | 225 | 3225 | 0405601003 | Region IV-A (CALABARZON) | Quezon | Agdangan | Ibabang Kinagunan | 13.8603 | 121.9373 | R | 1397 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 1.72 | Terrestrial Optical Fiber Drop | 2.8 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3226 | 4 | 226 | 3226 | 0907322042 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Santa Lucia | 7.8205 | 123.4334 | U | 6138 | 1573 | 472 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0013 | PTCI/MIDC | 7.8221 | 123.4304 | 0.38 | Terrestrial Optical Fiber Drop | 1.31 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3227 | 4 | 227 | 3227 | 0631000175 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Tabuc Suba | 10.7333 | 122.5544 | U | 11248 | 2678 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0038 | PTCI/MIDC | 10.7327 | 122.5502 | 0.47 | Terrestrial Optical Fiber Drop | 1.91 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3228 | 4 | 228 | 3228 | 0304903090 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Aduas Norte | 15.5002 | 120.9708 | U | 6273 | 1792 | 538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03202 | Edgepoint | 15.5009 | 120.9654 | 0.59 | Terrestrial Optical Fiber Drop | 2.31 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3229 | 4 | 229 | 3229 | 0803738101 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Tambulilid | 11.0237 | 124.584 | U | 11704 | 3080 | 924 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0047 | PTCI/MIDC | 11.0196 | 124.5872 | 0.56 | Terrestrial Optical Fiber Drop | 1.67 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3230 | 4 | 230 | 3230 | 0307114022 | Region III (Central Luzon) | Zambales | Subic | Santo Tomas | 14.8572 | 120.2561 | U | 5691 | 1497 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-01109 | Edgepoint | 14.8567 | 120.2486 | 0.81 | Terrestrial Optical Fiber Drop | 1.84 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3231 | 4 | 231 | 3231 | 0702234013 | Region VII (Central Visayas) | Cebu | City of Naga | Lanas | 10.2734 | 123.7191 | R | 3344 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 2.77 | Terrestrial Optical Fiber Drop | 2.19 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3232 | 4 | 232 | 3232 | 0304916023 | Region III (Central Luzon) | Nueva Ecija | Lupao | Poblacion West | 15.8766 | 120.8935 | R | 1512 | 432 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 0.67 | Terrestrial Optical Fiber Drop | 1.03 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3233 | 4 | 233 | 3233 | 0730600049 | Region VII (Central Visayas) | Cebu | City of Cebu | Mambaling | 10.2878 | 123.8818 | U | 30496 | 9530 | 2859 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0026 | PTCI/MIDC | 10.2919 | 123.8848 | 0.56 | Terrestrial Optical Fiber Drop | 2.37 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3234 | 4 | 234 | 3234 | 0931700087 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Tetuan | 6.9189 | 122.0849 | U | 30882 | 8578 | 2573 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0107 | PTCI/MIDC | 6.9162 | 122.0832 | 0.36 | Terrestrial Optical Fiber Drop | 1.56 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3235 | 4 | 235 | 3235 | 0105518018 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Malued | 16.0291 | 120.3349 | U | 9339 | 2594 | 778 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00443 | Edgepoint | 16.0274 | 120.3367 | 0.27 | Terrestrial Optical Fiber Drop | 1.04 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3236 | 4 | 236 | 3236 | 0105517020 | Region I (Ilocos Region) | Pangasinan | Calasiao | Quesban | 16.0125 | 120.3728 | R | 3217 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010159 | FTAP Globe | 16.0185 | 120.3743 | 0.69 | Terrestrial Optical Fiber Drop | 1.6 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3237 | 4 | 237 | 3237 | 0500514023 | Region V (Bicol Region) | Albay | Polangui | Kinale | 13.292 | 123.4685 | R | 2709 | 660 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ALB-02561 | Edgepoint | 13.2932 | 123.4678 | 0.15 | Terrestrial Optical Fiber Drop | 1.61 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3238 | 4 | 238 | 3238 | 0405804041 | Region IV-A (CALABARZON) | Rizal | Binangonan | San Carlos | 14.5153 | 121.1692 | U | 13488 | 3746 | 1124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0120 | PTCI/MIDC | 14.5179 | 121.1678 | 0.32 | Terrestrial Optical Fiber Drop | 2.06 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3239 | 4 | 239 | 3239 | 1230800011 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Lagao | 6.1313 | 125.185 | U | 55612 | 14259 | 4278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0018 | PTCI/MIDC | 6.1321 | 125.1886 | 0.41 | Terrestrial Optical Fiber Drop | 1.72 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3240 | 4 | 240 | 3240 | 1430300004 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Bakakeng Central | 16.3974 | 120.575 | U | 13166 | 3464 | 1039 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0052 | LDIC | 16.4013 | 120.5766 | 0.47 | Terrestrial Optical Fiber Drop | 1.64 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3241 | 4 | 241 | 3241 | 0603037027 | Region VI (Western Visayas) | Iloilo | Pototan | Jamabalud | 10.8896 | 122.6171 | R | 3095 | 814 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060022 | FTAP BTS | 10.8772 | 122.6131 | 1.44 | Terrestrial Optical Fiber Drop | 2.41 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3242 | 4 | 242 | 3242 | 1030500040 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bonbon | 8.508 | 124.6485 | U | 11175 | 3104 | 931 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100136 | FTAP Globe | 8.5063 | 124.6472 | 0.24 | Terrestrial Optical Fiber Drop | 1.38 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3243 | 4 | 243 | 3243 | 0300801011 | Region III (Central Luzon) | Bataan | Abucay | Wawa | 14.7214 | 120.5415 | R | 4432 | 1231 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-03190 | Edgepoint | 14.7182 | 120.5368 | 0.62 | Terrestrial Optical Fiber Drop | 4.08 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3244 | 4 | 244 | 3244 | 0403403025 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Tubigan | 14.3288 | 121.07 | U | 6848 | 2075 | 623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0035 | PTCI/MIDC | 14.3307 | 121.078 | 0.89 | Terrestrial Optical Fiber Drop | 1.25 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3245 | 4 | 245 | 3245 | 0201504014 | Region II (Cagayan Valley) | Cagayan | Amulung | Calamagui | 17.846 | 121.7284 | R | 1832 | 469 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01178-B06 | PTCI/MIDC | 17.8338 | 121.7241 | 1.44 | Terrestrial Optical Fiber Drop | 1.13 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3246 | 4 | 246 | 3246 | 0307102020 | Region III (Central Luzon) | Zambales | Cabangan | San Juan | 15.1557 | 120.0607 | R | 1752 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ZMB-00841 | Edgepoint | 15.1496 | 120.0483 | 1.49 | Terrestrial Optical Fiber Drop | 1.01 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3247 | 4 | 247 | 3247 | 0203135026 | Region II (Cagayan Valley) | Isabela | City of Santiago | Rosario | 16.6799 | 121.5457 | U | 12845 | 3380 | 1014 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02685-B06 | PTCI/MIDC | 16.6788 | 121.5438 | 0.24 | Terrestrial Optical Fiber Drop | 2.39 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3248 | 4 | 248 | 3248 | 0105511010 | Region I (Ilocos Region) | Pangasinan | Bayambang | Bacnono | 15.8241 | 120.4627 | R | 2315 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0003 | LDIC | 15.8219 | 120.4585 | 0.51 | Terrestrial Optical Fiber Drop | 1.2 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3249 | 4 | 249 | 3249 | 0205013011 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Quezon | 16.5167 | 121.1733 | U | 6052 | 1592 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0020 | PTCI/MIDC | 16.5206 | 121.1751 | 0.47 | Terrestrial Optical Fiber Drop | 1.27 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3250 | 4 | 250 | 3250 | 0300809012 | Region III (Central Luzon) | Bataan | Orani | Palihan | 14.8014 | 120.519 | R | 2633 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030111 | FTAP BTS | 14.7936 | 120.5218 | 0.38 | Terrestrial Optical Fiber Drop | 1.87 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3251 | 4 | 251 | 3251 | 0402115032 | Region IV-A (CALABARZON) | Cavite | Naic | Timalan Concepcion | 14.337 | 120.7792 | R | 4804 | 1412 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02145-C08 | PTCI/MIDC | 14.3426 | 120.7815 | 0.67 | Terrestrial Optical Fiber Drop | 1.89 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3252 | 4 | 252 | 3252 | 0402103013 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog I | 14.4231 | 120.9578 | U | 12980 | 3817 | 1145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01919-C08 | PTCI/MIDC | 14.4412 | 120.9522 | 0.54 | Terrestrial Optical Fiber Drop | 0.88 | 2.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3253 | 4 | 253 | 3253 | 0702219007 | Region VII (Central Visayas) | Cebu | Consolacion | Lamac | 10.3857 | 123.9651 | U | 11475 | 3019 | 906 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070325 | FTAP Globe | 10.3879 | 123.9644 | 0.26 | Terrestrial Optical Fiber Drop | 1.23 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3254 | 4 | 254 | 3254 | 1102319026 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo West | 7.4475 | 125.8018 | U | 13141 | 3551 | 1065 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0026 | PTCI/MIDC | 7.4333 | 125.7875 | 0.45 | Terrestrial Optical Fiber Drop | 2.51 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3255 | 4 | 255 | 3255 | 0301411015 | Region III (Central Luzon) | Bulacan | Marilao | Saog | 14.7647 | 120.9558 | U | 16319 | 4662 | 1399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01219 | Edgepoint | 14.7628 | 120.9552 | 0.22 | Terrestrial Optical Fiber Drop | 1.67 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3256 | 4 | 256 | 3256 | 0301406011 | Region III (Central Luzon) | Bulacan | Bustos | San Pedro | 14.9491 | 120.9083 | U | 8480 | 2422 | 727 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBUG0064 | PTCI/MIDC | 14.9473 | 120.9142 | 0.66 | Terrestrial Optical Fiber Drop | 1.13 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3257 | 4 | 257 | 3257 | 0304916028 | Region III (Central Luzon) | Nueva Ecija | Lupao | San Antonio Este | 15.8694 | 120.8963 | R | 2386 | 681 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 1.23 | Terrestrial Optical Fiber Drop | 1.72 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3258 | 4 | 258 | 3258 | 0105522018 | Region I (Ilocos Region) | Pangasinan | Lingayen | Libsong West | 16.03 | 120.2406 | U | 5327 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N5459 | FTAP Smart | 16.0272 | 120.2381 | 0.41 | Terrestrial Optical Fiber Drop | 1.15 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3259 | 4 | 259 | 3259 | 0604524010 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay I | 10.4937 | 123.4281 | U | 11121 | 3005 | 902 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02860-D13 | PTCI/MIDC | 10.4865 | 123.4234 | 0.96 | Terrestrial Optical Fiber Drop | 1.81 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3260 | 4 | 260 | 3260 | 0631000023 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Bonifacio | 10.7046 | 122.5623 | R | 2064 | 491 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060267 | FTAP Globe | 10.7314 | 122.5613 | 0.49 | Terrestrial Optical Fiber Drop | 1.2 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3261 | 4 | 261 | 3261 | 0501721006 | Region V (Bicol Region) | Camarines Sur | Milaor | Capucnasan | 13.6071 | 123.2199 | R | 3393 | 807 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03172 | Edgepoint | 13.6103 | 123.2128 | 0.84 | Terrestrial Optical Fiber Drop | 3.08 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3262 | 4 | 262 | 3262 | 0702250022 | Region VII (Central Visayas) | Cebu | City of Talisay | Lawaan III | 10.2651 | 123.8286 | U | 14739 | 3878 | 1163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 1.69 | Terrestrial Optical Fiber Drop | 1.37 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3263 | 4 | 263 | 3263 | 1004308001 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Agay-ayan | 8.8622 | 125.0569 | R | 4500 | 1153 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0049 | PTCI/MIDC | 8.8468 | 125.0566 | 1.72 | Terrestrial Optical Fiber Drop | 6.62 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3264 | 4 | 264 | 3264 | 1102502002 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Caganganan | 6.9441 | 126.0174 | R | 2385 | 662 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDLG0042 | PTCI/MIDC | 6.9472 | 126.0115 | 0.74 | Terrestrial Optical Fiber Drop | 2.18 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3265 | 4 | 265 | 3265 | 0304903017 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Bonifacio District | 15.4903 | 120.9702 | R | 3315 | 947 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02544 | Edgepoint | 15.499 | 120.9766 | 0.93 | Terrestrial Optical Fiber Drop | 1.36 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3266 | 4 | 266 | 3266 | 0403419011 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Pinagsanjan | 14.2671 | 121.4577 | U | 5628 | 1705 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02115-C08 | PTCI/MIDC | 14.2703 | 121.4567 | 0.37 | Terrestrial Optical Fiber Drop | 1.08 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3267 | 4 | 267 | 3267 | 0702232019 | Region VII (Central Visayas) | Cebu | Minglanilla | Tungkil | 10.2407 | 123.8124 | U | 13904 | 3658 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0127 | PTCI/MIDC | 10.2405 | 123.8149 | 0.28 | Terrestrial Optical Fiber Drop | 1.57 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3268 | 4 | 268 | 3268 | 0908305003 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Bulu-an | 7.716 | 122.5202 | R | 3966 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZYG0023 | PTCI/MIDC | 7.7081 | 122.5193 | 0.89 | Terrestrial Optical Fiber Drop | 9.98 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3269 | 4 | 269 | 3269 | 0704610015 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Looc | 9.3136 | 123.3102 | U | 4230 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0064 | PTCI/MIDC | 9.3099 | 123.3075 | 0.5 | Terrestrial Optical Fiber Drop | 1.1 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3270 | 4 | 270 | 3270 | 0203107021 | Region II (Cagayan Valley) | Isabela | Cabatuan | Saranay | 16.9574 | 121.6753 | R | 4092 | 1076 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020073 | FTAP Globe | 16.9514 | 121.6787 | 0.76 | Terrestrial Optical Fiber Drop | 4.37 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3271 | 4 | 271 | 3271 | 0305411011 | Region III (Central Luzon) | Pampanga | Magalang | San Jose | 15.1868 | 120.6406 | U | 3780 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4917 | FTAP Smart | 15.1896 | 120.642 | 0.34 | Terrestrial Optical Fiber Drop | 1.53 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3272 | 4 | 272 | 3272 | 0405628008 | Region IV-A (CALABARZON) | Quezon | Mulanay | Barangay 2 | 13.5239 | 122.4061 | R | 3381 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-03181 | Edgepoint | 13.5248 | 122.4031 | 0.34 | Terrestrial Optical Fiber Drop | 1.25 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3273 | 4 | 273 | 3273 | 0331400013 | Region III (Central Luzon) | Zambales | City of Olongapo | Mabayuan | 14.8467 | 120.284 | U | 12655 | 3420 | 1026 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030582 | FTAP Globe | 14.8478 | 120.2848 | 0.15 | Terrestrial Optical Fiber Drop | 1.49 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3274 | 4 | 274 | 3274 | 1030900035 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Santiago | 8.2466 | 124.2442 | U | 9339 | 2457 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0012 | PTCI/MIDC | 8.2524 | 124.248 | 0.76 | Terrestrial Optical Fiber Drop | 2.07 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3275 | 4 | 275 | 3275 | 1401114006 | Cordillera Administrative Region (CAR) | Benguet | Tublay | Caponga | 16.4883 | 120.6348 | U | 5362 | 1532 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02312-B05 | PTCI/MIDC | 16.4768 | 120.6329 | 1.29 | Terrestrial Optical Fiber Drop | 1.23 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3276 | 4 | 276 | 3276 | 0105524072 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Tambac | 15.8893 | 120.4486 | R | 3350 | 930 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00543 | Edgepoint | 15.8962 | 120.4263 | 0.77 | Terrestrial Optical Fiber Drop | 5.17 | 1.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3277 | 4 | 277 | 3277 | 0205005017 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | District IV | 16.4793 | 121.1471 | U | 4110 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020118 | FTAP Globe | 16.4833 | 121.1339 | 0.69 | Terrestrial Optical Fiber Drop | 0.93 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3278 | 4 | 278 | 3278 | 0305416029 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Juan | 15.0192 | 120.6806 | U | 6061 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00930 | Edgepoint | 15.0243 | 120.6836 | 0.65 | Terrestrial Optical Fiber Drop | 2.26 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3279 | 4 | 279 | 3279 | 0305416002 | Region III (Central Luzon) | Pampanga | City of San Fernando | Baliti | 15.1077 | 120.6227 | U | 7315 | 1828 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01547-B07 | PTCI/MIDC | 15.1025 | 120.6256 | 0.66 | Terrestrial Optical Fiber Drop | 1.53 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3280 | 4 | 280 | 3280 | 0105533023 | Region I (Ilocos Region) | Pangasinan | San Fabian | Sobol | 16.1329 | 120.4039 | R | 2885 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 0.61 | Terrestrial Optical Fiber Drop | 1.95 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3281 | 4 | 281 | 3281 | 1206511019 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | San Pablo | 6.6982 | 124.687 | U | 13266 | 3491 | 1047 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120136 | FTAP BTS | 6.7016 | 124.6881 | 0.39 | Terrestrial Optical Fiber Drop | 1.77 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3282 | 4 | 282 | 3282 | 0403425017 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Santo Niño | 14.3678 | 121.0593 | R | 4266 | 1292 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4284 | FTAP Smart | 14.364 | 121.0585 | 0.43 | Terrestrial Optical Fiber Drop | 2.09 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3283 | 4 | 283 | 3283 | 0301410029 | Region III (Central Luzon) | Bulacan | City of Malolos | Mabolo | 14.8422 | 120.8259 | U | 6565 | 1875 | 563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01147 | Edgepoint | 14.837 | 120.8261 | 0.58 | Terrestrial Optical Fiber Drop | 1.48 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3284 | 4 | 284 | 3284 | 0301404010 | Region III (Central Luzon) | Bulacan | Bocaue | Caingin | 14.8075 | 120.9385 | R | 5031 | 1437 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01186 | Edgepoint | 14.7982 | 120.93 | 0.67 | Terrestrial Optical Fiber Drop | 2.03 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3285 | 4 | 285 | 3285 | 0403405056 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Sirang Lupa | 14.2027 | 121.1062 | U | 14182 | 4297 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03060-C08 | PTCI/MIDC | 14.2044 | 121.1082 | 0.28 | Terrestrial Optical Fiber Drop | 2.01 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3286 | 4 | 286 | 3286 | 0203103026 | Region II (Cagayan Valley) | Isabela | Aurora | Santa Rita | 16.9927 | 121.6421 | R | 1605 | 422 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00207 | Edgepoint | 16.9916 | 121.6425 | 0.13 | Terrestrial Optical Fiber Drop | 1.11 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3287 | 4 | 287 | 3287 | 0304928025 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Del Pilar | 15.4344 | 120.9381 | R | 1481 | 423 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3532 | FTAP Smart | 15.4266 | 120.9483 | 0.82 | Terrestrial Optical Fiber Drop | 1.3 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3288 | 4 | 288 | 3288 | 0405802010 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mambugan | 14.6184 | 121.1358 | U | 52920 | 14700 | 4410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040024 | FTAP Globe | 14.6196 | 121.1348 | 0.17 | Terrestrial Optical Fiber Drop | 1.82 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3289 | 4 | 289 | 3289 | 0403413016 | Region IV-A (CALABARZON) | Laguna | Lumban | Wawa | 14.3047 | 121.4596 | R | 4477 | 1356 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.57 | Terrestrial Optical Fiber Drop | 1.03 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3290 | 4 | 290 | 3290 | 1004321006 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Igpit | 8.5035 | 124.5854 | U | 13322 | 3415 | 1025 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100135 | FTAP Globe | 8.5116 | 124.5869 | 0.92 | Terrestrial Optical Fiber Drop | 2.21 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3291 | 4 | 291 | 3291 | 0500506074 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 58 - Buragwis | 13.1362 | 123.7538 | R | 4500 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050178 | FTAP Globe | 13.14 | 123.7567 | 0.53 | Terrestrial Optical Fiber Drop | 1.59 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3292 | 4 | 292 | 3292 | 0306916085 | Region III (Central Luzon) | Tarlac | City of Tarlac | Suizo | 15.4643 | 120.6052 | R | 4138 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030044 | FTAP BTS | 15.4624 | 120.6117 | 0.73 | Terrestrial Optical Fiber Drop | 1.99 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3293 | 4 | 293 | 3293 | 0307109002 | Region III (Central Luzon) | Zambales | San Antonio | Antipolo | 14.9494 | 120.0883 | R | 2034 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 1.07 | Terrestrial Optical Fiber Drop | 0.24 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3294 | 4 | 294 | 3294 | 0803719002 | Region VIII (Eastern Visayas) | Leyte | Hilongos | Atabay | 10.3744 | 124.7435 | R | 4031 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080128 | FTAP BTS | 10.3801 | 124.7384 | 0.84 | Terrestrial Optical Fiber Drop | 26.16 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3295 | 4 | 295 | 3295 | 1108204011 | Region XI (Davao Region) | Davao de Oro | Maco | Hijo | 7.3717 | 125.8363 | R | 4308 | 1164 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110429 | FTAP Globe | 7.3773 | 125.8398 | 0.74 | Terrestrial Optical Fiber Drop | 2.75 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3296 | 4 | 296 | 3296 | 0401005020 | Region IV-A (CALABARZON) | Batangas | Batangas City | Cuta | 13.7511 | 121.055 | U | 14489 | 4024 | 1207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01965-C08 | PTCI/MIDC | 13.7494 | 121.0548 | 0.19 | Terrestrial Optical Fiber Drop | 1.26 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3297 | 4 | 297 | 3297 | 0105518017 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Lucao | 16.0138 | 120.3231 | U | 10234 | 2842 | 853 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00459 | Edgepoint | 16.0141 | 120.313 | 1.08 | Terrestrial Optical Fiber Drop | 1.1 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3298 | 4 | 298 | 3298 | 0306902012 | Region III (Central Luzon) | Tarlac | Bamban | San Rafael | 15.3227 | 120.5965 | R | 3031 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00764 | Edgepoint | 15.3185 | 120.5833 | 1.49 | Terrestrial Optical Fiber Drop | 2.71 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3299 | 4 | 299 | 3299 | 0301412023 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Tugatog | 14.7239 | 120.9666 | U | 5072 | 1449 | 435 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02506-A01 | PTCI/MIDC | 14.7208 | 120.9665 | 0.34 | Terrestrial Optical Fiber Drop | 1.61 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3300 | 4 | 300 | 3300 | 0601914045 | Region VI (Western Visayas) | Capiz | City of Roxas | Sibaguan | 11.5512 | 122.7201 | R | 4020 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0020 | PTCI/MIDC | 11.5548 | 122.7158 | 0.61 | Terrestrial Optical Fiber Drop | 4.4 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3301 | 4 | 301 | 3301 | 1004324002 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Casinglot | 8.5184 | 124.7525 | U | 10539 | 2702 | 811 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100131 | FTAP Globe | 8.5245 | 124.7608 | 1.14 | Terrestrial Optical Fiber Drop | 2.18 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3302 | 4 | 302 | 3302 | 1600203010 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Calamba | 9.1168 | 125.5333 | R | 3001 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 1.41 | Terrestrial Optical Fiber Drop | 1.33 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3303 | 4 | 303 | 3303 | 0307104008 | Region III (Central Luzon) | Zambales | Castillejos | San Agustin | 14.9334 | 120.1914 | R | 5062 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02717 | Edgepoint | 14.9397 | 120.1927 | 0.71 | Terrestrial Optical Fiber Drop | 1.08 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3304 | 4 | 304 | 3304 | 0803750007 | Region VIII (Eastern Visayas) | Leyte | Tunga | San Vicente | 11.2519 | 124.7559 | R | 878 | 231 | 69 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 0.92 | Terrestrial Optical Fiber Drop | 1.08 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3305 | 4 | 305 | 3305 | 0401019039 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Pantalan | 14.0832 | 120.6342 | R | 3962 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4166 | FTAP Smart | 14.0788 | 120.6298 | 0.68 | Terrestrial Optical Fiber Drop | 1.39 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3306 | 4 | 306 | 3306 | 1606807010 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Gamuton | 9.3577 | 125.9356 | R | 2898 | 706 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130055 | FTAP Globe | 9.3679 | 125.9511 | 2.05 | Terrestrial Optical Fiber Drop | 1.83 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3307 | 4 | 307 | 3307 | 1004324009 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Santa Cruz | 8.5461 | 124.7689 | U | 16544 | 4242 | 1273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0103 | PTCI/MIDC | 8.5516 | 124.7655 | 0.71 | Terrestrial Optical Fiber Drop | 1.98 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3308 | 4 | 308 | 3308 | 0301410034 | Region III (Central Luzon) | Bulacan | City of Malolos | Mojon | 14.8576 | 120.8175 | U | 16901 | 4828 | 1448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03204-B07 | PTCI/MIDC | 14.8685 | 120.8136 | 0.28 | Terrestrial Optical Fiber Drop | 0.27 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3309 | 4 | 309 | 3309 | 1600203018 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | La Union | 9.1167 | 125.5333 | U | 7717 | 1882 | 565 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 1.41 | Terrestrial Optical Fiber Drop | 1.33 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3310 | 4 | 310 | 3310 | 0330100029 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Rosario | 15.1372 | 120.5901 | U | 6094 | 1692 | 508 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02685 | Edgepoint | 15.1624 | 120.5704 | 0.35 | Terrestrial Optical Fiber Drop | 0.97 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3311 | 4 | 311 | 3311 | 0203108070 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Turayong | 16.9405 | 121.7759 | U | 3465 | 911 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0023 | PTCI/MIDC | 16.9378 | 121.7763 | 0.31 | Terrestrial Optical Fiber Drop | 1.24 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3312 | 4 | 312 | 3312 | 1001314020 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Santiago | 8.3684 | 124.8628 | R | 1756 | 462 | 139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 1.51 | Terrestrial Optical Fiber Drop | 1.95 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3313 | 4 | 313 | 3313 | 1630400049 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Kinamlutan | 8.9162 | 125.5234 | R | 3815 | 930 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0003 | PTCI/MIDC | 8.9158 | 125.542 | 2.04 | Terrestrial Optical Fiber Drop | 3.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3314 | 4 | 314 | 3314 | 0300803018 | Region III (Central Luzon) | Bataan | City of Balanga | Camacho | 14.682 | 120.5274 | R | 4015 | 1115 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02389-B07 | PTCI/MIDC | 14.6763 | 120.5278 | 0.64 | Terrestrial Optical Fiber Drop | 1.37 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3315 | 4 | 315 | 3315 | 0300803008 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang Proper | 14.6684 | 120.5436 | U | 12098 | 3360 | 1008 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01437 | Edgepoint | 14.6683 | 120.5477 | 0.45 | Terrestrial Optical Fiber Drop | 1.71 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3316 | 4 | 316 | 3316 | 1401110004 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Bahong | 16.4682 | 120.6077 | U | 6156 | 1758 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1846 | FTAP Smart | 16.461 | 120.6138 | 1.03 | Terrestrial Optical Fiber Drop | 1.07 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3317 | 4 | 317 | 3317 | 0403410021 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Taykin | 14.1431 | 121.4387 | R | 3268 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02121-C08 | PTCI/MIDC | 14.1337 | 121.4379 | 1.1 | Terrestrial Optical Fiber Drop | 0.81 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3318 | 4 | 318 | 3318 | 0401013015 | Region IV-A (CALABARZON) | Batangas | Lian | Matabungkay | 13.9508 | 120.6262 | U | 5558 | 1543 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01953-C08 | PTCI/MIDC | 13.9499 | 120.627 | 0.13 | Terrestrial Optical Fiber Drop | 1.6 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3319 | 4 | 319 | 3319 | 0630200026 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 3 | 10.6833 | 122.9537 | R | 3010 | 836 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0104 | PTCI/MIDC | 10.6304 | 122.942 | 0.76 | Terrestrial Optical Fiber Drop | 1.84 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3320 | 4 | 320 | 3320 | 0601915009 | Region VI (Western Visayas) | Capiz | Sapi-An | Maninang | 11.4782 | 122.5881 | R | 3032 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060232 | FTAP Globe | 11.4829 | 122.5847 | 0.64 | Terrestrial Optical Fiber Drop | 2.59 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3321 | 4 | 321 | 3321 | 1600201002 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Agong-ong | 8.9766 | 125.4092 | R | 1680 | 409 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0002 | PTCI/MIDC | 8.9795 | 125.4097 | 0.32 | Terrestrial Optical Fiber Drop | 1.13 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3322 | 4 | 322 | 3322 | 0403426002 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Bagumbayan | 14.2684 | 121.4 | U | 14649 | 4439 | 1332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040201 | FTAP Globe | 14.2743 | 121.4075 | 1.04 | Terrestrial Optical Fiber Drop | 1.85 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3323 | 4 | 323 | 3323 | 0601911011 | Region VI (Western Visayas) | Capiz | Pilar | Natividad | 11.4768 | 123.01 | R | 4818 | 1267 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCZG0007 | PTCI/MIDC | 11.491 | 123.0069 | 1.62 | Terrestrial Optical Fiber Drop | 8.7 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3324 | 4 | 324 | 3324 | 1102319025 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo South | 7.4486 | 125.8023 | U | 11757 | 3177 | 953 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0032 | PTCI/MIDC | 7.4506 | 125.8016 | 0.23 | Terrestrial Optical Fiber Drop | 2.39 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3325 | 4 | 325 | 3325 | 0203112066 | Region II (Cagayan Valley) | Isabela | Echague | Cabugao | 16.7042 | 121.6744 | R | 1913 | 503 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00275 | Edgepoint | 16.7034 | 121.6773 | 0.31 | Terrestrial Optical Fiber Drop | 1.1 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3326 | 4 | 326 | 3326 | 0704610018 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Piapi | 9.3217 | 123.3065 | U | 5042 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0059 | PTCI/MIDC | 9.3216 | 123.3084 | 0.21 | Terrestrial Optical Fiber Drop | 1.8 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3327 | 4 | 327 | 3327 | 0301406013 | Region III (Central Luzon) | Bulacan | Bustos | Tanawan | 14.9325 | 120.9278 | U | 2855 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-01022 | Edgepoint | 14.9338 | 120.9094 | 1.23 | Terrestrial Optical Fiber Drop | 1.28 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3328 | 4 | 328 | 3328 | 0501723016 | Region V (Bicol Region) | Camarines Sur | Nabua | Paloyon Proper | 13.3743 | 123.3785 | R | 3078 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050125 | FTAP Globe | 13.3818 | 123.3726 | 1.05 | Terrestrial Optical Fiber Drop | 2.24 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3329 | 4 | 329 | 3329 | 0105518026 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Pogo Grande | 16.0337 | 120.3383 | R | 2006 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00437 | Edgepoint | 16.0381 | 120.335 | 0.61 | Terrestrial Optical Fiber Drop | 1.66 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3330 | 4 | 330 | 3330 | 0330100035 | Region III (Central Luzon) | Pampanga | City of Angeles | Amsic | 15.16 | 120.5679 | U | 17705 | 4918 | 1475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02685 | Edgepoint | 15.1624 | 120.5704 | 0.38 | Terrestrial Optical Fiber Drop | 1 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3331 | 4 | 331 | 3331 | 0604526015 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Mambulac | 10.7974 | 122.9676 | U | 19466 | 5261 | 1578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060130 | FTAP BTS | 10.8015 | 122.9685 | 0.47 | Terrestrial Optical Fiber Drop | 1.17 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3332 | 4 | 332 | 3332 | 0501724006 | Region V (Bicol Region) | Camarines Sur | City of Naga | Calauag | 13.643 | 123.1912 | U | 11268 | 2682 | 805 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0835 | FTAP Smart | 13.6383 | 123.1859 | 0.77 | Terrestrial Optical Fiber Drop | 1.79 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3333 | 4 | 333 | 3333 | 0803738060 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Linao | 11.0157 | 124.5924 | U | 8425 | 2217 | 665 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0046 | PTCI/MIDC | 11.0183 | 124.5947 | 0.37 | Terrestrial Optical Fiber Drop | 1.01 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3334 | 4 | 334 | 3334 | 0500516004 | Region V (Bicol Region) | Albay | Santo Domingo | Fidel Surtida | 13.2452 | 123.7628 | R | 2657 | 648 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 1.04 | Terrestrial Optical Fiber Drop | 1.8 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3335 | 4 | 335 | 3335 | 0501736024 | Region V (Bicol Region) | Camarines Sur | Tigaon | Vinagre | 13.6289 | 123.5078 | R | 3031 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 1.7 | Terrestrial Optical Fiber Drop | 1.13 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3336 | 4 | 336 | 3336 | 0403425015 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Roque | 14.3665 | 121.0617 | U | 7850 | 2378 | 713 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4284 | FTAP Smart | 14.364 | 121.0585 | 0.44 | Terrestrial Optical Fiber Drop | 1.89 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3337 | 4 | 337 | 3337 | 0631000077 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Jereos | 10.7052 | 122.5621 | U | 3635 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060262 | FTAP Globe | 10.7625 | 122.5963 | 1.08 | Terrestrial Optical Fiber Drop | 1.15 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3338 | 4 | 338 | 3338 | 0501716021 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Nicolas | 13.4351 | 123.4196 | U | 11637 | 2770 | 831 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03385-C10 | PTCI/MIDC | 13.4376 | 123.4129 | 0.78 | Terrestrial Optical Fiber Drop | 1.66 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3339 | 4 | 339 | 3339 | 1600201009 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Malpoc | 8.9639 | 125.4036 | R | 2686 | 655 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 0.68 | Terrestrial Optical Fiber Drop | 1.56 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3340 | 4 | 340 | 3340 | 0306905027 | Region III (Central Luzon) | Tarlac | Concepcion | San Agustin | 15.4036 | 120.6079 | U | 7749 | 1986 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01783-B07 | PTCI/MIDC | 15.4118 | 120.604 | 1.01 | Terrestrial Optical Fiber Drop | 1.29 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3341 | 4 | 341 | 3341 | 0305403012 | Region III (Central Luzon) | Pampanga | Arayat | Lacquios | 15.1677 | 120.7734 | R | 3964 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00818 | Edgepoint | 15.1706 | 120.7679 | 0.67 | Terrestrial Optical Fiber Drop | 2.84 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3342 | 4 | 342 | 3342 | 0702232016 | Region VII (Central Visayas) | Cebu | Minglanilla | Tunghaan | 10.246 | 123.7786 | U | 16912 | 4450 | 1335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070362 | FTAP Globe | 10.2441 | 123.7824 | 0.46 | Terrestrial Optical Fiber Drop | 1.07 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3343 | 4 | 343 | 3343 | 0603005013 | Region VI (Western Visayas) | Iloilo | Balasan | Mamhut Norte | 11.4794 | 123.0938 | R | 1724 | 453 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.41 | Terrestrial Optical Fiber Drop | 1.04 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3344 | 4 | 344 | 3344 | 0500518007 | Region V (Bicol Region) | Albay | Tiwi | Cale | 13.4639 | 123.6536 | U | 6012 | 1466 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050115 | FTAP Globe | 13.4748 | 123.6707 | 2.2 | Terrestrial Optical Fiber Drop | 2.57 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3345 | 4 | 345 | 3345 | 1600308018 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 4 | 8.5045 | 125.9844 | U | 3397 | 871 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.85 | Terrestrial Optical Fiber Drop | 1.07 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3346 | 4 | 346 | 3346 | 0103314059 | Region I (Ilocos Region) | La Union | City of San Fernando | Tanqui | 16.6165 | 120.3239 | U | 5298 | 1431 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010091 | FTAP Globe | 16.6156 | 120.3296 | 0.61 | Terrestrial Optical Fiber Drop | 1.58 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3347 | 4 | 347 | 3347 | 0731300024 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tawason | 10.3784 | 123.9272 | U | 6991 | 1997 | 599 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070327 | FTAP Globe | 10.3761 | 123.9347 | 0.86 | Terrestrial Optical Fiber Drop | 1.27 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3348 | 4 | 348 | 3348 | 0105526004 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Banaoang | 16.0603 | 120.4092 | U | 5904 | 1640 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02521-B07 | PTCI/MIDC | 16.0657 | 120.4078 | 0.62 | Terrestrial Optical Fiber Drop | 1.12 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3349 | 4 | 349 | 3349 | 0501606016 | Region V (Bicol Region) | Camarines Norte | Labo | Bulhao | 14.162 | 122.8322 | R | 2387 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAN-01919 | Edgepoint | 14.1648 | 122.8187 | 1.49 | Terrestrial Optical Fiber Drop | 1.11 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3350 | 4 | 350 | 3350 | 0501606036 | Region V (Bicol Region) | Camarines Norte | Labo | Malasugui | 14.1543 | 122.8455 | R | 4044 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03390-C10 | PTCI/MIDC | 14.1462 | 122.844 | 0.92 | Terrestrial Optical Fiber Drop | 1.25 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3351 | 4 | 351 | 3351 | 0301404015 | Region III (Central Luzon) | Bulacan | Bocaue | Sulucan | 14.7902 | 120.9246 | R | 2919 | 834 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030608 | FTAP Globe | 14.7908 | 120.9227 | 0.22 | Terrestrial Optical Fiber Drop | 1.68 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3352 | 4 | 352 | 3352 | 0405802011 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Bagong Nayon | 14.6297 | 121.1677 | U | 47008 | 13057 | 3917 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00757-A04 | PTCI/MIDC | 14.6294 | 121.1697 | 0.22 | Terrestrial Optical Fiber Drop | 1.01 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3353 | 4 | 353 | 3353 | 0730600067 | Region VII (Central Visayas) | Cebu | City of Cebu | San Jose | 10.3798 | 123.9135 | U | 8037 | 2511 | 753 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070026 | FTAP BTS | 10.3825 | 123.9142 | 0.3 | Terrestrial Optical Fiber Drop | 1.27 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3354 | 4 | 354 | 3354 | 0603042004 | Region VI (Western Visayas) | Iloilo | San Rafael | Ilongbukid | 11.1747 | 122.8493 | R | 2094 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0069 | PTCI/MIDC | 11.1801 | 122.8301 | 2.18 | Terrestrial Optical Fiber Drop | 2.18 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3355 | 4 | 355 | 3355 | 0702214006 | Region VII (Central Visayas) | Cebu | City of Carcar | Liburon | 10.1155 | 123.6521 | U | 9454 | 2487 | 746 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070365 | FTAP Globe | 10.1181 | 123.6524 | 0.29 | Terrestrial Optical Fiber Drop | 2.19 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3356 | 4 | 356 | 3356 | 0702250004 | Region VII (Central Visayas) | Cebu | City of Talisay | Dumlog | 10.2405 | 123.8407 | U | 22196 | 5841 | 1752 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0228 | PTCI/MIDC | 10.2395 | 123.8406 | 0.11 | Terrestrial Optical Fiber Drop | 0.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3357 | 4 | 357 | 3357 | 0402111005 | Region IV-A (CALABARZON) | Cavite | Kawit | Panamitan | 14.4369 | 120.8931 | R | 3577 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040103 | FTAP Globe | 14.4337 | 120.9016 | 0.98 | Terrestrial Optical Fiber Drop | 1.36 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3358 | 4 | 358 | 3358 | 0704610009 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Calindagan | 9.2984 | 123.3105 | U | 6985 | 1838 | 551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0065 | PTCI/MIDC | 9.3046 | 123.3088 | 0.72 | Terrestrial Optical Fiber Drop | 1.07 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3359 | 4 | 359 | 3359 | 1400101004 | Cordillera Administrative Region (CAR) | Abra | Bangued | Bangbangar | 17.6056 | 120.6107 | R | 2438 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTABG0001 | PTCI/MIDC | 17.6077 | 120.6078 | 0.39 | Terrestrial Optical Fiber Drop | 1.69 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3360 | 4 | 360 | 3360 | 0600613020 | Region VI (Western Visayas) | Antique | San Jose | Madrangca | 10.7482 | 121.9352 | R | 3077 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060029 | FTAP BTS | 10.7722 | 121.9445 | 0.3 | Terrestrial Optical Fiber Drop | 1.6 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3361 | 4 | 361 | 3361 | 0604510012 | Region VI (Western Visayas) | Negros Occidental | City of Himamaylan | Sara-et | 10.0033 | 122.9654 | R | 4365 | 1179 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060116 | FTAP BTS | 10.1058 | 122.8721 | 2.89 | Terrestrial Optical Fiber Drop | 16.62 | 13.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3362 | 4 | 362 | 3362 | 0301421045 | Region III (Central Luzon) | Bulacan | San Miguel | San Juan | 15.1416 | 120.9845 | U | 9355 | 2672 | 802 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01104-B07 | PTCI/MIDC | 15.136 | 120.984 | 0.62 | Terrestrial Optical Fiber Drop | 1.7 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3363 | 4 | 363 | 3363 | 0305416026 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Isidro | 15.0601 | 120.647 | U | 10203 | 2550 | 765 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030484 | FTAP Globe | 15.0605 | 120.6473 | 0.06 | Terrestrial Optical Fiber Drop | 1.86 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3364 | 4 | 364 | 3364 | 0105517003 | Region I (Ilocos Region) | Pangasinan | Calasiao | Banaoang | 16.0111 | 120.3391 | U | 5072 | 1408 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00465 | Edgepoint | 16.0087 | 120.3432 | 0.51 | Terrestrial Optical Fiber Drop | 1.45 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3365 | 4 | 365 | 3365 | 0301420045 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Manuel | 14.7763 | 121.0677 | U | 11950 | 3414 | 1024 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00494-A01 | PTCI/MIDC | 14.7749 | 121.0661 | 0.24 | Terrestrial Optical Fiber Drop | 1.74 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3366 | 4 | 366 | 3366 | 0401019042 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Putat | 14.0821 | 120.6669 | R | 3688 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBGG0061 | PTCI/MIDC | 14.0747 | 120.6673 | 0.81 | Terrestrial Optical Fiber Drop | 3.76 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3367 | 4 | 367 | 3367 | 0306910014 | Region III (Central Luzon) | Tarlac | Paniqui | Coral | 15.6601 | 120.5724 | R | 2429 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00610 | Edgepoint | 15.6665 | 120.5713 | 0.71 | Terrestrial Optical Fiber Drop | 1.8 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3368 | 4 | 368 | 3368 | 0403404015 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | San Isidro | 14.2408 | 121.1397 | U | 25567 | 7747 | 2324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02046-C08 | PTCI/MIDC | 14.239 | 121.1339 | 0.65 | Terrestrial Optical Fiber Drop | 1.25 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3369 | 4 | 369 | 3369 | 1400101010 | Cordillera Administrative Region (CAR) | Abra | Bangued | Dangdangla | 17.599 | 120.6287 | R | 2037 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTABG0003 | PTCI/MIDC | 17.6085 | 120.6263 | 1.08 | Terrestrial Optical Fiber Drop | 1.23 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3370 | 4 | 370 | 3370 | 0306909026 | Region III (Central Luzon) | Tarlac | Moncada | San Julian | 15.7188 | 120.584 | R | 3103 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01796-B07 | PTCI/MIDC | 15.7192 | 120.5771 | 0.74 | Terrestrial Optical Fiber Drop | 1.19 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3371 | 4 | 371 | 3371 | 0402109042 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma III | 14.4076 | 120.9359 | R | 3866 | 1137 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01930-C08 | PTCI/MIDC | 14.4344 | 120.9174 | 0.56 | Terrestrial Optical Fiber Drop | 0.52 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3372 | 4 | 372 | 3372 | 0403425007 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Laram | 14.3418 | 121.0436 | U | 7165 | 2171 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040151 | FTAP Globe | 14.347 | 121.0481 | 0.6 | Terrestrial Optical Fiber Drop | 0.47 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3373 | 4 | 373 | 3373 | 0803715004 | Region VIII (Eastern Visayas) | Leyte | Carigara | Barugohay Norte | 11.3007 | 124.7047 | R | 2062 | 542 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0017 | PTCI/MIDC | 11.2951 | 124.7001 | 0.8 | Terrestrial Optical Fiber Drop | 1.68 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3374 | 4 | 374 | 3374 | 0403405044 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 7 | 14.2121 | 121.1636 | R | 2584 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03063-C08 | PTCI/MIDC | 14.21 | 121.1283 | 0.89 | Terrestrial Optical Fiber Drop | 2.5 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3375 | 4 | 375 | 3375 | 1401111009 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Palasaan | 16.8357 | 120.7966 | R | 3052 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 2.5 | Terrestrial Optical Fiber Drop | 1.98 | 0.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3376 | 4 | 376 | 3376 | 0604529003 | Region VI (Western Visayas) | Negros Occidental | Toboso | General Luna | 10.7209 | 123.49 | R | 5137 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-NEC-03149 | Edgepoint | 10.7185 | 123.5096 | 2.16 | Terrestrial Optical Fiber Drop | 13.52 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3377 | 4 | 377 | 3377 | 0603009019 | Region VI (Western Visayas) | Iloilo | Batad | Poblacion | 11.4119 | 123.1035 | R | 1754 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 1.39 | Terrestrial Optical Fiber Drop | 1.2 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3378 | 4 | 378 | 3378 | 0403403020 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Jose | 14.3458 | 121.0817 | U | 7234 | 2192 | 658 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02055-C08 | PTCI/MIDC | 14.3485 | 121.0836 | 0.36 | Terrestrial Optical Fiber Drop | 1.03 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3379 | 4 | 379 | 3379 | 0405603009 | Region IV-A (CALABARZON) | Quezon | Atimonan | Caridad Ibaba | 14.006 | 121.9159 | U | 6196 | 1630 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 1.14 | Terrestrial Optical Fiber Drop | 1.17 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3380 | 4 | 380 | 3380 | 0603034014 | Region VI (Western Visayas) | Iloilo | Oton | Cagbang | 10.6994 | 122.5024 | U | 5942 | 1563 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060016 | FTAP BTS | 10.7001 | 122.4999 | 0.29 | Terrestrial Optical Fiber Drop | 2.53 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3381 | 4 | 381 | 3381 | 0702205040 | Region VII (Central Visayas) | Cebu | Argao | Talaytay | 9.8929 | 123.5981 | R | 1934 | 508 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070017 | FTAP BTS | 9.8956 | 123.5985 | 0.3 | Terrestrial Optical Fiber Drop | 1.04 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3382 | 4 | 382 | 3382 | 0401022019 | Region IV-A (CALABARZON) | Batangas | San Jose | Lumil | 13.8696 | 121.0897 | U | 3274 | 909 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02522-C08 | PTCI/MIDC | 13.8694 | 121.0821 | 0.82 | Terrestrial Optical Fiber Drop | 1.96 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3383 | 4 | 383 | 3383 | 0501701012 | Region V (Bicol Region) | Camarines Sur | Baao | Sagrada | 13.4399 | 123.3904 | R | 4399 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03061-C10 | PTCI/MIDC | 13.4384 | 123.3912 | 0.19 | Terrestrial Optical Fiber Drop | 3.29 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3384 | 4 | 384 | 3384 | 0405641010 | Region IV-A (CALABARZON) | Quezon | San Antonio | Loob | 13.8779 | 121.2761 | R | 1854 | 487 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03161-C08 | PTCI/MIDC | 13.8725 | 121.2905 | 1.67 | Terrestrial Optical Fiber Drop | 1.37 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3385 | 4 | 385 | 3385 | 0803750005 | Region VIII (Eastern Visayas) | Leyte | Tunga | San Pedro | 11.2521 | 124.7558 | R | 1210 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 0.88 | Terrestrial Optical Fiber Drop | 1.09 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3386 | 4 | 386 | 3386 | 0907322043 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Santiago | 7.8202 | 123.4403 | U | 3274 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSR0014 | PTCI/MIDC | 7.8223 | 123.4377 | 0.37 | Terrestrial Optical Fiber Drop | 1.19 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3387 | 4 | 387 | 3387 | 0506203006 | Region V (Bicol Region) | Sorsogon | Bulan | Zone II Pob. | 12.6595 | 123.8757 | U | 5950 | 1487 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.98 | Terrestrial Optical Fiber Drop | 1.18 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3388 | 4 | 388 | 3388 | 0403411013 | Region IV-A (CALABARZON) | Laguna | Los Baños | Tadlak | 14.1801 | 121.2094 | R | 4432 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02048-C08 | PTCI/MIDC | 14.1818 | 121.2034 | 0.68 | Terrestrial Optical Fiber Drop | 3.55 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3389 | 4 | 389 | 3389 | 0300810029 | Region III (Central Luzon) | Bataan | Orion | Wawa | 14.6239 | 120.5839 | R | 1888 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 0.41 | Terrestrial Optical Fiber Drop | 1.08 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3390 | 4 | 390 | 3390 | 0105517010 | Region I (Ilocos Region) | Pangasinan | Calasiao | Lasip | 16.0058 | 120.3528 | R | 3425 | 951 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00473 | Edgepoint | 15.999 | 120.3479 | 0.92 | Terrestrial Optical Fiber Drop | 2.94 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3391 | 4 | 391 | 3391 | 1401110015 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Tawang | 16.4546 | 120.6021 | U | 8674 | 2478 | 743 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140177 | FTAP Globe | 16.4562 | 120.6053 | 0.38 | Terrestrial Optical Fiber Drop | 1.62 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3392 | 4 | 392 | 3392 | 0403425023 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Chrysanthemum | 14.3414 | 121.0442 | U | 13629 | 4130 | 1239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03021-C08 | PTCI/MIDC | 14.3568 | 121.0515 | 0.71 | Terrestrial Optical Fiber Drop | 0.54 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3393 | 4 | 393 | 3393 | 0301407001 | Region III (Central Luzon) | Bulacan | Calumpit | Balite | 14.8984 | 120.7864 | U | 5243 | 1498 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02325 | Edgepoint | 14.8962 | 120.7791 | 0.83 | Terrestrial Optical Fiber Drop | 2.19 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3394 | 4 | 394 | 3394 | 0730600071 | Region VII (Central Visayas) | Cebu | City of Cebu | Sawang Calero | 10.2907 | 123.8909 | U | 7685 | 2401 | 720 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CEB-03229 | Edgepoint | 10.2899 | 123.8937 | 0.32 | Terrestrial Optical Fiber Drop | 1.43 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3395 | 4 | 395 | 3395 | 0501724009 | Region V (Bicol Region) | Camarines Sur | City of Naga | Concepcion Grande | 13.6198 | 123.2205 | U | 11098 | 2642 | 793 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0712 | FTAP Smart | 13.6196 | 123.2243 | 0.41 | Terrestrial Optical Fiber Drop | 2.53 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3396 | 4 | 396 | 3396 | 0301417005 | Region III (Central Luzon) | Bulacan | Plaridel | Bintog | 14.9015 | 120.8906 | R | 4793 | 1369 | 411 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02203 | Edgepoint | 14.9029 | 120.8971 | 0.71 | Terrestrial Optical Fiber Drop | 4.3 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3397 | 4 | 397 | 3397 | 0305421006 | Region III (Central Luzon) | Pampanga | Sto. Tomas | San Matias | 15.009 | 120.712 | U | 14609 | 3652 | 1096 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00911 | Edgepoint | 15.0498 | 120.6542 | 0.62 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3398 | 4 | 398 | 3398 | 0702211022 | Region VII (Central Visayas) | Cebu | City of Bogo | Polambato | 11.0611 | 123.9866 | R | 4430 | 1165 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0020 | PTCI/MIDC | 11.0663 | 123.9912 | 0.76 | Terrestrial Optical Fiber Drop | 2.77 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3399 | 4 | 399 | 3399 | 1705209018 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Palayan | 13.026 | 121.4516 | R | 1981 | 507 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170096 | FTAP Globe | 13.0506 | 121.4483 | 2.21 | Terrestrial Optical Fiber Drop | 3.14 | 2.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3400 | 4 | 400 | 3400 | 1004301005 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Lanao | 8.5796 | 124.4675 | R | 2342 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100122 | FTAP Globe | 8.5696 | 124.4727 | 1.25 | Terrestrial Optical Fiber Drop | 1.28 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3401 | 4 | 401 | 3401 | 1600201001 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Abilan | 8.9774 | 125.4084 | R | 3261 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0002 | PTCI/MIDC | 8.9795 | 125.4097 | 0.28 | Terrestrial Optical Fiber Drop | 1.25 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3402 | 4 | 402 | 3402 | 0506216011 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Buhatan | 12.9737 | 124.0483 | U | 3935 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02793-C10 | PTCI/MIDC | 12.9806 | 124.0127 | 5.01 | Terrestrial Optical Fiber Drop | 3.02 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3403 | 4 | 403 | 3403 | 0304902006 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Cruz | 15.6158 | 121.1552 | R | 2275 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030347 | FTAP Globe | 15.6094 | 121.1676 | 1.5 | Terrestrial Optical Fiber Drop | 1.3 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3404 | 4 | 404 | 3404 | 0105526024 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Palua | 16.0903 | 120.3958 | R | 2406 | 668 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00421 | Edgepoint | 16.068 | 120.4097 | 0.37 | Terrestrial Optical Fiber Drop | 2.59 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3405 | 4 | 405 | 3405 | 0305416031 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Pedro | 15.0182 | 120.6922 | U | 12784 | 3196 | 959 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1823 | FTAP Smart | 15.0178 | 120.6924 | 0.06 | Terrestrial Optical Fiber Drop | 2.41 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3406 | 4 | 406 | 3406 | 0500518023 | Region V (Bicol Region) | Albay | Tiwi | Nagas | 13.4344 | 123.6783 | R | 3372 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 2.6 | Terrestrial Optical Fiber Drop | 2.44 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3407 | 4 | 407 | 3407 | 0402120020 | Region IV-A (CALABARZON) | Cavite | Tanza | Punta I | 14.341 | 120.8596 | U | 21479 | 6317 | 1895 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02215-C08 | PTCI/MIDC | 14.3809 | 120.8375 | 1.36 | Terrestrial Optical Fiber Drop | 3.12 | 2.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3408 | 4 | 408 | 3408 | 0401014062 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Lucas | 14.0173 | 121.1843 | U | 4359 | 1210 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01990-C08 | PTCI/MIDC | 14.0229 | 121.1856 | 0.63 | Terrestrial Optical Fiber Drop | 1.58 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3409 | 4 | 409 | 3409 | 0603044032 | Region VI (Western Visayas) | Iloilo | Sara | Pasig | 11.2631 | 123.0087 | R | 3536 | 930 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.74 | Terrestrial Optical Fiber Drop | 1.24 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3410 | 4 | 410 | 3410 | 0301403013 | Region III (Central Luzon) | Bulacan | Baliuag | Pinagbarilan | 14.9566 | 120.8787 | U | 6878 | 1965 | 590 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00936-B07 | PTCI/MIDC | 14.9532 | 120.8768 | 0.43 | Terrestrial Optical Fiber Drop | 1.38 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3411 | 4 | 411 | 3411 | 0301407015 | Region III (Central Luzon) | Bulacan | Calumpit | Longos | 14.8757 | 120.7859 | R | 4458 | 1273 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030569 | FTAP Globe | 14.8741 | 120.7851 | 0.2 | Terrestrial Optical Fiber Drop | 3.92 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3412 | 4 | 412 | 3412 | 0402112011 | Region IV-A (CALABARZON) | Cavite | Magallanes | Ramirez | 14.18 | 120.7307 | R | 1938 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040272 | FTAP Globe | 14.1766 | 120.7389 | 0.96 | Terrestrial Optical Fiber Drop | 1.37 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3413 | 4 | 413 | 3413 | 0105522029 | Region I (Ilocos Region) | Pangasinan | Lingayen | Quibaol | 16.0036 | 120.2304 | R | 3285 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00464 | Edgepoint | 16.0091 | 120.2223 | 1.06 | Terrestrial Optical Fiber Drop | 2.17 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3414 | 4 | 414 | 3414 | 0401019016 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Bucana | 14.0651 | 120.6263 | U | 4650 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1366 | FTAP Smart | 14.0663 | 120.6324 | 0.67 | Terrestrial Optical Fiber Drop | 1.05 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3415 | 4 | 415 | 3415 | 0306903025 | Region III (Central Luzon) | Tarlac | Camiling | Libueg | 15.7064 | 120.4173 | R | 2671 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00591 | Edgepoint | 15.7161 | 120.4236 | 1.26 | Terrestrial Optical Fiber Drop | 1.94 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3416 | 4 | 416 | 3416 | 1130700138 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 5-A | 7.0715 | 125.5962 | U | 11612 | 3415 | 1025 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSR0032 | PTCI/MIDC | 7.0763 | 125.5982 | 0.57 | Terrestrial Optical Fiber Drop | 1.57 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3417 | 4 | 417 | 3417 | 0701242014 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Taloto | 9.6753 | 123.8528 | U | 6467 | 1616 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070174 | FTAP BTS | 9.6794 | 123.8543 | 0.49 | Terrestrial Optical Fiber Drop | 1.4 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3418 | 4 | 418 | 3418 | 0405645014 | Region IV-A (CALABARZON) | Quezon | Sariaya | Concepcion Palasan | 13.9242 | 121.4638 | U | 6856 | 1804 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02139-C08 | PTCI/MIDC | 13.9299 | 121.4588 | 0.84 | Terrestrial Optical Fiber Drop | 2.41 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3419 | 4 | 419 | 3419 | 0307102019 | Region III (Central Luzon) | Zambales | Cabangan | San Isidro | 15.1689 | 120.0455 | R | 2434 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00822 | Edgepoint | 15.1674 | 120.0507 | 0.59 | Terrestrial Optical Fiber Drop | 1.21 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3420 | 4 | 420 | 3420 | 0803739030 | Region VIII (Eastern Visayas) | Leyte | Palo | San Jose | 11.1692 | 124.9884 | U | 5247 | 1380 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080145 | FTAP BTS | 11.1732 | 124.9819 | 0.83 | Terrestrial Optical Fiber Drop | 2.51 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3421 | 4 | 421 | 3421 | 0506203045 | Region V (Bicol Region) | Sorsogon | Bulan | J.P. Laurel | 12.6805 | 123.8692 | R | 4244 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_SOR_0002 | LDIC | 12.6765 | 123.8744 | 0.72 | Terrestrial Optical Fiber Drop | 1.26 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3422 | 4 | 422 | 3422 | 0305403028 | Region III (Central Luzon) | Pampanga | Arayat | San Nicolas | 15.1248 | 120.7833 | U | 9371 | 2342 | 703 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00864 | Edgepoint | 15.1204 | 120.7768 | 0.86 | Terrestrial Optical Fiber Drop | 2.31 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3423 | 4 | 423 | 3423 | 0500514031 | Region V (Bicol Region) | Albay | Polangui | Magurang | 13.2911 | 123.498 | R | 3793 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 0.96 | Terrestrial Optical Fiber Drop | 1.6 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3424 | 4 | 424 | 3424 | 0603034017 | Region VI (Western Visayas) | Iloilo | Oton | Lambuyao | 10.7011 | 122.4913 | R | 3284 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060016 | FTAP BTS | 10.7001 | 122.4999 | 0.94 | Terrestrial Optical Fiber Drop | 1.51 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3425 | 4 | 425 | 3425 | 0102906017 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Calongbuyan | 17.1741 | 120.4348 | R | 2944 | 774 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01246-B05 | PTCI/MIDC | 17.1761 | 120.4359 | 0.25 | Terrestrial Optical Fiber Drop | 2.34 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3426 | 4 | 426 | 3426 | 0803708084 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | San Isidro | 10.6967 | 124.807 | R | 2279 | 599 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080131 | FTAP BTS | 10.7013 | 124.8108 | 0.66 | Terrestrial Optical Fiber Drop | 2 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3427 | 4 | 427 | 3427 | 0501603008 | Region V (Bicol Region) | Camarines Norte | Daet | Cobangbang | 14.1057 | 122.96 | R | 3875 | 968 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050023 | FTAP Globe | 14.1078 | 122.9594 | 0.25 | Terrestrial Optical Fiber Drop | 1.2 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3428 | 4 | 428 | 3428 | 0401007016 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Camastilisan | 13.9253 | 120.8025 | R | 4296 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B61 | FTAP Smart | 13.9285 | 120.8051 | 0.45 | Terrestrial Optical Fiber Drop | 1.07 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3429 | 4 | 429 | 3429 | 0103317019 | Region I (Ilocos Region) | La Union | Santo Tomas | Poblacion | 16.2813 | 120.3816 | R | 1759 | 475 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00374 | Edgepoint | 16.2818 | 120.3824 | 0.09 | Terrestrial Optical Fiber Drop | 1.15 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3430 | 4 | 430 | 3430 | 0201529017 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Capatan | 17.6176 | 121.7498 | R | 3901 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020048 | FTAP Globe | 17.6114 | 121.751 | 0.7 | Terrestrial Optical Fiber Drop | 3.76 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3431 | 4 | 431 | 3431 | 0831600135 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 109-A | 11.1996 | 124.9987 | U | 8294 | 2022 | 607 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0065 | PTCI/MIDC | 11.2049 | 124.9973 | 0.61 | Terrestrial Optical Fiber Drop | 1.85 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3432 | 4 | 432 | 3432 | 0305406027 | Region III (Central Luzon) | Pampanga | Floridablanca | San Nicolas | 14.9728 | 120.5088 | U | 6244 | 1561 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00967 | Edgepoint | 14.9795 | 120.5061 | 0.8 | Terrestrial Optical Fiber Drop | 1.21 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3433 | 4 | 433 | 3433 | 0702245006 | Region VII (Central Visayas) | Cebu | Santander | Looc | 9.4329 | 123.3331 | R | 2239 | 589 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0153 | PTCI/MIDC | 9.4196 | 123.3343 | 1.39 | Terrestrial Optical Fiber Drop | 1.74 | 1.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3434 | 4 | 434 | 3434 | 0401023021 | Region IV-A (CALABARZON) | Batangas | San Juan | Mabalanoy | 13.8186 | 121.3856 | R | 4905 | 1362 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01956-C08 | PTCI/MIDC | 13.8259 | 121.3951 | 1.31 | Terrestrial Optical Fiber Drop | 1.23 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3435 | 4 | 435 | 3435 | 0300803006 | Region III (Central Luzon) | Bataan | City of Balanga | Central | 14.6637 | 120.5376 | U | 7399 | 2055 | 617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0027 | PTCI/MIDC | 14.661 | 120.536 | 0.34 | Terrestrial Optical Fiber Drop | 1.68 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3436 | 4 | 436 | 3436 | 0301406006 | Region III (Central Luzon) | Bulacan | Bustos | Catacte | 14.9087 | 120.9402 | U | 8781 | 2508 | 752 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030130 | FTAP BTS | 14.9096 | 120.942 | 0.22 | Terrestrial Optical Fiber Drop | 1.78 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3437 | 4 | 437 | 3437 | 0105512020 | Region I (Ilocos Region) | Pangasinan | Binalonan | Sta. Catalina | 16.0832 | 120.6119 | R | 2640 | 733 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02466-B07 | PTCI/MIDC | 16.0505 | 120.5941 | 1.12 | Terrestrial Optical Fiber Drop | 5.18 | 2.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3438 | 4 | 438 | 3438 | 1004307001 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Amoros | 8.5274 | 124.5463 | R | 5055 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0045 | PTCI/MIDC | 8.5357 | 124.5477 | 0.94 | Terrestrial Optical Fiber Drop | 3.24 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3439 | 4 | 439 | 3439 | 0402111009 | Region IV-A (CALABARZON) | Cavite | Kawit | Santa Isabel | 14.4381 | 120.8891 | U | 5479 | 1611 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0042 | PTCI/MIDC | 14.4397 | 120.8833 | 0.64 | Terrestrial Optical Fiber Drop | 1.16 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3440 | 4 | 440 | 3440 | 0301412026 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Caingin | 14.7268 | 120.9688 | U | 7207 | 2059 | 618 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01272 | Edgepoint | 14.7259 | 120.9697 | 0.14 | Terrestrial Optical Fiber Drop | 1.29 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3441 | 4 | 441 | 3441 | 0401028016 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Luis | 14.0235 | 121.1968 | U | 3027 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040500 | FTAP Globe | 13.9093 | 121.0582 | 0.24 | Terrestrial Optical Fiber Drop | 0.08 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3442 | 4 | 442 | 3442 | 0205004009 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Buag | 16.3858 | 121.1 | R | 3399 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0018 | PTCI/MIDC | 16.3833 | 121.1015 | 0.32 | Terrestrial Optical Fiber Drop | 1.42 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3443 | 4 | 443 | 3443 | 0701242006 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Dampas | 9.6459 | 123.8721 | U | 9192 | 2298 | 689 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070181 | FTAP BTS | 9.6448 | 123.8695 | 0.31 | Terrestrial Optical Fiber Drop | 1.63 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3444 | 4 | 444 | 3444 | 0731300011 | Region VII (Central Visayas) | Cebu | City of Mandaue | Cubacub | 10.3695 | 123.9386 | U | 13846 | 3956 | 1187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070002 | FTAP BTS | 10.3689 | 123.94 | 0.17 | Terrestrial Optical Fiber Drop | 2.11 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3445 | 4 | 445 | 3445 | 1401113011 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Tadiangan | 16.426 | 120.5423 | U | 8585 | 2452 | 736 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03273-B05 | PTCI/MIDC | 16.4382 | 120.547 | 1.45 | Terrestrial Optical Fiber Drop | 2.12 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3446 | 4 | 446 | 3446 | 0630200049 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Granada | 10.6713 | 123.0524 | U | 33140 | 9205 | 2762 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_NEC_0033 | LDIC | 10.6738 | 122.9641 | 0.5 | Terrestrial Optical Fiber Drop | 1.96 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3447 | 4 | 447 | 3447 | 0405809007 | Region IV-A (CALABARZON) | Rizal | Morong | San Juan | 14.5142 | 121.247 | U | 10706 | 2973 | 892 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040071 | FTAP Globe | 14.5114 | 121.2446 | 0.4 | Terrestrial Optical Fiber Drop | 1.15 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3448 | 4 | 448 | 3448 | 0105518020 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Mangin | 16.0383 | 120.3628 | R | 4112 | 1142 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1374 | FTAP Smart | 16.0366 | 120.36 | 0.36 | Terrestrial Optical Fiber Drop | 3.75 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3449 | 4 | 449 | 3449 | 0403424049 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Gregorio | 14.0494 | 121.3294 | U | 9559 | 2896 | 869 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040356 | FTAP Globe | 14.0509 | 121.3378 | 0.92 | Terrestrial Optical Fiber Drop | 1.1 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3450 | 4 | 450 | 3450 | 0304928036 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Tagpos | 15.436 | 121.0117 | R | 3783 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01512-B07 | PTCI/MIDC | 15.431 | 121.0084 | 0.65 | Terrestrial Optical Fiber Drop | 0.84 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3451 | 4 | 451 | 3451 | 0301412005 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bayugo | 14.7329 | 120.9536 | U | 20064 | 5732 | 1720 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01259 | Edgepoint | 14.7315 | 120.9537 | 0.16 | Terrestrial Optical Fiber Drop | 1.71 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3452 | 4 | 452 | 3452 | 0603044006 | Region VI (Western Visayas) | Iloilo | Sara | Apologista | 11.2188 | 122.9771 | R | 2976 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.97 | Terrestrial Optical Fiber Drop | 5.36 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3453 | 4 | 453 | 3453 | 1004302031 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Talusan | 8.7367 | 124.7936 | R | 3532 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100039 | FTAP BTS | 8.7367 | 124.803 | 1.03 | Terrestrial Optical Fiber Drop | 2.04 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3454 | 4 | 454 | 3454 | 0402105064 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 10-B | 14.4704 | 120.8893 | R | 2881 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | A00012-A03 | PTCI/MIDC | 14.4784 | 120.9747 | 0.48 | Terrestrial Optical Fiber Drop | 0.52 | 3.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3455 | 4 | 455 | 3455 | 0304911009 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bantug | 15.6445 | 120.762 | R | 4791 | 1368 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1187 | FTAP Smart | 15.64 | 120.7622 | 0.51 | Terrestrial Optical Fiber Drop | 1.58 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3456 | 4 | 456 | 3456 | 0301407010 | Region III (Central Luzon) | Bulacan | Calumpit | Frances | 14.9174 | 120.7581 | U | 6406 | 1830 | 549 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1128 | FTAP Smart | 14.9158 | 120.7575 | 0.19 | Terrestrial Optical Fiber Drop | 1.61 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3457 | 4 | 457 | 3457 | 1130700023 | Region XI (Davao Region) | Davao del Sur | City of Davao | Cabantian | 7.1207 | 125.6196 | U | 52130 | 15332 | 4600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0103 | PTCI/MIDC | 7.1243 | 125.6241 | 0.63 | Terrestrial Optical Fiber Drop | 1.47 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3458 | 4 | 458 | 3458 | 0405804023 | Region IV-A (CALABARZON) | Rizal | Binangonan | Mahabang Parang | 14.4684 | 121.2078 | U | 10580 | 2938 | 881 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0133 | PTCI/MIDC | 14.4692 | 121.2101 | 0.26 | Terrestrial Optical Fiber Drop | 1.1 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3459 | 4 | 459 | 3459 | 0603007024 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Tabuc-Suba | 10.917 | 122.6954 | R | 2145 | 564 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 1.21 | Terrestrial Optical Fiber Drop | 2.35 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3460 | 4 | 460 | 3460 | 0630200057 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Taculing | 10.6497 | 122.9471 | U | 43732 | 12147 | 3644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0010 | PTCI/MIDC | 10.6477 | 122.9488 | 0.28 | Terrestrial Optical Fiber Drop | 1.99 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3461 | 4 | 461 | 3461 | 0500508040 | Region V (Bicol Region) | Albay | City of Ligao | Pinit | 13.2554 | 123.5577 | R | 3604 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050155 | FTAP Globe | 13.2473 | 123.5607 | 0.96 | Terrestrial Optical Fiber Drop | 2.86 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3462 | 4 | 462 | 3462 | 0304928004 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Malacañang | 15.469 | 121.0827 | R | 2093 | 598 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 2.22 | Terrestrial Optical Fiber Drop | 2.34 | 2.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3463 | 4 | 463 | 3463 | 0402102007 | Region IV-A (CALABARZON) | Cavite | Amadeo | Maitim I | 14.1418 | 120.9479 | R | 3395 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02154-C08 | PTCI/MIDC | 14.136 | 120.9539 | 0.91 | Terrestrial Optical Fiber Drop | 2.52 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3464 | 4 | 464 | 3464 | 0403403012 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Malaban | 14.3461 | 121.0888 | U | 39450 | 11954 | 3586 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02055-C08 | PTCI/MIDC | 14.3485 | 121.0836 | 0.62 | Terrestrial Optical Fiber Drop | 1.63 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3465 | 4 | 465 | 3465 | 1606804011 | Region XIII (Caraga) | Surigao del Sur | Cagwait | Unidad | 8.9145 | 126.2973 | R | 4286 | 1045 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130081 | FTAP Globe | 8.8886 | 126.3087 | 1.42 | Terrestrial Optical Fiber Drop | 21.14 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3466 | 4 | 466 | 3466 | 0301407004 | Region III (Central Luzon) | Bulacan | Calumpit | Buguion | 14.8983 | 120.7929 | R | 4015 | 1147 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030552 | FTAP Globe | 14.8968 | 120.7949 | 0.27 | Terrestrial Optical Fiber Drop | 2.84 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3467 | 4 | 467 | 3467 | 0603044010 | Region VI (Western Visayas) | Iloilo | Sara | Aspera | 11.219 | 122.9775 | R | 2096 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.91 | Terrestrial Optical Fiber Drop | 5.41 | 2.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3468 | 4 | 468 | 3468 | 0304909002 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Balangkare Norte | 15.5971 | 121.0409 | R | 1805 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03329-B07 | PTCI/MIDC | 15.5959 | 121.0397 | 0.19 | Terrestrial Optical Fiber Drop | 1.26 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3469 | 4 | 469 | 3469 | 0405645016 | Region IV-A (CALABARZON) | Quezon | Sariaya | Guisguis-San Roque | 13.8733 | 121.5205 | R | 2361 | 621 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0016 | PTCI/MIDC | 13.8738 | 121.5193 | 0.14 | Terrestrial Optical Fiber Drop | 1.87 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3470 | 4 | 470 | 3470 | 0401005104 | Region IV-A (CALABARZON) | Batangas | Batangas City | Sorosoro Ilaya | 13.8079 | 121.0891 | U | 7877 | 2188 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02767-C08 | PTCI/MIDC | 13.7588 | 121.0702 | 0.3 | Terrestrial Optical Fiber Drop | 4.29 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3471 | 4 | 471 | 3471 | 0304903057 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Pagas | 15.5023 | 120.9551 | R | 3554 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1357 | FTAP Smart | 15.5046 | 120.9558 | 0.27 | Terrestrial Optical Fiber Drop | 2.38 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3472 | 4 | 472 | 3472 | 0701219011 | Region VII (Central Visayas) | Bohol | Dauis | Totolan | 9.6338 | 123.8519 | U | 8015 | 2003 | 601 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0018 | PTCI/MIDC | 9.6348 | 123.8454 | 0.72 | Terrestrial Optical Fiber Drop | 1.26 | 0.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3473 | 4 | 473 | 3473 | 0105518015 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Lasip Grande | 16.0282 | 120.3429 | R | 2432 | 675 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00443 | Edgepoint | 16.0274 | 120.3367 | 0.67 | Terrestrial Optical Fiber Drop | 1.59 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3474 | 4 | 474 | 3474 | 1004322019 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Casulog | 8.8791 | 124.8083 | R | 3479 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 3.18 | Terrestrial Optical Fiber Drop | 3.31 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3475 | 4 | 475 | 3475 | 1001312012 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Casisang | 8.1421 | 125.1189 | U | 32902 | 8658 | 2597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0056 | PTCI/MIDC | 8.1403 | 125.1175 | 0.25 | Terrestrial Optical Fiber Drop | 1.61 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3476 | 4 | 476 | 3476 | 0300809026 | Region III (Central Luzon) | Bataan | Orani | Kabalutan | 14.8133 | 120.5328 | R | 3154 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00908-B07 | PTCI/MIDC | 14.8084 | 120.5269 | 0.83 | Terrestrial Optical Fiber Drop | 1.3 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3477 | 4 | 477 | 3477 | 1606724041 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | San Juan | 9.7909 | 125.4845 | U | 17526 | 4274 | 1282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSNG0014 | PTCI/MIDC | 9.7864 | 125.4817 | 0.59 | Terrestrial Optical Fiber Drop | 1.17 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3478 | 4 | 478 | 3478 | 0702250002 | Region VII (Central Visayas) | Cebu | City of Talisay | Cadulawan | 10.2787 | 123.8432 | U | 6433 | 1692 | 508 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0197 | PTCI/MIDC | 10.2761 | 123.8445 | 0.31 | Terrestrial Optical Fiber Drop | 1.87 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3479 | 4 | 479 | 3479 | 0506209016 | Region V (Bicol Region) | Sorsogon | Irosin | Macawayan | 12.7047 | 124.0171 | R | 3250 | 812 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 2.18 | Terrestrial Optical Fiber Drop | 2.03 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3480 | 4 | 480 | 3480 | 0301410012 | Region III (Central Luzon) | Bulacan | City of Malolos | Bulihan | 14.8581 | 120.8005 | U | 16583 | 4738 | 1421 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030579 | FTAP Globe | 14.852 | 120.8047 | 0.82 | Terrestrial Optical Fiber Drop | 1.85 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3481 | 4 | 481 | 3481 | 0403430002 | Region IV-A (CALABARZON) | Laguna | Victoria | Daniw | 14.2004 | 121.355 | R | 1770 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02113-C08 | PTCI/MIDC | 14.2028 | 121.346 | 1.01 | Terrestrial Optical Fiber Drop | 1.22 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3482 | 4 | 482 | 3482 | 0402106022 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima I | 14.3205 | 120.9567 | U | 7140 | 2100 | 630 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02622-C08 | PTCI/MIDC | 14.3084 | 120.9411 | 0.8 | Terrestrial Optical Fiber Drop | 1.33 | 2.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3483 | 4 | 483 | 3483 | 0506216006 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Bibincahan | 12.9841 | 124.0101 | U | 21026 | 5256 | 1577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02793-C10 | PTCI/MIDC | 12.9806 | 124.0127 | 0.48 | Terrestrial Optical Fiber Drop | 1.74 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3484 | 4 | 484 | 3484 | 0702218006 | Region VII (Central Visayas) | Cebu | Compostela | Canamucan | 10.4674 | 124.0086 | U | 5088 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070185 | FTAP BTS | 10.468 | 124.0168 | 0.9 | Terrestrial Optical Fiber Drop | 1.69 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3485 | 4 | 485 | 3485 | 0305417002 | Region III (Central Luzon) | Pampanga | San Luis | San Carlos | 15.0422 | 120.7585 | R | 4730 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030034 | FTAP BTS | 15.0385 | 120.7648 | 0.79 | Terrestrial Optical Fiber Drop | 3.21 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3486 | 4 | 486 | 3486 | 0205015005 | Region II (Cagayan Valley) | Nueva Vizcaya | Alfonso Castaneda | Lublub | 15.803 | 121.3044 | R | 4457 | 1172 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02878-B06 | PTCI/MIDC | 15.8022 | 121.3038 | 0.11 | Terrestrial Optical Fiber Drop | 17.2 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3487 | 4 | 487 | 3487 | 0105526029 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Tebag | 16.0803 | 120.407 | R | 3084 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00414 | Edgepoint | 16.083 | 120.3977 | 1.04 | Terrestrial Optical Fiber Drop | 1.48 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3488 | 4 | 488 | 3488 | 0403426023 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santisima Cruz | 14.2881 | 121.412 | U | 10744 | 3255 | 977 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.6 | Terrestrial Optical Fiber Drop | 1.01 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3489 | 4 | 489 | 3489 | 0401012003 | Region IV-A (CALABARZON) | Batangas | Lemery | Ayao-iyao | 13.9066 | 120.9053 | R | 3276 | 910 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040496 | FTAP Globe | 13.9101 | 120.9078 | 0.46 | Terrestrial Optical Fiber Drop | 2.29 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3490 | 4 | 490 | 3490 | 1400101030 | Cordillera Administrative Region (CAR) | Abra | Bangued | Zone 7 Pob. | 17.5971 | 120.6177 | U | 3047 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02672-B05 | PTCI/MIDC | 17.6009 | 120.618 | 1.29 | Terrestrial Optical Fiber Drop | 0.51 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3491 | 4 | 491 | 3491 | 0304917008 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Catalanacan | 15.7137 | 120.8851 | R | 4123 | 1178 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1223 | FTAP Smart | 15.7227 | 120.8764 | 1.37 | Terrestrial Optical Fiber Drop | 1.93 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3492 | 4 | 492 | 3492 | 1206511006 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Virginia Griño | 6.6774 | 124.6734 | U | 6887 | 1812 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120127 | FTAP BTS | 6.6711 | 124.6851 | 0.81 | Terrestrial Optical Fiber Drop | 1.36 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3493 | 4 | 493 | 3493 | 1004314011 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Tubajon | 8.5877 | 124.4427 | R | 3166 | 811 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 1.54 | Terrestrial Optical Fiber Drop | 1.53 | 1.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3494 | 4 | 494 | 3494 | 0702210039 | Region VII (Central Visayas) | Cebu | Barili | San Rafael | 10.1114 | 123.5275 | R | 1994 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070062 | FTAP BTS | 10.116 | 123.5147 | 1.01 | Terrestrial Optical Fiber Drop | 2.07 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3495 | 4 | 495 | 3495 | 0402106051 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima II | 14.3183 | 120.9522 | U | 4532 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02156-C08 | PTCI/MIDC | 14.2976 | 120.9238 | 0.47 | Terrestrial Optical Fiber Drop | 1.59 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3496 | 4 | 496 | 3496 | 0105526027 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Salaan | 16.0852 | 120.4039 | R | 2958 | 821 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00414 | Edgepoint | 16.083 | 120.3977 | 0.7 | Terrestrial Optical Fiber Drop | 1.94 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3497 | 4 | 497 | 3497 | 0403428008 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Labas | 14.3064 | 121.1113 | U | 23335 | 7071 | 2121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4299 | FTAP Smart | 14.3067 | 121.1098 | 0.16 | Terrestrial Optical Fiber Drop | 1.05 | 0.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3498 | 4 | 498 | 3498 | 1130700141 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 8-A | 7.0714 | 125.5963 | U | 15877 | 4669 | 1401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0061 | PTCI/MIDC | 7.1851 | 125.4704 | 0.4 | Terrestrial Optical Fiber Drop | 1.56 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3499 | 4 | 499 | 3499 | 0500510012 | Region V (Bicol Region) | Albay | Malinao | Estancia | 13.3591 | 123.681 | R | 4774 | 1164 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 1.26 | Terrestrial Optical Fiber Drop | 2.88 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3500 | 4 | 500 | 3500 | 0306905043 | Region III (Central Luzon) | Tarlac | Concepcion | Santa Rita | 15.3165 | 120.6605 | U | 5826 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00763 | Edgepoint | 15.323 | 120.6635 | 0.78 | Terrestrial Optical Fiber Drop | 1.03 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3501 | 4 | 501 | 3501 | 0730600056 | Region VII (Central Visayas) | Cebu | City of Cebu | Pasil | 10.2906 | 123.8944 | U | 8405 | 2626 | 788 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CEB-03229 | Edgepoint | 10.2899 | 123.8937 | 0.11 | Terrestrial Optical Fiber Drop | 1.23 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3502 | 4 | 502 | 3502 | 0604531017 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XIV | 10.9038 | 123.0608 | R | 4791 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0079 | PTCI/MIDC | 10.9046 | 123.0617 | 0.13 | Terrestrial Optical Fiber Drop | 1.37 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3503 | 4 | 503 | 3503 | 0603031001 | Region VI (Western Visayas) | Iloilo | Mina | Abat | 10.9402 | 122.5655 | R | 958 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 1.85 | Terrestrial Optical Fiber Drop | 1.03 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3504 | 4 | 504 | 3504 | 1004302019 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Napaliran | 8.7735 | 124.7919 | R | 3792 | 972 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0107 | PTCI/MIDC | 8.7737 | 124.7956 | 0.41 | Terrestrial Optical Fiber Drop | 2.85 | 0.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3505 | 4 | 505 | 3505 | 0307114003 | Region III (Central Luzon) | Zambales | Subic | Asinan Proper | 14.8953 | 120.228 | U | 9489 | 2497 | 749 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0020 | PTCI/MIDC | 14.893 | 120.2374 | 1.04 | Terrestrial Optical Fiber Drop | 1.26 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3506 | 4 | 506 | 3506 | 0105524003 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Alacan | 15.9105 | 120.407 | R | 2029 | 563 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_PNG_0006 | LDIC | 15.9097 | 120.4032 | 0.42 | Terrestrial Optical Fiber Drop | 1.25 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3507 | 4 | 507 | 3507 | 0600407005 | Region VI (Western Visayas) | Aklan | Kalibo | Buswang New | 11.7108 | 122.3753 | U | 11732 | 3008 | 902 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKG0007 | PTCI/MIDC | 11.7125 | 122.3747 | 0.2 | Terrestrial Optical Fiber Drop | 1.74 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3508 | 4 | 508 | 3508 | 0431200003 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 10 | 13.9268 | 121.6183 | U | 5178 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040470 | FTAP Globe | 13.9255 | 121.6213 | 0.36 | Terrestrial Optical Fiber Drop | 1.01 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3509 | 4 | 509 | 3509 | 0631000094 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Loboc-Lapuz | 10.7048 | 122.5627 | U | 2615 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 1.29 | Terrestrial Optical Fiber Drop | 1.15 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3510 | 4 | 510 | 3510 | 0704610005 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Bantayan | 9.3136 | 123.2887 | U | 4613 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0024 | PTCI/MIDC | 9.3142 | 123.294 | 0.47 | Terrestrial Optical Fiber Drop | 1.91 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3511 | 4 | 511 | 3511 | 0305404004 | Region III (Central Luzon) | Pampanga | Bacolor | Cabetican | 15.2221 | 120.6088 | U | 3724 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00793 | Edgepoint | 15.2255 | 120.6073 | 0.41 | Terrestrial Optical Fiber Drop | 1.15 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3512 | 4 | 512 | 3512 | 0405804038 | Region IV-A (CALABARZON) | Rizal | Binangonan | Libid | 14.4615 | 121.1994 | U | 7723 | 2145 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01897 | Edgepoint | 14.4587 | 121.1985 | 0.32 | Terrestrial Optical Fiber Drop | 1.56 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3513 | 4 | 513 | 3513 | 0304928024 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Burgos | 15.4339 | 120.9379 | R | 1550 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 1.43 | Terrestrial Optical Fiber Drop | 1.24 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3514 | 4 | 514 | 3514 | 1001314016 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Mantibugao | 8.3686 | 124.8625 | R | 4168 | 1096 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 0.66 | Terrestrial Optical Fiber Drop | 1.91 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3515 | 4 | 515 | 3515 | 0403425022 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Narra | 14.3421 | 121.0232 | R | 2518 | 763 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02057-C08 | PTCI/MIDC | 14.3453 | 121.028 | 0.44 | Terrestrial Optical Fiber Drop | 1.86 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3516 | 4 | 516 | 3516 | 0403403001 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Biñan | 14.3359 | 121.081 | U | 7786 | 2359 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02089-C08 | PTCI/MIDC | 14.3186 | 121.0757 | 0.34 | Terrestrial Optical Fiber Drop | 0.64 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3517 | 4 | 517 | 3517 | 0203130013 | Region II (Cagayan Valley) | Isabela | San Manuel | District 3 | 17.0241 | 121.6379 | R | 3112 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02357-B06 | PTCI/MIDC | 17.031 | 121.6292 | 0.92 | Terrestrial Optical Fiber Drop | 3.02 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3518 | 4 | 518 | 3518 | 0603045042 | Region VI (Western Visayas) | Iloilo | Tigbauan | Napnapan Norte | 10.7081 | 122.3982 | R | 2225 | 585 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0082 | PTCI/MIDC | 10.6764 | 122.3997 | 0.72 | Terrestrial Optical Fiber Drop | 3.71 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3519 | 4 | 519 | 3519 | 0803739032 | Region VIII (Eastern Visayas) | Leyte | Palo | Tacuranga | 11.1595 | 124.9862 | R | 2027 | 533 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.74 | Terrestrial Optical Fiber Drop | 1.88 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3520 | 4 | 520 | 3520 | 1130700196 | Region XI (Davao Region) | Davao del Sur | City of Davao | Wilfredo Aquino | 7.0907 | 125.6259 | U | 8391 | 2467 | 740 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0124 | PTCI/MIDC | 7.0902 | 125.6281 | 0.24 | Terrestrial Optical Fiber Drop | 2.27 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3521 | 4 | 521 | 3521 | 0501715010 | Region V (Bicol Region) | Camarines Sur | Goa | Gimaga | 13.7041 | 123.4766 | R | 2342 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050064 | FTAP Globe | 13.6982 | 123.4789 | 0.7 | Terrestrial Optical Fiber Drop | 1.59 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3522 | 4 | 522 | 3522 | 0300804050 | Region III (Central Luzon) | Bataan | Dinalupihan | Jose C. Payumo, Jr. | 14.8669 | 120.4339 | R | 4080 | 1133 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O06 | FTAP Smart | 14.8624 | 120.4361 | 0.55 | Terrestrial Optical Fiber Drop | 2.42 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3523 | 4 | 523 | 3523 | 0702223044 | Region VII (Central Visayas) | Cebu | Danao City | Tuburan Sur | 10.5136 | 124.0171 | U | 8162 | 2147 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0079 | PTCI/MIDC | 10.5161 | 124.022 | 0.6 | Terrestrial Optical Fiber Drop | 1.36 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3524 | 4 | 524 | 3524 | 1130700057 | Region XI (Davao Region) | Davao del Sur | City of Davao | Lizada | 7.1651 | 125.4715 | U | 24678 | 7258 | 2177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0005 | PTCI/MIDC | 7.0039 | 125.4998 | 0.64 | Terrestrial Optical Fiber Drop | 2.96 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3525 | 4 | 525 | 3525 | 0102805036 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Quiling Sur | 18.0659 | 120.5515 | R | 3317 | 896 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010026 | FTAP Globe | 18.0588 | 120.5595 | 1.15 | Terrestrial Optical Fiber Drop | 1.05 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3526 | 4 | 526 | 3526 | 0301408012 | Region III (Central Luzon) | Bulacan | Guiguinto | Tabe | 14.8368 | 120.8876 | U | 9629 | 2751 | 825 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0011 | LDIC | 14.8349 | 120.8893 | 0.27 | Terrestrial Optical Fiber Drop | 1.81 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3527 | 4 | 527 | 3527 | 0105535007 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Norte | 16.0707 | 120.6533 | U | 5411 | 1503 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010143 | FTAP Globe | 16.0623 | 120.6491 | 1.04 | Terrestrial Optical Fiber Drop | 1.75 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3528 | 4 | 528 | 3528 | 0501701013 | Region V (Bicol Region) | Camarines Sur | Baao | Salvacion | 13.4603 | 123.374 | R | 3217 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050118 | FTAP Globe | 13.4568 | 123.3687 | 0.69 | Terrestrial Optical Fiber Drop | 1.09 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3529 | 4 | 529 | 3529 | 0304904024 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Carlos | 15.2414 | 120.8387 | R | 4164 | 1189 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030431 | FTAP Globe | 15.2353 | 120.8462 | 1.05 | Terrestrial Optical Fiber Drop | 3.84 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3530 | 4 | 530 | 3530 | 0401027013 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Sampa | 13.8615 | 120.9677 | R | 1600 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0759 | FTAP Smart | 13.899 | 120.9757 | 1.56 | Terrestrial Optical Fiber Drop | 1.88 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3531 | 4 | 531 | 3531 | 0401026024 | Region IV-A (CALABARZON) | Batangas | San Pascual | Sambat | 13.8014 | 121.0127 | U | 6184 | 1717 | 515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0048 | PTCI/MIDC | 13.7974 | 121.0156 | 0.54 | Terrestrial Optical Fiber Drop | 1.3 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3532 | 4 | 532 | 3532 | 0501603018 | Region V (Bicol Region) | Camarines Norte | Daet | Magang | 14.0983 | 122.9456 | U | 7371 | 1842 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAN-03170 | Edgepoint | 14.0939 | 122.9489 | 0.61 | Terrestrial Optical Fiber Drop | 2 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3533 | 4 | 533 | 3533 | 0330100023 | Region III (Central Luzon) | Pampanga | City of Angeles | San Jose | 15.1469 | 120.606 | U | 7506 | 2085 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02453-B07 | PTCI/MIDC | 15.1447 | 120.5885 | 0.24 | Terrestrial Optical Fiber Drop | 1.58 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3534 | 4 | 534 | 3534 | 0402117014 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong IV | 14.4275 | 120.8704 | R | 3117 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040116 | FTAP Globe | 14.41 | 120.8725 | 0.53 | Terrestrial Optical Fiber Drop | 1.38 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3535 | 4 | 535 | 3535 | 0402120010 | Region IV-A (CALABARZON) | Cavite | Tanza | Halayhay | 14.3729 | 120.8127 | U | 6976 | 2051 | 615 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02222-C08 | PTCI/MIDC | 14.3698 | 120.8191 | 0.78 | Terrestrial Optical Fiber Drop | 1.15 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3536 | 4 | 536 | 3536 | 0301420050 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael III | 14.8537 | 121.0458 | R | 2841 | 811 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0043 | PTCI/MIDC | 14.7859 | 121.0524 | 0.15 | Terrestrial Optical Fiber Drop | 1.6 | 5.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3537 | 4 | 537 | 3537 | 1001321004 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Batangan | 7.9096 | 125.0942 | U | 15973 | 4203 | 1261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 1.13 | Terrestrial Optical Fiber Drop | 0.47 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3538 | 4 | 538 | 3538 | 0300801010 | Region III (Central Luzon) | Bataan | Abucay | Salian | 14.7125 | 120.5288 | R | 4003 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0024 | PTCI/MIDC | 14.7093 | 120.5229 | 0.73 | Terrestrial Optical Fiber Drop | 3.3 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3539 | 4 | 539 | 3539 | 0301412010 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Langka | 14.7395 | 120.9806 | U | 4515 | 1290 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00962-B07 | PTCI/MIDC | 14.7409 | 120.9799 | 0.18 | Terrestrial Optical Fiber Drop | 1.31 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3540 | 4 | 540 | 3540 | 0305416006 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dela Paz Sur | 15.0757 | 120.631 | U | 3214 | 803 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00892 | Edgepoint | 15.0763 | 120.6349 | 0.42 | Terrestrial Optical Fiber Drop | 1.2 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3541 | 4 | 541 | 3541 | 1401105013 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Poblacion | 16.7835 | 120.8244 | R | 3192 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBEG0006 | PTCI/MIDC | 16.7904 | 120.8171 | 1.09 | Terrestrial Optical Fiber Drop | 2.25 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3542 | 4 | 542 | 3542 | 0702219016 | Region VII (Central Visayas) | Cebu | Consolacion | Pulpogan | 10.3862 | 123.9567 | U | 15032 | 3955 | 1187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070325 | FTAP Globe | 10.3879 | 123.9644 | 0.86 | Terrestrial Optical Fiber Drop | 1.1 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3543 | 4 | 543 | 3543 | 0301410053 | Region III (Central Luzon) | Bulacan | City of Malolos | Sumapang Matanda | 14.857 | 120.8278 | U | 9114 | 2604 | 781 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01110 | Edgepoint | 14.856 | 120.8206 | 0.78 | Terrestrial Optical Fiber Drop | 1.14 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3544 | 4 | 544 | 3544 | 0501708036 | Region V (Bicol Region) | Camarines Sur | Calabanga | San Lucas | 13.7047 | 123.1944 | R | 2645 | 629 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0026 | PTCI/MIDC | 13.7053 | 123.1926 | 0.21 | Terrestrial Optical Fiber Drop | 1.62 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3545 | 4 | 545 | 3545 | 0500517003 | Region V (Bicol Region) | Albay | City of Tabaco | Bangkilingan | 13.3486 | 123.7123 | U | 4845 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050133 | FTAP Globe | 13.3444 | 123.7023 | 0.75 | Terrestrial Optical Fiber Drop | 2.11 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3546 | 4 | 546 | 3546 | 0402120042 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan VIII | 14.4043 | 120.8467 | U | 5275 | 1551 | 465 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02222-C08 | PTCI/MIDC | 14.3698 | 120.8191 | 1.07 | Terrestrial Optical Fiber Drop | 1.78 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3547 | 4 | 547 | 3547 | 1230800036 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas South | 6.1105 | 125.1755 | U | 4986 | 1278 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCR0010 | PTCI/MIDC | 6.1091 | 125.1784 | 0.35 | Terrestrial Optical Fiber Drop | 1.58 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3548 | 4 | 548 | 3548 | 0105522025 | Region I (Ilocos Region) | Pangasinan | Lingayen | Namolan | 16.0172 | 120.2486 | R | 2648 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010163 | FTAP Globe | 16.009 | 120.2529 | 1.02 | Terrestrial Optical Fiber Drop | 1.82 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3549 | 4 | 549 | 3549 | 0105520010 | Region I (Ilocos Region) | Pangasinan | Infanta | Nayom | 15.8175 | 119.8986 | R | 2110 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00569 | Edgepoint | 15.8208 | 119.9067 | 0.94 | Terrestrial Optical Fiber Drop | 1.54 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3550 | 4 | 550 | 3550 | 0601904016 | Region VI (Western Visayas) | Capiz | Dumarao | Codingle | 11.2558 | 122.6858 | R | 1790 | 471 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060244 | FTAP Globe | 11.2736 | 122.6783 | 2.14 | Terrestrial Optical Fiber Drop | 1 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3551 | 4 | 551 | 3551 | 0304904003 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Bagong Silang | 15.2548 | 120.851 | R | 4654 | 1329 | 399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0019 | PTCI/MIDC | 15.2529 | 120.8499 | 0.24 | Terrestrial Optical Fiber Drop | 1.92 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3552 | 4 | 552 | 3552 | 0105526022 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Nibaliw | 16.0773 | 120.4096 | R | 3363 | 934 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02359-B07 | PTCI/MIDC | 16.0739 | 120.4161 | 0.78 | Terrestrial Optical Fiber Drop | 1.31 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3553 | 4 | 553 | 3553 | 0401017018 | Region IV-A (CALABARZON) | Batangas | Malvar | San Pedro I | 14.0506 | 121.1471 | R | 3883 | 1078 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040355 | FTAP Globe | 14.0531 | 121.1549 | 0.88 | Terrestrial Optical Fiber Drop | 3.59 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3554 | 4 | 554 | 3554 | 0704601007 | Region VII (Central Visayas) | Negros Oriental | Amlan | Tambojangin | 9.449 | 123.2104 | R | 2372 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070259 | FTAP Globe | 9.4593 | 123.2167 | 1.34 | Terrestrial Optical Fiber Drop | 1.85 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3555 | 4 | 555 | 3555 | 0403411010 | Region IV-A (CALABARZON) | Laguna | Los Baños | Mayondon | 14.1882 | 121.2383 | U | 19530 | 5918 | 1775 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02047-C08 | PTCI/MIDC | 14.1865 | 121.2336 | 0.54 | Terrestrial Optical Fiber Drop | 1.09 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3556 | 4 | 556 | 3556 | 0301418011 | Region III (Central Luzon) | Bulacan | Pulilan | Lumbac | 14.9041 | 120.8479 | R | 4982 | 1423 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01092-B07 | PTCI/MIDC | 14.9141 | 120.8331 | 0.26 | Terrestrial Optical Fiber Drop | 0.36 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3557 | 4 | 557 | 3557 | 0704621018 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | San Isidro | 9.5223 | 123.1481 | R | 4503 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070258 | FTAP Globe | 9.5141 | 123.156 | 1.25 | Terrestrial Optical Fiber Drop | 8.03 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3558 | 4 | 558 | 3558 | 0102934034 | Region I (Ilocos Region) | Ilocos Sur | City of Vigan | San Julian Norte | 17.5717 | 120.3974 | R | 2931 | 771 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01259-B05 | PTCI/MIDC | 17.5676 | 120.4033 | 0.78 | Terrestrial Optical Fiber Drop | 2.55 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3559 | 4 | 559 | 3559 | 0803726010 | Region VIII (Eastern Visayas) | Leyte | Kananga | Masarayao | 11.1167 | 124.593 | R | 3342 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0029 | PTCI/MIDC | 11.128 | 124.5855 | 1.5 | Terrestrial Optical Fiber Drop | 2.19 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3560 | 4 | 560 | 3560 | 0405645006 | Region IV-A (CALABARZON) | Quezon | Sariaya | Bignay 1 | 13.863 | 121.4885 | U | 5450 | 1434 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03101-C08 | PTCI/MIDC | 13.8418 | 121.4761 | 2.71 | Terrestrial Optical Fiber Drop | 2.15 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3561 | 4 | 561 | 3561 | 0405608022 | Region IV-A (CALABARZON) | Quezon | Candelaria | San Andres | 13.9096 | 121.4446 | U | 5198 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1264 | FTAP Smart | 13.9179 | 121.4369 | 1.24 | Terrestrial Optical Fiber Drop | 1.3 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3562 | 4 | 562 | 3562 | 1404402014 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Monamon Norte | 16.8989 | 120.891 | R | 2809 | 759 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MOU-00237 | Edgepoint | 16.8985 | 120.8953 | 0.46 | Terrestrial Optical Fiber Drop | 1.87 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3563 | 4 | 563 | 3563 | 0304919014 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Caballero | 15.5444 | 121.0876 | R | 3939 | 1125 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01486-B07 | PTCI/MIDC | 15.5444 | 121.0886 | 0.11 | Terrestrial Optical Fiber Drop | 0.95 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3564 | 4 | 564 | 3564 | 0604520023 | Region VI (Western Visayas) | Negros Occidental | Murcia | Santa Rosa | 10.5715 | 123.1018 | U | 5759 | 1556 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060357 | FTAP Globe | 10.5658 | 123.076 | 2.89 | Terrestrial Optical Fiber Drop | 2.71 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3565 | 4 | 565 | 3565 | 0201529039 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Atulayan Sur | 17.6352 | 121.7202 | R | 4645 | 1191 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCGG0009 | PTCI/MIDC | 17.6356 | 121.7189 | 0.15 | Terrestrial Optical Fiber Drop | 3.37 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3566 | 4 | 566 | 3566 | 0402103020 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Salinas I | 14.4399 | 120.9359 | U | 20694 | 6086 | 1826 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0005 | LDIC | 14.4384 | 120.9327 | 0.39 | Terrestrial Optical Fiber Drop | 1.52 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3567 | 4 | 567 | 3567 | 0402117021 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa III | 14.4117 | 120.848 | U | 12517 | 3681 | 1104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040123 | FTAP Globe | 14.4014 | 120.8458 | 0.39 | Terrestrial Optical Fiber Drop | 2.13 | 2.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3568 | 4 | 568 | 3568 | 1705105008 | MIMAROPA Region | Occidental Mindoro | Magsaysay | Nicolas | 12.2997 | 121.2425 | R | 4362 | 1118 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170140 | FTAP Globe | 12.2889 | 121.1903 | 5.8 | Terrestrial Optical Fiber Drop | 10.14 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3569 | 4 | 569 | 3569 | 0304919015 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Caimito | 15.5449 | 121.087 | R | 2783 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01486-B07 | PTCI/MIDC | 15.5444 | 121.0886 | 0.18 | Terrestrial Optical Fiber Drop | 0.96 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3570 | 4 | 570 | 3570 | 0500503005 | Region V (Bicol Region) | Albay | Daraga | Balinad | 13.1415 | 123.698 | R | 2692 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050185 | FTAP Globe | 13.1281 | 123.7033 | 1.59 | Terrestrial Optical Fiber Drop | 1.62 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3571 | 4 | 571 | 3571 | 0304903091 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Aduas Sur | 15.4964 | 120.9672 | U | 8327 | 2379 | 714 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030371 | FTAP Globe | 15.4982 | 120.9647 | 0.33 | Terrestrial Optical Fiber Drop | 1.76 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3572 | 4 | 572 | 3572 | 0730600085 | Region VII (Central Visayas) | Cebu | City of Cebu | Tisa | 10.2985 | 123.8695 | U | 47421 | 14819 | 4446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CEB_0004 | LDIC | 10.2979 | 123.8697 | 0.07 | Terrestrial Optical Fiber Drop | 1.8 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3573 | 4 | 573 | 3573 | 0105517001 | Region I (Ilocos Region) | Pangasinan | Calasiao | Ambonao | 16.0264 | 120.3695 | U | 6934 | 1926 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03242-B07 | PTCI/MIDC | 16.0315 | 120.3716 | 0.61 | Terrestrial Optical Fiber Drop | 2.35 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3574 | 4 | 574 | 3574 | 0301404017 | Region III (Central Luzon) | Bulacan | Bocaue | Tambobong | 14.8157 | 120.9398 | U | 7655 | 2187 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01168 | Edgepoint | 14.8158 | 120.9364 | 0.36 | Terrestrial Optical Fiber Drop | 2.01 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3575 | 4 | 575 | 3575 | 0603005003 | Region VI (Western Visayas) | Iloilo | Balasan | Balanti-an | 11.4883 | 123.0888 | R | 2555 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 2.53 | Terrestrial Optical Fiber Drop | 1.92 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3576 | 4 | 576 | 3576 | 0601914040 | Region VI (Western Visayas) | Capiz | City of Roxas | Mongpong | 11.5935 | 122.7713 | U | 5484 | 1443 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060224 | FTAP Globe | 11.594 | 122.7672 | 0.45 | Terrestrial Optical Fiber Drop | 2.56 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3577 | 4 | 577 | 3577 | 0307109012 | Region III (Central Luzon) | Zambales | San Antonio | San Nicolas | 14.949 | 120.0795 | R | 3380 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.98 | Terrestrial Optical Fiber Drop | 1.18 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3578 | 4 | 578 | 3578 | 0405810009 | Region IV-A (CALABARZON) | Rizal | Pililla | Wawa | 14.4636 | 121.3248 | R | 4180 | 1161 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01900 | Edgepoint | 14.45 | 121.3307 | 0.75 | Terrestrial Optical Fiber Drop | 0.12 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3579 | 4 | 579 | 3579 | 0301404008 | Region III (Central Luzon) | Bulacan | Bocaue | Bundukan | 14.7896 | 120.9414 | U | 11633 | 3323 | 997 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01189 | Edgepoint | 14.7896 | 120.9485 | 0.77 | Terrestrial Optical Fiber Drop | 1.29 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3580 | 4 | 580 | 3580 | 1003502001 | Region X (Northern Mindanao) | Lanao del Norte | Baloi | Abaga | 8.1006 | 124.2153 | R | 4117 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLNG0003 | PTCI/MIDC | 8.1579 | 124.2035 | 5.86 | Terrestrial Optical Fiber Drop | 11.98 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3581 | 4 | 581 | 3581 | 0405811003 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 2 | 14.7001 | 121.1227 | U | 12514 | 3476 | 1043 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0045 | PTCI/MIDC | 14.675 | 121.1345 | 0.7 | Terrestrial Optical Fiber Drop | 1.63 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3582 | 4 | 582 | 3582 | 0305408005 | Region III (Central Luzon) | Pampanga | Lubao | Calangain | 14.8929 | 120.5517 | R | 3157 | 789 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030559 | FTAP Globe | 14.8918 | 120.5547 | 0.34 | Terrestrial Optical Fiber Drop | 2.01 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3583 | 4 | 583 | 3583 | 0301423021 | Region III (Central Luzon) | Bulacan | Santa Maria | Sta. Clara | 14.8226 | 120.95 | U | 12981 | 3708 | 1112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1597 | FTAP Smart | 14.8276 | 120.9809 | 0.59 | Terrestrial Optical Fiber Drop | 1.35 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3584 | 4 | 584 | 3584 | 0402115023 | Region IV-A (CALABARZON) | Cavite | Naic | Munting Mapino | 14.3353 | 120.772 | U | 5730 | 1685 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02145-C08 | PTCI/MIDC | 14.3426 | 120.7815 | 1.3 | Terrestrial Optical Fiber Drop | 1.52 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3585 | 4 | 585 | 3585 | 0704610027 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Pulantubig | 9.3242 | 123.2886 | R | 3117 | 820 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070264 | FTAP Globe | 9.3258 | 123.2903 | 0.26 | Terrestrial Optical Fiber Drop | 2.68 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3586 | 4 | 586 | 3586 | 0301404002 | Region III (Central Luzon) | Bulacan | Bocaue | Bagumbayan | 14.8076 | 120.9382 | R | 4038 | 1153 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01177 | Edgepoint | 14.8086 | 120.9275 | 0.46 | Terrestrial Optical Fiber Drop | 2.06 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3587 | 4 | 587 | 3587 | 0304927002 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Bonifacio District | 15.361 | 120.9423 | R | 3590 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03195-B07 | PTCI/MIDC | 15.3513 | 120.9393 | 1.07 | Terrestrial Optical Fiber Drop | 0.7 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3588 | 4 | 588 | 3588 | 0604530003 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Bagumbayan | 10.4604 | 122.8246 | R | 3767 | 1018 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060372 | FTAP Globe | 10.4155 | 122.8522 | 2.21 | Terrestrial Optical Fiber Drop | 0.64 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3589 | 4 | 589 | 3589 | 1903617112 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Rorogagus Proper | 8.0192 | 124.2824 | U | 5854 | 1027 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLSG0004 | PTCI/MIDC | 8.0153 | 124.2885 | 0.81 | Terrestrial Optical Fiber Drop | 1.36 | 0.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3590 | 4 | 590 | 3590 | 0301417020 | Region III (Central Luzon) | Bulacan | Plaridel | Sipat | 14.8979 | 120.8298 | U | 8176 | 2336 | 701 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0044 | PTCI/MIDC | 14.9011 | 120.8315 | 0.39 | Terrestrial Optical Fiber Drop | 2.29 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3591 | 4 | 591 | 3591 | 0403405029 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Masili | 14.1824 | 121.2003 | R | 4195 | 1271 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02048-C08 | PTCI/MIDC | 14.1818 | 121.2034 | 0.33 | Terrestrial Optical Fiber Drop | 4.54 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3592 | 4 | 592 | 3592 | 0403423011 | Region IV-A (CALABARZON) | Laguna | Rizal | Tuy | 14.113 | 121.3945 | R | 2025 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 1.41 | Terrestrial Optical Fiber Drop | 0.34 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3593 | 4 | 593 | 3593 | 1102404020 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Paligue | 6.6623 | 125.3573 | R | 3353 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110155 | FTAP BTS | 6.6594 | 125.3476 | 1.12 | Terrestrial Optical Fiber Drop | 3.32 | 0.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3594 | 4 | 594 | 3594 | 0403425029 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Lorenzo Ruiz | 14.3414 | 121.0435 | U | 6358 | 1926 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02060-C08 | PTCI/MIDC | 14.3343 | 121.0562 | 0.49 | Terrestrial Optical Fiber Drop | 0.49 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3595 | 4 | 595 | 3595 | 0203126012 | Region II (Cagayan Valley) | Isabela | Roxas | Vira | 17.1203 | 121.6138 | U | 3934 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0045 | PTCI/MIDC | 17.1242 | 121.6215 | 0.76 | Terrestrial Optical Fiber Drop | 0.51 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3596 | 4 | 596 | 3596 | 1401111011 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Sapid | 16.8535 | 120.7842 | R | 2956 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 1.11 | Terrestrial Optical Fiber Drop | 1.13 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3597 | 4 | 597 | 3597 | 0301407002 | Region III (Central Luzon) | Bulacan | Calumpit | Balungao | 14.8975 | 120.7646 | U | 5979 | 1708 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3210 | FTAP Smart | 14.8903 | 120.762 | 0.72 | Terrestrial Optical Fiber Drop | 1.04 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3598 | 4 | 598 | 3598 | 0330100032 | Region III (Central Luzon) | Pampanga | City of Angeles | Tabun | 15.1509 | 120.6153 | U | 14261 | 3961 | 1188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01543-B07 | PTCI/MIDC | 15.1477 | 120.6107 | 0.6 | Terrestrial Optical Fiber Drop | 1.19 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3599 | 4 | 599 | 3599 | 0301423019 | Region III (Central Luzon) | Bulacan | Santa Maria | San Jose Patag | 14.8246 | 120.98 | U | 14618 | 4176 | 1253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030592 | FTAP Globe | 14.8243 | 120.9817 | 0.18 | Terrestrial Optical Fiber Drop | 1.02 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3600 | 4 | 600 | 3600 | 0305415022 | Region III (Central Luzon) | Pampanga | Porac | Palat | 15.0424 | 120.5365 | R | 4696 | 1174 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N2962 | FTAP Smart | 15.0471 | 120.5325 | 0.67 | Terrestrial Optical Fiber Drop | 2.51 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3601 | 4 | 601 | 3601 | 0305407030 | Region III (Central Luzon) | Pampanga | Guagua | Santa Ursula | 14.9683 | 120.6508 | U | 6381 | 1595 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-00980 | Edgepoint | 14.9738 | 120.6394 | 1.37 | Terrestrial Optical Fiber Drop | 2.35 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3602 | 4 | 602 | 3602 | 0500506054 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 55 - Estanza | 13.1228 | 123.7291 | U | 5285 | 1289 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0013 | PTCI/MIDC | 13.1306 | 123.7233 | 1.07 | Terrestrial Optical Fiber Drop | 2.06 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3603 | 4 | 603 | 3603 | 0403411005 | Region IV-A (CALABARZON) | Laguna | Los Baños | Baybayin | 14.1797 | 121.2296 | R | 1607 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0016 | PTCI/MIDC | 14.1707 | 121.2412 | 0.56 | Terrestrial Optical Fiber Drop | 1.38 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3604 | 4 | 604 | 3604 | 0403403026 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Zapote | 14.3175 | 121.0812 | U | 16096 | 4877 | 1463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02008-C08 | PTCI/MIDC | 14.3164 | 121.0803 | 0.15 | Terrestrial Optical Fiber Drop | 2 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3605 | 4 | 605 | 3605 | 0305409007 | Region III (Central Luzon) | Pampanga | Mabalacat City | Dapdap | 15.2214 | 120.61 | U | 44239 | 11059 | 3318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00793 | Edgepoint | 15.2255 | 120.6073 | 0.54 | Terrestrial Optical Fiber Drop | 1 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3606 | 4 | 606 | 3606 | 0405801013 | Region IV-A (CALABARZON) | Rizal | Angono | Santo Niño | 14.5299 | 121.1538 | R | 2316 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | A00026-A04 | PTCI/MIDC | 14.5387 | 121.1581 | 0.73 | Terrestrial Optical Fiber Drop | 0.28 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3607 | 4 | 607 | 3607 | 0501707004 | Region V (Bicol Region) | Camarines Sur | Cabusao | Camagong | 13.7191 | 123.1075 | R | 1517 | 361 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050057 | FTAP Globe | 13.7244 | 123.1076 | 0.59 | Terrestrial Optical Fiber Drop | 1 | 10.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3608 | 4 | 608 | 3608 | 0105530015 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Imbalbalatong | 16.1203 | 120.554 | R | 2444 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 1.68 | Terrestrial Optical Fiber Drop | 1.24 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3609 | 4 | 609 | 3609 | 1630400062 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Mahogany Pob. | 8.9606 | 125.5508 | U | 6371 | 1553 | 466 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130071 | FTAP Globe | 8.9621 | 125.5348 | 1.77 | Terrestrial Optical Fiber Drop | 1.7 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3610 | 4 | 610 | 3610 | 0301417008 | Region III (Central Luzon) | Bulacan | Plaridel | Dampol | 14.8993 | 120.8196 | R | 3633 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030553 | FTAP Globe | 14.8967 | 120.8186 | 0.32 | Terrestrial Optical Fiber Drop | 3.35 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3611 | 4 | 611 | 3611 | 0501722024 | Region V (Bicol Region) | Camarines Sur | Minalabac | Tariric | 13.5747 | 123.2268 | R | 3075 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03151-C10 | PTCI/MIDC | 13.5781 | 123.2179 | 1.03 | Terrestrial Optical Fiber Drop | 1 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3612 | 4 | 612 | 3612 | 0506209007 | Region V (Bicol Region) | Sorsogon | Irosin | Carriedo | 12.6925 | 124.0319 | R | 3748 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 1.09 | Terrestrial Optical Fiber Drop | 1.16 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3613 | 4 | 613 | 3613 | 0403424056 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Lucas 1 | 14.0839 | 121.3253 | U | 6716 | 2035 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02377-C08 | PTCI/MIDC | 14.0812 | 121.3236 | 0.35 | Terrestrial Optical Fiber Drop | 1 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3614 | 4 | 614 | 3614 | 0402118012 | Region IV-A (CALABARZON) | Cavite | Silang | Cabangaan | 14.1649 | 121.0087 | R | 1636 | 481 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02159-C08 | PTCI/MIDC | 14.1651 | 120.9988 | 1.07 | Terrestrial Optical Fiber Drop | 1.31 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3615 | 4 | 615 | 3615 | 0908305002 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Bangkerohan | 7.7733 | 122.5909 | R | 4109 | 978 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZYG0003 | PTCI/MIDC | 7.7721 | 122.5856 | 0.6 | Terrestrial Optical Fiber Drop | 1.13 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3616 | 4 | 616 | 3616 | 0402109101 | Region IV-A (CALABARZON) | Cavite | City of Imus | Toclong II-B | 14.4408 | 120.9291 | R | 2513 | 739 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01870-C08 | PTCI/MIDC | 14.4428 | 120.9258 | 0.41 | Terrestrial Optical Fiber Drop | 2.15 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3617 | 4 | 617 | 3617 | 0405648026 | Region IV-A (CALABARZON) | Quezon | Tiaong | San Pedro | 13.9711 | 121.3014 | R | 2461 | 647 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040398 | FTAP Globe | 13.9797 | 121.2968 | 1.08 | Terrestrial Optical Fiber Drop | 1.01 | 2.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3618 | 4 | 618 | 3618 | 0401031038 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 7 | 14.1033 | 121.0788 | U | 5377 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1231 | FTAP Smart | 14.1042 | 121.1116 | 0.52 | Terrestrial Optical Fiber Drop | 2.14 | 6.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3619 | 4 | 619 | 3619 | 0500502033 | Region V (Bicol Region) | Albay | Camalig | Quirangay | 13.1954 | 123.6563 | R | 3565 | 869 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ALB-02100 | Edgepoint | 13.1885 | 123.6646 | 1.18 | Terrestrial Optical Fiber Drop | 2.09 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3620 | 4 | 620 | 3620 | 0401016035 | Region IV-A (CALABARZON) | Batangas | Mabini | Talaga East | 13.7312 | 120.9327 | R | 1869 | 519 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1356 | FTAP Smart | 13.7421 | 120.9389 | 1.16 | Terrestrial Optical Fiber Drop | 2.08 | 10.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3621 | 4 | 621 | 3621 | 1004302003 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Baliwagan | 8.7095 | 124.7841 | R | 3891 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0001 | PTCI/MIDC | 8.7178 | 124.7811 | 0.98 | Terrestrial Optical Fiber Drop | 4.54 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3622 | 4 | 622 | 3622 | 0304912006 | Region III (Central Luzon) | Nueva Ecija | Jaen | Lambakin | 15.3713 | 120.8593 | R | 4381 | 1251 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01471-B07 | PTCI/MIDC | 15.3687 | 120.8582 | 0.32 | Terrestrial Optical Fiber Drop | 1.01 | 7.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3623 | 4 | 623 | 3623 | 0402121007 | Region IV-A (CALABARZON) | Cavite | Ternate | San Juan I | 14.2965 | 120.7291 | R | 3016 | 887 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.26 | Terrestrial Optical Fiber Drop | 1.83 | 2.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3624 | 4 | 624 | 3624 | 0300809003 | Region III (Central Luzon) | Bataan | Orani | Bayan | 14.7902 | 120.5197 | U | 6663 | 1850 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030111 | FTAP BTS | 14.7936 | 120.5218 | 0.44 | Terrestrial Optical Fiber Drop | 2.23 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3625 | 4 | 625 | 3625 | 1401110010 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Lubas | 16.445 | 120.5995 | U | 7917 | 2262 | 679 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O28 | FTAP Smart | 16.4454 | 120.5915 | 0.85 | Terrestrial Optical Fiber Drop | 1.2 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3626 | 4 | 626 | 3626 | 0402106073 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel II | 14.3179 | 120.9527 | R | 2717 | 799 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02168-C08 | PTCI/MIDC | 14.2788 | 120.9146 | 0.73 | Terrestrial Optical Fiber Drop | 1.52 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3627 | 4 | 627 | 3627 | 0304906027 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | Latap | 15.7854 | 120.6716 | R | 2402 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01474-B07 | PTCI/MIDC | 15.7777 | 120.6688 | 0.9 | Terrestrial Optical Fiber Drop | 1.01 | 6.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3628 | 4 | 628 | 3628 | 0305416014 | Region III (Central Luzon) | Pampanga | City of San Fernando | Magliman | 15.0351 | 120.6647 | U | 7073 | 1768 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00919 | Edgepoint | 15.0369 | 120.6605 | 0.49 | Terrestrial Optical Fiber Drop | 1.65 | 0.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3629 | 4 | 629 | 3629 | 0704608008 | Region VII (Central Visayas) | Negros Oriental | City of Canlaon | Panubigan | 10.3802 | 123.238 | U | 7998 | 2104 | 631 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0018 | PTCI/MIDC | 10.3863 | 123.2275 | 1.34 | Terrestrial Optical Fiber Drop | 1.01 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3630 | 4 | 630 | 3630 | 0402101016 | Region IV-A (CALABARZON) | Cavite | Alfonso | Sikat | 14.0955 | 120.8881 | R | 2404 | 707 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02240-C08 | PTCI/MIDC | 14.096 | 120.881 | 0.76 | Terrestrial Optical Fiber Drop | 1.5 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3631 | 4 | 631 | 3631 | 0301409008 | Region III (Central Luzon) | Bulacan | Hagonoy | San Agustin | 14.8398 | 120.7421 | U | 10857 | 3102 | 931 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBUG0059 | PTCI/MIDC | 14.8374 | 120.7372 | 0.59 | Terrestrial Optical Fiber Drop | 1.01 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3632 | 4 | 632 | 3632 | 1102404002 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Balutakay | 6.7225 | 125.3444 | R | 3252 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110034 | FTAP BTS | 6.7312 | 125.3487 | 1.09 | Terrestrial Optical Fiber Drop | 2.81 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3633 | 4 | 633 | 3633 | 0403403006 | Region IV-A (CALABARZON) | Laguna | City of Biñan | De La Paz | 14.3482 | 121.085 | U | 35999 | 10908 | 3272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02055-C08 | PTCI/MIDC | 14.3485 | 121.0836 | 0.15 | Terrestrial Optical Fiber Drop | 1.46 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3634 | 4 | 634 | 3634 | 0401021004 | Region IV-A (CALABARZON) | Batangas | Rosario | Balibago | 13.8524 | 121.2826 | R | 2499 | 694 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040547 | FTAP Globe | 13.8427 | 121.2809 | 1.1 | Terrestrial Optical Fiber Drop | 2.23 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3635 | 4 | 635 | 3635 | 0330100010 | Region III (Central Luzon) | Pampanga | City of Angeles | Lourdes North West | 15.1454 | 120.5847 | U | 10500 | 2916 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01545-B07 | PTCI/MIDC | 15.1458 | 120.5866 | 0.2 | Terrestrial Optical Fiber Drop | 1.04 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3636 | 4 | 636 | 3636 | 0500509014 | Region V (Bicol Region) | Albay | Malilipot | San Isidro Iraya | 13.3314 | 123.7266 | U | 5434 | 1325 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0018 | PTCI/MIDC | 13.3386 | 123.7226 | 0.91 | Terrestrial Optical Fiber Drop | 2.43 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3637 | 4 | 637 | 3637 | 0803739029 | Region VIII (Eastern Visayas) | Leyte | Palo | San Joaquin | 11.1419 | 125.0049 | R | 2919 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 1.75 | Terrestrial Optical Fiber Drop | 1.02 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3638 | 4 | 638 | 3638 | 0402101010 | Region IV-A (CALABARZON) | Cavite | Alfonso | Luksuhin | 14.0934 | 120.881 | U | 5026 | 1478 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02240-C08 | PTCI/MIDC | 14.096 | 120.881 | 0.29 | Terrestrial Optical Fiber Drop | 1.03 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3639 | 4 | 639 | 3639 | 0304909003 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Balangkare Sur | 15.597 | 121.041 | R | 1646 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0050 | PTCI/MIDC | 15.5844 | 121.051 | 0.5 | Terrestrial Optical Fiber Drop | 1.25 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3640 | 4 | 640 | 3640 | 0403428011 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Malusak | 14.3142 | 121.1126 | U | 3185 | 965 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040181 | FTAP Globe | 14.3125 | 121.1123 | 0.19 | Terrestrial Optical Fiber Drop | 1.02 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3641 | 4 | 641 | 3641 | 0501718067 | Region V (Bicol Region) | Camarines Sur | Libmanan | Taban-Fundado | 13.6919 | 123.055 | R | 2176 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02007 | Edgepoint | 13.6955 | 123.0601 | 0.68 | Terrestrial Optical Fiber Drop | 1.01 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3642 | 4 | 642 | 3642 | 0403417035 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Poblacion III | 14.141 | 121.4133 | R | 2572 | 779 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040305 | FTAP Globe | 14.1176 | 121.4176 | 1.03 | Terrestrial Optical Fiber Drop | 0.47 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3643 | 4 | 643 | 3643 | 0401003048 | Region IV-A (CALABARZON) | Batangas | Balayan | Santol | 13.9412 | 120.7131 | R | 4267 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0870 | FTAP Smart | 13.9497 | 120.7097 | 1.01 | Terrestrial Optical Fiber Drop | 1.64 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3644 | 4 | 644 | 3644 | 0702214012 | Region VII (Central Visayas) | Cebu | City of Carcar | Poblacion I | 10.106 | 123.6314 | U | 10763 | 2832 | 850 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070019 | FTAP BTS | 10.1211 | 123.6452 | 2.26 | Terrestrial Optical Fiber Drop | 1.11 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3645 | 4 | 645 | 3645 | 1102509022 | Region XI (Davao Region) | Davao Oriental | City of Mati | Sainz | 6.9602 | 126.2244 | U | 10624 | 2951 | 885 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDLG0021 | PTCI/MIDC | 6.9597 | 126.2218 | 0.3 | Terrestrial Optical Fiber Drop | 1.63 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3646 | 4 | 646 | 3646 | 0504121019 | Region V (Bicol Region) | Masbate | Uson | Marcella | 12.246 | 123.7535 | R | 2122 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMSG0001 | PTCI/MIDC | 12.243 | 123.7468 | 0.8 | Terrestrial Optical Fiber Drop | 1.03 | 18.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3647 | 4 | 647 | 3647 | 1230800037 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas West | 6.1097 | 125.169 | U | 13554 | 3475 | 1043 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCR0011 | PTCI/MIDC | 6.1112 | 125.1712 | 0.29 | Terrestrial Optical Fiber Drop | 1.61 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3648 | 4 | 648 | 3648 | 1206511010 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | New Isabela | 6.6775 | 124.6733 | U | 10641 | 2800 | 840 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120131 | FTAP BTS | 6.6753 | 124.6699 | 0.44 | Terrestrial Optical Fiber Drop | 1.35 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3649 | 4 | 649 | 3649 | 1001321034 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Tugaya | 7.9091 | 125.094 | R | 2980 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 1.4 | Terrestrial Optical Fiber Drop | 0.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3650 | 4 | 650 | 3650 | 0301405004 | Region III (Central Luzon) | Bulacan | Bulacan | Matungao | 14.8051 | 120.8804 | U | 13536 | 3867 | 1160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01116-B07 | PTCI/MIDC | 14.8008 | 120.8762 | 0.65 | Terrestrial Optical Fiber Drop | 1.03 | 2.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3651 | 4 | 651 | 3651 | 0304928005 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Maliolio | 15.4208 | 120.9198 | R | 1749 | 499 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1331 | FTAP Smart | 15.4259 | 120.9264 | 0.9 | Terrestrial Optical Fiber Drop | 1.03 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3652 | 4 | 652 | 3652 | 0402101028 | Region IV-A (CALABARZON) | Cavite | Alfonso | Kaytitinga II | 14.1058 | 120.8385 | R | 1797 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040302 | FTAP Globe | 14.1248 | 120.8631 | 0.94 | Terrestrial Optical Fiber Drop | 3.91 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3653 | 4 | 653 | 3653 | 0403422002 | Region IV-A (CALABARZON) | Laguna | Pila | Bagong Pook | 14.2553 | 121.3693 | U | 5709 | 1730 | 519 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040217 | FTAP Globe | 14.2501 | 121.3549 | 1.65 | Terrestrial Optical Fiber Drop | 2.06 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3654 | 4 | 654 | 3654 | 0401031040 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Sambat | 14.0842 | 121.1387 | R | 4578 | 1271 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040334 | FTAP Globe | 14.0866 | 121.1381 | 0.28 | Terrestrial Optical Fiber Drop | 1.1 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3655 | 4 | 655 | 3655 | 0401003038 | Region IV-A (CALABARZON) | Batangas | Balayan | Navotas | 13.9309 | 120.7208 | R | 4235 | 1176 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040448 | FTAP Globe | 13.9369 | 120.728 | 1.02 | Terrestrial Optical Fiber Drop | 1.6 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3656 | 4 | 656 | 3656 | 0403417040 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | San Francisco | 14.1064 | 121.4235 | R | 3008 | 911 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040305 | FTAP Globe | 14.1176 | 121.4176 | 1.39 | Terrestrial Optical Fiber Drop | 3.34 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3657 | 4 | 657 | 3657 | 0603036001 | Region VI (Western Visayas) | Iloilo | Pavia | Aganan | 10.7639 | 122.5385 | U | 5042 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0057 | PTCI/MIDC | 10.7647 | 122.5323 | 0.63 | Terrestrial Optical Fiber Drop | 1.3 | 3.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3658 | 4 | 658 | 3658 | 0402104008 | Region IV-A (CALABARZON) | Cavite | Carmona | Lantic | 14.2976 | 121.05 | U | 26024 | 7654 | 2296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1183 | FTAP Smart | 14.3053 | 121.0487 | 0.86 | Terrestrial Optical Fiber Drop | 1.03 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3659 | 4 | 659 | 3659 | 1130700164 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 31-D | 7.0869 | 125.6128 | U | 8825 | 2595 | 779 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110454 | FTAP Globe | 7.185 | 125.4541 | 1.46 | Terrestrial Optical Fiber Drop | 0.98 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3660 | 4 | 660 | 3660 | 0604502020 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Poblacion | 10.5373 | 122.8368 | U | 12059 | 3259 | 978 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0105 | PTCI/MIDC | 10.5327 | 122.8386 | 0.55 | Terrestrial Optical Fiber Drop | 1.05 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3661 | 4 | 661 | 3661 | 1600307009 | Region XIII (Caraga) | Agusan del Sur | Rosario | Wasi-an | 8.3875 | 125.9775 | R | 4658 | 1194 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130096 | FTAP Globe | 8.3847 | 126.002 | 2.1 | Terrestrial Optical Fiber Drop | 3.13 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3662 | 4 | 662 | 3662 | 0401030025 | Region IV-A (CALABARZON) | Batangas | Talisay | Tumaway | 14.0926 | 121.028 | R | 3678 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B87 | FTAP Smart | 14.0935 | 121.0313 | 0.36 | Terrestrial Optical Fiber Drop | 1.03 | 6.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3663 | 4 | 663 | 3663 | 0604520014 | Region VI (Western Visayas) | Negros Occidental | Murcia | Damsite | 10.6206 | 123.0646 | R | 3347 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 1.49 | Terrestrial Optical Fiber Drop | 2.91 | 2.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3664 | 4 | 664 | 3664 | 0803708092 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Poblacion Zone 1 | 10.6677 | 124.8033 | R | 3204 | 843 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00117-D11 | PTCI/MIDC | 10.6643 | 124.807 | 1.58 | Terrestrial Optical Fiber Drop | 1.32 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3665 | 4 | 665 | 3665 | 1705206012 | MIMAROPA Region | Oriental Mindoro | Gloria | Kawit | 12.9572 | 121.487 | R | 2434 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 2.05 | Terrestrial Optical Fiber Drop | 1.05 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3666 | 4 | 666 | 3666 | 0731300021 | Region VII (Central Visayas) | Cebu | City of Mandaue | Pagsabungan | 10.3565 | 123.9405 | U | 20286 | 5796 | 1739 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CEB_0013 | LDIC | 10.3587 | 123.9368 | 0.49 | Terrestrial Optical Fiber Drop | 1.07 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3667 | 4 | 667 | 3667 | 0402119036 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Sungay North | 14.1237 | 120.9895 | R | 5155 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02242-C08 | PTCI/MIDC | 14.1289 | 121.0001 | 1.27 | Terrestrial Optical Fiber Drop | 1.07 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3668 | 4 | 668 | 3668 | 0702219020 | Region VII (Central Visayas) | Cebu | Consolacion | Tolotolo | 10.3893 | 123.9417 | R | 4164 | 1095 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070323 | FTAP Globe | 10.392 | 123.9426 | 0.31 | Terrestrial Optical Fiber Drop | 2.34 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3669 | 4 | 669 | 3669 | 0304903002 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Aduas Centro | 15.4984 | 120.9616 | U | 5576 | 1593 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030371 | FTAP Globe | 15.4982 | 120.9647 | 0.33 | Terrestrial Optical Fiber Drop | 1.86 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3670 | 4 | 670 | 3670 | 0307103006 | Region III (Central Luzon) | Zambales | Candelaria | Libertador | 15.6273 | 119.9235 | R | 1485 | 390 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 1.16 | Terrestrial Optical Fiber Drop | 1.04 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3671 | 4 | 671 | 3671 | 0702232018 | Region VII (Central Visayas) | Cebu | Minglanilla | Vito | 10.2543 | 123.7925 | U | 11385 | 2996 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0129 | PTCI/MIDC | 10.251 | 123.7892 | 0.51 | Terrestrial Optical Fiber Drop | 1.08 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3672 | 4 | 672 | 3672 | 0301418003 | Region III (Central Luzon) | Bulacan | Pulilan | Cutcot | 14.9042 | 120.8483 | U | 8697 | 2484 | 745 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01048 | Edgepoint | 14.9046 | 120.8412 | 0.88 | Terrestrial Optical Fiber Drop | 0.33 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3673 | 4 | 673 | 3673 | 0506212042 | Region V (Bicol Region) | Sorsogon | Matnog | Tablac | 12.5893 | 124.0914 | R | 1478 | 369 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050233 | FTAP Globe | 12.59 | 124.0937 | 0.26 | Terrestrial Optical Fiber Drop | 1.12 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3674 | 4 | 674 | 3674 | 0506204012 | Region V (Bicol Region) | Sorsogon | Bulusan | Sabang | 12.7478 | 124.1353 | R | 1335 | 333 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050224 | FTAP Globe | 12.7527 | 124.1332 | 0.59 | Terrestrial Optical Fiber Drop | 1.05 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3675 | 4 | 675 | 3675 | 0306916031 | Region III (Central Luzon) | Tarlac | City of Tarlac | Dalayap | 15.5295 | 120.604 | R | 4080 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03349-B07 | PTCI/MIDC | 15.5367 | 120.6101 | 1.03 | Terrestrial Optical Fiber Drop | 4.5 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3676 | 4 | 676 | 3676 | 0307708018 | Region III (Central Luzon) | Aurora | San Luis | Zarah | 15.7322 | 121.5244 | R | 2138 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F00886-B06 | PTCI/MIDC | 15.7199 | 121.5215 | 1.4 | Terrestrial Optical Fiber Drop | 1.05 | 2.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3677 | 4 | 677 | 3677 | 0402120037 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan III | 14.4044 | 120.8464 | R | 2229 | 655 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040133 | FTAP Globe | 14.3857 | 120.8304 | 0.79 | Terrestrial Optical Fiber Drop | 1.82 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3678 | 4 | 678 | 3678 | 0907322014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Dao | 7.8477 | 123.4288 | U | 6787 | 1740 | 522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0023 | PTCI/MIDC | 7.8446 | 123.4285 | 0.34 | Terrestrial Optical Fiber Drop | 2.2 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3679 | 4 | 679 | 3679 | 0306905033 | Region III (Central Luzon) | Tarlac | Concepcion | San Juan | 15.3538 | 120.605 | U | 5524 | 1416 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00750 | Edgepoint | 15.3614 | 120.6022 | 0.89 | Terrestrial Optical Fiber Drop | 1.47 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3680 | 4 | 680 | 3680 | 0304932025 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santa Lucia Young | 15.46 | 120.7952 | R | 4124 | 1178 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 1.42 | Terrestrial Optical Fiber Drop | 1.08 | 1.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3681 | 4 | 681 | 3681 | 0506209026 | Region V (Bicol Region) | Sorsogon | Irosin | Tabon-Tabon | 12.7035 | 124.0454 | R | 1655 | 413 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050226 | FTAP Globe | 12.7081 | 124.0387 | 0.89 | Terrestrial Optical Fiber Drop | 1.07 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3682 | 4 | 682 | 3682 | 0401029011 | Region IV-A (CALABARZON) | Batangas | Taal | Cultihan | 13.8916 | 120.9586 | R | 2051 | 569 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040522 | FTAP Globe | 13.8841 | 120.9487 | 1.35 | Terrestrial Optical Fiber Drop | 1.7 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3683 | 4 | 683 | 3683 | 0403403022 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Soro-soro | 14.3255 | 121.0612 | U | 7880 | 2387 | 716 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040171 | FTAP Globe | 14.3204 | 121.0566 | 0.76 | Terrestrial Optical Fiber Drop | 1.55 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3684 | 4 | 684 | 3684 | 0401031035 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 4 | 14.1034 | 121.0785 | U | 5389 | 1496 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040327 | FTAP Globe | 14.0929 | 121.1101 | 0.62 | Terrestrial Optical Fiber Drop | 2.17 | 6.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3685 | 4 | 685 | 3685 | 0704610001 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Bagacay | 9.3135 | 123.2888 | U | 9987 | 2628 | 788 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0062 | PTCI/MIDC | 9.2988 | 123.2874 | 0.73 | Terrestrial Optical Fiber Drop | 1.9 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3686 | 4 | 686 | 3686 | 0603034025 | Region VI (Western Visayas) | Iloilo | Oton | Rizal | 10.7498 | 122.4496 | R | 2308 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060051 | FTAP BTS | 10.7122 | 122.4778 | 1.24 | Terrestrial Optical Fiber Drop | 7.15 | 3.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3687 | 4 | 687 | 3687 | 0105514001 | Region I (Ilocos Region) | Pangasinan | Bolinao | Arnedo | 16.3827 | 119.8836 | U | 5848 | 1624 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00346 | Edgepoint | 16.3802 | 119.8939 | 1.13 | Terrestrial Optical Fiber Drop | 1.39 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3688 | 4 | 688 | 3688 | 0403417007 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Bambang | 14.1411 | 121.413 | R | 2381 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02122-C08 | PTCI/MIDC | 14.1344 | 121.4104 | 0.51 | Terrestrial Optical Fiber Drop | 0.5 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3689 | 4 | 689 | 3689 | 0402109033 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-F | 14.3651 | 120.9288 | R | 2816 | 828 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01908-C08 | PTCI/MIDC | 14.4012 | 120.9688 | 0.35 | Terrestrial Optical Fiber Drop | 2 | 7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3690 | 4 | 690 | 3690 | 0401014022 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Kayumanggi | 13.9233 | 121.161 | U | 7980 | 2216 | 665 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1502 | FTAP Smart | 13.9276 | 121.1571 | 0.63 | Terrestrial Optical Fiber Drop | 2.4 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3691 | 4 | 691 | 3691 | 0931700075 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Santa Catalina | 6.9088 | 122.0878 | U | 17353 | 4820 | 1446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0040 | PTCI/MIDC | 6.9123 | 122.0877 | 0.39 | Terrestrial Optical Fiber Drop | 1.56 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3692 | 4 | 692 | 3692 | 0301412012 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Libtong | 14.7442 | 120.9804 | U | 13319 | 3805 | 1142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01235 | Edgepoint | 14.7455 | 120.9814 | 0.18 | Terrestrial Optical Fiber Drop | 1.45 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3693 | 4 | 693 | 3693 | 0501724029 | Region V (Bicol Region) | Camarines Sur | City of Naga | Santa Cruz | 13.6263 | 123.182 | U | 7118 | 1694 | 508 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | I19 | FTAP Smart | 13.6234 | 123.1842 | 0.4 | Terrestrial Optical Fiber Drop | 1.29 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3694 | 4 | 694 | 3694 | 0631000021 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Bolilao | 10.7109 | 122.5544 | U | 5520 | 1314 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02811-D13 | PTCI/MIDC | 10.7107 | 122.5574 | 0.33 | Terrestrial Optical Fiber Drop | 1.52 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3695 | 4 | 695 | 3695 | 0203134009 | Region II (Cagayan Valley) | Isabela | Santa Maria | Mozzozzin Sur | 17.4586 | 121.7492 | R | 1994 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01365-B06 | PTCI/MIDC | 17.4743 | 121.7463 | 0.66 | Terrestrial Optical Fiber Drop | 1.89 | 3.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3696 | 4 | 696 | 3696 | 0631000151 | Region VI (Western Visayas) | Iloilo | City of Iloilo | San Isidro | 10.7371 | 122.5513 | U | 12141 | 2890 | 867 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0038 | PTCI/MIDC | 10.7327 | 122.5502 | 0.51 | Terrestrial Optical Fiber Drop | 1.93 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3697 | 4 | 697 | 3697 | 0402109030 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-C | 14.402 | 120.9404 | U | 7750 | 2279 | 684 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040107 | FTAP Globe | 14.424 | 120.9533 | 0.1 | Terrestrial Optical Fiber Drop | 0.56 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3698 | 4 | 698 | 3698 | 0401006002 | Region IV-A (CALABARZON) | Batangas | Bauan | Aplaya | 13.7817 | 121.0069 | U | 8070 | 2241 | 672 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1333 | FTAP Smart | 13.7875 | 121.0037 | 0.73 | Terrestrial Optical Fiber Drop | 1.51 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3699 | 4 | 699 | 3699 | 0402121011 | Region IV-A (CALABARZON) | Cavite | Ternate | Sapang II | 14.2826 | 120.7102 | R | 2194 | 645 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 1.38 | Terrestrial Optical Fiber Drop | 0.93 | 2.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3700 | 4 | 700 | 3700 | 0301420013 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin I | 14.8598 | 121.0546 | R | 4280 | 1222 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02716-B07 | PTCI/MIDC | 14.828 | 121.0701 | 0.36 | Terrestrial Optical Fiber Drop | 2.73 | 5.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3701 | 4 | 701 | 3701 | 0401004004 | Region IV-A (CALABARZON) | Batangas | Balete | Magapi | 14.0275 | 121.0984 | R | 2252 | 625 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 0.15 | Terrestrial Optical Fiber Drop | 1.06 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3702 | 4 | 702 | 3702 | 0401022003 | Region IV-A (CALABARZON) | Batangas | San Jose | Aya | 13.8943 | 121.1146 | U | 3921 | 1089 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040526 | FTAP Globe | 13.8797 | 121.1194 | 1.7 | Terrestrial Optical Fiber Drop | 1.98 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3703 | 4 | 703 | 3703 | 1430300006 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Happy Hollow | 16.4024 | 120.6251 | R | 2689 | 707 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0011 | LDIC | 16.4048 | 120.6219 | 0.43 | Terrestrial Optical Fiber Drop | 1.96 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3704 | 4 | 704 | 3704 | 0405645017 | Region IV-A (CALABARZON) | Quezon | Sariaya | Guisguis-Talon | 13.8678 | 121.5005 | R | 3907 | 1028 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTQZG0016 | PTCI/MIDC | 13.8738 | 121.5193 | 2.14 | Terrestrial Optical Fiber Drop | 1.11 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3705 | 4 | 705 | 3705 | 0401028006 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Antonio | 14.1186 | 121.1568 | U | 17251 | 4791 | 1437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03100-C08 | PTCI/MIDC | 13.8876 | 121.0401 | 1.21 | Terrestrial Optical Fiber Drop | 3.69 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3706 | 4 | 706 | 3706 | 0304903047 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Mabini Homesite | 15.4773 | 120.9763 | U | 5996 | 1713 | 514 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030388 | FTAP Globe | 15.476 | 120.9773 | 0.17 | Terrestrial Optical Fiber Drop | 1.7 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3707 | 4 | 707 | 3707 | 0102812024 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 35, Gabu Sur | 18.1881 | 120.5298 | R | 1843 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010012 | FTAP Globe | 18.2059 | 120.5796 | 1.06 | Terrestrial Optical Fiber Drop | 6.23 | 5.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3708 | 4 | 708 | 3708 | 1102414016 | Region XI (Davao Region) | Davao del Sur | Sulop | Palili | 6.613 | 125.3551 | R | 2077 | 610 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110531 | FTAP Globe | 6.6039 | 125.3444 | 1.56 | Terrestrial Optical Fiber Drop | 2.01 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3709 | 4 | 709 | 3709 | 0306904025 | Region III (Central Luzon) | Tarlac | Capas | Cristo Rey | 15.3583 | 120.5304 | U | 36855 | 9450 | 2835 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00753 | Edgepoint | 15.3588 | 120.5312 | 0.1 | Terrestrial Optical Fiber Drop | 1.06 | 6.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3710 | 4 | 710 | 3710 | 0300807015 | Region III (Central Luzon) | Bataan | Mariveles | Camaya | 14.4443 | 120.4802 | U | 19642 | 5456 | 1637 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030636 | FTAP Globe | 14.4411 | 120.489 | 1.01 | Terrestrial Optical Fiber Drop | 1.45 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3711 | 4 | 711 | 3711 | 0500508049 | Region V (Bicol Region) | Albay | City of Ligao | Tinago | 13.2481 | 123.5468 | R | 4822 | 1176 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 0.96 | Terrestrial Optical Fiber Drop | 1.57 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3712 | 4 | 712 | 3712 | 0301420046 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin II | 14.8597 | 121.0547 | R | 3687 | 1053 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02341 | Edgepoint | 14.7945 | 121.0843 | 0.18 | Terrestrial Optical Fiber Drop | 2.73 | 5.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3713 | 4 | 713 | 3713 | 0402103001 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Alima | 14.4584 | 120.9373 | U | 5936 | 1745 | 524 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040092 | FTAP Globe | 14.4604 | 120.9401 | 0.37 | Terrestrial Optical Fiber Drop | 1.81 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3714 | 4 | 714 | 3714 | 0305409010 | Region III (Central Luzon) | Pampanga | Mabalacat City | Duquit | 15.178 | 120.6001 | U | 14747 | 3686 | 1106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00814 | Edgepoint | 15.1779 | 120.6035 | 0.37 | Terrestrial Optical Fiber Drop | 1.33 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3715 | 4 | 715 | 3715 | 0105524014 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Banawang | 15.9129 | 120.4261 | R | 3244 | 901 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00532 | Edgepoint | 15.919 | 120.4212 | 0.86 | Terrestrial Optical Fiber Drop | 1.67 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3716 | 4 | 716 | 3716 | 0603007001 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Acuit | 10.8847 | 122.6963 | R | 2856 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060031 | FTAP BTS | 10.8748 | 122.7063 | 1.55 | Terrestrial Optical Fiber Drop | 1.81 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3717 | 4 | 717 | 3717 | 1130700086 | Region XI (Davao Region) | Davao del Sur | City of Davao | Pampanga | 7.1093 | 125.6355 | U | 16249 | 4779 | 1434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110471 | FTAP Globe | 7.1225 | 125.6535 | 0.79 | Terrestrial Optical Fiber Drop | 1.43 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3718 | 4 | 718 | 3718 | 0205004012 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Homestead | 16.3823 | 121.1056 | U | 4407 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0018 | PTCI/MIDC | 16.3833 | 121.1015 | 1.1 | Terrestrial Optical Fiber Drop | 1.02 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3719 | 4 | 719 | 3719 | 0301403004 | Region III (Central Luzon) | Bulacan | Baliuag | Catulinan | 14.9636 | 120.8804 | R | 2219 | 634 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01063-B07 | PTCI/MIDC | 14.9682 | 120.8795 | 0.52 | Terrestrial Optical Fiber Drop | 1.91 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3720 | 4 | 720 | 3720 | 0301404018 | Region III (Central Luzon) | Bulacan | Bocaue | Turo | 14.8076 | 120.9384 | U | 12401 | 3543 | 1063 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0222 | FTAP Smart | 14.8096 | 120.9368 | 0.27 | Terrestrial Optical Fiber Drop | 2.04 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3721 | 4 | 721 | 3721 | 0102809025 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Saludares | 18.0723 | 120.6863 | R | 1495 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 1.14 | Terrestrial Optical Fiber Drop | 3.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3722 | 4 | 722 | 3722 | 0600415012 | Region VI (Western Visayas) | Aklan | New Washington | Pinamuk-an | 11.6397 | 122.4296 | R | 2979 | 763 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 4.58 | Terrestrial Optical Fiber Drop | 1.07 | 6.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3723 | 4 | 723 | 3723 | 0603018019 | Region VI (Western Visayas) | Iloilo | Dumangas | Ermita | 10.8143 | 122.6904 | R | 3428 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060257 | FTAP Globe | 10.8222 | 122.684 | 1.12 | Terrestrial Optical Fiber Drop | 2.47 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3724 | 4 | 724 | 3724 | 1705110026 | MIMAROPA Region | Occidental Mindoro | San Jose | Labangan Poblacion | 12.3588 | 121.085 | U | 10120 | 2594 | 778 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1524 | FTAP Smart | 12.3767 | 121.0856 | 1.99 | Terrestrial Optical Fiber Drop | 2.38 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3725 | 4 | 725 | 3725 | 0600407001 | Region VI (Western Visayas) | Aklan | Kalibo | Andagaw | 11.7041 | 122.377 | U | 15878 | 4071 | 1221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKG0018 | PTCI/MIDC | 11.702 | 122.3757 | 0.28 | Terrestrial Optical Fiber Drop | 1.31 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3726 | 4 | 726 | 3726 | 1130700002 | Region XI (Davao Region) | Davao del Sur | City of Davao | Agdao | 7.0897 | 125.6275 | U | 7239 | 2129 | 639 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0124 | PTCI/MIDC | 7.0902 | 125.6281 | 0.09 | Terrestrial Optical Fiber Drop | 2.46 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3727 | 4 | 727 | 3727 | 1030500058 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Nazareth | 8.4728 | 124.6478 | U | 7097 | 1971 | 591 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLR0020 | PTCI/MIDC | 8.477 | 124.6501 | 0.53 | Terrestrial Optical Fiber Drop | 1.07 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3728 | 4 | 728 | 3728 | 0301410019 | Region III (Central Luzon) | Bulacan | City of Malolos | Canalate | 14.8417 | 120.8024 | R | 3796 | 1084 | 325 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01139 | Edgepoint | 14.8407 | 120.8008 | 0.21 | Terrestrial Optical Fiber Drop | 1.07 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3729 | 4 | 729 | 3729 | 0702252019 | Region VII (Central Visayas) | Cebu | Tuburan | Daan Lungsod | 10.7027 | 123.8372 | R | 2709 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0124 | PTCI/MIDC | 11.1643 | 123.9534 | 1.97 | Terrestrial Optical Fiber Drop | 19.04 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3730 | 4 | 730 | 3730 | 0405623008 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 5 | 14.1173 | 121.5502 | R | 2399 | 631 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1477 | FTAP Smart | 14.1083 | 121.5626 | 1.43 | Terrestrial Optical Fiber Drop | 0.94 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3731 | 4 | 731 | 3731 | 0401006011 | Region IV-A (CALABARZON) | Batangas | Bauan | Bolo | 13.7867 | 120.9767 | R | 4397 | 1221 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4095 | FTAP Smart | 13.7889 | 120.9729 | 0.48 | Terrestrial Optical Fiber Drop | 1.08 | 2.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3732 | 4 | 732 | 3732 | 0301405012 | Region III (Central Luzon) | Bulacan | Bulacan | San Nicolas | 14.7974 | 120.8681 | U | 6563 | 1875 | 563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00947-B07 | PTCI/MIDC | 14.7991 | 120.8681 | 0.19 | Terrestrial Optical Fiber Drop | 1.08 | 3.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3733 | 4 | 733 | 3733 | 0301412011 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Lawa | 14.7348 | 120.9778 | U | 16298 | 4656 | 1397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01082-B07 | PTCI/MIDC | 14.7352 | 120.9776 | 0.05 | Terrestrial Optical Fiber Drop | 1.08 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3734 | 4 | 734 | 3734 | 0105518012 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Caranglaan | 16.0313 | 120.3499 | U | 5927 | 1646 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010152 | FTAP Globe | 16.0323 | 120.3491 | 0.13 | Terrestrial Optical Fiber Drop | 2.4 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3735 | 4 | 735 | 3735 | 0330100015 | Region III (Central Luzon) | Pampanga | City of Angeles | Mining | 15.1419 | 120.607 | U | 5498 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02366-B07 | PTCI/MIDC | 15.1424 | 120.6059 | 0.13 | Terrestrial Optical Fiber Drop | 1.85 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3736 | 4 | 736 | 3736 | 0402103014 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino I | 14.4226 | 120.9757 | U | 17504 | 5148 | 1544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01864-C08 | PTCI/MIDC | 14.4276 | 120.9749 | 0.56 | Terrestrial Optical Fiber Drop | 1.08 | 3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3737 | 4 | 737 | 3737 | 0402109028 | Region IV-A (CALABARZON) | Cavite | City of Imus | Alapan II-B | 14.4155 | 120.919 | U | 4899 | 1440 | 432 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01882-C08 | PTCI/MIDC | 14.3986 | 120.9556 | 0.83 | Terrestrial Optical Fiber Drop | 2.52 | 2.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3738 | 4 | 738 | 3738 | 0402103041 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog II | 14.4233 | 120.9583 | U | 7505 | 2207 | 662 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01870-C08 | PTCI/MIDC | 14.4428 | 120.9258 | 0.36 | Terrestrial Optical Fiber Drop | 0.84 | 2.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3739 | 4 | 739 | 3739 | 0702231003 | Region VII (Central Visayas) | Cebu | Medellin | Daanlungsod | 11.1467 | 123.9499 | R | 3014 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0124 | PTCI/MIDC | 11.1643 | 123.9534 | 1.99 | Terrestrial Optical Fiber Drop | 1.74 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3740 | 4 | 740 | 3740 | 0304919017 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Imelda Valley | 15.5779 | 121.1225 | R | 2830 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00648 | Edgepoint | 15.5854 | 121.1205 | 0.86 | Terrestrial Optical Fiber Drop | 2.77 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3741 | 4 | 741 | 3741 | 0301410038 | Region III (Central Luzon) | Bulacan | City of Malolos | Panasahan | 14.8219 | 120.827 | U | 9913 | 2832 | 850 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02487 | Edgepoint | 14.8248 | 120.8221 | 0.61 | Terrestrial Optical Fiber Drop | 1.08 | 2.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3742 | 4 | 742 | 3742 | 0402103021 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas I | 14.4331 | 120.9746 | U | 8425 | 2477 | 743 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01902-C08 | PTCI/MIDC | 14.4427 | 120.9642 | 0.58 | Terrestrial Optical Fiber Drop | 1.33 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3743 | 4 | 743 | 3743 | 0401029044 | Region IV-A (CALABARZON) | Batangas | Taal | Seiran | 13.8866 | 120.9216 | R | 3104 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BAT_0004 | LDIC | 13.8858 | 120.9194 | 0.25 | Terrestrial Optical Fiber Drop | 1.23 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3744 | 4 | 744 | 3744 | 0831600117 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 84 | 11.1967 | 125.016 | U | 6818 | 1662 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0062 | PTCI/MIDC | 11.1957 | 125.0207 | 0.52 | Terrestrial Optical Fiber Drop | 1.89 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3745 | 4 | 745 | 3745 | 0402122014 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Lapidario | 14.2717 | 120.8671 | U | 13493 | 3968 | 1190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1119 | FTAP Smart | 14.2697 | 120.8684 | 0.25 | Terrestrial Optical Fiber Drop | 1.21 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3746 | 4 | 746 | 3746 | 1004302010 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Cogon | 8.7489 | 124.7713 | U | 7396 | 1896 | 569 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0002 | PTCI/MIDC | 8.7436 | 124.7779 | 0.93 | Terrestrial Optical Fiber Drop | 1.09 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3747 | 4 | 747 | 3747 | 0301407013 | Region III (Central Luzon) | Bulacan | Calumpit | Iba Este | 14.8912 | 120.7677 | U | 4349 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3210 | FTAP Smart | 14.8903 | 120.762 | 0.61 | Terrestrial Optical Fiber Drop | 1.68 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3748 | 4 | 748 | 3748 | 1600204010 | Region XIII (Caraga) | Agusan del Norte | Carmen | Rojales | 8.9815 | 125.276 | R | 3151 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0015 | PTCI/MIDC | 8.9888 | 125.2896 | 1.7 | Terrestrial Optical Fiber Drop | 1.48 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3749 | 4 | 749 | 3749 | 0402115001 | Region IV-A (CALABARZON) | Cavite | Naic | Bagong Karsada | 14.3101 | 120.7722 | R | 2176 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02212-C08 | PTCI/MIDC | 14.3059 | 120.7754 | 0.58 | Terrestrial Optical Fiber Drop | 1.29 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3750 | 4 | 750 | 3750 | 0301420014 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz I | 14.8562 | 121.0517 | U | 5074 | 1449 | 435 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030600 | FTAP Globe | 14.8098 | 121.0635 | 0.19 | Terrestrial Optical Fiber Drop | 2.23 | 5.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3751 | 4 | 751 | 3751 | 0305408001 | Region III (Central Luzon) | Pampanga | Lubao | Balantacan | 14.8973 | 120.5604 | R | 2644 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030559 | FTAP Globe | 14.8918 | 120.5547 | 0.87 | Terrestrial Optical Fiber Drop | 1.66 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3752 | 4 | 752 | 3752 | 0304926035 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 3rd | 15.8115 | 120.9749 | U | 10737 | 3067 | 920 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02434-B07 | PTCI/MIDC | 15.8097 | 120.9753 | 0.2 | Terrestrial Optical Fiber Drop | 2.33 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3753 | 4 | 753 | 3753 | 0105511029 | Region I (Ilocos Region) | Pangasinan | Bayambang | Hermoza | 15.7766 | 120.3948 | R | 3599 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00578 | Edgepoint | 15.7738 | 120.3905 | 0.55 | Terrestrial Optical Fiber Drop | 1.1 | 5.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3754 | 4 | 754 | 3754 | 0306906027 | Region III (Central Luzon) | Tarlac | Gerona | Pinasling | 15.6015 | 120.5893 | R | 3860 | 989 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00633 | Edgepoint | 15.6103 | 120.5971 | 1.28 | Terrestrial Optical Fiber Drop | 1.83 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3755 | 4 | 755 | 3755 | 0704610014 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Junob | 9.2916 | 123.2857 | U | 7966 | 2096 | 629 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0021 | PTCI/MIDC | 9.291 | 123.2842 | 0.18 | Terrestrial Optical Fiber Drop | 2.56 | 1.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3756 | 4 | 756 | 3756 | 0604520001 | Region VI (Western Visayas) | Negros Occidental | Murcia | Abo-abo | 10.5987 | 123.0648 | R | 3556 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 2.54 | Terrestrial Optical Fiber Drop | 2.63 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3757 | 4 | 757 | 3757 | 0405608019 | Region IV-A (CALABARZON) | Quezon | Candelaria | Pahinga Norte | 13.9163 | 121.4223 | U | 14495 | 3814 | 1144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1264 | FTAP Smart | 13.9179 | 121.4369 | 1.59 | Terrestrial Optical Fiber Drop | 1.31 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3758 | 4 | 758 | 3758 | 0401029002 | Region IV-A (CALABARZON) | Batangas | Taal | Balisong | 13.8788 | 120.9329 | R | 3638 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040527 | FTAP Globe | 13.8776 | 120.9277 | 0.57 | Terrestrial Optical Fiber Drop | 1.74 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3759 | 4 | 759 | 3759 | 0702219021 | Region VII (Central Visayas) | Cebu | Consolacion | Tugbongan | 10.3637 | 123.9618 | U | 8866 | 2333 | 700 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070009 | FTAP BTS | 10.3628 | 123.9625 | 0.12 | Terrestrial Optical Fiber Drop | 1.47 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3760 | 4 | 760 | 3760 | 0405810001 | Region IV-A (CALABARZON) | Rizal | Pililla | Bagumbayan | 14.4813 | 121.3258 | U | 12893 | 3581 | 1074 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040083 | FTAP Globe | 14.4816 | 121.327 | 0.13 | Terrestrial Optical Fiber Drop | 1.86 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3761 | 4 | 761 | 3761 | 0402103015 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Niog I | 14.4538 | 120.9582 | U | 5389 | 1585 | 476 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01864-C08 | PTCI/MIDC | 14.4276 | 120.9749 | 0.25 | Terrestrial Optical Fiber Drop | 0.37 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3762 | 4 | 762 | 3762 | 1102502013 | Region XI (Davao Region) | Davao Oriental | Banaybanay | San Vicente | 6.9982 | 125.9952 | U | 3065 | 851 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDLG0039 | PTCI/MIDC | 6.9759 | 126.023 | 0.29 | Terrestrial Optical Fiber Drop | 4.37 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3763 | 4 | 763 | 3763 | 1108204013 | Region XI (Davao Region) | Davao de Oro | Maco | Langgam | 7.355 | 125.8669 | R | 3506 | 947 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 0.44 | Terrestrial Optical Fiber Drop | 1.21 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3764 | 4 | 764 | 3764 | 0501608027 | Region V (Bicol Region) | Camarines Norte | Paracale | Tugos | 14.2714 | 122.7805 | U | 6044 | 1511 | 453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 1.18 | Terrestrial Optical Fiber Drop | 1.11 | 8.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3765 | 4 | 765 | 3765 | 0330100031 | Region III (Central Luzon) | Pampanga | City of Angeles | Sapangbato | 15.1682 | 120.5122 | U | 14529 | 4035 | 1211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00821 | Edgepoint | 15.1676 | 120.5106 | 0.18 | Terrestrial Optical Fiber Drop | 2.37 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3766 | 4 | 766 | 3766 | 0601914031 | Region VI (Western Visayas) | Capiz | City of Roxas | Jumaguicjic | 11.5019 | 122.7508 | R | 2882 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060231 | FTAP Globe | 11.5001 | 122.7634 | 1.39 | Terrestrial Optical Fiber Drop | 2.02 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3767 | 4 | 767 | 3767 | 0401001016 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Pook | 13.9311 | 120.9271 | R | 2881 | 800 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040476 | FTAP Globe | 13.9226 | 120.9218 | 1.1 | Terrestrial Optical Fiber Drop | 1.11 | 3.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3768 | 4 | 768 | 3768 | 0631000106 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Marcelo H. del Pilar | 10.6981 | 122.5495 | U | 3930 | 935 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0028 | PTCI/MIDC | 10.6971 | 122.5512 | 0.22 | Terrestrial Optical Fiber Drop | 1.11 | 2.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3769 | 4 | 769 | 3769 | 0701233001 | Region VII (Central Visayas) | Bohol | Panglao | Bil-isan | 9.595 | 123.7626 | R | 4041 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070148 | FTAP BTS | 9.5989 | 123.7684 | 0.78 | Terrestrial Optical Fiber Drop | 1.11 | 10.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3770 | 4 | 770 | 3770 | 0105508010 | Region I (Ilocos Region) | Pangasinan | Bani | Dacap Sur | 16.2371 | 119.8061 | R | 3048 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH010117 | FTAP Globe | 16.1982 | 119.7787 | 5.23 | Terrestrial Optical Fiber Drop | 1.11 | 5.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3771 | 4 | 771 | 3771 | 1400101022 | Cordillera Administrative Region (CAR) | Abra | Bangued | Santa Rosa | 17.5864 | 120.6072 | R | 2259 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00870-B05 | PTCI/MIDC | 17.5938 | 120.6095 | 0.86 | Terrestrial Optical Fiber Drop | 1.45 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3772 | 4 | 772 | 3772 | 1130700179 | Region XI (Davao Region) | Davao del Sur | City of Davao | Centro | 7.106 | 125.5628 | U | 16998 | 4999 | 1500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTDSR0039 | PTCI/MIDC | 7.0939 | 125.6361 | 0.26 | Terrestrial Optical Fiber Drop | 4.37 | 4.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3773 | 4 | 773 | 3773 | 0105506016 | Region I (Ilocos Region) | Pangasinan | Asingan | Poblacion East | 16.005 | 120.6662 | R | 2491 | 691 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.41 | Terrestrial Optical Fiber Drop | 0.39 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3774 | 4 | 774 | 3774 | 1102303003 | Region XI (Davao Region) | Davao del Norte | Carmen | Asuncion | 7.3537 | 125.6924 | R | 1891 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDNG0041 | PTCI/MIDC | 7.351 | 125.7028 | 1.18 | Terrestrial Optical Fiber Drop | 1.41 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3775 | 4 | 775 | 3775 | 0105538012 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Malanay | 16.01 | 120.4127 | R | 2786 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01764-B07 | PTCI/MIDC | 16.0018 | 120.4132 | 0.91 | Terrestrial Optical Fiber Drop | 2.73 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3776 | 4 | 776 | 3776 | 0304923028 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion Sur | 15.713 | 121.1037 | U | 3532 | 981 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 1.58 | Terrestrial Optical Fiber Drop | 0.23 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3777 | 4 | 777 | 3777 | 0301420027 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Guijo | 14.8144 | 121.0617 | U | 7288 | 2082 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02217 | Edgepoint | 14.816 | 121.059 | 0.34 | Terrestrial Optical Fiber Drop | 1.11 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3778 | 4 | 778 | 3778 | 0405804024 | Region IV-A (CALABARZON) | Rizal | Binangonan | Macamot | 14.4864 | 121.1971 | U | 9861 | 2739 | 822 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040082 | FTAP Globe | 14.4877 | 121.1969 | 0.15 | Terrestrial Optical Fiber Drop | 1.28 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3779 | 4 | 779 | 3779 | 1705209031 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Sta. Isabel | 13.0452 | 121.4824 | R | 2937 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMRG0011 | PTCI/MIDC | 13.0381 | 121.4907 | 2.43 | Terrestrial Optical Fiber Drop | 0.83 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3780 | 4 | 780 | 3780 | 0330100018 | Region III (Central Luzon) | Pampanga | City of Angeles | Pandan | 15.1521 | 120.6042 | U | 24989 | 6941 | 2082 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1109 | FTAP Smart | 15.1503 | 120.6022 | 0.3 | Terrestrial Optical Fiber Drop | 1.31 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3781 | 4 | 781 | 3781 | 0305415001 | Region III (Central Luzon) | Pampanga | Porac | Babo Pangulo | 15.076 | 120.5326 | R | 4287 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 1.01 | Terrestrial Optical Fiber Drop | 1.71 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3782 | 4 | 782 | 3782 | 0301406002 | Region III (Central Luzon) | Bulacan | Bustos | Bonga Menor | 14.9499 | 120.9339 | U | 5541 | 1583 | 475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01102-B07 | PTCI/MIDC | 14.9447 | 120.9241 | 1.21 | Terrestrial Optical Fiber Drop | 1.73 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3783 | 4 | 783 | 3783 | 0105547009 | Region I (Ilocos Region) | Pangasinan | Villasis | Lipay | 15.8998 | 120.6051 | R | 3790 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_PNG_0011 | LDIC | 120.608 | 15.9085 | 1.01 | Terrestrial Optical Fiber Drop | 2.76 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3784 | 4 | 784 | 3784 | 0702223041 | Region VII (Central Visayas) | Cebu | Danao City | Taboc | 10.5295 | 124.014 | U | 7136 | 1877 | 563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0080 | PTCI/MIDC | 10.5228 | 124.0089 | 0.94 | Terrestrial Optical Fiber Drop | 1.6 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3785 | 4 | 785 | 3785 | 0500508015 | Region V (Bicol Region) | Albay | City of Ligao | Bonga | 13.2274 | 123.5471 | R | 3778 | 921 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 1.93 | Terrestrial Optical Fiber Drop | 1.85 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3786 | 4 | 786 | 3786 | 0401032007 | Region IV-A (CALABARZON) | Batangas | Taysan | Mabayabas | 13.7942 | 121.2002 | R | 2489 | 691 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01959-C08 | PTCI/MIDC | 13.7986 | 121.1878 | 1.43 | Terrestrial Optical Fiber Drop | 1.11 | 5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3787 | 4 | 787 | 3787 | 0305404005 | Region III (Central Luzon) | Pampanga | Bacolor | Calibutbut | 15.1024 | 120.6055 | U | 13476 | 3369 | 1011 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01592-B07 | PTCI/MIDC | 15.099 | 120.6052 | 0.37 | Terrestrial Optical Fiber Drop | 1.32 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3788 | 4 | 788 | 3788 | 0402109099 | Region IV-A (CALABARZON) | Cavite | City of Imus | Toclong I-B | 14.4407 | 120.9292 | R | 1821 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040154 | FTAP Globe | 14.3448 | 121.0163 | 0.14 | Terrestrial Optical Fiber Drop | 2.14 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3789 | 4 | 789 | 3789 | 0702227004 | Region VII (Central Visayas) | Cebu | Liloan | Cotcot | 10.4333 | 123.9929 | U | 10837 | 2851 | 855 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0104 | PTCI/MIDC | 10.4246 | 123.9957 | 1.01 | Terrestrial Optical Fiber Drop | 1.96 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3790 | 4 | 790 | 3790 | 1102404013 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Leling | 6.7104 | 125.3612 | R | 3293 | 968 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110148 | FTAP BTS | 6.7172 | 125.366 | 0.93 | Terrestrial Optical Fiber Drop | 3.1 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3791 | 4 | 791 | 3791 | 1600210002 | Region XIII (Caraga) | Agusan del Norte | Santiago | Curva | 9.2669 | 125.5589 | R | 2949 | 719 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 1.54 | Terrestrial Optical Fiber Drop | 0.05 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3792 | 4 | 792 | 3792 | 0330100011 | Region III (Central Luzon) | Pampanga | City of Angeles | Lourdes Sur | 15.1447 | 120.5924 | U | 5095 | 1415 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-03111 | Edgepoint | 15.1538 | 120.5756 | 0.66 | Terrestrial Optical Fiber Drop | 0.76 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3793 | 4 | 793 | 3793 | 0403425024 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Fatima | 14.3419 | 121.044 | U | 7115 | 2156 | 647 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LAG-03143 | Edgepoint | 14.334 | 121.0524 | 0.49 | Terrestrial Optical Fiber Drop | 0.49 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3794 | 4 | 794 | 3794 | 0501705035 | Region V (Bicol Region) | Camarines Sur | Buhi | Santa Clara | 13.4161 | 123.5144 | R | 2687 | 639 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 0.95 | Terrestrial Optical Fiber Drop | 0.03 | 10.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3795 | 4 | 795 | 3795 | 0300809010 | Region III (Central Luzon) | Bataan | Orani | Mulawin | 14.8015 | 120.5194 | R | 4958 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030604 | FTAP Globe | 14.8 | 120.5202 | 2.15 | Terrestrial Optical Fiber Drop | 1.82 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3796 | 4 | 796 | 3796 | 0300803015 | Region III (Central Luzon) | Bataan | City of Balanga | Pto. Rivas Itaas | 14.6899 | 120.5564 | R | 1903 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01375 | Edgepoint | 14.6877 | 120.5554 | 0.27 | Terrestrial Optical Fiber Drop | 1.37 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3797 | 4 | 797 | 3797 | 1102315005 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Cagangohan | 7.2798 | 125.6827 | U | 13446 | 3634 | 1090 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110445 | FTAP Globe | 7.2802 | 125.6816 | 0.13 | Terrestrial Optical Fiber Drop | 2.33 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3798 | 4 | 798 | 3798 | 0301418037 | Region III (Central Luzon) | Bulacan | Pulilan | Tinejero | 14.9038 | 120.848 | U | 4341 | 1240 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01118-B07 | PTCI/MIDC | 14.9024 | 120.8479 | 1.22 | Terrestrial Optical Fiber Drop | 0.33 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3799 | 4 | 799 | 3799 | 0301422032 | Region III (Central Luzon) | Bulacan | San Rafael | Tambubong | 14.9689 | 120.9263 | U | 8068 | 2305 | 692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02974-B07 | PTCI/MIDC | 14.9693 | 120.928 | 0.19 | Terrestrial Optical Fiber Drop | 1.57 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3800 | 4 | 800 | 3800 | 0405803010 | Region IV-A (CALABARZON) | Rizal | Baras | Pinugay | 14.6225 | 121.2625 | U | 48448 | 13457 | 4037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-RIZ-01651 | Edgepoint | 14.609 | 121.2609 | 1.52 | Terrestrial Optical Fiber Drop | 1.12 | 8.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3801 | 4 | 801 | 3801 | 0731300020 | Region VII (Central Visayas) | Cebu | City of Mandaue | Pakna-an | 10.345 | 123.9585 | U | 30563 | 8732 | 2620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0214 | PTCI/MIDC | 10.352 | 123.9517 | 1.07 | Terrestrial Optical Fiber Drop | 1.3 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3802 | 4 | 802 | 3802 | 0702227010 | Region VII (Central Visayas) | Cebu | Liloan | San Vicente | 10.3992 | 123.9761 | U | 13364 | 3516 | 1055 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0238 | PTCI/MIDC | 10.3973 | 123.9805 | 0.53 | Terrestrial Optical Fiber Drop | 2.55 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3803 | 4 | 803 | 3803 | 0330100006 | Region III (Central Luzon) | Pampanga | City of Angeles | Cuayan | 15.1476 | 120.5487 | U | 15713 | 4364 | 1309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02353-B07 | PTCI/MIDC | 15.1471 | 120.5498 | 0.13 | Terrestrial Optical Fiber Drop | 1.14 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3804 | 4 | 804 | 3804 | 0105526016 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Lanas | 16.0775 | 120.3867 | R | 3366 | 935 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 1.32 | Terrestrial Optical Fiber Drop | 1.99 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3805 | 4 | 805 | 3805 | 0403404019 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Tres | 14.2766 | 121.1269 | U | 4685 | 1419 | 426 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040222 | FTAP Globe | 14.2428 | 121.1232 | 0.89 | Terrestrial Optical Fiber Drop | 1.97 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3806 | 4 | 806 | 3806 | 0403426004 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Calios | 14.275 | 121.4029 | U | 11052 | 3349 | 1005 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040201 | FTAP Globe | 14.2743 | 121.4075 | 0.49 | Terrestrial Optical Fiber Drop | 1.19 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3807 | 4 | 807 | 3807 | 0304903072 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | San Josef Sur | 15.4779 | 120.9474 | U | 8485 | 2424 | 727 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N2096 | FTAP Smart | 15.478 | 120.9538 | 0.68 | Terrestrial Optical Fiber Drop | 1.53 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3808 | 4 | 808 | 3808 | 0401003001 | Region IV-A (CALABARZON) | Batangas | Balayan | Baclaran | 13.9298 | 120.7721 | R | 2753 | 764 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040445 | FTAP Globe | 13.9391 | 120.7656 | 1.24 | Terrestrial Optical Fiber Drop | 2.04 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3809 | 4 | 809 | 3809 | 0305408019 | Region III (Central Luzon) | Pampanga | Lubao | San Juan | 14.9246 | 120.5688 | R | 2744 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03224-B07 | PTCI/MIDC | 14.9164 | 120.5576 | 0.53 | Terrestrial Optical Fiber Drop | 2.21 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3810 | 4 | 810 | 3810 | 0306902007 | Region III (Central Luzon) | Tarlac | Bamban | Lourdes | 15.2796 | 120.526 | U | 6958 | 1784 | 535 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-02239 | Edgepoint | 15.2783 | 120.5204 | 0.62 | Terrestrial Optical Fiber Drop | 1.14 | 1.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3811 | 4 | 811 | 3811 | 0403424066 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Ana | 14.0089 | 121.3261 | R | 3207 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02127-C08 | PTCI/MIDC | 13.9949 | 121.3333 | 1.73 | Terrestrial Optical Fiber Drop | 4.27 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3812 | 4 | 812 | 3812 | 0402109037 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-D | 14.3736 | 120.9415 | U | 5551 | 1632 | 490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1177 | FTAP Smart | 14.3766 | 120.9425 | 0.35 | Terrestrial Optical Fiber Drop | 1.14 | 7.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3813 | 4 | 813 | 3813 | 0402106036 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel | 14.3384 | 120.9497 | R | 4335 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0020 | PTCI/MIDC | 14.3098 | 120.9862 | 0.6 | Terrestrial Optical Fiber Drop | 1.74 | 4.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3814 | 4 | 814 | 3814 | 0402119014 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Neogan | 14.0984 | 120.8941 | U | 3541 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02152-C08 | PTCI/MIDC | 14.095 | 120.9042 | 1.15 | Terrestrial Optical Fiber Drop | 2.15 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3815 | 4 | 815 | 3815 | 0403424051 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Isidro | 13.9846 | 121.3094 | R | 4672 | 1415 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040398 | FTAP Globe | 13.9797 | 121.2968 | 1.47 | Terrestrial Optical Fiber Drop | 1.13 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3816 | 4 | 816 | 3816 | 0306917026 | Region III (Central Luzon) | Tarlac | Victoria | Santa Barbara | 15.5779 | 120.6885 | U | 6088 | 1561 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00655 | Edgepoint | 15.5757 | 120.6851 | 0.44 | Terrestrial Optical Fiber Drop | 1.13 | 6.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3817 | 4 | 817 | 3817 | 0501732012 | Region V (Bicol Region) | Camarines Sur | San Fernando | Grijalvo | 13.5489 | 123.1343 | R | 2456 | 584 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 1.57 | Terrestrial Optical Fiber Drop | 1.47 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3818 | 4 | 818 | 3818 | 0102906008 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Bagani Ubbog | 17.192 | 120.4589 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILS-00161 | Edgepoint | 17.1934 | 120.4516 | 0.79 | Terrestrial Optical Fiber Drop | 1.3 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3819 | 4 | 819 | 3819 | 0105535004 | Region I (Ilocos Region) | Pangasinan | San Manuel | Cabaritan | 16.0522 | 120.654 | R | 2420 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010143 | FTAP Globe | 16.0623 | 120.6491 | 1.24 | Terrestrial Optical Fiber Drop | 2.18 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3820 | 4 | 820 | 3820 | 1600301009 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Marcelina | 8.6919 | 125.7596 | R | 3906 | 1001 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0001 | PTCI/MIDC | 8.7141 | 125.7595 | 1.67 | Terrestrial Optical Fiber Drop | 2.43 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3821 | 4 | 821 | 3821 | 0501728021 | Region V (Bicol Region) | Camarines Sur | Pili | San Juan | 13.5761 | 123.2861 | R | 2091 | 497 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0710 | FTAP Smart | 13.5587 | 123.2775 | 1.35 | Terrestrial Optical Fiber Drop | 1.9 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3822 | 4 | 822 | 3822 | 0205011010 | Region II (Cagayan Valley) | Nueva Vizcaya | Quezon | Runruno | 16.4865 | 121.2966 | U | 4953 | 1303 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01537-B05 | PTCI/MIDC | 16.4937 | 121.2937 | 0.86 | Terrestrial Optical Fiber Drop | 1.14 | 8.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3823 | 4 | 823 | 3823 | 0403407015 | Region IV-A (CALABARZON) | Laguna | Cavinti | Poblacion | 14.2456 | 121.5098 | U | 7340 | 2224 | 667 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040218 | FTAP Globe | 14.2498 | 121.5044 | 0.76 | Terrestrial Optical Fiber Drop | 1.14 | 6.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3824 | 4 | 824 | 3824 | 0402118057 | Region IV-A (CALABARZON) | Cavite | Silang | Hoyo | 14.1956 | 121.0063 | R | 2552 | 750 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02221-C08 | PTCI/MIDC | 14.1843 | 121.0128 | 1.44 | Terrestrial Optical Fiber Drop | 1.15 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3825 | 4 | 825 | 3825 | 0301415006 | Region III (Central Luzon) | Bulacan | Pandi | Cacarong Bata | 14.9036 | 120.9673 | U | 15301 | 4371 | 1311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030556 | FTAP Globe | 14.8934 | 120.9692 | 1.16 | Terrestrial Optical Fiber Drop | 1.54 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3826 | 4 | 826 | 3826 | 0501724011 | Region V (Bicol Region) | Camarines Sur | City of Naga | Dayangdang | 13.6292 | 123.2099 | U | 4120 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0712 | FTAP Smart | 13.6196 | 123.2243 | 0.67 | Terrestrial Optical Fiber Drop | 1.17 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3827 | 4 | 827 | 3827 | 0402119006 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Iruhin West | 14.1389 | 121.0004 | R | 3589 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03123-C08 | PTCI/MIDC | 14.1386 | 121.0001 | 0.05 | Terrestrial Optical Fiber Drop | 2.61 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3828 | 4 | 828 | 3828 | 0105525004 | Region I (Ilocos Region) | Pangasinan | Manaoag | Baritao | 16.0396 | 120.4748 | U | 5621 | 1561 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010146 | FTAP Globe | 16.0483 | 120.4791 | 1.07 | Terrestrial Optical Fiber Drop | 1.15 | 6.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3829 | 4 | 829 | 3829 | 0304903071 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | San Josef Norte | 15.4786 | 120.9476 | R | 5105 | 1458 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N2096 | FTAP Smart | 15.478 | 120.9538 | 0.67 | Terrestrial Optical Fiber Drop | 1.49 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3830 | 4 | 830 | 3830 | 0105525036 | Region I (Ilocos Region) | Pangasinan | Manaoag | Pantal | 16.0348 | 120.4856 | R | 3236 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02431 | Edgepoint | 16.0356 | 120.4927 | 0.77 | Terrestrial Optical Fiber Drop | 1.15 | 6.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3831 | 4 | 831 | 3831 | 0402103027 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row East | 14.3976 | 120.9897 | U | 19338 | 5687 | 1706 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00454-A03 | PTCI/MIDC | 14.4461 | 120.9843 | 0.92 | Terrestrial Optical Fiber Drop | 1.29 | 4.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3832 | 4 | 832 | 3832 | 0301415007 | Region III (Central Luzon) | Bulacan | Pandi | Cacarong Matanda | 14.9036 | 120.9673 | U | 13060 | 3731 | 1119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030556 | FTAP Globe | 14.8934 | 120.9692 | 1.16 | Terrestrial Optical Fiber Drop | 1.55 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3833 | 4 | 833 | 3833 | 0105546018 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Dilan Paurido | 15.9747 | 120.5817 | U | 7450 | 2069 | 621 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTPNG0001 | PTCI/MIDC | 15.9724 | 120.5856 | 0.49 | Terrestrial Optical Fiber Drop | 1.82 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3834 | 4 | 834 | 3834 | 1102401018 | Region XI (Davao Region) | Davao del Sur | Bansalan | Poblacion | 6.7799 | 125.216 | U | 7026 | 2066 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110274 | FTAP BTS | 6.7794 | 125.2171 | 0.14 | Terrestrial Optical Fiber Drop | 1.15 | 16.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3835 | 4 | 835 | 3835 | 0405801001 | Region IV-A (CALABARZON) | Rizal | Angono | Bagumbayan | 14.5294 | 121.1536 | R | 2660 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040061 | FTAP Globe | 14.5317 | 121.1643 | 0.05 | Terrestrial Optical Fiber Drop | 0.24 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3836 | 4 | 836 | 3836 | 0501708009 | Region V (Bicol Region) | Camarines Sur | Calabanga | Bonot-Santa Rosa | 13.7415 | 123.2608 | R | 4101 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-02606 | Edgepoint | 13.7165 | 123.2373 | 1.12 | Terrestrial Optical Fiber Drop | 1.26 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3837 | 4 | 837 | 3837 | 0105506014 | Region I (Ilocos Region) | Pangasinan | Asingan | Macalong | 16.0109 | 120.6602 | R | 3976 | 1104 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.7 | Terrestrial Optical Fiber Drop | 1.21 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3838 | 4 | 838 | 3838 | 0501737040 | Region V (Bicol Region) | Camarines Sur | Tinambac | Sogod | 13.826 | 123.3231 | R | 3928 | 935 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-01993 | Edgepoint | 123.3311 | 13.8166 | 1.36 | Terrestrial Optical Fiber Drop | 1.99 | 1.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3839 | 4 | 839 | 3839 | 1430300005 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Bakakeng North | 16.3908 | 120.5944 | U | 10928 | 2875 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBEG0031 | PTCI/MIDC | 16.3866 | 120.5921 | 0.53 | Terrestrial Optical Fiber Drop | 1.28 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3840 | 4 | 840 | 3840 | 0203129003 | Region II (Cagayan Valley) | Isabela | San Isidro | Gomez | 16.7355 | 121.6408 | R | 3155 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01277-B06 | PTCI/MIDC | 16.7371 | 121.6452 | 0.5 | Terrestrial Optical Fiber Drop | 1.15 | 4.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3841 | 4 | 841 | 3841 | 0403422012 | Region IV-A (CALABARZON) | Laguna | Pila | Pinagbayanan | 14.2498 | 121.36 | U | 6680 | 2024 | 607 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040217 | FTAP Globe | 14.2501 | 121.3549 | 0.54 | Terrestrial Optical Fiber Drop | 1.55 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3842 | 4 | 842 | 3842 | 0401019002 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Balaytigui | 14.1315 | 120.5976 | R | 4708 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040298 | FTAP Globe | 14.1309 | 120.5971 | 0.09 | Terrestrial Optical Fiber Drop | 1.15 | 6.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3843 | 4 | 843 | 3843 | 0731300007 | Region VII (Central Visayas) | Cebu | City of Mandaue | Canduman | 10.3684 | 123.9351 | U | 23479 | 6708 | 2012 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070002 | FTAP BTS | 10.3689 | 123.94 | 0.55 | Terrestrial Optical Fiber Drop | 1.73 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3844 | 4 | 844 | 3844 | 1600301029 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Bucac | 8.7001 | 125.7499 | R | 4733 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0001 | PTCI/MIDC | 8.7141 | 125.7595 | 1.88 | Terrestrial Optical Fiber Drop | 1.66 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3845 | 4 | 845 | 3845 | 0103301040 | Region I (Ilocos Region) | La Union | Agoo | Santa Ana | 16.3224 | 120.366 | R | 2096 | 566 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00360 | Edgepoint | 16.3212 | 120.351 | 0.66 | Terrestrial Optical Fiber Drop | 0.3 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3846 | 4 | 846 | 3846 | 1705215016 | MIMAROPA Region | Oriental Mindoro | Victoria | Ordovilla | 13.1716 | 121.2672 | R | 2229 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03226-C09 | PTCI/MIDC | 13.1756 | 121.2763 | 1.09 | Terrestrial Optical Fiber Drop | 1.46 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3847 | 4 | 847 | 3847 | 0102906031 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Paypayad | 17.1797 | 120.4329 | R | 2432 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILS-00166 | Edgepoint | 17.1778 | 120.4313 | 0.27 | Terrestrial Optical Fiber Drop | 1.99 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3848 | 4 | 848 | 3848 | 0702208012 | Region VII (Central Visayas) | Cebu | Balamban | Cantuod | 10.5157 | 123.7274 | R | 5099 | 1341 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0009 | PTCI/MIDC | 10.5104 | 123.7272 | 0.59 | Terrestrial Optical Fiber Drop | 1.61 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3849 | 4 | 849 | 3849 | 0403403011 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Loma | 14.2878 | 121.0668 | U | 14325 | 4340 | 1302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02004-C08 | PTCI/MIDC | 14.287 | 121.0672 | 0.1 | Terrestrial Optical Fiber Drop | 1.16 | 2.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3850 | 4 | 850 | 3850 | 0105538008 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Dalongue | 16.0027 | 120.389 | R | 2046 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTPNG0005 | PTCI/MIDC | 16.0077 | 120.3999 | 1.29 | Terrestrial Optical Fiber Drop | 1.33 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3851 | 4 | 851 | 3851 | 0630200004 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 1 | 10.6835 | 122.9534 | U | 5641 | 1566 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0108 | PTCI/MIDC | 10.6512 | 122.9723 | 0.44 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3852 | 4 | 852 | 3852 | 0304929029 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Sagaba | 15.6023 | 120.8748 | R | 3852 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00640 | Edgepoint | 15.5955 | 120.8796 | 0.92 | Terrestrial Optical Fiber Drop | 1.17 | 4.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3853 | 4 | 853 | 3853 | 0701242005 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Dao | 9.6727 | 123.8704 | U | 10836 | 2709 | 813 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0043 | PTCI/MIDC | 9.6775 | 123.872 | 0.56 | Terrestrial Optical Fiber Drop | 2.79 | 1.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3854 | 4 | 854 | 3854 | 0402106039 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Simon | 14.3213 | 120.9714 | U | 6571 | 1932 | 580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01921-C08 | PTCI/MIDC | 14.3223 | 120.9722 | 0.13 | Terrestrial Optical Fiber Drop | 1.17 | 2.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3855 | 4 | 855 | 3855 | 0501706002 | Region V (Bicol Region) | Camarines Sur | Bula | Bagumbayan | 13.4821 | 123.2779 | R | 2210 | 526 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 1.08 | Terrestrial Optical Fiber Drop | 1.17 | 4.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3856 | 4 | 856 | 3856 | 0704604018 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Lo-oc | 9.5885 | 123.1348 | R | 2648 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070256 | FTAP Globe | 9.5841 | 123.1354 | 0.5 | Terrestrial Optical Fiber Drop | 1.27 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3857 | 4 | 857 | 3857 | 0704619016 | Region VII (Central Visayas) | Negros Oriental | Siaton | Mantuyop | 9.0551 | 123.023 | R | 2311 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0045 | PTCI/MIDC | 9.0635 | 123.0334 | 1.47 | Terrestrial Optical Fiber Drop | 1.17 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3858 | 4 | 858 | 3858 | 0702232013 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward IV | 10.2444 | 123.7979 | U | 4414 | 1161 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0129 | PTCI/MIDC | 10.251 | 123.7892 | 0.4 | Terrestrial Optical Fiber Drop | 0.46 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3859 | 4 | 859 | 3859 | 1130700186 | Region XI (Davao Region) | Davao del Sur | City of Davao | Lapu-lapu | 7.1647 | 125.4713 | U | 13740 | 4041 | 1212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110356 | FTAP BTS | 7.0986 | 125.6467 | 0.58 | Terrestrial Optical Fiber Drop | 2.98 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3860 | 4 | 860 | 3860 | 0401020025 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Quilo-quilo South | 13.8548 | 121.2266 | R | 3758 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBGG0009 | PTCI/MIDC | 13.8479 | 121.2131 | 1.65 | Terrestrial Optical Fiber Drop | 2.96 | 1.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3861 | 4 | 861 | 3861 | 0907322057 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Dumagoc | 7.8157 | 123.4316 | U | 8927 | 2288 | 686 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0013 | PTCI/MIDC | 7.8221 | 123.4304 | 0.73 | Terrestrial Optical Fiber Drop | 1.89 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3862 | 4 | 862 | 3862 | 1430300018 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Camp 8 | 16.425 | 120.6047 | R | 2653 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00332 | Edgepoint | 16.4251 | 120.6019 | 0.3 | Terrestrial Optical Fiber Drop | 1.17 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3863 | 4 | 863 | 3863 | 0631000183 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Ticud | 10.7169 | 122.5783 | U | 3472 | 826 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0033 | PTCI/MIDC | 10.7171 | 122.5793 | 0.11 | Terrestrial Optical Fiber Drop | 1.18 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3864 | 4 | 864 | 3864 | 0105531026 | Region I (Ilocos Region) | Pangasinan | Rosales | San Pedro West | 15.8984 | 120.6434 | R | 4369 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00544 | Edgepoint | 15.8933 | 120.6367 | 0.91 | Terrestrial Optical Fiber Drop | 1.44 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3865 | 4 | 865 | 3865 | 0402104012 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 1 | 14.3134 | 121.0537 | R | 3303 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1183 | FTAP Smart | 14.3053 | 121.0487 | 0.72 | Terrestrial Optical Fiber Drop | 0.48 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3866 | 4 | 866 | 3866 | 1600301003 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Fili | 8.7683 | 125.7769 | R | 3668 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0001 | PTCI/MIDC | 8.7141 | 125.7595 | 1.26 | Terrestrial Optical Fiber Drop | 6.49 | 6.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3867 | 4 | 867 | 3867 | 0305414010 | Region III (Central Luzon) | Pampanga | Minalin | San Pedro | 14.9768 | 120.6897 | R | 2689 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01561-B07 | PTCI/MIDC | 14.9747 | 120.6883 | 0.28 | Terrestrial Optical Fiber Drop | 1.17 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3868 | 4 | 868 | 3868 | 0401031017 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Pagaspas | 14.0991 | 121.1374 | U | 6035 | 1676 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040327 | FTAP Globe | 14.0929 | 121.1101 | 0.42 | Terrestrial Optical Fiber Drop | 2.19 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3869 | 4 | 869 | 3869 | 0704610007 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Bunao | 9.3136 | 123.2885 | R | 2835 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0062 | PTCI/MIDC | 9.2988 | 123.2874 | 0.23 | Terrestrial Optical Fiber Drop | 1.93 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3870 | 4 | 870 | 3870 | 0203108062 | Region II (Cagayan Valley) | Isabela | City of Cauayan | San Luis | 16.9657 | 121.8298 | R | 2515 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00214 | Edgepoint | 16.9635 | 121.8264 | 0.44 | Terrestrial Optical Fiber Drop | 1.17 | 3.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3871 | 4 | 871 | 3871 | 0501716035 | Region V (Bicol Region) | Camarines Sur | City of Iriga | Santo Domingo | 13.4203 | 123.4305 | U | 6568 | 1563 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03096-C10 | PTCI/MIDC | 13.4165 | 123.4384 | 0.95 | Terrestrial Optical Fiber Drop | 1.57 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3872 | 4 | 872 | 3872 | 0305406015 | Region III (Central Luzon) | Pampanga | Floridablanca | Sto. Rosario | 14.8957 | 120.4831 | R | 2225 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01555-B07 | PTCI/MIDC | 14.981 | 120.5138 | 1.25 | Terrestrial Optical Fiber Drop | 3.8 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3873 | 4 | 873 | 3873 | 0305402012 | Region III (Central Luzon) | Pampanga | Apalit | San Vicente | 14.9457 | 120.7468 | U | 25131 | 6282 | 1885 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02431-B07 | PTCI/MIDC | 14.9437 | 120.7447 | 0.31 | Terrestrial Optical Fiber Drop | 1.37 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3874 | 4 | 874 | 3874 | 0403428012 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Market Area | 14.3151 | 121.1114 | U | 17557 | 5320 | 1596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040181 | FTAP Globe | 14.3125 | 121.1123 | 0.31 | Terrestrial Optical Fiber Drop | 1.18 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3875 | 4 | 875 | 3875 | 0304903039 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Isla | 15.4926 | 120.9594 | R | 2550 | 728 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-02303 | Edgepoint | 15.4941 | 120.9646 | 0.58 | Terrestrial Optical Fiber Drop | 1.22 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3876 | 4 | 876 | 3876 | 0501705030 | Region V (Bicol Region) | Camarines Sur | Buhi | San Pedro | 13.4259 | 123.5186 | R | 2311 | 550 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 0.69 | Terrestrial Optical Fiber Drop | 1.19 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3877 | 4 | 877 | 3877 | 0402109086 | Region IV-A (CALABARZON) | Cavite | City of Imus | Pinagbuklod | 14.4072 | 120.9364 | R | 1896 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | G6076 | FTAP Smart | 14.4481 | 121.0031 | 0.4 | Terrestrial Optical Fiber Drop | 0.46 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3878 | 4 | 878 | 3878 | 0931700074 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Santa Barbara | 6.9029 | 122.0826 | U | 6997 | 1943 | 583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0108 | PTCI/MIDC | 6.9046 | 122.0803 | 0.31 | Terrestrial Optical Fiber Drop | 1.28 | 1.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3879 | 4 | 879 | 3879 | 1004306015 | Region X (Northern Mindanao) | Misamis Oriental | Claveria | Mat-i | 8.634 | 124.9786 | R | 4823 | 1236 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0043 | PTCI/MIDC | 8.6471 | 124.9061 | 8.11 | Terrestrial Optical Fiber Drop | 1.18 | 23.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3880 | 4 | 880 | 3880 | 0301405013 | Region III (Central Luzon) | Bulacan | Bulacan | Santa Ana | 14.787 | 120.8839 | U | 8360 | 2388 | 716 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02984-B07 | PTCI/MIDC | 14.7832 | 120.8788 | 0.7 | Terrestrial Optical Fiber Drop | 1.19 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3881 | 4 | 881 | 3881 | 1430300126 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Ambiong | 16.4069 | 120.5974 | R | 3340 | 878 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02312-B05 | PTCI/MIDC | 16.4768 | 120.6329 | 1.38 | Terrestrial Optical Fiber Drop | 0.54 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3882 | 4 | 882 | 3882 | 0405627042 | Region IV-A (CALABARZON) | Quezon | Mauban | Lual Rural | 14.1884 | 121.7289 | R | 4093 | 1077 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02455-C08 | PTCI/MIDC | 14.1865 | 121.7262 | 0.98 | Terrestrial Optical Fiber Drop | 1.53 | 19.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3883 | 4 | 883 | 3883 | 0401018017 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Upa | 13.9669 | 121.1107 | R | 2004 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01964-C08 | PTCI/MIDC | 13.9582 | 121.119 | 1.32 | Terrestrial Optical Fiber Drop | 1.19 | 3.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3884 | 4 | 884 | 3884 | 0603026013 | Region VI (Western Visayas) | Iloilo | Leganes | Guinobatan | 10.7837 | 122.6 | R | 2435 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 1.01 | Terrestrial Optical Fiber Drop | 1.34 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3885 | 4 | 885 | 3885 | 0103314050 | Region I (Ilocos Region) | La Union | City of San Fernando | Sagayad | 16.5938 | 120.3326 | R | 3174 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02862-B05 | PTCI/MIDC | 16.5908 | 120.3355 | 0.45 | Terrestrial Optical Fiber Drop | 1.92 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3886 | 4 | 886 | 3886 | 0307106013 | Region III (Central Luzon) | Zambales | Masinloc | Tapuac | 15.5488 | 119.9625 | R | 3237 | 851 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03362-B07 | PTCI/MIDC | 15.5488 | 119.9474 | 1.61 | Terrestrial Optical Fiber Drop | 1.72 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3887 | 4 | 887 | 3887 | 0402106040 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina I | 14.3219 | 120.971 | R | 3481 | 1023 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01921-C08 | PTCI/MIDC | 14.3223 | 120.9722 | 0.13 | Terrestrial Optical Fiber Drop | 1.2 | 2.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3888 | 4 | 888 | 3888 | 0506213004 | Region V (Bicol Region) | Sorsogon | Pilar | Banuyo | 12.9256 | 123.6747 | R | 3884 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 1.1 | Terrestrial Optical Fiber Drop | 1.2 | 10.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3889 | 4 | 889 | 3889 | 0105526021 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Navaluan | 16.0659 | 120.4159 | R | 4149 | 1152 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00421 | Edgepoint | 16.068 | 120.4097 | 0.7 | Terrestrial Optical Fiber Drop | 1.47 | 1.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3890 | 4 | 890 | 3890 | 0301420056 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz IV | 14.8557 | 121.0515 | R | 3319 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01038-B07 | PTCI/MIDC | 14.8505 | 121.0788 | 1.05 | Terrestrial Optical Fiber Drop | 2.17 | 5.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3891 | 4 | 891 | 3891 | 0401003044 | Region IV-A (CALABARZON) | Batangas | Balayan | Sampaga | 13.943 | 120.7671 | R | 3215 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040445 | FTAP Globe | 13.9391 | 120.7656 | 2.01 | Terrestrial Optical Fiber Drop | 2.22 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3892 | 4 | 892 | 3892 | 0401032008 | Region IV-A (CALABARZON) | Batangas | Taysan | Mahanadiong | 13.7931 | 121.1921 | R | 2320 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01959-C08 | PTCI/MIDC | 13.7986 | 121.1878 | 1.9 | Terrestrial Optical Fiber Drop | 0.22 | 4.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3893 | 4 | 893 | 3893 | 0105533022 | Region I (Ilocos Region) | Pangasinan | San Fabian | Sagud-Bahley | 16.1198 | 120.3888 | U | 4389 | 1219 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00403 | Edgepoint | 16.1211 | 120.4056 | 1.8 | Terrestrial Optical Fiber Drop | 1.19 | 1.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3894 | 4 | 894 | 3894 | 0500506063 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 59 - Puro | 13.1355 | 123.7608 | U | 5907 | 1440 | 432 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050178 | FTAP Globe | 13.14 | 123.7567 | 0.67 | Terrestrial Optical Fiber Drop | 2.36 | 1.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3895 | 4 | 895 | 3895 | 0401022012 | Region IV-A (CALABARZON) | Batangas | San Jose | Dagatan | 13.8502 | 121.1026 | R | 3221 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03255-C08 | PTCI/MIDC | 13.854 | 121.105 | 0.5 | Terrestrial Optical Fiber Drop | 3.23 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3896 | 4 | 896 | 3896 | 0301405005 | Region III (Central Luzon) | Bulacan | Bulacan | Maysantol | 14.7933 | 120.8811 | R | 3089 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02984-B07 | PTCI/MIDC | 14.7832 | 120.8788 | 0.64 | Terrestrial Optical Fiber Drop | 0.45 | 3.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3897 | 4 | 897 | 3897 | 1108211010 | Region XI (Davao Region) | Davao de Oro | Pantukan | Tambongon | 7.1032 | 125.9359 | R | 4113 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110467 | FTAP Globe | 7.1345 | 125.9542 | 4.02 | Terrestrial Optical Fiber Drop | 5.33 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3898 | 4 | 898 | 3898 | 0401026029 | Region IV-A (CALABARZON) | Batangas | San Pascual | Santo Niño | 13.7994 | 121.0212 | R | 3470 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03052-C08 | PTCI/MIDC | 13.7971 | 121.021 | 0.25 | Terrestrial Optical Fiber Drop | 2.05 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3899 | 4 | 899 | 3899 | 0301412017 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Pandayan | 14.7505 | 120.9684 | U | 17948 | 5128 | 1538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01231 | Edgepoint | 14.7509 | 120.9691 | 0.09 | Terrestrial Optical Fiber Drop | 1.29 | 1.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3900 | 4 | 900 | 3900 | 0405802002 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Cupang | 14.6388 | 121.1331 | U | 129296 | 35915 | 10775 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-02516 | Edgepoint | 14.6401 | 121.1329 | 0.14 | Terrestrial Optical Fiber Drop | 1.51 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3901 | 4 | 901 | 3901 | 0105522020 | Region I (Ilocos Region) | Pangasinan | Lingayen | Malimpuec | 16.0169 | 120.1894 | R | 3903 | 1084 | 325 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00454 | Edgepoint | 16.0189 | 120.1922 | 0.37 | Terrestrial Optical Fiber Drop | 4.67 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3902 | 4 | 902 | 3902 | 0506208001 | Region V (Bicol Region) | Sorsogon | Gubat | Ariman | 12.9081 | 124.1161 | R | 1795 | 448 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03159-C10 | PTCI/MIDC | 12.912 | 124.1171 | 0.44 | Terrestrial Optical Fiber Drop | 1.2 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3903 | 4 | 903 | 3903 | 0501733018 | Region V (Bicol Region) | Camarines Sur | San Jose | Pugay | 13.686 | 123.5192 | R | 2402 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 1.67 | Terrestrial Optical Fiber Drop | 1.21 | 2.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3904 | 4 | 904 | 3904 | 1705309032 | MIMAROPA Region | Palawan | Coron | Barangay VI | 11.9991 | 120.2132 | U | 5297 | 1358 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170202 | FTAP Globe | 12.0797 | 120.196 | 5.69 | Satellite LEO Backhaul (Starlink Business) | 3.83 | 100.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3905 | 4 | 905 | 3905 | 0600402009 | Region VI (Western Visayas) | Aklan | Balete | Morales | 11.5452 | 122.3735 | R | 3496 | 896 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060221 | FTAP Globe | 11.5343 | 122.369 | 1.3 | Terrestrial Optical Fiber Drop | 1.35 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3906 | 4 | 906 | 3906 | 0301410002 | Region III (Central Luzon) | Bulacan | City of Malolos | Atlag | 14.8295 | 120.8205 | U | 4887 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02487 | Edgepoint | 14.8248 | 120.8221 | 0.56 | Terrestrial Optical Fiber Drop | 1.21 | 2.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3907 | 4 | 907 | 3907 | 0601909013 | Region VI (Western Visayas) | Capiz | Panay | Bonga | 11.5531 | 122.8069 | R | 2172 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060227 | FTAP Globe | 11.5586 | 122.7957 | 1.37 | Terrestrial Optical Fiber Drop | 1.28 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3908 | 4 | 908 | 3908 | 0402103003 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Banalo | 14.4419 | 120.9719 | R | 2998 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0028 | PTCI/MIDC | 14.4355 | 120.9551 | 0.27 | Terrestrial Optical Fiber Drop | 2.03 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3909 | 4 | 909 | 3909 | 1705209023 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Pili | 13.0691 | 121.5167 | R | 3985 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170094 | FTAP Globe | 13.0692 | 121.5176 | 0.1 | Terrestrial Optical Fiber Drop | 1.21 | 5.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3910 | 4 | 910 | 3910 | 0401010001 | Region IV-A (CALABARZON) | Batangas | Ibaan | Bago | 13.8294 | 121.136 | R | 2207 | 613 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 1.46 | Terrestrial Optical Fiber Drop | 1.71 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3911 | 4 | 911 | 3911 | 0301424004 | Region III (Central Luzon) | Bulacan | Doña Remedios Trinidad | Camachile | 14.9774 | 121.0658 | R | 4820 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00973 | Edgepoint | 14.9766 | 121.0658 | 0.09 | Terrestrial Optical Fiber Drop | 1.22 | 13.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3912 | 4 | 912 | 3912 | 0702251006 | Region VII (Central Visayas) | Cebu | City of Toledo | Bunga | 10.3034 | 123.6853 | U | 5482 | 1442 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0163 | PTCI/MIDC | 10.3105 | 123.6964 | 1.45 | Terrestrial Optical Fiber Drop | 1.59 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3913 | 4 | 913 | 3913 | 1030500042 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Camaman-an | 8.4729 | 124.659 | U | 35877 | 9965 | 2990 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLR0019 | PTCI/MIDC | 8.4762 | 124.6552 | 0.56 | Terrestrial Optical Fiber Drop | 1.61 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3914 | 4 | 914 | 3914 | 0403429007 | Region IV-A (CALABARZON) | Laguna | Siniloan | Halayhayin | 14.4237 | 121.4483 | U | 5313 | 1610 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040106 | FTAP Globe | 14.4246 | 121.4454 | 0.33 | Terrestrial Optical Fiber Drop | 1.33 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3915 | 4 | 915 | 3915 | 0401001021 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Subic Ibaba | 13.9461 | 120.9413 | R | 3755 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01957-C08 | PTCI/MIDC | 13.9528 | 120.9371 | 0.88 | Terrestrial Optical Fiber Drop | 1.22 | 5.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3916 | 4 | 916 | 3916 | 0402122008 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Osorio | 14.2911 | 120.8797 | U | 11614 | 3415 | 1025 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02150-C08 | PTCI/MIDC | 14.2958 | 120.8761 | 0.65 | Terrestrial Optical Fiber Drop | 1.51 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3917 | 4 | 917 | 3917 | 0203101004 | Region II (Cagayan Valley) | Isabela | Alicia | Aurora | 16.7856 | 121.6816 | U | 4045 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0003 | PTCI/MIDC | 16.7803 | 121.684 | 0.64 | Terrestrial Optical Fiber Drop | 1.21 | 2.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3918 | 4 | 918 | 3918 | 0402103023 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Tabing Dagat | 14.4593 | 120.9394 | R | 3605 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040092 | FTAP Globe | 14.4604 | 120.9401 | 0.14 | Terrestrial Optical Fiber Drop | 1.76 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3919 | 4 | 919 | 3919 | 1630400091 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Obrero Pob. | 8.9628 | 125.5378 | U | 8935 | 2179 | 654 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130071 | FTAP Globe | 8.9621 | 125.5348 | 0.34 | Terrestrial Optical Fiber Drop | 1.3 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3920 | 4 | 920 | 3920 | 0600402007 | Region VI (Western Visayas) | Aklan | Balete | Fulgencio | 11.5882 | 122.3687 | R | 3736 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 1.93 | Terrestrial Optical Fiber Drop | 2.77 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3921 | 4 | 921 | 3921 | 0907322052 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Kawit | 7.8242 | 123.4482 | U | 9962 | 2554 | 766 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0091 | PTCI/MIDC | 7.8212 | 123.4498 | 0.38 | Terrestrial Optical Fiber Drop | 1.23 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3922 | 4 | 922 | 3922 | 0301410027 | Region III (Central Luzon) | Bulacan | City of Malolos | Look 2nd | 14.8229 | 120.8619 | U | 3220 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03004-A02 | PTCI/MIDC | 14.8251 | 120.8603 | 0.31 | Terrestrial Optical Fiber Drop | 1.36 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3923 | 4 | 923 | 3923 | 0702214011 | Region VII (Central Visayas) | Cebu | City of Carcar | Valladolid | 10.0975 | 123.6553 | U | 13009 | 3423 | 1027 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0023 | PTCI/MIDC | 10.1027 | 123.6533 | 0.61 | Terrestrial Optical Fiber Drop | 1.75 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3924 | 4 | 924 | 3924 | 0103311012 | Region I (Ilocos Region) | La Union | Naguilian | Bato | 16.5187 | 120.4043 | R | 1681 | 454 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010102 | FTAP Globe | 16.5099 | 120.412 | 1.28 | Terrestrial Optical Fiber Drop | 1.23 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3925 | 4 | 925 | 3925 | 0306910010 | Region III (Central Luzon) | Tarlac | Paniqui | Canan | 15.6839 | 120.5953 | R | 3349 | 858 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00603 | Edgepoint | 15.6812 | 120.5835 | 1.3 | Terrestrial Optical Fiber Drop | 1.97 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3926 | 4 | 926 | 3926 | 0631000029 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Caingin | 10.7047 | 122.562 | R | 4860 | 1157 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0033 | PTCI/MIDC | 10.7171 | 122.5793 | 0.66 | Terrestrial Optical Fiber Drop | 1.2 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3927 | 4 | 927 | 3927 | 0731300019 | Region VII (Central Visayas) | Cebu | City of Mandaue | Opao | 10.3321 | 123.9542 | U | 12026 | 3436 | 1031 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070337 | FTAP Globe | 10.3346 | 123.9545 | 0.28 | Terrestrial Optical Fiber Drop | 2.22 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3928 | 4 | 928 | 3928 | 0603037039 | Region VI (Western Visayas) | Iloilo | Pototan | Nanga | 10.9409 | 122.6343 | R | 2964 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 2.15 | Terrestrial Optical Fiber Drop | 0.96 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3929 | 4 | 929 | 3929 | 0501710020 | Region V (Bicol Region) | Camarines Sur | Canaman | San Vicente | 13.6357 | 123.1743 | R | 3158 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050076 | FTAP Globe | 13.634 | 123.178 | 0.44 | Terrestrial Optical Fiber Drop | 1.76 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3930 | 4 | 930 | 3930 | 0306905041 | Region III (Central Luzon) | Tarlac | Concepcion | Santa Maria | 15.336 | 120.6582 | R | 2356 | 604 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00763 | Edgepoint | 15.323 | 120.6635 | 1.55 | Terrestrial Optical Fiber Drop | 1.27 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3931 | 4 | 931 | 3931 | 0401034022 | Region IV-A (CALABARZON) | Batangas | Tuy | Toong | 14.071 | 120.7655 | R | 2648 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | Q23 | FTAP Smart | 14.0808 | 120.7592 | 1.28 | Terrestrial Optical Fiber Drop | 1.6 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3932 | 4 | 932 | 3932 | 0402118051 | Region IV-A (CALABARZON) | Cavite | Silang | Ipil I | 14.2739 | 120.9947 | R | 3128 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040200 | FTAP Globe | 14.2755 | 120.9928 | 0.27 | Terrestrial Optical Fiber Drop | 1.23 | 2.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3933 | 4 | 933 | 3933 | 0402103045 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino II | 14.4152 | 120.972 | U | 44630 | 13126 | 3938 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040112 | FTAP Globe | 14.4161 | 120.9742 | 0.25 | Terrestrial Optical Fiber Drop | 1.23 | 3.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3934 | 4 | 934 | 3934 | 0907322002 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Balangasan | 7.8236 | 123.42 | U | 15720 | 4030 | 1209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0015 | PTCI/MIDC | 7.8233 | 123.4243 | 0.47 | Terrestrial Optical Fiber Drop | 2.27 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3935 | 4 | 935 | 3935 | 0500518001 | Region V (Bicol Region) | Albay | Tiwi | Bagumbayan | 13.4525 | 123.6619 | R | 2758 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 2.16 | Terrestrial Optical Fiber Drop | 1.59 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3936 | 4 | 936 | 3936 | 0105518001 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Bacayao Norte | 16.0323 | 120.3442 | R | 4329 | 1202 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010152 | FTAP Globe | 16.0323 | 120.3491 | 0.52 | Terrestrial Optical Fiber Drop | 1.96 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3937 | 4 | 937 | 3937 | 0402111015 | Region IV-A (CALABARZON) | Cavite | Kawit | Binakayan-Aplaya | 14.4438 | 120.9105 | R | 3521 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01930-C08 | PTCI/MIDC | 14.4344 | 120.9174 | 0.74 | Terrestrial Optical Fiber Drop | 3.36 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3938 | 4 | 938 | 3938 | 0405807004 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Second District | 14.3261 | 121.307 | R | 2140 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040162 | FTAP Globe | 14.3315 | 121.3542 | 1.89 | Terrestrial Optical Fiber Drop | 3.8 | 11.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3939 | 4 | 939 | 3939 | 0105530007 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Batakil | 16.1224 | 120.5224 | R | 2767 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00407 | Edgepoint | 16.11 | 120.5398 | 0.73 | Terrestrial Optical Fiber Drop | 2.3 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3940 | 4 | 940 | 3940 | 0402122004 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | De Ocampo | 14.2953 | 120.8669 | U | 13294 | 3910 | 1173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02150-C08 | PTCI/MIDC | 14.2958 | 120.8761 | 0.99 | Terrestrial Optical Fiber Drop | 1.45 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3941 | 4 | 941 | 3941 | 0301423008 | Region III (Central Luzon) | Bulacan | Santa Maria | Caysio | 14.8461 | 120.9685 | U | 15657 | 4473 | 1342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01069-B07 | PTCI/MIDC | 14.8493 | 120.9686 | 0.36 | Terrestrial Optical Fiber Drop | 2.28 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3942 | 4 | 942 | 3942 | 0305402011 | Region III (Central Luzon) | Pampanga | Apalit | San Juan | 14.9544 | 120.7702 | U | 9402 | 2350 | 705 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00997 | Edgepoint | 14.9564 | 120.7724 | 0.32 | Terrestrial Optical Fiber Drop | 1.36 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3943 | 4 | 943 | 3943 | 1001317016 | Region X (Northern Mindanao) | Bukidnon | Quezon | Magsaysay | 7.7028 | 125.1137 | R | 2111 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 1.12 | Terrestrial Optical Fiber Drop | 0.56 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3944 | 4 | 944 | 3944 | 1130700075 | Region XI (Davao Region) | Davao del Sur | City of Davao | Matina Crossing | 7.0795 | 125.574 | U | 43085 | 12672 | 3802 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0033 | PTCI/MIDC | 7.0763 | 125.5673 | 0.82 | Terrestrial Optical Fiber Drop | 1.25 | 2.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3945 | 4 | 945 | 3945 | 0401022029 | Region IV-A (CALABARZON) | Batangas | San Jose | Santo Cristo | 13.8838 | 121.0985 | U | 3271 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040536 | FTAP Globe | 13.8641 | 121.1219 | 1.1 | Terrestrial Optical Fiber Drop | 0.87 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3946 | 4 | 946 | 3946 | 0603043041 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Lanag | 10.8336 | 122.544 | R | 2310 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0072 | PTCI/MIDC | 10.8243 | 122.5364 | 1.32 | Terrestrial Optical Fiber Drop | 1.24 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3947 | 4 | 947 | 3947 | 0305416012 | Region III (Central Luzon) | Pampanga | City of San Fernando | Lara | 15.094 | 120.6113 | U | 4024 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-03021 | Edgepoint | 120.6106 | 15.0923 | 0.2 | Terrestrial Optical Fiber Drop | 2.18 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3948 | 4 | 948 | 3948 | 0604531015 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XII | 10.8716 | 123.1004 | R | 4320 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0078 | PTCI/MIDC | 10.8984 | 123.08 | 1.29 | Terrestrial Optical Fiber Drop | 4.47 | 4.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3949 | 4 | 949 | 3949 | 0105513009 | Region I (Ilocos Region) | Pangasinan | Binmaley | Calit | 16.0061 | 120.319 | R | 2537 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010161 | FTAP Globe | 16.014 | 120.313 | 1.09 | Terrestrial Optical Fiber Drop | 2.03 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3950 | 4 | 950 | 3950 | 0501708042 | Region V (Bicol Region) | Camarines Sur | Calabanga | Santa Cruz Poblacion | 13.7416 | 123.2607 | R | 2047 | 487 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050054 | FTAP Globe | 13.7374 | 123.2697 | 1.08 | Terrestrial Optical Fiber Drop | 1.28 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3951 | 4 | 951 | 3951 | 0702219014 | Region VII (Central Visayas) | Cebu | Consolacion | Poblacion Oriental | 10.3765 | 123.9574 | U | 3218 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070054 | FTAP BTS | 10.3904 | 123.9473 | 0.93 | Terrestrial Optical Fiber Drop | 0.15 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3952 | 4 | 952 | 3952 | 0401028028 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Santa Maria | 14.074 | 121.168 | U | 18532 | 5147 | 1544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03243-C08 | PTCI/MIDC | 13.8652 | 121.0025 | 1.13 | Terrestrial Optical Fiber Drop | 1.91 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3953 | 4 | 953 | 3953 | 0402110006 | Region IV-A (CALABARZON) | Cavite | Indang | Buna Cerca | 14.1867 | 120.8865 | U | 4279 | 1258 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0034 | FTAP Smart | 14.1948 | 120.8764 | 1.41 | Terrestrial Optical Fiber Drop | 1.25 | 8.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3954 | 4 | 954 | 3954 | 0704603010 | Region VII (Central Visayas) | Negros Oriental | Bacong | Lutao | 9.2473 | 123.2676 | R | 1351 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 2.05 | Terrestrial Optical Fiber Drop | 2.48 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3955 | 4 | 955 | 3955 | 0631000010 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Balabago | 10.7391 | 122.5799 | U | 10376 | 2470 | 741 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060266 | FTAP Globe | 10.7351 | 122.5715 | 1.02 | Terrestrial Optical Fiber Drop | 1.59 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3956 | 4 | 956 | 3956 | 0301407006 | Region III (Central Luzon) | Bulacan | Calumpit | Calizon | 14.9133 | 120.7547 | R | 2322 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02962-B07 | PTCI/MIDC | 14.9133 | 120.7524 | 0.26 | Terrestrial Optical Fiber Drop | 1.6 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3957 | 4 | 957 | 3957 | 0603044016 | Region VI (Western Visayas) | Iloilo | Sara | Del Castillo | 11.2648 | 123.0032 | R | 2231 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 1.34 | Terrestrial Optical Fiber Drop | 1.83 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3958 | 4 | 958 | 3958 | 0501727005 | Region V (Bicol Region) | Camarines Sur | Pasacao | Caranan | 13.524 | 123.0148 | U | 10435 | 2484 | 745 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02840-C10 | PTCI/MIDC | 13.5211 | 123.015 | 0.33 | Terrestrial Optical Fiber Drop | 1.25 | 1.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3959 | 4 | 959 | 3959 | 0501723042 | Region V (Bicol Region) | Camarines Sur | Nabua | Santiago Old | 13.3999 | 123.3627 | R | 2281 | 543 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03050-C10 | PTCI/MIDC | 13.3902 | 123.3623 | 1.08 | Terrestrial Optical Fiber Drop | 1.31 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3960 | 4 | 960 | 3960 | 1130700020 | Region XI (Davao Region) | Davao del Sur | City of Davao | Bucana | 7.0603 | 125.6028 | U | 83801 | 24647 | 7394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110492 | FTAP Globe | 7.0518 | 125.6094 | 0.6 | Terrestrial Optical Fiber Drop | 1.38 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3961 | 4 | 961 | 3961 | 0803738086 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Vicente | 11.0519 | 124.5217 | R | 2029 | 533 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080191 | FTAP BTS | 11.0648 | 124.5167 | 1.54 | Terrestrial Optical Fiber Drop | 1.25 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3962 | 4 | 962 | 3962 | 0304920009 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Malbang | 15.8058 | 121.1553 | R | 3061 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1432 | FTAP Smart | 15.8078 | 121.1574 | 0.31 | Terrestrial Optical Fiber Drop | 1.25 | 10.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3963 | 4 | 963 | 3963 | 0402117009 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa I | 14.4158 | 120.8509 | R | 2056 | 604 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040117 | FTAP Globe | 14.409 | 120.8561 | 0.21 | Terrestrial Optical Fiber Drop | 2.29 | 2.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3964 | 4 | 964 | 3964 | 0401014059 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Francisco | 13.8978 | 121.2455 | R | 3201 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040514 | FTAP Globe | 13.8971 | 121.2443 | 0.15 | Terrestrial Optical Fiber Drop | 2.77 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3965 | 4 | 965 | 3965 | 0306917019 | Region III (Central Luzon) | Tarlac | Victoria | San Fernando | 15.5776 | 120.681 | R | 3472 | 890 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00655 | Edgepoint | 15.5757 | 120.6851 | 0.9 | Terrestrial Optical Fiber Drop | 0.41 | 6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3966 | 4 | 966 | 3966 | 0301409017 | Region III (Central Luzon) | Bulacan | Hagonoy | San Pedro | 14.8415 | 120.7629 | U | 5956 | 1701 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02376-B07 | PTCI/MIDC | 14.8434 | 120.7633 | 0.22 | Terrestrial Optical Fiber Drop | 1.25 | 2.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3967 | 4 | 967 | 3967 | 0401006016 | Region IV-A (CALABARZON) | Batangas | Bauan | Inicbulan | 13.8204 | 120.982 | R | 3968 | 1102 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040558 | FTAP Globe | 13.8156 | 120.9849 | 0.62 | Terrestrial Optical Fiber Drop | 3.65 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3968 | 4 | 968 | 3968 | 1600203017 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Kauswagan | 9.1307 | 125.5292 | R | 3629 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 2.01 | Terrestrial Optical Fiber Drop | 2.41 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3969 | 4 | 969 | 3969 | 0205005028 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Vista Alegre | 16.4878 | 121.1499 | R | 4868 | 1281 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0016 | PTCI/MIDC | 16.5005 | 121.1392 | 0.8 | Terrestrial Optical Fiber Drop | 0.31 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3970 | 4 | 970 | 3970 | 0731300025 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tingub | 10.3555 | 123.9365 | U | 6088 | 1739 | 522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CEB_0013 | LDIC | 10.3587 | 123.9368 | 0.36 | Terrestrial Optical Fiber Drop | 1.44 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3971 | 4 | 971 | 3971 | 0306904001 | Region III (Central Luzon) | Tarlac | Capas | Aranguren | 15.3559 | 120.5274 | U | 8046 | 2063 | 619 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00753 | Edgepoint | 15.3588 | 120.5312 | 0.52 | Terrestrial Optical Fiber Drop | 1.26 | 6.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3972 | 4 | 972 | 3972 | 0831600134 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 109 | 11.2054 | 124.9962 | U | 5260 | 1282 | 385 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0065 | PTCI/MIDC | 11.2049 | 124.9973 | 0.13 | Terrestrial Optical Fiber Drop | 1.64 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3973 | 4 | 973 | 3973 | 0105506012 | Region I (Ilocos Region) | Pangasinan | Asingan | Domanpot | 15.9999 | 120.6594 | U | 5499 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.6 | Terrestrial Optical Fiber Drop | 1.26 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3974 | 4 | 974 | 3974 | 0305417015 | Region III (Central Luzon) | Pampanga | San Luis | Santa Rita | 15.0317 | 120.7775 | R | 2806 | 701 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02380-B07 | PTCI/MIDC | 15.0232 | 120.7746 | 1 | Terrestrial Optical Fiber Drop | 1.44 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3975 | 4 | 975 | 3975 | 0105517025 | Region I (Ilocos Region) | Pangasinan | Calasiao | Talibaew | 16.0053 | 120.3728 | R | 4866 | 1351 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00471 | Edgepoint | 16.0011 | 120.3605 | 1.39 | Terrestrial Optical Fiber Drop | 1.89 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3976 | 4 | 976 | 3976 | 0402103040 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi III | 14.46 | 120.9521 | U | 6439 | 1893 | 568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1116 | FTAP Smart | 14.4061 | 120.9879 | 0.57 | Terrestrial Optical Fiber Drop | 0.77 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3977 | 4 | 977 | 3977 | 0506208016 | Region V (Bicol Region) | Sorsogon | Gubat | Cota Na Daco | 12.9258 | 124.1234 | R | 1771 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 0.55 | Terrestrial Optical Fiber Drop | 1.27 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3978 | 4 | 978 | 3978 | 0102820015 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Marcos | 18.1606 | 120.5758 | R | 3052 | 824 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ILN_0001 | LDIC | 18.161 | 120.5894 | 1.44 | Terrestrial Optical Fiber Drop | 2.15 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3979 | 4 | 979 | 3979 | 0401010024 | Region IV-A (CALABARZON) | Batangas | Ibaan | Santo Niño | 13.8559 | 121.1343 | R | 3781 | 1050 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040542 | FTAP Globe | 13.8512 | 121.1467 | 1.43 | Terrestrial Optical Fiber Drop | 4.1 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3980 | 4 | 980 | 3980 | 0500504041 | Region V (Bicol Region) | Albay | Guinobatan | Quitago | 13.1766 | 123.6069 | R | 2749 | 670 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0037 | PTCI/MIDC | 13.1678 | 123.6042 | 1.02 | Terrestrial Optical Fiber Drop | 1.37 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3981 | 4 | 981 | 3981 | 0304921014 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | San Josef | 15.346 | 121.0083 | U | 5989 | 1711 | 513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01423-B07 | PTCI/MIDC | 15.3505 | 121.0032 | 0.74 | Terrestrial Optical Fiber Drop | 1.27 | 6.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3982 | 4 | 982 | 3982 | 1230800016 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Mabuhay | 6.1505 | 125.1449 | U | 38964 | 9990 | 2997 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120067 | FTAP BTS | 6.1552 | 125.1469 | 0.57 | Terrestrial Optical Fiber Drop | 1.74 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3983 | 4 | 983 | 3983 | 0301420024 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima III | 14.8455 | 121.0482 | R | 2038 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01137 | Edgepoint | 14.8428 | 121.0475 | 0.3 | Terrestrial Optical Fiber Drop | 1.27 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3984 | 4 | 984 | 3984 | 0105530025 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Palguyod | 16.1227 | 120.5218 | R | 3328 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00401 | Edgepoint | 16.1384 | 120.5248 | 1.77 | Terrestrial Optical Fiber Drop | 2.37 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3985 | 4 | 985 | 3985 | 0730600003 | Region VII (Central Visayas) | Cebu | City of Cebu | Apas | 10.337 | 123.9065 | U | 24223 | 7569 | 2271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0053 | PTCI/MIDC | 10.3434 | 123.9117 | 0.91 | Terrestrial Optical Fiber Drop | 1.27 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3986 | 4 | 986 | 3986 | 0402120009 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya I | 14.3966 | 120.8536 | U | 5047 | 1484 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.69 | Terrestrial Optical Fiber Drop | 0.93 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3987 | 4 | 987 | 3987 | 0403425025 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Maharlika | 14.3411 | 121.044 | U | 6117 | 1853 | 556 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040146 | FTAP Globe | 14.3562 | 121.0336 | 0.86 | Terrestrial Optical Fiber Drop | 0.55 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3988 | 4 | 988 | 3988 | 1030500061 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Patag | 8.4862 | 124.6223 | U | 18266 | 5073 | 1522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100145 | FTAP Globe | 8.4801 | 124.6244 | 0.71 | Terrestrial Optical Fiber Drop | 2.16 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3989 | 4 | 989 | 3989 | 0301405016 | Region III (Central Luzon) | Bulacan | Bulacan | Tibig | 14.8024 | 120.8681 | R | 3318 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01185 | Edgepoint | 14.7992 | 120.8681 | 0.35 | Terrestrial Optical Fiber Drop | 1.27 | 2.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3990 | 4 | 990 | 3990 | 0402115005 | Region IV-A (CALABARZON) | Cavite | Naic | Bucana Sasahan | 14.3227 | 120.7599 | U | 6274 | 1845 | 554 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02143-C08 | PTCI/MIDC | 14.3258 | 120.7645 | 0.61 | Terrestrial Optical Fiber Drop | 1.28 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3991 | 4 | 991 | 3991 | 0304919003 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Bo. Militar | 15.434 | 121.0743 | U | 7495 | 2141 | 642 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0201 | FTAP Smart | 15.4342 | 121.0803 | 0.64 | Terrestrial Optical Fiber Drop | 1.27 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3992 | 4 | 992 | 3992 | 0730600036 | Region VII (Central Visayas) | Cebu | City of Cebu | Camputhaw | 10.319 | 123.8969 | U | 17685 | 5526 | 1658 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070340 | FTAP Globe | 10.3206 | 123.8877 | 1.02 | Terrestrial Optical Fiber Drop | 1.28 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3993 | 4 | 993 | 3993 | 0403404010 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Marinig | 14.2702 | 121.1574 | U | 49703 | 15061 | 4518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02056-C08 | PTCI/MIDC | 14.2705 | 121.1559 | 0.17 | Terrestrial Optical Fiber Drop | 1.28 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3994 | 4 | 994 | 3994 | 0631000086 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Lanit | 10.7723 | 122.5708 | U | 8904 | 2120 | 636 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 1.11 | Terrestrial Optical Fiber Drop | 2.44 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3995 | 4 | 995 | 3995 | 0401014007 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Bagong Pook | 13.9436 | 121.1102 | U | 7291 | 2025 | 608 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040441 | FTAP Globe | 13.9414 | 121.1139 | 0.47 | Terrestrial Optical Fiber Drop | 1.31 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3996 | 4 | 996 | 3996 | 1004324001 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Baluarte | 8.5431 | 124.7423 | U | 11214 | 2875 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100127 | FTAP Globe | 8.5379 | 124.752 | 1.21 | Terrestrial Optical Fiber Drop | 1.28 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3997 | 4 | 997 | 3997 | 0401029014 | Region IV-A (CALABARZON) | Batangas | Taal | Iba | 13.8719 | 120.941 | R | 3444 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040527 | FTAP Globe | 13.8776 | 120.9277 | 1.57 | Terrestrial Optical Fiber Drop | 2.63 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3998 | 4 | 998 | 3998 | 0305411001 | Region III (Central Luzon) | Pampanga | Magalang | Camias | 15.1915 | 120.6517 | R | 2328 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030441 | FTAP Globe | 15.1902 | 120.6419 | 1.06 | Terrestrial Optical Fiber Drop | 1.28 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3999 | 4 | 999 | 3999 | 0501705037 | Region V (Bicol Region) | Camarines Sur | Buhi | Santa Elena | 13.4157 | 123.5141 | U | 3810 | 907 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCSG0019 | PTCI/MIDC | 13.3969 | 123.5113 | 2.3 | Terrestrial Optical Fiber Drop | 0.05 | 10.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4000 | 4 | 1000 | 4000 | 1003510008 | Region X (Northern Mindanao) | Lanao del Norte | Linamon | Samburon | 8.1711 | 124.1609 | R | 4097 | 975 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100177 | FTAP Globe | 8.1829 | 124.1753 | 1.67 | Terrestrial Optical Fiber Drop | 10.83 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4001 | 5 | 1 | 4001 | 1705208016 | MIMAROPA Region | Oriental Mindoro | Naujan | Estrella | 13.3297 | 121.3104 | R | 2818 | 722 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMRG0004 | PTCI/MIDC | 13.3268 | 121.3034 | 0.82 | Terrestrial Optical Fiber Drop | 1.28 | 8.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4002 | 5 | 2 | 4002 | 0401020015 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Bukal | 13.8592 | 121.2573 | R | 2930 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01948-C08 | PTCI/MIDC | 13.8813 | 121.259 | 2.46 | Terrestrial Optical Fiber Drop | 1.28 | 2.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4003 | 5 | 3 | 4003 | 0203125019 | Region II (Cagayan Valley) | Isabela | Reina Mercedes | Turod | 16.9986 | 121.7878 | R | 3290 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02882-B06 | PTCI/MIDC | 17.0005 | 121.7845 | 0.41 | Terrestrial Optical Fiber Drop | 3.15 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4004 | 5 | 4 | 4004 | 0403426025 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Norte | 14.2885 | 121.4058 | U | 5938 | 1799 | 540 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 1.06 | Terrestrial Optical Fiber Drop | 1.31 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4005 | 5 | 5 | 4005 | 0305414013 | Region III (Central Luzon) | Pampanga | Minalin | Sta. Rita | 14.9796 | 120.6929 | R | 4792 | 1198 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01561-B07 | PTCI/MIDC | 14.9747 | 120.6883 | 0.72 | Terrestrial Optical Fiber Drop | 0.73 | 3.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4006 | 5 | 6 | 4006 | 0402103026 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row Central | 14.3977 | 120.9896 | U | 6419 | 1887 | 566 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01863-C08 | PTCI/MIDC | 14.4006 | 120.9872 | 0.41 | Terrestrial Optical Fiber Drop | 1.28 | 4.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4007 | 5 | 7 | 4007 | 0702202001 | Region VII (Central Visayas) | Cebu | Alcoy | Atabay | 9.7027 | 123.4932 | R | 2375 | 625 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 5.84 | Terrestrial Optical Fiber Drop | 1.6 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4008 | 5 | 8 | 4008 | 0304909005 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Belen | 15.5814 | 121.0484 | R | 2552 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0050 | PTCI/MIDC | 15.5844 | 121.051 | 0.44 | Terrestrial Optical Fiber Drop | 1.29 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4009 | 5 | 9 | 4009 | 0504111024 | Region V (Bicol Region) | Masbate | City of Masbate | Nursery | 12.3639 | 123.6276 | U | 12680 | 3092 | 928 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMSG0003 | PTCI/MIDC | 12.3658 | 123.6299 | 0.33 | Terrestrial Optical Fiber Drop | 1.36 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4010 | 5 | 10 | 4010 | 0704615005 | Region VII (Central Visayas) | Negros Oriental | Manjuyod | Bolisong | 9.6984 | 123.1566 | R | 3679 | 968 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0036 | PTCI/MIDC | 9.7006 | 123.1462 | 1.17 | Terrestrial Optical Fiber Drop | 12.57 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4011 | 5 | 11 | 4011 | 0402103036 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Ligas III | 14.4417 | 120.9717 | U | 8652 | 2544 | 763 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01894-C08 | PTCI/MIDC | 14.4392 | 120.9724 | 0.29 | Terrestrial Optical Fiber Drop | 2 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4012 | 5 | 12 | 4012 | 0401031007 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Bagumbayan | 14.0758 | 121.1391 | U | 7884 | 2190 | 657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1500 | FTAP Smart | 14.07 | 121.1327 | 0.95 | Terrestrial Optical Fiber Drop | 1.31 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4013 | 5 | 13 | 4013 | 0402106012 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran I | 14.3493 | 120.9407 | U | 5430 | 1597 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040177 | FTAP Globe | 14.315 | 120.9532 | 0.09 | Terrestrial Optical Fiber Drop | 0.18 | 5.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4014 | 5 | 14 | 4014 | 0702252017 | Region VII (Central Visayas) | Cebu | Tuburan | Cogon | 10.7126 | 123.8288 | R | 4393 | 1156 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0177 | PTCI/MIDC | 10.7293 | 123.8271 | 1.87 | Terrestrial Optical Fiber Drop | 19.66 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4015 | 5 | 15 | 4015 | 0401012038 | Region IV-A (CALABARZON) | Batangas | Lemery | Sambal Ilaya | 13.8836 | 120.9081 | R | 4367 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02456-C08 | PTCI/MIDC | 13.8905 | 120.9127 | 0.91 | Terrestrial Optical Fiber Drop | 1.29 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4016 | 5 | 16 | 4016 | 1130700074 | Region XI (Davao Region) | Davao del Sur | City of Davao | Matina Aplaya | 7.0464 | 125.5679 | U | 33709 | 9914 | 2974 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110493 | FTAP Globe | 7.0476 | 125.5666 | 0.19 | Terrestrial Optical Fiber Drop | 2.44 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4017 | 5 | 17 | 4017 | 0203101014 | Region II (Cagayan Valley) | Isabela | Alicia | Linglingay | 16.7984 | 121.6987 | R | 2856 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01320-B06 | PTCI/MIDC | 16.7871 | 121.6978 | 1.26 | Terrestrial Optical Fiber Drop | 1.66 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4018 | 5 | 18 | 4018 | 0405608017 | Region IV-A (CALABARZON) | Quezon | Candelaria | Masin Sur | 14.1683 | 121.4089 | U | 5233 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTQZG0006 | PTCI/MIDC | 13.9405 | 121.4289 | 0.32 | Terrestrial Optical Fiber Drop | 3.52 | 2.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4019 | 5 | 19 | 4019 | 0501730004 | Region V (Bicol Region) | Camarines Sur | Ragay | Apad | 13.8141 | 122.7678 | R | 2868 | 682 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03249-C10 | PTCI/MIDC | 13.8167 | 122.7702 | 0.38 | Terrestrial Optical Fiber Drop | 2.29 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4020 | 5 | 20 | 4020 | 0603006026 | Region VI (Western Visayas) | Iloilo | Banate | San Salvador | 10.9985 | 122.8343 | R | 3430 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02851-D13 | PTCI/MIDC | 10.9969 | 122.7958 | 4.21 | Terrestrial Optical Fiber Drop | 2.06 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4021 | 5 | 21 | 4021 | 0203127010 | Region II (Cagayan Valley) | Isabela | San Agustin | Masaya Sur | 16.4991 | 121.7463 | R | 2570 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01360-B06 | PTCI/MIDC | 16.5141 | 121.7471 | 1.66 | Terrestrial Optical Fiber Drop | 1.3 | 12.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4022 | 5 | 22 | 4022 | 0304930049 | Region III (Central Luzon) | Nueva Ecija | Talavera | Sampaloc | 15.5885 | 120.9318 | R | 1947 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0034 | PTCI/MIDC | 15.5909 | 120.933 | 0.3 | Terrestrial Optical Fiber Drop | 1.52 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4023 | 5 | 23 | 4023 | 0403403002 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Bungahan | 14.3024 | 121.0728 | R | 4179 | 1266 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040184 | FTAP Globe | 14.3064 | 121.075 | 0.51 | Terrestrial Optical Fiber Drop | 1.45 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4024 | 5 | 24 | 4024 | 0803738108 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Alta Vista | 11.0129 | 124.6209 | U | 5346 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080066 | FTAP BTS | 11.0119 | 124.6226 | 0.21 | Terrestrial Optical Fiber Drop | 2.18 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4025 | 5 | 25 | 4025 | 0501724026 | Region V (Bicol Region) | Camarines Sur | City of Naga | San Felipe | 13.6408 | 123.204 | U | 21048 | 5011 | 1503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050073 | FTAP Globe | 13.6442 | 123.2044 | 0.38 | Terrestrial Optical Fiber Drop | 1.43 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4026 | 5 | 26 | 4026 | 0500512030 | Region V (Bicol Region) | Albay | Oas | Maramba | 13.2238 | 123.4518 | R | 2945 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050073 | FTAP Globe | 13.6442 | 123.2044 | 0.38 | Terrestrial Optical Fiber Drop | 4.5 | 6.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4027 | 5 | 27 | 4027 | 0402114003 | Region IV-A (CALABARZON) | Cavite | Mendez | Galicia I | 14.1287 | 120.9067 | R | 2019 | 593 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03184-C08 | PTCI/MIDC | 14.129 | 120.9102 | 0.38 | Terrestrial Optical Fiber Drop | 1.3 | 3.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4028 | 5 | 28 | 4028 | 0304927013 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | San Roque | 15.3267 | 120.9254 | R | 3588 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0197 | FTAP Smart | 15.3283 | 120.9203 | 0.58 | Terrestrial Optical Fiber Drop | 2.22 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4029 | 5 | 29 | 4029 | 0401011006 | Region IV-A (CALABARZON) | Batangas | Laurel | Bugaan East | 14.0448 | 120.9413 | R | 2217 | 615 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 1.82 | Terrestrial Optical Fiber Drop | 1.24 | 5.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4030 | 5 | 30 | 4030 | 1430300086 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Pinget | 16.4319 | 120.5835 | U | 7818 | 2057 | 617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02596-B05 | PTCI/MIDC | 16.4339 | 120.5842 | 0.23 | Terrestrial Optical Fiber Drop | 1.3 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4031 | 5 | 31 | 4031 | 0306902010 | Region III (Central Luzon) | Tarlac | Bamban | San Nicolas | 15.2788 | 120.5221 | U | 20628 | 5289 | 1587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02239 | Edgepoint | 15.2783 | 120.5204 | 0.19 | Terrestrial Optical Fiber Drop | 1.3 | 2.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4032 | 5 | 32 | 4032 | 0402122015 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Luciano | 14.2685 | 120.8713 | U | 9480 | 2788 | 836 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040207 | FTAP Globe | 14.2674 | 120.8722 | 0.15 | Terrestrial Optical Fiber Drop | 1.57 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4033 | 5 | 33 | 4033 | 0501705040 | Region V (Bicol Region) | Camarines Sur | Buhi | Lourdes | 13.4081 | 123.5053 | R | 3832 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCSG0019 | PTCI/MIDC | 13.3969 | 123.5113 | 1.4 | Terrestrial Optical Fiber Drop | 1.3 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4034 | 5 | 34 | 4034 | 0203134014 | Region II (Cagayan Valley) | Isabela | Santa Maria | Poblacion 3 | 17.4638 | 121.7506 | R | 2266 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ISA-02500 | Edgepoint | 17.4581 | 121.7448 | 0.89 | Terrestrial Optical Fiber Drop | 1.31 | 4.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4035 | 5 | 35 | 4035 | 0307103001 | Region III (Central Luzon) | Zambales | Candelaria | Babancal | 15.619 | 119.947 | R | 2084 | 548 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03357-B07 | PTCI/MIDC | 15.6183 | 119.9418 | 0.57 | Terrestrial Optical Fiber Drop | 1.65 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4036 | 5 | 36 | 4036 | 0402109010 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma I | 14.4071 | 120.9357 | U | 4359 | 1282 | 385 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01872-C08 | PTCI/MIDC | 14.4172 | 120.9307 | 0.5 | Terrestrial Optical Fiber Drop | 0.54 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4037 | 5 | 37 | 4037 | 0201505030 | Region II (Cagayan Valley) | Cagayan | Aparri | Maura | 18.3547 | 121.6483 | U | 8322 | 2133 | 640 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02918-B06 | PTCI/MIDC | 18.3545 | 121.6525 | 0.44 | Terrestrial Optical Fiber Drop | 1.3 | 11.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4038 | 5 | 38 | 4038 | 0205005023 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | La Torre South | 16.4962 | 121.1366 | R | 2809 | 739 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNVG0016 | PTCI/MIDC | 16.5005 | 121.1392 | 0.56 | Terrestrial Optical Fiber Drop | 1.46 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4039 | 5 | 39 | 4039 | 0105543002 | Region I (Ilocos Region) | Pangasinan | Tayug | Amistad | 16.0076 | 120.7541 | R | 2478 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00476 | Edgepoint | 15.9942 | 120.7505 | 1.43 | Terrestrial Optical Fiber Drop | 2.16 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4040 | 5 | 40 | 4040 | 0500506049 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 51 - Buyuan | 13.2035 | 123.7426 | R | 4358 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0034 | PTCI/MIDC | 13.2044 | 123.7388 | 0.43 | Terrestrial Optical Fiber Drop | 5.28 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4041 | 5 | 41 | 4041 | 0501710002 | Region V (Bicol Region) | Camarines Sur | Canaman | Del Rosario | 13.6316 | 123.1702 | R | 3735 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050076 | FTAP Globe | 13.634 | 123.178 | 0.89 | Terrestrial Optical Fiber Drop | 1.31 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4042 | 5 | 42 | 4042 | 1030900046 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Ubaldo Laya | 8.2133 | 124.2523 | U | 13814 | 3635 | 1091 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0028 | PTCI/MIDC | 8.2202 | 124.2543 | 0.8 | Terrestrial Optical Fiber Drop | 2.12 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4043 | 5 | 43 | 4043 | 1630400087 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tungao | 8.9628 | 125.5376 | R | 4763 | 1161 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0016 | PTCI/MIDC | 8.7351 | 125.602 | 5.88 | Terrestrial Optical Fiber Drop | 1.3 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4044 | 5 | 44 | 4044 | 0402106026 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua I | 14.3201 | 120.9565 | U | 3587 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0020 | LDIC | 14.3227 | 120.9552 | 0.31 | Terrestrial Optical Fiber Drop | 1.31 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4045 | 5 | 45 | 4045 | 0301411007 | Region III (Central Luzon) | Bulacan | Marilao | Nagbalon | 14.7695 | 120.9686 | U | 3677 | 1050 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00996-B07 | PTCI/MIDC | 14.7701 | 120.9792 | 0.44 | Terrestrial Optical Fiber Drop | 2.02 | 2.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4046 | 5 | 46 | 4046 | 0301405014 | Region III (Central Luzon) | Bulacan | Bulacan | Santa Ines | 14.7849 | 120.8818 | R | 2508 | 716 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02984-B07 | PTCI/MIDC | 14.7832 | 120.8788 | 0.37 | Terrestrial Optical Fiber Drop | 1.31 | 4.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4047 | 5 | 47 | 4047 | 0301419012 | Region III (Central Luzon) | Bulacan | San Ildefonso | Calasag | 15.069 | 120.9307 | U | 3873 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-00894 | Edgepoint | 15.0739 | 120.9169 | 1.57 | Terrestrial Optical Fiber Drop | 1.44 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4048 | 5 | 48 | 4048 | 1401106008 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Ucab | 16.3747 | 120.6618 | U | 8989 | 2568 | 770 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BEN-00347 | Edgepoint | 16.3779 | 120.6735 | 1.29 | Terrestrial Optical Fiber Drop | 1.31 | 4.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4049 | 5 | 49 | 4049 | 0403424057 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Lucas 2 | 14.0872 | 121.3268 | U | 7097 | 2150 | 645 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040331 | FTAP Globe | 14.0884 | 121.3259 | 0.16 | Terrestrial Optical Fiber Drop | 1.31 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4050 | 5 | 50 | 4050 | 0908305015 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Lower Taway | 7.7836 | 122.5839 | R | 2576 | 613 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090142 | FTAP Globe | 7.7821 | 122.5819 | 1.25 | Terrestrial Optical Fiber Drop | 0.38 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4051 | 5 | 51 | 4051 | 0304903056 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Padre Crisostomo | 15.4904 | 120.9706 | R | 4685 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00686 | Edgepoint | 15.5089 | 120.972 | 0.96 | Terrestrial Optical Fiber Drop | 1.4 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4052 | 5 | 52 | 4052 | 0402123025 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Jose | 14.3313 | 121.0369 | R | 4558 | 1340 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0001 | PTCI/MIDC | 14.3376 | 121.0391 | 0.74 | Terrestrial Optical Fiber Drop | 1.5 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4053 | 5 | 53 | 4053 | 0205013015 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | San Luis | 16.5325 | 121.1859 | R | 2965 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02526-B05 | PTCI/MIDC | 16.5241 | 121.1859 | 0.93 | Terrestrial Optical Fiber Drop | 2.18 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4054 | 5 | 54 | 4054 | 0604521010 | Region VI (Western Visayas) | Negros Occidental | Pontevedra | Canroma | 10.3552 | 122.8812 | R | 3451 | 932 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060374 | FTAP Globe | 10.3746 | 122.8671 | 2.65 | Terrestrial Optical Fiber Drop | 2.42 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4055 | 5 | 55 | 4055 | 0401028009 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Fernando | 14.0261 | 121.1635 | R | 3211 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040531 | FTAP Globe | 13.8698 | 121.0537 | 1 | Terrestrial Optical Fiber Drop | 0.64 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4056 | 5 | 56 | 4056 | 1204704038 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Singao | 6.9953 | 125.0695 | U | 7952 | 2092 | 628 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120274 | FTAP Globe | 6.9986 | 125.081 | 1.32 | Terrestrial Optical Fiber Drop | 2.56 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4057 | 5 | 57 | 4057 | 0401005027 | Region IV-A (CALABARZON) | Batangas | Batangas City | Dumantay | 13.7656 | 121.1034 | U | 5924 | 1645 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03402-C08 | PTCI/MIDC | 13.7631 | 121.1069 | 0.47 | Terrestrial Optical Fiber Drop | 1.32 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4058 | 5 | 58 | 4058 | 0500514045 | Region V (Bicol Region) | Albay | Polangui | Sugcad | 13.3055 | 123.4866 | R | 4095 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 1.95 | Terrestrial Optical Fiber Drop | 1.41 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4059 | 5 | 59 | 4059 | 0730600044 | Region VII (Central Visayas) | Cebu | City of Cebu | Luz | 10.3243 | 123.9072 | U | 16195 | 5060 | 1518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0046 | PTCI/MIDC | 10.3223 | 123.9122 | 0.58 | Terrestrial Optical Fiber Drop | 1.32 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4060 | 5 | 60 | 4060 | 0301410015 | Region III (Central Luzon) | Bulacan | City of Malolos | Guinhawa | 14.8531 | 120.8178 | U | 4408 | 1259 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01147 | Edgepoint | 14.837 | 120.8261 | 0.25 | Terrestrial Optical Fiber Drop | 0.23 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4061 | 5 | 61 | 4061 | 0631000137 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Rizal Estanzuela | 10.6931 | 122.5604 | R | 3328 | 792 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0093 | PTCI/MIDC | 10.6978 | 122.5646 | 0.7 | Terrestrial Optical Fiber Drop | 1.95 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4062 | 5 | 62 | 4062 | 0401005044 | Region IV-A (CALABARZON) | Batangas | Batangas City | Malitam | 13.7442 | 121.0586 | U | 8817 | 2449 | 735 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040589 | FTAP Globe | 13.7414 | 121.0546 | 0.53 | Terrestrial Optical Fiber Drop | 2.02 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4063 | 5 | 63 | 4063 | 0504113018 | Region V (Bicol Region) | Masbate | Mobo | Pinamarbuhan | 12.3434 | 123.6486 | U | 3545 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03121-C10 | PTCI/MIDC | 12.3376 | 123.6441 | 0.81 | Terrestrial Optical Fiber Drop | 1.32 | 3.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4064 | 5 | 64 | 4064 | 1004324005 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Natumolan | 8.5345 | 124.7662 | U | 11232 | 2880 | 864 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100131 | FTAP Globe | 8.5245 | 124.7608 | 1.27 | Terrestrial Optical Fiber Drop | 1.53 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4065 | 5 | 65 | 4065 | 1600206005 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Mahayahay | 9.445 | 125.5843 | R | 3165 | 771 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 5.71 | Terrestrial Optical Fiber Drop | 1.86 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4066 | 5 | 66 | 4066 | 0301408004 | Region III (Central Luzon) | Bulacan | Guiguinto | Malis | 14.8403 | 120.8819 | U | 17614 | 5032 | 1510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01136 | Edgepoint | 14.8429 | 120.8826 | 0.3 | Terrestrial Optical Fiber Drop | 1.59 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4067 | 5 | 67 | 4067 | 0403411006 | Region IV-A (CALABARZON) | Laguna | Los Baños | Bayog | 14.1909 | 121.2444 | U | 12730 | 3857 | 1157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040257 | FTAP Globe | 14.1937 | 121.2396 | 0.61 | Terrestrial Optical Fiber Drop | 1.33 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4068 | 5 | 68 | 4068 | 0402106014 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin I | 14.3139 | 120.9507 | U | 12602 | 3706 | 1112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040177 | FTAP Globe | 14.315 | 120.9532 | 0.3 | Terrestrial Optical Fiber Drop | 1.62 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4069 | 5 | 69 | 4069 | 0301412014 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Longos | 14.7371 | 120.9481 | R | 3034 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02348 | Edgepoint | 14.7361 | 120.9496 | 0.2 | Terrestrial Optical Fiber Drop | 1.66 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4070 | 5 | 70 | 4070 | 0500504021 | Region V (Bicol Region) | Albay | Guinobatan | Maguiron | 13.1769 | 123.5994 | R | 2230 | 543 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0037 | PTCI/MIDC | 13.1678 | 123.6042 | 1.14 | Terrestrial Optical Fiber Drop | 1.38 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4071 | 5 | 71 | 4071 | 0600411012 | Region VI (Western Visayas) | Aklan | Makato | Dumga | 11.7296 | 122.2813 | R | 2516 | 645 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 1.13 | Terrestrial Optical Fiber Drop | 2.01 | 8.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4072 | 5 | 72 | 4072 | 0603026014 | Region VI (Western Visayas) | Iloilo | Leganes | Guintas | 10.7723 | 122.5968 | R | 2196 | 577 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060262 | FTAP Globe | 10.7625 | 122.5963 | 1.09 | Terrestrial Optical Fiber Drop | 1.12 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4073 | 5 | 73 | 4073 | 0401021020 | Region IV-A (CALABARZON) | Batangas | Rosario | Marilag | 13.8493 | 121.1796 | R | 3392 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03045-C08 | PTCI/MIDC | 13.8488 | 121.1704 | 1 | Terrestrial Optical Fiber Drop | 2.41 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4074 | 5 | 74 | 4074 | 0105530022 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Nama | 16.1306 | 120.5466 | R | 3315 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 2.03 | Terrestrial Optical Fiber Drop | 1.6 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4075 | 5 | 75 | 4075 | 0301420028 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Mulawin | 14.8068 | 121.0621 | U | 11734 | 3352 | 1006 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0010 | LDIC | 14.8082 | 121.0603 | 0.24 | Terrestrial Optical Fiber Drop | 1.33 | 1.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4076 | 5 | 76 | 4076 | 0702210015 | Region VII (Central Visayas) | Cebu | Barili | Japitan | 10.1272 | 123.4941 | R | 4354 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 2.04 | Terrestrial Optical Fiber Drop | 2.15 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4077 | 5 | 77 | 4077 | 0301424006 | Region III (Central Luzon) | Bulacan | Doña Remedios Trinidad | Pulong Sampalok | 14.9579 | 121.072 | U | 3736 | 1067 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01120-B07 | PTCI/MIDC | 14.9737 | 121.0659 | 1.87 | Terrestrial Optical Fiber Drop | 1.33 | 12.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4078 | 5 | 78 | 4078 | 0402102018 | Region IV-A (CALABARZON) | Cavite | Amadeo | Barangay V | 14.1673 | 120.9251 | R | 2081 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02223-C08 | PTCI/MIDC | 14.1743 | 120.9201 | 0.81 | Terrestrial Optical Fiber Drop | 0.34 | 3.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4079 | 5 | 79 | 4079 | 0304919010 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Malate | 15.5428 | 121.0843 | R | 2323 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00669 | Edgepoint | 15.5423 | 121.0839 | 0.07 | Terrestrial Optical Fiber Drop | 1.32 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4080 | 5 | 80 | 4080 | 1030500056 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Macasandig | 8.4638 | 124.6439 | U | 23657 | 6571 | 1971 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLR0013 | PTCI/MIDC | 8.4623 | 124.6435 | 0.17 | Terrestrial Optical Fiber Drop | 1.33 | 2.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4081 | 5 | 81 | 4081 | 0630200041 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 6 | 10.6618 | 122.9442 | R | 2233 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0004 | PTCI/MIDC | 10.6084 | 122.9533 | 1.37 | Terrestrial Optical Fiber Drop | 1.05 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4082 | 5 | 82 | 4082 | 0105526010 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Embarcadero | 16.0724 | 120.4163 | R | 2740 | 761 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02359-B07 | PTCI/MIDC | 16.0739 | 120.4161 | 0.17 | Terrestrial Optical Fiber Drop | 1.59 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4083 | 5 | 83 | 4083 | 0401029001 | Region IV-A (CALABARZON) | Batangas | Taal | Apacay | 13.9092 | 120.9266 | R | 2368 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02250-C08 | PTCI/MIDC | 13.9142 | 120.9312 | 0.74 | Terrestrial Optical Fiber Drop | 1.33 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4084 | 5 | 84 | 4084 | 0831600092 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 62 | 11.2208 | 125.0004 | R | 1776 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0068 | PTCI/MIDC | 11.2236 | 125.0004 | 0.32 | Terrestrial Optical Fiber Drop | 1.35 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4085 | 5 | 85 | 4085 | 0307109004 | Region III (Central Luzon) | Zambales | San Antonio | West Dirita | 14.9611 | 120.0745 | R | 4032 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N52 | FTAP Smart | 14.97 | 120.086 | 1.58 | Terrestrial Optical Fiber Drop | 2.08 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4086 | 5 | 86 | 4086 | 0506213016 | Region V (Bicol Region) | Sorsogon | Pilar | Dao | 12.923 | 123.6733 | R | 2534 | 633 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 0.87 | Terrestrial Optical Fiber Drop | 1.33 | 10.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4087 | 5 | 87 | 4087 | 0305405001 | Region III (Central Luzon) | Pampanga | Candaba | Bahay Pare | 15.0308 | 120.8828 | U | 12901 | 3225 | 968 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01631-B07 | PTCI/MIDC | 15.0268 | 120.8817 | 0.47 | Terrestrial Optical Fiber Drop | 1.98 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4088 | 5 | 88 | 4088 | 0203112020 | Region II (Cagayan Valley) | Isabela | Echague | Gucab | 16.7014 | 121.68 | R | 3209 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00275 | Edgepoint | 16.7034 | 121.6773 | 0.36 | Terrestrial Optical Fiber Drop | 1.34 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4089 | 5 | 89 | 4089 | 0631000001 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Santa Cruz | 10.7053 | 122.5625 | R | 3947 | 939 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02811-D13 | PTCI/MIDC | 10.7107 | 122.5574 | 0.56 | Terrestrial Optical Fiber Drop | 1.12 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4090 | 5 | 90 | 4090 | 1705202013 | MIMAROPA Region | Oriental Mindoro | Bansud | Proper Tiguisan | 12.8324 | 121.474 | R | 2310 | 592 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03377-C09 | PTCI/MIDC | 12.821 | 121.463 | 1.74 | Terrestrial Optical Fiber Drop | 1.52 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4091 | 5 | 91 | 4091 | 0402103064 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | San Nicolas II | 14.4332 | 120.9745 | U | 12673 | 3727 | 1118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01864-C08 | PTCI/MIDC | 14.4276 | 120.9749 | 0.63 | Terrestrial Optical Fiber Drop | 1.33 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4092 | 5 | 92 | 4092 | 0105543001 | Region I (Ilocos Region) | Pangasinan | Tayug | Agno | 16.0227 | 120.7306 | R | 2356 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00445 | Edgepoint | 16.0267 | 120.7436 | 1.46 | Terrestrial Optical Fiber Drop | 1.68 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4093 | 5 | 93 | 4093 | 1004317006 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Cabubuhan | 9.0182 | 125.1936 | R | 1884 | 483 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0089 | PTCI/MIDC | 9.0209 | 125.184 | 1.1 | Terrestrial Optical Fiber Drop | 1.33 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4094 | 5 | 94 | 4094 | 1430300087 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Pinsao Pilot Project | 16.4278 | 120.5812 | R | 4790 | 1260 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0004 | LDIC | 16.4259 | 120.5852 | 0.48 | Terrestrial Optical Fiber Drop | 1.34 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4095 | 5 | 95 | 4095 | 0403406014 | Region IV-A (CALABARZON) | Laguna | Calauan | Silangan | 14.1554 | 121.3159 | R | 1822 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02343-C08 | PTCI/MIDC | 14.1396 | 121.3118 | 1.44 | Terrestrial Optical Fiber Drop | 1.07 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4096 | 5 | 96 | 4096 | 0501606022 | Region V (Bicol Region) | Camarines Norte | Labo | Dalas | 14.1459 | 122.8207 | U | 5425 | 1356 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03169-C10 | PTCI/MIDC | 14.1294 | 122.8268 | 1.95 | Terrestrial Optical Fiber Drop | 1.61 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4097 | 5 | 97 | 4097 | 0501706027 | Region V (Bicol Region) | Camarines Sur | Bula | San Miguel | 13.4807 | 123.2705 | R | 2934 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03129-C10 | PTCI/MIDC | 13.4831 | 123.264 | 0.75 | Terrestrial Optical Fiber Drop | 1.34 | 4.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4098 | 5 | 98 | 4098 | 0702225012 | Region VII (Central Visayas) | Cebu | Ginatilan | Poblacion | 9.5712 | 123.3266 | R | 3292 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070369 | FTAP Globe | 9.5673 | 123.3118 | 1.68 | Terrestrial Optical Fiber Drop | 12.91 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4099 | 5 | 99 | 4099 | 1004324010 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Sugbongcogon | 8.5284 | 124.7532 | U | 4752 | 1218 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0098 | PTCI/MIDC | 8.5402 | 124.755 | 1.48 | Terrestrial Optical Fiber Drop | 1.08 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4100 | 5 | 100 | 4100 | 0201512006 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay III | 17.5591 | 121.6935 | R | 2704 | 693 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00113 | Edgepoint | 17.5573 | 121.6932 | 1.08 | Terrestrial Optical Fiber Drop | 0.43 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4101 | 5 | 101 | 4101 | 0402109058 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang I-C | 14.3888 | 120.9282 | R | 4692 | 1380 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4375 | FTAP Smart | 14.3878 | 120.9283 | 0.11 | Terrestrial Optical Fiber Drop | 1.34 | 5.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4102 | 5 | 102 | 4102 | 0630200060 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Vista Alegre | 10.6507 | 123.0147 | U | 33693 | 9359 | 2808 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0108 | PTCI/MIDC | 10.6512 | 122.9723 | 0.64 | Terrestrial Optical Fiber Drop | 2.76 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4103 | 5 | 103 | 4103 | 1102403001 | Region XI (Davao Region) | Davao del Sur | City of Digos | Aplaya | 6.7385 | 125.3804 | U | 19931 | 5862 | 1759 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110239 | FTAP BTS | 6.7379 | 125.3786 | 0.21 | Terrestrial Optical Fiber Drop | 1.77 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4104 | 5 | 104 | 4104 | 0403403014 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Mampalasan | 14.2917 | 121.0781 | U | 14892 | 4512 | 1354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01998-C08 | PTCI/MIDC | 14.2831 | 121.0762 | 0.98 | Terrestrial Optical Fiber Drop | 1.78 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4105 | 5 | 105 | 4105 | 0305420003 | Region III (Central Luzon) | Pampanga | Santa Rita | San Agustin | 14.9929 | 120.6004 | R | 4023 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00956 | Edgepoint | 14.9909 | 120.5988 | 0.29 | Terrestrial Optical Fiber Drop | 3.82 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4106 | 5 | 106 | 4106 | 0401020017 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Cawongan | 13.871 | 121.2265 | R | 4376 | 1215 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 1.27 | Terrestrial Optical Fiber Drop | 1.78 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4107 | 5 | 107 | 4107 | 0203135021 | Region II (Cagayan Valley) | Isabela | City of Santiago | Nabbuan | 16.6807 | 121.5649 | R | 4035 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02693-B06 | PTCI/MIDC | 16.6826 | 121.5642 | 0.23 | Terrestrial Optical Fiber Drop | 4.19 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4108 | 5 | 108 | 4108 | 0305416038 | Region III (Central Luzon) | Pampanga | City of San Fernando | Pulung Bulu | 15.128 | 120.612 | U | 6841 | 1710 | 513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00861 | Edgepoint | 15.1269 | 120.6133 | 0.18 | Terrestrial Optical Fiber Drop | 1.61 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4109 | 5 | 109 | 4109 | 0401031021 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Janopol Oriental | 14.0889 | 121.0978 | U | 3504 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040332 | FTAP Globe | 14.0871 | 121.0986 | 0.22 | Terrestrial Optical Fiber Drop | 1.35 | 5.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4110 | 5 | 110 | 4110 | 0704621021 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | Santa Cruz Nuevo | 9.5311 | 123.091 | R | 5180 | 1363 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070257 | FTAP Globe | 9.5389 | 123.1009 | 1.39 | Terrestrial Optical Fiber Drop | 7.47 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4111 | 5 | 111 | 4111 | 0301418008 | Region III (Central Luzon) | Bulacan | Pulilan | Dulong Malabon | 14.9207 | 120.8176 | R | 4300 | 1228 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00958-B07 | PTCI/MIDC | 14.9214 | 120.8096 | 0.87 | Terrestrial Optical Fiber Drop | 4.1 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4112 | 5 | 112 | 4112 | 0704603006 | Region VII (Central Visayas) | Negros Oriental | Bacong | Combado | 9.2472 | 123.2677 | R | 3914 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 2.99 | Terrestrial Optical Fiber Drop | 2.47 | 2.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4113 | 5 | 113 | 4113 | 0401007044 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Timbain | 13.9437 | 120.8112 | R | 2672 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040449 | FTAP Globe | 13.9358 | 120.813 | 0.9 | Terrestrial Optical Fiber Drop | 1.86 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4114 | 5 | 114 | 4114 | 0402117005 | Region IV-A (CALABARZON) | Cavite | Rosario | Ligtong I | 14.4276 | 120.8703 | R | 5045 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4398 | FTAP Smart | 14.4244 | 120.8705 | 0.36 | Terrestrial Optical Fiber Drop | 1.39 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4115 | 5 | 115 | 4115 | 0403405016 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Kay-Anlog | 14.1639 | 121.1194 | U | 22457 | 6805 | 2042 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03028-C08 | PTCI/MIDC | 14.1658 | 121.1231 | 0.46 | Terrestrial Optical Fiber Drop | 1.61 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4116 | 5 | 116 | 4116 | 0301415015 | Region III (Central Luzon) | Bulacan | Pandi | Pinagkuartelan | 14.8969 | 120.9805 | U | 7211 | 2060 | 618 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030169 | FTAP BTS | 14.8977 | 120.9836 | 0.34 | Terrestrial Optical Fiber Drop | 1.5 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4117 | 5 | 117 | 4117 | 0304924013 | Region III (Central Luzon) | Nueva Ecija | San Antonio | San Mariano | 15.3191 | 120.864 | U | 7925 | 2264 | 679 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0015 | LDIC | 15.3206 | 120.8687 | 0.53 | Terrestrial Optical Fiber Drop | 1.36 | 3.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4118 | 5 | 118 | 4118 | 0504101016 | Region V (Bicol Region) | Masbate | Aroroy | Jaboyoan | 12.5101 | 123.4113 | R | 2746 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 1.51 | Terrestrial Optical Fiber Drop | 1.35 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4119 | 5 | 119 | 4119 | 0301420058 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santo Niño II | 14.8455 | 121.048 | R | 3916 | 1118 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00954-B07 | PTCI/MIDC | 14.846 | 121.0199 | 0.54 | Terrestrial Optical Fiber Drop | 1.25 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4120 | 5 | 120 | 4120 | 0401010002 | Region IV-A (CALABARZON) | Batangas | Ibaan | Balanga | 13.8079 | 121.1405 | R | 2586 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040559 | FTAP Globe | 13.8144 | 121.1337 | 1.03 | Terrestrial Optical Fiber Drop | 1.63 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4121 | 5 | 121 | 4121 | 0604530012 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Pacol | 10.4717 | 122.8346 | R | 2098 | 567 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 2.43 | Terrestrial Optical Fiber Drop | 1.36 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4122 | 5 | 122 | 4122 | 0501724001 | Region V (Bicol Region) | Camarines Sur | City of Naga | Abella | 13.6291 | 123.24 | U | 5743 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCSG0032 | PTCI/MIDC | 13.6242 | 123.2293 | 0.72 | Terrestrial Optical Fiber Drop | 3.2 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4123 | 5 | 123 | 4123 | 0304910004 | Region III (Central Luzon) | Nueva Ecija | General Tinio | Padolina | 15.3467 | 121.0275 | U | 5721 | 1634 | 490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03336-B07 | PTCI/MIDC | 15.3501 | 121.0376 | 1.15 | Terrestrial Optical Fiber Drop | 1.36 | 8.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4124 | 5 | 124 | 4124 | 0306906021 | Region III (Central Luzon) | Tarlac | Gerona | Matayumcab | 15.589 | 120.5974 | R | 1905 | 488 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01807-B07 | PTCI/MIDC | 15.6057 | 120.6012 | 1.89 | Terrestrial Optical Fiber Drop | 1.4 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4125 | 5 | 125 | 4125 | 0105513017 | Region I (Ilocos Region) | Pangasinan | Binmaley | Lomboy | 16.0145 | 120.2614 | R | 3534 | 981 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010163 | FTAP Globe | 16.009 | 120.2529 | 1.09 | Terrestrial Optical Fiber Drop | 3.21 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4126 | 5 | 126 | 4126 | 0304911059 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santa Lucia | 15.658 | 120.7603 | R | 2406 | 687 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NUE_0005 | LDIC | 15.6738 | 120.7684 | 0.94 | Terrestrial Optical Fiber Drop | 0.69 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4127 | 5 | 127 | 4127 | 0402122005 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Lallana | 14.2683 | 120.8714 | R | 4353 | 1280 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040207 | FTAP Globe | 14.2674 | 120.8722 | 0.37 | Terrestrial Optical Fiber Drop | 1.59 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4128 | 5 | 128 | 4128 | 1102403011 | Region XI (Davao Region) | Davao del Sur | City of Digos | Kiagot | 6.7721 | 125.3652 | U | 6406 | 1884 | 565 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110260 | FTAP BTS | 6.7819 | 125.3632 | 1.11 | Terrestrial Optical Fiber Drop | 2.15 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4129 | 5 | 129 | 4129 | 0603032007 | Region VI (Western Visayas) | Iloilo | New Lucena | Bololacao | 10.8885 | 122.5895 | R | 2080 | 547 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 1.7 | Terrestrial Optical Fiber Drop | 1.45 | 2.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4130 | 5 | 130 | 4130 | 0301420030 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Yakal | 14.8088 | 121.0518 | R | 3889 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01031-B07 | PTCI/MIDC | 14.8086 | 121.0527 | 0.11 | Terrestrial Optical Fiber Drop | 1.83 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4131 | 5 | 131 | 4131 | 0305412029 | Region III (Central Luzon) | Pampanga | Masantol | Sto. Niño | 14.8643 | 120.685 | U | 3824 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH030564 | FTAP Globe | 14.8804 | 120.7061 | 1.11 | Terrestrial Optical Fiber Drop | 3.82 | 10.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4132 | 5 | 132 | 4132 | 0401027009 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Pacifico | 13.8616 | 120.9676 | R | 1841 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040537 | FTAP Globe | 13.8612 | 120.965 | 0.29 | Terrestrial Optical Fiber Drop | 1.87 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4133 | 5 | 133 | 4133 | 0205703001 | Region II (Cagayan Valley) | Quirino | Diffun | Andres Bonifacio | 16.6004 | 121.5036 | U | 3574 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_QUI_0002 | LDIC | 16.5992 | 121.5091 | 0.6 | Terrestrial Optical Fiber Drop | 1.38 | 7.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4134 | 5 | 134 | 4134 | 0305411019 | Region III (Central Luzon) | Pampanga | Magalang | San Vicente | 15.2013 | 120.6837 | R | 4568 | 1142 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030206 | FTAP BTS | 15.1917 | 120.6862 | 1.09 | Terrestrial Optical Fiber Drop | 4.27 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4135 | 5 | 135 | 4135 | 0603032001 | Region VI (Western Visayas) | Iloilo | New Lucena | Baclayan | 10.869 | 122.5901 | R | 2280 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 1.1 | Terrestrial Optical Fiber Drop | 1.38 | 2.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4136 | 5 | 136 | 4136 | 0402115031 | Region IV-A (CALABARZON) | Cavite | Naic | Timalan Balsahan | 14.3308 | 120.8013 | U | 19137 | 5628 | 1688 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040176 | FTAP Globe | 14.3157 | 120.7904 | 2.05 | Terrestrial Optical Fiber Drop | 1.38 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4137 | 5 | 137 | 4137 | 0403427005 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Cabooan | 14.4598 | 121.4269 | R | 2172 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040090 | FTAP Globe | 14.4653 | 121.4312 | 0.77 | Terrestrial Optical Fiber Drop | 1.38 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4138 | 5 | 138 | 4138 | 0604530006 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Central Tabao | 10.4605 | 122.8243 | R | 3643 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060372 | FTAP Globe | 10.4155 | 122.8522 | 2.1 | Terrestrial Optical Fiber Drop | 0.62 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4139 | 5 | 139 | 4139 | 0304924015 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Santo Cristo | 15.2977 | 120.8514 | U | 10181 | 2908 | 872 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00768 | Edgepoint | 15.3047 | 120.8562 | 0.93 | Terrestrial Optical Fiber Drop | 1.38 | 3.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4140 | 5 | 140 | 4140 | 0301420043 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Poblacion I | 14.8123 | 121.0457 | U | 5871 | 1677 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02327-B07 | PTCI/MIDC | 14.853 | 121.0673 | 0.2 | Terrestrial Optical Fiber Drop | 1.55 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4141 | 5 | 141 | 4141 | 0702220006 | Region VII (Central Visayas) | Cebu | Cordova | Dapitan | 10.2554 | 123.9441 | R | 3463 | 911 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0190 | PTCI/MIDC | 10.2481 | 123.9489 | 0.78 | Terrestrial Optical Fiber Drop | 0.82 | 6.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4142 | 5 | 142 | 4142 | 0301420035 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Lawang Pari | 14.856 | 121.071 | U | 5305 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01111 | Edgepoint | 14.8554 | 121.0703 | 0.11 | Terrestrial Optical Fiber Drop | 1.38 | 4.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4143 | 5 | 143 | 4143 | 0405620010 | Region IV-A (CALABARZON) | Quezon | Infanta | Banugao | 14.7448 | 121.6262 | R | 2508 | 660 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03110-A04 | PTCI/MIDC | 14.7488 | 121.6188 | 0.91 | Satellite LEO Backhaul (Starlink Business) | 1.38 | 39.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4144 | 5 | 144 | 4144 | 0203114024 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Cabannungan 2nd | 17.1251 | 121.8521 | R | 1919 | 505 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02902-B06 | PTCI/MIDC | 17.1313 | 121.8522 | 0.69 | Terrestrial Optical Fiber Drop | 1.4 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4145 | 5 | 145 | 4145 | 0307111007 | Region III (Central Luzon) | Zambales | San Marcelino | Laoag | 14.9769 | 120.1681 | R | 3366 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030515 | FTAP Globe | 14.9784 | 120.1827 | 1.58 | Terrestrial Optical Fiber Drop | 1.7 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4146 | 5 | 146 | 4146 | 0731300016 | Region VII (Central Visayas) | Cebu | City of Mandaue | Looc | 10.3232 | 123.9528 | U | 17412 | 4974 | 1492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0109 | PTCI/MIDC | 10.3249 | 123.9528 | 0.18 | Terrestrial Optical Fiber Drop | 1.39 | 1.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4147 | 5 | 147 | 4147 | 0704611031 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Tinayunan Beach | 10.104 | 123.2652 | R | 3973 | 1045 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0028 | LDIC | 10.0807 | 123.2574 | 2.72 | Terrestrial Optical Fiber Drop | 1.39 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4148 | 5 | 148 | 4148 | 0403402010 | Region IV-A (CALABARZON) | Laguna | Bay | San Antonio | 14.1934 | 121.2817 | U | 6281 | 1903 | 571 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 1 | Terrestrial Optical Fiber Drop | 1.39 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4149 | 5 | 149 | 4149 | 0402119020 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Sungay South | 14.1241 | 120.993 | R | 4933 | 1450 | 435 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02242-C08 | PTCI/MIDC | 14.1289 | 121.0001 | 0.93 | Terrestrial Optical Fiber Drop | 1.43 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4150 | 5 | 150 | 4150 | 0301420007 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Muzon | 14.7902 | 121.0301 | U | 133279 | 38079 | 11424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030610 | FTAP Globe | 14.7886 | 121.0338 | 0.43 | Terrestrial Optical Fiber Drop | 1.44 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4151 | 5 | 151 | 4151 | 0305416017 | Region III (Central Luzon) | Pampanga | City of San Fernando | Malpitic | 15.0806 | 120.6554 | U | 7967 | 1991 | 597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02687 | Edgepoint | 15.0784 | 120.6573 | 0.32 | Terrestrial Optical Fiber Drop | 1.49 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4152 | 5 | 152 | 4152 | 0403405028 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mapagong | 14.2333 | 121.1212 | U | 7952 | 2409 | 723 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0004 | PTCI/MIDC | 14.2333 | 121.1178 | 0.37 | Terrestrial Optical Fiber Drop | 1.69 | 1.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4153 | 5 | 153 | 4153 | 0405623007 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 4 | 14.1168 | 121.5499 | R | 2555 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02140-C08 | PTCI/MIDC | 14.1164 | 121.5576 | 1.27 | Terrestrial Optical Fiber Drop | 0.95 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4154 | 5 | 154 | 4154 | 1705209034 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Wawa | 13.0259 | 121.4517 | R | 4823 | 1236 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMRG0011 | PTCI/MIDC | 13.0381 | 121.4907 | 0.46 | Terrestrial Optical Fiber Drop | 3.14 | 2.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4155 | 5 | 155 | 4155 | 0304930009 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bantug | 15.5555 | 120.9128 | R | 5367 | 1533 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0002 | LDIC | 15.5604 | 120.9156 | 0.63 | Terrestrial Optical Fiber Drop | 3.02 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4156 | 5 | 156 | 4156 | 0702220010 | Region VII (Central Visayas) | Cebu | Cordova | Ibabao | 10.2718 | 123.9555 | U | 10458 | 2752 | 826 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0230 | PTCI/MIDC | 10.2681 | 123.9526 | 0.52 | Terrestrial Optical Fiber Drop | 1.4 | 6.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4157 | 5 | 157 | 4157 | 0803739015 | Region VIII (Eastern Visayas) | Leyte | Palo | Gacao | 11.1538 | 124.974 | R | 3621 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080019 | FTAP BTS | 11.1528 | 124.9789 | 0.54 | Terrestrial Optical Fiber Drop | 2.91 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4158 | 5 | 158 | 4158 | 1030500005 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Balulang | 8.4436 | 124.6342 | U | 42971 | 11936 | 3581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100154 | FTAP Globe | 8.4428 | 124.6339 | 0.09 | Terrestrial Optical Fiber Drop | 1.81 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4159 | 5 | 159 | 4159 | 0702224009 | Region VII (Central Visayas) | Cebu | Dumanjug | Calaboon | 10.0568 | 123.4213 | R | 2387 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0084 | PTCI/MIDC | 10.0456 | 123.429 | 1.51 | Terrestrial Optical Fiber Drop | 1.62 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4160 | 5 | 160 | 4160 | 0307114021 | Region III (Central Luzon) | Zambales | Subic | San Isidro | 14.8643 | 120.2573 | U | 9133 | 2403 | 721 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0013 | PTCI/MIDC | 14.8616 | 120.2482 | 1.02 | Terrestrial Optical Fiber Drop | 2.36 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4161 | 5 | 161 | 4161 | 0301413016 | Region III (Central Luzon) | Bulacan | Norzagaray | Minuyan | 14.8601 | 121.0845 | U | 11692 | 3340 | 1002 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-01090 | Edgepoint | 14.8689 | 121.0785 | 1.17 | Terrestrial Optical Fiber Drop | 1.41 | 5.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4162 | 5 | 162 | 4162 | 0702223009 | Region VII (Central Visayas) | Cebu | Danao City | Cambanay | 10.5388 | 124.0115 | R | 4418 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0082 | PTCI/MIDC | 10.5475 | 124.0154 | 1.06 | Terrestrial Optical Fiber Drop | 2.49 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4163 | 5 | 163 | 4163 | 0403425018 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | United Bayanihan | 14.3337 | 121.0293 | U | 5903 | 1788 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.13 | Terrestrial Optical Fiber Drop | 1.68 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4164 | 5 | 164 | 4164 | 0304925002 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Calaba | 15.3004 | 120.874 | U | 5766 | 1647 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01487-B07 | PTCI/MIDC | 15.3008 | 120.8777 | 0.4 | Terrestrial Optical Fiber Drop | 1.87 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4165 | 5 | 165 | 4165 | 1102408002 | Region XI (Davao Region) | Davao del Sur | Malalag | Baybay | 6.6007 | 125.4023 | R | 4517 | 1328 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110532 | FTAP Globe | 6.5977 | 125.4013 | 0.35 | Terrestrial Optical Fiber Drop | 1.41 | 5.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4166 | 5 | 166 | 4166 | 0501704001 | Region V (Bicol Region) | Camarines Sur | Bombon | San Antonio | 13.6911 | 123.2138 | R | 4362 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050069 | FTAP Globe | 13.6763 | 123.2048 | 1.92 | Terrestrial Optical Fiber Drop | 1.8 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4167 | 5 | 167 | 4167 | 0403427025 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Talangka | 14.4742 | 121.4327 | R | 2062 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040090 | FTAP Globe | 14.4653 | 121.4312 | 1 | Terrestrial Optical Fiber Drop | 1.41 | 3.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4168 | 5 | 168 | 4168 | 1731500066 | MIMAROPA Region | Palawan | City of Puerto Princesa | San Manuel | 9.7782 | 118.761 | U | 19070 | 5154 | 1546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170246 | FTAP Globe | 9.7771 | 118.7637 | 0.32 | Terrestrial Optical Fiber Drop | 2.4 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4169 | 5 | 169 | 4169 | 1705206028 | MIMAROPA Region | Oriental Mindoro | Gloria | Tambong | 12.9771 | 121.4912 | R | 3548 | 909 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 1.9 | Terrestrial Optical Fiber Drop | 2.47 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4170 | 5 | 170 | 4170 | 0501608006 | Region V (Bicol Region) | Camarines Norte | Paracale | Capacuan | 14.2482 | 122.735 | R | 2548 | 637 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050009 | FTAP Globe | 14.2156 | 122.7526 | 4.09 | Terrestrial Optical Fiber Drop | 1.41 | 7.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4171 | 5 | 171 | 4171 | 0604531029 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VI-A | 10.9097 | 123.0608 | U | 6586 | 1780 | 534 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0079 | PTCI/MIDC | 10.9046 | 123.0617 | 0.58 | Terrestrial Optical Fiber Drop | 1.63 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4172 | 5 | 172 | 4172 | 0301421033 | Region III (Central Luzon) | Bulacan | San Miguel | Paliwasan | 15.1199 | 120.9673 | R | 3387 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-00858 | Edgepoint | 15.1312 | 120.9589 | 1.55 | Terrestrial Optical Fiber Drop | 1.52 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4173 | 5 | 173 | 4173 | 0501709001 | Region V (Bicol Region) | Camarines Sur | Camaligan | Dugcal | 13.6262 | 123.1607 | R | 4830 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 1.25 | Terrestrial Optical Fiber Drop | 1.41 | 2.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4174 | 5 | 174 | 4174 | 1001317008 | Region X (Northern Mindanao) | Bukidnon | Quezon | Kiburiao | 7.6401 | 125.0911 | R | 4014 | 1056 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100216 | FTAP Globe | 7.6434 | 125.0934 | 0.45 | Terrestrial Optical Fiber Drop | 4.31 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4175 | 5 | 175 | 4175 | 0401009009 | Region IV-A (CALABARZON) | Batangas | Cuenca | Emmanuel | 13.8811 | 121.0516 | R | 2389 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 4617 | FTAP Smart | 13.8703 | 121.0551 | 1.26 | Terrestrial Optical Fiber Drop | 1.92 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4176 | 5 | 176 | 4176 | 0504113025 | Region V (Bicol Region) | Masbate | Mobo | Tabuc | 12.3259 | 123.6655 | R | 2692 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 1.28 | Terrestrial Optical Fiber Drop | 1.42 | 5.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4177 | 5 | 177 | 4177 | 0803738057 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Lao | 11.0265 | 124.5515 | R | 4489 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0048 | PTCI/MIDC | 11.0365 | 124.5646 | 1.81 | Terrestrial Optical Fiber Drop | 5.23 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4178 | 5 | 178 | 4178 | 0731100021 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Poblacion | 10.3089 | 123.9477 | U | 6241 | 1783 | 535 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0215 | PTCI/MIDC | 10.3131 | 123.9482 | 0.47 | Terrestrial Optical Fiber Drop | 1.42 | 2.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4179 | 5 | 179 | 4179 | 0402114005 | Region IV-A (CALABARZON) | Cavite | Mendez | Panungyan I | 14.1357 | 120.8952 | R | 2103 | 618 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040293 | FTAP Globe | 14.137 | 120.8946 | 0.89 | Terrestrial Optical Fiber Drop | 0.66 | 4.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4180 | 5 | 180 | 4180 | 0702243011 | Region VII (Central Visayas) | Cebu | San Remigio | Hagnaya | 11.0927 | 123.9431 | R | 4317 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070302 | FTAP Globe | 11.08 | 123.9405 | 1.44 | Terrestrial Optical Fiber Drop | 1.43 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4181 | 5 | 181 | 4181 | 0301411005 | Region III (Central Luzon) | Bulacan | Marilao | Lias | 14.7619 | 120.9653 | U | 15947 | 4556 | 1367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00994-B07 | PTCI/MIDC | 14.7632 | 120.964 | 0.21 | Terrestrial Optical Fiber Drop | 1.66 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4182 | 5 | 182 | 4182 | 1001321011 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Kahapunan | 7.9097 | 125.0939 | U | 7389 | 1944 | 583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 0.1 | Terrestrial Optical Fiber Drop | 0.45 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4183 | 5 | 183 | 4183 | 0201527006 | Region II (Cagayan Valley) | Cagayan | Solana | Bauan East | 17.7181 | 121.6881 | R | 2611 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 3809 | FTAP Smart | 17.7129 | 121.6903 | 0.63 | Terrestrial Optical Fiber Drop | 1.43 | 5.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4184 | 5 | 184 | 4184 | 0702250013 | Region VII (Central Visayas) | Cebu | City of Talisay | Pooc | 10.2412 | 123.8235 | U | 13217 | 3478 | 1043 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070361 | FTAP Globe | 10.2444 | 123.8249 | 0.39 | Terrestrial Optical Fiber Drop | 2.16 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4185 | 5 | 185 | 4185 | 0603043019 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Bolong Oeste | 10.8142 | 122.5292 | R | 2985 | 785 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0071 | PTCI/MIDC | 10.8136 | 122.532 | 0.32 | Terrestrial Optical Fiber Drop | 1.58 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4186 | 5 | 186 | 4186 | 0600401008 | Region VI (Western Visayas) | Aklan | Altavas | Lupo | 11.5073 | 122.4759 | R | 2284 | 585 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.93 | Terrestrial Optical Fiber Drop | 3.21 | 3.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4187 | 5 | 187 | 4187 | 0401006031 | Region IV-A (CALABARZON) | Batangas | Bauan | San Andres Proper | 13.7828 | 120.9974 | R | 2576 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1333 | FTAP Smart | 13.7875 | 121.0037 | 0.86 | Terrestrial Optical Fiber Drop | 1.44 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4188 | 5 | 188 | 4188 | 0603016001 | Region VI (Western Visayas) | Iloilo | Dingle | Abangay | 10.9599 | 122.6543 | R | 2492 | 655 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 2.29 | Terrestrial Optical Fiber Drop | 2.09 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4189 | 5 | 189 | 4189 | 0402103059 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu VIII | 14.4565 | 120.9548 | U | 8291 | 2438 | 731 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01871-C08 | PTCI/MIDC | 14.3949 | 120.9259 | 0.73 | Terrestrial Optical Fiber Drop | 0.42 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4190 | 5 | 190 | 4190 | 0304929031 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | San Fabian | 15.5969 | 120.9067 | R | 2828 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0030 | PTCI/MIDC | 15.6015 | 120.9038 | 0.6 | Terrestrial Optical Fiber Drop | 2.14 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4191 | 5 | 191 | 4191 | 0307110011 | Region III (Central Luzon) | Zambales | San Felipe | Sto. Niño | 15.0594 | 120.0641 | R | 5134 | 1351 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00898 | Edgepoint | 15.0678 | 120.0687 | 1.96 | Terrestrial Optical Fiber Drop | 0.67 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4192 | 5 | 192 | 4192 | 0402108025 | Region IV-A (CALABARZON) | Cavite | City of General Trias | San Juan I | 14.3826 | 120.8773 | U | 5496 | 1616 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01922-C08 | PTCI/MIDC | 14.3844 | 120.8815 | 0.5 | Terrestrial Optical Fiber Drop | 1.43 | 1.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4193 | 5 | 193 | 4193 | 0402116015 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael IV | 14.4315 | 120.8799 | R | 2585 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0042 | PTCI/MIDC | 14.4397 | 120.8833 | 0.65 | Terrestrial Optical Fiber Drop | 0.4 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4194 | 5 | 194 | 4194 | 0205702011 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Zamora | 16.5053 | 121.5223 | R | 3006 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQRG0004 | PTCI/MIDC | 16.51 | 121.5214 | 0.53 | Terrestrial Optical Fiber Drop | 1.43 | 2.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4195 | 5 | 195 | 4195 | 1401101002 | Cordillera Administrative Region (CAR) | Benguet | Atok | Caliking | 16.5342 | 120.7046 | R | 3459 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH010101 | FTAP Globe | 16.5149 | 120.4598 | 0.13 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4196 | 5 | 196 | 4196 | 0403426012 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Palasan | 14.2544 | 121.4202 | R | 3968 | 1202 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040213 | FTAP Globe | 14.2574 | 121.4184 | 0.39 | Terrestrial Optical Fiber Drop | 2.85 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4197 | 5 | 197 | 4197 | 0402103034 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay II | 14.4486 | 120.9442 | U | 12515 | 3680 | 1104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6818 | FTAP Smart | 14.4054 | 120.9592 | 0.54 | Terrestrial Optical Fiber Drop | 0.53 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4198 | 5 | 198 | 4198 | 0105526018 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Maasin | 16.0636 | 120.3756 | R | 4179 | 1160 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00428 | Edgepoint | 16.0514 | 120.3822 | 1.53 | Terrestrial Optical Fiber Drop | 2.89 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4199 | 5 | 199 | 4199 | 1403213022 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Magsaysay | 17.464 | 121.465 | U | 4642 | 1079 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140131 | FTAP Globe | 17.4672 | 121.4677 | 0.46 | Terrestrial Optical Fiber Drop | 1.44 | 3.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4200 | 5 | 200 | 4200 | 0501723046 | Region V (Bicol Region) | Camarines Sur | Nabua | Topas Proper | 13.4041 | 123.3142 | R | 2483 | 591 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03257-C10 | PTCI/MIDC | 13.4086 | 123.3098 | 0.7 | Terrestrial Optical Fiber Drop | 1.44 | 6.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4201 | 5 | 201 | 4201 | 0501603001 | Region V (Bicol Region) | Camarines Norte | Daet | Alawihao | 14.1097 | 122.9302 | U | 11314 | 2828 | 848 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCNG0005 | PTCI/MIDC | 14.1083 | 122.928 | 0.29 | Terrestrial Optical Fiber Drop | 2.59 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4202 | 5 | 202 | 4202 | 0402118004 | Region IV-A (CALABARZON) | Cavite | Silang | Balite II | 14.1834 | 120.9747 | R | 3039 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02199-C08 | PTCI/MIDC | 14.1841 | 120.9731 | 0.19 | Terrestrial Optical Fiber Drop | 2.95 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4203 | 5 | 203 | 4203 | 0402123027 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Tiniente Tiago | 14.3041 | 121.0074 | R | 3276 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02625-C08 | PTCI/MIDC | 14.3212 | 120.9965 | 0.66 | Terrestrial Optical Fiber Drop | 2.48 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4204 | 5 | 204 | 4204 | 0506207012 | Region V (Bicol Region) | Sorsogon | Donsol | Dancalan | 12.9152 | 123.5853 | R | 3567 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050213 | FTAP Globe | 12.9091 | 123.5966 | 1.4 | Terrestrial Optical Fiber Drop | 1.44 | 18.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4205 | 5 | 205 | 4205 | 0403404007 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Gulod | 14.2584 | 121.1656 | U | 18870 | 5718 | 1715 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040211 | FTAP Globe | 14.2629 | 121.162 | 0.64 | Terrestrial Optical Fiber Drop | 1.44 | 4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4206 | 5 | 206 | 4206 | 0403429019 | Region IV-A (CALABARZON) | Laguna | Siniloan | P. Burgos | 14.4527 | 121.4622 | R | 5267 | 1596 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040091 | FTAP Globe | 14.4629 | 121.4693 | 1.42 | Terrestrial Optical Fiber Drop | 2.32 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4207 | 5 | 207 | 4207 | 0631000168 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Santo Niño Sur | 10.6807 | 122.5004 | U | 9592 | 2283 | 685 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0025 | PTCI/MIDC | 10.6838 | 122.5002 | 0.34 | Terrestrial Optical Fiber Drop | 2.59 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4208 | 5 | 208 | 4208 | 0401017012 | Region IV-A (CALABARZON) | Batangas | Malvar | San Andres | 14.0029 | 121.1528 | R | 3330 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02249-C08 | PTCI/MIDC | 14.0027 | 121.1523 | 0.06 | Terrestrial Optical Fiber Drop | 2.21 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4209 | 5 | 209 | 4209 | 0402123021 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Nicolasa Virata | 14.3304 | 121.0354 | U | 6608 | 1943 | 583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.82 | Terrestrial Optical Fiber Drop | 1.65 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4210 | 5 | 210 | 4210 | 0405801014 | Region IV-A (CALABARZON) | Rizal | Angono | Mahabang Parang | 14.5476 | 121.1897 | U | 36264 | 10073 | 3022 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-02549 | Edgepoint | 14.5482 | 121.1896 | 0.07 | Terrestrial Optical Fiber Drop | 2.05 | 1.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4211 | 5 | 211 | 4211 | 0730600007 | Region VII (Central Visayas) | Cebu | City of Cebu | Banilad | 10.3467 | 123.9124 | U | 6344 | 1982 | 595 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0054 | PTCI/MIDC | 10.3473 | 123.9147 | 0.26 | Terrestrial Optical Fiber Drop | 1.44 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4212 | 5 | 212 | 4212 | 0506216038 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Balete | 13.0221 | 124.0282 | R | 2937 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 2.07 | Terrestrial Optical Fiber Drop | 1.45 | 5.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4213 | 5 | 213 | 4213 | 0401014052 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Quezon | 13.8994 | 121.1363 | R | 1966 | 546 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040437 | FTAP Globe | 13.9436 | 121.1805 | 0.09 | Terrestrial Optical Fiber Drop | 4.06 | 1.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4214 | 5 | 214 | 4214 | 0702219004 | Region VII (Central Visayas) | Cebu | Consolacion | Danglag | 10.3908 | 123.9565 | R | 4615 | 1214 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070325 | FTAP Globe | 10.3879 | 123.9644 | 0.92 | Terrestrial Optical Fiber Drop | 1.61 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4215 | 5 | 215 | 4215 | 0301414010 | Region III (Central Luzon) | Bulacan | Obando | San Pascual | 14.7206 | 120.9297 | U | 8121 | 2320 | 696 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1172 | FTAP Smart | 14.7213 | 120.9293 | 0.09 | Terrestrial Optical Fiber Drop | 1.45 | 2.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4216 | 5 | 216 | 4216 | 1102404012 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Lapulabao | 6.6794 | 125.2858 | R | 2062 | 606 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110527 | FTAP Globe | 6.6897 | 125.2969 | 1.68 | Terrestrial Optical Fiber Drop | 1.45 | 3.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4217 | 5 | 217 | 4217 | 0401016024 | Region IV-A (CALABARZON) | Batangas | Mabini | Sampaguita | 13.7207 | 120.9079 | R | 2341 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S1969 | FTAP Smart | 13.736 | 120.9315 | 0.3 | Terrestrial Optical Fiber Drop | 3.8 | 12.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4218 | 5 | 218 | 4218 | 0403405018 | Region IV-A (CALABARZON) | Laguna | City of Calamba | La Mesa | 14.1809 | 121.1569 | U | 19259 | 5836 | 1751 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040267 | FTAP Globe | 14.1824 | 121.1578 | 0.19 | Terrestrial Optical Fiber Drop | 2.16 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4219 | 5 | 219 | 4219 | 0201529003 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Bagay | 17.6329 | 121.7098 | R | 4085 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01138-B06 | PTCI/MIDC | 17.636 | 121.711 | 0.37 | Terrestrial Optical Fiber Drop | 4.09 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4220 | 5 | 220 | 4220 | 0301416002 | Region III (Central Luzon) | Bulacan | Paombong | Kapitangan | 14.8645 | 120.7876 | R | 4921 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02281 | Edgepoint | 14.865 | 120.7952 | 0.81 | Terrestrial Optical Fiber Drop | 3.37 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4221 | 5 | 221 | 4221 | 0105511041 | Region I (Ilocos Region) | Pangasinan | Bayambang | Malioer | 15.7785 | 120.3786 | R | 2593 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01711-B07 | PTCI/MIDC | 15.7747 | 120.3893 | 1.22 | Terrestrial Optical Fiber Drop | 1.46 | 7.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4222 | 5 | 222 | 4222 | 0501730016 | Region V (Bicol Region) | Camarines Sur | Ragay | Godofredo Reyes Sr. | 13.8778 | 122.6643 | R | 4336 | 1032 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050045 | FTAP Globe | 13.8174 | 122.7937 | 1.73 | Terrestrial Optical Fiber Drop | 4.93 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4223 | 5 | 223 | 4223 | 0305409017 | Region III (Central Luzon) | Pampanga | Mabalacat City | Marcos Village | 15.2031 | 120.4951 | R | 5259 | 1314 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1851 | FTAP Smart | 15.1875 | 120.4978 | 1.76 | Terrestrial Optical Fiber Drop | 4.33 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4224 | 5 | 224 | 4224 | 0401005007 | Region IV-A (CALABARZON) | Batangas | Batangas City | Banaba Kanluran | 13.8053 | 121.0542 | R | 4066 | 1129 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Z50 | FTAP Smart | 13.8032 | 121.0589 | 0.56 | Terrestrial Optical Fiber Drop | 3.49 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4225 | 5 | 225 | 4225 | 0501731004 | Region V (Bicol Region) | Camarines Sur | Sagñay | Buracan | 13.5998 | 123.5053 | R | 3143 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050090 | FTAP Globe | 13.6036 | 123.5204 | 1.68 | Terrestrial Optical Fiber Drop | 1.72 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4226 | 5 | 226 | 4226 | 0506209001 | Region V (Bicol Region) | Sorsogon | Irosin | Bagsangan | 12.722 | 124.0367 | R | 3114 | 778 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050226 | FTAP Globe | 12.7081 | 124.0387 | 1.56 | Terrestrial Optical Fiber Drop | 2.2 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4227 | 5 | 227 | 4227 | 0500503003 | Region V (Bicol Region) | Albay | Daraga | Anislag | 13.0636 | 123.6927 | U | 12920 | 3151 | 945 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050193 | FTAP Globe | 13.0676 | 123.7045 | 1.35 | Terrestrial Optical Fiber Drop | 1.48 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4228 | 5 | 228 | 4228 | 1600208009 | Region XIII (Caraga) | Agusan del Norte | Magallanes | Marcos | 9.0353 | 125.5251 | U | 3894 | 949 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130065 | FTAP Globe | 8.9969 | 125.4871 | 4.73 | Terrestrial Optical Fiber Drop | 0.26 | 7.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4229 | 5 | 229 | 4229 | 0401031008 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Balele | 14.0703 | 121.1017 | U | 10292 | 2858 | 857 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040347 | FTAP Globe | 14.0684 | 121.0998 | 0.3 | Terrestrial Optical Fiber Drop | 1.46 | 5.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4230 | 5 | 230 | 4230 | 0301419006 | Region III (Central Luzon) | Bulacan | San Ildefonso | Bagong Barrio | 15.0118 | 120.9877 | R | 2516 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030507 | FTAP Globe | 15.001 | 120.9731 | 1.98 | Terrestrial Optical Fiber Drop | 1.47 | 5.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4231 | 5 | 231 | 4231 | 1401105016 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Sebang | 16.7408 | 120.8262 | R | 2918 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140171 | FTAP Globe | 16.7237 | 120.784 | 4.88 | Terrestrial Optical Fiber Drop | 2.37 | 1.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4232 | 5 | 232 | 4232 | 0402114022 | Region IV-A (CALABARZON) | Cavite | Mendez | Galicia III | 14.1282 | 120.9078 | R | 4462 | 1312 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040293 | FTAP Globe | 14.137 | 120.8946 | 1.43 | Terrestrial Optical Fiber Drop | 1.41 | 3.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4233 | 5 | 233 | 4233 | 0702206022 | Region VII (Central Visayas) | Cebu | Asturias | Santa Lucia | 10.642 | 123.7533 | R | 4763 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0258 | PTCI/MIDC | 10.6781 | 123.8069 | 7.1 | Terrestrial Optical Fiber Drop | 15.39 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4234 | 5 | 234 | 4234 | 0203136005 | Region II (Cagayan Valley) | Isabela | Santo Tomas | Balelleng | 17.3785 | 121.7587 | R | 2056 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_ISA_0012 | LDIC | 121.7438 | 17.3639 | 2.27 | Terrestrial Optical Fiber Drop | 1.62 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4235 | 5 | 235 | 4235 | 0301409022 | Region III (Central Luzon) | Bulacan | Hagonoy | Santa Monica | 14.8391 | 120.7378 | U | 8538 | 2439 | 732 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0059 | PTCI/MIDC | 14.8374 | 120.7372 | 0.2 | Terrestrial Optical Fiber Drop | 1.47 | 2.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4236 | 5 | 236 | 4236 | 0405642004 | Region IV-A (CALABARZON) | Quezon | San Francisco | Cawayan I | 13.3642 | 122.5108 | R | 3855 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040623 | FTAP Globe | 13.3485 | 122.5191 | 1.2 | Terrestrial Optical Fiber Drop | 2.21 | 21.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4237 | 5 | 237 | 4237 | 0401020024 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Quilo-quilo North | 13.8652 | 121.222 | R | 3015 | 837 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 1.33 | Terrestrial Optical Fiber Drop | 2.37 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4238 | 5 | 238 | 4238 | 0304929024 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Malaya | 15.5793 | 120.8782 | R | 3809 | 1088 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0031 | PTCI/MIDC | 15.5809 | 120.8782 | 0.18 | Terrestrial Optical Fiber Drop | 1.48 | 4.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4239 | 5 | 239 | 4239 | 0701219010 | Region VII (Central Visayas) | Bohol | Dauis | Tinago | 9.6087 | 123.8257 | R | 3369 | 842 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBOG0016 | PTCI/MIDC | 9.6209 | 123.8133 | 1.91 | Terrestrial Optical Fiber Drop | 1.47 | 4.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4240 | 5 | 240 | 4240 | 0301407012 | Region III (Central Luzon) | Bulacan | Calumpit | Gugo | 14.9015 | 120.7547 | R | 2049 | 585 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030558 | FTAP Globe | 14.8933 | 120.7485 | 1.13 | Terrestrial Optical Fiber Drop | 1.51 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4241 | 5 | 241 | 4241 | 1404406005 | Cordillera Administrative Region (CAR) | Mountain Province | Paracelis | Butigue | 17.1021 | 121.4632 | R | 3221 | 870 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140137 | FTAP Globe | 17.184 | 121.4072 | 10.88 | Terrestrial Optical Fiber Drop | 1.47 | 16.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4242 | 5 | 242 | 4242 | 1600211007 | Region XIII (Caraga) | Agusan del Norte | Tubay | Poblacion 2 | 9.1571 | 125.547 | R | 3416 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130060 | FTAP Globe | 9.1659 | 125.5227 | 2.84 | Terrestrial Optical Fiber Drop | 1.52 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4243 | 5 | 243 | 4243 | 0506213051 | Region V (Bicol Region) | Sorsogon | Pilar | Santa Fe | 12.9256 | 123.6561 | R | 2436 | 609 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 1.08 | Terrestrial Optical Fiber Drop | 1.47 | 11.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4244 | 5 | 244 | 4244 | 0402103005 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Daang Bukid | 14.4414 | 120.9716 | R | 2989 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01894-C08 | PTCI/MIDC | 14.4392 | 120.9724 | 0.4 | Terrestrial Optical Fiber Drop | 1.97 | 1.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4245 | 5 | 245 | 4245 | 0305406024 | Region III (Central Luzon) | Pampanga | Floridablanca | San Antonio | 14.972 | 120.5265 | R | 3793 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00978 | Edgepoint | 14.9748 | 120.5295 | 0.45 | Terrestrial Optical Fiber Drop | 1.48 | 2.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4246 | 5 | 246 | 4246 | 0803726023 | Region VIII (Eastern Visayas) | Leyte | Kananga | Tugbong | 11.1669 | 124.5453 | R | 3789 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 2.19 | Terrestrial Optical Fiber Drop | 2.67 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4247 | 5 | 247 | 4247 | 0304932005 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Del Pilar | 15.4444 | 120.7996 | R | 4083 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 1.39 | Terrestrial Optical Fiber Drop | 1.3 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4248 | 5 | 248 | 4248 | 0506208034 | Region V (Bicol Region) | Sorsogon | Gubat | Rizal | 12.8823 | 124.1378 | R | 2717 | 679 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050219 | FTAP Globe | 12.8603 | 124.1471 | 2.64 | Terrestrial Optical Fiber Drop | 1.48 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4249 | 5 | 249 | 4249 | 0403422011 | Region IV-A (CALABARZON) | Laguna | Pila | Pansol | 14.2165 | 121.3737 | R | 2733 | 828 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040247 | FTAP Globe | 14.208 | 121.3811 | 1.23 | Terrestrial Optical Fiber Drop | 2.44 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4250 | 5 | 250 | 4250 | 0603019001 | Region VI (Western Visayas) | Iloilo | Estancia | Lumbia | 11.4446 | 123.1202 | R | 2238 | 588 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060014 | FTAP BTS | 11.4586 | 123.1301 | 1.89 | Terrestrial Optical Fiber Drop | 1.65 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4251 | 5 | 251 | 4251 | 0304929033 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | San Pascual | 15.5902 | 120.8652 | R | 3261 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0029 | PTCI/MIDC | 15.5903 | 120.8627 | 0.27 | Terrestrial Optical Fiber Drop | 1.48 | 5.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4252 | 5 | 252 | 4252 | 0401010008 | Region IV-A (CALABARZON) | Batangas | Ibaan | Lapu-lapu | 13.8289 | 121.1358 | R | 2116 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040552 | FTAP Globe | 13.8283 | 121.1127 | 0.88 | Terrestrial Optical Fiber Drop | 1.65 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4253 | 5 | 253 | 4253 | 0803740039 | Region VIII (Eastern Visayas) | Leyte | Palompon | San Miguel | 11.06 | 124.4058 | R | 2552 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 6.96 | Terrestrial Optical Fiber Drop | 2.35 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4254 | 5 | 254 | 4254 | 0301412007 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Camalig | 14.7721 | 120.9934 | U | 8768 | 2505 | 752 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01207 | Edgepoint | 14.7674 | 120.997 | 0.65 | Terrestrial Optical Fiber Drop | 1.48 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4255 | 5 | 255 | 4255 | 0631000014 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Sinikway | 10.7045 | 122.5625 | R | 2884 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0081 | PTCI/MIDC | 10.6964 | 122.5546 | 0.19 | Terrestrial Optical Fiber Drop | 1.2 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4256 | 5 | 256 | 4256 | 0831600121 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 88 | 11.2175 | 125.022 | R | 3711 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0098 | PTCI/MIDC | 11.2066 | 125.0214 | 1.21 | Terrestrial Optical Fiber Drop | 1.48 | 1.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4257 | 5 | 257 | 4257 | 0403407012 | Region IV-A (CALABARZON) | Laguna | Cavinti | Mahipon | 14.2672 | 121.5444 | R | 2713 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040203 | FTAP Globe | 14.2731 | 121.546 | 0.68 | Terrestrial Optical Fiber Drop | 1.49 | 9.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4258 | 5 | 258 | 4258 | 0105517015 | Region I (Ilocos Region) | Pangasinan | Calasiao | Mancup | 15.997 | 120.3618 | R | 3650 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00471 | Edgepoint | 16.0011 | 120.3605 | 0.47 | Terrestrial Optical Fiber Drop | 3.38 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4259 | 5 | 259 | 4259 | 1731500006 | MIMAROPA Region | Palawan | City of Puerto Princesa | Bagong Silang | 9.7304 | 118.7424 | U | 4351 | 1175 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B99 | FTAP Smart | 9.7346 | 118.7417 | 0.47 | Terrestrial Optical Fiber Drop | 1.49 | 2.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4260 | 5 | 260 | 4260 | 0803738087 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Santo Niño | 11.0422 | 124.5905 | R | 2994 | 787 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080192 | FTAP BTS | 11.0357 | 124.5932 | 0.79 | Terrestrial Optical Fiber Drop | 2.24 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4261 | 5 | 261 | 4261 | 0105506003 | Region I (Ilocos Region) | Pangasinan | Asingan | Ariston Weste | 16.0108 | 120.6603 | R | 3315 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.75 | Terrestrial Optical Fiber Drop | 1.2 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4262 | 5 | 262 | 4262 | 0201529038 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Annafunan West | 17.6431 | 121.7206 | R | 3822 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00091 | Edgepoint | 17.6237 | 121.7659 | 0.94 | Terrestrial Optical Fiber Drop | 2.96 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4263 | 5 | 263 | 4263 | 1401112006 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Bayabas | 16.475 | 120.4861 | R | 2532 | 723 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BEN-00324 | Edgepoint | 16.4767 | 120.5004 | 1.54 | Terrestrial Optical Fiber Drop | 2.66 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4264 | 5 | 264 | 4264 | 1001312064 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Sinanglanan | 7.992 | 125.2107 | R | 4077 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100198 | FTAP Globe | 7.9734 | 125.1346 | 8.64 | Terrestrial Optical Fiber Drop | 1.49 | 5.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4265 | 5 | 265 | 4265 | 0401026003 | Region IV-A (CALABARZON) | Batangas | San Pascual | Balimbing | 13.794 | 121.0394 | R | 2075 | 576 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1379 | FTAP Smart | 13.7835 | 121.0359 | 1.22 | Terrestrial Optical Fiber Drop | 1.54 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4266 | 5 | 266 | 4266 | 0501736009 | Region V (Bicol Region) | Camarines Sur | Tigaon | Gubat | 13.6324 | 123.4818 | R | 3580 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 1.4 | Terrestrial Optical Fiber Drop | 1.71 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4267 | 5 | 267 | 4267 | 0402103047 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino IV | 14.3818 | 120.9763 | U | 70412 | 20709 | 6213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01888-C08 | PTCI/MIDC | 14.3799 | 120.9775 | 0.24 | Terrestrial Optical Fiber Drop | 1.5 | 4.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4268 | 5 | 268 | 4268 | 0730600025 | Region VII (Central Visayas) | Cebu | City of Cebu | Day-as | 10.3214 | 123.8846 | U | 3820 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070335 | FTAP Globe | 10.3424 | 123.883 | 0.67 | Terrestrial Optical Fiber Drop | 1.69 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4269 | 5 | 269 | 4269 | 1130700156 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 23-C | 7.0865 | 125.6133 | U | 17720 | 5211 | 1563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0136 | PTCI/MIDC | 7.0708 | 125.621 | 0.53 | Terrestrial Optical Fiber Drop | 1.05 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4270 | 5 | 270 | 4270 | 0301407014 | Region III (Central Luzon) | Bulacan | Calumpit | Iba O'Este | 14.8896 | 120.7641 | U | 14723 | 4206 | 1262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3210 | FTAP Smart | 14.8903 | 120.762 | 0.23 | Terrestrial Optical Fiber Drop | 1.9 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4271 | 5 | 271 | 4271 | 0402109048 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma IX | 14.4077 | 120.9362 | R | 3087 | 907 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040141 | FTAP Globe | 14.3698 | 120.9382 | 1.38 | Terrestrial Optical Fiber Drop | 0.49 | 4.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4272 | 5 | 272 | 4272 | 0304915023 | Region III (Central Luzon) | Nueva Ecija | Llanera | Victoria | 15.6789 | 121.016 | R | 3471 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01467-B07 | PTCI/MIDC | 15.6627 | 121.0175 | 1.81 | Terrestrial Optical Fiber Drop | 1.5 | 6.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4273 | 5 | 273 | 4273 | 1102408014 | Region XI (Davao Region) | Davao del Sur | Malalag | New Baclayon | 6.5831 | 125.3702 | R | 4267 | 1255 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110157 | FTAP BTS | 6.6005 | 125.3863 | 2.63 | Terrestrial Optical Fiber Drop | 3.41 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4274 | 5 | 274 | 4274 | 0305408040 | Region III (Central Luzon) | Pampanga | Lubao | Santa Teresa 1st | 14.9246 | 120.5592 | R | 3826 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030534 | FTAP Globe | 14.9266 | 120.5618 | 0.35 | Terrestrial Optical Fiber Drop | 1.63 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4275 | 5 | 275 | 4275 | 1130700006 | Region XI (Davao Region) | Davao del Sur | City of Davao | Bago Oshiro | 7.0777 | 125.4975 | U | 18435 | 5422 | 1627 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110481 | FTAP Globe | 7.0856 | 125.4971 | 0.88 | Terrestrial Optical Fiber Drop | 1.54 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4276 | 5 | 276 | 4276 | 0401026012 | Region IV-A (CALABARZON) | Batangas | San Pascual | Laurel | 13.7955 | 121.0355 | R | 2554 | 709 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01939-C08 | PTCI/MIDC | 13.7844 | 121.0323 | 1.29 | Terrestrial Optical Fiber Drop | 1.56 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4277 | 5 | 277 | 4277 | 0401011001 | Region IV-A (CALABARZON) | Batangas | Laurel | As-Is | 14.0556 | 120.9201 | R | 2700 | 750 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 1.07 | Terrestrial Optical Fiber Drop | 1.5 | 3.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4278 | 5 | 278 | 4278 | 0105512009 | Region I (Ilocos Region) | Pangasinan | Binalonan | Linmansangan | 16.0482 | 120.5718 | U | 4124 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 1.93 | Terrestrial Optical Fiber Drop | 1.5 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4279 | 5 | 279 | 4279 | 0103302025 | Region I (Ilocos Region) | La Union | Aringay | Santa Rita West | 16.3532 | 120.3451 | R | 3652 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010106 | FTAP Globe | 16.3557 | 120.3531 | 0.9 | Terrestrial Optical Fiber Drop | 4.14 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4280 | 5 | 280 | 4280 | 0205706010 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Ponggo | 16.228 | 121.6055 | R | 2687 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1021 | FTAP Smart | 16.2289 | 121.6012 | 0.47 | Terrestrial Optical Fiber Drop | 1.51 | 5.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4281 | 5 | 281 | 4281 | 0704608009 | Region VII (Central Visayas) | Negros Oriental | City of Canlaon | Mabigo | 10.3894 | 123.217 | U | 12917 | 3399 | 1020 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0019 | PTCI/MIDC | 10.3878 | 123.22 | 0.37 | Terrestrial Optical Fiber Drop | 1.5 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4282 | 5 | 282 | 4282 | 0402103044 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog V | 14.4228 | 120.958 | R | 4034 | 1186 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01882-C08 | PTCI/MIDC | 14.3986 | 120.9556 | 0.48 | Terrestrial Optical Fiber Drop | 0.87 | 2.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4283 | 5 | 283 | 4283 | 0702232009 | Region VII (Central Visayas) | Cebu | Minglanilla | Pakigne | 10.2547 | 123.7921 | U | 14675 | 3861 | 1158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070012 | FTAP BTS | 10.2612 | 123.7963 | 0.5 | Terrestrial Optical Fiber Drop | 1.14 | 1.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4284 | 5 | 284 | 4284 | 1600203011 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Calibunan | 9.1064 | 125.5328 | R | 4316 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 2.18 | Terrestrial Optical Fiber Drop | 1.74 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4285 | 5 | 285 | 4285 | 0702220008 | Region VII (Central Visayas) | Cebu | Cordova | Gabi | 10.2627 | 123.9612 | U | 6279 | 1652 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00128-D12 | PTCI/MIDC | 10.263 | 123.9602 | 0.11 | Terrestrial Optical Fiber Drop | 1.5 | 7.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4286 | 5 | 286 | 4286 | 0702250009 | Region VII (Central Visayas) | Cebu | City of Talisay | Maghaway | 10.2722 | 123.8225 | U | 7280 | 1915 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070358 | FTAP Globe | 10.2604 | 123.8131 | 1.67 | Terrestrial Optical Fiber Drop | 2.29 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4287 | 5 | 287 | 4287 | 0305403030 | Region III (Central Luzon) | Pampanga | Arayat | Cupang | 15.1338 | 120.7886 | U | 4609 | 1152 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02355-B07 | PTCI/MIDC | 15.1347 | 120.7822 | 0.7 | Terrestrial Optical Fiber Drop | 2.05 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4288 | 5 | 288 | 4288 | 0702232014 | Region VII (Central Visayas) | Cebu | Minglanilla | Tubod | 10.2618 | 123.7969 | U | 5252 | 1382 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070012 | FTAP BTS | 10.2612 | 123.7963 | 0.1 | Terrestrial Optical Fiber Drop | 1.57 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4289 | 5 | 289 | 4289 | 0401005116 | Region IV-A (CALABARZON) | Batangas | Batangas City | Tulo | 13.7541 | 121.123 | R | 4488 | 1246 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03403-C08 | PTCI/MIDC | 13.7549 | 121.1135 | 1.03 | Terrestrial Optical Fiber Drop | 1.51 | 4.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4290 | 5 | 290 | 4290 | 0600407014 | Region VI (Western Visayas) | Aklan | Kalibo | Pook | 11.6915 | 122.3806 | U | 6509 | 1668 | 500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0005 | PTCI/MIDC | 11.6975 | 122.3768 | 0.79 | Terrestrial Optical Fiber Drop | 1.62 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4291 | 5 | 291 | 4291 | 0401006037 | Region IV-A (CALABARZON) | Batangas | Bauan | San Roque | 13.7943 | 120.9851 | U | 6554 | 1820 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040571 | FTAP Globe | 13.7886 | 120.9836 | 0.65 | Terrestrial Optical Fiber Drop | 1.92 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4292 | 5 | 292 | 4292 | 0403422008 | Region IV-A (CALABARZON) | Laguna | Pila | Linga | 14.2551 | 121.36 | R | 3924 | 1189 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040217 | FTAP Globe | 14.2501 | 121.3549 | 0.78 | Terrestrial Optical Fiber Drop | 2.1 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4293 | 5 | 293 | 4293 | 0403403024 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Timbao | 14.2823 | 121.0542 | U | 16951 | 5136 | 1541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02033-C08 | PTCI/MIDC | 14.2876 | 121.0557 | 0.61 | Terrestrial Optical Fiber Drop | 1.52 | 3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4294 | 5 | 294 | 4294 | 1403213030 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | San Juan | 17.4272 | 121.4457 | R | 3049 | 709 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH140132 | FTAP Globe | 17.4146 | 121.443 | 1.42 | Terrestrial Optical Fiber Drop | 1.63 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4295 | 5 | 295 | 4295 | 0305410019 | Region III (Central Luzon) | Pampanga | Macabebe | Sta. Maria | 14.9074 | 120.692 | U | 5441 | 1360 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 1.14 | Terrestrial Optical Fiber Drop | 2.38 | 7.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4296 | 5 | 296 | 4296 | 0301423005 | Region III (Central Luzon) | Bulacan | Santa Maria | Camangyanan | 14.7971 | 120.9709 | U | 5246 | 1498 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02419-B07 | PTCI/MIDC | 14.7971 | 120.9753 | 0.47 | Terrestrial Optical Fiber Drop | 2 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4297 | 5 | 297 | 4297 | 0831600136 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 110 | 11.2296 | 124.9929 | U | 7271 | 1773 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0071 | PTCI/MIDC | 11.2299 | 124.9912 | 0.19 | Terrestrial Optical Fiber Drop | 1.52 | 2.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4298 | 5 | 298 | 4298 | 0730600048 | Region VII (Central Visayas) | Cebu | City of Cebu | Malubog | 10.3795 | 123.8689 | R | 3320 | 1037 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0266 | PTCI/MIDC | 10.3934 | 123.8485 | 2.71 | Terrestrial Optical Fiber Drop | 1.51 | 5.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4299 | 5 | 299 | 4299 | 1004314002 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Gasi | 8.5877 | 124.443 | R | 2007 | 514 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 1.04 | Terrestrial Optical Fiber Drop | 1.52 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4300 | 5 | 300 | 4300 | 0600406014 | Region VI (Western Visayas) | Aklan | Ibajay | Laguinbanua | 11.7081 | 122.3481 | R | 3333 | 854 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060216 | FTAP Globe | 11.7192 | 122.3578 | 1.62 | Terrestrial Optical Fiber Drop | 2.27 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4301 | 5 | 301 | 4301 | 0831600120 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 87 | 11.2048 | 125.0223 | R | 3293 | 803 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0098 | PTCI/MIDC | 11.2066 | 125.0214 | 0.23 | Terrestrial Optical Fiber Drop | 1.64 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4302 | 5 | 302 | 4302 | 0501723012 | Region V (Bicol Region) | Camarines Sur | Nabua | Lourdes Young | 13.3867 | 123.3863 | R | 3601 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050125 | FTAP Globe | 13.3818 | 123.3726 | 1.58 | Terrestrial Optical Fiber Drop | 2.22 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4303 | 5 | 303 | 4303 | 0405804012 | Region IV-A (CALABARZON) | Rizal | Binangonan | Ithan | 14.4317 | 121.2143 | R | 3597 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00710-A04 | PTCI/MIDC | 14.4357 | 121.2093 | 0.7 | Terrestrial Optical Fiber Drop | 1.52 | 4.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4304 | 5 | 304 | 4304 | 0402116010 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo II | 14.4285 | 120.8761 | U | 6752 | 1985 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4398 | FTAP Smart | 14.4244 | 120.8705 | 0.14 | Terrestrial Optical Fiber Drop | 0.76 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4305 | 5 | 305 | 4305 | 0305406031 | Region III (Central Luzon) | Pampanga | Floridablanca | Sta. Monica | 14.9432 | 120.4989 | R | 4159 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01597-B07 | PTCI/MIDC | 14.9723 | 120.5012 | 1.4 | Terrestrial Optical Fiber Drop | 4.58 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4306 | 5 | 306 | 4306 | 0702220004 | Region VII (Central Visayas) | Cebu | Cordova | Catarman | 10.2482 | 123.9462 | U | 5976 | 1572 | 472 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0190 | PTCI/MIDC | 10.2481 | 123.9489 | 0.3 | Terrestrial Optical Fiber Drop | 1.53 | 7.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4307 | 5 | 307 | 4307 | 0405802018 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Muntingdilaw | 14.5974 | 121.1262 | U | 12938 | 3593 | 1078 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-RIZ-02195 | Edgepoint | 14.6017 | 121.1242 | 0.53 | Terrestrial Optical Fiber Drop | 1.57 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4308 | 5 | 308 | 4308 | 0201527039 | Region II (Cagayan Valley) | Cagayan | Solana | Bauan West | 17.718 | 121.6882 | R | 2754 | 706 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01149-B06 | PTCI/MIDC | 17.646 | 121.678 | 1.94 | Terrestrial Optical Fiber Drop | 1.41 | 5.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4309 | 5 | 309 | 4309 | 0631000005 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Alalasan Lapuz | 10.7051 | 122.5619 | R | 2929 | 697 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02858-D13 | PTCI/MIDC | 10.7032 | 122.5524 | 0.51 | Terrestrial Optical Fiber Drop | 1.17 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4310 | 5 | 310 | 4310 | 0304922001 | Region III (Central Luzon) | Nueva Ecija | Quezon | Bertese | 15.5748 | 120.8151 | R | 4278 | 1125 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030355 | FTAP Globe | 15.5757 | 120.8275 | 1.33 | Terrestrial Optical Fiber Drop | 1.88 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4311 | 5 | 311 | 4311 | 0301422018 | Region III (Central Luzon) | Bulacan | San Rafael | Pantubig | 14.9683 | 120.9513 | U | 3961 | 1131 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02413 | Edgepoint | 14.9672 | 120.9542 | 0.34 | Terrestrial Optical Fiber Drop | 1.53 | 3.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4312 | 5 | 312 | 4312 | 0731100012 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Gun-ob | 10.3017 | 123.9519 | U | 38005 | 10858 | 3257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070341 | FTAP Globe | 10.3064 | 123.9516 | 0.52 | Terrestrial Optical Fiber Drop | 1.53 | 3.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4313 | 5 | 313 | 4313 | 0304911003 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bacayao | 15.6625 | 120.7533 | R | 3022 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030336 | FTAP Globe | 15.6651 | 120.7496 | 0.49 | Terrestrial Optical Fiber Drop | 1.52 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4314 | 5 | 314 | 4314 | 0401005095 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Clara | 13.7531 | 121.0446 | U | 13224 | 3673 | 1102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01975-C08 | PTCI/MIDC | 13.7537 | 121.0448 | 0.07 | Terrestrial Optical Fiber Drop | 1.67 | 1.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4315 | 5 | 315 | 4315 | 0702220001 | Region VII (Central Visayas) | Cebu | Cordova | Alegria | 10.257 | 123.9605 | R | 4562 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00128-D12 | PTCI/MIDC | 10.263 | 123.9602 | 0.67 | Terrestrial Optical Fiber Drop | 1.53 | 8.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4316 | 5 | 316 | 4316 | 0401023039 | Region IV-A (CALABARZON) | Batangas | San Juan | Talahiban I | 13.8085 | 121.3906 | R | 2685 | 745 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02838-C08 | PTCI/MIDC | 13.814 | 121.3996 | 1.15 | Terrestrial Optical Fiber Drop | 1.54 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4317 | 5 | 317 | 4317 | 1030500064 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Puntod | 8.4998 | 124.6572 | U | 19116 | 5310 | 1593 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100136 | FTAP Globe | 8.5063 | 124.6472 | 1.32 | Terrestrial Optical Fiber Drop | 1.53 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4318 | 5 | 318 | 4318 | 0105545008 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Dalanguiring | 15.8384 | 120.3323 | U | 6510 | 1808 | 542 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTPNG0008 | PTCI/MIDC | 15.8222 | 120.356 | 0.73 | Terrestrial Optical Fiber Drop | 1.37 | 9.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4319 | 5 | 319 | 4319 | 0501705018 | Region V (Bicol Region) | Camarines Sur | Buhi | Monte Calvario | 13.4118 | 123.5275 | R | 3229 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCSG0019 | PTCI/MIDC | 13.3969 | 123.5113 | 2.4 | Terrestrial Optical Fiber Drop | 1.53 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4320 | 5 | 320 | 4320 | 0402117013 | Region IV-A (CALABARZON) | Cavite | Rosario | Bagbag II | 14.4207 | 120.8673 | U | 6477 | 1905 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0009 | LDIC | 14.42 | 120.8639 | 0.37 | Terrestrial Optical Fiber Drop | 1.96 | 1.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4321 | 5 | 321 | 4321 | 0601912024 | Region VI (Western Visayas) | Capiz | Pontevedra | Sublangon | 11.4786 | 122.8183 | R | 2648 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060102 | FTAP BTS | 11.4732 | 122.8116 | 0.95 | Terrestrial Optical Fiber Drop | 1.7 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4322 | 5 | 322 | 4322 | 0500511004 | Region V (Bicol Region) | Albay | Manito | Buyo | 13.1106 | 123.8656 | R | 4102 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050186 | FTAP Globe | 13.1258 | 123.8679 | 1.71 | Terrestrial Optical Fiber Drop | 1.54 | 12.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4323 | 5 | 323 | 4323 | 0301421059 | Region III (Central Luzon) | Bulacan | San Miguel | Tigpalas | 15.1662 | 120.995 | U | 4596 | 1313 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01047-B07 | PTCI/MIDC | 15.1819 | 120.9951 | 0.91 | Terrestrial Optical Fiber Drop | 2.37 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4324 | 5 | 324 | 4324 | 1600201003 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Alubijid | 8.9387 | 125.4574 | R | 4566 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130074 | FTAP Globe | 8.9527 | 125.4626 | 1.65 | Terrestrial Optical Fiber Drop | 4.93 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4325 | 5 | 325 | 4325 | 0701233006 | Region VII (Central Visayas) | Bohol | Panglao | Looc | 9.5904 | 123.7558 | R | 3153 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070426 | FTAP Globe | 9.5816 | 123.7493 | 1.2 | Terrestrial Optical Fiber Drop | 1.53 | 11.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4326 | 5 | 326 | 4326 | 1705312005 | MIMAROPA Region | Palawan | El Nido | Corong-corong Pob. | 11.1672 | 119.3981 | U | 4303 | 1103 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170211 | FTAP Globe | 11.1881 | 119.4005 | 2.35 | Satellite LEO Backhaul (Starlink Business) | 1.54 | 40.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4327 | 5 | 327 | 4327 | 0401014069 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Santo Toribio | 13.9046 | 121.2216 | R | 3707 | 1029 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040486 | FTAP Globe | 13.9189 | 121.2314 | 1.9 | Terrestrial Optical Fiber Drop | 1.55 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4328 | 5 | 328 | 4328 | 0401020002 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Banaybanay | 13.8993 | 121.2168 | R | 2409 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01954-C08 | PTCI/MIDC | 13.893 | 121.1996 | 1.98 | Terrestrial Optical Fiber Drop | 1.55 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4329 | 5 | 329 | 4329 | 0603043012 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Barangay Zone IV | 10.8218 | 122.5328 | R | 2064 | 543 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0103 | PTCI/MIDC | 10.8218 | 122.5258 | 0.76 | Terrestrial Optical Fiber Drop | 0.65 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4330 | 5 | 330 | 4330 | 0304903095 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Sumacab South | 15.49 | 120.9703 | U | 6296 | 1798 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01430-B07 | PTCI/MIDC | 15.4563 | 120.9571 | 1.17 | Terrestrial Optical Fiber Drop | 1.35 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4331 | 5 | 331 | 4331 | 0405809001 | Region IV-A (CALABARZON) | Rizal | Morong | Bombongan | 14.5059 | 121.2197 | R | 3722 | 1033 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040073 | FTAP Globe | 14.5102 | 121.2146 | 0.73 | Terrestrial Optical Fiber Drop | 1.67 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4332 | 5 | 332 | 4332 | 0330100017 | Region III (Central Luzon) | Pampanga | City of Angeles | Pampang | 15.1465 | 120.5754 | U | 25746 | 7151 | 2145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00840 | Edgepoint | 15.1502 | 120.575 | 0.42 | Terrestrial Optical Fiber Drop | 1.81 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4333 | 5 | 333 | 4333 | 0506211008 | Region V (Bicol Region) | Sorsogon | Magallanes | Behia | 12.8209 | 123.8203 | R | 2624 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 2.35 | Terrestrial Optical Fiber Drop | 2.12 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4334 | 5 | 334 | 4334 | 0306916093 | Region III (Central Luzon) | Tarlac | City of Tarlac | Ungot | 15.4605 | 120.6137 | R | 4178 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030044 | FTAP BTS | 15.4624 | 120.6117 | 0.3 | Terrestrial Optical Fiber Drop | 2.28 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4335 | 5 | 335 | 4335 | 1401114005 | Cordillera Administrative Region (CAR) | Benguet | Tublay | Daclan | 16.5003 | 120.6337 | R | 2450 | 700 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02312-B05 | PTCI/MIDC | 16.4768 | 120.6329 | 2.62 | Terrestrial Optical Fiber Drop | 2.55 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4336 | 5 | 336 | 4336 | 0501708029 | Region V (Bicol Region) | Camarines Sur | Calabanga | Salvacion-Baybay | 13.7212 | 123.2103 | R | 2795 | 665 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050061 | FTAP Globe | 13.7087 | 123.2167 | 1.55 | Terrestrial Optical Fiber Drop | 1.61 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4337 | 5 | 337 | 4337 | 0401014056 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Benito | 13.9307 | 121.218 | R | 4641 | 1289 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040465 | FTAP Globe | 13.9264 | 121.2118 | 0.82 | Terrestrial Optical Fiber Drop | 1.55 | 4.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4338 | 5 | 338 | 4338 | 0402120011 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan I | 14.4046 | 120.8468 | U | 5325 | 1566 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02821-C08 | PTCI/MIDC | 14.368 | 120.84 | 0.56 | Terrestrial Optical Fiber Drop | 1.79 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4339 | 5 | 339 | 4339 | 0301420008 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Poblacion | 14.8124 | 121.0456 | R | 2376 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01000-B07 | PTCI/MIDC | 14.8108 | 121.0462 | 0.19 | Terrestrial Optical Fiber Drop | 1.56 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4340 | 5 | 340 | 4340 | 0403422018 | Region IV-A (CALABARZON) | Laguna | Pila | Tubuan | 14.2322 | 121.3492 | R | 2530 | 766 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040233 | FTAP Globe | 14.2302 | 121.3513 | 0.32 | Terrestrial Optical Fiber Drop | 1.87 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4341 | 5 | 341 | 4341 | 0301422007 | Region III (Central Luzon) | Bulacan | San Rafael | Diliman I | 15.0259 | 120.9491 | R | 3799 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00931 | Edgepoint | 15.0241 | 120.9454 | 0.45 | Terrestrial Optical Fiber Drop | 2.05 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4342 | 5 | 342 | 4342 | 0501733019 | Region V (Bicol Region) | Camarines Sur | San Jose | Sabang | 13.7206 | 123.5767 | R | 2952 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 2.16 | Terrestrial Optical Fiber Drop | 6.06 | 9.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4343 | 5 | 343 | 4343 | 0501612005 | Region V (Bicol Region) | Camarines Norte | Vinzons | Calangcawan Norte | 14.1824 | 122.9192 | U | 4934 | 1233 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03144-C10 | PTCI/MIDC | 14.1847 | 122.9206 | 0.29 | Terrestrial Optical Fiber Drop | 1.56 | 4.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4344 | 5 | 344 | 4344 | 0403425027 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 2 | 14.3493 | 121.0477 | U | 13146 | 3983 | 1195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.53 | Terrestrial Optical Fiber Drop | 0.97 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4345 | 5 | 345 | 4345 | 0306917007 | Region III (Central Luzon) | Tarlac | Victoria | Bulo | 15.5686 | 120.6654 | R | 3161 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00654 | Edgepoint | 15.5761 | 120.6713 | 1.05 | Terrestrial Optical Fiber Drop | 1.56 | 5.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4346 | 5 | 346 | 4346 | 0402120023 | Region IV-A (CALABARZON) | Cavite | Tanza | Santol | 14.375 | 120.8733 | U | 10915 | 3210 | 963 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02195-C08 | PTCI/MIDC | 14.3836 | 120.8718 | 0.96 | Terrestrial Optical Fiber Drop | 1.56 | 2.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4347 | 5 | 347 | 4347 | 0500504030 | Region V (Bicol Region) | Albay | Guinobatan | Mauraro | 13.1419 | 123.5975 | U | 6861 | 1673 | 502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050177 | FTAP Globe | 13.1433 | 123.6026 | 0.58 | Terrestrial Optical Fiber Drop | 1.57 | 5.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4348 | 5 | 348 | 4348 | 0908305018 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Magdaup | 7.7614 | 122.5853 | U | 5831 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0026 | PTCI/MIDC | 7.7617 | 122.5825 | 0.31 | Terrestrial Optical Fiber Drop | 2.11 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4349 | 5 | 349 | 4349 | 1102315032 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Vicente | 7.3095 | 125.6997 | U | 19658 | 5312 | 1594 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0009 | PTCI/MIDC | 7.3135 | 125.6988 | 0.46 | Terrestrial Optical Fiber Drop | 2.36 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4350 | 5 | 350 | 4350 | 0402110005 | Region IV-A (CALABARZON) | Cavite | Indang | Bancod | 14.2107 | 120.8775 | R | 2769 | 814 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040242 | FTAP Globe | 14.2134 | 120.8868 | 1.05 | Terrestrial Optical Fiber Drop | 1.57 | 7.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4351 | 5 | 351 | 4351 | 0403402014 | Region IV-A (CALABARZON) | Laguna | Bay | Tagumpay | 14.193 | 121.2913 | R | 3418 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 1.36 | Terrestrial Optical Fiber Drop | 1.78 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4352 | 5 | 352 | 4352 | 1130700187 | Region XI (Davao Region) | Davao del Sur | City of Davao | Leon Garcia, Sr. | 7.1653 | 125.4712 | U | 13477 | 3963 | 1189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0124 | PTCI/MIDC | 7.0902 | 125.6281 | 0.88 | Terrestrial Optical Fiber Drop | 2.93 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4353 | 5 | 353 | 4353 | 0401025006 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Calangay | 13.9193 | 120.942 | R | 2202 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02250-C08 | PTCI/MIDC | 13.9142 | 120.9312 | 1.3 | Terrestrial Optical Fiber Drop | 1.57 | 3.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4354 | 5 | 354 | 4354 | 0402106065 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Agustin II | 14.318 | 120.9524 | U | 12308 | 3620 | 1086 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040177 | FTAP Globe | 14.315 | 120.9532 | 0.35 | Terrestrial Optical Fiber Drop | 1.56 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4355 | 5 | 355 | 4355 | 0304927006 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Magpapalayoc | 15.3757 | 120.9259 | U | 6395 | 1827 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030406 | FTAP Globe | 15.3766 | 120.9268 | 0.14 | Terrestrial Optical Fiber Drop | 1.72 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4356 | 5 | 356 | 4356 | 0704606027 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Villareal | 9.3571 | 122.8247 | U | 11172 | 2940 | 882 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0009 | PTCI/MIDC | 9.3595 | 122.8171 | 0.88 | Terrestrial Optical Fiber Drop | 1.57 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4357 | 5 | 357 | 4357 | 1108207017 | Region XI (Davao Region) | Davao de Oro | Monkayo | San Jose | 7.8463 | 126.0495 | R | 3211 | 867 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDOG0015 | PTCI/MIDC | 7.8475 | 126.0672 | 1.95 | Terrestrial Optical Fiber Drop | 2.23 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4358 | 5 | 358 | 4358 | 0300809029 | Region III (Central Luzon) | Bataan | Orani | Tagumpay | 14.8011 | 120.5192 | R | 2665 | 740 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03325-B07 | PTCI/MIDC | 14.7765 | 120.5213 | 0.91 | Terrestrial Optical Fiber Drop | 1.85 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4359 | 5 | 359 | 4359 | 0304912015 | Region III (Central Luzon) | Nueva Ecija | Jaen | Niyugan | 15.3239 | 120.8927 | U | 8041 | 2297 | 689 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030418 | FTAP Globe | 15.3172 | 120.8949 | 0.78 | Terrestrial Optical Fiber Drop | 1.57 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4360 | 5 | 360 | 4360 | 0402109050 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bucandala III | 14.407 | 120.9261 | U | 8837 | 2599 | 780 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 672 | FTAP Smart | 14.4064 | 120.9275 | 0.16 | Terrestrial Optical Fiber Drop | 1.57 | 3.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4361 | 5 | 361 | 4361 | 0402123026 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Severino De Las Alas | 14.3043 | 121.0078 | U | 8000 | 2352 | 706 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040206 | FTAP Globe | 14.2682 | 121.0073 | 1.71 | Terrestrial Optical Fiber Drop | 2.51 | 4.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4362 | 5 | 362 | 4362 | 0603045004 | Region VI (Western Visayas) | Iloilo | Tigbauan | Baguingin | 10.6949 | 122.403 | R | 3569 | 939 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0082 | PTCI/MIDC | 10.6764 | 122.3997 | 2.09 | Terrestrial Optical Fiber Drop | 2.96 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4363 | 5 | 363 | 4363 | 0301415014 | Region III (Central Luzon) | Bulacan | Pandi | Masuso | 14.882 | 120.9401 | U | 8688 | 2482 | 745 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-02581 | Edgepoint | 14.8983 | 120.94 | 1.82 | Terrestrial Optical Fiber Drop | 1.58 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4364 | 5 | 364 | 4364 | 0831600129 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 95 | 11.2093 | 124.9943 | U | 5396 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0099 | PTCI/MIDC | 11.2145 | 124.9956 | 0.59 | Terrestrial Optical Fiber Drop | 1.69 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4365 | 5 | 365 | 4365 | 0500516019 | Region V (Bicol Region) | Albay | Santo Domingo | San Andres | 13.2602 | 123.7777 | R | 4476 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ALB-03197 | Edgepoint | 13.2481 | 123.7819 | 1.42 | Terrestrial Optical Fiber Drop | 2.58 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4366 | 5 | 366 | 4366 | 0402119015 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Patutong Malaki South | 14.1101 | 120.9121 | R | 4452 | 1309 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02194-C08 | PTCI/MIDC | 14.1129 | 120.9094 | 0.42 | Terrestrial Optical Fiber Drop | 3.42 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4367 | 5 | 367 | 4367 | 0401008028 | Region IV-A (CALABARZON) | Batangas | Calatagan | Tanagan | 13.8182 | 120.6421 | R | 4734 | 1315 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1341 | FTAP Smart | 13.8225 | 120.6342 | 0.98 | Terrestrial Optical Fiber Drop | 1.58 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4368 | 5 | 368 | 4368 | 0305413021 | Region III (Central Luzon) | Pampanga | Mexico | Pandacaqui | 15.181 | 120.6472 | U | 30798 | 7699 | 2310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01590-B07 | PTCI/MIDC | 15.1803 | 120.6499 | 0.3 | Terrestrial Optical Fiber Drop | 2.16 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4369 | 5 | 369 | 4369 | 0201528012 | Region II (Cagayan Valley) | Cagayan | Tuao | Cato | 17.7342 | 121.4453 | R | 2687 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01183-B06 | PTCI/MIDC | 17.737 | 121.4557 | 1.14 | Terrestrial Optical Fiber Drop | 1.58 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4370 | 5 | 370 | 4370 | 0403410028 | Region IV-A (CALABARZON) | Laguna | Liliw | Maslun | 14.143 | 121.4388 | R | 3042 | 921 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 1.64 | Terrestrial Optical Fiber Drop | 0.8 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4371 | 5 | 371 | 4371 | 0604510009 | Region VI (Western Visayas) | Negros Occidental | City of Himamaylan | Nabali-an | 10.0031 | 122.9655 | R | 3678 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060383 | FTAP Globe | 10.1671 | 122.8599 | 2.47 | Terrestrial Optical Fiber Drop | 16.63 | 13.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4372 | 5 | 372 | 4372 | 0931700004 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Baliwasan | 6.915 | 122.0602 | U | 18696 | 5193 | 1558 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090192 | FTAP Globe | 6.9181 | 122.0618 | 0.39 | Terrestrial Optical Fiber Drop | 1.58 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4373 | 5 | 373 | 4373 | 0305402015 | Region III (Central Luzon) | Pampanga | Apalit | Tabuyuc | 14.9507 | 120.7737 | U | 9963 | 2490 | 747 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00997 | Edgepoint | 14.9564 | 120.7724 | 0.65 | Terrestrial Optical Fiber Drop | 1.58 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4374 | 5 | 374 | 4374 | 0604515029 | Region VI (Western Visayas) | Negros Occidental | City of Kabankalan | Talubangi | 10.0078 | 122.8036 | U | 4115 | 1112 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0099 | PTCI/MIDC | 10.0014 | 122.8061 | 0.77 | Terrestrial Optical Fiber Drop | 2.12 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4375 | 5 | 375 | 4375 | 0604504021 | Region VI (Western Visayas) | Negros Occidental | City of Cadiz | Sicaba | 10.9695 | 123.219 | R | 4465 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0034 | PTCI/MIDC | 10.9646 | 123.2001 | 2.14 | Terrestrial Optical Fiber Drop | 10.04 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4376 | 5 | 376 | 4376 | 0402110002 | Region IV-A (CALABARZON) | Cavite | Indang | Alulod | 14.2062 | 120.8894 | U | 5321 | 1565 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0062 | PTCI/MIDC | 14.2012 | 120.8889 | 0.56 | Terrestrial Optical Fiber Drop | 1.59 | 8.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4377 | 5 | 377 | 4377 | 0501601016 | Region V (Bicol Region) | Camarines Norte | Basud | Matnog | 14.0759 | 122.9455 | R | 3809 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050026 | FTAP Globe | 14.0713 | 122.9603 | 1.68 | Terrestrial Optical Fiber Drop | 4.39 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4378 | 5 | 378 | 4378 | 1705203024 | MIMAROPA Region | Oriental Mindoro | Bongabong | Sagana | 12.7264 | 121.5008 | R | 3181 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170114 | FTAP Globe | 12.7482 | 121.4852 | 2.96 | Terrestrial Optical Fiber Drop | 2.44 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4379 | 5 | 379 | 4379 | 1001317034 | Region X (Northern Mindanao) | Bukidnon | Quezon | Santa Cruz | 7.7023 | 125.1134 | R | 1983 | 521 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 1.37 | Terrestrial Optical Fiber Drop | 0.52 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4380 | 5 | 380 | 4380 | 0304903079 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Sumacab Norte | 15.4588 | 120.9338 | R | 5307 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1211 | FTAP Smart | 15.4576 | 120.9342 | 0.15 | Terrestrial Optical Fiber Drop | 3.39 | 1.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4381 | 5 | 381 | 4381 | 0603019004 | Region VI (Western Visayas) | Iloilo | Estancia | Botongon | 11.4625 | 123.1684 | U | 5152 | 1355 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ILI-03156 | Edgepoint | 11.4517 | 123.147 | 0.79 | Terrestrial Optical Fiber Drop | 4.6 | 6.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4382 | 5 | 382 | 4382 | 0301410001 | Region III (Central Luzon) | Bulacan | City of Malolos | Anilao | 14.8425 | 120.7977 | R | 3149 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01139 | Edgepoint | 14.8407 | 120.8008 | 0.39 | Terrestrial Optical Fiber Drop | 1.59 | 2.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4383 | 5 | 383 | 4383 | 0402106010 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sabang | 14.344 | 120.9264 | U | 18243 | 5365 | 1610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02637-C08 | PTCI/MIDC | 14.3489 | 120.9229 | 0.66 | Terrestrial Optical Fiber Drop | 1.6 | 5.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4384 | 5 | 384 | 4384 | 0701219007 | Region VII (Central Visayas) | Bohol | Dauis | Poblacion | 9.6241 | 123.8573 | R | 3015 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBOG0015 | PTCI/MIDC | 9.6184 | 123.8486 | 1.15 | Terrestrial Optical Fiber Drop | 2.32 | 1.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4385 | 5 | 385 | 4385 | 1204704029 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Paco | 7.0222 | 125.0303 | U | 3961 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH120077 | FTAP BTS | 7.0329 | 125.0495 | 2.43 | Terrestrial Optical Fiber Drop | 1.83 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4386 | 5 | 386 | 4386 | 0301410007 | Region III (Central Luzon) | Bulacan | City of Malolos | Balite | 14.8297 | 120.8368 | U | 3625 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00946-B07 | PTCI/MIDC | 14.8339 | 120.8349 | 0.51 | Terrestrial Optical Fiber Drop | 2.4 | 1.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4387 | 5 | 387 | 4387 | 0402108011 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Biclatan | 14.2778 | 120.9164 | U | 24320 | 7152 | 2146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02168-C08 | PTCI/MIDC | 14.2788 | 120.9146 | 0.22 | Terrestrial Optical Fiber Drop | 1.95 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4388 | 5 | 388 | 4388 | 0306905037 | Region III (Central Luzon) | Tarlac | Concepcion | Santo Niño | 15.3465 | 120.6311 | R | 4625 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030414 | FTAP Globe | 15.3356 | 120.6238 | 1.44 | Terrestrial Optical Fiber Drop | 3.38 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4389 | 5 | 389 | 4389 | 0330100026 | Region III (Central Luzon) | Pampanga | City of Angeles | Sta. Trinidad | 15.144 | 120.5806 | U | 6483 | 1800 | 540 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00840 | Edgepoint | 15.1502 | 120.575 | 0.44 | Terrestrial Optical Fiber Drop | 1.49 | 1.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4390 | 5 | 390 | 4390 | 0501708041 | Region V (Bicol Region) | Camarines Sur | Calabanga | Santa Cruz Ratay | 13.7121 | 123.2284 | U | 5443 | 1295 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02606 | Edgepoint | 13.7165 | 123.2373 | 2.02 | Terrestrial Optical Fiber Drop | 2.15 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4391 | 5 | 391 | 4391 | 0402106033 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis I | 14.3197 | 120.9567 | R | 4172 | 1227 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1052 | FTAP Smart | 14.3324 | 120.9753 | 0.25 | Terrestrial Optical Fiber Drop | 1.26 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4392 | 5 | 392 | 4392 | 1130700101 | Region XI (Davao Region) | Davao del Sur | City of Davao | Sasa | 7.1649 | 125.4717 | U | 57085 | 16789 | 5037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0051 | PTCI/MIDC | 7.1254 | 125.6604 | 0.44 | Terrestrial Optical Fiber Drop | 2.99 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4393 | 5 | 393 | 4393 | 0402106030 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Isidro Labrador I | 14.3407 | 120.9506 | R | 5089 | 1496 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 5796 | FTAP Smart | 14.3408 | 120.95 | 0.06 | Terrestrial Optical Fiber Drop | 1.61 | 4.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4394 | 5 | 394 | 4394 | 0305411014 | Region III (Central Luzon) | Pampanga | Magalang | San Nicolas 2nd | 15.2162 | 120.6601 | R | 4550 | 1137 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030434 | FTAP Globe | 15.2264 | 120.6858 | 1.02 | Terrestrial Optical Fiber Drop | 2.49 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4395 | 5 | 395 | 4395 | 0405648001 | Region IV-A (CALABARZON) | Quezon | Tiaong | Anastacia | 13.9647 | 121.3528 | R | 3853 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040389 | FTAP Globe | 13.9902 | 121.3571 | 2.88 | Terrestrial Optical Fiber Drop | 3.51 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4396 | 5 | 396 | 4396 | 1030900016 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Palao | 8.227 | 124.2552 | U | 10927 | 2875 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LDN_0004 | LDIC | 8.2257 | 124.2539 | 0.2 | Terrestrial Optical Fiber Drop | 1.62 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4397 | 5 | 397 | 4397 | 0103314012 | Region I (Ilocos Region) | La Union | City of San Fernando | Biday | 16.6153 | 120.3361 | U | 4436 | 1198 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1547 | FTAP Smart | 16.6157 | 120.3296 | 0.31 | Terrestrial Optical Fiber Drop | 2.35 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4398 | 5 | 398 | 4398 | 0506203030 | Region V (Bicol Region) | Sorsogon | Bulan | Lajong | 12.6798 | 123.9012 | R | 3711 | 927 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_SOR_0003 | LDIC | 12.666 | 123.8894 | 1.99 | Terrestrial Optical Fiber Drop | 3.27 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4399 | 5 | 399 | 4399 | 0305410014 | Region III (Central Luzon) | Pampanga | Macabebe | San Rafael | 14.9058 | 120.7042 | R | 3811 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01046 | Edgepoint | 14.9054 | 120.7014 | 0.31 | Terrestrial Optical Fiber Drop | 1.62 | 2.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4400 | 5 | 400 | 4400 | 0301420021 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay III | 14.8456 | 121.0485 | U | 5956 | 1701 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0008 | LDIC | 14.8299 | 121.0847 | 0.52 | Terrestrial Optical Fiber Drop | 1.29 | 5.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4401 | 5 | 401 | 4401 | 0301411004 | Region III (Central Luzon) | Bulacan | Marilao | Lambakin | 14.7655 | 120.971 | U | 50365 | 14390 | 4317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02435-B07 | PTCI/MIDC | 14.7694 | 120.97 | 0.45 | Terrestrial Optical Fiber Drop | 1.61 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4402 | 5 | 402 | 4402 | 0401005022 | Region IV-A (CALABARZON) | Batangas | Batangas City | Dela Paz | 13.6395 | 121.0937 | R | 2807 | 779 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBGG0007 | PTCI/MIDC | 13.6326 | 121.0737 | 2.3 | Terrestrial Optical Fiber Drop | 1.62 | 13.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4403 | 5 | 403 | 4403 | 0401005052 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pinamucan | 13.6979 | 121.0541 | R | 4422 | 1228 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040602 | FTAP Globe | 13.695 | 121.0596 | 0.67 | Terrestrial Optical Fiber Drop | 1.62 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4404 | 5 | 404 | 4404 | 0402103028 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Queens Row West | 14.3977 | 120.9893 | U | 11169 | 3285 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4722 | FTAP Smart | 14.4133 | 120.9523 | 0.27 | Terrestrial Optical Fiber Drop | 1.26 | 4.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4405 | 5 | 405 | 4405 | 0105522026 | Region I (Ilocos Region) | Pangasinan | Lingayen | Pangapisan North | 16.0235 | 120.215 | U | 8570 | 2380 | 714 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00449 | Edgepoint | 16.0239 | 120.2157 | 0.09 | Terrestrial Optical Fiber Drop | 1.89 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4406 | 5 | 406 | 4406 | 0402109073 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion I-C | 14.4348 | 120.9308 | R | 3227 | 949 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S34 | FTAP Smart | 14.435 | 120.9347 | 0.42 | Terrestrial Optical Fiber Drop | 1.69 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4407 | 5 | 407 | 4407 | 0402103006 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Digman | 14.4624 | 120.9431 | R | 2188 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040092 | FTAP Globe | 14.4604 | 120.9401 | 0.39 | Terrestrial Optical Fiber Drop | 1.77 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4408 | 5 | 408 | 4408 | 0631000121 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Obrero-Lapuz | 10.6974 | 122.5854 | U | 6980 | 1661 | 498 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060269 | FTAP Globe | 10.7073 | 122.5897 | 1.21 | Terrestrial Optical Fiber Drop | 2.63 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4409 | 5 | 409 | 4409 | 0401013013 | Region IV-A (CALABARZON) | Batangas | Lian | Luyahan | 13.959 | 120.6208 | R | 2746 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040412 | FTAP Globe | 13.96 | 120.6216 | 0.14 | Terrestrial Optical Fiber Drop | 1.86 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4410 | 5 | 410 | 4410 | 0402118003 | Region IV-A (CALABARZON) | Cavite | Silang | Balite I | 14.1998 | 120.981 | R | 3616 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040254 | FTAP Globe | 14.196 | 120.9818 | 0.42 | Terrestrial Optical Fiber Drop | 3.51 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4411 | 5 | 411 | 4411 | 0203108045 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Marabulig I | 16.9185 | 121.7464 | R | 4705 | 1238 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00225 | Edgepoint | 16.9204 | 121.7493 | 0.37 | Terrestrial Optical Fiber Drop | 2.76 | 1.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4412 | 5 | 412 | 4412 | 0301420006 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan I | 14.8448 | 121.0803 | R | 3484 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00997-B07 | PTCI/MIDC | 14.8172 | 121.059 | 0.41 | Terrestrial Optical Fiber Drop | 0.35 | 5.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4413 | 5 | 413 | 4413 | 0500501051 | Region V (Bicol Region) | Albay | Bacacay | Sogod | 13.3103 | 123.7669 | U | 5133 | 1251 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0033 | PTCI/MIDC | 13.3032 | 123.7738 | 1.09 | Terrestrial Optical Fiber Drop | 1.97 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4414 | 5 | 414 | 4414 | 1600302003 | Region XIII (Caraga) | Agusan del Sur | Bunawan | Libertad | 8.109 | 126.0234 | U | 6867 | 1760 | 528 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0009 | PTCI/MIDC | 8.2105 | 125.9905 | 3.02 | Terrestrial Optical Fiber Drop | 8.31 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4415 | 5 | 415 | 4415 | 1004326013 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Poblacion 3 | 8.5842 | 124.7718 | R | 4299 | 1102 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0080 | PTCI/MIDC | 8.5798 | 124.7768 | 1.25 | Terrestrial Optical Fiber Drop | 1.2 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4416 | 5 | 416 | 4416 | 0105526030 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Talogtog | 16.0842 | 120.3771 | R | 2595 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00413 | Edgepoint | 16.0837 | 120.3745 | 0.28 | Terrestrial Optical Fiber Drop | 2.41 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4417 | 5 | 417 | 4417 | 0701205015 | Region VII (Central Visayas) | Bohol | Baclayon | Santa Cruz | 9.6248 | 123.9217 | R | 1625 | 406 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 4.22 | Terrestrial Optical Fiber Drop | 0.97 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4418 | 5 | 418 | 4418 | 0300803022 | Region III (Central Luzon) | Bataan | City of Balanga | Tortugas | 14.6928 | 120.5601 | R | 2979 | 827 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030625 | FTAP Globe | 14.6875 | 120.5556 | 0.77 | Terrestrial Optical Fiber Drop | 1.89 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4419 | 5 | 419 | 4419 | 0405640006 | Region IV-A (CALABARZON) | Quezon | San Andres | Talisay | 13.2324 | 122.6999 | U | 5248 | 1381 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-02083 | Edgepoint | 13.2638 | 122.6803 | 4.08 | Satellite LEO Backhaul (Starlink Business) | 1.65 | 40.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4420 | 5 | 420 | 4420 | 0402106047 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol I | 14.3262 | 120.96 | U | 18198 | 5352 | 1606 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0027 | PTCI/MIDC | 14.3249 | 120.9627 | 0.32 | Terrestrial Optical Fiber Drop | 1.65 | 2.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4421 | 5 | 421 | 4421 | 0203115039 | Region II (Cagayan Valley) | Isabela | Jones | San Vicente | 16.5701 | 121.7102 | R | 2600 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0011 | PTCI/MIDC | 16.5697 | 121.7087 | 0.16 | Terrestrial Optical Fiber Drop | 1.65 | 13.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4422 | 5 | 422 | 4422 | 0306916035 | Region III (Central Luzon) | Tarlac | City of Tarlac | Dolores | 15.5241 | 120.5793 | R | 4143 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030368 | FTAP Globe | 15.5098 | 120.5775 | 1.6 | Terrestrial Optical Fiber Drop | 1.81 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4423 | 5 | 423 | 4423 | 1102507001 | Region XI (Davao Region) | Davao Oriental | Lupon | Bagumbayan | 6.9132 | 125.9966 | U | 5901 | 1639 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110509 | FTAP Globe | 6.9282 | 126.0077 | 2.07 | Terrestrial Optical Fiber Drop | 2.56 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4424 | 5 | 424 | 4424 | 0301406014 | Region III (Central Luzon) | Bulacan | Bustos | Tibagan | 14.9579 | 120.946 | U | 6790 | 1940 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00996 | Edgepoint | 14.9564 | 120.9432 | 0.34 | Terrestrial Optical Fiber Drop | 1.64 | 2.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4425 | 5 | 425 | 4425 | 1102315026 | Region XI (Davao Region) | Davao del Norte | City of Panabo | New Visayas | 7.3088 | 125.6677 | U | 19306 | 5217 | 1565 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0116 | PTCI/MIDC | 7.3067 | 125.6687 | 0.25 | Terrestrial Optical Fiber Drop | 1.65 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4426 | 5 | 426 | 4426 | 0405804026 | Region IV-A (CALABARZON) | Rizal | Binangonan | Palangoy | 14.507 | 121.1873 | U | 17102 | 4750 | 1425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-02403 | Edgepoint | 14.5072 | 121.1863 | 0.1 | Terrestrial Optical Fiber Drop | 1.67 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4427 | 5 | 427 | 4427 | 0506208003 | Region V (Bicol Region) | Sorsogon | Gubat | Balud Del Norte | 12.9153 | 124.0986 | R | 2050 | 512 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03159-C10 | PTCI/MIDC | 12.912 | 124.1171 | 0.87 | Terrestrial Optical Fiber Drop | 2.87 | 3.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4428 | 5 | 428 | 4428 | 0105518011 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Carael | 16.0381 | 120.316 | U | 6542 | 1817 | 545 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01749-B07 | PTCI/MIDC | 16.0375 | 120.3291 | 1.4 | Terrestrial Optical Fiber Drop | 2.44 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4429 | 5 | 429 | 4429 | 0402117002 | Region IV-A (CALABARZON) | Cavite | Rosario | Bagbag I | 14.4235 | 120.8678 | U | 6350 | 1867 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4398 | FTAP Smart | 14.4244 | 120.8705 | 0.3 | Terrestrial Optical Fiber Drop | 1.77 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4430 | 5 | 430 | 4430 | 0301420029 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Francisco Homes-Narra | 14.8101 | 121.0576 | U | 8668 | 2476 | 743 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0010 | LDIC | 14.8082 | 121.0603 | 0.36 | Terrestrial Optical Fiber Drop | 1.65 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4431 | 5 | 431 | 4431 | 0304906051 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | Ungab | 15.7993 | 120.6232 | R | 2242 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 1.09 | Terrestrial Optical Fiber Drop | 1.66 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4432 | 5 | 432 | 4432 | 0401018010 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Kinalaglagan | 14.003 | 121.0932 | R | 2744 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 2.78 | Terrestrial Optical Fiber Drop | 1.66 | 7.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4433 | 5 | 433 | 4433 | 0402106046 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño I | 14.3203 | 120.9561 | R | 3010 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040158 | FTAP Globe | 14.3361 | 120.9854 | 0.88 | Terrestrial Optical Fiber Drop | 1.36 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4434 | 5 | 434 | 4434 | 0702247017 | Region VII (Central Visayas) | Cebu | Sogod | Tabunok | 10.7821 | 124.018 | R | 4156 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0156 | PTCI/MIDC | 10.7893 | 124.0279 | 1.34 | Terrestrial Optical Fiber Drop | 3.68 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4435 | 5 | 435 | 4435 | 0305417004 | Region III (Central Luzon) | Pampanga | San Luis | San Jose | 15.0019 | 120.8695 | U | 7835 | 1958 | 587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030502 | FTAP Globe | 15.0168 | 120.8697 | 1.66 | Terrestrial Optical Fiber Drop | 1.68 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4436 | 5 | 436 | 4436 | 1401110003 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Ambiong | 16.4364 | 120.6043 | U | 8567 | 2447 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140180 | FTAP Globe | 16.4336 | 120.6065 | 0.39 | Terrestrial Optical Fiber Drop | 1.66 | 1.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4437 | 5 | 437 | 4437 | 0301412019 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Perez | 14.764 | 121.0009 | U | 19701 | 5628 | 1688 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02949-B07 | PTCI/MIDC | 14.7634 | 120.9991 | 0.21 | Terrestrial Optical Fiber Drop | 1.69 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4438 | 5 | 438 | 4438 | 0402109015 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-A | 14.3732 | 120.9284 | U | 16997 | 4999 | 1500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6862 | FTAP Smart | 14.3712 | 120.9292 | 0.24 | Terrestrial Optical Fiber Drop | 1.66 | 6.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4439 | 5 | 439 | 4439 | 0603018028 | Region VI (Western Visayas) | Iloilo | Dumangas | Pd Monfort North | 10.8426 | 122.7018 | R | 4633 | 1219 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 2.2 | Terrestrial Optical Fiber Drop | 2.05 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4440 | 5 | 440 | 4440 | 0500504022 | Region V (Bicol Region) | Albay | Guinobatan | Maipon | 13.213 | 123.5988 | R | 3802 | 927 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050163 | FTAP Globe | 13.2093 | 123.5802 | 2.05 | Terrestrial Optical Fiber Drop | 2.77 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4441 | 5 | 441 | 4441 | 0431200016 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Cotta | 13.9182 | 121.6081 | U | 21712 | 5428 | 1628 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040491 | FTAP Globe | 13.9133 | 121.6054 | 0.61 | Terrestrial Optical Fiber Drop | 1.71 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4442 | 5 | 442 | 4442 | 0402103052 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Niog III | 14.454 | 120.9579 | U | 4843 | 1424 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00408-A03 | PTCI/MIDC | 14.4199 | 121.0001 | 0.28 | Terrestrial Optical Fiber Drop | 0.36 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4443 | 5 | 443 | 4443 | 0702211011 | Region VII (Central Visayas) | Cebu | City of Bogo | Gairan | 11.0538 | 124.0215 | U | 10786 | 2838 | 851 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0017 | PTCI/MIDC | 11.0454 | 124.0265 | 1.08 | Terrestrial Optical Fiber Drop | 1.69 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4444 | 5 | 444 | 4444 | 0702220003 | Region VII (Central Visayas) | Cebu | Cordova | Buagsong | 10.2491 | 123.9397 | U | 5863 | 1542 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0186 | PTCI/MIDC | 10.251 | 123.9425 | 0.38 | Terrestrial Optical Fiber Drop | 1.67 | 7.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4445 | 5 | 445 | 4445 | 0330100004 | Region III (Central Luzon) | Pampanga | City of Angeles | Capaya | 15.145 | 120.6167 | U | 13161 | 3655 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00842 | Edgepoint | 15.1463 | 120.6112 | 0.61 | Terrestrial Optical Fiber Drop | 1.82 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4446 | 5 | 446 | 4446 | 0201507020 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Santa Cruz | 18.4012 | 121.5264 | R | 3836 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CAG_0024 | LDIC | 121.535 | 18.396 | 1.08 | Terrestrial Optical Fiber Drop | 1.67 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4447 | 5 | 447 | 4447 | 0301419034 | Region III (Central Luzon) | Bulacan | San Ildefonso | Sumandig | 15.0767 | 120.9834 | R | 2516 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030483 | FTAP Globe | 15.0649 | 120.973 | 1.72 | Terrestrial Optical Fiber Drop | 1.67 | 4.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4448 | 5 | 448 | 4448 | 1130700082 | Region XI (Davao Region) | Davao del Sur | City of Davao | New Carmen | 7.1504 | 125.5713 | R | 3114 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110461 | FTAP Globe | 7.162 | 125.5811 | 1.68 | Terrestrial Optical Fiber Drop | 1.67 | 2.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4449 | 5 | 449 | 4449 | 0402106019 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone IV | 14.3131 | 120.9719 | U | 3969 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0020 | LDIC | 14.3227 | 120.9552 | 0.07 | Terrestrial Optical Fiber Drop | 0.67 | 2.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4450 | 5 | 450 | 4450 | 0731300027 | Region VII (Central Visayas) | Cebu | City of Mandaue | Umapad | 10.3347 | 123.9609 | U | 18798 | 5370 | 1611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0115 | PTCI/MIDC | 10.3337 | 123.9616 | 0.13 | Terrestrial Optical Fiber Drop | 2.37 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4451 | 5 | 451 | 4451 | 1206511008 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Enrique J.C. Montilla | 6.6775 | 124.6731 | U | 6352 | 1671 | 501 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120131 | FTAP BTS | 6.6753 | 124.6699 | 0.29 | Terrestrial Optical Fiber Drop | 1.35 | 1.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4452 | 5 | 452 | 4452 | 0301413020 | Region III (Central Luzon) | Bulacan | Norzagaray | Partida | 14.8934 | 121.0286 | U | 7136 | 2038 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01062 | Edgepoint | 14.8917 | 121.0219 | 0.74 | Terrestrial Optical Fiber Drop | 1.68 | 3.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4453 | 5 | 453 | 4453 | 0604510015 | Region VI (Western Visayas) | Negros Occidental | City of Himamaylan | To-oy | 10.0522 | 122.8646 | R | 4749 | 1283 | 385 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060385 | FTAP Globe | 10.0499 | 122.8435 | 2.33 | Terrestrial Optical Fiber Drop | 8.71 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4454 | 5 | 454 | 4454 | 0931700076 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Santa Maria | 6.9291 | 122.0658 | U | 25161 | 6989 | 2097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0102 | PTCI/MIDC | 6.9287 | 122.0586 | 0.8 | Terrestrial Optical Fiber Drop | 2.26 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4455 | 5 | 455 | 4455 | 0402109066 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-E | 14.3601 | 120.9276 | R | 2500 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAV-03176 | Edgepoint | 14.3575 | 120.9237 | 0.51 | Terrestrial Optical Fiber Drop | 1.68 | 7.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4456 | 5 | 456 | 4456 | 0402109034 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-G | 14.4026 | 120.9403 | R | 2544 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1286 | FTAP Smart | 14.385 | 120.9131 | 0.16 | Terrestrial Optical Fiber Drop | 0.49 | 4.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4457 | 5 | 457 | 4457 | 0601905014 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Sur | 11.5222 | 122.6949 | R | 2503 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060229 | FTAP Globe | 11.5171 | 122.6938 | 2.07 | Terrestrial Optical Fiber Drop | 0.16 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4458 | 5 | 458 | 4458 | 0305412006 | Region III (Central Luzon) | Pampanga | Masantol | Bebe Anac | 14.8763 | 120.7076 | U | 7200 | 1800 | 540 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01074 | Edgepoint | 14.8802 | 120.7094 | 0.48 | Terrestrial Optical Fiber Drop | 1.69 | 1.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4459 | 5 | 459 | 4459 | 0402102003 | Region IV-A (CALABARZON) | Cavite | Amadeo | Dagatan | 14.1837 | 120.9317 | R | 3189 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040261 | FTAP Globe | 14.1898 | 120.9327 | 0.68 | Terrestrial Optical Fiber Drop | 1.69 | 3.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4460 | 5 | 460 | 4460 | 0501723044 | Region V (Bicol Region) | Camarines Sur | Nabua | Santo Domingo | 13.4077 | 123.3262 | U | 5911 | 1407 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | K36 | FTAP Smart | 13.4077 | 123.3288 | 0.29 | Terrestrial Optical Fiber Drop | 1.69 | 5.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4461 | 5 | 461 | 4461 | 0402109027 | Region IV-A (CALABARZON) | Cavite | City of Imus | Alapan I-C | 14.4022 | 120.9408 | U | 13166 | 3872 | 1162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1486 | FTAP Smart | 14.4256 | 120.9318 | 0.12 | Terrestrial Optical Fiber Drop | 0.53 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4462 | 5 | 462 | 4462 | 0306910023 | Region III (Central Luzon) | Tarlac | Paniqui | Patalan | 15.6452 | 120.5716 | R | 3387 | 868 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01797-B07 | PTCI/MIDC | 15.6418 | 120.5709 | 0.38 | Terrestrial Optical Fiber Drop | 3.03 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4463 | 5 | 463 | 4463 | 0907322034 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Muricay | 7.8255 | 123.467 | R | 3527 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0020 | PTCI/MIDC | 7.8296 | 123.4648 | 0.51 | Terrestrial Optical Fiber Drop | 3.11 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4464 | 5 | 464 | 4464 | 0401025015 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Sinturisan | 13.9073 | 120.9367 | R | 2301 | 639 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02250-C08 | PTCI/MIDC | 13.9142 | 120.9312 | 0.97 | Terrestrial Optical Fiber Drop | 1.73 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4465 | 5 | 465 | 4465 | 0631000064 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Guzman-Jesena | 10.705 | 122.5628 | U | 5717 | 1361 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 1.46 | Terrestrial Optical Fiber Drop | 1.12 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4466 | 5 | 466 | 4466 | 0730600075 | Region VII (Central Visayas) | Cebu | City of Cebu | Suba Pob. | 10.3004 | 123.8962 | U | 10619 | 3318 | 995 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0266 | PTCI/MIDC | 10.3934 | 123.8485 | 3.39 | Terrestrial Optical Fiber Drop | 0.32 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4467 | 5 | 467 | 4467 | 0631000031 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Calaparan | 10.6824 | 122.5297 | U | 9480 | 2257 | 677 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060113 | FTAP BTS | 10.6817 | 122.5268 | 0.33 | Terrestrial Optical Fiber Drop | 1.69 | 3.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4468 | 5 | 468 | 4468 | 0504111015 | Region V (Bicol Region) | Masbate | City of Masbate | Espinosa | 12.3752 | 123.6209 | U | 7138 | 1740 | 522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03025-C10 | PTCI/MIDC | 12.3717 | 123.6207 | 0.39 | Terrestrial Optical Fiber Drop | 2.02 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4469 | 5 | 469 | 4469 | 0402118055 | Region IV-A (CALABARZON) | Cavite | Silang | Banaba | 14.2252 | 120.9623 | U | 6648 | 1955 | 587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02174-C08 | PTCI/MIDC | 14.1997 | 120.9896 | 1.35 | Terrestrial Optical Fiber Drop | 6.76 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4470 | 5 | 470 | 4470 | 0405814009 | Region IV-A (CALABARZON) | Rizal | Teresa | San Roque | 14.5584 | 121.2137 | R | 3326 | 923 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040048 | FTAP Globe | 14.5658 | 121.2287 | 0.48 | Terrestrial Optical Fiber Drop | 0.69 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4471 | 5 | 471 | 4471 | 0305410003 | Region III (Central Luzon) | Pampanga | Macabebe | Candelaria | 14.8837 | 120.7204 | R | 3215 | 803 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030565 | FTAP Globe | 14.8791 | 120.7282 | 0.99 | Terrestrial Optical Fiber Drop | 1.69 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4472 | 5 | 472 | 4472 | 0402106076 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cristina II | 14.3218 | 120.9711 | R | 3690 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1214 | FTAP Smart | 14.2686 | 120.9829 | 1.25 | Terrestrial Optical Fiber Drop | 1.19 | 2.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4473 | 5 | 473 | 4473 | 0501612018 | Region V (Bicol Region) | Camarines Norte | Vinzons | Santo Domingo | 14.1534 | 122.8987 | R | 4471 | 1117 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCNG0012 | PTCI/MIDC | 14.1399 | 122.8921 | 1.66 | Terrestrial Optical Fiber Drop | 2.5 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4474 | 5 | 474 | 4474 | 0402101022 | Region IV-A (CALABARZON) | Cavite | Alfonso | Upli | 14.0929 | 120.8636 | R | 2653 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02180-C08 | PTCI/MIDC | 14.0893 | 120.858 | 0.72 | Terrestrial Optical Fiber Drop | 2.08 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4475 | 5 | 475 | 4475 | 0300805015 | Region III (Central Luzon) | Bataan | Hermosa | Pandatung | 14.8263 | 120.4701 | R | 2529 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03322-B07 | PTCI/MIDC | 14.8195 | 120.466 | 0.87 | Terrestrial Optical Fiber Drop | 2.1 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4476 | 5 | 476 | 4476 | 0301420012 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Citrus | 14.8482 | 121.0649 | U | 23929 | 6836 | 2051 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030581 | FTAP Globe | 14.849 | 121.0643 | 0.12 | Terrestrial Optical Fiber Drop | 1.7 | 3.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4477 | 5 | 477 | 4477 | 0301410013 | Region III (Central Luzon) | Bulacan | City of Malolos | Bungahan | 14.863 | 120.843 | R | 3162 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02587 | Edgepoint | 14.863 | 120.8422 | 0.09 | Terrestrial Optical Fiber Drop | 2.89 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4478 | 5 | 478 | 4478 | 0931700068 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Rio Hondo | 6.899 | 122.0853 | U | 9203 | 2556 | 767 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0097 | PTCI/MIDC | 6.9031 | 122.0905 | 0.73 | Terrestrial Optical Fiber Drop | 1.79 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4479 | 5 | 479 | 4479 | 0402106023 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Luzviminda I | 14.3203 | 120.957 | R | 3753 | 1103 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0061 | PTCI/MIDC | 14.3253 | 120.9634 | 0.37 | Terrestrial Optical Fiber Drop | 1.28 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4480 | 5 | 480 | 4480 | 0402118038 | Region IV-A (CALABARZON) | Cavite | Silang | Pulong Bunga | 14.1728 | 120.9849 | R | 3810 | 1120 | 336 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02207-C08 | PTCI/MIDC | 14.1713 | 120.9829 | 0.27 | Terrestrial Optical Fiber Drop | 2.41 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4481 | 5 | 481 | 4481 | 0402106062 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc III | 14.2918 | 120.9747 | U | 14535 | 4275 | 1283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040196 | FTAP Globe | 14.285 | 120.978 | 0.84 | Terrestrial Optical Fiber Drop | 1.95 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4482 | 5 | 482 | 4482 | 1102403022 | Region XI (Davao Region) | Davao del Sur | City of Digos | San Miguel | 6.7353 | 125.3437 | U | 17939 | 5276 | 1583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110525 | FTAP Globe | 6.7361 | 125.345 | 0.17 | Terrestrial Optical Fiber Drop | 2.3 | 1.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4483 | 5 | 483 | 4483 | 0403419002 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Biñan | 14.2671 | 121.4575 | U | 7053 | 2137 | 641 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040208 | FTAP Globe | 14.2666 | 121.4429 | 1.78 | Terrestrial Optical Fiber Drop | 1.06 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4484 | 5 | 484 | 4484 | 0500506012 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 16 - Kawit-East Washington Drive | 13.1405 | 123.7362 | U | 5355 | 1306 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050182 | FTAP Globe | 13.1312 | 123.7542 | 0.74 | Terrestrial Optical Fiber Drop | 0.4 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4485 | 5 | 485 | 4485 | 0304902022 | Region III (Central Luzon) | Nueva Ecija | Bongabon | San Roque | 15.6385 | 121.1759 | R | 3022 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02493 | Edgepoint | 15.6344 | 121.1471 | 1.84 | Terrestrial Optical Fiber Drop | 3.53 | 3.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4486 | 5 | 486 | 4486 | 0401031043 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Santor | 14.0943 | 121.1148 | U | 5239 | 1455 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040327 | FTAP Globe | 14.0929 | 121.1101 | 0.53 | Terrestrial Optical Fiber Drop | 1.72 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4487 | 5 | 487 | 4487 | 0105533013 | Region I (Ilocos Region) | Pangasinan | San Fabian | Lekep-Butao | 16.1031 | 120.4106 | R | 2783 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-02184 | Edgepoint | 16.0971 | 120.3938 | 1.92 | Terrestrial Optical Fiber Drop | 1.88 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4488 | 5 | 488 | 4488 | 0402106074 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Miguel II | 14.3385 | 120.9496 | R | 2392 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 5796 | FTAP Smart | 14.3408 | 120.95 | 0.27 | Terrestrial Optical Fiber Drop | 1.72 | 4.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4489 | 5 | 489 | 4489 | 1630400019 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Basag | 8.9331 | 125.6147 | R | 4128 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0009 | PTCI/MIDC | 8.9384 | 125.5902 | 2.76 | Terrestrial Optical Fiber Drop | 3.42 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4490 | 5 | 490 | 4490 | 1108211003 | Region XI (Davao Region) | Davao de Oro | Pantukan | P. Fuentes | 7.0975 | 125.9514 | R | 3991 | 1078 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTDLG0038 | PTCI/MIDC | 7.0669 | 125.9606 | 3.55 | Terrestrial Optical Fiber Drop | 7.07 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4491 | 5 | 491 | 4491 | 0402108032 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Buenavista II | 14.305 | 120.8977 | U | 11946 | 3513 | 1054 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02155-C08 | PTCI/MIDC | 14.3077 | 120.9029 | 0.64 | Terrestrial Optical Fiber Drop | 1.79 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4492 | 5 | 492 | 4492 | 0403429022 | Region IV-A (CALABARZON) | Laguna | Siniloan | Wawa | 14.4155 | 121.4466 | R | 3321 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02085-C08 | PTCI/MIDC | 14.415 | 121.4491 | 0.28 | Terrestrial Optical Fiber Drop | 2.04 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4493 | 5 | 493 | 4493 | 0603019022 | Region VI (Western Visayas) | Iloilo | Estancia | Tacbuyan | 11.4658 | 123.1402 | R | 4571 | 1202 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILI-03162 | Edgepoint | 11.4681 | 123.1473 | 0.82 | Terrestrial Optical Fiber Drop | 1.72 | 3.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4494 | 5 | 494 | 4494 | 1204707029 | Region XII (SOCCSKSARGEN) | Cotabato | Makilala | Poblacion | 6.9668 | 125.1019 | U | 8899 | 2341 | 702 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNCG0022 | PTCI/MIDC | 6.9508 | 125.0986 | 1.82 | Terrestrial Optical Fiber Drop | 1.72 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4495 | 5 | 495 | 4495 | 0305416004 | Region III (Central Luzon) | Pampanga | City of San Fernando | Calulut | 15.0907 | 120.6506 | U | 45123 | 11280 | 3384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Y15 | FTAP Smart | 15.0922 | 120.6555 | 0.55 | Terrestrial Optical Fiber Drop | 1.85 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4496 | 5 | 496 | 4496 | 0403425001 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Bagong Silang | 14.3355 | 121.0241 | U | 6288 | 1905 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.57 | Terrestrial Optical Fiber Drop | 2 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4497 | 5 | 497 | 4497 | 0105524015 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Barang | 15.9356 | 120.4177 | R | 2722 | 756 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00528 | Edgepoint | 15.9293 | 120.4132 | 0.85 | Terrestrial Optical Fiber Drop | 1.77 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4498 | 5 | 498 | 4498 | 0401019046 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Tumalim | 14.0796 | 120.7237 | R | 4670 | 1297 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040339 | FTAP Globe | 14.0802 | 120.7249 | 0.15 | Terrestrial Optical Fiber Drop | 3.03 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4499 | 5 | 499 | 4499 | 0402107003 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Castaños Cerca | 14.1818 | 120.7992 | U | 3143 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 1.68 | Terrestrial Optical Fiber Drop | 0.37 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4500 | 5 | 500 | 4500 | 1401111012 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Tabio | 16.8576 | 120.8139 | R | 3663 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 2.17 | Terrestrial Optical Fiber Drop | 2.07 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4501 | 5 | 501 | 4501 | 0301420032 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc Central | 14.8223 | 121.0578 | R | 4310 | 1231 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01169 | Edgepoint | 14.815 | 121.0394 | 0.23 | Terrestrial Optical Fiber Drop | 1.7 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4502 | 5 | 502 | 4502 | 0301410006 | Region III (Central Luzon) | Bulacan | City of Malolos | Balayong | 14.8288 | 120.8299 | R | 3710 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00946-B07 | PTCI/MIDC | 14.8339 | 120.8349 | 0.78 | Terrestrial Optical Fiber Drop | 1.73 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4503 | 5 | 503 | 4503 | 0105535005 | Region I (Ilocos Region) | Pangasinan | San Manuel | Flores | 16.0652 | 120.6865 | U | 5974 | 1659 | 498 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02535-B07 | PTCI/MIDC | 16.0667 | 120.6911 | 0.52 | Terrestrial Optical Fiber Drop | 1.9 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4504 | 5 | 504 | 4504 | 0401001022 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Subic Ilaya | 13.9511 | 120.9417 | R | 3767 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01957-C08 | PTCI/MIDC | 13.9528 | 120.9371 | 0.54 | Terrestrial Optical Fiber Drop | 1.74 | 6.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4505 | 5 | 505 | 4505 | 1705209010 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Lumambayan | 13.049 | 121.4991 | R | 2738 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170098 | FTAP Globe | 13.0172 | 121.4471 | 2.11 | Terrestrial Optical Fiber Drop | 1.89 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4506 | 5 | 506 | 4506 | 0402103048 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino V | 14.4225 | 120.9758 | U | 6908 | 2031 | 609 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040092 | FTAP Globe | 14.4604 | 120.9401 | 1.06 | Terrestrial Optical Fiber Drop | 1.09 | 3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4507 | 5 | 507 | 4507 | 1600209007 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Culit | 8.9594 | 125.3544 | R | 3576 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130075 | FTAP Globe | 8.9473 | 125.3554 | 1.35 | Terrestrial Optical Fiber Drop | 2.06 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4508 | 5 | 508 | 4508 | 0631000019 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Bito-on | 10.75 | 122.5899 | U | 6985 | 1663 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060263 | FTAP Globe | 10.7551 | 122.5845 | 0.81 | Terrestrial Optical Fiber Drop | 2.57 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4509 | 5 | 509 | 4509 | 0501603013 | Region V (Bicol Region) | Camarines Norte | Daet | Gahonon | 14.1302 | 122.955 | R | 3490 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0003 | PTCI/MIDC | 14.1236 | 122.9559 | 0.74 | Terrestrial Optical Fiber Drop | 1.75 | 2.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4510 | 5 | 510 | 4510 | 0630200032 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 35 | 10.6627 | 122.9541 | U | 8778 | 2438 | 731 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOR0008 | PTCI/MIDC | 10.6251 | 122.9644 | 0.97 | Terrestrial Optical Fiber Drop | 0.5 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4511 | 5 | 511 | 4511 | 0402108033 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Buenavista III | 14.3076 | 120.9017 | U | 9621 | 2829 | 849 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02155-C08 | PTCI/MIDC | 14.3077 | 120.9029 | 0.13 | Terrestrial Optical Fiber Drop | 1.74 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4512 | 5 | 512 | 4512 | 0105503009 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Bued | 16.1599 | 119.9989 | R | 3741 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010123 | FTAP Globe | 16.1602 | 120.0024 | 0.38 | Terrestrial Optical Fiber Drop | 1.81 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4513 | 5 | 513 | 4513 | 0403405009 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Burol | 14.1606 | 121.0995 | U | 3892 | 1179 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040284 | FTAP Globe | 14.1558 | 121.1075 | 1.01 | Terrestrial Optical Fiber Drop | 1.85 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4514 | 5 | 514 | 4514 | 0105545001 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Angatel | 15.8118 | 120.3417 | R | 3176 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00567 | Edgepoint | 15.8227 | 120.332 | 1.59 | Terrestrial Optical Fiber Drop | 1.75 | 11.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4515 | 5 | 515 | 4515 | 0201528022 | Region II (Cagayan Valley) | Cagayan | Tuao | Mungo | 17.7197 | 121.4675 | R | 5134 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAG-02384 | Edgepoint | 17.7363 | 121.4569 | 2.16 | Terrestrial Optical Fiber Drop | 1.75 | 3.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4516 | 5 | 516 | 4516 | 0600411008 | Region VI (Western Visayas) | Aklan | Makato | Calangcang | 11.7012 | 122.2991 | R | 2213 | 567 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 1.71 | Terrestrial Optical Fiber Drop | 1.75 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4517 | 5 | 517 | 4517 | 0201527015 | Region II (Cagayan Valley) | Cagayan | Solana | Lanna | 17.6943 | 121.703 | R | 4471 | 1146 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01164-B06 | PTCI/MIDC | 17.6966 | 121.7005 | 0.37 | Terrestrial Optical Fiber Drop | 1.75 | 4.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4518 | 5 | 518 | 4518 | 0403405031 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Maunong | 14.1691 | 121.1539 | R | 4818 | 1460 | 438 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040267 | FTAP Globe | 14.1824 | 121.1578 | 1.53 | Terrestrial Optical Fiber Drop | 3.24 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4519 | 5 | 519 | 4519 | 0401014029 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Malitlit | 13.9199 | 121.2406 | R | 2601 | 722 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040486 | FTAP Globe | 13.9189 | 121.2314 | 1 | Terrestrial Optical Fiber Drop | 1.75 | 3.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4520 | 5 | 520 | 4520 | 0604526013 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Lantad | 10.8159 | 122.963 | U | 10298 | 2783 | 835 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060333 | FTAP Globe | 10.8273 | 122.9543 | 1.6 | Terrestrial Optical Fiber Drop | 2.07 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4521 | 5 | 521 | 4521 | 0500508036 | Region V (Bicol Region) | Albay | City of Ligao | Pandan | 13.2241 | 123.5312 | U | 5107 | 1245 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050161 | FTAP Globe | 13.2193 | 123.5292 | 0.57 | Terrestrial Optical Fiber Drop | 1.76 | 1.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4522 | 5 | 522 | 4522 | 0402117003 | Region IV-A (CALABARZON) | Cavite | Rosario | Kanluran | 14.4197 | 120.862 | R | 3968 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0009 | LDIC | 14.42 | 120.8639 | 0.67 | Terrestrial Optical Fiber Drop | 2.39 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4523 | 5 | 523 | 4523 | 0402117007 | Region IV-A (CALABARZON) | Cavite | Rosario | Muzon I | 14.4196 | 120.8621 | R | 4091 | 1203 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0009 | LDIC | 14.42 | 120.8639 | 0.33 | Terrestrial Optical Fiber Drop | 2.38 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4524 | 5 | 524 | 4524 | 0401022005 | Region IV-A (CALABARZON) | Batangas | San Jose | Balagtasin | 13.902 | 121.0883 | R | 3796 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1351 | FTAP Smart | 13.8931 | 121.0981 | 1.44 | Terrestrial Optical Fiber Drop | 3.11 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4525 | 5 | 525 | 4525 | 1230800027 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Tambler | 6.0556 | 125.1425 | U | 32658 | 8373 | 2512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCG0006 | PTCI/MIDC | 6.0556 | 125.1359 | 0.73 | Terrestrial Optical Fiber Drop | 1.76 | 7.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4526 | 5 | 526 | 4526 | 0103314015 | Region I (Ilocos Region) | La Union | City of San Fernando | Cabaroan | 16.6148 | 120.3358 | R | 3672 | 992 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02862-B05 | PTCI/MIDC | 16.5908 | 120.3355 | 0.33 | Terrestrial Optical Fiber Drop | 2.3 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4527 | 5 | 527 | 4527 | 0402109065 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-D | 14.4053 | 120.9262 | R | 4043 | 1189 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02382-C08 | PTCI/MIDC | 14.3772 | 120.882 | 0.6 | Terrestrial Optical Fiber Drop | 1.57 | 4.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4528 | 5 | 528 | 4528 | 0301412002 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bahay Pare | 14.7672 | 121.0105 | U | 13831 | 3951 | 1185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01211 | Edgepoint | 14.7663 | 121.0114 | 0.14 | Terrestrial Optical Fiber Drop | 1.8 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4529 | 5 | 529 | 4529 | 0105513032 | Region I (Ilocos Region) | Pangasinan | Binmaley | Santa Rosa | 15.9987 | 120.3135 | R | 3725 | 1034 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010161 | FTAP Globe | 16.014 | 120.313 | 1.7 | Terrestrial Optical Fiber Drop | 3.05 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4530 | 5 | 530 | 4530 | 0401005117 | Region IV-A (CALABARZON) | Batangas | Batangas City | Wawa | 13.7411 | 121.0532 | U | 8860 | 2461 | 738 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040589 | FTAP Globe | 13.7414 | 121.0546 | 0.16 | Terrestrial Optical Fiber Drop | 2.39 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4531 | 5 | 531 | 4531 | 0403424069 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Felomina | 14.0895 | 121.2877 | R | 3910 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040335 | FTAP Globe | 14.0853 | 121.2819 | 0.78 | Terrestrial Optical Fiber Drop | 3.24 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4532 | 5 | 532 | 4532 | 0401014063 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Salvador | 13.9692 | 121.1258 | R | 4514 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S6824 | FTAP Smart | 13.9603 | 121.1327 | 1.24 | Terrestrial Optical Fiber Drop | 1.77 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4533 | 5 | 533 | 4533 | 0604531028 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay XXI | 10.9008 | 123.0778 | R | 5181 | 1400 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0078 | PTCI/MIDC | 10.8984 | 123.08 | 1.51 | Terrestrial Optical Fiber Drop | 0.52 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4534 | 5 | 534 | 4534 | 0501603005 | Region V (Bicol Region) | Camarines Norte | Daet | Borabod | 14.1266 | 122.9644 | R | 4076 | 1019 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050020 | FTAP Globe | 14.1316 | 122.9683 | 0.69 | Terrestrial Optical Fiber Drop | 1.77 | 2.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4535 | 5 | 535 | 4535 | 0304919008 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Marcos Village | 15.4438 | 121.1234 | U | 2989 | 854 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNEG0001 | PTCI/MIDC | 15.4474 | 121.1139 | 1.1 | Terrestrial Optical Fiber Drop | 1.77 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4536 | 5 | 536 | 4536 | 0931700037 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Lanzones | 6.9862 | 122.1304 | R | 3846 | 1068 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH090074 | FTAP BTS | 6.9845 | 122.1403 | 1.11 | Terrestrial Optical Fiber Drop | 10.5 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4537 | 5 | 537 | 4537 | 0402112002 | Region IV-A (CALABARZON) | Cavite | Magallanes | Bendita I | 14.161 | 120.752 | R | 2104 | 618 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040282 | FTAP Globe | 14.1583 | 120.7606 | 0.98 | Terrestrial Optical Fiber Drop | 1.79 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4538 | 5 | 538 | 4538 | 1001321025 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | San Carlos | 7.9093 | 125.0944 | R | 5458 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100202 | FTAP Globe | 7.9439 | 125.1039 | 2.24 | Terrestrial Optical Fiber Drop | 0.46 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4539 | 5 | 539 | 4539 | 0403404004 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Butong | 14.2901 | 121.1371 | U | 16184 | 4904 | 1471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0006 | PTCI/MIDC | 14.2878 | 121.1396 | 0.37 | Terrestrial Optical Fiber Drop | 1.77 | 2.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4540 | 5 | 540 | 4540 | 1204704027 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Nuangan | 7.0076 | 125.1071 | U | 4338 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120145 | FTAP BTS | 7.0111 | 125.1061 | 0.4 | Terrestrial Optical Fiber Drop | 2.12 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4541 | 5 | 541 | 4541 | 0105526008 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Buenlag | 16.0501 | 120.413 | U | 4522 | 1256 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00431 | Edgepoint | 16.0471 | 120.4124 | 0.34 | Terrestrial Optical Fiber Drop | 2.27 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4542 | 5 | 542 | 4542 | 0402123002 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 1 Poblacion | 14.2974 | 121.0078 | U | 6913 | 2033 | 610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040189 | FTAP Globe | 14.2936 | 121.0062 | 0.46 | Terrestrial Optical Fiber Drop | 1.78 | 4.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4543 | 5 | 543 | 4543 | 0301421036 | Region III (Central Luzon) | Bulacan | San Miguel | Pinambaran | 15.2016 | 120.9786 | R | 4780 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01047-B07 | PTCI/MIDC | 15.1819 | 120.9951 | 2.82 | Terrestrial Optical Fiber Drop | 1.77 | 2.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4544 | 5 | 544 | 4544 | 0402123011 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Francisco Reyes | 14.3038 | 121.0076 | U | 8348 | 2455 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03416-C08 | PTCI/MIDC | 14.3098 | 121.0205 | 0.93 | Terrestrial Optical Fiber Drop | 2.45 | 4.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4545 | 5 | 545 | 4545 | 0701219002 | Region VII (Central Visayas) | Bohol | Dauis | Bingag | 9.6206 | 123.8047 | U | 5174 | 1293 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070178 | FTAP BTS | 9.6229 | 123.8027 | 0.33 | Terrestrial Optical Fiber Drop | 1.78 | 5.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4546 | 5 | 546 | 4546 | 0401014032 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Munting Pulo | 13.9509 | 121.1822 | R | 4997 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2719 | FTAP Smart | 13.9562 | 121.1794 | 0.67 | Terrestrial Optical Fiber Drop | 1.85 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4547 | 5 | 547 | 4547 | 0201529001 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Annafunan East | 17.6433 | 121.7205 | R | 5084 | 1303 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00080 | Edgepoint | 17.6455 | 121.7219 | 0.29 | Terrestrial Optical Fiber Drop | 2.97 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4548 | 5 | 548 | 4548 | 0403405017 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Laguerta | 14.1738 | 121.09 | U | 5986 | 1813 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040278 | FTAP Globe | 14.1659 | 121.0917 | 0.9 | Terrestrial Optical Fiber Drop | 2.06 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4549 | 5 | 549 | 4549 | 0307105017 | Region III (Central Luzon) | Zambales | Iba | Santa Barbara | 15.3319 | 119.9991 | R | 4746 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0010 | PTCI/MIDC | 15.3325 | 120.0001 | 0.12 | Terrestrial Optical Fiber Drop | 2.35 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4550 | 5 | 550 | 4550 | 0702203008 | Region VII (Central Visayas) | Cebu | Alegria | Santa Filomena | 9.7415 | 123.3584 | R | 3564 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0246 | PTCI/MIDC | 9.7724 | 123.3473 | 3.64 | Terrestrial Optical Fiber Drop | 16.65 | 1.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4551 | 5 | 551 | 4551 | 0501728016 | Region V (Bicol Region) | Camarines Sur | Pili | Sagrada | 13.5615 | 123.3002 | R | 3286 | 782 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050101 | FTAP Globe | 13.5742 | 123.3003 | 1.41 | Terrestrial Optical Fiber Drop | 1.96 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4552 | 5 | 552 | 4552 | 0304920013 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Poblacion West | 15.8231 | 121.1396 | R | 2861 | 817 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01421-B07 | PTCI/MIDC | 15.8043 | 121.149 | 2.32 | Terrestrial Optical Fiber Drop | 1.79 | 11.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4553 | 5 | 553 | 4553 | 0402109064 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-C | 14.3887 | 120.9283 | U | 6653 | 1956 | 587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02560-C08 | PTCI/MIDC | 14.3963 | 120.9952 | 0.25 | Terrestrial Optical Fiber Drop | 1.33 | 5.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4554 | 5 | 554 | 4554 | 0203113012 | Region II (Cagayan Valley) | Isabela | Gamu | Mabini | 17.0966 | 121.7365 | R | 4693 | 1235 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01333-B06 | PTCI/MIDC | 17.0994 | 121.7392 | 0.43 | Terrestrial Optical Fiber Drop | 3.38 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4555 | 5 | 555 | 4555 | 0301407028 | Region III (Central Luzon) | Bulacan | Calumpit | Sapang Bayan | 14.8976 | 120.7642 | R | 3282 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3210 | FTAP Smart | 14.8903 | 120.762 | 0.37 | Terrestrial Optical Fiber Drop | 1.04 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4556 | 5 | 556 | 4556 | 0306916028 | Region III (Central Luzon) | Tarlac | City of Tarlac | Culipat | 15.4991 | 120.6172 | R | 2883 | 739 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030083 | FTAP BTS | 15.4951 | 120.6282 | 1.26 | Terrestrial Optical Fiber Drop | 2.09 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4557 | 5 | 557 | 4557 | 0403424062 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Pedro | 14.0974 | 121.3312 | R | 3420 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02091-C08 | PTCI/MIDC | 14.0991 | 121.3316 | 0.19 | Terrestrial Optical Fiber Drop | 2.42 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4558 | 5 | 558 | 4558 | 0105503017 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Magsaysay | 16.1727 | 119.9844 | R | 4016 | 1115 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01703-B07 | PTCI/MIDC | 16.1706 | 119.9873 | 0.38 | Terrestrial Optical Fiber Drop | 2.37 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4559 | 5 | 559 | 4559 | 0304919020 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Santolan | 15.5397 | 121.1169 | R | 2176 | 621 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-NUE-02328 | Edgepoint | 15.5029 | 121.0799 | 3.76 | Terrestrial Optical Fiber Drop | 3.03 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4560 | 5 | 560 | 4560 | 0401023013 | Region IV-A (CALABARZON) | Batangas | San Juan | Escribano | 13.813 | 121.3646 | R | 3823 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040553 | FTAP Globe | 13.828 | 121.3363 | 3.49 | Terrestrial Optical Fiber Drop | 3.58 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4561 | 5 | 561 | 4561 | 0306905026 | Region III (Central Luzon) | Tarlac | Concepcion | Pitabunan | 15.3417 | 120.654 | R | 3513 | 900 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030411 | FTAP Globe | 15.3515 | 120.6477 | 1.28 | Terrestrial Optical Fiber Drop | 1.9 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4562 | 5 | 562 | 4562 | 0301403028 | Region III (Central Luzon) | Bulacan | Baliuag | Tilapayong | 14.9795 | 120.8766 | R | 3160 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030513 | FTAP Globe | 14.9814 | 120.8821 | 0.63 | Terrestrial Optical Fiber Drop | 3.71 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4563 | 5 | 563 | 4563 | 0431200027 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Crossing | 13.9191 | 121.6214 | U | 17192 | 4298 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1429 | FTAP Smart | 13.9146 | 121.6178 | 0.63 | Terrestrial Optical Fiber Drop | 1.9 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4564 | 5 | 564 | 4564 | 1004311008 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Luz Banzon | 8.6573 | 124.7534 | U | 3798 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.36 | Terrestrial Optical Fiber Drop | 0.84 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4565 | 5 | 565 | 4565 | 0702243021 | Region VII (Central Visayas) | Cebu | San Remigio | Punta | 11.0985 | 123.9353 | R | 3346 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070302 | FTAP Globe | 11.08 | 123.9405 | 2.14 | Terrestrial Optical Fiber Drop | 1.79 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4566 | 5 | 566 | 4566 | 0301420048 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Martin IV | 14.8599 | 121.0543 | R | 4270 | 1220 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02326-B07 | PTCI/MIDC | 14.8304 | 121.0291 | 0.31 | Terrestrial Optical Fiber Drop | 2.72 | 5.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4567 | 5 | 567 | 4567 | 0730600078 | Region VII (Central Visayas) | Cebu | City of Cebu | T. Padilla | 10.3213 | 123.8847 | U | 6727 | 2102 | 631 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0053 | PTCI/MIDC | 10.3434 | 123.9117 | 0.49 | Terrestrial Optical Fiber Drop | 1.69 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4568 | 5 | 568 | 4568 | 0301420005 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Kaybanban | 14.8104 | 121.0878 | R | 3392 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030601 | FTAP Globe | 14.8086 | 121.0898 | 0.28 | Terrestrial Optical Fiber Drop | 1.8 | 2.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4569 | 5 | 569 | 4569 | 1102404008 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Hagonoy Crossing | 6.6854 | 125.313 | R | 3577 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0109 | PTCI/MIDC | 6.6757 | 125.3226 | 1.51 | Terrestrial Optical Fiber Drop | 1.8 | 4.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4570 | 5 | 570 | 4570 | 0402106078 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Niño II | 14.3178 | 120.952 | R | 2881 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02020-C08 | PTCI/MIDC | 14.3403 | 121.0215 | 0.15 | Terrestrial Optical Fiber Drop | 1.59 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4571 | 5 | 571 | 4571 | 0301414004 | Region III (Central Luzon) | Bulacan | Obando | Lawa | 14.7236 | 120.9283 | U | 9287 | 2653 | 796 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1172 | FTAP Smart | 14.7213 | 120.9293 | 0.27 | Terrestrial Optical Fiber Drop | 1.81 | 3.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4572 | 5 | 572 | 4572 | 0205013005 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Curifang | 16.5149 | 121.2199 | R | 5411 | 1423 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020115 | FTAP Globe | 16.5139 | 121.218 | 0.23 | Terrestrial Optical Fiber Drop | 3.77 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4573 | 5 | 573 | 4573 | 0731100003 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Bankal | 10.3065 | 123.989 | U | 22873 | 6535 | 1961 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0187 | PTCI/MIDC | 10.3058 | 123.9935 | 0.51 | Terrestrial Optical Fiber Drop | 1.81 | 5.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4574 | 5 | 574 | 4574 | 0405807014 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Sipsipin | 14.3719 | 121.3321 | U | 5301 | 1472 | 442 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040140 | FTAP Globe | 14.3709 | 121.3275 | 0.5 | Terrestrial Optical Fiber Drop | 1.82 | 9.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4575 | 5 | 575 | 4575 | 0500507023 | Region V (Bicol Region) | Albay | Libon | Macabugos | 13.2271 | 123.3118 | R | 2825 | 689 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050168 | FTAP Globe | 13.1892 | 123.3257 | 4.47 | Terrestrial Optical Fiber Drop | 1.81 | 15.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4576 | 5 | 576 | 4576 | 0103315019 | Region I (Ilocos Region) | La Union | San Gabriel | Poblacion | 16.6743 | 120.4117 | R | 2834 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010080 | FTAP Globe | 16.6791 | 120.4005 | 1.3 | Terrestrial Optical Fiber Drop | 1.81 | 7.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4577 | 5 | 577 | 4577 | 0300803014 | Region III (Central Luzon) | Bataan | City of Balanga | Pto. Rivas Ibaba | 14.6959 | 120.5597 | U | 4478 | 1243 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BAN-01375 | Edgepoint | 14.6877 | 120.5554 | 1.03 | Terrestrial Optical Fiber Drop | 2.06 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4578 | 5 | 578 | 4578 | 0307701009 | Region III (Central Luzon) | Aurora | Baler | Pingit | 15.7415 | 121.5565 | U | 4858 | 1278 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02611-B06 | PTCI/MIDC | 15.7449 | 121.5571 | 0.39 | Terrestrial Optical Fiber Drop | 2.26 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4579 | 5 | 579 | 4579 | 0402102024 | Region IV-A (CALABARZON) | Cavite | Amadeo | Talon | 14.1361 | 120.9401 | R | 3996 | 1175 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040296 | FTAP Globe | 14.1354 | 120.9321 | 0.87 | Terrestrial Optical Fiber Drop | 3.49 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4580 | 5 | 580 | 4580 | 0504111017 | Region V (Bicol Region) | Masbate | City of Masbate | Ibingay | 12.3725 | 123.6268 | U | 8138 | 1984 | 595 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMSG0002 | PTCI/MIDC | 12.3723 | 123.6242 | 0.28 | Terrestrial Optical Fiber Drop | 1.98 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4581 | 5 | 581 | 4581 | 0402106071 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz II | 14.3184 | 120.9525 | R | 4500 | 1323 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAV-03176 | Edgepoint | 14.3575 | 120.9237 | 0.22 | Terrestrial Optical Fiber Drop | 1.57 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4582 | 5 | 582 | 4582 | 0501715006 | Region V (Bicol Region) | Camarines Sur | Goa | Buyo | 13.6792 | 123.4742 | R | 4430 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050064 | FTAP Globe | 13.6982 | 123.4789 | 2.17 | Terrestrial Optical Fiber Drop | 2.34 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4583 | 5 | 583 | 4583 | 0301421049 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Rita Bata | 15.1663 | 120.9946 | U | 4002 | 1143 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030138 | FTAP BTS | 15.1692 | 120.9891 | 0.71 | Terrestrial Optical Fiber Drop | 2.35 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4584 | 5 | 584 | 4584 | 0305417010 | Region III (Central Luzon) | Pampanga | San Luis | Santa Catalina | 15.0583 | 120.7981 | R | 3662 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00906 | Edgepoint | 15.0551 | 120.7977 | 0.35 | Terrestrial Optical Fiber Drop | 2.35 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4585 | 5 | 585 | 4585 | 0501612006 | Region V (Bicol Region) | Camarines Norte | Vinzons | Calangcawan Sur | 14.1691 | 122.9235 | U | 5220 | 1305 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050015 | FTAP Globe | 14.1707 | 122.912 | 1.25 | Terrestrial Optical Fiber Drop | 1.82 | 2.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4586 | 5 | 586 | 4586 | 0105543004 | Region I (Ilocos Region) | Pangasinan | Tayug | Carriedo | 16.0338 | 120.7625 | R | 2730 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01767-B07 | PTCI/MIDC | 16.0297 | 120.7499 | 1.43 | Terrestrial Optical Fiber Drop | 1.99 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4587 | 5 | 587 | 4587 | 1206511003 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Calean | 6.667 | 124.6696 | R | 3112 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120131 | FTAP BTS | 6.6753 | 124.6699 | 0.92 | Terrestrial Optical Fiber Drop | 2.55 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4588 | 5 | 588 | 4588 | 0305409002 | Region III (Central Luzon) | Pampanga | Mabalacat City | Bical | 15.1944 | 120.619 | R | 5078 | 1269 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-03226 | Edgepoint | 15.8126 | 120.4437 | 0.6 | Terrestrial Optical Fiber Drop | 2.66 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4589 | 5 | 589 | 4589 | 0403424048 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Gabriel | 14.0515 | 121.3114 | U | 9728 | 2947 | 884 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02075-C08 | PTCI/MIDC | 14.0549 | 121.3128 | 0.41 | Terrestrial Optical Fiber Drop | 2.14 | 1.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4590 | 5 | 590 | 4590 | 0402106035 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Mateo | 14.3197 | 120.9563 | R | 5211 | 1532 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0013 | PTCI/MIDC | 14.3393 | 120.9399 | 0.58 | Terrestrial Optical Fiber Drop | 1.3 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4591 | 5 | 591 | 4591 | 0401017016 | Region IV-A (CALABARZON) | Batangas | Malvar | San Juan | 14.0218 | 121.1448 | R | 3156 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S2737 | FTAP Smart | 14.0199 | 121.147 | 0.32 | Terrestrial Optical Fiber Drop | 1.92 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4592 | 5 | 592 | 4592 | 1004303003 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Baukbauk Pob. | 9.0059 | 124.8526 | R | 2911 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 2.01 | Terrestrial Optical Fiber Drop | 1.1 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4593 | 5 | 593 | 4593 | 0103301010 | Region I (Ilocos Region) | La Union | Agoo | San Agustin East | 16.3334 | 120.3718 | R | 2487 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01258-B05 | PTCI/MIDC | 17.0607 | 120.4841 | 1.34 | Terrestrial Optical Fiber Drop | 1.15 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4594 | 5 | 594 | 4594 | 0105511016 | Region I (Ilocos Region) | Pangasinan | Bayambang | Bical Norte | 15.8134 | 120.4381 | R | 3690 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-03226 | Edgepoint | 15.8126 | 120.4437 | 0.6 | Terrestrial Optical Fiber Drop | 1.83 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4595 | 5 | 595 | 4595 | 0702223011 | Region VII (Central Visayas) | Cebu | Danao City | Cogon-Cruz | 10.5149 | 124.008 | U | 5232 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0080 | PTCI/MIDC | 10.5228 | 124.0089 | 0.88 | Terrestrial Optical Fiber Drop | 2.15 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4596 | 5 | 596 | 4596 | 0301420051 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael IV | 14.8536 | 121.0459 | U | 6739 | 1925 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01107 | Edgepoint | 14.8568 | 121.0462 | 0.22 | Terrestrial Optical Fiber Drop | 1.59 | 5.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4597 | 5 | 597 | 4597 | 0631000115 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Navais | 10.7043 | 122.533 | R | 4686 | 1115 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0030 | PTCI/MIDC | 10.7126 | 122.5296 | 1 | Terrestrial Optical Fiber Drop | 1.84 | 3.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4598 | 5 | 598 | 4598 | 0301409023 | Region III (Central Luzon) | Bulacan | Hagonoy | Santo Niño | 14.8361 | 120.7347 | U | 4760 | 1360 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0059 | PTCI/MIDC | 14.8374 | 120.7372 | 0.31 | Terrestrial Optical Fiber Drop | 1.84 | 2.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4599 | 5 | 599 | 4599 | 0604530013 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Palaka | 10.4607 | 122.8247 | R | 3358 | 907 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060372 | FTAP Globe | 10.4155 | 122.8522 | 2.93 | Terrestrial Optical Fiber Drop | 0.61 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4600 | 5 | 600 | 4600 | 0403427007 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Cambuja | 14.4625 | 121.4023 | R | 2345 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040097 | FTAP Globe | 14.4463 | 121.3812 | 2.9 | Terrestrial Optical Fiber Drop | 2.13 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4601 | 5 | 601 | 4601 | 0201529046 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Linao Norte | 17.654 | 121.7256 | R | 3798 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1398 | FTAP Smart | 17.6552 | 121.7289 | 0.37 | Terrestrial Optical Fiber Drop | 2.31 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4602 | 5 | 602 | 4602 | 0402123015 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Inocencio Salud | 14.3044 | 121.0075 | R | 2702 | 794 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02625-C08 | PTCI/MIDC | 14.3212 | 120.9965 | 0.81 | Terrestrial Optical Fiber Drop | 2.51 | 4.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4603 | 5 | 603 | 4603 | 0301415013 | Region III (Central Luzon) | Bulacan | Pandi | Masagana | 14.8855 | 120.93 | R | 3071 | 877 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-02581 | Edgepoint | 14.8983 | 120.94 | 1.78 | Terrestrial Optical Fiber Drop | 2.65 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4604 | 5 | 604 | 4604 | 0401023022 | Region IV-A (CALABARZON) | Batangas | San Juan | Nagsaulay | 13.7112 | 121.4408 | R | 2882 | 800 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040597 | FTAP Globe | 13.7212 | 121.4269 | 1.86 | Terrestrial Optical Fiber Drop | 1.85 | 8.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4605 | 5 | 605 | 4605 | 0306916034 | Region III (Central Luzon) | Tarlac | City of Tarlac | Dela Paz | 15.4246 | 120.5815 | R | 3557 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00731 | Edgepoint | 15.4238 | 120.5807 | 0.13 | Terrestrial Optical Fiber Drop | 2.03 | 1.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4606 | 5 | 606 | 4606 | 0201529022 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Cataggaman Viejo | 17.5968 | 121.7072 | R | 4626 | 1186 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00103 | Edgepoint | 17.5984 | 121.7091 | 0.26 | Terrestrial Optical Fiber Drop | 4.04 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4607 | 5 | 607 | 4607 | 0504117025 | Region V (Bicol Region) | Masbate | Placer | Pasiagon | 11.8791 | 123.8956 | R | 3803 | 927 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03141-C10 | PTCI/MIDC | 11.8768 | 123.8915 | 0.51 | Satellite LEO Backhaul (Starlink Business) | 1.85 | 40.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4608 | 5 | 608 | 4608 | 0301411012 | Region III (Central Luzon) | Bulacan | Marilao | Prenza II | 14.7835 | 120.9832 | U | 14408 | 4116 | 1235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01197 | Edgepoint | 14.7777 | 120.9744 | 0.46 | Terrestrial Optical Fiber Drop | 2.49 | 2.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4609 | 5 | 609 | 4609 | 0803738069 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Matica-a | 11.135 | 124.5535 | R | 3876 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080148 | FTAP BTS | 11.1247 | 124.5606 | 1.38 | Terrestrial Optical Fiber Drop | 3.77 | 1.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4610 | 5 | 610 | 4610 | 0401021044 | Region IV-A (CALABARZON) | Batangas | Rosario | Santa Cruz | 13.8629 | 121.1893 | R | 3364 | 934 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040535 | FTAP Globe | 13.8642 | 121.1884 | 0.17 | Terrestrial Optical Fiber Drop | 2.43 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4611 | 5 | 611 | 4611 | 0603036009 | Region VI (Western Visayas) | Iloilo | Pavia | Cabugao Norte | 10.7914 | 122.5427 | R | 2842 | 747 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060039 | FTAP BTS | 10.7884 | 122.5371 | 0.7 | Terrestrial Optical Fiber Drop | 1.86 | 4.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4612 | 5 | 612 | 4612 | 0504101007 | Region V (Bicol Region) | Masbate | Aroroy | Bangon | 12.4997 | 123.3858 | R | 2921 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03102-C10 | PTCI/MIDC | 12.5006 | 123.3814 | 0.48 | Terrestrial Optical Fiber Drop | 1.85 | 5.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4613 | 5 | 613 | 4613 | 0304903100 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Santo Niño | 15.4469 | 120.9217 | R | 2121 | 606 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02326 | Edgepoint | 15.4456 | 120.9202 | 0.21 | Terrestrial Optical Fiber Drop | 1.86 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4614 | 5 | 614 | 4614 | 0704625006 | Region VII (Central Visayas) | Negros Oriental | Zamboanguita | Mayabon | 9.0971 | 123.1801 | U | 7926 | 2085 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070272 | FTAP Globe | 9.0939 | 123.1688 | 1.29 | Terrestrial Optical Fiber Drop | 1.85 | 16.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4615 | 5 | 615 | 4615 | 1102412019 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone II | 6.8521 | 125.3964 | U | 6310 | 1855 | 557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.63 | Terrestrial Optical Fiber Drop | 1.87 | 1.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4616 | 5 | 616 | 4616 | 0405627021 | Region IV-A (CALABARZON) | Quezon | Mauban | Sadsaran | 14.1887 | 121.7328 | R | 4090 | 1076 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02455-C08 | PTCI/MIDC | 14.1865 | 121.7262 | 0.75 | Terrestrial Optical Fiber Drop | 1.86 | 19.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4617 | 5 | 617 | 4617 | 0203114081 | Region II (Cagayan Valley) | Isabela | City of Ilagan | San Ignacio | 17.1995 | 121.8653 | R | 3365 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020058 | FTAP Globe | 17.2219 | 121.874 | 2.65 | Terrestrial Optical Fiber Drop | 3.02 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4618 | 5 | 618 | 4618 | 1003509012 | Region X (Northern Mindanao) | Lanao del Norte | Lala | Lala Proper | 7.955 | 123.7624 | R | 4543 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0041 | PTCI/MIDC | 7.9564 | 123.759 | 0.18 | Terrestrial Optical Fiber Drop | 10.58 | 1.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4619 | 5 | 619 | 4619 | 0304903048 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Macatbong | 15.5037 | 121.0784 | R | 3949 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02328 | Edgepoint | 15.5029 | 121.0799 | 0.18 | Terrestrial Optical Fiber Drop | 1.85 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4620 | 5 | 620 | 4620 | 0301406001 | Region III (Central Luzon) | Bulacan | Bustos | Bonga Mayor | 14.9543 | 120.9392 | U | 6788 | 1939 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00996 | Edgepoint | 14.9564 | 120.9432 | 0.49 | Terrestrial Optical Fiber Drop | 2.27 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4621 | 5 | 621 | 4621 | 0401011002 | Region IV-A (CALABARZON) | Batangas | Laurel | Balakilong | 14.0702 | 120.9335 | R | 4467 | 1240 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 1.57 | Terrestrial Optical Fiber Drop | 1.87 | 2.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4622 | 5 | 622 | 4622 | 1600303011 | Region XIII (Caraga) | Agusan del Sur | Esperanza | Guadalupe | 8.6022 | 125.7083 | R | 4117 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0003 | PTCI/MIDC | 8.7151 | 125.7419 | 6.87 | Terrestrial Optical Fiber Drop | 13.46 | 7.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4623 | 5 | 623 | 4623 | 0402110008 | Region IV-A (CALABARZON) | Cavite | Indang | Calumpang Cerca | 14.212 | 120.8656 | R | 3195 | 939 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02220-C08 | PTCI/MIDC | 14.2092 | 120.8664 | 0.32 | Terrestrial Optical Fiber Drop | 1.87 | 7.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4624 | 5 | 624 | 4624 | 0402106050 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado II | 14.3176 | 120.9526 | R | 2943 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040185 | FTAP Globe | 14.3044 | 120.993 | 0.85 | Terrestrial Optical Fiber Drop | 1.53 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4625 | 5 | 625 | 4625 | 0304930053 | Region III (Central Luzon) | Nueva Ecija | Talavera | Sibul | 15.6273 | 120.9593 | R | 3531 | 1008 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00825 | Edgepoint | 15.1665 | 121.0591 | 0.52 | Terrestrial Optical Fiber Drop | 6.62 | 3.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4626 | 5 | 626 | 4626 | 0105538024 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Sonquil | 15.9882 | 120.3902 | R | 3298 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00489 | Edgepoint | 15.9778 | 120.378 | 1.74 | Terrestrial Optical Fiber Drop | 2.94 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4627 | 5 | 627 | 4627 | 0304912008 | Region III (Central Luzon) | Nueva Ecija | Jaen | Magsalisi | 15.4 | 120.9245 | R | 4023 | 1149 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01490-B07 | PTCI/MIDC | 15.3847 | 120.9127 | 2.12 | Terrestrial Optical Fiber Drop | 2.84 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4628 | 5 | 628 | 4628 | 0501721014 | Region V (Bicol Region) | Camarines Sur | Milaor | San Antonio | 13.5981 | 123.2315 | R | 3932 | 936 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCSG0006 | PTCI/MIDC | 13.6014 | 123.2473 | 1.75 | Terrestrial Optical Fiber Drop | 2.19 | 1.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4629 | 5 | 629 | 4629 | 0403402009 | Region IV-A (CALABARZON) | Laguna | Bay | Puypuy | 14.1596 | 121.2738 | U | 4812 | 1458 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040289 | FTAP Globe | 14.1446 | 121.271 | 1.69 | Terrestrial Optical Fiber Drop | 2.06 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4630 | 5 | 630 | 4630 | 0401014003 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Anilao | 13.9016 | 121.1709 | R | 4411 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040495 | FTAP Globe | 13.9107 | 121.1854 | 1.86 | Terrestrial Optical Fiber Drop | 4.76 | 1.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4631 | 5 | 631 | 4631 | 0301406009 | Region III (Central Luzon) | Bulacan | Bustos | Malawak | 14.914 | 120.952 | R | 3084 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030544 | FTAP Globe | 14.9103 | 120.9489 | 0.53 | Terrestrial Optical Fiber Drop | 2.49 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4632 | 5 | 632 | 4632 | 0500506062 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 44 - Pawa | 13.177 | 123.7301 | R | 3996 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03401-C10 | PTCI/MIDC | 13.1742 | 123.7318 | 0.36 | Terrestrial Optical Fiber Drop | 3.87 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4633 | 5 | 633 | 4633 | 0506216058 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | San Roque | 13.0165 | 124.0333 | R | 3708 | 927 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 2.33 | Terrestrial Optical Fiber Drop | 1.89 | 4.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4634 | 5 | 634 | 4634 | 0304917004 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Bical | 15.7429 | 120.9011 | R | 3126 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1221 | FTAP Smart | 15.74 | 120.9022 | 0.34 | Terrestrial Optical Fiber Drop | 3.04 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4635 | 5 | 635 | 4635 | 0105546011 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Camanang | 15.9616 | 120.5923 | U | 5150 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00504 | Edgepoint | 15.9601 | 120.5887 | 0.42 | Terrestrial Optical Fiber Drop | 1.93 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4636 | 5 | 636 | 4636 | 1206317003 | Region XII (SOCCSKSARGEN) | South Cotabato | Tupi | Bunao | 6.32 | 124.9359 | U | 5805 | 1612 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH120121 | FTAP BTS | 6.3394 | 124.9432 | 2.3 | Terrestrial Optical Fiber Drop | 1.89 | 8.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4637 | 5 | 637 | 4637 | 0402115003 | Region IV-A (CALABARZON) | Cavite | Naic | Bancaan | 14.3185 | 120.7541 | R | 5091 | 1497 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040174 | FTAP Globe | 14.318 | 120.7546 | 0.08 | Terrestrial Optical Fiber Drop | 1.92 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4638 | 5 | 638 | 4638 | 0304926007 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Camanacsacan | 15.7683 | 120.9817 | R | 3147 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00575 | Edgepoint | 15.7836 | 120.9855 | 1.74 | Terrestrial Optical Fiber Drop | 2.99 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4639 | 5 | 639 | 4639 | 0304907016 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Tagumpay | 15.4837 | 121.3153 | R | 2801 | 800 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02887-B07 | PTCI/MIDC | 15.478 | 121.3066 | 1.13 | Terrestrial Optical Fiber Drop | 1.89 | 21.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4640 | 5 | 640 | 4640 | 0301421009 | Region III (Central Luzon) | Bulacan | San Miguel | Batasan Matanda | 15.1664 | 120.9951 | R | 3558 | 1016 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030138 | FTAP BTS | 15.1692 | 120.9891 | 0.5 | Terrestrial Optical Fiber Drop | 2.4 | 2.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4641 | 5 | 641 | 4641 | 0403426020 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Juan | 14.2439 | 121.4069 | R | 4354 | 1319 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02039-C08 | PTCI/MIDC | 14.2395 | 121.4046 | 0.54 | Terrestrial Optical Fiber Drop | 3.97 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4642 | 5 | 642 | 4642 | 0301421052 | Region III (Central Luzon) | Bulacan | San Miguel | Sibul | 15.1681 | 121.0638 | U | 11594 | 3312 | 994 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00825 | Edgepoint | 15.1665 | 121.0591 | 0.53 | Terrestrial Optical Fiber Drop | 1.9 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4643 | 5 | 643 | 4643 | 0401014036 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Pangao | 13.9151 | 121.1232 | U | 6763 | 1878 | 563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03439-C08 | PTCI/MIDC | 13.9136 | 121.1173 | 0.65 | Terrestrial Optical Fiber Drop | 2.41 | 1.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4644 | 5 | 644 | 4644 | 0631000030 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Calahunan | 10.7044 | 122.5621 | U | 5250 | 1250 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060273 | FTAP Globe | 10.688 | 122.5288 | 0.64 | Terrestrial Optical Fiber Drop | 1.22 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4645 | 5 | 645 | 4645 | 0631000072 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Ingore | 10.7128 | 122.5855 | U | 4395 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060269 | FTAP Globe | 10.7073 | 122.5897 | 0.76 | Terrestrial Optical Fiber Drop | 1.92 | 1.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4646 | 5 | 646 | 4646 | 1108203013 | Region XI (Davao Region) | Davao de Oro | Mabini | Cabuyuan | 7.3146 | 125.8755 | R | 2942 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110440 | FTAP Globe | 7.3117 | 125.8547 | 2.32 | Terrestrial Optical Fiber Drop | 2.29 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4647 | 5 | 647 | 4647 | 0401031015 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Cale | 14.1177 | 121.0941 | R | 4068 | 1130 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040310 | FTAP Globe | 14.1106 | 121.0931 | 0.8 | Terrestrial Optical Fiber Drop | 1.92 | 4.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4648 | 5 | 648 | 4648 | 0401031006 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Bagbag | 14.0347 | 121.0915 | R | 3763 | 1045 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03461-C08 | PTCI/MIDC | 14.0335 | 121.0877 | 0.43 | Terrestrial Optical Fiber Drop | 1.92 | 7.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4649 | 5 | 649 | 4649 | 0500504045 | Region V (Bicol Region) | Albay | Guinobatan | San Rafael | 13.184 | 123.5817 | U | 4426 | 1079 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0037 | PTCI/MIDC | 13.1678 | 123.6042 | 1.3 | Terrestrial Optical Fiber Drop | 2.45 | 1.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4650 | 5 | 650 | 4650 | 0601914019 | Region VI (Western Visayas) | Capiz | City of Roxas | Baybay | 11.6044 | 122.7381 | U | 10096 | 2656 | 797 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0015 | PTCI/MIDC | 11.6009 | 122.7423 | 0.6 | Terrestrial Optical Fiber Drop | 2.05 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4651 | 5 | 651 | 4651 | 1001321003 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Barobo | 7.9093 | 125.0937 | R | 4606 | 1212 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 0.7 | Terrestrial Optical Fiber Drop | 0.4 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4652 | 5 | 652 | 4652 | 0301420002 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Dulong Bayan | 14.8266 | 121.0449 | U | 11506 | 3287 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01163 | Edgepoint | 14.8231 | 121.049 | 0.59 | Terrestrial Optical Fiber Drop | 1.92 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4653 | 5 | 653 | 4653 | 0305415008 | Region III (Central Luzon) | Pampanga | Porac | Calzadang Bayu | 15.1026 | 120.5802 | U | 8254 | 2063 | 619 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1124 | FTAP Smart | 15.096 | 120.5914 | 1.41 | Terrestrial Optical Fiber Drop | 2.14 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4654 | 5 | 654 | 4654 | 0304912007 | Region III (Central Luzon) | Nueva Ecija | Jaen | Langla | 15.3264 | 120.9188 | R | 3586 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0197 | FTAP Smart | 15.3283 | 120.9203 | 0.27 | Terrestrial Optical Fiber Drop | 1.92 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4655 | 5 | 655 | 4655 | 0731100014 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Looc | 10.3042 | 123.9448 | U | 15417 | 4404 | 1321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0093 | PTCI/MIDC | 10.2975 | 123.9458 | 0.76 | Terrestrial Optical Fiber Drop | 1.92 | 3.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4656 | 5 | 656 | 4656 | 1001314001 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Agusan Canyon | 8.3405 | 124.8251 | U | 10332 | 2718 | 815 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0023 | PTCI/MIDC | 8.3522 | 124.8106 | 2.06 | Terrestrial Optical Fiber Drop | 1.93 | 4.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4657 | 5 | 657 | 4657 | 0402115008 | Region IV-A (CALABARZON) | Cavite | Naic | Palangue 2 & 3 | 14.262 | 120.8298 | R | 3895 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02160-C08 | PTCI/MIDC | 14.2703 | 120.8208 | 1.33 | Terrestrial Optical Fiber Drop | 1.92 | 2.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4658 | 5 | 658 | 4658 | 1130700035 | Region XI (Davao Region) | Davao del Sur | City of Davao | Communal | 7.1404 | 125.6244 | U | 17059 | 5017 | 1505 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0055 | PTCI/MIDC | 7.1389 | 125.6272 | 0.35 | Terrestrial Optical Fiber Drop | 2.27 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4659 | 5 | 659 | 4659 | 0402106031 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Juan | 14.3207 | 120.9564 | R | 3860 | 1135 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01860-C08 | PTCI/MIDC | 14.3014 | 120.9785 | 0.11 | Terrestrial Optical Fiber Drop | 1.36 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4660 | 5 | 660 | 4660 | 0402106032 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Lorenzo Ruiz I | 14.3198 | 120.957 | R | 3486 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0026 | PTCI/MIDC | 14.307 | 120.9364 | 0.47 | Terrestrial Optical Fiber Drop | 1.25 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4661 | 5 | 661 | 4661 | 1401106006 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Tinongdan | 16.3901 | 120.7298 | R | 3745 | 1070 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 3886 | FTAP Smart | 16.3763 | 120.7215 | 1.78 | Terrestrial Optical Fiber Drop | 1.94 | 3.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4662 | 5 | 662 | 4662 | 0305422012 | Region III (Central Luzon) | Pampanga | Sasmuan | Santo Tomas | 14.9474 | 120.6232 | R | 3424 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030524 | FTAP Globe | 14.9536 | 120.6316 | 1.13 | Terrestrial Optical Fiber Drop | 2.92 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4663 | 5 | 663 | 4663 | 0301423011 | Region III (Central Luzon) | Bulacan | Santa Maria | Mag-asawang Sapa | 14.8789 | 120.9827 | U | 10851 | 3100 | 930 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030566 | FTAP Globe | 14.8789 | 120.981 | 0.18 | Terrestrial Optical Fiber Drop | 1.94 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4664 | 5 | 664 | 4664 | 0102822009 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Juan | 18.1183 | 120.7443 | R | 2438 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01220-B05 | PTCI/MIDC | 18.0958 | 120.7728 | 2.17 | Terrestrial Optical Fiber Drop | 3.56 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4665 | 5 | 665 | 4665 | 0105525031 | Region I (Ilocos Region) | Pangasinan | Manaoag | Nalsian | 16.0338 | 120.4978 | R | 2803 | 778 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02431 | Edgepoint | 16.0356 | 120.4927 | 0.58 | Terrestrial Optical Fiber Drop | 1.94 | 6.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4666 | 5 | 666 | 4666 | 0205013020 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Bagahabag | 16.509 | 121.2082 | R | 4997 | 1315 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-00319 | Edgepoint | 16.5121 | 121.2119 | 0.53 | Terrestrial Optical Fiber Drop | 2.55 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4667 | 5 | 667 | 4667 | 0105532086 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Tarece | 15.9393 | 120.3622 | R | 4510 | 1252 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01723-B07 | PTCI/MIDC | 15.9337 | 120.3615 | 0.63 | Terrestrial Optical Fiber Drop | 1.95 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4668 | 5 | 668 | 4668 | 0501732002 | Region V (Bicol Region) | Camarines Sur | San Fernando | Beberon | 13.5439 | 123.1448 | R | 2937 | 699 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 1.8 | Terrestrial Optical Fiber Drop | 1.97 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4669 | 5 | 669 | 4669 | 0301404011 | Region III (Central Luzon) | Bulacan | Bocaue | Duhat | 14.7859 | 120.9534 | U | 9308 | 2659 | 798 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01192 | Edgepoint | 14.7848 | 120.9505 | 0.34 | Terrestrial Optical Fiber Drop | 2.05 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4670 | 5 | 670 | 4670 | 0402117017 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa III | 14.4159 | 120.8506 | R | 4448 | 1308 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4398 | FTAP Smart | 14.4244 | 120.8705 | 0.98 | Terrestrial Optical Fiber Drop | 2.32 | 2.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4671 | 5 | 671 | 4671 | 1102401019 | Region XI (Davao Region) | Davao del Sur | Bansalan | Rizal | 6.7837 | 125.1924 | R | 3781 | 1112 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0144 | PTCI/MIDC | 6.7938 | 125.2038 | 1.68 | Terrestrial Optical Fiber Drop | 1.95 | 18.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4672 | 5 | 672 | 4672 | 1102408019 | Region XI (Davao Region) | Davao del Sur | Malalag | Bagumbayan | 6.6027 | 125.3947 | R | 2884 | 848 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110532 | FTAP Globe | 6.5977 | 125.4013 | 0.92 | Terrestrial Optical Fiber Drop | 1.96 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4673 | 5 | 673 | 4673 | 0301420017 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | San Rafael II | 14.8537 | 121.0456 | U | 8507 | 2430 | 729 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01031-B07 | PTCI/MIDC | 14.8086 | 121.0527 | 0.61 | Terrestrial Optical Fiber Drop | 1.59 | 5.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4674 | 5 | 674 | 4674 | 0105526023 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Osiem | 16.0595 | 120.422 | R | 3375 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00423 | Edgepoint | 16.0623 | 120.4214 | 0.32 | Terrestrial Optical Fiber Drop | 2.3 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4675 | 5 | 675 | 4675 | 0803738073 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Naungan | 11.0125 | 124.5786 | R | 4038 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080194 | FTAP BTS | 11.0129 | 124.581 | 0.26 | Terrestrial Optical Fiber Drop | 2.43 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4676 | 5 | 676 | 4676 | 0301418018 | Region III (Central Luzon) | Bulacan | Pulilan | Paltao | 14.9044 | 120.8479 | U | 6749 | 1928 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030537 | FTAP Globe | 14.9216 | 120.8449 | 0.3 | Terrestrial Optical Fiber Drop | 0.37 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4677 | 5 | 677 | 4677 | 0803740038 | Region VIII (Eastern Visayas) | Leyte | Palompon | San Juan | 11.0675 | 124.3782 | R | 2950 | 776 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 8.58 | Terrestrial Optical Fiber Drop | 1.97 | 2.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4678 | 5 | 678 | 4678 | 0301421019 | Region III (Central Luzon) | Bulacan | San Miguel | Cambio | 15.166 | 120.9948 | R | 2324 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01047-B07 | PTCI/MIDC | 15.1819 | 120.9951 | 0.71 | Terrestrial Optical Fiber Drop | 2.35 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4679 | 5 | 679 | 4679 | 0501605001 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Bagong Bayan | 14.2971 | 122.6882 | R | 3091 | 772 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050004 | FTAP Globe | 14.2889 | 122.6958 | 1.23 | Terrestrial Optical Fiber Drop | 1.96 | 11.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4680 | 5 | 680 | 4680 | 0105502003 | Region I (Ilocos Region) | Pangasinan | Aguilar | Baybay | 15.9008 | 120.2294 | R | 3710 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00546 | Edgepoint | 15.8907 | 120.2394 | 1.55 | Terrestrial Optical Fiber Drop | 1.97 | 12.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4681 | 5 | 681 | 4681 | 0401011021 | Region IV-A (CALABARZON) | Batangas | Laurel | San Gabriel | 14.049 | 120.9161 | R | 2999 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 1.71 | Terrestrial Optical Fiber Drop | 1.96 | 4.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4682 | 5 | 682 | 4682 | 0702221009 | Region VII (Central Visayas) | Cebu | Daanbantayan | Lanao | 11.246 | 124.0277 | R | 4355 | 1146 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0071 | PTCI/MIDC | 11.2487 | 124.026 | 0.36 | Terrestrial Optical Fiber Drop | 2.44 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4683 | 5 | 683 | 4683 | 0401020022 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Payapa | 13.8627 | 121.2364 | R | 3604 | 1001 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040545 | FTAP Globe | 13.8444 | 121.2397 | 2.07 | Terrestrial Optical Fiber Drop | 3.05 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4684 | 5 | 684 | 4684 | 0701233008 | Region VII (Central Visayas) | Bohol | Panglao | Poblacion | 9.5807 | 123.753 | U | 6134 | 1533 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070426 | FTAP Globe | 9.5816 | 123.7493 | 0.41 | Terrestrial Optical Fiber Drop | 1.97 | 12.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4685 | 5 | 685 | 4685 | 0403412013 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Isidro | 14.1849 | 121.5153 | R | 3051 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 2.27 | Terrestrial Optical Fiber Drop | 1.01 | 4.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4686 | 5 | 686 | 4686 | 0203135023 | Region II (Cagayan Valley) | Isabela | City of Santiago | Patul | 16.6722 | 121.5326 | U | 6062 | 1595 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-03075 | Edgepoint | 121.5292 | 16.6699 | 0.44 | Terrestrial Optical Fiber Drop | 2.31 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4687 | 5 | 687 | 4687 | 0105505011 | Region I (Ilocos Region) | Pangasinan | Anda | Mal-ong | 16.3012 | 119.9349 | R | 3248 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00370 | Edgepoint | 16.2909 | 119.9464 | 1.68 | Terrestrial Optical Fiber Drop | 1.98 | 4.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4688 | 5 | 688 | 4688 | 0301419025 | Region III (Central Luzon) | Bulacan | San Ildefonso | Pinaod | 15.072 | 120.9628 | U | 8088 | 2310 | 693 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00993-B07 | PTCI/MIDC | 15.0713 | 120.9667 | 0.42 | Terrestrial Optical Fiber Drop | 2.14 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4689 | 5 | 689 | 4689 | 0201528005 | Region II (Cagayan Valley) | Cagayan | Tuao | Bagumbayan | 17.7064 | 121.4509 | R | 4599 | 1179 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0081 | LDIC | 121.4439 | 17.7081 | 0.77 | Terrestrial Optical Fiber Drop | 3.22 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4690 | 5 | 690 | 4690 | 0601914026 | Region VI (Western Visayas) | Capiz | City of Roxas | Dumolog | 11.6057 | 122.7568 | U | 4164 | 1095 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCZG0015 | PTCI/MIDC | 11.6009 | 122.7423 | 1.67 | Terrestrial Optical Fiber Drop | 2.09 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4691 | 5 | 691 | 4691 | 0305406018 | Region III (Central Luzon) | Pampanga | Floridablanca | Pabanlag | 14.9819 | 120.4843 | R | 3551 | 887 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00976 | Edgepoint | 14.9759 | 120.4805 | 0.79 | Terrestrial Optical Fiber Drop | 2.78 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4692 | 5 | 692 | 4692 | 0701219009 | Region VII (Central Visayas) | Bohol | Dauis | Tabalong | 9.6229 | 123.8197 | U | 6284 | 1571 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0016 | PTCI/MIDC | 9.6209 | 123.8133 | 0.74 | Terrestrial Optical Fiber Drop | 1.99 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4693 | 5 | 693 | 4693 | 0831600124 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 91 | 11.2366 | 124.9845 | U | 10185 | 2484 | 745 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0086 | PTCI/MIDC | 11.2391 | 124.9846 | 0.28 | Terrestrial Optical Fiber Drop | 1.98 | 3.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4694 | 5 | 694 | 4694 | 0402123022 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Pantaleon Granados | 14.304 | 121.008 | R | 3651 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040185 | FTAP Globe | 14.3044 | 120.993 | 0.23 | Terrestrial Optical Fiber Drop | 2.48 | 4.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4695 | 5 | 695 | 4695 | 0401014061 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Jose | 13.9403 | 121.1853 | U | 7054 | 1959 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040437 | FTAP Globe | 13.9436 | 121.1805 | 0.63 | Terrestrial Optical Fiber Drop | 2.08 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4696 | 5 | 696 | 4696 | 0603045032 | Region VI (Western Visayas) | Iloilo | Tigbauan | Dorong-an | 10.6991 | 122.37 | R | 2808 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0100 | PTCI/MIDC | 10.6974 | 122.3535 | 1.81 | Terrestrial Optical Fiber Drop | 2.53 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4697 | 5 | 697 | 4697 | 0501716007 | Region V (Bicol Region) | Camarines Sur | City of Iriga | La Purisima | 13.4031 | 123.4241 | R | 3166 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03232-C10 | PTCI/MIDC | 13.4035 | 123.4047 | 2.1 | Terrestrial Optical Fiber Drop | 2.14 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4698 | 5 | 698 | 4698 | 0301421016 | Region III (Central Luzon) | Bulacan | San Miguel | Calumpang | 15.1804 | 121.0316 | U | 5781 | 1651 | 495 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030145 | FTAP BTS | 15.1747 | 121.027 | 0.8 | Terrestrial Optical Fiber Drop | 1.99 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4699 | 5 | 699 | 4699 | 0301411010 | Region III (Central Luzon) | Bulacan | Marilao | Poblacion II | 14.7538 | 120.9494 | U | 5193 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-03201 | Edgepoint | 14.7715 | 120.9649 | 0.13 | Terrestrial Optical Fiber Drop | 0.89 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4700 | 5 | 700 | 4700 | 0402106043 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Lucia | 14.3201 | 120.956 | U | 5826 | 1713 | 514 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040196 | FTAP Globe | 14.285 | 120.978 | 0.33 | Terrestrial Optical Fiber Drop | 1.35 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4701 | 5 | 701 | 4701 | 0403427008 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Coralan | 14.4884 | 121.4219 | R | 2902 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040090 | FTAP Globe | 14.4653 | 121.4312 | 2.75 | Terrestrial Optical Fiber Drop | 2 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4702 | 5 | 702 | 4702 | 0304913006 | Region III (Central Luzon) | Nueva Ecija | Laur | Canantong | 15.5624 | 121.1874 | R | 3173 | 906 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03331-B07 | PTCI/MIDC | 15.5639 | 121.1872 | 0.16 | Terrestrial Optical Fiber Drop | 2 | 6.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4703 | 5 | 703 | 4703 | 0301420018 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santo Niño I | 14.8452 | 121.0482 | R | 2728 | 779 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01155 | Edgepoint | 14.831 | 121.0739 | 0.57 | Terrestrial Optical Fiber Drop | 1.25 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4704 | 5 | 704 | 4704 | 0500514027 | Region V (Bicol Region) | Albay | Polangui | Lanigay | 13.3141 | 123.4789 | R | 4404 | 1074 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0031 | PTCI/MIDC | 13.318 | 123.4721 | 0.86 | Terrestrial Optical Fiber Drop | 2.37 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4705 | 5 | 705 | 4705 | 0401012046 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ibaba | 13.8756 | 120.9137 | R | 2772 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1188 | FTAP Smart | 13.9336 | 120.9095 | 0.83 | Terrestrial Optical Fiber Drop | 0.35 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4706 | 5 | 706 | 4706 | 1004314003 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Kibaghot | 8.5893 | 124.4533 | R | 4147 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0110 | PTCI/MIDC | 8.5932 | 124.4529 | 0.43 | Terrestrial Optical Fiber Drop | 2.02 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4707 | 5 | 707 | 4707 | 0600414021 | Region VI (Western Visayas) | Aklan | Nabas | Union | 11.933 | 121.9558 | R | 3744 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060214 | FTAP Globe | 11.9463 | 121.9425 | 2.06 | Terrestrial Optical Fiber Drop | 2.02 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4708 | 5 | 708 | 4708 | 0103314054 | Region I (Ilocos Region) | La Union | City of San Fernando | Santiago Norte | 16.6151 | 120.3359 | R | 4099 | 1107 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1547 | FTAP Smart | 16.6157 | 120.3296 | 0.67 | Terrestrial Optical Fiber Drop | 2.32 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4709 | 5 | 709 | 4709 | 0402123020 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Marcelino Memije | 14.3039 | 121.0073 | R | 5213 | 1533 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCAG0031 | PTCI/MIDC | 14.2863 | 121.0479 | 1.71 | Terrestrial Optical Fiber Drop | 2.45 | 4.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4710 | 5 | 710 | 4710 | 0631000177 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Tacas | 10.7594 | 122.5534 | U | 6510 | 1550 | 465 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0039 | PTCI/MIDC | 10.7499 | 122.5523 | 1.06 | Terrestrial Optical Fiber Drop | 2.02 | 2.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4711 | 5 | 711 | 4711 | 0305408025 | Region III (Central Luzon) | Pampanga | Lubao | San Pablo 2nd | 14.9222 | 120.5392 | R | 4605 | 1151 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01036 | Edgepoint | 14.9196 | 120.5365 | 0.41 | Terrestrial Optical Fiber Drop | 2.02 | 2.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4712 | 5 | 712 | 4712 | 1401110002 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Alno | 16.4865 | 120.5939 | R | 3340 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BGT_0009 | LDIC | 16.4927 | 120.595 | 0.7 | Terrestrial Optical Fiber Drop | 2.03 | 2.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4713 | 5 | 713 | 4713 | 0304928007 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Mapalad | 15.4692 | 121.0937 | R | 4838 | 1382 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01499-B07 | PTCI/MIDC | 15.4676 | 121.0848 | 0.97 | Terrestrial Optical Fiber Drop | 2.02 | 2.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4714 | 5 | 714 | 4714 | 0403429013 | Region IV-A (CALABARZON) | Laguna | Siniloan | Pandeno | 14.4178 | 121.4434 | R | 3808 | 1153 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02085-C08 | PTCI/MIDC | 14.415 | 121.4491 | 0.68 | Terrestrial Optical Fiber Drop | 2.09 | 2.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4715 | 5 | 715 | 4715 | 0301420020 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay II | 14.8457 | 121.0481 | U | 4364 | 1246 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01163 | Edgepoint | 14.8231 | 121.049 | 0.48 | Terrestrial Optical Fiber Drop | 1.26 | 5.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4716 | 5 | 716 | 4716 | 0203124005 | Region II (Cagayan Valley) | Isabela | Ramon | Burgos | 16.8054 | 121.5292 | R | 2967 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ISA-02518 | Edgepoint | 16.82 | 121.5244 | 1.7 | Terrestrial Optical Fiber Drop | 2.04 | 12.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4717 | 5 | 717 | 4717 | 0305405010 | Region III (Central Luzon) | Pampanga | Candaba | Dulong Ilog | 15.0379 | 120.865 | R | 5082 | 1270 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-03136 | Edgepoint | 15.0462 | 120.8612 | 1.01 | Terrestrial Optical Fiber Drop | 2.42 | 2.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4718 | 5 | 718 | 4718 | 0402111017 | Region IV-A (CALABARZON) | Cavite | Kawit | Manggahan-Lawin | 14.4434 | 120.9102 | R | 4886 | 1437 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0019 | PTCI/MIDC | 14.452 | 120.881 | 1.17 | Terrestrial Optical Fiber Drop | 3.31 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4719 | 5 | 719 | 4719 | 0704603016 | Region VII (Central Visayas) | Negros Oriental | Bacong | San Miguel | 9.2241 | 123.2858 | U | 4958 | 1304 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 0.25 | Terrestrial Optical Fiber Drop | 2.1 | 1.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4720 | 5 | 720 | 4720 | 0105515008 | Region I (Ilocos Region) | Pangasinan | Bugallon | Cayanga | 15.9216 | 120.2073 | R | 3113 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00531 | Edgepoint | 15.9193 | 120.2233 | 1.73 | Terrestrial Optical Fiber Drop | 2.05 | 9.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4721 | 5 | 721 | 4721 | 0205007010 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Ineangan | 16.316 | 121.0912 | R | 4849 | 1276 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02470-B05 | PTCI/MIDC | 16.3152 | 121.0917 | 0.11 | Terrestrial Optical Fiber Drop | 2.05 | 2.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4722 | 5 | 722 | 4722 | 0105514018 | Region I (Ilocos Region) | Pangasinan | Bolinao | Luciente 2.0 | 16.3681 | 119.9114 | R | 3837 | 1065 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-02299 | Edgepoint | 16.3495 | 119.9126 | 2.07 | Terrestrial Optical Fiber Drop | 2.93 | 2.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4723 | 5 | 723 | 4723 | 0301420015 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Fatima I | 14.8454 | 121.0486 | R | 3250 | 928 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-03127 | Edgepoint | 14.8264 | 121.0579 | 0.28 | Terrestrial Optical Fiber Drop | 1.3 | 5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4724 | 5 | 724 | 4724 | 0402123012 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Fiorello Calimag | 14.3045 | 121.0078 | R | 2756 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040189 | FTAP Globe | 14.2936 | 121.0062 | 0.89 | Terrestrial Optical Fiber Drop | 2.53 | 4.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4725 | 5 | 725 | 4725 | 0305410015 | Region III (Central Luzon) | Pampanga | Macabebe | San Roque | 14.908 | 120.7159 | R | 4379 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01044 | Edgepoint | 14.9077 | 120.7159 | 0.04 | Terrestrial Optical Fiber Drop | 2.09 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4726 | 5 | 726 | 4726 | 1600210011 | Region XIII (Caraga) | Agusan del Norte | Santiago | Poblacion II | 9.2748 | 125.5765 | R | 4990 | 1217 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 2.06 | Terrestrial Optical Fiber Drop | 2.09 | 2.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4727 | 5 | 727 | 4727 | 0300807014 | Region III (Central Luzon) | Bataan | Mariveles | Biaan | 14.444 | 120.4519 | R | 2782 | 772 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | U26 | FTAP Smart | 14.448 | 120.464 | 1.38 | Terrestrial Optical Fiber Drop | 2.09 | 1.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4728 | 5 | 728 | 4728 | 0103311010 | Region I (Ilocos Region) | La Union | Naguilian | Baraoas Sur | 16.545 | 120.3896 | R | 3554 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 1.28 | Terrestrial Optical Fiber Drop | 2.1 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4729 | 5 | 729 | 4729 | 0730600018 | Region VII (Central Visayas) | Cebu | City of Cebu | Calamba | 10.3214 | 123.8843 | U | 9846 | 3076 | 923 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070335 | FTAP Globe | 10.3424 | 123.883 | 0.29 | Terrestrial Optical Fiber Drop | 1.71 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4730 | 5 | 730 | 4730 | 1102319019 | Region XI (Davao Region) | Davao del Norte | City of Tagum | San Isidro | 7.3911 | 125.789 | R | 4875 | 1317 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110311 | FTAP BTS | 7.3907 | 125.7925 | 0.38 | Terrestrial Optical Fiber Drop | 3.39 | 2.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4731 | 5 | 731 | 4731 | 0402103060 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Real II | 14.4332 | 120.9398 | R | 4947 | 1455 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0040 | PTCI/MIDC | 14.467 | 120.9631 | 1.76 | Terrestrial Optical Fiber Drop | 0.72 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4732 | 5 | 732 | 4732 | 0501715035 | Region V (Bicol Region) | Camarines Sur | Goa | Taytay | 13.712 | 123.4988 | R | 3365 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050065 | FTAP Globe | 13.6979 | 123.4893 | 1.87 | Terrestrial Optical Fiber Drop | 2.18 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4733 | 5 | 733 | 4733 | 0301409025 | Region III (Central Luzon) | Bulacan | Hagonoy | Tampok | 14.8493 | 120.7349 | R | 3147 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01134 | Edgepoint | 14.8432 | 120.7374 | 0.73 | Terrestrial Optical Fiber Drop | 2.1 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4734 | 5 | 734 | 4734 | 0105545005 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Bayaoas | 15.8326 | 120.3546 | R | 4386 | 1218 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTPNG0008 | PTCI/MIDC | 15.8222 | 120.356 | 1.16 | Terrestrial Optical Fiber Drop | 2.1 | 9.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4735 | 5 | 735 | 4735 | 0405615007 | Region IV-A (CALABARZON) | Quezon | Dolores | Dagatan | 14.0031 | 121.3743 | R | 3088 | 812 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040380 | FTAP Globe | 14.0132 | 121.3897 | 2.01 | Terrestrial Optical Fiber Drop | 2.11 | 4.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4736 | 5 | 736 | 4736 | 0403417045 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Santa Lucia | 14.1794 | 121.4086 | R | 3315 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02074-C08 | PTCI/MIDC | 14.1838 | 121.4085 | 0.49 | Terrestrial Optical Fiber Drop | 3.19 | 2.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4737 | 5 | 737 | 4737 | 0501603014 | Region V (Bicol Region) | Camarines Norte | Daet | Gubat | 14.1062 | 122.9533 | U | 6433 | 1608 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCNG0006 | PTCI/MIDC | 14.1178 | 122.9809 | 0.88 | Terrestrial Optical Fiber Drop | 0.93 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4738 | 5 | 738 | 4738 | 0105524019 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Bolaoit | 15.9319 | 120.43 | R | 3028 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00524 | Edgepoint | 15.9352 | 120.4328 | 0.47 | Terrestrial Optical Fiber Drop | 2.26 | 2.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4739 | 5 | 739 | 4739 | 0105543009 | Region I (Ilocos Region) | Pangasinan | Tayug | Legaspi | 16.0438 | 120.7404 | R | 3521 | 978 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03344-B07 | PTCI/MIDC | 16.0422 | 120.7422 | 0.26 | Terrestrial Optical Fiber Drop | 2.13 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4740 | 5 | 740 | 4740 | 0402106045 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santo Cristo | 14.3394 | 120.9556 | R | 4791 | 1409 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1469 | FTAP Smart | 14.3404 | 120.9555 | 0.11 | Terrestrial Optical Fiber Drop | 2.12 | 4.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4741 | 5 | 741 | 4741 | 0500513009 | Region V (Bicol Region) | Albay | Pio Duran | Caratagan | 13.0444 | 123.4572 | U | 5567 | 1357 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0038 | PTCI/MIDC | 13.0561 | 123.4573 | 1.3 | Terrestrial Optical Fiber Drop | 2.13 | 22.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4742 | 5 | 742 | 4742 | 0301423013 | Region III (Central Luzon) | Bulacan | Santa Maria | Mahabang Parang | 14.7902 | 120.9621 | U | 5373 | 1535 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0220 | FTAP Smart | 14.7875 | 120.9647 | 0.41 | Terrestrial Optical Fiber Drop | 2.2 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4743 | 5 | 743 | 4743 | 0431200029 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Parada | 13.9341 | 121.651 | R | 4016 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1427 | FTAP Smart | 13.9294 | 121.6545 | 0.65 | Terrestrial Optical Fiber Drop | 2.33 | 2.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4744 | 5 | 744 | 4744 | 0401028027 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Santa Elena | 14.0968 | 121.2048 | R | 3965 | 1101 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02522-C08 | PTCI/MIDC | 13.8694 | 121.0821 | 0.69 | Terrestrial Optical Fiber Drop | 3.38 | 2.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4745 | 5 | 745 | 4745 | 0701219006 | Region VII (Central Visayas) | Bohol | Dauis | Mayacabac | 9.6158 | 123.8649 | R | 4925 | 1231 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0014 | PTCI/MIDC | 9.6102 | 123.8632 | 0.65 | Terrestrial Optical Fiber Drop | 3.42 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4746 | 5 | 746 | 4746 | 0401030019 | Region IV-A (CALABARZON) | Batangas | Talisay | Quiling | 14.0943 | 121.0383 | R | 5147 | 1429 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B87 | FTAP Smart | 14.0935 | 121.0313 | 0.76 | Terrestrial Optical Fiber Drop | 2.14 | 7.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4747 | 5 | 747 | 4747 | 0403425003 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Estrella | 14.3355 | 121.0198 | U | 8797 | 2665 | 800 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02054-C08 | PTCI/MIDC | 14.3315 | 121.0204 | 0.46 | Terrestrial Optical Fiber Drop | 2.3 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4748 | 5 | 748 | 4748 | 0402117015 | Region IV-A (CALABARZON) | Cavite | Rosario | Muzon II | 14.4206 | 120.8666 | R | 2960 | 870 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01884-C08 | PTCI/MIDC | 14.4138 | 120.8487 | 0.27 | Terrestrial Optical Fiber Drop | 2.03 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4749 | 5 | 749 | 4749 | 0201506013 | Region II (Cagayan Valley) | Cagayan | Baggao | Bitag Grande | 17.9004 | 121.8524 | R | 3460 | 887 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O18 | FTAP Smart | 17.9001 | 121.8441 | 0.88 | Terrestrial Optical Fiber Drop | 2.15 | 14.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4750 | 5 | 750 | 4750 | 0402123007 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Benjamin Tirona | 14.3037 | 121.0078 | R | 3078 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 648 | FTAP Smart | 14.2961 | 121.016 | 0.36 | Terrestrial Optical Fiber Drop | 2.44 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4751 | 5 | 751 | 4751 | 0105547006 | Region I (Ilocos Region) | Pangasinan | Villasis | Caramutan | 15.9131 | 120.608 | R | 3913 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01685-B07 | PTCI/MIDC | 15.91 | 120.6062 | 0.4 | Terrestrial Optical Fiber Drop | 3.14 | 2.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4752 | 5 | 752 | 4752 | 0304912014 | Region III (Central Luzon) | Nueva Ecija | Jaen | San Josef | 15.3342 | 120.9115 | R | 3183 | 909 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03340-B07 | PTCI/MIDC | 15.3403 | 120.9134 | 0.71 | Terrestrial Optical Fiber Drop | 2.18 | 2.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4753 | 5 | 753 | 4753 | 0201505026 | Region II (Cagayan Valley) | Cagayan | Aparri | Gaddang | 18.343 | 121.6512 | R | 3141 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00015 | Edgepoint | 18.3401 | 121.6479 | 0.47 | Terrestrial Optical Fiber Drop | 2.17 | 10.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4754 | 5 | 754 | 4754 | 0405615005 | Region IV-A (CALABARZON) | Quezon | Dolores | Bungoy | 13.9956 | 121.369 | R | 3668 | 965 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040389 | FTAP Globe | 13.9902 | 121.3571 | 1.42 | Terrestrial Optical Fiber Drop | 2.18 | 3.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4755 | 5 | 755 | 4755 | 0205005011 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Masoc | 16.5023 | 121.1197 | R | 4136 | 1088 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNVG0016 | PTCI/MIDC | 16.5005 | 121.1392 | 2.09 | Terrestrial Optical Fiber Drop | 3.34 | 2.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4756 | 5 | 756 | 4756 | 0501717031 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Ramon | 13.7234 | 123.5402 | R | 3925 | 934 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | 4025 | FTAP Smart | 13.7298 | 123.5199 | 2.31 | Terrestrial Optical Fiber Drop | 2.19 | 6.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4757 | 5 | 757 | 4757 | 0402123005 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 4 Poblacion | 14.3043 | 121.0072 | R | 4992 | 1468 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03416-C08 | PTCI/MIDC | 14.3098 | 121.0205 | 0.25 | Terrestrial Optical Fiber Drop | 2.49 | 4.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4758 | 5 | 758 | 4758 | 0301420055 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz III | 14.856 | 121.0515 | R | 3166 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0069 | PTCI/MIDC | 14.8536 | 121.0509 | 0.28 | Terrestrial Optical Fiber Drop | 2.2 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4759 | 5 | 759 | 4759 | 0301407017 | Region III (Central Luzon) | Bulacan | Calumpit | Meyto | 14.8897 | 120.7271 | R | 3057 | 873 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01068 | Edgepoint | 14.8842 | 120.7321 | 0.8 | Terrestrial Optical Fiber Drop | 2.19 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4760 | 5 | 760 | 4760 | 0702234001 | Region VII (Central Visayas) | Cebu | City of Naga | Alfaco | 10.2423 | 123.6948 | R | 4076 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 5.2 | Terrestrial Optical Fiber Drop | 2.27 | 2.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4761 | 5 | 761 | 4761 | 0403414004 | Region IV-A (CALABARZON) | Laguna | Mabitac | Matalatala | 14.4173 | 121.4104 | R | 4771 | 1445 | 434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040113 | FTAP Globe | 14.4157 | 121.4068 | 0.43 | Terrestrial Optical Fiber Drop | 2.2 | 2.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4762 | 5 | 762 | 4762 | 0301411008 | Region III (Central Luzon) | Bulacan | Marilao | Patubig | 14.7787 | 120.9603 | U | 8800 | 2514 | 754 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00973-B07 | PTCI/MIDC | 14.7742 | 120.9577 | 0.57 | Terrestrial Optical Fiber Drop | 2.29 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4763 | 5 | 763 | 4763 | 0704610012 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Cantil-e | 9.2817 | 123.2732 | R | 4891 | 1287 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0021 | PTCI/MIDC | 9.291 | 123.2842 | 1.59 | Terrestrial Optical Fiber Drop | 3.2 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4764 | 5 | 764 | 4764 | 0105524029 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Cawayan Bogtong | 15.9422 | 120.4031 | R | 3201 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00512 | Edgepoint | 15.9511 | 120.3984 | 1.1 | Terrestrial Optical Fiber Drop | 2.63 | 2.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4765 | 5 | 765 | 4765 | 1600209017 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Punta | 8.969 | 125.295 | R | 4069 | 992 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0015 | PTCI/MIDC | 8.9888 | 125.2896 | 2.28 | Terrestrial Optical Fiber Drop | 2.39 | 2.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4766 | 5 | 766 | 4766 | 0105532048 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Malacañang | 15.8807 | 120.3262 | R | 3868 | 1074 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01713-B07 | PTCI/MIDC | 15.906 | 120.3364 | 1.48 | Terrestrial Optical Fiber Drop | 5.76 | 5.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4767 | 5 | 767 | 4767 | 1206312009 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Lumakil | 6.2141 | 125.0365 | R | 3930 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120066 | FTAP BTS | 6.2133 | 125.0389 | 0.28 | Terrestrial Optical Fiber Drop | 3.2 | 3.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4768 | 5 | 768 | 4768 | 0604532005 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Kumaliskis | 10.5419 | 123.2491 | R | 3744 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060364 | FTAP Globe | 10.5112 | 123.2785 | 6.91 | Terrestrial Optical Fiber Drop | 5.86 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4769 | 5 | 769 | 4769 | 0504111021 | Region V (Bicol Region) | Masbate | City of Masbate | Malinta | 12.3757 | 123.6287 | R | 4661 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMSG0002 | PTCI/MIDC | 12.3723 | 123.6242 | 0.61 | Terrestrial Optical Fiber Drop | 2.39 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4770 | 5 | 770 | 4770 | 0405645032 | Region IV-A (CALABARZON) | Quezon | Sariaya | Pili | 13.9437 | 121.5396 | R | 3746 | 985 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03244-C08 | PTCI/MIDC | 13.9415 | 121.5272 | 1.35 | Terrestrial Optical Fiber Drop | 3.05 | 2.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4771 | 5 | 771 | 4771 | 0405807005 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Third District | 14.326 | 121.3071 | R | 2982 | 828 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01912 | Edgepoint | 14.3279 | 121.3089 | 2.02 | Terrestrial Optical Fiber Drop | 3.78 | 11.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4772 | 5 | 772 | 4772 | 0305408041 | Region III (Central Luzon) | Pampanga | Lubao | Santa Teresa 2nd | 14.8869 | 120.5635 | R | 4515 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030559 | FTAP Globe | 14.8918 | 120.5547 | 1.09 | Terrestrial Optical Fiber Drop | 2.85 | 2.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4773 | 5 | 773 | 4773 | 0301414007 | Region III (Central Luzon) | Bulacan | Obando | Pag-asa | 14.7205 | 120.9298 | R | 3604 | 1029 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01025-A01 | PTCI/MIDC | 14.726 | 120.926 | 0.96 | Terrestrial Optical Fiber Drop | 1.44 | 2.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4774 | 5 | 774 | 4774 | 0301409011 | Region III (Central Luzon) | Bulacan | Hagonoy | San Jose | 14.8307 | 120.7326 | R | 4469 | 1276 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01157 | Edgepoint | 14.83 | 120.7349 | 0.26 | Terrestrial Optical Fiber Drop | 2.24 | 3.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4775 | 5 | 775 | 4775 | 1705205058 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Sapul | 13.3652 | 121.1898 | R | 4507 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 2.7 | Terrestrial Optical Fiber Drop | 3.06 | 2.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4776 | 5 | 776 | 4776 | 0304911022 | Region III (Central Luzon) | Nueva Ecija | Guimba | Cavite | 15.6783 | 120.7711 | R | 4435 | 1267 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0005 | LDIC | 15.6738 | 120.7684 | 0.57 | Terrestrial Optical Fiber Drop | 2.3 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4777 | 5 | 777 | 4777 | 1102319007 | Region XI (Davao Region) | Davao del Norte | City of Tagum | La Filipina | 7.4753 | 125.8051 | U | 21619 | 5842 | 1753 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110417 | FTAP Globe | 7.4743 | 125.8071 | 0.24 | Terrestrial Optical Fiber Drop | 2.27 | 1.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4778 | 5 | 778 | 4778 | 0403422001 | Region IV-A (CALABARZON) | Laguna | Pila | Aplaya | 14.2594 | 121.3546 | R | 3621 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040217 | FTAP Globe | 14.2501 | 121.3549 | 1.04 | Terrestrial Optical Fiber Drop | 2.76 | 2.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4779 | 5 | 779 | 4779 | 0402120031 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya V | 14.3834 | 120.8339 | R | 3089 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 1.75 | Terrestrial Optical Fiber Drop | 1.9 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4780 | 5 | 780 | 4780 | 0402106068 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Antonio De Padua II | 14.3206 | 120.9569 | R | 3223 | 947 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02155-C08 | PTCI/MIDC | 14.3077 | 120.9029 | 0.84 | Terrestrial Optical Fiber Drop | 1.31 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4781 | 5 | 781 | 4781 | 0504121002 | Region V (Bicol Region) | Masbate | Uson | Armenia | 12.2534 | 123.7438 | R | 4334 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMSG0001 | PTCI/MIDC | 12.243 | 123.7468 | 1.2 | Terrestrial Optical Fiber Drop | 2.28 | 17.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4782 | 5 | 782 | 4782 | 0704608002 | Region VII (Central Visayas) | Negros Oriental | City of Canlaon | Binalbagan | 10.378 | 123.2495 | R | 2675 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0018 | PTCI/MIDC | 10.3863 | 123.2275 | 2.58 | Terrestrial Optical Fiber Drop | 2.28 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4783 | 5 | 783 | 4783 | 0601914027 | Region VI (Western Visayas) | Capiz | City of Roxas | Dayao | 11.5897 | 122.7255 | U | 5406 | 1422 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060225 | FTAP Globe | 11.5916 | 122.7235 | 0.31 | Terrestrial Optical Fiber Drop | 2.44 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4784 | 5 | 784 | 4784 | 0506208015 | Region V (Bicol Region) | Sorsogon | Gubat | Cogon | 12.9351 | 124.1257 | R | 2742 | 685 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 1.61 | Terrestrial Optical Fiber Drop | 2.3 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4785 | 5 | 785 | 4785 | 0604503012 | Region VI (Western Visayas) | Negros Occidental | Binalbagan | San Pedro | 10.1928 | 122.9352 | U | 3922 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0018 | PTCI/MIDC | 10.3863 | 123.2275 | 2.59 | Terrestrial Optical Fiber Drop | 16.98 | 5.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4786 | 5 | 786 | 4786 | 0403408007 | Region IV-A (CALABARZON) | Laguna | Famy | Bulihan | 14.4592 | 121.4507 | R | 3109 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040091 | FTAP Globe | 14.4629 | 121.4693 | 1.04 | Terrestrial Optical Fiber Drop | 2.63 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4787 | 5 | 787 | 4787 | 0704623002 | Region VII (Central Visayas) | Negros Oriental | Valencia | Balabag East | 9.2957 | 123.2583 | R | 4077 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070268 | FTAP Globe | 9.2958 | 123.275 | 1.83 | Terrestrial Optical Fiber Drop | 2.31 | 4.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4788 | 5 | 788 | 4788 | 0205703018 | Region II (Cagayan Valley) | Quirino | Diffun | Rizal | 16.598 | 121.5197 | R | 3801 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_QUI_0002 | LDIC | 16.5992 | 121.5091 | 1.14 | Terrestrial Optical Fiber Drop | 2.31 | 5.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4789 | 5 | 789 | 4789 | 0702211015 | Region VII (Central Visayas) | Cebu | City of Bogo | Libertad | 11.0255 | 124.0209 | R | 4883 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0014 | PTCI/MIDC | 11.029 | 124.0217 | 0.4 | Terrestrial Optical Fiber Drop | 2.8 | 2.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4790 | 5 | 790 | 4790 | 0105525037 | Region I (Ilocos Region) | Pangasinan | Manaoag | Pao | 16.05 | 120.5049 | R | 3837 | 1065 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03212-B07 | PTCI/MIDC | 16.0506 | 120.5069 | 0.22 | Terrestrial Optical Fiber Drop | 2.32 | 7.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4791 | 5 | 791 | 4791 | 0301411013 | Region III (Central Luzon) | Bulacan | Marilao | Santa Rosa I | 14.7785 | 120.9732 | U | 11770 | 3362 | 1009 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01197 | Edgepoint | 14.7777 | 120.9744 | 0.16 | Terrestrial Optical Fiber Drop | 2.32 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4792 | 5 | 792 | 4792 | 0403429016 | Region IV-A (CALABARZON) | Laguna | Siniloan | Macatad | 14.4528 | 121.4621 | R | 3326 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040095 | FTAP Globe | 14.4476 | 121.4537 | 1.08 | Terrestrial Optical Fiber Drop | 2.32 | 2.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4793 | 5 | 793 | 4793 | 0402115018 | Region IV-A (CALABARZON) | Cavite | Naic | Mabolo | 14.3154 | 120.7458 | R | 4681 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040180 | FTAP Globe | 14.3125 | 120.7409 | 0.62 | Terrestrial Optical Fiber Drop | 2.87 | 2.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4794 | 5 | 794 | 4794 | 1102319003 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Bincungan | 7.3741 | 125.7778 | R | 4113 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110240 | FTAP BTS | 7.3873 | 125.761 | 2.36 | Terrestrial Optical Fiber Drop | 3.13 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4795 | 5 | 795 | 4795 | 0402118061 | Region IV-A (CALABARZON) | Cavite | Silang | Narra III | 14.2251 | 120.9624 | R | 3393 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040270 | FTAP Globe | 14.1788 | 120.9837 | 0.75 | Terrestrial Optical Fiber Drop | 6.74 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4796 | 5 | 796 | 4796 | 0600402002 | Region VI (Western Visayas) | Aklan | Balete | Arcangel | 11.5442 | 122.373 | R | 3727 | 955 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060221 | FTAP Globe | 11.5343 | 122.369 | 1.93 | Terrestrial Optical Fiber Drop | 1.47 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4797 | 5 | 797 | 4797 | 1001312060 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | San Martin | 7.9962 | 125.1975 | R | 3721 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100195 | FTAP Globe | 8.0083 | 125.1335 | 7.18 | Terrestrial Optical Fiber Drop | 2.35 | 5.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4798 | 5 | 798 | 4798 | 0401028014 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Jose | 14.0732 | 121.1972 | R | 4122 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4617 | FTAP Smart | 13.8703 | 121.0551 | 0.75 | Terrestrial Optical Fiber Drop | 3.11 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4799 | 5 | 799 | 4799 | 0301416015 | Region III (Central Luzon) | Bulacan | Paombong | Santo Niño | 14.8374 | 120.7908 | R | 3736 | 1067 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01152 | Edgepoint | 14.8318 | 120.7889 | 0.66 | Terrestrial Optical Fiber Drop | 2.34 | 3.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4800 | 5 | 800 | 4800 | 0301403008 | Region III (Central Luzon) | Bulacan | Baliuag | Matangtubig | 14.9546 | 120.8624 | R | 3483 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01071-B07 | PTCI/MIDC | 14.9558 | 120.8622 | 0.14 | Terrestrial Optical Fiber Drop | 2.84 | 2.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4801 | 5 | 801 | 4801 | 0402106025 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres I | 14.3195 | 120.9566 | R | 4484 | 1318 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03022-C08 | PTCI/MIDC | 14.3249 | 120.9482 | 0.55 | Terrestrial Optical Fiber Drop | 1.26 | 1.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4802 | 5 | 802 | 4802 | 0306907006 | Region III (Central Luzon) | Tarlac | La Paz | Dumarais | 15.4347 | 120.6896 | R | 4892 | 1254 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030398 | FTAP Globe | 15.4386 | 120.6795 | 1.17 | Terrestrial Optical Fiber Drop | 3.25 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4803 | 5 | 803 | 4803 | 0401011022 | Region IV-A (CALABARZON) | Batangas | Laurel | San Gregorio | 14.0407 | 120.864 | R | 3907 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1319 | FTAP Smart | 14.05 | 120.8534 | 1.55 | Terrestrial Optical Fiber Drop | 2.37 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4804 | 5 | 804 | 4804 | 0105532029 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Cobol | 15.8993 | 120.3918 | R | 3991 | 1108 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_PNG_0006 | LDIC | 15.9097 | 120.4032 | 1.68 | Terrestrial Optical Fiber Drop | 3.23 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4805 | 5 | 805 | 4805 | 0401011011 | Region IV-A (CALABARZON) | Batangas | Laurel | Gulod | 14.0331 | 120.9411 | R | 3182 | 883 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 2.87 | Terrestrial Optical Fiber Drop | 2.38 | 6.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4806 | 5 | 806 | 4806 | 0402102005 | Region IV-A (CALABARZON) | Cavite | Amadeo | Loma | 14.1495 | 120.9299 | R | 2872 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040287 | FTAP Globe | 14.1494 | 120.9289 | 0.11 | Terrestrial Optical Fiber Drop | 2.38 | 2.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4807 | 5 | 807 | 4807 | 0301421014 | Region III (Central Luzon) | Bulacan | San Miguel | Buliran | 15.1663 | 120.9949 | U | 5748 | 1642 | 493 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030138 | FTAP BTS | 15.1692 | 120.9891 | 0.7 | Terrestrial Optical Fiber Drop | 2.37 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4808 | 5 | 808 | 4808 | 0403405060 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Uwisan | 14.2377 | 121.1721 | R | 3257 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040220 | FTAP Globe | 14.2432 | 121.1711 | 0.63 | Terrestrial Optical Fiber Drop | 3.26 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4809 | 5 | 809 | 4809 | 0403424060 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Miguel | 14.0481 | 121.3059 | R | 3851 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040364 | FTAP Globe | 14.0421 | 121.2985 | 1.05 | Terrestrial Optical Fiber Drop | 2.84 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4810 | 5 | 810 | 4810 | 0105532078 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | San Juan | 15.916 | 120.3285 | R | 3496 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00534 | Edgepoint | 15.9146 | 120.3296 | 0.2 | Terrestrial Optical Fiber Drop | 2.5 | 2.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4811 | 5 | 811 | 4811 | 0504112028 | Region V (Bicol Region) | Masbate | Milagros | Tinaclipan | 12.2158 | 123.4862 | R | 1167 | 284 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03140-C10 | PTCI/MIDC | 12.2309 | 123.5058 | 2.72 | Terrestrial Optical Fiber Drop | 0.54 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4812 | 5 | 812 | 4812 | 0304913022 | Region III (Central Luzon) | Nueva Ecija | Laur | Siclong | 15.58 | 121.223 | R | 3705 | 1058 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00650 | Edgepoint | 15.5821 | 121.2232 | 0.23 | Terrestrial Optical Fiber Drop | 2.38 | 8.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4813 | 5 | 813 | 4813 | 0730600074 | Region VII (Central Visayas) | Cebu | City of Cebu | Sirao | 10.4167 | 123.8707 | R | 3651 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0058 | PTCI/MIDC | 10.4161 | 123.8716 | 0.12 | Terrestrial Optical Fiber Drop | 2.39 | 6.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4814 | 5 | 814 | 4814 | 0506207025 | Region V (Bicol Region) | Sorsogon | Donsol | Ogod | 12.9012 | 123.6152 | R | 4272 | 1068 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050214 | FTAP Globe | 12.9005 | 123.6171 | 0.22 | Terrestrial Optical Fiber Drop | 2.39 | 16.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4815 | 5 | 815 | 4815 | 0401005026 | Region IV-A (CALABARZON) | Batangas | Batangas City | Domoclay | 13.7458 | 121.0891 | R | 4024 | 1117 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040585 | FTAP Globe | 13.7475 | 121.0914 | 0.31 | Terrestrial Optical Fiber Drop | 2.4 | 3.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4816 | 5 | 816 | 4816 | 0105545014 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Malibong | 15.8375 | 120.3165 | R | 3289 | 913 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010217 | FTAP Globe | 15.8239 | 120.3269 | 1.88 | Terrestrial Optical Fiber Drop | 2.41 | 10.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4817 | 5 | 817 | 4817 | 0631000194 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Yulo Drive | 10.6833 | 122.518 | R | 4035 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060274 | FTAP Globe | 10.6867 | 122.5207 | 0.48 | Terrestrial Optical Fiber Drop | 2.82 | 2.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4818 | 5 | 818 | 4818 | 1102502003 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Calubihan | 6.9738 | 125.99 | R | 4269 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDLG0043 | PTCI/MIDC | 6.9736 | 125.99 | 0.03 | Terrestrial Optical Fiber Drop | 2.83 | 2.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4819 | 5 | 819 | 4819 | 0301411011 | Region III (Central Luzon) | Bulacan | Marilao | Prenza I | 14.783 | 120.9842 | U | 9427 | 2693 | 808 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030613 | FTAP Globe | 14.7823 | 120.986 | 0.21 | Terrestrial Optical Fiber Drop | 2.43 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4820 | 5 | 820 | 4820 | 0105525043 | Region I (Ilocos Region) | Pangasinan | Manaoag | Sapang | 16.0337 | 120.4979 | R | 3108 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03212-B07 | PTCI/MIDC | 16.0506 | 120.5069 | 0.76 | Terrestrial Optical Fiber Drop | 1.96 | 6.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4821 | 5 | 821 | 4821 | 0501604006 | Region V (Bicol Region) | Camarines Norte | San Lorenzo Ruiz | Mampurog | 14.0458 | 122.8844 | R | 2849 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050028 | FTAP Globe | 14.0401 | 122.876 | 1.11 | Terrestrial Optical Fiber Drop | 2.42 | 5.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4822 | 5 | 822 | 4822 | 0702221004 | Region VII (Central Visayas) | Cebu | Daanbantayan | Bateria | 11.1413 | 124.0256 | R | 3952 | 1040 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0067 | PTCI/MIDC | 11.2021 | 124.0202 | 6.79 | Terrestrial Optical Fiber Drop | 2.48 | 2.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4823 | 5 | 823 | 4823 | 1705205021 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Guinobatan | 13.3883 | 121.1837 | R | 4477 | 1147 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 0.38 | Terrestrial Optical Fiber Drop | 2.89 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4824 | 5 | 824 | 4824 | 0402120006 | Region IV-A (CALABARZON) | Cavite | Tanza | Bunga | 14.3549 | 120.8719 | R | 4061 | 1194 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02211-C08 | PTCI/MIDC | 14.3398 | 120.8811 | 1.95 | Terrestrial Optical Fiber Drop | 2.42 | 3.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4825 | 5 | 825 | 4825 | 0401010015 | Region IV-A (CALABARZON) | Batangas | Ibaan | Pangao | 13.8295 | 121.1356 | R | 3480 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040552 | FTAP Globe | 13.8283 | 121.1127 | 0.37 | Terrestrial Optical Fiber Drop | 1.7 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4826 | 5 | 826 | 4826 | 0704624001 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Bagawines | 10.3576 | 123.3254 | U | 6042 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070250 | FTAP Globe | 10.3733 | 123.3313 | 1.86 | Terrestrial Optical Fiber Drop | 2.44 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4827 | 5 | 827 | 4827 | 0304924004 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Lawang Kupang | 15.3485 | 120.8578 | R | 3436 | 981 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNEG0047 | PTCI/MIDC | 15.3471 | 120.839 | 2.02 | Terrestrial Optical Fiber Drop | 2.45 | 6.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4828 | 5 | 828 | 4828 | 0403424079 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Soledad | 14.0423 | 121.3149 | R | 4122 | 1249 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02080-C08 | PTCI/MIDC | 14.0357 | 121.3253 | 1.35 | Terrestrial Optical Fiber Drop | 2.46 | 2.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4829 | 5 | 829 | 4829 | 0907322007 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Bomba | 7.8054 | 123.426 | R | 4320 | 1107 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0092 | PTCI/MIDC | 7.7954 | 123.4262 | 1.11 | Terrestrial Optical Fiber Drop | 3.19 | 2.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4830 | 5 | 830 | 4830 | 0402106029 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco I | 14.3206 | 120.9561 | R | 3262 | 959 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0034 | PTCI/MIDC | 14.3326 | 120.9569 | 0.29 | Terrestrial Optical Fiber Drop | 1.38 | 2.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4831 | 5 | 831 | 4831 | 0105517007 | Region I (Ilocos Region) | Pangasinan | Calasiao | Dinalaoan | 15.9956 | 120.3411 | R | 4147 | 1151 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010165 | FTAP Globe | 15.9927 | 120.3364 | 0.59 | Terrestrial Optical Fiber Drop | 3.06 | 2.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4832 | 5 | 832 | 4832 | 0201528003 | Region II (Cagayan Valley) | Cagayan | Tuao | Alabug | 17.7245 | 121.4812 | R | 3688 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAG-02384 | Edgepoint | 17.7363 | 121.4569 | 2.89 | Terrestrial Optical Fiber Drop | 2.45 | 5.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4833 | 5 | 833 | 4833 | 0730600002 | Region VII (Central Visayas) | Cebu | City of Cebu | Agsungot | 10.4346 | 123.9111 | R | 2775 | 867 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070320 | FTAP Globe | 10.4256 | 123.9164 | 1.15 | Terrestrial Optical Fiber Drop | 2.46 | 4.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4834 | 5 | 834 | 4834 | 0501736023 | Region V (Bicol Region) | Camarines Sur | Tigaon | Tinawagan | 13.6259 | 123.4669 | R | 4190 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 2.62 | Terrestrial Optical Fiber Drop | 3.34 | 2.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4835 | 5 | 835 | 4835 | 0401001008 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Coral Na Munti | 13.9345 | 120.9129 | R | 4476 | 1243 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1188 | FTAP Smart | 13.9336 | 120.9095 | 0.38 | Terrestrial Optical Fiber Drop | 2.46 | 3.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4836 | 5 | 836 | 4836 | 0301421031 | Region III (Central Luzon) | Bulacan | San Miguel | Masalipit | 15.1489 | 121.0372 | R | 3523 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01042-B07 | PTCI/MIDC | 15.1477 | 121.0378 | 0.15 | Terrestrial Optical Fiber Drop | 2.48 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4837 | 5 | 837 | 4837 | 0403415021 | Region IV-A (CALABARZON) | Laguna | Magdalena | Salasad | 14.2023 | 121.4286 | R | 3340 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040248 | FTAP Globe | 14.2076 | 121.3988 | 0.95 | Terrestrial Optical Fiber Drop | 0.48 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4838 | 5 | 838 | 4838 | 0402118062 | Region IV-A (CALABARZON) | Cavite | Silang | Pooc II | 14.1987 | 120.9913 | R | 2938 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02174-C08 | PTCI/MIDC | 14.1997 | 120.9896 | 0.22 | Terrestrial Optical Fiber Drop | 2.48 | 2.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4839 | 5 | 839 | 4839 | 0105545019 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Real | 15.8065 | 120.3463 | R | 3153 | 875 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTPNG0008 | PTCI/MIDC | 15.8222 | 120.356 | 2.03 | Terrestrial Optical Fiber Drop | 2.5 | 11.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4840 | 5 | 840 | 4840 | 0105532053 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Matagdem | 15.9474 | 120.3599 | R | 3433 | 953 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00513 | Edgepoint | 15.951 | 120.3521 | 0.93 | Terrestrial Optical Fiber Drop | 2.5 | 1.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4841 | 5 | 841 | 4841 | 0402106075 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas II | 14.315 | 120.9686 | R | 4817 | 1416 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01888-C08 | PTCI/MIDC | 14.3799 | 120.9775 | 0.82 | Terrestrial Optical Fiber Drop | 0.42 | 2.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4842 | 5 | 842 | 4842 | 0307109011 | Region III (Central Luzon) | Zambales | San Antonio | San Miguel | 14.9507 | 120.0652 | R | 4277 | 1125 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030528 | FTAP Globe | 14.9501 | 120.061 | 0.46 | Terrestrial Optical Fiber Drop | 2.7 | 2.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4843 | 5 | 843 | 4843 | 0301421035 | Region III (Central Luzon) | Bulacan | San Miguel | Partida | 15.2011 | 121.0146 | R | 3662 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-BUL-00798 | Edgepoint | 15.2201 | 121.0067 | 2.27 | Terrestrial Optical Fiber Drop | 2.51 | 3.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4844 | 5 | 844 | 4844 | 0601902016 | Region VI (Western Visayas) | Capiz | Dao | Matagnop | 11.3806 | 122.7031 | R | 4158 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060243 | FTAP Globe | 11.3433 | 122.6758 | 5.1 | Terrestrial Optical Fiber Drop | 2.52 | 3.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4845 | 5 | 845 | 4845 | 0105501002 | Region I (Ilocos Region) | Pangasinan | Agno | Aloleng | 16.1233 | 119.7836 | R | 3147 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH010129 | FTAP Globe | 16.122 | 119.8094 | 2.75 | Terrestrial Optical Fiber Drop | 2.53 | 10.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4846 | 5 | 846 | 4846 | 0401032004 | Region IV-A (CALABARZON) | Batangas | Taysan | Dagatan | 13.736 | 121.2007 | R | 3822 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040588 | FTAP Globe | 13.7414 | 121.1851 | 1.79 | Terrestrial Optical Fiber Drop | 2.54 | 11.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4847 | 5 | 847 | 4847 | 0730600001 | Region VII (Central Visayas) | Cebu | City of Cebu | Adlaon | 10.4369 | 123.8696 | R | 4418 | 1380 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0058 | PTCI/MIDC | 10.4161 | 123.8716 | 2.33 | Terrestrial Optical Fiber Drop | 2.53 | 7.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4848 | 5 | 848 | 4848 | 0203131023 | Region II (Cagayan Valley) | Isabela | San Mariano | Minanga | 17.0004 | 122.0312 | R | 4830 | 1271 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01324-B06 | PTCI/MIDC | 16.9856 | 122.0265 | 1.72 | Terrestrial Optical Fiber Drop | 2.56 | 18.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4849 | 5 | 849 | 4849 | 0305413036 | Region III (Central Luzon) | Pampanga | Mexico | San Patricio | 15.0918 | 120.7272 | R | 5150 | 1287 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01649-B07 | PTCI/MIDC | 15.0951 | 120.7293 | 0.44 | Terrestrial Optical Fiber Drop | 2.57 | 2.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4850 | 5 | 850 | 4850 | 0504111028 | Region V (Bicol Region) | Masbate | City of Masbate | Tugbo | 12.3507 | 123.6396 | U | 8553 | 2086 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1018 | FTAP Smart | 12.3584 | 123.638 | 0.88 | Terrestrial Optical Fiber Drop | 2.57 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4851 | 5 | 851 | 4851 | 0402106072 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Luis II | 14.3182 | 120.952 | R | 4565 | 1342 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03416-C08 | PTCI/MIDC | 14.3098 | 121.0205 | 0.63 | Terrestrial Optical Fiber Drop | 1.61 | 1.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4852 | 5 | 852 | 4852 | 0306917017 | Region III (Central Luzon) | Tarlac | Victoria | San Agustin | 15.598 | 120.6817 | R | 3741 | 959 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030003 | FTAP BTS | 15.5907 | 120.6712 | 1.38 | Terrestrial Optical Fiber Drop | 2.59 | 4.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4853 | 5 | 853 | 4853 | 0304921001 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Callos | 15.3377 | 121.0347 | R | 3825 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03336-B07 | PTCI/MIDC | 15.3501 | 121.0376 | 1.42 | Terrestrial Optical Fiber Drop | 2.59 | 8.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4854 | 5 | 854 | 4854 | 0105533002 | Region I (Ilocos Region) | Pangasinan | San Fabian | Angio | 16.1139 | 120.4272 | R | 3443 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00406 | Edgepoint | 16.1128 | 120.4274 | 0.12 | Terrestrial Optical Fiber Drop | 2.99 | 2.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4855 | 5 | 855 | 4855 | 1400108010 | Cordillera Administrative Region (CAR) | Abra | La Paz | Poblacion | 17.6777 | 120.6888 | R | 3627 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140111 | FTAP Globe | 17.6746 | 120.6892 | 0.35 | Terrestrial Optical Fiber Drop | 2.95 | 2.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4856 | 5 | 856 | 4856 | 0301415020 | Region III (Central Luzon) | Bulacan | Pandi | Siling Matanda | 14.9043 | 120.9896 | R | 3721 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030049 | FTAP BTS | 14.9033 | 120.9911 | 0.18 | Terrestrial Optical Fiber Drop | 2.77 | 2.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4857 | 5 | 857 | 4857 | 0301407005 | Region III (Central Luzon) | Bulacan | Calumpit | Bulusan | 14.9086 | 120.7425 | R | 2721 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01042 | Edgepoint | 14.9092 | 120.7424 | 0.06 | Terrestrial Optical Fiber Drop | 2.73 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4858 | 5 | 858 | 4858 | 0803738083 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Jose | 11.0988 | 124.552 | R | 3995 | 1051 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080189 | FTAP BTS | 11.0827 | 124.5638 | 2.21 | Terrestrial Optical Fiber Drop | 2.71 | 2.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4859 | 5 | 859 | 4859 | 0205007002 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Belance | 16.1928 | 121.2418 | R | 3949 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-00385 | Edgepoint | 16.1959 | 121.2371 | 0.61 | Terrestrial Optical Fiber Drop | 2.63 | 23.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4860 | 5 | 860 | 4860 | 0402123003 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Barangay 2 Poblacion | 14.3043 | 121.0081 | R | 4382 | 1288 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03416-C08 | PTCI/MIDC | 14.3098 | 121.0205 | 0.72 | Terrestrial Optical Fiber Drop | 2.51 | 4.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4861 | 5 | 861 | 4861 | 1001312027 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Apo Macote | 7.9592 | 125.2229 | U | 5621 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100198 | FTAP Globe | 7.9734 | 125.1346 | 9.86 | Terrestrial Optical Fiber Drop | 2.63 | 1.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4862 | 5 | 862 | 4862 | 0730600010 | Region VII (Central Visayas) | Cebu | City of Cebu | Binaliw | 10.4249 | 123.9162 | R | 3497 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CEB-03155 | Edgepoint | 10.425 | 123.9168 | 0.07 | Terrestrial Optical Fiber Drop | 2.86 | 2.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4863 | 5 | 863 | 4863 | 0702224019 | Region VII (Central Visayas) | Cebu | Dumanjug | Cogon | 10.0355 | 123.4521 | R | 3479 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0084 | PTCI/MIDC | 10.0456 | 123.429 | 2.77 | Terrestrial Optical Fiber Drop | 2.91 | 2.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4864 | 5 | 864 | 4864 | 0631000167 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Santo Niño Norte | 10.6811 | 122.5194 | R | 4060 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060274 | FTAP Globe | 10.6867 | 122.5207 | 0.64 | Terrestrial Optical Fiber Drop | 2.76 | 2.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4865 | 5 | 865 | 4865 | 0301409014 | Region III (Central Luzon) | Bulacan | Hagonoy | San Nicolas | 14.8276 | 120.7297 | R | 4852 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01157 | Edgepoint | 14.83 | 120.7349 | 0.62 | Terrestrial Optical Fiber Drop | 2.67 | 4.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4866 | 5 | 866 | 4866 | 0506209019 | Region V (Bicol Region) | Sorsogon | Irosin | Patag | 12.7153 | 124.0566 | R | 3459 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050226 | FTAP Globe | 12.7081 | 124.0387 | 2.11 | Terrestrial Optical Fiber Drop | 2.7 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4867 | 5 | 867 | 4867 | 0803748015 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Cabuynan | 11.0816 | 125.0249 | R | 3151 | 829 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0081 | PTCI/MIDC | 11.0803 | 125.0204 | 0.51 | Terrestrial Optical Fiber Drop | 2.69 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4868 | 5 | 868 | 4868 | 0201505039 | Region II (Cagayan Valley) | Cagayan | Aparri | Tallungan | 18.3369 | 121.6514 | R | 3517 | 901 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00015 | Edgepoint | 18.3401 | 121.6479 | 0.52 | Terrestrial Optical Fiber Drop | 2.69 | 9.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4869 | 5 | 869 | 4869 | 0304912028 | Region III (Central Luzon) | Nueva Ecija | Jaen | Santo Tomas South | 15.3545 | 120.9141 | R | 5384 | 1538 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00759 | Edgepoint | 15.3475 | 120.9069 | 1.09 | Terrestrial Optical Fiber Drop | 2.9 | 2.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4870 | 5 | 870 | 4870 | 0105526001 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Alitaya | 16.0327 | 120.4079 | R | 4725 | 1312 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00446 | Edgepoint | 16.0255 | 120.4179 | 1.33 | Terrestrial Optical Fiber Drop | 2.97 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4871 | 5 | 871 | 4871 | 0501605025 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Santa Rosa Norte | 14.2936 | 122.7212 | R | 4029 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050004 | FTAP Globe | 14.2889 | 122.6958 | 2.79 | Terrestrial Optical Fiber Drop | 2.71 | 11.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4872 | 5 | 872 | 4872 | 1001320026 | Region X (Northern Mindanao) | Bukidnon | Talakag | San Antonio | 8.2135 | 124.6062 | R | 4544 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0043 | PTCI/MIDC | 8.2021 | 124.6056 | 1.27 | Terrestrial Optical Fiber Drop | 2.73 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4873 | 5 | 873 | 4873 | 0601914035 | Region VI (Western Visayas) | Capiz | City of Roxas | Libas | 11.5942 | 122.7221 | U | 8094 | 2130 | 639 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060225 | FTAP Globe | 11.5916 | 122.7235 | 0.33 | Terrestrial Optical Fiber Drop | 1.82 | 1.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4874 | 5 | 874 | 4874 | 0301415017 | Region III (Central Luzon) | Bulacan | Pandi | Real de Cacarong | 14.9165 | 120.9762 | R | 4871 | 1391 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBUG0054 | PTCI/MIDC | 14.9208 | 120.9714 | 0.7 | Terrestrial Optical Fiber Drop | 3.08 | 2.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4875 | 5 | 875 | 4875 | 0702213007 | Region VII (Central Visayas) | Cebu | Borbon | Cadaruhan | 10.8595 | 124.019 | R | 4888 | 1286 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070308 | FTAP Globe | 10.8648 | 123.9816 | 4.12 | Terrestrial Optical Fiber Drop | 2.75 | 4.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4876 | 5 | 876 | 4876 | 0402108028 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Tapia | 14.3644 | 120.8794 | R | 5173 | 1521 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040144 | FTAP Globe | 14.3672 | 120.8924 | 1.43 | Terrestrial Optical Fiber Drop | 2.73 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4877 | 5 | 877 | 4877 | 0205706011 | Region II (Cagayan Valley) | Quirino | Nagtipunan | San Dionisio II | 16.2393 | 121.5938 | R | 3574 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1021 | FTAP Smart | 16.2289 | 121.6012 | 1.4 | Terrestrial Optical Fiber Drop | 2.75 | 6.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4878 | 5 | 878 | 4878 | 0501608026 | Region V (Bicol Region) | Camarines Norte | Paracale | Tawig | 14.2552 | 122.7568 | R | 3977 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 4.28 | Terrestrial Optical Fiber Drop | 2.75 | 7.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4879 | 5 | 879 | 4879 | 0500508029 | Region V (Bicol Region) | Albay | City of Ligao | Mahaba | 13.2693 | 123.5471 | R | 3579 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050152 | FTAP Globe | 13.259 | 123.5426 | 1.24 | Terrestrial Optical Fiber Drop | 3.56 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4880 | 5 | 880 | 4880 | 0304912002 | Region III (Central Luzon) | Nueva Ecija | Jaen | Dampulan | 15.34 | 120.9099 | R | 5391 | 1540 | 462 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02676 | Edgepoint | 15.3391 | 120.9072 | 0.3 | Terrestrial Optical Fiber Drop | 2.76 | 3.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4881 | 5 | 881 | 4881 | 0604520021 | Region VI (Western Visayas) | Negros Occidental | Murcia | San Miguel | 10.5386 | 123.083 | R | 4207 | 1137 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0054 | PTCI/MIDC | 10.515 | 123.0955 | 2.95 | Terrestrial Optical Fiber Drop | 3.13 | 2.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4882 | 5 | 882 | 4882 | 0105532028 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Caoayan-Kiling | 15.8493 | 120.3255 | R | 4514 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01715-B07 | PTCI/MIDC | 15.8585 | 120.3329 | 1.29 | Terrestrial Optical Fiber Drop | 2.76 | 8.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4883 | 5 | 883 | 4883 | 1206312017 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Rubber | 6.1983 | 125.0454 | R | 3777 | 1049 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSCG0072 | PTCI/MIDC | 6.2028 | 125.0594 | 1.63 | Terrestrial Optical Fiber Drop | 2.95 | 2.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4884 | 5 | 884 | 4884 | 0304907001 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Bagong Sikat | 15.4813 | 121.3073 | R | 3203 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02887-B07 | PTCI/MIDC | 15.478 | 121.3066 | 0.37 | Terrestrial Optical Fiber Drop | 2.76 | 20.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4885 | 5 | 885 | 4885 | 0402109068 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-G | 14.3928 | 120.9198 | R | 4989 | 1467 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040152 | FTAP Globe | 14.3465 | 120.9752 | 1.12 | Terrestrial Optical Fiber Drop | 2.35 | 4.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4886 | 5 | 886 | 4886 | 0401018003 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | District III | 13.9586 | 121.1164 | R | 3485 | 968 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040403 | FTAP Globe | 13.9756 | 121.1014 | 1.03 | Terrestrial Optical Fiber Drop | 0.22 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4887 | 5 | 887 | 4887 | 0704603003 | Region VII (Central Visayas) | Negros Oriental | Bacong | Buntis | 9.2473 | 123.2674 | R | 4151 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 3.25 | Terrestrial Optical Fiber Drop | 2.5 | 2.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4888 | 5 | 888 | 4888 | 0600412005 | Region VI (Western Visayas) | Aklan | Malay | Caticlan | 11.9238 | 121.9519 | U | 8476 | 2173 | 652 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060214 | FTAP Globe | 11.9463 | 121.9425 | 2.7 | Terrestrial Optical Fiber Drop | 2.81 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4889 | 5 | 889 | 4889 | 0803726021 | Region VIII (Eastern Visayas) | Leyte | Kananga | Tagaytay | 11.1972 | 124.5371 | R | 3839 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 3.4 | Terrestrial Optical Fiber Drop | 2.98 | 2.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4890 | 5 | 890 | 4890 | 0701219012 | Region VII (Central Visayas) | Bohol | Dauis | Mariveles | 9.6176 | 123.8445 | R | 3847 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0015 | PTCI/MIDC | 9.6184 | 123.8486 | 0.46 | Terrestrial Optical Fiber Drop | 3.23 | 2.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4891 | 5 | 891 | 4891 | 0601902004 | Region VI (Western Visayas) | Capiz | Dao | Balucuan | 11.3758 | 122.6906 | R | 3516 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060243 | FTAP Globe | 11.3433 | 122.6758 | 4.36 | Terrestrial Optical Fiber Drop | 2.22 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4892 | 5 | 892 | 4892 | 0304914005 | Region III (Central Luzon) | Nueva Ecija | Licab | San Casimiro | 15.5519 | 120.7822 | R | 3500 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00668 | Edgepoint | 15.5472 | 120.7645 | 1.97 | Terrestrial Optical Fiber Drop | 2.95 | 2.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4893 | 5 | 893 | 4893 | 0304912027 | Region III (Central Luzon) | Nueva Ecija | Jaen | Santo Tomas North | 15.3693 | 120.9122 | R | 3776 | 1078 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01490-B07 | PTCI/MIDC | 15.3847 | 120.9127 | 1.72 | Terrestrial Optical Fiber Drop | 2.82 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4894 | 5 | 894 | 4894 | 0405645044 | Region IV-A (CALABARZON) | Quezon | Sariaya | Tumbaga 1 | 13.9363 | 121.5299 | R | 4377 | 1151 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03244-C08 | PTCI/MIDC | 13.9415 | 121.5272 | 0.65 | Terrestrial Optical Fiber Drop | 3.04 | 3.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4895 | 5 | 895 | 4895 | 1102401008 | Region XI (Davao Region) | Davao del Sur | Bansalan | Dolo | 6.8076 | 125.1928 | R | 4514 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0144 | PTCI/MIDC | 6.7938 | 125.2038 | 1.96 | Terrestrial Optical Fiber Drop | 2.85 | 19.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4896 | 5 | 896 | 4896 | 0201528010 | Region II (Cagayan Valley) | Cagayan | Tuao | Bulagao | 17.7507 | 121.45 | R | 3867 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCGG0013 | PTCI/MIDC | 17.6716 | 121.5071 | 2.39 | Terrestrial Optical Fiber Drop | 2.16 | 3.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4897 | 5 | 897 | 4897 | 0402102010 | Region IV-A (CALABARZON) | Cavite | Amadeo | Pangil | 14.1991 | 120.9057 | R | 3619 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040250 | FTAP Globe | 14.2029 | 120.9097 | 0.61 | Terrestrial Optical Fiber Drop | 2.85 | 6.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4898 | 5 | 898 | 4898 | 0701233009 | Region VII (Central Visayas) | Bohol | Panglao | Tangnan | 9.6113 | 123.7802 | R | 4093 | 1023 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070188 | FTAP BTS | 9.6142 | 123.7827 | 0.43 | Terrestrial Optical Fiber Drop | 2.87 | 8.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4899 | 5 | 899 | 4899 | 0403424034 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Bautista | 14.0018 | 121.2855 | R | 3516 | 1065 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040386 | FTAP Globe | 14.0007 | 121.283 | 0.3 | Terrestrial Optical Fiber Drop | 2.87 | 4.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4900 | 5 | 900 | 4900 | 0402123009 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Epifanio Malia | 14.3037 | 121.0074 | R | 4369 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03043-C08 | PTCI/MIDC | 14.3183 | 121.0142 | 0.57 | Terrestrial Optical Fiber Drop | 2.43 | 4.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4901 | 5 | 901 | 4901 | 0702234007 | Region VII (Central Visayas) | Cebu | City of Naga | Cogon | 10.2694 | 123.7424 | R | 4759 | 1252 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 1.26 | Terrestrial Optical Fiber Drop | 3.81 | 2.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4902 | 5 | 902 | 4902 | 0301419015 | Region III (Central Luzon) | Bulacan | San Ildefonso | Gabihan | 15.049 | 121.0111 | R | 3866 | 1104 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00908 | Edgepoint | 15.0517 | 121.0062 | 0.61 | Terrestrial Optical Fiber Drop | 2.88 | 7.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4903 | 5 | 903 | 4903 | 0205014002 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Ibung | 16.6067 | 121.1833 | R | 4945 | 1301 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00299 | Edgepoint | 16.6067 | 121.1846 | 0.13 | Terrestrial Optical Fiber Drop | 2.9 | 5.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4904 | 5 | 904 | 4904 | 0304924005 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Luyos | 15.2839 | 120.8482 | R | 4081 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01479-B07 | PTCI/MIDC | 15.2877 | 120.8611 | 1.45 | Terrestrial Optical Fiber Drop | 2.9 | 3.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4905 | 5 | 905 | 4905 | 0401025004 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Bancoro | 13.9095 | 120.9687 | R | 3244 | 901 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040490 | FTAP Globe | 13.9133 | 120.9647 | 0.61 | Terrestrial Optical Fiber Drop | 2.91 | 3.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4906 | 5 | 906 | 4906 | 0301407016 | Region III (Central Luzon) | Bulacan | Calumpit | Meysulao | 14.9079 | 120.7396 | R | 4474 | 1278 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01042 | Edgepoint | 14.9092 | 120.7424 | 0.33 | Terrestrial Optical Fiber Drop | 3.04 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4907 | 5 | 907 | 4907 | 0301416012 | Region III (Central Luzon) | Bulacan | Paombong | San Roque | 14.8319 | 120.7865 | R | 5028 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01152 | Edgepoint | 14.8318 | 120.7889 | 0.26 | Terrestrial Optical Fiber Drop | 2.92 | 3.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4908 | 5 | 908 | 4908 | 0105501003 | Region I (Ilocos Region) | Pangasinan | Agno | Bangan-Oda | 16.1086 | 119.8304 | R | 3638 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-02227 | Edgepoint | 16.1209 | 119.8108 | 2.5 | Terrestrial Optical Fiber Drop | 2.93 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4909 | 5 | 909 | 4909 | 0501608022 | Region V (Bicol Region) | Camarines Norte | Paracale | Poblacion Norte | 14.28 | 122.785 | R | 3842 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050007 | FTAP Globe | 14.2443 | 122.8098 | 2.67 | Terrestrial Optical Fiber Drop | 0.19 | 9.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4910 | 5 | 910 | 4910 | 0403410008 | Region IV-A (CALABARZON) | Laguna | Liliw | Calumpang | 14.2011 | 121.4016 | R | 4088 | 1238 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040248 | FTAP Globe | 14.2076 | 121.3988 | 0.79 | Terrestrial Optical Fiber Drop | 3.17 | 2.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4911 | 5 | 911 | 4911 | 0105535013 | Region I (Ilocos Region) | Pangasinan | San Manuel | San Bonifacio | 16.0919 | 120.6631 | R | 3739 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010132 | FTAP Globe | 16.0994 | 120.6788 | 1.87 | Terrestrial Optical Fiber Drop | 2.97 | 3.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4912 | 5 | 912 | 4912 | 0306912002 | Region III (Central Luzon) | Tarlac | Ramos | Guiteb | 15.669 | 120.6148 | R | 3838 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01789-B07 | PTCI/MIDC | 15.6642 | 120.6204 | 0.8 | Terrestrial Optical Fiber Drop | 2.97 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4913 | 5 | 913 | 4913 | 0702251009 | Region VII (Central Visayas) | Cebu | City of Toledo | Cambang-ug | 10.3483 | 123.7027 | R | 4218 | 1110 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0167 | PTCI/MIDC | 10.3397 | 123.7125 | 1.44 | Terrestrial Optical Fiber Drop | 3.88 | 2.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4914 | 5 | 914 | 4914 | 0402110003 | Region IV-A (CALABARZON) | Cavite | Indang | Banaba Cerca | 14.2146 | 120.8528 | R | 3533 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02220-C08 | PTCI/MIDC | 14.2092 | 120.8664 | 1.59 | Terrestrial Optical Fiber Drop | 2.99 | 7.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4915 | 5 | 915 | 4915 | 0105528004 | Region I (Ilocos Region) | Pangasinan | Mapandan | Baloling | 16.0372 | 120.4571 | R | 4428 | 1230 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01754-B07 | PTCI/MIDC | 16.0252 | 120.453 | 1.41 | Terrestrial Optical Fiber Drop | 2.99 | 5.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4916 | 5 | 916 | 4916 | 1705210012 | MIMAROPA Region | Oriental Mindoro | Pola | Maluanluan | 13.0911 | 121.4217 | R | 3988 | 1022 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170090 | FTAP Globe | 13.0951 | 121.4229 | 0.47 | Terrestrial Optical Fiber Drop | 3.02 | 3.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4917 | 5 | 917 | 4917 | 0105546030 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Palina West | 15.9473 | 120.5458 | R | 3413 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010187 | FTAP Globe | 15.9516 | 120.5577 | 1.37 | Terrestrial Optical Fiber Drop | 3.36 | 1.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4918 | 5 | 918 | 4918 | 0304908014 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santa Cruz | 15.2889 | 120.9796 | R | 4011 | 1146 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02877-B07 | PTCI/MIDC | 15.2959 | 120.9864 | 1.07 | Terrestrial Optical Fiber Drop | 3.04 | 3.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4919 | 5 | 919 | 4919 | 0105532058 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Pagal | 15.95 | 120.3314 | R | 4752 | 1320 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_PNG_0019 | LDIC | 120.3328 | 15.9469 | 0.37 | Terrestrial Optical Fiber Drop | 3.06 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4920 | 5 | 920 | 4920 | 0402106052 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Fatima III | 14.3214 | 120.9794 | R | 3878 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01929-C08 | PTCI/MIDC | 14.3533 | 120.9795 | 0.19 | Terrestrial Optical Fiber Drop | 0.45 | 3.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4921 | 5 | 921 | 4921 | 1102408005 | Region XI (Davao Region) | Davao del Sur | Malalag | Bulacan | 6.5624 | 125.415 | R | 5101 | 1500 | 450 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110153 | FTAP BTS | 6.5862 | 125.4044 | 2.89 | Terrestrial Optical Fiber Drop | 3.08 | 5.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4922 | 5 | 922 | 4922 | 0304921003 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Las Piñas | 15.3729 | 120.9964 | R | 3664 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-02679 | Edgepoint | 15.3677 | 120.9961 | 0.58 | Terrestrial Optical Fiber Drop | 3.08 | 6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4923 | 5 | 923 | 4923 | 1001321019 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Mabuhay | 7.8437 | 125.1373 | R | 4472 | 1176 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100060 | FTAP BTS | 7.8574 | 125.1411 | 1.58 | Terrestrial Optical Fiber Drop | 3.09 | 7.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4924 | 5 | 924 | 4924 | 0301416009 | Region III (Central Luzon) | Bulacan | Paombong | San Isidro I | 14.8368 | 120.78 | R | 3582 | 1023 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-01152 | Edgepoint | 14.8318 | 120.7889 | 1.12 | Terrestrial Optical Fiber Drop | 3.08 | 4.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4925 | 5 | 925 | 4925 | 0304913004 | Region III (Central Luzon) | Nueva Ecija | Laur | Barangay IV | 15.5832 | 121.1785 | R | 3483 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03331-B07 | PTCI/MIDC | 15.5639 | 121.1872 | 1.14 | Terrestrial Optical Fiber Drop | 3.41 | 4.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4926 | 5 | 926 | 4926 | 1130700080 | Region XI (Davao Region) | Davao del Sur | City of Davao | Mudiang | 7.1827 | 125.6215 | R | 4282 | 1259 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110160 | FTAP BTS | 7.1711 | 125.6292 | 1.54 | Terrestrial Optical Fiber Drop | 3.16 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4927 | 5 | 927 | 4927 | 0301409012 | Region III (Central Luzon) | Bulacan | Hagonoy | San Juan | 14.8659 | 120.7422 | R | 3868 | 1105 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01099 | Edgepoint | 14.8626 | 120.7425 | 0.38 | Terrestrial Optical Fiber Drop | 3.13 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4928 | 5 | 928 | 4928 | 0403412012 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Diego | 14.185 | 121.515 | R | 2965 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 3.29 | Terrestrial Optical Fiber Drop | 0.97 | 4.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4929 | 5 | 929 | 4929 | 1001321023 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Pinatilan | 7.8826 | 125.1121 | R | 4074 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 2.47 | Terrestrial Optical Fiber Drop | 3.51 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4930 | 5 | 930 | 4930 | 0304913017 | Region III (Central Luzon) | Nueva Ecija | Laur | San Fernando | 15.5928 | 121.218 | R | 3469 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00650 | Edgepoint | 15.5821 | 121.2232 | 1.31 | Terrestrial Optical Fiber Drop | 3.18 | 7.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4931 | 5 | 931 | 4931 | 0501717007 | Region V (Bicol Region) | Camarines Sur | Lagonoy | Burabod | 13.7281 | 123.551 | R | 4027 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03082-C10 | PTCI/MIDC | 13.7198 | 123.5758 | 2.84 | Terrestrial Optical Fiber Drop | 3.18 | 7.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4932 | 5 | 932 | 4932 | 0601912025 | Region VI (Western Visayas) | Capiz | Pontevedra | Tabuc | 11.4578 | 122.8272 | R | 3964 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCZG0029 | PTCI/MIDC | 11.4484 | 122.8313 | 3.67 | Terrestrial Optical Fiber Drop | 2.35 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4933 | 5 | 933 | 4933 | 0704604023 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Okiot | 9.5952 | 123.153 | R | 3979 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070256 | FTAP Globe | 9.5841 | 123.1354 | 2.29 | Terrestrial Optical Fiber Drop | 3.31 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4934 | 5 | 934 | 4934 | 0105532018 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Bolingit | 15.9567 | 120.3491 | R | 3708 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00508 | Edgepoint | 15.9533 | 120.3474 | 0.42 | Terrestrial Optical Fiber Drop | 3.21 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4935 | 5 | 935 | 4935 | 0301421048 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Lucia | 15.22 | 121.0043 | R | 4186 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00798 | Edgepoint | 15.2201 | 121.0067 | 0.26 | Terrestrial Optical Fiber Drop | 3.22 | 5.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4936 | 5 | 936 | 4936 | 0201519012 | Region II (Cagayan Valley) | Cagayan | Peñablanca | Dodan | 17.6459 | 121.7975 | R | 3900 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0047 | LDIC | 121.7943 | 17.6537 | 0.92 | Terrestrial Optical Fiber Drop | 3.25 | 4.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4937 | 5 | 937 | 4937 | 0604517010 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Nato | 10.314 | 122.9914 | R | 4431 | 1197 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0147 | PTCI/MIDC | 10.2943 | 122.995 | 2.22 | Terrestrial Optical Fiber Drop | 3.23 | 3.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4938 | 5 | 938 | 4938 | 0105532026 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Calomboyan | 15.9447 | 120.3005 | R | 3918 | 1088 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01712-B07 | PTCI/MIDC | 15.9527 | 120.3073 | 1.16 | Terrestrial Optical Fiber Drop | 3.24 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4939 | 5 | 939 | 4939 | 0403408006 | Region IV-A (CALABARZON) | Laguna | Famy | Batuhan | 14.4591 | 121.4508 | R | 3260 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040091 | FTAP Globe | 14.4629 | 121.4693 | 1.36 | Terrestrial Optical Fiber Drop | 2.62 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4940 | 5 | 940 | 4940 | 1600301023 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Santa Irene | 8.7422 | 125.7647 | R | 4577 | 1173 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130083 | FTAP Globe | 8.735 | 125.754 | 1.42 | Terrestrial Optical Fiber Drop | 3.32 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4941 | 5 | 941 | 4941 | 0704618008 | Region VII (Central Visayas) | Negros Oriental | Santa Catalina | Caranoche | 9.3518 | 122.8396 | R | 4497 | 1183 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070261 | FTAP Globe | 9.3612 | 122.8354 | 1.14 | Terrestrial Optical Fiber Drop | 3.29 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4942 | 5 | 942 | 4942 | 0105504021 | Region I (Ilocos Region) | Pangasinan | Alcala | San Vicente | 15.8444 | 120.5094 | R | 4418 | 1227 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00562 | Edgepoint | 15.8454 | 120.5154 | 0.66 | Terrestrial Optical Fiber Drop | 3.32 | 5.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4943 | 5 | 943 | 4943 | 0702211019 | Region VII (Central Visayas) | Cebu | City of Bogo | Nailon | 11.0536 | 124.0378 | U | 6911 | 1818 | 545 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0019 | PTCI/MIDC | 11.0552 | 124.0388 | 0.2 | Terrestrial Optical Fiber Drop | 0.6 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4944 | 5 | 944 | 4944 | 0601914017 | Region VI (Western Visayas) | Capiz | City of Roxas | Barra | 11.5885 | 122.7152 | R | 3057 | 804 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCZG0013 | PTCI/MIDC | 11.5904 | 122.7172 | 0.3 | Terrestrial Optical Fiber Drop | 2.2 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4945 | 5 | 945 | 4945 | 0501706005 | Region V (Bicol Region) | Camarines Sur | Bula | Casugad | 13.4445 | 123.2632 | R | 4271 | 1016 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0013 | PTCI/MIDC | 13.445 | 123.2629 | 0.07 | Terrestrial Optical Fiber Drop | 3.44 | 8.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4946 | 5 | 946 | 4946 | 0501605007 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Luklukan Sur | 14.3065 | 122.7192 | R | 4173 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050004 | FTAP Globe | 14.2889 | 122.6958 | 3.19 | Terrestrial Optical Fiber Drop | 3.44 | 12.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4947 | 5 | 947 | 4947 | 0604531010 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VII | 10.9018 | 123.0764 | R | 3980 | 1075 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060330 | FTAP Globe | 10.875 | 123.0733 | 1.89 | Terrestrial Optical Fiber Drop | 0.36 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4948 | 5 | 948 | 4948 | 0704611006 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Buenavista | 10.1384 | 123.2471 | R | 4658 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0029 | PTCI/MIDC | 10.1381 | 123.2458 | 0.15 | Terrestrial Optical Fiber Drop | 3.57 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4949 | 5 | 949 | 4949 | 0704610003 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Balugo | 9.3079 | 123.2613 | R | 4279 | 1126 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070265 | FTAP Globe | 9.3143 | 123.261 | 0.71 | Terrestrial Optical Fiber Drop | 3.6 | 4.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4950 | 5 | 950 | 4950 | 1630400057 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Lumbocan | 9.009 | 125.5084 | R | 5127 | 1250 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130065 | FTAP Globe | 8.9969 | 125.4871 | 2.7 | Terrestrial Optical Fiber Drop | 3.64 | 5.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4951 | 5 | 951 | 4951 | 0603019010 | Region VI (Western Visayas) | Iloilo | Estancia | Gogo | 11.4768 | 123.1543 | R | 3909 | 1028 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0021 | PTCI/MIDC | 11.4706 | 123.1569 | 0.74 | Terrestrial Optical Fiber Drop | 3.67 | 4.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4952 | 5 | 952 | 4952 | 0730600086 | Region VII (Central Visayas) | Cebu | City of Cebu | To-ong Pardo | 10.3105 | 123.838 | R | 4554 | 1423 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0029 | PTCI/MIDC | 10.2972 | 123.8554 | 2.4 | Terrestrial Optical Fiber Drop | 3.74 | 3.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4953 | 5 | 953 | 4953 | 0704611022 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Malusay | 10.1501 | 123.2772 | R | 3881 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0030 | PTCI/MIDC | 10.1609 | 123.28 | 1.24 | Terrestrial Optical Fiber Drop | 3.93 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4954 | 5 | 954 | 4954 | 0300802014 | Region III (Central Luzon) | Bataan | Bagac | Saysain | 14.5703 | 120.3948 | R | 3623 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0025 | PTCI/MIDC | 14.57 | 120.3975 | 0.29 | Terrestrial Optical Fiber Drop | 3.95 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4955 | 5 | 955 | 4955 | 0702232006 | Region VII (Central Visayas) | Cebu | Minglanilla | Guindaruhan | 10.2674 | 123.7568 | R | 3969 | 1044 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 2.16 | Terrestrial Optical Fiber Drop | 3.88 | 3.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4956 | 5 | 956 | 4956 | 0600603008 | Region VI (Western Visayas) | Antique | Belison | Poblacion | 10.8351 | 121.9636 | R | 4726 | 1211 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAQG0005 | PTCI/MIDC | 10.8444 | 121.9595 | 1.12 | Terrestrial Optical Fiber Drop | 8.56 | 3.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4957 | 5 | 957 | 4957 | 0604502019 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Pacol | 10.4957 | 122.8661 | R | 4605 | 1244 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0140 | PTCI/MIDC | 10.511 | 122.8732 | 1.87 | Terrestrial Optical Fiber Drop | 4.63 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4958 | 5 | 958 | 4958 | 0601914025 | Region VI (Western Visayas) | Capiz | City of Roxas | Culasi | 11.6049 | 122.7101 | U | 8164 | 2148 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCZG0016 | PTCI/MIDC | 11.6045 | 122.7114 | 0.15 | Terrestrial Optical Fiber Drop | 0.53 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4959 | 5 | 959 | 4959 | 0704624014 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Tagbino | 10.3731 | 123.2702 | R | 4249 | 1118 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0018 | PTCI/MIDC | 10.3863 | 123.2275 | 4.9 | Terrestrial Optical Fiber Drop | 4.61 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4960 | 5 | 960 | 4960 | 1230800039 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Olympog | 6.2214 | 125.1943 | R | 4613 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH120317 | FTAP Globe | 6.1971 | 125.1858 | 2.86 | Terrestrial Optical Fiber Drop | 6.15 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4961 | 5 | 961 | 4961 | 0704608004 | Region VII (Central Visayas) | Negros Oriental | City of Canlaon | Linothangan | 10.3866 | 123.1852 | R | 4248 | 1117 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0020 | PTCI/MIDC | 10.3971 | 123.2166 | 3.62 | Terrestrial Optical Fiber Drop | 4.85 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4962 | 5 | 962 | 4962 | 0603010010 | Region VI (Western Visayas) | Iloilo | Bingawan | Poblacion | 11.2325 | 122.5662 | R | 4671 | 1229 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_ILO_0014 | LDIC | 11.2099 | 122.5761 | 2.73 | Terrestrial Optical Fiber Drop | 12.35 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4963 | 5 | 963 | 4963 | 0704624011 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Poblacion | 10.3343 | 123.3267 | R | 5131 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0054 | PTCI/MIDC | 10.3309 | 123.3245 | 0.45 | Terrestrial Optical Fiber Drop | 4.95 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4964 | 5 | 964 | 4964 | 0704615007 | Region VII (Central Visayas) | Negros Oriental | Manjuyod | Campuyo | 9.6646 | 123.1468 | R | 3610 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0035 | PTCI/MIDC | 9.6808 | 123.1499 | 1.83 | Terrestrial Optical Fiber Drop | 8.67 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4965 | 5 | 965 | 4965 | 0604517009 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Masulog | 10.375 | 123.1751 | R | 3995 | 1079 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0019 | PTCI/MIDC | 10.3878 | 123.22 | 5.11 | Terrestrial Optical Fiber Drop | 6.02 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4966 | 5 | 966 | 4966 | 1001321015 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Lumbayao | 7.956 | 125.2598 | R | 4332 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100205 | FTAP Globe | 7.9269 | 125.3286 | 8.24 | Terrestrial Optical Fiber Drop | 6.1 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4967 | 5 | 967 | 4967 | 0603001018 | Region VI (Western Visayas) | Iloilo | Ajuy | Pili | 11.1186 | 123.0131 | R | 3490 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0107 | PTCI/MIDC | 11.0825 | 122.9968 | 4.39 | Terrestrial Optical Fiber Drop | 15.07 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4968 | 5 | 968 | 4968 | 0604502021 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Sagasa | 10.4686 | 122.8933 | R | 5051 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060141 | FTAP BTS | 10.4765 | 122.9317 | 4.28 | Terrestrial Optical Fiber Drop | 7.63 | 1.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4969 | 5 | 969 | 4969 | 0704611007 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Bulado | 10.1912 | 123.2864 | R | 3800 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070251 | FTAP Globe | 10.1913 | 123.2672 | 2.1 | Terrestrial Optical Fiber Drop | 8.61 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4970 | 5 | 970 | 4970 | 0604519013 | Region VI (Western Visayas) | Negros Occidental | Moises Padilla | Magallon Cadre | 10.2853 | 123.0909 | R | 5202 | 1405 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060378 | FTAP Globe | 10.2694 | 123.075 | 2.48 | Terrestrial Optical Fiber Drop | 8.66 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4971 | 5 | 971 | 4971 | 0604516007 | Region VI (Western Visayas) | Negros Occidental | City of La Carlota | Haguimit | 10.4086 | 123.0378 | R | 4719 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0017 | LDIC | 10.4474 | 123.0556 | 6.79 | Terrestrial Optical Fiber Drop | 9.99 | 17.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4972 | 5 | 972 | 4972 | 0604502010 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Caridad | 10.4808 | 122.9097 | R | 4020 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060141 | FTAP BTS | 10.4765 | 122.9317 | 2.45 | Terrestrial Optical Fiber Drop | 9.11 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4973 | 5 | 973 | 4973 | 0604517001 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Biaknabato | 10.3552 | 123.1508 | R | 4309 | 1164 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0019 | PTCI/MIDC | 10.3878 | 123.22 | 8.4 | Terrestrial Optical Fiber Drop | 9.17 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4974 | 5 | 974 | 4974 | 0604519009 | Region VI (Western Visayas) | Negros Occidental | Moises Padilla | Crossing Magallon | 10.2628 | 123.0125 | R | 4375 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060378 | FTAP Globe | 10.2694 | 123.075 | 2.73 | Terrestrial Optical Fiber Drop | 6.47 | 15.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4975 | 5 | 975 | 4975 | 0604519010 | Region VI (Western Visayas) | Negros Occidental | Moises Padilla | Guinpana-an | 10.2969 | 123.1143 | R | 3615 | 977 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060378 | FTAP Globe | 10.2694 | 123.075 | 5.28 | Terrestrial Optical Fiber Drop | 10.61 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4976 | 5 | 976 | 4976 | 0704618001 | Region VII (Central Visayas) | Negros Oriental | Santa Catalina | Alangilan | 9.2761 | 122.8784 | R | 4370 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0043 | PTCI/MIDC | 9.2661 | 122.8786 | 1.1 | Terrestrial Optical Fiber Drop | 12.08 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4977 | 5 | 977 | 4977 | 0603001009 | Region VI (Western Visayas) | Iloilo | Ajuy | Culasi | 11.0762 | 122.9773 | R | 4466 | 1175 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060248 | FTAP Globe | 11.0771 | 122.968 | 1.02 | Terrestrial Optical Fiber Drop | 17.44 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4978 | 5 | 978 | 4978 | 1705914005 | MIMAROPA Region | Romblon | San Jose | Poblacion | 12.0614 | 121.9585 | R | 3879 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170184 | FTAP Globe | 12.0599 | 121.9578 | 0.19 | Terrestrial Optical Fiber Drop | 12.65 | 4.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4979 | 5 | 979 | 4979 | 0803718041 | Region VIII (Eastern Visayas) | Leyte | Dulag | San Jose | 10.9869 | 125.0387 | R | 4662 | 1226 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0021 | PTCI/MIDC | 10.9793 | 125.0367 | 0.87 | Terrestrial Optical Fiber Drop | 13.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4980 | 5 | 980 | 4980 | 0704611004 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Basak | 10.229 | 123.3094 | R | 4405 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0031 | PTCI/MIDC | 10.2181 | 123.3038 | 1.35 | Terrestrial Optical Fiber Drop | 13.34 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4981 | 5 | 981 | 4981 | 1102301008 | Region XI (Davao Region) | Davao del Norte | Asuncion | Cabaywa | 7.565 | 125.7564 | R | 3536 | 955 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTDNG0060 | PTCI/MIDC | 7.5875 | 125.748 | 2.67 | Terrestrial Optical Fiber Drop | 13.5 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4982 | 5 | 982 | 4982 | 1001320010 | Region X (Northern Mindanao) | Bukidnon | Talakag | Indulang | 8.1107 | 124.576 | R | 4939 | 1299 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0041 | PTCI/MIDC | 8.0928 | 124.5782 | 2.01 | Terrestrial Optical Fiber Drop | 14.36 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4983 | 5 | 983 | 4983 | 0600414005 | Region VI (Western Visayas) | Aklan | Nabas | Gibon | 11.8579 | 122.043 | R | 3585 | 919 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060163 | FTAP BTS | 11.821 | 122.1229 | 9.62 | Terrestrial Optical Fiber Drop | 14.59 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4984 | 5 | 984 | 4984 | 1402711003 | Cordillera Administrative Region (CAR) | Ifugao | Asipulo | Camandag | 16.5765 | 121.0149 | R | 4217 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020113 | FTAP Globe | 16.5314 | 121.027 | 5.17 | Terrestrial Optical Fiber Drop | 17.2 | 15.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4985 | 5 | 985 | 4985 | 0600414012 | Region VI (Western Visayas) | Aklan | Nabas | Nagustan | 11.8445 | 122.0581 | R | 3967 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060163 | FTAP BTS | 11.821 | 122.1229 | 7.52 | Terrestrial Optical Fiber Drop | 16.81 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4986 | 5 | 986 | 4986 | 0803701008 | Region VIII (Eastern Visayas) | Leyte | Abuyog | Balocawehay | 10.7113 | 124.9591 | R | 3687 | 970 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080360 | FTAP Globe | 10.6948 | 124.9604 | 1.84 | Terrestrial Optical Fiber Drop | 17.56 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4987 | 5 | 987 | 4987 | 1001318029 | Region X (Northern Mindanao) | Bukidnon | San Fernando | Mabuhay | 7.8957 | 125.3482 | R | 3802 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0038 | PTCI/MIDC | 7.9013 | 125.3457 | 0.68 | Terrestrial Optical Fiber Drop | 17.86 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4988 | 5 | 988 | 4988 | 0803731017 | Region VIII (Eastern Visayas) | Leyte | Mahaplag | Poblacion | 10.6054 | 124.9658 | R | 3741 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080362 | FTAP Globe | 10.6046 | 124.9636 | 0.27 | Terrestrial Optical Fiber Drop | 19.74 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4989 | 5 | 989 | 4989 | 1102305018 | Region XI (Davao Region) | Davao del Norte | Kapalong | Pag-asa | 7.5786 | 125.6915 | R | 3687 | 996 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110407 | FTAP Globe | 7.5844 | 125.706 | 1.73 | Terrestrial Optical Fiber Drop | 19.27 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4990 | 5 | 990 | 4990 | 1001320018 | Region X (Northern Mindanao) | Bukidnon | Talakag | Miarayon | 8.1051 | 124.6013 | R | 3588 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0020 | PTCI/MIDC | 8.0537 | 124.902 | 12.86 | Terrestrial Optical Fiber Drop | 14.72 | 14.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4991 | 5 | 991 | 4991 | 0806417039 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | San Pedro | 10.3895 | 124.9706 | R | 2196 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080363 | FTAP Globe | 10.3953 | 124.9748 | 0.78 | Terrestrial Optical Fiber Drop | 1.34 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4992 | 5 | 992 | 4992 | 1001320029 | Region X (Northern Mindanao) | Bukidnon | Talakag | San Rafael | 8.0475 | 124.6098 | R | 3518 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0041 | PTCI/MIDC | 8.0928 | 124.5782 | 6.11 | Terrestrial Optical Fiber Drop | 21.14 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4993 | 5 | 993 | 4993 | 0806417031 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Zone V | 10.3874 | 124.9802 | U | 4475 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080363 | FTAP Globe | 10.3953 | 124.9748 | 0.27 | Terrestrial Optical Fiber Drop | 32.76 | 21.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4994 | 5 | 994 | 4994 | 0806417027 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Zone I | 10.3875 | 124.9801 | U | 1659 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSLG0096 | PTCI/MIDC | 10.3917 | 124.981 | 0.48 | Terrestrial Optical Fiber Drop | 0.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4995 | 5 | 995 | 4995 | 0806417032 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Rizal | 10.3918 | 124.9821 | R | 1930 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSLG0096 | PTCI/MIDC | 10.3917 | 124.981 | 0.12 | Terrestrial Optical Fiber Drop | 0.64 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4996 | 5 | 996 | 4996 | 0806417044 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | Tampoong | 10.4151 | 124.9934 | R | 2123 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_SOL_0001 | LDIC | 10.3826 | 124.9855 | 0.63 | Terrestrial Optical Fiber Drop | 36.1 | 24.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4997 | 5 | 997 | 4997 | 1001320031 | Region X (Northern Mindanao) | Bukidnon | Talakag | Tikalaan | 8.0331 | 124.6228 | R | 4583 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0041 | PTCI/MIDC | 8.0928 | 124.5782 | 8.25 | Terrestrial Optical Fiber Drop | 22.86 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4998 | 5 | 998 | 4998 | 0806417038 | Region VIII (Eastern Visayas) | Southern Leyte | Sogod | San Miguel | 10.3988 | 124.9852 | R | 1991 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSLG0096 | PTCI/MIDC | 10.3917 | 124.981 | 0.92 | Terrestrial Optical Fiber Drop | 1.45 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-4999 | 5 | 999 | 4999 | 1705302003 | MIMAROPA Region | Palawan | Agutaya | Concepcion | 11.4282 | 120.7762 | R | 4063 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170206 | FTAP Globe | 11.3582 | 120.7244 | 9.61 | Satellite LEO Backhaul (Starlink Business) | 86.04 | 105.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-5000 | 5 | 1000 | 5000 | 1705302002 | MIMAROPA Region | Palawan | Agutaya | Algeciras | 11.4186 | 120.812 | R | 5867 | 1504 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170206 | FTAP Globe | 11.3582 | 120.7244 | 11.67 | Satellite LEO Backhaul (Starlink Business) | 89.47 | 104.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)

## Phase 1 (First 1,000 Sites)
5G FWA Candidate Site Schedule — Batch 1 (Phase 1 Priority — First 1,000 Sites)
Carrier-Grade Candidate Siting Data for Turnkey Bidding (Lots 1, 2, 4, 5) ¦ Band n50 SA Architecture
Site ID | Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Households | Target Subscribers | Carrier Spectrum | Initial BTS | Civil Siting Category | Tower Screening Class | Nearest Tower ID | Nearest TowerCo | Nearest Tower Latitude | Nearest Tower Longitude | Dist to Tower (km) | Transmission Medium | Dist to Node (km) | Dist to Line (km) | Power Arrangement
FWA-SITE-0001 | 1 | 1 | 1 | 0501705020 | Region V (Bicol Region) | Camarines Sur | Buhi | Sagrada Familia | 13.416 | 123.5142 | R | 4566 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.6 | Terrestrial Optical Fiber Drop | 0.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0002 | 1 | 2 | 2 | 0401024016 | Region IV-A (CALABARZON) | Batangas | San Luis | Muzon | 13.8594 | 120.9871 | R | 2280 | 633 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1310 | FTAP Smart | 13.8604 | 120.9908 | 0.42 | Terrestrial Optical Fiber Drop | 0.03 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0003 | 1 | 3 | 3 | 0405803001 | Region IV-A (CALABARZON) | Rizal | Baras | Evangelista | 14.517 | 121.2766 | R | 4064 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00855-A04 | PTCI/MIDC | 14.5166 | 121.2786 | 0.22 | Terrestrial Optical Fiber Drop | 0.03 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0004 | 1 | 4 | 4 | 0401032019 | Region IV-A (CALABARZON) | Batangas | Taysan | Santo Niño | 13.7571 | 121.21 | R | 2588 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040579 | FTAP Globe | 13.7584 | 121.2072 | 0.33 | Terrestrial Optical Fiber Drop | 0.03 | 9.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0005 | 1 | 5 | 5 | 0102933035 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Quirino | 16.937 | 120.4448 | R | 679 | 178 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.5 | Terrestrial Optical Fiber Drop | 0.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0006 | 1 | 6 | 6 | 1030500063 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Puerto | 8.4993 | 124.7484 | U | 13413 | 3725 | 1118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0035 | PTCI/MIDC | 8.4944 | 124.7476 | 0.55 | Terrestrial Optical Fiber Drop | 0.03 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0007 | 1 | 7 | 7 | 0600403019 | Region VI (Western Visayas) | Aklan | Banga | Poblacion | 11.6975 | 122.3674 | U | 1923 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0005 | PTCI/MIDC | 11.6975 | 122.3768 | 1.02 | Terrestrial Optical Fiber Drop | 0.04 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0008 | 1 | 8 | 8 | 0500508037 | Region V (Bicol Region) | Albay | City of Ligao | Paulba | 13.1838 | 123.4585 | R | 2511 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050165 | FTAP Globe | 13.1979 | 123.4637 | 1.66 | Terrestrial Optical Fiber Drop | 0.04 | 9.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0009 | 1 | 9 | 9 | 0701242002 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Booy | 9.6572 | 123.8505 | U | 10128 | 2532 | 760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070149 | FTAP BTS | 9.658 | 123.8482 | 0.27 | Terrestrial Optical Fiber Drop | 0.04 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1004 | 1 | 10 | 10 | 0300804040 | Region III (Central Luzon) | Bataan | Dinalupihan | Santa Isabel | 14.8599 | 120.4714 | U | 2819 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-02568 | Edgepoint | 14.8582 | 120.4764 | 0.57 | Terrestrial Optical Fiber Drop | 0.54 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0011 | 1 | 11 | 11 | 0105521010 | Region I (Ilocos Region) | Pangasinan | Labrador | Uyong | 16.05 | 120.1208 | R | 2852 | 792 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00427 | Edgepoint | 16.053 | 120.1143 | 0.77 | Terrestrial Optical Fiber Drop | 0.05 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0012 | 1 | 12 | 12 | 0401015026 | Region IV-A (CALABARZON) | Batangas | Lobo | Poblacion | 13.6479 | 121.209 | U | 2733 | 759 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040611 | FTAP Globe | 13.6478 | 121.2124 | 0.37 | Terrestrial Optical Fiber Drop | 0.05 | 19.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0013 | 1 | 13 | 13 | 1705210010 | MIMAROPA Region | Oriental Mindoro | Pola | Casiligan | 13.1177 | 121.4251 | R | 1764 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170090 | FTAP Globe | 13.0951 | 121.4229 | 2.52 | Terrestrial Optical Fiber Drop | 0.05 | 6.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0014 | 1 | 14 | 14 | 0304909010 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Mag-asawang Sampaloc | 15.5922 | 121.052 | R | 1355 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0050 | PTCI/MIDC | 15.5844 | 121.051 | 0.87 | Terrestrial Optical Fiber Drop | 0.05 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0015 | 1 | 15 | 15 | 1731500010 | MIMAROPA Region | Palawan | City of Puerto Princesa | Binduyan | 10.0141 | 119.071 | R | 1565 | 422 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170230 | FTAP Globe | 9.9965 | 118.9862 | 9.49 | Terrestrial Optical Fiber Drop | 0.05 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0016 | 1 | 16 | 16 | 0403403003 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Tomas | 14.3113 | 121.0635 | U | 61000 | 18484 | 5545 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.59 | Terrestrial Optical Fiber Drop | 0.06 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0017 | 1 | 17 | 17 | 0300805024 | Region III (Central Luzon) | Bataan | Hermosa | Judge Roman Cruz Sr. | 14.8341 | 120.4884 | R | 4747 | 1318 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0015 | PTCI/MIDC | 14.8323 | 120.4895 | 0.24 | Terrestrial Optical Fiber Drop | 0.06 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0018 | 1 | 18 | 18 | 0307114014 | Region III (Central Luzon) | Zambales | Subic | Mangan-Vaca | 14.8886 | 120.2376 | U | 14223 | 3742 | 1123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01065 | Edgepoint | 14.8869 | 120.2347 | 0.36 | Terrestrial Optical Fiber Drop | 0.06 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0019 | 1 | 19 | 19 | 0600415013 | Region VI (Western Visayas) | Aklan | New Washington | Poblacion | 11.6482 | 122.434 | U | 6291 | 1613 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 4.06 | Terrestrial Optical Fiber Drop | 0.06 | 7.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0020 | 1 | 20 | 20 | 0501707006 | Region V (Bicol Region) | Camarines Sur | Cabusao | New Poblacion | 13.7265 | 123.1135 | R | 1301 | 309 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050057 | FTAP Globe | 13.7244 | 123.1076 | 0.69 | Terrestrial Optical Fiber Drop | 0.06 | 9.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0021 | 1 | 21 | 21 | 0501601025 | Region V (Bicol Region) | Camarines Norte | Basud | San Felipe | 14.0124 | 122.9305 | R | 3833 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03181-C10 | PTCI/MIDC | 14.0036 | 122.9312 | 0.97 | Terrestrial Optical Fiber Drop | 0.06 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0022 | 1 | 22 | 22 | 1606807004 | Region XIII (Caraga) | Surigao del Sur | Carrascal | Baybay | 9.4195 | 125.8877 | R | 1661 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130055 | FTAP Globe | 9.3679 | 125.9511 | 0.22 | Terrestrial Optical Fiber Drop | 8.8 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0023 | 1 | 23 | 23 | 0401027002 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Bihis | 13.8777 | 120.9665 | R | 1597 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040533 | FTAP Globe | 13.8691 | 120.9761 | 1.41 | Terrestrial Optical Fiber Drop | 0.06 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0024 | 1 | 24 | 24 | 0403407003 | Region IV-A (CALABARZON) | Laguna | Cavinti | Bukal | 14.2385 | 121.5444 | R | 1384 | 419 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040203 | FTAP Globe | 14.2731 | 121.546 | 3.85 | Terrestrial Optical Fiber Drop | 0.06 | 10.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0025 | 1 | 25 | 25 | 0304901005 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Bucot | 15.5025 | 120.8716 | U | 5837 | 1667 | 500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01498-B07 | PTCI/MIDC | 15.5018 | 120.8731 | 0.18 | Terrestrial Optical Fiber Drop | 0.07 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1014 | 1 | 26 | 26 | 0307109006 | Region III (Central Luzon) | Zambales | San Antonio | Luna | 14.9491 | 120.0882 | R | 2805 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.11 | Terrestrial Optical Fiber Drop | 0.26 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0027 | 1 | 27 | 27 | 0402101006 | Region IV-A (CALABARZON) | Cavite | Alfonso | Barangay V | 14.1362 | 120.8562 | U | 1543 | 453 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 0.73 | Terrestrial Optical Fiber Drop | 0.07 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0028 | 1 | 28 | 28 | 1600210005 | Region XIII (Caraga) | Agusan del Norte | Santiago | La Paz | 9.267 | 125.5588 | R | 1969 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 0.43 | Terrestrial Optical Fiber Drop | 0.07 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0029 | 1 | 29 | 29 | 0203102020 | Region II (Cagayan Valley) | Isabela | Angadanan | Consular | 16.7878 | 121.7604 | R | 675 | 177 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01319-B06 | PTCI/MIDC | 16.7923 | 121.7648 | 0.68 | Terrestrial Optical Fiber Drop | 0.07 | 4.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0030 | 1 | 30 | 30 | 0307704009 | Region III (Central Luzon) | Aurora | Dinalungan | Simbahan | 16.129 | 121.895 | R | 1295 | 340 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-AUR-02984 | Edgepoint | 16.1187 | 121.8586 | 4.05 | Terrestrial Optical Fiber Drop | 0.07 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0031 | 1 | 31 | 31 | 0201504045 | Region II (Cagayan Valley) | Cagayan | Amulung | Palayag | 17.811 | 121.6759 | R | 1435 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CAG_0004 | LDIC | 17.7947 | 121.6576 | 2.65 | Terrestrial Optical Fiber Drop | 0.07 | 5.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0032 | 1 | 32 | 32 | 0500517032 | Region V (Bicol Region) | Albay | City of Tabaco | Quinastillojan | 13.3411 | 123.6615 | R | 1915 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 3.53 | Terrestrial Optical Fiber Drop | 0.07 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0033 | 1 | 33 | 33 | 1705213007 | MIMAROPA Region | Oriental Mindoro | San Teodoro | Poblacion | 13.4356 | 121.019 | R | 1576 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170052 | FTAP Globe | 13.4328 | 121.0194 | 0.31 | Terrestrial Optical Fiber Drop | 0.07 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0034 | 1 | 34 | 34 | 0506202019 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Norte | 12.8702 | 124.1423 | R | 1751 | 437 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050219 | FTAP Globe | 12.8603 | 124.1471 | 1.22 | Terrestrial Optical Fiber Drop | 0.07 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0035 | 1 | 35 | 35 | 0431200026 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Isabang | 13.9497 | 121.5812 | U | 14084 | 3521 | 1056 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0004 | PTCI/MIDC | 13.9458 | 121.5774 | 0.6 | Terrestrial Optical Fiber Drop | 0.07 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0036 | 1 | 36 | 36 | 1102414018 | Region XI (Davao Region) | Davao del Sur | Sulop | Poblacion | 6.5983 | 125.3439 | U | 8316 | 2445 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0081 | PTCI/MIDC | 6.5956 | 125.3442 | 0.3 | Terrestrial Optical Fiber Drop | 0.07 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0037 | 1 | 37 | 37 | 0201518009 | Region II (Cagayan Valley) | Cagayan | Pamplona | Centro | 18.4648 | 121.3397 | R | 1091 | 279 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00010 | Edgepoint | 18.4669 | 121.339 | 0.24 | Terrestrial Optical Fiber Drop | 0.07 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0038 | 1 | 38 | 38 | 0304904014 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Sur | 15.2632 | 120.8669 | U | 14187 | 4053 | 1216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02448 | Edgepoint | 15.261 | 120.8642 | 0.38 | Terrestrial Optical Fiber Drop | 0.07 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0039 | 1 | 39 | 39 | 0201527003 | Region II (Cagayan Valley) | Cagayan | Solana | Bangag | 17.7087 | 121.6973 | R | 4656 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020031 | FTAP Globe | 17.7126 | 121.6905 | 0.84 | Terrestrial Optical Fiber Drop | 0.07 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0040 | 1 | 40 | 40 | 0401023004 | Region IV-A (CALABARZON) | Batangas | San Juan | Bataan | 13.6957 | 121.4333 | R | 1962 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040597 | FTAP Globe | 13.7212 | 121.4269 | 2.92 | Terrestrial Optical Fiber Drop | 0.07 | 10.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0041 | 1 | 41 | 41 | 0506210006 | Region V (Bicol Region) | Sorsogon | Juban | Buraburan | 12.7757 | 123.9907 | R | 2263 | 565 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050223 | FTAP Globe | 12.7829 | 123.9944 | 0.9 | Terrestrial Optical Fiber Drop | 0.07 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0042 | 1 | 42 | 42 | 1130700126 | Region XI (Davao Region) | Davao del Sur | City of Davao | Toril | 7.0127 | 125.4995 | U | 12895 | 3792 | 1138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0004 | LDIC | 7.0121 | 125.5013 | 0.21 | Terrestrial Optical Fiber Drop | 0.07 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0043 | 1 | 43 | 43 | 1430300008 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Bayan Park West | 16.4073 | 120.5973 | R | 1486 | 391 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02601-B05 | PTCI/MIDC | 16.4118 | 120.6028 | 0.24 | Terrestrial Optical Fiber Drop | 0.59 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0044 | 1 | 44 | 44 | 0105527023 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Cabayaoasan | 15.7697 | 120.3885 | R | 1476 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00578 | Edgepoint | 15.7738 | 120.3905 | 0.51 | Terrestrial Optical Fiber Drop | 0.08 | 6.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0045 | 1 | 45 | 45 | 1403209004 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Apatan | 17.5571 | 121.34 | R | 2121 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | N2029 | FTAP Smart | 17.5707 | 121.3629 | 2.86 | Terrestrial Optical Fiber Drop | 0.08 | 9.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0046 | 1 | 46 | 46 | 1130700026 | Region XI (Davao Region) | Davao del Sur | City of Davao | Calinan | 7.1861 | 125.4555 | U | 25199 | 7411 | 2223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110454 | FTAP Globe | 7.185 | 125.4541 | 0.2 | Terrestrial Optical Fiber Drop | 0.08 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0047 | 1 | 47 | 47 | 0201506035 | Region II (Cagayan Valley) | Cagayan | Baggao | San Jose | 17.8914 | 121.8712 | U | 4663 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01179-B06 | PTCI/MIDC | 17.8906 | 121.8735 | 0.25 | Terrestrial Optical Fiber Drop | 0.08 | 16.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0048 | 1 | 48 | 48 | 0506215005 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion III | 12.6457 | 124.105 | R | 863 | 215 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.55 | Terrestrial Optical Fiber Drop | 0.08 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0049 | 1 | 49 | 49 | 0402104009 | Region IV-A (CALABARZON) | Cavite | Carmona | Mabuhay | 14.3103 | 121.0505 | U | 13384 | 3936 | 1181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040182 | FTAP Globe | 14.3107 | 121.0494 | 0.13 | Terrestrial Optical Fiber Drop | 0.08 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0050 | 1 | 50 | 50 | 0401013004 | Region IV-A (CALABARZON) | Batangas | Lian | Binubusan | 13.9603 | 120.6382 | R | 4668 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040415 | FTAP Globe | 13.9594 | 120.6399 | 0.21 | Terrestrial Optical Fiber Drop | 0.08 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0051 | 1 | 51 | 51 | 0506213005 | Region V (Bicol Region) | Sorsogon | Pilar | Bayasong | 12.9876 | 123.6834 | R | 1768 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050201 | FTAP Globe | 13.0151 | 123.7154 | 4.62 | Terrestrial Optical Fiber Drop | 0.08 | 4.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0052 | 1 | 52 | 52 | 0405607042 | Region IV-A (CALABARZON) | Quezon | Calauag | Lagay | 14.0912 | 122.2153 | R | 731 | 192 | 58 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01941 | Edgepoint | 14.0072 | 122.1816 | 10.02 | Terrestrial Optical Fiber Drop | 0.08 | 14.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1009 | 1 | 53 | 53 | 0500518028 | Region V (Bicol Region) | Albay | Tiwi | Tigbi | 13.4532 | 123.68 | U | 2944 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 0.5 | Terrestrial Optical Fiber Drop | 0.54 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0054 | 1 | 54 | 54 | 1600210010 | Region XIII (Caraga) | Agusan del Norte | Santiago | Estanislao Morgado | 9.2663 | 125.5587 | R | 2114 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 0.38 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0055 | 1 | 55 | 55 | 1402705009 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Nayon | 16.7195 | 121.1718 | R | 1226 | 314 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N2035 | FTAP Smart | 16.7138 | 121.1695 | 0.68 | Terrestrial Optical Fiber Drop | 0.09 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0056 | 1 | 56 | 56 | 1600212001 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | Poblacion I | 9.0535 | 125.5878 | R | 2819 | 687 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 0.3 | Terrestrial Optical Fiber Drop | 0.09 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0057 | 1 | 57 | 57 | 1705201029 | MIMAROPA Region | Oriental Mindoro | Baco | Poblacion | 13.3591 | 121.0953 | R | 2895 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170066 | FTAP Globe | 13.3624 | 121.1001 | 0.63 | Terrestrial Optical Fiber Drop | 0.09 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0058 | 1 | 58 | 58 | 0803726015 | Region VIII (Eastern Visayas) | Leyte | Kananga | Poblacion | 11.1858 | 124.5612 | U | 8692 | 2287 | 686 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 0.82 | Terrestrial Optical Fiber Drop | 0.09 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0059 | 1 | 59 | 59 | 0203124004 | Region II (Cagayan Valley) | Isabela | Ramon | Bugallon Norte | 16.7877 | 121.532 | U | 5967 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00261 | Edgepoint | 16.7869 | 121.528 | 0.43 | Terrestrial Optical Fiber Drop | 0.09 | 10.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0060 | 1 | 60 | 60 | 0704619018 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion I | 9.0622 | 123.0312 | U | 1964 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0045 | PTCI/MIDC | 9.0635 | 123.0334 | 0.28 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0061 | 1 | 61 | 61 | 1401110001 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Alapang | 16.4685 | 120.5985 | U | 5383 | 1538 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C57 | FTAP Smart | 16.463 | 120.5956 | 0.69 | Terrestrial Optical Fiber Drop | 0.09 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1018 | 1 | 62 | 62 | 0304917027 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion North | 15.7205 | 120.904 | R | 2951 | 843 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0180 | FTAP Smart | 15.7184 | 120.9059 | 0.31 | Terrestrial Optical Fiber Drop | 0.55 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0063 | 1 | 63 | 63 | 1600212006 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | San Antonio | 9.0535 | 125.5878 | R | 2351 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 0.3 | Terrestrial Optical Fiber Drop | 0.09 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0064 | 1 | 64 | 64 | 0630200024 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 28 | 10.6661 | 122.952 | U | 1571 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0018 | PTCI/MIDC | 10.6685 | 122.9484 | 0.48 | Terrestrial Optical Fiber Drop | 0.09 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0065 | 1 | 65 | 65 | 0205705004 | Region II (Cagayan Valley) | Quirino | Saguday | Rizal | 16.5446 | 121.5631 | R | 2953 | 757 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01775-B06 | PTCI/MIDC | 16.5455 | 121.5638 | 0.13 | Terrestrial Optical Fiber Drop | 0.09 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0066 | 1 | 66 | 66 | 1004304007 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Poblacion | 8.9186 | 124.7853 | R | 2153 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 3.77 | Terrestrial Optical Fiber Drop | 0.09 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0067 | 1 | 67 | 67 | 0504102020 | Region V (Bicol Region) | Masbate | Baleno | Poblacion | 12.4737 | 123.4955 | R | 4033 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MAS-02159 | Edgepoint | 12.4729 | 123.4959 | 0.1 | Terrestrial Optical Fiber Drop | 0.09 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0068 | 1 | 68 | 68 | 1600205001 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Baleguian | 9.3577 | 125.5537 | R | 2400 | 585 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 10.45 | Terrestrial Optical Fiber Drop | 0.09 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0069 | 1 | 69 | 69 | 0506216001 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Abuyog | 12.9463 | 124.0524 | R | 4670 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 5.7 | Terrestrial Optical Fiber Drop | 0.1 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0070 | 1 | 70 | 70 | 1381300011 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbayan | 14.6078 | 121.0827 | U | 24092 | 6441 | 1932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00524-A02 | PTCI/MIDC | 14.6095 | 121.0826 | 0.19 | Terrestrial Optical Fiber Drop | 0.1 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0071 | 1 | 71 | 71 | 0301419009 | Region III (Central Luzon) | Bulacan | San Ildefonso | Bubulong Malaki | 15.0877 | 120.995 | R | 2300 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-BUL-03129 | Edgepoint | 120.9721 | 15.1005 | 2.84 | Terrestrial Optical Fiber Drop | 0.1 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0072 | 1 | 72 | 72 | 1381300096 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | San Antonio | 14.647 | 121.0164 | U | 22880 | 6320 | 1896 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000211 | FTAP Globe | 14.6464 | 121.0151 | 0.15 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0073 | 1 | 73 | 73 | 0403404006 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Casile | 14.1696 | 121.0193 | U | 3967 | 1202 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02029-C08 | PTCI/MIDC | 14.1661 | 121.0191 | 0.39 | Terrestrial Optical Fiber Drop | 0.1 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0074 | 1 | 74 | 74 | 0301422030 | Region III (Central Luzon) | Bulacan | San Rafael | San Roque | 15.0084 | 120.9324 | U | 10112 | 2889 | 867 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01021-B07 | PTCI/MIDC | 15.0066 | 120.9375 | 0.58 | Terrestrial Optical Fiber Drop | 0.1 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0075 | 1 | 75 | 75 | 0401014058 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Celestino | 13.9174 | 121.2247 | R | 2388 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040486 | FTAP Globe | 13.9189 | 121.2314 | 0.74 | Terrestrial Optical Fiber Drop | 0.1 | 3.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0076 | 1 | 76 | 76 | 1430300029 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | DPS Area | 16.4072 | 120.5974 | R | 958 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140185 | FTAP Globe | 16.4169 | 120.5768 | 0.33 | Terrestrial Optical Fiber Drop | 0.58 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0077 | 1 | 77 | 77 | 0305412019 | Region III (Central Luzon) | Pampanga | Masantol | San Nicolas | 14.8906 | 120.7072 | R | 3980 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.51 | Terrestrial Optical Fiber Drop | 0.1 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0078 | 1 | 78 | 78 | 0304919013 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Atate | 15.5607 | 121.1003 | R | 4297 | 1227 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030154 | FTAP BTS | 15.5656 | 121.0987 | 0.58 | Terrestrial Optical Fiber Drop | 0.04 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0079 | 1 | 79 | 79 | 1430300013 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cabinet Hill-Teacher's Camp | 16.4074 | 120.5971 | U | 3498 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0024 | PTCI/MIDC | 16.4185 | 120.5888 | 0.32 | Terrestrial Optical Fiber Drop | 0.59 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0080 | 1 | 80 | 80 | 0405804027 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pantok | 14.4945 | 121.1801 | U | 16083 | 4467 | 1340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040080 | FTAP Globe | 14.4946 | 121.1826 | 0.27 | Terrestrial Optical Fiber Drop | 0.1 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0081 | 1 | 81 | 81 | 0402102004 | Region IV-A (CALABARZON) | Cavite | Amadeo | Halang | 14.1992 | 120.9319 | R | 2321 | 682 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02223-C08 | PTCI/MIDC | 14.1743 | 120.9201 | 0.45 | Terrestrial Optical Fiber Drop | 3.28 | 3.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0082 | 1 | 82 | 82 | 0405605019 | Region IV-A (CALABARZON) | Quezon | Buenavista | Lilukin | 13.7435 | 122.4591 | R | 1310 | 344 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02789-C10 | PTCI/MIDC | 13.7448 | 122.4555 | 0.42 | Terrestrial Optical Fiber Drop | 0.1 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0083 | 1 | 83 | 83 | 0405603004 | Region IV-A (CALABARZON) | Quezon | Atimonan | Barangay Zone 1 | 14.0003 | 121.9245 | U | 2938 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 0.04 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0084 | 1 | 84 | 84 | 0203123014 | Region II (Cagayan Valley) | Isabela | Quirino | Santa Lucia | 17.1349 | 121.7371 | R | 1899 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ISA-00178 | Edgepoint | 17.1279 | 121.7205 | 1.93 | Terrestrial Optical Fiber Drop | 0.1 | 5.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0085 | 1 | 85 | 85 | 1102407015 | Region XI (Davao Region) | Davao del Sur | Magsaysay | Poblacion | 6.7532 | 125.151 | U | 8011 | 2356 | 707 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110522 | FTAP Globe | 6.7543 | 125.152 | 0.16 | Terrestrial Optical Fiber Drop | 0.1 | 18.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1021 | 1 | 86 | 86 | 0803739025 | Region VIII (Eastern Visayas) | Leyte | Palo | Salvacion | 11.1543 | 124.9981 | R | 2668 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.3 | Terrestrial Optical Fiber Drop | 0.55 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0087 | 1 | 87 | 87 | 0506209002 | Region V (Bicol Region) | Sorsogon | Irosin | Bacolod | 12.7014 | 124.0359 | R | 4737 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 0.11 | Terrestrial Optical Fiber Drop | 0.1 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0088 | 1 | 88 | 88 | 0501734041 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Villazar | 13.8554 | 122.9516 | R | 2067 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 1.45 | Terrestrial Optical Fiber Drop | 0.1 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0089 | 1 | 89 | 89 | 0803733012 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | Talisay | 11.1446 | 124.4718 | R | 628 | 165 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0037 | PTCI/MIDC | 11.1493 | 124.4693 | 0.59 | Terrestrial Optical Fiber Drop | 0.1 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0090 | 1 | 90 | 90 | 0702215007 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Norte | 10.5766 | 124.0181 | R | 4807 | 1265 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 1.18 | Terrestrial Optical Fiber Drop | 0.1 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0091 | 1 | 91 | 91 | 0402123024 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | San Gabriel | 14.2826 | 121.0011 | U | 9168 | 2696 | 809 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.36 | Terrestrial Optical Fiber Drop | 0.11 | 3.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0092 | 1 | 92 | 92 | 0305403025 | Region III (Central Luzon) | Pampanga | Arayat | San Jose Mesulo | 15.1425 | 120.7707 | U | 5717 | 1429 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00850 | Edgepoint | 15.1386 | 120.7722 | 0.47 | Terrestrial Optical Fiber Drop | 0.11 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0093 | 1 | 93 | 93 | 0500512024 | Region V (Bicol Region) | Albay | Oas | Ilaor Norte | 13.2628 | 123.4965 | R | 1480 | 360 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050151 | FTAP Globe | 13.2593 | 123.5008 | 0.6 | Terrestrial Optical Fiber Drop | 0.11 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0094 | 1 | 94 | 94 | 1705318015 | MIMAROPA Region | Palawan | Roxas | Barangay 1 | 10.3169 | 119.345 | U | 5443 | 1395 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 1.52 | Terrestrial Optical Fiber Drop | 0.11 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0095 | 1 | 95 | 95 | 0304905030 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Minuli | 16.0728 | 120.9429 | R | 1949 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH030303 | FTAP Globe | 16.0078 | 120.9617 | 7.5 | Terrestrial Optical Fiber Drop | 0.11 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0096 | 1 | 96 | 96 | 0203103022 | Region II (Cagayan Valley) | Isabela | Aurora | San Andres | 16.9635 | 121.5885 | R | 473 | 124 | 37 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0021 | PTCI/MIDC | 16.9834 | 121.6506 | 0.62 | Terrestrial Optical Fiber Drop | 6.27 | 5.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0097 | 1 | 97 | 97 | 1380300021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Post Proper Northside | 14.5636 | 121.0336 | U | 28506 | 8144 | 2443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03214 | Edgepoint | 14.5544 | 121.022 | 0.09 | Terrestrial Optical Fiber Drop | 0.61 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0098 | 1 | 98 | 98 | 0702241018 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion South | 10.1621 | 123.707 | U | 9150 | 2407 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.75 | Terrestrial Optical Fiber Drop | 0.11 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0099 | 1 | 99 | 99 | 0102906006 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | Bagani Gabor | 17.1881 | 120.4461 | R | 548 | 144 | 43 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILS-00162 | Edgepoint | 17.193 | 120.4425 | 0.37 | Terrestrial Optical Fiber Drop | 0.42 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0100 | 1 | 100 | 100 | 0306906036 | Region III (Central Luzon) | Tarlac | Gerona | San Antonio | 15.5983 | 120.6051 | R | 3323 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01807-B07 | PTCI/MIDC | 15.6057 | 120.6012 | 0.92 | Terrestrial Optical Fiber Drop | 0.11 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0101 | 1 | 101 | 101 | 0306916023 | Region III (Central Luzon) | Tarlac | City of Tarlac | Burot | 15.4141 | 120.6006 | U | 8013 | 2054 | 616 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.26 | Terrestrial Optical Fiber Drop | 0.12 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0102 | 1 | 102 | 102 | 0307113017 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion North | 15.7688 | 119.9092 | R | 3317 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 1.67 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0103 | 1 | 103 | 103 | 0307110005 | Region III (Central Luzon) | Zambales | San Felipe | Feria | 15.0603 | 120.0712 | R | 1146 | 301 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00904 | Edgepoint | 15.0611 | 120.0686 | 0.3 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0104 | 1 | 104 | 104 | 0201527019 | Region II (Cagayan Valley) | Cagayan | Solana | Nangalisan | 17.648 | 121.6734 | U | 2964 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01149-B06 | PTCI/MIDC | 17.646 | 121.678 | 0.53 | Terrestrial Optical Fiber Drop | 0.12 | 3.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0105 | 1 | 105 | 105 | 0403406013 | Region IV-A (CALABARZON) | Laguna | Calauan | Kanluran | 14.147 | 121.3136 | R | 1538 | 466 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040288 | FTAP Globe | 14.1455 | 121.3143 | 0.19 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1022 | 1 | 106 | 106 | 1102315009 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Gredu | 7.2961 | 125.6784 | U | 16525 | 4466 | 1340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110294 | FTAP BTS | 7.2974 | 125.6811 | 0.33 | Terrestrial Optical Fiber Drop | 0.55 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0107 | 1 | 107 | 107 | 0405608008 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Norte | 13.9308 | 121.4386 | U | 12010 | 3160 | 948 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1409 | FTAP Smart | 13.9294 | 121.4292 | 1.03 | Terrestrial Optical Fiber Drop | 0.12 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0108 | 1 | 108 | 108 | 0702234003 | Region VII (Central Visayas) | Cebu | City of Naga | Balirong | 10.2566 | 123.7109 | U | 5268 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 3.11 | Terrestrial Optical Fiber Drop | 0.12 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0109 | 1 | 109 | 109 | 1381500015 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Upper Bicutan | 14.4866 | 121.0475 | U | 47397 | 12706 | 3812 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01879 | Edgepoint | 14.4893 | 121.0471 | 0.31 | Terrestrial Optical Fiber Drop | 0.12 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0110 | 1 | 110 | 110 | 1004312011 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Poblacion | 8.9826 | 124.7938 | R | 2396 | 614 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 0.32 | Terrestrial Optical Fiber Drop | 0.12 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0111 | 1 | 111 | 111 | 0501604008 | Region V (Bicol Region) | Camarines Norte | San Lorenzo Ruiz | Matacong | 14.0361 | 122.8655 | R | 3830 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050028 | FTAP Globe | 14.0401 | 122.876 | 1.21 | Terrestrial Optical Fiber Drop | 0.12 | 7.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0112 | 1 | 112 | 112 | 0201523008 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Palawig | 18.4751 | 122.1519 | R | 3082 | 790 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0080 | LDIC | 122.1517 | 18.4728 | 0.26 | Terrestrial Optical Fiber Drop | 0.12 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0113 | 1 | 113 | 113 | 0431200010 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 7 | 13.9326 | 121.6106 | U | 2240 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02137-C08 | PTCI/MIDC | 13.9336 | 121.6126 | 0.24 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0114 | 1 | 114 | 114 | 1381500017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Wawa | 14.5201 | 121.0736 | U | 15930 | 4002 | 1201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01860 | Edgepoint | 14.5168 | 121.075 | 0.39 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0115 | 1 | 115 | 115 | 0405644001 | Region IV-A (CALABARZON) | Quezon | San Narciso | Abuyon | 13.6223 | 122.519 | U | 4981 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040617 | FTAP Globe | 13.6148 | 122.5239 | 0.99 | Terrestrial Optical Fiber Drop | 0.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0116 | 1 | 116 | 116 | 0304902024 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Sinipit | 15.6246 | 121.1476 | R | 2771 | 791 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.4 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0117 | 1 | 117 | 117 | 1004325010 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Poblacion | 8.9988 | 124.8815 | U | 5516 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0078 | PTCI/MIDC | 8.9948 | 124.8803 | 0.46 | Terrestrial Optical Fiber Drop | 0.12 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0118 | 1 | 118 | 118 | 1102412005 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Inawayan | 6.9552 | 125.472 | U | 8909 | 2620 | 786 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110507 | FTAP Globe | 6.9539 | 125.4714 | 0.16 | Terrestrial Optical Fiber Drop | 0.13 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0119 | 1 | 119 | 119 | 0501601001 | Region V (Bicol Region) | Camarines Norte | Basud | Angas | 14.0459 | 123.0178 | R | 1424 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0015 | PTCI/MIDC | 14.0448 | 123.0232 | 0.6 | Terrestrial Optical Fiber Drop | 0.12 | 6.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0120 | 1 | 120 | 120 | 0403416035 | Region IV-A (CALABARZON) | Laguna | Majayjay | San Miguel | 14.1424 | 121.4711 | R | 4529 | 1372 | 412 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.38 | Terrestrial Optical Fiber Drop | 0.12 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0121 | 1 | 121 | 121 | 0702231015 | Region VII (Central Visayas) | Cebu | Medellin | Tindog | 11.1249 | 124.0119 | U | 4071 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 5.18 | Terrestrial Optical Fiber Drop | 0.13 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0122 | 1 | 122 | 122 | 0403424047 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Francisco | 14.0595 | 121.3284 | U | 16350 | 4954 | 1486 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02002-C08 | PTCI/MIDC | 14.0573 | 121.336 | 0.86 | Terrestrial Optical Fiber Drop | 0.13 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0123 | 1 | 123 | 123 | 1381300062 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Marilag | 14.6255 | 121.0696 | U | 17891 | 4075 | 1223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR- 02351 | Edgepoint | 14.6259 | 121.0671 | 0.27 | Terrestrial Optical Fiber Drop | 0.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0124 | 1 | 124 | 124 | 0500504017 | Region V (Bicol Region) | Albay | Guinobatan | Iraya | 13.1894 | 123.603 | U | 1454 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 0.41 | Terrestrial Optical Fiber Drop | 0.13 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0125 | 1 | 125 | 125 | 0603045011 | Region VI (Western Visayas) | Iloilo | Tigbauan | Barangay 4 | 10.6794 | 122.3823 | R | 1056 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0075 | PTCI/MIDC | 10.674 | 122.3827 | 0.6 | Terrestrial Optical Fiber Drop | 0.13 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0126 | 1 | 126 | 126 | 1001317029 | Region X (Northern Mindanao) | Bukidnon | Quezon | Puntian | 7.6083 | 125.112 | R | 2488 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 0.89 | Terrestrial Optical Fiber Drop | 0.13 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0127 | 1 | 127 | 127 | 0405638008 | Region IV-A (CALABARZON) | Quezon | Real | Maragondon | 14.5336 | 121.5746 | R | 1993 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040059 | FTAP Globe | 14.5404 | 121.5893 | 1.75 | Terrestrial Optical Fiber Drop | 0.13 | 16.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0128 | 1 | 128 | 128 | 0501610019 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Tabugon | 14.0727 | 122.3721 | R | 1844 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050025 | FTAP Globe | 14.0747 | 122.3729 | 0.23 | Terrestrial Optical Fiber Drop | 0.13 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0129 | 1 | 129 | 129 | 0201501010 | Region II (Cagayan Valley) | Cagayan | Abulug | Libertad | 18.3416 | 121.4173 | U | 4010 | 1028 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0039 | LDIC | 121.4092 | 18.3463 | 1 | Terrestrial Optical Fiber Drop | 0.13 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0130 | 1 | 130 | 130 | 0405622007 | Region IV-A (CALABARZON) | Quezon | Lopez | Magsaysay | 13.8871 | 122.261 | R | 4204 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.14 | Terrestrial Optical Fiber Drop | 0.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0131 | 1 | 131 | 131 | 0405618034 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Manlayo | 13.9029 | 122.4511 | R | 1720 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040512 | FTAP Globe | 13.8986 | 122.4538 | 0.56 | Terrestrial Optical Fiber Drop | 0.13 | 11.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0132 | 1 | 132 | 132 | 1004323008 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Poblacion | 8.9556 | 124.7883 | R | 3746 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 0.51 | Terrestrial Optical Fiber Drop | 0.13 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0133 | 1 | 133 | 133 | 0201510006 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Bantay | 18.2484 | 121.6962 | R | 979 | 251 | 75 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02639-B06 | PTCI/MIDC | 18.2633 | 121.6878 | 0.27 | Terrestrial Optical Fiber Drop | 1.61 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0134 | 1 | 134 | 134 | 0203114079 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Centro - San Antonio | 17.0918 | 121.9637 | R | 4798 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01297-B06 | PTCI/MIDC | 17.0916 | 121.9656 | 0.2 | Terrestrial Optical Fiber Drop | 0.13 | 6.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0135 | 1 | 135 | 135 | 0501715028 | Region V (Bicol Region) | Camarines Sur | Goa | San Juan Bautista | 13.6961 | 123.4873 | R | 1297 | 308 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050065 | FTAP Globe | 13.6979 | 123.4893 | 0.29 | Terrestrial Optical Fiber Drop | 0.13 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1024 | 1 | 136 | 136 | 0301411001 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Norte | 14.7743 | 120.944 | U | 11934 | 3409 | 1023 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01039-B07 | PTCI/MIDC | 14.77 | 120.942 | 0.53 | Terrestrial Optical Fiber Drop | 0.55 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0137 | 1 | 137 | 137 | 0403407017 | Region IV-A (CALABARZON) | Laguna | Cavinti | Silangan Talaongan | 14.2793 | 121.5369 | R | 2219 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040203 | FTAP Globe | 14.2731 | 121.546 | 1.2 | Terrestrial Optical Fiber Drop | 0.13 | 7.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0138 | 1 | 138 | 138 | 1030500068 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Taglimao | 8.3939 | 124.5222 | R | 1416 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0005 | PTCI/MIDC | 8.3963 | 124.594 | 7.91 | Terrestrial Optical Fiber Drop | 0.14 | 9.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0139 | 1 | 139 | 139 | 0500517048 | Region V (Bicol Region) | Albay | City of Tabaco | Tagas | 13.3486 | 123.7125 | U | 2241 | 546 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050132 | FTAP Globe | 13.3504 | 123.734 | 0.39 | Terrestrial Optical Fiber Drop | 2.09 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0140 | 1 | 140 | 140 | 0506215003 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Barangay Poblacion I | 12.6445 | 124.1051 | R | 1113 | 278 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050230 | FTAP Globe | 12.6485 | 124.1096 | 0.66 | Terrestrial Optical Fiber Drop | 0.14 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0141 | 1 | 141 | 141 | 0304902028 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Tulay na Bato | 15.6239 | 121.1453 | R | 2497 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.33 | Terrestrial Optical Fiber Drop | 0.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0142 | 1 | 142 | 142 | 0401010006 | Region IV-A (CALABARZON) | Batangas | Ibaan | Coliat | 13.8149 | 121.1279 | R | 4448 | 1235 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040559 | FTAP Globe | 13.8144 | 121.1337 | 0.63 | Terrestrial Optical Fiber Drop | 0.14 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0143 | 1 | 143 | 143 | 0702213015 | Region VII (Central Visayas) | Cebu | Borbon | Poblacion | 10.835 | 124.0258 | U | 5405 | 1422 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070309 | FTAP Globe | 10.8085 | 123.9899 | 4.91 | Terrestrial Optical Fiber Drop | 0.14 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0144 | 1 | 144 | 144 | 1403215014 | Cordillera Administrative Region (CAR) | Kalinga | Tinglayan | Poblacion | 17.265 | 121.149 | R | 861 | 200 | 60 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140135 | FTAP Globe | 17.2657 | 121.1491 | 0.07 | Terrestrial Optical Fiber Drop | 0.14 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0145 | 1 | 145 | 145 | 0731300004 | Region VII (Central Visayas) | Cebu | City of Mandaue | Basak | 10.354 | 123.9499 | U | 11789 | 3368 | 1010 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0214 | PTCI/MIDC | 10.352 | 123.9517 | 0.29 | Terrestrial Optical Fiber Drop | 0.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0146 | 1 | 146 | 146 | 0203101005 | Region II (Cagayan Valley) | Isabela | Alicia | Bagnos | 16.8076 | 121.6285 | R | 2297 | 604 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020090 | FTAP Globe | 16.8028 | 121.6133 | 1.7 | Terrestrial Optical Fiber Drop | 0.14 | 8.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0147 | 1 | 147 | 147 | 1380400008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Hulong Duhat | 14.6768 | 120.9412 | U | 12265 | 3555 | 1067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02466 | Edgepoint | 14.6781 | 120.9407 | 0.16 | Terrestrial Optical Fiber Drop | 0.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0148 | 1 | 148 | 148 | 0730600065 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag II | 10.3011 | 123.8955 | U | 12188 | 3808 | 1142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0050 | PTCI/MIDC | 10.3311 | 123.8977 | 0.16 | Terrestrial Optical Fiber Drop | 0.39 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0149 | 1 | 149 | 149 | 0401017020 | Region IV-A (CALABARZON) | Batangas | Malvar | Santiago | 14.0193 | 121.1631 | U | 8479 | 2355 | 707 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040374 | FTAP Globe | 14.0197 | 121.1546 | 0.92 | Terrestrial Optical Fiber Drop | 0.14 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0150 | 1 | 150 | 150 | 0205706014 | Region II (Cagayan Valley) | Quirino | Nagtipunan | Sangbay | 16.2519 | 121.6655 | R | 1853 | 475 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02909-B06 | PTCI/MIDC | 16.2659 | 121.6494 | 2.31 | Terrestrial Optical Fiber Drop | 0.14 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0151 | 1 | 151 | 151 | 1731500001 | MIMAROPA Region | Palawan | City of Puerto Princesa | Babuyan | 9.981 | 118.9323 | R | 3016 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4626 | FTAP Smart | 9.9824 | 118.9396 | 0.82 | Terrestrial Optical Fiber Drop | 0.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0152 | 1 | 152 | 152 | 0402107013 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Poblacion III | 14.1818 | 120.7994 | U | 1337 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.04 | Terrestrial Optical Fiber Drop | 0.39 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0153 | 1 | 153 | 153 | 0702202006 | Region VII (Central Visayas) | Cebu | Alcoy | Poblacion | 9.7097 | 123.5073 | R | 4032 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 4.56 | Terrestrial Optical Fiber Drop | 0.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0154 | 1 | 154 | 154 | 0401018004 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | District IV | 13.9583 | 121.1158 | R | 1791 | 497 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01964-C08 | PTCI/MIDC | 13.9582 | 121.119 | 0.34 | Terrestrial Optical Fiber Drop | 0.14 | 2.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0155 | 1 | 155 | 155 | 0201514020 | Region II (Cagayan Valley) | Cagayan | Gonzaga | San Jose | 18.3579 | 122.103 | R | 1591 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020009 | FTAP Globe | 18.3493 | 122.0877 | 1.88 | Terrestrial Optical Fiber Drop | 0.15 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0156 | 1 | 156 | 156 | 0305416036 | Region III (Central Luzon) | Pampanga | City of San Fernando | Sindalan | 15.0774 | 120.6418 | U | 15912 | 3978 | 1193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00891 | Edgepoint | 15.0791 | 120.6456 | 0.45 | Terrestrial Optical Fiber Drop | 0.15 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0157 | 1 | 157 | 157 | 0403402002 | Region IV-A (CALABARZON) | Laguna | Bay | Calo | 14.182 | 121.2796 | R | 4494 | 1361 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.39 | Terrestrial Optical Fiber Drop | 0.15 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0158 | 1 | 158 | 158 | 0405802007 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Isidro | 14.6182 | 121.1857 | U | 62732 | 17425 | 5228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01616 | Edgepoint | 14.6173 | 121.1835 | 0.26 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0159 | 1 | 159 | 159 | 1401108013 | Cordillera Administrative Region (CAR) | Benguet | Kapangan | Paykek | 16.5747 | 120.6049 | R | 1528 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140174 | FTAP Globe | 16.5757 | 120.6022 | 0.31 | Terrestrial Optical Fiber Drop | 0.15 | 10.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0160 | 1 | 160 | 160 | 0403404017 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Barangay Uno | 14.2767 | 121.1268 | U | 4045 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02403-C08 | PTCI/MIDC | 14.2496 | 121.129 | 0.48 | Terrestrial Optical Fiber Drop | 1.96 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0161 | 1 | 161 | 161 | 0405808010 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Jose | 14.7456 | 121.1294 | U | 135763 | 37711 | 11313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00832-A04 | PTCI/MIDC | 14.7422 | 121.1314 | 0.44 | Terrestrial Optical Fiber Drop | 0.15 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0162 | 1 | 162 | 162 | 0730600004 | Region VII (Central Visayas) | Cebu | City of Cebu | Babag | 10.3803 | 123.856 | U | 5952 | 1860 | 558 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0266 | PTCI/MIDC | 10.3934 | 123.8485 | 1.68 | Terrestrial Optical Fiber Drop | 0.15 | 6.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0163 | 1 | 163 | 163 | 0504113016 | Region V (Bicol Region) | Masbate | Mobo | Nasunduan | 12.338 | 123.6591 | R | 1402 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.37 | Terrestrial Optical Fiber Drop | 0.15 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0164 | 1 | 164 | 164 | 0401022013 | Region IV-A (CALABARZON) | Batangas | San Jose | Don Luis | 13.8836 | 121.0982 | R | 2162 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1373 | FTAP Smart | 13.8745 | 121.1021 | 0.73 | Terrestrial Optical Fiber Drop | 0.88 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1027 | 1 | 165 | 165 | 0402103008 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Habay I | 14.4487 | 120.9441 | U | 21018 | 6181 | 1854 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0095 | FTAP Smart | 14.4464 | 120.9456 | 0.3 | Terrestrial Optical Fiber Drop | 0.55 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1028 | 1 | 166 | 166 | 0301412015 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Malhacan | 14.7399 | 120.9637 | U | 22515 | 6432 | 1930 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030621 | FTAP Globe | 14.738 | 120.9621 | 0.27 | Terrestrial Optical Fiber Drop | 0.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0167 | 1 | 167 | 167 | 0402118016 | Region IV-A (CALABARZON) | Cavite | Silang | Inchican | 14.2504 | 121.0533 | U | 6206 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040216 | FTAP Globe | 14.2503 | 121.0524 | 0.1 | Terrestrial Optical Fiber Drop | 0.16 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0168 | 1 | 168 | 168 | 0402121009 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I A | 14.2847 | 120.7193 | R | 2010 | 591 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.78 | Terrestrial Optical Fiber Drop | 0.16 | 2.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0169 | 1 | 169 | 169 | 1430300003 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Atok Trail | 16.4075 | 120.5975 | R | 1944 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1746 | FTAP Smart | 16.4044 | 120.5998 | 0.26 | Terrestrial Optical Fiber Drop | 0.61 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0170 | 1 | 170 | 170 | 0402109090 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-B | 14.4265 | 120.9335 | R | 688 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.54 | Terrestrial Optical Fiber Drop | 1.38 | 2.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0171 | 1 | 171 | 171 | 0403420003 | Region IV-A (CALABARZON) | Laguna | Pakil | Burgos | 14.3803 | 121.4778 | R | 2415 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040132 | FTAP Globe | 14.3864 | 121.4768 | 0.7 | Terrestrial Optical Fiber Drop | 0.16 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0172 | 1 | 172 | 172 | 0730600030 | Region VII (Central Visayas) | Cebu | City of Cebu | Guba | 10.4251 | 123.8901 | U | 5739 | 1793 | 538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0058 | PTCI/MIDC | 10.4161 | 123.8716 | 2.25 | Terrestrial Optical Fiber Drop | 0.16 | 4.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0173 | 1 | 173 | 173 | 0304911011 | Region III (Central Luzon) | Nueva Ecija | Guimba | Bulakid | 15.6577 | 120.7602 | R | 607 | 173 | 52 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00616 | Edgepoint | 15.6577 | 120.7688 | 0.07 | Terrestrial Optical Fiber Drop | 0.7 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0174 | 1 | 174 | 174 | 0501723030 | Region V (Bicol Region) | Camarines Sur | Nabua | San Miguel | 13.4043 | 123.3749 | U | 1706 | 406 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02601 | Edgepoint | 13.4058 | 123.3723 | 0.34 | Terrestrial Optical Fiber Drop | 0.16 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0175 | 1 | 175 | 175 | 0600416016 | Region VI (Western Visayas) | Aklan | Numancia | Poblacion | 11.7047 | 122.3274 | R | 1829 | 468 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0012 | PTCI/MIDC | 11.7264 | 122.3458 | 3.13 | Terrestrial Optical Fiber Drop | 0.16 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0176 | 1 | 176 | 176 | 0702243013 | Region VII (Central Visayas) | Cebu | San Remigio | Kinawahan | 10.9472 | 123.9205 | R | 1225 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0148 | PTCI/MIDC | 10.9719 | 123.9357 | 3.21 | Terrestrial Optical Fiber Drop | 0.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0177 | 1 | 177 | 177 | 0405601006 | Region IV-A (CALABARZON) | Quezon | Agdangan | Kanlurang Maligaya | 13.8603 | 121.9375 | R | 278 | 73 | 22 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.56 | Terrestrial Optical Fiber Drop | 2.82 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0178 | 1 | 178 | 178 | 0403415002 | Region IV-A (CALABARZON) | Laguna | Magdalena | Malaking Ambling | 14.1973 | 121.4298 | R | 813 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.49 | Terrestrial Optical Fiber Drop | 0.16 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0179 | 1 | 179 | 179 | 0403421008 | Region IV-A (CALABARZON) | Laguna | Pangil | Sulib | 14.4049 | 121.4638 | U | 7425 | 2250 | 675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.15 | Terrestrial Optical Fiber Drop | 0.16 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0180 | 1 | 180 | 180 | 0501724008 | Region V (Bicol Region) | Camarines Sur | City of Naga | Carolina | 13.6641 | 123.2877 | U | 6854 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050070 | FTAP Globe | 13.6634 | 123.2777 | 1.07 | Terrestrial Optical Fiber Drop | 0.16 | 6.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0181 | 1 | 181 | 181 | 0405811011 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid II | 14.6871 | 121.1147 | U | 4458 | 1238 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 6564 | FTAP Smart | 14.6857 | 121.1157 | 0.19 | Terrestrial Optical Fiber Drop | 0.16 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0182 | 1 | 182 | 182 | 0702250016 | Region VII (Central Visayas) | Cebu | City of Talisay | Tabunoc | 10.2634 | 123.8406 | U | 17918 | 4715 | 1415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 0.62 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0183 | 1 | 183 | 183 | 0203130002 | Region II (Cagayan Valley) | Isabela | San Manuel | Babanuang | 17.0502 | 121.6282 | R | 3136 | 825 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0053 | LDIC | 121.6307 | 17.0461 | 0.54 | Terrestrial Optical Fiber Drop | 0.16 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0184 | 1 | 184 | 184 | 0306916015 | Region III (Central Luzon) | Tarlac | City of Tarlac | Baras-baras | 15.5181 | 120.5652 | U | 5396 | 1383 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00679 | Edgepoint | 15.5236 | 120.5602 | 0.81 | Terrestrial Optical Fiber Drop | 0.16 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0185 | 1 | 185 | 185 | 0102916017 | Region I (Ilocos Region) | Ilocos Sur | Salcedo | Poblacion Norte | 17.1512 | 120.5377 | R | 927 | 243 | 73 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ILS-00172 | Edgepoint | 17.1492 | 120.5195 | 1.95 | Terrestrial Optical Fiber Drop | 0.16 | 9.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0186 | 1 | 186 | 186 | 0405630014 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Ilayang Polo | 13.9304 | 121.7759 | R | 2234 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S0800 | FTAP Smart | 13.9046 | 121.7508 | 3.95 | Terrestrial Optical Fiber Drop | 0.16 | 4.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0187 | 1 | 187 | 187 | 0704624006 | Region VII (Central Visayas) | Negros Oriental | Vallehermoso | Macapso | 10.38 | 123.3322 | R | 1564 | 411 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070250 | FTAP Globe | 10.3733 | 123.3313 | 0.75 | Terrestrial Optical Fiber Drop | 0.16 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0188 | 1 | 188 | 188 | 0105538026 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tebag West | 15.9821 | 120.4599 | U | 2558 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 0.1 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0189 | 1 | 189 | 189 | 0601912026 | Region VI (Western Visayas) | Capiz | Pontevedra | Tacas | 11.4767 | 122.8347 | R | 4684 | 1232 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAP_0003 | LDIC | 11.4838 | 122.8327 | 0.82 | Terrestrial Optical Fiber Drop | 0.16 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0190 | 1 | 190 | 190 | 0402109095 | Region IV-A (CALABARZON) | Cavite | City of Imus | Tanzang Luma III | 14.4152 | 120.9453 | U | 2098 | 617 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000700 | FTAP Globe | 14.4266 | 121.0283 | 0.16 | Terrestrial Optical Fiber Drop | 1.04 | 3.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0191 | 1 | 191 | 191 | 1004326011 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Looc | 8.5943 | 124.7735 | R | 5071 | 1300 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 1.42 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0192 | 1 | 192 | 192 | 0201521012 | Region II (Cagayan Valley) | Cagayan | Rizal | Illuru Norte | 17.8426 | 121.3894 | R | 658 | 182 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020026 | FTAP Globe | 17.832 | 121.4108 | 2.56 | Terrestrial Optical Fiber Drop | 0.16 | 7.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0193 | 1 | 193 | 193 | 0405615013 | Region IV-A (CALABARZON) | Quezon | Dolores | San Mateo | 13.9902 | 121.3873 | R | 1714 | 451 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03164-C08 | PTCI/MIDC | 13.9739 | 121.3789 | 2.02 | Terrestrial Optical Fiber Drop | 0.16 | 5.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0194 | 1 | 194 | 194 | 0203114082 | Region II (Cagayan Valley) | Isabela | City of Ilagan | San Isidro | 17.1668 | 121.9157 | R | 1603 | 421 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0006 | PTCI/MIDC | 17.1681 | 121.9149 | 0.17 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0195 | 1 | 195 | 195 | 0806407066 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Combado | 10.1344 | 124.8288 | U | 5919 | 1443 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.94 | Terrestrial Optical Fiber Drop | 0.17 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0196 | 1 | 196 | 196 | 0307706014 | Region III (Central Luzon) | Aurora | Dipaculao | Lipit | 15.8337 | 121.5344 | R | 794 | 208 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02886-B06 | PTCI/MIDC | 15.8296 | 121.5263 | 0.99 | Terrestrial Optical Fiber Drop | 0.17 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0197 | 1 | 197 | 197 | 0402118023 | Region IV-A (CALABARZON) | Cavite | Silang | Lumil | 14.1828 | 121.0116 | U | 5440 | 1600 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02221-C08 | PTCI/MIDC | 14.1843 | 121.0128 | 0.2 | Terrestrial Optical Fiber Drop | 0.16 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0198 | 1 | 198 | 198 | 0500518020 | Region V (Bicol Region) | Albay | Tiwi | Misibis | 13.509 | 123.6092 | R | 2262 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050113 | FTAP Globe | 13.4889 | 123.6261 | 2.88 | Terrestrial Optical Fiber Drop | 0.17 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0199 | 1 | 199 | 199 | 1400118018 | Cordillera Administrative Region (CAR) | Abra | Pidigan | Suyo | 17.5566 | 120.5643 | R | 694 | 182 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ABR_0005 | LDIC | 17.5493 | 120.5575 | 1.08 | Terrestrial Optical Fiber Drop | 0.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0200 | 1 | 200 | 200 | 1381300089 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Ramon Magsaysay | 14.6616 | 121.0218 | U | 16641 | 4923 | 1477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00539-A01 | PTCI/MIDC | 14.6603 | 121.0204 | 0.2 | Terrestrial Optical Fiber Drop | 0.17 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0201 | 1 | 201 | 201 | 0604528038 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 12 | 10.7394 | 122.9686 | R | 2653 | 717 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060339 | FTAP Globe | 10.7358 | 122.9652 | 0.55 | Terrestrial Optical Fiber Drop | 0.17 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0202 | 1 | 202 | 202 | 0102811016 | Region I (Ilocos Region) | Ilocos Norte | Banna | Marcos | 17.9818 | 120.6554 | R | 1064 | 287 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01214-B05 | PTCI/MIDC | 17.9849 | 120.6531 | 0.42 | Terrestrial Optical Fiber Drop | 0.17 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0203 | 1 | 203 | 203 | 0201508005 | Region II (Cagayan Valley) | Cagayan | Buguey | Centro | 18.2883 | 121.8347 | R | 2315 | 593 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0063 | LDIC | 121.8378 | 18.285 | 0.49 | Terrestrial Optical Fiber Drop | 0.17 | 4.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0204 | 1 | 204 | 204 | 0504112019 | Region V (Bicol Region) | Masbate | Milagros | Poblacion East | 12.2177 | 123.5102 | R | 2648 | 645 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050248 | FTAP Globe | 12.2182 | 123.5128 | 0.29 | Terrestrial Optical Fiber Drop | 0.17 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0205 | 1 | 205 | 205 | 0402106058 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Salitran II | 14.3494 | 120.9406 | U | 12987 | 3819 | 1146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01927-C08 | PTCI/MIDC | 14.3499 | 120.9431 | 0.27 | Terrestrial Optical Fiber Drop | 0.17 | 5.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0206 | 1 | 206 | 206 | 1381300115 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Socorro | 14.6214 | 121.0583 | U | 25177 | 7276 | 2183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01583 | Edgepoint | 14.6241 | 121.0577 | 0.31 | Terrestrial Optical Fiber Drop | 0.17 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0207 | 1 | 207 | 207 | 1401109005 | Cordillera Administrative Region (CAR) | Benguet | Kibungan | Poblacion | 16.697 | 120.6564 | R | 2493 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140172 | FTAP Globe | 16.6933 | 120.6569 | 0.41 | Terrestrial Optical Fiber Drop | 0.17 | 11.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0208 | 1 | 208 | 208 | 0601905013 | Region VI (Western Visayas) | Capiz | Ivisan | Poblacion Norte | 11.5223 | 122.6948 | R | 2776 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060229 | FTAP Globe | 11.5171 | 122.6938 | 0.59 | Terrestrial Optical Fiber Drop | 0.17 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0209 | 1 | 209 | 209 | 1102502012 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Poblacion | 6.962 | 126.0125 | U | 9412 | 2614 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110504 | FTAP Globe | 6.9665 | 126.0107 | 0.53 | Terrestrial Optical Fiber Drop | 0.17 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0210 | 1 | 210 | 210 | 0201522003 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Centro I | 18.559 | 121.2347 | U | 2554 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01125-B05 | PTCI/MIDC | 18.5618 | 121.2361 | 0.35 | Terrestrial Optical Fiber Drop | 0.17 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0211 | 1 | 211 | 211 | 0604526016 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Rizal | 10.8039 | 122.9779 | U | 11084 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0063 | PTCI/MIDC | 10.8009 | 122.9774 | 0.34 | Terrestrial Optical Fiber Drop | 0.17 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0212 | 1 | 212 | 212 | 1403213040 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | New Tanglag | 17.4627 | 121.4264 | R | 1456 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00127 | Edgepoint | 17.4695 | 121.4577 | 3.4 | Terrestrial Optical Fiber Drop | 0.17 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0213 | 1 | 213 | 213 | 0201516021 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Logac | 18.1542 | 121.6091 | R | 2454 | 629 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020015 | FTAP Globe | 18.1593 | 121.6024 | 0.9 | Terrestrial Optical Fiber Drop | 0.18 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0214 | 1 | 214 | 214 | 0405649025 | Region IV-A (CALABARZON) | Quezon | Unisan | F. De Jesus | 13.839 | 121.9777 | R | 2291 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040549 | FTAP Globe | 13.8415 | 121.9735 | 0.52 | Terrestrial Optical Fiber Drop | 0.18 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0215 | 1 | 215 | 215 | 0403423010 | Region IV-A (CALABARZON) | Laguna | Rizal | Talaga | 14.1112 | 121.3913 | R | 2220 | 616 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.45 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0216 | 1 | 216 | 216 | 0401005053 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pinamucan Ibaba | 13.6875 | 121.0623 | R | 1876 | 521 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2244 | FTAP Smart | 13.6816 | 121.0591 | 0.74 | Terrestrial Optical Fiber Drop | 0.18 | 7.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1029 | 1 | 217 | 217 | 0402103029 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban II | 14.4609 | 120.9643 | R | 3451 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03026-C08 | PTCI/MIDC | 14.4623 | 120.9625 | 0.25 | Terrestrial Optical Fiber Drop | 0.55 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0218 | 1 | 218 | 218 | 1408105008 | Cordillera Administrative Region (CAR) | Apayao | Luna | Quirino | 18.3367 | 121.3865 | R | 1484 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CAG_0039 | LDIC | 121.4092 | 18.3463 | 2.63 | Terrestrial Optical Fiber Drop | 0.18 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0219 | 1 | 219 | 219 | 0603009016 | Region VI (Western Visayas) | Iloilo | Batad | Malico | 11.4193 | 123.1092 | R | 463 | 121 | 36 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.43 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0220 | 1 | 220 | 220 | 1404402012 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Mabaay | 16.917 | 120.8873 | R | 1289 | 348 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-MOU-00237 | Edgepoint | 16.8985 | 120.8953 | 2.23 | Terrestrial Optical Fiber Drop | 0.18 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0221 | 1 | 221 | 221 | 1401113004 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Camp 4 | 16.3099 | 120.6163 | U | 7022 | 2006 | 602 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140197 | FTAP Globe | 16.3137 | 120.6188 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 9.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0222 | 1 | 222 | 222 | 0304929017 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Malasin | 15.591 | 120.8782 | U | 2120 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00642 | Edgepoint | 15.5899 | 120.8795 | 0.18 | Terrestrial Optical Fiber Drop | 0.18 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0223 | 1 | 223 | 223 | 0401014010 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Banaybanay | 13.9357 | 121.1185 | U | 13356 | 3710 | 1113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040441 | FTAP Globe | 13.9414 | 121.1139 | 0.81 | Terrestrial Optical Fiber Drop | 0.18 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0224 | 1 | 224 | 224 | 1004308003 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Anakan | 8.8416 | 125.1564 | R | 3773 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100111 | FTAP Globe | 8.8451 | 125.1592 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0225 | 1 | 225 | 225 | 0402121005 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion III | 14.2849 | 120.7186 | R | 1850 | 544 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.95 | Terrestrial Optical Fiber Drop | 0.18 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0226 | 1 | 226 | 226 | 0501606005 | Region V (Bicol Region) | Camarines Norte | Labo | Bagong Silang I | 14.1769 | 122.6252 | R | 3154 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAN-03208 | Edgepoint | 14.1763 | 122.626 | 0.11 | Terrestrial Optical Fiber Drop | 0.19 | 1.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0227 | 1 | 227 | 227 | 0330100027 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Cristo | 15.1425 | 120.5986 | U | 4240 | 1177 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00826 | Edgepoint | 15.1639 | 120.5897 | 0.45 | Terrestrial Optical Fiber Drop | 1.23 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0228 | 1 | 228 | 228 | 0205014009 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Norte | 16.5828 | 121.1891 | R | 3059 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-00302 | Edgepoint | 16.5766 | 121.1908 | 0.72 | Terrestrial Optical Fiber Drop | 0.19 | 5.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0229 | 1 | 229 | 229 | 0205701015 | Region II (Cagayan Valley) | Quirino | Aglipay | Victoria | 16.4379 | 121.6367 | R | 1242 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01774-B06 | PTCI/MIDC | 16.4293 | 121.6392 | 1 | Terrestrial Optical Fiber Drop | 0.19 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0230 | 1 | 230 | 230 | 0306903011 | Region III (Central Luzon) | Tarlac | Camiling | Bobon Caarosipan | 15.6875 | 120.4205 | R | 754 | 193 | 58 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00605 | Edgepoint | 15.6807 | 120.415 | 0.49 | Terrestrial Optical Fiber Drop | 0.6 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0231 | 1 | 231 | 231 | 0401030006 | Region IV-A (CALABARZON) | Batangas | Talisay | Buco | 14.0839 | 120.9969 | R | 1096 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.34 | Terrestrial Optical Fiber Drop | 2.53 | 5.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0232 | 1 | 232 | 232 | 0500516017 | Region V (Bicol Region) | Albay | Santo Domingo | Nagsiya Pob. | 13.2383 | 123.776 | R | 1057 | 257 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.86 | Terrestrial Optical Fiber Drop | 0.19 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0233 | 1 | 233 | 233 | 0401034015 | Region IV-A (CALABARZON) | Batangas | Tuy | Rizal | 14.0217 | 120.7301 | R | 1169 | 324 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.39 | Terrestrial Optical Fiber Drop | 0.19 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0234 | 1 | 234 | 234 | 1130700198 | Region XI (Davao Region) | Davao del Sur | City of Davao | Vicente Hizon Sr. | 7.165 | 125.4713 | U | 11674 | 3433 | 1030 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110474 | FTAP Globe | 7.1148 | 125.6545 | 0.63 | Terrestrial Optical Fiber Drop | 2.96 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0235 | 1 | 235 | 235 | 0306903044 | Region III (Central Luzon) | Tarlac | Camiling | Poblacion B | 15.6889 | 120.4133 | R | 1920 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02715 | Edgepoint | 15.6897 | 120.4131 | 0.09 | Terrestrial Optical Fiber Drop | 0.19 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0236 | 1 | 236 | 236 | 0102821012 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Leandro | 18.1546 | 120.6446 | R | 1287 | 347 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01210-B05 | PTCI/MIDC | 18.156 | 120.6512 | 0.72 | Terrestrial Optical Fiber Drop | 0.19 | 5.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0237 | 1 | 237 | 237 | 0402121001 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion I | 14.285 | 120.7185 | R | 1999 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.7 | Terrestrial Optical Fiber Drop | 0.19 | 2.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0238 | 1 | 238 | 238 | 0500507027 | Region V (Bicol Region) | Albay | Libon | Matara | 13.3008 | 123.438 | R | 854 | 208 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.42 | Terrestrial Optical Fiber Drop | 0.19 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0239 | 1 | 239 | 239 | 0501721002 | Region V (Bicol Region) | Camarines Sur | Milaor | Amparado | 13.5965 | 123.1783 | R | 420 | 100 | 30 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050093 | FTAP Globe | 13.5996 | 123.1749 | 0.5 | Terrestrial Optical Fiber Drop | 0.19 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0240 | 1 | 240 | 240 | 0701205011 | Region VII (Central Visayas) | Bohol | Baclayon | Poblacion | 9.6223 | 123.9117 | R | 1899 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 4.82 | Terrestrial Optical Fiber Drop | 0.19 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0241 | 1 | 241 | 241 | 0402113012 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pantihan II | 14.2431 | 120.7943 | R | 1216 | 357 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040235 | FTAP Globe | 14.2274 | 120.8012 | 1.89 | Terrestrial Optical Fiber Drop | 0.19 | 2.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0242 | 1 | 242 | 242 | 0704603017 | Region VII (Central Visayas) | Negros Oriental | Bacong | South Poblacion | 9.2471 | 123.2958 | R | 1553 | 408 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 2.78 | Terrestrial Optical Fiber Drop | 0.92 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0243 | 1 | 243 | 243 | 0307102018 | Region III (Central Luzon) | Zambales | Cabangan | San Antonio | 15.1609 | 120.0548 | R | 826 | 217 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00822 | Edgepoint | 15.1674 | 120.0507 | 0.84 | Terrestrial Optical Fiber Drop | 0.2 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0244 | 1 | 244 | 244 | 0405601012 | Region IV-A (CALABARZON) | Quezon | Agdangan | Poblacion I | 13.8737 | 121.9146 | R | 1409 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.41 | Terrestrial Optical Fiber Drop | 0.2 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0245 | 1 | 245 | 245 | 1380500013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Highway Hills | 14.5824 | 121.0494 | U | 49455 | 14631 | 4389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000343 | FTAP Globe | 14.5845 | 121.0497 | 0.23 | Terrestrial Optical Fiber Drop | 0.2 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0246 | 1 | 246 | 246 | 0506216035 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Talisay | 12.9683 | 124.0041 | U | 2686 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.15 | Terrestrial Optical Fiber Drop | 0.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0247 | 1 | 247 | 247 | 0402114002 | Region IV-A (CALABARZON) | Cavite | Mendez | Asis I | 14.137 | 120.9007 | R | 3842 | 1130 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02216-C08 | PTCI/MIDC | 14.1324 | 120.9008 | 0.5 | Terrestrial Optical Fiber Drop | 0.2 | 4.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0248 | 1 | 248 | 248 | 0403410016 | Region IV-A (CALABARZON) | Laguna | Liliw | Ibabang Taykin | 14.1345 | 121.4362 | R | 1106 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02121-C08 | PTCI/MIDC | 14.1337 | 121.4379 | 0.21 | Terrestrial Optical Fiber Drop | 0.2 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0249 | 1 | 249 | 249 | 1001304022 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Sur | 7.6777 | 124.9943 | U | 12727 | 3349 | 1005 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 0.88 | Terrestrial Optical Fiber Drop | 0.2 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0250 | 1 | 250 | 250 | 0102811014 | Region I (Ilocos Region) | Ilocos Norte | Banna | Lorenzo | 17.9803 | 120.6584 | R | 757 | 204 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILN_0007 | LDIC | 120.6603 | 17.9829 | 0.34 | Terrestrial Optical Fiber Drop | 0.2 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0251 | 1 | 251 | 251 | 0603047004 | Region VI (Western Visayas) | Iloilo | Zarraga | Dawis Centro | 10.828 | 122.6085 | R | 257 | 67 | 20 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.78 | Terrestrial Optical Fiber Drop | 0.2 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0252 | 1 | 252 | 252 | 1001321010 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Guinoyuran | 7.8949 | 125.0054 | U | 8132 | 2140 | 642 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100208 | FTAP Globe | 7.8969 | 125.0047 | 0.24 | Terrestrial Optical Fiber Drop | 0.2 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0253 | 1 | 253 | 253 | 0702212005 | Region VII (Central Visayas) | Cebu | Boljoon | Poblacion | 9.6253 | 123.4801 | R | 4263 | 1121 | 336 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 12.36 | Terrestrial Optical Fiber Drop | 0.2 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0254 | 1 | 254 | 254 | 0500508032 | Region V (Bicol Region) | Albay | City of Ligao | Nasisi | 13.2591 | 123.5846 | R | 1989 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.46 | Terrestrial Optical Fiber Drop | 0.2 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0255 | 1 | 255 | 255 | 1380400011 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Maysilo | 14.6827 | 120.9617 | U | 10481 | 3003 | 901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00674-A01 | PTCI/MIDC | 14.6831 | 120.9595 | 0.24 | Terrestrial Optical Fiber Drop | 0.2 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0256 | 1 | 256 | 256 | 0402105006 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 13 | 14.4732 | 120.8867 | R | 1750 | 514 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040089 | FTAP Globe | 14.4741 | 120.8882 | 0.2 | Terrestrial Optical Fiber Drop | 0.2 | 4.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0257 | 1 | 257 | 257 | 1705319005 | MIMAROPA Region | Palawan | San Vicente | New Agutaya | 10.5394 | 119.2792 | R | 5179 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02441-C09 | PTCI/MIDC | 10.5366 | 119.2409 | 4.19 | Terrestrial Optical Fiber Drop | 0.2 | 9.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0258 | 1 | 258 | 258 | 0403407006 | Region IV-A (CALABARZON) | Laguna | Cavinti | Duhat | 14.2473 | 121.5011 | R | 2006 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040218 | FTAP Globe | 14.2498 | 121.5044 | 0.45 | Terrestrial Optical Fiber Drop | 0.2 | 5.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0259 | 1 | 259 | 259 | 0403426021 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Norte | 14.2842 | 121.4181 | R | 3016 | 913 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040201 | FTAP Globe | 14.2743 | 121.4075 | 0.64 | Terrestrial Optical Fiber Drop | 0.78 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0260 | 1 | 260 | 260 | 0403402004 | Region IV-A (CALABARZON) | Laguna | Bay | Maitim | 14.1793 | 121.2755 | U | 5105 | 1546 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02363-C08 | PTCI/MIDC | 14.1757 | 121.2709 | 0.64 | Terrestrial Optical Fiber Drop | 0.2 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0261 | 1 | 261 | 261 | 1705212013 | MIMAROPA Region | Oriental Mindoro | Roxas | San Jose | 12.6055 | 121.5526 | R | 3605 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S87 | FTAP Smart | 12.5916 | 121.5236 | 3.5 | Terrestrial Optical Fiber Drop | 0.2 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1038 | 1 | 262 | 262 | 1381300007 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagumbuhay | 14.6253 | 121.0642 | U | 6739 | 1643 | 493 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02529-A01 | PTCI/MIDC | 14.6246 | 121.0657 | 0.18 | Terrestrial Optical Fiber Drop | 0.55 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0263 | 1 | 263 | 263 | 0331400006 | Region III (Central Luzon) | Zambales | City of Olongapo | East Tapinac | 14.8336 | 120.2828 | U | 10127 | 2737 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030589 | FTAP Globe | 14.8335 | 120.2862 | 0.37 | Terrestrial Optical Fiber Drop | 0.2 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0264 | 1 | 264 | 264 | 0803748050 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Santo Niño Pob. | 11.1037 | 125.0208 | U | 3845 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0083 | PTCI/MIDC | 11.1054 | 125.0132 | 0.85 | Terrestrial Optical Fiber Drop | 0.2 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0265 | 1 | 265 | 265 | 0307702019 | Region III (Central Luzon) | Aurora | Casiguran | Bianuan | 16.2056 | 122.0424 | R | 2790 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030301 | FTAP Globe | 16.2078 | 122.0393 | 0.41 | Terrestrial Optical Fiber Drop | 0.2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0266 | 1 | 266 | 266 | 0301404013 | Region III (Central Luzon) | Bulacan | Bocaue | Lolomboy | 14.7794 | 120.9337 | U | 15091 | 4311 | 1293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02495 | Edgepoint | 14.7799 | 120.935 | 0.15 | Terrestrial Optical Fiber Drop | 0.2 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0267 | 1 | 267 | 267 | 0603005018 | Region VI (Western Visayas) | Iloilo | Balasan | Poblacion Sur | 11.4721 | 123.088 | U | 2558 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.31 | Terrestrial Optical Fiber Drop | 0.2 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0268 | 1 | 268 | 268 | 1408102003 | Cordillera Administrative Region (CAR) | Apayao | Conner | Caglayan | 17.7953 | 121.3232 | R | 2435 | 579 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03392-B06 | PTCI/MIDC | 17.7968 | 121.3195 | 0.43 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0269 | 1 | 269 | 269 | 0102812062 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 1, San Lorenzo | 18.2049 | 120.5843 | U | 5541 | 1497 | 449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-03234 | Edgepoint | 18.206 | 120.5863 | 0.24 | Terrestrial Optical Fiber Drop | 0.21 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0270 | 1 | 270 | 270 | 0501734040 | Region V (Bicol Region) | Camarines Sur | Sipocot | South Centro | 13.7639 | 122.9755 | U | 6551 | 1559 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 1.58 | Terrestrial Optical Fiber Drop | 0.21 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0271 | 1 | 271 | 271 | 1400101023 | Cordillera Administrative Region (CAR) | Abra | Bangued | Sao-atan | 17.5972 | 120.6176 | R | 1052 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ABR-03102 | Edgepoint | 120.6153 | 17.5944 | 0.47 | Terrestrial Optical Fiber Drop | 0.53 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0272 | 1 | 272 | 272 | 0301407020 | Region III (Central Luzon) | Bulacan | Calumpit | Pio Cruzcosa | 14.8976 | 120.7645 | U | 4874 | 1392 | 418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01097-B07 | PTCI/MIDC | 14.9017 | 120.7697 | 0.48 | Terrestrial Optical Fiber Drop | 1.04 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0273 | 1 | 273 | 273 | 0105543015 | Region I (Ilocos Region) | Pangasinan | Tayug | Barangay B | 16.0255 | 120.748 | U | 1548 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00445 | Edgepoint | 16.0267 | 120.7436 | 0.49 | Terrestrial Optical Fiber Drop | 0.21 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0274 | 1 | 274 | 274 | 0501608023 | Region V (Bicol Region) | Camarines Norte | Paracale | Poblacion Sur | 14.2801 | 122.7849 | R | 1668 | 417 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.31 | Terrestrial Optical Fiber Drop | 0.21 | 9.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0275 | 1 | 275 | 275 | 0103301004 | Region I (Ilocos Region) | La Union | Agoo | Consolacion | 16.3251 | 120.3695 | U | 1720 | 464 | 139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.47 | Terrestrial Optical Fiber Drop | 0.21 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0276 | 1 | 276 | 276 | 0504101001 | Region V (Bicol Region) | Masbate | Aroroy | Ambolong | 12.5106 | 123.3969 | R | 4642 | 1132 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.07 | Terrestrial Optical Fiber Drop | 0.21 | 4.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0277 | 1 | 277 | 277 | 0401024028 | Region IV-A (CALABARZON) | Batangas | San Luis | Poblacion | 13.8547 | 120.9171 | U | 2396 | 665 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040541 | FTAP Globe | 13.8548 | 120.9176 | 0.06 | Terrestrial Optical Fiber Drop | 0.21 | 4.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0278 | 1 | 278 | 278 | 0403415006 | Region IV-A (CALABARZON) | Laguna | Magdalena | Bucal | 14.2023 | 121.4288 | R | 538 | 163 | 49 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.44 | Terrestrial Optical Fiber Drop | 0.47 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0279 | 1 | 279 | 279 | 0702241013 | Region VII (Central Visayas) | Cebu | San Fernando | Poblacion North | 10.1642 | 123.7078 | R | 4710 | 1239 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.99 | Terrestrial Optical Fiber Drop | 0.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0280 | 1 | 280 | 280 | 0604524001 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Bagonbon | 10.5831 | 123.3983 | U | 6059 | 1637 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0035 | PTCI/MIDC | 10.564 | 123.4683 | 7.95 | Terrestrial Optical Fiber Drop | 0.21 | 7.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0281 | 1 | 281 | 281 | 0105526014 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guilig | 16.0666 | 120.4007 | R | 3480 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.72 | Terrestrial Optical Fiber Drop | 0.21 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0282 | 1 | 282 | 282 | 0604517012 | Region VI (Western Visayas) | Negros Occidental | La Castellana | Robles | 10.3187 | 123.0195 | U | 21507 | 5812 | 1744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060377 | FTAP Globe | 10.3212 | 123.0205 | 0.3 | Terrestrial Optical Fiber Drop | 0.21 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0283 | 1 | 283 | 283 | 1130700040 | Region XI (Davao Region) | Davao del Sur | City of Davao | Daliao | 7.0113 | 125.5014 | U | 22349 | 6573 | 1972 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0004 | LDIC | 7.0121 | 125.5013 | 0.09 | Terrestrial Optical Fiber Drop | 0.21 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0284 | 1 | 284 | 284 | 1381100171 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 171 | 14.5335 | 121.0129 | U | 3492 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02585 | Edgepoint | 14.7527 | 120.954 | 0.23 | Terrestrial Optical Fiber Drop | 1.32 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0285 | 1 | 285 | 285 | 0304930055 | Region III (Central Luzon) | Nueva Ecija | Talavera | Tabacao | 15.5838 | 120.9188 | R | 4856 | 1387 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030351 | FTAP Globe | 15.5879 | 120.9213 | 0.52 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0286 | 1 | 286 | 286 | 0205703003 | Region II (Cagayan Valley) | Quirino | Diffun | Aurora West | 16.5874 | 121.5023 | R | 2574 | 660 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Y51 | FTAP Smart | 16.5918 | 121.5046 | 0.55 | Terrestrial Optical Fiber Drop | 0.21 | 7.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0287 | 1 | 287 | 287 | 0304930035 | Region III (Central Luzon) | Nueva Ecija | Talavera | Maestrang Kikay | 15.5834 | 120.9206 | U | 4291 | 1226 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030351 | FTAP Globe | 15.5879 | 120.9213 | 0.5 | Terrestrial Optical Fiber Drop | 0.21 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0288 | 1 | 288 | 288 | 0731300003 | Region VII (Central Visayas) | Cebu | City of Mandaue | Banilad | 10.3392 | 123.9226 | U | 18404 | 5258 | 1577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0116 | PTCI/MIDC | 10.3371 | 123.9196 | 0.69 | Terrestrial Optical Fiber Drop | 0.15 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0289 | 1 | 289 | 289 | 0402114004 | Region IV-A (CALABARZON) | Cavite | Mendez | Palocpoc I | 14.1281 | 120.8789 | R | 1736 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040294 | FTAP Globe | 14.1367 | 120.8759 | 1.01 | Terrestrial Optical Fiber Drop | 0.21 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0290 | 1 | 290 | 290 | 0203110005 | Region II (Cagayan Valley) | Isabela | Dinapigue | Digumased | 16.5247 | 122.2657 | R | 3023 | 795 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ISA-00314 | Edgepoint | 16.5292 | 122.2595 | 0.83 | Terrestrial Optical Fiber Drop | 0.21 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0291 | 1 | 291 | 291 | 1705211012 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Poblacion | 13.5011 | 120.9545 | U | 5395 | 1383 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170046 | FTAP Globe | 13.5009 | 120.9529 | 0.18 | Terrestrial Optical Fiber Drop | 0.21 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0292 | 1 | 292 | 292 | 0103320007 | Region I (Ilocos Region) | La Union | Tubao | Gonzales | 16.3254 | 120.369 | R | 1918 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.53 | Terrestrial Optical Fiber Drop | 0.21 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0293 | 1 | 293 | 293 | 0403412010 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Antonio | 14.1857 | 121.5062 | R | 3605 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 0.54 | Terrestrial Optical Fiber Drop | 0.21 | 4.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0294 | 1 | 294 | 294 | 1004315005 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Poblacion | 8.5593 | 124.3527 | U | 5423 | 1390 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 0.35 | Terrestrial Optical Fiber Drop | 0.21 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0295 | 1 | 295 | 295 | 1381300009 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Bagong Pag-asa | 14.6631 | 121.0338 | U | 28022 | 7983 | 2395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01451 | Edgepoint | 14.6644 | 121.0318 | 0.25 | Terrestrial Optical Fiber Drop | 0.21 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0296 | 1 | 296 | 296 | 0306905035 | Region III (Central Luzon) | Tarlac | Concepcion | San Nicolas | 15.3261 | 120.6544 | U | 5092 | 1305 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.65 | Terrestrial Optical Fiber Drop | 0.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1041 | 1 | 297 | 297 | 1130700170 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 37-D | 7.0866 | 125.6128 | U | 6005 | 1766 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0025 | PTCI/MIDC | 7.0664 | 125.6152 | 0.36 | Terrestrial Optical Fiber Drop | 0.99 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0298 | 1 | 298 | 298 | 0500507036 | Region V (Bicol Region) | Albay | Libon | Sampongan | 13.2599 | 123.3973 | R | 452 | 110 | 33 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.46 | Terrestrial Optical Fiber Drop | 6.29 | 7.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0299 | 1 | 299 | 299 | 0301410050 | Region III (Central Luzon) | Bulacan | City of Malolos | Santo Rosario | 14.8532 | 120.8177 | U | 7665 | 2190 | 657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01088-B07 | PTCI/MIDC | 14.8537 | 120.8194 | 0.2 | Terrestrial Optical Fiber Drop | 0.22 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0300 | 1 | 300 | 300 | 0504113020 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. II | 12.3386 | 123.658 | R | 2067 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.42 | Terrestrial Optical Fiber Drop | 0.22 | 4.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0301 | 1 | 301 | 301 | 0305406012 | Region III (Central Luzon) | Pampanga | Floridablanca | Fortuna | 14.9828 | 120.5164 | U | 5744 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01555-B07 | PTCI/MIDC | 14.981 | 120.5138 | 0.34 | Terrestrial Optical Fiber Drop | 0.22 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0302 | 1 | 302 | 302 | 0730600081 | Region VII (Central Visayas) | Cebu | City of Cebu | Talamban | 10.3696 | 123.9174 | U | 33422 | 10444 | 3133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0120 | PTCI/MIDC | 10.3627 | 123.9271 | 1.32 | Terrestrial Optical Fiber Drop | 0.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1042 | 1 | 303 | 303 | 0205013013 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Roxas | 16.5178 | 121.1851 | U | 9738 | 2562 | 769 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00317 | Edgepoint | 16.5169 | 121.1814 | 0.41 | Terrestrial Optical Fiber Drop | 0.55 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0304 | 1 | 304 | 304 | 0701216010 | Region VII (Central Visayas) | Bohol | Cortes | Poblacion | 9.7197 | 123.8768 | R | 1352 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070415 | FTAP Globe | 9.7203 | 123.8782 | 0.16 | Terrestrial Optical Fiber Drop | 0.22 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0305 | 1 | 305 | 305 | 0501718060 | Region V (Bicol Region) | Camarines Sur | Libmanan | San Isidro | 13.6723 | 123.0088 | R | 3990 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-02607 | Edgepoint | 13.6871 | 122.9969 | 2.09 | Terrestrial Optical Fiber Drop | 0.22 | 3.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0306 | 1 | 306 | 306 | 0205013012 | Region II (Cagayan Valley) | Nueva Vizcaya | Solano | Quirino | 16.5128 | 121.1825 | U | 7173 | 1887 | 566 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00317 | Edgepoint | 16.5169 | 121.1814 | 0.48 | Terrestrial Optical Fiber Drop | 0.22 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0307 | 1 | 307 | 307 | 0500502019 | Region V (Bicol Region) | Albay | Camalig | Iluluan | 13.1273 | 123.6 | R | 1602 | 390 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050177 | FTAP Globe | 13.1433 | 123.6026 | 1.8 | Terrestrial Optical Fiber Drop | 0.22 | 6.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0308 | 1 | 308 | 308 | 0201520019 | Region II (Cagayan Valley) | Cagayan | Piat | Poblacion II | 17.7925 | 121.4758 | R | 1534 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0059 | LDIC | 121.4784 | 17.7911 | 0.32 | Terrestrial Optical Fiber Drop | 0.22 | 8.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0309 | 1 | 309 | 309 | 1380300013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Magallanes | 14.5635 | 121.0337 | U | 5473 | 1169 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00502-A02 | PTCI/MIDC | 14.5699 | 121.0284 | 0.18 | Terrestrial Optical Fiber Drop | 0.63 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0310 | 1 | 310 | 310 | 0501718006 | Region V (Bicol Region) | Camarines Sur | Libmanan | Bagumbayan | 13.6768 | 123.0323 | U | 1869 | 445 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02607 | Edgepoint | 13.6871 | 122.9969 | 2.14 | Terrestrial Optical Fiber Drop | 2.6 | 2.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0311 | 1 | 311 | 311 | 0405629011 | Region IV-A (CALABARZON) | Quezon | Padre Burgos | Burgos | 13.9171 | 121.8175 | R | 805 | 211 | 63 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040480 | FTAP Globe | 13.9209 | 121.8193 | 0.46 | Terrestrial Optical Fiber Drop | 0.22 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0312 | 1 | 312 | 312 | 0402104016 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 5 | 14.3136 | 121.0539 | R | 560 | 164 | 49 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0044 | PTCI/MIDC | 14.3102 | 121.0334 | 0.7 | Terrestrial Optical Fiber Drop | 0.51 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0313 | 1 | 313 | 313 | 0301422023 | Region III (Central Luzon) | Bulacan | San Rafael | Poblacion | 14.9587 | 120.9685 | U | 1714 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0069 | PTCI/MIDC | 11.1801 | 122.8301 | 0.16 | Terrestrial Optical Fiber Drop | 0.77 | 4.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0314 | 1 | 314 | 314 | 0305417018 | Region III (Central Luzon) | Pampanga | San Luis | Santo Tomas | 15.0408 | 120.7897 | U | 2678 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.11 | Terrestrial Optical Fiber Drop | 0.22 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0315 | 1 | 315 | 315 | 0704603015 | Region VII (Central Visayas) | Negros Oriental | Bacong | Sacsac | 9.2547 | 123.2901 | R | 4372 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 2.42 | Terrestrial Optical Fiber Drop | 0.23 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0316 | 1 | 316 | 316 | 0803739014 | Region VIII (Eastern Visayas) | Leyte | Palo | Cogon | 11.148 | 124.9998 | R | 3047 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.88 | Terrestrial Optical Fiber Drop | 0.23 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0317 | 1 | 317 | 317 | 0307108015 | Region III (Central Luzon) | Zambales | Palauig | West Poblacion | 15.4341 | 119.9049 | R | 1240 | 326 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00729 | Edgepoint | 15.4369 | 119.9033 | 0.36 | Terrestrial Optical Fiber Drop | 0.23 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0318 | 1 | 318 | 318 | 0105531035 | Region I (Ilocos Region) | Pangasinan | Rosales | Carmay East | 15.8959 | 120.6322 | U | 3147 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00540 | Edgepoint | 15.8985 | 120.6329 | 0.3 | Terrestrial Optical Fiber Drop | 0.23 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0319 | 1 | 319 | 319 | 0331400015 | Region III (Central Luzon) | Zambales | City of Olongapo | New Ilalim | 14.835 | 120.2793 | R | 1589 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3883 | FTAP Smart | 14.8372 | 120.2825 | 0.42 | Terrestrial Optical Fiber Drop | 0.23 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0320 | 1 | 320 | 320 | 1380400001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Acacia | 14.6675 | 120.9689 | U | 4965 | 1299 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0025 | PTCI/MIDC | 14.667 | 120.9688 | 0.05 | Terrestrial Optical Fiber Drop | 0.23 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0321 | 1 | 321 | 321 | 0307105009 | Region III (Central Luzon) | Zambales | Iba | Zone 1 Pob. | 15.3285 | 119.9763 | U | 2520 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.46 | Terrestrial Optical Fiber Drop | 0.23 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0322 | 1 | 322 | 322 | 0304920012 | Region III (Central Luzon) | Nueva Ecija | Pantabangan | Poblacion East | 15.8056 | 121.1447 | R | 4095 | 1170 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01421-B07 | PTCI/MIDC | 15.8043 | 121.149 | 0.48 | Terrestrial Optical Fiber Drop | 0.23 | 10.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0323 | 1 | 323 | 323 | 0501734038 | Region V (Bicol Region) | Camarines Sur | Sipocot | San Vicente | 13.7641 | 122.9755 | R | 1166 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 1.56 | Terrestrial Optical Fiber Drop | 0.23 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0324 | 1 | 324 | 324 | 0105506017 | Region I (Ilocos Region) | Pangasinan | Asingan | Poblacion West | 16.0031 | 120.6693 | U | 1558 | 432 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.84 | Terrestrial Optical Fiber Drop | 0.23 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0325 | 1 | 325 | 325 | 0301421051 | Region III (Central Luzon) | Bulacan | San Miguel | Sapang | 15.1922 | 120.9908 | R | 2087 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01047-B07 | PTCI/MIDC | 15.1819 | 120.9951 | 1.24 | Terrestrial Optical Fiber Drop | 0.23 | 2.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0326 | 1 | 326 | 326 | 0600415014 | Region VI (Western Visayas) | Aklan | New Washington | Polo | 11.65 | 122.4341 | R | 3752 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.92 | Terrestrial Optical Fiber Drop | 0.23 | 7.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0327 | 1 | 327 | 327 | 0501610009 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Santa Elena | 14.1821 | 122.3932 | U | 9627 | 2406 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050008 | FTAP Globe | 14.218 | 122.3945 | 3.99 | Terrestrial Optical Fiber Drop | 0.23 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0328 | 1 | 328 | 328 | 0305413005 | Region III (Central Luzon) | Pampanga | Mexico | Camuning | 15.1151 | 120.6645 | R | 3008 | 752 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00867 | Edgepoint | 15.1183 | 120.6573 | 0.86 | Terrestrial Optical Fiber Drop | 0.23 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0329 | 1 | 329 | 329 | 0504111020 | Region V (Bicol Region) | Masbate | City of Masbate | Kinamaligan | 12.359 | 123.6184 | U | 5390 | 1314 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03057-C10 | PTCI/MIDC | 12.3584 | 123.6151 | 0.36 | Terrestrial Optical Fiber Drop | 0.23 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0330 | 1 | 330 | 330 | 1401105001 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Abatan | 16.8037 | 120.8233 | U | 3644 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 0.88 | Terrestrial Optical Fiber Drop | 0.23 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0331 | 1 | 331 | 331 | 0103309006 | Region I (Ilocos Region) | La Union | Caba | Poblacion Norte | 16.4312 | 120.3457 | R | 1350 | 364 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.29 | Terrestrial Optical Fiber Drop | 0.23 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0332 | 1 | 332 | 332 | 0405801009 | Region IV-A (CALABARZON) | Rizal | Angono | San Isidro | 14.5295 | 121.1543 | U | 32767 | 9101 | 2730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02296-A04 | PTCI/MIDC | 14.5283 | 121.1526 | 0.23 | Terrestrial Optical Fiber Drop | 0.23 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0333 | 1 | 333 | 333 | 1705320018 | MIMAROPA Region | Palawan | Taytay | Pancol | 10.8707 | 119.4166 | R | 3530 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170216 | FTAP Globe | 10.8254 | 119.4866 | 9.16 | Terrestrial Optical Fiber Drop | 0.23 | 10.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0334 | 1 | 334 | 334 | 0201516003 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Bagumbayan | 18.1935 | 121.6635 | R | 2142 | 549 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.19 | Terrestrial Optical Fiber Drop | 0.23 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0335 | 1 | 335 | 335 | 0601909036 | Region VI (Western Visayas) | Capiz | Panay | Poblacion Ilawod | 11.5575 | 122.7967 | R | 520 | 136 | 41 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060227 | FTAP Globe | 11.5586 | 122.7957 | 0.16 | Terrestrial Optical Fiber Drop | 0.24 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0336 | 1 | 336 | 336 | 0603034020 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion East | 10.6914 | 122.4787 | R | 4302 | 1132 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060007 | FTAP BTS | 10.6921 | 122.4753 | 0.39 | Terrestrial Optical Fiber Drop | 0.24 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0337 | 1 | 337 | 337 | 0702223031 | Region VII (Central Visayas) | Cebu | Danao City | Poblacion | 10.5202 | 124.0277 | U | 9928 | 2612 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.36 | Terrestrial Optical Fiber Drop | 0.24 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0338 | 1 | 338 | 338 | 0203127008 | Region II (Cagayan Valley) | Isabela | San Agustin | Masaya Centro | 16.509 | 121.7457 | R | 1576 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01360-B06 | PTCI/MIDC | 16.5141 | 121.7471 | 0.59 | Terrestrial Optical Fiber Drop | 0.24 | 13.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0339 | 1 | 339 | 339 | 1381200014 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Palatiw | 14.5646 | 121.083 | U | 28185 | 7961 | 2388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02350 | Edgepoint | 14.5651 | 121.0814 | 0.18 | Terrestrial Optical Fiber Drop | 0.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0340 | 1 | 340 | 340 | 0702233011 | Region VII (Central Visayas) | Cebu | Moalboal | Poblacion West | 9.939 | 123.3927 | R | 3648 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 1.76 | Terrestrial Optical Fiber Drop | 0.24 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0341 | 1 | 341 | 341 | 0405644013 | Region IV-A (CALABARZON) | Quezon | San Narciso | Pagkakaisa | 13.5679 | 122.5541 | R | 1456 | 383 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040621 | FTAP Globe | 13.5669 | 122.5556 | 0.2 | Terrestrial Optical Fiber Drop | 0.24 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0342 | 1 | 342 | 342 | 0203112036 | Region II (Cagayan Valley) | Isabela | Echague | Pangal Norte | 16.6102 | 121.6771 | R | 1617 | 425 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0023 | LDIC | 121.6823 | 16.6043 | 0.86 | Terrestrial Optical Fiber Drop | 0.24 | 10.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0343 | 1 | 343 | 343 | 1004314008 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Poblacion | 8.5755 | 124.445 | U | 3866 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 0.59 | Terrestrial Optical Fiber Drop | 0.24 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0344 | 1 | 344 | 344 | 1004304005 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Mosangot | 8.9157 | 124.7852 | R | 1418 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 4.1 | Terrestrial Optical Fiber Drop | 0.24 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0345 | 1 | 345 | 345 | 0604524015 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay VI | 10.4802 | 123.4187 | U | 5619 | 1518 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0058 | PTCI/MIDC | 10.4822 | 123.4207 | 0.3 | Terrestrial Optical Fiber Drop | 0.24 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0346 | 1 | 346 | 346 | 0501612014 | Region V (Bicol Region) | Camarines Norte | Vinzons | Barangay I | 14.1757 | 122.909 | R | 2130 | 532 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050015 | FTAP Globe | 14.1707 | 122.912 | 0.64 | Terrestrial Optical Fiber Drop | 0.24 | 3.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0347 | 1 | 347 | 347 | 0405639017 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Isidro | 14.1633 | 121.6399 | R | 1556 | 409 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.18 | Terrestrial Optical Fiber Drop | 0.24 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0348 | 1 | 348 | 348 | 0304923027 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion Norte | 15.7131 | 121.1036 | R | 3213 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 0.66 | Terrestrial Optical Fiber Drop | 0.24 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0349 | 1 | 349 | 349 | 0803750004 | Region VIII (Eastern Visayas) | Leyte | Tunga | San Antonio | 11.2466 | 124.7503 | R | 873 | 229 | 69 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 0.15 | Terrestrial Optical Fiber Drop | 0.24 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0350 | 1 | 350 | 350 | 1600204011 | Region XIII (Caraga) | Agusan del Norte | Carmen | San Agustin | 9.0564 | 125.2236 | R | 1323 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0064 | PTCI/MIDC | 9.059 | 125.1954 | 3.11 | Terrestrial Optical Fiber Drop | 0.24 | 5.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0351 | 1 | 351 | 351 | 0105523008 | Region I (Ilocos Region) | Pangasinan | Mabini | Calzada | 16.0826 | 119.9275 | R | 1899 | 527 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00410 | Edgepoint | 16.0915 | 119.94 | 1.66 | Terrestrial Optical Fiber Drop | 0.24 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0352 | 1 | 352 | 352 | 1600312006 | Region XIII (Caraga) | Agusan del Sur | Trento | Poblacion | 8.0475 | 126.0633 | U | 18953 | 4859 | 1458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130103 | FTAP Globe | 8.0454 | 126.064 | 0.25 | Terrestrial Optical Fiber Drop | 0.24 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0353 | 1 | 353 | 353 | 0501709013 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Roque | 13.6207 | 123.1741 | U | 3091 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.36 | Terrestrial Optical Fiber Drop | 0.24 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0354 | 1 | 354 | 354 | 0403422004 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Norte | 14.2349 | 121.3655 | R | 2537 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.51 | Terrestrial Optical Fiber Drop | 0.24 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0355 | 1 | 355 | 355 | 1030500003 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bulua | 8.5029 | 124.6167 | U | 36039 | 10010 | 3003 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100050 | FTAP BTS | 8.5056 | 124.6153 | 0.33 | Terrestrial Optical Fiber Drop | 0.24 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0356 | 1 | 356 | 356 | 0831600108 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 77 | 11.2111 | 125.0077 | U | 3726 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0066 | PTCI/MIDC | 11.2106 | 125.008 | 0.06 | Terrestrial Optical Fiber Drop | 0.24 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0357 | 1 | 357 | 357 | 0304906023 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VI | 15.7792 | 120.6621 | R | 1936 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0032 | PTCI/MIDC | 15.7841 | 120.6581 | 0.69 | Terrestrial Optical Fiber Drop | 0.24 | 6.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0358 | 1 | 358 | 358 | 1600205011 | Region XIII (Caraga) | Agusan del Norte | Jabonga | Poblacion | 9.3486 | 125.5078 | R | 4175 | 1018 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 9.97 | Terrestrial Optical Fiber Drop | 1.03 | 4.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0359 | 1 | 359 | 359 | 0405802004 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Mayamot | 14.6297 | 121.1209 | U | 50271 | 13964 | 4189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02986-A04 | PTCI/MIDC | 14.6287 | 121.1229 | 0.24 | Terrestrial Optical Fiber Drop | 0.24 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0360 | 1 | 360 | 360 | 0803703015 | Region VIII (Eastern Visayas) | Leyte | Albuera | Tabgas | 10.8976 | 124.7081 | R | 3171 | 834 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080133 | FTAP BTS | 10.901 | 124.7063 | 0.42 | Terrestrial Optical Fiber Drop | 0.24 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0361 | 1 | 361 | 361 | 1004307012 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Poblacion | 8.557 | 124.5216 | U | 8953 | 2295 | 689 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100124 (FTAP_GLO_PH100124) | FTAP Globe | 8.5545 | 124.5256 | 0.52 | Terrestrial Optical Fiber Drop | 0.24 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0362 | 1 | 362 | 362 | 0604531008 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay V | 10.902 | 123.0753 | R | 1805 | 487 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.48 | Terrestrial Optical Fiber Drop | 0.25 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0363 | 1 | 363 | 363 | 0501706008 | Region V (Bicol Region) | Camarines Sur | Bula | Inoyonan | 13.4698 | 123.2772 | R | 1302 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.29 | Terrestrial Optical Fiber Drop | 0.25 | 5.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0364 | 1 | 364 | 364 | 0401014041 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 10 | 13.9422 | 121.1574 | R | 3085 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040434 | FTAP Globe | 13.9453 | 121.1715 | 0.37 | Terrestrial Optical Fiber Drop | 1 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0365 | 1 | 365 | 365 | 0500511010 | Region V (Bicol Region) | Albay | Manito | It-Ba | 13.1261 | 123.8698 | R | 3750 | 914 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050186 | FTAP Globe | 13.1258 | 123.8679 | 0.2 | Terrestrial Optical Fiber Drop | 0.25 | 12.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0366 | 1 | 366 | 366 | 1600208001 | Region XIII (Caraga) | Agusan del Norte | Magallanes | Buhang | 9.0354 | 125.525 | R | 4178 | 1019 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130065 | FTAP Globe | 8.9969 | 125.4871 | 5.98 | Terrestrial Optical Fiber Drop | 0.25 | 7.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0367 | 1 | 367 | 367 | 0500507016 | Region V (Bicol Region) | Albay | Libon | Caguscos | 13.2311 | 123.3303 | R | 1034 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050168 | FTAP Globe | 13.1892 | 123.3257 | 4.69 | Terrestrial Optical Fiber Drop | 0.25 | 14.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0368 | 1 | 368 | 368 | 0500516012 | Region V (Bicol Region) | Albay | Santo Domingo | San Rafael Pob. | 13.2367 | 123.7794 | R | 554 | 135 | 41 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 1.23 | Terrestrial Optical Fiber Drop | 0.25 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0369 | 1 | 369 | 369 | 0203105007 | Region II (Cagayan Valley) | Isabela | Burgos | Cullalabo San Antonio | 17.0888 | 121.7049 | R | 3513 | 924 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0027 | LDIC | 121.7027 | 17.0894 | 0.24 | Terrestrial Optical Fiber Drop | 0.25 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0370 | 1 | 370 | 370 | 0402113008 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I A | 14.2767 | 120.7352 | R | 1877 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.55 | Terrestrial Optical Fiber Drop | 0.25 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0371 | 1 | 371 | 371 | 1705215020 | MIMAROPA Region | Oriental Mindoro | Victoria | Poblacion III | 13.1669 | 121.2777 | U | 4126 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03226-C09 | PTCI/MIDC | 13.1756 | 121.2763 | 0.98 | Terrestrial Optical Fiber Drop | 0.25 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0372 | 1 | 372 | 372 | 0405814010 | Region IV-A (CALABARZON) | Rizal | Teresa | Calumpang Santo Cristo | 14.5586 | 121.2136 | R | 1394 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00850-A04 | PTCI/MIDC | 14.5535 | 121.2133 | 0.41 | Terrestrial Optical Fiber Drop | 0.71 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0373 | 1 | 373 | 373 | 0803733021 | Region VIII (Eastern Visayas) | Leyte | Matag-Ob | San Guillermo | 11.1467 | 124.4704 | R | 630 | 165 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0037 | PTCI/MIDC | 11.1493 | 124.4693 | 0.31 | Terrestrial Optical Fiber Drop | 0.25 | 9.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0374 | 1 | 374 | 374 | 0501737008 | Region V (Bicol Region) | Camarines Sur | Tinambac | Binalay | 13.8158 | 123.3409 | R | 2335 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050046 | FTAP Globe | 13.8167 | 123.3373 | 0.4 | Terrestrial Optical Fiber Drop | 0.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0375 | 1 | 375 | 375 | 0402109008 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion III-A | 14.4264 | 120.9336 | R | 1136 | 334 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4755 | FTAP Smart | 14.4069 | 120.9425 | 0.21 | Terrestrial Optical Fiber Drop | 1.37 | 2.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0376 | 1 | 376 | 376 | 0102809018 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Medina | 18.0775 | 120.7042 | R | 1318 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 0.31 | Terrestrial Optical Fiber Drop | 2.39 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0377 | 1 | 377 | 377 | 0205701022 | Region II (Cagayan Valley) | Quirino | Aglipay | Pinaripad Norte | 16.4783 | 121.5996 | R | 1084 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020117 | FTAP Globe | 16.4887 | 121.588 | 1.69 | Terrestrial Optical Fiber Drop | 0.25 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0378 | 1 | 378 | 378 | 1705207013 | MIMAROPA Region | Oriental Mindoro | Mansalay | Poblacion | 12.5218 | 121.4411 | U | 4357 | 1117 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170126 | FTAP Globe | 12.5234 | 121.4387 | 0.32 | Terrestrial Optical Fiber Drop | 0.25 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0379 | 1 | 379 | 379 | 1380500023 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pleasant Hills | 14.5872 | 121.0386 | U | 6097 | 1698 | 509 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02647 | Edgepoint | 14.5884 | 121.0398 | 0.18 | Terrestrial Optical Fiber Drop | 0.26 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0380 | 1 | 380 | 380 | 1400108005 | Cordillera Administrative Region (CAR) | Abra | La Paz | Canan | 17.662 | 120.6689 | R | 1507 | 396 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_ABR_0001 | LDIC | 120.6611 | 17.6816 | 2.33 | Terrestrial Optical Fiber Drop | 0.25 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0381 | 1 | 381 | 381 | 0702210038 | Region VII (Central Visayas) | Cebu | Barili | Poblacion | 10.1153 | 123.511 | U | 5196 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 0.35 | Terrestrial Optical Fiber Drop | 0.26 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0382 | 1 | 382 | 382 | 0307104015 | Region III (Central Luzon) | Zambales | Castillejos | Santa Maria | 14.9373 | 120.1983 | R | 2109 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.31 | Terrestrial Optical Fiber Drop | 0.87 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0383 | 1 | 383 | 383 | 1004317016 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Poblacion | 9.0213 | 125.1817 | R | 1713 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0089 | PTCI/MIDC | 9.0209 | 125.184 | 0.25 | Terrestrial Optical Fiber Drop | 0.26 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0384 | 1 | 384 | 384 | 0403415019 | Region IV-A (CALABARZON) | Laguna | Magdalena | Poblacion | 14.1993 | 121.4286 | R | 2735 | 828 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.24 | Terrestrial Optical Fiber Drop | 0.26 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0385 | 1 | 385 | 385 | 0405618012 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Capuluan Tulon | 13.8208 | 122.4877 | R | 937 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-02699 | Edgepoint | 13.8025 | 122.4147 | 8.14 | Terrestrial Optical Fiber Drop | 0.26 | 7.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0386 | 1 | 386 | 386 | 0603044004 | Region VI (Western Visayas) | Iloilo | Sara | Anoring | 11.2188 | 122.9773 | R | 2609 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.4 | Terrestrial Optical Fiber Drop | 5.39 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0387 | 1 | 387 | 387 | 1600206011 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Songkoy | 9.4556 | 125.5743 | R | 2543 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 4.59 | Terrestrial Optical Fiber Drop | 0.26 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0388 | 1 | 388 | 388 | 0704623020 | Region VII (Central Visayas) | Negros Oriental | Valencia | North Poblacion | 9.2823 | 123.2454 | R | 768 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070270 | FTAP Globe | 9.2811 | 123.2423 | 0.37 | Terrestrial Optical Fiber Drop | 0.26 | 5.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0389 | 1 | 389 | 389 | 0306916082 | Region III (Central Luzon) | Tarlac | City of Tarlac | Sapang Tagalog | 15.4218 | 120.5992 | U | 5451 | 1397 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.66 | Terrestrial Optical Fiber Drop | 0.26 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0390 | 1 | 390 | 390 | 1381500009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Maharlika Village | 14.4978 | 121.0551 | U | 26241 | 7809 | 2343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00357-A02 | PTCI/MIDC | 14.4973 | 121.0528 | 0.25 | Terrestrial Optical Fiber Drop | 0.26 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0391 | 1 | 391 | 391 | 0501737004 | Region V (Bicol Region) | Camarines Sur | Tinambac | Banga | 13.8884 | 123.3857 | R | 1188 | 282 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050046 | FTAP Globe | 13.8167 | 123.3373 | 9.54 | Terrestrial Optical Fiber Drop | 0.26 | 9.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0392 | 1 | 392 | 392 | 0603039011 | Region VI (Western Visayas) | Iloilo | San Enrique | Dacal | 11.0697 | 122.6567 | R | 1096 | 288 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.44 | Terrestrial Optical Fiber Drop | 0.26 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0393 | 1 | 393 | 393 | 0405628031 | Region IV-A (CALABARZON) | Quezon | Mulanay | Santa Rosa | 13.5289 | 122.3932 | R | 3511 | 923 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-QUE-03181 | Edgepoint | 13.5248 | 122.4031 | 1.16 | Terrestrial Optical Fiber Drop | 0.26 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0394 | 1 | 394 | 394 | 0304906025 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | District VIII | 15.7803 | 120.662 | R | 1383 | 395 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0032 | PTCI/MIDC | 15.7841 | 120.6581 | 0.59 | Terrestrial Optical Fiber Drop | 0.26 | 6.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0395 | 1 | 395 | 395 | 0803736011 | Region VIII (Eastern Visayas) | Leyte | Merida | Libas | 10.9397 | 124.5447 | R | 2435 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0041 | PTCI/MIDC | 10.9685 | 124.5339 | 3.42 | Terrestrial Optical Fiber Drop | 0.26 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0396 | 1 | 396 | 396 | 1600307001 | Region XIII (Caraga) | Agusan del Sur | Rosario | Bayugan 3 | 8.386 | 126.0814 | U | 14871 | 3813 | 1144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130097 | FTAP Globe | 8.3116 | 126.0093 | 1.17 | Terrestrial Optical Fiber Drop | 8.66 | 7.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0397 | 1 | 397 | 397 | 0501730029 | Region V (Bicol Region) | Camarines Sur | Ragay | Poblacion Ilaod | 13.8192 | 122.7909 | R | 1812 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050045 | FTAP Globe | 13.8174 | 122.7937 | 0.36 | Terrestrial Optical Fiber Drop | 0.26 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0398 | 1 | 398 | 398 | 0304917026 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion East | 15.7143 | 120.9051 | U | 2186 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0180 | FTAP Smart | 15.7184 | 120.9059 | 0.47 | Terrestrial Optical Fiber Drop | 0.26 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0399 | 1 | 399 | 399 | 0603009024 | Region VI (Western Visayas) | Iloilo | Batad | Tanao | 11.4191 | 123.111 | R | 2058 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.5 | Terrestrial Optical Fiber Drop | 0.26 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0400 | 1 | 400 | 400 | 0402109084 | Region IV-A (CALABARZON) | Cavite | City of Imus | Palico IV | 14.4281 | 120.947 | U | 3871 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01878-C08 | PTCI/MIDC | 14.4292 | 120.9451 | 0.23 | Terrestrial Optical Fiber Drop | 0.27 | 2.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0401 | 1 | 401 | 401 | 1381500001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Tanyag | 14.4801 | 121.0471 | U | 24705 | 7744 | 2323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01865 | Edgepoint | 14.5092 | 121.0624 | 0.09 | Terrestrial Optical Fiber Drop | 0.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0402 | 1 | 402 | 402 | 0501603032 | Region V (Bicol Region) | Camarines Norte | Daet | San Isidro | 14.106 | 122.9536 | R | 3341 | 835 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S92 | FTAP Smart | 14.1147 | 122.9549 | 0.13 | Terrestrial Optical Fiber Drop | 0.95 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0403 | 1 | 403 | 403 | 0401025013 | Region IV-A (CALABARZON) | Batangas | San Nicolas | Poblacion | 13.9281 | 120.9499 | R | 3272 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040462 | FTAP Globe | 13.9283 | 120.9517 | 0.19 | Terrestrial Optical Fiber Drop | 0.27 | 4.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0404 | 1 | 404 | 404 | 0307109014 | Region III (Central Luzon) | Zambales | San Antonio | Rizal | 14.9492 | 120.0881 | R | 478 | 125 | 38 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.41 | Terrestrial Optical Fiber Drop | 0.27 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0405 | 1 | 405 | 405 | 1380500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Wack-wack Greenhills | 14.5836 | 121.0338 | U | 13775 | 3625 | 1088 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0115 | PTCI/MIDC | 14.5645 | 121.0253 | 0.16 | Terrestrial Optical Fiber Drop | 0.62 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0406 | 1 | 406 | 406 | 0803722019 | Region VIII (Eastern Visayas) | Leyte | Isabel | San Roque | 10.9243 | 124.4398 | R | 1525 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080356 | FTAP Globe | 10.9258 | 124.4385 | 0.22 | Terrestrial Optical Fiber Drop | 0.27 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0407 | 1 | 407 | 407 | 0405801005 | Region IV-A (CALABARZON) | Rizal | Angono | Kalayaan | 14.5297 | 121.1536 | U | 19309 | 5363 | 1609 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02296-A04 | PTCI/MIDC | 14.5283 | 121.1526 | 0.19 | Terrestrial Optical Fiber Drop | 0.27 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0408 | 1 | 408 | 408 | 0600415002 | Region VI (Western Visayas) | Aklan | New Washington | Cawayan | 11.6503 | 122.4336 | R | 4310 | 1105 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.86 | Terrestrial Optical Fiber Drop | 0.27 | 7.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0409 | 1 | 409 | 409 | 0803715035 | Region VIII (Eastern Visayas) | Leyte | Carigara | Sawang | 11.3001 | 124.6869 | R | 2393 | 629 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 0.98 | Terrestrial Optical Fiber Drop | 0.27 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0410 | 1 | 410 | 410 | 0803738090 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Valencia | 11.1081 | 124.5773 | U | 4374 | 1151 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0029 | PTCI/MIDC | 11.128 | 124.5855 | 2.39 | Terrestrial Optical Fiber Drop | 0.27 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0411 | 1 | 411 | 411 | 0603009004 | Region VI (Western Visayas) | Iloilo | Batad | Batad Viejo | 11.419 | 123.111 | R | 1207 | 317 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.51 | Terrestrial Optical Fiber Drop | 0.27 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0412 | 1 | 412 | 412 | 0604531009 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay VI | 10.9091 | 123.0764 | U | 5874 | 1587 | 476 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.47 | Terrestrial Optical Fiber Drop | 0.91 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0413 | 1 | 413 | 413 | 0307109009 | Region III (Central Luzon) | Zambales | San Antonio | San Gregorio | 14.9519 | 120.0885 | R | 1062 | 279 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.7 | Terrestrial Optical Fiber Drop | 0.27 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0414 | 1 | 414 | 414 | 0402106008 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan I | 14.3215 | 120.9793 | U | 10659 | 3135 | 941 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.63 | Terrestrial Optical Fiber Drop | 0.46 | 3.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0415 | 1 | 415 | 415 | 0105526002 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Amansabina | 16.0666 | 120.4001 | U | 2732 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.7 | Terrestrial Optical Fiber Drop | 0.27 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0416 | 1 | 416 | 416 | 0501602015 | Region V (Bicol Region) | Camarines Norte | Capalonga | Magsaysay | 14.2266 | 122.5522 | R | 1956 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050011 | FTAP Globe | 14.191 | 122.5157 | 5.58 | Terrestrial Optical Fiber Drop | 0.27 | 5.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0417 | 1 | 417 | 417 | 0102812004 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 56-B, Bacsil South | 18.1988 | 120.6558 | R | 1366 | 369 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-ILN-03234 | Edgepoint | 18.206 | 120.5863 | 0.36 | Terrestrial Optical Fiber Drop | 4.99 | 5.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0418 | 1 | 418 | 418 | 0201504020 | Region II (Cagayan Valley) | Cagayan | Amulung | Centro | 17.8343 | 121.7243 | U | 2918 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01178-B06 | PTCI/MIDC | 17.8338 | 121.7241 | 0.07 | Terrestrial Optical Fiber Drop | 0.28 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0419 | 1 | 419 | 419 | 0402103046 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Molino III | 14.3976 | 120.9775 | U | 63684 | 18730 | 5619 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040127 | FTAP Globe | 14.3946 | 120.9746 | 0.46 | Terrestrial Optical Fiber Drop | 0.28 | 5.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0420 | 1 | 420 | 420 | 0405607060 | Region IV-A (CALABARZON) | Quezon | Calauag | Pinagkamaligan | 13.9561 | 122.285 | R | 1843 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0005 | PTCI/MIDC | 13.957 | 122.2821 | 0.33 | Terrestrial Optical Fiber Drop | 0.27 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0421 | 1 | 421 | 421 | 0304901021 | Region III (Central Luzon) | Nueva Ecija | Aliaga | Poblacion East I | 15.5011 | 120.8511 | R | 2597 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01498-B07 | PTCI/MIDC | 15.5018 | 120.8731 | 0.51 | Terrestrial Optical Fiber Drop | 2.15 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0422 | 1 | 422 | 422 | 1606819005 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Bongtod Pob. | 17.1051 | 122.2743 | U | 6121 | 1492 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.64 | Terrestrial Optical Fiber Drop | 27.55 | 37.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0423 | 1 | 423 | 423 | 0702243020 | Region VII (Central Visayas) | Cebu | San Remigio | Poblacion | 11.081 | 123.9378 | U | 5869 | 1544 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070302 | FTAP Globe | 11.08 | 123.9405 | 0.32 | Terrestrial Optical Fiber Drop | 0.28 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0424 | 1 | 424 | 424 | 0702248018 | Region VII (Central Visayas) | Cebu | Tabogon | Poblacion | 10.9412 | 124.0281 | R | 1631 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070306 | FTAP Globe | 10.9458 | 124.0265 | 0.54 | Terrestrial Optical Fiber Drop | 0.28 | 6.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0425 | 1 | 425 | 425 | 0306913005 | Region III (Central Luzon) | Tarlac | San Clemente | Catagudingan | 15.7082 | 120.366 | R | 720 | 184 | 55 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01813-B07 | PTCI/MIDC | 15.7092 | 120.3597 | 0.69 | Terrestrial Optical Fiber Drop | 0.28 | 5.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0426 | 1 | 426 | 426 | 0401031034 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 3 | 14.1034 | 121.0787 | U | 5284 | 1467 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040316 | FTAP Globe | 14.1024 | 121.0968 | 0.27 | Terrestrial Optical Fiber Drop | 2.15 | 6.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0427 | 1 | 427 | 427 | 0201524004 | Region II (Cagayan Valley) | Cagayan | Santa Praxedes | Centro II | 18.5632 | 120.9902 | R | 939 | 240 | 72 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0052 | LDIC | 120.9909 | 18.5648 | 0.19 | Terrestrial Optical Fiber Drop | 0.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0428 | 1 | 428 | 428 | 0600401007 | Region VI (Western Visayas) | Aklan | Altavas | Lumaynay | 11.4866 | 122.4282 | R | 1190 | 305 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 3.26 | Terrestrial Optical Fiber Drop | 8.28 | 5.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0429 | 1 | 429 | 429 | 0405625018 | Region IV-A (CALABARZON) | Quezon | Macalelon | Rizal | 13.7477 | 122.1383 | R | 474 | 124 | 37 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.18 | Terrestrial Optical Fiber Drop | 0.28 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0430 | 1 | 430 | 430 | 1380200009 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Zapote | 14.4639 | 120.9708 | U | 19994 | 5234 | 1570 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02396-A03 | PTCI/MIDC | 14.4619 | 120.9719 | 0.25 | Terrestrial Optical Fiber Drop | 0.28 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0431 | 1 | 431 | 431 | 1001321029 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Sinayawan | 7.8732 | 125.1439 | U | 8940 | 2352 | 706 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100209 | FTAP Globe | 7.8774 | 125.142 | 0.51 | Terrestrial Optical Fiber Drop | 0.28 | 4.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0432 | 1 | 432 | 432 | 1380700010 | National Capital Region (NCR) | Metro Manila (NCR) | City of Marikina | Santo Niño | 14.639 | 121.0958 | U | 30271 | 8248 | 2474 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00284-A01 | PTCI/MIDC | 14.6371 | 121.0972 | 0.27 | Terrestrial Optical Fiber Drop | 0.28 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0433 | 1 | 433 | 433 | 0803702052 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Milagrosa | 11.2189 | 124.8596 | R | 1125 | 296 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 0.32 | Terrestrial Optical Fiber Drop | 2.38 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0434 | 1 | 434 | 434 | 1001304004 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Calaocalao | 7.6872 | 124.9182 | R | 3163 | 832 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0007 | PTCI/MIDC | 7.6385 | 124.9046 | 5.62 | Terrestrial Optical Fiber Drop | 0.28 | 8.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0435 | 1 | 435 | 435 | 0301421050 | Region III (Central Luzon) | Bulacan | San Miguel | Santa Rita Matanda | 15.1336 | 120.9661 | R | 3118 | 890 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030029 | FTAP BTS | 15.1372 | 120.9654 | 0.41 | Terrestrial Optical Fiber Drop | 0.28 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0436 | 1 | 436 | 436 | 0403428002 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Balibago | 14.2963 | 121.1045 | U | 23640 | 7163 | 2149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040188 | FTAP Globe | 14.2948 | 121.1032 | 0.22 | Terrestrial Optical Fiber Drop | 0.28 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0437 | 1 | 437 | 437 | 0300808001 | Region III (Central Luzon) | Bataan | Morong | Binaritan | 14.6824 | 120.268 | U | 7440 | 2066 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02575 | Edgepoint | 14.6805 | 120.2704 | 0.33 | Terrestrial Optical Fiber Drop | 0.28 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0438 | 1 | 438 | 438 | 1381000001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Baclaran | 14.5298 | 120.9989 | U | 35290 | 14582 | 4375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00585-A02 | PTCI/MIDC | 14.5278 | 120.9978 | 0.25 | Terrestrial Optical Fiber Drop | 0.28 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0439 | 1 | 439 | 439 | 0702208027 | Region VII (Central Visayas) | Cebu | Balamban | Baliwagan | 10.5066 | 123.7145 | U | 6280 | 1652 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 1.12 | Terrestrial Optical Fiber Drop | 0.28 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0440 | 1 | 440 | 440 | 0105516007 | Region I (Ilocos Region) | Pangasinan | Burgos | Poblacion | 16.0548 | 119.8647 | U | 3491 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01737-B07 | PTCI/MIDC | 16.0575 | 119.864 | 0.31 | Terrestrial Optical Fiber Drop | 0.28 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0441 | 1 | 441 | 441 | 0506216013 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Burabod | 12.9718 | 124.0051 | U | 2249 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.31 | Terrestrial Optical Fiber Drop | 0.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0442 | 1 | 442 | 442 | 0506203009 | Region V (Bicol Region) | Sorsogon | Bulan | Zone V Pob. | 12.6694 | 123.8754 | R | 1494 | 373 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.56 | Terrestrial Optical Fiber Drop | 0.28 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0443 | 1 | 443 | 443 | 0600411009 | Region VI (Western Visayas) | Aklan | Makato | Calimbajan | 11.7215 | 122.2751 | R | 2139 | 548 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.1 | Terrestrial Optical Fiber Drop | 2.09 | 9.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0444 | 1 | 444 | 444 | 0405647043 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Mateuna | 14.0242 | 121.596 | U | 5954 | 1566 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1446 | FTAP Smart | 14.0221 | 121.5973 | 0.28 | Terrestrial Optical Fiber Drop | 0.28 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0445 | 1 | 445 | 445 | 0300803019 | Region III (Central Luzon) | Bataan | City of Balanga | Talisay | 14.6811 | 120.5454 | R | 2278 | 632 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N55 | FTAP Smart | 14.6842 | 120.5412 | 0.57 | Terrestrial Optical Fiber Drop | 0.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0446 | 1 | 446 | 446 | 0203105005 | Region II (Cagayan Valley) | Isabela | Burgos | Catabban | 17.0303 | 121.7419 | R | 1768 | 465 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0034 | LDIC | 121.7481 | 17.0468 | 1.95 | Terrestrial Optical Fiber Drop | 0.28 | 4.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0447 | 1 | 447 | 447 | 0401004009 | Region IV-A (CALABARZON) | Batangas | Balete | Poblacion | 14.02 | 121.0938 | R | 2357 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 0.92 | Terrestrial Optical Fiber Drop | 0.28 | 7.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0448 | 1 | 448 | 448 | 1381300077 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Pansol | 14.6659 | 121.0713 | U | 35572 | 8915 | 2675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01443 | Edgepoint | 14.6661 | 121.0725 | 0.13 | Terrestrial Optical Fiber Drop | 0.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0449 | 1 | 449 | 449 | 1381000006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Parañaque | Tambo | 14.5167 | 120.9969 | U | 35356 | 9607 | 2882 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | H18 | FTAP Smart | 14.5163 | 120.995 | 0.21 | Terrestrial Optical Fiber Drop | 0.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0450 | 1 | 450 | 450 | 1380500004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Barangka Ibaba | 14.5733 | 121.0381 | U | 9473 | 2794 | 838 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02522 | Edgepoint | 14.5811 | 121.0289 | 0.1 | Terrestrial Optical Fiber Drop | 1.27 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0451 | 1 | 451 | 451 | 0501733020 | Region V (Bicol Region) | Camarines Sur | San Jose | Salogon | 13.6992 | 123.5183 | R | 3170 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 0.36 | Terrestrial Optical Fiber Drop | 0.29 | 2.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0452 | 1 | 452 | 452 | 0307111003 | Region III (Central Luzon) | Zambales | San Marcelino | Burgos | 14.9791 | 120.1551 | R | 2260 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00974 | Edgepoint | 14.9764 | 120.153 | 0.37 | Terrestrial Optical Fiber Drop | 0.28 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0453 | 1 | 453 | 453 | 0501712020 | Region V (Bicol Region) | Camarines Sur | Del Gallego | Poblacion Zone III | 13.9228 | 122.5968 | R | 1521 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050037 | FTAP Globe | 13.9255 | 122.5947 | 0.38 | Terrestrial Optical Fiber Drop | 0.29 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0454 | 1 | 454 | 454 | 0405639018 | Region IV-A (CALABARZON) | Quezon | Sampaloc | San Roque | 14.1599 | 121.6375 | R | 2487 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.27 | Terrestrial Optical Fiber Drop | 0.29 | 9.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0455 | 1 | 455 | 455 | 0603018021 | Region VI (Western Visayas) | Iloilo | Dumangas | Ilaya 1st | 10.827 | 122.7121 | R | 682 | 179 | 54 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.03 | Terrestrial Optical Fiber Drop | 0.29 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0456 | 1 | 456 | 456 | 0504103030 | Region V (Bicol Region) | Masbate | Balud | Tonga | 12.0681 | 123.2379 | R | 1044 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050256 | FTAP Globe | 12.0387 | 123.1919 | 5.98 | Terrestrial Optical Fiber Drop | 0.29 | 14.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0457 | 1 | 457 | 457 | 0405630021 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 3 Del Carmen | 13.9695 | 121.6834 | R | 1381 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.18 | Terrestrial Optical Fiber Drop | 0.29 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0458 | 1 | 458 | 458 | 0402104011 | Region IV-A (CALABARZON) | Cavite | Carmona | Milagrosa | 14.3083 | 121.0494 | U | 25103 | 7383 | 2215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040182 | FTAP Globe | 14.3107 | 121.0494 | 0.26 | Terrestrial Optical Fiber Drop | 0.29 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0459 | 1 | 459 | 459 | 0403408001 | Region IV-A (CALABARZON) | Laguna | Famy | Asana | 14.4381 | 121.4495 | R | 582 | 176 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040101 | FTAP Globe | 14.4377 | 121.4463 | 0.35 | Terrestrial Optical Fiber Drop | 0.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0460 | 1 | 460 | 460 | 0103306026 | Region I (Ilocos Region) | La Union | Bangar | Central East No. 2 | 16.8957 | 120.4241 | R | 1049 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.07 | Terrestrial Optical Fiber Drop | 0.29 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0461 | 1 | 461 | 461 | 1004324006 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Poblacion | 8.5373 | 124.7553 | U | 10662 | 2733 | 820 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0098 | PTCI/MIDC | 8.5402 | 124.755 | 0.32 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0462 | 1 | 462 | 462 | 0803714016 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone II | 11.2931 | 124.6381 | R | 4790 | 1260 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 1.89 | Terrestrial Optical Fiber Drop | 0.29 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0463 | 1 | 463 | 463 | 0105535008 | Region I (Ilocos Region) | Pangasinan | San Manuel | Guiset Sur | 16.0636 | 120.6672 | R | 4860 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00422 | Edgepoint | 16.0668 | 120.6701 | 0.47 | Terrestrial Optical Fiber Drop | 0.29 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0464 | 1 | 464 | 464 | 0603026019 | Region VI (Western Visayas) | Iloilo | Leganes | Poblacion | 10.7882 | 122.5899 | U | 3436 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.37 | Terrestrial Optical Fiber Drop | 0.29 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0465 | 1 | 465 | 465 | 0702245008 | Region VII (Central Visayas) | Cebu | Santander | Poblacion | 9.4173 | 123.334 | R | 2968 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0153 | PTCI/MIDC | 9.4196 | 123.3343 | 0.26 | Terrestrial Optical Fiber Drop | 0.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0466 | 1 | 466 | 466 | 1102403028 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 1 | 6.7576 | 125.3554 | U | 17556 | 5163 | 1549 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0071 | PTCI/MIDC | 6.7534 | 125.365 | 1.17 | Terrestrial Optical Fiber Drop | 0.29 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0467 | 1 | 467 | 467 | 0102819016 | Region I (Ilocos Region) | Ilocos Norte | Pinili | Pagdilao | 17.9511 | 120.5259 | R | 1159 | 313 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01219-B05 | PTCI/MIDC | 17.9518 | 120.5224 | 0.37 | Terrestrial Optical Fiber Drop | 0.29 | 3.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0468 | 1 | 468 | 468 | 0701232016 | Region VII (Central Visayas) | Bohol | Maribojoc | Poblacion | 9.7395 | 123.844 | R | 2098 | 524 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070413 | FTAP Globe | 9.7455 | 123.842 | 0.7 | Terrestrial Optical Fiber Drop | 0.3 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0469 | 1 | 469 | 469 | 0401034013 | Region IV-A (CALABARZON) | Batangas | Tuy | Luna | 14.0212 | 120.7311 | R | 2745 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.44 | Terrestrial Optical Fiber Drop | 0.29 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0470 | 1 | 470 | 470 | 0603017048 | Region VI (Western Visayas) | Iloilo | Dueñas | Poblacion A | 11.0667 | 122.6169 | R | 1432 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0018 | PTCI/MIDC | 11.065 | 122.622 | 0.58 | Terrestrial Optical Fiber Drop | 0.3 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0471 | 1 | 471 | 471 | 0506206029 | Region V (Bicol Region) | Sorsogon | Castilla | San Isidro | 12.9736 | 123.8402 | R | 4377 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-02708 | Edgepoint | 12.9755 | 123.847 | 0.76 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0472 | 1 | 472 | 472 | 0604531007 | Region VI (Western Visayas) | Negros Occidental | City of Victorias | Barangay IV | 10.9009 | 123.0777 | R | 1183 | 319 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060328 | FTAP Globe | 10.9029 | 123.071 | 0.5 | Terrestrial Optical Fiber Drop | 0.51 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0473 | 1 | 473 | 473 | 0501726017 | Region V (Bicol Region) | Camarines Sur | Pamplona | Tambo | 13.5783 | 123.0639 | U | 4221 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050103 | FTAP Globe | 13.5641 | 123.0576 | 1.72 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0474 | 1 | 474 | 474 | 0405603041 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tinandog | 13.9963 | 121.9121 | R | 1260 | 331 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | B55 | FTAP Smart | 13.998 | 121.9283 | 0.33 | Terrestrial Optical Fiber Drop | 1.51 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0475 | 1 | 475 | 475 | 0301423002 | Region III (Central Luzon) | Bulacan | Santa Maria | Balasing | 14.8506 | 121.0019 | U | 10173 | 2906 | 872 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01122 | Edgepoint | 14.8505 | 121.0044 | 0.27 | Terrestrial Optical Fiber Drop | 0.3 | 1.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0476 | 1 | 476 | 476 | 1705205049 | MIMAROPA Region | Oriental Mindoro | City of Calapan | San Antonio | 13.4261 | 121.1956 | U | 3564 | 913 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 0.4 | Terrestrial Optical Fiber Drop | 0.3 | 6.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0477 | 1 | 477 | 477 | 0403426026 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Sur | 14.2812 | 121.4113 | U | 4457 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.34 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0478 | 1 | 478 | 478 | 0405607017 | Region IV-A (CALABARZON) | Quezon | Calauag | Barangay V | 13.9582 | 122.2897 | R | 961 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040424 | FTAP Globe | 13.9534 | 122.2876 | 0.58 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0479 | 1 | 479 | 479 | 0203131029 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone III | 16.9877 | 122.0143 | R | 3856 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.83 | Terrestrial Optical Fiber Drop | 0.3 | 16.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0480 | 1 | 480 | 480 | 0500517007 | Region V (Bicol Region) | Albay | City of Tabaco | Basud | 13.3541 | 123.7289 | U | 2697 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050129 | FTAP Globe | 13.3576 | 123.7292 | 0.39 | Terrestrial Optical Fiber Drop | 0.3 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0481 | 1 | 481 | 481 | 0300810016 | Region III (Central Luzon) | Bataan | Orion | Kapunitan | 14.6163 | 120.5817 | R | 4322 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0002 | PTCI/MIDC | 14.6145 | 120.5801 | 0.26 | Terrestrial Optical Fiber Drop | 0.3 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0482 | 1 | 482 | 482 | 0403424036 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Del Remedio | 14.0815 | 121.3137 | U | 19590 | 5936 | 1781 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040337 | FTAP Globe | 14.0845 | 121.3149 | 0.35 | Terrestrial Optical Fiber Drop | 0.3 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0483 | 1 | 483 | 483 | 0405641014 | Region IV-A (CALABARZON) | Quezon | San Antonio | Poblacion | 13.8904 | 121.2872 | R | 2007 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03161-C08 | PTCI/MIDC | 13.8725 | 121.2905 | 2.03 | Terrestrial Optical Fiber Drop | 0.3 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0484 | 1 | 484 | 484 | 0105527011 | Region I (Ilocos Region) | Pangasinan | Mangatarem | Bogtong Silag | 15.8127 | 120.2812 | R | 1901 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-02360 | Edgepoint | 15.8237 | 120.2701 | 1.71 | Terrestrial Optical Fiber Drop | 0.3 | 14.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0485 | 1 | 485 | 485 | 0304931014 | Region III (Central Luzon) | Nueva Ecija | Talugtug | Osmeña | 15.7783 | 120.8138 | R | 1191 | 340 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030317 | FTAP Globe | 15.7792 | 120.8099 | 0.43 | Terrestrial Optical Fiber Drop | 0.3 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0486 | 1 | 486 | 486 | 0201508016 | Region II (Cagayan Valley) | Cagayan | Buguey | Pattao | 18.2481 | 121.8158 | R | 3799 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0006 | LDIC | 18.2476 | 121.8139 | 0.21 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0487 | 1 | 487 | 487 | 0102820002 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Ildefonso | 18.1728 | 120.5946 | R | 1769 | 478 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.08 | Terrestrial Optical Fiber Drop | 0.3 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0488 | 1 | 488 | 488 | 0405618010 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Calimpak | 13.9007 | 122.4515 | U | 5082 | 1337 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040512 | FTAP Globe | 13.8986 | 122.4538 | 0.34 | Terrestrial Optical Fiber Drop | 0.3 | 11.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0489 | 1 | 489 | 489 | 1004317008 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Consuelo | 8.9155 | 125.1874 | R | 4051 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0062 | PTCI/MIDC | 8.9119 | 125.1864 | 0.41 | Terrestrial Optical Fiber Drop | 0.3 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0490 | 1 | 490 | 490 | 0402116001 | Region IV-A (CALABARZON) | Cavite | Noveleta | Magdiwang | 14.4313 | 120.8798 | U | 2351 | 691 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.29 | Terrestrial Optical Fiber Drop | 0.39 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0491 | 1 | 491 | 491 | 0500507005 | Region V (Bicol Region) | Albay | Libon | Zone II | 13.2982 | 123.4415 | R | 1085 | 264 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050140 | FTAP Globe | 13.2972 | 123.4391 | 0.28 | Terrestrial Optical Fiber Drop | 0.3 | 1.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0492 | 1 | 492 | 492 | 0203119006 | Region II (Cagayan Valley) | Isabela | Mallig | Maligaya | 17.1847 | 121.6121 | R | 2493 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03318-B06 | PTCI/MIDC | 17.184 | 121.6115 | 0.1 | Terrestrial Optical Fiber Drop | 0.3 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0493 | 1 | 493 | 493 | 0601912020 | Region VI (Western Visayas) | Capiz | Pontevedra | Ilaya | 11.4795 | 122.8317 | R | 972 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAP_0003 | LDIC | 11.4838 | 122.8327 | 0.49 | Terrestrial Optical Fiber Drop | 0.3 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0494 | 1 | 494 | 494 | 1404409014 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Poblacion | 17.085 | 120.8979 | U | 1411 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01407-B05 | PTCI/MIDC | 17.0819 | 120.9043 | 0.77 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0495 | 1 | 495 | 495 | 0306911014 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 3 | 15.6242 | 120.6485 | R | 1243 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.07 | Terrestrial Optical Fiber Drop | 0.3 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0496 | 1 | 496 | 496 | 0405647003 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Angeles Zone I | 14.0223 | 121.5959 | R | 1781 | 468 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1446 | FTAP Smart | 14.0221 | 121.5973 | 0.15 | Terrestrial Optical Fiber Drop | 0.31 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0497 | 1 | 497 | 497 | 0401031046 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Talaga | 14.1034 | 121.097 | U | 5766 | 1601 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040316 | FTAP Globe | 14.1024 | 121.0968 | 0.11 | Terrestrial Optical Fiber Drop | 0.31 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0498 | 1 | 498 | 498 | 0103311025 | Region I (Ilocos Region) | La Union | Naguilian | Magungunay | 16.4743 | 120.4064 | R | 872 | 235 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 0.82 | Terrestrial Optical Fiber Drop | 6.09 | 7.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0499 | 1 | 499 | 499 | 1408106014 | Cordillera Administrative Region (CAR) | Apayao | Pudtol | Mataguisi | 18.1287 | 121.3478 | R | 1114 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140103 | FTAP Globe | 18.1451 | 121.4478 | 10.72 | Terrestrial Optical Fiber Drop | 0.31 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0500 | 1 | 500 | 500 | 1004309009 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Poblacion | 8.5952 | 124.4068 | R | 3192 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100118 | FTAP Globe | 8.5922 | 124.3873 | 2.18 | Terrestrial Optical Fiber Drop | 0.31 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0501 | 1 | 501 | 501 | 0401019009 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Barangay 4 | 14.0735 | 120.6335 | R | 1373 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01947-C08 | PTCI/MIDC | 14.0724 | 120.6355 | 0.25 | Terrestrial Optical Fiber Drop | 0.31 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0502 | 1 | 502 | 502 | 0203126013 | Region II (Cagayan Valley) | Isabela | Roxas | Bantug | 17.1144 | 121.6129 | U | 5908 | 1554 | 466 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0060 | PTCI/MIDC | 17.1203 | 121.6155 | 0.72 | Terrestrial Optical Fiber Drop | 0.31 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0503 | 1 | 503 | 503 | 0401029015 | Region IV-A (CALABARZON) | Batangas | Taal | Ilog | 13.8926 | 120.9315 | R | 1437 | 399 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040516 | FTAP Globe | 13.893 | 120.9287 | 0.46 | Terrestrial Optical Fiber Drop | 0.94 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0504 | 1 | 504 | 504 | 0307706009 | Region III (Central Luzon) | Aurora | Dipaculao | Dinadiawan | 16.0772 | 121.7706 | R | 3215 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02908-B06 | PTCI/MIDC | 16.0788 | 121.768 | 0.32 | Terrestrial Optical Fiber Drop | 0.31 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0505 | 1 | 505 | 505 | 0301423018 | Region III (Central Luzon) | Bulacan | Santa Maria | San Gabriel | 14.8069 | 120.9585 | U | 10066 | 2876 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02211 | Edgepoint | 14.8035 | 120.9555 | 0.5 | Terrestrial Optical Fiber Drop | 0.31 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0506 | 1 | 506 | 506 | 0306903027 | Region III (Central Luzon) | Tarlac | Camiling | Malacampa | 15.6402 | 120.4118 | U | 6156 | 1578 | 473 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00623 | Edgepoint | 15.6378 | 120.4097 | 0.35 | Terrestrial Optical Fiber Drop | 0.31 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0507 | 1 | 507 | 507 | 0103305012 | Region I (Ilocos Region) | La Union | Balaoan | Cabuaan Oeste | 16.8014 | 120.4186 | R | 1221 | 330 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00255 | Edgepoint | 16.8196 | 120.4033 | 0.42 | Terrestrial Optical Fiber Drop | 2.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0508 | 1 | 508 | 508 | 0330100001 | Region III (Central Luzon) | Pampanga | City of Angeles | Agapito del Rosario | 15.1494 | 120.5926 | U | 2669 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 538 | FTAP Smart | 15.15 | 120.591 | 0.15 | Terrestrial Optical Fiber Drop | 0.25 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0509 | 1 | 509 | 509 | 0506207034 | Region V (Bicol Region) | Sorsogon | Donsol | Rawis | 12.9034 | 123.5959 | R | 2324 | 581 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050213 | FTAP Globe | 12.9091 | 123.5966 | 0.64 | Terrestrial Optical Fiber Drop | 0.31 | 18.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0510 | 1 | 510 | 510 | 1705320021 | MIMAROPA Region | Palawan | Taytay | Pularaquen | 10.9559 | 119.4853 | R | 3467 | 888 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S2220 | FTAP Smart | 11.02 | 119.4203 | 10.06 | Terrestrial Optical Fiber Drop | 0.31 | 15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0511 | 1 | 511 | 511 | 1001320021 | Region X (Northern Mindanao) | Bukidnon | Talakag | Barangay 3 | 8.2347 | 124.6002 | R | 1641 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0044 | PTCI/MIDC | 8.235 | 124.6022 | 0.22 | Terrestrial Optical Fiber Drop | 0.31 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0512 | 1 | 512 | 512 | 0600402011 | Region VI (Western Visayas) | Aklan | Balete | Poblacion | 11.5573 | 122.3783 | R | 899 | 230 | 69 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 2.48 | Terrestrial Optical Fiber Drop | 0.31 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0513 | 1 | 513 | 513 | 0306907003 | Region III (Central Luzon) | Tarlac | La Paz | Caramutan | 15.4454 | 120.7197 | U | 4566 | 1170 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.92 | Terrestrial Optical Fiber Drop | 0.31 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0514 | 1 | 514 | 514 | 0305415033 | Region III (Central Luzon) | Pampanga | Porac | Sinura | 15.1161 | 120.57 | R | 3859 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01636-B07 | PTCI/MIDC | 15.113 | 120.5717 | 0.39 | Terrestrial Optical Fiber Drop | 0.31 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0515 | 1 | 515 | 515 | 1380900001 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Sipac-Almacen | 14.6583 | 120.9483 | U | 9097 | 2614 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000482 | FTAP Globe | 14.6587 | 120.9471 | 0.13 | Terrestrial Optical Fiber Drop | 0.31 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0516 | 1 | 516 | 516 | 0402109075 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion II-B | 14.4051 | 120.9263 | R | 1605 | 472 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.39 | Terrestrial Optical Fiber Drop | 1.56 | 4.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0517 | 1 | 517 | 517 | 0307104012 | Region III (Central Luzon) | Zambales | Castillejos | San Nicolas | 14.927 | 120.2016 | R | 4602 | 1211 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.36 | Terrestrial Optical Fiber Drop | 0.31 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0518 | 1 | 518 | 518 | 0401023029 | Region IV-A (CALABARZON) | Batangas | San Juan | Poblacion | 13.8272 | 121.3943 | U | 3208 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01956-C08 | PTCI/MIDC | 13.8259 | 121.3951 | 0.17 | Terrestrial Optical Fiber Drop | 0.31 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1043 | 1 | 519 | 519 | 0401006022 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Proper | 13.7944 | 120.9978 | U | 11200 | 3111 | 933 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B15 | FTAP Smart | 13.7981 | 120.9984 | 0.41 | Terrestrial Optical Fiber Drop | 0.55 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0520 | 1 | 520 | 520 | 0701230036 | Region VII (Central Visayas) | Bohol | Loon | Cogon Norte | 9.8033 | 123.8002 | R | 2127 | 531 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 1.09 | Terrestrial Optical Fiber Drop | 0.31 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0521 | 1 | 521 | 521 | 0305417014 | Region III (Central Luzon) | Pampanga | San Luis | Santa Monica | 15.0364 | 120.7896 | R | 3403 | 850 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02210 | Edgepoint | 15.0355 | 120.7875 | 0.25 | Terrestrial Optical Fiber Drop | 0.32 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0522 | 1 | 522 | 522 | 0501736022 | Region V (Bicol Region) | Camarines Sur | Tigaon | Talojongon | 13.6277 | 123.4963 | U | 4109 | 978 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 0.74 | Terrestrial Optical Fiber Drop | 0.32 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0523 | 1 | 523 | 523 | 0205704014 | Region II (Cagayan Valley) | Quirino | Maddela | Lusod | 16.334 | 121.6792 | R | 1908 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0003 | LDIC | 121.6809 | 16.3353 | 0.23 | Terrestrial Optical Fiber Drop | 0.32 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0524 | 1 | 524 | 524 | 0702247016 | Region VII (Central Visayas) | Cebu | Sogod | Poblacion | 10.7491 | 124.0048 | R | 3637 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 0.43 | Terrestrial Optical Fiber Drop | 0.32 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0525 | 1 | 525 | 525 | 0405627024 | Region IV-A (CALABARZON) | Quezon | Mauban | Polo | 14.1771 | 121.7166 | U | 3775 | 993 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02130-C08 | PTCI/MIDC | 14.1755 | 121.7259 | 1.02 | Terrestrial Optical Fiber Drop | 0.32 | 17.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0526 | 1 | 526 | 526 | 0205014001 | Region II (Cagayan Valley) | Nueva Vizcaya | Villaverde | Bintawan Sur | 16.5783 | 121.1888 | R | 3354 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00302 | Edgepoint | 16.5766 | 121.1908 | 0.29 | Terrestrial Optical Fiber Drop | 0.32 | 5.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0527 | 1 | 527 | 527 | 0201502010 | Region II (Cagayan Valley) | Cagayan | Alcala | Centro Norte | 17.9027 | 121.6547 | R | 2228 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0061 | LDIC | 121.6537 | 17.9074 | 0.54 | Terrestrial Optical Fiber Drop | 0.32 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0528 | 1 | 528 | 528 | 0201506019 | Region II (Cagayan Valley) | Cagayan | Baggao | Poblacion | 17.9344 | 121.7718 | U | 3504 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01180-B06 | PTCI/MIDC | 17.932 | 121.7711 | 0.27 | Terrestrial Optical Fiber Drop | 0.32 | 9.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0529 | 1 | 529 | 529 | 0304932017 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Vicente | 15.4546 | 120.7904 | R | 1703 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03332-B07 | PTCI/MIDC | 15.445 | 120.791 | 1.07 | Terrestrial Optical Fiber Drop | 0.32 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0530 | 1 | 530 | 530 | 0301415019 | Region III (Central Luzon) | Bulacan | Pandi | Siling Bata | 14.8924 | 120.97 | U | 13147 | 3756 | 1127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030556 | FTAP Globe | 14.8934 | 120.9692 | 0.14 | Terrestrial Optical Fiber Drop | 0.32 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0531 | 1 | 531 | 531 | 1380800004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Muntinlupa | Cupang | 14.4304 | 121.0495 | U | 57482 | 14334 | 4300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.82 | Terrestrial Optical Fiber Drop | 0.28 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0532 | 1 | 532 | 532 | 0401001015 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Poblacion | 13.934 | 120.9344 | U | 1923 | 534 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01944-C08 | PTCI/MIDC | 13.9385 | 120.9342 | 0.49 | Terrestrial Optical Fiber Drop | 0.32 | 4.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0533 | 1 | 533 | 533 | 1102315029 | Region XI (Davao Region) | Davao del Norte | City of Panabo | San Francisco | 7.3033 | 125.6813 | U | 14187 | 3834 | 1150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0119 | PTCI/MIDC | 7.304 | 125.6832 | 0.22 | Terrestrial Optical Fiber Drop | 0.32 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0534 | 1 | 534 | 534 | 0301419001 | Region III (Central Luzon) | Bulacan | San Ildefonso | Akle | 15.0484 | 121.0715 | U | 4864 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030489 | FTAP Globe | 15.0501 | 121.062 | 1.03 | Terrestrial Optical Fiber Drop | 0.32 | 6.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0535 | 1 | 535 | 535 | 0102818003 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Anao | 18.168 | 120.7195 | R | 1253 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 3987 | FTAP Smart | 18.1615 | 120.7123 | 0.4 | Terrestrial Optical Fiber Drop | 0.6 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0536 | 1 | 536 | 536 | 0501726009 | Region V (Bicol Region) | Camarines Sur | Pamplona | Poblacion | 13.5915 | 123.0795 | U | 6227 | 1482 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 0.49 | Terrestrial Optical Fiber Drop | 0.32 | 1.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0537 | 1 | 537 | 537 | 0402110026 | Region IV-A (CALABARZON) | Cavite | Indang | Barangay 4 | 14.2 | 120.8734 | U | 2496 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0034 | FTAP Smart | 14.1948 | 120.8764 | 0.66 | Terrestrial Optical Fiber Drop | 0.32 | 8.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0538 | 1 | 538 | 538 | 0201505037 | Region II (Cagayan Valley) | Cagayan | Aparri | Punta | 18.3587 | 121.6344 | U | 4977 | 1276 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02764-B06 | PTCI/MIDC | 18.3593 | 121.6365 | 0.23 | Terrestrial Optical Fiber Drop | 0.32 | 10.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0539 | 1 | 539 | 539 | 0501703004 | Region V (Bicol Region) | Camarines Sur | Bato | Caricot | 13.3561 | 123.3639 | R | 542 | 129 | 39 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.47 | Terrestrial Optical Fiber Drop | 0.32 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0540 | 1 | 540 | 540 | 0401004010 | Region IV-A (CALABARZON) | Batangas | Balete | Sala | 14.0199 | 121.1017 | R | 1786 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 1.03 | Terrestrial Optical Fiber Drop | 0.55 | 6.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0541 | 1 | 541 | 541 | 0306917025 | Region III (Central Luzon) | Tarlac | Victoria | San Vicente | 15.5775 | 120.6813 | R | 2286 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.67 | Terrestrial Optical Fiber Drop | 0.43 | 6.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0542 | 1 | 542 | 542 | 0305417012 | Region III (Central Luzon) | Pampanga | San Luis | Santa Cruz Poblacion | 15.041 | 120.7908 | U | 1868 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.21 | Terrestrial Optical Fiber Drop | 0.32 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0543 | 1 | 543 | 543 | 1381200024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Santa Cruz | 14.563 | 121.0791 | U | 5821 | 1653 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02395-A02 | PTCI/MIDC | 14.5632 | 121.0804 | 0.14 | Terrestrial Optical Fiber Drop | 0.33 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0544 | 1 | 544 | 544 | 0500510010 | Region V (Bicol Region) | Albay | Malinao | Comun | 13.3437 | 123.6629 | R | 1845 | 450 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 3.19 | Terrestrial Optical Fiber Drop | 0.33 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0545 | 1 | 545 | 545 | 0603009003 | Region VI (Western Visayas) | Iloilo | Batad | Banban | 11.4184 | 123.1111 | R | 388 | 102 | 31 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.57 | Terrestrial Optical Fiber Drop | 0.33 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0546 | 1 | 546 | 546 | 1606819022 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Telaje | 17.105 | 122.2744 | U | 7962 | 1941 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.13 | Terrestrial Optical Fiber Drop | 27.56 | 37.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0547 | 1 | 547 | 547 | 0105524062 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Poblacion | 15.9233 | 120.4127 | U | 8389 | 2330 | 699 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00528 | Edgepoint | 15.9293 | 120.4132 | 0.67 | Terrestrial Optical Fiber Drop | 0.33 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0548 | 1 | 548 | 548 | 1381200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Antonio | 14.5668 | 121.0848 | U | 14904 | 4151 | 1245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 414 | FTAP Smart | 14.5695 | 121.0843 | 0.3 | Terrestrial Optical Fiber Drop | 0.33 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0549 | 1 | 549 | 549 | 0301423016 | Region III (Central Luzon) | Bulacan | Santa Maria | Poblacion | 14.822 | 120.9625 | U | 13454 | 3844 | 1153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030596 | FTAP Globe | 14.8198 | 120.9635 | 0.26 | Terrestrial Optical Fiber Drop | 0.33 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0550 | 1 | 550 | 550 | 0301403030 | Region III (Central Luzon) | Bulacan | Baliuag | Virgen delas Flores | 14.9458 | 120.886 | U | 7686 | 2196 | 659 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03207-B07 | PTCI/MIDC | 14.9436 | 120.8816 | 0.53 | Terrestrial Optical Fiber Drop | 0.33 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0551 | 1 | 551 | 551 | 0504113019 | Region V (Bicol Region) | Masbate | Mobo | Poblacion Dist. I | 12.3373 | 123.6557 | R | 1891 | 461 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050243 | FTAP Globe | 12.3348 | 123.6581 | 0.38 | Terrestrial Optical Fiber Drop | 0.33 | 4.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0552 | 1 | 552 | 552 | 1705206023 | MIMAROPA Region | Oriental Mindoro | Gloria | Narra | 12.9564 | 121.4778 | R | 2934 | 752 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 1.69 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0553 | 1 | 553 | 553 | 0405616022 | Region IV-A (CALABARZON) | Quezon | General Luna | San Jose | 13.6937 | 122.1715 | R | 2076 | 546 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040603 | FTAP Globe | 13.6919 | 122.1735 | 0.3 | Terrestrial Optical Fiber Drop | 0.33 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0554 | 1 | 554 | 554 | 0403413015 | Region IV-A (CALABARZON) | Laguna | Lumban | Santo Niño | 14.2985 | 121.4615 | R | 1206 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.16 | Terrestrial Optical Fiber Drop | 0.33 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0555 | 1 | 555 | 555 | 0305417006 | Region III (Central Luzon) | Pampanga | San Luis | San Nicolas | 15.041 | 120.7908 | R | 1941 | 485 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030491 | FTAP Globe | 15.0401 | 120.789 | 0.22 | Terrestrial Optical Fiber Drop | 0.33 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0556 | 1 | 556 | 556 | 0205005026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | San Nicolas North | 16.4878 | 121.1501 | R | 2608 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.29 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0557 | 1 | 557 | 557 | 0501706029 | Region V (Bicol Region) | Camarines Sur | Bula | San Roque | 13.4695 | 123.2764 | R | 2440 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.33 | Terrestrial Optical Fiber Drop | 0.33 | 5.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0558 | 1 | 558 | 558 | 1004301010 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Poblacion | 8.5731 | 124.473 | R | 3800 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100122 | FTAP Globe | 8.5696 | 124.4727 | 0.38 | Terrestrial Optical Fiber Drop | 0.33 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0559 | 1 | 559 | 559 | 1004322011 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Poblacion | 8.8592 | 124.7901 | U | 6231 | 1597 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 0.64 | Terrestrial Optical Fiber Drop | 0.33 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0560 | 1 | 560 | 560 | 0702216014 | Region VII (Central Visayas) | Cebu | Catmon | Macaas | 10.6961 | 124.0119 | R | 3612 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070059 | FTAP BTS | 10.7094 | 124.0134 | 1.49 | Terrestrial Optical Fiber Drop | 0.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0561 | 1 | 561 | 561 | 0301415016 | Region III (Central Luzon) | Bulacan | Pandi | Poblacion | 14.8664 | 120.9562 | U | 9072 | 2592 | 778 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01095 | Edgepoint | 14.8658 | 120.955 | 0.15 | Terrestrial Optical Fiber Drop | 0.33 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0562 | 1 | 562 | 562 | 0401027004 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Calayaan | 13.8776 | 120.9666 | R | 2389 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040522 | FTAP Globe | 13.8841 | 120.9487 | 1.78 | Terrestrial Optical Fiber Drop | 0.08 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0563 | 1 | 563 | 563 | 0402108015 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Manggahan | 14.2966 | 120.9118 | U | 20805 | 6119 | 1836 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02219-C08 | PTCI/MIDC | 14.2984 | 120.9147 | 0.37 | Terrestrial Optical Fiber Drop | 0.33 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0564 | 1 | 564 | 564 | 0704625010 | Region VII (Central Visayas) | Negros Oriental | Zamboanguita | Poblacion | 9.101 | 123.1991 | U | 6716 | 1767 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0057 | PTCI/MIDC | 9.0988 | 123.1959 | 0.43 | Terrestrial Optical Fiber Drop | 0.33 | 16.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0565 | 1 | 565 | 565 | 1004321014 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Poblacion | 8.5205 | 124.5718 | U | 3486 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100132 | FTAP Globe | 8.5148 | 124.5755 | 0.75 | Terrestrial Optical Fiber Drop | 0.33 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0566 | 1 | 566 | 566 | 0431200011 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 8 | 13.9301 | 121.6114 | U | 4021 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02698 | Edgepoint | 13.9316 | 121.6129 | 0.22 | Terrestrial Optical Fiber Drop | 0.34 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0567 | 1 | 567 | 567 | 0402122003 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Cabuco | 14.2676 | 120.8472 | U | 40657 | 11957 | 3587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03415-C08 | PTCI/MIDC | 14.274 | 120.8536 | 0.99 | Terrestrial Optical Fiber Drop | 0.34 | 1.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0568 | 1 | 568 | 568 | 0402102011 | Region IV-A (CALABARZON) | Cavite | Amadeo | Barangay I | 14.1672 | 120.924 | R | 1633 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02223-C08 | PTCI/MIDC | 14.1743 | 120.9201 | 0.89 | Terrestrial Optical Fiber Drop | 0.34 | 3.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0569 | 1 | 569 | 569 | 1402703018 | Cordillera Administrative Region (CAR) | Ifugao | Kiangan | Poblacion | 16.7774 | 121.084 | R | 1576 | 404 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02598-B05 | PTCI/MIDC | 16.7758 | 121.0866 | 0.33 | Terrestrial Optical Fiber Drop | 0.34 | 3.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0570 | 1 | 570 | 570 | 1381100081 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 81 | 14.5433 | 120.9981 | U | 2479 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00293-A03 | PTCI/MIDC | 14.4377 | 121.0059 | 0.36 | Terrestrial Optical Fiber Drop | 0.41 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0571 | 1 | 571 | 571 | 0203135033 | Region II (Cagayan Valley) | Isabela | City of Santiago | Sinsayon | 16.691 | 121.5246 | U | 3782 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0053 | PTCI/MIDC | 16.6938 | 121.5261 | 0.35 | Terrestrial Optical Fiber Drop | 0.34 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0572 | 1 | 572 | 572 | 0401008017 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 2 | 13.8331 | 120.63 | R | 1446 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 0.38 | Terrestrial Optical Fiber Drop | 0.34 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0573 | 1 | 573 | 573 | 1401107017 | Cordillera Administrative Region (CAR) | Benguet | Kabayan | Poblacion | 16.623 | 120.8387 | R | 1970 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N2018 | FTAP Smart | 16.6305 | 120.8313 | 1.14 | Terrestrial Optical Fiber Drop | 0.34 | 7.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0574 | 1 | 574 | 574 | 0600415008 | Region VI (Western Visayas) | Aklan | New Washington | Lawa-an | 11.6508 | 122.4333 | R | 1562 | 400 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.79 | Terrestrial Optical Fiber Drop | 0.34 | 7.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0575 | 1 | 575 | 575 | 0403413002 | Region IV-A (CALABARZON) | Laguna | Lumban | Balimbingan | 14.2984 | 121.4616 | R | 1153 | 349 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.55 | Terrestrial Optical Fiber Drop | 0.32 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0576 | 1 | 576 | 576 | 1381200022 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | San Miguel | 14.5669 | 121.0847 | U | 44629 | 13087 | 3926 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 414 | FTAP Smart | 14.5695 | 121.0843 | 0.29 | Terrestrial Optical Fiber Drop | 0.34 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0577 | 1 | 577 | 577 | 0601914032 | Region VI (Western Visayas) | Capiz | City of Roxas | Lanot | 11.5177 | 122.7551 | U | 6661 | 1752 | 526 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02814-D13 | PTCI/MIDC | 11.5219 | 122.7569 | 0.51 | Terrestrial Optical Fiber Drop | 0.34 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0578 | 1 | 578 | 578 | 0301418022 | Region III (Central Luzon) | Bulacan | Pulilan | Poblacion | 14.9041 | 120.8481 | U | 13958 | 3988 | 1196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01118-B07 | PTCI/MIDC | 14.9024 | 120.8479 | 0.18 | Terrestrial Optical Fiber Drop | 0.34 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0579 | 1 | 579 | 579 | 0704601004 | Region VII (Central Visayas) | Negros Oriental | Amlan | Mag-abo | 9.4642 | 123.2206 | R | 2265 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070259 | FTAP Globe | 9.4593 | 123.2167 | 0.7 | Terrestrial Optical Fiber Drop | 0.34 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0580 | 1 | 580 | 580 | 0105514030 | Region I (Ilocos Region) | Pangasinan | Bolinao | Victory | 16.3866 | 119.8929 | R | 1415 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00346 | Edgepoint | 16.3802 | 119.8939 | 0.72 | Terrestrial Optical Fiber Drop | 0.34 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0581 | 1 | 581 | 581 | 0501725016 | Region V (Bicol Region) | Camarines Sur | Ocampo | Poblacion West | 13.5591 | 123.3747 | R | 894 | 212 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.72 | Terrestrial Optical Fiber Drop | 0.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0582 | 1 | 582 | 582 | 0102806011 | Region I (Ilocos Region) | Ilocos Norte | Burgos | Poblacion | 18.5124 | 120.6439 | R | 1490 | 402 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-02617 | Edgepoint | 18.5104 | 120.6401 | 0.45 | Terrestrial Optical Fiber Drop | 0.34 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0583 | 1 | 583 | 583 | 0203134016 | Region II (Cagayan Valley) | Isabela | Santa Maria | San Antonio | 17.4771 | 121.7575 | R | 1561 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ISA_0016 | LDIC | 121.7628 | 17.4833 | 0.89 | Terrestrial Optical Fiber Drop | 0.34 | 4.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0584 | 1 | 584 | 584 | 0603009002 | Region VI (Western Visayas) | Iloilo | Batad | Alinsolong | 11.4183 | 123.1111 | R | 1335 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.59 | Terrestrial Optical Fiber Drop | 0.34 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0585 | 1 | 585 | 585 | 0501709015 | Region V (Bicol Region) | Camarines Sur | Camaligan | Santo Tomas | 13.621 | 123.1656 | R | 705 | 167 | 50 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.5 | Terrestrial Optical Fiber Drop | 0.7 | 1.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0586 | 1 | 586 | 586 | 0304921008 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Poblacion III | 15.3516 | 121.001 | R | 1405 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0184 | FTAP Smart | 15.3526 | 121.0171 | 0.46 | Terrestrial Optical Fiber Drop | 1.74 | 6.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0587 | 1 | 587 | 587 | 0300810001 | Region III (Central Luzon) | Bataan | Orion | Arellano | 14.618 | 120.5771 | R | 539 | 149 | 45 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0398 | FTAP Smart | 14.6168 | 120.5791 | 0.42 | Terrestrial Optical Fiber Drop | 0.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0588 | 1 | 588 | 588 | 0405802009 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Roque | 14.5844 | 121.1737 | U | 67126 | 18646 | 5594 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01743 | Edgepoint | 14.5861 | 121.1735 | 0.18 | Terrestrial Optical Fiber Drop | 0.35 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0589 | 1 | 589 | 589 | 0405812005 | Region IV-A (CALABARZON) | Rizal | Tanay | Kaybuto | 14.4976 | 121.2811 | U | 8757 | 2432 | 730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00800-A04 | PTCI/MIDC | 14.4978 | 121.2849 | 0.41 | Terrestrial Optical Fiber Drop | 0.35 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0590 | 1 | 590 | 590 | 0105514011 | Region I (Ilocos Region) | Pangasinan | Bolinao | Germinal | 16.3861 | 119.894 | U | 2899 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00346 | Edgepoint | 16.3802 | 119.8939 | 0.65 | Terrestrial Optical Fiber Drop | 0.35 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0591 | 1 | 591 | 591 | 0403422005 | Region IV-A (CALABARZON) | Laguna | Pila | Bulilan Sur | 14.234 | 121.3661 | U | 3816 | 1156 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.51 | Terrestrial Optical Fiber Drop | 0.35 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0592 | 1 | 592 | 592 | 0405807015 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Special District | 14.3541 | 121.324 | R | 4320 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01908 | Edgepoint | 14.3513 | 121.3253 | 0.34 | Terrestrial Optical Fiber Drop | 0.35 | 11.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0593 | 1 | 593 | 593 | 0201516023 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Magapit | 18.1285 | 121.6791 | U | 4128 | 1058 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020016 | FTAP Globe | 18.1207 | 121.6801 | 0.87 | Terrestrial Optical Fiber Drop | 0.35 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0594 | 1 | 594 | 594 | 1001306014 | Region X (Northern Mindanao) | Bukidnon | Kadingilan | Poblacion | 7.6014 | 124.91 | U | 7059 | 1857 | 557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0014 | PTCI/MIDC | 7.605 | 124.9048 | 0.7 | Terrestrial Optical Fiber Drop | 0.35 | 8.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0595 | 1 | 595 | 595 | 0306903003 | Region III (Central Luzon) | Tarlac | Camiling | Anoling 3rd | 15.6474 | 120.3884 | R | 1393 | 357 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-TAR-02715 | Edgepoint | 15.6897 | 120.4131 | 0.33 | Terrestrial Optical Fiber Drop | 2.42 | 2.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0596 | 1 | 596 | 596 | 0603026011 | Region VI (Western Visayas) | Iloilo | Leganes | Gua-an | 10.7881 | 122.59 | R | 1299 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.68 | Terrestrial Optical Fiber Drop | 0.29 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0597 | 1 | 597 | 597 | 0603044033 | Region VI (Western Visayas) | Iloilo | Sara | Poblacion Ilawod | 11.2573 | 123.0194 | U | 1790 | 471 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.63 | Terrestrial Optical Fiber Drop | 0.35 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0598 | 1 | 598 | 598 | 1381100183 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 183 | 14.5239 | 121.0131 | U | 41113 | 12420 | 3726 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | A00025-A02 | PTCI/MIDC | 14.5259 | 121.0143 | 0.26 | Terrestrial Optical Fiber Drop | 0.35 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0599 | 1 | 599 | 599 | 0201526011 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Centro Sur | 17.8813 | 121.571 | R | 2542 | 651 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01127-B06 | PTCI/MIDC | 17.8862 | 121.5706 | 0.55 | Terrestrial Optical Fiber Drop | 0.35 | 7.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0600 | 1 | 600 | 600 | 1381500012 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Santa Ana | 14.5255 | 121.0754 | U | 24174 | 6089 | 1827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000618 | FTAP Globe | 14.526 | 121.074 | 0.16 | Terrestrial Optical Fiber Drop | 0.35 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0601 | 1 | 601 | 601 | 0931700012 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Buenavista | 7.2389 | 122.2581 | U | 8501 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0080 | PTCI/MIDC | 7.2415 | 122.2622 | 0.54 | Terrestrial Optical Fiber Drop | 0.35 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0602 | 1 | 602 | 602 | 0603019007 | Region VI (Western Visayas) | Iloilo | Estancia | Cano-an | 11.4575 | 123.1296 | U | 2847 | 749 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060014 | FTAP BTS | 11.4586 | 123.1301 | 0.14 | Terrestrial Optical Fiber Drop | 0.35 | 2.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0603 | 1 | 603 | 603 | 0403417002 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Alibungbungan | 14.139 | 121.4181 | R | 2161 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02122-C08 | PTCI/MIDC | 14.1344 | 121.4104 | 0.98 | Terrestrial Optical Fiber Drop | 0.35 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0604 | 1 | 604 | 604 | 0403423005 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 2 | 14.113 | 121.3947 | R | 2020 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.31 | Terrestrial Optical Fiber Drop | 0.35 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0605 | 1 | 605 | 605 | 1381300031 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Doña Imelda | 14.6153 | 121.0183 | U | 17695 | 4390 | 1317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01633 | Edgepoint | 14.6133 | 121.0179 | 0.23 | Terrestrial Optical Fiber Drop | 0.35 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0606 | 1 | 606 | 606 | 0402106013 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc I | 14.2986 | 120.9559 | U | 8066 | 2372 | 712 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.69 | Terrestrial Optical Fiber Drop | 0.35 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0607 | 1 | 607 | 607 | 0631000098 | Region VI (Western Visayas) | Iloilo | City of Iloilo | M. V. Hechanova | 10.7473 | 122.5641 | U | 4301 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.68 | Terrestrial Optical Fiber Drop | 0.35 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0608 | 1 | 608 | 608 | 0731300017 | Region VII (Central Visayas) | Cebu | City of Mandaue | Maguikay | 10.341 | 123.9365 | U | 14971 | 4277 | 1283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070336 | FTAP Globe | 10.3399 | 123.9305 | 0.67 | Terrestrial Optical Fiber Drop | 0.35 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0609 | 1 | 609 | 609 | 0103306031 | Region I (Ilocos Region) | La Union | Bangar | Reyna Regente | 16.8926 | 120.4282 | R | 1122 | 303 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.54 | Terrestrial Optical Fiber Drop | 0.35 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0610 | 1 | 610 | 610 | 1204704032 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Poblacion | 7.0067 | 125.0899 | U | 23166 | 6096 | 1829 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NOC_0003 | LDIC | 7.0053 | 125.0887 | 0.2 | Terrestrial Optical Fiber Drop | 0.36 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0611 | 1 | 611 | 611 | 0203131028 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone II | 16.9825 | 122.0147 | R | 2552 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.59 | Terrestrial Optical Fiber Drop | 0.36 | 17.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0612 | 1 | 612 | 612 | 0704606025 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Tinago | 9.3624 | 122.8083 | U | 3322 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0009 | PTCI/MIDC | 9.3595 | 122.8171 | 1.02 | Terrestrial Optical Fiber Drop | 0.35 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0613 | 1 | 613 | 613 | 1430300076 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | New Lucban | 16.4225 | 120.5948 | R | 2082 | 547 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0023 | PTCI/MIDC | 16.4221 | 120.5951 | 0.06 | Terrestrial Optical Fiber Drop | 0.36 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0614 | 1 | 614 | 614 | 0403405049 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Real | 14.1985 | 121.1492 | U | 17945 | 5437 | 1631 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040256 | FTAP Globe | 14.1944 | 121.147 | 0.52 | Terrestrial Optical Fiber Drop | 0.36 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0615 | 1 | 615 | 615 | 1004308062 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Punong | 8.8423 | 125.1534 | R | 1080 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100111 | FTAP Globe | 8.8451 | 125.1592 | 0.71 | Terrestrial Optical Fiber Drop | 0.36 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0616 | 1 | 616 | 616 | 0402121002 | Region IV-A (CALABARZON) | Cavite | Ternate | Poblacion II | 14.2863 | 120.7176 | R | 2111 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.59 | Terrestrial Optical Fiber Drop | 0.36 | 2.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0617 | 1 | 617 | 617 | 1380200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Uno | 14.4385 | 121.0024 | U | 42677 | 10999 | 3300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000694 | FTAP Globe | 14.4372 | 121.0013 | 0.19 | Terrestrial Optical Fiber Drop | 0.36 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0618 | 1 | 618 | 618 | 0102926005 | Region I (Ilocos Region) | Ilocos Sur | Santa Maria | Baliw Laud | 17.3812 | 120.4821 | R | 645 | 169 | 51 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01267-B05 | PTCI/MIDC | 17.3721 | 120.4847 | 0.21 | Terrestrial Optical Fiber Drop | 0.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0619 | 1 | 619 | 619 | 0402115016 | Region IV-A (CALABARZON) | Cavite | Naic | Latoria | 14.3098 | 120.772 | R | 2301 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4395 | FTAP Smart | 14.3166 | 120.7682 | 0.42 | Terrestrial Optical Fiber Drop | 1.32 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0620 | 1 | 620 | 620 | 0403408020 | Region IV-A (CALABARZON) | Laguna | Famy | Tunhac | 14.4387 | 121.4499 | U | 2145 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040101 | FTAP Globe | 14.4377 | 121.4463 | 0.41 | Terrestrial Optical Fiber Drop | 0.36 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0621 | 1 | 621 | 621 | 0402103051 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Niog II | 14.4539 | 120.9581 | U | 7376 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.56 | Terrestrial Optical Fiber Drop | 0.36 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0622 | 1 | 622 | 622 | 0105544046 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion East | 15.9267 | 120.8424 | U | 1858 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 0.67 | Terrestrial Optical Fiber Drop | 0.36 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0623 | 1 | 623 | 623 | 0301406010 | Region III (Central Luzon) | Bulacan | Bustos | Poblacion | 14.9558 | 120.919 | U | 8636 | 2467 | 740 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00979-B07 | PTCI/MIDC | 14.956 | 120.921 | 0.21 | Terrestrial Optical Fiber Drop | 0.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0624 | 1 | 624 | 624 | 0603009012 | Region VI (Western Visayas) | Iloilo | Batad | Caw-i | 11.4177 | 123.1098 | R | 905 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0007 | PTCI/MIDC | 11.4231 | 123.109 | 0.61 | Terrestrial Optical Fiber Drop | 0.36 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0625 | 1 | 625 | 625 | 0201528023 | Region II (Cagayan Valley) | Cagayan | Tuao | Naruangan | 17.6693 | 121.5151 | R | 2164 | 554 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020036 | FTAP Globe | 17.6721 | 121.5173 | 0.39 | Terrestrial Optical Fiber Drop | 0.36 | 8.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0626 | 1 | 626 | 626 | 0803738076 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Punta | 11.009 | 124.5999 | U | 4544 | 1195 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0045 | PTCI/MIDC | 11.0153 | 124.6014 | 0.72 | Terrestrial Optical Fiber Drop | 0.36 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0627 | 1 | 627 | 627 | 0501724004 | Region V (Bicol Region) | Camarines Sur | City of Naga | Balatas | 13.6311 | 123.2015 | U | 11086 | 2639 | 792 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S95 | FTAP Smart | 13.6322 | 123.1997 | 0.23 | Terrestrial Optical Fiber Drop | 0.36 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0628 | 1 | 628 | 628 | 0306914007 | Region III (Central Luzon) | Tarlac | San Manuel | Poblacion | 15.7997 | 120.6081 | R | 1616 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01805-B07 | PTCI/MIDC | 15.8018 | 120.6063 | 0.29 | Terrestrial Optical Fiber Drop | 0.36 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0629 | 1 | 629 | 629 | 0205702007 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Gundaway | 16.5203 | 121.528 | U | 3953 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQRG0002 | PTCI/MIDC | 16.5179 | 121.5264 | 0.32 | Terrestrial Optical Fiber Drop | 0.36 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0630 | 1 | 630 | 630 | 0631000135 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Quintin Salas | 10.7428 | 122.5648 | U | 5438 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060164 | FTAP BTS | 10.7393 | 122.5632 | 0.43 | Terrestrial Optical Fiber Drop | 0.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0631 | 1 | 631 | 631 | 0431200021 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Iyam | 13.9307 | 121.6093 | U | 28220 | 7055 | 2117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02698 | Edgepoint | 13.9316 | 121.6129 | 0.39 | Terrestrial Optical Fiber Drop | 0.36 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0632 | 1 | 632 | 632 | 0630200051 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Mansilingan | 10.6195 | 122.9762 | U | 53935 | 14981 | 4494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0006 | PTCI/MIDC | 10.6237 | 122.9796 | 0.89 | Terrestrial Optical Fiber Drop | 1.55 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0633 | 1 | 633 | 633 | 0102820022 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | Santa Asuncion | 18.1725 | 120.596 | R | 937 | 253 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.17 | Terrestrial Optical Fiber Drop | 0.37 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0634 | 1 | 634 | 634 | 1130700152 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 19-B | 7.0944 | 125.6036 | U | 31998 | 9411 | 2823 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSR0042 | PTCI/MIDC | 7.1049 | 125.6016 | 1.18 | Terrestrial Optical Fiber Drop | 0.37 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0635 | 1 | 635 | 635 | 0401012047 | Region IV-A (CALABARZON) | Batangas | Lemery | Wawa Ilaya | 13.8757 | 120.9136 | R | 1499 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01950-C08 | PTCI/MIDC | 13.8765 | 120.9183 | 0.51 | Terrestrial Optical Fiber Drop | 0.36 | 2.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0636 | 1 | 636 | 636 | 0102808015 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Pias Norte | 17.9919 | 120.5027 | R | 946 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010029 | FTAP Globe | 18.006 | 120.5028 | 1.57 | Terrestrial Optical Fiber Drop | 0.37 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0637 | 1 | 637 | 637 | 0500517015 | Region V (Bicol Region) | Albay | City of Tabaco | Cobo | 13.3508 | 123.7286 | R | 3451 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ALB-02560 | Edgepoint | 13.3488 | 123.728 | 0.23 | Terrestrial Optical Fiber Drop | 0.37 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0638 | 1 | 638 | 638 | 1230800034 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | City Heights | 6.1256 | 125.1742 | U | 25207 | 6463 | 1939 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0017 | PTCI/MIDC | 6.1297 | 125.1743 | 0.45 | Terrestrial Optical Fiber Drop | 0.37 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0639 | 1 | 639 | 639 | 0203122002 | Region II (Cagayan Valley) | Isabela | Quezon | Alunan | 17.3118 | 121.6093 | R | 1340 | 352 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0003 | LDIC | 121.6055 | 17.3127 | 0.42 | Terrestrial Optical Fiber Drop | 0.37 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0640 | 1 | 640 | 640 | 1403213037 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Dagupan Weste | 17.4739 | 121.4658 | U | 4743 | 1103 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140131 | FTAP Globe | 17.4672 | 121.4677 | 0.78 | Terrestrial Optical Fiber Drop | 0.37 | 3.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0641 | 1 | 641 | 641 | 0501736015 | Region V (Bicol Region) | Camarines Sur | Tigaon | Poblacion | 13.6332 | 123.4959 | U | 3068 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.52 | Terrestrial Optical Fiber Drop | 0.37 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0642 | 1 | 642 | 642 | 0403419013 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Barangay II | 14.2752 | 121.4533 | U | 2128 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.17 | Terrestrial Optical Fiber Drop | 0.37 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0643 | 1 | 643 | 643 | 0603036003 | Region VI (Western Visayas) | Iloilo | Pavia | Anilao | 10.7776 | 122.5392 | R | 1380 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 0.19 | Terrestrial Optical Fiber Drop | 0.54 | 4.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0644 | 1 | 644 | 644 | 1600314024 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Kolambugan | 9.0311 | 125.7891 | R | 2105 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.84 | Terrestrial Optical Fiber Drop | 22.15 | 19.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0645 | 1 | 645 | 645 | 0501721015 | Region V (Bicol Region) | Camarines Sur | Milaor | San Jose | 13.5993 | 123.1779 | U | 2260 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050093 | FTAP Globe | 13.5996 | 123.1749 | 0.33 | Terrestrial Optical Fiber Drop | 0.37 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0646 | 1 | 646 | 646 | 0701205016 | Region VII (Central Visayas) | Bohol | Baclayon | Taguihon | 9.625 | 123.9219 | R | 2119 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070157 | FTAP BTS | 9.654 | 123.8788 | 4.72 | Terrestrial Optical Fiber Drop | 0.99 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0647 | 1 | 647 | 647 | 0908305013 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Lower Ipil Heights | 7.7835 | 122.5843 | R | 1497 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090142 | FTAP Globe | 7.7821 | 122.5819 | 0.38 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0648 | 1 | 648 | 648 | 0405804021 | Region IV-A (CALABARZON) | Rizal | Binangonan | Limbon-limbon | 14.4414 | 121.2056 | R | 1629 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01901 | Edgepoint | 14.4417 | 121.2063 | 0.08 | Terrestrial Optical Fiber Drop | 0.37 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0649 | 1 | 649 | 649 | 0506211001 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Norte | 12.8241 | 123.8424 | R | 1413 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 0.49 | Terrestrial Optical Fiber Drop | 0.37 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0650 | 1 | 650 | 650 | 0402113024 | Region IV-A (CALABARZON) | Cavite | Maragondon | Garita I B | 14.2768 | 120.7341 | R | 1655 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.45 | Terrestrial Optical Fiber Drop | 0.37 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0651 | 1 | 651 | 651 | 0431200008 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 5 | 13.9358 | 121.6095 | U | 2387 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040447 | FTAP Globe | 13.9371 | 121.6094 | 0.14 | Terrestrial Optical Fiber Drop | 0.37 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0652 | 1 | 652 | 652 | 1380200018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Tres | 14.4407 | 121.004 | U | 33192 | 8298 | 2489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00293-A03 | PTCI/MIDC | 14.4377 | 121.0059 | 0.39 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0653 | 1 | 653 | 653 | 1402701016 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Poblacion | 16.9141 | 121.0601 | R | 2686 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.57 | Terrestrial Optical Fiber Drop | 0.37 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0654 | 1 | 654 | 654 | 0402103039 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi II | 14.4599 | 120.9524 | R | 2928 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00687-A03 | PTCI/MIDC | 14.4623 | 120.969 | 0.31 | Terrestrial Optical Fiber Drop | 0.74 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0655 | 1 | 655 | 655 | 0304924009 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Poblacion | 15.3067 | 120.8554 | R | 2148 | 613 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00768 | Edgepoint | 15.3047 | 120.8562 | 0.24 | Terrestrial Optical Fiber Drop | 0.37 | 3.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0656 | 1 | 656 | 656 | 0506211002 | Region V (Bicol Region) | Sorsogon | Magallanes | Aguada Sur | 12.8187 | 123.841 | R | 1249 | 312 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 0.16 | Terrestrial Optical Fiber Drop | 0.37 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0657 | 1 | 657 | 657 | 0105505014 | Region I (Ilocos Region) | Pangasinan | Anda | Poblacion | 16.2866 | 119.9508 | U | 3823 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00370 | Edgepoint | 16.2909 | 119.9464 | 0.67 | Terrestrial Optical Fiber Drop | 0.37 | 6.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0658 | 1 | 658 | 658 | 0803715031 | Region VIII (Eastern Visayas) | Leyte | Carigara | Ponong | 11.3015 | 124.6865 | R | 2495 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 1.01 | Terrestrial Optical Fiber Drop | 0.37 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0659 | 1 | 659 | 659 | 0803738068 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Mas-in | 11.0632 | 124.5147 | R | 1937 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080191 | FTAP BTS | 11.0648 | 124.5167 | 0.28 | Terrestrial Optical Fiber Drop | 0.37 | 3.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0660 | 1 | 660 | 660 | 0205010027 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Castillo Village | 16.3547 | 120.8926 | R | 783 | 206 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01524-B05 | PTCI/MIDC | 16.3482 | 120.9094 | 1.93 | Terrestrial Optical Fiber Drop | 0.37 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0661 | 1 | 661 | 661 | 0600413008 | Region VI (Western Visayas) | Aklan | Malinao | Kinalangay Nuevo | 11.6231 | 122.2935 | R | 916 | 234 | 70 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060219 | FTAP Globe | 11.6476 | 122.3063 | 3.05 | Terrestrial Optical Fiber Drop | 0.37 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0662 | 1 | 662 | 662 | 0506216010 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Buenavista | 13.039 | 124.1073 | R | 2073 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03189-C10 | PTCI/MIDC | 13.0209 | 124.102 | 2.1 | Terrestrial Optical Fiber Drop | 0.37 | 9.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0663 | 1 | 663 | 663 | 1380200019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Talon Kuatro | 14.435 | 121.0036 | U | 17656 | 4850 | 1455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000694 | FTAP Globe | 14.4372 | 121.0013 | 0.35 | Terrestrial Optical Fiber Drop | 0.37 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0664 | 1 | 664 | 664 | 0301420041 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan Proper | 14.8447 | 121.0801 | U | 48261 | 13788 | 4136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02432-B07 | PTCI/MIDC | 14.8426 | 121.0785 | 0.29 | Terrestrial Optical Fiber Drop | 0.37 | 4.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0665 | 1 | 665 | 665 | 1001314006 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Diclum | 8.3736 | 124.8495 | R | 5043 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 1.6 | Terrestrial Optical Fiber Drop | 0.37 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0666 | 1 | 666 | 666 | 0304905015 | Region III (Central Luzon) | Nueva Ecija | Carranglan | Joson | 15.9483 | 120.9778 | U | 6074 | 1735 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00510 | Edgepoint | 15.9515 | 120.9795 | 0.4 | Terrestrial Optical Fiber Drop | 0.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0667 | 1 | 667 | 667 | 0300810012 | Region III (Central Luzon) | Bataan | Orion | Daang Bilolo | 14.6181 | 120.577 | R | 3206 | 890 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0398 | FTAP Smart | 14.6168 | 120.5791 | 0.27 | Terrestrial Optical Fiber Drop | 0.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0668 | 1 | 668 | 668 | 0102933019 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Farola | 16.9328 | 120.4475 | R | 1027 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.45 | Terrestrial Optical Fiber Drop | 0.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0669 | 1 | 669 | 669 | 0908305009 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Ipil Heights | 7.7836 | 122.5842 | R | 3976 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090142 | FTAP Globe | 7.7821 | 122.5819 | 0.3 | Terrestrial Optical Fiber Drop | 0.38 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0670 | 1 | 670 | 670 | 0405648021 | Region IV-A (CALABARZON) | Quezon | Tiaong | Quipot | 13.9596 | 121.3203 | U | 3810 | 1002 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040409 | FTAP Globe | 13.9631 | 121.3238 | 0.54 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0671 | 1 | 671 | 671 | 0803738051 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Don Felipe Larrazabal | 11.0112 | 124.6042 | U | 1669 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080355 | FTAP Globe | 11.0081 | 124.6074 | 0.48 | Terrestrial Optical Fiber Drop | 0.38 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0672 | 1 | 672 | 672 | 0301423017 | Region III (Central Luzon) | Bulacan | Santa Maria | Pulong Buhangin | 14.8666 | 120.997 | U | 43084 | 12309 | 3693 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00971-B07 | PTCI/MIDC | 14.8646 | 120.9966 | 0.22 | Terrestrial Optical Fiber Drop | 0.38 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0673 | 1 | 673 | 673 | 1381701006 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | San Roque | 14.5421 | 121.0707 | U | 4897 | 1278 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01837 | Edgepoint | 14.5422 | 121.0702 | 0.05 | Terrestrial Optical Fiber Drop | 0.38 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0674 | 1 | 674 | 674 | 0405641018 | Region IV-A (CALABARZON) | Quezon | San Antonio | Sampaguita | 13.8889 | 121.2865 | R | 1978 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03161-C08 | PTCI/MIDC | 13.8725 | 121.2905 | 1.88 | Terrestrial Optical Fiber Drop | 0.38 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0675 | 1 | 675 | 675 | 0307103003 | Region III (Central Luzon) | Zambales | Candelaria | Catol | 15.621 | 119.9347 | R | 1349 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.57 | Terrestrial Optical Fiber Drop | 0.38 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0676 | 1 | 676 | 676 | 0201505002 | Region II (Cagayan Valley) | Cagayan | Aparri | Bangag | 18.2982 | 121.559 | R | 1886 | 483 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020012 | FTAP Globe | 18.2954 | 121.5634 | 0.55 | Terrestrial Optical Fiber Drop | 0.38 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0677 | 1 | 677 | 677 | 0300811001 | Region III (Central Luzon) | Bataan | Pilar | Ala-uli | 14.6457 | 120.5386 | U | 5656 | 1571 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.2 | Terrestrial Optical Fiber Drop | 0.38 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0678 | 1 | 678 | 678 | 1381300029 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Del Monte | 14.6445 | 121.0129 | U | 10819 | 2725 | 818 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02254 | Edgepoint | 14.6418 | 121.013 | 0.3 | Terrestrial Optical Fiber Drop | 0.38 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0679 | 1 | 679 | 679 | 1001309026 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Poblacion | 7.6342 | 125.0065 | R | 5364 | 1411 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100218 | FTAP Globe | 7.6065 | 125.0055 | 3.08 | Terrestrial Optical Fiber Drop | 0.38 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0680 | 1 | 680 | 680 | 0205006010 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Poblacion | 16.6604 | 121.3652 | R | 3966 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NUV_0006 | LDIC | 121.3694 | 16.6623 | 0.49 | Terrestrial Optical Fiber Drop | 0.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0681 | 1 | 681 | 681 | 0600401009 | Region VI (Western Visayas) | Aklan | Altavas | Man-up | 11.5342 | 122.4758 | R | 1148 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 3.16 | Terrestrial Optical Fiber Drop | 1.18 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0682 | 1 | 682 | 682 | 0203131027 | Region II (Cagayan Valley) | Isabela | San Mariano | Zone I | 16.9838 | 122.0098 | R | 1647 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01361-B06 | PTCI/MIDC | 16.982 | 122.0092 | 0.21 | Terrestrial Optical Fiber Drop | 0.38 | 16.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0683 | 1 | 683 | 683 | 0506215013 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Roque | 12.6456 | 124.1051 | R | 1208 | 302 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.75 | Terrestrial Optical Fiber Drop | 0.07 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0684 | 1 | 684 | 684 | 0603035039 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilawod | 11.1052 | 122.6427 | U | 6043 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.47 | Terrestrial Optical Fiber Drop | 0.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0685 | 1 | 685 | 685 | 0405808011 | Region IV-A (CALABARZON) | Rizal | Rodriguez | San Rafael | 14.7325 | 121.1584 | U | 30559 | 8488 | 2546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01253 | Edgepoint | 14.7353 | 121.1563 | 0.38 | Terrestrial Optical Fiber Drop | 0.39 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0686 | 1 | 686 | 686 | 0300806015 | Region III (Central Luzon) | Bataan | Limay | St. Francis II | 14.5719 | 120.5924 | U | 13425 | 3729 | 1119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-03011 | Edgepoint | 120.5896 | 14.5707 | 0.33 | Terrestrial Optical Fiber Drop | 0.39 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0687 | 1 | 687 | 687 | 0405808001 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Balite | 14.7325 | 121.1445 | U | 8169 | 2269 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01264 | Edgepoint | 14.7303 | 121.1441 | 0.25 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0688 | 1 | 688 | 688 | 0306909012 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan West | 15.7204 | 120.5705 | R | 1351 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01796-B07 | PTCI/MIDC | 15.7192 | 120.5771 | 0.71 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0689 | 1 | 689 | 689 | 0403410018 | Region IV-A (CALABARZON) | Laguna | Liliw | Ilayang Palina | 14.134 | 121.4335 | R | 2517 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02121-C08 | PTCI/MIDC | 14.1337 | 121.4379 | 0.48 | Terrestrial Optical Fiber Drop | 0.39 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0690 | 1 | 690 | 690 | 1600308017 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 3 | 8.5072 | 125.9725 | U | 3575 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.91 | Terrestrial Optical Fiber Drop | 0.39 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0691 | 1 | 691 | 691 | 0702218007 | Region VII (Central Visayas) | Cebu | Compostela | Cogon | 10.4553 | 124.0092 | U | 8155 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0061 | PTCI/MIDC | 10.4566 | 124.0086 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0692 | 1 | 692 | 692 | 0307106011 | Region III (Central Luzon) | Zambales | Masinloc | South Poblacion | 15.5343 | 119.95 | R | 4617 | 1215 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0012 | PTCI/MIDC | 15.5354 | 119.9518 | 0.22 | Terrestrial Optical Fiber Drop | 0.39 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0693 | 1 | 693 | 693 | 0203137033 | Region II (Cagayan Valley) | Isabela | Tumauini | Namnama | 17.2908 | 121.8706 | R | 1672 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0044 | PTCI/MIDC | 17.2915 | 121.8697 | 0.12 | Terrestrial Optical Fiber Drop | 0.39 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0694 | 1 | 694 | 694 | 0501718013 | Region V (Bicol Region) | Camarines Sur | Libmanan | Begajo Sur | 13.6955 | 123.0674 | R | 1097 | 261 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02007 | Edgepoint | 13.6955 | 123.0601 | 0.79 | Terrestrial Optical Fiber Drop | 0.39 | 7.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0695 | 1 | 695 | 695 | 0500514014 | Region V (Bicol Region) | Albay | Polangui | Centro Oriental | 13.2948 | 123.4865 | U | 2019 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 0.81 | Terrestrial Optical Fiber Drop | 0.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0696 | 1 | 696 | 696 | 0301420040 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan V | 14.8445 | 121.0802 | R | 2300 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BUL_0009 | LDIC | 14.7988 | 121.0417 | 0.26 | Terrestrial Optical Fiber Drop | 0.39 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0697 | 1 | 697 | 697 | 0501723031 | Region V (Bicol Region) | Camarines Sur | Nabua | San Nicolas | 13.4038 | 123.3709 | R | 1105 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02601 | Edgepoint | 13.4058 | 123.3723 | 0.27 | Terrestrial Optical Fiber Drop | 0.39 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0698 | 1 | 698 | 698 | 1402709008 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Piwong | 16.8456 | 121.0932 | R | 1248 | 320 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-IFU-00249 | Edgepoint | 16.8463 | 121.1071 | 1.49 | Terrestrial Optical Fiber Drop | 0.39 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0699 | 1 | 699 | 699 | 1600206001 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Bangayan | 9.3608 | 125.5528 | R | 1767 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130057 | FTAP Globe | 9.264 | 125.5612 | 10.8 | Terrestrial Optical Fiber Drop | 0.39 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0700 | 1 | 700 | 700 | 0603039024 | Region VI (Western Visayas) | Iloilo | San Enrique | Poblacion Ilaya | 11.0735 | 122.6593 | R | 1219 | 320 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 3.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0701 | 1 | 701 | 701 | 1102411007 | Region XI (Davao Region) | Davao del Sur | Padada | N C Ordaneza District | 6.638 | 125.3416 | U | 2238 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.77 | Terrestrial Optical Fiber Drop | 0.39 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0702 | 1 | 702 | 702 | 0405639013 | Region IV-A (CALABARZON) | Quezon | Sampaloc | Ilayang Owain | 14.1621 | 121.6414 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03371-C08 | PTCI/MIDC | 14.1619 | 121.639 | 0.26 | Terrestrial Optical Fiber Drop | 0.39 | 9.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0703 | 1 | 703 | 703 | 0403418009 | Region IV-A (CALABARZON) | Laguna | Paete | Quinale | 14.3617 | 121.4834 | U | 7953 | 2410 | 723 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.88 | Terrestrial Optical Fiber Drop | 0.39 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0704 | 1 | 704 | 704 | 0506202018 | Region V (Bicol Region) | Sorsogon | Barcelona | Poblacion Central | 12.8664 | 124.1436 | R | 1062 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050219 | FTAP Globe | 12.8603 | 124.1471 | 0.77 | Terrestrial Optical Fiber Drop | 0.39 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0705 | 1 | 705 | 705 | 0203101010 | Region II (Cagayan Valley) | Isabela | Alicia | Calaocan | 16.7814 | 121.6913 | U | 3769 | 991 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 0.36 | Terrestrial Optical Fiber Drop | 0.39 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0706 | 1 | 706 | 706 | 1004310011 | Region X (Northern Mindanao) | Misamis Oriental | Initao | Poblacion | 8.4975 | 124.3062 | U | 8103 | 2077 | 623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100140 | FTAP Globe | 8.4972 | 124.3038 | 0.27 | Terrestrial Optical Fiber Drop | 0.4 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0707 | 1 | 707 | 707 | 0201525015 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Centro West | 18.2474 | 121.9073 | R | 1745 | 447 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01129-B06 | PTCI/MIDC | 18.2464 | 121.9084 | 0.15 | Terrestrial Optical Fiber Drop | 0.39 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0708 | 1 | 708 | 708 | 0203132002 | Region II (Cagayan Valley) | Isabela | San Mateo | Bagong Sikat | 16.8831 | 121.5878 | R | 2602 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01370-B06 | PTCI/MIDC | 16.8794 | 121.5907 | 0.52 | Terrestrial Optical Fiber Drop | 0.39 | 11.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0709 | 1 | 709 | 709 | 0504101031 | Region V (Bicol Region) | Masbate | Aroroy | Poblacion | 12.5107 | 123.3952 | U | 4099 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.24 | Terrestrial Optical Fiber Drop | 0.39 | 4.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1001 | 1 | 710 | 710 | 0600411015 | Region VI (Western Visayas) | Aklan | Makato | Poblacion | 11.7125 | 122.29 | R | 3445 | 883 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.35 | Terrestrial Optical Fiber Drop | 0.54 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0711 | 1 | 711 | 711 | 0506212012 | Region V (Bicol Region) | Sorsogon | Matnog | Caloocan | 12.5835 | 124.0838 | R | 1082 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050233 | FTAP Globe | 12.59 | 124.0937 | 1.3 | Terrestrial Optical Fiber Drop | 0.4 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0712 | 1 | 712 | 712 | 0402109085 | Region IV-A (CALABARZON) | Cavite | City of Imus | Pasong Buaya II | 14.3899 | 120.9649 | U | 37476 | 11022 | 3307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4076 | FTAP Smart | 14.3871 | 120.9619 | 0.45 | Terrestrial Optical Fiber Drop | 0.4 | 6.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0713 | 1 | 713 | 713 | 0501728005 | Region V (Bicol Region) | Camarines Sur | Pili | Cadlan | 13.5999 | 123.2539 | U | 5986 | 1425 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050094 | FTAP Globe | 13.5974 | 123.2574 | 0.47 | Terrestrial Optical Fiber Drop | 0.4 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0714 | 1 | 714 | 714 | 0702223040 | Region VII (Central Visayas) | Cebu | Danao City | Suba | 10.5245 | 124.0287 | U | 7790 | 2050 | 615 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.16 | Terrestrial Optical Fiber Drop | 0.4 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0715 | 1 | 715 | 715 | 1404409009 | Cordillera Administrative Region (CAR) | Mountain Province | Sagada | Demang | 17.0843 | 120.8981 | R | 702 | 189 | 57 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01407-B05 | PTCI/MIDC | 17.0819 | 120.9043 | 0.48 | Terrestrial Optical Fiber Drop | 0.28 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0716 | 1 | 716 | 716 | 0405622006 | Region IV-A (CALABARZON) | Quezon | Lopez | Gomez | 13.8861 | 122.2587 | U | 3496 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.41 | Terrestrial Optical Fiber Drop | 0.4 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0717 | 1 | 717 | 717 | 0403411012 | Region IV-A (CALABARZON) | Laguna | Los Baños | San Antonio | 14.1768 | 121.2451 | U | 17515 | 5307 | 1592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.31 | Terrestrial Optical Fiber Drop | 0.4 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0718 | 1 | 718 | 718 | 0203104007 | Region II (Cagayan Valley) | Isabela | Benito Soliven | District II | 16.9865 | 121.9588 | R | 2011 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0041 | LDIC | 16.9909 | 121.9458 | 1.47 | Terrestrial Optical Fiber Drop | 0.4 | 11.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0719 | 1 | 719 | 719 | 0105544047 | Region I (Ilocos Region) | Pangasinan | Umingan | Poblacion West | 15.928 | 120.8393 | U | 2419 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 0.41 | Terrestrial Optical Fiber Drop | 0.4 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0720 | 1 | 720 | 720 | 0304930042 | Region III (Central Luzon) | Nueva Ecija | Talavera | Pag-asa | 15.5846 | 120.9168 | U | 5626 | 1607 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030352 | FTAP Globe | 15.583 | 120.9117 | 0.57 | Terrestrial Optical Fiber Drop | 0.4 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0721 | 1 | 721 | 721 | 0702218014 | Region VII (Central Visayas) | Cebu | Compostela | Poblacion | 10.456 | 124.0115 | U | 12857 | 3383 | 1015 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0061 | PTCI/MIDC | 10.4566 | 124.0086 | 0.33 | Terrestrial Optical Fiber Drop | 0.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0722 | 1 | 722 | 722 | 1004321015 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Taboc | 8.517 | 124.5762 | U | 4039 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100132 | FTAP Globe | 8.5148 | 124.5755 | 0.25 | Terrestrial Optical Fiber Drop | 0.4 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0723 | 1 | 723 | 723 | 0300804013 | Region III (Central Luzon) | Bataan | Dinalupihan | Happy Valley | 14.847 | 120.4009 | R | 1998 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030583 | FTAP Globe | 14.8459 | 120.405 | 0.45 | Terrestrial Optical Fiber Drop | 0.4 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0724 | 1 | 724 | 724 | 0306917027 | Region III (Central Luzon) | Tarlac | Victoria | Santa Lucia | 15.5785 | 120.679 | R | 1640 | 420 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.2 | Terrestrial Optical Fiber Drop | 0.4 | 5.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0725 | 1 | 725 | 725 | 1380400017 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Santolan | 14.6854 | 120.9589 | U | 13736 | 3836 | 1151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0023 | PTCI/MIDC | 14.6847 | 120.9593 | 0.09 | Terrestrial Optical Fiber Drop | 0.4 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0726 | 1 | 726 | 726 | 0301419036 | Region III (Central Luzon) | Bulacan | San Ildefonso | Upig | 15.025 | 120.9922 | R | 2853 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-BUL-00932 | Edgepoint | 15.0225 | 120.973 | 2.08 | Terrestrial Optical Fiber Drop | 0.4 | 6.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0727 | 1 | 727 | 727 | 0402103030 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban III | 14.4608 | 120.9644 | R | 881 | 259 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.55 | Terrestrial Optical Fiber Drop | 0.54 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0728 | 1 | 728 | 728 | 1208007005 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Banate | 6.4742 | 125.3216 | R | 3940 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120294 | FTAP Globe | 6.4811 | 125.3261 | 0.91 | Terrestrial Optical Fiber Drop | 0.4 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0729 | 1 | 729 | 729 | 0306903064 | Region III (Central Luzon) | Tarlac | Camiling | Surgui 2nd | 15.6761 | 120.4145 | R | 1574 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00605 | Edgepoint | 15.6807 | 120.415 | 0.51 | Terrestrial Optical Fiber Drop | 0.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0730 | 1 | 730 | 730 | 0102906037 | Region I (Ilocos Region) | Ilocos Sur | City of Candon | San Isidro | 17.1882 | 120.446 | U | 1868 | 491 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03281-B05 | PTCI/MIDC | 17.1848 | 120.4469 | 0.4 | Terrestrial Optical Fiber Drop | 0.41 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0731 | 1 | 731 | 731 | 1402709006 | Cordillera Administrative Region (CAR) | Ifugao | Hingyon | Namulditan | 16.8426 | 121.0866 | R | 1012 | 259 | 78 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-IFU-00249 | Edgepoint | 16.8463 | 121.1071 | 2.22 | Terrestrial Optical Fiber Drop | 0.4 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0732 | 1 | 732 | 732 | 0603027025 | Region VI (Western Visayas) | Iloilo | Lemery | San Jose Moto | 11.227 | 122.925 | R | 1095 | 288 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0101 | PTCI/MIDC | 11.2258 | 122.9295 | 0.5 | Terrestrial Optical Fiber Drop | 0.4 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1003 | 1 | 733 | 733 | 0403416011 | Region IV-A (CALABARZON) | Laguna | Majayjay | Botocan | 14.1564 | 121.4907 | R | 1021 | 309 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.53 | Terrestrial Optical Fiber Drop | 2.67 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0734 | 1 | 734 | 734 | 0730600064 | Region VII (Central Visayas) | Cebu | City of Cebu | Sambag I | 10.2994 | 123.8956 | U | 11540 | 3606 | 1082 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0119 | PTCI/MIDC | 10.2993 | 123.8942 | 0.16 | Terrestrial Optical Fiber Drop | 0.4 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0735 | 1 | 735 | 735 | 0506204009 | Region V (Bicol Region) | Sorsogon | Bulusan | Madlawon | 12.7606 | 124.1362 | R | 1275 | 318 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050224 | FTAP Globe | 12.7527 | 124.1332 | 0.94 | Terrestrial Optical Fiber Drop | 0.41 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0736 | 1 | 736 | 736 | 0402103053 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu II | 14.4562 | 120.955 | R | 1833 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01868-C08 | PTCI/MIDC | 14.4511 | 120.9538 | 0.58 | Terrestrial Optical Fiber Drop | 0.4 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0737 | 1 | 737 | 737 | 0105506013 | Region I (Ilocos Region) | Pangasinan | Asingan | Dupac | 16.0085 | 120.6684 | R | 2391 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0024 | LDIC | 120.6617 | 16.0048 | 0.82 | Terrestrial Optical Fiber Drop | 0.41 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0738 | 1 | 738 | 738 | 0301423020 | Region III (Central Luzon) | Bulacan | Santa Maria | San Vicente | 14.8095 | 121.0127 | U | 25558 | 7302 | 2191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01013-B07 | PTCI/MIDC | 14.8125 | 121.0117 | 0.35 | Terrestrial Optical Fiber Drop | 0.41 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0739 | 1 | 739 | 739 | 0501701022 | Region V (Bicol Region) | Camarines Sur | Baao | San Ramon | 13.4545 | 123.3683 | R | 458 | 109 | 33 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050118 | FTAP Globe | 13.4568 | 123.3687 | 0.26 | Terrestrial Optical Fiber Drop | 0.41 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0740 | 1 | 740 | 740 | 0702239010 | Region VII (Central Visayas) | Cebu | Ronda | Palanas | 9.9966 | 123.4094 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0264 | PTCI/MIDC | 10.0263 | 123.4161 | 3.38 | Terrestrial Optical Fiber Drop | 0.41 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0741 | 1 | 741 | 741 | 0201507008 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Centro East | 18.4099 | 121.5176 | U | 4291 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-00013 | Edgepoint | 18.4074 | 121.515 | 0.39 | Terrestrial Optical Fiber Drop | 0.41 | 7.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0742 | 1 | 742 | 742 | 0405628021 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ilayang Yuni | 13.4536 | 122.5231 | R | 3428 | 902 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02052 | Edgepoint | 13.4535 | 122.5227 | 2.29 | Terrestrial Optical Fiber Drop | 1.98 | 12.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0743 | 1 | 743 | 743 | 0604509002 | Region VI (Western Visayas) | Negros Occidental | City of Escalante | Balintawak | 10.8394 | 123.4969 | U | 14659 | 3961 | 1188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0088 | PTCI/MIDC | 10.8432 | 123.499 | 0.49 | Terrestrial Optical Fiber Drop | 0.41 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0744 | 1 | 744 | 744 | 0203112045 | Region II (Cagayan Valley) | Isabela | Echague | San Fabian | 16.7122 | 121.6819 | U | 4156 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH020095 | FTAP Globe | 16.7091 | 121.6785 | 0.51 | Terrestrial Optical Fiber Drop | 0.41 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0745 | 1 | 745 | 745 | 0402116007 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael II | 14.4314 | 120.8797 | R | 3707 | 1090 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.43 | Terrestrial Optical Fiber Drop | 0.41 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0746 | 1 | 746 | 746 | 1130700137 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 4-A | 7.0707 | 125.6099 | U | 1761 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110487 | FTAP Globe | 7.0656 | 125.6094 | 0.57 | Terrestrial Optical Fiber Drop | 0.41 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0747 | 1 | 747 | 747 | 0300807013 | Region III (Central Luzon) | Bataan | Mariveles | Balon-Anito | 14.4365 | 120.4734 | U | 16526 | 4590 | 1377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1515 | FTAP Smart | 14.4338 | 120.4754 | 0.37 | Terrestrial Optical Fiber Drop | 0.41 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0748 | 1 | 748 | 748 | 1130700050 | Region XI (Davao Region) | Davao del Sur | City of Davao | Indangan | 7.1616 | 125.5957 | U | 25887 | 7613 | 2284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110320 | FTAP BTS | 7.1611 | 125.5956 | 0.06 | Terrestrial Optical Fiber Drop | 0.41 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0749 | 1 | 749 | 749 | 0803722021 | Region VIII (Eastern Visayas) | Leyte | Isabel | Santo Niño | 10.9285 | 124.4367 | U | 6550 | 1723 | 517 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080137 | FTAP BTS | 10.9299 | 124.4346 | 0.28 | Terrestrial Optical Fiber Drop | 0.41 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0750 | 1 | 750 | 750 | 0907322039 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Francisco | 7.8272 | 123.4387 | U | 3238 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090135 | FTAP Globe | 7.8243 | 123.4374 | 0.35 | Terrestrial Optical Fiber Drop | 0.41 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0751 | 1 | 751 | 751 | 0931700061 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Barangay Zone I | 6.907 | 122.0722 | U | 5011 | 1391 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0109 | PTCI/MIDC | 6.905 | 122.0706 | 0.28 | Terrestrial Optical Fiber Drop | 0.41 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0752 | 1 | 752 | 752 | 0405807008 | Region IV-A (CALABARZON) | Rizal | Jala-Jala | Pagkalinawan | 14.3155 | 121.3391 | R | 2030 | 563 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02370-A04 | PTCI/MIDC | 14.3075 | 121.3293 | 1.38 | Terrestrial Optical Fiber Drop | 0.41 | 8.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0753 | 1 | 753 | 753 | 1401110006 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Beckel | 16.4363 | 120.6316 | U | 4684 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00328 | Edgepoint | 16.4361 | 120.6292 | 0.25 | Terrestrial Optical Fiber Drop | 0.41 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0754 | 1 | 754 | 754 | 0103306010 | Region I (Ilocos Region) | La Union | Bangar | General Prim East | 16.899 | 120.4387 | R | 936 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.09 | Terrestrial Optical Fiber Drop | 1.6 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0755 | 1 | 755 | 755 | 0300808004 | Region III (Central Luzon) | Bataan | Morong | Poblacion | 14.6777 | 120.268 | U | 7656 | 2126 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00907-B07 | PTCI/MIDC | 14.6793 | 120.2702 | 0.29 | Terrestrial Optical Fiber Drop | 0.41 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0756 | 1 | 756 | 756 | 0402106067 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Andres II | 14.3179 | 120.9525 | R | 3585 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.4 | Terrestrial Optical Fiber Drop | 1.55 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0757 | 1 | 757 | 757 | 0504101037 | Region V (Bicol Region) | Masbate | Aroroy | Talabaan | 12.5106 | 123.3951 | R | 1558 | 380 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.26 | Terrestrial Optical Fiber Drop | 0.41 | 4.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0758 | 1 | 758 | 758 | 0304916007 | Region III (Central Luzon) | Nueva Ecija | Lupao | Bagong Flores | 15.8879 | 120.9 | R | 4328 | 1236 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01414-B07 | PTCI/MIDC | 15.8805 | 120.8984 | 0.84 | Terrestrial Optical Fiber Drop | 0.41 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0759 | 1 | 759 | 759 | 1600314015 | Region XIII (Caraga) | Agusan del Sur | Sibagat | Poblacion | 8.8236 | 125.6956 | U | 6338 | 1625 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0004 | PTCI/MIDC | 8.825 | 125.6929 | 0.33 | Terrestrial Optical Fiber Drop | 0.41 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0760 | 1 | 760 | 760 | 0704611028 | Region VII (Central Visayas) | Negros Oriental | City of Guihulngan | Poblacion | 10.1191 | 123.2689 | U | 16827 | 4428 | 1328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0029 | PTCI/MIDC | 10.1381 | 123.2458 | 3.3 | Terrestrial Optical Fiber Drop | 0.41 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0761 | 1 | 761 | 761 | 1403209016 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Malagnat | 17.6424 | 121.3897 | R | 2012 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00102 | Edgepoint | 17.6007 | 121.4263 | 6.04 | Terrestrial Optical Fiber Drop | 0.41 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0762 | 1 | 762 | 762 | 0831600076 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 49 | 11.2398 | 124.9986 | R | 1049 | 255 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0072 | PTCI/MIDC | 11.2381 | 125.0038 | 0.59 | Terrestrial Optical Fiber Drop | 0.41 | 3.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0763 | 1 | 763 | 763 | 0203136024 | Region II (Cagayan Valley) | Isabela | Santo Tomas | San Roque | 17.3876 | 121.7751 | R | 1241 | 326 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0036 | PTCI/MIDC | 17.3894 | 121.7832 | 0.89 | Terrestrial Optical Fiber Drop | 0.41 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0764 | 1 | 764 | 764 | 1408103014 | Cordillera Administrative Region (CAR) | Apayao | Flora | Poblacion West | 18.214 | 121.4161 | R | 2167 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_APY_0001 | LDIC | 121.4211 | 18.2128 | 0.54 | Terrestrial Optical Fiber Drop | 0.42 | 4.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0765 | 1 | 765 | 765 | 0402106037 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Nicolas I | 14.3151 | 120.9685 | R | 2180 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.41 | Terrestrial Optical Fiber Drop | 0.42 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0766 | 1 | 766 | 766 | 0105531033 | Region I (Ilocos Region) | Pangasinan | Rosales | Zone I | 15.8912 | 120.6312 | R | 1283 | 356 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01756-B07 | PTCI/MIDC | 15.8943 | 120.6276 | 0.51 | Terrestrial Optical Fiber Drop | 0.42 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0767 | 1 | 767 | 767 | 0105526013 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Guiguilonen | 16.0702 | 120.4057 | U | 3480 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01752-B07 | PTCI/MIDC | 16.0725 | 120.3979 | 0.64 | Terrestrial Optical Fiber Drop | 0.45 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0768 | 1 | 768 | 768 | 0405814001 | Region IV-A (CALABARZON) | Rizal | Teresa | Bagumbayan | 14.5499 | 121.2184 | U | 15588 | 4330 | 1299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00788-A04 | PTCI/MIDC | 14.5507 | 121.221 | 0.29 | Terrestrial Optical Fiber Drop | 0.42 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0769 | 1 | 769 | 769 | 1380500025 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | San Jose | 14.58 | 121.0292 | U | 7888 | 2383 | 715 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02522 | Edgepoint | 14.5811 | 121.0289 | 0.13 | Terrestrial Optical Fiber Drop | 0.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0770 | 1 | 770 | 770 | 1004303010 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | San Alonzo | 9.0037 | 124.8389 | R | 1719 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 1.59 | Terrestrial Optical Fiber Drop | 0.42 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0771 | 1 | 771 | 771 | 0300811006 | Region III (Central Luzon) | Bataan | Pilar | Balut II | 14.6866 | 120.5587 | R | 1360 | 377 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.49 | Terrestrial Optical Fiber Drop | 1.48 | 1.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0772 | 1 | 772 | 772 | 0300803017 | Region III (Central Luzon) | Bataan | City of Balanga | Sibacan | 14.687 | 120.5472 | R | 2889 | 802 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.63 | Terrestrial Optical Fiber Drop | 0.42 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0773 | 1 | 773 | 773 | 0604520020 | Region VI (Western Visayas) | Negros Occidental | Murcia | Pandanon | 10.6067 | 123.0383 | R | 3123 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 2.69 | Terrestrial Optical Fiber Drop | 0.42 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0774 | 1 | 774 | 774 | 0203115007 | Region II (Cagayan Valley) | Isabela | Jones | Barangay II | 16.554 | 121.7005 | R | 3289 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0057 | PTCI/MIDC | 16.5544 | 121.7027 | 0.23 | Terrestrial Optical Fiber Drop | 0.42 | 11.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0775 | 1 | 775 | 775 | 0702251007 | Region VII (Central Visayas) | Cebu | City of Toledo | Cabitoonan | 10.3526 | 123.6131 | U | 5607 | 1475 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0168 | PTCI/MIDC | 10.3534 | 123.6102 | 0.33 | Terrestrial Optical Fiber Drop | 0.42 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0776 | 1 | 776 | 776 | 0306911010 | Region III (Central Luzon) | Tarlac | Pura | Nilasin 1st | 15.6247 | 120.6547 | R | 1278 | 327 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01811-B07 | PTCI/MIDC | 15.6262 | 120.6521 | 0.32 | Terrestrial Optical Fiber Drop | 0.42 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0777 | 1 | 777 | 777 | 0604515025 | Region VI (Western Visayas) | Negros Occidental | City of Kabankalan | Barangay 4 | 9.9883 | 122.8158 | R | 1475 | 398 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060388 | FTAP Globe | 9.9942 | 122.8157 | 0.65 | Terrestrial Optical Fiber Drop | 0.42 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0778 | 1 | 778 | 778 | 0102808024 | Region I (Ilocos Region) | Ilocos Norte | Currimao | Victoria | 17.9977 | 120.4999 | R | 913 | 246 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010029 | FTAP Globe | 18.006 | 120.5028 | 0.96 | Terrestrial Optical Fiber Drop | 0.42 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0779 | 1 | 779 | 779 | 1381500003 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Bambang | 14.5118 | 121.0586 | U | 15749 | 3850 | 1155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000624 | FTAP Globe | 14.515 | 121.0524 | 0.26 | Terrestrial Optical Fiber Drop | 0.82 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0780 | 1 | 780 | 780 | 0405649028 | Region IV-A (CALABARZON) | Quezon | Unisan | R. Magsaysay | 13.8426 | 121.9783 | R | 672 | 176 | 53 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040549 | FTAP Globe | 13.8415 | 121.9735 | 0.53 | Terrestrial Optical Fiber Drop | 0.42 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0781 | 1 | 781 | 781 | 0501709017 | Region V (Bicol Region) | Camarines Sur | Camaligan | Tarosanan | 13.6165 | 123.1703 | R | 2223 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.48 | Terrestrial Optical Fiber Drop | 0.43 | 1.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0782 | 1 | 782 | 782 | 0405806027 | Region IV-A (CALABARZON) | Rizal | Cardona | San Roque | 14.4862 | 121.2265 | R | 2945 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00823-A04 | PTCI/MIDC | 14.4814 | 121.2254 | 0.55 | Terrestrial Optical Fiber Drop | 0.42 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0783 | 1 | 783 | 783 | 0201512021 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay III-A | 17.5592 | 121.6934 | R | 2677 | 686 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0027 | LDIC | 121.695 | 17.5597 | 0.18 | Terrestrial Optical Fiber Drop | 0.42 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0784 | 1 | 784 | 784 | 0501703030 | Region V (Bicol Region) | Camarines Sur | Bato | San Vicente | 13.3621 | 123.3668 | U | 6695 | 1594 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.73 | Terrestrial Optical Fiber Drop | 0.43 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0785 | 1 | 785 | 785 | 0306917024 | Region III (Central Luzon) | Tarlac | Victoria | San Nicolas | 15.5776 | 120.6812 | R | 2875 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01804-B07 | PTCI/MIDC | 15.5781 | 120.6772 | 0.44 | Terrestrial Optical Fiber Drop | 0.43 | 6.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0786 | 1 | 786 | 786 | 0205010016 | Region II (Cagayan Valley) | Nueva Vizcaya | Kayapa | Pampang | 16.3578 | 120.8865 | R | 1298 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01524-B05 | PTCI/MIDC | 16.3482 | 120.9094 | 2.66 | Terrestrial Optical Fiber Drop | 0.43 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0787 | 1 | 787 | 787 | 0601916003 | Region VI (Western Visayas) | Capiz | Sigma | Balucuan | 11.4 | 122.6378 | R | 1190 | 313 | 94 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1 | Terrestrial Optical Fiber Drop | 4.09 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0788 | 1 | 788 | 788 | 0704610029 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Taclobo | 9.3095 | 123.3037 | U | 9848 | 2591 | 777 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLR0023 | PTCI/MIDC | 9.3104 | 123.3049 | 0.16 | Terrestrial Optical Fiber Drop | 0.43 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0789 | 1 | 789 | 789 | 1380200006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Las Piñas | Pamplona Uno | 14.4581 | 120.97 | U | 19658 | 5284 | 1585 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000677 | FTAP Globe | 14.4591 | 120.9704 | 0.12 | Terrestrial Optical Fiber Drop | 0.43 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0790 | 1 | 790 | 790 | 1380500021 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Pag-asa | 14.5835 | 121.0339 | U | 4493 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01737 | Edgepoint | 14.5877 | 121.0521 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0791 | 1 | 791 | 791 | 0306914015 | Region III (Central Luzon) | Tarlac | San Manuel | Santa Maria | 15.798 | 120.6116 | R | 1715 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 0.17 | Terrestrial Optical Fiber Drop | 0.43 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0792 | 1 | 792 | 792 | 0105522021 | Region I (Ilocos Region) | Pangasinan | Lingayen | Maniboc | 16.0194 | 120.2312 | U | 8214 | 2281 | 684 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-03115 | Edgepoint | 16.0264 | 120.2268 | 0.91 | Terrestrial Optical Fiber Drop | 0.43 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0793 | 1 | 793 | 793 | 1705208044 | MIMAROPA Region | Oriental Mindoro | Naujan | Pinagsabangan II | 13.2674 | 121.2684 | R | 2782 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S7012 | FTAP Smart | 13.2756 | 121.2396 | 3.25 | Terrestrial Optical Fiber Drop | 0.43 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0794 | 1 | 794 | 794 | 0631000024 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Buhang | 10.7494 | 122.5666 | U | 3938 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.36 | Terrestrial Optical Fiber Drop | 0.44 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0795 | 1 | 795 | 795 | 1381701007 | National Capital Region (NCR) | Metro Manila (NCR) | Pateros | Santa Ana | 14.5466 | 121.0718 | U | 30950 | 8102 | 2431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000598 | FTAP Globe | 14.5471 | 121.0723 | 0.08 | Terrestrial Optical Fiber Drop | 0.43 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0796 | 1 | 796 | 796 | 0105508015 | Region I (Ilocos Region) | Pangasinan | Bani | Poblacion | 16.187 | 119.8595 | U | 4855 | 1348 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N5519 | FTAP Smart | 16.1813 | 119.8603 | 0.64 | Terrestrial Optical Fiber Drop | 0.44 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0797 | 1 | 797 | 797 | 0307707007 | Region III (Central Luzon) | Aurora | Maria Aurora | Barangay III | 15.7972 | 121.4751 | R | 779 | 205 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3806 | FTAP Smart | 15.7998 | 121.4765 | 0.33 | Terrestrial Optical Fiber Drop | 0.44 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0798 | 1 | 798 | 798 | 0501608017 | Region V (Bicol Region) | Camarines Norte | Paracale | Mangkasay | 14.2554 | 122.8195 | R | 1461 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050007 | FTAP Globe | 14.2443 | 122.8098 | 1.61 | Terrestrial Optical Fiber Drop | 0.44 | 7.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0799 | 1 | 799 | 799 | 0908316005 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Tungawan | Libertad | 7.6027 | 122.4242 | U | 5986 | 1425 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090159 | FTAP Globe | 7.6017 | 122.4207 | 0.4 | Terrestrial Optical Fiber Drop | 0.44 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0800 | 1 | 800 | 800 | 0702220013 | Region VII (Central Visayas) | Cebu | Cordova | San Miguel | 10.2609 | 123.9437 | R | 4106 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.49 | Terrestrial Optical Fiber Drop | 0.44 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0801 | 1 | 801 | 801 | 0601914047 | Region VI (Western Visayas) | Capiz | City of Roxas | Tanque | 11.5874 | 122.752 | U | 6144 | 1616 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.89 | Terrestrial Optical Fiber Drop | 0.44 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0802 | 1 | 802 | 802 | 1381100192 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 192 | 14.5332 | 121.0006 | U | 4274 | 1264 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040184 | FTAP Globe | 14.3064 | 121.075 | 0.94 | Terrestrial Optical Fiber Drop | 0.7 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0803 | 1 | 803 | 803 | 0103314057 | Region I (Ilocos Region) | La Union | City of San Fernando | Sevilla | 16.6021 | 120.3216 | U | 11353 | 3068 | 920 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010095 | FTAP Globe | 16.6018 | 120.3189 | 0.29 | Terrestrial Optical Fiber Drop | 0.44 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0804 | 1 | 804 | 804 | 0102930020 | Region I (Ilocos Region) | Ilocos Sur | Sinait | Macabiag | 17.8645 | 120.4566 | R | 902 | 237 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTIRG0006 | PTCI/MIDC | 17.8693 | 120.4588 | 0.58 | Terrestrial Optical Fiber Drop | 0.44 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0805 | 1 | 805 | 805 | 0402110033 | Region IV-A (CALABARZON) | Cavite | Indang | Daine II | 14.1855 | 120.8459 | R | 2449 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0034 | FTAP Smart | 14.1948 | 120.8764 | 0.6 | Terrestrial Optical Fiber Drop | 3.27 | 8.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0806 | 1 | 806 | 806 | 0105539014 | Region I (Ilocos Region) | Pangasinan | Santa Maria | Poblacion East | 15.9806 | 120.7009 | R | 1027 | 285 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01765-B07 | PTCI/MIDC | 15.9765 | 120.6972 | 0.6 | Terrestrial Optical Fiber Drop | 0.44 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0807 | 1 | 807 | 807 | 0731300009 | Region VII (Central Visayas) | Cebu | City of Mandaue | Casuntingan | 10.3466 | 123.9408 | U | 16863 | 4818 | 1445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0118 | PTCI/MIDC | 10.3479 | 123.9486 | 0.56 | Terrestrial Optical Fiber Drop | 0.88 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0808 | 1 | 808 | 808 | 0600403015 | Region VI (Western Visayas) | Aklan | Banga | Mangan | 11.6293 | 122.3444 | R | 1846 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 1.78 | Terrestrial Optical Fiber Drop | 0.44 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0809 | 1 | 809 | 809 | 1381500027 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | South Daang Hari | 14.469 | 121.0499 | U | 25037 | 6322 | 1897 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01875 | Edgepoint | 14.4936 | 121.0495 | 0.16 | Terrestrial Optical Fiber Drop | 1.48 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0810 | 1 | 810 | 810 | 0307103011 | Region III (Central Luzon) | Zambales | Candelaria | Pamibian | 15.6249 | 119.9363 | R | 1501 | 395 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.27 | Terrestrial Optical Fiber Drop | 0.44 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0811 | 1 | 811 | 811 | 0402116012 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Jose II | 14.4318 | 120.8864 | R | 1941 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03072-C08 | PTCI/MIDC | 14.4296 | 120.8833 | 0.42 | Terrestrial Optical Fiber Drop | 0.44 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0812 | 1 | 812 | 812 | 0306904020 | Region III (Central Luzon) | Tarlac | Capas | Santo Domingo 2nd | 15.3434 | 120.5952 | U | 7231 | 1854 | 556 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01802-B07 | PTCI/MIDC | 15.342 | 120.5972 | 0.26 | Terrestrial Optical Fiber Drop | 0.44 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0813 | 1 | 813 | 813 | 0603043008 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Bantay | 10.8692 | 122.5409 | R | 434 | 114 | 34 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0072 | PTCI/MIDC | 10.8243 | 122.5364 | 0.82 | Terrestrial Optical Fiber Drop | 4.71 | 3.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0814 | 1 | 814 | 814 | 1705209037 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Guinhawa | 13.0665 | 121.5033 | R | 2263 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170094 | FTAP Globe | 13.0692 | 121.5176 | 1.58 | Terrestrial Optical Fiber Drop | 0.44 | 3.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0815 | 1 | 815 | 815 | 1380400019 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Tinajeros | 14.6713 | 120.9699 | U | 18677 | 5351 | 1605 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01420 | Edgepoint | 14.6727 | 120.9686 | 0.21 | Terrestrial Optical Fiber Drop | 0.45 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0816 | 1 | 816 | 816 | 0702222029 | Region VII (Central Visayas) | Cebu | Dalaguete | Poblacion | 9.7583 | 123.5338 | U | 6846 | 1801 | 540 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070368 | FTAP Globe | 9.7578 | 123.5312 | 0.28 | Terrestrial Optical Fiber Drop | 0.45 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0817 | 1 | 817 | 817 | 0305406023 | Region III (Central Luzon) | Pampanga | Floridablanca | Poblacion | 14.9786 | 120.4998 | U | 3751 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01555-B07 | PTCI/MIDC | 14.981 | 120.5138 | 0.69 | Terrestrial Optical Fiber Drop | 1.55 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0818 | 1 | 818 | 818 | 0105526025 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Poblacion | 16.0703 | 120.4056 | U | 4206 | 1168 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00421 | Edgepoint | 16.068 | 120.4097 | 0.51 | Terrestrial Optical Fiber Drop | 0.45 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0819 | 1 | 819 | 819 | 1030500018 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Barangay 22 | 8.4905 | 124.6538 | U | 3384 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLR0026 | PTCI/MIDC | 8.4839 | 124.6532 | 0.74 | Terrestrial Optical Fiber Drop | 0.45 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0820 | 1 | 820 | 820 | 0301414008 | Region III (Central Luzon) | Bulacan | Obando | Paliwas | 14.7132 | 120.935 | U | 5749 | 1642 | 493 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01307 | Edgepoint | 14.712 | 120.9332 | 0.24 | Terrestrial Optical Fiber Drop | 0.45 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0821 | 1 | 821 | 821 | 1380300004 | National Capital Region (NCR) | Metro Manila (NCR) | City of Makati | Comembo | 14.5461 | 121.0645 | U | 7776 | 2221 | 666 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01833 | Edgepoint | 14.5455 | 121.0684 | 0.43 | Terrestrial Optical Fiber Drop | 0.45 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0822 | 1 | 822 | 822 | 0731300002 | Region VII (Central Visayas) | Cebu | City of Mandaue | Bakilid | 10.3387 | 123.9342 | U | 4391 | 1254 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070336 | FTAP Globe | 10.3399 | 123.9305 | 0.42 | Terrestrial Optical Fiber Drop | 0.45 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0823 | 1 | 823 | 823 | 0402106049 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Burol III | 14.3244 | 120.9607 | U | 11497 | 3381 | 1014 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01927-C08 | PTCI/MIDC | 14.3499 | 120.9431 | 0.08 | Terrestrial Optical Fiber Drop | 1.44 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0824 | 1 | 824 | 824 | 0402104014 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 3 | 14.3138 | 121.0535 | R | 916 | 269 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1183 | FTAP Smart | 14.3053 | 121.0487 | 0.39 | Terrestrial Optical Fiber Drop | 0.49 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0825 | 1 | 825 | 825 | 0501703035 | Region V (Bicol Region) | Camarines Sur | Bato | Tres Reyes | 13.3544 | 123.3654 | R | 1545 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.34 | Terrestrial Optical Fiber Drop | 0.45 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0826 | 1 | 826 | 826 | 0402120012 | Region IV-A (CALABARZON) | Cavite | Tanza | Mulawin | 14.3746 | 120.8542 | U | 12931 | 3803 | 1141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.64 | Terrestrial Optical Fiber Drop | 0.67 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0827 | 1 | 827 | 827 | 1630400086 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tiniwisan | 8.9472 | 125.5397 | U | 4188 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.14 | Terrestrial Optical Fiber Drop | 0.45 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0828 | 1 | 828 | 828 | 0402109004 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-A | 14.3877 | 120.9399 | U | 3560 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01924-C08 | PTCI/MIDC | 14.3888 | 120.9378 | 0.26 | Terrestrial Optical Fiber Drop | 0.45 | 6.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0829 | 1 | 829 | 829 | 0306902005 | Region III (Central Luzon) | Tarlac | Bamban | Dela Cruz | 15.2798 | 120.5682 | U | 2483 | 636 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01780-B07 | PTCI/MIDC | 15.2833 | 120.5694 | 0.4 | Terrestrial Optical Fiber Drop | 0.45 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0830 | 1 | 830 | 830 | 1001317019 | Region X (Northern Mindanao) | Bukidnon | Quezon | Merangerang | 7.7026 | 125.1135 | R | 3706 | 975 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.71 | Terrestrial Optical Fiber Drop | 0.55 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0831 | 1 | 831 | 831 | 0702232010 | Region VII (Central Visayas) | Cebu | Minglanilla | Poblacion Ward I | 10.2443 | 123.7983 | U | 2358 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0128 | PTCI/MIDC | 10.2407 | 123.8002 | 0.45 | Terrestrial Optical Fiber Drop | 0.45 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0832 | 1 | 832 | 832 | 0402118020 | Region IV-A (CALABARZON) | Cavite | Silang | Lalaan II | 14.1581 | 120.9572 | U | 8272 | 2432 | 730 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040285 | FTAP Globe | 14.1551 | 120.9563 | 0.35 | Terrestrial Optical Fiber Drop | 0.45 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0833 | 1 | 833 | 833 | 0102814009 | Region I (Ilocos Region) | Ilocos Norte | Nueva Era | Poblacion | 17.9167 | 120.663 | R | 3255 | 879 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILN-02610 | Edgepoint | 17.9183 | 120.6677 | 0.53 | Terrestrial Optical Fiber Drop | 0.45 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0834 | 1 | 834 | 834 | 0405623006 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 3 | 14.1171 | 121.55 | R | 1547 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02806-C08 | PTCI/MIDC | 14.1101 | 121.5584 | 0.16 | Terrestrial Optical Fiber Drop | 0.96 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0835 | 1 | 835 | 835 | 0307110009 | Region III (Central Luzon) | Zambales | San Felipe | San Rafael | 15.0576 | 120.0667 | R | 1224 | 322 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00904 | Edgepoint | 15.0611 | 120.0686 | 0.44 | Terrestrial Optical Fiber Drop | 0.46 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0836 | 1 | 836 | 836 | 0603023020 | Region VI (Western Visayas) | Iloilo | Janiuay | Damo-ong | 10.9418 | 122.5157 | R | 1996 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060020 | FTAP BTS | 10.9483 | 122.509 | 1.03 | Terrestrial Optical Fiber Drop | 0.46 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0837 | 1 | 837 | 837 | 0304923029 | Region III (Central Luzon) | Nueva Ecija | Rizal | Poblacion West | 15.7143 | 121.1016 | R | 3651 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03193-B07 | PTCI/MIDC | 15.7165 | 121.0971 | 0.54 | Terrestrial Optical Fiber Drop | 0.46 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0838 | 1 | 838 | 838 | 0105530028 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Poblacion III | 16.113 | 120.545 | R | 1469 | 408 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.55 | Terrestrial Optical Fiber Drop | 0.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0839 | 1 | 839 | 839 | 0506209024 | Region V (Bicol Region) | Sorsogon | Irosin | San Julian | 12.7063 | 124.0344 | U | 2318 | 579 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050226 | FTAP Globe | 12.7081 | 124.0387 | 0.51 | Terrestrial Optical Fiber Drop | 0.46 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0840 | 1 | 840 | 840 | 0307701011 | Region III (Central Luzon) | Aurora | Baler | Sabang | 15.7599 | 121.5676 | R | 3274 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03289-B06 | PTCI/MIDC | 15.7633 | 121.5658 | 0.42 | Terrestrial Optical Fiber Drop | 0.46 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0841 | 1 | 841 | 841 | 0405625007 | Region IV-A (CALABARZON) | Quezon | Macalelon | Luctob | 13.7473 | 122.1323 | R | 1901 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.77 | Terrestrial Optical Fiber Drop | 0.46 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0842 | 1 | 842 | 842 | 0631000099 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Burgos-Mabini-Plaza | 10.7173 | 122.5656 | U | 1865 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0032 | PTCI/MIDC | 10.7162 | 122.5662 | 0.14 | Terrestrial Optical Fiber Drop | 0.46 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0843 | 1 | 843 | 843 | 0704610019 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Poblacion No. 1 | 9.3091 | 123.3044 | R | 2229 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLR0022 | PTCI/MIDC | 9.2995 | 123.3026 | 0.39 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0844 | 1 | 844 | 844 | 0331400016 | Region III (Central Luzon) | Zambales | City of Olongapo | New Kababae | 14.8315 | 120.2772 | R | 2465 | 666 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.32 | Terrestrial Optical Fiber Drop | 0.46 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0845 | 1 | 845 | 845 | 0306913015 | Region III (Central Luzon) | Tarlac | San Clemente | Poblacion Sur | 15.7118 | 120.3605 | R | 1691 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01813-B07 | PTCI/MIDC | 15.7092 | 120.3597 | 0.3 | Terrestrial Optical Fiber Drop | 0.46 | 6.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0846 | 1 | 846 | 846 | 0105530010 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Cablong | 16.1145 | 120.5468 | U | 2413 | 670 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.74 | Terrestrial Optical Fiber Drop | 0.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0847 | 1 | 847 | 847 | 0908302029 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Datu Panas | 7.7369 | 123.0572 | R | 2219 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.66 | Terrestrial Optical Fiber Drop | 0.82 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0848 | 1 | 848 | 848 | 0307110007 | Region III (Central Luzon) | Zambales | San Felipe | Manglicmot | 15.0556 | 120.071 | R | 1827 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0003 | PTCI/MIDC | 15.0546 | 120.0704 | 0.13 | Terrestrial Optical Fiber Drop | 0.47 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0849 | 1 | 849 | 849 | 0402116002 | Region IV-A (CALABARZON) | Cavite | Noveleta | Poblacion | 14.4264 | 120.8802 | R | 2291 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.46 | Terrestrial Optical Fiber Drop | 0.46 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0850 | 1 | 850 | 850 | 0730600087 | Region VII (Central Visayas) | Cebu | City of Cebu | Zapatera | 10.3036 | 123.9021 | U | 2961 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0033 | PTCI/MIDC | 10.303 | 123.8978 | 0.48 | Terrestrial Optical Fiber Drop | 0.47 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0851 | 1 | 851 | 851 | 1004325015 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | Santa Ines | 8.9688 | 124.9405 | R | 2015 | 516 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100108 | FTAP Globe | 8.9649 | 124.9453 | 0.69 | Terrestrial Optical Fiber Drop | 0.46 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0852 | 1 | 852 | 852 | 1030500050 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Indahag | 8.4313 | 124.6703 | U | 18154 | 5042 | 1513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0007 | PTCI/MIDC | 8.4333 | 124.6676 | 0.36 | Terrestrial Optical Fiber Drop | 0.46 | 4.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0853 | 1 | 853 | 853 | 0203115006 | Region II (Cagayan Valley) | Isabela | Jones | Barangay I | 16.5614 | 121.7002 | U | 2314 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00305 | Edgepoint | 16.5618 | 121.7013 | 0.13 | Terrestrial Optical Fiber Drop | 0.47 | 12.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0854 | 1 | 854 | 854 | 1381300129 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Vasra | 14.6589 | 121.0466 | U | 7883 | 2036 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02667 | Edgepoint | 14.6595 | 121.0502 | 0.39 | Terrestrial Optical Fiber Drop | 0.47 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0855 | 1 | 855 | 855 | 0403417038 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Palina | 14.1411 | 121.4132 | R | 1685 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.31 | Terrestrial Optical Fiber Drop | 0.49 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0856 | 1 | 856 | 856 | 1102411012 | Region XI (Davao Region) | Davao del Sur | Padada | Quirino District | 6.6444 | 125.3459 | R | 1762 | 518 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.7 | Terrestrial Optical Fiber Drop | 1.01 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0857 | 1 | 857 | 857 | 0702205014 | Region VII (Central Visayas) | Cebu | Argao | Canbanua | 9.8848 | 123.5946 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070017 | FTAP BTS | 9.8956 | 123.5985 | 1.28 | Terrestrial Optical Fiber Drop | 0.47 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0858 | 1 | 858 | 858 | 1108207013 | Region XI (Davao Region) | Davao de Oro | Monkayo | Poblacion | 7.8247 | 126.0529 | U | 20867 | 5639 | 1692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDOG0003 | PTCI/MIDC | 7.8235 | 126.0516 | 0.19 | Terrestrial Optical Fiber Drop | 0.47 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0859 | 1 | 859 | 859 | 0301421041 | Region III (Central Luzon) | Bulacan | San Miguel | Salangan | 15.1341 | 120.9593 | U | 5606 | 1601 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00858 | Edgepoint | 15.1312 | 120.9589 | 0.33 | Terrestrial Optical Fiber Drop | 0.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0860 | 1 | 860 | 860 | 0405646034 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | San Isidro | 14.016 | 122.4656 | R | 1231 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0817 | FTAP Smart | 14.0255 | 122.4572 | 1.39 | Terrestrial Optical Fiber Drop | 0.47 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0861 | 1 | 861 | 861 | 0301420001 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Bagong Buhay I | 14.8453 | 121.0483 | U | 7593 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0042 | PTCI/MIDC | 14.818 | 121.0664 | 0.22 | Terrestrial Optical Fiber Drop | 1.27 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0862 | 1 | 862 | 862 | 0307104014 | Region III (Central Luzon) | Zambales | Castillejos | San Roque | 14.9297 | 120.2052 | R | 1491 | 392 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01026 | Edgepoint | 14.9302 | 120.201 | 0.46 | Terrestrial Optical Fiber Drop | 0.47 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0863 | 1 | 863 | 863 | 1380500024 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Poblacion | 14.5865 | 121.0249 | U | 16407 | 4728 | 1418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03000-A02 | PTCI/MIDC | 14.5854 | 121.0259 | 0.16 | Terrestrial Optical Fiber Drop | 0.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0864 | 1 | 864 | 864 | 0103306013 | Region I (Ilocos Region) | La Union | Bangar | General Terrero | 16.897 | 120.423 | R | 1150 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.2 | Terrestrial Optical Fiber Drop | 0.47 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0865 | 1 | 865 | 865 | 0631000016 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Banuyao | 10.7048 | 122.5624 | R | 1406 | 334 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0032 | PTCI/MIDC | 10.7162 | 122.5662 | 0.23 | Terrestrial Optical Fiber Drop | 1.17 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0866 | 1 | 866 | 866 | 0300803001 | Region III (Central Luzon) | Bataan | City of Balanga | Bagumbayan | 14.6796 | 120.5464 | R | 2159 | 599 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.61 | Terrestrial Optical Fiber Drop | 0.47 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0867 | 1 | 867 | 867 | 0304921013 | Region III (Central Luzon) | Nueva Ecija | Peñaranda | Sinasajan | 15.3494 | 121.0168 | U | 5591 | 1597 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0184 | FTAP Smart | 15.3526 | 121.0171 | 0.35 | Terrestrial Optical Fiber Drop | 0.47 | 7.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0868 | 1 | 868 | 868 | 1630400014 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Bading Pob. | 8.9469 | 125.5394 | U | 5860 | 1429 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.17 | Terrestrial Optical Fiber Drop | 0.47 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0869 | 1 | 869 | 869 | 0501717029 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Isidro Norte | 13.7357 | 123.5201 | R | 1593 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050055 | FTAP Globe | 13.7358 | 123.5217 | 0.18 | Terrestrial Optical Fiber Drop | 0.47 | 5.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0870 | 1 | 870 | 870 | 0405607080 | Region IV-A (CALABARZON) | Quezon | Calauag | Sumulong | 13.959 | 122.3313 | R | 1090 | 286 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | B42 | FTAP Smart | 13.9539 | 122.3 | 3.43 | Terrestrial Optical Fiber Drop | 0.47 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0871 | 1 | 871 | 871 | 0305415002 | Region III (Central Luzon) | Pampanga | Porac | Babo Sacan | 15.0683 | 120.5428 | U | 6277 | 1569 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.1 | Terrestrial Optical Fiber Drop | 0.47 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0872 | 1 | 872 | 872 | 0403416037 | Region IV-A (CALABARZON) | Laguna | Majayjay | Santa Catalina | 14.1472 | 121.4711 | R | 2238 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02098-C08 | PTCI/MIDC | 14.1452 | 121.469 | 0.32 | Terrestrial Optical Fiber Drop | 0.47 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0873 | 1 | 873 | 873 | 0401007019 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Dacanlao | 13.9393 | 120.7917 | U | 6495 | 1804 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040446 | FTAP Globe | 13.9387 | 120.7992 | 0.82 | Terrestrial Optical Fiber Drop | 0.47 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0874 | 1 | 874 | 874 | 0501606009 | Region V (Bicol Region) | Camarines Norte | Labo | Bayabas | 14.1859 | 122.4694 | R | 1420 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050011 | FTAP Globe | 14.191 | 122.5157 | 5.03 | Terrestrial Optical Fiber Drop | 0.47 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0875 | 1 | 875 | 875 | 0405615004 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin I | 14.0171 | 121.3862 | R | 2719 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040380 | FTAP Globe | 14.0132 | 121.3897 | 0.58 | Terrestrial Optical Fiber Drop | 0.47 | 4.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0876 | 1 | 876 | 876 | 1600210008 | Region XIII (Caraga) | Agusan del Norte | Santiago | San Isidro | 9.1576 | 125.5608 | R | 3099 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130060 | FTAP Globe | 9.1659 | 125.5227 | 4.29 | Terrestrial Optical Fiber Drop | 0.48 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0877 | 1 | 877 | 877 | 1004311014 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Upper Jasaan | 8.6541 | 124.7541 | R | 4469 | 1145 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.71 | Terrestrial Optical Fiber Drop | 0.48 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0878 | 1 | 878 | 878 | 0601916019 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Norte | 11.4236 | 122.6644 | R | 1267 | 333 | 100 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1 | Terrestrial Optical Fiber Drop | 0.47 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0879 | 1 | 879 | 879 | 0105519014 | Region I (Ilocos Region) | Pangasinan | Dasol | Poblacion | 15.9898 | 119.8798 | R | 3471 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.73 | Terrestrial Optical Fiber Drop | 0.47 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0880 | 1 | 880 | 880 | 0102928008 | Region I (Ilocos Region) | Ilocos Sur | Santo Domingo | Camestizoan | 17.6387 | 120.4107 | R | 1181 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01269-B05 | PTCI/MIDC | 17.6374 | 120.4065 | 1.64 | Terrestrial Optical Fiber Drop | 0.9 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0881 | 1 | 881 | 881 | 0205007013 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Malasin | 16.3071 | 121.1053 | U | 5618 | 1478 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01538-B05 | PTCI/MIDC | 16.3062 | 121.1064 | 0.16 | Terrestrial Optical Fiber Drop | 0.48 | 3.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0882 | 1 | 882 | 882 | 0604520025 | Region VI (Western Visayas) | Negros Occidental | Murcia | Talotog | 10.6204 | 123.0644 | R | 2131 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060357 | FTAP Globe | 10.5658 | 123.076 | 0.58 | Terrestrial Optical Fiber Drop | 2.88 | 2.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0883 | 1 | 883 | 883 | 0306909011 | Region III (Central Luzon) | Tarlac | Moncada | Camangaan East | 15.7264 | 120.5717 | R | 1787 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01796-B07 | PTCI/MIDC | 15.7192 | 120.5771 | 0.98 | Terrestrial Optical Fiber Drop | 0.48 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0884 | 1 | 884 | 884 | 0702235020 | Region VII (Central Visayas) | Cebu | Oslob | Poblacion | 9.5247 | 123.4339 | U | 4546 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 0.24 | Terrestrial Optical Fiber Drop | 0.48 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0885 | 1 | 885 | 885 | 0305415018 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Paralaya | 15.1151 | 120.5671 | U | 14310 | 3577 | 1073 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00869 | Edgepoint | 15.1162 | 120.5663 | 0.15 | Terrestrial Optical Fiber Drop | 0.48 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0886 | 1 | 886 | 886 | 0702220002 | Region VII (Central Visayas) | Cebu | Cordova | Bangbang | 10.2589 | 123.9444 | U | 6702 | 1763 | 529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.26 | Terrestrial Optical Fiber Drop | 0.48 | 6.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0887 | 1 | 887 | 887 | 0401014054 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Sabang | 13.9459 | 121.1706 | U | 22810 | 6336 | 1901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040434 | FTAP Globe | 13.9453 | 121.1715 | 0.12 | Terrestrial Optical Fiber Drop | 0.48 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0888 | 1 | 888 | 888 | 0304913020 | Region III (Central Luzon) | Nueva Ecija | Laur | San Juan | 15.5705 | 121.2031 | R | 2654 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03331-B07 | PTCI/MIDC | 15.5639 | 121.1872 | 1.86 | Terrestrial Optical Fiber Drop | 0.48 | 7.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0889 | 1 | 889 | 889 | 0405804028 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pila Pila | 14.4483 | 121.2079 | U | 9034 | 2509 | 753 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040098 | FTAP Globe | 14.4457 | 121.2079 | 0.28 | Terrestrial Optical Fiber Drop | 0.48 | 2.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0890 | 1 | 890 | 890 | 0307103015 | Region III (Central Luzon) | Zambales | Candelaria | Poblacion | 15.6275 | 119.9304 | R | 1300 | 342 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01835-B07 | PTCI/MIDC | 15.6261 | 119.9342 | 0.44 | Terrestrial Optical Fiber Drop | 0.48 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0891 | 1 | 891 | 891 | 0205005016 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | District III Pob. | 16.483 | 121.1515 | U | 2564 | 674 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.95 | Terrestrial Optical Fiber Drop | 0.71 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0892 | 1 | 892 | 892 | 0501719016 | Region V (Bicol Region) | Camarines Sur | Lupi | Colacling | 13.7741 | 122.8726 | R | 2738 | 651 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050051 | FTAP Globe | 13.7773 | 122.8741 | 0.38 | Terrestrial Optical Fiber Drop | 0.48 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0893 | 1 | 893 | 893 | 0803740050 | Region VIII (Eastern Visayas) | Leyte | Palompon | Pinagdait Pob. | 11.0485 | 124.3829 | R | 1731 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 9.55 | Terrestrial Optical Fiber Drop | 0.49 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0894 | 1 | 894 | 894 | 0402103068 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba IV | 14.4612 | 120.9602 | U | 3259 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.12 | Terrestrial Optical Fiber Drop | 0.49 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0895 | 1 | 895 | 895 | 0403425020 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Sampaguita Village | 14.3442 | 121.0358 | R | 5416 | 1641 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.54 | Terrestrial Optical Fiber Drop | 0.48 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0896 | 1 | 896 | 896 | 1430300036 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Fairview Village | 16.4159 | 120.5837 | U | 8029 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00335 | Edgepoint | 16.4147 | 120.5826 | 0.17 | Terrestrial Optical Fiber Drop | 0.49 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0897 | 1 | 897 | 897 | 0702219009 | Region VII (Central Visayas) | Cebu | Consolacion | Nangka | 10.3721 | 123.9591 | U | 13307 | 3501 | 1050 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070328 | FTAP Globe | 10.3709 | 123.9588 | 0.14 | Terrestrial Optical Fiber Drop | 0.49 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0898 | 1 | 898 | 898 | 0500508013 | Region V (Bicol Region) | Albay | City of Ligao | Binatagan | 13.2412 | 123.5312 | R | 4002 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 0.93 | Terrestrial Optical Fiber Drop | 0.49 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0899 | 1 | 899 | 899 | 1380400002 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | Baritan | 14.6717 | 120.9493 | U | 12461 | 3857 | 1157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00314-A01 | PTCI/MIDC | 14.6731 | 120.9464 | 0.34 | Terrestrial Optical Fiber Drop | 0.49 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0900 | 1 | 900 | 900 | 0306911013 | Region III (Central Luzon) | Tarlac | Pura | Poblacion 2 | 15.6241 | 120.6486 | R | 1260 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.68 | Terrestrial Optical Fiber Drop | 0.29 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0901 | 1 | 901 | 901 | 1402701023 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Tam-an | 16.9068 | 121.0628 | R | 1481 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.36 | Terrestrial Optical Fiber Drop | 0.49 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0902 | 1 | 902 | 902 | 0102905033 | Region I (Ilocos Region) | Ilocos Sur | Cabugao | Turod-Patac | 17.7889 | 120.458 | R | 968 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILS-00065 | Edgepoint | 17.79 | 120.4556 | 0.3 | Terrestrial Optical Fiber Drop | 0.21 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0903 | 1 | 903 | 903 | 0500514022 | Region V (Bicol Region) | Albay | Polangui | Itaran | 13.3295 | 123.5164 | R | 2247 | 548 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0030 | PTCI/MIDC | 13.3261 | 123.5129 | 0.53 | Terrestrial Optical Fiber Drop | 0.49 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0904 | 1 | 904 | 904 | 1004320008 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Poblacion | 8.4326 | 124.2948 | U | 5900 | 1512 | 454 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0070 | PTCI/MIDC | 8.4298 | 124.2956 | 0.33 | Terrestrial Optical Fiber Drop | 0.49 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0905 | 1 | 905 | 905 | 0103307033 | Region I (Ilocos Region) | La Union | Bauang | Quinavite | 16.5378 | 120.3295 | R | 3893 | 1052 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 1.19 | Terrestrial Optical Fiber Drop | 0.49 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0906 | 1 | 906 | 906 | 0500516022 | Region V (Bicol Region) | Albay | Santo Domingo | San Roque | 13.2534 | 123.768 | R | 1799 | 438 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.5 | Terrestrial Optical Fiber Drop | 2.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0907 | 1 | 907 | 907 | 0304924017 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Tikiw | 15.3105 | 120.8623 | R | 3172 | 906 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02181 | Edgepoint | 15.3094 | 120.858 | 0.48 | Terrestrial Optical Fiber Drop | 0.49 | 3.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0908 | 1 | 908 | 908 | 0405812020 | Region IV-A (CALABARZON) | Rizal | Tanay | Wawa | 14.4928 | 121.285 | U | 8036 | 2232 | 670 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01876 | Edgepoint | 14.4917 | 121.282 | 0.35 | Terrestrial Optical Fiber Drop | 0.5 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0909 | 1 | 909 | 909 | 1381300141 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Greater Lagro | 14.7306 | 121.0662 | U | 24104 | 6244 | 1873 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00326-A01 | PTCI/MIDC | 14.7312 | 121.067 | 0.11 | Terrestrial Optical Fiber Drop | 0.5 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0910 | 1 | 910 | 910 | 0704619020 | Region VII (Central Visayas) | Negros Oriental | Siaton | Poblacion III | 9.0597 | 123.0357 | R | 3757 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0045 | PTCI/MIDC | 9.0635 | 123.0334 | 0.5 | Terrestrial Optical Fiber Drop | 0.5 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0911 | 1 | 911 | 911 | 0603034021 | Region VI (Western Visayas) | Iloilo | Oton | Poblacion North | 10.6908 | 122.4842 | R | 1342 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060151 | FTAP BTS | 10.6858 | 122.4903 | 0.86 | Terrestrial Optical Fiber Drop | 0.5 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0912 | 1 | 912 | 912 | 0501730037 | Region V (Bicol Region) | Camarines Sur | Ragay | F. Simeon | 13.8445 | 122.701 | R | 3119 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050043 | FTAP Globe | 13.8306 | 122.7251 | 3.03 | Terrestrial Optical Fiber Drop | 0.5 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0913 | 1 | 913 | 913 | 0501706021 | Region V (Bicol Region) | Camarines Sur | Bula | Sagrada | 13.4759 | 123.2799 | R | 2017 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.49 | Terrestrial Optical Fiber Drop | 0.5 | 4.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0914 | 1 | 914 | 914 | 0702220011 | Region VII (Central Visayas) | Cebu | Cordova | Pilipog | 10.2663 | 123.9462 | U | 4765 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0230 | PTCI/MIDC | 10.2681 | 123.9526 | 0.73 | Terrestrial Optical Fiber Drop | 0.5 | 6.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0915 | 1 | 915 | 915 | 0402103009 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Kaingin | 14.4416 | 120.9718 | R | 3688 | 1084 | 325 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040108 | FTAP Globe | 14.4232 | 120.9631 | 0.21 | Terrestrial Optical Fiber Drop | 1.99 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0916 | 1 | 916 | 916 | 1430300026 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Cresencia Village | 16.4196 | 120.588 | R | 1680 | 442 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0024 | PTCI/MIDC | 16.4185 | 120.5888 | 0.16 | Terrestrial Optical Fiber Drop | 0.5 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0917 | 1 | 917 | 917 | 0304932021 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Rafael | 15.454 | 120.794 | R | 1489 | 425 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.9 | Terrestrial Optical Fiber Drop | 0.5 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0918 | 1 | 918 | 918 | 0402109047 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VIII | 14.4073 | 120.936 | U | 2881 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03245-C08 | PTCI/MIDC | 14.4097 | 120.9383 | 0.36 | Terrestrial Optical Fiber Drop | 0.5 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0919 | 1 | 919 | 919 | 1705204012 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Poblacion | 12.3264 | 121.3421 | U | 3852 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03378-C09 | PTCI/MIDC | 12.32 | 121.3406 | 0.73 | Terrestrial Optical Fiber Drop | 0.5 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0920 | 1 | 920 | 920 | 0403425016 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Vicente | 14.3415 | 121.0438 | U | 30211 | 9154 | 2746 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.38 | Terrestrial Optical Fiber Drop | 0.5 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0921 | 1 | 921 | 921 | 0403404013 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Pulo | 14.2423 | 121.1318 | U | 38490 | 11663 | 3499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02046-C08 | PTCI/MIDC | 14.239 | 121.1339 | 0.43 | Terrestrial Optical Fiber Drop | 0.5 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0922 | 1 | 922 | 922 | 0403426014 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Barangay I | 14.2788 | 121.4177 | R | 1367 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.63 | Terrestrial Optical Fiber Drop | 0.5 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0923 | 1 | 923 | 923 | 0501707001 | Region V (Bicol Region) | Camarines Sur | Cabusao | Barcelonita | 13.7722 | 123.0446 | R | 2478 | 590 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050056 | FTAP Globe | 13.7336 | 123.0213 | 4.98 | Terrestrial Optical Fiber Drop | 0.5 | 6.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0924 | 1 | 924 | 924 | 0305413032 | Region III (Central Luzon) | Pampanga | Mexico | San Lorenzo | 15.0682 | 120.7374 | R | 2989 | 747 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01646-B07 | PTCI/MIDC | 15.0675 | 120.7391 | 0.19 | Terrestrial Optical Fiber Drop | 0.5 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0925 | 1 | 925 | 925 | 0702219002 | Region VII (Central Visayas) | Cebu | Consolacion | Cansaga | 10.3788 | 123.9627 | U | 6651 | 1750 | 525 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00111-D12 | PTCI/MIDC | 10.3742 | 123.9666 | 0.67 | Terrestrial Optical Fiber Drop | 0.5 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0926 | 1 | 926 | 926 | 0403405032 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Mayapa | 14.2113 | 121.1273 | U | 31024 | 9401 | 2820 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03063-C08 | PTCI/MIDC | 14.21 | 121.1283 | 0.18 | Terrestrial Optical Fiber Drop | 0.5 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0927 | 1 | 927 | 927 | 0500514013 | Region V (Bicol Region) | Albay | Polangui | Centro Occidental | 13.2965 | 123.4865 | U | 3335 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050143 | FTAP Globe | 13.2882 | 123.4896 | 0.99 | Terrestrial Optical Fiber Drop | 0.5 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0928 | 1 | 928 | 928 | 0305406026 | Region III (Central Luzon) | Pampanga | Floridablanca | San Jose | 14.9853 | 120.511 | U | 9350 | 2337 | 701 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00959 | Edgepoint | 14.988 | 120.5114 | 0.3 | Terrestrial Optical Fiber Drop | 0.51 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0929 | 1 | 929 | 929 | 0405804002 | Region IV-A (CALABARZON) | Rizal | Binangonan | Batingan | 14.4726 | 121.1968 | U | 15585 | 4329 | 1299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0011 | PTCI/MIDC | 14.4723 | 121.1985 | 0.19 | Terrestrial Optical Fiber Drop | 0.5 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0930 | 1 | 930 | 930 | 0306914002 | Region III (Central Luzon) | Tarlac | San Manuel | Lanat | 15.7923 | 120.6061 | R | 2429 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 0.95 | Terrestrial Optical Fiber Drop | 0.51 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0931 | 1 | 931 | 931 | 1001305013 | Region X (Northern Mindanao) | Bukidnon | Impasug-ong | Poblacion | 8.3065 | 125.002 | U | 14202 | 3737 | 1121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0012 | PTCI/MIDC | 8.3034 | 124.9993 | 0.45 | Terrestrial Optical Fiber Drop | 0.51 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0932 | 1 | 932 | 932 | 0600413022 | Region VI (Western Visayas) | Aklan | Malinao | Tambuan | 11.6252 | 122.3008 | R | 1277 | 327 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060219 | FTAP Globe | 11.6476 | 122.3063 | 2.56 | Terrestrial Optical Fiber Drop | 0.51 | 4.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0933 | 1 | 933 | 933 | 0405801010 | Region IV-A (CALABARZON) | Rizal | Angono | San Pedro | 14.5296 | 121.1537 | U | 1739 | 483 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 450 | FTAP Smart | 14.5268 | 121.1582 | 0.13 | Terrestrial Optical Fiber Drop | 0.25 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0934 | 1 | 934 | 934 | 0402104019 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 8 | 14.3137 | 121.0538 | R | 3290 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.55 | Terrestrial Optical Fiber Drop | 0.51 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0935 | 1 | 935 | 935 | 0500506011 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 15 - Ilawod East Pob. | 13.1488 | 123.7527 | U | 2206 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0039 | PTCI/MIDC | 13.1354 | 123.7419 | 0.61 | Terrestrial Optical Fiber Drop | 1.85 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0936 | 1 | 936 | 936 | 0604527005 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 5 | 9.7526 | 122.4009 | R | 3304 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060396 | FTAP Globe | 9.7491 | 122.4063 | 0.71 | Terrestrial Optical Fiber Drop | 0.51 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0937 | 1 | 937 | 937 | 0102933025 | Region I (Ilocos Region) | Ilocos Sur | Tagudin | Las-ud | 16.939 | 120.4408 | R | 1128 | 296 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010068 | FTAP Globe | 16.9383 | 120.4402 | 0.11 | Terrestrial Optical Fiber Drop | 0.51 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0938 | 1 | 938 | 938 | 0306905032 | Region III (Central Luzon) | Tarlac | Concepcion | San Jose | 15.3264 | 120.6605 | U | 10904 | 2795 | 839 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00763 | Edgepoint | 15.323 | 120.6635 | 0.49 | Terrestrial Optical Fiber Drop | 0.51 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0939 | 1 | 939 | 939 | 0105531036 | Region I (Ilocos Region) | Pangasinan | Rosales | Don Antonio Village | 15.8915 | 120.6272 | R | 859 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01756-B07 | PTCI/MIDC | 15.8943 | 120.6276 | 0.32 | Terrestrial Optical Fiber Drop | 0.51 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0940 | 1 | 940 | 940 | 1380900013 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Tangos South | 14.6582 | 120.9484 | U | 18971 | 5498 | 1649 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01485 | Edgepoint | 14.6538 | 120.9609 | 0.35 | Terrestrial Optical Fiber Drop | 0.31 | 1.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0941 | 1 | 941 | 941 | 0105523007 | Region I (Ilocos Region) | Pangasinan | Mabini | Cabinuangan | 16.0817 | 119.9226 | R | 1568 | 435 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-00410 | Edgepoint | 16.0915 | 119.94 | 2.15 | Terrestrial Optical Fiber Drop | 0.51 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0942 | 1 | 942 | 942 | 1600301016 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Poblacion | 8.7144 | 125.7519 | U | 16880 | 4328 | 1298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0001 | PTCI/MIDC | 8.7141 | 125.7595 | 0.83 | Terrestrial Optical Fiber Drop | 0.51 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0943 | 1 | 943 | 943 | 1102401023 | Region XI (Davao Region) | Davao del Sur | Bansalan | Tubod | 6.792 | 125.2119 | R | 3650 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0001 | PTCI/MIDC | 6.7864 | 125.2163 | 0.79 | Terrestrial Optical Fiber Drop | 0.51 | 16.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0944 | 1 | 944 | 944 | 0103306005 | Region I (Ilocos Region) | La Union | Bangar | Bangaoilan West | 16.9001 | 120.4476 | R | 1049 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.23 | Terrestrial Optical Fiber Drop | 2.53 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0945 | 1 | 945 | 945 | 0501603030 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VII | 14.1164 | 122.958 | U | 1936 | 484 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03029-C10 | PTCI/MIDC | 14.1154 | 122.961 | 0.34 | Terrestrial Optical Fiber Drop | 0.51 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0946 | 1 | 946 | 946 | 0301423025 | Region III (Central Luzon) | Bulacan | Santa Maria | Tumana | 14.8131 | 120.9736 | U | 10877 | 3107 | 932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01171 | Edgepoint | 14.8148 | 120.9767 | 0.39 | Terrestrial Optical Fiber Drop | 0.51 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0947 | 1 | 947 | 947 | 0403406015 | Region IV-A (CALABARZON) | Laguna | Calauan | Prinza | 14.1424 | 121.3168 | R | 3113 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040288 | FTAP Globe | 14.1455 | 121.3143 | 0.44 | Terrestrial Optical Fiber Drop | 0.51 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0948 | 1 | 948 | 948 | 1130700158 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 25-C | 7.0865 | 125.6131 | U | 2000 | 588 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110454 | FTAP Globe | 7.185 | 125.4541 | 0.53 | Terrestrial Optical Fiber Drop | 1.03 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0949 | 1 | 949 | 949 | 0506208033 | Region V (Bicol Region) | Sorsogon | Gubat | Pinontingan | 12.9191 | 124.1257 | R | 1481 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 0.61 | Terrestrial Optical Fiber Drop | 0.51 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0950 | 1 | 950 | 950 | 0631000040 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Cuartero | 10.7236 | 122.5547 | U | 2173 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060264 | FTAP Globe | 10.7496 | 122.5698 | 0.07 | Terrestrial Optical Fiber Drop | 1.82 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0951 | 1 | 951 | 951 | 0203126016 | Region II (Cagayan Valley) | Isabela | Roxas | Rang-ayan | 17.1159 | 121.6249 | R | 1511 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01359-B06 | PTCI/MIDC | 17.1149 | 121.6222 | 0.29 | Terrestrial Optical Fiber Drop | 1.03 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0952 | 1 | 952 | 952 | 1380400016 | National Capital Region (NCR) | Metro Manila (NCR) | City of Malabon | San Agustin | 14.6622 | 120.9525 | U | 10993 | 3105 | 932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00261-A01 | PTCI/MIDC | 14.6619 | 120.951 | 0.16 | Terrestrial Optical Fiber Drop | 0.51 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0953 | 1 | 953 | 953 | 0501702013 | Region V (Bicol Region) | Camarines Sur | Balatan | Siramag | 13.3185 | 123.2398 | U | 4957 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050137 | FTAP Globe | 13.3165 | 123.2349 | 0.57 | Terrestrial Optical Fiber Drop | 0.51 | 14.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0954 | 1 | 954 | 954 | 1102403029 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 2 | 6.7505 | 125.3573 | U | 7839 | 2305 | 692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0071 | PTCI/MIDC | 6.7534 | 125.365 | 0.91 | Terrestrial Optical Fiber Drop | 0.52 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0955 | 1 | 955 | 955 | 0600401011 | Region VI (Western Visayas) | Aklan | Altavas | Poblacion | 11.535 | 122.4913 | R | 4795 | 1229 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 4.05 | Terrestrial Optical Fiber Drop | 0.51 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0956 | 1 | 956 | 956 | 0402103002 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban I | 14.461 | 120.9641 | U | 3517 | 1034 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040108 | FTAP Globe | 14.4232 | 120.9631 | 0.76 | Terrestrial Optical Fiber Drop | 0.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0957 | 1 | 957 | 957 | 0402106027 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Dionisio | 14.32 | 120.9566 | U | 7096 | 2087 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0032 | PTCI/MIDC | 14.3181 | 120.9773 | 0.25 | Terrestrial Optical Fiber Drop | 1.29 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0958 | 1 | 958 | 958 | 0301411003 | Region III (Central Luzon) | Bulacan | Marilao | Ibayo | 14.753 | 120.9597 | U | 8686 | 2481 | 744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0008 | PTCI/MIDC | 14.7535 | 120.9607 | 0.12 | Terrestrial Optical Fiber Drop | 0.52 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0959 | 1 | 959 | 959 | 0501606051 | Region V (Bicol Region) | Camarines Norte | Labo | Talobatib | 14.1816 | 122.7854 | R | 3954 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050012 | FTAP Globe | 14.1849 | 122.7842 | 0.39 | Terrestrial Optical Fiber Drop | 0.52 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0960 | 1 | 960 | 960 | 0405615016 | Region IV-A (CALABARZON) | Quezon | Dolores | Bulakin II | 14.0169 | 121.3863 | R | 2231 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040380 | FTAP Globe | 14.0132 | 121.3897 | 0.68 | Terrestrial Optical Fiber Drop | 0.46 | 4.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0961 | 1 | 961 | 961 | 0405809004 | Region IV-A (CALABARZON) | Rizal | Morong | Maybancal | 14.5251 | 121.2424 | U | 17211 | 4780 | 1434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01858 | Edgepoint | 14.5223 | 121.2408 | 0.36 | Terrestrial Optical Fiber Drop | 0.52 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0962 | 1 | 962 | 962 | 0402120005 | Region IV-A (CALABARZON) | Cavite | Tanza | Bucal | 14.3903 | 120.8622 | U | 17246 | 5072 | 1522 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.27 | Terrestrial Optical Fiber Drop | 0.52 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0963 | 1 | 963 | 963 | 0501605012 | Region V (Bicol Region) | Camarines Norte | Jose Panganiban | Parang | 14.2814 | 122.6941 | U | 6242 | 1560 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050004 | FTAP Globe | 14.2889 | 122.6958 | 0.85 | Terrestrial Optical Fiber Drop | 0.52 | 9.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0964 | 1 | 964 | 964 | 0908305023 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Poblacion | 7.7802 | 122.5881 | U | 4596 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0004 | PTCI/MIDC | 7.7816 | 122.588 | 0.16 | Terrestrial Optical Fiber Drop | 0.52 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0965 | 1 | 965 | 965 | 1001321022 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Nabago | 7.9094 | 125.094 | R | 2872 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0049 | PTCI/MIDC | 7.9041 | 125.1067 | 1.2 | Terrestrial Optical Fiber Drop | 0.44 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0966 | 1 | 966 | 966 | 0405809006 | Region IV-A (CALABARZON) | Rizal | Morong | San Jose | 14.525 | 121.2425 | R | 4110 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01858 | Edgepoint | 14.5223 | 121.2408 | 0.35 | Terrestrial Optical Fiber Drop | 0.51 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0967 | 1 | 967 | 967 | 1206312014 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Poblacion | 6.2184 | 125.0694 | U | 53313 | 14809 | 4443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCG0044 | PTCI/MIDC | 6.2191 | 125.075 | 0.63 | Terrestrial Optical Fiber Drop | 0.52 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0968 | 1 | 968 | 968 | 0604528041 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 2 | 10.7438 | 122.9641 | U | 2184 | 590 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060161 | FTAP BTS | 10.7427 | 122.9638 | 0.12 | Terrestrial Optical Fiber Drop | 0.23 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0969 | 1 | 969 | 969 | 0402109003 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-A | 14.4023 | 120.9405 | U | 6594 | 1939 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040121 | FTAP Globe | 14.4038 | 120.9443 | 0.44 | Terrestrial Optical Fiber Drop | 0.52 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0970 | 1 | 970 | 970 | 0631000032 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Calumpang | 10.687 | 122.5398 | U | 16557 | 3942 | 1183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0026 | PTCI/MIDC | 10.6895 | 122.5363 | 0.48 | Terrestrial Optical Fiber Drop | 0.52 | 3.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0971 | 1 | 971 | 971 | 0301412008 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Hulo | 14.7327 | 120.9569 | U | 2804 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01030-B07 | PTCI/MIDC | 14.7397 | 120.9711 | 0.31 | Terrestrial Optical Fiber Drop | 1.39 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0972 | 1 | 972 | 972 | 0305416010 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dolores | 15.0361 | 120.6827 | U | 21795 | 5448 | 1634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02616-B07 | PTCI/MIDC | 15.0339 | 120.6814 | 0.28 | Terrestrial Optical Fiber Drop | 0.52 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0973 | 1 | 973 | 973 | 1381300084 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Project 6 | 14.6626 | 121.0399 | U | 12595 | 4011 | 1203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000183 | FTAP Globe | 14.662 | 121.0414 | 0.18 | Terrestrial Optical Fiber Drop | 0.52 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0974 | 1 | 974 | 974 | 0102805044 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Tabug | 18.0543 | 120.5566 | R | 3406 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00049 | Edgepoint | 18.0553 | 120.5558 | 0.14 | Terrestrial Optical Fiber Drop | 0.52 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0975 | 1 | 975 | 975 | 1408107013 | Cordillera Administrative Region (CAR) | Apayao | Santa Marcela | San Carlos | 18.2913 | 121.436 | R | 1525 | 363 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-APA-02247 | Edgepoint | 18.2887 | 121.4356 | 0.3 | Terrestrial Optical Fiber Drop | 0.53 | 4.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0976 | 1 | 976 | 976 | 0301403005 | Region III (Central Luzon) | Bulacan | Baliuag | Concepcion | 14.9527 | 120.8889 | U | 10619 | 3034 | 910 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01065-B07 | PTCI/MIDC | 14.9538 | 120.8908 | 0.24 | Terrestrial Optical Fiber Drop | 0.53 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0977 | 1 | 977 | 977 | 0402113002 | Region IV-A (CALABARZON) | Cavite | Maragondon | Bucal I | 14.2729 | 120.7412 | R | 3478 | 1022 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02184-C08 | PTCI/MIDC | 14.2716 | 120.7386 | 0.31 | Terrestrial Optical Fiber Drop | 0.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0978 | 1 | 978 | 978 | 0203126025 | Region II (Cagayan Valley) | Isabela | Roxas | Sotero Nuesa | 17.1204 | 121.6137 | U | 6564 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0060 | PTCI/MIDC | 17.1203 | 121.6155 | 0.19 | Terrestrial Optical Fiber Drop | 0.53 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0979 | 1 | 979 | 979 | 0403428018 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pulong Santa Cruz | 14.28 | 121.0855 | U | 32250 | 9772 | 2932 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0009 | PTCI/MIDC | 14.2828 | 121.0916 | 0.73 | Terrestrial Optical Fiber Drop | 0.53 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0980 | 1 | 980 | 980 | 0105520012 | Region I (Ilocos Region) | Pangasinan | Infanta | Poblacion | 15.8224 | 119.9069 | R | 3276 | 910 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00569 | Edgepoint | 15.8208 | 119.9067 | 0.18 | Terrestrial Optical Fiber Drop | 0.53 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0981 | 1 | 981 | 981 | 0403425004 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | G.S.I.S. | 14.3414 | 121.0439 | R | 3100 | 939 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040151 | FTAP Globe | 14.347 | 121.0481 | 0.46 | Terrestrial Optical Fiber Drop | 0.52 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0982 | 1 | 982 | 982 | 0102822020 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Santa Ana | 18.1 | 120.7667 | R | 1302 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01220-B05 | PTCI/MIDC | 18.0958 | 120.7728 | 0.8 | Terrestrial Optical Fiber Drop | 0.53 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0983 | 1 | 983 | 983 | 0803738062 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Macabug | 10.9583 | 124.653 | U | 3817 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0042 | PTCI/MIDC | 10.9609 | 124.652 | 0.3 | Terrestrial Optical Fiber Drop | 0.53 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0984 | 1 | 984 | 984 | 1381300067 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Milagrosa | 14.6218 | 121.0682 | U | 6923 | 1688 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00470-A01 | PTCI/MIDC | 14.6229 | 121.0671 | 0.18 | Terrestrial Optical Fiber Drop | 0.53 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0985 | 1 | 985 | 985 | 0704623008 | Region VII (Central Visayas) | Negros Oriental | Valencia | Bong-ao | 9.2789 | 123.2487 | R | 3361 | 884 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070270 | FTAP Globe | 9.2811 | 123.2423 | 0.74 | Terrestrial Optical Fiber Drop | 0.53 | 4.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0986 | 1 | 986 | 986 | 0501720010 | Region V (Bicol Region) | Camarines Sur | Magarao | San Juan | 13.6624 | 123.1895 | R | 1180 | 280 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 0.88 | Terrestrial Optical Fiber Drop | 1.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0987 | 1 | 987 | 987 | 1004311009 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Natubo | 8.6573 | 124.7536 | R | 2804 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 4.98 | Terrestrial Optical Fiber Drop | 0.84 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1011 | 1 | 988 | 988 | 0102804012 | Region I (Ilocos Region) | Ilocos Norte | Bangui | San Lorenzo | 18.5383 | 120.7636 | R | 2295 | 620 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ILN-03184 | Edgepoint | 18.5335 | 120.7602 | 0.64 | Terrestrial Optical Fiber Drop | 0.54 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0989 | 1 | 989 | 989 | 0506215002 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | Peñafrancia | 12.6354 | 124.0936 | R | 852 | 213 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 0.13 | Terrestrial Optical Fiber Drop | 1.74 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0990 | 1 | 990 | 990 | 0402104017 | Region IV-A (CALABARZON) | Cavite | Carmona | Barangay 6 | 14.3139 | 121.054 | R | 767 | 225 | 68 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02005-C08 | PTCI/MIDC | 14.2994 | 121.0588 | 0.17 | Terrestrial Optical Fiber Drop | 0.53 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0991 | 1 | 991 | 991 | 1381300110 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Santol | 14.6126 | 121.0154 | U | 6590 | 1757 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01637 | Edgepoint | 14.6126 | 121.0162 | 0.08 | Terrestrial Optical Fiber Drop | 0.53 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0992 | 1 | 992 | 992 | 0105535018 | Region I (Ilocos Region) | Pangasinan | San Manuel | Sto. Domingo | 16.0712 | 120.6397 | U | 6146 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01761-B07 | PTCI/MIDC | 16.0657 | 120.6724 | 0.27 | Terrestrial Optical Fiber Drop | 3.16 | 1.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0993 | 1 | 993 | 993 | 0603035040 | Region VI (Western Visayas) | Iloilo | City of Passi | Poblacion Ilaya | 11.1093 | 122.6436 | U | 2603 | 685 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060054 | FTAP BTS | 11.1194 | 122.6461 | 1.15 | Terrestrial Optical Fiber Drop | 0.54 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0994 | 1 | 994 | 994 | 1381200008 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Kapasigan | 14.567 | 121.0845 | U | 4952 | 1519 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01786 | Edgepoint | 14.5755 | 121.0794 | 0.09 | Terrestrial Optical Fiber Drop | 0.34 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0995 | 1 | 995 | 995 | 0501731017 | Region V (Bicol Region) | Camarines Sur | Sagñay | San Isidro | 13.6054 | 123.5246 | R | 1378 | 328 | 98 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050090 | FTAP Globe | 13.6036 | 123.5204 | 0.49 | Terrestrial Optical Fiber Drop | 0.54 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0996 | 1 | 996 | 996 | 0401008018 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 3 | 13.8322 | 120.6343 | R | 1065 | 295 | 89 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 0.71 | Terrestrial Optical Fiber Drop | 0.53 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0997 | 1 | 997 | 997 | 0500517040 | Region V (Bicol Region) | Albay | City of Tabaco | San Ramon | 13.3479 | 123.7313 | R | 3225 | 786 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ALB-02560 | Edgepoint | 13.3488 | 123.728 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0998 | 1 | 998 | 998 | 0304906044 | Region III (Central Luzon) | Nueva Ecija | Cuyapo | San Jose | 15.7781 | 120.6691 | R | 1437 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01474-B07 | PTCI/MIDC | 15.7777 | 120.6688 | 0.05 | Terrestrial Optical Fiber Drop | 0.54 | 6.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0999 | 1 | 999 | 999 | 0500510021 | Region V (Bicol Region) | Albay | Malinao | Poblacion | 13.3977 | 123.7059 | R | 654 | 159 | 48 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050124 | FTAP Globe | 13.3997 | 123.7064 | 0.23 | Terrestrial Optical Fiber Drop | 0.54 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1000 | 1 | 1000 | 1000 | 0405625023 | Region IV-A (CALABARZON) | Quezon | Macalelon | San Isidro | 13.75 | 122.1333 | R | 784 | 206 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02000 | Edgepoint | 13.7491 | 122.1391 | 0.63 | Terrestrial Optical Fiber Drop | 0.54 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)

## Batch 2 (1,001 - 2,000)
5G FWA Candidate Site Schedule — Batch 2 (Expansion 1,000 Sites)
Carrier-Grade Candidate Siting Data for Turnkey Bidding (Lots 1, 2, 4, 5) ¦ Band n50 SA Architecture
Site ID | Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Households | Target Subscribers | Carrier Spectrum | Initial BTS | Civil Siting Category | Tower Screening Class | Nearest Tower ID | Nearest TowerCo | Nearest Tower Latitude | Nearest Tower Longitude | Dist to Tower (km) | Transmission Medium | Dist to Node (km) | Dist to Line (km) | Power Arrangement
FWA-SITE-0710 | 2 | 1 | 1001 | 0405642012 | Region IV-A (CALABARZON) | Quezon | San Francisco | Poblacion | 13.3494 | 122.5199 | U | 5458 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040623 | FTAP Globe | 13.3485 | 122.5191 | 0.14 | Satellite LEO Backhaul (Starlink Business) | 0.4 | 23.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1002 | 2 | 2 | 1002 | 0501608019 | Region V (Bicol Region) | Camarines Norte | Paracale | Palanas | 14.2794 | 122.7916 | R | 4124 | 1031 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.43 | Terrestrial Optical Fiber Drop | 0.54 | 9.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0733 | 2 | 3 | 1003 | 0205007022 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Norte | Macabenga | 16.2108 | 121.2328 | R | 1807 | 475 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUV-00385 | Edgepoint | 16.1959 | 121.2371 | 1.72 | Satellite LEO Backhaul (Starlink Business) | 0.41 | 21.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0010 | 2 | 4 | 1004 | 0405640007 | Region IV-A (CALABARZON) | Quezon | San Andres | Poblacion | 13.3238 | 122.6769 | U | 5242 | 1379 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-QUE-02071 | Edgepoint | 13.3259 | 122.6776 | 0.24 | Satellite LEO Backhaul (Starlink Business) | 0.05 | 29.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1005 | 2 | 5 | 1005 | 0401020001 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Banaba | 13.8858 | 121.2177 | R | 3949 | 1096 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 1.17 | Terrestrial Optical Fiber Drop | 0.54 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1006 | 2 | 6 | 1006 | 1380900018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Tanza 2 | 14.6789 | 120.9337 | U | 16184 | 4650 | 1395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02267-A01 | PTCI/MIDC | 14.6624 | 120.9638 | 0.21 | Terrestrial Optical Fiber Drop | 0.96 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1007 | 2 | 7 | 1007 | 0803714015 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Poblacion Zone I | 11.2923 | 124.6403 | R | 2449 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 1.65 | Terrestrial Optical Fiber Drop | 0.54 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1008 | 2 | 8 | 1008 | 0102924013 | Region I (Ilocos Region) | Ilocos Sur | Santa Cruz | Casilagan | 17.0693 | 120.4595 | R | 908 | 238 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTIRG0007 | PTCI/MIDC | 17.0711 | 120.4566 | 0.48 | Terrestrial Optical Fiber Drop | 0.36 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0053 | 2 | 9 | 1009 | 1705312003 | MIMAROPA Region | Palawan | El Nido | Barotuan | 11.3064 | 119.4504 | U | 2900 | 743 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170207 | FTAP Globe | 11.3359 | 119.4569 | 3.36 | Satellite LEO Backhaul (Starlink Business) | 0.09 | 54.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1010 | 2 | 10 | 1010 | 0304903044 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | M. S. Garcia | 15.4772 | 120.9631 | U | 6701 | 1914 | 574 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00715 | Edgepoint | 15.4745 | 120.967 | 0.52 | Terrestrial Optical Fiber Drop | 0.54 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0988 | 2 | 11 | 1011 | 1705312013 | MIMAROPA Region | Palawan | El Nido | Sibaltan | 11.3032 | 119.561 | R | 2377 | 609 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170208 | FTAP Globe | 11.2711 | 119.5606 | 3.57 | Satellite LEO Backhaul (Starlink Business) | 0.53 | 53.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1012 | 2 | 12 | 1012 | 0203108071 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Union | 16.9596 | 121.816 | R | 1605 | 422 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00215 | Edgepoint | 16.9565 | 121.815 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1013 | 2 | 13 | 1013 | 1004321002 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Bagocboc | 8.4178 | 124.5021 | R | 3374 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100152 | FTAP Globe | 8.4584 | 124.5671 | 8.45 | Terrestrial Optical Fiber Drop | 0.54 | 12.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0026 | 2 | 14 | 1014 | 0201506022 | Region II (Cagayan Valley) | Cagayan | Baggao | Dalla | 17.9546 | 121.8907 | R | 1720 | 441 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH020022 | FTAP Globe | 17.9559 | 121.9101 | 2.05 | Satellite LEO Backhaul (Starlink Business) | 0.07 | 21.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1015 | 2 | 15 | 1015 | 0603031019 | Region VI (Western Visayas) | Iloilo | Mina | Talibong Pequeño | 10.9406 | 122.5734 | R | 557 | 146 | 44 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 2.46 | Terrestrial Optical Fiber Drop | 1.73 | 1.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1016 | 2 | 16 | 1016 | 0403425021 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Calendola | 14.3428 | 121.0355 | R | 4162 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.55 | Terrestrial Optical Fiber Drop | 0.54 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1017 | 2 | 17 | 1017 | 0203101002 | Region II (Cagayan Valley) | Isabela | Alicia | Antonino | 16.7828 | 121.6977 | U | 4886 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 0.36 | Terrestrial Optical Fiber Drop | 0.54 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0062 | 2 | 18 | 1018 | 1402707017 | Cordillera Administrative Region (CAR) | Ifugao | Alfonso Lista | Santa Maria | 16.891 | 121.4596 | U | 5445 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-IFU-00229 | Edgepoint | 16.9123 | 121.4906 | 4.06 | Satellite LEO Backhaul (Starlink Business) | 0.09 | 21.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1019 | 2 | 19 | 1019 | 0603047007 | Region VI (Western Visayas) | Iloilo | Zarraga | Gines | 10.7402 | 122.5412 | R | 1344 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.92 | Terrestrial Optical Fiber Drop | 2.85 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1020 | 2 | 20 | 1020 | 0403403009 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Langkiwa | 14.2999 | 121.0602 | U | 43327 | 13129 | 3939 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02005-C08 | PTCI/MIDC | 14.2994 | 121.0588 | 0.16 | Terrestrial Optical Fiber Drop | 0.55 | 1.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0086 | 2 | 21 | 1021 | 0304907011 | Region III (Central Luzon) | Nueva Ecija | Gabaldon | Malinao | 15.483 | 121.3325 | R | 2759 | 788 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02887-B07 | PTCI/MIDC | 15.478 | 121.3066 | 2.83 | Satellite LEO Backhaul (Starlink Business) | 0.1 | 23.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0106 | 2 | 22 | 1022 | 0205009003 | Region II (Cagayan Valley) | Nueva Vizcaya | Kasibu | Poblacion | 16.3166 | 121.2954 | R | 2596 | 683 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01522-B05 | PTCI/MIDC | 16.3128 | 121.2922 | 0.54 | Satellite LEO Backhaul (Starlink Business) | 0.12 | 21.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1023 | 2 | 23 | 1023 | 0500506042 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 8 - Bagumbayan | 13.1416 | 123.7354 | U | 2781 | 678 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050176 | FTAP Globe | 13.1455 | 123.7378 | 0.5 | Terrestrial Optical Fiber Drop | 0.55 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0136 | 2 | 24 | 1024 | 0405620026 | Region IV-A (CALABARZON) | Quezon | Infanta | Libjo | 14.7545 | 121.6659 | R | 2438 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01234 | Edgepoint | 14.7475 | 121.6479 | 2.09 | Satellite LEO Backhaul (Starlink Business) | 0.13 | 42.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1025 | 2 | 25 | 1025 | 0501728010 | Region V (Bicol Region) | Camarines Sur | Pili | La Purisima | 13.5621 | 123.2864 | R | 3202 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0710 | FTAP Smart | 13.5587 | 123.2775 | 1.04 | Terrestrial Optical Fiber Drop | 0.55 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1026 | 2 | 26 | 1026 | 0402106041 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Santa Cruz I | 14.3128 | 120.9607 | U | 5381 | 1582 | 475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0082 | FTAP Smart | 14.3162 | 120.9648 | 0.59 | Terrestrial Optical Fiber Drop | 0.55 | 1.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0165 | 2 | 27 | 1027 | 0205008008 | Region II (Cagayan Valley) | Nueva Vizcaya | Dupax del Sur | Ganao | 16.1647 | 121.1809 | R | 1373 | 361 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-NUV-00385 | Edgepoint | 16.1959 | 121.2371 | 6.93 | Satellite LEO Backhaul (Starlink Business) | 0.15 | 20.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0166 | 2 | 28 | 1028 | 1404405007 | Cordillera Administrative Region (CAR) | Mountain Province | Natonin | Poblacion | 17.1081 | 121.2787 | R | 1430 | 386 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140139 | FTAP Globe | 17.111 | 121.2786 | 0.32 | Satellite LEO Backhaul (Starlink Business) | 0.15 | 21.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0217 | 2 | 29 | 1029 | 0501711048 | Region V (Bicol Region) | Camarines Sur | Caramoan | Tawog | 13.7728 | 123.8641 | U | 1800 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050052 | FTAP Globe | 13.77 | 123.8625 | 0.35 | Satellite LEO Backhaul (Starlink Business) | 0.18 | 38.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1030 | 2 | 30 | 1030 | 1408105021 | Cordillera Administrative Region (CAR) | Apayao | Luna | San Isidro Sur | 18.3351 | 121.3808 | R | 1739 | 414 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140100 | FTAP Globe | 18.3288 | 121.3546 | 2.85 | Terrestrial Optical Fiber Drop | 0.55 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1031 | 2 | 31 | 1031 | 0401004005 | Region IV-A (CALABARZON) | Batangas | Balete | Makina | 14.0201 | 121.1016 | R | 3732 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 0.98 | Terrestrial Optical Fiber Drop | 0.55 | 6.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1032 | 2 | 32 | 1032 | 1705202001 | MIMAROPA Region | Oriental Mindoro | Bansud | Alcadesma | 12.8395 | 121.4598 | R | 1907 | 488 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170107 | FTAP Globe | 12.8565 | 121.4577 | 1.9 | Terrestrial Optical Fiber Drop | 0.55 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1033 | 2 | 33 | 1033 | 0604521003 | Region VI (Western Visayas) | Negros Occidental | Pontevedra | Barangay II | 10.368 | 122.8694 | R | 2056 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060374 | FTAP Globe | 10.3746 | 122.8671 | 0.78 | Terrestrial Optical Fiber Drop | 0.55 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1034 | 2 | 34 | 1034 | 0205006003 | Region II (Cagayan Valley) | Nueva Vizcaya | Diadi | Bugnay | 16.6571 | 121.3731 | R | 1750 | 460 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUV_0006 | LDIC | 121.3694 | 16.6623 | 0.7 | Terrestrial Optical Fiber Drop | 0.55 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1035 | 2 | 35 | 1035 | 0306916059 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Francisco | 15.4239 | 120.5974 | R | 3004 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00733 | Edgepoint | 15.4163 | 120.6016 | 0.96 | Terrestrial Optical Fiber Drop | 0.55 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1036 | 2 | 36 | 1036 | 0301412018 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Pantoc | 14.766 | 120.9839 | U | 13146 | 3756 | 1127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01214 | Edgepoint | 14.7649 | 120.9827 | 0.18 | Terrestrial Optical Fiber Drop | 0.55 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1037 | 2 | 37 | 1037 | 1004308045 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 20 | 8.8269 | 125.1003 | U | 3364 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.33 | Terrestrial Optical Fiber Drop | 0.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0262 | 2 | 38 | 1038 | 0504117036 | Region V (Bicol Region) | Masbate | Placer | Villa Inocencio | 11.8695 | 123.9082 | U | 5173 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03138-C10 | PTCI/MIDC | 11.869 | 123.9056 | 0.28 | Satellite LEO Backhaul (Starlink Business) | 0.2 | 40.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1039 | 2 | 39 | 1039 | 0405810008 | Region IV-A (CALABARZON) | Rizal | Pililla | Quisao | 14.4365 | 121.3356 | U | 16563 | 4600 | 1380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01902 | Edgepoint | 14.438 | 121.3354 | 0.17 | Terrestrial Optical Fiber Drop | 0.55 | 2.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1040 | 2 | 40 | 1040 | 1630400071 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Ong Yiu Pob. | 8.9558 | 125.5369 | U | 5507 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130071 | FTAP Globe | 8.9621 | 125.5348 | 0.74 | Terrestrial Optical Fiber Drop | 0.55 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0297 | 2 | 41 | 1041 | 0405617001 | Region IV-A (CALABARZON) | Quezon | General Nakar | Anoling | 14.7554 | 121.6236 | R | 3791 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040005 | FTAP Globe | 14.7565 | 121.6198 | 0.43 | Satellite LEO Backhaul (Starlink Business) | 0.22 | 40.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0303 | 2 | 42 | 1042 | 0500513006 | Region V (Bicol Region) | Albay | Pio Duran | Binodegahan | 13.0616 | 123.4584 | R | 2590 | 631 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0038 | PTCI/MIDC | 13.0561 | 123.4573 | 0.62 | Satellite LEO Backhaul (Starlink Business) | 0.22 | 20.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-0519 | 2 | 43 | 1043 | 0405638004 | Region IV-A (CALABARZON) | Quezon | Real | Kiloloran | 14.6422 | 121.6065 | R | 2230 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-01455 | Edgepoint | 14.6633 | 121.6056 | 2.35 | Satellite LEO Backhaul (Starlink Business) | 0.31 | 28.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1044 | 2 | 44 | 1044 | 0105514017 | Region I (Ilocos Region) | Pangasinan | Bolinao | Luciente 1.0 | 16.3892 | 119.9 | U | 5519 | 1533 | 460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1705 | FTAP Smart | 16.389 | 119.8995 | 0.05 | Terrestrial Optical Fiber Drop | 0.55 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1045 | 2 | 45 | 1045 | 1606801015 | Region XIII (Caraga) | Surigao del Sur | Barobo | Poblacion | 17.105 | 122.2742 | U | 14683 | 3581 | 1074 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130030 | FTAP BTS | 8.5393 | 126.1199 | 0.73 | Terrestrial Optical Fiber Drop | 27.54 | 37.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1046 | 2 | 46 | 1046 | 0201502011 | Region II (Cagayan Valley) | Cagayan | Alcala | Centro Sur | 17.9023 | 121.6586 | R | 3026 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0061 | LDIC | 121.6537 | 17.9074 | 0.77 | Terrestrial Optical Fiber Drop | 0.55 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1047 | 2 | 47 | 1047 | 0405803006 | Region IV-A (CALABARZON) | Rizal | Baras | Concepcion | 14.5215 | 121.2679 | R | 1095 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040068 | FTAP Globe | 14.522 | 121.2696 | 0.2 | Terrestrial Optical Fiber Drop | 0.56 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1048 | 2 | 48 | 1048 | 0103301025 | Region I (Ilocos Region) | La Union | Agoo | San Julian West | 16.3214 | 120.347 | R | 2132 | 576 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0015 | LDIC | 16.3241 | 120.3738 | 0.64 | Terrestrial Optical Fiber Drop | 2.3 | 2.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1049 | 2 | 49 | 1049 | 0304927016 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tambo Adorable | 15.3658 | 120.9332 | U | 6398 | 1828 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1327 | FTAP Smart | 15.3572 | 120.9313 | 0.98 | Terrestrial Optical Fiber Drop | 0.55 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1050 | 2 | 50 | 1050 | 0306905019 | Region III (Central Luzon) | Tarlac | Concepcion | Minane | 15.3201 | 120.6508 | R | 3879 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.27 | Terrestrial Optical Fiber Drop | 0.56 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1051 | 2 | 51 | 1051 | 0501717030 | Region V (Bicol Region) | Camarines Sur | Lagonoy | San Rafael | 13.7276 | 123.519 | R | 2163 | 515 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4025 | FTAP Smart | 13.7298 | 123.5199 | 0.26 | Terrestrial Optical Fiber Drop | 0.56 | 4.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1052 | 2 | 52 | 1052 | 1380900007 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Navotas West | 14.6583 | 120.948 | U | 6293 | 1787 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01450 | Edgepoint | 14.6645 | 120.9516 | 0.19 | Terrestrial Optical Fiber Drop | 0.3 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1053 | 2 | 53 | 1053 | 0105519015 | Region I (Ilocos Region) | Pangasinan | Dasol | San Vicente | 15.9897 | 119.8806 | R | 1403 | 389 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.67 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1054 | 2 | 54 | 1054 | 0300810022 | Region III (Central Luzon) | Bataan | Orion | San Vicente | 14.6181 | 120.5768 | R | 1391 | 386 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0002 | PTCI/MIDC | 14.6145 | 120.5801 | 0.45 | Terrestrial Optical Fiber Drop | 0.39 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1055 | 2 | 55 | 1055 | 0105519016 | Region I (Ilocos Region) | Pangasinan | Dasol | Tambac | 15.9898 | 119.8806 | R | 891 | 247 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.66 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1056 | 2 | 56 | 1056 | 0301421043 | Region III (Central Luzon) | Bulacan | San Miguel | San Agustin | 15.1378 | 120.9621 | R | 4519 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030029 | FTAP BTS | 15.1372 | 120.9654 | 0.37 | Terrestrial Optical Fiber Drop | 0.56 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1057 | 2 | 57 | 1057 | 0105519007 | Region I (Ilocos Region) | Pangasinan | Dasol | Macalang | 15.9897 | 119.8806 | R | 1955 | 543 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.67 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1058 | 2 | 58 | 1058 | 0203108059 | Region II (Cagayan Valley) | Isabela | City of Cauayan | San Fermin | 16.9373 | 121.7606 | U | 12480 | 3284 | 985 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C20 | FTAP Smart | 16.9396 | 121.7643 | 0.46 | Terrestrial Optical Fiber Drop | 0.56 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1059 | 2 | 59 | 1059 | 0403406006 | Region IV-A (CALABARZON) | Laguna | Calauan | Lamot 1 | 14.1544 | 121.326 | R | 3215 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02343-C08 | PTCI/MIDC | 14.1396 | 121.3118 | 0.33 | Terrestrial Optical Fiber Drop | 1.61 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1060 | 2 | 60 | 1060 | 0105519011 | Region I (Ilocos Region) | Pangasinan | Dasol | Malimpin | 15.9898 | 119.8806 | R | 1659 | 460 | 138 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02229 | Edgepoint | 15.993 | 119.8858 | 0.66 | Terrestrial Optical Fiber Drop | 0.56 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1061 | 2 | 61 | 1061 | 0702220005 | Region VII (Central Visayas) | Cebu | Cordova | Cogon | 10.2655 | 123.9511 | R | 2980 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0230 | PTCI/MIDC | 10.2681 | 123.9526 | 0.33 | Terrestrial Optical Fiber Drop | 0.56 | 6.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1062 | 2 | 62 | 1062 | 0402122006 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | San Agustin | 14.2875 | 120.8688 | U | 9798 | 2881 | 864 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4408 | FTAP Smart | 14.2836 | 120.8648 | 0.61 | Terrestrial Optical Fiber Drop | 0.56 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1063 | 2 | 63 | 1063 | 0603007014 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Lagubang | 10.8934 | 122.7042 | R | 2863 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 0.49 | Terrestrial Optical Fiber Drop | 0.56 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1064 | 2 | 64 | 1064 | 0401023020 | Region IV-A (CALABARZON) | Batangas | San Juan | Lipahan | 13.8305 | 121.3972 | R | 4248 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BTG-03175 | Edgepoint | 13.8273 | 121.397 | 0.36 | Terrestrial Optical Fiber Drop | 0.56 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1065 | 2 | 65 | 1065 | 0103303034 | Region I (Ilocos Region) | La Union | Bacnotan | Poblacion | 16.7226 | 120.3533 | U | 3632 | 981 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01390-B05 | PTCI/MIDC | 16.7188 | 120.3533 | 0.42 | Terrestrial Optical Fiber Drop | 0.56 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1066 | 2 | 66 | 1066 | 0604520024 | Region VI (Western Visayas) | Negros Occidental | Murcia | Salvacion | 10.6018 | 123.0439 | U | 6825 | 1844 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 3.51 | Terrestrial Optical Fiber Drop | 0.56 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1067 | 2 | 67 | 1067 | 0103320001 | Region I (Ilocos Region) | La Union | Tubao | Amallapay | 16.3278 | 120.4087 | R | 2032 | 549 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01404-B05 | PTCI/MIDC | 16.3395 | 120.406 | 1.33 | Terrestrial Optical Fiber Drop | 0.56 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1068 | 2 | 68 | 1068 | 1004306020 | Region X (Northern Mindanao) | Misamis Oriental | Claveria | Poblacion | 8.6146 | 124.8975 | U | 10929 | 2802 | 841 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100116 | FTAP Globe | 8.6136 | 124.8946 | 0.33 | Terrestrial Optical Fiber Drop | 0.56 | 13.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1069 | 2 | 69 | 1069 | 1381500026 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | San Miguel | 14.5118 | 121.0709 | U | 11833 | 3113 | 934 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-01860 | Edgepoint | 14.5168 | 121.075 | 0.31 | Terrestrial Optical Fiber Drop | 0.68 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1070 | 2 | 70 | 1070 | 0631000096 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Lopez Jaena Sur | 10.7106 | 122.5719 | U | 2256 | 537 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0029 | PTCI/MIDC | 10.7118 | 122.5727 | 0.16 | Terrestrial Optical Fiber Drop | 0.56 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1071 | 2 | 71 | 1071 | 0730600063 | Region VII (Central Visayas) | Cebu | City of Cebu | Quiot Pardo | 10.2881 | 123.8563 | U | 28018 | 8755 | 2627 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070025 | FTAP BTS | 10.2911 | 123.8552 | 0.35 | Terrestrial Optical Fiber Drop | 0.56 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1072 | 2 | 72 | 1072 | 0305409011 | Region III (Central Luzon) | Pampanga | Mabalacat City | Lakandula | 15.1758 | 120.5829 | U | 8899 | 2224 | 667 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02981-B07 | PTCI/MIDC | 15.1789 | 120.582 | 0.36 | Terrestrial Optical Fiber Drop | 0.56 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1073 | 2 | 73 | 1073 | 0501608002 | Region V (Bicol Region) | Camarines Norte | Paracale | Bagumbayan | 14.2834 | 122.7833 | U | 5367 | 1341 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050006 | FTAP Globe | 14.2795 | 122.7877 | 0.63 | Terrestrial Optical Fiber Drop | 0.57 | 9.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1074 | 2 | 74 | 1074 | 0301415003 | Region III (Central Luzon) | Bulacan | Pandi | Bunsuran III | 14.8626 | 120.9361 | U | 2562 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01092 | Edgepoint | 14.8681 | 120.9559 | 1.28 | Terrestrial Optical Fiber Drop | 2.32 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1075 | 2 | 75 | 1075 | 0103317015 | Region I (Ilocos Region) | La Union | Santo Tomas | Namboongan | 16.2935 | 120.381 | R | 2472 | 668 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010116 | FTAP Globe | 16.2914 | 120.3899 | 0.99 | Terrestrial Optical Fiber Drop | 0.56 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1076 | 2 | 76 | 1076 | 0201503011 | Region II (Cagayan Valley) | Cagayan | Allacapan | Centro West | 18.222 | 121.5558 | R | 1951 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01186-B06 | PTCI/MIDC | 18.2268 | 121.5579 | 0.58 | Terrestrial Optical Fiber Drop | 0.57 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1077 | 2 | 77 | 1077 | 0301422034 | Region III (Central Luzon) | Bulacan | San Rafael | Ulingao | 14.9732 | 120.9174 | U | 3879 | 1108 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030518 | FTAP Globe | 14.9711 | 120.9162 | 0.27 | Terrestrial Optical Fiber Drop | 0.56 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1078 | 2 | 78 | 1078 | 0403425005 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Landayan | 14.3535 | 121.0679 | U | 36431 | 11039 | 3312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0002 | PTCI/MIDC | 14.3522 | 121.0664 | 0.22 | Terrestrial Optical Fiber Drop | 0.57 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1079 | 2 | 79 | 1079 | 0402120027 | Region IV-A (CALABARZON) | Cavite | Tanza | Lambingan | 14.3747 | 120.8538 | R | 2904 | 854 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040136 | FTAP Globe | 14.3739 | 120.827 | 0.44 | Terrestrial Optical Fiber Drop | 0.69 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1080 | 2 | 80 | 1080 | 0405619047 | Region IV-A (CALABARZON) | Quezon | Gumaca | Tabing Dagat | 13.9155 | 122.1256 | U | 2559 | 673 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-QUE-03196 | Edgepoint | 13.921 | 122.1079 | 0.76 | Terrestrial Optical Fiber Drop | 2.1 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1081 | 2 | 81 | 1081 | 0402104001 | Region IV-A (CALABARZON) | Cavite | Carmona | Bancal | 14.282 | 121.0072 | U | 17076 | 5022 | 1507 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.88 | Terrestrial Optical Fiber Drop | 0.57 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1082 | 2 | 82 | 1082 | 1004318010 | Region X (Northern Mindanao) | Misamis Oriental | Manticao | Poblacion | 8.4043 | 124.2908 | U | 9067 | 2324 | 697 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0066 | PTCI/MIDC | 8.4036 | 124.2859 | 0.54 | Terrestrial Optical Fiber Drop | 0.57 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1083 | 2 | 83 | 1083 | 0731300006 | Region VII (Central Visayas) | Cebu | City of Mandaue | Cambaro | 10.3467 | 123.9405 | U | 8999 | 2571 | 771 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070334 | FTAP Globe | 10.3495 | 123.929 | 0.48 | Terrestrial Optical Fiber Drop | 0.86 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1084 | 2 | 84 | 1084 | 0704604001 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Barangay I | 9.5937 | 123.1194 | U | 3621 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0004 | PTCI/MIDC | 9.5938 | 123.1254 | 0.66 | Terrestrial Optical Fiber Drop | 0.57 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1085 | 2 | 85 | 1085 | 0501705023 | Region V (Bicol Region) | Camarines Sur | Buhi | San Buenaventura | 13.4159 | 123.5143 | U | 2359 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCSG0019 | PTCI/MIDC | 13.3969 | 123.5113 | 1.78 | Terrestrial Optical Fiber Drop | 0.04 | 10.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1086 | 2 | 86 | 1086 | 0203120019 | Region II (Cagayan Valley) | Isabela | Naguilian | San Manuel | 17.0218 | 121.8651 | R | 2683 | 706 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ISA-00197 | Edgepoint | 17.0258 | 121.862 | 0.55 | Terrestrial Optical Fiber Drop | 0.57 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1087 | 2 | 87 | 1087 | 0301414002 | Region III (Central Luzon) | Bulacan | Obando | Catanghalan | 14.7069 | 120.9412 | U | 3385 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030623 | FTAP Globe | 14.7059 | 120.9421 | 0.14 | Terrestrial Optical Fiber Drop | 0.57 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1088 | 2 | 88 | 1088 | 0304911049 | Region III (Central Luzon) | Nueva Ecija | Guimba | Saint John District | 15.66 | 120.7716 | R | 1937 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01413-B07 | PTCI/MIDC | 15.6577 | 120.7705 | 0.28 | Terrestrial Optical Fiber Drop | 0.57 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1089 | 2 | 89 | 1089 | 0500503004 | Region V (Bicol Region) | Albay | Daraga | Bagumbayan | 13.144 | 123.7159 | U | 4020 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0036 | PTCI/MIDC | 13.1437 | 123.7182 | 0.25 | Terrestrial Optical Fiber Drop | 0.57 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1090 | 2 | 90 | 1090 | 0105532051 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Mamarlao | 15.9159 | 120.3286 | R | 3147 | 874 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00525 | Edgepoint | 15.9336 | 120.3479 | 0.17 | Terrestrial Optical Fiber Drop | 2.5 | 2.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1091 | 2 | 91 | 1091 | 0102812044 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 27, Nstra. Sra. De Soledad | 18.1923 | 120.6108 | R | 1685 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.35 | Terrestrial Optical Fiber Drop | 3.05 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1092 | 2 | 92 | 1092 | 0405812014 | Region IV-A (CALABARZON) | Rizal | Tanay | San Isidro | 14.4956 | 121.2793 | R | 3187 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02631-A04 | PTCI/MIDC | 14.4979 | 121.2773 | 0.33 | Terrestrial Optical Fiber Drop | 0.57 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1093 | 2 | 93 | 1093 | 0600412010 | Region VI (Western Visayas) | Aklan | Malay | Manoc-Manoc | 11.95 | 121.9409 | U | 21135 | 5419 | 1626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060214 | FTAP Globe | 11.9463 | 121.9425 | 0.45 | Terrestrial Optical Fiber Drop | 0.57 | 2.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1094 | 2 | 94 | 1094 | 1705214023 | MIMAROPA Region | Oriental Mindoro | Socorro | Zone IV | 13.0585 | 121.4038 | U | 2287 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170095 | FTAP Globe | 13.0601 | 121.4094 | 0.62 | Terrestrial Optical Fiber Drop | 0.57 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1095 | 2 | 95 | 1095 | 0506214013 | Region V (Bicol Region) | Sorsogon | Prieto Diaz | Rizal | 13.048 | 124.1917 | R | 1095 | 273 | 82 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050197 | FTAP Globe | 13.0399 | 124.192 | 0.9 | Terrestrial Optical Fiber Drop | 0.57 | 15.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1096 | 2 | 96 | 1096 | 0403411004 | Region IV-A (CALABARZON) | Laguna | Los Baños | Batong Malake | 14.1741 | 121.2435 | U | 13788 | 4178 | 1253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.26 | Terrestrial Optical Fiber Drop | 0.58 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1097 | 2 | 97 | 1097 | 0402117010 | Region IV-A (CALABARZON) | Cavite | Rosario | Tejeros Convention | 14.403 | 120.86 | U | 21580 | 6347 | 1904 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040117 | FTAP Globe | 14.409 | 120.8561 | 0.79 | Terrestrial Optical Fiber Drop | 0.57 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1098 | 2 | 98 | 1098 | 0501608004 | Region V (Bicol Region) | Camarines Norte | Paracale | Batobalani | 14.2351 | 122.7453 | U | 5003 | 1250 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050009 | FTAP Globe | 14.2156 | 122.7526 | 2.31 | Terrestrial Optical Fiber Drop | 0.57 | 5.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1099 | 2 | 99 | 1099 | 0405610012 | Region IV-A (CALABARZON) | Quezon | Catanauan | Bolo | 13.6291 | 122.2578 | R | 1367 | 359 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040613 | FTAP Globe | 13.6328 | 122.2423 | 1.72 | Terrestrial Optical Fiber Drop | 0.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1100 | 2 | 100 | 1100 | 1380900003 | National Capital Region (NCR) | Metro Manila (NCR) | City of Navotas | Bagumbayan South | 14.6512 | 120.9486 | U | 4489 | 1328 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMG0024 | PTCI/MIDC | 14.6496 | 120.9492 | 0.19 | Terrestrial Optical Fiber Drop | 0.58 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1101 | 2 | 101 | 1101 | 0301419007 | Region III (Central Luzon) | Bulacan | San Ildefonso | Basuit | 15.0409 | 120.99 | R | 2299 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030486 | FTAP Globe | 15.054 | 121.0004 | 1.84 | Terrestrial Optical Fiber Drop | 0.57 | 5.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1102 | 2 | 102 | 1102 | 0201517013 | Region II (Cagayan Valley) | Cagayan | Lasam | Ignacio Jurado | 18.0655 | 121.6097 | R | 1757 | 450 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03292-B06 | PTCI/MIDC | 18.0629 | 121.6086 | 0.31 | Terrestrial Optical Fiber Drop | 0.58 | 3.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1103 | 2 | 103 | 1103 | 1380500006 | National Capital Region (NCR) | Metro Manila (NCR) | City of Mandaluyong | Barangka Itaas | 14.5836 | 121.0336 | U | 11354 | 3639 | 1092 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-02647 | Edgepoint | 14.5884 | 121.0398 | 0.37 | Terrestrial Optical Fiber Drop | 0.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1104 | 2 | 104 | 1104 | 1102404021 | Region XI (Davao Region) | Davao del Sur | Hagonoy | Poblacion | 6.6839 | 125.3012 | R | 4650 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110527 | FTAP Globe | 6.6897 | 125.2969 | 0.8 | Terrestrial Optical Fiber Drop | 0.58 | 4.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1105 | 2 | 105 | 1105 | 1630400007 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Ampayon | 8.9631 | 125.605 | U | 14288 | 3484 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130073 | FTAP Globe | 8.9578 | 125.5836 | 2.42 | Terrestrial Optical Fiber Drop | 0.58 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1106 | 2 | 106 | 1106 | 0702210027 | Region VII (Central Visayas) | Cebu | Barili | Mantalongon | 10.1252 | 123.5762 | R | 3081 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070364 | FTAP Globe | 10.1317 | 123.5785 | 0.76 | Terrestrial Optical Fiber Drop | 0.58 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1107 | 2 | 107 | 1107 | 0501603027 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay IV | 14.117 | 122.949 | U | 7810 | 1952 | 586 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S92 | FTAP Smart | 14.1147 | 122.9549 | 0.69 | Terrestrial Optical Fiber Drop | 0.58 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1108 | 2 | 108 | 1108 | 0401034010 | Region IV-A (CALABARZON) | Batangas | Tuy | Malibu | 13.9962 | 120.7067 | R | 1458 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.53 | Terrestrial Optical Fiber Drop | 3.66 | 2.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1109 | 2 | 109 | 1109 | 0603043036 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Gen. Martin T. Delgado | 10.8321 | 122.5324 | R | 1933 | 508 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0073 | PTCI/MIDC | 10.8367 | 122.5265 | 0.82 | Terrestrial Optical Fiber Drop | 0.58 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1110 | 2 | 110 | 1110 | 0702211001 | Region VII (Central Visayas) | Cebu | City of Bogo | Cogon | 11.0435 | 124.0037 | U | 2857 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070035 | FTAP BTS | 11.041 | 124.0001 | 0.48 | Terrestrial Optical Fiber Drop | 0.58 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1111 | 2 | 111 | 1111 | 1004308048 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 23 | 8.8225 | 125.1006 | R | 3323 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.36 | Terrestrial Optical Fiber Drop | 0.58 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1112 | 2 | 112 | 1112 | 0604528042 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Zone 3 | 10.7437 | 122.9634 | U | 6901 | 1865 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060161 | FTAP BTS | 10.7427 | 122.9638 | 0.12 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1113 | 2 | 113 | 1113 | 1381100132 | National Capital Region (NCR) | Metro Manila (NCR) | Pasay City | Barangay 132 | 14.548 | 121.0063 | U | 3967 | 1309 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03189 | Edgepoint | 14.5499 | 121.0084 | 0.31 | Terrestrial Optical Fiber Drop | 0.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1114 | 2 | 114 | 1114 | 0304911062 | Region III (Central Luzon) | Nueva Ecija | Guimba | Saranay District | 15.6592 | 120.772 | U | 2824 | 806 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01413-B07 | PTCI/MIDC | 15.6577 | 120.7705 | 0.23 | Terrestrial Optical Fiber Drop | 0.58 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1115 | 2 | 115 | 1115 | 0500517041 | Region V (Bicol Region) | Albay | City of Tabaco | San Roque | 13.3555 | 123.7359 | U | 5362 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ALB_0001 | LDIC | 13.3557 | 123.7364 | 0.05 | Terrestrial Optical Fiber Drop | 0.58 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1116 | 2 | 116 | 1116 | 0500517019 | Region V (Bicol Region) | Albay | City of Tabaco | Fatima | 13.3492 | 123.7353 | R | 4365 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050132 | FTAP Globe | 13.3504 | 123.734 | 0.19 | Terrestrial Optical Fiber Drop | 0.58 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1117 | 2 | 117 | 1117 | 0306910001 | Region III (Central Luzon) | Tarlac | Paniqui | Abogado | 15.6708 | 120.5917 | R | 4810 | 1233 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 1.14 | Terrestrial Optical Fiber Drop | 0.58 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1118 | 2 | 118 | 1118 | 0401003008 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 3 | 13.9378 | 120.7325 | R | 1519 | 421 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 0.42 | Terrestrial Optical Fiber Drop | 0.79 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1119 | 2 | 119 | 1119 | 0702227008 | Region VII (Central Visayas) | Cebu | Liloan | Poblacion | 10.4023 | 123.9978 | U | 17033 | 4482 | 1345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0227 | PTCI/MIDC | 10.4015 | 123.9905 | 0.81 | Terrestrial Optical Fiber Drop | 0.59 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1120 | 2 | 120 | 1120 | 0301419026 | Region III (Central Luzon) | Bulacan | San Ildefonso | Poblacion | 15.0792 | 120.944 | U | 5123 | 1463 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1619 | FTAP Smart | 15.0772 | 120.9428 | 0.26 | Terrestrial Optical Fiber Drop | 0.59 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1121 | 2 | 121 | 1121 | 0803715020 | Region VIII (Eastern Visayas) | Leyte | Carigara | Jugaban | 11.2991 | 124.6947 | R | 1893 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0018 | PTCI/MIDC | 11.3015 | 124.6958 | 0.29 | Terrestrial Optical Fiber Drop | 0.58 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1122 | 2 | 122 | 1122 | 1705319008 | MIMAROPA Region | Palawan | San Vicente | Poblacion | 10.5365 | 119.2823 | U | 7496 | 1922 | 577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02441-C09 | PTCI/MIDC | 10.5366 | 119.2409 | 4.52 | Terrestrial Optical Fiber Drop | 0.59 | 8.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1123 | 2 | 123 | 1123 | 0401005082 | Region IV-A (CALABARZON) | Batangas | Batangas City | Sampaga | 13.7549 | 121.1037 | R | 4590 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03402-C08 | PTCI/MIDC | 13.7631 | 121.1069 | 0.97 | Terrestrial Optical Fiber Drop | 0.59 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1124 | 2 | 124 | 1124 | 0907322054 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Santa Maria | 7.8361 | 123.4388 | U | 4770 | 1223 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 1.04 | Terrestrial Optical Fiber Drop | 0.59 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1125 | 2 | 125 | 1125 | 0402114024 | Region IV-A (CALABARZON) | Cavite | Mendez | Palocpoc II | 14.128 | 120.879 | R | 1290 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040302 | FTAP Globe | 14.1248 | 120.8631 | 1.11 | Terrestrial Optical Fiber Drop | 0.23 | 4.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1126 | 2 | 126 | 1126 | 0300809013 | Region III (Central Luzon) | Bataan | Orani | Pantalan Bago | 14.803 | 120.5417 | R | 2370 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030603 | FTAP Globe | 14.8016 | 120.536 | 0.64 | Terrestrial Optical Fiber Drop | 0.59 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1127 | 2 | 127 | 1127 | 0306903017 | Region III (Central Luzon) | Tarlac | Camiling | Cacamilingan Norte | 15.6876 | 120.4204 | R | 2597 | 665 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030330 | FTAP Globe | 15.6892 | 120.4213 | 0.21 | Terrestrial Optical Fiber Drop | 0.59 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1128 | 2 | 128 | 1128 | 0105517004 | Region I (Ilocos Region) | Pangasinan | Calasiao | Bued | 16.0175 | 120.3831 | U | 5943 | 1650 | 495 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02246-B07 | PTCI/MIDC | 16.0148 | 120.3817 | 0.33 | Terrestrial Optical Fiber Drop | 0.59 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1129 | 2 | 129 | 1129 | 0403420008 | Region IV-A (CALABARZON) | Laguna | Pakil | Kabulusan | 14.3682 | 121.3996 | R | 4746 | 1438 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02564-A04 | PTCI/MIDC | 14.3471 | 121.3751 | 3.53 | Terrestrial Optical Fiber Drop | 0.59 | 7.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1130 | 2 | 130 | 1130 | 0603018013 | Region VI (Western Visayas) | Iloilo | Dumangas | Cali | 10.8311 | 122.7112 | R | 2035 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 1.46 | Terrestrial Optical Fiber Drop | 0.59 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1131 | 2 | 131 | 1131 | 1001319008 | Region X (Northern Mindanao) | Bukidnon | Sumilao | San Vicente | 8.3679 | 124.9779 | U | 3693 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0063 | PTCI/MIDC | 8.3585 | 124.979 | 1.06 | Terrestrial Optical Fiber Drop | 0.59 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1132 | 2 | 132 | 1132 | 0403403004 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Canlalay | 14.3425 | 121.072 | U | 22311 | 6760 | 2028 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S2016 | FTAP Smart | 14.3406 | 121.0722 | 0.22 | Terrestrial Optical Fiber Drop | 0.59 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1133 | 2 | 133 | 1133 | 0501709003 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Francisco | 13.6164 | 123.1704 | R | 872 | 207 | 62 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.52 | Terrestrial Optical Fiber Drop | 0.43 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1134 | 2 | 134 | 1134 | 0500510003 | Region V (Bicol Region) | Albay | Malinao | Balading | 13.3882 | 123.7091 | U | 3127 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050126 | FTAP Globe | 13.3795 | 123.7173 | 1.31 | Terrestrial Optical Fiber Drop | 0.59 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1135 | 2 | 135 | 1135 | 0506214010 | Region V (Bicol Region) | Sorsogon | Prieto Diaz | Maningcay De Oro | 13.0402 | 124.1895 | R | 1295 | 323 | 97 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050197 | FTAP Globe | 13.0399 | 124.192 | 0.27 | Terrestrial Optical Fiber Drop | 0.59 | 14.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1136 | 2 | 136 | 1136 | 0201505038 | Region II (Cagayan Valley) | Cagayan | Aparri | San Antonio | 18.3592 | 121.6407 | U | 4084 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0026 | LDIC | 121.6392 | 18.3577 | 0.23 | Terrestrial Optical Fiber Drop | 0.59 | 10.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1137 | 2 | 137 | 1137 | 1004313008 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Poblacion | 8.8105 | 124.7899 | R | 4238 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.47 | Terrestrial Optical Fiber Drop | 0.6 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1138 | 2 | 138 | 1138 | 0600613005 | Region VI (Western Visayas) | Antique | San Jose | Barangay 3 | 10.7519 | 121.9416 | R | 3574 | 916 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170137 | FTAP Globe | 12.3508 | 121.0661 | 0.53 | Terrestrial Optical Fiber Drop | 1.22 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1139 | 2 | 139 | 1139 | 0402106080 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | H-2 | 14.318 | 120.9522 | U | 9797 | 2881 | 864 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01898-C08 | PTCI/MIDC | 14.3775 | 120.9413 | 0.19 | Terrestrial Optical Fiber Drop | 1.58 | 1.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1140 | 2 | 140 | 1140 | 1430300002 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Asin Road | 16.4042 | 120.5669 | U | 13901 | 3658 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0006 | LDIC | 16.4046 | 120.5669 | 0.05 | Terrestrial Optical Fiber Drop | 0.6 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1141 | 2 | 141 | 1141 | 0603032023 | Region VI (Western Visayas) | Iloilo | New Lucena | Wari-wari | 10.8837 | 122.6 | R | 1050 | 276 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 0.97 | Terrestrial Optical Fiber Drop | 0.6 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1142 | 2 | 142 | 1142 | 0307109003 | Region III (Central Luzon) | Zambales | San Antonio | Burgos | 14.9463 | 120.0943 | U | 6185 | 1627 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.69 | Terrestrial Optical Fiber Drop | 0.59 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1143 | 2 | 143 | 1143 | 0803738081 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Antonio | 10.9643 | 124.6447 | R | 1977 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0042 | PTCI/MIDC | 10.9609 | 124.652 | 0.88 | Terrestrial Optical Fiber Drop | 0.59 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1144 | 2 | 144 | 1144 | 0506208029 | Region V (Bicol Region) | Sorsogon | Gubat | Paradijon | 12.9168 | 124.1202 | R | 1381 | 345 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050212 | FTAP Globe | 12.9215 | 124.1207 | 0.53 | Terrestrial Optical Fiber Drop | 0.59 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1145 | 2 | 145 | 1145 | 0102809013 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Guerrero | 18.0948 | 120.7057 | R | 1519 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 1.03 | Terrestrial Optical Fiber Drop | 0.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1146 | 2 | 146 | 1146 | 0402106017 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone II | 14.3182 | 120.9526 | R | 1765 | 519 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.95 | Terrestrial Optical Fiber Drop | 1.55 | 1.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1147 | 2 | 147 | 1147 | 0506208028 | Region V (Bicol Region) | Sorsogon | Gubat | Panganiban | 12.9139 | 124.1196 | R | 2167 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03159-C10 | PTCI/MIDC | 12.912 | 124.1171 | 0.35 | Terrestrial Optical Fiber Drop | 0.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1148 | 2 | 148 | 1148 | 1004302020 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Barangay 1 | 8.7449 | 124.7801 | R | 1373 | 352 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0002 | PTCI/MIDC | 8.7436 | 124.7779 | 0.28 | Terrestrial Optical Fiber Drop | 0.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1149 | 2 | 149 | 1149 | 0702224024 | Region VII (Central Visayas) | Cebu | Dumanjug | Liong | 10.052 | 123.4328 | R | 2755 | 725 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0084 | PTCI/MIDC | 10.0456 | 123.429 | 0.83 | Terrestrial Optical Fiber Drop | 0.6 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1150 | 2 | 150 | 1150 | 0307105010 | Region III (Central Luzon) | Zambales | Iba | Lipay-Dingin-Panibuatan | 15.3217 | 119.977 | R | 3572 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.66 | Terrestrial Optical Fiber Drop | 0.6 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1151 | 2 | 151 | 1151 | 0500508026 | Region V (Bicol Region) | Albay | City of Ligao | Herrera | 13.2628 | 123.5839 | R | 2721 | 663 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.83 | Terrestrial Optical Fiber Drop | 0.6 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1152 | 2 | 152 | 1152 | 0501728013 | Region V (Bicol Region) | Camarines Sur | Pili | Palestina | 13.6075 | 123.2492 | U | 6010 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCSG0006 | PTCI/MIDC | 13.6014 | 123.2473 | 0.71 | Terrestrial Optical Fiber Drop | 0.6 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1153 | 2 | 153 | 1153 | 0702221016 | Region VII (Central Visayas) | Cebu | Daanbantayan | Poblacion | 11.2505 | 124.0005 | U | 8592 | 2261 | 678 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0072 | PTCI/MIDC | 11.2494 | 124.0028 | 0.28 | Terrestrial Optical Fiber Drop | 0.6 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1154 | 2 | 154 | 1154 | 0506209021 | Region V (Bicol Region) | Sorsogon | Irosin | San Agustin | 12.7027 | 124.0411 | R | 2380 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 0.5 | Terrestrial Optical Fiber Drop | 0.6 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1155 | 2 | 155 | 1155 | 0504121034 | Region V (Bicol Region) | Masbate | Uson | Sawang | 12.2322 | 123.7556 | R | 1556 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMSG0001 | PTCI/MIDC | 12.243 | 123.7468 | 1.54 | Terrestrial Optical Fiber Drop | 0.6 | 20.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1156 | 2 | 156 | 1156 | 0405802016 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | San Luis | 14.6201 | 121.1903 | U | 63518 | 17643 | 5293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00829-A04 | PTCI/MIDC | 14.6207 | 121.1902 | 0.06 | Terrestrial Optical Fiber Drop | 0.6 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1157 | 2 | 157 | 1157 | 0305405009 | Region III (Central Luzon) | Pampanga | Candaba | Dalayap | 15.0153 | 120.8659 | R | 2631 | 657 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030502 | FTAP Globe | 15.0168 | 120.8697 | 0.44 | Terrestrial Optical Fiber Drop | 0.6 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1158 | 2 | 158 | 1158 | 0102818007 | Region I (Ilocos Region) | Ilocos Norte | Piddig | Cabaroan | 18.1682 | 120.7194 | R | 975 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 3987 | FTAP Smart | 18.1615 | 120.7123 | 1.06 | Terrestrial Optical Fiber Drop | 0.6 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1159 | 2 | 159 | 1159 | 0405805018 | Region IV-A (CALABARZON) | Rizal | Cainta | Santa Rosa | 14.5798 | 121.1136 | R | 1550 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01758 | Edgepoint | 14.5824 | 121.1199 | 0.2 | Terrestrial Optical Fiber Drop | 1.15 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1160 | 2 | 160 | 1160 | 0304926030 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 1st | 15.7991 | 120.991 | U | 7950 | 2271 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01436-B07 | PTCI/MIDC | 15.8005 | 120.9908 | 0.16 | Terrestrial Optical Fiber Drop | 0.6 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1161 | 2 | 161 | 1161 | 0403413005 | Region IV-A (CALABARZON) | Laguna | Lumban | Concepcion | 14.299 | 121.4566 | R | 4711 | 1427 | 428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.44 | Terrestrial Optical Fiber Drop | 0.6 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1162 | 2 | 162 | 1162 | 1108204026 | Region XI (Davao Region) | Davao de Oro | Maco | Poblacion | 7.3612 | 125.859 | U | 8701 | 2351 | 705 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 0.67 | Terrestrial Optical Fiber Drop | 0.61 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1163 | 2 | 163 | 1163 | 0403425013 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Riverside | 14.3416 | 121.0436 | R | 3319 | 1005 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040146 | FTAP Globe | 14.3562 | 121.0336 | 0.25 | Terrestrial Optical Fiber Drop | 0.48 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1164 | 2 | 164 | 1164 | 1430300069 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Quirino Hill, Middle | 16.4302 | 120.5906 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1852 | FTAP Smart | 16.4305 | 120.5909 | 0.05 | Terrestrial Optical Fiber Drop | 0.61 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1165 | 2 | 165 | 1165 | 0504112001 | Region V (Bicol Region) | Masbate | Milagros | Bacolod | 12.2245 | 123.5084 | R | 3357 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03140-C10 | PTCI/MIDC | 12.2309 | 123.5058 | 0.77 | Terrestrial Optical Fiber Drop | 0.61 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1166 | 2 | 166 | 1166 | 0402114012 | Region IV-A (CALABARZON) | Cavite | Mendez | Poblacion VI | 14.1348 | 120.9044 | R | 1337 | 393 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02216-C08 | PTCI/MIDC | 14.1324 | 120.9008 | 0.48 | Terrestrial Optical Fiber Drop | 0.61 | 4.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1167 | 2 | 167 | 1167 | 0103313022 | Region I (Ilocos Region) | La Union | Rosario | Poblacion East | 16.2293 | 120.4882 | U | 2497 | 674 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01398-B05 | PTCI/MIDC | 16.2273 | 120.4884 | 0.23 | Terrestrial Optical Fiber Drop | 0.61 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1168 | 2 | 168 | 1168 | 0305405017 | Region III (Central Luzon) | Pampanga | Candaba | Mangga | 15.016 | 120.8768 | U | 4283 | 1070 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030502 | FTAP Globe | 15.0168 | 120.8697 | 0.77 | Terrestrial Optical Fiber Drop | 0.61 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1169 | 2 | 169 | 1169 | 1401106001 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Ampucao | 16.3253 | 120.6547 | U | 11221 | 3206 | 962 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BEN-00357 | Edgepoint | 16.3305 | 120.6474 | 0.98 | Terrestrial Optical Fiber Drop | 0.61 | 10.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1170 | 2 | 170 | 1170 | 0401012026 | Region IV-A (CALABARZON) | Batangas | Lemery | Mayasang | 14.0162 | 120.8632 | R | 2831 | 786 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1361 | FTAP Smart | 14.0201 | 120.8589 | 0.63 | Terrestrial Optical Fiber Drop | 0.61 | 4.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1171 | 2 | 171 | 1171 | 0402120033 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya VII | 14.3831 | 120.8338 | R | 2698 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02192-C08 | PTCI/MIDC | 14.3879 | 120.8622 | 0.64 | Terrestrial Optical Fiber Drop | 1.87 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1172 | 2 | 172 | 1172 | 0630200023 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 27 | 10.666 | 122.9521 | R | 1800 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOR0022 | PTCI/MIDC | 10.6747 | 122.9555 | 0.44 | Terrestrial Optical Fiber Drop | 0.1 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1173 | 2 | 173 | 1173 | 0403405005 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bubuyan | 14.1719 | 121.104 | R | 3500 | 1060 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02067-C08 | PTCI/MIDC | 14.1719 | 121.1028 | 0.13 | Terrestrial Optical Fiber Drop | 0.61 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1174 | 2 | 174 | 1174 | 1381300094 | National Capital Region (NCR) | Metro Manila (NCR) | Quezon City | Salvacion | 14.6588 | 121.0467 | U | 6861 | 1844 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170066 | FTAP Globe | 13.3624 | 121.1001 | 0.56 | Terrestrial Optical Fiber Drop | 0.48 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1175 | 2 | 175 | 1175 | 1705320005 | MIMAROPA Region | Palawan | Taytay | Bato | 10.7121 | 119.4853 | R | 4263 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170219 | FTAP Globe | 10.6697 | 119.4514 | 6 | Terrestrial Optical Fiber Drop | 0.61 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1176 | 2 | 176 | 1176 | 1381200018 | National Capital Region (NCR) | Metro Manila (NCR) | City of Pasig | Sagad | 14.5661 | 121.0796 | U | 6357 | 1826 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000381 | FTAP Globe | 14.5672 | 121.0801 | 0.13 | Terrestrial Optical Fiber Drop | 0.62 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1177 | 2 | 177 | 1177 | 0500504043 | Region V (Bicol Region) | Albay | Guinobatan | San Francisco | 13.1892 | 123.6095 | U | 3199 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 1.11 | Terrestrial Optical Fiber Drop | 0.62 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1178 | 2 | 178 | 1178 | 0403425010 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Nueva | 14.3417 | 121.044 | U | 4698 | 1423 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0001 | PTCI/MIDC | 14.3376 | 121.0391 | 0.17 | Terrestrial Optical Fiber Drop | 0.51 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1179 | 2 | 179 | 1179 | 0631000052 | Region VI (Western Visayas) | Iloilo | City of Iloilo | East Baluarte | 10.6925 | 122.5481 | R | 1863 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0041 | PTCI/MIDC | 10.6914 | 122.5427 | 0.6 | Terrestrial Optical Fiber Drop | 0.62 | 2.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1180 | 2 | 180 | 1180 | 0403424027 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay VI-D | 14.0776 | 121.321 | R | 1678 | 508 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.37 | Terrestrial Optical Fiber Drop | 0.62 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1181 | 2 | 181 | 1181 | 0102803012 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Gabut Sur | 17.9653 | 120.4745 | R | 908 | 245 | 74 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01223-B05 | PTCI/MIDC | 17.9199 | 120.4864 | 0.59 | Terrestrial Optical Fiber Drop | 4.48 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1182 | 2 | 182 | 1182 | 0907302042 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Aurora | Poblacion | 7.9471 | 123.5854 | U | 5108 | 1344 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0001 | PTCI/MIDC | 7.9502 | 123.5859 | 0.35 | Terrestrial Optical Fiber Drop | 0.62 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1183 | 2 | 183 | 1183 | 0604532004 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Igmaya-an | 10.5582 | 123.1957 | R | 4474 | 1209 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0124 | PTCI/MIDC | 10.4742 | 123.1992 | 9.35 | Terrestrial Optical Fiber Drop | 0.62 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1184 | 2 | 184 | 1184 | 0403418004 | Region IV-A (CALABARZON) | Laguna | Paete | Ibaba del Norte | 14.3639 | 121.4792 | R | 3407 | 1032 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.51 | Terrestrial Optical Fiber Drop | 0.62 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1185 | 2 | 185 | 1185 | 0105530032 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Talogtog | 16.1225 | 120.5223 | R | 2264 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00407 | Edgepoint | 16.11 | 120.5398 | 0.21 | Terrestrial Optical Fiber Drop | 2.31 | 1.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1186 | 2 | 186 | 1186 | 0603039006 | Region VI (Western Visayas) | Iloilo | San Enrique | Cabugao Viejo | 11.0754 | 122.6605 | R | 1392 | 366 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0062 | PTCI/MIDC | 11.0735 | 122.6579 | 0.35 | Terrestrial Optical Fiber Drop | 0.62 | 3.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1187 | 2 | 187 | 1187 | 0604530015 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Poblacion | 10.4605 | 122.8245 | U | 3790 | 1024 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 0.96 | Terrestrial Optical Fiber Drop | 0.63 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1188 | 2 | 188 | 1188 | 1001312001 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Aglayan | 8.0547 | 125.1353 | U | 9192 | 2418 | 725 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100192 | FTAP Globe | 8.0534 | 125.1347 | 0.15 | Terrestrial Optical Fiber Drop | 0.63 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1189 | 2 | 189 | 1189 | 0701205013 | Region VII (Central Visayas) | Bohol | Baclayon | San Roque | 9.6251 | 123.9216 | R | 1760 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 4.81 | Terrestrial Optical Fiber Drop | 0.96 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1190 | 2 | 190 | 1190 | 0401028003 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Barangay III | 14.1054 | 121.1425 | R | 2240 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 0.46 | Terrestrial Optical Fiber Drop | 2.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1191 | 2 | 191 | 1191 | 1381500014 | National Capital Region (NCR) | Metro Manila (NCR) | City of Taguig | Tuktukan | 14.5117 | 121.0587 | U | 12414 | 3301 | 990 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NCR-03000 | Edgepoint | 121.07 | 14.5109 | 0.23 | Terrestrial Optical Fiber Drop | 0.8 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1192 | 2 | 192 | 1192 | 1600203024 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Poblacion 12 | 9.1176 | 125.54 | R | 2577 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 0.73 | Terrestrial Optical Fiber Drop | 0.62 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1193 | 2 | 193 | 1193 | 0405802017 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Santa Cruz | 14.6153 | 121.1708 | U | 62537 | 17371 | 5211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0175 | PTCI/MIDC | 14.6161 | 121.1691 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1194 | 2 | 194 | 1194 | 0403420007 | Region IV-A (CALABARZON) | Laguna | Pakil | Gonzales | 14.3847 | 121.4769 | R | 2865 | 868 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040132 | FTAP Globe | 14.3864 | 121.4768 | 0.2 | Terrestrial Optical Fiber Drop | 0.63 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1195 | 2 | 195 | 1195 | 0403417053 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Yukos | 14.1321 | 121.413 | U | 5953 | 1803 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02088-C08 | PTCI/MIDC | 14.1299 | 121.4147 | 0.3 | Terrestrial Optical Fiber Drop | 0.63 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1196 | 2 | 196 | 1196 | 0405805016 | Region IV-A (CALABARZON) | Rizal | Cainta | San Juan | 14.5398 | 121.1109 | U | 99685 | 27690 | 8307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03263-A04 | PTCI/MIDC | 14.5411 | 121.112 | 0.18 | Terrestrial Optical Fiber Drop | 0.63 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1197 | 2 | 197 | 1197 | 0431200007 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 4 | 13.9366 | 121.6161 | U | 2925 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.45 | Terrestrial Optical Fiber Drop | 0.63 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1198 | 2 | 198 | 1198 | 0403403023 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Domingo | 14.336 | 121.0809 | U | 6751 | 2045 | 614 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02537-C08 | PTCI/MIDC | 14.3337 | 121.0825 | 0.31 | Terrestrial Optical Fiber Drop | 0.63 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1199 | 2 | 199 | 1199 | 0105501014 | Region I (Ilocos Region) | Pangasinan | Agno | Poblacion East | 16.1183 | 119.7967 | R | 1543 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-02227 | Edgepoint | 16.1209 | 119.8108 | 1.67 | Terrestrial Optical Fiber Drop | 1.12 | 9.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1200 | 2 | 200 | 1200 | 0401005014 | Region IV-A (CALABARZON) | Batangas | Batangas City | Calicanto | 13.7669 | 121.0534 | U | 11089 | 3080 | 924 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6911 | FTAP Smart | 13.7698 | 121.0545 | 0.35 | Terrestrial Optical Fiber Drop | 0.63 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1201 | 2 | 201 | 1201 | 0203115012 | Region II (Cagayan Valley) | Isabela | Jones | Dibuluan | 16.5195 | 121.7611 | R | 2556 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01292-B06 | PTCI/MIDC | 16.5232 | 121.7634 | 0.48 | Terrestrial Optical Fiber Drop | 0.63 | 15.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1202 | 2 | 202 | 1202 | 0403430009 | Region IV-A (CALABARZON) | Laguna | Victoria | San Francisco | 14.2119 | 121.3444 | U | 7217 | 2186 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02113-C08 | PTCI/MIDC | 14.2028 | 121.346 | 1.02 | Terrestrial Optical Fiber Drop | 0.63 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1203 | 2 | 203 | 1203 | 0305412018 | Region III (Central Luzon) | Pampanga | Masantol | San Isidro Matua | 14.8913 | 120.7009 | R | 3735 | 933 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.34 | Terrestrial Optical Fiber Drop | 0.63 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1204 | 2 | 204 | 1204 | 1230800009 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Katangawan | 6.1733 | 125.221 | U | 17971 | 4607 | 1382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0022 | PTCI/MIDC | 6.1749 | 125.2217 | 0.19 | Terrestrial Optical Fiber Drop | 0.63 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1205 | 2 | 205 | 1205 | 0405804040 | Region IV-A (CALABARZON) | Rizal | Binangonan | Pag-Asa | 14.527 | 121.1605 | U | 18644 | 5178 | 1553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 450 | FTAP Smart | 14.5268 | 121.1582 | 0.25 | Terrestrial Optical Fiber Drop | 0.63 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1206 | 2 | 206 | 1206 | 0803748041 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Canramos | 11.1062 | 125.0142 | R | 3407 | 896 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0083 | PTCI/MIDC | 11.1054 | 125.0132 | 0.14 | Terrestrial Optical Fiber Drop | 0.63 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1207 | 2 | 207 | 1207 | 0405808005 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Manggahan | 14.7235 | 121.143 | U | 17089 | 4746 | 1424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-RIZ-01264 | Edgepoint | 14.7303 | 121.1441 | 0.77 | Terrestrial Optical Fiber Drop | 0.63 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1208 | 2 | 208 | 1208 | 0301407009 | Region III (Central Luzon) | Bulacan | Calumpit | Corazon | 14.912 | 120.7683 | U | 2273 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1599 | FTAP Smart | 14.9149 | 120.7688 | 0.32 | Terrestrial Optical Fiber Drop | 0.63 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1209 | 2 | 209 | 1209 | 1705205048 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Salong | 13.4203 | 121.1902 | U | 3831 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 1.24 | Terrestrial Optical Fiber Drop | 0.63 | 5.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1210 | 2 | 210 | 1210 | 0506205001 | Region V (Bicol Region) | Sorsogon | Casiguran | Adovis | 12.8687 | 124.0097 | R | 808 | 202 | 61 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 0.72 | Terrestrial Optical Fiber Drop | 0.63 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1211 | 2 | 211 | 1211 | 0201525012 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Villa | 18.2476 | 121.917 | R | 2279 | 584 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0073 | LDIC | 121.911 | 18.2439 | 0.76 | Terrestrial Optical Fiber Drop | 0.63 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1212 | 2 | 212 | 1212 | 0403419010 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Maulawin | 14.2697 | 121.4546 | R | 4627 | 1402 | 421 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02115-C08 | PTCI/MIDC | 14.2703 | 121.4567 | 0.24 | Terrestrial Optical Fiber Drop | 0.63 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1213 | 2 | 213 | 1213 | 0603005006 | Region VI (Western Visayas) | Iloilo | Balasan | Camambugan | 11.4731 | 123.0842 | R | 2318 | 610 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.75 | Terrestrial Optical Fiber Drop | 0.63 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1214 | 2 | 214 | 1214 | 0501708039 | Region V (Bicol Region) | Camarines Sur | Calabanga | San Roque | 13.7122 | 123.2108 | U | 6318 | 1504 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050061 | FTAP Globe | 13.7087 | 123.2167 | 0.75 | Terrestrial Optical Fiber Drop | 0.64 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1215 | 2 | 215 | 1215 | 0603014022 | Region VI (Western Visayas) | Iloilo | Carles | Granada | 11.6167 | 123.3433 | R | 3367 | 886 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060345 | FTAP Globe | 10.6647 | 123.0376 | 0.48 | Terrestrial Optical Fiber Drop | 29.48 | 30.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1216 | 2 | 216 | 1216 | 0403425026 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Pacita 1 | 14.3494 | 121.0476 | U | 24752 | 7500 | 2250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02019-C08 | PTCI/MIDC | 14.3488 | 121.0601 | 0.5 | Terrestrial Optical Fiber Drop | 0.97 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1217 | 2 | 217 | 1217 | 1403213008 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao | 17.4077 | 121.4451 | U | 20300 | 4720 | 1416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00001-B06 | PTCI/MIDC | 17.4073 | 121.4431 | 0.22 | Terrestrial Optical Fiber Drop | 0.64 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1218 | 2 | 218 | 1218 | 0401006041 | Region IV-A (CALABARZON) | Batangas | Bauan | Santa Maria | 13.7738 | 120.964 | U | 4923 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1336 | FTAP Smart | 13.7759 | 120.9646 | 0.71 | Terrestrial Optical Fiber Drop | 0.91 | 4.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1219 | 2 | 219 | 1219 | 0405648016 | Region IV-A (CALABARZON) | Quezon | Tiaong | Lumingon | 13.9607 | 121.3257 | U | 4592 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040409 | FTAP Globe | 13.9631 | 121.3238 | 0.34 | Terrestrial Optical Fiber Drop | 0.64 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1220 | 2 | 220 | 1220 | 1402701005 | Cordillera Administrative Region (CAR) | Ifugao | Banaue | Bocos | 16.9162 | 121.0632 | R | 2621 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02519-B05 | PTCI/MIDC | 16.9091 | 121.0603 | 0.85 | Terrestrial Optical Fiber Drop | 0.64 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1221 | 2 | 221 | 1221 | 0500517004 | Region V (Bicol Region) | Albay | City of Tabaco | Bantayan | 13.3376 | 123.6573 | R | 1637 | 399 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050138 | FTAP Globe | 13.3099 | 123.6425 | 3.47 | Terrestrial Optical Fiber Drop | 0.64 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1222 | 2 | 222 | 1222 | 0403402003 | Region IV-A (CALABARZON) | Laguna | Bay | Dila | 14.1809 | 121.2864 | U | 7412 | 2246 | 674 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.6 | Terrestrial Optical Fiber Drop | 0.64 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1223 | 2 | 223 | 1223 | 0403428016 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Pook | 14.3024 | 121.1096 | U | 61062 | 18503 | 5551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0006 | LDIC | 14.3036 | 121.1072 | 0.29 | Terrestrial Optical Fiber Drop | 0.64 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1224 | 2 | 224 | 1224 | 0402103058 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu VII | 14.4561 | 120.9551 | U | 3876 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 386 | FTAP Smart | 14.4378 | 121.0069 | 0.52 | Terrestrial Optical Fiber Drop | 0.4 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1225 | 2 | 225 | 1225 | 0401017013 | Region IV-A (CALABARZON) | Batangas | Malvar | San Fernando | 14.0261 | 121.1635 | U | 5844 | 1623 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.94 | Terrestrial Optical Fiber Drop | 0.64 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1226 | 2 | 226 | 1226 | 0307105008 | Region III (Central Luzon) | Zambales | Iba | Dirita-Baloguen | 15.3326 | 119.9794 | U | 3946 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02718 | Edgepoint | 15.3268 | 119.9802 | 0.65 | Terrestrial Optical Fiber Drop | 0.64 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1227 | 2 | 227 | 1227 | 0402104010 | Region IV-A (CALABARZON) | Cavite | Carmona | Maduya | 14.3169 | 121.0608 | U | 11154 | 3280 | 984 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02248-C08 | PTCI/MIDC | 14.3141 | 121.0588 | 0.38 | Terrestrial Optical Fiber Drop | 0.64 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1228 | 2 | 228 | 1228 | 0300805013 | Region III (Central Luzon) | Bataan | Hermosa | Mambog - Mandama | 14.8335 | 120.4938 | R | 3864 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1510 | FTAP Smart | 14.8334 | 120.4947 | 0.1 | Terrestrial Optical Fiber Drop | 0.64 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1229 | 2 | 229 | 1229 | 0304929026 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Pulong Buli | 15.5942 | 120.8731 | R | 2414 | 689 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01429-B07 | PTCI/MIDC | 15.5935 | 120.8781 | 0.55 | Terrestrial Optical Fiber Drop | 0.64 | 4.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1230 | 2 | 230 | 1230 | 0301423006 | Region III (Central Luzon) | Bulacan | Santa Maria | Catmon | 14.8287 | 121.0014 | U | 16660 | 4760 | 1428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01161 | Edgepoint | 14.8276 | 120.9962 | 0.57 | Terrestrial Optical Fiber Drop | 0.64 | 2.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1231 | 2 | 231 | 1231 | 0102820007 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Eugenio | 18.1531 | 120.5955 | R | 1037 | 280 | 84 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ILN_0001 | LDIC | 18.161 | 120.5894 | 0.48 | Terrestrial Optical Fiber Drop | 1.93 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1232 | 2 | 232 | 1232 | 0331400002 | Region III (Central Luzon) | Zambales | City of Olongapo | Banicain | 14.8286 | 120.2757 | U | 7696 | 2080 | 624 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.53 | Terrestrial Optical Fiber Drop | 0.65 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1233 | 2 | 233 | 1233 | 0402103056 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu V | 14.4562 | 120.9548 | U | 5937 | 1746 | 524 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040129 | FTAP Globe | 14.3884 | 120.9771 | 0.32 | Terrestrial Optical Fiber Drop | 0.43 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1234 | 2 | 234 | 1234 | 0405646030 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Rizal | 13.9602 | 122.5435 | R | 3375 | 888 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.73 | Terrestrial Optical Fiber Drop | 0.65 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1235 | 2 | 235 | 1235 | 0403421006 | Region IV-A (CALABARZON) | Laguna | Pangil | Natividad | 14.3995 | 121.4712 | R | 2814 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.64 | Terrestrial Optical Fiber Drop | 1.15 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1236 | 2 | 236 | 1236 | 0501716010 | Region V (Bicol Region) | Camarines Sur | City of Iriga | Perpetual Help | 13.4264 | 123.4148 | R | 4380 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-03180 | Edgepoint | 13.428 | 123.4178 | 0.37 | Terrestrial Optical Fiber Drop | 0.65 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1237 | 2 | 237 | 1237 | 1204702032 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Poblacion | 7.2056 | 124.7977 | U | 10414 | 2740 | 822 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0015 | PTCI/MIDC | 8.9888 | 125.2896 | 0.51 | Terrestrial Optical Fiber Drop | 0.34 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1238 | 2 | 238 | 1238 | 0803748046 | Region VIII (Eastern Visayas) | Leyte | Tanauan | San Roque | 11.111 | 125.0213 | R | 3634 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080011 | FTAP BTS | 11.1165 | 125.0165 | 0.81 | Terrestrial Optical Fiber Drop | 0.65 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1239 | 2 | 239 | 1239 | 1401113013 | Cordillera Administrative Region (CAR) | Benguet | Tuba | Taloy Sur | 16.3837 | 120.5304 | R | 3618 | 1033 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00916-B05 | PTCI/MIDC | 16.3864 | 120.5261 | 0.55 | Terrestrial Optical Fiber Drop | 0.65 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1240 | 2 | 240 | 1240 | 0702250014 | Region VII (Central Visayas) | Cebu | City of Talisay | San Isidro | 10.2564 | 123.839 | U | 18044 | 4748 | 1424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 0.41 | Terrestrial Optical Fiber Drop | 0.15 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1241 | 2 | 241 | 1241 | 0601902019 | Region VI (Western Visayas) | Capiz | Dao | Poblacion Ilaya | 11.3906 | 122.6817 | R | 1995 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 3.18 | Terrestrial Optical Fiber Drop | 0.65 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1242 | 2 | 242 | 1242 | 0103306033 | Region I (Ilocos Region) | La Union | Bangar | San Blas | 16.888 | 120.4221 | R | 1395 | 377 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.32 | Terrestrial Optical Fiber Drop | 0.65 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1243 | 2 | 243 | 1243 | 0304902008 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Curva | 15.6187 | 121.1489 | R | 4163 | 1189 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 1.01 | Terrestrial Optical Fiber Drop | 0.65 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1244 | 2 | 244 | 1244 | 0307108005 | Region III (Central Luzon) | Zambales | Palauig | Garreta | 15.4366 | 119.9019 | R | 1532 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00729 | Edgepoint | 15.4369 | 119.9033 | 0.15 | Terrestrial Optical Fiber Drop | 0.65 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1245 | 2 | 245 | 1245 | 0402108029 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Tejero | 14.3922 | 120.8643 | U | 8578 | 2522 | 757 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040128 | FTAP Globe | 14.3935 | 120.8639 | 0.15 | Terrestrial Optical Fiber Drop | 0.65 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1246 | 2 | 246 | 1246 | 0205005008 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | La Torre North | 16.4877 | 121.1502 | R | 2504 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0017 | PTCI/MIDC | 16.4767 | 121.1461 | 0.84 | Terrestrial Optical Fiber Drop | 0.34 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1247 | 2 | 247 | 1247 | 0105539023 | Region I (Ilocos Region) | Pangasinan | Santa Maria | San Vicente | 15.9873 | 120.7081 | R | 4140 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01765-B07 | PTCI/MIDC | 15.9765 | 120.6972 | 1.67 | Terrestrial Optical Fiber Drop | 0.65 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1248 | 2 | 248 | 1248 | 0506203038 | Region V (Bicol Region) | Sorsogon | Bulan | Obrero | 12.6693 | 123.8788 | R | 2985 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.27 | Terrestrial Optical Fiber Drop | 0.65 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1249 | 2 | 249 | 1249 | 0603017049 | Region VI (Western Visayas) | Iloilo | Dueñas | Poblacion B | 11.0701 | 122.6164 | R | 797 | 209 | 63 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0018 | PTCI/MIDC | 11.065 | 122.622 | 0.82 | Terrestrial Optical Fiber Drop | 0.65 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1250 | 2 | 250 | 1250 | 0402105002 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 10 | 14.4706 | 120.8892 | R | 1380 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040084 | FTAP Globe | 14.4812 | 120.8948 | 0.5 | Terrestrial Optical Fiber Drop | 0.5 | 3.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1251 | 2 | 251 | 1251 | 0402122012 | Region IV-A (CALABARZON) | Cavite | City of Trece Martires | Gregorio | 14.2877 | 120.8715 | U | 5438 | 1599 | 480 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4408 | FTAP Smart | 14.2836 | 120.8648 | 0.85 | Terrestrial Optical Fiber Drop | 0.65 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1252 | 2 | 252 | 1252 | 0402107011 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Tabora | 14.1886 | 120.7921 | R | 2133 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.8 | Terrestrial Optical Fiber Drop | 0.65 | 3.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1253 | 2 | 253 | 1253 | 0603018010 | Region VI (Western Visayas) | Iloilo | Dumangas | Bolilao | 10.8297 | 122.7143 | R | 3144 | 827 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.38 | Terrestrial Optical Fiber Drop | 0.65 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1254 | 2 | 254 | 1254 | 0501702008 | Region V (Bicol Region) | Camarines Sur | Balatan | Duran | 13.3101 | 123.2368 | U | 5460 | 1300 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050137 | FTAP Globe | 13.3165 | 123.2349 | 0.74 | Terrestrial Optical Fiber Drop | 0.66 | 14.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1255 | 2 | 255 | 1255 | 0304930046 | Region III (Central Luzon) | Nueva Ecija | Talavera | Poblacion Sur | 15.5763 | 120.9178 | U | 3979 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0023 | PTCI/MIDC | 15.5775 | 120.9214 | 0.41 | Terrestrial Optical Fiber Drop | 0.66 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1256 | 2 | 256 | 1256 | 0731300018 | Region VII (Central Visayas) | Cebu | City of Mandaue | Mantuyong | 10.3469 | 123.9409 | U | 5493 | 1569 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0113 | PTCI/MIDC | 10.3319 | 123.936 | 0.75 | Terrestrial Optical Fiber Drop | 0.9 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1257 | 2 | 257 | 1257 | 0306903018 | Region III (Central Luzon) | Tarlac | Camiling | Cacamilingan Sur | 15.6876 | 120.4202 | R | 2373 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.23 | Terrestrial Optical Fiber Drop | 0.57 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1258 | 2 | 258 | 1258 | 0500514033 | Region V (Bicol Region) | Albay | Polangui | Maynaga | 13.3391 | 123.52 | R | 1389 | 338 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050131 | FTAP Globe | 13.3511 | 123.5258 | 1.48 | Terrestrial Optical Fiber Drop | 0.66 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1259 | 2 | 259 | 1259 | 1705307012 | MIMAROPA Region | Palawan | Busuanga | Salvacion | 12.1328 | 119.9311 | U | 4052 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170200 | FTAP Globe | 12.129 | 119.9382 | 0.88 | Satellite LEO Backhaul (Starlink Business) | 0.65 | 125.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1260 | 2 | 260 | 1260 | 0205705003 | Region II (Cagayan Valley) | Quirino | Saguday | Magsaysay | 16.5383 | 121.5609 | R | 2636 | 675 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0005 | LDIC | 121.5628 | 16.5421 | 0.47 | Terrestrial Optical Fiber Drop | 0.66 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1261 | 2 | 261 | 1261 | 0201507009 | Region II (Cagayan Valley) | Cagayan | Ballesteros | Centro West | 18.4141 | 121.509 | R | 2104 | 539 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01193-B06 | PTCI/MIDC | 18.4117 | 121.5126 | 0.46 | Terrestrial Optical Fiber Drop | 0.66 | 7.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1262 | 2 | 262 | 1262 | 0405805014 | Region IV-A (CALABARZON) | Rizal | Cainta | San Andres | 14.5741 | 121.1106 | U | 115400 | 32055 | 9617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02575-A04 | PTCI/MIDC | 14.5718 | 121.1128 | 0.36 | Terrestrial Optical Fiber Drop | 0.66 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1263 | 2 | 263 | 1263 | 1731500067 | MIMAROPA Region | Palawan | City of Puerto Princesa | Tiniguiban | 9.7753 | 118.7379 | U | 13976 | 3777 | 1133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02443-C09 | PTCI/MIDC | 9.7787 | 118.7391 | 0.4 | Terrestrial Optical Fiber Drop | 0.66 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1264 | 2 | 264 | 1264 | 0403412014 | Region IV-A (CALABARZON) | Laguna | Luisiana | San Jose | 14.185 | 121.5152 | R | 1024 | 310 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02114-C08 | PTCI/MIDC | 14.1903 | 121.5048 | 0.97 | Terrestrial Optical Fiber Drop | 0.99 | 4.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1265 | 2 | 265 | 1265 | 1705309024 | MIMAROPA Region | Palawan | Coron | Tagumpay | 12.0086 | 120.2443 | U | 9745 | 2498 | 749 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170202 | FTAP Globe | 12.0797 | 120.196 | 9.49 | Satellite LEO Backhaul (Starlink Business) | 0.66 | 96.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1266 | 2 | 266 | 1266 | 0402106063 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc IV | 14.3132 | 120.9718 | U | 43875 | 12904 | 3871 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040179 | FTAP Globe | 14.3126 | 120.9715 | 0.08 | Terrestrial Optical Fiber Drop | 0.66 | 2.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1267 | 2 | 267 | 1267 | 1102315025 | Region XI (Davao Region) | Davao del Norte | City of Panabo | New Pandan | 7.2956 | 125.6835 | U | 8693 | 2349 | 705 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110294 | FTAP BTS | 7.2974 | 125.6811 | 0.33 | Terrestrial Optical Fiber Drop | 0.66 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1268 | 2 | 268 | 1268 | 0405634005 | Region IV-A (CALABARZON) | Quezon | Pitogo | Bilucao | 13.8164 | 122.0989 | R | 816 | 214 | 64 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040556 | FTAP Globe | 13.8171 | 122.0981 | 0.96 | Terrestrial Optical Fiber Drop | 0.32 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1269 | 2 | 269 | 1269 | 0431200002 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 1 | 13.9391 | 121.6107 | U | 2597 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040447 | FTAP Globe | 13.9371 | 121.6094 | 0.25 | Terrestrial Optical Fiber Drop | 0.66 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1270 | 2 | 270 | 1270 | 1130700142 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 9-A | 7.0725 | 125.6085 | U | 7083 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110485 | FTAP Globe | 7.0759 | 125.6041 | 0.62 | Terrestrial Optical Fiber Drop | 0.66 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1271 | 2 | 271 | 1271 | 0304908015 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Norte | 15.2853 | 120.9476 | U | 6716 | 1918 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030425 | FTAP Globe | 15.2822 | 120.9466 | 0.36 | Terrestrial Optical Fiber Drop | 0.03 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1272 | 2 | 272 | 1272 | 0730600041 | Region VII (Central Visayas) | Cebu | City of Cebu | Lahug | 10.3247 | 123.8984 | U | 45908 | 14346 | 4304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0048 | PTCI/MIDC | 10.3284 | 123.8973 | 0.43 | Terrestrial Optical Fiber Drop | 0.67 | 1.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1273 | 2 | 273 | 1273 | 0102809016 | Region I (Ilocos Region) | Ilocos Norte | Dingras | Madamba | 18.1042 | 120.699 | R | 1991 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00043 | Edgepoint | 18.1026 | 120.7004 | 0.23 | Terrestrial Optical Fiber Drop | 0.67 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1274 | 2 | 274 | 1274 | 0330100013 | Region III (Central Luzon) | Pampanga | City of Angeles | Malabañas | 15.1493 | 120.5927 | U | 31164 | 8656 | 2597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3794 | FTAP Smart | 15.1578 | 120.5914 | 0.34 | Terrestrial Optical Fiber Drop | 0.26 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1275 | 2 | 275 | 1275 | 0301410021 | Region III (Central Luzon) | Bulacan | City of Malolos | Catmon | 14.8504 | 120.8136 | U | 2350 | 671 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1589 | FTAP Smart | 14.8511 | 120.8139 | 0.09 | Terrestrial Optical Fiber Drop | 0.67 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1276 | 2 | 276 | 1276 | 0506212018 | Region V (Bicol Region) | Sorsogon | Matnog | Gadgaron | 12.5922 | 124.0804 | R | 2576 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050233 | FTAP Globe | 12.59 | 124.0937 | 1.47 | Terrestrial Optical Fiber Drop | 0.67 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1277 | 2 | 277 | 1277 | 1206511013 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Poblacion | 6.6942 | 124.6775 | U | 14133 | 3719 | 1116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120280 | FTAP Globe | 6.6939 | 124.6788 | 0.15 | Terrestrial Optical Fiber Drop | 0.67 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1278 | 2 | 278 | 1278 | 0403424077 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santo Cristo | 14.0646 | 121.3325 | R | 3552 | 1076 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02002-C08 | PTCI/MIDC | 14.0573 | 121.336 | 0.9 | Terrestrial Optical Fiber Drop | 0.67 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1279 | 2 | 279 | 1279 | 0402114025 | Region IV-A (CALABARZON) | Cavite | Mendez | Panungyan II | 14.1358 | 120.8951 | R | 1786 | 525 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040293 | FTAP Globe | 14.137 | 120.8946 | 0.14 | Terrestrial Optical Fiber Drop | 0.67 | 4.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1280 | 2 | 280 | 1280 | 0403409001 | Region IV-A (CALABARZON) | Laguna | Kalayaan | Longos | 14.337 | 121.4817 | U | 7487 | 2268 | 680 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040168 | FTAP Globe | 14.3245 | 121.4782 | 1.44 | Terrestrial Optical Fiber Drop | 0.67 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1281 | 2 | 281 | 1281 | 0907322053 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Lumbia | 7.8296 | 123.4452 | U | 4427 | 1135 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 0.33 | Terrestrial Optical Fiber Drop | 0.67 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1282 | 2 | 282 | 1282 | 0203137014 | Region II (Cagayan Valley) | Isabela | Tumauini | Carpentero | 17.2713 | 121.8092 | R | 1107 | 291 | 87 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 1.23 | Terrestrial Optical Fiber Drop | 0.67 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1283 | 2 | 283 | 1283 | 0402103018 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu I | 14.4563 | 120.9552 | U | 4531 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01903-C08 | PTCI/MIDC | 14.4247 | 120.9487 | 0.34 | Terrestrial Optical Fiber Drop | 0.38 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1284 | 2 | 284 | 1284 | 0103309004 | Region I (Ilocos Region) | La Union | Caba | Las-ud | 16.4332 | 120.3419 | R | 1354 | 365 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.18 | Terrestrial Optical Fiber Drop | 0.67 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1285 | 2 | 285 | 1285 | 0103306018 | Region I (Ilocos Region) | La Union | Bangar | Maria Cristina East | 16.8918 | 120.431 | R | 948 | 256 | 77 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.83 | Terrestrial Optical Fiber Drop | 0.67 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1286 | 2 | 286 | 1286 | 0301405002 | Region III (Central Luzon) | Bulacan | Bulacan | Balubad | 14.8016 | 120.8753 | U | 3907 | 1116 | 335 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01116-B07 | PTCI/MIDC | 14.8008 | 120.8762 | 0.13 | Terrestrial Optical Fiber Drop | 0.67 | 2.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1287 | 2 | 287 | 1287 | 0403421007 | Region IV-A (CALABARZON) | Laguna | Pangil | San Jose | 14.3997 | 121.4709 | R | 1440 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040118 | FTAP Globe | 14.4055 | 121.4625 | 0.68 | Terrestrial Optical Fiber Drop | 1.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1288 | 2 | 288 | 1288 | 0105544040 | Region I (Ilocos Region) | Pangasinan | Umingan | Nancalabasaan | 15.936 | 120.8432 | R | 2736 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | C41 | FTAP Smart | 15.9259 | 120.8361 | 1.35 | Terrestrial Optical Fiber Drop | 0.68 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1289 | 2 | 289 | 1289 | 0701232010 | Region VII (Central Visayas) | Bohol | Maribojoc | Dipatlong | 9.7464 | 123.8408 | R | 1717 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070413 | FTAP Globe | 9.7455 | 123.842 | 0.16 | Terrestrial Optical Fiber Drop | 0.67 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1290 | 2 | 290 | 1290 | 0307109010 | Region III (Central Luzon) | Zambales | San Antonio | San Juan | 14.945 | 120.0872 | R | 1714 | 451 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 0.1 | Terrestrial Optical Fiber Drop | 0.68 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1291 | 2 | 291 | 1291 | 0500506017 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 18 - Cabagñan West | 13.1418 | 123.749 | U | 4014 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050181 | FTAP Globe | 13.136 | 123.7293 | 0.55 | Terrestrial Optical Fiber Drop | 1.12 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1292 | 2 | 292 | 1292 | 0405813005 | Region IV-A (CALABARZON) | Rizal | Taytay | Santa Ana | 14.5372 | 121.1093 | U | 102828 | 28563 | 8569 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-02461 | Edgepoint | 14.5378 | 121.1085 | 0.11 | Terrestrial Optical Fiber Drop | 0.68 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1293 | 2 | 293 | 1293 | 0301408006 | Region III (Central Luzon) | Bulacan | Guiguinto | Poblacion | 14.8286 | 120.8791 | U | 3625 | 1035 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01115-B07 | PTCI/MIDC | 14.8289 | 120.8826 | 0.38 | Terrestrial Optical Fiber Drop | 0.67 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1294 | 2 | 294 | 1294 | 0402103072 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote II | 14.4654 | 120.9642 | U | 5408 | 1590 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0040 | PTCI/MIDC | 14.467 | 120.9631 | 0.22 | Terrestrial Optical Fiber Drop | 0.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1295 | 2 | 295 | 1295 | 0702219013 | Region VII (Central Visayas) | Cebu | Consolacion | Poblacion Occidental | 10.3727 | 123.954 | U | 6123 | 1611 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0263 | PTCI/MIDC | 10.3701 | 123.9507 | 0.45 | Terrestrial Optical Fiber Drop | 0.68 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1296 | 2 | 296 | 1296 | 0603018023 | Region VI (Western Visayas) | Iloilo | Dumangas | Ilaya 3rd | 10.8269 | 122.7122 | R | 766 | 201 | 60 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.55 | Terrestrial Optical Fiber Drop | 0.29 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1297 | 2 | 297 | 1297 | 0301415018 | Region III (Central Luzon) | Bulacan | Pandi | San Roque | 14.8579 | 120.956 | R | 3025 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01119 | Edgepoint | 14.8516 | 120.9571 | 0.7 | Terrestrial Optical Fiber Drop | 0.68 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1298 | 2 | 298 | 1298 | 0301422026 | Region III (Central Luzon) | Bulacan | San Rafael | Salapungan | 15.0213 | 120.9639 | U | 2553 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02979-B07 | PTCI/MIDC | 15.0224 | 120.963 | 0.15 | Terrestrial Optical Fiber Drop | 0.68 | 3.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1299 | 2 | 299 | 1299 | 0500518014 | Region V (Bicol Region) | Albay | Tiwi | Libtong | 13.453 | 123.6708 | R | 2278 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 1.23 | Terrestrial Optical Fiber Drop | 0.68 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1300 | 2 | 300 | 1300 | 0301420039 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan IV | 14.8474 | 121.0745 | U | 4985 | 1424 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01061-B07 | PTCI/MIDC | 14.8466 | 121.0708 | 0.4 | Terrestrial Optical Fiber Drop | 0.68 | 3.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1301 | 2 | 301 | 1301 | 0201516013 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Centro | 18.2016 | 121.6627 | R | 1463 | 375 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.75 | Terrestrial Optical Fiber Drop | 0.68 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1302 | 2 | 302 | 1302 | 0102820009 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Gregorio | 18.1746 | 120.5888 | R | 2017 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C61 | FTAP Smart | 18.1726 | 120.5935 | 0.55 | Terrestrial Optical Fiber Drop | 0.68 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1303 | 2 | 303 | 1303 | 0402117018 | Region IV-A (CALABARZON) | Cavite | Rosario | Sapa IV | 14.4159 | 120.8508 | R | 1019 | 299 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040116 | FTAP Globe | 14.41 | 120.8725 | 1.05 | Terrestrial Optical Fiber Drop | 2.31 | 2.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1304 | 2 | 304 | 1304 | 0402120022 | Region IV-A (CALABARZON) | Cavite | Tanza | Sanja Mayor | 14.3747 | 120.8541 | U | 15472 | 4550 | 1365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 1.37 | Terrestrial Optical Fiber Drop | 0.68 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1305 | 2 | 305 | 1305 | 0405607067 | Region IV-A (CALABARZON) | Quezon | Calauag | Sabang II | 13.9568 | 122.2808 | R | 3981 | 1047 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0005 | PTCI/MIDC | 13.957 | 122.2821 | 0.14 | Terrestrial Optical Fiber Drop | 0.68 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1306 | 2 | 306 | 1306 | 0702235014 | Region VII (Central Visayas) | Cebu | Oslob | Lagunde | 9.5257 | 123.4359 | R | 3347 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0137 | PTCI/MIDC | 9.5232 | 123.4355 | 0.28 | Terrestrial Optical Fiber Drop | 0.68 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1307 | 2 | 307 | 1307 | 0301403017 | Region III (Central Luzon) | Bulacan | Baliuag | San Jose | 14.9484 | 120.8943 | U | 7044 | 2012 | 604 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00966-B07 | PTCI/MIDC | 14.9475 | 120.8906 | 0.41 | Terrestrial Optical Fiber Drop | 0.68 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1308 | 2 | 308 | 1308 | 1705203033 | MIMAROPA Region | Oriental Mindoro | Bongabong | Aplaya | 12.7501 | 121.487 | R | 2735 | 701 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170114 | FTAP Globe | 12.7482 | 121.4852 | 0.29 | Terrestrial Optical Fiber Drop | 0.68 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1309 | 2 | 309 | 1309 | 0300809014 | Region III (Central Luzon) | Bataan | Orani | Pantalan Luma | 14.8014 | 120.5426 | U | 5862 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030603 | FTAP Globe | 14.8016 | 120.536 | 0.71 | Terrestrial Optical Fiber Drop | 0.68 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1310 | 2 | 310 | 1310 | 0402109056 | Region IV-A (CALABARZON) | Cavite | City of Imus | Maharlika | 14.3966 | 120.9593 | U | 6091 | 1791 | 537 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q10 | FTAP Smart | 14.3992 | 120.9596 | 0.28 | Terrestrial Optical Fiber Drop | 0.68 | 5.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1311 | 2 | 311 | 1311 | 0305416037 | Region III (Central Luzon) | Pampanga | City of San Fernando | Telabastagan | 15.1176 | 120.6049 | U | 16571 | 4142 | 1243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030468 | FTAP Globe | 15.1169 | 120.6026 | 0.26 | Terrestrial Optical Fiber Drop | 0.68 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1312 | 2 | 312 | 1312 | 0731100015 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Mactan | 10.3103 | 124.0095 | U | 50985 | 14567 | 4370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070191 | FTAP BTS | 10.3103 | 123.9999 | 1.05 | Terrestrial Optical Fiber Drop | 0.68 | 6.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1313 | 2 | 313 | 1313 | 0304926021 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Canuto Ramos Pob. | 15.7887 | 120.9897 | R | 2255 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01418-B07 | PTCI/MIDC | 15.7875 | 120.9873 | 0.29 | Terrestrial Optical Fiber Drop | 0.68 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1314 | 2 | 314 | 1314 | 0402118011 | Region IV-A (CALABARZON) | Cavite | Silang | Bulihan | 14.2802 | 120.9962 | U | 26302 | 7735 | 2321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02146-C08 | PTCI/MIDC | 14.2833 | 120.9978 | 0.39 | Terrestrial Optical Fiber Drop | 0.68 | 3.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1315 | 2 | 315 | 1315 | 0600613002 | Region VI (Western Visayas) | Antique | San Jose | Badiang | 10.7652 | 121.9435 | R | 3647 | 935 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0021 | PTCI/MIDC | 10.7615 | 121.9442 | 0.42 | Terrestrial Optical Fiber Drop | 0.68 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1316 | 2 | 316 | 1316 | 1408103010 | Cordillera Administrative Region (CAR) | Apayao | Flora | Poblacion East | 18.2142 | 121.4245 | R | 2699 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-APA-00028 | Edgepoint | 18.2111 | 121.4232 | 0.37 | Terrestrial Optical Fiber Drop | 0.68 | 4.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1317 | 2 | 317 | 1317 | 0402106056 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Paliparan III | 14.3144 | 120.9821 | U | 76791 | 22585 | 6776 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040172 | FTAP Globe | 14.3194 | 120.9838 | 0.59 | Terrestrial Optical Fiber Drop | 0.69 | 3.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1318 | 2 | 318 | 1318 | 0403422010 | Region IV-A (CALABARZON) | Laguna | Pila | Mojon | 14.2202 | 121.383 | R | 1464 | 443 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02383-C08 | PTCI/MIDC | 14.232 | 121.3618 | 0.18 | Terrestrial Optical Fiber Drop | 2.63 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1319 | 2 | 319 | 1319 | 0500508044 | Region V (Bicol Region) | Albay | City of Ligao | Santa Cruz | 13.2334 | 123.5341 | U | 2351 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 1.23 | Terrestrial Optical Fiber Drop | 0.69 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1320 | 2 | 320 | 1320 | 0604502006 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Balingasag | 10.5333 | 122.85 | R | 5052 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0089 | PTCI/MIDC | 10.5344 | 122.8445 | 0.62 | Terrestrial Optical Fiber Drop | 0.68 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1321 | 2 | 321 | 1321 | 0701242004 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Cogon | 9.6529 | 123.8543 | U | 16078 | 4019 | 1206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0056 | PTCI/MIDC | 9.6527 | 123.8555 | 0.13 | Terrestrial Optical Fiber Drop | 0.53 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1322 | 2 | 322 | 1322 | 0402103055 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | P.F. Espiritu IV | 14.4559 | 120.9549 | U | 12310 | 3620 | 1086 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00434-A03 | PTCI/MIDC | 14.4712 | 120.9864 | 0.33 | Terrestrial Optical Fiber Drop | 0.42 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1323 | 2 | 323 | 1323 | 0105508007 | Region I (Ilocos Region) | Pangasinan | Bani | Centro Toma | 16.2528 | 119.8022 | R | 2249 | 624 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-PAN-00371 | Edgepoint | 16.29 | 119.8146 | 4.35 | Terrestrial Optical Fiber Drop | 0.69 | 6.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1324 | 2 | 324 | 1324 | 0203124022 | Region II (Cagayan Valley) | Isabela | Ramon | Bugallon Proper | 16.7812 | 121.5331 | U | 7599 | 1999 | 600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01358-B06 | PTCI/MIDC | 16.7799 | 121.5383 | 0.57 | Terrestrial Optical Fiber Drop | 0.69 | 9.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1325 | 2 | 325 | 1325 | 0604527002 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Barangay 2 | 9.7489 | 122.4091 | R | 4282 | 1157 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060396 | FTAP Globe | 9.7491 | 122.4063 | 0.31 | Terrestrial Optical Fiber Drop | 0.68 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1326 | 2 | 326 | 1326 | 0403414009 | Region IV-A (CALABARZON) | Laguna | Mabitac | Libis ng Nayon | 14.4267 | 121.4321 | R | 1212 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040105 | FTAP Globe | 14.4284 | 121.4288 | 0.4 | Terrestrial Optical Fiber Drop | 0.68 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1327 | 2 | 327 | 1327 | 1004314006 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Mauswagon | 8.5876 | 124.4431 | R | 3634 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 0.39 | Terrestrial Optical Fiber Drop | 1.51 | 1.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1328 | 2 | 328 | 1328 | 0102821017 | Region I (Ilocos Region) | Ilocos Norte | Sarrat | San Nicolas | 18.1602 | 120.6496 | R | 1774 | 479 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01210-B05 | PTCI/MIDC | 18.156 | 120.6512 | 0.49 | Terrestrial Optical Fiber Drop | 0.69 | 4.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1329 | 2 | 329 | 1329 | 0304903013 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Barrera District | 15.4807 | 120.9674 | U | 5766 | 1647 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0004 | PTCI/MIDC | 15.481 | 120.9671 | 0.06 | Terrestrial Optical Fiber Drop | 0.68 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1330 | 2 | 330 | 1330 | 0402110036 | Region IV-A (CALABARZON) | Cavite | Indang | Kaytapos | 14.1965 | 120.8857 | R | 1640 | 482 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCAG0062 | PTCI/MIDC | 14.2012 | 120.8889 | 0.63 | Terrestrial Optical Fiber Drop | 0.68 | 8.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1331 | 2 | 331 | 1331 | 0401016022 | Region IV-A (CALABARZON) | Batangas | Mabini | Pulong Niogan | 13.7539 | 120.9424 | R | 2496 | 693 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1355 | FTAP Smart | 13.7545 | 120.943 | 0.09 | Terrestrial Optical Fiber Drop | 0.69 | 7.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1332 | 2 | 332 | 1332 | 1102408016 | Region XI (Davao Region) | Davao del Sur | Malalag | Poblacion | 6.589 | 125.3988 | U | 6711 | 1973 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110153 | FTAP BTS | 6.5862 | 125.4044 | 0.7 | Terrestrial Optical Fiber Drop | 0.69 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1333 | 2 | 333 | 1333 | 0301412021 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Saluysoy | 14.7435 | 120.9556 | U | 11523 | 3292 | 988 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02488 | Edgepoint | 14.7447 | 120.9604 | 0.53 | Terrestrial Optical Fiber Drop | 0.69 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1334 | 2 | 334 | 1334 | 0401031037 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Poblacion Barangay 6 | 14.0868 | 121.1439 | U | 3654 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040334 | FTAP Globe | 14.0866 | 121.1381 | 0.63 | Terrestrial Optical Fiber Drop | 0.69 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1335 | 2 | 335 | 1335 | 0431200035 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Market View | 13.9338 | 121.6179 | U | 12596 | 3149 | 945 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.33 | Terrestrial Optical Fiber Drop | 0.69 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1336 | 2 | 336 | 1336 | 0405646029 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Poblacion | 13.9671 | 122.5362 | U | 3983 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.54 | Terrestrial Optical Fiber Drop | 0.69 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1337 | 2 | 337 | 1337 | 1004315001 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Dulong | 8.5644 | 124.3591 | R | 1650 | 423 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 0.91 | Terrestrial Optical Fiber Drop | 0.69 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1338 | 2 | 338 | 1338 | 0105526006 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bari | 16.0616 | 120.4026 | U | 6120 | 1700 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00424 | Edgepoint | 16.0601 | 120.4026 | 0.17 | Terrestrial Optical Fiber Drop | 0.69 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1339 | 2 | 339 | 1339 | 0401028008 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Felix | 14.0792 | 121.1891 | U | 6153 | 1709 | 513 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040505 | FTAP Globe | 13.9071 | 121.0424 | 0.55 | Terrestrial Optical Fiber Drop | 2 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1340 | 2 | 340 | 1340 | 1705215018 | MIMAROPA Region | Oriental Mindoro | Victoria | Poblacion I | 13.1731 | 121.2827 | U | 2691 | 690 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170084 | FTAP Globe | 13.1757 | 121.2767 | 0.72 | Terrestrial Optical Fiber Drop | 0.69 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1341 | 2 | 341 | 1341 | 0403425006 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Langgam | 14.3275 | 121.0197 | U | 33922 | 10279 | 3084 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1658 | FTAP Smart | 14.3429 | 121.0406 | 0.83 | Terrestrial Optical Fiber Drop | 2.9 | 2.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1342 | 2 | 342 | 1342 | 0730600060 | Region VII (Central Visayas) | Cebu | City of Cebu | Pung-ol-Sibugay | 10.3311 | 123.8907 | R | 2336 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070338 | FTAP Globe | 10.329 | 123.8925 | 0.3 | Terrestrial Optical Fiber Drop | 0.69 | 2.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1343 | 2 | 343 | 1343 | 0301407008 | Region III (Central Luzon) | Bulacan | Calumpit | Caniogan | 14.9044 | 120.7739 | U | 4714 | 1346 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01097-B07 | PTCI/MIDC | 14.9017 | 120.7697 | 0.55 | Terrestrial Optical Fiber Drop | 0.69 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1344 | 2 | 344 | 1344 | 0304903038 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Imelda District | 15.4755 | 120.9612 | U | 3966 | 1133 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00715 | Edgepoint | 15.4745 | 120.967 | 0.64 | Terrestrial Optical Fiber Drop | 0.69 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1345 | 2 | 345 | 1345 | 0702234011 | Region VII (Central Visayas) | Cebu | City of Naga | Inayagan | 10.2361 | 123.7733 | U | 10585 | 2785 | 836 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0236 | PTCI/MIDC | 10.2326 | 123.7762 | 0.5 | Terrestrial Optical Fiber Drop | 0.18 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1346 | 2 | 346 | 1346 | 0105512002 | Region I (Ilocos Region) | Pangasinan | Binalonan | Bued | 16.0404 | 120.5904 | U | 2858 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 1.1 | Terrestrial Optical Fiber Drop | 0.69 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1347 | 2 | 347 | 1347 | 1004308073 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 18 | 8.8292 | 125.1099 | R | 1432 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0087 | PTCI/MIDC | 8.8252 | 125.1109 | 0.46 | Terrestrial Optical Fiber Drop | 0.69 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1348 | 2 | 348 | 1348 | 0401010023 | Region IV-A (CALABARZON) | Batangas | Ibaan | Sandalan | 13.8292 | 121.1358 | R | 1328 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 0.33 | Terrestrial Optical Fiber Drop | 1.68 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1349 | 2 | 349 | 1349 | 0402103025 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote I | 14.4653 | 120.9643 | U | 6154 | 1810 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040100 | FTAP Globe | 14.4418 | 120.9433 | 0.43 | Terrestrial Optical Fiber Drop | 0.66 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1350 | 2 | 350 | 1350 | 0405806008 | Region IV-A (CALABARZON) | Rizal | Cardona | Dalig | 14.4804 | 121.2343 | U | 6801 | 1889 | 567 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01886 | Edgepoint | 14.4807 | 121.2314 | 0.32 | Terrestrial Optical Fiber Drop | 0.69 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1351 | 2 | 351 | 1351 | 0307102010 | Region III (Central Luzon) | Zambales | Cabangan | Dolores | 15.1688 | 120.0456 | R | 1374 | 361 | 108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00822 | Edgepoint | 15.1674 | 120.0507 | 0.76 | Terrestrial Optical Fiber Drop | 1.2 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1352 | 2 | 352 | 1352 | 0603019017 | Region VI (Western Visayas) | Iloilo | Estancia | Poblacion Zone 1 | 11.456 | 123.1494 | R | 2821 | 742 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060014 | FTAP BTS | 11.4586 | 123.1301 | 0.41 | Terrestrial Optical Fiber Drop | 2.51 | 4.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1353 | 2 | 353 | 1353 | 0301420036 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Maharlika | 14.8223 | 121.058 | U | 3195 | 912 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0004 | PTCI/MIDC | 14.7931 | 121.063 | 0.27 | Terrestrial Optical Fiber Drop | 1.68 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1354 | 2 | 354 | 1354 | 0304927015 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Tagumpay | 15.3608 | 120.9421 | R | 1295 | 370 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03195-B07 | PTCI/MIDC | 15.3513 | 120.9393 | 1.1 | Terrestrial Optical Fiber Drop | 0.7 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1355 | 2 | 355 | 1355 | 0300804036 | Region III (Central Luzon) | Bataan | Dinalupihan | San Ramon | 14.8692 | 120.4626 | U | 3953 | 1098 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030571 | FTAP Globe | 14.8719 | 120.4652 | 0.41 | Terrestrial Optical Fiber Drop | 0.7 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1356 | 2 | 356 | 1356 | 0205005021 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Don Mariano Marcos | 16.4831 | 121.1514 | U | 2213 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00322 | Edgepoint | 16.4862 | 121.1523 | 0.37 | Terrestrial Optical Fiber Drop | 0.7 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1357 | 2 | 357 | 1357 | 0403406001 | Region IV-A (CALABARZON) | Laguna | Calauan | Balayhangin | 14.1411 | 121.3099 | U | 6106 | 1850 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02343-C08 | PTCI/MIDC | 14.1396 | 121.3118 | 0.26 | Terrestrial Optical Fiber Drop | 0.7 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1358 | 2 | 358 | 1358 | 0105546027 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Nancayasan | 15.954 | 120.5766 | U | 8812 | 2447 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01769-B07 | PTCI/MIDC | 15.9536 | 120.5749 | 0.19 | Terrestrial Optical Fiber Drop | 0.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1359 | 2 | 359 | 1359 | 1606724048 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Taft | 9.7836 | 125.4986 | U | 20358 | 4965 | 1490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0012 | PTCI/MIDC | 9.7815 | 125.4989 | 0.19 | Terrestrial Optical Fiber Drop | 0.65 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1360 | 2 | 360 | 1360 | 1001315014 | Region X (Northern Mindanao) | Bukidnon | Maramag | North Poblacion | 7.7596 | 125.0075 | U | 16064 | 4227 | 1268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0054 | PTCI/MIDC | 7.7578 | 125.0049 | 0.35 | Terrestrial Optical Fiber Drop | 0.7 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1361 | 2 | 361 | 1361 | 0307106004 | Region III (Central Luzon) | Zambales | Masinloc | Collat | 15.5425 | 119.9526 | R | 3339 | 878 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0012 | PTCI/MIDC | 15.5354 | 119.9518 | 0.8 | Terrestrial Optical Fiber Drop | 0.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1362 | 2 | 362 | 1362 | 0803702054 | Region VIII (Eastern Visayas) | Leyte | Alangalang | San Roque | 11.2086 | 124.8466 | R | 1145 | 301 | 90 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 0.44 | Terrestrial Optical Fiber Drop | 0.7 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1363 | 2 | 363 | 1363 | 1030500041 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bugo | 8.5035 | 124.7527 | U | 31796 | 8832 | 2650 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0039 | PTCI/MIDC | 8.5035 | 124.756 | 0.36 | Terrestrial Optical Fiber Drop | 0.7 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1364 | 2 | 364 | 1364 | 0600415006 | Region VI (Western Visayas) | Aklan | New Washington | Jalas | 11.6617 | 122.4007 | R | 1699 | 435 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0004 | PTCI/MIDC | 11.676 | 122.4098 | 3.93 | Terrestrial Optical Fiber Drop | 3.99 | 4.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1365 | 2 | 365 | 1365 | 0603047015 | Region VI (Western Visayas) | Iloilo | Zarraga | Pajo | 10.7401 | 122.5413 | R | 1279 | 336 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.85 | Terrestrial Optical Fiber Drop | 2.85 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1366 | 2 | 366 | 1366 | 1004313009 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Tabok | 8.801 | 124.7851 | R | 2492 | 638 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.72 | Terrestrial Optical Fiber Drop | 0.7 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1367 | 2 | 367 | 1367 | 0105531029 | Region I (Ilocos Region) | Pangasinan | Rosales | Station District | 15.89 | 120.6345 | R | 2772 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00544 | Edgepoint | 15.8933 | 120.6367 | 0.43 | Terrestrial Optical Fiber Drop | 0.7 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1368 | 2 | 368 | 1368 | 0803748040 | Region VIII (Eastern Visayas) | Leyte | Tanauan | Buntay | 11.1109 | 125.0168 | R | 967 | 254 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080011 | FTAP BTS | 11.1165 | 125.0165 | 0.63 | Terrestrial Optical Fiber Drop | 0.7 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1369 | 2 | 369 | 1369 | 0631000156 | Region VI (Western Visayas) | Iloilo | City of Iloilo | San Juan | 10.6849 | 122.5453 | U | 11852 | 2821 | 846 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0041 | PTCI/MIDC | 10.6914 | 122.5427 | 0.78 | Terrestrial Optical Fiber Drop | 0.7 | 3.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1370 | 2 | 370 | 1370 | 1606724068 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Washington | 9.786 | 125.4888 | U | 20439 | 4985 | 1496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0009 | PTCI/MIDC | 9.7834 | 125.4889 | 0.29 | Terrestrial Optical Fiber Drop | 0.7 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1371 | 2 | 371 | 1371 | 0301410043 | Region III (Central Luzon) | Bulacan | City of Malolos | San Juan | 14.8344 | 120.8148 | U | 4773 | 1363 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02258 | Edgepoint | 14.8415 | 120.8115 | 0.86 | Terrestrial Optical Fiber Drop | 0.71 | 1.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1372 | 2 | 372 | 1372 | 0405647030 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Ipilan | 14.024 | 121.587 | R | 4041 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B39 | FTAP Smart | 14.0303 | 121.5879 | 0.71 | Terrestrial Optical Fiber Drop | 0.7 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1373 | 2 | 373 | 1373 | 0105522030 | Region I (Ilocos Region) | Pangasinan | Lingayen | Rosario | 15.9453 | 120.2669 | R | 2541 | 705 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00518 | Edgepoint | 15.9402 | 120.2679 | 0.58 | Terrestrial Optical Fiber Drop | 0.71 | 7.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1374 | 2 | 374 | 1374 | 0300809001 | Region III (Central Luzon) | Bataan | Orani | Bagong Paraiso | 14.7999 | 120.5302 | R | 3258 | 905 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01183 | Edgepoint | 14.8017 | 120.5308 | 0.22 | Terrestrial Optical Fiber Drop | 0.71 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1375 | 2 | 375 | 1375 | 1001317003 | Region X (Northern Mindanao) | Bukidnon | Quezon | Delapa | 7.7025 | 125.1136 | R | 2898 | 762 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.5 | Terrestrial Optical Fiber Drop | 0.54 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1376 | 2 | 376 | 1376 | 0401021025 | Region IV-A (CALABARZON) | Batangas | Rosario | Namuco | 13.8381 | 121.2019 | U | 6065 | 1684 | 505 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 0.98 | Terrestrial Optical Fiber Drop | 0.71 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1377 | 2 | 377 | 1377 | 0402106021 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Emmanuel Bergado I | 14.3202 | 120.9563 | U | 8424 | 2477 | 743 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040179 | FTAP Globe | 14.3126 | 120.9715 | 0.16 | Terrestrial Optical Fiber Drop | 1.33 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1378 | 2 | 378 | 1378 | 0306905055 | Region III (Central Luzon) | Tarlac | Concepcion | Green Village | 15.3244 | 120.6464 | R | 2985 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01798-B07 | PTCI/MIDC | 15.3203 | 120.6534 | 0.87 | Terrestrial Optical Fiber Drop | 0.71 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1379 | 2 | 379 | 1379 | 1403213042 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Bulanao Norte | 17.4189 | 121.4444 | U | 5871 | 1365 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140132 | FTAP Globe | 17.4146 | 121.443 | 0.5 | Terrestrial Optical Fiber Drop | 0.71 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1380 | 2 | 380 | 1380 | 0402109045 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VI | 14.4072 | 120.9361 | R | 2858 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAM0364 | PTCI/MIDC | 14.3883 | 120.8963 | 0.19 | Terrestrial Optical Fiber Drop | 0.49 | 4.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1381 | 2 | 381 | 1381 | 0600403026 | Region VI (Western Visayas) | Aklan | Banga | Tabayon | 11.6327 | 122.347 | R | 2005 | 514 | 154 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 2.06 | Terrestrial Optical Fiber Drop | 0.71 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1382 | 2 | 382 | 1382 | 1408104020 | Cordillera Administrative Region (CAR) | Apayao | Kabugao | Poblacion | 18.0256 | 121.1833 | R | 3210 | 764 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-APA-00050 | Edgepoint | 18.0144 | 121.1855 | 1.26 | Terrestrial Optical Fiber Drop | 0.71 | 9.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1383 | 2 | 383 | 1383 | 0203114013 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Baligatan | 17.1233 | 121.8669 | U | 2812 | 740 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0016 | PTCI/MIDC | 17.1227 | 121.8677 | 0.1 | Terrestrial Optical Fiber Drop | 0.71 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1384 | 2 | 384 | 1384 | 0604524011 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay II | 10.4844 | 123.4169 | U | 6797 | 1837 | 551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0058 | PTCI/MIDC | 10.4822 | 123.4207 | 0.48 | Terrestrial Optical Fiber Drop | 0.71 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1385 | 2 | 385 | 1385 | 0330100005 | Region III (Central Luzon) | Pampanga | City of Angeles | Claro M. Recto | 15.1452 | 120.5927 | U | 5377 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.24 | Terrestrial Optical Fiber Drop | 0.71 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1386 | 2 | 386 | 1386 | 1630400055 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Limaha Pob. | 8.9526 | 125.5323 | U | 5768 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0010 | PTCI/MIDC | 8.947 | 125.5334 | 0.63 | Terrestrial Optical Fiber Drop | 0.71 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1387 | 2 | 387 | 1387 | 0203104016 | Region II (Cagayan Valley) | Isabela | Benito Soliven | District I | 16.979 | 121.9586 | R | 3549 | 933 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_ISA_0041 | LDIC | 16.9909 | 121.9458 | 1.9 | Terrestrial Optical Fiber Drop | 0.71 | 11.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1388 | 2 | 388 | 1388 | 0301423001 | Region III (Central Luzon) | Bulacan | Santa Maria | Bagbaguin | 14.8188 | 120.9555 | U | 8194 | 2341 | 702 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01054-B07 | PTCI/MIDC | 14.8182 | 120.9565 | 0.13 | Terrestrial Optical Fiber Drop | 0.71 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1389 | 2 | 389 | 1389 | 0401030004 | Region IV-A (CALABARZON) | Batangas | Talisay | Banga | 14.0927 | 121.0119 | U | 4977 | 1382 | 415 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.58 | Terrestrial Optical Fiber Drop | 0.71 | 5.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1390 | 2 | 390 | 1390 | 0601914030 | Region VI (Western Visayas) | Capiz | City of Roxas | Inzo Arnaldo Village | 11.586 | 122.7541 | U | 5115 | 1346 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.73 | Terrestrial Optical Fiber Drop | 0.71 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1391 | 2 | 391 | 1391 | 0304911061 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santo Cristo District | 15.6578 | 120.7601 | U | 4141 | 1183 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02875-B07 | PTCI/MIDC | 15.6577 | 120.7609 | 0.09 | Terrestrial Optical Fiber Drop | 0.71 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1392 | 2 | 392 | 1392 | 0301412001 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bagbaguin | 14.8189 | 120.9555 | U | 8807 | 2516 | 755 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01054-B07 | PTCI/MIDC | 14.8182 | 120.9565 | 0.13 | Terrestrial Optical Fiber Drop | 0.71 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1393 | 2 | 393 | 1393 | 0403424010 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-F | 14.0601 | 121.323 | U | 2395 | 725 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02075-C08 | PTCI/MIDC | 14.0549 | 121.3128 | 1.24 | Terrestrial Optical Fiber Drop | 0.71 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1394 | 2 | 394 | 1394 | 0402109031 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu I-D | 14.3735 | 120.9416 | U | 4030 | 1185 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01898-C08 | PTCI/MIDC | 14.3775 | 120.9413 | 0.45 | Terrestrial Optical Fiber Drop | 1.15 | 7.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1395 | 2 | 395 | 1395 | 0307707033 | Region III (Central Luzon) | Aurora | Maria Aurora | San Jose | 15.7874 | 121.4786 | R | 1312 | 345 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02889-B06 | PTCI/MIDC | 15.7802 | 121.482 | 0.88 | Terrestrial Optical Fiber Drop | 0.72 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1396 | 2 | 396 | 1396 | 0403414013 | Region IV-A (CALABARZON) | Laguna | Mabitac | Sinagtala | 14.4417 | 121.4005 | R | 968 | 293 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_LAG_0002 | LDIC | 121.4271 | 14.4267 | 0.93 | Terrestrial Optical Fiber Drop | 3.11 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1397 | 2 | 397 | 1397 | 0601916020 | Region VI (Western Visayas) | Capiz | Sigma | Poblacion Sur | 11.4219 | 122.6617 | R | 1889 | 497 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060239 | FTAP Globe | 11.4171 | 122.6709 | 1.13 | Terrestrial Optical Fiber Drop | 0.72 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1398 | 2 | 398 | 1398 | 0601914014 | Region VI (Western Visayas) | Capiz | City of Roxas | Poblacion VII | 11.5825 | 122.7471 | R | 2196 | 577 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.74 | Terrestrial Optical Fiber Drop | 0.72 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1399 | 2 | 399 | 1399 | 0402109019 | Region IV-A (CALABARZON) | Cavite | City of Imus | Palico I | 14.4278 | 120.9466 | R | 2175 | 639 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01924-C08 | PTCI/MIDC | 14.3888 | 120.9378 | 0.48 | Terrestrial Optical Fiber Drop | 0.28 | 2.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1400 | 2 | 400 | 1400 | 0401021026 | Region IV-A (CALABARZON) | Batangas | Rosario | Namunga | 13.8454 | 121.1948 | U | 5862 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 0.21 | Terrestrial Optical Fiber Drop | 0.72 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1401 | 2 | 401 | 1401 | 0103314019 | Region I (Ilocos Region) | La Union | City of San Fernando | Camansi | 16.615 | 120.336 | R | 1000 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3087 | FTAP Smart | 16.6106 | 120.321 | 0.55 | Terrestrial Optical Fiber Drop | 2.32 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1402 | 2 | 402 | 1402 | 0201513021 | Region II (Cagayan Valley) | Cagayan | Gattaran | Centro Sur | 18.0605 | 121.6425 | R | 2191 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00048 | Edgepoint | 18.056 | 121.6434 | 0.5 | Terrestrial Optical Fiber Drop | 0.72 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1403 | 2 | 403 | 1403 | 0402103038 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mabolo III | 14.4516 | 120.9291 | R | 2458 | 722 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S3365 | FTAP Smart | 14.4127 | 120.9414 | 0.29 | Terrestrial Optical Fiber Drop | 2.17 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1404 | 2 | 404 | 1404 | 0307113024 | Region III (Central Luzon) | Zambales | Santa Cruz | Poblacion South | 15.7614 | 119.9107 | U | 3885 | 1022 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZMG0008 | PTCI/MIDC | 15.7531 | 119.9154 | 1.05 | Terrestrial Optical Fiber Drop | 0.72 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1405 | 2 | 405 | 1405 | 0304927003 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Burgos District | 15.3607 | 120.9422 | R | 2367 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1327 | FTAP Smart | 15.3572 | 120.9313 | 0.81 | Terrestrial Optical Fiber Drop | 0.71 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1406 | 2 | 406 | 1406 | 0431200024 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ilayang Iyam | 13.9346 | 121.6051 | U | 12231 | 3057 | 917 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S0893 | FTAP Smart | 13.9374 | 121.609 | 0.53 | Terrestrial Optical Fiber Drop | 0.72 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1407 | 2 | 407 | 1407 | 1001317007 | Region X (Northern Mindanao) | Bukidnon | Quezon | Cawayan | 7.7004 | 125.1742 | R | 1078 | 283 | 85 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 0.68 | Terrestrial Optical Fiber Drop | 6.55 | 6.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1408 | 2 | 408 | 1408 | 0307111008 | Region III (Central Luzon) | Zambales | San Marcelino | Linasin | 14.9735 | 120.1496 | R | 3215 | 846 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00974 | Edgepoint | 14.9764 | 120.153 | 0.49 | Terrestrial Optical Fiber Drop | 0.72 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1409 | 2 | 409 | 1409 | 0500516011 | Region V (Bicol Region) | Albay | Santo Domingo | San Vicente Pob. | 13.2382 | 123.7761 | R | 1357 | 330 | 99 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050154 | FTAP Globe | 13.2479 | 123.7822 | 1.57 | Terrestrial Optical Fiber Drop | 0.17 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1410 | 2 | 410 | 1410 | 1705204007 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Campaasan | 12.3365 | 121.3394 | U | 3268 | 837 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03378-C09 | PTCI/MIDC | 12.32 | 121.3406 | 1.84 | Terrestrial Optical Fiber Drop | 0.72 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1411 | 2 | 411 | 1411 | 0405808003 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Geronimo | 14.7325 | 121.1496 | U | 6475 | 1798 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00837-A04 | PTCI/MIDC | 14.7318 | 121.151 | 0.17 | Terrestrial Optical Fiber Drop | 0.72 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1412 | 2 | 412 | 1412 | 0600411007 | Region VI (Western Visayas) | Aklan | Makato | Cajilo | 11.7222 | 122.2957 | R | 2061 | 528 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060217 | FTAP Globe | 11.715 | 122.292 | 0.9 | Terrestrial Optical Fiber Drop | 0.73 | 1.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1413 | 2 | 413 | 1413 | 0803740022 | Region VIII (Eastern Visayas) | Leyte | Palompon | Mazawalo Pob. | 11.0458 | 124.389 | R | 4628 | 1217 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 9.33 | Terrestrial Optical Fiber Drop | 0.73 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1414 | 2 | 414 | 1414 | 0604518002 | Region VI (Western Visayas) | Negros Occidental | Manapla | Barangay I | 10.8505 | 123.16 | R | 2253 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060323 | FTAP Globe | 10.9526 | 123.1256 | 0.41 | Terrestrial Optical Fiber Drop | 11.05 | 9.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1415 | 2 | 415 | 1415 | 1030500037 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Bayabas | 8.5132 | 124.6388 | U | 14245 | 3956 | 1187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0041 | PTCI/MIDC | 8.5098 | 124.6401 | 0.41 | Terrestrial Optical Fiber Drop | 0.73 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1416 | 2 | 416 | 1416 | 0403405045 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Prinza | 14.2007 | 121.1405 | U | 5792 | 1755 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0010 | LDIC | 14.1974 | 121.1394 | 0.39 | Terrestrial Optical Fiber Drop | 0.73 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1417 | 2 | 417 | 1417 | 0405804014 | Region IV-A (CALABARZON) | Rizal | Binangonan | Kalawaan | 14.491 | 121.185 | U | 37983 | 10550 | 3165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0115 | PTCI/MIDC | 14.4923 | 121.1859 | 0.18 | Terrestrial Optical Fiber Drop | 0.73 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1418 | 2 | 418 | 1418 | 0301422021 | Region III (Central Luzon) | Bulacan | San Rafael | Pasong Intsik | 15.0106 | 120.9694 | R | 1560 | 445 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030507 | FTAP Globe | 15.001 | 120.9731 | 1.14 | Terrestrial Optical Fiber Drop | 0.73 | 3.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1419 | 2 | 419 | 1419 | 0301403019 | Region III (Central Luzon) | Bulacan | Baliuag | Santa Barbara | 14.9419 | 120.8903 | U | 13210 | 3774 | 1132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01008 | Edgepoint | 14.9414 | 120.888 | 0.25 | Terrestrial Optical Fiber Drop | 0.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1420 | 2 | 420 | 1420 | 1705110034 | MIMAROPA Region | Occidental Mindoro | San Jose | Pag-Asa | 12.3443 | 121.0655 | U | 12657 | 3245 | 974 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170137 | FTAP Globe | 12.3508 | 121.0661 | 0.73 | Terrestrial Optical Fiber Drop | 0.73 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1421 | 2 | 421 | 1421 | 0600613017 | Region VI (Western Visayas) | Antique | San Jose | Funda-Dalipe | 10.7602 | 121.9317 | U | 7419 | 1902 | 571 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0020 | PTCI/MIDC | 10.76 | 121.9281 | 0.4 | Terrestrial Optical Fiber Drop | 0.73 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1422 | 2 | 422 | 1422 | 0201505029 | Region II (Cagayan Valley) | Cagayan | Aparri | Macanaya | 18.3506 | 121.6396 | U | 5709 | 1463 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3433 | FTAP Smart | 18.3503 | 121.639 | 0.07 | Terrestrial Optical Fiber Drop | 0.73 | 10.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1423 | 2 | 423 | 1423 | 1705205029 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Lazareto | 13.4283 | 121.1996 | R | 4858 | 1245 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 0.37 | Terrestrial Optical Fiber Drop | 0.73 | 6.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1424 | 2 | 424 | 1424 | 0506203025 | Region V (Bicol Region) | Sorsogon | Bulan | Benigno S. Aquino | 12.6759 | 123.8752 | R | 3631 | 907 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SOR_0002 | LDIC | 12.6765 | 123.8744 | 0.11 | Terrestrial Optical Fiber Drop | 0.73 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1425 | 2 | 425 | 1425 | 0330100003 | Region III (Central Luzon) | Pampanga | City of Angeles | Balibago | 15.1699 | 120.5837 | U | 44148 | 12263 | 3679 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030444 | FTAP Globe | 15.1704 | 120.5779 | 0.62 | Terrestrial Optical Fiber Drop | 0.73 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1426 | 2 | 426 | 1426 | 0402115013 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Silangan | 14.3243 | 120.7778 | U | 11097 | 3263 | 979 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02229-C08 | PTCI/MIDC | 14.3227 | 120.7719 | 0.67 | Terrestrial Optical Fiber Drop | 0.73 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1427 | 2 | 427 | 1427 | 0501723006 | Region V (Bicol Region) | Camarines Sur | Nabua | Inapatan | 13.3991 | 123.3183 | R | 2942 | 700 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03257-C10 | PTCI/MIDC | 13.4086 | 123.3098 | 1.41 | Terrestrial Optical Fiber Drop | 0.73 | 5.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1428 | 2 | 428 | 1428 | 0305403018 | Region III (Central Luzon) | Pampanga | Arayat | Poblacion | 15.1489 | 120.771 | U | 2331 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.15 | Terrestrial Optical Fiber Drop | 0.73 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1429 | 2 | 429 | 1429 | 0500504009 | Region V (Bicol Region) | Albay | Guinobatan | Calzada | 13.1906 | 123.5974 | R | 2600 | 634 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 0.27 | Terrestrial Optical Fiber Drop | 0.73 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1430 | 2 | 430 | 1430 | 0403417048 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Talangan | 14.1437 | 121.4138 | R | 2234 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02122-C08 | PTCI/MIDC | 14.1344 | 121.4104 | 1.1 | Terrestrial Optical Fiber Drop | 0.73 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1431 | 2 | 431 | 1431 | 0203137042 | Region II (Cagayan Valley) | Isabela | Tumauini | San Pedro | 17.2775 | 121.8103 | U | 3086 | 812 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 0.71 | Terrestrial Optical Fiber Drop | 0.73 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1432 | 2 | 432 | 1432 | 0105518008 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Bonuan Boquig | 16.0778 | 120.3583 | U | 15474 | 4298 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00416 | Edgepoint | 16.0777 | 120.3608 | 0.27 | Terrestrial Optical Fiber Drop | 0.73 | 3.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1433 | 2 | 433 | 1433 | 0603043061 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Barangay Zone VI | 10.8219 | 122.5327 | R | 3583 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.18 | Terrestrial Optical Fiber Drop | 0.64 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1434 | 2 | 434 | 1434 | 0402106016 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Zone I | 14.3203 | 120.9567 | U | 4441 | 1306 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01857-C08 | PTCI/MIDC | 14.3195 | 120.9635 | 0.35 | Terrestrial Optical Fiber Drop | 1.3 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1435 | 2 | 435 | 1435 | 0500504048 | Region V (Bicol Region) | Albay | Guinobatan | Travesia | 13.1892 | 123.6105 | R | 3871 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050169 | FTAP Globe | 13.1889 | 123.5992 | 1.22 | Terrestrial Optical Fiber Drop | 0.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1436 | 2 | 436 | 1436 | 0405635010 | Region IV-A (CALABARZON) | Quezon | Plaridel | Pampaaralan | 13.9553 | 122.0153 | R | 544 | 143 | 43 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040420 | FTAP Globe | 13.9547 | 122.0232 | 0.85 | Terrestrial Optical Fiber Drop | 0.73 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1437 | 2 | 437 | 1437 | 0603047011 | Region VI (Western Visayas) | Iloilo | Zarraga | Jalaud Norte | 10.8298 | 122.6158 | R | 2460 | 647 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060021 | FTAP BTS | 10.8361 | 122.6092 | 1.01 | Terrestrial Optical Fiber Drop | 0.73 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1438 | 2 | 438 | 1438 | 0306910016 | Region III (Central Luzon) | Tarlac | Paniqui | Estacion | 15.6743 | 120.5847 | U | 4960 | 1271 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.52 | Terrestrial Optical Fiber Drop | 0.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1439 | 2 | 439 | 1439 | 0402116003 | Region IV-A (CALABARZON) | Cavite | Noveleta | Salcedo I | 14.4285 | 120.8763 | R | 1999 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.23 | Terrestrial Optical Fiber Drop | 0.73 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1440 | 2 | 440 | 1440 | 0402103019 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Real I | 14.4333 | 120.9397 | U | 5560 | 1635 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01895-C08 | PTCI/MIDC | 14.433 | 120.9376 | 0.23 | Terrestrial Optical Fiber Drop | 0.74 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1441 | 2 | 441 | 1441 | 0431200030 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Silangan | 13.9513 | 121.6415 | U | 9383 | 2345 | 704 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040414 | FTAP Globe | 13.9597 | 121.6314 | 1.43 | Terrestrial Optical Fiber Drop | 0.74 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1442 | 2 | 442 | 1442 | 0405608009 | Region IV-A (CALABARZON) | Quezon | Candelaria | Malabanban Sur | 13.9164 | 121.4306 | U | 8660 | 2278 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1264 | FTAP Smart | 13.9179 | 121.4369 | 0.7 | Terrestrial Optical Fiber Drop | 0.74 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1443 | 2 | 443 | 1443 | 0701232004 | Region VII (Central Visayas) | Bohol | Maribojoc | Anislag | 9.7376 | 123.8501 | R | 1054 | 263 | 79 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BOH_0006 | LDIC | 9.7452 | 123.8513 | 0.85 | Terrestrial Optical Fiber Drop | 0.74 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1444 | 2 | 444 | 1444 | 0201526010 | Region II (Cagayan Valley) | Cagayan | Santo Niño | Centro Norte | 17.8829 | 121.5712 | R | 3115 | 798 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAG-02201 | Edgepoint | 17.8863 | 121.5699 | 0.52 | Terrestrial Optical Fiber Drop | 0.25 | 7.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1445 | 2 | 445 | 1445 | 0803702018 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Cavite | 11.2188 | 124.8597 | R | 904 | 237 | 71 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0003 | PTCI/MIDC | 11.2031 | 124.8469 | 0.46 | Terrestrial Optical Fiber Drop | 2.39 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1446 | 2 | 446 | 1446 | 0402109001 | Region IV-A (CALABARZON) | Cavite | City of Imus | Alapan I-A | 14.4081 | 120.8967 | U | 14840 | 4364 | 1309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01880-C08 | PTCI/MIDC | 14.3979 | 120.9428 | 0.47 | Terrestrial Optical Fiber Drop | 2.73 | 1.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1447 | 2 | 447 | 1447 | 0806407059 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Tagnipa | 10.136 | 124.8353 | U | 3302 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.27 | Terrestrial Optical Fiber Drop | 0.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1448 | 2 | 448 | 1448 | 0402119021 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Tolentino West | 14.132 | 120.9761 | R | 1517 | 446 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1604 | FTAP Smart | 14.1302 | 120.978 | 0.28 | Terrestrial Optical Fiber Drop | 0.74 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1449 | 2 | 449 | 1449 | 1402705007 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Mabatobato | 16.6594 | 121.2071 | R | 2152 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02362-B05 | PTCI/MIDC | 16.6558 | 121.209 | 0.45 | Terrestrial Optical Fiber Drop | 0.74 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1450 | 2 | 450 | 1450 | 0105525039 | Region I (Ilocos Region) | Pangasinan | Manaoag | Poblacion | 16.0452 | 120.4908 | U | 5514 | 1531 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_PNG_0001 | LDIC | 16.0437 | 120.492 | 0.2 | Terrestrial Optical Fiber Drop | 0.74 | 7.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1451 | 2 | 451 | 1451 | 0501725019 | Region V (Bicol Region) | Camarines Sur | Ocampo | San Francisco | 13.5595 | 123.3822 | R | 3182 | 757 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.1 | Terrestrial Optical Fiber Drop | 0.74 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1452 | 2 | 452 | 1452 | 0501716033 | Region V (Bicol Region) | Camarines Sur | City of Iriga | Santa Teresita | 13.484 | 123.4245 | R | 3076 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03173-C10 | PTCI/MIDC | 13.48 | 123.4199 | 0.67 | Terrestrial Optical Fiber Drop | 0.74 | 5.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1453 | 2 | 453 | 1453 | 0403428003 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Caingin | 14.3047 | 121.1255 | U | 26835 | 8131 | 2439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02093-C08 | PTCI/MIDC | 14.3014 | 121.117 | 0.99 | Terrestrial Optical Fiber Drop | 0.74 | 2.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1454 | 2 | 454 | 1454 | 0501705025 | Region V (Bicol Region) | Camarines Sur | Buhi | San Isidro | 13.3789 | 123.5101 | R | 2741 | 652 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.75 | Terrestrial Optical Fiber Drop | 4.16 | 9.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1455 | 2 | 455 | 1455 | 0500506008 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 12 - Tula-tula | 13.1406 | 123.7361 | R | 2338 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0039 | PTCI/MIDC | 13.1354 | 123.7419 | 0.32 | Terrestrial Optical Fiber Drop | 0.42 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1456 | 2 | 456 | 1456 | 0105545013 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Malayo | 15.8272 | 120.3429 | R | 2045 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00567 | Edgepoint | 15.8227 | 120.332 | 1.27 | Terrestrial Optical Fiber Drop | 0.74 | 10.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1457 | 2 | 457 | 1457 | 0304911060 | Region III (Central Luzon) | Nueva Ecija | Guimba | Santa Veronica District | 15.663 | 120.7621 | U | 4221 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02875-B07 | PTCI/MIDC | 15.6577 | 120.7609 | 0.61 | Terrestrial Optical Fiber Drop | 0.75 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1458 | 2 | 458 | 1458 | 0401022001 | Region IV-A (CALABARZON) | Batangas | San Jose | Aguila | 13.8835 | 121.0983 | U | 3031 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1014 | FTAP Smart | 13.8783 | 121.0934 | 0.5 | Terrestrial Optical Fiber Drop | 0.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1459 | 2 | 459 | 1459 | 1430300046 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Holy Ghost Extension | 16.4179 | 120.6046 | R | 2945 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0015 | LDIC | 16.4176 | 120.6046 | 0.03 | Terrestrial Optical Fiber Drop | 0.75 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1460 | 2 | 460 | 1460 | 1606819018 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | San Agustin Sur | 9.0775 | 126.1906 | U | 5982 | 1459 | 438 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 3.77 | Terrestrial Optical Fiber Drop | 0.75 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1461 | 2 | 461 | 1461 | 0403425028 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Rosario | 14.3361 | 121.0486 | U | 6479 | 1963 | 589 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03020-C08 | PTCI/MIDC | 14.3628 | 121.0347 | 0.67 | Terrestrial Optical Fiber Drop | 1.29 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1462 | 2 | 462 | 1462 | 0401022031 | Region IV-A (CALABARZON) | Batangas | San Jose | Taysan | 13.8835 | 121.0996 | U | 3214 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1014 | FTAP Smart | 13.8783 | 121.0934 | 0.88 | Terrestrial Optical Fiber Drop | 0.75 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1463 | 2 | 463 | 1463 | 0306906034 | Region III (Central Luzon) | Tarlac | Gerona | Salapungan | 15.594 | 120.6114 | U | 3181 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00639 | Edgepoint | 15.5983 | 120.6246 | 1.49 | Terrestrial Optical Fiber Drop | 0.75 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1464 | 2 | 464 | 1464 | 0405647045 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Opias | 14.03 | 121.5908 | U | 5490 | 1444 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00120-C08 | PTCI/MIDC | 14.028 | 121.5926 | 0.29 | Terrestrial Optical Fiber Drop | 0.75 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1465 | 2 | 465 | 1465 | 0401029013 | Region IV-A (CALABARZON) | Batangas | Taal | Halang | 13.9006 | 120.9304 | R | 1585 | 440 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040516 | FTAP Globe | 13.893 | 120.9287 | 0.86 | Terrestrial Optical Fiber Drop | 0.75 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1466 | 2 | 466 | 1466 | 0401001014 | Region IV-A (CALABARZON) | Batangas | Agoncillo | Pansipit | 13.9286 | 120.9448 | R | 1842 | 511 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040462 | FTAP Globe | 13.9283 | 120.9517 | 0.74 | Terrestrial Optical Fiber Drop | 0.75 | 4.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1467 | 2 | 467 | 1467 | 0402107007 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Kaypaaba | 14.1836 | 120.7893 | R | 2213 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.94 | Terrestrial Optical Fiber Drop | 0.75 | 3.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1468 | 2 | 468 | 1468 | 0401027006 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Cuta East | 13.8654 | 120.99 | R | 1233 | 342 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1310 | FTAP Smart | 13.8604 | 120.9908 | 0.57 | Terrestrial Optical Fiber Drop | 0.75 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1469 | 2 | 469 | 1469 | 0401034001 | Region IV-A (CALABARZON) | Batangas | Tuy | Acle | 14.0216 | 120.7302 | R | 1207 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040375 | FTAP Globe | 14.0191 | 120.7277 | 0.64 | Terrestrial Optical Fiber Drop | 0.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1470 | 2 | 470 | 1470 | 1130700134 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 1-A | 7.0637 | 125.6074 | R | 3214 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0021 | PTCI/MIDC | 7.0614 | 125.6075 | 0.26 | Terrestrial Optical Fiber Drop | 0.75 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1471 | 2 | 471 | 1471 | 0300811023 | Region III (Central Luzon) | Bataan | Pilar | Santa Rosa | 14.6772 | 120.5473 | U | 7499 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1501 | FTAP Smart | 14.6827 | 120.551 | 0.74 | Terrestrial Optical Fiber Drop | 0.75 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1472 | 2 | 472 | 1472 | 0402103012 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Maliksi I | 14.46 | 120.9523 | U | 5551 | 1632 | 490 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.93 | Terrestrial Optical Fiber Drop | 0.75 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1473 | 2 | 473 | 1473 | 0301405010 | Region III (Central Luzon) | Bulacan | Bulacan | San Jose | 14.7934 | 120.881 | U | 3732 | 1066 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01187 | Edgepoint | 14.7956 | 120.8781 | 0.72 | Terrestrial Optical Fiber Drop | 0.44 | 3.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1474 | 2 | 474 | 1474 | 1130700069 | Region XI (Davao Region) | Davao del Sur | City of Davao | Mandug | 7.1554 | 125.5886 | U | 15916 | 4681 | 1404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110320 | FTAP BTS | 7.1611 | 125.5956 | 1 | Terrestrial Optical Fiber Drop | 0.75 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1475 | 2 | 475 | 1475 | 1401110005 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Balili | 16.4497 | 120.5949 | U | 18238 | 5210 | 1563 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140179 | FTAP Globe | 16.4461 | 120.5914 | 0.56 | Terrestrial Optical Fiber Drop | 0.75 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1476 | 2 | 476 | 1476 | 0301421054 | Region III (Central Luzon) | Bulacan | San Miguel | Tartaro | 15.1664 | 121.0398 | U | 6312 | 1803 | 541 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030445 | FTAP Globe | 15.1702 | 121.044 | 0.62 | Terrestrial Optical Fiber Drop | 0.75 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1477 | 2 | 477 | 1477 | 1001315008 | Region X (Northern Mindanao) | Bukidnon | Maramag | Dologon | 7.8351 | 125.0421 | U | 15472 | 4071 | 1221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0031 | PTCI/MIDC | 7.835 | 125.045 | 0.33 | Terrestrial Optical Fiber Drop | 0.76 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1478 | 2 | 478 | 1478 | 0402104006 | Region IV-A (CALABARZON) | Cavite | Carmona | Cabilang Baybay | 14.3177 | 121.0498 | U | 8144 | 2395 | 719 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040171 | FTAP Globe | 14.3204 | 121.0566 | 0.79 | Terrestrial Optical Fiber Drop | 0.76 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1479 | 2 | 479 | 1479 | 0506216052 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Rawis | 13.039 | 124.0309 | R | 1682 | 420 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 1.12 | Terrestrial Optical Fiber Drop | 0.76 | 6.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1480 | 2 | 480 | 1480 | 1705318030 | MIMAROPA Region | Palawan | Roxas | Barangay III | 10.3228 | 119.349 | U | 6360 | 1630 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 0.81 | Terrestrial Optical Fiber Drop | 0.76 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1481 | 2 | 481 | 1481 | 0304915015 | Region III (Central Luzon) | Nueva Ecija | Llanera | Plaridel | 15.6788 | 121.0161 | R | 4045 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01467-B07 | PTCI/MIDC | 15.6627 | 121.0175 | 0.98 | Terrestrial Optical Fiber Drop | 1.49 | 6.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1482 | 2 | 482 | 1482 | 0405623001 | Region IV-A (CALABARZON) | Quezon | Lucban | Abang | 14.117 | 121.5501 | R | 2291 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02140-C08 | PTCI/MIDC | 14.1164 | 121.5576 | 0.81 | Terrestrial Optical Fiber Drop | 0.94 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1483 | 2 | 483 | 1483 | 0405638006 | Region IV-A (CALABARZON) | Quezon | Real | Lubayat | 14.4992 | 121.6261 | R | 1709 | 449 | 135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040059 | FTAP Globe | 14.5404 | 121.5893 | 6.05 | Terrestrial Optical Fiber Drop | 0.76 | 19.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1484 | 2 | 484 | 1484 | 0501706026 | Region V (Bicol Region) | Camarines Sur | Bula | San Jose | 13.4738 | 123.2853 | R | 2557 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050116 | FTAP Globe | 13.4724 | 123.277 | 0.91 | Terrestrial Optical Fiber Drop | 0.76 | 4.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1485 | 2 | 485 | 1485 | 0301411002 | Region III (Central Luzon) | Bulacan | Marilao | Abangan Sur | 14.7639 | 120.9426 | U | 11075 | 3164 | 949 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0062 | PTCI/MIDC | 14.7657 | 120.9398 | 0.36 | Terrestrial Optical Fiber Drop | 0.76 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1486 | 2 | 486 | 1486 | 0405803005 | Region IV-A (CALABARZON) | Rizal | Baras | Santiago | 14.5215 | 121.2622 | R | 3964 | 1101 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01857 | Edgepoint | 14.5237 | 121.2629 | 0.25 | Terrestrial Optical Fiber Drop | 0.76 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1487 | 2 | 487 | 1487 | 1600206006 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Poblacion | 9.4546 | 125.5794 | R | 2474 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 4.64 | Terrestrial Optical Fiber Drop | 0.76 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1488 | 2 | 488 | 1488 | 1102509005 | Region XI (Davao Region) | Davao Oriental | City of Mati | Central | 6.9663 | 126.208 | U | 35778 | 9938 | 2981 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110506 | FTAP Globe | 6.9607 | 126.212 | 0.76 | Terrestrial Optical Fiber Drop | 0.77 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1489 | 2 | 489 | 1489 | 0731100019 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Pajo | 10.3109 | 123.9666 | U | 25856 | 7387 | 2216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0099 | PTCI/MIDC | 10.3117 | 123.9593 | 0.81 | Terrestrial Optical Fiber Drop | 0.76 | 3.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1490 | 2 | 490 | 1490 | 0402120004 | Region IV-A (CALABARZON) | Cavite | Tanza | Biwas | 14.3983 | 120.855 | U | 7357 | 2163 | 649 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040123 | FTAP Globe | 14.4014 | 120.8458 | 1.04 | Terrestrial Optical Fiber Drop | 0.76 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1491 | 2 | 491 | 1491 | 0205004020 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | San Antonio North | 16.3671 | 121.1059 | R | 2569 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01534-B05 | PTCI/MIDC | 16.3595 | 121.1042 | 0.86 | Terrestrial Optical Fiber Drop | 0.77 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1492 | 2 | 492 | 1492 | 1600209020 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Triangulo | 8.9734 | 125.3531 | U | 2916 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130068 | FTAP Globe | 8.9748 | 125.3618 | 0.96 | Terrestrial Optical Fiber Drop | 0.76 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1493 | 2 | 493 | 1493 | 1401106007 | Cordillera Administrative Region (CAR) | Benguet | Itogon | Tuding | 16.419 | 120.6406 | U | 10488 | 2996 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BEN-00334 | Edgepoint | 16.4152 | 120.6326 | 0.95 | Terrestrial Optical Fiber Drop | 0.77 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1494 | 2 | 494 | 1494 | 0203108031 | Region II (Cagayan Valley) | Isabela | City of Cauayan | District I | 16.9316 | 121.7715 | U | 11763 | 3095 | 929 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020076 | FTAP Globe | 16.9339 | 121.7741 | 0.38 | Terrestrial Optical Fiber Drop | 0.77 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1495 | 2 | 495 | 1495 | 0405806007 | Region IV-A (CALABARZON) | Rizal | Cardona | Calahan | 14.4908 | 121.2345 | U | 5775 | 1604 | 481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040081 | FTAP Globe | 14.4931 | 121.234 | 0.26 | Terrestrial Optical Fiber Drop | 0.77 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1496 | 2 | 496 | 1496 | 0401029006 | Region IV-A (CALABARZON) | Batangas | Taal | Butong | 13.8691 | 120.9152 | U | 5493 | 1525 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01950-C08 | PTCI/MIDC | 13.8765 | 120.9183 | 0.89 | Terrestrial Optical Fiber Drop | 0.77 | 3.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1497 | 2 | 497 | 1497 | 0501719005 | Region V (Bicol Region) | Camarines Sur | Lupi | Bel-Cruz | 13.7764 | 122.8615 | R | 1023 | 243 | 73 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03080 | Edgepoint | 122.867 | 13.7754 | 0.6 | Terrestrial Optical Fiber Drop | 0.77 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1498 | 2 | 498 | 1498 | 0604502013 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Lag-Asan | 10.525 | 122.8412 | U | 13466 | 3639 | 1092 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0081 | PTCI/MIDC | 10.5207 | 122.8433 | 0.53 | Terrestrial Optical Fiber Drop | 0.77 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1499 | 2 | 499 | 1499 | 0931700021 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Canelar | 6.9155 | 122.0691 | U | 10960 | 3044 | 913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0121 | PTCI/MIDC | 6.9159 | 122.0719 | 0.31 | Terrestrial Optical Fiber Drop | 0.77 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1500 | 2 | 500 | 1500 | 0403402011 | Region IV-A (CALABARZON) | Laguna | Bay | San Isidro | 14.1856 | 121.2858 | R | 3019 | 914 | 274 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02100-C08 | PTCI/MIDC | 14.1845 | 121.2822 | 0.4 | Terrestrial Optical Fiber Drop | 0.77 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1501 | 2 | 501 | 1501 | 0304924003 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Julo | 15.304 | 120.8644 | U | 5539 | 1582 | 475 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00769 | Edgepoint | 15.3045 | 120.8649 | 0.08 | Terrestrial Optical Fiber Drop | 0.77 | 2.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1502 | 2 | 502 | 1502 | 1430300099 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | San Vicente | 16.3951 | 120.5968 | U | 5346 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0013 | PTCI/MIDC | 16.3965 | 120.5968 | 0.15 | Terrestrial Optical Fiber Drop | 0.77 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1503 | 2 | 503 | 1503 | 0405646037 | Region IV-A (CALABARZON) | Quezon | Tagkawayan | Santa Cecilia | 13.9669 | 122.5354 | R | 3763 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B98 | FTAP Smart | 13.9663 | 122.5411 | 0.62 | Terrestrial Optical Fiber Drop | 0.77 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1504 | 2 | 504 | 1504 | 0201525003 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Centro East | 18.2529 | 121.9066 | R | 1890 | 484 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01129-B06 | PTCI/MIDC | 18.2464 | 121.9084 | 0.75 | Terrestrial Optical Fiber Drop | 0.77 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1505 | 2 | 505 | 1505 | 0203126020 | Region II (Cagayan Valley) | Isabela | Roxas | San Placido | 17.1212 | 121.62 | U | 3617 | 951 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00180 | Edgepoint | 17.1198 | 121.6225 | 0.31 | Terrestrial Optical Fiber Drop | 0.77 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1506 | 2 | 506 | 1506 | 0201522010 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Langagan | 18.5535 | 121.2414 | R | 2505 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0031 | LDIC | 121.2405 | 18.556 | 0.3 | Terrestrial Optical Fiber Drop | 0.77 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1507 | 2 | 507 | 1507 | 0403424009 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-E | 14.0642 | 121.3244 | U | 2355 | 713 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 1.01 | Terrestrial Optical Fiber Drop | 0.77 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1508 | 2 | 508 | 1508 | 0403419015 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sampaloc | 14.2696 | 121.4444 | U | 4667 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040208 | FTAP Globe | 14.2666 | 121.4429 | 0.37 | Terrestrial Optical Fiber Drop | 0.77 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1509 | 2 | 509 | 1509 | 0304922005 | Region III (Central Luzon) | Nueva Ecija | Quezon | Dulong Bayan | 15.5544 | 120.8141 | U | 4184 | 1101 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00659 | Edgepoint | 15.5563 | 120.8126 | 0.27 | Terrestrial Optical Fiber Drop | 0.78 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1510 | 2 | 510 | 1510 | 0402103070 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba VI | 14.4611 | 120.9603 | R | 2729 | 802 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000702 | FTAP Globe | 14.4246 | 121.0236 | 0.29 | Terrestrial Optical Fiber Drop | 0.48 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1511 | 2 | 511 | 1511 | 0506216030 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Sampaloc | 12.9711 | 124.0104 | R | 4685 | 1171 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 0.6 | Terrestrial Optical Fiber Drop | 0.77 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1512 | 2 | 512 | 1512 | 1001317028 | Region X (Northern Mindanao) | Bukidnon | Quezon | Poblacion | 7.7293 | 125.0979 | U | 15246 | 4012 | 1204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100058 | FTAP BTS | 7.7366 | 125.095 | 0.88 | Terrestrial Optical Fiber Drop | 0.78 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1513 | 2 | 513 | 1513 | 0501709008 | Region V (Bicol Region) | Camarines Sur | Camaligan | San Marcos | 13.6209 | 123.1657 | R | 1491 | 355 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.65 | Terrestrial Optical Fiber Drop | 0.69 | 1.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1514 | 2 | 514 | 1514 | 0306911007 | Region III (Central Luzon) | Tarlac | Pura | Matindeg | 15.6163 | 120.6527 | R | 1352 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00627 | Edgepoint | 15.6244 | 120.6492 | 0.98 | Terrestrial Optical Fiber Drop | 0.78 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1515 | 2 | 515 | 1515 | 0105503022 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Pocalpocal | 16.1601 | 119.9819 | R | 2800 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N6719 | FTAP Smart | 16.155 | 119.9806 | 0.53 | Terrestrial Optical Fiber Drop | 1 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1516 | 2 | 516 | 1516 | 0501705029 | Region V (Bicol Region) | Camarines Sur | Buhi | San Pascual | 13.416 | 123.514 | R | 1235 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050122 | FTAP Globe | 13.4303 | 123.5142 | 1.28 | Terrestrial Optical Fiber Drop | 0.02 | 10.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1517 | 2 | 517 | 1517 | 0402103024 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba I | 14.4612 | 120.96 | R | 1949 | 573 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040112 | FTAP Globe | 14.4161 | 120.9742 | 0.59 | Terrestrial Optical Fiber Drop | 0.48 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1518 | 2 | 518 | 1518 | 1102412020 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone III | 6.8377 | 125.4155 | U | 12562 | 3694 | 1108 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.17 | Terrestrial Optical Fiber Drop | 0.78 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1519 | 2 | 519 | 1519 | 0401021030 | Region IV-A (CALABARZON) | Batangas | Rosario | Pinagsibaan | 13.8397 | 121.3131 | R | 3648 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040548 | FTAP Globe | 13.8424 | 121.2877 | 2.76 | Terrestrial Optical Fiber Drop | 0.78 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1520 | 2 | 520 | 1520 | 1230800033 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Calumpang | 6.0785 | 125.141 | U | 90831 | 23290 | 6987 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH120330 | FTAP Globe | 6.0828 | 125.1436 | 0.56 | Terrestrial Optical Fiber Drop | 0.78 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1521 | 2 | 521 | 1521 | 1130700135 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 2-A | 7.0631 | 125.6076 | U | 3054 | 898 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0021 | PTCI/MIDC | 7.0614 | 125.6075 | 0.19 | Terrestrial Optical Fiber Drop | 0.78 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1522 | 2 | 522 | 1522 | 0401005075 | Region IV-A (CALABARZON) | Batangas | Batangas City | Barangay 6 | 13.7603 | 121.0637 | R | 1864 | 517 | 155 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01986-C08 | PTCI/MIDC | 13.7624 | 121.0631 | 0.24 | Terrestrial Optical Fiber Drop | 0.78 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1523 | 2 | 523 | 1523 | 0702251017 | Region VII (Central Visayas) | Cebu | City of Toledo | Dumlog | 10.3937 | 123.6525 | U | 6743 | 1774 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 0.82 | Terrestrial Optical Fiber Drop | 0.78 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1524 | 2 | 524 | 1524 | 0630200022 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 26 | 10.6661 | 122.9518 | R | 1467 | 407 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0006 | PTCI/MIDC | 10.6237 | 122.9796 | 0.72 | Terrestrial Optical Fiber Drop | 0.1 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1525 | 2 | 525 | 1525 | 0330100022 | Region III (Central Luzon) | Pampanga | City of Angeles | Salapungan | 15.148 | 120.5983 | U | 5533 | 1536 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.47 | Terrestrial Optical Fiber Drop | 0.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1526 | 2 | 526 | 1526 | 0702214014 | Region VII (Central Visayas) | Cebu | City of Carcar | Poblacion III | 10.1056 | 123.6439 | U | 7495 | 1972 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0023 | PTCI/MIDC | 10.1027 | 123.6533 | 1.08 | Terrestrial Optical Fiber Drop | 0.78 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1527 | 2 | 527 | 1527 | 0305410021 | Region III (Central Luzon) | Pampanga | Macabebe | Sto. Niño | 14.9072 | 120.6936 | R | 2785 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030557 | FTAP Globe | 14.8933 | 120.7033 | 0.64 | Terrestrial Optical Fiber Drop | 2.26 | 7.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1528 | 2 | 528 | 1528 | 0306910025 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Sur | 15.6647 | 120.5807 | U | 4922 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.74 | Terrestrial Optical Fiber Drop | 0.78 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1529 | 2 | 529 | 1529 | 0301420010 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Sapang Palay | 14.8388 | 121.0434 | U | 6067 | 1733 | 520 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02259 | Edgepoint | 14.8402 | 121.044 | 0.17 | Terrestrial Optical Fiber Drop | 0.78 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1530 | 2 | 530 | 1530 | 0301420037 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Minuyan II | 14.8447 | 121.0799 | U | 6248 | 1785 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02259 | Edgepoint | 14.8402 | 121.044 | 0.04 | Terrestrial Optical Fiber Drop | 0.38 | 5.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1531 | 2 | 531 | 1531 | 0304928010 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Rizal | 15.4214 | 120.9379 | U | 2270 | 648 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01493-B07 | PTCI/MIDC | 15.4207 | 120.9403 | 0.27 | Terrestrial Optical Fiber Drop | 0.4 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1532 | 2 | 532 | 1532 | 0401029008 | Region IV-A (CALABARZON) | Batangas | Taal | Cawit | 13.8915 | 120.9204 | R | 2563 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0004 | LDIC | 13.8858 | 120.9194 | 0.64 | Terrestrial Optical Fiber Drop | 0.78 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1533 | 2 | 533 | 1533 | 1400101002 | Cordillera Administrative Region (CAR) | Abra | Bangued | Angad | 17.5887 | 120.6252 | R | 2743 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ABR-03102 | Edgepoint | 120.6153 | 17.5944 | 1.23 | Terrestrial Optical Fiber Drop | 0.78 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1534 | 2 | 534 | 1534 | 0203132011 | Region II (Cagayan Valley) | Isabela | San Mateo | Marasat Grande | 16.881 | 121.5803 | R | 1632 | 429 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0019 | PTCI/MIDC | 16.8744 | 121.5803 | 0.46 | Terrestrial Optical Fiber Drop | 0.48 | 12.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1535 | 2 | 535 | 1535 | 0201512019 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay IV | 17.5552 | 121.6978 | R | 1229 | 315 | 95 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00113 | Edgepoint | 17.5573 | 121.6932 | 0.54 | Terrestrial Optical Fiber Drop | 0.79 | 1.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1536 | 2 | 536 | 1536 | 0402103032 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Aniban V | 14.4611 | 120.9645 | R | 2857 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02374-C08 | PTCI/MIDC | 14.4282 | 120.938 | 0.18 | Terrestrial Optical Fiber Drop | 0.52 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1537 | 2 | 537 | 1537 | 0403426022 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | San Pablo Sur | 14.2843 | 121.418 | R | 3508 | 1063 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0050 | PTCI/MIDC | 14.286 | 121.4191 | 0.22 | Terrestrial Optical Fiber Drop | 0.79 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1538 | 2 | 538 | 1538 | 0501732019 | Region V (Bicol Region) | Camarines Sur | San Fernando | Rizal | 13.5651 | 123.1458 | R | 1530 | 364 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 0.62 | Terrestrial Optical Fiber Drop | 0.79 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1539 | 2 | 539 | 1539 | 0105501011 | Region I (Ilocos Region) | Pangasinan | Agno | Magsaysay | 16.1168 | 119.8 | R | 1560 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010129 | FTAP Globe | 16.122 | 119.8094 | 1.16 | Terrestrial Optical Fiber Drop | 0.79 | 9.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1540 | 2 | 540 | 1540 | 0402120003 | Region IV-A (CALABARZON) | Cavite | Tanza | Biga | 14.3617 | 120.8563 | U | 17918 | 5270 | 1581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 0.36 | Terrestrial Optical Fiber Drop | 0.79 | 2.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1541 | 2 | 541 | 1541 | 0105504009 | Region I (Ilocos Region) | Pangasinan | Alcala | Kisikis | 15.8439 | 120.5357 | U | 3690 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00561 | Edgepoint | 15.8477 | 120.5232 | 1.32 | Terrestrial Optical Fiber Drop | 1.04 | 7.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1542 | 2 | 542 | 1542 | 0403429005 | Region IV-A (CALABARZON) | Laguna | Siniloan | Buhay | 14.4286 | 121.4486 | R | 1217 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040106 | FTAP Globe | 14.4246 | 121.4454 | 0.56 | Terrestrial Optical Fiber Drop | 0.79 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1543 | 2 | 543 | 1543 | 0402109076 | Region IV-A (CALABARZON) | Cavite | City of Imus | Medicion II-C | 14.4347 | 120.9309 | R | 1619 | 476 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02396-A03 | PTCI/MIDC | 14.4619 | 120.9719 | 0.66 | Terrestrial Optical Fiber Drop | 1.68 | 1.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1544 | 2 | 544 | 1544 | 0600407011 | Region VI (Western Visayas) | Aklan | Kalibo | Mobo | 11.6988 | 122.3599 | R | 1863 | 477 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 1.46 | Terrestrial Optical Fiber Drop | 0.79 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1545 | 2 | 545 | 1545 | 0300807019 | Region III (Central Luzon) | Bataan | Mariveles | Mt. View | 14.4501 | 120.5779 | U | 13666 | 3796 | 1139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1514 | FTAP Smart | 14.4519 | 120.5791 | 0.24 | Terrestrial Optical Fiber Drop | 0.79 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1546 | 2 | 546 | 1546 | 0103307014 | Region I (Ilocos Region) | La Union | Bauang | Central East | 16.5281 | 120.3336 | U | 4199 | 1134 | 340 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 0.34 | Terrestrial Optical Fiber Drop | 0.79 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1547 | 2 | 547 | 1547 | 0306910024 | Region III (Central Luzon) | Tarlac | Paniqui | Poblacion Norte | 15.6718 | 120.5808 | U | 9205 | 2360 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030335 | FTAP Globe | 15.6713 | 120.581 | 0.06 | Terrestrial Optical Fiber Drop | 0.79 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1548 | 2 | 548 | 1548 | 0330100019 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulung Maragul | 15.1586 | 120.6108 | U | 21592 | 5997 | 1799 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02481 | Edgepoint | 15.1613 | 120.6108 | 0.3 | Terrestrial Optical Fiber Drop | 0.79 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1549 | 2 | 549 | 1549 | 0105533018 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw Magliba | 16.1204 | 120.3934 | R | 1779 | 494 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00403 | Edgepoint | 16.1211 | 120.4056 | 1.3 | Terrestrial Optical Fiber Drop | 0.79 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1550 | 2 | 550 | 1550 | 0702210024 | Region VII (Central Visayas) | Cebu | Barili | Maghanoy | 10.1091 | 123.504 | R | 1456 | 383 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 1.25 | Terrestrial Optical Fiber Drop | 0.79 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1551 | 2 | 551 | 1551 | 1600301024 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Taglatawan | 8.7099 | 125.7503 | U | 12652 | 3244 | 973 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0003 | PTCI/MIDC | 8.7151 | 125.7419 | 1.09 | Terrestrial Optical Fiber Drop | 0.79 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1552 | 2 | 552 | 1552 | 0501716019 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Juan | 13.4226 | 123.423 | R | 4462 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03180 | Edgepoint | 13.428 | 123.4178 | 0.82 | Terrestrial Optical Fiber Drop | 0.79 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1553 | 2 | 553 | 1553 | 0506211006 | Region V (Bicol Region) | Sorsogon | Magallanes | Banacud | 12.8279 | 123.8359 | R | 1168 | 292 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050222 | FTAP Globe | 12.8197 | 123.842 | 1.12 | Terrestrial Optical Fiber Drop | 0.8 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1554 | 2 | 554 | 1554 | 0301413022 | Region III (Central Luzon) | Bulacan | Norzagaray | Poblacion | 14.9079 | 121.044 | U | 15956 | 4558 | 1367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030543 | FTAP Globe | 14.9106 | 121.0449 | 0.32 | Terrestrial Optical Fiber Drop | 0.79 | 6.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1555 | 2 | 555 | 1555 | 0403405054 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Jose | 14.2006 | 121.1406 | U | 4452 | 1349 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040256 | FTAP Globe | 14.1944 | 121.147 | 0.57 | Terrestrial Optical Fiber Drop | 0.71 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1556 | 2 | 556 | 1556 | 0402101014 | Region IV-A (CALABARZON) | Cavite | Alfonso | Pajo | 14.1437 | 120.8582 | R | 2316 | 681 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 0.27 | Terrestrial Optical Fiber Drop | 0.8 | 6.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1557 | 2 | 557 | 1557 | 1102411003 | Region XI (Davao Region) | Davao del Sur | Padada | Harada Butai | 6.6364 | 125.3369 | R | 2689 | 790 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110340 | FTAP BTS | 6.6431 | 125.3367 | 0.74 | Terrestrial Optical Fiber Drop | 0.79 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1558 | 2 | 558 | 1558 | 0305403009 | Region III (Central Luzon) | Pampanga | Arayat | Guemasan | 15.1476 | 120.7767 | R | 4424 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.71 | Terrestrial Optical Fiber Drop | 0.8 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1559 | 2 | 559 | 1559 | 0307103012 | Region III (Central Luzon) | Zambales | Candelaria | Panayonan | 15.6247 | 119.9364 | R | 1275 | 335 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03357-B07 | PTCI/MIDC | 15.6183 | 119.9418 | 0.53 | Terrestrial Optical Fiber Drop | 0.45 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1560 | 2 | 560 | 1560 | 0403413008 | Region IV-A (CALABARZON) | Laguna | Lumban | Maytalang I | 14.2889 | 121.4582 | U | 4369 | 1323 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.58 | Terrestrial Optical Fiber Drop | 0.8 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1561 | 2 | 561 | 1561 | 0402103043 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog IV | 14.423 | 120.9582 | U | 14599 | 4293 | 1288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00594-A03 | PTCI/MIDC | 14.4466 | 120.9981 | 0.57 | Terrestrial Optical Fiber Drop | 0.85 | 2.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1562 | 2 | 562 | 1562 | 0304916017 | Region III (Central Luzon) | Nueva Ecija | Lupao | Namulandayan | 15.8824 | 120.9049 | R | 2243 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01414-B07 | PTCI/MIDC | 15.8805 | 120.8984 | 0.73 | Terrestrial Optical Fiber Drop | 0.8 | 1.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1563 | 2 | 563 | 1563 | 0306914001 | Region III (Central Luzon) | Tarlac | San Manuel | Colubot | 15.7903 | 120.6041 | R | 1191 | 305 | 92 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00574 | Edgepoint | 15.7974 | 120.6132 | 1.25 | Terrestrial Optical Fiber Drop | 0.8 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1564 | 2 | 564 | 1564 | 0402115012 | Region IV-A (CALABARZON) | Cavite | Naic | Ibayo Estacion | 14.3233 | 120.7644 | U | 5324 | 1565 | 470 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02143-C08 | PTCI/MIDC | 14.3258 | 120.7645 | 0.28 | Terrestrial Optical Fiber Drop | 0.8 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1565 | 2 | 565 | 1565 | 1401110016 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Wangal | 16.403 | 120.6044 | U | 6933 | 1980 | 594 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0024 | LDIC | 16.4025 | 120.6048 | 0.07 | Terrestrial Optical Fiber Drop | 0.8 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1566 | 2 | 566 | 1566 | 0300811013 | Region III (Central Luzon) | Bataan | Pilar | Landing | 14.6698 | 120.5513 | R | 1375 | 381 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1519 | FTAP Smart | 14.6476 | 120.5385 | 0.59 | Terrestrial Optical Fiber Drop | 1.67 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1567 | 2 | 567 | 1567 | 1004313006 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Lumbo | 8.8075 | 124.7969 | R | 2878 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 0.91 | Terrestrial Optical Fiber Drop | 0.8 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1568 | 2 | 568 | 1568 | 0330100012 | Region III (Central Luzon) | Pampanga | City of Angeles | Lourdes Sur East | 15.1445 | 120.5936 | U | 3800 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3709 | FTAP Smart | 15.1453 | 120.5949 | 0.17 | Terrestrial Optical Fiber Drop | 0.81 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1569 | 2 | 569 | 1569 | 0600613001 | Region VI (Western Visayas) | Antique | San Jose | Atabay | 10.7569 | 121.9429 | U | 2287 | 586 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAQG0021 | PTCI/MIDC | 10.7615 | 121.9442 | 0.53 | Terrestrial Optical Fiber Drop | 0.81 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1570 | 2 | 570 | 1570 | 0402109006 | Region IV-A (CALABARZON) | Cavite | City of Imus | Poblacion I-A | 14.4269 | 120.9391 | R | 2052 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S3369 | FTAP Smart | 14.4253 | 120.9393 | 0.18 | Terrestrial Optical Fiber Drop | 0.8 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1571 | 2 | 571 | 1571 | 0102805035 | Region I (Ilocos Region) | Ilocos Norte | City of Batac | Quiling Norte | 18.0658 | 120.5516 | R | 1551 | 419 | 126 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01224-B05 | PTCI/MIDC | 18.0488 | 120.5532 | 0.13 | Terrestrial Optical Fiber Drop | 1.04 | 0.9 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1572 | 2 | 572 | 1572 | 0304923007 | Region III (Central Luzon) | Nueva Ecija | Rizal | Calaocan District | 15.7046 | 121.1077 | R | 3678 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 0.38 | Terrestrial Optical Fiber Drop | 0.81 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1573 | 2 | 573 | 1573 | 0301406003 | Region III (Central Luzon) | Bulacan | Bustos | Buisan | 14.9324 | 120.9281 | R | 1961 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-02275 | Edgepoint | 14.9411 | 120.9418 | 1.84 | Terrestrial Optical Fiber Drop | 1.26 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1574 | 2 | 574 | 1574 | 0403428007 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Ibaba | 14.3023 | 121.1097 | U | 8845 | 2680 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4294 | FTAP Smart | 14.2944 | 121.107 | 0.35 | Terrestrial Optical Fiber Drop | 0.64 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1575 | 2 | 575 | 1575 | 0702246021 | Region VII (Central Visayas) | Cebu | Sibonga | Poblacion | 10.0189 | 123.6146 | U | 7421 | 1952 | 586 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070018 | FTAP BTS | 10.0136 | 123.619 | 0.77 | Terrestrial Optical Fiber Drop | 0.81 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1576 | 2 | 576 | 1576 | 1430300007 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Balsigan | 16.407 | 120.5972 | R | 2506 | 659 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0008 | LDIC | 16.4071 | 120.5887 | 0.12 | Terrestrial Optical Fiber Drop | 0.55 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1577 | 2 | 577 | 1577 | 1004323006 | Region X (Northern Mindanao) | Misamis Oriental | Sugbongcogon | Mangga | 8.9606 | 124.7825 | R | 1552 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 0.94 | Terrestrial Optical Fiber Drop | 0.81 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1578 | 2 | 578 | 1578 | 0305415010 | Region III (Central Luzon) | Pampanga | Porac | Cangatba | 15.0682 | 120.5429 | U | 3116 | 779 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.28 | Terrestrial Optical Fiber Drop | 0.46 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1579 | 2 | 579 | 1579 | 0105512021 | Region I (Ilocos Region) | Pangasinan | Binalonan | Sta. Maria Norte | 16.0613 | 120.5879 | U | 2783 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02466-B07 | PTCI/MIDC | 16.0505 | 120.5941 | 0.65 | Terrestrial Optical Fiber Drop | 1.91 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1580 | 2 | 580 | 1580 | 0403428009 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Macabling | 14.2986 | 121.0975 | U | 22368 | 6778 | 2033 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0027 | PTCI/MIDC | 14.3001 | 121.0996 | 0.28 | Terrestrial Optical Fiber Drop | 0.81 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1581 | 2 | 581 | 1581 | 0403418001 | Region IV-A (CALABARZON) | Laguna | Paete | Bagumbayan | 14.3661 | 121.482 | U | 6032 | 1827 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040142 | FTAP Globe | 14.3685 | 121.4793 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1582 | 2 | 582 | 1582 | 0501736013 | Region V (Bicol Region) | Camarines Sur | Tigaon | May-Anao | 13.6248 | 123.5024 | R | 3326 | 791 | 237 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 1.25 | Terrestrial Optical Fiber Drop | 0.81 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1583 | 2 | 583 | 1583 | 0304928002 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | La Fuente | 15.4297 | 120.9259 | R | 3386 | 967 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0006 | PTCI/MIDC | 15.4304 | 120.9236 | 0.26 | Terrestrial Optical Fiber Drop | 0.03 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1584 | 2 | 584 | 1584 | 0102908015 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | San Juan | 16.9837 | 120.7196 | R | 2189 | 576 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010067 | FTAP Globe | 16.982 | 120.7044 | 1.62 | Terrestrial Optical Fiber Drop | 0.81 | 1.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1585 | 2 | 585 | 1585 | 1030900048 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Villa Verde | 8.2345 | 124.2446 | U | 5590 | 1471 | 441 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0009 | PTCI/MIDC | 8.2328 | 124.2427 | 0.28 | Terrestrial Optical Fiber Drop | 0.82 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1586 | 2 | 586 | 1586 | 1403213015 | Cordillera Administrative Region (CAR) | Kalinga | City of Tabuk | Gobgob | 17.469 | 121.4314 | R | 2123 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00127 | Edgepoint | 17.4695 | 121.4577 | 2.8 | Terrestrial Optical Fiber Drop | 0.82 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1587 | 2 | 587 | 1587 | 0102908004 | Region I (Ilocos Region) | Ilocos Sur | Cervantes | Concepcion | 16.9834 | 120.7197 | R | 2080 | 547 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010067 | FTAP Globe | 16.982 | 120.7044 | 1.63 | Terrestrial Optical Fiber Drop | 0.81 | 1.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1588 | 2 | 588 | 1588 | 0730600050 | Region VII (Central Visayas) | Cebu | City of Cebu | Pahina Central | 10.2976 | 123.8924 | U | 5646 | 1764 | 529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0119 | PTCI/MIDC | 10.2993 | 123.8942 | 0.28 | Terrestrial Optical Fiber Drop | 0.81 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1589 | 2 | 589 | 1589 | 0102812068 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 5, San Pedro | 18.2037 | 120.5927 | R | 1404 | 379 | 114 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00029 | Edgepoint | 18.2009 | 120.5898 | 0.44 | Terrestrial Optical Fiber Drop | 0.81 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1590 | 2 | 590 | 1590 | 0603006008 | Region VI (Western Visayas) | Iloilo | Banate | Bularan | 11.0042 | 122.822 | R | 1084 | 285 | 86 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02851-D13 | PTCI/MIDC | 10.9969 | 122.7958 | 2.97 | Terrestrial Optical Fiber Drop | 0.82 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1591 | 2 | 591 | 1591 | 0403413003 | Region IV-A (CALABARZON) | Laguna | Lumban | Balubad | 14.2885 | 121.463 | R | 2336 | 707 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.37 | Terrestrial Optical Fiber Drop | 0.82 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1592 | 2 | 592 | 1592 | 0401018009 | Region IV-A (CALABARZON) | Batangas | Mataasnakahoy | Calingatan | 13.9616 | 121.1212 | R | 3220 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01964-C08 | PTCI/MIDC | 13.9582 | 121.119 | 0.45 | Terrestrial Optical Fiber Drop | 0.82 | 2.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1593 | 2 | 593 | 1593 | 0306903021 | Region III (Central Luzon) | Tarlac | Camiling | Cayaoan | 15.6965 | 120.4149 | R | 2360 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.45 | Terrestrial Optical Fiber Drop | 0.82 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1594 | 2 | 594 | 1594 | 1102319024 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo North | 7.4653 | 125.8138 | U | 8739 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110338 | FTAP BTS | 7.4641 | 125.8151 | 0.2 | Terrestrial Optical Fiber Drop | 0.82 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1595 | 2 | 595 | 1595 | 0702207004 | Region VII (Central Visayas) | Cebu | Badian | Basak | 10.29 | 123.8659 | R | 1743 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070008 | FTAP BTS | 10.2831 | 123.8687 | 0.82 | Terrestrial Optical Fiber Drop | 0.82 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1596 | 2 | 596 | 1596 | 0300810004 | Region III (Central Luzon) | Bataan | Orion | Balut | 14.6183 | 120.5772 | R | 1461 | 405 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 0.16 | Terrestrial Optical Fiber Drop | 0.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1597 | 2 | 597 | 1597 | 0501737039 | Region V (Bicol Region) | Camarines Sur | Tinambac | Santa Cruz | 13.8129 | 123.3319 | R | 3827 | 911 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-01993 | Edgepoint | 123.3311 | 13.8166 | 0.42 | Terrestrial Optical Fiber Drop | 0.82 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1598 | 2 | 598 | 1598 | 0501732006 | Region V (Bicol Region) | Camarines Sur | San Fernando | Buenavista | 13.5654 | 123.1459 | R | 1561 | 371 | 111 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050105 | FTAP Globe | 13.56 | 123.1434 | 0.67 | Terrestrial Optical Fiber Drop | 0.82 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1599 | 2 | 599 | 1599 | 0701230029 | Region VII (Central Visayas) | Bohol | Loon | Catagbacan Handig | 9.8227 | 123.8109 | R | 1098 | 274 | 82 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 1.71 | Terrestrial Optical Fiber Drop | 2.41 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1600 | 2 | 600 | 1600 | 0103307016 | Region I (Ilocos Region) | La Union | Bauang | Dili | 16.528 | 120.334 | R | 2249 | 607 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3684 | FTAP Smart | 16.5272 | 120.3305 | 0.38 | Terrestrial Optical Fiber Drop | 0.84 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1601 | 2 | 601 | 1601 | 0600415003 | Region VI (Western Visayas) | Aklan | New Washington | Dumaguit | 11.6008 | 122.4811 | R | 2275 | 583 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-AKL-03154 | Edgepoint | 11.6211 | 122.4683 | 3.98 | Terrestrial Optical Fiber Drop | 7.3 | 5.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1602 | 2 | 602 | 1602 | 0401009021 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 7 | 13.9056 | 121.0483 | U | 2231 | 619 | 186 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1603 | 2 | 603 | 1603 | 0105530026 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Poblacion I | 16.1128 | 120.5451 | U | 2203 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 0.75 | Terrestrial Optical Fiber Drop | 0.47 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1604 | 2 | 604 | 1604 | 0402109043 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma IV | 14.4073 | 120.9358 | U | 2851 | 838 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040129 | FTAP Globe | 14.3884 | 120.9771 | 0.32 | Terrestrial Optical Fiber Drop | 0.52 | 4.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1605 | 2 | 605 | 1605 | 0300804014 | Region III (Central Luzon) | Bataan | Dinalupihan | Kataasan | 14.8713 | 120.4628 | R | 3219 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030571 | FTAP Globe | 14.8719 | 120.4652 | 0.26 | Terrestrial Optical Fiber Drop | 0.82 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1606 | 2 | 606 | 1606 | 1630400054 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Libertad | 8.9485 | 125.5076 | U | 26152 | 6378 | 1913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130044 | FTAP BTS | 8.9443 | 125.5078 | 0.47 | Terrestrial Optical Fiber Drop | 0.82 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1607 | 2 | 607 | 1607 | 1903617010 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Beyaba-Damag | 8.0032 | 124.2857 | R | 2789 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH150100 | FTAP Globe | 7.9922 | 124.265 | 1.4 | Terrestrial Optical Fiber Drop | 1.47 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1608 | 2 | 608 | 1608 | 0331400001 | Region III (Central Luzon) | Zambales | City of Olongapo | Asinan | 14.8285 | 120.2864 | U | 3546 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01156 | Edgepoint | 14.8305 | 120.288 | 0.28 | Terrestrial Optical Fiber Drop | 0.82 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1609 | 2 | 609 | 1609 | 1430300022 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | City Camp Central | 16.4076 | 120.5971 | R | 1732 | 455 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH140183 | FTAP Globe | 16.4206 | 120.5975 | 0.19 | Terrestrial Optical Fiber Drop | 0.62 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1610 | 2 | 610 | 1610 | 0306916048 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maliwalo | 15.4821 | 120.6195 | U | 16799 | 4307 | 1292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00708 | Edgepoint | 15.4836 | 120.623 | 0.4 | Terrestrial Optical Fiber Drop | 0.82 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1611 | 2 | 611 | 1611 | 0305409008 | Region III (Central Luzon) | Pampanga | Mabalacat City | Dau | 15.182 | 120.5854 | U | 66184 | 16546 | 4964 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02294 | Edgepoint | 15.1821 | 120.5833 | 0.23 | Terrestrial Optical Fiber Drop | 0.83 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1612 | 2 | 612 | 1612 | 1130700116 | Region XI (Davao Region) | Davao del Sur | City of Davao | Talomo | 7.0494 | 125.5463 | U | 64198 | 18881 | 5664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSR0013 | PTCI/MIDC | 7.0507 | 125.541 | 0.6 | Terrestrial Optical Fiber Drop | 0.83 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1613 | 2 | 613 | 1613 | 0504112020 | Region V (Bicol Region) | Masbate | Milagros | Poblacion West | 12.2186 | 123.5021 | R | 4014 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050248 | FTAP Globe | 12.2182 | 123.5128 | 1.16 | Terrestrial Optical Fiber Drop | 0.82 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1614 | 2 | 614 | 1614 | 0301410020 | Region III (Central Luzon) | Bulacan | City of Malolos | Caniogan | 14.8462 | 120.817 | U | 5455 | 1558 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0051 | PTCI/MIDC | 14.8438 | 120.8198 | 0.4 | Terrestrial Optical Fiber Drop | 0.83 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1615 | 2 | 615 | 1615 | 0730600083 | Region VII (Central Visayas) | Cebu | City of Cebu | Tejero | 10.3007 | 123.9066 | U | 14101 | 4406 | 1322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCER0033 | PTCI/MIDC | 10.303 | 123.8978 | 1 | Terrestrial Optical Fiber Drop | 0.82 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1616 | 2 | 616 | 1616 | 0908302023 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Bliss | 7.737 | 123.0571 | R | 3169 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.52 | Terrestrial Optical Fiber Drop | 0.83 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1617 | 2 | 617 | 1617 | 0301410045 | Region III (Central Luzon) | Bulacan | City of Malolos | San Vicente | 14.8421 | 120.826 | U | 2511 | 717 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBUG0051 | PTCI/MIDC | 14.8438 | 120.8198 | 0.46 | Terrestrial Optical Fiber Drop | 1.49 | 0.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1618 | 2 | 618 | 1618 | 0306903036 | Region III (Central Luzon) | Tarlac | Camiling | Palimbo Caarosipan | 15.6907 | 120.4076 | R | 3626 | 929 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_TAR_0001 | LDIC | 15.6933 | 120.4118 | 0.54 | Terrestrial Optical Fiber Drop | 0.83 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1619 | 2 | 619 | 1619 | 1401110011 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Pico | 16.4409 | 120.5841 | U | 26490 | 7568 | 2270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0012 | PTCI/MIDC | 16.4413 | 120.5819 | 0.24 | Terrestrial Optical Fiber Drop | 0.83 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1620 | 2 | 620 | 1620 | 0301415005 | Region III (Central Luzon) | Bulacan | Pandi | Bunsuran II | 14.8625 | 120.9362 | U | 3816 | 1090 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00982-B07 | PTCI/MIDC | 14.8912 | 120.9541 | 1.13 | Terrestrial Optical Fiber Drop | 2.31 | 2.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1621 | 2 | 621 | 1621 | 0306916007 | Region III (Central Luzon) | Tarlac | City of Tarlac | Atioc | 15.4245 | 120.5816 | R | 2670 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.36 | Terrestrial Optical Fiber Drop | 2.02 | 1.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1622 | 2 | 622 | 1622 | 0803740036 | Region VIII (Eastern Visayas) | Leyte | Palompon | San Isidro | 11.0589 | 124.3843 | U | 3841 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0036 | PTCI/MIDC | 11.1106 | 124.4434 | 8.63 | Terrestrial Optical Fiber Drop | 0.83 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1623 | 2 | 623 | 1623 | 0301409015 | Region III (Central Luzon) | Bulacan | Hagonoy | San Pablo | 14.8318 | 120.7516 | U | 3627 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02944-B07 | PTCI/MIDC | 14.8395 | 120.7514 | 0.85 | Terrestrial Optical Fiber Drop | 0.83 | 3.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1624 | 2 | 624 | 1624 | 0402121006 | Region IV-A (CALABARZON) | Cavite | Ternate | San Jose | 14.2906 | 120.717 | R | 2061 | 606 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.75 | Terrestrial Optical Fiber Drop | 0.83 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1625 | 2 | 625 | 1625 | 0603032022 | Region VI (Western Visayas) | Iloilo | New Lucena | Poblacion | 10.8754 | 122.5913 | R | 3184 | 837 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0055 | PTCI/MIDC | 10.8752 | 122.598 | 0.74 | Terrestrial Optical Fiber Drop | 0.83 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1626 | 2 | 626 | 1626 | 0307114013 | Region III (Central Luzon) | Zambales | Subic | Ilwas | 14.8821 | 120.2349 | R | 3097 | 815 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-01065 | Edgepoint | 14.8869 | 120.2347 | 0.54 | Terrestrial Optical Fiber Drop | 0.83 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1627 | 2 | 627 | 1627 | 0405607073 | Region IV-A (CALABARZON) | Quezon | Calauag | Santa Maria | 13.9572 | 122.2948 | U | 6195 | 1630 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | B42 | FTAP Smart | 13.9539 | 122.3 | 0.67 | Terrestrial Optical Fiber Drop | 0.83 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1628 | 2 | 628 | 1628 | 0300806014 | Region III (Central Luzon) | Bataan | Limay | San Francisco de Asis | 14.5686 | 120.5955 | U | 6571 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030629 | FTAP Globe | 14.568 | 120.5957 | 0.08 | Terrestrial Optical Fiber Drop | 0.83 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1629 | 2 | 629 | 1629 | 0730600038 | Region VII (Central Visayas) | Cebu | City of Cebu | Kinasang-an Pardo | 10.2786 | 123.8563 | U | 18779 | 5868 | 1760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.66 | Terrestrial Optical Fiber Drop | 0.84 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1630 | 2 | 630 | 1630 | 1705209006 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Cacawan | 13.0452 | 121.4824 | U | 6819 | 1748 | 524 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMRG0011 | PTCI/MIDC | 13.0381 | 121.4907 | 1.2 | Terrestrial Optical Fiber Drop | 0.83 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1631 | 2 | 631 | 1631 | 1130700193 | Region XI (Davao Region) | Davao del Sur | City of Davao | Santo Niño | 7.0806 | 125.5056 | U | 21782 | 6406 | 1922 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110484 | FTAP Globe | 7.0774 | 125.5149 | 1.08 | Terrestrial Optical Fiber Drop | 0.84 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1632 | 2 | 632 | 1632 | 0405804003 | Region IV-A (CALABARZON) | Rizal | Binangonan | Bilibiran | 14.4995 | 121.1736 | U | 17784 | 4940 | 1482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0136 | PTCI/MIDC | 14.4981 | 121.1739 | 0.15 | Terrestrial Optical Fiber Drop | 0.84 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1633 | 2 | 633 | 1633 | 0403422016 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Norte | 14.2338 | 121.3662 | R | 2742 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 1.1 | Terrestrial Optical Fiber Drop | 0.36 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1634 | 2 | 634 | 1634 | 0105546036 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Santo Domingo | 15.959 | 120.5666 | U | 3639 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01735-B07 | PTCI/MIDC | 15.956 | 120.5666 | 0.33 | Terrestrial Optical Fiber Drop | 0.83 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1635 | 2 | 635 | 1635 | 0401012005 | Region IV-A (CALABARZON) | Batangas | Lemery | Bagong Sikat | 13.8832 | 120.9153 | R | 1354 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0004 | LDIC | 13.8858 | 120.9194 | 0.53 | Terrestrial Optical Fiber Drop | 0.84 | 1.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1636 | 2 | 636 | 1636 | 0331400011 | Region III (Central Luzon) | Zambales | City of Olongapo | Kalaklan | 14.8301 | 120.273 | U | 14962 | 4043 | 1213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01827-B07 | PTCI/MIDC | 14.8308 | 120.2801 | 0.77 | Terrestrial Optical Fiber Drop | 0.84 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1637 | 2 | 637 | 1637 | 0401004008 | Region IV-A (CALABARZON) | Batangas | Balete | Palsara | 14.0111 | 121.1001 | R | 1473 | 409 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040370 | FTAP Globe | 14.0277 | 121.097 | 1.87 | Terrestrial Optical Fiber Drop | 0.84 | 6.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1638 | 2 | 638 | 1638 | 0401027010 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Poblacion I | 13.8688 | 120.979 | R | 1780 | 494 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040533 | FTAP Globe | 13.8691 | 120.9761 | 0.75 | Terrestrial Optical Fiber Drop | 1.34 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1639 | 2 | 639 | 1639 | 0304902007 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Digmala | 15.6252 | 121.1543 | R | 1683 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 1.04 | Terrestrial Optical Fiber Drop | 0.84 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1640 | 2 | 640 | 1640 | 0501720002 | Region V (Bicol Region) | Camarines Sur | Magarao | Bell | 13.6605 | 123.175 | R | 2490 | 592 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 1.29 | Terrestrial Optical Fiber Drop | 0.84 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1641 | 2 | 641 | 1641 | 0203132012 | Region II (Cagayan Valley) | Isabela | San Mateo | Marasat Pequeño | 16.9056 | 121.6153 | R | 2302 | 605 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01370-B06 | PTCI/MIDC | 16.8794 | 121.5907 | 0.36 | Terrestrial Optical Fiber Drop | 4.14 | 7.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1642 | 2 | 642 | 1642 | 0103309002 | Region I (Ilocos Region) | La Union | Caba | Gana | 16.4364 | 120.3601 | R | 2255 | 609 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LU_0033 | LDIC | 16.4309 | 120.358 | 0.42 | Terrestrial Optical Fiber Drop | 1.6 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1643 | 2 | 643 | 1643 | 0831600094 | Region VIII (Eastern Visayas) | Leyte | City of Tacloban | Barangay 64 | 11.216 | 125.0026 | R | 2198 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0099 | PTCI/MIDC | 11.2145 | 124.9956 | 0.78 | Terrestrial Optical Fiber Drop | 0.84 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1644 | 2 | 644 | 1644 | 0102822004 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Barcelona | 18.1061 | 120.7675 | R | 1426 | 385 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01220-B05 | PTCI/MIDC | 18.0958 | 120.7728 | 1.28 | Terrestrial Optical Fiber Drop | 0.84 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1645 | 2 | 645 | 1645 | 0305411008 | Region III (Central Luzon) | Pampanga | Magalang | San Franciso | 15.2062 | 120.6488 | U | 5250 | 1312 | 394 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02259-B07 | PTCI/MIDC | 15.2013 | 120.6406 | 1.03 | Terrestrial Optical Fiber Drop | 0.84 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1646 | 2 | 646 | 1646 | 0603036017 | Region VI (Western Visayas) | Iloilo | Pavia | Tigum | 10.7806 | 122.5481 | R | 2646 | 696 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.21 | Terrestrial Optical Fiber Drop | 0.84 | 3.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1647 | 2 | 647 | 1647 | 0300802016 | Region III (Central Luzon) | Bataan | Bagac | Atilano L. Ricardo | 14.606 | 120.4058 | R | 3467 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 3934 | FTAP Smart | 14.6029 | 120.3972 | 0.99 | Terrestrial Optical Fiber Drop | 0.84 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1648 | 2 | 648 | 1648 | 0501707005 | Region V (Bicol Region) | Camarines Sur | Cabusao | Castillo | 13.7334 | 123.115 | U | 5092 | 1212 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050057 | FTAP Globe | 13.7244 | 123.1076 | 1.29 | Terrestrial Optical Fiber Drop | 0.85 | 10.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1649 | 2 | 649 | 1649 | 0401009015 | Region IV-A (CALABARZON) | Batangas | Cuenca | Barangay 1 | 13.8988 | 121.0493 | R | 2058 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.92 | Terrestrial Optical Fiber Drop | 0.06 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1650 | 2 | 650 | 1650 | 1001312053 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Barangay 10 | 8.1517 | 125.1236 | U | 3857 | 1015 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0056 | PTCI/MIDC | 8.1403 | 125.1175 | 1.44 | Terrestrial Optical Fiber Drop | 0.84 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1651 | 2 | 651 | 1651 | 0307701006 | Region III (Central Luzon) | Aurora | Baler | Buhangin | 15.7666 | 121.5584 | U | 4430 | 1165 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03289-B06 | PTCI/MIDC | 15.7633 | 121.5658 | 0.87 | Terrestrial Optical Fiber Drop | 0.85 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1652 | 2 | 652 | 1652 | 0702219012 | Region VII (Central Visayas) | Cebu | Consolacion | Pitogo | 10.3794 | 123.9659 | U | 4392 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00111-D12 | PTCI/MIDC | 10.3742 | 123.9666 | 0.58 | Terrestrial Optical Fiber Drop | 0.85 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1653 | 2 | 653 | 1653 | 0501701025 | Region V (Bicol Region) | Camarines Sur | Baao | Santa Cruz | 13.453 | 123.3721 | R | 2954 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050118 | FTAP Globe | 13.4568 | 123.3687 | 0.56 | Terrestrial Optical Fiber Drop | 0.85 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1654 | 2 | 654 | 1654 | 0501603028 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay V | 14.1212 | 122.9497 | U | 4639 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0003 | PTCI/MIDC | 14.1236 | 122.9559 | 0.72 | Terrestrial Optical Fiber Drop | 0.85 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1655 | 2 | 655 | 1655 | 0402120028 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya II | 14.3832 | 120.8335 | U | 13139 | 3864 | 1159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040145 | FTAP Globe | 14.3624 | 120.8531 | 1.19 | Terrestrial Optical Fiber Drop | 1.86 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1656 | 2 | 656 | 1656 | 0402107004 | Region IV-A (CALABARZON) | Cavite | General Emilio Aguinaldo | Castaños Lejos | 14.1817 | 120.7995 | U | 2901 | 853 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02243-C08 | PTCI/MIDC | 14.1843 | 120.798 | 0.92 | Terrestrial Optical Fiber Drop | 0.4 | 4.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1657 | 2 | 657 | 1657 | 0402116005 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan I | 14.4376 | 120.8853 | R | 3130 | 920 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02739-C08 | PTCI/MIDC | 14.4354 | 120.8825 | 0.56 | Terrestrial Optical Fiber Drop | 0.93 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1658 | 2 | 658 | 1658 | 0105545018 | Region I (Ilocos Region) | Pangasinan | Urbiztondo | Poblacion | 15.8229 | 120.329 | U | 5276 | 1465 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010217 | FTAP Globe | 15.8239 | 120.3269 | 0.25 | Terrestrial Optical Fiber Drop | 0.85 | 11.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1659 | 2 | 659 | 1659 | 1001321001 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Bagontaas | 7.946 | 125.1027 | U | 14291 | 3760 | 1128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100202 | FTAP Globe | 7.9439 | 125.1039 | 0.27 | Terrestrial Optical Fiber Drop | 0.85 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1660 | 2 | 660 | 1660 | 1903617066 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Basak Malutlut | 8.0026 | 124.2723 | R | 3981 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH150100 | FTAP Globe | 7.9922 | 124.265 | 1.41 | Terrestrial Optical Fiber Drop | 0.85 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1661 | 2 | 661 | 1661 | 0501709002 | Region V (Bicol Region) | Camarines Sur | Camaligan | Marupit | 13.627 | 123.1688 | U | 5025 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050086 | FTAP Globe | 13.6208 | 123.1708 | 0.72 | Terrestrial Optical Fiber Drop | 0.85 | 2.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1662 | 2 | 662 | 1662 | 1430300097 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | San Luis Village | 16.4057 | 120.5768 | U | 9032 | 2376 | 713 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0027 | PTCI/MIDC | 16.4083 | 120.5779 | 0.31 | Terrestrial Optical Fiber Drop | 0.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1663 | 2 | 663 | 1663 | 0105533020 | Region I (Ilocos Region) | Pangasinan | San Fabian | Poblacion | 16.123 | 120.4022 | U | 3941 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00403 | Edgepoint | 16.1211 | 120.4056 | 0.42 | Terrestrial Optical Fiber Drop | 0.85 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1664 | 2 | 664 | 1664 | 0702247003 | Region VII (Central Visayas) | Cebu | Sogod | Bagatayam | 10.7596 | 124.0037 | R | 2902 | 763 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 0.83 | Terrestrial Optical Fiber Drop | 0.86 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1665 | 2 | 665 | 1665 | 0301420019 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Assumption | 14.8222 | 121.0581 | R | 4559 | 1302 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-03221 | Edgepoint | 14.8111 | 121.0649 | 0.86 | Terrestrial Optical Fiber Drop | 1.67 | 3.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1666 | 2 | 666 | 1666 | 0405620030 | Region IV-A (CALABARZON) | Quezon | Infanta | Miswa | 14.7376 | 121.6547 | R | 2193 | 577 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040007 | FTAP Globe | 14.747 | 121.648 | 1.44 | Satellite LEO Backhaul (Starlink Business) | 1.11 | 40.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1667 | 2 | 667 | 1667 | 0402112013 | Region IV-A (CALABARZON) | Cavite | Magallanes | Urdaneta | 14.165 | 120.7323 | R | 2342 | 688 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02186-C08 | PTCI/MIDC | 14.1641 | 120.7306 | 0.22 | Terrestrial Optical Fiber Drop | 0.85 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1668 | 2 | 668 | 1668 | 1004311007 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Lower Jasaan | 8.6571 | 124.7537 | U | 6140 | 1574 | 472 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.33 | Terrestrial Optical Fiber Drop | 0.82 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1669 | 2 | 669 | 1669 | 0401005112 | Region IV-A (CALABARZON) | Batangas | Batangas City | Talumpok Kanluran | 13.7337 | 121.1364 | R | 2986 | 829 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040586 | FTAP Globe | 13.7453 | 121.1393 | 1.32 | Terrestrial Optical Fiber Drop | 0.86 | 7.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1670 | 2 | 670 | 1670 | 1130700161 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 28-C | 7.0868 | 125.6132 | U | 3260 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0136 | PTCI/MIDC | 7.0708 | 125.621 | 0.27 | Terrestrial Optical Fiber Drop | 1.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1671 | 2 | 671 | 1671 | 0403428004 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dila | 14.2895 | 121.1091 | U | 43294 | 13119 | 3936 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S4294 | FTAP Smart | 14.2944 | 121.107 | 0.59 | Terrestrial Optical Fiber Drop | 0.85 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1672 | 2 | 672 | 1672 | 0403409003 | Region IV-A (CALABARZON) | Laguna | Kalayaan | San Juan | 14.3248 | 121.4766 | U | 7303 | 2213 | 664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040168 | FTAP Globe | 14.3245 | 121.4782 | 0.17 | Terrestrial Optical Fiber Drop | 0.86 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1673 | 2 | 673 | 1673 | 0806407064 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Tunga-tunga | 10.1314 | 124.8369 | U | 1975 | 481 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 1.07 | Terrestrial Optical Fiber Drop | 0.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1674 | 2 | 674 | 1674 | 0401029045 | Region IV-A (CALABARZON) | Batangas | Taal | Laguile | 13.8975 | 120.9164 | R | 3320 | 922 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01943-C08 | PTCI/MIDC | 13.8964 | 120.9122 | 0.47 | Terrestrial Optical Fiber Drop | 0.85 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1675 | 2 | 675 | 1675 | 0203126011 | Region II (Cagayan Valley) | Isabela | Roxas | Rizal | 17.1225 | 121.6194 | U | 6490 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0045 | PTCI/MIDC | 17.1242 | 121.6215 | 0.28 | Terrestrial Optical Fiber Drop | 0.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1676 | 2 | 676 | 1676 | 1401111010 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Poblacion | 16.8599 | 120.7904 | R | 2256 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 0.39 | Terrestrial Optical Fiber Drop | 0.86 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1677 | 2 | 677 | 1677 | 0401011017 | Region IV-A (CALABARZON) | Batangas | Laurel | Barangay 2 | 14.0551 | 120.9313 | R | 1705 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040354 | FTAP Globe | 14.0565 | 120.93 | 0.77 | Terrestrial Optical Fiber Drop | 0.33 | 4.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1678 | 2 | 678 | 1678 | 0402106024 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Saint Peter I | 14.3199 | 120.9565 | R | 2408 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0021 | PTCI/MIDC | 14.2975 | 120.9622 | 0.55 | Terrestrial Optical Fiber Drop | 1.29 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1679 | 2 | 679 | 1679 | 0403426024 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Santo Angel Central | 14.2854 | 121.4084 | R | 5029 | 1523 | 457 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040197 | FTAP Globe | 14.2831 | 121.4139 | 0.64 | Terrestrial Optical Fiber Drop | 0.86 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1680 | 2 | 680 | 1680 | 0603031021 | Region VI (Western Visayas) | Iloilo | Mina | Tolarucan | 10.9333 | 122.5674 | R | 1977 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 1.48 | Terrestrial Optical Fiber Drop | 0.86 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1681 | 2 | 681 | 1681 | 0506205007 | Region V (Bicol Region) | Sorsogon | Casiguran | Colambis | 12.8756 | 124.0212 | R | 1350 | 337 | 101 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 1.45 | Terrestrial Optical Fiber Drop | 0.86 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1682 | 2 | 682 | 1682 | 0402120021 | Region IV-A (CALABARZON) | Cavite | Tanza | Sahud Ulan | 14.3776 | 120.8246 | U | 23343 | 6865 | 2060 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040136 | FTAP Globe | 14.3739 | 120.827 | 0.49 | Terrestrial Optical Fiber Drop | 0.87 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1683 | 2 | 683 | 1683 | 0402103075 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Zapote V | 14.4688 | 120.9656 | U | 20125 | 5919 | 1776 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00135-A03 | PTCI/MIDC | 14.4672 | 120.9652 | 0.18 | Terrestrial Optical Fiber Drop | 0.86 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1684 | 2 | 684 | 1684 | 0301417012 | Region III (Central Luzon) | Bulacan | Plaridel | Lumang Bayan | 14.8954 | 120.8544 | U | 5863 | 1675 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02950-B07 | PTCI/MIDC | 14.8952 | 120.852 | 0.26 | Terrestrial Optical Fiber Drop | 0.86 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1685 | 2 | 685 | 1685 | 0506207050 | Region V (Bicol Region) | Sorsogon | Donsol | Tupas | 12.9128 | 123.594 | R | 2017 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050213 | FTAP Globe | 12.9091 | 123.5966 | 0.5 | Terrestrial Optical Fiber Drop | 0.87 | 17.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1686 | 2 | 686 | 1686 | 0402109035 | Region IV-A (CALABARZON) | Cavite | City of Imus | Anabu II-B | 14.4049 | 120.9264 | U | 8053 | 2368 | 710 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1120 | FTAP Smart | 14.4377 | 120.9409 | 0.23 | Terrestrial Optical Fiber Drop | 1.55 | 4.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1687 | 2 | 687 | 1687 | 0601904031 | Region VI (Western Visayas) | Capiz | Dumarao | Salcedo | 11.2556 | 122.6689 | R | 1734 | 456 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060244 | FTAP Globe | 11.2736 | 122.6783 | 2.26 | Terrestrial Optical Fiber Drop | 0.86 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1688 | 2 | 688 | 1688 | 0402108016 | Region IV-A (CALABARZON) | Cavite | City of General Trias | Navarro | 14.3866 | 120.9036 | U | 50641 | 14894 | 4468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01885-C08 | PTCI/MIDC | 14.3896 | 120.9068 | 0.48 | Terrestrial Optical Fiber Drop | 0.86 | 3.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1689 | 2 | 689 | 1689 | 0405809005 | Region IV-A (CALABARZON) | Rizal | Morong | San Guillermo | 14.5233 | 121.2131 | U | 12213 | 3392 | 1018 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3743 | FTAP Smart | 14.5236 | 121.2155 | 0.26 | Terrestrial Optical Fiber Drop | 0.87 | 1.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1690 | 2 | 690 | 1690 | 0402103042 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Mambog III | 14.4231 | 120.9581 | U | 22576 | 6640 | 1992 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040107 | FTAP Globe | 14.424 | 120.9533 | 0.52 | Terrestrial Optical Fiber Drop | 0.86 | 2.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1691 | 2 | 691 | 1691 | 0301422015 | Region III (Central Luzon) | Bulacan | San Rafael | Maronquillo | 14.9664 | 121.0011 | R | 4137 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030507 | FTAP Globe | 15.001 | 120.9731 | 1.4 | Terrestrial Optical Fiber Drop | 4.37 | 8.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1692 | 2 | 692 | 1692 | 0105538027 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Tuliao | 16.0123 | 120.3954 | U | 6475 | 1798 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTPNG0005 | PTCI/MIDC | 16.0077 | 120.3999 | 0.71 | Terrestrial Optical Fiber Drop | 0.86 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1693 | 2 | 693 | 1693 | 0500518013 | Region V (Bicol Region) | Albay | Tiwi | Libjo | 13.4626 | 123.6715 | U | 3013 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 1.19 | Terrestrial Optical Fiber Drop | 0.87 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1694 | 2 | 694 | 1694 | 1600201013 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Poblacion 1 | 8.975 | 125.4079 | R | 1543 | 376 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 0.37 | Terrestrial Optical Fiber Drop | 1.12 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1695 | 2 | 695 | 1695 | 0730600005 | Region VII (Central Visayas) | Cebu | City of Cebu | Basak Pardo | 10.2909 | 123.8656 | U | 17876 | 5586 | 1676 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CEB_0004 | LDIC | 10.2979 | 123.8697 | 0.9 | Terrestrial Optical Fiber Drop | 0.87 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1696 | 2 | 696 | 1696 | 0603037032 | Region VI (Western Visayas) | Iloilo | Pototan | Lopez Jaena Ward | 10.9406 | 122.6342 | R | 1511 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.71 | Terrestrial Optical Fiber Drop | 0.98 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1697 | 2 | 697 | 1697 | 0105504020 | Region I (Ilocos Region) | Pangasinan | Alcala | San Pedro Ili | 15.8482 | 120.5325 | R | 4184 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00561 | Edgepoint | 15.8477 | 120.5232 | 0.99 | Terrestrial Optical Fiber Drop | 0.87 | 7.67 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1698 | 2 | 698 | 1698 | 1206312016 | Region XII (SOCCSKSARGEN) | South Cotabato | Polomolok | Magsaysay | 6.2153 | 125.0576 | U | 14447 | 4013 | 1204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCG0043 | PTCI/MIDC | 6.215 | 125.0629 | 0.59 | Terrestrial Optical Fiber Drop | 0.86 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1699 | 2 | 699 | 1699 | 0402109053 | Region IV-A (CALABARZON) | Cavite | City of Imus | Buhay na Tubig | 14.4001 | 120.9604 | U | 41067 | 12078 | 3623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q10 | FTAP Smart | 14.3992 | 120.9596 | 0.14 | Terrestrial Optical Fiber Drop | 0.87 | 5.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1700 | 2 | 700 | 1700 | 1600308019 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Barangay 5 | 8.5043 | 125.9845 | U | 6068 | 1555 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 1.7 | Terrestrial Optical Fiber Drop | 1.09 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1701 | 2 | 701 | 1701 | 0301419017 | Region III (Central Luzon) | Bulacan | San Ildefonso | Lapnit | 15.078 | 120.936 | U | 3416 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030477 | FTAP Globe | 15.082 | 120.9387 | 0.53 | Terrestrial Optical Fiber Drop | 0.87 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1702 | 2 | 702 | 1702 | 0603026005 | Region VI (Western Visayas) | Iloilo | Leganes | Cagamutan Sur | 10.8121 | 122.6014 | R | 2022 | 532 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 0.56 | Terrestrial Optical Fiber Drop | 2.13 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1703 | 2 | 703 | 1703 | 0403413001 | Region IV-A (CALABARZON) | Laguna | Lumban | Bagong Silang | 14.2985 | 121.4613 | R | 3248 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040190 | FTAP Globe | 14.2918 | 121.4627 | 0.55 | Terrestrial Optical Fiber Drop | 0.33 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1704 | 2 | 704 | 1704 | 0907322040 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Jose | 7.8328 | 123.4317 | U | 8371 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0089 | PTCI/MIDC | 7.8352 | 123.422 | 1.1 | Terrestrial Optical Fiber Drop | 0.87 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1705 | 2 | 705 | 1705 | 0403426013 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Patimbao | 14.2724 | 121.4172 | U | 10201 | 3091 | 927 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4291 | FTAP Smart | 14.2707 | 121.4145 | 0.34 | Terrestrial Optical Fiber Drop | 0.87 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1706 | 2 | 706 | 1706 | 0403405039 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 2 | 14.2047 | 121.1585 | U | 11649 | 3530 | 1059 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LAG_0010 | LDIC | 14.1974 | 121.1394 | 0.16 | Terrestrial Optical Fiber Drop | 1.57 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1707 | 2 | 707 | 1707 | 0301403016 | Region III (Central Luzon) | Bulacan | Baliuag | Sabang | 14.9653 | 120.9092 | U | 13115 | 3747 | 1124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02325-B07 | PTCI/MIDC | 14.9682 | 120.9088 | 0.32 | Terrestrial Optical Fiber Drop | 0.87 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1708 | 2 | 708 | 1708 | 0702250021 | Region VII (Central Visayas) | Cebu | City of Talisay | Lawaan II | 10.2651 | 123.8316 | U | 7003 | 1842 | 553 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0161 | PTCI/MIDC | 10.2581 | 123.8423 | 1.28 | Terrestrial Optical Fiber Drop | 1.05 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1709 | 2 | 709 | 1709 | 0702234027 | Region VII (Central Visayas) | Cebu | City of Naga | Tuyan | 10.2299 | 123.7682 | U | 13748 | 3617 | 1085 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0236 | PTCI/MIDC | 10.2326 | 123.7762 | 0.92 | Terrestrial Optical Fiber Drop | 0.85 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1710 | 2 | 710 | 1710 | 0730600053 | Region VII (Central Visayas) | Cebu | City of Cebu | Pardo | 10.2779 | 123.8569 | U | 12030 | 3759 | 1128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.56 | Terrestrial Optical Fiber Drop | 0.87 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1711 | 2 | 711 | 1711 | 0306902013 | Region III (Central Luzon) | Tarlac | Bamban | San Roque | 15.2763 | 120.5662 | U | 12502 | 3205 | 962 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03350-B07 | PTCI/MIDC | 15.2745 | 120.5676 | 0.25 | Terrestrial Optical Fiber Drop | 0.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1712 | 2 | 712 | 1712 | 0401031029 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Natatas | 14.0825 | 121.1192 | U | 5962 | 1656 | 497 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1393 | FTAP Smart | 14.0841 | 121.1253 | 0.68 | Terrestrial Optical Fiber Drop | 0.87 | 3.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1713 | 2 | 713 | 1713 | 1030500052 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Kauswagan | 8.5012 | 124.6309 | U | 40969 | 11380 | 3414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLR0038 | PTCI/MIDC | 8.4984 | 124.6309 | 0.31 | Terrestrial Optical Fiber Drop | 0.88 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1714 | 2 | 714 | 1714 | 0600405015 | Region VI (Western Visayas) | Aklan | Buruanga | Tigum | 11.8555 | 121.8921 | R | 1656 | 424 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060260 | FTAP Globe | 10.7754 | 122.5384 | 1.23 | Terrestrial Optical Fiber Drop | 11.86 | 53.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1715 | 2 | 715 | 1715 | 0405608011 | Region IV-A (CALABARZON) | Quezon | Candelaria | Mangilag Sur | 13.9317 | 121.4505 | U | 7544 | 1985 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040455 | FTAP Globe | 13.9315 | 121.4483 | 0.24 | Terrestrial Optical Fiber Drop | 0.87 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1716 | 2 | 716 | 1716 | 0201518012 | Region II (Cagayan Valley) | Cagayan | Pamplona | Masi | 18.457 | 121.339 | R | 2308 | 591 | 177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020007 | FTAP Globe | 18.4653 | 121.3439 | 1.06 | Terrestrial Optical Fiber Drop | 0.88 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1717 | 2 | 717 | 1717 | 0401007037 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Salong | 13.9205 | 120.8168 | U | 5026 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040472 | FTAP Globe | 13.9244 | 120.8212 | 0.65 | Terrestrial Optical Fiber Drop | 0.88 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1718 | 2 | 718 | 1718 | 0403404002 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banaybanay | 14.254 | 121.1309 | U | 37555 | 11380 | 3414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02403-C08 | PTCI/MIDC | 14.2496 | 121.129 | 0.53 | Terrestrial Optical Fiber Drop | 0.88 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1719 | 2 | 719 | 1719 | 0301415002 | Region III (Central Luzon) | Bulacan | Pandi | Bagong Barrio | 14.8921 | 120.9544 | U | 16035 | 4581 | 1374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00982-B07 | PTCI/MIDC | 14.8912 | 120.9541 | 0.1 | Terrestrial Optical Fiber Drop | 0.88 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1720 | 2 | 720 | 1720 | 0300804026 | Region III (Central Luzon) | Bataan | Dinalupihan | Pinulot | 14.8501 | 120.3895 | R | 4758 | 1321 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0008 | PTCI/MIDC | 14.8525 | 120.3875 | 0.35 | Terrestrial Optical Fiber Drop | 0.87 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1721 | 2 | 721 | 1721 | 0731300023 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tabok | 10.3467 | 123.9407 | U | 19506 | 5573 | 1672 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0118 | PTCI/MIDC | 10.3479 | 123.9486 | 0.87 | Terrestrial Optical Fiber Drop | 0.88 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1722 | 2 | 722 | 1722 | 0300804016 | Region III (Central Luzon) | Bataan | Dinalupihan | Luacan | 14.8651 | 120.4486 | U | 6219 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0004 | PTCI/MIDC | 14.8608 | 120.4461 | 0.55 | Terrestrial Optical Fiber Drop | 0.87 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1723 | 2 | 723 | 1723 | 1102412021 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone IV | 6.8335 | 125.4108 | U | 7229 | 2126 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.47 | Terrestrial Optical Fiber Drop | 0.88 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1724 | 2 | 724 | 1724 | 0330100025 | Region III (Central Luzon) | Pampanga | City of Angeles | Sta. Teresita | 15.1496 | 120.5855 | U | 9570 | 2658 | 797 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1109 | FTAP Smart | 15.1503 | 120.6022 | 0.26 | Terrestrial Optical Fiber Drop | 0.74 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1725 | 2 | 725 | 1725 | 0501733009 | Region V (Bicol Region) | Camarines Sur | San Jose | Danlog | 13.6947 | 123.5273 | R | 2087 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050063 | FTAP Globe | 13.7006 | 123.5153 | 1.45 | Terrestrial Optical Fiber Drop | 0.88 | 3.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1726 | 2 | 726 | 1726 | 0405802013 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dalig | 14.561 | 121.1897 | U | 56096 | 15582 | 4675 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040050 | FTAP Globe | 14.5625 | 121.1888 | 0.2 | Terrestrial Optical Fiber Drop | 0.88 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1727 | 2 | 727 | 1727 | 0402101012 | Region IV-A (CALABARZON) | Cavite | Alfonso | Marahan I | 14.1328 | 120.8488 | U | 3251 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAV-03178 | Edgepoint | 14.1427 | 120.8558 | 1.34 | Terrestrial Optical Fiber Drop | 0.88 | 4.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1728 | 2 | 728 | 1728 | 0504101004 | Region V (Bicol Region) | Masbate | Aroroy | Bagauma | 12.4752 | 123.3812 | R | 2847 | 694 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050236 | FTAP Globe | 12.5111 | 123.3974 | 0.9 | Terrestrial Optical Fiber Drop | 4.36 | 26.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1729 | 2 | 729 | 1729 | 0307104010 | Region III (Central Luzon) | Zambales | Castillejos | San Jose | 14.9374 | 120.1982 | R | 3977 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02717 | Edgepoint | 14.9397 | 120.1927 | 0.64 | Terrestrial Optical Fiber Drop | 0.88 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1730 | 2 | 730 | 1730 | 1600206010 | Region XIII (Caraga) | Agusan del Norte | Kitcharao | Crossing | 9.4498 | 125.5748 | U | 3506 | 855 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 5.21 | Terrestrial Optical Fiber Drop | 0.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1731 | 2 | 731 | 1731 | 0401003013 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 8 | 13.9377 | 120.7326 | R | 2170 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6852 | FTAP Smart | 13.9412 | 120.7322 | 0.48 | Terrestrial Optical Fiber Drop | 0.81 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1732 | 2 | 732 | 1732 | 0403402013 | Region IV-A (CALABARZON) | Laguna | Bay | Santo Domingo | 14.1768 | 121.266 | U | 10856 | 3289 | 987 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040274 | FTAP Globe | 14.1747 | 121.2663 | 0.24 | Terrestrial Optical Fiber Drop | 0.88 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1733 | 2 | 733 | 1733 | 0305411010 | Region III (Central Luzon) | Pampanga | Magalang | San Isidro | 15.2325 | 120.6362 | U | 28421 | 7105 | 2132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030433 | FTAP Globe | 15.2267 | 120.6323 | 0.77 | Terrestrial Optical Fiber Drop | 0.89 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1734 | 2 | 734 | 1734 | 0306914012 | Region III (Central Luzon) | Tarlac | San Manuel | San Miguel | 15.8044 | 120.6072 | R | 2552 | 654 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02478 | Edgepoint | 15.8041 | 120.6062 | 0.11 | Terrestrial Optical Fiber Drop | 0.89 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1735 | 2 | 735 | 1735 | 0402116006 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael I | 14.4314 | 120.8795 | R | 1316 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.62 | Terrestrial Optical Fiber Drop | 0.43 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1736 | 2 | 736 | 1736 | 0500518003 | Region V (Bicol Region) | Albay | Tiwi | Baybay | 13.4603 | 123.6831 | R | 2408 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050117 | FTAP Globe | 13.4576 | 123.6811 | 0.37 | Terrestrial Optical Fiber Drop | 0.88 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1737 | 2 | 737 | 1737 | 1403209020 | Cordillera Administrative Region (CAR) | Kalinga | Pinukpuk | Pinukpuk Junction | 17.6153 | 121.4085 | R | 3147 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-00102 | Edgepoint | 17.6007 | 121.4263 | 2.49 | Terrestrial Optical Fiber Drop | 0.88 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1738 | 2 | 738 | 1738 | 1705211008 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Santo Niño | 13.503 | 120.9477 | R | 2744 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170046 | FTAP Globe | 13.5009 | 120.9529 | 0.6 | Terrestrial Optical Fiber Drop | 0.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1739 | 2 | 739 | 1739 | 1731500065 | MIMAROPA Region | Palawan | City of Puerto Princesa | Mandaragat | 9.7473 | 118.738 | U | 10559 | 2853 | 856 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170252 | FTAP Globe | 9.7413 | 118.7357 | 0.71 | Terrestrial Optical Fiber Drop | 0.89 | 1.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1740 | 2 | 740 | 1740 | 0105526007 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bateng | 16.0703 | 120.4054 | R | 2912 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02521-B07 | PTCI/MIDC | 16.0657 | 120.4078 | 0.36 | Terrestrial Optical Fiber Drop | 0.43 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1741 | 2 | 741 | 1741 | 0300805008 | Region III (Central Luzon) | Bataan | Hermosa | Culis | 14.8396 | 120.4818 | U | 10782 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1505 | FTAP Smart | 14.8402 | 120.4776 | 0.46 | Terrestrial Optical Fiber Drop | 0.89 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1742 | 2 | 742 | 1742 | 1630400085 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Tandang Sora Pob. | 8.9475 | 125.5314 | U | 4147 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0010 | PTCI/MIDC | 8.947 | 125.5334 | 0.23 | Terrestrial Optical Fiber Drop | 0.88 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1743 | 2 | 743 | 1743 | 0330100030 | Region III (Central Luzon) | Pampanga | City of Angeles | Sapalibutad | 15.1588 | 120.6255 | U | 14913 | 4142 | 1243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02978-B07 | PTCI/MIDC | 15.1531 | 120.6213 | 0.78 | Terrestrial Optical Fiber Drop | 0.88 | 1.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1744 | 2 | 744 | 1744 | 1403211007 | Cordillera Administrative Region (CAR) | Kalinga | Rizal | Liwan West | 17.4925 | 121.5885 | R | 3022 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-KAL-02200 | Edgepoint | 17.4717 | 121.5708 | 2.98 | Terrestrial Optical Fiber Drop | 0.89 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1745 | 2 | 745 | 1745 | 0103306006 | Region I (Ilocos Region) | La Union | Bangar | Barraca | 16.8984 | 120.4186 | R | 1358 | 367 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | C55 | FTAP Smart | 16.8961 | 120.4247 | 0.69 | Terrestrial Optical Fiber Drop | 0.89 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1746 | 2 | 746 | 1746 | 0702205035 | Region VII (Central Visayas) | Cebu | Argao | Poblacion | 9.877 | 123.6033 | U | 6145 | 1617 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 0.64 | Terrestrial Optical Fiber Drop | 0.89 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1747 | 2 | 747 | 1747 | 0603037012 | Region VI (Western Visayas) | Iloilo | Pototan | Cau-ayan | 10.9415 | 122.6429 | U | 3091 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 1.21 | Terrestrial Optical Fiber Drop | 0.54 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1748 | 2 | 748 | 1748 | 0731300015 | Region VII (Central Visayas) | Cebu | City of Mandaue | Labogon | 10.3541 | 123.9576 | U | 20487 | 5853 | 1756 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0214 | PTCI/MIDC | 10.352 | 123.9517 | 0.68 | Terrestrial Optical Fiber Drop | 0.89 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1749 | 2 | 749 | 1749 | 1102403030 | Region XI (Davao Region) | Davao del Sur | City of Digos | Zone 3 | 6.7442 | 125.3591 | U | 18722 | 5506 | 1652 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0070 | PTCI/MIDC | 6.7422 | 125.3619 | 0.38 | Terrestrial Optical Fiber Drop | 0.89 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1750 | 2 | 750 | 1750 | 0305415014 | Region III (Central Luzon) | Pampanga | Porac | Jalung | 15.066 | 120.5347 | U | 5096 | 1274 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.96 | Terrestrial Optical Fiber Drop | 0.89 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1751 | 2 | 751 | 1751 | 0401027016 | Region IV-A (CALABARZON) | Batangas | Santa Teresita | Tambo Ilaya | 13.8959 | 120.9743 | R | 1123 | 311 | 93 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040537 | FTAP Globe | 13.8612 | 120.965 | 1.58 | Terrestrial Optical Fiber Drop | 2.13 | 2.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1752 | 2 | 752 | 1752 | 0300809008 | Region III (Central Luzon) | Bataan | Orani | Kaparangan | 14.7943 | 120.5386 | R | 3108 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030611 | FTAP Globe | 14.7884 | 120.5392 | 0.66 | Terrestrial Optical Fiber Drop | 0.9 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1753 | 2 | 753 | 1753 | 0405619060 | Region IV-A (CALABARZON) | Quezon | Gumaca | Lagyo | 13.9226 | 122.116 | R | 1856 | 488 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-03196 | Edgepoint | 13.921 | 122.1079 | 0.89 | Terrestrial Optical Fiber Drop | 0.89 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1754 | 2 | 754 | 1754 | 0304931010 | Region III (Central Luzon) | Nueva Ecija | Talugtug | Magsaysay | 15.7789 | 120.8056 | R | 1657 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00577 | Edgepoint | 15.779 | 120.8098 | 0.45 | Terrestrial Optical Fiber Drop | 0.89 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1755 | 2 | 755 | 1755 | 0702205026 | Region VII (Central Visayas) | Cebu | Argao | Langtad | 9.8887 | 123.6051 | R | 3494 | 919 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 0.75 | Terrestrial Optical Fiber Drop | 0.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1756 | 2 | 756 | 1756 | 0604532002 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Bagong Silang | 10.6056 | 123.2814 | R | 2903 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02854-D13 | PTCI/MIDC | 10.6776 | 123.3415 | 10.36 | Terrestrial Optical Fiber Drop | 0.89 | 3.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1757 | 2 | 757 | 1757 | 0305402014 | Region III (Central Luzon) | Pampanga | Apalit | Sulipan | 14.9402 | 120.7598 | U | 12406 | 3101 | 930 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030532 | FTAP Globe | 14.9371 | 120.7625 | 0.45 | Terrestrial Optical Fiber Drop | 0.9 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1758 | 2 | 758 | 1758 | 1401110008 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Betag | 16.4496 | 120.595 | U | 9549 | 2728 | 818 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH140179 | FTAP Globe | 16.4461 | 120.5914 | 0.72 | Terrestrial Optical Fiber Drop | 0.76 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1759 | 2 | 759 | 1759 | 0704603022 | Region VII (Central Visayas) | Negros Oriental | Bacong | West Poblacion | 9.2472 | 123.2957 | R | 687 | 180 | 54 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0002 | PTCI/MIDC | 9.2246 | 123.2836 | 2.85 | Terrestrial Optical Fiber Drop | 0.5 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1760 | 2 | 760 | 1760 | 1600201011 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Matabao | 8.9751 | 125.4219 | U | 5798 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 0.45 | Terrestrial Optical Fiber Drop | 0.85 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1761 | 2 | 761 | 1761 | 0330100024 | Region III (Central Luzon) | Pampanga | City of Angeles | San Nicolas | 15.1494 | 120.5924 | U | 5024 | 1395 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00829 | Edgepoint | 15.1615 | 120.5826 | 0.05 | Terrestrial Optical Fiber Drop | 0.24 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1762 | 2 | 762 | 1762 | 1004322008 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Looc | 8.8492 | 124.7885 | R | 3486 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 0.77 | Terrestrial Optical Fiber Drop | 0.9 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1763 | 2 | 763 | 1763 | 0506203065 | Region V (Bicol Region) | Sorsogon | Bulan | Zone VIII Pob. | 12.6689 | 123.8811 | R | 2226 | 556 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.22 | Terrestrial Optical Fiber Drop | 0.9 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1764 | 2 | 764 | 1764 | 0500517005 | Region V (Bicol Region) | Albay | City of Tabaco | Baranghawon | 13.3523 | 123.723 | R | 4803 | 1171 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.29 | Terrestrial Optical Fiber Drop | 0.9 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1765 | 2 | 765 | 1765 | 0630200015 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 2 | 10.6835 | 122.9536 | U | 3407 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060346 | FTAP Globe | 10.6547 | 122.9607 | 0.73 | Terrestrial Optical Fiber Drop | 1.85 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1766 | 2 | 766 | 1766 | 0403423004 | Region IV-A (CALABARZON) | Laguna | Rizal | Paule 1 | 14.1129 | 121.3948 | R | 1222 | 339 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.74 | Terrestrial Optical Fiber Drop | 0.35 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1767 | 2 | 767 | 1767 | 0304912017 | Region III (Central Luzon) | Nueva Ecija | Jaen | Pakol | 15.3759 | 120.8657 | R | 1909 | 545 | 164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03333-B07 | PTCI/MIDC | 15.384 | 120.8662 | 0.91 | Terrestrial Optical Fiber Drop | 0.9 | 6.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1768 | 2 | 768 | 1768 | 0305410001 | Region III (Central Luzon) | Pampanga | Macabebe | Batasan | 14.8918 | 120.7151 | R | 4722 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-01067 | Edgepoint | 14.8851 | 120.7075 | 1.1 | Terrestrial Optical Fiber Drop | 0.9 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1769 | 2 | 769 | 1769 | 0402117020 | Region IV-A (CALABARZON) | Cavite | Rosario | Wawa II | 14.4118 | 120.8479 | U | 6185 | 1819 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.41 | Terrestrial Optical Fiber Drop | 2.15 | 2.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1770 | 2 | 770 | 1770 | 0305416009 | Region III (Central Luzon) | Pampanga | City of San Fernando | Del Rosario | 15.0685 | 120.6394 | U | 8600 | 2150 | 645 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030479 | FTAP Globe | 15.0731 | 120.6443 | 0.74 | Terrestrial Optical Fiber Drop | 0.91 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1771 | 2 | 771 | 1771 | 0402123018 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Koronel Jose P. Elises | 14.3041 | 121.0076 | R | 4747 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.33 | Terrestrial Optical Fiber Drop | 2.48 | 4.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1772 | 2 | 772 | 1772 | 0702216011 | Region VII (Central Visayas) | Cebu | Catmon | Catmondaan | 10.6858 | 124.0145 | R | 3423 | 900 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070313 | FTAP Globe | 10.674 | 124.0182 | 1.38 | Terrestrial Optical Fiber Drop | 0.91 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1773 | 2 | 773 | 1773 | 0600416002 | Region VI (Western Visayas) | Aklan | Numancia | Aliputos | 11.6993 | 122.335 | R | 2643 | 677 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060024 | FTAP BTS | 11.6775 | 122.3507 | 2.97 | Terrestrial Optical Fiber Drop | 0.9 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1774 | 2 | 774 | 1774 | 0301412009 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Iba | 14.7539 | 120.9818 | U | 9791 | 2797 | 839 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00977-B07 | PTCI/MIDC | 14.7557 | 120.9758 | 0.68 | Terrestrial Optical Fiber Drop | 0.91 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1775 | 2 | 775 | 1775 | 0330100020 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulungbulu | 15.1363 | 120.5945 | U | 13602 | 3778 | 1133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0023 | FTAP Smart | 15.1368 | 120.5909 | 0.39 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1776 | 2 | 776 | 1776 | 0402123016 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Jacinto Lumbreras | 14.2906 | 121.002 | R | 4497 | 1322 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040193 | FTAP Globe | 14.2884 | 121.0025 | 0.25 | Terrestrial Optical Fiber Drop | 0.91 | 4.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1777 | 2 | 777 | 1777 | 0304929014 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Hulo | 15.5847 | 120.8813 | R | 2196 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0031 | PTCI/MIDC | 15.5809 | 120.8782 | 0.54 | Terrestrial Optical Fiber Drop | 0.91 | 4.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1778 | 2 | 778 | 1778 | 0304903084 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Vijandre District | 15.4903 | 120.9704 | R | 1195 | 341 | 102 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N2096 | FTAP Smart | 15.478 | 120.9538 | 0.12 | Terrestrial Optical Fiber Drop | 1.37 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1779 | 2 | 779 | 1779 | 0702220012 | Region VII (Central Visayas) | Cebu | Cordova | Poblacion | 10.2541 | 123.95 | U | 10393 | 2735 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.65 | Terrestrial Optical Fiber Drop | 0.91 | 7.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1780 | 2 | 780 | 1780 | 0402116004 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio I | 14.4185 | 120.8859 | U | 5804 | 1707 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040102 | FTAP Globe | 14.4342 | 120.8769 | 0.36 | Terrestrial Optical Fiber Drop | 1.27 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1781 | 2 | 781 | 1781 | 0201516030 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | San Jose | 18.2036 | 121.6613 | R | 1613 | 413 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 0.98 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1782 | 2 | 782 | 1782 | 0402106081 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Victoria Reyes | 14.3186 | 120.9752 | U | 14568 | 4284 | 1285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0032 | PTCI/MIDC | 14.3181 | 120.9773 | 0.23 | Terrestrial Optical Fiber Drop | 0.91 | 2.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1783 | 2 | 783 | 1783 | 0300804048 | Region III (Central Luzon) | Bataan | Dinalupihan | Pentor | 14.8711 | 120.4739 | R | 3429 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0007 | PTCI/MIDC | 14.8692 | 120.4753 | 0.26 | Terrestrial Optical Fiber Drop | 0.91 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1784 | 2 | 784 | 1784 | 0405622015 | Region IV-A (CALABARZON) | Quezon | Lopez | Bocboc | 13.8791 | 122.261 | R | 2482 | 653 | 196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.91 | Terrestrial Optical Fiber Drop | 0.91 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1785 | 2 | 785 | 1785 | 1102411001 | Region XI (Davao Region) | Davao del Sur | Padada | Almendras | 6.6446 | 125.3456 | U | 3910 | 1150 | 345 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110530 | FTAP Globe | 6.6448 | 125.3465 | 0.15 | Terrestrial Optical Fiber Drop | 1.02 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1786 | 2 | 786 | 1786 | 0405801011 | Region IV-A (CALABARZON) | Rizal | Angono | San Roque | 14.5325 | 121.1614 | U | 12209 | 3391 | 1017 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02331-A04 | PTCI/MIDC | 14.5317 | 121.1611 | 0.1 | Terrestrial Optical Fiber Drop | 0.91 | 0.87 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1787 | 2 | 787 | 1787 | 0203118017 | Region II (Cagayan Valley) | Isabela | Delfin Albano | San Antonio | 17.2732 | 121.7916 | R | 3331 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020057 | FTAP Globe | 17.2868 | 121.785 | 1.66 | Terrestrial Optical Fiber Drop | 0.91 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1788 | 2 | 788 | 1788 | 0402109067 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang II-F | 14.4051 | 120.9261 | R | 1538 | 452 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 676 | FTAP Smart | 14.4604 | 120.9609 | 0.98 | Terrestrial Optical Fiber Drop | 1.58 | 4.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1789 | 2 | 789 | 1789 | 0301421044 | Region III (Central Luzon) | Bulacan | San Miguel | San Jose | 15.1483 | 120.9816 | U | 4822 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1604 | FTAP Smart | 15.1496 | 120.9781 | 0.41 | Terrestrial Optical Fiber Drop | 0.92 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1790 | 2 | 790 | 1790 | 0403423009 | Region IV-A (CALABARZON) | Laguna | Rizal | Tala | 14.1111 | 121.3914 | R | 2885 | 801 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 0.99 | Terrestrial Optical Fiber Drop | 0.16 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1791 | 2 | 791 | 1791 | 0405622008 | Region IV-A (CALABARZON) | Quezon | Lopez | Talolong | 13.879 | 122.2616 | U | 3786 | 996 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-QUE-02695 | Edgepoint | 13.8872 | 122.2623 | 0.91 | Terrestrial Optical Fiber Drop | 0.92 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1792 | 2 | 792 | 1792 | 0803703002 | Region VIII (Eastern Visayas) | Leyte | Albuera | Balugo | 10.8876 | 124.7111 | U | 5230 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0005 | PTCI/MIDC | 10.8845 | 124.7097 | 0.38 | Terrestrial Optical Fiber Drop | 0.92 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1793 | 2 | 793 | 1793 | 0304928028 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Isla | 15.4175 | 120.9273 | R | 2736 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1331 | FTAP Smart | 15.4259 | 120.9264 | 0.95 | Terrestrial Optical Fiber Drop | 0.9 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1794 | 2 | 794 | 1794 | 0501724025 | Region V (Bicol Region) | Camarines Sur | City of Naga | Sabang | 13.6203 | 123.1805 | U | 6822 | 1624 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 0.53 | Terrestrial Optical Fiber Drop | 0.91 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1795 | 2 | 795 | 1795 | 0403410022 | Region IV-A (CALABARZON) | Laguna | Liliw | Kanlurang Bukal | 14.1286 | 121.4395 | R | 4848 | 1469 | 441 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02072-C08 | PTCI/MIDC | 14.1295 | 121.4404 | 0.13 | Terrestrial Optical Fiber Drop | 0.92 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1796 | 2 | 796 | 1796 | 0501703032 | Region V (Bicol Region) | Camarines Sur | Bato | Santiago | 13.3519 | 123.371 | R | 3579 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050130 | FTAP Globe | 13.3557 | 123.3682 | 0.51 | Terrestrial Optical Fiber Drop | 0.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1797 | 2 | 797 | 1797 | 0301423024 | Region III (Central Luzon) | Bulacan | Santa Maria | Tabing Bakod | 14.8017 | 120.9542 | U | 5655 | 1615 | 485 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02211 | Edgepoint | 14.8035 | 120.9555 | 0.25 | Terrestrial Optical Fiber Drop | 0.92 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1798 | 2 | 798 | 1798 | 0305411021 | Region III (Central Luzon) | Pampanga | Magalang | Santa Lucia | 15.2234 | 120.6279 | U | 10263 | 2565 | 770 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00795 | Edgepoint | 15.2244 | 120.63 | 0.25 | Terrestrial Optical Fiber Drop | 0.92 | 1.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1799 | 2 | 799 | 1799 | 1003522021 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | San Antonio | 8.0372 | 123.8051 | R | 2335 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 1.74 | Terrestrial Optical Fiber Drop | 0.92 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1800 | 2 | 800 | 1800 | 0105503019 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | Palamis | 16.15 | 119.976 | U | 4745 | 1318 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N6719 | FTAP Smart | 16.155 | 119.9806 | 0.75 | Terrestrial Optical Fiber Drop | 0.92 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1801 | 2 | 801 | 1801 | 0304926002 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Abar Ist | 15.7895 | 120.9811 | U | 23122 | 6606 | 1982 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0196 | FTAP Smart | 15.7902 | 120.9765 | 0.49 | Terrestrial Optical Fiber Drop | 0.92 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1802 | 2 | 802 | 1802 | 0304924006 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Maugat | 15.3163 | 120.8585 | U | 5867 | 1676 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03335-B07 | PTCI/MIDC | 15.3157 | 120.8564 | 0.23 | Terrestrial Optical Fiber Drop | 0.92 | 3.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1803 | 2 | 803 | 1803 | 0402106069 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Francisco II | 14.3177 | 120.9523 | R | 3540 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000722 | FTAP Globe | 14.3509 | 121.01 | 0.95 | Terrestrial Optical Fiber Drop | 1.55 | 1.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1804 | 2 | 804 | 1804 | 0402103010 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Ligas I | 14.4536 | 120.9686 | U | 5049 | 1485 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH000677 | FTAP Globe | 14.4591 | 120.9704 | 0.64 | Terrestrial Optical Fiber Drop | 0.93 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1805 | 2 | 805 | 1805 | 0306916018 | Region III (Central Luzon) | Tarlac | City of Tarlac | Binauganan | 15.4769 | 120.6045 | U | 6040 | 1548 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.33 | Terrestrial Optical Fiber Drop | 0.92 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1806 | 2 | 806 | 1806 | 0506205026 | Region V (Bicol Region) | Sorsogon | Casiguran | Tulay | 12.8729 | 124.0053 | R | 2328 | 582 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050218 | FTAP Globe | 12.8749 | 124.0078 | 0.35 | Terrestrial Optical Fiber Drop | 0.92 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1807 | 2 | 807 | 1807 | 1130700124 | Region XI (Davao Region) | Davao del Sur | City of Davao | Tibungco | 7.189 | 125.6412 | U | 51647 | 15190 | 4557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110453 | FTAP Globe | 7.1893 | 125.6441 | 0.33 | Terrestrial Optical Fiber Drop | 0.92 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1808 | 2 | 808 | 1808 | 0501730026 | Region V (Bicol Region) | Camarines Sur | Ragay | Panaytayan | 13.8231 | 122.7814 | R | 2321 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03249-C10 | PTCI/MIDC | 13.8167 | 122.7702 | 1.41 | Terrestrial Optical Fiber Drop | 0.92 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1809 | 2 | 809 | 1809 | 0205704017 | Region II (Cagayan Valley) | Quirino | Maddela | Poblacion Norte | 16.3436 | 121.685 | U | 2662 | 682 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0010 | LDIC | 16.3416 | 121.6868 | 0.29 | Terrestrial Optical Fiber Drop | 0.93 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1810 | 2 | 810 | 1810 | 0402116014 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Rafael III | 14.4365 | 120.8783 | U | 6490 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040102 | FTAP Globe | 14.4342 | 120.8769 | 0.3 | Terrestrial Optical Fiber Drop | 0.93 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1811 | 2 | 811 | 1811 | 0702220007 | Region VII (Central Visayas) | Cebu | Cordova | Day-as | 10.2543 | 123.944 | R | 5003 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0065 | PTCI/MIDC | 10.2565 | 123.9446 | 0.25 | Terrestrial Optical Fiber Drop | 0.93 | 7.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1812 | 2 | 812 | 1812 | 0405623009 | Region IV-A (CALABARZON) | Quezon | Lucban | Barangay 6 | 14.1171 | 121.5498 | R | 1646 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0021 | PTCI/MIDC | 14.1109 | 121.5533 | 0.45 | Terrestrial Optical Fiber Drop | 0.98 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1813 | 2 | 813 | 1813 | 0600407007 | Region VI (Western Visayas) | Aklan | Kalibo | Caano | 11.7054 | 122.3643 | R | 1949 | 499 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.59 | Terrestrial Optical Fiber Drop | 0.93 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1814 | 2 | 814 | 1814 | 0103301044 | Region I (Ilocos Region) | La Union | Agoo | Santa Monica | 16.3225 | 120.3659 | R | 1307 | 353 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01404-B05 | PTCI/MIDC | 16.3395 | 120.406 | 0.12 | Terrestrial Optical Fiber Drop | 0.3 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1815 | 2 | 815 | 1815 | 0731300005 | Region VII (Central Visayas) | Cebu | City of Mandaue | Cabancalan | 10.3482 | 123.9254 | U | 14856 | 4244 | 1273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070334 | FTAP Globe | 10.3495 | 123.929 | 0.42 | Terrestrial Optical Fiber Drop | 0.93 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1816 | 2 | 816 | 1816 | 0103307027 | Region I (Ilocos Region) | La Union | Bauang | Payocpoc Norte Oeste | 16.5279 | 120.3341 | R | 2015 | 544 | 163 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00315 | Edgepoint | 16.5247 | 120.3269 | 0.41 | Terrestrial Optical Fiber Drop | 0.85 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1817 | 2 | 817 | 1817 | 0304912029 | Region III (Central Luzon) | Nueva Ecija | Jaen | Sapang | 15.324 | 120.9057 | R | 4479 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030415 | FTAP Globe | 15.3266 | 120.9075 | 0.35 | Terrestrial Optical Fiber Drop | 0.93 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1818 | 2 | 818 | 1818 | 0401026020 | Region IV-A (CALABARZON) | Batangas | San Pascual | Poblacion | 13.7867 | 121.0259 | U | 11379 | 3160 | 948 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01939-C08 | PTCI/MIDC | 13.7844 | 121.0323 | 0.74 | Terrestrial Optical Fiber Drop | 0.93 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1819 | 2 | 819 | 1819 | 0330100036 | Region III (Central Luzon) | Pampanga | City of Angeles | Ninoy Aquino | 15.1512 | 120.6007 | U | 11840 | 3288 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1109 | FTAP Smart | 15.1503 | 120.6022 | 0.19 | Terrestrial Optical Fiber Drop | 0.93 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1820 | 2 | 820 | 1820 | 1401110009 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Cruz | 16.4497 | 120.5947 | R | 3493 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1845 | FTAP Smart | 16.4542 | 120.5894 | 0.39 | Terrestrial Optical Fiber Drop | 0.73 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1821 | 2 | 821 | 1821 | 0908302017 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Buug | Poblacion | 7.7276 | 123.0632 | U | 7772 | 1850 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090146 | FTAP Globe | 7.7325 | 123.056 | 0.96 | Terrestrial Optical Fiber Drop | 0.93 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1822 | 2 | 822 | 1822 | 0501603025 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay II | 14.1062 | 122.9535 | R | 2919 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCNG0009 | PTCI/MIDC | 14.1084 | 122.9523 | 0.28 | Terrestrial Optical Fiber Drop | 0.93 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1823 | 2 | 823 | 1823 | 0103311030 | Region I (Ilocos Region) | La Union | Naguilian | Ortiz | 16.5325 | 120.3916 | U | 2793 | 754 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 0.45 | Terrestrial Optical Fiber Drop | 0.93 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1824 | 2 | 824 | 1824 | 0301419021 | Region III (Central Luzon) | Bulacan | San Ildefonso | Matimbubong | 15.0659 | 120.9453 | R | 2933 | 838 | 251 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01093-B07 | PTCI/MIDC | 15.0639 | 120.9444 | 0.24 | Terrestrial Optical Fiber Drop | 0.93 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1825 | 2 | 825 | 1825 | 0402123017 | Region IV-A (CALABARZON) | Cavite | Gen. Mariano Alvarez | Kapitan Kua | 14.304 | 121.0077 | R | 3595 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCAG0044 | PTCI/MIDC | 14.3102 | 121.0334 | 0.28 | Terrestrial Optical Fiber Drop | 2.47 | 4.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1826 | 2 | 826 | 1826 | 0600407003 | Region VI (Western Visayas) | Aklan | Kalibo | Bachaw Sur | 11.7261 | 122.3685 | R | 3705 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTAKG0005 | PTCI/MIDC | 11.6975 | 122.3768 | 0.73 | Terrestrial Optical Fiber Drop | 3.19 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1827 | 2 | 827 | 1827 | 0402116013 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Juan II | 14.4377 | 120.8852 | R | 3488 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0042 | PTCI/MIDC | 14.4397 | 120.8833 | 0.3 | Terrestrial Optical Fiber Drop | 0.94 | 0.7 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1828 | 2 | 828 | 1828 | 0201510018 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Gang-ngo | 18.2646 | 121.6877 | R | 1571 | 402 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020014 | FTAP Globe | 18.2526 | 121.6864 | 0.96 | Terrestrial Optical Fiber Drop | 0.44 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1829 | 2 | 829 | 1829 | 0403419009 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Magdapio | 14.2744 | 121.4589 | R | 2560 | 775 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.45 | Terrestrial Optical Fiber Drop | 0.93 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1830 | 2 | 830 | 1830 | 0105515021 | Region I (Ilocos Region) | Pangasinan | Bugallon | Salomague Sur | 15.91 | 120.2278 | U | 3352 | 931 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01747-B07 | PTCI/MIDC | 15.9191 | 120.2262 | 1.03 | Terrestrial Optical Fiber Drop | 0.94 | 11.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1831 | 2 | 831 | 1831 | 0103311017 | Region I (Ilocos Region) | La Union | Naguilian | Dal-lipaoen | 16.5307 | 120.3955 | R | 1799 | 486 | 146 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | C52 | FTAP Smart | 16.5348 | 120.395 | 1.71 | Terrestrial Optical Fiber Drop | 0.47 | 4.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1832 | 2 | 832 | 1832 | 0304924001 | Region III (Central Luzon) | Nueva Ecija | San Antonio | Buliran | 15.2706 | 120.8646 | R | 5048 | 1442 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-02448 | Edgepoint | 15.261 | 120.8642 | 1.07 | Terrestrial Optical Fiber Drop | 0.94 | 0.88 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1833 | 2 | 833 | 1833 | 0304916022 | Region III (Central Luzon) | Nueva Ecija | Lupao | Poblacion South | 15.8764 | 120.8988 | R | 1853 | 529 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 0.43 | Terrestrial Optical Fiber Drop | 0.94 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1834 | 2 | 834 | 1834 | 1102507028 | Region XI (Davao Region) | Davao Oriental | Lupon | Poblacion | 6.8879 | 126.0134 | U | 17775 | 4937 | 1481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110325 | FTAP BTS | 6.8905 | 126.021 | 0.88 | Terrestrial Optical Fiber Drop | 0.94 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1835 | 2 | 835 | 1835 | 0402120034 | Region IV-A (CALABARZON) | Cavite | Tanza | Daang Amaya II | 14.3967 | 120.8535 | U | 7228 | 2125 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02478-C08 | PTCI/MIDC | 14.3915 | 120.8482 | 0.81 | Terrestrial Optical Fiber Drop | 0.94 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1836 | 2 | 836 | 1836 | 0600403012 | Region VI (Western Visayas) | Aklan | Banga | Libas | 11.6237 | 122.3451 | R | 1667 | 427 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTAKG0017 | PTCI/MIDC | 11.6308 | 122.3281 | 2.01 | Terrestrial Optical Fiber Drop | 0.94 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1837 | 2 | 837 | 1837 | 0803739018 | Region VIII (Eastern Visayas) | Leyte | Palo | Naga-naga | 11.1539 | 124.9928 | R | 2731 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.29 | Terrestrial Optical Fiber Drop | 0.94 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1838 | 2 | 838 | 1838 | 0305415032 | Region III (Central Luzon) | Pampanga | Porac | Sepung Bulaon | 15.0684 | 120.5426 | U | 5932 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02688 | Edgepoint | 15.0693 | 120.543 | 0.53 | Terrestrial Optical Fiber Drop | 0.48 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1839 | 2 | 839 | 1839 | 0401009012 | Region IV-A (CALABARZON) | Batangas | Cuenca | Pinagkaisahan | 13.9062 | 121.0525 | R | 2020 | 561 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040510 | FTAP Globe | 13.9025 | 121.0501 | 0.48 | Terrestrial Optical Fiber Drop | 0.94 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1840 | 2 | 840 | 1840 | 0731300026 | Region VII (Central Visayas) | Cebu | City of Mandaue | Tipolo | 10.3323 | 123.9275 | U | 15806 | 4516 | 1355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0205 | PTCI/MIDC | 10.3298 | 123.9314 | 0.51 | Terrestrial Optical Fiber Drop | 0.95 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1841 | 2 | 841 | 1841 | 0402109061 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang I-F | 14.4022 | 120.9406 | U | 11100 | 3264 | 979 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040148 | FTAP Globe | 14.3495 | 120.9381 | 0.76 | Terrestrial Optical Fiber Drop | 0.53 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1842 | 2 | 842 | 1842 | 0205005024 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Luyang | 16.4962 | 121.1463 | R | 1690 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNVG0016 | PTCI/MIDC | 16.5005 | 121.1392 | 0.9 | Terrestrial Optical Fiber Drop | 0.95 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1843 | 2 | 843 | 1843 | 1600307006 | Region XIII (Caraga) | Agusan del Sur | Rosario | Poblacion | 8.3826 | 125.9982 | U | 5440 | 1394 | 418 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130096 | FTAP Globe | 8.3847 | 126.002 | 0.48 | Terrestrial Optical Fiber Drop | 0.95 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1844 | 2 | 844 | 1844 | 0402103004 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Bayanan | 14.4254 | 120.9746 | U | 11757 | 3457 | 1037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01864-C08 | PTCI/MIDC | 14.4276 | 120.9749 | 0.24 | Terrestrial Optical Fiber Drop | 0.94 | 2.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1845 | 2 | 845 | 1845 | 0501716016 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Francisco | 13.4132 | 123.4118 | U | 6423 | 1529 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02059 | Edgepoint | 123.406 | 13.4185 | 0.87 | Terrestrial Optical Fiber Drop | 0.95 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1846 | 2 | 846 | 1846 | 0504117027 | Region V (Bicol Region) | Masbate | Placer | Poblacion | 11.8689 | 123.9184 | R | 2305 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MAS-02172 | Edgepoint | 11.871 | 123.9194 | 0.26 | Satellite LEO Backhaul (Starlink Business) | 0.94 | 41.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1847 | 2 | 847 | 1847 | 0405806014 | Region IV-A (CALABARZON) | Rizal | Cardona | Looc | 14.4797 | 121.2237 | U | 9929 | 2758 | 827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01885 | Edgepoint | 14.4811 | 121.2241 | 0.17 | Terrestrial Optical Fiber Drop | 0.94 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1848 | 2 | 848 | 1848 | 0401030011 | Region IV-A (CALABARZON) | Batangas | Talisay | Poblacion Barangay 1 | 14.095 | 121.0216 | R | 2088 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040323 | FTAP Globe | 14.0965 | 121.0212 | 0.45 | Terrestrial Optical Fiber Drop | 0.41 | 5.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1849 | 2 | 849 | 1849 | 0403413011 | Region IV-A (CALABARZON) | Laguna | Lumban | Primera Pulo | 14.2987 | 121.4617 | R | 2306 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03270-C08 | PTCI/MIDC | 14.2998 | 121.4607 | 0.5 | Terrestrial Optical Fiber Drop | 0.35 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1850 | 2 | 850 | 1850 | 0301420054 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz II | 14.8559 | 121.0516 | R | 3559 | 1016 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01066-B07 | PTCI/MIDC | 14.8065 | 121.0228 | 0.14 | Terrestrial Optical Fiber Drop | 2.2 | 5.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1851 | 2 | 851 | 1851 | 1430300135 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Dominican Hill-Mirador | 16.4066 | 120.5833 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0007 | LDIC | 16.4062 | 120.5863 | 0.32 | Terrestrial Optical Fiber Drop | 0.95 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1852 | 2 | 852 | 1852 | 0603037006 | Region VI (Western Visayas) | Iloilo | Pototan | Bongco | 10.9407 | 122.6339 | R | 1802 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.57 | Terrestrial Optical Fiber Drop | 1 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1853 | 2 | 853 | 1853 | 0402121008 | Region IV-A (CALABARZON) | Cavite | Ternate | Sapang I | 14.2827 | 120.7101 | U | 7797 | 2293 | 688 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040194 | FTAP Globe | 14.2858 | 120.7121 | 0.4 | Terrestrial Optical Fiber Drop | 0.94 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1854 | 2 | 854 | 1854 | 0402109044 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma V | 14.4131 | 120.9345 | R | 4905 | 1442 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03245-C08 | PTCI/MIDC | 14.4097 | 120.9383 | 0.55 | Terrestrial Optical Fiber Drop | 0.95 | 3.92 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1855 | 2 | 855 | 1855 | 0301420033 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc East | 14.7994 | 121.0612 | U | 5619 | 1605 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01019-B07 | PTCI/MIDC | 14.8383 | 121.0824 | 0.2 | Terrestrial Optical Fiber Drop | 0.98 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1856 | 2 | 856 | 1856 | 0305413043 | Region III (Central Luzon) | Pampanga | Mexico | Santo Rosario | 15.0702 | 120.7241 | U | 4417 | 1104 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030482 | FTAP Globe | 15.0664 | 120.7233 | 0.43 | Terrestrial Optical Fiber Drop | 0.94 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1857 | 2 | 857 | 1857 | 0401010009 | Region IV-A (CALABARZON) | Batangas | Ibaan | Lucsuhin | 13.8291 | 121.1359 | R | 1775 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02240-C08 | PTCI/MIDC | 14.096 | 120.881 | 0.37 | Terrestrial Optical Fiber Drop | 1.67 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1858 | 2 | 858 | 1858 | 0401014048 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 7 | 13.9374 | 121.1612 | U | 4742 | 1317 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1300 | FTAP Smart | 13.9384 | 121.1622 | 0.16 | Terrestrial Optical Fiber Drop | 0.95 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1859 | 2 | 859 | 1859 | 0301410016 | Region III (Central Luzon) | Bulacan | City of Malolos | Caingin | 14.8442 | 120.8045 | U | 7681 | 2194 | 658 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01139 | Edgepoint | 14.8407 | 120.8008 | 0.55 | Terrestrial Optical Fiber Drop | 0.94 | 1.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1860 | 2 | 860 | 1860 | 0501603031 | Region V (Bicol Region) | Camarines Norte | Daet | Barangay VIII | 14.1143 | 122.9625 | U | 2819 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03029-C10 | PTCI/MIDC | 14.1154 | 122.961 | 0.2 | Terrestrial Optical Fiber Drop | 0.94 | 1.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1861 | 2 | 861 | 1861 | 1606724005 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Serna | 9.7835 | 125.4987 | R | 1800 | 439 | 132 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0011 | PTCI/MIDC | 9.7878 | 125.4925 | 0.73 | Terrestrial Optical Fiber Drop | 0.66 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1862 | 2 | 862 | 1862 | 0105511046 | Region I (Ilocos Region) | Pangasinan | Bayambang | Mangayao | 15.7968 | 120.4394 | R | 1277 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00570 | Edgepoint | 15.8173 | 120.45 | 0.4 | Terrestrial Optical Fiber Drop | 2.73 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1863 | 2 | 863 | 1863 | 1204704041 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Magsaysay | 7.0122 | 125.0799 | U | 4720 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNCG0011 | PTCI/MIDC | 7.0064 | 125.0798 | 0.64 | Terrestrial Optical Fiber Drop | 0.95 | 0.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1864 | 2 | 864 | 1864 | 0305409006 | Region III (Central Luzon) | Pampanga | Mabalacat City | Camachiles | 15.1929 | 120.5857 | U | 13860 | 3465 | 1040 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01553-B07 | PTCI/MIDC | 15.1914 | 120.5809 | 0.55 | Terrestrial Optical Fiber Drop | 0.95 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1865 | 2 | 865 | 1865 | 0103307032 | Region I (Ilocos Region) | La Union | Bauang | Pugo | 16.5274 | 120.3223 | R | 3328 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00315 | Edgepoint | 16.5247 | 120.3269 | 0.58 | Terrestrial Optical Fiber Drop | 0.95 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1866 | 2 | 866 | 1866 | 0331400012 | Region III (Central Luzon) | Zambales | City of Olongapo | New Kalalake | 14.8305 | 120.2891 | U | 10477 | 2831 | 849 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01156 | Edgepoint | 14.8305 | 120.288 | 0.12 | Terrestrial Optical Fiber Drop | 0.95 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1867 | 2 | 867 | 1867 | 1903617008 | Bangsamoro Autonomous Region In Muslim Mindanao (BARMM) | Lanao del Sur | City of Marawi | Banggolo Poblacion | 8.0033 | 124.2913 | R | 3754 | 658 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLSG0004 | PTCI/MIDC | 8.0153 | 124.2885 | 1.33 | Terrestrial Optical Fiber Drop | 2.02 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1868 | 2 | 868 | 1868 | 0201517031 | Region II (Cagayan Valley) | Cagayan | Lasam | Centro II | 18.0638 | 121.5999 | R | 2186 | 560 | 168 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02351-B06 | PTCI/MIDC | 18.0609 | 121.5987 | 0.35 | Terrestrial Optical Fiber Drop | 0.95 | 4.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1869 | 2 | 869 | 1869 | 1130700079 | Region XI (Davao Region) | Davao del Sur | City of Davao | Mintal | 7.0936 | 125.4999 | U | 19434 | 5715 | 1715 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0005 | LDIC | 7.0922 | 125.4988 | 0.2 | Terrestrial Optical Fiber Drop | 0.95 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1870 | 2 | 870 | 1870 | 0402113025 | Region IV-A (CALABARZON) | Cavite | Maragondon | Pinagsanhan I B | 14.2713 | 120.7297 | R | 4060 | 1194 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02228-C08 | PTCI/MIDC | 14.2795 | 120.7309 | 0.92 | Terrestrial Optical Fiber Drop | 0.95 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1871 | 2 | 871 | 1871 | 0907322041 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | San Pedro | 7.8237 | 123.4441 | U | 8496 | 2178 | 653 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0019 | PTCI/MIDC | 7.8277 | 123.443 | 0.46 | Terrestrial Optical Fiber Drop | 0.96 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1872 | 2 | 872 | 1872 | 0102903003 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Balaleng | 17.5867 | 120.385 | U | 3074 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02461-B05 | PTCI/MIDC | 17.5829 | 120.3867 | 0.46 | Terrestrial Optical Fiber Drop | 0.96 | 0.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1873 | 2 | 873 | 1873 | 0105538005 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Botao | 15.975 | 120.4588 | R | 3428 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010177 | FTAP Globe | 15.9751 | 120.4633 | 0.48 | Terrestrial Optical Fiber Drop | 0.96 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1874 | 2 | 874 | 1874 | 0501734032 | Region V (Bicol Region) | Camarines Sur | Sipocot | North Villazar | 13.8629 | 122.9497 | R | 1629 | 387 | 116 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 0.6 | Terrestrial Optical Fiber Drop | 0.96 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1875 | 2 | 875 | 1875 | 0203137005 | Region II (Cagayan Valley) | Isabela | Tumauini | Arcon | 17.2754 | 121.8238 | R | 2264 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02341-B06 | PTCI/MIDC | 17.2758 | 121.8225 | 0.15 | Terrestrial Optical Fiber Drop | 0.95 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1876 | 2 | 876 | 1876 | 0401010017 | Region IV-A (CALABARZON) | Batangas | Ibaan | Poblacion | 13.8227 | 121.1338 | U | 2316 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 0.28 | Terrestrial Optical Fiber Drop | 0.96 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1877 | 2 | 877 | 1877 | 0304902020 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Rizal | 15.629 | 121.1392 | R | 3481 | 994 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-03200 | Edgepoint | 15.6268 | 121.1447 | 0.63 | Terrestrial Optical Fiber Drop | 0.96 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1878 | 2 | 878 | 1878 | 0402103035 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Ligas II | 14.4417 | 120.9715 | U | 5296 | 1557 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0095 | FTAP Smart | 14.4464 | 120.9456 | 0.76 | Terrestrial Optical Fiber Drop | 2 | 1.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1879 | 2 | 879 | 1879 | 0330100002 | Region III (Central Luzon) | Pampanga | City of Angeles | Anunas | 15.1555 | 120.5553 | U | 27219 | 7560 | 2268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00833 | Edgepoint | 15.1553 | 120.5521 | 0.34 | Terrestrial Optical Fiber Drop | 0.96 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1880 | 2 | 880 | 1880 | 0405804035 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tatala | 14.4829 | 121.205 | U | 15462 | 4295 | 1289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00773-A04 | PTCI/MIDC | 14.4837 | 121.2042 | 0.13 | Terrestrial Optical Fiber Drop | 0.96 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1881 | 2 | 881 | 1881 | 0305408034 | Region III (Central Luzon) | Pampanga | Lubao | Santa Cruz | 14.9104 | 120.5627 | U | 18780 | 4695 | 1409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-01043 | Edgepoint | 14.9083 | 120.5583 | 0.53 | Terrestrial Optical Fiber Drop | 0.96 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1882 | 2 | 882 | 1882 | 0102822010 | Region I (Ilocos Region) | Ilocos Norte | Solsona | Laureta | 18.0912 | 120.7697 | R | 1471 | 397 | 119 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00044 | Edgepoint | 18.0904 | 120.7705 | 0.11 | Terrestrial Optical Fiber Drop | 0.96 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1883 | 2 | 883 | 1883 | 0402109046 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bayan Luma VII | 14.4074 | 120.9362 | U | 4350 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01919-C08 | PTCI/MIDC | 14.4412 | 120.9522 | 0.45 | Terrestrial Optical Fiber Drop | 0.48 | 4.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1884 | 2 | 884 | 1884 | 0102820014 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Lucas | 18.153 | 120.5956 | R | 1299 | 351 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.88 | Terrestrial Optical Fiber Drop | 1.94 | 1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1885 | 2 | 885 | 1885 | 0403425008 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Magsaysay | 14.3391 | 121.0332 | U | 14023 | 4249 | 1275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02096-C08 | PTCI/MIDC | 14.3349 | 121.0294 | 0.63 | Terrestrial Optical Fiber Drop | 0.96 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1886 | 2 | 886 | 1886 | 0405603005 | Region IV-A (CALABARZON) | Quezon | Atimonan | Barangay Zone 2 | 14.0011 | 121.9165 | U | 2700 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 0.9 | Terrestrial Optical Fiber Drop | 0.96 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1887 | 2 | 887 | 1887 | 0304929006 | Region III (Central Luzon) | Nueva Ecija | Santo Domingo | Cabugao | 15.5848 | 120.8747 | R | 2661 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0031 | PTCI/MIDC | 15.5809 | 120.8782 | 0.58 | Terrestrial Optical Fiber Drop | 0.96 | 4.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1888 | 2 | 888 | 1888 | 0403428001 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Aplaya | 14.318 | 121.1211 | U | 17383 | 5267 | 1580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01994-C08 | PTCI/MIDC | 14.3131 | 121.1213 | 0.54 | Terrestrial Optical Fiber Drop | 0.97 | 2.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1889 | 2 | 889 | 1889 | 0603043004 | Region VI (Western Visayas) | Iloilo | Santa Barbara | Balabag | 10.776 | 122.5033 | R | 3784 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0072 | PTCI/MIDC | 10.8243 | 122.5364 | 0.76 | Terrestrial Optical Fiber Drop | 4.35 | 1.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1890 | 2 | 890 | 1890 | 1606701001 | Region XIII (Caraga) | Surigao del Norte | Alegria | Poblacion | 9.4662 | 125.5743 | R | 1927 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 3.43 | Terrestrial Optical Fiber Drop | 0.97 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1891 | 2 | 891 | 1891 | 0907322046 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Tuburan | 7.8365 | 123.4459 | U | 9989 | 2561 | 768 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH090131 | FTAP Globe | 7.8452 | 123.4458 | 0.97 | Terrestrial Optical Fiber Drop | 0.96 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1892 | 2 | 892 | 1892 | 0500508033 | Region V (Bicol Region) | Albay | City of Ligao | Nabonton | 13.2522 | 123.5911 | R | 2858 | 697 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050153 | FTAP Globe | 13.2564 | 123.5878 | 0.59 | Terrestrial Optical Fiber Drop | 0.96 | 1.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1893 | 2 | 893 | 1893 | 0403411008 | Region IV-A (CALABARZON) | Laguna | Los Baños | Maahas | 14.1774 | 121.2511 | U | 9630 | 2918 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0017 | PTCI/MIDC | 14.1741 | 121.2459 | 0.67 | Terrestrial Optical Fiber Drop | 0.96 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1894 | 2 | 894 | 1894 | 0301412006 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Calvario | 14.7335 | 120.961 | U | 5304 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01106-B07 | PTCI/MIDC | 14.7353 | 120.9581 | 0.37 | Terrestrial Optical Fiber Drop | 0.96 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1895 | 2 | 895 | 1895 | 0603044003 | Region VI (Western Visayas) | Iloilo | Sara | Alibayog | 11.2533 | 123.0083 | R | 1741 | 458 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 0.84 | Terrestrial Optical Fiber Drop | 0.96 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1896 | 2 | 896 | 1896 | 0304925006 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Poblacion | 15.307 | 120.905 | U | 8135 | 2324 | 697 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02257 | Edgepoint | 15.3113 | 120.9036 | 0.5 | Terrestrial Optical Fiber Drop | 0.45 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1897 | 2 | 897 | 1897 | 0702232002 | Region VII (Central Visayas) | Cebu | Minglanilla | Calajo-an | 10.2397 | 123.8028 | U | 13251 | 3487 | 1046 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0128 | PTCI/MIDC | 10.2407 | 123.8002 | 0.31 | Terrestrial Optical Fiber Drop | 0.97 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1898 | 2 | 898 | 1898 | 0102803017 | Region I (Ilocos Region) | Ilocos Norte | Badoc | Lacuben | 17.9309 | 120.4762 | R | 1729 | 467 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4944 | FTAP Smart | 17.9248 | 120.4771 | 0.68 | Terrestrial Optical Fiber Drop | 0.97 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1899 | 2 | 899 | 1899 | 0506209025 | Region V (Bicol Region) | Sorsogon | Irosin | San Pedro | 12.7016 | 124.0267 | R | 3332 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050227 | FTAP Globe | 12.701 | 124.0368 | 1.1 | Terrestrial Optical Fiber Drop | 0.97 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1900 | 2 | 900 | 1900 | 1705215031 | MIMAROPA Region | Oriental Mindoro | Victoria | San Isidro | 13.1604 | 121.2851 | R | 2054 | 526 | 158 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170084 | FTAP Globe | 13.1757 | 121.2767 | 1.93 | Terrestrial Optical Fiber Drop | 0.97 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1901 | 2 | 901 | 1901 | 0301403026 | Region III (Central Luzon) | Bulacan | Baliuag | Tiaong | 14.9442 | 120.8961 | U | 6126 | 1750 | 525 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00966-B07 | PTCI/MIDC | 14.9475 | 120.8906 | 0.69 | Terrestrial Optical Fiber Drop | 0.97 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1902 | 2 | 902 | 1902 | 0501724031 | Region V (Bicol Region) | Camarines Sur | City of Naga | Tinago | 13.6256 | 123.1908 | U | 2897 | 689 | 207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0001 | PTCI/MIDC | 13.6235 | 123.1923 | 0.28 | Terrestrial Optical Fiber Drop | 0.97 | 0.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1903 | 2 | 903 | 1903 | 0105522028 | Region I (Ilocos Region) | Pangasinan | Lingayen | Poblacion | 16.0316 | 120.231 | U | 12958 | 3599 | 1080 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010153 | FTAP Globe | 16.0313 | 120.2316 | 0.08 | Terrestrial Optical Fiber Drop | 0.97 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1904 | 2 | 904 | 1904 | 0401005097 | Region IV-A (CALABARZON) | Batangas | Batangas City | Santa Rita Karsada | 13.7783 | 121.0411 | U | 20924 | 5812 | 1744 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03083-C08 | PTCI/MIDC | 13.7803 | 121.0482 | 0.8 | Terrestrial Optical Fiber Drop | 0.97 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1905 | 2 | 905 | 1905 | 0603044026 | Region VI (Western Visayas) | Iloilo | Sara | Labigan | 11.2468 | 123.0188 | R | 1376 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILO_0004 | LDIC | 11.2454 | 123.022 | 0.39 | Terrestrial Optical Fiber Drop | 0.97 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1906 | 2 | 906 | 1906 | 0402106028 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Esteban | 14.3204 | 120.9564 | R | 4825 | 1419 | 426 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0023 | PTCI/MIDC | 14.2938 | 120.9461 | 0.59 | Terrestrial Optical Fiber Drop | 1.34 | 2.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1907 | 2 | 907 | 1907 | 0500516003 | Region V (Bicol Region) | Albay | Santo Domingo | Calayucay | 13.2381 | 123.786 | R | 1788 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050154 | FTAP Globe | 13.2479 | 123.7822 | 1.16 | Terrestrial Optical Fiber Drop | 0.97 | 0.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1908 | 2 | 908 | 1908 | 1004321008 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Luyongbonbon | 8.5281 | 124.5707 | U | 3274 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0044 | PTCI/MIDC | 8.5331 | 124.5712 | 0.56 | Terrestrial Optical Fiber Drop | 0.98 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1909 | 2 | 909 | 1909 | 0102820016 | Region I (Ilocos Region) | Ilocos Norte | San Nicolas | San Miguel | 18.1708 | 120.6026 | R | 1725 | 466 | 140 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01231-B05 | PTCI/MIDC | 18.1721 | 120.5945 | 0.86 | Terrestrial Optical Fiber Drop | 0.97 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1910 | 2 | 910 | 1910 | 1030500049 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Gusa | 8.4764 | 124.6828 | U | 29500 | 8194 | 2458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0018 | PTCI/MIDC | 8.4727 | 124.6825 | 0.4 | Terrestrial Optical Fiber Drop | 0.97 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1911 | 2 | 911 | 1911 | 1102403003 | Region XI (Davao Region) | Davao del Sur | City of Digos | San Jose | 6.7335 | 125.3568 | U | 7263 | 2136 | 641 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0068 | PTCI/MIDC | 6.7353 | 125.3569 | 0.2 | Terrestrial Optical Fiber Drop | 0.97 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1912 | 2 | 912 | 1912 | 0731100006 | Region VII (Central Visayas) | Cebu | City of Lapu-Lapu | Buaya | 10.3182 | 123.9967 | U | 19086 | 5453 | 1636 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0180 | PTCI/MIDC | 10.3173 | 123.9947 | 0.25 | Terrestrial Optical Fiber Drop | 0.98 | 5.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1913 | 2 | 913 | 1913 | 0604530004 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Batuan | 10.4746 | 122.8216 | R | 1127 | 304 | 91 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 2.56 | Terrestrial Optical Fiber Drop | 0.98 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1914 | 2 | 914 | 1914 | 1430300012 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Brookside | 16.4215 | 120.6018 | R | 1814 | 477 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBEG0017 | PTCI/MIDC | 16.4226 | 120.6009 | 0.16 | Terrestrial Optical Fiber Drop | 0.98 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1915 | 2 | 915 | 1915 | 0603005010 | Region VI (Western Visayas) | Iloilo | Balasan | Kinalkalan | 11.4765 | 123.0825 | R | 1333 | 350 | 105 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 2.06 | Terrestrial Optical Fiber Drop | 0.98 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1916 | 2 | 916 | 1916 | 0506213011 | Region V (Bicol Region) | Sorsogon | Pilar | Calongay | 12.9409 | 123.6719 | R | 1958 | 489 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 2.22 | Terrestrial Optical Fiber Drop | 0.98 | 9.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1917 | 2 | 917 | 1917 | 0702215016 | Region VII (Central Visayas) | Cebu | Carmen | Poblacion | 10.5851 | 124.0161 | U | 5569 | 1465 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 0.46 | Terrestrial Optical Fiber Drop | 0.98 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1918 | 2 | 918 | 1918 | 1102403007 | Region XI (Davao Region) | Davao del Sur | City of Digos | Dawis | 6.7293 | 125.3649 | U | 6025 | 1772 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSG0143 | PTCI/MIDC | 6.7257 | 125.3721 | 0.88 | Terrestrial Optical Fiber Drop | 0.98 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1919 | 2 | 919 | 1919 | 0403403016 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Poblacion | 14.3295 | 121.078 | U | 5494 | 1664 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02089-C08 | PTCI/MIDC | 14.3186 | 121.0757 | 0.96 | Terrestrial Optical Fiber Drop | 1.04 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1920 | 2 | 920 | 1920 | 0701230045 | Region VII (Central Visayas) | Bohol | Loon | Napo | 9.7996 | 123.7911 | R | 1435 | 358 | 107 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0023 | PTCI/MIDC | 9.7973 | 123.7924 | 0.3 | Terrestrial Optical Fiber Drop | 0.98 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1921 | 2 | 921 | 1921 | 0701205008 | Region VII (Central Visayas) | Bohol | Baclayon | Montana | 9.6251 | 123.9218 | R | 1896 | 474 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 3.88 | Terrestrial Optical Fiber Drop | 0.98 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1922 | 2 | 922 | 1922 | 0102815011 | Region I (Ilocos Region) | Ilocos Norte | Pagudpud | Pasaleng | 18.5487 | 120.9363 | R | 1820 | 491 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-00007 | Edgepoint | 18.5501 | 120.9325 | 0.43 | Terrestrial Optical Fiber Drop | 0.98 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1923 | 2 | 923 | 1923 | 0301410004 | Region III (Central Luzon) | Bulacan | City of Malolos | Bagna | 14.8271 | 120.8213 | U | 5171 | 1477 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02487 | Edgepoint | 14.8248 | 120.8221 | 0.27 | Terrestrial Optical Fiber Drop | 0.98 | 2.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1924 | 2 | 924 | 1924 | 0702215008 | Region VII (Central Visayas) | Cebu | Carmen | Dawis Sur | 10.5679 | 124.0198 | R | 2706 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0024 | PTCI/MIDC | 10.5658 | 124.018 | 0.31 | Terrestrial Optical Fiber Drop | 0.98 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1925 | 2 | 925 | 1925 | 0402118044 | Region IV-A (CALABARZON) | Cavite | Silang | Santol | 14.1694 | 120.9532 | R | 2419 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02172-C08 | PTCI/MIDC | 14.1692 | 120.9623 | 0.98 | Terrestrial Optical Fiber Drop | 0.98 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1926 | 2 | 926 | 1926 | 1430300016 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Camp Allen | 16.4072 | 120.5976 | R | 2343 | 616 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_BGT_0024 | LDIC | 16.4025 | 120.6048 | 0.2 | Terrestrial Optical Fiber Drop | 0.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1927 | 2 | 927 | 1927 | 0603037036 | Region VI (Western Visayas) | Iloilo | Pototan | Naslo | 10.9502 | 122.6334 | R | 1637 | 430 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.39 | Terrestrial Optical Fiber Drop | 0.98 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1928 | 2 | 928 | 1928 | 0506213033 | Region V (Bicol Region) | Sorsogon | Pilar | Marifosque | 12.9247 | 123.6688 | R | 2522 | 630 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050211 | FTAP Globe | 12.922 | 123.6653 | 0.48 | Terrestrial Optical Fiber Drop | 0.99 | 10.91 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1929 | 2 | 929 | 1929 | 0803702035 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Salvacion Poblacion | 11.2082 | 124.8492 | R | 1215 | 319 | 96 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0003 | PTCI/MIDC | 11.2031 | 124.8469 | 0.61 | Terrestrial Optical Fiber Drop | 0.98 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1930 | 2 | 930 | 1930 | 0403430001 | Region IV-A (CALABARZON) | Laguna | Victoria | Banca-banca | 14.2024 | 121.3455 | R | 4281 | 1297 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02113-C08 | PTCI/MIDC | 14.2028 | 121.346 | 0.07 | Terrestrial Optical Fiber Drop | 0.99 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1931 | 2 | 931 | 1931 | 0401030008 | Region IV-A (CALABARZON) | Batangas | Talisay | Caloocan | 14.0882 | 120.9794 | R | 1793 | 498 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S2747 | FTAP Smart | 14.0934 | 121.0172 | 0.83 | Terrestrial Optical Fiber Drop | 4.25 | 3.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1932 | 2 | 932 | 1932 | 0401028011 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | San Isidro Norte | 14.0598 | 121.1806 | R | 2475 | 687 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 1.07 | Terrestrial Optical Fiber Drop | 3.44 | 2.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1933 | 2 | 933 | 1933 | 0405622010 | Region IV-A (CALABARZON) | Quezon | Lopez | Bebito | 13.8924 | 122.2695 | R | 1659 | 436 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0001 | PTCI/MIDC | 13.8896 | 122.2685 | 0.34 | Terrestrial Optical Fiber Drop | 0.98 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1934 | 2 | 934 | 1934 | 0504111016 | Region V (Bicol Region) | Masbate | City of Masbate | F. Magallanes | 12.3635 | 123.6237 | U | 3376 | 823 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03024-C10 | PTCI/MIDC | 12.359 | 123.6263 | 0.58 | Terrestrial Optical Fiber Drop | 0.98 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1935 | 2 | 935 | 1935 | 0405630022 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 4 Parang | 13.9714 | 121.6911 | R | 2057 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.71 | Terrestrial Optical Fiber Drop | 0.98 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1936 | 2 | 936 | 1936 | 0405618032 | Region IV-A (CALABARZON) | Quezon | Guinayangan | Manggagawa | 13.8948 | 122.4536 | R | 2793 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1413 | FTAP Smart | 13.892 | 122.4548 | 0.34 | Terrestrial Optical Fiber Drop | 0.99 | 11.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1937 | 2 | 937 | 1937 | 0603037031 | Region VI (Western Visayas) | Iloilo | Pototan | Primitivo Ledesma Ward | 10.9407 | 122.6341 | R | 2236 | 588 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.71 | Terrestrial Optical Fiber Drop | 0.99 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1938 | 2 | 938 | 1938 | 0402103061 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Salinas II | 14.4384 | 120.9423 | U | 6082 | 1788 | 536 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1120 | FTAP Smart | 14.4377 | 120.9409 | 0.17 | Terrestrial Optical Fiber Drop | 0.99 | 1.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1939 | 2 | 939 | 1939 | 0402109069 | Region IV-A (CALABARZON) | Cavite | City of Imus | Mariano Espeleta I | 14.4023 | 120.9403 | R | 1474 | 433 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01910-C08 | PTCI/MIDC | 14.4264 | 120.8759 | 0.14 | Terrestrial Optical Fiber Drop | 0.52 | 4.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1940 | 2 | 940 | 1940 | 0405801007 | Region IV-A (CALABARZON) | Rizal | Angono | Poblacion Ibaba | 14.5297 | 121.1534 | R | 3472 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01844 | Edgepoint | 14.5376 | 121.1542 | 0.13 | Terrestrial Optical Fiber Drop | 0.28 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1941 | 2 | 941 | 1941 | 1130700021 | Region XI (Davao Region) | Davao del Sur | City of Davao | Buhangin | 7.1131 | 125.6312 | U | 70251 | 20662 | 6199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0043 | PTCI/MIDC | 7.1097 | 125.6319 | 0.39 | Terrestrial Optical Fiber Drop | 0.99 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1942 | 2 | 942 | 1942 | 0301408011 | Region III (Central Luzon) | Bulacan | Guiguinto | Tabang | 14.8315 | 120.8641 | U | 11984 | 3424 | 1027 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01151 | Edgepoint | 14.8322 | 120.8602 | 0.43 | Terrestrial Optical Fiber Drop | 0.99 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1943 | 2 | 943 | 1943 | 1705205062 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Suqui | 13.4179 | 121.2021 | R | 3824 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170053 | FTAP Globe | 13.4297 | 121.1964 | 1.45 | Terrestrial Optical Fiber Drop | 0.99 | 6.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1944 | 2 | 944 | 1944 | 1430300145 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Liwanag-Loakan | 16.4072 | 120.5969 | R | 4868 | 1281 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00357 | Edgepoint | 16.3305 | 120.6474 | 1.75 | Terrestrial Optical Fiber Drop | 0.57 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1945 | 2 | 945 | 1945 | 0103306021 | Region I (Ilocos Region) | La Union | Bangar | Nagsabaran | 16.8951 | 120.4158 | R | 1487 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01379-B05 | PTCI/MIDC | 16.8907 | 120.4231 | 0.92 | Terrestrial Optical Fiber Drop | 0.99 | 0.85 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1946 | 2 | 946 | 1946 | 0506216051 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Poblacion | 13.0401 | 124.041 | R | 4739 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050199 | FTAP Globe | 13.0361 | 124.0408 | 0.45 | Terrestrial Optical Fiber Drop | 0.99 | 7.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1947 | 2 | 947 | 1947 | 0405801012 | Region IV-A (CALABARZON) | Rizal | Angono | San Vicente | 14.523 | 121.1468 | U | 13646 | 3790 | 1137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00848-A04 | PTCI/MIDC | 14.5239 | 121.1457 | 0.15 | Terrestrial Optical Fiber Drop | 0.99 | 0.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1948 | 2 | 948 | 1948 | 0102817014 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Naglicuan | 18.3145 | 120.6034 | R | 1777 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01229-B05 | PTCI/MIDC | 18.3313 | 120.6116 | 2.06 | Terrestrial Optical Fiber Drop | 0.99 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1949 | 2 | 949 | 1949 | 0105538011 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Leet | 15.9913 | 120.4645 | U | 7333 | 2036 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 1.12 | Terrestrial Optical Fiber Drop | 0.99 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1950 | 2 | 950 | 1950 | 0403405046 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Punta | 14.1771 | 121.1178 | U | 8025 | 2431 | 729 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040271 | FTAP Globe | 14.1786 | 121.1216 | 0.43 | Terrestrial Optical Fiber Drop | 0.99 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1951 | 2 | 951 | 1951 | 1731500048 | MIMAROPA Region | Palawan | City of Puerto Princesa | San Pedro | 9.7635 | 118.7347 | U | 26694 | 7214 | 2164 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S2216 | FTAP Smart | 9.7591 | 118.7398 | 0.74 | Terrestrial Optical Fiber Drop | 0.99 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1952 | 2 | 952 | 1952 | 0402109011 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bucandala I | 14.4052 | 120.9265 | U | 10459 | 3076 | 923 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0004 | LDIC | 14.4037 | 120.95 | 0.39 | Terrestrial Optical Fiber Drop | 1.53 | 4.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1953 | 2 | 953 | 1953 | 0401015002 | Region IV-A (CALABARZON) | Batangas | Lobo | Balatbat | 13.6563 | 121.2066 | R | 2515 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040610 | FTAP Globe | 13.6527 | 121.201 | 0.73 | Terrestrial Optical Fiber Drop | 1 | 18.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1954 | 2 | 954 | 1954 | 0504111011 | Region V (Bicol Region) | Masbate | City of Masbate | Cagay | 12.3647 | 123.6225 | R | 1782 | 434 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03024-C10 | PTCI/MIDC | 12.359 | 123.6263 | 0.76 | Terrestrial Optical Fiber Drop | 1 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1955 | 2 | 955 | 1955 | 0103309015 | Region I (Ilocos Region) | La Union | Caba | Santiago Sur | 16.4269 | 120.338 | R | 2089 | 564 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-02357 | Edgepoint | 16.4321 | 120.3431 | 0.8 | Terrestrial Optical Fiber Drop | 0.99 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1956 | 2 | 956 | 1956 | 0105532005 | Region I (Ilocos Region) | Pangasinan | City of San Carlos | Antipangol | 15.9313 | 120.2728 | R | 1816 | 504 | 151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010191 | FTAP Globe | 15.94 | 120.2689 | 1.06 | Terrestrial Optical Fiber Drop | 1 | 7.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1957 | 2 | 957 | 1957 | 0405601011 | Region IV-A (CALABARZON) | Quezon | Agdangan | Sildora | 13.8602 | 121.9376 | R | 1055 | 277 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040528 | FTAP Globe | 13.8765 | 121.9123 | 0.99 | Terrestrial Optical Fiber Drop | 2.84 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1958 | 2 | 958 | 1958 | 0403403007 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Ganado | 14.285 | 121.0804 | U | 7085 | 2146 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01998-C08 | PTCI/MIDC | 14.2831 | 121.0762 | 0.5 | Terrestrial Optical Fiber Drop | 1 | 0.73 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1959 | 2 | 959 | 1959 | 1030500044 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Carmen | 8.4683 | 124.6314 | U | 79167 | 21990 | 6597 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0014 | PTCI/MIDC | 8.4674 | 124.6312 | 0.11 | Terrestrial Optical Fiber Drop | 1 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1960 | 2 | 960 | 1960 | 0731300001 | Region VII (Central Visayas) | Cebu | City of Mandaue | Alang-alang | 10.3464 | 123.9407 | U | 11507 | 3287 | 986 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0117 | PTCI/MIDC | 10.3409 | 123.9486 | 0.7 | Terrestrial Optical Fiber Drop | 0.85 | 0.81 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1961 | 2 | 961 | 1961 | 0307706023 | Region III (Central Luzon) | Aurora | Dipaculao | South Poblacion | 15.8441 | 121.5357 | R | 1424 | 374 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3804 | FTAP Smart | 15.8454 | 121.5368 | 0.19 | Terrestrial Optical Fiber Drop | 1 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1962 | 2 | 962 | 1962 | 0403427002 | Region IV-A (CALABARZON) | Laguna | Santa Maria | Bagong Pook | 14.4708 | 121.4295 | R | 2532 | 767 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040090 | FTAP Globe | 14.4653 | 121.4312 | 0.64 | Terrestrial Optical Fiber Drop | 0.99 | 2.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1963 | 2 | 963 | 1963 | 0205005025 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Salvacion | 16.4791 | 121.1499 | R | 4495 | 1182 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNVG0017 | PTCI/MIDC | 16.4767 | 121.1461 | 0.49 | Terrestrial Optical Fiber Drop | 1 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1964 | 2 | 964 | 1964 | 0103307037 | Region I (Ilocos Region) | La Union | Bauang | Taberna | 16.528 | 120.3338 | R | 2113 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010100 | FTAP Globe | 16.5519 | 120.3302 | 1.41 | Terrestrial Optical Fiber Drop | 0.82 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1965 | 2 | 965 | 1965 | 0305415019 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Pasig | 15.1088 | 120.5524 | U | 5346 | 1336 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00793 | Edgepoint | 15.2255 | 120.6073 | 0.54 | Terrestrial Optical Fiber Drop | 2.14 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1966 | 2 | 966 | 1966 | 0403404005 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Bigaa | 14.2911 | 121.1285 | U | 14979 | 4539 | 1362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02035-C08 | PTCI/MIDC | 14.2963 | 121.1289 | 0.58 | Terrestrial Optical Fiber Drop | 1 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1967 | 2 | 967 | 1967 | 0600407010 | Region VI (Western Visayas) | Aklan | Kalibo | Mabilo | 11.7061 | 122.3644 | R | 2655 | 680 | 204 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.51 | Terrestrial Optical Fiber Drop | 1 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1968 | 2 | 968 | 1968 | 0403425014 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | San Antonio | 14.3534 | 121.0411 | U | 65077 | 19720 | 5916 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0010 | PTCI/MIDC | 14.3568 | 121.0417 | 0.38 | Terrestrial Optical Fiber Drop | 1 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1969 | 2 | 969 | 1969 | 0301420034 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gumaoc West | 14.7995 | 121.0611 | U | 9287 | 2653 | 796 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00992-B07 | PTCI/MIDC | 14.8014 | 121.0618 | 0.23 | Terrestrial Optical Fiber Drop | 1 | 0.83 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1970 | 2 | 970 | 1970 | 0403420002 | Region IV-A (CALABARZON) | Laguna | Pakil | Banilan | 14.3814 | 121.4003 | R | 2020 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | S1205 | FTAP Smart | 14.4157 | 121.4066 | 3.88 | Terrestrial Optical Fiber Drop | 1 | 6.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1971 | 2 | 971 | 1971 | 0203114057 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Marana I | 17.1592 | 121.922 | R | 1809 | 476 | 143 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020060 | FTAP Globe | 17.1618 | 121.9209 | 0.31 | Terrestrial Optical Fiber Drop | 1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1972 | 2 | 972 | 1972 | 0300803021 | Region III (Central Luzon) | Bataan | City of Balanga | Tenejero | 14.6787 | 120.533 | U | 9639 | 2677 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N2086 | FTAP Smart | 14.6763 | 120.5321 | 0.28 | Terrestrial Optical Fiber Drop | 1 | 0.96 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1973 | 2 | 973 | 1973 | 0405608005 | Region IV-A (CALABARZON) | Quezon | Candelaria | Bukal Sur | 13.9363 | 121.3886 | U | 7573 | 1992 | 598 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0015 | PTCI/MIDC | 13.9343 | 121.391 | 0.35 | Terrestrial Optical Fiber Drop | 2.35 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1974 | 2 | 974 | 1974 | 0401012024 | Region IV-A (CALABARZON) | Batangas | Lemery | Matingain I | 13.909 | 120.8868 | R | 3885 | 1079 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040501 | FTAP Globe | 13.9093 | 120.8899 | 0.34 | Terrestrial Optical Fiber Drop | 4.25 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1975 | 2 | 975 | 1975 | 0401005012 | Region IV-A (CALABARZON) | Batangas | Batangas City | Bolbok | 13.7741 | 121.046 | U | 13167 | 3657 | 1097 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03083-C08 | PTCI/MIDC | 13.7803 | 121.0482 | 0.73 | Terrestrial Optical Fiber Drop | 1.66 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1976 | 2 | 976 | 1976 | 1630400080 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Sumilihon | 8.9914 | 125.6133 | R | 5102 | 1244 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130066 | FTAP Globe | 8.9937 | 125.6116 | 0.32 | Terrestrial Optical Fiber Drop | 3.72 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1977 | 2 | 977 | 1977 | 0600613023 | Region VI (Western Visayas) | Antique | San Jose | Maybato Norte | 10.7305 | 121.9555 | R | 4778 | 1225 | 368 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0015 | PTCI/MIDC | 10.7278 | 121.9577 | 0.38 | Terrestrial Optical Fiber Drop | 4.02 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1978 | 2 | 978 | 1978 | 0403428005 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Dita | 14.2815 | 121.1122 | U | 37982 | 11509 | 3453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02001-C08 | PTCI/MIDC | 14.291 | 121.1178 | 1.21 | Terrestrial Optical Fiber Drop | 1.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1979 | 2 | 979 | 1979 | 0300811019 | Region III (Central Luzon) | Bataan | Pilar | Panilao | 14.6699 | 120.5512 | U | 6118 | 1699 | 510 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-01437 | Edgepoint | 14.6683 | 120.5477 | 0.41 | Terrestrial Optical Fiber Drop | 1.66 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1980 | 2 | 980 | 1980 | 0300804035 | Region III (Central Luzon) | Bataan | Dinalupihan | San Pablo | 14.8526 | 120.3788 | U | 8080 | 2244 | 673 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030578 | FTAP Globe | 14.8566 | 120.3772 | 0.47 | Terrestrial Optical Fiber Drop | 2.06 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1981 | 2 | 981 | 1981 | 1004317012 | Region X (Northern Mindanao) | Misamis Oriental | Magsaysay | Kibungsod | 9.0065 | 125.2059 | R | 3441 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0063 | PTCI/MIDC | 9.007 | 125.2065 | 0.09 | Terrestrial Optical Fiber Drop | 3.02 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1982 | 2 | 982 | 1982 | 1630400093 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | De Oro | 8.9425 | 125.5157 | R | 2466 | 601 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANG0011 | PTCI/MIDC | 8.9395 | 125.5155 | 0.33 | Terrestrial Optical Fiber Drop | 1.51 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1983 | 2 | 983 | 1983 | 0600613028 | Region VI (Western Visayas) | Antique | San Jose | San Fernando | 10.7763 | 121.9416 | R | 3396 | 870 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060029 | FTAP BTS | 10.7722 | 121.9445 | 0.56 | Terrestrial Optical Fiber Drop | 1.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1984 | 2 | 984 | 1984 | 0702201007 | Region VII (Central Visayas) | Cebu | Alcantara | Poblacion | 9.9743 | 123.4054 | R | 2773 | 729 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 2.43 | Terrestrial Optical Fiber Drop | 2.87 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1985 | 2 | 985 | 1985 | 0401003043 | Region IV-A (CALABARZON) | Batangas | Balayan | Sambat | 13.9508 | 120.7055 | R | 3169 | 880 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S0870 | FTAP Smart | 13.9497 | 120.7097 | 0.47 | Terrestrial Optical Fiber Drop | 2.57 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1986 | 2 | 986 | 1986 | 0603044002 | Region VI (Western Visayas) | Iloilo | Sara | Aldeguer | 11.2187 | 122.9774 | R | 2046 | 538 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0074 | PTCI/MIDC | 11.2587 | 123.0138 | 1.14 | Terrestrial Optical Fiber Drop | 5.4 | 2.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1987 | 2 | 987 | 1987 | 0702251029 | Region VII (Central Visayas) | Cebu | City of Toledo | Poog | 10.3219 | 123.6856 | U | 7242 | 1905 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0165 | PTCI/MIDC | 10.3178 | 123.6875 | 0.5 | Terrestrial Optical Fiber Drop | 1.3 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1988 | 2 | 988 | 1988 | 1705205009 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Bucayao | 13.3064 | 121.1921 | R | 2672 | 685 | 206 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170072 | FTAP Globe | 13.3066 | 121.1896 | 0.27 | Terrestrial Optical Fiber Drop | 1.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1989 | 2 | 989 | 1989 | 0500510004 | Region V (Bicol Region) | Albay | Malinao | Balza | 13.4015 | 123.7032 | R | 2287 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050124 | FTAP Globe | 13.3997 | 123.7064 | 0.4 | Terrestrial Optical Fiber Drop | 1.02 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1990 | 2 | 990 | 1990 | 0803736018 | Region VIII (Eastern Visayas) | Leyte | Merida | Puerto Bello | 10.9859 | 124.5313 | R | 4484 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080193 | FTAP BTS | 11.0011 | 124.5391 | 1.9 | Terrestrial Optical Fiber Drop | 5.09 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1991 | 2 | 991 | 1991 | 0305421002 | Region III (Central Luzon) | Pampanga | Sto. Tomas | Moras De La Paz | 15.0159 | 120.7103 | U | 5823 | 1455 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00909 | Edgepoint | 15.0517 | 120.6663 | 0.27 | Terrestrial Optical Fiber Drop | 0.88 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1992 | 2 | 992 | 1992 | 1001321028 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Sinabuagan | 7.9093 | 125.0941 | R | 2547 | 670 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100077 | FTAP BTS | 7.9209 | 125.0869 | 0.59 | Terrestrial Optical Fiber Drop | 0.44 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1993 | 2 | 993 | 1993 | 0403423001 | Region IV-A (CALABARZON) | Laguna | Rizal | Antipolo | 14.1108 | 121.3814 | R | 2871 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040311 | FTAP Globe | 14.1103 | 121.3953 | 1.5 | Terrestrial Optical Fiber Drop | 1.22 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1994 | 2 | 994 | 1994 | 0601905008 | Region VI (Western Visayas) | Capiz | Ivisan | Malocloc Norte | 11.5056 | 122.6797 | R | 2526 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060230 | FTAP Globe | 11.5064 | 122.6843 | 0.51 | Terrestrial Optical Fiber Drop | 2.32 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1995 | 2 | 995 | 1995 | 0702251037 | Region VII (Central Visayas) | Cebu | City of Toledo | Talavera | 10.4124 | 123.6662 | U | 7906 | 2080 | 624 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0174 | PTCI/MIDC | 10.4192 | 123.6706 | 0.9 | Terrestrial Optical Fiber Drop | 1.78 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1996 | 2 | 996 | 1996 | 0702243002 | Region VII (Central Visayas) | Cebu | San Remigio | Argawanon | 11.0703 | 123.9573 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0021 | PTCI/MIDC | 11.0674 | 123.9638 | 0.78 | Terrestrial Optical Fiber Drop | 2.39 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1997 | 2 | 997 | 1997 | 0405647031 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Isabang | 13.9644 | 121.5653 | U | 12686 | 3338 | 1001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040406 | FTAP Globe | 13.9695 | 121.5636 | 0.59 | Terrestrial Optical Fiber Drop | 2.32 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1998 | 2 | 998 | 1998 | 0300806008 | Region III (Central Luzon) | Bataan | Limay | Reformista | 14.5637 | 120.5955 | U | 5400 | 1500 | 450 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030629 | FTAP Globe | 14.568 | 120.5957 | 0.47 | Terrestrial Optical Fiber Drop | 1.21 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-1999 | 2 | 999 | 1999 | 0300804021 | Region III (Central Luzon) | Bataan | Dinalupihan | New San Jose | 14.8806 | 120.4618 | U | 6942 | 1928 | 578 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0396 | FTAP Smart | 14.8836 | 120.4592 | 0.43 | Terrestrial Optical Fiber Drop | 1.59 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2000 | 2 | 1000 | 2000 | 0702223033 | Region VII (Central Visayas) | Cebu | Danao City | Sabang | 10.4974 | 124.0309 | U | 16515 | 4346 | 1304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0185 | PTCI/MIDC | 10.4925 | 124.0289 | 0.59 | Terrestrial Optical Fiber Drop | 2.76 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)

## Batch 3 (2,001 - 3,000)
5G FWA Candidate Site Schedule — Batch 3 (Expansion 1,000 Sites)
Carrier-Grade Candidate Siting Data for Turnkey Bidding (Lots 1, 2, 4, 5) ¦ Band n50 SA Architecture
Site ID | Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Households | Target Subscribers | Carrier Spectrum | Initial BTS | Civil Siting Category | Tower Screening Class | Nearest Tower ID | Nearest TowerCo | Nearest Tower Latitude | Nearest Tower Longitude | Dist to Tower (km) | Transmission Medium | Dist to Node (km) | Dist to Line (km) | Power Arrangement
FWA-SITE-2001 | 3 | 1 | 2001 | 0501726001 | Region V (Bicol Region) | Camarines Sur | Pamplona | Batang | 13.5678 | 123.0601 | R | 2324 | 553 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050103 | FTAP Globe | 13.5641 | 123.0576 | 0.49 | Terrestrial Optical Fiber Drop | 1.14 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2002 | 3 | 2 | 2002 | 0702250015 | Region VII (Central Visayas) | Cebu | City of Talisay | San Roque | 10.2565 | 123.8604 | U | 22512 | 5924 | 1777 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0160 | PTCI/MIDC | 10.2575 | 123.8595 | 0.15 | Terrestrial Optical Fiber Drop | 2.22 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2003 | 3 | 3 | 2003 | 0501728017 | Region V (Bicol Region) | Camarines Sur | Pili | San Agustin | 13.5679 | 123.267 | U | 5708 | 1359 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03384-C10 | PTCI/MIDC | 13.5661 | 123.2692 | 0.31 | Terrestrial Optical Fiber Drop | 1.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2004 | 3 | 4 | 2004 | 0702250007 | Region VII (Central Visayas) | Cebu | City of Talisay | Lawaan I | 10.2586 | 123.8222 | U | 10935 | 2877 | 863 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0159 | PTCI/MIDC | 10.2524 | 123.8198 | 0.73 | Terrestrial Optical Fiber Drop | 1.96 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2005 | 3 | 5 | 2005 | 0401034008 | Region IV-A (CALABARZON) | Batangas | Tuy | Luntal | 14.034 | 120.7094 | R | 3732 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040361 | FTAP Globe | 14.0458 | 120.6994 | 1.69 | Terrestrial Optical Fiber Drop | 2.48 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2006 | 3 | 6 | 2006 | 0702241002 | Region VII (Central Visayas) | Cebu | San Fernando | Balud | 10.1486 | 123.6949 | U | 5062 | 1332 | 400 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 1.26 | Terrestrial Optical Fiber Drop | 2.09 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2007 | 3 | 7 | 2007 | 0401021001 | Region IV-A (CALABARZON) | Batangas | Rosario | Alupay | 13.8441 | 121.2947 | R | 4434 | 1231 | 369 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040548 | FTAP Globe | 13.8424 | 121.2877 | 0.77 | Terrestrial Optical Fiber Drop | 2.82 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2008 | 3 | 8 | 2008 | 0305411024 | Region III (Central Luzon) | Pampanga | Magalang | Santo Rosario | 15.2449 | 120.6384 | U | 5554 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00788 | Edgepoint | 15.244 | 120.6364 | 0.23 | Terrestrial Optical Fiber Drop | 2.27 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2009 | 3 | 9 | 2009 | 0803738088 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Pablo | 11.0472 | 124.6061 | U | 6541 | 1721 | 516 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0095 | PTCI/MIDC | 11.0504 | 124.6081 | 0.41 | Terrestrial Optical Fiber Drop | 2.68 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2010 | 3 | 10 | 2010 | 0403406010 | Region IV-A (CALABARZON) | Laguna | Calauan | Masiit | 14.1611 | 121.3057 | U | 5456 | 1653 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02102-C08 | PTCI/MIDC | 14.1591 | 121.3135 | 0.87 | Terrestrial Optical Fiber Drop | 1.9 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2011 | 3 | 11 | 2011 | 0307106001 | Region III (Central Luzon) | Zambales | Masinloc | Baloganon | 15.5518 | 119.9462 | U | 8165 | 2148 | 644 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03362-B07 | PTCI/MIDC | 15.5488 | 119.9474 | 0.36 | Terrestrial Optical Fiber Drop | 1.89 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2012 | 3 | 12 | 2012 | 0803726006 | Region VIII (Eastern Visayas) | Leyte | Kananga | Libongao | 11.1617 | 124.561 | R | 2939 | 773 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 1.86 | Terrestrial Optical Fiber Drop | 2.59 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2013 | 3 | 13 | 2013 | 0431200012 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Barangay 9 | 13.9309 | 121.6111 | U | 3420 | 855 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUE_0001 | LDIC | 13.9357 | 121.6202 | 0.4 | Terrestrial Optical Fiber Drop | 0.25 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2014 | 3 | 14 | 2014 | 0702250017 | Region VII (Central Visayas) | Cebu | City of Talisay | Tangke | 10.2505 | 123.8594 | U | 14376 | 3783 | 1135 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0160 | PTCI/MIDC | 10.2575 | 123.8595 | 0.78 | Terrestrial Optical Fiber Drop | 1.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2015 | 3 | 15 | 2015 | 0105522002 | Region I (Ilocos Region) | Pangasinan | Lingayen | Baay | 16.0097 | 120.2236 | U | 5865 | 1629 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00464 | Edgepoint | 16.0091 | 120.2223 | 0.15 | Terrestrial Optical Fiber Drop | 1.77 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2016 | 3 | 16 | 2016 | 0501725023 | Region V (Bicol Region) | Camarines Sur | Ocampo | San Vicente | 13.5594 | 123.3823 | R | 2130 | 507 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050106 | FTAP Globe | 13.5599 | 123.3814 | 0.56 | Terrestrial Optical Fiber Drop | 0.75 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2017 | 3 | 17 | 2017 | 0300804008 | Region III (Central Luzon) | Bataan | Dinalupihan | Daang Bago | 14.857 | 120.4794 | R | 3392 | 942 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02568 | Edgepoint | 14.8582 | 120.4764 | 0.35 | Terrestrial Optical Fiber Drop | 1.36 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2018 | 3 | 18 | 2018 | 0401020026 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | San Felipe | 13.8852 | 121.2048 | U | 3694 | 1026 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01954-C08 | PTCI/MIDC | 13.893 | 121.1996 | 1.03 | Terrestrial Optical Fiber Drop | 1.93 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2019 | 3 | 19 | 2019 | 0105526028 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Salay | 16.0794 | 120.3977 | U | 5931 | 1647 | 494 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00414 | Edgepoint | 16.083 | 120.3977 | 0.4 | Terrestrial Optical Fiber Drop | 1.38 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2020 | 3 | 20 | 2020 | 0405623004 | Region IV-A (CALABARZON) | Quezon | Lucban | Ayuti | 14.1169 | 121.5487 | U | 10218 | 2688 | 806 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0021 | PTCI/MIDC | 14.1109 | 121.5533 | 0.83 | Terrestrial Optical Fiber Drop | 1.08 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2021 | 3 | 21 | 2021 | 0105530024 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Palacpalac | 16.1267 | 120.5339 | R | 3173 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00405 | Edgepoint | 16.1135 | 120.5399 | 1.61 | Terrestrial Optical Fiber Drop | 1.49 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2022 | 3 | 22 | 2022 | 0401020014 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Bawi | 13.8868 | 121.233 | R | 4041 | 1122 | 337 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040514 | FTAP Globe | 13.8971 | 121.2443 | 1.67 | Terrestrial Optical Fiber Drop | 1.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2023 | 3 | 23 | 2023 | 0307113015 | Region III (Central Luzon) | Zambales | Santa Cruz | Malabago | 15.7878 | 119.9053 | R | 2916 | 767 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 0.66 | Terrestrial Optical Fiber Drop | 2.27 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2024 | 3 | 24 | 2024 | 0105512019 | Region I (Ilocos Region) | Pangasinan | Binalonan | San Pablo | 16.016 | 120.6016 | R | 1919 | 533 | 160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 0.48 | Terrestrial Optical Fiber Drop | 3.6 | 2.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2025 | 3 | 25 | 2025 | 0300811016 | Region III (Central Luzon) | Bataan | Pilar | Nagwaling | 14.6341 | 120.5245 | R | 3730 | 1036 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030627 | FTAP Globe | 14.6352 | 120.5287 | 0.47 | Terrestrial Optical Fiber Drop | 2.36 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2026 | 3 | 26 | 2026 | 0702210011 | Region VII (Central Visayas) | Cebu | Barili | Guibuangan | 10.1153 | 123.496 | R | 2653 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CEB-03147 | Edgepoint | 10.1184 | 123.5105 | 1.62 | Terrestrial Optical Fiber Drop | 1.42 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2027 | 3 | 27 | 2027 | 0401021003 | Region IV-A (CALABARZON) | Batangas | Rosario | Bagong Pook | 13.8449 | 121.221 | U | 6454 | 1792 | 538 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBGG0009 | PTCI/MIDC | 13.8479 | 121.2131 | 0.92 | Terrestrial Optical Fiber Drop | 2.11 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2028 | 3 | 28 | 2028 | 0401022008 | Region IV-A (CALABARZON) | Batangas | San Jose | Banaybanay II | 13.9212 | 121.106 | U | 4648 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040460 | FTAP Globe | 13.9286 | 121.1095 | 0.91 | Terrestrial Optical Fiber Drop | 2.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2029 | 3 | 29 | 2029 | 0704601003 | Region VII (Central Visayas) | Negros Oriental | Amlan | Jugno | 9.4596 | 123.2002 | R | 4456 | 1172 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 1.74 | Terrestrial Optical Fiber Drop | 2.37 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2030 | 3 | 30 | 2030 | 0704610016 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Mangnao-Canal | 9.2934 | 123.2985 | U | 3241 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNLG0080 | PTCI/MIDC | 9.2957 | 123.2949 | 0.48 | Terrestrial Optical Fiber Drop | 1.5 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2031 | 3 | 31 | 2031 | 0304919001 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Aulo | 15.5208 | 121.0945 | R | 1405 | 401 | 120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01505-B07 | PTCI/MIDC | 15.5057 | 121.0775 | 2.48 | Terrestrial Optical Fiber Drop | 0.01 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2032 | 3 | 32 | 2032 | 0506215011 | Region V (Bicol Region) | Sorsogon | Santa Magdalena | San Isidro | 12.6502 | 124.0952 | R | 1612 | 403 | 121 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-SOR-03235 | Edgepoint | 12.6505 | 124.1062 | 1.19 | Terrestrial Optical Fiber Drop | 1.25 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2033 | 3 | 33 | 2033 | 0702232007 | Region VII (Central Visayas) | Cebu | Minglanilla | Linao | 10.255 | 123.8103 | U | 16506 | 4343 | 1303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070359 | FTAP Globe | 10.2495 | 123.8123 | 0.65 | Terrestrial Optical Fiber Drop | 1.36 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2034 | 3 | 34 | 2034 | 0305403013 | Region III (Central Luzon) | Pampanga | Arayat | Mangga-Cacutud | 15.1471 | 120.7628 | U | 11667 | 2916 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01550-B07 | PTCI/MIDC | 15.1477 | 120.7629 | 0.07 | Terrestrial Optical Fiber Drop | 1.08 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2035 | 3 | 35 | 2035 | 0304902012 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Lusok | 15.6039 | 121.1426 | R | 2558 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03157-B07 | PTCI/MIDC | 15.6037 | 121.1431 | 0.05 | Terrestrial Optical Fiber Drop | 2.28 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2036 | 3 | 36 | 2036 | 0306914003 | Region III (Central Luzon) | Tarlac | San Manuel | Legaspi | 15.8193 | 120.6067 | R | 2982 | 764 | 229 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00566 | Edgepoint | 15.8254 | 120.6029 | 0.8 | Terrestrial Optical Fiber Drop | 2.54 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2037 | 3 | 37 | 2037 | 1600203012 | Region XIII (Caraga) | Agusan del Norte | City of Cabadbaran | Comagascas | 9.1359 | 125.5585 | R | 4324 | 1054 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0018 | PTCI/MIDC | 9.1218 | 125.5451 | 2.15 | Terrestrial Optical Fiber Drop | 1.95 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2038 | 3 | 38 | 2038 | 0304917003 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Bantug | 15.7201 | 120.9191 | U | 12103 | 3458 | 1037 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0028 | PTCI/MIDC | 15.7203 | 120.9237 | 0.5 | Terrestrial Optical Fiber Drop | 1.78 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2039 | 3 | 39 | 2039 | 0402106061 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc II | 14.2833 | 120.9604 | U | 19186 | 5642 | 1693 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.16 | Terrestrial Optical Fiber Drop | 1.88 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2040 | 3 | 40 | 2040 | 0301423009 | Region III (Central Luzon) | Bulacan | Santa Maria | Guyong | 14.837 | 120.977 | U | 17675 | 5050 | 1515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01111-B07 | PTCI/MIDC | 14.8361 | 120.9745 | 0.28 | Terrestrial Optical Fiber Drop | 2.35 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2041 | 3 | 41 | 2041 | 1630400009 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Antongalon | 8.9486 | 125.6212 | R | 4300 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTANG0009 | PTCI/MIDC | 8.9384 | 125.5902 | 3.59 | Terrestrial Optical Fiber Drop | 2.63 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2042 | 3 | 42 | 2042 | 0702232017 | Region VII (Central Visayas) | Cebu | Minglanilla | Tungkop | 10.2403 | 123.7824 | U | 14574 | 3835 | 1151 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070362 | FTAP Globe | 10.2441 | 123.7824 | 0.43 | Terrestrial Optical Fiber Drop | 0.92 | 0.01 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2043 | 3 | 43 | 2043 | 0803714002 | Region VIII (Eastern Visayas) | Leyte | Capoocan | Balud | 11.2923 | 124.6508 | R | 2968 | 781 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080136 | FTAP BTS | 11.2914 | 124.6553 | 0.5 | Terrestrial Optical Fiber Drop | 1.65 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2044 | 3 | 44 | 2044 | 0500517042 | Region V (Bicol Region) | Albay | City of Tabaco | San Vicente | 13.3565 | 123.7 | R | 4686 | 1142 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050133 | FTAP Globe | 13.3444 | 123.7023 | 1.37 | Terrestrial Optical Fiber Drop | 3.42 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2045 | 3 | 45 | 2045 | 0702222031 | Region VII (Central Visayas) | Cebu | Dalaguete | Tapun | 9.7734 | 123.5307 | R | 4845 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0075 | PTCI/MIDC | 9.7647 | 123.5349 | 1.07 | Terrestrial Optical Fiber Drop | 1.29 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2046 | 3 | 46 | 2046 | 0500503010 | Region V (Bicol Region) | Albay | Daraga | Binitayan | 13.1553 | 123.7162 | U | 4659 | 1136 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050173 | FTAP Globe | 13.155 | 123.7161 | 0.03 | Terrestrial Optical Fiber Drop | 1.03 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2047 | 3 | 47 | 2047 | 0301410055 | Region III (Central Luzon) | Bulacan | City of Malolos | Tikay | 14.8406 | 120.8539 | U | 13170 | 3762 | 1129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01141 | Edgepoint | 14.8402 | 120.8564 | 0.27 | Terrestrial Optical Fiber Drop | 2.42 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2048 | 3 | 48 | 2048 | 0702231001 | Region VII (Central Visayas) | Cebu | Medellin | Antipolo | 11.1605 | 123.9597 | U | 6680 | 1757 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0124 | PTCI/MIDC | 11.1643 | 123.9534 | 0.81 | Terrestrial Optical Fiber Drop | 2.48 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2049 | 3 | 49 | 2049 | 0307701007 | Region III (Central Luzon) | Aurora | Baler | Calabuanan | 15.7482 | 121.5097 | U | 4098 | 1078 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030320 | FTAP Globe | 15.7547 | 121.4939 | 1.84 | Terrestrial Optical Fiber Drop | 1.74 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2050 | 3 | 50 | 2050 | 0301421046 | Region III (Central Luzon) | Bulacan | San Miguel | San Vicente | 15.1398 | 120.971 | R | 2870 | 820 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01122-B07 | PTCI/MIDC | 15.144 | 120.9745 | 0.6 | Terrestrial Optical Fiber Drop | 1.1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2051 | 3 | 51 | 2051 | 0603035024 | Region VI (Western Visayas) | Iloilo | City of Passi | Imbang Grande | 11.1055 | 122.6624 | R | 2839 | 747 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.44 | Terrestrial Optical Fiber Drop | 1.76 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2052 | 3 | 52 | 2052 | 0702234015 | Region VII (Central Visayas) | Cebu | City of Naga | Lutac | 10.2486 | 123.725 | U | 5622 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0002 | LDIC | 10.2585 | 123.7393 | 1.91 | Terrestrial Optical Fiber Drop | 1.76 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2053 | 3 | 53 | 2053 | 0601914043 | Region VI (Western Visayas) | Capiz | City of Roxas | Punta Tabuc | 11.5748 | 122.7446 | U | 5999 | 1578 | 473 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060226 | FTAP Globe | 11.5755 | 122.7465 | 0.23 | Terrestrial Optical Fiber Drop | 1.63 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2054 | 3 | 54 | 2054 | 0306904003 | Region III (Central Luzon) | Tarlac | Capas | Cubcub | 15.3324 | 120.5909 | U | 4213 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01802-B07 | PTCI/MIDC | 15.342 | 120.5972 | 1.26 | Terrestrial Optical Fiber Drop | 1.63 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2055 | 3 | 55 | 2055 | 0500517037 | Region V (Bicol Region) | Albay | City of Tabaco | San Carlos | 13.3757 | 123.7189 | R | 4226 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050126 | FTAP Globe | 13.3795 | 123.7173 | 0.45 | Terrestrial Optical Fiber Drop | 2.33 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2056 | 3 | 56 | 2056 | 0402116009 | Region IV-A (CALABARZON) | Cavite | Noveleta | Santa Rosa I | 14.4283 | 120.8764 | U | 5192 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.46 | Terrestrial Optical Fiber Drop | 0.73 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2057 | 3 | 57 | 2057 | 0300810020 | Region III (Central Luzon) | Bataan | Orion | Puting Buhangin | 14.585 | 120.5889 | R | 3189 | 885 | 266 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00904-B07 | PTCI/MIDC | 14.5834 | 120.5868 | 0.29 | Terrestrial Optical Fiber Drop | 1.38 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2058 | 3 | 58 | 2058 | 1705211007 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | San Isidro | 13.5039 | 120.9173 | U | 5300 | 1358 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170042 | FTAP Globe | 13.5044 | 120.9155 | 0.2 | Terrestrial Optical Fiber Drop | 1.22 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2059 | 3 | 59 | 2059 | 0201502025 | Region II (Cagayan Valley) | Cagayan | Alcala | Tupang | 17.9055 | 121.6423 | R | 2603 | 667 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0016 | LDIC | 17.9095 | 121.64 | 0.52 | Terrestrial Optical Fiber Drop | 1.31 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2060 | 3 | 60 | 2060 | 1705205006 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Bayanan II | 13.357 | 121.1701 | R | 3122 | 800 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 3.58 | Terrestrial Optical Fiber Drop | 1.91 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2061 | 3 | 61 | 2061 | 0304926003 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Abar 2nd | 15.7817 | 120.9698 | R | 4394 | 1255 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00576 | Edgepoint | 15.7797 | 120.9688 | 0.25 | Terrestrial Optical Fiber Drop | 2.4 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2062 | 3 | 62 | 2062 | 0403414005 | Region IV-A (CALABARZON) | Laguna | Mabitac | Nanguma | 14.445 | 121.4214 | R | 2749 | 833 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040099 | FTAP Globe | 14.4448 | 121.4243 | 0.31 | Terrestrial Optical Fiber Drop | 1.8 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2063 | 3 | 63 | 2063 | 0803736010 | Region VIII (Eastern Visayas) | Leyte | Merida | Lamanoc | 10.9267 | 124.5482 | R | 2219 | 583 | 175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0040 | PTCI/MIDC | 10.9068 | 124.5349 | 2.66 | Terrestrial Optical Fiber Drop | 1.75 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2064 | 3 | 64 | 2064 | 0405811005 | Region IV-A (CALABARZON) | Rizal | San Mateo | Guitnang Bayan I | 14.6953 | 121.1209 | U | 33621 | 9339 | 2802 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01351 | Edgepoint | 14.6941 | 121.1205 | 0.15 | Terrestrial Optical Fiber Drop | 1.08 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2065 | 3 | 65 | 2065 | 0501724012 | Region V (Bicol Region) | Camarines Sur | City of Naga | Del Rosario | 13.6176 | 123.2379 | U | 10312 | 2455 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-03171 | Edgepoint | 13.6175 | 123.2364 | 0.17 | Terrestrial Optical Fiber Drop | 2.22 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2066 | 3 | 66 | 2066 | 0704620002 | Region VII (Central Visayas) | Negros Oriental | Sibulan | Ajong | 9.3815 | 123.2578 | R | 3691 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0050 | PTCI/MIDC | 9.377 | 123.2563 | 0.52 | Terrestrial Optical Fiber Drop | 9 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2067 | 3 | 67 | 2067 | 0806407002 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Asuncion | 10.1304 | 124.8614 | U | 5120 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080346 | FTAP Globe | 10.1393 | 124.8569 | 1.11 | Terrestrial Optical Fiber Drop | 0.46 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2068 | 3 | 68 | 2068 | 0402118031 | Region IV-A (CALABARZON) | Cavite | Silang | Pasong Langka | 14.1627 | 120.9982 | U | 4059 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02159-C08 | PTCI/MIDC | 14.1651 | 120.9988 | 0.28 | Terrestrial Optical Fiber Drop | 1.99 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2069 | 3 | 69 | 2069 | 0305407019 | Region III (Central Luzon) | Pampanga | Guagua | San Miguel | 14.9821 | 120.6481 | U | 5420 | 1355 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01639-B07 | PTCI/MIDC | 14.9819 | 120.6451 | 0.32 | Terrestrial Optical Fiber Drop | 2.24 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2070 | 3 | 70 | 2070 | 0704621017 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | Polo | 9.482 | 123.18 | R | 3900 | 1026 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 2.08 | Terrestrial Optical Fiber Drop | 5.12 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2071 | 3 | 71 | 2071 | 0300804020 | Region III (Central Luzon) | Bataan | Dinalupihan | Naparing | 14.8459 | 120.4069 | R | 3244 | 901 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02475-B07 | PTCI/MIDC | 14.846 | 120.4054 | 0.16 | Terrestrial Optical Fiber Drop | 1.05 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2072 | 3 | 72 | 2072 | 0306907011 | Region III (Central Luzon) | Tarlac | La Paz | Laungcupang | 15.4545 | 120.703 | R | 2396 | 614 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03433-B07 | PTCI/MIDC | 15.4762 | 120.7074 | 2.46 | Terrestrial Optical Fiber Drop | 1.75 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2073 | 3 | 73 | 2073 | 0304903016 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Bitas | 15.4966 | 120.978 | U | 6009 | 1716 | 515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01412-B07 | PTCI/MIDC | 15.4974 | 120.9762 | 0.21 | Terrestrial Optical Fiber Drop | 2.45 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2074 | 3 | 74 | 2074 | 0305403014 | Region III (Central Luzon) | Pampanga | Arayat | Mapalad | 15.2054 | 120.8102 | R | 4196 | 1049 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00803 | Edgepoint | 15.2038 | 120.8107 | 0.18 | Terrestrial Optical Fiber Drop | 8.15 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2075 | 3 | 75 | 2075 | 1600302010 | Region XIII (Caraga) | Agusan del Sur | Bunawan | San Teodoro | 8.1703 | 125.9994 | U | 7095 | 1819 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0009 | PTCI/MIDC | 8.2105 | 125.9905 | 4.57 | Terrestrial Optical Fiber Drop | 1.37 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2076 | 3 | 76 | 2076 | 0105518031 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Tapuac | 16.0372 | 120.3329 | U | 5044 | 1401 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00437 | Edgepoint | 16.0381 | 120.335 | 0.25 | Terrestrial Optical Fiber Drop | 1.83 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2077 | 3 | 77 | 2077 | 0401021037 | Region IV-A (CALABARZON) | Batangas | Rosario | Quilib | 13.8595 | 121.2064 | U | 6515 | 1809 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1032 | FTAP Smart | 13.8539 | 121.205 | 0.63 | Terrestrial Optical Fiber Drop | 1.75 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2078 | 3 | 78 | 2078 | 0305416030 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Nicolas | 15.0167 | 120.7035 | U | 10503 | 2625 | 788 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00941 | Edgepoint | 15.0162 | 120.7031 | 0.06 | Terrestrial Optical Fiber Drop | 1.33 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2079 | 3 | 79 | 2079 | 0702247004 | Region VII (Central Visayas) | Cebu | Sogod | Bawo | 10.7406 | 124.0087 | R | 2884 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 1.46 | Terrestrial Optical Fiber Drop | 1.35 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2080 | 3 | 80 | 2080 | 0702221005 | Region VII (Central Visayas) | Cebu | Daanbantayan | Bitoon | 11.2337 | 123.9939 | U | 5386 | 1417 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0072 | PTCI/MIDC | 11.2494 | 124.0028 | 1.99 | Terrestrial Optical Fiber Drop | 2.04 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2081 | 3 | 81 | 2081 | 0401003029 | Region IV-A (CALABARZON) | Batangas | Balayan | Gumamela | 13.9453 | 120.7417 | R | 3142 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 1.08 | Terrestrial Optical Fiber Drop | 1.49 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2082 | 3 | 82 | 2082 | 0601914001 | Region VI (Western Visayas) | Capiz | City of Roxas | Adlawan | 11.4972 | 122.7657 | R | 2694 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060231 | FTAP Globe | 11.5001 | 122.7634 | 0.41 | Terrestrial Optical Fiber Drop | 2.52 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2083 | 3 | 83 | 2083 | 0301420003 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Gaya-gaya | 14.7959 | 121.05 | U | 59472 | 16992 | 5098 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N64 | FTAP Smart | 14.7956 | 121.0522 | 0.24 | Terrestrial Optical Fiber Drop | 1.57 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2084 | 3 | 84 | 2084 | 0803738058 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Libertad | 11.0346 | 124.5686 | R | 4685 | 1232 | 370 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0048 | PTCI/MIDC | 11.0365 | 124.5646 | 0.48 | Terrestrial Optical Fiber Drop | 3.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2085 | 3 | 85 | 2085 | 0401029005 | Region IV-A (CALABARZON) | Batangas | Taal | Buli | 13.8818 | 120.9544 | U | 5872 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040522 | FTAP Globe | 13.8841 | 120.9487 | 0.67 | Terrestrial Optical Fiber Drop | 1.36 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2086 | 3 | 86 | 2086 | 0702243019 | Region VII (Central Visayas) | Cebu | San Remigio | Mano | 11.0518 | 123.9366 | R | 4438 | 1167 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0151 | PTCI/MIDC | 11.0425 | 123.9341 | 1.08 | Terrestrial Optical Fiber Drop | 2.97 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2087 | 3 | 87 | 2087 | 0301403018 | Region III (Central Luzon) | Bulacan | Baliuag | San Roque | 14.997 | 120.8915 | R | 4147 | 1184 | 355 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00950 | Edgepoint | 14.9981 | 120.8907 | 0.16 | Terrestrial Optical Fiber Drop | 3.11 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2088 | 3 | 88 | 2088 | 0501734019 | Region V (Bicol Region) | Camarines Sur | Sipocot | Gaongan | 13.759 | 122.9664 | R | 2084 | 496 | 149 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 2.46 | Terrestrial Optical Fiber Drop | 1.07 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2089 | 3 | 89 | 2089 | 0702246022 | Region VII (Central Visayas) | Cebu | Sibonga | Sabang | 10.0315 | 123.6185 | R | 2978 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070063 | FTAP BTS | 10.0269 | 123.6162 | 0.57 | Terrestrial Optical Fiber Drop | 2.06 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2090 | 3 | 90 | 2090 | 0300805004 | Region III (Central Luzon) | Bataan | Hermosa | Balsic | 14.8637 | 120.4901 | U | 8190 | 2275 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-01088 | Edgepoint | 14.871 | 120.5021 | 1.52 | Terrestrial Optical Fiber Drop | 2.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2091 | 3 | 91 | 2091 | 0306916064 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Juan de Mata | 15.5355 | 120.5288 | R | 4602 | 1180 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00673 | Edgepoint | 15.528 | 120.5216 | 1.14 | Terrestrial Optical Fiber Drop | 4.28 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2092 | 3 | 92 | 2092 | 0105524031 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Don Pedro | 15.8866 | 120.4304 | R | 3472 | 964 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00547 | Edgepoint | 15.89 | 120.4328 | 0.46 | Terrestrial Optical Fiber Drop | 4.22 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2093 | 3 | 93 | 2093 | 0403424041 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Antonio 2 | 13.9973 | 121.3334 | R | 5144 | 1558 | 467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02127-C08 | PTCI/MIDC | 13.9949 | 121.3333 | 0.26 | Terrestrial Optical Fiber Drop | 4.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2094 | 3 | 94 | 2094 | 0307108007 | Region III (Central Luzon) | Zambales | Palauig | Liozon | 15.399 | 119.9327 | R | 3789 | 997 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-00736 | Edgepoint | 15.4019 | 119.9278 | 0.62 | Terrestrial Optical Fiber Drop | 4.69 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2095 | 3 | 95 | 2095 | 0105533025 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tocok | 16.1416 | 120.4198 | R | 3807 | 1057 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 2.14 | Terrestrial Optical Fiber Drop | 3.61 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2096 | 3 | 96 | 2096 | 0300806009 | Region III (Central Luzon) | Bataan | Limay | Townsite | 14.561 | 120.5951 | U | 5874 | 1631 | 489 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3935 | FTAP Smart | 14.5589 | 120.5947 | 0.23 | Terrestrial Optical Fiber Drop | 1.45 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2097 | 3 | 97 | 2097 | 0300810013 | Region III (Central Luzon) | Bataan | Orion | Daang Pare | 14.6001 | 120.5794 | U | 8415 | 2337 | 701 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0017 | PTCI/MIDC | 14.5986 | 120.5807 | 0.22 | Terrestrial Optical Fiber Drop | 1.7 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2098 | 3 | 98 | 2098 | 0403417049 | Region IV-A (CALABARZON) | Laguna | Nagcarlan | Taytay | 14.1109 | 121.4141 | U | 3826 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040305 | FTAP Globe | 14.1176 | 121.4176 | 0.84 | Terrestrial Optical Fiber Drop | 2.3 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2099 | 3 | 99 | 2099 | 0305405033 | Region III (Central Luzon) | Pampanga | Candaba | Talang | 15.0191 | 120.8529 | U | 3940 | 985 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02373 | Edgepoint | 15.0195 | 120.8521 | 0.09 | Terrestrial Optical Fiber Drop | 1.99 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2100 | 3 | 100 | 2100 | 0603045005 | Region VI (Western Visayas) | Iloilo | Tigbauan | Bagumbayan | 10.6929 | 122.3872 | R | 2186 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0075 | PTCI/MIDC | 10.674 | 122.3827 | 2.16 | Terrestrial Optical Fiber Drop | 1.66 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2101 | 3 | 101 | 2101 | 1705110027 | MIMAROPA Region | Occidental Mindoro | San Jose | Mabini | 12.3714 | 121.0901 | R | 3710 | 951 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1524 | FTAP Smart | 12.3767 | 121.0856 | 0.76 | Terrestrial Optical Fiber Drop | 3.59 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2102 | 3 | 102 | 2102 | 0402118027 | Region IV-A (CALABARZON) | Cavite | Silang | Malabag | 14.1433 | 120.9646 | U | 5249 | 1543 | 463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040290 | FTAP Globe | 14.1428 | 120.96 | 0.5 | Terrestrial Optical Fiber Drop | 2.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2103 | 3 | 103 | 2103 | 0301404005 | Region III (Central Luzon) | Bulacan | Bocaue | Biñang 1st | 14.7939 | 120.9308 | R | 3560 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01186 | Edgepoint | 14.7982 | 120.93 | 0.49 | Terrestrial Optical Fiber Drop | 1.69 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2104 | 3 | 104 | 2104 | 1705208043 | MIMAROPA Region | Oriental Mindoro | Naujan | Pinagsabangan I | 13.2538 | 121.2684 | R | 2624 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170080 | FTAP Globe | 13.2359 | 121.2697 | 2 | Terrestrial Optical Fiber Drop | 1.24 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2105 | 3 | 105 | 2105 | 0405814005 | Region IV-A (CALABARZON) | Rizal | Teresa | May-Iba | 14.5633 | 121.2067 | U | 5907 | 1640 | 492 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00741-A04 | PTCI/MIDC | 14.5655 | 121.2092 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2106 | 3 | 106 | 2106 | 0506205002 | Region V (Bicol Region) | Sorsogon | Casiguran | Boton | 12.9291 | 124.0472 | R | 2415 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050207 | FTAP Globe | 12.969 | 124.0053 | 6.35 | Terrestrial Optical Fiber Drop | 2.01 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2107 | 3 | 107 | 2107 | 0300801003 | Region III (Central Luzon) | Bataan | Abucay | Capitangan | 14.7061 | 120.5378 | U | 7605 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030099 | FTAP BTS | 14.7029 | 120.5358 | 0.42 | Terrestrial Optical Fiber Drop | 2.38 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2108 | 3 | 108 | 2108 | 0102914017 | Region I (Ilocos Region) | Ilocos Sur | Narvacan | Margaay | 17.4253 | 120.474 | U | 2657 | 699 | 210 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_ILS_0021 | LDIC | 17.4195 | 120.4733 | 0.65 | Terrestrial Optical Fiber Drop | 1.05 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2109 | 3 | 109 | 2109 | 0405814004 | Region IV-A (CALABARZON) | Rizal | Teresa | Dulumbayan | 14.5633 | 121.2067 | U | 8898 | 2471 | 741 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00741-A04 | PTCI/MIDC | 14.5655 | 121.2092 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2110 | 3 | 110 | 2110 | 0304901032 | Region III (Central Luzon) | Nueva Ecija | Aliaga | San Juan | 15.5069 | 120.8933 | U | 5728 | 1636 | 491 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02883-B07 | PTCI/MIDC | 15.5052 | 120.8868 | 0.72 | Terrestrial Optical Fiber Drop | 2.42 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2111 | 3 | 111 | 2111 | 0405811015 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santo Niño | 14.6694 | 121.1347 | U | 12224 | 3395 | 1019 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01422 | Edgepoint | 14.671 | 121.1347 | 0.18 | Terrestrial Optical Fiber Drop | 2.39 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2112 | 3 | 112 | 2112 | 0701201005 | Region VII (Central Visayas) | Bohol | Alburquerque | East Poblacion | 9.6109 | 123.9568 | R | 2271 | 567 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 0.3 | Terrestrial Optical Fiber Drop | 2.16 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2113 | 3 | 113 | 2113 | 0604527010 | Region VI (Western Visayas) | Negros Occidental | City of Sipalay | Cayhagan | 9.688 | 122.4477 | R | 3878 | 1048 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0066 | PTCI/MIDC | 9.7261 | 122.4402 | 4.32 | Terrestrial Optical Fiber Drop | 8.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2114 | 3 | 114 | 2114 | 0405648022 | Region IV-A (CALABARZON) | Quezon | Tiaong | San Agustin | 13.9436 | 121.3178 | R | 2542 | 668 | 200 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03369-C08 | PTCI/MIDC | 13.9469 | 121.3102 | 0.89 | Terrestrial Optical Fiber Drop | 2.17 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2115 | 3 | 115 | 2115 | 0401014035 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Pagolingin West | 13.8936 | 121.1623 | R | 2144 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.45 | Terrestrial Optical Fiber Drop | 5.65 | 1.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2116 | 3 | 116 | 2116 | 0405808008 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Rosario | 14.7486 | 121.1487 | U | 6573 | 1825 | 548 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00729-A04 | PTCI/MIDC | 14.7456 | 121.164 | 0.27 | Terrestrial Optical Fiber Drop | 1.69 | 1.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2117 | 3 | 117 | 2117 | 1004319007 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Maanas | 8.8912 | 125.0322 | R | 4451 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0067 | PTCI/MIDC | 8.8896 | 125.032 | 0.17 | Terrestrial Optical Fiber Drop | 2.52 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2118 | 3 | 118 | 2118 | 0201529018 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Carig | 17.6644 | 121.7495 | U | 5159 | 1322 | 397 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02278 | Edgepoint | 17.6685 | 121.7522 | 0.53 | Terrestrial Optical Fiber Drop | 1.48 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2119 | 3 | 119 | 2119 | 0301422014 | Region III (Central Luzon) | Bulacan | San Rafael | Maguinao | 15.0236 | 120.9342 | U | 5164 | 1475 | 443 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00926 | Edgepoint | 15.0273 | 120.9352 | 0.42 | Terrestrial Optical Fiber Drop | 1.8 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2120 | 3 | 120 | 2120 | 0501710012 | Region V (Bicol Region) | Camarines Sur | Canaman | San Agustin | 13.6455 | 123.183 | R | 3184 | 758 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03033-C10 | PTCI/MIDC | 13.6498 | 123.1798 | 0.59 | Terrestrial Optical Fiber Drop | 1.18 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2121 | 3 | 121 | 2121 | 0306910027 | Region III (Central Luzon) | Tarlac | Paniqui | Salumague | 15.6662 | 120.5656 | R | 3681 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00610 | Edgepoint | 15.6665 | 120.5713 | 0.62 | Terrestrial Optical Fiber Drop | 2.31 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2122 | 3 | 122 | 2122 | 0304928018 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Santo Rosario | 15.4338 | 120.8894 | R | 3179 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01513-B07 | PTCI/MIDC | 15.4356 | 120.8836 | 0.65 | Terrestrial Optical Fiber Drop | 3.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2123 | 3 | 123 | 2123 | 0702208021 | Region VII (Central Visayas) | Cebu | Balamban | Nangka | 10.5332 | 123.7194 | U | 7401 | 1947 | 584 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 0.3 | Terrestrial Optical Fiber Drop | 2.73 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2124 | 3 | 124 | 2124 | 0305409003 | Region III (Central Luzon) | Pampanga | Mabalacat City | Bundagul | 15.212 | 120.5801 | U | 4122 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02973-B07 | PTCI/MIDC | 15.219 | 120.5769 | 0.36 | Terrestrial Optical Fiber Drop | 1.26 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2125 | 3 | 125 | 2125 | 0405805015 | Region IV-A (CALABARZON) | Rizal | Cainta | San Isidro | 14.6362 | 121.1086 | U | 83020 | 23061 | 6918 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01543 | Edgepoint | 14.6353 | 121.1093 | 0.13 | Terrestrial Optical Fiber Drop | 1.55 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2126 | 3 | 126 | 2126 | 0702243017 | Region VII (Central Visayas) | Cebu | San Remigio | Looc | 11.0665 | 123.9368 | R | 2423 | 637 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070033 | FTAP BTS | 11.076 | 123.9377 | 1.06 | Terrestrial Optical Fiber Drop | 1.34 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2127 | 3 | 127 | 2127 | 1130700019 | Region XI (Davao Region) | Davao del Sur | City of Davao | Binugao | 7.1649 | 125.4714 | U | 8991 | 2644 | 793 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110319 | FTAP BTS | 6.9653 | 125.4772 | 1.06 | Terrestrial Optical Fiber Drop | 2.98 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2128 | 3 | 128 | 2128 | 1102502005 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Punta Linao | 7.0624 | 125.9618 | R | 3404 | 945 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDLG0038 | PTCI/MIDC | 7.0669 | 125.9606 | 0.51 | Terrestrial Optical Fiber Drop | 10.57 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2129 | 3 | 129 | 2129 | 0403422014 | Region IV-A (CALABARZON) | Laguna | Pila | San Antonio | 14.2179 | 121.3592 | R | 4205 | 1274 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 1.57 | Terrestrial Optical Fiber Drop | 1.32 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2130 | 3 | 130 | 2130 | 1102412011 | Region XI (Davao Region) | Davao del Sur | Santa Cruz | Zone I | 6.8494 | 125.4189 | U | 9351 | 2750 | 825 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDSG0080 | PTCI/MIDC | 6.8467 | 125.4102 | 1.01 | Terrestrial Optical Fiber Drop | 1.37 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2131 | 3 | 131 | 2131 | 0331400019 | Region III (Central Luzon) | Zambales | City of Olongapo | West Bajac-bajac | 14.844 | 120.2894 | U | 8582 | 2319 | 696 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 521 | FTAP Smart | 14.8444 | 120.2929 | 0.39 | Terrestrial Optical Fiber Drop | 1.47 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2132 | 3 | 132 | 2132 | 0305408044 | Region III (Central Luzon) | Pampanga | Lubao | Santo Niño | 14.8726 | 120.5039 | R | 4087 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-01088 | Edgepoint | 14.871 | 120.5021 | 0.27 | Terrestrial Optical Fiber Drop | 3.84 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2133 | 3 | 133 | 2133 | 0301406007 | Region III (Central Luzon) | Bulacan | Bustos | Liciada | 14.9092 | 120.9306 | U | 6416 | 1833 | 550 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02547 | Edgepoint | 14.9056 | 120.9286 | 0.45 | Terrestrial Optical Fiber Drop | 1.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2134 | 3 | 134 | 2134 | 0307106005 | Region III (Central Luzon) | Zambales | Masinloc | Inhobol | 15.5289 | 119.9603 | U | 10276 | 2704 | 811 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-ZMB-02455 | Edgepoint | 15.5334 | 119.9561 | 0.67 | Terrestrial Optical Fiber Drop | 1.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2135 | 3 | 135 | 2135 | 1204704005 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Benoligan | 7.0435 | 125.0062 | R | 2857 | 751 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120126 | FTAP BTS | 7.0423 | 125.0077 | 0.21 | Terrestrial Optical Fiber Drop | 2.24 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2136 | 3 | 136 | 2136 | 0501723015 | Region V (Bicol Region) | Camarines Sur | Nabua | La Opinion | 13.3809 | 123.3716 | U | 5641 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050125 | FTAP Globe | 13.3818 | 123.3726 | 0.15 | Terrestrial Optical Fiber Drop | 2.48 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2137 | 3 | 137 | 2137 | 0403405062 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Majada Labas | 14.1951 | 121.1064 | U | 11588 | 3511 | 1053 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040253 | FTAP Globe | 14.1964 | 121.1107 | 0.48 | Terrestrial Optical Fiber Drop | 2.32 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2138 | 3 | 138 | 2138 | 0402115026 | Region IV-A (CALABARZON) | Cavite | Naic | Sabang | 14.3146 | 120.7934 | U | 23095 | 6792 | 2038 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040176 | FTAP Globe | 14.3157 | 120.7904 | 0.35 | Terrestrial Optical Fiber Drop | 1.64 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2139 | 3 | 139 | 2139 | 0405805017 | Region IV-A (CALABARZON) | Rizal | Cainta | San Roque | 14.5763 | 121.1173 | U | 9850 | 2736 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01787 | Edgepoint | 14.5753 | 121.1157 | 0.21 | Terrestrial Optical Fiber Drop | 1.04 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2140 | 3 | 140 | 2140 | 0501701014 | Region V (Bicol Region) | Camarines Sur | Baao | Buluang | 13.4699 | 123.3569 | U | 7954 | 1893 | 568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02841-C10 | PTCI/MIDC | 13.4681 | 123.3583 | 0.25 | Terrestrial Optical Fiber Drop | 1.76 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2141 | 3 | 141 | 2141 | 1705206017 | MIMAROPA Region | Oriental Mindoro | Gloria | Maligaya | 12.9686 | 121.4774 | R | 3305 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170100 | FTAP Globe | 12.9713 | 121.4747 | 0.42 | Terrestrial Optical Fiber Drop | 1.03 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2142 | 3 | 142 | 2142 | 0702251018 | Region VII (Central Visayas) | Cebu | City of Toledo | Ibo | 10.3653 | 123.6192 | R | 4834 | 1272 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0170 | PTCI/MIDC | 10.3695 | 123.626 | 0.88 | Terrestrial Optical Fiber Drop | 1.34 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2143 | 3 | 143 | 2143 | 0305415024 | Region III (Central Luzon) | Pampanga | Porac | Pio | 15.0837 | 120.5499 | U | 19317 | 4829 | 1449 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 1.57 | Terrestrial Optical Fiber Drop | 2.31 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2144 | 3 | 144 | 2144 | 0501720009 | Region V (Bicol Region) | Camarines Sur | Magarao | San Isidro | 13.6615 | 123.189 | U | 3104 | 739 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0004 | PTCI/MIDC | 13.6631 | 123.1918 | 0.35 | Terrestrial Optical Fiber Drop | 1.04 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2145 | 3 | 145 | 2145 | 0405804007 | Region IV-A (CALABARZON) | Rizal | Binangonan | Calumpang | 14.4777 | 121.1888 | U | 18277 | 5076 | 1523 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040087 | FTAP Globe | 14.4766 | 121.1901 | 0.18 | Terrestrial Optical Fiber Drop | 1.28 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2146 | 3 | 146 | 2146 | 0307109013 | Region III (Central Luzon) | Zambales | San Antonio | Santiago | 14.9492 | 120.0879 | R | 1628 | 428 | 128 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | O51 | FTAP Smart | 14.9456 | 120.0879 | 1.41 | Terrestrial Optical Fiber Drop | 0.29 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2147 | 3 | 147 | 2147 | 0405802003 | Region IV-A (CALABARZON) | Rizal | City of Antipolo | Dela Paz | 14.5975 | 121.1726 | U | 73910 | 20530 | 6159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01716 | Edgepoint | 14.5948 | 121.1701 | 0.41 | Terrestrial Optical Fiber Drop | 1.12 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2148 | 3 | 148 | 2148 | 1004302005 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Binitinan | 8.7154 | 124.7775 | R | 3972 | 1018 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0001 | PTCI/MIDC | 8.7178 | 124.7811 | 0.48 | Terrestrial Optical Fiber Drop | 3.88 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2149 | 3 | 149 | 2149 | 0402115020 | Region IV-A (CALABARZON) | Cavite | Naic | Malainen Bago | 14.3079 | 120.7681 | U | 9906 | 2913 | 874 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040178 | FTAP Globe | 14.314 | 120.7694 | 0.7 | Terrestrial Optical Fiber Drop | 1.58 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2150 | 3 | 150 | 2150 | 0702206017 | Region VII (Central Visayas) | Cebu | Asturias | Owak | 10.5391 | 123.7179 | R | 5002 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 0.95 | Terrestrial Optical Fiber Drop | 3.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2151 | 3 | 151 | 2151 | 0604518011 | Region VI (Western Visayas) | Negros Occidental | Manapla | Santa Teresa | 10.9489 | 123.1718 | R | 3641 | 984 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0030 | PTCI/MIDC | 10.9496 | 123.1816 | 1.07 | Terrestrial Optical Fiber Drop | 4.65 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2152 | 3 | 152 | 2152 | 1208007018 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Malalag Cogon | 6.4053 | 125.289 | R | 4870 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSRG0013 | PTCI/MIDC | 6.4042 | 125.289 | 0.12 | Terrestrial Optical Fiber Drop | 8.09 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2153 | 3 | 153 | 2153 | 0500503045 | Region V (Bicol Region) | Albay | Daraga | Salvacion | 13.1749 | 123.6809 | U | 4365 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050171 | FTAP Globe | 13.1731 | 123.6842 | 0.4 | Terrestrial Optical Fiber Drop | 1.42 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2154 | 3 | 154 | 2154 | 0603045025 | Region VI (Western Visayas) | Iloilo | Tigbauan | Buyu-an | 10.6706 | 122.3575 | R | 3868 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060158 | FTAP BTS | 10.6758 | 122.3662 | 1.11 | Terrestrial Optical Fiber Drop | 2.75 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2155 | 3 | 155 | 2155 | 0203114054 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Manaring | 17.1719 | 121.9021 | R | 2729 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01289-B06 | PTCI/MIDC | 17.1737 | 121.9002 | 0.28 | Terrestrial Optical Fiber Drop | 1.69 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2156 | 3 | 156 | 2156 | 0907322045 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Tiguma | 7.8415 | 123.4568 | U | 13203 | 3385 | 1016 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090132 | FTAP Globe | 7.8421 | 123.4561 | 0.11 | Terrestrial Optical Fiber Drop | 2.27 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2157 | 3 | 157 | 2157 | 0102914024 | Region I (Ilocos Region) | Ilocos Sur | Narvacan | Quinarayan | 17.4449 | 120.4717 | R | 2782 | 732 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01266-B05 | PTCI/MIDC | 17.4497 | 120.463 | 1.06 | Terrestrial Optical Fiber Drop | 1.2 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2158 | 3 | 158 | 2158 | 0501736003 | Region V (Bicol Region) | Camarines Sur | Tigaon | Caraycayon | 13.6122 | 123.4855 | U | 4963 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050082 | FTAP Globe | 13.6235 | 123.491 | 1.39 | Terrestrial Optical Fiber Drop | 2.39 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2159 | 3 | 159 | 2159 | 0603037004 | Region VI (Western Visayas) | Iloilo | Pototan | Barasan | 10.9558 | 122.6404 | R | 1988 | 523 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.88 | Terrestrial Optical Fiber Drop | 1.09 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2160 | 3 | 160 | 2160 | 0201514003 | Region II (Cagayan Valley) | Cagayan | Gonzaga | Baua | 18.3495 | 122.0908 | R | 2350 | 602 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020009 | FTAP Globe | 18.3493 | 122.0877 | 0.32 | Terrestrial Optical Fiber Drop | 1.45 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2161 | 3 | 161 | 2161 | 0702232015 | Region VII (Central Visayas) | Cebu | Minglanilla | Tulay | 10.2391 | 123.7927 | U | 12101 | 3184 | 955 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0126 | PTCI/MIDC | 10.2361 | 123.7871 | 0.7 | Terrestrial Optical Fiber Drop | 1.28 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2162 | 3 | 162 | 2162 | 0304928019 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Soledad | 15.4286 | 120.9949 | U | 7394 | 2112 | 634 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 0.91 | Terrestrial Optical Fiber Drop | 0.04 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2163 | 3 | 163 | 2163 | 0405813002 | Region IV-A (CALABARZON) | Rizal | Taytay | Muzon | 14.5432 | 121.1444 | U | 32623 | 9061 | 2718 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00794-A04 | PTCI/MIDC | 14.5422 | 121.1425 | 0.23 | Terrestrial Optical Fiber Drop | 1.97 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2164 | 3 | 164 | 2164 | 0305405034 | Region III (Central Luzon) | Pampanga | Candaba | Tenejero | 15.0195 | 120.8583 | U | 3465 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030500 | FTAP Globe | 15.019 | 120.8538 | 0.48 | Terrestrial Optical Fiber Drop | 1.42 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2165 | 3 | 165 | 2165 | 0701201001 | Region VII (Central Visayas) | Bohol | Alburquerque | Bahi | 9.6123 | 123.9445 | R | 1063 | 265 | 80 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 1.06 | Terrestrial Optical Fiber Drop | 0.81 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2166 | 3 | 166 | 2166 | 0330100014 | Region III (Central Luzon) | Pampanga | City of Angeles | Margot | 15.1714 | 120.5379 | U | 12771 | 3547 | 1064 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00784 (EP_PH-TAR-00784 / N1858) | EdgePoint | 15.2672 | 120.565 | 0.27 | Terrestrial Optical Fiber Drop | 1.49 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2167 | 3 | 167 | 2167 | 1001309010 | Region X (Northern Mindanao) | Bukidnon | Kitaotao | Kahusayan | 7.6171 | 125.1098 | R | 1688 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 1.21 | Terrestrial Optical Fiber Drop | 1.07 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2168 | 3 | 168 | 2168 | 0601912021 | Region VI (Western Visayas) | Capiz | Pontevedra | Rizal | 11.4369 | 122.8389 | R | 4445 | 1169 | 351 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060235 | FTAP Globe | 11.4291 | 122.8426 | 0.96 | Terrestrial Optical Fiber Drop | 4.59 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2169 | 3 | 169 | 2169 | 0301406008 | Region III (Central Luzon) | Bulacan | Bustos | Malamig | 14.9325 | 120.928 | U | 8005 | 2287 | 686 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01102-B07 | PTCI/MIDC | 14.9447 | 120.9241 | 1.42 | Terrestrial Optical Fiber Drop | 1.27 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2170 | 3 | 170 | 2170 | 0702222008 | Region VII (Central Visayas) | Cebu | Dalaguete | Casay | 9.8217 | 123.5503 | R | 4787 | 1259 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_CEB_0003 | LDIC | 9.8666 | 123.5804 | 5.98 | Terrestrial Optical Fiber Drop | 6.94 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2171 | 3 | 171 | 2171 | 1102303006 | Region XI (Davao Region) | Davao del Norte | Carmen | Guadalupe | 7.3761 | 125.7392 | R | 3203 | 865 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110430 | FTAP Globe | 7.3754 | 125.7397 | 0.1 | Terrestrial Optical Fiber Drop | 1.13 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2172 | 3 | 172 | 2172 | 0405804037 | Region IV-A (CALABARZON) | Rizal | Binangonan | Layunan | 14.4695 | 121.1934 | U | 2465 | 684 | 205 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | G6338 | FTAP Smart | 14.4681 | 121.1914 | 0.27 | Terrestrial Optical Fiber Drop | 1.01 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2173 | 3 | 173 | 2173 | 0304919022 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Bagong Buhay | 15.4622 | 121.1163 | R | 760 | 217 | 65 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNEG0002 | PTCI/MIDC | 15.4539 | 121.1051 | 1.51 | Terrestrial Optical Fiber Drop | 0.04 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2174 | 3 | 174 | 2174 | 0305407023 | Region III (Central Luzon) | Pampanga | Guagua | San Pedro | 14.9653 | 120.6242 | U | 5779 | 1444 | 433 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030519 | FTAP Globe | 14.9629 | 120.6303 | 0.71 | Terrestrial Optical Fiber Drop | 1.02 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2175 | 3 | 175 | 2175 | 0105538003 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Banaoang | 15.9935 | 120.4316 | R | 4513 | 1253 | 376 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00478 | Edgepoint | 15.9911 | 120.4345 | 0.41 | Terrestrial Optical Fiber Drop | 3.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2176 | 3 | 176 | 2176 | 0403403021 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Vicente | 14.3296 | 121.0779 | U | 10124 | 3067 | 920 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0035 | PTCI/MIDC | 14.3307 | 121.078 | 0.12 | Terrestrial Optical Fiber Drop | 1.03 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2177 | 3 | 177 | 2177 | 0301421004 | Region III (Central Luzon) | Bulacan | San Miguel | Bantog | 15.2112 | 120.9561 | U | 4134 | 1181 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BUL-00797 | Edgepoint | 15.2222 | 120.9532 | 1.27 | Terrestrial Optical Fiber Drop | 1.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2178 | 3 | 178 | 2178 | 1600301011 | Region XIII (Caraga) | Agusan del Sur | City of Bayugan | Noli | 8.7428 | 125.7233 | R | 4844 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130083 | FTAP Globe | 8.735 | 125.754 | 3.48 | Terrestrial Optical Fiber Drop | 4.88 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2179 | 3 | 179 | 2179 | 0702202007 | Region VII (Central Visayas) | Cebu | Alcoy | Pugalo | 9.728 | 123.5082 | R | 2729 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 2.6 | Terrestrial Optical Fiber Drop | 2.17 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2180 | 3 | 180 | 2180 | 0401008016 | Region IV-A (CALABARZON) | Batangas | Calatagan | Barangay 1 | 13.8459 | 120.6323 | R | 4186 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S0747 | FTAP Smart | 13.8365 | 120.6294 | 1.09 | Terrestrial Optical Fiber Drop | 1.78 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2181 | 3 | 181 | 2181 | 0103313014 | Region I (Ilocos Region) | La Union | Rosario | Concepcion | 16.2236 | 120.4695 | U | 3845 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02700-B05 | PTCI/MIDC | 16.2244 | 120.4789 | 1.01 | Terrestrial Optical Fiber Drop | 1.5 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2182 | 3 | 182 | 2182 | 0102817009 | Region I (Ilocos Region) | Ilocos Norte | Pasuquin | Davila | 18.4681 | 120.5784 | R | 4050 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4932 | FTAP Smart | 18.4671 | 120.5793 | 0.15 | Terrestrial Optical Fiber Drop | 1.05 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2183 | 3 | 183 | 2183 | 0307105018 | Region III (Central Luzon) | Zambales | Iba | Santo Rosario | 15.3311 | 119.9654 | R | 4578 | 1204 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0011 | PTCI/MIDC | 15.3368 | 119.9669 | 0.65 | Terrestrial Optical Fiber Drop | 1.4 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2184 | 3 | 184 | 2184 | 0403424006 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-B | 14.0648 | 121.3215 | R | 2031 | 615 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 1.06 | Terrestrial Optical Fiber Drop | 1.06 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2185 | 3 | 185 | 2185 | 0500517027 | Region V (Bicol Region) | Albay | City of Tabaco | Panal | 13.3568 | 123.7195 | U | 3517 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.68 | Terrestrial Optical Fiber Drop | 1.36 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2186 | 3 | 186 | 2186 | 0301415012 | Region III (Central Luzon) | Bulacan | Pandi | Mapulang Lupa | 14.8803 | 120.9651 | U | 31602 | 9029 | 2709 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BUL_0004 | LDIC | 14.8798 | 120.9728 | 0.83 | Terrestrial Optical Fiber Drop | 1.13 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2187 | 3 | 187 | 2187 | 0600407008 | Region VI (Western Visayas) | Aklan | Kalibo | Estancia | 11.6873 | 122.3661 | U | 9882 | 2533 | 760 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0016 | PTCI/MIDC | 11.6816 | 122.3635 | 0.69 | Terrestrial Optical Fiber Drop | 1.14 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2188 | 3 | 188 | 2188 | 1705209021 | MIMAROPA Region | Oriental Mindoro | Pinamalayan | Panggulayan | 13.0482 | 121.4585 | R | 2823 | 723 | 217 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170096 | FTAP Globe | 13.0506 | 121.4483 | 1.14 | Terrestrial Optical Fiber Drop | 2.13 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2189 | 3 | 189 | 2189 | 0501736018 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Antonio | 13.6449 | 123.4997 | R | 2983 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.94 | Terrestrial Optical Fiber Drop | 1.65 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2190 | 3 | 190 | 2190 | 0500506055 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 38 - Gogon | 13.1554 | 123.7449 | U | 6177 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050172 | FTAP Globe | 13.156 | 123.7413 | 0.4 | Terrestrial Optical Fiber Drop | 1.99 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2191 | 3 | 191 | 2191 | 1004301008 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Lumbo | 8.5716 | 124.4591 | R | 2229 | 571 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100122 | FTAP Globe | 8.5696 | 124.4727 | 1.51 | Terrestrial Optical Fiber Drop | 1.74 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2192 | 3 | 192 | 2192 | 0405645040 | Region IV-A (CALABARZON) | Quezon | Sariaya | Sampaloc 2 | 13.9537 | 121.506 | U | 6126 | 1612 | 484 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040416 | FTAP Globe | 13.9577 | 121.5077 | 0.48 | Terrestrial Optical Fiber Drop | 1.47 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2193 | 3 | 193 | 2193 | 0702221014 | Region VII (Central Visayas) | Cebu | Daanbantayan | Pajo | 11.2361 | 124.0125 | R | 4554 | 1198 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0070 | PTCI/MIDC | 11.2467 | 124.0163 | 1.25 | Terrestrial Optical Fiber Drop | 1.55 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2194 | 3 | 194 | 2194 | 0402118045 | Region IV-A (CALABARZON) | Cavite | Silang | Tartaria | 14.2036 | 121.0229 | U | 16542 | 4865 | 1460 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02231-C08 | PTCI/MIDC | 14.2027 | 121.0216 | 0.17 | Terrestrial Optical Fiber Drop | 2.37 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2195 | 3 | 195 | 2195 | 0305403020 | Region III (Central Luzon) | Pampanga | Arayat | San Agustin Norte | 15.1636 | 120.7791 | R | 3848 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01596-B07 | PTCI/MIDC | 15.1652 | 120.7792 | 0.18 | Terrestrial Optical Fiber Drop | 2.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2196 | 3 | 196 | 2196 | 0803738018 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Curva | 11.0323 | 124.5243 | R | 3396 | 893 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0044 | PTCI/MIDC | 11.0146 | 124.5305 | 2.08 | Terrestrial Optical Fiber Drop | 3.28 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2197 | 3 | 197 | 2197 | 0304917029 | Region III (Central Luzon) | Nueva Ecija | Science City of Muñoz | Poblacion West | 15.7204 | 120.9041 | U | 3539 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0027 | PTCI/MIDC | 15.7254 | 120.9006 | 0.54 | Terrestrial Optical Fiber Drop | 0.54 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2198 | 3 | 198 | 2198 | 0403424058 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Marcos | 14.1049 | 121.3013 | R | 3021 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040314 | FTAP Globe | 14.1042 | 121.3036 | 0.26 | Terrestrial Optical Fiber Drop | 3.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2199 | 3 | 199 | 2199 | 1600209009 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Kinabjangan | 8.9744 | 125.3601 | R | 3980 | 970 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH130068 | FTAP Globe | 8.9748 | 125.3618 | 0.19 | Terrestrial Optical Fiber Drop | 1.47 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2200 | 3 | 200 | 2200 | 0203114003 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Alibagu | 17.1011 | 121.8607 | U | 8201 | 2158 | 647 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00181 | Edgepoint | 17.1003 | 121.8622 | 0.19 | Terrestrial Optical Fiber Drop | 1.9 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2201 | 3 | 201 | 2201 | 0405645027 | Region IV-A (CALABARZON) | Quezon | Sariaya | Manggalang-Bantilan | 13.8361 | 121.4327 | R | 3636 | 956 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03252-C08 | PTCI/MIDC | 13.8382 | 121.449 | 1.78 | Terrestrial Optical Fiber Drop | 4.07 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2202 | 3 | 202 | 2202 | 0702218011 | Region VII (Central Visayas) | Cebu | Compostela | Magay | 10.4716 | 124.0188 | R | 3878 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070185 | FTAP BTS | 10.468 | 124.0168 | 0.45 | Terrestrial Optical Fiber Drop | 2.29 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2203 | 3 | 203 | 2203 | 0603026004 | Region VI (Western Visayas) | Iloilo | Leganes | Cagamutan Norte | 10.8122 | 122.6013 | R | 2555 | 672 | 202 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060040 | FTAP BTS | 10.805 | 122.5973 | 0.91 | Terrestrial Optical Fiber Drop | 2.12 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2204 | 3 | 204 | 2204 | 0501708024 | Region V (Bicol Region) | Camarines Sur | Calabanga | Paolbo | 13.7187 | 123.2502 | R | 4370 | 1040 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAS-02606 | Edgepoint | 13.7165 | 123.2373 | 1.42 | Terrestrial Optical Fiber Drop | 2.76 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2205 | 3 | 205 | 2205 | 1004308031 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Pangasihan | 8.8611 | 125.1703 | R | 2808 | 720 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0094 | PTCI/MIDC | 8.864 | 125.1706 | 0.33 | Terrestrial Optical Fiber Drop | 2.5 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2206 | 3 | 206 | 2206 | 0301421015 | Region III (Central Luzon) | Bulacan | San Miguel | Bulualto | 15.2199 | 120.9539 | R | 3021 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00797 | Edgepoint | 15.2222 | 120.9532 | 0.27 | Terrestrial Optical Fiber Drop | 0.43 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2207 | 3 | 207 | 2207 | 0102804001 | Region I (Ilocos Region) | Ilocos Norte | Bangui | Abaca | 18.5321 | 120.7561 | R | 1870 | 505 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ILN-03184 | Edgepoint | 18.5335 | 120.7602 | 0.46 | Terrestrial Optical Fiber Drop | 1.43 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2208 | 3 | 208 | 2208 | 0300804042 | Region III (Central Luzon) | Bataan | Dinalupihan | Tucop | 14.8973 | 120.4726 | R | 4784 | 1328 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 3937 | FTAP Smart | 14.8987 | 120.4736 | 0.19 | Terrestrial Optical Fiber Drop | 3.69 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2209 | 3 | 209 | 2209 | 0301423015 | Region III (Central Luzon) | Bulacan | Santa Maria | Parada | 14.8102 | 120.9865 | U | 9845 | 2812 | 844 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01012-B07 | PTCI/MIDC | 14.8101 | 120.9911 | 0.49 | Terrestrial Optical Fiber Drop | 1.17 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2210 | 3 | 210 | 2210 | 0500501006 | Region V (Bicol Region) | Albay | Bacacay | Bonga | 13.2873 | 123.7573 | U | 8025 | 1957 | 587 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050147 | FTAP Globe | 13.2832 | 123.7577 | 0.46 | Terrestrial Optical Fiber Drop | 2.81 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2211 | 3 | 211 | 2211 | 0304908017 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Niño | 15.3051 | 120.9435 | U | 5470 | 1562 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00765 | Edgepoint | 15.3098 | 120.9441 | 0.53 | Terrestrial Optical Fiber Drop | 0.04 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2212 | 3 | 212 | 2212 | 0501727016 | Region V (Bicol Region) | Camarines Sur | Pasacao | Santa Rosa Del Norte | 13.5138 | 123.0427 | U | 4126 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0005 | PTCI/MIDC | 13.5171 | 123.0437 | 0.38 | Terrestrial Optical Fiber Drop | 1.39 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2213 | 3 | 213 | 2213 | 0702250012 | Region VII (Central Visayas) | Cebu | City of Talisay | Poblacion | 10.2455 | 123.8446 | U | 10556 | 2777 | 833 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0228 | PTCI/MIDC | 10.2395 | 123.8406 | 0.8 | Terrestrial Optical Fiber Drop | 0.4 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2214 | 3 | 214 | 2214 | 1600212003 | Region XIII (Caraga) | Agusan del Norte | Remedios T. Romualdez | Basilisa | 9.0664 | 125.5807 | R | 2410 | 587 | 176 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130062 | FTAP Globe | 9.053 | 125.5852 | 1.57 | Terrestrial Optical Fiber Drop | 1.69 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2215 | 3 | 215 | 2215 | 0304909026 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Talabutab Sur | 15.57 | 121.0645 | R | 2826 | 807 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03339-B07 | PTCI/MIDC | 15.5689 | 121.0628 | 0.22 | Terrestrial Optical Fiber Drop | 2.86 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2216 | 3 | 216 | 2216 | 0803726008 | Region VIII (Eastern Visayas) | Leyte | Kananga | Lonoy | 11.2078 | 124.5673 | R | 3057 | 804 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 3.33 | Terrestrial Optical Fiber Drop | 2.61 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2217 | 3 | 217 | 2217 | 1004313002 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Dampil | 8.8265 | 124.7905 | R | 3042 | 780 | 234 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 2.24 | Terrestrial Optical Fiber Drop | 2.38 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2218 | 3 | 218 | 2218 | 1102414024 | Region XI (Davao Region) | Davao del Sur | Sulop | Talas | 6.6165 | 125.3454 | R | 2115 | 622 | 187 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110531 | FTAP Globe | 6.6039 | 125.3444 | 1.4 | Terrestrial Optical Fiber Drop | 1.96 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2219 | 3 | 219 | 2219 | 0702248008 | Region VII (Central Visayas) | Cebu | Tabogon | Ilihan | 10.9024 | 123.9675 | R | 3904 | 1027 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070307 | FTAP Globe | 10.9294 | 123.9607 | 3.09 | Terrestrial Optical Fiber Drop | 7.16 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2220 | 3 | 220 | 2220 | 0403424059 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Mateo | 14.112 | 121.299 | R | 3443 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040307 | FTAP Globe | 14.1123 | 121.3045 | 0.59 | Terrestrial Optical Fiber Drop | 3.92 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2221 | 3 | 221 | 2221 | 0600402001 | Region VI (Western Visayas) | Aklan | Balete | Aranas | 11.5645 | 122.3961 | U | 5782 | 1482 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 3.87 | Terrestrial Optical Fiber Drop | 2.38 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2222 | 3 | 222 | 2222 | 1102502007 | Region XI (Davao Region) | Davao Oriental | Banaybanay | Maputi | 7.0432 | 125.9655 | R | 4199 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTDLG0038 | PTCI/MIDC | 7.0669 | 125.9606 | 2.69 | Terrestrial Optical Fiber Drop | 10.33 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2223 | 3 | 223 | 2223 | 0300805014 | Region III (Central Luzon) | Bataan | Hermosa | Palihan | 14.8438 | 120.4732 | U | 6848 | 1902 | 571 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N1505 | FTAP Smart | 14.8402 | 120.4776 | 0.62 | Terrestrial Optical Fiber Drop | 1.9 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2224 | 3 | 224 | 2224 | 0105517009 | Region I (Ilocos Region) | Pangasinan | Calasiao | Gabon | 16.0114 | 120.3617 | R | 3050 | 847 | 254 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01748-B07 | PTCI/MIDC | 16.0133 | 120.3586 | 0.39 | Terrestrial Optical Fiber Drop | 2.8 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2225 | 3 | 225 | 2225 | 0203120012 | Region II (Cagayan Valley) | Isabela | Naguilian | Palattao | 17.0044 | 121.8259 | R | 2714 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01356-B06 | PTCI/MIDC | 17.0051 | 121.8251 | 0.11 | Terrestrial Optical Fiber Drop | 1.14 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2226 | 3 | 226 | 2226 | 0307114009 | Region III (Central Luzon) | Zambales | Subic | Calapandayan | 14.8738 | 120.2355 | U | 10846 | 2854 | 856 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0019 | PTCI/MIDC | 14.8723 | 120.2383 | 0.35 | Terrestrial Optical Fiber Drop | 1.71 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2227 | 3 | 227 | 2227 | 0702215015 | Region VII (Central Visayas) | Cebu | Carmen | Luyang | 10.6009 | 124.0224 | U | 6739 | 1773 | 532 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070028 | FTAP BTS | 10.6051 | 124.0252 | 0.56 | Terrestrial Optical Fiber Drop | 2.71 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2228 | 3 | 228 | 2228 | 0702239012 | Region VII (Central Visayas) | Cebu | Ronda | Santa Cruz | 10.0124 | 123.4126 | R | 3654 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0264 | PTCI/MIDC | 10.0263 | 123.4161 | 1.6 | Terrestrial Optical Fiber Drop | 1.47 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2229 | 3 | 229 | 2229 | 0402112014 | Region IV-A (CALABARZON) | Cavite | Magallanes | Kabulusan | 14.1789 | 120.7447 | R | 1952 | 574 | 172 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040272 | FTAP Globe | 14.1766 | 120.7389 | 0.68 | Terrestrial Optical Fiber Drop | 1.2 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2230 | 3 | 230 | 2230 | 0501603021 | Region V (Bicol Region) | Camarines Norte | Daet | Mancruz | 14.0965 | 122.9552 | R | 3490 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAN-03170 | Edgepoint | 14.0939 | 122.9489 | 0.74 | Terrestrial Optical Fiber Drop | 2.01 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2231 | 3 | 231 | 2231 | 0401020021 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Pansol | 13.8861 | 121.2476 | R | 4860 | 1350 | 405 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040514 | FTAP Globe | 13.8971 | 121.2443 | 1.27 | Terrestrial Optical Fiber Drop | 2.69 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2232 | 3 | 232 | 2232 | 0803708057 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Plaridel | 10.5647 | 124.7646 | R | 3711 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0010 | PTCI/MIDC | 10.5624 | 124.7653 | 0.27 | Terrestrial Optical Fiber Drop | 13.39 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2233 | 3 | 233 | 2233 | 0403405004 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barandal | 14.1885 | 121.1302 | U | 19814 | 6004 | 1801 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.35 | Terrestrial Optical Fiber Drop | 1.98 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2234 | 3 | 234 | 2234 | 0401019003 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Banilad | 14.0674 | 120.7343 | U | 5158 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040339 | FTAP Globe | 14.0802 | 120.7249 | 1.75 | Terrestrial Optical Fiber Drop | 2.07 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2235 | 3 | 235 | 2235 | 0301422009 | Region III (Central Luzon) | Bulacan | San Rafael | Capihan | 14.9975 | 120.9304 | U | 6405 | 1830 | 549 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00949 | Edgepoint | 15.0009 | 120.9306 | 0.37 | Terrestrial Optical Fiber Drop | 1.14 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2236 | 3 | 236 | 2236 | 0105533014 | Region I (Ilocos Region) | Pangasinan | San Fabian | Longos | 16.1059 | 120.3952 | R | 2872 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02184 | Edgepoint | 16.0971 | 120.3938 | 0.99 | Terrestrial Optical Fiber Drop | 1.19 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2237 | 3 | 237 | 2237 | 0403404003 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Banlic | 14.2316 | 121.1371 | U | 22631 | 6857 | 2057 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040231 | FTAP Globe | 14.2324 | 121.1364 | 0.11 | Terrestrial Optical Fiber Drop | 1.82 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2238 | 3 | 238 | 2238 | 0702214001 | Region VII (Central Visayas) | Cebu | City of Carcar | Bolinawan | 10.0896 | 123.6331 | U | 13804 | 3632 | 1090 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0022 | PTCI/MIDC | 10.0841 | 123.6309 | 0.66 | Terrestrial Optical Fiber Drop | 1.36 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2239 | 3 | 239 | 2239 | 1402705013 | Cordillera Administrative Region (CAR) | Ifugao | Lamut | Poblacion East | 16.65 | 121.2211 | R | 2037 | 522 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_IFU_0002 | LDIC | 121.2223 | 16.654 | 0.47 | Terrestrial Optical Fiber Drop | 1.09 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2240 | 3 | 240 | 2240 | 0401009007 | Region IV-A (CALABARZON) | Batangas | Cuenca | Dita | 13.917 | 121.0731 | R | 4793 | 1331 | 399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4164 | FTAP Smart | 13.9218 | 121.0718 | 0.54 | Terrestrial Optical Fiber Drop | 3.3 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2241 | 3 | 241 | 2241 | 0305413044 | Region III (Central Luzon) | Pampanga | Mexico | Sapang Maisac | 15.1809 | 120.6281 | U | 8578 | 2144 | 643 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01629-B07 | PTCI/MIDC | 15.1801 | 120.6295 | 0.18 | Terrestrial Optical Fiber Drop | 2.45 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2242 | 3 | 242 | 2242 | 1102303007 | Region XI (Davao Region) | Davao del Norte | Carmen | Ising | 7.3598 | 125.7063 | U | 14442 | 3903 | 1171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110326 | FTAP BTS | 7.3553 | 125.708 | 0.54 | Terrestrial Optical Fiber Drop | 1.01 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2243 | 3 | 243 | 2243 | 0301406005 | Region III (Central Luzon) | Bulacan | Bustos | Cambaog | 14.928 | 120.8966 | U | 6899 | 1971 | 591 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01030 | Edgepoint | 14.9277 | 120.8939 | 0.3 | Terrestrial Optical Fiber Drop | 2.41 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2244 | 3 | 244 | 2244 | 0201516034 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Sta. Maria | 18.1471 | 121.6611 | R | 2451 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 1.34 | Terrestrial Optical Fiber Drop | 2.84 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2245 | 3 | 245 | 2245 | 0304926012 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Malasin | 15.8074 | 121.0007 | U | 9389 | 2682 | 805 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N0194 | FTAP Smart | 15.8027 | 120.9985 | 0.57 | Terrestrial Optical Fiber Drop | 1.98 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2246 | 3 | 246 | 2246 | 0306907019 | Region III (Central Luzon) | Tarlac | La Paz | San Isidro | 15.4413 | 120.728 | U | 3771 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.09 | Terrestrial Optical Fiber Drop | 1.31 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2247 | 3 | 247 | 2247 | 0307113011 | Region III (Central Luzon) | Zambales | Santa Cruz | Lipay | 15.7492 | 119.9092 | U | 6760 | 1778 | 533 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZMG0008 | PTCI/MIDC | 15.7531 | 119.9154 | 0.79 | Terrestrial Optical Fiber Drop | 2.07 | 0.71 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2248 | 3 | 248 | 2248 | 1108211002 | Region XI (Davao Region) | Davao de Oro | Pantukan | Bongbong | 7.1076 | 125.9083 | R | 4676 | 1263 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCVG0011 | PTCI/MIDC | 7.1283 | 125.8981 | 2.56 | Terrestrial Optical Fiber Drop | 3.13 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2249 | 3 | 249 | 2249 | 0304911056 | Region III (Central Luzon) | Nueva Ecija | Guimba | San Roque | 15.6578 | 120.7599 | U | 6874 | 1964 | 589 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02180 | Edgepoint | 15.2484 | 120.9527 | 0.77 | Terrestrial Optical Fiber Drop | 0.73 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2250 | 3 | 250 | 2250 | 0931700088 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Tictapul | 7.4044 | 122.315 | R | 3677 | 1021 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH090167 | FTAP Globe | 7.4165 | 122.325 | 1.73 | Terrestrial Optical Fiber Drop | 19.17 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2251 | 3 | 251 | 2251 | 0105503031 | Region I (Ilocos Region) | Pangasinan | City of Alaminos | San Vicente | 16.14 | 119.9933 | U | 4473 | 1242 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010127 | FTAP Globe | 16.1319 | 119.9976 | 1.02 | Terrestrial Optical Fiber Drop | 1.58 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2252 | 3 | 252 | 2252 | 0702245004 | Region VII (Central Visayas) | Cebu | Santander | Liloan | 9.4219 | 123.3091 | R | 2383 | 627 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0251 | PTCI/MIDC | 9.444 | 123.3042 | 2.5 | Terrestrial Optical Fiber Drop | 2.5 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2253 | 3 | 253 | 2253 | 0305415017 | Region III (Central Luzon) | Pampanga | Porac | Manibaug Libutad | 15.1075 | 120.5624 | U | 5916 | 1479 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-00869 | Edgepoint | 15.1162 | 120.5663 | 1.06 | Terrestrial Optical Fiber Drop | 1.48 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2254 | 3 | 254 | 2254 | 0702240011 | Region VII (Central Visayas) | Cebu | Samboan | Poblacion | 9.5325 | 123.3063 | R | 3975 | 1046 | 314 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0143 | PTCI/MIDC | 9.5262 | 123.3076 | 0.71 | Terrestrial Optical Fiber Drop | 12.19 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2255 | 3 | 255 | 2255 | 0304908011 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Nicolas | 15.3037 | 120.9361 | U | 14324 | 4092 | 1228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030051 | FTAP BTS | 15.3014 | 120.9329 | 0.43 | Terrestrial Optical Fiber Drop | 0.04 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2256 | 3 | 256 | 2256 | 0401020023 | Region IV-A (CALABARZON) | Batangas | Padre Garcia | Poblacion | 13.8794 | 121.2092 | U | 3461 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040529 | FTAP Globe | 13.8755 | 121.2157 | 0.82 | Terrestrial Optical Fiber Drop | 1.65 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2257 | 3 | 257 | 2257 | 0304932003 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Carmen | 15.4456 | 120.8278 | R | 3949 | 1128 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01502-B07 | PTCI/MIDC | 15.4529 | 120.8084 | 2.24 | Terrestrial Optical Fiber Drop | 4.1 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2258 | 3 | 258 | 2258 | 0803702005 | Region VIII (Eastern Visayas) | Leyte | Alangalang | Binongto-an | 11.2159 | 124.8269 | R | 2525 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0004 | PTCI/MIDC | 11.2093 | 124.8426 | 1.86 | Terrestrial Optical Fiber Drop | 1.64 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2259 | 3 | 259 | 2259 | 0600407015 | Region VI (Western Visayas) | Aklan | Kalibo | Tigayon | 11.6738 | 122.3609 | U | 6328 | 1622 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0016 | PTCI/MIDC | 11.6816 | 122.3635 | 0.91 | Terrestrial Optical Fiber Drop | 2.71 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2260 | 3 | 260 | 2260 | 0105512024 | Region I (Ilocos Region) | Pangasinan | Binalonan | Sumabnit | 16.0307 | 120.5822 | U | 4988 | 1385 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00450 | Edgepoint | 16.0229 | 120.5792 | 0.92 | Terrestrial Optical Fiber Drop | 1.55 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2261 | 3 | 261 | 2261 | 0401022022 | Region IV-A (CALABARZON) | Batangas | San Jose | Pinagtung-Ulan | 13.9235 | 121.0832 | R | 4879 | 1355 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040466 | FTAP Globe | 13.9262 | 121.0878 | 0.57 | Terrestrial Optical Fiber Drop | 4.22 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2262 | 3 | 262 | 2262 | 0401034016 | Region IV-A (CALABARZON) | Batangas | Tuy | Rillo | 14.0217 | 120.7299 | U | 2660 | 738 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1398 | FTAP Smart | 14.0064 | 120.7303 | 0.6 | Terrestrial Optical Fiber Drop | 0.17 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2263 | 3 | 263 | 2263 | 0403415007 | Region IV-A (CALABARZON) | Laguna | Magdalena | Buenavista | 14.2246 | 121.4288 | R | 2699 | 817 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 2.61 | Terrestrial Optical Fiber Drop | 2.9 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2264 | 3 | 264 | 2264 | 0203126014 | Region II (Cagayan Valley) | Isabela | Roxas | Luna | 17.116 | 121.6248 | R | 1583 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01359-B06 | PTCI/MIDC | 17.1149 | 121.6222 | 0.3 | Terrestrial Optical Fiber Drop | 1.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2265 | 3 | 265 | 2265 | 0401008003 | Region IV-A (CALABARZON) | Batangas | Calatagan | Balibago | 13.9271 | 120.6276 | R | 3963 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040474 | FTAP Globe | 13.9239 | 120.6238 | 0.55 | Terrestrial Optical Fiber Drop | 2.69 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2266 | 3 | 266 | 2266 | 0102903029 | Region I (Ilocos Region) | Ilocos Sur | Bantay | Tay-ac | 17.6102 | 120.4458 | R | 2644 | 695 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010054 | FTAP Globe | 17.2614 | 120.5377 | 2.32 | Terrestrial Optical Fiber Drop | 5.35 | 2.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2267 | 3 | 267 | 2267 | 0500517036 | Region V (Bicol Region) | Albay | City of Tabaco | San Antonio | 13.3488 | 123.6793 | R | 4907 | 1196 | 359 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02487-C10 | PTCI/MIDC | 13.3694 | 123.6761 | 2.32 | Terrestrial Optical Fiber Drop | 2.06 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2268 | 3 | 268 | 2268 | 0702251028 | Region VII (Central Visayas) | Cebu | City of Toledo | Poblacion | 10.3796 | 123.6415 | U | 15924 | 4190 | 1257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0172 | PTCI/MIDC | 10.3817 | 123.6436 | 0.33 | Terrestrial Optical Fiber Drop | 2.76 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2269 | 3 | 269 | 2269 | 0305411020 | Region III (Central Luzon) | Pampanga | Magalang | Santa Cruz | 15.2103 | 120.6621 | U | 7765 | 1941 | 582 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03221-B07 | PTCI/MIDC | 15.211 | 120.6581 | 0.44 | Terrestrial Optical Fiber Drop | 2.26 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2270 | 3 | 270 | 2270 | 1001302015 | Region X (Northern Mindanao) | Bukidnon | Damulog | Poblacion | 7.4837 | 124.9439 | R | 5479 | 1441 | 432 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0004 | PTCI/MIDC | 7.4878 | 124.9412 | 0.55 | Terrestrial Optical Fiber Drop | 9.96 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2271 | 3 | 271 | 2271 | 1004314010 | Region X (Northern Mindanao) | Misamis Oriental | Laguindingan | Sinai | 8.5777 | 124.4284 | R | 2506 | 642 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0059 | PTCI/MIDC | 8.5798 | 124.448 | 2.18 | Terrestrial Optical Fiber Drop | 1.71 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2272 | 3 | 272 | 2272 | 0105538017 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Minien West | 15.9786 | 120.4727 | U | 5272 | 1464 | 439 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00487 | Edgepoint | 15.9796 | 120.4704 | 0.27 | Terrestrial Optical Fiber Drop | 1.49 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2273 | 3 | 273 | 2273 | 0405628018 | Region IV-A (CALABARZON) | Quezon | Mulanay | Ibabang Cambuga | 13.5848 | 122.4592 | R | 3750 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040617 | FTAP Globe | 13.6148 | 122.5239 | 7.74 | Terrestrial Optical Fiber Drop | 2.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2274 | 3 | 274 | 2274 | 0908313029 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Siay | Monching | 7.7282 | 122.8438 | R | 4117 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH090144 | FTAP Globe | 7.7505 | 122.8299 | 2.9 | Terrestrial Optical Fiber Drop | 23.28 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2275 | 3 | 275 | 2275 | 1600302006 | Region XIII (Caraga) | Agusan del Sur | Bunawan | San Andres | 8.2025 | 125.9939 | R | 4413 | 1131 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0009 | PTCI/MIDC | 8.2105 | 125.9905 | 0.96 | Terrestrial Optical Fiber Drop | 2.49 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2276 | 3 | 276 | 2276 | 0307105012 | Region III (Central Luzon) | Zambales | Iba | Palanginan | 15.3171 | 119.9916 | U | 11507 | 3028 | 908 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030417 | FTAP Globe | 15.3178 | 119.9943 | 0.3 | Terrestrial Optical Fiber Drop | 1.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2277 | 3 | 277 | 2277 | 0701216001 | Region VII (Central Visayas) | Bohol | Cortes | De la Paz | 9.701 | 123.8677 | R | 2987 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0011 | PTCI/MIDC | 9.7063 | 123.8715 | 0.72 | Terrestrial Optical Fiber Drop | 2.52 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2278 | 3 | 278 | 2278 | 0301406012 | Region III (Central Luzon) | Bulacan | Bustos | Talampas | 14.9312 | 120.9068 | R | 3802 | 1086 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01022 | Edgepoint | 14.9338 | 120.9094 | 0.4 | Terrestrial Optical Fiber Drop | 2.69 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2279 | 3 | 279 | 2279 | 1108207004 | Region XI (Davao Region) | Davao de Oro | Monkayo | Baylo | 7.8539 | 126.071 | R | 4017 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0015 | PTCI/MIDC | 7.8475 | 126.0672 | 0.83 | Terrestrial Optical Fiber Drop | 3.37 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2280 | 3 | 280 | 2280 | 1004320005 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Maputi | 8.4477 | 124.293 | R | 3099 | 794 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0071 | PTCI/MIDC | 8.4328 | 124.2889 | 1.71 | Terrestrial Optical Fiber Drop | 1.82 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2281 | 3 | 281 | 2281 | 1606706002 | Region XIII (Caraga) | Surigao del Norte | Claver | Cagdianao | 9.5311 | 125.8618 | R | 4433 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130017 | FTAP BTS | 9.5401 | 125.841 | 2.49 | Terrestrial Optical Fiber Drop | 20.49 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2282 | 3 | 282 | 2282 | 0201525011 | Region II (Cagayan Valley) | Cagayan | Santa Teresita | Simpatuyo | 18.2478 | 121.8957 | R | 2746 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0015 | LDIC | 18.2484 | 121.8962 | 0.08 | Terrestrial Optical Fiber Drop | 1.63 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2283 | 3 | 283 | 2283 | 0501715008 | Region V (Bicol Region) | Camarines Sur | Goa | Catagbacan | 13.6727 | 123.5006 | R | 4540 | 1080 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-02602 | Edgepoint | 13.6957 | 123.4931 | 2.68 | Terrestrial Optical Fiber Drop | 2.85 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2284 | 3 | 284 | 2284 | 0603047014 | Region VI (Western Visayas) | Iloilo | Zarraga | Malunang | 10.8202 | 122.6078 | R | 1479 | 389 | 117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060258 | FTAP Globe | 10.821 | 122.6091 | 0.17 | Terrestrial Optical Fiber Drop | 1.06 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2285 | 3 | 285 | 2285 | 0402118010 | Region IV-A (CALABARZON) | Cavite | Silang | Bucal | 14.283 | 120.9602 | R | 2192 | 644 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.18 | Terrestrial Optical Fiber Drop | 1.9 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2286 | 3 | 286 | 2286 | 0402120007 | Region IV-A (CALABARZON) | Cavite | Tanza | Calibuyo | 14.3584 | 120.8068 | U | 6930 | 2038 | 611 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02640-C08 | PTCI/MIDC | 14.359 | 120.8103 | 0.38 | Terrestrial Optical Fiber Drop | 2.16 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2287 | 3 | 287 | 2287 | 0301404009 | Region III (Central Luzon) | Bulacan | Bocaue | Bunlo | 14.7882 | 120.932 | U | 4200 | 1200 | 360 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-02208 | Edgepoint | 14.7838 | 120.934 | 0.53 | Terrestrial Optical Fiber Drop | 1.04 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2288 | 3 | 288 | 2288 | 1001312025 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Patpat | 8.1954 | 125.0607 | U | 4885 | 1285 | 386 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100176 | FTAP Globe | 8.1951 | 125.0658 | 0.56 | Terrestrial Optical Fiber Drop | 1.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2289 | 3 | 289 | 2289 | 0604529009 | Region VI (Western Visayas) | Negros Occidental | Toboso | Tabun-ac | 10.7284 | 123.4875 | R | 4046 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060338 | FTAP Globe | 10.7452 | 123.4815 | 1.99 | Terrestrial Optical Fiber Drop | 12.71 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2290 | 3 | 290 | 2290 | 1004304001 | Region X (Northern Mindanao) | Misamis Oriental | Binuangan | Dampias | 8.9082 | 124.7861 | R | 1057 | 271 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0074 | PTCI/MIDC | 8.9525 | 124.7849 | 4.93 | Terrestrial Optical Fiber Drop | 1.07 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2291 | 3 | 291 | 2291 | 0702233013 | Region VII (Central Visayas) | Cebu | Moalboal | Tomonoy | 9.9305 | 123.4005 | R | 2694 | 708 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 2.52 | Terrestrial Optical Fiber Drop | 1.1 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2292 | 3 | 292 | 2292 | 0702252040 | Region VII (Central Visayas) | Cebu | Tuburan | Putat | 10.7987 | 123.8553 | R | 4978 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0178 | PTCI/MIDC | 10.7864 | 123.8481 | 1.57 | Terrestrial Optical Fiber Drop | 17.08 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2293 | 3 | 293 | 2293 | 0306910011 | Region III (Central Luzon) | Tarlac | Paniqui | Carino | 15.6463 | 120.5887 | U | 5420 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00618 | Edgepoint | 15.6463 | 120.5901 | 0.16 | Terrestrial Optical Fiber Drop | 2.42 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2294 | 3 | 294 | 2294 | 0301421037 | Region III (Central Luzon) | Bulacan | San Miguel | Poblacion | 15.1443 | 120.9769 | R | 3269 | 934 | 280 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00845 | Edgepoint | 15.1441 | 120.9747 | 0.24 | Terrestrial Optical Fiber Drop | 1.16 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2295 | 3 | 295 | 2295 | 0500508053 | Region V (Bicol Region) | Albay | City of Ligao | Tuburan | 13.2382 | 123.5512 | U | 6437 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0017 | PTCI/MIDC | 13.2431 | 123.5395 | 1.38 | Terrestrial Optical Fiber Drop | 1.73 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2296 | 3 | 296 | 2296 | 0306916068 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Miguel | 15.4376 | 120.5982 | U | 8881 | 2277 | 683 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030399 | FTAP Globe | 15.4372 | 120.6017 | 0.38 | Terrestrial Optical Fiber Drop | 2.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2297 | 3 | 297 | 2297 | 0105543010 | Region I (Ilocos Region) | Pangasinan | Tayug | Libertad | 16.018 | 120.7583 | R | 2635 | 731 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01767-B07 | PTCI/MIDC | 16.0297 | 120.7499 | 1.58 | Terrestrial Optical Fiber Drop | 1.54 | 1.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2298 | 3 | 298 | 2298 | 0603027021 | Region VI (Western Visayas) | Iloilo | Lemery | Poblacion SE Zone | 11.2114 | 122.9108 | R | 2853 | 750 | 225 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0048 | PTCI/MIDC | 11.2198 | 122.9209 | 1.44 | Terrestrial Optical Fiber Drop | 2.49 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2299 | 3 | 299 | 2299 | 0403401008 | Region IV-A (CALABARZON) | Laguna | Alaminos | San Andres | 14.0595 | 121.218 | R | 4903 | 1485 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_BAT_0016 | LDIC | 121.1983 | 14.0565 | 2.15 | Terrestrial Optical Fiber Drop | 4.54 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2300 | 3 | 300 | 2300 | 0301419028 | Region III (Central Luzon) | Bulacan | San Ildefonso | San Juan | 15.0833 | 120.9393 | U | 5212 | 1489 | 447 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030477 | FTAP Globe | 15.082 | 120.9387 | 0.16 | Terrestrial Optical Fiber Drop | 1.11 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2301 | 3 | 301 | 2301 | 0300804032 | Region III (Central Luzon) | Bataan | Dinalupihan | Saguing | 14.8618 | 120.4406 | U | 5424 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-02573 | Edgepoint | 14.8612 | 120.4383 | 0.26 | Terrestrial Optical Fiber Drop | 1.81 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2302 | 3 | 302 | 2302 | 1102303019 | Region XI (Davao Region) | Davao del Norte | Carmen | Santo Niño | 7.3358 | 125.6952 | U | 6314 | 1706 | 512 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0003 | PTCI/MIDC | 7.3381 | 125.6955 | 0.25 | Terrestrial Optical Fiber Drop | 1.99 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2303 | 3 | 303 | 2303 | 0701205005 | Region VII (Central Visayas) | Bohol | Baclayon | Landican | 9.6291 | 123.9055 | R | 1010 | 252 | 76 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070157 | FTAP BTS | 9.654 | 123.8788 | 4.02 | Terrestrial Optical Fiber Drop | 1.04 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2304 | 3 | 304 | 2304 | 1003512001 | Region X (Northern Mindanao) | Lanao del Norte | Maigo | Balagatasa | 8.1479 | 123.9403 | R | 4786 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100180 | FTAP Globe | 8.1602 | 123.961 | 2.66 | Terrestrial Optical Fiber Drop | 19.43 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2305 | 3 | 305 | 2305 | 0730600057 | Region VII (Central Visayas) | Cebu | City of Cebu | Pit-os | 10.3941 | 123.922 | U | 7761 | 2425 | 728 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070321 | FTAP Globe | 10.3983 | 123.9199 | 0.52 | Terrestrial Optical Fiber Drop | 2.7 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2306 | 3 | 306 | 2306 | 1004310013 | Region X (Northern Mindanao) | Misamis Oriental | Initao | San Pedro | 8.4875 | 124.2968 | R | 3162 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0051 | PTCI/MIDC | 8.477 | 124.2967 | 1.17 | Terrestrial Optical Fiber Drop | 1.9 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2307 | 3 | 307 | 2307 | 0205002004 | Region II (Cagayan Valley) | Nueva Vizcaya | Aritao | Bone South | 16.242 | 120.9934 | R | 4916 | 1293 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00377 | Edgepoint | 16.2448 | 120.9951 | 0.37 | Terrestrial Optical Fiber Drop | 8.59 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2308 | 3 | 308 | 2308 | 0601914036 | Region VI (Western Visayas) | Capiz | City of Roxas | Loctugan | 11.5102 | 122.7661 | R | 2447 | 643 | 193 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAP-03142 | Edgepoint | 11.5148 | 122.7618 | 0.69 | Terrestrial Optical Fiber Drop | 1.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2309 | 3 | 309 | 2309 | 0631000011 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Balantang | 10.7567 | 122.5739 | U | 4930 | 1173 | 352 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.89 | Terrestrial Optical Fiber Drop | 1.47 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2310 | 3 | 310 | 2310 | 1001321020 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Mailag | 7.9717 | 125.1156 | U | 8615 | 2267 | 680 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100198 | FTAP Globe | 7.9734 | 125.1346 | 2.1 | Terrestrial Optical Fiber Drop | 2.36 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2311 | 3 | 311 | 2311 | 0500514032 | Region V (Bicol Region) | Albay | Polangui | Matacon | 13.3258 | 123.4295 | R | 4666 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050135 | FTAP Globe | 13.3317 | 123.4228 | 0.98 | Terrestrial Optical Fiber Drop | 3.11 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2312 | 3 | 312 | 2312 | 0301410047 | Region III (Central Luzon) | Bulacan | City of Malolos | Santisima Trinidad | 14.8758 | 120.8253 | U | 6991 | 1997 | 599 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01080 | Edgepoint | 14.8745 | 120.8238 | 0.22 | Terrestrial Optical Fiber Drop | 2.46 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2313 | 3 | 313 | 2313 | 1003505028 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Lapinig | 7.9229 | 123.6866 | R | 4735 | 1127 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100204 | FTAP Globe | 7.9274 | 123.6714 | 1.74 | Terrestrial Optical Fiber Drop | 11.52 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2314 | 3 | 314 | 2314 | 1600209018 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Santa Ana | 8.9699 | 125.3396 | R | 2930 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0017 | PTCI/MIDC | 8.9849 | 125.3459 | 1.8 | Terrestrial Optical Fiber Drop | 1.06 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2315 | 3 | 315 | 2315 | 0731300022 | Region VII (Central Visayas) | Cebu | City of Mandaue | Subangdaku | 10.3225 | 123.923 | U | 17114 | 4889 | 1467 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0106 | PTCI/MIDC | 10.3197 | 123.9204 | 0.42 | Terrestrial Optical Fiber Drop | 1.95 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2316 | 3 | 316 | 2316 | 1731500026 | MIMAROPA Region | Palawan | City of Puerto Princesa | Manalo | 9.7361 | 118.7457 | R | 2877 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170233 | FTAP Globe | 9.9781 | 118.8602 | 3.79 | Terrestrial Optical Fiber Drop | 1.42 | 1.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2317 | 3 | 317 | 2317 | 0331400014 | Region III (Central Luzon) | Zambales | City of Olongapo | New Cabalan | 14.8496 | 120.3354 | U | 33937 | 9172 | 2752 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03327-B07 | PTCI/MIDC | 14.8451 | 120.3401 | 0.71 | Terrestrial Optical Fiber Drop | 1.22 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2318 | 3 | 318 | 2318 | 0506211014 | Region V (Bicol Region) | Sorsogon | Magallanes | Caditaan | 12.8042 | 123.8507 | R | 3603 | 900 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSOG0002 | PTCI/MIDC | 12.8037 | 123.8513 | 0.09 | Terrestrial Optical Fiber Drop | 2.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2319 | 3 | 319 | 2319 | 0307110012 | Region III (Central Luzon) | Zambales | San Felipe | Sindol | 15.077 | 120.0663 | R | 2433 | 640 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ZMB-00898 | Edgepoint | 15.0678 | 120.0687 | 1.04 | Terrestrial Optical Fiber Drop | 1.96 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2320 | 3 | 320 | 2320 | 0803708038 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Kilim | 10.7127 | 124.7966 | R | 3625 | 953 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080359 | FTAP Globe | 10.7106 | 124.7977 | 0.27 | Terrestrial Optical Fiber Drop | 3.74 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2321 | 3 | 321 | 2321 | 0603037005 | Region VI (Western Visayas) | Iloilo | Pototan | Batuan | 10.9556 | 122.6404 | R | 1936 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILR0060 | PTCI/MIDC | 10.9488 | 122.6366 | 0.86 | Terrestrial Optical Fiber Drop | 1.06 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2322 | 3 | 322 | 2322 | 0501603023 | Region V (Bicol Region) | Camarines Norte | Daet | Pamorangon | 14.091 | 122.9574 | R | 3299 | 824 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAN-03170 | Edgepoint | 14.0939 | 122.9489 | 0.97 | Terrestrial Optical Fiber Drop | 2.65 | 1.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2323 | 3 | 323 | 2323 | 0501610004 | Region V (Bicol Region) | Camarines Norte | Santa Elena | Rizal | 14.1969 | 122.4031 | R | 3062 | 765 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050008 | FTAP Globe | 14.218 | 122.3945 | 2.52 | Terrestrial Optical Fiber Drop | 2.18 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2324 | 3 | 324 | 2324 | 0201516025 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Maxingal | 18.2119 | 121.6657 | R | 2741 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-02600 | Edgepoint | 18.1948 | 121.6623 | 1.93 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2325 | 3 | 325 | 2325 | 0401014012 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Bugtong na Pulo | 14.0004 | 121.1675 | U | 7906 | 2196 | 659 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01963-C08 | PTCI/MIDC | 14.0096 | 121.1646 | 1.08 | Terrestrial Optical Fiber Drop | 2.3 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2326 | 3 | 326 | 2326 | 0105533030 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw Vidal | 16.1203 | 120.3935 | R | 3605 | 1001 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00399 | Edgepoint | 16.1619 | 120.4277 | 1.46 | Terrestrial Optical Fiber Drop | 0.78 | 0.77 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2327 | 3 | 327 | 2327 | 1705204011 | MIMAROPA Region | Oriental Mindoro | Bulalacao | Nasukob | 12.3632 | 121.3441 | R | 3745 | 960 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170138 | FTAP Globe | 12.3442 | 121.3679 | 3.34 | Terrestrial Optical Fiber Drop | 3.59 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2328 | 3 | 328 | 2328 | 0403406005 | Region IV-A (CALABARZON) | Laguna | Calauan | Imok | 14.1226 | 121.3031 | R | 2778 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040307 | FTAP Globe | 14.1123 | 121.3045 | 1.16 | Terrestrial Optical Fiber Drop | 2.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2329 | 3 | 329 | 2329 | 0405603039 | Region IV-A (CALABARZON) | Quezon | Atimonan | Tagbakin | 13.9964 | 121.912 | U | 5639 | 1483 | 445 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1405 | FTAP Smart | 14.0006 | 121.9248 | 1.45 | Terrestrial Optical Fiber Drop | 1.52 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2330 | 3 | 330 | 2330 | 0405619026 | Region IV-A (CALABARZON) | Quezon | Gumaca | Mabini | 13.9183 | 122.0961 | R | 1988 | 523 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1414 | FTAP Smart | 13.9191 | 122.0931 | 0.34 | Terrestrial Optical Fiber Drop | 1.35 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2331 | 3 | 331 | 2331 | 0702213011 | Region VII (Central Visayas) | Cebu | Borbon | Don Gregorio Antigua | 10.8762 | 123.9774 | R | 4071 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070308 | FTAP Globe | 10.8648 | 123.9816 | 1.35 | Terrestrial Optical Fiber Drop | 7 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2332 | 3 | 332 | 2332 | 0603026012 | Region VI (Western Visayas) | Iloilo | Leganes | Guihaman | 10.7768 | 122.5843 | R | 2324 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0047 | PTCI/MIDC | 10.785 | 122.5909 | 1.17 | Terrestrial Optical Fiber Drop | 1.13 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2333 | 3 | 333 | 2333 | 0300804007 | Region III (Central Luzon) | Bataan | Dinalupihan | Colo | 14.848 | 120.4125 | R | 3814 | 1059 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0006 | PTCI/MIDC | 14.8469 | 120.4161 | 0.4 | Terrestrial Optical Fiber Drop | 1.63 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2334 | 3 | 334 | 2334 | 0401021021 | Region IV-A (CALABARZON) | Batangas | Rosario | Masaya | 13.8371 | 121.1846 | U | 4757 | 1321 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F01951-C08 | PTCI/MIDC | 13.8436 | 121.1948 | 1.32 | Terrestrial Optical Fiber Drop | 1.99 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2335 | 3 | 335 | 2335 | 0304916006 | Region III (Central Luzon) | Nueva Ecija | Lupao | J. U. Tienzo | 15.8723 | 120.9038 | R | 1980 | 565 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-00551 | Edgepoint | 15.8803 | 120.8984 | 1.05 | Terrestrial Optical Fiber Drop | 1.53 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2336 | 3 | 336 | 2336 | 0304930005 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bakal II | 15.6977 | 120.8986 | U | 4059 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1224 | FTAP Smart | 15.6939 | 120.8967 | 0.47 | Terrestrial Optical Fiber Drop | 2.05 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2337 | 3 | 337 | 2337 | 0304932020 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | San Isidro | 15.4485 | 120.8005 | U | 6681 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.12 | Terrestrial Optical Fiber Drop | 1.18 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2338 | 3 | 338 | 2338 | 0500509015 | Region V (Bicol Region) | Albay | Malilipot | San Jose | 13.2935 | 123.7581 | U | 5308 | 1294 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050139 | FTAP Globe | 13.3004 | 123.7597 | 0.78 | Terrestrial Optical Fiber Drop | 2.49 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2339 | 3 | 339 | 2339 | 0931700054 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Muti | 7.2786 | 122.2685 | R | 3566 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTZSG0081 | PTCI/MIDC | 7.2909 | 122.2725 | 1.44 | Terrestrial Optical Fiber Drop | 4.29 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2340 | 3 | 340 | 2340 | 1030500057 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Mambuaya | 8.3264 | 124.5973 | U | 6071 | 1686 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100083 | FTAP BTS | 8.3287 | 124.5967 | 0.26 | Terrestrial Optical Fiber Drop | 1.78 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2341 | 3 | 341 | 2341 | 0304908005 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Malimba | 15.2562 | 120.952 | R | 4045 | 1155 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01439-B07 | PTCI/MIDC | 15.2534 | 120.9527 | 0.32 | Terrestrial Optical Fiber Drop | 0.07 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2342 | 3 | 342 | 2342 | 0205005005 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Busilac | 16.4728 | 121.1156 | R | 3945 | 1038 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01532-B05 | PTCI/MIDC | 16.4761 | 121.1175 | 0.42 | Terrestrial Optical Fiber Drop | 3.74 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2343 | 3 | 343 | 2343 | 0403405040 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 3 | 14.2074 | 121.1622 | U | 4973 | 1506 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4230 | FTAP Smart | 14.2081 | 121.1581 | 0.45 | Terrestrial Optical Fiber Drop | 2.07 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2344 | 3 | 344 | 2344 | 0803723013 | Region VIII (Eastern Visayas) | Leyte | Jaro | Hiagsam | 11.2331 | 124.7616 | R | 2161 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0085 | PTCI/MIDC | 11.2474 | 124.7492 | 2.09 | Terrestrial Optical Fiber Drop | 1.86 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2345 | 3 | 345 | 2345 | 0201501011 | Region II (Cagayan Valley) | Cagayan | Abulug | Lucban | 18.3367 | 121.4318 | R | 3218 | 825 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CAG_0060 | LDIC | 121.4433 | 18.3357 | 1.22 | Terrestrial Optical Fiber Drop | 1.75 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2346 | 3 | 346 | 2346 | 0401014005 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Antipolo Del Norte | 13.9282 | 121.1699 | U | 6258 | 1738 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040469 | FTAP Globe | 13.9258 | 121.1665 | 0.46 | Terrestrial Optical Fiber Drop | 1.82 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2347 | 3 | 347 | 2347 | 0105517017 | Region I (Ilocos Region) | Pangasinan | Calasiao | Nalsian | 16.0211 | 120.3503 | U | 6961 | 1933 | 580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00451 | Edgepoint | 16.0219 | 120.3511 | 0.12 | Terrestrial Optical Fiber Drop | 2.15 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2348 | 3 | 348 | 2348 | 0702204009 | Region VII (Central Visayas) | Cebu | Aloguinsan | Poblacion | 10.2179 | 123.5514 | R | 3811 | 1002 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0003 | PTCI/MIDC | 10.2277 | 123.5519 | 1.09 | Terrestrial Optical Fiber Drop | 8.89 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2349 | 3 | 349 | 2349 | 0603018040 | Region VI (Western Visayas) | Iloilo | Dumangas | Tabucan | 10.8428 | 122.7017 | R | 2389 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060259 | FTAP Globe | 10.8178 | 122.7111 | 1.15 | Terrestrial Optical Fiber Drop | 2.07 | 1.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2350 | 3 | 350 | 2350 | 1206315001 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | Bukay Pait | 6.5636 | 124.7689 | R | 4334 | 1203 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120202 | FTAP BTS | 6.5643 | 124.7666 | 0.26 | Terrestrial Optical Fiber Drop | 17.53 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2351 | 3 | 351 | 2351 | 0405619013 | Region IV-A (CALABARZON) | Quezon | Gumaca | Calumangin | 13.9494 | 122.0317 | R | 1939 | 510 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040420 | FTAP Globe | 13.9547 | 122.0232 | 1.1 | Terrestrial Optical Fiber Drop | 1.26 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2352 | 3 | 352 | 2352 | 0105520005 | Region I (Ilocos Region) | Pangasinan | Infanta | Cato | 15.8387 | 119.915 | R | 4888 | 1357 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00565 | Edgepoint | 15.8345 | 119.914 | 0.48 | Terrestrial Optical Fiber Drop | 1.49 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2353 | 3 | 353 | 2353 | 0601916014 | Region VI (Western Visayas) | Capiz | Sigma | Mianay | 11.4603 | 122.69 | R | 3912 | 1029 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060230 | FTAP Globe | 11.5064 | 122.6843 | 5.17 | Terrestrial Optical Fiber Drop | 4.92 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2354 | 3 | 354 | 2354 | 0105511062 | Region I (Ilocos Region) | Pangasinan | Bayambang | Tamaro | 15.8276 | 120.4574 | R | 1834 | 509 | 153 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0003 | LDIC | 15.8219 | 120.4585 | 0.64 | Terrestrial Optical Fiber Drop | 1.29 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2355 | 3 | 355 | 2355 | 1004311013 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Solana | 8.6254 | 124.7646 | R | 4715 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 2.41 | Terrestrial Optical Fiber Drop | 2.94 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2356 | 3 | 356 | 2356 | 0306910005 | Region III (Central Luzon) | Tarlac | Paniqui | Balaoang | 15.6653 | 120.5122 | R | 4549 | 1166 | 350 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00613 | Edgepoint | 15.6634 | 120.5104 | 0.29 | Terrestrial Optical Fiber Drop | 8.02 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2357 | 3 | 357 | 2357 | 1606811010 | Region XIII (Caraga) | Surigao del Sur | Lianga | Poblacion | 8.632 | 126.0877 | R | 4892 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130030 | FTAP BTS | 8.5393 | 126.1199 | 10.48 | Terrestrial Optical Fiber Drop | 12 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2358 | 3 | 358 | 2358 | 0702210043 | Region VII (Central Visayas) | Cebu | Barili | Tubod | 10.1165 | 123.567 | R | 2543 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070364 | FTAP Globe | 10.1317 | 123.5785 | 2.11 | Terrestrial Optical Fiber Drop | 1.98 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2359 | 3 | 359 | 2359 | 0401013003 | Region IV-A (CALABARZON) | Batangas | Lian | Balibago | 13.9372 | 120.6314 | R | 3749 | 1041 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040450 | FTAP Globe | 13.934 | 120.6326 | 0.38 | Terrestrial Optical Fiber Drop | 2.15 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2360 | 3 | 360 | 2360 | 0304919011 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Sapang Buho | 15.5912 | 121.1248 | R | 4900 | 1400 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00644 | Edgepoint | 15.5896 | 121.119 | 0.65 | Terrestrial Optical Fiber Drop | 3.96 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2361 | 3 | 361 | 2361 | 0306904004 | Region III (Central Luzon) | Tarlac | Capas | Cutcut 1st | 15.3276 | 120.5908 | U | 12578 | 3225 | 968 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00764 | Edgepoint | 15.3185 | 120.5833 | 1.29 | Terrestrial Optical Fiber Drop | 2.16 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2362 | 3 | 362 | 2362 | 0702233015 | Region VII (Central Visayas) | Cebu | Moalboal | Tunga | 9.9539 | 123.4001 | R | 2927 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 0.09 | Terrestrial Optical Fiber Drop | 1.79 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2363 | 3 | 363 | 2363 | 0702251016 | Region VII (Central Visayas) | Cebu | City of Toledo | Don Andres Soriano | 10.3063 | 123.7116 | U | 19376 | 5098 | 1529 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0163 | PTCI/MIDC | 10.3105 | 123.6964 | 1.72 | Terrestrial Optical Fiber Drop | 2.05 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2364 | 3 | 364 | 2364 | 0105511020 | Region I (Ilocos Region) | Pangasinan | Bayambang | Buayaen | 15.7884 | 120.4516 | R | 3137 | 871 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_PNG_0010 | LDIC | 15.7841 | 120.4494 | 0.53 | Terrestrial Optical Fiber Drop | 3.13 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2365 | 3 | 365 | 2365 | 0105538015 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Maticmatic | 15.9871 | 120.4507 | U | 5157 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00484 | Edgepoint | 15.9826 | 120.4591 | 1.03 | Terrestrial Optical Fiber Drop | 1.05 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2366 | 3 | 366 | 2366 | 0401021036 | Region IV-A (CALABARZON) | Batangas | Rosario | Putingkahoy | 13.8292 | 121.329 | R | 3086 | 857 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040553 | FTAP Globe | 13.828 | 121.3363 | 0.8 | Terrestrial Optical Fiber Drop | 1.31 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2367 | 3 | 367 | 2367 | 1600308028 | Region XIII (Caraga) | Agusan del Sur | San Francisco | Karaus | 8.4906 | 125.9761 | U | 3723 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 0.06 | Terrestrial Optical Fiber Drop | 2.02 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2368 | 3 | 368 | 2368 | 0702223021 | Region VII (Central Visayas) | Cebu | Danao City | Looc | 10.5066 | 124.0295 | U | 12347 | 3249 | 975 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070319 | FTAP Globe | 10.5049 | 124.0235 | 0.68 | Terrestrial Optical Fiber Drop | 1.72 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2369 | 3 | 369 | 2369 | 0604512004 | Region VI (Western Visayas) | Negros Occidental | Hinoba-an | Barangay I | 9.5673 | 122.6217 | R | 3526 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060124 | FTAP BTS | 9.6057 | 122.4649 | 0.88 | Terrestrial Optical Fiber Drop | 30.87 | 10.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2370 | 3 | 370 | 2370 | 0704605003 | Region VII (Central Visayas) | Negros Oriental | Basay | Bongalonan | 9.4357 | 122.5983 | R | 4357 | 1146 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070260 | FTAP Globe | 9.4071 | 122.6411 | 5.67 | Terrestrial Optical Fiber Drop | 24.77 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2371 | 3 | 371 | 2371 | 0403411014 | Region IV-A (CALABARZON) | Laguna | Los Baños | Timugan | 14.1781 | 121.2224 | U | 6410 | 1942 | 583 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02109-C08 | PTCI/MIDC | 14.18 | 121.2259 | 0.44 | Terrestrial Optical Fiber Drop | 2.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2372 | 3 | 372 | 2372 | 0201511041 | Region II (Cagayan Valley) | Cagayan | Claveria | Taggat Sur | 18.6028 | 121.0582 | R | 2210 | 566 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F01189-B05 | PTCI/MIDC | 18.6025 | 121.0861 | 2.95 | Terrestrial Optical Fiber Drop | 1.27 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2373 | 3 | 373 | 2373 | 0105523018 | Region I (Ilocos Region) | Pangasinan | Mabini | Tagudin | 16.0831 | 119.954 | R | 4246 | 1179 | 354 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH010140 | FTAP Globe | 16.0709 | 119.9479 | 1.51 | Terrestrial Optical Fiber Drop | 2.95 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2374 | 3 | 374 | 2374 | 1731500058 | MIMAROPA Region | Palawan | City of Puerto Princesa | Tagburos | 9.8206 | 118.7438 | U | 10122 | 2735 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S2229 | FTAP Smart | 9.8095 | 118.7405 | 1.28 | Terrestrial Optical Fiber Drop | 2.28 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2375 | 3 | 375 | 2375 | 1001304021 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Pinamaloy | 7.6646 | 124.9964 | R | 3621 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 0.59 | Terrestrial Optical Fiber Drop | 1.43 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2376 | 3 | 376 | 2376 | 0105546032 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Poblacion | 15.9752 | 120.5655 | U | 7343 | 2039 | 612 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00491 | Edgepoint | 15.9774 | 120.565 | 0.26 | Terrestrial Optical Fiber Drop | 1.94 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2377 | 3 | 377 | 2377 | 0201510016 | Region II (Cagayan Valley) | Cagayan | Camalaniugan | Dugo | 18.2507 | 121.6862 | R | 1847 | 473 | 142 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020014 | FTAP Globe | 18.2526 | 121.6864 | 0.21 | Terrestrial Optical Fiber Drop | 1.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2378 | 3 | 378 | 2378 | 1102507009 | Region XI (Davao Region) | Davao Oriental | Lupon | Corporacion | 6.9104 | 126.0298 | R | 3421 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTDLG0031 | PTCI/MIDC | 6.9029 | 126.0175 | 1.6 | Terrestrial Optical Fiber Drop | 2.51 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2379 | 3 | 379 | 2379 | 0403424035 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Concepcion | 14.0745 | 121.3351 | U | 9089 | 2754 | 826 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 0.95 | Terrestrial Optical Fiber Drop | 1.8 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2380 | 3 | 380 | 2380 | 0702224035 | Region VII (Central Visayas) | Cebu | Dumanjug | Tapon | 10.0621 | 123.4444 | R | 4211 | 1108 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0001 | LDIC | 10.0758 | 123.4523 | 1.75 | Terrestrial Optical Fiber Drop | 1.11 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2381 | 3 | 381 | 2381 | 0500506070 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 56 - Taysan | 13.1166 | 123.7443 | U | 15240 | 3717 | 1115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050188 | FTAP Globe | 13.1173 | 123.7423 | 0.23 | Terrestrial Optical Fiber Drop | 2.49 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2382 | 3 | 382 | 2382 | 0306916088 | Region III (Central Luzon) | Tarlac | City of Tarlac | Tibag | 15.5073 | 120.5707 | U | 18566 | 4760 | 1428 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030368 | FTAP Globe | 15.5098 | 120.5775 | 0.78 | Terrestrial Optical Fiber Drop | 1.31 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2383 | 3 | 383 | 2383 | 1401105010 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Loo | 16.7915 | 120.8309 | R | 5014 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 1.25 | Terrestrial Optical Fiber Drop | 1.68 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2384 | 3 | 384 | 2384 | 0300804025 | Region III (Central Luzon) | Bataan | Dinalupihan | Pagalanggang | 14.8934 | 120.4672 | R | 4402 | 1222 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00896-B07 | PTCI/MIDC | 14.894 | 120.4644 | 0.31 | Terrestrial Optical Fiber Drop | 3.13 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2385 | 3 | 385 | 2385 | 1130700049 | Region XI (Davao Region) | Davao del Sur | City of Davao | Ilang | 7.165 | 125.4711 | U | 27210 | 8002 | 2401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110453 | FTAP Globe | 7.1893 | 125.6441 | 1.54 | Terrestrial Optical Fiber Drop | 2.95 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2386 | 3 | 386 | 2386 | 0702205007 | Region VII (Central Visayas) | Cebu | Argao | Bogo | 9.858 | 123.5714 | R | 4057 | 1067 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CEB_0003 | LDIC | 9.8666 | 123.5804 | 1.37 | Terrestrial Optical Fiber Drop | 4.13 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2387 | 3 | 387 | 2387 | 0730600006 | Region VII (Central Visayas) | Cebu | City of Cebu | Bacayan | 10.3873 | 123.922 | U | 14477 | 4524 | 1357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0063 | PTCI/MIDC | 10.3895 | 123.9263 | 0.53 | Terrestrial Optical Fiber Drop | 1.96 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2388 | 3 | 388 | 2388 | 0702216018 | Region VII (Central Visayas) | Cebu | Catmon | San Jose Pob. | 10.7283 | 124.0127 | R | 3846 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070312 | FTAP Globe | 10.7253 | 124.014 | 0.37 | Terrestrial Optical Fiber Drop | 2.78 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2389 | 3 | 389 | 2389 | 0301408015 | Region III (Central Luzon) | Bulacan | Guiguinto | Tuktukan | 14.827 | 120.8917 | U | 12398 | 3542 | 1063 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02391-B07 | PTCI/MIDC | 14.8254 | 120.8885 | 0.39 | Terrestrial Optical Fiber Drop | 2.04 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2390 | 3 | 390 | 2390 | 0300812005 | Region III (Central Luzon) | Bataan | Samal | Lalawigan | 14.779 | 120.5426 | R | 5001 | 1389 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030063 | FTAP BTS | 14.7777 | 120.5416 | 0.18 | Terrestrial Optical Fiber Drop | 2.65 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2391 | 3 | 391 | 2391 | 0803722013 | Region VIII (Eastern Visayas) | Leyte | Isabel | Marvel | 10.9369 | 124.4322 | U | 4160 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080190 | FTAP BTS | 10.9422 | 124.4325 | 0.59 | Terrestrial Optical Fiber Drop | 1.42 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2392 | 3 | 392 | 2392 | 1102303022 | Region XI (Davao Region) | Davao del Norte | Carmen | Tuganay | 7.3693 | 125.7222 | R | 5049 | 1364 | 409 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110432 | FTAP Globe | 7.3642 | 125.7133 | 1.13 | Terrestrial Optical Fiber Drop | 2.8 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2393 | 3 | 393 | 2393 | 0730600032 | Region VII (Central Visayas) | Cebu | City of Cebu | Inayawan | 10.2718 | 123.856 | U | 32714 | 10223 | 3067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070354 | FTAP Globe | 10.2732 | 123.8587 | 0.33 | Terrestrial Optical Fiber Drop | 1.54 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2394 | 3 | 394 | 2394 | 0305416027 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Jose | 15.04 | 120.6999 | U | 17150 | 4287 | 1286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00001-B07 | PTCI/MIDC | 15.0404 | 120.701 | 0.13 | Terrestrial Optical Fiber Drop | 1.93 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2395 | 3 | 395 | 2395 | 1206317013 | Region XII (SOCCSKSARGEN) | South Cotabato | Tupi | Poblacion | 6.3415 | 124.9417 | U | 15943 | 4428 | 1328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120121 | FTAP BTS | 6.3394 | 124.9432 | 0.28 | Terrestrial Optical Fiber Drop | 1.45 | 6.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2396 | 3 | 396 | 2396 | 0103317018 | Region I (Ilocos Region) | La Union | Santo Tomas | Patac | 16.2748 | 120.3935 | U | 3416 | 923 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-LUN-00375 | Edgepoint | 16.2755 | 120.3824 | 1.19 | Terrestrial Optical Fiber Drop | 1.99 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2397 | 3 | 397 | 2397 | 1204704015 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Lanao | 7.0255 | 125.0814 | U | 7862 | 2068 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNCG0017 | PTCI/MIDC | 7.0271 | 125.085 | 0.43 | Terrestrial Optical Fiber Drop | 1.95 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2398 | 3 | 398 | 2398 | 0105526020 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Malabago | 16.0551 | 120.388 | U | 5172 | 1436 | 431 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00428 | Edgepoint | 16.0514 | 120.3822 | 0.75 | Terrestrial Optical Fiber Drop | 2.08 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2399 | 3 | 399 | 2399 | 0301417015 | Region III (Central Luzon) | Bulacan | Plaridel | Poblacion | 14.8843 | 120.8594 | U | 4054 | 1158 | 347 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030563 | FTAP Globe | 14.8814 | 120.8665 | 0.82 | Terrestrial Optical Fiber Drop | 2.21 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2400 | 3 | 400 | 2400 | 0403405058 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Turbina | 14.1832 | 121.1343 | U | 6871 | 2082 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.74 | Terrestrial Optical Fiber Drop | 2.01 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2401 | 3 | 401 | 2401 | 0401031016 | Region IV-A (CALABARZON) | Batangas | City of Tanauan | Darasa | 14.0692 | 121.1533 | U | 24699 | 6860 | 2058 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 4114 | FTAP Smart | 14.0627 | 121.1529 | 0.72 | Terrestrial Optical Fiber Drop | 1.6 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2402 | 3 | 402 | 2402 | 0401014071 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Tambo | 13.9407 | 121.1469 | U | 12945 | 3595 | 1079 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02802-C08 | PTCI/MIDC | 13.9457 | 121.149 | 0.6 | Terrestrial Optical Fiber Drop | 2.15 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2403 | 3 | 403 | 2403 | 0201529044 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Leonarda | 17.6424 | 121.7399 | U | 3353 | 859 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01134-B06 | PTCI/MIDC | 17.6428 | 121.7405 | 0.07 | Terrestrial Optical Fiber Drop | 1.25 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2404 | 3 | 404 | 2404 | 0604512001 | Region VI (Western Visayas) | Negros Occidental | Hinoba-an | Alim | 9.5207 | 122.5407 | R | 5101 | 1378 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0048 | PTCI/MIDC | 9.5664 | 122.4924 | 0.63 | Terrestrial Optical Fiber Drop | 29.49 | 0.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2405 | 3 | 405 | 2405 | 0401014031 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Mataas Na Lupa | 13.9421 | 121.1575 | U | 4644 | 1290 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040444 | FTAP Globe | 13.9393 | 121.1666 | 0.47 | Terrestrial Optical Fiber Drop | 0.99 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2406 | 3 | 406 | 2406 | 0702222027 | Region VII (Central Visayas) | Cebu | Dalaguete | Obong | 9.7399 | 123.5109 | R | 3285 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 1.29 | Terrestrial Optical Fiber Drop | 3.36 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2407 | 3 | 407 | 2407 | 0306916056 | Region III (Central Luzon) | Tarlac | City of Tarlac | Paraiso | 15.443 | 120.5987 | R | 3583 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-03013 | Edgepoint | 120.5986 | 15.4446 | 0.18 | Terrestrial Optical Fiber Drop | 2.61 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2408 | 3 | 408 | 2408 | 0306906018 | Region III (Central Luzon) | Tarlac | Gerona | Magaspac | 15.6154 | 120.5979 | R | 5109 | 1310 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00633 | Edgepoint | 15.6103 | 120.5971 | 0.57 | Terrestrial Optical Fiber Drop | 2.07 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2409 | 3 | 409 | 2409 | 0307114019 | Region III (Central Luzon) | Zambales | Subic | Pamatawan | 14.9241 | 120.2192 | R | 5163 | 1358 | 407 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ZMB-01037 | Edgepoint | 14.9175 | 120.2302 | 1.39 | Terrestrial Optical Fiber Drop | 2.07 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2410 | 3 | 410 | 2410 | 1108203002 | Region XI (Davao Region) | Davao de Oro | Mabini | Cadunan | 7.3309 | 125.8579 | U | 4653 | 1257 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH110440 | FTAP Globe | 7.3117 | 125.8547 | 2.17 | Terrestrial Optical Fiber Drop | 2.47 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2411 | 3 | 411 | 2411 | 1001314017 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Tankulan | 8.3684 | 124.8643 | U | 10019 | 2636 | 791 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 0.44 | Terrestrial Optical Fiber Drop | 2.11 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2412 | 3 | 412 | 2412 | 0205702008 | Region II (Cagayan Valley) | Quirino | Cabarroguis | Mangandingay | 16.5162 | 121.5475 | R | 3342 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_QUI_0004 | LDIC | 121.5504 | 16.5144 | 0.37 | Terrestrial Optical Fiber Drop | 2.1 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2413 | 3 | 413 | 2413 | 0301423014 | Region III (Central Luzon) | Bulacan | Santa Maria | Manggahan | 14.8528 | 120.9575 | U | 2905 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01119 | Edgepoint | 14.8516 | 120.9571 | 0.13 | Terrestrial Optical Fiber Drop | 1.22 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2414 | 3 | 414 | 2414 | 1003523012 | Region X (Northern Mindanao) | Lanao del Norte | Pantar | Kalanganan East | 8.0828 | 124.2512 | R | 3745 | 891 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100189 | FTAP Globe | 8.0656 | 124.2637 | 2.35 | Terrestrial Optical Fiber Drop | 8.49 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2415 | 3 | 415 | 2415 | 0401005035 | Region IV-A (CALABARZON) | Batangas | Batangas City | Kumintang Ilaya | 13.7744 | 121.0656 | U | 11223 | 3117 | 935 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | B74 | FTAP Smart | 13.7784 | 121.0676 | 0.49 | Terrestrial Optical Fiber Drop | 1.64 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2416 | 3 | 416 | 2416 | 0431200022 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Talim | 13.9157 | 121.5777 | R | 3834 | 958 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02141-C08 | PTCI/MIDC | 13.9298 | 121.5959 | 2.51 | Terrestrial Optical Fiber Drop | 3.8 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2417 | 3 | 417 | 2417 | 0307103016 | Region III (Central Luzon) | Zambales | Candelaria | Sinabacan | 15.6566 | 119.9351 | R | 4096 | 1077 | 323 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01832-B07 | PTCI/MIDC | 15.6522 | 119.9312 | 0.64 | Terrestrial Optical Fiber Drop | 3.68 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2418 | 3 | 418 | 2418 | 0403405055 | Region IV-A (CALABARZON) | Laguna | City of Calamba | San Juan | 14.2171 | 121.1758 | R | 5290 | 1603 | 481 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040241 | FTAP Globe | 14.2171 | 121.1746 | 0.13 | Terrestrial Optical Fiber Drop | 3.88 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2419 | 3 | 419 | 2419 | 0405645035 | Region IV-A (CALABARZON) | Quezon | Sariaya | Barangay 4 | 13.9625 | 121.5272 | U | 3165 | 832 | 250 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | Q55 | FTAP Smart | 13.9641 | 121.529 | 0.27 | Terrestrial Optical Fiber Drop | 1.06 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2420 | 3 | 420 | 2420 | 0702251022 | Region VII (Central Visayas) | Cebu | City of Toledo | Luray II | 10.381 | 123.644 | U | 4847 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0172 | PTCI/MIDC | 10.3817 | 123.6436 | 0.09 | Terrestrial Optical Fiber Drop | 2.48 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2421 | 3 | 421 | 2421 | 1004303008 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Mantangale | 9.0046 | 124.8574 | R | 1882 | 482 | 145 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 0.45 | Terrestrial Optical Fiber Drop | 1.62 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2422 | 3 | 422 | 2422 | 0304925004 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Malapit | 15.3043 | 120.9212 | U | 10459 | 2988 | 896 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0013 | LDIC | 15.3017 | 120.9258 | 0.57 | Terrestrial Optical Fiber Drop | 0.07 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2423 | 3 | 423 | 2423 | 1430300101 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Santo Rosario | 16.4002 | 120.5869 | R | 1920 | 505 | 152 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SC_BGT_0053 | LDIC | 16.402 | 120.584 | 0.38 | Terrestrial Optical Fiber Drop | 1.09 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2424 | 3 | 424 | 2424 | 1004320002 | Region X (Northern Mindanao) | Misamis Oriental | Naawan | Linangkayan | 8.4115 | 124.2918 | R | 3118 | 799 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0102 | PTCI/MIDC | 8.4093 | 124.2918 | 0.25 | Terrestrial Optical Fiber Drop | 1.36 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2425 | 3 | 425 | 2425 | 0931700066 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Quiniput | 7.1795 | 122.1725 | R | 4186 | 1162 | 349 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTZSG0150 | PTCI/MIDC | 7.1844 | 122.2194 | 0.14 | Terrestrial Optical Fiber Drop | 11.87 | 5.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2426 | 3 | 426 | 2426 | 1108207003 | Region XI (Davao Region) | Davao de Oro | Monkayo | Banlag | 7.8263 | 126.0341 | R | 4887 | 1320 | 396 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDOG0097 | PTCI/MIDC | 7.8249 | 126.0332 | 0.18 | Terrestrial Optical Fiber Drop | 2.43 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2427 | 3 | 427 | 2427 | 0803721021 | Region VIII (Eastern Visayas) | Leyte | Inopacan | Tinago | 10.4967 | 124.7376 | R | 3158 | 831 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080217 | FTAP BTS | 10.4266 | 124.7271 | 7.88 | Terrestrial Optical Fiber Drop | 21.5 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2428 | 3 | 428 | 2428 | 0501721009 | Region V (Bicol Region) | Camarines Sur | Milaor | Flordeliz | 13.5899 | 123.1694 | R | 1523 | 362 | 109 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050098 | FTAP Globe | 13.5913 | 123.1714 | 0.27 | Terrestrial Optical Fiber Drop | 1.05 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2429 | 3 | 429 | 2429 | 0604530011 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Mabini | 10.4939 | 122.8271 | R | 4270 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0081 | PTCI/MIDC | 10.5207 | 122.8433 | 3.46 | Terrestrial Optical Fiber Drop | 3.12 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2430 | 3 | 430 | 2430 | 1004311002 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Bobontugan | 8.6571 | 124.7464 | U | 7072 | 1813 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0055 | PTCI/MIDC | 8.6959 | 124.7474 | 4.32 | Terrestrial Optical Fiber Drop | 1.19 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2431 | 3 | 431 | 2431 | 1130700068 | Region XI (Davao Region) | Davao del Sur | City of Davao | Manambulan | 7.1034 | 125.4523 | R | 3635 | 1069 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110472 | FTAP Globe | 7.12 | 125.4504 | 1.86 | Terrestrial Optical Fiber Drop | 6.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2432 | 3 | 432 | 2432 | 0506216019 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Macabog | 12.9844 | 123.9912 | R | 4479 | 1119 | 336 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_SOR_0001 | LDIC | 12.9853 | 123.9959 | 0.53 | Terrestrial Optical Fiber Drop | 2.08 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2433 | 3 | 433 | 2433 | 0304903010 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Bantug Bulalo | 15.4899 | 120.9758 | R | 2190 | 625 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00696 | Edgepoint | 15.4906 | 120.9774 | 0.19 | Terrestrial Optical Fiber Drop | 1.82 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2434 | 3 | 434 | 2434 | 0405610033 | Region IV-A (CALABARZON) | Quezon | Catanauan | San Isidro | 13.6311 | 122.2422 | R | 3291 | 866 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040613 | FTAP Globe | 13.6328 | 122.2423 | 0.19 | Terrestrial Optical Fiber Drop | 1.14 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2435 | 3 | 435 | 2435 | 1004310006 | Region X (Northern Mindanao) | Misamis Oriental | Initao | Jampason | 8.5148 | 124.3097 | R | 2341 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0052 | PTCI/MIDC | 8.5168 | 124.3105 | 0.25 | Terrestrial Optical Fiber Drop | 1.57 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2436 | 3 | 436 | 2436 | 1004308065 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | San Juan | 8.8273 | 125.0869 | R | 5055 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100112 | FTAP Globe | 8.8252 | 125.0887 | 0.31 | Terrestrial Optical Fiber Drop | 2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2437 | 3 | 437 | 2437 | 0300804002 | Region III (Central Luzon) | Bataan | Dinalupihan | Bangal | 14.8453 | 120.3396 | U | 5278 | 1466 | 440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03327-B07 | PTCI/MIDC | 14.8451 | 120.3401 | 0.06 | Terrestrial Optical Fiber Drop | 1.77 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2438 | 3 | 438 | 2438 | 0601914020 | Region VI (Western Visayas) | Capiz | City of Roxas | Bolo | 11.5388 | 122.7573 | U | 8301 | 2184 | 655 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060228 | FTAP Globe | 11.5361 | 122.7582 | 0.31 | Terrestrial Optical Fiber Drop | 2.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2439 | 3 | 439 | 2439 | 1108208011 | Region XI (Davao Region) | Davao de Oro | Montevista | Linoan | 7.676 | 125.9855 | R | 4272 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0026 | PTCI/MIDC | 7.6833 | 125.9877 | 0.84 | Terrestrial Optical Fiber Drop | 18.54 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2440 | 3 | 440 | 2440 | 0306916074 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Sebastian | 15.4746 | 120.598 | U | 4413 | 1131 | 339 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00713 | Edgepoint | 15.4779 | 120.6016 | 0.53 | Terrestrial Optical Fiber Drop | 1.66 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2441 | 3 | 441 | 2441 | 0300810024 | Region III (Central Luzon) | Bataan | Orion | Santo Domingo | 14.6338 | 120.5729 | R | 4590 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 1.46 | Terrestrial Optical Fiber Drop | 2.15 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2442 | 3 | 442 | 2442 | 0201529002 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Atulayan Norte | 17.6351 | 121.7203 | R | 4335 | 1111 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1008 | FTAP Smart | 17.6126 | 121.7294 | 0.65 | Terrestrial Optical Fiber Drop | 3.37 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2443 | 3 | 443 | 2443 | 0603031006 | Region VI (Western Visayas) | Iloilo | Mina | Cabalabaguan | 10.936 | 122.582 | R | 2262 | 595 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 0.31 | Terrestrial Optical Fiber Drop | 2.47 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2444 | 3 | 444 | 2444 | 0500506056 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 62 - Homapon | 13.0912 | 123.7393 | U | 5336 | 1301 | 390 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02493-C10 | PTCI/MIDC | 13.0832 | 123.7423 | 0.95 | Terrestrial Optical Fiber Drop | 1.59 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2445 | 3 | 445 | 2445 | 0203135015 | Region II (Cagayan Valley) | Isabela | City of Santiago | Divisoria | 16.6974 | 121.6083 | R | 4366 | 1148 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0020 | LDIC | 121.6084 | 16.6944 | 0.34 | Terrestrial Optical Fiber Drop | 4.78 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2446 | 3 | 446 | 2446 | 0500517039 | Region V (Bicol Region) | Albay | City of Tabaco | San Lorenzo | 13.3365 | 123.7362 | U | 8144 | 1986 | 596 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050134 | FTAP Globe | 13.3413 | 123.7311 | 0.77 | Terrestrial Optical Fiber Drop | 1.89 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2447 | 3 | 447 | 2447 | 0403405035 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Palo-Alto | 14.1843 | 121.1073 | U | 20689 | 6269 | 1881 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02049-C08 | PTCI/MIDC | 14.1853 | 121.1088 | 0.2 | Terrestrial Optical Fiber Drop | 1.12 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2448 | 3 | 448 | 2448 | 1001317026 | Region X (Northern Mindanao) | Bukidnon | Quezon | Palacapao | 7.6103 | 125.1308 | R | 2921 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBKG0036 | PTCI/MIDC | 7.6116 | 125.1193 | 1.28 | Terrestrial Optical Fiber Drop | 1.97 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2449 | 3 | 449 | 2449 | 0301407027 | Region III (Central Luzon) | Bulacan | Calumpit | Santo Niño | 14.9058 | 120.7808 | U | 2659 | 759 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01049 | Edgepoint | 14.9045 | 120.7807 | 0.15 | Terrestrial Optical Fiber Drop | 1.4 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2450 | 3 | 450 | 2450 | 1004315002 | Region X (Northern Mindanao) | Misamis Oriental | Libertad | Gimaylan | 8.5488 | 124.3356 | R | 2386 | 611 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100128 | FTAP Globe | 8.5377 | 124.3211 | 2.01 | Terrestrial Optical Fiber Drop | 2.42 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2451 | 3 | 451 | 2451 | 0601912004 | Region VI (Western Visayas) | Capiz | Pontevedra | Bailan | 11.458 | 122.8271 | R | 2921 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCZG0029 | PTCI/MIDC | 11.4484 | 122.8313 | 1.16 | Terrestrial Optical Fiber Drop | 2.34 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2452 | 3 | 452 | 2452 | 0306907020 | Region III (Central Luzon) | Tarlac | La Paz | San Roque | 15.4431 | 120.7334 | U | 8464 | 2170 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00728 | Edgepoint | 15.4413 | 120.7272 | 0.7 | Terrestrial Optical Fiber Drop | 1.78 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2453 | 3 | 453 | 2453 | 0304923035 | Region III (Central Luzon) | Nueva Ecija | Rizal | San Gregorio | 15.7051 | 121.115 | R | 1875 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-03183 | Edgepoint | 15.7076 | 121.106 | 1 | Terrestrial Optical Fiber Drop | 1.34 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2454 | 3 | 454 | 2454 | 0501706020 | Region V (Bicol Region) | Camarines Sur | Bula | Pawili | 13.5223 | 123.2961 | R | 2990 | 711 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03115-C10 | PTCI/MIDC | 13.519 | 123.297 | 0.39 | Terrestrial Optical Fiber Drop | 1.01 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2455 | 3 | 455 | 2455 | 0501732015 | Region V (Bicol Region) | Camarines Sur | San Fernando | Pamukid | 13.5574 | 123.1236 | U | 6125 | 1458 | 437 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050104 | FTAP Globe | 13.5612 | 123.1229 | 0.42 | Terrestrial Optical Fiber Drop | 1.81 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2456 | 3 | 456 | 2456 | 0304909019 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Poblacion | 15.6038 | 121.0509 | R | 4214 | 1204 | 361 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01422-B07 | PTCI/MIDC | 15.6038 | 121.0489 | 0.22 | Terrestrial Optical Fiber Drop | 1.25 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2457 | 3 | 457 | 2457 | 0501736019 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Francisco | 13.6406 | 123.4986 | R | 1549 | 368 | 110 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 0.5 | Terrestrial Optical Fiber Drop | 1.15 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2458 | 3 | 458 | 2458 | 0403405037 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Parian | 14.2142 | 121.1515 | U | 28016 | 8489 | 2547 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03427-A04 | PTCI/MIDC | 14.2116 | 121.1438 | 0.88 | Terrestrial Optical Fiber Drop | 1.97 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2459 | 3 | 459 | 2459 | 0103301020 | Region I (Ilocos Region) | La Union | Agoo | San Jose Sur | 16.3122 | 120.3706 | R | 1824 | 492 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00361 | Edgepoint | 16.3204 | 120.3699 | 0.91 | Terrestrial Optical Fiber Drop | 1.28 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2460 | 3 | 460 | 2460 | 1401110012 | Cordillera Administrative Region (CAR) | Benguet | La Trinidad | Poblacion | 16.4584 | 120.5796 | U | 13029 | 3722 | 1117 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBEG0043 | PTCI/MIDC | 16.4614 | 120.5761 | 0.51 | Terrestrial Optical Fiber Drop | 1.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2461 | 3 | 461 | 2461 | 0704606003 | Region VII (Central Visayas) | Negros Oriental | City of Bayawan | Banga | 9.3705 | 122.7952 | U | 7880 | 2073 | 622 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0010 | PTCI/MIDC | 9.3759 | 122.7973 | 0.64 | Terrestrial Optical Fiber Drop | 2.01 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2462 | 3 | 462 | 2462 | 0500503008 | Region V (Bicol Region) | Albay | Daraga | Bascaran | 13.1044 | 123.6976 | R | 4825 | 1176 | 353 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050190 | FTAP Globe | 13.1008 | 123.6996 | 0.45 | Terrestrial Optical Fiber Drop | 4.12 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2463 | 3 | 463 | 2463 | 0630200056 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Sum-ag | 10.6019 | 122.9199 | U | 21273 | 5909 | 1773 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0002 | PTCI/MIDC | 10.6013 | 122.9168 | 0.39 | Terrestrial Optical Fiber Drop | 1.82 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2464 | 3 | 464 | 2464 | 0704605002 | Region VII (Central Visayas) | Negros Oriental | Basay | Bal-os | 9.428 | 122.6255 | R | 4344 | 1143 | 343 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070260 | FTAP Globe | 9.4071 | 122.6411 | 2.89 | Terrestrial Optical Fiber Drop | 21.68 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2465 | 3 | 465 | 2465 | 0405809002 | Region IV-A (CALABARZON) | Rizal | Morong | Can-Cal-Lan | 14.5271 | 121.2499 | R | 4707 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01852 | Edgepoint | 14.5282 | 121.2492 | 0.13 | Terrestrial Optical Fiber Drop | 1.29 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2466 | 3 | 466 | 2466 | 0304928003 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Liwayway | 15.4435 | 121.0651 | R | 4402 | 1257 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | N1208 | FTAP Smart | 15.446 | 121.0747 | 1.07 | Terrestrial Optical Fiber Drop | 0.07 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2467 | 3 | 467 | 2467 | 1004311001 | Region X (Northern Mindanao) | Misamis Oriental | Jasaan | Aplaya | 8.6054 | 124.7656 | U | 6221 | 1595 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0053 | PTCI/MIDC | 8.6037 | 124.7648 | 0.21 | Terrestrial Optical Fiber Drop | 1.38 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2468 | 3 | 468 | 2468 | 0702251033 | Region VII (Central Visayas) | Cebu | City of Toledo | Sangi | 10.3868 | 123.6528 | U | 5497 | 1446 | 434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 1.12 | Terrestrial Optical Fiber Drop | 1.48 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2469 | 3 | 469 | 2469 | 0307114004 | Region III (Central Luzon) | Zambales | Subic | Baraca-Camachile | 14.8788 | 120.2336 | U | 3533 | 929 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01076 | Edgepoint | 14.8785 | 120.2313 | 0.25 | Terrestrial Optical Fiber Drop | 1.22 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2470 | 3 | 470 | 2470 | 0506209018 | Region V (Bicol Region) | Sorsogon | Irosin | Monbon | 12.7289 | 124.0169 | R | 4378 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03124-C10 | PTCI/MIDC | 12.733 | 124.0141 | 0.55 | Terrestrial Optical Fiber Drop | 3.58 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2471 | 3 | 471 | 2471 | 0105522033 | Region I (Ilocos Region) | Pangasinan | Lingayen | Tonton | 16.0272 | 120.25 | R | 4826 | 1340 | 402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00442 | Edgepoint | 16.0278 | 120.2507 | 0.1 | Terrestrial Optical Fiber Drop | 1.91 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2472 | 3 | 472 | 2472 | 0803738056 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Ipil | 10.9761 | 124.6345 | U | 9712 | 2555 | 767 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0094 | PTCI/MIDC | 10.9899 | 124.6235 | 1.95 | Terrestrial Optical Fiber Drop | 2.3 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2473 | 3 | 473 | 2473 | 0201523002 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Casambalangan | 18.3764 | 122.1261 | R | 4651 | 1192 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01161-B06 | PTCI/MIDC | 18.375 | 122.1235 | 0.31 | Terrestrial Optical Fiber Drop | 3.33 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2474 | 3 | 474 | 2474 | 0702234018 | Region VII (Central Visayas) | Cebu | City of Naga | Naalad | 10.2094 | 123.7445 | R | 3626 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 1.39 | Terrestrial Optical Fiber Drop | 4.07 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2475 | 3 | 475 | 2475 | 1206315008 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | New Iloilo | 6.5462 | 124.789 | R | 4972 | 1381 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120101 | FTAP BTS | 6.5372 | 124.7964 | 1.28 | Terrestrial Optical Fiber Drop | 20.43 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2476 | 3 | 476 | 2476 | 0803726014 | Region VIII (Eastern Visayas) | Leyte | Kananga | Natubgan | 11.1975 | 124.5654 | R | 3126 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0032 | PTCI/MIDC | 11.1784 | 124.5616 | 2.16 | Terrestrial Optical Fiber Drop | 1.45 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2477 | 3 | 477 | 2477 | 0401002011 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Muzon Primero | 13.8482 | 120.9914 | R | 2599 | 721 | 216 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040546 | FTAP Globe | 13.8434 | 120.99 | 0.56 | Terrestrial Optical Fiber Drop | 1.34 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2478 | 3 | 478 | 2478 | 1001304029 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Sinangguyan | 7.7072 | 125.0037 | R | 4953 | 1303 | 391 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100214 | FTAP Globe | 7.7079 | 125.02 | 1.8 | Terrestrial Optical Fiber Drop | 3.41 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2479 | 3 | 479 | 2479 | 0405811013 | Region IV-A (CALABARZON) | Rizal | San Mateo | Gulod Malaya | 14.6735 | 121.1333 | U | 12408 | 3446 | 1034 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0045 | PTCI/MIDC | 14.675 | 121.1345 | 0.21 | Terrestrial Optical Fiber Drop | 2.37 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2480 | 3 | 480 | 2480 | 0603034028 | Region VI (Western Visayas) | Iloilo | Oton | San Antonio | 10.693 | 122.4915 | R | 2471 | 650 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060151 | FTAP BTS | 10.6858 | 122.4903 | 0.81 | Terrestrial Optical Fiber Drop | 1.23 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2481 | 3 | 481 | 2481 | 0402103007 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Dulong Bayan | 14.4497 | 120.9355 | U | 7100 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0001 | LDIC | 14.4497 | 120.9334 | 0.22 | Terrestrial Optical Fiber Drop | 1.45 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2482 | 3 | 482 | 2482 | 0931700103 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Zamboanga | Victoria | 7.049 | 122.1939 | R | 3537 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTZSG0135 | PTCI/MIDC | 7.0578 | 122.1946 | 0.99 | Terrestrial Optical Fiber Drop | 20.33 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2483 | 3 | 483 | 2483 | 0201522015 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Namuac | 18.6058 | 121.1738 | R | 3793 | 972 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CAG_0066 | LDIC | 121.1798 | 18.6012 | 0.82 | Terrestrial Optical Fiber Drop | 8.44 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2484 | 3 | 484 | 2484 | 1102315028 | Region XI (Davao Region) | Davao del Norte | City of Panabo | Salvacion | 7.3178 | 125.6887 | U | 10928 | 2953 | 886 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDNG0120 | PTCI/MIDC | 7.3129 | 125.6909 | 0.6 | Terrestrial Optical Fiber Drop | 2.12 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2485 | 3 | 485 | 2485 | 1600210003 | Region XIII (Caraga) | Agusan del Norte | Santiago | Jagupit | 9.2424 | 125.5579 | R | 3315 | 808 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ADN_0005 | LDIC | 9.2418 | 125.5594 | 0.18 | Terrestrial Optical Fiber Drop | 2.7 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2486 | 3 | 486 | 2486 | 0205004005 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Almaguer North | 16.363 | 121.0966 | U | 3339 | 878 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01534-B05 | PTCI/MIDC | 16.3595 | 121.1042 | 0.9 | Terrestrial Optical Fiber Drop | 1.36 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2487 | 3 | 487 | 2487 | 0403406004 | Region IV-A (CALABARZON) | Laguna | Calauan | Hanggan | 14.1782 | 121.3023 | R | 3413 | 1034 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040277 | FTAP Globe | 14.1723 | 121.3161 | 1.63 | Terrestrial Optical Fiber Drop | 2.37 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2488 | 3 | 488 | 2488 | 0403419016 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | San Isidro | 14.2798 | 121.4581 | R | 3022 | 915 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02334-C08 | PTCI/MIDC | 14.2753 | 121.4548 | 0.62 | Terrestrial Optical Fiber Drop | 1.09 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2489 | 3 | 489 | 2489 | 0604532006 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pandanon | 10.5765 | 123.178 | R | 2908 | 785 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOG0126 | PTCI/MIDC | 10.6316 | 123.1015 | 10.37 | Terrestrial Optical Fiber Drop | 2.85 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2490 | 3 | 490 | 2490 | 0203101023 | Region II (Cagayan Valley) | Isabela | Alicia | San Antonio | 16.7738 | 121.6997 | R | 2161 | 568 | 170 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-ISA-00262 | Edgepoint | 16.7814 | 121.6946 | 1.01 | Terrestrial Optical Fiber Drop | 1.39 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2491 | 3 | 491 | 2491 | 0403426008 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Labuin | 14.2683 | 121.4001 | R | 5029 | 1523 | 457 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S4291 | FTAP Smart | 14.2707 | 121.4145 | 0.26 | Terrestrial Optical Fiber Drop | 1.85 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2492 | 3 | 492 | 2492 | 0702216015 | Region VII (Central Visayas) | Cebu | Catmon | Panalipan | 10.6494 | 124.0239 | R | 4169 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070060 | FTAP BTS | 10.6562 | 124.0212 | 0.81 | Terrestrial Optical Fiber Drop | 5.08 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2493 | 3 | 493 | 2493 | 0501606037 | Region V (Bicol Region) | Camarines Norte | Labo | Malatap | 14.1642 | 122.6174 | R | 2597 | 649 | 195 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050014 | FTAP Globe | 14.1778 | 122.6227 | 1.62 | Terrestrial Optical Fiber Drop | 1.69 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2494 | 3 | 494 | 2494 | 1001312065 | Region X (Northern Mindanao) | Bukidnon | City of Malaybalay | Sumpong | 8.1641 | 125.1194 | U | 10342 | 2721 | 816 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100123 (FTAP_GLO_PH100123) | FTAP Globe | 8.5573 | 124.3551 | 1.1 | Terrestrial Optical Fiber Drop | 2.03 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2495 | 3 | 495 | 2495 | 0604520009 | Region VI (Western Visayas) | Negros Occidental | Murcia | Blumentritt | 10.6203 | 123.0645 | U | 12890 | 3483 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060352 | FTAP Globe | 10.6249 | 123.022 | 0.92 | Terrestrial Optical Fiber Drop | 2.88 | 2.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2496 | 3 | 496 | 2496 | 0305407031 | Region III (Central Luzon) | Pampanga | Guagua | Santo Cristo | 14.9722 | 120.6182 | U | 3997 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 1.55 | Terrestrial Optical Fiber Drop | 1.21 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2497 | 3 | 497 | 2497 | 0105530001 | Region I (Ilocos Region) | Pangasinan | Pozorrubio | Alipangpang | 16.1062 | 120.5631 | U | 6355 | 1765 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00408 | Edgepoint | 16.1087 | 120.5657 | 0.39 | Terrestrial Optical Fiber Drop | 2.43 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2498 | 3 | 498 | 2498 | 0702241015 | Region VII (Central Visayas) | Cebu | San Fernando | Pitalo | 10.1757 | 123.7217 | U | 8064 | 2122 | 637 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0146 | PTCI/MIDC | 10.1738 | 123.7182 | 0.44 | Terrestrial Optical Fiber Drop | 2.11 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2499 | 3 | 499 | 2499 | 0402119035 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | Silang Junction North | 14.1307 | 120.9548 | U | 2614 | 768 | 230 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02196-C08 | PTCI/MIDC | 14.1417 | 120.974 | 0.59 | Terrestrial Optical Fiber Drop | 2.76 | 1.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2500 | 3 | 500 | 2500 | 0304903094 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Sumacab Este | 15.4446 | 120.9443 | U | 4923 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NUE_0004 | LDIC | 15.4419 | 120.9391 | 0.64 | Terrestrial Optical Fiber Drop | 2.04 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2501 | 3 | 501 | 2501 | 0431200017 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Gulang-gulang | 13.9548 | 121.6119 | U | 28548 | 7137 | 2141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02135-C08 | PTCI/MIDC | 13.9601 | 121.6134 | 0.61 | Terrestrial Optical Fiber Drop | 2.4 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2502 | 3 | 502 | 2502 | 0501715033 | Region V (Bicol Region) | Camarines Sur | Goa | Tagongtong | 13.6949 | 123.4752 | R | 2716 | 646 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050064 | FTAP Globe | 13.6982 | 123.4789 | 0.54 | Terrestrial Optical Fiber Drop | 1.41 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2503 | 3 | 503 | 2503 | 0304904015 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Gregorio | 15.2551 | 120.86 | R | 2344 | 669 | 201 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.64 | Terrestrial Optical Fiber Drop | 1.11 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2504 | 3 | 504 | 2504 | 0301403027 | Region III (Central Luzon) | Bulacan | Baliuag | Tibag | 14.9555 | 120.9039 | U | 3114 | 889 | 267 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030523 | FTAP Globe | 14.9547 | 120.9046 | 0.11 | Terrestrial Optical Fiber Drop | 1.55 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2505 | 3 | 505 | 2505 | 0103302014 | Region I (Ilocos Region) | La Union | Aringay | San Benito Norte | 16.4127 | 120.3528 | R | 3012 | 814 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_LU_0013 | LDIC | 16.4152 | 120.3518 | 0.3 | Terrestrial Optical Fiber Drop | 1.97 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2506 | 3 | 506 | 2506 | 0307113004 | Region III (Central Luzon) | Zambales | Santa Cruz | Bayto | 15.7275 | 119.9097 | R | 4316 | 1135 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00590 | Edgepoint | 15.7248 | 119.9066 | 0.45 | Terrestrial Optical Fiber Drop | 4.48 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2507 | 3 | 507 | 2507 | 0402119018 | Region IV-A (CALABARZON) | Cavite | City of Tagaytay | San Jose | 14.123 | 120.968 | U | 7133 | 2097 | 629 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02153-C08 | PTCI/MIDC | 14.1292 | 120.9715 | 0.79 | Terrestrial Optical Fiber Drop | 1.35 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2508 | 3 | 508 | 2508 | 0305403017 | Region III (Central Luzon) | Pampanga | Arayat | Plazang Luma | 15.151 | 120.7672 | U | 5689 | 1422 | 427 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02381 | Edgepoint | 15.1479 | 120.7701 | 0.47 | Terrestrial Optical Fiber Drop | 1.09 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2509 | 3 | 509 | 2509 | 1102319005 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Canocotan | 7.4068 | 125.7784 | U | 9916 | 2680 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0019 | PTCI/MIDC | 7.4089 | 125.7784 | 0.23 | Terrestrial Optical Fiber Drop | 2.24 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2510 | 3 | 510 | 2510 | 0304932027 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Young | 15.4451 | 120.7812 | R | 4233 | 1209 | 363 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01419-B07 | PTCI/MIDC | 15.4394 | 120.779 | 0.68 | Terrestrial Optical Fiber Drop | 1.2 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2511 | 3 | 511 | 2511 | 0600401006 | Region VI (Western Visayas) | Aklan | Altavas | Linayasan | 11.5402 | 122.4746 | R | 2068 | 530 | 159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.44 | Terrestrial Optical Fiber Drop | 1.48 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2512 | 3 | 512 | 2512 | 0306916047 | Region III (Central Luzon) | Tarlac | City of Tarlac | Maligaya | 15.4406 | 120.5992 | U | 4331 | 1110 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-03013 | Edgepoint | 120.5986 | 15.4446 | 0.45 | Terrestrial Optical Fiber Drop | 2.35 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2513 | 3 | 513 | 2513 | 1004326012 | Region X (Northern Mindanao) | Misamis Oriental | Villanueva | Poblacion 2 | 8.5843 | 124.7717 | R | 2792 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0080 | PTCI/MIDC | 8.5798 | 124.7768 | 0.76 | Terrestrial Optical Fiber Drop | 1.18 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2514 | 3 | 514 | 2514 | 0803739017 | Region VIII (Eastern Visayas) | Leyte | Palo | Libertad | 11.1736 | 124.9574 | R | 4363 | 1148 | 344 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080146 | FTAP BTS | 11.1554 | 124.9671 | 2.28 | Terrestrial Optical Fiber Drop | 5.38 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2515 | 3 | 515 | 2515 | 0806407040 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Mantahan | 10.1333 | 124.8517 | R | 4152 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSLG0012 | PTCI/MIDC | 10.133 | 124.8465 | 0.57 | Terrestrial Optical Fiber Drop | 0.72 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2516 | 3 | 516 | 2516 | 1130700043 | Region XI (Davao Region) | Davao del Sur | City of Davao | Dumoy | 7.0322 | 125.5124 | U | 20432 | 6009 | 1803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110497 | FTAP Globe | 7.0355 | 125.5126 | 0.37 | Terrestrial Optical Fiber Drop | 2.54 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2517 | 3 | 517 | 2517 | 0403424063 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Rafael | 14.0729 | 121.309 | U | 5121 | 1551 | 465 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01993-C08 | PTCI/MIDC | 14.0703 | 121.3069 | 0.36 | Terrestrial Optical Fiber Drop | 1.21 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2518 | 3 | 518 | 2518 | 0304926031 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Santo Niño 2nd | 15.7975 | 120.9751 | U | 6641 | 1897 | 569 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01506-B07 | PTCI/MIDC | 15.7991 | 120.9771 | 0.28 | Terrestrial Optical Fiber Drop | 1.4 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2519 | 3 | 519 | 2519 | 0702207020 | Region VII (Central Visayas) | Cebu | Badian | Poblacion | 9.8645 | 123.3934 | R | 4388 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070367 | FTAP Globe | 9.7893 | 123.3464 | 9.82 | Terrestrial Optical Fiber Drop | 8.24 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2520 | 3 | 520 | 2520 | 0603031012 | Region VI (Western Visayas) | Iloilo | Mina | Mina East | 10.9302 | 122.5722 | R | 1317 | 346 | 104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTILG0054 | PTCI/MIDC | 10.9333 | 122.581 | 1.02 | Terrestrial Optical Fiber Drop | 1.42 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2521 | 3 | 521 | 2521 | 0301419020 | Region III (Central Luzon) | Bulacan | San Ildefonso | Malipampang | 15.0562 | 120.939 | U | 6904 | 1972 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N3642 | FTAP Smart | 15.0561 | 120.9369 | 0.22 | Terrestrial Optical Fiber Drop | 2.02 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2522 | 3 | 522 | 2522 | 1004307003 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Bolobolo | 8.5561 | 124.5333 | U | 4752 | 1218 | 365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100124 (FTAP_GLO_PH100124) | FTAP Globe | 8.5545 | 124.5256 | 0.87 | Terrestrial Optical Fiber Drop | 1.05 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2523 | 3 | 523 | 2523 | 0501730024 | Region V (Bicol Region) | Camarines Sur | Ragay | Lower Santa Cruz | 13.8166 | 122.7976 | R | 1448 | 344 | 103 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050045 | FTAP Globe | 13.8174 | 122.7937 | 0.43 | Terrestrial Optical Fiber Drop | 1 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2524 | 3 | 524 | 2524 | 0300809021 | Region III (Central Luzon) | Bataan | Orani | Tapulao | 14.8131 | 120.5198 | R | 5148 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00908-B07 | PTCI/MIDC | 14.8084 | 120.5269 | 0.93 | Terrestrial Optical Fiber Drop | 2.16 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2525 | 3 | 525 | 2525 | 1108204003 | Region XI (Davao Region) | Davao de Oro | Maco | Binuangan | 7.3703 | 125.854 | U | 6907 | 1866 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110429 | FTAP Globe | 7.3773 | 125.8398 | 1.75 | Terrestrial Optical Fiber Drop | 1.54 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2526 | 3 | 526 | 2526 | 0601914021 | Region VI (Western Visayas) | Capiz | City of Roxas | Cabugao | 11.5123 | 122.7476 | R | 2513 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 1.16 | Terrestrial Optical Fiber Drop | 1.34 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2527 | 3 | 527 | 2527 | 0402115028 | Region IV-A (CALABARZON) | Cavite | Naic | San Roque | 14.3099 | 120.7719 | R | 4809 | 1414 | 424 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040178 | FTAP Globe | 14.314 | 120.7694 | 0.53 | Terrestrial Optical Fiber Drop | 1.3 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2528 | 3 | 528 | 2528 | 0501736016 | Region V (Bicol Region) | Camarines Sur | Tigaon | Salvacion | 13.6021 | 123.4728 | R | 4195 | 998 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050097 | FTAP Globe | 13.5917 | 123.4584 | 1.93 | Terrestrial Optical Fiber Drop | 4.12 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2529 | 3 | 529 | 2529 | 0401014040 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 1 | 13.9422 | 121.1568 | U | 3616 | 1004 | 301 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040438 | FTAP Globe | 13.9434 | 121.1521 | 0.53 | Terrestrial Optical Fiber Drop | 1.07 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2530 | 3 | 530 | 2530 | 0702211013 | Region VII (Central Visayas) | Cebu | City of Bogo | La Paz | 10.9983 | 123.9822 | R | 4204 | 1106 | 332 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070304 | FTAP Globe | 11.0038 | 123.9821 | 0.6 | Terrestrial Optical Fiber Drop | 6.08 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2531 | 3 | 531 | 2531 | 0201522004 | Region II (Cagayan Valley) | Cagayan | Sanchez-Mira | Centro II | 18.5657 | 121.2284 | R | 2744 | 703 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-00006 | Edgepoint | 18.5712 | 121.2253 | 0.69 | Terrestrial Optical Fiber Drop | 1.16 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2532 | 3 | 532 | 2532 | 0403424002 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Bagong Pook VI-C | 14.073 | 121.3212 | R | 2038 | 617 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.4 | Terrestrial Optical Fiber Drop | 1.03 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2533 | 3 | 533 | 2533 | 0500509013 | Region V (Bicol Region) | Albay | Malilipot | San Isidro Ilawod | 13.3311 | 123.7377 | R | 3952 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050136 | FTAP Globe | 13.3221 | 123.7369 | 1.01 | Terrestrial Optical Fiber Drop | 2.51 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2534 | 3 | 534 | 2534 | 0501701001 | Region V (Bicol Region) | Camarines Sur | Baao | Agdangan Pob. | 13.4932 | 123.3249 | R | 4589 | 1092 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050112 | FTAP Globe | 13.4917 | 123.3276 | 0.33 | Terrestrial Optical Fiber Drop | 3.52 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2535 | 3 | 535 | 2535 | 0907333014 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Lakewood | Tubod | 7.8063 | 123.2052 | R | 3976 | 1019 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTZSG0033 | PTCI/MIDC | 7.8339 | 123.2242 | 3.71 | Terrestrial Optical Fiber Drop | 18.6 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2536 | 3 | 536 | 2536 | 0305404002 | Region III (Central Luzon) | Pampanga | Bacolor | Cabalantian | 15.0204 | 120.6735 | U | 6500 | 1625 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02684 | Edgepoint | 15.0212 | 120.6732 | 0.09 | Terrestrial Optical Fiber Drop | 2.22 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2537 | 3 | 537 | 2537 | 0305406009 | Region III (Central Luzon) | Pampanga | Floridablanca | Consuelo | 14.97 | 120.4974 | R | 3829 | 957 | 287 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01597-B07 | PTCI/MIDC | 14.9723 | 120.5012 | 0.49 | Terrestrial Optical Fiber Drop | 2.36 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2538 | 3 | 538 | 2538 | 1208007021 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Nagpan | 6.333 | 125.2642 | R | 3494 | 895 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120306 | FTAP Globe | 6.3454 | 125.2651 | 1.38 | Terrestrial Optical Fiber Drop | 3.14 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2539 | 3 | 539 | 2539 | 0405619037 | Region IV-A (CALABARZON) | Quezon | Gumaca | Progreso | 13.9077 | 122.0878 | R | 3156 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040502 | FTAP Globe | 13.9084 | 122.0941 | 0.69 | Terrestrial Optical Fiber Drop | 2.74 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2540 | 3 | 540 | 2540 | 0105518002 | Region I (Ilocos Region) | Pangasinan | City of Dagupan | Bacayao Sur | 16.0222 | 120.3463 | R | 2540 | 705 | 212 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00451 | Edgepoint | 16.0219 | 120.3511 | 0.51 | Terrestrial Optical Fiber Drop | 1.73 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2541 | 3 | 541 | 2541 | 0601905007 | Region VI (Western Visayas) | Capiz | Ivisan | Ilaya-Ivisan | 11.5178 | 122.7197 | R | 4049 | 1065 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 2.19 | Terrestrial Optical Fiber Drop | 2.83 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2542 | 3 | 542 | 2542 | 1404404005 | Cordillera Administrative Region (CAR) | Mountain Province | Bontoc | Bontoc Ili | 17.0872 | 120.9756 | R | 4395 | 1187 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-MOU-00185 | Edgepoint | 17.0863 | 120.9769 | 0.17 | Terrestrial Optical Fiber Drop | 7.96 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2543 | 3 | 543 | 2543 | 0403414007 | Region IV-A (CALABARZON) | Laguna | Mabitac | Paagahan | 14.4423 | 121.4004 | R | 4432 | 1343 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040097 | FTAP Globe | 14.4463 | 121.3812 | 2.12 | Terrestrial Optical Fiber Drop | 3.14 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2544 | 3 | 544 | 2544 | 0301403024 | Region III (Central Luzon) | Bulacan | Baliuag | Tangos | 14.9703 | 120.8945 | U | 8119 | 2319 | 696 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02426-B07 | PTCI/MIDC | 14.9694 | 120.896 | 0.19 | Terrestrial Optical Fiber Drop | 1.92 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2545 | 3 | 545 | 2545 | 0305402010 | Region III (Central Luzon) | Pampanga | Apalit | Sampaloc | 14.9673 | 120.7567 | U | 14226 | 3556 | 1067 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1118 | FTAP Smart | 14.9691 | 120.7568 | 0.2 | Terrestrial Optical Fiber Drop | 2.13 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2546 | 3 | 546 | 2546 | 0403424001 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Bagong Bayan II-A | 14.067 | 121.3195 | U | 7093 | 2149 | 645 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.93 | Terrestrial Optical Fiber Drop | 1.39 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2547 | 3 | 547 | 2547 | 1030500001 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Agusan | 8.4914 | 124.7429 | U | 19384 | 5384 | 1615 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0035 | PTCI/MIDC | 8.4944 | 124.7476 | 0.62 | Terrestrial Optical Fiber Drop | 1.04 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2548 | 3 | 548 | 2548 | 0501606041 | Region V (Bicol Region) | Camarines Norte | Labo | Masalong | 14.1693 | 122.8075 | R | 3471 | 867 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03171-C10 | PTCI/MIDC | 14.1738 | 122.81 | 0.57 | Terrestrial Optical Fiber Drop | 3.27 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2549 | 3 | 549 | 2549 | 0203114062 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Naguilian Norte | 17.1644 | 121.8722 | R | 3349 | 881 | 264 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ISA_0006 | LDIC | 17.1613 | 121.8715 | 0.35 | Terrestrial Optical Fiber Drop | 1.14 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2550 | 3 | 550 | 2550 | 0301420057 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Santa Cruz V | 14.856 | 121.0513 | R | 3984 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01200 | Edgepoint | 14.7762 | 121.072 | 0.47 | Terrestrial Optical Fiber Drop | 2.18 | 5.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2551 | 3 | 551 | 2551 | 0201503012 | Region II (Cagayan Valley) | Cagayan | Allacapan | Daan-Ili | 18.2385 | 121.5551 | R | 1923 | 493 | 148 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | LDIC_CAG_0062 | LDIC | 121.5595 | 18.2277 | 1.28 | Terrestrial Optical Fiber Drop | 1.38 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2552 | 3 | 552 | 2552 | 0603035033 | Region VI (Western Visayas) | Iloilo | City of Passi | Man-it | 11.099 | 122.6362 | R | 4702 | 1237 | 371 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060030 | FTAP BTS | 11.0965 | 122.6529 | 1.84 | Terrestrial Optical Fiber Drop | 1.3 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2553 | 3 | 553 | 2553 | 0103302010 | Region I (Ilocos Region) | La Union | Aringay | Poblacion | 16.3958 | 120.3557 | R | 3517 | 950 | 285 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-LUN-00343 | Edgepoint | 16.3924 | 120.3526 | 0.51 | Terrestrial Optical Fiber Drop | 3.86 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2554 | 3 | 554 | 2554 | 0403415011 | Region IV-A (CALABARZON) | Laguna | Magdalena | Cigaras | 14.2239 | 121.4301 | R | 3939 | 1193 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 2.54 | Terrestrial Optical Fiber Drop | 2.82 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2555 | 3 | 555 | 2555 | 0301418010 | Region III (Central Luzon) | Bulacan | Pulilan | Longos | 14.8967 | 120.8648 | U | 6080 | 1737 | 521 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01059 | Edgepoint | 14.8942 | 120.8668 | 0.36 | Terrestrial Optical Fiber Drop | 1.64 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2556 | 3 | 556 | 2556 | 0304909025 | Region III (Central Luzon) | Nueva Ecija | General Mamerto Natividad | Talabutab Norte | 15.5998 | 121.0781 | R | 4419 | 1262 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00637 | Edgepoint | 15.5998 | 121.0747 | 0.37 | Terrestrial Optical Fiber Drop | 2.95 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2557 | 3 | 557 | 2557 | 0401014043 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Poblacion Barangay 2 | 13.9422 | 121.1573 | U | 3253 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.56 | Terrestrial Optical Fiber Drop | 1.01 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2558 | 3 | 558 | 2558 | 0501720013 | Region V (Bicol Region) | Camarines Sur | Magarao | Santa Lucia | 13.6651 | 123.2025 | U | 6463 | 1538 | 461 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0002 | PTCI/MIDC | 13.6611 | 123.2033 | 0.45 | Terrestrial Optical Fiber Drop | 2.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2559 | 3 | 559 | 2559 | 0300809025 | Region III (Central Luzon) | Bataan | Orani | Apollo | 14.8013 | 120.5193 | R | 1948 | 541 | 162 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0016 | PTCI/MIDC | 14.8006 | 120.5268 | 0.27 | Terrestrial Optical Fiber Drop | 1.83 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2560 | 3 | 560 | 2560 | 1004322007 | Region X (Northern Mindanao) | Misamis Oriental | Salay | Inobulan | 8.885 | 124.7911 | R | 3210 | 823 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0073 | PTCI/MIDC | 8.8555 | 124.7856 | 3.33 | Terrestrial Optical Fiber Drop | 3.1 | 0.11 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2561 | 3 | 561 | 2561 | 0702250003 | Region VII (Central Visayas) | Cebu | City of Talisay | Cansojong | 10.2503 | 123.8543 | U | 17756 | 4672 | 1402 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070360 | FTAP Globe | 10.2466 | 123.8519 | 0.49 | Terrestrial Optical Fiber Drop | 1.37 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2562 | 3 | 562 | 2562 | 0307104003 | Region III (Central Luzon) | Zambales | Castillejos | Del Pilar | 14.9261 | 120.2148 | U | 12730 | 3350 | 1005 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01836-B07 | PTCI/MIDC | 14.9337 | 120.2109 | 0.94 | Terrestrial Optical Fiber Drop | 1.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2563 | 3 | 563 | 2563 | 0305416008 | Region III (Central Luzon) | Pampanga | City of San Fernando | Del Pilar | 15.034 | 120.6953 | U | 11493 | 2873 | 862 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00010-B07 | PTCI/MIDC | 15.0353 | 120.694 | 0.21 | Terrestrial Optical Fiber Drop | 1.65 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2564 | 3 | 564 | 2564 | 0301403021 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Niño | 14.986 | 120.8917 | R | 4520 | 1291 | 387 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02373-B07 | PTCI/MIDC | 14.9881 | 120.8862 | 0.64 | Terrestrial Optical Fiber Drop | 2.66 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2565 | 3 | 565 | 2565 | 0702231002 | Region VII (Central Visayas) | Cebu | Medellin | Curva | 11.139 | 124.0035 | R | 2524 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 4.7 | Terrestrial Optical Fiber Drop | 1.83 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2566 | 3 | 566 | 2566 | 0701205014 | Region VII (Central Visayas) | Bohol | Baclayon | San Vicente | 9.6252 | 123.922 | R | 1417 | 354 | 106 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 3.6 | Terrestrial Optical Fiber Drop | 1 | 0 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2567 | 3 | 567 | 2567 | 0704601008 | Region VII (Central Visayas) | Negros Oriental | Amlan | Tandayag | 9.4478 | 123.2361 | R | 4074 | 1072 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0070 | PTCI/MIDC | 9.4414 | 123.2359 | 0.71 | Terrestrial Optical Fiber Drop | 2.18 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2568 | 3 | 568 | 2568 | 0803738011 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Cagbuhangin | 11.1003 | 124.5846 | R | 1984 | 522 | 157 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH080189 | FTAP BTS | 11.0827 | 124.5638 | 3 | Terrestrial Optical Fiber Drop | 1.39 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2569 | 3 | 569 | 2569 | 0501708022 | Region V (Bicol Region) | Camarines Sur | Calabanga | Manguiring | 13.7461 | 123.2783 | U | 4100 | 976 | 293 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050054 | FTAP Globe | 13.7374 | 123.2697 | 1.34 | Terrestrial Optical Fiber Drop | 1.58 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2570 | 3 | 570 | 2570 | 0604511021 | Region VI (Western Visayas) | Negros Occidental | Hinigaran | Pilar | 10.2489 | 122.8578 | R | 5013 | 1354 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060380 | FTAP Globe | 10.24 | 122.8972 | 4.42 | Terrestrial Optical Fiber Drop | 13.83 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2571 | 3 | 571 | 2571 | 0702234008 | Region VII (Central Visayas) | Cebu | City of Naga | Colon | 10.2213 | 123.7611 | U | 5364 | 1411 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 2.07 | Terrestrial Optical Fiber Drop | 1.83 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2572 | 3 | 572 | 2572 | 0105546022 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Mabanogbog | 15.9755 | 120.5515 | R | 3498 | 971 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010178 | FTAP Globe | 15.9724 | 120.5531 | 0.39 | Terrestrial Optical Fiber Drop | 2.99 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2573 | 3 | 573 | 2573 | 0306904008 | Region III (Central Luzon) | Tarlac | Capas | Estrada | 15.3996 | 120.5984 | U | 4234 | 1085 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01809-B07 | PTCI/MIDC | 15.3957 | 120.5942 | 0.63 | Terrestrial Optical Fiber Drop | 1.57 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2574 | 3 | 574 | 2574 | 0201512003 | Region II (Cagayan Valley) | Cagayan | Enrile | Barangay II | 17.5705 | 121.6781 | R | 2746 | 704 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020052 | FTAP Globe | 17.5692 | 121.6685 | 1.02 | Terrestrial Optical Fiber Drop | 2.12 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2575 | 3 | 575 | 2575 | 0704604025 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Panala-an | 9.6076 | 123.0362 | R | 4233 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNLG0007 | PTCI/MIDC | 9.6245 | 123.0979 | 7.03 | Terrestrial Optical Fiber Drop | 9.74 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2576 | 3 | 576 | 2576 | 0704614001 | Region VII (Central Visayas) | Negros Oriental | Mabinay | Abis | 9.7385 | 122.9381 | R | 3751 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0034 | PTCI/MIDC | 9.7257 | 122.9276 | 1.83 | Terrestrial Optical Fiber Drop | 1.55 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2577 | 3 | 577 | 2577 | 0501701018 | Region V (Bicol Region) | Camarines Sur | Baao | San Juan | 13.4519 | 123.3874 | R | 3794 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050119 | FTAP Globe | 13.4487 | 123.3867 | 0.36 | Terrestrial Optical Fiber Drop | 2.47 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2578 | 3 | 578 | 2578 | 1401105006 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Bangao | 16.8184 | 120.8334 | U | 5463 | 1560 | 468 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_BGT_0002 | LDIC | 16.7963 | 120.8203 | 2.83 | Terrestrial Optical Fiber Drop | 2.11 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2579 | 3 | 579 | 2579 | 1004312003 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Buko | 8.9939 | 124.8048 | R | 2578 | 661 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 1.96 | Terrestrial Optical Fiber Drop | 1.72 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2580 | 3 | 580 | 2580 | 0401002018 | Region IV-A (CALABARZON) | Batangas | Alitagtag | San Jose | 13.8647 | 120.9969 | R | 2513 | 698 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03243-C08 | PTCI/MIDC | 13.8652 | 121.0025 | 0.61 | Terrestrial Optical Fiber Drop | 1.23 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2581 | 3 | 581 | 2581 | 0600403013 | Region VI (Western Visayas) | Aklan | Banga | Linabuan Sur | 11.6499 | 122.3444 | R | 4098 | 1050 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKG0015 | PTCI/MIDC | 11.6564 | 122.3448 | 0.73 | Terrestrial Optical Fiber Drop | 2.15 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2582 | 3 | 582 | 2582 | 1130700036 | Region XI (Davao Region) | Davao del Sur | City of Davao | Crossing Bayabas | 7.0252 | 125.4948 | U | 12909 | 3796 | 1139 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110207 | FTAP BTS | 7.028 | 125.4948 | 0.31 | Terrestrial Optical Fiber Drop | 1.5 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2583 | 3 | 583 | 2583 | 0702205010 | Region VII (Central Visayas) | Cebu | Argao | Bulasa | 9.9315 | 123.6177 | R | 4032 | 1061 | 318 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0006 | PTCI/MIDC | 9.9557 | 123.6173 | 2.7 | Terrestrial Optical Fiber Drop | 5.71 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2584 | 3 | 584 | 2584 | 0105546034 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | San Vicente | 15.9803 | 120.5701 | U | 9856 | 2737 | 821 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00491 | Edgepoint | 15.9774 | 120.565 | 0.64 | Terrestrial Optical Fiber Drop | 2.31 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2585 | 3 | 585 | 2585 | 0604520011 | Region VI (Western Visayas) | Negros Occidental | Murcia | Caliban | 10.5854 | 123.0719 | R | 3194 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 0.89 | Terrestrial Optical Fiber Drop | 2.22 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2586 | 3 | 586 | 2586 | 0300809023 | Region III (Central Luzon) | Bataan | Orani | Tugatog | 14.8014 | 120.5192 | U | 8501 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030604 | FTAP Globe | 14.8 | 120.5202 | 0.18 | Terrestrial Optical Fiber Drop | 1.84 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2587 | 3 | 587 | 2587 | 0702227014 | Region VII (Central Visayas) | Cebu | Liloan | Yati | 10.3933 | 123.9832 | U | 37883 | 9969 | 2991 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070322 | FTAP Globe | 10.3959 | 123.985 | 0.36 | Terrestrial Optical Fiber Drop | 2.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2588 | 3 | 588 | 2588 | 0304916018 | Region III (Central Luzon) | Nueva Ecija | Lupao | Parista | 15.8631 | 120.9193 | R | 4851 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030307 | FTAP Globe | 15.8633 | 120.9183 | 0.1 | Terrestrial Optical Fiber Drop | 3.32 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2589 | 3 | 589 | 2589 | 0105521009 | Region I (Ilocos Region) | Pangasinan | Labrador | Tobuan | 16.0556 | 120.1097 | R | 3257 | 904 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00427 | Edgepoint | 16.053 | 120.1143 | 0.57 | Terrestrial Optical Fiber Drop | 1.39 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2590 | 3 | 590 | 2590 | 0431200028 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Mayao Kanluran | 13.9497 | 121.6352 | U | 13027 | 3256 | 977 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0003 | PTCI/MIDC | 13.9492 | 121.6278 | 0.8 | Terrestrial Optical Fiber Drop | 1.42 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2591 | 3 | 591 | 2591 | 0501703027 | Region V (Bicol Region) | Camarines Sur | Bato | San Miguel | 13.3475 | 123.3836 | R | 4379 | 1042 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02836-C10 | PTCI/MIDC | 13.3486 | 123.3761 | 0.83 | Terrestrial Optical Fiber Drop | 2.29 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2592 | 3 | 592 | 2592 | 0803738082 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | San Isidro | 11.0271 | 124.5948 | U | 6373 | 1677 | 503 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0101 | PTCI/MIDC | 11.0267 | 124.5934 | 0.16 | Terrestrial Optical Fiber Drop | 0.59 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2593 | 3 | 593 | 2593 | 1001317025 | Region X (Northern Mindanao) | Bukidnon | Quezon | Paitan | 7.7027 | 125.1132 | R | 3600 | 947 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100215 | FTAP Globe | 7.7003 | 125.1167 | 1.35 | Terrestrial Optical Fiber Drop | 0.56 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2594 | 3 | 594 | 2594 | 0305408016 | Region III (Central Luzon) | Pampanga | Lubao | San Isidro | 14.8847 | 120.5243 | R | 4453 | 1113 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030561 | FTAP Globe | 14.8856 | 120.5198 | 0.49 | Terrestrial Optical Fiber Drop | 4.31 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2595 | 3 | 595 | 2595 | 1108204002 | Region XI (Davao Region) | Davao de Oro | Maco | Anislagan | 7.3458 | 125.8596 | R | 2787 | 753 | 226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 1.39 | Terrestrial Optical Fiber Drop | 1.26 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2596 | 3 | 596 | 2596 | 0304903046 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Mabini Extension | 15.4857 | 120.9742 | U | 3497 | 999 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030381 | FTAP Globe | 15.486 | 120.9751 | 0.11 | Terrestrial Optical Fiber Drop | 1.47 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2597 | 3 | 597 | 2597 | 0403404011 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Niugan | 14.263 | 121.1286 | U | 42286 | 12813 | 3844 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02105-C08 | PTCI/MIDC | 14.2643 | 121.1272 | 0.21 | Terrestrial Optical Fiber Drop | 1.87 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2598 | 3 | 598 | 2598 | 1401103005 | Cordillera Administrative Region (CAR) | Benguet | Bakun | Gambang | 16.7419 | 120.7976 | R | 3886 | 1110 | 333 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH140171 | FTAP Globe | 16.7237 | 120.784 | 2.48 | Terrestrial Optical Fiber Drop | 2.89 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2599 | 3 | 599 | 2599 | 1001315018 | Region X (Northern Mindanao) | Bukidnon | Maramag | Tubigon | 7.8357 | 125.0214 | R | 2775 | 730 | 219 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100053 | FTAP BTS | 7.837 | 125.0323 | 1.21 | Terrestrial Optical Fiber Drop | 2.6 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2600 | 3 | 600 | 2600 | 0405805019 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Niño | 14.5797 | 121.1137 | U | 6105 | 1695 | 509 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040040 | FTAP Globe | 14.5854 | 121.1118 | 0.4 | Terrestrial Optical Fiber Drop | 1.14 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2601 | 3 | 601 | 2601 | 0500516021 | Region V (Bicol Region) | Albay | Santo Domingo | San Isidro | 13.2296 | 123.7683 | R | 3161 | 770 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1669 | FTAP Smart | 13.2375 | 123.7681 | 0.88 | Terrestrial Optical Fiber Drop | 1.27 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2602 | 3 | 602 | 2602 | 0301403025 | Region III (Central Luzon) | Bulacan | Baliuag | Tarcan | 14.9325 | 120.8792 | U | 9208 | 2630 | 789 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01040-B07 | PTCI/MIDC | 14.9291 | 120.8846 | 0.69 | Terrestrial Optical Fiber Drop | 1.96 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2603 | 3 | 603 | 2603 | 0403405013 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Halang | 14.1978 | 121.1603 | U | 9407 | 2850 | 855 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02120-C08 | PTCI/MIDC | 14.2013 | 121.1654 | 0.68 | Terrestrial Optical Fiber Drop | 1.52 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2604 | 3 | 604 | 2604 | 0500518012 | Region V (Bicol Region) | Albay | Tiwi | Joroan | 13.4912 | 123.6213 | R | 3015 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050113 | FTAP Globe | 13.4889 | 123.6261 | 0.57 | Terrestrial Optical Fiber Drop | 2.27 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2605 | 3 | 605 | 2605 | 0304908016 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Santo Cristo Sur | 15.2675 | 120.9499 | R | 4886 | 1396 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NUE_0012 | LDIC | 15.2678 | 120.9503 | 0.05 | Terrestrial Optical Fiber Drop | 0.13 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2606 | 3 | 606 | 2606 | 1004321003 | Region X (Northern Mindanao) | Misamis Oriental | Opol | Barra | 8.514 | 124.6076 | U | 15306 | 3924 | 1177 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0042 | PTCI/MIDC | 8.5124 | 124.6138 | 0.7 | Terrestrial Optical Fiber Drop | 1.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2607 | 3 | 607 | 2607 | 0403424013 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay III-C | 14.0687 | 121.3305 | R | 3040 | 921 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_LAG_0009 | LDIC | 14.073 | 121.3264 | 0.65 | Terrestrial Optical Fiber Drop | 1.05 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2608 | 3 | 608 | 2608 | 0403406007 | Region IV-A (CALABARZON) | Laguna | Calauan | Lamot 2 | 14.1616 | 121.3296 | U | 8226 | 2492 | 748 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040281 | FTAP Globe | 14.1602 | 121.3319 | 0.28 | Terrestrial Optical Fiber Drop | 2.42 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2609 | 3 | 609 | 2609 | 0630200042 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 7 | 10.6619 | 122.9441 | U | 2503 | 695 | 209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0015 | PTCI/MIDC | 10.6614 | 122.9402 | 0.43 | Terrestrial Optical Fiber Drop | 1.05 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2610 | 3 | 610 | 2610 | 0330100028 | Region III (Central Luzon) | Pampanga | City of Angeles | Sto. Domingo | 15.1265 | 120.6004 | U | 19500 | 5416 | 1625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0023 | FTAP Smart | 15.1368 | 120.5909 | 0.4 | Terrestrial Optical Fiber Drop | 0.41 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2611 | 3 | 611 | 2611 | 0403424070 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Isabel | 14.0868 | 121.35 | R | 4198 | 1272 | 382 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040336 | FTAP Globe | 14.0846 | 121.3413 | 0.97 | Terrestrial Optical Fiber Drop | 3.68 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2612 | 3 | 612 | 2612 | 0702241014 | Region VII (Central Visayas) | Cebu | San Fernando | Panadtaran | 10.1514 | 123.6988 | U | 6360 | 1673 | 502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070192 | FTAP BTS | 10.1566 | 123.7032 | 0.75 | Terrestrial Optical Fiber Drop | 1.58 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2613 | 3 | 613 | 2613 | 0631000026 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Buntatala | 10.7686 | 122.5836 | U | 4584 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.89 | Terrestrial Optical Fiber Drop | 2.02 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2614 | 3 | 614 | 2614 | 0203126017 | Region II (Cagayan Valley) | Isabela | Roxas | San Antonio | 17.0951 | 121.615 | R | 3658 | 962 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0041 | PTCI/MIDC | 17.0989 | 121.6164 | 0.45 | Terrestrial Optical Fiber Drop | 2.31 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2615 | 3 | 615 | 2615 | 0304908010 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Lorenzo | 15.3125 | 120.9538 | U | 6467 | 1847 | 554 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02508 | Edgepoint | 15.3146 | 120.9576 | 0.47 | Terrestrial Optical Fiber Drop | 1.04 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2616 | 3 | 616 | 2616 | 0304908013 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | San Vicente | 15.3141 | 120.9479 | U | 9910 | 2831 | 849 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030419 | FTAP Globe | 15.3115 | 120.9467 | 0.32 | Terrestrial Optical Fiber Drop | 0.75 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2617 | 3 | 617 | 2617 | 1600302005 | Region XIII (Caraga) | Agusan del Sur | Bunawan | Poblacion | 8.1702 | 125.9995 | R | 4991 | 1279 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTASG0010 | PTCI/MIDC | 8.4903 | 125.9756 | 2.91 | Terrestrial Optical Fiber Drop | 1.39 | 0.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2618 | 3 | 618 | 2618 | 0702216020 | Region VII (Central Visayas) | Cebu | Catmon | Flores | 10.7178 | 124.0124 | R | 3458 | 910 | 273 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070312 | FTAP Globe | 10.7253 | 124.014 | 0.85 | Terrestrial Optical Fiber Drop | 2.66 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2619 | 3 | 619 | 2619 | 0702224034 | Region VII (Central Visayas) | Cebu | Dumanjug | Tangil | 10.0722 | 123.4493 | R | 3196 | 841 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_CEB_0001 | LDIC | 10.0758 | 123.4523 | 0.52 | Terrestrial Optical Fiber Drop | 2.28 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2620 | 3 | 620 | 2620 | 0401017006 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Sur | 14.0362 | 121.162 | R | 5100 | 1416 | 425 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.59 | Terrestrial Optical Fiber Drop | 1.75 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2621 | 3 | 621 | 2621 | 0600402004 | Region VI (Western Visayas) | Aklan | Balete | Calizo | 11.5682 | 122.3639 | R | 4501 | 1154 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_AKN_0006 | LDIC | 11.5723 | 122.3615 | 0.52 | Terrestrial Optical Fiber Drop | 1.02 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2622 | 3 | 622 | 2622 | 0307701012 | Region III (Central Luzon) | Aurora | Baler | Suclayin | 15.7557 | 121.5486 | U | 4865 | 1280 | 384 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-AUR-02563 | Edgepoint | 15.7541 | 121.5528 | 0.48 | Terrestrial Optical Fiber Drop | 1.67 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2623 | 3 | 623 | 2623 | 0403426011 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Pagsawitan | 14.2651 | 121.4252 | U | 11162 | 3382 | 1015 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01991-C08 | PTCI/MIDC | 14.2664 | 121.4208 | 0.49 | Terrestrial Optical Fiber Drop | 2.02 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2624 | 3 | 624 | 2624 | 0704601001 | Region VII (Central Visayas) | Negros Oriental | Amlan | Bio-os | 9.4707 | 123.1956 | R | 4275 | 1125 | 338 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0082 | PTCI/MIDC | 9.4639 | 123.1849 | 1.39 | Terrestrial Optical Fiber Drop | 3.05 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2625 | 3 | 625 | 2625 | 0301417003 | Region III (Central Luzon) | Bulacan | Plaridel | Banga I | 14.8879 | 120.8711 | U | 6159 | 1759 | 528 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030563 | FTAP Globe | 14.8814 | 120.8665 | 0.51 | Terrestrial Optical Fiber Drop | 2.72 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2626 | 3 | 626 | 2626 | 0702241016 | Region VII (Central Visayas) | Cebu | San Fernando | San Isidro | 10.1725 | 123.7149 | U | 4641 | 1221 | 366 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0146 | PTCI/MIDC | 10.1738 | 123.7182 | 0.38 | Terrestrial Optical Fiber Drop | 1.36 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2627 | 3 | 627 | 2627 | 0305416013 | Region III (Central Luzon) | Pampanga | City of San Fernando | Lourdes | 15.0314 | 120.6878 | R | 4292 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00922 | Edgepoint | 15.0321 | 120.6895 | 0.2 | Terrestrial Optical Fiber Drop | 1.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2628 | 3 | 628 | 2628 | 1606724026 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Luna | 9.7668 | 125.4845 | U | 14000 | 3414 | 1024 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130037 | FTAP BTS | 9.7788 | 125.4839 | 1.34 | Terrestrial Optical Fiber Drop | 2.62 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2629 | 3 | 629 | 2629 | 0305421007 | Region III (Central Luzon) | Pampanga | Sto. Tomas | San Vicente | 14.9946 | 120.7044 | U | 10661 | 2665 | 800 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00900 | Edgepoint | 15.0665 | 120.6602 | 0.66 | Terrestrial Optical Fiber Drop | 1.47 | 1.68 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2630 | 3 | 630 | 2630 | 1606819008 | Region XIII (Caraga) | Surigao del Sur | City of Tandag | Mabua | 17.1051 | 122.2741 | U | 8562 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130063 | FTAP Globe | 9.0487 | 126.2087 | 1.72 | Terrestrial Optical Fiber Drop | 27.52 | 37.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2631 | 3 | 631 | 2631 | 0304903031 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Dicarma | 15.4843 | 120.9713 | U | 4735 | 1352 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1236 | FTAP Smart | 15.4805 | 120.9702 | 0.44 | Terrestrial Optical Fiber Drop | 1.13 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2632 | 3 | 632 | 2632 | 0600407006 | Region VI (Western Visayas) | Aklan | Kalibo | Buswang Old | 11.7068 | 122.3645 | U | 3796 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.44 | Terrestrial Optical Fiber Drop | 1.07 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2633 | 3 | 633 | 2633 | 1130700176 | Region XI (Davao Region) | Davao del Sur | City of Davao | Bago Aplaya | 7.0466 | 125.5373 | U | 19697 | 5793 | 1738 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDSR0013 | PTCI/MIDC | 7.0507 | 125.541 | 0.62 | Terrestrial Optical Fiber Drop | 1.65 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2634 | 3 | 634 | 2634 | 0300803025 | Region III (Central Luzon) | Bataan | City of Balanga | Cupang North | 14.6751 | 120.5386 | R | 2656 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030624 | FTAP Globe | 14.6886 | 120.5239 | 0.69 | Terrestrial Optical Fiber Drop | 1.08 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2635 | 3 | 635 | 2635 | 0402106038 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Roque | 14.3201 | 120.9569 | R | 3006 | 884 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAG0023 | PTCI/MIDC | 14.2938 | 120.9461 | 1.06 | Terrestrial Optical Fiber Drop | 1.27 | 2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2636 | 3 | 636 | 2636 | 0601914004 | Region VI (Western Visayas) | Capiz | City of Roxas | Banica | 11.5822 | 122.7594 | U | 9285 | 2443 | 733 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCZG0026 | PTCI/MIDC | 11.5794 | 122.7532 | 0.74 | Terrestrial Optical Fiber Drop | 1.42 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2637 | 3 | 637 | 2637 | 0631000179 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Tagbac | 10.7668 | 122.5795 | U | 5212 | 1240 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILG0040 | PTCI/MIDC | 10.7642 | 122.5768 | 0.41 | Terrestrial Optical Fiber Drop | 2.36 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2638 | 3 | 638 | 2638 | 1208007014 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Kinabalan | 6.4588 | 125.3111 | R | 2094 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH120294 | FTAP Globe | 6.4811 | 125.3261 | 2.98 | Terrestrial Optical Fiber Drop | 1.68 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2639 | 3 | 639 | 2639 | 0307103007 | Region III (Central Luzon) | Zambales | Candelaria | Malabon | 15.6385 | 119.9349 | R | 3329 | 876 | 263 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-00621 | Edgepoint | 15.6398 | 119.9316 | 0.38 | Terrestrial Optical Fiber Drop | 1.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2640 | 3 | 640 | 2640 | 0402105044 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 49 | 14.4882 | 120.897 | R | 1477 | 434 | 130 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.3 | Terrestrial Optical Fiber Drop | 1.8 | 4.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2641 | 3 | 641 | 2641 | 0803707013 | Region VIII (Eastern Visayas) | Leyte | Bato | Dolho | 10.3349 | 124.7857 | R | 3536 | 930 | 279 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080139 | FTAP BTS | 10.3279 | 124.7938 | 1.18 | Terrestrial Optical Fiber Drop | 22.26 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2642 | 3 | 642 | 2642 | 1001304005 | Region X (Northern Mindanao) | Bukidnon | Don Carlos | Don Carlos Norte | 7.6906 | 124.9977 | U | 8257 | 2172 | 652 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTBKG0053 | PTCI/MIDC | 7.6698 | 124.9955 | 2.33 | Terrestrial Optical Fiber Drop | 1.48 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2643 | 3 | 643 | 2643 | 0401026025 | Region IV-A (CALABARZON) | Batangas | San Pascual | San Antonio | 13.7871 | 121.0186 | U | 10340 | 2872 | 862 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S1335 | FTAP Smart | 13.7873 | 121.0133 | 0.57 | Terrestrial Optical Fiber Drop | 1.64 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2644 | 3 | 644 | 2644 | 0307104005 | Region III (Central Luzon) | Zambales | Castillejos | Magsaysay | 14.9419 | 120.1887 | U | 3852 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-02717 | Edgepoint | 14.9397 | 120.1927 | 0.49 | Terrestrial Optical Fiber Drop | 1.86 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2645 | 3 | 645 | 2645 | 0105512015 | Region I (Ilocos Region) | Pangasinan | Binalonan | Poblacion | 16.0529 | 120.5892 | U | 7412 | 2058 | 617 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N0052 | FTAP Smart | 16.0503 | 120.5898 | 0.3 | Terrestrial Optical Fiber Drop | 1.05 | 0.75 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2646 | 3 | 646 | 2646 | 0403426005 | Region IV-A (CALABARZON) | Laguna | Santa Cruz | Duhat | 14.2467 | 121.3793 | U | 8104 | 2455 | 737 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02018-C08 | PTCI/MIDC | 14.2525 | 121.3876 | 1.1 | Terrestrial Optical Fiber Drop | 1.81 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2647 | 3 | 647 | 2647 | 0103313030 | Region I (Ilocos Region) | La Union | Rosario | Tabtabungao | 16.2406 | 120.4545 | R | 3264 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02700-B05 | PTCI/MIDC | 16.2244 | 120.4789 | 1.31 | Terrestrial Optical Fiber Drop | 3.28 | 1.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2648 | 3 | 648 | 2648 | 0304916033 | Region III (Central Luzon) | Nueva Ecija | Lupao | San Roque | 15.8955 | 120.8913 | R | 2098 | 599 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01463-B07 | PTCI/MIDC | 15.8972 | 120.8923 | 0.22 | Terrestrial Optical Fiber Drop | 1.38 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2649 | 3 | 649 | 2649 | 0501603007 | Region V (Bicol Region) | Camarines Norte | Daet | Camambugan | 14.1072 | 122.9475 | U | 9118 | 2279 | 684 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCNG0009 | PTCI/MIDC | 14.1084 | 122.9523 | 0.53 | Terrestrial Optical Fiber Drop | 1.06 | 1.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2650 | 3 | 650 | 2650 | 1004303007 | Region X (Northern Mindanao) | Misamis Oriental | Balingoan | Lapinig | 9.006 | 124.8525 | R | 1463 | 375 | 113 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0003 | PTCI/MIDC | 9.004 | 124.8534 | 0.24 | Terrestrial Optical Fiber Drop | 1.1 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2651 | 3 | 651 | 2651 | 0907344001 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Tigbao | Begong | 7.8298 | 123.313 | R | 3769 | 966 | 290 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090134 | FTAP Globe | 7.8313 | 123.3137 | 0.18 | Terrestrial Optical Fiber Drop | 13.92 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2652 | 3 | 652 | 2652 | 0405641015 | Region IV-A (CALABARZON) | Quezon | San Antonio | Pulo | 13.8904 | 121.3151 | R | 2337 | 615 | 185 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02132-C08 | PTCI/MIDC | 13.9068 | 121.3032 | 0.91 | Terrestrial Optical Fiber Drop | 2.85 | 2.02 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2653 | 3 | 653 | 2653 | 0702211009 | Region VII (Central Visayas) | Cebu | City of Bogo | Dakit | 11.0294 | 124.0015 | U | 6548 | 1723 | 517 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0015 | PTCI/MIDC | 11.0328 | 124.0006 | 0.38 | Terrestrial Optical Fiber Drop | 2.07 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2654 | 3 | 654 | 2654 | 0603007025 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Tabucan | 10.9041 | 122.6912 | R | 3802 | 1000 | 300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0005 | PTCI/MIDC | 10.9016 | 122.6874 | 0.5 | Terrestrial Optical Fiber Drop | 1.69 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2655 | 3 | 655 | 2655 | 0203113009 | Region II (Cagayan Valley) | Isabela | Gamu | Guibang | 17.0561 | 121.8561 | R | 3122 | 821 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH020067 | FTAP Globe | 17.0544 | 121.8573 | 0.23 | Terrestrial Optical Fiber Drop | 1.99 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2656 | 3 | 656 | 2656 | 0500516023 | Region V (Bicol Region) | Albay | Santo Domingo | Santa Misericordia | 13.2548 | 123.7587 | R | 3256 | 794 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03092-C10 | PTCI/MIDC | 13.2545 | 123.7582 | 0.06 | Terrestrial Optical Fiber Drop | 2.81 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2657 | 3 | 657 | 2657 | 0301403010 | Region III (Central Luzon) | Bulacan | Baliuag | Pagala | 14.9526 | 120.889 | U | 7563 | 2160 | 648 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0006 | PTCI/MIDC | 14.9582 | 120.8893 | 0.38 | Terrestrial Optical Fiber Drop | 0.52 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2658 | 3 | 658 | 2658 | 0401009010 | Region IV-A (CALABARZON) | Batangas | Cuenca | Ibabao | 13.9087 | 121.0723 | R | 3935 | 1093 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4624 | FTAP Smart | 13.9068 | 121.0708 | 0.26 | Terrestrial Optical Fiber Drop | 2.73 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2659 | 3 | 659 | 2659 | 0301418034 | Region III (Central Luzon) | Bulacan | Pulilan | Tabon | 14.9106 | 120.827 | R | 5154 | 1472 | 442 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02490 | Edgepoint | 14.9094 | 120.8288 | 0.24 | Terrestrial Optical Fiber Drop | 2.7 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2660 | 3 | 660 | 2660 | 0403419014 | Region IV-A (CALABARZON) | Laguna | Pagsanjan | Sabang | 14.2669 | 121.4578 | R | 4090 | 1239 | 372 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040208 | FTAP Globe | 14.2666 | 121.4429 | 0.14 | Terrestrial Optical Fiber Drop | 1.09 | 0.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2661 | 3 | 661 | 2661 | 0603037011 | Region VI (Western Visayas) | Iloilo | Pototan | Cato-ogan | 10.937 | 122.6473 | R | 2575 | 677 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 0.82 | Terrestrial Optical Fiber Drop | 1.2 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2662 | 3 | 662 | 2662 | 0304926006 | Region III (Central Luzon) | Nueva Ecija | San Jose City | Calaocan | 15.786 | 120.9948 | U | 6480 | 1851 | 555 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030316 | FTAP Globe | 15.7882 | 120.9994 | 0.55 | Terrestrial Optical Fiber Drop | 1.22 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2663 | 3 | 663 | 2663 | 0730600015 | Region VII (Central Visayas) | Cebu | City of Cebu | Bulacao | 10.276 | 123.8497 | U | 28710 | 8971 | 2691 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0197 | PTCI/MIDC | 10.2761 | 123.8445 | 0.57 | Terrestrial Optical Fiber Drop | 1.54 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2664 | 3 | 664 | 2664 | 0730600046 | Region VII (Central Visayas) | Cebu | City of Cebu | Mabolo | 10.313 | 123.9153 | U | 21642 | 6763 | 2029 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.38 | Terrestrial Optical Fiber Drop | 2.24 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2665 | 3 | 665 | 2665 | 0306906001 | Region III (Central Luzon) | Tarlac | Gerona | Abagon | 15.6118 | 120.609 | U | 4879 | 1251 | 375 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00635 | Edgepoint | 15.6074 | 120.6046 | 0.68 | Terrestrial Optical Fiber Drop | 1.51 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2666 | 3 | 666 | 2666 | 0500508010 | Region V (Bicol Region) | Albay | City of Ligao | Batang | 13.2507 | 123.5641 | R | 3705 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050155 | FTAP Globe | 13.2473 | 123.5607 | 0.53 | Terrestrial Optical Fiber Drop | 2.28 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2667 | 3 | 667 | 2667 | 0403424004 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay I-B | 14.0691 | 121.3161 | U | 4387 | 1329 | 399 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02125-C08 | PTCI/MIDC | 14.0754 | 121.3184 | 0.74 | Terrestrial Optical Fiber Drop | 1.33 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2668 | 3 | 668 | 2668 | 0403405038 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 1 | 14.2049 | 121.1584 | U | 6383 | 1934 | 580 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4230 | FTAP Smart | 14.2081 | 121.1581 | 0.36 | Terrestrial Optical Fiber Drop | 1.57 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2669 | 3 | 669 | 2669 | 0405648015 | Region IV-A (CALABARZON) | Quezon | Tiaong | Lalig | 13.9791 | 121.327 | U | 8479 | 2231 | 669 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0014 | PTCI/MIDC | 13.98 | 121.3268 | 0.1 | Terrestrial Optical Fiber Drop | 1.93 | 0.15 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2670 | 3 | 670 | 2670 | 0305416011 | Region III (Central Luzon) | Pampanga | City of San Fernando | Juliana | 15.0346 | 120.6906 | U | 4295 | 1073 | 322 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00922 | Edgepoint | 15.0321 | 120.6895 | 0.31 | Terrestrial Optical Fiber Drop | 1.18 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2671 | 3 | 671 | 2671 | 1600209005 | Region XIII (Caraga) | Agusan del Norte | Nasipit | Camagong | 8.9702 | 125.3363 | U | 5875 | 1432 | 430 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0017 | PTCI/MIDC | 8.9849 | 125.3459 | 1.94 | Terrestrial Optical Fiber Drop | 1.33 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2672 | 3 | 672 | 2672 | 0203109003 | Region II (Cagayan Valley) | Isabela | Cordon | Capirpiriwan | 16.6674 | 121.4549 | R | 3762 | 990 | 297 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03316-B06 | PTCI/MIDC | 16.6644 | 121.4538 | 0.35 | Terrestrial Optical Fiber Drop | 8.22 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2673 | 3 | 673 | 2673 | 0501603015 | Region V (Bicol Region) | Camarines Norte | Daet | Lag-On | 14.1182 | 122.9421 | U | 6015 | 1503 | 451 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03030-C10 | PTCI/MIDC | 14.1218 | 122.9428 | 0.41 | Terrestrial Optical Fiber Drop | 1.31 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2674 | 3 | 674 | 2674 | 0203135020 | Region II (Cagayan Valley) | Isabela | City of Santiago | Malvar | 16.6826 | 121.5512 | U | 5125 | 1348 | 404 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00283 | Edgepoint | 16.687 | 121.5473 | 0.17 | Terrestrial Optical Fiber Drop | 2.75 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2675 | 3 | 675 | 2675 | 0401023008 | Region IV-A (CALABARZON) | Batangas | San Juan | Calitcalit | 13.8282 | 121.4107 | U | 4903 | 1361 | 408 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BTG-03175 | Edgepoint | 13.8273 | 121.397 | 1.49 | Terrestrial Optical Fiber Drop | 1.56 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2676 | 3 | 676 | 2676 | 0401014008 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Sebastian | 13.9351 | 121.1549 | U | 3755 | 1043 | 313 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S5200 | FTAP Smart | 13.9377 | 121.1597 | 0.59 | Terrestrial Optical Fiber Drop | 1.61 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2677 | 3 | 677 | 2677 | 0501724019 | Region V (Bicol Region) | Camarines Sur | City of Naga | Mabolo | 13.6146 | 123.1811 | U | 8106 | 1930 | 579 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 1 | Terrestrial Optical Fiber Drop | 1.15 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2678 | 3 | 678 | 2678 | 0907311010 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | Kumalarang | Diplo | 7.7828 | 123.1168 | R | 3928 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZSG0132 | PTCI/MIDC | 7.7816 | 123.117 | 0.14 | Terrestrial Optical Fiber Drop | 9 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2679 | 3 | 679 | 2679 | 0403424054 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Juan | 14.0928 | 121.3028 | R | 3679 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02083-C08 | PTCI/MIDC | 14.0881 | 121.3067 | 0.68 | Terrestrial Optical Fiber Drop | 1.97 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2680 | 3 | 680 | 2680 | 1030900008 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Hinaplanon | 8.2439 | 124.2572 | U | 15637 | 4115 | 1235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNR0010 | PTCI/MIDC | 8.2442 | 124.2545 | 0.3 | Terrestrial Optical Fiber Drop | 2.53 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2681 | 3 | 681 | 2681 | 0405804034 | Region IV-A (CALABARZON) | Rizal | Binangonan | Tagpos | 14.5082 | 121.169 | U | 15316 | 4254 | 1276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02301-A04 | PTCI/MIDC | 14.5078 | 121.1693 | 0.06 | Terrestrial Optical Fiber Drop | 1.9 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2682 | 3 | 682 | 2682 | 0403411001 | Region IV-A (CALABARZON) | Laguna | Los Baños | Anos | 14.1798 | 121.2295 | U | 9663 | 2928 | 878 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02109-C08 | PTCI/MIDC | 14.18 | 121.2259 | 0.38 | Terrestrial Optical Fiber Drop | 1.39 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2683 | 3 | 683 | 2683 | 1108209014 | Region XI (Davao Region) | Davao de Oro | Nabunturan | Mipangi | 7.5421 | 125.9196 | R | 4290 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDOG0030 | PTCI/MIDC | 7.5357 | 125.9157 | 0.82 | Terrestrial Optical Fiber Drop | 14.2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2684 | 3 | 684 | 2684 | 0600407013 | Region VI (Western Visayas) | Aklan | Kalibo | Poblacion | 11.7078 | 122.3679 | U | 12369 | 3171 | 951 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.3 | Terrestrial Optical Fiber Drop | 1.15 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2685 | 3 | 685 | 2685 | 0702251019 | Region VII (Central Visayas) | Cebu | City of Toledo | Ilihan | 10.3791 | 123.6576 | R | 4522 | 1190 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0171 | PTCI/MIDC | 10.3758 | 123.6582 | 0.38 | Terrestrial Optical Fiber Drop | 2.28 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2686 | 3 | 686 | 2686 | 0803708034 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Candadam | 10.6902 | 124.8033 | R | 3240 | 852 | 256 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080212 | FTAP BTS | 10.6869 | 124.8048 | 0.4 | Terrestrial Optical Fiber Drop | 1.21 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2687 | 3 | 687 | 2687 | 0501726006 | Region V (Bicol Region) | Camarines Sur | Pamplona | Del Rosario | 13.5762 | 123.0858 | R | 2668 | 635 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 1.98 | Terrestrial Optical Fiber Drop | 1.62 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2688 | 3 | 688 | 2688 | 0603045046 | Region VI (Western Visayas) | Iloilo | Tigbauan | Parara Sur | 10.6733 | 122.3665 | R | 2818 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060158 | FTAP BTS | 10.6758 | 122.3662 | 0.28 | Terrestrial Optical Fiber Drop | 1.74 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2689 | 3 | 689 | 2689 | 0405645002 | Region IV-A (CALABARZON) | Quezon | Sariaya | Balubal | 13.9678 | 121.5365 | U | 4735 | 1246 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Q55 | FTAP Smart | 13.9641 | 121.529 | 0.91 | Terrestrial Optical Fiber Drop | 2.19 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2690 | 3 | 690 | 2690 | 0203137001 | Region II (Cagayan Valley) | Isabela | Tumauini | Annafunan | 17.2743 | 121.8052 | R | 2094 | 551 | 165 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0032 | PTCI/MIDC | 17.2818 | 121.8054 | 0.83 | Terrestrial Optical Fiber Drop | 1.08 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2691 | 3 | 691 | 2691 | 0600407016 | Region VI (Western Visayas) | Aklan | Kalibo | Tinigaw | 11.7063 | 122.364 | U | 3370 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTAKR0006 | PTCI/MIDC | 11.7102 | 122.3667 | 0.52 | Terrestrial Optical Fiber Drop | 1.03 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2692 | 3 | 692 | 2692 | 0305407029 | Region III (Central Luzon) | Pampanga | Guagua | Santa Ines | 14.9804 | 120.649 | R | 4159 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01639-B07 | PTCI/MIDC | 14.9819 | 120.6451 | 0.45 | Terrestrial Optical Fiber Drop | 2.25 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2693 | 3 | 693 | 2693 | 0702205041 | Region VII (Central Visayas) | Cebu | Argao | Talo-ot | 9.9543 | 123.6171 | R | 4329 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0006 | PTCI/MIDC | 9.9557 | 123.6173 | 0.15 | Terrestrial Optical Fiber Drop | 6.52 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2694 | 3 | 694 | 2694 | 0331400020 | Region III (Central Luzon) | Zambales | City of Olongapo | West Tapinac | 14.8353 | 120.2816 | U | 7305 | 1974 | 592 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01123 | Edgepoint | 14.85 | 120.2999 | 0.25 | Terrestrial Optical Fiber Drop | 0.2 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2695 | 3 | 695 | 2695 | 0403422007 | Region IV-A (CALABARZON) | Laguna | Pila | Labuin | 14.246 | 121.3683 | U | 6312 | 1912 | 574 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040225 | FTAP Globe | 14.2383 | 121.3616 | 1.12 | Terrestrial Optical Fiber Drop | 1.03 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2696 | 3 | 696 | 2696 | 0103303007 | Region I (Ilocos Region) | La Union | Bacnotan | Baroro | 16.7102 | 120.3405 | U | 2936 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-LUN-00274 | Edgepoint | 16.7069 | 120.34 | 0.37 | Terrestrial Optical Fiber Drop | 1.38 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2697 | 3 | 697 | 2697 | 0403424064 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | San Roque | 14.071 | 121.3123 | U | 3632 | 1100 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01993-C08 | PTCI/MIDC | 14.0703 | 121.3069 | 0.59 | Terrestrial Optical Fiber Drop | 1.2 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2698 | 3 | 698 | 2698 | 0203114033 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Calamagui 1st | 17.1378 | 121.8686 | U | 4059 | 1068 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0014 | PTCI/MIDC | 17.1409 | 121.8693 | 0.36 | Terrestrial Optical Fiber Drop | 2.27 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2699 | 3 | 699 | 2699 | 0305407021 | Region III (Central Luzon) | Pampanga | Guagua | San Nicolas 2nd | 14.9748 | 120.6469 | U | 3475 | 868 | 260 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00964 | Edgepoint | 14.9817 | 120.6451 | 0.79 | Terrestrial Optical Fiber Drop | 1.88 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2700 | 3 | 700 | 2700 | 0401017005 | Region IV-A (CALABARZON) | Batangas | Malvar | Luta Del Norte | 14.0388 | 121.158 | R | 4522 | 1256 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040367 | FTAP Globe | 14.0327 | 121.158 | 0.68 | Terrestrial Optical Fiber Drop | 2.09 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2701 | 3 | 701 | 2701 | 0501606024 | Region V (Bicol Region) | Camarines Norte | Labo | Exciban | 14.1843 | 122.6564 | R | 3671 | 917 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050013 | FTAP Globe | 14.1823 | 122.6602 | 0.47 | Terrestrial Optical Fiber Drop | 3.32 | 1.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2702 | 3 | 702 | 2702 | 0702243027 | Region VII (Central Visayas) | Cebu | San Remigio | Victoria | 10.9362 | 123.9109 | R | 2258 | 594 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0157 | PTCI/MIDC | 10.9044 | 123.895 | 3.94 | Terrestrial Optical Fiber Drop | 1.77 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2703 | 3 | 703 | 2703 | 0803722011 | Region VIII (Eastern Visayas) | Leyte | Isabel | Libertad | 10.9081 | 124.4521 | U | 5324 | 1401 | 420 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0024 | PTCI/MIDC | 10.8906 | 124.4556 | 1.98 | Terrestrial Optical Fiber Drop | 2.46 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2704 | 3 | 704 | 2704 | 0105538021 | Region I (Ilocos Region) | Pangasinan | Santa Barbara | Poblacion Norte | 16.0007 | 120.4021 | R | 4714 | 1309 | 393 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00469 | Edgepoint | 16.0013 | 120.4046 | 0.28 | Terrestrial Optical Fiber Drop | 2.18 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2705 | 3 | 705 | 2705 | 1401112011 | Cordillera Administrative Region (CAR) | Benguet | Sablan | Poblacion | 16.5022 | 120.4757 | R | 2816 | 804 | 241 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-BEN-00320 | Edgepoint | 16.5044 | 120.4848 | 1 | Terrestrial Optical Fiber Drop | 1.16 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2706 | 3 | 706 | 2706 | 0305413024 | Region III (Central Luzon) | Pampanga | Mexico | Parian | 15.0594 | 120.717 | U | 6107 | 1526 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1617 | FTAP Smart | 15.0585 | 120.7182 | 0.16 | Terrestrial Optical Fiber Drop | 2.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2707 | 3 | 707 | 2707 | 0405619039 | Region IV-A (CALABARZON) | Quezon | Gumaca | Rosario | 13.9301 | 122.0913 | U | 5782 | 1521 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTQZG0020 | PTCI/MIDC | 13.9258 | 122.0933 | 0.52 | Terrestrial Optical Fiber Drop | 1.95 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2708 | 3 | 708 | 2708 | 1102411005 | Region XI (Davao Region) | Davao del Sur | Padada | Lower Limonzo | 6.6446 | 125.3458 | R | 1769 | 520 | 156 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110530 | FTAP Globe | 6.6448 | 125.3465 | 0.08 | Terrestrial Optical Fiber Drop | 1.02 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2709 | 3 | 709 | 2709 | 0806407028 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Ibarra | 10.1283 | 124.8783 | R | 4395 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 1.92 | Terrestrial Optical Fiber Drop | 2.31 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2710 | 3 | 710 | 2710 | 0305413026 | Region III (Central Luzon) | Pampanga | Mexico | San Antonio | 15.0636 | 120.7241 | U | 6110 | 1527 | 458 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030482 | FTAP Globe | 15.0664 | 120.7233 | 0.32 | Terrestrial Optical Fiber Drop | 1.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2711 | 3 | 711 | 2711 | 0501720012 | Region V (Bicol Region) | Camarines Sur | Magarao | San Pantaleon | 13.6623 | 123.1896 | R | 1235 | 294 | 88 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0004 | PTCI/MIDC | 13.6631 | 123.1918 | 0.23 | Terrestrial Optical Fiber Drop | 1.14 | 0.12 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2712 | 3 | 712 | 2712 | 0402111004 | Region IV-A (CALABARZON) | Cavite | Kawit | Marulas | 14.4436 | 120.9104 | R | 4054 | 1192 | 358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01875-C08 | PTCI/MIDC | 14.4494 | 120.9205 | 0.72 | Terrestrial Optical Fiber Drop | 3.33 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2713 | 3 | 713 | 2713 | 0501725013 | Region V (Bicol Region) | Camarines Sur | Ocampo | Pinit | 13.5648 | 123.4116 | R | 4259 | 1014 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050100 | FTAP Globe | 13.5784 | 123.4267 | 2.23 | Terrestrial Optical Fiber Drop | 3.95 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2714 | 3 | 714 | 2714 | 0402109051 | Region IV-A (CALABARZON) | Cavite | City of Imus | Bucandala IV | 14.4048 | 120.9263 | U | 5634 | 1657 | 497 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01926-C08 | PTCI/MIDC | 14.4259 | 120.8894 | 0.81 | Terrestrial Optical Fiber Drop | 1.57 | 4.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2715 | 3 | 715 | 2715 | 0300804033 | Region III (Central Luzon) | Bataan | Dinalupihan | San Benito | 14.848 | 120.4248 | R | 3085 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1508 | FTAP Smart | 14.8488 | 120.4252 | 0.09 | Terrestrial Optical Fiber Drop | 2.95 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2716 | 3 | 716 | 2716 | 0402111019 | Region IV-A (CALABARZON) | Cavite | Kawit | Samala-Marquez | 14.4437 | 120.91 | U | 6789 | 1996 | 599 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01920-C08 | PTCI/MIDC | 14.452 | 120.9266 | 0.38 | Terrestrial Optical Fiber Drop | 3.31 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2717 | 3 | 717 | 2717 | 0304904013 | Region III (Central Luzon) | Nueva Ecija | Cabiao | San Fernando Norte | 15.2763 | 120.8766 | R | 4166 | 1190 | 357 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00783 | Edgepoint | 15.2714 | 120.8765 | 0.55 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2718 | 3 | 718 | 2718 | 0304928026 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Gomez | 15.416 | 120.9374 | R | 2023 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01493-B07 | PTCI/MIDC | 15.4207 | 120.9403 | 0.6 | Terrestrial Optical Fiber Drop | 0.99 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2719 | 3 | 719 | 2719 | 0402111016 | Region IV-A (CALABARZON) | Cavite | Kawit | Congbalay-Legaspi | 14.4513 | 120.9226 | R | 4597 | 1352 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01875-C08 | PTCI/MIDC | 14.4494 | 120.9205 | 0.3 | Terrestrial Optical Fiber Drop | 2.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2720 | 3 | 720 | 2720 | 0305409012 | Region III (Central Luzon) | Pampanga | Mabalacat City | Mabiga | 15.2121 | 120.58 | U | 25509 | 6377 | 1913 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01602-B07 | PTCI/MIDC | 15.2096 | 120.5783 | 0.33 | Terrestrial Optical Fiber Drop | 1.27 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2721 | 3 | 721 | 2721 | 0803708016 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Caridad | 10.6462 | 124.8215 | R | 4321 | 1137 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLEG0012 | PTCI/MIDC | 10.8334 | 124.7546 | 0.22 | Terrestrial Optical Fiber Drop | 4.28 | 1.66 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2722 | 3 | 722 | 2722 | 0702218009 | Region VII (Central Visayas) | Cebu | Compostela | Estaca | 10.4375 | 124.0071 | U | 7394 | 1945 | 584 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0060 | PTCI/MIDC | 10.437 | 124.0045 | 0.29 | Terrestrial Optical Fiber Drop | 1.72 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2723 | 3 | 723 | 2723 | 0803739016 | Region VIII (Eastern Visayas) | Leyte | Palo | Guindapunan | 11.167 | 124.9983 | U | 7916 | 2083 | 625 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 1.42 | Terrestrial Optical Fiber Drop | 1.91 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2724 | 3 | 724 | 2724 | 0301423022 | Region III (Central Luzon) | Bulacan | Santa Maria | Sta. Cruz | 14.8421 | 120.9563 | U | 11878 | 3393 | 1018 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01111-B07 | PTCI/MIDC | 14.8361 | 120.9745 | 0.03 | Terrestrial Optical Fiber Drop | 2.41 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2725 | 3 | 725 | 2725 | 1004313004 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Kabulawan | 8.8166 | 124.7911 | R | 3661 | 938 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0056 | PTCI/MIDC | 8.8065 | 124.7886 | 1.16 | Terrestrial Optical Fiber Drop | 1.28 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2726 | 3 | 726 | 2726 | 1030500053 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Lapasan | 8.4814 | 124.6638 | U | 39946 | 11096 | 3329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0028 | PTCI/MIDC | 8.4862 | 124.6626 | 0.55 | Terrestrial Optical Fiber Drop | 1.24 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2727 | 3 | 727 | 2727 | 1204704039 | Region XII (SOCCSKSARGEN) | Cotabato | City of Kidapawan | Sudapin | 7.019 | 125.0935 | U | 9293 | 2445 | 734 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNCG0061 | PTCI/MIDC | 7.0176 | 125.0944 | 0.18 | Terrestrial Optical Fiber Drop | 1.25 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2728 | 3 | 728 | 2728 | 1705110003 | MIMAROPA Region | Occidental Mindoro | San Jose | Bagong Sikat | 12.3672 | 121.0631 | U | 8146 | 2088 | 626 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S6930 | FTAP Smart | 12.3704 | 121.0662 | 0.49 | Terrestrial Optical Fiber Drop | 1.83 | 0.18 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2729 | 3 | 729 | 2729 | 0304904006 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Maligaya | 15.2492 | 120.8599 | U | 3018 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.09 | Terrestrial Optical Fiber Drop | 1.67 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2730 | 3 | 730 | 2730 | 0103317013 | Region I (Ilocos Region) | La Union | Santo Tomas | Lomboy | 16.2747 | 120.3936 | R | 1542 | 416 | 125 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-LUN-00374 | Edgepoint | 16.2818 | 120.3824 | 0.59 | Terrestrial Optical Fiber Drop | 2 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2731 | 3 | 731 | 2731 | 0405630026 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Talipan | 13.9631 | 121.6546 | U | 6711 | 1766 | 530 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040413 | FTAP Globe | 13.9599 | 121.6568 | 0.42 | Terrestrial Optical Fiber Drop | 1.21 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2732 | 3 | 732 | 2732 | 0403421001 | Region IV-A (CALABARZON) | Laguna | Pangil | Balian | 14.3943 | 121.4749 | U | 7054 | 2137 | 641 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040124 | FTAP Globe | 14.4013 | 121.4743 | 0.79 | Terrestrial Optical Fiber Drop | 1.71 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2733 | 3 | 733 | 2733 | 0601910013 | Region VI (Western Visayas) | Capiz | Panitan | Cogon | 11.4594 | 122.8175 | R | 3953 | 1040 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060102 | FTAP BTS | 11.4732 | 122.8116 | 1.66 | Terrestrial Optical Fiber Drop | 2.72 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2734 | 3 | 734 | 2734 | 1030500047 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Dansolihon | 8.4682 | 124.6315 | U | 6319 | 1755 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100083 | FTAP BTS | 8.3287 | 124.5967 | 3.13 | Terrestrial Optical Fiber Drop | 1 | 1.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2735 | 3 | 735 | 2735 | 0501611001 | Region V (Bicol Region) | Camarines Norte | Talisay | Binanuaan | 14.1284 | 122.9365 | R | 2809 | 702 | 211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03030-C10 | PTCI/MIDC | 14.1218 | 122.9428 | 1 | Terrestrial Optical Fiber Drop | 2.41 | 0.8 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2736 | 3 | 736 | 2736 | 0402106064 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | Sampaloc V | 14.28 | 120.9649 | R | 3423 | 1006 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.54 | Terrestrial Optical Fiber Drop | 2.33 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2737 | 3 | 737 | 2737 | 0203126030 | Region II (Cagayan Valley) | Isabela | Roxas | Muñoz West | 17.1579 | 121.6114 | R | 3827 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00171 | Edgepoint | 17.1573 | 121.6124 | 0.13 | Terrestrial Optical Fiber Drop | 2.68 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2738 | 3 | 738 | 2738 | 0403403019 | Region IV-A (CALABARZON) | Laguna | City of Biñan | San Antonio | 14.3364 | 121.0882 | U | 39641 | 12012 | 3604 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02537-C08 | PTCI/MIDC | 14.3337 | 121.0825 | 0.68 | Terrestrial Optical Fiber Drop | 1.36 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2739 | 3 | 739 | 2739 | 0105533024 | Region I (Ilocos Region) | Pangasinan | San Fabian | Tempra-Guilig | 16.1265 | 120.4087 | R | 3955 | 1098 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 0.32 | Terrestrial Optical Fiber Drop | 1.55 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2740 | 3 | 740 | 2740 | 0501724003 | Region V (Bicol Region) | Camarines Sur | City of Naga | Bagumbayan Sur | 13.6333 | 123.1858 | U | 7848 | 1868 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050078 | FTAP Globe | 13.631 | 123.1834 | 0.36 | Terrestrial Optical Fiber Drop | 1.52 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2741 | 3 | 741 | 2741 | 0331400005 | Region III (Central Luzon) | Zambales | City of Olongapo | East Bajac-bajac | 14.8367 | 120.29 | U | 19729 | 5332 | 1600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ZMB-01146 | Edgepoint | 14.8379 | 120.2895 | 0.14 | Terrestrial Optical Fiber Drop | 1.03 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2742 | 3 | 742 | 2742 | 1400101006 | Cordillera Administrative Region (CAR) | Abra | Bangued | Calaba | 17.6133 | 120.6191 | U | 4784 | 1258 | 377 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00865-B05 | PTCI/MIDC | 17.6127 | 120.6165 | 0.28 | Terrestrial Optical Fiber Drop | 2.29 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2743 | 3 | 743 | 2743 | 0304908006 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Mangino | 15.3112 | 120.9623 | U | 14084 | 4024 | 1207 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-02508 | Edgepoint | 15.3146 | 120.9576 | 0.64 | Terrestrial Optical Fiber Drop | 1.82 | 0.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2744 | 3 | 744 | 2744 | 0500506035 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 37 - Bitano | 13.1492 | 123.7448 | U | 7825 | 1908 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03399-C10 | PTCI/MIDC | 13.1487 | 123.7436 | 0.14 | Terrestrial Optical Fiber Drop | 1.34 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2745 | 3 | 745 | 2745 | 1004301006 | Region X (Northern Mindanao) | Misamis Oriental | Alubijid | Loguilo | 8.5759 | 124.4941 | R | 3582 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100121 | FTAP Globe | 8.5721 | 124.5078 | 1.56 | Terrestrial Optical Fiber Drop | 2.19 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2746 | 3 | 746 | 2746 | 1705320001 | MIMAROPA Region | Palawan | Taytay | Abongan | 10.679 | 119.4527 | R | 5497 | 1409 | 423 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170219 | FTAP Globe | 10.6697 | 119.4514 | 1.04 | Terrestrial Optical Fiber Drop | 2.87 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2747 | 3 | 747 | 2747 | 0306910004 | Region III (Central Luzon) | Tarlac | Paniqui | Apulid | 15.6832 | 120.5816 | R | 4025 | 1032 | 310 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00603 | Edgepoint | 15.6812 | 120.5835 | 0.3 | Terrestrial Optical Fiber Drop | 1.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2748 | 3 | 748 | 2748 | 0702227005 | Region VII (Central Visayas) | Cebu | Liloan | Jubay | 10.4188 | 123.9959 | U | 15241 | 4010 | 1203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0104 | PTCI/MIDC | 10.4246 | 123.9957 | 0.64 | Terrestrial Optical Fiber Drop | 0.33 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2749 | 3 | 749 | 2749 | 0305409021 | Region III (Central Luzon) | Pampanga | Mabalacat City | San Francisco | 15.2165 | 120.5788 | U | 15556 | 3889 | 1167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02973-B07 | PTCI/MIDC | 15.219 | 120.5769 | 0.35 | Terrestrial Optical Fiber Drop | 1.78 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2750 | 3 | 750 | 2750 | 0702246004 | Region VII (Central Visayas) | Cebu | Sibonga | Bahay | 9.9911 | 123.6121 | U | 5774 | 1519 | 456 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0244 | PTCI/MIDC | 9.9858 | 123.6163 | 0.74 | Terrestrial Optical Fiber Drop | 2.54 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2751 | 3 | 751 | 2751 | 1004307016 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Taytay | 8.5424 | 124.5408 | R | 4450 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0045 | PTCI/MIDC | 8.5357 | 124.5477 | 1.06 | Terrestrial Optical Fiber Drop | 2.46 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2752 | 3 | 752 | 2752 | 0731300008 | Region VII (Central Visayas) | Cebu | City of Mandaue | Casili | 10.3791 | 123.9353 | U | 5408 | 1545 | 464 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070327 | FTAP Globe | 10.3761 | 123.9347 | 0.34 | Terrestrial Optical Fiber Drop | 2.02 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2753 | 3 | 753 | 2753 | 1004309007 | Region X (Northern Mindanao) | Misamis Oriental | Gitagum | Matangad | 8.5752 | 124.372 | R | 4152 | 1064 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100118 | FTAP Globe | 8.5922 | 124.3873 | 2.53 | Terrestrial Optical Fiber Drop | 2.55 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2754 | 3 | 754 | 2754 | 0500503031 | Region V (Bicol Region) | Albay | Daraga | Malabog | 13.172 | 123.6851 | R | 4458 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050171 | FTAP Globe | 13.1731 | 123.6842 | 0.16 | Terrestrial Optical Fiber Drop | 1.97 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2755 | 3 | 755 | 2755 | 0702219003 | Region VII (Central Visayas) | Cebu | Consolacion | Casili | 10.3791 | 123.9353 | U | 19021 | 5005 | 1502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070327 | FTAP Globe | 10.3761 | 123.9347 | 0.34 | Terrestrial Optical Fiber Drop | 2.02 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2756 | 3 | 756 | 2756 | 0300810021 | Region III (Central Luzon) | Bataan | Orion | Sabatan | 14.6141 | 120.5686 | U | 3931 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03328-B07 | PTCI/MIDC | 14.6114 | 120.5701 | 0.34 | Terrestrial Optical Fiber Drop | 1.14 | 1.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2757 | 3 | 757 | 2757 | 0501731012 | Region V (Bicol Region) | Camarines Sur | Sagñay | Nato | 13.6096 | 123.5359 | R | 4071 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050089 | FTAP Globe | 13.6069 | 123.5336 | 0.39 | Terrestrial Optical Fiber Drop | 1.82 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2758 | 3 | 758 | 2758 | 0806407041 | Region VIII (Eastern Visayas) | Southern Leyte | City of Maasin | Maria Clara | 10.1215 | 124.8929 | R | 2433 | 593 | 178 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 0.22 | Terrestrial Optical Fiber Drop | 1.32 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2759 | 3 | 759 | 2759 | 0702206011 | Region VII (Central Visayas) | Cebu | Asturias | Langub | 10.5811 | 123.7335 | R | 4073 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070318 | FTAP Globe | 10.5306 | 123.7187 | 5.85 | Terrestrial Optical Fiber Drop | 8.28 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2760 | 3 | 760 | 2760 | 0501736021 | Region V (Bicol Region) | Camarines Sur | Tigaon | San Rafael | 13.6606 | 123.5017 | R | 4172 | 993 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050074 | FTAP Globe | 13.6378 | 123.4949 | 2.64 | Terrestrial Optical Fiber Drop | 3.4 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2761 | 3 | 761 | 2761 | 0405809003 | Region IV-A (CALABARZON) | Rizal | Morong | Lagundi | 14.5274 | 121.2544 | U | 9646 | 2679 | 804 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01851 | Edgepoint | 14.529 | 121.254 | 0.17 | Terrestrial Optical Fiber Drop | 1.37 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2762 | 3 | 762 | 2762 | 0730600027 | Region VII (Central Visayas) | Cebu | City of Cebu | Duljo | 10.2949 | 123.8857 | U | 15870 | 4959 | 1488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0026 | PTCI/MIDC | 10.2919 | 123.8848 | 0.34 | Terrestrial Optical Fiber Drop | 1.61 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2763 | 3 | 763 | 2763 | 0304903073 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | San Juan Pob. | 15.4718 | 120.9582 | U | 9561 | 2731 | 819 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-00717 | Edgepoint | 15.4684 | 120.9565 | 0.41 | Terrestrial Optical Fiber Drop | 1.15 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2764 | 3 | 764 | 2764 | 0604504001 | Region VI (Western Visayas) | Negros Occidental | City of Cadiz | Andres Bonifacio | 10.9041 | 123.2305 | U | 6506 | 1758 | 527 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTNOR0024 | PTCI/MIDC | 10.6784 | 122.9604 | 0.86 | Terrestrial Optical Fiber Drop | 12.19 | 5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2765 | 3 | 765 | 2765 | 0506206019 | Region V (Bicol Region) | Sorsogon | Castilla | Milagrosa | 12.9792 | 123.8517 | R | 1785 | 446 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050205 | FTAP Globe | 12.9754 | 123.8474 | 0.63 | Terrestrial Optical Fiber Drop | 1.1 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2766 | 3 | 766 | 2766 | 0402118019 | Region IV-A (CALABARZON) | Cavite | Silang | Lalaan I | 14.1821 | 120.963 | U | 6436 | 1892 | 568 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02158-C08 | PTCI/MIDC | 14.1794 | 120.9616 | 0.33 | Terrestrial Optical Fiber Drop | 2.28 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2767 | 3 | 767 | 2767 | 0702247010 | Region VII (Central Visayas) | Cebu | Sogod | Damolog | 10.7691 | 124.0037 | R | 3987 | 1049 | 315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070311 | FTAP Globe | 10.7522 | 124.0024 | 1.88 | Terrestrial Optical Fiber Drop | 1.91 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2768 | 3 | 768 | 2768 | 0401006023 | Region IV-A (CALABARZON) | Batangas | Bauan | Manghinao Uno | 13.8027 | 120.9948 | U | 2821 | 783 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1334 | FTAP Smart | 13.7999 | 120.9945 | 0.32 | Terrestrial Optical Fiber Drop | 1.26 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2769 | 3 | 769 | 2769 | 0301421020 | Region III (Central Luzon) | Bulacan | San Miguel | Camias | 15.1636 | 120.9731 | U | 8942 | 2554 | 766 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030449 | FTAP Globe | 15.1671 | 120.9765 | 0.53 | Terrestrial Optical Fiber Drop | 1.05 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2770 | 3 | 770 | 2770 | 1705211003 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Dulangan | 13.4677 | 120.9748 | R | 3978 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMRG0009 | PTCI/MIDC | 13.4655 | 120.9692 | 0.65 | Terrestrial Optical Fiber Drop | 4.11 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2771 | 3 | 771 | 2771 | 0403405020 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lecheria | 14.2033 | 121.1614 | U | 11956 | 3623 | 1087 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02120-C08 | PTCI/MIDC | 14.2013 | 121.1654 | 0.48 | Terrestrial Optical Fiber Drop | 1.78 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2772 | 3 | 772 | 2772 | 0205005003 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Bonfal West | 16.4984 | 121.1664 | U | 5944 | 1564 | 469 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-00321 | Edgepoint | 16.4983 | 121.1676 | 0.13 | Terrestrial Optical Fiber Drop | 2.39 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2773 | 3 | 773 | 2773 | 0401007033 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Puting Bato West | 13.9228 | 120.8339 | U | 3685 | 1023 | 307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040482 | FTAP Globe | 13.9204 | 120.8358 | 0.35 | Terrestrial Optical Fiber Drop | 2.37 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2774 | 3 | 774 | 2774 | 0403425019 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | United Better Living | 14.3412 | 121.0438 | U | 6801 | 2060 | 618 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02621-C08 | PTCI/MIDC | 14.3435 | 121.0576 | 0.48 | Terrestrial Optical Fiber Drop | 0.52 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2775 | 3 | 775 | 2775 | 1606808002 | Region XIII (Caraga) | Surigao del Sur | Cortes | Burgos | 9.2547 | 126.1733 | R | 3668 | 894 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130061 | FTAP Globe | 9.1425 | 126.1699 | 12.48 | Terrestrial Optical Fiber Drop | 19.94 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2776 | 3 | 776 | 2776 | 0500506046 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 41 - Bogtong | 13.1611 | 123.7331 | U | 5099 | 1243 | 373 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050174 | FTAP Globe | 13.1521 | 123.7315 | 1.01 | Terrestrial Optical Fiber Drop | 2.6 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2777 | 3 | 777 | 2777 | 0701242012 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion III | 9.639 | 123.8642 | U | 5103 | 1275 | 383 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBOG0034 | PTCI/MIDC | 9.6382 | 123.8698 | 0.61 | Terrestrial Optical Fiber Drop | 1.24 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2778 | 3 | 778 | 2778 | 0702210001 | Region VII (Central Visayas) | Cebu | Barili | Azucena | 10.1271 | 123.5216 | R | 2266 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070062 | FTAP BTS | 10.116 | 123.5147 | 1.44 | Terrestrial Optical Fiber Drop | 1.98 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2779 | 3 | 779 | 2779 | 1003507010 | Region X (Northern Mindanao) | Lanao del Norte | Kauswagan | Poblacion | 8.1906 | 124.0869 | R | 4074 | 970 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0015 | PTCI/MIDC | 8.1921 | 124.0889 | 0.27 | Terrestrial Optical Fiber Drop | 17.41 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2780 | 3 | 780 | 2780 | 0401019048 | Region IV-A (CALABARZON) | Batangas | Nasugbu | Wawa | 14.0812 | 120.6246 | U | 15886 | 4412 | 1324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1364 | FTAP Smart | 14.0832 | 120.6249 | 0.22 | Terrestrial Optical Fiber Drop | 1.54 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2781 | 3 | 781 | 2781 | 0402116011 | Region IV-A (CALABARZON) | Cavite | Noveleta | San Antonio II | 14.4186 | 120.8858 | R | 2182 | 641 | 192 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03036-C08 | PTCI/MIDC | 14.4147 | 120.8819 | 0.6 | Terrestrial Optical Fiber Drop | 1.25 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2782 | 3 | 782 | 2782 | 0105521004 | Region I (Ilocos Region) | Pangasinan | Labrador | Laois | 16.0364 | 120.1381 | R | 2855 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01750-B07 | PTCI/MIDC | 16.0291 | 120.1409 | 0.86 | Terrestrial Optical Fiber Drop | 2.33 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2783 | 3 | 783 | 2783 | 0803708025 | Region VIII (Eastern Visayas) | Leyte | City of Baybay | Hipusngo | 10.6583 | 124.8098 | R | 3141 | 826 | 248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E00117-D11 | PTCI/MIDC | 10.6643 | 124.807 | 0.74 | Terrestrial Optical Fiber Drop | 2.52 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2784 | 3 | 784 | 2784 | 0105526005 | Region I (Ilocos Region) | Pangasinan | Mangaldan | Bantayan | 16.09 | 120.3897 | R | 3840 | 1066 | 320 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-02184 | Edgepoint | 16.0971 | 120.3938 | 0.9 | Terrestrial Optical Fiber Drop | 2.81 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2785 | 3 | 785 | 2785 | 0203114102 | Region II (Cagayan Valley) | Isabela | City of Ilagan | Imelda Bliss Village | 17.1219 | 121.8754 | U | 8237 | 2167 | 650 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTISG0016 | PTCI/MIDC | 17.1227 | 121.8677 | 0.83 | Terrestrial Optical Fiber Drop | 1.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2786 | 3 | 786 | 2786 | 0201502005 | Region II (Cagayan Valley) | Cagayan | Alcala | Baculod | 17.9091 | 121.6714 | R | 2380 | 610 | 183 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-CAG-00055 | Edgepoint | 17.9092 | 121.6539 | 1.85 | Terrestrial Optical Fiber Drop | 1.81 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2787 | 3 | 787 | 2787 | 0500506067 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 32 - San Roque | 13.153 | 123.7543 | U | 5759 | 1404 | 421 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03400-C10 | PTCI/MIDC | 13.1476 | 123.7504 | 0.73 | Terrestrial Optical Fiber Drop | 2.29 | 0.22 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2788 | 3 | 788 | 2788 | 1705211001 | MIMAROPA Region | Oriental Mindoro | Puerto Galera | Aninuan | 13.4973 | 120.8985 | U | 3238 | 830 | 249 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH170044 | FTAP Globe | 13.5034 | 120.9011 | 0.74 | Terrestrial Optical Fiber Drop | 1.01 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2789 | 3 | 789 | 2789 | 0405813003 | Region IV-A (CALABARZON) | Rizal | Taytay | San Isidro | 14.5728 | 121.1314 | U | 39685 | 11023 | 3307 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0145 | PTCI/MIDC | 14.5742 | 121.1329 | 0.23 | Terrestrial Optical Fiber Drop | 1.36 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2790 | 3 | 790 | 2790 | 0730600021 | Region VII (Central Visayas) | Cebu | City of Cebu | Carreta | 10.3075 | 123.9088 | U | 11412 | 3566 | 1070 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.7 | Terrestrial Optical Fiber Drop | 1.3 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2791 | 3 | 791 | 2791 | 1130700153 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 20-B | 7.0866 | 125.613 | U | 5129 | 1508 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSR0035 | PTCI/MIDC | 7.0835 | 125.6125 | 0.35 | Terrestrial Optical Fiber Drop | 1.01 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2792 | 3 | 792 | 2792 | 0501715016 | Region V (Bicol Region) | Camarines Sur | Goa | Matacla | 13.6879 | 123.4956 | U | 5571 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAS-02602 | Edgepoint | 13.6957 | 123.4931 | 0.9 | Terrestrial Optical Fiber Drop | 1.14 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2793 | 3 | 793 | 2793 | 0401014009 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Balintawak | 13.954 | 121.161 | U | 19850 | 5513 | 1654 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040430 | FTAP Globe | 13.9477 | 121.1559 | 0.89 | Terrestrial Optical Fiber Drop | 1.24 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2794 | 3 | 794 | 2794 | 0403405001 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Bagong Kalsada | 14.2008 | 121.1403 | U | 4266 | 1292 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.24 | Terrestrial Optical Fiber Drop | 0.75 | 0.04 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2795 | 3 | 795 | 2795 | 1600306023 | Region XIII (Caraga) | Agusan del Sur | Prosperidad | San Jose | 8.6931 | 125.8352 | R | 2875 | 737 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130084 | FTAP Globe | 8.661 | 125.8901 | 7.01 | Terrestrial Optical Fiber Drop | 1.67 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2796 | 3 | 796 | 2796 | 0103312003 | Region I (Ilocos Region) | La Union | Pugo | Cares | 16.3208 | 120.4686 | R | 2717 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01397-B05 | PTCI/MIDC | 16.3194 | 120.4687 | 0.15 | Terrestrial Optical Fiber Drop | 1.45 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2797 | 3 | 797 | 2797 | 1001314005 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | Damilag | 8.3685 | 124.8627 | U | 18241 | 4800 | 1440 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBKG0024 | PTCI/MIDC | 8.3656 | 124.8616 | 0.89 | Terrestrial Optical Fiber Drop | 1.93 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2798 | 3 | 798 | 2798 | 0306905030 | Region III (Central Luzon) | Tarlac | Concepcion | San Francisco | 15.311 | 120.6424 | U | 9208 | 2361 | 708 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-02470 | Edgepoint | 15.3132 | 120.6411 | 0.28 | Terrestrial Optical Fiber Drop | 1.9 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2799 | 3 | 799 | 2799 | 1004308068 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Santiago | 8.8285 | 125.1299 | R | 3582 | 918 | 275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0048 | PTCI/MIDC | 8.83 | 125.1208 | 1.01 | Terrestrial Optical Fiber Drop | 2.76 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2800 | 3 | 800 | 2800 | 0103314029 | Region I (Ilocos Region) | La Union | City of San Fernando | Langcuas | 16.6151 | 120.3357 | R | 2067 | 558 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH010097 | FTAP Globe | 16.5923 | 120.3211 | 0.42 | Terrestrial Optical Fiber Drop | 2.3 | 1.99 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2801 | 3 | 801 | 2801 | 0306905001 | Region III (Central Luzon) | Tarlac | Concepcion | Alfonso | 15.3299 | 120.6389 | U | 9944 | 2549 | 765 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-TAR-00761 | Edgepoint | 15.3331 | 120.625 | 1.53 | Terrestrial Optical Fiber Drop | 1.62 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2802 | 3 | 802 | 2802 | 0305407017 | Region III (Central Luzon) | Pampanga | Guagua | San Juan Nepomuceno | 14.9791 | 120.6415 | U | 7045 | 1761 | 528 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00964 | Edgepoint | 14.9817 | 120.6451 | 0.49 | Terrestrial Optical Fiber Drop | 1.45 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2803 | 3 | 803 | 2803 | 0702207016 | Region VII (Central Visayas) | Cebu | Badian | Malhiao | 9.8855 | 123.4039 | R | 3876 | 1020 | 306 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0131 | PTCI/MIDC | 9.9532 | 123.3997 | 7.54 | Terrestrial Optical Fiber Drop | 6 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2804 | 3 | 804 | 2804 | 0403425011 | Region IV-A (CALABARZON) | Laguna | City of San Pedro | Poblacion | 14.3638 | 121.058 | U | 6326 | 1916 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S4284 | FTAP Smart | 14.364 | 121.0585 | 0.06 | Terrestrial Optical Fiber Drop | 1.71 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2805 | 3 | 805 | 2805 | 0702222003 | Region VII (Central Visayas) | Cebu | Dalaguete | Balud | 9.7533 | 123.5217 | R | 3756 | 988 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070061 | FTAP BTS | 9.7495 | 123.5175 | 0.62 | Terrestrial Optical Fiber Drop | 1.48 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2806 | 3 | 806 | 2806 | 0506216008 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Bitan-o/Dalipay | 13.1458 | 123.7456 | U | 3374 | 843 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03399-C10 | PTCI/MIDC | 13.1487 | 123.7436 | 0.39 | Terrestrial Optical Fiber Drop | 1.06 | 0.23 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2807 | 3 | 807 | 2807 | 0300806006 | Region III (Central Luzon) | Bataan | Limay | Landing | 14.5514 | 120.5971 | R | 3333 | 925 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-02566 | Edgepoint | 14.5403 | 120.5882 | 0.67 | Terrestrial Optical Fiber Drop | 2.52 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2808 | 3 | 808 | 2808 | 0405811002 | Region IV-A (CALABARZON) | Rizal | San Mateo | Dulong Bayan 1 | 14.7002 | 121.1226 | U | 5006 | 1390 | 417 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00706-A04 | PTCI/MIDC | 14.6991 | 121.1241 | 0.2 | Terrestrial Optical Fiber Drop | 1.64 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2809 | 3 | 809 | 2809 | 0401021027 | Region IV-A (CALABARZON) | Batangas | Rosario | Natu | 13.8404 | 121.2692 | R | 2905 | 806 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040550 | FTAP Globe | 13.8351 | 121.2595 | 1.2 | Terrestrial Optical Fiber Drop | 2.82 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2810 | 3 | 810 | 2810 | 0501606008 | Region V (Bicol Region) | Camarines Norte | Labo | Bautista | 14.1445 | 122.8456 | R | 2936 | 734 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03390-C10 | PTCI/MIDC | 14.1462 | 122.844 | 0.25 | Terrestrial Optical Fiber Drop | 1.5 | 1.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2811 | 3 | 811 | 2811 | 0305416023 | Region III (Central Luzon) | Pampanga | City of San Fernando | Saguin | 15.0958 | 120.6221 | U | 8760 | 2190 | 657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | 4916 | FTAP Smart | 15.096 | 120.6241 | 0.21 | Terrestrial Optical Fiber Drop | 2.38 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2812 | 3 | 812 | 2812 | 0307113018 | Region III (Central Luzon) | Zambales | Santa Cruz | Pagatpat | 15.7816 | 119.9006 | R | 3733 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0005 | PTCI/MIDC | 15.7825 | 119.9027 | 0.24 | Terrestrial Optical Fiber Drop | 1.8 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2813 | 3 | 813 | 2813 | 0401022007 | Region IV-A (CALABARZON) | Batangas | San Jose | Banaybanay I | 13.8977 | 121.1069 | U | 6560 | 1822 | 547 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1351 | FTAP Smart | 13.8931 | 121.0981 | 1.08 | Terrestrial Optical Fiber Drop | 2.07 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2814 | 3 | 814 | 2814 | 1003505010 | Region X (Northern Mindanao) | Lanao del Norte | Kapatagan | Butadon | 7.885 | 123.7465 | R | 4433 | 1055 | 317 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0040 | PTCI/MIDC | 7.8874 | 123.7416 | 0.6 | Terrestrial Optical Fiber Drop | 18.5 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2815 | 3 | 815 | 2815 | 0506216037 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Tugos | 12.9713 | 123.9885 | R | 3273 | 818 | 245 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 1.04 | Terrestrial Optical Fiber Drop | 1.62 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2816 | 3 | 816 | 2816 | 0304903023 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Kapitan Pepe | 15.4902 | 120.9705 | U | 5226 | 1493 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030381 | FTAP Globe | 15.486 | 120.9751 | 0.28 | Terrestrial Optical Fiber Drop | 1.37 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2817 | 3 | 817 | 2817 | 0203108012 | Region II (Cagayan Valley) | Isabela | City of Cauayan | Cabaruan | 16.9542 | 121.7694 | U | 8540 | 2247 | 674 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0013 | PTCI/MIDC | 16.9538 | 121.7732 | 0.41 | Terrestrial Optical Fiber Drop | 2.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2818 | 3 | 818 | 2818 | 0401007022 | Region IV-A (CALABARZON) | Batangas | City of Calaca | Lumbang Calzada | 13.9271 | 120.8253 | R | 3336 | 926 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040472 | FTAP Globe | 13.9244 | 120.8212 | 0.54 | Terrestrial Optical Fiber Drop | 1.41 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2819 | 3 | 819 | 2819 | 0405808002 | Region IV-A (CALABARZON) | Rizal | Rodriguez | Burgos | 14.7194 | 121.1393 | U | 49247 | 13679 | 4104 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01291 | Edgepoint | 14.7179 | 121.1384 | 0.19 | Terrestrial Optical Fiber Drop | 1.19 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2820 | 3 | 820 | 2820 | 0731300013 | Region VII (Central Visayas) | Cebu | City of Mandaue | Ibabao-Estancia | 10.3353 | 123.9436 | U | 7001 | 2000 | 600 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0114 | PTCI/MIDC | 10.3327 | 123.9448 | 0.31 | Terrestrial Optical Fiber Drop | 1.36 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2821 | 3 | 821 | 2821 | 0403405033 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Paciano Rizal | 14.2168 | 121.1368 | U | 17187 | 5208 | 1562 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040243 | FTAP Globe | 14.2133 | 121.134 | 0.49 | Terrestrial Optical Fiber Drop | 1.64 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2822 | 3 | 822 | 2822 | 0702250008 | Region VII (Central Visayas) | Cebu | City of Talisay | Linao | 10.2549 | 123.8172 | U | 14807 | 3896 | 1169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0159 | PTCI/MIDC | 10.2524 | 123.8198 | 0.39 | Terrestrial Optical Fiber Drop | 2.03 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2823 | 3 | 823 | 2823 | 0702223042 | Region VII (Central Visayas) | Cebu | Danao City | Taytay | 10.5322 | 124.0275 | R | 4744 | 1248 | 374 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0081 | PTCI/MIDC | 10.5234 | 124.0277 | 0.98 | Terrestrial Optical Fiber Drop | 1.16 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2824 | 3 | 824 | 2824 | 0306902001 | Region III (Central Luzon) | Tarlac | Bamban | Anupul | 15.2937 | 120.5629 | U | 22732 | 5828 | 1748 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00776 | Edgepoint | 15.2875 | 120.5694 | 0.98 | Terrestrial Optical Fiber Drop | 1.24 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2825 | 3 | 825 | 2825 | 0300807004 | Region III (Central Luzon) | Bataan | Mariveles | Cabcaben | 14.4546 | 120.5889 | U | 8007 | 2224 | 667 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030634 | FTAP Globe | 14.448 | 120.5861 | 0.79 | Terrestrial Optical Fiber Drop | 1.82 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2826 | 3 | 826 | 2826 | 0305407013 | Region III (Central Luzon) | Pampanga | Guagua | San Antonio | 14.9648 | 120.6142 | U | 5184 | 1296 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N50 | FTAP Smart | 14.9641 | 120.6111 | 0.34 | Terrestrial Optical Fiber Drop | 1.87 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2827 | 3 | 827 | 2827 | 0300801008 | Region III (Central Luzon) | Bataan | Abucay | Omboy | 14.7186 | 120.5386 | R | 3538 | 982 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BAN-03190 | Edgepoint | 14.7182 | 120.5368 | 0.2 | Terrestrial Optical Fiber Drop | 3.76 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2828 | 3 | 828 | 2828 | 0203126021 | Region II (Cagayan Valley) | Isabela | Roxas | San Rafael | 17.1025 | 121.6136 | R | 3848 | 1012 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTISG0041 | PTCI/MIDC | 17.0989 | 121.6164 | 0.5 | Terrestrial Optical Fiber Drop | 1.5 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2829 | 3 | 829 | 2829 | 1004325014 | Region X (Northern Mindanao) | Misamis Oriental | Talisayan | San Jose | 8.9937 | 124.8888 | R | 3886 | 996 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMLG0078 | PTCI/MIDC | 8.9948 | 124.8803 | 0.94 | Terrestrial Optical Fiber Drop | 1.02 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2830 | 3 | 830 | 2830 | 1705207020 | MIMAROPA Region | Oriental Mindoro | Mansalay | Santa Teresita | 12.518 | 121.422 | U | 5449 | 1397 | 419 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170126 | FTAP Globe | 12.5234 | 121.4387 | 1.91 | Terrestrial Optical Fiber Drop | 1.88 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2831 | 3 | 831 | 2831 | 0603044043 | Region VI (Western Visayas) | Iloilo | Sara | Zerrudo | 11.2442 | 123.0246 | R | 2169 | 570 | 171 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_ILO_0004 | LDIC | 11.2454 | 123.022 | 0.32 | Terrestrial Optical Fiber Drop | 1.5 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2832 | 3 | 832 | 2832 | 0305416032 | Region III (Central Luzon) | Pampanga | City of San Fernando | Santa Lucia | 15.0249 | 120.6925 | U | 10706 | 2676 | 803 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030497 | FTAP Globe | 15.0278 | 120.6925 | 0.32 | Terrestrial Optical Fiber Drop | 2.13 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2833 | 3 | 833 | 2833 | 1208007019 | Region XII (SOCCSKSARGEN) | Sarangani | Malungon | Malandag | 6.2862 | 125.2574 | U | 15960 | 4092 | 1228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120311 | FTAP Globe | 6.2761 | 125.2567 | 1.13 | Terrestrial Optical Fiber Drop | 2.38 | 0.25 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2834 | 3 | 834 | 2834 | 0405608001 | Region IV-A (CALABARZON) | Quezon | Candelaria | Poblacion | 13.9315 | 121.4268 | U | 5761 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTQZG0002 | PTCI/MIDC | 13.9297 | 121.4287 | 0.28 | Terrestrial Optical Fiber Drop | 1.24 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2835 | 3 | 835 | 2835 | 0203113025 | Region II (Cagayan Valley) | Isabela | Gamu | Upi | 17.0693 | 121.8597 | U | 5347 | 1407 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH020067 | FTAP Globe | 17.0544 | 121.8573 | 1.68 | Terrestrial Optical Fiber Drop | 1.05 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2836 | 3 | 836 | 2836 | 0403404014 | Region IV-A (CALABARZON) | Laguna | City of Cabuyao | Sala | 14.2713 | 121.1262 | U | 11951 | 3621 | 1086 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02105-C08 | PTCI/MIDC | 14.2643 | 121.1272 | 0.79 | Terrestrial Optical Fiber Drop | 2.45 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2837 | 3 | 837 | 2837 | 0305407027 | Region III (Central Luzon) | Pampanga | Guagua | San Juan | 14.9724 | 120.6181 | R | 2905 | 726 | 218 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 0.53 | Terrestrial Optical Fiber Drop | 1.22 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2838 | 3 | 838 | 2838 | 0305408029 | Region III (Central Luzon) | Pampanga | Lubao | San Roque Arbol | 14.8965 | 120.5451 | R | 3613 | 903 | 271 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01558-B07 | PTCI/MIDC | 14.8999 | 120.5459 | 0.39 | Terrestrial Optical Fiber Drop | 1.85 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2839 | 3 | 839 | 2839 | 0701242009 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Mansasa | 9.632 | 123.8708 | U | 6609 | 1652 | 496 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0055 | PTCI/MIDC | 9.6342 | 123.8691 | 0.32 | Terrestrial Optical Fiber Drop | 2.28 | 0.09 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2840 | 3 | 840 | 2840 | 0500504032 | Region V (Bicol Region) | Albay | Guinobatan | Morera | 13.1986 | 123.5937 | R | 2511 | 612 | 184 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03382-C10 | PTCI/MIDC | 13.1904 | 123.5935 | 0.92 | Terrestrial Optical Fiber Drop | 1.57 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2841 | 3 | 841 | 2841 | 0702231014 | Region VII (Central Visayas) | Cebu | Medellin | Poblacion | 11.1287 | 123.9607 | U | 6979 | 1836 | 551 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 0.97 | Terrestrial Optical Fiber Drop | 1.12 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2842 | 3 | 842 | 2842 | 0205004007 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Banggot | 16.385 | 121.1103 | U | 4827 | 1270 | 381 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUV-02410 | Edgepoint | 16.3852 | 121.1076 | 0.28 | Terrestrial Optical Fiber Drop | 1.49 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2843 | 3 | 843 | 2843 | 1600201024 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Sacol | 8.9727 | 125.3937 | R | 3513 | 856 | 257 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTANG0001 | PTCI/MIDC | 8.9697 | 125.4057 | 1.36 | Terrestrial Optical Fiber Drop | 2.53 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2844 | 3 | 844 | 2844 | 0301407024 | Region III (Central Luzon) | Bulacan | Calumpit | San Marcos | 14.8978 | 120.7787 | U | 2792 | 797 | 239 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02325 | Edgepoint | 14.8962 | 120.7791 | 0.18 | Terrestrial Optical Fiber Drop | 1.51 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2845 | 3 | 845 | 2845 | 0402106034 | Region IV-A (CALABARZON) | Cavite | City of Dasmariñas | San Manuel I | 14.32 | 120.9562 | R | 2971 | 873 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02151-C08 | PTCI/MIDC | 14.2837 | 120.9617 | 0.45 | Terrestrial Optical Fiber Drop | 1.32 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2846 | 3 | 846 | 2846 | 0401028004 | Region IV-A (CALABARZON) | Batangas | City of Sto. Tomas | Barangay IV | 14.1053 | 121.1426 | U | 3529 | 980 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03100-C08 | PTCI/MIDC | 13.8876 | 121.0401 | 0.85 | Terrestrial Optical Fiber Drop | 2.59 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2847 | 3 | 847 | 2847 | 0702205044 | Region VII (Central Visayas) | Cebu | Argao | Tulic | 9.8747 | 123.5957 | R | 3060 | 805 | 242 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTCEG0004 | PTCI/MIDC | 9.882 | 123.606 | 1.4 | Terrestrial Optical Fiber Drop | 1.04 | 0.26 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2848 | 3 | 848 | 2848 | 0803739022 | Region VIII (Eastern Visayas) | Leyte | Palo | Cavite West | 11.1583 | 124.9881 | R | 2036 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLEG0052 | PTCI/MIDC | 11.1546 | 124.9954 | 0.89 | Terrestrial Optical Fiber Drop | 1.63 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2849 | 3 | 849 | 2849 | 0301419019 | Region III (Central Luzon) | Bulacan | San Ildefonso | Makapilapil | 15.0891 | 120.9416 | R | 2868 | 819 | 246 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00988-B07 | PTCI/MIDC | 15.089 | 120.9374 | 0.45 | Terrestrial Optical Fiber Drop | 1.69 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2850 | 3 | 850 | 2850 | 0403428006 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Don Jose | 14.2549 | 121.0644 | U | 19774 | 5992 | 1798 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | Q34 | FTAP Smart | 14.2566 | 121.0577 | 0.75 | Terrestrial Optical Fiber Drop | 1.28 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2851 | 3 | 851 | 2851 | 0908305024 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Sanito | 7.7865 | 122.5957 | U | 9618 | 2290 | 687 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0005 | PTCI/MIDC | 7.7895 | 122.5928 | 0.47 | Terrestrial Optical Fiber Drop | 1.52 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2852 | 3 | 852 | 2852 | 0501724030 | Region V (Bicol Region) | Camarines Sur | City of Naga | Tabuco | 13.6175 | 123.1838 | U | 4230 | 1007 | 302 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050083 | FTAP Globe | 13.6229 | 123.1846 | 0.61 | Terrestrial Optical Fiber Drop | 1.3 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2853 | 3 | 853 | 2853 | 0403405019 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Lawa | 14.207 | 121.1453 | U | 13423 | 4067 | 1220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03427-A04 | PTCI/MIDC | 14.2116 | 121.1438 | 0.54 | Terrestrial Optical Fiber Drop | 1.08 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2854 | 3 | 854 | 2854 | 0306916073 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Roque | 15.4845 | 120.5896 | U | 6267 | 1606 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00703 | Edgepoint | 15.4867 | 120.5874 | 0.34 | Terrestrial Optical Fiber Drop | 2.43 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2855 | 3 | 855 | 2855 | 0803738016 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Cogon Combado | 11.0208 | 124.6052 | U | 6006 | 1580 | 474 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLER0045 | PTCI/MIDC | 11.0153 | 124.6014 | 0.74 | Terrestrial Optical Fiber Drop | 0.74 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2856 | 3 | 856 | 2856 | 0604526011 | Region VI (Western Visayas) | Negros Occidental | City of Silay | Guinhalaran | 10.78 | 122.9695 | U | 16750 | 4527 | 1358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060337 | FTAP Globe | 10.7768 | 122.9645 | 0.65 | Terrestrial Optical Fiber Drop | 2.66 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2857 | 3 | 857 | 2857 | 0307109005 | Region III (Central Luzon) | Zambales | San Antonio | East Dirita | 14.969 | 120.0887 | R | 4039 | 1062 | 319 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N52 | FTAP Smart | 14.97 | 120.086 | 0.32 | Terrestrial Optical Fiber Drop | 2.09 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2858 | 3 | 858 | 2858 | 0604528011 | Region VI (Western Visayas) | Negros Occidental | City of Talisay | Efigenio Lizares | 10.7454 | 122.998 | R | 4695 | 1268 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0070 | PTCI/MIDC | 10.7469 | 122.9872 | 1.19 | Terrestrial Optical Fiber Drop | 3.36 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2859 | 3 | 859 | 2859 | 0301420011 | Region III (Central Luzon) | Bulacan | City of San Jose Del Monte | Tungkong Mangga | 14.7875 | 121.0718 | U | 17063 | 4875 | 1463 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01190 | Edgepoint | 14.788 | 121.0743 | 0.27 | Terrestrial Optical Fiber Drop | 1.16 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2860 | 3 | 860 | 2860 | 0600401010 | Region VI (Western Visayas) | Aklan | Altavas | Odiong | 11.5409 | 122.479 | R | 3364 | 862 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.91 | Terrestrial Optical Fiber Drop | 1.12 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2861 | 3 | 861 | 2861 | 0306916069 | Region III (Central Luzon) | Tarlac | City of Tarlac | San Nicolas | 15.4927 | 120.5947 | U | 7100 | 1820 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00694 | Edgepoint | 15.4936 | 120.597 | 0.27 | Terrestrial Optical Fiber Drop | 2.26 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2862 | 3 | 862 | 2862 | 0500503053 | Region V (Bicol Region) | Albay | Daraga | Tagas | 13.1598 | 123.7235 | U | 7662 | 1868 | 560 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0035 | PTCI/MIDC | 13.1569 | 123.7229 | 0.33 | Terrestrial Optical Fiber Drop | 1.9 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2863 | 3 | 863 | 2863 | 0431200020 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Ibabang Dupay | 13.9396 | 121.6255 | U | 28261 | 7065 | 2120 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1422 | FTAP Smart | 13.9416 | 121.6241 | 0.26 | Terrestrial Optical Fiber Drop | 1.68 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2864 | 3 | 864 | 2864 | 1004324003 | Region X (Northern Mindanao) | Misamis Oriental | Tagoloan | Gracia | 8.5285 | 124.7531 | U | 3031 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMLG0075 | PTCI/MIDC | 8.5289 | 124.7525 | 0.08 | Terrestrial Optical Fiber Drop | 1.07 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2865 | 3 | 865 | 2865 | 0401014066 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Sico | 13.9417 | 121.1297 | U | 5360 | 1488 | 446 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040436 | FTAP Globe | 13.9441 | 121.1298 | 0.27 | Terrestrial Optical Fiber Drop | 1.2 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2866 | 3 | 866 | 2866 | 0401003026 | Region IV-A (CALABARZON) | Batangas | Balayan | Duhatan | 13.9409 | 120.6606 | R | 1729 | 480 | 144 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH040475 | FTAP Globe | 13.9229 | 120.6613 | 2 | Terrestrial Optical Fiber Drop | 1.21 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2867 | 3 | 867 | 2867 | 0304930001 | Region III (Central Luzon) | Nueva Ecija | Talavera | Andal Alino | 15.5938 | 120.9224 | R | 2294 | 655 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0016 | PTCI/MIDC | 15.5946 | 120.9217 | 0.12 | Terrestrial Optical Fiber Drop | 1.35 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2868 | 3 | 868 | 2868 | 0702251026 | Region VII (Central Visayas) | Cebu | City of Toledo | Media Once | 10.3289 | 123.6749 | U | 9508 | 2502 | 751 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0166 | PTCI/MIDC | 10.3293 | 123.6743 | 0.08 | Terrestrial Optical Fiber Drop | 2.71 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2869 | 3 | 869 | 2869 | 0601914037 | Region VI (Western Visayas) | Capiz | City of Roxas | Lonoy | 11.5078 | 122.7367 | R | 3195 | 840 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02815-D13 | PTCI/MIDC | 11.5088 | 122.7376 | 0.15 | Terrestrial Optical Fiber Drop | 2.62 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2870 | 3 | 870 | 2870 | 0306916025 | Region III (Central Luzon) | Tarlac | City of Tarlac | Capehan | 15.433 | 120.6013 | R | 2335 | 598 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030399 | FTAP Globe | 15.4372 | 120.6017 | 0.46 | Terrestrial Optical Fiber Drop | 1.51 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2871 | 3 | 871 | 2871 | 0401009013 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Felipe | 13.8914 | 121.0399 | R | 4012 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03100-C08 | PTCI/MIDC | 13.8876 | 121.0401 | 0.42 | Terrestrial Optical Fiber Drop | 1.26 | 0.76 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2872 | 3 | 872 | 2872 | 0403405041 | Region IV-A (CALABARZON) | Laguna | City of Calamba | Barangay 4 | 14.2073 | 121.1623 | R | 3618 | 1096 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0026 | PTCI/MIDC | 14.1898 | 121.1331 | 0.64 | Terrestrial Optical Fiber Drop | 2.07 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2873 | 3 | 873 | 2873 | 0701242010 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion I | 9.644 | 123.8585 | U | 2965 | 741 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0050 | PTCI/MIDC | 9.6529 | 123.8676 | 0.31 | Terrestrial Optical Fiber Drop | 1.76 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2874 | 3 | 874 | 2874 | 0500506025 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 28 - Victory Village North | 13.1444 | 123.7561 | R | 2467 | 601 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050178 | FTAP Globe | 13.14 | 123.7567 | 0.5 | Terrestrial Optical Fiber Drop | 1.94 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2875 | 3 | 875 | 2875 | 0405630020 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Barangay 2 Daungan | 13.9688 | 121.6837 | R | 2040 | 536 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040407 | FTAP Globe | 13.9689 | 121.685 | 0.72 | Terrestrial Optical Fiber Drop | 0.38 | 0.16 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2876 | 3 | 876 | 2876 | 0304919012 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Singalat | 15.572 | 121.095 | U | 2799 | 799 | 240 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0007 | PTCI/MIDC | 15.5726 | 121.0971 | 0.23 | Terrestrial Optical Fiber Drop | 1.12 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2877 | 3 | 877 | 2877 | 0301411016 | Region III (Central Luzon) | Bulacan | Marilao | Tabing Ilog | 14.7649 | 120.9489 | U | 8421 | 2406 | 722 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01213 | Edgepoint | 14.7661 | 120.9455 | 0.39 | Terrestrial Optical Fiber Drop | 1.07 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2878 | 3 | 878 | 2878 | 0500517008 | Region V (Bicol Region) | Albay | City of Tabaco | Bogñabong | 13.3419 | 123.7159 | R | 3219 | 785 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTALG0021 | PTCI/MIDC | 13.354 | 123.7251 | 0.52 | Terrestrial Optical Fiber Drop | 2.06 | 1.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2879 | 3 | 879 | 2879 | 1102509009 | Region XI (Davao Region) | Davao Oriental | City of Mati | Dawan | 6.9075 | 126.167 | R | 4097 | 1138 | 341 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTDLG0011 | PTCI/MIDC | 6.9124 | 126.1725 | 0.82 | Terrestrial Optical Fiber Drop | 7.47 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2880 | 3 | 880 | 2880 | 0304930006 | Region III (Central Luzon) | Nueva Ecija | Talavera | Bakal III | 15.7035 | 120.8989 | U | 7145 | 2041 | 612 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01484-B07 | PTCI/MIDC | 15.7038 | 120.9027 | 0.4 | Terrestrial Optical Fiber Drop | 1.42 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2881 | 3 | 881 | 2881 | 0304928021 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Zamora | 15.4342 | 120.9379 | R | 1423 | 406 | 122 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N3532 | FTAP Smart | 15.4266 | 120.9483 | 1.5 | Terrestrial Optical Fiber Drop | 1.27 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2882 | 3 | 882 | 2882 | 0330100008 | Region III (Central Luzon) | Pampanga | City of Angeles | Cutud | 15.1756 | 120.6265 | U | 25921 | 7200 | 2160 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01548-B07 | PTCI/MIDC | 15.1764 | 120.621 | 0.59 | Terrestrial Optical Fiber Drop | 1.85 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2883 | 3 | 883 | 2883 | 0304927004 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Castellano | 15.3195 | 120.9345 | U | 6047 | 1727 | 518 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01449-B07 | PTCI/MIDC | 15.3191 | 120.9382 | 0.41 | Terrestrial Optical Fiber Drop | 1.64 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2884 | 3 | 884 | 2884 | 0203136019 | Region II (Cagayan Valley) | Isabela | Santo Tomas | Centro | 17.3974 | 121.7644 | R | 2888 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-ISA-00138 | Edgepoint | 17.3993 | 121.7662 | 0.28 | Terrestrial Optical Fiber Drop | 1.39 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2885 | 3 | 885 | 2885 | 0402111002 | Region IV-A (CALABARZON) | Cavite | Kawit | Gahak | 14.4437 | 120.9103 | R | 3089 | 908 | 272 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01901-C08 | PTCI/MIDC | 14.4412 | 120.9121 | 0.34 | Terrestrial Optical Fiber Drop | 3.33 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2886 | 3 | 886 | 2886 | 0702250019 | Region VII (Central Visayas) | Cebu | City of Talisay | Biasong | 10.2481 | 123.8337 | U | 10653 | 2803 | 841 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0158 | PTCI/MIDC | 10.2398 | 123.8339 | 0.92 | Terrestrial Optical Fiber Drop | 0.91 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2887 | 3 | 887 | 2887 | 0401003017 | Region IV-A (CALABARZON) | Batangas | Balayan | Caloocan | 13.9527 | 120.7239 | U | 6470 | 1797 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBGG0059 | PTCI/MIDC | 13.9557 | 120.7255 | 0.37 | Terrestrial Optical Fiber Drop | 1.12 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2888 | 3 | 888 | 2888 | 0702219006 | Region VII (Central Visayas) | Cebu | Consolacion | Jugan | 10.38 | 123.9725 | U | 13063 | 3437 | 1031 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070326 | FTAP Globe | 10.3811 | 123.9709 | 0.2 | Terrestrial Optical Fiber Drop | 1.55 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2889 | 3 | 889 | 2889 | 0604530017 | Region VI (Western Visayas) | Negros Occidental | Valladolid | Tabao Proper | 10.4451 | 122.8263 | R | 4471 | 1208 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0074 | PTCI/MIDC | 10.4519 | 122.8251 | 0.77 | Terrestrial Optical Fiber Drop | 2.35 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2890 | 3 | 890 | 2890 | 0201529019 | Region II (Cagayan Valley) | Cagayan | Tuguegarao City | Caritan Norte | 17.6747 | 121.7561 | R | 3683 | 944 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-CAG-02278 | Edgepoint | 17.6685 | 121.7522 | 0.81 | Terrestrial Optical Fiber Drop | 2.77 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2891 | 3 | 891 | 2891 | 0501724024 | Region V (Bicol Region) | Camarines Sur | City of Naga | Peñafrancia | 13.6315 | 123.1895 | U | 4492 | 1069 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH050079 | FTAP Globe | 13.6298 | 123.1911 | 0.26 | Terrestrial Optical Fiber Drop | 1.08 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2892 | 3 | 892 | 2892 | 0300807008 | Region III (Central Luzon) | Bataan | Mariveles | Poblacion | 14.4361 | 120.4841 | U | 8835 | 2454 | 736 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0003 | PTCI/MIDC | 14.4309 | 120.4797 | 0.75 | Terrestrial Optical Fiber Drop | 1.56 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2893 | 3 | 893 | 2893 | 0301423010 | Region III (Central Luzon) | Bulacan | Santa Maria | Lalakhan | 14.8151 | 120.9461 | R | 2424 | 692 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01170 | Edgepoint | 14.8149 | 120.9461 | 0.02 | Terrestrial Optical Fiber Drop | 1.36 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2894 | 3 | 894 | 2894 | 0300810008 | Region III (Central Luzon) | Bataan | Orion | Bilolo | 14.6152 | 120.5617 | U | 8178 | 2271 | 681 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1518 | FTAP Smart | 14.6186 | 120.5623 | 0.39 | Terrestrial Optical Fiber Drop | 1.87 | 1.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2895 | 3 | 895 | 2895 | 0604502024 | Region VI (Western Visayas) | Negros Occidental | City of Bago | Sampinit | 10.5448 | 122.863 | U | 10158 | 2745 | 824 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNOG0089 | PTCI/MIDC | 10.5344 | 122.8445 | 1.37 | Terrestrial Optical Fiber Drop | 2.55 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2896 | 3 | 896 | 2896 | 0401022006 | Region IV-A (CALABARZON) | Batangas | San Jose | Balagtasin I | 13.9018 | 121.0884 | R | 1642 | 456 | 137 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | S1351 | FTAP Smart | 13.8931 | 121.0981 | 0.71 | Terrestrial Optical Fiber Drop | 3.09 | 1.74 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2897 | 3 | 897 | 2897 | 0403422017 | Region IV-A (CALABARZON) | Laguna | Pila | Santa Clara Sur | 14.234 | 121.3659 | U | 6468 | 1960 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02116-C08 | PTCI/MIDC | 14.229 | 121.3683 | 0.63 | Terrestrial Optical Fiber Drop | 0.34 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2898 | 3 | 898 | 2898 | 0402111013 | Region IV-A (CALABARZON) | Cavite | Kawit | Batong Dalig | 14.4349 | 120.8971 | U | 5412 | 1591 | 477 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040103 | FTAP Globe | 14.4337 | 120.9016 | 0.5 | Terrestrial Optical Fiber Drop | 1.63 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2899 | 3 | 899 | 2899 | 0401005009 | Region IV-A (CALABARZON) | Batangas | Batangas City | Banaba Ibaba | 13.7914 | 121.0583 | R | 3509 | 974 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040572 | FTAP Globe | 13.7858 | 121.0578 | 0.63 | Terrestrial Optical Fiber Drop | 2.96 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2900 | 3 | 900 | 2900 | 0201516011 | Region II (Cagayan Valley) | Cagayan | Lal-Lo | Catayauan | 18.1589 | 121.6538 | R | 4242 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAG_0032 | LDIC | 121.6633 | 18.1613 | 1.54 | Terrestrial Optical Fiber Drop | 4.17 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2901 | 3 | 901 | 2901 | 0301404003 | Region III (Central Luzon) | Bulacan | Bocaue | Bambang | 14.7885 | 120.9286 | U | 9241 | 2640 | 792 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030608 | FTAP Globe | 14.7908 | 120.9227 | 0.68 | Terrestrial Optical Fiber Drop | 1.26 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2902 | 3 | 902 | 2902 | 1400101031 | Cordillera Administrative Region (CAR) | Abra | Bangued | Zone 1 Pob. | 17.6021 | 120.6162 | R | 2266 | 596 | 179 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02672-B05 | PTCI/MIDC | 17.6009 | 120.618 | 0.24 | Terrestrial Optical Fiber Drop | 1.09 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2903 | 3 | 903 | 2903 | 0305409018 | Region III (Central Luzon) | Pampanga | Mabalacat City | Mawaque | 15.2086 | 120.5911 | U | 3917 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01668-B07 | PTCI/MIDC | 15.2079 | 120.5954 | 0.47 | Terrestrial Optical Fiber Drop | 1.24 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2904 | 3 | 904 | 2904 | 1004313005 | Region X (Northern Mindanao) | Misamis Oriental | Lagonglong | Kauswagan | 8.7881 | 124.7843 | R | 3715 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100040 | FTAP BTS | 8.7788 | 124.7843 | 1.03 | Terrestrial Optical Fiber Drop | 2 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2905 | 3 | 905 | 2905 | 0401014038 | Region IV-A (CALABARZON) | Batangas | City of Lipa | Pinagtongulan | 13.9306 | 121.0995 | U | 3916 | 1087 | 326 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03441-C08 | PTCI/MIDC | 13.9276 | 121.0981 | 0.36 | Terrestrial Optical Fiber Drop | 2.3 | 0.78 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2906 | 3 | 906 | 2906 | 0300807020 | Region III (Central Luzon) | Bataan | Mariveles | Townsite | 14.4579 | 120.5944 | U | 7524 | 2090 | 627 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | O00 | FTAP Smart | 14.466 | 120.5989 | 1.03 | Terrestrial Optical Fiber Drop | 2.44 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2907 | 3 | 907 | 2907 | 1705110039 | MIMAROPA Region | Occidental Mindoro | San Jose | San Roque | 12.3586 | 121.0566 | U | 16580 | 4251 | 1275 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | 4053 | FTAP Smart | 12.3689 | 121.0524 | 1.24 | Terrestrial Optical Fiber Drop | 1.23 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2908 | 3 | 908 | 2908 | 1108203018 | Region XI (Davao Region) | Davao de Oro | Mabini | San Antonio | 7.2922 | 125.8542 | R | 3124 | 844 | 253 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110444 | FTAP Globe | 7.2844 | 125.8539 | 0.86 | Terrestrial Optical Fiber Drop | 1.86 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2909 | 3 | 909 | 2909 | 0603037023 | Region VI (Western Visayas) | Iloilo | Pototan | Igang | 10.9114 | 122.6269 | R | 4005 | 1053 | 316 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTILG0059 | PTCI/MIDC | 10.9403 | 122.6406 | 3.55 | Terrestrial Optical Fiber Drop | 4.17 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2910 | 3 | 910 | 2910 | 0306903066 | Region III (Central Luzon) | Tarlac | Camiling | Tambugan | 15.6982 | 120.4191 | R | 1656 | 424 | 127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00600 | Edgepoint | 15.6931 | 120.4127 | 0.89 | Terrestrial Optical Fiber Drop | 1.1 | 0.65 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2911 | 3 | 911 | 2911 | 1004307011 | Region X (Northern Mindanao) | Misamis Oriental | City of El Salvador | Molugan | 8.5328 | 124.5622 | U | 13261 | 3400 | 1020 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100057 | FTAP BTS | 8.5349 | 124.5605 | 0.29 | Terrestrial Optical Fiber Drop | 1.97 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2912 | 3 | 912 | 2912 | 0604520003 | Region VI (Western Visayas) | Negros Occidental | Murcia | Amayco | 10.6205 | 123.0642 | R | 2439 | 659 | 198 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_NEC_0032 | LDIC | 10.5776 | 123.0739 | 0.45 | Terrestrial Optical Fiber Drop | 2.86 | 2.72 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2913 | 3 | 913 | 2913 | 0301412003 | Region III (Central Luzon) | Bulacan | City of Meycauayan | Bancal | 14.7207 | 120.9618 | U | 13261 | 3788 | 1136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02506-A01 | PTCI/MIDC | 14.7208 | 120.9665 | 0.51 | Terrestrial Optical Fiber Drop | 1.35 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2914 | 3 | 914 | 2914 | 0301410039 | Region III (Central Luzon) | Bulacan | City of Malolos | Pinagbakahan | 14.8753 | 120.8195 | U | 7905 | 2258 | 677 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030568 | FTAP Globe | 14.8757 | 120.818 | 0.17 | Terrestrial Optical Fiber Drop | 2.25 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2915 | 3 | 915 | 2915 | 0300810003 | Region III (Central Luzon) | Bataan | Orion | Balagtas | 14.6296 | 120.5777 | R | 2084 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00909-B07 | PTCI/MIDC | 14.6228 | 120.5803 | 0.81 | Terrestrial Optical Fiber Drop | 1.58 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2916 | 3 | 916 | 2916 | 1108203014 | Region XI (Davao Region) | Davao de Oro | Mabini | Del Pilar | 7.2991 | 125.8591 | R | 2503 | 676 | 203 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH110440 | FTAP Globe | 7.3117 | 125.8547 | 1.48 | Terrestrial Optical Fiber Drop | 1.16 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2917 | 3 | 917 | 2917 | 0600613010 | Region VI (Western Visayas) | Antique | San Jose | Barangay 8 | 10.7453 | 121.9493 | U | 5389 | 1381 | 414 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTAQG0018 | PTCI/MIDC | 10.7471 | 121.9496 | 0.2 | Terrestrial Optical Fiber Drop | 2.27 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2918 | 3 | 918 | 2918 | 0300802008 | Region III (Central Luzon) | Bataan | Bagac | Pag-asa | 14.6088 | 120.3868 | R | 3895 | 1081 | 324 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F00901-B07 | PTCI/MIDC | 14.602 | 120.3962 | 1.25 | Terrestrial Optical Fiber Drop | 1.25 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2919 | 3 | 919 | 2919 | 0304908001 | Region III (Central Luzon) | Nueva Ecija | City of Gapan | Bayanihan | 15.2995 | 120.9449 | U | 5999 | 1714 | 514 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNEG0003 | PTCI/MIDC | 15.307 | 120.9519 | 1.13 | Terrestrial Optical Fiber Drop | 0.31 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2920 | 3 | 920 | 2920 | 1630400027 | Region XIII (Caraga) | Agusan del Norte | City of Butuan | Buhangin Pob. | 8.9627 | 125.5379 | U | 5174 | 1261 | 378 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTANR0011 | PTCI/MIDC | 8.9471 | 125.541 | 0.95 | Terrestrial Optical Fiber Drop | 1.29 | 1.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2921 | 3 | 921 | 2921 | 0702250001 | Region VII (Central Visayas) | Cebu | City of Talisay | Bulacao | 10.2711 | 123.8424 | U | 12639 | 3326 | 998 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0197 | PTCI/MIDC | 10.2761 | 123.8445 | 0.6 | Terrestrial Optical Fiber Drop | 1.03 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2922 | 3 | 922 | 2922 | 1204702035 | Region XII (SOCCSKSARGEN) | Cotabato | Carmen | Tacupan | 7.2163 | 124.7973 | R | 2464 | 648 | 194 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120262 | FTAP Globe | 7.2057 | 124.7944 | 1.22 | Terrestrial Optical Fiber Drop | 1.52 | 0.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2923 | 3 | 923 | 2923 | 0501716020 | Region V (Bicol Region) | Camarines Sur | City of Iriga | San Miguel | 13.4174 | 123.4061 | U | 3306 | 787 | 236 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-CAS-02059 | Edgepoint | 123.406 | 13.4185 | 0.13 | Terrestrial Optical Fiber Drop | 1.13 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2924 | 3 | 924 | 2924 | 1206511004 | Region XII (SOCCSKSARGEN) | Sultan Kudarat | City of Tacurong | Carmen | 6.6721 | 124.6822 | U | 3684 | 969 | 291 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH120127 | FTAP BTS | 6.6711 | 124.6851 | 0.33 | Terrestrial Optical Fiber Drop | 2.17 | 0.31 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2925 | 3 | 925 | 2925 | 0806408007 | Region VIII (Eastern Visayas) | Southern Leyte | Macrohon | Ichon | 10.1104 | 124.9005 | R | 3843 | 937 | 281 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH080216 | FTAP BTS | 10.1224 | 124.8948 | 1.47 | Terrestrial Optical Fiber Drop | 0.25 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2926 | 3 | 926 | 2926 | 0702206026 | Region VII (Central Visayas) | Cebu | Asturias | Tubigagmanok | 10.6296 | 123.7467 | R | 4967 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0258 | PTCI/MIDC | 10.6781 | 123.8069 | 8.51 | Terrestrial Optical Fiber Drop | 13.86 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2927 | 3 | 927 | 2927 | 1705205057 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Sto. Niño | 13.4062 | 121.1855 | U | 3715 | 952 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170062 | FTAP Globe | 13.3876 | 121.1802 | 3.3 | Terrestrial Optical Fiber Drop | 2.18 | 3.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2928 | 3 | 928 | 2928 | 1130700031 | Region XI (Davao Region) | Davao del Sur | City of Davao | Catalunan Pequeño | 7.0764 | 125.5206 | U | 26806 | 7884 | 2365 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH110484 | FTAP Globe | 7.0774 | 125.5149 | 0.64 | Terrestrial Optical Fiber Drop | 2.03 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2929 | 3 | 929 | 2929 | 0506203023 | Region V (Bicol Region) | Sorsogon | Bulan | Fabrica | 12.6621 | 123.889 | R | 2771 | 692 | 208 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_SOR_0003 | LDIC | 12.666 | 123.8894 | 0.44 | Terrestrial Optical Fiber Drop | 1.95 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2930 | 3 | 930 | 2930 | 0305411017 | Region III (Central Luzon) | Pampanga | Magalang | San Pedro II | 15.2109 | 120.6487 | U | 5721 | 1430 | 429 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03221-B07 | PTCI/MIDC | 15.211 | 120.6581 | 1.02 | Terrestrial Optical Fiber Drop | 1.29 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2931 | 3 | 931 | 2931 | 0500503037 | Region V (Bicol Region) | Albay | Daraga | Mayon | 13.0588 | 123.7052 | R | 2054 | 500 | 150 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050193 | FTAP Globe | 13.0676 | 123.7045 | 0.97 | Terrestrial Optical Fiber Drop | 1.04 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2932 | 3 | 932 | 2932 | 0331400017 | Region III (Central Luzon) | Zambales | City of Olongapo | Pag-asa | 14.8497 | 120.2937 | U | 6709 | 1813 | 544 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZMG0018 | PTCI/MIDC | 14.8485 | 120.2913 | 0.29 | Terrestrial Optical Fiber Drop | 2.25 | 0.28 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2933 | 3 | 933 | 2933 | 0307106012 | Region III (Central Luzon) | Zambales | Masinloc | Taltal | 15.5745 | 119.9476 | R | 5041 | 1326 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030354 | FTAP Globe | 15.5762 | 119.9471 | 0.19 | Terrestrial Optical Fiber Drop | 4.3 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2934 | 3 | 934 | 2934 | 0702201006 | Region VII (Central Visayas) | Cebu | Alcantara | Palanas | 9.9849 | 123.4103 | R | 3312 | 871 | 261 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCEG0132 | PTCI/MIDC | 9.9782 | 123.3783 | 3.58 | Terrestrial Optical Fiber Drop | 1.69 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2935 | 3 | 935 | 2935 | 0401009014 | Region IV-A (CALABARZON) | Batangas | Cuenca | San Isidro | 13.905 | 121.0596 | R | 2641 | 733 | 220 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040500 | FTAP Globe | 13.9093 | 121.0582 | 0.51 | Terrestrial Optical Fiber Drop | 1.33 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2936 | 3 | 936 | 2936 | 0501726015 | Region V (Bicol Region) | Camarines Sur | Pamplona | San Vicente | 13.5954 | 123.0515 | R | 4250 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH050096 | FTAP Globe | 13.5938 | 123.0833 | 3.45 | Terrestrial Optical Fiber Drop | 2.62 | 2.64 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2937 | 3 | 937 | 2937 | 0405804020 | Region IV-A (CALABARZON) | Rizal | Binangonan | Libis | 14.4653 | 121.1888 | U | 5653 | 1570 | 471 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01896 | Edgepoint | 14.4645 | 121.1909 | 0.24 | Terrestrial Optical Fiber Drop | 1.69 | 0.32 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2938 | 3 | 938 | 2938 | 0305416015 | Region III (Central Luzon) | Pampanga | City of San Fernando | Maimpis | 15.0689 | 120.6527 | U | 13631 | 3407 | 1022 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00896 | Edgepoint | 15.0727 | 120.65 | 0.52 | Terrestrial Optical Fiber Drop | 1.39 | 0.33 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2939 | 3 | 939 | 2939 | 0301403002 | Region III (Central Luzon) | Bulacan | Baliuag | Barangca | 14.9876 | 120.8958 | R | 3538 | 1010 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F00964-B07 | PTCI/MIDC | 14.9952 | 120.8923 | 0.93 | Terrestrial Optical Fiber Drop | 2.42 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2940 | 3 | 940 | 2940 | 0731300012 | Region VII (Central Visayas) | Cebu | City of Mandaue | Guizo | 10.3289 | 123.9358 | U | 7265 | 2075 | 623 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0113 | PTCI/MIDC | 10.3319 | 123.936 | 0.34 | Terrestrial Optical Fiber Drop | 1.56 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2941 | 3 | 941 | 2941 | 0305415028 | Region III (Central Luzon) | Pampanga | Porac | Pulung Santol | 15.0478 | 120.5576 | U | 7742 | 1935 | 581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.74 | Terrestrial Optical Fiber Drop | 2.42 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2942 | 3 | 942 | 2942 | 0306916052 | Region III (Central Luzon) | Tarlac | City of Tarlac | Matatalaib | 15.4966 | 120.6 | U | 26018 | 6671 | 2001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTTAG0013 | PTCI/MIDC | 15.5002 | 120.5985 | 0.43 | Terrestrial Optical Fiber Drop | 2.16 | 0.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2943 | 3 | 943 | 2943 | 0631000012 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Baldoza | 10.7049 | 122.5621 | U | 6365 | 1515 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTILR0088 | PTCI/MIDC | 10.7259 | 122.5515 | 0.3 | Terrestrial Optical Fiber Drop | 1.18 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2944 | 3 | 944 | 2944 | 1130700112 | Region XI (Davao Region) | Davao del Sur | City of Davao | Tagakpan | 7.1258 | 125.4325 | R | 5156 | 1516 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0090 | PTCI/MIDC | 7.1261 | 125.4282 | 0.47 | Terrestrial Optical Fiber Drop | 7.14 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2945 | 3 | 945 | 2945 | 0305408012 | Region III (Central Luzon) | Pampanga | Lubao | Remedios | 14.9179 | 120.5797 | R | 4754 | 1188 | 356 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH030546 | FTAP Globe | 14.9085 | 120.5852 | 1.2 | Terrestrial Optical Fiber Drop | 2.89 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2946 | 3 | 946 | 2946 | 0105524060 | Region I (Ilocos Region) | Pangasinan | Malasiqui | Pasima | 15.9253 | 120.4012 | R | 2743 | 761 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00529 | Edgepoint | 15.9206 | 120.4066 | 0.77 | Terrestrial Optical Fiber Drop | 1.33 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2947 | 3 | 947 | 2947 | 0403406002 | Region IV-A (CALABARZON) | Laguna | Calauan | Bangyas | 14.174 | 121.3169 | R | 3213 | 973 | 292 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040277 | FTAP Globe | 14.1723 | 121.3161 | 0.2 | Terrestrial Optical Fiber Drop | 3.13 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2948 | 3 | 948 | 2948 | 1705318013 | MIMAROPA Region | Palawan | Roxas | New Barbacan | 10.3291 | 119.3496 | R | 5417 | 1388 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 0.15 | Terrestrial Optical Fiber Drop | 1.38 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2949 | 3 | 949 | 2949 | 0301403022 | Region III (Central Luzon) | Bulacan | Baliuag | Subic | 14.9635 | 120.9033 | U | 6728 | 1922 | 577 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.61 | Terrestrial Optical Fiber Drop | 1.39 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2950 | 3 | 950 | 2950 | 0504111023 | Region V (Bicol Region) | Masbate | City of Masbate | Mayngaran | 12.3496 | 123.5996 | U | 5015 | 1223 | 367 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTMSG0006 | PTCI/MIDC | 12.3538 | 123.5951 | 0.68 | Terrestrial Optical Fiber Drop | 2.08 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2951 | 3 | 951 | 2951 | 0603007006 | Region VI (Western Visayas) | Iloilo | Barotac Nuevo | Bungca | 10.9083 | 122.7161 | R | 2410 | 634 | 190 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060012 | FTAP BTS | 10.8977 | 122.7054 | 1.66 | Terrestrial Optical Fiber Drop | 1.6 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2952 | 3 | 952 | 2952 | 0702215001 | Region VII (Central Visayas) | Cebu | Carmen | Baring | 10.5875 | 124.0146 | U | 5732 | 1508 | 452 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 0.39 | Terrestrial Optical Fiber Drop | 1.29 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2953 | 3 | 953 | 2953 | 1230800007 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas East | 6.1159 | 125.1771 | U | 3507 | 899 | 270 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSCG0013 | PTCI/MIDC | 6.1175 | 125.1764 | 0.19 | Terrestrial Optical Fiber Drop | 1.11 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2954 | 3 | 954 | 2954 | 1401105007 | Cordillera Administrative Region (CAR) | Benguet | Buguias | Buyacaoan | 16.776 | 120.8121 | R | 3989 | 1139 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTBEG0006 | PTCI/MIDC | 16.7904 | 120.8171 | 1.69 | Terrestrial Optical Fiber Drop | 3.2 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2955 | 3 | 955 | 2955 | 0702215009 | Region VII (Central Visayas) | Cebu | Carmen | Cogon East | 10.5909 | 124.0212 | R | 3391 | 892 | 268 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070027 | FTAP BTS | 10.5852 | 124.0119 | 1.2 | Terrestrial Optical Fiber Drop | 1.58 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2956 | 3 | 956 | 2956 | 0701236013 | Region VII (Central Visayas) | Bohol | Sagbayan | Poblacion | 9.9155 | 124.0955 | R | 4055 | 1013 | 304 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOG0030 | PTCI/MIDC | 9.9121 | 124.0943 | 0.4 | Terrestrial Optical Fiber Drop | 32.18 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2957 | 3 | 957 | 2957 | 0403424005 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Barangay II-A | 14.0623 | 121.3201 | R | 3174 | 961 | 288 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02075-C08 | PTCI/MIDC | 14.0549 | 121.3128 | 1.13 | Terrestrial Optical Fiber Drop | 1.08 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2958 | 3 | 958 | 2958 | 0401021043 | Region IV-A (CALABARZON) | Batangas | Rosario | San Roque | 13.8562 | 121.2089 | U | 4740 | 1316 | 395 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | S1032 | FTAP Smart | 13.8539 | 121.205 | 0.49 | Terrestrial Optical Fiber Drop | 1.53 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2959 | 3 | 959 | 2959 | 1705203017 | MIMAROPA Region | Oriental Mindoro | Bongabong | Malitbog | 12.7554 | 121.4686 | R | 3313 | 849 | 255 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH170114 | FTAP Globe | 12.7482 | 121.4852 | 1.97 | Terrestrial Optical Fiber Drop | 2.4 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2960 | 3 | 960 | 2960 | 0330100007 | Region III (Central Luzon) | Pampanga | City of Angeles | Cutcut | 15.1392 | 120.5672 | U | 29551 | 8208 | 2462 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030459 | FTAP Globe | 15.1438 | 120.5664 | 0.52 | Terrestrial Optical Fiber Drop | 1.07 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2961 | 3 | 961 | 2961 | 0630200011 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Barangay 16 | 10.665 | 122.9412 | U | 7870 | 2186 | 656 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0090 | PTCI/MIDC | 10.6661 | 122.9446 | 0.27 | Terrestrial Optical Fiber Drop | 1.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2962 | 3 | 962 | 2962 | 1430300089 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Poliwes | 16.4077 | 120.5974 | R | 2871 | 755 | 227 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1846 | FTAP Smart | 16.461 | 120.6138 | 0.58 | Terrestrial Optical Fiber Drop | 0.61 | 0.3 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2963 | 3 | 963 | 2963 | 0603018034 | Region VI (Western Visayas) | Iloilo | Dumangas | Paloc Sool | 10.8333 | 122.7167 | R | 3595 | 946 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 0.97 | Terrestrial Optical Fiber Drop | 1.12 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2964 | 3 | 964 | 2964 | 0702205006 | Region VII (Central Visayas) | Cebu | Argao | Binlod | 9.9138 | 123.605 | R | 4159 | 1094 | 328 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070017 | FTAP BTS | 9.8956 | 123.5985 | 2.14 | Terrestrial Optical Fiber Drop | 3.43 | 0.35 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2965 | 3 | 965 | 2965 | 0405805020 | Region IV-A (CALABARZON) | Rizal | Cainta | Santo Domingo | 14.5833 | 121.1112 | U | 45228 | 12563 | 3769 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01759 (EP_PH-RIZ-01759) | EdgePoint | 14.5824 | 121.1131 | 0.22 | Terrestrial Optical Fiber Drop | 1.32 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2966 | 3 | 966 | 2966 | 0307101017 | Region III (Central Luzon) | Zambales | Botolan | Porac | 15.252 | 120.0172 | R | 3753 | 987 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030429 | FTAP Globe | 15.2536 | 120.0187 | 0.24 | Terrestrial Optical Fiber Drop | 9.35 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2967 | 3 | 967 | 2967 | 1404402015 | Cordillera Administrative Region (CAR) | Mountain Province | Bauko | Monamon Sur | 16.8814 | 120.8838 | R | 3671 | 992 | 298 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-MOU-00237 | Edgepoint | 16.8985 | 120.8953 | 2.27 | Terrestrial Optical Fiber Drop | 1.84 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2968 | 3 | 968 | 2968 | 0701242011 | Region VII (Central Visayas) | Bohol | City of Tagbilaran | Poblacion II | 9.6435 | 123.8588 | U | 4396 | 1099 | 330 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBOR0035 | PTCI/MIDC | 9.6414 | 123.8556 | 0.41 | Terrestrial Optical Fiber Drop | 0.48 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2969 | 3 | 969 | 2969 | 0702234029 | Region VII (Central Visayas) | Cebu | City of Naga | West Poblacion | 10.21 | 123.7555 | R | 4169 | 1097 | 329 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0134 | PTCI/MIDC | 10.2035 | 123.7557 | 0.73 | Terrestrial Optical Fiber Drop | 3.07 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2970 | 3 | 970 | 2970 | 0704621006 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | Obogon | 9.5094 | 123.1503 | R | 3918 | 1031 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070258 | FTAP Globe | 9.5141 | 123.156 | 0.81 | Terrestrial Optical Fiber Drop | 9.46 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2971 | 3 | 971 | 2971 | 0305406003 | Region III (Central Luzon) | Pampanga | Floridablanca | Basa Air Base | 14.9787 | 120.4997 | R | 2657 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00982 | Edgepoint | 14.973 | 120.5008 | 0.64 | Terrestrial Optical Fiber Drop | 1.55 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2972 | 3 | 972 | 2972 | 0702223014 | Region VII (Central Visayas) | Cebu | Danao City | Dunggoan | 10.5546 | 124.0191 | U | 7478 | 1967 | 590 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0083 | PTCI/MIDC | 10.5494 | 124.0218 | 0.64 | Terrestrial Optical Fiber Drop | 2.47 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2973 | 3 | 973 | 2973 | 0306916076 | Region III (Central Luzon) | Tarlac | City of Tarlac | Santa Cruz | 15.5372 | 120.5968 | R | 4449 | 1140 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030362 | FTAP Globe | 15.5405 | 120.5949 | 0.42 | Terrestrial Optical Fiber Drop | 4.15 | 0.36 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2974 | 3 | 974 | 2974 | 0405811007 | Region IV-A (CALABARZON) | Rizal | San Mateo | Malanday | 14.7046 | 121.125 | U | 13906 | 3862 | 1159 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIM0002 | PTCI/MIDC | 14.7047 | 121.1282 | 0.35 | Terrestrial Optical Fiber Drop | 2.1 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2975 | 3 | 975 | 2975 | 0730600031 | Region VII (Central Visayas) | Cebu | City of Cebu | Hippodromo | 10.3136 | 123.9072 | U | 9586 | 2995 | 899 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0039 | PTCI/MIDC | 10.3131 | 123.9118 | 0.51 | Terrestrial Optical Fiber Drop | 1.69 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2976 | 3 | 976 | 2976 | 0305415026 | Region III (Central Luzon) | Pampanga | Porac | Poblacion | 15.0724 | 120.5389 | R | 1650 | 412 | 124 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-02430 | Edgepoint | 15.0723 | 120.5412 | 0.25 | Terrestrial Optical Fiber Drop | 1.01 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2977 | 3 | 977 | 2977 | 0405804025 | Region IV-A (CALABARZON) | Rizal | Binangonan | Mambog | 14.4809 | 121.2124 | U | 10886 | 3023 | 907 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00784-A04 | PTCI/MIDC | 14.4823 | 121.2135 | 0.19 | Terrestrial Optical Fiber Drop | 1.41 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2978 | 3 | 978 | 2978 | 0403424071 | Region IV-A (CALABARZON) | Laguna | City of San Pablo | Santa Maria Magdalena | 14.0948 | 121.3073 | R | 3045 | 922 | 277 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02083-C08 | PTCI/MIDC | 14.0881 | 121.3067 | 0.75 | Terrestrial Optical Fiber Drop | 1.82 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2979 | 3 | 979 | 2979 | 0105543012 | Region I (Ilocos Region) | Pangasinan | Tayug | Magallanes | 16.0187 | 120.7389 | U | 3525 | 979 | 294 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAN-00445 | Edgepoint | 16.0267 | 120.7436 | 1.03 | Terrestrial Optical Fiber Drop | 1.08 | 0.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2980 | 3 | 980 | 2980 | 1230800035 | Region XII (SOCCSKSARGEN) | South Cotabato | City of General Santos | Dadiangas North | 6.1156 | 125.1669 | U | 7042 | 1805 | 542 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTSCR0011 | PTCI/MIDC | 6.1112 | 125.1712 | 0.68 | Terrestrial Optical Fiber Drop | 1.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2981 | 3 | 981 | 2981 | 0401002012 | Region IV-A (CALABARZON) | Batangas | Alitagtag | Muzon Segundo | 13.8696 | 121.0215 | R | 2362 | 656 | 197 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03243-C08 | PTCI/MIDC | 13.8652 | 121.0025 | 0.53 | Terrestrial Optical Fiber Drop | 3.91 | 0.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2982 | 3 | 982 | 2982 | 0405813004 | Region IV-A (CALABARZON) | Rizal | Taytay | San Juan | 14.5443 | 121.1201 | U | 122533 | 34036 | 10211 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00804-A04 | PTCI/MIDC | 14.5436 | 121.1186 | 0.18 | Terrestrial Optical Fiber Drop | 1.58 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2983 | 3 | 983 | 2983 | 0304928030 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Luna | 15.4341 | 120.938 | R | 2032 | 580 | 174 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01514-B07 | PTCI/MIDC | 15.4297 | 120.9864 | 1.89 | Terrestrial Optical Fiber Drop | 1.27 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2984 | 3 | 984 | 2984 | 0501734020 | Region V (Bicol Region) | Camarines Sur | Sipocot | Impig | 13.7764 | 122.9772 | R | 3331 | 793 | 238 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03065-C10 | PTCI/MIDC | 13.7778 | 122.9784 | 0.2 | Terrestrial Optical Fiber Drop | 1.6 | 0.89 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2985 | 3 | 985 | 2985 | 0300812008 | Region III (Central Luzon) | Bataan | Samal | San Juan | 14.7697 | 120.5395 | R | 4655 | 1293 | 388 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | N95 | FTAP Smart | 14.7656 | 120.5422 | 0.54 | Terrestrial Optical Fiber Drop | 3.62 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2986 | 3 | 986 | 2986 | 0105511068 | Region I (Ilocos Region) | Pangasinan | Bayambang | Telbang | 15.7977 | 120.4535 | R | 2572 | 714 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00572 | Edgepoint | 15.8049 | 120.457 | 0.88 | Terrestrial Optical Fiber Drop | 2.07 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2987 | 3 | 987 | 2987 | 0301418020 | Region III (Central Luzon) | Bulacan | Pulilan | Penabatan | 14.904 | 120.8482 | R | 2485 | 710 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01048 | Edgepoint | 14.9046 | 120.8412 | 0.3 | Terrestrial Optical Fiber Drop | 0.32 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2988 | 3 | 988 | 2988 | 0702208009 | Region VII (Central Visayas) | Cebu | Balamban | Cambuhawe | 10.5 | 123.719 | R | 3845 | 1011 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 0.74 | Terrestrial Optical Fiber Drop | 1.13 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2989 | 3 | 989 | 2989 | 0500503044 | Region V (Bicol Region) | Albay | Daraga | Sagpon | 13.1486 | 123.7261 | U | 5321 | 1297 | 389 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02799-C10 | PTCI/MIDC | 13.1485 | 123.7198 | 0.68 | Terrestrial Optical Fiber Drop | 1.56 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2990 | 3 | 990 | 2990 | 0304928001 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | Cojuangco | 15.4891 | 120.971 | U | 2838 | 810 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNEG0040 | PTCI/MIDC | 15.4927 | 120.972 | 0.41 | Terrestrial Optical Fiber Drop | 1.34 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2991 | 3 | 991 | 2991 | 1705318031 | MIMAROPA Region | Palawan | Roxas | Barangay IV | 10.3199 | 119.3333 | U | 7469 | 1915 | 575 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02628-C09 | PTCI/MIDC | 10.3301 | 119.3487 | 2.03 | Terrestrial Optical Fiber Drop | 1.24 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2992 | 3 | 992 | 2992 | 0301407011 | Region III (Central Luzon) | Bulacan | Calumpit | Gatbuca | 14.9228 | 120.769 | U | 6673 | 1906 | 572 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01032 | Edgepoint | 14.9253 | 120.766 | 0.42 | Terrestrial Optical Fiber Drop | 1.84 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2993 | 3 | 993 | 2993 | 0501701017 | Region V (Bicol Region) | Camarines Sur | Baao | San Jose | 13.4877 | 123.3827 | R | 2419 | 575 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E02841-C10 | PTCI/MIDC | 13.4681 | 123.3583 | 0.49 | Terrestrial Optical Fiber Drop | 4 | 3.29 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2994 | 3 | 994 | 2994 | 0304925001 | Region III (Central Luzon) | Nueva Ecija | San Isidro | Alua | 15.3097 | 120.8941 | U | 5621 | 1606 | 482 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00767 | Edgepoint | 15.3064 | 120.8903 | 0.55 | Terrestrial Optical Fiber Drop | 1.32 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2995 | 3 | 995 | 2995 | 0301408003 | Region III (Central Luzon) | Bulacan | Guiguinto | Ilang-Ilang | 14.8391 | 120.866 | U | 6006 | 1716 | 515 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01144 | Edgepoint | 14.8392 | 120.8702 | 0.45 | Terrestrial Optical Fiber Drop | 1.35 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2996 | 3 | 996 | 2996 | 0205004026 | Region II (Cagayan Valley) | Nueva Vizcaya | Bambang | Magsaysay Hills | 16.3792 | 121.1114 | R | 2200 | 578 | 173 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUV-02410 | Edgepoint | 16.3852 | 121.1076 | 0.78 | Terrestrial Optical Fiber Drop | 1.08 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2997 | 3 | 997 | 2997 | 0305408009 | Region III (Central Luzon) | Pampanga | Lubao | Don Ignacio Dimson | 14.9247 | 120.5687 | U | 6051 | 1512 | 454 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03224-B07 | PTCI/MIDC | 14.9164 | 120.5576 | 0.88 | Terrestrial Optical Fiber Drop | 2.21 | 0.95 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2998 | 3 | 998 | 2998 | 0601902017 | Region VI (Western Visayas) | Capiz | Dao | Nasunogan | 11.3717 | 122.6753 | R | 2942 | 774 | 232 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060243 | FTAP Globe | 11.3433 | 122.6758 | 3.15 | Terrestrial Optical Fiber Drop | 2.83 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-2999 | 3 | 999 | 2999 | 0301422027 | Region III (Central Luzon) | Bulacan | San Rafael | Sampaloc | 14.9801 | 120.9297 | U | 4683 | 1338 | 401 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030512 | FTAP Globe | 14.9818 | 120.9272 | 0.33 | Terrestrial Optical Fiber Drop | 2.05 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3000 | 3 | 1000 | 3000 | 0305416005 | Region III (Central Luzon) | Pampanga | City of San Fernando | Dela Paz Norte | 15.0866 | 120.6284 | U | 6120 | 1530 | 459 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030476 | FTAP Globe | 15.0875 | 120.6226 | 0.64 | Terrestrial Optical Fiber Drop | 1.88 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)

## Batch 4 (3,001 - 4,000)
5G FWA Candidate Site Schedule — Batch 4 (Expansion 1,000 Sites)
Carrier-Grade Candidate Siting Data for Turnkey Bidding (Lots 1, 2, 4, 5) ¦ Band n50 SA Architecture
Site ID | Batch | Batch Rank | Overall Rank | PSGC Code | Region | Province | Municipality | Barangay | Latitude | Longitude | Urban / Rural | 2024 Population | Households | Target Subscribers | Carrier Spectrum | Initial BTS | Civil Siting Category | Tower Screening Class | Nearest Tower ID | Nearest TowerCo | Nearest Tower Latitude | Nearest Tower Longitude | Dist to Tower (km) | Transmission Medium | Dist to Node (km) | Dist to Line (km) | Power Arrangement
FWA-SITE-3001 | 4 | 1 | 3001 | 0306910028 | Region III (Central Luzon) | Tarlac | Paniqui | Samput | 15.6498 | 120.5829 | U | 6522 | 1672 | 502 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00618 | Edgepoint | 15.6463 | 120.5901 | 0.86 | Terrestrial Optical Fiber Drop | 2.08 | 0.37 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3002 | 4 | 2 | 3002 | 0501731023 | Region V (Bicol Region) | Camarines Sur | Sagñay | Turague | 13.5896 | 123.5231 | R | 3620 | 861 | 258 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH050090 | FTAP Globe | 13.6036 | 123.5204 | 1.58 | Terrestrial Optical Fiber Drop | 1.4 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3003 | 4 | 3 | 3003 | 0401022020 | Region IV-A (CALABARZON) | Batangas | San Jose | Natunuan | 13.8837 | 121.098 | R | 1927 | 535 | 161 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH040530 | FTAP Globe | 13.8725 | 121.1036 | 0.57 | Terrestrial Optical Fiber Drop | 0.9 | 0.27 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3004 | 4 | 4 | 3004 | 0401010012 | Region IV-A (CALABARZON) | Batangas | Ibaan | Matala | 13.8292 | 121.1356 | R | 3107 | 863 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | LDIC_BAT_0003 | LDIC | 13.8214 | 121.1316 | 1.42 | Terrestrial Optical Fiber Drop | 1.67 | 0.07 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3005 | 4 | 5 | 3005 | 0500503035 | Region V (Bicol Region) | Albay | Daraga | Maroroy | 13.1504 | 123.724 | U | 5443 | 1327 | 398 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02799-C10 | PTCI/MIDC | 13.1485 | 123.7198 | 0.49 | Terrestrial Optical Fiber Drop | 1.38 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3006 | 4 | 6 | 3006 | 0305409027 | Region III (Central Luzon) | Pampanga | Mabalacat City | Sapang Biabas | 15.2058 | 120.607 | U | 30871 | 7717 | 2315 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01606-B07 | PTCI/MIDC | 15.2031 | 120.6095 | 0.39 | Terrestrial Optical Fiber Drop | 1.87 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3007 | 4 | 7 | 3007 | 0506203057 | Region V (Bicol Region) | Sorsogon | Bulan | San Vicente | 12.6627 | 123.8813 | U | 5414 | 1353 | 406 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050228 | FTAP Globe | 12.6672 | 123.8801 | 0.52 | Terrestrial Optical Fiber Drop | 1.21 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3008 | 4 | 8 | 3008 | 0105506004 | Region I (Ilocos Region) | Pangasinan | Asingan | Bantog | 16.0099 | 120.6913 | R | 4368 | 1213 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01733-B07 | PTCI/MIDC | 16.0117 | 120.6906 | 0.22 | Terrestrial Optical Fiber Drop | 2.35 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3009 | 4 | 9 | 3009 | 1705205017 | MIMAROPA Region | Oriental Mindoro | City of Calapan | Canubing I | 13.3579 | 121.1355 | R | 3998 | 1025 | 308 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH170064 | FTAP Globe | 13.3808 | 121.1359 | 2.54 | Terrestrial Optical Fiber Drop | 3.33 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3010 | 4 | 10 | 3010 | 0306909008 | Region III (Central Luzon) | Tarlac | Moncada | Burgos | 15.7357 | 120.5771 | R | 2354 | 603 | 181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.37 | Terrestrial Optical Fiber Drop | 1.53 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3011 | 4 | 11 | 3011 | 0304902014 | Region III (Central Luzon) | Nueva Ecija | Bongabon | Magtanggol | 15.6344 | 121.1479 | R | 1566 | 447 | 134 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-NUE-02493 | Edgepoint | 15.6344 | 121.1471 | 0.09 | Terrestrial Optical Fiber Drop | 1.16 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3012 | 4 | 12 | 3012 | 0300804024 | Region III (Central Luzon) | Bataan | Dinalupihan | Pag-asa | 14.8506 | 120.4195 | R | 2576 | 715 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0006 | PTCI/MIDC | 14.8469 | 120.4161 | 0.55 | Terrestrial Optical Fiber Drop | 2.4 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3013 | 4 | 13 | 3013 | 0803738109 | Region VIII (Eastern Visayas) | Leyte | Ormoc City | Bagong Buhay | 11.0299 | 124.5935 | U | 6059 | 1594 | 478 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLEG0101 | PTCI/MIDC | 11.0267 | 124.5934 | 0.35 | Terrestrial Optical Fiber Drop | 0.9 | 0.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3014 | 4 | 14 | 3014 | 0405811012 | Region IV-A (CALABARZON) | Rizal | San Mateo | Banaba | 14.6726 | 121.1128 | U | 26718 | 7421 | 2226 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F00282-A01 | PTCI/MIDC | 14.6721 | 121.1122 | 0.09 | Terrestrial Optical Fiber Drop | 1.62 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3015 | 4 | 15 | 3015 | 0405809008 | Region IV-A (CALABARZON) | Rizal | Morong | San Pedro | 14.5105 | 121.2415 | U | 5797 | 1610 | 483 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040071 | FTAP Globe | 14.5114 | 121.2446 | 0.34 | Terrestrial Optical Fiber Drop | 1.24 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3016 | 4 | 16 | 3016 | 0300803004 | Region III (Central Luzon) | Bataan | City of Balanga | Munting Batangas | 14.6829 | 120.5146 | R | 3468 | 963 | 289 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BAN-01391 | Edgepoint | 14.682 | 120.5099 | 0.52 | Terrestrial Optical Fiber Drop | 2.71 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3017 | 4 | 17 | 3017 | 1606711010 | Region XIII (Caraga) | Surigao del Norte | Gigaquit | San Isidro | 9.5785 | 125.6901 | R | 4262 | 1039 | 312 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130016 | FTAP BTS | 9.5619 | 125.7137 | 2.88 | Terrestrial Optical Fiber Drop | 18.58 | 1.97 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3018 | 4 | 18 | 3018 | 0304904010 | Region III (Central Luzon) | Nueva Ecija | Cabiao | Palasinan | 15.2536 | 120.8563 | R | 3900 | 1114 | 334 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00787 | Edgepoint | 15.2494 | 120.8606 | 0.67 | Terrestrial Optical Fiber Drop | 1.51 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3019 | 4 | 19 | 3019 | 1130700072 | Region XI (Davao Region) | Davao del Sur | City of Davao | Marapangi | 7.0152 | 125.4871 | U | 8284 | 2436 | 731 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH110211 | FTAP BTS | 7.0191 | 125.4856 | 0.46 | Terrestrial Optical Fiber Drop | 1.47 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3020 | 4 | 20 | 3020 | 0603018014 | Region VI (Western Visayas) | Iloilo | Dumangas | Cansilayan | 10.8333 | 122.717 | R | 1500 | 394 | 118 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0104 | PTCI/MIDC | 10.8418 | 122.7189 | 0.97 | Terrestrial Optical Fiber Drop | 1.14 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3021 | 4 | 21 | 3021 | 0402118048 | Region IV-A (CALABARZON) | Cavite | Silang | Ulat | 14.1468 | 120.9886 | R | 3383 | 995 | 299 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02238-C08 | PTCI/MIDC | 14.1436 | 120.9888 | 0.36 | Terrestrial Optical Fiber Drop | 2.44 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3022 | 4 | 22 | 3022 | 1606814008 | Region XIII (Caraga) | Surigao del Sur | Marihatag | Poblacion | 8.7951 | 126.2949 | R | 4223 | 1030 | 309 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130012 | FTAP BTS | 8.7748 | 126.249 | 4.88 | Terrestrial Optical Fiber Drop | 33.12 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3023 | 4 | 23 | 3023 | 0604505004 | Region VI (Western Visayas) | Negros Occidental | Calatrava | Bantayanon | 10.5846 | 123.4761 | R | 4975 | 1344 | 403 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_NEC_0009 | LDIC | 10.5884 | 123.4776 | 0.43 | Terrestrial Optical Fiber Drop | 8.32 | 0.17 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3024 | 4 | 24 | 3024 | 1430300088 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Pinsao Proper | 16.4277 | 120.5819 | U | 8408 | 2212 | 664 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1849 | FTAP Smart | 16.3797 | 120.5438 | 0.51 | Terrestrial Optical Fiber Drop | 1.28 | 1.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3025 | 4 | 25 | 3025 | 0305411012 | Region III (Central Luzon) | Pampanga | Magalang | San Miguel | 15.2253 | 120.658 | R | 2960 | 740 | 222 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00799 | Edgepoint | 15.2184 | 120.6592 | 0.78 | Terrestrial Optical Fiber Drop | 2.32 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3026 | 4 | 26 | 3026 | 0304930032 | Region III (Central Luzon) | Nueva Ecija | Talavera | La Torre | 15.5648 | 120.9191 | U | 5315 | 1518 | 455 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1217 | FTAP Smart | 15.5622 | 120.9206 | 0.32 | Terrestrial Optical Fiber Drop | 1.92 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3027 | 4 | 27 | 3027 | 0702208022 | Region VII (Central Visayas) | Cebu | Balamban | Pondol | 10.4906 | 123.7166 | U | 10482 | 2758 | 827 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0008 | PTCI/MIDC | 10.4966 | 123.7132 | 0.77 | Terrestrial Optical Fiber Drop | 2.07 | 0.39 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3028 | 4 | 28 | 3028 | 0402105072 | Region IV-A (CALABARZON) | Cavite | City of Cavite | Barangay 42-C | 14.483 | 120.8971 | R | 1888 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTMMR0008 | PTCI/MIDC | 14.4542 | 120.9788 | 0.3 | Terrestrial Optical Fiber Drop | 1.37 | 4.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3029 | 4 | 29 | 3029 | 0730600068 | Region VII (Central Visayas) | Cebu | City of Cebu | San Nicolas Central | 10.294 | 123.8903 | U | 5333 | 1666 | 500 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCER0028 | PTCI/MIDC | 10.2941 | 123.891 | 0.09 | Terrestrial Optical Fiber Drop | 1.22 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3030 | 4 | 30 | 3030 | 0201523003 | Region II (Cagayan Valley) | Cagayan | Santa Ana | Centro | 18.455 | 122.1441 | U | 6489 | 1663 | 499 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01126-B06 | PTCI/MIDC | 18.4557 | 122.1429 | 0.15 | Terrestrial Optical Fiber Drop | 2.27 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3031 | 4 | 31 | 3031 | 0402109055 | Region IV-A (CALABARZON) | Cavite | City of Imus | Magdalo | 14.407 | 120.936 | R | 4715 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CAV_0001 | LDIC | 14.4497 | 120.9334 | 0.46 | Terrestrial Optical Fiber Drop | 0.5 | 4.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3032 | 4 | 32 | 3032 | 0603005011 | Region VI (Western Visayas) | Iloilo | Balasan | Lawis | 11.4669 | 123.1128 | R | 2417 | 636 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060233 | FTAP Globe | 11.4679 | 123.0993 | 1.48 | Terrestrial Optical Fiber Drop | 1.78 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3033 | 4 | 33 | 3033 | 1004302018 | Region X (Northern Mindanao) | Misamis Oriental | Balingasag | Mandangoa | 8.7664 | 124.779 | U | 4498 | 1153 | 346 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100040 | FTAP BTS | 8.7788 | 124.7843 | 1.5 | Terrestrial Optical Fiber Drop | 1.82 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3034 | 4 | 34 | 3034 | 0305402005 | Region III (Central Luzon) | Pampanga | Apalit | Capalangan | 14.9299 | 120.7674 | U | 7845 | 1961 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02350-B07 | PTCI/MIDC | 14.9296 | 120.7683 | 0.1 | Terrestrial Optical Fiber Drop | 2.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3035 | 4 | 35 | 3035 | 0431200014 | Region IV-A (CALABARZON) | Quezon | City of Lucena | Bocohan | 13.9579 | 121.5936 | U | 6394 | 1598 | 479 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040410 | FTAP Globe | 13.9627 | 121.5855 | 1.03 | Terrestrial Optical Fiber Drop | 1.67 | 1.38 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3036 | 4 | 36 | 3036 | 0631000073 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Jalandoni Estate-Lapuz | 10.7026 | 122.575 | R | 1903 | 453 | 136 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTILG0087 | PTCI/MIDC | 10.7076 | 122.5713 | 0.69 | Terrestrial Optical Fiber Drop | 1.46 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3037 | 4 | 37 | 3037 | 0304928033 | Region III (Central Luzon) | Nueva Ecija | Santa Rosa | San Josep | 15.4341 | 120.9181 | U | 2937 | 839 | 252 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNEG0006 | PTCI/MIDC | 15.4304 | 120.9236 | 0.71 | Terrestrial Optical Fiber Drop | 0.5 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3038 | 4 | 38 | 3038 | 0103314022 | Region I (Ilocos Region) | La Union | City of San Fernando | Catbangen | 16.6126 | 120.3124 | U | 9670 | 2613 | 784 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH010094 | FTAP Globe | 16.6084 | 120.309 | 0.59 | Terrestrial Optical Fiber Drop | 1.15 | 0.4 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3039 | 4 | 39 | 3039 | 0405619059 | Region IV-A (CALABARZON) | Quezon | Gumaca | Villa Nava | 13.917 | 122.1 | R | 3091 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040488 | FTAP Globe | 13.9156 | 122.1017 | 0.24 | Terrestrial Optical Fiber Drop | 1.06 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3040 | 4 | 40 | 3040 | 0405811001 | Region IV-A (CALABARZON) | Rizal | San Mateo | Ampid I | 14.6778 | 121.1168 | U | 26178 | 7271 | 2181 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTRIG0046 | PTCI/MIDC | 14.6785 | 121.1182 | 0.17 | Terrestrial Optical Fiber Drop | 1.01 | 0.41 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3041 | 4 | 41 | 3041 | 0304919016 | Region III (Central Luzon) | Nueva Ecija | City of Palayan | Doña Josefa | 15.4436 | 121.1235 | R | 2206 | 630 | 189 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-NUE-02328 | Edgepoint | 15.5029 | 121.0799 | 2.33 | Terrestrial Optical Fiber Drop | 4.59 | 1.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3042 | 4 | 42 | 3042 | 0205005027 | Region II (Cagayan Valley) | Nueva Vizcaya | Bayombong | Santa Rosa | 16.489 | 121.1648 | R | 2959 | 778 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNVG0023 | PTCI/MIDC | 16.4915 | 121.1569 | 0.89 | Terrestrial Optical Fiber Drop | 1.91 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3043 | 4 | 43 | 3043 | 0301403014 | Region III (Central Luzon) | Bulacan | Baliuag | Poblacion | 14.9574 | 120.8988 | U | 11052 | 3157 | 947 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.53 | Terrestrial Optical Fiber Drop | 1.57 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3044 | 4 | 44 | 3044 | 0506216054 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | San Isidro | 13.0014 | 124.0395 | R | 3108 | 777 | 233 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_SOR_0001 | LDIC | 12.9853 | 123.9959 | 0.82 | Terrestrial Optical Fiber Drop | 3.59 | 2.79 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3045 | 4 | 45 | 3045 | 0704621019 | Region VII (Central Visayas) | Negros Oriental | City of Tanjay | San Jose | 9.5089 | 123.1402 | R | 4338 | 1141 | 342 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0039 | PTCI/MIDC | 9.5016 | 123.1412 | 0.82 | Terrestrial Optical Fiber Drop | 9.23 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3046 | 4 | 46 | 3046 | 0908305038 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Veteran's Village | 7.7734 | 122.5719 | U | 9384 | 2234 | 670 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0027 | PTCI/MIDC | 7.769 | 122.5718 | 0.49 | Terrestrial Optical Fiber Drop | 1.48 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3047 | 4 | 47 | 3047 | 0306916024 | Region III (Central Luzon) | Tarlac | City of Tarlac | Calingcuan | 15.4876 | 120.6225 | R | 3837 | 983 | 295 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-TAR-00708 | Edgepoint | 15.4836 | 120.623 | 0.45 | Terrestrial Optical Fiber Drop | 1.35 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3048 | 4 | 48 | 3048 | 0105522017 | Region I (Ilocos Region) | Pangasinan | Lingayen | Libsong East | 16.0299 | 120.2407 | U | 6519 | 1810 | 543 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAN-00464 | Edgepoint | 16.0091 | 120.2223 | 0.54 | Terrestrial Optical Fiber Drop | 1.15 | 0.62 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3049 | 4 | 49 | 3049 | 1130700154 | Region XI (Davao Region) | Davao del Sur | City of Davao | Barangay 21-C | 7.0863 | 125.6129 | U | 7568 | 2225 | 668 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_DAS_0001 | LDIC | 7.1827 | 125.4633 | 0.91 | Terrestrial Optical Fiber Drop | 1.02 | 0.2 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3050 | 4 | 50 | 3050 | 0301418005 | Region III (Central Luzon) | Bulacan | Pulilan | Dampol I | 14.9021 | 120.833 | U | 7077 | 2022 | 607 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBUG0044 | PTCI/MIDC | 14.9011 | 120.8315 | 0.2 | Terrestrial Optical Fiber Drop | 1.89 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3051 | 4 | 51 | 3051 | 0601905015 | Region VI (Western Visayas) | Capiz | Ivisan | Santa Cruz | 11.5206 | 122.7094 | R | 2123 | 558 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH060229 | FTAP Globe | 11.5171 | 122.6938 | 1.75 | Terrestrial Optical Fiber Drop | 1.68 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3052 | 4 | 52 | 3052 | 0500508027 | Region V (Bicol Region) | Albay | City of Ligao | Layon | 13.2411 | 123.5624 | R | 3371 | 822 | 247 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050155 | FTAP Globe | 13.2473 | 123.5607 | 0.71 | Terrestrial Optical Fiber Drop | 2.94 | 0.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3053 | 4 | 53 | 3053 | 1600306004 | Region XIII (Caraga) | Agusan del Sur | Prosperidad | Poblacion | 8.5985 | 125.9134 | U | 13580 | 3482 | 1045 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH130086 | FTAP Globe | 8.6223 | 125.9094 | 0.48 | Terrestrial Optical Fiber Drop | 1.2 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3054 | 4 | 54 | 3054 | 0401009011 | Region IV-A (CALABARZON) | Batangas | Cuenca | Labac | 13.8954 | 121.0582 | R | 2286 | 635 | 191 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH040513 | FTAP Globe | 13.8972 | 121.0481 | 1.11 | Terrestrial Optical Fiber Drop | 1.01 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3055 | 4 | 55 | 3055 | 1030500045 | Region X (Northern Mindanao) | Misamis Oriental | City of Cagayan De Oro | Consolacion | 8.4912 | 124.6458 | U | 9566 | 2657 | 797 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLR0026 | PTCI/MIDC | 8.4839 | 124.6532 | 1.15 | Terrestrial Optical Fiber Drop | 1.02 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3056 | 4 | 56 | 3056 | 1004308049 | Region X (Northern Mindanao) | Misamis Oriental | City of Gingoog | Barangay 24 | 8.8273 | 125.0957 | R | 3442 | 882 | 265 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100113 | FTAP Globe | 8.825 | 125.1026 | 0.8 | Terrestrial Optical Fiber Drop | 1.05 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3057 | 4 | 57 | 3057 | 1001308035 | Region X (Northern Mindanao) | Bukidnon | Kibawe | West Kibawe | 7.5751 | 124.9877 | U | 2982 | 784 | 235 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH100062 | FTAP BTS | 7.5747 | 124.9878 | 0.05 | Terrestrial Optical Fiber Drop | 1.29 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3058 | 4 | 58 | 3058 | 0730600008 | Region VII (Central Visayas) | Cebu | City of Cebu | Basak San Nicolas | 10.286 | 123.8707 | U | 39012 | 12191 | 3657 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH070008 | FTAP BTS | 10.2831 | 123.8687 | 0.39 | Terrestrial Optical Fiber Drop | 1.13 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3059 | 4 | 59 | 3059 | 0301403001 | Region III (Central Luzon) | Bulacan | Baliuag | Bagong Nayon | 14.9597 | 120.8988 | U | 4441 | 1268 | 380 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-00991 | Edgepoint | 14.9621 | 120.8979 | 0.28 | Terrestrial Optical Fiber Drop | 1.74 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3060 | 4 | 60 | 3060 | 0403421004 | Region IV-A (CALABARZON) | Laguna | Pangil | Isla | 14.3996 | 121.4711 | R | 3151 | 954 | 286 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040124 | FTAP Globe | 14.4013 | 121.4743 | 0.39 | Terrestrial Optical Fiber Drop | 1.14 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3061 | 4 | 61 | 3061 | 1430300040 | Cordillera Administrative Region (CAR) | Benguet | City of Baguio | Gibraltar | 16.4186 | 120.6229 | U | 8088 | 2128 | 638 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BEN-00333 | Edgepoint | 16.4171 | 120.6255 | 0.32 | Terrestrial Optical Fiber Drop | 2.01 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3062 | 4 | 62 | 3062 | 0631000041 | Region VI (Western Visayas) | Iloilo | City of Iloilo | Cubay | 10.7325 | 122.5641 | U | 6979 | 1661 | 498 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060267 | FTAP Globe | 10.7314 | 122.5613 | 0.33 | Terrestrial Optical Fiber Drop | 1.46 | 0.43 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3063 | 4 | 63 | 3063 | 0301407022 | Region III (Central Luzon) | Bulacan | Calumpit | Pungo | 14.9018 | 120.79 | U | 9959 | 2845 | 854 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030552 | FTAP Globe | 14.8968 | 120.7949 | 0.76 | Terrestrial Optical Fiber Drop | 2.44 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3064 | 4 | 64 | 3064 | 0401005051 | Region IV-A (CALABARZON) | Batangas | Batangas City | Pallocan Kanluran | 13.7542 | 121.0662 | U | 7057 | 1960 | 588 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E03125-C08 | PTCI/MIDC | 13.756 | 121.0657 | 0.21 | Terrestrial Optical Fiber Drop | 1.36 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3065 | 4 | 65 | 3065 | 0402103066 | Region IV-A (CALABARZON) | Cavite | City of Bacoor | Talaba II | 14.4614 | 120.9604 | U | 15394 | 4527 | 1358 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH000665 | FTAP Globe | 14.4686 | 121.0038 | 0.05 | Terrestrial Optical Fiber Drop | 0.51 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3066 | 4 | 66 | 3066 | 0506216015 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Cambulaga | 12.968 | 123.9899 | R | 5054 | 1263 | 379 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 1.42 | Terrestrial Optical Fiber Drop | 1.48 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3067 | 4 | 67 | 3067 | 0600416006 | Region VI (Western Visayas) | Aklan | Numancia | Bulwang | 11.7196 | 122.356 | U | 5334 | 1367 | 410 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060216 | FTAP Globe | 11.7192 | 122.3578 | 0.2 | Terrestrial Optical Fiber Drop | 2.73 | 0.44 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3068 | 4 | 68 | 3068 | 1401111003 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Bulalacao | 16.8422 | 120.8112 | R | 3453 | 986 | 296 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | E03214-B05 | PTCI/MIDC | 16.858 | 120.7935 | 2.58 | Terrestrial Optical Fiber Drop | 2.14 | 0.6 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3069 | 4 | 69 | 3069 | 0402120001 | Region IV-A (CALABARZON) | Cavite | Tanza | Amaya I | 14.3832 | 120.8337 | U | 14142 | 4159 | 1248 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040133 | FTAP Globe | 14.3857 | 120.8304 | 0.45 | Terrestrial Optical Fiber Drop | 1.88 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3070 | 4 | 70 | 3070 | 0704614030 | Region VII (Central Visayas) | Negros Oriental | Mabinay | Poblacion | 9.7208 | 122.9352 | U | 7357 | 1936 | 581 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNLG0034 | PTCI/MIDC | 9.7257 | 122.9276 | 1 | Terrestrial Optical Fiber Drop | 1.11 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3071 | 4 | 71 | 3071 | 1705203012 | MIMAROPA Region | Oriental Mindoro | Bongabong | Labasan | 12.778 | 121.4704 | R | 4730 | 1212 | 364 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH170111 | FTAP Globe | 12.7816 | 121.4714 | 0.45 | Terrestrial Optical Fiber Drop | 4.21 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3072 | 4 | 72 | 3072 | 0305406025 | Region III (Central Luzon) | Pampanga | Floridablanca | San Isidro | 15.0077 | 120.5116 | R | 2657 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01623-B07 | PTCI/MIDC | 15.0122 | 120.5175 | 0.81 | Terrestrial Optical Fiber Drop | 2.06 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3073 | 4 | 73 | 3073 | 0704603002 | Region VII (Central Visayas) | Negros Oriental | Bacong | Banilad | 9.2708 | 123.2885 | U | 5739 | 1510 | 453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070271 | FTAP Globe | 9.2764 | 123.2901 | 0.65 | Terrestrial Optical Fiber Drop | 2.01 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3074 | 4 | 74 | 3074 | 0304903033 | Region III (Central Luzon) | Nueva Ecija | City of Cabanatuan | Dionisio S. Garcia | 15.4722 | 120.9609 | U | 8071 | 2306 | 692 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-NUE-00717 | Edgepoint | 15.4684 | 120.9565 | 0.63 | Terrestrial Optical Fiber Drop | 1.05 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3075 | 4 | 75 | 3075 | 0403403018 | Region IV-A (CALABARZON) | Laguna | City of Biñan | Santo Niño | 14.328 | 121.0823 | U | 8480 | 2569 | 771 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLAG0035 | PTCI/MIDC | 14.3307 | 121.078 | 0.55 | Terrestrial Optical Fiber Drop | 1.37 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3076 | 4 | 76 | 3076 | 0702210012 | Region VII (Central Visayas) | Cebu | Barili | Giwanon | 10.1115 | 123.5274 | R | 2101 | 552 | 166 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH070062 | FTAP BTS | 10.116 | 123.5147 | 0.87 | Terrestrial Optical Fiber Drop | 2.06 | 1.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3077 | 4 | 77 | 3077 | 0402111021 | Region IV-A (CALABARZON) | Cavite | Kawit | Tabon III | 14.4422 | 120.904 | R | 2424 | 712 | 214 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | S6811 | FTAP Smart | 14.4193 | 120.8997 | 0.78 | Terrestrial Optical Fiber Drop | 2.67 | 0.61 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3078 | 4 | 78 | 3078 | 0500506005 | Region V (Bicol Region) | Albay | City of Legazpi | Bgy. 1 - Em's Barrio | 13.1463 | 123.7301 | R | 3334 | 813 | 244 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050174 | FTAP Globe | 13.1521 | 123.7315 | 0.66 | Terrestrial Optical Fiber Drop | 1.32 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3079 | 4 | 79 | 3079 | 0305416024 | Region III (Central Luzon) | Pampanga | City of San Fernando | San Agustin | 15.0418 | 120.6693 | U | 23914 | 5978 | 1793 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00916 | Edgepoint | 15.0445 | 120.6724 | 0.44 | Terrestrial Optical Fiber Drop | 1.12 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3080 | 4 | 80 | 3080 | 0402109059 | Region IV-A (CALABARZON) | Cavite | City of Imus | Malagasang I-D | 14.4025 | 120.9407 | R | 4925 | 1448 | 434 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCAM0355 | PTCI/MIDC | 14.4068 | 120.8907 | 0.98 | Terrestrial Optical Fiber Drop | 0.5 | 4.93 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3081 | 4 | 81 | 3081 | 0401013014 | Region IV-A (CALABARZON) | Batangas | Lian | Malaruhatan | 14.0378 | 120.6573 | R | 4960 | 1377 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E00132-C08 | PTCI/MIDC | 14.0389 | 120.6568 | 0.13 | Terrestrial Optical Fiber Drop | 4.44 | 0.45 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3082 | 4 | 82 | 3082 | 1600312003 | Region XIII (Caraga) | Agusan del Sur | Trento | Kapatungan | 8.0652 | 126.0171 | R | 5000 | 1282 | 385 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH130102 | FTAP Globe | 8.0802 | 126.0361 | 1.39 | Terrestrial Optical Fiber Drop | 5.51 | 2.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3083 | 4 | 83 | 3083 | 0402120040 | Region IV-A (CALABARZON) | Cavite | Tanza | Julugan VI | 14.4044 | 120.8466 | R | 5236 | 1540 | 462 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02478-C08 | PTCI/MIDC | 14.3915 | 120.8482 | 0.34 | Terrestrial Optical Fiber Drop | 1.8 | 1.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3084 | 4 | 84 | 3084 | 0701205006 | Region VII (Central Visayas) | Bohol | Baclayon | Laya | 9.6177 | 123.9299 | R | 1114 | 278 | 83 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH070423 | FTAP Globe | 9.6107 | 123.9541 | 2.76 | Terrestrial Optical Fiber Drop | 0.9 | 0.06 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3085 | 4 | 85 | 3085 | 0305416022 | Region III (Central Luzon) | Pampanga | City of San Fernando | Quebiauan | 15.0566 | 120.665 | U | 11673 | 2918 | 875 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00909 | Edgepoint | 15.0517 | 120.6663 | 0.56 | Terrestrial Optical Fiber Drop | 2.44 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3086 | 4 | 86 | 3086 | 0300804038 | Region III (Central Luzon) | Bataan | Dinalupihan | Santo Niño | 14.8765 | 120.4591 | R | 3633 | 1009 | 303 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH030118 | FTAP BTS | 14.8738 | 120.4626 | 0.48 | Terrestrial Optical Fiber Drop | 1.06 | 0.59 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3087 | 4 | 87 | 3087 | 0500517035 | Region V (Bicol Region) | Albay | City of Tabaco | Salvacion | 13.3485 | 123.7126 | U | 3855 | 940 | 282 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTALG0020 | PTCI/MIDC | 13.3645 | 123.7226 | 0.48 | Terrestrial Optical Fiber Drop | 2.08 | 0.86 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3088 | 4 | 88 | 3088 | 0907322011 | Region IX (Zamboanga Peninsula) | Zamboanga del Sur | City of Pagadian | Bulatok | 7.8473 | 123.4459 | U | 5778 | 1481 | 444 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH090131 | FTAP Globe | 7.8452 | 123.4458 | 0.24 | Terrestrial Optical Fiber Drop | 1.98 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3089 | 4 | 89 | 3089 | 0500503025 | Region V (Bicol Region) | Albay | Daraga | Kilicao | 13.16 | 123.7155 | R | 4947 | 1206 | 362 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050173 | FTAP Globe | 13.155 | 123.7161 | 0.56 | Terrestrial Optical Fiber Drop | 1.48 | 0.46 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3090 | 4 | 90 | 3090 | 0301410056 | Region III (Central Luzon) | Bulacan | City of Malolos | Cofradia | 14.8422 | 120.8316 | U | 4817 | 1376 | 413 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-BUL-01130 | Edgepoint | 14.8467 | 120.8352 | 0.63 | Terrestrial Optical Fiber Drop | 2.09 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3091 | 4 | 91 | 3091 | 0604518007 | Region VI (Western Visayas) | Negros Occidental | Manapla | Punta Mesa | 10.935 | 123.1131 | U | 7887 | 2131 | 639 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060323 | FTAP Globe | 10.9526 | 123.1256 | 2.38 | Terrestrial Optical Fiber Drop | 2.42 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3092 | 4 | 92 | 3092 | 1030900030 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Tubod | 8.2137 | 124.2427 | U | 33702 | 8868 | 2660 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100173 | FTAP Globe | 8.2092 | 124.2416 | 0.51 | Terrestrial Optical Fiber Drop | 1.65 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3093 | 4 | 93 | 3093 | 0500512010 | Region V (Bicol Region) | Albay | Oas | Bongoran | 13.2534 | 123.5032 | R | 1823 | 444 | 133 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH050151 | FTAP Globe | 13.2593 | 123.5008 | 0.71 | Terrestrial Optical Fiber Drop | 1.17 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3094 | 4 | 94 | 3094 | 0702231009 | Region VII (Central Visayas) | Cebu | Medellin | Caputatan Sur | 11.1237 | 123.9685 | R | 2835 | 746 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070301 | FTAP Globe | 11.1209 | 123.9645 | 0.53 | Terrestrial Optical Fiber Drop | 1.74 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3095 | 4 | 95 | 3095 | 0305420008 | Region III (Central Luzon) | Pampanga | Santa Rita | San Matias | 14.9774 | 120.6207 | R | 3795 | 948 | 284 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH-PAM-00986 | Edgepoint | 14.9676 | 120.6177 | 1.14 | Terrestrial Optical Fiber Drop | 1.06 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3096 | 4 | 96 | 3096 | 0105533017 | Region I (Ilocos Region) | Pangasinan | San Fabian | Nibaliw East | 16.1265 | 120.4002 | R | 2555 | 709 | 213 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01759-B07 | PTCI/MIDC | 16.1277 | 120.4059 | 0.63 | Terrestrial Optical Fiber Drop | 1.18 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3097 | 4 | 97 | 3097 | 1102319023 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo East | 7.4497 | 125.8167 | U | 16035 | 4333 | 1300 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0031 | PTCI/MIDC | 7.4488 | 125.8199 | 0.36 | Terrestrial Optical Fiber Drop | 1.31 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3098 | 4 | 98 | 3098 | 1206315006 | Region XII (SOCCSKSARGEN) | South Cotabato | Tantangan | Maibo | 6.5522 | 124.7765 | R | 3398 | 943 | 283 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH120202 | FTAP BTS | 6.5643 | 124.7666 | 1.73 | Terrestrial Optical Fiber Drop | 19.05 | 1.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3099 | 4 | 99 | 3099 | 0704604032 | Region VII (Central Visayas) | Negros Oriental | City of Bais | Talungon | 9.6008 | 123.1195 | U | 3867 | 1017 | 305 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTNLG0004 | PTCI/MIDC | 9.5938 | 123.1254 | 1.01 | Terrestrial Optical Fiber Drop | 1.25 | 0.47 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3100 | 4 | 100 | 3100 | 0304927011 | Region III (Central Luzon) | Nueva Ecija | San Leonardo | Rizal District | 15.3608 | 120.9418 | R | 2606 | 744 | 223 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | E03195-B07 | PTCI/MIDC | 15.3513 | 120.9393 | 0.46 | Terrestrial Optical Fiber Drop | 0.68 | 0.24 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3101 | 4 | 101 | 3101 | 0630200002 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Alijis | 10.6311 | 122.9558 | U | 23511 | 6530 | 1959 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTNOG0116 | PTCI/MIDC | 10.6309 | 122.9621 | 0.69 | Terrestrial Optical Fiber Drop | 1.95 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3102 | 4 | 102 | 3102 | 0305407002 | Region III (Central Luzon) | Pampanga | Guagua | Bancal | 14.9612 | 120.6334 | U | 7190 | 1797 | 539 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-PAM-00990 | Edgepoint | 14.9623 | 120.6303 | 0.35 | Terrestrial Optical Fiber Drop | 1.38 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3103 | 4 | 103 | 3103 | 1401111008 | Cordillera Administrative Region (CAR) | Benguet | Mankayan | Paco | 16.8672 | 120.7793 | U | 4976 | 1421 | 426 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | 3946 | FTAP Smart | 16.8676 | 120.788 | 0.93 | Terrestrial Optical Fiber Drop | 2.25 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3104 | 4 | 104 | 3104 | 0500517029 | Region V (Bicol Region) | Albay | City of Tabaco | Pawa | 13.3656 | 123.7208 | R | 4520 | 1102 | 331 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTALG0020 | PTCI/MIDC | 13.3645 | 123.7226 | 0.23 | Terrestrial Optical Fiber Drop | 1.83 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3105 | 4 | 105 | 3105 | 0401014057 | Region IV-A (CALABARZON) | Batangas | City of Lipa | San Carlos | 13.9487 | 121.1517 | U | 7989 | 2219 | 666 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02802-C08 | PTCI/MIDC | 13.9457 | 121.149 | 0.44 | Terrestrial Optical Fiber Drop | 1.67 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3106 | 4 | 106 | 3106 | 0702250011 | Region VII (Central Visayas) | Cebu | City of Talisay | Mohon | 10.2492 | 123.8264 | U | 11545 | 3038 | 911 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070361 | FTAP Globe | 10.2444 | 123.8249 | 0.56 | Terrestrial Optical Fiber Drop | 1.71 | 0.19 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3107 | 4 | 107 | 3107 | 0401003003 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 1 | 13.9378 | 120.7323 | R | 2162 | 600 | 180 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01949-C08 | PTCI/MIDC | 13.9485 | 120.7323 | 0.62 | Terrestrial Optical Fiber Drop | 0.78 | 0.14 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3108 | 4 | 108 | 3108 | 1001321035 | Region X (Northern Mindanao) | Bukidnon | City of Valencia | Vintar | 7.9095 | 125.0938 | R | 2843 | 748 | 224 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH100202 | FTAP Globe | 7.9439 | 125.1039 | 1.23 | Terrestrial Optical Fiber Drop | 0.43 | 0.03 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3109 | 4 | 109 | 3109 | 1004319002 | Region X (Northern Mindanao) | Misamis Oriental | Medina | Bulwa | 8.9089 | 125.0165 | R | 1914 | 490 | 147 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTMLG0109 | PTCI/MIDC | 8.8977 | 125.027 | 1.7 | Terrestrial Optical Fiber Drop | 1.03 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3110 | 4 | 110 | 3110 | 1001314018 | Region X (Northern Mindanao) | Bukidnon | Manolo Fortich | San Miguel | 8.3826 | 124.8341 | U | 6171 | 1623 | 487 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100160 | FTAP Globe | 8.3902 | 124.836 | 0.87 | Terrestrial Optical Fiber Drop | 1.6 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3111 | 4 | 111 | 3111 | 1004319011 | Region X (Northern Mindanao) | Misamis Oriental | Medina | North Poblacion | 8.9136 | 125.0142 | U | 5827 | 1494 | 448 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTMLG0069 | PTCI/MIDC | 8.9279 | 125.0013 | 2.13 | Terrestrial Optical Fiber Drop | 1.19 | 0.48 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3112 | 4 | 112 | 3112 | 0704610013 | Region VII (Central Visayas) | Negros Oriental | City of Dumaguete | Daro | 9.3223 | 123.2948 | U | 6418 | 1688 | 506 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH070264 | FTAP Globe | 9.3258 | 123.2903 | 0.62 | Terrestrial Optical Fiber Drop | 2.12 | 0.49 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3113 | 4 | 113 | 3113 | 0908305006 | Region IX (Zamboanga Peninsula) | Zamboanga Sibugay | Ipil | Don Andres | 7.771 | 122.5814 | U | 7016 | 1670 | 501 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTZYG0003 | PTCI/MIDC | 7.7721 | 122.5856 | 0.48 | Terrestrial Optical Fiber Drop | 1.05 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3114 | 4 | 114 | 3114 | 0600401005 | Region VI (Western Visayas) | Aklan | Altavas | Ginictan | 11.5344 | 122.4757 | R | 1682 | 431 | 129 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | LDIC_AKN_0003 | LDIC | 11.5308 | 122.4544 | 2.35 | Terrestrial Optical Fiber Drop | 1.2 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3115 | 4 | 115 | 3115 | 0401003004 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 10 | 13.9341 | 120.7329 | R | 2777 | 771 | 231 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBGG0059 | PTCI/MIDC | 13.9557 | 120.7255 | 0.35 | Terrestrial Optical Fiber Drop | 1.16 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3116 | 4 | 116 | 3116 | 1003503015 | Region X (Northern Mindanao) | Lanao del Norte | Baroy | Poblacion | 8.025 | 123.78 | R | 3018 | 718 | 215 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLNG0004 | PTCI/MIDC | 8.0239 | 123.7821 | 0.26 | Terrestrial Optical Fiber Drop | 2.9 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3117 | 4 | 117 | 3117 | 0604523008 | Region VI (Western Visayas) | Negros Occidental | City of Sagay | Fabrica | 10.8958 | 123.3549 | R | 5129 | 1386 | 416 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTNOG0027 | PTCI/MIDC | 10.894 | 123.3521 | 0.37 | Terrestrial Optical Fiber Drop | 16.87 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3118 | 4 | 118 | 3118 | 0506216022 | Region V (Bicol Region) | Sorsogon | City of Sorsogon | Pangpang | 12.9847 | 123.9841 | U | 10402 | 2600 | 780 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02440-C10 | PTCI/MIDC | 12.9786 | 123.9826 | 0.69 | Terrestrial Optical Fiber Drop | 2.66 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3119 | 4 | 119 | 3119 | 0604524014 | Region VI (Western Visayas) | Negros Occidental | City of San Carlos | Barangay V | 10.4791 | 123.411 | U | 7527 | 2034 | 610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH060367 | FTAP Globe | 10.4828 | 123.4094 | 0.45 | Terrestrial Optical Fiber Drop | 1.06 | 0.34 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3120 | 4 | 120 | 3120 | 0301414009 | Region III (Central Luzon) | Bulacan | Obando | Panghulo | 14.6979 | 120.9463 | U | 13716 | 3918 | 1175 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02514 | Edgepoint | 14.6992 | 120.9457 | 0.16 | Terrestrial Optical Fiber Drop | 1.65 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3121 | 4 | 121 | 3121 | 0730600062 | Region VII (Central Visayas) | Cebu | City of Cebu | Punta Princesa | 10.2944 | 123.872 | U | 22685 | 7089 | 2127 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | LDIC_CEB_0004 | LDIC | 10.2979 | 123.8697 | 0.47 | Terrestrial Optical Fiber Drop | 1.65 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3122 | 4 | 122 | 3122 | 0402115030 | Region IV-A (CALABARZON) | Cavite | Naic | Sapa | 14.31 | 120.7717 | R | 1486 | 437 | 131 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F02229-C08 | PTCI/MIDC | 14.3227 | 120.7719 | 1.14 | Terrestrial Optical Fiber Drop | 1.3 | 0.08 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3123 | 4 | 123 | 3123 | 0301423007 | Region III (Central Luzon) | Bulacan | Santa Maria | Cay Pombo | 14.8523 | 120.9779 | U | 34153 | 9758 | 2927 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-02583 | Edgepoint | 14.8531 | 120.9756 | 0.27 | Terrestrial Optical Fiber Drop | 2.32 | 0.5 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3124 | 4 | 124 | 3124 | 0405811010 | Region IV-A (CALABARZON) | Rizal | San Mateo | Santa Ana | 14.6963 | 121.116 | U | 10398 | 2888 | 866 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-RIZ-01354 | Edgepoint | 14.6926 | 121.1157 | 0.42 | Terrestrial Optical Fiber Drop | 1.05 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3125 | 4 | 125 | 3125 | 0604532007 | Region VI (Western Visayas) | Negros Occidental | Salvador Benedicto | Pinowayan | 10.5713 | 123.2182 | R | 2812 | 760 | 228 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH060364 | FTAP Globe | 10.5112 | 123.2785 | 9.39 | Terrestrial Optical Fiber Drop | 2.27 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3126 | 4 | 126 | 3126 | 0305407012 | Region III (Central Luzon) | Pampanga | Guagua | San Agustin | 14.9929 | 120.6234 | U | 7282 | 1820 | 546 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAM-00955 | Edgepoint | 14.9916 | 120.6305 | 0.78 | Terrestrial Optical Fiber Drop | 2.31 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3127 | 4 | 127 | 3127 | 0102812030 | Region I (Ilocos Region) | Ilocos Norte | City of Laoag | Bgy. No. 32-A, La Paz East | 18.205 | 120.5316 | R | 1416 | 382 | 115 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01209-B05 | PTCI/MIDC | 18.2087 | 120.5983 | 0.38 | Terrestrial Optical Fiber Drop | 5.7 | 5.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3128 | 4 | 128 | 3128 | 0301403020 | Region III (Central Luzon) | Bulacan | Baliuag | Santo Cristo | 14.9564 | 120.8967 | U | 10035 | 2867 | 860 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | N1598 | FTAP Smart | 14.9544 | 120.894 | 0.37 | Terrestrial Optical Fiber Drop | 1.33 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3129 | 4 | 129 | 3129 | 0501724032 | Region V (Bicol Region) | Camarines Sur | City of Naga | Triangulo | 13.6195 | 123.1959 | U | 8681 | 2066 | 620 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCSG0029 | PTCI/MIDC | 13.6169 | 123.1988 | 0.42 | Terrestrial Optical Fiber Drop | 1.1 | 0.94 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3130 | 4 | 130 | 3130 | 0403415003 | Region IV-A (CALABARZON) | Laguna | Magdalena | Munting Ambling | 14.2022 | 121.4289 | R | 1834 | 555 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02112-C08 | PTCI/MIDC | 14.2011 | 121.4276 | 0.74 | Terrestrial Optical Fiber Drop | 0.46 | 0.1 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3131 | 4 | 131 | 3131 | 0304932004 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Concepcion | 15.4445 | 120.7995 | U | 6502 | 1857 | 557 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01494-B07 | PTCI/MIDC | 15.4479 | 120.7996 | 0.37 | Terrestrial Optical Fiber Drop | 1.29 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3132 | 4 | 132 | 3132 | 0730600040 | Region VII (Central Visayas) | Cebu | City of Cebu | Labangon | 10.3 | 123.8817 | U | 32865 | 10270 | 3081 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCER0027 | PTCI/MIDC | 10.294 | 123.8817 | 0.67 | Terrestrial Optical Fiber Drop | 1.91 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3133 | 4 | 133 | 3133 | 1102319016 | Region XI (Davao Region) | Davao del Norte | City of Tagum | Magugpo Poblacion | 7.4476 | 125.8017 | U | 2994 | 809 | 243 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDNG0124 | PTCI/MIDC | 7.4318 | 125.8027 | 0.31 | Terrestrial Optical Fiber Drop | 2.51 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3134 | 4 | 134 | 3134 | 0403411015 | Region IV-A (CALABARZON) | Laguna | Los Baños | Malinta | 14.1859 | 121.2301 | U | 7159 | 2169 | 651 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F02047-C08 | PTCI/MIDC | 14.1865 | 121.2336 | 0.38 | Terrestrial Optical Fiber Drop | 1.52 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3135 | 4 | 135 | 3135 | 0402120043 | Region IV-A (CALABARZON) | Cavite | Tanza | Paradahan II | 14.3248 | 120.8592 | R | 5133 | 1509 | 453 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH040169 | FTAP Globe | 14.3237 | 120.8601 | 0.15 | Terrestrial Optical Fiber Drop | 4.82 | 0.51 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3136 | 4 | 136 | 3136 | 1003522004 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | Bulod | 8.0479 | 123.811 | R | 2342 | 557 | 167 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 2.2 | Terrestrial Optical Fiber Drop | 1.41 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3137 | 4 | 137 | 3137 | 0105546003 | Region I (Ilocos Region) | Pangasinan | City of Urdaneta | Bactad East | 15.9768 | 120.6195 | R | 2192 | 608 | 182 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PTPNG0006 | PTCI/MIDC | 15.9738 | 120.5695 | 0.46 | Terrestrial Optical Fiber Drop | 5.18 | 5.13 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3138 | 4 | 138 | 3138 | 1600201015 | Region XIII (Caraga) | Agusan del Norte | Buenavista | Poblacion 3 | 8.9751 | 125.4078 | U | 3797 | 926 | 278 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTASG0002 | PTCI/MIDC | 8.9795 | 125.4097 | 0.53 | Terrestrial Optical Fiber Drop | 1.14 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3139 | 4 | 139 | 3139 | 0301410051 | Region III (Central Luzon) | Bulacan | City of Malolos | Santor | 14.8391 | 120.8136 | U | 8937 | 2553 | 766 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01114 | Edgepoint | 14.8539 | 120.8364 | 0.77 | Terrestrial Optical Fiber Drop | 0.19 | 1.42 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3140 | 4 | 140 | 3140 | 0405630018 | Region IV-A (CALABARZON) | Quezon | Pagbilao | Pinagbayanan | 13.9713 | 121.6912 | R | 4405 | 1159 | 348 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E03053-C10 | PTCI/MIDC | 13.978 | 121.686 | 2.85 | Terrestrial Optical Fiber Drop | 0.99 | 0.21 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3141 | 4 | 141 | 3141 | 1003522019 | Region X (Northern Mindanao) | Lanao del Norte | Tubod | Poblacion | 8.0513 | 123.7939 | U | 11654 | 2774 | 832 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNG0046 | PTCI/MIDC | 8.0447 | 123.7913 | 0.79 | Terrestrial Optical Fiber Drop | 1.1 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3142 | 4 | 142 | 3142 | 1606724096 | Region XIII (Caraga) | Surigao del Norte | City of Surigao | Canlanipa | 9.7762 | 125.4951 | U | 12311 | 3002 | 901 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTSNG0015 | PTCI/MIDC | 9.7735 | 125.496 | 0.32 | Terrestrial Optical Fiber Drop | 1.32 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3143 | 4 | 143 | 3143 | 0201511008 | Region II (Cagayan Valley) | Cagayan | Claveria | Centro I | 18.6069 | 121.0789 | R | 1835 | 470 | 141 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | F01189-B05 | PTCI/MIDC | 18.6025 | 121.0861 | 0.9 | Terrestrial Optical Fiber Drop | 1.06 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3144 | 4 | 144 | 3144 | 0731300014 | Region VII (Central Visayas) | Cebu | City of Mandaue | Jagobiao | 10.3647 | 123.9561 | U | 12150 | 3471 | 1041 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTCEG0121 | PTCI/MIDC | 10.3645 | 123.9514 | 0.51 | Terrestrial Optical Fiber Drop | 1.35 | 0.52 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3145 | 4 | 145 | 3145 | 0306909015 | Region III (Central Luzon) | Tarlac | Moncada | Camposanto 2 | 15.7345 | 120.5682 | R | 2192 | 562 | 169 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.6 | Terrestrial Optical Fiber Drop | 1.46 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3146 | 4 | 146 | 3146 | 0301417018 | Region III (Central Luzon) | Bulacan | Plaridel | Santa Ines | 14.8842 | 120.8595 | U | 3054 | 872 | 262 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02950-B07 | PTCI/MIDC | 14.8952 | 120.852 | 0.66 | Terrestrial Optical Fiber Drop | 2.23 | 0.05 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3147 | 4 | 147 | 3147 | 0403428015 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Kanluran | 14.3024 | 121.1094 | U | 4643 | 1406 | 422 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0029 | PTCI/MIDC | 14.2926 | 121.0962 | 0.34 | Terrestrial Optical Fiber Drop | 0.62 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3148 | 4 | 148 | 3148 | 0105519005 | Region I (Ilocos Region) | Pangasinan | Dasol | Gais-Guipe | 15.9789 | 119.8692 | R | 2646 | 735 | 221 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01738-B07 | PTCI/MIDC | 15.9818 | 119.8707 | 0.36 | Terrestrial Optical Fiber Drop | 1.35 | 0.57 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3149 | 4 | 149 | 3149 | 1004312015 | Region X (Northern Mindanao) | Misamis Oriental | Kinoguitan | Sumalag | 8.9776 | 124.7854 | R | 1056 | 270 | 81 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH100107 | FTAP Globe | 8.9798 | 124.7941 | 0.99 | Terrestrial Optical Fiber Drop | 1.08 | 0.84 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3150 | 4 | 150 | 3150 | 0331400003 | Region III (Central Luzon) | Zambales | City of Olongapo | Barretto | 14.8564 | 120.2706 | U | 22178 | 5994 | 1798 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH030584 | FTAP Globe | 14.8444 | 120.293 | 0.64 | Terrestrial Optical Fiber Drop | 1.12 | 0.98 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3151 | 4 | 151 | 3151 | 1102403005 | Region XI (Davao Region) | Davao del Sur | City of Digos | Cogon | 6.7589 | 125.3694 | U | 10000 | 2941 | 882 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTDSG0112 | PTCI/MIDC | 6.7584 | 125.3731 | 0.41 | Terrestrial Optical Fiber Drop | 1.54 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3152 | 4 | 152 | 3152 | 0301410014 | Region III (Central Luzon) | Bulacan | City of Malolos | Dakila | 14.8506 | 120.8354 | U | 7114 | 2032 | 610 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PH-BUL-01114 | Edgepoint | 14.8539 | 120.8364 | 0.38 | Terrestrial Optical Fiber Drop | 2 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3153 | 4 | 153 | 3153 | 0401003005 | Region IV-A (CALABARZON) | Batangas | Balayan | Barangay 11 | 13.9343 | 120.7328 | R | 1479 | 410 | 123 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01973-C08 | PTCI/MIDC | 13.9355 | 120.7354 | 0.32 | Terrestrial Optical Fiber Drop | 1.14 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3154 | 4 | 154 | 3154 | 0501734014 | Region V (Bicol Region) | Camarines Sur | Sipocot | Calagbangan | 13.8372 | 122.9634 | R | 3860 | 919 | 276 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH-CAS-03084 | Edgepoint | 13.8681 | 122.9482 | 3.8 | Terrestrial Optical Fiber Drop | 2.29 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3155 | 4 | 155 | 3155 | 0105510021 | Region I (Ilocos Region) | Pangasinan | Bautista | Baluyot | 15.8011 | 120.4637 | R | 3735 | 1037 | 311 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-PAN-00572 | Edgepoint | 15.8049 | 120.457 | 0.83 | Terrestrial Optical Fiber Drop | 1.93 | 0.69 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3156 | 4 | 156 | 3156 | 0330100021 | Region III (Central Luzon) | Pampanga | City of Angeles | Pulung Cacutud | 15.1709 | 120.6152 | U | 26510 | 7363 | 2209 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02946-B07 | PTCI/MIDC | 15.1703 | 120.6123 | 0.32 | Terrestrial Optical Fiber Drop | 1.1 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3157 | 4 | 157 | 3157 | 1606701007 | Region XIII (Caraga) | Surigao del Norte | Alegria | San Pedro | 9.4799 | 125.574 | R | 2576 | 628 | 188 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | PH130042 | FTAP BTS | 9.4963 | 125.5809 | 1.97 | Terrestrial Optical Fiber Drop | 2.49 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3158 | 4 | 158 | 3158 | 1003520004 | Region X (Northern Mindanao) | Lanao del Norte | Tagoloan | Inagongan | 8.1031 | 124.2445 | R | 3770 | 897 | 269 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PH100189 | FTAP Globe | 8.0656 | 124.2637 | 4.67 | Terrestrial Optical Fiber Drop | 10.86 | 0.82 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3159 | 4 | 159 | 3159 | 0405814007 | Region IV-A (CALABARZON) | Rizal | Teresa | Prinza | 14.5363 | 121.2172 | U | 7180 | 1994 | 598 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | E02990-A04 | PTCI/MIDC | 14.5352 | 121.2159 | 0.19 | Terrestrial Optical Fiber Drop | 1.81 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3160 | 4 | 160 | 3160 | 1030900031 | Region X (Northern Mindanao) | Lanao del Norte | City of Iligan | Bagong Silang | 8.2393 | 124.2549 | U | 6188 | 1628 | 488 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTLNR0010 | PTCI/MIDC | 8.2442 | 124.2545 | 0.54 | Terrestrial Optical Fiber Drop | 2 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3161 | 4 | 161 | 3161 | 0405647037 | Region IV-A (CALABARZON) | Quezon | City of Tayabas | Lalo | 14.0406 | 121.5712 | R | 4149 | 1091 | 327 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T3: Survey Tower Candidate (1.0-2.0 km) | F02129-C08 | PTCI/MIDC | 14.0285 | 121.5816 | 1.75 | Terrestrial Optical Fiber Drop | 3.05 | 0.53 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3162 | 4 | 162 | 3162 | 0300808005 | Region III (Central Luzon) | Bataan | Morong | Sabang | 14.6912 | 120.2504 | U | 8389 | 2330 | 699 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PTBNG0020 | PTCI/MIDC | 14.6958 | 120.2519 | 0.53 | Terrestrial Optical Fiber Drop | 2.41 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3163 | 4 | 163 | 3163 | 0306909016 | Region III (Central Luzon) | Tarlac | Moncada | Capaoayan | 15.7304 | 120.5669 | R | 3371 | 864 | 259 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH-TAR-00588 | Edgepoint | 15.7353 | 120.5737 | 0.91 | Terrestrial Optical Fiber Drop | 1.13 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3164 | 4 | 164 | 3164 | 0300807016 | Region III (Central Luzon) | Bataan | Mariveles | Ipag | 14.4298 | 120.4782 | U | 12016 | 3337 | 1001 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTBNG0003 | PTCI/MIDC | 14.4309 | 120.4797 | 0.2 | Terrestrial Optical Fiber Drop | 1.17 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3165 | 4 | 165 | 3165 | 0803703012 | Region VIII (Eastern Visayas) | Leyte | Albuera | San Pedro | 10.9128 | 124.7055 | R | 4072 | 1071 | 321 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH080134 | FTAP BTS | 10.9117 | 124.6992 | 0.7 | Terrestrial Optical Fiber Drop | 1.96 | 0.63 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3166 | 4 | 166 | 3166 | 0301403006 | Region III (Central Luzon) | Bulacan | Baliuag | Hinukay | 15.0125 | 120.8815 | R | 2327 | 664 | 199 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | E02444-B07 | PTCI/MIDC | 15.0175 | 120.8885 | 0.94 | Terrestrial Optical Fiber Drop | 1.2 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3167 | 4 | 167 | 3167 | 0702251014 | Region VII (Central Visayas) | Cebu | City of Toledo | Carmen | 10.3923 | 123.6635 | R | 4967 | 1307 | 392 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTCEG0173 | PTCI/MIDC | 10.394 | 123.66 | 0.43 | Terrestrial Optical Fiber Drop | 1.13 | 0.58 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3168 | 4 | 168 | 3168 | 0304932026 | Region III (Central Luzon) | Nueva Ecija | Zaragoza | Santo Rosario Old | 15.4407 | 120.7792 | R | 3933 | 1123 | 337 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | F01419-B07 | PTCI/MIDC | 15.4394 | 120.779 | 0.15 | Terrestrial Optical Fiber Drop | 1.68 | 0.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3169 | 4 | 169 | 3169 | 0630200058 | Region VI (Western Visayas) | Negros Occidental | City of Bacolod | Tangub | 10.6336 | 122.9344 | U | 46530 | 12925 | 3878 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T2: Close Tower Candidate (0.5-1.0 km) | PH060350 | FTAP Globe | 10.6355 | 122.9397 | 0.62 | Terrestrial Optical Fiber Drop | 2.15 | 0.54 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3170 | 4 | 170 | 3170 | 1108204017 | Region XI (Davao Region) | Davao de Oro | Maco | Lumatab | 7.4278 | 125.9081 | R | 1379 | 372 | 112 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Greenfield Monopole (New Build) | Class T4: Preliminary Greenfield (>2.0 km) | PTCVG0004 | PTCI/MIDC | 7.3576 | 125.8639 | 1.66 | Terrestrial Optical Fiber Drop | 9.78 | 7.55 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)
FWA-SITE-3171 | 4 | 171 | 3171 | 0403428023 | Region IV-A (CALABARZON) | Laguna | City of Santa Rosa | Tagapo | 14.3189 | 121.1032 | U | 46153 | 13985 | 4196 | Band n50 (1.5 GHz, 60 MHz TDD) | 1 | Co-location (Existing Tower) | Class T1: Immediate Tower Candidate (<=0.5 km) | PTLAG0019 | PTCI/MIDC | 14.3211 | 121.1055 | 0.35 | Terrestrial Optical Fiber Drop | 2.16 | 0.56 | Commercial 220V Grid + 4h LiFePO4 ESS (>=19.0 kWh)